## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Nalbithi Madhabpur and adjoining Mouzas water supply scheme , SM/06723 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Nalbithi Madhabpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | 1238/RD/PHE | 16/10/2020 | 40 | M/S LOKENATH CONST | 91.32 | 0 | 0 | 0
2 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Nalbithi Madhabpur and adjoining Mouzas water supply scheme , SM/06723 | Retrofitting | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C, Vehicle No. WB 59D 1337) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Months (Period from 15.07.2024 upto 14.01.2025). | 2159/RD/PHE | 15/07/2024 | 184 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 2.4 | 0 | 0 | 0
3 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Nalbithi Madhabpur and adjoining Mouzas water supply scheme , SM/06723 | Retrofitting | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 15.01.2025 to 14.07.2025 | 296/RD/PHE | 15/01/2025 | 181 | DEBASISH GHOSH | 2.4 | 0 | 0 | 0
4 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Barobila and adjoining Mouzas water supply scheme , SM/06726 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Barabilla and adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | 1241/RD/PHE | 16/10/2020 | 40 | BHOLA PAUL | 62.49 | 23.59 | 37.74 | 0
5 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Barobila and adjoining Mouzas water supply scheme , SM/06726 | Retrofitting | FHTC OF BARABILLA PWSS | 1505/RD/PHE | 23/12/2020 | 30 | M/S LUCKY CONSTRUCTION | 11.66 | 0 | 0 | 0
6 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Barobila and adjoining Mouzas water supply scheme , SM/06726 | Retrofitting | OFFICE ACCESSORIES BILL | 767/W | 11/03/2022 | 0 | DIGITEK SOLUTIONS | 0.1 | 0 | 0 | 0
7 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Barobila and adjoining Mouzas water supply scheme , SM/06726 | Retrofitting | OFFICE ACCESSORIES BILL | 771/W | 11/03/2022 | 0 | M/S DUTTA ENTERPRISE | 0.07 | 0 | 0 | 0
8 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Kotar for installation of FHTC. , SM/09169 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of KOTAR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2122/RD/PHE | 03/11/2021 | 30 | APEX ENTERPRISES | 8.31 | 0 | 0 | 1
9 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kunore and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. , SM/09172 | Retrofitting | Route Survey & Preparation of DPR of KUNORE PWSS under Raiganj Division, PHE Dte. | 156/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 4.14 | 0 | 0 | 0
10 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kunore and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. , SM/09172 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Kunore Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Kaliaganj Block under Raiganj Division, P.H.E. Dte. | 2072/RD/PHE | 02/11/2021 | 30 | M/S BHOWMIK ENTERPRISE | 8.79 | 0 | 0 | 1
11 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kunore and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. , SM/09172 | Retrofitting | Material Requisition To Resource Division | 28/RD/PHE | 06/01/2022 | 0 | Resource Division | 2.06 | 0 | 0 | 0
12 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kunore and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. , SM/09172 | Retrofitting | Material Requisition To Resource Division | 1802/RD/PHE | 23/09/2022 | 0 | Resource Division | 2.31 | 0 | 0 | 0
13 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. , SM/09182 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Chopra Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Chopra Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1829/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.7 | 3.7 | 100 | 0
14 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. , SM/09182 | Retrofitting | Retrofitting Of Functional Household Tap Connections(FHTC) under Chopra Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Chopra Block under Raiganj Division, P.H.E Dte. | 486/RD/PHE | 25/02/2022 | 30 | M/S LUCKY CONSTRUCTION | 11.46 | 0 | 0 | 0
15 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. , SM/09182 | Retrofitting | Preparation of 70 Nos. deeds and arrangement of Registration of Land for implementation of different Piped Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E., Dte. | 598/RD/PHE | 11/03/2022 | 60 | ASHIM CHANDA | 2.45 | 0 | 0 | 1
16 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. , SM/09182 | Retrofitting | Preparation of 70 Nos. deeds and arrangement of Registration of Land for implementation of different Piped Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 992/RD/PHED | 05/05/2022 | 60 | ASHIM CHANDA | 2.45 | 0 | 0 | 1
17 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. , SM/09182 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Chopra Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Chopra Block under Raiganj Division, P.H.E. Dte. | 2082/RD/PHE | 02/11/2021 | 30 | M/S LUCKY CONSTRUCTION | 18.64 | 0 | 0 | 1
18 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. , SM/09182 | Retrofitting | Material Requisition To Resource Division | 42/RD/PHE | 06/01/2022 | 0 | Resource Division | 0.29 | 0 | 0 | 0
19 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. , SM/09182 | Retrofitting | Material Requisition To Resource Division | 1815/RD/PHE | 26/09/2022 | 0 | Resource Division | 3.26 | 0 | 0 | 0
20 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chopra and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. , SM/09182 | Retrofitting | Allied works in connection with retrofitting of FHTC in Chopra PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1041/RD/PHE | 02/04/2025 | 60 | ASHIM CHANDA | 0.49 | 0 | 0 | 0
21 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sitlagaon and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. , SM/09193 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Sitlagaon Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Chopra Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1813/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.87 | 2.85 | 100 | 0
22 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sitlagaon and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. , SM/09193 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Sitlagaon Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Chopra Block under Raiganj Division, P.H.E. Dte. | 2381/RD/PHE | 24/12/2021 | 30 | M/S LUCKY CONSTRUCTION | 9.24 | 0 | 0 | 0
23 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sitlagaon and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. , SM/09193 | Retrofitting | Preparation of 70 Nos. deeds and arrangement of Registration of Land for implementation of different Piped Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E., Dte. | 553/RD/PHE | 04/03/2022 | 60 | ASHIM CHANDA | 2.45 | 0 | 0 | 1
24 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sitlagaon and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. , SM/09193 | Retrofitting | Material Requisition To Resource Division | 41/RD/PHE | 06/01/2022 | 0 | Resource Division | 1.9 | 0 | 0 | 0
25 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sitlagaon and adjoining mouzas Water Supply Scheme In Chopra Block Under Raiganj Division, P. H. E. Dte. , SM/09193 | Retrofitting | Material Requisition To Resource Division | 1816/RD/PHE | 28/09/2022 | 0 | Resource Division | 1.23 | 0 | 0 | 0
26 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Poaltair WSS for installation of FHTC. , SM/09144 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of POALTAIR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2104/RD/PHE | 03/11/2021 | 30 | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 15.91 | 0 | 0 | 1
27 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Choprabari WSS for installation of FHTC. , SM/09134 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Choprabari Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2150/RD/PHE | 12/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 1.38 | 0 | 0 | 1
28 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Baruna WSS for installation of FHTC. , SM/09142 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of BARUNA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2102/RD/PHE | 03/11/2021 | 30 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CAST SOCIETY LTD. | 5.16 | 0 | 0 | 1
29 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Bamair WSS for installation of FHTC. , SM/09143 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of BAMAIR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2103/RD/PHE | 03/11/2021 | 30 | SANKAR DAS | 8.81 | 0 | 0 | 1
30 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Phulatti WSS for installation of FHTC. , SM/09146 | Retrofitting | Laying of Additional Pipe Line for Retrofitting ofF PHULATTI Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2105/RD/PHE | 03/11/2021 | 30 | RAHUL ENTERPRISE | 6.57 | 0 | 0 | 1
31 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Chotparua WSS for installation of FHTC. , SM/09148 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of CHOTPARUA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2107/RD/PHE | 03/11/2021 | 30 | NIMAI DAS | 9.36 | 0 | 0 | 1
32 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Chandanpur WSS for installation of FHTC (Part-A & B). , SM/09111 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Chandanpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | 2137/RD/PHE | 12/11/2021 | 30 | UTTAM SAHA | 3.94 | 0 | 0 | 1
33 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Chandanpur WSS for installation of FHTC (Part-A & B). , SM/09111 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Chandanpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | 2136/RD/PHE | 12/11/2021 | 30 | UTTAM SAHA | 3.94 | 0 | 0 | 1
34 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Chandanpur WSS for installation of FHTC (Part-A & B). , SM/09111 | Retrofitting | office accessories bill | BP-2022-23-29 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.06 | 0 | 0 | 0
35 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Chandanpur WSS for installation of FHTC (Part-A & B). , SM/09111 | Retrofitting | Preliminary Route Survey for finding feasibility of providing FHTC in different PWSS (Which excluded design year) Preparation of DPR of No.1. Goalpukhur PWSS 2. Lakhipur PWSS 3. Khanta PWSS 4. Hemtabad PWSS 5. Dharampur PWSS Zone-II under Raiganj Division, P.H.E. Dte. | 896/RD/PHED | 20/04/2022 | 7 | M/S DUTTA ENTERPRISE | 4.46 | 0 | 0 | 100
36 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Deona (Part-A & B) for installation of FHTC. , SM/09121 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Deona Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | 2143/RD/PHE | 12/11/2021 | 30 | SWAGATA | 4.42 | 0 | 0 | 1
37 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Deona (Part-A & B) for installation of FHTC. , SM/09121 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Deona Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | 2192/RD/PHE | 17/11/2021 | 30 | HAQUE CONSTRUCTION | 6.19 | 0 | 0 | 0
38 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Gunabari for installation of FHTC. , SM/09124 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Gunabari Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2194/RD/PHE | 17/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 6.52 | 0 | 0 | 0
39 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at under Baruna and adjoining Mouza Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | 1527/RD/PHE | 23/12/2020 | 45 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 104.88 | 0 | 0 | 0
40 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS(FHTC) UNDER PAHARAJPUR AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN ITAHAR BLOCK IN UNDER RAIGANJ DIVISION. | 1560/RD/PHE | 24/12/2020 | 60 | J.D.J. ENTERPRISE | 133.31 | 0 | 0 | 0
41 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Gutin and adjoining Mouzas Water Supply Scheme in Hemtabad Block under Raiganj Division, P.H.E. Dte. | 1528/RD/PHE | 23/12/2020 | 45 | M/S LOKENATH CONST | 101.7 | 0 | 0 | 0
42 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kaliganj and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | 1544/RD/PHE | 23/12/2020 | 40 | NEOGI ENTERPRISE | 98.37 | 0 | 0 | 0
43 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Phulatti and adjoining mouzas Water Supply Scheme in Kaliaganj Block in under Raiganj Division.(Part-III) | 476/RD/PHE | 26/02/2021 | 45 | SUBHAS CHOWDHURY | 4.1 | 0 | 0 | 0
44 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Supplying, laying, fitting, fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete (1:2:4) in connection with Retrofitting of Functional Household Tap Connections(FHTC) under Pokheria and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | 374/RD/PHE | 05/02/2021 | 25 | SARNALI ENTERPRISE | 3.36 | 0 | 0 | 1
45 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Sridharpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | 1526/RD/PHE | 23/12/2020 | 45 | AJIT PARMANIK | 126.43 | 0 | 0 | 0
46 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Deona and adjoining Mouzas Water Supply Scheme in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. | 1542/RD/PHE | 23/12/2020 | 40 | MAMATA USHA ENTERPRISE | 94.51 | 0 | 0 | 0
47 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Sherpur Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Raiganj,Capacity- 90 M3/hr. | 1208/RD/PHE | 18/06/2021 | 90 | M/S LOKENATH CONSTRUCTION | 37.36 | 0 | 0 | 0
48 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Bindol and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E. Dte. | 1529/RD/PHE | 23/12/2020 | 45 | AJIT PARMANIK | 125.64 | 0 | 0 | 0
49 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS(FHTC) UNDER BHAGABATI AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN CHOPRA BLOCK IN UNDER RAIGANJ DIVISION. | 1564/RD/PHE | 24/12/2020 | 60 | M/S LOKENATH CONSTRUCTION | 194.09 | 0 | 0 | 0
50 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | SUPPLYING LAYING FITTING FIXING OF FHTC OF JAINGAON PWSS | 1498/RD | 23/12/2020 | 25 | DULAL MAJUMDER | 3.82 | 0 | 0 | 0
51 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | SUPPLYING FITTING UPVC PIPE FOR KALIGANJ PWSS | 1503/RD | 23/12/2020 | 25 | ALI ENTERPRISE | 2.75 | 0 | 0 | 0
52 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | SUPPLYING LAYING FITTING FIXING OF FHTC OF GUNABARI PWSS | 1499/RD | 23/12/2020 | 25 | M/S GHOSH CONSTRUCTION | 2.5 | 0 | 0 | 0
53 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | SUPPLYING LAYING FITTING FIXING AND JOINTING UPVC PIPE INCLUDING DISMANTLING PCC FHTC OF BAMAIR PWSS | 1508/RD/PHE | 23/12/2020 | 30 | RURAL DEVELOPMENT CO-OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 8.91 | 0 | 0 | 0
54 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | SUPPLYING LAYING FITTING FIXING AND JOINTING OF UPVC PIPE INCLUDING DISMANTLING PCC OF FHTC OF DEONA PWSS | 1507/RD | 23/12/2020 | 30 | M/S LUCKY CONSTRUCTION | 11.66 | 0 | 0 | 0
55 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | supply, laying, fitting , fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete (1;2:4) for FHTC under Bhagabati and adjoining mouzas water supply scheme in chopra block under Raiganj Division, P.h.e.dte. | 1509/RD/PHE | 23/12/2020 | 30 | PRINCE BUILDERS | 8.31 | 0 | 0 | 0
56 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Supplying, laying, fitting, fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete (1:2:4) in connection with Retrofitting of Functional Household Tap Connections(FHTC) under Sridharpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | 375/RD/PHE | 05/02/2021 | 25 | GOPES SAHA | 3.33 | 0 | 0 | 1
57 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | SUPPLYING LAYING FITTING FIXING AND JOINTING UPVC PIPE INCLUDING DISMANTLING PCC FHTC OF GUTIN PWSS | 1514/RD | 23/12/2020 | 30 | M/S.BANGARAJ | 9.92 | 0 | 0 | 0
58 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | office accessories bill | BP-2022-23-36 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.13 | 0 | 0 | 0
59 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | office accessories bill | BP-2022-23-28 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
60 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | hire charge of vehicle | BP-2022-23-137 | 12/09/2022 | 0 | DIGENDRANATH DAS | 0.04 | 0 | 0 | 0
61 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Supply of urgent office article against laying of additional pipeline Siripur | BP-2022-23-158 | 28/09/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
62 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Supply of urgent office article against laying of additional pipeline Siripur | BP-2022-23-159 | 28/09/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
63 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | office accessories bill | BP-2022-23-26 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.09 | 0 | 0 | 0
64 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Tungail Bilpara and adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | 1524/RD/PHE | 23/12/2020 | 45 | SANYAL ENTERPRISE | 110.26 | 0 | 0 | 0
65 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Sitgram and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E. Dte. | 1537/RD/PHE | 23/12/2020 | 45 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 103.65 | 0 | 0 | 15
66 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Jaingaon for installation of FHTC under Raiganj Division P.H.E. Dte. | 2196/RD/PHE | 17/11/2021 | 30 | M/S SARKAR ENTERPRISE | 44.62 | 0 | 0 | 0
67 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Laying of Additional Pipe Line for improving FHTC nos. of Jaingaon Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | 2256/RD/PHE | 22/12/2022 | 30 | APEX ENTERPRISES RUPESH.RNJ@GMAIL.COM | 5.75 | 0 | 0 | 0
68 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Laying of Additional Pipe Line for Providing Functional Household Tap Connection for Sridharpur(Paharajpur) Water Supply Scheme under Itahar Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | 500/RD/PHE | 17/02/2023 | 45 | SANDIP SARKAR | 7.18 | 0 | 0 | 0
69 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Supplying, Laying, Fixing and Jointing of UPVC Pipe including Dismantling PCC & Ordinary Cement Concrete [1:2:4] in connection with retrofitting of FHTC under TUNGAIL BILLPARA & Adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division ,P.H.E Dte. | 475/RD/PHE | 26/02/2021 | 30 | M/S.SADHANA ENTERPRISE | 6.36 | 0 | 0 | 0
70 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Restoration of damaged Pipe Line work required for FHTC work at Dakshin Jibakata Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | 2428/RD/PHE | 31/12/2021 | 30 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 4.87 | 0 | 0 | 100
71 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Providing Functional House Hold Connection (FHTC) for the purpose of Bheur Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 493/RD/PHE | 17/02/2023 | 45 | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 6.22 | 0 | 0 | 0
72 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Gopalpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | 1533/RD/PHE | 23/12/2020 | 45 | M/S LOKENATH CONST | 110.89 | 0 | 0 | 0
73 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Bamair and adjoining Mouzas Water Supply Scheme in Hemtabad Block under Raiganj Division, P.H.E. Dte. | 1531/RD/PHE | 23/12/2020 | 45 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 116.81 | 0 | 0 | 0
74 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Gunabari and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | 1534 /RD/PHE | 23/12/2020 | 45 | M/S LOKENATH CONSTRUCTION | 122.2 | 0 | 0 | 0
75 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Mahinagar and adjoining Mouzas Water Supply Scheme in Kaliaganj Block under Raiganj Division, P.H.E. Dte. | 1543/RD/PHE | 23/12/2020 | 40 | SANYAL ENTERPRISE | 96.95 | 0 | 0 | 0
76 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Puria and adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | 362/RD/PHE | 04/02/2021 | 40 | UTTAM SAHA | 91.12 | 0 | 0 | 1
77 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | FHTC OF MAHINAGAR WSS | 1504/RD | 23/12/2020 | 25 | M/S ARVI CONSTRUCTION | 3.06 | 0 | 0 | 0
78 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Pokheria and adjoining Mouzas Water Supply Scheme in Goalpoklher-I Block under Raiganj Division, P.H.E. Dte. | 1530/RD/PHE | 23/12/2020 | 45 | AJIT PARMANIK | 134.73 | 0 | 0 | 50
79 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Poaltair and adjoining Mouzas water supply scheme in Hemtabad Block under Raiganj Division, P.H.E. Dte. | 1539/RD/PHE | 23/12/2020 | 45 | SANYAL ENTERPRISE | 106.28 | 0 | 0 | 0
80 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | FHTC OF GOPALPUR WSS | 1502/RD | 23/12/2020 | 25 | KARTICK BISWAS | 1.8 | 0 | 0 | 0
81 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Dakhin Jibakata and adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | 1540/RD/PHE | 23/12/2020 | 45 | CALCON CONSTRUCTION | 126.63 | 0 | 0 | 100
82 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at under Bheur and adjoining Mouza Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | 1557/RD/PHE | 24/12/2020 | 60 | UTTAM SAHA | 124.33 | 0 | 0 | 100
83 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 19 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07390 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Jaingaon and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | 1538/RD/PHE | 23/12/2020 | 45 | M/S SOMNATH KUNDU | 104.31 | 0 | 0 | 90
84 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Faridpur Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12640 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Faridpur Piped Water Supply Scheme of Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1915/RD/PHE | 28/10/2022 | 901 | M/S P.S. ENTERPRISE | 39.95 | 0 | 0 | 70
85 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Faridpur Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12640 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Source Augmentation of Faridpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015281) | 2496/MLMD | 04/08/2023 | 120 | BANIK BROTHERS | 10.47 | 0 | 0 | 100
86 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Faridpur Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12640 | Augmentation | Material Requisition To Resource Division | 16/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
87 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Faridpur Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12640 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Faridpur, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-218 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 6.76 | 0 | 0 | 0
88 | UTTAR DINAJPUR | Raiganj Division | BARA DOPAHARU Piped Water Supply Scheme , SM/12396 | New | Material Requisition To Resource Division | 1036/RD/PHE | 04/04/2023 | 0 | Resource Division | 25.91 | 0 | 0 | 0
89 | UTTAR DINAJPUR | Malda Mechanical | BARA DOPAHARU Piped Water Supply Scheme , SM/12396 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bara Dopaharu Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014803) | 2478/MLMD | 04/08/2023 | 922 | ANIMA ENTERPRISE | 28.34 | 0 | 0 | 74
90 | UTTAR DINAJPUR | Malda Mechanical | BARA DOPAHARU Piped Water Supply Scheme , SM/12396 | New | Quotation for new service connection at BARA DOPAHARU PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12396) | BP-2024-25-307 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 18.64 | 0 | 0 | 0
91 | UTTAR DINAJPUR | Raiganj Division | BARA DOPAHARU Piped Water Supply Scheme , SM/12396 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
92 | UTTAR DINAJPUR | Raiganj Division | BARA DOPAHARU Piped Water Supply Scheme , SM/12396 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bara Dopaharu Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | 1978/RD/PHE | 03/07/2025 | 180 | MONDAL PRECISION PRIVATE LIMITED | 18.74 | 0 | 0 | 0
93 | UTTAR DINAJPUR | Raiganj Division | BARA DOPAHARU Piped Water Supply Scheme , SM/12396 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at BARA DOPAHARU PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | 2097/RD/PHE | 15/07/2025 | 180 | M/S SACHIN KUMAR | 43.32 | 0 | 0 | 0
94 | UTTAR DINAJPUR | Raiganj Division | BARA DOPAHARU Piped Water Supply Scheme , SM/12396 | New | Providing FHTC in connection with Bara Dopaharu Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd Call) | 2174/RD/PHE | 25/07/2025 | 90 | M/S SHIB ENTERPRISE | 5.4 | 0 | 0 | 0
95 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Material Requisition To Resource Division | 1972/RD/PHE | 08/11/2022 | 0 | Resource Division | 142.48 | 0 | 0 | 0
96 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Augmentation of PANJIPARA (Zone-I)Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | 1551/RD/PHE | 26/08/2022 | 90 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 162.49 | 0 | 0 | 0
97 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Panjipara Water Supply Scheme (Zone-I) TW no II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 263/MLMD | 24/02/2023 | 90 | DIPALI CONSTRUCTION. | 11.47 | 0 | 0 | 0
98 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No.- I of Augmentation of Panjipara (Zone- I) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011666) | 2131/MLMD | 07/07/2023 | 1915 | SUBHAS CHANDRA KESHORI | 6.97 | 0 | 0 | 0
99 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Panjipara, Zone-I, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003160435 | 17/05/2023 | 365 | W.B.S.E.D.C.LTD | 19.87 | 0 | 0 | 0
100 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Panjipara Zone-I Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 374/RD/PHE | 07/02/2023 | 45 | M/S PAYEL CONSTRUCTION HIMADRI.RNJ@GMAIL.COM | 5.01 | 0 | 0 | 100
101 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | FHTC (Functional Household Tap Connection) for Panjipara Zone-I Water Supply Scheme [Augmentation Scheme] in Goalpokhar-I Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2024/RD/PHE | 17/11/2022 | 992 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 82.85 | 0 | 0 | 40
102 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Providing FHTC at Panjipara Santinagar of Panjipara Zone-I PWSS in connection with Augmentation of Panjipara Zone-I PWSS in Goalpukhur-I Block of Uttar Dinajpur under Raiganj Division PHE Dte. | 2787/RD/PHE | 11/10/2023 | 30 | NANDANIK ENGINEERS C-OPERATIVE SOCIETY LTD. | 2.87 | 0 | 0 | 100
103 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Panjipara Water Supply Scheme (Zone-I) TW no I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 771/MLMD | 26/04/2023 | 270 | MANIK CHANDRA SAHA. | 11.45 | 0 | 0 | 100
104 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
105 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Balance pipeline with dismantling of concrete road in connection with Augmentation Of Panjipara Zone-I PWSS at Goalpukhur-I Block under Raiganj Division,PHE dte. | 44/RD/PHE | 03/01/2025 | 45 | M/S J.M.M. CONSTRUCTION | 22.75 | 0 | 0 | 0
106 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Construction of Boundary Wall With Gate at Head Work Site, & 3rd Tube-Well Site under Augmentation of Panjipara PWSS at Goalpukhur-I Block under Raiganj Division, PHE dte. | 2892/RD/PHE | 25/09/2024 | 180 | HAQUE CONSTRUCTION | 26.07 | 0 | 0 | 60
107 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Laying additional pipe line with FHTC for Augmentation of Panjipara Zone-I Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division., P.H.E. Dte. | 3801/RD/PHE | 20/12/2024 | 180 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 28.73 | 0 | 0 | 0
108 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Panjipara Zone-I Water Supply Scheme (Augmentation) at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | 2509/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 32.36 | 0 | 0 | 0
109 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Repair Pump House 2nd Tube well & 3rd Tubewell Site in connection with Augmentation of Panjipara Zone-I piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | 377/RD/PHE | 07/02/2023 | 540 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 2.1 | 0 | 0 | 100
110 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Construction of Over Head Reservoir(Capacity-400 Cum) of PANJIPARA (Zone-I) Pipe Water Supply Scheme in connection with Augmentation at Goalpokher-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 734/RD/PHE | 15/03/2023 | 636 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 143.15 | 0 | 0 | 80
111 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-I in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur , SM/11800 | Augmentation | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Panjipara Zone-I Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 1031/RD/PHE | 31/03/2023 | 504 | M/S PAYEL CONSTRUCTION HIMADRI.RNJ@GMAIL.COM | 4.1 | 0 | 0 | 100
112 | UTTAR DINAJPUR | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block , SM/12094 | New | Material Requisition To Resource Division | 2180/RD/PHE | 12/12/2022 | 0 | Resource Division | 39.53 | 0 | 0 | 0
113 | UTTAR DINAJPUR | Malda Mechanical | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block , SM/12094 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of CHAK DILAL PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003202414 | 02/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.15 | 0 | 0 | 100
114 | UTTAR DINAJPUR | Malda Mechanical | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block , SM/12094 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Chak Dilal PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003202777 | 04/08/2023 | 90 | W.B.S.E.D.C.LTD | 5.89 | 0 | 0 | 100
115 | UTTAR DINAJPUR | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block , SM/12094 | New | Implementation of CHAKDILAL and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division. | 292/RD/PHE | 01/02/2023 | 1065 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 620.92 | 0 | 0 | 58
116 | UTTAR DINAJPUR | Malda Mechanical | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block , SM/12094 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chak Dilal Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012812) | 2093/MLMD | 04/07/2023 | 950 | DAS CONSTRUCTION | 25.47 | 0 | 0 | 85
117 | UTTAR DINAJPUR | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block , SM/12094 | New | Wayleave/ track crossing proposal with application ID: NFR-KIR-2024-WL-20 under Katihar Division of North East Frontier Railway in connection with Chakdilal PWSS in Kaliyaganj Block under Raiganj Division PHE Dte. | BP-2024-25-106 | 09/07/2024 | 0 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 0.12 | 0 | 0 | 0
118 | UTTAR DINAJPUR | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block , SM/12094 | New | Wayleave/ track crossing proposal with application ID: NFR-KIR-2024-WL-20 under Katihar Division of Northeast Frontier Railway in connection with Chakdilal PWSS in Kaliyaganj Block under Raiganj Division PHE Dte. | BP-2024-25-177 | 29/08/2024 | 0 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 6.81 | 0 | 0 | 0
119 | UTTAR DINAJPUR | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block , SM/12094 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chakdilal PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3737/RD/PHE | 18/12/2024 | 135 | AJIT PRAMANIK | 68.07 | 0 | 0 | 0
120 | UTTAR DINAJPUR | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block , SM/12094 | New | Trial Run For Chakdilal PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | 519/RD/PHE | 12/02/2025 | 90 | M/S P.S. ENTERPRISE | 0.88 | 0 | 0 | 0
121 | UTTAR DINAJPUR | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block , SM/12094 | New | Construction Of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAKDILAL Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 595/RD/PHE | 05/03/2024 | 148 | M/S. ROY & CO. | 11.27 | 0 | 0 | 100
122 | UTTAR DINAJPUR | Raiganj Division | CHAK DILAL Piped Water Supply Scheme at Kaliyaganj Block , SM/12094 | New | Construction Of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAKDILAL Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 580/RD/PHE | 05/03/2024 | 148 | M C CONSTRUCTION | 11.27 | 0 | 0 | 100
123 | UTTAR DINAJPUR | Malda Mechanical | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12098 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Uttar Laxmipur PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003202783 | 07/08/2023 | 90 | W.B.S.E.D.C.LTD | 5.11 | 0 | 0 | 100
124 | UTTAR DINAJPUR | Malda Mechanical | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12098 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Uttar Laxmipur PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003202768 | 08/08/2023 | 90 | W.B.S.E.D.C.LTD | 4.72 | 0 | 0 | 100
125 | UTTAR DINAJPUR | Raiganj Division | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12098 | New | Material Requisition To Resource Division | 30/RD/PHE | 06/01/2023 | 0 | Resource Division | 24.11 | 0 | 0 | 0
126 | UTTAR DINAJPUR | Malda Mechanical | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12098 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Uttar Laxmipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013025) | 1117/MLMD | 23/06/2023 | 120 | S.P. ENTERPRISE (KOLKATA) | 25.13 | 0 | 0 | 84
127 | UTTAR DINAJPUR | Raiganj Division | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12098 | New | Implementation of UTTAR LAKSHMIPUR andit's adjoining mouzas Pipe Water Supply Scheme at KALIYAGANJ BLOCK of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 69/RD/PHE | 16/01/2023 | 665 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 232.09 | 0 | 0 | 70
128 | UTTAR DINAJPUR | Raiganj Division | UTTAR LAKSHMIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12098 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
129 | UTTAR DINAJPUR | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12108 | New | Material Requisition To Resource Division | 2200/RD/PHE | 14/12/2022 | 0 | Resource Division | 28.55 | 0 | 0 | 0
130 | UTTAR DINAJPUR | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12108 | New | Implementation of ADAIR and its adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte(2nd Call). | 621/RD/PHE | 28/02/2023 | 455 | M/S SOMNATH KUNDU | 338.34 | 0 | 0 | 60
131 | UTTAR DINAJPUR | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12108 | New | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehical No. WB60T 9215) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 17.10.2024 to 14.01.2025) | 3045/RD/PHE | 04/10/2024 | 90 | ARNAB DUTTA | 1.2 | 0 | 0 | 0
132 | UTTAR DINAJPUR | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12108 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Adiar PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3755/RD/PHED | 18/12/2024 | 45 | M/S SOMNATH KUNDU | 30.08 | 0 | 0 | 0
133 | UTTAR DINAJPUR | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12108 | New | Laying distribution of rising main and Balance Pipeline for Implementation of ADIAR and its adjoining mouzas Piped Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. (Phase-1) | 2226/RD/PHE | 23/07/2024 | 60 | M/S SOMNATH KUNDU | 32.67 | 0 | 0 | 63
134 | UTTAR DINAJPUR | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12108 | New | DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | BP-2024-25-24 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 5.18 | 0 | 0 | 0
135 | UTTAR DINAJPUR | Malda Mechanical | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12108 | New | Additional Quotation for TW-II of Adiar Water Supply Scheme in the District of Uttar Dinajpur. | BP-2024-25-487 | 09/09/2024 | 0 | W.B.S.E.D.C.LTD | 0.74 | 0 | 0 | 0
136 | UTTAR DINAJPUR | Malda Mechanical | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12108 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Adiar, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-519 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 2.53 | 0 | 0 | 0
137 | UTTAR DINAJPUR | Malda Mechanical | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12108 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Adiar, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-520 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 6.12 | 0 | 0 | 0
138 | UTTAR DINAJPUR | Malda Mechanical | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12108 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Adiar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012052) | 2456/MLMD | 04/08/2023 | 962 | M/S D.G.B. ENTERPRISE. | 26.47 | 0 | 0 | 90
139 | UTTAR DINAJPUR | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12108 | New | Trial Run For Adiar PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | 539/RD/PHE | 12/02/2025 | 90 | M/S SOMNATH KUNDU | 0.88 | 0 | 0 | 0
140 | UTTAR DINAJPUR | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12108 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Adiar Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | 1816/RD/PHE | 24/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 19.35 | 0 | 0 | 0
141 | UTTAR DINAJPUR | Raiganj Division | ADIAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12108 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under ADIAR Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 571/RD/PHE | 05/03/2024 | 135 | BHOLA PAUL | 22.57 | 0 | 0 | 100
142 | UTTAR DINAJPUR | Raiganj Division | KAMALPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12787 | New | Material Requisition To Resource Division | 1123/RD/PHE | 24/04/2023 | 0 | Resource Division | 23.6 | 0 | 0 | 0
143 | UTTAR DINAJPUR | Malda Mechanical | KAMALPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12787 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Kamalpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014417) | 2370/MLMD | 28/07/2023 | 1064 | DAS CONSTRUCTION | 25.7 | 0 | 0 | 72
144 | UTTAR DINAJPUR | Malda Mechanical | KAMALPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12787 | New | Quotation for new service connection at KAMALPUR PH-I (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12787) | BP-2024-25-278 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 13.21 | 0 | 0 | 0
145 | UTTAR DINAJPUR | Malda Mechanical | KAMALPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12787 | New | Quotation for new service connection at KAMALPUR PH-II (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12787) | BP-2024-25-277 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 3.62 | 0 | 0 | 0
146 | UTTAR DINAJPUR | Raiganj Division | KAMALPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12787 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kamalpur Water Supply Scheme at Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 20 M3/hr. | 1818/RD/PHE | 24/06/2025 | 180 | AJIT PRAMANIK | 15.38 | 0 | 0 | 0
147 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Providing functional house hold tap connection at Village-Amritkhanda of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 774/RD/PHE | 17/03/2023 | 60 | M/S BHOWMIK CONSTRUCTION | 16 | 0 | 0 | 0
148 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Construction of OHR (Capacity-250Cum) of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur district under Raiganj Division, P.H.E. Dte. | 853/RD/PHE | 24/03/2023 | 275 | DIPAK SAHA | 95.39 | 0 | 0 | 0
149 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Providing Functional House Hold Tap Connection at village- Bishahar of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 960/RD/PHE | 29/03/2023 | 60 | DAS CONSTRUCTION COMPANY | 15.45 | 0 | 0 | 0
150 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Laying, Rising-Main of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 858/RD/PHE | 24/03/2023 | 60 | M/S MANDAL ENTERPRISE TUMPASONU05@YAHOO.COM | 4.52 | 0 | 0 | 0
151 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Construction of Pump house and boundary wall at Head Work Site of Bishahar PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 826/RD/PHE | 22/03/2023 | 60 | DISCOVERY CO. OPERATIVE LABOUR CONT AND CONST SOC. LTD. | 24.86 | 0 | 0 | 0
152 | UTTAR DINAJPUR | Malda Mechanical | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Bishahar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018229) | 2468/MLMD | 04/08/2023 | 120 | R. S. ENTERPRISE | 25.32 | 0 | 0 | 0
153 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Material Requisition To Resource Division | 1679/RD/PHE | 19/06/2023 | 0 | Resource Division | 39.44 | 0 | 0 | 0
154 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Kokra, 2.Bishahar, 3. Dhoabishua in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 539/RD/PHE | 22/02/2023 | 630 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 0 | 65
155 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Laying Pipe line at Village-Bishahar of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 959/RD/PHE | 29/03/2023 | 60 | MAA SHEETALA ENTERPRISE | 40.95 | 0 | 0 | 35
156 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Laying distribution of Pipe line of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 820/RD/PHE | 22/03/2023 | 45 | M/S P.S. ENTERPRISE | 47.35 | 0 | 0 | 20
157 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Laying pipe line at Dakhshin Bishnupur of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 949/RD/PHED | 29/03/2023 | 60 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 40.88 | 0 | 0 | 15
158 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Laying of pipe line at Village-Amritakhanda of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 764/RD/PHE | 17/03/2023 | 60 | M/S PIONEER ENTERPRISE | 40.84 | 0 | 0 | 20
159 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Laying of Pipe Line at village-Birahimkhanda & Ital of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 874/RD/PHE | 27/03/2023 | 60 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 41.03 | 0 | 0 | 20
160 | UTTAR DINAJPUR | Malda Mechanical | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Bishahar, Birnagar CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-624 | 04/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.74 | 0 | 0 | 0
161 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Providing functional House hold tap connection at village-Birhimkhanda & Ital of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 879/RD/PHE | 27/03/2023 | 735 | SANDIP SARKAR | 15.22 | 0 | 0 | 15
162 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
163 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Providing functional house hold tap connection at village-Dakhshin Bishnupur of BISHAHAR PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2047/RD/PHE | 19/07/2023 | 622 | SANDIP SARKAR | 16.32 | 0 | 0 | 0
164 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bishahar PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 16/RD/PHE | 02/01/2025 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 24.95 | 0 | 0 | 0
165 | UTTAR DINAJPUR | Raiganj Division | BISHAHAR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14144 | New | Construction of boundary wall and Pump house at 2nd tube-well of BISHAHAR PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 769/RD/PHE | 17/03/2023 | 540 | DULAL DUTTA | 11.28 | 0 | 0 | 100
166 | UTTAR DINAJPUR | Raiganj Division | PRATAPPUR PIPED WATER SUPPLY SCHEME , SM/14128 | New | Material Requisition To Resource Division | 1201/RD/PHE | 28/04/2023 | 0 | Resource Division | 37.78 | 0 | 0 | 0
167 | UTTAR DINAJPUR | Malda Mechanical | PRATAPPUR PIPED WATER SUPPLY SCHEME , SM/14128 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of PRATAPPUR, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-432 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 11.43 | 0 | 0 | 0
168 | UTTAR DINAJPUR | Malda Mechanical | PRATAPPUR PIPED WATER SUPPLY SCHEME , SM/14128 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of PRATAPPUR, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-431 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.69 | 0 | 0 | 0
169 | UTTAR DINAJPUR | Malda Mechanical | PRATAPPUR PIPED WATER SUPPLY SCHEME , SM/14128 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Pratappur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016739) | 3691/MLMD | 29/11/2023 | 939 | MERCURY ENGINEERING COMPANY. | 27.51 | 0 | 0 | 85
170 | UTTAR DINAJPUR | Raiganj Division | PRATAPPUR PIPED WATER SUPPLY SCHEME , SM/14128 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Pratappur Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | 1803/RD/PHE | 24/06/2025 | 180 | JAL PRAVAHIKA PRIVATE LIMITED | 29.55 | 0 | 0 | 0
171 | UTTAR DINAJPUR | Raiganj Division | PRATAPPUR PIPED WATER SUPPLY SCHEME , SM/14128 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at PRATAPPUR PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | 2087/RD/PHE | 14/07/2025 | 180 | ROY ENGINEERS. (PATNA) | 38.64 | 0 | 0 | 0
172 | UTTAR DINAJPUR | Raiganj Division | DAMODARKHURI Piped Water Supply Scheme , SM/13236 | New | Material Requisition To Resource Division | 848/RD/PHE | 24/03/2023 | 0 | Resource Division | 30.26 | 0 | 0 | 0
173 | UTTAR DINAJPUR | Malda Mechanical | DAMODARKHURI Piped Water Supply Scheme , SM/13236 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Damodarkhuri Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015341) | 2488/MLMD | 04/08/2023 | 840 | DEY ENTERPRISE.. | 26.44 | 0 | 0 | 72
174 | UTTAR DINAJPUR | Raiganj Division | DAMODARKHURI Piped Water Supply Scheme , SM/13236 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
175 | UTTAR DINAJPUR | Raiganj Division | DAMODARKHURI Piped Water Supply Scheme , SM/13236 | New | Providing FHTC in connection with Damodarkhuri Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 1172/RD/PHE | 23/04/2025 | 30 | ANILA CONSTRUCTION | 10.08 | 0 | 0 | 0
176 | UTTAR DINAJPUR | Raiganj Division | DAMODARKHURI Piped Water Supply Scheme , SM/13236 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Damodarkhuri Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | 2496/RD/PHE | 12/09/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 29.58 | 0 | 0 | 0
177 | UTTAR DINAJPUR | Malda Mechanical | PANDITPOTA PIPED WATER SUPPLY SCHEME , SM/13542 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of PANDITPOTA, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003215071 | 23/08/2023 | 90 | W.B.S.E.D.C.LTD | 8.43 | 0 | 0 | 100
178 | UTTAR DINAJPUR | Malda Mechanical | PANDITPOTA PIPED WATER SUPPLY SCHEME , SM/13542 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of PANDITPOTA, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003229632 | 13/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.25 | 0 | 0 | 100
179 | UTTAR DINAJPUR | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME , SM/13542 | New | Material Requisition To Resource Division | 599/RD/PHE | 27/02/2023 | 0 | Resource Division | 24.54 | 0 | 0 | 0
180 | UTTAR DINAJPUR | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME , SM/13542 | New | Protection and restoration work of damaged flank caused by excavation for water supply project of PHE of Islampur- Amaljhari- Sonamoti Road under Uttar Dinajpur division, PWD. | BILL/00506/2023 | 30/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 7.97 | 0 | 0 | 0
181 | UTTAR DINAJPUR | Malda Mechanical | PANDITPOTA PIPED WATER SUPPLY SCHEME , SM/13542 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Panditpota Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015533) | 2528/MLMD | 04/08/2023 | 937 | M/S S. S. ENTERPRISE | 28.05 | 0 | 0 | 70
182 | UTTAR DINAJPUR | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME , SM/13542 | New | Laying of Additional Pipeline ,FHTC with Land development and Path way for PANDITPOTA Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte.under Raiganj Division, P.H.E Dte.,U/D. | 3581/RD/PHE | 05/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 65.94 | 0 | 0 | 0
183 | UTTAR DINAJPUR | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME , SM/13542 | New | Construction Of Single Row 1200 Mm Dia Np3 Hume Pipe Culvert In Front Of Panditpota Head Works Site For Approach Road Under Raiganj Division, Phe Dte. | 3578/RD/PHE | 05/12/2024 | 15 | UTTAM SAHA | 3.13 | 0 | 0 | 0
184 | UTTAR DINAJPUR | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME , SM/13542 | New | Implementation of PANDITPOTA and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 569/RD/PHE | 23/02/2023 | 1038 | SANYAL ENTERPRISE | 320.79 | 0 | 0 | 81
185 | UTTAR DINAJPUR | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME , SM/13542 | New | Providing FHTC in connection with Panditpota Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 54/RD/PHE | 03/01/2025 | 45 | SANYAL ENTERPRISE | 10.39 | 0 | 0 | 0
186 | UTTAR DINAJPUR | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME , SM/13542 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under PANDITPOTA PWSS at Islampur Block under Raiganj Division, PHE Dte. | 1711/RD/PHE | 10/06/2024 | 270 | BHAGYA LAXMI ENTERPRISE | 22.59 | 0 | 0 | 0
187 | UTTAR DINAJPUR | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME , SM/13542 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Panditpota Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | 1924/RD/PHE | 30/06/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 18.74 | 0 | 0 | 0
188 | UTTAR DINAJPUR | Raiganj Division | PANDITPOTA PIPED WATER SUPPLY SCHEME , SM/13542 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
189 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Providing FHTC at village- Dhangaon of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 772/RD/PHE | 17/03/2023 | 60 | M/S P.S. ENTERPRISE | 17.95 | 0 | 0 | 0
190 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Laying pipe line at village- Dhangaon of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 762/RD/PHE | 17/03/2023 | 60 | CHAITANYA SAMAL | 48.9 | 0 | 0 | 0
191 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Construction of Boundary Wall and Pump House at 2nd Tube-well site of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 767/RD/PHE | 17/03/2023 | 60 | M/S UNIQUE 13 | 11.28 | 0 | 0 | 0
192 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Providing FHTC at village- Bhagdoarin of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 877/RD/PHE | 27/03/2023 | 60 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 17.08 | 0 | 0 | 0
193 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Laying of Rising Main of LAHUTARA Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 856/RD/PHE | 24/03/2023 | 60 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. LOKNATH.ITR@GMAIL.COM | 5.25 | 0 | 0 | 0
194 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Providing FHTC at village- Lahutara & Gurulbhasa of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 952/RD/PHE | 29/03/2023 | 60 | JEET CONSTRUCTION UKILPARA CTNJIT38@GMAIL.COM | 19.57 | 0 | 0 | 0
195 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Material Requisition To Resource Division | 1321/RD/PHE | 12/05/2023 | 0 | Resource Division | 44.41 | 0 | 0 | 0
196 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Laying of Pipe line of village-Bhagdarin of LAHUTARA Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 872/RD/PHE | 27/03/2023 | 608 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. TANAJIT77@GMAIL.COM | 47.52 | 0 | 0 | 75
197 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Laying distribution of pipe line of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 818/RD/PHE | 22/03/2023 | 730 | BHOWMICK ENTERPRISE | 50.31 | 0 | 0 | 70
198 | UTTAR DINAJPUR | Malda Mechanical | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Lahutara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017508) | 2516/MLMD | 04/08/2023 | 937 | TARUN KUMAR DEY | 25.08 | 0 | 0 | 77
199 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for LAHUTARA Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | 3486/RD/PHE | 02/12/2024 | 30 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 16.66 | 0 | 0 | 0
200 | UTTAR DINAJPUR | Malda Mechanical | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Quotation for new service connection at LAHUTARA PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/ 14165) | BP-2024-25-485 | 09/09/2024 | 0 | W.B.S.E.D.C.LTD | 12.11 | 0 | 0 | 0
201 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Lahutara, 2. Hemenpur, 3. Basudebpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 541/RD/PHE | 22/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 61.71 | 0 | 0 | 60
202 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Construction of OHR(Capacity-300Cum) of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte.. | 851/RD/PHE | 24/03/2023 | 709 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 96.67 | 0 | 0 | 0
203 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Providing FHTC at village-Lahutara of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 957/RD/PHE | 29/03/2023 | 481 | RURAL DEVELOPMENT CO-OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 16.29 | 0 | 0 | 0
204 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Laying of pipe line at village -Lahutara & Gurul Bhasa of LAHUTARA Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 947/RD/PHED | 29/03/2023 | 60 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 48.48 | 0 | 0 | 0
205 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
206 | UTTAR DINAJPUR | Raiganj Division | LAHUTARA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14165 | New | Laying of Additional pipeline with other ancillary works at different mouzas of LAHUTARA PWSS under Islampur Sub-Division P.H.E. Dte. | 3498/RD/PHE | 02/12/2024 | 270 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 48.12 | 0 | 0 | 30
207 | UTTAR DINAJPUR | Raiganj Division | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14167 | New | Material Requisition To Resource Division | 902/RD/PHE | 28/03/2023 | 0 | Resource Division | 60.85 | 0 | 0 | 0
208 | UTTAR DINAJPUR | Malda Mechanical | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14167 | New | Quotation for new service connection at CHITAURA PH-I (Kanki ccc) in the district of Uttar Dinajpur. | BP-2023-24-651 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 9.23 | 0 | 0 | 0
209 | UTTAR DINAJPUR | Malda Mechanical | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14167 | New | Quotation for new service connection at CHITAURA PH-I (Kanki ccc) in the district of Uttar Dinajpur. | BP-2023-24-652 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 8.8 | 0 | 0 | 0
210 | UTTAR DINAJPUR | Raiganj Division | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14167 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
211 | UTTAR DINAJPUR | Malda Mechanical | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14167 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chitaura Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016571) | 3695/MLMD | 29/11/2023 | 880 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 27.49 | 0 | 0 | 84
212 | UTTAR DINAJPUR | Raiganj Division | CHITAURA PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14167 | New | Additional pipeline and other ancillary works at Chitaura piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | 2362/RD/PHE | 25/08/2025 | 45 | MILAN GHOSH | 61.51 | 0 | 0 | 0
213 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Barobilla Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14225 | Augmentation | Material Requisition To Resource Division | 2388/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.4 | 0 | 0 | 0
214 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Barobilla Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14225 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Barabilla Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016481) | 3693/MLMD | 29/11/2023 | 791 | DAS CONSTRUCTION | 10.91 | 0 | 0 | 84
215 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Barobilla Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14225 | Augmentation | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Barobilla Piped Water Supply Scheme of Chopra Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 56/RD/PHE | 16/01/2023 | 45 | SUSANTA GOBINDA DEB GOPALDEB9475@GMAIL.COM | 28.53 | 0 | 0 | 60
216 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Laying Rising Main of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 857/RD/PHE | 24/03/2023 | 60 | M/S DAS CONSTRUCTION ITAHAR | 4.52 | 0 | 0 | 0
217 | UTTAR DINAJPUR | Malda Mechanical | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of DHOABISHUA, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003196207 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 8.77 | 0 | 0 | 100
218 | UTTAR DINAJPUR | Malda Mechanical | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of DHOABISHUA, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003196209 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 6.06 | 0 | 0 | 100
219 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Material Requisition To Resource Division | 1680/RD/PHE | 19/06/2023 | 0 | Resource Division | 42.41 | 0 | 0 | 0
220 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Kokra, 2.Bishahar, 3. Dhoabishua in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 539/RD/PHE | 22/02/2023 | 630 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 0 | 65
221 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Laying Pipeline at village-Aulabari of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 763/RD/PHE | 17/03/2023 | 60 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 50.29 | 0 | 0 | 65
222 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Construction of OHR (Capacity-250Cum) with pipeline of Dhoabishua Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 852/RD/PHE | 24/03/2023 | 725 | M/S RATAN SARKAR & SON | 95.77 | 0 | 0 | 45
223 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Laying pipe line of village-Balihar & Shialtore of DHOABISHUA PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 873/RD/PHE | 27/03/2023 | 705 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 46.8 | 0 | 0 | 65
224 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Laying distribution of pipe line of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 819/RD/PHE | 22/03/2023 | 675 | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 57.91 | 0 | 0 | 60
225 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Laying pipe line of village- Deogaon & Ekar of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 948/RD/PHED | 29/03/2023 | 360 | S. B. CONSTRUCTION | 50.92 | 0 | 0 | 55
226 | UTTAR DINAJPUR | Malda Mechanical | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Dhoabishua Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018369) | 2744/MLMD | 14/08/2023 | 180 | TAPAN BISWAS. | 24.25 | 0 | 0 | 75
227 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Construction of boundary wall and pump house at head work site of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 825/RD/PHE | 22/03/2023 | 395 | M/S. ROY & CO. | 24.75 | 0 | 0 | 95
228 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Construction of boundary wall and pump house at 2nd tube-well site of DHOABISHUA PWSS at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 768/RD/PHE | 17/03/2023 | 60 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 11 | 0 | 0 | 80
229 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Providing Functional House hold tap connection at village- Aulabari of DHOABISHUA Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 773/RD/PHE | 17/03/2023 | 775 | BITTU ENTERPRISE BISWAJIT.RNJ@GMAIL.COM | 15.25 | 0 | 0 | 0
230 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Providing functional house hold tap connection at Village-Balihar & Shialtore of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 878/RD/PHE | 27/03/2023 | 764 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 15.99 | 0 | 0 | 0
231 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Providing functional house hold tap connection of village-Dhoabishua of DHOABISHUA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 958/RD/PHE | 29/03/2023 | 763 | M/S P.S. ENTERPRISE | 15.41 | 0 | 0 | 0
232 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Providing Functional house Hold Tap Connections at village- Balihar and Ekar of DHOABISHUA Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 953/RD/PHE | 29/03/2023 | 823 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 16.18 | 0 | 0 | 0
233 | UTTAR DINAJPUR | Raiganj Division | DHOABISHUA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15212 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Dhoabishua PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3743/RD/PHE | 18/12/2024 | 135 | DONE ENTERPRISE | 14.77 | 0 | 0 | 0
234 | UTTAR DINAJPUR | Raiganj Division | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16199 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 0 | 100
235 | UTTAR DINAJPUR | Raiganj Division | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16199 | New | Material Requisition To Resource Division | 1678/RD/PHE | 19/06/2023 | 0 | Resource Division | 3.19 | 0 | 0 | 0
236 | UTTAR DINAJPUR | Raiganj Division | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16199 | New | Implementation of Pakhuria and it's adjoining mouzas Pipe Water Supply Scheme at Itahar Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House at Head Work Site.) | 679/RD/PHE | 06/03/2023 | 90 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 48.68 | 0 | 0 | 40
237 | UTTAR DINAJPUR | Raiganj Division | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16199 | New | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under PAKHURIA PWSS at Itahar Block under Raiganj Division, PHE Dte. | 615/RD/PHE | 05/03/2024 | 45 | GOPES SAHA | 5.57 | 0 | 0 | 100
238 | UTTAR DINAJPUR | Malda Mechanical | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16199 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Pakhuria , Itahar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-393 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.16 | 0 | 0 | 0
239 | UTTAR DINAJPUR | Malda Mechanical | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16199 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. III of Source augmentation of Pakhuria Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016131) | 2450/MLMD | 04/08/2023 | 301 | M/S SABANA CONSTRUCTION | 6.89 | 0 | 0 | 100
240 | UTTAR DINAJPUR | Raiganj Division | Pakhuria Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16199 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Pakhuria Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj, Capacity- 5 M3/hr. | 1631/RD/PHE | 20/06/2025 | 180 | AJIT PRAMANIK | 12.4 | 0 | 0 | 0
241 | UTTAR DINAJPUR | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16220 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
242 | UTTAR DINAJPUR | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16220 | New | Material Requisition To Resource Division | 809/RD/PHE | 21/03/2023 | 0 | Resource Division | 20.28 | 0 | 0 | 0
243 | UTTAR DINAJPUR | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16220 | New | Implementation of HARINARAYANPUR(Zone- II) and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1276/RD/PHE | 08/05/2023 | 900 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 306.66 | 0 | 0 | 10
244 | UTTAR DINAJPUR | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16220 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under HARINARAYANPUR ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 634/RD/PHE | 05/03/2024 | 45 | M/S R.D. CONSTRUCTION | 24.48 | 0 | 0 | 0
245 | UTTAR DINAJPUR | Malda Mechanical | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16220 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Harinarayanpur, (Zone-II), Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-471 | 26/01/2024 | 0 | W.B.S.E.D.C.LTD | 11.36 | 0 | 0 | 0
246 | UTTAR DINAJPUR | Malda Mechanical | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16220 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Harinarayanpur, (Zone-II), Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-470 | 26/01/2024 | 0 | W.B.S.E.D.C.LTD | 12.34 | 0 | 0 | 0
247 | UTTAR DINAJPUR | Malda Mechanical | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16220 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Harinarayanpur Zone- II Water Supply Scheme in the District of Malda under Uttar Dinajpur Mechanical Division, PHE Dte. (TSM/018697) | 2749/MLMD | 14/08/2023 | 837 | JOYSHREE CONCERN. | 22.21 | 0 | 0 | 89
248 | UTTAR DINAJPUR | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16220 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Harinarayanpur Zone-2 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 24/RD/PHE | 02/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 22.97 | 0 | 0 | 0
249 | UTTAR DINAJPUR | Raiganj Division | Harinarayanpur Zone-II Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16220 | New | Trial Run For Harinarayanpur Zone-II PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 month | 533/RD/PHE | 12/02/2025 | 90 | M/S P.S. ENTERPRISE | 0.88 | 0 | 0 | 0
250 | UTTAR DINAJPUR | Raiganj Division | MAHADIPUR MINI PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18155 | New | Material Requisition To Resource Division | 2254/RD/PHE | 03/08/2023 | 0 | Resource Division | 5.67 | 0 | 0 | 0
251 | UTTAR DINAJPUR | Raiganj Division | MAHADIPUR MINI PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18155 | New | Implementation of MAHADIPUR Mini Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division. | 1561/RD/PHE | 29/05/2023 | 90 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 58.48 | 0 | 0 | 20
252 | UTTAR DINAJPUR | Raiganj Division | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18167 | New | Material Requisition To Resource Division | 2257/RD/PHE | 03/08/2023 | 0 | Resource Division | 6.26 | 0 | 0 | 0
253 | UTTAR DINAJPUR | Raiganj Division | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18167 | New | Implementation of BANKUR and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | 1557/RD/PHE | 29/05/2023 | 90 | UTTAM SAHA | 84.34 | 0 | 0 | 55
254 | UTTAR DINAJPUR | Malda Mechanical | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18167 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. I & II of Bankur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020973) | 2708/MLMD | 11/08/2023 | 1050 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 14.28 | 0 | 0 | 69
255 | UTTAR DINAJPUR | Raiganj Division | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18167 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 29.07.2024 to 02.08.2024. | BP-2024-25-180 | 30/08/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
256 | UTTAR DINAJPUR | Raiganj Division | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18167 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 01.07.2024 to 05.07.2024. | BP-2024-25-155 | 30/07/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
257 | UTTAR DINAJPUR | Raiganj Division | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18167 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 08.07.2024 to 12.07.2024. | BP-2024-25-156 | 30/07/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
258 | UTTAR DINAJPUR | Raiganj Division | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18167 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bankur Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 10 M3/hr. | 2494/RD/PHE | 12/09/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.82 | 0 | 0 | 0
259 | UTTAR DINAJPUR | Raiganj Division | BANKUR PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18167 | New | Construction Of Approach Road,Laying Of Pipe Line And Other Allied Works Of Bankur Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3570/RD/PHE | 05/12/2024 | 30 | UTTAM SAHA | 11.15 | 0 | 0 | 0
260 | UTTAR DINAJPUR | Raiganj Division | Sripur Piped Water Supply Scheme , SM/17226 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 0 | 100
261 | UTTAR DINAJPUR | Raiganj Division | Sripur Piped Water Supply Scheme , SM/17226 | New | Material Requisition To Resource Division | 1315/RD/PHE | 12/05/2023 | 0 | Resource Division | 6.2 | 0 | 0 | 0
262 | UTTAR DINAJPUR | Malda Mechanical | Sripur Piped Water Supply Scheme , SM/17226 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. III of Source augmentation of Sripur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016135) | 2452/MLMD | 04/08/2023 | 962 | SOVA ENTERPRISE. | 6.95 | 0 | 0 | 81
263 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kaliganj (Bangar village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. , SM/17740 | Augmentation | Preparation of DPR for drinking water supply scheme to facilitate 4(Four)Nos. Augmentation Scheme and 1(One) No. New PWSS (List Enclosed) Uncovered mouzas under Uttar Dinajpur District which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Raiganj Division P.H.E. Dte. | 2226/RD/PHE | 31/07/2023 | 15 | RADIANT | 11.57 | 0 | 0 | 100
264 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kaliganj (Bangar village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. , SM/17740 | Augmentation | Material Requisition To Resource Division | 1106/RD/PHE | 20/04/2023 | 0 | Resource Division | 6.34 | 0 | 0 | 0
265 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Kaliganj (Bangar village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. , SM/17740 | Augmentation | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.III of Source augmentation of Kaliganj (Bangar Village) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018636) | 2753/MLMD | 14/08/2023 | 1047 | M/S. MAYUKH BHADURI | 7.16 | 0 | 0 | 81
266 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kaliganj (Bangar village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. , SM/17740 | Augmentation | Augmentation of Kaliganj (Bangar) and it's adjoining mouzas Pipe Water Supply Scheme at Itahar Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House) | 884/RD/PHE | 27/03/2023 | 989 | BHOLA PAUL | 78.26 | 0 | 0 | 30
267 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kaliganj (Bangar village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. , SM/17740 | Augmentation | Construction of Approach Road, Laying of Pipe Line, FHTC And Other Allied Works of Kaliganj(Bangar) Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3560/RD/PHE | 05/12/2024 | 91 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 18.03 | 0 | 0 | 0
268 | UTTAR DINAJPUR | Raiganj Division | TUNIBHITA PWSS , SM/18291 | New | Material Requisition To Resource Division | 637/RD/PHE | 02/03/2023 | 0 | Resource Division | 58.92 | 0 | 0 | 0
269 | UTTAR DINAJPUR | Malda Mechanical | TUNIBHITA PWSS , SM/18291 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Tunibhita Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018453) | 3704/MLMD | 29/11/2023 | 730 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 37.34 | 0 | 0 | 66
270 | UTTAR DINAJPUR | Raiganj Division | TUNIBHITA PWSS , SM/18291 | New | Laying of Additional Pipeline with pathway at TUNIBHITA Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte. under Raiganj Division, P.H.E Dte.,U/D. | 3555/RD/PHE | 05/12/2024 | 45 | CALCON CONSTRUCTION | 53.07 | 0 | 0 | 0
271 | UTTAR DINAJPUR | Malda Mechanical | TUNIBHITA PWSS , SM/18291 | New | Quotation for new service connection at TUNIVITA PH-III (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18291) | BP-2024-25-582 | 03/12/2024 | 0 | W.B.S.E.D.C.LTD | 17.28 | 0 | 0 | 0
272 | UTTAR DINAJPUR | Raiganj Division | TUNIBHITA PWSS , SM/18291 | New | Implementation of TUNIBHITA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rdTubeWell) | 2477/RD/PHE | 24/08/2023 | 576 | CALCON CONSTRUCTION | 843.51 | 0 | 0 | 50
273 | UTTAR DINAJPUR | Raiganj Division | TUNIBHITA PWSS , SM/18291 | New | Construction of Boundary Wall With Gate at Head Work Site ,2nd &3rd Tube-Well Site under TUNIVITA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 642/RD/PHE | 05/03/2024 | 183 | DULAL DUTTA | 27.71 | 0 | 0 | 100
274 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17437 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
275 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17437 | New | Material Requisition To Resource Division | 2239/RD/PHE | 02/08/2023 | 0 | Resource Division | 11.53 | 0 | 0 | 0
276 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17437 | New | Implementation of SURANGAPUR (ZONE-III) and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1995/RD/PHE | 13/07/2023 | 270 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 164.11 | 0 | 0 | 40
277 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17437 | New | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under SURANGAPUR ZONE-III PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 648/RD/PHE | 05/03/2024 | 45 | M/S ARITRA DUTTA | 5.56 | 0 | 0 | 0
278 | UTTAR DINAJPUR | Malda Mechanical | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17437 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Surangapur (Zone-III), Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-74 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 0.14 | 0 | 0 | 0
279 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17437 | New | Approach road with land development of headwork site and road restoration of Surangapur zone III PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 05/RD/PHE | 02/01/2025 | 45 | M/S ROYAL CONSTRUCTION | 5.7 | 0 | 0 | 0
280 | UTTAR DINAJPUR | Malda Mechanical | Surangapur Zone-III Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17437 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Surangapur (Zone-III) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018494) | 2725/MLMD | 14/08/2023 | 180 | S.G.ENTERPRISE | 7.17 | 0 | 0 | 100
281 | UTTAR DINAJPUR | Raiganj Division | TOPAMARI PWSS , SM/18243 | New | Material Requisition To Resource Division | 602/RD/PHE | 27/02/2023 | 0 | Resource Division | 57.96 | 0 | 0 | 0
282 | UTTAR DINAJPUR | Malda Mechanical | TOPAMARI PWSS , SM/18243 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Topamari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014297) | 2537/MLMD | 04/08/2023 | 907 | HANNAN BUILDERS PVT. LTD. | 38.26 | 0 | 0 | 76
283 | UTTAR DINAJPUR | Raiganj Division | TOPAMARI PWSS , SM/18243 | New | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for Topamari Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division, PHED.,U/D. | 3502/RD/PHE | 02/12/2024 | 30 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 15.72 | 0 | 0 | 0
284 | UTTAR DINAJPUR | Raiganj Division | TOPAMARI PWSS , SM/18243 | New | Additional pipeline and other ancillary works at Topamari piped water Supply Scheme Under Islampur SubDivision under Raiganj Division, P.H.E Dte. | 3501/RD/PHE | 02/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 40.29 | 0 | 0 | 0
285 | UTTAR DINAJPUR | Malda Mechanical | TOPAMARI PWSS , SM/18243 | New | Quotation for new service connection at TOPAMARI PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18243) | BP-2024-25-262 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 4.38 | 0 | 0 | 0
286 | UTTAR DINAJPUR | Raiganj Division | TOPAMARI PWSS , SM/18243 | New | Implementation of TOPAMARI and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd & 3rd Tube Well) | 2003/RD/PHE | 13/07/2023 | 626 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 833.91 | 0 | 0 | 50
287 | UTTAR DINAJPUR | Raiganj Division | TOPAMARI PWSS , SM/18243 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Topamari Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | 1797/RD/PHE | 24/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 36.36 | 0 | 0 | 0
288 | UTTAR DINAJPUR | Raiganj Division | TOPAMARI PWSS , SM/18243 | New | Construction of Boundary Wall with Gate at Head Work Site, 2nd & 3rd Tube-Well Site under TOPAMARI Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 563/RD/PHE | 05/03/2024 | 450 | MS SANDHYA CONSTRUCTION | 27.69 | 0 | 0 | 95
289 | UTTAR DINAJPUR | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/18451 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
290 | UTTAR DINAJPUR | Malda Mechanical | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/18451 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Kalua,PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003279144 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 4.53 | 0 | 0 | 100
291 | UTTAR DINAJPUR | Malda Mechanical | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/18451 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Kalua,PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003279164 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 12.79 | 0 | 0 | 100
292 | UTTAR DINAJPUR | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/18451 | New | Material Requisition To Resource Division | 2243/RD/PHE | 02/08/2023 | 0 | Resource Division | 99.68 | 0 | 0 | 0
293 | UTTAR DINAJPUR | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/18451 | New | Construction of Boundary Wall With Gate at Head Work, 2nd, 3rd, 4th & 5th Tube-Well Site under KALUA PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 651/RD/PHE | 05/03/2024 | 360 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 37.97 | 0 | 0 | 80
294 | UTTAR DINAJPUR | Malda Mechanical | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/18451 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Kalua, Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-620 | 04/03/2024 | 0 | W.B.S.E.D.C.LTD | 6.78 | 0 | 0 | 0
295 | UTTAR DINAJPUR | Malda Mechanical | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/18451 | New | Additional quotation of Kalua PWSS TW-III in the district of Uttar Dinajpur. | BP-2024-25-437 | 20/08/2024 | 0 | W.B.S.E.D.C.LTD | 3.7 | 0 | 0 | 0
296 | UTTAR DINAJPUR | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/18451 | New | Implementation of KALUA and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2090/RD/PHE | 27/07/2023 | 990 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 798.98 | 0 | 0 | 56
297 | UTTAR DINAJPUR | Malda Mechanical | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/18451 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II,III,IV & V and making compound lighting arrangement ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Kalua Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018393) | 2754/MLMD | 14/08/2023 | 2005 | DILIP MAHATO. | 67.92 | 0 | 0 | 77
298 | UTTAR DINAJPUR | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/18451 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site, 2nd & 3rd tubewell site and road restoration of Kalua PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3747/RD/PHE | 18/12/2024 | 135 | AJIT PRAMANIK | 84.29 | 0 | 0 | 0
299 | UTTAR DINAJPUR | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/18451 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kalua Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity- 150 M3/hr. | 2472/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 52.02 | 0 | 0 | 0
300 | UTTAR DINAJPUR | Raiganj Division | Kalua Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/18451 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
301 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Kamartor and adjoining Mouzas water supply scheme in Karandighi Block , SM/07071 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kamartor and Adjoining Mouzas Water Supply Scheme in Karandighi Block under Raiganj Division, P.H.E. Dte. | 1414/RD/PHE | 11/12/2020 | 40 | J.D.J. ENTERPRISE | 88.73 | 0 | 0 | 100
302 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Kamartor and adjoining Mouzas water supply scheme in Karandighi Block , SM/07071 | Retrofitting | Barbed Fencing work at Kamartor Head Work Site of Kamartor Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | 2254/RD/PHE | 22/12/2022 | 596 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 1.49 | 0 | 0 | 100
303 | UTTAR DINAJPUR | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 0 | 100
304 | UTTAR DINAJPUR | Malda Mechanical | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Pajol, Itahar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003233393 | 22/09/2023 | 90 | W.B.S.E.D.C.LTD | 6.22 | 0 | 0 | 100
305 | UTTAR DINAJPUR | Malda Mechanical | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Pajol, Itahar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003233390 | 22/09/2023 | 90 | W.B.S.E.D.C.LTD | 7.92 | 0 | 0 | 100
306 | UTTAR DINAJPUR | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | Material Requisition To Resource Division | 786/RD/PHE | 18/03/2023 | 0 | Resource Division | 137.43 | 0 | 0 | 0
307 | UTTAR DINAJPUR | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under PAJOL PWSS at Itahar Block under Raiganj Division, PHE Dte. | 630/RD/PHE | 05/03/2024 | 118 | R. R. CONSTRUCTION | 12.24 | 0 | 0 | 70
308 | UTTAR DINAJPUR | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | DI Pipe Carrying RCC Structure Over Sooin River of Pajol PWSS at Itahar Block under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3011/RD/PHE | 03/10/2024 | 30 | BHOLA PAUL | 6.06 | 0 | 0 | 0
309 | UTTAR DINAJPUR | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 24.06.2024 to 28.06.2024. | BP-2024-25-154 | 30/07/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
310 | UTTAR DINAJPUR | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 18.06.2024 to 21.06.2024. | BP-2024-25-153 | 30/07/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
311 | UTTAR DINAJPUR | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 22.07.2024 to 26.07.2024. | BP-2024-25-179 | 30/08/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
312 | UTTAR DINAJPUR | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | Implementation of PAJOL and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 556/RD/PHE | 23/02/2023 | 1043 | BHOLA PAUL | 315.3 | 0 | 0 | 44
313 | UTTAR DINAJPUR | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
314 | UTTAR DINAJPUR | Malda Mechanical | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound yard lighting arrangement at T/W no. I of Pajol Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018893) | 2803/MLMD | 17/08/2023 | 834 | NIRMAN. | 25.82 | 0 | 0 | 77
315 | UTTAR DINAJPUR | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Pajol PWSS at Itahar Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3734/RD/PHE | 18/12/2024 | 135 | BHOLA PAUL | 48.58 | 0 | 0 | 0
316 | UTTAR DINAJPUR | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Pajol Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj, Capacity- 50 M3/hr. | 1632/RD/PHE | 20/06/2025 | 180 | AJIT PRAMANIK | 20.74 | 0 | 0 | 0
317 | UTTAR DINAJPUR | Raiganj Division | Pajol Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/15148 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under PAJOL PWSS at Itahar Block under Raiganj Division, PHE Dte. | 631/RD/PHE | 05/03/2024 | 90 | M/S NATARAJ CONSTRUCTION DEBUABCD.1234@REDIFFMAIL.COM | 12.24 | 0 | 0 | 90
318 | UTTAR DINAJPUR | Raiganj Division | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12112 | New | Material Requisition To Resource Division | 2198/RD/PHE | 14/12/2022 | 0 | Resource Division | 67.14 | 0 | 0 | 0
319 | UTTAR DINAJPUR | Malda Mechanical | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12112 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of CHADGAON PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003276603 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 3.88 | 0 | 0 | 100
320 | UTTAR DINAJPUR | Malda Mechanical | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12112 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of CHADGAON PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003276544 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 3.87 | 0 | 0 | 100
321 | UTTAR DINAJPUR | Malda Mechanical | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12112 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Chadgaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013024) | 2113/MLMD | 05/07/2023 | 892 | DAS CONSTRUCTION | 24.15 | 0 | 0 | 89
322 | UTTAR DINAJPUR | Raiganj Division | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12112 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHADGAON Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 579/RD/PHE | 05/03/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 22.57 | 0 | 0 | 0
323 | UTTAR DINAJPUR | Raiganj Division | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12112 | New | Construction of Culvert with Hume Pipe Across PWD Borrow Pit for making accessible Road at Chandgaon PWSS Head Work Site at Kaliyaganj Block under Raiganj Division, P.H.E. Dte., Uttar Dinajpur. | 3009/RD/PHE | 03/10/2024 | 30 | PINTU SWARNAKAR | 2.17 | 0 | 0 | 100
324 | UTTAR DINAJPUR | Raiganj Division | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12112 | New | Implementation of CHADGAON andit's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 74/RD/PHE | 16/01/2023 | 1120 | UJJWAL DAS | 408.1 | 0 | 0 | 80
325 | UTTAR DINAJPUR | Raiganj Division | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12112 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chandgaon PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3735/RD/PHE | 18/12/2024 | 135 | UJJWAL DAS | 56.93 | 0 | 0 | 0
326 | UTTAR DINAJPUR | Raiganj Division | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12112 | New | Trial Run For Chandgaon PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | 520/RD/PHE | 12/02/2025 | 90 | UJJWAL DAS | 0.88 | 0 | 0 | 0
327 | UTTAR DINAJPUR | Raiganj Division | CHADGAON Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12112 | New | Balance work i.c.w. Construction of boundary wall of Chandgaon piped water supply scheme of Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E Dte. | 1608/RD/PHE | 17/06/2025 | 120 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 3.36 | 0 | 0 | 0
328 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte , SM/07977 | Retrofitting | Providing functional household Tap connection under Purba Chutiakhor and adjoining Mouzas Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte.¿ | 342/RD/PHE | 01/02/2021 | 60 | SANYAL ENTERPRISE | 110.45 | 0 | 0 | 1
329 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte , SM/07977 | Retrofitting | Providing functional household Tap connection under Bhojpur and adjoining Mouzas Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte | 343/RD/PHE | 01/02/2021 | 60 | M/S LOKENATH CONST | 117.62 | 0 | 0 | 1
330 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte , SM/07977 | Retrofitting | Providing functional household Tap connection under Mahua and adjoining Mouzas Water Supply Scheme at Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | 344/RD/PHE | 01/02/2021 | 60 | J.D.J. ENTERPRISE | 150.74 | 0 | 0 | 1
331 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte , SM/07977 | Retrofitting | office accessories | BP-2022-23-19 | 28/04/2022 | 0 | SAHA CONSTRUCTION | 0.09 | 0 | 0 | 0
332 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte , SM/07977 | Retrofitting | office accessories bill | BP-2022-23-32 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
333 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte , SM/07977 | Retrofitting | office accessories bill | BP-2022-23-31 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
334 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte , SM/07977 | Retrofitting | stationary bill | BP-2022-23-17 | 28/04/2022 | 0 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.09 | 0 | 0 | 0
335 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte , SM/07977 | Retrofitting | Collection of House Hold Details 6 Nos PWSS at Prescribed format through Mobile App/Hard Copy including Geo-Reference as directed by EIC and submission of the same to PHE Dte. in soft copy. | 148/RD/PHE | 20/01/2021 | 30 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. TANAJIT77@GMAIL.COM | 2.63 | 0 | 0 | 0
336 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte , SM/07977 | Retrofitting | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Puria Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Kaliaganj,Capacity- 80 M3/hr. | 1218/RD/PHE | 18/06/2021 | 90 | AJIT PARMANIK | 36.22 | 0 | 0 | 50
337 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte , SM/07977 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Puria and adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | 362/RD/PHE | 04/02/2021 | 40 | UTTAM SAHA | 91.12 | 0 | 0 | 1
338 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under 4 Nos. different Schemes and their adjoining Mouzas water supply scheme in different Block under Raiganj Division, PHE Dte , SM/07977 | Retrofitting | Retrofitting of FHTC with additional Pipe Line at Purba Chutiyakhore PWSS in Chopra Block in connection with retrofitting of FHTC under 4nos different schemes Under Raiganj Division, PHE Dte. | 2658/RD/PHE | 15/09/2023 | 379 | KARTICK BISWAS | 32.47 | 0 | 0 | 50
339 | UTTAR DINAJPUR | Raiganj Division | Arrangement of W/S by Type-IB solar power operated pumping machinery for Anganwadi Centers having no electrical grid power connections and within the command area of PWSS for 162 Nos AWCs. , SM/07933 | Anganwadi | Extending piped water supply to Anganwadi Centres (AWCs) housed in own building through tap connection for 162 Nos. Anganwadi Centers within the District of Uttar Dinajpur. | 1254/RD/PHE | 24/06/2021 | 60 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 215.78 | 126.69 | 58.71 | 0
340 | UTTAR DINAJPUR | Raiganj Division | Arrangement of W/S by Type-IB solar power operated pumping machinery for Anganwadi Centers having no electrical grid power connections and within the command area of PWSS for 162 Nos AWCs. , SM/07933 | Anganwadi | Balance Work in connection with arrangement of w/s by Type-IB solar power operated pumping machinery for Anganwadi Centres having no electrical grid power connections and within the command area of PWSS for 162 Nos. AWCs within the District Of Uttar Dinajpur | 1584/RD/PHE | 02/06/2023 | 30 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 49.46 | 0 | 0 | 10
341 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sariabad and adjoining mouzas Water Supply Scheme In Raiganj Block Under Raiganj Division, P. H. E. Dte. , SM/09179 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Sariabad Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1823/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.69 | 0 | 0 | 0
342 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sariabad and adjoining mouzas Water Supply Scheme In Raiganj Block Under Raiganj Division, P. H. E. Dte. , SM/09179 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Sariabad Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Raiganj Block under Raiganj Division, P.H.E. Dte. | 2079/RD/PHE | 02/11/2021 | 30 | M/S GHOSH CONSTRUCTION | 7.63 | 0 | 0 | 1
343 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sariabad and adjoining mouzas Water Supply Scheme In Raiganj Block Under Raiganj Division, P. H. E. Dte. , SM/09179 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Sariabad Piped Water Supply Scheme And adjoining Mouzas Water Supply Scheme In Raiganj Block under Raiganj Division, P.H.E Dte. | 431/RD/PHE | 16/02/2022 | 30 | M/S ARVI CONSTRUCTION | 7.57 | 0 | 0 | 0
344 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sariabad and adjoining mouzas Water Supply Scheme In Raiganj Block Under Raiganj Division, P. H. E. Dte. , SM/09179 | Retrofitting | Material Requisition To Resource Division | 26/RD/PHE | 06/01/2022 | 0 | Resource Division | 1.7 | 0 | 0 | 0
345 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sariabad and adjoining mouzas Water Supply Scheme In Raiganj Block Under Raiganj Division, P. H. E. Dte. , SM/09179 | Retrofitting | Material Requisition To Resource Division | 1805/RD/PHE | 23/09/2022 | 0 | Resource Division | 2.03 | 0 | 0 | 0
346 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Matikunda (Part-I/II) WSS for installation of FHTC. , SM/09130 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Matikunda for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-I) | 2386/RD/PHE | 24/12/2021 | 30 | M/S LUCKY CONSTRUCTION | 7.89 | 0 | 0 | 0
347 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-II and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09185 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Dharampur-II Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1815/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.94 | 0 | 0 | 0
348 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-II and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09185 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Dharam Zone-Ii Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E Dte. | 485/RD/PHE | 25/02/2022 | 30 | M/S CHOUDHURY CONSTRUCTION | 10.21 | 0 | 0 | 0
349 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-II and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09185 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Dharam Zone-II Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. | 2085/RD/PHE | 02/11/2021 | 30 | M/S CHOUDHURY CONSTRUCTION | 10.38 | 0 | 0 | 1
350 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-II and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09185 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Dharampur Zone-I Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E Dte. | 435/RD/PHE | 16/02/2022 | 30 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 9.16 | 0 | 0 | 0
351 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-II and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09185 | Retrofitting | Material Requisition To Resource Division | 40/RD/PHE | 06/01/2022 | 0 | Resource Division | 2.51 | 0 | 0 | 0
352 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Mahinagar for installation of FHTC. , SM/09156 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of MAHINAGAR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2112/RD/PHE | 03/11/2021 | 30 | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 5.69 | 0 | 0 | 1
353 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Maslandapur for installation of FHTC. , SM/09166 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of MASLANDPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2120/RD/PHE | 03/11/2021 | 30 | CHAITANYA SAMAL | 19.24 | 0 | 0 | 1
354 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Sahavita WSS for installation of FHTC. , SM/09115 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Sahavita Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | 2140/RD/PHE | 12/11/2021 | 30 | M/S P.S. ENTERPRISE | 4.3 | 0 | 0 | 1
355 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Sahavita WSS for installation of FHTC. , SM/09115 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of SAHAVITA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part A) | 2187/RD/PHE | 17/11/2021 | 30 | TAPAN KUMAR DUTTA | 7.31 | 0 | 0 | 0
356 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Lodhon WSS for installation of FHTC (Part-A & B). , SM/09127 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[NM] and adjoining Mouzas Water Supply Scheme In Raiganj Block under Raiganj Division, P.H.E. Dte. | 2071/RD/PHE | 02/11/2021 | 30 | S.B.CONSTRUCTION | 6.49 | 0 | 0 | 100
357 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Lodhon WSS for installation of FHTC (Part-A & B). , SM/09127 | Retrofitting | Route Survey & Preparation of DPR of MARNAI PWSS under Raiganj Division, PHE Dte. | 151/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 3.93 | 0 | 0 | 0
358 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Lodhon WSS for installation of FHTC (Part-A & B). , SM/09127 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[NM] and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E Dte. | 425/RD/PHE | 16/02/2022 | 30 | S.B.CONSTRUCTION | 6.43 | 0 | 0 | 100
359 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Lodhon WSS for installation of FHTC (Part-A & B). , SM/09127 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Lodhon for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | 2197/RD/PHE | 17/11/2021 | 30 | NIMAI DAS | 6.42 | 0 | 0 | 0
360 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Sahavita Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) , SM/10443 | Retrofitting | Restoration of pipe line for providing FHTC for Sahavita water Supply Scheme under Itahar Block under Raiganj Division PHE Dte.(Phase - II) | 1042/RD/PHED | 12/05/2022 | 30 | BITTU ENTERPRISE | 8.68 | 0 | 0 | 1
361 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Kaliganj WSS for installation of FHTC. , SM/09149 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of KALIGANJ Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2108/RD/PHE | 03/11/2021 | 30 | DULAL MAJUMDER | 7.14 | 0 | 0 | 1
362 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe Line for Retrofitting FHTC of Mahadevpur Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) , SM/10450 | Retrofitting | Restoration of Pipe line for Retrofitting FHTC of Mahadevpur piped water Supply Scheme under Raiganj Division P.H.E. Dte. (Phase-II) | 1044/RD/PHED | 12/05/2022 | 30 | SANKAR DAS | 9.39 | 0 | 0 | 1
363 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Sinking 3(Three) nos. of Ground Bored Wells, 300mm diameter x 200mm diameter, 250mtr. Deep Tube Well including proper development and necessary yield for Ground Water Based PWSS for CHOPRA and its adjoining Mouzas Water Supply Scheme under ) of Chopra Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | 396/RD/PHE | 10/02/2022 | 21 | HAQUE CONSTRUCTION | 47.3 | 0 | 0 | 1
364 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Laying Distribution System for CHOPRA and its adjoining Mouza Water Supply Scheme at CHOPRA Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | 394/RD/PHE | 10/02/2022 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION | 228.06 | 0 | 0 | 1
365 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Soil Investigation for Construction of 600 cum capacity 20 Mtr. staging height RCC Over Head Reservoir For Augmentation of Chopra W/S Scheme In Chopra Block In Uttar Dinajpur District. | 1240/RD/PHE | 20/06/2022 | 20 | G. MITRA & ASSOCIATES | 2.39 | 0 | 0 | 0
366 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | 1520\RD | 24/08/2022 | 7 | JUMBO XEROX | 0.1 | 0 | 0 | 0
367 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | 1536\RD | 25/08/2022 | 7 | JUMBO XEROX | 0.1 | 0 | 0 | 0
368 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Material Requisition To Resource Division | 2007/RD/PHE | 16/11/2022 | 0 | Resource Division | 147.27 | 0 | 0 | 0
369 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | xerox bill | BP-2022-23-211 | 04/11/2022 | 0 | JUMBO XEROX | 0.1 | 0 | 0 | 0
370 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | xerox bill | BP-2022-23-209 | 04/11/2022 | 0 | JUMBO XEROX | 0.1 | 0 | 0 | 0
371 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Laying Rising Main pipeline inter-connection of Tubewells including construction of valve chamber and other related works for CHOPRA (augmentation) and its adjoining Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | 395/RD/PHE | 10/02/2022 | 45 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 1.57 | 0 | 0 | 0
372 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Repairing of Pump House at 2nd Tube well site in connection with Augmentation of Chopra piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | 366/RD/PHE | 07/02/2023 | 45 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 2.1 | 0 | 0 | 0
373 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Construction of Pump House (without Toilet) at 3rd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Chopra Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 367/RD/PHE | 07/02/2023 | 45 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 4.12 | 0 | 0 | 0
374 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Chopra , C.C.C of Chopra in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003147552 | 28/04/2023 | 90 | W.B.S.E.D.C.LTD | 5.16 | 0 | 0 | 0
375 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Approach Road including earthwork for roads at 2nd & 3rd Tube Well Site of Chopra Piped Water Supply Scheme in connection with Augmentation of Chopra PWSS under Islampur Sub-Division PHE Dte. | 2253/RD/PHE | 22/12/2022 | 20 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 3.19 | 0 | 0 | 0
376 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Material Requisition To Resource Division | 639/RD/PHE | 23/03/2022 | 0 | Resource Division | 126.92 | 0 | 0 | 0
377 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Material Requisition To Resource Division | 1514/RD/PHE | 22/08/2022 | 0 | Resource Division | 19.32 | 0 | 0 | 0
378 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Providing Functional household Tap Connection for Chopra Water Supply Scheme (under Augmentation) at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 1272/RD/PHE | 24/06/2022 | 1191 | UTTAM SAHA | 119.51 | 0 | 0 | 65
379 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of CHOPRA Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2413/MLMD | 26/09/2022 | 90 | HANNAN BUILDERS PVT. LTD. | 10.76 | 0 | 0 | 100
380 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of CHOPRA Water Supply Scheme T/W no. III in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2414/MLMD | 26/09/2022 | 90 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 10.97 | 0 | 0 | 100
381 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of CHOPRA Water Supply Scheme T/W no.I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2412/MLMD | 26/09/2022 | 90 | HANNAN BUILDERS PVT. LTD. | 10.76 | 0 | 0 | 100
382 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Chopra Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 365/RD/PHE | 07/02/2023 | 45 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 5.04 | 0 | 0 | 100
383 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | hiring of inspection vehicle | BP-2023-24-279 | 16/02/2024 | 0 | DEBASISH GHOSH | 0.4 | 0 | 0 | 0
384 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Construction of Over Head Reservoir(Capacity-600 Cum) of CHOPRA Pipe Water Supply Scheme in connection with Augmentation at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 736/RD/PHE | 15/03/2023 | 365 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 188.99 | 0 | 0 | 80
385 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
386 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under Augmentation of Chopra PWSS at Chopra Block under Raiganj Division,PHE dte. | 2890/RD/PHE | 25/09/2024 | 450 | MOTI INDUSTRIES | 39.68 | 0 | 0 | 50
387 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Balance work for Pipeline crossing, earth filling & other ancillary works at CHOPRA Piped Water Supply Scheme in connection with Augmentation of Chopra PWSS under Islampur Sub-Division under Raiganj Division PHE Dte. | 1689/RD/PHE | 10/06/2024 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 22.38 | 0 | 0 | 0
388 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Laying additional pipe line with FHTC for Augmentation of Chopra Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 2886/RD/PHE | 25/09/2024 | 45 | UTTAM SAHA | 37.35 | 0 | 0 | 0
389 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Providing FHTC in connection with augmentation of Chopra Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division. | 46/RD/PHE | 03/01/2025 | 67 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 23.43 | 0 | 0 | 0
390 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Laying of additional pipeline for improving FHTC at different mouzas at Chopra Piped Water Supply Scheme (In Connection with Augmentation of Chopra PWSS) under Islampur Sub-Division P.H.E. Dte. | 2838/RD/PHE | 23/09/2024 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 27.83 | 0 | 0 | 0
391 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Construction Of Boundary Wall With Gate at 3rd Tube-Well Site in connection with Augmentation of Chopra PWSS at Chopra Block under Raiganj Division, PHE Dte. | 3297/RD/PHE | 20/11/2024 | 166 | M C CONSTRUCTION | 5.55 | 0 | 0 | 100
392 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Chopra Water Supply Scheme. , SM/10129 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chopra Water Supply Scheme (Augmentation) at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 105 M3/hr. | 2504/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 43.83 | 0 | 0 | 0
393 | UTTAR DINAJPUR | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Chopra and Goalpokhar-II in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. , SM/11520 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Chopra & Goalpokhor-II Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1283/RD/PHE | 08/05/2023 | 92 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 656.06 | 0 | 0 | 30
394 | UTTAR DINAJPUR | Raiganj Division | DPR for source augmentation for Biprit Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12638 | Augmentation | Material Requisition To Resource Division | 2392/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.57 | 0 | 0 | 0
395 | UTTAR DINAJPUR | Malda Mechanical | DPR for source augmentation for Biprit Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12638 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Biprit Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015258) | 2472/MLMD | 04/08/2023 | 907 | M/S SABANA CONSTRUCTION | 10.8 | 0 | 0 | 84
396 | UTTAR DINAJPUR | Raiganj Division | DPR for source augmentation for Biprit Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12638 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Biprit Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1927/RD/PHE | 28/10/2022 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 33.13 | 0 | 0 | 60
397 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Gutin Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12642 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Gutin PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003279197 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 3.62 | 0 | 0 | 100
398 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Gutin Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12642 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Gutin Piped Water Supply Scheme of Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1916/RD/PHE | 28/10/2022 | 881 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 39.77 | 0 | 0 | 75
399 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Gutin Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12642 | Augmentation | Material Requisition To Resource Division | 15/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
400 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME , SM/11725 | Augmentation | FHTC (Functional Household Tap Connection) for Marnai Water Supply Scheme [Augmentation Scheme] in Raiganj Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2029/RD/PHE | 17/11/2022 | 90 | M/S LOKENATH CONSTRUCTION | 79.34 | 0 | 0 | 0
401 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME , SM/11725 | Augmentation | Material Requisition To Resource Division | 12/RD/PHE | 04/01/2023 | 0 | Resource Division | 58.04 | 0 | 0 | 0
402 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME , SM/11725 | Augmentation | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Marnai Water Supply Scheme at Itahar Block Under Raiganj Division, P.H.E Dte. | 407/RD/PHE | 09/02/2023 | 45 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 3.53 | 0 | 0 | 0
403 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME , SM/11725 | Augmentation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Augmentation of Marnai Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011652) | 3872/MLMD | 18/12/2023 | 1915 | SHREE BISHNU CONSTRUCTION | 6.98 | 0 | 0 | 85
404 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME , SM/11725 | Augmentation | Supply, installation, commissioning and trial run of electro-mechanical components of Augmentation of MARNAI Water Supply Scheme T/W no. III in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2944/MLMD | 11/09/2024 | 90 | S.P. ENTERPRISE (KOLKATA) | 10.56 | 0 | 0 | 0
405 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME , SM/11725 | Augmentation | Quotation for new service connection at MARNAI PH-III (Itahar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-62 | 09/04/2024 | 0 | W.B.S.E.D.C.LTD | 6.97 | 0 | 0 | 0
406 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME , SM/11725 | Augmentation | Augmentation work of MARNAI and it's adjoining mouzas Piped Water Supply Scheme at Itahar Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | 1546/RD/PHE | 26/08/2022 | 1118 | M/S LOKENATH CONSTRUCTION | 354.98 | 0 | 0 | 55
407 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME , SM/11725 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of MARNAI Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011419) | 2204/MLMD | 18/07/2023 | 894 | MERCURY ENGINEERING COMPANY. | 10.53 | 0 | 0 | 81
408 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME , SM/11725 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of MARNAI Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011419) | 2205/MLMD | 18/07/2023 | 533 | MANIK CHANDRA SAHA. | 10.38 | 0 | 0 | 100
409 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME , SM/11725 | Augmentation | Construction of Pump House (size 4.10 m x 3.50 m outer to outer) with sanitary and water supply arrangement according to departmental drawing with toilet at 3nd Tube-Well Site in connection with Augmentation of Marnai PWSS | 2363/RD/PHE | 11/08/2023 | 60 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 5.02 | 0 | 0 | 0
410 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME , SM/11725 | Augmentation | Construction of Approach Road,Boundary Wall,Fhtc And Other Allied Works Of Marnai Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3573/RD/PHE | 05/12/2024 | 91 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 41.84 | 0 | 0 | 0
411 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF MARNAI PIPED WATER SUPPLY SCHEME , SM/11725 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Marnai Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | 2207/RD/PHE | 29/07/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 33.6 | 0 | 0 | 0
412 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11798 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of SARIABAD Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte | 781/MLMD | 27/04/2023 | 90 | NEOGI ENTERPRISE. | 10.38 | 0 | 0 | 0
413 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11798 | Augmentation | Construction of Pump house for (5.4 x 3.6) at Head work site of Sariabad Augmentation Water Supply Schemes under Raiganj Block under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 388/RD/PHE | 07/02/2023 | 45 | SANTOSI ENTERPRISE AMIT.RAIGANJ@GMAIL.COM | 5.79 | 0 | 0 | 100
414 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11798 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T.W.No. I of Sariabad pwss, Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003055164 | 28/12/2022 | 7 | W.B.S.E.D.C.LTD | 0.55 | 0 | 0 | 0
415 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11798 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of SARIABAD Water Supply Scheme T/W no. III in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 1115/MLMD | 23/06/2023 | 90 | ANIMA ENTERPRISE | 10.55 | 0 | 0 | 100
416 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11798 | Augmentation | Material Requisition To Resource Division | 1949/RD/PHE | 04/11/2022 | 0 | Resource Division | 33.5 | 0 | 0 | 0
417 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11798 | Augmentation | Augmentation of SARIABAD Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | 1549/RD/PHE | 26/08/2022 | 930 | TAPAN KUMAR DUTTA | 152.36 | 0 | 0 | 90
418 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11798 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of SARIABAD Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 782/MLMD | 27/04/2023 | 796 | M/S SAJAHAN CHOWDHURY | 10.38 | 0 | 0 | 81
419 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11798 | Augmentation | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Sariyabad PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3749/RD/PHED | 18/12/2024 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 37.92 | 0 | 0 | 75
420 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11798 | Augmentation | Balance distribution System of Laying pipeline with Construction of Boundary Wall With Gate at Head Work Site, & 2nd Tube-Well Site under Augmentation of Sariabad PWSS at Raiganj Block under Raiganj Division, PHE dte. | 2888/RD/PHE | 25/09/2024 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 37.18 | 0 | 0 | 0
421 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11798 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Sariabad Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 60 M3/hr. | 1659/RD/PHE | 23/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.57 | 0 | 0 | 0
422 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11798 | Augmentation | FHTC (Functional Household Tap Connection) for Sariabad Water Supply Scheme [Augmentation Scheme] in Raiganj Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2031/RD/PHE | 17/11/2022 | 930 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 44.4 | 0 | 0 | 67
423 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11798 | Augmentation | Repairing of Pump House of 2nd Tube Well and 3rd Tube Well Site of Sariabad Augmentation Water Supply Scheme at Raiganj Block under Raiganj Division P.H.E Dte. | 401/RD/PHE | 08/02/2023 | 450 | LAXMI CONSTRUCTION NAMEDUTTA@GMAIL.COM | 3.31 | 0 | 0 | 80
424 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Sariabad in Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11798 | Augmentation | Construction of Over Head Reservoir(Capacity-300 Cum) of SARIABAD Pipe Water Supply Scheme in connection with Augmentation at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 657/RD/PHE | 03/03/2023 | 690 | VISCOUS ENGINEERS PVT. LTD. | 84.86 | 0 | 0 | 82
425 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe Line for providing FHTC for Lodhan Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) , SM/10425 | Retrofitting | Restoration of Pipeline for Providing FHTC for LODHON Water Supply Scheme under Raiganj Division, P.H.E Dte (Phase - II) | 1034/RD/PHED | 12/05/2022 | 30 | RAHUL ENTERPRISE | 5.51 | 0 | 0 | 1
426 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Piplan Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10499 | Retrofitting | Restoration of Pipe Line For Providing FHTC for Piplan Water Supply Scheme under Raiganj Block under Raiganj Division P.H.E. Dte. In The District of Uttar Dinajpur. (Phase - II) | 1043/RD/PHED | 12/05/2022 | 30 | DAS CONSTRUCTION COMPANY | 7.82 | 0 | 0 | 100
427 | UTTAR DINAJPUR | Raiganj Division | Source augmentation for Ghirnigaon Khas Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12647 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Ghirnigaon Khas Piped Water Supply Scheme of Chopra Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1925/RD/PHE | 28/10/2022 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 33.2 | 0 | 0 | 0
428 | UTTAR DINAJPUR | Raiganj Division | Source augmentation for Ghirnigaon Khas Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12647 | Augmentation | Material Requisition To Resource Division | 2398/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.48 | 0 | 0 | 0
429 | UTTAR DINAJPUR | Malda Mechanical | Source augmentation for Ghirnigaon Khas Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12647 | Augmentation | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. III of Ghirnigaonkhas Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015286) | 2367/MLMD | 28/07/2023 | 944 | SOVON KUMAR DAS. | 10.57 | 0 | 0 | 87
430 | UTTAR DINAJPUR | Raiganj Division | KATAGAON Piped Water Supply Scheme at Chopra Block , SM/12082 | New | Material Requisition To Resource Division | 1038/RD/PHE | 04/04/2023 | 0 | Resource Division | 24.58 | 0 | 0 | 0
431 | UTTAR DINAJPUR | Malda Mechanical | KATAGAON Piped Water Supply Scheme at Chopra Block , SM/12082 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Katagaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014361) | 2209/MLMD | 18/07/2023 | 810 | MERCURY ENGINEERING COMPANY. | 27.22 | 0 | 0 | 74
432 | UTTAR DINAJPUR | Malda Mechanical | KATAGAON Piped Water Supply Scheme at Chopra Block , SM/12082 | New | Quotation for new service connection at KATAGAON PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12082) | BP-2024-25-311 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 16.37 | 0 | 0 | 0
433 | UTTAR DINAJPUR | Malda Mechanical | KATAGAON Piped Water Supply Scheme at Chopra Block , SM/12082 | New | Quotation for new service connection at KATAGAON PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12082) | BP-2024-25-312 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 5.31 | 0 | 0 | 0
434 | UTTAR DINAJPUR | Raiganj Division | KATAGAON Piped Water Supply Scheme at Chopra Block , SM/12082 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
435 | UTTAR DINAJPUR | Raiganj Division | KATAGAON Piped Water Supply Scheme at Chopra Block , SM/12082 | New | Providing FHTC in connection with Katagaon Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 1174/RD/PHE | 23/04/2025 | 15 | DIPANKAR SARKAR | 6.94 | 0 | 0 | 0
436 | UTTAR DINAJPUR | Raiganj Division | KATAGAON Piped Water Supply Scheme at Chopra Block , SM/12082 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at KATAGAON PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | 2161/RD/PHE | 23/07/2025 | 180 | M/S SACHIN KUMAR | 32.55 | 0 | 0 | 0
437 | UTTAR DINAJPUR | Raiganj Division | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13739 | New | Material Requisition To Resource Division | 598/RD/PHE | 27/02/2023 | 0 | Resource Division | 43.88 | 0 | 0 | 0
438 | UTTAR DINAJPUR | Raiganj Division | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13739 | New | Protection and restoration work of damaged flank caused by excavation for water supply project of PHE of Islampur- Amaljhari- Sonamoti Road under Uttar Dinajpur division, PWD. | BILL/00506/2023 | 30/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 7.97 | 0 | 0 | 0
439 | UTTAR DINAJPUR | Raiganj Division | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13739 | New | Implementation of KHABARGAON and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 567/RD/PHE | 23/02/2023 | 1133 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 496.73 | 0 | 0 | 50
440 | UTTAR DINAJPUR | Malda Mechanical | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13739 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Khabargaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015710) | 2511/MLMD | 04/08/2023 | 937 | SUBHAS CHANDRA KESHORI | 28.32 | 0 | 0 | 75
441 | UTTAR DINAJPUR | Raiganj Division | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13739 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KHABARGAON PWSS at Islampur Block under Raiganj Division, PHE Dte. | 608/RD/PHE | 05/03/2024 | 45 | DUTTA BUILDERS | 22.51 | 0 | 0 | 0
442 | UTTAR DINAJPUR | Malda Mechanical | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13739 | New | Quotation for new service connection at KHABARGAON PH-II (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/13739) | BP-2024-25-271 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 5.42 | 0 | 0 | 0
443 | UTTAR DINAJPUR | Raiganj Division | KHABARGAON PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13739 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Khabargaon Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | 1949/RD/PHE | 01/07/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.36 | 0 | 0 | 0
444 | UTTAR DINAJPUR | Raiganj Division | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. , SM/11897 | New | Material Requisition To Resource Division | 574/RD/PHE | 23/02/2023 | 0 | Resource Division | 31.27 | 0 | 0 | 0
445 | UTTAR DINAJPUR | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. , SM/11897 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Laksmania, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-566 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 0.65 | 0 | 0 | 0
446 | UTTAR DINAJPUR | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. , SM/11897 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Laksmania, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-565 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 0.54 | 0 | 0 | 0
447 | UTTAR DINAJPUR | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. , SM/11897 | New | Additional Quotation for TW-II of Laksmania Water supply scheme in the district of Uttar Dinajpur. | BP-2024-25-488 | 09/09/2024 | 0 | W.B.S.E.D.C.LTD | 0.23 | 0 | 0 | 0
448 | UTTAR DINAJPUR | Raiganj Division | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. , SM/11897 | New | Implementation of Laksmania and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1306/RD/PHE | 12/05/2023 | 965 | UNIVERSAL ENTERPRISES | 279.7 | 0 | 0 | 70
449 | UTTAR DINAJPUR | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. , SM/11897 | New | Making compound lighting arrangement with allied works at T/W no. I of Laksmania Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011694) | 2231/MLMD | 18/07/2023 | 810 | M/S PARIMAL DAS. | 3.83 | 0 | 0 | 0
450 | UTTAR DINAJPUR | Raiganj Division | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. , SM/11897 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under LAKSMANIA Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 572/RD/PHE | 05/03/2024 | 390 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 22.58 | 0 | 0 | 85
451 | UTTAR DINAJPUR | Raiganj Division | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. , SM/11897 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd Tubewell Site and road restoration of Laksmania PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 1606/RD/PHE | 17/06/2025 | 120 | SARVATAH PROJECTS PRIVATE LIMITED | 39.5 | 0 | 0 | 0
452 | UTTAR DINAJPUR | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. , SM/11897 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of LAKSMANIA Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011694) | 2197/MLMD | 18/07/2023 | 585 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 11.3 | 0 | 0 | 100
453 | UTTAR DINAJPUR | Malda Mechanical | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. , SM/11897 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of LAKSMANIA Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011694) | 2198/MLMD | 18/07/2023 | 592 | HANNAN BUILDERS PVT. LTD. | 11.3 | 0 | 0 | 100
454 | UTTAR DINAJPUR | Raiganj Division | LAKSMANIA Piped water supply scheme in Raiganj block in Uttar Dinajpur District. , SM/11897 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
455 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Chandol Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/13021 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Chandol Piped Water Supply Scheme of Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1913/RD/PHE | 28/10/2022 | 405 | M/S PIONEER ENTERPRISE | 34.31 | 0 | 0 | 30
456 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Chandol Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/13021 | Augmentation | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. III of Source augmentation of Chandol Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015274) | 2365/MLMD | 28/07/2023 | 180 | PABITRA MANDAL | 10.54 | 0 | 0 | 100
457 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Chandol Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/13021 | Augmentation | Material Requisition To Resource Division | 08/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
458 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Chandol Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/13021 | Augmentation | Quotation for new service connection at Chandol PH-III (Itahar ccc) | BP-2023-24-534 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 3.47 | 0 | 0 | 0
459 | UTTAR DINAJPUR | Malda Mechanical | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12786 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Jharbari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014422) | 2368/MLMD | 28/07/2023 | 180 | SUNRISE ENGINEERING CORPORATION. | 27.23 | 0 | 0 | 0
460 | UTTAR DINAJPUR | Raiganj Division | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12786 | New | Material Requisition To Resource Division | 1124/RD/PHE | 24/04/2023 | 0 | Resource Division | 36.54 | 0 | 0 | 0
461 | UTTAR DINAJPUR | Malda Mechanical | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12786 | New | Quotation for new service connection at JHARBARI PH-II (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-89 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 6.69 | 0 | 0 | 0
462 | UTTAR DINAJPUR | Raiganj Division | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12786 | New | Providing FHTC in connection with Jharbari Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 1176/RD/PHE | 23/04/2025 | 30 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 12.6 | 0 | 0 | 0
463 | UTTAR DINAJPUR | Raiganj Division | JHARBARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12786 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Jharbari Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | 2012/RD/PHE | 08/07/2025 | 180 | AJIT PRAMANIK | 30.93 | 0 | 0 | 0
464 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Barobilla for installation of FHTC. , SM/09135 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Barobilla Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2151/RD/PHE | 12/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 2.17 | 0 | 0 | 0
465 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Noabari for installation of FHTC. , SM/09159 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of NOABARI Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2115/RD/PHE | 03/11/2021 | 30 | MAA BICHITRA CONSTRUCTION | 13.93 | 0 | 0 | 1
466 | UTTAR DINAJPUR | Malda Mechanical | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/13795 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of JAGATAGAON, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003215033 | 23/08/2023 | 90 | W.B.S.E.D.C.LTD | 5.01 | 0 | 0 | 100
467 | UTTAR DINAJPUR | Malda Mechanical | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/13795 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of JAGATAGAON, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003215012 | 23/08/2023 | 90 | W.B.S.E.D.C.LTD | 8.89 | 0 | 0 | 100
468 | UTTAR DINAJPUR | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/13795 | New | Material Requisition To Resource Division | 581/RD/PHE | 24/02/2023 | 0 | Resource Division | 75.77 | 0 | 0 | 0
469 | UTTAR DINAJPUR | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/13795 | New | Protection and Restoration work of damaged flank caused by excavation for water supply project of PHE of Matikunda- Moragoti Road under uttar dinajpur division, PWD. | BP-2023-24-143 | 30/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 9.23 | 0 | 0 | 0
470 | UTTAR DINAJPUR | Malda Mechanical | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/13795 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I, II & III and making compound lighting arrangement at T/W no. I of Jagatgaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013510) | 2443/MLMD | 04/08/2023 | 1027 | GHOSH BROTHERS... | 39.57 | 0 | 0 | 77
471 | UTTAR DINAJPUR | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/13795 | New | Construction of concrete pathway with earth filling at Head Work Site Pump House & 2nd TW Site Pump House for JAGTAGAON Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHE Dte,U/D. | 3304/RD/PHE | 20/11/2024 | 30 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 9.63 | 0 | 0 | 0
472 | UTTAR DINAJPUR | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/13795 | New | Implementation of JAGATGAON and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division. | 289/RD/PHE | 01/02/2023 | 1307 | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 910.72 | 0 | 0 | 60
473 | UTTAR DINAJPUR | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/13795 | New | Additional pipeline and other ancillary works at Jagtagaon piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | 3303/RD/PHE | 20/11/2024 | 135 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 49.57 | 0 | 0 | 0
474 | UTTAR DINAJPUR | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/13795 | New | Construction of Boundary Wall with Gate at Head Work Site, 2nd & 3rd Tube-Well Site under JAGATAGAON Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 561/RD/PHE | 05/03/2024 | 360 | M/S RATAN SARKAR & SON | 27.68 | 0 | 0 | 85
475 | UTTAR DINAJPUR | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/13795 | New | Providing FHTC in connection with Jagtagaon Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 55/RD/PHE | 03/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 5.98 | 0 | 0 | 0
476 | UTTAR DINAJPUR | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/13795 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
477 | UTTAR DINAJPUR | Raiganj Division | JAGATAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/13795 | New | Trial Run For Jagtagaon PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | 550/RD/PHE | 12/02/2025 | 90 | CHAPDUAR LABOUR CO- OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 0.87 | 0 | 0 | 0
478 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Providing FHTC at village-Kamat of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 771/RD/PHE | 17/03/2023 | 60 | PANDIT CONSTRUCTION PANDIT.RNJ@GMAIL.COM | 15.4 | 0 | 0 | 0
479 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Providing FHTC at village-Pargaon of ALIANAGAR Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division. | 876/RD/PHE | 27/03/2023 | 60 | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 17.46 | 0 | 0 | 0
480 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Material Requisition To Resource Division | 1318/RD/PHE | 12/05/2023 | 0 | Resource Division | 46.84 | 0 | 0 | 0
481 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Raniganj, 2. Alianagar in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 542/RD/PHE | 22/02/2023 | 628 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 51.42 | 0 | 0 | 80
482 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Alianagar PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3766/RD/PHED | 18/12/2024 | 45 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 33.63 | 0 | 0 | 0
483 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. | BP-2024-25-11 | 08/04/2024 | 0 | M/S DILWAR HOSAIN | 0.07 | 0 | 0 | 0
484 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. | BP-2024-25-15 | 08/04/2024 | 0 | M/S DILWAR HOSAIN | 0.05 | 0 | 0 | 0
485 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. | BP-2024-25-12 | 08/04/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
486 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. | BP-2024-25-14 | 08/04/2024 | 0 | M/S DILWAR HOSAIN | 0.09 | 0 | 0 | 0
487 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. | BP-2024-25-13 | 08/04/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
488 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Construction of boundary wall and Pump house at 2nd Tube-well site of Aliangar Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 766/RD/PHE | 17/03/2023 | 702 | M/S UNIQUE 13 | 11.28 | 0 | 0 | 100
489 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Laying of pipe line at village-Kamat of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 761/RD/PHE | 17/03/2023 | 720 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 49.21 | 0 | 0 | 35
490 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Laying of pipe line at village-Pargaon of ALIANAGAR Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 871/RD/PHE | 27/03/2023 | 723 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 49.76 | 0 | 0 | 35
491 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Construction of OHR(Capacity-300Cum) of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 1020/RD/PHE | 31/03/2023 | 275 | MS SANDHYA CONSTRUCTION | 96.8 | 0 | 0 | 35
492 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Providing FHTC of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 951/RD/PHE | 29/03/2023 | 600 | M/S GHOSH CONSTRUCTION GHOSH1.RNJ@GMAIL.COM | 16.85 | 0 | 0 | 0
493 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Laying of pipe line at village-Alianagar of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 946/RD/PHE | 29/03/2023 | 750 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 45.14 | 0 | 0 | 37
494 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Laying distribution of pipe line of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 817/RD/PHE | 22/03/2023 | 705 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 49.51 | 0 | 0 | 40
495 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Providing FHTC at village-Pargaon and Kamat of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 956/RD/PHE | 29/03/2023 | 660 | M/S ARVI CONSTRUCTION | 18.26 | 0 | 0 | 0
496 | UTTAR DINAJPUR | Malda Mechanical | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Alianagar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017531) | 2458/MLMD | 04/08/2023 | 840 | M/S D.G.B. ENTERPRISE. | 24.89 | 0 | 0 | 67
497 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | 1816/RD/PHE | 26/06/2024 | 198 | MD ZAFAR EQUEBAL | 2.6 | 0 | 0 | 100
498 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.Vehicle no. WB74AP 7552) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month( period from 27.11.2024 to 26.05.2025). | 3446/RD/PHE | 26/11/2024 | 181 | M/S SARKAR ENTERPRISE SILIGURI | 2.4 | 0 | 0 | 0
499 | UTTAR DINAJPUR | Malda Mechanical | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 4337/MLMD | 31/12/2024 | 59 | NITAI PANDEY | 0.77 | 0 | 0 | 100
500 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Alianagar Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | 2484/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 30.93 | 0 | 0 | 0
501 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Laying of Rising Main of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 855/RD/PHE | 24/03/2023 | 660 | M/S DAS ENTERPRISE SUMAN974967@GMAIL.COM | 4.58 | 0 | 0 | 10
502 | UTTAR DINAJPUR | Raiganj Division | ALIANAGAR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14164 | New | Construction of boundary wall and Pump house at head work site of ALIANAGAR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 823/RD/PHE | 22/03/2023 | 539 | GULJAN BEGAM | 24.87 | 0 | 0 | 100
503 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Gunabari Piped Water Suppply Scheme under Islampur block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14228 | Augmentation | Rig Bored Tube-Well In connection with Source Augmentation In Different Piped Water Supply Scheme 1.Debiganj, 2.Gunabari, 3. Majlishpur. 4. Sripur in the District of Uttar Dinajpur Under Raiganj Division, P.H.E. Dte. | 470/RD/PHE | 16/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI | 42.57 | 0 | 0 | 100
504 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Gunabari Piped Water Suppply Scheme under Islampur block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14228 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Gunabari, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003268843 | 10/11/2023 | 90 | W.B.S.E.D.C.LTD | 4.53 | 0 | 0 | 100
505 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Gunabari Piped Water Suppply Scheme under Islampur block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14228 | Augmentation | Material Requisition To Resource Division | 2394/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.4 | 0 | 0 | 0
506 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Gunabari Piped Water Suppply Scheme under Islampur block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14228 | Augmentation | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Gunabari Piped Water Supply Scheme of Islampur Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 58/RD/PHE | 16/01/2023 | 562 | JEET CONSTRUCTION UKILPARA CTNJIT38@GMAIL.COM | 17.58 | 0 | 0 | 100
507 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Gunabari Piped Water Suppply Scheme under Islampur block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14228 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Gunabari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016494) | 2504/MLMD | 04/08/2023 | 360 | BASUDEV GHOSH. | 10.9 | 0 | 0 | 100
508 | UTTAR DINAJPUR | Raiganj Division | MANORA Piped Water Supply Scheme , SM/15126 | New | Material Requisition To Resource Division | 976/RD/PHE | 30/03/2023 | 0 | Resource Division | 97.5 | 0 | 0 | 0
509 | UTTAR DINAJPUR | Malda Mechanical | MANORA Piped Water Supply Scheme , SM/15126 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I, II & III and making compound lighting arrangement at T/W no. I of Manora Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015952) | 2448/MLMD | 04/08/2023 | 1027 | GHOSH BROTHERS... | 39.3 | 0 | 0 | 0
510 | UTTAR DINAJPUR | Raiganj Division | MANORA Piped Water Supply Scheme , SM/15126 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
511 | UTTAR DINAJPUR | Raiganj Division | MANORA Piped Water Supply Scheme , SM/15126 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Manora Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | 1798/RD/PHE | 24/06/2025 | 180 | S. DUTTA | 36.38 | 0 | 0 | 0
512 | UTTAR DINAJPUR | Raiganj Division | GODASAMAL Piped Water Supply Scheme , SM/15128 | New | Material Requisition To Resource Division | 889/RD/PHE | 27/03/2023 | 0 | Resource Division | 50.62 | 0 | 0 | 0
513 | UTTAR DINAJPUR | Malda Mechanical | GODASAMAL Piped Water Supply Scheme , SM/15128 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Godasamal Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016367) | 2503/MLMD | 04/08/2023 | 907 | GHOSH BROTHERS... | 39.8 | 0 | 0 | 77
514 | UTTAR DINAJPUR | Raiganj Division | GODASAMAL Piped Water Supply Scheme , SM/15128 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
515 | UTTAR DINAJPUR | Malda Mechanical | GODASAMAL Piped Water Supply Scheme , SM/15128 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte | 3015/MLMD | 18/09/2024 | 61 | RAMCHANDRA BASAK | 0.78 | 0 | 0 | 100
516 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Mahua Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14232 | Augmentation | Material Requisition To Resource Division | 2395/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.4 | 0 | 0 | 0
517 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Mahua Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14232 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Mahua Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016477) | 2522/MLMD | 04/08/2023 | 120 | JIBU SINGHA | 10.9 | 0 | 0 | 84
518 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Mahua Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14232 | Augmentation | Quotation for new service connection at Source Augmentation of MAHUA PH-III (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/14232) | BP-2024-25-569 | 14/11/2024 | 0 | W.B.S.E.D.C.LTD | 6.89 | 0 | 0 | 0
519 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Mahua Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14232 | Augmentation | Rig Bored Tube-Well in connection with Source Augmentation In Different Piped Water Supply Scheme 1.Mohua, 2. Pawakhali, 3. Pokheria in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 471/RD/PHE | 16/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI | 31.92 | 0 | 0 | 80
520 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Mahua Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14232 | Augmentation | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Mahua Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 59/RD/PHE | 16/01/2023 | 854 | SUDIP MITRA SUDIP.RNJ@GMAIL.COM | 17.67 | 0 | 0 | 100
521 | UTTAR DINAJPUR | Raiganj Division | BHOTAMARI Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/14239 | New | Material Requisition To Resource Division | 970/RD/PHE | 29/03/2023 | 0 | Resource Division | 62.76 | 0 | 0 | 0
522 | UTTAR DINAJPUR | Malda Mechanical | BHOTAMARI Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/14239 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Bhotamari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015735) | 2466/MLMD | 04/08/2023 | 960 | MERCURY ENGINEERING COMPANY. | 42.69 | 0 | 0 | 79
523 | UTTAR DINAJPUR | Malda Mechanical | BHOTAMARI Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/14239 | New | Quotation for new service connection at BHOTAMARI PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/14239) | BP-2024-25-299 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 5.14 | 0 | 0 | 0
524 | UTTAR DINAJPUR | Malda Mechanical | BHOTAMARI Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/14239 | New | Quotation for new service connection at BHOTAMARI PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/14239) | BP-2024-25-300 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 5.52 | 0 | 0 | 0
525 | UTTAR DINAJPUR | Raiganj Division | BHOTAMARI Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/14239 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
526 | UTTAR DINAJPUR | Raiganj Division | BHOTAMARI Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/14239 | New | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at BHOTAMARI PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | 1206/RD/PHE | 25/04/2025 | 45 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 76.36 | 0 | 0 | 0
527 | UTTAR DINAJPUR | Raiganj Division | BHOTAMARI Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/14239 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Botamari Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | 1926/RD/PHE | 30/06/2025 | 180 | RHYNO INFRASTRUCTURE | 36.34 | 0 | 0 | 0
528 | UTTAR DINAJPUR | Malda Mechanical | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. , SM/15146 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of CHAPDUAR, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003196234 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 11.07 | 0 | 0 | 100
529 | UTTAR DINAJPUR | Malda Mechanical | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. , SM/15146 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of CHAPDUAR, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003196218 | 29/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.7 | 0 | 0 | 100
530 | UTTAR DINAJPUR | Raiganj Division | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. , SM/15146 | New | Material Requisition To Resource Division | 2235/RD/PHE | 02/08/2023 | 0 | Resource Division | 32.15 | 0 | 0 | 0
531 | UTTAR DINAJPUR | Malda Mechanical | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. , SM/15146 | New | shifting/Reorientation of 1 no 25 KVA DTR on Safety ground at Tubewell site-I of Chapduar water supply scheme under Birnagar CCC in the District of Uttar Dinajpur | BP-2024-25-566 | 29/10/2024 | 0 | W.B.S.E.D.C.LTD | 1.06 | 0 | 0 | 0
532 | UTTAR DINAJPUR | Malda Mechanical | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. , SM/15146 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Chapduar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018241) | 2740/MLMD | 14/08/2023 | 987 | HANNAN BUILDERS PVT. LTD. | 25.98 | 0 | 0 | 89
533 | UTTAR DINAJPUR | Raiganj Division | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. , SM/15146 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | 1746/RD/PHE | 14/06/2024 | 198 | DEBASISH GHOSH | 2.6 | 0 | 0 | 0
534 | UTTAR DINAJPUR | Raiganj Division | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. , SM/15146 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chapduar PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3741/RD/PHE | 18/12/2024 | 135 | UTTAM SAHA | 21.16 | 0 | 0 | 0
535 | UTTAR DINAJPUR | Raiganj Division | CHAPDUAR Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. , SM/15146 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAPDUAR PWSS at Raiganj Block under Raiganj Division, PHE Dte. | 652/RD/PHE | 05/03/2024 | 77 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 22.58 | 0 | 0 | 100
536 | UTTAR DINAJPUR | Raiganj Division | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16219 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
537 | UTTAR DINAJPUR | Raiganj Division | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16219 | New | Material Requisition To Resource Division | 808/RD/PHE | 21/03/2023 | 0 | Resource Division | 46.32 | 0 | 0 | 0
538 | UTTAR DINAJPUR | Raiganj Division | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16219 | New | Implementation of HARINARAYANPUR(Zone- I) and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1275/RD/PHE | 08/05/2023 | 969 | UJJWAL DAS | 344.33 | 0 | 0 | 50
539 | UTTAR DINAJPUR | Malda Mechanical | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16219 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Harinarayanpur Zone-I Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018695) | 2750/MLMD | 14/08/2023 | 180 | DAS CONSTRUCTION | 24.35 | 0 | 0 | 89
540 | UTTAR DINAJPUR | Malda Mechanical | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16219 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Harinarayanpur (Zone-I), Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-635 | 06/03/2024 | 0 | W.B.S.E.D.C.LTD | 0.45 | 0 | 0 | 0
541 | UTTAR DINAJPUR | Malda Mechanical | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16219 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Harinarayanpur (Zone-I), Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-634 | 06/03/2024 | 0 | W.B.S.E.D.C.LTD | 0.56 | 0 | 0 | 0
542 | UTTAR DINAJPUR | Raiganj Division | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16219 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under HARINARAYANPUR ZONE-I PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 1710/RD/PHE | 10/06/2024 | 45 | ADYA MAA CONSTRUCTION | 24.47 | 0 | 0 | 100
543 | UTTAR DINAJPUR | Raiganj Division | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16219 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Harinarayanpur Zone-1 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 22/RD/PHE | 02/01/2025 | 45 | UJJWAL DAS | 47.1 | 0 | 0 | 0
544 | UTTAR DINAJPUR | Raiganj Division | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16219 | New | Trial Run For Harinarayanpur Zone-I PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 month | 534/RD/PHE | 12/02/2025 | 90 | UJJWAL DAS | 0.88 | 0 | 0 | 0
545 | UTTAR DINAJPUR | Raiganj Division | Harinarayanpur Zone-I Piped Water Supply Scheme at Hemtabad Block under Utar Dinajpur District. , SM/16219 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Harinarayanpur Zone-I Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Block:- Raiganj,Capacity- 45 M3/hr. | 1628/RD/PHE | 19/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 19.35 | 0 | 0 | 0
546 | UTTAR DINAJPUR | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/16258 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
547 | UTTAR DINAJPUR | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/16258 | New | Material Requisition To Resource Division | 2242/RD/PHE | 02/08/2023 | 0 | Resource Division | 44.72 | 0 | 0 | 0
548 | UTTAR DINAJPUR | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/16258 | New | Implementation of CHAINAGAR and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 749/RD/PHE | 16/03/2023 | 665 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 358.48 | 0 | 0 | 58
549 | UTTAR DINAJPUR | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/16258 | New | Arrangement for erection of display board for different piped water supply schemes (1.Jagadishpur PWSS, 2.Chainagar PWSS, 3.Hemtabad Zone-II PWSS) under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | BP-2024-25-254 | 07/10/2024 | 0 | M/S MANDAL ENTERPRISE | 0.1 | 0 | 0 | 0
550 | UTTAR DINAJPUR | Malda Mechanical | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/16258 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of Chainagar PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-466 | 26/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.62 | 0 | 0 | 0
551 | UTTAR DINAJPUR | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/16258 | New | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | BP-2024-25-25 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 11.85 | 0 | 0 | 0
552 | UTTAR DINAJPUR | Malda Mechanical | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/16258 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.II of Chainagar PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-467 | 26/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.94 | 0 | 0 | 0
553 | UTTAR DINAJPUR | Malda Mechanical | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/16258 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite at T/W no. I of Chainagar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017839) | 2481/MLMD | 04/08/2023 | 575 | MUKHERJEE ART CENTRE | 25.2 | 0 | 0 | 85
554 | UTTAR DINAJPUR | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/16258 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAINAGAR PWSS at HEMTABAD Block under Raiganj Division, PHE Dte. | 545/RD/PHE | 05/03/2024 | 45 | MAA MANASHA ENGINEERS | 11.28 | 0 | 0 | 100
555 | UTTAR DINAJPUR | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/16258 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chainagar PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3745/RD/PHE | 18/12/2024 | 135 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 46.37 | 0 | 0 | 0
556 | UTTAR DINAJPUR | Raiganj Division | Chainagar Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/16258 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAINAGAR PWSS at HEMTABAD Block under Raiganj Division, PHE Dte. | 544/RD/PHE | 05/03/2024 | 45 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 11.28 | 0 | 0 | 100
557 | UTTAR DINAJPUR | Raiganj Division | BILASPUR Piped Water Supply Scheme , SM/16563 | New | Material Requisition To Resource Division | 632/RD/PHE | 02/03/2023 | 0 | Resource Division | 38.8 | 0 | 0 | 0
558 | UTTAR DINAJPUR | Malda Mechanical | BILASPUR Piped Water Supply Scheme , SM/16563 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Bilaspur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018367) | 2738/MLMD | 14/08/2023 | 867 | MANIK CHANDRA SAHA. | 26.91 | 0 | 0 | 77
559 | UTTAR DINAJPUR | Raiganj Division | BILASPUR Piped Water Supply Scheme , SM/16563 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bilaspur PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3768/RD/PHED | 18/12/2024 | 45 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 19.54 | 0 | 0 | 0
560 | UTTAR DINAJPUR | Raiganj Division | BILASPUR Piped Water Supply Scheme , SM/16563 | New | Implementation of BILASPUR and its adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2406/RD/PHE | 17/08/2023 | 600 | M/S ALISA CONSTRUCTION | 303.65 | 0 | 0 | 30
561 | UTTAR DINAJPUR | Raiganj Division | Khalsi Piped Water Supply Scheme. , SM/18179 | New | Material Requisition To Resource Division | 1332/RD/PHE | 15/05/2023 | 0 | Resource Division | 41.2 | 0 | 0 | 0
562 | UTTAR DINAJPUR | Malda Mechanical | Khalsi Piped Water Supply Scheme. , SM/18179 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II of Khalshi Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/004009) | 100/MLMD | 11/01/2024 | 180 | R. S. ENTERPRISE | 23.44 | 0 | 0 | 47
563 | UTTAR DINAJPUR | Raiganj Division | Khalsi Piped Water Supply Scheme. , SM/18179 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Khalsi, 2.Dwipnagar in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 1490/RD/PHE | 17/05/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 52.73 | 0 | 0 | 90
564 | UTTAR DINAJPUR | Malda Mechanical | Khalsi Piped Water Supply Scheme. , SM/18179 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Khalsi,, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-546 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 0.75 | 0 | 0 | 0
565 | UTTAR DINAJPUR | Malda Mechanical | Khalsi Piped Water Supply Scheme. , SM/18179 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Khalsi, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-184 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 1.85 | 0 | 0 | 0
566 | UTTAR DINAJPUR | Raiganj Division | Khalsi Piped Water Supply Scheme. , SM/18179 | New | Implementation of KHALSI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1129/RD/PHE | 24/04/2023 | 1111 | SANYAL ENTERPRISE | 386.06 | 0 | 0 | 50
567 | UTTAR DINAJPUR | Raiganj Division | MACHHALI PWSS , SM/18289 | New | Material Requisition To Resource Division | 723/RD/PHE | 15/03/2023 | 0 | Resource Division | 83.09 | 0 | 0 | 0
568 | UTTAR DINAJPUR | Raiganj Division | MACHHALI PWSS , SM/18289 | New | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 4(Four) Month (01/03/2024 to 30/06/2024). | 472/RD/PHE | 28/02/2024 | 121 | PRITAM SARKAR | 1.6 | 0 | 0 | 0
569 | UTTAR DINAJPUR | Malda Mechanical | MACHHALI PWSS , SM/18289 | New | Quotation for new service connection at MACHHALI PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-70 | 15/04/2024 | 0 | W.B.S.E.D.C.LTD | 8.34 | 0 | 0 | 0
570 | UTTAR DINAJPUR | Malda Mechanical | MACHHALI PWSS , SM/18289 | New | Quotation for new service connection at MACHHALI PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-69 | 15/04/2024 | 0 | W.B.S.E.D.C.LTD | 6.24 | 0 | 0 | 0
571 | UTTAR DINAJPUR | Malda Mechanical | MACHHALI PWSS , SM/18289 | New | Quotation for new service connection at MACHHALI PH-III (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-122 | 24/04/2024 | 0 | W.B.S.E.D.C.LTD | 13.65 | 0 | 0 | 0
572 | UTTAR DINAJPUR | Raiganj Division | MACHHALI PWSS , SM/18289 | New | Implementation of MACHHALI and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division. (Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rdTubeWell) | 2479/RD/PHE | 24/08/2023 | 976 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 742.57 | 0 | 0 | 55
573 | UTTAR DINAJPUR | Raiganj Division | MACHHALI PWSS , SM/18289 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Machhal PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3765/RD/PHED | 18/12/2024 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 75.22 | 0 | 0 | 0
574 | UTTAR DINAJPUR | Raiganj Division | MACHHALI PWSS , SM/18289 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under MACHHALI PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 656/RD/PHE | 05/03/2024 | 525 | BIKASH KAR | 27.72 | 0 | 0 | 100
575 | UTTAR DINAJPUR | Raiganj Division | MACHHALI PWSS , SM/18289 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Machhali Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | 2487/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 36.37 | 0 | 0 | 0
576 | UTTAR DINAJPUR | Raiganj Division | DULEPUR PWSS , SM/18293 | New | Material Requisition To Resource Division | 636/RD/PHE | 02/03/2023 | 0 | Resource Division | 83.32 | 0 | 0 | 0
577 | UTTAR DINAJPUR | Raiganj Division | DULEPUR PWSS , SM/18293 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under DULEPUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 660/RD/PHE | 05/03/2024 | 45 | BHAGIRATH CONSTRUCTION | 13.86 | 0 | 0 | 0
578 | UTTAR DINAJPUR | Raiganj Division | DULEPUR PWSS , SM/18293 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under DULEPUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 659/RD/PHE | 05/03/2024 | 45 | ANILA CONSTRUCTION | 13.86 | 0 | 0 | 0
579 | UTTAR DINAJPUR | Malda Mechanical | DULEPUR PWSS , SM/18293 | New | Quotation for new service connection at DULEPUR PH-III (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18293) | BP-2024-25-376 | 18/07/2024 | 0 | W.B.S.E.D.C.LTD | 9.99 | 0 | 0 | 0
580 | UTTAR DINAJPUR | Malda Mechanical | DULEPUR PWSS , SM/18293 | New | Quotation for new service connection at DULEPUR PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18293) | BP-2024-25-374 | 18/07/2024 | 0 | W.B.S.E.D.C.LTD | 4.09 | 0 | 0 | 0
581 | UTTAR DINAJPUR | Malda Mechanical | DULEPUR PWSS , SM/18293 | New | Quotation for new service connection at DULEPUR PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18293) | BP-2024-25-375 | 18/07/2024 | 0 | W.B.S.E.D.C.LTD | 10.65 | 0 | 0 | 0
582 | UTTAR DINAJPUR | Malda Mechanical | DULEPUR PWSS , SM/18293 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Dulepur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018374) | 2746/MLMD | 14/08/2023 | 1047 | M/S S. S. ENTERPRISE | 37.3 | 0 | 0 | 0
583 | UTTAR DINAJPUR | Raiganj Division | DULEPUR PWSS , SM/18293 | New | Implementation of DULEPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rdTubeWell) | 2478/RD/PHE | 24/08/2023 | 1226 | UTTAM SAHA | 660.02 | 0 | 0 | 10
584 | UTTAR DINAJPUR | Raiganj Division | DULEPUR PWSS , SM/18293 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Dulepur PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3763/RD/PHED | 18/12/2024 | 315 | M/S SARKAR ENTERPRISE SILIGURI | 94.92 | 0 | 0 | 30
585 | UTTAR DINAJPUR | Raiganj Division | DULEPUR PWSS , SM/18293 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.Vehicle no. WB74AP 7552) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month( period from 27.11.2024 to 26.05.2025). | 3446/RD/PHE | 26/11/2024 | 181 | M/S SARKAR ENTERPRISE SILIGURI | 2.4 | 0 | 0 | 0
586 | UTTAR DINAJPUR | Raiganj Division | DULEPUR PWSS , SM/18293 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dulehpur Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | 2485/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 36.38 | 0 | 0 | 0
587 | UTTAR DINAJPUR | Raiganj Division | GUNJARIA PWSS , SM/18296 | New | Material Requisition To Resource Division | 618/RD/PHE | 28/02/2023 | 0 | Resource Division | 83.71 | 0 | 0 | 0
588 | UTTAR DINAJPUR | Raiganj Division | GUNJARIA PWSS , SM/18296 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under GUNJARIA PWSS at Islampur Block under Raiganj Division, PHE Dte. | 653/RD/PHE | 05/03/2024 | 45 | M/S LUCKY CONSTRUCTION | 24.49 | 0 | 0 | 0
589 | UTTAR DINAJPUR | Raiganj Division | GUNJARIA PWSS , SM/18296 | New | Implementation of GUNJARIA and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd Tube Well) | 2296/RD/PHE | 04/08/2023 | 998 | UTTAM SAHA | 631.56 | 0 | 0 | 40
590 | UTTAR DINAJPUR | Malda Mechanical | GUNJARIA PWSS , SM/18296 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Gunjaria Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/016520) | 2640/MLMD | 10/08/2023 | 1051 | JAL PRAVAHIKA PVT. LTD. | 29.41 | 0 | 0 | 0
591 | UTTAR DINAJPUR | Raiganj Division | GUNJARIA PWSS , SM/18296 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | 1816/RD/PHE | 26/06/2024 | 198 | MD ZAFAR EQUEBAL | 2.6 | 0 | 0 | 100
592 | UTTAR DINAJPUR | Raiganj Division | GUNJARIA PWSS , SM/18296 | New | Providing FHTC in connection with Gunjaria Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 56/RD/PHE | 03/01/2025 | 45 | M/S. B. PAUL & COMPANY | 13.85 | 0 | 0 | 0
593 | UTTAR DINAJPUR | Raiganj Division | GUNJARIA PWSS , SM/18296 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Gunjaria Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | 1807/RD/PHE | 24/06/2025 | 180 | AJIT PRAMANIK | 33.6 | 0 | 0 | 0
594 | UTTAR DINAJPUR | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/18298 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
595 | UTTAR DINAJPUR | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/18298 | New | Material Requisition To Resource Division | 2245/RD/PHE | 02/08/2023 | 0 | Resource Division | 30.75 | 0 | 0 | 0
596 | UTTAR DINAJPUR | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/18298 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DHOARAI (Zone-I)PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 672/RD/PHE | 05/03/2024 | 270 | D. K. ASSOCIATES | 22.58 | 0 | 0 | 100
597 | UTTAR DINAJPUR | Malda Mechanical | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/18298 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Dhoarai (Zone-I), Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-628 | 06/03/2024 | 0 | W.B.S.E.D.C.LTD | 0.45 | 0 | 0 | 0
598 | UTTAR DINAJPUR | Malda Mechanical | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/18298 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dhoarai (Zone-I), Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-629 | 06/03/2024 | 0 | W.B.S.E.D.C.LTD | 0.55 | 0 | 0 | 0
599 | UTTAR DINAJPUR | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/18298 | New | Implementation of DHOARAI ZONE-I and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1999/RD/PHE | 13/07/2023 | 903 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 476.5 | 0 | 0 | 50
600 | UTTAR DINAJPUR | Malda Mechanical | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/18298 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite at T/W no. I of Dhoarai Zone-I Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017842) | 2487/MLMD | 04/08/2023 | 967 | M/S TRILOCHAN CONSTRUCTION CO. | 25.16 | 0 | 0 | 85
601 | UTTAR DINAJPUR | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/18298 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Dhoarai Zone-1 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 21/RD/PHE | 02/01/2025 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 51.46 | 0 | 0 | 0
602 | UTTAR DINAJPUR | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/18298 | New | Trial Run For Dharai Zone-II PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 months | 529/RD/PHE | 12/02/2025 | 90 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. | 0.82 | 0 | 0 | 0
603 | UTTAR DINAJPUR | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/18298 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dhoaroi Zone-I Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist:Uttar Dinajpur, Block: Raiganj,Capacity- 60 M3/hr. | 1627/RD/PHE | 19/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.58 | 0 | 0 | 0
604 | UTTAR DINAJPUR | Raiganj Division | Dhoarai Zone-I Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/18298 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
605 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09174 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Itahar Piped Water Supply Scheme And adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E. Dte. | 2074/RD/PHE | 02/11/2021 | 30 | TAPAN KUMAR MAJUMDER | 19.75 | 0 | 0 | 1
606 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09174 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Itahar Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Itahar Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1828/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.5 | 0 | 0 | 0
607 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09174 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Dhulahar Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E Dte. | 432/RD/PHE | 16/02/2022 | 30 | RAHUL ENTERPRISE | 6.65 | 0 | 0 | 0
608 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09174 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Itahar Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E Dte. | 483/RD/PHE | 25/02/2022 | 30 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 19.39 | 0 | 0 | 0
609 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09174 | Retrofitting | Preparation of Additional DPR For Itahar Zone-II in connection with Retrofitting of Functional House Hold Tap Connection of Itahar PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur | 2133/RD/PHE | 07/12/2022 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM MANASIJ_DUTTA@VSNL.COM | 0.78 | 0 | 0 | 1
610 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09174 | Retrofitting | Allied works in connection with retrofitting of FHTC in Itahar PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2603/RD/PHE | 13/09/2023 | 60 | ASHIM CHANDA | 0.98 | 0 | 0 | 100
611 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09174 | Retrofitting | Material Requisition To Resource Division | 1806/RD/PHE | 23/09/2022 | 0 | Resource Division | 5.26 | 0 | 0 | 0
612 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Nalbithi for installation of FHTC. , SM/09155 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of NALBITHI MADHABPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte | 2111/RD/PHE | 03/11/2021 | 30 | TAPAN KUMAR MAJUMDER | 8.2 | 0 | 0 | 1
613 | UTTAR DINAJPUR | Raiganj Division | NIZAMPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16490 | New | Material Requisition To Resource Division | 847/RD/PHE | 24/03/2023 | 0 | Resource Division | 36.11 | 0 | 0 | 0
614 | UTTAR DINAJPUR | Malda Mechanical | NIZAMPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16490 | New | Quotation for new service connection at NIZAMPUR PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-75 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 6.38 | 0 | 0 | 0
615 | UTTAR DINAJPUR | Malda Mechanical | NIZAMPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16490 | New | Quotation for new service connection at NIZAMPUR PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-76 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 9.18 | 0 | 0 | 0
616 | UTTAR DINAJPUR | Raiganj Division | NIZAMPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16490 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
617 | UTTAR DINAJPUR | Malda Mechanical | NIZAMPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16490 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Nizampur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015931) | 3423/MLMD | 01/11/2023 | 720 | SUBRATA KUMAR DAS. | 26.44 | 0 | 0 | 79
618 | UTTAR DINAJPUR | Raiganj Division | NIZAMPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16490 | New | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 05/10/2024 to 14/01/2025. | 3041/RD/PHE | 03/10/2024 | 102 | SISIR KUMAR DUTTA | 1.35 | 0 | 0 | 0
619 | UTTAR DINAJPUR | Raiganj Division | NIZAMPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16490 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Nizampur Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | 1805/RD/PHE | 24/06/2025 | 180 | S. DUTTA | 29.59 | 0 | 0 | 0
620 | UTTAR DINAJPUR | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Hemtabad, Islampur And Itahar in the District of Uttar Dinajpur Under Raiganj Division P.H.E. DTE. , SM/11517 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Hemtabad, Islampur & Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte | 1284/RD/PHE | 08/05/2023 | 969 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 709.96 | 0 | 0 | 50
621 | UTTAR DINAJPUR | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Hemtabad, Islampur And Itahar in the District of Uttar Dinajpur Under Raiganj Division P.H.E. DTE. , SM/11517 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Patnihar village under Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 593/RD/PHE | 19/02/2025 | 60 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 43.7 | 0 | 0 | 0
622 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Khowaspur and adjoining Mouzas water supply scheme , SM/07143 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Purba Mohanpur and Khowaspur Mouza under Khowaspur Water Supply Scheme in Karandithi Block under Raiganj Division, P.H.E. Dte. | 1431/RD/PHE | 11/12/2020 | 30 | M/S PIONEER ENTERPRISE | 24.17 | 0 | 0 | 1
623 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Khowaspur and adjoining Mouzas water supply scheme , SM/07143 | Retrofitting | OFFICE ACCESSORIES BILL | 770/W | 11/03/2022 | 0 | M/S DUTTA ENTERPRISE | 0.09 | 0 | 0 | 0
624 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Khowaspur and adjoining Mouzas water supply scheme , SM/07143 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Jotilamat and Purba Pipla Mouza under Khowaspur Water Supply Scheme in Karandithi Block under Raiganj Division, P.H.E. Dte. | 1430/RD/PHE | 11/12/2020 | 30 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 22.06 | 0 | 0 | 1
625 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Purba Rampur and adjoining Mouzas water supply scheme , SM/07144 | Retrofitting | OFFICE ACCESSORIES BILL | 774/W | 11/03/2022 | 0 | BEEKAY.COM | 0.09 | 0 | 0 | 0
626 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Purba Rampur and adjoining Mouzas water supply scheme , SM/07144 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Purba Rampur and adjoining Mouzas Water Supply Scheme in Kaliyganj Block under Raiganj Division, P.H.E. Dte. | 1416/RD/PHE | 11/12/2020 | 40 | PRASANTA DUTTA | 84.08 | 0 | 0 | 0
627 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Purba Rampur and adjoining Mouzas water supply scheme , SM/07144 | Retrofitting | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 15.01.2025 to 14.07.2025 | 296/RD/PHE | 15/01/2025 | 181 | DEBASISH GHOSH | 2.4 | 0 | 0 | 0
628 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Mahammadpur and adjoining Mouzas water supply scheme , SM/06725 | Retrofitting | Supply, laying, fitting, fixing & jointing of upvc pipe including PCC & ordinary concrete( 1:2:4) connection with retrofitting of functional household tap connection (FHTC) under MAHAMMADPUR water Supply Scheme Under Raiganj Division, P.H.E.Dte. | 1501/RD/PHE | 23/12/2020 | 25 | ANILA CONSTRUCTION | 3.11 | 0 | 0 | 0
629 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Mahammadpur and adjoining Mouzas water supply scheme , SM/06725 | Retrofitting | OFFICE ACCESSORIES BILL | 773/W | 11/03/2022 | 0 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.08 | 0 | 0 | 0
630 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Mahammadpur and adjoining Mouzas water supply scheme , SM/06725 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Mahammadpur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | 1239/RD/PHE | 16/10/2020 | 40 | TAPAN KUMAR DUTTA | 84.41 | 0 | 0 | 0
631 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Mahammadpur and adjoining Mouzas water supply scheme , SM/06725 | Retrofitting | FHTC OF MAHAMMADPUR WSS | 1239/RD | 16/10/2020 | 40 | TAPAN KUMAR DUTTA | 84.41 | 53.16 | 100 | 0
632 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Choprabari and adjoining Mouzas water supply scheme , SM/06730 | Retrofitting | SUPPLYING LAYING FIXING AND JOINTING UPVC PIPE FHTC OF CHOPRABARI PWSS | 1511/RD | 23/12/2020 | 30 | M/S CHOUDHURY CONSTRUCTION | 8.56 | 0 | 0 | 0
633 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Choprabari and adjoining Mouzas water supply scheme , SM/06730 | Retrofitting | OFFICE ACCESSORIES BILL | 776/W | 11/03/2022 | 0 | SAHA CONSTRUCTION | 0.09 | 0 | 0 | 0
634 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Choprabari and adjoining Mouzas water supply scheme , SM/06730 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Choprabari and adjoining Mouzas Water Supply Scheme in Karandighi Block under Raiganj Division, P.H.E. Dte. | 1242/RD/PHE | 16/10/2020 | 40 | AJIT PARMANIK | 74.35 | 0 | 0 | 0
635 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Choprabari and adjoining Mouzas water supply scheme , SM/06730 | Retrofitting | FHTC OF CHOPRABARI | 1242/RD | 16/10/2020 | 40 | AJIT PARMANIK | 74.59 | 49.06 | 100 | 0
636 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Choprabari and adjoining Mouzas water supply scheme , SM/06730 | Retrofitting | Continuation Order for Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C, Vehicle No. WB 59D 1337) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Months (Period from 15.01.2025 to 14.07.2025). | 299/RD/PHE | 15/01/2025 | 181 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 2.4 | 0 | 0 | 0
637 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Marnai and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09178 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Marnai Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E. Dte. | 2078/RD/PHE | 02/11/2021 | 30 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 9.05 | 0 | 0 | 1
638 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Marnai and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09178 | Retrofitting | Retrofitting Of Functional Household Tap Connections(FHTC) under Marnai Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P.H.E Dte. | 430/RD/PHE | 16/02/2022 | 30 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 8.98 | 0 | 0 | 0
639 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Marnai and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09178 | Retrofitting | Route Survey & Preparation of DPR of MARNAI PWSS under Raiganj Division, PHE Dte. | 151/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 3.93 | 0 | 0 | 0
640 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Marnai and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09178 | Retrofitting | Material Requisition To Resource Division | 27/RD/PHE | 06/01/2022 | 0 | Resource Division | 2.15 | 0 | 0 | 0
641 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Marnai and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09178 | Retrofitting | Material Requisition To Resource Division | 1804/RD/PHE | 23/09/2022 | 0 | Resource Division | 2.41 | 0 | 0 | 0
642 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Pawakhali WSS for installation of FHTC. , SM/09131 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Pawakhali Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part B) | 2147/RD/PHE | 12/11/2021 | 30 | M/S P.S. ENTERPRISE | 4.85 | 0 | 0 | 1
643 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Pawakhali WSS for installation of FHTC. , SM/09131 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Pawakhali for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | 2200/RD/PHE | 17/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 16.22 | 0 | 0 | 0
644 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Sripur for installation of FHTC. , SM/09163 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of SRIPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2118/RD/PHE | 03/11/2021 | 30 | M/S SARKAR ENTERPRISE | 9.48 | 0 | 0 | 1
645 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Pakhuriya for installation of FHTC. , SM/09165 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of PAKHURIYA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2119/RD/PHE | 03/11/2021 | 30 | M/S PIONEER ENTERPRISE | 31.98 | 0 | 0 | 1
646 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Gopalpur for installation of FHTC. , SM/09151 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of GOPALPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2110/RD/PHE | 03/11/2021 | 30 | DAS CONSTRUCTION COMPANY | 9.22 | 0 | 0 | 1
647 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Bindal WSS for installation of FHTC. , SM/09116 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of BINDOL Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2188/RD/PHE | 17/11/2021 | 30 | UTTAM SAHA | 12.9 | 0 | 0 | 0
648 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME , SM/10548 | Augmentation | Augmentation work of Dhulahar Water Supply Scheme at Ithar Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | 1373/RD/PHE | 14/07/2022 | 90 | M/S LOKENATH CONSTRUCTION | 118.85 | 0 | 0 | 0
649 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME , SM/10548 | Augmentation | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Dhulahar Water Supply Scheme at Itahar Block Block Under Raiganj Division, P.H.E Dte. | 432/RD/PHE | 10/02/2023 | 45 | M/S PRIME BUILDERS PRIME.BUILDERS@GMAIL.COM | 3.51 | 0 | 0 | 0
650 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME , SM/10548 | Augmentation | Supply, delivery, installation, commissioning of electro-mechanical components of Augmentation of Dhulahar Water Supply Scheme TW no I in the District of Uttar dinajpur under Malda Mechanical Division, PHE Dte. | 422/MLMD | 14/03/2023 | 90 | JIBU SINGHA | 10.18 | 0 | 0 | 0
651 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME , SM/10548 | Augmentation | Supply, delivery, installation, commissioning of electro-mechanical components of Augmentation of Dhulahar Water Supply Scheme TW no II in the District of Uttar dinajpur under Malda Mechanical Division, PHE Dte. | 423/MLMD | 14/03/2023 | 90 | ALPHA ENTERPRISE. | 10.08 | 0 | 0 | 100
652 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME , SM/10548 | Augmentation | Construction of Over Head Reservoir(Capacity-300 Cum) of DHULAHAR Pipe Water Supply Scheme in connection with Augmentation at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 656/RD/PHE | 03/03/2023 | 240 | M/S PIONEER ENTERPRISE | 84.9 | 0 | 0 | 0
653 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME , SM/10548 | Augmentation | Material Requisition To Resource Division | 1950/RD/PHE | 04/11/2022 | 0 | Resource Division | 10.93 | 0 | 0 | 0
654 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME , SM/10548 | Augmentation | Material Requisition To Resource Division | 1944/RD/PHE | 04/11/2022 | 0 | Resource Division | 7.27 | 0 | 0 | 0
655 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME , SM/10548 | Augmentation | FHTC (Functional Household Tap Connection) for Dhulahar Water Supply Scheme [Augmentation Scheme] in Itahar Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2020/RD/PHE | 17/11/2022 | 60 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 35.2 | 0 | 0 | 100
656 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME , SM/10548 | Augmentation | hiring of inspection vehicle | BP-2023-24-282 | 16/02/2024 | 0 | DEBASISH GHOSH | 0.2 | 0 | 0 | 0
657 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF DHULAHAR PIPED WATER SUPPLY SCHEME , SM/10548 | Augmentation | Construction of Approach Road, Laying of Pipe Line,Fhtc And Other Allied Works Of Dhulahar Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3574/RD/PHE | 05/12/2024 | 91 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 36.88 | 0 | 0 | 0
658 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe Line for providing FHTC for Barua Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) , SM/10448 | Retrofitting | Restoration of Pipeline for Providing FHTC for BARUA PIPED Water Supply Scheme for under Raiganj Division, P.H.E Dte. (Phase - II) | 1047/RD/PHED | 12/05/2022 | 45 | M/S ROYAL CONSTRUCTION | 10.97 | 0 | 0 | 1
659 | UTTAR DINAJPUR | Raiganj Division | Restoration of Damaged Pipe Line for providing FHTC at Dakshin Jibakata Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) , SM/10487 | Retrofitting | Restoration of Damaged Pipe line for providing FHTC at Dakshin Jibakata Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte.(Phase-II) | 1051/RD/PHED | 12/05/2022 | 45 | M/S.BANGARAJ | 15.57 | 0 | 0 | 1
660 | UTTAR DINAJPUR | Malda Mechanical | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11824 | New | Making compound lighting arrangement with allied works at T/W no. I of Maladhanda Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011914) | 2236/MLMD | 12/07/2023 | 90 | M/S. MAYUKH BHADURI | 2.64 | 0 | 0 | 0
661 | UTTAR DINAJPUR | Malda Mechanical | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11824 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Maladkhanda PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003133003 | 16/04/2023 | 90 | W.B.S.E.D.C.LTD | 0.84 | 0 | 0 | 100
662 | UTTAR DINAJPUR | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11824 | New | Material Requisition To Resource Division | 572/RD/PHE | 23/02/2023 | 0 | Resource Division | 120.41 | 0 | 0 | 0
663 | UTTAR DINAJPUR | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11824 | New | Rig bored Tubewell at MALADKHANDA PWSS in connection with Implementation of New Maladkhanda PWSS at Raiganj Block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2751/RD/PHE | 05/10/2023 | 20 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 26.26 | 0 | 0 | 100
664 | UTTAR DINAJPUR | Malda Mechanical | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11824 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Maladkhanda, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-623 | 04/03/2024 | 0 | W.B.S.E.D.C.LTD | 0.73 | 0 | 0 | 0
665 | UTTAR DINAJPUR | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11824 | New | Implementation of MALADKHANDA and its adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 555/RD/PHE | 23/02/2023 | 1148 | UTTAM SAHA | 685.62 | 0 | 0 | 53
666 | UTTAR DINAJPUR | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11824 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MALADKHANDA Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 570/RD/PHE | 05/03/2024 | 383 | M/S REGAL BUILDERS | 22.57 | 0 | 0 | 100
667 | UTTAR DINAJPUR | Malda Mechanical | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11824 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of MALADKHANDA Water Supply Scheme T/W no.II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 3681/MLMD | 29/11/2023 | 468 | M/S SABANA CONSTRUCTION | 12.11 | 0 | 0 | 85
668 | UTTAR DINAJPUR | Raiganj Division | MALADKHANDA PWSS IN RAJGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11824 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
669 | UTTAR DINAJPUR | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Kaliyaganj and Karandighi in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. , SM/11519 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Kaluhar village under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2885/RD/PHE | 25/09/2024 | 60 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 40.07 | 0 | 0 | 0
670 | UTTAR DINAJPUR | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Kaliyaganj and Karandighi in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. , SM/11519 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Kaliyaganj & Karandighi Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1286/RD/PHE | 08/05/2023 | 970 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 616.73 | 0 | 0 | 15
671 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Jujharpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09194 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Jujharpur Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Karandighi Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1820/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.76 | 0 | 0 | 0
672 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Jujharpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09194 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Jujharpur Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E. Dte. | 2382/RD/PHE | 24/12/2021 | 30 | SAHA CONSTRUCTION | 8.32 | 0 | 0 | 0
673 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Jujharpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09194 | Retrofitting | Material Requisition To Resource Division | 34/RD/PHE | 06/01/2022 | 0 | Resource Division | 1.98 | 0 | 0 | 0
674 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Jujharpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09194 | Retrofitting | Material Requisition To Resource Division | 1817/RD/PHE | 28/09/2022 | 0 | Resource Division | 1.11 | 0 | 0 | 0
675 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Bamair Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12639 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Bamair Piped Water Supply Scheme of Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1911/RD/PHE | 28/10/2022 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 35.1 | 0 | 0 | 75
676 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Bamair Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12639 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Source Augmentation of Bamair Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015280) | 2465/MLMD | 04/08/2023 | 120 | JIBU SINGHA | 11.36 | 0 | 0 | 100
677 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Bamair Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12639 | Augmentation | Material Requisition To Resource Division | 10/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
678 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Bamair Piped Water Supply Scheme under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12639 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Bamair, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-472 | 26/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.41 | 0 | 0 | 0
679 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Jujharpur Piped Water Supply Scheme in Karandighi block of Uttar Dinajpur District. , SM/12395 | Augmentation | Material Requisition To Resource Division | 2170/RD/PHE | 09/12/2022 | 0 | Resource Division | 37.57 | 0 | 0 | 0
680 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Jujharpur Piped Water Supply Scheme in Karandighi block of Uttar Dinajpur District. , SM/12395 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Jujharpur, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003209172 | 07/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.67 | 0 | 0 | 100
681 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Jujharpur Piped Water Supply Scheme in Karandighi block of Uttar Dinajpur District. , SM/12395 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No.III of Jujharpur, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 100000096206 | 22/12/2023 | 90 | W.B.S.E.D.C.LTD | 0.02 | 0 | 0 | 100
682 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Jujharpur Piped Water Supply Scheme in Karandighi block of Uttar Dinajpur District. , SM/12395 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III and Grid connected ground mounted solar PV system with net metering at T/W no. I of Jujaharpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013312) | 2660/MLMD | 10/08/2023 | 2005 | SHREE BISHNU CONSTRUCTION | 17.52 | 0 | 0 | 35
683 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Jujharpur Piped Water Supply Scheme in Karandighi block of Uttar Dinajpur District. , SM/12395 | Augmentation | Land development at Head Work Site Pump House and other ancillary works for JUJHARPUR Piped Water Supply Scheme(Augmentation Jujharpur PWSS) under Islampur Sub-Division PHED under Raiganj Division, PHED., Uttar Dinajpur. | 3021/RD/PHE | 03/10/2024 | 20 | A D ENTERPRISE | 10.89 | 0 | 0 | 0
684 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Jujharpur Piped Water Supply Scheme in Karandighi block of Uttar Dinajpur District. , SM/12395 | Augmentation | Construction of concrete pathway at Head Work Site Pump House for JUJHARPUR Piped Water Supply Scheme (Augmentation of Jujharpur) under Islampur Sub-Division PHED under Raiganj Division, PHED., Uttar Dinajpur. | 3020/RD/PHE | 03/10/2024 | 30 | A D ENTERPRISE | 8.57 | 0 | 0 | 0
685 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Jujharpur Piped Water Supply Scheme in Karandighi block of Uttar Dinajpur District. , SM/12395 | Augmentation | Additional Quotation for new service connection at Augmentation of JUJHARPUR PH-III (HWS) (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12395) | BP-2024-25-434 | 07/08/2024 | 0 | W.B.S.E.D.C.LTD | 3.08 | 0 | 0 | 0
686 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Jujharpur Piped Water Supply Scheme in Karandighi block of Uttar Dinajpur District. , SM/12395 | Augmentation | Augmentation of JUJHARPUR and it's adjoining mouzas Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division,PHE Dte. | 126/RD/PHE | 20/01/2023 | 1075 | A D ENTERPRISE | 281.65 | 0 | 0 | 90
687 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Jujharpur Piped Water Supply Scheme in Karandighi block of Uttar Dinajpur District. , SM/12395 | Augmentation | Supply, installation & commissioning of electro-mechanical components at T/W no. I & II of Jujaharpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013312) | 2336/MLMD | 26/07/2023 | 960 | MAA BHABOTARINE ENTERPRISE. | 19.31 | 0 | 0 | 82
688 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Jujharpur Piped Water Supply Scheme in Karandighi block of Uttar Dinajpur District. , SM/12395 | Augmentation | Dismantling of all types of plain cement concrete works and concreting with Ordinary Cement Concrete for laying of Pipe Line to provide FHTC at JUJHARPUR Piped Water Supply Scheme (Augmentation Jujharpur) at Karandighi Block under Islampur Sub-Division under Raiganj Division, PHE Dte. Uttar Dinajpur. | 3019/RD/PHE | 03/10/2024 | 180 | A D ENTERPRISE | 40.14 | 0 | 0 | 80
689 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Jujharpur Piped Water Supply Scheme in Karandighi block of Uttar Dinajpur District. , SM/12395 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Jujharpur Water Supply Scheme(Augmentation) at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity-50 M3/hr. | 2506/RD/PHE | 12/09/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 20.74 | 0 | 0 | 0
690 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Kotar Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10495 | Retrofitting | Restoration of Pipe Line for Providing FHTC for Kotar Water Supply Scheme under Itahar Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. (Phase - II) | 1010/RD/PHE | 11/05/2022 | 20 | SANDIP SARKAR | 4.84 | 0 | 0 | 1
691 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Bheur Water Supply Scheme under Kaliyaganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10497 | Retrofitting | Restoration of Pipe Line For Providing FHTC for Bheur Water Supply Scheme Under Kaliyaganj Block under Raiganj Division P.H.E.Dte. in the District Of Uttar Dinajpur. (Phase-II) | 1038/RD/PHED | 12/05/2022 | 30 | HERO CONSTRUCTION | 6.61 | 0 | 0 | 1
692 | UTTAR DINAJPUR | Raiganj Division | BARAKHANTI Piped Water Supply Scheme at Islampur Block , SM/12093 | New | Material Requisition To Resource Division | 2185/RD/PHE | 12/12/2022 | 0 | Resource Division | 32.36 | 0 | 0 | 0
693 | UTTAR DINAJPUR | Raiganj Division | BARAKHANTI Piped Water Supply Scheme at Islampur Block , SM/12093 | New | Material Requisition To Resource Division | 583/RD/PHE | 24/02/2023 | 0 | Resource Division | 32.13 | 0 | 0 | 0
694 | UTTAR DINAJPUR | Raiganj Division | BARAKHANTI Piped Water Supply Scheme at Islampur Block , SM/12093 | New | Protection and restoration work of damaged flank caused by excavation for water supply project of PHE of patagora- Moragoti Road under Uttar Dinajpur Division, PWD. | BP-2023-24-145 | 30/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 6.39 | 0 | 0 | 0
695 | UTTAR DINAJPUR | Raiganj Division | BARAKHANTI Piped Water Supply Scheme at Islampur Block , SM/12093 | New | Implementation of BARAKHANTI and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | 297/RD/PHE | 01/02/2023 | 1151 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 617.49 | 0 | 0 | 30
696 | UTTAR DINAJPUR | Malda Mechanical | BARAKHANTI Piped Water Supply Scheme at Islampur Block , SM/12093 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Barakhanti Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013549) | 2210/MLMD | 18/07/2023 | 840 | SUBRATA SAHA | 27.22 | 0 | 0 | 73
697 | UTTAR DINAJPUR | Raiganj Division | BARAKHANTI Piped Water Supply Scheme at Islampur Block , SM/12093 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BARAKHANTI Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 591/RD/PHE | 05/03/2024 | 45 | M/S DUTTA ENTERPRISE | 22.57 | 0 | 0 | 0
698 | UTTAR DINAJPUR | Raiganj Division | BARAKHANTI Piped Water Supply Scheme at Islampur Block , SM/12093 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
699 | UTTAR DINAJPUR | Raiganj Division | BARA MIRCHA Piped Water Supply Scheme , SM/12397 | New | Material Requisition To Resource Division | 1475/RD/PHE | 16/05/2023 | 0 | Resource Division | 16.84 | 0 | 0 | 0
700 | UTTAR DINAJPUR | Malda Mechanical | BARA MIRCHA Piped Water Supply Scheme , SM/12397 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Baramircha Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014689) | 2476/MLMD | 04/08/2023 | 953 | DAS CONSTRUCTION | 25.68 | 0 | 0 | 72
701 | UTTAR DINAJPUR | Malda Mechanical | BARA MIRCHA Piped Water Supply Scheme , SM/12397 | New | Quotation for new service connection at BARAMIRCHA PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-58 | 09/04/2024 | 0 | W.B.S.E.D.C.LTD | 5.49 | 0 | 0 | 0
702 | UTTAR DINAJPUR | Malda Mechanical | BARA MIRCHA Piped Water Supply Scheme , SM/12397 | New | Quotation for new service connection at BARAMIRCHA PH-II (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-59 | 09/04/2024 | 0 | W.B.S.E.D.C.LTD | 10.03 | 0 | 0 | 0
703 | UTTAR DINAJPUR | Raiganj Division | BARA MIRCHA Piped Water Supply Scheme , SM/12397 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
704 | UTTAR DINAJPUR | Raiganj Division | BARA MIRCHA Piped Water Supply Scheme , SM/12397 | New | Providing FHTC in connection with Bara Mircha Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 1171/RD/PHE | 23/04/2025 | 15 | CHAPDUAR LABOUR CO- OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 5.4 | 0 | 0 | 0
705 | UTTAR DINAJPUR | Raiganj Division | BARA MIRCHA Piped Water Supply Scheme , SM/12397 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bara Mircha Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 25 M3/hr. | 1977/RD/PHE | 03/07/2025 | 180 | LIMRA CIVIL CONSTRUCTION | 16.3 | 0 | 0 | 0
706 | UTTAR DINAJPUR | Raiganj Division | BARA MIRCHA Piped Water Supply Scheme , SM/12397 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at Bara Mircha PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | 2095/RD/PHE | 15/07/2025 | 180 | M/S SACHIN KUMAR | 25.81 | 0 | 0 | 0
707 | UTTAR DINAJPUR | Malda Mechanical | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block , SM/12096 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of UTTAR MIRZAPUR PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003202233 | 02/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.17 | 0 | 0 | 100
708 | UTTAR DINAJPUR | Malda Mechanical | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block , SM/12096 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of UTTAR MIRZAPUR, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003224928 | 08/09/2023 | 90 | W.B.S.E.D.C.LTD | 3.64 | 0 | 0 | 100
709 | UTTAR DINAJPUR | Raiganj Division | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block , SM/12096 | New | Material Requisition To Resource Division | 28/RD/PHE | 06/01/2023 | 0 | Resource Division | 29.02 | 0 | 0 | 0
710 | UTTAR DINAJPUR | Malda Mechanical | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block , SM/12096 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite ,of Uttar Mirzapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012989) | 2086/MLMD | 04/07/2023 | 120 | NEOGI ENTERPRISE. | 24.39 | 0 | 0 | 89
711 | UTTAR DINAJPUR | Raiganj Division | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block , SM/12096 | New | Implementation of UTTAR MIRZAPUR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 66/RD/PHE | 16/01/2023 | 1081 | SANYAL ENTERPRISE | 277.69 | 0 | 0 | 65
712 | UTTAR DINAJPUR | Raiganj Division | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block , SM/12096 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under UTTAR MIRZADPUR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 588/RD/PHE | 05/03/2024 | 45 | LAXMI ENTERPRISE (DIPAK MISHRA) | 11.29 | 0 | 0 | 0
713 | UTTAR DINAJPUR | Raiganj Division | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block , SM/12096 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Uttar Mirzapur PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 08/RD/PHE | 02/01/2025 | 45 | UTTAM SAHA | 51.89 | 0 | 0 | 0
714 | UTTAR DINAJPUR | Raiganj Division | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block , SM/12096 | New | Trial Run For Uttar Mirzapur PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | 523/RD/PHE | 12/02/2025 | 90 | SANYAL ENTERPRISE | 0.88 | 0 | 0 | 0
715 | UTTAR DINAJPUR | Raiganj Division | UTTAR MIRZAPUR Piped Water Supply Scheme at Kaliyaganj Block , SM/12096 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under UTTAR MIRZADPUR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 596/RD/PHE | 05/03/2024 | 405 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 11.29 | 0 | 0 | 80
716 | UTTAR DINAJPUR | Raiganj Division | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12106 | New | Material Requisition To Resource Division | 2192/RD/PHE | 12/12/2022 | 0 | Resource Division | 35.44 | 0 | 0 | 0
717 | UTTAR DINAJPUR | Malda Mechanical | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12106 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bhitihar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012695) | 1121/MLMD | 23/06/2023 | 120 | ORIENTAL ENGINEERING CO. | 25.95 | 0 | 0 | 0
718 | UTTAR DINAJPUR | Malda Mechanical | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12106 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BHITIHAR PWSS, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003196243 | 29/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.24 | 0 | 0 | 100
719 | UTTAR DINAJPUR | Malda Mechanical | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12106 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Bhitihar, Birnagar CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-569 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 6.39 | 0 | 0 | 0
720 | UTTAR DINAJPUR | Malda Mechanical | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12106 | New | Additional Quotation of TW-II of Bhitihar water supply scheme in the district of Uttar Dinajpur. | BP-2024-25-399 | 29/07/2024 | 0 | W.B.S.E.D.C.LTD | 3.54 | 0 | 0 | 0
721 | UTTAR DINAJPUR | Malda Mechanical | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12106 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of BHITIHAR,PWSS, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-502 | 01/02/2024 | 0 | W.B.S.E.D.C.LTD | 3.15 | 0 | 0 | 0
722 | UTTAR DINAJPUR | Raiganj Division | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12106 | New | Implementation of BHITIHAR andit's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 75/RD/PHE | 16/01/2023 | 1082 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 503.79 | 0 | 0 | 30
723 | UTTAR DINAJPUR | Raiganj Division | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12106 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BHITIHAR Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 578/RD/PHE | 05/03/2024 | 405 | RAKSHIT TRADERS | 22.58 | 0 | 0 | 100
724 | UTTAR DINAJPUR | Raiganj Division | BHITIHAR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12106 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bhitihar PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 15/RD/PHE | 02/01/2025 | 45 | AJIT PRAMANIK | 87.65 | 0 | 0 | 0
725 | UTTAR DINAJPUR | Malda Mechanical | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12107 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Balas PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003123615 | 31/03/2023 | 15 | W.B.S.E.D.C.LTD | 0.63 | 0 | 0 | 0
726 | UTTAR DINAJPUR | Malda Mechanical | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12107 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Balas PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003123622 | 31/03/2023 | 15 | W.B.S.E.D.C.LTD | 0.74 | 0 | 0 | 0
727 | UTTAR DINAJPUR | Raiganj Division | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12107 | New | Material Requisition To Resource Division | 32/RD/PHE | 06/01/2023 | 0 | Resource Division | 22.64 | 0 | 0 | 0
728 | UTTAR DINAJPUR | Malda Mechanical | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12107 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement and allied works at T/W no. I of Balas Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012635) | 1136/MLMD | 26/06/2023 | 931 | HANNAN BUILDERS PVT. LTD. | 26.32 | 0 | 0 | 90
729 | UTTAR DINAJPUR | Raiganj Division | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12107 | New | Implementation of BALAS and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 68/RD/PHE | 16/01/2023 | 1081 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 359.92 | 0 | 0 | 70
730 | UTTAR DINAJPUR | Raiganj Division | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12107 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Balas PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 28/RD/PHE | 02/01/2025 | 45 | BHOLA PAUL | 44.41 | 0 | 0 | 0
731 | UTTAR DINAJPUR | Raiganj Division | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12107 | New | Trial Run For Balas PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | 527/RD/PHE | 12/02/2025 | 90 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0 | 0
732 | UTTAR DINAJPUR | Raiganj Division | BALAS Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12107 | New | Balance distribution System of Laying pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BALAS Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 576/RD/PHE | 05/03/2024 | 45 | BHOLA PAUL | 22.89 | 0 | 0 | 80
733 | UTTAR DINAJPUR | Raiganj Division | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. , SM/12443 | New | Material Requisition To Resource Division | 1119/RD/PHE | 24/04/2023 | 0 | Resource Division | 27.72 | 0 | 0 | 0
734 | UTTAR DINAJPUR | Malda Mechanical | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. , SM/12443 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Barbila Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014694) | 2474/MLMD | 04/08/2023 | 907 | DILIP MAHATO. | 26.3 | 0 | 0 | 72
735 | UTTAR DINAJPUR | Malda Mechanical | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. , SM/12443 | New | Quotation for new service connection at BARBILA PH-I (Goalpokher ccc) in the district of Uttar Dinajpur. | BP-2023-24-694 | 15/03/2024 | 0 | W.B.S.E.D.C.LTD | 6.4 | 0 | 0 | 0
736 | UTTAR DINAJPUR | Malda Mechanical | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. , SM/12443 | New | Quotation for new service connection at BARBILA PH-II (Goalpokher ccc) in the district of Uttar Dinajpur. | BP-2023-24-693 | 15/03/2024 | 0 | W.B.S.E.D.C.LTD | 19.74 | 0 | 0 | 0
737 | UTTAR DINAJPUR | Raiganj Division | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. , SM/12443 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
738 | UTTAR DINAJPUR | Raiganj Division | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. , SM/12443 | New | Construction of concrete pathway with land development at Head Work Site Pump House & 2nd TW Site Pump House for BARABILLA Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | 1202/RD/PHE | 25/04/2025 | 45 | GULJAN BEGAM | 9.98 | 0 | 0 | 0
739 | UTTAR DINAJPUR | Raiganj Division | BARBILA PWSS at Goalpokhar-l block under Uttar Dinajpur District. , SM/12443 | New | Providing FHTC in connection with Barobilla Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 1179/RD/PHE | 23/04/2025 | 15 | HAQUE CONSTRUCTION | 6.94 | 0 | 0 | 0
740 | UTTAR DINAJPUR | Raiganj Division | PASCHIM ARIAGAON Piped Water Supply Scheme at Chopra Block , SM/12083 | New | Material Requisition To Resource Division | 961/RD/PHE | 29/03/2023 | 0 | Resource Division | 19.09 | 0 | 0 | 0
741 | UTTAR DINAJPUR | Malda Mechanical | PASCHIM ARIAGAON Piped Water Supply Scheme at Chopra Block , SM/12083 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Paschim Ariagaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014313) | 2219/MLMD | 18/07/2023 | 924 | HANNAN BUILDERS PVT. LTD. | 27.23 | 0 | 0 | 73
742 | UTTAR DINAJPUR | Malda Mechanical | PASCHIM ARIAGAON Piped Water Supply Scheme at Chopra Block , SM/12083 | New | Quotation for new service connection at PASCHIM ARIAGAON PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-95 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 18.73 | 0 | 0 | 0
743 | UTTAR DINAJPUR | Malda Mechanical | PASCHIM ARIAGAON Piped Water Supply Scheme at Chopra Block , SM/12083 | New | Quotation for new service connection at PASCHIM ARIAGAON PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-96 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 6.52 | 0 | 0 | 0
744 | UTTAR DINAJPUR | Raiganj Division | PASCHIM ARIAGAON Piped Water Supply Scheme at Chopra Block , SM/12083 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
745 | UTTAR DINAJPUR | Raiganj Division | PASCHIM ARIAGAON Piped Water Supply Scheme at Chopra Block , SM/12083 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Paschim Ariagaon Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, ,Capacity- 35 M3/hr. | 1994/RD/PHE | 07/07/2025 | 180 | MONDAL PRECISION PRIVATE LIMITED | 18.03 | 0 | 0 | 0
746 | UTTAR DINAJPUR | Malda Mechanical | MANIKPUR Piped Water Supply Scheme at Islampur Block , SM/12084 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of MANIKPUR,Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003205417 | 04/08/2023 | 90 | W.B.S.E.D.C.LTD | 21.16 | 0 | 0 | 100
747 | UTTAR DINAJPUR | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block , SM/12084 | New | Material Requisition To Resource Division | 597/RD/PHE | 27/02/2023 | 0 | Resource Division | 25.59 | 0 | 0 | 0
748 | UTTAR DINAJPUR | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block , SM/12084 | New | New Service Connection charge with Security Deposit for Implementation of Manikpur PH-II WSS under Islampur CCC in the district of Uttar Dinajpur. | BP-2023-24-134 | 29/09/2023 | 0 | WEST BENGAL STATE ELETRICITY DISTRIBUTION COMPANY LIMITED | 23.16 | 0 | 0 | 0
749 | UTTAR DINAJPUR | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block , SM/12084 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MANIKPUR Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 592/RD/PHE | 05/03/2024 | 180 | CHADNI CONSTRUCTION | 22.58 | 0 | 0 | 90
750 | UTTAR DINAJPUR | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block , SM/12084 | New | Implementation of MANIKPUR and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and 2nd Tube Well) | 548/RD/PHE | 23/02/2023 | 960 | UJJWAL DAS NAMEDUTTA@GMAIL.COM | 457.08 | 0 | 0 | 85
751 | UTTAR DINAJPUR | Malda Mechanical | MANIKPUR Piped Water Supply Scheme at Islampur Block , SM/12084 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Manikpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014295) | 2114/MLMD | 05/07/2023 | 120 | NEOGI ENTERPRISE. | 26.45 | 0 | 0 | 85
752 | UTTAR DINAJPUR | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block , SM/12084 | New | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 05/10/2024 to 14/01/2025. | 3041/RD/PHE | 03/10/2024 | 102 | SISIR KUMAR DUTTA | 1.35 | 0 | 0 | 0
753 | UTTAR DINAJPUR | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block , SM/12084 | New | Providing FHTC in connection with Manikpur Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 57/RD/PHE | 03/01/2025 | 360 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 15.76 | 0 | 0 | 65
754 | UTTAR DINAJPUR | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block , SM/12084 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
755 | UTTAR DINAJPUR | Raiganj Division | MANIKPUR Piped Water Supply Scheme at Islampur Block , SM/12084 | New | Trial Run For Manikpur PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | 547/RD/PHE | 12/02/2025 | 90 | UJJWAL DAS | 0.88 | 0 | 0 | 0
756 | UTTAR DINAJPUR | Malda Mechanical | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11642 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Gouri PWSS , Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003132438 | 12/04/2023 | 15 | W.B.S.E.D.C.LTD | 0.74 | 0 | 0 | 0
757 | UTTAR DINAJPUR | Malda Mechanical | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11642 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Gouri PWSS , Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003132554 | 12/04/2023 | 15 | W.B.S.E.D.C.LTD | 0.63 | 0 | 0 | 0
758 | UTTAR DINAJPUR | Raiganj Division | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11642 | New | Material Requisition To Resource Division | 1957/RD/PHE | 04/11/2022 | 0 | Resource Division | 46.51 | 0 | 0 | 0
759 | UTTAR DINAJPUR | Malda Mechanical | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11642 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of GOURI Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 1673/MLMD | 28/06/2023 | 90 | DAS ENTERPRISE. | 11.9 | 0 | 0 | 100
760 | UTTAR DINAJPUR | Malda Mechanical | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11642 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of GOURI Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 1674/MLMD | 28/06/2023 | 90 | DILIP MAHATO. | 11.95 | 0 | 0 | 100
761 | UTTAR DINAJPUR | Raiganj Division | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11642 | New | Implementation of GOURI and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | 1541/RD/PHE | 26/08/2022 | 806 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 376.23 | 0 | 0 | 56
762 | UTTAR DINAJPUR | Raiganj Division | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11642 | New | Construction Over Head Resorvoir (OHR) and other allied works of GOURI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | 1281/RD/PHE | 08/05/2023 | 970 | UTTAM SAHA | 240.92 | 0 | 0 | 50
763 | UTTAR DINAJPUR | Raiganj Division | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11642 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
764 | UTTAR DINAJPUR | Malda Mechanical | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11642 | New | Making compound lighting arrangement with allied works at T/W no. I of Gouri Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011695) | 2242/MLMD | 18/07/2023 | 927 | M/S SABANA CONSTRUCTION | 2.64 | 0 | 0 | 0
765 | UTTAR DINAJPUR | Raiganj Division | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11642 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Gouri PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 12/RD/PHE | 02/01/2025 | 45 | M/S P.S. ENTERPRISE | 88.14 | 0 | 0 | 0
766 | UTTAR DINAJPUR | Raiganj Division | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11642 | New | Trial Run For Gouri PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | 536/RD/PHE | 12/02/2025 | 90 | M/S P.S. ENTERPRISE | 0.88 | 0 | 0 | 0
767 | UTTAR DINAJPUR | Raiganj Division | GOURI PIPE WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11642 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under GOURI Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 568/RD/PHE | 05/03/2024 | 225 | M/S BARENDRA CONSTRUCTION | 22.58 | 0 | 0 | 70
768 | UTTAR DINAJPUR | Raiganj Division | KAMLAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/12788 | New | Material Requisition To Resource Division | 614/RD/PHE | 28/02/2023 | 0 | Resource Division | 29.14 | 0 | 0 | 0
769 | UTTAR DINAJPUR | Raiganj Division | KAMLAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/12788 | New | Implementation of KAMLAGAON and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd Tube Well.) | 549/RD/PHE | 23/02/2023 | 1008 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 442.06 | 0 | 0 | 45
770 | UTTAR DINAJPUR | Raiganj Division | KAMLAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/12788 | New | Laying of Additional Pipeline With landf development and path way for KAMLAGAON Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte.under Raiganj Division, P.H.E Dte.,U/D. | 3580/RD/PHE | 05/12/2024 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 80.34 | 0 | 0 | 0
771 | UTTAR DINAJPUR | Malda Mechanical | KAMLAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/12788 | New | Quotation for new service connection at KAMLAGAON PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12788) | BP-2024-25-276 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 4.28 | 0 | 0 | 0
772 | UTTAR DINAJPUR | Malda Mechanical | KAMLAGAON Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/12788 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Kamlagaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014738) | 2515/MLMD | 04/08/2023 | 600 | SUJOY RANJAN BHOWMICK | 27.17 | 0 | 0 | 78
773 | UTTAR DINAJPUR | Raiganj Division | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12793 | New | Material Requisition To Resource Division | 1117/RD/PHE | 24/04/2023 | 0 | Resource Division | 51.31 | 0 | 0 | 0
774 | UTTAR DINAJPUR | Malda Mechanical | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12793 | New | Quotation for new service connection at Sholpara PH-II (Goalpokher ccc) in the district of Uttar Dinajpur. | BP-2023-24-695 | 15/03/2024 | 0 | W.B.S.E.D.C.LTD | 10.3 | 0 | 0 | 0
775 | UTTAR DINAJPUR | Malda Mechanical | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12793 | New | Quotation for new service connection at Sholpara PH-I (Goalpokher ccc) | BP-2023-24-535 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 4.65 | 0 | 0 | 0
776 | UTTAR DINAJPUR | Malda Mechanical | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12793 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Sholpara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014404) | 2532/MLMD | 04/08/2023 | 907 | M/S. KUNDU CONSTRACTION | 29.72 | 0 | 0 | 85
777 | UTTAR DINAJPUR | Raiganj Division | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12793 | New | Providing FHTC in connection with Solpara Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 1177/RD/PHE | 23/04/2025 | 30 | CHAITANYA SAMAL | 10.15 | 0 | 0 | 0
778 | UTTAR DINAJPUR | Raiganj Division | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12793 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at SHOLPARA PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | 2047/RD/PHE | 10/07/2025 | 180 | ROY ENGINEERS. (PATNA) | 52.51 | 0 | 0 | 0
779 | UTTAR DINAJPUR | Raiganj Division | SHOLPARA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12793 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Sholpara Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | 1979/RD/PHE | 03/07/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 33.59 | 0 | 0 | 0
780 | UTTAR DINAJPUR | Raiganj Division | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11961 | New | Material Requisition To Resource Division | 2124/RD/PHE | 03/12/2022 | 0 | Resource Division | 21.7 | 0 | 0 | 0
781 | UTTAR DINAJPUR | Malda Mechanical | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11961 | New | Making compound lighting arrangement with allied works at T/W no. I of Basain Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011690) | 2243/MLMD | 18/07/2023 | 90 | M/S CHANDRANATH MUKHERJEE. | 3.83 | 0 | 0 | 0
782 | UTTAR DINAJPUR | Raiganj Division | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11961 | New | Construction of Pump House & Boundary Wall at Basain Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division.( Pump House at Head Work,2nd TubeWell and Boundary Wall at Head work Site and 2nd Tube-Well. ) | 385/RD/PHE | 08/02/2023 | 60 | SAHA CONSTRUCTION SAHAKUMARESH51@GMAIL.COM | 36.15 | 0 | 0 | 100
783 | UTTAR DINAJPUR | Malda Mechanical | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11961 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Basain PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003132972 | 16/04/2023 | 15 | W.B.S.E.D.C.LTD | 0.56 | 0 | 0 | 0
784 | UTTAR DINAJPUR | Malda Mechanical | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11961 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Basain PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003132989 | 16/04/2023 | 15 | W.B.S.E.D.C.LTD | 0.45 | 0 | 0 | 0
785 | UTTAR DINAJPUR | Raiganj Division | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11961 | New | Restoration in connection with laying of PHE pipeline of Barduary- Bindole road under the jurisdiction of Uttar Dinajpur Highway Division in the district Uttar Dinajpur. | BP-2023-24-129 | 29/09/2023 | 0 | EXECUTIVE ENGINEER PWD ROADS | 22.53 | 0 | 0 | 0
786 | UTTAR DINAJPUR | Malda Mechanical | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11961 | New | additional quotation of basian TW-I & basian TW-II in the district of Uttar Dinajpur. | BP-2024-25-400 | 29/07/2024 | 0 | W.B.S.E.D.C.LTD | 2.47 | 0 | 0 | 0
787 | UTTAR DINAJPUR | Raiganj Division | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11961 | New | Implementation of Basain and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 1991/RD/PHE | 14/11/2022 | 1145 | AJIT PRAMANIK AJITPRAMANICK83@GMAIL.COM | 456.96 | 0 | 0 | 62
788 | UTTAR DINAJPUR | Malda Mechanical | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11961 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BASAIN Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 0257/MLMD | 24/02/2023 | 692 | DEBAPRIYA SAHA | 11.66 | 0 | 0 | 100
789 | UTTAR DINAJPUR | Malda Mechanical | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11961 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BASAIN Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 0258/MLMD | 24/02/2023 | 692 | DEBAPRIYA SAHA | 11.66 | 0 | 0 | 100
790 | UTTAR DINAJPUR | Malda Mechanical | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11961 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 1120/MLMD | 22/03/2024 | 61 | DAS CONSTRUCTION | 0.77 | 0 | 0 | 100
791 | UTTAR DINAJPUR | Raiganj Division | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11961 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Basain PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3754/RD/PHED | 18/12/2024 | 270 | AJIT PRAMANIK | 39.05 | 0 | 0 | 80
792 | UTTAR DINAJPUR | Raiganj Division | BASAIN PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11961 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
793 | UTTAR DINAJPUR | Raiganj Division | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11865 | New | Material Requisition To Resource Division | 2122/RD/PHE | 03/12/2022 | 0 | Resource Division | 69.45 | 0 | 0 | 0
794 | UTTAR DINAJPUR | Raiganj Division | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11865 | New | Laying Pipe line at MOKDOMPUR Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E Dte. | 1536/RD/PHE | 24/05/2023 | 678 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 65.55 | 0 | 0 | 50
795 | UTTAR DINAJPUR | Malda Mechanical | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11865 | New | Making compound lighting arrangement with allied works at T/W no. I of Makdampur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011908) | 2238/MLMD | 18/07/2023 | 90 | J.K. ENGINEERING CO. | 3.82 | 0 | 0 | 0
796 | UTTAR DINAJPUR | Malda Mechanical | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11865 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Makdampur PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003133026 | 16/04/2023 | 90 | W.B.S.E.D.C.LTD | 0.56 | 0 | 0 | 100
797 | UTTAR DINAJPUR | Malda Mechanical | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11865 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.II of Makdampur PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003133037 | 16/04/2023 | 90 | W.B.S.E.D.C.LTD | 0.45 | 0 | 0 | 100
798 | UTTAR DINAJPUR | Malda Mechanical | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11865 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of MAKDAMPUR Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2201/MLMD | 18/07/2023 | 716 | NEOGI ENTERPRISE. | 10.81 | 0 | 0 | 83
799 | UTTAR DINAJPUR | Raiganj Division | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11865 | New | Construction of Pump House & Boundary Wall at Makdampur Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division.( Pump House at Head Work,2nd TubaeWell and Boundary Wall at Head work Site and 2nd Tube-Well. ) | 384/RD/PHE | 08/02/2023 | 810 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 36.14 | 0 | 0 | 60
800 | UTTAR DINAJPUR | Raiganj Division | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11865 | New | Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of Makdampur -Bhatol Road due to pipe laying under Makdampur Pipe Water Supply Scheme at different stretches of road under Uttar Dinajpur Highway Division. | BP-2024-25-197 | 20/09/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 13.36 | 0 | 0 | 0
801 | UTTAR DINAJPUR | Raiganj Division | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11865 | New | Implementation of MAKDAMPUR andit's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division. | 1992/RD/PHE | 14/11/2022 | 1146 | AJIT PRAMANIK AJITPRAMANICK83@GMAIL.COM | 412.01 | 0 | 0 | 70
802 | UTTAR DINAJPUR | Raiganj Division | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11865 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Makdampur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3753/RD/PHED | 18/12/2024 | 225 | SANDIP SARKAR | 34.56 | 0 | 0 | 65
803 | UTTAR DINAJPUR | Malda Mechanical | MAKDAMPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT. , SM/11865 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of MAKDAMPUR Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011908) | 2202/MLMD | 18/07/2023 | 673 | M/S D.G.B. ENTERPRISE. | 10.92 | 0 | 0 | 100
804 | UTTAR DINAJPUR | Raiganj Division | MALIGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13502 | New | Material Requisition To Resource Division | 977/RD/PHE | 30/03/2023 | 0 | Resource Division | 34.86 | 0 | 0 | 0
805 | UTTAR DINAJPUR | Malda Mechanical | MALIGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13502 | New | Quotation for new service connection at MALIGAON PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(SM/13502) | BP-2024-25-239 | 29/05/2024 | 0 | W.B.S.E.D.C.LTD | 12.83 | 0 | 0 | 0
806 | UTTAR DINAJPUR | Malda Mechanical | MALIGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13502 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Maligaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015800) | 2520/MLMD | 04/08/2023 | 907 | M/S. KUNDU CONSTRACTION | 27.47 | 0 | 0 | 80
807 | UTTAR DINAJPUR | Raiganj Division | MALIGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13502 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
808 | UTTAR DINAJPUR | Raiganj Division | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13503 | New | Material Requisition To Resource Division | 1044/RD/PHE | 05/04/2023 | 0 | Resource Division | 29.31 | 0 | 0 | 0
809 | UTTAR DINAJPUR | Malda Mechanical | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13503 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Tarapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015620) | 2536/MLMD | 04/08/2023 | 817 | MANIK CHANDRA SAHA. | 26.44 | 0 | 0 | 72
810 | UTTAR DINAJPUR | Malda Mechanical | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13503 | New | Quotation for Tarapur PH-II pwss (Kanki CCC). | BP-2023-24-518 | 08/02/2024 | 0 | W.B.S.E.D.C.LTD | 7.72 | 0 | 0 | 0
811 | UTTAR DINAJPUR | Malda Mechanical | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13503 | New | Quotation for new service connection at TARAPUR PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-88 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 6.92 | 0 | 0 | 0
812 | UTTAR DINAJPUR | Raiganj Division | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13503 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
813 | UTTAR DINAJPUR | Raiganj Division | TARAPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13503 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Tarapur Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | 1826/RD/PHE | 25/06/2025 | 180 | AJIT PRAMANIK | 29.59 | 0 | 0 | 0
814 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN RAMPUR Piped Water Supply Scheme , SM/13232 | New | Material Requisition To Resource Division | 849/RD/PHE | 24/03/2023 | 0 | Resource Division | 28.8 | 0 | 0 | 0
815 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN RAMPUR Piped Water Supply Scheme , SM/13232 | New | Quotation for new service connection at Dakshin Rampur PH-I (Kanki ccc) in the district of Uttar Dinajpur. | BP-2023-24-655 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 6.23 | 0 | 0 | 0
816 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN RAMPUR Piped Water Supply Scheme , SM/13232 | New | Quotation for new service connection at Dakshin Rampur PH-II (Kanki ccc) in the district of Uttar Dinajpur. | BP-2023-24-656 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.03 | 0 | 0 | 0
817 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN RAMPUR Piped Water Supply Scheme , SM/13232 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
818 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN RAMPUR Piped Water Supply Scheme , SM/13232 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dakshin Rampur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015519) | 3696/MLMD | 29/11/2023 | 790 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 27.49 | 0 | 0 | 74
819 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN RAMPUR Piped Water Supply Scheme , SM/13232 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakshin Rampur Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | 1987/RD/PHE | 04/07/2025 | 180 | AJIT PRAMANIK | 30.93 | 0 | 0 | 0
820 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Majlishpur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14230 | Augmentation | Rig Bored Tube-Well In connection with Source Augmentation In Different Piped Water Supply Scheme 1.Debiganj, 2.Gunabari, 3. Majlishpur. 4. Sripur in the District of Uttar Dinajpur Under Raiganj Division, P.H.E. Dte. | 470/RD/PHE | 16/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI | 42.57 | 0 | 0 | 100
821 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Majlishpur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14230 | Augmentation | Material Requisition To Resource Division | 2387/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.4 | 0 | 0 | 0
822 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Majlishpur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14230 | Augmentation | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Majlishpur Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 61/RD/PHE | 16/01/2023 | 45 | DONE ENTERPRISE PAPIYABHOWMICK7@GMAIL.COM | 17.7 | 0 | 0 | 62
823 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Majlishpur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14230 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Majlishpur, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-433 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.68 | 0 | 0 | 0
824 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Majlishpur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14230 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Majlishpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016480) | 2521/MLMD | 04/08/2023 | 480 | JIBON GHOSH. | 10.86 | 0 | 0 | 100
825 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN ARIAGAON Pipe Water Supply Scheme , SM/15305 | New | Material Requisition To Resource Division | 899/RD/PHE | 28/03/2023 | 0 | Resource Division | 36.35 | 0 | 0 | 0
826 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN ARIAGAON Pipe Water Supply Scheme , SM/15305 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dakshin Ariagaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018381) | 2636/MLMD | 10/08/2023 | 871 | M/S D.G.B. ENTERPRISE. | 26.28 | 0 | 0 | 64
827 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN ARIAGAON Pipe Water Supply Scheme , SM/15305 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
828 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN ARIAGAON Pipe Water Supply Scheme , SM/15305 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakhin Ariagaon Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | 2495/RD/PHE | 12/09/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 29.58 | 0 | 0 | 0
829 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Pokheria Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14226 | Augmentation | Material Requisition To Resource Division | 2399/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.38 | 0 | 0 | 0
830 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Pokheria Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14226 | Augmentation | Quotation for new service connection at Source Augmentation of POKHERIA PH-III (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-79 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 14.28 | 0 | 0 | 0
831 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Pokheria Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14226 | Augmentation | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Pokheria Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 62/RD/PHE | 16/01/2023 | 941 | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 17.78 | 0 | 0 | 90
832 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Pokheria Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14226 | Augmentation | Rig Bored Tube-Well in connection with Source Augmentation In Different Piped Water Supply Scheme 1.Mohua, 2. Pawakhali, 3. Pokheria in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 471/RD/PHE | 16/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI | 31.92 | 0 | 0 | 80
833 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Pokheria Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14226 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Pokheria Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016497) | 4771/MLMD | 29/12/2023 | 474 | ARATI ENGINEERING | 10.91 | 0 | 0 | 100
834 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16491 | New | Material Requisition To Resource Division | 838/RD/PHE | 23/03/2023 | 0 | Resource Division | 41.51 | 0 | 0 | 0
835 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16491 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dakshin Neamatpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015935) | 2491/MLMD | 04/08/2023 | 907 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 26.45 | 0 | 0 | 72
836 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16491 | New | Quotation for new service connection at DAKSHIN NEAMATPUR PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/16491) | BP-2024-25-264 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 5.41 | 0 | 0 | 0
837 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16491 | New | Quotation for new service connection at DAKSHIN NEAMATPUR PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/16491) | BP-2024-25-263 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 5.41 | 0 | 0 | 0
838 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN NEAMATPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16491 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
839 | UTTAR DINAJPUR | Raiganj Division | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/16226 | New | Material Requisition To Resource Division | 1203/RD/PHE | 28/04/2023 | 0 | Resource Division | 22.84 | 0 | 0 | 0
840 | UTTAR DINAJPUR | Raiganj Division | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/16226 | New | Laying of Additional pipeline with other ancillary works at different mouzas of BARDAHI PWSS under Islampur Sub-Division P.H.E. Dte. | 3495/RD/PHE | 02/12/2024 | 45 | APEX ENTERPRISES | 24.82 | 0 | 0 | 0
841 | UTTAR DINAJPUR | Raiganj Division | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/16226 | New | Construction of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Bardahi PWSS at Karandighi Block under Raiganj Division, PHE dte. | 2897/RD/PHE | 25/09/2024 | 20 | SANDIP SARKAR | 6.83 | 0 | 0 | 0
842 | UTTAR DINAJPUR | Raiganj Division | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/16226 | New | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 13.09.2024 and 18.09.2024. | BP-2024-25-225 | 04/10/2024 | 0 | SAHA CONSTRUCTION | 0.05 | 0 | 0 | 0
843 | UTTAR DINAJPUR | Malda Mechanical | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/16226 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Bardahi Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017556) | 2732/MLMD | 14/08/2023 | 867 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 24.37 | 0 | 0 | 42
844 | UTTAR DINAJPUR | Raiganj Division | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/16226 | New | Implementation of BARDAHI and its adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2628/RD/PHE | 13/09/2023 | 890 | A D ENTERPRISE | 183.7 | 0 | 0 | 55
845 | UTTAR DINAJPUR | Raiganj Division | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/16226 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BARDAHI PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 654/RD/PHE | 05/03/2024 | 319 | UJJAL KUMAR SARKAR PARTNER KUMARUJJAL51@GMAIL.COM | 11.27 | 0 | 0 | 100
846 | UTTAR DINAJPUR | Raiganj Division | BARDAHI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/16226 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BARDAHI PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 655/RD/PHE | 05/03/2024 | 319 | PANDIT CONSTRUCTION PANDIT.RNJ@GMAIL.COM | 11.27 | 0 | 0 | 100
847 | UTTAR DINAJPUR | Raiganj Division | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16223 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
848 | UTTAR DINAJPUR | Malda Mechanical | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16223 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Bahala (Zone-II) PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003279126 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 4.28 | 0 | 0 | 100
849 | UTTAR DINAJPUR | Malda Mechanical | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16223 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Bahala (Zone-II) PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003279119 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 3.29 | 0 | 0 | 100
850 | UTTAR DINAJPUR | Raiganj Division | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16223 | New | Material Requisition To Resource Division | 2241/RD/PHE | 02/08/2023 | 0 | Resource Division | 23.33 | 0 | 0 | 0
851 | UTTAR DINAJPUR | Raiganj Division | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16223 | New | Implementation of BAHALA ZONE-II and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1278/RD/PHE | 08/05/2023 | 969 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 345.32 | 0 | 0 | 52
852 | UTTAR DINAJPUR | Malda Mechanical | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16223 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Bahala Zone- II Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018496) | 2727/MLMD | 14/08/2023 | 888 | S PATHAK & CO. | 24.05 | 0 | 0 | 88
853 | UTTAR DINAJPUR | Raiganj Division | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16223 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | 1746/RD/PHE | 14/06/2024 | 198 | DEBASISH GHOSH | 2.6 | 0 | 0 | 0
854 | UTTAR DINAJPUR | Raiganj Division | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16223 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bahala zone -2 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 25/RD/PHE | 02/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 57.51 | 0 | 0 | 0
855 | UTTAR DINAJPUR | Raiganj Division | Bahala Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16223 | New | Balance distribution System Of Laying pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAHALA ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 635/RD/PHE | 05/03/2024 | 225 | M/S GHOSH CONSTRUCTION GHOSH1.RNJ@GMAIL.COM | 22.7 | 0 | 0 | 25
856 | UTTAR DINAJPUR | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/17255 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
857 | UTTAR DINAJPUR | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/17255 | New | Material Requisition To Resource Division | 2250/RD/PHE | 03/08/2023 | 0 | Resource Division | 28.77 | 0 | 0 | 0
858 | UTTAR DINAJPUR | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/17255 | New | Implementation of SAMASPUR and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division,PHE Dte. | 1280/RD/PHE | 08/05/2023 | 900 | UTTAM SAHA | 418.14 | 0 | 0 | 35
859 | UTTAR DINAJPUR | Malda Mechanical | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/17255 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Samaspur, Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-632 | 06/03/2024 | 0 | W.B.S.E.D.C.LTD | 0.56 | 0 | 0 | 0
860 | UTTAR DINAJPUR | Malda Mechanical | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/17255 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Samaspur, Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-633 | 06/03/2024 | 0 | W.B.S.E.D.C.LTD | 0.45 | 0 | 0 | 0
861 | UTTAR DINAJPUR | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/17255 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
862 | UTTAR DINAJPUR | Malda Mechanical | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/17255 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Samaspur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/019160) | 2767/MLMD | 14/08/2023 | 987 | M/S TRILOCHAN CONSTRUCTION CO. | 24.39 | 0 | 0 | 88
863 | UTTAR DINAJPUR | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/17255 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | 1746/RD/PHE | 14/06/2024 | 198 | DEBASISH GHOSH | 2.6 | 0 | 0 | 0
864 | UTTAR DINAJPUR | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT HEMTABAD BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/17255 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Samaspur PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 26/RD/PHE | 02/01/2025 | 45 | UTTAM SAHA | 31.62 | 0 | 0 | 0
865 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. , SM/18295 | Augmentation | Material Requisition To Resource Division | 1188/RD/PHE | 27/04/2023 | 0 | Resource Division | 288.75 | 0 | 0 | 0
866 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. , SM/18295 | Augmentation | Augmentation of ITAHAR Zone-I and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division,PHE Dte. | 1997/RD/PHE | 13/07/2023 | 928 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 568.17 | 0 | 0 | 30
867 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. , SM/18295 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound yard lighting arrangement at T/W no. I of Augmentation of Itahar Water Supply Scheme(Zone-I) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018165) | 2644/MLMD | 10/08/2023 | 1021 | JIBU SINGHA | 26.96 | 0 | 0 | 0
868 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. , SM/18295 | Augmentation | Construction Of Approach Road, Laying of Pipe Line,Retaining And Other Allied Works Of Itahar Zone -I Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3566/RD/PHE | 05/12/2024 | 91 | AJIT PRAMANIK | 95.62 | 0 | 0 | 0
869 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. , SM/18295 | Augmentation | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.Vehicle no. WB74AP 7552) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month( period from 27.11.2024 to 26.05.2025). | 3446/RD/PHE | 26/11/2024 | 181 | M/S SARKAR ENTERPRISE SILIGURI | 2.4 | 0 | 0 | 0
870 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Itahar Zone-I Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. , SM/18295 | Augmentation | Supply, installation and commissioning of electro-mechanical components at T/W No. III of Augmentation of ITAHAR water supply scheme (Zone- I) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 1692/MLMD | 28/03/2025 | 120 | DAS CONSTRUCTION | 11.06 | 0 | 0 | 0
871 | UTTAR DINAJPUR | Raiganj Division | Dwipnagar Piped Water Supply Scheme. , SM/18180 | New | Material Requisition To Resource Division | 653/RD/PHE | 03/03/2023 | 0 | Resource Division | 77.81 | 0 | 0 | 0
872 | UTTAR DINAJPUR | Raiganj Division | Dwipnagar Piped Water Supply Scheme. , SM/18180 | New | Material Requisition To Resource Division | 1330/RD/PHE | 15/05/2023 | 0 | Resource Division | 77.13 | 0 | 0 | 0
873 | UTTAR DINAJPUR | Raiganj Division | Dwipnagar Piped Water Supply Scheme. , SM/18180 | New | Implementation of DWIPNAGAR and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1133/RD/PHE | 24/04/2023 | 983 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 374.36 | 0 | 0 | 50
874 | UTTAR DINAJPUR | Raiganj Division | Dwipnagar Piped Water Supply Scheme. , SM/18180 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Khalsi, 2.Dwipnagar in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 1490/RD/PHE | 17/05/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 52.73 | 0 | 0 | 90
875 | UTTAR DINAJPUR | Malda Mechanical | Dwipnagar Piped Water Supply Scheme. , SM/18180 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dwipnagar, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-553 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 3.3 | 0 | 0 | 0
876 | UTTAR DINAJPUR | Malda Mechanical | Dwipnagar Piped Water Supply Scheme. , SM/18180 | New | Additional Quotation of Dwipnagar TW-II in the district of Uttar Dinajpur. | BP-2024-25-413 | 30/07/2024 | 0 | W.B.S.E.D.C.LTD | 4.03 | 0 | 0 | 0
877 | UTTAR DINAJPUR | Malda Mechanical | Dwipnagar Piped Water Supply Scheme. , SM/18180 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Dwipnagar, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-552 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 5.62 | 0 | 0 | 0
878 | UTTAR DINAJPUR | Malda Mechanical | Dwipnagar Piped Water Supply Scheme. , SM/18180 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II of Dwipnagar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/004005) | 2440/MLMD | 04/08/2023 | 815 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 22.38 | 0 | 0 | 100
879 | UTTAR DINAJPUR | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. , SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Chotaparua PWSS 2.Udaypur PWSS 3.Piplan PWSS 4.Barua PWSS 5.Bindol PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | 3281/RD/PHE | 20/11/2024 | 45 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 21.67 | 0 | 0 | 0
880 | UTTAR DINAJPUR | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. , SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Kanki PWSS 2.Deona PWSS 3.Pokheria PWSS 4.Lodhon PWSS under Islampur Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and ongoing PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | 3277/RD/PHE | 20/11/2024 | 45 | HAQUE CONSTRUCTION | 17.33 | 0 | 0 | 0
881 | UTTAR DINAJPUR | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. , SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Dakshin Kundalpukhur PWSS 2.Purba Chutiakhore PWSS 3.Pawakhali PWSS 4.Amalbari PWSS under Islampur Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | 3279/RD/PHE | 20/11/2024 | 45 | M/S LUCKY CONSTRUCTION | 17.32 | 0 | 0 | 0
882 | UTTAR DINAJPUR | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. , SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Goagaon PWSS 2.Ghirnigaonkhas PWSS 3.Panjipara PWSS 4.Khowaspur PWSS under Islampur Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | 3278/RD/PHE | 20/11/2024 | 45 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 17.34 | 0 | 0 | 0
883 | UTTAR DINAJPUR | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. , SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Kasba NM PWSS 2.Sitgram PWSS 3.Sasan PWSS 4.Gutin PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | 3282/RD/PHE | 20/11/2024 | 45 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 17.34 | 0 | 0 | 0
884 | UTTAR DINAJPUR | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. , SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Malgaon PWSS 2.Bheur PWSS 3.Purba Rampur PWSS 4.Faridpur PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte. (TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | 3284/RD/PHE | 20/11/2024 | 45 | UJJAL KUMAR SARKAR PARTNER | 17.33 | 0 | 0 | 0
885 | UTTAR DINAJPUR | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. , SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Baruna PWSS 2.Mahinagar PWSS 3.Kunore PWSS 4.Majhiar PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte. (TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | 3285/RD/PHE | 20/11/2024 | 45 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 17.33 | 0 | 0 | 0
886 | UTTAR DINAJPUR | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. , SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Surun PWSS 2.Shridharpur PWSS 3.Kaliganj PWSS 4.Chandol PWSS 5.Kotar PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | 3287/RD/PHE | 20/11/2024 | 45 | PANDIT CONSTRUCTION | 21.67 | 0 | 0 | 0
887 | UTTAR DINAJPUR | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. , SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Bamir PWSS 2.Hemtabad Zone-I PWSS 3.Poaltair PWSS 4.Tungail Bilpara PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | 3283/RD/PHE | 20/11/2024 | 45 | BISWADEEP MALLICK | 17.34 | 0 | 0 | 0
888 | UTTAR DINAJPUR | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. , SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Sergram PWSS 2.Phulatti PWSS 3.Puria PWSS under Raiganj Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | 3286/RD/PHE | 20/11/2024 | 45 | M/S BHOWMIK CONSTRUCTION | 13 | 0 | 0 | 0
889 | UTTAR DINAJPUR | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. , SM/18828 | Augmentation | Construction of Soak well at Head Work Site of Paharajpur Piped Water Supply Scheme in connection with additional source of drinking water by creating stand posts and soak gallery at different locations in each Commissioned and On-Going PWSS under Raiganj Division, P.H.E. Dte. | 2672/RD/PHE | 20/09/2023 | 30 | M/S PRATIMA CHOUDHURY | 5.42 | 0 | 0 | 100
890 | UTTAR DINAJPUR | Raiganj Division | Additional source of drinking water by creating stand posts and soak gallery at different locations in each commissioned and on-going PWSSs. , SM/18828 | Augmentation | Construction of 3 mtr Internal diameter and 6 mtr Deep Circular Soak Well for Wash out /Over Flow water from IEP & OHR in Head Work Site at 1.Bhutijhari PWSS 2.Matikunda PWSS 3.Goalpokhur PWSS 4.Chakulia PWSS under Islampur Sub-Division in connection with Additional Sources of drinking water by Creating Stand Posts and Soak Gallery at different locations in each commissioned and on going PWSS under Raiganj Division,PHE dte.(TSM/005420) in the District Of Uttar Dinajpur under Raiganj Division,PHE Dte. | 3280/RD/PHE | 20/11/2024 | 225 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 17.32 | 0 | 0 | 0
891 | UTTAR DINAJPUR | Raiganj Division | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. , SM/13456 | New | Material Requisition To Resource Division | 1198/RD/PHE | 28/04/2023 | 0 | Resource Division | 35.74 | 0 | 0 | 0
892 | UTTAR DINAJPUR | Raiganj Division | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. , SM/13456 | New | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 23.08.2024 & 28.08.2024. | BP-2024-25-221 | 04/10/2024 | 0 | SAHA CONSTRUCTION | 0.08 | 0 | 0 | 0
893 | UTTAR DINAJPUR | Malda Mechanical | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. , SM/13456 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Agoi, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-428 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.95 | 0 | 0 | 0
894 | UTTAR DINAJPUR | Malda Mechanical | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. , SM/13456 | New | Quotation for new service connection at AGOI PH-I (Goalpokher CCC) in the district of Uttar Dinajpur. | BP-2023-24-618 | 04/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.2 | 0 | 0 | 0
895 | UTTAR DINAJPUR | Malda Mechanical | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. , SM/13456 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Agoi Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015320) | 2457/MLMD | 04/08/2023 | 840 | M/S D.G.B. ENTERPRISE. | 27.27 | 0 | 0 | 86
896 | UTTAR DINAJPUR | Raiganj Division | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. , SM/13456 | New | Providing FHTC in connection with Agoi Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 1181/RD/PHE | 23/04/2025 | 30 | ANILA CONSTRUCTION | 5.06 | 0 | 0 | 0
897 | UTTAR DINAJPUR | Raiganj Division | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. , SM/13456 | New | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at AGOI PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. | 1204/RD/PHE | 25/04/2025 | 45 | M/S PINKI CONSTRUCTION | 63.3 | 0 | 0 | 0
898 | UTTAR DINAJPUR | Raiganj Division | AGOI Piped Water Supply Scheme at Goalpokhar-I Block Under Uttar Dinajpur District. , SM/13456 | New | Providing FHTC in connection with Agoi Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 1182/RD/PHE | 23/04/2025 | 30 | M/S SARKAR ENTERPRISE | 5.06 | 0 | 0 | 0
899 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Bhagabati Piped Water Supply Scheme under Chopra Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12648 | Augmentation | Source(Rig Bored Tube-Well) Augmentation of Bhagabati Piped Water Supply Scheme of Chopra Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1910/RD | 28/10/2022 | 45 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 32.3 | 0 | 0 | 0
900 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Bhagabati Piped Water Supply Scheme under Chopra Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12648 | Augmentation | Material Requisition To Resource Division | 2401/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.48 | 0 | 0 | 0
901 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Bhagabati Piped Water Supply Scheme under Chopra Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12648 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Bhagabati Water Supply Scheme in the District of Uttar DInajpur under Malda Mechanical Division, PHE Dte. (TSM/015035) | 3690/MLMD | 29/11/2023 | 911 | SUBRATA KUMAR DAS. | 10.57 | 0 | 0 | 87
902 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Bhagabati Piped Water Supply Scheme under Chopra Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12648 | Augmentation | Quotation for new service connection at Source Aug of BHAGABATI PH-III (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-57 | 09/04/2024 | 0 | W.B.S.E.D.C.LTD | 5.58 | 0 | 0 | 0
903 | UTTAR DINAJPUR | Raiganj Division | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12789 | New | Material Requisition To Resource Division | 1200/RD/PHE | 28/04/2023 | 0 | Resource Division | 26.38 | 0 | 0 | 0
904 | UTTAR DINAJPUR | Malda Mechanical | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12789 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Kichaktola Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014974) | 2512/MLMD | 04/08/2023 | 937 | SUBHAS CHANDRA KESHORI | 26.43 | 0 | 0 | 72
905 | UTTAR DINAJPUR | Malda Mechanical | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12789 | New | Quotation for new service connection at KICHAKTALA PH-I (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-51 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 7.74 | 0 | 0 | 0
906 | UTTAR DINAJPUR | Malda Mechanical | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12789 | New | Quotation for new service connection at KICHAKTALA PH-II (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-52 | 09/04/2024 | 0 | W.B.S.E.D.C.LTD | 7.53 | 0 | 0 | 0
907 | UTTAR DINAJPUR | Raiganj Division | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12789 | New | Providing FHTC in connection with Kichaktola Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 1178/RD/PHE | 23/04/2025 | 30 | MAA SHEETALA ENTERPRISE | 12.76 | 0 | 0 | 0
908 | UTTAR DINAJPUR | Raiganj Division | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12789 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kichaktala Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | 1825/RD/PHE | 25/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.59 | 0 | 0 | 0
909 | UTTAR DINAJPUR | Raiganj Division | KICHAKTALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12789 | New | Laying of additional pipeline for improving FHTCwith ancillary works at different mouzas at KICHAKTOLA PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | 2079/RD/PHE | 14/07/2025 | 180 | ROY ENGINEERS. (PATNA) | 38.99 | 0 | 0 | 0
910 | UTTAR DINAJPUR | Raiganj Division | KABUTARKHOPI Piped Water Supply Scheme , SM/13235 | New | Material Requisition To Resource Division | 971/RD/PHE | 29/03/2023 | 0 | Resource Division | 31.69 | 0 | 0 | 0
911 | UTTAR DINAJPUR | Malda Mechanical | KABUTARKHOPI Piped Water Supply Scheme , SM/13235 | New | Quotation for new service connection at Kabutarkhopi PH-I (Kanki ccc) in the district of Uttar Dinajpur. | BP-2023-24-657 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 6.8 | 0 | 0 | 0
912 | UTTAR DINAJPUR | Malda Mechanical | KABUTARKHOPI Piped Water Supply Scheme , SM/13235 | New | Quotation for new service connection at Kabutarkhopi PH-II (Kanki ccc) in the district of Uttar Dinajpur. | BP-2023-24-658 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 14.37 | 0 | 0 | 0
913 | UTTAR DINAJPUR | Raiganj Division | KABUTARKHOPI Piped Water Supply Scheme , SM/13235 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
914 | UTTAR DINAJPUR | Malda Mechanical | KABUTARKHOPI Piped Water Supply Scheme , SM/13235 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Kabutarkhopi Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 3755/MLMD | 27/11/2024 | 450 | DAS CONSTRUCTION | 26.2 | 0 | 0 | 81
915 | UTTAR DINAJPUR | Raiganj Division | Source augmentation for Goagoan Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12655 | Augmentation | Material Requisition To Resource Division | 2391/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.48 | 0 | 0 | 0
916 | UTTAR DINAJPUR | Malda Mechanical | Source augmentation for Goagoan Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12655 | Augmentation | Quotation for new service connection at Source Augmentation of GOAGAON PH-III (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-91 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 4.01 | 0 | 0 | 0
917 | UTTAR DINAJPUR | Raiganj Division | Source augmentation for Goagoan Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12655 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Goagaon Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1924/RD/PHE | 28/10/2022 | 270 | S. B. CONSTRUCTION | 33.07 | 0 | 0 | 25
918 | UTTAR DINAJPUR | Malda Mechanical | Source augmentation for Goagoan Piped Water Supply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12655 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Goagaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2947/MLMD | 11/09/2024 | 506 | SARADA MAA CONSTRUCTION. | 10.78 | 0 | 0 | 84
919 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Sherpur Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/13015 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No.III of Sherpur , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003260403 | 08/11/2023 | 90 | W.B.S.E.D.C.LTD | 3.56 | 0 | 0 | 100
920 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Sherpur Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/13015 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Source Augmentation of Sherpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015245) | 2531/MLMD | 04/08/2023 | 120 | BINA CONSTRUCTION | 9.72 | 0 | 0 | 100
921 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Sherpur Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/13015 | Augmentation | Material Requisition To Resource Division | 19/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
922 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Sherpur Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/13015 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Sherpur Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1920/RD/PHE | 28/10/2022 | 786 | BIKASH KAR | 29.96 | 0 | 0 | 100
923 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Karandighi Zone-I Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 364/RD/PHE | 07/02/2023 | 45 | M/S MANDAL ENTERPRISE TUMPASONU05@YAHOO.COM | 4.12 | 0 | 0 | 100
924 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Karandighi Zone-I Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 1030/RD/PHE | 31/03/2023 | 45 | M/S SANTI TRADERS | 5.03 | 0 | 0 | 100
925 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Karandighi, Zone-I, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003118815 | 26/03/2023 | 7 | W.B.S.E.D.C.LTD | 0.73 | 0 | 0 | 0
926 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | Material Requisition To Resource Division | 1945/RD/PHE | 04/11/2022 | 0 | Resource Division | 112.29 | 0 | 0 | 0
927 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | Construction Of Boundary Wall With Gate at Head Work Site, & 2nd Tube-Well Site in connection with Augmentation Of Karandighi Zone-I PWSS at Chopra Block under Raiganj Division,PHE dte. | 3290/RD/PHE | 20/11/2024 | 30 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 15.76 | 0 | 0 | 0
928 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | Augmentation of KARANDIGHI(Zone-I)Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | 1670/RD/PHE | 05/09/2022 | 90 | DIPESH BHOWMIK | 196.21 | 0 | 0 | 100
929 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | Making compound lighting arrangement with allied works at T/W no. I of Karandighi Water Supply Scheme, (Zone- I) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011651) | 2234/MLMD | 18/07/2023 | 90 | SUBHAS CHANDRA KESHORI | 2.33 | 0 | 0 | 100
930 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | BP-2024-25-24 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 14.86 | 0 | 0 | 0
931 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | FHTC (Functional Household Tap Connection) for Karandighi Zone-I Water Supply Scheme [Augmentation Scheme] in Karandighi Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2030/RD/PHE | 17/11/2022 | 1169 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 80.36 | 0 | 0 | 70
932 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
933 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | Laying additional pipe line with FHTC for Augmentation Of Karandighi Zone-I Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | 3783/RD/PHE | 19/12/2024 | 405 | BHOLA PAUL | 46.07 | 0 | 0 | 60
934 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | Providing FHTC in connection with augmentation of Karandighi Zone-I Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | 47/RD/PHE | 03/01/2025 | 45 | M/S P.S. ENTERPRISE | 25.35 | 0 | 0 | 0
935 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
936 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Karandighi Zone-I Water Supply Scheme(Augmentation) at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | 2501/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 19.35 | 0 | 0 | 0
937 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of KARANDIGHI Water Supply Scheme (Zone-I) T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 247/MLMD | 24/02/2023 | 490 | DEY ENTERPRISE [HOWRAH] | 12.62 | 0 | 0 | 100
938 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of KARANDIGHI Water Supply Scheme (Zone-I) T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 246/MLMD | 24/02/2023 | 443 | DIPALI CONSTRUCTION. | 12.45 | 0 | 0 | 100
939 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-I in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11721 | Augmentation | Construction of Over Head Reservoir(Capacity-500 Cum) of KARANDIGHI(Zone-I) Pipe Water Supply Scheme at in connection with Augmentation Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 727/RD/PHE | 15/03/2023 | 839 | M/S ELITE CONSTRUCTION | 165.61 | 0 | 0 | 90
940 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Lakhipur and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. , SM/09181 | Retrofitting | Route Survey & Preparation of DPR of LAKHIPUR PWSS under Raiganj Division, PHE Dte. | 152/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 3.38 | 0 | 0 | 0
941 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Lakhipur and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. , SM/09181 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Lakhipur Piped Water Supply Scheme And adjoining Mouzas Water Supply Scheme In Islampur Block under Raiganj Division, P.H.E. Dte. | 2081/RD/PHE | 02/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 9.01 | 0 | 0 | 100
942 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Lakhipur and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. , SM/09181 | Retrofitting | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
943 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Ramganj and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. , SM/09187 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Ramganj Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Islampur Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1819/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 4.37 | 0 | 0 | 0
944 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Ramganj and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. , SM/09187 | Retrofitting | Preparation of Additional DPR For Ramganj Zone-II in connection with Retrofitting of Functional House Hold Tap Connection of Ramganj PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur | 2134/RD/PHE | 07/12/2022 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM MANASIJ_DUTTA@VSNL.COM | 0.78 | 0 | 0 | 1
945 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Ramganj and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. , SM/09187 | Retrofitting | Allied works in connection with retrofitting of FHTC in Ramganj PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2605/RD/PHE | 13/09/2023 | 60 | ASHIM CHANDA | 0.91 | 0 | 0 | 100
946 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Ramganj and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. , SM/09187 | Retrofitting | Material Requisition To Resource Division | 35/RD/PHE | 06/01/2022 | 0 | Resource Division | 6.81 | 0 | 0 | 0
947 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Ramganj and adjoining mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P. H. E. Dte. , SM/09187 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) Under Ramganj Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Islampur Block Under Raiganj Division, P.H.E. Dte. | 2087/RD/PHE | 02/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 28.69 | 0 | 0 | 1
948 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Paharajpur WSS for installation of FHTC. , SM/09145 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of PAHARAJPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2383/RD/PHE | 24/12/2021 | 30 | M/S LOKENATH CONSTRUCTION | 8.44 | 0 | 0 | 0
949 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Siripur for installation of FHTC. , SM/09136 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Siripur for installation of FHTC under Raiganj Division P.H.E. Dte. | 2201/RD/PHE | 17/11/2021 | 30 | HAQUE CONSTRUCTION | 8.21 | 0 | 0 | 0
950 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Goagaon for installation of FHTC. , SM/09123 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Goagaon Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2144/RD/PHE | 12/11/2021 | 30 | PANDIT CONSTRUCTION | 3.36 | 0 | 0 | 1
951 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Maslandpur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. (Phase-II) , SM/10463 | Retrofitting | Restoration Of Pipe Line For Providing FHTC for Maslandapur Water Supply Scheme under Raiganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | 1039/RD/PHED | 12/05/2022 | 30 | M/S MANDAL ENTERPRISE | 7.33 | 0 | 0 | 65
952 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe Line for providing FHTC of Intia Piped Water Supply Scheme for installation of FHTC under Raiganj Division, P.H.E. Dte. (Phase-II) , SM/10447 | Retrofitting | Restoration of Pipeline for Providing FHTC of Intia Water Supply Scheme for installation of FHTC under Raiganj Division, P.H.E Dte. (Phase - II) | 1037/RD/PHED | 12/05/2022 | 30 | PANDIT CONSTRUCTION | 6.59 | 0 | 0 | 1
953 | UTTAR DINAJPUR | Malda Mechanical | Solarisation of WBSEDCL energised Pump house with Supply and Installation of Grid Connected Rooftop solar PV systems with Net metering for Sahavita water Supply scheme in the district of Uttar Dinajpur under malda Mechanical Division, PHE Dte. , SM/10232 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Rooftop Solar PV systems with Net Metering including five (05) years comprehensive maintenance for Sahavita Water Supply Scheme in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 544 /MLMD | 28/03/2022 | 1871 | CARBON SERVICES INDIA | 5.82 | 0 | 0 | 0
954 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Sripur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) , SM/10441 | Retrofitting | Restoration of pipe line for providing FHTC for Sripur water Supply Scheme under Itahar Block under Raiganj Division PHE Dte.(Phase - II) | 1033/RD/PHED | 12/05/2022 | 30 | UJJAL KUMAR SARKAR | 5.15 | 0 | 0 | 100
955 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Mahammadpur Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12654 | Augmentation | Material Requisition To Resource Division | 13/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
956 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Mahammadpur Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12654 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Mahammadpur Piped Water Supply Scheme of Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1917/RD/PHE | 28/10/2022 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 34.87 | 0 | 0 | 0
957 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Mahammadpur Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12654 | Augmentation | Supply, installation, commissioning & trial operation of electro-mechanical components at T/W No. III of Source Augmentation of MAHAMMADPUR Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 1004/MLMD | 11/03/2024 | 837 | DAS CONSTRUCTION | 11.48 | 0 | 0 | 0
958 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe Line for providing FHTC at Bhagabati Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) , SM/10424 | Retrofitting | Restoration of damaged Pipe Line work required for FHTC work at Bhagabati Piped Water Supply Scheme under Islampur Sub-Divion, P.H.E. Dte. (Part-A) | 2319/RD/PHED | 09/12/2021 | 45 | M/S P.S. ENTERPRISE | 10.21 | 0 | 0 | 1
959 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe Line for providing FHTC at Bhagabati Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) , SM/10424 | Retrofitting | Restoration of Pipe Line for providing F.H.T.C. at Bhagabati Water Supply Scheme under Islampur Sub-Division P.H.E. Dte.(Phase-II) | 1050/RD/PHED | 12/05/2022 | 45 | TAPAN KUMAR MAJUMDER | 14.06 | 0 | 0 | 1
960 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | Material Requisition To Resource Division | 1974/RD/PHE | 08/11/2022 | 0 | Resource Division | 36.35 | 0 | 0 | 0
961 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Kasba(NM) Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E Dte. | 433/RD/PHE | 10/02/2023 | 45 | M/S NATARAJ CONSTRUCTION DEBUABCD.1234@REDIFFMAIL.COM | 3.24 | 0 | 0 | 0
962 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of KASBA (NM) Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 426/MLMD | 14/03/2023 | 90 | HANNAN BUILDERS PVT. LTD. | 10.8 | 0 | 0 | 0
963 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of KASBA (NM) Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 427/MLMD | 14/03/2023 | 90 | MERCURY ENGINEERING COMPANY. | 10.44 | 0 | 0 | 100
964 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Kasba (NM) PWSS , Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003132613 | 12/04/2023 | 15 | W.B.S.E.D.C.LTD | 0.54 | 0 | 0 | 0
965 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Kasba (NM), Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 100000094175 | 30/11/2023 | 90 | W.B.S.E.D.C.LTD | 1.17 | 0 | 0 | 100
966 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | Construction of Over Head Reservoir(Capacity-450 Cum) of KASBA(NM) Pipe Water Supply Scheme in connection with Augmentation at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 725/RD/PHE | 15/03/2023 | 716 | CHAKRABORTY CONSTRUCTION | 158.66 | 0 | 0 | 40
967 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | FHTC (Functional Household Tap Connection) for Kasba(NM) Water Supply Scheme [Augmentation Scheme]in Raiganj Block Of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 757/RD/PHE | 17/03/2023 | 801 | BHOLA PAUL | 92.67 | 0 | 0 | 55
968 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | Construction of Pump House (size 4.10 m x 3.50 m outer to outer) with sanitary and water supply arrangement according to departmental drawing with toilet at 3nd Tube-Well Site in connection with Augmentation of Kasba-NM PWSS | 2362/RD/PHE | 11/08/2023 | 60 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 5.02 | 0 | 0 | 92
969 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | Augmentation work of KASBA(NM) Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | 1544/RD/PHE | 26/08/2022 | 90 | AJIT PARMANIK | 212.07 | 0 | 0 | 95
970 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | Construction of Boundary Wall With Gate at 2nd and 3rd Tube-Well Site under Augmentation Kasba NM PWSS at Raiganj Block under Raiganj Division,PHE dte. | 2887/RD/PHE | 25/09/2024 | 45 | BHOLA PAUL | 11.13 | 0 | 0 | 0
971 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of KASBA (NM) Water Supply Scheme T/W no. III in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 428/MLMD | 14/03/2023 | 90 | KUNDU CONSTRUCTION. | 10.97 | 0 | 0 | 100
972 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site, 2nd & 3rd tubewell site and road restoration of Kasba NM PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 417/RD/PHE | 29/01/2025 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 11.32 | 0 | 0 | 0
973 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kasba(NM) Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | 1801/RD/PHE | 24/06/2025 | 180 | AJIT PRAMANIK | 18.73 | 0 | 0 | 0
974 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KASBA (NM) PIPED WATER SUPPLY SCHEME , SM/11797 | Augmentation | Additional Pipe Line (UPVC) For Providing FHTC at Kasba(NM) PWSS at Raiganj Block of Uttar Dinajpur District Under Raiganj Division ,PHE Dte. | 1693/RD/PHE | 10/06/2024 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 10.68 | 0 | 0 | 100
975 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Noabari Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10500 | Retrofitting | Restoration of Pipe line for providing FHTC for Noabari(Kunore) Pipe Water Supply Scheme of Kaliaganj Block in the District of Uttar Dinajpur District under Raiganj Division, P.H.E Dte. | 1024/RD/PHE | 31/03/2023 | 30 | BHOWMICK ENTERPRISE | 0.91 | 0 | 0 | 0
976 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Noabari Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10500 | Retrofitting | Restoration of Pipe Line For Providing FHTC for Noabari(Baruna) Water Supply Scheme under Kaliyaganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | 1022/RD/PHE | 31/03/2023 | 45 | ANILA CONSTRUCTION | 11.49 | 0 | 0 | 100
977 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Noabari Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10500 | Retrofitting | charges for vehicle inspection | BP-2023-24-281 | 16/02/2024 | 0 | DEBASISH GHOSH | 0.4 | 0 | 0 | 0
978 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME , SM/11196 | Augmentation | Material Requisition To Resource Division | 1975/RD/PHE | 08/11/2022 | 0 | Resource Division | 70.56 | 0 | 0 | 0
979 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME , SM/11196 | Augmentation | Restoration of road for laying of water pipeline along and across the Kanki-Goagaon Road at different stretches under Chakulia PWSS under Raiganj Division, P.H.E.Dte. |  | 07/12/2022 | 0 | EXECUTIVE ENGINEER PWD ROADS | 1.7 | 0 | 0 | 0
980 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME , SM/11196 | Augmentation | Construction of Over Head Reservoir(Capacity-500 Cum) of CHAKULIA Pipe Water Supply Scheme in connection with Augmentation at GOALPOKHAR-II Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 728/RD/PHE | 15/03/2023 | 365 | MD HAKIMUDDIN | 165.54 | 0 | 0 | 0
981 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME , SM/11196 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Chakulia, Kanki C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003131653 | 24/05/2023 | 90 | W.B.S.E.D.C.LTD | 6.29 | 0 | 0 | 0
982 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME , SM/11196 | Augmentation |  | BP-2022-23-264 | 30/12/2022 | 0 | EXECUTIVE ENGINEER PWD ROADS | 1.7 | 0 | 0 | 0
983 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME , SM/11196 | Augmentation | FHTC (Functional Household Tap Connection) for Chakulia Water Supply Scheme [Augmentation Scheme] in Goalpukhur-II Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2016/RD/PHE | 17/11/2022 | 90 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 80 | 0 | 0 | 65
984 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME , SM/11196 | Augmentation | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | BP-2024-25-25 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 0.15 | 0 | 0 | 0
985 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME , SM/11196 | Augmentation | Augmentation of CHAKALIA Water Supply Scheme at Goalpokhar-II Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | 1407/RD/PHE | 25/07/2022 | 890 | SANYAL ENTERPRISE | 248.78 | 0 | 0 | 85
986 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME , SM/11196 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components and making compound lighting arrangement at T/W no. I of Augmentation of Chakulia Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/009723) | 266/MLMD | 24/02/2023 | 961 | KARMAKAR CONSTRICTION. | 13.73 | 0 | 0 | 0
987 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME , SM/11196 | Augmentation | Providing FHTC in connection with augmentation of Chakulia Pipe Water Supply Scheme at Goalpokher-II Block of Uttar Dinajpur District under Raiganj Division. | 51/RD/PHE | 03/01/2025 | 45 | AJIT PRAMANIK | 15.76 | 0 | 0 | 0
988 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME , SM/11196 | Augmentation | Construction of Boundary Wall With Gate at Head Work Site, & 3rd Tube-Well Site under Augmentation of Chakulia PWSS at Goalpukhur-II Block under Raiganj Division,PHE dte. | 2891/RD/PHE | 25/09/2024 | 315 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 44.17 | 0 | 0 | 75
989 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME , SM/11196 | Augmentation | Restoration of damaged pipeline due Culvert, Drain & PCC Road Construction with ancillary works at various mouzas in connection with Augmentation of Chakulia PWSS under Islampur Sub-Division P.H.E. Dte. | 3024/RD/PHE | 03/10/2024 | 60 | SANYAL ENTERPRISE | 20.59 | 0 | 0 | 0
990 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF CHAKULIA PIPED WATER SUPPLY SCHEME , SM/11196 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- II & III of Chakulia Water Supply Scheme in the District of Utter Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/009723) | 268/MLMD | 24/02/2023 | 476 | JIBU SINGHA | 20.69 | 0 | 0 | 100
991 | UTTAR DINAJPUR | Raiganj Division | POTHIA Piped Water Supply Scheme at Islampur Block , SM/12088 | New | Material Requisition To Resource Division | 607/RD/PHE | 27/02/2023 | 0 | Resource Division | 43.16 | 0 | 0 | 0
992 | UTTAR DINAJPUR | Malda Mechanical | POTHIA Piped Water Supply Scheme at Islampur Block , SM/12088 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Pothia Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014140) | 2216/MLMD | 18/07/2023 | 120 | S. P. CONSTRUCTION | 27.17 | 0 | 0 | 54
993 | UTTAR DINAJPUR | Raiganj Division | POTHIA Piped Water Supply Scheme at Islampur Block , SM/12088 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under POTHIA Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 594/RD/PHE | 05/03/2024 | 45 | PRINCE BUILDERS | 22.58 | 0 | 0 | 0
994 | UTTAR DINAJPUR | Malda Mechanical | POTHIA Piped Water Supply Scheme at Islampur Block , SM/12088 | New | Quotation for new service connection at Pothia PH-II (Islampur ccc) district Uttar Dinajpur. | BP-2023-24-590 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 14.25 | 0 | 0 | 0
995 | UTTAR DINAJPUR | Malda Mechanical | POTHIA Piped Water Supply Scheme at Islampur Block , SM/12088 | New | Quotation for new service connection at Pothia PH-I (Islampur ccc) | BP-2023-24-589 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 8.02 | 0 | 0 | 0
996 | UTTAR DINAJPUR | Raiganj Division | POTHIA Piped Water Supply Scheme at Islampur Block , SM/12088 | New | Implementation of POTHIA and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd Tube Well.) | 675/RD/PHE | 06/03/2023 | 1204 | UJJWAL DAS | 511.92 | 0 | 0 | 20
997 | UTTAR DINAJPUR | Raiganj Division | POTHIA Piped Water Supply Scheme at Islampur Block , SM/12088 | New | Laying of Additional pipeline with other ancillary works at different mouzas of POTHIA PWSS under Islampur Sub-Division P.H.E. Dte. | 3489/RD/PHE | 02/12/2024 | 90 | UJJWAL DAS | 36.3 | 0 | 0 | 50
998 | UTTAR DINAJPUR | Raiganj Division | POTHIA Piped Water Supply Scheme at Islampur Block , SM/12088 | New | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 05/10/2024 to 14/01/2025. | 3041/RD/PHE | 03/10/2024 | 102 | SISIR KUMAR DUTTA | 1.35 | 0 | 0 | 0
999 | UTTAR DINAJPUR | Raiganj Division | POTHIA Piped Water Supply Scheme at Islampur Block , SM/12088 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Pothia Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | 1986/RD/PHE | 04/07/2025 | 180 | AJIT PRAMANIK | 30.94 | 0 | 0 | 0
1000 | UTTAR DINAJPUR | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block , SM/12091 | New | Material Requisition To Resource Division | 2186/RD/PHE | 12/12/2022 | 0 | Resource Division | 30.47 | 0 | 0 | 0
1001 | UTTAR DINAJPUR | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block , SM/12091 | New | Material Requisition To Resource Division | 1217/RD/PHE | 02/05/2023 | 0 | Resource Division | 30.24 | 0 | 0 | 0
1002 | UTTAR DINAJPUR | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block , SM/12091 | New | Protection and restoration work of damaged flank caused by excavation for water supply project of PHE of patagora- Moragoti Road under Uttar Dinajpur Division, PWD. | BP-2023-24-145 | 30/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 6.39 | 0 | 0 | 0
1003 | UTTAR DINAJPUR | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block , SM/12091 | New | Construction of concrete pathway ,Land development and other ancillary works for AGDIMTI Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHED.under Raiganj Division, PHED.,U/D. | 3583/RD/PHE | 05/12/2024 | 30 | SOVAN KUMAR ROY | 10.96 | 0 | 0 | 0
1004 | UTTAR DINAJPUR | Malda Mechanical | AGDIMTI Piped Water Supply Scheme at Islampur Block , SM/12091 | New | Quotation for new service connection at AGDIMTI PH-II (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-93 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 9.15 | 0 | 0 | 0
1005 | UTTAR DINAJPUR | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block , SM/12091 | New | MDR T01, RAMKRISHHNAPUR TO MDR T10 DIMTI VIA BHARDRAKALI (ROAD CODE T06) | BP-2024-25-73 | 12/06/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 12.52 | 0 | 0 | 0
1006 | UTTAR DINAJPUR | Malda Mechanical | AGDIMTI Piped Water Supply Scheme at Islampur Block , SM/12091 | New | Quotation for new service connection at AGDIMTI PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-94 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 6.33 | 0 | 0 | 0
1007 | UTTAR DINAJPUR | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block , SM/12091 | New | Implementation of AGDIMTI and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under RaiganjDivision. PHE Dte. | 1035/RD/PHE | 04/04/2023 | 1066 | SOVAN KUMAR ROY | 563.17 | 0 | 0 | 71
1008 | UTTAR DINAJPUR | Malda Mechanical | AGDIMTI Piped Water Supply Scheme at Islampur Block , SM/12091 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Agdimti Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013515) | 2215/MLMD | 18/07/2023 | 836 | DIPALI CONSTRUCTION. | 27.17 | 0 | 0 | 67
1009 | UTTAR DINAJPUR | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block , SM/12091 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
1010 | UTTAR DINAJPUR | Raiganj Division | AGDIMTI Piped Water Supply Scheme at Islampur Block , SM/12091 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under AGDIMTI Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 589/RD/PHE | 05/03/2024 | 90 | BABA LOKNATH ENTERPRISE | 22.57 | 0 | 0 | 0
1011 | UTTAR DINAJPUR | Raiganj Division | GAISAL Piped Water Supply Scheme at Islampur Block , SM/12092 | New | Material Requisition To Resource Division | 2182/RD/PHE | 12/12/2022 | 0 | Resource Division | 33.1 | 0 | 0 | 0
1012 | UTTAR DINAJPUR | Malda Mechanical | GAISAL Piped Water Supply Scheme at Islampur Block , SM/12092 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Gaisal, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003199236 | 25/07/2023 | 90 | W.B.S.E.D.C.LTD | 12.15 | 0 | 0 | 100
1013 | UTTAR DINAJPUR | Malda Mechanical | GAISAL Piped Water Supply Scheme at Islampur Block , SM/12092 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Gaisal, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003204407 | 23/08/2023 | 90 | W.B.S.E.D.C.LTD | 8.02 | 0 | 0 | 100
1014 | UTTAR DINAJPUR | Raiganj Division | GAISAL Piped Water Supply Scheme at Islampur Block , SM/12092 | New | Material Requisition To Resource Division | 580/RD/PHE | 24/02/2023 | 0 | Resource Division | 33.1 | 0 | 0 | 0
1015 | UTTAR DINAJPUR | Malda Mechanical | GAISAL Piped Water Supply Scheme at Islampur Block , SM/12092 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Gaisal Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013516) | 2218/MLMD | 18/07/2023 | 834 | MANIK CHANDRA SAHA. | 27.22 | 0 | 0 | 73
1016 | UTTAR DINAJPUR | Raiganj Division | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12097 | New | Material Requisition To Resource Division | 2190/RD/PHE | 12/12/2022 | 0 | Resource Division | 44.2 | 0 | 0 | 0
1017 | UTTAR DINAJPUR | Malda Mechanical | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12097 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of PURGRAM, PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003123574 | 31/03/2023 | 365 | W.B.S.E.D.C.LTD | 0.74 | 0 | 0 | 0
1018 | UTTAR DINAJPUR | Malda Mechanical | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12097 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.II of Purgram PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003225016 | 08/09/2023 | 90 | W.B.S.E.D.C.LTD | 4 | 0 | 0 | 100
1019 | UTTAR DINAJPUR | Malda Mechanical | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12097 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Purgram Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013010) | 2087/MLMD | 04/07/2023 | 833 | KARMAKAR CONSTRICTION. | 26.42 | 0 | 0 | 90
1020 | UTTAR DINAJPUR | Raiganj Division | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12097 | New | Implementation of PURGRAM and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 70/RD/PHE | 16/01/2023 | 365 | SANYAL ENTERPRISE | 365.19 | 0 | 0 | 70
1021 | UTTAR DINAJPUR | Raiganj Division | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12097 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Purgram PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 09/RD/PHE | 02/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 38.95 | 0 | 0 | 0
1022 | UTTAR DINAJPUR | Raiganj Division | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12097 | New | Trial Run For Purgram PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | 526/RD/PHE | 12/02/2025 | 90 | SANYAL ENTERPRISE | 0.88 | 0 | 0 | 0
1023 | UTTAR DINAJPUR | Raiganj Division | PURGRAM Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12097 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Purgram Water Supply Scheme at Kaliaganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 40 M3/hr. | 1626/RD/PHE | 19/06/2025 | 180 | AJIT PRAMANIK | 18.73 | 0 | 0 | 0
1024 | UTTAR DINAJPUR | Raiganj Division | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12102 | New | Material Requisition To Resource Division | 2188/RD/PHE | 12/12/2022 | 0 | Resource Division | 21.78 | 0 | 0 | 0
1025 | UTTAR DINAJPUR | Malda Mechanical | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12102 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of CHANDIPUR PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003224917 | 08/09/2023 | 90 | W.B.S.E.D.C.LTD | 3.21 | 0 | 0 | 100
1026 | UTTAR DINAJPUR | Malda Mechanical | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12102 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of CHANDIPUR PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003224948 | 08/09/2023 | 90 | W.B.S.E.D.C.LTD | 3.87 | 0 | 0 | 100
1027 | UTTAR DINAJPUR | Malda Mechanical | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12102 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chandipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012771) | 2335/MLMD | 26/07/2023 | 120 | ORIENTAL ENGINEERING CO. | 25.19 | 0 | 0 | 85
1028 | UTTAR DINAJPUR | Raiganj Division | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12102 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHANDIPUR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 581/RD/PHE | 05/03/2024 | 45 | TRINAYANI ENTERPRISE | 22.58 | 0 | 0 | 0
1029 | UTTAR DINAJPUR | Malda Mechanical | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12102 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Chandipur PWSS ,Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-503 | 01/02/2024 | 0 | W.B.S.E.D.C.LTD | 4.22 | 0 | 0 | 0
1030 | UTTAR DINAJPUR | Raiganj Division | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12102 | New | Implementation of CHANDIPUR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 76/RD/PHE | 16/01/2023 | 1081 | PRASENJIT BASAK PROSENJITBASAK44@GMAIL.COM | 253.54 | 0 | 0 | 25
1031 | UTTAR DINAJPUR | Raiganj Division | CHANDIPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12102 | New | Balance Distribution system of Laying Pipeline with FHTC under Chandipur Piped Water Supply Scheme at Kaliyaganj Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dijanpur. (Phase-II) | 3012/RD/PHE | 03/10/2024 | 495 | PRASENJIT BASAK PROSENJITBASAK44@GMAIL.COM | 66.23 | 0 | 0 | 50
1032 | UTTAR DINAJPUR | Raiganj Division | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12105 | New | Material Requisition To Resource Division | 2183/RD/PHE | 12/12/2022 | 0 | Resource Division | 48.49 | 0 | 0 | 0
1033 | UTTAR DINAJPUR | Raiganj Division | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12105 | New | Restoration in connection with laying of PHE pipeline of Barduary- Bindole road under the jurisdiction of Uttar Dinajpur Highway Division in the district Uttar Dinajpur. | BP-2023-24-129 | 29/09/2023 | 0 | EXECUTIVE ENGINEER PWD ROADS | 22.53 | 0 | 0 | 0
1034 | UTTAR DINAJPUR | Malda Mechanical | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12105 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Rampur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012698) | 2371/MLMD | 28/07/2023 | 822 | WEST BENGAL ENGINEERING COMPANY. | 24.97 | 0 | 0 | 42
1035 | UTTAR DINAJPUR | Malda Mechanical | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12105 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Rampur Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-554 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 2.87 | 0 | 0 | 0
1036 | UTTAR DINAJPUR | Malda Mechanical | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12105 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Rampur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-555 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 6.87 | 0 | 0 | 0
1037 | UTTAR DINAJPUR | Malda Mechanical | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12105 | New | Additional Quotation of Rampur Water Supply Scheme Pump House-I in the Dist of Uttar Dinajpur. | BP-2024-25-308 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 6.79 | 0 | 0 | 0
1038 | UTTAR DINAJPUR | Raiganj Division | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12105 | New | Implementation of RAMPUR and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division. | 294/RD/PHE | 01/02/2023 | 1065 | UTTAM SAHA | 588.22 | 0 | 0 | 40
1039 | UTTAR DINAJPUR | Raiganj Division | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12105 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Rampur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3756/RD/PHED | 18/12/2024 | 103 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 95.53 | 0 | 0 | 0
1040 | UTTAR DINAJPUR | Raiganj Division | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12105 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RAMPUR Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 586/RD/PHE | 05/03/2024 | 360 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 22.82 | 0 | 0 | 90
1041 | UTTAR DINAJPUR | Raiganj Division | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12105 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Rampur Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 70 M3/hr. | 1796/RD/PHE | 24/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.92 | 0 | 0 | 0
1042 | UTTAR DINAJPUR | Raiganj Division | RAMPUR Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12105 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
1043 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Phulatti Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12646 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Phulatti PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003276671 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 8.1 | 0 | 0 | 100
1044 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Phulatti Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12646 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Source Augmentation of Phulatti Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015246) | 2525/MLMD | 04/08/2023 | 120 | BEE GEE CONSTRUCTION. | 9.71 | 0 | 0 | 100
1045 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Phulatti Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12646 | Augmentation | Material Requisition To Resource Division | 09/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
1046 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Phulatti Piped Water Supply Scheme under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12646 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Phulatti Piped Water Supply Scheme of Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1921/RD/PHE | 28/10/2022 | 815 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 25.83 | 0 | 0 | 85
1047 | UTTAR DINAJPUR | Malda Mechanical | KUNDARGAON Piped Water Supply Scheme at Islampur Block , SM/12086 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of KUNDARGAON, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003151020 | 18/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.39 | 0 | 0 | 100
1048 | UTTAR DINAJPUR | Malda Mechanical | KUNDARGAON Piped Water Supply Scheme at Islampur Block , SM/12086 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of KUNDARGAON , Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003194828 | 18/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.84 | 0 | 0 | 100
1049 | UTTAR DINAJPUR | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block , SM/12086 | New | Material Requisition To Resource Division | 617/RD/PHE | 28/02/2023 | 0 | Resource Division | 24.12 | 0 | 0 | 0
1050 | UTTAR DINAJPUR | Malda Mechanical | KUNDARGAON Piped Water Supply Scheme at Islampur Block , SM/12086 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Kundargaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014258) | 2214/MLMD | 18/07/2023 | 954 | M/S S. S. ENTERPRISE | 27.22 | 0 | 0 | 70
1051 | UTTAR DINAJPUR | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block , SM/12086 | New | Additional pipeline and other ancillary works at Kundargaon piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | 3484/RD/PHE | 02/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 41.22 | 0 | 0 | 0
1052 | UTTAR DINAJPUR | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block , SM/12086 | New | Implementation of KUNDARGAON and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd & 3rd Tube Well.) | 552/RD/PHE | 23/02/2023 | 720 | SANYAL ENTERPRISE | 321.28 | 0 | 0 | 60
1053 | UTTAR DINAJPUR | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block , SM/12086 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
1054 | UTTAR DINAJPUR | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block , SM/12086 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KUNDARGAON Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 293/RD/PHE | 15/01/2025 | 45 | MOON CONSTRUCTION | 22.58 | 0 | 0 | 0
1055 | UTTAR DINAJPUR | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block , SM/12086 | New | Trial Run For Kundargaon PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | 553/RD/PHE | 12/02/2025 | 90 | SANYAL ENTERPRISE | 0.88 | 0 | 0 | 0
1056 | UTTAR DINAJPUR | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block , SM/12086 | New | Construction of concrete pathway with earth filling at Head Work Site Pump House & 2nd TW Site Pump House for Kundargaon Piped Water Supply Scheme under Islampur Sub-Division PHED under Raiganj Division, PHED., U/D. (2nd Call) | 2042/RD/PHE | 09/07/2025 | 90 | M/S RATAN SARKAR & SON | 5.4 | 0 | 0 | 0
1057 | UTTAR DINAJPUR | Raiganj Division | KUNDARGAON Piped Water Supply Scheme at Islampur Block , SM/12086 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
1058 | UTTAR DINAJPUR | Raiganj Division | UTTAR GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12794 | New | Material Requisition To Resource Division | 1328/RD/PHE | 15/05/2023 | 0 | Resource Division | 50.25 | 0 | 0 | 0
1059 | UTTAR DINAJPUR | Malda Mechanical | UTTAR GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12794 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Uttar Gorasahid Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014632) | 2539/MLMD | 04/08/2023 | 840 | SUBRATA SAHA | 26.44 | 0 | 0 | 72
1060 | UTTAR DINAJPUR | Malda Mechanical | UTTAR GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12794 | New | Quotation for new service connection at UTTAR GORASAHID PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12794) | BP-2024-25-275 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 3.93 | 0 | 0 | 0
1061 | UTTAR DINAJPUR | Raiganj Division | UTTAR GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12794 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
1062 | UTTAR DINAJPUR | Raiganj Division | UTTAR GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12794 | New | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at UTTAR GORASAHID PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | 1208/RD/PHE | 25/04/2025 | 45 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 40.28 | 0 | 0 | 0
1063 | UTTAR DINAJPUR | Raiganj Division | UTTAR GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12794 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Uttar Gorasahid Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | 1802/RD/PHE | 24/06/2025 | 180 | FIZA CONSTRUCTION | 29.57 | 0 | 0 | 0
1064 | UTTAR DINAJPUR | Raiganj Division | GHIMIGAON Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12783 | New | Material Requisition To Resource Division | 969/RD/PHE | 29/03/2023 | 0 | Resource Division | 16.16 | 0 | 0 | 0
1065 | UTTAR DINAJPUR | Malda Mechanical | GHIMIGAON Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12783 | New | Quotation for new service connection at GHIRNIGAON PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-126 | 25/04/2024 | 0 | W.B.S.E.D.C.LTD | 6.93 | 0 | 0 | 0
1066 | UTTAR DINAJPUR | Malda Mechanical | GHIMIGAON Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12783 | New | Quotation for new service connection at GHIRNIGAON PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-127 | 25/04/2024 | 0 | W.B.S.E.D.C.LTD | 7.94 | 0 | 0 | 0
1067 | UTTAR DINAJPUR | Malda Mechanical | GHIMIGAON Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12783 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Ghirnigaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014815) | 2502/MLMD | 04/08/2023 | 907 | M/S TRILOCHAN CONSTRUCTION CO. | 25.36 | 0 | 0 | 77
1068 | UTTAR DINAJPUR | Raiganj Division | GHIMIGAON Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12783 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
1069 | UTTAR DINAJPUR | Raiganj Division | GHIMIGAON Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12783 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Ghirnigaon Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 20 M3/hr. | 1824/RD/PHE | 25/06/2025 | 180 | FARQUE AZAM | 15.37 | 0 | 0 | 0
1070 | UTTAR DINAJPUR | Malda Mechanical | GOALIN Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12784 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Goalin Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014474) | 2501/MLMD | 04/08/2023 | 120 | A.G ENTERPRISE. | 29.41 | 0 | 0 | 0
1071 | UTTAR DINAJPUR | Raiganj Division | GOALIN Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12784 | New | Material Requisition To Resource Division | 1125/RD/PHE | 24/04/2023 | 0 | Resource Division | 43.9 | 0 | 0 | 0
1072 | UTTAR DINAJPUR | Raiganj Division | GOALIN Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12784 | New | Providing FHTC in connection with Goalin Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd Call) | 2181/RD/PHE | 29/07/2025 | 90 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 6.17 | 0 | 0 | 0
1073 | UTTAR DINAJPUR | Raiganj Division | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. , SM/12707 | New | Material Requisition To Resource Division | 1118/RD/PHE | 24/04/2023 | 0 | Resource Division | 29.16 | 0 | 0 | 0
1074 | UTTAR DINAJPUR | Malda Mechanical | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. , SM/12707 | New | Quotation for new service connection at Angarbhasa PH-I (Goalpokher ccc). | BP-2023-24-544 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 9.41 | 0 | 0 | 0
1075 | UTTAR DINAJPUR | Malda Mechanical | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. , SM/12707 | New | Additional Quotation for new service connection at ANGARBHASA PH-I (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12707) | BP-2024-25-216 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 0.72 | 0 | 0 | 0
1076 | UTTAR DINAJPUR | Malda Mechanical | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. , SM/12707 | New | Quotation for new service connection at ANGARBHASA PH-II (Goalpokher ccc) in the district of Uttar Dinajpur. | BP-2023-24-617 | 04/03/2024 | 0 | W.B.S.E.D.C.LTD | 22.5 | 0 | 0 | 0
1077 | UTTAR DINAJPUR | Raiganj Division | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. , SM/12707 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | 1816/RD/PHE | 26/06/2024 | 198 | MD ZAFAR EQUEBAL | 2.6 | 0 | 0 | 100
1078 | UTTAR DINAJPUR | Raiganj Division | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. , SM/12707 | New | Laying of additional pipeline for improving FHTC at different mouzas at ANGARBHASA PWSS of Goalpokhar-I Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | 2048/RD/PHE | 10/07/2025 | 180 | ROY ENGINEERS. (PATNA) | 29.06 | 0 | 0 | 0
1079 | UTTAR DINAJPUR | Raiganj Division | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. , SM/12707 | New | Providing FHTC in connection with Angurbhasa Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd Call) | 2182/RD/PHE | 29/07/2025 | 90 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 5.79 | 0 | 0 | 0
1080 | UTTAR DINAJPUR | Raiganj Division | ANGARBHASA Piped Water Supply Scheme at Goalpokhar-l Block under Uttar Dinajpur District. , SM/12707 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Angarbhasa Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 50 M3/hr. | 1923/RD/PHE | 30/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 20.74 | 0 | 0 | 0
1081 | UTTAR DINAJPUR | Raiganj Division | BELAN Piped Water Supply Scheme , SM/13233 | New | Material Requisition To Resource Division | 981/RD/PHE | 30/03/2023 | 0 | Resource Division | 50.16 | 0 | 0 | 0
1082 | UTTAR DINAJPUR | Malda Mechanical | BELAN Piped Water Supply Scheme , SM/13233 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Belan Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015468) | 2463/MLMD | 04/08/2023 | 1027 | JAL PRAVAHIKA PVT. LTD. | 28.11 | 0 | 0 | 0
1083 | UTTAR DINAJPUR | Raiganj Division | BELAN Piped Water Supply Scheme , SM/13233 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
1084 | UTTAR DINAJPUR | Raiganj Division | FASHIA DIATION PIPED WATER SUPPLY SCHEME , SM/14129 | New | Material Requisition To Resource Division | 979/RD/PHE | 30/03/2023 | 0 | Resource Division | 38.57 | 0 | 0 | 0
1085 | UTTAR DINAJPUR | Malda Mechanical | FASHIA DIATION PIPED WATER SUPPLY SCHEME , SM/14129 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Fashia Diation Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016516) | 2441/MLMD | 04/08/2023 | 937 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD.. | 27.22 | 0 | 0 | 53
1086 | UTTAR DINAJPUR | Raiganj Division | FASHIA DIATION PIPED WATER SUPPLY SCHEME , SM/14129 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
1087 | UTTAR DINAJPUR | Raiganj Division | KOKRA Piped Water Supply Scheme , SM/14175 | New | Material Requisition To Resource Division | 863/RD/PHE | 25/03/2023 | 0 | Resource Division | 33.6 | 0 | 0 | 0
1088 | UTTAR DINAJPUR | Raiganj Division | KOKRA Piped Water Supply Scheme , SM/14175 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Kokra, 2.Bishahar, 3. Dhoabishua in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 539/RD/PHE | 22/02/2023 | 630 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 0 | 65
1089 | UTTAR DINAJPUR | Malda Mechanical | KOKRA Piped Water Supply Scheme , SM/14175 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Kokra, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-567 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 0.54 | 0 | 0 | 0
1090 | UTTAR DINAJPUR | Malda Mechanical | KOKRA Piped Water Supply Scheme , SM/14175 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Kokra, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-568 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 0.65 | 0 | 0 | 0
1091 | UTTAR DINAJPUR | Raiganj Division | KOKRA Piped Water Supply Scheme , SM/14175 | New | Implementation of KOKRA and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 557/RD/PHE | 23/02/2023 | 1159 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 264.99 | 0 | 0 | 5
1092 | UTTAR DINAJPUR | Malda Mechanical | KOKRA Piped Water Supply Scheme , SM/14175 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Kokra Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018226) | 2513/MLMD | 04/08/2023 | 935 | PABITRA MANDAL | 25.41 | 0 | 0 | 89
1093 | UTTAR DINAJPUR | Raiganj Division | KOKRA Piped Water Supply Scheme , SM/14175 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Kokra PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3758/RD/PHED | 18/12/2024 | 90 | MAA TARA CONSTRUCTION (SEVOKPALLY) RGJMAATARA@GMAIL.COM | 24.91 | 0 | 0 | 0
1094 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Tungail Bilpara Water Supply Scheme under Kaliyaganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10465 | Retrofitting | Restoration of Pipe Line for Providing FHTC for Tungail Bilpara Water Supply Scheme under Kaliyaganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur.(Phase - II) | 1032/RD/PHED | 12/05/2022 | 30 | SARNALI ENTERPRISE | 5.79 | 0 | 0 | 1
1095 | UTTAR DINAJPUR | Malda Mechanical | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14163 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite at T/W no. I of Bhattagidighi Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018205) | 2734/MLMD | 14/08/2023 | 180 | SHREE BISHNU CONSTRUCTION | 26.91 | 0 | 0 | 0
1096 | UTTAR DINAJPUR | Raiganj Division | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14163 | New | Material Requisition To Resource Division | 578/RD/PHE | 24/02/2023 | 0 | Resource Division | 47.07 | 0 | 0 | 0
1097 | UTTAR DINAJPUR | Raiganj Division | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14163 | New | Implementation of BHATTAGIDIGHI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 559/RD/PHE | 23/02/2023 | 1043 | M/S LOKENATH CONSTRUCTION | 618.78 | 0 | 0 | 45
1098 | UTTAR DINAJPUR | Malda Mechanical | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14163 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Bhattagidighi, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-572 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 5.69 | 0 | 0 | 0
1099 | UTTAR DINAJPUR | Malda Mechanical | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14163 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Bhattagidighi, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-622 | 04/03/2024 | 0 | W.B.S.E.D.C.LTD | 10.22 | 0 | 0 | 0
1100 | UTTAR DINAJPUR | Raiganj Division | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14163 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Dakshin Goalpara, 2. Bhattagidighi, 3. Maharajpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 540/RD/PHE | 22/02/2023 | 630 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 0 | 80
1101 | UTTAR DINAJPUR | Raiganj Division | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14163 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
1102 | UTTAR DINAJPUR | Raiganj Division | BHATTAGIDIGHI PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14163 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site , Tube well and Pump Houseroad restoration of Bhattadighi PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 02/RD/PHE | 02/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 69.15 | 0 | 0 | 0
1103 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME , SM/15125 | Augmentation | Material Requisition To Resource Division | 722/RD/PHE | 15/03/2023 | 0 | Resource Division | 26.68 | 0 | 0 | 0
1104 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME , SM/15125 | Augmentation | Supply, installation & commissioning of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Augmentation of Khanta Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011435) | 2509/MLMD | 04/08/2023 | 120 | SHREE BISHNU CONSTRUCTION | 24.68 | 0 | 0 | 82
1105 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME , SM/15125 | Augmentation | Construction of concrete pathway ,Land development and other ancillary works for Augmentation Of KHANTA RASAKHOWA Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHED.under Raiganj Division,PHE Dte U/D. | 3775/RD/PHE | 19/12/2024 | 45 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 26.93 | 0 | 0 | 0
1106 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME , SM/15125 | Augmentation | Construction of Pump House (size 5.40m x 4.10m outer to outer) with sanitary and water supply arrangement according to departmental drawing with toilet at Head Work Site of Augmentation Of KHANTA-RASAKHOWA Piped Water Supply Schemes under Raiganj Division, PHE Dte. | 2361/RD/PHE | 11/08/2023 | 60 | BISWA PROKASH JHA | 5.75 | 0 | 0 | 100
1107 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME , SM/15125 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Khanta PWSS , Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-397 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 7.39 | 0 | 0 | 0
1108 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME , SM/15125 | Augmentation | Additional Quotation for new service connection at KHANTA PH-III (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15125) | BP-2024-25-483 | 09/09/2024 | 0 | W.B.S.E.D.C.LTD | 6.87 | 0 | 0 | 0
1109 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME , SM/15125 | Augmentation | Augmentation of KHANTA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 570/RD/PHE | 23/02/2023 | 768 | PRASANTA DUTTA | 363.57 | 0 | 0 | 65
1110 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME , SM/15125 | Augmentation | Construction of Boundary Wall with Gate at Head Work Site & repair, renovation of boundary wall of 2nd Tube-Well Site under Augmentation of Khanta (Rasakhowa) PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 1542/RD/PHE | 11/06/2025 | 90 | CHAPDUAR LABOUR CO- OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 12.61 | 0 | 0 | 0
1111 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME , SM/15125 | Augmentation | Construction of Boundary Wall with Gate at Head Work Site & repair, renovation of boundary wall of 2nd Tube-Well Site under Augmentation of Khanta (Rasakhowa) PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 1437/RD/PHE | 30/05/2025 | 90 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 12.61 | 0 | 0 | 0
1112 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME , SM/15125 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Khanta-Rasakhowa Water Supply Scheme(Augmentation) at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity-70 M3/hr. | 2497/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 30.93 | 0 | 0 | 0
1113 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KHANTA PIPED WATER SUPPLY SCHEME , SM/15125 | Augmentation | Repairing for 2nd Pump House & Construction of Toilet at Kahanta (Rasakhowa) in connection with Augmentation of Khanta PWSS under Islampur Sub-Division under Raiganj Division, PHE Dte. | 2051/RD/PHE | 19/07/2023 | 496 | M/S DAS ENTERPRISE SUMAN974967@GMAIL.COM | 3.12 | 0 | 0 | 100
1114 | UTTAR DINAJPUR | Raiganj Division | SARJAPUR Piped Water Supply Scheme , SM/15127 | New | Material Requisition To Resource Division | 886/RD/PHE | 27/03/2023 | 0 | Resource Division | 47.4 | 0 | 0 | 0
1115 | UTTAR DINAJPUR | Malda Mechanical | SARJAPUR Piped Water Supply Scheme , SM/15127 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Sarjapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015948) | 2535/MLMD | 04/08/2023 | 817 | MANIK CHANDRA SAHA. | 28.33 | 0 | 0 | 74
1116 | UTTAR DINAJPUR | Raiganj Division | SARJAPUR Piped Water Supply Scheme , SM/15127 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
1117 | UTTAR DINAJPUR | Raiganj Division | RANIGANJ Piped Water Supply Scheme , SM/14181 | New | Material Requisition To Resource Division | 887/RD/PHE | 27/03/2023 | 0 | Resource Division | 73.71 | 0 | 0 | 0
1118 | UTTAR DINAJPUR | Raiganj Division | RANIGANJ Piped Water Supply Scheme , SM/14181 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Raniganj, 2. Alianagar in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 542/RD/PHE | 22/02/2023 | 628 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 51.42 | 0 | 0 | 80
1119 | UTTAR DINAJPUR | Malda Mechanical | RANIGANJ Piped Water Supply Scheme , SM/14181 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I, II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Raniganj Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017338) | 2529/MLMD | 04/08/2023 | 907 | HANNAN BUILDERS PVT. LTD. | 36.8 | 0 | 0 | 79
1120 | UTTAR DINAJPUR | Raiganj Division | RANIGANJ Piped Water Supply Scheme , SM/14181 | New | Implementation of RANIGANJ and its adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2475/RD/PHE | 24/08/2023 | 862 | UJJWAL DAS | 509.3 | 0 | 0 | 80
1121 | UTTAR DINAJPUR | Malda Mechanical | RANIGANJ Piped Water Supply Scheme , SM/14181 | New | Quotation for new service connection at RANIGANJ PH-I (Dalkhola ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-82 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.31 | 0 | 0 | 0
1122 | UTTAR DINAJPUR | Malda Mechanical | RANIGANJ Piped Water Supply Scheme , SM/14181 | New | Quotation for new service connection at RANIGANJ PH-II (Dalkhola ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-81 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 8.25 | 0 | 0 | 0
1123 | UTTAR DINAJPUR | Malda Mechanical | RANIGANJ Piped Water Supply Scheme , SM/14181 | New | Quotation for new service connection at RANIGANJ PH-III (Dalkhola ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-80 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 7.5 | 0 | 0 | 0
1124 | UTTAR DINAJPUR | Raiganj Division | RANIGANJ Piped Water Supply Scheme , SM/14181 | New | Construction of concrete pathway ,Land development and other ancillary works for RANIGANJ Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | 45/RD/PHE | 03/01/2025 | 225 | GULJAN BEGAM | 22.31 | 0 | 0 | 60
1125 | UTTAR DINAJPUR | Malda Mechanical | MAHARAJPUR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15214 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Maharajpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018311) | 2761/MLMD | 14/08/2023 | 180 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 26.71 | 0 | 0 | 0
1126 | UTTAR DINAJPUR | Raiganj Division | MAHARAJPUR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15214 | New | Material Requisition To Resource Division | 864/RD/PHE | 25/03/2023 | 0 | Resource Division | 46.67 | 0 | 0 | 0
1127 | UTTAR DINAJPUR | Raiganj Division | MAHARAJPUR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15214 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Maharajpur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3757/RD/PHED | 18/12/2024 | 45 | UTTAM SAHA | 22.87 | 0 | 0 | 0
1128 | UTTAR DINAJPUR | Raiganj Division | MAHARAJPUR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15214 | New | Implementation of MAHARAJPUR and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 560/RD/PHE | 23/02/2023 | 1042 | UTTAM SAHA | 600.95 | 0 | 0 | 40
1129 | UTTAR DINAJPUR | Raiganj Division | MAHARAJPUR PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15214 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Dakshin Goalpara, 2. Bhattagidighi, 3. Maharajpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 540/RD/PHE | 22/02/2023 | 630 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 0 | 80
1130 | UTTAR DINAJPUR | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16493 | New | Material Requisition To Resource Division | 962/RD/PHE | 29/03/2023 | 0 | Resource Division | 31.81 | 0 | 0 | 0
1131 | UTTAR DINAJPUR | Malda Mechanical | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16493 | New | Quotation for new service connection at Samaspur TW-I. | BP-2023-24-545 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 18.97 | 0 | 0 | 0
1132 | UTTAR DINAJPUR | Malda Mechanical | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16493 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Samaspur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016128) | 2451/MLMD | 04/08/2023 | 797 | ANIMA ENTERPRISE | 28.12 | 0 | 0 | 100
1133 | UTTAR DINAJPUR | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16493 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
1134 | UTTAR DINAJPUR | Raiganj Division | SAMASPUR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16493 | New | Trial Run For Samaspur PWSS under Goalpukhur-II Block under Raiganj Division ,PHE Dte. for 3 months | 554/RD/PHE | 12/02/2025 | 90 | SANDIP SARKAR | 0.87 | 0 | 0 | 0
1135 | UTTAR DINAJPUR | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/15147 | New | Construction of Reinforcement Concrete Pathway at Headwork Site for Bhulki PWSS of Islampur Sub-Division under Raiganj Division, PHE Dte.(NEW Scheme) | 2654/RD/PHE | 15/09/2023 | 30 | R. R. CONSTRUCTION | 9.98 | 0 | 0 | 0
1136 | UTTAR DINAJPUR | Malda Mechanical | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/15147 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BHULKI, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003194764 | 19/09/2023 | 90 | W.B.S.E.D.C.LTD | 5.92 | 0 | 0 | 100
1137 | UTTAR DINAJPUR | Malda Mechanical | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/15147 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of BHULKI, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003209110 | 21/09/2023 | 90 | W.B.S.E.D.C.LTD | 3.54 | 0 | 0 | 100
1138 | UTTAR DINAJPUR | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/15147 | New | Material Requisition To Resource Division | 634/RD/PHE | 02/03/2023 | 0 | Resource Division | 58.74 | 0 | 0 | 0
1139 | UTTAR DINAJPUR | Malda Mechanical | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/15147 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Bhulki Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018418) | 2112/MLMD | 05/07/2023 | 180 | SHREE BISHNU CONSTRUCTION | 26.9 | 0 | 0 | 90
1140 | UTTAR DINAJPUR | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/15147 | New | Laying of Additional pipeline with other ancillary works at different mouzas of BHULKI PWSS under Islampur Sub-Division P.H.E. Dte. | 3494/RD/PHE | 02/12/2024 | 45 | S.B.CONSTRUCTION | 34.78 | 0 | 0 | 0
1141 | UTTAR DINAJPUR | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/15147 | New | Laying additional pipe line with FHTC for New Scheme Of Bhulki Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | 3785/RD/PHE | 19/12/2024 | 45 | S M CONSTRUCTION RAJ.GSHOSH325@GMAIL.COM | 34.76 | 0 | 0 | 0
1142 | UTTAR DINAJPUR | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/15147 | New | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | BP-2024-25-24 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 9.3 | 0 | 0 | 0
1143 | UTTAR DINAJPUR | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/15147 | New | Implementation of BHULKI and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd Tube Well) | 747/RD/PHE | 16/03/2023 | 1090 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 463.74 | 0 | 0 | 20
1144 | UTTAR DINAJPUR | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/15147 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BHULKI PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 647/RD/PHE | 05/03/2024 | 149 | SANDIP SARKAR | 22.58 | 0 | 0 | 0
1145 | UTTAR DINAJPUR | Raiganj Division | BHULKI Piped Water Supply Scheme at Karandighi Block under Uttar Dinajpur District. , SM/15147 | New | Construction of concrete pathway at 2nd TW Site Pump House for BHULKI Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | 3485/RD/PHE | 02/12/2024 | 15 | BHAGYA LAXMI ENTERPRISE | 4.28 | 0 | 0 | 0
1146 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Khesra for installation of FHTC. , SM/09160 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of KHESRA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2116/RD/PHE | 03/11/2021 | 30 | KARTICK BISWAS | 15.94 | 0 | 0 | 1
1147 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Khesra for installation of FHTC. , SM/09160 | Retrofitting | office accessories | BP-2022-23-34 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
1148 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Khesra for installation of FHTC. , SM/09160 | Retrofitting | office accessories bill | BP-2022-23-35 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.07 | 0 | 0 | 0
1149 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Khesra for installation of FHTC. , SM/09160 | Retrofitting | office accessories bill | BP-2022-23-33 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
1150 | UTTAR DINAJPUR | Raiganj Division | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. , SM/15516 | New | Material Requisition To Resource Division | 846/RD/PHE | 24/03/2023 | 0 | Resource Division | 64.22 | 0 | 0 | 0
1151 | UTTAR DINAJPUR | Malda Mechanical | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. , SM/15516 | New | Quotation for new service connection at MAJRA PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-123 | 24/04/2024 | 0 | W.B.S.E.D.C.LTD | 17.66 | 0 | 0 | 0
1152 | UTTAR DINAJPUR | Malda Mechanical | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. , SM/15516 | New | Quotation for new service connection at MAJRA PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-41 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 15.98 | 0 | 0 | 0
1153 | UTTAR DINAJPUR | Malda Mechanical | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. , SM/15516 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Majra Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015895) | 2517/MLMD | 04/08/2023 | 120 | GHOSH BROTHERS... | 39.77 | 0 | 0 | 83
1154 | UTTAR DINAJPUR | Raiganj Division | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. , SM/15516 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
1155 | UTTAR DINAJPUR | Raiganj Division | MAJRA Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. , SM/15516 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
1156 | UTTAR DINAJPUR | Raiganj Division | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15211 | New | Material Requisition To Resource Division | 1320/RD/PHE | 12/05/2023 | 0 | Resource Division | 35.97 | 0 | 0 | 0
1157 | UTTAR DINAJPUR | Raiganj Division | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15211 | New | Construction of concrete pathway with earth Filling at Head Work Site Pump House & 2nd TW Site Pump House for Shiripur Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division, PHE Dte., U/D. | 3310/RD/PHE | 20/11/2024 | 30 | NIRMAN ENTERPRISE | 10.84 | 0 | 0 | 0
1158 | UTTAR DINAJPUR | Raiganj Division | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15211 | New | Additional pipeline and other ancillary works at Shiripur piped water Supply Scheme Under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | 3309/RD/PHE | 20/11/2024 | 30 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 12.42 | 0 | 0 | 0
1159 | UTTAR DINAJPUR | Malda Mechanical | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15211 | New | Quotation for new service connection at SHRIPUR PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15211) | BP-2024-25-482 | 09/09/2024 | 0 | W.B.S.E.D.C.LTD | 3.73 | 0 | 0 | 0
1160 | UTTAR DINAJPUR | Malda Mechanical | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15211 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Shripur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018397) | 2768/MLMD | 14/08/2023 | 837 | M/S TRILOCHAN CONSTRUCTION CO. | 27.01 | 0 | 0 | 77
1161 | UTTAR DINAJPUR | Raiganj Division | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15211 | New | Implementation of SHRIPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Tube-Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work & 2nd TubeWell) | 2629/RD/PHE | 13/09/2023 | 1091 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 403.31 | 0 | 0 | 45
1162 | UTTAR DINAJPUR | Raiganj Division | SHRIPUR PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15211 | New | Construction of Boundary Wall with Gate at Head Work Site& 2nd Tube-Well Site under Shripur PWSS at Karandighi Block under Raiganj Division, P.H.E Dte. | 1541/RD/PHE | 11/06/2025 | 90 | BISWA PROKASH JHA | 24.48 | 0 | 0 | 0
1163 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN MAKHANPOKHAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16495 | New | Material Requisition To Resource Division | 898/RD/PHE | 28/03/2023 | 0 | Resource Division | 21.54 | 0 | 0 | 0
1164 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN MAKHANPOKHAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16495 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dakshin Makhanpokher Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016150) | 2439/MLMD | 04/08/2023 | 960 | MERCURY ENGINEERING COMPANY. | 25.69 | 0 | 0 | 72
1165 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN MAKHANPOKHAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16495 | New | Quotation for new service connection at Dakshin Makhanpokhar PH-II (Kanki ccc) in the district of Uttar Dinajpur. | BP-2023-24-654 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.26 | 0 | 0 | 0
1166 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN MAKHANPOKHAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16495 | New | Quotation for new service connection at Dakshin Makhanpokhar PH-I (Kanki ccc) in the district of Uttar Dinajpur. | BP-2023-24-653 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 12.97 | 0 | 0 | 0
1167 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN MAKHANPOKHAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16495 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
1168 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN MAKHANPOKHAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16495 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakhshin Makhanpukur Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 50 M3/hr. | 2016/RD/PHE | 08/07/2025 | 180 | S. DUTTA | 20.74 | 0 | 0 | 0
1169 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16224 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
1170 | UTTAR DINAJPUR | Malda Mechanical | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16224 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Surangapur (Zone-I) PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003278961 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 3.51 | 0 | 0 | 100
1171 | UTTAR DINAJPUR | Malda Mechanical | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16224 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Surangapur (Zone-I) PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003279009 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 3.39 | 0 | 0 | 100
1172 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16224 | New | Material Requisition To Resource Division | 1681/RD/PHE | 19/06/2023 | 0 | Resource Division | 29.81 | 0 | 0 | 0
1173 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16224 | New | Hiring of Inspection Vehicle for office of the Assistant engineer, Raiganj Sub-Division, P.H.E. Dte. for the period from 16.02.2023 to 15.03.2023. |  | 05/12/2023 | 0 | DEBASISH GHOSH | 0.32 | 0 | 0 | 0
1174 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16224 | New |  | BP-2023-24-212 | 07/12/2023 | 0 | DEBASISH GHOSH | 0.32 | 0 | 0 | 0
1175 | UTTAR DINAJPUR | Malda Mechanical | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16224 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Surangapur Zone- I Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018409) | 2772/MLMD | 14/08/2023 | 506 | THE BANERJEE CONCERN | 24.02 | 0 | 0 | 88
1176 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16224 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SURANGAPUR ZONE-I PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 640/RD/PHE | 05/03/2024 | 180 | UTPAL SAHA | 12.24 | 0 | 0 | 90
1177 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16224 | New | Implementation of SURANGAPUR (ZONE-I) and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 806/RD/PHE | 21/03/2023 | 890 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 363.11 | 0 | 0 | 60
1178 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16224 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Suragapur zone I PWSS at Itahar Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 04/RD/PHE | 02/01/2025 | 45 | M/S MAA TARA CONSTRUCTION | 51.54 | 0 | 0 | 0
1179 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16224 | New | Trial Run For Surangapur Zone-I PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 months | 532/RD/PHE | 12/02/2025 | 90 | M/S MAA TARA CONSTRUCTION | 0.88 | 0 | 0 | 0
1180 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16224 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SURANGAPUR ZONE-I PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 641/RD/PHE | 05/03/2024 | 45 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 12.24 | 0 | 0 | 80
1181 | UTTAR DINAJPUR | Raiganj Division | RAYNAGAR PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18161 | New | Material Requisition To Resource Division | 2258/RD/PHE | 03/08/2023 | 0 | Resource Division | 3.89 | 0 | 0 | 0
1182 | UTTAR DINAJPUR | Malda Mechanical | RAYNAGAR PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18161 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Raynagar, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-187 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 4.55 | 0 | 0 | 0
1183 | UTTAR DINAJPUR | Raiganj Division | RAYNAGAR PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18161 | New | Implementation of RAYNAGAR and it's adjoining mouzas Pipe Water Supply Scheme at KALIAGANJ Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | 1560/RD/PHE | 29/05/2023 | 701 | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 53.01 | 0 | 0 | 70
1184 | UTTAR DINAJPUR | Raiganj Division | RAYNAGAR PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18161 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Raynagar Water Supply Scheme at Kaliaganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 10 M3/hr. | 2493/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 13.82 | 0 | 0 | 0
1185 | UTTAR DINAJPUR | Malda Mechanical | RAYNAGAR PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18161 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Raynagar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020854) | 2699/MLMD | 11/08/2023 | 660 | M/S. MAYUKH BHADURI | 7.17 | 0 | 0 | 100
1186 | UTTAR DINAJPUR | Raiganj Division | BIRSINGGACHH MINI PIPED WATER SUPPLY SCHEME IN ISLAMPUR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18166 | New | Material Requisition To Resource Division | 2298/RD/PHE | 04/08/2023 | 0 | Resource Division | 2.18 | 0 | 0 | 0
1187 | UTTAR DINAJPUR | Raiganj Division | BIRSINGGACHH MINI PIPED WATER SUPPLY SCHEME IN ISLAMPUR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18166 | New | Implementation of BIRSINGGACHH Mini Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | 2379/RD/PHE | 14/08/2023 | 896 | MOTI INDUSTRIES | 66.92 | 0 | 0 | 80
1188 | UTTAR DINAJPUR | Raiganj Division | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17256 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
1189 | UTTAR DINAJPUR | Raiganj Division | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17256 | New | Material Requisition To Resource Division | 2236/RD/PHE | 02/08/2023 | 0 | Resource Division | 6.43 | 0 | 0 | 0
1190 | UTTAR DINAJPUR | Raiganj Division | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17256 | New | Implementation of Balufara Zone-I and it's adjoining mouzas Pipe Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House Head Work.) | 954/RD/PHE | 29/03/2023 | 703 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 88.07 | 0 | 0 | 50
1191 | UTTAR DINAJPUR | Raiganj Division | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17256 | New | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under BALUFARA ZONE-I PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 619/RD/PHE | 05/03/2024 | 45 | M/S PRATIMA CHOUDHURY | 5.57 | 0 | 0 | 0
1192 | UTTAR DINAJPUR | Raiganj Division | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17256 | New | Requisition of fund regarding payment for permanent restoration of rural roads damaged due to laying of pipeline by PHE Dte. as on 24.09.2024 i.c.w Balufara to Agapur (Package No. WB15198), under coverage of Balufara Zone I PWSS (SM/17256) | BP-2024-25-277 | 08/10/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 1.41 | 0 | 0 | 0
1193 | UTTAR DINAJPUR | Malda Mechanical | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17256 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Balufara (Zone-I), Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-631 | 06/03/2024 | 0 | W.B.S.E.D.C.LTD | 0.12 | 0 | 0 | 0
1194 | UTTAR DINAJPUR | Raiganj Division | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17256 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Balufara Zone-1 PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 20/RD/PHE | 02/01/2025 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 10.09 | 0 | 0 | 0
1195 | UTTAR DINAJPUR | Raiganj Division | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17256 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bahala zone -I PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 23/RD/PHE | 02/01/2025 | 105 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 44.47 | 0 | 0 | 0
1196 | UTTAR DINAJPUR | Malda Mechanical | Balufara Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17256 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Balufara (Zone-I) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020259) | 2731/MLMD | 14/08/2023 | 646 | CHATTERJEE CONSTRUCTION | 7.18 | 0 | 0 | 100
1197 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. , SM/17742 | Augmentation | Preparation of DPR for drinking water supply scheme to facilitate 4(Four)Nos. Augmentation Scheme and 1(One) No. New PWSS (List Enclosed) Uncovered mouzas under Uttar Dinajpur District which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Raiganj Division P.H.E. Dte. | 2226/RD/PHE | 31/07/2023 | 15 | RADIANT | 11.57 | 0 | 0 | 100
1198 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. , SM/17742 | Augmentation | Material Requisition To Resource Division | 1104/RD/PHE | 20/04/2023 | 0 | Resource Division | 4.6 | 0 | 0 | 0
1199 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. , SM/17742 | Augmentation | Augmentation of Sergram and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House) | 883/RD/PHE | 27/03/2023 | 720 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 88.22 | 0 | 0 | 45
1200 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. , SM/17742 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Shergram, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-630 | 06/03/2024 | 0 | W.B.S.E.D.C.LTD | 0.12 | 0 | 0 | 0
1201 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. , SM/17742 | Augmentation | Additional quotation for energization at TW No-III of Shergram water supply scheme in the district of Uttar Dinajpur. | BP-2024-25-359 | 04/07/2024 | 0 | W.B.S.E.D.C.LTD | 3.84 | 0 | 0 | 0
1202 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Sergram Piped Water Supply Scheme at Kaliyaganj block under Uttar Dinajpur District. , SM/17742 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Augmentation of Shergram Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018651) | 2724/MLMD | 14/08/2023 | 180 | JOY MAA SANTOSHI ENTERPRISE. | 7.18 | 0 | 0 | 100
1203 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Bamair Water Supply Scheme under Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10493 | Retrofitting | Restoration of Pipe Line for Providing FHTC for Bamir Water Supply Scheme under Itahar Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur.(Phase - II) | 1009/RD/PHED | 11/05/2022 | 20 | RURAL DEVELOPMENT CO-OP. LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 3.51 | 0 | 0 | 1
1204 | UTTAR DINAJPUR | Raiganj Division | BUDHRA PWSS , SM/19012 | New | Material Requisition To Resource Division | 638/RD/PHE | 02/03/2023 | 0 | Resource Division | 43.1 | 0 | 0 | 0
1205 | UTTAR DINAJPUR | Malda Mechanical | BUDHRA PWSS , SM/19012 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Budhra Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018370) | 4770/MLMD | 29/12/2023 | 910 | M/S. KUNDU CONSTRACTION | 24.27 | 0 | 0 | 69
1206 | UTTAR DINAJPUR | Raiganj Division | BUDHRA PWSS , SM/19012 | New | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 4(Four) Month (01/03/2024 to 30/06/2024). | 472/RD/PHE | 28/02/2024 | 121 | PRITAM SARKAR | 1.6 | 0 | 0 | 0
1207 | UTTAR DINAJPUR | Malda Mechanical | BUDHRA PWSS , SM/19012 | New | Quotation for new service connection at BUDHRA PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/19012). | BP-2024-25-256 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 7.42 | 0 | 0 | 0
1208 | UTTAR DINAJPUR | Malda Mechanical | BUDHRA PWSS , SM/19012 | New | Quotation for new service connection at BUDHRA PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/19012). | BP-2024-25-255 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 5.69 | 0 | 0 | 0
1209 | UTTAR DINAJPUR | Raiganj Division | BUDHRA PWSS , SM/19012 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BUDHRA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 644/RD/PHE | 05/03/2024 | 45 | JEET CONSTRUCTION UKILPARA | 11.29 | 0 | 0 | 0
1210 | UTTAR DINAJPUR | Raiganj Division | BUDHRA PWSS , SM/19012 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BUDHRA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 645/RD/PHE | 05/03/2024 | 45 | BITTU ENTERPRISE | 11.29 | 0 | 0 | 10
1211 | UTTAR DINAJPUR | Malda Mechanical | BUDHRA PWSS , SM/19012 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 3420/MLMD | 28/10/2024 | 61 | NITAI PANDEY | 0.78 | 0 | 0 | 0
1212 | UTTAR DINAJPUR | Raiganj Division | BUDHRA PWSS , SM/19012 | New | Implementation of BUDHRA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd Tube Well) | 2888/RD/PHE | 30/10/2023 | 488 | M/S ALISA CONSTRUCTION | 352.41 | 0 | 0 | 35
1213 | UTTAR DINAJPUR | Raiganj Division | BUDHRA PWSS , SM/19012 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Budhra PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3767/RD/PHED | 18/12/2024 | 165 | UTTAM SAHA | 33.94 | 0 | 0 | 60
1214 | UTTAR DINAJPUR | Raiganj Division | BUDHRA PWSS , SM/19012 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Budhra Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 50 M3/hr. | 2486/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 20.74 | 0 | 0 | 0
1215 | UTTAR DINAJPUR | Raiganj Division | SADIPUR PWSS , SM/18994 | New | Material Requisition To Resource Division | 640/RD/PHE | 02/03/2023 | 0 | Resource Division | 46.68 | 0 | 0 | 0
1216 | UTTAR DINAJPUR | Malda Mechanical | SADIPUR PWSS , SM/18994 | New | Quotation for new service connection at SADIPUR PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-120 | 24/04/2024 | 0 | W.B.S.E.D.C.LTD | 5.42 | 0 | 0 | 0
1217 | UTTAR DINAJPUR | Malda Mechanical | SADIPUR PWSS , SM/18994 | New | Quotation for new service connection at SADIPUR PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-121 | 24/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.68 | 0 | 0 | 0
1218 | UTTAR DINAJPUR | Raiganj Division | SADIPUR PWSS , SM/18994 | New | Implementation of SADIPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2869/RD/PHE | 17/10/2023 | 990 | UTTAM SAHA | 645.28 | 0 | 0 | 57
1219 | UTTAR DINAJPUR | Malda Mechanical | SADIPUR PWSS , SM/18994 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Sadipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018395) | 3342/MLMD | 30/10/2023 | 790 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 25.43 | 0 | 0 | 42
1220 | UTTAR DINAJPUR | Raiganj Division | SADIPUR PWSS , SM/18994 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Sadipur PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3764/RD/PHED | 18/12/2024 | 45 | M/S REGAL BUILDERS | 94.78 | 0 | 0 | 0
1221 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. , SM/12393 | Augmentation | Material Requisition To Resource Division | 2171/RD/PHE | 09/12/2022 | 0 | Resource Division | 34.71 | 0 | 0 | 0
1222 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. , SM/12393 | Augmentation | Augmentation of DHARAMPUR Zone-I and it's adjoining mouzas Pipe Water Supply Scheme at Goalpukhur-I & II Block of Uttar Dinajpur District under Raiganj Division, PHE Dte.. | 114/RD/PHE | 20/01/2023 | 1072 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 388.45 | 0 | 0 | 74
1223 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. , SM/12393 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components, making compound lighting arrangement and grid connected ground mounted solar PV system with net metering at T/W no. I of Augmentation of Dharampur (Zone-I) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/013310) | 2088/MLMD | 04/07/2023 | 2005 | DILIP MAHATO. | 21.41 | 0 | 0 | 45
1224 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. , SM/12393 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- II of Dharampur Water Supply Scheme, (Zone- I) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 809/MLMD | 15/02/2024 | 533 | MAA BHABOTARINE ENTERPRISE | 10.76 | 0 | 0 | 89
1225 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. , SM/12393 | Augmentation | Additional Pipe Line and other ancillary works to provide FHTC at DHARAMPUR ZONE-I PWSS in connection with augmentation of Dharampur PWSS at Goalpokher-I Block under Islampur Sub-Division, P.H.E. Dte. under Raiganj Division ,PHED, Uttar Dinajpur. | 3022/RD/PHE | 03/10/2024 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 33.34 | 0 | 0 | 0
1226 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. , SM/12393 | Augmentation | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
1227 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Dharampur Zone-I Piped Water Supply Scheme in Goalpokhar-I and Goalpokhar-II block of Uttar Dinajpur District. , SM/12393 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dharampur Zone-I Water Supply Scheme (Augmentation) at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | 2489/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.93 | 0 | 0 | 0
1228 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME , SM/11796 | Augmentation | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Kasba (Itahar) Water Supply Scheme Scheme at Itahar Block under Raiganj Division P.H.E Dte. | 387/RD/PHE | 07/02/2023 | 45 | SARNALI ENTERPRISE SARNALI.RNJ@GMAIL.COM | 3.48 | 0 | 0 | 0
1229 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME , SM/11796 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of KASBA ITAHAR Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 424/MLMD | 14/03/2023 | 90 | M.S. ENTERPRISE | 11.56 | 0 | 0 | 0
1230 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME , SM/11796 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of KASBA ITAHAR Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 425/MLMD | 14/03/2023 | 90 | T.N. BANERJEE | 11.25 | 0 | 0 | 0
1231 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME , SM/11796 | Augmentation | Material Requisition To Resource Division | 1951/RD/PHE | 04/11/2022 | 0 | Resource Division | 50.19 | 0 | 0 | 0
1232 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME , SM/11796 | Augmentation | Hiring of vehicle for inspection and monitoring of Augmentation work of Kasba(Itahar) under JJM under Raiganj sub-division of Raiganj Division, PHE Dte. for the period from 24.11.2022 to 05.12.2022. | BP-2023-24-76 | 19/07/2023 | 0 | DEBASISH GHOSH | 0.1 | 0 | 0 | 0
1233 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME , SM/11796 | Augmentation | FHTC (Functional Household Tap Connection) for Kasba (Itahar) Water Supply Scheme [Augmentation Scheme] in Itahar Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2019/RD/PHE | 17/11/2022 | 90 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 60.76 | 0 | 0 | 0
1234 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME , SM/11796 | Augmentation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Augmentation of Kasba (Itahar) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011409) | 2806/MLMD | 17/08/2023 | 1915 | THE BUSINESS ENGINEERS INDIA | 6.77 | 0 | 0 | 85
1235 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME , SM/11796 | Augmentation | Augmentation work of KASBA(Itahar) and it's adjoining mouzas Piped Water Supply Scheme at Itahar Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | 1543/RD/PHE | 26/08/2022 | 810 | SANYAL ENTERPRISE | 300.01 | 0 | 0 | 100
1236 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME , SM/11796 | Augmentation | Construction Of Approach Road,Boundary Wall,Fhtc And Other Allied Works Of Kasba Itahar Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3571/RD/PHE | 05/12/2024 | 45 | SAHA CONSTRUCTION | 15.15 | 0 | 0 | 100
1237 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION FOR KASBA (ITAHAR) PIPED WATER SUPPLY SCHEME , SM/11796 | Augmentation | Construction Of Approach Road,Boundary Wall,Fhtc And Other Allied Works Of Kasba Itahar Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3572/RD/PHE | 05/12/2024 | 90 | SANTI TRADERS | 15.15 | 0 | 0 | 100
1238 | UTTAR DINAJPUR | Raiganj Division | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18147 | New | Material Requisition To Resource Division | 3314/RD/PHE | 05/12/2023 | 0 | Resource Division | 3.25 | 0 | 0 | 0
1239 | UTTAR DINAJPUR | Raiganj Division | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18147 | New | Implementation of PASCHIM GAGRA and it's adjoining mouzas Pipe Water Supply Scheme at KALIAGANJ Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | 1559/RD/PHE | 29/05/2023 | 90 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. TANAJIT77@GMAIL.COM | 59.46 | 0 | 0 | 61
1240 | UTTAR DINAJPUR | Raiganj Division | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18147 | New | Approach road with land development of headwork site & 2nd tubewell site and road restoration of Paschim Gagra PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur | 3782/RD/PHE | 19/12/2024 | 45 | DAS CONSTRUCTION COMPANY | 5.78 | 0 | 0 | 0
1241 | UTTAR DINAJPUR | Malda Mechanical | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18147 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Paschim Gagara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020864) | 2700/MLMD | 11/08/2023 | 509 | M/S JIBU SINGHA | 7.18 | 0 | 0 | 100
1242 | UTTAR DINAJPUR | Malda Mechanical | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18147 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Paschim Gagara, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-73 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 0.14 | 0 | 0 | 0
1243 | UTTAR DINAJPUR | Raiganj Division | PASCHIM GAGARA PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18147 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Paschim Gagra Water Supply Scheme at Kaliaganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 10 M3/hr. | 2492/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 13.83 | 0 | 0 | 0
1244 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Dakshin Kundal Pukur for installation of FHTC. , SM/09120 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Dakshin Kundal Pukur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2385/RD/PHE | 24/12/2021 | 30 | M/S LUCKY CONSTRUCTION | 13.19 | 0 | 0 | 0
1245 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Pawakhali and adjoining Mouzas water supply scheme , SM/07141 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Pawakhali and adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | 1415/RD/PHE | 11/12/2020 | 40 | M/S J.S.B ASSOCIATE CONSTRUCTION | 76.67 | 0 | 0 | 100
1246 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | SUPPLYING LAYING FITTING OF FHTC OF MAJLISHPUR WSS | 1576/RD | 23/12/2020 | 30 | DONE ENTERPRISE | 16.14 | 7.45 | 48.48 | 0
1247 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Khesra and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | 1525/RD/PHE | 23/12/2020 | 45 | UTTAM SAHA | 126.33 | 0 | 0 | 0
1248 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Faridpur Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Kaliaganj, Capacity- 60 M3/hr. | 1211/RD/PHE | 18/06/2021 | 90 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 33.59 | 0 | 0 | 0
1249 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Relaying of Pipe Line along embankment of Canal at Churakutti mouza for Functional Household Tap Connection of Majhlishpur Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | 2159/RD/PHE | 12/11/2021 | 30 | SAHA CONSTRUCTION | 4.59 | 0 | 0 | 1
1250 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | SUPPLYING LAYING FITTING OF GOAGAON PWSS | 1513/RD | 23/12/2020 | 30 | M/S GHOSH CONSTRUCTION | 7.87 | 0 | 0 | 0
1251 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | SUPPLYING LAYING FITTING FIXING OF FHTC OF MAJLISHPUR PWSS | 1576/ RD | 23/12/2020 | 30 | DONE ENTERPRISE | 16.14 | 0 | 0 | 0
1252 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | SUPPLYING FITTING UPVC PIPE FOR PIROJPUR PWSS | 1521/RD | 03/12/2020 | 30 | M/S HINDUSTHAN CONSTRUCTION | 14.46 | 0 | 0 | 1
1253 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Intia and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | 1541/RD/PHE | 23/12/2020 | 40 | UTTAM SAHA | 90.4 | 0 | 0 | 0
1254 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Allied Works for Construction and driving including vertical load test of 500 mm dia. (4 Piles Group) of Pile and 23mtr. deep in connection with construction of O.H.R. of FARIDPUR Water Supply Scheme under Raiganj Division, PHE Dte. | 2161/RD/PHE | 12/11/2021 | 30 | M/S ROYAL CONSTRUCTION | 4.43 | 0 | 0 | 1
1255 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | office accessories bill | BP-2022-23-27 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.05 | 0 | 0 | 0
1256 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | RESOURCE BILL | BP-2021-22-140 | 24/03/2022 | 0 | SUBSIDARY AC OF JJM WB ESCROW AC RESOURCE DIV PHE DIR | 37.16 | 0 | 0 | 0
1257 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | office accessories bill | BP-2022-23-30 | 28/04/2022 | 0 | M/S DUTTA ENTERPRISE | 0.1 | 0 | 0 | 0
1258 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER PIROJPUR AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, P.H.E.DTE. | 1559/RD/PHE | 24/12/2020 | 60 | AJIT PARMANIK | 193.98 | 0 | 0 | 0
1259 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER PHULATTI AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN KALIAGANJ BLOCK IN UNDER RAIGANJ DIVISION. (Part-VI) | 1223/RD/PHE | 18/06/2021 | 30 | DONE ENTERPRISE | 8.83 | 0 | 0 | 0
1260 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Ghirinigaon Khas and adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E.Dte. | 1532/RD/PHE | 23/12/2020 | 45 | SANYAL ENTERPRISE | 122.54 | 0 | 0 | 0
1261 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Purba-Rampur Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Kaliaganj,Capacity- 80 M3/hr. | 1207/RD/PHE | 18/06/2021 | 90 | M/S LOKENATH CONSTRUCTION | 36.22 | 0 | 0 | 0
1262 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS(FHTC) UNDER UDAYPUR AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UNDER RAIGANJ DIVISION. | 1561/RD/PHE | 24/12/2020 | 60 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 138.21 | 0 | 0 | 0
1263 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS(FHTC) UNDER PIPLAN AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN RAIGANJ BLOCK IN UNDER RAIGANJ DIVISION. | 1562/RD/PHE | 24/12/2020 | 60 | UTTAM SAHA | 144.08 | 0 | 0 | 0
1264 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Ghirnigaon Khas Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2193/RD/PHE | 17/11/2021 | 30 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 88.75 | 0 | 0 | 0
1265 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Restoration and Laying of Pipe Line for Functional Household Tap Connections of Biprit Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | 2427/RD/PHE | 31/12/2021 | 30 | M/S BHOWMIK ENTERPRISE BHOWMICKJ21@GMAIL.COM | 4.95 | 0 | 0 | 100
1266 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Jujharpur Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E. Dte. | 2382/RD/PHE | 24/12/2021 | 30 | SAHA CONSTRUCTION | 8.32 | 0 | 0 | 0
1267 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Work Order for Preparation of 70 Nos. deeds and arrangement of Registration of Land for implementation of different Piped Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E., Dte. | 1511/RD/PHE | 18/08/2022 | 60 | ASHIM CHANDA | 2.45 | 0 | 0 | 0
1268 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Providing Functional House Hold Connection (FHTC) for the purpose of Udaypur Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 494/RD/PHE | 17/02/2023 | 45 | SANKAR DAS | 8.07 | 0 | 0 | 0
1269 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Providing Functional House Hold Connection (FHTC) for the purpose of Maslandpur Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 495/RD/PHE | 17/02/2023 | 45 | GOPES SAHA | 6.91 | 0 | 0 | 0
1270 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Design, Fabrication, Supplying, Installation, Commissioning, Trial Run and 1(one) year Operation & maintenance of Pressure Type I.E.P (Iron Elimination Plant) for Purba Chutiakhore Water Supply Scheme under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:-Chopra, Capacity- 100 M3/hr. | 1212/RD/PHE | 18/06/2021 | 90 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 40.01 | 0 | 0 | 50
1271 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Goagaon and adjoining Mouzas Water Supply Scheme in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. | 1535/RD/PHE | 23/12/2020 | 45 | ALOK ENTERPRISE | 112.77 | 0 | 0 | 0
1272 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Malgaon and adjoining Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | 1536/RD/PHE | 23/12/2020 | 45 | UTTAM SAHA | 110.22 | 0 | 0 | 0
1273 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER MAJLISHPUR AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN GOALPOKHER-I BLOCK UNDER RAIGANJ DIVISION, P.H.E.DTE. | 1558/RD/PHE | 24/12/2020 | 60 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 151.59 | 0 | 0 | 0
1274 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | FHTC OF KHESRA WSS | 1515/RD | 23/12/2020 | 30 | MAA BICHITRA CONSTRUCTION | 8.64 | 0 | 0 | 0
1275 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Jaingaon and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | 1538/RD/PHE | 23/12/2020 | 45 | M/S SOMNATH KUNDU | 104.31 | 0 | 0 | 90
1276 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Wok Order for supplying, laying, fitting, fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete(1:2:4) in connection with Retrofitting of Functional Household Tap Connection(FHTC) under Majlishpur and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | 1516/RD/PHE | 23/12/2020 | 30 | DONE ENTERPRISE | 16.13 | 0 | 0 | 0
1277 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of functional Household Tap Connections (FHTC) under 10 nos. different schemes and Adj. Mouzas Water Supply Scheme in different block , SM/07389 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kamartor and Adjoining Mouzas Water Supply Scheme in Karandighi Block under Raiganj Division, P.H.E. Dte. | 1414/RD/PHE | 11/12/2020 | 40 | J.D.J. ENTERPRISE | 88.73 | 0 | 0 | 100
1278 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sripur and adjoining Mouzas water supply scheme , SM/06724 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Sripur and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E. Dte. | 1237/RD/PHE | 16/10/2020 | 40 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 80.5 | 0 | 0 | 0
1279 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sripur and adjoining Mouzas water supply scheme , SM/06724 | Retrofitting | LAYING FITTING FHTC OF SRIPUR WSS | 1523/RD | 23/12/2020 | 30 | MS SARKAR ENTERPRISE ABDULGHATA | 8.14 | 5.63 | 99.6 | 0
1280 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sripur and adjoining Mouzas water supply scheme , SM/06724 | Retrofitting | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C, Vehicle No. WB 59D 1337) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Months (Period from 15.07.2024 upto 14.01.2025). | 2159/RD/PHE | 15/07/2024 | 184 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 2.4 | 0 | 0 | 0
1281 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem , SM/06728 | Retrofitting | FHTC OF DEBIGANJ WSS | 1512/RD | 23/12/2020 | 30 | HAQUE CONSTRUCTION | 18.37 | 18.34 | 99.81 | 0
1282 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem , SM/06728 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Debiganj and adjoining Mouzas water supply scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | 1236/RD/PHE | 16/10/2020 | 40 | HAQUE CONSTRUCTION | 56.27 | 0 | 0 | 0
1283 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Debiganj and adjoining Mouzas water supply schem , SM/06728 | Retrofitting | FHTC FOR DEBIGANJ WSS | 1236/RD | 16/10/2020 | 40 | HAQUE CONSTRUCTION | 56.27 | 53.65 | 100 | 0
1284 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chakulia and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. , SM/09183 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Chakulia Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Islampur Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1818/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.84 | 0 | 0 | 0
1285 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chakulia and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. , SM/09183 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Chakulia Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-Ii Block under Raiganj Division, P.H.E. Dte. | 2083/RD/PHE | 02/11/2021 | 30 | TAPAN KUMAR MAJUMDER | 10.6 | 0 | 0 | 1
1286 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chakulia and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. , SM/09183 | Retrofitting | Material Requisition To Resource Division | 36/RD/PHE | 06/01/2022 | 0 | Resource Division | 2.5 | 0 | 0 | 0
1287 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Chakulia and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. , SM/09183 | Retrofitting | Allied works in connection with retrofitting of FHTC in Chakulia PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1040/RD/PHE | 02/04/2025 | 60 | ASHIM CHANDA | 0.98 | 0 | 0 | 0
1288 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Goalpukhur and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09186 | Retrofitting | Route Survey & Preparation of DPR of GOALPOKHAR PWSS under Raiganj Division, PHE Dte. | 150/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 4.32 | 0 | 0 | 0
1289 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Goalpukhur and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09186 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Goalpukhur Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. | 2086/RD/PHE | 02/11/2021 | 421 | HAQUE CONSTRUCTION | 9.01 | 0 | 0 | 100
1290 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Karandighi and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09188 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Karandighi Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Karandighi Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1821/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.29 | 0 | 0 | 0
1291 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Karandighi and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09188 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Karandighi Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E Dte. | 436/RD/PHE | 16/02/2022 | 30 | M/S BHOWMIK CONSTRUCTION | 4.6 | 0 | 0 | 0
1292 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Karandighi and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09188 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Karandighi Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E. Dte. | 2088/RD/PHE | 02/11/2021 | 30 | MAA SHEETALA ENTERPRISE | 16.55 | 0 | 0 | 1
1293 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Karandighi and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09188 | Retrofitting | Preparation of Additional DPR For Karandighi Zone-II in connection with Retrofitting of Functional House Hold Tap Connection of Karandighi PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 2150/RD/PHE | 07/12/2022 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM MANASIJ_DUTTA@VSNL.COM | 0.78 | 0 | 0 | 1
1294 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Karandighi and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09188 | Retrofitting | Allied works in connection with retrofitting of FHTC in Karandighi PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2604/RD/PHE | 13/09/2023 | 60 | ASHIM CHANDA | 0.95 | 0 | 0 | 100
1295 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Karandighi and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09188 | Retrofitting | Material Requisition To Resource Division | 33/RD/PHE | 06/01/2022 | 0 | Resource Division | 3.93 | 0 | 0 | 0
1296 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Karandighi and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09188 | Retrofitting | Material Requisition To Resource Division | 1814/RD/PHE | 26/09/2022 | 0 | Resource Division | 2.83 | 0 | 0 | 0
1297 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Panjipara and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09190 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Panjipara Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1816/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.3 | 0 | 0 | 0
1298 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Panjipara and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09190 | Retrofitting | Preparation of Additional DPR For Panjipara Zone-II in connection with Retrofitting of Functional House Hold Tap Connection of Panjipara PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 2135/RD/PHE | 07/12/2022 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM MANASIJ_DUTTA@VSNL.COM | 0.78 | 0 | 0 | 1
1299 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Panjipara and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09190 | Retrofitting | Material Requisition To Resource Division | 38/RD/PHE | 06/01/2022 | 0 | Resource Division | 3.98 | 0 | 0 | 0
1300 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Panjipara and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09190 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Panjipara Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. | 2090/RD/PHE | 02/11/2021 | 30 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.75 | 0 | 0 | 100
1301 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Panjipara and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09190 | Retrofitting | Allied works in connection with retrofitting of FHTC in Panjipara PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2608/RD/PHE | 13/09/2023 | 60 | ASHIM CHANDA | 0.84 | 0 | 0 | 100
1302 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Tungail for installation of FHTC. , SM/09164 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Tungail Bilpara Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2155/RD/PHE | 12/11/2021 | 30 | M/S ROYAL CONSTRUCTION | 4.55 | 0 | 0 | 1
1303 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Sherpur for installation of FHTC. , SM/09167 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Sherpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2156/RD/PHE | 12/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 4.51 | 0 | 0 | 0
1304 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Dakshin Jibhokati for installation of FHTC. , SM/09138 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Dakshin Jibhakata Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2152/RD/PHE | 12/11/2021 | 30 | M/S BHOWMIK ENTERPRISE | 1.38 | 0 | 0 | 1
1305 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Gutin WSS for installation of FHTC. , SM/09141 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of GUTIN Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2101RD/PHE | 03/11/2021 | 30 | M/S.BANGARAJ | 8.82 | 0 | 0 | 1
1306 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Bheur WSS for installation of FHTC. , SM/09147 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of BHEUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2106/RD/PHE | 03/11/2021 | 30 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. | 8.82 | 0 | 0 | 1
1307 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of SridharpurWSS for installation of FHTC. , SM/09150 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of SRIDHARPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2109/RD/PHE | 03/11/2021 | 30 | RAHUL ENTERPRISE | 11.38 | 0 | 0 | 1
1308 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Shergram WSS for installation of FHTC (Part-A & B). , SM/09109 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of SHERGRAM Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (PART-B) | 2183/RD/PHE | 17/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 14.39 | 0 | 0 | 0
1309 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Shergram WSS for installation of FHTC (Part-A & B). , SM/09109 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of SHERGRAM Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (PART-A) | 2182/RD/PHE | 17/11/2021 | 30 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 5.53 | 0 | 0 | 0
1310 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Barua WSS for installation of FHTC. , SM/09118 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of BARUA Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | 2190/RD/PHE | 17/11/2021 | 30 | M/S P.S. ENTERPRISE | 18.32 | 0 | 0 | 0
1311 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Barua WSS for installation of FHTC. , SM/09118 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Barua Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | 2141/RD/PHE | 12/11/2021 | 30 | M/S ROYAL CONSTRUCTION | 4.85 | 0 | 0 | 1
1312 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Barua WSS for installation of FHTC. , SM/09118 | Retrofitting | HIRE CHARGES OF VEHICLE OF EXECUTIVE ENGINEER,RAIGANJ DIVISION,P.HE.DTE. | BP-2024-25-18 | 15/04/2024 | 0 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.77 | 0 | 0 | 0
1313 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Sitgram for installation of FHTC. , SM/09119 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Sitgram Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | 2142/RD/PHE | 12/11/2021 | 30 | M/S ROYAL CONSTRUCTION | 4.85 | 0 | 0 | 1
1314 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Sitgram for installation of FHTC. , SM/09119 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of SITGRAM Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | 2191/RD/PHE | 17/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 11.69 | 0 | 0 | 0
1315 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Ghirnigaonfor installation of FHTC. , SM/09122 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Ghirnigaon Khas Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2193/RD/PHE | 17/11/2021 | 30 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 88.75 | 0 | 0 | 0
1316 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Sinking 2 nos. of Ground Bored wells,(250mm x 150mm X 120mtr) including cost of materials with proper development and necessary yield for ground water based PWSS for Kanki Matiari and its adjoining Mouzas Piped Water Supply Scheme at Goalpokhar-II Block under Raiganj Division, P.H.E Dte in the district of Uttar Dinajpur. | 49/RD/PHE | 07/01/2022 | 21 | M/S SARKAR ENTERPRISE | 16.99 | 0 | 0 | 1
1317 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Providing and delivering A4 Xerox copies of DPRs for Raiganj Division, P.H.E. Dte., | 1502/RD | 18/08/2022 | 7 | JUMBO XEROX | 0.09 | 0 | 0 | 0
1318 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Providing and delivering A4 Xerox copies of DPRs for Raiganj Division, P.H.E. Dte., | 1503/RD | 18/08/2022 | 7 | JUMBO XEROX | 0.02 | 0 | 0 | 0
1319 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | 1537\RD | 25/08/2022 | 7 | JUMBO XEROX | 0.1 | 0 | 0 | 0
1320 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Soil Investigation for Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including RCC Bored Pile & Pile Cap upto pedestal For Kanki Matiari W/S Scheme in Goalpukhur-II Block in Uttar Dinajpur District. | 1238/RD/PHE | 20/06/2022 | 20 | MOYTEC | 1.98 | 0 | 0 | 0
1321 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Material Requisition To Resource Division | 2006/RD/PHE | 16/11/2022 | 0 | Resource Division | 10.51 | 0 | 0 | 0
1322 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | xerox bill | BP-2022-23-212 | 04/11/2022 | 0 | JUMBO XEROX | 0.1 | 0 | 0 | 0
1323 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | xerox bill | BP-2022-23-206 | 04/11/2022 | 0 | JUMBO XEROX | 0.02 | 0 | 0 | 0
1324 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | xerox bill | BP-2022-23-205 | 04/11/2022 | 0 | JUMBO XEROX | 0.09 | 0 | 0 | 0
1325 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Kanki Matiari Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 381/RD/PHE | 07/02/2023 | 45 | UJJAL KUMAR SARKAR KUMARUJJAL51@GMAIL.COM | 5.01 | 0 | 0 | 100
1326 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Kanki-Matiari Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 378/RD/PHE | 07/02/2023 | 45 | PANDIT CONSTRUCTION PANDIT.RNJ@GMAIL.COM | 4.09 | 0 | 0 | 100
1327 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Material Requisition To Resource Division | 638/RD/PHE | 23/03/2022 | 0 | Resource Division | 8.75 | 0 | 0 | 0
1328 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Construction of Over Head Reservoir(Capacity-250 Cum) of KANKI MATIARI Pipe Water Supply Scheme in connection with Augmentation at GOALPOKHAR-II Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 655/RD/PHE | 03/03/2023 | 240 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 77.82 | 0 | 0 | 75
1329 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Laying of Distribution system including construction of Valve Chamber and Other related works for Kanki Matiari and its adjoining Mouzas Piped Water Supply Scheme at Goalpokhar-II Block under Raiganj Division, P.H.E Dte in the district of Uttar Dinajpur. (PART-A) | 50/RD/PHE | 07/01/2022 | 45 | HAQUE CONSTRUCTION | 59.72 | 0 | 0 | 100
1330 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of KANKI MATIYARI Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2415/MLMD | 26/09/2022 | 90 | TARUN KUMAR DEY | 9.24 | 0 | 0 | 100
1331 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of KANKI MATIYARI Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2416/MLMD | 26/09/2022 | 90 | UTTAM KUMAR GHOSH | 9.27 | 0 | 0 | 100
1332 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Laying Rising Main pipeline interconnection of Tubewells including construction of Valve Chamber and Other related works for Kanki Matiari and its adjoining Mouzas Piped Water Supply Scheme at Goalpokhar-II Block under Raiganj Division, P.H.E Dte in the district of Uttar Dinajpur.(PART -A) | 48/RD/PHE | 07/01/2022 | 45 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 0.94 | 0 | 0 | 100
1333 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Additional Pipe line with construction of Boundary Wall(Head Work) and other ancillary works at Kanki-Matiari Piped Water Supply Scheme in connection with Augmentation of Kanki-Matiari PWSS under Islampur Sub-Division P.H.E. Dte Under Raiganj Division, PHE Dte. | 1691/RD/PHE | 10/06/2024 | 480 | HAQUE CONSTRUCTION | 25.31 | 0 | 0 | 50
1334 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kanki Matiari Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 25 M3/hr. | 2507/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 16.3 | 0 | 0 | 0
1335 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kanki Matiari Piped Water Supply Scheme. , SM/09985 | Augmentation | FHTC (Functional Household Tap Connection) for Kanki Matiari Water Supply Scheme [Augmentation Scheme] in Goalpukhur-II Block of Uttar Dinajpur District | 1018/RD/PHED | 12/05/2022 | 45 | M/S SARKAR ENTERPRISE | 26.8 | 0 | 0 | 100
1336 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Pirojpur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10445 | Retrofitting | Restoration of pipe line for providing FHTC for Pirojpur Water Supply Scheme at Raiganj Block In the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte.(Phase-II). | 1273/RD/PHE | 24/06/2022 | 45 | TAPAN KUMAR DUTTA | 80.45 | 0 | 0 | 0
1337 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Pirojpur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10445 | Retrofitting | hiring of inspection vehicle | BP-2023-24-283 | 16/02/2024 | 0 | DEBASISH GHOSH | 0.4 | 0 | 0 | 0
1338 | UTTAR DINAJPUR | Raiganj Division | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR , SM/11820 | New | Material Requisition To Resource Division | 2125/RD/PHE | 03/12/2022 | 0 | Resource Division | 26.44 | 0 | 0 | 0
1339 | UTTAR DINAJPUR | Malda Mechanical | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR , SM/11820 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of PASCHIM GOALGAON PWSS, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003196193 | 27/07/2023 | 90 | W.B.S.E.D.C.LTD | 6.65 | 0 | 0 | 100
1340 | UTTAR DINAJPUR | Malda Mechanical | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR , SM/11820 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of PASCHIM GOALGAON PWSS, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003196200 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.27 | 0 | 0 | 100
1341 | UTTAR DINAJPUR | Malda Mechanical | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR , SM/11820 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Paschim Goalgaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011936) | 2095/MLMD | 04/07/2023 | 180 | SRI KRISHNA NIRMAN | 24.03 | 0 | 0 | 88
1342 | UTTAR DINAJPUR | Raiganj Division | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR , SM/11820 | New | DI Pipe Carrying RCC Structure Through River of Paschim Goalgaon PWSS(New Scheme) at Raiganj Block under Raiganj Division P.H.E. Dte., Uttar Dinajpur.(Phase-I) | 3015/RD/PHE | 03/10/2024 | 45 | CHAPDUAR LABOUR CO- OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 29.02 | 0 | 0 | 0
1343 | UTTAR DINAJPUR | Raiganj Division | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR , SM/11820 | New | Implementation of PASCHIM GOALGAON and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division. | 1993/RD/PHE | 14/11/2022 | 1144 | M/S LOKENATH CONSTRUCTION | 487.48 | 0 | 0 | 60
1344 | UTTAR DINAJPUR | Raiganj Division | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR , SM/11820 | New | Construction of Pump House & Boundary Wall at Paschim Goalgaon Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division.( Pump House at Head Work,2nd TubeWell and Boundary Wall at Head work Site and 2nd Tube-Well. ) | 383/RD/PHE | 07/02/2023 | 327 | HERO CONSTRUCTION HEROCONST.RNJ@GMAIL.COM | 35.61 | 0 | 0 | 67
1345 | UTTAR DINAJPUR | Raiganj Division | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR , SM/11820 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Paschim Goalgaon PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 13/RD/PHE | 02/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 43.4 | 0 | 0 | 0
1346 | UTTAR DINAJPUR | Raiganj Division | PASCHIM GOALGAON PWSS IN RAIGANJ BLOCK IN THE DISTRICT OF UTTAR DINAJPUR , SM/11820 | New | Trial Run For Paschim Goalgaon PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | 535/RD/PHE | 12/02/2025 | 90 | M/S RATAN SARKAR & SON | 0.87 | 0 | 0 | 0
1347 | UTTAR DINAJPUR | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Goalpokhar-II, Goalpokhar-I and Hemtabad in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. , SM/11516 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Goalpokhor-ll & Goalpokhor-I, Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1501/RD/PHE | 19/05/2023 | 92 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 432.57 | 0 | 0 | 2
1348 | UTTAR DINAJPUR | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Goalpokhar-II, Goalpokhar-I and Hemtabad in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. , SM/11516 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Itahara village under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2882/RD/PHE | 25/09/2024 | 180 | MAA SHEETALA ENTERPRISE | 40.1 | 0 | 0 | 0
1349 | UTTAR DINAJPUR | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR , SM/11819 | New | Material Requisition To Resource Division | 2123/RD/PHE | 03/12/2022 | 0 | Resource Division | 31.4 | 0 | 0 | 0
1350 | UTTAR DINAJPUR | Malda Mechanical | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR , SM/11819 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Tenahari PWSS , Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003133018 | 12/04/2023 | 15 | W.B.S.E.D.C.LTD | 0.63 | 0 | 0 | 0
1351 | UTTAR DINAJPUR | Malda Mechanical | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR , SM/11819 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Tenahari PWSS , Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003133029 | 12/04/2023 | 15 | W.B.S.E.D.C.LTD | 0.74 | 0 | 0 | 0
1352 | UTTAR DINAJPUR | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR , SM/11819 | New | Hiring of Inspection Vehicle for office of the Assistant engineer, Raiganj Sub-Division, P.H.E. Dte. for the period from 16.01.2023 to 15.02.2023. | BP-2023-24-213 | 07/12/2023 | 0 | DEBASISH GHOSH | 0.4 | 0 | 0 | 0
1353 | UTTAR DINAJPUR | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR , SM/11819 | New | Implementation of TENAHARI and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 1994/RD/PHE | 14/11/2022 | 365 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 260.7 | 0 | 0 | 80
1354 | UTTAR DINAJPUR | Malda Mechanical | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR , SM/11819 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II of Tenahari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011957) | 1135/MLMD | 26/06/2023 | 120 | DEBAPRIYA SAHA | 27.11 | 0 | 0 | 86
1355 | UTTAR DINAJPUR | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR , SM/11819 | New | Construction of Pump House & Boundary Wall at Tenahari Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division. (Pump House at Head Work, 2nd TubeWell and Boundary Wall at Head work Site and 2nd Tube-Well.) | 386/RD/PHE | 08/02/2023 | 385 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 36.15 | 0 | 0 | 100
1356 | UTTAR DINAJPUR | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR , SM/11819 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Tenahari PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3744/RD/PHE | 18/12/2024 | 135 | M/S MAA TARA CONSTRUCTION | 26.62 | 0 | 0 | 0
1357 | UTTAR DINAJPUR | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR , SM/11819 | New | Trial Run For Tenahari PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | 543/RD/PHE | 12/02/2025 | 90 | M/S MAA TARA CONSTRUCTION | 0.88 | 0 | 0 | 0
1358 | UTTAR DINAJPUR | Raiganj Division | TENAHARI PWSS IN THE DISTRICT OF UTTAR DINAJPUR , SM/11819 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
1359 | UTTAR DINAJPUR | Malda Mechanical | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11821 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Kuliara Anantapur PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003203670 | 02/08/2023 | 90 | W.B.S.E.D.C.LTD | 8.31 | 0 | 0 | 100
1360 | UTTAR DINAJPUR | Raiganj Division | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11821 | New | Material Requisition To Resource Division | 521/RD/PHE | 20/02/2023 | 0 | Resource Division | 33.03 | 0 | 0 | 0
1361 | UTTAR DINAJPUR | Raiganj Division | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11821 | New | Material Requisition To Resource Division | 521/RD/PHE | 20/02/2023 | 0 | Resource Division | 32.76 | 0 | 0 | 0
1362 | UTTAR DINAJPUR | Malda Mechanical | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11821 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of KULIARA ANANTAPUR PWSS ,Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-465 | 26/01/2024 | 0 | W.B.S.E.D.C.LTD | 0.45 | 0 | 0 | 0
1363 | UTTAR DINAJPUR | Malda Mechanical | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11821 | New | Modified Quotation Charge at TW No- II of Kuliara Anantapur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-98 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 7.84 | 0 | 0 | 0
1364 | UTTAR DINAJPUR | Raiganj Division | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11821 | New | Implementation of KULIARA ANANTAPUR and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. (2nd Call) | 96/RD/PHE | 19/01/2023 | 1078 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 369 | 0 | 0 | 45
1365 | UTTAR DINAJPUR | Raiganj Division | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11821 | New | Construction of Pump House & Boundary Wall at Kuliara Anantapur Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division.( Pump House at Head Work, 2nd Tube Well and Boundary Wall at Head work Site and 2nd Tube-Well. ) | 382/RD/PHE | 08/02/2023 | 781 | M/S. BANGARAJ ASHOKLALRNJ@GMAIL.COM | 36.13 | 0 | 0 | 70
1366 | UTTAR DINAJPUR | Malda Mechanical | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11821 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Kuliara Anantapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011943) | 3689/MLMD | 29/11/2023 | 655 | MANIK CHANDRA SAHA. | 25.33 | 0 | 0 | 78
1367 | UTTAR DINAJPUR | Raiganj Division | KULIARA ANANTAPUR PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR , SM/11821 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Kuliara Anantapur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3750/RD/PHED | 18/12/2024 | 135 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 40.59 | 0 | 0 | 0
1368 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. , SM/12394 | Augmentation | Material Requisition To Resource Division | 2172/RD/PHE | 09/12/2022 | 0 | Resource Division | 40.38 | 0 | 0 | 0
1369 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. , SM/12394 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- II of Dharampur Water Supply Scheme, (Zone- II) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013311) | 2092/MLMD | 04/07/2023 | 90 | S.P. ENTERPRISE (SILIGURI) | 10.66 | 0 | 0 | 99
1370 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. , SM/12394 | Augmentation | Augmentation of DHARAMPUR Zone-II and it's adjoining mouzas Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 125/RD/PHE | 20/01/2023 | 802 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 363.42 | 0 | 0 | 60
1371 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. , SM/12394 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components, making compound lighting arrangement and grid connected ground mounted solar PV system with net metering at T/W no. I of Augmentation of Dharampur (Zone-II) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013311) | 2089/MLMD | 04/07/2023 | 2005 | DILIP MAHATO. | 21.42 | 0 | 0 | 45
1372 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. , SM/12394 | Augmentation | Laying & Distribution pipeline at Dharampur Zone-II in connection with Augmentation of DHARAMPUR Zone-II at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.( Laying Distribution pipe line.) | 3342/RD/PHE | 06/12/2023 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 71.53 | 0 | 0 | 60
1373 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. , SM/12394 | Augmentation | Construction of Approach Road in connection with Augmentation of Dharampur Zone-II PWSS at Goalpokhur-I Block under Raiganj Division, PHE Dte. | 3296/RD/PHE | 20/11/2024 | 15 | KULICK ENTERPRISE | 3.77 | 0 | 0 | 0
1374 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. , SM/12394 | Augmentation | Inter-connecting various CIDF Pipe & with main delivery line and other ancillary works for Dharampur Zone- II Piped Water Supply Scheme (Augmentation Dharampur Zone-II)under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | 3023/RD/PHE | 03/10/2024 | 20 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 8.8 | 0 | 0 | 0
1375 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Dharampur Zone-II Piped Water Supply Scheme in Goalpokhar-I block of Uttar Dinajpur District. , SM/12394 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dharampur Zone-II Water Supply Scheme(Augmentation) at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | 2490/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.93 | 0 | 0 | 0
1376 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME , SM/11724 | Augmentation | Augmentation work of LAKHIPUR and it's adjoining mouzas Piped Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | 1545/RD/PHE | 26/08/2022 | 90 | UTTAM SAHA | 194.17 | 0 | 0 | 0
1377 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME , SM/11724 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Lakhipur Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 406/RD/PHE | 09/02/2023 | 45 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 4.95 | 0 | 0 | 0
1378 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME , SM/11724 | Augmentation | Repairing of Pump House at 2nd Tubewell Site in connection with Augmentation of Lakhipur Piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | 375/RD/PHE | 07/02/2023 | 45 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 2.09 | 0 | 0 | 0
1379 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME , SM/11724 | Augmentation | Construction of Over Head Reservoir(Capacity-450 Cum) of LAKHIPUR Pipe Water Supply Scheme in connection with Augmentation at CHOPRA Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 737/RD/PHE | 15/03/2023 | 365 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 158.66 | 0 | 0 | 0
1380 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME , SM/11724 | Augmentation | Making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Lakhipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011434) | 2659/MLMD | 10/08/2023 | 1915 | MAA BHABOTARINE ENTERPRISE. | 10.54 | 0 | 0 | 0
1381 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME , SM/11724 | Augmentation | Material Requisition To Resource Division | 1946/RD/PHE | 04/11/2022 | 0 | Resource Division | 26.53 | 0 | 0 | 0
1382 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME , SM/11724 | Augmentation | FHTC (Functional Household Tap Connection) for Lakhipur Water Supply Scheme [Augmentation Scheme] in Chopra Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2027/RD/PHE | 17/11/2022 | 90 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 79.41 | 0 | 0 | 45
1383 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME , SM/11724 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Lakhipur Water Supply Scheme TW no I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 739/ MLMD | 20/04/2023 | 90 | GHOSH BROTHERS... | 12.5 | 0 | 0 | 100
1384 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME , SM/11724 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Lakhipur Water Supply Scheme TW no II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 518/MLMD | 20/03/2023 | 90 | M/S. KUNDU CONSTRACTION | 12.5 | 0 | 0 | 100
1385 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME , SM/11724 | Augmentation | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month(Period from 01.07.2023 to 30.06.2024). | 1722/RD/PHE | 28/06/2023 | 366 | DEBASISH GHOSH | 4.8 | 0 | 0 | 0
1386 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME , SM/11724 | Augmentation | Construction Of Boundary Wall With Gate at Head Work Site, & 2nd Tube-Well Site under Augmentation Of Lakhipur PWSS at Chopra Block under Raiganj Division, PHE dte. | 3295/RD/PHE | 20/11/2024 | 480 | M/S GHOSH CONSTRUCTION GHOSH1.RNJ@GMAIL.COM | 8.59 | 0 | 0 | 70
1387 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME , SM/11724 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Lakhipur Water Supply Scheme (Aumentation)at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | 1927/RD/PHE | 30/06/2025 | 180 | KOHINOOR ALAM | 32.33 | 0 | 0 | 0
1388 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF LAKHIPUR PIPED WATER SUPPLY SCHEME , SM/11724 | Augmentation | Laying additional pipe line with FHTC in connection with Augmentation Of Lakhipur Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.PHE Dte. | 3298/RD/PHE | 20/11/2024 | 120 | D. K. ASSOCIATES | 9.35 | 0 | 0 | 100
1389 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11799 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-I) T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 251/MLMD | 24/02/2023 | 90 | H.K. DAS & CO. | 11.46 | 0 | 0 | 0
1390 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11799 | Augmentation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Augmentation of Hemtabad Water Supply Scheme, ( Zone- I) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011647) | 3701/MLMD | 29/11/2023 | 1825 | AMITAVA CHAKRABORTY | 6.85 | 0 | 0 | 0
1391 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11799 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-I) T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 250/MLMD | 24/02/2023 | 90 | AHALYA ENGINEERING WORKS | 11.51 | 0 | 0 | 100
1392 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11799 | Augmentation | Repairing of Pump house of Head Works and 2nd Tube Well Site in connection with Augmentation of Hemtabad Zone-I Water Supply Scheme at Hemtabad block under Raiganj Division P.H.E. Dte. | 400/RD/PHE | 08/02/2023 | 45 | M/S SARKAR ENTERPRISE (UDAYPUR) SARKARTAPATI.UDI@GMAIL.COM | 2.98 | 0 | 0 | 100
1393 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11799 | Augmentation | Material Requisition To Resource Division | 1952/RD/PHE | 04/11/2022 | 0 | Resource Division | 91.08 | 0 | 0 | 0
1394 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11799 | Augmentation | Material Requisition To Resource Division | 1518/RD/PHE | 23/05/2023 | 0 | Resource Division | 2.02 | 0 | 0 | 0
1395 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11799 | Augmentation | Augmentation work of HEMTABAD ZONE-I Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | 1754/RD/PHE | 15/09/2022 | 90 | M/S LOKENATH CONSTRUCTION | 501.39 | 0 | 0 | 90
1396 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11799 | Augmentation | Construction of boundary wall & toilet block of Augmentation of Hemtabad Zone-I PWSS at 2nd tube well site at Hemtabad block under Raiganj Division PHE Dte., Uttar Dinajpur. | 2785/RD/PHE | 10/10/2023 | 75 | M/S SARKAR ENTERPRISE UDAYPUR | 5.05 | 0 | 0 | 100
1397 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11799 | Augmentation | FHTC (Functional Household Tap Connection) for Hemtabad Zone-I Water Supply Scheme [Augmentation Scheme] in Hemtabad Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2028/RD/PHE | 17/11/2022 | 852 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. TANAJIT77@GMAIL.COM | 72.5 | 0 | 0 | 60
1398 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-I in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11799 | Augmentation | Construction of Over Head Reservoir(Capacity-400 Cum) of HEMTABAD (Zone-I) Pipe Water Supply Scheme in connection with Augmentation at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 730/RD/PHE | 15/03/2023 | 438 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 143.13 | 0 | 0 | 40
1399 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe Line for providing FHTC of Gunabari Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) , SM/10426 | Retrofitting | Restoration of Pipeline for Providing FHTC of Gunabari Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) | 1046/RD/PHED | 12/05/2022 | 45 | M/S.SADHANA ENTERPRISE | 10.26 | 0 | 0 | 1
1400 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block , SM/12089 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dakshin Besabari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013508) | 2211/MLMD | 18/07/2023 | 120 | DEBAPRIYA SAHA | 26.19 | 0 | 0 | 0
1401 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block , SM/12089 | New | Material Requisition To Resource Division | 1039/RD/PHE | 04/04/2023 | 0 | Resource Division | 17.39 | 0 | 0 | 0
1402 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block , SM/12089 | New | Quotation for new service connection at DAKSHIN BESABARI PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12089) | BP-2024-25-309 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 6.55 | 0 | 0 | 0
1403 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block , SM/12089 | New | Quotation for new service connection at DAKSHIN BESABARI PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12089) | BP-2024-25-310 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 5.58 | 0 | 0 | 0
1404 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block , SM/12089 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
1405 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block , SM/12089 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | 1816/RD/PHE | 26/06/2024 | 198 | MD ZAFAR EQUEBAL | 2.6 | 0 | 0 | 100
1406 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block , SM/12089 | New | Providing FHTC in connection with Dakhshin Besabari Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 1173/RD/PHE | 23/04/2025 | 15 | R. R. CONSTRUCTION | 6.75 | 0 | 0 | 0
1407 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block , SM/12089 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakshin Besabari Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 30 M3/hr. | 1817/RD/PHE | 24/06/2025 | 180 | M K ENTERPRISE | 17.34 | 0 | 0 | 0
1408 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN BESABARI Piped Water Supply Scheme at Chopra Block , SM/12089 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at DAKSHIN BESABRI PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | 2096/RD/PHE | 15/07/2025 | 180 | M/S SACHIN KUMAR | 33.76 | 0 | 0 | 0
1409 | UTTAR DINAJPUR | Raiganj Division | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12099 | New | Material Requisition To Resource Division | 2181/RD/PHE | 12/12/2022 | 0 | Resource Division | 27.75 | 0 | 0 | 0
1410 | UTTAR DINAJPUR | Malda Mechanical | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12099 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of PALIHAR PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003202403 | 02/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.7 | 0 | 0 | 100
1411 | UTTAR DINAJPUR | Malda Mechanical | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12099 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of PALIHAR PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003224937 | 08/09/2023 | 90 | W.B.S.E.D.C.LTD | 3.2 | 0 | 0 | 100
1412 | UTTAR DINAJPUR | Raiganj Division | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12099 | New | Implementation of PALIHAR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division. | 295/RD/PHE | 01/02/2023 | 1065 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 509.77 | 0 | 0 | 67
1413 | UTTAR DINAJPUR | Raiganj Division | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12099 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under PALIHAR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 585/RD/PHE | 05/03/2024 | 45 | M/S ARITRA DUTTA | 22.57 | 0 | 0 | 0
1414 | UTTAR DINAJPUR | Malda Mechanical | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12099 | New | Additional quotation for palihar water supply scheme TW-II in the district of uttar dinajpur | BP-2024-25-352 | 24/06/2024 | 0 | W.B.S.E.D.C.LTD | 1.07 | 0 | 0 | 0
1415 | UTTAR DINAJPUR | Malda Mechanical | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12099 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Palihar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013030) | 1119/MLMD | 23/06/2023 | 898 | DEY ENTERPRISE.. | 26.36 | 0 | 0 | 84
1416 | UTTAR DINAJPUR | Raiganj Division | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12099 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Palihar PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 07/RD/PHE | 02/01/2025 | 45 | AJIT PRAMANIK | 58.77 | 0 | 0 | 0
1417 | UTTAR DINAJPUR | Raiganj Division | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12099 | New | Trial Run For Palihar PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | 522/RD/PHE | 12/02/2025 | 90 | AJIT PRAMANIK | 0.88 | 0 | 0 | 0
1418 | UTTAR DINAJPUR | Raiganj Division | PALIHAR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12099 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
1419 | UTTAR DINAJPUR | Raiganj Division | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12101 | New | Material Requisition To Resource Division | 2189/RD/PHE | 12/12/2022 | 0 | Resource Division | 33.71 | 0 | 0 | 0
1420 | UTTAR DINAJPUR | Malda Mechanical | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12101 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of MADHABPUR, PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003123589 | 04/04/2023 | 365 | W.B.S.E.D.C.LTD | 0.63 | 0 | 0 | 0
1421 | UTTAR DINAJPUR | Malda Mechanical | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12101 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of MADHABPUR, PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003123584 | 04/04/2023 | 365 | W.B.S.E.D.C.LTD | 0.74 | 0 | 0 | 0
1422 | UTTAR DINAJPUR | Raiganj Division | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12101 | New | Implementation of MADHABPUR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 71/RD/PHE | 16/01/2023 | 928 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 366.24 | 0 | 0 | 60
1423 | UTTAR DINAJPUR | Malda Mechanical | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12101 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Madhabpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013032) | 1134/MLMD | 26/06/2023 | 180 | MAA BHABOTARINE ENTERPRISE. | 25.36 | 0 | 0 | 90
1424 | UTTAR DINAJPUR | Raiganj Division | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12101 | New | :Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of Shibpur Madanpur Pacca Rasta - Kunarhat Tala Pacca Rasta ( WB15296 : Under DLP) caused due to pipe laying by PHED under Madhabpur PWSS at different stretched of road under WBSRDA Uttar Dinajpur Division. | BP-2024-25-279 | 08/10/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 3.2 | 0 | 0 | 0
1425 | UTTAR DINAJPUR | Raiganj Division | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12101 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Madhabpur PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3739/RD/PHE | 18/12/2024 | 135 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 23.53 | 0 | 0 | 0
1426 | UTTAR DINAJPUR | Raiganj Division | MADHABPUR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12101 | New | Trial Run For Madhabpur PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | 521/RD/PHE | 12/02/2025 | 90 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0 | 0
1427 | UTTAR DINAJPUR | Raiganj Division | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12103 | New | Material Requisition To Resource Division | 2191/RD/PHE | 12/12/2022 | 0 | Resource Division | 28.04 | 0 | 0 | 0
1428 | UTTAR DINAJPUR | Malda Mechanical | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12103 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of KHATSA, PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003123596 | 04/04/2023 | 365 | W.B.S.E.D.C.LTD | 0.45 | 0 | 0 | 0
1429 | UTTAR DINAJPUR | Malda Mechanical | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12103 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Khatsa PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003123608 | 04/04/2023 | 15 | W.B.S.E.D.C.LTD | 0.56 | 0 | 0 | 0
1430 | UTTAR DINAJPUR | Raiganj Division | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12103 | New | Implementation of KHATSA and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 73/RD/PHE | 16/01/2023 | 725 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 464.26 | 0 | 0 | 53
1431 | UTTAR DINAJPUR | Malda Mechanical | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12103 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Khatsa Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012769) | 1133/MLMD | 26/06/2023 | 811 | MANIK CHANDRA SAHA. | 25.28 | 0 | 0 | 90
1432 | UTTAR DINAJPUR | Raiganj Division | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12103 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KHATSA Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 583/RD/PHE | 05/03/2024 | 45 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 22.58 | 0 | 0 | 100
1433 | UTTAR DINAJPUR | Raiganj Division | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12103 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Khatsa PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3738/RD/PHE | 18/12/2024 | 90 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 9.83 | 0 | 0 | 0
1434 | UTTAR DINAJPUR | Raiganj Division | KHATSA Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12103 | New | Trial Run For Khatsa PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | 518/RD/PHE | 12/02/2025 | 90 | M/S P.S. ENTERPRISE | 0.88 | 0 | 0 | 0
1435 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Jaingaon Piped Water Supply Scheme under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12652 | Augmentation | Material Requisition To Resource Division | 2390/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.48 | 0 | 0 | 0
1436 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Jaingaon Piped Water Supply Scheme under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12652 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Jaingaon, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-436 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.19 | 0 | 0 | 0
1437 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Jaingaon Piped Water Supply Scheme under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12652 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Jaingaon Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1923/RD/PHE | 28/10/2022 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 33.25 | 0 | 0 | 70
1438 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Jaingaon Piped Water Supply Scheme under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12652 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Jaingaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015252) | 2801/MLMD | 17/08/2023 | 502 | M/S SABANA CONSTRUCTION | 10.9 | 0 | 0 | 100
1439 | UTTAR DINAJPUR | Malda Mechanical | DURGAPUR Piped Water Supply Scheme at Islampur Block , SM/12087 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Durgapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014156) | 2212/MLMD | 18/07/2023 | 120 | SUNRISE ENGINEERING CORPORATION. | 25.3 | 0 | 0 | 0
1440 | UTTAR DINAJPUR | Malda Mechanical | DURGAPUR Piped Water Supply Scheme at Islampur Block , SM/12087 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of DURGAPUR, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003226066 | 08/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.38 | 0 | 0 | 100
1441 | UTTAR DINAJPUR | Malda Mechanical | DURGAPUR Piped Water Supply Scheme at Islampur Block , SM/12087 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.II of DURGAPUR, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003226068 | 08/09/2023 | 90 | W.B.S.E.D.C.LTD | 8.15 | 0 | 0 | 100
1442 | UTTAR DINAJPUR | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block , SM/12087 | New | Material Requisition To Resource Division | 601/RD/PHE | 27/02/2023 | 0 | Resource Division | 20.57 | 0 | 0 | 0
1443 | UTTAR DINAJPUR | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block , SM/12087 | New | Protection and Restoration work of damaged flank caused by excavation for water supply project of PHE of Matikunda- Moragoti Road under uttar dinajpur division, PWD. | BP-2023-24-143 | 30/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, UTTAR DINAJPUR | 9.23 | 0 | 0 | 0
1444 | UTTAR DINAJPUR | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block , SM/12087 | New | Additional pipeline and other ancillary works at Durgapur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | 3481/RD/PHE | 02/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 22 | 0 | 0 | 0
1445 | UTTAR DINAJPUR | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block , SM/12087 | New | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for Durgapur Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | 3482/RD/PHE | 02/12/2024 | 30 | SHANKAR SAHA | 9.25 | 0 | 0 | 0
1446 | UTTAR DINAJPUR | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block , SM/12087 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DURGAPUR Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 593/RD/PHE | 05/03/2024 | 45 | M/S LUCKY CONSTRUCTION | 22.58 | 0 | 0 | 0
1447 | UTTAR DINAJPUR | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block , SM/12087 | New | Implementation of DURGAPUR and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work,2nd & 3rd Tube Well.) | 550/RD/PHE | 23/02/2023 | 960 | UJJWAL DAS NAMEDUTTA@GMAIL.COM | 341.08 | 0 | 0 | 38
1448 | UTTAR DINAJPUR | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block , SM/12087 | New | Providing FHTC in connection with Durgapur Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 53/RD/PHE | 03/01/2025 | 45 | APEX ENTERPRISES | 5.59 | 0 | 0 | 0
1449 | UTTAR DINAJPUR | Raiganj Division | DURGAPUR Piped Water Supply Scheme at Islampur Block , SM/12087 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Durgapur Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | 1815/RD/PHE | 24/06/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.35 | 0 | 0 | 0
1450 | UTTAR DINAJPUR | Malda Mechanical | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13717 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of DHANTOLA, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003229554 | 13/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.14 | 0 | 0 | 100
1451 | UTTAR DINAJPUR | Raiganj Division | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13717 | New | Material Requisition To Resource Division | 603/RD/PHE | 27/02/2023 | 0 | Resource Division | 109 | 0 | 0 | 0
1452 | UTTAR DINAJPUR | Malda Mechanical | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13717 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Dhantola Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014170) | 2494/MLMD | 04/08/2023 | 937 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD.. | 42.27 | 0 | 0 | 58
1453 | UTTAR DINAJPUR | Raiganj Division | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13717 | New | Construction of Boundary Wall with Gate at Head Work Site, 2nd & 3rd Tube-Well Site under DHANTOLA Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 564/RD/PHE | 05/03/2024 | 180 | M/S CAMELLIA CONSTRUCTION AND CO. | 27.65 | 0 | 0 | 100
1454 | UTTAR DINAJPUR | Raiganj Division | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13717 | New | Implementation of DHANTALA and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line,Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd & 3rdTube Well.) | 674/RD/PHE | 06/03/2023 | 757 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 840.35 | 0 | 0 | 6
1455 | UTTAR DINAJPUR | Raiganj Division | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13717 | New | Construction Of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Dhantola PWSS at Islampur Block under Raiganj Division, PHE dte. | 2894/RD/PHE | 25/09/2024 | 20 | SHANKAR SAHA | 4.31 | 0 | 0 | 0
1456 | UTTAR DINAJPUR | Raiganj Division | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13717 | New | Providing FHTC in connection with Dhantaola Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 52/RD/PHE | 03/01/2025 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 8.23 | 0 | 0 | 0
1457 | UTTAR DINAJPUR | Raiganj Division | DHANTOLA PIPED WATER SUPPLY SCHEME AT ISLAMPUR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13717 | New | Laying of Additional pipeline with other ancillary works at different mouzas of DHANTALA PWSS under Islampur Sub-Division P.H.E. Dte. | 3491/RD/PHE | 02/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 55.01 | 0 | 0 | 0
1458 | UTTAR DINAJPUR | Raiganj Division | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12790 | New | Material Requisition To Resource Division | 1204/RD/PHE | 28/04/2023 | 0 | Resource Division | 2.69 | 0 | 0 | 0
1459 | UTTAR DINAJPUR | Malda Mechanical | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12790 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of PHARABARI , Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-392 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 18.12 | 0 | 0 | 0
1460 | UTTAR DINAJPUR | Raiganj Division | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12790 | New | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 16.08.2024 & 20.08.2024. | BP-2024-25-224 | 04/10/2024 | 0 | SAHA CONSTRUCTION | 0.06 | 0 | 0 | 0
1461 | UTTAR DINAJPUR | Malda Mechanical | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12790 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Pharabari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014703) | 3707/MLMD | 29/11/2023 | 540 | SOVON KUMAR DAS. | 11.98 | 0 | 0 | 100
1462 | UTTAR DINAJPUR | Raiganj Division | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12790 | New | Implementation of Pharabari and it's adjoining mouzas Pipe Water Supply Scheme at Goalpokhar-I Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House at Head Work Site.) | 536/RD/PHE | 22/02/2023 | 591 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 43.62 | 0 | 0 | 100
1463 | UTTAR DINAJPUR | Raiganj Division | PHARABARI Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12790 | New | Construction of Boundary Wall With Gate at Head Work Site Tube-Well Site under PHARABARI PWSS at Goalpokhar-I Block under Raiganj Division, PHE Dte. | 605/RD/PHE | 05/03/2024 | 90 | HAQUE CONSTRUCTION | 5.13 | 0 | 0 | 100
1464 | UTTAR DINAJPUR | Raiganj Division | BALARAMPUR PIPED WATER SUPPLY SCHEME , SM/13520 | New | Material Requisition To Resource Division | 968/RD/PHE | 29/03/2023 | 0 | Resource Division | 21.22 | 0 | 0 | 0
1465 | UTTAR DINAJPUR | Malda Mechanical | BALARAMPUR PIPED WATER SUPPLY SCHEME , SM/13520 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Balarampur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015266) | 2477/MLMD | 04/08/2023 | 953 | DAS CONSTRUCTION | 27.47 | 0 | 0 | 73
1466 | UTTAR DINAJPUR | Malda Mechanical | BALARAMPUR PIPED WATER SUPPLY SCHEME , SM/13520 | New | Quotation for new service connection at BALARAMPUR PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/13520) | BP-2024-25-302 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 8.41 | 0 | 0 | 0
1467 | UTTAR DINAJPUR | Malda Mechanical | BALARAMPUR PIPED WATER SUPPLY SCHEME , SM/13520 | New | Quotation for new service connection at BALARAMPUR PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/13520) | BP-2024-25-303 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 4.39 | 0 | 0 | 0
1468 | UTTAR DINAJPUR | Raiganj Division | BALARAMPUR PIPED WATER SUPPLY SCHEME , SM/13520 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
1469 | UTTAR DINAJPUR | Raiganj Division | BALARAMPUR PIPED WATER SUPPLY SCHEME , SM/13520 | New | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at BALRAMPUR PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | 1207/RD/PHE | 25/04/2025 | 45 | M/S PIONEER ENTERPRISE | 40.01 | 0 | 0 | 0
1470 | UTTAR DINAJPUR | Raiganj Division | BALARAMPUR PIPED WATER SUPPLY SCHEME , SM/13520 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Balrampur Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 35 M3/hr. | 1993/RD/PHE | 07/07/2025 | 180 | MONDAL PRECISION PRIVATE LIMITED | 18.03 | 0 | 0 | 0
1471 | UTTAR DINAJPUR | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14641 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 0 | 100
1472 | UTTAR DINAJPUR | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14641 | New | Material Requisition To Resource Division | 2231/RD/PHE | 01/08/2023 | 0 | Resource Division | 40.65 | 0 | 0 | 0
1473 | UTTAR DINAJPUR | Malda Mechanical | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14641 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no- I,II & Making compound yard lighting arrangement at T/W no- I of CHANDIGRAM Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016709) | 2799/MLMD | 17/08/2023 | 180 | SHREE BISHNU CONSTRUCTION | 25.79 | 0 | 0 | 77
1474 | UTTAR DINAJPUR | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14641 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under CHANDIGRAM PWSS at Itahar Block under Raiganj Division, PHE Dte. | 622/RD/PHE | 05/03/2024 | 285 | MITALI CONSTRUCTION | 24.47 | 0 | 0 | 60
1475 | UTTAR DINAJPUR | Malda Mechanical | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14641 | New | Quotation for new service connection at Chandigram PH-I (Itahar ccc) | BP-2023-24-536 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 3.63 | 0 | 0 | 0
1476 | UTTAR DINAJPUR | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14641 | New | Implementation of CHANDIGRAM and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 568/RD/PHE | 23/02/2023 | 1276 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 381.9 | 0 | 0 | 40
1477 | UTTAR DINAJPUR | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14641 | New | Construction of Approach Road,Laying of Pipe Line,Fhtc And other Allied Works of Chandigram Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3562/RD/PHE | 05/12/2024 | 91 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 80.89 | 0 | 0 | 0
1478 | UTTAR DINAJPUR | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14641 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chandigram Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 50 M3/hr. | 1657/RD/PHE | 23/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 20.73 | 0 | 0 | 0
1479 | UTTAR DINAJPUR | Raiganj Division | Chandigram Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14641 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
1480 | UTTAR DINAJPUR | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14642 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 0 | 100
1481 | UTTAR DINAJPUR | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14642 | New | Material Requisition To Resource Division | 2251/RD/PHE | 03/08/2023 | 0 | Resource Division | 38.67 | 0 | 0 | 0
1482 | UTTAR DINAJPUR | Malda Mechanical | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14642 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no- I,II & Making compound yard lighting arrangement at T/W no- I of BASRATPUR Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016824) | 2438/MLMD | 04/08/2023 | 907 | HANNAN BUILDERS PVT. LTD. | 25.52 | 0 | 0 | 72
1483 | UTTAR DINAJPUR | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14642 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 20.05.2024 to 22.05.2024 and 24.05.2024. | BP-2024-25-95 | 28/06/2024 | 0 | M/S DILWAR HOSAIN | 0.07 | 0 | 0 | 0
1484 | UTTAR DINAJPUR | Malda Mechanical | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14642 | New | Quotation for new service connection at BASRATPUR PH-I (Itahar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2023-24-690 | 15/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.89 | 0 | 0 | 0
1485 | UTTAR DINAJPUR | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14642 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 27.05.2024 to 31.05.2024. | BP-2024-25-96 | 28/06/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
1486 | UTTAR DINAJPUR | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14642 | New | Implementation of BASRATPUR and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 566/RD/PHE | 23/02/2023 | 910 | M/S LOKENATH CONSTRUCTION | 352.8 | 0 | 0 | 20
1487 | UTTAR DINAJPUR | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14642 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BASRATPUR PWSS at Itahar Block under Raiganj Division, PHE Dte. | 617/RD/PHE | 05/03/2024 | 451 | M/S UNIQUE 13 | 11.28 | 0 | 0 | 40
1488 | UTTAR DINAJPUR | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14642 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BASRATPUR PWSS at Itahar Block under Raiganj Division, PHE Dte. | 618/RD/PHE | 05/03/2024 | 406 | M/S PINKI CONSTRUCTION | 11.28 | 0 | 0 | 40
1489 | UTTAR DINAJPUR | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14642 | New | Construction of Approach Road, Laying of Pipe Line, FHTC And Other allied Works of Basratpur PWSS Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3558/RD/PHE | 05/12/2024 | 91 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 78.8 | 0 | 0 | 0
1490 | UTTAR DINAJPUR | Raiganj Division | Basratpur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/14642 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Basratpur Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | 2477/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 18.73 | 0 | 0 | 0
1491 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14145 | New | Construction of Boundary Wall and Pump House at 2nd Tube-Well with providing Functional House hold Tap Connection of DAKHSHIN GOALPARA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 821/RD/PHE | 22/03/2023 | 60 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 39.84 | 0 | 0 | 0
1492 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14145 | New | Material Requisition To Resource Division | 1570/RD/PHE | 31/05/2023 | 0 | Resource Division | 43.02 | 0 | 0 | 0
1493 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14145 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Dakshin Goalpara, 2. Bhattagidighi, 3. Maharajpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 540/RD/PHE | 22/02/2023 | 630 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 0 | 80
1494 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14145 | New | Providing FHTC with laying distribution of pipe line at village Taherpur of DAKHSHIN GOALPARA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 759/RD/PHE | 16/03/2023 | 750 | M/S JHA CONSTRUCTION | 91.73 | 0 | 0 | 50
1495 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14145 | New | Implementation of DAKHSHIN GOALPARA andit's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ BLOCK of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1271/RD/PHE | 08/05/2023 | 700 | PRASANTA DUTTA | 206.31 | 0 | 0 | 50
1496 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14145 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Dakshin Goalpara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018225) | 2490/MLMD | 04/08/2023 | 907 | M/S TRILOCHAN CONSTRUCTION CO. | 25.28 | 0 | 0 | 0
1497 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14145 | New | pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Dakshin Goalpara PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 18/RD/PHE | 02/01/2025 | 30 | M/S JHA CONSTRUCTION | 18.16 | 0 | 0 | 0
1498 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14145 | New | Laying distribution of pipe Line and Providing FHTC at Village Dakhin Goal Para of DAKHSHIN GOALPARA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 854/RD/PHE | 24/03/2023 | 760 | M/S AMIT KUMAR GUPTA | 85.53 | 0 | 0 | 80
1499 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN GOALPARA PIPED WATER SUPPLY SCHEME AT RAIGANJ BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14145 | New | Laying of pipe line at Naopara of DAKHSHIN GOALPARA PWSS at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 815/RD/PHE | 22/03/2023 | 45 | M/S P.S. ENTERPRISE | 50.51 | 0 | 0 | 100
1500 | UTTAR DINAJPUR | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | Material Requisition To Resource Division | 2178/RD/PHE | 12/12/2022 | 0 | Resource Division | 55.82 | 0 | 0 | 0
1501 | UTTAR DINAJPUR | Malda Mechanical | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Atghara PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003202769 | 03/08/2023 | 90 | W.B.S.E.D.C.LTD | 5.71 | 0 | 0 | 100
1502 | UTTAR DINAJPUR | Malda Mechanical | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.III of Atghara, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003202782 | 08/08/2023 | 90 | W.B.S.E.D.C.LTD | 5.13 | 0 | 0 | 100
1503 | UTTAR DINAJPUR | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | Implementation of ATGHARA and it's adjoining mouzas Pipe Water Supply Scheme at Kaliyaganj Block of Uttar Dinajpur District under Raiganj Division. | 290/RD/PHE | 01/02/2023 | 1065 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 892 | 0 | 0 | 60
1504 | UTTAR DINAJPUR | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | Approach road with land development of headwork site & 2nd tubewell site and road restoration of Atghara PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3776/RD/PHE | 19/12/2024 | 45 | M/S P.S. ENTERPRISE | 12.46 | 0 | 0 | 0
1505 | UTTAR DINAJPUR | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under ATGHARA Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 565/RD/PHE | 05/03/2024 | 165 | M/S P.S. ENTERPRISE | 27.93 | 0 | 0 | 25
1506 | UTTAR DINAJPUR | Malda Mechanical | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of ATGHARA PWSS ,Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-475 | 26/01/2024 | 0 | W.B.S.E.D.C.LTD | 11.12 | 0 | 0 | 0
1507 | UTTAR DINAJPUR | Malda Mechanical | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | Additional Quotation of TW-II of Ataghara water supply scheme in the district if Uttar Dinajpur. | BP-2024-25-457 | 23/08/2024 | 0 | W.B.S.E.D.C.LTD | 6.67 | 0 | 0 | 0
1508 | UTTAR DINAJPUR | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | Requisition of fund regarding payment for permanent restoration of rural roads damaged due to laying of pipeline by PHE Dte. as on 24.09.2024 i.c.w L026-FATEPUR to PURBA SANKARPUR (Package No. WB15301: Under DLP), under coverage of Atghara PWSS (SM/13796) | BP-2024-25-275 | 08/10/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 1.98 | 0 | 0 | 0
1509 | UTTAR DINAJPUR | Malda Mechanical | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | Additional Quotation charge at TW No- I of Ataghara, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-17 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 1.04 | 0 | 0 | 0
1510 | UTTAR DINAJPUR | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
1511 | UTTAR DINAJPUR | Malda Mechanical | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I, II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Ataghara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012590) | 2652/MLMD | 10/08/2023 | 901 | SUBRATA SAHA | 37.17 | 0 | 0 | 92
1512 | UTTAR DINAJPUR | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month(Period from 01.07.2023 to 30.06.2024). | 1722/RD/PHE | 28/06/2023 | 366 | DEBASISH GHOSH | 4.8 | 0 | 0 | 0
1513 | UTTAR DINAJPUR | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | Trial Run For Atghara PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | 528/RD/PHE | 12/02/2025 | 90 | AJIT PRAMANIK | 0.88 | 0 | 0 | 0
1514 | UTTAR DINAJPUR | Raiganj Division | ATGHARA PIPED WATER SUPPLY SCHEME , SM/13796 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Atghara Water Supply Scheme at Kaliaganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 100 M3/hr. | 1620/RD/PHE | 19/06/2025 | 180 | AJIT PRAMANIK | 36.38 | 0 | 0 | 0
1515 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Debiganj Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14229 | Augmentation | Rig Bored Tube-Well In connection with Source Augmentation In Different Piped Water Supply Scheme 1.Debiganj, 2.Gunabari, 3. Majlishpur. 4. Sripur in the District of Uttar Dinajpur Under Raiganj Division, P.H.E. Dte. | 470/RD/PHE | 16/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI | 42.57 | 0 | 0 | 100
1516 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Debiganj Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14229 | Augmentation | Material Requisition To Resource Division | 2397/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.4 | 0 | 0 | 0
1517 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Debiganj Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14229 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Debiganj Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016478) | 2485/MLMD | 04/08/2023 | 120 | S.G.ENTERPRISE | 10.89 | 0 | 0 | 84
1518 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Debiganj Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14229 | Augmentation | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Debiganj Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 57/RD/PHE | 16/01/2023 | 45 | SUBHASIS MAJUMDER SUBHASIS@REDIFFMAIL.COM | 17.69 | 0 | 0 | 98
1519 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Debiganj Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14229 | Augmentation | Land development at 3rd Pump House (Source Augmentation) site for Debiganj Piped Water Supply Scheme under Islampur Sub-Division under Raiganj Division, PHE Dte., Uttar Dinajpur. | 1701/RD/PHE | 10/06/2024 | 30 | HAQUE CONSTRUCTION | 1.5 | 0 | 0 | 100
1520 | UTTAR DINAJPUR | Raiganj Division | BASATPUT Piped Water Supply Scheme , SM/15129 | New | Material Requisition To Resource Division | 978/RD/PHE | 30/03/2023 | 0 | Resource Division | 48.44 | 0 | 0 | 0
1521 | UTTAR DINAJPUR | Malda Mechanical | BASATPUT Piped Water Supply Scheme , SM/15129 | New | Quotation for new service connection at BASATPUR PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15129) | BP-2024-25-568 | 14/11/2024 | 0 | W.B.S.E.D.C.LTD | 14.54 | 0 | 0 | 0
1522 | UTTAR DINAJPUR | Raiganj Division | BASATPUT Piped Water Supply Scheme , SM/15129 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
1523 | UTTAR DINAJPUR | Malda Mechanical | BASATPUT Piped Water Supply Scheme , SM/15129 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Basatpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016384) | 99/MLMD | 11/01/2024 | 717 | DIPALI CONSTRUCTION. | 29.09 | 0 | 0 | 0
1524 | UTTAR DINAJPUR | Raiganj Division | BASATPUT Piped Water Supply Scheme , SM/15129 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
1525 | UTTAR DINAJPUR | Raiganj Division | BASATPUT Piped Water Supply Scheme , SM/15129 | New | Additional pipeline and other ancillary works at Basatpur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | 2363/RD/PHE | 25/08/2025 | 45 | MILAN GHOSH | 67.94 | 0 | 0 | 0
1526 | UTTAR DINAJPUR | Raiganj Division | BASATPUT Piped Water Supply Scheme , SM/15129 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Basatpur Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | 1809/RD/PHE | 24/06/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 33.59 | 0 | 0 | 0
1527 | UTTAR DINAJPUR | Raiganj Division | ATHIALA PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15215 | New | Material Requisition To Resource Division | 963/RD/PHE | 29/03/2023 | 0 | Resource Division | 32.29 | 0 | 0 | 0
1528 | UTTAR DINAJPUR | Malda Mechanical | ATHIALA PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15215 | New | Quotation for new service connection at ATHIALA PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15215) | BP-2024-25-298 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 6.8 | 0 | 0 | 0
1529 | UTTAR DINAJPUR | Malda Mechanical | ATHIALA PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15215 | New | Quotation for new service connection at ATHIALA PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15215) | BP-2024-25-297 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 5.67 | 0 | 0 | 0
1530 | UTTAR DINAJPUR | Malda Mechanical | ATHIALA PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15215 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Athiala(Chopra Block) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018130) | 2643/MLMD | 10/08/2023 | 630 | ANIMA ENTERPRISE | 27.45 | 0 | 0 | 100
1531 | UTTAR DINAJPUR | Raiganj Division | ATHIALA PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15215 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
1532 | UTTAR DINAJPUR | Raiganj Division | ATHIALA PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15215 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at ATHIALA PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | 1205/RD/PHE | 25/04/2025 | 45 | MD HAKIMUDDIN | 69.94 | 0 | 0 | 0
1533 | UTTAR DINAJPUR | Raiganj Division | ATHIALA PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15215 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Athiala Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | 1985/RD/PHE | 04/07/2025 | 180 | MONDAL PRECISION PRIVATE LIMITED | 30.95 | 0 | 0 | 0
1534 | UTTAR DINAJPUR | Raiganj Division | BANGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-I UNDER UTTAR DINAJPUR DISTRICT. , SM/16471 | New | Material Requisition To Resource Division | 2270/RD | 03/08/2023 | 0 | Resource Division | 23.83 | 0 | 0 | 0
1535 | UTTAR DINAJPUR | Malda Mechanical | BANGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-I UNDER UTTAR DINAJPUR DISTRICT. , SM/16471 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bangaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015388) | 2475/MLMD | 04/08/2023 | 907 | DILIP MAHATO. | 26.3 | 0 | 0 | 72
1536 | UTTAR DINAJPUR | Raiganj Division | BANGAON PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-I UNDER UTTAR DINAJPUR DISTRICT. , SM/16471 | New | Construction Of OHR at Bangaon Pipe Water Supply Scheme at Goalpokhar-I Block of Uttar Dinajpur District under Raiganj Division. | 3288/RD/PHE | 20/11/2024 | 45 | VISCOUS ENGINEERS PVT. LTD. | 71.86 | 0 | 0 | 0
1537 | UTTAR DINAJPUR | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16221 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 0 | 100
1538 | UTTAR DINAJPUR | Malda Mechanical | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16221 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Sonapur, Itahar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003233398 | 22/09/2023 | 90 | W.B.S.E.D.C.LTD | 5.12 | 0 | 0 | 100
1539 | UTTAR DINAJPUR | Malda Mechanical | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16221 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Sonapur, Itahar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003233395 | 22/09/2023 | 90 | W.B.S.E.D.C.LTD | 9.43 | 0 | 0 | 100
1540 | UTTAR DINAJPUR | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16221 | New | Material Requisition To Resource Division | 1569/RD/PHE | 31/05/2023 | 0 | Resource Division | 22.31 | 0 | 0 | 0
1541 | UTTAR DINAJPUR | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16221 | New | Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of L039-PURBADURLAVPUR TO UTTAR MAHESHPUR (Package No. WB15303 : Under DLP) caused due to pipe laying by PHED under Sonapur PWSS at different stretched of road under WBSRDA Uttar Dinajpur Division. | BP-2024-25-273 | 08/10/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 0.9 | 0 | 0 | 0
1542 | UTTAR DINAJPUR | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16221 | New | Implementation of SONAPUR and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1273/RD/PHE | 08/05/2023 | 270 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 362.18 | 0 | 0 | 50
1543 | UTTAR DINAJPUR | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16221 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
1544 | UTTAR DINAJPUR | Malda Mechanical | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16221 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound yard lighting arrangement at T/W no. I of Sonapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2945/MLMD | 11/09/2024 | 473 | MANIK CHANDRA SAHA. | 26.45 | 0 | 0 | 70
1545 | UTTAR DINAJPUR | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16221 | New | Construction Of Approach Road, Laying of Pipe Line,Fhtc and Other Allied Works Of Sonapur Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3565/RD/PHE | 05/12/2024 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 76.02 | 0 | 0 | 0
1546 | UTTAR DINAJPUR | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16221 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SONAPUR PWSS at Itahar Block under Raiganj Division, PHE Dte. | 629/RD/PHE | 05/03/2024 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 22.58 | 0 | 0 | 0
1547 | UTTAR DINAJPUR | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16221 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12 months (Period from 17.10.2023 to 16.10.2024) | 2876/RD/PHE | 17/10/2023 | 366 | ARNAB DUTTA | 4.8 | 0 | 0 | 100
1548 | UTTAR DINAJPUR | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16221 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Sonapur Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity- 40 M3/hr. | 2474/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 18.73 | 0 | 0 | 0
1549 | UTTAR DINAJPUR | Raiganj Division | Sonapur Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/16221 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
1550 | UTTAR DINAJPUR | Raiganj Division | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16222 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
1551 | UTTAR DINAJPUR | Malda Mechanical | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16222 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Bahala (Zone-I) PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003279110 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 5.13 | 0 | 0 | 100
1552 | UTTAR DINAJPUR | Malda Mechanical | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16222 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Bahala (Zone-I) PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003279099 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 8.75 | 0 | 0 | 100
1553 | UTTAR DINAJPUR | Raiganj Division | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16222 | New | Material Requisition To Resource Division | 2240/RD/PHE | 02/08/2023 | 0 | Resource Division | 22.87 | 0 | 0 | 0
1554 | UTTAR DINAJPUR | Raiganj Division | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16222 | New | Implementation of BAHALA ZONE-I and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1277/RD/PHE | 08/05/2023 | 969 | BHOLA PAUL | 310.32 | 0 | 0 | 30
1555 | UTTAR DINAJPUR | Malda Mechanical | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16222 | New | Additional quotation of Bahala Zone-I PWSS TW-I in the district of Uttar Dinajpur. | BP-2024-25-438 | 20/08/2024 | 0 | W.B.S.E.D.C.LTD | 5.27 | 0 | 0 | 0
1556 | UTTAR DINAJPUR | Malda Mechanical | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16222 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Bahala Zone- I Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018495) | 2728/MLMD | 14/08/2023 | 888 | S PATHAK & CO. | 24.05 | 0 | 0 | 88
1557 | UTTAR DINAJPUR | Raiganj Division | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16222 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | 1746/RD/PHE | 14/06/2024 | 198 | DEBASISH GHOSH | 2.6 | 0 | 0 | 0
1558 | UTTAR DINAJPUR | Raiganj Division | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16222 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
1559 | UTTAR DINAJPUR | Raiganj Division | Bahala Zone-I Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16222 | New | Balance distribution System Of Laying pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAHALA ZONE-I PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 636/RD/PHE | 05/03/2024 | 45 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 22.72 | 0 | 0 | 100
1560 | UTTAR DINAJPUR | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/16536 | New | Preparation & Submission of DPR for Proposed Bagela Piped Water Supply Scheme under Karandighi Development Block (sl no-I). | 603/RD/PHE | 15/03/2022 | 7 | M/S SOBHA & CO. | 8.6 | 0 | 0 | 0
1561 | UTTAR DINAJPUR | Malda Mechanical | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/16536 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Bagela,Dalkhola C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003196575 | 20/07/2023 | 90 | W.B.S.E.D.C.LTD | 8.06 | 0 | 0 | 100
1562 | UTTAR DINAJPUR | Malda Mechanical | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/16536 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Bagela,Dalkhola C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003196562 | 20/07/2023 | 90 | W.B.S.E.D.C.LTD | 6.84 | 0 | 0 | 100
1563 | UTTAR DINAJPUR | Malda Mechanical | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/16536 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Bagela,Dalkhola C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003196566 | 20/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.57 | 0 | 0 | 100
1564 | UTTAR DINAJPUR | Malda Mechanical | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/16536 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. IV of Bagela,Dalkhola C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003196570 | 20/07/2023 | 90 | W.B.S.E.D.C.LTD | 6.94 | 0 | 0 | 100
1565 | UTTAR DINAJPUR | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/16536 | New | Material Requisition To Resource Division | 1219/RD/PHE | 02/05/2023 | 0 | Resource Division | 258.85 | 0 | 0 | 0
1566 | UTTAR DINAJPUR | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/16536 | New | Laying of Additional Pipeline, Pathway and Land development with anciliary works for installation of FHTC Work for BAGELA Water Supply Scheme under Islampur Sub-Division P.H.E. Dte.under Raiganj Division, P.H.E Dte.,U/D. | 3777/RD/PHE | 19/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 59.67 | 0 | 0 | 0
1567 | UTTAR DINAJPUR | Malda Mechanical | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/16536 | New | Additional quotation for HT cable at BAGELA PH-I (Dalkhola ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2023-24-696 | 15/03/2024 | 0 | W.B.S.E.D.C.LTD | 14.8 | 0 | 0 | 0
1568 | UTTAR DINAJPUR | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/16536 | New | Implementation of BAGELA andit's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1068/RD/PHE | 11/04/2023 | 731 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 647.26 | 0 | 0 | 75
1569 | UTTAR DINAJPUR | Malda Mechanical | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/16536 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II,III,IV & V and making compound lighting arrangement ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Bagela Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015098) | 2726/MLMD | 14/08/2023 | 2005 | GHOSH BROTHERS... | 68.76 | 0 | 0 | 79
1570 | UTTAR DINAJPUR | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/16536 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd, 3rd & 4th Tube-Well Site under BAGELA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 602/RD/PHE | 05/03/2024 | 138 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 16.43 | 0 | 0 | 0
1571 | UTTAR DINAJPUR | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/16536 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd, 3rd & 4th Tube-Well Site under BAGELA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 601/RD/PHE | 05/03/2024 | 138 | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 16.43 | 0 | 0 | 0
1572 | UTTAR DINAJPUR | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/16536 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bagela Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 150 M3/hr. | 2483/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 51.99 | 0 | 0 | 0
1573 | UTTAR DINAJPUR | Raiganj Division | Bagela Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/16536 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
1574 | UTTAR DINAJPUR | Raiganj Division | Palaibari Piped Water Supply Scheme. , SM/18181 | New | Material Requisition To Resource Division | 1331/RD/PHE | 15/05/2023 | 0 | Resource Division | 44.22 | 0 | 0 | 0
1575 | UTTAR DINAJPUR | Raiganj Division | Palaibari Piped Water Supply Scheme. , SM/18181 | New | Implementation of PALAIBARI and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1128/RD/PHE | 24/04/2023 | 977 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 555.91 | 0 | 0 | 50
1576 | UTTAR DINAJPUR | Malda Mechanical | Palaibari Piped Water Supply Scheme. , SM/18181 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no.I, II & III and making compound lighting arrangement at T/W no.I of PALAIBARI Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 813/MLMD | 15/02/2024 | 180 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 40.02 | 0 | 0 | 83
1577 | UTTAR DINAJPUR | Raiganj Division | Palaibari Piped Water Supply Scheme. , SM/18181 | New | Balance work of sinking Rig bored Tube-Well in connection with 2nd and 3rd Tube-Well site due to non-availability of water at the shallow depth of Tube-Well under Palaibari PWSS(New Scheme) at Itahar Block, Raiganj Division ,PHE Dte. | 3025/RD/PHE | 03/10/2024 | 30 | M/S SARKAR ENTERPRISE SILIGURI | 18.33 | 0 | 0 | 0
1578 | UTTAR DINAJPUR | Raiganj Division | Palaibari Piped Water Supply Scheme. , SM/18181 | New | Arrangement for erection of display board for different piped water supply schemes (1.Palaibari PWSS, 2.Bhomra PWSS, 3.Chandgaon PWSS) under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | BP-2024-25-271 | 07/10/2024 | 0 | M/S MANDAL ENTERPRISE | 0.1 | 0 | 0 | 0
1579 | UTTAR DINAJPUR | Raiganj Division | Palaibari Piped Water Supply Scheme. , SM/18181 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Palaibari, 2.Kashimpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 1491/RD/PHE | 17/05/2023 | 675 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 57.19 | 0 | 0 | 80
1580 | UTTAR DINAJPUR | Raiganj Division | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18148 | New | Material Requisition To Resource Division | 2266/RD/PHE | 03/08/2023 | 0 | Resource Division | 15.02 | 0 | 0 | 0
1581 | UTTAR DINAJPUR | Raiganj Division | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18148 | New | Implementation of DAKSHINAL and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2385/RD/PHE | 16/08/2023 | 840 | MILAN DEBNATH | 215.59 | 0 | 0 | 25
1582 | UTTAR DINAJPUR | Malda Mechanical | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18148 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. I & II of Dakshinal Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020903) | 4768/MLMD | 29/12/2023 | 720 | M/S S. S. ENTERPRISE | 21.07 | 0 | 0 | 84
1583 | UTTAR DINAJPUR | Raiganj Division | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18148 | New | Construction of Approach Road,Laying of Pipe Line,Fhtc and Other Allied Works Of Dakshinal Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3564/RD/PHE | 05/12/2024 | 252 | M/S. DEBNATH ENTERPRISE | 41.36 | 0 | 0 | 0
1584 | UTTAR DINAJPUR | Raiganj Division | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18148 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DAKSHINAL PWSS at Itahar Block under Raiganj Division, PHE Dte. | 624/RD/PHE | 05/03/2024 | 415 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. | 11.29 | 0 | 0 | 100
1585 | UTTAR DINAJPUR | Raiganj Division | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18148 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakshinal Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 30 M3/hr. | 2479/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 17.34 | 0 | 0 | 0
1586 | UTTAR DINAJPUR | Raiganj Division | DAKSHINAL PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18148 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DAKSHINAL PWSS at Itahar Block under Raiganj Division, PHE Dte. | 625/RD/PHE | 05/03/2024 | 412 | DULAL MAJUMDER | 11.29 | 0 | 0 | 100
1587 | UTTAR DINAJPUR | Malda Mechanical | DOHASO PWSS , SM/18304 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Dohaso, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003216769 | 24/08/2023 | 90 | W.B.S.E.D.C.LTD | 9.76 | 0 | 0 | 100
1588 | UTTAR DINAJPUR | Raiganj Division | DOHASO PWSS , SM/18304 | New | Material Requisition To Resource Division | 605/RD/PHE | 27/02/2023 | 0 | Resource Division | 93.61 | 0 | 0 | 0
1589 | UTTAR DINAJPUR | Raiganj Division | DOHASO PWSS , SM/18304 | New | ADDITIONAL LAYING OF UPVC PIPE LINE with anciliary works at DOHASO PWSS WITHIN ISLAMPUR BLOCK UNDER RAIGANJ DIVISION P.H.E. DTE., RAIGANJ, UTTAR DINAJPUR. | 3480/RD/PHE | 02/12/2024 | 45 | AJIT PRAMANIK | 81.53 | 0 | 0 | 0
1590 | UTTAR DINAJPUR | Malda Mechanical | DOHASO PWSS , SM/18304 | New | Quotation for new service connection at DOHASO PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-37 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 8.77 | 0 | 0 | 0
1591 | UTTAR DINAJPUR | Malda Mechanical | DOHASO PWSS , SM/18304 | New | Quotation for new service connection at DOHASO PH-III (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-38 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 7.61 | 0 | 0 | 0
1592 | UTTAR DINAJPUR | Raiganj Division | DOHASO PWSS , SM/18304 | New | Implementation of DOHASO and its adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2091/RD/PHE | 27/07/2023 | 889 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 1441.52 | 0 | 0 | 60
1593 | UTTAR DINAJPUR | Malda Mechanical | DOHASO PWSS , SM/18304 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Dohaso Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015576) | 2495/MLMD | 04/08/2023 | 937 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD.. | 42.58 | 0 | 0 | 58
1594 | UTTAR DINAJPUR | Raiganj Division | DOHASO PWSS , SM/18304 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under DOHASO PWSS at Islampur Block under Raiganj Division, PHE Dte. | 609/RD/PHE | 05/03/2024 | 225 | DIPAK SAHA | 13.85 | 0 | 0 | 100
1595 | UTTAR DINAJPUR | Raiganj Division | DOHASO PWSS , SM/18304 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under DOHASO PWSS at Islampur Block under Raiganj Division, PHE Dte. | 610/RD/PHE | 05/03/2024 | 225 | M/S ANTARA | 13.85 | 0 | 0 | 100
1596 | UTTAR DINAJPUR | Raiganj Division | IKARCHALA PWSS , SM/18294 | New | Material Requisition To Resource Division | 1202/RD/PHE | 28/04/2023 | 0 | Resource Division | 58.45 | 0 | 0 | 0
1597 | UTTAR DINAJPUR | Malda Mechanical | IKARCHALA PWSS , SM/18294 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Ikarchala (Zone - II) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014639) | 2696/MLMD | 11/08/2023 | 529 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 25.53 | 0 | 0 | 76
1598 | UTTAR DINAJPUR | Malda Mechanical | IKARCHALA PWSS , SM/18294 | New | Quotation for new service connection at IKARCHALA ZONE-II PH-I (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-68 | 15/04/2024 | 0 | W.B.S.E.D.C.LTD | 12.83 | 0 | 0 | 0
1599 | UTTAR DINAJPUR | Malda Mechanical | IKARCHALA PWSS , SM/18294 | New | Quotation for new service connection at IKARCHALA ZONE-I PH-II (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18294) | BP-2024-25-260 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 4.8 | 0 | 0 | 0
1600 | UTTAR DINAJPUR | Malda Mechanical | IKARCHALA PWSS , SM/18294 | New | Quotation for new service connection at IKARCHALA ZONE-II PH-II (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-67 | 15/04/2024 | 0 | W.B.S.E.D.C.LTD | 8.19 | 0 | 0 | 0
1601 | UTTAR DINAJPUR | Malda Mechanical | IKARCHALA PWSS , SM/18294 | New | Quotation for new service connection at IKARCHALA ZONE-I PH-I (Goalpokher ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18294) | BP-2024-25-261 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 14.56 | 0 | 0 | 0
1602 | UTTAR DINAJPUR | Malda Mechanical | IKARCHALA PWSS , SM/18294 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Ikarchala Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014639) | 2638/MLMD | 10/08/2023 | 978 | M/S D.G.B. ENTERPRISE. | 25.52 | 0 | 0 | 63
1603 | UTTAR DINAJPUR | Raiganj Division | IKARCHALA PWSS , SM/18294 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
1604 | UTTAR DINAJPUR | Raiganj Division | IKARCHALA PWSS , SM/18294 | New | Providing FHTC in connection with Ikarchala Zone-I & II Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 1180/RD/PHE | 23/04/2025 | 45 | HAQUE CONSTRUCTION | 38.77 | 0 | 0 | 0
1605 | UTTAR DINAJPUR | Raiganj Division | IKARCHALA PWSS , SM/18294 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Ikarchala Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | 1995/RD/PHE | 07/07/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.93 | 0 | 0 | 0
1606 | UTTAR DINAJPUR | Raiganj Division | IKARCHALA PWSS , SM/18294 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at IKARCHALA ZONE-I PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | 2044/RD/PHE | 09/07/2025 | 180 | GANGARAMPUR UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.29 | 0 | 0 | 0
1607 | UTTAR DINAJPUR | Raiganj Division | IKARCHALA PWSS , SM/18294 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at IKARCHALA ZONE-II PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | 2046/RD/PHE | 10/07/2025 | 180 | ROY ENGINEERS. (PATNA) | 32.95 | 0 | 0 | 0
1608 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17436 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
1609 | UTTAR DINAJPUR | Malda Mechanical | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17436 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Surangapur (Zone-II) PWSS, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003279058 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 17.09 | 0 | 0 | 100
1610 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17436 | New | Material Requisition To Resource Division | 2238/RD/PHE | 02/08/2023 | 0 | Resource Division | 24.57 | 0 | 0 | 0
1611 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17436 | New | Implementation of SURANGAPUR (ZONE-II) and its adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1279/RD/PHE | 08/05/2023 | 969 | SANYAL ENTERPRISE | 281.07 | 0 | 0 | 65
1612 | UTTAR DINAJPUR | Malda Mechanical | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17436 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Surangapur Zone- II Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018492) | 2771/MLMD | 14/08/2023 | 797 | PABITRA MANDAL | 24.23 | 0 | 0 | 88
1613 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17436 | New | Restoration of Damaged CC Road Near 2nd Tubewell Site of Surangapur Zone-II Water Supply Scheme (New Scheme) at Hemtabad Block Under Raiganj Division P.H.E Dte. | 3016/RD/PHE | 03/10/2024 | 20 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 3.24 | 0 | 0 | 0
1614 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17436 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SURANGAPUR ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 650/RD/PHE | 05/03/2024 | 45 | CHAITANYA SAMAL | 11.29 | 0 | 0 | 100
1615 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17436 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SURANGAPUR ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 649/RD/PHE | 05/03/2024 | 45 | SAHA CONSTRUCTION SAHAKUMARESH51@GMAIL.COM | 11.29 | 0 | 0 | 100
1616 | UTTAR DINAJPUR | Malda Mechanical | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17436 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Surangapur PWSS (Zone-II), Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-399 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 7.51 | 0 | 0 | 0
1617 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17436 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Surangapur Zone II PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 03/RD/PHE | 02/01/2025 | 45 | SANYAL ENTERPRISE | 42.37 | 0 | 0 | 0
1618 | UTTAR DINAJPUR | Raiganj Division | Surangapur Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17436 | New | Trial Run For Surangapur Zone-II PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 months | 531/RD/PHE | 12/02/2025 | 90 | SANYAL ENTERPRISE | 0.88 | 0 | 0 | 0
1619 | UTTAR DINAJPUR | Raiganj Division | JHITKAI PWSS , SM/18476 | New | Material Requisition To Resource Division | 1052/RD/PHE | 06/04/2023 | 0 | Resource Division | 74.65 | 0 | 0 | 0
1620 | UTTAR DINAJPUR | Malda Mechanical | JHITKAI PWSS , SM/18476 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Jhitkai, Birnagar CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-571 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 3.2 | 0 | 0 | 0
1621 | UTTAR DINAJPUR | Malda Mechanical | JHITKAI PWSS , SM/18476 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Jhitkai, Birnagar CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-396 | 29/07/2024 | 0 | W.B.S.E.D.C.LTD | 13.84 | 0 | 0 | 0
1622 | UTTAR DINAJPUR | Raiganj Division | JHITKAI PWSS , SM/18476 | New | Wayleave/ track crossing proposal with application ID : NFR-KIR-2024-WL-11 under Katihar Division of Northeast Frontier Railway in connection with Jhitkai PWSS in Raiganj Block under Raiganj Division PHE Dte. | BP-2024-25-69 | 06/06/2024 | 0 | EXECUTIVE ENGINEER | 0.11 | 0 | 0 | 0
1623 | UTTAR DINAJPUR | Raiganj Division | JHITKAI PWSS , SM/18476 | New | Way leave/track crossing proposal with application id: NFR-KIR-2024-WL-11 under Kathihar Division of North East Fronter Railway in connection with Jhitkia PWSS in Raiganj Block under Raiganj Division, PHE Dte. | BP-2024-25-104 | 09/07/2024 | 0 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 6.13 | 0 | 0 | 0
1624 | UTTAR DINAJPUR | Raiganj Division | JHITKAI PWSS , SM/18476 | New | Implementation of JHITKAI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte | 2294/RD/PHE | 04/08/2023 | 990 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 751.51 | 0 | 0 | 50
1625 | UTTAR DINAJPUR | Raiganj Division | JHITKAI PWSS , SM/18476 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Jhitkia, 2.Bhomra in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 2366/RD/PHE | 11/08/2023 | 540 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 0 | 100
1626 | UTTAR DINAJPUR | Malda Mechanical | JHITKAI PWSS , SM/18476 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I, II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Jhitkai Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018220) | 2508/MLMD | 04/08/2023 | 787 | GHOSH BROTHERS... | 37.06 | 0 | 0 | 83
1627 | UTTAR DINAJPUR | Raiganj Division | JHITKAI PWSS , SM/18476 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site, 2nd & 3rd tubewell site and road restoration of Jhitkai PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3742/RD/PHE | 18/12/2024 | 135 | BHOLA PAUL | 29.79 | 0 | 0 | 0
1628 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME , SM/15124 | Augmentation | Material Requisition To Resource Division | 721/RD/PHE | 15/03/2023 | 0 | Resource Division | 53.77 | 0 | 0 | 0
1629 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME , SM/15124 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Bhatol, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-213 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.07 | 0 | 0 | 0
1630 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME , SM/15124 | Augmentation | Additional Quotation for TW No-III of Bhatol water supply scheme in the district of Uttar Dinajpur. | BP-2024-25-545 | 01/10/2024 | 0 | W.B.S.E.D.C.LTD | 3.83 | 0 | 0 | 0
1631 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME , SM/15124 | Augmentation | Augmentation of Bhatol and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 553/RD/PHE | 23/02/2023 | 1131 | KAMIRUL SK & CO. | 502.82 | 0 | 0 | 5
1632 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME , SM/15124 | Augmentation | Supply, installation & commissioning of electro-mechanical components of T/W no. I & II and Supply, installation, commissioning, Trial operation T/W no-III and making compound lighting arrangement at Headwork site of Augmentation of Bhatol Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011426) | 3694/MLMD | 29/11/2023 | 655 | DEY ENTERPRISE.. | 34.56 | 0 | 0 | 62
1633 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME , SM/15124 | Augmentation | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bhatol PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. (2nd Call) | 2035/RD/PHE | 09/07/2025 | 180 | KAMIRUL SK & CO. | 46.67 | 0 | 0 | 0
1634 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION BHATOL PIPED WATER SUPPLY SCHEME , SM/15124 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bhatol Water Supply Scheme(Augmentation) at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | 1800/RD/PHE | 24/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 18.73 | 0 | 0 | 0
1635 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | Material Requisition To Resource Division | 2263/RD/PHE | 23/12/2022 | 0 | Resource Division | 116.35 | 0 | 0 | 0
1636 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | Construction of Over Head Reservoir(Capacity-700 Cum) of RAMGANJ(Zone-I) Pipe Water Supply Scheme in connection with Augmentation at Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 732/RD/PHE | 15/03/2023 | 365 | SOVAN KUMAR ROY | 231.74 | 0 | 0 | 0
1637 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | FHTC (Functional Household Tap Connection) for Ramganj Zone-I Water Supply Scheme [Augmentation Scheme] in Islampur Block Of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 758/RD/PHE | 17/03/2023 | 180 | PRASANTA DUTTA | 123.24 | 0 | 0 | 0
1638 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | Repairing for 2nd Pump House & Construction of Toilet at Ramganj Zone-I in connection with Augmentation of Ramganj (Zone-I) PWSS under Islampur Sub-Division under Raiganj Division, PHE Dte.. | 2053/RD/PHE | 19/07/2023 | 45 | MAA SHEETALA ENTERPRISE | 3.12 | 0 | 0 | 0
1639 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | Supply, installation & commissioning of electro-mechanical components at T/W no. I of Augmentation of Ramganj (Zone- I) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011646) | 2333/MLMD | 26/07/2023 | 90 | DEB CONSTRUCTION. | 12.27 | 0 | 0 | 0
1640 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | Making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Ramganj (Zone- I) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011646) | 2695/MLMD | 11/08/2023 | 1915 | PABITRA MANDAL | 10.51 | 0 | 0 | 0
1641 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | Construction of Pump House at Head Work site (5.40mx3.60m) of Ramganj Zone-I Piped Water Supply Scheme in connection with Augmentation of Ramganj Zone-I PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 1542/RD/PHE | 24/05/2023 | 60 | M/S ANTARA | 5.32 | 0 | 0 | 100
1642 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | Quotation for new service connection at RAMGANJ ZONE-I, PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-48 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 6.88 | 0 | 0 | 0
1643 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | Augmentation of RAMGANJ(Zone-I)Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | 2119/RD/PHE | 02/12/2022 | 850 | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 324.17 | 0 | 0 | 30
1644 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | Construction of Pump House at 3rd Tube Well site (5.40mx3.60m) of Ramganj Zone-I Piped Water Supply Scheme in connection with Augmentation of Ramganj Zone -I PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 1541/RD/PHE | 24/05/2023 | 547 | M/S ANTARA | 5.32 | 0 | 0 | 0
1645 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. II & III of Augmentation of Ramganj (Zone- I) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011646) | 2334/MLMD | 26/07/2023 | 840 | MANIK CHANDRA SAHA. | 24.71 | 0 | 0 | 94
1646 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
1647 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | Construction Of Boundary Wall With Gate at Head Work Site, & 2nd Tube-Well Site in connection with Augmentation Of Ramganj Zone-I PWSS at Chopra Block under Raiganj Division,PHE dte. | 3292/RD/PHE | 20/11/2024 | 45 | MAA SHEETALA ENTERPRISE | 27.18 | 0 | 0 | 0
1648 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
1649 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-I in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/13115 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Ramganj Zone-I Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 135 M3/hr. | 2503/RD/PHE | 12/09/2025 | 180 | JAL PRAVAHIKA PRIVATE LIMITED | 47.78 | 0 | 0 | 0
1650 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block , SM/07385 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Phulatti and Banigaon, Phulatti and Lahanda Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | 1392/RD/PHE | 09/12/2020 | 35 | PRASANTA DUTTA | 22.35 | 0 | 0 | 1
1651 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block , SM/07385 | Retrofitting | FHTC OF PHULATTI WSS | 1394/RD | 09/12/2020 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 7.56 | 0 | 0 | 100
1652 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block , SM/07385 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER PHULATTI AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN KALIAGANJ BLOCK IN UNDER RAIGANJ DIVISION. (Part-IV) | 1260/RD/PHE | 25/06/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 6.23 | 5.56 | 89.19 | 10
1653 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block , SM/07385 | Retrofitting | RETROFITTING OF FUNCTIONAL HOUSEHOLD TAP CONNECTIONS (FHTC) UNDER PHULATTI AND ADJOINING MOUZAS WATER SUPPLY SCHEME IN KALIAGANJ BLOCK IN UNDER RAIGANJ DIVISION. (Part-VI) | 1223/RD/PHE | 18/06/2021 | 30 | DONE ENTERPRISE | 8.83 | 0 | 0 | 0
1654 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block , SM/07385 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Phulatti and Kasidanga Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | 1390/RD/PHE | 09/12/2020 | 30 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 15.15 | 0 | 0 | 0
1655 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block , SM/07385 | Retrofitting | Material Requisition To Resource Division | 1813/RD/PHE | 23/09/2022 | 0 | Resource Division | 0.97 | 0 | 0 | 0
1656 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Phulatti and adjoining Mouzas water supply scheme in Kaliyaganj Block , SM/07385 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Phulatti and Sahapur Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | 1393/RD/PHE | 09/12/2020 | 30 | M/S P.S ENTERPRISE | 12.96 | 0 | 0 | 60
1657 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of FHTC under Kasba [NM] and adjoining mouzas WSS. , SM/09171 | Retrofitting | Route Survey & Preparation of DPR of KASBA NM PWSS under Raiganj Division, PHE Dte. | 154/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 2.53 | 0 | 0 | 0
1658 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of FHTC under Kasba [NM] and adjoining mouzas WSS. , SM/09171 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[NM] and adjoining Mouzas Water Supply Scheme In Raiganj Block under Raiganj Division, P.H.E. Dte. | 2071/RD/PHE | 02/11/2021 | 30 | S.B.CONSTRUCTION | 6.49 | 0 | 0 | 100
1659 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of FHTC under Kasba [NM] and adjoining mouzas WSS. , SM/09171 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[NM] and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E Dte. | 425/RD/PHE | 16/02/2022 | 30 | S.B.CONSTRUCTION | 6.43 | 0 | 0 | 100
1660 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of FHTC under Kasba [NM] and adjoining mouzas WSS. , SM/09171 | Retrofitting | Material Requisition To Resource Division | 30/RD/PHE | 06/01/2022 | 0 | Resource Division | 1.54 | 0 | 0 | 0
1661 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of FHTC under Kasba [NM] and adjoining mouzas WSS. , SM/09171 | Retrofitting | Material Requisition To Resource Division | 1801/RD/PHE | 23/09/2022 | 0 | Resource Division | 1.66 | 0 | 0 | 0
1662 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09180 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Dhulahar Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Itahar Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1827/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.97 | 0 | 0 | 0
1663 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09180 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Dhulahar Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E Dte. | 432/RD/PHE | 16/02/2022 | 30 | RAHUL ENTERPRISE | 6.65 | 0 | 0 | 0
1664 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09180 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Dhulahar Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E. Dte. | 2080/RD/PHE | 02/11/2021 | 30 | RAHUL ENTERPRISE | 6.95 | 0 | 0 | 100
1665 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Itahar and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09180 | Retrofitting | Material Requisition To Resource Division | 25/RD/PHE | 06/01/2022 | 0 | Resource Division | 4.69 | 0 | 0 | 0
1666 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Mahadebpur WSS for installation of FHTC. , SM/09128 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Mahadevpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | 2146/RD/PHE | 12/11/2021 | 30 | M/S ROYAL CONSTRUCTION | 4.85 | 0 | 0 | 1
1667 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Mahadebpur WSS for installation of FHTC. , SM/09128 | Retrofitting | Additional Pipe Line for Retrofitting of Mahadevpur for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | 2198/RD/PHE | 17/11/2021 | 30 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 7.56 | 0 | 0 | 0
1668 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Mahadebpur WSS for installation of FHTC. , SM/09128 | Retrofitting | stationary bill | BP-2022-23-18 | 28/04/2022 | 0 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.08 | 0 | 0 | 0
1669 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Mahadebpur WSS for installation of FHTC. , SM/09128 | Retrofitting | stationary bill | BP-2022-23-16 | 28/04/2022 | 0 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.09 | 0 | 0 | 0
1670 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09189 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) Under Khanta[Rasakhowa] Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E. Dte. | 2089/RD/PHE | 02/11/2021 | 30 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 9.46 | 0 | 0 | 1
1671 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09189 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Khanta [Rasakhowa] Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E Dte. | 434/RD/PHE | 16/02/2022 | 30 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 7.34 | 0 | 0 | 0
1672 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09189 | Retrofitting | Route Survey & Preparation of DPR of KHANTA PWSS under Raiganj Division, PHE Dte. | 153/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 3.02 | 0 | 0 | 0
1673 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09189 | Retrofitting | Material Requisition To Resource Division | 1819/RD/PHE | 28/09/2022 | 0 | Resource Division | 2.25 | 0 | 0 | 0
1674 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09189 | Retrofitting | Allied works in connection with retrofitting of FHTC in Khanta (Rasakhowa) PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2607/RD/PHE | 13/09/2023 | 60 | ASHIM CHANDA | 0.88 | 0 | 0 | 100
1675 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Khanta [Rasakhowa] and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09189 | Retrofitting | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | BP-2024-25-24 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 2.84 | 0 | 0 | 0
1676 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Pirojpur for installation of FHTC. , SM/09157 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of PIROJPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2113/RD/PHE | 03/11/2021 | 30 | M/S HINDUSTHAN CONSTRUCTION | 11.23 | 0 | 0 | 1
1677 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Udaypur for installation of FHTC. , SM/09158 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of UDAYPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2114/RD/PHE | 03/11/2021 | 30 | M/S SARKAR ENTERPRISE | 15.21 | 0 | 0 | 1
1678 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Piplan for installation of FHTC. , SM/09161 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of PIPLAN Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2117/RD/PHE | 03/11/2021 | 30 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 7.83 | 0 | 0 | 1
1679 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Surun for installation of FHTC. , SM/09168 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of SURUN Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2121/RD/PHE | 03/11/2021 | 30 | DIPANKAR SARKAR | 9.99 | 0 | 0 | 1
1680 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Pokheria WSS for installation of FHTC. , SM/09132 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Pokheria Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2148/RD/PHE | 12/11/2021 | 30 | M/S P.S. ENTERPRISE | 3.81 | 0 | 0 | 1
1681 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Biprit WSS for installation of FHTC. , SM/09133 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Biprit Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2149/RD/PHE | 12/11/2021 | 30 | HERO CONSTRUCTION | 1.37 | 0 | 0 | 1
1682 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Majlishpur for installation of FHTC. , SM/09140 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Majlishpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2154/RD/PHE | 12/11/2021 | 30 | M/S P.S. ENTERPRISE | 2.17 | 0 | 0 | 0
1683 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Intia WSS for installation of FHTC (Part-A & B) . , SM/09125 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Intia Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | 2145/RD/PHE | 12/11/2021 | 30 | M/S P.S. ENTERPRISE | 4.75 | 0 | 0 | 1
1684 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Intia WSS for installation of FHTC (Part-A & B) . , SM/09125 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Intia Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | 2195/RD/PHE | 17/11/2021 | 30 | M/S P.S. ENTERPRISE | 15.49 | 0 | 0 | 0
1685 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Chhotoparua Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10466 | Retrofitting | Restoration of Pipe Line For Providing FHTC For Chhotoparua Water Supply Scheme under Raiganj Block under Raiganj Division P.H.E. Dte. In The District of Uttar Dinajpur. (Phase-II) | 1041/RD/PHED | 12/05/2022 | 30 | RAHUL ENTERPRISE | 8.27 | 0 | 0 | 1
1686 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Mahammadpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) , SM/10444 | Retrofitting | Laying of Additional Pipe Line for Providing Functional Household Tap Connection for Mahammadpur(Surun) Water Supply Scheme under Itahar Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | 499/RD/PHE | 17/02/2023 | 45 | M/S DUTTA ENTERPRISE (JAYANTAJKD.USE@GMAIL.COM) | 9.08 | 0 | 0 | 0
1687 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Paharajpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10446 | Retrofitting | Restoration of Pipe Line For Providing FHTC for Paharajpur Water Supply Scheme under Itahar Block under Raiganj Division P.H.E. Dte. In The District of Uttar Dinajpur.(Phase-II) | 1036/RD/PHED | 12/05/2022 | 30 | RAHUL ENTERPRISE | 6.02 | 0 | 0 | 1
1688 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Sherpur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10494 | Retrofitting | Restoration of Pipe Line For Providing FHTC for Sherpur Water Supply Scheme under Kaliyaganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur.(Phase-II) | 1035/RD/PHED | 12/05/2022 | 30 | SARNALI ENTERPRISE | 5.8 | 0 | 0 | 1
1689 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme , SM/06722 | Retrofitting | FHTC OF BIPRIT PWSS | 1497/RD | 23/12/2020 | 25 | HERO CONSTRUCTION | 3.52 | 0 | 0 | 0
1690 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme , SM/06722 | Retrofitting | OFFICE ACCESSORIES BILL | 768/W | 11/03/2022 | 0 | DIGITEK SOLUTIONS | 0.1 | 0 | 0 | 0
1691 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Biprit and adjoining Mouzas water supply scheme , SM/06722 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Biprit and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | 1244/RD/PHE | 16/10/2020 | 40 | PRASANTO DUTTA | 90.07 | 0 | 0 | 0
1692 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | Material Requisition To Resource Division | 1973/RD/PHE | 08/11/2022 | 0 | Resource Division | 67.7 | 0 | 0 | 0
1693 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | FHTC (Functional Household Tap Connection) for Panjipara Zone-II Water Supply Scheme [Augmentation Scheme] in Goalpokhar-I Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2025/RD/PHE | 17/11/2022 | 90 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 78.25 | 0 | 0 | 0
1694 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Panjipara, Zone-II, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003160488 | 19/05/2023 | 365 | W.B.S.E.D.C.LTD | 7.27 | 0 | 0 | 0
1695 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No.- I of Augmentation of Panjipara (Zone- II) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011660) | 4769/MLMD | 29/12/2023 | 1915 | THE BUSINESS ENGINEERS INDIA | 6.76 | 0 | 0 | 0
1696 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Panjipara Zone-II Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 362/RD/PHE | 07/02/2023 | 45 | PULAK TALUKDAR PULAK.RNJ@GMAIL.COM | 5 | 0 | 0 | 100
1697 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | Repairing of Pump House at 2nd Tube well site in connection with Augmentation of Panjipara Zone-II piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | 363/RD/PHE | 07/02/2023 | 45 | M/S D. R. CONSTRUCTION AND COMPANY PAUL.RNJ@REDIFFMAIL.COM | 2.5 | 0 | 0 | 100
1698 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | Augmentation of PANJIPARA(Zone-II)Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | 1669/RD/PHE | 05/09/2022 | 90 | UTTAM SAHA | 207.19 | 0 | 0 | 80
1699 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Panjipara Water Supply Scheme (Zone-II) TW no I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 264/MLMD | 24/02/2023 | 90 | MAA BHABOTARINE ENTERPRISE. | 11.47 | 0 | 0 | 100
1700 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
1701 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | Construction Of Approach Road in connection with Augmentation Of Panjipara Zone-II PWSS at Goalpokhur- I Block under Raiganj Division,PHE dte. | 3774/RD/PHE | 19/12/2024 | 90 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 7.35 | 0 | 0 | 0
1702 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | Construction Of Boundary Wall With Gate at 2nd Tube-Well Site in connection with Augmentation Of Panjipara Zone-II PWSS at Goalpukhur-I Block under Raiganj Division,PHE dte. | 3311/RD/PHE | 20/11/2024 | 315 | MR CONSTRUCTION | 8.86 | 0 | 0 | 100
1703 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | Trial Run For Panjipara Zone-II PWSS under Goalpukhur-I Block under Raiganj Division ,PHE Dte. for 3 months | 555/RD/PHE | 12/02/2025 | 90 | APEX ENTERPRISES | 0.88 | 0 | 0 | 0
1704 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Panjipara Zone-II Water Supply Scheme(Augmentation) at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | 1969/RD/PHE | 02/07/2025 | 180 | AJIT PRAMANIK | 32.35 | 0 | 0 | 0
1705 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | Construction of Over Head Reservoir(Capacity-400 Cum) of PANJIPARA (Zone-II) Pipe Water Supply Scheme in connection with Augmentation at Goalpokher-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 733/RD/PHE | 15/03/2023 | 626 | M/S ELITE CONSTRUCTION | 143.09 | 0 | 0 | 100
1706 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | Laying distribution of additional pipeline(left out) with construction of Boundary Wall at Panjipara Zone-II in connection with augmentation of Panjipara Zone-II PWSS at Goalpukhor-I Block under Raiganj Division PHE Dte. | 2749/RD/PHE | 05/10/2023 | 629 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 25.81 | 0 | 0 | 40
1707 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Panjipara Zone-II in Goalpokhar-I Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11801 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Panjipara Water Supply Scheme (Zone-II) TW no II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 3682/MLMD | 29/11/2023 | 457 | BEE GEE CONSTRUCTION. | 11.41 | 0 | 0 | 100
1708 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Bindol Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12650 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Source Augmentation of Bindol Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015257) | 2469/MLMD | 04/08/2023 | 932 | SOVA ENTERPRISE. | 11.37 | 0 | 0 | 87
1709 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Bindol Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12650 | Augmentation | Material Requisition To Resource Division | 14/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
1710 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Bindol Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12650 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Bindol, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-217 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 5.06 | 0 | 0 | 0
1711 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Bindol Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12650 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Bindol Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1912/RD/PHE | 28/10/2022 | 855 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 29.34 | 0 | 0 | 50
1712 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Kotar Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12651 | Augmentation | Source(Rig Bored Tube-Well) Augmentation of Kotar Piped Water Supply Scheme of Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1908/RD/PHE | 28/10/2022 | 495 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 32.51 | 0 | 0 | 30
1713 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Kotar Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12651 | Augmentation | Material Requisition To Resource Division | 11/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
1714 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Kotar Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12651 | Augmentation | Quotation for new service connection at Source Augmentation of KOTAR PH-III (Itahar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12651) | BP-2024-25-240 | 29/05/2024 | 0 | W.B.S.E.D.C.LTD | 4.39 | 0 | 0 | 0
1715 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Kotar Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12651 | Augmentation | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. III of Source augmentation of Kotar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015244) | 2369/MLMD | 28/07/2023 | 479 | SUBRATA KUMAR DAS. | 10.55 | 0 | 0 | 100
1716 | UTTAR DINAJPUR | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block , SM/12095 | New | Material Requisition To Resource Division | 2179/RD/PHE | 12/12/2022 | 0 | Resource Division | 32.43 | 0 | 0 | 0
1717 | UTTAR DINAJPUR | Malda Mechanical | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block , SM/12095 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of CHAPAIR PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003202775 | 08/08/2023 | 90 | W.B.S.E.D.C.LTD | 5.2 | 0 | 0 | 100
1718 | UTTAR DINAJPUR | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block , SM/12095 | New | Implementation of CHAPOIR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division. | 291/RD/PHE | 01/02/2023 | 1055 | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 570.71 | 0 | 0 | 56
1719 | UTTAR DINAJPUR | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block , SM/12095 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Chapor PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3778/RD/PHE | 19/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 57.12 | 0 | 0 | 0
1720 | UTTAR DINAJPUR | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block , SM/12095 | New | Requisition of fund regarding payment for permanent restoration of rural roads damaged due to laying of pipeline by PHE Dte. as on 24.09.2024 i.c.w L042 BHABAK to CHAPOIR (Package No. WB15302: Under DLP), under coverage of Chapoir PWSS (SM/12095) | BP-2024-25-278 | 08/10/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 1.68 | 0 | 0 | 0
1721 | UTTAR DINAJPUR | Malda Mechanical | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block , SM/12095 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of CHAPAIR PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-400 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 10.81 | 0 | 0 | 0
1722 | UTTAR DINAJPUR | Malda Mechanical | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block , SM/12095 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chapair Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012816) | 2094/MLMD | 04/07/2023 | 837 | DILIP MAHATO. | 26.31 | 0 | 0 | 86
1723 | UTTAR DINAJPUR | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block , SM/12095 | New | Additional pipe line laying for Chapoir Piped Water Supply Scheme at Kaliyaganj Block of Uttar Diunajpur District Under Raiganj Division P.H.E. Dte. | 2837/RD/PHE | 23/09/2024 | 30 | M/S P.S. ENTERPRISE | 20.64 | 0 | 0 | 0
1724 | UTTAR DINAJPUR | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block , SM/12095 | New | Trial Run For Chapoir PWSS under Kaliaganj Block under Raiganj Division ,PHE Dte. for 3 months | 542/RD/PHE | 12/02/2025 | 90 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 0.88 | 0 | 0 | 0
1725 | UTTAR DINAJPUR | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block , SM/12095 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chapoir Water Supply Scheme at Kaliaganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 60 M3/hr. | 1621/RD/PHE | 19/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.58 | 0 | 0 | 0
1726 | UTTAR DINAJPUR | Raiganj Division | CHAPAIR Piped Water Supply Scheme at Kaliyaganj Block , SM/12095 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHAPAIR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 582/RD/PHE | 05/03/2024 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 22.87 | 0 | 0 | 50
1727 | UTTAR DINAJPUR | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12115 | New | Material Requisition To Resource Division | 2184/RD/PHE | 12/12/2022 | 0 | Resource Division | 30.98 | 0 | 0 | 0
1728 | UTTAR DINAJPUR | Malda Mechanical | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12115 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of LAXMIPUR PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003201648 | 29/07/2023 | 90 | W.B.S.E.D.C.LTD | 5.21 | 0 | 0 | 100
1729 | UTTAR DINAJPUR | Malda Mechanical | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12115 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of LAXMIPUR PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003201640 | 29/07/2023 | 90 | W.B.S.E.D.C.LTD | 5.73 | 0 | 0 | 100
1730 | UTTAR DINAJPUR | Malda Mechanical | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12115 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Laxmipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013047) | 1118/MLMD | 23/06/2023 | 934 | HANNAN BUILDERS PVT. LTD. | 26.14 | 0 | 0 | 85
1731 | UTTAR DINAJPUR | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12115 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under LAXMIPUR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 584/RD/PHE | 05/03/2024 | 45 | M/S P.S. ENTERPRISE | 22.91 | 0 | 0 | 40
1732 | UTTAR DINAJPUR | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12115 | New | Implementation of LAXMIPUR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division. | 296/RD/PHE | 01/02/2023 | 1065 | M/S LOKENATH CONSTRUCTION NAYANDASRAIGANJ75@GMAIL.COM | 580.95 | 0 | 0 | 65
1733 | UTTAR DINAJPUR | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12115 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Uttar Laxmipur PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3740/RD/PHE | 18/12/2024 | 225 | M/S MAA TARA CONSTRUCTION | 35.64 | 0 | 0 | 0
1734 | UTTAR DINAJPUR | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12115 | New | Balance pipe line for providing functional household tap bconnection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Laxmipur PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 06/RD/PHE | 02/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 56.25 | 0 | 0 | 0
1735 | UTTAR DINAJPUR | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12115 | New | Trial Run For Laxmipur PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | 525/RD/PHE | 12/02/2025 | 90 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 0.88 | 0 | 0 | 0
1736 | UTTAR DINAJPUR | Raiganj Division | LAXMIPUR Piped Water Supply Scheme at Kaliyaganj block under uttar Dinajpur district , SM/12115 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
1737 | UTTAR DINAJPUR | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Itahar and Kaliyaganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. , SM/11518 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Balahar village under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2883/RD/PHE | 25/09/2024 | 60 | NANDANIK ENGINEERS C-OPERATIVE SOCIETY LTD. | 43.71 | 0 | 0 | 0
1738 | UTTAR DINAJPUR | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Itahar and Kaliyaganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. , SM/11518 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Chakbhabanipur village under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2884/RD/PHE | 25/09/2024 | 60 | M/S. B. PAUL & COMPANY | 40.94 | 0 | 0 | 0
1739 | UTTAR DINAJPUR | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Itahar and Kaliyaganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. , SM/11518 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Itahar & Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1285/RD/PHE | 08/05/2023 | 970 | UJJWAL DAS | 503.04 | 0 | 0 | 20
1740 | UTTAR DINAJPUR | Raiganj Division | PASCHIM CHUTIAKHOR Piped Water Supply Scheme at Chopra Block , SM/12085 | New | Material Requisition To Resource Division | 967/RD/PHE | 29/03/2023 | 0 | Resource Division | 38.72 | 0 | 0 | 0
1741 | UTTAR DINAJPUR | Malda Mechanical | PASCHIM CHUTIAKHOR Piped Water Supply Scheme at Chopra Block , SM/12085 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Paschim Chutiakhore Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014265) | 2217/MLMD | 18/07/2023 | 842 | EASTERN INDIA SALES & SERVICE. | 27.21 | 0 | 0 | 0
1742 | UTTAR DINAJPUR | Raiganj Division | PASCHIM CHUTIAKHOR Piped Water Supply Scheme at Chopra Block , SM/12085 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
1743 | UTTAR DINAJPUR | Raiganj Division | PASCHIM CHUTIAKHOR Piped Water Supply Scheme at Chopra Block , SM/12085 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at PASCHIM CHUTIYAKHOR PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | 1209/RD/PHE | 25/04/2025 | 45 | RHYNO INFRASTRUCTURE | 59.96 | 0 | 0 | 0
1744 | UTTAR DINAJPUR | Raiganj Division | PASCHIM CHUTIAKHOR Piped Water Supply Scheme at Chopra Block , SM/12085 | New | Providing FHTC in connection with Paschim Chutikhore Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division. | 2162/RD/PHE | 23/07/2025 | 90 | M/S MAA BOLLA CONSTRUCTION | 8.62 | 0 | 0 | 0
1745 | UTTAR DINAJPUR | Raiganj Division | PASCHIM CHUTIAKHOR Piped Water Supply Scheme at Chopra Block , SM/12085 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Paschim Chutiakhore Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | 2511/RD/PHE | 12/09/2025 | 180 | MONDAL PRECISION PRIVATE LIMITED | 30.95 | 0 | 0 | 0
1746 | UTTAR DINAJPUR | Raiganj Division | UTTAR JIBHAKATA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12795 | New | Material Requisition To Resource Division | 1037/RD/PHE | 04/04/2023 | 0 | Resource Division | 48.17 | 0 | 0 | 0
1747 | UTTAR DINAJPUR | Malda Mechanical | UTTAR JIBHAKATA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12795 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Uttar Jibakata Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014469) | 2540/MLMD | 04/08/2023 | 960 | SUBRATA SAHA | 27.47 | 0 | 0 | 73
1748 | UTTAR DINAJPUR | Raiganj Division | UTTAR JIBHAKATA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12795 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
1749 | UTTAR DINAJPUR | Raiganj Division | UTTAR JIBHAKATA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12795 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Uttar Jibakata Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 35 M3/hr. | 2505/RD/PHE | 12/09/2025 | 180 | MONDAL PRECISION PRIVATE LIMITED | 18.03 | 0 | 0 | 0
1750 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Deona Piped Water Supply Scheme under Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/13020 | Augmentation | Material Requisition To Resource Division | 2393/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.48 | 0 | 0 | 0
1751 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Deona Piped Water Supply Scheme under Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/13020 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Deona Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1926/RD/PHE | 28/10/2022 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 32.87 | 0 | 0 | 15
1752 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Deona Piped Water Supply Scheme under Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/13020 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Deona, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-434 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.41 | 0 | 0 | 0
1753 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Deona Piped Water Supply Scheme under Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/13020 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Deona Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015282) | 2492/MLMD | 04/08/2023 | 600 | SARADA MAA CONSTRUCTION. | 10.87 | 0 | 0 | 100
1754 | UTTAR DINAJPUR | Malda Mechanical | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Cheramoti PWSS , Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003132796 | 12/04/2023 | 15 | W.B.S.E.D.C.LTD | 0.55 | 0 | 0 | 0
1755 | UTTAR DINAJPUR | Malda Mechanical | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Cheramoti PWSS , Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003132810 | 12/04/2023 | 15 | W.B.S.E.D.C.LTD | 0.49 | 0 | 0 | 0
1756 | UTTAR DINAJPUR | Malda Mechanical | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | Continuation work- Hiring of Inspection Vehicle (Diesel Driven) for official use of Executive Engineer for the office of the Executive Engineer under Malda Mechanical Division, PHED. | 2965/MLMD | 28/12/2022 | 121 | NITAI PANDEY | 0.72 | 0 | 0 | 100
1757 | UTTAR DINAJPUR | Malda Mechanical | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | Claim for purchase of fuel for hiring of inspection for different site visit use for Executive Engineer-,Under Mechanical Division, P.H.E. Dte | 2965/MLMD. | 28/12/2022 | 120 | NITAI PANDEY | 0.48 | 0 | 0 | 100
1758 | UTTAR DINAJPUR | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | Material Requisition To Resource Division | 1954/RD/PHE | 04/11/2022 | 0 | Resource Division | 16.22 | 0 | 0 | 0
1759 | UTTAR DINAJPUR | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | Implementation of CHERAMOTI and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | 1668/RD/PHE | 05/09/2022 | 1214 | SANYAL ENTERPRISE | 158.77 | 0 | 0 | 99
1760 | UTTAR DINAJPUR | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | Additional Pipe Line For Providing FHTC CHERAMOTI Piped Water Supply Scheme at Raiganj Block of Uttar Diunajpur District Under Raiganj Division P.H.E.Dte.(Phase-I) | 1690/RD/PHE | 10/06/2024 | 270 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 19.23 | 0 | 0 | 95
1761 | UTTAR DINAJPUR | Malda Mechanical | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of CHERAMOTI Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 255/MLMD | 24/02/2023 | 90 | DEY ENTERPRISE.. | 10.92 | 0 | 0 | 100
1762 | UTTAR DINAJPUR | Malda Mechanical | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of CHERAMOTI Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 256/MLMD | 24/02/2023 | 90 | SUDIP DEY | 10.85 | 0 | 0 | 100
1763 | UTTAR DINAJPUR | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | Construction of OHR & other allied works of CHERAMOTI and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | 588/RD/PHE | 24/02/2023 | 1042 | UTTAM SAHA | 128.61 | 0 | 0 | 70
1764 | UTTAR DINAJPUR | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | 1746/RD/PHE | 14/06/2024 | 198 | DEBASISH GHOSH | 2.6 | 0 | 0 | 0
1765 | UTTAR DINAJPUR | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under CHERAMOTI Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 567/RD/PHE | 05/03/2024 | 360 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 22.58 | 0 | 0 | 95
1766 | UTTAR DINAJPUR | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | Additional Pipe Line for Providing FHTC Cheramoti Piped Water Supply Scheme at Raiganj Block of Uttar Diunajpur District under Raiganj Division, P.H.E. Dte. (Phase-II) | 3013/RD/PHE | 03/10/2024 | 180 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 19.22 | 0 | 0 | 30
1767 | UTTAR DINAJPUR | Raiganj Division | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | Trial Run For Cheramoti PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | 537/RD/PHE | 12/02/2025 | 90 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0 | 0
1768 | UTTAR DINAJPUR | Malda Mechanical | CHERAMOTI PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK , SM/11863 | New | Making compound lighting arrangement with allied works at T/W no. I of Cheramati Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011704) | 02241/MLMD | 18/07/2023 | 606 | ANIMA ENTERPRISE | 3.53 | 0 | 0 | 100
1769 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF KUNORE PIPED WATER SUPPLY SCHEME , SM/11795 | Augmentation | Making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Kunore Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011433) | 2656/MLMD | 10/08/2023 | 1915 | MAA BHABOTARINE ENTERPRISE. | 10.28 | 0 | 0 | 0
1770 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KUNORE PIPED WATER SUPPLY SCHEME , SM/11795 | Augmentation | Material Requisition To Resource Division | 1948/RD/PHE | 04/11/2022 | 0 | Resource Division | 36.52 | 0 | 0 | 0
1771 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KUNORE PIPED WATER SUPPLY SCHEME , SM/11795 | Augmentation | Augmentation of KUNORE Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | 1542/RD/PHE | 26/08/2022 | 90 | UJJWAL DAS | 259.24 | 0 | 0 | 95
1772 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KUNORE PIPED WATER SUPPLY SCHEME , SM/11795 | Augmentation | FHTC (Functional Household Tap Connection) for Kunore Water Supply Scheme [Augmentation Scheme] in Kaliaganj Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2023/RD/PHE | 17/11/2022 | 90 | UJJWAL DAS | 73.38 | 0 | 0 | 70
1773 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KUNORE PIPED WATER SUPPLY SCHEME , SM/11795 | Augmentation | Repairing of Pump House of Head Works and 2nd Tube Well Site of Kunore in Connection with Augmentation of Kunore Piped Water Supply Scheme at Kaliyaganj Block under Raiganj Division P.H.E Dte. | 1544/RD/PHE | 24/05/2023 | 60 | A.S.B ENTERPRISE | 4.8 | 0 | 0 | 100
1774 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF KUNORE PIPED WATER SUPPLY SCHEME , SM/11795 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of KUNORE Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 757/MLMD | 25/04/2023 | 90 | S. P. CONSTRUCTION | 11.51 | 0 | 0 | 100
1775 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KUNORE PIPED WATER SUPPLY SCHEME , SM/11795 | Augmentation | Requisition of fund regarding payment for permanent restoration of rural roads damaged due to laying of pipeline by PHE Dte. as on 24.09.2024 i.c.w Shibpur - Madanpur Pacca Rasta- Kunarhat tala Pacca Rasta (Package No. WB15296: Under DLP), under coverage of Augmentation of Kunore PWSS (SM/11795) | BP-2024-25-276 | 08/10/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 3.2 | 0 | 0 | 0
1776 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF KUNORE PIPED WATER SUPPLY SCHEME , SM/11795 | Augmentation | Construction of Over Head Reservoir(Capacity-400 Cum) of KUNORE Pipe Water Supply Scheme in connection with Augmentation at KALIYAGANJ Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 726/RD/PHE | 15/03/2023 | 905 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. DEBASISHGHOSHDG76@GMAIL.COM | 143.15 | 0 | 0 | 45
1777 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Chandol WSS for installation of FHTC. , SM/09113 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of CHANDDOL Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2185/RD/PHE | 17/11/2021 | 30 | M/S BHOWMIK CONSTRUCTION | 7.02 | 0 | 0 | 0
1778 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Chandol WSS for installation of FHTC. , SM/09113 | Retrofitting | Vehicle hiring for inspection and monitoring of Augmentation work of Sariabad PWSS under Raiganj sub-division under Raiganj division, PHE Dte. for the period 13.12.2022 to 16.12.2022 | BP-2023-24-77 | 19/07/2023 | 0 | DEBASISH GHOSH | 0.04 | 0 | 0 | 0
1779 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Chandol WSS for installation of FHTC. , SM/09113 | Retrofitting |  | BP-2023-24-78 | 19/07/2023 | 0 | DEBASISH GHOSH | 0.08 | 0 | 0 | 0
1780 | UTTAR DINAJPUR | Raiganj Division | Sathaur Piped Water Supply Scheme , SM/13231 | New | Material Requisition To Resource Division | 888/RD/PHE | 27/03/2023 | 0 | Resource Division | 23.7 | 0 | 0 | 0
1781 | UTTAR DINAJPUR | Malda Mechanical | Sathaur Piped Water Supply Scheme , SM/13231 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Sathuar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015526) | 2534/MLMD | 04/08/2023 | 817 | MANIK CHANDRA SAHA. | 26.43 | 0 | 0 | 72
1782 | UTTAR DINAJPUR | Malda Mechanical | Sathaur Piped Water Supply Scheme , SM/13231 | New | Quotation for new service connection at SATHAUR PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-47 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 5.17 | 0 | 0 | 0
1783 | UTTAR DINAJPUR | Malda Mechanical | Sathaur Piped Water Supply Scheme , SM/13231 | New | Quotation for new service connection at SATHAUR PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-46 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 6.28 | 0 | 0 | 0
1784 | UTTAR DINAJPUR | Raiganj Division | Sathaur Piped Water Supply Scheme , SM/13231 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
1785 | UTTAR DINAJPUR | Raiganj Division | Sathaur Piped Water Supply Scheme , SM/13231 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Sathuar Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | 1877/RD/PHE | 26/06/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 29.58 | 0 | 0 | 0
1786 | UTTAR DINAJPUR | Raiganj Division | BALDIABASA Piped Water Supply Scheme , SM/13234 | New | Material Requisition To Resource Division | 890/RD/PHE | 27/03/2023 | 0 | Resource Division | 16.66 | 0 | 0 | 0
1787 | UTTAR DINAJPUR | Malda Mechanical | BALDIABASA Piped Water Supply Scheme , SM/13234 | New | Quotation for new service connection at BALDIABASA PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/13234) | BP-2024-25-272 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 16.82 | 0 | 0 | 0
1788 | UTTAR DINAJPUR | Malda Mechanical | BALDIABASA Piped Water Supply Scheme , SM/13234 | New | Quotation for new service connection at BALDIABASA PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/13234) | BP-2024-25-273 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 3.26 | 0 | 0 | 0
1789 | UTTAR DINAJPUR | Malda Mechanical | BALDIABASA Piped Water Supply Scheme , SM/13234 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Baldiabasa Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015377) | 2462/MLMD | 04/08/2023 | 907 | JAL PRAVAHIKA PVT. LTD. | 25.49 | 0 | 0 | 81
1790 | UTTAR DINAJPUR | Raiganj Division | BALDIABASA Piped Water Supply Scheme , SM/13234 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
1791 | UTTAR DINAJPUR | Raiganj Division | Gorahar Piped Water Supply Scheme. , SM/14640 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 0 | 100
1792 | UTTAR DINAJPUR | Raiganj Division | Gorahar Piped Water Supply Scheme. , SM/14640 | New | Material Requisition To Resource Division | 2230/RD/PHE | 01/08/2023 | 0 | Resource Division | 24.45 | 0 | 0 | 0
1793 | UTTAR DINAJPUR | Raiganj Division | Gorahar Piped Water Supply Scheme. , SM/14640 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under GORAHAR PWSS at Itahar Block under Raiganj Division, PHE Dte. | 613/RD/PHE | 05/03/2024 | 45 | M/S NATARAJ CONSTRUCTION DEBUABCD.1234@REDIFFMAIL.COM | 22.58 | 0 | 0 | 0
1794 | UTTAR DINAJPUR | Malda Mechanical | Gorahar Piped Water Supply Scheme. , SM/14640 | New | Quotation for new service connection at GORAHAR PH-I (Itahar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2023-24-691 | 15/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.55 | 0 | 0 | 0
1795 | UTTAR DINAJPUR | Malda Mechanical | Gorahar Piped Water Supply Scheme. , SM/14640 | New | Quotation for new service connection at GORAHAR PH-II (Birnagar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2023-24-692 | 15/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.89 | 0 | 0 | 0
1796 | UTTAR DINAJPUR | Malda Mechanical | Gorahar Piped Water Supply Scheme. , SM/14640 | New | Additional Quotation for new service connection at GORAHAR PH-I (ITAHAR ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/14640) | BP-2024-25-484 | 09/09/2024 | 0 | W.B.S.E.D.C.LTD | 3.44 | 0 | 0 | 0
1797 | UTTAR DINAJPUR | Malda Mechanical | Gorahar Piped Water Supply Scheme. , SM/14640 | New | Additional Quotation for TW No- II of Gorahar Water supply scheme, Birnagar CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-398 | 29/07/2024 | 0 | W.B.S.E.D.C.LTD | 2.39 | 0 | 0 | 0
1798 | UTTAR DINAJPUR | Raiganj Division | Gorahar Piped Water Supply Scheme. , SM/14640 | New | Implementation of GORAHAR and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 564/RD/PHE | 23/02/2023 | 1042 | SANYAL ENTERPRISE | 243.13 | 0 | 0 | 38
1799 | UTTAR DINAJPUR | Malda Mechanical | Gorahar Piped Water Supply Scheme. , SM/14640 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no- I,II & Making compound yard lighting arrangement at T/W no- I of GORAHAR Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016130) | 3422/MLMD | 01/11/2023 | 720 | MAA BHABOTARINE ENTERPRISE | 25.16 | 0 | 0 | 78
1800 | UTTAR DINAJPUR | Raiganj Division | Gorahar Piped Water Supply Scheme. , SM/14640 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Gorahar PWSS at Itahar Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 11/RD/PHE | 02/01/2025 | 45 | AJIT PRAMANIK | 29.8 | 0 | 0 | 0
1801 | UTTAR DINAJPUR | Raiganj Division | DANGRA DANGRI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14168 | New | Material Requisition To Resource Division | 2268/RD | 03/08/2023 | 0 | Resource Division | 49.81 | 0 | 0 | 0
1802 | UTTAR DINAJPUR | Malda Mechanical | DANGRA DANGRI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14168 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dangra Dangri Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016572) | 2489/MLMD | 04/08/2023 | 840 | DEY ENTERPRISE.. | 26.44 | 0 | 0 | 72
1803 | UTTAR DINAJPUR | Raiganj Division | DANGRA DANGRI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14168 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
1804 | UTTAR DINAJPUR | Raiganj Division | DANGRA DANGRI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14168 | New | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at DANGRA DANGRI .PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | 1210/RD/PHE | 25/04/2025 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 61.96 | 0 | 0 | 0
1805 | UTTAR DINAJPUR | Raiganj Division | MALKOT Pipe Water Supply Scheme , SM/15303 | New | Material Requisition To Resource Division | 965/RD/PHE | 29/03/2023 | 0 | Resource Division | 35.14 | 0 | 0 | 0
1806 | UTTAR DINAJPUR | Malda Mechanical | MALKOT Pipe Water Supply Scheme , SM/15303 | New | Quotation for new service connection at MALKOT PH-I (Dalkhola ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15303) | BP-2024-25-211 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 16.6 | 0 | 0 | 0
1807 | UTTAR DINAJPUR | Malda Mechanical | MALKOT Pipe Water Supply Scheme , SM/15303 | New | Quotation for new service connection at MALKOT PH-II (Dalkhola ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15303) | BP-2024-25-212 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 4.41 | 0 | 0 | 0
1808 | UTTAR DINAJPUR | Raiganj Division | MALKOT Pipe Water Supply Scheme , SM/15303 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
1809 | UTTAR DINAJPUR | Raiganj Division | MALKOT Pipe Water Supply Scheme , SM/15303 | New | Implementation of MALKOT and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd Tube Well) | 2066/RD/PHE | 21/07/2023 | 817 | KAMIRUL SK & CO. | 449.37 | 0 | 0 | 30
1810 | UTTAR DINAJPUR | Malda Mechanical | MALKOT Pipe Water Supply Scheme , SM/15303 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement at T/W no. I Malkot Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018415) | 2762/MLMD | 14/08/2023 | 1043 | BEE GEE CONSTRUCTION. | 25.45 | 0 | 0 | 88
1811 | UTTAR DINAJPUR | Raiganj Division | MALKOT Pipe Water Supply Scheme , SM/15303 | New | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for Malkot Piped Water Supply Scheme under Islampur Sub-Division PHED under Raiganj Division, PHE Dte.,U/D. (2nd Call) | 2041/RD/PHE | 09/07/2025 | 180 | PRIYA CONSTRUCTION | 20.46 | 0 | 0 | 0
1812 | UTTAR DINAJPUR | Raiganj Division | MALKOT Pipe Water Supply Scheme , SM/15303 | New | Additional pipeline and other ancillary works at Malkot piped water Supply Scheme Under Islampur Sub-Division under Raiganj Division, P.H.E Dte. (2nd Call) | 2040/RD/PHE | 09/07/2025 | 180 | M/S CHOUDHURY CONSTRUCTION | 43.33 | 0 | 0 | 0
1813 | UTTAR DINAJPUR | Raiganj Division | MALKOT Pipe Water Supply Scheme , SM/15303 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Malkot Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | 1929/RD/PHE | 30/06/2025 | 180 | AJIT PRAMANIK | 32.36 | 0 | 0 | 0
1814 | UTTAR DINAJPUR | Raiganj Division | MALKOT Pipe Water Supply Scheme , SM/15303 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MALKOT PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 646/RD/PHE | 05/03/2024 | 335 | MAA DURGA CONSTRUCTION | 22.58 | 0 | 0 | 100
1815 | UTTAR DINAJPUR | Raiganj Division | JAMIRA Piped Water Supply Scheme , SM/14179 | New | Material Requisition To Resource Division | 983/RD/PHE | 30/03/2023 | 0 | Resource Division | 41.55 | 0 | 0 | 0
1816 | UTTAR DINAJPUR | Malda Mechanical | JAMIRA Piped Water Supply Scheme , SM/14179 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Jamira Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017295) | 2444/MLMD | 04/08/2023 | 937 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD.. | 29.24 | 0 | 0 | 55
1817 | UTTAR DINAJPUR | Malda Mechanical | JAMIRA Piped Water Supply Scheme , SM/14179 | New | Quotation for new service connection at JAMIRA PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-83 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 13.49 | 0 | 0 | 0
1818 | UTTAR DINAJPUR | Malda Mechanical | JAMIRA Piped Water Supply Scheme , SM/14179 | New | Quotation for new service connection at JAMIRA PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-125 | 25/04/2024 | 0 | W.B.S.E.D.C.LTD | 12.06 | 0 | 0 | 0
1819 | UTTAR DINAJPUR | Raiganj Division | JAMIRA Piped Water Supply Scheme , SM/14179 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
1820 | UTTAR DINAJPUR | Raiganj Division | JAMIRA Piped Water Supply Scheme , SM/14179 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Jamira Water Supply Scheme at Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 90 M3/hr. | 1806/RD/PHE | 24/06/2025 | 180 | AJIT PRAMANIK | 33.59 | 0 | 0 | 0
1821 | UTTAR DINAJPUR | Raiganj Division | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Providing functional house hold tap connection at village-Dubel Babhania & Purba Goalgaon of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 770/RD/PHE | 17/03/2023 | 60 | UJJAL KUMAR SARKAR KUMARUJJAL51@GMAIL.COM | 11.13 | 0 | 0 | 0
1822 | UTTAR DINAJPUR | Raiganj Division | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Construction of OHR(Capacity-250 cum) HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 850/RD/PHE | 24/03/2023 | 275 | BHOWMICK ENTERPRISE | 91.89 | 0 | 0 | 0
1823 | UTTAR DINAJPUR | Raiganj Division | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Material Requisition To Resource Division | 1220/RD/PHE | 02/05/2023 | 0 | Resource Division | 36.73 | 0 | 0 | 0
1824 | UTTAR DINAJPUR | Raiganj Division | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Construction of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Hemenpur PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 2896/RD/PHE | 25/09/2024 | 30 | M/S SANJIB BHATTACHARJEE | 6.83 | 0 | 0 | 0
1825 | UTTAR DINAJPUR | Raiganj Division | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Construction of Boundary Wall & pump House at 2nd Tube-well Site of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 765/RD/PHE | 17/03/2023 | 60 | M/S BRIGHT CONSTRUCTION | 11.26 | 0 | 0 | 100
1826 | UTTAR DINAJPUR | Raiganj Division | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Construction of Boundary Wall and pump House at Head work Site of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 822/RD/PHE | 22/03/2023 | 60 | SAMRAT BOSE | 24.86 | 0 | 0 | 95
1827 | UTTAR DINAJPUR | Malda Mechanical | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Quotation for new service connection at HEMENPUR PH-II (Dalkhola ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/14180) | BP-2024-25-215 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 9.21 | 0 | 0 | 0
1828 | UTTAR DINAJPUR | Malda Mechanical | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Quotation for new service connection at HEMENPUR PH-I (Dalkhola ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/14180) | BP-2024-25-214 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 4.21 | 0 | 0 | 0
1829 | UTTAR DINAJPUR | Raiganj Division | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Lahutara, 2. Hemenpur, 3. Basudebpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 541/RD/PHE | 22/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 61.71 | 0 | 0 | 60
1830 | UTTAR DINAJPUR | Raiganj Division | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Providing functional house hold tap connection of Village-Hemenpur of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 955/RD/PHE | 29/03/2023 | 609 | APEX ENTERPRISES RUPESH.RNJ@GMAIL.COM | 11.81 | 0 | 0 | 0
1831 | UTTAR DINAJPUR | Raiganj Division | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Providing functional house hold tap connection at village-Paschim Goalgaon & Chengatuli of HEMENPUR Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 875/RD/PHE | 27/03/2023 | 493 | SANDIP SARKAR | 11.81 | 0 | 0 | 0
1832 | UTTAR DINAJPUR | Raiganj Division | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Laying of Rising Main of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 2048/RD/PHE | 19/07/2023 | 563 | M/S SAHA CONSTRUCTION | 4.31 | 0 | 0 | 100
1833 | UTTAR DINAJPUR | Malda Mechanical | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Hemenpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017332) | 2505/MLMD | 04/08/2023 | 600 | SHREE BISHNU CONSTRUCTION | 24.48 | 0 | 0 | 89
1834 | UTTAR DINAJPUR | Raiganj Division | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Laying of Additional pipeline with other ancillary works at different mouzas of HEMENPUR PWSS under Islampur Sub-Division P.H.E. Dte. | 3497/RD/PHE | 02/12/2024 | 90 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 53.33 | 0 | 0 | 0
1835 | UTTAR DINAJPUR | Raiganj Division | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Laying of pipeline main at village-Paschim Goalgaon and Chengatuli of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 870/RD/PHE | 27/03/2023 | 429 | SAHA CONSTRUCTION SAHAKUMARESH51@GMAIL.COM | 35.44 | 0 | 0 | 85
1836 | UTTAR DINAJPUR | Raiganj Division | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Laying of pipeline at village-Bhagabanpur of Hemenpur Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 945/RD/PHE | 29/03/2023 | 718 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 32.21 | 0 | 0 | 100
1837 | UTTAR DINAJPUR | Raiganj Division | HEMENPUR Piped Water Supply Scheme , SM/14180 | New | Providing functional house hold tap connection at village- Bhagabanpur of HEMENPUR Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 950/RD/PHE | 29/03/2023 | 668 | M/S.SADHANA ENTERPRISE | 11.91 | 0 | 0 | 90
1838 | UTTAR DINAJPUR | Raiganj Division | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/16228 | New | Material Requisition To Resource Division | 1053/RD/PHE | 06/04/2023 | 0 | Resource Division | 47.89 | 0 | 0 | 0
1839 | UTTAR DINAJPUR | Malda Mechanical | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/16228 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chitalghata Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018400) | 2641/MLMD | 10/08/2023 | 871 | MANIK CHANDRA SAHA. | 29.53 | 0 | 0 | 73
1840 | UTTAR DINAJPUR | Raiganj Division | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/16228 | New | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 20.09.2024 and 23.09.2024. | BP-2024-25-222 | 04/10/2024 | 0 | SAHA CONSTRUCTION | 0.06 | 0 | 0 | 0
1841 | UTTAR DINAJPUR | Raiganj Division | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/16228 | New | Implementation of Chitalghata and it's adjoining mouzas Pipe Water Supply Scheme at CHOPRA Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1553/RD/PHE | 26/05/2023 | 1080 | UTTAM SAHA | 665.31 | 0 | 0 | 65
1842 | UTTAR DINAJPUR | Raiganj Division | CHITALGHATA Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/16228 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | 1816/RD/PHE | 26/06/2024 | 198 | MD ZAFAR EQUEBAL | 2.6 | 0 | 0 | 100
1843 | UTTAR DINAJPUR | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16494 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 0 | 100
1844 | UTTAR DINAJPUR | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16494 | New | Material Requisition To Resource Division | 1694/RD/PHE | 22/06/2023 | 0 | Resource Division | 29.47 | 0 | 0 | 0
1845 | UTTAR DINAJPUR | Malda Mechanical | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16494 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no- I,II & Making compound yard lighting arrangement at T/W no- I of PARA Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016133) | 2449/MLMD | 04/08/2023 | 937 | SANJIB SAHA | 25.26 | 0 | 0 | 72
1846 | UTTAR DINAJPUR | Malda Mechanical | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16494 | New | Quotation for new service connection at Para PH-I (Itahar ccc) | BP-2023-24-538 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 3.37 | 0 | 0 | 0
1847 | UTTAR DINAJPUR | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16494 | New | Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of L032-GULANDAR TO MUKUNDAPUR Road (Package No. WB15311 : Under DLP) caused due to pipe laying by PHED under Para PWSS at different stretched of road under WBSRDA Uttar Dinajpur Division. | BP-2024-25-274 | 08/10/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 1.38 | 0 | 0 | 0
1848 | UTTAR DINAJPUR | Malda Mechanical | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16494 | New | Quotation for new service connection at Para PH-II (Itahar ccc) | BP-2023-24-537 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 4.11 | 0 | 0 | 0
1849 | UTTAR DINAJPUR | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16494 | New | Implementation of PARA and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 748/RD/PHE | 16/03/2023 | 1157 | SANYAL ENTERPRISE | 388.91 | 0 | 0 | 52
1850 | UTTAR DINAJPUR | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16494 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Para PWSS at Itahar Block under Raiganj Division, PHE Dte.,Uttar Dinajpur. | 3733/RD/PHE | 18/12/2024 | 225 | SANYAL ENTERPRISE | 23.02 | 0 | 0 | 0
1851 | UTTAR DINAJPUR | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16494 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Para Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj,Capacity- 50 M3/hr. | 1656/RD/PHE | 23/06/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 20.73 | 0 | 0 | 0
1852 | UTTAR DINAJPUR | Raiganj Division | PARA PIPED WATER SUPPLY SCHEME AT ITAHAR BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16494 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under PARA PWSS at Itahar Block under Raiganj Division, PHE Dte. | 614/RD/PHE | 05/03/2024 | 165 | M/S MAA BAIRA KALI CONSTRUCTION | 24.47 | 0 | 0 | 100
1853 | UTTAR DINAJPUR | Raiganj Division | Kashimpur Piped Water Supply Scheme. , SM/18182 | New | Material Requisition To Resource Division | 1333/RD/PHE | 15/05/2023 | 0 | Resource Division | 36.1 | 0 | 0 | 0
1854 | UTTAR DINAJPUR | Malda Mechanical | Kashimpur Piped Water Supply Scheme. , SM/18182 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Kashimpur, Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-71 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.37 | 0 | 0 | 0
1855 | UTTAR DINAJPUR | Malda Mechanical | Kashimpur Piped Water Supply Scheme. , SM/18182 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Kashimpur, Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-72 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 7 | 0 | 0 | 0
1856 | UTTAR DINAJPUR | Raiganj Division | Kashimpur Piped Water Supply Scheme. , SM/18182 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Palaibari, 2.Kashimpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 1491/RD/PHE | 17/05/2023 | 675 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 57.19 | 0 | 0 | 80
1857 | UTTAR DINAJPUR | Malda Mechanical | Kashimpur Piped Water Supply Scheme. , SM/18182 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II of Kashimpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/003990) | 2446/MLMD | 04/08/2023 | 516 | DEB CONSTRUCTION. | 22.84 | 0 | 0 | 100
1858 | UTTAR DINAJPUR | Raiganj Division | Kashimpur Piped Water Supply Scheme. , SM/18182 | New | Implementation of KASHIMPUR and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1132/RD/PHE | 24/04/2023 | 1080 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 407.34 | 0 | 0 | 55
1859 | UTTAR DINAJPUR | Raiganj Division | Kashimpur Piped Water Supply Scheme. , SM/18182 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kashimpur Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity- 80 M3/hr. | 2473/RD/PHE | 12/09/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.36 | 0 | 0 | 0
1860 | UTTAR DINAJPUR | Raiganj Division | LOHANDA PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18159 | New | Material Requisition To Resource Division | 2262/RD/PHE | 03/08/2023 | 0 | Resource Division | 10.97 | 0 | 0 | 0
1861 | UTTAR DINAJPUR | Malda Mechanical | LOHANDA PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18159 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II of Lohanda Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020859) | 4766/MLMD | 29/12/2023 | 180 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 19.98 | 0 | 0 | 82
1862 | UTTAR DINAJPUR | Raiganj Division | LOHANDA PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18159 | New | Implementation of LOHANDA and its adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1282/RD/PHE | 08/05/2023 | 1091 | BHOLA PAUL | 135.29 | 0 | 0 | 50
1863 | UTTAR DINAJPUR | Raiganj Division | LOHANDA PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18159 | New | Construction of Boundary Wall With Gate at Head Work & 2nd Tube-Well Site under LOHANDA PWSS at Raiganj Block under Raiganj Division, PHE Dte. | 628/RD/PHE | 05/03/2024 | 361 | M/S MANDAL ENTERPRISE | 11.14 | 0 | 0 | 48
1864 | UTTAR DINAJPUR | Raiganj Division | LOHANDA PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18159 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Lohanda PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 17/RD/PHE | 02/01/2025 | 30 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 11.25 | 0 | 0 | 0
1865 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Nalbithi Madhabpur Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. , SM/17743 | Augmentation | Preparation of DPR for drinking water supply scheme to facilitate 4(Four)Nos. Augmentation Scheme and 1(One) No. New PWSS (List Enclosed) Uncovered mouzas under Uttar Dinajpur District which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Raiganj Division P.H.E. Dte. | 2226/RD/PHE | 31/07/2023 | 15 | RADIANT | 11.57 | 0 | 0 | 100
1866 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Nalbithi Madhabpur Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. , SM/17743 | Augmentation | Material Requisition To Resource Division | 1105/RD/PHE | 20/04/2023 | 0 | Resource Division | 4.7 | 0 | 0 | 0
1867 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Nalbithi Madhabpur Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. , SM/17743 | Augmentation | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. III of Source augmentation of Nalbithi-Madhabpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2949/MLMD | 11/09/2024 | 90 | MANAS KUMAR SAHA | 7.16 | 0 | 0 | 0
1868 | UTTAR DINAJPUR | Raiganj Division | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17199 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
1869 | UTTAR DINAJPUR | Raiganj Division | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17199 | New | Material Requisition To Resource Division | 2249/RD/PHE | 03/08/2023 | 0 | Resource Division | 125.79 | 0 | 0 | 0
1870 | UTTAR DINAJPUR | Raiganj Division | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17199 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MOHISHGAON PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 632/RD/PHE | 05/03/2024 | 45 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 22.58 | 0 | 0 | 100
1871 | UTTAR DINAJPUR | Malda Mechanical | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17199 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Mohishgaon, Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-573 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 5.89 | 0 | 0 | 0
1872 | UTTAR DINAJPUR | Malda Mechanical | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17199 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Mohishgaon, Hemtabad CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-619 | 04/03/2024 | 0 | W.B.S.E.D.C.LTD | 8.92 | 0 | 0 | 0
1873 | UTTAR DINAJPUR | Raiganj Division | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17199 | New | Implementation of MOHISHGAON and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1274/RD/PHE | 08/05/2023 | 1080 | UTTAM SAHA | 373.39 | 0 | 0 | 50
1874 | UTTAR DINAJPUR | Malda Mechanical | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17199 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Mohishgaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018892) | 2763/MLMD | 14/08/2023 | 180 | UTTAM KUMAR GHOSH | 24.23 | 0 | 0 | 88
1875 | UTTAR DINAJPUR | Raiganj Division | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17199 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Mahishgaon PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3748/RD/PHE | 18/12/2024 | 135 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 21.97 | 0 | 0 | 0
1876 | UTTAR DINAJPUR | Raiganj Division | Mohishgaon Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/17199 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Mohishgaon Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity-45 M3/hr. | 2471/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 19.34 | 0 | 0 | 0
1877 | UTTAR DINAJPUR | Raiganj Division | DIGHALGAON PWSS , SM/18292 | New | Material Requisition To Resource Division | 639/RD/PHE | 02/03/2023 | 0 | Resource Division | 53.73 | 0 | 0 | 0
1878 | UTTAR DINAJPUR | Raiganj Division | DIGHALGAON PWSS , SM/18292 | New | Implementation of DIGHALGAON and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rdTubeWell) | 2002/RD/PHE | 13/07/2023 | 786 | DIPESH BHOWMIK | 503.41 | 0 | 0 | 40
1879 | UTTAR DINAJPUR | Malda Mechanical | DIGHALGAON PWSS , SM/18292 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Dighalgaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018378) | 2745/MLMD | 14/08/2023 | 987 | M/S S. S. ENTERPRISE | 38.21 | 0 | 0 | 0
1880 | UTTAR DINAJPUR | Raiganj Division | DIGHALGAON PWSS , SM/18292 | New | Additional pipeline and other ancillary works at Dighalgaon piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | 327/RD/PHE | 17/01/2025 | 90 | DIPESH BHOWMIK | 52.29 | 0 | 0 | 0
1881 | UTTAR DINAJPUR | Raiganj Division | DIGHALGAON PWSS , SM/18292 | New | Laying of pipeline with FHTC of DIGHALGAON and it¿s adjoining mouzas Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 738/RD/PHE | 12/03/2024 | 430 | M/S SOMNATH KUNDU | 96.35 | 0 | 0 | 60
1882 | UTTAR DINAJPUR | Malda Mechanical | DIGHALGAON PWSS , SM/18292 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 1276/MLMD | 27/02/2025 | 61 | NITAI PANDEY | 0.78 | 0 | 0 | 100
1883 | UTTAR DINAJPUR | Raiganj Division | DIGHALGAON PWSS , SM/18292 | New | Construction of Boundary Wall With Gate at Head Work Site ,2nd &3rd Tube-Well Site under DIGHALGAON PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 638/RD/PHE | 05/03/2024 | 441 | BASU AND COMPANY | 13.85 | 0 | 0 | 60
1884 | UTTAR DINAJPUR | Raiganj Division | KONAL PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14166 | New | Material Requisition To Resource Division | 980/RD/PHE | 30/03/2023 | 0 | Resource Division | 46.38 | 0 | 0 | 0
1885 | UTTAR DINAJPUR | Malda Mechanical | KONAL PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14166 | New | Quotation for new service connection at KONAL PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/14166) | BP-2024-25-270 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 8.23 | 0 | 0 | 0
1886 | UTTAR DINAJPUR | Malda Mechanical | KONAL PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14166 | New | Quotation for new service connection at KONAL PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/14166) | BP-2024-25-269 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 9.76 | 0 | 0 | 0
1887 | UTTAR DINAJPUR | Malda Mechanical | KONAL PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14166 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Konal Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017365) | 2445/MLMD | 04/08/2023 | 937 | ALOK ENTERPRISE, A UNIT OF SAKET TREXIM PVT. LTD.. | 29.24 | 0 | 0 | 55
1888 | UTTAR DINAJPUR | Raiganj Division | KONAL PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14166 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
1889 | UTTAR DINAJPUR | Raiganj Division | KONAL PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/14166 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
1890 | UTTAR DINAJPUR | Raiganj Division | BAJARGAON PWSS , SM/18626 | New | Material Requisition To Resource Division | 1317/RD/PHE | 12/05/2023 | 0 | Resource Division | 88.18 | 0 | 0 | 0
1891 | UTTAR DINAJPUR | Raiganj Division | BAJARGAON PWSS , SM/18626 | New | Estimate for the work of PMGSY Road in connection with laying of pipeline along the road shoulder. | BP-2024-25-127 | 22/07/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 9.21 | 0 | 0 | 0
1892 | UTTAR DINAJPUR | Malda Mechanical | BAJARGAON PWSS , SM/18626 | New | Quotation for new service connection at BAJARGAON PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18626) | BP-2024-25-478 | 09/09/2024 | 0 | W.B.S.E.D.C.LTD | 22.74 | 0 | 0 | 0
1893 | UTTAR DINAJPUR | Malda Mechanical | BAJARGAON PWSS , SM/18626 | New | Quotation for new service connection at BAJARGAON PH-III (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18626) | BP-2024-25-479 | 09/09/2024 | 0 | W.B.S.E.D.C.LTD | 11.71 | 0 | 0 | 0
1894 | UTTAR DINAJPUR | Malda Mechanical | BAJARGAON PWSS , SM/18626 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I, II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Bajargaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018347) | 2730/MLMD | 14/08/2023 | 867 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 41.58 | 0 | 0 | 0
1895 | UTTAR DINAJPUR | Raiganj Division | BAJARGAON PWSS , SM/18626 | New | Implementation of BAJARGAON and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Tube-Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd &3rd TubeWell) | 2480/RD/PHE | 24/08/2023 | 591 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 841.02 | 0 | 0 | 66
1896 | UTTAR DINAJPUR | Raiganj Division | BAJARGAON PWSS , SM/18626 | New | Construction of Approach Road at Head Work Site, & 3rd Tube-Well Site under New Scheme of Bazargaon PWSS at Karandighi Block under Raiganj Division, PHE dte. | 2898/RD/PHE | 25/09/2024 | 30 | SARNALI ENTERPRISE | 6.78 | 0 | 0 | 0
1897 | UTTAR DINAJPUR | Raiganj Division | BAJARGAON PWSS , SM/18626 | New | Laying of Additional pipeline with other ancillary works at different mouzas of BAZARGAON PWSS under Islampur Sub-Division P.H.E. Dte. | 3496/RD/PHE | 02/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 31.92 | 0 | 0 | 0
1898 | UTTAR DINAJPUR | Raiganj Division | BAJARGAON PWSS , SM/18626 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bazargaon Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | 2014/RD/PHE | 08/07/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 36.36 | 0 | 0 | 0
1899 | UTTAR DINAJPUR | Raiganj Division | BAJARGAON PWSS , SM/18626 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under BAJARGAON PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 657/RD/PHE | 05/03/2024 | 315 | M/S CHAKRABORTY ENTERPRISE | 13.85 | 0 | 0 | 100
1900 | UTTAR DINAJPUR | Raiganj Division | BAJARGAON PWSS , SM/18626 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd &3rd Tube-Well Site under BAJARGAON PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 658/RD/PHE | 05/03/2024 | 315 | DISCOVERY CO. OPERATIVE LABOUR CONT AND CONST SOC. LTD. | 13.85 | 0 | 0 | 100
1901 | UTTAR DINAJPUR | Raiganj Division | PURBBA GOMAIDIGHI PWSS , SM/18448 | New | Material Requisition To Resource Division | 619/RD/PHE | 28/02/2023 | 0 | Resource Division | 41.78 | 0 | 0 | 0
1902 | UTTAR DINAJPUR | Raiganj Division | PURBBA GOMAIDIGHI PWSS , SM/18448 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under PURBA GUMAIDIGHI PWSS at Islampur Block under Raiganj Division, PHE Dte. | 546/RD/PHE | 05/03/2024 | 45 | M/S BABA LOKNATH CONSTRUCTION | 22.57 | 0 | 0 | 0
1903 | UTTAR DINAJPUR | Malda Mechanical | PURBBA GOMAIDIGHI PWSS , SM/18448 | New | Quotation for new service connection at PURBBA GOMAIDIGHI PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-66 | 15/04/2024 | 0 | W.B.S.E.D.C.LTD | 10.07 | 0 | 0 | 0
1904 | UTTAR DINAJPUR | Malda Mechanical | PURBBA GOMAIDIGHI PWSS , SM/18448 | New | Quotation for new service connection at PURBBA GOMAIDIGHI PH-II (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-65 | 15/04/2024 | 0 | W.B.S.E.D.C.LTD | 10.53 | 0 | 0 | 0
1905 | UTTAR DINAJPUR | Raiganj Division | PURBBA GOMAIDIGHI PWSS , SM/18448 | New | Implementation of PURBA GOMAIDIGHI and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte | 2470/RD/PHE | 24/08/2023 | 861 | PRADIP KUMAR PAUL | 692.96 | 0 | 0 | 75
1906 | UTTAR DINAJPUR | Raiganj Division | PURBBA GOMAIDIGHI PWSS , SM/18448 | New | Laying of Additional pipeline with other ancillary works at different mouzas of PURBA GOMAIDIGHI PWSS under Islampur Sub-Division P.H.E. Dte. | 3493/RD/PHE | 02/12/2024 | 405 | PRADIP KUMAR PAUL | 78.28 | 0 | 0 | 40
1907 | UTTAR DINAJPUR | Malda Mechanical | PURBBA GOMAIDIGHI PWSS , SM/18448 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no.I & II and making compound lighting arrangement at T/W no.I of PURBA GOMAIDIGHI Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 1003/MLMD | 11/03/2024 | 837 | DEY ENTERPRISE.. | 28.11 | 0 | 0 | 79
1908 | UTTAR DINAJPUR | Raiganj Division | PURBBA GOMAIDIGHI PWSS , SM/18448 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Purba Gomaidighi Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | 1810/RD/PHE | 24/06/2025 | 180 | PRADIP KUMAR PAUL | 19.12 | 0 | 0 | 0
1909 | UTTAR DINAJPUR | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District , SM/18450 | New | Preparation of DPR for drinking water supply scheme to facilitate 4(Four)Nos. Augmentation Scheme and 1(One) No. New PWSS (List Enclosed) Uncovered mouzas under Uttar Dinajpur District which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Raiganj Division P.H.E. Dte. | 2226/RD/PHE | 31/07/2023 | 15 | RADIANT | 11.57 | 0 | 0 | 100
1910 | UTTAR DINAJPUR | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District , SM/18450 | New | Material Requisition To Resource Division | 2259/RD/PHE | 03/08/2023 | 0 | Resource Division | 141.14 | 0 | 0 | 0
1911 | UTTAR DINAJPUR | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District , SM/18450 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 10.06.2024 to 14.06.2024. | BP-2024-25-93 | 28/06/2024 | 0 | M/S DILWAR HOSAIN | 0.08 | 0 | 0 | 0
1912 | UTTAR DINAJPUR | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District , SM/18450 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 13.05.2024 to 17.05.2024. | BP-2024-25-94 | 28/06/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
1913 | UTTAR DINAJPUR | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District , SM/18450 | New | Beldangi Road from 7.00 km to 9.40 km under Dakshin Dinajpur Highway Division in the District of Dakshin Dinajpur, Urgent restoration of Hard Shoulder in stretches caused due to laying of pipeline by PHED under Chhayghara PWSS under Raiganj Divison, PHE Dte. | BP-2024-25-281 | 05/11/2024 | 0 | EXECUTIVE ENGINEER (DAKSHIN DINAJPUR HIGHWAY DIVISION) | 11.19 | 0 | 0 | 0
1914 | UTTAR DINAJPUR | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District , SM/18450 | New | Work Order for hiring charges of vehicle with fuel, hired for works of Raiganj Division, P.H.E. Dte. for 03.09.2024 and 09.09.2024. | BP-2024-25-223 | 04/10/2024 | 0 | SAHA CONSTRUCTION | 0.07 | 0 | 0 | 0
1915 | UTTAR DINAJPUR | Malda Mechanical | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District , SM/18450 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no- I & II of Chhayghara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018690) | 2741/MLMD | 14/08/2023 | 898 | MAA BHABOTARINE ENTERPRISE. | 24.24 | 0 | 0 | 84
1916 | UTTAR DINAJPUR | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District , SM/18450 | New | Implementation of CHHAYGHARA and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2471/RD/PHE | 24/08/2023 | 848 | M/S S.D. ENTERPRISE | 775.32 | 0 | 0 | 30
1917 | UTTAR DINAJPUR | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District , SM/18450 | New | Construction Of Approach Road,Laying Of Pipe Line,Fhtc And Other Allied Works Of Chayaghara Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3568/RD/PHE | 05/12/2024 | 91 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 52.27 | 0 | 0 | 0
1918 | UTTAR DINAJPUR | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District , SM/18450 | New | Construction of Boundary Wall With Gate at Head Work Site ,2nd &3rd Tube-Well Site under CHHAYGHARA PWSS at Itahar Block under Raiganj Division, PHE Dte. | 633/RD/PHE | 05/03/2024 | 360 | PRIMECON ENTERPRISE | 27.71 | 0 | 0 | 60
1919 | UTTAR DINAJPUR | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District , SM/18450 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12 months (Period from 17.10.2023 to 16.10.2024) | 2876/RD/PHE | 17/10/2023 | 366 | ARNAB DUTTA | 4.8 | 0 | 0 | 100
1920 | UTTAR DINAJPUR | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District , SM/18450 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.Vehicle no. WB74AP 7552) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month( period from 27.11.2024 to 26.05.2025). | 3446/RD/PHE | 26/11/2024 | 181 | M/S SARKAR ENTERPRISE SILIGURI | 2.4 | 0 | 0 | 0
1921 | UTTAR DINAJPUR | Raiganj Division | Chhayghara Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District , SM/18450 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chhayghora Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 45 M3/hr. | 2478/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 19.35 | 0 | 0 | 0
1922 | UTTAR DINAJPUR | Raiganj Division | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/18341 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 0 | 100
1923 | UTTAR DINAJPUR | Raiganj Division | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/18341 | New | Material Requisition To Resource Division | 2244/RD/PHE | 02/08/2023 | 0 | Resource Division | 123.16 | 0 | 0 | 0
1924 | UTTAR DINAJPUR | Raiganj Division | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/18341 | New | Implementation of KAPASIA and its adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte | 2092/RD/PHE | 27/07/2023 | 930 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 1262.96 | 0 | 0 | 30
1925 | UTTAR DINAJPUR | Raiganj Division | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/18341 | New | Construction of Approach Road, Laying of Pipe Line, FHTC And Other Allied Works of Kapasia PWSS Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3559/RD/PHE | 05/12/2024 | 91 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 48.29 | 0 | 0 | 0
1926 | UTTAR DINAJPUR | Raiganj Division | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/18341 | New | Construction of Boundary Wall With Gate at Head Work Site, 2nd, 3rd & 4th Tube-Well Site under KAPASIA PWSS at Itahar Block under Raiganj Division, PHE Dte. | 621/RD/PHE | 05/03/2024 | 338 | KRISHNA CONSTRUCTION | 35.63 | 0 | 0 | 50
1927 | UTTAR DINAJPUR | Raiganj Division | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/18341 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12 months (Period from 17.10.2023 to 16.10.2024) | 2876/RD/PHE | 17/10/2023 | 366 | ARNAB DUTTA | 4.8 | 0 | 0 | 100
1928 | UTTAR DINAJPUR | Raiganj Division | Kapasia Piped Water Supply Scheme at Itahar Block under Uttar Dinajpur District. , SM/18341 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kapasia Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 150 M3/hr. | 2491/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 52.01 | 0 | 0 | 0
1929 | UTTAR DINAJPUR | Raiganj Division | Source augmentation for Dakshin Kundal Pukhar Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12649 | Augmentation | Source(Rig Bored Tube-Well) Augmentation of Dakshin Kundal Pukur Piped Water Supply Scheme of Chopra Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1909/RD/PHE | 28/10/2022 | 45 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 32.3 | 0 | 0 | 0
1930 | UTTAR DINAJPUR | Raiganj Division | Source augmentation for Dakshin Kundal Pukhar Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12649 | Augmentation | Material Requisition To Resource Division | 2396/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.48 | 0 | 0 | 0
1931 | UTTAR DINAJPUR | Malda Mechanical | Source augmentation for Dakshin Kundal Pukhar Piped Water Supply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12649 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Dakshin Kundalpukur Water Supply Scheme in the District of Uttar DInajpur under Malda Mechanical Division, PHE Dte. (TSM/002870) | 2651/MLMD | 10/08/2023 | 1051 | PABITRA MANDAL | 10.54 | 0 | 0 | 86
1932 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Surun Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12645 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Surun Piped Water Supply Scheme of Itahar Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1918/RD/PHE | 28/10/2022 | 75 | M/S P.S. ENTERPRISE | 32.83 | 0 | 0 | 30
1933 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Surun Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12645 | Augmentation | Material Requisition To Resource Division | 12/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
1934 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Surun Piped Water Supply Scheme under Itahar Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12645 | Augmentation | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. III of Source augmentation of Surun Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015248) | 2453/MLMD | 04/08/2023 | 600 | M/S. MAYUKH BHADURI | 10.48 | 0 | 0 | 100
1935 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Baruna Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12641 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Baruna PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003276648 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 3.92 | 0 | 0 | 100
1936 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Baruna Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12641 | Augmentation | Source(Rig Bored Tube-Well) Augmentation of Baruna Piped Water Supply Scheme of Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1907/RD/PHE | 28/10/2022 | 45 | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 25.99 | 0 | 0 | 65
1937 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Baruna Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12641 | Augmentation | Material Requisition To Resource Division | 21/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
1938 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Baruna Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12641 | Augmentation | Additional Quotation charge at TW No- III of Baruna, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-704 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 1.41 | 0 | 0 | 0
1939 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Baruna Piped Water Supply Scheme under Kaliaganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12641 | Augmentation | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. III of Source augmentation of Baruna Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015272) | 2467/MLMD | 04/08/2023 | 593 | JOY ENTERPRISE. | 10.54 | 0 | 0 | 100
1940 | UTTAR DINAJPUR | Malda Mechanical | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12104 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of BEURJHARI PWSS, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003202432 | 02/08/2023 | 90 | W.B.S.E.D.C.LTD | 4.77 | 0 | 0 | 100
1941 | UTTAR DINAJPUR | Malda Mechanical | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12104 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of BEURJHARI PWSS , Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003202773 | 07/08/2023 | 90 | W.B.S.E.D.C.LTD | 5.6 | 0 | 0 | 100
1942 | UTTAR DINAJPUR | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12104 | New | Material Requisition To Resource Division | 31/RD/PHE | 06/01/2023 | 0 | Resource Division | 22.57 | 0 | 0 | 0
1943 | UTTAR DINAJPUR | Malda Mechanical | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12104 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Beurjhari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012758) | 1116/MLMD | 23/06/2023 | 120 | ASHUTOSH DAS AND CO. | 25.17 | 0 | 0 | 87
1944 | UTTAR DINAJPUR | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12104 | New | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehical No. WB60T 9215) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 17.10.2024 to 14.01.2025) | 3045/RD/PHE | 04/10/2024 | 90 | ARNAB DUTTA | 1.2 | 0 | 0 | 0
1945 | UTTAR DINAJPUR | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12104 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
1946 | UTTAR DINAJPUR | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12104 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Beurjhari PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3736/RD/PHE | 18/12/2024 | 135 | BHOLA PAUL | 20.01 | 0 | 0 | 0
1947 | UTTAR DINAJPUR | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12104 | New | Trial Run For Beurjhari PWSS under Kaliaganj Block under Raiganj Division ,PHE Dte. for 3 months | 541/RD/PHE | 12/02/2025 | 90 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.87 | 0 | 0 | 0
1948 | UTTAR DINAJPUR | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12104 | New | Implementation of BEURJHARI and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 67/RD/HE | 16/01/2023 | 715 | BHOLA PAUL | 223.52 | 0 | 0 | 80
1949 | UTTAR DINAJPUR | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12104 | New | Balance UPVC Pipe Line of Bheurjhari PWSS at Kaliyaganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | 2227/RD/PHE | 23/07/2024 | 30 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 8.66 | 0 | 0 | 100
1950 | UTTAR DINAJPUR | Raiganj Division | BEURJHARI Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12104 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BEURJHARI Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 577/RD/PHE | 05/03/2024 | 75 | BHOLA PAUL | 22.93 | 0 | 0 | 90
1951 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme , SM/06727 | Retrofitting | OFFICE ACCESSORIES BILL | 766/W | 11/03/2022 | 0 | DIGITEK SOLUTIONS | 0.1 | 0 | 0 | 0
1952 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme , SM/06727 | Retrofitting | HIRE CHRAGE OF VEHICLE | 322/W | 14/09/2022 | 0 | JOYDEB GHOSH | 0.06 | 0 | 0 | 0
1953 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme , SM/06727 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Chhotaparua and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E. Dte. | 1243/RD/PHE | 16/10/2020 | 40 | PRASANTA DUTTA | 77.11 | 0 | 0 | 0
1954 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme , SM/06727 | Retrofitting | Providing Functional House Hold Connection (FHTC) for the purpose of Chotaparua Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 496/RD/PHE | 17/02/2023 | 45 | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 3.18 | 0 | 0 | 0
1955 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Chhotaparua and adjoining Mouzas water supply scheme , SM/06727 | Retrofitting | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 15.01.2025 to 14.07.2025 | 296/RD/PHE | 15/01/2025 | 181 | DEBASISH GHOSH | 2.4 | 0 | 0 | 0
1956 | UTTAR DINAJPUR | Raiganj Division | UTTAR SHAHAPUR PWSS , SM/18475 | New | Material Requisition To Resource Division | 982/RD/PHE | 30/03/2023 | 0 | Resource Division | 66.81 | 0 | 0 | 0
1957 | UTTAR DINAJPUR | Malda Mechanical | UTTAR SHAHAPUR PWSS , SM/18475 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Uttar Sahapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016451) | 2538/MLMD | 04/08/2023 | 907 | HANNAN BUILDERS PVT. LTD. | 39.82 | 0 | 0 | 77
1958 | UTTAR DINAJPUR | Malda Mechanical | UTTAR SHAHAPUR PWSS , SM/18475 | New | Quotation for new service connection at UTTAR SHAHAPUR PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18475) | BP-2024-25-258 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 6.85 | 0 | 0 | 0
1959 | UTTAR DINAJPUR | Malda Mechanical | UTTAR SHAHAPUR PWSS , SM/18475 | New | Quotation for new service connection at UTTAR SHAHAPUR PH-III (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18475) | BP-2024-25-257 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 6.18 | 0 | 0 | 0
1960 | UTTAR DINAJPUR | Malda Mechanical | UTTAR SHAHAPUR PWSS , SM/18475 | New | Quotation for new service connection at UTTAR SHAHAPUR PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18475) | BP-2024-25-259 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 8.3 | 0 | 0 | 0
1961 | UTTAR DINAJPUR | Raiganj Division | UTTAR SHAHAPUR PWSS , SM/18475 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
1962 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Faridpur and adjoining Mouzas water supply scheme , SM/07139 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under FARIDPUR and ADJOINING Mouzas Water Supply Scheme in Kaliyaganj Block under Raiganj Division, P.H.E. Dte. | 1413/ RD | 11/12/2020 | 40 | M/S MAA TARA CONSTRUCTION BIRNAGAR SUNILPRAMAICK1961@GMAIL.COM | 67.94 | 0 | 0 | 1
1963 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block , SM/07072 | Retrofitting | OFFICE ACCESSORIES BILL | 765/W | 11/03/2022 | 0 | BEEKAY.COM | 0.1 | 0 | 0 | 0
1964 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block , SM/07072 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Sergram Part Mouza under Sergram Water Supply Scheme in Kaliyganj Block under Raiganj Division, P.H.E. Dte. | 1432/RD/PHE | 11/12/2020 | 30 | M/S P.S ENTERPRISE | 17.7 | 0 | 0 | 0
1965 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block , SM/07072 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Sergram Mouza under Sergram Water Supply Scheme in Kaliyganj Block under Raiganj Division, P.H.E. Dte. | 1434/RD/PHE | 11/12/2020 | 30 | AJIT PARMANIK | 18.68 | 0 | 0 | 0
1966 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block , SM/07072 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Shursa Mouza under Sergram Water Supply Scheme in Kaliyganj Block under Raiganj Division, P.H.E. Dte. | 1433/RD/PHE | 11/12/2020 | 30 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 19.38 | 0 | 0 | 0
1967 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Sergram and adjoining Mouzas water supply scheme in Kaliyaganj Block , SM/07072 | Retrofitting | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month(Period from 01.07.2023 to 30.06.2024). | 1722/RD/PHE | 28/06/2023 | 366 | DEBASISH GHOSH | 4.8 | 0 | 0 | 0
1968 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block , SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Laguar Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | 1418/RD/PHE | 11/12/2020 | 30 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CAST SOCIETY LTD. | 10.53 | 0 | 0 | 1
1969 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block , SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Habipur Mouza under Amalbari and Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | 1420/RD/PHE | 11/12/2020 | 30 | SANJIB BHATTACHARJEE | 10.54 | 0 | 0 | 1
1970 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block , SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Sahasra Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | 1419/RD/PHE | 11/12/2020 | 30 | LOKENATH CO-OP LBOUR CONTRACT &CONSTRUCTION SOCIETY LTD. | 10.56 | 0 | 0 | 1
1971 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block , SM/07073 | Retrofitting | OFFICE ACCESSORIES BILL | 772/W | 11/03/2022 | 0 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.06 | 0 | 0 | 0
1972 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block , SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Baldoria Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block Under Raiganj Division, P.H.E. Dte. | 1440/RD/PHE | 11/12/2020 | 30 | DIPANKAR SARKAR | 10.56 | 0 | 0 | 1
1973 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block , SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Amalbari Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | 1417/RD/PHE | 11/12/2020 | 30 | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 10.56 | 0 | 0 | 100
1974 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalbari and adjoining Mouzas water supply scheme in Golapokhar-II Block , SM/07073 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) at Ranipur Mouza under Amalbari Water Supply Scheme in Goalpokher-II Block under Raiganj Division, P.H.E. Dte. | 467/RD/PHE | 26/02/2021 | 30 | M/S BHOWMIK ENTERPRISE | 10.53 | 0 | 0 | 0
1975 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme , SM/07140 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Majhiali Mouza under Dakshin Kundal Pukur Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | 1426/RD/PHE | 11/12/2020 | 30 | S.B.CONSTRUCTION | 16.48 | 0 | 0 | 1
1976 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme , SM/07140 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Dakshin Kundal Pukur Mouza under Dakshin Kundal Pukur Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | 1428/RD/PHE | 11/12/2020 | 30 | M/S BHOWMIK ENTERPRISE | 16.5 | 0 | 0 | 1
1977 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme , SM/07140 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Ariagaon Mouza under Dakshin Kundal Pukur Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | 1427/RD/PHE | 11/12/2020 | 30 | CHAITANYA SAMAL | 17.17 | 4.93 | 31.14 | 1
1978 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme , SM/07140 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Uttar Besarbari Mouza under Dakshin Kundal Pukur Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | 1429/RD/PHE | 11/12/2020 | 30 | IDEAL CO-OP LABOUR CONTRACT &CONST SOCIETY LTD. | 16.94 | 0 | 0 | 1
1979 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme , SM/07140 | Retrofitting | OFFICE ACCESSORIES BILL | 752/W | 11/03/2022 | 0 | JHUNU SAHA | 0.1 | 0 | 0 | 0
1980 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dakshin Kundal Pukhar and adjoining Mouzas water supply scheme , SM/07140 | Retrofitting | OFFICE ACCESSORIES BILL | 753/W | 11/03/2022 | 0 | SAHA CONSTRUCTION | 0.1 | 0 | 0 | 0
1981 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Lodhan and adjoining Mouzas water supply scheme , SM/06731 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Lodhan and adjoining Mouzas Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | 1240/RD/PHE | 16/10/2020 | 40 | J.D.J. ENTERPRISE | 65.65 | 0 | 0 | 0
1982 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Lodhan and adjoining Mouzas water supply scheme , SM/06731 | Retrofitting | OFFICE ACCESSORIES BILL | 775/W | 11/03/2022 | 0 | SAHA CONSTRUCTION | 0.06 | 0 | 0 | 0
1983 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of FHTC under Bhatol and adjoining mouzas WSS. , SM/09170 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Bhatol and adjoining Mouzas Water Supply Scheme in Raiganj Block under Raiganj Division, P.H.E. Dte. | 2070/RD/PHE | 02/11/2021 | 30 | JEET CONSTRUCTION | 8.09 | 0 | 0 | 1
1984 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of FHTC under Bhatol and adjoining mouzas WSS. , SM/09170 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Bhatol and adjoining mouzas water supply scheme in Raiganj Block Under Raiganj Division, P.H.E Dte. | 424/RD/PHE | 16/02/2022 | 30 | JEET CONSTRUCTION | 7.8 | 0 | 0 | 0
1985 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of FHTC under Bhatol and adjoining mouzas WSS. , SM/09170 | Retrofitting | Route Survey & Preparation of DPR of BHATOL PWSS under Raiganj Division, PHE Dte. | 155/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 3.85 | 0 | 0 | 0
1986 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of FHTC under Bhatol and adjoining mouzas WSS. , SM/09170 | Retrofitting | Material Requisition To Resource Division | 31/RD/PHE | 06/01/2022 | 0 | Resource Division | 1.89 | 0 | 0 | 0
1987 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of FHTC under Bhatol and adjoining mouzas WSS. , SM/09170 | Retrofitting | Material Requisition To Resource Division | 1800/RD/PHE | 23/09/2022 | 0 | Resource Division | 2.12 | 0 | 0 | 0
1988 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dilwarpur and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. , SM/09176 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Dilwarpur Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1825/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.73 | 2.72 | 100 | 0
1989 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dilwarpur and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. , SM/09176 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Dilwarpur Piped Water Supply Scheme And adjoining Mouzas Water Supply Scheme In Kaliaganj Block under Raiganj Division, P.H.E Dte. | 428/RD/PHE | 16/02/2022 | 30 | MAA SHEETALA ENTERPRISE | 7.07 | 0 | 0 | 0
1990 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dilwarpur and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. , SM/09176 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Dilwarpur Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Kaliaganj Block under Raiganj Division, P.H.E. Dte. | 2076/RD/PHE | 02/11/2021 | 30 | M/S GHOSH CONSTRUCTION | 7.18 | 0 | 0 | 1
1991 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dilwarpur and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. , SM/09176 | Retrofitting | Material Requisition To Resource Division | 1793/RD/PHE | 22/09/2022 | 0 | Resource Division | 1.9 | 0 | 0 | 0
1992 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kanki-Matiari and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. , SM/09191 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Kanki-Matiari Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Goalpokhar - II Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1817/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.6 | 2.49 | 100 | 0
1993 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kanki-Matiari and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. , SM/09191 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kanki-Matiari Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. | 437/RD/PHE | 16/02/2022 | 30 | TAPAN KUMAR MAJUMDER | 2.99 | 0 | 0 | 0
1994 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kanki-Matiari and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. , SM/09191 | Retrofitting | Material Requisition To Resource Division | 37/RD/PHE | 06/01/2022 | 0 | Resource Division | 1.35 | 0 | 0 | 0
1995 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kanki-Matiari and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. , SM/09191 | Retrofitting | Material Requisition To Resource Division | 1826/RD/PHE | 28/09/2022 | 0 | Resource Division | 1.17 | 0 | 0 | 0
1996 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Kanki-Matiari and adjoining mouzas Water Supply Scheme In Goalpokhor-II Block Under Raiganj Division, P. H. E. Dte. , SM/09191 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kanki-Matiari Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-II Block under Raiganj Division, P.H.E. Dte. | 2091/RD/PHE | 02/11/2021 | 30 | TAPAN KUMAR MAJUMDER | 5.8 | 0 | 0 | 50
1997 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Raghabpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09192 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Raghabpur Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Karandighi Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1822/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.04 | 0 | 0 | 0
1998 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Raghabpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09192 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Raghabpur Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E. Dte. | 2092/RD/PHE | 02/11/2021 | 30 | M/S DOLPHIN CONSTRUCTION | 7.63 | 0 | 0 | 1
1999 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Raghabpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09192 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Raghabpur Piped Water Supply Scheme And adjoining Mouzas Water Supply Scheme In Karandighi Block under Raiganj Division, P.H.E Dte. | 433/RD/PHE | 16/02/2022 | 30 | M/S DOLPHIN CONSTRUCTION | 7.34 | 0 | 0 | 0
2000 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Raghabpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09192 | Retrofitting | Material Requisition To Resource Division | 32/RD/PHE | 06/01/2022 | 0 | Resource Division | 1.78 | 0 | 0 | 0
2001 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Raghabpur and adjoining mouzas Water Supply Scheme In Karandighi Block Under Raiganj Division, P. H. E. Dte. , SM/09192 | Retrofitting | Material Requisition To Resource Division | 1818/RD/PHE | 28/09/2022 | 0 | Resource Division | 2 | 0 | 0 | 0
2002 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Purba Durlavpur WSS for installation of FHTC. , SM/09112 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Purba Durlavpur Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | 2138/RD/PHE | 12/11/2021 | 30 | UTTAM SAHA | 4.85 | 0 | 0 | 1
2003 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Purba Durlavpur WSS for installation of FHTC. , SM/09112 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of PURBA DURLAVPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | 2184/RD/PHE | 17/11/2021 | 30 | TAPAN KUMAR DUTTA | 5.91 | 0 | 0 | 0
2004 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Kaliganj Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) , SM/10464 | Retrofitting | Laying of additional Pipeline for providing functional household tap connections for Kaliganj(Poaltair) Water Supply Scheme under Hemtabad Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. | 1029/RD/PHE | 31/03/2023 | 45 | SARNALI ENTERPRISE SARNALI.RNJ@GMAIL.COM | 7.53 | 0 | 0 | 100
2005 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe Line for Retrofitting FHTC of Deona Piped Water Supply Scheme under Raiganj Division, P.H.E. Dte. (Phase-II) , SM/10427 | Retrofitting | Restoration of Pipe line for Retrofitting FHTC of Deona piped water Supply Scheme under Raiganj Division P.H.E. Dte. (Phase-II) | 1008/RD/PHED | 11/05/2022 | 20 | NIMAI DAS | 2.01 | 0 | 0 | 1
2006 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | 1519\RD | 24/08/2022 | 7 | JUMBO XEROX | 0.1 | 0 | 0 | 0
2007 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Providing and delivering A4 Size Xerox paper under Raiganj Division,P.H.E.Dte. | 1522\RD | 24/08/2022 | 7 | JUMBO XEROX | 0.1 | 0 | 0 | 0
2008 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Construction of 2Nos. Tube-Well (250mm diameter x 150mmx150mtr) for Augmentation of SASAN Water Supply Scheme in HEMTABAD Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | 1201/RD/PHE | 06/06/2022 | 30 | M/S SARKAR ENTERPRISE | 18.2 | 0 | 0 | 1
2009 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Material Requisition To Resource Division | 1981/RD/PHE | 09/11/2022 | 0 | Resource Division | 9.56 | 0 | 0 | 0
2010 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | xerox bill | BP-2022-23-210 | 04/11/2022 | 0 | JUMBO XEROX | 0.1 | 0 | 0 | 0
2011 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | xerox bill | BP-2022-23-208 | 04/11/2022 | 0 | JUMBO XEROX | 0.1 | 0 | 0 | 0
2012 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | FHTC (Functional Household Tap Connection) for Sasan Water Supply Scheme [Augmentation Scheme] in Hemtabad Block of Uttar Dinajpur District. | 1016/RD/PHED | 12/05/2022 | 45 | M/S HINDUSTHAN CONSTRUCTION | 43.64 | 0 | 0 | 20
2013 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Laying Rising Main pipeline inter-connection of Tubewells including construction of valve chamber and other related works for SASAN PWSS [Augmentation] and its adjoining Water Supply Scheme in Hemtabad Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | 1533/RD/PHE | 25/08/2022 | 30 | M/S CHOUDHURY CONSTRUCTION KUMARCHOUDHURYSAMIR0@GMAIL.COM | 0.7 | 0 | 0 | 0
2014 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of SHASAN Water Supply Scheme T/W no.II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2274/MLMD | 31/08/2022 | 45 | ANIMA ENTERPRISE | 6.1 | 0 | 0 | 0
2015 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of SASAN Water Supply Scheme T/W no.I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2273/MLMD | 31/08/2022 | 45 | MAA BHABOTARINE ENTERPRISE | 7.54 | 0 | 0 | 0
2016 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Soil Investigation for Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including RCC Over Pile Foundation For Augmentation of Sasan Water W/S Scheme in Hemtabad Block in Uttar Dinajpur District. | 1239/RD/PHE | 20/06/2022 | 20 | K.S. GROUP | 1.99 | 0 | 0 | 0
2017 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Repairing of Pump House of Head Works and 2nd Tube Well Site in connection with Augmentation of Sasan Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E Dte. | 434/RD/PHE | 10/02/2023 | 45 | SHYAM ENTERPRISE SHYAMENTERPRISE.RNJ@GMAIL.COM | 3 | 0 | 0 | 100
2018 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Material Requisition To Resource Division | 641/RD/PHE | 23/03/2022 | 0 | Resource Division | 4.86 | 0 | 0 | 0
2019 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Hiring of vehicle for Inspection and monitoring of Augmentation work of Sasan PWSS under JJM for the period 16.11.2022 to 23.11.2022. | BP-2023-24-75 | 19/07/2023 | 0 | DEBASISH GHOSH | 0.1 | 0 | 0 | 0
2020 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Hiring of vehicle for Inspection and monitoring of Augmentation work of Sasan PWSS under JJM for the period 16.11.2022 to 23.11.2022. |  | 15/06/2023 | 0 | DEBASISH GHOSH | 0.1 | 0 | 0 | 0
2021 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Laying Distribution System for SASAN and its adjoining Mouza Water Supply Scheme at Hemtabad Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | 487/RD/PHE | 25/02/2022 | 30 | BHOLA PAUL | 85.26 | 0 | 0 | 75
2022 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Construction of Over Head Reservoir(Capacity-300 Cum)of SASAN Pipe Water Supply Scheme in connection with Augmentation at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 77/RD/PHE | 17/01/2023 | 690 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. LOKNATH.ITR@GMAIL.COM | 84.28 | 0 | 0 | 95
2023 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Sasan PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 19/RD/PHE | 02/01/2025 | 120 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 14.82 | 0 | 0 | 100
2024 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Ancillary works regarding Inter Connection of rising main with Teube-well with construction of boundary wall for additional land for Augmentation of Sasan PWSS at Hemtabad Block under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 416/RD/PHE | 29/01/2025 | 45 | BHOLA PAUL | 14.33 | 0 | 0 | 0
2025 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Ancillary Works Regarding Interconnection of Rising Main With Tubewell of Sasan PWSS at Headwork Site & 2nd TW Site In Connection with Sasan Augmentation at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur | 1543/RD/PHE | 11/06/2025 | 30 | M/S CHOUDHURY CONSTRUCTION | 1.35 | 0 | 0 | 0
2026 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION OF SASAN PIPED WATER SUPPLY SCHEME , SM/10040 | Augmentation | Ancillary works and inter connection b/w rising main and OHR, I.C.W. Augmentation of Sasan PWSS at Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E Dte. | 1607/RD/PHE | 17/06/2025 | 120 | SANDIP SARKAR | 3.79 | 0 | 0 | 0
2027 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Shridharpur Water Supply Scheme under Itahar Block under Raiganj Division, P.H.E. Dte. (Phase-II) , SM/10442 | Retrofitting | Restoration of Pipe Line for Providing FHTC for Shridharpur WSS (Purba Durlavpur PWSS) under Raiganj Division, PHE Dte. | 2788/RD/PHE | 11/10/2023 | 30 | GOPES SAHA | 4.67 | 0 | 0 | 100
2028 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under under Kasba [Itahar] and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09173 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba[Itahar] Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E. Dte. | 2073/RD/PHE | 02/11/2021 | 30 | SUBHASIS MAJUMDER | 8.77 | 0 | 0 | 1
2029 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under under Kasba [Itahar] and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09173 | Retrofitting | Route Survey & Preparation of DPR of KASBA -ITAHAR PWSS under PHE Dte. | 174/RD/PHE | 25/01/2022 | 30 | ENVIROTECH SOLUTIONS | 4.02 | 0 | 0 | 0
2030 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under under Kasba [Itahar] and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09173 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Kasba [Itahar] Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme in Itahar Block under Raiganj Division, P.H.E Dte. | 427/RD/PHE | 16/02/2022 | 30 | SUBHASIS MAJUMDER | 8.48 | 0 | 0 | 0
2031 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under under Kasba [Itahar] and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09173 | Retrofitting | Material Requisition To Resource Division | 29/RD/PHE | 06/01/2022 | 0 | Resource Division | 2.06 | 0 | 0 | 0
2032 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under under Kasba [Itahar] and adjoining mouzas Water Supply Scheme In Itahar Block Under Raiganj Division, P. H. E. Dte. , SM/09173 | Retrofitting | Material Requisition To Resource Division | 1803/RD/PHE | 23/09/2022 | 0 | Resource Division | 2.31 | 0 | 0 | 0
2033 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Ramganj Water Supply Scheme (Zone-II) TW no I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 259/MLMD | 24/02/2023 | 90 | DEVI ENTERPRISE... | 11.53 | 0 | 0 | 0
2034 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Construction of Over Head Reservoir(Capacity-400 Cum) of RAMGANJ(Zone-II) Pipe Water Supply Scheme in connection with Augmentation at Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 731/RD/PHE | 15/03/2023 | 365 | SOVAN KUMAR ROY | 143.15 | 0 | 0 | 0
2035 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Ramganj, Zone-II, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003120505 | 28/04/2023 | 90 | W.B.S.E.D.C.LTD | 9.99 | 0 | 0 | 0
2036 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Ramganj, Zone-II, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003120516 | 28/04/2023 | 90 | W.B.S.E.D.C.LTD | 13.59 | 0 | 0 | 0
2037 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Laying of Additional Pipe line for Ramganj Zone-II Piped water Supply Scheme in connection with Augmentation of Ramganj Zone-II PWSS under Raiganj Division P.H.E. Dte in the District of Uttar Dinajpur. | 1543/RD/PHE | 24/05/2023 | 30 | UJJWAL DAS | 7.59 | 0 | 0 | 0
2038 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Ramganj Zone-II Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 368/RD/PHE | 07/02/2023 | 45 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 5.02 | 0 | 0 | 100
2039 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m)in connection with Augmentation of Ramganj Zone-II Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 379/RD/PHE | 07/02/2023 | 45 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. SRAMAJEEBEECO@GMAIL.COM | 4.1 | 0 | 0 | 100
2040 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Material Requisition To Resource Division | 1946/RD/PHE | 04/11/2022 | 0 | Resource Division | 55.2 | 0 | 0 | 0
2041 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Ramganj Water Supply Scheme, (Zone-II) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011644) | 2655/MLMD | 10/08/2023 | 1915 | DAS CONSTRUCTION | 10.54 | 0 | 0 | 0
2042 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Augmentation of RAMGANJ(Zone-II)Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | 1552/RD/PHE | 26/08/2022 | 818 | UJJWAL DAS | 177.43 | 0 | 0 | 98
2043 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | FHTC (Functional Household Tap Connection) for Ramganj Zone-II Water Supply Scheme [Augmentation Scheme] in Islampur Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2018/RD/PHE | 17/11/2022 | 90 | M/S CHOUDHURY CONSTRUCTION KUMARCHOUDHURYSAMIR0@GMAIL.COM | 56.88 | 0 | 0 | 38
2044 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Supply, Installation & Commissioning of electro-mechanical accessories and other allied works at Augmentation of Ramganj Zone-II (PH-I) W/S Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 837/MLMD | 19/02/2024 | 15 | MAA BHABOTARINE ENTERPRISE | 1.45 | 0 | 0 | 100
2045 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
2046 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Providing FHTC in connection with augmentation of Ramganj Zone-II Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | 50/RD/PHE | 03/01/2025 | 45 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 29.19 | 0 | 0 | 0
2047 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Restoration of damaged pipeline with some ancillary works at different mouzas under Ramganj Z-II PWSS under Islampur Sub-Division P.H.E. Dte. | 3299/RD/PHE | 20/11/2024 | 135 | UJJWAL DAS | 21.68 | 0 | 0 | 0
2048 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Balance Distribution System of Laying Pipeline with Construction of Boundary Wall with Gate at Head Work Site & 2nd Tube-Well Site under RAMGANJ Zone-II PWSS(Augmentation) at Islampur Block under Raiganj Division, PHE Dte. | 739/RD/PHE | 12/03/2024 | 549 | SOVAN KUMAR ROY | 25.87 | 0 | 0 | 95
2049 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
2050 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Trial Run For Ramganj Zone-II PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | 545/RD/PHE | 12/02/2025 | 90 | UJJWAL DAS | 0.88 | 0 | 0 | 0
2051 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Ramganj Water Supply Scheme (Zone-II) TW no II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 262/MLMD | 24/02/2023 | 90 | DILIP MAHATO. | 11.45 | 0 | 0 | 0
2052 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramganj Zone-II in Islampur Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11802 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Ramganj Zone-II Water Supply Scheme (Augmentation) at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | 2502/RD/PHE | 12/09/2025 | 180 | JAL PRAVAHIKA PRIVATE LIMITED | 32.32 | 0 | 0 | 0
2053 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Udaypur Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10496 | Retrofitting | Restoration of Pipe Line For Providing FHTC for Udaypur Water Supply Scheme under Raiganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur.(Phase-II) | 1049/RD/PHED | 12/05/2022 | 45 | M/S P.S. ENTERPRISE | 14.2 | 0 | 0 | 1
2054 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Mahinagar Water Supply Scheme under Kaliyaganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/10498 | Retrofitting | Restoration of Pipe Line For Providing Functional Household Tap Connection for Mahinagar Water Supply Scheme under Kaliyaganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur. | 498/RD/PHE | 17/02/2023 | 45 | TAPAN KUMAR ROY | 6.11 | 0 | 0 | 100
2055 | UTTAR DINAJPUR | Malda Mechanical | BANIKANER ALISA RAHATPUR PWSS , SM/12522 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of BANIKANER ALISA RAHATPUR , Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003194822 | 18/07/2023 | 90 | W.B.S.E.D.C.LTD | 7.99 | 0 | 0 | 100
2056 | UTTAR DINAJPUR | Malda Mechanical | BANIKANER ALISA RAHATPUR PWSS , SM/12522 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of BANIKANER ALISA RAHATPUR,Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003199237 | 25/07/2023 | 90 | W.B.S.E.D.C.LTD | 10.46 | 0 | 0 | 100
2057 | UTTAR DINAJPUR | Raiganj Division | BANIKANER ALISA RAHATPUR PWSS , SM/12522 | New | Material Requisition To Resource Division | 616/RD/PHE | 28/02/2023 | 0 | Resource Division | 25.55 | 0 | 0 | 0
2058 | UTTAR DINAJPUR | Raiganj Division | BANIKANER ALISA RAHATPUR PWSS , SM/12522 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BANIKANER ALISA PWSS at Islampur Block under Raiganj Division, PHE Dte. | 597/RD/PHE | 05/03/2024 | 45 | K.G.N BUILDERS | 22.57 | 0 | 0 | 0
2059 | UTTAR DINAJPUR | Raiganj Division | BANIKANER ALISA RAHATPUR PWSS , SM/12522 | New | Implementation of BANIKANER ALISA RAHATPUR and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd Tube Well.) | 551/RD/PHE | 23/02/2023 | 1248 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 232.41 | 0 | 0 | 80
2060 | UTTAR DINAJPUR | Malda Mechanical | BANIKANER ALISA RAHATPUR PWSS , SM/12522 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Banikaner Alisa Rahatpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014361) | 2479/MLMD | 04/08/2023 | 907 | M/S TRILOCHAN CONSTRUCTION CO. | 25.38 | 0 | 0 | 78
2061 | UTTAR DINAJPUR | Raiganj Division | BANIKANER ALISA RAHATPUR PWSS , SM/12522 | New | Construction of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Banikaner Alisa Rahatpur PWSS at Islampur Block under Raiganj Division,PHE dte. | 2895/RD/PHE | 25/09/2024 | 20 | SHANKAR SAHA | 4.31 | 0 | 0 | 0
2062 | UTTAR DINAJPUR | Raiganj Division | BANIKANER ALISA RAHATPUR PWSS , SM/12522 | New | Laying of Additional pipeline with other ancillary works at different mouzas of BENIKANER ALIAS RAHATPUR PWSS under Islampur Sub-Division P.H.E. Dte. | 3490/RD/PHE | 02/12/2024 | 30 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 14.85 | 0 | 0 | 0
2063 | UTTAR DINAJPUR | Raiganj Division | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12109 | New | Material Requisition To Resource Division | 2199/RD/PHE | 14/12/2022 | 0 | Resource Division | 59.08 | 0 | 0 | 0
2064 | UTTAR DINAJPUR | Raiganj Division | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12109 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Runia PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3760/RD/PHED | 18/12/2024 | 45 | AJIT PRAMANIK | 74.5 | 0 | 0 | 0
2065 | UTTAR DINAJPUR | Malda Mechanical | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12109 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Runia, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-551 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 5.83 | 0 | 0 | 0
2066 | UTTAR DINAJPUR | Malda Mechanical | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12109 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Runia Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-550 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 4.25 | 0 | 0 | 0
2067 | UTTAR DINAJPUR | Raiganj Division | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12109 | New | Implementation of RUNIA and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 98/RD/PHE | 19/01/2023 | 1078 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 451 | 0 | 0 | 10
2068 | UTTAR DINAJPUR | Malda Mechanical | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12109 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Runia Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012037) | 2530/MLMD | 04/08/2023 | 815 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 24.9 | 0 | 0 | 90
2069 | UTTAR DINAJPUR | Raiganj Division | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12109 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RUNIA Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 575/RD/PHE | 05/03/2024 | 360 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 22.94 | 0 | 0 | 75
2070 | UTTAR DINAJPUR | Raiganj Division | RUNIA Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12109 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
2071 | UTTAR DINAJPUR | Raiganj Division | BIRGHAI Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12110 | New | Material Requisition To Resource Division | 2177/RD/PHE | 12/12/2022 | 0 | Resource Division | 27.08 | 0 | 0 | 0
2072 | UTTAR DINAJPUR | Raiganj Division | BIRGHAI Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12110 | New | Implementation of BIRGHAI and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 288/RD/PHE | 01/02/2023 | 1065 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. MAJUMDERSUBHANDU1976@GMAIL.COM | 560.3 | 0 | 0 | 15
2073 | UTTAR DINAJPUR | Malda Mechanical | BIRGHAI Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12110 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Birghai Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011862) | 2400/MLMD | 28/07/2023 | 884 | MERCURY ENGINEERING COMPANY. | 26.79 | 0 | 0 | 34
2074 | UTTAR DINAJPUR | Raiganj Division | BIRGHAI Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12110 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BIRGHAI Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 574/RD/PHE | 05/03/2024 | 45 | M/S POYEM ENTERPRISE | 22.57 | 0 | 0 | 70
2075 | UTTAR DINAJPUR | Raiganj Division | BIRGHAI Piped Water Supply Scheme at Raiganj block under uttar Dinajpur district , SM/12110 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Birghai PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 14/RD/PHE | 02/01/2025 | 270 | DULAL MAJUMDER | 78.38 | 0 | 0 | 0
2076 | UTTAR DINAJPUR | Raiganj Division | Source augmentation for Chhotaparua Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12643 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Chhotaparua Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1914/RD/PHE | 28/10/2022 | 405 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 30.69 | 0 | 0 | 50
2077 | UTTAR DINAJPUR | Raiganj Division | Source augmentation for Chhotaparua Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12643 | Augmentation | Material Requisition To Resource Division | 18/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
2078 | UTTAR DINAJPUR | Malda Mechanical | Source augmentation for Chhotaparua Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12643 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Chhotaparua , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-398 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 8.35 | 0 | 0 | 0
2079 | UTTAR DINAJPUR | Malda Mechanical | Source augmentation for Chhotaparua Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12643 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Source Augmentation of Chhotaparua Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015259) | 2484/MLMD | 04/08/2023 | 565 | SUBRATA KUMAR DAS. | 11.37 | 0 | 0 | 100
2080 | UTTAR DINAJPUR | Malda Mechanical | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ , SM/11643 | New | Making compound lighting arrangement with allied works at T/W no. I of Baghan Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011707) | 2237/MLMD | 18/07/2023 | 90 | SHREE BISHNU CONSTRUCTION | 2.64 | 0 | 0 | 0
2081 | UTTAR DINAJPUR | Malda Mechanical | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ , SM/11643 | New | W.B.S.E.D.C.LTD Quotation charge at P/H-I of Baghan, of Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003074327 | 01/02/2023 | 90 | W.B.S.E.D.C.LTD | 0.84 | 0 | 0 | 1
2082 | UTTAR DINAJPUR | Malda Mechanical | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ , SM/11643 | New | W.B.S.E.D.C.LTD Quotation charge at P/H-II of Baghan, of Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003074355 | 01/02/2023 | 90 | W.B.S.E.D.C.LTD | 0.73 | 0 | 0 | 1
2083 | UTTAR DINAJPUR | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ , SM/11643 | New | Material Requisition To Resource Division | 1956/RD/PHE | 04/11/2022 | 0 | Resource Division | 28.75 | 0 | 0 | 0
2084 | UTTAR DINAJPUR | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ , SM/11643 | New | Construction of OHR & other allied works of BAGHAN and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal. | 589/RD/PHE | 24/02/2023 | 1042 | PRASANTA DUTTA | 137.78 | 0 | 0 | 61
2085 | UTTAR DINAJPUR | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ , SM/11643 | New | Additional Pipe Line For Providing FHTC at Baghan PWSS at Kaliaganj Block of Uttar Dinajpur District Under Raiganj Division ,PHE Dte.(New PWSS) | 1694/RD/PHE | 10/06/2024 | 45 | PRASANTA DUTTA | 9.75 | 0 | 0 | 0
2086 | UTTAR DINAJPUR | Malda Mechanical | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ , SM/11643 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAGHAN Water Supply Scheme T/W no. II in the District of Uttar Dinajpur | 261/MLMD | 24/02/2023 | 90 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 12.99 | 0 | 0 | 100
2087 | UTTAR DINAJPUR | Malda Mechanical | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ , SM/11643 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAGHAN Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 260/MLMD | 24/02/2023 | 90 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 12.99 | 0 | 0 | 100
2088 | UTTAR DINAJPUR | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ , SM/11643 | New | Wayleave/track crossing proposal with application ID:NFR-KIR-2024-WL-08 under katihar division of northeast frontier railway in connection with Baghan PWSS in kaliyaganj block under Raiganj division PHE Dte. | BP-2024-25-103 | 09/07/2024 | 0 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 6.13 | 0 | 0 | 0
2089 | UTTAR DINAJPUR | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ , SM/11643 | New | Wayleave/ track crossing proposal with application ID : NFR-KIR-2024-WL-08 under Katihar Division of Northeast Frontier Railway in connection with Baghan PWSS in Kaliyaganj Block under Raiganj Division PHE Dte. | BP-2024-25-67 | 06/06/2024 | 0 | EXECUTIVE ENGINEER | 0.11 | 0 | 0 | 0
2090 | UTTAR DINAJPUR | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ , SM/11643 | New | Implementation of Baghan and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division , PHE Dte, Govt. of West Bengal. | 1507/RD/PHE | 18/08/2022 | 1232 | PRASANTA DUTTA | 121.02 | 0 | 0 | 70
2091 | UTTAR DINAJPUR | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ , SM/11643 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAGHAN Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 566/RD/PHE | 05/03/2024 | 405 | M/S P.S. ENTERPRISE | 22.76 | 0 | 0 | 80
2092 | UTTAR DINAJPUR | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ , SM/11643 | New | Trial Run For Baghan PWSS under Kaliaganj Block under Raiganj Division ,PHE Dte. for 3 months | 544/RD/PHE | 12/02/2025 | 90 | PRASANTA DUTTA | 0.88 | 0 | 0 | 0
2093 | UTTAR DINAJPUR | Raiganj Division | BAGHAN PIPE WATER SUPPLY SCHEME IN KALIAGANJ , SM/11643 | New | Jack Pushing of M.S. Pipe of 200 mm dia. Through 600 mm dia. M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 37/8 to 37/9 near Kaliyaganj Railway Station (KAJ) for Baghan and it's adjoining mouzas water supply scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 2832/RD/PHE | 23/09/2024 | 207 | RAY CONSTRUCTION &CO. | 27.72 | 0 | 0 | 100
2094 | UTTAR DINAJPUR | Raiganj Division | JIAKHORI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13738 | New | Material Requisition To Resource Division | 1476/RD/PHE | 16/05/2023 | 0 | Resource Division | 43.66 | 0 | 0 | 0
2095 | UTTAR DINAJPUR | Malda Mechanical | JIAKHORI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13738 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Jiakhori Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015618) | 2506/MLMD | 04/08/2023 | 960 | MAA BHABOTARINE ENTERPRISE. | 28.31 | 0 | 0 | 74
2096 | UTTAR DINAJPUR | Malda Mechanical | JIAKHORI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13738 | New | Quotation for new service connection at JIAKHORI PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/13738) | BP-2024-25-301 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 3.98 | 0 | 0 | 0
2097 | UTTAR DINAJPUR | Raiganj Division | JIAKHORI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13738 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
2098 | UTTAR DINAJPUR | Raiganj Division | JIAKHORI PIPED WATER SUPPLY SCHEME AT CHOPRA BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13738 | New | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at JIAKHORI PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | 1211/RD/PHE | 25/04/2025 | 45 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 69.49 | 0 | 0 | 0
2099 | UTTAR DINAJPUR | Raiganj Division | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13012 | New | Preparation & submission of DPR for proposed FATEPUR (Kantirpa-Fatepur) PWSS under Karandighi Block. | 617/RD/PHE | 16/03/2022 | 30 | ECO CARE | 6.64 | 0 | 0 | 0
2100 | UTTAR DINAJPUR | Malda Mechanical | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13012 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Fatepur, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003227345 | 21/09/2023 | 90 | W.B.S.E.D.C.LTD | 5.69 | 0 | 0 | 100
2101 | UTTAR DINAJPUR | Malda Mechanical | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13012 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Fatepur, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003227134 | 21/09/2023 | 90 | W.B.S.E.D.C.LTD | 3.84 | 0 | 0 | 100
2102 | UTTAR DINAJPUR | Raiganj Division | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13012 | New | Material Requisition To Resource Division | 1218/RD/PHE | 02/05/2023 | 0 | Resource Division | 97.41 | 0 | 0 | 0
2103 | UTTAR DINAJPUR | Raiganj Division | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13012 | New | Additional pipeline and other ancillary works at Fatepur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | 3780/RD/PHE | 19/12/2024 | 45 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 42.77 | 0 | 0 | 0
2104 | UTTAR DINAJPUR | Malda Mechanical | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13012 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Fatepur ,Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-464 | 17/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.96 | 0 | 0 | 0
2105 | UTTAR DINAJPUR | Raiganj Division | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13012 | New | Implementation of FATEPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 554/RD/PHE | 23/02/2023 | 825 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 484.38 | 0 | 0 | 60
2106 | UTTAR DINAJPUR | Raiganj Division | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13012 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under FATEPUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 607/RD/PHE | 05/03/2024 | 135 | M/S ARVI CONSTRUCTION | 22.58 | 0 | 0 | 60
2107 | UTTAR DINAJPUR | Raiganj Division | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13012 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Fatepur Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | 1950/RD/PHE | 01/07/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.35 | 0 | 0 | 0
2108 | UTTAR DINAJPUR | Malda Mechanical | Fatepur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13012 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head work site at T/W no. I of Fatepur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015104) | 2497/MLMD | 04/08/2023 | 600 | ANIMA ENTERPRISE | 29.56 | 0 | 0 | 100
2109 | UTTAR DINAJPUR | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13013 | New | Laying of Pipe line at KACHARA Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, P.H.E Dte. | 1535/RD/PHE | 24/05/2023 | 45 | M/S P.S. ENTERPRISE | 14.82 | 0 | 0 | 95
2110 | UTTAR DINAJPUR | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13013 | New | Preparation & Submission of DPR for proposed Kochra Piped Water Supply Scheme under Karandighi Development Block. | 618/RD/PHE | 16/03/2022 | 30 | ECO CARE | 5.16 | 0 | 0 | 0
2111 | UTTAR DINAJPUR | Malda Mechanical | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13013 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Kachara PWSS , Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003220425 | 19/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.49 | 0 | 0 | 100
2112 | UTTAR DINAJPUR | Malda Mechanical | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13013 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Kachara PWSS , Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003220426 | 08/09/2023 | 90 | W.B.S.E.D.C.LTD | 5.57 | 0 | 0 | 100
2113 | UTTAR DINAJPUR | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13013 | New | Material Requisition To Resource Division | 582/RD/PHE | 24/02/2023 | 0 | Resource Division | 97.41 | 0 | 0 | 0
2114 | UTTAR DINAJPUR | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13013 | New | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 4(Four) Month (01/03/2024 to 30/06/2024). | 472/RD/PHE | 28/02/2024 | 121 | PRITAM SARKAR | 1.6 | 0 | 0 | 0
2115 | UTTAR DINAJPUR | Malda Mechanical | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13013 | New | Additional quotation for HT cable at KACHARA PH-II under Karandighi ccc under Uttar Dinajpur. | BP-2023-24-583 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 6.99 | 0 | 0 | 0
2116 | UTTAR DINAJPUR | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13013 | New | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | BP-2024-25-26 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 3.85 | 0 | 0 | 0
2117 | UTTAR DINAJPUR | Malda Mechanical | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13013 | New | Additional quotation for HT cable at KACHARA PH-I under Karandighi ccc under Uttar Dinajpur. | BP-2023-24-584 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 2.1 | 0 | 0 | 0
2118 | UTTAR DINAJPUR | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13013 | New | Implementation of KACHARA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 97/RD/PHE | 19/01/2023 | 1443 | SANYAL ENTERPRISE | 370.28 | 0 | 0 | 65
2119 | UTTAR DINAJPUR | Malda Mechanical | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13013 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Kachara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015107) | 2751/MLMD | 14/08/2023 | 2005 | DAS CONSTRUCTION | 32.67 | 0 | 0 | 71
2120 | UTTAR DINAJPUR | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13013 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Kochra PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3762/RD/PHED | 18/12/2024 | 45 | UTTAM SAHA | 14.05 | 0 | 0 | 0
2121 | UTTAR DINAJPUR | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13013 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KACHARA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 604/RD/PHE | 05/03/2024 | 569 | BIMAL KUMAR SINHA | 22.57 | 0 | 0 | 65
2122 | UTTAR DINAJPUR | Raiganj Division | Kachara Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13013 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kachra Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | 2510/RD/PHE | 12/09/2025 | 180 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 29.58 | 0 | 0 | 0
2123 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Material Requisition To Resource Division | 2264/RD/PHE | 23/12/2022 | 0 | Resource Division | 119.05 | 0 | 0 | 0
2124 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Repairing of Pump House at 2nd tube well site in connection with Augmentation of Karandighi Zone -II Piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | 370/RD/PHE | 07/02/2023 | 45 | ALI ENTERPRISE ALIENTERPRISE.HEM@GMAIL.COM | 2.1 | 0 | 0 | 100
2125 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Karandighi, Zone-II, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003118849 | 26/03/2023 | 7 | W.B.S.E.D.C.LTD | 0.55 | 0 | 0 | 0
2126 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 271/MLMD | 24/02/2023 | 60 | RAMCHANDRA BASAK | 0.29 | 0 | 0 | 100
2127 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Claim for purchase of fuel for hiring of inspection for different site visit use for Assistant Engineer-I ,Under Mechanical Division, P.H.E. Dte. | 271/MLMD. | 24/02/2023 | 60 | RAMCHANDRA BASAK | 0.51 | 0 | 0 | 100
2128 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Balance Laying of pipeline with Construction Of Boundary Wall With Gate and Approach Road at Head Work Site, 2nd Tube-Well under Augmentation Of Karandighi Zone-II PWSS at Karandighi Block under Raiganj Division,PHE dte. | 3289/RD/PHE | 20/11/2024 | 45 | KARTICK BISWAS | 36.07 | 0 | 0 | 0
2129 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Construction of Over Head Reservoir(Capacity-300 Cum) of KARANDIGHI(Zone-II) Pipe Water Supply Scheme in connection with Augmentation at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 80/RD/PHE | 17/01/2023 | 240 | M/S SARKAR ENTERPRISE (ABDULGHATA) MSSARKAR.RNJ@GMAIL.COM | 86.13 | 0 | 0 | 1
2130 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Karandighi Zone-II Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 369/RD/PHE | 07/02/2023 | 45 | M/S DAS ENTERPRISE SUMAN974967@GMAIL.COM | 5.03 | 0 | 0 | 100
2131 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of KARANDIGHI Water Supply Scheme (Zone-II) T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 248/MLMD | 24/02/2023 | 90 | MANAS KUMAR SAHA | 10.46 | 0 | 0 | 100
2132 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of KARANDIGHI Water Supply Scheme (Zone-II) T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 249/MLMD | 24/02/2023 | 90 | SOVON KUMAR DAS. | 10.55 | 0 | 0 | 100
2133 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | FHTC (Functional Household Tap Connection) for Karandighi Zone-II Water Supply Scheme [Augmentation Scheme] in Karandighi Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2017/RD/PHE | 17/11/2022 | 629 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 56.82 | 0 | 0 | 60
2134 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Augmentation of KARANDIGHI(Zone-II)Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal.(2nd Call). | 2047/RD/PHE | 21/11/2022 | 951 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 154.85 | 0 | 0 | 70
2135 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Augmentation of Karandighi Water Supply Scheme, ( Zone- II) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011647) | 2130/MLMD | 07/07/2023 | 1915 | M/S. KUNDU CONSTRACTION | 6.97 | 0 | 0 | 80
2136 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
2137 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Providing FHTC in connection with augmentation of Karandighi Zone-II Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | 48/RD/PHE | 03/01/2025 | 45 | AJIT PRAMANIK | 15.76 | 0 | 0 | 0
2138 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Trial Run For Karandighi Zone-II PWSS under Karandighi Block under Raiganj Division ,PHE Dte. for 3 months | 546/RD/PHE | 12/02/2025 | 90 | AJIT PRAMANIK | 0.88 | 0 | 0 | 0
2139 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Karandighi Zone-II in Karandighi Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11794 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Karandighi Zone-II Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | 2499/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 29.58 | 0 | 0 | 0
2140 | UTTAR DINAJPUR | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | Preparation & Submission of DPR for proposed Barhans Piped Water Supply Scheme under Karandighi Development Block. | 616/RD/PHE | 16/03/2022 | 30 | ENVIROTECH SOLUTIONS | 3.11 | 0 | 0 | 0
2141 | UTTAR DINAJPUR | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | Preparation & Submission of DPR for Proposed Barhans Piped Water Supply Scheme under Karandighi block. | 616/RD/PHED | 16/03/2022 | 30 | ENVIROTECH SOLUTIONS | 3.11 | 0 | 0 | 0
2142 | UTTAR DINAJPUR | Malda Mechanical | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Barhans PWSS , Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003220342 | 07/09/2023 | 90 | W.B.S.E.D.C.LTD | 5.38 | 0 | 0 | 100
2143 | UTTAR DINAJPUR | Malda Mechanical | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Barhans PWSS , Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003220337 | 07/09/2023 | 90 | W.B.S.E.D.C.LTD | 14.71 | 0 | 0 | 100
2144 | UTTAR DINAJPUR | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | Material Requisition To Resource Division | 586/RD/PHE | 24/02/2023 | 0 | Resource Division | 15.91 | 0 | 0 | 0
2145 | UTTAR DINAJPUR | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | Material Requisition To Resource Division | 2352/RD/PHE | 11/08/2023 | 0 | Resource Division | 16.43 | 0 | 0 | 0
2146 | UTTAR DINAJPUR | Malda Mechanical | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite at T/W no. I of Barhans Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014865) | 2471/MLMD | 04/08/2023 | 815 | NIRMAN. | 24.86 | 0 | 0 | 72
2147 | UTTAR DINAJPUR | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | Hiring of well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, RWS Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire RWS Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 4(Four) Month (01/03/2024 to 30/06/2024). | 472/RD/PHE | 28/02/2024 | 121 | PRITAM SARKAR | 1.6 | 0 | 0 | 0
2148 | UTTAR DINAJPUR | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BARHANS PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 603/RD/PHE | 05/03/2024 | 360 | M/S MAA BOLLA CONSTRUCTION | 22.57 | 0 | 0 | 100
2149 | UTTAR DINAJPUR | Malda Mechanical | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | Additional Quotation for HT AB cable at BARHANS PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12779). | BP-2024-25-279 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 6.56 | 0 | 0 | 0
2150 | UTTAR DINAJPUR | Malda Mechanical | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | Additional Quotation for new service connection at BARHANS PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12779) | BP-2024-25-486 | 09/09/2024 | 0 | W.B.S.E.D.C.LTD | 3.4 | 0 | 0 | 0
2151 | UTTAR DINAJPUR | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | Implementation of BARHANS and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte | 99/RD/PHE | 19/01/2023 | 1443 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 271.31 | 0 | 0 | 62
2152 | UTTAR DINAJPUR | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Barhans PWSS at Karandighi Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3761/RD/PHED | 18/12/2024 | 30 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 11.73 | 0 | 0 | 0
2153 | UTTAR DINAJPUR | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.Vehicle no. WB74AP 7552) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month( period from 27.11.2024 to 26.05.2025). | 3446/RD/PHE | 26/11/2024 | 181 | M/S SARKAR ENTERPRISE SILIGURI | 2.4 | 0 | 0 | 0
2154 | UTTAR DINAJPUR | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Barhans Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | 2488/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 18.74 | 0 | 0 | 0
2155 | UTTAR DINAJPUR | Raiganj Division | Barhans Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12779 | New | Additional Laying distribution and Rising Main of Pipe line for Barhans Pipe Water Supply Scheme (Barhans New PWSS) at Karandighi Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 3393/RD/PHE | 12/12/2023 | 405 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 7.87 | 0 | 0 | 100
2156 | UTTAR DINAJPUR | Raiganj Division | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12778 | New | Material Requisition To Resource Division | 1122/RD/PHE | 24/04/2023 | 0 | Resource Division | 41.33 | 0 | 0 | 0
2157 | UTTAR DINAJPUR | Malda Mechanical | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12778 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Athiala Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014486) | 2459/MLMD | 04/08/2023 | 1027 | JAL PRAVAHIKA PVT. LTD. | 28.11 | 0 | 0 | 63
2158 | UTTAR DINAJPUR | Malda Mechanical | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12778 | New | Quotation for new service connection at Athiala PH-II (Goalpokher ccc). | BP-2023-24-543 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 18.86 | 0 | 0 | 0
2159 | UTTAR DINAJPUR | Malda Mechanical | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12778 | New | Quotation for new service connection at Athiala PH-I (Goalpokher ccc) | BP-2023-24-542 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 18.09 | 0 | 0 | 0
2160 | UTTAR DINAJPUR | Raiganj Division | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12778 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2023 to 30.06.2024.) | 1710/RD/PHE | 26/06/2023 | 366 | MD ZAFAR EQUEBAL | 4.8 | 0 | 0 | 100
2161 | UTTAR DINAJPUR | Raiganj Division | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12778 | New | Providing FHTC in connection with Athiala Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 1200/RD/PHE | 25/04/2025 | 30 | DEEP CONSTRUCTION | 11.93 | 0 | 0 | 0
2162 | UTTAR DINAJPUR | Raiganj Division | ATHIALA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12778 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at ATHIALA PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. | 1203/RD/PHE | 25/04/2025 | 45 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 40.92 | 0 | 0 | 0
2163 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12782 | New | Material Requisition To Resource Division | 1121/RD/PHE | 24/04/2023 | 0 | Resource Division | 27.44 | 0 | 0 | 0
2164 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12782 | New | Quotation for new service connection at Dakshin Sahapur PH-II (Goalpokher ccc) | BP-2023-24-525 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 4.17 | 0 | 0 | 0
2165 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12782 | New | Quotation for new service connection at Dakshin Sahapur PH-I (Goalpokher ccc) | BP-2023-24-524 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 6.08 | 0 | 0 | 0
2166 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12782 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dakshin Sahapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014427) | 2366/MLMD | 28/07/2023 | 1064 | WEST BENGAL ENGINEERING COMPANY. | 26.18 | 0 | 0 | 77
2167 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12782 | New | Providing FHTC in connection with Dakhshin Sahapur Pipe Water Supply Scheme at Goalpukhur-I Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) | 1175/RD/PHE | 23/04/2025 | 30 | BIKASH KAR | 8.09 | 0 | 0 | 0
2168 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12782 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakshin Sahapur Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | 1804/RD/PHE | 24/06/2025 | 180 | JAL PRAVAHIKA PRIVATE LIMITED | 29.55 | 0 | 0 | 0
2169 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN SAHAPUR Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12782 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at DAKSHIN SAHAPUR PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | 2094/RD/PHE | 15/07/2025 | 180 | M/S SACHIN KUMAR | 39.1 | 0 | 0 | 0
2170 | UTTAR DINAJPUR | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/14146 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
2171 | UTTAR DINAJPUR | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/14146 | New | Material Requisition To Resource Division | 2237/RD/PHE | 02/08/2023 | 0 | Resource Division | 27.73 | 0 | 0 | 0
2172 | UTTAR DINAJPUR | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/14146 | New | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehical No. WB60T 9215) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 17.10.2024 to 14.01.2025) | 3045/RD/PHE | 04/10/2024 | 90 | ARNAB DUTTA | 1.2 | 0 | 0 | 0
2173 | UTTAR DINAJPUR | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/14146 | New | Construction Culvert with Hume Pipe Across PWD Borrow Pit for Making Accessible Road at Bahin Paharpur PWSS Head Work Site at Hemtabad Block under Raiganj Division, P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3010/RD/PHE | 03/10/2024 | 30 | BHOLA PAUL | 4.22 | 0 | 0 | 0
2174 | UTTAR DINAJPUR | Malda Mechanical | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/14146 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.II of Bahin Paharpur, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-469 | 26/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.49 | 0 | 0 | 0
2175 | UTTAR DINAJPUR | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/14146 | New | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | BP-2024-25-25 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 14.43 | 0 | 0 | 0
2176 | UTTAR DINAJPUR | Malda Mechanical | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/14146 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of Bahin Paharpur, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-468 | 26/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.12 | 0 | 0 | 0
2177 | UTTAR DINAJPUR | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/14146 | New | Implementation of BAHIN PAHARPUR and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 563/RD/PHE | 23/02/2023 | 1175 | BHOLA PAUL | 305.86 | 0 | 0 | 53
2178 | UTTAR DINAJPUR | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/14146 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
2179 | UTTAR DINAJPUR | Malda Mechanical | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/14146 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite at T/W no. I of Bahin Paharpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017738) | 2464/MLMD | 04/08/2023 | 562 | SUBHRA ENTERPRISE | 25.01 | 0 | 0 | 93
2180 | UTTAR DINAJPUR | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/14146 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bahin Paharpur PWSS at Hemtabad Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3746/RD/PHE | 18/12/2024 | 135 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 32.59 | 0 | 0 | 0
2181 | UTTAR DINAJPUR | Raiganj Division | Bahin Paharpur Piped Water Supply Scheme at Hemtabad block under Uttar Dinajpur District. , SM/14146 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAHINPAHARPUR PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 673/RD/PHE | 05/03/2024 | 45 | BHOLA PAUL | 22.58 | 0 | 0 | 100
2182 | UTTAR DINAJPUR | Raiganj Division | PUAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13550 | New | Material Requisition To Resource Division | 984/RD/PHE | 30/03/2023 | 0 | Resource Division | 30.7 | 0 | 0 | 0
2183 | UTTAR DINAJPUR | Malda Mechanical | PUAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13550 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Puar Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015848) | 2524/MLMD | 04/08/2023 | 960 | MERCURY ENGINEERING COMPANY. | 29.75 | 0 | 0 | 75
2184 | UTTAR DINAJPUR | Malda Mechanical | PUAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13550 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte | 1670/MLMD | 25/06/2024 | 62 | RAMCHANDRA BASAK | 0.78 | 0 | 0 | 100
2185 | UTTAR DINAJPUR | Raiganj Division | PUAR PIPED WATER SUPPLY SCHEME AT GOALPOKHAR-II BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/13550 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
2186 | UTTAR DINAJPUR | Raiganj Division | MIRJADPUR Piped Water Supply Scheme , SM/14627 | New | Material Requisition To Resource Division | 900/RD/PHE | 28/03/2023 | 0 | Resource Division | 40.24 | 0 | 0 | 0
2187 | UTTAR DINAJPUR | Malda Mechanical | MIRJADPUR Piped Water Supply Scheme , SM/14627 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Mirjadpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016582) | 2447/MLMD | 04/08/2023 | 1027 | DILIP MAHATO. | 27.46 | 0 | 0 | 0
2188 | UTTAR DINAJPUR | Raiganj Division | MIRJADPUR Piped Water Supply Scheme , SM/14627 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
2189 | UTTAR DINAJPUR | Raiganj Division | CHOUKAI Pipe Water Supply Scheme , SM/15304 | New | Material Requisition To Resource Division | 901/RD/PHE | 28/03/2023 | 0 | Resource Division | 39.85 | 0 | 0 | 0
2190 | UTTAR DINAJPUR | Malda Mechanical | CHOUKAI Pipe Water Supply Scheme , SM/15304 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Choukai Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018404) | 3700/MLMD | 29/11/2023 | 760 | MANIK CHANDRA SAHA. | 27.45 | 0 | 0 | 73
2191 | UTTAR DINAJPUR | Raiganj Division | CHOUKAI Pipe Water Supply Scheme , SM/15304 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
2192 | UTTAR DINAJPUR | Raiganj Division | KOTGRAM Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. , SM/16227 | New | Material Requisition To Resource Division | 2232/RD/PHE | 02/08/2023 | 0 | Resource Division | 43.48 | 0 | 0 | 0
2193 | UTTAR DINAJPUR | Malda Mechanical | KOTGRAM Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. , SM/16227 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Kotgram Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018271) | 2759/MLMD | 14/08/2023 | 180 | M/S MANABESH ROY | 25 | 0 | 0 | 59
2194 | UTTAR DINAJPUR | Raiganj Division | KOTGRAM Piped Water Supply Scheme at Raiganj Block under Uttar Dinajpur District. , SM/16227 | New | Implementation of KOTGRAM andit's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1272/RD/PHE | 08/05/2023 | 969 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 480.8 | 0 | 0 | 12
2195 | UTTAR DINAJPUR | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR , SM/18160 | New | Material Requisition To Resource Division | 2263/RD/PHE | 03/08/2023 | 0 | Resource Division | 14.12 | 0 | 0 | 0
2196 | UTTAR DINAJPUR | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR , SM/18160 | New | Construction of Approach Road,Laying of Pipe Line,Fhtc and other Allied Works of Hasua Pwss within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3563/RD/PHE | 05/12/2024 | 45 | M/S SARKAR ENTERPRISE | 47.11 | 0 | 0 | 0
2197 | UTTAR DINAJPUR | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR , SM/18160 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 15.07.2024 to 16.07.2024 and from 18.07.2024 to 19.07.2024. | BP-2024-25-181 | 30/08/2024 | 0 | M/S DILWAR HOSAIN | 0.08 | 0 | 0 | 0
2198 | UTTAR DINAJPUR | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR , SM/18160 | New | Hiring of well-maintained Diesel Maxi Cab having Luxury Taxi Permit for contract carriage (Non-A.C.) for the office of the Executive Engineer, Raiganj Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12(twelve) Month.Period for 12(Twelve) Month (01/07/2023 to 30/06/2024). | 1724/RD/PHE | 28/06/2023 | 366 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 4.8 | 0 | 0 | 100
2199 | UTTAR DINAJPUR | Malda Mechanical | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR , SM/18160 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. I & II of Hasua Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020862) | 2709/MLMD | 11/08/2023 | 870 | MUKHERJEE ART CENTRE | 20.41 | 0 | 0 | 0
2200 | UTTAR DINAJPUR | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR , SM/18160 | New | Implementation of HASUA and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2600/RD/PHE | 13/09/2023 | 510 | M/S EVEREST INFRATECH INC | 220.85 | 0 | 0 | 45
2201 | UTTAR DINAJPUR | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR , SM/18160 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under HASUA PWSS at Itahar Block under Raiganj Division, PHE Dte. | 623/RD/PHE | 05/03/2024 | 45 | WAMOL ENGINEERS CO-OPERATIVE SOCIETY LTD. WAMOLENGICOOPSOCIETYLTD@GMAIL.COM | 24.48 | 0 | 0 | 40
2202 | UTTAR DINAJPUR | Raiganj Division | HASUA PIPED WATER SUPPLY SCHEME IN ITAHAR BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR , SM/18160 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Hasua Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 30 M3/hr. | 2480/RD/PHE | 12/09/2025 | 180 | AJIT PRAMANIK | 17.34 | 0 | 0 | 0
2203 | UTTAR DINAJPUR | Raiganj Division | BINAPUR PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18165 | New | Implementation of BINAPUR and it's adjoining mouzas Pipe Water Supply Scheme at CHOPRA Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | 2378/RD/PHE | 14/08/2023 | 90 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 53.95 | 0 | 0 | 0
2204 | UTTAR DINAJPUR | Raiganj Division | BINAPUR PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18165 | New | Material Requisition To Resource Division | 3315/RD/PHE | 05/12/2023 | 0 | Resource Division | 4.8 | 0 | 0 | 0
2205 | UTTAR DINAJPUR | Malda Mechanical | BINAPUR PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18165 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Binapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020936) | 2706/MLMD | 11/08/2023 | 1020 | M/S JIBU SINGHA | 7.2 | 0 | 0 | 0
2206 | UTTAR DINAJPUR | Raiganj Division | BINAPUR PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18165 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | 1816/RD/PHE | 26/06/2024 | 198 | MD ZAFAR EQUEBAL | 2.6 | 0 | 0 | 100
2207 | UTTAR DINAJPUR | Raiganj Division | DHABAIL PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18169 | New | Material Requisition To Resource Division | 2255/RD/PHE | 03/08/2023 | 0 | Resource Division | 3.42 | 0 | 0 | 0
2208 | UTTAR DINAJPUR | Malda Mechanical | DHABAIL PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18169 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dhabail, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-207 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.05 | 0 | 0 | 0
2209 | UTTAR DINAJPUR | Malda Mechanical | DHABAIL PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18169 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Dhabail Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020919) | 2702/MLMD | 11/08/2023 | 568 | SOVA ENTERPRISE. | 7.17 | 0 | 0 | 100
2210 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kaliganj (Tharais village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. , SM/17741 | Augmentation | Preparation of DPR for drinking water supply scheme to facilitate 4(Four)Nos. Augmentation Scheme and 1(One) No. New PWSS (List Enclosed) Uncovered mouzas under Uttar Dinajpur District which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Raiganj Division P.H.E. Dte. | 2226/RD/PHE | 31/07/2023 | 15 | RADIANT | 11.57 | 0 | 0 | 100
2211 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kaliganj (Tharais village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. , SM/17741 | Augmentation | Material Requisition To Resource Division | 1103/RD/PHE | 20/04/2023 | 0 | Resource Division | 4.82 | 0 | 0 | 0
2212 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kaliganj (Tharais village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. , SM/17741 | Augmentation | Construction Of Boundary Wall With Gate at in connection with Augmentation Of KALIGANJ(THARAIS) PWSS at ITAHAR Block under Raiganj Division,PHE dte. | 3575/RD/PHE | 05/12/2024 | 30 | SUBHASIS MAJUMDER | 11.77 | 0 | 0 | 0
2213 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Kaliganj (Tharais village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. , SM/17741 | Augmentation | Augmentation of Kaliganj (Tharais) and it's adjoining mouzas Pipe Water Supply Scheme at Itahar Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House) | 881/RD/PHE | 27/03/2023 | 1080 | BHOWMICK ENTERPRISE | 61.85 | 0 | 0 | 1
2214 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Kaliganj (Tharais village) Piped Water Supply Scheme at Itahar block under Uttar Dinajpur District. , SM/17741 | Augmentation | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. I of Tharais Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018631) | 2646/MLMD | 10/08/2023 | 871 | J.K. ENGINEERING CO. | 7.11 | 0 | 0 | 0
2215 | UTTAR DINAJPUR | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division , SM/18123 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Majlishpur and adjacent Water Supply Schemes at Goalpokhor-I Block in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016626) | 2143/MLMD | 07/07/2023 | 1915 | SWITCHING AVO ELECTRO POWER LTD | 41.82 | 0 | 0 | 0
2216 | UTTAR DINAJPUR | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division , SM/18123 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Malgaon and adjacent Water Supply Schemes at Kaliyaganj Block in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016626) | 2142/MLMD | 07/07/2023 | 1915 | A.K. INDUSTRIES | 41.83 | 0 | 0 | 0
2217 | UTTAR DINAJPUR | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division , SM/18123 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Khesra Water Supply Schemes at Itahar Block in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016626) | 2141/MLMD | 07/07/2023 | 1915 | BINGAS ELECTRICAL ELECTRONICS AND SOLAR SYSTEM | 27.84 | 0 | 0 | 0
2218 | UTTAR DINAJPUR | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division , SM/18123 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Ghrinigaon Khas and adjacent Water Supply Schemes at Chopra Block in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016626) | 2815/MLMD | 17/08/2023 | 1915 | DAS CONSTRUCTION | 20.89 | 0 | 0 | 0
2219 | UTTAR DINAJPUR | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division , SM/18123 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Gunabari Water Supply Schemes at Islampur Block in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016626) | 2814/MLMD | 17/08/2023 | 1915 | AMITAVA CHAKRABORTY | 6.7 | 0 | 0 | 0
2220 | UTTAR DINAJPUR | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division , SM/18123 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Barua and adjacent Water Supply Schemes at Raiganj Block in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016626) | 3630/MLMD | 23/11/2023 | 1915 | BINGAS ELECTRICAL ELECTRONICS AND SOLAR SYSTEM | 44.19 | 0 | 0 | 0
2221 | UTTAR DINAJPUR | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid-connected, ground mounted solar PV Systems with Net Metering of twenty eight nos. PWSS in the district of Uttar Dinajpur under Malda Mechanical Division , SM/18123 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Gutin and adjacent Water Supply Schemes at Hemtabad Block in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016626) | 2813/MLMD | 17/08/2023 | 1915 | M/S. KUNDU CONSTRACTION | 20.9 | 0 | 0 | 79
2222 | UTTAR DINAJPUR | Raiganj Division | Baligora Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. , SM/17631 | New | Material Requisition To Resource Division | 1045/RD/PHE | 05/04/2023 | 0 | Resource Division | 30.48 | 0 | 0 | 0
2223 | UTTAR DINAJPUR | Malda Mechanical | Baligora Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. , SM/17631 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Baligora Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/003985) | 2435/MLMD | 04/08/2023 | 937 | SOUNAK ENTERPRISE | 26.22 | 0 | 0 | 0
2224 | UTTAR DINAJPUR | Raiganj Division | Baligora Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. , SM/17631 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,Construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 25 nos. Piped water supply Schemes within GOALPOKHAR-II Dev. Block of Uttar Dinajpur District under Raiganj Division ,PHE Dte. | 2590/RD/PHE | 11/09/2023 | 1080 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 12931.07 | 0 | 0 | 35
2225 | UTTAR DINAJPUR | Raiganj Division | Baligora Piped Water Supply Scheme at Goalpokhar-II Block under Uttar Dinajpur District. , SM/17631 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur.For 12(twelve) Months. | 2752/RD/PHE | 05/10/2023 | 366 | SISIR KUMAR DUTTA | 4.8 | 0 | 0 | 0
2226 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Itahar Zone-II Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. , SM/18290 | Augmentation | Material Requisition To Resource Division | 1189/RD/PHE | 27/04/2023 | 0 | Resource Division | 115.81 | 0 | 0 | 0
2227 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Itahar Zone-II Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. , SM/18290 | Augmentation | Augmentation of ITAHAR Zone-II and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under Raiganj Division.PHE Dte. | 1998/RD/PHE | 13/07/2023 | 928 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 639.84 | 0 | 0 | 10
2228 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Itahar Zone-II Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. , SM/18290 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound yard lighting arrangement at T/W no. I of Augmentation of Itahar Water Supply Scheme(Zone-II) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018223) | 2645/MLMD | 10/08/2023 | 841 | M/S TRILOCHAN CONSTRUCTION CO. | 26.7 | 0 | 0 | 72
2229 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Itahar Zone-II Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. , SM/18290 | Augmentation | Construction Of Approach Road,Laying Of Pipe Line,Fhtc And Other Allied Works Of Itahar Zone - Ii Pwss Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3567/RD/PHE | 05/12/2024 | 91 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 89.77 | 0 | 0 | 0
2230 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Itahar Zone-II Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. , SM/18290 | Augmentation | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.Vehicle no. WB74AP 7552) for the office of the Assistant Engineer, Head Quarter, Raiganj Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 6(Six) Month( period from 27.11.2024 to 26.05.2025). | 3446/RD/PHE | 26/11/2024 | 181 | M/S SARKAR ENTERPRISE SILIGURI | 2.4 | 0 | 0 | 0
2231 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Itahar Zone-II Piped Water Supply Scheme in Itahar Block of Uttar Dinajpur District. , SM/18290 | Augmentation | Supply, installation and commissioning of electro-mechanical components at T/W No. III of Augmentation of ITAHAR water supply scheme (Zone- II) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 1691/MLMD | 28/03/2025 | 120 | M/S. KUNDU CONSTRACTION | 11.07 | 0 | 0 | 0
2232 | UTTAR DINAJPUR | Raiganj Division | KUCHILA PWSS , SM/18325 | New | Material Requisition To Resource Division | 600/RD/PHE | 27/02/2023 | 0 | Resource Division | 53.38 | 0 | 0 | 0
2233 | UTTAR DINAJPUR | Raiganj Division | KUCHILA PWSS , SM/18325 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KUCHILA PWSS at Islampur Block under Raiganj Division, PHE Dte. | 547/RD/PHE | 05/03/2024 | 45 | ASHRAFIA BUILDERS | 22.45 | 0 | 0 | 0
2234 | UTTAR DINAJPUR | Raiganj Division | KUCHILA PWSS , SM/18325 | New | Additional pipeline and other ancillary works at Kuchila piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | 3483/RD/PHE | 02/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 46.55 | 0 | 0 | 0
2235 | UTTAR DINAJPUR | Raiganj Division | KUCHILA PWSS , SM/18325 | New | MDR T01, RAMKRISHNAPUR TO MDR T10 DIMTI VIA BHARDRAKALI(ROAD CODE T06) | BP-2024-25-72 | 12/06/2024 | 0 | EXECUTIVE ENGINEER,WBSRDA,UTTAR DINAJPUR DIVISION | 15.49 | 0 | 0 | 0
2236 | UTTAR DINAJPUR | Raiganj Division | KUCHILA PWSS , SM/18325 | New | Implementation of KUCHILA and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2000/RD/PHE | 13/07/2023 | 896 | UTTAM SAHA | 736.01 | 0 | 0 | 40
2237 | UTTAR DINAJPUR | Malda Mechanical | KUCHILA PWSS , SM/18325 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Kuchila Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016546) | 2514/MLMD | 04/08/2023 | 937 | SUJOY RANJAN BHOWMICK | 29.4 | 0 | 0 | 0
2238 | UTTAR DINAJPUR | Raiganj Division | KUCHILA PWSS , SM/18325 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Kuchila Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 100 M3/hr. | 2508/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 36.36 | 0 | 0 | 0
2239 | UTTAR DINAJPUR | Raiganj Division | JAGDISHPUR PWSS , SM/18287 | New | Material Requisition To Resource Division | 33/RD/PHE | 06/01/2023 | 0 | Resource Division | 115.16 | 0 | 0 | 0
2240 | UTTAR DINAJPUR | Malda Mechanical | JAGDISHPUR PWSS , SM/18287 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Jagdispur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-548 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 7.62 | 0 | 0 | 0
2241 | UTTAR DINAJPUR | Malda Mechanical | JAGDISHPUR PWSS , SM/18287 | New | Additional Quotation for Tw-I of Jagadishpur water supply scheme in the district of Uttar Dinajpur. | BP-2024-25-546 | 01/10/2024 | 0 | W.B.S.E.D.C.LTD | 0.8 | 0 | 0 | 0
2242 | UTTAR DINAJPUR | Malda Mechanical | JAGDISHPUR PWSS , SM/18287 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Jagadispur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-549 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 5.13 | 0 | 0 | 0
2243 | UTTAR DINAJPUR | Raiganj Division | JAGDISHPUR PWSS , SM/18287 | New | Demand for placing necessary fund for the work Permanent restoration of damaged hard shoulder/flank of Makdampur- Bhatol Road caused due to pipe laying by PHED under Jagadishpur PWSS at different stretched of road under Uttar Dinajpur Highway Division. | BP-2024-25-195 | 18/09/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 21.58 | 0 | 0 | 0
2244 | UTTAR DINAJPUR | Raiganj Division | JAGDISHPUR PWSS , SM/18287 | New | Implementation of JAGADISHPUR and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division. | 2001/RD/PHE | 13/07/2023 | 911 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 759.23 | 0 | 0 | 50
2245 | UTTAR DINAJPUR | Malda Mechanical | JAGDISHPUR PWSS , SM/18287 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Jagdishpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012027) | 2507/MLMD | 04/08/2023 | 907 | GHOSH BROTHERS... | 36.72 | 0 | 0 | 87
2246 | UTTAR DINAJPUR | Raiganj Division | BHOMRA PWSS , SM/18627 | New | Material Requisition To Resource Division | 862/RD/PHE | 25/03/2023 | 0 | Resource Division | 79.68 | 0 | 0 | 0
2247 | UTTAR DINAJPUR | Malda Mechanical | BHOMRA PWSS , SM/18627 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I, II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Bhomra Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018346) | 3703/MLMD | 29/11/2023 | 180 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 37 | 0 | 0 | 78
2248 | UTTAR DINAJPUR | Raiganj Division | BHOMRA PWSS , SM/18627 | New | Wayleave/ track crossing proposal with application ID : NFR-KIR-2024-WL-09 under Katihar Division of Northeast Frontier Railway in connection with Bhomra PWSS in Raiganj Block under Raiganj Division PHE Dte. | BP-2024-25-68 | 06/06/2024 | 0 | EXECUTIVE ENGINEER | 0.1 | 0 | 0 | 0
2249 | UTTAR DINAJPUR | Raiganj Division | BHOMRA PWSS , SM/18627 | New | Way leave/track crossing proposal with application id: NFR-KIR-2024-WL-11 under Kathihar Division of North East Fronter Railway in connection with Bhomra PWSS in Raiganj Block under Raiganj Division, PHE Dte. | BP-2024-25-105 | 09/07/2024 | 0 | EXECUTIVE ENGINEER,RAIGANJ DIVISION,PHED | 6.04 | 0 | 0 | 0
2250 | UTTAR DINAJPUR | Malda Mechanical | BHOMRA PWSS , SM/18627 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Bhomra, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-616 | 04/03/2024 | 0 | W.B.S.E.D.C.LTD | 3 | 0 | 0 | 0
2251 | UTTAR DINAJPUR | Malda Mechanical | BHOMRA PWSS , SM/18627 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Bhomra, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-615 | 04/03/2024 | 0 | W.B.S.E.D.C.LTD | 2.41 | 0 | 0 | 0
2252 | UTTAR DINAJPUR | Malda Mechanical | BHOMRA PWSS , SM/18627 | New | Additional Quotation of Bhomra TW-I in the District of Uttar Dinajpur. | BP-2024-25-412 | 30/07/2024 | 0 | W.B.S.E.D.C.LTD | 1.26 | 0 | 0 | 0
2253 | UTTAR DINAJPUR | Raiganj Division | BHOMRA PWSS , SM/18627 | New | Implementation of BHOMRA and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under RaiganjDivision, PHE Dte. | 2293/RD/PHE | 04/08/2023 | 881 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 890.66 | 0 | 0 | 50
2254 | UTTAR DINAJPUR | Raiganj Division | BHOMRA PWSS , SM/18627 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Jhitkia, 2.Bhomra in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 2366/RD/PHE | 11/08/2023 | 540 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 79.6 | 0 | 0 | 100
2255 | UTTAR DINAJPUR | Raiganj Division | BHOMRA PWSS , SM/18627 | New | Approach road with land development of headwork site & 2nd tubewell site and road restoration of Bhomra PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 01/RD/PHE | 02/01/2025 | 45 | AJIT PRAMANIK | 19.24 | 0 | 0 | 0
2256 | UTTAR DINAJPUR | Raiganj Division | BHOMRA PWSS , SM/18627 | New | Jack Pushing of M.S. Pipe of 300 mm dia. Through 600 mm dia. M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 23/8 to 23/9 near Jhitkia Railway Station (RGJ) for Bhomra and it's adjoining mouzas water supply scheme under Raiganj Division, PHE Dte. In the district of Uttar Dinajpur. | 2833/RD/PHE | 23/09/2024 | 110 | RAY CONSTRUCTION &CO. | 28.76 | 0 | 0 | 100
2257 | UTTAR DINAJPUR | Raiganj Division | BHABANIPUR PWSS , SM/18629 | New | Material Requisition To Resource Division | 633/RD/PHE | 02/03/2023 | 0 | Resource Division | 81.83 | 0 | 0 | 0
2258 | UTTAR DINAJPUR | Raiganj Division | BHABANIPUR PWSS , SM/18629 | New | Laying of Additional pipeline with other ancillary works at different mouzas of BHABANIPUR PWSS under Islampur Sub-Division P.H.E. Dte. | 3499/RD/PHE | 02/12/2024 | 45 | M/S PINKI CONSTRUCTION | 34.81 | 0 | 0 | 0
2259 | UTTAR DINAJPUR | Malda Mechanical | BHABANIPUR PWSS , SM/18629 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Bhabanipur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018353) | 2733/MLMD | 14/08/2023 | 1047 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 41.69 | 0 | 0 | 0
2260 | UTTAR DINAJPUR | Raiganj Division | BHABANIPUR PWSS , SM/18629 | New | Implementation of BHABANIPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2473/RD/PHE | 24/08/2023 | 660 | M/S PINKI CONSTRUCTION | 974.94 | 0 | 0 | 66
2261 | UTTAR DINAJPUR | Raiganj Division | BHABANIPUR PWSS , SM/18629 | New | Construction of concrete pathway at Head Work Site Pump House,2nd TW Site & 3rd TW Site Pump House for BHABANIPUR Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | 3488/RD/PHE | 02/12/2024 | 30 | SANDIP SARKAR | 9.25 | 0 | 0 | 0
2262 | UTTAR DINAJPUR | Raiganj Division | BHABANIPUR PWSS , SM/18629 | New | Continuation Order for Hiring of well-maintained Diesel Maxi Cab(Non-A.C. Vehical No. WB59C 3704) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. (Period from 01.07.2024 to 14.01.2025.) | 1816/RD/PHE | 26/06/2024 | 198 | MD ZAFAR EQUEBAL | 2.6 | 0 | 0 | 100
2263 | UTTAR DINAJPUR | Raiganj Division | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12791 | New | Material Requisition To Resource Division | 966/RD/PHE | 29/03/2023 | 0 | Resource Division | 28.51 | 0 | 0 | 0
2264 | UTTAR DINAJPUR | Malda Mechanical | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12791 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Purba Jaypura Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014442) | 2527/MLMD | 04/08/2023 | 937 | M/S CHANDRANATH MUKHERJEE. | 26.16 | 0 | 0 | 72
2265 | UTTAR DINAJPUR | Malda Mechanical | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12791 | New | Quotation for new service connection at PURBA JAYPURA PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12791) | BP-2024-25-304 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 6.86 | 0 | 0 | 0
2266 | UTTAR DINAJPUR | Malda Mechanical | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12791 | New | Quotation for new service connection at PURBA JAYPURA PH-I (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12791) | BP-2024-25-305 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 9.14 | 0 | 0 | 0
2267 | UTTAR DINAJPUR | Raiganj Division | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12791 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
2268 | UTTAR DINAJPUR | Raiganj Division | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12791 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Purba Joypura Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | 1928/RD/PHE | 30/06/2025 | 180 | MONDAL PRECISION PRIVATE LIMITED | 32.38 | 0 | 0 | 0
2269 | UTTAR DINAJPUR | Raiganj Division | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12791 | New | Providing FHTC in connection with Purba Jaypura Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd call). | 2170/RD/PHE | 25/07/2025 | 90 | M/S SHIB ENTERPRISE | 6.63 | 0 | 0 | 0
2270 | UTTAR DINAJPUR | Raiganj Division | PURBA JAYPURA Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12791 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at PURBA JAYPURA PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | 2098/RD/PHE | 15/07/2025 | 180 | M/S SACHIN KUMAR | 56.82 | 0 | 0 | 0
2271 | UTTAR DINAJPUR | Raiganj Division | BARA SINGHANATH Piped Water Supply Scheme , SM/12529 | New | Material Requisition To Resource Division | 1120/RD/PHE | 24/04/2023 | 0 | Resource Division | 37.22 | 0 | 0 | 0
2272 | UTTAR DINAJPUR | Malda Mechanical | BARA SINGHANATH Piped Water Supply Scheme , SM/12529 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of BARA SINGHANATH, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-429 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.7 | 0 | 0 | 0
2273 | UTTAR DINAJPUR | Malda Mechanical | BARA SINGHANATH Piped Water Supply Scheme , SM/12529 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of BARA SINGHANATH, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-430 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.96 | 0 | 0 | 0
2274 | UTTAR DINAJPUR | Malda Mechanical | BARA SINGHANATH Piped Water Supply Scheme , SM/12529 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Barasinghanath Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014476) | 2473/MLMD | 04/08/2023 | 907 | DILIP MAHATO. | 27.32 | 0 | 0 | 84
2275 | UTTAR DINAJPUR | Raiganj Division | BARA SINGHANATH Piped Water Supply Scheme , SM/12529 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bara Singhanath Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | 1984/RD/PHE | 04/07/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 30.93 | 0 | 0 | 0
2276 | UTTAR DINAJPUR | Raiganj Division | BARA SINGHANATH Piped Water Supply Scheme , SM/12529 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at BARA SINGHNATH PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. (2nd Call) | 2086/RD/PHE | 14/07/2025 | 180 | ROY ENGINEERS. (PATNA) | 45.73 | 0 | 0 | 0
2277 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe Line for providing FHTC at Jaingaon Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) , SM/10547 | Retrofitting | Restoration of Pipe Line for providing F.H.T.C. at Jaingaon Water Supply Scheme under Islampur Sub-Division P.H.E. Dte.(Phase-II) | 1048/RD/PHED | 12/05/2022 | 45 | SAHA CONSTRUCTION | 13.7 | 0 | 0 | 100
2278 | UTTAR DINAJPUR | Raiganj Division | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | Preparation and submission of DPR for drinking Water Supply Scheme to facilitate uncovered mouzas under Uttar Dinajpur District, Block- Itahar. | 1770/RD/PHE | 19/09/2022 | 15 | RADIANT | 47.87 | 0 | 0 | 100
2279 | UTTAR DINAJPUR | Raiganj Division | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | Material Requisition To Resource Division | 2232/RD/PHE | 01/08/2023 | 0 | Resource Division | 29.61 | 0 | 0 | 0
2280 | UTTAR DINAJPUR | Raiganj Division | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period from 03.06.2024 to 07.06.2024. | BP-2024-25-92 | 28/06/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
2281 | UTTAR DINAJPUR | Malda Mechanical | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | Quotation for new service connection at DHAMDHOL PH-II (Itahar ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-16 | 04/04/2024 | 0 | W.B.S.E.D.C.LTD | 6.04 | 0 | 0 | 0
2282 | UTTAR DINAJPUR | Malda Mechanical | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | Quotation for new service connection at Dhamdhol PH-I (Itahar ccc) | BP-2023-24-539 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 3.97 | 0 | 0 | 0
2283 | UTTAR DINAJPUR | Raiganj Division | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for the period for 02.05.2024 to 03.05.2024, 06.05.2024 to 07.05.2024 and 09.05.2024 to 10.05.2024. | BP-2024-25-91 | 28/06/2024 | 0 | M/S DILWAR HOSAIN | 0.1 | 0 | 0 | 0
2284 | UTTAR DINAJPUR | Raiganj Division | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | SUBMISSION OF DETAILED ESTIMATE & DEMAND FOR PLACING NECESSARY FUND UNDER DIFFERENT PWSS | BP-2024-25-25 | 24/04/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 6.55 | 0 | 0 | 0
2285 | UTTAR DINAJPUR | Raiganj Division | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | Implementation of DHAMDOL and it's adjoining mouzas Pipe Water Supply Scheme at ITAHAR Block of Uttar Dinajpur District under RaiganjDivision, PHE Dte. | 565/RD/PHE | 23/02/2023 | 1276 | M/S LOKENATH CONSTRUCTION | 300.71 | 0 | 0 | 40
2286 | UTTAR DINAJPUR | Malda Mechanical | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no- I,II & Making compound yard lighting arrangement at T/W no- I of DHAMDHOL Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte (TSM/016124) | 3632/MLMD | 23/11/2023 | 856 | DILIP MAHATO. | 25.51 | 0 | 0 | 83
2287 | UTTAR DINAJPUR | Raiganj Division | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | Construction Of Approach Road, Laying of Pipe Line And Other Allied Works Of Dhamdhol PWSS Within Itahar Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 3561/RD/PHE | 05/12/2024 | 271 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 71.06 | 0 | 0 | 0
2288 | UTTAR DINAJPUR | Raiganj Division | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. For 12 months (Period from 17.10.2023 to 16.10.2024) | 2876/RD/PHE | 17/10/2023 | 366 | ARNAB DUTTA | 4.8 | 0 | 0 | 100
2289 | UTTAR DINAJPUR | Raiganj Division | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dhamdol Water Supply Scheme at Itahar Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 35 M3/hr. | 2476/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 18.01 | 0 | 0 | 0
2290 | UTTAR DINAJPUR | Raiganj Division | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DHAMDOL PWSS at Itahar Block under Raiganj Division, PHE Dte. | 611/RD/PHE | 05/03/2024 | 316 | SUBHASIS MAJUMDER | 11.29 | 0 | 0 | 100
2291 | UTTAR DINAJPUR | Raiganj Division | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DHAMDOL PWSS at Itahar Block under Raiganj Division, PHE Dte. | 612/RD/PHE | 05/03/2024 | 311 | M/S. ROY & CO. | 11.29 | 0 | 0 | 100
2292 | UTTAR DINAJPUR | Raiganj Division | Dhamdhol Piped Water Supply Scheme. , SM/14639 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
2293 | UTTAR DINAJPUR | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block , SM/12090 | New | Material Requisition To Resource Division | 2187/RD/PHE | 12/12/2022 | 0 | Resource Division | 48.12 | 0 | 0 | 0
2294 | UTTAR DINAJPUR | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block , SM/12090 | New | Material Requisition To Resource Division | 579/RD/PHE | 24/02/2023 | 0 | Resource Division | 47.6 | 0 | 0 | 0
2295 | UTTAR DINAJPUR | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block , SM/12090 | New | Laying of Balance Pipeline with ancillary works for ALIGANJ Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte. under Raiganj Division, P.H.E Dte.,U/D. | 3554/RD/PHE | 05/12/2024 | 45 | KARTICK BISWAS | 37.13 | 0 | 0 | 0
2296 | UTTAR DINAJPUR | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block , SM/12090 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under ALIGANJ Piped Water Supply Scheme at Islampur Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 590/RD/PHE | 05/03/2024 | 45 | NIMAI DAS NIMAI.RNJ@GMAIL.COM | 22.52 | 0 | 0 | 0
2297 | UTTAR DINAJPUR | Raiganj Division | ALIGANJ Piped Water Supply Scheme at Islampur Block , SM/12090 | New | Implementation of ALIGANJ and it's adjoining mouzas Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | 298/RD/PHE | 01/02/2023 | 1065 | UTTAM SAHA | 707.12 | 0 | 0 | 65
2298 | UTTAR DINAJPUR | Malda Mechanical | ALIGANJ Piped Water Supply Scheme at Islampur Block , SM/12090 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , & II and making compound lighting arrangement at T/W no. I of Aliganj Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/013513) | 2213/MLMD | 18/07/2023 | 863 | M/S D.G.B. ENTERPRISE. | 27.21 | 0 | 0 | 65
2299 | UTTAR DINAJPUR | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District , SM/11644 | New | Making compound lighting arrangement with allied works at T/W no. I of Baje Bindole Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011708) | 2240/MLMD | 18/07/2023 | 90 | MUKHERJEE ART CENTRE | 3.83 | 0 | 0 | 0
2300 | UTTAR DINAJPUR | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District , SM/11644 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Baje Bindol PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003137386 | 18/04/2023 | 15 | W.B.S.E.D.C.LTD | 0.5 | 0 | 0 | 0
2301 | UTTAR DINAJPUR | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District , SM/11644 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Baje Bindol PWSS , Raiganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003132926 | 16/04/2023 | 15 | W.B.S.E.D.C.LTD | 0.55 | 0 | 0 | 0
2302 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District , SM/11644 | New | Material Requisition To Resource Division | 1955/RD/PHE | 04/11/2022 | 0 | Resource Division | 30.7 | 0 | 0 | 0
2303 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District , SM/11644 | New | Restoration in connection with laying of PHE pipeline of Barduary- Bindole road under the jurisdiction of Uttar Dinajpur Highway Division in the district Uttar Dinajpur. | BP-2023-24-129 | 29/09/2023 | 0 | EXECUTIVE ENGINEER PWD ROADS | 22.53 | 0 | 0 | 0
2304 | UTTAR DINAJPUR | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District , SM/11644 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAJE BINDOLWater Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 421/MLMD | 14/03/2023 | 90 | M/S PARIMAL DAS. | 10.92 | 0 | 0 | 100
2305 | UTTAR DINAJPUR | Malda Mechanical | Baje Bindol PWSS in Raiganj Block in North Dinajpur District , SM/11644 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAJE BINDOLWater Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 420/MLMD | 14/03/2023 | 90 | M/S. KUNDU CONSTRACTION | 10.89 | 0 | 0 | 100
2306 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District , SM/11644 | New | Construction of OHR & other allied works of BAJE BINDOL and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte, Govt. of West Bengal | 587/RD/PHE | 24/02/2023 | 767 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 157.71 | 0 | 0 | 85
2307 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District , SM/11644 | New | Balance distribution System of Laying Pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAJE BINDOL Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 569/RD/PHE | 05/03/2024 | 361 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 22.76 | 0 | 0 | 75
2308 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District , SM/11644 | New | Trial Run For Baje Bindol PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | 538/RD/PHE | 12/02/2025 | 90 | M/S MAA TARA CONSTRUCTION | 0.88 | 0 | 0 | 0
2309 | UTTAR DINAJPUR | Raiganj Division | Baje Bindol PWSS in Raiganj Block in North Dinajpur District , SM/11644 | New | Implementation of BAJE BINDOLE and it's adjoining mouzas Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | 1540/RD/PHE | 26/08/2022 | 630 | M/S MAA TARA CONSTRUCTION | 239.58 | 0 | 0 | 100
2310 | UTTAR DINAJPUR | Raiganj Division | Balia Piped Water Supply Scheme. , SM/18493 | New | Material Requisition To Resource Division | 654/RD/PHE | 03/03/2023 | 0 | Resource Division | 33.83 | 0 | 0 | 0
2311 | UTTAR DINAJPUR | Raiganj Division | Balia Piped Water Supply Scheme. , SM/18493 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) BALIA in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 2365/RD/PHE | 11/08/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 17.79 | 0 | 0 | 100
2312 | UTTAR DINAJPUR | Malda Mechanical | Balia Piped Water Supply Scheme. , SM/18493 | New | Additional Quotation for p/h-I of Balia PWSS in the district of Uttar Dinajpur. | BP-2024-25-522 | 26/09/2024 | 0 | W.B.S.E.D.C.LTD | 4.76 | 0 | 0 | 0
2313 | UTTAR DINAJPUR | Malda Mechanical | Balia Piped Water Supply Scheme. , SM/18493 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Balia, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-237 | 29/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.95 | 0 | 0 | 0
2314 | UTTAR DINAJPUR | Malda Mechanical | Balia Piped Water Supply Scheme. , SM/18493 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Balia, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-238 | 29/05/2024 | 0 | W.B.S.E.D.C.LTD | 1.95 | 0 | 0 | 0
2315 | UTTAR DINAJPUR | Malda Mechanical | Balia Piped Water Supply Scheme. , SM/18493 | New | Additional Quotation for p/h-II of Balia PWSS in the district of Uttar Dinajpur. | BP-2024-25-521 | 26/09/2024 | 0 | W.B.S.E.D.C.LTD | 1.93 | 0 | 0 | 0
2316 | UTTAR DINAJPUR | Raiganj Division | Balia Piped Water Supply Scheme. , SM/18493 | New | Implementation of BALIA and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2295/RD/PHE | 04/08/2023 | 990 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 578.22 | 0 | 0 | 40
2317 | UTTAR DINAJPUR | Malda Mechanical | Balia Piped Water Supply Scheme. , SM/18493 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II of Balia Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/004007) | 2437/MLMD | 04/08/2023 | 667 | SOUNAK ENTERPRISE | 22.21 | 0 | 0 | 100
2318 | UTTAR DINAJPUR | Raiganj Division | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. , SM/16229 | New | Material Requisition To Resource Division | 839/RD/PHE | 23/03/2023 | 0 | Resource Division | 31.09 | 0 | 0 | 0
2319 | UTTAR DINAJPUR | Malda Mechanical | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. , SM/16229 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Prraul Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018405) | 2637/MLMD | 10/08/2023 | 960 | M/S D.G.B. ENTERPRISE. | 25.52 | 0 | 0 | 63
2320 | UTTAR DINAJPUR | Raiganj Division | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. , SM/16229 | New | Construction Of Approach Road Of Prraul PWSS at Goalpukhur-II Block under Raiganj Division,PHE dte. | 3306/RD/PHE | 20/11/2024 | 30 | M/S TRIBENI CONSTRUCTION | 6.2 | 0 | 0 | 0
2321 | UTTAR DINAJPUR | Raiganj Division | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. , SM/16229 | New | Earth Filling at Parrul PWSS under Islampur Sub-Division P.H.E. Dte. | 3305/RD/PHE | 20/11/2024 | 30 | S.G. CONSTRUCTION | 11.3 | 0 | 0 | 0
2322 | UTTAR DINAJPUR | Malda Mechanical | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. , SM/16229 | New | Quotation for new service connection at PRRAUL PH-I (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-77 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 4.69 | 0 | 0 | 0
2323 | UTTAR DINAJPUR | Malda Mechanical | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. , SM/16229 | New | Quotation for new service connection at PRRAUL PH-II (Kanki ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-78 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 16.25 | 0 | 0 | 0
2324 | UTTAR DINAJPUR | Raiganj Division | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. , SM/16229 | New | Implementation of PRRAUL and its adjoining mouzas Pipe Water Supply Scheme at GOALPOKHAR-II Block of Uttar Dinajpur District under Raiganj Division, PHEDte. | 2407/RD/PHE | 17/08/2023 | 593 | S.G. CONSTRUCTION | 236.76 | 0 | 0 | 95
2325 | UTTAR DINAJPUR | Raiganj Division | PRRAUL Piped Water Supply Scheme at Gaolpokhar-II Block under Uttar Dinajpur District. , SM/16229 | New | Continuation Order Hiring of Additional well-maintained Diesel Maxi Cab (Non-A.C., Vehicle no. WB59 D0577) for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. for the purpose of supervision of JJM works having jurisdiction over the entire Islampur Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period for 05/10/2024 to 14/01/2025. | 3041/RD/PHE | 03/10/2024 | 102 | SISIR KUMAR DUTTA | 1.35 | 0 | 0 | 0
2326 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme , SM/07142 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Butijhari and Adjoining Mouzas Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E. Dte. | 1412/RD/PHE | 11/12/2020 | 40 | SANYAL ENTERPRISE | 86.29 | 0 | 0 | 1
2327 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Butijhari and adjoining Mouzas water supply scheme , SM/07142 | Retrofitting | OFFICE ACCESSORIES BILL | 754/W | 11/03/2022 | 0 | SAHA CONSTRUCTION | 0.09 | 0 | 0 | 0
2328 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme , SM/07145 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Unatiagachh Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | 1424/RD/PHE | 11/12/2020 | 30 | RAHUL ENTERPRISE | 10.45 | 0 | 0 | 1
2329 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme , SM/07145 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Madhya Phulbari Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | 1423/RD/PHE | 11/12/2020 | 30 | NIMAI DAS | 10.93 | 0 | 0 | 1
2330 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme , SM/07145 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Dehar Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | 1436/RD/PHE | 11/12/2020 | 30 | MAA BICHITRA CONSTRUCTION | 10.43 | 0 | 0 | 1
2331 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme , SM/07145 | Retrofitting | OFFICE ACCESSORIES BILL | 764/W | 11/03/2022 | 0 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.1 | 0 | 0 | 0
2332 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme , SM/07145 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Paschim Phulbari Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | 1422/RD/PHE | 11/12/2020 | 30 | KARTICK BISWAS | 11 | 0 | 0 | 10
2333 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme , SM/07145 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Bhindabari Mouza under Dehar Water Supply Scheme in Goalpokher-I Block under Raiganj Division, P.H.E. Dte. | 1425/RD/PHE | 11/12/2020 | 30 | MS SARKAR ENTERPRISE ABDULGHATA | 10.63 | 0 | 0 | 100
2334 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Dehar and adjoining Mouzas water supply scheme , SM/07145 | Retrofitting | FHTC OF DEHAR PWSS | 1425/RD | 11/12/2020 | 30 | M/S SARKAR ENTERPRISE | 10.63 | 7.39 | 69.81 | 100
2335 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme , SM/07146 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Daribhir Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | 1435/RD/PHE | 11/12/2020 | 30 | SAMIRAN PODDAR | 11.06 | 0 | 0 | 1
2336 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme , SM/07146 | Retrofitting | OFFICE ACCESSORIES BILL | 763/W | 11/03/2022 | 0 | WEST DINAJPUR WHOLESALE CONSUMERS SO-OPERATIVE SOCIETY LTD, RAIGANJ | 0.08 | 0 | 0 | 0
2337 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme , SM/07146 | Retrofitting | OFFICE ACCESSORIES BILL | 769/W | 11/03/2022 | 0 | M/S DUTTA ENTERPRISE | 0.09 | 0 | 0 | 0
2338 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme , SM/07146 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Gangamaila Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | 1439/RD/PHE | 11/12/2020 | 30 | AJIT PARMANIK | 10.77 | 0 | 0 | 0
2339 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme , SM/07146 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Phulhar Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | 1438/RD/PHE | 11/12/2020 | 30 | M/S P.S ENTERPRISE | 10.94 | 0 | 0 | 0
2340 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme , SM/07146 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Amlijhari Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | 1421/RD/PHE | 11/12/2020 | 30 | MAA SHEETALA ENTERPRISE | 11.38 | 0 | 0 | 100
2341 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Amalijhari and adjoining Mouzas water supply scheme , SM/07146 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) at Bijekhor Mouza under Amaljhari Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | 1437/RD/PHE | 11/12/2020 | 751 | HAQUE CONSTRUCTION | 11.29 | 0 | 0 | 100
2342 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Siripur and adjoining Mouzas water supply scheme , SM/06729 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Siripur and adjoining Mouzas Water Supply Scheme in Galpokher-I Block under Raiganj Division, P.H.E. Dte. | 1234/RD/ PHE | 16/10/2020 | 40 | SAMIRAN PODDAR | 65.04 | 0 | 0 | 0
2343 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Siripur and adjoining Mouzas water supply scheme , SM/06729 | Retrofitting | LAYING UPVC OF FHTC OF SIRIPUR PWSS | 1522/RD | 23/12/2020 | 30 | M/S DOLPHIN CONSTRUCTION | 6.9 | 0 | 0 | 0
2344 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Matikunda and adjoining Mouzas water supply scheme in Islampur Block (Part-I,II,III) , SM/07384 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Matikunda and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. (Part-I) | 1387/RD/PHE | 09/12/2020 | 30 | M/S LUCKY CONSTRUCTION | 15.93 | 0 | 0 | 1
2345 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Matikunda and adjoining Mouzas water supply scheme in Islampur Block (Part-I,II,III) , SM/07384 | Retrofitting | Supplying, laying, fitting, fixing and jointing of UPVC pipe including dismantling PCC and ordinary cement concrete (1:2:4) in connection with Retrofitting of Functional Household Tap Connections(FHTC) under Matikunda and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. | 369/RD/PHE | 04/02/2021 | 25 | MAA TARA CONSTRUCTION | 4.12 | 0 | 0 | 1
2346 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Matikunda and adjoining Mouzas water supply scheme in Islampur Block (Part-I,II,III) , SM/07384 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Matikunda and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. (Part-III) | 1389/RD/PHE | 09/12/2020 | 30 | M/S HINDUSTHAN CONSTRUCTION | 15.86 | 0 | 0 | 1
2347 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional household Tap connection (FHTC) under Matikunda and adjoining Mouzas water supply scheme in Islampur Block (Part-I,II,III) , SM/07384 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Matikunda and adjoining Mouzas Water Supply Scheme in Islampur Block under Raiganj Division, P.H.E. Dte. (Part-II) | 1388/RD/PHE | 09/12/2020 | 30 | M/S CHOUDHURY CONSTRUCTION | 15.84 | 0 | 0 | 1
2348 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. , SM/09175 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Hemtabad Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Hemtabad Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1824/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 3.44 | 0 | 0 | 0
2349 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. , SM/09175 | Retrofitting | Preliminary Route Survey for finding feasibility of providing FHTC in different PWSS (Which excluded design year) Preparation of DPR of No.1. Goalpukhur PWSS 2. Lakhipur PWSS 3. Khanta PWSS 4. Hemtabad PWSS 5. Dharampur PWSS Zone-II under Raiganj Division, P.H.E. Dte. | 896/RD/PHED | 20/04/2022 | 7 | M/S DUTTA ENTERPRISE | 4.46 | 0 | 0 | 100
2350 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. , SM/09175 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Hemtabad Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Hemtabad Block under Raiganj Division, P.H.E Dte. | 484/RD/PHE | 25/02/2022 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 17.61 | 0 | 0 | 100
2351 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. , SM/09175 | Retrofitting | Preparation of Additional DPR For Hemtabad Zone-II in connection with Retrofitting of Functional House Hold Tap Connection of Hemtabad PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 2151/RD/PHE | 07/12/2022 | 7 | GEOTECHNICAL ENGINEERS CONSORTIUM MANASIJ_DUTTA@VSNL.COM | 0.78 | 0 | 0 | 1
2352 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. , SM/09175 | Retrofitting | Material Requisition To Resource Division | 1807/RD/PHE | 23/09/2022 | 0 | Resource Division | 2.4 | 0 | 0 | 0
2353 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. , SM/09175 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Hemtabad Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Hemtabad Block under Raiganj Division, P.H.E. Dte. | 2075/RD/PHE | 02/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 17.93 | 0 | 0 | 1
2354 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Hemtabad and adjoining mouzas Water Supply Scheme In Hemtabad Block Under Raiganj Division, P. H. E. Dte. , SM/09175 | Retrofitting | Allied works in connection with retrofitting of FHTC in Hemtabad PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2609/RD/PHE | 13/09/2023 | 60 | ASHIM CHANDA | 0.98 | 0 | 0 | 100
2355 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sasan and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. , SM/09177 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Sasan Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Kaliyaganj Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1826/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.98 | 0 | 0 | 0
2356 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sasan and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. , SM/09177 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) under Sasan Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Kaliaganj Block under Raiganj Division, P.H.E. Dte. | 2077/RD/PHE | 02/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION | 5.8 | 0 | 0 | 1
2357 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sasan and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. , SM/09177 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Sasan Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Kaliaganj Block under Raiganj Division, P.H.E Dte. | 429/RD/PHE | 16/02/2022 | 30 | TAPAN KUMAR MAJUMDER | 5.74 | 0 | 0 | 0
2358 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Sasan and adjoining mouzas Water Supply Scheme In Kaliyaganj Block Under Raiganj Division, P. H. E. Dte. , SM/09177 | Retrofitting | Material Requisition To Resource Division | 1792/RD/PHE | 22/09/2022 | 0 | Resource Division | 1.54 | 0 | 0 | 0
2359 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Mahua WSS for installation of FHTC (Part-I/II/III/IV). , SM/09129 | Retrofitting | Pipeline work and other ancillary works at Kulavita village of Mahua Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | 1414/RD/PHE | 07/07/2021 | 30 | M/S MANDAL ENTERPRISE | 4.82 | 0 | 0 | 1
2360 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Mahua WSS for installation of FHTC (Part-I/II/III/IV). , SM/09129 | Retrofitting | Pipeline work and other ancillary works at Motilal village of Mahua Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | 1415/RD/PHE | 07/07/2021 | 30 | M/S DUTTA ENTERPRISE | 4.8 | 0 | 0 | 1
2361 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Mahua WSS for installation of FHTC (Part-I/II/III/IV). , SM/09129 | Retrofitting | Pipeline work and other ancillary works at Magurjan village of Mahua Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | 1416/RD/PHE | 07/07/2021 | 30 | DONE ENTERPRISE | 4.3 | 0 | 0 | 1
2362 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Mahua WSS for installation of FHTC (Part-I/II/III/IV). , SM/09129 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Mahua for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-IV) | 2199/RD/PHE | 17/11/2021 | 30 | M/S HINDUSTHAN CONSTRUCTION | 25.63 | 0 | 0 | 0
2363 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Mahua WSS for installation of FHTC (Part-I/II/III/IV). , SM/09129 | Retrofitting | Laying of D.I. Pipeline and Ancillary works for improving the FHTC of Mahua Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | 2255/RD/PHE | 22/12/2022 | 20 | M/S HINDUSTHAN CONSTRUCTION HCONSTRUCTION.RNJ@GMAIL.COM | 1 | 0 | 0 | 100
2364 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Malgaon for installation of FHTC. , SM/09162 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of MALGAON Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2384/RD/PHE | 24/12/2021 | 30 | DONE ENTERPRISE | 13.71 | 0 | 0 | 0
2365 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Majhihar WSS for installation of FHTC. , SM/09110 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Majhihar Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | 2134/RD/PHE | 12/11/2021 | 30 | PRASANTA DUTTA | 4.74 | 0 | 0 | 1
2366 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Majhihar WSS for installation of FHTC. , SM/09110 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Majhihar Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-A) | 2135/RD/PHE | 12/11/2021 | 30 | PRASANTA DUTTA | 4.74 | 0 | 0 | 1
2367 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Mahammadpur WSS for installation of FHTC. , SM/09117 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of MAHAMMADPUR Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2189/RD/PHE | 17/11/2021 | 30 | TAPAN KUMAR MAJUMDER | 18.25 | 0 | 0 | 0
2368 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Jaingaon WSS for installation of FHTC. , SM/09126 | Retrofitting | Restoration of Pipe Line damaged and other allied works at Jaingaon Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | 2165/RD/PHE | 12/11/2021 | 30 | TAPAN KUMAR ROY | 2.62 | 0 | 0 | 1
2369 | UTTAR DINAJPUR | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. , SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Kamartor Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | 1026/RD/PHED | 12/05/2022 | 45 | CHOPRA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 23.5 | 0 | 0 | 1
2370 | UTTAR DINAJPUR | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. , SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Purba Chutiakhore Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | 1030/RD/PHED | 12/05/2022 | 45 | M/S LUCKY CONSTRUCTION | 46.82 | 0 | 0 | 1
2371 | UTTAR DINAJPUR | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. , SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Amalbari Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | 1023/RD/PHED | 12/05/2022 | 45 | KARTICK BISWAS | 13.46 | 0 | 0 | 1
2372 | UTTAR DINAJPUR | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. , SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Butijhari Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | 1019/RD/PHE | 12/05/2022 | 45 | CHAITANYA SAMAL | 10.67 | 0 | 0 | 100
2373 | UTTAR DINAJPUR | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. , SM/10545 | Augmentation | Laying additional Pipe Line for Providing Functional Household Tap Connection of Faridpur Water Supply Scheme under Raiganj Division P.H.E. Dte. | 1021/RD/PHED | 12/05/2022 | 45 | TAPAN KUMAR MAJUMDER | 11.27 | 0 | 0 | 100
2374 | UTTAR DINAJPUR | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. , SM/10545 | Augmentation | Laying Additional Pipe Line Beyond the scope of Pipeline to be laid as per DPR Purba Rampur Water Supply Scheme under Raiganj Division P.H.E. Dte. | 1027/RD/PHED | 12/05/2022 | 45 | WAMOL ENGINEERS CO-OPERATIVE SOCIEY LTD. | 27.28 | 0 | 0 | 100
2375 | UTTAR DINAJPUR | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. , SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Dehar Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | 1025/RD/PHED | 12/05/2022 | 45 | SRAMAJEEBEE CO-OPERATIVE LABOUR CONTRACT & CAST SOCIETY LTD. | 21.86 | 0 | 0 | 1
2376 | UTTAR DINAJPUR | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. , SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Khowaspur Piped Water Supply Scheme under Islampur Sub-Division P.H.E. Dte. | 1022/RD/PHED | 12/05/2022 | 45 | DIPANKAR SARKAR | 12.85 | 0 | 0 | 1
2377 | UTTAR DINAJPUR | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. , SM/10545 | Augmentation | Restoration of Pipe Line for providing F.H.T.C. at Bhagabati Water Supply Scheme under Islampur Sub-Division P.H.E. Dte.(Phase-II) | 1050/RD/PHED | 12/05/2022 | 45 | TAPAN KUMAR MAJUMDER | 14.06 | 0 | 0 | 1
2378 | UTTAR DINAJPUR | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. , SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Bhojpur Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | 1028/RD/PHED | 12/05/2022 | 45 | M/S PIONEER ENTERPRISE | 31.81 | 0 | 0 | 1
2379 | UTTAR DINAJPUR | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. , SM/10545 | Augmentation | Restoration of Damaged Pipe line work required for FHTC Work at Bhagabati Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte.(PART -B) | 2250/RD/PHE | 22/12/2022 | 20 | M/S GHOSH CONSTRUCTION GHOSH1.RNJ@GMAIL.COM | 10.28 | 0 | 0 | 0
2380 | UTTAR DINAJPUR | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. , SM/10545 | Augmentation | Laying Additional Pipe Line for Providing Functional Household Tap Connection of Puria Water Supply Scheme under Raiganj Division P.H.E. Dte. | 1024/RD/PHED | 12/05/2022 | 45 | NIMAI DAS | 18.89 | 0 | 0 | 1
2381 | UTTAR DINAJPUR | Raiganj Division | Extention & Restoration of Pipe Line in connection with providing FHTC under the command area of 13(Thirteen) Nos. different schemes under Raiganj Division P.H.E. Dte. , SM/10545 | Augmentation | Laying of additional pipe line to be laid the scope of DPR in the command area at Amaljhari Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. | 1031/RD/PHED | 12/05/2022 | 30 | APEX ENTERPRISES | 8.95 | 0 | 0 | 100
2382 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe Line for providing FHTC at Pokharia Piped Water Supply Scheme under Islampur Sub-Division, P.H.E. Dte. (Phase-II) , SM/10449 | Retrofitting | Restoration of Pipe Line for providing F.H.T.C. at Pokheria Water Supply Scheme under Islampur Sub-Division P.H.E. Dte.(Phase-II) | 1040/RD/PHED | 12/05/2022 | 30 | TAPAN KUMAR MAJUMDER | 7.03 | 0 | 0 | 1
2383 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Construction of 2 Nos. Tube-Well ( 250mm diameter x 150mmx140 mtr) for Dilwarpur Water Supply Scheme in Kaliaganj Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | 47/RD/PHE | 07/01/2022 | 21 | BHOLA PAUL | 17.54 | 0 | 0 | 1
2384 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Soil Investigation for Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including RCC Bored Pile & Pile Cap upto pedestal For Dilwarpur W/S Scheme in Kaliaganj Block in Uttar Dinajpur District. | 1237/RD/PHE | 20/06/2022 | 20 | BENGAL CO-OP. ENGINEERS' CONSTRUCTION SOCIETY LTD. | 1.99 | 0 | 0 | 0
2385 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Providing and delivering A4 Xerox copies of DPRs for Raiganj Division, P.H.E. Dte., | 1512/RD | 22/08/2022 | 7 | JUMBO XEROX | 0.09 | 0 | 0 | 0
2386 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | xerox bill | BP-2022-23-207 | 04/11/2022 | 0 | JUMBO XEROX | 0.09 | 0 | 0 | 0
2387 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Laying Distribution System for DILWARPUR and its adjoining Mouza Water Supply Scheme at KALIAGANJ Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | 177/RD/PHE | 27/01/2022 | 45 | M/S MAA TARA CONSTRUCTION | 119.05 | 0 | 0 | 100
2388 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | FHTC (Functional Household Tap Connection) for Dilwarpur Water Supply Scheme [Augmentation Scheme] in Kaliaganj Block of Uttar Dinajpur District. | 1015/RD/PHED | 12/05/2022 | 45 | BHOLA PAUL | 45.2 | 0 | 0 | 95
2389 | UTTAR DINAJPUR | Malda Mechanical | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of DILWARPUR Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2275/MLMD | 31/08/2022 | 45 | SUBRATA SAHA | 7.34 | 0 | 0 | 0
2390 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Construction of Over Head Reservoir(Capacity-300 Cum) of Dilwarpur Pipe Water Supply Scheme in connection with Augmentation at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 78/RD/PHE | 17/01/2023 | 240 | M/S MASCOT CONSTRUCTION KRISHNADITYA06@GMAIL.COM | 84.11 | 0 | 0 | 0
2391 | UTTAR DINAJPUR | Malda Mechanical | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Making compound lighting arrangement with allied works at T/W no. I of Dilwarpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/009096) | 2239/MLMD | 18/07/2023 | 90 | NIRMAN. | 2.61 | 0 | 0 | 0
2392 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dilwarpur Water Supply Scheme(Augmentation of Dilwarpur PWSS) under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj, Capacity-35 M3/hr. | 3392/RD/PHE | 12/12/2023 | 140 | AJIT PRAMANIK | 17.73 | 0 | 0 | 0
2393 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Repairing of Pump House of Head Works and 2nd Tube Well Site under Augmentation of Dilwarpur Water Supply Scheme at Kaliyaganj Block under Raiganj Division P.H.E Dte. | 1534/RD/PHE | 25/08/2022 | 30 | M/S CHOUDHURY CONSTRUCTION | 4.23 | 0 | 0 | 0
2394 | UTTAR DINAJPUR | Malda Mechanical | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of Dilwarpur Water Supply Scheme T/W no.II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2276/MLMD | 31/08/2022 | 365 | SOUMEN ELECTRIC, | 7.56 | 0 | 0 | 0
2395 | UTTAR DINAJPUR | Malda Mechanical | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Supply & fitting, fixing of three phase actuator operated wafer type butterfly valve at P.H. NO-II Of Dilwarpur Water Supply Scheme in the district of Uttar Dinajpur under Malda Mehanical Division, PHE Dte. | 2202/MLMD | 17/08/2022 | 10 | SOUMEN ELECTRIC, | 0.96 | 0 | 0 | 0
2396 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Material Requisition To Resource Division | 637/RD/PHE | 23/03/2022 | 0 | Resource Division | 9.75 | 0 | 0 | 0
2397 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Material Requisition To Resource Division | 125/RSD/PHE | 10/08/2022 | 0 | Resource Division | 0.61 | 0 | 0 | 0
2398 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Material Requisition To Resource Division | 126/RSD/PHE | 10/08/2022 | 0 | Resource Division | 0.16 | 0 | 0 | 0
2399 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Material Requisition To Resource Division | 1215/RD/PHE | 10/06/2022 | 0 | Resource Division | 8.56 | 0 | 0 | 0
2400 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Hiring of Inspection Vehicle for office of the Assistant engineer, Raiganj Sub-Division, P.H.E. Dte. for the period from 17.12.2022 to 15.01.2023. | BP-2023-24-223 | 15/12/2023 | 0 | DEBASISH GHOSH | 0.4 | 0 | 0 | 0
2401 | UTTAR DINAJPUR | Raiganj Division | Augmentation Dilwarpur Piped Water Supply Scheme. , SM/09989 | Augmentation | Laying Rising Main pipeline inter-connection of Tubewells including construction of valve chamber and other related works for DILWARPUR (Augmentation) and its adjoining Water Supply Scheme in Kaliaganj Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | 46/RD/PHE | 07/01/2022 | 45 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 0.77 | 0 | 0 | 100
2402 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Laying Distribution System for SITLAGAON and its adjoining Mouza Water Supply Scheme at CHOPRA Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | 178/RD /PHE | 27/01/2022 | 180 | M/S MAA TARA CONSTRUCTION | 111.99 | 0 | 0 | 0
2403 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Material Requisition To Resource Division | 2005/RD/PHE | 16/11/2022 | 0 | Resource Division | 17.06 | 0 | 0 | 0
2404 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Laying Rising Main pipeline inter-connection of Tubewells including construction of valve chamber and other related works for SITLAGAON (Augmentation) and its adjoining Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | 51/RD/PHE | 07/01/2022 | 45 | M/S MAA TARA CONSTRUCTION BIRNAGAR | 0.52 | 0 | 0 | 0
2405 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Sinking 2 nos. of Ground Bored Wells, 300mm diameter x 200mm diameter, 200mtr. Deep Tube Well including proper development and necessary yield for Ground Water Based PWSS for SITLAGAON nad its adjoining Mouzas Water Supply Scheme under ) of Chopra Water Supply Scheme in Chopra Block under Raiganj Division, P.H.E Dte. in the District of Uttar Dinajpur. | 52/RD/PHE | 07/01/2022 | 21 | HAQUE CONSTRUCTION | 19.76 | 0 | 0 | 1
2406 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Approach Road including earthwork for road at 2nd Tube Well Site of Sitlagaon Piped Water Supply Scheme in connection with Augmentation of Sitalgaon PWSS under Islampur Sub-Division PHE Dte. | 2252/RD/PHE | 22/12/2022 | 20 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 2.65 | 0 | 0 | 0
2407 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Sitlagaon Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 376/RD/PHE | 07/02/2023 | 45 | BITTU ENTERPRISE BISWAJIT.RNJ@GMAIL.COM | 5.03 | 0 | 0 | 100
2408 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Material Requisition To Resource Division | 640/RD/PHE | 23/03/2022 | 0 | Resource Division | 11.38 | 0 | 0 | 0
2409 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | FHTC (Functional Household Tap Connection) for Shitlagaon Water Supply Scheme [Augmentation Scheme] in Chopra Block of Uttar Dinajpur District | 1017/RD/PHED | 12/05/2022 | 855 | HAQUE CONSTRUCTION | 53.31 | 0 | 0 | 50
2410 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Construction of Over Head Reservoir(Capacity-350 Cum) of SITLAGAON Pipe Water Supply Scheme in connection with Augmentation at Chopra Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 738/RD/PHE | 15/03/2023 | 635 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 143.55 | 0 | 0 | 70
2411 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Laying additional pipe line with FHTC in connection with Augmentation Of Sitlagaon Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division. | 3300/RD/PHE | 20/11/2024 | 30 | ZAREEN ENTERPRISE | 6.61 | 0 | 0 | 0
2412 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Balance Laying of pipeline with Construction Of Boundary Wall With Gate and Approach Road at Head Work Site, 2nd Tube-Well in connection with Augmentation Of Sitlagaon PWSS at Chopra Block under Raiganj Division,PHE dte. | 3294/RD/PHE | 20/11/2024 | 45 | M/S LUCKY CONSTRUCTION | 29.78 | 0 | 0 | 0
2413 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of SITALGAON Water Supply Scheme T/W no.I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2417/MLMD | 26/09/2022 | 90 | PABITRA MANDAL | 9.41 | 0 | 0 | 100
2414 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of SITALGAON Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2418/MLMD | 26/09/2022 | 90 | JOYSHREE CONCERN | 9.38 | 0 | 0 | 100
2415 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Construction of Pump House (without Toilet) at 2nd Tubewell Site (5.40mx3.60m) in connection with Augmentation of Sitlagaon Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 373/RD/PHE | 07/02/2023 | 45 | ZAREEN ENTERPRISE MSLUCKYCONSTRUCTION@GMAIL.COM | 4.12 | 0 | 0 | 100
2416 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Laying Distribution System for SITLAGAON and its adjoining Mouza Water Supply Scheme at CHOPRA Block under Raiganj Division, P.H.E Dte. In the District of Uttar Dinajpur. | 178/RD/PHE | 27/01/2022 | 45 | MAA TARA CONSTRUCTION | 111.99 | 0 | 0 | 0
2417 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Soil Investigation for Construction of 350 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including RCC Bored Pile & Pile Cap upto pedestal For Shitlagaon W/S Scheme In Chopra Block In Uttar Dinajpur District. | 1236/RD/PHE | 20/06/2022 | 20 | GEOCON INDIA | 1.98 | 0 | 0 | 100
2418 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Providing FHTC in connection with augmentation of Shitlagaon Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division. | 49/RD/PHE | 03/01/2025 | 45 | SANDIP SARKAR | 6.17 | 0 | 0 | 0
2419 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Sitalgaon Piped Water Supply Scheme. , SM/09990 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Shitlagaon Water Supply Scheme(Augmentation) at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity-45 M3/hr. | 2500/RD/PHE | 12/09/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 19.35 | 0 | 0 | 0
2420 | UTTAR DINAJPUR | Malda Mechanical | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11825 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. IV of BAMANGRAM ,Bamongola C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 3004228400 | 26/04/2023 | 90 | W.B.S.E.D.C.LTD | 6.31 | 0 | 0 | 0
2421 | UTTAR DINAJPUR | Malda Mechanical | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11825 | New | Making compound lighting arrangement with allied works at T/W no. I of Bamangram Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011913) | 2235/MLMD | 18/07/2023 | 90 | CHATTERJEE CONSTRUCTION | 2.64 | 0 | 0 | 0
2422 | UTTAR DINAJPUR | Raiganj Division | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11825 | New | Material Requisition To Resource Division | 573/RD/PHE | 23/02/2023 | 0 | Resource Division | 36.39 | 0 | 0 | 0
2423 | UTTAR DINAJPUR | Raiganj Division | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11825 | New | Rig bored Tubewell at BAMANGRAM PWSS in connection with Implementation of New Bamangram PWSS at Raiganj Block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2750/RD/PHE | 05/10/2023 | 20 | BHOLA PAUL | 26.11 | 0 | 0 | 98
2424 | UTTAR DINAJPUR | Malda Mechanical | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11825 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAMANGRAM Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 3349/MLMD | 30/10/2023 | 90 | DEY ENTERPRISE.. | 11.23 | 0 | 0 | 84
2425 | UTTAR DINAJPUR | Malda Mechanical | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11825 | New | Charge against shifting/Reorientation of 1 no 25 KVA DTR on Safety ground at Tubewell site-I of Bamangram water supply scheme under Birnagar CCC in the District of Uttar Dinajpur | BP-2024-25-567 | 29/10/2024 | 0 | W.B.S.E.D.C.LTD | 1.34 | 0 | 0 | 0
2426 | UTTAR DINAJPUR | Malda Mechanical | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11825 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Bamangram, Birnagar CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-621 | 04/03/2024 | 0 | W.B.S.E.D.C.LTD | 6.51 | 0 | 0 | 0
2427 | UTTAR DINAJPUR | Malda Mechanical | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11825 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Bamangram, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-570 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 4.61 | 0 | 0 | 0
2428 | UTTAR DINAJPUR | Raiganj Division | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11825 | New | Implementation of BAMANGRAM and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 561/RD/PHE | 23/02/2023 | 1043 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 525.45 | 0 | 0 | 4
2429 | UTTAR DINAJPUR | Raiganj Division | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11825 | New | Balance distribution System of Laying Pipeline with Construction Of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BAMANGRAM Piped Water Supply Scheme at Raiganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 573/RD/PHE | 05/03/2024 | 360 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 22.87 | 0 | 0 | 80
2430 | UTTAR DINAJPUR | Raiganj Division | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11825 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Bamangram PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3752/RD/PHED | 18/12/2024 | 135 | BHOLA PAUL | 91.18 | 0 | 0 | 0
2431 | UTTAR DINAJPUR | Raiganj Division | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11825 | New | Trial Run For Bamongram PWSS under Raiganj Block under Raiganj Division ,PHE Dte. for 3 months | 540/RD/PHE | 12/02/2025 | 90 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0 | 0
2432 | UTTAR DINAJPUR | Raiganj Division | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11825 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Bamangram Water Supply Scheme at Raiganj Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Block:- Raiganj, Capacity- 80 M3/hr. | 1658/RD/PHE | 23/06/2025 | 180 | AJIT PRAMANIK | 32.35 | 0 | 0 | 0
2433 | UTTAR DINAJPUR | Malda Mechanical | BAMANGRAM PWSS IN RAIGANJ BLOCK IN UTTAR DINAJPUR DISTRICT , SM/11825 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of BAMANGRAM Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 3350/MLMD | 03/11/2023 | 333 | JAL PRAVAHIKA PVT. LTD. | 11.93 | 0 | 0 | 100
2434 | UTTAR DINAJPUR | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Karandighi and Raiganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. , SM/11521 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House Hold) in Jugiamer village under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2880/RD/PHE | 25/09/2024 | 60 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 43.97 | 0 | 0 | 0
2435 | UTTAR DINAJPUR | Raiganj Division | Mini Piped Water Supply Scheme for the Blocks of Karandighi and Raiganj in the District of Uttar Dinajpur under Raiganj Division P.H.E. DTE. , SM/11521 | New | Implementation of Ground Water Based Mini Piped Water Supply Scheme(Maximum 100 House old) in Different Villages under Karandighi & Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1287/RD/PHE | 08/05/2023 | 1035 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 206.76 | 0 | 0 | 5
2436 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME , SM/11726 | Augmentation | Material Requisition To Resource Division | 1944/RD/PHE | 04/11/2022 | 0 | Resource Division | 33.97 | 0 | 0 | 0
2437 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME , SM/11726 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & III and installation of grid connection solar PV system with net metering at T/W no.- I of Goalpokher Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011422) | 2090/MLMD | 04/07/2023 | 2005 | DILIP MAHATO. | 27.26 | 0 | 0 | 65
2438 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME , SM/11726 | Augmentation | FHTC (Functional Household Tap Connection) for Goalpokhar Water Supply Scheme [Augmentation Scheme] in Goalpokhar-I Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2026/RD/PHE | 17/11/2022 | 90 | MAA BICHITRA CONSTRUCTION MAABICHITRACONST@GMAIL.COM | 66.67 | 0 | 0 | 98
2439 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME , SM/11726 | Augmentation | Repairing for Head Work Site Pump House & Construction of Toilet at Goalpokher in connection with Goalpokher PWSS under Islampur Sub-Division under Raiganj Division,PHE Dte. | 1539/RD/PHE | 24/05/2023 | 45 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 2.35 | 0 | 0 | 100
2440 | UTTAR DINAJPUR | Malda Mechanical | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME , SM/11726 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at Pole Shifting of Goalpokher PWS, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-449 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 1.48 | 0 | 0 | 0
2441 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME , SM/11726 | Augmentation | Augmentation work of GOALPOKHAR and it's adjoining mouzas Piped Water Supply Scheme at Goalpokhar-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | 1547/RD/PHE | 26/08/2022 | 90 | AJIT PARMANIK | 319.76 | 0 | 0 | 95
2442 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME , SM/11726 | Augmentation | Construction of Over Head Reservoir(Capacity-500 Cum) of GOALPOKHER Pipe Water Supply Scheme in connection with Augmentation at GOALPOKHAR-I Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 735/RD/PHE | 15/03/2023 | 730 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 165.64 | 0 | 0 | 85
2443 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME , SM/11726 | Augmentation | Repair and Maintenance of Boundary Wall and construction of Concrete Pathway at both Head work site and 2nd tube well Pump House site in connection with Augmentation of Goalpokhar Pipe W/S scheme under Islampur Sub-Division PHE Dte.under Raiganj Division, PHE Dte.,U/D. | 30/RD/PHE | 02/01/2025 | 45 | HAQUE CONSTRUCTION | 8.16 | 0 | 0 | 0
2444 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME , SM/11726 | Augmentation | Laying of Additional Pipeline for Retrofitting in connection with augmentation of Goalpokhar Water Supply Scheme for installation of FHTC under Islampur Sub-Division P.H.E. Dte.under Raiganj Division, P.H.E Dte.,U/D. | 43/RD/PHE | 03/01/2025 | 45 | HAQUE CONSTRUCTION | 40.57 | 0 | 0 | 0
2445 | UTTAR DINAJPUR | Raiganj Division | AUGMENTATION GOALPOKHER PIPED WATER SUPPLY SCHEME , SM/11726 | Augmentation | Repairing for 2nd Pump House & Construction of Toilet at Goalpokher in connection with Goalpokher PWSS under Islampur Sub-Division under Raiganj Division,PHE Dte. | 1538/RD/PHE | 24/05/2023 | 413 | HAQUE CONSTRUCTION HAQUE@GMAIL.COM | 3.14 | 0 | 0 | 100
2446 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | Repairing of Pump House at 3rd Tubewell site in connection with Augmentation of Raghabpur Piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | 380/RD/PHE | 07/02/2023 | 45 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 2.06 | 0 | 0 | 0
2447 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | Construction of Over Head Reservoir(Capacity-300 Cum) of RAGHABPUR Pipe Water Supply Scheme in connection with Augmentation at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 79/RD/PHE | 17/01/2023 | 240 | LOKNATH CO-OP. LBOUR CONTRACT & CONSTRUCTION SOCIETY LTD. LOKNATH.ITR@GMAIL.COM | 86.06 | 0 | 0 | 0
2448 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | Making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Raghabpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011648) | 2654/MLMD | 10/08/2023 | 1915 | DAS CONSTRUCTION | 10.55 | 0 | 0 | 0
2449 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of RAGHABPUR Water Supply Scheme T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 253/MLMD | 24/02/2023 | 90 | S.P. ENTERPRISE (KOLKATA) | 10.45 | 0 | 0 | 100
2450 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Raghabpur, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003118806 | 26/03/2023 | 7 | W.B.S.E.D.C.LTD | 0.55 | 0 | 0 | 0
2451 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | Construction of Pump House at 3rd tubewell Site (3.60mx3.00m ) Raghabpur Piped Water Supply Scheme in connection with Augmentation of Raghabpur PWSS under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 1540/RD/PHE | 24/05/2023 | 60 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 4.09 | 0 | 0 | 100
2452 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Raghabpur PWSS , Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003266667 | 23/11/2023 | 90 | W.B.S.E.D.C.LTD | 6.4 | 0 | 0 | 100
2453 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | Material Requisition To Resource Division | 1943/RD/PHE | 04/11/2022 | 0 | Resource Division | 20.88 | 0 | 0 | 0
2454 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | FHTC (Functional Household Tap Connection) for Raghabpur Water Supply Scheme [Augmentation Scheme] in Karandighi Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2022/RD/PHE | 17/11/2022 | 90 | M/S BHOWMIK ENTERPRISE BHOWMICKJ21@GMAIL.COM | 53.39 | 0 | 0 | 70
2455 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | Balance Laying of pipeline with Construction Of Boundary Wall With Gate and Approach Road at Head Work Site, 2nd Tube-Well in connection with Augmentation Of Raghabpur PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 3291/RD/PHE | 20/11/2024 | 45 | NANDANIK ENGINEERS C-OPERATIVE SOCIETY LTD. | 39.82 | 0 | 0 | 0
2456 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | Laying additional pipe line with FHTC for Augmentation Of Raghabpur Pipe Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division. | 3784/RD/PHE | 19/12/2024 | 45 | BIKASH KAR | 26.17 | 0 | 0 | 0
2457 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | Augmentation of RAGHABPUR Water Supply Scheme at Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal. | 1550/RD/PHE | 26/08/2022 | 90 | DIPESH BHOWMIK | 144.6 | 0 | 0 | 100
2458 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of RAGHABPUR Water Supply Scheme T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 0252/MLMD | 24/02/2023 | 90 | DEB CONSTRUCTION. | 10.36 | 0 | 0 | 100
2459 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | Supply, installation and commissioning of electro-mechanical components of Augmentation of RAGHABPUR Water Supply Scheme T/W no. III in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 254/MLMD | 24/02/2023 | 90 | FUTURE | 10.55 | 0 | 0 | 100
2460 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | Construction of Pump House at Head Work Site (5.40mx3.60m) in connection with Augmentation of Raghabpur Piped Water Supply Scheme under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 371/RD/PHE | 07/02/2023 | 45 | D. K. ASSOCIATES BISWAJITKAR9434@GMAIL.COM | 4.96 | 0 | 0 | 100
2461 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | Repairing of Pump House at 2nd Tubewell site in connection with Augmentation of RAGHABPUR Piped Water Supply Scheme under Islampur Sub-Division PHE Dte. | 372/RD/PHE | 07/02/2023 | 45 | SINHA CONSTRUCTION BIMALJYOTI.RNJ@GMAIL.COM | 2.02 | 0 | 0 | 100
2462 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Raghabpur in Karandighi Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. , SM/11728 | Augmentation | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Raghabpur Water Supply Scheme(Augmentation) at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist: Uttar Dinajpur, Capacity-60 M3/hr. | 2498/RD/PHE | 12/09/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 29.59 | 0 | 0 | 0
2463 | UTTAR DINAJPUR | Malda Mechanical | Source augmentation for Sitgram Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12644 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Sitgram,PWSS, Birnagar C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003270394 | 06/12/2023 | 90 | W.B.S.E.D.C.LTD | 4.25 | 0 | 0 | 100
2464 | UTTAR DINAJPUR | Raiganj Division | Source augmentation for Sitgram Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12644 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Sitgram Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1919/RD/PHE | 28/10/2022 | 45 | BHOLA PAUL | 31.5 | 0 | 0 | 30
2465 | UTTAR DINAJPUR | Malda Mechanical | Source augmentation for Sitgram Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12644 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Source Augmentation of Sitgram Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015290) | 2769/MLMD | 14/08/2023 | 180 | J.S. ERECTORS. | 10.51 | 0 | 0 | 100
2466 | UTTAR DINAJPUR | Raiganj Division | Source augmentation for Sitgram Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12644 | Augmentation | Material Requisition To Resource Division | 20/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
2467 | UTTAR DINAJPUR | Raiganj Division | Source augmentation for Sitgram Piped Water Supply Scheme under Raiganj block in the district of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12644 | Augmentation | Ancillary work I.C.W. retrofitting of Sitgram PWSS, Raiganj Block in connection with Augmentation of Sitgram PWSS under Raiganj Division, PHE Dte. Uttar Dinajpur | 1544/RD/PHE | 11/06/2025 | 30 | M/S. BANGARAJ | 2.03 | 0 | 0 | 0
2468 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Maslandpur Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12653 | Augmentation | Material Requisition To Resource Division | 17/RD/PHE | 03/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
2469 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Maslandpur Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12653 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Maslandpur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-547 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 8.42 | 0 | 0 | 0
2470 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Maslandpur Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12653 | Augmentation | Construction of Boundary Wall, Pump House, Laying Pipeline and Providing FHTC in Connection with Source Augmentation of Maslandpur Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1922/RD/PHE | 28/10/2022 | 885 | M/S BHOWMIK ENTERPRISE BHOWMICKJ21@GMAIL.COM | 31.56 | 0 | 0 | 71
2471 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Maslandpur Piped Water Supply Scheme under Raiganj Block in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. , SM/12653 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Source Augmentation of Maslandpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/002771) | 2518/MLMD | 04/08/2023 | 575 | M/S. MAYUKH BHADURI | 10.92 | 0 | 0 | 100
2472 | UTTAR DINAJPUR | Malda Mechanical | ROHIA Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/12792 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of ROHIA, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003198611 | 24/07/2023 | 90 | W.B.S.E.D.C.LTD | 10.69 | 0 | 0 | 100
2473 | UTTAR DINAJPUR | Malda Mechanical | ROHIA Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/12792 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of ROHIA, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003198607 | 24/07/2023 | 90 | W.B.S.E.D.C.LTD | 12.8 | 0 | 0 | 100
2474 | UTTAR DINAJPUR | Raiganj Division | ROHIA Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/12792 | New | Material Requisition To Resource Division | 615/RD/PHE | 28/02/2023 | 0 | Resource Division | 27.28 | 0 | 0 | 0
2475 | UTTAR DINAJPUR | Malda Mechanical | ROHIA Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/12792 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Rohia Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014488) | 2372/MLMD | 28/07/2023 | 180 | WEST BENGAL ENGINEERING COMPANY. | 27.21 | 0 | 0 | 82
2476 | UTTAR DINAJPUR | Raiganj Division | ROHIA Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/12792 | New | Balance distribution System of Laying pipeline with Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under ROHIA PWSS at Islampur Block under Raiganj Division, PHE Dte. | 598/RD/PHE | 05/03/2024 | 45 | PRASANTA DUTTA | 22.75 | 0 | 0 | 0
2477 | UTTAR DINAJPUR | Raiganj Division | ROHIA Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/12792 | New | Construction of concrete pathway With Earth Filling at Head Work Site Pump House & 2nd TW Site Pump House for Rohia Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division, PHED.,U/D. | 3500/RD/PHE | 02/12/2024 | 15 | SUDIP MITRA | 6.36 | 0 | 0 | 0
2478 | UTTAR DINAJPUR | Raiganj Division | ROHIA Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/12792 | New | Implementation of ROHIA and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House Head Work, 2nd Tube Well.) | 673/RD/PHE | 06/03/2023 | 906 | UTTAM SAHA | 654.73 | 0 | 0 | 60
2479 | UTTAR DINAJPUR | Raiganj Division | ROHIA Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/12792 | New | Trial Run For Rohia PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | 549/RD/PHE | 12/02/2025 | 90 | UTTAM SAHA | 0.88 | 0 | 0 | 0
2480 | UTTAR DINAJPUR | Raiganj Division | ROHIA Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/12792 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Rohia Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | 1968/RD/PHE | 02/07/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.35 | 0 | 0 | 0
2481 | UTTAR DINAJPUR | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13014 | New | Laying Pipe line at MANKAUR Pipe Water Supply Scheme at Raiganj Block of Uttar Dinajpur District under Raiganj Division, P.H.E Dte. | 1537/RD/PHE | 24/05/2023 | 45 | M/S P.S. ENTERPRISE | 15.39 | 0 | 0 | 0
2482 | UTTAR DINAJPUR | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13014 | New | Preparation and Submission of DPR for proposed Mankaur Piped Water Supply Scheme under Karandighi Block. | 611/RD/PHED | 15/03/2022 | 30 | M/S SOBHA & CO. | 4.4 | 0 | 0 | 0
2483 | UTTAR DINAJPUR | Malda Mechanical | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13014 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Mankaur ,Dalkhola C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003196602 | 20/07/2023 | 90 | W.B.S.E.D.C.LTD | 5.64 | 0 | 0 | 100
2484 | UTTAR DINAJPUR | Malda Mechanical | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13014 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Mankaur ,Dalkhola C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003196598 | 20/07/2023 | 90 | W.B.S.E.D.C.LTD | 8.66 | 0 | 0 | 100
2485 | UTTAR DINAJPUR | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13014 | New | Material Requisition To Resource Division | 585/RD/PHE | 24/02/2023 | 0 | Resource Division | 46.32 | 0 | 0 | 0
2486 | UTTAR DINAJPUR | Malda Mechanical | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13014 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head workite at T/W no. I of Mankaur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/015108) | 2519/MLMD | 04/08/2023 | 930 | PABITRA MANDAL | 25.32 | 0 | 0 | 86
2487 | UTTAR DINAJPUR | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13014 | New | Implementation of MANKAUR andit's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 113/RD/PHE | 20/01/2023 | 805 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 379.57 | 0 | 0 | 60
2488 | UTTAR DINAJPUR | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13014 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MANKAUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 599/RD/PHE | 05/03/2024 | 360 | M/S CHOUDHURY CONSTRUCTION | 11.29 | 0 | 0 | 75
2489 | UTTAR DINAJPUR | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13014 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under MANKAUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 600/RD/PHE | 05/03/2024 | 360 | NANDANIK ENGINEERS C-OPERATIVE SOCIETY LTD. | 11.29 | 0 | 0 | 80
2490 | UTTAR DINAJPUR | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13014 | New | Trial Run For Mankaur PWSS under Karandighi Block under Raiganj Division ,PHE Dte. for 3 months | 551/RD/PHE | 12/02/2025 | 90 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 0.88 | 0 | 0 | 0
2491 | UTTAR DINAJPUR | Raiganj Division | Mankaur Piped Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. , SM/13014 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Mankaur Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 60 M3/hr. | 2482/RD/PHE | 12/09/2025 | 180 | BHOLA PAUL | 29.56 | 0 | 0 | 0
2492 | UTTAR DINAJPUR | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12785 | New | Preparation & Submission of DPR for proposed Gopalpur Piped Water Supply Scheme under Karandighi Development Block. | 602/RD/PHE | 15/03/2022 | 30 | ENVIROTECH SOLUTIONS | 5.1 | 0 | 0 | 0
2493 | UTTAR DINAJPUR | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12785 | New | Preparation and submission of DPR for proposed Gopalpur PWSS under Karandighi block. | 602/RD/PHED | 15/03/2022 | 30 | ENVIROTECH SOLUTIONS | 5.1 | 0 | 0 | 0
2494 | UTTAR DINAJPUR | Malda Mechanical | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12785 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of GOPALPUR, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003220371 | 21/09/2023 | 90 | W.B.S.E.D.C.LTD | 3.7 | 0 | 0 | 100
2495 | UTTAR DINAJPUR | Malda Mechanical | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12785 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of GOPALPUR, Karandighi C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003220366 | 21/09/2023 | 90 | W.B.S.E.D.C.LTD | 3.6 | 0 | 0 | 100
2496 | UTTAR DINAJPUR | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12785 | New | Material Requisition To Resource Division | 584/RD/PHE | 24/02/2023 | 0 | Resource Division | 33.67 | 0 | 0 | 0
2497 | UTTAR DINAJPUR | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12785 | New | Implementation of GOPALPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 299/RD/PHE | 01/02/2023 | 790 | UTTAM SAHA | 529.88 | 0 | 0 | 75
2498 | UTTAR DINAJPUR | Malda Mechanical | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12785 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head work site at T/W no. I of Gopalpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014866) | 2499/MLMD | 04/08/2023 | 120 | A.G ENTERPRISE. | 29.23 | 0 | 0 | 84
2499 | UTTAR DINAJPUR | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12785 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under GOPALPUR PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 606/RD/PHE | 05/03/2024 | 45 | M/S PRITHWIRAJ CONSTRUCTION | 22.58 | 0 | 0 | 0
2500 | UTTAR DINAJPUR | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12785 | New | Additional Pipe Line and other ancillary works to provide FHTC at GOPALPUR PWSS (New Scheme) under Islampur Sub-Division ,P.H.E. Dte. under Raiganj Division, PHED, Uttar Dinajpur. | 3018/RD/PHE | 03/10/2024 | 45 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 27.54 | 0 | 0 | 0
2501 | UTTAR DINAJPUR | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12785 | New | Construction of concrete pathway ,Land development and other ancillary works for GOPALPUR Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHED.under Raiganj Division,PHED.,U/D. | 3576/RD/PHE | 05/12/2024 | 45 | UTTAM SAHA | 20.94 | 0 | 0 | 0
2502 | UTTAR DINAJPUR | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12785 | New | Trial Run For Gopalpur PWSS under Karandighi Block under Raiganj Division ,PHE Dte. for 3 months | 552/RD/PHE | 12/02/2025 | 90 | UTTAM SAHA | 0.88 | 0 | 0 | 0
2503 | UTTAR DINAJPUR | Raiganj Division | Gopalpur Piped Water Supply Scheme at Karandighi block in the district of Uttar Dinajpur. , SM/12785 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Gopalpur Water Supply Scheme at Karandighi Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 80 M3/hr. | 2481/RD/PHE | 12/09/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 32.36 | 0 | 0 | 0
2504 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12781 | New | Material Requisition To Resource Division | 1329/RD/PHE | 15/05/2023 | 0 | Resource Division | 20.34 | 0 | 0 | 0
2505 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12781 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Dakshin Gorasahid Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014440) | 2493/MLMD | 04/08/2023 | 907 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 28.34 | 0 | 0 | 74
2506 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12781 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
2507 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12781 | New | Laying of additional pipeline for improving FHTC with anciliary works at different mouzas at DAKSHIN GORASAHID PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | 1213/RD/PHE | 25/04/2025 | 45 | SAMIRAN PODDAR SPODDER.UDP@GMAIL.COM | 40.48 | 0 | 0 | 0
2508 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN GORASAHID Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12781 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Dakhshin Gorasahid Water Supply Scheme at Chopra Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 40 M3/hr. | 1925/RD/PHE | 30/06/2025 | 180 | KOHINOOR ALAM | 18.72 | 0 | 0 | 0
2509 | UTTAR DINAJPUR | Raiganj Division | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12796 | New | Material Requisition To Resource Division | 964/RD/PHE | 29/03/2023 | 0 | Resource Division | 16.24 | 0 | 0 | 0
2510 | UTTAR DINAJPUR | Malda Mechanical | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12796 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Uttar Mohangachh Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014503) | 2541/MLMD | 04/08/2023 | 960 | SUBRATA SAHA | 25.68 | 0 | 0 | 72
2511 | UTTAR DINAJPUR | Malda Mechanical | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12796 | New | Quotation for new service connection at UTTAR MOHANGACHH PH-II (Chopra ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/12796) | BP-2024-25-274 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 4.02 | 0 | 0 | 0
2512 | UTTAR DINAJPUR | Raiganj Division | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12796 | New | Sinking of Tube Well, laying of rising main & distribution system, providing FHTC ,construction of Over Head Reservoir over Pile / Raft Foundation including subsoil investigation, construction of Pump House, Chlorine room, Boundary Wall & Approach Road and allied works for 19 nos. Piped water supply Schemes within CHOPRA Dev. Block of Uttar Dinajpur District under Raiganj Division PHE Dte. | 2567/RD/PHE | 01/09/2023 | 805 | ROY ENGINEERS. (PATNA) | 7213.93 | 0 | 0 | 30
2513 | UTTAR DINAJPUR | Raiganj Division | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12796 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at UTTAR MOHANGACHH PWSS Of CHOPRA Block under Islampur Sub-Division P.H.E. Dte. | 1212/RD/PHE | 25/04/2025 | 45 | K.G.N BUILDERS | 33.45 | 0 | 0 | 0
2514 | UTTAR DINAJPUR | Raiganj Division | UTTAR MOHANGACHH Piped Water Supply Scheme at Chopra block under Uttar Dinajpur District. , SM/12796 | New | Providing FHTC in connection with Uttar Mahangachh Pipe Water Supply Scheme at Chopra Block of Uttar Dinajpur District under Raiganj Division.(New PWSS) (2nd Call) | 2173/RD/PHE | 25/07/2025 | 90 | RAKSHIT TRADERS | 8.37 | 0 | 0 | 0
2515 | UTTAR DINAJPUR | Raiganj Division | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12780 | New | Material Requisition To Resource Division | 1126/RD/PHE | 24/04/2023 | 0 | Resource Division | 36.82 | 0 | 0 | 0
2516 | UTTAR DINAJPUR | Malda Mechanical | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12780 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chhota Patna Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/014398) | 2482/MLMD | 04/08/2023 | 960 | MAA BHABOTARINE ENTERPRISE. | 27.46 | 0 | 0 | 73
2517 | UTTAR DINAJPUR | Malda Mechanical | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12780 | New | Quotation for new service connection at Choto Patna PH-I (Goalpokher ccc) | BP-2023-24-541 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 12.08 | 0 | 0 | 0
2518 | UTTAR DINAJPUR | Malda Mechanical | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12780 | New | Quotation for new service connection at Choto Patna PH-II (Goalpokher ccc) | BP-2023-24-540 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 10.71 | 0 | 0 | 0
2519 | UTTAR DINAJPUR | Raiganj Division | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12780 | New | Laying of additional pipeline for improving FHTC with ancillary works at different mouzas at CHOTA PATNA PWSS Of Goalpokhar-1 Block under Islampur Sub-Division P.H.E. Dte. | 1201/RD/PHE | 25/04/2025 | 45 | HAQUE CONSTRUCTION | 39.32 | 0 | 0 | 0
2520 | UTTAR DINAJPUR | Raiganj Division | CHHOTA PATNA Piped Water Supply Scheme at Goalpokhar-I Block under Uttar Dinajpur District. , SM/12780 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Chotopatna Water Supply Scheme at Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 70 M3/hr. | 1996/RD/PHE | 07/07/2025 | 180 | UNIVERSAL ENGINEERS CO-OPERATIVE SOCIETY LTD. | 30.94 | 0 | 0 | 0
2521 | UTTAR DINAJPUR | Raiganj Division | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/14827 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
2522 | UTTAR DINAJPUR | Raiganj Division | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/14827 | New | Material Requisition To Resource Division | 1314/RD/PHE | 12/05/2023 | 0 | Resource Division | 4.13 | 0 | 0 | 0
2523 | UTTAR DINAJPUR | Raiganj Division | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/14827 | New | Implementation of Dhoarai Zone-II and it's adjoining mouzas Pipe Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House at Head Work Site.) | 535/RD/PHE | 22/02/2023 | 90 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. DEBASISHGHOSHDG76@GMAIL.COM | 41.35 | 0 | 0 | 75
2524 | UTTAR DINAJPUR | Raiganj Division | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/14827 | New | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under DHORAI ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 671/RD/PHE | 05/03/2024 | 45 | SCON | 5.57 | 0 | 0 | 0
2525 | UTTAR DINAJPUR | Malda Mechanical | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/14827 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Dhoarai (Zone-II) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017861) | 2743/MLMD | 14/08/2023 | 180 | BINA CONSTRUCTION | 7.19 | 0 | 0 | 100
2526 | UTTAR DINAJPUR | Malda Mechanical | Dhoarai Zone-II Piped Water Supply Scheme at Hemtabad block under Uttar Dianjpur District. , SM/14827 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Dhoarai, (Zone-II), Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-473 | 26/01/2024 | 0 | W.B.S.E.D.C.LTD | 0.14 | 0 | 0 | 0
2527 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Siripur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14227 | Augmentation | Rig Bored Tube-Well In connection with Source Augmentation In Different Piped Water Supply Scheme 1.Debiganj, 2.Gunabari, 3. Majlishpur. 4. Sripur in the District of Uttar Dinajpur Under Raiganj Division, P.H.E. Dte. | 470/RD/PHE | 16/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI | 42.57 | 0 | 0 | 100
2528 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Siripur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14227 | Augmentation | Material Requisition To Resource Division | 2400/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.4 | 0 | 0 | 0
2529 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Siripur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14227 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Siripur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016479) | 2533/MLMD | 04/08/2023 | 120 | BASUDEV GHOSH. | 10.91 | 0 | 0 | 79
2530 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Siripur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14227 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Siripur, Goalpokher C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-435 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.79 | 0 | 0 | 0
2531 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Siripur Piped Water Suppply Scheme under Goalpokhar-I block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14227 | Augmentation | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Siripur Piped Water Supply Scheme of Goalpokhar-I Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 63/RD/PHE | 16/01/2023 | 45 | M/S DOLPHIN CONSTRUCTION DOLPHIN.RGJ@GMAIL.COM | 17.7 | 0 | 0 | 60
2532 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Pawakhali Piped Water Suppply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14231 | Augmentation | Material Requisition To Resource Division | 2389/RD/PHE | 17/08/2023 | 0 | Resource Division | 2.4 | 0 | 0 | 0
2533 | UTTAR DINAJPUR | Malda Mechanical | Source Augmentation for Pawakhali Piped Water Suppply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14231 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Pawakhali Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016476) | 2802/MLMD | 17/08/2023 | 1014 | M/S SABANA CONSTRUCTION | 10.9 | 0 | 0 | 84
2534 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Pawakhali Piped Water Suppply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14231 | Augmentation | Construction of Boundary Wall Laying Distribution, Providing FHTC, Pump House in connection with Source Augmentation of Pawakhali Piped Water Supply Scheme of Chopra Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 60/RD/PHE | 16/01/2023 | 1013 | RAHUL ENTERPRISE RNJRAHULENTERPRISE@GMAIL.COM | 17.91 | 0 | 0 | 50
2535 | UTTAR DINAJPUR | Raiganj Division | Source Augmentation for Pawakhali Piped Water Suppply Scheme under Chopra block in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/14231 | Augmentation | Rig Bored Tube-Well in connection with Source Augmentation In Different Piped Water Supply Scheme 1.Mohua, 2. Pawakhali, 3. Pokheria in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 471/RD/PHE | 16/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI | 31.92 | 0 | 0 | 80
2536 | UTTAR DINAJPUR | Raiganj Division | RAUTARA Pipe Water Supply Scheme , SM/15306 | New | Material Requisition To Resource Division | 1319/RD/PHE | 12/05/2023 | 0 | Resource Division | 45.19 | 0 | 0 | 0
2537 | UTTAR DINAJPUR | Raiganj Division | RAUTARA Pipe Water Supply Scheme , SM/15306 | New | Additional pipeline and other ancillary works at Rahutara piped water Supply Scheme Under Islampur SubDivision under Raiganj Division, P.H.E Dte. | 3307/RD/PHE | 20/11/2024 | 45 | AJIT PRAMANIK | 20.98 | 0 | 0 | 0
2538 | UTTAR DINAJPUR | Raiganj Division | RAUTARA Pipe Water Supply Scheme , SM/15306 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RAUTARA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 661/RD/PHE | 05/03/2024 | 45 | M/S PRATIMA CHOUDHURY | 11.29 | 0 | 0 | 0
2539 | UTTAR DINAJPUR | Raiganj Division | RAUTARA Pipe Water Supply Scheme , SM/15306 | New | Construction of concrete pathway at Head Work Site Pump House & 2nd TW Site Pump House for Rahutara Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHE Dte., U/D. | 3308/RD/PHE | 20/11/2024 | 45 | AJIT PRAMANIK | 16.57 | 0 | 0 | 0
2540 | UTTAR DINAJPUR | Malda Mechanical | RAUTARA Pipe Water Supply Scheme , SM/15306 | New | Quotation for new service connection at RAUTARA PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15306) | BP-2024-25-266 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 13.44 | 0 | 0 | 0
2541 | UTTAR DINAJPUR | Malda Mechanical | RAUTARA Pipe Water Supply Scheme , SM/15306 | New | Quotation for new service connection at RAUTARA PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15306) | BP-2024-25-265 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 7.63 | 0 | 0 | 0
2542 | UTTAR DINAJPUR | Raiganj Division | RAUTARA Pipe Water Supply Scheme , SM/15306 | New | Implementation of RAUTARA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.( Tube-Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work & 2nd TubeWell) | 2481/RD/PHE | 24/08/2023 | 951 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 451.99 | 0 | 0 | 60
2543 | UTTAR DINAJPUR | Malda Mechanical | RAUTARA Pipe Water Supply Scheme , SM/15306 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Rautara Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018384) | 2819/MLMD | 17/08/2023 | 864 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 25.43 | 0 | 0 | 42
2544 | UTTAR DINAJPUR | Raiganj Division | RAUTARA Pipe Water Supply Scheme , SM/15306 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under RAUTARA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 662/RD/PHE | 05/03/2024 | 553 | M/S SANTI TRADERS | 11.29 | 0 | 0 | 80
2545 | UTTAR DINAJPUR | Raiganj Division | KADERGANJ Pipe Water Supply Scheme , SM/15307 | New | Material Requisition To Resource Division | 641/RD/PHE | 02/03/2023 | 0 | Resource Division | 50.52 | 0 | 0 | 0
2546 | UTTAR DINAJPUR | Malda Mechanical | KADERGANJ Pipe Water Supply Scheme , SM/15307 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Kaderganj Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018390) | 2752/MLMD | 14/08/2023 | 867 | M/S PARIMAL DAS. | 25.7 | 0 | 0 | 76
2547 | UTTAR DINAJPUR | Raiganj Division | KADERGANJ Pipe Water Supply Scheme , SM/15307 | New | Construction of concrete pathway ,Land development and other ancillary works for KADERGANJ Piped Water Supply Scheme at Head Work Site Pump House & 2nd Pump House Site under Islampur Sub-Division PHE Dte. under Raiganj Division,PHE Dte.,U/D. | 3781/RD/PHE | 19/12/2024 | 30 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 12.65 | 0 | 0 | 0
2548 | UTTAR DINAJPUR | Raiganj Division | BASUDEBPUR Piped Water Supply Scheme , SM/14182 | New | Material Requisition To Resource Division | 1199/RD/PHE | 28/04/2023 | 0 | Resource Division | 54.77 | 0 | 0 | 0
2549 | UTTAR DINAJPUR | Malda Mechanical | BASUDEBPUR Piped Water Supply Scheme , SM/14182 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Basudebpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017263) | 2470/MLMD | 04/08/2023 | 907 | ANIMA ENTERPRISE | 25.54 | 0 | 0 | 76
2550 | UTTAR DINAJPUR | Raiganj Division | BASUDEBPUR Piped Water Supply Scheme , SM/14182 | New | Construction of concrete pathway with earth filling at Head Work Site Pump House & 2nd TW Site Pump House for Basudebpur Piped Water Supply Scheme under Islampur Sub-Division PHED.under Raiganj Division,PHE Dte.,U/D. | 3302/RD/PHE | 20/11/2024 | 30 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 10.41 | 0 | 0 | 0
2551 | UTTAR DINAJPUR | Raiganj Division | BASUDEBPUR Piped Water Supply Scheme , SM/14182 | New | Rig bored Tube-Well in connection with Implementation of New PWSS in different Pipe Water Supply Scheme(New) 1.Lahutara, 2. Hemenpur, 3. Basudebpur in the District Of Uttar Dinajpur under Raiganj Division, PHE Dte. | 541/RD/PHE | 22/02/2023 | 45 | M/S SARKAR ENTERPRISE SILIGURI SARKARETP2010@GMAIL.COM | 61.71 | 0 | 0 | 60
2552 | UTTAR DINAJPUR | Raiganj Division | BASUDEBPUR Piped Water Supply Scheme , SM/14182 | New | Implementation of BASUDEBPUR and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 562/RD/PHE | 23/02/2023 | 1035 | M/S LOKENATH CONSTRUCTION | 536.97 | 0 | 0 | 45
2553 | UTTAR DINAJPUR | Raiganj Division | BASUDEBPUR Piped Water Supply Scheme , SM/14182 | New | Additional pipeline and other ancillary works at Basudebpur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | 3301/RD/PHE | 20/11/2024 | 45 | JANAPATH ENGINEERS CO-OP. SOCIETY LTD. | 36.59 | 0 | 0 | 0
2554 | UTTAR DINAJPUR | Raiganj Division | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15213 | New | Material Requisition To Resource Division | 635/RD/PHE | 02/03/2023 | 0 | Resource Division | 49.14 | 0 | 0 | 0
2555 | UTTAR DINAJPUR | Raiganj Division | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15213 | New | Implementation of DHAUTA and it's adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, OHR, Pump House at Head Work,2nd Tube Well) | 2476/RD/PHE | 24/08/2023 | 823 | AJIT PRAMANIK AJITPRAMANICK82@GMAIL.COM | 448.76 | 0 | 0 | 62
2556 | UTTAR DINAJPUR | Malda Mechanical | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15213 | New | Quotation for new service connection at DHAUTA PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15213). | BP-2024-25-268 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 7.37 | 0 | 0 | 0
2557 | UTTAR DINAJPUR | Malda Mechanical | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15213 | New | Quotation for new service connection at DHAUTA PH-II (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/15213). | BP-2024-25-267 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 8.09 | 0 | 0 | 0
2558 | UTTAR DINAJPUR | Malda Mechanical | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15213 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II of Dhauta Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018375) | 2742/MLMD | 14/08/2023 | 870 | M/S TRILOCHAN CONSTRUCTION CO. | 24.36 | 0 | 0 | 90
2559 | UTTAR DINAJPUR | Raiganj Division | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15213 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DHAUTA PWSS at Karandighi Block under Raiganj Division, PHE Dte. | 643/RD/PHE | 05/03/2024 | 501 | UP-SHINE ENGINEERS CO-OP.&CONTRUCTION SOCIETY LTD. | 22.58 | 0 | 0 | 80
2560 | UTTAR DINAJPUR | Raiganj Division | DHAUTA PIPED WATER SUPPLY SCHEME AT KARANDIGHI BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/15213 | New | Laying Upvc Pipe Line And Others Anciliary Warks Of Dhauta Pwss Within Karandighi Block Under Raiganj Division P.H.E. Dte., Raiganj, Uttar Dinajpur. | 29/RD/PHE | 02/01/2025 | 45 | AJIT PRAMANIK | 94.84 | 0 | 0 | 0
2561 | UTTAR DINAJPUR | Raiganj Division | NARAYANPUR Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/16225 | New | Material Requisition To Resource Division | 807/RD/PHE | 21/03/2023 | 0 | Resource Division | 27.45 | 0 | 0 | 0
2562 | UTTAR DINAJPUR | Raiganj Division | NARAYANPUR Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/16225 | New | Implementation of NARAYANPUR and its adjoining mouzas Pipe Water Supply Scheme at CHOPRA Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1500/RD/PHE | 19/05/2023 | 1110 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 270.42 | 0 | 0 | 60
2563 | UTTAR DINAJPUR | Raiganj Division | NARAYANPUR Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/16225 | New | Laying of Additional Pipeline with land development for NARAYANPUR Water Supply Scheme for installation of FHTC Work under Islampur Sub-Division P.H.E. Dte. under Raiganj Division, P.H.E Dte.,U/D. | 3557/RD/PHE | 05/12/2024 | 45 | SANDIP SARKAR | 27.06 | 0 | 0 | 0
2564 | UTTAR DINAJPUR | Malda Mechanical | NARAYANPUR Piped Water Supply Scheme at Chopra Block under Uttar Dinajpur District. , SM/16225 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Narayanpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018406) | 2639/MLMD | 10/08/2023 | 1051 | JAL PRAVAHIKA PVT. LTD. | 26.28 | 0 | 0 | 0
2565 | UTTAR DINAJPUR | Raiganj Division | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16505 | New | Preparation & Submission of DPR for drinking water supply scheme to facilitate 10 Nos (List Enclosed) Uncovered mouzas under Uttar Dinajpur District (Hemtabad Block) under Raiganj Division, PHE Dte. (Sl no 1) | 1769/RD/PHE | 19/09/2022 | 7 | RADIANT | 63.04 | 0 | 0 | 100
2566 | UTTAR DINAJPUR | Raiganj Division | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16505 | New | Material Requisition To Resource Division | 1313/RD/PHE | 12/05/2023 | 0 | Resource Division | 3.19 | 0 | 0 | 0
2567 | UTTAR DINAJPUR | Raiganj Division | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16505 | New | Providing Balance Functional House Hold Connection (FHTC) For Balufara Zone-II Piped Water Supply Scheme of Raiganj Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2225/RD/PHE | 23/07/2024 | 30 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 6.52 | 0 | 0 | 0
2568 | UTTAR DINAJPUR | Malda Mechanical | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16505 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I of Balufara (Zone-II) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/016905) | 2460/MLMD | 04/08/2023 | 120 | JOY MAA SANTOSHI ENTERPRISE. | 7.18 | 0 | 0 | 100
2569 | UTTAR DINAJPUR | Malda Mechanical | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16505 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Balufara, (Zone-II), Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-474 | 26/01/2024 | 0 | W.B.S.E.D.C.LTD | 0.14 | 0 | 0 | 0
2570 | UTTAR DINAJPUR | Raiganj Division | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16505 | New | Implementation of Balufara Zone-II and it's adjoining mouzas Pipe Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House at Head Work Site.) | 680/RD/PHE | 06/03/2023 | 630 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 51.19 | 0 | 0 | 100
2571 | UTTAR DINAJPUR | Raiganj Division | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16505 | New | Trial Run For Balufara Zone-II PWSS under Hemtabad Block under Raiganj Division ,PHE Dte. for 3 months | 530/RD/PHE | 12/02/2025 | 90 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 0.82 | 0 | 0 | 0
2572 | UTTAR DINAJPUR | Raiganj Division | Balufara Zone-II Piped Water Supply Scheme at Hemtabad Block under Uttar Dinajpur District. , SM/16505 | New | Construction of Boundary Wall With Gate at Head Work Tube-Well Site under BALUFARA ZONE-II PWSS at Hemtabad Block under Raiganj Division, PHE Dte. | 620/RD/PHE | 05/03/2024 | 225 | M/S MAA BOLLA CONSTRUCTION | 5.56 | 0 | 0 | 100
2573 | UTTAR DINAJPUR | Malda Mechanical | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/15904 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BELAGACHHI, Islampur C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003195371 | 18/07/2023 | 90 | W.B.S.E.D.C.LTD | 10.69 | 0 | 0 | 100
2574 | UTTAR DINAJPUR | Raiganj Division | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/15904 | New | Material Requisition To Resource Division | 606/RD/PHE | 27/02/2023 | 0 | Resource Division | 42.2 | 0 | 0 | 0
2575 | UTTAR DINAJPUR | Malda Mechanical | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/15904 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bhelagachhi Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/017356) | 2480/MLMD | 04/08/2023 | 480 | ANIMA ENTERPRISE | 26.45 | 0 | 0 | 100
2576 | UTTAR DINAJPUR | Malda Mechanical | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/15904 | New | Additional Quotation for new service connection at BHELAGACCHI PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | BP-2024-25-40 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 5.28 | 0 | 0 | 0
2577 | UTTAR DINAJPUR | Raiganj Division | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/15904 | New | Hiring of vehicle for transportation of water sample collection from different BPHC to district lab uttar dinajpur | BP-2023-24-274 | 09/02/2024 | 0 | FARHAD ALI | 0.05 | 0 | 0 | 0
2578 | UTTAR DINAJPUR | Malda Mechanical | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/15904 | New | Quotation for new service connection at Bhelagacchi PH-II (Islampur ccc) district Uttar Dinajpur. | BP-2023-24-591 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 7.31 | 0 | 0 | 0
2579 | UTTAR DINAJPUR | Raiganj Division | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/15904 | New | Implementation of BHELAGACHHI and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division.PHE Dte. | 670/RD/PHE | 06/03/2023 | 970 | M/S LOKENATH CONSTRUCTION | 581.2 | 0 | 0 | 65
2580 | UTTAR DINAJPUR | Raiganj Division | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/15904 | New | Laying of Additional pipeline with other ancillary works at different mouzas of BHELAGACHHI PWSS under Islampur Sub-Division P.H.E. Dte. | 3492/RD/PHE | 02/12/2024 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 79.83 | 0 | 0 | 0
2581 | UTTAR DINAJPUR | Raiganj Division | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/15904 | New | Construction of Approach Road at Head Work Site, & 2nd Tube-Well Site under New Scheme of Bhelagachhi PWSS at Islampur Block under Raiganj Division, PHE dte. | 2893/RD/PHE | 25/09/2024 | 20 | GOPES SAHA | 6.18 | 0 | 0 | 0
2582 | UTTAR DINAJPUR | Raiganj Division | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/15904 | New | Trial Run For Bhelagachi PWSS under Islampur Block under Raiganj Division ,PHE Dte. for 3 months | 548/RD/PHE | 12/02/2025 | 90 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 0.88 | 0 | 0 | 0
2583 | UTTAR DINAJPUR | Raiganj Division | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/15904 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BHELAGACHHI PWSS at Islampur Block under Raiganj Division, PHE Dte. | 543/RD/PHE | 05/03/2024 | 360 | KULICK ENTERPRISE | 11.28 | 0 | 0 | 100
2584 | UTTAR DINAJPUR | Raiganj Division | BELAGACHHI Piped Water Supply Scheme at Islampur Block under Uttar Dinajpur District. , SM/15904 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under BHELAGACHHI PWSS at Islampur Block under Raiganj Division, PHE Dte. | 542/RD/PHE | 05/03/2024 | 333 | M/S UNIQUE 13 | 11.28 | 0 | 0 | 100
2585 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN DAMORGACHH PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR. , SM/18149 | New | Material Requisition To Resource Division | 2271/RD | 03/08/2023 | 0 | Resource Division | 6.79 | 0 | 0 | 0
2586 | UTTAR DINAJPUR | Malda Mechanical | DAKSHIN DAMORGACHH PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR. , SM/18149 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no. I & II of Dakshin Damorgachh Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020855) | 4776/MLMD | 29/12/2023 | 180 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 14.41 | 0 | 0 | 82
2587 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN DAMORGACHH PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR. , SM/18149 | New | Implementation of DAKSHIN DAMODARGACHH and it's adjoining mouzas Pipe Water Supply Scheme at CHOPRA Block of Uttar Dinajpur District under Raiganj Division. (Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections & Pump House.) | 1555/RD/PHE | 29/05/2023 | 909 | M/S LUCKY CONSTRUCTION MSLUCKYCONSTRUCTION@GMAIL.COM | 81.37 | 0 | 0 | 50
2588 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN DAMORGACHH PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR. , SM/18149 | New | Additional pipeline, Pathway, Land Development and other ancillary works at Dakshin Damodargachh Piped Water Supply Scheme Under Islampur Sub-Division under Raiganj Division, P.H.E Dte. | 1596/RD/PHE | 16/06/2025 | 120 | SANDIP SARKAR | 12.06 | 0 | 0 | 0
2589 | UTTAR DINAJPUR | Raiganj Division | DAKSHIN DAMORGACHH PIPED WATER SUPPLY SCHEME IN CHOPRA BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR. , SM/18149 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DAKSHIN DAOMODARGACHH PWSS at Chopra Block under Raiganj Division, PHE Dte. | 1709/RD/PHE | 10/06/2024 | 270 | FIZA CONSTRUCTION | 10.19 | 0 | 0 | 100
2590 | UTTAR DINAJPUR | Raiganj Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18164 | New | Material Requisition To Resource Division | 2265/RD/PHE | 03/08/2023 | 0 | Resource Division | 11.63 | 0 | 0 | 0
2591 | UTTAR DINAJPUR | Malda Mechanical | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18164 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II of Krishnapur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020850) | 4765/MLMD | 29/12/2023 | 180 | JOY MAA SANTOSHI ENTERPRISE. | 19.99 | 0 | 0 | 82
2592 | UTTAR DINAJPUR | Raiganj Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18164 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under KRISNAPUR PWSS at Raiganj Block under Raiganj Division,PHE Dte. | 626/RD/PHE | 05/03/2024 | 45 | M/S UNIQUE 13 | 10.26 | 0 | 0 | 0
2593 | UTTAR DINAJPUR | Malda Mechanical | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18164 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Krishnapur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-209 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 1.13 | 0 | 0 | 0
2594 | UTTAR DINAJPUR | Malda Mechanical | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18164 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Krishnapur, Raiganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-208 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.18 | 0 | 0 | 0
2595 | UTTAR DINAJPUR | Raiganj Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18164 | New | Demand for placing necessary fund for the work of Permanent restoration of damaged hard shoulder/flank caused due pipe laying by PHE Department under Krishnapur PWSS at a stretches of Thakurbari-Bindol road under Uttar Dinajpur Highway Division, PWD (Roads) Dte. | BP-2024-25-83 | 18/06/2024 | 0 | EXECUTIVE ENGINEER PWD ROADS | 10.34 | 0 | 0 | 0
2596 | UTTAR DINAJPUR | Raiganj Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18164 | New | Implementation of KRISHNAPUR and it's adjoining mouzas Pipe Water Supply Scheme at RAIGANJ Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1996/RD/PHE | 13/07/2023 | 629 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 135.44 | 0 | 0 | 55
2597 | UTTAR DINAJPUR | Raiganj Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME IN RAIGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18164 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Krishnapur PWSS at Raiganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3759/RD/PHED | 18/12/2024 | 135 | ANILA CONSTRUCTION | 11.51 | 0 | 0 | 0
2598 | UTTAR DINAJPUR | Raiganj Division | DALIMGAON PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18168 | New | Material Requisition To Resource Division | 2264/RD/PHE | 03/08/2023 | 0 | Resource Division | 11.05 | 0 | 0 | 0
2599 | UTTAR DINAJPUR | Raiganj Division | DALIMGAON PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18168 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Dalimgaon PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 3779/RD/PHE | 19/12/2024 | 45 | JEET CONSTRUCTION (UKILPARA) | 15.07 | 0 | 0 | 0
2600 | UTTAR DINAJPUR | Malda Mechanical | DALIMGAON PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18168 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Dalimgaon, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-186 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.65 | 0 | 0 | 0
2601 | UTTAR DINAJPUR | Malda Mechanical | DALIMGAON PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18168 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dalimgaon, Kaliyaganj CCC in the dist of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2024-25-185 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 6.11 | 0 | 0 | 0
2602 | UTTAR DINAJPUR | Raiganj Division | DALIMGAON PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18168 | New | Implementation of DALIMGAON and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 1305/RD/PHE | 12/05/2023 | 810 | TAPAN KUMAR DUTTA ARNABD121@GMAIL.COM | 130.31 | 0 | 0 | 50
2603 | UTTAR DINAJPUR | Malda Mechanical | DALIMGAON PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18168 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II of Dalimgaon Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020863) | 4767/MLMD | 29/12/2023 | 400 | KAMAKHYA ENTERPRISE. | 19.81 | 0 | 0 | 100
2604 | UTTAR DINAJPUR | Raiganj Division | DALIMGAON PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18168 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | 1746/RD/PHE | 14/06/2024 | 198 | DEBASISH GHOSH | 2.6 | 0 | 0 | 0
2605 | UTTAR DINAJPUR | Raiganj Division | DALIMGAON PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18168 | New | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
2606 | UTTAR DINAJPUR | Raiganj Division | DALIMGAON PIPED WATER SUPPLY SCHEME IN KALIYAGANJ BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18168 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under DALIMGAON PWSS at Kaliaganj Block under Raiganj Division, PHE Dte. | 627/RD/PHE | 05/03/2024 | 45 | BIKRAM KUNDU | 10.26 | 0 | 0 | 100
2607 | UTTAR DINAJPUR | Raiganj Division | BHARATPUR PIPED WATER SUPPLY SCHEME IN HEMTABAD BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18170 | New | Material Requisition To Resource Division | 2256/RD/PHE | 03/08/2023 | 0 | Resource Division | 5.9 | 0 | 0 | 0
2608 | UTTAR DINAJPUR | Malda Mechanical | BHARATPUR PIPED WATER SUPPLY SCHEME IN HEMTABAD BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18170 | New | Supply, installation ,commissioning and trial operation of electro-mechanical components at T/W no.I & II of Bharatpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/020865) | 2701/MLMD | 11/08/2023 | 989 | SUBRATA KUMAR DAS. | 14.25 | 0 | 0 | 79
2609 | UTTAR DINAJPUR | Raiganj Division | BHARATPUR PIPED WATER SUPPLY SCHEME IN HEMTABAD BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18170 | New | Implementation of BHARATPUR and it's adjoining mouzas Pipe Water Supply Scheme at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division.(Sinking of Tube Well, Laying of Rising Main, Laying Distribution pipe line, Providing Functional house Hold Tap Connections, Pump House and Boundary Wall.) | 1556/RD/PHE | 29/05/2023 | 900 | BHOLA PAUL | 92.43 | 0 | 0 | 50
2610 | UTTAR DINAJPUR | Raiganj Division | BHARATPUR PIPED WATER SUPPLY SCHEME IN HEMTABAD BLOCK UNDER RAIGANJ DIVISION, UTTAR DINAJPUR DISTRICT. , SM/18170 | New | Continuation Order Hiring of well-maintained Diesel Maxi Cab (Non-A.C. , Vehicle no. WB59C 2323) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire Raiganj Sub-Division, P.H.E. Dte. under Raiganj Division, P.H.E. Dte. in the District of Uttar Dinajpur. Period from 01.07.2024 to 14.01.2025. | 1746/RD/PHE | 14/06/2024 | 198 | DEBASISH GHOSH | 2.6 | 0 | 0 | 0
2611 | UTTAR DINAJPUR | Raiganj Division | CHAPWA PIPED WATER SUPPLY SCHEME at GOALPOKHAR-I BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16647 | New | Material Requisition To Resource Division | 2269/RD | 03/08/2023 | 0 | Resource Division | 30.86 | 0 | 0 | 0
2612 | UTTAR DINAJPUR | Malda Mechanical | CHAPWA PIPED WATER SUPPLY SCHEME at GOALPOKHAR-I BLOCK UNDER UTTAR DINAJPUR DISTRICT. , SM/16647 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chapwa Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018401) | 2642/MLMD | 10/08/2023 | 1034 | ANIMA ENTERPRISE | 27.45 | 0 | 0 | 0
2613 | UTTAR DINAJPUR | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. , SM/18227 | Augmentation | GROUND BORED BIG DIA TUBE WELL FOR KALIAGANJ MUNICIPAL ZONE-I WSS | 156/RD | 04/02/2020 | 2192 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 8.01 | 0 | 0 | 100
2614 | UTTAR DINAJPUR | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. , SM/18227 | Augmentation | GROUND BORED BIG DIA TUBE WELL FOR KUNOR WSS | 157/RD | 04/02/2020 | 2192 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 8.64 | 0 | 0 | 100
2615 | UTTAR DINAJPUR | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. , SM/18227 | Augmentation | SINKING GROUND BORED REPLACEMENT OF ISLAMPUR ZONE-II PWSS | 155/RD | 04/02/2020 | 90 | SAMIRAN PODDAR | 13.96 | 0 | 0 | 100
2616 | UTTAR DINAJPUR | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. , SM/18227 | Augmentation | Replacement of 250 x150mm dia. Tube-Well 250mtr. deep Rig bored Tube-Well for Pokheria PWSS at Itahar Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 199/RD/PHE | 25/01/2024 | 20 | UNITED PROGRESSIVE ENGINEERS CO-OP &CONSTRUCTION SOCIETY LTD. | 12.89 | 0 | 0 | 100
2617 | UTTAR DINAJPUR | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. , SM/18227 | Augmentation | Sinking of Ground Bored Replacement Tube-Well 250mm x 150mm dia. of 180 mtr. Direct Rotary Rig Method at Ghirnigaon Khas TW Site under Raiganj Division, P.H.E Dte.(SM/18227) | 71/RD/PHE | 06/01/2025 | 30 | M/S SARKAR ENTERPRISE SILIGURI | 10.69 | 0 | 0 | 0
2618 | UTTAR DINAJPUR | Raiganj Division | Replacement T/W for 4 Nos. water supply scheme. , SM/18227 | Augmentation | Replacement for Replacement Tube-Well & Inter Connection in connection With Head Work Site of Phulatti PWSS under Raiganj Division, P.H.E Dte. | 72/RD/PHE | 06/01/2025 | 30 | M/S SARKAR ENTERPRISE SILIGURI | 11.35 | 0 | 0 | 0
2619 | UTTAR DINAJPUR | Raiganj Division | BHIKHANPUR PWSS , SM/18628 | New | Material Requisition To Resource Division | 829/RD/PHE | 22/03/2023 | 0 | Resource Division | 79.15 | 0 | 0 | 0
2620 | UTTAR DINAJPUR | Raiganj Division | BHIKHANPUR PWSS , SM/18628 | New | Material Requisition To Resource Division | 642/RD/PHE | 02/03/2023 | 0 | Resource Division | 78.14 | 0 | 0 | 0
2621 | UTTAR DINAJPUR | Raiganj Division | BHIKHANPUR PWSS , SM/18628 | New | Additional pipeline and other ancillary works at Bhikhanpur piped water Supply Scheme Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | 3487/RD/PHE | 02/12/2024 | 45 | RAKSHIT TRADERS | 29.04 | 0 | 0 | 0
2622 | UTTAR DINAJPUR | Malda Mechanical | BHIKHANPUR PWSS , SM/18628 | New | Quotation for new service connection at BHIKHANPUR PH-III (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18628) | BP-2024-25-520 | 26/09/2024 | 0 | W.B.S.E.D.C.LTD | 13.39 | 0 | 0 | 0
2623 | UTTAR DINAJPUR | Malda Mechanical | BHIKHANPUR PWSS , SM/18628 | New | Quotation for new service connection at BHIKHANPUR PH-I (Karandighi ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18628) | BP-2024-25-519 | 26/09/2024 | 0 | W.B.S.E.D.C.LTD | 9.89 | 0 | 0 | 0
2624 | UTTAR DINAJPUR | Raiganj Division | BHIKHANPUR PWSS , SM/18628 | New | Implementation of BHIKHANPUR and its adjoining mouzas Pipe Water Supply Scheme at KARANDIGHI Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2474/RD/PHE | 24/08/2023 | 860 | M/S PINKI CONSTRUCTION | 647.91 | 0 | 0 | 65
2625 | UTTAR DINAJPUR | Malda Mechanical | BHIKHANPUR PWSS , SM/18628 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Bhikhanpur Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018357) | 3702/MLMD | 29/11/2023 | 910 | ANIMA ENTERPRISE | 37.03 | 0 | 0 | 88
2626 | UTTAR DINAJPUR | Malda Mechanical | BHIKHANPUR PWSS , SM/18628 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-I under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte | 4277/MLMD | 27/12/2024 | 59 | RAMCHANDRA BASAK | 0.77 | 0 | 0 | 100
2627 | UTTAR DINAJPUR | Raiganj Division | BHIKHANPUR PWSS , SM/18628 | New | Restoration of damage pipeline during road widening at Bikhanpur piped water Supply Scheme at Karandighi Block Under Islampur SubDivision under Raiganj Division,P.H.E Dte. | 1609/RD/PHE | 17/06/2025 | 120 | M/S PINKI CONSTRUCTION | 13.22 | 0 | 0 | 0
2628 | UTTAR DINAJPUR | Malda Mechanical | ILLUABARI PWSS , SM/18449 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Iluabari Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte.(TSM/018454) | 3699/MLMD | 29/11/2023 | 180 | SHREE BISHNU CONSTRUCTION | 27.45 | 0 | 0 | 0
2629 | UTTAR DINAJPUR | Raiganj Division | ILLUABARI PWSS , SM/18449 | New | Material Requisition To Resource Division | 604/RD/PHE | 27/02/2023 | 0 | Resource Division | 35.46 | 0 | 0 | 0
2630 | UTTAR DINAJPUR | Malda Mechanical | ILLUABARI PWSS , SM/18449 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Iluabari (Zone-I) Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/018454) | 2697/MLMD | 11/08/2023 | 1050 | KAMAKHYA ENTERPRISE. | 27.18 | 0 | 0 | 82
2631 | UTTAR DINAJPUR | Malda Mechanical | ILLUABARI PWSS , SM/18449 | New | Quotation for new service connection at ILLUABARI PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18449) | BP-2024-25-180 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 12.28 | 0 | 0 | 0
2632 | UTTAR DINAJPUR | Malda Mechanical | ILLUABARI PWSS , SM/18449 | New | Quotation for new service connection at ILLUABARI PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18449) | BP-2024-25-179 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 8.84 | 0 | 0 | 0
2633 | UTTAR DINAJPUR | Malda Mechanical | ILLUABARI PWSS , SM/18449 | New | Quotation for new service connection at ILLUABARI ZONE-II PH-II (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18449) | BP-2024-25-481 | 09/09/2024 | 0 | W.B.S.E.D.C.LTD | 3.64 | 0 | 0 | 0
2634 | UTTAR DINAJPUR | Malda Mechanical | ILLUABARI PWSS , SM/18449 | New | Quotation for new service connection at ILLUABARI ZONE-II PH-I (Islampur ccc) in the district of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (SM/18449) | BP-2024-25-480 | 09/09/2024 | 0 | W.B.S.E.D.C.LTD | 5.89 | 0 | 0 | 0
2635 | UTTAR DINAJPUR | Raiganj Division | ILLUABARI PWSS , SM/18449 | New | Implementation of ILUABARI (Zone-I & Zone-II) and it's adjoining mouzas Pipe Water Supply Scheme at ISLAMPUR Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 2301/RD/PHE | 04/08/2023 | 881 | M/S. B. PAUL & COMPANY | 1194.94 | 0 | 0 | 60
2636 | UTTAR DINAJPUR | Raiganj Division | ILLUABARI PWSS , SM/18449 | New | Construction of Boundary Wall With Gate at Head Work Site& 2nd Tube-Well Site under ILUABARI PWSS (ZONE-I) & ILUABARI PWSS (ZONE-II) at Islampur Block under Raiganj Division, PHE Dte. | 637/RD/PHE | 05/03/2024 | 434 | M/S. B. PAUL & COMPANY | 47.94 | 0 | 0 | 85
2637 | UTTAR DINAJPUR | Raiganj Division | ILLUABARI PWSS , SM/18449 | New | Laying additional pipe line,Road Restoration and Approach Road in connection with New Scheme Of Iluabari Zone-I and Zone-II Pipe Water Supply Scheme at Islampur Block of Uttar Dinajpur District under Raiganj Division. | 3579/RD/PHE | 05/12/2024 | 405 | M/S. B. PAUL & COMPANY | 97.01 | 0 | 0 | 20
2638 | UTTAR DINAJPUR | Raiganj Division | ILLUABARI PWSS , SM/18449 | New | Designing, Supplying, Febrication, Erection on suitable RCC foundation, commissioning with 3(three) months Trial Run (including cost of routine testing of water sample and flow/hr for performance evaluation) of pressure type Iron Removal Plant as per design norms of CPHEEO(latest) with necessary accessories for Iluabari Zone-I & Zone-II Water Supply Scheme at Islampur Block under Raiganj Division, P.H.E. Dte. Dist:- Uttar Dinajpur, Capacity- 120 M3/hr. | 2013/RD/PHE | 08/07/2025 | 180 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 59.18 | 0 | 0 | 0
2639 | UTTAR DINAJPUR | Raiganj Division | Restoration of Pipe line for providing FHTC for Bindol Water Supply Scheme under Raiganj Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur (Phase-II) , SM/18993 | Retrofitting | Restoration of Pipe Line For Providing FHTC for Bindol Water Supply Scheme Under Raiganj Block under Raiganj Division P.H.E. Dte. in the District of Uttar Dinajpur.(Phase-II) | 2873/RD/PHE | 17/10/2023 | 45 | SARNALI ENTERPRISE SARNALI.RNJ@GMAIL.COM | 8.45 | 0 | 0 | 100
2640 | UTTAR DINAJPUR | Malda Mechanical | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12100 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of SINTAIR, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003195013 | 19/07/2023 | 90 | W.B.S.E.D.C.LTD | 2.56 | 0 | 0 | 100
2641 | UTTAR DINAJPUR | Malda Mechanical | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12100 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of SINTAIR, Kaliyaganj C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003194802 | 18/07/2023 | 90 | W.B.S.E.D.C.LTD | 2.81 | 0 | 0 | 100
2642 | UTTAR DINAJPUR | Raiganj Division | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12100 | New | Material Requisition To Resource Division | 27/RD/PHE | 06/01/2023 | 0 | Resource Division | 31.09 | 0 | 0 | 0
2643 | UTTAR DINAJPUR | Raiganj Division | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12100 | New | Implementation of SINTAIR and it's adjoining mouzas Pipe Water Supply Scheme at Kaliaganj Block of Uttar Dinajpur District under Raiganj Division, PHE Dte. | 72/RD/PHE | 16/01/2023 | 1081 | SANYAL ENTERPRISE ABHIJITSANYAL2010@GMAIL.COM | 405.17 | 0 | 0 | 55
2644 | UTTAR DINAJPUR | Malda Mechanical | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12100 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Sintair Water Supply Scheme in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/012780) | 1120/MLMD | 23/06/2023 | 120 | DEY ENTERPRISE [HOWRAH] | 25.23 | 0 | 0 | 84
2645 | UTTAR DINAJPUR | Raiganj Division | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12100 | New | Construction of Boundary Wall With Gate at Head Work Site & 2nd Tube-Well Site under SINTAIR Piped Water Supply Scheme at Kaliaganj Block under Raiganj Division, PHE Dte. in the District of Uttar Dinajpur. | 587/RD/PHE | 05/03/2024 | 45 | M/S KALYAN | 22.57 | 0 | 0 | 0
2646 | UTTAR DINAJPUR | Raiganj Division | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12100 | New | Balance pipe line for providing functional household tap connection (FHTC), approach road with land development of headwork site & 2nd tubewell site and road restoration of Sintair PWSS at Kaliyaganj Block under Raiganj Division, PHE Dte., Uttar Dinajpur. | 10/RD/PHE | 02/01/2025 | 45 | M/S LOKENATH CONSTRUCTION (SUDARSHANPUR) | 58.34 | 0 | 0 | 0
2647 | UTTAR DINAJPUR | Raiganj Division | SINTAIR Piped Water Supply Scheme at kaliyaganj block under uttar Dinajpur district , SM/12100 | New | Trial Run For Sintair PWSS under Kaliayaganj Block under Raiganj Division ,PHE Dte. for 3 months | 524/RD/PHE | 12/02/2025 | 90 | SANYAL ENTERPRISE | 0.88 | 0 | 0 | 0
2648 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11727 | Augmentation | FHTC (Functional Household Tap Connection) for Hemtabad Zone-II Water Supply Scheme [Augmentation Scheme] in Hemtabad Block of Uttar Dinajpur District Under Raiganj Division, PHE Dte. | 2021/RD/PHE | 17/11/2022 | 90 | BHOLA PAUL | 64.54 | 0 | 0 | 0
2649 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11727 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-II) T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 2953/MLMD | 28/12/2022 | 90 | BISWAS SUPPLIERS. | 10.94 | 0 | 0 | 0
2650 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11727 | Augmentation | Construction of Pump house for (5.4 x 3.6) at Head work site and(3.6x3.0) at 2nd Tubewell Site of Hemtabad Zone-II Water Supply Schemes Augmentation under Hemtabad Block under Raiganj Division, PHE Dte. in the district of Uttar Dinajpur. | 389/RD/PHE | 07/02/2023 | 45 | M/S SANJIB BHATTACHARJEE SANJIB.RNJ@GMAIL.COM | 11.8 | 0 | 0 | 100
2651 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11727 | Augmentation | Construction of Over Head Reservoir(Capacity-400 Cum) of HEMTABAD (Zone-II) Pipe Water Supply Scheme in connection with Augmentation at HEMTABAD Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte. | 729/RD/PHE | 15/03/2023 | 365 | SOVAN KUMAR ROY | 143.15 | 0 | 0 | 0
2652 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11727 | Augmentation | Making compound lighting arrangement and installation of grid connected solar PV system with net metering at T/W no. I of Augmentation of Hemtabad Water Supply Scheme, (Zone- II) in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011655) | 2657/MLMD | 10/08/2023 | 1915 | MAA BHABOTARINE ENTERPRISE. | 9.02 | 0 | 0 | 0
2653 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11727 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T.W No. II (Zone-II) of Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003083063 | 13/02/2023 | 7 | W.B.S.E.D.C.LTD | 0.54 | 0 | 0 | 0
2654 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11727 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T.W No. I (Zone-II) of Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | 4003083051 | 13/02/2023 | 7 | W.B.S.E.D.C.LTD | 0.65 | 0 | 0 | 0
2655 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11727 | Augmentation | Material Requisition To Resource Division | 1953/RD/PHE | 04/11/2022 | 0 | Resource Division | 143.46 | 0 | 0 | 0
2656 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11727 | Augmentation | Augmentation work of HEMTABAD ZONE-II Water Supply Scheme at Hemtabad Block of Uttar Dinajpur District under Raiganj Division, P.H.E. Dte., Govt. of West Bengal | 1548/RD/PHE | 26/08/2022 | 90 | UTTAM SAHA | 425.89 | 0 | 0 | 52
2657 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11727 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-II) T/W no. II in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. | 245/MLMD | 24/02/2023 | 90 | DAS CONSTRUCTION | 11.06 | 0 | 0 | 100
2658 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11727 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation of HEMTABAD Water Supply Scheme (Zone-II) T/W no. I in the District of Uttar Dinajpur under Malda Mechanical Division, PHE Dte. (TSM/011655) | 1664/MLMD | 28/06/2023 | 90 | PABITRA MANDAL | 11.51 | 0 | 0 | 100
2659 | UTTAR DINAJPUR | Malda Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11727 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Hemtabad, Zone-II, Hemtabad C.C.C in the district of Uttar Dinajpur Under Malda Mechanical Division PHE Dte. | BP-2023-24-414 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.53 | 0 | 0 | 0
2660 | UTTAR DINAJPUR | Raiganj Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Hemtabad Zone-II in Hemtabad Block under Raiganj Division, P.H.E. Dte. in the district of Uttar Dinajpur. , SM/11727 | Augmentation | Field level data validation of FHTC executed by various Agencies on the basis of pictorial data with the objective of controlling multiple entry, improving data quality in terms of absolute household by verification through electric connection or any other unique documents and making error free database in different Pipe Water Supply Scheme in different Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. | 737/RD/PHE | 12/03/2024 | 30 | HORIZEN | 5 | 0 | 0 | 100
2661 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09184 | Retrofitting | Providing support services for DPR preparation of Rejuvenation & Augmentation of existing Dharampur -I Piped Water Supply Scheme for providing Functional Household Tap Connection (FHTC) to all house Holds in connection with Jal Jeevan Mission and Jal Swapna under Goalpokhar - I Block in the District of Uttar Dinajpur under Raiganj Division, PHE Dte. Govt. of W.B. | 1814/RD/PHE | 14/09/2021 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM | 2.9 | 0 | 0 | 0
2662 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09184 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Dharam Zone-I Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E. Dte. | 2084/RD/PHE | 02/11/2021 | 30 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 10.59 | 0 | 0 | 1
2663 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09184 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Dharampur Zone-I Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Goalpukhur-I Block under Raiganj Division, P.H.E Dte. | 435/RD/PHE | 16/02/2022 | 30 | IDEAL CO-OP LABOUR CONTRACT & CONST SOCIETY LTD. | 9.16 | 0 | 0 | 0
2664 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09184 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) under Dhulahar Piped Water Supply Scheme and adjoining Mouzas Water Supply Scheme In Itahar Block under Raiganj Division, P.H.E. Dte. | 2080/RD/PHE | 02/11/2021 | 30 | RAHUL ENTERPRISE | 6.95 | 0 | 0 | 100
2665 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09184 | Retrofitting | Material Requisition To Resource Division | 39/RD/PHE | 06/01/2022 | 0 | Resource Division | 0.76 | 0 | 0 | 0
2666 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09184 | Retrofitting | Allied works in connection with retrofitting of FHTC in Dharampur Zone-I PWSS & adjoining mouzas Water Supply Scheme in the district of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 2606/RD/PHE | 13/09/2023 | 60 | ASHIM CHANDA | 0.98 | 0 | 0 | 100
2667 | UTTAR DINAJPUR | Raiganj Division | Retrofitting of Functional House Hold Tap Connections (FHTC) under Dharam Zone-I and adjoining mouzas Water Supply Scheme In Goalpokhor-I Block Under Raiganj Division, P. H. E. Dte. , SM/09184 | Retrofitting | HIRE CHARGES OF VEHICLE OF EXECUTIVE ENGINEER,RAIGANJ DIVISION,P.HE.DTE. | BP-2024-25-18 | 15/04/2024 | 0 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.77 | 0 | 0 | 0
2668 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Bhagabati for installation of FHTC. , SM/09139 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Bhagabati Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. | 2153/RD/PHE | 12/11/2021 | 30 | M/S P.S. ENTERPRISE | 2.76 | 0 | 0 | 1
2669 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of JOYHAT Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part A) | 2186/RD/PHE | 17/11/2021 | 30 | M/S.BANGARAJ | 7.76 | 0 | 0 | 0
2670 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Laying of Additional Pipe Line for Retrofitting of Joyhat Water Supply Scheme for installation of FHTC under Raiganj Division P.H.E. Dte. (Part-B) | 2139/RD/PHE | 12/11/2021 | 30 | M/S J.S.B ASSOCIATE CONSTRUCTION NAMEDUTTA@GMAIL.COM | 4.85 | 0 | 0 | 0
2671 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 29.04.2024,30.04.2024, 02.05.2024 and 03.05.2024. | 1353/RD/PHE | 25/04/2024 | 4 | M/S DILWAR HOSAIN | 0.07 | 0 | 0 | 100
2672 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 08.04.2024,09.04.2024, and 12.04.2024 | 1203/RD/PHE | 06/04/2024 | 3 | M/S DILWAR HOSAIN | 0.07 | 0 | 0 | 100
2673 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 22.04.2024 to 26.04.2024 | 1274/RD/PHE | 19/04/2024 | 5 | M/S DILWAR HOSAIN | 0.08 | 0 | 0 | 100
2674 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 15.04.2024 to 19.04.2024. | 1238/RD/PHE | 12/04/2024 | 5 | M/S DILWAR HOSAIN | 0.07 | 0 | 0 | 100
2675 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Work Order for hiring charges of vehicle with fuel, hired for site works of Raiganj Division, P.H.E. Dte. for 01.04.2024 to 05.04.2024 . | 1160/RD/PHE | 03/04/2024 | 5 | M/S DILWAR HOSAIN | 0.08 | 0 | 0 | 100
2676 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 16.08.2023 to 23.08.2023. | BP-2023-24-313 | 04/03/2024 | 0 | ARNAB DUTTA | 0.12 | 0 | 0 | 0
2677 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 02.05.2023 to 08.05.2023. | BP-2023-24-302 | 04/03/2024 | 0 | ARNAB DUTTA | 0.09 | 0 | 0 | 0
2678 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 18.09.2023 to 27.09.2023. | BP-2023-24-317 | 04/03/2024 | 0 | ARNAB DUTTA | 0.15 | 0 | 0 | 0
2679 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | HIRE CHARGES OF VEHICLE OF EXECUTIVE ENGINEER,RAIGANJ DIVISION,P.HE.DTE. | BP-2024-25-18 | 15/04/2024 | 0 | TAPAN KUMAR MAJUMDER NAMEDUTTA@GMAIL.COM | 0.77 | 0 | 0 | 0
2680 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 29.09.2023 to 01.10.2023. | BP-2023-24-318 | 04/03/2024 | 0 | ARNAB DUTTA | 0.04 | 0 | 0 | 0
2681 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 25.08.2023 to 29.08.2023. | BP-2023-24-314 | 04/03/2024 | 0 | ARNAB DUTTA | 0.07 | 0 | 0 | 0
2682 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 12.06.2023 to 19.06.2023. | BP-2023-24-306 | 04/03/2024 | 0 | ARNAB DUTTA | 0.1 | 0 | 0 | 0
2683 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 01.09.2023 to 07.09.2023. | BP-2023-24-315 | 04/03/2024 | 0 | ARNAB DUTTA | 0.1 | 0 | 0 | 0
2684 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 10.09.2023 to 14.09.2023 | BP-2023-24-316 | 04/03/2024 | 0 | ARNAB DUTTA | 0.07 | 0 | 0 | 0
2685 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 10.05.2023 to 18.05.2023. | BP-2023-24-303 | 04/03/2024 | 0 | ARNAB DUTTA | 0.15 | 0 | 0 | 0
2686 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 21.06.2023 to 28.06.2023. | BP-2023-24-307 | 04/03/2024 | 0 | ARNAB DUTTA | 0.12 | 0 | 0 | 0
2687 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 22.05.2023 to 30.05.2023. | BP-2023-24-304 | 04/03/2024 | 0 | ARNAB DUTTA | 0.15 | 0 | 0 | 0
2688 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 01.06.2033 to 09.06.2023. | BP-2023-24-305 | 04/03/2024 | 0 | ARNAB DUTTA | 0.15 | 0 | 0 | 0
2689 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 10.07.2023 to 16.07.2023. | BP-2023-24-309 | 04/03/2024 | 0 | ARNAB DUTTA | 0.1 | 0 | 0 | 0
2690 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 03.07.2023 to 07.07.2023. | BP-2023-24-308 | 04/03/2024 | 0 | ARNAB DUTTA | 0.09 | 0 | 0 | 0
2691 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 01.08.2023 to 07.08.2023. | BP-2023-24-311 | 04/03/2024 | 0 | ARNAB DUTTA | 0.11 | 0 | 0 | 0
2692 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 09.08.2023 to 14.08.2023. | BP-2023-24-312 | 04/03/2024 | 0 | ARNAB DUTTA | 0.1 | 0 | 0 | 0
2693 | UTTAR DINAJPUR | Raiganj Division | Laying of additional pipe line for retrofitting of Joyhat WSS for installation of FHTC. , SM/09114 | Retrofitting | Continuation Order for Hiring of well-maintaine Diesel Maxi Cab(Non-A.C.) for the office of the Assistant Engineer, Raiganj Sub-Division, P.H.E. Dte. for the purpose of office duty having jurisdiction over the entire under Raiganj Division, P.H.E. Dte. in Uttar Dinajpur District. for 19.07.2023 to 26.07.2023. | BP-2023-24-310 | 04/03/2024 | 0 | ARNAB DUTTA | 0.13 | 0 | 0 | 0
2694 | UTTAR DINAJPUR | Raiganj Division | Survey and Water Sample Collection from School and Anganwadis at various block in the district, Uttar Dinajpur under Raiganj Division, P.H.E. Dte. , SM/11619 | Support-WQMSP | Survey, Water Sample Collection from Schools and Anganwadis at various Block in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. | 1518/RD/PHE | 22/08/2022 | 20 | M/S DUTTA ENTERPRISE | 8.39 | 0 | 0 | 0
2695 | UTTAR DINAJPUR | Raiganj Division | Requirement of miscellaneous activities for upgradation in connection with NABL Uttar Dinajpur District Laboratory. , SM/10615 | Support-WQMSP | PAYMENT FOR QUALITY COUNCIL OF INDIA ACCREDITATION FEE FOR UTTAR DINAJPUR DISTRICT LABORATORY | 1376/RD/1 | 15/07/2022 | 30 | DULAL MAJUMDER | 0.28 | 0 | 0 | 0
2696 | UTTAR DINAJPUR | Raiganj Division | Requirement of miscellaneous activities for upgradation in connection with NABL Uttar Dinajpur District Laboratory. , SM/10615 | Support-WQMSP | PAYMENT FOR QUALITY COUNCIL OF INDIA FOR ACCREDITATION FEE FOR UTTAR DINAJPUR DISTRICT LABORATORY UNDER RAIGANJ DIVISION,P.H.E.DTE. | 1376/RD | 15/07/2022 | 365 | DULAL MAJUMDER | 0.28 | 0 | 0 | 0
2697 | UTTAR DINAJPUR | Raiganj Division | Requirement of miscellaneous activities for upgradation in connection with NABL Uttar Dinajpur District Laboratory. , SM/10615 | Support-WQMSP | Document review charge(NABL) & dist lab raiganj(green economy | BP-2022-23-83 | 22/06/2022 | 0 | DULAL MAJUMDER | 0.09 | 0 | 0 | 0
2698 | UTTAR DINAJPUR | Raiganj Division | Requirement of chemicals & consumables, glasswares for 12 Months and annual maintenance of computer, printer, UPS and other related peripherals of all Laboratories for smooth running of different Labs , SM/06641 | Support-WQMSP | Supply of Consumable, Chemicals & Glass Ware in Itahar Sub-District Laboratory in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. as per Direction of EIC. | 1786/RD/PHE | 10/09/2021 | 15 | DULAL MAJUMDER | 4.97 | 0 | 0 | 0
2699 | UTTAR DINAJPUR | Raiganj Division | Requirement of chemicals & consumables, glasswares for 12 Months and annual maintenance of computer, printer, UPS and other related peripherals of all Laboratories for smooth running of different Labs , SM/06641 | Support-WQMSP | Supply of Consumable, Chemicals & Glass Ware in Raiganj District Laboratory in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. as per Direction of EIC. | 1782/RD/PHE | 10/09/2021 | 15 | DULAL MAJUMDER | 5 | 0 | 0 | 0
2700 | UTTAR DINAJPUR | Raiganj Division | Requirement of chemicals & consumables, glasswares for 12 Months and annual maintenance of computer, printer, UPS and other related peripherals of all Laboratories for smooth running of different Labs , SM/06641 | Support-WQMSP | LABORATORY BILL | 1162/RD | 01/06/2021 | 180 | DULAL MAJUMDER | 4.16 | 0 | 0 | 0
2701 | UTTAR DINAJPUR | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Uttar Dinajpur District. , SM/08980 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Uttar Dinajpur District. | 4690/RS | 17/08/2022 | 365 | HARISHCHANDRAPUR PALLY UNNAYAN SAMITY | 190.69 | 0 | 0 | 100
2702 | UTTAR DINAJPUR | Raiganj Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission. , SM/19073 | Support-WQMSP | Uploading of all Collected & tested data through Field Test Kit and special features along with reorientation in PHED W.Q. Dashboard under Raiganj Division, PHE Dte. | 733/RD/PHE | 05/03/2025 | 360 | DULAL MAJUMDER | 4 | 0 | 0 | 55
2703 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/19074 | Support-WQMSP | Continuation Order for Annual Maintenance Contract (AMC) for one number Computer, Printers, UPS and other related peripherals installed in each 5(Five) Nos. laboratories namely : (i) Uttar Dinajpur District Water Testing Laboratory, (ii) Islampur Sub-Divisional Water Testing Laboratory, (iii) Goalpokhar Sub-Divisional Water Testing Laboratory, (iv) Hemtabad Sub-Divisional Water Testing Laboratory and (v) Itahar Sub-Divisional Water Testing Laboratory under Raiganj Division, PHE Dte. under Raiganj Division, PHE Dte. [For 08 (eight) Months] (01.01.2025 to 31.08.2025) | 3789/RD/PHE | 19/12/2024 | 243 | M/S DUTTA ENTERPRISE | 0.5 | 0 | 0 | 0
2704 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/19074 | Support-WQMSP | Continuation order of Chemicals, Glasswares & Instruments Related to NABL Recognition of Itahar Sub-District Laboratory as per ISO/IEC 17025:2017 under Raiganj Division, P.H.E Dte. | 1935/RD/PHE | 01/07/2025 | 30 | DULAL MAJUMDER | 1.12 | 0 | 0 | 0
2705 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/19074 | Support-WQMSP | Requirements of free Residual Chlorine Field Test Kit for smooth running of Water Testing Laboratories of Uttar Dinajpur District under Raiganj Division, PHE Dte, Government of West Bengal. | 696/RD/PHE | 27/02/2025 | 15 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.98 | 0 | 0 | 0
2706 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/19074 | Support-WQMSP | Continuation Order of Chemicals, Glasswares & Instruments Related to NABL Recognition of Goalpukhur Sub-District Laboratory as per ISO/IEC 17025:2017 under Raiganj Division, P.H.E Dte, | 1934/RD/PHE | 01/07/2025 | 30 | DULAL MAJUMDER | 1.09 | 0 | 0 | 0
2707 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/19074 | Support-WQMSP | Continuation Order for Assigning Resource person/s for one month for supervision of retaining NABL recognition of Block level Sub-district Government drinking water quality testing Laboratory under Raiganj Division including Calibration of measuring instruments, PT testing support and supply of all necessary reagent chemicals to perform day-to-day water quality testing of all laboratories under Raiganj Division, P.H.E. Dte. Government of West Bengal. | 1936/RD/PHE | 01/07/2025 | 60 | DULAL MAJUMDER | 0.29 | 0 | 0 | 0
2708 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/19074 | Support-WQMSP | Continuation Order for Engagement of Resource person to implement water testing laboratory quality management system as per ISO/IEC: 17025 including supply of required equipment's, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instruments & calibration of measuring instruments as per ISO 17025: 2017 protocol for Raiganj District Water Testing Laboratory under the Executive Engineer, Raiganj Division, PHE Dte, Government of West Bengal. | 1930/RD/PHE | 01/07/2025 | 20 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.05 | 0 | 0 | 0
2709 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/19074 | Support-WQMSP | Supply & delivery Chemicals & Consumables etc. for District Laboratory and Sub-District Laboratories in the District of Uttar Dinajpur under Raiganj Division P.H.E. Dte. | 73/RD/PHE | 06/01/2025 | 30 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 30.48 | 0 | 0 | 100
2710 | UTTAR DINAJPUR | Raiganj Division | On-Site assessment with sample collection & testing of Community Water Purification Plants (CWPPs) & Solar Water Plants including supply & delivery of 2 On-site Mobile Analysis System with required consumables in addition to monitoring & processing data o , SM/19280 | Support-WQMSP | On-site assessment, sample collection, and testing of CWPPs and SWPs, including the supply and delivery of two On-site Mobile Analysis Systems with 1,188 consumables for general parameters and 1,782 consumables for fluoride analysis, along with monitoring and processing data from CWPPs and SWPs for precise analysis and evaluation of the plants, with data uploaded to the State Water Quality Dashboard segment hosted on the PHE Web Portal for a duration of 12 months under Raiganj Division ,PHE Dte. | 329/RD/PHE | 17/01/2025 | 365 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 25.48 | 0 | 0 | 0
2711 | UTTAR DINAJPUR | Raiganj Division | Infrastructure upgradation of Uttar Dinajpur District Laboratory at Raiganj PHE Office Complex under Raiganj Division, P.H.E. Dte. , SM/10636 | Support-WQMSP | T.A BILL FOR WATER SAMPLE COLLECTION | BP-2022-23-59 | 26/05/2022 | 0 | MOJAMMIL HOQUE | 0.02 | 0 | 0 | 0
2712 | UTTAR DINAJPUR | Raiganj Division | Infrastructure upgradation of Uttar Dinajpur District Laboratory at Raiganj PHE Office Complex under Raiganj Division, P.H.E. Dte. , SM/10636 | Support-WQMSP | T.A BILL FOR WATER SAMPLE COLLECTION | BP-2022-23-53 | 25/05/2022 | 0 | KALU BARMAN | 0.07 | 0 | 0 | 0
2713 | UTTAR DINAJPUR | Raiganj Division | Infrastructure upgradation of Uttar Dinajpur District Laboratory at Raiganj PHE Office Complex under Raiganj Division, P.H.E. Dte. , SM/10636 | Support-WQMSP | T.A BILL FOR WATER SAMPLE COLLECTION | BP-2022-23-58 | 25/05/2022 | 0 | TANMOY BISWAS | 0.12 | 0 | 0 | 0
2714 | UTTAR DINAJPUR | Raiganj Division | Infrastructure upgradation of Uttar Dinajpur District Laboratory at Raiganj PHE Office Complex under Raiganj Division, P.H.E. Dte. , SM/10636 | Support-WQMSP | T.A BILL FOR WATER SAMPLE COLLECTION | BP-2022-23-55 | 25/05/2022 | 0 | SUMIT KUMAR SARKAR | 0.12 | 0 | 0 | 0
2715 | UTTAR DINAJPUR | Raiganj Division | Infrastructure upgradation of Uttar Dinajpur District Laboratory at Raiganj PHE Office Complex under Raiganj Division, P.H.E. Dte. , SM/10636 | Support-WQMSP | T.A BILL FOR WATER SAMPLE COLLECTION | BP-2022-23-56 | 25/05/2022 | 0 | FARHAD ALI | 0.12 | 0 | 0 | 0
2716 | UTTAR DINAJPUR | Raiganj Division | Infrastructure upgradation of Uttar Dinajpur District Laboratory at Raiganj PHE Office Complex under Raiganj Division, P.H.E. Dte. , SM/10636 | Support-WQMSP | T.A BILL FOR WATER SAMPLE COLLECTION | BP-2022-23-57 | 25/05/2022 | 0 | SURAJIT NANDI | 0.12 | 0 | 0 | 0
2717 | UTTAR DINAJPUR | Raiganj Division | Infrastructure upgradation of Uttar Dinajpur District Laboratory at Raiganj PHE Office Complex under Raiganj Division, P.H.E. Dte. , SM/10636 | Support-WQMSP | T.A BILL FOR WATER SAMPLE COLLECTION | BP-2022-23-54 | 25/05/2022 | 0 | KALU BARMAN | 0.19 | 0 | 0 | 0
2718 | UTTAR DINAJPUR | Raiganj Division | Infrastructure upgradation of Uttar Dinajpur District Laboratory at Raiganj PHE Office Complex under Raiganj Division, P.H.E. Dte. , SM/10636 | Support-WQMSP | supply of 0.5 HP motor pump at sub dist lab hemtabad | BP-2022-23-202 | 01/10/2022 | 0 | M/S SARKAR ENTERPRISE UDAYPUR | 0.11 | 0 | 0 | 0
2719 | UTTAR DINAJPUR | Raiganj Division | Infrastructure upgradation of Uttar Dinajpur District Laboratory at Raiganj PHE Office Complex under Raiganj Division, P.H.E. Dte. , SM/10636 | Support-WQMSP | Repair and Rejuvenation works of Uttar Dinajpur District Laboratory in connection with NABL at Raiganj PHE Complex under Raiganj Division, P.H.E. Dte. | 318/RD/PHE | 31/01/2022 | 365 | DULAL MAJUMDER | 3.5 | 0 | 0 | 0
2720 | UTTAR DINAJPUR | Raiganj Division | Infrastructure upgradation of Uttar Dinajpur District Laboratory at Raiganj PHE Office Complex under Raiganj Division, P.H.E. Dte. , SM/10636 | Support-WQMSP | Repair and rejuvenation works of Uttar Dinajpur District Laboratory in connection with NABL at Raiganj PHE Complex under Raiganj Division, P.H.E. Dte. | 1290/RD/PHE | 28/06/2022 | 45 | DULAL MAJUMDER | 12.02 | 0 | 0 | 0
2721 | UTTAR DINAJPUR | Raiganj Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. , SM/08982 | Support-WQMSP | PLACEMENT OF FUND REGARDING ENGAGEMENT OF ASHA FOR WATER QUALITY TESTING USING FIELD TESTING KiT(FTK) | BP-2022-23-71 | 09/06/2022 | 0 | CMOH | 8 | 0 | 0 | 0
2722 | UTTAR DINAJPUR | Raiganj Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. , SM/08982 | Support-WQMSP | Water testing of Schools & AWC w.r.t SJSS Campaign for Hemtabad Sub-District Laboratory. |  | 18/12/2023 | 0 | MD. MIZANUR RAHAMAN | 1.38 | 0 | 0 | 0
2723 | UTTAR DINAJPUR | Raiganj Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. , SM/08982 | Support-WQMSP | water testing of School & AWC w.r.t SJSS Campaign for Islampur sub Dist. Laboratory. | BP-2023-24-243 | 08/01/2024 | 0 | DEBASMITA BHATTACHARJEE | 0.94 | 0 | 0 | 0
2724 | UTTAR DINAJPUR | Raiganj Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. , SM/08982 | Support-WQMSP | Water testing of Schoools and AWC w.r.t SJSS Campaign for Uttar Dinajpur Dist. Laboratory. | BP-2023-24-238 | 08/01/2024 | 0 | FARHAD ALI | 2.02 | 0 | 0 | 0
2725 | UTTAR DINAJPUR | Raiganj Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. , SM/08982 | Support-WQMSP | water testing of Schools & AWC w.r.t SJSS for Goalpokher Sub-District Laboratory . | BP-2023-24-241 | 08/01/2024 | 0 | MOJAMMIL HOQUE | 0.89 | 0 | 0 | 0
2726 | UTTAR DINAJPUR | Raiganj Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. , SM/08982 | Support-WQMSP | Water testing of Schools & AWC w.r.t SJSS Campaign for Hemtabad Sub-District Laboratory. | BP-2023-24-242 | 08/01/2024 | 0 | MD. MIZANUR RAHAMAN | 1.19 | 0 | 0 | 0
2727 | UTTAR DINAJPUR | Raiganj Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under JJM. , SM/08982 | Support-WQMSP | Water testing of Schools & AWC w.r.t SJSS Campaign for Itahar Sub-Dist. Laboratory. | BP-2023-24-240 | 08/01/2024 | 0 | SACHIN ROY | 0.6 | 0 | 0 | 0
2728 | UTTAR DINAJPUR | Raiganj Division | Supply,Delivery and Installtion of computer & peripherals for official use under Raiganj Division, P.H.E. Dte. , SM/10390 | Support-MIS | SUPPLY OF COMPUTER PERIPHERALS UNDER RAIGANJ DIVISION, P.H.E.DTE. | GEMC-511687724974541 | 28/05/2022 | 30 | IONET | 11.54 | 0 | 0 | 0
2729 | UTTAR DINAJPUR | Raiganj Division | Supply,Delivery and Installtion of computer & peripherals for official use under Raiganj Division, P.H.E. Dte. , SM/10390 | Support-MIS | SUPPLY OF COMPUTER PERIPHERALS | BP-2022-23-47 | 12/05/2022 | 0 | IONET | 2.75 | 0 | 0 | 0
2730 | UTTAR DINAJPUR | Raiganj Division | Supply,Delivery and Installtion of computer & peripherals for official use under Raiganj Division, P.H.E. Dte. , SM/10390 | Support-MIS | SUPPLY OF COMPUTER PERIPHERALS | BP-2022-23-49 | 12/05/2022 | 0 | IONET | 0.72 | 0 | 0 | 0
2731 | UTTAR DINAJPUR | Raiganj Division | Supply,Delivery and Installtion of computer & peripherals for official use under Raiganj Division, P.H.E. Dte. , SM/10390 | Support-MIS | SUPPLY OF COMPUTER PERIPHERALS | BP-2022-23-46 | 12/05/2022 | 0 | IONET | 0.75 | 0 | 0 | 0
2732 | UTTAR DINAJPUR | Raiganj Division | Supply,Delivery and Installtion of computer & peripherals for official use under Raiganj Division, P.H.E. Dte. , SM/10390 | Support-MIS | SUPPLY OF COMPUTER PERIPHERALS | BP-2022-23-50 | 12/05/2022 | 0 | IONET | 2.79 | 0 | 0 | 0
2733 | UTTAR DINAJPUR | Raiganj Division | Supply,Delivery and Installtion of computer & peripherals for official use under Raiganj Division, P.H.E. Dte. , SM/10390 | Support-MIS | SUPPLY OF COMPUTER PERIPHERALS | BP-2022-23-48 | 12/05/2022 | 0 | IONET | 4.3 | 0 | 0 | 0
2734 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/11804 | Support-WQMSP | Supply of Consumable, Chemicals & Glass Ware in WBCADC Kaliyaganj Project SD Laboratory in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. as per Direction of EIC. | 1784/RD/PHE | 10/09/2021 | 15 | DULAL MAJUMDER | 4.96 | 0 | 0 | 0
2735 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/11804 | Support-WQMSP | Supply of Consumable, Chemicals & Glass Ware in Goalpokhar-I Sub- District Laboratory in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. as per Direction of EIC. | 1785/RD/PHE | 10/09/2021 | 15 | DULAL MAJUMDER | 4.84 | 0 | 0 | 0
2736 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/11804 | Support-WQMSP | DEPLYOMENT OF LABORATORY PERSONNEL FOR 02 DISTRICT LABORATORIES FOR WQMSP AND PWSS AND DAY TO DAY WASHING CLEANING OF ALL LABORATORY OF DISTRICT LABORATORIES | 1162/ RD | 01/06/2021 | 180 | DULAL MAJUMDER | 4.16 | 0 | 0 | 0
2737 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/11804 | Support-WQMSP | Supply of Consumable, Chemicals & Glass Ware in Prashika RDO Laboratory in the District of Uttar Dinajpur under Raiganj Division, P.H.E. Dte. as per Direction of EIC. | 1783/RD/PHE | 10/09/2021 | 15 | DULAL MAJUMDER | 4.72 | 0 | 0 | 0
2738 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/11804 | Support-WQMSP | LABORATORY BILL | 1162/RD | 01/06/2021 | 180 | DULAL MAJUMDER | 4.16 | 0 | 0 | 0
2739 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/11804 | Support-WQMSP | Requirement of Consumables Chemicals for District Laboratory under Raiganj Division, P.H.E. Dte. (Part-A) | 709/RD/PHE | 13/03/2023 | 7 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 0.96 | 0 | 0 | 100
2740 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/11804 | Support-WQMSP | Requirement of Consumables Chemicals for District Laboratory under Raiganj Division, P.H.E. Dte. (Part-B) | 710/RD/PHE | 13/03/2023 | 7 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 0.95 | 0 | 0 | 100
2741 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/11804 | Support-WQMSP | Supply of all necessary regent chemicals to perform day to day water quality testing for District Laboratory Karnajora under Raiganj Division, P.H.E. Dte. | 2704/RD/PHE | 09/09/2024 | 15 | DULAL MAJUMDER | 0.98 | 0 | 0 | 100
2742 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/11804 | Support-WQMSP | Supply of all necessary regent chemicals to perform day to day water quality testing for Islampur Sub-District Laboratory under Raiganj Division, P.H.E. Dte. | 2707/RD/PHE | 09/09/2024 | 15 | DULAL MAJUMDER | 0.95 | 0 | 0 | 100
2743 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/11804 | Support-WQMSP | Supply of all necessary regent chemicals to perform day to day water quality testing for Itahar Sub-District Laboratory under Raiganj Division, P.H.E. Dte. | 2708/RD/PHE | 09/09/2024 | 15 | DULAL MAJUMDER | 0.92 | 0 | 0 | 100
2744 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/11804 | Support-WQMSP | Supply of all necessary regent chemicals to perform day to day water quality testing for Goalpokhar Sub-District Laboratory under Raiganj Division, P.H.E. Dte. | 2709/RD/PHE | 09/09/2024 | 15 | DULAL MAJUMDER | 0.87 | 0 | 0 | 100
2745 | UTTAR DINAJPUR | Raiganj Division | Requirements of Chemicals, Glasswares & OMAS Consumables and Annual Maintenance of Computer, Printers of all laboratories for smooth running of different 5 Nos. Labs under Raiganj Division P.H.E. Dte. , SM/11804 | Support-WQMSP | Supply of all necessary regent chemicals to perform day to day water quality testing for Hemtabad Sub-District Laboratory under Raiganj Division, P.H.E. Dte. | 2710/RD/PHE | 09/09/2024 | 15 | DULAL MAJUMDER | 0.7 | 0 | 0 | 100
2746 | UTTAR DINAJPUR | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div , SM/11803 | Support-WQMSP | Deployment of Laboratory Personnel for 01(One) No. Sub-District Laboratories for water quality Monitoring & Surveillance of Spot Source and Piped Water Supply Scheme by testing of all parameter as per Direction and all Data upload into PHED Dash Board [PART-A] and Day to day washing cleaning of all laboratory instruments, Laboratory room and other inside area of Laboratory etc. for 01 (One) No. Sub-District Laboratories at Itahar [Part-B] under Raiganj Division, P.H.E. Dte. (Period for 12(Twelve) Months (01.02.2022 to 31.01.2023) | 313/RD/PHE | 31/01/2022 | 365 | DULAL MAJUMDER | 3.74 | 0 | 0 | 0
2747 | UTTAR DINAJPUR | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div , SM/11803 | Support-WQMSP | Deployment of Laboratory Personnel for 01(One) Nos. Sub-District Laboratories for water quality Monitoring & Surveillance of Spot Source and Piped Water Supply Scheme by testing of all parameter as per Direction and all Data upload into PHED Dash Board and Day to day washing cleaning of all laboratory instruments, Laboratory room and other inside area of Laboratory etc. for Hemtabad Sub-District Laboratories under Raiganj Division, P.H.E. Dte. (Period from 01.07.2022 to 31.03.2023) | 1343/RD/PHE | 08/07/2022 | 270 | DULAL MAJUMDER | 4.42 | 0 | 0 | 0
2748 | UTTAR DINAJPUR | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div , SM/11803 | Support-WQMSP | Deployment of Laboratory personnel for 02(two) Sub-district Laboratories for water quality monitoring & Surveillance of Spot Source and piped Water Supply Scheme by testing of all parameter as per Direction and all Data upload into PHED Dash Board [Part-A] and Day to Day to washing cleaning of all laboratory instruments, Laboratory room including meeting room and other inside area of Laboratory etc. of 02(two) Sub-District Laboratories at Itahar & Goalpokhar (Part B) under Raiganj Division, PHE Dte 01 Month (01.01.2022 to 31.01.2022) | 2432/RD/PHE | 31/12/2021 | 31 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 0.57 | 0 | 0 | 0
2749 | UTTAR DINAJPUR | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div , SM/11803 | Support-WQMSP | Deployment of Laboratory Personnel for District Laboratory for water quality Monitoring & Surveillance of Spot Source and Piped Water Supply Scheme by testing of all parameter as per Direction and all Data upload into PHED Dash Board [PART-A] and Day to day washing cleaning of all laboratory instruments, Laboratory room including meeting room and other inside area of Laboratory etc. of District Laboratory at Karnajora[Part-B] under Raiganj Division, P.H.E. Dte. [(For the period from 16.01.2022 to 15.01.2023) 12(twelve) Months.] | 82/RD/PHE | 14/01/2022 | 365 | DULAL MAJUMDER | 8.47 | 0 | 0 | 0
2750 | UTTAR DINAJPUR | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div , SM/11803 | Support-WQMSP | Deployment of Laboratory Personnel for 01(One) Nos.Sub-District Laboratories for water quality Monitoring & Surveillance of Spot Source and Piped Water Supply Scheme by testing of all parameter as per Direction and all Data upload into PHED Dash Board and Day to day washing cleaning of all laboratory instruments, Laboratory room and other inside area of Laboratory etc. for Islampur Sub-District Laboratories under Raiganj Division, P.H.E. Dte. (Period from 01.07.2022 to 31.03.2023) | 1344/RD/PHE | 08/07/2022 | 270 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 4.42 | 0 | 0 | 100
2751 | UTTAR DINAJPUR | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div , SM/11803 | Support-WQMSP | Deployment of Laboratory Personnel for 01(One) No. Sub-District Laboratories for water quality Monitoring & Surveillance of Spot Source and Piped Water Supply Scheme by testing of all parameter as per Direction and all Data upload into PHED Dash Board [PART-A] and Day to day washing cleaning of all laboratory instruments, Laboratory room and other inside area of Laboratory etc. for 01 (One) No. Sub-District Laboratories at Goalpokhar [Part-B] under Raiganj Division, P.H.E. Dte. (Period for 12(Twelve) Months (01.02.2022 to 31.01.2023) | 314/RD/PHE | 31/01/2022 | 365 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 3.74 | 0 | 0 | 100
2752 | UTTAR DINAJPUR | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source by testing of all parameter and upload data into PHED Dash Board and Maintenance of all laboratory for smooth running of different 5 Nos. Labs under Raiganj Div , SM/11803 | Support-WQMSP | Continuation Order for Deployment of Laboratory Personnel for 01(One) No. Sub-District Laboratories for water quality Monitoring & Surveillance of Spot Source and Piped Water Supply Scheme by testing of all parameter as per Direction and all Data upload into PHED Dash Board [PART-A] and Day to day washing cleaning of all laboratory instruments, Laboratory room and other inside area of Laboratory etc. for 01 (One) No. Sub-District Laboratories at Goalpokhar [Part-B] under Raiganj Division, P.H.E. Dte. (Period for 59(Fifty Nine) Days (01.02.2023 to 31.03.2023) | 283/RD/PHE | 31/01/2023 | 59 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 0.62 | 0 | 0 | 100
2753 | UTTAR DINAJPUR | Raiganj Division | Requirement of OMAS Kit Consumables for 12 Months for smooth running of different Labs (5 Nos.). , SM/06640 | Support-WQMSP | Procurement of Consumables OMAS as directed by EIC, Raiganj Division under Public Health Engineering Department Govt. of West Bengal. | 2324/RD/PHED | 13/12/2021 | 15 | SUNANDA ENVIRONMENTAL INTERNATIONAL PVT LTD | 4.29 | 0 | 0 | 0
2754 | UTTAR DINAJPUR | Raiganj Division | Requirement of OMAS Kit Consumables for 12 Months for smooth running of different Labs (5 Nos.). , SM/06640 | Support-WQMSP | Procurement of Consumable OMAS as directed by EIC, Raiganj Division under Public Health Engineering Department Govt. of West Bengal. | 1059/RD/PHED | 13/05/2022 | 15 | SUNANDA ENVIRONMENTAL INTERNATIONAL PVT LTD | 4.29 | 0 | 0 | 0
2755 | UTTAR DINAJPUR | Raiganj Division | Requirement of OMAS Kit Consumables for 12 Months for smooth running of different Labs (5 Nos.). , SM/06640 | Support-WQMSP | OFFICE ACCESSORIES BILL | 368/W | 28/09/2022 | 0 | DIGITEK SOLUTIONS | 0.08 | 0 | 0 | 0
2756 | UTTAR DINAJPUR | Raiganj Division | Requirement of OMAS Kit Consumables for 12 Months for smooth running of different Labs (5 Nos.). , SM/06640 | Support-WQMSP | OFFICE ACCESSORIES BILL | 373/W | 28/09/2022 | 0 | DIGITEK SOLUTIONS | 0.07 | 0 | 0 | 0
2757 | UTTAR DINAJPUR | Raiganj Division | Requirement of OMAS Kit Consumables for 12 Months for smooth running of different Labs (5 Nos.). , SM/06640 | Support-WQMSP |  | 844314 | 04/08/2023 | 0 | KALU BARMAN | 0.03 | 0 | 0 | 0
2758 | UTTAR DINAJPUR | Raiganj Division | Requirement of OMAS Kit Consumables for 12 Months for smooth running of different Labs (5 Nos.). , SM/06640 | Support-WQMSP | Supply and delivery of portable multi-parameter water quality testing device [Field Test Kits (FTKs)] integrated with Training on Operation of Kits, Data Collection system through Water Quality Mobile Application and District-wise specific Database Management System (integrated with current PHED, WB, structure) and other functionalities related to Data transfer to both PHED and WQMIS Dashboard, for monitoring water safety status of rural drinking water sources of all Gram Panchayats in Uttar Dinajpur District of West Bengal under Raiganj Division, PHE Dte. | 2334/RD/PHE | 16/12/2021 | 835 | DULAL MAJUMDER | 10.04 | 0 | 0 | 100
2759 | UTTAR DINAJPUR | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen , SM/11226 | Support-WQMSP | Engagement of Resource person to implement water testing laboratory quality management system as per ISO/IEC: 17025 including supply of required equipment's, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instruments & calibration of measuring instruments as per ISO 17025: 2017 protocol for Raiganj District Water Testing Laboratory under the Executive Engineer, Raiganj Division, PHE Dte, Government of West Bengal. | 1687/RD/PHE | 26/08/2021 | 15 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 20.3 | 0 | 0 | 0
2760 | UTTAR DINAJPUR | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen , SM/11226 | Support-WQMSP | Supply of additional items for implementation of NABL accreditation in dist lab | BP-2022-23-241 | 25/11/2022 | 0 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.1 | 0 | 0 | 0
2761 | UTTAR DINAJPUR | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen , SM/11226 | Support-WQMSP | Supply of additional items for implementation of NABL accreditation in district lab | BP-2022-23-238 | 25/11/2022 | 0 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.09 | 0 | 0 | 0
2762 | UTTAR DINAJPUR | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen , SM/11226 | Support-WQMSP | Supply of additional items for implementation of NABL accreditation in district lab | BP-2022-23-242 | 25/11/2022 | 0 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.1 | 0 | 0 | 0
2763 | UTTAR DINAJPUR | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen , SM/11226 | Support-WQMSP | Supply of additional items for implementation of NABL accreditation in district lab | BP-2022-23-243 | 25/11/2022 | 0 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.1 | 0 | 0 | 0
2764 | UTTAR DINAJPUR | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen , SM/11226 | Support-WQMSP | Supply of additional items for implementation of NABL accreditation in district lab | BP-2022-23-240 | 25/11/2022 | 0 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.1 | 0 | 0 | 0
2765 | UTTAR DINAJPUR | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen , SM/11226 | Support-WQMSP | Supply of additional items for implementation of NABL accreditation in district lab | BP-2022-23-239 | 25/11/2022 | 0 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.1 | 0 | 0 | 0
2766 | UTTAR DINAJPUR | Raiganj Division | Engagement of resource person to implement water testing laboratory quality management system as per ISO IEC 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instrumen , SM/11226 | Support-WQMSP | Engagement of Resource person to implement water testing laboratory quality management system as per ISO/IEC: 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instruments & calibration of measuring instruments as per ISO 17025: 2017 protocol for Raiganj District Water Testing Laboratory under the Executive Engineer, Raiganj Division, PHE Dte, Government of West Bengal. | 1560/RD/PHE | 04/08/2021 | 15 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 20.3 | 0 | 0 | 0
2767 | UTTAR DINAJPUR | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/Pipe Water Supply by testing of all parameters and upload data into PHED Dash Board and Maintenance of all laboratories for smooth running in different 5 Nos. La , SM/19075 | Support-WQMSP | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/PWSS by testing of all parameter and upload data into PHED Dash Board and maintenance of Laboratory of District Laboratory at Karnajora under Raiganj Division, P.H.E. Dte. For 12(twelve) Months. | 1009/RD/PHE | 31/03/2023 | 366 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 13.9 | 0 | 0 | 100
2768 | UTTAR DINAJPUR | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/Pipe Water Supply by testing of all parameters and upload data into PHED Dash Board and Maintenance of all laboratories for smooth running in different 5 Nos. La , SM/19075 | Support-WQMSP | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/PWSS by testing of all parameter and upload data into PHED Dash Board and maintenance for 01(One) Nos. Sub-District Laboratories at Goalpukhur under Raiganj Division, P.H.E. Dte. for 12(twelve) Months. | 1010/RD/PHE | 31/03/2023 | 366 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 8.36 | 0 | 0 | 100
2769 | UTTAR DINAJPUR | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/Pipe Water Supply by testing of all parameters and upload data into PHED Dash Board and Maintenance of all laboratories for smooth running in different 5 Nos. La , SM/19075 | Support-WQMSP | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/PWSS by testing of all parameter and upload data into PHED Dash Board and maintenance for 01(One) Nos. Sub-District Laboratories at Itahar under Raiganj Division, P.H.E. Dte. for 12(twelve) Months. | 1011/RD/PHE | 31/03/2023 | 366 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 8.36 | 0 | 0 | 100
2770 | UTTAR DINAJPUR | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/Pipe Water Supply by testing of all parameters and upload data into PHED Dash Board and Maintenance of all laboratories for smooth running in different 5 Nos. La , SM/19075 | Support-WQMSP | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/PWSS by testing of all parameter and upload Data into PHED Dash Board and maintenance of Islampur Sub-District Laboratory, Islampur under Raiganj Division, P.H.E. Dte. for 12(twelve) Months. | 1012/RD/PHE | 31/03/2023 | 366 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 8.63 | 0 | 0 | 100
2771 | UTTAR DINAJPUR | Raiganj Division | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/Pipe Water Supply by testing of all parameters and upload data into PHED Dash Board and Maintenance of all laboratories for smooth running in different 5 Nos. La , SM/19075 | Support-WQMSP | Deployment of Laboratory Personnel for water quality Monitoring & Surveillance of Spot Source/PWSS by testing of all parameter and upload Data into PHED Dash Board and maintenance of Hemtabad Sub-District Laboratory, Hemtabad under Raiganj Division, P.H.E. Dte. for 12(twelve) Months. | 1013/RD/PHE | 31/03/2023 | 366 | DULAL MAJUMDER DULALMAJUMDER382@GMAIL.COM | 8.63 | 0 | 0 | 100
2772 | UTTAR DINAJPUR | Raiganj Division | SUPPLY, DELIVERY AND INSTALLATION OF COMPUTER & PERIPHERALS FOR OFFICIAL USE UNRED RAIGANJ DIVISION, P.H.E. DTE. , SM/19115 | Support-MIS | supply of delivery of computer for Raiganj Division, PHE Dte | BP-2023-24-270 | 08/02/2024 | 0 | BIOS COMPUTER | 4.95 | 0 | 0 | 0
2773 | UTTAR DINAJPUR | Raiganj Division | SUPPLY, DELIVERY AND INSTALLATION OF COMPUTER & PERIPHERALS FOR OFFICIAL USE UNRED RAIGANJ DIVISION, P.H.E. DTE. , SM/19115 | Support-MIS | Supply of 02(TWO) Nos. Desktop computers acer Intel Core i513500 8GB/1000GB HDD/Windows 11 Professional for Raiganj Sub-Division office under Raiganj Division, P.H.E.Dte. | BP-2024-25-164 | 09/08/2024 | 0 | BIOS COMPUTER | 0.99 | 0 | 0 | 0
Total | [9 empty] | 586376.76 | 367.2 | 0.06