## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Ashrafpur, JL. No. 132, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 297/MD | 28/01/2021 | 30 | M/S BANERJEE CONSTRUCTION | 13.91 | 0 | 0 | 0
2 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Chhatia, JL. No. 133, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 298/MD | 28/01/2021 | 30 | M/S BANERJEE CONSTRUCTION | 17.51 | 0 | 0 | 0
3 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bhabanipur, JL. No. 85, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 306/MD | 28/01/2021 | 30 | RANJIT ADHIKARY | 8.8 | 0 | 0 | 0
4 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bhairabpur, JL. No. 86, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 308/MD | 28/01/2021 | 30 | CHARU CONSTRUCTION | 5.85 | 0 | 0 | 0
5 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Kanua Bhabanipur, JL. No. 78, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | 289/MD | 28/01/2021 | 30 | JOYDEB SENGUPTA | 6.64 | 0 | 0 | 0
6 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Teliapara, JL. No. 74, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 296/MD | 28/01/2021 | 30 | GOALPAR CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 5.53 | 0 | 0 | 0
7 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Kumedpur, JL. No. 142, G.P.-Sadlichak of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 3004/MD | 07/10/2021 | 30 | FUTURE | 49.95 | 0 | 0 | 1
8 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Muchia, JL. No. 124, G.P.-Muchia of MOBARAKPUR Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | 509/MD | 09/02/2021 | 30 | M/S KUNDU CONSTRUCTION | 46.63 | 46.62 | 100 | 1
9 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Alampur, JL. No. 107, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 291/MD | 28/01/2021 | 30 | RANJIT ADHIKARY | 5.68 | 0 | 0 | 1
10 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Barinda, JL. No. 95, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 292/MD | 28/01/2021 | 30 | GOALPAR CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 5.85 | 4.99 | 100 | 1
11 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Harinandanbati, JL. No. 109, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 293/MD | 28/01/2021 | 30 | S. R. CONSTRUCTION | 15.52 | 0 | 0 | 1
12 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Manoharpur, JL. No. 117, G.P.-Sultannagar of GANNADIA Water Supply Scheme at Harischandrapur - II Block under Malda Division, PHE Dte. | 447/MD | 08/02/2021 | 30 | MANIK CHOUDHURY | 37.13 | 0 | 0 | 0
13 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bahirgachhi, JL. No. 24, G.P.-Bahirgachhi-I of BAHIRGACHHI Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | 556/MD | 12/02/2021 | 45 | UTTAM KUMAR GHOSH | 71.29 | 0 | 0 | 0
14 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Arazi Deharul, JL. No. 21, G.P.-Bahirgachhi-II of BAHIRGACHHI Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | 555/MD | 12/02/2021 | 30 | BEE GEE CONSTRUCTION | 52.81 | 0 | 0 | 1
15 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bampal Charkhi, JL. No. 51, G.P.- Chandmoni-I of KANKOT Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | 267/MD | 28/01/2021 | 30 | MANIK CHOUDHURY | 35.11 | 8.47 | 100 | 0
16 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Memua, JL. No. 122, G.P.- Muchia of NEMUA Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | 269/MD | 28/01/2021 | 30 | GOBINDA ENTERPRISE | 23.19 | 22.91 | 100 | 1
17 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Gaushpur, JL. No. 90, G.P.- Daulatpur of MALIPAKAR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 271/MD | 28/01/2021 | 30 | GOBINDA ENTERPRISE | 14.36 | 12.51 | 100 | 1
18 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Gangnadia, JL. No. 114, G.P.-Mahendrapur of GANNADIA Water Supply Scheme at Harischandrapur - II Block under Malda Division, PHE Dte. | 265/MD | 28/01/2021 | 30 | MANIK CHOUDHURY | 38.45 | 19.73 | 76.83 | 1
19 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Naikanda, JL. No. 39, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 282/MD | 28/01/2021 | 30 | FAIZUL HAQUE BISWAS | 16.18 | 0 | 0 | 1
20 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Jagdala, JL. No. 77, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 300/MD | 28/01/2021 | 30 | PABITRA MONDAL | 9.57 | 8.78 | 100 | 1
21 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bhabuk, JL. No. 89, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 307/MD | 28/01/2021 | 30 | S. R. CONSTRUCTION | 14.93 | 14.43 | 100 | 1
22 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Dharmma Danga, JL. No. 44, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 311/MD | 28/01/2021 | 30 | MANAS KUMAR SAHA | 18.67 | 0 | 0 | 1
23 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Khatil, JL. No. 42, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 452/MD | 08/02/2021 | 30 | GOBINDA ENTERPRISE | 22.15 | 16.1 | 45.68 | 1
24 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Elam, JL. No. 75, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | 287/MD | 28/01/2021 | 30 | ACHARYYA CONSTRUCTION | 12.36 | 0 | 0 | 1
25 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Harischandrapur, JL. No. 83, G.P.- Baidyapur of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 305/MD | 28/01/2021 | 30 | KRISHNENDU DUTTA | 25.76 | 0 | 0 | 1
26 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Adampur, JL. No. 121, G.P.- Muchia of NEMUA Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | 268/MD | 28/01/2021 | 30 | BEE GEE CONSTRUCTION | 29.13 | 26.57 | 100 | 1
27 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Gorakhpur, JL. No. 76, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | 449/MD | 08/02/2021 | 30 | TARUN KUMAR DEY | 27.04 | 0 | 0 | 1
28 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Basudebpur, JL. No. 150, G.P.- Sadlichak of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 273/MD | 28/01/2021 | 30 | MD WARESH ALI | 14.72 | 0 | 0 | 1
29 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Emergent repairing and laying of uPVC pipeline and Construction of SSP with other allied work to proper functioning of FHTC work within the command area of NEMUA Water Supply scheme under Malda Division, PHE Dte. in the district of Malda. | 2961/MD | 07/12/2022 | 30 | SUDEB KARMAKAR | 2.09 | 0 | 0 | 0
30 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Daksin Sahar, JL. No. 133, G.P.-Chanchal of DAKSHIN SAHAR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 2456/MD | 12/10/2020 | 30 | M/S BANERJEE CONSTRUCTION | 19.18 | 6.37 | 90.6 | 0
31 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Sanjib, JL. No. 136, G.P.-Chanchal of DAKSHIN SAHAR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 2457/MD | 12/10/2020 | 30 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.51 | 7.28 | 93.27 | 0
32 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Sahabajpur, JL. No. 55, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 281/MD | 28/01/2021 | 30 | M/S. TEWARI CONSTRUCTION | 20.81 | 14.29 | 84.86 | 1
33 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Rasulpur, JL. No. 71, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | 284/MD | 28/01/2021 | 30 | A. K. SIKDAR | 8.24 | 0 | 0 | 1
34 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Agra, JL. No. 84, G.P.- Jajail of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 451/MD | 08/02/2021 | 30 | M/S. TEWARI CONSTRUCTION | 25.53 | 0 | 0 | 1
35 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bansdol, JL. No. 94, G.P.- Daulatpur of DAULATPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 266/MD | 28/01/2021 | 30 | M/S. TEWARI CONSTRUCTION | 21.96 | 0 | 0 | 1
36 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Gopalnagar, JL. No. 80, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 299/MD | 28/01/2021 | 30 | S. N. CONSTRUCTION | 18.77 | 0 | 0 | 1
37 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Parameswarpur, JL. No. 81, G.P.- Jogdala of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 301/MD | 28/01/2021 | 30 | A. K. SIKDAR | 7.04 | 0 | 0 | 1
38 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bhadreshwar, JL. No. 78, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 303/MD | 28/01/2021 | 30 | ACHARYYA CONSTRUCTION | 13.25 | 0 | 0 | 1
39 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Dihatti, JL. No. 79, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 304/MD | 28/01/2021 | 30 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 5.93 | 0 | 0 | 0
40 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Kasba, JL. No. 45, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 312/MD | 28/01/2021 | 30 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 15.48 | 0 | 0 | 1
41 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Kendua, JL. No. 54, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 448/MD | 08/02/2021 | 30 | FAIZUL HAQUE BISWAS | 25.78 | 0 | 0 | 1
42 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Collection of household tap connection details through baseline household mobile's App (Jal Swapna) under commend area of Rajarampur, Mekpur, Purba Binodpur, Mianagar & Basora Piped Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | 515/MSD | 31/12/2021 | 1 | DHRITIPALI | 0.96 | 0 | 0 | 1
43 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Lalpur Bodra, JL. No. 31, G.P.-Aktail of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 3102/MD | 15/12/2020 | 30 | M/S SINHA ENTERPRISE | 0 | 0 | 0 | 1
44 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Laying and extension of uPVC Pipe Line of different diameter at Dihotti & Bhadreswar Mouza of PARAMESHWARPUR Water Supply Scheme at BAMONGOLA Block under Malda Division P.H.E. Dte. in the district of Malda. | 3413/MD | 02/12/2021 | 1 | ACHARYYA CONSTRUCTION | 1.25 | 0 | 0 | 1
45 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of ARBARA Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 2196/MD | 22/09/2022 | 30 | S & G CONSTRUCTION | 7.96 | 0 | 0 | 1
46 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Jot Haricharan, JL. No. 43, G.P.-Bamangola of KHATIL Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 310/MD | 28/01/2021 | 30 | JOY ENTERPRISE | 6.77 | 0 | 0 | 1
47 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Rampur, JL. No. 74, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | 286/MD | 28/01/2021 | 30 | S. N. CONSTRUCTION | 16.86 | 0 | 0 | 1
48 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village-Dubol, JL. No. 93, G.P.- Daulatpur of DAULATPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 2314/MD | 30/09/2020 | 31 | PRITAM ENTERPRISE | 3.31 | 0 | 0 | 0
49 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection under MOBARAKPUR Piped Water Supply Scheme at Old Malda Block in the district of Malda under Malda Division, PHE Dte. | 591/MD | 18/02/2021 | 60 | NIRENDRA NATH KUNDU | 125 | 0 | 0 | 0
50 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Konar, JL. No. 73, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | 450/MD | 08/02/2021 | 30 | M/S. TEWARI CONSTRUCTION | 25.97 | 0 | 0 | 0
51 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Restoration pipe line for Providing FHTC in connection with JJM at Birasthal along NH-81 under command area of Dakshin Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | 2547/MD | 03/11/2022 | 30 | M/S. TEWARI CONSTRUCTION | 1.15 | 0 | 0 | 0
52 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village-Sadhail, JL. No. 116, G.P.- Muchia of NEMUA Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | 2312/MD | 30/09/2020 | 31 | DEVI ENTERPRISE | 2.07 | 0 | 0 | 1
53 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bibijhuti, JL. No. 58, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 283/MD | 28/01/2021 | 30 | ANUKUL CHANDRA DAS | 9.41 | 7.95 | 100 | 1
54 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Bhabanipur, JL. No. 73, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | 285/MD | 28/01/2021 | 30 | M/S BANERJEE CONSTRUCTION | 13.56 | 0 | 0 | 1
55 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Isadpur, JL. No. 77, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | 288/MD | 28/01/2021 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 24.42 | 0 | 0 | 1
56 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Lakshmanpur, JL. No. 74, G.P.- Bhingole of KONAR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | 290/MD | 28/01/2021 | 30 | M/S SABANA CONSTRUCTION | 27.25 | 0 | 0 | 1
57 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Daulatpur, JL. No. 92, G.P.-Daulatpur of DAULATPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 569/MD | 15/02/2021 | 45 | M/S TRILOCHAN CONSTRUCTION CO | 84.94 | 0 | 0 | 1
58 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Kankot, JL. No. 50, G.P.-Chandmoni-I of KANKOT Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | 557/MD | 12/02/2021 | 30 | RAY CONSTRUCTION CO. | 57.6 | 0 | 0 | 1
59 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Continuation of work order for hiring of inspection vehicle (motor cab or Maruti omni category non air condition Bharat stage III purchase on or after 1.05.2008 with deiseal/LPG/CNG Engine ) in perfectly good condition of performing along journey and should cover anywhere without any trouble on monthly heir basis for official use of the office of the Assistant Engineer ,RWS Malda sub division ,PHE Dte.( Period from 06/07/2023 to 31/12/2023 ) | 199/RWS | 06/06/2023 | 178 | SHYAMAL KUMAR MAITRA | 0.85 | 0 | 0 | 55
60 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Laying of additional pipe line and Providing FHTC connection at Uttar Rasulpur village of Rampur water supply scheme, Chanchal-II Dev. Block , Chanchal Sub-Division of PHE Dte. | 2546/MD | 03/11/2022 | 30 | ANUKUL CHANDRA DAS | 6.35 | 0 | 0 | 100
61 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Malipakar, JL. No. 91, G.P.-Daulatpur of MALIPAKAR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 568/MD | 15/02/2021 | 45 | NEOGI ENTERPRISE | 78.3 | 33.11 | 42.29 | 46
62 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Nemua Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 3367/MD | 29/08/2023 | 45 | MOMTAJ ALI | 40.32 | 0 | 0 | 74
63 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 23/12/2023 to 19/06/2024=180 Days). Vehicle no. WB 65A/4911. | 5151/MD | 21/12/2023 | 180 | USHA ENTERPRISE | 0.86 | 0 | 0 | 0
64 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kankot Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 6164/MD | 05/12/2024 | 45 | MD WARESH ALI | 30.59 | 0 | 0 | 0
65 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/08/2023 to 31/01/2024). | 2023/NBC-II | 30/08/2023 | 180 | TARUN KUMAR BHATTACHARYA | 0.86 | 0 | 0 | 76
66 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Rampur Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | 5484/MD | 24/10/2024 | 45 | M/S JHA CONSTRUCTION | 57.8 | 0 | 0 | 0
67 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Raikhadighi Mouza under BAHIRGACHHI Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6418/MD | 19/12/2024 | 45 | ANUKUL CHANDRA DAS | 18.48 | 0 | 0 | 0
68 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village-Basantapur, JL. No. 82, G.P.- Baidyapur of BHABUK Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 2315/MD | 30/09/2020 | 31 | M/S RADHA KRISHNA ENTERPRISE | 2.64 | 1.26 | 100 | 0
69 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Arbara, JL. No. 57, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 2459/MD | 12/10/2020 | 30 | TARUN KUMAR DEY | 31.69 | 11.55 | 100 | 0
70 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Bagunja, JL. No. 38, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 2460/MD | 12/10/2020 | 30 | M/S N. N. ENTERPRISE | 5.71 | 4.75 | 100 | 0
71 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Haripur, JL. No. 20, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 2461/MD | 12/10/2020 | 30 | M/S STAR INDIA CONSTRUTION | 17.3 | 11.07 | 100 | 0
72 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Khadiarpur, JL. No. 21, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 2462/MD | 12/10/2020 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 16.85 | 11.71 | 100 | 0
73 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Khosalpur, JL. No. 56, G.P.- Bhagabanpur of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 2463/MD | 12/10/2020 | 30 | IDEAL CONSTRUCTION | 9.01 | 5.91 | 100 | 0
74 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Barijpur, JL. No. 43, G.P.-Pandua of PURBA BINODPUR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | 2448/MD | 12/10/2020 | 30 | PARIJAT RAY | 41.39 | 28.07 | 70.69 | 0
75 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Sankail, JL. No. 166, G.P.-Aktail of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 2452/MD | 12/10/2020 | 30 | M/S BABLU ENTERPRISE | 20.5 | 15.37 | 100 | 0
76 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Mahupaul, JL. No. 100, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 2306/MD | 30/09/2020 | 31 | RABIUL ISLAM | 2.82 | 1.72 | 100 | 0
77 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Chandipur, JL. No. 40, G.P.-Bhagabanpur of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 2301/MD | 30/09/2020 | 31 | BIDYUT MAHALDAR | 4.45 | 3.82 | 100 | 0
78 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Surjyapura Tengurpura, JL. No. 151, G.P.- Sadlichak of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 274/MD | 28/01/2021 | 30 | A. K. CONSTRUCTION | 29.56 | 0 | 0 | 100
79 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Latasi, JL. No. 89, G.P.- Daulatpur of MALIPAKAR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 272/MD | 28/01/2021 | 30 | M/S SABANA CONSTRUCTION | 35.86 | 0 | 0 | 1
80 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village-Jalakar Bithan, JL. No. 115, G.P.- Muchia of MOBARAKPUR Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | 295/MD | 28/01/2021 | 30 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 7.78 | 0 | 0 | 100
81 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Extension of UPVC pipe line laying for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Uttar Arbara under command area of ARBARA Water Supply Scheme at Chanchal-I Block under Malda Division. PHE Dte. | 3053/MD | 09/08/2023 | 30 | SOFIKUL ISLAM | 3.09 | 0 | 0 | 100
82 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Mabrakpur Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 3365/MD | 29/08/2023 | 45 | GOBINDA ENTERPRISE | 36.28 | 0 | 0 | 100
83 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Purba Binodpur Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 3368/MD | 29/08/2023 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 10.11 | 0 | 0 | 100
84 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Kankot Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 3811/MD | 29/09/2023 | 30 | PRITAM ENTERPRISE | 7.66 | 0 | 0 | 100
85 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of UTTAR KUMEDPUR Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 4771/MD | 05/12/2023 | 45 | MD WARESH ALI | 19.7 | 0 | 0 | 80
86 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Basara Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | 1512/MD | 16/03/2024 | 168 | MANIK CHOUDHURY | 21.17 | 0 | 0 | 100
87 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Material Requisition To Resource Division | 34/MD | 04/01/2024 | 0 | Resource Division | 3.08 | 0 | 0 | 0
88 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Material Requisition To Resource Division | 55/MD | 04/01/2024 | 0 | Resource Division | 0.62 | 0 | 0 | 0
89 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Material Requisition To Resource Division | 112/MD | 05/01/2024 | 0 | Resource Division | 1.23 | 0 | 0 | 0
90 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Material Requisition To Resource Division | 31/MD | 04/01/2024 | 0 | Resource Division | 5.85 | 0 | 0 | 0
91 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Material Requisition To Resource Division | 3993/MD | 08/08/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
92 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bujurkhali, JL. No. 110, G.P.-Pakuahat of BASARA Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 294/MD | 28/01/2021 | 1799 | GOBINDA ENTERPRISE | 14.53 | 0 | 0 | 0
93 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Birasthali, JL. No. 137, G.P.-Chanchal of DAKSHIN SAHAR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 2458/MD | 12/10/2020 | 30 | M/S. TEWARI CONSTRUCTION | 28.57 | 0 | 0 | 66
94 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dakhin Sahar Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 5403/MD | 21/10/2024 | 340 | GOBINDA ENTERPRISE | 65.18 | 0 | 0 | 0
95 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Laying of additional pipeline for retrofitting and Installation of Functional House Connection of Nemua Piped Water Supply Scheme at Old Malda Block under Malda Division PHE. Dte. | 352/MD | 30/01/2025 | 180 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 89.7 | 0 | 0 | 34
96 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sankail Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 6163/MD | 05/12/2024 | 300 | M/S N. N. ENTERPRISE | 38.42 | 0 | 0 | 0
97 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Malipakar Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 6585/MD | 31/12/2024 | 289 | M/S BABLU ENTERPRISE | 44.5 | 0 | 0 | 50
98 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Augmentation work of OHR, Pump House and Boundary Wall of Arbara Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1051/MD | 18/03/2025 | 75 | M/S ANKUSH ENTERPRISE | 32.37 | 0 | 0 | 0
99 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 50 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Malipakar Water Supply Scheme of Harishchandrapur-II Dev. Block under Malda Division P.H.E Dte in the District of Malda. | 2510/MD | 29/05/2025 | 135 | BANIK BROTHERS | 20.04 | 0 | 0 | 0
100 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arbara Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 2334/MD | 22/05/2025 | 60 | S & G CONSTRUCTION | 28.65 | 0 | 0 | 0
101 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe & providing FHTC for PURBA BINODPUR piped Water Supply Scheme at Gazole Block in the District of Malda under Malda Division, P.H.E.Dte. | 3722/MD | 30/07/2025 | 60 | ABHIJIT CONSTRUCTION | 17.47 | 0 | 0 | 0
102 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Additional laying of Pipe line for improvement of FHTC functionality by different dia UPVC pipe & FHTC for BASARA piped Water Supply Scheme at Bamongola Block in the District of Malda under Malda Division, P.H.E.Dte. | 3693/MD | 29/07/2025 | 156 | MANIK CHOUDHURY | 60.11 | 0 | 0 | 0
103 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Sinking of 200mm (all through) Big Dia Tube Well of 180m Deep at 3rd Tube Well Site and Construction of Pump House at 3rd Tube Well site Laying of dedicated/Parallel pipe line and Providing balanced FHTC under GANNADIA Piped Water Supply Scheme under at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 3723/MD | 30/07/2025 | 245 | HARUN ALL RASHID & BROTHERS | 39.34 | 0 | 0 | 0
104 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Raykhandighi, JL. No. 23, G.P.-Bahirgachhi-I of BAHIRGACHHI Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | 270/MD | 28/01/2021 | 1381 | M/S KUNDU CONSTRUCTION | 25.44 | 0 | 0 | 100
105 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bhabanipur, JL. No. 75, G.P.-Chandpur of PARAMESWARPUR Water Supply Scheme at Bamangola Block under Malda Division, PHE Dte. | 302/MD | 28/01/2021 | 489 | MARSS INTERNATIONAL | 7.25 | 0 | 0 | 100
106 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) At -Bibijhuti (JL. No. 58), Naikanda (JL. No. 39) & Chandipur (JL. No. 40) G.P.-Kharba In connection of Source Augmentation of Kendua PWSS at Chanchal-I Block under Malda Division. PHE Dte. | 3458/MD | 07/09/2023 | 328 | M/S /FAIZUL HAQUE BISWAS | 33.7 | 0 | 0 | 100
107 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BAHIRGACHHI Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 4766/MD | 05/12/2023 | 229 | IDEAL CONSTRUCTION | 12.1 | 0 | 0 | 80
108 | MALDAH | Malda Division | Providing Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bahirgachhi, Purba Binodpur, Sankail, Khatil, Kendua, Dakshin Sahar, Rampur, Gannadia, Basara, Parameswarpur, Arbara, Konar, Nem , SM/07972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at RAIKHADIGHI Mouza under BAHIRGACHI Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 1176/MD | 14/03/2024 | 293 | ABHIJIT ENTERPRISE | 13.25 | 0 | 0 | 100
109 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AKALPUR Water Supply Scheme , SM/06851 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AKALPUR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | 2716/MD | 10/11/2020 | 45 | M/S AMIT KUMAR GUPTA | 73.35 | 15.66 | 21.34 | 40
110 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of AKALPUR Water Supply Scheme , SM/06851 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Akalpur Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 5936/MD | 27/11/2024 | 90 | S. N. CONSTRUCTION | 42.82 | 0 | 0 | 0
111 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ARJUNA Water Supply Scheme , SM/06854 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ARJUNA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 2717/MD | 10/11/2020 | 45 | UNIVERSAL ENTERPRIESES | 70.14 | 57.26 | 45.98 | 1
112 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ARJUNA Water Supply Scheme , SM/06854 | Retrofitting | Material Requisition To Resource Division | 3915/MD | 06/08/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
113 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block , SM/09660 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KuddibarMohonpur, Munshipara, ShyampurColoni, Madia of Milki Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1750/MAAD | 24/11/2021 | 45 | M/S N. N. ENTERPRISE | 11.76 | 0 | 0 | 1
114 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block , SM/09660 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kuddibari Mohonpur of Milki Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1721/MAAD | 18/11/2021 | 30 | M/S N. N. ENTERPRISE | 4.79 | 0 | 0 | 1
115 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block , SM/09660 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Madia Mouza of Milki Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1761/MAAD | 24/11/2021 | 60 | BHOLANATH CONSTRUCTION | 41.21 | 0 | 0 | 1
116 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block , SM/09660 | Retrofitting | Repairing & Laying of pipeline at Bhabanipur & Pirpur under Bhabanipur mouza in connection with Jal Jeevan Mission (JJM), Repairing of valve Chamber & other allied works at Milki Distribution zone under Malda Arsenic Area Water Supply Division PHED. | 1876/MAAD | 28/09/2022 | 45 | M/S N. N. ENTERPRISE | 5.27 | 0 | 0 | 1
117 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block , SM/09660 | Retrofitting | Material Requisition To Resource Division | 1339/MAAD | 18/07/2022 | 0 | Resource Division | 12.3 | 0 | 0 | 0
118 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block , SM/09660 | Retrofitting | Material Requisition To Resource Division | 1701/MAAD | 21/09/2022 | 0 | Resource Division | 1.23 | 0 | 0 | 0
119 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block , SM/09660 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Khaskol Chandipur & Bhabanipur Mouza of Milki Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1400/MAAD | 26/07/2022 | 60 | M/S N. N. ENTERPRISE | 27.51 | 0 | 0 | 100
120 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block , SM/09660 | Retrofitting | Laying of pipeline at Milki G.S. Colony & Bhabanipur in connection with Jal Jeevan Mission (JJM) to provide FHTC at Milki Distribution Zone under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 884/MAAD | 11/05/2023 | 60 | M/S N. N. ENTERPRISE | 7.75 | 0 | 0 | 100
121 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Milki Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block , SM/09660 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
122 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09661 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sherpur Water Supply Scheme (Mouza- Chirampur, Purba Chandpur, Dakshin Debipur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 822/MAAD | 28/04/2022 | 60 | A. K. CONSTRUCTION | 80.44 | 0 | 0 | 1
123 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09661 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sherpur Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Sherpur) | 1746/MAAD | 24/11/2021 | 60 | A. K. CONSTRUCTION | 43.13 | 0 | 0 | 1
124 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09661 | Retrofitting | Laying of uPVC Pipe line at Dandi Gram, Jafarabad for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area Water Supply Division, PHE Dte. | 388/MAAD | 08/03/2022 | 45 | A. K. CONSTRUCTION | 13.29 | 0 | 0 | 1
125 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09661 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: -Sherpur Habitations: - Fatekhani for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1825MAAD | 27/09/2022 | 45 | A. K. CONSTRUCTION | 5.59 | 0 | 0 | 100
126 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09661 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: -Sherpur Habitations: - Sherpur for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1827MAAD | 27/09/2022 | 45 | A. K. CONSTRUCTION | 6.84 | 0 | 0 | 100
127 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09661 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: -Sherpur, Chhirampur Habitations: - Jamirgata, Chhatragachi, Mandal Para, Kamat, Jalalpur, Chhirampur for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1826/MAAD | 27/09/2022 | 45 | A. K. CONSTRUCTION | 5.19 | 0 | 0 | 100
128 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09661 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: -Sherpur, Chhirampur Habitations: - Jamirgata, Chhatragachi, Mandal Para, Kamat, Jalalpur, Chhirampur for installation of FHTC under Sherpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1868/MAAD | 28/09/2022 | 30 | A. K. CONSTRUCTION | 4.87 | 0 | 0 | 100
129 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09661 | Retrofitting | Material Requisition To Resource Division | 1702/MAAD | 21/09/2022 | 0 | Resource Division | 4.93 | 0 | 0 | 0
130 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sherpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09661 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
131 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mothabari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-II Bl , SM/09651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mothabari Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Tap Protappar) | 1745/MAAD | 24/11/2021 | 60 | FUTURE | 48.77 | 0 | 0 | 1
132 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mothabari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-II Bl , SM/09651 | Retrofitting | Laying of 75mm uPVC pipe line at Dulauri, Kuttu Mandal Tola & Satanga Para for installation of FHTC under Mothabari distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 354/MAAD | 07/03/2022 | 45 | FUTURE | 4.29 | 0 | 0 | 1
133 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mothabari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-II Bl , SM/09651 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: -Tap Pratappur, Habitations: - Jotkabil, Satangapara for installation of FHTC under Mothabari distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 949MAAD | 11/05/2022 | 15 | FUTURE | 3.78 | 0 | 0 | 1
134 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mothabari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-II Bl , SM/09651 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: -Tap Pratappur, Habitations: - Amlitola, Kuttu Mandal Tola, Laxmipur, Dhulauri, Haibatola for installation of FHTC under Mothabari distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 950/MAAD | 11/05/2022 | 15 | FUTURE | 2.95 | 0 | 0 | 1
135 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mothabari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-II Bl , SM/09651 | Retrofitting | Laying of 75mm uPVC pipe line at different places for installation of FHTC under Mothabari distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 355/MAAD | 07/03/2022 | 45 | FUTURE | 3.71 | 0 | 0 | 1
136 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mothabari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-II Bl , SM/09651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mothabari Water Supply Scheme (Mouza- Debipur & Chakpratappur) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1019/MAAD | 12/05/2022 | 60 | M/S ALISA CONSTRUCTION | 51.08 | 0 | 0 | 1
137 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mothabari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-II Bl , SM/09651 | Retrofitting | Material Requisition To Resource Division | 1338/MAAD | 18/07/2022 | 0 | Resource Division | 12.3 | 0 | 0 | 0
138 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mothabari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-II Bl , SM/09651 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
139 | MALDAH | Malda Division | Augmentation of Tilasan Piped water supply scheme , SM/09567 | Augmentation | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of TILASAN Piped Water Supply Scheme under Malda Division, PHE Dte. | 2693/MD | 09/09/2021 | 7 | RADIANT | 1.25 | 0 | 0 | 1
140 | MALDAH | Malda Division | Augmentation of Tilasan Piped water supply scheme , SM/09567 | Augmentation | Acceptance cum formal work order for Laying of Rising Main including connection of Pump No-1 & Pump No 2 and by pass arrangement for TILASAN Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the District of Malda. | 1307/MD | 01/06/2022 | 30 | M/S EHAN ENTERPRISE | 4.44 | 0 | 0 | 1
141 | MALDAH | Central Drilling | Augmentation of Tilasan Piped water supply scheme , SM/09567 | Augmentation | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT TILASAN, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. | 347/CMSD-I | 25/07/2022 | 15 | CHANDA ENTERPRISE | 4.69 | 0 | 0 | 0
142 | MALDAH | Central Drilling | Augmentation of Tilasan Piped water supply scheme , SM/09567 | Augmentation | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITEFOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. | 346/CMSD-I | 25/07/2022 | 15 | CHANDA ENTERPRISE | 4.66 | 0 | 0 | 0
143 | MALDAH | Malda Division | Augmentation of Tilasan Piped water supply scheme , SM/09567 | Augmentation | Acceptance cum formal work order for Dismentling of Concrete road and Construction the same from Head Work site to 2nd Tube Well Site of TILASAN Water Supply Scheme at Habibpur Dev. Block under Malda Division, P.H.E. Dte. In the district of Malda. | 1443/MD | 29/03/2023 | 30 | M/S EHAN ENTERPRISE | 3.15 | 0 | 0 | 100
144 | MALDAH | Malda Division | Augmentation of Tilasan Piped water supply scheme , SM/09567 | Augmentation | Acceptance cum formal work order for Dismantling of concrete road and Construction the same at different places of road connecting to LDS of TILASAN Piped Water Supply Scheme at Habibpur Dev. Block, under Malda Division, P.H.E. Dte. in the District of Malda. | 2177/MD | 07/06/2023 | 30 | UTTAM KUMAR GHOSH | 21.68 | 0 | 0 | 100
145 | MALDAH | Malda Division | Augmentation of Tilasan Piped water supply scheme , SM/09567 | Augmentation | Acceptance cum formal work order for Providing Functional House hold Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under Command area of Augmentation of TILASAN Piped Water Supply Scheme at Habibpur Dev. Block, under Malda Division, P.H.E. Dte. in the District of Malda. | 2178//MD | 07/06/2023 | 30 | UTTAM KUMAR GHOSH | 13.35 | 0 | 0 | 100
146 | MALDAH | Malda Division | Augmentation of Tilasan Piped water supply scheme , SM/09567 | Augmentation | Material Requisition To Resource Division | 1107/MD | 17/05/2022 | 0 | Resource Division | 16.55 | 0 | 0 | 0
147 | MALDAH | Malda Division | Augmentation of Tilasan Piped water supply scheme , SM/09567 | Augmentation | Material Requisition To Resource Division | 1587/MD | 28/03/2023 | 0 | Resource Division | 0.41 | 0 | 0 | 0
148 | MALDAH | Malda Division | Augmentation of Tilasan Piped water supply scheme , SM/09567 | Augmentation | Material Requisition To Resource Division | 1461/MD | 22/06/2022 | 0 | Resource Division | 6.78 | 0 | 0 | 0
149 | MALDAH | Malda Mechanical | Augmentation of Tilasan Piped water supply scheme , SM/09567 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- I of Tilason Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/009047) | 2226/MLMD | 18/07/2023 | 839 | SUBRATA KUMAR DAS. | 10.08 | 0 | 0 | 30
150 | MALDAH | Central Drilling | Augmentation of Tilasan Piped water supply scheme , SM/09567 | Augmentation | Hiring of Diesel Driven Motor Cab (BS-IV & Above) having contract carriage permit along with driver for the office of the Calcutta Mecha nical Sub Division-I(D), CDD, P.H.Engineering Dte. For Supervision of JJM related works. | 13/CMSD-I(D) | 15/01/2024 | 198 | AJAY KUMAR | 0.94 | 0 | 0 | 15
151 | MALDAH | Malda Division | Augmentation of Tilasan Piped water supply scheme , SM/09567 | Augmentation | Formal work order for Augmentation of TILASAN Piped water supply scheme for the work of Geotechnical Study,construction of 200 Cum RCC OHR,Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Habibpur Block under Malda Division PH Engg.Dte. In the District of Malda. | 996/MD | 22/04/2022 | 365 | UTTAM KUMAR GHOSH | 180.23 | 0 | 0 | 100
152 | MALDAH | Malda Mechanical | Augmentation of Tilasan Piped water supply scheme , SM/09567 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- II of Tilason Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/009047) | 2227/MLMD | 18/07/2023 | 542 | JOY ENTERPRISE. | 7.57 | 0 | 0 | 25
153 | MALDAH | Malda Division | INSTALLATION OF 85 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP-ALAL,KARKACH,DEOTALA& BABUPUR IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10307 | Anganwadi | Material Requisition To Resource Division | 525/MD | 03/03/2022 | 0 | Resource Division | 44.95 | 0 | 0 | 0
154 | MALDAH | Malda Division | INSTALLATION OF 85 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP-ALAL,KARKACH,DEOTALA& BABUPUR IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10307 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Karkach GP of Gazole Dev. Block under Malda Division, PHE Dte. | 116/MD | 18/01/2023 | 75 | MERCURY ENGINEERING COMPANY | 218.07 | 0 | 0 | 100
155 | MALDAH | Malda Division | INSTALLATION OF 85 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP-ALAL,KARKACH,DEOTALA& BABUPUR IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10307 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Alal, Deotola & Babupur GP of Gazole Dev. Block under Malda Division, PHE Dte. | 61/MD | 16/01/2023 | 75 | PRADIP KUMAR DAS | 218.07 | 0 | 0 | 100
156 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at Head Work site of UTTAR HARISHCHANDRAPUR ZONE-II & its adjoining mouza Water Supply Scheme under Malda Division,PHE Dte. In the District of Malda. | 1486/MD | 23/06/2022 | 60 | S. N. CONSTRUCTION | 6.18 | 0 | 0 | 0
157 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Laying Emergent repairing of distribution pipe line & laying of UPVC pipe line of UTTAR HARISHCHANDRAPUR water supply scheme under Malda Division, PHE Dte. | 856/MD | 20/03/2020 | 0 | PARIJAT RAY | 4.57 | 0 | 0 | 1
158 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Material Requisition To Resource Division | 1206/MD | 24/05/2022 | 0 | Resource Division | 53.31 | 0 | 0 | 0
159 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Soil Investigation and design of substructure for Over Head Reservoirs for UTTAR HARISHCHANDRAPUR ZONE-I Piped Water Supply Scheme at Harishchandapur-I Dev. Block under Malda Division, PHE Dte. In the district of Malda. | BP-2022-23-196 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
160 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Bill for reimbursement of cost of Diesel and Mobile in respect of hired Vehicle Car No. WB65A/4911 for the month of May & June 2023. |  | 04/09/2023 | 0 | USHA ENTERPRISE | 0.41 | 0 | 0 | 0
161 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Placement of fund against the work for road restoration work for laying of pipe line for NH-81 to Harishchandarapur Railway Station Road under Malda Division, PHE Dte. In the district of Malda. | BP-2022-23-213 | 17/03/2023 | 0 | EXECUTIVE ENGINEER, MALDA HIGHWAY DIVISION, P.W. (ROADS) DIRECTORATE. | 1.4 | 0 | 0 | 0
162 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Formal work order for the work of Construction of 400 M3 Capacity OHR with Soil Investigation and FHTC of UTTAR HARISHCHANDRAPUR ZONE-II Piped Water Supply Scheme at Harishchandrapur-I and II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2682/MD | 13/07/2023 | 988 | KANAN CONSTRUCTION ENTERPRISE | 229.11 | 0 | 0 | 65
163 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Uttar Harishchandrapur Zone-I PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 276/MD | 11/01/2024 | 45 | M/S DUTTA ENTERPRISE | 4.18 | 0 | 0 | 0
164 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Construction of Boundary Wall at Head Work site of Uttar Harishchandrapur Zone-II Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 3032/MD | 13/06/2024 | 153 | M/S. B. PAUL & COMPANY | 25.13 | 0 | 0 | 82
165 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Acceptance cum formal work order for Sinking of 01 (One) Nos. 300mm. Dia. x 200mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Uttar Harishchandrapur (Zone-I) Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda . | 1393/MD | 14/06/2022 | 21 | M/S DEBASISH GHOSH | 10.83 | 0 | 0 | 96
166 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Acceptance cum formal work order for Sinking of 01 (One) Nos. 300mm. Dia. x 200mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Uttar Harishchandrapur (Zone-II) Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda . | 1394/MD | 14/06/2022 | 21 | SNEHASISH GHOSH | 10.82 | 0 | 0 | 95
167 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Construction of 5.40 mtr.X 3.60 mtr Switch Room cum chlorine room at UTTAR HARISHCHANDRAPUR ZONE-II Piped Water Supply Scheme at Head Work Site under Harishchandrapur-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | 2891/MD | 07/06/2024 | 45 | KANAN CONSTRUCTION ENTERPRISE | 6.6 | 0 | 0 | 100
168 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Material Requisition To Resource Division | 35/MD | 04/01/2024 | 0 | Resource Division | 17.33 | 0 | 0 | 0
169 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Material Requisition To Resource Division | 97/MD | 05/01/2024 | 0 | Resource Division | 11.4 | 0 | 0 | 0
170 | MALDAH | Malda Mechanical | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Quatation for new service connection at Uttar Harishchandrapur w/s sch. Zone I T/W no IV UNDER MLMD. Dist Malda. (Harishchandrapur C. C. C) | BP-2023-24-527 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 8.02 | 0 | 0 | 0
171 | MALDAH | Malda Mechanical | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | New service connection at UTTAR HARISHCHANDRAPUR PWSS Zone II T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | BP-2023-24-730 | 28/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.42 | 0 | 0 | 0
172 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Uttar Harishchandrapur Zone-II Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. (2nd Call) | 377/MD | 31/01/2023 | 1034 | KUNDU CONSTRUCTION | 227.6 | 0 | 0 | 41
173 | MALDAH | Malda Mechanical | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Augmentation of Uttar Harishandropur (Zone- II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008163) | 2254/MLMD | 18/07/2023 | 862 | DAS ENTERPRISE. | 21.45 | 0 | 0 | 45
174 | MALDAH | Malda Mechanical | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II, III & IV and making compound lighting arrangement at T/W no. I of Augmentation of Uttar Harishandropur (Zone- I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008163) | 2253/MLMD | 18/07/2023 | 1016 | M/S P.P. ELECTRICALS | 50.68 | 0 | 0 | 82
175 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Formal work order for the work of Construction of 900 M3 Capacity OHR with FHTC (Mouza- Uttar Harishchandrapur 50% area covered) of Uttar Harishchandrapur Zone-I Piped Water Supply Scheme at Harishchandrapur-I & II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 3615/MD | 21/09/2023 | 468 | MAHAMAYA BURIMA ENTERPRISE | 340.61 | 0 | 0 | 65
176 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Laying of Additional Pipeline HDPE in connection with Jal Jeevan Mission (JJM) at Uttar Harishchandrapur Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 5831/MD | 22/11/2024 | 317 | KUNDU CONSTRUCTION | 95.04 | 0 | 0 | 0
177 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Construction of Boundary Wall at 3rd Tube well site of Uttar Harishchandrapur Zone-I Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 3031/MD | 13/06/2024 | 657 | M/S GHOSH CONSTRUCTION | 10.19 | 0 | 0 | 0
178 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Construction of Boundary Wall at Head Work site of Uttar Harishchandrapur Zone-I Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 5002/MD | 27/09/2024 | 270 | SAJEDUR RAHAMAN | 34.41 | 0 | 0 | 80
179 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Road restoration work related to laying of Pipeleine at Uttar Harishchandrapur Zone-I Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | 2881/MD | 17/06/2025 | 45 | PRADIP KUMAR DAS | 56.21 | 0 | 0 | 0
180 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Pump House No. 4 of Uttar Harishchandrapur Zone-I PWSS under Harishchandrapur-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 2278/MD | 21/05/2025 | 45 | MASUMA ENTERPRISE | 4.28 | 0 | 0 | 100
181 | MALDAH | Malda Division | Augmentation of Uttar Harishandropur piped water supply scheme. , SM/10291 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Uttar Harishchandrapur Zone-I Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. (2ND Call) | 1791/MD | 01/08/2022 | 1035 | PRADIP KUMAR DAS | 369.64 | 0 | 0 | 100
182 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Western Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (77 nos. AWCs in English Bazar Block) , SM/10202 | Anganwadi | Material Requisition To Resource Division | 332/MAAD | 28/02/2022 | 0 | Resource Division | 50.25 | 0 | 0 | 0
183 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Western Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (77 nos. AWCs in English Bazar Block) , SM/10202 | Anganwadi | Providing Drinking Water Supply in 10 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 660/MAAD | 01/04/2022 | 899 | MERCURY ENGINEERING COMPANY | 70.55 | 0 | 0 | 37
184 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Western Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (77 nos. AWCs in English Bazar Block) , SM/10202 | Anganwadi | Providing Drinking Water Supply in 12 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 658/MAAD | 01/04/2022 | 120 | HANNAN BUILDERS PVT. LTD. | 84.7 | 0 | 0 | 90
185 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Western Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (77 nos. AWCs in English Bazar Block) , SM/10202 | Anganwadi | Providing Drinking Water Supply in 10 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 659/MAAD | 01/04/2022 | 1006 | MERCURY ENGINEERING COMPANY | 70.55 | 0 | 0 | 70
186 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Western Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (77 nos. AWCs in English Bazar Block) , SM/10202 | Anganwadi | Formal work order for Providing Drinking Water Supply in 45 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure-V ) | 1075/MAAD | 01/06/2022 | 878 | MERCURY ENGINEERING COMPANY | 319.24 | 0 | 0 | 90
187 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10237 | Anganwadi | Providing Drinking Water Supply in 7 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure) | 657/MAAD | 01/04/2022 | 120 | BANIK BROTHERS | 49.4 | 0 | 0 | 0
188 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10237 | Anganwadi | Formal work order for Providing Drinking Water Supply in 15 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 1050/MAAD | 23/05/2022 | 120 | ALOK ENTERPRISE. A UNIT OF SAKET TREXIM PVT. LTD. | 105.78 | 0 | 0 | 0
189 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10237 | Anganwadi | Supply & delivery of G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for providing Drinking Water Supply in Source Less ICDS at Manikchak Block under Malda Arsenic Area Water Supply Divisio, P.H.E. Dte. | 2051/MAAD | 18/11/2022 | 15 | MERCURY ENGINEERING COMPANY | 10.17 | 0 | 0 | 0
190 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10237 | Anganwadi | Supply & delivery of G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for providing Drinking Water Supply in Source Less Schols & ICDS at Manikchak Block (Phase -II ) under Malda Arsenic Area Water Supply Divisio, P.H.E. Dte. | 320/MAAD | 21/02/2023 | 15 | M/S TRILOCHAN CONSTRUCTION CO. | 2.61 | 0 | 0 | 100
191 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10237 | Anganwadi | Material Requisition To Resource Division | 333/MAAD | 28/02/2022 | 0 | Resource Division | 61.62 | 0 | 0 | 0
192 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10237 | Anganwadi | Formal work order for Providing Drinking Water Supply in 25 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 783/MAAD | 26/04/2022 | 120 | NEOGI ENTERPRISE | 176.42 | 0 | 0 | 43
193 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10237 | Anganwadi | Providing Drinking Water Supply in 10 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 656/MAAD | 01/04/2022 | 120 | MILLENNIUM ENTERPRISE | 70.52 | 0 | 0 | 65
194 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10237 | Anganwadi | Supply & delivery of G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for providing Drinking Water Supply in Source Less Schools & ICDS at Manikchak Block (Phase -III) under Malda Arsenic Area Water Supply Divisio, P.H.E. Dte. | 319/MAAD | 21/02/2023 | 15 | M/S TAPAS KUMAR CHAKRABORTY | 1.65 | 0 | 0 | 100
195 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 67 nos. Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10237 | Anganwadi | Providing Drinking Water Supply in 10 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 655/MAAD | 01/04/2022 | 120 | M/S TRILOCHAN CONSTRUCTION CO. | 70.31 | 0 | 0 | 6
196 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11588 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Kariali Zone-I Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | 656/MD | 22/03/2022 | 15 | M/S SOBHA & CO. | 3.23 | 0 | 0 | 1
197 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11588 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 56.72 | 0 | 0 | 0
198 | MALDAH | Malda Mechanical | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11588 | New | Supply, installation, commissioning of electro-mechanical components at T/W no. I, II,III of Kariali (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011278) | 2756/MLMD | 14/08/2023 | 898 | DILIP MAHATO. | 43.59 | 0 | 0 | 69
199 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11588 | New | Material Requisition To Resource Division | 100/MD | 05/01/2024 | 0 | Resource Division | 25.06 | 0 | 0 | 0
200 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11588 | New | Formal work order for the work of Augmentation of KARIALI ZONE-I Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2681/MD | 13/07/2023 | 1019 | KANAN CONSTRUCTION ENTERPRISE | 437.7 | 0 | 0 | 75
201 | MALDAH | Malda Mechanical | Ground Water Based for Kariali Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11588 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 2212/MLMD | 21/08/2024 | 61 | NITAI PANDEY | 0.78 | 0 | 0 | 0
202 | MALDAH | Malda Division | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12305 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well no-3 ( 115 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at RAJARAMPUR Water Supply Scheme of Habibpur Block .under Malda Division, PHE Dte. in the District of Malda. | 2301/MD | 28/09/2022 | 30 | DUTTA ENTERPRISE | 8.24 | 0 | 0 | 1
203 | MALDAH | Malda Division | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12305 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of RAJARAMPUR Water Supply Scheme of Habibpur Block. under Malda Division, PHE Dte. in the District of Malda. | 3109/MD | 20/12/2022 | 45 | M/S SRINJOYEE | 6.68 | 0 | 0 | 1
204 | MALDAH | Malda Mechanical | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12305 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H-III site of Rajarampur C.C.C Aiho in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004231191 | 21/03/2023 | 7 | W.B.S.E.D.C.LTD | 0.71 | 0 | 0 | 1
205 | MALDAH | Malda Mechanical | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12305 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Rajarampur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012802) | 821/MLMD | 03/05/2023 | 180 | SUDIP DEY | 11.22 | 0 | 0 | 98
206 | MALDAH | Malda Division | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12305 | Augmentation | Material Requisition To Resource Division | 2406/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0 | 0
207 | MALDAH | Malda Division | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12305 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for RAJARAMPUR Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | 2505//MD | 03/11/2022 | 45 | GOBINDA ENTERPRISE | 43.92 | 0 | 0 | 100
208 | MALDAH | Malda Mechanical | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12305 | Augmentation | Hiring of Inspection vehicle (Diesel driven) for official use of AE-II for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 1130/MLMD | 23/06/2023 | 7 | SUBRATA SAHA | 0.86 | 0 | 0 | 100
209 | MALDAH | Malda Division | Source Augmentation of Rajarampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12305 | Augmentation | Augmentation of Head work site Pump House, PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at RAJARAMPUR Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1122/MD | 21/03/2025 | 369 | THREE BROTHERS CONSTRUCTION & CO | 9.43 | 0 | 0 | 0
210 | MALDAH | Malda Division | KISMAT BAROL Piped Water Supply Scheme , SM/12190 | New | Material Requisition To Resource Division | 3046/MD | 12/12/2022 | 0 | Resource Division | 22.91 | 0 | 0 | 0
211 | MALDAH | Malda Division | KISMAT BAROL Piped Water Supply Scheme , SM/12190 | New | Material Requisition To Resource Division | 1612/MD | 11/04/2023 | 0 | Resource Division | 14.33 | 0 | 0 | 0
212 | MALDAH | Malda Mechanical | KISMAT BAROL Piped Water Supply Scheme , SM/12190 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Kismat Barol Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013044) | 2322/MLMD | 26/07/2023 | 120 | S. P. CONSTRUCTION | 26.28 | 0 | 0 | 52
213 | MALDAH | Malda Division | KISMAT BAROL Piped Water Supply Scheme , SM/12190 | New | Construction of Boundary Wall at 2nd Tube Well site of Kismatbarol Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 2942/MD | 10/06/2024 | 30 | S & G CONSTRUCTION | 8.41 | 0 | 0 | 0
214 | MALDAH | Malda Mechanical | KISMAT BAROL Piped Water Supply Scheme , SM/12190 | New | New service connection at KISMATBAROL Pwss pH NO II Under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) | BP-2023-24-663 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 8.14 | 0 | 0 | 0
215 | MALDAH | Malda Mechanical | KISMAT BAROL Piped Water Supply Scheme , SM/12190 | New | New service connection at Kismatbaral PWSS T/W NO I Under EE/MLMD PHE DTE DIST. Malda.(kushida c c c) | BP-2024-25-203 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.79 | 0 | 0 | 0
216 | MALDAH | Malda Division | KISMAT BAROL Piped Water Supply Scheme , SM/12190 | New | Formal work order for the work of Implementation of KISMAT BAROL Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2115/MD | 06/06/2023 | 602 | MILLENNIUM ENTERPRISR | 463.93 | 0 | 0 | 52
217 | MALDAH | Malda Division | KISMAT BAROL Piped Water Supply Scheme , SM/12190 | New | Construction of Boundary Wall at Head Work site of Kismatbarol Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 3035/MD | 13/06/2024 | 567 | MILLENNIUM ENTERPRISE | 28.66 | 0 | 0 | 80
218 | MALDAH | Malda Division | KISMAT BAROL Piped Water Supply Scheme , SM/12190 | New | Dedicated/Parallel Pipe Line for better functionality and road restoration of Kismat Baral Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 5919/MD | 26/11/2025 | 60 | MILLENNIUM ENTERPRISE | 44.43 | 0 | 0 | 0
219 | MALDAH | Malda Division | Alal Zone-II Piped Water Supply Scheme , SM/12877 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Alal Zone-II Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | 652/MD | 22/03/2022 | 15 | TECHVISION | 3.33 | 0 | 0 | 0
220 | MALDAH | Malda Division | Alal Zone-II Piped Water Supply Scheme , SM/12877 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 10.65 | 0 | 0 | 0
221 | MALDAH | Malda Mechanical | Alal Zone-II Piped Water Supply Scheme , SM/12877 | New | Supply, installation, commissioning of electro-mechanical components & Trial operation at T/W no. I & II, and making compound lighting arrangement at head worksite of Alal Zone-II Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011886) | 2584/MLMD | 04/08/2023 | 832 | DAS CONSTRUCTION | 25.24 | 0 | 0 | 70
222 | MALDAH | Malda Division | Alal Zone-II Piped Water Supply Scheme , SM/12877 | New | Material Requisition To Resource Division | 252/MD | 10/01/2024 | 0 | Resource Division | 8.7 | 0 | 0 | 0
223 | MALDAH | Malda Mechanical | Alal Zone-II Piped Water Supply Scheme , SM/12877 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Alal Zone-II, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-712 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.64 | 0 | 0 | 0
224 | MALDAH | Malda Division | Alal Zone-II Piped Water Supply Scheme , SM/12877 | New | Formal work order for the work of Augmentation of ALAL ZONE-II Piped Water Supply Scheme at Gajol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2000/MD | 17/05/2023 | 944 | KRISHNENDU DUTTA | 357.66 | 0 | 0 | 50
225 | MALDAH | Malda Division | Alal Zone-II Piped Water Supply Scheme , SM/12877 | New | Construction of Boundary Wall at Head Work site of Alal Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3415/MD | 09/07/2024 | 571 | KRISHNENDU DUTTA | 33.49 | 0 | 0 | 0
226 | MALDAH | Malda Division | Alal Zone-II Piped Water Supply Scheme , SM/12877 | New | Construction of Boundary Wall at 2nd Tube Well site of Alal Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3952/MD | 07/08/2024 | 557 | KRISHNENDU DUTTA | 8.71 | 0 | 0 | 0
227 | MALDAH | Malda Division | Alal Zone-II Piped Water Supply Scheme , SM/12877 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6407/MD | 19/12/2024 | 407 | KRISHNENDU DUTTA | 28.08 | 0 | 0 | 0
228 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Milki, Niamatpur, Gosaipur, Mobarakpur, Madapur and Uttar Jadupur Zone Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11911 | Retrofitting | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Laxmipur, Nagrai and adjoining villages under command area of Laxmighat Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1480/MAAD | 03/09/2024 | 60 | S. N. CONSTRUCTION | 7.08 | 0 | 0 | 0
229 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Milki, Niamatpur, Gosaipur, Mobarakpur, Madapur and Uttar Jadupur Zone Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11911 | Retrofitting | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Milki G.S. Colony under command area of Milki Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 303/MAAD | 11/03/2024 | 30 | M/S N. N. ENTERPRISE | 4.2 | 0 | 0 | 90
230 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Milki, Niamatpur, Gosaipur, Mobarakpur, Madapur and Uttar Jadupur Zone Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11911 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
231 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Milki, Niamatpur, Gosaipur, Mobarakpur, Madapur and Uttar Jadupur Zone Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11911 | Retrofitting | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Laxmipur under command area of Laxmighat Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1481/MAAD | 03/09/2024 | 333 | FUTURE | 7.08 | 0 | 0 | 0
232 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09591 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Enayetpur Water Supply Scheme( Enayetpur mouza) at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1757/MAAD | 24/11/2021 | 45 | A. B. CONSTRUCTION | 24.33 | 0 | 0 | 1
233 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09591 | Retrofitting | Laying of HDPE pipe 20mm dia at Enayetpur Mouza for installation of FHTC under Enayetpur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 361/MAAD | 07/03/2022 | 30 | A. B. CONSTRUCTION | 3.03 | 0 | 0 | 1
234 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09591 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area (Mouza Enayetpur part, Miragram) & others Allied works at Enayetpur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 825/MAAD | 28/04/2022 | 60 | GOBINDA ENTERPRISE | 36.64 | 0 | 0 | 1
235 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09591 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bakipur (Laddutola) under Enayetpur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 1473/MAAD | 29/07/2022 | 45 | ABHIJIT ENTERPRISE | 4.84 | 0 | 0 | 1
236 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09591 | Retrofitting | Repairing of pipe line by laying of UPVC pipeline at Miragram Mouza for installation of FHTC at Enayetpur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 1170/MAAD | 13/06/2022 | 45 | GOBINDA ENTERPRISE | 4.82 | 0 | 0 | 1
237 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09591 | Retrofitting | Laying of 63 mm dia UPVC Pipe and 20 mm dia HDPE pipe and other allied works at Miragram for installation of House Connection under Enayetpur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1870/MAAD | 28/09/2022 | 45 | GOBINDA ENTERPRISE | 3.93 | 0 | 0 | 1
238 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09591 | Retrofitting | Laying UPVC pipe and installation of Street Stand post at Sekhpura purbapara under Enayetpur W/S Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | 945/MAAD | 23/05/2023 | 45 | ABHIJIT ENTERPRISE | 3.53 | 0 | 0 | 0
239 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09591 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at Salabadganj Paschim Para under Enayetpur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 1477/MAAD | 29/07/2022 | 45 | M/S. AYUSH BUILDERS | 4.77 | 0 | 0 | 1
240 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09591 | Retrofitting | Laying of 90 mm dia UPVC Pipeline and other allied works at Salabadganj for installation of House Connection under Enayetpur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1873/MAAD | 28/09/2022 | 45 | M/S. AYUSH BUILDERS | 2.66 | 0 | 0 | 1
241 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Enayetpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09591 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
242 | MALDAH | Malda Division | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12760 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Basara Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte. | 1202/MD | 21/03/2023 | 45 | M.S. ENTERPRISE | 4.17 | 0 | 0 | 0
243 | MALDAH | Malda Division | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12760 | Augmentation | Acceptance cum formal work order for Sinking of (200mm. Dia. x 150 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at BASARA Piped Water Supply Scheme (Tube Well No-3) of Malda District under Malda Division, PHE Dte. | 2706/MD | 17/11/2022 | 30 | RATAN CHANDRA SARKAR | 6.81 | 0 | 0 | 0
244 | MALDAH | Central Drilling | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12760 | Augmentation | Resistivity survey for Sankail PWSS, Basara PWSS and Pannapur PWSS at Habibipur & Bamongola block under Malda district, CMSD-II (D), CDD, PHE Dte. | 135/CMSD-II(D) | 24/05/2023 | 15 | S B S ENTERPRISE | 0.82 | 0 | 0 | 100
245 | MALDAH | Malda Division | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12760 | Augmentation | Sinking of ( 200 mm Dia. X 150 mm Dia.) Tube well No.-4 (250 M deep) by D.R Rig. Method using P.V.C. Pipe & Gravel Filter including Supply of materials at BASARA Water Supply Scheme of Bamongola Block under Malda Division, P.H.E Dte in the District of Malda. | 380/MD | 17/01/2024 | 45 | A. L. ENGINEERING SOLUTION | 12.74 | 0 | 0 | 100
246 | MALDAH | Malda Division | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12760 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for BASARA Piped Water Supply Scheme at Bamangola Dev. Block in the District of Malda under Malda Division, PHE Dte. | 2987/MD | 07/12/2022 | 936 | M/S JHA CONSTRUCTION | 81.06 | 0 | 0 | 100
247 | MALDAH | Malda Mechanical | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12760 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. IV of Basara Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015035) | 2312/MLMD | 26/07/2023 | 535 | JOY ENTERPRISE. | 11.01 | 0 | 0 | 22
248 | MALDAH | Malda Division | Source Augmentation of Basara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12760 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bujurkhali, Harinandanbati & Chandipur Mouza of Basara Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | 349/MD | 30/01/2025 | 92 | DHRITIPALI | 21.06 | 0 | 0 | 0
249 | MALDAH | Malda Division | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme , SM/13792 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 186.59 | 0 | 0 | 0
250 | MALDAH | Malda Mechanical | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme , SM/13792 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering and making compound lighting arrangement at T/W no. I of Chanchal (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011884) | 2662/MLMD | 10/08/2023 | 2005 | HANNAN BUILDERS PVT. LTD. | 35.18 | 0 | 0 | 60
251 | MALDAH | Malda Mechanical | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme , SM/13792 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II, Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering and making compound lighting arrangement at T/W no. I of Chanchal (zone-III) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011884) | 3425/MLMD | 01/11/2023 | 818 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 33.92 | 0 | 0 | 65
252 | MALDAH | Malda Division | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme , SM/13792 | Augmentation | Material Requisition To Resource Division | 111/MD | 05/01/2024 | 0 | Resource Division | 34.35 | 0 | 0 | 0
253 | MALDAH | Malda Mechanical | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme , SM/13792 | Augmentation | New service connection at CHANCHAL PWSS Zone III T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( CHANCHAL c c c) | BP-2024-25-85 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.36 | 0 | 0 | 0
254 | MALDAH | Malda Division | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme , SM/13792 | Augmentation | Formal work order for the work of Augmentation of CHANCHAL ZONE-I, ZONE-II AND ZONE-III Piped Water Supply Scheme at Chanchal-I Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1026/MD | 13/03/2023 | 1111 | GHOSH BROTHERS | 1318.2 | 0 | 0 | 15
255 | MALDAH | Malda Mechanical | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme , SM/13792 | Augmentation | Supply, installation, commissioning of electro-mechanical components at T/W no. I, II,III &IV of Chanchal (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011884) | 2385/MLMD | 28/07/2023 | 884 | GHOSH BROTHERS... | 39.33 | 0 | 0 | 0
256 | MALDAH | Malda Division | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme , SM/13792 | Augmentation | Laying of Distribution Sysytem of Chanchal Zone -I, II & III Piped Water Supply Scheme at Chanchal -I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 535/MD | 30/01/2024 | 548 | GHOSH BROTHERS | 56.98 | 0 | 0 | 35
257 | MALDAH | Malda Division | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme , SM/13792 | Augmentation | Emergent Interconnection between Existing Tube Well and Bolck office building water tank in connection of CHANCHAL Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 6621/MD | 31/12/2024 | 180 | BIDYUT MAHALDAR | 0.86 | 0 | 0 | 100
258 | MALDAH | Malda Division | Ground Water Based Augmentation of Chanchal Piped Water Supply Scheme , SM/13792 | Augmentation | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-2) (Period from 01/01/2025 to 30/06/2025). | 6636/MD | 31/12/2024 | 181 | M/S TEWARI CONSTRUCTION | 0.86 | 0 | 0 | 0
259 | MALDAH | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15093 | Augmentation | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for MOYNA Piped Water Supply Scheme (Mouza- Moyna, JL No. 119 & Mouza- Anantarapur, JL No. 120) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | 1163/MD | 20/03/2023 | 45 | MOMTAJ ALI | 24.65 | 0 | 0 | 0
260 | MALDAH | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15093 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 (171.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MOYNA Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | 1170/MD | 20/03/2023 | 30 | A. D. D. ASSOCIATES | 10.56 | 0 | 0 | 0
261 | MALDAH | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15093 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 (171.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MOYNA Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | 1169/MD | 20/03/2023 | 30 | M/S SAHA CONSTRUCTION | 9.8 | 0 | 0 | 100
262 | MALDAH | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15093 | Augmentation | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Moyna Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | 1206/MD | 21/03/2023 | 45 | M/S /FAIZUL HAQUE BISWAS | 8.33 | 0 | 0 | 50
263 | MALDAH | Malda Mechanical | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15093 | Augmentation | Supply, installation, commissioning & Trial operation of electro-mechanical components at T/W no III & IV of Source Augmentation Moyna Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016347) | 2764/MLMD | 14/08/2023 | 180 | MUKHERJEE ART CENTRE | 22.53 | 0 | 0 | 79
264 | MALDAH | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15093 | Augmentation | Material Requisition To Resource Division | 248/MD | 10/01/2024 | 0 | Resource Division | 3.08 | 0 | 0 | 0
265 | MALDAH | Malda Mechanical | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15093 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- IV of Moyna, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-673 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.28 | 0 | 0 | 0
266 | MALDAH | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15093 | Augmentation | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for MOYNA Piped Water Supply Scheme (Moua- Bade Myna, JL No. 117) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | 1155/MD | 20/03/2023 | 879 | M/S BABLU ENTERPRISE | 22.65 | 0 | 0 | 37
267 | MALDAH | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15093 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Moyna Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 297/MD | 29/01/2025 | 45 | MOMTAJ ALI | 52.13 | 0 | 0 | 0
268 | MALDAH | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15093 | Augmentation | Augmentation of ensure proper functioning of 450 M³ capacity 20 Mtr. staging height RCC Over Head Reservoir of MOYNA Water Supply scheme under Malda Division, P.H.E.Dte. in the District of Malda. | 1127/MD | 21/03/2025 | 45 | HIND CO-OPERATIVA LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 9.24 | 0 | 0 | 0
269 | MALDAH | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15093 | Augmentation | Construction of Boundary Wall at 3rd Tube well site of Moyna Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6202/MD | 09/12/2024 | 45 | M/S /FAIZUL HAQUE BISWAS | 7.17 | 0 | 0 | 100
270 | MALDAH | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15093 | Augmentation | Augmentation of Head Work site Pump House at MOYNA Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1124/MD | 21/03/2025 | 45 | M/S /FAIZUL HAQUE BISWAS | 2.06 | 0 | 0 | 100
271 | MALDAH | Malda Division | Source Augmentation of Moyna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15093 | Augmentation | Augmentation of Pump House-2 at MOYNA Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1125/MD | 21/03/2025 | 45 | M/S /FAIZUL HAQUE BISWAS | 2.02 | 0 | 0 | 100
272 | MALDAH | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15275 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Sabdulpur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004364396 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 6.59 | 0 | 0 | 100
273 | MALDAH | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15275 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Sabdulpur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004364409 | 31/07/2023 | 90 | W.B.S.E.D.C.LTD | 5.14 | 0 | 0 | 100
274 | MALDAH | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15275 | New | Material Requisition To Resource Division | 630/MAAD | 05/04/2023 | 0 | Resource Division | 166.19 | 0 | 0 | 0
275 | MALDAH | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15275 | New | Laying of Distribution System & others allied works at Sukdevpur under Sabdalpur Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte.(Kaliachak-III) | 967/MAAD | 31/05/2023 | 90 | KRISHNENDU DUTTA | 49.45 | 0 | 0 | 0
276 | MALDAH | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15275 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Head Work Site of Sabdalpur Piped Water supply scheme of Southern Sector in the disrtict of Malda(Kaliachak-III). (2nd Call) | 964/MAAD | 31/05/2023 | 45 | ASHIS CONSTRUCTION | 7.66 | 0 | 0 | 100
277 | MALDAH | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15275 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at 2nd Site of Sabdalpur Piped Water supply scheme of Southern Sector in the disrtict of Malda (Kaliachak-III). (2nd Call) | 965/MAAD | 31/05/2023 | 45 | ABHIJIT PAUL | 7.65 | 0 | 0 | 100
278 | MALDAH | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15275 | New | ERECTION OF NEW HTOH LINE FOR SABDALPUR PH1 UNDER GOLAPGANJ CCC UNDER MALDA DISTRICT | BP-2023-24-588 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 3.1 | 0 | 0 | 0
279 | MALDAH | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15275 | New | ERECTION OF HTOH FOR SABDALPUR PH 2 UNDER GOLAPGANJ CCC UNDER MALDA DISTRICT | BP-2023-24-587 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 2.45 | 0 | 0 | 0
280 | MALDAH | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15275 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) at Sabdalpur Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(Kaliachak-lll)(2nd Call) | 984/MAAD | 06/06/2023 | 607 | MOTI RAHAMAN | 168.03 | 0 | 0 | 55
281 | MALDAH | Malda Mechanical | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15275 | New | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Sabdalpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017775) | 2686/MLMD | 11/08/2023 | 879 | DAS ENTERPRISE. | 76.87 | 0 | 0 | 20
282 | MALDAH | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15275 | New | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Sabdulpur Piped Water Supply scheme at Kaliachak-III Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. (3rd Call) | 1708/MAAD | 20/09/2023 | 650 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 222.96 | 0 | 0 | 65
283 | MALDAH | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15275 | New | Laying of Distribution System & others allied works at Sabdalpur under Sabdalpur Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte. (Kaliachak-III) | 1741/MAAD | 26/09/2023 | 522 | M/S ALISA CONSTRUCTION | 64.67 | 0 | 0 | 15
284 | MALDAH | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15275 | New | Construction of Boundary Wall at Head Work Site,2nd tubewell site , C.C road from existing road to Head works Site and Land Development Work for HWS ,Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission(JJM & Jal Swapna), Laying of rising main from Tube Well Site to HWS & including supply of all specials & valves for Sabdulpur Piped Water Supply scheme at Kaliachak-III Development Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 14/MAAD | 03/01/2025 | 60 | M/S AMIT KUMAR GUPTA | 89.63 | 0 | 0 | 0
285 | MALDAH | Malda Ars Area W/S Division | Sabdulpur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15275 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Sabdulpur Piped Water Supply Scheme of Southern Sector under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda.(Kaliachak-III) | 966/MAAD | 31/05/2023 | 487 | ABHIJIT CONSTRUCTION | 5 | 0 | 0 | 100
286 | MALDAH | Malda Division | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15190 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-II) | 760/MD | 17/02/2023 | 30 | J. M. CONSTRUCTION | 5.95 | 0 | 0 | 100
287 | MALDAH | Malda Division | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15190 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-III) | 763/MD | 17/02/2023 | 30 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 8.87 | 0 | 0 | 100
288 | MALDAH | Malda Division | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15190 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 200mm. Dia. x 150mm. Big dia Tube Well 143 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of MALIPAKAR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | 1439/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.2 | 0 | 0 | 100
289 | MALDAH | Malda Division | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15190 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-I) | 1213/MD | 21/03/2023 | 45 | S & G CONSTRUCTION | 20.67 | 0 | 0 | 100
290 | MALDAH | Malda Division | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15190 | Augmentation | Construction of Boundary Wall at 3rd Tube Well site of Malipakar Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 2951/MD | 10/06/2024 | 30 | BINA CONSTRUCTION | 9.07 | 0 | 0 | 0
291 | MALDAH | Malda Division | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15190 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Malipakar Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | 1300/MD | 23/03/2023 | 45 | A.K. AGENCY | 4.18 | 0 | 0 | 98
292 | MALDAH | Malda Mechanical | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15190 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Malipakar, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-394 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 9.61 | 0 | 0 | 0
293 | MALDAH | Malda Mechanical | Source Augmentation of Malipakar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15190 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Malipakar Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte.(TSM/016606) | 2624/MLMD | 10/08/2023 | 601 | SUBRATA KUMAR DAS. | 11.44 | 0 | 0 | 100
294 | MALDAH | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15201 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. All through) Tube Well No - 3 (75.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at DAKSHIN BRINDABANBATI Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | 1431/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 6.72 | 0 | 0 | 100
295 | MALDAH | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15201 | Augmentation | Replacement of 200 mm dia. (all through)Tubewell No:-2 (75 M Deep by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at DAKSHIN BRINDABANBATI Water Supply Scheme of Habibpur Malda Block under Malda Division, PHE Dte. | 4816/MD | 13/09/2024 | 30 | JOY GURU ENTERPRISE | 6.9 | 0 | 0 | 0
296 | MALDAH | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15201 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for DAKSHIN BRINDABANBATI Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | 1161/MD | 20/03/2023 | 555 | M/S JHA CONSTRUCTION | 77.26 | 0 | 0 | 100
297 | MALDAH | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15201 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | 1200/MD | 21/03/2023 | 45 | SURAJIT MONDAL | 4.16 | 0 | 0 | 100
298 | MALDAH | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15201 | Augmentation | Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for DAKSHIN BRINDABANBATI Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | 977/MD | 04/03/2024 | 45 | M/S JHA CONSTRUCTION | 44.56 | 0 | 0 | 85
299 | MALDAH | Malda Mechanical | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15201 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Dakshin Brindabanbati, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-427 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.65 | 0 | 0 | 0
300 | MALDAH | Malda Division | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15201 | Augmentation | Augmentation of Head work site Pump House,PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at DAKSHIN BRINDABANBATI Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1118/MD | 21/03/2025 | 178 | ACHARYYA CONSTRUCTION | 9.3 | 0 | 0 | 0
301 | MALDAH | Malda Mechanical | Source Augmentation of Dakshin Brindabanbati Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15201 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Dakshin Brindabanbati Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/005686) | 2619/MLMD | 10/08/2023 | 541 | KUNDU CONSTRUCTION. | 10.61 | 0 | 0 | 90
302 | MALDAH | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. of Bholaichak ,Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004305025/quot/03 | 29/05/2023 | 90 | W.B.S.E.D.C.LTD | 1.83 | 0 | 0 | 0
303 | MALDAH | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. of Uttar Laxmipur,Southern Zone ,Mothabari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004298515/quot/03 | 19/05/2023 | 90 | W.B.S.E.D.C.LTD | 1.83 | 0 | 0 | 0
304 | MALDAH | Malda Ars Area W/S Division | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Alinagar ) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 239/MAAD | 09/02/2023 | 90 | M/S MOON LIGHT CONSTRUCTION & CO. | 32.97 | 0 | 0 | 100
305 | MALDAH | Malda Ars Area W/S Division | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Bholaichak ) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 240/MAAD | 09/02/2023 | 90 | FUTURE | 32.98 | 0 | 0 | 100
306 | MALDAH | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. of NARAYANPUR Distribution Zone, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004364587 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.32 | 0 | 0 | 100
307 | MALDAH | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. of Alinagar Distribution Zone, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004365949 | 20/07/2023 | 90 | W.B.S.E.D.C.LTD | 1.8 | 0 | 0 | 100
308 | MALDAH | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | W.B.S.E.D.C.LTD Quotation charge of Sattari Distribution Zone, Rathbari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte | 3004371435 | 31/07/2023 | 90 | W.B.S.E.D.C.LTD | 1.22 | 0 | 0 | 100
309 | MALDAH | Malda Ars Area W/S Division | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Sattari ) Distribution Zone of Nothern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda | 242/MAAD | 09/02/2023 | 506 | SUBHAS CHANDRA KESHARI | 32.99 | 0 | 0 | 70
310 | MALDAH | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Sattari Distribution Zone within Malda Arsenic Area Water Supply Scheme (Northern Sector) under Malda Mechanical Division PHE Dte. | 540/MLMD | 22/03/2023 | 180 | M/S P.P. ELECTRICALS | 62.79 | 0 | 0 | 96
311 | MALDAH | Malda Ars Area W/S Division | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Bamongram) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 268/MAAD | 15/02/2023 | 90 | BEE GEE CONSTRUCTION | 29.06 | 0 | 0 | 100
312 | MALDAH | Malda Ars Area W/S Division | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Narayanpur) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 241/MAAD | 09/02/2023 | 90 | M/S PARIMAL DAS | 33.02 | 0 | 0 | 100
313 | MALDAH | Malda Ars Area W/S Division | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | Construction of 150 Cum Capacity Clear Water Reservoir (CWR) as per Departmental Design & Drawing including pipe connection and cost of pipes, specials and High Lift Pump House for Clear Water Reservoir (CWR) at Head Work Site (Uttar Laxmipur ) Distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 243/MAAD | 09/02/2023 | 90 | DISHERY ENGINEERS CO OP SOCIETY LTD. | 32.96 | 0 | 0 | 100
314 | MALDAH | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Utar Laxmipur Distribution Zone within Malda Arsenic Area Water Supply Scheme (Southern Sector) under Malda Mechanical Division PHE Dte. | 454/MLMD | 16/03/2023 | 180 | EASTERN INDIA SALES & SERVICE. | 62.77 | 0 | 0 | 100
315 | MALDAH | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Alinagar Distribution Zone within Malda Arsenic Area Water Supply Scheme (Southern Sector) under Malda Mechanical Division PHE Dte. | 539/MLMD | 22/03/2023 | 180 | DEY ENTERPRISE [HOWRAH] | 62.34 | 0 | 0 | 100
316 | MALDAH | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Bamangram Distribution Zone within Malda Arsenic Area Water Supply Scheme (Southern Sector) under Malda Mechanical Division PHE Dte. | 536/MLMD | 22/03/2023 | 180 | DEY ENTERPRISE.. | 62.79 | 0 | 0 | 100
317 | MALDAH | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | Supply, installation, commissioning and trial operation of Electro-Mechanical and instrumentation components at newly constructed CWR under Narayanpur Distribution Zone within Malda Arsenic Area Water Supply Scheme (Southern Sector) under Malda Mechanical Division PHE Dte. | 537/MLMD | 22/03/2023 | 180 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 62.75 | 0 | 0 | 100
318 | MALDAH | Malda Mechanical | Construction of 6 (six) nos CWR in connection with providing FHTC under surface water based Malda arsenic Area water supply scheme ( Northern & Southern Sector) , SM/15142 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 845/MLMD | 21/02/2024 | 61 | NITAI PANDEY | 0.78 | 0 | 0 | 100
319 | MALDAH | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site at Deonapur Piped Water Supply Scheme at Kaliachak-lll Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 1376/MAAD | 13/07/2023 | 60 | TROYEE | 5 | 0 | 0 | 0
320 | MALDAH | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | Route servey & design for prepration of DPR of Deonapur, Saidpur & Mobarakpur Piped Water Supply Scheme at Kaliachak - III & Kaliachak - II Development Block under Malda Arsenic Area W/S Division, PHE Dte. in the district of Malda. | 1764/MAAD | 30/09/2023 | 15 | FUTURE | 0.99 | 0 | 0 | 100
321 | MALDAH | Malda Mechanical | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Deonapur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004364433 | 31/07/2023 | 90 | W.B.S.E.D.C.LTD | 5.51 | 0 | 0 | 100
322 | MALDAH | Malda Mechanical | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Deonapur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004364419 | 31/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.24 | 0 | 0 | 100
323 | MALDAH | Malda Mechanical | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Deonapur PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004364426 | 31/07/2023 | 90 | W.B.S.E.D.C.LTD | 6.35 | 0 | 0 | 100
324 | MALDAH | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | Material Requisition To Resource Division | 625/MAAD | 05/04/2023 | 0 | Resource Division | 190.2 | 0 | 0 | 0
325 | MALDAH | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | Laying of Distribution System for and other allied works at Ainul Hut under Deonapur Piped Water supply scheme of Kaliachak-III Block of Southern Sector at under Malda Arsenic Area W/S Division, P.H.E. Dte. | 1378/MAAD | 13/07/2023 | 60 | USHA ENTERPRISE | 80.37 | 0 | 0 | 84
326 | MALDAH | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | Laying of Distribution System for and other allied works at Bakrabad Char under Deonapur Piped Water supply scheme of Southern Sector at under Malda Arsenic Area W/S Division, P.H.E. Dte. (Kaliachak-III). | 1379/MAAD | 13/07/2023 | 152 | A. B. CONSTRUCTION | 57.65 | 0 | 0 | 80
327 | MALDAH | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Deonapur Piped Water supply scheme (3RD Site) of Kaliachak -III Block under Malda Arsenic Area water Supply Division in the disrtict of Malda.(2nd Call) | 1382/MAAD | 13/07/2023 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 7.64 | 0 | 0 | 100
328 | MALDAH | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Deonapur Piped Water supply scheme (2ND Site) of Kaliachak -III Block under Malda Arsenic Area water Supply Division in the disrtict of Malda. (2nd Call) | 1381/MAAD | 13/07/2023 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 7.65 | 0 | 0 | 100
329 | MALDAH | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Deonapur Piped Water supply scheme (Head Work Site) of Kaliachak -III Block under Malda Arsenic Area water Supply Division in the disrtict of Malda. | 1377/MAAD | 13/07/2023 | 45 | MD. TALEB ALI | 7.65 | 0 | 0 | 100
330 | MALDAH | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 3rd Tube Well site of Deonapur Piped Water Supply Scheme at Kaliachak-lll Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 1375/MAAD | 13/07/2023 | 107 | MADHUMITA ENTERPRISE | 4.99 | 0 | 0 | 100
331 | MALDAH | Malda Mechanical | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I, II & III and Arsenic Iron Removal Plant at Deonapur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/018102) | 2691/MLMD | 11/08/2023 | 1075 | GHOSH BROTHERS... | 82.34 | 0 | 0 | 0
332 | MALDAH | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) at Deonapur Piped Water supply scheme of Kaliachak-III Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. (2ND Call) | 1991/MAAD | 02/11/2023 | 455 | WATER TECH | 216.09 | 0 | 0 | 75
333 | MALDAH | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | Construction of 700 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Deonapur Piped Water Supply scheme at Kaliachak-III Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 3025/MAAD | 07/12/2023 | 634 | BANIK BROTHERS | 299.38 | 0 | 0 | 60
334 | MALDAH | Malda Ars Area W/S Division | Deonapur Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/18232 | New | Laying of Distribution System for and other allied works at Thakur Das Mandalpara under Deonapur Piped Water supply scheme of Southern Sector at under Malda Arsenic Area W/S Division, P.H.E. Dte. (Kaliachak-III). | 1380/MAAD | 13/07/2023 | 535 | BANIK BROTHERS | 95.3 | 0 | 0 | 100
335 | MALDAH | Malda Division | MORGRAM PWSS , SM/18557 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Morgram Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 5918/MD | 26/11/2024 | 45 | NEOGI ENTERPRISE | 81.8 | 0 | 0 | 0
336 | MALDAH | Malda Division | MORGRAM PWSS , SM/18557 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 8/5 to 8/6 between Malda Court Station (MLFC) to Shingabad Station(SQB) for MORGRAM and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | 4110/MD | 10/10/2023 | 397 | RAY CONSTRUCTION CO. | 20.07 | 0 | 0 | 100
337 | MALDAH | Malda Division | MORGRAM PWSS , SM/18557 | New | Material Requisition To Resource Division | 810/MD | 21/02/2024 | 0 | Resource Division | 66.34 | 0 | 0 | 0
338 | MALDAH | Malda Division | MORGRAM PWSS , SM/18557 | New | Material Requisition To Resource Division | 238/MD | 10/01/2024 | 0 | Resource Division | 16.12 | 0 | 0 | 0
339 | MALDAH | Malda Mechanical | MORGRAM PWSS , SM/18557 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Morgram, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-529 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 12.58 | 0 | 0 | 0
340 | MALDAH | Malda Division | MORGRAM PWSS , SM/18557 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 8/5 to 8/6 between Malda Court Station (MLFC) to Shingabad Station(SQB) for MORGRAM and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | BP-2023-24-603 | 28/03/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 4.28 | 0 | 0 | 0
341 | MALDAH | Malda Mechanical | MORGRAM PWSS , SM/18557 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Morgram, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-530 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 10.78 | 0 | 0 | 0
342 | MALDAH | Malda Division | MORGRAM PWSS , SM/18557 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 8/5 to 8/6 between Malda Court Station (MLFC) to Shingabad Station(SQB) for MORGRAM and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | BP-2023-24-461 | 02/02/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 0.05 | 0 | 0 | 0
343 | MALDAH | Malda Mechanical | MORGRAM PWSS , SM/18557 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Morgram, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte | BP-2023-24-531 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 5.07 | 0 | 0 | 0
344 | MALDAH | Malda Division | MORGRAM PWSS , SM/18557 | New | Formal work order for the work of Implementation of MORGRAM Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3107/MD | 10/08/2023 | 900 | NEOGI ENTERPRISE | 664.04 | 0 | 0 | 70
345 | MALDAH | Malda Mechanical | MORGRAM PWSS , SM/18557 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Morgram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/018419) | 2818/MLMD | 17/08/2023 | 527 | MERCURY ENGINEERING COMPANY. | 36.65 | 0 | 0 | 87
346 | MALDAH | Malda Division | MORGRAM PWSS , SM/18557 | New | Construction of Boundary Wall at head work site of Morgram Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 2989/MD | 11/06/2024 | 416 | NEOGI ENTERPRISE | 25.32 | 0 | 0 | 67
347 | MALDAH | Malda Division | MORGRAM PWSS , SM/18557 | New | Design, Fabrication, Supplying, Installing, Commissioning and 3 (three) months Trial Run of 100 m³/hr. capacity of Iron Elimination Plant (Pressure Type) with provision of polishing unit and Construction of 3.60 mtr. X 3.00 mtr. Blower room of Head Work Site of MORGRAM Water Supply Scheme of Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | 4232/MD | 29/08/2025 | 60 | NEOGI ENTERPRISE | 34.98 | 0 | 0 | 0
348 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11587 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Tulshihatta Zone-II Piped Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | 655/MD | 22/03/2022 | 15 | M/S SOBHA & CO. | 3.27 | 0 | 0 | 1
349 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11587 | New | Material Requisition To Resource Division | 1806/MD | 27/04/2023 | 0 | Resource Division | 17.43 | 0 | 0 | 0
350 | MALDAH | Malda Mechanical | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11587 | New | Supply, installation, commissioning of electro-mechanical components at T/W no. I of Tulshihata (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011277) | 2774/MLMD | 14/08/2023 | 956 | SOVA ENTERPRISE. | 7.87 | 0 | 0 | 88
351 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11587 | New | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep of Tube Well No. 1 at Tulsihatta Zone-II of Harischandrapur - I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 3397/MD | 31/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 10.81 | 0 | 0 | 96
352 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11587 | New | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep of Tube Well No. 2 at Tulsihatta Zone-II of Harischandrapur - I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 3398/MD | 31/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 10.81 | 0 | 0 | 95
353 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11587 | New | Material Requisition To Resource Division | 98/MD | 05/01/2024 | 0 | Resource Division | 6.9 | 0 | 0 | 0
354 | MALDAH | Malda Mechanical | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11587 | New | New service connection at TULSHIHATA PWSS Zone II T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | BP-2023-24-729 | 28/03/2024 | 0 | W.B.S.E.D.C.LTD | 7.47 | 0 | 0 | 0
355 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11587 | New | Formal work order for the work of Augmentation of TULSHIHATTA ZONE-II Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1885/MD | 08/05/2023 | 962 | MANIK CHANDRA SAHA | 276.32 | 0 | 0 | 71
356 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11587 | New | Construction of Boundary Wall at Head Work site of Tulshihata Zone-II Water Supply Scheme under Harischandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 5742/MD | 20/11/2024 | 452 | M/S BABLU ENTERPRISE | 25.14 | 0 | 0 | 75
357 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11587 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Tulshihatta Zone-II Water Supply Scheme under Harishchandrtapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 75 | 13/01/2025 | 45 | M/S BABLU ENTERPRISE | 24.37 | 0 | 0 | 0
358 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11587 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Pump House No. 2 of Tulshihatta Zone-II Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 2266/MD | 21/05/2025 | 45 | M/S GLOBAL ENTERPRISE | 4.34 | 0 | 0 | 100
359 | MALDAH | Malda Mechanical | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- III of Malatipur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008173) | 2228/MLMD | 18/07/2023 | 120 | EMCON. | 12.51 | 0 | 0 | 0
360 | MALDAH | Malda Division | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Material Requisition To Resource Division | 1207/MD | 24/05/2022 | 0 | Resource Division | 0.61 | 0 | 0 | 0
361 | MALDAH | Malda Division | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Material Requisition To Resource Division | 1801/MD | 27/04/2023 | 0 | Resource Division | 0.59 | 0 | 0 | 0
362 | MALDAH | Malda Division | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Soil Investigation and design of substructure for Over Head Reservoirs for MALATIPUR Piped Water Supply Scheme at Chanchal-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. | BP-2022-23-198 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
363 | MALDAH | Malda Division | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Submission of bill for hire charges & HSD & Mobil charges of vehicle No. WB61A/3084 for the month of May-2023. | BP-2023-24-147 | 10/08/2023 | 0 | SHYAMAL KUMAR MAITRA | 0.36 | 0 | 0 | 0
364 | MALDAH | Malda Division | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Bill for reimbursement of cost of Diesel and Mobile in respect of hired Vehicle Car No. WB65C/6570 for the month of July2023. | BP-2023-24-195 | 07/09/2023 | 0 | UTTAM KUMAR GHOSH | 0.4 | 0 | 0 | 0
365 | MALDAH | Malda Division | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Submission of Bill for Hire Charges & HSD & Mobil charges of Vehicle No. - WB61A/3084 for the month of April 2023 | BP-2023-24-115 | 20/07/2023 | 0 | SHYAMAL KUMAR MAITRA | 0.31 | 0 | 0 | 0
366 | MALDAH | Malda Division | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Malatipur Pipe Water Supply Scheme at Chanchal-II Block in the District of Malda under Malda Division P.H.E. Dte. (2ND Call) | 1788/MD | 01/08/2022 | 823 | M/S MAA TARA CONSTRUCTION | 300.02 | 0 | 0 | 85
367 | MALDAH | Malda Mechanical | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components at T/W no. I of Augmentation of Malatipur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008173) | 2264/MLMD | 18/07/2023 | 90 | M/S DYNAMIC ENGINEERS ENTERPRISE.... | 11.11 | 0 | 0 | 68
368 | MALDAH | Malda Mechanical | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- II of Malatipur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008173) | 415/MLMD | 14/03/2023 | 120 | PABITRA MANDAL | 10.28 | 0 | 0 | 100
369 | MALDAH | Malda Division | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Material Requisition To Resource Division | 113/MD | 05/01/2024 | 0 | Resource Division | 8.6 | 0 | 0 | 0
370 | MALDAH | Malda Division | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Material Requisition To Resource Division | 3925/MD | 06/08/2024 | 0 | Resource Division | 8.01 | 0 | 0 | 0
371 | MALDAH | Malda Division | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kharba Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 7811/MD | 11/06/2025 | 60 | HANNAN BUILDERS PVT. LTD. | 130.04 | 0 | 0 | 0
372 | MALDAH | Malda Division | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Formal work order for the work of Construction of 400 M3 Capacity OHR with FHTC (Mouza-Harishpara, Kashipara and Gobindapara) of MALATIPUR Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2914/MD | 31/07/2023 | 180 | DEEP CONSTRUCTION | 183.27 | 0 | 0 | 100
373 | MALDAH | Malda Division | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Malatipur Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | 2879/MD | 17/06/2025 | 60 | SAHA CONSTRUCTION | 56.44 | 0 | 0 | 0
374 | MALDAH | Malda Division | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Erection of Property board related to Jal Jeevan Mission works of Kshempur & Malatipur GP under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | 636/MD | 19/02/2025 | 7 | BIDYUT MAHALDAR | 0.82 | 0 | 0 | 0
375 | MALDAH | Malda Division | AUGMENTATION OF MALATIPUR PWSS , SM/09987 | Augmentation | Augmentation Pump House and Boundary Wall of Malatipur Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2492/MD | 28/05/2025 | 75 | CHARU CONSTRUCTION | 16.65 | 0 | 0 | 0
376 | MALDAH | Malda Division | PERAPUR PWSS , SM/18420 | New | Construction of Boundary Wall at 2nd Tubewell site of Perapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 1260/MD | 15/03/2024 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 7.65 | 0 | 0 | 0
377 | MALDAH | Malda Division | PERAPUR PWSS , SM/18420 | New | Construction of Boundary Wall at Head Work site of Perapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 2923/MD | 10/06/2024 | 600 | GHOSH CONSTRUCTION | 23.72 | 0 | 0 | 70
378 | MALDAH | Malda Division | PERAPUR PWSS , SM/18420 | New | Material Requisition To Resource Division | 812/MD | 21/02/2024 | 0 | Resource Division | 54.03 | 0 | 0 | 0
379 | MALDAH | Malda Division | PERAPUR PWSS , SM/18420 | New | Material Requisition To Resource Division | 234/MD | 10/01/2024 | 0 | Resource Division | 17.65 | 0 | 0 | 0
380 | MALDAH | Malda Division | PERAPUR PWSS , SM/18420 | New | Formal work order for the work of Implementation of PERAPUR Piped Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3016/MD | 08/08/2023 | 813 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 838.31 | 0 | 0 | 10
381 | MALDAH | Malda Mechanical | PERAPUR PWSS , SM/18420 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Perapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015903) | 2565/MLMD | 04/08/2023 | 937 | GHOSH BROTHERS... | 29.98 | 0 | 0 | 0
382 | MALDAH | Malda Division | PERAPUR PWSS , SM/18420 | New | Laying of Distribution of UPVC Pipeline of PERAPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 1214/MD | 25/03/2025 | 310 | BANIK BROTHERS | 66.48 | 0 | 0 | 0
383 | MALDAH | Malda Division | PERAPUR PWSS , SM/18420 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Perapur Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 1612/MD | 30/04/2025 | 120 | MANIK CHANDRA SAHA | 97.83 | 0 | 0 | 0
384 | MALDAH | Malda Mechanical | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani , SM/19225 | Augmentation | Formal work order for Supply, Installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for 8 nos Distribution Zone (OHR SITE) within Manikchak Block under Augmentation of Malda Arsenic Area W/S scheme (Northern Sector) under Malda Mechanical Division, PHE Dte. | 3852/MLMD | 03/12/2024 | 180 | MACHINE SUPPLIERS SYNDICATE (P) LTD. | 341.1 | 0 | 0 | 0
385 | MALDAH | Malda Mechanical | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani , SM/19225 | Augmentation | Formal work order for Supply, Installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for 7 nos Distribution Zone (OHR SITE) within Kaliachak Block-I under Augmentation of Malda Arsenic Area W/S scheme (Northern Sector) under Malda Mechanical Division, PHE Dte. | 4083/MLMD | 16/12/2024 | 180 | CREATIVE WATER & PROCESS TECH. PVT. LTD. | 298.3 | 0 | 0 | 0
386 | MALDAH | Malda Mechanical | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani , SM/19225 | Augmentation | Formal work order for Supply, Installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for 5 nos Distribution Zone (OHR SITE) within Englishbazar Block under Augmentation of Malda Arsenic Area W/S scheme (Northern Sector) under Malda Mechanical Division, PHE Dte. | 4082/MLMD | 16/12/2024 | 180 | EASTERN INDIA SALES & SERVICE. | 212.97 | 0 | 0 | 0
387 | MALDAH | Malda Mechanical | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani , SM/19225 | Augmentation | Formal work order for Supply, Installation & commissioning of Secondary Gaseous Chlorination Arrangement and other allied works for 18 nos Distribution Zone (OHR SITE) within Kaliachak Block-III under Augmentation of Malda Arsenic Area W/S scheme (Southern Sector) under Malda Mechanical Division, PHE Dte. | 3894/MLMD | 05/12/2024 | 180 | ORIENTAL ENGINEERING CO. | 765.98 | 0 | 0 | 0
388 | MALDAH | Malda Mechanical | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani , SM/19225 | Augmentation | Formal work order for Various electro-mechanical works for existing High Lift pumping station at Dariapur under Augmentation of Malda Arsenic Area W/S scheme (Southern Sector) under Malda Mechanical Division, PHE Dte. | 3911/MLMD | 06/12/2024 | 180 | ALPHA ENTERPRISE. | 153.89 | 0 | 0 | 0
389 | MALDAH | Malda Mechanical | Additional Capital Cost Estimate for mechanical/ electrical components for Augmentation of Surface based piped water supply scheme under Northern and Southern Sector of Manikchak, English Bazar, Kaliachak -I, II, III block, dist. Malda under Malda Mechani , SM/19225 | Augmentation | Supply, Installation & commissioning of Secondary gaseous chlorination arrangement and other allied works for 2 nos Distribution Zone (OHR site) within Manikchak and English bazar Block under Augmentation of Malda Arsenic Area Water Supply Scheme (Northern Sector), under Malda Mechanical Division, PHE Dte. | 1084/MLMD | 12/02/2025 | 90 | SHREE BISHNU CONSTRUCTION | 81.51 | 0 | 0 | 0
390 | MALDAH | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 88.29 | 0 | 0 | 0
391 | MALDAH | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | Bill for reimbursement of cost of Diesel and mobil in respect of hired vehicle Ambassador Car No.- WB-65/D2727 For the month of January, February and March 2023. |  | 22/08/2023 | 0 | ARUN KUMAR DAS | 0.96 | 0 | 0 | 0
392 | MALDAH | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | Construction of Boundary Wall at 3rd Tube Well site of Kharba Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 2947/MD | 10/06/2024 | 30 | M/S GHOSH ENTERPRISE | 8.66 | 0 | 0 | 0
393 | MALDAH | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | Construction of Boundary Wall at Head Work site of Kharba Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 3040/MD | 13/06/2024 | 30 | SOVAN KUMAR ROY | 24.8 | 0 | 0 | 0
394 | MALDAH | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 160 Mtr. Deep Big dia Tube well (2 Nos.) at KHARBA Water Supply Scheme under Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1140/MD | 20/03/2023 | 30 | DUTTA ENTERPRISE | 21.12 | 0 | 0 | 95
395 | MALDAH | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep at Head Work Site at Kharba under Chanchal-I under Malda Division, PHE Dte, Govt. of West Bengal. | 275/MD | 11/01/2024 | 45 | A. L. ENGINEERING SOLUTION | 10.64 | 0 | 0 | 95
396 | MALDAH | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | Material Requisition To Resource Division | 86/MD | 05/01/2024 | 0 | Resource Division | 16.23 | 0 | 0 | 0
397 | MALDAH | Malda Mechanical | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | New service connection at kharba w/s supply sch. under EE/MLMD PHE DTE Dist. malda (chanchal c.c.c) | BP-2023-24-561 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 5.27 | 0 | 0 | 0
398 | MALDAH | Malda Mechanical | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | New service connection at KHARBA PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Chanchal c c c) | BP-2024-25-473 | 28/08/2024 | 0 | W.B.S.E.D.C.LTD | 4.6 | 0 | 0 | 0
399 | MALDAH | Malda Mechanical | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | New service connection at KHARBA PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( CHANCHAL c c c) | BP-2024-25-472 | 28/08/2024 | 0 | W.B.S.E.D.C.LTD | 4.04 | 0 | 0 | 0
400 | MALDAH | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | Formal work order for the work of Laying distribution pipe line of KHARBA and it's adjoining mouzas Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte. Govt of West Bengal. | 2033/MD | 19/05/2023 | 90 | HANNAN BUILDERS PVT. LTD. | 430.15 | 0 | 0 | 80
401 | MALDAH | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | Formal work order for the work of Construction of 750 M3 Capacity OHR with Soil Investigation and FHTC of KHARBA Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2020/MD | 18/05/2023 | 954 | SOVAN KUMAR ROY | 355.8 | 0 | 0 | 40
402 | MALDAH | Malda Mechanical | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Augmentation of Kharba Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011882) | 2223/MLMD | 18/07/2023 | 924 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 42.98 | 0 | 0 | 90
403 | MALDAH | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of KHARBA Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte. | 1128/MD | 20/03/2023 | 45 | M/S FOUR STAR CONSTRUCTION | 4.2 | 0 | 0 | 100
404 | MALDAH | Malda Division | KHARBA PIPED WATER SUPPLY SCHEME. , SM/13793 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Kharba PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 274/MD | 11/01/2024 | 45 | SABITA CONSTRUCTION COMPANY | 4.17 | 0 | 0 | 98
405 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of NAGHARIA Water Supply Scheme , SM/06849 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of NAGHARIA Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1120/MAAD | 09/11/2020 | 45 | MILLENNIUM ENTERPRISE | 70.6 | 53.73 | 100 | 1
406 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of NAGHARIA Water Supply Scheme , SM/06849 | Retrofitting | Transfer of funds from the account of Implementing Agencies to Singles Nodal Account (Escrow Account) under Jal Jeevan Mission. | 580 | 29/03/2022 | 0 | JAL JEEVAN MISSION WEST BENGAL ESCROW ACCOUNT | 23.94 | 0 | 0 | 0
407 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of NAGHARIA Water Supply Scheme , SM/06849 | Retrofitting | Collection of House Hold Details at prescribed format in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Nagharia Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 88/MAAD | 15/01/2021 | 30 | M/S PARIMAL DAS | 0.52 | 0.52 | 100 | 0
408 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of HARDAMNAGAR Water Supply Scheme , SM/06862 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Hardamnagar Water Supply Scheme at Harishchandrapur-II under Malda Division, PHE Dte. | 2380/MD | 13/08/2021 | 30 | PARIJAT RAY | 22.39 | 0 | 0 | 1
409 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of HARDAMNAGAR Water Supply Scheme , SM/06862 | Retrofitting | Augmentation work of Pump House and Boundary Wall of Hardamnagar Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1031/MD | 18/03/2025 | 303 | ASHIS CONSTRUCTION | 17.22 | 0 | 0 | 0
410 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Jote Basanta, Laxmighat water supply scheme at English Bazar Block and Gopalpur Water Supply Scheme at Manikchak Block , SM/08283 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JOTE BASANTA Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 207/MAAD | 08/02/2021 | 60 | M/S PARIMAL DAS | 112.64 | 103.43 | 92.68 | 1
411 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Jote Basanta, Laxmighat water supply scheme at English Bazar Block and Gopalpur Water Supply Scheme at Manikchak Block , SM/08283 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of LAKSHMIGHAT Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 206/MAAD | 08/02/2021 | 60 | BANIK BROTHERS | 107.79 | 90.47 | 84.19 | 1
412 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Jote Basanta, Laxmighat water supply scheme at English Bazar Block and Gopalpur Water Supply Scheme at Manikchak Block , SM/08283 | Retrofitting | Collection of House Hold Details at prescribed format in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Gopalpur,Jote Basanta,Lakshmighat Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 87/MAAD | 15/01/2021 | 30 | BINA CONSTRUCTION | 2.99 | 2.54 | 85 | 1
413 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Jote Basanta, Laxmighat water supply scheme at English Bazar Block and Gopalpur Water Supply Scheme at Manikchak Block , SM/08283 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Pal Para, Budia of Jote Basanta Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 2033/MAAD | 29/12/2021 | 30 | M/S PARIMAL DAS | 3.98 | 0 | 0 | 1
414 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Jote Basanta, Laxmighat water supply scheme at English Bazar Block and Gopalpur Water Supply Scheme at Manikchak Block , SM/08283 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Budia Part of Jote Basanta Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 364/MAAD | 07/03/2022 | 30 | M/S PARIMAL DAS | 1.68 | 0 | 0 | 1
415 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Jote Basanta, Laxmighat water supply scheme at English Bazar Block and Gopalpur Water Supply Scheme at Manikchak Block , SM/08283 | Retrofitting | Construction of Road Crossing for PVC pipe line at Laxmighat Water Supply Scheme to provide FHTC under Malda Arsenic Area W/S Division P.H.E Dte. | 957/MAAD | 11/05/2022 | 15 | BANIK BROTHERS | 1.99 | 0 | 0 | 1
416 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Jote Basanta, Laxmighat water supply scheme at English Bazar Block and Gopalpur Water Supply Scheme at Manikchak Block , SM/08283 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOPALPUR Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 828/MAAD | 04/06/2021 | 60 | MILLENNIUM ENTERPRISE | 170.16 | 0 | 0 | 1
417 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Jote Basanta, Laxmighat water supply scheme at English Bazar Block and Gopalpur Water Supply Scheme at Manikchak Block , SM/08283 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Jote Basanta Water Supply Scheme ( Habitation Kachari Para, Tiyor Para, Colony ,Purba Para, Lalchand Para, village Jote Basanta) at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 2036/MAAD | 16/11/2022 | 45 | BINA CONSTRUCTION | 7.44 | 0 | 0 | 1
418 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and Jal Swapna) under command area of Jote Basanta, Laxmighat water supply scheme at English Bazar Block and Gopalpur Water Supply Scheme at Manikchak Block , SM/08283 | Retrofitting | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2023 to 31.12.2023) | 2294/MAAD | 28/12/2022 | 365 | M/S PARIMAL DAS | 1.73 | 0 | 0 | 100
419 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo , SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Lalapur Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1649/MAAD | 03/11/2021 | 45 | GOUTAM SAHA | 14.69 | 0 | 0 | 1
420 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo , SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mahabbatpur (East Zone) Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1652/MAAD | 03/11/2021 | 45 | S. R. CONSTRUCTION | 10 | 0 | 0 | 1
421 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo , SM/08760 | Retrofitting | Laying of HDPE pipe 20mm dia at Lalapur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 969/MAAD | 11/05/2022 | 15 | GOUTAM SAHA | 3.39 | 0 | 0 | 1
422 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo , SM/08760 | Retrofitting | Laying of HDPE pipe 20mm dia alongwith providing FHTCat Mahabbatpur East Zone water supply Scheme of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 968/MAAD | 11/05/2022 | 15 | S. R. CONSTRUCTION | 3.73 | 0 | 0 | 1
423 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo , SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Itakhola Water Supply Scheme (Mouza- Itakhola, Habitation- Tekra) at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 736/MAAD | 19/04/2022 | 30 | DHRITIPALI | 2.34 | 0 | 0 | 1
424 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo , SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Talimnagar Zone-II Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1724/MAAD | 18/11/2021 | 30 | S & G CONSTRUCTION | 3.82 | 0 | 0 | 1
425 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo , SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Itakhola Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1651/MAAD | 03/11/2021 | 45 | DHRITIPALI | 7.16 | 0 | 0 | 1
426 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo , SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mahabbatpur (West Zone) Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1653/MAAD | 03/11/2021 | 60 | USHA ENTERPRISE | 39.32 | 0 | 0 | 1
427 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo , SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Barachak Water Supply Scheme (Village- Parbatya) With pipe line at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1832/MAAD | 27/09/2022 | 45 | DHRITIPALI | 4.22 | 0 | 0 | 1
428 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo , SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Barachak water Supply Scheme in Gopinathpur villages within English Bazar Block in Malda District under Malda Arsenic Area Water Supply Division PHE Dte. | 1650/MAAD | 03/11/2021 | 45 | UTTAM KUMAR GHOSH | 19.1 | 0 | 0 | 1
429 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo , SM/08760 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Itakhola Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1651/MAAD | 03/11/2021 | 45 | DHRITIPALI | 10 | 0 | 0 | 1
430 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo , SM/08760 | Retrofitting | Material Requisition To Resource Division | 194/MAAD | 11/02/2022 | 0 | Resource Division | 14.54 | 0 | 0 | 0
431 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with quality improvement by installation of AIRP/IEP under command area of Barachak,Itakhola,Lalapur Water Supply Scheme at English Bazar Block and Talimnagar Zone-II, Mahabbatpur (East Zo , SM/08760 | Retrofitting | Service connection Charges/ Security Deposit for Itakhola AIRP of Itakhola distribution zone under Malda Arsenic Area W/S Division. | C092441964963 | 26/09/2024 | 0 | W.B.S.E.D.C.LTD | 3.81 | 0 | 0 | 0
432 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Niyamatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar , SM/09589 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Niamatpur Mouza of Niyamatpur Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1762/MAAD | 24/11/2021 | 60 | MANIK CH. SAHA | 37.54 | 0 | 0 | 1
433 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Niyamatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar , SM/09589 | Retrofitting | Providing Functional Household Tap Connection (FHTC) by providing branch line in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Niyamatpur ( From health sub centre towards SSK) of Niyamatpur Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte.. | 1865/MAAD | 28/09/2022 | 45 | SUDIP DEY | 4.14 | 0 | 0 | 1
434 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Niyamatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar , SM/09589 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
435 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ADHNA Water Supply Scheme , SM/06850 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | 522/MSD | 31/12/2021 | 2191 | UTTAM KUMAR GHOSH | 0.86 | 0 | 0 | 0
436 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ADHNA Water Supply Scheme , SM/06850 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of ADHNA Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | 2153/MD | 16/09/2020 | 30 | TARUN KUMAR DEY | 47.5 | 24.59 | 78.77 | 0
437 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ADHNA Water Supply Scheme , SM/06850 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Adhna Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 842/MD | 06/03/2025 | 346 | M/S /FAIZUL HAQUE BISWAS | 30.31 | 0 | 0 | 0
438 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ADHNA Water Supply Scheme , SM/06850 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Adhna Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 3363/MD | 29/08/2023 | 45 | UNITED FRIENDS UNEMPLOYED ENGG CO-OPE SOCEITY LTD | 10.1 | 0 | 0 | 100
439 | MALDAH | Malda Division | INSTALLATION OF 118 nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-CHAKNAGAR,SALAIDANGA,SAHAJADPUR,GAZOLE-I,GAZOLE-II & BAHIRGACHHI -II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE , SM/10244 | Anganwadi | Acceptance cum formal work order for Supplying G.I. pipe strainer for installation of CWPP at AWC of G.P.- Chaknagar, Salaidanga, Sahajadpur, Gazole-I, Gazole-II & Bahirgachhi-II in Gazole Dev. Block at Mangalbari Stack Yard under Malda Division, PHE Dte.(Part-II) | 1435/MD | 20/06/2022 | 15 | SAUDAGAR (INDIA) | 20.75 | 0 | 0 | 0
440 | MALDAH | Malda Division | INSTALLATION OF 118 nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-CHAKNAGAR,SALAIDANGA,SAHAJADPUR,GAZOLE-I,GAZOLE-II & BAHIRGACHHI -II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE , SM/10244 | Anganwadi | Material Requisition To Resource Division | 528/MD | 03/03/2022 | 0 | Resource Division | 72.38 | 0 | 0 | 0
441 | MALDAH | Malda Division | INSTALLATION OF 118 nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-CHAKNAGAR,SALAIDANGA,SAHAJADPUR,GAZOLE-I,GAZOLE-II & BAHIRGACHHI -II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE , SM/10244 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) at different Anganwadi Centres (AWCs) of G.P.- Chaknagar, Salaidanga, Sahajadpur, Gazole-I, Gazole-II & Bahirgachhi-II in Gazole Dev. Block, Malda under Malda Division, PHE Dte. | 1135/MD | 20/05/2022 | 120 | M/S S. DAS & ENTERPRISE | 675.32 | 0 | 0 | 80
442 | MALDAH | Malda Division | INSTALLATION OF 96 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF OLD MALDA DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE , SM/10247 | Anganwadi | Acceptance cum formal work order for Supplying G.I. pipe strainer for installation of CWPP at AWC of Old Malda Dev. Block at Mangalbari Stack Yard under Malda Division, PHE Dte. | 1433/MD | 20/06/2022 | 15 | M/S S. S. ENTERPRISE | 17.19 | 0 | 0 | 0
443 | MALDAH | Malda Division | INSTALLATION OF 96 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF OLD MALDA DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE , SM/10247 | Anganwadi | Material Requisition To Resource Division | 521/MD | 03/03/2022 | 0 | Resource Division | 4.49 | 0 | 0 | 0
444 | MALDAH | Malda Division | INSTALLATION OF 96 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF OLD MALDA DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE , SM/10247 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) at different Anganwadi Centres (AWCs) of Old Malda Dev. Block, Malda under Malda Division, PHE Dte. | 1512/MD | 29/06/2022 | 120 | M/S S. S. ENTERPRISE | 549.41 | 0 | 0 | 94
445 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 no) of Chanchal-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10387 | School | Material Requisition To Resource Division | 726/MD | 25/03/2022 | 0 | Resource Division | 72.33 | 0 | 0 | 0
446 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 no) of Chanchal-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10387 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Bhagabanpur & Kharba GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | 479/MD | 07/02/2023 | 75 | DUTTA ENTERPRISE | 188.68 | 0 | 0 | 60
447 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 no) of Chanchal-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10387 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Chanchal & Mahanandapur GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | 478/MD | 07/02/2023 | 75 | DUTTA ENTERPRISE | 161.73 | 0 | 0 | 60
448 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 no) of Chanchal-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10387 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Mokdampur & Koligram GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | 816/MD | 20/02/2023 | 75 | WIST WATER SOLUTIONS | 105.41 | 0 | 0 | 75
449 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 no) of Chanchal-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10387 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Matiharpur & Alihanda GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | 42/MD | 16/01/2023 | 563 | MILLENNIUM ENTERPRISR | 113.21 | 0 | 0 | 100
450 | MALDAH | Malda Division | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. , SM/12267 | New | Material Requisition To Resource Division | 3042/MD | 12/12/2022 | 0 | Resource Division | 26.32 | 0 | 0 | 0
451 | MALDAH | Malda Division | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. , SM/12267 | New | Material Requisition To Resource Division | 1608/MD | 11/04/2023 | 0 | Resource Division | 15.61 | 0 | 0 | 0
452 | MALDAH | Malda Division | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. , SM/12267 | New | Sinking of 200mm. (all through) Big dia. Tube Well of 180m Deep at Head Work Site by D.R. Rig Method using P.V.C. pipe including supply of materials at GOCHIYA Water Supply Scheme of Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 6044/MD | 02/12/2024 | 45 | A. L. ENGINEERING SOLUTION | 10.84 | 0 | 0 | 0
453 | MALDAH | Malda Mechanical | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. , SM/12267 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of GOCHIYA PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-443 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.79 | 0 | 0 | 0
454 | MALDAH | Malda Mechanical | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. , SM/12267 | New | New service connection at GOCHIYA Pwss pH NO II Under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) | BP-2023-24-664 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 9.63 | 0 | 0 | 0
455 | MALDAH | Malda Division | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. , SM/12267 | New | Formal work order for the work of Implementation of GOCHIYA Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2319/MD | 08/06/2023 | 365 | M/S PARIMAL DAS | 508.24 | 0 | 0 | 35
456 | MALDAH | Malda Division | GOCHIYA PWSS , Harischandrapur_I Block in Malda Division. , SM/12267 | New | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution pipeline in connection with Jal Jeevan Mission (JJM) at Gochiya Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 1259/MD | 28/03/2025 | 45 | M/S PARIMAL DAS | 48.34 | 0 | 0 | 0
457 | MALDAH | Malda Mechanical | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12312 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Altor, Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004279849 | 04/05/2023 | 90 | W.B.S.E.D.C.LTD | 2.87 | 0 | 0 | 100
458 | MALDAH | Malda Division | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12312 | Augmentation | Material Requisition To Resource Division | 2408/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0 | 0
459 | MALDAH | Malda Division | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12312 | Augmentation | Material Requisition To Resource Division | 2404/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0 | 0
460 | MALDAH | Malda Division | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12312 | Augmentation | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200mm. Dia ) Tube Well no-3 ( 160 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at ALTOR Water Supply Scheme of Gazole Block .under Malda Division P.H.E Dte in the District of Malda. | 2509/MD | 03/11/2022 | 30 | A. D. D. ASSOCIATES | 9.91 | 0 | 0 | 100
461 | MALDAH | Malda Division | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12312 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of ALTOR Water Supply Scheme of Gazole Block .under Malda Division P.H.E Dte in the District of Malda. | 2550/MD | 03/11/2022 | 45 | SUDEB KARMAKAR | 6.69 | 0 | 0 | 100
462 | MALDAH | Malda Mechanical | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12312 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Altore Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012799) | 2310/MLMD | 26/07/2023 | 120 | JIBON GHOSH. | 11.54 | 0 | 0 | 100
463 | MALDAH | Malda Division | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12312 | Augmentation | Construction of Boundary Wall at 2nd Tube well site of Altore Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6204/MD | 09/12/2024 | 310 | MOSTAKIM ANSARI | 7.17 | 0 | 0 | 0
464 | MALDAH | Malda Division | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12312 | Augmentation | Augmentation of ensure proper functioning of 450 M³ capacity 20 Mtr. staging height RCC Over Head Reservoir of ALTOR Water Supply scheme under Malda Division, P.H.E.Dte. in the District of Malda. | 1128/MD | 21/03/2025 | 45 | GOBINDA ENTERPRISE | 8.15 | 0 | 0 | 0
465 | MALDAH | Malda Division | Source Augmentation of Altor Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12312 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for ALTOR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | 2507/MD | 03/11/2022 | 475 | M/S STAR INDIA CONSTRUTION | 40.04 | 0 | 0 | 1
466 | MALDAH | Malda Mechanical | JIBJALSAR Piped Water Supply Scheme , SM/12182 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Jibjalsar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013490) | 2574/MLMD | 04/08/2023 | 120 | PABITRA MANDAL | 11.8 | 0 | 0 | 70
467 | MALDAH | Malda Division | JIBJALSAR Piped Water Supply Scheme , SM/12182 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 180 Mtr. Deep Big dia Tube well (1 No) at JIBJALSAR Water Supply Scheme under Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 927/MD | 27/02/2023 | 30 | DUTTA ENTERPRISE | 10.71 | 0 | 0 | 100
468 | MALDAH | Malda Mechanical | JIBJALSAR Piped Water Supply Scheme , SM/12182 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of JIBJALSAR PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004387480 | 11/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.55 | 0 | 0 | 100
469 | MALDAH | Malda Division | JIBJALSAR Piped Water Supply Scheme , SM/12182 | New | Material Requisition To Resource Division | 1614/MD | 11/04/2023 | 0 | Resource Division | 0.9 | 0 | 0 | 0
470 | MALDAH | Malda Division | JIBJALSAR Piped Water Supply Scheme , SM/12182 | New | Material Requisition To Resource Division | 1580 | 10/04/2023 | 0 | Resource Division | 0.9 | 0 | 0 | 0
471 | MALDAH | Malda Division | JIBJALSAR Piped Water Supply Scheme , SM/12182 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of JIBJALSAR Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | 1126/MD | 20/03/2023 | 45 | BANIK BROTHERS | 6.57 | 0 | 0 | 100
472 | MALDAH | Malda Division | JIBJALSAR Piped Water Supply Scheme , SM/12182 | New | Material Requisition To Resource Division | 251/MD | 10/01/2024 | 0 | Resource Division | 1.03 | 0 | 0 | 0
473 | MALDAH | Malda Division | JIBJALSAR Piped Water Supply Scheme , SM/12182 | New | Acceptance cum formal work order for Implementation of JIBJALSAR Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. | 195/MD | 19/01/2023 | 1166 | ACHARYYA CONSTRUCTION | 25 | 0 | 0 | 80
474 | MALDAH | Malda Division | JIBJALSAR Piped Water Supply Scheme , SM/12182 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Jibjalsar Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 659/MD | 08/02/2024 | 631 | ACHARYYA CONSTRUCTION | 7.36 | 0 | 0 | 0
475 | MALDAH | Malda Division | BETAHAL Piped Water Supply Scheme , SM/12191 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of BETAHAL Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | 2701/MD | 17/11/2022 | 30 | ASHIS CONSTRUCTION | 9.2 | 0 | 0 | 1
476 | MALDAH | Malda Mechanical | BETAHAL Piped Water Supply Scheme , SM/12191 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Betahal PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004232800 | 17/05/2023 | 90 | W.B.S.E.D.C.LTD | 4.96 | 0 | 0 | 0
477 | MALDAH | Malda Division | BETAHAL Piped Water Supply Scheme , SM/12191 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 23.84 | 0 | 0 | 0
478 | MALDAH | Malda Division | BETAHAL Piped Water Supply Scheme , SM/12191 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Betahal Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 3444/MD | 11/07/2024 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 18.55 | 0 | 0 | 0
479 | MALDAH | Malda Division | BETAHAL Piped Water Supply Scheme , SM/12191 | New | Construction of Boundary Wall at 2nd Tube Well site of Betahal Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 3953/MD | 07/08/2024 | 45 | M/S ALISA CONSTRUCTIION | 7.26 | 0 | 0 | 0
480 | MALDAH | Malda Division | BETAHAL Piped Water Supply Scheme , SM/12191 | New | Material Requisition To Resource Division | 95/MD | 05/01/2024 | 0 | Resource Division | 7.39 | 0 | 0 | 0
481 | MALDAH | Malda Division | BETAHAL Piped Water Supply Scheme , SM/12191 | New | Material Requisition To Resource Division | 3916/MD | 06/08/2024 | 0 | Resource Division | 0.86 | 0 | 0 | 0
482 | MALDAH | Malda Mechanical | BETAHAL Piped Water Supply Scheme , SM/12191 | New | New service connection at Bethal PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | BP-2024-25-202 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 8.73 | 0 | 0 | 0
483 | MALDAH | Malda Division | BETAHAL Piped Water Supply Scheme , SM/12191 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sahara Bahara Mouza of Betahal Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 54 | 08/01/2025 | 45 | M I CONSTRUCTION | 7.44 | 0 | 0 | 0
484 | MALDAH | Malda Division | BETAHAL Piped Water Supply Scheme , SM/12191 | New | Laying of Distribution of UPVC Pipeline of BETAHAL Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 545/MD | 31/01/2024 | 517 | FUTURE | 88.28 | 0 | 0 | 80
485 | MALDAH | Malda Division | Augmentation of Jatradanga Piped water supply scheme , SM/12734 | Augmentation | Acceptance cum formal work order for Construction of 3.60 Mtr. X 3.00 Mtr. Bore Hole Pump House for Tube Well No. 3 of JATRADANGA Water Supply Scheme under Malda Division, PHE Dte. | 3228MD | 28/12/2020 | 60 | M/S A. B. CONSTRUCTION | 4.74 | 0 | 0 | 1
486 | MALDAH | Malda Division | Augmentation of Jatradanga Piped water supply scheme , SM/12734 | Augmentation | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of JATRADANGA Piped Water Supply Scheme under Malda Division, PHE Dte. | 2695/MD | 09/09/2021 | 7 | RADIANT | 1.25 | 0 | 0 | 1
487 | MALDAH | Malda Division | Augmentation of Jatradanga Piped water supply scheme , SM/12734 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of JATRADANGA Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | 1133/MD | 20/03/2023 | 45 | M/S KAMALA ENTERPRISE | 4.16 | 0 | 0 | 0
488 | MALDAH | Malda Mechanical | Augmentation of Jatradanga Piped water supply scheme , SM/12734 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II of Augmentation of Jatradanga Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/010498) | 2221/MLMD | 18/07/2023 | 90 | JOY MAA SANTOSHI ENTERPRISE. | 6.42 | 0 | 0 | 0
489 | MALDAH | Malda Division | Augmentation of Jatradanga Piped water supply scheme , SM/12734 | Augmentation | Material Requisition To Resource Division | 1809/MD | 27/04/2023 | 0 | Resource Division | 6.98 | 0 | 0 | 0
490 | MALDAH | Malda Division | Augmentation of Jatradanga Piped water supply scheme , SM/12734 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 66.49 | 0 | 0 | 0
491 | MALDAH | Malda Division | Augmentation of Jatradanga Piped water supply scheme , SM/12734 | Augmentation | Formal work order for the work of Augmentation of JATRADANGA Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2830/MD | 25/07/2023 | 270 | M/S KUNDU CONSTRUCTION | 171.22 | 0 | 0 | 53
492 | MALDAH | Malda Division | Augmentation of Jatradanga Piped water supply scheme , SM/12734 | Augmentation | Additional Laying, Road restroration and Providing Functional Household Tap Connection (FHTC) at Jatradanga Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 5271/MD | 01/10/2024 | 81 | M/S KUNDU CONSTRUCTION | 28.27 | 0 | 0 | 100
493 | MALDAH | Malda Division | PARO PWSS , SM/12195 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 12.8 | 0 | 0 | 0
494 | MALDAH | Malda Division | PARO PWSS , SM/12195 | New | Material Requisition To Resource Division | 109/MD | 05/01/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
495 | MALDAH | Malda Division | PARO PWSS , SM/12195 | New | Material Requisition To Resource Division | 3994/MD | 08/08/2024 | 0 | Resource Division | 7.39 | 0 | 0 | 0
496 | MALDAH | Malda Mechanical | PARO PWSS , SM/12195 | New | New service connection at PARO PWSS T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | BP-2024-25-576 | 28/11/2024 | 0 | W.B.S.E.D.C.LTD | 11.55 | 0 | 0 | 0
497 | MALDAH | Malda Mechanical | PARO PWSS , SM/12195 | New | New service connection at PARO PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | BP-2024-25-575 | 28/11/2024 | 0 | W.B.S.E.D.C.LTD | 4.05 | 0 | 0 | 0
498 | MALDAH | Malda Division | PARO PWSS , SM/12195 | New | Formal work order for the work of Implementation of PARO Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2873/MD | 26/07/2023 | 980 | VISCOUS ENGINEERS PVT. LTD. | 228.95 | 0 | 0 | 72
499 | MALDAH | Malda Division | PARO PWSS , SM/12195 | New | Laying of Distribution of UPVC Pipeline of PARO Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 598/MD | 06/02/2024 | 60 | MD. TALEB ALI | 64.62 | 0 | 0 | 80
500 | MALDAH | Malda Division | PARO PWSS , SM/12195 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Paro Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 4994/MD | 27/09/2024 | 171 | S. R. CONSTRUCTION | 52.14 | 0 | 0 | 0
501 | MALDAH | Malda Division | MABARAKPUR PWSS , SM/12197 | New | Material Requisition To Resource Division | 3045/MD | 12/12/2022 | 0 | Resource Division | 24.43 | 0 | 0 | 0
502 | MALDAH | Malda Mechanical | MABARAKPUR PWSS , SM/12197 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of MABARAKPUR PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004375733 | 01/09/2023 | 90 | W.B.S.E.D.C.LTD | 5.77 | 0 | 0 | 100
503 | MALDAH | Malda Mechanical | MABARAKPUR PWSS , SM/12197 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. IV of MABARAKPUR PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004375650 | 01/09/2023 | 90 | W.B.S.E.D.C.LTD | 3.11 | 0 | 0 | 100
504 | MALDAH | Malda Division | MABARAKPUR PWSS , SM/12197 | New | Material Requisition To Resource Division | 1619/MD | 11/04/2023 | 0 | Resource Division | 16.07 | 0 | 0 | 0
505 | MALDAH | Malda Division | MABARAKPUR PWSS , SM/12197 | New | Construction of Boundary Wall at 2nd Tube Well site of Mabarakpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 2943/MD | 10/06/2024 | 30 | SUBHAS CHANDRA KESHARI | 8.39 | 0 | 0 | 0
506 | MALDAH | Malda Division | MABARAKPUR PWSS , SM/12197 | New | Construction of Boundary Wall at Head Work site of Mabarakpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 3036/MD | 13/06/2024 | 30 | SUBHAS CHANDRA KESHARI | 25.86 | 0 | 0 | 0
507 | MALDAH | Malda Division | MABARAKPUR PWSS , SM/12197 | New | Material Requisition To Resource Division | 774/MD | 20/02/2024 | 0 | Resource Division | 5.54 | 0 | 0 | 0
508 | MALDAH | Malda Mechanical | MABARAKPUR PWSS , SM/12197 | New | New service connection at MABARAKPURPUR Pwss pH NO II EE/MLMD PHE DTE DIST. Malda.( kushida c c c) | BP-2023-24-659 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 7.69 | 0 | 0 | 0
509 | MALDAH | Malda Mechanical | MABARAKPUR PWSS , SM/12197 | New | New service connection at MABARAKPUR Pwss pH NO I under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) | BP-2023-24-660 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.44 | 0 | 0 | 0
510 | MALDAH | Malda Division | MABARAKPUR PWSS , SM/12197 | New | Formal work order for the work of Implementation of MOBARAKPUR Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte. | 2035/MD | 19/05/2023 | 1048 | SUBHAS CHANDRA KESHARI | 501.69 | 0 | 0 | 64
511 | MALDAH | Malda Mechanical | MABARAKPUR PWSS , SM/12197 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Mabarakpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012922) | 2323/MLMD | 26/07/2023 | 811 | M/S. KUNDU CONSTRACTION | 28.45 | 0 | 0 | 57
512 | MALDAH | Malda Division | MABARAKPUR PWSS , SM/12197 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mabarakpur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 73 | 13/01/2025 | 45 | SUBHAS CHANDRA KESHARI | 38.17 | 0 | 0 | 0
513 | MALDAH | Malda Division | MABARAKPUR PWSS , SM/12197 | New | Dedicated/Parallel Pipe Line for better functionality and road restoration and providing balance FHTC of Mobarakpur Water Supply Scheme under Harishchandrapur -I Block under Malda Division, PHE Dte. in the district of Malda. | 5920/MD | 26/11/2025 | 60 | SUBHAS CHANDRA KESHARI | 28.7 | 0 | 0 | 0
514 | MALDAH | Malda Division | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme , SM/14099 | Augmentation | Acceptance cum formal work order for Route survey, design and preparation of DPR of Baharal Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. | 650/MD | 22/03/2022 | 15 | ENVIROTECH SOLUTIONS | 4.59 | 0 | 0 | 100
515 | MALDAH | Malda Division | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme , SM/14099 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 90.88 | 0 | 0 | 0
516 | MALDAH | Malda Mechanical | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme , SM/14099 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Baharal (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011899) | 2581/MLMD | 04/08/2023 | 840 | MERCURY ENGINEERING COMPANY. | 33.22 | 0 | 0 | 76
517 | MALDAH | Malda Mechanical | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme , SM/14099 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Baharal (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011899) | 2582/MLMD | 04/08/2023 | 920 | ANIMA ENTERPRISE | 33.36 | 0 | 0 | 76
518 | MALDAH | Malda Division | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme , SM/14099 | Augmentation | Formal work order for the work of Augmentation of BAHARAL ZONE-I and II Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3067/MD | 09/08/2023 | 1075 | GHOSH BROTHERS | 1160.22 | 0 | 0 | 2
519 | MALDAH | Malda Division | Augmentation of Baharal Zone-I & II Piped Water Supply Scheme , SM/14099 | Augmentation | Erection of Property board and dissemination of Property information through pipe painting related to Jal Jeevan Mission works of Bharal, Bhado, Bilaimari and Chandmoni-I & II GP under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 659/MD | 19/02/2025 | 7 | M/S TEWARI CONSTRUCTION | 0.97 | 0 | 0 | 0
520 | MALDAH | Malda Division | RAJARAM CHAK PIPED WATER SUPPLY SCHEME , SM/14461 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 27.36 | 0 | 0 | 0
521 | MALDAH | Malda Division | RAJARAM CHAK PIPED WATER SUPPLY SCHEME , SM/14461 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of RAJARAMCHAK Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | 1131/MD | 20/03/2023 | 45 | ABHIJIT PAUL | 6.57 | 0 | 0 | 100
522 | MALDAH | Malda Division | RAJARAM CHAK PIPED WATER SUPPLY SCHEME , SM/14461 | New | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of RAJARAMCHAK Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | 1136/MD | 20/03/2023 | 45 | RAJIB MANI | 4.17 | 0 | 0 | 100
523 | MALDAH | Malda Division | RAJARAM CHAK PIPED WATER SUPPLY SCHEME , SM/14461 | New | Material Requisition To Resource Division | 253/MD | 10/01/2024 | 0 | Resource Division | 7.85 | 0 | 0 | 0
524 | MALDAH | Malda Mechanical | RAJARAM CHAK PIPED WATER SUPPLY SCHEME , SM/14461 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Rajaramchak, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-668 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.18 | 0 | 0 | 0
525 | MALDAH | Malda Mechanical | RAJARAM CHAK PIPED WATER SUPPLY SCHEME , SM/14461 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Rajaramchak, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-709 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.4 | 0 | 0 | 0
526 | MALDAH | Malda Division | RAJARAM CHAK PIPED WATER SUPPLY SCHEME , SM/14461 | New | Formal work order for the work of Implementation of RAJARAMCHAK Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3087/MD | 10/08/2023 | 1053 | MONDAL CONSTRUCTION | 234.19 | 0 | 0 | 55
527 | MALDAH | Malda Mechanical | RAJARAM CHAK PIPED WATER SUPPLY SCHEME , SM/14461 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Rajaram Chak Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013552) | 2564/MLMD | 04/08/2023 | 815 | M/S. KUNDU CONSTRACTION | 28.76 | 0 | 0 | 88
528 | MALDAH | Malda Division | RAJARAM CHAK PIPED WATER SUPPLY SCHEME , SM/14461 | New | Laying of Distribution of UPVC Pipeline of RAJARAM CHAK Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 4640/MD | 24/11/2023 | 857 | M/S MOON LIGHT CONSTRUCTION & CO. | 51.23 | 0 | 0 | 25
529 | MALDAH | Malda Division | RAJARAM CHAK PIPED WATER SUPPLY SCHEME , SM/14461 | New | Construction of Boundary Wall at Head Work site of Rajaramchak Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3227/MD | 28/06/2024 | 218 | MONDAL CONSTRUCTION | 20.25 | 0 | 0 | 0
530 | MALDAH | Malda Mechanical | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15113 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. V of Bahirgachi , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004293382 | 16/05/2023 | 90 | W.B.S.E.D.C.LTD | 3.67 | 0 | 0 | 34
531 | MALDAH | Malda Mechanical | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15113 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. IV of Bahirgachi , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004293388 | 16/05/2023 | 90 | W.B.S.E.D.C.LTD | 10.01 | 0 | 0 | 34
532 | MALDAH | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15113 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 (160.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at BAHIRGACHHI Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | 1176/MD | 20/03/2023 | 30 | M/S DYNAMIC CONSTRUCTION | 10.03 | 0 | 0 | 100
533 | MALDAH | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15113 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 5 (160.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at BAHIRGACHHI Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | 1177/MD | 20/03/2023 | 30 | M/S DYNAMIC CONSTRUCTION | 10.03 | 0 | 0 | 100
534 | MALDAH | Malda Mechanical | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15113 | Augmentation | Supply, installation, commissioning & Trial operation of electro-mechanical components at T/W no IV,V,VI & VII of Source Augmentation Bahirgachi Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015614) | 4764/MLMD | 29/12/2023 | 180 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 45.26 | 0 | 0 | 48
535 | MALDAH | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15113 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 40m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Tubewell no. 4 site of Bahirgachi Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | 1178/MD | 14/03/2024 | 180 | A. K. CONSTRUCTION | 17.97 | 0 | 0 | 0
536 | MALDAH | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15113 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 40m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Tubewell no. 5 site of Bahirgachi Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | 1179/MD | 14/03/2024 | 180 | UTTAM KUMAR GHOSH | 18 | 0 | 0 | 0
537 | MALDAH | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15113 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHIRGACHHI Piped Water Supply Scheme (Raikhadighi JL-24) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | 1162/MD | 20/03/2023 | 45 | UTTAM KUMAR GHOSH | 54.79 | 0 | 0 | 100
538 | MALDAH | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15113 | Augmentation | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Bahirgachhi Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | 1203/MD | 21/03/2023 | 45 | M/S. TEWARI CONSTRUCTION | 8.33 | 0 | 0 | 100
539 | MALDAH | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15113 | Augmentation | Construction of Boundary Wall at 5th Tube Well site of Bahirgachi Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 1177/MD | 14/03/2024 | 30 | M/S MANDAL & SONS | 12.5 | 0 | 0 | 100
540 | MALDAH | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15113 | Augmentation | Construction of Boundary Wall at 4th Tube Well site of Bahirgachi Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 1249/MD | 15/03/2024 | 200 | A. L. ENGINEERING SOLUTION | 9.45 | 0 | 0 | 100
541 | MALDAH | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15113 | Augmentation | Laying of Pipeline work for facilitating FHTC at Bahirgachi Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3223/MD | 27/06/2024 | 226 | M/S NARESH KUMAR JAIN | 4.95 | 0 | 0 | 100
542 | MALDAH | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15113 | Augmentation | Augmentation of Head work site Pump House, Pump House No.-2, Pump House No.-3, Earth filling and 3 Nos. Boundary wall at Bahirgachhi Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 2954/MD | 19/06/2025 | 60 | ABHIJIT PAUL | 12.95 | 0 | 0 | 0
543 | MALDAH | Malda Division | Source Augmentation of Bahirgachi Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15113 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHIRGACHHI Piped Water Supply Scheme (Raikhadighi JL-23) at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | 1154/MD | 20/03/2023 | 613 | M/S KUNDU CONSTRUCTION | 46.45 | 0 | 0 | 80
544 | MALDAH | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED , SM/12708 | New | Continuation work order for Route survey & design for praparation of DPR of Kadamtola, Joteparam & Alipur Pipe Water Supply Scheme at Kaliachak-I Development Block under Malda Arsenic Area W/S Division, Phe Dte | 1669/MAAD | 12/09/2022 | 10 | FUTURE | 0.99 | 0 | 0 | 1
545 | MALDAH | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED , SM/12708 | New | Route survey & design for praparation of DPR of Kadamtola, Joteparam & Alipur Pipe Water Supply Scheme at Kaliachak-I Development Block under Malda Arsenic Area W/S Division, Phe Dte | 1658/MAAD | 08/09/2022 | 10 | FUTURE | 0.99 | 0 | 0 | 1
546 | MALDAH | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED , SM/12708 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Kadamtala Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda. | 125/MAAD | 31/01/2023 | 45 | JOY GURU ENTERPRISE | 14.57 | 0 | 0 | 100
547 | MALDAH | Malda Mechanical | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED , SM/12708 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. of Kadamtola, Sujapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004459313 | 11/10/2023 | 90 | W.B.S.E.D.C.LTD | 4.14 | 0 | 0 | 100
548 | MALDAH | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED , SM/12708 | New | Material Requisition To Resource Division | 632/MAAD | 05/04/2023 | 0 | Resource Division | 1.06 | 0 | 0 | 0
549 | MALDAH | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED , SM/12708 | New | Construction of 300 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Kadamtala Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (3rd Call) | 1920/MAAD | 16/10/2023 | 270 | MD. TALEB ALI | 126.12 | 0 | 0 | 85
550 | MALDAH | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED , SM/12708 | New | Laying of Distribution System for Kadamtala Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 221/MAAD | 03/02/2023 | 90 | M/S. JHA CONSTRUCTION | 71 | 0 | 0 | 90
551 | MALDAH | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED , SM/12708 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Kadamtala Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | 983/MAAD | 06/06/2023 | 665 | DIPAYAN DEY | 139.41 | 0 | 0 | 75
552 | MALDAH | Malda Mechanical | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED , SM/12708 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I and Arsenic Iron Removal Plant at Kadamtala Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/014767) | 2265/MLMD | 18/07/2023 | 894 | DEY ENTERPRISE.. | 54.08 | 0 | 0 | 48
553 | MALDAH | Malda Ars Area W/S Division | Kadamtola Mouza Piped water Supply scheme of Kaliachak-I block under Malda Arsenic Area Water Supply Division, PHED , SM/12708 | New | Construction of Boundary Wall at Head Work Site and Providing Functional House Hold Tap Connection (FHTC) for Kadamtala Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 12/MAAD | 03/01/2025 | 60 | M/S. JHA CONSTRUCTION | 52.96 | 0 | 0 | 0
554 | MALDAH | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15090 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Mahendrapur Piped Water Supply scheme in Harischandrapur I Block under Malda Division PHE. Dte. (Part-II) | 758/MD | 17/02/2023 | 30 | M/S FOUR STAR CONSTRUCTION | 14.57 | 0 | 0 | 0
555 | MALDAH | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15090 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Mahendrapur Piped Water Supply scheme in Harischandrapur I Block under Malda Division PHE. Dte. (Part-I) | 751/MD | 17/02/2023 | 30 | RAHANUL ALAM | 11.27 | 0 | 0 | 100
556 | MALDAH | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15090 | Augmentation | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 5618/MD | 06/11/2024 | 30 | RUQAIYA ENTERPRISE | 1.82 | 0 | 0 | 0
557 | MALDAH | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15090 | Augmentation | Construction of Boundary Wall at 2nd Tube Well site of Dakshin Mahendrapur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 2950/MD | 10/06/2024 | 30 | RAHANUL ALAM | 7.23 | 0 | 0 | 0
558 | MALDAH | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15090 | Augmentation | Construction of Boundary Wall at Head Work site of Dakshin Mahendrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 3203/MD | 27/06/2024 | 30 | M/S EHAN ENTERPRISE | 11.45 | 0 | 0 | 0
559 | MALDAH | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15090 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Mahendrapur Piped Water Supply scheme in Harischandrapur I Block under Malda Division PHE. Dte. (Part-III) | 767/MD | 17/02/2023 | 30 | RAHANUL ALAM | 11.31 | 0 | 0 | 100
560 | MALDAH | Malda Mechanical | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15090 | Augmentation | New service connection at DAKSHIN MAHENDRAPUR T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | BP-2024-25-193 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 6.78 | 0 | 0 | 0
561 | MALDAH | Malda Mechanical | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15090 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Dakshin Mahemdrapur Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte. (TSM/017129) | 2621/MLMD | 10/08/2023 | 691 | SUBRATA SAHA | 10.91 | 0 | 0 | 100
562 | MALDAH | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15090 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 140 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of DAKSHIN MAHENDRAPUR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | 1438/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.45 | 0 | 0 | 95
563 | MALDAH | Malda Division | Source Augmentation of Dakshin Mahendrapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15090 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Dakhin Mahendrapur PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 278/MD | 11/01/2024 | 45 | S N CONSTRUCTION | 4.18 | 0 | 0 | 99
564 | MALDAH | Malda Mechanical | MATHURAPUR PIPED WATER SUPPLY SCHEME , SM/15248 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of MATHURAPUR, Chanchal C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004371615 | 25/07/2023 | 90 | W.B.S.E.D.C.LTD | 9.08 | 0 | 0 | 100
565 | MALDAH | Malda Division | MATHURAPUR PIPED WATER SUPPLY SCHEME , SM/15248 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 12.83 | 0 | 0 | 0
566 | MALDAH | Malda Mechanical | MATHURAPUR PIPED WATER SUPPLY SCHEME , SM/15248 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Mathurapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013453) | 2567/MLMD | 04/08/2023 | 787 | DAS ENTERPRISE. | 26.54 | 0 | 0 | 43
567 | MALDAH | Malda Division | MATHURAPUR PIPED WATER SUPPLY SCHEME , SM/15248 | New | Laying of Distribution of UPVC Pipeline of MATHURAPUR Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 2331/MD | 08/06/2023 | 60 | SAHA CONSTRUCTION | 42.05 | 0 | 0 | 100
568 | MALDAH | Malda Division | MATHURAPUR PIPED WATER SUPPLY SCHEME , SM/15248 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mathurapur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 5338/MD | 03/10/2024 | 45 | SAHA CONSTRUCTION | 63.03 | 0 | 0 | 0
569 | MALDAH | Malda Division | MATHURAPUR PIPED WATER SUPPLY SCHEME , SM/15248 | New | Material Requisition To Resource Division | 90/MD | 05/01/2024 | 0 | Resource Division | 7.39 | 0 | 0 | 0
570 | MALDAH | Malda Division | MATHURAPUR PIPED WATER SUPPLY SCHEME , SM/15248 | New | Formal work order for the work of Implementation of MATHURAPUR Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1932/MD | 12/05/2023 | 1020 | A. D. ENTERPRISE | 310.11 | 0 | 0 | 66
571 | MALDAH | Malda Division | MATHURAPUR PIPED WATER SUPPLY SCHEME , SM/15248 | New | Sinking of Tube Well, Providing FHTC, Construction of Pump House & Boundary Wall at Matiharpur Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. Govt. of West Bengal. | 2280/MD | 21/05/2025 | 225 | M/S /FAIZUL HAQUE BISWAS | 52.25 | 0 | 0 | 0
572 | MALDAH | Malda Division | MATHURAPUR PIPED WATER SUPPLY SCHEME , SM/15248 | New | Construction of Boundary Wall at Head Work site of Mathurapur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 1222/MD | 26/03/2025 | 30 | M/S MADHU CONSTRUCTION | 22.79 | 0 | 0 | 0
573 | MALDAH | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15079 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 ( 78.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at DALLA Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | 1428/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 6.86 | 0 | 0 | 100
574 | MALDAH | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15079 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 78.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at DALLA Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | 1429/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 6.86 | 0 | 0 | 100
575 | MALDAH | Malda Mechanical | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15079 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. IV of Dalla, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004413357 | 05/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.77 | 0 | 0 | 100
576 | MALDAH | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15079 | Augmentation | Construction of Boundary Wall of Tubewell site at Dalla Mouza of Dalla Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 1186/MD | 14/03/2024 | 30 | J. M. CONSTRUCTION | 11.89 | 0 | 0 | 75
577 | MALDAH | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15079 | Augmentation | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dalla Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | 1303/MD | 23/03/2023 | 45 | M/S BHARATI CONSTRUCTION | 8.34 | 0 | 0 | 100
578 | MALDAH | Malda Mechanical | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15079 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III & IV of Dalla Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016720) | 2615/MLMD | 10/08/2023 | 180 | ANIMA ENTERPRISE | 22.09 | 0 | 0 | 100
579 | MALDAH | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15079 | Augmentation | Devlopment of 200 mm dia. (90 Mtr. Deep) Big dia. Tube Well at Head Work Site by using suitable Air compressor at DALLA Piped Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. | 456/MD | 19/01/2024 | 7 | ABHIJIT PAUL | 0.68 | 0 | 0 | 100
580 | MALDAH | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15079 | Augmentation | Material Requisition To Resource Division | 3997/MD | 08/08/2024 | 0 | Resource Division | 7.39 | 0 | 0 | 0
581 | MALDAH | Malda Mechanical | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15079 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Dalla, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-401 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.25 | 0 | 0 | 0
582 | MALDAH | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15079 | Augmentation | Replacement of ( 200 mm Dia. All through) Tubewell No.-1 (75 M deep) at Head Work Site by D.R Rig. Method using P.V.C. pipe & Gravel Filter including Supply of materials at DALLA Water Supply Scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | 871/MD | 27/02/2024 | 347 | A. L. ENGINEERING SOLUTION | 7 | 0 | 0 | 100
583 | MALDAH | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15079 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for DALLA Piped Water Supply Scheme (Moua-Aragacchhi, JL-No. 57) at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | 1208/MD | 21/03/2023 | 377 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 22.03 | 0 | 0 | 100
584 | MALDAH | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15079 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for DALLA Piped Water Supply Scheme (Mouza-Dalla, JL No. 54) at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | 1210/MD | 21/03/2023 | 361 | TARUN KUMAR DEY | 28.46 | 0 | 0 | 100
585 | MALDAH | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15079 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 30m³/hr. capacity Pressure type IRON ELIMINATION Plant for providing FHTC with Construction of Blower room & backwash water disposal at Tubewell no. 4 site of Dalla Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | 1185/MD | 14/03/2024 | 413 | MERCURY ENGINEERING COMPANY | 16.64 | 0 | 0 | 50
586 | MALDAH | Malda Division | Source Augmentation of Dalla Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15079 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 30m³/hr. capacity Pressure type IRON ELIMINATION Plant for providing FHTC with Construction of Blower room & backwash water disposal at Tubewell no. 3 site of Dalla Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | 1184/MD | 14/03/2024 | 413 | MERCURY ENGINEERING COMPANY | 16.64 | 0 | 0 | 30
587 | MALDAH | Malda Division | Source Augmentation of Talsur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15065 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 150 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of TALSUR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | 1437/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 9.92 | 0 | 0 | 100
588 | MALDAH | Malda Division | Source Augmentation of Talsur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15065 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipeline connection to Source Augmentation of Talsur Piped Water Supply scheme under Malda Division PHE. Dte. (Part-II) | 762/MD | 17/02/2023 | 45 | M/S TRILOCHAN CONSTRUCTION CO | 93.98 | 0 | 0 | 98
589 | MALDAH | Malda Division | Source Augmentation of Talsur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15065 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipeline connection to Source Augmentation of Talsur Piped Water Supply scheme under Malda Division, P.H.E.Dte. (Part-I) | 753/MD | 17/02/2023 | 45 | M/S. TEWARI CONSTRUCTION | 48.93 | 0 | 0 | 98
590 | MALDAH | Malda Division | Source Augmentation of Talsur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15065 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Talsur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | 1196/MD | 21/03/2023 | 45 | M/S RAKHI ENTERPRISE | 4.18 | 0 | 0 | 96
591 | MALDAH | Malda Mechanical | Source Augmentation of Talsur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15065 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. IV of Talsur PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-447 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.26 | 0 | 0 | 0
592 | MALDAH | Malda Mechanical | Source Augmentation of Talsur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15065 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Talsur Water Supply Scheme in the District of under Malda Mechanical Division, PHE Dte.(TSM/016724) | 2628/MLMD | 10/08/2023 | 600 | SOVON KUMAR DAS. | 11.45 | 0 | 0 | 100
593 | MALDAH | Malda Division | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. , SM/15086 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline for Talbangura Piped Water Supply Scheme in Harischandrapur II Block for Installation of FHTC under Malda Division PHE. Dte. | 761/MD | 17/02/2023 | 30 | M/S N. N. ENTERPRISE | 19.12 | 0 | 0 | 100
594 | MALDAH | Malda Division | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. , SM/15086 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline for Daulatpur Piped Water Supply Scheme in Harischandrapur II Block for Installation of FHTC under Malda Division PHE. Dte. (Part-I) | 750/MD | 17/02/2023 | 30 | M/S FOUR STAR CONSTRUCTION | 14.54 | 0 | 0 | 100
595 | MALDAH | Malda Division | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. , SM/15086 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline Gannadia Piped Water Supply Scheme in Harischandrapur I & II Block for Installation of FHTC under Malda Division PHE. Dte. | 752/MD | 17/02/2023 | 45 | PARIJAT RAY | 31.32 | 0 | 0 | 77
596 | MALDAH | Malda Division | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. , SM/15086 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline for Daulatpur Piped Water Supply Scheme in Harischandrapur II Block for Installation of FHTC under Malda Division PHE. Dte. (Part-II) | 757/MD | 17/02/2023 | 30 | M/S SABANA CONSTRUCTION | 18.76 | 0 | 0 | 70
597 | MALDAH | Malda Division | Laying of additional pipe line at various Piped Water Supply Schemes under Harishchandrapur-I & II Block under Malda Division, PHE Dte. , SM/15086 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline Konar Piped Water Supply Scheme in Harischandrapur I Block for Installation of FHTC under Malda Division PHE. Dte. | 1214/MD | 21/03/2023 | 45 | M/S. TEWARI CONSTRUCTION | 21.7 | 0 | 0 | 90
598 | MALDAH | Malda Mechanical | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15193 | Augmentation | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-XIV,XV and Arsenic Iron Removal Plant at Uttar Chandipur(Zone-IV B) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019390) | 2683/MLMD | 11/08/2023 | 180 | A.G ENTERPRISE. | 71.71 | 0 | 0 | 0
599 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15193 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 84.6 | 0 | 0 | 0
600 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15193 | Augmentation | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (90 Mtr. Deep) for UTTAR CHANDIPUR ZONE-IVB Water Supply Scheme at T/W-1 Head Work Site of Manikchak Block of Malda District under Malda Division, PHE Dte. | 3057/MD | 09/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 9.17 | 0 | 0 | 100
601 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15193 | Augmentation | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (90 Mtr. Deep) for UTTAR CHANDIPUR ZONE-IVB Water Supply Scheme at T/W-2 of Manikchak Block of Malda District under Malda Division, PHE Dte. | 3058/MD | 09/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 9.16 | 0 | 0 | 100
602 | MALDAH | Malda Mechanical | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15193 | Augmentation | QUOTATION PAYMENT FOR UTTARCHANDIPUR ZONE IV B T/W NO XIV UNDER MANIKCHAK CCC UNDER MALDA DISTRICT | BP-2024-25-435 | 07/08/2024 | 0 | W.B.S.E.D.C.LTD | 8.28 | 0 | 0 | 0
603 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15193 | Augmentation | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-IVB Piped Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2094/MD | 02/06/2023 | 1153 | M/S N. C. SARKAR | 392.9 | 0 | 0 | 31
604 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15193 | Augmentation | Formal work order for the work of Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 82.40M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-IVB Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | 826/MD | 28/02/2024 | 480 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 197.84 | 0 | 0 | 0
605 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- IV B Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15193 | Augmentation | Construction of Boundary Wall at 2nd Tubewell Site of Uttar Chandipur Zone-IV-B Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | 1254/MD | 15/03/2024 | 473 | A.K. AGENCY | 7.58 | 0 | 0 | 0
606 | MALDAH | Malda Mechanical | Augmentation of Adina Zone-II Piped Water Supply Scheme , SM/15956 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Adina PWSS, Zone-II Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004474993 | 08/11/2023 | 90 | W.B.S.E.D.C.LTD | 5.36 | 0 | 0 | 100
607 | MALDAH | Malda Division | Augmentation of Adina Zone-II Piped Water Supply Scheme , SM/15956 | Augmentation | Material Requisition To Resource Division | 1611/MD | 11/04/2023 | 0 | Resource Division | 4.15 | 0 | 0 | 0
608 | MALDAH | Malda Division | Augmentation of Adina Zone-II Piped Water Supply Scheme , SM/15956 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 2.97 | 0 | 0 | 0
609 | MALDAH | Malda Division | Augmentation of Adina Zone-II Piped Water Supply Scheme , SM/15956 | Augmentation | Formal work order for the work of Augmentation of ADINA ZONE-II Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte. | 1839/MD | 02/05/2023 | 791 | M/S PARIMAL DAS | 275.44 | 0 | 0 | 50
610 | MALDAH | Malda Division | Augmentation of Adina Zone-II Piped Water Supply Scheme , SM/15956 | Augmentation | Acceptance cum formal work order for Route survey, design and preparation of DPR of Adina Zone-II Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | 649/MD | 22/03/2022 | 15 | TECHVISION | 3.11 | 0 | 0 | 100
611 | MALDAH | Malda Mechanical | Augmentation of Adina Zone-II Piped Water Supply Scheme , SM/15956 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Adina Zone-II Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011890) | 4763/MLMD | 29/12/2023 | 720 | M/S TRILOCHAN CONSTRUCTION CO. | 20.75 | 0 | 0 | 55
612 | MALDAH | Malda Division | Augmentation of Adina Zone-II Piped Water Supply Scheme , SM/15956 | Augmentation | Augmentation of Pump House No.-2 at Adina Zone-II Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1070/MD | 19/03/2025 | 60 | MAHA MAYA CONSTRUCTION | 1.81 | 0 | 0 | 0
613 | MALDAH | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division , SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Gourhanda Water Supply Schemes at Chanchal-II Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | 2136/MLMD | 07/07/2023 | 1915 | MAA BHABOTARINE ENTERPRISE. | 6.97 | 0 | 0 | 0
614 | MALDAH | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division , SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Laxmighat Water Supply Schemes at Ratua-II Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | 2140/MLMD | 07/07/2023 | 1915 | MAA BHABOTARINE ENTERPRISE. | 6.97 | 0 | 0 | 0
615 | MALDAH | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division , SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Dhanjana and adjacent Water Supply Schemes at Chanchal-I Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | 2137/MLMD | 07/07/2023 | 1915 | EQUIPMENTS AND SPARES AGENCIES | 41.76 | 0 | 0 | 0
616 | MALDAH | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division , SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Arapur Water Supply Schemes at English Bazar Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | 2812/MLMD | 17/08/2023 | 1915 | NIRMAN. | 13.54 | 0 | 0 | 0
617 | MALDAH | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division , SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Adhna and adjacent Water Supply Schemes at Gazole Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | 2138/MLMD | 07/07/2023 | 1915 | DEY ENTERPRISE.. | 21.11 | 0 | 0 | 83
618 | MALDAH | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division , SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Arjuna and adjacent Water Supply Schemes at Harishchandrapur-II Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | 3631/MLMD | 23/11/2023 | 1915 | DILIP MAHATO. | 33.85 | 0 | 0 | 83
619 | MALDAH | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division , SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Arapur Water Supply Schemes at English Bazar Block in the district of Malda under Malda Mechanical Division, PHE Dte. | 3830/MLMD | 02/12/2024 | 90 | DILIP MAHATO. | 13.54 | 0 | 0 | 0
620 | MALDAH | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division , SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Habibpur and adjacent Water Supply Schemes at Habibpur Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | 2139/MLMD | 07/07/2023 | 1915 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 35.2 | 0 | 0 | 82
621 | MALDAH | Malda Mechanical | Solarisation of WBSEDCL Energised pump house with supply and installation of Grid connected, ground mounted solar PV Systems with Net Metering of 28 nos PWSS in the district of Malda under Malda Mechanical Division , SM/18124 | Solarisation | Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering for Mahammadpur and adjacent Water Supply Schemes at Old Malda Block in the district of Malda under Malda Mechanical Division, PHE Dte. (TSM/016528) | 2811/MLMD | 17/08/2023 | 1915 | SWITCHING AVO ELECTRO POWER LTD | 34.83 | 0 | 0 | 20
622 | MALDAH | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14097 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Ratua Zone-II Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. | 647/MD | 22/03/2022 | 15 | ENVIROTECH SOLUTIONS | 3.67 | 0 | 0 | 1
623 | MALDAH | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14097 | New | Bill for reimbursement of cost of Diesel and Mobil in respect of hired vehicle Car No. WB-65C/6570 for the Month of JUNE 2023 under Malda Division PHE Dte. | BP-2023-24-159 | 18/08/2023 | 0 | UTTAM KUMAR GHOSH | 0.39 | 0 | 0 | 0
624 | MALDAH | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14097 | New | Formal work order for the work of Augmentation of RATUA ZONE-II Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1999/MD | 17/05/2023 | 270 | NIRMAN | 550.19 | 0 | 0 | 30
625 | MALDAH | Malda Mechanical | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14097 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Ratua (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011274) | 2578/MLMD | 04/08/2023 | 907 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 33.37 | 0 | 0 | 81
626 | MALDAH | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14097 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Ratua Zone-II Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 5739/MD | 20/11/2024 | 180 | M/S TEWARI CONSTRUCTION | 72.46 | 0 | 0 | 0
627 | MALDAH | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14097 | New | Material Requisition To Resource Division | 121/MD | 06/01/2024 | 0 | Resource Division | 54.12 | 0 | 0 | 0
628 | MALDAH | Malda Mechanical | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14097 | New | New service connection at RATUA (ZONE II) PWSS T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( SAMSI c c c) | BP-2024-25-198 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 4.6 | 0 | 0 | 0
629 | MALDAH | Malda Mechanical | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14097 | New | New service connection at RATUA (ZONE II) PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( SAMSI c c c) | BP-2024-25-197 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 4.16 | 0 | 0 | 0
630 | MALDAH | Malda Mechanical | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14097 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 1200/MLMD | 02/04/2024 | 61 | SUBRATA SAHA | 0.78 | 0 | 0 | 100
631 | MALDAH | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14097 | New | Erection of Property board related to Jal Jeevan Mission works of Sambalpur, Gobarjona, Kadamtali & Magura PWSS under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | 660/MD | 19/02/2025 | 7 | J. M. CONSTRUCTION | 0.73 | 0 | 0 | 0
632 | MALDAH | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14097 | New | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the Assistant Engineer, Malda Division, PHE Dte. (Period from 01/01/2025 to 30/06/2025). | 6634/MD | 31/12/2024 | 181 | AMIN ENTERPRISE | 0.86 | 0 | 0 | 0
633 | MALDAH | Malda Division | Ratua Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14097 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Pump House No. 3 of Ratua Zone-II Piped Water Supply Scheme under Ratua-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 2508/MD | 29/05/2025 | 45 | M/S NAMITA CONSTRUCTION | 4.18 | 0 | 0 | 0
634 | MALDAH | Malda Mechanical | Mahil Piped Water Supply Scheme , SM/13733 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Mahil PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004390616 | 11/08/2023 | 90 | W.B.S.E.D.C.LTD | 6.34 | 0 | 0 | 100
635 | MALDAH | Malda Mechanical | Mahil Piped Water Supply Scheme , SM/13733 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Mahil PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004390525 | 11/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.58 | 0 | 0 | 100
636 | MALDAH | Malda Division | Mahil Piped Water Supply Scheme , SM/13733 | New | Material Requisition To Resource Division | 1583/MD | 10/04/2023 | 0 | Resource Division | 29.33 | 0 | 0 | 0
637 | MALDAH | Malda Division | Mahil Piped Water Supply Scheme , SM/13733 | New | Material Requisition To Resource Division | 1804/MD | 27/04/2023 | 0 | Resource Division | 69.4 | 0 | 0 | 0
638 | MALDAH | Malda Division | Mahil Piped Water Supply Scheme , SM/13733 | New | Material Requisition To Resource Division | 244/MD | 10/01/2024 | 0 | Resource Division | 23.41 | 0 | 0 | 0
639 | MALDAH | Malda Mechanical | Mahil Piped Water Supply Scheme , SM/13733 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Mahil, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-708 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.96 | 0 | 0 | 0
640 | MALDAH | Malda Division | Mahil Piped Water Supply Scheme , SM/13733 | New | Formal work order for the work of Implementation of MAHIL Piped Water Supply at Gazole Dev. Block in the District Malda under Malda Division, PHE Dte. Govt. of West Bengal. | 1038/MD | 13/03/2023 | 1115 | GHOSH BROTHERS | 1500.23 | 0 | 0 | 40
641 | MALDAH | Malda Mechanical | Mahil Piped Water Supply Scheme , SM/13733 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Mahil Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014388) | 2391/MLMD | 28/07/2023 | 824 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 42.44 | 0 | 0 | 91
642 | MALDAH | Malda Division | Mahil Piped Water Supply Scheme , SM/13733 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 439/MD | 06/02/2025 | 45 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 53.22 | 0 | 0 | 0
643 | MALDAH | Malda Division | Mahil Piped Water Supply Scheme , SM/13733 | New | Construction of Boundary Wall at Head Work site of Mahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3052/MD | 13/06/2024 | 391 | J. M. CONSTRUCTION | 23.32 | 0 | 0 | 60
644 | MALDAH | Malda Division | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | Material Requisition To Resource Division | 2752/MD | 22/11/2022 | 0 | Resource Division | 17.38 | 0 | 0 | 0
645 | MALDAH | Malda Division | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | Acceptance cum formal work order for Bamboo Pile Walling and Horizontal Road Crossing for piped water supply scheme of SANJAIL Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | 1447/MD | 29/03/2023 | 30 | M/S PARIMAL DAS | 3.44 | 0 | 0 | 0
646 | MALDAH | Malda Mechanical | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Sanjail PWSS , Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004243252 | 27/04/2023 | 90 | W.B.S.E.D.C.LTD | 3.12 | 0 | 0 | 0
647 | MALDAH | Malda Division | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150mm. dia., 140 Mtr. deep Big dia Tube Well at Head Work Site by D.R. Rig method using PVC pipe & Gravel Filter including supply of Materials at Sanjail Water Supply Scheme of Old Malda Dev. Block under Malda Division, PHE Dte. in the District of Malda. | 2237/MD | 16/09/2022 | 15 | M/S DEBASISH GHOSH | 8.81 | 0 | 0 | 100
648 | MALDAH | Malda Division | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 140 Mtr. Deep Big dia Tube well (1 Nos.) at SANJAIL Water Supply Scheme under Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1676/MD | 18/04/2023 | 30 | A. L. ENGINEERING SOLUTION | 9.83 | 0 | 0 | 100
649 | MALDAH | Malda Mechanical | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. II of Sanjail Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | 811/MLMD | 15/02/2024 | 180 | UTTAM KUMAR GHOSH | 10.74 | 0 | 0 | 83
650 | MALDAH | Malda Division | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | Laying of Rising Main including Specials and Valves for Sanjail Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 705/MD | 09/02/2024 | 45 | SADHANA CONSTRUCTION | 5.8 | 0 | 0 | 65
651 | MALDAH | Malda Division | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of SANJAIL & its adjoining mouza Water Scheme under Malda Division,PHE Dte. In the District of Malda. | 2236/MD | 16/09/2022 | 45 | SARIF BUILDERS | 6.14 | 0 | 0 | 98
652 | MALDAH | Malda Division | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | Acceptance cum formal work order for Construction of 100 M³ Capacity 20 mtr. staging height RCC Elevated service reservoir as per Departmental Design & drawing ( Ref FRG No-PC/-I/OHR/3/2012) including pipe connection and cost of pipes, specials delivery inlet, washout & overflow pipe etc, all complete with Geotechnical Investigation for SANJAIL Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | 44/MD | 16/01/2023 | 180 | M/S PARIMAL DAS | 55.12 | 0 | 0 | 99
653 | MALDAH | Malda Division | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of SANJAIL Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 455/MD | 19/01/2024 | 45 | M/S SHREE CONSORTIUM | 20.24 | 0 | 0 | 99
654 | MALDAH | Malda Division | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | Construction of Boundary Wall at Head Work site of Sanjail Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 270/MD | 11/01/2024 | 45 | M/S BHARATI CONSTRUCTION | 18.49 | 0 | 0 | 95
655 | MALDAH | Malda Mechanical | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Sanjail Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011706) | 778/ MLMD | 27/04/2023 | 120 | DEVI ENTERPRISE... | 25.41 | 0 | 0 | 0
656 | MALDAH | Malda Mechanical | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Sanjail, Old Malda CCC in the dist of Malda, Under Malda Mechanical Division PHE Dte. | BP-2023-24-592 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 4.69 | 0 | 0 | 0
657 | MALDAH | Malda Division | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | Providing balance Functional Household Tap Connection (FHTC) and Construction of Pump House in 2nd Tubewell site in connection with Jal Jeevan Mission (JJM) at Sanjail Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 2890/MD | 17/06/2025 | 60 | MADHUMITA ENTERPRISE | 19.36 | 0 | 0 | 0
658 | MALDAH | Malda Division | Sanjail PWSS in Old Malda Block in District Malda , SM/12337 | New | Formal work order for the work of Laying of Distribution pipe line SANJAIL its adjoining mouzas Pipe Water Supply Scheme at Old Malda Block in the District of Malda under Malda Division P.H.E. Dte. | 2170/MD | 21/09/2022 | 558 | M/S PARIMAL DAS | 124.75 | 0 | 0 | 100
659 | MALDAH | Malda Division | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12761 | Augmentation | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at GUN SANKARUL Piped Water Supply Scheme (Tube Well No-3) of Old Malda Block of Malda District under Malda Division, PHE Dte. | 2704/MD | 17/11/2022 | 30 | A. L. ENGINEERING SOLUTION | 8.52 | 0 | 0 | 1
660 | MALDAH | Malda Mechanical | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12761 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Gun Sankrul PWSS , Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004243248 | 27/04/2023 | 90 | W.B.S.E.D.C.LTD | 5.61 | 0 | 0 | 0
661 | MALDAH | Malda Division | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12761 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 120.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at GUN SANKRUL Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | 1174/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 8.52 | 0 | 0 | 100
662 | MALDAH | Malda Division | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12761 | Augmentation | Material Requisition To Resource Division | 2407/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0 | 0
663 | MALDAH | Malda Mechanical | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12761 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Gunsankrul Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014744) | 510/MLMD | 20/03/2023 | 180 | SHREE BISHNU CONSTRUCTION | 10.58 | 0 | 0 | 100
664 | MALDAH | Malda Division | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12761 | Augmentation | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Gun Sankrul Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | 2003/MD | 17/05/2023 | 45 | M/S. CHATTERJEE ENTERPRISE | 8.3 | 0 | 0 | 100
665 | MALDAH | Malda Mechanical | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12761 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. IV of Source Augmentation GunSankrul Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | 2177/MLMD | 20/08/2024 | 90 | SHREE BISHNU CONSTRUCTION | 10.62 | 0 | 0 | 100
666 | MALDAH | Malda Mechanical | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12761 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- IV of Gunsankrul, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-532 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 10.49 | 0 | 0 | 0
667 | MALDAH | Malda Division | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12761 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Pashim Banjapara-, JL- 32, Chirakuti, JL-39, Hatidubi JL-40, Bag Malancha JL-41) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | 2988/MD | 07/12/2022 | 816 | MANAS KUMAR SAHA | 65.41 | 0 | 0 | 90
668 | MALDAH | Malda Division | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12761 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Kuripara-, JL- 36, Bhabuk, JL-37, Paramanika JL-38) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | 2989/MD | 07/12/2022 | 45 | KRISHNENDU DUTTA | 59.95 | 0 | 0 | 100
669 | MALDAH | Malda Division | Source Augmentation of Gun Sankrul Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12761 | Augmentation | Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Jadupur JL- 28, Kamaldighi JL-29, Dhumadighi JL-30, Gungaon JL-31, Fatepur JL-34) of Old Malda Block in the District of Malda under Malda Division, PHE Dte. | 976/MD | 04/03/2024 | 211 | M/S AMIT KUMAR GUPTA | 45.81 | 0 | 0 | 71
670 | MALDAH | Malda Division | Alal Zone-I Piped Water Supply Scheme , SM/12075 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Alal Zone-I Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | 651/MD | 22/03/2022 | 15 | TECHVISION | 3.42 | 0 | 0 | 1
671 | MALDAH | Malda Division | Alal Zone-I Piped Water Supply Scheme , SM/12075 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 40.31 | 0 | 0 | 0
672 | MALDAH | Malda Division | Alal Zone-I Piped Water Supply Scheme , SM/12075 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of ALAL ZONE-I Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 2327/MD | 08/06/2023 | 60 | MD. TALEB ALI | 70.61 | 0 | 0 | 40
673 | MALDAH | Malda Mechanical | Alal Zone-I Piped Water Supply Scheme , SM/12075 | New | Supply, installation, commissioning of electro-mechanical components at T/W no. I,II, and Supply, installation, commissioning & Trial operation of electro-mechanical components at T/W no III and making compound lighting arrangement at head worksite of Alal Zone-I Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011887) | 2583/MLMD | 04/08/2023 | 800 | ANIMA ENTERPRISE | 28.62 | 0 | 0 | 72
674 | MALDAH | Malda Division | Alal Zone-I Piped Water Supply Scheme , SM/12075 | New | Construction of Boundary Wall at Head Work site of Alal zone-l Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3051/MD | 13/06/2024 | 413 | SAHA CONSTRUCTION | 50.08 | 0 | 0 | 40
675 | MALDAH | Malda Division | Alal Zone-I Piped Water Supply Scheme , SM/12075 | New | Material Requisition To Resource Division | 246/MD | 10/01/2024 | 0 | Resource Division | 9.71 | 0 | 0 | 0
676 | MALDAH | Malda Mechanical | Alal Zone-I Piped Water Supply Scheme , SM/12075 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Alal Zone-I, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-710 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.1 | 0 | 0 | 0
677 | MALDAH | Malda Division | Alal Zone-I Piped Water Supply Scheme , SM/12075 | New | Formal work order for the work of Augmentation of ALAL ZONE-I Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1994/MD | 17/05/2023 | 991 | UTTAM KUMAR DUTTA | 417.89 | 0 | 0 | 40
678 | MALDAH | Malda Division | Alal Zone-I Piped Water Supply Scheme , SM/12075 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3210/MD | 27/06/2024 | 506 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.15 | 0 | 0 | 0
679 | MALDAH | Malda Division | Alal Zone-I Piped Water Supply Scheme , SM/12075 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6406/MD | 19/12/2024 | 332 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 16.46 | 0 | 0 | 0
680 | MALDAH | Malda Division | Alal Zone-I Piped Water Supply Scheme , SM/12075 | New | Augmentation of Pump House-1 & Pump House-2, at ALAL Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1129/MD | 21/03/2025 | 45 | ARUN MUKHERJEE | 2.42 | 0 | 0 | 0
681 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme , SM/06856 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte. | 2720/MD | 10/11/2020 | 45 | M/S JHA CONSTRUCTION | 71.77 | 51.42 | 100 | 1
682 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme , SM/06856 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | 2719/MD | 10/11/2020 | 30 | MANAS KUMAR SAHA | 50.07 | 5.7 | 100 | 1
683 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme , SM/06856 | Retrofitting | Sinking of 200 mm (all through) Big Dia. Tube-Well NO-02 (130 ) M Deep by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at BORKOL Water Supply Scheme of Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal | 4813/MD | 13/09/2024 | 30 | M/S DAS CONSTRUCTION | 9.07 | 0 | 0 | 100
684 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BARKOL Water Supply Scheme , SM/06856 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Barkol Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 2485/MD | 28/05/2025 | 60 | SURAJIT MONDAL | 9.44 | 0 | 0 | 0
685 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme , SM/06859 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 2718/MD | 10/11/2020 | 30 | NIRENDRA NATH KUNDU | 58.72 | 32.7 | 65.79 | 1
686 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme , SM/06859 | Retrofitting | Extension of UPVC pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Dhanjana Madhaypara command area of Dhanjana Water Supply Scheme at Chanchal-I Block under Malda Division. PHE Dte. | 4139/MD | 11/10/2023 | 30 | M/S BANERJEE CONSTRUCTION | 3.7 | 0 | 0 | 100
687 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme , SM/06859 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DHANJANA Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 4775/MD | 05/12/2023 | 45 | ANUKUL CHANDRA DAS | 7.04 | 0 | 0 | 100
688 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme , SM/06859 | Retrofitting | Material Requisition To Resource Division | 39/MD | 04/01/2024 | 0 | Resource Division | 1.08 | 0 | 0 | 0
689 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIHAGHAT Water Supply Scheme , SM/06868 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIAGHAT Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 3001/MD | 10/12/2020 | 30 | A. K. CONSTRUCTION | 49.81 | 0 | 0 | 1
690 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIHAGHAT Water Supply Scheme , SM/06868 | Retrofitting | Material Requisition To Resource Division | 3917/MD | 06/08/2024 | 0 | Resource Division | 3.76 | 0 | 0 | 0
691 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09655 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sujapur Water Supply Scheme (Mouza- Chaspara, Habitation-Ajeiulla Biswas Para) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1158/MAAD | 13/06/2022 | 45 | A. K. CONSTRUCTION | 4.79 | 0 | 0 | 1
692 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09655 | Retrofitting | Laying of 20mm dia HDPE pipe at Chaspara, Bara Sujapur Mouzas for installation of FHTC under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1828/MAAD | 27/09/2022 | 45 | A. K. CONSTRUCTION | 6.25 | 0 | 0 | 1
693 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09655 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sujapur Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Chota Sujapur) | 1747/MAAD | 24/11/2021 | 60 | A. K. CONSTRUCTION | 45.01 | 0 | 0 | 1
694 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09655 | Retrofitting | Laying UPVC Pipe line at Chaspara under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 68/MAAD | 21/01/2022 | 45 | A. K. CONSTRUCTION | 4.78 | 0 | 0 | 100
695 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09655 | Retrofitting | Laying of 90mm dia UPVC Pipe at Bishu More, Bokatola and near Naimouza Subhania High Madrasah under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 71/MAAD | 21/01/2022 | 45 | A. K. CONSTRUCTION | 4.81 | 0 | 0 | 100
696 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09655 | Retrofitting | Laying of different dia uPVC Pipe at Ajijullah Biswas Para, Makul Biswas Para near Chaspara under Sujapur distribution Zone of Southern sector under Malda Arsenic Area Water Supply Division, PHE Dte. | 389/MAAD | 08/03/2022 | 45 | A. K. CONSTRUCTION | 14.81 | 0 | 0 | 1
697 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09655 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sujapur Water Supply Scheme (Mouza- Chaspara) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 823/MAAD | 28/04/2022 | 60 | SUBHASH CHANDRA KESHARI | 52.16 | 0 | 0 | 100
698 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09655 | Retrofitting | Laying of 90mm & 160mm dia distribution Pipeline from Firanchak to Muriwali Para for installation of FHTC under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 821/MAAD | 27/04/2023 | 60 | S & G CONSTRUCTION | 14.69 | 0 | 0 | 100
699 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09655 | Retrofitting | Laying of distribution Pipe line at Bokatola, Chaspara, Brahmotra for installation of FHTC under Sujapur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 955/MAAD | 11/05/2022 | 30 | A. K. CONSTRUCTION | 4.77 | 0 | 0 | 100
700 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09655 | Retrofitting | Material Requisition To Resource Division | 1336/MAAD | 18/07/2022 | 0 | Resource Division | 12.3 | 0 | 0 | 0
701 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sujapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Block , SM/09655 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
702 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc , SM/09657 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sadipur Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Sadipur) | 1740/MAAD | 24/11/2021 | 60 | M/S TRILOCHAN CONSTRUCTION CO. | 56.03 | 0 | 0 | 1
703 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc , SM/09657 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sadipur Water Supply Scheme (Mouza- Mobarakpur) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 829/MAAD | 28/04/2022 | 45 | M/S BABLU ENTERPRISE, | 11.69 | 0 | 0 | 1
704 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc , SM/09657 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sadipur Water Supply Scheme (Mouza- Jote Anantapur, Habitation- Bangitola) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1024/MAAD | 12/05/2022 | 45 | BENGAL ENGINEERING COMPANY | 10.05 | 0 | 0 | 100
705 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc , SM/09657 | Retrofitting | Laying of 75 mm, 90 mm dia uPVC Pipe line at East Janutola, Barkattabad, Rishipara, Dhanuk Para, SK. Para, Bridge Para for installation of FHTC under Sadipur distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1180/MAAD | 13/06/2022 | 45 | M/S TRILOCHAN CONSTRUCTION CO. | 4.83 | 0 | 0 | 100
706 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc , SM/09657 | Retrofitting | Laying of 20mm dia HDPE pipe at Sadipur Mouza for installation of FHTC under Sadipur distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 2040/MAAD | 16/11/2022 | 45 | M/S TRILOCHAN CONSTRUCTION CO. | 4.63 | 0 | 0 | 1
707 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc , SM/09657 | Retrofitting | Laying of UPVC Pipe line at Panchkiritola for installation of FHTC under Sadipur distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 2041/MAAD | 16/11/2022 | 45 | M/S TRILOCHAN CONSTRUCTION CO. | 2.64 | 0 | 0 | 100
708 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc , SM/09657 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sadipur Water Supply Scheme (Mouza- Jote Anantapur, Habitation- Akandaberia, Paschim Janutola) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1020/MAAD | 12/05/2022 | 45 | M/S MANDAL & SONS | 26.16 | 0 | 0 | 100
709 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sadipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliachak-II Bloc , SM/09657 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
710 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc , SM/09659 | Retrofitting | Placing of diesel driven Car on hire basis for official use of the Executive Engineer, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2022 to 31.12.2022) | 2040MAAD | 29/12/2021 | 365 | NITAI PANDAY | 1.73 | 0 | 0 | 1
711 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc , SM/09659 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme (Mouza- Dullugram, Krishnapur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1012/MAAD | 12/05/2022 | 60 | M/S ALISA CONSTRUCTION | 50.82 | 0 | 0 | 1
712 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc , SM/09659 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Alinagar) | 1741/MAAD | 24/11/2021 | 60 | M/S TRILOCHAN CONSTRUCTION CO. | 73.99 | 0 | 0 | 1
713 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc , SM/09659 | Retrofitting | Laying of 75 mm dia uPVC Pipe line at Ghoshpara, Sardar Tola, Babu Tola and Momin Para for installation of FHTC under Alinagar distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1171MAAD | 13/06/2022 | 45 | M/S TRILOCHAN CONSTRUCTION CO. | 3.66 | 0 | 0 | 100
714 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc , SM/09659 | Retrofitting | Laying of 20mm dia HDPE pipe at Alinagar Mouza for installation of FHTC under Alinagar distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1823MAAD | 27/09/2022 | 45 | M/S TRILOCHAN CONSTRUCTION CO. | 6.35 | 0 | 0 | 100
715 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc , SM/09659 | Retrofitting | Laying of 20mm dia HDPE pipe at Jote Dhani, Jote Param, Nabinagar, Nurnagar Mouzas for installation of FHTC under Alinagar distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1824/MAAD | 27/09/2022 | 45 | M/S TRILOCHAN CONSTRUCTION CO. | 6.56 | 0 | 0 | 100
716 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc , SM/09659 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme (Mouza- Khaltipur, Silampur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1057/MAAD | 24/05/2022 | 60 | M/S SABANA CONSTRUCTION | 39.06 | 0 | 0 | 100
717 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc , SM/09659 | Retrofitting | Material Requisition To Resource Division | 1786/MAAD | 26/11/2021 | 0 | Resource Division | 29.65 | 0 | 0 | 0
718 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Alinagar Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bloc , SM/09659 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme (Mouza- Nabinagar) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1014/MAAD | 12/05/2022 | 60 | M/S ALISA CONSTRUCTION | 82.2 | 0 | 0 | 15
719 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B , SM/09662 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Block under Malda Arsenic Area W/S Division, PHE Dte. | 1788/MAAD | 26/11/2021 | 1 | RESOURCE DIVISION, P.H.E. DTE. | 142 | 0 | 0 | 0
720 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B , SM/09662 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Doulatpur Water Supply Scheme (Mouza- Bagbari, Doulatpur) extra pipe line at Bagbari Bundh, Doulatpur and Ganipur at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1398/MAAD | 26/07/2022 | 60 | SOVON KUMAR DAS | 42.88 | 0 | 0 | 82
721 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B , SM/09662 | Retrofitting | Laying 63/75 mm dia Pipe at Basakpara village near Ashoke Basak house to Ramlal Chowdhury house, Protap Basak house to Shyamal Ghosh house, Sita Basak house to Ananda Basak house, Gopal Chowdhury house to Gopesh Rajak house, Suku paul house to Bijoy Mandal, Ramesh Mandal house to Sanjay Basak under Doulatpur W/S Scheme under Malda Arsenic Area W/S Division P.H.E Dte | 1456/MAAD | 29/07/2022 | 45 | MAA MANASHA CONSTRUCTION | 1.68 | 0 | 0 | 0
722 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B , SM/09662 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanpur , Bagbari, Laxmipur, Doulatpur Mouza of Doulatpur Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1749/MAAD | 24/11/2021 | 60 | SOVON KUMAR DAS | 44.81 | 0 | 0 | 1
723 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B , SM/09662 | Retrofitting | Laying UPVC pipe at Bahannabigha village for FHTC under Doulatpur Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | 2244/MAAD | 22/12/2022 | 45 | SOVON KUMAR DAS | 19.89 | 0 | 0 | 100
724 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B , SM/09662 | Retrofitting | Laying UPVC pipe from PW Roads Towards Bahannabigha village for FHTC under Doulatpur Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | 2243/MAAD | 22/12/2022 | 45 | M/S AMIT KUMAR GUPTA | 13.95 | 0 | 0 | 1
725 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B , SM/09662 | Retrofitting | Laying of 20mm dia extra HDPE pipe at Bagbari, Doulatpur mouza for installation of FHTC under Doulatpur distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1864/MAAD | 28/09/2022 | 30 | SOVON KUMAR DAS | 6.35 | 0 | 0 | 1
726 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B , SM/09662 | Retrofitting | Material Requisition To Resource Division | 1788/MAAD | 26/11/2021 | 0 | Resource Division | 56.12 | 0 | 0 | 0
727 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B , SM/09662 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Doulatpur Water Supply Scheme (Mouza- Laxmipur, Madhapur) at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1399/MAAD | 26/07/2022 | 60 | PARIJAT RAY | 33.54 | 0 | 0 | 75
728 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B , SM/09662 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Doulatpur Water Supply Scheme (Mouza- Chandipur) With pipe line at the same mouza Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1534/MAAD | 05/08/2022 | 60 | SAHA CONSTRUCTION | 34 | 0 | 0 | 100
729 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B , SM/09662 | Retrofitting | Laying UPVC pipe at near Bagbari village for FHTC under Doulatpur Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | 305/MAAD | 11/03/2024 | 30 | SR ENTERPRISE | 3.74 | 0 | 0 | 100
730 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B , SM/09662 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
731 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B , SM/09662 | Retrofitting | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bagbari and adjoining villages under command area of Doulatpur Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 302/MAAD | 11/03/2024 | 30 | M/S MAA TARA ENTERPRISE | 8.77 | 0 | 0 | 80
732 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Doulatpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar B , SM/09662 | Retrofitting | Laying UPVC pipe at Rajnagar Bagbari village & adjacent areas for FHTC under Doulatpur Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | 307/MAAD | 11/03/2024 | 30 | HIRAK ROYCHOUDHURY | 3.98 | 0 | 0 | 100
733 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Sultanganj,Habitation-Old 16 mile,Tingaria at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1729/MAAD | 24/11/2021 | 60 | MD. TALEB ALI | 40.17 | 0 | 0 | 1
734 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Sultanganj,Habitation-New Tingaria,Beguntola,BramattatTola,KartikTola,Ghoshpara,Jallutola )at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1731/MAAD | 24/11/2021 | 45 | M/S MOON LIGHT CONSTRUCTION & CO. | 33.14 | 0 | 0 | 1
735 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Sultanganj,Habitation-Kanchitola,V.D.O more ,Agnutola,Charbabupur,Anarditola,Dinutola,Khikirbona,Kanainagar )at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1730/MAAD | 24/11/2021 | 60 | MD. TALEB ALI | 38.3 | 0 | 0 | 1
736 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Baisnabnagar,Habitation-Old 16 mile,16 mile band,Rameshtartola,Mahajantola,KamalTola,Guruprasad Tola,17 Mile &17 mile rail Gate )at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1732/MAAD | 24/11/2021 | 60 | M/S MOON LIGHT CONSTRUCTION & CO. | 48.93 | 0 | 0 | 1
737 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme(Mouza- Babupur,Habitation-Nasirtola,Radhanathtola,Mukandapur,Guljartola,Hatichapa &Babupur )at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1734/MAAD | 24/11/2021 | 45 | M/S KUNDU CONSTRUCTION | 33.55 | 0 | 0 | 1
738 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sultanganj Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1018/MAAD | 12/05/2022 | 60 | MANASH KUMAR SAHA | 69.64 | 0 | 0 | 1
739 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Old 16 mile,16 mile,Rameshwartola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1159MAAD | 13/06/2022 | 15 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.02 | 0 | 0 | 1
740 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Old 16 mile,16 mile,Rameshwartola,Kamai Tola &Guruprassad Tola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1160/MAAD | 13/06/2022 | 15 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.48 | 0 | 0 | 1
741 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Ghoshpara & Jallutola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1162/MAAD | 13/06/2022 | 15 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.28 | 0 | 0 | 1
742 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at New Agnutola &Charbabupur & Anarditola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1165/MAAD | 13/06/2022 | 15 | MD. TALEB ALI | 4.28 | 0 | 0 | 1
743 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Old 16 mile under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1166/MAAD | 13/06/2022 | 15 | MD. TALEB ALI | 4.54 | 0 | 0 | 1
744 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Tingaria under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1167/MAAD | 13/06/2022 | 15 | MD. TALEB ALI | 4.41 | 0 | 0 | 1
745 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Kanchitola &VDO more under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1168/MAAD | 13/06/2022 | 15 | MD. TALEB ALI | 4.4 | 0 | 0 | 1
746 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at 17 Mile,17Mile rail Gate,New Tingaria,Beguntola ,Bramattatola & Kartik Tola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1161MAAD | 13/06/2022 | 15 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.15 | 0 | 0 | 1
747 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Nasirtola, Guljartola, Vimagram, Mukundatola, under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1163/MAAD | 13/06/2022 | 15 | M/S KUNDU CONSTRUCTION | 4.77 | 0 | 0 | 1
748 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at Charbabupur under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1164/MAAD | 13/06/2022 | 15 | MD. TALEB ALI | 4.81 | 0 | 0 | 1
749 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Laying of HDPE pipe 20mm dia at lalutola, sarkartola, Birnagar,Guljartola, Jaladitola under Sultanganj water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 608/MAAD | 31/03/2023 | 15 | MANASH KUMAR SAHA | 5.57 | 0 | 0 | 0
750 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Ramchandrapur Water Supply Scheme (Habitation- Ramnathpur) English Bazar Block under Malda Arsenic Area Water Supply Division, P.H.E Dte. | 2007/MAAD | 28/12/2021 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.38 | 0 | 0 | 1
751 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Gudhuyagram Village under command area of Sultanganj Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 2032/MAAD | 16/11/2022 | 45 | THREE BROTHERS CONSTRUCTION & CO. | 8.48 | 0 | 0 | 1
752 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Material Requisition To Resource Division | 131/MAAD | 28/01/2022 | 0 | Resource Division | 6.97 | 0 | 0 | 0
753 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Material Requisition To Resource Division | 193/MAAD | 11/02/2022 | 0 | Resource Division | 53.98 | 0 | 0 | 0
754 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Material Requisition To Resource Division | 1700/MAAD | 21/09/2022 | 0 | Resource Division | 3.7 | 0 | 0 | 0
755 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sultanganj Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09653 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
756 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kamalpur Mouza of Mathurapur Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1751/MAAD | 24/11/2021 | 60 | M/S PARIMAL DAS | 59.54 | 0 | 0 | 1
757 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Karia Sultanpur Mouza of Mathurapur Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1758/MAAD | 24/11/2021 | 45 | M/S STAR INDIA CONSTRUCTION | 33.92 | 0 | 0 | 1
758 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | FHTC works for various distribution zones under Malda Arsenic Area Water Supply Division, PHE Dte. | 1245/MAAD | 07/09/2021 | 1 | RESOURCE DIVISION, P.H.E. DTE. | 14.88 | 0 | 0 | 0
759 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | Repairing of pipe line by Laying of UPVC pipe line at Karia Sultanpur of Mathurapur Distribution zone under Malda Arsenic Area Water Supply Division PHED. | 396/MAAD | 08/03/2022 | 45 | M/S STAR INDIA CONSTRUCTION | 6.78 | 0 | 0 | 1
760 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | Laying of HDPE pipe 20mm dia at Kamalpur Mouza (Rabidas para, Rajak para, Thakur para) under Mathurapur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 958/MAAD | 11/05/2022 | 15 | M/S PARIMAL DAS | 4.82 | 0 | 0 | 1
761 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | Laying of HDPE pipe 20mm dia at Kamalpur Mouza (Dhunia para, Pathan para, Momin para) under Mathurapur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 959/MAAD | 11/05/2022 | 15 | M/S PARIMAL DAS | 3.26 | 0 | 0 | 1
762 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mathurapur Mouza of Mathurapur Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1752/MAAD | 24/11/2021 | 60 | NEOGI ENTERPRISE | 66.96 | 0 | 0 | 1
763 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Ugritola Mouza of Mathurapur Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1754/MAAD | 24/11/2021 | 60 | M/S MAA TARA CONSTRUCTION | 36.86 | 0 | 0 | 1
764 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sekhpura Mouza of Mathurapur Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 2020/MAAD | 29/12/2021 | 60 | MANIK CHOUDHURY | 44.82 | 0 | 0 | 1
765 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | Laying of HDPE pipe 20mm dia at MathurapurMouza (Dhrarmutola, Rajakpara) underMathurapur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 2249/MAAD | 22/12/2022 | 30 | NEOGI ENTERPRISE | 4.84 | 0 | 0 | 1
766 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | Repairing of pipe line by Laying of UPVC pipe line at Bistala Paschim para at Sekhpura Mouza of Mathurapur Distribution zone under Malda Arsenic Area Water Supply Division PHED. | 1874/MAAD | 28/09/2022 | 45 | MANIK CHOUDHURY | 5.27 | 0 | 0 | 1
767 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | Laying of HDPE pipe 20mm dia at MathurapurMouza (Kaharpara, Bochahi) underMathurapur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 2250/MAAD | 22/12/2022 | 30 | NEOGI ENTERPRISE | 3.02 | 0 | 0 | 1
768 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | Laying of HDPE pipe 20mm dia at Mathurapur Mouza (Pathan para) under Mathurapur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 2248/MAAD | 22/12/2022 | 30 | NEOGI ENTERPRISE | 4.84 | 0 | 0 | 1
769 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | Material Requisition To Resource Division | 192/MAAD | 11/02/2022 | 0 | Resource Division | 47.26 | 0 | 0 | 0
770 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mathurapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Bloc , SM/09588 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
771 | MALDAH | Malda Division | INSTALLATION OF 100 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP MADNABATI,GOBINDAPUR & MAHESHPUR AND CHANDPUR IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE , SM/10215 | Anganwadi | Acceptance cum formal work order for Supplying G.I. pipe strainer for installation of CWPP at AWC of G.P.- Madnabati, Gobindapur & Maheshpur and Chandpur in Bamangola Dev. Block at Mangalbari Stack Yard under Malda Division, PHE Dte. | 1502/MD | 28/06/2022 | 15 | SAUDAGAR (INDIA) | 18.01 | 0 | 0 | 100
772 | MALDAH | Malda Division | INSTALLATION OF 100 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP MADNABATI,GOBINDAPUR & MAHESHPUR AND CHANDPUR IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE , SM/10215 | Anganwadi | Material Requisition To Resource Division | 523/MD | 03/03/2022 | 0 | Resource Division | 20.91 | 0 | 0 | 0
773 | MALDAH | Malda Division | INSTALLATION OF 100 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP MADNABATI,GOBINDAPUR & MAHESHPUR AND CHANDPUR IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE , SM/10215 | Anganwadi | Material Requisition To Resource Division | 118/MD | 05/01/2024 | 0 | Resource Division | 16.32 | 0 | 0 | 0
774 | MALDAH | Malda Division | INSTALLATION OF 100 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES OF GP MADNABATI,GOBINDAPUR & MAHESHPUR AND CHANDPUR IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE , SM/10215 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) at different Anganwadi Centres (AWCs) of G.P.- Madnabati, Gobindapur & Maheshpur and Chandpur in Bamangola Dev. Block, Malda under Malda Division, PHE Dte. | 1134/MD | 20/05/2022 | 120 | M/S GUHA & ROY ENTERPRISE | 572.3 | 0 | 0 | 98
775 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. , SM/10383 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Deotala & Alal GP of Gazole Dev. Block under Malda Division, PHE Dte. | 85/MD | 17/01/2023 | 60 | M/S DAS CONSTRUCTION | 96.99 | 0 | 0 | 100
776 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. , SM/10383 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Gazole-I & Gazole-II GP of Gazole Dev. Block under Malda Division, PHE Dte. | 92/MD | 17/01/2023 | 75 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 113.26 | 0 | 0 | 59
777 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. , SM/10383 | School | Material Requisition To Resource Division | 723/MD | 25/03/2022 | 0 | Resource Division | 84.32 | 0 | 0 | 0
778 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. , SM/10383 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Salaidanga GP of Gazole Dev. Block under Malda Division, PHE Dte. | 59/MD | 16/01/2023 | 75 | M/S TRILOCHAN CONSTRUCTION CO | 107.8 | 0 | 0 | 100
779 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. , SM/10383 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Raniganj-I & II and Majhra GP of Gazole Dev. Block under Malda Division, PHE Dte. | 40/MD | 16/01/2023 | 75 | A. D. D. ASSOCIATES | 123.99 | 0 | 0 | 90
780 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. , SM/10383 | School | Material Requisition To Resource Division | 120/MD | 05/01/2024 | 0 | Resource Division | 8.16 | 0 | 0 | 0
781 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. , SM/10383 | School | Installation of Solar Powered Standalone Community Water Purification Plant (CWPP) for Schools at different places of Gazole Dev. Block under Malda Division, PHE Dte. (Quantity: 7 Nos.) | 1914/MD | 14/05/2025 | 150 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 40.41 | 0 | 0 | 0
782 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. , SM/10383 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Chaknagar & Karkach GP of Gazole Dev. Block under Malda Division, PHE Dte. | 84/MD | 17/01/2023 | 594 | M/S DAS CONSTRUCTION | 102.38 | 0 | 0 | 60
783 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant (128 nos.) at Schools of Gazole Dev. Block, Malda under Malda Division, PHE Dte. , SM/10383 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Pandua and Bahirgachhi-II GP of Gazole Dev. Block under Malda Division, PHE Dte. | 62/MD | 16/01/2023 | 715 | MERCURY ENGINEERING COMPANY | 107.9 | 0 | 0 | 100
784 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. AWCs in Kaliachak-II Block) , SM/10235 | Anganwadi | Providing Drinking Water Supply in 10 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 650/MAAD | 01/04/2022 | 120 | ALOK ENTERPRISE. A UNIT OF SAKET TREXIM PVT. LTD. | 70.52 | 0 | 0 | 0
785 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. AWCs in Kaliachak-II Block) , SM/10235 | Anganwadi | Providing Drinking Water Supply in 13 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 649/MAAD | 01/04/2022 | 120 | MILLENNIUM ENTERPRISE | 91.67 | 0 | 0 | 100
786 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. AWCs in Kaliachak-II Block) , SM/10235 | Anganwadi | Material Requisition To Resource Division | 330/MAAD | 28/02/2022 | 0 | Resource Division | 43.52 | 0 | 0 | 0
787 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. AWCs in Kaliachak-II Block) , SM/10235 | Anganwadi | Formal work order for Providing Drinking Water Supply in 20 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 793/MAAD | 26/04/2022 | 120 | J. S. CONSTRUCTION | 140.8 | 0 | 0 | 100
788 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. AWCs in Kaliachak-II Block) , SM/10235 | Anganwadi | Providing Drinking Water Supply in 6 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 1068/MAAD | 27/05/2022 | 120 | M/S AMIT KUMAR GUPTA | 42.34 | 0 | 0 | 100
789 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. AWCs in Kaliachak-II Block) , SM/10235 | Anganwadi | Providing Drinking Water Supply in 4 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 1133/MAAD | 10/06/2022 | 783 | M/S AMIT KUMAR GUPTA | 28.22 | 0 | 0 | 100
790 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. AWCs in Kaliachak-II Block) , SM/10235 | Anganwadi | Providing Drinking Water Supply in 2 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 1134/MAAD | 10/06/2022 | 120 | M/S PARIMAL DAS | 14.05 | 0 | 0 | 100
791 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. AWCs in Kaliachak-II Block) , SM/10235 | Anganwadi | Providing Drinking Water Supply in 4 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 1132/MAAD | 10/06/2022 | 120 | M/S. JHA CONSTRUCTION | 28.23 | 0 | 0 | 100
792 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. AWCs in Kaliachak-II Block) , SM/10235 | Anganwadi | Providing Drinking Water Supply in 10 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 648/MAAD | 01/04/2022 | 120 | M/S TRILOCHAN CONSTRUCTION CO. | 70.24 | 0 | 0 | 50
793 | MALDAH | Malda Division | KHARANGAPUR JABRA Piped Water Supply Scheme , SM/12183 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 11.42 | 0 | 0 | 0
794 | MALDAH | Malda Division | KHARANGAPUR JABRA Piped Water Supply Scheme , SM/12183 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of KHARANGAPUR JABRA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte. | 779/MD | 17/02/2023 | 30 | MERCURY ENGINEERING COMPANY | 9.2 | 0 | 0 | 98
795 | MALDAH | Malda Division | KHARANGAPUR JABRA Piped Water Supply Scheme , SM/12183 | New | Material Requisition To Resource Division | 110/MD | 05/01/2024 | 0 | Resource Division | 4.81 | 0 | 0 | 0
796 | MALDAH | Malda Mechanical | KHARANGAPUR JABRA Piped Water Supply Scheme , SM/12183 | New | New service connection at KHARANGAPUR JABRA T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | BP-2024-25-206 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.63 | 0 | 0 | 0
797 | MALDAH | Malda Mechanical | KHARANGAPUR JABRA Piped Water Supply Scheme , SM/12183 | New | New service connection at KHARANGAPURJABRA PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | BP-2024-25-574 | 28/11/2024 | 0 | W.B.S.E.D.C.LTD | 3.75 | 0 | 0 | 0
798 | MALDAH | Malda Mechanical | KHARANGAPUR JABRA Piped Water Supply Scheme , SM/12183 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Kharangapur Jabra Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013445) | 2321/MLMD | 26/07/2023 | 834 | DILIP MAHATO. | 26.54 | 0 | 0 | 85
799 | MALDAH | Malda Division | KHARANGAPUR JABRA Piped Water Supply Scheme , SM/12183 | New | Construction of Boundary Wall at Head Work site of Kharangapur Jabra Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 3447/MD | 11/07/2024 | 417 | GOBINDA ENTERPRISE | 29.37 | 0 | 0 | 70
800 | MALDAH | Malda Division | KHARANGAPUR JABRA Piped Water Supply Scheme , SM/12183 | New | Restoration of Road of KHARANGAPUR JABRA Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 3725/MD | 30/07/2025 | 30 | GOBINDA ENTERPRISE | 29.03 | 0 | 0 | 0
801 | MALDAH | Malda Division | KHARANGAPUR JABRA Piped Water Supply Scheme , SM/12183 | New | Formal work order for the work of Implementation of KHARANGAPUR JABRA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2709/MD | 14/07/2023 | 720 | GOBINDA ENTERPRISE | 168.68 | 0 | 0 | 84
802 | MALDAH | Malda Division | Sharanpur Piped Water Supply Scheme , SM/12631 | New | Material Requisition To Resource Division | 3048/MD | 12/12/2022 | 0 | Resource Division | 17.95 | 0 | 0 | 0
803 | MALDAH | Malda Division | Sharanpur Piped Water Supply Scheme , SM/12631 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of SHARANPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | 2697/MD | 17/11/2022 | 30 | ASHIS CONSTRUCTION | 9.2 | 0 | 0 | 0
804 | MALDAH | Malda Mechanical | Sharanpur Piped Water Supply Scheme , SM/12631 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Sharanpur PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004302713 | 21/07/2023 | 90 | W.B.S.E.D.C.LTD | 7.5 | 0 | 0 | 100
805 | MALDAH | Malda Mechanical | Sharanpur Piped Water Supply Scheme , SM/12631 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Sharanpur, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004368694 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.49 | 0 | 0 | 100
806 | MALDAH | Malda Division | Sharanpur Piped Water Supply Scheme , SM/12631 | New | Material Requisition To Resource Division | 1581 | 10/04/2023 | 0 | Resource Division | 6.65 | 0 | 0 | 0
807 | MALDAH | Malda Division | Sharanpur Piped Water Supply Scheme , SM/12631 | New | Material Requisition To Resource Division | 1617/MD | 11/04/2023 | 0 | Resource Division | 6.65 | 0 | 0 | 0
808 | MALDAH | Malda Division | Sharanpur Piped Water Supply Scheme , SM/12631 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at SAHARANPUR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 925/MD | 27/02/2023 | 166 | DUTTA ENTERPRISE | 10.13 | 0 | 0 | 100
809 | MALDAH | Malda Division | Sharanpur Piped Water Supply Scheme , SM/12631 | New | Formal work order for the work of Implementation of SHARANPUR Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | 825/MD | 21/02/2023 | 1043 | M/S DAS CONSTRUCTION | 189.29 | 0 | 0 | 85
810 | MALDAH | Malda Mechanical | Sharanpur Piped Water Supply Scheme , SM/12631 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Sharanpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013210) | 2798/MLMD | 17/08/2023 | 503 | SHREE BISHNU CONSTRUCTION | 22.93 | 0 | 0 | 100
811 | MALDAH | Malda Division | Sharanpur Piped Water Supply Scheme , SM/12631 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 3443/MD | 11/07/2024 | 598 | M/S DAS CONSTRUCTION | 22.19 | 0 | 0 | 70
812 | MALDAH | Malda Division | Sharanpur Piped Water Supply Scheme , SM/12631 | New | Construction of Boundary Wall at 2nd Tube Well site of Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 2959/MD | 10/06/2024 | 416 | M/S DAS CONSTRUCTION | 9.32 | 0 | 0 | 0
813 | MALDAH | Malda Division | Sharanpur Piped Water Supply Scheme , SM/12631 | New | Construction of Boundary Wall at Head Work site of Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 5550/MD | 29/10/2024 | 519 | M/S DAS CONSTRUCTION | 31.36 | 0 | 0 | 70
814 | MALDAH | Malda Division | Sharanpur Piped Water Supply Scheme , SM/12631 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sharanpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 2338/MD | 22/05/2025 | 313 | M/S DAS CONSTRUCTION | 31.48 | 0 | 0 | 0
815 | MALDAH | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. , SM/12632 | New | Material Requisition To Resource Division | 3047/MD | 12/12/2022 | 0 | Resource Division | 19.68 | 0 | 0 | 0
816 | MALDAH | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. , SM/12632 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of CHHATRAK Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | 2698/MD | 17/11/2022 | 30 | MERCURY ENGINEERING COMPANY | 9.2 | 0 | 0 | 0
817 | MALDAH | Malda Mechanical | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. , SM/12632 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Chhatrak PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004232695 | 17/05/2023 | 90 | W.B.S.E.D.C.LTD | 5.3 | 0 | 0 | 0
818 | MALDAH | Malda Mechanical | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. , SM/12632 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of CHHATRAK PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004302727 | 21/07/2023 | 90 | W.B.S.E.D.C.LTD | 8.02 | 0 | 0 | 100
819 | MALDAH | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. , SM/12632 | New | Material Requisition To Resource Division | 1613/MD | 11/04/2023 | 0 | Resource Division | 4.3 | 0 | 0 | 0
820 | MALDAH | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. , SM/12632 | New | Material Requisition To Resource Division | 1584/MD | 10/04/2023 | 0 | Resource Division | 4.3 | 0 | 0 | 0
821 | MALDAH | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. , SM/12632 | New | Formal work order for the work of Implementation of CHHATRAK Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte. | 875/MD | 22/02/2023 | 1317 | M/S TRILOCHAN CONSTRUCTION CO | 150.77 | 0 | 0 | 90
822 | MALDAH | Malda Mechanical | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. , SM/12632 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Chhatrak Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012833) | 786/MLMD | 27/04/2023 | 914 | M/S S. S. ENTERPRISE | 25.16 | 0 | 0 | 85
823 | MALDAH | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. , SM/12632 | New | Construction of Boundary Wall at 2nd Tubewell site of Chhatrak Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 3034/MD | 13/06/2024 | 30 | BIDYUT MAHALDAR | 10.41 | 0 | 0 | 0
824 | MALDAH | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. , SM/12632 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Chhatrak Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 4995/MD | 27/09/2024 | 45 | BIDYUT MAHALDAR | 14.99 | 0 | 0 | 0
825 | MALDAH | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. , SM/12632 | New | Material Requisition To Resource Division | 3995/MD | 08/08/2024 | 0 | Resource Division | 2.22 | 0 | 0 | 0
826 | MALDAH | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. , SM/12632 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at CHHATRAK Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 924/MD | 27/02/2023 | 30 | SAUDAGAR INDIA | 10.13 | 0 | 0 | 0
827 | MALDAH | Malda Division | CHHATRAK PWSS at Harishchandrapur-II of Malda Division PHE Dte. , SM/12632 | New | Construction of Boundary Wall at Head Work site of Chhatrak Water Supply Scheme under Harischandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 3033/MD | 13/06/2024 | 536 | M/S TRILOCHAN CONSTRUCTION CO | 26.65 | 0 | 0 | 75
828 | MALDAH | Malda Division | Sahapur Piped Water Supply Scheme , SM/11968 | New | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of SAHAPUR Piped Water Supply Scheme under Malda Division, PHE Dte. | 2692/MD | 09/09/2021 | 7 | RADIANT | 1.72 | 0 | 0 | 1
829 | MALDAH | Malda Division | Sahapur Piped Water Supply Scheme , SM/11968 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 4/6 to 4/7 between Old Malda Station (OLMF) to Malda Court Station (MLFC) for SAHAPUR and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | 4111/MD | 10/10/2023 | 181 | M/S TRILOCHAN CONSTRUCTION CO | 22.05 | 0 | 0 | 0
830 | MALDAH | Malda Division | Sahapur Piped Water Supply Scheme , SM/11968 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 104.87 | 0 | 0 | 0
831 | MALDAH | Malda Division | Sahapur Piped Water Supply Scheme , SM/11968 | New | Formal work order for the work of Augmentation of SAHAPUR Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2093/MD | 02/06/2023 | 1145 | S DUTTA | 785.2 | 0 | 0 | 45
832 | MALDAH | Malda Mechanical | Sahapur Piped Water Supply Scheme , SM/11968 | New | Supply, installation, commissioning of electro-mechanical components at T/W no. II,III & IV of Augmentation of Sahapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013245) | 2766/MLMD | 14/08/2023 | 1032 | HANNAN BUILDERS PVT. LTD. | 31.15 | 0 | 0 | 84
833 | MALDAH | Malda Division | Sahapur Piped Water Supply Scheme , SM/11968 | New | Material Requisition To Resource Division | 821/MD | 21/02/2024 | 0 | Resource Division | 23.62 | 0 | 0 | 0
834 | MALDAH | Malda Division | Sahapur Piped Water Supply Scheme , SM/11968 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 4/6 to 4/7 between Old Malda Station (OLMF) to Malda Court Station (MLFC) for SAHAPUR and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | BP-2023-24-461 | 02/02/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 0.05 | 0 | 0 | 0
835 | MALDAH | Malda Division | Sahapur Piped Water Supply Scheme , SM/11968 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 4/6 to 4/7 between Old Malda Station (OLMF) to Malda Court Station (MLFC) for SAHAPUR and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | BP-2023-24-602 | 28/03/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 4.41 | 0 | 0 | 0
836 | MALDAH | Malda Division | Sahapur Piped Water Supply Scheme , SM/11968 | New | Laying of 200 mm dia HDPE water carrying pipe of chainage 327.800 of the NH-34 of Sahapur GhoshparaBypass More of Saha & Adjoining Mouza water supply Scheme under Malda Division, PHE Dte. | BP-2023-24-478 | 15/02/2024 | 0 | NATIONAL HIGHWAYS AUTHORITY OF INDIA PAYABLE AT MALDA | 0.56 | 0 | 0 | 0
837 | MALDAH | Malda Division | Sahapur Piped Water Supply Scheme , SM/11968 | New | Laying of Rising Main including Specials and Valves for Sahapur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2990/MD | 11/06/2024 | 315 | S. N. CONSTRUCTION | 24.73 | 0 | 0 | 0
838 | MALDAH | Malda Division | Sahapur Piped Water Supply Scheme , SM/11968 | New | Formal work order for the work of Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sahapur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 2534/MD | 30/05/2025 | 120 | M/S DAS CONSTRUCTION | 123.11 | 0 | 0 | 0
839 | MALDAH | Malda Division | Sahapur Piped Water Supply Scheme , SM/11968 | New | Augmentation work of Construction of Boundary Wall at Head Work site of Sahapur Water Supply Scheme under Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 1224/MD | 26/03/2025 | 75 | SHREE BISHNU CONSTRUCTION | 25.15 | 0 | 0 | 0
840 | MALDAH | Malda Division | Sahapur Piped Water Supply Scheme , SM/11968 | New | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 1st Tube Well Site of SAHAPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | 1226/MD | 26/03/2025 | 75 | M/S AMIT KUMAR GUPTA | 11.48 | 0 | 0 | 0
841 | MALDAH | Malda Division | Sahapur Piped Water Supply Scheme , SM/11968 | New | Augmentation work of Pump House and Construction of Toilet at Head Work site Site of Sahapur Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | 1225/MD | 26/03/2025 | 75 | M/S S. S. CONSTRUCTION | 3.73 | 0 | 0 | 0
842 | MALDAH | Malda Division | Sahapur Piped Water Supply Scheme , SM/11968 | New | Augmentation of Boundary wall, Pump House and Construction of Toilet at 3rdd Tube Well Site of SAHAPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | 1227/MD | 26/03/2025 | 75 | M/S AMIT KUMAR GUPTA | 5.02 | 0 | 0 | 0
843 | MALDAH | Malda Mechanical | BAIRAT Piped Water Supply Scheme , SM/12743 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of BAIRAT ,Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004353764 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 9.45 | 0 | 0 | 100
844 | MALDAH | Malda Mechanical | BAIRAT Piped Water Supply Scheme , SM/12743 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Bairat, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004353771 | 08/08/2023 | 90 | W.B.S.E.D.C.LTD | 4.51 | 0 | 0 | 100
845 | MALDAH | Malda Division | BAIRAT Piped Water Supply Scheme , SM/12743 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 27.83 | 0 | 0 | 0
846 | MALDAH | Malda Mechanical | BAIRAT Piped Water Supply Scheme , SM/12743 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bairat Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014439) | 2382/MLMD | 28/07/2023 | 1049 | M/S. KUNDU CONSTRACTION | 27.77 | 0 | 0 | 86
847 | MALDAH | Malda Division | BAIRAT Piped Water Supply Scheme , SM/12743 | New | Material Requisition To Resource Division | 37/MD | 04/01/2024 | 0 | Resource Division | 16.2 | 0 | 0 | 0
848 | MALDAH | Malda Division | BAIRAT Piped Water Supply Scheme , SM/12743 | New | Formal work order for the work of Implementation of BAIRAT Piped Water Supply Scheme at Harishchandrapur-I Dev. Block of Malda District under Malda Division, PHE Dte. Govt. of West Bengal. | 581/MD | 09/02/2023 | 1295 | USHA ENTERPRISE | 732.14 | 0 | 0 | 79
849 | MALDAH | Malda Division | BAIRAT Piped Water Supply Scheme , SM/12743 | New | Construction of Boundary Wall at Head Work site of Bairat Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 160/MD | 08/01/2024 | 494 | USHA ENTERPRISE | 21.58 | 0 | 0 | 70
850 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11912 | Retrofitting | Laying of 90 mm dia UPVC pipe & Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission (JJM& Jal Swapna) at Karmakarpara under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | 3071/MAAD | 14/12/2023 | 60 | DEY CONSTRUCTIONS | 9.92 | 0 | 0 | 100
851 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11912 | Retrofitting | Laying of 90 mm dia UPVC pipe & Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission(JJM& Jal Swapna) at Nayagram (Baishnabnagar) under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | 3070/MAAD | 14/12/2023 | 60 | UNITED FRIENDS UMEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD | 4.97 | 0 | 0 | 100
852 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11912 | Retrofitting | Laying of 90 mm dia & 75 mm dia UPVC pipe,Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission (JJM& Jal Swapna) from 17 mile bandh to Kamartola village under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | 3072/MAAD | 14/12/2023 | 60 | MD. TALEB ALI | 16.82 | 0 | 0 | 100
853 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11912 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
854 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jalalpur, Maksudpur and Sultanganj Zone Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11912 | Retrofitting | Laying of 125 mm dia & 75 mm dia UPVC pipe,Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission(JJM& Jal Swapna) from Old 18 mile to Chamagram, Chhoto chamagram, Poladtola, Ajimtola village under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | 3075/MAAD | 14/12/2023 | 443 | ACHARYYA CONSTRUCTION | 29.1 | 0 | 0 | 100
855 | MALDAH | Malda Division | BANGRUA PWSS , SM/12193 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of BANGRUA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte. | 778/MD | 17/02/2023 | 30 | SAUDAGAR (INDIA) | 9.2 | 0 | 0 | 100
856 | MALDAH | Malda Mechanical | BANGRUA PWSS , SM/12193 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of BANGRUA PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004401750 | 12/09/2023 | 90 | W.B.S.E.D.C.LTD | 5.47 | 0 | 0 | 100
857 | MALDAH | Malda Division | BANGRUA PWSS , SM/12193 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 6.97 | 0 | 0 | 0
858 | MALDAH | Malda Division | BANGRUA PWSS , SM/12193 | New | Material Requisition To Resource Division | 94/MD | 05/01/2024 | 0 | Resource Division | 3.08 | 0 | 0 | 0
859 | MALDAH | Malda Division | BANGRUA PWSS , SM/12193 | New | Material Requisition To Resource Division | 3993/MD | 08/08/2024 | 0 | Resource Division | 3.7 | 0 | 0 | 0
860 | MALDAH | Malda Mechanical | BANGRUA PWSS , SM/12193 | New | New service connection at BANGRUA PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | BP-2024-25-201 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.27 | 0 | 0 | 0
861 | MALDAH | Malda Mechanical | BANGRUA PWSS , SM/12193 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bangrua Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013018) | 2260/MLMD | 18/07/2023 | 852 | SOUMEN ELECTRIC, | 26.41 | 0 | 0 | 84
862 | MALDAH | Malda Division | BANGRUA PWSS , SM/12193 | New | Formal work order for the work of Implementation of BANGRUA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3289/MD | 23/08/2023 | 678 | KUNDU CONSTRUCTION | 148.48 | 0 | 0 | 65
863 | MALDAH | Malda Division | BANGRUA PWSS , SM/12193 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bangrua Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 1150/MD | 21/03/2025 | 225 | A. B. CONSTRUCTION | 26.08 | 0 | 0 | 60
864 | MALDAH | Malda Division | BANGRUA PWSS , SM/12193 | New | Construction of Boundary Wall at Head Work site of BANGURA Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 3704/MD | 29/07/2025 | 60 | M/S GHOSH CONSTRUCTION | 22.26 | 0 | 0 | 0
865 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Paramanandapur, Biswambhar Binodpur, Bishnupur Shrirampara, Kamalpur, Paschim Narayanpur, Enayetpur and Gouripurr Zone Water Supply Scheme at Manikchak Block under Malda Arsenic Ar , SM/11917 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
866 | MALDAH | Malda Division | MATIHARPUR Piped Water Supply Scheme , SM/12769 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of MATIHARPUR Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 1010/MD | 10/03/2023 | 60 | M/S DAS CONSTRUCTION | 84.75 | 0 | 0 | 0
867 | MALDAH | Malda Division | MATIHARPUR Piped Water Supply Scheme , SM/12769 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 50.44 | 0 | 0 | 0
868 | MALDAH | Malda Division | MATIHARPUR Piped Water Supply Scheme , SM/12769 | New | Material Requisition To Resource Division | 88/MD | 05/01/2024 | 0 | Resource Division | 15.4 | 0 | 0 | 0
869 | MALDAH | Malda Mechanical | MATIHARPUR Piped Water Supply Scheme , SM/12769 | New | New service connection at MOTIHARPUR PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.(CHANCHAL c c c) | BP-2024-25-199 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 5.4 | 0 | 0 | 0
870 | MALDAH | Malda Mechanical | MATIHARPUR Piped Water Supply Scheme , SM/12769 | New | New service connection at motiharpur T/W no I under EE/MLMD PHE DTE Dist. malda (chanchal c. c. c) | BP-2023-24-563 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 9.37 | 0 | 0 | 0
871 | MALDAH | Malda Mechanical | MATIHARPUR Piped Water Supply Scheme , SM/12769 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Matiharpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013447) | 2324/MLMD | 26/07/2023 | 946 | HANNAN BUILDERS PVT. LTD. | 38.62 | 0 | 0 | 46
872 | MALDAH | Malda Division | MATIHARPUR Piped Water Supply Scheme , SM/12769 | New | Construction of Boundary Wall at Head Work site of Matiharpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | 2692/MD | 04/06/2025 | 45 | M/S ROY CONSTRUCTION | 29.35 | 0 | 0 | 0
873 | MALDAH | Malda Mechanical | EMAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13720 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Emamnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004467227 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 3.4 | 0 | 0 | 100
874 | MALDAH | Malda Mechanical | EMAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13720 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Emamnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004467170 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 3.8 | 0 | 0 | 100
875 | MALDAH | Malda Division | EMAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13720 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 113.13 | 0 | 0 | 0
876 | MALDAH | Malda Division | EMAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13720 | New | Material Requisition To Resource Division | 250/MD | 10/01/2024 | 0 | Resource Division | 16.78 | 0 | 0 | 0
877 | MALDAH | Malda Division | EMAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13720 | New | Formal work order for the work of Implementation of EMAMNAGAR Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1039/MD | 13/03/2023 | 1115 | GHOSH BROTHERS | 1113.74 | 0 | 0 | 50
878 | MALDAH | Malda Mechanical | EMAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13720 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Emamnagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014505) | 2387/MLMD | 28/07/2023 | 854 | DAS ENTERPRISE. | 28.65 | 0 | 0 | 0
879 | MALDAH | Malda Division | EMAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/13720 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Emamnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6410/MD | 19/12/2024 | 466 | ABANI BHUSAN GHOSH | 52.11 | 0 | 0 | 0
880 | MALDAH | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14098 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Ratua Zone-I Piped Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. | 646/MD | 22/03/2022 | 15 | ENVIROTECH SOLUTIONS | 4.4 | 0 | 0 | 1
881 | MALDAH | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14098 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 80.51 | 0 | 0 | 0
882 | MALDAH | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14098 | New | Bill for reimbursement of cost of Diesel and Mobil in respect of hired vehicle Car No. WB-04-H-8254 for the Month of MAY, JUNE and JULY 2023 under Malda Division PHE Dte. |  | 10/08/2023 | 0 | SHABNAM ARA | 1.18 | 0 | 0 | 0
883 | MALDAH | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14098 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Ratua Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 6206/MD | 09/12/2024 | 45 | RAJA CONSTRUCTION | 4.51 | 0 | 0 | 0
884 | MALDAH | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14098 | New | Formal work order for the work of Augmentation of RATUA ZONE-I Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2042/MD | 19/05/2023 | 1074 | STARCO CONSTRUCTIONS | 853.24 | 0 | 0 | 60
885 | MALDAH | Malda Mechanical | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14098 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & III and making compound lighting arrangement at Head worksite of Ratua (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011269) | 2579/MLMD | 04/08/2023 | 907 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 33.64 | 0 | 0 | 87
886 | MALDAH | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14098 | New | Dismantling of abandoned room at Head work site of Ratua-I PWSS under Ratua-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 654/MD | 08/02/2024 | 30 | M/S. TEWARI CONSTRUCTION | 1.93 | 0 | 0 | 100
887 | MALDAH | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14098 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Ratua Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 1517/MD | 16/03/2024 | 715 | UTTAM KUMAR GHOSH | 79.16 | 0 | 0 | 0
888 | MALDAH | Malda Division | Ratua Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14098 | New | Construction of Boundary Wall at 3rd Tube well site of Ratua Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 6200/MD | 09/12/2024 | 45 | UTTAM KUMAR GHOSH | 7.56 | 0 | 0 | 100
889 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme , SM/14100 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. | 659/MD | 22/03/2022 | 15 | ECO CARE | 3.71 | 0 | 0 | 1
890 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme , SM/14100 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 120.24 | 0 | 0 | 0
891 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme , SM/14100 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 1 at Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 652/MD | 08/02/2024 | 45 | J. M. CONSTRUCTION | 4.76 | 0 | 0 | 0
892 | MALDAH | Malda Mechanical | Pukuria Piped Water Supply Scheme , SM/14100 | New | New service connection at PUKURIA PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( Paranpur c c c) | BP-2024-25-524 | 26/09/2024 | 0 | W.B.S.E.D.C.LTD | 4.77 | 0 | 0 | 0
893 | MALDAH | Malda Mechanical | Pukuria Piped Water Supply Scheme , SM/14100 | New | New service connection at pukuria PWSS T/W NO Iv Under EE/MLMD PHE DTE DIST. Malda.( paranpur c c c) | BP-2024-25-523 | 26/09/2024 | 0 | W.B.S.E.D.C.LTD | 4.96 | 0 | 0 | 0
894 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme , SM/14100 | New | Formal work order for the work of Augmentation of PUKHURIA Piped Water Supply Scheme at Ratua-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2022/MD | 18/05/2023 | 1137 | DUTTA ENTERPRISE | 957.93 | 0 | 0 | 60
895 | MALDAH | Malda Mechanical | Pukuria Piped Water Supply Scheme , SM/14100 | New | Name of Work: Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II,III & IV and making compound lighting arrangement at Head worksite of Pukuria Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011879) | 2580/MLMD | 04/08/2023 | 907 | DEY ENTERPRISE.. | 44.39 | 0 | 0 | 92
896 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme , SM/14100 | New | Construction of Boundary Wall at 4th Tube Well site of Pukuria Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | 3955/MD | 07/08/2024 | 45 | MAHA MAYA CONSTRUCTION | 7.12 | 0 | 0 | 100
897 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme , SM/14100 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Pukuria Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | 5794/MD | 13/11/2025 | 60 | DUTTA ENTERPRISE | 117.25 | 0 | 0 | 0
898 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme , SM/14100 | New | Erection of Property board related to Jal Jeevan Mission works of Paharpur, Sultanpur, Pukuria PWSS under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | 661/MD | 19/02/2025 | 7 | J. M. CONSTRUCTION | 0.73 | 0 | 0 | 0
899 | MALDAH | Malda Division | Pukuria Piped Water Supply Scheme , SM/14100 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 2 at Pukuria Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 651/MD | 08/02/2024 | 45 | CHAKRABORTY & MANDAL ENTERPRISE | 4.76 | 0 | 0 | 100
900 | MALDAH | Malda Mechanical | JIGIN Piped Water Supply Scheme , SM/13430 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Jigin PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004387500 | 18/08/2023 | 90 | W.B.S.E.D.C.LTD | 10.6 | 0 | 0 | 100
901 | MALDAH | Malda Mechanical | JIGIN Piped Water Supply Scheme , SM/13430 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Jigin PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004387515 | 18/08/2023 | 90 | W.B.S.E.D.C.LTD | 6.63 | 0 | 0 | 100
902 | MALDAH | Malda Division | JIGIN Piped Water Supply Scheme , SM/13430 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 34.75 | 0 | 0 | 0
903 | MALDAH | Malda Mechanical | JIGIN Piped Water Supply Scheme , SM/13430 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Jigin Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015837) | 2319/MLMD | 26/07/2023 | 525 | RMD TRADING. | 26.24 | 0 | 0 | 78
904 | MALDAH | Malda Division | JIGIN Piped Water Supply Scheme , SM/13430 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of JIGIN Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | 1129/MD | 20/03/2023 | 45 | JOYDEB SENGUPTA | 6.58 | 0 | 0 | 100
905 | MALDAH | Malda Division | JIGIN Piped Water Supply Scheme , SM/13430 | New | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of JIGIN Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | 1134/MD | 20/03/2023 | 45 | M/S ROY CONSTRUCTION | 4.21 | 0 | 0 | 100
906 | MALDAH | Malda Division | JIGIN Piped Water Supply Scheme , SM/13430 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Jigin Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 2509/MD | 29/05/2025 | 60 | ARKADEEP ENTERPRISE | 7.24 | 0 | 0 | 0
907 | MALDAH | Malda Division | JIGIN Piped Water Supply Scheme , SM/13430 | New | Formal work order for Implementation of JIGIN Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1251/MD | 22/03/2023 | 590 | GOBINDA ENTERPRISE | 88.5 | 0 | 0 | 100
908 | MALDAH | Malda Division | Source Augmentation of Kankot Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15057 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Kankot Water Supply Scheme in Ratua I Block for Installation of FHTC under Malda Division PHE. Dte. | 754/MD | 17/02/2023 | 30 | PRITAM ENTERPRISE | 4.76 | 0 | 0 | 0
909 | MALDAH | Malda Division | Source Augmentation of Kankot Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15057 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 138 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of KANKOT Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | 1435/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.68 | 0 | 0 | 0
910 | MALDAH | Malda Division | Source Augmentation of Kankot Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15057 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Kankot Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte. | 1198/MD | 21/03/2023 | 45 | PRITAM ENTERPRISE | 4.16 | 0 | 0 | 0
911 | MALDAH | Malda Mechanical | Source Augmentation of Kankot Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15057 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Kankot Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte.(TSM/017203) | 2623/MLMD | 10/08/2023 | 1051 | M/S SABANA CONSTRUCTION | 11.44 | 0 | 0 | 87
912 | MALDAH | Malda Division | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15074 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipeline connection to Source Augmentation of Arjuna Piped Water Supply scheme at Harishchandrapur-II under Malda Division, P.H.E.Dte. | 755/MD | 17/02/2023 | 30 | GHOSH CONSTRUCTION | 15.53 | 0 | 0 | 0
913 | MALDAH | Malda Division | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15074 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 138 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of ARJUNA Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | 1433/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.68 | 0 | 0 | 100
914 | MALDAH | Malda Mechanical | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15074 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Arjuna PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-448 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.4 | 0 | 0 | 0
915 | MALDAH | Malda Division | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15074 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arjuna Mouza of Arjuna Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 10 | 03/01/2025 | 45 | TWO BROTHERS CONSTRUCTION | 10.01 | 0 | 0 | 0
916 | MALDAH | Malda Division | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15074 | Augmentation | Augmentation work of OHR, Pump House and Boundary Wall of Arjuna Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1053/MD | 18/03/2025 | 75 | M/S KUNDU CONSTRUCTION | 28.76 | 0 | 0 | 0
917 | MALDAH | Malda Division | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15074 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Arjuna Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | 1297/MD | 23/03/2023 | 45 | SAYEM ENTERPRISE | 4.2 | 0 | 0 | 100
918 | MALDAH | Malda Mechanical | Source Augmentation of Arjuna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15074 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Arjuna Water Supply Scheme in the District of under Malda Mechanical Division, PHE Dte.(TSM/016722) | 2617/MLMD | 10/08/2023 | 600 | NEOGI ENTERPRISE. | 10.92 | 0 | 0 | 100
919 | MALDAH | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME , SM/15155 | Augmentation | Construction of R.C.C. Culvert (Approach) infront of Head Works Site of AIHO ZONE-I Piped Water Supply Scheme under Malda Division PHE Dte. In the district of Malda. | 4142/MD | 11/10/2023 | 30 | M/S STAR INDIA CONSTRUTION | 1.12 | 0 | 0 | 100
920 | MALDAH | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME , SM/15155 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 8.74 | 0 | 0 | 0
921 | MALDAH | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME , SM/15155 | Augmentation | Acceptance cum formal work order for Laying of Rising main and Construction of Pump houses for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1840/MD | 02/05/2023 | 45 | SARIF BUILDERS | 12.75 | 0 | 0 | 100
922 | MALDAH | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME , SM/15155 | Augmentation | Dismantling of concrete for the laying of Distribution system through the concrete roads within Aiho Zone-I Piped Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 5004/MD | 27/09/2024 | 45 | M/S FRIENDS CONSTRUCTION & CO. | 19.96 | 0 | 0 | 90
923 | MALDAH | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME , SM/15155 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at AIHO ZONE-1 Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 979/MD | 04/03/2024 | 45 | S. R. CONSTRUCTION | 28.24 | 0 | 0 | 100
924 | MALDAH | Malda Mechanical | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME , SM/15155 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Augmentation of Aiho(zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017676) | 2632/MLMD | 10/08/2023 | 697 | MUKHERJEE ART CENTRE | 25.83 | 0 | 0 | 0
925 | MALDAH | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME , SM/15155 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Aiho Zone-I Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 1260/MD | 28/03/2025 | 134 | SIVRAM ENTERPRISE | 17.36 | 0 | 0 | 0
926 | MALDAH | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME , SM/15155 | Augmentation | Acceptance cum formal work order for Laying of Distribution system for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 1179/MD | 21/03/2023 | 710 | M/S STAR INDIA CONSTRUTION | 85.22 | 0 | 0 | 100
927 | MALDAH | Malda Division | AUGMENTATION OF AIHO ZONE-I PIPED WATER SUPPLY SCHEME , SM/15155 | Augmentation | Acceptance cum formal work order for Construction of 150 cum capacity 20 mtr. Staging height RCC OHR and Providing Household Tap Connection (FHTC) for Augmentation of AIHO ZONE-I Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1211/MD | 22/03/2023 | 710 | M/S FRIENDS CONSTRUCTION & CO. | 91.59 | 0 | 0 | 65
928 | MALDAH | Malda Division | Laying of additional pipeline and restoration in connection with retrofitting of Baherpur Water Supply Scheme ( Zone I & Zone II) in Bamongola Dev. Block under Malda Division P.H.E Dte Malda. , SM/15197 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHERPUR ZONE-II Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | 1159/MD | 20/03/2023 | 45 | KRISHNENDU DUTTA | 59.38 | 0 | 0 | 85
929 | MALDAH | Malda Division | Laying of additional pipeline and restoration in connection with retrofitting of Baherpur Water Supply Scheme ( Zone I & Zone II) in Bamongola Dev. Block under Malda Division P.H.E Dte Malda. , SM/15197 | Augmentation | Augmentation of Boundary Walls and Construction of Switch Room of size 3.60 x 3.0 M of BAHERPUR ( ZONE I & II) Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 6389/MD | 18/12/2024 | 45 | PABITRA MANDAL | 21.71 | 0 | 0 | 0
930 | MALDAH | Malda Division | Laying of additional pipeline and restoration in connection with retrofitting of Baherpur Water Supply Scheme ( Zone I & Zone II) in Bamongola Dev. Block under Malda Division P.H.E Dte Malda. , SM/15197 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for BAHERPUR ZONE-I Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | 828/MD | 21/02/2023 | 45 | M/S PARIMAL DAS | 82.32 | 0 | 0 | 98
931 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16382 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 144.69 | 0 | 0 | 0
932 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16382 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 92.00M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-II Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | 1278/MD | 15/03/2024 | 240 | DEBAPRIYA SAHA | 210.87 | 0 | 0 | 0
933 | MALDAH | Malda Mechanical | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16382 | Augmentation | QUOTATION PAYMENT FOR UTTAR CHANDIPUR ZONE II TW NO XII UNDER MANIKCHAK CCC UNDER MALDA DISTRICT | BP-2024-25-414 | 30/07/2024 | 0 | W.B.S.E.D.C.LTD | 6.98 | 0 | 0 | 0
934 | MALDAH | Malda Mechanical | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16382 | Augmentation | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-XII and Arsenic Iron Removal Plant at Uttar Chandipur (Zone-II) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019387) | 2680/MLMD | 11/08/2023 | 180 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 60.44 | 0 | 0 | 50
935 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16382 | Augmentation | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-II Piped Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3238/MD | 22/08/2023 | 1042 | M/S N. C. SARKAR | 442.76 | 0 | 0 | 25
936 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16382 | Augmentation | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-II Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | 2919/MD | 10/06/2024 | 386 | M/S N. C. SARKAR | 34.1 | 0 | 0 | 0
937 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16382 | Augmentation | Construction of Approach Road at Head Work site of Uttar Chandipur Zone-II Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | 272/MD | 11/01/2024 | 264 | M/S N. C. SARKAR | 3.91 | 0 | 0 | 100
938 | MALDAH | Malda Mechanical | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME , SM/15948 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no.II & IV and making compound lighting arrangement at H/W site Augumentation of Bhingal Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017675) | 2736/MLMD | 14/08/2023 | 180 | SHREE BISHNU CONSTRUCTION | 22.69 | 0 | 0 | 0
939 | MALDAH | Malda Division | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME , SM/15948 | Augmentation | Material Requisition To Resource Division | 1610/MD | 11/04/2023 | 0 | Resource Division | 4.52 | 0 | 0 | 0
940 | MALDAH | Malda Division | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME , SM/15948 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 8.78 | 0 | 0 | 0
941 | MALDAH | Malda Division | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME , SM/15948 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bhingole Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 5404/MD | 21/10/2024 | 45 | MAHA MAYA CONSTRUCTION | 21.72 | 0 | 0 | 0
942 | MALDAH | Malda Division | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME , SM/15948 | Augmentation | Construction of Boundary Wall at Head Work site of Bhingole Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 3446/MD | 11/07/2024 | 30 | M/S TEWARI CONSTRUCTION | 37.37 | 0 | 0 | 0
943 | MALDAH | Malda Mechanical | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME , SM/15948 | Augmentation | Supply, installation & commissioning of electro-mechanical components at T/W no. I, Augmentation of Bhingal Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017675) | 2722/MLMD | 14/08/2023 | 180 | CHOWDHURY CONCERN | 4.42 | 0 | 0 | 100
944 | MALDAH | Malda Mechanical | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME , SM/15948 | Augmentation | New service connection at BHINGOL T/W NO IV Under EE/MLMD PHE DTE DIST. Malda.( Harishchandrapur c c c) | BP-2024-25-189 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.65 | 0 | 0 | 0
945 | MALDAH | Malda Division | AUGMENTATION OF BHINGOL PIPED WATER SUPPLY SCHEME , SM/15948 | Augmentation | Augmentation work of Pump House and Boundary Wall of Bhingole Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1033/MD | 18/03/2025 | 75 | BINA CONSTRUCTION | 10.95 | 0 | 0 | 0
946 | MALDAH | Malda Mechanical | Augmentation of Adina Zone-I Piped Water Supply Scheme , SM/15958 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Adina Zone-I Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011889) | 2719/MLMD | 14/08/2023 | 2005 | SUNRISE ENGINEERING CORPORATION. | 28.74 | 0 | 0 | 0
947 | MALDAH | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme , SM/15958 | Augmentation | Acceptance cum formal work order for Route survey, design and preparation of DPR of Adina Zone-I Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | 648/MD | 22/03/2022 | 15 | TECHVISION | 3.04 | 0 | 0 | 1
948 | MALDAH | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme , SM/15958 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 34.17 | 0 | 0 | 0
949 | MALDAH | Malda Mechanical | Augmentation of Adina Zone-I Piped Water Supply Scheme , SM/15958 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Adina Zone-I, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-676 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 8.67 | 0 | 0 | 0
950 | MALDAH | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme , SM/15958 | Augmentation | Formal work order for the work of Augmentation of ADINA ZONE-I Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2322/MD | 08/06/2023 | 840 | M/S TRILOCHAN CONSTRUCTION CO | 348.95 | 0 | 0 | 35
951 | MALDAH | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme , SM/15958 | Augmentation | Continuation work order Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 15/12/2024 to 31/12/2024). | 6291/MD | 11/12/2024 | 17 | RUQAIYA ENTERPRISE | 0.08 | 0 | 0 | 0
952 | MALDAH | Malda Division | Augmentation of Adina Zone-I Piped Water Supply Scheme , SM/15958 | Augmentation | Construction of Boundary Wall at Head Work site of Adina Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 162/MD | 08/01/2024 | 219 | M/S PARIMAL DAS | 21.89 | 0 | 0 | 85
953 | MALDAH | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED , SM/17178 | New | Material Requisition To Resource Division | 633/MAAD | 05/04/2023 | 0 | Resource Division | 42.92 | 0 | 0 | 0
954 | MALDAH | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED , SM/17178 | New | Laying of Distribution System at Chowdhuri Tola for Mobarakpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 1473/MAAD | 01/08/2023 | 90 | A. K. CONSTRUCTION | 43.94 | 0 | 0 | 95
955 | MALDAH | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED , SM/17178 | New | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Mobarakpur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1696/MAAD | 19/11/2024 | 50 | BINA CONSTRUCTION | 66.6 | 0 | 0 | 0
956 | MALDAH | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED , SM/17178 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Mobarakpur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | 1471/MAAD | 01/08/2023 | 45 | A ONE ENTERPRISE | 14.79 | 0 | 0 | 100
957 | MALDAH | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED , SM/17178 | New | Laying of Distribution System at Jahantola, Narasinghatola, Rabiramtola for Mobarakpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 1474/MAAD | 01/08/2023 | 425 | GOBINDA ENTERPRISE | 42.15 | 0 | 0 | 92
958 | MALDAH | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED , SM/17178 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Mobarakpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda | 1472/MAAD | 01/08/2023 | 366 | M/S EHAN ENTERPRISE | 5.02 | 0 | 0 | 100
959 | MALDAH | Malda Ars Area W/S Division | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED , SM/17178 | New | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Mobarakpur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. .(3rd Call) | 3081/MAAD | 14/12/2023 | 474 | M/S PARIMAL DAS | 212.51 | 0 | 0 | 70
960 | MALDAH | Malda Mechanical | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED , SM/17178 | New | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Mabarakpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte | 97/MLMD | 11/01/2024 | 476 | HANNAN BUILDERS PVT. LTD. | 70.67 | 0 | 0 | 50
961 | MALDAH | Malda Mechanical | Mabarakpur Mouza Piped water supply Scheme of Kaliachak-II block under Malda Arsenic area water Supply Division, PHED , SM/17178 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 2083/MLMD | 30/04/2025 | 61 | SUBRATA SAHA | 0.78 | 0 | 0 | 0
962 | MALDAH | Malda Ars Area W/S Division | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED , SM/18418 | New | Route servey & design for prepration of DPR of Uttar & Dakshin Jadupur, Purba Saidpur & Arapur Piped Water Supply Scheme at Englishbazar & Manikchak Development Block under Malda Arsenic Area W/S Division, PHE Dte. in the district of Malda. | 1762/MAAD | 30/09/2023 | 15 | FUTURE | 0.99 | 0 | 0 | 100
963 | MALDAH | Malda Ars Area W/S Division | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED , SM/18418 | New | Material Requisition To Resource Division | 631/MAAD | 05/04/2023 | 0 | Resource Division | 147.11 | 0 | 0 | 0
964 | MALDAH | Malda Ars Area W/S Division | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED , SM/18418 | New | Laying of Distribution System at Dilalpur under Uttar Jadupur Piped Water supply scheme at English Bazar under Malda Arsenic Area W/S Division, P.H.E.Dte. | 1492/MAAD | 04/08/2023 | 90 | ABANI BHUSAN GHOSH | 41.08 | 0 | 0 | 75
965 | MALDAH | Malda Ars Area W/S Division | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED , SM/18418 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Uttar Jadupur Piped Water supply scheme at Head Work Site of English Bazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. in the District of Malda. | 1481/MAAD | 01/08/2023 | 45 | M/S DYNAMIC CONSTRUCTION | 7.65 | 0 | 0 | 100
966 | MALDAH | Malda Ars Area W/S Division | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED , SM/18418 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Uttar Jadupur Piped Water supply scheme at 2nd Site of English Bazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. in the District of Malda. | 1482/MAAD | 01/08/2023 | 45 | M/S DYNAMIC CONSTRUCTION | 7.65 | 0 | 0 | 100
967 | MALDAH | Malda Ars Area W/S Division | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED , SM/18418 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Uttar Jadupur Piped Water supply scheme at 3rd Site of English Bazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. in the District of Malda. | 1483MAAD | 01/08/2023 | 45 | M/S DYNAMIC CONSTRUCTION | 7.65 | 0 | 0 | 100
968 | MALDAH | Malda Ars Area W/S Division | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED , SM/18418 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 3rd Tube Well site of Uttar Jadupur Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 1485/MAAD | 01/08/2023 | 60 | GIRIDHARI CONSTRUCTION | 5 | 0 | 0 | 100
969 | MALDAH | Malda Ars Area W/S Division | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED , SM/18418 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Uttar Jadupur Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 1484/MAAD | 01/08/2023 | 60 | DEY CONSTRUCTIONS | 5 | 0 | 0 | 100
970 | MALDAH | Malda Mechanical | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED , SM/18418 | New | QUOTATION PAYMENT FOR Uttar Jadupur T/W No-2 UNDER MOKDUMPUR CCC UNDER MALDA DISTRICT | BP-2024-25-34 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.82 | 0 | 0 | 0
971 | MALDAH | Malda Mechanical | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED , SM/18418 | New | QUOTATION PAYMENT FOR Uttar Jadupur T/W No-3 UNDER MOKDUMPUR CCC UNDER MALDA DISTRICT | BP-2024-25-36 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 4.82 | 0 | 0 | 0
972 | MALDAH | Malda Mechanical | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED , SM/18418 | New | QUOTATION PAYMENT FOR Uttar Jadupur T/W No1 UNDER MOKDUMPUR CCC UNDER MALDA DISTRICT | BP-2024-25-35 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 5.12 | 0 | 0 | 0
973 | MALDAH | Malda Mechanical | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED , SM/18418 | New | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I, II & III and Arsenic Iron Removal Plant at Uttar Jadupur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017806) | 2678/MLMD | 11/08/2023 | 711 | WEST BENGAL ENGINEERING COMPANY. | 82.31 | 0 | 0 | 20
974 | MALDAH | Malda Ars Area W/S Division | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED , SM/18418 | New | Construction of 700 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Uttar Jadupur Piped Water Supply scheme at English Bazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. (2nd Call) | 1583/MAAD | 28/08/2023 | 270 | BANIK BROTHERS | 290.34 | 0 | 0 | 10
975 | MALDAH | Malda Ars Area W/S Division | Uttar Jadupur piped water supply Scheme of English Bazar block under Malda Arsenic Area water supply Division, PHED , SM/18418 | New | Laying of Distribution System at Sonatala, Kechuahi, Jaharpur, Uttar Jadupur,, Model Colony & Nayagram Uttar Jadupur Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area W/S Division, P.H.E.Dte. | 1493/MAAD | 04/08/2023 | 681 | FUTURE | 96.7 | 0 | 0 | 75
976 | MALDAH | Malda Division | Augmentation of Samsi PWSS. , SM/18447 | Augmentation | Continuation work order for the work of Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/11/2023 to 30/04/2024). | 4428/MD | 30/10/2023 | 183 | SHABNAM ARA | 0.86 | 0 | 0 | 56
977 | MALDAH | Malda Division | Augmentation of Samsi PWSS. , SM/18447 | Augmentation | Sinking of 200 mm (all through) Big Dia. Tube-Well of 120 M Deep at Tubewell No-1of Samsi Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 4809/MD | 13/09/2024 | 30 | ASHIS CONSTRUCTION | 8.5 | 0 | 0 | 0
978 | MALDAH | Malda Division | Augmentation of Samsi PWSS. , SM/18447 | Augmentation | Sinking of 200 mm (all through) Big Dia. Tube-Well of 120 M Deep at Tubewell No-2 of Samsi Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 4810/MD | 13/09/2024 | 30 | ASHIS CONSTRUCTION | 8.5 | 0 | 0 | 100
979 | MALDAH | Malda Division | Augmentation of Samsi PWSS. , SM/18447 | Augmentation | Sinking of 200 mm (all through) Big Dia. Tube-Well of 120 M Deep at Samsi Hospital of Samsi Zone-I PWSS under Ratua-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 4811/MD | 13/09/2024 | 30 | ABHIJIT PAUL | 8.5 | 0 | 0 | 100
980 | MALDAH | Malda Division | Augmentation of Samsi PWSS. , SM/18447 | Augmentation | Material Requisition To Resource Division | 818/MD | 21/02/2024 | 0 | Resource Division | 98.17 | 0 | 0 | 0
981 | MALDAH | Malda Division | Augmentation of Samsi PWSS. , SM/18447 | Augmentation | Material Requisition To Resource Division | 358/MD | 16/01/2024 | 0 | Resource Division | 30.48 | 0 | 0 | 0
982 | MALDAH | Malda Division | Augmentation of Samsi PWSS. , SM/18447 | Augmentation | Formal work order for the work of Augmentation of SAMSI (Zone-I & II) Piped Water Supply Scheme at Ratua-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3014/MD | 08/08/2023 | 995 | DUTTA ENTERPRISE | 1066.35 | 0 | 0 | 38
983 | MALDAH | Malda Mechanical | Augmentation of Samsi PWSS. , SM/18447 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I, II, III & IV of Samsi (Zone-I) Water Supply Scheme and making compound lighting arrangement at Head Work Site in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008164) | 2572/MLMD | 04/08/2023 | 937 | GHOSH BROTHERS... | 44.09 | 0 | 0 | 0
984 | MALDAH | Malda Mechanical | Augmentation of Samsi PWSS. , SM/18447 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at Head worksite of Samsi (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008164) | 2571/MLMD | 04/08/2023 | 932 | SUDIP DEY | 24.47 | 0 | 0 | 75
985 | MALDAH | Malda Division | Augmentation of Samsi PWSS. , SM/18447 | Augmentation | 1st layer Land Development Work at Head Work site of Samsi Zone-II Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 6622 | 31/12/2024 | 30 | M/S FOUR STAR CONSTRUCTION | 0.95 | 0 | 0 | 100
986 | MALDAH | Malda Mechanical | Augmentation of Samsi PWSS. , SM/18447 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 1275/MLMD | 27/02/2025 | 61 | SUBRATA SAHA | 0.78 | 0 | 0 | 0
987 | MALDAH | Malda Division | Augmentation of Samsi PWSS. , SM/18447 | Augmentation | Erection of Property board and dissemination of Property information through pipe painting related to Jal Jeevan Mission works of Debipur, Kahala, Mahanandatola, Ratua & Samsi GP under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 658/MD | 19/02/2025 | 7 | M/S TEWARI CONSTRUCTION | 0.97 | 0 | 0 | 0
988 | MALDAH | Malda Mechanical | HATNAGAR PIPED WATER SUPPLY SCHEME , SM/18496 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Hatnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004466956 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 4.45 | 0 | 0 | 100
989 | MALDAH | Malda Mechanical | HATNAGAR PIPED WATER SUPPLY SCHEME , SM/18496 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Hatnagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004466995 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 3.46 | 0 | 0 | 100
990 | MALDAH | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME , SM/18496 | New | Material Requisition To Resource Division | 247/MD | 10/01/2024 | 0 | Resource Division | 8.25 | 0 | 0 | 0
991 | MALDAH | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME , SM/18496 | New | Material Requisition To Resource Division | 817/MD | 21/02/2024 | 0 | Resource Division | 32.68 | 0 | 0 | 0
992 | MALDAH | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME , SM/18496 | New | Formal work order for the work of Implementation of HATNAGAR Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3104/MD | 10/08/2023 | 876 | M/S GUPTA ENTERPRISE | 628.84 | 0 | 0 | 70
993 | MALDAH | Malda Mechanical | HATNAGAR PIPED WATER SUPPLY SCHEME , SM/18496 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No. I of Hatnagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/020336) | 2822/MLMD | 17/08/2023 | 863 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 31.01 | 0 | 0 | 35
994 | MALDAH | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME , SM/18496 | New | Formal work order for the work of Providing Functional Household Tap Connection (FHTC), Laying of Distribution Pipeline and allied works in connection with Jal Jeevan Mission (JJM) at Hatnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 66/MD | 13/01/2025 | 443 | M/S GUPTA ENTERPRISE | 241.12 | 0 | 0 | 20
995 | MALDAH | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME , SM/18496 | New | Construction of Boundary Wall at Head Work site of Hatnagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 832/MD | 06/03/2025 | 209 | M/S GUPTA ENTERPRISE | 30.13 | 0 | 0 | 0
996 | MALDAH | Malda Division | HATNAGAR PIPED WATER SUPPLY SCHEME , SM/18496 | New | Dedicated Pipe laying for better Functionality and Providing Balance FHTC for HATNAGAR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. Govt. of West Bengal. | 3771/MD | 04/08/2025 | 60 | M/S GUPTA ENTERPRISE | 91.12 | 0 | 0 | 0
997 | MALDAH | Malda Mechanical | RAHIMPUR Piped Water Supply Scheme , SM/14174 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Rahimpur PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004390718 | 16/08/2023 | 90 | W.B.S.E.D.C.LTD | 18.35 | 0 | 0 | 100
998 | MALDAH | Malda Mechanical | RAHIMPUR Piped Water Supply Scheme , SM/14174 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of RAHIMPUR PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004390672 | 11/08/2023 | 90 | W.B.S.E.D.C.LTD | 5.39 | 0 | 0 | 100
999 | MALDAH | Malda Division | RAHIMPUR Piped Water Supply Scheme , SM/14174 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 14.65 | 0 | 0 | 0
1000 | MALDAH | Malda Division | RAHIMPUR Piped Water Supply Scheme , SM/14174 | New | Construction of Boundary Wall at 2nd Tube Well site of Rahimpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 2954/MD | 10/06/2024 | 236 | M/S AMIT KUMAR GUPTA | 7.17 | 0 | 0 | 50
1001 | MALDAH | Malda Division | RAHIMPUR Piped Water Supply Scheme , SM/14174 | New | Material Requisition To Resource Division | 28/MD | 04/01/2024 | 0 | Resource Division | 16.25 | 0 | 0 | 0
1002 | MALDAH | Malda Division | RAHIMPUR Piped Water Supply Scheme , SM/14174 | New | Formal work order for the work of Implementation of Rahimpur Piped Water Supply Scheme at Gazol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1571/MD | 10/04/2023 | 992 | M/S GUPTA ENTERPRISE | 841.12 | 0 | 0 | 90
1003 | MALDAH | Malda Mechanical | RAHIMPUR Piped Water Supply Scheme , SM/14174 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Rahimpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015255) | 2326/MLMD | 26/07/2023 | 786 | JAL PRAVAHIKA PVT. LTD. | 28.25 | 0 | 0 | 84
1004 | MALDAH | Malda Division | RAHIMPUR Piped Water Supply Scheme , SM/14174 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Rahimpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 5911/MD | 26/11/2024 | 309 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 48.65 | 0 | 0 | 20
1005 | MALDAH | Malda Division | RAHIMPUR Piped Water Supply Scheme , SM/14174 | New | Construction of Boundary Wall at Head Work site of Rahimpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 831/MD | 06/03/2025 | 209 | M/S GUPTA ENTERPRISE | 28.39 | 0 | 0 | 60
1006 | MALDAH | Malda Division | RAHIMPUR Piped Water Supply Scheme , SM/14174 | New | Dedicated Pipe laying for better Functionality and Providing Balance FHTC for RAHIMPUR Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 3770/MD | 04/08/2025 | 150 | M/S GUPTA ENTERPRISE | 11.35 | 0 | 0 | 0
1007 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ALTOR Water Supply Scheme , SM/06852 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ALTOR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | 2713/MAAD | 10/11/2020 | 45 | MANIK CHANDRA SAHA | 68.5 | 27.33 | 100 | 0
1008 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ALTOR Water Supply Scheme , SM/06852 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Bibijhuti, JL. No. 58, G.P.-Kharba of KENDUA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 283/MD | 28/01/2021 | 30 | ANUKUL CHANDRA DAS | 9.41 | 0 | 0 | 1
1009 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ALTOR Water Supply Scheme , SM/06852 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Altor Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 3364/MD | 29/08/2023 | 45 | M/S BABLU ENTERPRISE | 18.17 | 0 | 0 | 80
1010 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ALTOR Water Supply Scheme , SM/06852 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Altore Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 5738/MD | 20/11/2024 | 346 | SAMBHU NATH SARKAR | 42.53 | 0 | 0 | 0
1011 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ALTOR Water Supply Scheme , SM/06852 | Retrofitting | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 40 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Altor Water Supply Scheme of Gazole Dev. Block under Malda Division P.H.E Dte in the District of Malda. | 2619/MD | 02/06/2025 | 135 | M/S AMIT KUMAR GUPTA | 18.01 | 0 | 0 | 0
1012 | MALDAH | Malda Mechanical | NABAGRAM Piped Water Supply Scheme , SM/12767 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of NABAGRAM PWSS, Chanchal C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004407809 | 11/09/2023 | 90 | W.B.S.E.D.C.LTD | 12.15 | 0 | 0 | 100
1013 | MALDAH | Malda Mechanical | NABAGRAM Piped Water Supply Scheme , SM/12767 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Nabagram, Chanchal C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004460870 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 3.46 | 0 | 0 | 100
1014 | MALDAH | Malda Division | NABAGRAM Piped Water Supply Scheme , SM/12767 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 21.33 | 0 | 0 | 0
1015 | MALDAH | Malda Mechanical | NABAGRAM Piped Water Supply Scheme , SM/12767 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Nabagram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013452) | 2566/MLMD | 04/08/2023 | 787 | DAS ENTERPRISE. | 29.85 | 0 | 0 | 87
1016 | MALDAH | Malda Division | NABAGRAM Piped Water Supply Scheme , SM/12767 | New | Material Requisition To Resource Division | 89/MD | 05/01/2024 | 0 | Resource Division | 18.48 | 0 | 0 | 0
1017 | MALDAH | Malda Division | NABAGRAM Piped Water Supply Scheme , SM/12767 | New | Construction of Boundary Wall at 2nd Tube Well site of Nabagram Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 2933/MD | 10/06/2024 | 30 | M/S BHARATI CONSTRUCTION | 7.23 | 0 | 0 | 80
1018 | MALDAH | Malda Division | NABAGRAM Piped Water Supply Scheme , SM/12767 | New | Construction of Boundary Wall at Head Work site of Nabagram Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | 2688/MD | 04/06/2025 | 45 | MODERN CO-OPERATIVE LABOUR CONTRCT & CONSTRUCTION SOCIETY LIMITED. | 34.99 | 0 | 0 | 0
1019 | MALDAH | Malda Division | NABAGRAM Piped Water Supply Scheme , SM/12767 | New | Restoration of Road at Bhagabatipur Mouza of Nabagram Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 3632/MD | 24/07/2025 | 45 | M/S FOUR STAR CONSTRUCTION | 12.6 | 0 | 0 | 0
1020 | MALDAH | Malda Division | NABAGRAM Piped Water Supply Scheme , SM/12767 | New | Additional Laying Distribution of UPVC pipe line of NABAGRAM Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, P.H.E Dte. | 710/MD | 09/02/2024 | 143 | RATAN KARMAKAR | 4.11 | 0 | 0 | 90
1021 | MALDAH | Malda Division | NABAGRAM Piped Water Supply Scheme , SM/12767 | New | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160m Deep at Nabagram PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 3450/MD | 10/07/2024 | 73 | A. L. ENGINEERING SOLUTION | 10.44 | 0 | 0 | 95
1022 | MALDAH | Malda Mechanical | PARAIL PWSS , SM/18431 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Parail Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014391) | 2392/MLMD | 28/07/2023 | 180 | ALPHA ENTERPRISE. | 28.69 | 0 | 0 | 0
1023 | MALDAH | Malda Division | PARAIL PWSS , SM/18431 | New | Material Requisition To Resource Division | 813/MD | 21/02/2024 | 0 | Resource Division | 39.07 | 0 | 0 | 0
1024 | MALDAH | Malda Division | PARAIL PWSS , SM/18431 | New | Material Requisition To Resource Division | 235/MD | 10/01/2024 | 0 | Resource Division | 7.35 | 0 | 0 | 0
1025 | MALDAH | Malda Mechanical | PARAIL PWSS , SM/18431 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Parail, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-707 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 22.02 | 0 | 0 | 0
1026 | MALDAH | Malda Division | PARAIL PWSS , SM/18431 | New | Formal work order for the work of Implementation of PARAIL Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3008/MD | 07/08/2023 | 1025 | M/S TAPAS KUMAR CHAKRABORTY & CO | 1011.34 | 0 | 0 | 55
1027 | MALDAH | Malda Division | PARAIL PWSS , SM/18431 | New | Construction of Boundary Wall at Head Work site of Parail Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3212/MD | 27/06/2024 | 641 | M/S JHA CONSTRUCTION | 26.23 | 0 | 0 | 70
1028 | MALDAH | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Formal Work Order for Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries at Boosting Pumping Station, Niyamatpur ( for Zonal OHRS of English Bazar Block) under Augmentation of Surface Water Based Piped Water Supply Scheme (Northeren Sector), District - Malda, PHE Dte. | 2667/MLMD | 10/08/2023 | 180 | ORIENTAL ENGINEERING CO. | 546.37 | 0 | 0 | 0
1029 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Material Requisition To Resource Division | 494/MAAD | 23/03/2023 | 0 | Resource Division | 13510.42 | 0 | 0 | 0
1030 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Material Requisition To Resource Division | 1716/MAAD | 21/09/2023 | 0 | Resource Division | 21.3 | 0 | 0 | 0
1031 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Material Requisition To Resource Division | 1973/MAAD | 30/10/2023 | 0 | Resource Division | 20.22 | 0 | 0 | 0
1032 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.09.2023 to 02.03.2024) | 1552/MAAD | 18/08/2023 | 184 | UNITED ENGINEERS CORPORATION | 0.87 | 0 | 0 | 0
1033 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2023 to 31.12.2023) | 2294/MAAD | 28/12/2022 | 365 | M/S PARIMAL DAS | 1.73 | 0 | 0 | 100
1034 | MALDAH | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 1343/MLMD | 26/04/2024 | 61 | NITAI PANDEY | 0.78 | 0 | 0 | 0
1035 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for BAHIRBONAScheme (Capacity-450 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | 816/MAAD | 22/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 0 | 0 | 5
1036 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for MOHABBATPUR Scheme (Capacity-500 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | 739/MAAD | 19/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 0 | 0 | 5
1037 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for SULTANGANJ Scheme (Capacity-600 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | 815/MAAD | 22/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 0 | 0 | 5
1038 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for MOKSADPUR Scheme (Capacity-1250 cum) in Kaliachak-I Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | 817/MAAD | 22/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 0 | 0 | 5
1039 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for UTTAR CHANDIPUR Scheme (Capacity-750 cum) in English Bazar Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | 737/MAAD | 19/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 0 | 0 | 100
1040 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for SATANGAPARA Scheme (Capacity-600 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | 738/MAAD | 19/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 0 | 0 | 5
1041 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for JAYENPUR Scheme (Capacity-400 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | 814/MAAD | 22/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 0 | 0 | 5
1042 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for CHARIANANTAPUR Scheme (Capacity-500 cum) in Kaliachak-III Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | 740/MAAD | 19/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 0 | 0 | 5
1043 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for BRAHMONGRAM Scheme (Capacity-450 cum) in Manikchak Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | 735/MAAD | 19/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 0 | 0 | 100
1044 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Vetting of Soil Investigation Report and Recommendation of foundation for Construction of OHR for PASCHIMNARAYANPUR Scheme (Capacity-300 cum) in Manikchak Block under "Augmentation of Surface Water Based Piped Water Supply Scheme for Malda Arsenic Area (Northern & Southern Sector)". | 736/MAAD | 19/04/2024 | 30 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR | 1.3 | 0 | 0 | 5
1045 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Material Requisition To Resource Division | 1612/MAAD | 04/10/2024 | 0 | Resource Division | 125.49 | 0 | 0 | 0
1046 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Material Requisition To Resource Division | 1032/MAAD | 16/05/2024 | 0 | Resource Division | 1906.64 | 0 | 0 | 0
1047 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Material Requisition To Resource Division | 216/MAAD | 23/02/2024 | 0 | Resource Division | 2555.83 | 0 | 0 | 0
1048 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Restoration of damaged PWD road for Chainage 18.00 KM to 220..00 Km to 30.00 KM and chainage 30.00 KM to 32.50 KM in Laying of water rising main at SH-10 under Augmentation of surface water based piped water supply scheme for Malda Arsenic Area (Northern & Southern Sector). | C062409333417 | 11/06/2024 | 0 | EXUCUTIVE ENGINEER PWD MALDA | 54.95 | 0 | 0 | 0
1049 | MALDAH | Malda Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | The payment to WBSRDA against the repair of damaged roads. |  | 11/11/2024 | 0 | EXECUTIVE ENGINEER, HPIU, WBSRDA, MALDA DIVISION | 6 | 0 | 0 | 0
1050 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Quotation the shifting of LTOH line above newly constructing pipe line. | C022455072524 | 20/02/2024 | 0 | W.B.S.E.D.C.LTD | 0.81 | 0 | 0 | 0
1051 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
1052 | MALDAH | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Modification of existing High Lift pumping station and Sub-station at Mathurapur (for Zonal OHRS of Manikchak Block) under Augmentation of Surface Water Based Piped Water Supply Scheme (Northern Sector) Dist. Malda, PHE Dte. | 2669/MLMD | 10/08/2023 | 720 | WEST BENGAL ENGINEERING COMPANY. | 353.77 | 0 | 0 | 73
1053 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Continuation Work Order for Placing of diesel driven Car on hire basis for official use of the Executive Engineer, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(for the period from 01.01.2024 to 30.12.2024)= 365 days | 3290/MAAD | 29/12/2023 | 365 | NITAI PANDEY | 1.73 | 0 | 0 | 10
1054 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Continuation Work Order for Placing of diesel driven Car on hire basis for the official use of the Assistant Engineer-I, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte. (for the period from 01.01.2024 to 30.12.2024)= 365 days. | 3289/MAAD | 29/12/2023 | 365 | SUBRATA SAHA | 1.73 | 0 | 0 | 40
1055 | MALDAH | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Formal work order for Installation of 33KV terminal arrangement with 36KV indoor type equipments (non-extensible type) with VCB, CT, PT etc. at Sub-Station of Shyamdaspur Boosting Station for augmentation of PWSS for Malda Arsenic Affected Area at District Malda (Northern & Southern Sector). | 1693/MLMD | 28/03/2025 | 92 | ORIENTAL ENGINEERING CO. | 38.62 | 0 | 0 | 0
1056 | MALDAH | Malda Mechanical | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Formal work order for Installation of 33KV terminal arrangement with 36KV indoor type equipments (non-extensible type) with VCB, CT, PT etc. at Sub-Station of Mathurapur WTP site for augmentation of PWSS for Malda Arsenic Affected Area at District Malda (Northern & Southern Sector). | 1694/MLMD | 28/03/2025 | 92 | WEST BENGAL ENGINEERING COMPANY. | 38.92 | 0 | 0 | 0
1057 | MALDAH | Malda Ars Area W/S Division | AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR MALDAH ARSENIC AREA (NORTHERN & SOUTHERN SECTOR) , SM/18660 | Augmentation | Supply of different DI materials for the work of "Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II& III Blocks in the district of Malda." | 1163/MAAD | 07/06/2024 | 265 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 76.96 | 0 | 0 | 50
1058 | MALDAH | Malda Division | Augmentation of Bejpura Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18910 | Augmentation | Construction of 400 M3 Capacity, 20mtr. staging height RCC Elevated Service Reservoir as per Departmental type design (Ref :- DRG.No. PC/-I/OHR/11/2012) including delivery, inlet & overflow pipe connection etc. all complete for piped water supply scheme of BEJPURA PWSS at Harishchandrapur-II Block in the District of Malda, under Malda Division, PHE Dte. | 4556/MD | 30/08/2024 | 669 | NILMANI BASAK | 131.79 | 0 | 0 | 25
1059 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15308 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 72.43 | 0 | 0 | 0
1060 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15308 | Augmentation | Formal work order for the work of Implementation of UTTAR CHANDIPUR ZONE-IV A Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1850/MD | 03/05/2023 | 975 | BANIK BROTHERS | 341.23 | 0 | 0 | 22
1061 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15308 | Augmentation | Laying of Rising Main including Specials and Valves for Uttar Chandipur Zone-IV A Piped Water Supply Scheme at Manikchak Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 164/MD | 08/01/2024 | 45 | J. M. CONSTRUCTION | 10.08 | 0 | 0 | 95
1062 | MALDAH | Malda Mechanical | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15308 | Augmentation | QUOTATION PAYMENT FOR UTTARCHANDIPUR ZONE IV-A AIRP UNDER MANIKCHAK CCC UNDER MALDA DISTRICT | BP-2024-25-415 | 30/07/2024 | 0 | W.B.S.E.D.C.LTD | 5.76 | 0 | 0 | 0
1063 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15308 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Uttar Chandipur Zone-IV B Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | 7812/MD | 11/06/2025 | 60 | BEE GEE CONSTRUCTION | 121.68 | 0 | 0 | 0
1064 | MALDAH | Malda Mechanical | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15308 | Augmentation | Supply,delivery, installation and trial operation of Arsenic Iron Removal Plant at Uttar Chandipur (Zone-IV A) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019389) | 2682/MLMD | 11/08/2023 | 180 | EASTERN INDIA SALES & SERVICE. | 52.42 | 0 | 0 | 20
1065 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15308 | Augmentation | Formal work order for the work of Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 75M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-IVA Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | 1079/MD | 13/03/2024 | 624 | DUTTA ENTERPRISE | 188.41 | 0 | 0 | 0
1066 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15308 | Augmentation | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-IV-A Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | 1515/MD | 16/03/2024 | 657 | BANIK BROTHERS | 28.69 | 0 | 0 | 0
1067 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- IV A Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15308 | Augmentation | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-IV-B Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | 1516/MD | 16/03/2024 | 472 | M/S N. C. SARKAR | 26.44 | 0 | 0 | 0
1068 | MALDAH | Malda Division | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12315 | Augmentation | Acceptance cum formal work order for Sinking of (200mm. Dia. x 150mm. Dia) Tube Well no-3 ( 70 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at PANNAPUR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | 2299/MD | 28/09/2022 | 30 | MECHANO TRADING CO. | 5.25 | 0 | 0 | 0
1069 | MALDAH | Malda Division | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12315 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of PANNAPUR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | 3112/MD | 20/12/2022 | 45 | HIRAK ROY CHOUDHURY | 6.69 | 0 | 0 | 0
1070 | MALDAH | Central Drilling | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12315 | Augmentation | Resistivity survey for Sankail PWSS, Basara PWSS and Pannapur PWSS at Habibipur & Bamongola block under Malda district, CMSD-II (D), CDD, PHE Dte. | 135/CMSD-II(D) | 24/05/2023 | 15 | S B S ENTERPRISE | 0.82 | 0 | 0 | 100
1071 | MALDAH | Malda Division | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12315 | Augmentation | Material Requisition To Resource Division | 2405/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0 | 0
1072 | MALDAH | Malda Mechanical | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12315 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Pannapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012801) | 2393/MLMD | 28/07/2023 | 830 | SUBRATA KUMAR DAS. | 10.44 | 0 | 0 | 40
1073 | MALDAH | Malda Division | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12315 | Augmentation | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Pannapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 5791/MD | 21/11/2024 | 45 | DEY CONSTRUCTION | 36.95 | 0 | 0 | 0
1074 | MALDAH | Malda Division | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12315 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damage A.C pipe lineby different dia UPVC pipe for PANNAPUR Piped Water Supply Scheme ( Nimnail, Jahanabad) of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | 2605/MD | 10/11/2022 | 45 | MANIK CHANDRA SAHA | 69.14 | 0 | 0 | 88
1075 | MALDAH | Malda Mechanical | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12315 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Pannapur, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-421 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 8.39 | 0 | 0 | 0
1076 | MALDAH | Malda Division | Source Augmentation of Pannapur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12315 | Augmentation | Sinking of ( 250 mm Dia. X 200 mm Dia.) Tubewell No.-3 (250 M deep) by D.R Rig. Method using P.V.C. pipe & Gravel Filter including Supply of materials at PANNAPUR Water Supply Scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | 885/MD | 27/02/2024 | 347 | A. L. ENGINEERING SOLUTION | 14.82 | 0 | 0 | 100
1077 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Balupur Zone-III Water Supply Scheme at Ratua-I under Malda Division, PHE Dte. | 2379/MD | 13/08/2021 | 30 | FUTURE | 13.48 | 0 | 0 | 0
1078 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHANPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | 554/MD | 12/02/2021 | 30 | RAY CONSTRUCTION CO. | 57.64 | 40.18 | 100 | 1
1079 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | 520/MSD | 31/12/2021 | 181 | SHYAMAL KUMAR MAITRA | 0.86 | 0 | 0 | 1
1080 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAHARA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 2684/MD | 03/12/2020 | 1 | MADE & TRADE CO. | 0 | 0 | 0 | 1
1081 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for the work of Hiring of 1 no. diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/04/2022 to 27/09/2022) | 797/MD | 01/04/2022 | 180 | USHA ENTERPRISE | 0.86 | 0 | 0 | 1
1082 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | 520/MSD | 31/12/2021 | 6 | SHYAMAL KUMAR MAITRA | 2.16 | 0 | 0 | 0
1083 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for the work of Hiring of 1 no. diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/02/2022 to 31/03/2022) | 232/MD | 27/01/2022 | 59 | USHA ENTERPRISE | 0.28 | 0 | 0 | 1
1084 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Car hiring No. 51C/7999 for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 01/03/2022 to 30/06/2022) | 473/MD | 25/02/2022 | 120 | TARUN KUMAR BHATTACHARYA | 0.58 | 0 | 0 | 1
1085 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Placing of Diesel Driven Car on hire basis for official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. under Malda Division, PHE Dte. in good running condition. (Period from 01/01/2021 to 31/12/2021). | 3280/MD | 30/12/2020 | 365 | SHYAMAL KUMAR MAITRA | 1.73 | 0 | 0 | 1
1086 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Placing of Diesel Driven Bolero Car on hire basis for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/02/2020 to 31/01/2021) | 349/MD | 28/01/2020 | 0 | RANJIT ADHIKARY | 1.51 | 0 | 0 | 1
1087 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of SADLICHAK Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 1962/MD | 31/08/2020 | 30 | BEE GEE CONSTRUCTION | 43.35 | 5.82 | 15.09 | 1
1088 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection under BALUPUR ZONE-II Piped Water Supply Scheme at Ratua-I Block in the district of Malda under Malda Division, PHE Dte. | 512/MD | 09/02/2021 | 60 | JAL PRAVAHIKA PVT. LTD. | 104.87 | 0 | 0 | 0
1089 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Balupur Zone-I Water Supply Scheme under Malda Division, PHE Dte. | 2378/MD | 13/08/2021 | 30 | ACHARYYA CONSTRUCTION | 13.48 | 0 | 0 | 1
1090 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-II Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. (Phase-I) | 3573/MD | 20/12/2021 | 30 | M/S JHA CONSTRUCTION | 39.81 | 0 | 0 | 1
1091 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. (Phase-I) | 3575/MD | 20/12/2021 | 30 | PABITRA MANDAL | 19.48 | 0 | 0 | 1
1092 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Supplying, fitting and fixing of G.I. pipes of TATA make & Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Bejpura Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 542/CSD | 27/10/2021 | 30 | NEOGI ENTERPRISE | 4.26 | 0 | 0 | 1
1093 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Supplying, fitting and fixing of G.I. pipes of TATA make & Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Jalalpur Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | 545/CSD | 01/11/2021 | 30 | FUTURE | 4.72 | 0 | 0 | 1
1094 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Supplying, fitting and fixing of G.I. pipes of TATA make & Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) for Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Jalalpur Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | 546/CSD | 01/11/2021 | 30 | FUTURE | 2.66 | 0 | 0 | 1
1095 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-III Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. (Phase-I) | 3574/MD | 20/12/2021 | 30 | GOBINDA ENTERPRISE | 19.97 | 0 | 0 | 1
1096 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MOYNA Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | 49/MD | 13/01/2022 | 60 | S. R. CONSTRUCTION | 40.3 | 0 | 0 | 1
1097 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Emergent installation of Sulice Valve & Construction of Sluice Valve & Repairing of FHTC for Khanpur Hulashpur Water Supply Scheme under Malda division, P.H.E. Dte. In the District of Malda. | 31/CSD | 05/01/2022 | 15 | BIDYUT MAHALDAR | 1.27 | 0 | 0 | 1
1098 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) including upvc laying in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of UTTAR CHANDIPUR ZONE-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda (Phase - II). | 742/MD | 28/03/2022 | 30 | FUTURE | 22.06 | 0 | 0 | 1
1099 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Collection of Household Tap Connection details through baseline household Mobile's App( Jal Swapna) under commend area of Kutubsahar Water Supply Scheme of Gazole Block under Malda Division, PHE Dte. | 1899/MD | 30/06/2021 | 120 | RABIUL ISLAM | 10 | 0 | 0 | 0
1100 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAGURA ZONE-I Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. | 2551/MD | 15/10/2020 | 30 | MILLENNIUM ENTERPRISR | 1 | 0 | 0 | 1
1101 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-II Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-II) | 1640/MD | 19/07/2022 | 30 | KRISHNENDU DUTTA | 26.59 | 0 | 0 | 1
1102 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Supply of Stationary articles for the use of Malda District Laboratory. | 368/MD | 10/02/2022 | 1 | MALDA DISTRICT SERVICE CUM-MARKETING INDS. CO-OP UNION LTD. | 1.1 | 0 | 0 | 0
1103 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bejpura Piped Water Supply Scheme (Phase-II) at Harischandrapur - II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 1487/MD | 23/06/2022 | 30 | CHARU CONSTRUCTION | 6.53 | 0 | 0 | 1
1104 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-III Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-II) | 1641/MD | 19/07/2022 | 30 | UTTAM KUMAR GHOSH | 23.82 | 0 | 0 | 1
1105 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Car hiring No. WB 65 A/4911 for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. | 312/NBC-II | 01/04/2022 | 365 | USHA ENTERPRISE | 3.59 | 0 | 0 | 0
1106 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Supply of Forms & Stationary articles for the use of this office. | 3456/MD | 06/12/2021 | 1 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 1.28 | 0 | 0 | 1
1107 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | 522/MSD | 31/12/2021 | 181 | UTTAM KUMAR GHOSH | 0.86 | 0 | 0 | 1
1108 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | 521/MSD | 31/12/2021 | 181 | ARUN KUMAR DAS | 2.16 | 0 | 0 | 0
1109 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Continuation work order for Placing of Diesel Driven Car on hire basis for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. under Malda Division, PHE Dte. in good running condition. (Period from 01/02/2021 to 30/09/2021). | 276/MD | 28/01/2021 | 365 | RANJIT ADHIKARY | 2.66 | 0 | 0 | 0
1110 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Supply of Stationary articles for the use of Malda District Laboratory. | 367/MD | 10/02/2022 | 1 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.35 | 0 | 0 | 1
1111 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BHAIRABPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 2142/MD | 16/09/2020 | 60 | SUBHAS CHANDRA KESHARI | 92.31 | 0 | 0 | 1
1112 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN MAHENDRAPUR Water Supply Scheme at Harishchandrapur-I Block under Malda Division, PHE Dte. | 2683/MD | 06/11/2020 | 45 | MADE & TRADE CO. | 85.01 | 52.58 | 61.85 | 0
1113 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of TALSUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 2255/MD | 29/09/2020 | 90 | TARUN KUMAR BHATTACHARYA | 135.29 | 15 | 15.27 | 0
1114 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/07/2022 to 31/12/2022). | 213/MSD | 30/06/2022 | 184 | UTTAM KUMAR GHOSH | 0.86 | 0 | 0 | 1
1115 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2022 to 30/06/2022). | 521/MSD | 31/12/2021 | 365 | ARUN KUMAR DAS | 0.86 | 0 | 0 | 1
1116 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division, PHE Dte. (Period from 01/07/2022 to 31/12/2022). | 215/MSD | 30/06/2022 | 6 | SHYAMAL KUMAR MAITRA | 0.86 | 0 | 0 | 1
1117 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/07/2022 to 31/12/2022). | 215/1/MSD | 30/06/2022 | 184 | ARUN KUMAR DAS | 4.5 | 0 | 0 | 0
1118 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of MOYNA Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. In the district of Malda. | 2991/MD | 07/12/2022 | 45 | S. R. CONSTRUCTION | 25.41 | 0 | 0 | 0
1119 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Laying of distribution pipe line for Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM) under command area of Bhado of BHADO Water Supply Scheme under Malda Division, PHE Dte. | 2735/MD | 18/11/2022 | 30 | M/S MANDAL & SONS | 6.77 | 0 | 0 | 0
1120 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing car on daily hirer basis @ Rs. 12.00/km for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. | 653/CSD | 07/11/2022 | 365 | SAUDIPTA KUMAR DAS | 4.56 | 0 | 0 | 0
1121 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Continuation work order for the work of hiring of 1 no diesel vehicle in good condition (traffic authority) having licence contract carage permit from regional transport authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte (Period from 28/09/2022 to 26/03/2023) | 1108/MD | 20/09/2022 | 180 | USHA ENTERPRISE | 4.5 | 0 | 0 | 0
1122 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Supply & delivery of Steel Table with Locker and Wooden Top, Office Visitors Chair and High back mesh Executive Chair for the Conference Room of District Laboratory 1st Floor and office of the Superintending Engineer, North Bengal Circle - Il under Malda Division, PHE Dte. | 1712/MD | 20/04/2023 | 15 | M/S PARIMAL DAS | 2.42 | 0 | 0 | 0
1123 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BEJPURA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 2152/MD | 16/09/2020 | 45 | NEOGI ENTERPRISE | 68.33 | 18.14 | 100 | 1
1124 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of JAGANNATHPUR Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 2141/MD | 16/09/2020 | 45 | DEBAPRIYA SAHA | 77.59 | 0 | 0 | 0
1125 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KUTUB SAHAR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | 2135/MD | 16/09/2020 | 90 | HANNAN BUILDERS PVT. LTD. | 145.2 | 0 | 0 | 1
1126 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAHARA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 2684/MD | 06/11/2020 | 60 | MADE & TRADE CO. | 132.4 | 12.49 | 74.63 | 100
1127 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAMBALPUR Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. | 2437/MD | 12/10/2020 | 60 | HANNAN BUILDERS PVT. LTD. | 156.77 | 57.67 | 55.75 | 1
1128 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BHADO Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | 2704/MD | 10/11/2020 | 60 | GHOSH BROTHERS | 148.17 | 0 | 0 | 100
1129 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection under DAULATNAGAR Piped Water Supply Scheme at Harishchandrapur-II Block in the district of Malda under Malda Division, PHE Dte. | 553/MD | 12/02/2021 | 60 | NEOGI ENTERPRISE | 120.32 | 29.47 | 32.56 | 1
1130 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection under BEHERPUR ZONE-I Pipe Water Supply Scheme at Bamangola Block in the district of Malda under Malda Division, PHE Dte. | 435/MD | 08/02/2021 | 60 | PROJECT INDIA | 126.35 | 0 | 0 | 100
1131 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Different dia. Damaged pipe line repair on emergency basis (damage due to widening of road) in connection with annual operation maintenance and providing FHTC to villagers under MEKPUR Piped Water Supply Scheme at Old Malda Dev. block under Malda Division, PHE Dte. | 513/MSD | 31/12/2021 | 1 | A. K. CONSTRUCTION | 2.06 | 0 | 0 | 0
1132 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Replacement of different dia A.C pipe line (damage due to widening of road) by laying of different dia UPVC pipe in connection with annual operation maintenance and providing FHTC to Villagers under RAJARAMPUR Piped Water Supply Scheme of Habibpur Dev. Block in the District of Malda under Malda Division, PHE Dte. | 142/MSD | 31/03/2022 | 2 | SSD CONSTRUCTION | 4.84 | 0 | 0 | 1
1133 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Additional laying work of DI & UPVC pipe line of SADLICHAK W/S Scheme at HARISHCHANDRAPUR-II Dev. Block under Malda division.P.H.E.Dte. In the District of Malda. | 47/CSD | 14/01/2022 | 30 | BEE GEE CONSTRUCTION | 4.19 | 0 | 0 | 1
1134 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DALLA Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 2438/MD | 12/10/2020 | 120 | M/S JHA CONSTRUCTION | 10 | 0 | 0 | 1
1135 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Repairing of existing FHTC connection for Talsur Water Supply Scheme under Malda division.P.H.E.Dte. In the District of Malda. | 330/CSD | 22/06/2022 | 30 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 1.06 | 0 | 0 | 1
1136 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-III) | 1642/MD | 19/07/2022 | 30 | M/S AMIT KUMAR GUPTA | 16.26 | 0 | 0 | 1
1137 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/11/2022 to 30/04/2023). | 2474/MD | 21/10/2022 | 365 | SHABNAM ARA | 4.5 | 0 | 0 | 21
1138 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Divion, PHE Dte. (Period from 10/03/2023 to 09/08/2023). | 1020/MD | 10/03/2023 | 180 | M/S FOUR STAR CONSTRUCTION | 0.86 | 0 | 0 | 100
1139 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 20/02/2023 to 19/08/2023). | 809/MD | 17/02/2023 | 180 | M/S. TEWARI CONSTRUCTION | 0.86 | 0 | 0 | 100
1140 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHANPUR HULASPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. | 48/MD | 13/01/2022 | 21 | BIDYUT MAHALDAR | 7.56 | 0 | 0 | 0
1141 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Material Requisition To Resource Division | 3552/MD | 26/11/2021 | 0 | Resource Division | 8.78 | 0 | 0 | 0
1142 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Material Requisition To Resource Division | 3585/MD | 21/12/2021 | 0 | Resource Division | 6.45 | 0 | 0 | 0
1143 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Material Requisition To Resource Division | 456/MD | 22/02/2022 | 0 | Resource Division | 3.29 | 0 | 0 | 0
1144 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Material Requisition To Resource Division | 1258/MD | 27/05/2022 | 0 | Resource Division | 8.01 | 0 | 0 | 0
1145 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Bill for car hiring no. WB/51C/7999 for office of the Superintending Enginner, North Bengal Circle-II, PHE Dte. For the period from (01/02/2023 to 15/05/2023). | BP-2023-24-108 | 13/07/2023 | 0 | TARUN KUMAR BHATTACHARYA | 1.05 | 0 | 0 | 0
1146 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Bill for reimbursement of cost of Diesel and Mobil in respect of hired vehicle Car No. WB65C/6570, For the month of MAY, 2023. | BP-2023-24-143 | 09/08/2023 | 0 | UTTAM KUMAR GHOSH | 0.4 | 0 | 0 | 0
1147 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Saiyedpur Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 3371/MD | 29/08/2023 | 45 | S. R. CONSTRUCTION | 20.14 | 0 | 0 | 100
1148 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Hiring of 1 no. diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 26/06/2023 to 22/12/2023) | 1452/NBC-II | 21/06/2023 | 181 | USHA ENTERPRISE | 2.19 | 0 | 0 | 42
1149 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BALUPUR ZONE-II & III Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 5247/MD | 22/12/2023 | 45 | M/S. TEWARI CONSTRUCTION | 56.74 | 0 | 0 | 40
1150 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2024 to 30/06/2024). | 1010/MSD | 29/12/2023 | 183 | UTTAM KUMAR GHOSH | 0.86 | 0 | 0 | 25
1151 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2024 to 30/06/2024). | 1011/MSD | 29/12/2023 | 183 | ARUN KUMAR DAS | 0.86 | 0 | 0 | 67
1152 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Continuation of work order for hiring of inspection vehicle(Motor Cab or Maruti Omni Category(Standard,Non-Air Condition, Bharat Stage-III purchase on or after 01.05.2008 with Diesel/LPG/CNG Engine)in perfectly good condition of performing a very long journey and should cover anywhere without any trouble on monthly hire basis for official use of the office of the Assistant Engineer, R.W.S. Malda Sub-Division, PHE Dte.(Period from 01.01.2024 to 30.06.2024) | 431/RWS | 29/12/2023 | 182 | SHYAMAL KUMAR MAITRA | 0.86 | 0 | 0 | 70
1153 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 20/08/2023 to 15/02/2024). | 3225/MD | 18/08/2023 | 180 | M/S. TEWARI CONSTRUCTION | 0.86 | 0 | 0 | 90
1154 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Divion, PHE Dte. (Period from 10/08/2023 to 06/02/2024). | 3029/MD | 08/08/2023 | 180 | M/S FOUR STAR CONSTRUCTION | 0.86 | 0 | 0 | 99
1155 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Magura Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | 3196/MD | 27/06/2024 | 45 | NATIONAL CONSTRUCTION | 26.03 | 0 | 0 | 0
1156 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Extension of UPVC pipe line for Providing Functional Household Tap Connection with Jal Jeevan Mission (JJM) command area of Khanpur Hulashpur Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 3232/MD | 28/06/2024 | 45 | BIDYUT MAHALDAR | 9.98 | 0 | 0 | 0
1157 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Period from 01/03/2024 to 31/08/2024). | 843/MD | 22/02/2024 | 180 | RAJENDRA PRASAD SINGH | 0.86 | 0 | 0 | 17
1158 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mekpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 1513/MD | 16/03/2024 | 45 | A. B. CONSTRUCTION | 26.41 | 0 | 0 | 0
1159 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Continuation work order for the work of hiring of 1 no diesel vehicle in good condition (traffic authority) having licence contract carage permit from regional transport authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte (Period from 23/12/2023 to 19/06/2024) | 2089/NBC-II | 20/12/2023 | 180 | USHA ENTERPRISE | 0.86 | 0 | 0 | 26
1160 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Laying with Extension of different diameter (OD) uPVC pipe line under command area at Baherpur Zone-II Water Supply Scheme under Bamangola Block under Malda Division, PHE Dte. in the district of Malda. | 6167/MD | 05/12/2024 | 45 | S. R. CONSTRUCTION | 63.36 | 0 | 0 | 0
1161 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and allied laying work in connection with Jal Jeevan Mission (JJM) at Dahara Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 3206/MD | 27/06/2024 | 45 | M/S AMIT KUMAR GUPTA | 69.58 | 0 | 0 | 0
1162 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of JALALPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | 2140/MD | 16/09/2020 | 60 | FUTURE | 116.65 | 43.03 | 100 | 0
1163 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of GUN SANKRUL Water Supply Scheme at Malda Old Block under Malda Division, PHE Dte. | 2261/MD | 29/09/2020 | 45 | MILLENNIUM ENTERPRISR | 74.5 | 10.61 | 100 | 0
1164 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Uttar Bhabanipur, JL. No. 73, G.P.-Bhakri of RAMPUR Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | 285/MD | 28/01/2021 | 30 | M/S BANERJEE CONSTRUCTION | 13.56 | 8.97 | 100 | 1
1165 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Manoharpur, JL. No. 117, G.P.-Sultannagar of GANNADIA Water Supply Scheme at Harischandrapur - II Block under Malda Division, PHE Dte. | 447/MD | 08/02/2021 | 30 | MANIK CHOUDHURY | 37.13 | 11.44 | 100 | 0
1166 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Additional laying work of UPVC distribution pipe line for JALALPUR Water Supply Scheme at CHANCHAL- II Dev. Block under Malda Division, PHE Dte. In the District of Malda. | 552/MD | 12/02/2021 | 30 | FUTURE | 3.33 | 2.93 | 100 | 0
1167 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | 2719/MD | 10/11/2020 | 30 | MANAS KUMAR SAHA | 50.07 | 23.44 | 100 | 1
1168 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KHANPUR HULASHPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. In the district of Malda. | 2955/MD | 07/12/2022 | 30 | BIDYUT MAHALDAR | 5.17 | 0 | 0 | 100
1169 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for Extension of UPVC pipe line laying for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) under command area of Khanpur-Hulaspur W/S Scheme at Chanchal-I Block under Malda Division. PHE Dte. | 2963/MD | 07/12/2022 | 30 | BIDYUT MAHALDAR | 7.04 | 0 | 0 | 100
1170 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Acceptance cum formal work order for hiring of inspection vehicle (Motor Cab or Maruti Omni Category (Standard), Non-Air Condition, Bharat Stage-III purchased on or after 01.05.2008 with Diesel/LPG/CNG Engine) in perfectly good condition of performing a very long journey and should cover anywhere without any trouble on monthly hire basis for official use of the office of the Assistant Engineer, R.W.S. Malda Sub-Division, P.H.E. Dte. (Period from 06/01/2023 to 05/07/2023) | 193/RWS | 05/01/2023 | 181 | SHYAMAL KUMAR MAITRA | 0.86 | 0 | 0 | 15
1171 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/01/2023 to 30/06/2023). | 520/MSD | 30/12/2022 | 182 | UTTAM KUMAR GHOSH | 0.86 | 0 | 0 | 15
1172 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KHANPUR HULASPUR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 2139/MD | 16/09/2020 | 45 | M/S TRILOCHAN CONSTRUCTION CO | 65.52 | 8.47 | 100 | 0
1173 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of RAJARAMPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 2263/MD | 29/09/2020 | 45 | UTTAM KUMAR DUTTA | 59.93 | 24.09 | 100 | 0
1174 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/07/2023 to 31/12/2023). | 504/MSD | 30/06/2023 | 184 | UTTAM KUMAR GHOSH | 0.86 | 0 | 0 | 26
1175 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Mekpur Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 3366/MD | 29/08/2023 | 45 | MANIK CHOUDHURY | 16.14 | 0 | 0 | 90
1176 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Rajarampur Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 3369/MD | 29/08/2023 | 45 | M/S PRATIMA CONSTRUCTION | 16.13 | 0 | 0 | 100
1177 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Sadlichak Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 3810/MD | 16/10/2023 | 30 | RABIUL ISLAM | 8.8 | 0 | 0 | 90
1178 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KUTUB SAHAR Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 4769/MD | 05/12/2023 | 45 | ACHARYYA CONSTRUCTION | 12.14 | 0 | 0 | 100
1179 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DALLA Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 4767/MD | 05/12/2023 | 45 | A. B. CONSTRUCTION | 14.09 | 0 | 0 | 100
1180 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KHOPAKATI Water Supply Scheme at Harishchandrapuir-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 5245/MD | 22/12/2023 | 45 | M/S FOUR STAR CONSTRUCTION | 38.41 | 0 | 0 | 98
1181 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DAHARA Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 386/MD | 17/01/2024 | 45 | PARIJAT RAY | 58.89 | 0 | 0 | 70
1182 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Nikhrail command area of MAHANADAPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 285/MD | 11/01/2024 | 45 | M/S AYUSH BUILDERS | 6.37 | 0 | 0 | 100
1183 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Hazzabari Village of Khord Babupur Mouza under KUTUB SAHAR Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 978/MD | 04/03/2024 | 45 | DHRITIPALI | 12.79 | 0 | 0 | 100
1184 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at different CWPP site of Gazole & Habibpur Block under RWS Malda Sub-Division in the district of Malda. | 900/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.85 | 0 | 0 | 100
1185 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Source Augmentation Schemes of Gazole & Old Malda Block under RWS Malda Sub-Division in the district of Malda. | 903/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.97 | 0 | 0 | 100
1186 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at different Retrofitting Schemes of Habibpur Block under RWS Malda Sub-Division in the district of Malda. | 904/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.97 | 0 | 0 | 100
1187 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Ratua-I Block under RWS Malda Sub-Division in the district of Malda. | 895/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.85 | 0 | 0 | 100
1188 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Source Augmentation, Retrofitting Schemes and different CWPP site of Chanchal-II Block under RWS Malda Sub-Division in the district of Malda. | 897/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.85 | 0 | 0 | 100
1189 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes and different CWPP site of Old Malda Block under RWS Malda Sub-Division in the district of Malda. | 898/MD | 28/02/2024 | 7 | PRITAM ENTERPRISE | 0.85 | 0 | 0 | 100
1190 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Source Augmentation Schemes of Harishchandrapur-I & Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | 896/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.85 | 0 | 0 | 100
1191 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Chanchal-I & Harishchandrapur-I Block under RWS Malda Sub-Division in the district of Malda. | 892/MD | 28/02/2024 | 7 | RAHANUL ALAM | 0.85 | 0 | 0 | 100
1192 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Source Augmentation Schemes and different CWPP sites of Chanchal-I, Ratua-I & Ratua-II Block under RWS Malda Sub-Division in the district of Malda. | 907/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.6 | 0 | 0 | 100
1193 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Englishbazar & Manikchak Block under RWS Malda Sub-Division in the district of Malda. | 908/MD | 28/02/2024 | 7 | PRITAM ENTERPRISE | 0.36 | 0 | 0 | 100
1194 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Source Augmentation and Retrofitting Schemes of Habibpur Block under RWS Malda Sub-Division in the district of Malda. | 899/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.85 | 0 | 0 | 100
1195 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Bamongola Block under RWS Malda Sub-Division in the district of Malda. | 902/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.97 | 0 | 0 | 100
1196 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | 893/MD | 28/02/2024 | 7 | RAHANUL ALAM | 0.85 | 0 | 0 | 100
1197 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | 901/MD | 28/02/2024 | 7 | RAHANUL ALAM | 0.97 | 0 | 0 | 100
1198 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at different CWPP sites of Chanchal-I, Harishchandrapur-I & Harishchandrapur-II Block under RWS Malda Sub-Division in the district of Malda. | 906/MD | 28/02/2024 | 7 | RAHANUL ALAM | 0.73 | 0 | 0 | 100
1199 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at different Retrofitting Schemes of Gazole Block under RWS Malda Sub-Division in the district of Malda. | 905/MD | 28/02/2024 | 7 | M/S AYUSH BUILDERS | 0.97 | 0 | 0 | 100
1200 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Erection of Jal Jeevan Mission Sign Board at Retrofitting Schemes of Ratua-I & Ratua-II Block under RWS Malda Sub-Division in the district of Malda. | 894/MD | 28/02/2024 | 7 | RABIUL ISLAM | 0.85 | 0 | 0 | 100
1201 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for GUN SANKRUL Piped Water Supply Scheme (Gunkrul JL-34) of Old Malda Block in the District of Malda under Malda Division, PHE Dte. | 2931/MD | 10/06/2024 | 45 | RABIUL ISLAM | 17.29 | 0 | 0 | 100
1202 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Material Requisition To Resource Division | 30/MD | 04/01/2024 | 0 | Resource Division | 1.23 | 0 | 0 | 0
1203 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Material Requisition To Resource Division | 56/MD | 04/01/2024 | 0 | Resource Division | 0.31 | 0 | 0 | 0
1204 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Material Requisition To Resource Division | 40/MD | 04/01/2024 | 0 | Resource Division | 5.85 | 0 | 0 | 0
1205 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Material Requisition To Resource Division | 32/MD | 04/01/2024 | 0 | Resource Division | 1.42 | 0 | 0 | 0
1206 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Material Requisition To Resource Division | 52/MD | 04/01/2024 | 0 | Resource Division | 1.93 | 0 | 0 | 0
1207 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Material Requisition To Resource Division | 533/MD | 30/01/2024 | 0 | Resource Division | 12.94 | 0 | 0 | 0
1208 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Material Requisition To Resource Division | 3923/MD | 06/08/2024 | 0 | Resource Division | 4.31 | 0 | 0 | 0
1209 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Material Requisition To Resource Division | 3926/MD | 06/08/2024 | 0 | Resource Division | 5.13 | 0 | 0 | 0
1210 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Material Requisition To Resource Division | 5970/MD | 28/11/2024 | 0 | Resource Division | 154 | 0 | 0 | 0
1211 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Material Requisition To Resource Division | 5973/MD | 28/11/2024 | 0 | Resource Division | 154 | 0 | 0 | 0
1212 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Augmentation of Head work site Pump House, PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at DALLA Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1123/MD | 21/03/2025 | 45 | M/S GHOSH CONSTRUCTION | 9.58 | 0 | 0 | 0
1213 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Khopakati Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 5832/MD | 22/11/2024 | 450 | M/S SABANA CONSTRUCTION | 55.74 | 0 | 0 | 0
1214 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gun Sankrul Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 1189/MD | 14/03/2024 | 383 | TARUN KUMAR DEY | 26.39 | 0 | 0 | 0
1215 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Period from 01/09/2024 to 28/02/2025). | 4590/MD | 30/08/2024 | 180 | RAJENDRA PRASAD SINGH | 0.86 | 0 | 0 | 0
1216 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Malsa Mouza of KhanpurHulaspur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 5485/MD | 24/10/2024 | 361 | M/S /FAIZUL HAQUE BISWAS | 26.08 | 0 | 0 | 40
1217 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kutub Sahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6412/MD | 19/12/2024 | 194 | PABITRA MANDAL | 40.29 | 0 | 0 | 0
1218 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Mihaghat Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 56 | 08/01/2025 | 311 | ASHIS CONSTRUCTION | 26.57 | 0 | 0 | 0
1219 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the Assistant Engineer, Malda Division, PHE Dte. (Period from 01/07/2024 to 31/12/2024). | 3255/MD | 28/06/2024 | 180 | AMIN ENTERPRISE | 0.86 | 0 | 0 | 60
1220 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-1) (Period from 01/07/2024 to 31/12/2024). | 3256/MD | 28/06/2024 | 180 | M/S FOUR STAR CONSTRUCTION | 0.86 | 0 | 0 | 100
1221 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 15/06/2024 to 14/12/2024). | 3054/MD | 14/06/2024 | 180 | RUQAIYA ENTERPRISE | 0.86 | 0 | 0 | 0
1222 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Period from 01/07/2024 to 31/12/2024). | 3252/MD | 28/06/2024 | 180 | ARUN KUMAR DAS | 0.86 | 0 | 0 | 0
1223 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-1) (Period from 01/07/2024 to 31/12/2024). | 3253/MD | 28/06/2024 | 180 | SHYAMAL KUMAR MAITRA | 0.86 | 0 | 0 | 0
1224 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division Division, PHE Dte.(Car-1)(Period from 01/07/2024 to 31/12/2024). | 3257/MD | 28/06/2024 | 180 | M/S TEWARI CONSTRUCTION | 0.86 | 0 | 0 | 100
1225 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and allied laying work in connection with Jal Jeevan Mission (JJM) at Talsur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 3207/MD | 27/06/2024 | 443 | BEE GEE CONSTRUCTION | 88.37 | 0 | 0 | 65
1226 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dahara Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 80 | 13/01/2025 | 45 | M/S AMIT KUMAR GUPTA | 65.21 | 0 | 0 | 1
1227 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for DALLA Piped Water Supply Scheme (Dalla JL.-54, Aragachi JL-57) of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | 2252/MD | 21/05/2025 | 243 | ACHARYYA CONSTRUCTION | 25.17 | 0 | 0 | 0
1228 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for GUNSANKRUL Piped Water Supply Scheme (Jadupur JL.-28, Paschim Banjhapara JL32) of Old Malda Block in the District of Malda under Malda Division, PHE Dte. | 2253/MD | 21/05/2025 | 90 | RABIUL ISLAM | 22.84 | 0 | 0 | 0
1229 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Different Piped Water Supply Scheme under Harishchandrapur-I & II, Chanchal-I & II Block to facilitate Har Ghar Jal under Malda Division, PHE Dte. in the district of Malda. | 2340/MD | 22/05/2025 | 365 | M/S SABANA CONSTRUCTION | 65.08 | 0 | 0 | 0
1230 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Different Locations under Different Piped Water Supply Scheme under Ratua-I & II Block to facilitate Har Ghar Jal under Malda Division, PHE Dte. in the district of Malda. | 2341/MD | 22/05/2025 | 365 | M/S TEWARI CONSTRUCTION | 32.63 | 0 | 0 | 0
1231 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Khanpur Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | 2878/MD | 17/06/2025 | 60 | BINA CONSTRUCTION | 61.93 | 0 | 0 | 0
1232 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Jagannathpur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 2888/MD | 17/06/2025 | 255 | M/S SABANA CONSTRUCTION | 90.55 | 0 | 0 | 0
1233 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Birjabhita Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 2333/MD | 22/05/2025 | 60 | ACHARYYA CONSTRUCTION | 52.11 | 0 | 0 | 0
1234 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Augmentation of work to ensure proper functioning of 250 M³ Capacity 20 Mtr. Staging height RCC Over Head Reservoir of Dalla Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1060/MD | 19/03/2025 | 60 | BENGAL ENGINEERING COMPANY | 8.47 | 0 | 0 | 0
1235 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Augmentation work of OHR, Pump House and Boundary Wall of Daulatnagar Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1047/MD | 18/03/2025 | 75 | M/S PARIMAL DAS | 30.45 | 0 | 0 | 0
1236 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-II Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 2329/MD | 22/05/2025 | 60 | SAHA CONSTRUCTION | 43.45 | 0 | 0 | 0
1237 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-III Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 2330/MD | 22/05/2025 | 60 | BEE GEE CONSTRUCTION | 43.45 | 0 | 0 | 0
1238 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-IV Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 2331/MD | 22/05/2025 | 60 | M/S SRINJOYEE | 8.7 | 0 | 0 | 0
1239 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) and Laying with Extension of different diameter (OD) uPVC pipe line under command area at Baherpur Zone-I Water Supply Scheme under Bamangola Block under Malda Division, PHE Dte. in the district of Malda. | 2889/MD | 17/06/2025 | 60 | M/S SINHA ENTERPRISE | 43.12 | 0 | 0 | 0
1240 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Augmentation work of OHR, Pump House and Boundary Wall of Jalalpur Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1054/MD | 18/03/2025 | 75 | M/S MOON LIGHT CONSTRUCTION & CO. | 28.53 | 0 | 0 | 0
1241 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Different Locations under Different Piped Water Supply Scheme under Habibpur & Gazole Block to facilitate Har Ghar Jal under Malda Division, PHE Dte. in the district of Malda. | 2880/MD | 17/06/2025 | 365 | SAMBHU NATH SARKAR | 52.09 | 0 | 0 | 0
1242 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Augmentation work of OHR, Pump House and Boundary Wall of Khanpur-Hulaspur Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2897/MD | 17/06/2025 | 60 | M/S ROY CONSTRUCTION | 31.51 | 0 | 0 | 0
1243 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gadai Maharajpur Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 2313/MD | 22/05/2025 | 60 | M/S JHA CONSTRUCTION | 52.11 | 0 | 0 | 0
1244 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gobarjana Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | 2893/MD | 17/06/2025 | 60 | J. M. CONSTRUCTION | 26 | 0 | 0 | 0
1245 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bejpura Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 2282/MD | 21/05/2025 | 45 | M I CONSTRUCTION | 30.42 | 0 | 0 | 0
1246 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Additional laying of Pipe line for improvement of FHTC functionality by UPVC pipe line and Construction of Boundary wall ,Aproach Raod at HW & 2nd TW site in for PERAPUR Piped Water Supply Scheme at Habibpur Dev. Block in the District of Malda under Malda Division, P.H.E. Dte. | 4520/MD | 12/09/2025 | 292 | BANIK BROTHERS | 90.01 | 0 | 0 | 0
1247 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Laying of Parallel/ Dedicated Pipeline, Providing Common Manifold & providing Balance FHTC for better Functionality at Magura Zone-I Piped Water Supply Scheme at Ratua-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 4233/MD | 29/08/2025 | 60 | BEE GEE CONSTRUCTION | 51.17 | 0 | 0 | 0
1248 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Laying of Parallel/ Dedicated Pipeline, Providing Common Manifold, Land Development & providing Balance FHTC for better Functionality at Mekpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 4236/MD | 29/08/2025 | 60 | MANIK CHOUDHURY | 91.14 | 0 | 0 | 0
1249 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Replacement of 200 mm dia. X 150 mm Dia.) Tubewell No:-2 (130 M Deep) by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at MAHAMMADPUR Water Supply Scheme of Old Malda Block under Malda Division, PHE Dte. | 4807/MD | 13/09/2024 | 78 | GOBINDA ENTERPRISE | 8.29 | 0 | 0 | 100
1250 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Detail route survey and design & drawing of distribution network, for providing FHTC in Balupur Zone-I Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | 271/MD | 28/01/2025 | 15 | FUTURE | 0.84 | 0 | 0 | 100
1251 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of different Water Supply Schemes at different Blocks under Malda Division, PHE Dte , SM/07973 | Retrofitting | Detail route survey and design & drawing of distribution network, for providing FHTC in Balupur Zone-II Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | 272/MD | 28/01/2025 | 15 | FUTURE | 0.84 | 0 | 0 | 100
1252 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme , SM/06863 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme at Habibpu Block under Malda Division, PHE Dte. | 2447/MD | 12/10/2020 | 120 | MANIK CHOUDHURY | 12 | 0 | 0 | 1
1253 | MALDAH | Central Drilling | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme , SM/06863 | Retrofitting | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. | 302/CMSD-I (D) | 08/07/2022 | 15 | CHANDA ENTERPRISE | 4.66 | 0 | 0 | 0
1254 | MALDAH | Central Drilling | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme , SM/06863 | Retrofitting | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITEFOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. | 346/CMSD-I | 25/07/2022 | 15 | CHANDA ENTERPRISE | 4.66 | 0 | 0 | 0
1255 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme , SM/06863 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KADIRPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 1964/MD | 31/08/2020 | 30 | M/S KUNDU CONSTRUCTION | 39.43 | 0.01 | 100 | 1
1256 | MALDAH | Central Drilling | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme , SM/06863 | Retrofitting | PROVIDING TUBE WELL MATERIALS TO IS : 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT JAGJIBANPUR, HABIBPUR BLOCK, MALDA DISTRICT UNDER CDD, PHE DTE. | 301/CMSD-I (D) | 08/07/2022 | 15 | CHANDA ENTERPRISE | 4.69 | 0 | 0 | 50
1257 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme , SM/06863 | Retrofitting | Acceptance cum formal work order for Emergent repairing and laying of uPVC pipeline and Construction of different dia sluice valve chambers with other allied work to proper functioning of FHTC work within the command area of JAGJIBANPUR Water Supply scheme under Malda Division, PHE Dte. in the district of Malda. | 2960/MD | 07/12/2022 | 30 | M/S AYUSH BUILDERS | 3.64 | 0 | 0 | 1
1258 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of JAGJIBANPUR Water Supply Scheme , SM/06863 | Retrofitting | Acceptance cum formal work order for Providing FHTC (Functional House hold Tap Connection) of Ranghat Piped Water Supply Scheme at Chanchal-II Dev. Block, under Malda Division, P.H.E. Dte. in the District of Malda. | 1991/MD | 17/05/2023 | 15 | M/S FOUR STAR CONSTRUCTION | 9.06 | 0 | 0 | 100
1259 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dharampur Water Supply Scheme( Mouza-Nowada , Habitation-Sonapur,Haddatola, Kurbanitola, Nawada Haddatola, Dakshin Torabalitola) at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1755/MAAD | 24/11/2021 | 45 | ACHARYYA CONSTRUCTION | 15.91 | 0 | 0 | 1
1260 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dharampur Water Supply Scheme( Mouza-Manikchak , ShyamSundari) at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1756/MAAD | 24/11/2021 | 45 | ACHARYYA CONSTRUCTION | 16.02 | 0 | 0 | 1
1261 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Laying of 63 mm dia. UPVC pipe and 20mm dia. HDPE pipe at different places for installation of FHTC under Dharampur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 359/MAAD | 07/03/2022 | 30 | ACHARYYA CONSTRUCTION | 4.82 | 0 | 0 | 1
1262 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dharampur water supply Scheme (Mouza Dharampur, Habitation-Ranutola, New Kadamtola, Shyamsundartola, Jhaitantola, Sonapur) at Manikchak Block under Malda Arsenic Area water supply Divn PHE Dte. | 1023/MAAD | 12/05/2022 | 45 | DHRITIPALI | 15.99 | 0 | 0 | 1
1263 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Topographical and Hydrograpic Survey for Malda Arsenic Area Water Supply Scheme ( Northern Sector) at Sankaritolaghat, Manikchak under Malda Arsenic Area Water Supply Division, P.H.E. Dte. | 693/MAAD | 12/04/2022 | 20 | INTAKE SURVEY ENGINEERING CONSORTIUM | 2.15 | 0 | 0 | 1
1264 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at Kurbanitola & Sham Mahammad Tola at Dharampur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 1469/MAAD | 29/07/2022 | 45 | S. R. ENTERPRISE | 4.79 | 0 | 0 | 1
1265 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at Nawada Haddatola, Karmakartola under Dharampur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 1466/MAAD | 29/07/2022 | 45 | TARUN KANTI BAGCHI | 4.85 | 0 | 0 | 1
1266 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Placing of diesel driven Car on hire basis for official use of the Executive Engineer, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte. | 1409/MAAD | 31/12/2020 | 365 | NITAI PANDAY | 4.85 | 0 | 0 | 1
1267 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-I, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte. | 1339/MAAD | 14/09/2021 | 109 | SUBRATA SAHA | 0.52 | 0 | 0 | 1
1268 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Laying of 125 mm, 110 mm dia uPVC Pipe line at Dharampur Village under Jote Gopal Kagmari distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1402/MAAD | 26/07/2022 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.7 | 0 | 0 | 100
1269 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Continuation work order for Supply G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for Schools of English Bazar Block under Malda Arsenic Area W/S Division, PHE Dte. | 2107/MAAD | 07/12/2022 | 15 | M/S PARIMAL DAS | 0.41 | 0 | 0 | 1
1270 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Material Requisition To Resource Division | 196/MAAD | 11/02/2022 | 0 | Resource Division | 20.13 | 0 | 0 | 0
1271 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Haring of Charges of the Car. | BP-2022-23-304 | 09/03/2023 | 0 | M/S PARIMAL DAS | 0.22 | 0 | 0 | 0
1272 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
1273 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dharampur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manikchak Block , SM/09587 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area(Mouza Shyamsundari Part Manikchak Part, Ugritola) & others Allied works at Dharampur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 1022/MAAD | 12/05/2022 | 60 | ACHARYYA CONSTRUCTION | 33.38 | 0 | 0 | 1
1274 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. schools in Kaliachak-III Block) , SM/10205 | School | Supply G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for Schools of Kaliachak -III Block under Malda Arsenic Area W/S Division, PHE Dte. | 1030/MAAD | 12/05/2022 | 10 | FUTURE | 5 | 0 | 0 | 0
1275 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. schools in Kaliachak-III Block) , SM/10205 | School | Continuation work order for Supply G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for Schools of Kaliachak - III Block under Malda Arsenic Area Water Supply Division, P.H.E. Dte. | 1611/MAAD | 01/09/2022 | 10 | FUTURE | 4.39 | 0 | 0 | 0
1276 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. schools in Kaliachak-III Block) , SM/10205 | School | Formal work order for Providing Drinking Water Supply in 24 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 1055/MAAD | 24/05/2022 | 120 | MOTI RAHAMAN | 150.74 | 0 | 0 | 0
1277 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. schools in Kaliachak-III Block) , SM/10205 | School | Material Requisition To Resource Division | 337/MAAD | 28/02/2022 | 0 | Resource Division | 76.19 | 0 | 0 | 0
1278 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. schools in Kaliachak-III Block) , SM/10205 | School | Formal work order for Providing Drinking Water Supply in 30 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak ¿ III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 779/MAAD | 22/04/2022 | 120 | DEBAPRIYA SAHA | 188.97 | 0 | 0 | 100
1279 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (69 nos. schools in Kaliachak-III Block) , SM/10205 | School | Providing Drinking Water Supply in 15 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 641/MAAD | 01/04/2022 | 120 | DEBAPRIYA SAHA | 94.48 | 0 | 0 | 100
1280 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10206 | School | Providing Drinking Water Supply in 4 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 1129/MAAD | 10/06/2022 | 120 | M/S. JHA CONSTRUCTION | 25.21 | 0 | 0 | 0
1281 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10206 | School | Formal work order for Providing Drinking Water Supply in 30 Nos Source Less School Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure) | 786/MAAD | 26/04/2022 | 120 | USHA ENTERPRISE | 189.14 | 0 | 0 | 100
1282 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10206 | School | Providing Drinking Water Supply in 4 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 1130/MD | 10/06/2022 | 120 | M/S AMIT KUMAR GUPTA | 25.21 | 0 | 0 | 0
1283 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10206 | School | Providing Drinking Water Supply in 10 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 639/MAAD | 01/04/2022 | 120 | BANIK BROTHERS | 63.04 | 0 | 0 | 0
1284 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10206 | School | Supply & delivery of G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for providing Drinking Water Supply inSource Less Schools & ICDS at Kaliachak -I Block under Malda Arsenic Area Water Supply Divisio, P.H.E. Dte. | 1900/MAAD | 13/10/2022 | 15 | MERCURY ENGINEERING COMPANY | 11.91 | 0 | 0 | 0
1285 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10206 | School | Material Requisition To Resource Division | 336/MAAD | 28/02/2022 | 0 | Resource Division | 4.46 | 0 | 0 | 0
1286 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 50 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10206 | School | Providing Drinking Water Supply in 2 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 1131/MAAD | 10/06/2022 | 1026 | M/S PARIMAL DAS | 12.55 | 0 | 0 | 48
1287 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(87 nos) of Ratua-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10385 | School | Material Requisition To Resource Division | 719/MD | 25/03/2022 | 0 | Resource Division | 57.3 | 0 | 0 | 0
1288 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(87 nos) of Ratua-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10385 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Bilaimari & Mahanandatala GP of Ratua-I Dev. Block under Malda Division, PHE Dte. | 3193/MD | 27/12/2022 | 75 | WATER TECH | 157.2 | 0 | 0 | 63
1289 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(87 nos) of Ratua-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10385 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for School at Debipur, Kahala & Baharal GP of Ratua-I Dev. Block under Malda Division, PHE Dte. | 3199/MD | 27/12/2022 | 75 | USHA ENTERPRISE | 129.85 | 0 | 0 | 100
1290 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(87 nos) of Ratua-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10385 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Chandmani-I & Chandmani-II GP of Rtua-I Dev. Block under Malda Division, PHE Dte. | 468/MD | 07/02/2023 | 75 | MILLENNIUM ENTERPRISR | 136.58 | 0 | 0 | 100
1291 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(87 nos) of Ratua-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10385 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Bhado, Ratua & Samsi GP of Ratua-I Dev. Block under Malda Division, PHE Dte. | 102/MD | 18/01/2023 | 715 | MILLENNIUM ENTERPRISR | 136.58 | 0 | 0 | 100
1292 | MALDAH | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE , SM/10304 | Anganwadi | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Boroi Mahendrapur GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. (QTY:- 6 Nos.) | 2721/MD | 17/11/2022 | 60 | M/S S. S. ENTERPRISE | 41.18 | 0 | 0 | 47
1293 | MALDAH | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE , SM/10304 | Anganwadi | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Kushida and Rashidabad GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. (QTY:-12 Nos.) | 2722/MD | 17/11/2022 | 60 | ASIT PRAMANIK | 82.34 | 0 | 0 | 100
1294 | MALDAH | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE , SM/10304 | Anganwadi | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Harishchandrapur GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. (QTY:-14 Nos.) | 2717/MD | 17/11/2022 | 60 | M/S DAS CONSTRUCTION | 96.05 | 0 | 0 | 49
1295 | MALDAH | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE , SM/10304 | Anganwadi | Material Requisition To Resource Division | 527/MD | 03/03/2022 | 0 | Resource Division | 58.62 | 0 | 0 | 0
1296 | MALDAH | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE , SM/10304 | Anganwadi | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Boroi Mahendrapur GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. (QTY:- 7 Nos.) | 2720/MD | 17/11/2022 | 60 | ZEOLITE FRESH INDIA | 48.09 | 0 | 0 | 50
1297 | MALDAH | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE , SM/10304 | Anganwadi | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Bhingal GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. (QTY:-9 Nos.) | 2718/MD | 17/11/2022 | 60 | BANIK BROTHERS | 61.83 | 0 | 0 | 0
1298 | MALDAH | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE , SM/10304 | Anganwadi | Installation of Solar Powered Standalone Community Water Purification Plant (CWPP) for AWC's at different places of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. (Quantity: 15 Nos.) | 1913/MD | 14/05/2025 | 150 | SHREE BISHNU CONSTRUCTION | 96.81 | 0 | 0 | 0
1299 | MALDAH | Malda Division | INSTALLATION OF 89 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-I DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE , SM/10304 | Anganwadi | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Tulshihata GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. (QTY:-10 Nos.) | 2719/MD | 17/11/2022 | 348 | PACIFIC ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 68.5 | 0 | 0 | 100
1300 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 4th Tube Well site of Bhaluka Fatepur Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | 1192/MD | 24/05/2022 | 31 | M/S GULFAM CONSTRUCTION. | 4.78 | 0 | 0 | 0
1301 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 3rd Tube Well site of Bhaluka Fatepur Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | 1193/MD | 24/05/2022 | 31 | M/S SRINJOYEE | 4.78 | 0 | 0 | 0
1302 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Acceptance cum formal work order for Sinking of 02 (Two) Nos. 150mm. Dia. x 100mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Bhaluka Fatepur Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda. | 1395/MD | 14/06/2022 | 30 | A. L. ENGINEERING SOLUTION | 10 | 0 | 0 | 0
1303 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Continuation work order for Route survey for distribution network design for augmentation of Bhaluka Fatepur Water Supply Scheme in Harischandrapur-II block under Malda Division, PHE Dte. | 1840/MD | 30/06/2021 | 14 | INDRANIL DUTTA & ACCOCIATES | 1.45 | 0 | 0 | 0
1304 | MALDAH | Malda Mechanical | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Supply, installation & commissioning of electro-mechanical components at T/W no. I & II of Augmentation of Bhaluka Fatepur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | 267/MLMD | 24/02/2023 | 90 | SHREE BISHNU CONSTRUCTION | 7.97 | 0 | 0 | 70
1305 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of BHALUKA FATEPUR Piped Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. In the District of Malda. | 2173/MD | 07/06/2023 | 30 | M/S EHAN ENTERPRISE | 11.04 | 0 | 0 | 0
1306 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Bhaluka Fatepur Pipe Water Supply Scheme at Harishchandrapur-II Block in the District of Malda under Malda Division P.H.E. Dte. | 1828/MD | 04/08/2022 | 90 | GHOSH BROTHERS | 348.1 | 0 | 0 | 68
1307 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Material Requisition To Resource Division | 1871/MD | 16/08/2022 | 0 | Resource Division | 65.9 | 0 | 0 | 0
1308 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Material Requisition To Resource Division | 1607/MD | 11/04/2023 | 0 | Resource Division | 29.16 | 0 | 0 | 0
1309 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Material Requisition To Resource Division | 1801 | 27/04/2023 | 0 | Resource Division | 59.54 | 0 | 0 | 0
1310 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Soil Investigation and design of substructure for Over Head Reservoirs for BHALUKA FATEPUR Piped Water Supply Scheme at Harishchandapur-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. | BP-2022-23-192 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
1311 | MALDAH | Malda Mechanical | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- III & IV of Bhaluka Fatepur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/009046) | 2232/MLMD | 19/07/2023 | 833 | A.K. SIKDAR | 21.58 | 0 | 0 | 77
1312 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at BHALUKA FATEPUR Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 830/MD | 21/02/2024 | 45 | OLI CONSTRUCTION | 4.17 | 0 | 0 | 0
1313 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Construction of Boundary Wall at 3rd Tube Well site of Bhaluka Fatepur Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 2952/MD | 10/06/2024 | 30 | SARIF BUILDERS | 9.93 | 0 | 0 | 0
1314 | MALDAH | Malda Mechanical | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | New service connection at BHALUKA- FAFATEPUR PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( Bhaluka c.c.c) | BP-2024-25-351 | 24/06/2024 | 0 | W.B.S.E.D.C.LTD | 9.85 | 0 | 0 | 0
1315 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Formal work order for the work of Construction of 700 M3 Capacity OHR with FHTC (Mouza-Bhaluka) of Bhaluka Fatepur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 3020/MD | 08/08/2023 | 711 | GHOSH BROTHERS | 283.26 | 0 | 0 | 0
1316 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Laying of Rising Main including Specials and Valves for BHALUKA FATEPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 715/MD | 09/02/2024 | 45 | J. M. CONSTRUCTION | 14.06 | 0 | 0 | 80
1317 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Bhaluka Fatepur Water Supply Scheme in Harischandrapur-II block under Malda Division, PHE Dte. | 1750/MD | 15/06/2021 | 14 | INDRANIL DUTTA & ACCOCIATES | 2.86 | 0 | 0 | 1
1318 | MALDAH | Malda Division | Augmentation of Bhaluka Fatepur Piped water supply scheme , SM/10137 | Augmentation | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 180 Mtr. Deep Big dia Tube well (1 No) at BHALUKA FATEPUR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1673/MD | 18/04/2023 | 449 | MERCURY ENGINEERING COMPANY | 10.71 | 0 | 0 | 95
1319 | MALDAH | Malda Division | INSTALLATION OF 75 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10243 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Sultannagar, Bhaluka & Doulatnagar GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | 3198/MD | 27/12/2022 | 75 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 161.94 | 0 | 0 | 100
1320 | MALDAH | Malda Division | INSTALLATION OF 75 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10243 | Anganwadi | Material Requisition To Resource Division | 519/MD | 03/03/2022 | 0 | Resource Division | 49.36 | 0 | 0 | 0
1321 | MALDAH | Malda Division | INSTALLATION OF 75 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10243 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Islampur, Doulatpur & Sadlichak GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | 553/MD | 09/02/2023 | 75 | SOUNAK ENTERPRISE | 112.11 | 0 | 0 | 70
1322 | MALDAH | Malda Division | INSTALLATION OF 75 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF HARISHCHANDRAPUR-II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10243 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Malior-I & II and Masaldaha GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | 60/MD | 16/01/2023 | 75 | M/S TRILOCHAN CONSTRUCTION CO | 112 | 0 | 0 | 96
1323 | MALDAH | Malda Division | Augmentation of Deotala Water Supply Scheme , SM/09986 | Augmentation | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Deotala Water Supply Scheme in Gazole block under Malda Division, PHE Dte. | 1746/MD | 15/06/2021 | 14 | HORIZEN | 2.86 | 0 | 0 | 1
1324 | MALDAH | Malda Mechanical | Augmentation of Deotala Water Supply Scheme , SM/09986 | Augmentation | Supply, installation and commissioning of electro-mechanical components of T/W no. II and making compound lighting arrangement at T/W no. I of Augmentation of Deotala Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/005108) | 2723/MLMD | 14/08/2023 | 180 | JIBU SINGHA | 14.75 | 0 | 0 | 0
1325 | MALDAH | Malda Division | Augmentation of Deotala Water Supply Scheme , SM/09986 | Augmentation | Acceptance cum formal work order for Laying of Rising main with connection between 1st Tube well and 3 rd Tube well and condtructtion of standpost for DEOTALA Water Supply Scheme under Malda Division, PHE Dte. in the District of Malda. | 1308/MD | 01/06/2022 | 30 | JIBON GHOSH | 4.43 | 0 | 0 | 0
1326 | MALDAH | Malda Division | Augmentation of Deotala Water Supply Scheme , SM/09986 | Augmentation | Material Requisition To Resource Division | 1106/MD | 17/05/2022 | 0 | Resource Division | 37.39 | 0 | 0 | 0
1327 | MALDAH | Malda Division | Augmentation of Deotala Water Supply Scheme , SM/09986 | Augmentation | Material Requisition To Resource Division | 1585/MD | 28/03/2023 | 0 | Resource Division | 2.3 | 0 | 0 | 0
1328 | MALDAH | Malda Division | Augmentation of Deotala Water Supply Scheme , SM/09986 | Augmentation | Material Requisition To Resource Division | 816/MD | 21/02/2024 | 0 | Resource Division | 45.08 | 0 | 0 | 0
1329 | MALDAH | Malda Division | Augmentation of Deotala Water Supply Scheme , SM/09986 | Augmentation | Formal work order for Augmentation of DEOTALA Piped water supply scheme for the work of Geotechnical Study,construction of 500 Cum RCC OHR,Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Gazole Dev Block under Malda Division PH Engg Dte. In the District of Malda | 868/MD | 08/04/2022 | 1208 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 460.03 | 0 | 0 | 50
1330 | MALDAH | Malda Division | Augmentation of Deotala Water Supply Scheme , SM/09986 | Augmentation | Laying of Rising Main including Specials and Valves for Deotala Piped Water Supply Scheme at Deotala Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 163/MD | 08/01/2024 | 449 | M I CONSTRUCTION | 14.99 | 0 | 0 | 100
1331 | MALDAH | Malda Division | Augmentation of Deotala Water Supply Scheme , SM/09986 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Deotala Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6409/MD | 19/12/2024 | 331 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 26.07 | 0 | 0 | 0
1332 | MALDAH | Malda Division | Augmentation of Deotala Water Supply Scheme , SM/09986 | Augmentation | Augmentation of Head Work Site pump House at DEOTALA Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 2468/MD | 28/05/2025 | 45 | S. R. ENTERPRISE | 2.06 | 0 | 0 | 100
1333 | MALDAH | Malda Division | Augmentation of Deotala Water Supply Scheme , SM/09986 | Augmentation | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division Division, PHE Dte. (Car-2) (Period from 01/03/2025 to 31/08/2025). | 752/MD | 27/02/2025 | 181 | SINGH BROTHERS | 0.86 | 0 | 0 | 0
1334 | MALDAH | Malda Division | INSTALLATION OF 90 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MAHANANDATOLA,BELAIMARI,BHADO,SAMSI,CHANDMONI-I& CHANDMONI-II IN RATUA-I DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10245 | Anganwadi | Material Requisition To Resource Division | 520/MD | 03/03/2022 | 0 | Resource Division | 124.28 | 0 | 0 | 0
1335 | MALDAH | Malda Division | INSTALLATION OF 90 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MAHANANDATOLA,BELAIMARI,BHADO,SAMSI,CHANDMONI-I& CHANDMONI-II IN RATUA-I DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10245 | Anganwadi | Acceptance cum formal work order for Supplying G.I. pipe strainer for installation of CWPP at AWC of G.P.- Mahananda Tola, Belaimari, Bhado, Samsi, Chandmoni-I & Chandmoni-II in Ratua-I Dev. Block at Chanchal Stack Yard under Malda Division, PHE Dte. | 1436/MD | 20/06/2022 | 15 | M/S GOUTAM CHAKRABORTY | 16.12 | 0 | 0 | 95
1336 | MALDAH | Malda Division | INSTALLATION OF 90 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MAHANANDATOLA,BELAIMARI,BHADO,SAMSI,CHANDMONI-I& CHANDMONI-II IN RATUA-I DEV BLOCK,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10245 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) at different Anganwadi Centres (AWCs) of G.P.- Mahananda Tola, Belaimari, Bhado, Samsi, Chandmoni-I & Chandmoni-II in Ratua-I Dev. Block, Malda under Malda Division, PHE Dte. | 1133/MD | 20/05/2022 | 120 | M/S GOUTAM CHAKRABORTY | 634.77 | 0 | 0 | 99
1337 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10388 | School | Material Requisition To Resource Division | 721/MD | 25/03/2022 | 0 | Resource Division | 65.74 | 0 | 0 | 0
1338 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10388 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Harishchandrapur & Boroi GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | 90/MD | 17/01/2023 | 75 | MAMATA USHA ENTERPRISE | 188.85 | 0 | 0 | 97
1339 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10388 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Rashidabad & Kushida GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | 817/MD | 20/02/2023 | 75 | NEOGI ENTERPRISE | 129.47 | 0 | 0 | 95
1340 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10388 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Mahendrapur & Bhingole GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | 43/MD | 16/01/2023 | 563 | MILLENNIUM ENTERPRISR | 97.04 | 0 | 0 | 100
1341 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(100 nos) of Harishchandrapur-I Dev. Block, Malda under Malda Division, PHE Dte. , SM/10388 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Tulshihata GP of Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | 198/MD | 19/01/2023 | 560 | MILLENNIUM ENTERPRISR | 97.04 | 0 | 0 | 100
1342 | MALDAH | Malda Mechanical | SAHAPUR Piped Water Supply Scheme , SM/12187 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of SAHAPUR ,Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004353830 | 17/07/2023 | 90 | W.B.S.E.D.C.LTD | 8.31 | 0 | 0 | 100
1343 | MALDAH | Malda Division | SAHAPUR Piped Water Supply Scheme , SM/12187 | New | Material Requisition To Resource Division | 1616/MD | 11/04/2023 | 0 | Resource Division | 2.45 | 0 | 0 | 0
1344 | MALDAH | Malda Division | SAHAPUR Piped Water Supply Scheme , SM/12187 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 1.2 | 0 | 0 | 0
1345 | MALDAH | Malda Mechanical | SAHAPUR Piped Water Supply Scheme , SM/12187 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Sahapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013245) | 2331/MLMD | 26/07/2023 | 826 | BEE GEE CONSTRUCTION. | 13.37 | 0 | 0 | 74
1346 | MALDAH | Malda Division | SAHAPUR Piped Water Supply Scheme , SM/12187 | New | Material Requisition To Resource Division | 3996/MD | 08/08/2024 | 0 | Resource Division | 2.34 | 0 | 0 | 0
1347 | MALDAH | Malda Division | SAHAPUR Piped Water Supply Scheme , SM/12187 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of SAHAPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | 780/MD | 17/02/2023 | 30 | SAUDAGAR (INDIA) | 9.2 | 0 | 0 | 0
1348 | MALDAH | Malda Division | SAHAPUR Piped Water Supply Scheme , SM/12187 | New | Acceptance cum formal work order for Implementation of SAHAPUR Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | 594/MD | 09/02/2023 | 570 | M/S /FAIZUL HAQUE BISWAS | 57.62 | 0 | 0 | 90
1349 | MALDAH | Malda Division | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12313 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No-3 ( 135 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at PURBA BINODPUR Water Supply Scheme of Gazole Block .under Malda Division, PHE Dte. in the District of Malda. | 2305/MD | 28/09/2022 | 30 | DUTTA ENTERPRISE | 9.06 | 0 | 0 | 1
1350 | MALDAH | Malda Division | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12313 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of PURBA BINODPUR Water Supply Scheme of Gazole Block .under Malda Division, PHE Dte. in the District of Malda. | 2801/MD | 24/11/2022 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.69 | 0 | 0 | 0
1351 | MALDAH | Malda Mechanical | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12313 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Purba Binodpur PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004293401 | 16/05/2023 | 90 | W.B.S.E.D.C.LTD | 3.63 | 0 | 0 | 0
1352 | MALDAH | Malda Mechanical | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12313 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Source Augmentation of Purba Binodpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012798) | 511/MLMD | 20/03/2023 | 120 | M/S PARIMAL DAS. | 10.57 | 0 | 0 | 100
1353 | MALDAH | Malda Division | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12313 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for PURBA BINODPUR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | 2506/MD | 03/11/2022 | 530 | TARUN KUMAR DEY | 41.23 | 0 | 0 | 1
1354 | MALDAH | Malda Division | Source Augmentation of Purba Binodpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12313 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Purba Binodpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 1511/MD | 16/03/2024 | 230 | SARAJ TRADERS | 26.4 | 0 | 0 | 100
1355 | MALDAH | Malda Mechanical | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12317 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Kutubsahar PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004402679 | 29/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.54 | 0 | 0 | 100
1356 | MALDAH | Malda Mechanical | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12317 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. V of Kutub Sahar , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004496749 | 28/11/2023 | 90 | W.B.S.E.D.C.LTD | 5.28 | 0 | 0 | 100
1357 | MALDAH | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12317 | Augmentation | Material Requisition To Resource Division | 2409/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0 | 0
1358 | MALDAH | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12317 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Tubewell no. 4 site of Kutubshar Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | 1183/MD | 14/03/2024 | 180 | M/S JHA CONSTRUCTION | 17.28 | 0 | 0 | 0
1359 | MALDAH | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12317 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35 m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at 5th Tube Well Site of Kutub Sahar Water Supply Scheme of Gazole Block under Malda Division P.H.E Dte in the District of Malda. | 6411/MD | 19/12/2024 | 45 | ZEOLITE FRESH INDIA | 17.27 | 0 | 0 | 0
1360 | MALDAH | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12317 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C pipe line (damage due to widening of road) by different dia UPVC pipe for KUTUB SAHAR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | 2604/MD | 10/11/2022 | 690 | BEE GEE CONSTRUCTION | 55.12 | 0 | 0 | 65
1361 | MALDAH | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12317 | Augmentation | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200mm. Dia ) Tube Well no-4 & 5 ( 160 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at KUTUB SAHAR Water Supply Scheme of Gazole Block. under Malda Division P.H.E Dte in the District of Malda. | 2510/MD | 03/11/2022 | 30 | A. D. D. ASSOCIATES | 10.01 | 0 | 0 | 100
1362 | MALDAH | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12317 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of KUTUB SAHAR Water Supply Scheme of Gazole Block .under Malda Division P.H.E Dte in the District of Malda. | 2802/MD | 24/11/2022 | 45 | MARSS INTERNATIONAL | 6.69 | 0 | 0 | 100
1363 | MALDAH | Malda Mechanical | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12317 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. IV & V of Source Augmentation Kutub Sahar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014339) | 2577/MLMD | 04/08/2023 | 120 | MAA BHABOTARINE ENTERPRISE. | 23.05 | 0 | 0 | 100
1364 | MALDAH | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12317 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Tube Well No.-5 site in connection with Source Augmentation of KUTUB SAHAR Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | 3055/MD | 09/08/2023 | 45 | A. L. ENGINEERING SOLUTION | 4.15 | 0 | 0 | 100
1365 | MALDAH | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12317 | Augmentation | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well No. - 5 (160 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at KUTUB SAHAR Water Supply Scheme of Gazole Block of Malda District under Malda Division, PHE Dte. | 3352/MD | 29/08/2023 | 30 | A. L. ENGINEERING SOLUTION | 11.88 | 0 | 0 | 100
1366 | MALDAH | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12317 | Augmentation | Construction of Boundary Wall of Tubewell site at Misipur Mouza of Kutubsahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 1250/MD | 15/03/2024 | 382 | SATELLITE CONSTRUCTION | 9.6 | 0 | 0 | 100
1367 | MALDAH | Malda Division | Source Augmentation of Kutub Sahar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12317 | Augmentation | Construction of Boundary Wall of Tubewell site at Khord Babupur Mouza of Kutub Sahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 1193/MD | 14/03/2024 | 293 | AHONA ENTERPRISE | 10.71 | 0 | 0 | 100
1368 | MALDAH | Malda Mechanical | JAMALPUR Piped Water Supply Scheme. , SM/12879 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Jamalpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013493) | 2800/MLMD | 17/08/2023 | 714 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 27.35 | 0 | 0 | 30
1369 | MALDAH | Malda Division | JAMALPUR Piped Water Supply Scheme. , SM/12879 | New | Construction of Boundary Wall at 2nd Tubewell site of Jamalpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 1259/MD | 15/03/2024 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 8.5 | 0 | 0 | 0
1370 | MALDAH | Malda Division | JAMALPUR Piped Water Supply Scheme. , SM/12879 | New | Construction of Boundary Wall at Head work site of Jamalpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 5001/MD | 27/09/2024 | 45 | PABITRA MANDAL | 23.69 | 0 | 0 | 0
1371 | MALDAH | Malda Division | JAMALPUR Piped Water Supply Scheme. , SM/12879 | New | Material Requisition To Resource Division | 123/MD | 06/01/2024 | 0 | Resource Division | 46.72 | 0 | 0 | 0
1372 | MALDAH | Malda Division | JAMALPUR Piped Water Supply Scheme. , SM/12879 | New | Formal work order for the work of Implementation of JAMALPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1570/MD | 10/04/2023 | 933 | MAHAVIR PUMPS MANUFACTURING PVT. LTD. | 735.7 | 0 | 0 | 30
1373 | MALDAH | Malda Division | JAMALPUR Piped Water Supply Scheme. , SM/12879 | New | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works of Krishnapur, Horgoa, Perapur, Jamalpur & Rajarampur PWSS under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 642/MD | 19/02/2025 | 7 | SADHANA CONSTRUCTION | 0.8 | 0 | 0 | 0
1374 | MALDAH | Malda Division | JAMALPUR Piped Water Supply Scheme. , SM/12879 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Jamalpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda | 1298/MD | 04/04/2025 | 272 | UTTAM KUMAR GHOSH | 96.59 | 0 | 0 | 0
1375 | MALDAH | Malda Division | JAMALPUR Piped Water Supply Scheme. , SM/12879 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of JAMALPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 1061/MD | 15/03/2023 | 60 | BINA CONSTRUCTION | 51.95 | 0 | 0 | 100
1376 | MALDAH | Malda Division | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12316 | Augmentation | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200mm. Dia) Tube Well no-3 (100 Mtr. deep )by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MIANAGAR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | 2300/MD | 28/09/2022 | 30 | MECHANO TRADING CO. | 7.59 | 0 | 0 | 100
1377 | MALDAH | Malda Mechanical | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12316 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. of Mianagar, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004369303 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.64 | 0 | 0 | 100
1378 | MALDAH | Malda Division | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12316 | Augmentation | Construction of Boundary Wall at Mianagar Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 1253/MD | 15/03/2024 | 30 | CHARU CONSTRUCTION | 9.61 | 0 | 0 | 0
1379 | MALDAH | Malda Division | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12316 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for MIANAGAR Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | 2504/MD | 03/11/2022 | 45 | DEBAPRIYA SAHA | 76.83 | 0 | 0 | 100
1380 | MALDAH | Malda Division | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12316 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of MIANAGAR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte. in the District of Malda. | 2548/MD | 03/11/2022 | 45 | ANJIMA CONSTRUCTION CO. | 6.69 | 0 | 0 | 100
1381 | MALDAH | Malda Mechanical | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12316 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Mianagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014342) | 2144/MLMD | 07/07/2023 | 120 | A.S. ENGINEERING | 10.52 | 0 | 0 | 100
1382 | MALDAH | Malda Mechanical | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12316 | Augmentation | Quotation Payment of MIYANAGAR Under AIHO CCC Under the district of Malda. | BP-2024-25-63 | 09/04/2024 | 0 | W.B.S.E.D.C.LTD | 3.17 | 0 | 0 | 0
1383 | MALDAH | Malda Division | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12316 | Augmentation | Augmentation of Head work site Pump House,PUMP House No.-2 ,Earth filling and 2 Nos. Boundary wall at MIANAGAR Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1119/MD | 21/03/2025 | 45 | CHARU CONSTRUCTION | 9.63 | 0 | 0 | 0
1384 | MALDAH | Malda Division | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12316 | Augmentation | Laying of Pipeline work at Mianagar Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 3197/MD | 27/06/2024 | 45 | CHARU CONSTRUCTION | 18.22 | 0 | 0 | 100
1385 | MALDAH | Malda Division | Source Augmentation of Mianagar Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12316 | Augmentation | Replacement of 200 mm (all through)Big Dia. Tubewell No:-1 (130MDeep) at Headwork site by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at MIANAGAR Water Supply Scheme of Habibpur Block under Malda Division, PHE Dte,in the District of Malda. | 4806/MD | 13/09/2024 | 152 | JOY GURU ENTERPRISE | 9.56 | 0 | 0 | 100
1386 | MALDAH | Malda Division | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. , SM/13721 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 15.2 | 0 | 0 | 0
1387 | MALDAH | Malda Mechanical | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. , SM/13721 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Duba Khoskoan Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014431) | 2386/MLMD | 28/07/2023 | 869 | MANIK CHANDRA SAHA. | 27.39 | 0 | 0 | 70
1388 | MALDAH | Malda Division | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. , SM/13721 | New | Material Requisition To Resource Division | 249/MD | 10/01/2024 | 0 | Resource Division | 14.04 | 0 | 0 | 0
1389 | MALDAH | Malda Mechanical | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. , SM/13721 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Dubakhoskan, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-672 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.51 | 0 | 0 | 0
1390 | MALDAH | Malda Mechanical | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. , SM/13721 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dubakhoskan, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-671 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.58 | 0 | 0 | 0
1391 | MALDAH | Malda Division | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. , SM/13721 | New | Formal work order for the work of Implementation of DUBA KHOSKON Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3118/MD | 11/08/2023 | 509 | M/S NANDY ENTERPRISES | 904.54 | 0 | 0 | 0
1392 | MALDAH | Malda Division | DUBA KHOSKOAN PIPED WATER SUPPLY SCHEME. , SM/13721 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at DubaKhaskon Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6417/MD | 19/12/2024 | 286 | M/S MANDAL & SONS | 36.96 | 0 | 0 | 0
1393 | MALDAH | Malda Division | BISHANPUR PIPED WATER SUPPLY SCHEME , SM/13507 | New | Material Requisition To Resource Division | 1803/MD | 27/04/2023 | 0 | Resource Division | 38.38 | 0 | 0 | 0
1394 | MALDAH | Malda Division | BISHANPUR PIPED WATER SUPPLY SCHEME , SM/13507 | New | Material Requisition To Resource Division | 93/MD | 05/01/2024 | 0 | Resource Division | 8.31 | 0 | 0 | 0
1395 | MALDAH | Malda Mechanical | BISHANPUR PIPED WATER SUPPLY SCHEME , SM/13507 | New | New service connection at BISHANPUR PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( KUSHIDA c c c) | BP-2024-25-87 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 14.51 | 0 | 0 | 0
1396 | MALDAH | Malda Mechanical | BISHANPUR PIPED WATER SUPPLY SCHEME , SM/13507 | New | New service connection at BISHANPUR T/W NO I Under EE/MLMD PHE DTE DIST. Malda.( KUSHIDA c c c) | BP-2024-25-86 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 4.65 | 0 | 0 | 0
1397 | MALDAH | Malda Division | BISHANPUR PIPED WATER SUPPLY SCHEME , SM/13507 | New | Formal work order for the work of Implementation of BISHANPUR Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1911/MD | 11/05/2023 | 270 | A. K. CONSTRUCTION | 349.38 | 0 | 0 | 25
1398 | MALDAH | Malda Mechanical | BISHANPUR PIPED WATER SUPPLY SCHEME , SM/13507 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Bishanpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014466) | 2384/MLMD | 28/07/2023 | 824 | DAS ENTERPRISE. | 26.53 | 0 | 0 | 82
1399 | MALDAH | Malda Division | BISHANPUR PIPED WATER SUPPLY SCHEME , SM/13507 | New | Erection of Property board related to Jal Jeevan Mission works of Choupaldanga, Wari, Gochiya, Bangrua, Kharangapur Jabra, Bishanpur PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 646/MD | 19/02/2025 | 7 | RAHANUL ALAM | 0.95 | 0 | 0 | 100
1400 | MALDAH | Malda Division | BISHANPUR PIPED WATER SUPPLY SCHEME , SM/13507 | New | Erection of Property board related to Jal Jeevan Mission works of Bhakri, Chandrapara & Dhangra Bishanpur GP under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | 634/MD | 19/02/2025 | 7 | BIDYUT MAHALDAR | 0.9 | 0 | 0 | 0
1401 | MALDAH | Malda Division | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15102 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 (102.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at NEMUA Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | 1168/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 7.8 | 0 | 0 | 100
1402 | MALDAH | Malda Division | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15102 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Nemua Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | 1205/MD | 21/03/2023 | 45 | BINA CONSTRUCTION | 4.15 | 0 | 0 | 100
1403 | MALDAH | Malda Mechanical | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15102 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Nemua PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004375746 | 01/09/2023 | 90 | W.B.S.E.D.C.LTD | 7.84 | 0 | 0 | 100
1404 | MALDAH | Malda Division | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15102 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning,and 3 (three) months Trial Run and 40 cum/hr. capacity of Iron Elimination Plants (Pressure type) with provision of polishing unit alongwith Construction of 3.60 mtr.X 3.00 mtr Blower Room in connection with source Augmentation at 3rd Tube Well site of NEMUA Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | 4113/MD | 10/10/2023 | 120 | DEBAPRIYA SAHA | 17.17 | 0 | 0 | 90
1405 | MALDAH | Malda Division | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15102 | Augmentation | Material Requisition To Resource Division | 776/MD | 20/02/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
1406 | MALDAH | Malda Mechanical | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15102 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Source Augmentation Nemua Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | 2946/MLMD | 11/09/2024 | 90 | JOY MAA SANTOSHI ENTERPRISE. | 11.4 | 0 | 0 | 100
1407 | MALDAH | Malda Division | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15102 | Augmentation | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 2nd Tube Well Site of NEMUA Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | 2393/MD | 26/05/2025 | 75 | SURAJIT MONDAL | 5.98 | 0 | 0 | 0
1408 | MALDAH | Malda Division | Source Augmentation of Nemua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15102 | Augmentation | Construction of Boundary Wall and Pathway at 3rd Tube Well Site of Nemua Piped Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | 804/MD | 21/02/2024 | 273 | GOUTAM SAHA | 8.77 | 0 | 0 | 60
1409 | MALDAH | Malda Division | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15108 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 96.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at SAILPUR Water Supply Scheme of Englishbazar Block under Malda Division P.H.E Dte in the District of Malda. | 1167/MD | 20/03/2023 | 30 | ABHIJIT PAUL | 6.21 | 0 | 0 | 100
1410 | MALDAH | Malda Mechanical | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15108 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Sailpur, Fulbari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004454388 | 09/10/2023 | 90 | W.B.S.E.D.C.LTD | 7.69 | 0 | 0 | 100
1411 | MALDAH | Malda Division | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15108 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Sailpur Piped Water Supply Scheme at Englishbazar Block of Malda District under Malda Division, PHE Dte. | 1306/MD | 23/03/2023 | 45 | M/S A. B. CONSTRUCTION | 4.14 | 0 | 0 | 95
1412 | MALDAH | Malda Division | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15108 | Augmentation | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for SAILPUR Piped Water Supply Scheme at Englishbazar Dev. Block of Malda District under Malda Division, PHE Dte. | 1157/MD | 20/03/2023 | 45 | S. R. CONSTRUCTION | 18.8 | 0 | 0 | 79
1413 | MALDAH | Malda Mechanical | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15108 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of source augmentation of Sailpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte.(TSM/016471) | 2627/MLMD | 10/08/2023 | 180 | KUNDU CONSTRUCTION. | 10.52 | 0 | 0 | 70
1414 | MALDAH | Malda Division | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15108 | Augmentation | Material Requisition To Resource Division | 775/MD | 20/02/2024 | 0 | Resource Division | 1.85 | 0 | 0 | 0
1415 | MALDAH | Malda Division | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15108 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 20m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Sailpur Water Supply Scheme of Englishbazar Block under Malda Division P.H.E Dte in the District of Malda. (3rd Call). | 2421/MD | 27/05/2025 | 180 | M/S KUNDU CONSTRUCTION | 14.62 | 0 | 0 | 0
1416 | MALDAH | Malda Division | Source Augmentation of Sailpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15108 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sailpur Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | 703/MD | 21/02/2025 | 45 | CHARU CONSTRUCTION | 27.37 | 0 | 0 | 0
1417 | MALDAH | Malda Mechanical | FATEPUR Piped Water Supply Scheme , SM/14173 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Fatepur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015785) | 2388/MLMD | 28/07/2023 | 180 | NUPUR CHANDRA HALDER | 42.13 | 0 | 0 | 51
1418 | MALDAH | Malda Division | FATEPUR Piped Water Supply Scheme , SM/14173 | New | Construction of Boundary Wall at Head Work site of Fatepur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3229/MD | 28/06/2024 | 637 | THREE BROTHERS CONSTRUCTION & CO | 26.65 | 0 | 0 | 60
1419 | MALDAH | Malda Division | FATEPUR Piped Water Supply Scheme , SM/14173 | New | Material Requisition To Resource Division | 124/MD | 06/01/2024 | 0 | Resource Division | 121.21 | 0 | 0 | 0
1420 | MALDAH | Malda Division | FATEPUR Piped Water Supply Scheme , SM/14173 | New | Material Requisition To Resource Division | 243/MD | 10/01/2024 | 0 | Resource Division | 13.18 | 0 | 0 | 0
1421 | MALDAH | Malda Mechanical | FATEPUR Piped Water Supply Scheme , SM/14173 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Fatepur, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte | BP-2024-25-196 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 11.26 | 0 | 0 | 0
1422 | MALDAH | Malda Mechanical | FATEPUR Piped Water Supply Scheme , SM/14173 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Fatepur, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte | BP-2024-25-195 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 10.78 | 0 | 0 | 0
1423 | MALDAH | Malda Division | FATEPUR Piped Water Supply Scheme , SM/14173 | New | Formal work order for the work of Implementation of FATEPUR and its adjoinining mouzas Piped Water Supply Scheme at Gazol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1028/MD | 13/03/2023 | 1115 | GHOSH BROTHERS | 1157.58 | 0 | 0 | 50
1424 | MALDAH | Malda Ars Area W/S Division | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Gopalpur -I & II water supply schemes under Malda Arsenic area water supply Division, PHED , SM/15143 | Augmentation | Repairing work of Existing house connection, and Laying of damage UPVC Pipeline at Budhia Dubri under Jote Basanta Distribution zone under Malda Arsenic Area Water Supply Division PHED. | 1869MAAD | 28/09/2022 | 45 | M/S PARIMAL DAS | 6.24 | 0 | 0 | 1
1425 | MALDAH | Malda Ars Area W/S Division | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Gopalpur -I & II water supply schemes under Malda Arsenic area water supply Division, PHED , SM/15143 | Augmentation | Construction of Arsenic-cum-Iron Removal Plant (AIRP) of capacity 52.0 Cum/ Hr at Gopalpur Water Supply Scheme Zone-I under Malda Arsenic Area W/S Division, P.H.E. Dte. | 128/MAAD | 21/01/2021 | 270 | MILLENNIUM ENTERPRISE | 139.74 | 0 | 0 | 80
1426 | MALDAH | Malda Mechanical | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Gopalpur -I & II water supply schemes under Malda Arsenic area water supply Division, PHED , SM/15143 | Augmentation | NEW SERVICE CONNECTION CHARGE FOR GOPALPUR W S SCHEME | BP-2023-24-94 | 13/07/2023 | 0 | W.B.S.E.D.C.LTD | 1.73 | 0 | 0 | 0
1427 | MALDAH | Malda Mechanical | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Gopalpur -I & II water supply schemes under Malda Arsenic area water supply Division, PHED , SM/15143 | Augmentation | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Arsenic Iron Removal Plant at Gopalpur (Zone-I) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. | 763/MLMD | 26/04/2023 | 180 | DILIP MAHATO. | 46.07 | 0 | 0 | 61
1428 | MALDAH | Malda Ars Area W/S Division | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Gopalpur -I & II water supply schemes under Malda Arsenic area water supply Division, PHED , SM/15143 | Augmentation | Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 42.00 M³/ Hr. capacity Iron Elimination Plant (Pressure type) for Gopalpur Zone-II Water Supply Scheme at Manikchak Dev. Block under Malda Arsenic Area Water Supply Division, PHE Dte. in the district of Malda. | 401/MAAD | 06/03/2023 | 514 | SHREE BISHNU CONSTRUCTION | 18.65 | 0 | 0 | 54
1429 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED , SM/15144 | Augmentation | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 120 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 692/MAAD | 13/04/2023 | 45 | M/S DYNAMIC CONSTRUCTION | 7.38 | 0 | 0 | 100
1430 | MALDAH | Malda Mechanical | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED , SM/15144 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Daibakipur, Uttar Nazirpur, Fulbari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte | 3004409374 | 31/08/2023 | 90 | W.B.S.E.D.C.LTD | 4.88 | 0 | 0 | 100
1431 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED , SM/15144 | Augmentation | Route servey & design for prepration of DPR of Uttar Nazirpur, Sakullapur & Nabinagar Piped Water Supply Scheme at Englishbazar & Kaliachak - II Development Block under Malda Arsenic Area W/S Division, PHE Dte. in the district of Malda. | 1763/MAAD | 30/09/2023 | 15 | FUTURE | 0.99 | 0 | 0 | 100
1432 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED , SM/15144 | Augmentation | Laying of Distribution System and other allied works at Satichura in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 1710/MAAD | 20/09/2023 | 90 | M/S. AYUSH BUILDERS | 11.67 | 0 | 0 | 75
1433 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED , SM/15144 | Augmentation | Laying of Distribution System and other allied works at Daibakipur & Paharipara in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. | 3074/MAAD | 14/12/2023 | 60 | MAHA MAYA CONSTRUCTION | 16.89 | 0 | 0 | 85
1434 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED , SM/15144 | Augmentation | Construction of 5.40 mtr.X 3.6 mtr 3rd Pump House with Water Supply and sanitary arrangement in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 691/MAAD | 13/04/2023 | 60 | HIND CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 6.52 | 0 | 0 | 100
1435 | MALDAH | Malda Mechanical | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED , SM/15144 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of source augmentation of Uttar Nazirpur Water Supply Scheme in the District of under Malda Mechanical Division, PHE Dte.(TSM/017480) | 2631/MLMD | 10/08/2023 | 180 | FUTURE | 10.51 | 0 | 0 | 80
1436 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED , SM/15144 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) under command area of Uttar Nazirpur Water Supply Scheme (Augmentation) at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 304/MAAD | 11/03/2024 | 30 | PRITAM ENTERPRISE | 9.05 | 0 | 0 | 100
1437 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED , SM/15144 | Augmentation | Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 23.38 M³/ Hr. capacity Iron Elimination Plant (Pressure type) including construction of switch room in connection with source Augmentation of Uttar Nazirpur Piped Water Supply Scheme at English Bazar Dev. Block under Malda Arsenic Area Water Supply Division, PHE Dte. in the district of Malda. | 947/MAAD | 23/05/2023 | 540 | SOVON KUMAR DAS | 15.66 | 0 | 0 | 100
1438 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Uttar Nazirpur Piped water supply scheme under Malda arsenic Area w/s Division, PHED , SM/15144 | Augmentation | Construction of Boundary Wall at 3rd Pump House Site, Laying of distribution system and providing FHTC of Uttar Nazirpur Distribution Zone at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1700/MAAD | 19/11/2024 | 90 | DEY CONSTRUCTION | 25.94 | 0 | 0 | 100
1439 | MALDAH | Malda Division | DILALBATI Piped Water Supply Scheme. , SM/15903 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 7.53 | 0 | 0 | 0
1440 | MALDAH | Malda Division | DILALBATI Piped Water Supply Scheme. , SM/15903 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work Site of DILALBATI Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | 1130/MD | 20/03/2023 | 45 | SOFIKUL ISLAM | 6.54 | 0 | 0 | 100
1441 | MALDAH | Malda Division | DILALBATI Piped Water Supply Scheme. , SM/15903 | New | Material Requisition To Resource Division | 242/MD | 10/01/2024 | 0 | Resource Division | 2.56 | 0 | 0 | 0
1442 | MALDAH | Malda Mechanical | DILALBATI Piped Water Supply Scheme. , SM/15903 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Dilalbati, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-669 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 19.71 | 0 | 0 | 0
1443 | MALDAH | Malda Mechanical | DILALBATI Piped Water Supply Scheme. , SM/15903 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Dilalbati, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-670 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 6.45 | 0 | 0 | 0
1444 | MALDAH | Malda Mechanical | DILALBATI Piped Water Supply Scheme. , SM/15903 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Dilalbati Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014129) | 2569/MLMD | 04/08/2023 | 787 | M/S PARIMAL DAS. | 23.98 | 0 | 0 | 85
1445 | MALDAH | Malda Division | DILALBATI Piped Water Supply Scheme. , SM/15903 | New | Formal work order for the work of Implementation of DILALBATI Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3285/MD | 23/08/2023 | 1010 | ZEST INFRACON | 155.98 | 0 | 0 | 50
1446 | MALDAH | Malda Division | DILALBATI Piped Water Supply Scheme. , SM/15903 | New | Erection of Property board related to Jal Jeevan Mission works of Saidpur, Alal Zone-I, II, III, Rahimpur, Dilalbati & Altor PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 641/MD | 19/02/2025 | 7 | S. N. CONSTRUCTION | 0.95 | 0 | 0 | 0
1447 | MALDAH | Malda Division | DILALBATI Piped Water Supply Scheme. , SM/15903 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Dilalbati Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 2483/MD | 28/05/2025 | 126 | M/S GLOBAL ENTERPRISE | 4.85 | 0 | 0 | 0
1448 | MALDAH | Malda Division | DILALBATI Piped Water Supply Scheme. , SM/15903 | New | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of DILALBATI Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | 1135/MD | 20/03/2023 | 45 | UNITED FRIENDS UNEMPLOYED ENGG CO-OPE SOCEITY LTD | 4.15 | 0 | 0 | 100
1449 | MALDAH | Malda Mechanical | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED , SM/15947 | New | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Gayeshbari Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/018180) | 2685/MLMD | 11/08/2023 | 180 | SUNRISE ENGINEERING CORPORATION. | 63.77 | 0 | 0 | 0
1450 | MALDAH | Malda Ars Area W/S Division | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED , SM/15947 | New | Laying of Distribution System including Supply of all type of specials & valves for Gayeshbari Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 3076/MAAD | 14/12/2023 | 361 | FUTURE | 96.7 | 0 | 0 | 35
1451 | MALDAH | Malda Ars Area W/S Division | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED , SM/15947 | New | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Gayeshbari Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1693/MAAD | 19/11/2024 | 60 | M/S MOON LIGHT CONSTRUCTION & CO. | 75.67 | 0 | 0 | 0
1452 | MALDAH | Malda Ars Area W/S Division | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED , SM/15947 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Gayeshbari Piped Water supply scheme (Head Work Site & 2nd Tube Well Site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda (2nd Call) | 1478/MAAD | 01/08/2023 | 45 | ASHIS CONSTRUCTION | 14.64 | 0 | 0 | 50
1453 | MALDAH | Malda Mechanical | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED , SM/15947 | New | Quotation Payment for Gayeshbari under SUJAPUR CCC in the District Of Malda | BP-2023-24-564 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 7.72 | 0 | 0 | 0
1454 | MALDAH | Malda Ars Area W/S Division | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED , SM/15947 | New | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Gayeshbari Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. (2ND Call) | 3082/MAAD | 14/12/2023 | 688 | MAHBUB AND SONS | 225.34 | 0 | 0 | 75
1455 | MALDAH | Malda Ars Area W/S Division | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED , SM/15947 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Gayeshbari Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. (2nd Call) | 52/MAAD | 18/01/2024 | 439 | WIST WATER SOLUTIONS PRIVATE LIMITED | 166.2 | 0 | 0 | 1
1456 | MALDAH | Malda Ars Area W/S Division | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED , SM/15947 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site of Gayeshbari Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 1479/MAAD | 01/08/2023 | 335 | PRITAM ENTERPRISE | 5.02 | 0 | 0 | 100
1457 | MALDAH | Malda Ars Area W/S Division | Gayeshbari mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED , SM/15947 | New | Laying of Distribution System at Nayabasti, Jamirghata Station Road for Gayeshbari Piped Water supply scheme at Kaliachak-I Block under Malda Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 3073/MAAD | 14/12/2023 | 60 | GHOSH CONSTRUCTION | 18 | 0 | 0 | 100
1458 | MALDAH | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme , SM/15951 | Augmentation | Acceptance cum formal work order for Route survey, design and preparation of DPR of Alal Zone-III Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. | 653/MD | 22/03/2022 | 15 | TECHVISION | 2.95 | 0 | 0 | 1
1459 | MALDAH | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme , SM/15951 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 19.37 | 0 | 0 | 0
1460 | MALDAH | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme , SM/15951 | Augmentation | Material Requisition To Resource Division | 245/MD | 10/01/2024 | 0 | Resource Division | 4.42 | 0 | 0 | 0
1461 | MALDAH | Malda Mechanical | Augmentation of Alal Zone-III Piped Water Supply Scheme , SM/15951 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Alal Zone-III, Gazole CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-711 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.31 | 0 | 0 | 0
1462 | MALDAH | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme , SM/15951 | Augmentation | Formal work order for the work of Augmentation of ALAL ZONE- III Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2324/MD | 08/06/2023 | 1152 | SAMBHU NATH SARKAR | 283.63 | 0 | 0 | 85
1463 | MALDAH | Malda Mechanical | Augmentation of Alal Zone-III Piped Water Supply Scheme , SM/15951 | Augmentation | Supply, installation, commissioning and Trial Operation of electro-mechanical components at T/W no I and Supply, installation, commissioning of electro-mechanical components at T/W no II and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at headwork site of Alal Zone-III Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011885) | 2721/MLMD | 14/08/2023 | 2005 | M/S TRILOCHAN CONSTRUCTION CO. | 24.32 | 0 | 0 | 47
1464 | MALDAH | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme , SM/15951 | Augmentation | Dedicated Pipe laying for better Functionality and Providing Balance FHTC, Construction of Approach Road, Land development and allied work for ALAL Zone-III Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte. Govt. of West Bengal. | 3776/MD | 04/08/2025 | 60 | SAMBHU NATH SARKAR | 11.17 | 0 | 0 | 0
1465 | MALDAH | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme , SM/15951 | Augmentation | Construction of Boundary Wall at Head Work site of Alal Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3214/MD | 27/06/2024 | 247 | SAMBHU NATH SARKAR | 28.48 | 0 | 0 | 100
1466 | MALDAH | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme , SM/15951 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alal Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 5917/MD | 26/11/2024 | 176 | ABHIJIT CONSTRUCTION | 14.16 | 0 | 0 | 100
1467 | MALDAH | Malda Division | Augmentation of Alal Zone-III Piped Water Supply Scheme , SM/15951 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at ALAL ZONE-III Piped Water Supply Scheme under Gazole Block under Malda Division, PHE Dte, Govt. of West Bengal. | 831/MD | 21/02/2024 | 45 | SADHANA CONSTRUCTION | 4.16 | 0 | 0 | 100
1468 | MALDAH | Malda Mechanical | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15944 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of Bakhrabad PWSS, Golapganj C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004379428 | 01/08/2023 | 90 | W.B.S.E.D.C.LTD | 2.27 | 0 | 0 | 100
1469 | MALDAH | Malda Ars Area W/S Division | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15944 | New | Material Requisition To Resource Division | 626/MAAD | 05/04/2023 | 0 | Resource Division | 6.21 | 0 | 0 | 0
1470 | MALDAH | Malda Ars Area W/S Division | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15944 | New | Laying of Distribution System & others allied works at Kumbhira under Bakhrabad Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte.(Kaliachak-III) | 1477/MAAD | 01/08/2023 | 60 | S. R. CONSTRUCTION | 63.18 | 0 | 0 | 95
1471 | MALDAH | Malda Ars Area W/S Division | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15944 | New | Construction of Boundary Wall at Head Work Site , C.C road from existing road to Head works Site and Land Development Work for HWS ,Providing Functional House Hold Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM & Jal Swapna), Laying of rising main from Tube Well Site to HWS & including supply of all specials & valves for Bakhrabad Piped Water Supply scheme at Kaliachak-III Development Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1699/MAAD | 19/11/2024 | 45 | SOVON KUMAR DAS | 40.39 | 0 | 0 | 0
1472 | MALDAH | Malda Ars Area W/S Division | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15944 | New | Laying of Distribution System & others allied works at Char Bakrabad under Bakhrabad Piped Water supply scheme of Southern sector under Malda Arsenic Area W/S Division, P.H.E.Dte.(Kaliachak-III) | 1476/MAAD | 01/08/2023 | 60 | DEY CONSTRUCTION | 65.47 | 0 | 0 | 80
1473 | MALDAH | Malda Ars Area W/S Division | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15944 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Bakhrabad Piped Water supply scheme of Kaliachak-III Block (Head work site) under Malda arsenic Area water supply Division in the disrtict of Malda. | 1475/MAAD | 01/08/2023 | 45 | MD. TALEB ALI | 7.65 | 0 | 0 | 100
1474 | MALDAH | Malda Mechanical | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15944 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I and Arsenic Iron Removal Plant at Bakhrabad Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017774) | 2689/MLMD | 11/08/2023 | 716 | GHOSH BROTHERS... | 49.58 | 0 | 0 | 0
1475 | MALDAH | Malda Ars Area W/S Division | Bakhrabad Mouza piped water supply Scheme of Kaliachak-III block under Malda Arsenic Area water supply Division, PHED , SM/15944 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) at Bakrabad Piped Water supply scheme of Kaliachak-III Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | 51/MAAD | 18/01/2024 | 561 | WIST WATER SOLUTIONS PRIVATE LIMITED | 131.25 | 0 | 0 | 15
1476 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHAMMADPUR Water Supply Scheme , SM/06865 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | 2719/MD | 10/11/2020 | 30 | MANAS KUMAR SAHA | 50.07 | 6 | 100 | 1
1477 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHAMMADPUR Water Supply Scheme , SM/06865 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of MAHAMMADPUR Water Supply Scheme at Malda Old Block under Malda Division, PHE Dte. | 1963/MD | 31/08/2020 | 30 | A. K. CONSTRUCTION | 25.17 | 22.48 | 100 | 0
1478 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHAMMADPUR Water Supply Scheme , SM/06865 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of MAHAMMADPUR Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 4770/MD | 05/12/2023 | 45 | M/S EHAN ENTERPRISE | 8.07 | 0 | 0 | 100
1479 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHAMMADPUR Water Supply Scheme , SM/06865 | Retrofitting | Replacement of 200 mm dia. X 150 mm Dia.) Tubewell No:-2 (130 M Deep) by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at MAHAMMADPUR Water Supply Scheme of Old Malda Block under Malda Division, PHE Dte. | 4807/MD | 13/09/2024 | 78 | GOBINDA ENTERPRISE | 8.29 | 0 | 0 | 100
1480 | MALDAH | Malda Mechanical | SOURCE AUGMENTATION TROUGH INTRODUCING ROLLING TYPE BARGE FOR RAW WATER LIFTING FROM RIVER FULHAR AT INTAKE STATION OF BALUPUR WATER SUPPLY SCHEME UNDER RATUA-I BLOCK IN THE DISTRICT OF MALDA UNDER MALDA MECHANICAL DIVISION, PHE DTE. , SM/18911 | Augmentation | Formal Work Order for Design, manufacture, installation and commissioning of rolling pontoon type dismantling barge along with electro-mechanical equipments on river Fulhar at lntake Station of Balupur water supply scheme under Ratua-l Block in the District of Malda under Malda Mechanical Division, PHE Dte. | 995/MLMD | 07/03/2024 | 184 | SUNRISE ENGINEERING CORPORATION. | 105.37 | 0 | 0 | 39
1481 | MALDAH | Malda Division | SERBABAR BALARAMPUR Piped Water Supply Scheme , SM/12184 | New | Material Requisition To Resource Division | 3043/MD | 12/12/2022 | 0 | Resource Division | 25.7 | 0 | 0 | 0
1482 | MALDAH | Malda Division | SERBABAR BALARAMPUR Piped Water Supply Scheme , SM/12184 | New | Material Requisition To Resource Division | 1809/MD | 27/04/2023 | 0 | Resource Division | 18.28 | 0 | 0 | 0
1483 | MALDAH | Malda Division | SERBABAR BALARAMPUR Piped Water Supply Scheme , SM/12184 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Serbabar Balarampur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 6364/MD | 17/12/2024 | 45 | JAHANGIR ALAM | 58.94 | 0 | 0 | 0
1484 | MALDAH | Malda Mechanical | SERBABAR BALARAMPUR Piped Water Supply Scheme , SM/12184 | New | New service connection at SERBABBAR BALARAMPUR PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.(CHANCHAL c c c) | BP-2024-25-92 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 10.05 | 0 | 0 | 0
1485 | MALDAH | Malda Mechanical | SERBABAR BALARAMPUR Piped Water Supply Scheme , SM/12184 | New | New service connection at serbabbar balarampur under MLMD/PHE Dist. malda (chanchal c.c.c) | BP-2023-24-560 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 5.87 | 0 | 0 | 0
1486 | MALDAH | Malda Division | SERBABAR BALARAMPUR Piped Water Supply Scheme , SM/12184 | New | Formal work order for the work of Implementation of SERBABAR BALARAMPUR Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2019/MD | 18/05/2023 | 594 | JAHANGIR ALAM | 596.09 | 0 | 0 | 75
1487 | MALDAH | Malda Mechanical | SERBABAR BALARAMPUR Piped Water Supply Scheme , SM/12184 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Serbabar Balarampur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013253) | 2330/MLMD | 26/07/2023 | 916 | DEY ENTERPRISE.. | 28.99 | 0 | 0 | 84
1488 | MALDAH | Malda Division | SERBABAR BALARAMPUR Piped Water Supply Scheme , SM/12184 | New | Construction of Boundary Wall at Head Work site of Serbabar Balarampur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | 2691/MD | 04/06/2025 | 45 | JAHANGIR ALAM | 28.62 | 0 | 0 | 0
1489 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Krishnapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09650 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA)at Sisa, Bhagabanpur& others Allied works at Krishnapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 1021/MAAD | 12/05/2022 | 45 | SUDIP DEY | 15.28 | 0 | 0 | 1
1490 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Krishnapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09650 | Retrofitting | Providing Functional household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Krishnapur Water Supply Scheme (Jagirtola, Krishnapur Chama, Bechutola, Rajutola, Guntola, Mandai, Mandaichaipara, Nashtola joenpur, Chakbahadurpur, Bintola, Sachitrapara, Kopatola, Krishnapur, Kacharitola & KBS) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 50/MAAD | 20/01/2022 | 90 | ALOK ENTERPRISE. A UNIT OF SAKET TREXIM PVT. LTD. | 206.62 | 0 | 0 | 100
1491 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Krishnapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09650 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
1492 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme , SM/06858 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme at Harshchandrapur-II Block under Malda Division, PHE Dte. | 3046/MD | 11/12/2020 | 30 | S DUTTA | 44.04 | 34.78 | 44.2 | 1
1493 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme , SM/06858 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DHANJANA Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 2718/MD | 10/11/2020 | 30 | NIRENDRA NATH KUNDU | 58.72 | 0 | 0 | 1
1494 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme , SM/06858 | Retrofitting | Acceptance cum formal work order for Additional laying work of DI & UPVC pipe line of SADLICHAK W/S Scheme at HARISHCHANDRAPUR-II Dev. Block under Malda division.P.H.E.Dte. In the District of Malda. | 47/CSD | 14/01/2022 | 30 | BEE GEE CONSTRUCTION | 4.19 | 0 | 0 | 1
1495 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN GOURIPUR Water Supply Scheme , SM/06858 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Mouza- Dakshin Gouripur, Village-Baghuya, JL No. 167 GP-Malior-II of DAKSHIN GOURIPUR Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | 2736/MD | 18/11/2022 | 30 | M/S SABANA CONSTRUCTION | 3.28 | 0 | 0 | 100
1496 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme , SM/06871 | Retrofitting | Stationary Bill under Malda Division, PHE Dte. n the district of Malda | 1969/MD | 26/08/2022 | 1 | MALDA DISTRICT SERVICE CUM-MARKETING INDS. CO-OP UNION LTD. | 1.26 | 0 | 0 | 1
1497 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme , SM/06871 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | 2446/MD | 12/10/2020 | 30 | KRISHNENDU DUTTA | 43.4 | 0 | 0 | 1
1498 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme , SM/06871 | Retrofitting | Acceptance cum formal work order for Detail route survey and design & drawing of distribution network, for providing FHTC in Uttar Chandipur Zone-I Water Supply scheme of Manikchak Block in the District of Malda under Malda Division, P.H.E.Dte. | 478/MSD | 09/12/2022 | 15 | FUTURE | 0.84 | 0 | 0 | 1
1499 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme , SM/06871 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Village- Chatra, JL. No. 29, G.P.-Aktail of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 2453/MD | 12/10/2020 | 30 | BENGAL ENGINEERING COMPANY | 6.92 | 5.67 | 100 | 0
1500 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme , SM/06871 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Bodrail, JL. No. 167, G.P.-Kanturka of SANKAIL Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte | 2298/MD | 30/09/2020 | 31 | BAKUL CHANDRA HALDAR | 2.82 | 2.51 | 100 | 0
1501 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAILPUR Water Supply Scheme , SM/06871 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Sailpur Water Supply Scheme at Englishbazar Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 3370/MD | 29/08/2023 | 45 | BENGAL ENGINEERING COMPANY | 11.91 | 0 | 0 | 95
1502 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme , SM/06986 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1129/MAAD | 11/11/2020 | 30 | BEE GEE CONSTRUCTION | 34.65 | 32.5 | 95.97 | 1
1503 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme , SM/06986 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Sahajalalpur Water Supply Scheme (Habitation- Sarkar Para, Chowdhury Para) With pipe line at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1866/MAAD | 28/09/2022 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.98 | 0 | 0 | 1
1504 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme , SM/06986 | Retrofitting | SUPPLY & DELIVERY OF DIFFERENT MATERIALS FOR THE DIFFERENT ON-GOING WATER SUPPLY SCHEME UNDER JJM WORKS. |  | 22/09/2023 | 0 | DIGITEK SOLUTIONS | 0.42 | 0 | 0 | 0
1505 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme , SM/06986 | Retrofitting | SUPPLY OF THE FOLLOWING COMPUTER ACCESSORIES WITH SERVICE CHARGE FOR USE IN THE OFFICE OF THE EXECUTIVE ENGINEER, MALDA ARSENIC AREA W/S DIVISION, P.H.E. DTE. |  | 24/08/2023 | 0 | DIGITEK SOLUTIONS | 0.42 | 0 | 0 | 0
1506 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of SAHAZALALPUR Water Supply Scheme , SM/06986 | Retrofitting | SUPPLY OF OFFICE FURNITURE & OTHER STATIONERY ITEM FOR OFFICE USE STATIONERY ARTICLES FOR USE IN THE OFFICE OF THE EXECUTIVE ENGINEER, MALDA ARSENIC AREA W/S DIVISION, P.H.E. DTE. | C082336196084 | 24/08/2023 | 0 | MALDA DISTRICT SERVICE CUM-MARKETING INDUSTRIAL CO-OPERATIVE UNION LTD. | 1.1 | 0 | 0 | 0
1507 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo , SM/09647 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Jalalpur) | 1743/MAAD | 24/11/2021 | 60 | BEE GEE CONSTRUCTION | 56.38 | 0 | 0 | 1
1508 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo , SM/09647 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme (Mouza- Selimpur, Uttar Roypur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1016/MAAD | 12/05/2022 | 60 | NEOGI ENTERPRISE | 53.8 | 0 | 0 | 1
1509 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo , SM/09647 | Retrofitting | Laying of 90 mm dia UPVC Pipe line at Tatipara for installation of FHTC under Bamongram Distribution Zone of Southern Sector under Malda Arsenic Area Water Supply Division, PHE Dte. | 1449/MAAD | 29/07/2022 | 45 | SURAJIT MANDAL | 4.37 | 0 | 0 | 1
1510 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo , SM/09647 | Retrofitting | Laying of 75 mm dia uPVC Pipe line at Jhabri Tola, Tati Para, Colony & Chatra Para for installation of FHTC under Bamongram distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1175/MAAD | 13/06/2022 | 45 | BEE GEE CONSTRUCTION | 4.82 | 0 | 0 | 1
1511 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo , SM/09647 | Retrofitting | Placing of diesel driven Car on hire basis for the official use of the Assistant Engineer-I, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2022 to 31.12.2022) | 2041/MAAD | 29/12/2021 | 365 | SUBRATA SAHA | 4.5 | 0 | 0 | 1
1512 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo , SM/09647 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme (Mouza- Mokshedpur, Sayedpur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 818/MAAD | 28/04/2022 | 60 | BEE GEE CONSTRUCTION | 76.47 | 0 | 0 | 100
1513 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo , SM/09647 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme (Mouza- Natibpur, Purba Chandpur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 819/MAAD | 28/04/2022 | 45 | M/S PRATIMA CONSTRUCTION | 27.81 | 0 | 0 | 1
1514 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo , SM/09647 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Jalalpur) | 1743/MAAD | 24/11/2021 | 30 | BEE GEE CONSTRUCTION | 70 | 0 | 0 | 1
1515 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo , SM/09647 | Retrofitting | Laying of 90 mm dia UPVC Pipe line at Jhabritola, Khariyadoba for installation of FHTC under Bamongram Distribution Zone of Southern Sector under Malda Arsenic Area Water Supply Division, PHE Dte. | 1450/MAAD | 29/07/2022 | 45 | SURAJIT MANDAL | 1.64 | 0 | 0 | 1
1516 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo , SM/09647 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: - Jalalpur, Purba Chandpur, Selimpur, Uttar Raypur for installation of FHTC under Bamangram distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 2034/MAAD | 16/11/2022 | 45 | BEE GEE CONSTRUCTION | 7.28 | 0 | 0 | 1
1517 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo , SM/09647 | Retrofitting | Material Requisition To Resource Division | 1703/MAAD | 21/09/2022 | 0 | Resource Division | 3.08 | 0 | 0 | 0
1518 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bamangram Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Blo , SM/09647 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
1519 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Collection of House Hold Details at prescribed format in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sahajalalpur Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 90/MAAD | 15/01/2021 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 0.26 | 0 | 0 | 1
1520 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Collection of House Hold Details at prescribed format in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dakshin Chandipur,Ramchandrapur Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 91/MAAD | 15/01/2021 | 30 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 0.58 | 0 | 0 | 1
1521 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Jote-Gopal Kagmari Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- JoteGopalkagmari) | 1744/MAAD | 24/11/2021 | 60 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 45.01 | 0 | 0 | 1
1522 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Laying of UPVC Pipe line at Jote Daman & Chabilpara Village for installation of FHTC under Jote-Gopal Kagmari distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 70/MAAD | 21/01/2022 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.74 | 0 | 0 | 1
1523 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Topographical and Hydrograpic Survey for Malda Arsenic Area Water Supply Scheme ( Northern Sector) at Sankaritolaghat, Manikchak under Malda Arsenic Area Water Supply Division, P.H.E. Dte. | 693/MAAD | 12/04/2022 | 20 | INTAKE SURVEY ENGINEERING CONSORTIUM | 2.15 | 0 | 0 | 1
1524 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Collection of House Hold Details at prescribed format in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Nazirpur, Arapur, Phulbaria, Baro Phulbari Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 86/MAAD | 15/01/2021 | 30 | DHRITIPALI | 2.62 | 0 | 0 | 1
1525 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1066/MAAD | 14/10/2020 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 25.23 | 0 | 0 | 1
1526 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-I, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte. | 1339/MAAD | 14/09/2021 | 109 | SUBRATA SAHA | 0.52 | 0 | 0 | 1
1527 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Ramchandrapur Water Supply Scheme (Habitation- Ramnathpur) English Bazar Block under Malda Arsenic Area Water Supply Division, P.H.E Dte. | 2007/MAAD | 28/12/2021 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.38 | 0 | 0 | 1
1528 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: - Jote Gopal Kagmari, Meharapur Habitations: - Krishnapur, Pathanpara, Natunpara for installation of FHTC under Jote Gopal Kagmari distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1460/MAAD | 29/07/2022 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.25 | 0 | 0 | 100
1529 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: - Ail Para, Dharampur, Jot Daman, Jote Gopal Kagmari, Habitations: - Ail Para, Dharampur, Jote Daman, Jote Mansa for installation of FHTC under Jote Gopal Kagmari distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1461/MAAD | 29/07/2022 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.44 | 0 | 0 | 100
1530 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Laying of 110mm dia UPVC Pipeline at Ailpara, Supply of different dia DI Specials & other allied works under JoteGopalKagmari distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 2245/MAAD | 22/12/2022 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.86 | 0 | 0 | 100
1531 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Laying of 160mm dia distribution Pipeline and repairing of Existing Household Tap Connection in connection with Jal Jeevan Mission (JJM) from Jote Daman Academic School to Rathbari Bazar under Jote Gopal Kagmari distribution Zone under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 398/MAAD | 06/03/2023 | 60 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.24 | 0 | 0 | 100
1532 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: - Jote Daman, Habitations: - Chhabil Para for installation of FHTC under Jote Gopal Kagmari distribution Zone of Northern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1462/MAAD | 29/07/2022 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 3.85 | 0 | 0 | 100
1533 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2022 to 31.12.2022) | 2042MAAD | 29/12/2021 | 365 | M/S PARIMAL DAS | 1.73 | 0 | 0 | 0
1534 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Jot Gopalkagmari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Kaliacha , SM/09590 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
1535 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Charianantapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak- , SM/09592 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Charianantapur Water Supply Scheme(Mouza-Charianantapur)at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1735/MAAD | 24/11/2021 | 60 | GOBINDA ENTERPRISE | 55.64 | 0 | 0 | 1
1536 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Charianantapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak- , SM/09592 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Chari Anantapur Water Supply Scheme(Mouza-Baghabanpur) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1736/MAAD | 24/11/2021 | 60 | BANIK BROTHERS | 58.88 | 0 | 0 | 1
1537 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Charianantapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak- , SM/09592 | Retrofitting | Laying of HDPE pipe 20mm dia at Sekhpara, Nakulpara ,Tokkitola & Paglatola under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1475/MAAD | 29/07/2022 | 30 | BANIK BROTHERS | 4.45 | 0 | 0 | 1
1538 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Charianantapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak- , SM/09592 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Charianantapur Water Supply Scheme (Mouza-Kalinagar) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1737/MAAD | 24/11/2021 | 60 | BANIK BROTHERS | 37.54 | 0 | 0 | 1
1539 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Charianantapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak- , SM/09592 | Retrofitting | Laying of HDPE pipe 20mm dia at Charinantapur kamat,Mritanjoy Tola, Subedartola, Bhimtola, Nandalalpur, Suklaltola, Pirpara & Kamarpara under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 617/MAAD | 31/03/2023 | 15 | M/S STAR INDIA CONSTRUCTION | 7.5 | 0 | 0 | 0
1540 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Charianantapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak- , SM/09592 | Retrofitting | Laying of HDPE pipe 20mm dia at Charianantapur under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 995/MAAD | 10/05/2022 | 15 | GOBINDA ENTERPRISE | 4.81 | 0 | 0 | 1
1541 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Charianantapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak- , SM/09592 | Retrofitting | Laying of HDPE pipe 20mm dia at Nandalalpur Das para ,Chaksahedi,Ghoshpara khurshed Mondalpara under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1474/MAAD | 29/07/2022 | 30 | BANIK BROTHERS | 4.76 | 0 | 0 | 1
1542 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Charianantapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak- , SM/09592 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Charianantapur Mouza under command area of Charianantapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte | 2030MAAD | 16/11/2022 | 60 | M/S STAR INDIA CONSTRUCTION | 43.19 | 0 | 0 | 1
1543 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Charianantapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak- , SM/09592 | Retrofitting | Material Requisition To Resource Division | 1787/MAAD | 26/11/2021 | 0 | Resource Division | 52.62 | 0 | 0 | 0
1544 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Charianantapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak- , SM/09592 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
1545 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik , SM/09663 | Retrofitting | Improvement of existing water supply pipe line of Nurpur, Tiarpara, Shamlalpara of Biswambhar Binodpur Distribution zone under Malda Arsenic Area W/S Division, PHE Dte. | 511/MAAD | 10/06/2020 | 0 | KRISHNENDU DUTTA | 15.35 | 0 | 0 | 1
1546 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik , SM/09663 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Nurpur Mouza of Biswambhar Binodpur Piped Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1753/MAAD | 24/11/2021 | 60 | NEOGI ENTERPRISE | 44.84 | 0 | 0 | 1
1547 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik , SM/09663 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kashimnagar Mouza of BiswambharBinodpur Piped Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1759/MAAD | 24/11/2021 | 45 | ABANI BHUSAN GHOSH | 31.2 | 0 | 0 | 100
1548 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik , SM/09663 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Lalbathani, KanshaBinodpur, Niranjanpur Mouza of BiswambharBinodpur Piped Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1760/MAAD | 24/11/2021 | 60 | M/S. JHA CONSTRUCTION | 55.62 | 0 | 0 | 1
1549 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik , SM/09663 | Retrofitting | Repairing of pipe line by Laying of UPVC pipe line at Nurpur Mouza ( Dallu tola, Pyas Tola, Mandal Tola) of Biswambhar Binodpur Distribution zone under Malda Arsenic Area Water Supply Division PHED. | 1403/MAAD | 26/07/2022 | 45 | ABANI BHUSAN GHOSH | 24.12 | 0 | 0 | 1
1550 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik , SM/09663 | Retrofitting | Repairing of pipe line by Laying of UPVC pipe line at Kangso Binodpur, Madhupur, Lalbathani of Biswambhar Binodpur Distribution zone under Malda Arsenic Area Water Supply Division PHED in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) . | 1182/MAAD | 13/06/2022 | 45 | M/S. JHA CONSTRUCTION | 3.38 | 0 | 0 | 1
1551 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik , SM/09663 | Retrofitting | Laying of HDPE pipe 20mm dia at Kashimnagar Mouza under Biswambhar Binodpur water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 854/MAAD | 03/05/2023 | 15 | ABANI BHUSAN GHOSH | 4.58 | 0 | 0 | 100
1552 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik , SM/09663 | Retrofitting | Laying UPVC pipe line and Providing FHTC at Harekrishna Kongar Colony and Kanchantar Binod nagar para under Boro Fulbaria W/S Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | 951/MAAD | 23/05/2023 | 45 | TWO BROTHERS CONSTRUCTION | 4.63 | 0 | 0 | 100
1553 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Biswambhar Binodpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in Manik , SM/09663 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
1554 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) , SM/10234 | Anganwadi | Providing Drinking Water Supply in 10 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 653/MAAD | 01/04/2022 | 120 | M/S DAS CONSTRUCTION | 70.55 | 0 | 0 | 0
1555 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) , SM/10234 | Anganwadi | Formal work order for Providing Drinking Water Supply in 25 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 1056/MAAD | 24/05/2022 | 120 | MOTI RAHAMAN | 175.68 | 0 | 0 | 0
1556 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) , SM/10234 | Anganwadi | Providing Drinking Water Supply in 6 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 654/MAAD | 01/04/2022 | 120 | BANIK BROTHERS | 42.34 | 0 | 0 | 0
1557 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) , SM/10234 | Anganwadi | Supply & delivery of G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for providing Drinking Water Supply in Source Less Schols & ICDS at Kaliachak -III Block under Malda Arsenic Area Water Supply Divisio, P.H.E. Dte. | 2044/MAAD | 16/11/2022 | 15 | DIPAYAN DEY | 24 | 0 | 0 | 100
1558 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) , SM/10234 | Anganwadi | Material Requisition To Resource Division | 329/MAAD | 28/02/2022 | 0 | Resource Division | 64.54 | 0 | 0 | 0
1559 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) , SM/10234 | Anganwadi | Providing Drinking Water Supply in 12 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 652/MAAD | 01/04/2022 | 120 | MERCURY ENGINEERING COMPANY | 84.66 | 0 | 0 | 100
1560 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (65 nos. AWCs in Kaliachak-III Block) , SM/10234 | Anganwadi | Providing Drinking Water Supply in 12 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - III Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 651/MAAD | 01/04/2022 | 359 | HANNAN BUILDERS PVT. LTD. | 84.7 | 0 | 0 | 100
1561 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Acceptance cum formal work order for Excess laying of HDPE (PE-80) pipe for distribution system for the Augmentation of BAMANGRAM & its adjoining mouzas piped water supply at Bamongola Dev. Block in the District Malda under Malda Division, PHE Dte. | 2990/MD | 07/12/2022 | 45 | BINA CONSTRUCTION | 22.62 | 0 | 0 | 0
1562 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Bamangram Water Supply Scheme in Bamongola block under Malda Division, PHE Dte. | 1743/MD | 15/06/2021 | 14 | HORIZEN | 2.86 | 0 | 0 | 1
1563 | MALDAH | Malda Mechanical | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- I of Bamangram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | 413/MLMD | 14/03/2023 | 120 | M/S. SOMA ENTERPRISE | 7.98 | 0 | 0 | 1
1564 | MALDAH | Malda Mechanical | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- II of Bamangram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | 414/MLMD | 14/03/2023 | 120 | M/S. SOMA ENTERPRISE | 7.72 | 0 | 0 | 1
1565 | MALDAH | Malda Mechanical | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. of Bamongram Distribution Zone, Sujapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004335962 | 19/06/2023 | 365 | W.B.S.E.D.C.LTD | 1.3 | 0 | 0 | 100
1566 | MALDAH | Malda Mechanical | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Augmentation of Bamangram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | 2224/MLMD | 18/07/2023 | 120 | SUBHAS CHANDRA KESHORI | 10.85 | 0 | 0 | 0
1567 | MALDAH | Malda Mechanical | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Supply, installation, and commissioning of electro-mechanical components at T/W no. II of Augmentation of Bamongram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | 3685/MLMD | 29/11/2023 | 180 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 7.73 | 0 | 0 | 0
1568 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Acceptance cum formal work order for Sinking of 300mm. Dia. x 200mm. Big dia. Tube Well 125 Mtr. deep by Direct Rotary method using PVC pipe & Gravel Filter including supply of Materials at Bamangram Piped Water Supply Scheme of Bamangola Dev. Block under Malda Division, P.H.E. Dte. in the District of Malda. | 1397/MD | 14/06/2022 | 21 | SNEHASISH GHOSH | 9.71 | 0 | 0 | 100
1569 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Material Requisition To Resource Division | 1104/MD | 17/05/2022 | 0 | Resource Division | 77.51 | 0 | 0 | 0
1570 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Material Requisition To Resource Division | 1248/MD | 22/03/2023 | 0 | Resource Division | 79.81 | 0 | 0 | 0
1571 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Placement of fund against the work for Road restoration work for laying of pipe line for Bamongala Habibpur Road (Portion from 7.00 kmp to 7.50 kmp) for Bamongram Piped Water Supply Scheme under Malda Division, PHE Dte. | BP-2022-23-210 | 16/03/2023 | 0 | EXECUTIVE ENGINEER, MALDA HIGHWAY DIVISION, P.W. (ROADS) DIRECTORATE. | 12.47 | 0 | 0 | 0
1572 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Soil Investigation and design of substructure for ................ at Bamangola Dev. Block in Malda District. |  | 31/01/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
1573 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Soil Investigation and design of substructure for Over Head Reservoirs for Bamangram Piped Water Supply Scheme at Bamaongola Dev. Block in Malda district. | BP-2022-23-188 | 02/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
1574 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Formal work order for the work of Augmentation of BAMANGRAM Piped water supply scheme for the work of Geotechnical Study, construction of 500 Cum RCC OHR, Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Bamongola Dev. Block under Malda Division PH Engg.Dte. In the District of Malda | 1132/MD | 20/05/2022 | 365 | M/S S. DAS & ENTERPRISE | 571.92 | 0 | 0 | 90
1575 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Construction of Boundary Wall at 4th Tube Well Site of Bamongram Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | 3950/MD | 07/08/2024 | 45 | SWASTIK UDYOG | 8.01 | 0 | 0 | 0
1576 | MALDAH | Malda Mechanical | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Supply, installation, and commissioning of electro-mechanical components at T/W no. I of Augmentation of Bamongram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | 3684/MLMD | 29/11/2023 | 180 | BANIK BROTHERS | 8.07 | 0 | 0 | 30
1577 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Laying of Rising Main including Specials and Valves for Bamangram Piped Water Supply Scheme at Bamongola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 706/MD | 09/02/2024 | 45 | M/S GHOSH CONSTRUCTION | 8.85 | 0 | 0 | 100
1578 | MALDAH | Malda Mechanical | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. IV of Augmentation of Bamangram Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008160) | 2225/MLMD | 18/07/2023 | 592 | SUBHAS CHANDRA KESHORI | 12.49 | 0 | 0 | 100
1579 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Augmentation work of Pump Houses and Boundary Walls with New Construction of Boundary wall at Head work site of BAMANGRAM Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2412/MD | 27/05/2025 | 150 | M/S BHARATI CONSTRUCTION | 33.45 | 0 | 0 | 0
1580 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Augmentation of Head work site Pump House of Bamangram Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 294/MD | 29/01/2025 | 60 | M/S EHAN ENTERPRISE | 4.36 | 0 | 0 | 0
1581 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Laying of dedicated /Parallel pipe line for better functionality and providing balance FHTC of BAMANGRAM Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 3629/MD | 24/07/2025 | 60 | M/S MOON LIGHT CONSTRUCTION & CO. | 87.27 | 0 | 0 | 0
1582 | MALDAH | Malda Division | Augmentation of Bamongram piped water supply scheme. , SM/10138 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with 2nd Tube Well Site of Bamangram Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | 2673/MD | 13/07/2023 | 45 | DEB CONSTRUCTION | 4.17 | 0 | 0 | 100
1583 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Anganwadi(103 nos) Centres (AWCs) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10380 | Anganwadi | Material Requisition To Resource Division | 717/MD | 25/03/2022 | 0 | Resource Division | 67.41 | 0 | 0 | 0
1584 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Anganwadi(103 nos) Centres (AWCs) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10380 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Bhakri & Kshempur GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | 453/MD | 03/02/2023 | 75 | MOTI RAHAMAN | 168.68 | 0 | 0 | 25
1585 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Anganwadi(103 nos) Centres (AWCs) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10380 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Gour Handa and Dhangara Bishanpur GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | 826/MD | 21/02/2023 | 75 | M/S S. S. ENTERPRISE | 191.7 | 0 | 0 | 70
1586 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Anganwadi(103 nos) Centres (AWCs) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10380 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Jalalpur & Malatipur GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | 371/MD | 16/01/2024 | 75 | M/S S. DAS & ENTERPRISE | 191.7 | 0 | 0 | 50
1587 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Anganwadi(103 nos) Centres (AWCs) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10380 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Chandrapara GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | 552/MD | 09/02/2023 | 75 | MILLENNIUM ENTERPRISR | 107.29 | 0 | 0 | 97
1588 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Anganwadi(103 nos) Centres (AWCs) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10380 | Anganwadi | Material Requisition To Resource Division | 424/MD | 19/01/2024 | 0 | Resource Division | 98.18 | 0 | 0 | 0
1589 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant (71 nos.) at Schools of Ratua-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10382 | School | Material Requisition To Resource Division | 720/MD | 25/03/2022 | 0 | Resource Division | 28.67 | 0 | 0 | 0
1590 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant (71 nos.) at Schools of Ratua-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10382 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Pukhuria & Sambalpur GP of Ratua-II Dev. Block under Malda Division, PHE Dte. | 88/MD | 17/01/2023 | 75 | M/S TAPAS KUMAR CHAKRABORTY | 109.21 | 0 | 0 | 100
1591 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant (71 nos.) at Schools of Ratua-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10382 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Pirganj, Paranpur and Araidanga GP of Ratua-II Dev. Block under Malda Division, PHE Dte. | 39/MD | 16/01/2023 | 75 | DEBAPRIYA SAHA | 164.05 | 0 | 0 | 90
1592 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant (71 nos.) at Schools of Ratua-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10382 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Sripur-I, Sripur-II & Maharajpur GP of Ratua-II Dev. Block under Malda Division, PHE Dte. | 1643/MD | 13/04/2023 | 569 | USHA ENTERPRISE | 184.54 | 0 | 0 | 31
1593 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 75 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10207 | School | Supply G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for Schools of English Bazar Block under Malda Arsenic Area W/S Division, PHE Dte. | 1031/MAAD | 12/05/2022 | 10 | M/S PARIMAL DAS | 5 | 0 | 0 | 0
1594 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 75 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10207 | School | Continuation work order for Supply G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for Schools of English Bazar Block under Malda Arsenic Area Water Supply Division, P.H.E. Dte. | 1618/MAAD | 02/09/2022 | 10 | M/S PARIMAL DAS | 4.66 | 0 | 0 | 0
1595 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 75 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10207 | School | Providing Drinking Water Supply in 7 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 645/MAAD | 01/04/2022 | 120 | BANIK BROTHERS | 44.12 | 0 | 0 | 0
1596 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 75 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10207 | School | Material Requisition To Resource Division | 334/MAAD | 28/02/2022 | 0 | Resource Division | 82.76 | 0 | 0 | 0
1597 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 75 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10207 | School | Formal work order for Providing Drinking Water Supply in 23 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 790/MAAD | 26/04/2022 | 120 | HANNAN BUILDERS PVT. LTD. | 145.01 | 0 | 0 | 100
1598 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 75 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10207 | School | Providing Drinking Water Supply in 15 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 644/MAAD | 01/04/2022 | 120 | NEOGI ENTERPRISE | 94.53 | 0 | 0 | 85
1599 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 75 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10207 | School | Formal Work order for Providing Drinking Water Supply in 30 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 782/MAAD | 26/04/2022 | 120 | NEOGI ENTERPRISE | 189.12 | 0 | 0 | 0
1600 | MALDAH | Malda Division | INSTALLATION OF 18 nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT SCHOOLS OF OLD MALDA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10241 | School | Material Requisition To Resource Division | 530/MD | 03/03/2022 | 0 | Resource Division | 24.82 | 0 | 0 | 0
1601 | MALDAH | Malda Division | INSTALLATION OF 18 nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT SCHOOLS OF OLD MALDA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10241 | School | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) at different Schools of Old Malda Dev. Block, Malda under Malda Division, PHE Dte. | 830/MD | 06/04/2022 | 90 | NEOGI ENTERPRISE | 88.91 | 0 | 0 | 100
1602 | MALDAH | Malda Division | INSTALLATION OF 129 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES OF GP-BAMONGOLA,JAGDALA & PAKUAHAT IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10242 | Anganwadi | Material Requisition To Resource Division | 524/MD | 03/03/2022 | 0 | Resource Division | 79.15 | 0 | 0 | 0
1603 | MALDAH | Malda Division | INSTALLATION OF 129 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES OF GP-BAMONGOLA,JAGDALA & PAKUAHAT IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10242 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Jogdala GP of Bamangola Dev. Block under Malda Division, PHE Dte. | 117/MD | 18/01/2023 | 75 | MOTI RAHAMAN | 173.18 | 0 | 0 | 90
1604 | MALDAH | Malda Division | INSTALLATION OF 129 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES OF GP-BAMONGOLA,JAGDALA & PAKUAHAT IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10242 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Bamangola GP of Bamangola Dev. Block under Malda Division, PHE Dte. | 3197/MD | 27/12/2022 | 75 | MODERN CONSTRUCTION | 174.38 | 0 | 0 | 100
1605 | MALDAH | Malda Division | INSTALLATION OF 129 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES OF GP-BAMONGOLA,JAGDALA & PAKUAHAT IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10242 | Anganwadi | Installation of Solar Powered Standalone Community Water Purification Plant (CWPP) for AWC's at different places of Bamongola Dev. Block under Malda Division, PHE Dte. (Quantity: 14 Nos.) | 2953/MD | 19/06/2025 | 150 | USHA ENTERPRISE | 95.65 | 0 | 0 | 0
1606 | MALDAH | Malda Division | INSTALLATION OF 129 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES OF GP-BAMONGOLA,JAGDALA & PAKUAHAT IN BAMONGOLA DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10242 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Pakuahat GP of Bamongola Dev. Block under Malda Division, PHE Dte. | 95/MD | 17/01/2023 | 75 | J. S. CONSTRUCTION | 199.27 | 0 | 0 | 90
1607 | MALDAH | Malda Division | Installation of stand alone community purification plant (108 nos.) at Anganwadi centres(AWCs) of Chanchal-I dev block ,Malda under Malda Division,PHE Dte. , SM/10379 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Bhagabanpur-II & Mahanandapur GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | 827/MD | 21/02/2023 | 75 | MILLENNIUM ENTERPRISR | 93.38 | 0 | 0 | 0
1608 | MALDAH | Malda Division | Installation of stand alone community purification plant (108 nos.) at Anganwadi centres(AWCs) of Chanchal-I dev block ,Malda under Malda Division,PHE Dte. , SM/10379 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Alihanda & Mokdumpur GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | 601/MD | 10/02/2023 | 75 | M/S TAPAS KUMAR CHAKRABORTY | 124.45 | 0 | 0 | 100
1609 | MALDAH | Malda Division | Installation of stand alone community purification plant (108 nos.) at Anganwadi centres(AWCs) of Chanchal-I dev block ,Malda under Malda Division,PHE Dte. , SM/10379 | Anganwadi | Material Requisition To Resource Division | 718/MD | 25/03/2022 | 0 | Resource Division | 65.14 | 0 | 0 | 0
1610 | MALDAH | Malda Division | Installation of stand alone community purification plant (108 nos.) at Anganwadi centres(AWCs) of Chanchal-I dev block ,Malda under Malda Division,PHE Dte. , SM/10379 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Chanchal & Matiharpur GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | 480/MD | 07/02/2023 | 75 | DUTTA ENTERPRISE | 186.76 | 0 | 0 | 90
1611 | MALDAH | Malda Division | Installation of stand alone community purification plant (108 nos.) at Anganwadi centres(AWCs) of Chanchal-I dev block ,Malda under Malda Division,PHE Dte. , SM/10379 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Kaligram & Khorba GP of Chanchal-I Dev. Block under Malda Division, PHE Dte. | 93/MD | 17/01/2023 | 75 | MAMATA USHA ENTERPRISE | 118.39 | 0 | 0 | 99
1612 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(94 nos) of Habibpur Dev. Block, Malda under Malda Division, PHE Dte. , SM/10386 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Aiho, Rishipur & Srirampur GP of Habibpur Dev. Block under Malda Division, PHE Dte. | 3194/MD | 27/12/2022 | 75 | M/S GOUTAM CHAKRABORTY | 113.29 | 0 | 0 | 0
1613 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(94 nos) of Habibpur Dev. Block, Malda under Malda Division, PHE Dte. , SM/10386 | School | Material Requisition To Resource Division | 724/MD | 25/03/2022 | 0 | Resource Division | 61.91 | 0 | 0 | 0
1614 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(94 nos) of Habibpur Dev. Block, Malda under Malda Division, PHE Dte. , SM/10386 | School |  |  | 24/03/2023 | 0 | M/S GOUTAM CHAKRABORTY | 67.74 | 0 | 0 | 0
1615 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(94 nos) of Habibpur Dev. Block, Malda under Malda Division, PHE Dte. , SM/10386 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for School at Mangalpura, Dhumpur & Baidyapur GP of Habibpur Dev. Block under Malda Division, PHE Dte. | 556/MD | 09/02/2023 | 75 | MILLENNIUM ENTERPRISR | 113.21 | 0 | 0 | 45
1616 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(94 nos) of Habibpur Dev. Block, Malda under Malda Division, PHE Dte. , SM/10386 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Kanturka & Jajoil GP of Habibpur Dev. Block under Malda Division, PHE Dte. | 815/MD | 20/02/2023 | 75 | GIYASUDDIN SEKH | 118.65 | 0 | 0 | 100
1617 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(94 nos) of Habibpur Dev. Block, Malda under Malda Division, PHE Dte. , SM/10386 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Bulbulchandi, Habibpur & Aktail GP of Habibpur Dev. Block under Malda Division, PHE Dte. | 197/MD | 19/01/2023 | 75 | MILLENNIUM ENTERPRISR | 134.77 | 0 | 0 | 100
1618 | MALDAH | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte , SM/12304 | New | Material Requisition To Resource Division | 1809/MD | 27/04/2023 | 0 | Resource Division | 14.46 | 0 | 0 | 0
1619 | MALDAH | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte , SM/12304 | New | Laying of Distribution of UPVC Pipeline of KANTHALANPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 2328/MD | 08/06/2023 | 60 | UTTAM KUMAR GHOSH | 64.73 | 0 | 0 | 80
1620 | MALDAH | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte , SM/12304 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kanthalanpur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 5790/MD | 21/11/2024 | 45 | DHRITIPALI | 60.57 | 0 | 0 | 0
1621 | MALDAH | Malda Mechanical | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte , SM/12304 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of KANTHALANPUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-426 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 7.65 | 0 | 0 | 0
1622 | MALDAH | Malda Mechanical | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte , SM/12304 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of KANTHALANPUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-425 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.24 | 0 | 0 | 0
1623 | MALDAH | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte , SM/12304 | New | Formal work order for the work of Implementation of KANTHALANPUR Piped Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1849/MD | 03/05/2023 | 820 | SOVON KUMAR DAS | 322.9 | 0 | 0 | 100
1624 | MALDAH | Malda Mechanical | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte , SM/12304 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Kanthalanpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013454) | 2389/MLMD | 28/07/2023 | 898 | HANNAN BUILDERS PVT. LTD. | 30 | 0 | 0 | 19
1625 | MALDAH | Malda Division | KANTHALANPUR PWSS at Habibpur in Malda Division P.H.E.Dte , SM/12304 | New | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works of Oltara, Mianagar, Kadirpur, Bhabuk, Kanthalanpur PWSS under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 643/MD | 19/02/2025 | 7 | DHRITIPALI | 0.88 | 0 | 0 | 0
1626 | MALDAH | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well ( 135 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at SAIYADPUR Water Supply Scheme of Old Malda Block .under Malda Division, PHE Dte. in the District of Malda. | 2303/MD | 28/09/2022 | 30 | DUTTA ENTERPRISE | 9 | 0 | 0 | 1
1627 | MALDAH | Malda Mechanical | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III & IV of Source Augmentation of Saiyadpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012800) | 512/MLMD | 20/03/2023 | 120 | DEVI ENTERPRISE... | 21.57 | 0 | 0 | 0
1628 | MALDAH | Malda Mechanical | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No.III of Saiyadpur PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004243242 | 27/04/2023 | 90 | W.B.S.E.D.C.LTD | 4.41 | 0 | 0 | 0
1629 | MALDAH | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 132.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at SAIYADPUR Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | 1175/MD | 20/03/2023 | 30 | A. D. D. ASSOCIATES | 9.15 | 0 | 0 | 100
1630 | MALDAH | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Saiyadpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | 1207/MD | 21/03/2023 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 4.15 | 0 | 0 | 100
1631 | MALDAH | Malda Mechanical | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Claim for purchase of fuel for hiring of inspection for different site visit (diesel driven for official) use for Under Mechanical Division, P.H.E. Dte. | 917./MLMD | 12/09/2022 | 61 | MAA LAXMI FUEL STATION | 0.51 | 0 | 0 | 100
1632 | MALDAH | Malda Mechanical | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Claim for purchase of fuel for hiring of inspection for different site visit (diesel driven for official) use for AE-I, Under Mechanical Division, P.H.E. Dte. | 1145./MLMD | 26/06/2023 | 30 | RAMCHANDRA BASAK | 0.26 | 0 | 0 | 100
1633 | MALDAH | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Material Requisition To Resource Division | 2410/MD | 17/10/2022 | 0 | Resource Division | 10.98 | 0 | 0 | 0
1634 | MALDAH | Malda Mechanical | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | NEW SERVICE CONNECTION FOR TE NO. IV OF SAIYEDPUR W S SCHEME | BP-2023-24-95 | 13/07/2023 | 0 | W.B.S.E.D.C.LTD | 3.18 | 0 | 0 | 0
1635 | MALDAH | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C pipe line by different dia UPVC pipe for SAIYADPUR Piped Water Supply Scheme (Dhalsana JL-48, Horkhorka JL-49, & Saiyadpur ) under Old Malda Block in the District of Malda under Malda Division, PHE Dte. | 2603/MD | 10/11/2022 | 45 | A. K. CONSTRUCTION | 46.61 | 0 | 0 | 80
1636 | MALDAH | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of SAIYADPUR Water Supply Scheme of Old Malda Block .under Malda Division, PHE Dte. in the District of Malda. | 2549/MD | 03/11/2022 | 45 | J. M. CONSTRUCTION | 6.69 | 0 | 0 | 90
1637 | MALDAH | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for SAIYADPUR Piped Water Supply scheme ( Kutubpur JL-79, Basudevpur JL-80,Ijjatpur ,JL-81 & Minapara JL-92 ) under Old Malda Block in the District of Malda under Malda Division, PHE Dte. | 1638/MD | 12/04/2023 | 45 | SHREE BISHNU CONSTRUCTION | 56.31 | 0 | 0 | 90
1638 | MALDAH | Malda Mechanical | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Installation, Commissioning and trail operation of electro-mechanical components at T/W no-III & IV Source Augmentation of Saiyadpur W/S Scheme in the district of Malda under Malda Mechanical Division, P.H.Engineering Directorate. | 4756/MLMD | 28/12/2023 | 30 | PABITRA MANDAL | 3.01 | 0 | 0 | 49
1639 | MALDAH | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Construction of Boundary Wall and pathway at 3rd Tube well Site of SAIYADPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | 287/MD | 11/01/2024 | 45 | KANAN CONSTRUCTION ENTERPRISE | 6.32 | 0 | 0 | 0
1640 | MALDAH | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Laying of additional pipeline for retrofitting and Installation of Functional House Connection of Saiyadpur Piped Water Supply Scheme at Old Malda Block under Malda Division PHE. Dte. | 5919/MD | 26/11/2024 | 45 | SHREE BISHNU CONSTRUCTION | 88.25 | 0 | 0 | 0
1641 | MALDAH | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Extension of pipe line and replacing of damage A.C./uPVC pipe line by different dia. UPVC pipe for SAIYEDPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | 884/MD | 27/02/2024 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 12.59 | 0 | 0 | 100
1642 | MALDAH | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Material Requisition To Resource Division | 777/MD | 20/02/2024 | 0 | Resource Division | 3.08 | 0 | 0 | 0
1643 | MALDAH | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Augmentation work of Boundary wall, Pump House, Blower Room, RCC Over Head Reservior and Construction Pathway & Approch Road at Head Work Site of SAIYADPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | 2376/MD | 26/05/2025 | 75 | M/S T. K. CONSTRUCTION | 21.59 | 0 | 0 | 0
1644 | MALDAH | Malda Division | Source Augmentation of Saiyadpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12311 | Augmentation | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 2nd Tube Well Site of SAIYADPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | 2288/MD | 21/05/2025 | 75 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 7.42 | 0 | 0 | 0
1645 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11590 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Tulshihatta Zone-I Piped Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. | 654/MD | 22/03/2022 | 15 | M/S SOBHA & CO. | 3.42 | 0 | 0 | 1
1646 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11590 | New | Material Requisition To Resource Division | 1874/MD | 16/08/2022 | 0 | Resource Division | 18.81 | 0 | 0 | 0
1647 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11590 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 17.88 | 0 | 0 | 0
1648 | MALDAH | Malda Mechanical | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11590 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I, II of Tulshihata (zone-I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011266) | 2773/MLMD | 14/08/2023 | 1032 | SUDIP DEY | 25.6 | 0 | 0 | 85
1649 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11590 | New | Material Requisition To Resource Division | 33/MD | 04/01/2024 | 0 | Resource Division | 12.32 | 0 | 0 | 0
1650 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11590 | New | Material Requisition To Resource Division | 3921/MD | 06/08/2024 | 0 | Resource Division | 4.31 | 0 | 0 | 0
1651 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11590 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Tulshihatta Zone-I Water Supply Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 3372/MD | 29/08/2023 | 278 | M/S SABANA CONSTRUCTION | 80.46 | 0 | 0 | 100
1652 | MALDAH | Malda Mechanical | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11590 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 2780/MLMD | 27/08/2024 | 61 | SUBRATA SAHA | 0.78 | 0 | 0 | 100
1653 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11590 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Tulshihata Zone-I Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 60 | 08/01/2025 | 311 | M/S BABLU ENTERPRISE | 30.36 | 0 | 0 | 30
1654 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11590 | New | Erection of Property board related to Jal Jeevan Mission works of Bbairat, Paro, Mabarakpur, Sri Chandrapur, Tulshihatta Zone-I & II, Kismat Barol PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 647/MD | 19/02/2025 | 7 | RAHANUL ALAM | 0.95 | 0 | 0 | 100
1655 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11590 | New | Formal work order for the work of Laying Distribution pipe line for TULSHIHATA (ZONE-I) & its adjoining mouzas Piped Water Supply at Harishchandrapur-I Block in the District Malda under Malda Division, PHE Dte. (2nd Call). | 2129/MD | 16/09/2022 | 472 | BANIK BROTHERS | 168.65 | 0 | 0 | 100
1656 | MALDAH | Malda Division | Ground Water Based for Tulshihatta Zone-I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11590 | New | Laying of additional at Tulshihatta Zone-I Water Supply Scheme under Harishchandrtapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 76 | 13/01/2025 | 251 | M/S GHOSH CONSTRUCTION | 12.42 | 0 | 0 | 100
1657 | MALDAH | Malda Division | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Material Requisition To Resource Division | 2755/MD | 22/11/2022 | 0 | Resource Division | 53 | 0 | 0 | 0
1658 | MALDAH | Malda Division | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 150 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of CHOUPALDANGA Water Supply Scheme at Harishchandrapur I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2348/MD | 29/09/2022 | 30 | MECHANO TRADING CO. | 9.65 | 0 | 0 | 100
1659 | MALDAH | Malda Mechanical | Choupaldanga pipe water Supply Scheme , SM/12076 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Choupaldanga PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004302721 | 21/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.2 | 0 | 0 | 100
1660 | MALDAH | Malda Division | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Bill for reimbursement of cost of Diesel and Mobil in respect of hired Vehicle Car No. WB61A/3084, For the month of June and July 2023. | BP-2023-24-192 | 07/09/2023 | 0 | SHYAMAL KUMAR MAITRA | 0.36 | 0 | 0 | 0
1661 | MALDAH | Malda Division | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of CHOUPALDANGA & its adjoining mouza Water Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | 2194/MD | 22/09/2022 | 45 | M/S EHAN ENTERPRISE | 6.67 | 0 | 0 | 95
1662 | MALDAH | Malda Division | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (2 Nos.) at CHOUPALDANGA Water Supply Scheme under Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1139/MD | 20/03/2023 | 30 | DUTTA ENTERPRISE | 20.31 | 0 | 0 | 95
1663 | MALDAH | Malda Division | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Material Requisition To Resource Division | 91/MD | 05/01/2024 | 0 | Resource Division | 10.44 | 0 | 0 | 0
1664 | MALDAH | Malda Mechanical | Choupaldanga pipe water Supply Scheme , SM/12076 | New | New service connection at CHOUPALDANGA Pwss pH NO II Under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) | BP-2023-24-661 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.87 | 0 | 0 | 0
1665 | MALDAH | Malda Mechanical | Choupaldanga pipe water Supply Scheme , SM/12076 | New | New service connection at CHOUPALDANGA Pwss pH NO III Under EE/MLMD PHE DTE DIST. Malda.( kushida c c c) | BP-2023-24-662 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.06 | 0 | 0 | 0
1666 | MALDAH | Malda Division | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Formal work order for the work of Laying of Distribution pipe line of CHOUPALDANGA and its adjoining mouzas Pipe Water Supply Scheme at Harishchandrapur-I Block in the District of Malda under Malda Division P.H.E. Dte. | 2384/MD | 13/10/2022 | 811 | NEOGI ENTERPRISE | 275.7 | 0 | 0 | 100
1667 | MALDAH | Malda Division | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Formal work order for the work of Construction of 500 M3 Capacity OHR with Soil Investigation and FHTC of CHOUPALDANGA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2007/MD | 17/05/2023 | 865 | NIRMAN | 243.67 | 0 | 0 | 65
1668 | MALDAH | Malda Mechanical | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Choupaldanga Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011833) | 2314/MLMD | 26/07/2023 | 916 | COMBINE ENTERPRISE | 38.6 | 0 | 0 | 85
1669 | MALDAH | Malda Division | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at CHOUPALDANGA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 579/MD | 02/02/2024 | 45 | GULJAR CONSTRUCTION | 4.19 | 0 | 0 | 100
1670 | MALDAH | Malda Division | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at CHOUPALDANGA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 580/MD | 02/02/2024 | 45 | GULJAR CONSTRUCTION | 4.19 | 0 | 0 | 100
1671 | MALDAH | Malda Division | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Construction of Boundary Wall at Head Work site of Choupaldanga Water Supply Scheme under Harischandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | 2684/MD | 04/06/2025 | 150 | GIRIDHARI CONSTRUCTION | 25.91 | 0 | 0 | 0
1672 | MALDAH | Malda Division | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Construction of Boundary Wall at 2nd Tubewell site of Choupaldanga Water Supply Scheme under Harischandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. (2nd Call) | 2685/MD | 04/06/2025 | 211 | HARUN ALL RASHID & BROTHERS | 17.12 | 0 | 0 | 0
1673 | MALDAH | Malda Division | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Choupaldanga Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 1911/MD | 14/05/2025 | 60 | NEOGI ENTERPRISE | 104.36 | 0 | 0 | 0
1674 | MALDAH | Malda Division | Choupaldanga pipe water Supply Scheme , SM/12076 | New | Laying of Rising Main including Specials and Valves for CHOUPALDANGA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 511/MD | 29/01/2024 | 383 | AHONA ENTERPRISE | 14.91 | 0 | 0 | 99
1675 | MALDAH | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED , SM/12709 | New | Continuation work order for Route survey & design for praparation of DPR of Humidpur, Sukhdebpur & Bakhrabad Pipe Water Supply Scheme at Kaliachak-II & Kaliachak-III Development Block under Malda Arsenic Area W/S Division, Phe Dte. | 1671/MAAD | 12/09/2022 | 10 | FUTURE | 0.99 | 0 | 0 | 1
1676 | MALDAH | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED , SM/12709 | New | Route survey & design for praparation of DPR of Humidpur, Sukhdebpur & Bakhrabad Pipe Water Supply Scheme at Kaliachak-II & Kaliachak-III Development Block under Malda Arsenic Area W/S Division, Phe Dte. | 1667/MAAD | 08/09/2022 | 10 | FUTURE | 0.99 | 0 | 0 | 1
1677 | MALDAH | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED , SM/12709 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Hamidpur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | 661/MAAD | 06/04/2023 | 45 | JOY GURU ENTERPRISE | 14.6 | 0 | 0 | 100
1678 | MALDAH | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED , SM/12709 | New | Material Requisition To Resource Division | 624/MAAD | 05/04/2023 | 0 | Resource Division | 10.54 | 0 | 0 | 0
1679 | MALDAH | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED , SM/12709 | New | Laying of Distribution System at Paschim Tofi, Purba Tofi, Chumki Tola for Hamidpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. (2nd call) | 677/MAAD | 12/04/2023 | 90 | MD. TALEB ALI | 66.48 | 0 | 0 | 90
1680 | MALDAH | Malda Mechanical | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED , SM/12709 | New | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Humidpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte | 3390/MLMD | 31/10/2023 | 789 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 62.15 | 0 | 0 | 30
1681 | MALDAH | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED , SM/12709 | New | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Hamidpur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1697/MAAD | 19/11/2024 | 60 | M/S MANDAL & SONS | 64 | 0 | 0 | 0
1682 | MALDAH | Malda Mechanical | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED , SM/12709 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Executive Engineer under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 1650/MLMD | 25/06/2024 | 62 | NITAI PANDEY | 0.78 | 0 | 0 | 0
1683 | MALDAH | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED , SM/12709 | New | Laying of Distribution System at Nutun Tofi, Jalimtola, Sripur Colony, Sripur, Bakhrabaj ,for Hamidpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 836/MAAD | 02/05/2023 | 303 | M/S MOON LIGHT CONSTRUCTION & CO. | 46.85 | 0 | 0 | 100
1684 | MALDAH | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED , SM/12709 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Hamidpur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2ND Call) | 1411/MAAD | 20/07/2023 | 712 | WIST WATER SOLUTIONS PRIVATE LIMITED | 156.58 | 0 | 0 | 15
1685 | MALDAH | Malda Ars Area W/S Division | Hamidpur Mouza Piped Water Supply Scheme of Kaliachak-II Block under Malda Arsenic Area water Supply Division, PHED , SM/12709 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Hamidpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 1409/MAAD | 20/07/2023 | 256 | M. I. CONSTRUCTION | 4.96 | 0 | 0 | 100
1686 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Satangapara and Malatipur Zone Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11915 | Retrofitting | Laying of 110 mm dia & 90 mm dia UPVC pipe, Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission (JJM& Jal Swapna) at Kathalbari village under Sultanganj pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | 1258/MAAD | 24/06/2024 | 281 | SAHA CONSTRUCTION | 34.89 | 0 | 0 | 0
1687 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Satangapara and Malatipur Zone Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11915 | Retrofitting | Laying of 90 mm dia UPVC pipe & Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission(JJM& Jal Swapna) at Lalutola,Khublaltola & Gosaitola village under Charianantapur pipe water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte | 1257/MAAD | 24/06/2024 | 30 | MAHA MAYA CONSTRUCTION | 6.8 | 0 | 0 | 0
1688 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Satangapara and Malatipur Zone Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11915 | Retrofitting | Laying of UPVC pipe 160mm dia & DI pipe 250 mm dia From Dariapur WTP (Back wash OHR) to 16 mile & others Allied works of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | 1711/MAAD | 20/09/2023 | 90 | S. R. CONSTRUCTION | 22.28 | 0 | 0 | 100
1689 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Satangapara and Malatipur Zone Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11915 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
1690 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE , SM/11916 | Retrofitting | Laying of HDPE pipe 20mm dia at Akandabaria,Chakdomai & Umakantatola under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 915/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.71 | 0 | 0 | 1
1691 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE , SM/11916 | Retrofitting | Laying of HDPE pipe 20mm dia at Kalinagar, Malatipur & Zolatuli under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 916/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.67 | 0 | 0 | 1
1692 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE , SM/11916 | Retrofitting | Laying of HDPE pipe 20mm dia at Saharatola, Golabari & Bhagabanpur under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dt | 917/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.74 | 0 | 0 | 1
1693 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE , SM/11916 | Retrofitting | Laying of HDPE pipe 20mm dia at Chakkupara, Nandalalpur & Agnutola under Charianantapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 918/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.81 | 0 | 0 | 1
1694 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE , SM/11916 | Retrofitting | Laying of UVC pipe 200mm,90 mm dia at Kumvira to Nurnagar,Godhantola to munnatola & others Allied works to faciliate of house connection at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 622/MAAD | 05/04/2023 | 60 | MI CONSTRUCTION | 22.74 | 0 | 0 | 0
1695 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE , SM/11916 | Retrofitting | Laying of HDPE pipe 20mm dia at Sardah, Naldahari, Chaitanna Tola & Nowda under Bholaichak water supply Zone of Southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 853/MAAD | 03/05/2023 | 15 | BANIK BROTHERS | 8.37 | 0 | 0 | 100
1696 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE , SM/11916 | Retrofitting | Repair & renovation of CI /DI Clear water main (Group-I) 750mm,700 mm,500 mm,450 mm,300 mm,250 mm) pipeline at diferrence places (Kaliachak band,Kaliachak PWD,Kaliachak Suraj Grill factory,jalalpur,Majompur bridge &Bholaichak) under Southern Sector under Malda Arsenic Area W/S Divn.PHE. Dte. | 855/MAAD | 03/05/2023 | 30 | BANIK BROTHERS | 3.33 | 0 | 0 | 100
1697 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE , SM/11916 | Retrofitting | Laying of UPVC pipe 225mm,90 mm dia at Mohanpur ,Neoginagar & others Allied works at Kumvira W/S scheme at Kaliachak -III Block under Malda Arsenic Area water supply Divn PHE Dte. | 948/MAAD | 23/05/2023 | 45 | M/S SUBHASIS BHADURI | 8.83 | 0 | 0 | 100
1698 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE , SM/11916 | Retrofitting | Laying of UPVC pipe 225mm dia at Neogi nagar & others Allied works at Kumvira W/S scheme at Kaliachak-III Block under Malda Arsenic Area water supply Divn PHE Dte. | 949/MAAD | 23/05/2023 | 45 | SURAJIT MANDAL | 8.61 | 0 | 0 | 100
1699 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE , SM/11916 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) under command area of Kumbhira to Nurnagar at Kumbhira Piped Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 886/MAAD | 11/05/2023 | 150 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 38.78 | 0 | 0 | 40
1700 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE , SM/11916 | Retrofitting | Laying of UPVC pipe line & Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at Khuplaltola, Gosaitola under command area of Charianantapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1892/MAAD | 12/10/2023 | 30 | ABHIJIT CONSTRUCTION | 9.28 | 0 | 0 | 100
1701 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE , SM/11916 | Retrofitting | Laying of 90 mm dia UPVC pipe & Providing Functional House Hold Tap Connection (FHTC) & others Allied works in connection with Jal Jeevan Mission (JJM& Jal Swapna) at Satangapara (Kashipara) & Sammohammadtola under Dariapur water supply scheme of Kaliachak-III Dev. Block under Malda Arsenic Area W/S Division PHE Dte. | 3078/MAAD | 14/12/2023 | 60 | M/S EHAN ENTERPRISE | 9.86 | 0 | 0 | 100
1702 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jagannathpur, Baishnabnagar, Bholaichak, Charianantapur, Krishnapur and Kumbhira Zone water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE , SM/11916 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
1703 | MALDAH | Central Drilling | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12323 | Augmentation | Resistivity survey for Sankail PWSS, Basara PWSS and Pannapur PWSS at Habibipur & Bamongola block under Malda district, CMSD-II (D), CDD, PHE Dte. | 135/CMSD-II(D) | 24/05/2023 | 15 | S B S ENTERPRISE | 0.82 | 0 | 0 | 100
1704 | MALDAH | Malda Mechanical | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12323 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Sankail Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014344) | 2395/MLMD | 28/07/2023 | 737 | SUDIP DEY | 11.1 | 0 | 0 | 30
1705 | MALDAH | Malda Division | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12323 | Augmentation | Construction of Boundary Wall of Sankail Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 4998/MD | 27/09/2024 | 45 | BALAJI ENGINEERS CO OPERATIVE SOCIETY LT | 10.15 | 0 | 0 | 0
1706 | MALDAH | Malda Division | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12323 | Augmentation | Sinking of ( 250 mm Dia. X 200 mm Dia.) Tubewell No.-3 (130 M deep) by D.R Rig. Method using P.V.C. pipe & Gravel Filter including Supply of materials at SANKAIL Water Supply Scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | 381/MD | 17/01/2024 | 45 | A. L. ENGINEERING SOLUTION | 11.77 | 0 | 0 | 100
1707 | MALDAH | Malda Division | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12323 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for SANKAIL Piped Water Supply Scheme of Habibpur Block in the District of Malda under Malda Division, PHE Dte. | 2606/MD | 10/11/2022 | 1087 | M/S KUNDU CONSTRUCTION | 71.98 | 0 | 0 | 0
1708 | MALDAH | Malda Division | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12323 | Augmentation | Replacement of (200 mm Dia. All through) Tubewell No:-1 (130 m deep) at Headwork Site by D.R Rig Method using P.V.C. pipe & Filter including Supply of materials at SANKAIL water supply scheme of Habibpur Block under Malda Division, P.H.E Dte in the District of Malda. | 350/MD | 30/01/2025 | 30 | A. L. ENGINEERING SOLUTION | 9.06 | 0 | 0 | 0
1709 | MALDAH | Malda Division | Source Augmentation of Sankail Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12323 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of SANKAIL Water Supply Scheme of Habibpur Block. under Malda Division, PHE Dte. in the District of Malda. | 2800/MD | 24/11/2022 | 679 | M/S N. N. ENTERPRISE | 6.68 | 0 | 0 | 100
1710 | MALDAH | Malda Division | MALIOR PWSS , SM/12192 | New | Material Requisition To Resource Division | 3050/MD | 12/12/2022 | 0 | Resource Division | 25.1 | 0 | 0 | 0
1711 | MALDAH | Malda Division | MALIOR PWSS , SM/12192 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of MALIOR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | 2700/MD | 17/11/2022 | 30 | SAUDAGAR (INDIA) | 9.2 | 0 | 0 | 100
1712 | MALDAH | Malda Division | MALIOR PWSS , SM/12192 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at MALIOR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 922/MD | 27/02/2023 | 30 | MERCURY ENGINEERING COMPANY | 10.13 | 0 | 0 | 100
1713 | MALDAH | Malda Mechanical | MALIOR PWSS , SM/12192 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.II of Malior PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004390586 | 15/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.33 | 0 | 0 | 100
1714 | MALDAH | Malda Mechanical | MALIOR PWSS , SM/12192 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No.I of Malior PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004390575 | 15/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.14 | 0 | 0 | 100
1715 | MALDAH | Malda Division | MALIOR PWSS , SM/12192 | New | Material Requisition To Resource Division | 1618/MD | 11/04/2023 | 0 | Resource Division | 17.18 | 0 | 0 | 0
1716 | MALDAH | Malda Division | MALIOR PWSS , SM/12192 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Malior Water Supply Scheme of Harishchandrapur-II Block under Malda Division P.H.E Dte in the District of Malda. | 3967/MD | 07/08/2024 | 180 | SUBHAS CHANDRA KESHARI | 30.15 | 0 | 0 | 0
1717 | MALDAH | Malda Division | MALIOR PWSS , SM/12192 | New | Material Requisition To Resource Division | 3924/MD | 06/08/2024 | 0 | Resource Division | 4.07 | 0 | 0 | 0
1718 | MALDAH | Malda Division | MALIOR PWSS , SM/12192 | New | Formal work order for the work of Implementation of MALIOR Water Supply Scheme at HarishchandrapurII Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2021/MD | 18/05/2023 | 958 | JAHANGIR ALAM | 509.49 | 0 | 0 | 95
1719 | MALDAH | Malda Mechanical | MALIOR PWSS , SM/12192 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Malior Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013022) | 2259/MLMD | 18/07/2023 | 773 | NIRMAN. | 26.34 | 0 | 0 | 83
1720 | MALDAH | Malda Division | MALIOR PWSS , SM/12192 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Malior Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 55 | 08/01/2025 | 311 | ABHIJIT PAUL | 28.77 | 0 | 0 | 70
1721 | MALDAH | Malda Division | MALIOR PWSS , SM/12192 | New | Construction of Boundary Wall at Head Work site of Malior Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. (3rd Call). | 2420/MD | 27/05/2025 | 45 | JAHANGIR ALAM | 27.3 | 0 | 0 | 0
1722 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Narayanpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09656 | Retrofitting | Laying of distribution Pipe line at Shrirampur, Narayanpur for installation of FHTC under Narayanpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1178/MAAD | 13/06/2022 | 45 | BEE GEE CONSTRUCTION | 4.64 | 0 | 0 | 1
1723 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Narayanpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09656 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Narayanpur Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Narayanpur) | 1742/MAAD | 24/11/2021 | 60 | BEE GEE CONSTRUCTION | 56.38 | 0 | 0 | 1
1724 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Narayanpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09656 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Ramchandrapur Water Supply Scheme (Habitation- Ramnathpur) English Bazar Block under Malda Arsenic Area Water Supply Division, P.H.E Dte. | 2007/MAAD | 28/12/2021 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.38 | 0 | 0 | 1
1725 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Narayanpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09656 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: - Narayanpur, Mojampur, Srirampur for installation of FHTC under Narayanpur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 2042/MAAD | 16/11/2022 | 45 | BEE GEE CONSTRUCTION | 7.94 | 0 | 0 | 1
1726 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Narayanpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09656 | Retrofitting | Material Requisition To Resource Division | 1335 | 18/07/2022 | 0 | Resource Division | 12.3 | 0 | 0 | 0
1727 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Narayanpur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09656 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
1728 | MALDAH | Malda Division | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15105 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of DAHARA Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-II) | 756/MD | 17/02/2023 | 45 | SUBHAS CHANDRA KESHARI | 85.86 | 0 | 0 | 0
1729 | MALDAH | Malda Division | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15105 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 200mm. Big dia Tube Well 150 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of DAHARA Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | 1440/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 11.02 | 0 | 0 | 100
1730 | MALDAH | Malda Division | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15105 | Augmentation | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of DAHARA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 5596/MD | 05/11/2024 | 30 | M/S AMIT KUMAR GUPTA | 1.71 | 0 | 0 | 10
1731 | MALDAH | Malda Division | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15105 | Augmentation | Acceptance cum formal work order for Laying of additional pipeline & replacing damaged AC pipe line by UPVC Pipe line in connection with Source Augmentation of DAHARA Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda .(Part-I) | 748/MD | 17/02/2023 | 30 | M/S AMIT KUMAR GUPTA | 46.66 | 0 | 0 | 95
1732 | MALDAH | Malda Division | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15105 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dahara Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | 1298/MD | 23/03/2023 | 45 | A. L. ENGINEERING SOLUTION | 4.19 | 0 | 0 | 97
1733 | MALDAH | Malda Mechanical | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15105 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Dahara Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte. (TSM/016549) | 3698/MLMD | 29/11/2023 | 180 | DAS CONSTRUCTION | 12.55 | 0 | 0 | 100
1734 | MALDAH | Malda Mechanical | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15105 | Augmentation | Quatation for new service connection at DAHARAw/s sch. T/W no III UNDER MLMD. Dist Malda. (Harishchandrapur C. C. C) | BP-2023-24-528 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 8.41 | 0 | 0 | 0
1735 | MALDAH | Malda Division | Source Augmentation of Dahara Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15105 | Augmentation | Construction of Boundary Wall at 3rd Tube well site of Dahara Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 77 | 13/01/2025 | 45 | RAJIB MANI | 10.09 | 0 | 0 | 0
1736 | MALDAH | Malda Division | Source Augmentation of Dakshin Gouripur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15073 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and Replacing of damaged A.C pipe line by different dia UPVC pipe for Dakshin Gouripur Piped Water Supply scheme in Harischandrapur II Block under Malda Division PHE. Dte. | 768/MD | 17/02/2023 | 45 | SUDIPTA GHOSH | 29.67 | 0 | 0 | 0
1737 | MALDAH | Malda Division | Source Augmentation of Dakshin Gouripur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15073 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 140 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of DAKSHIN GOURIPUR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | 1436/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 9.62 | 0 | 0 | 100
1738 | MALDAH | Malda Division | Source Augmentation of Dakshin Gouripur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15073 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Dakshin Gouripur Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte. | 1295/MD | 23/03/2023 | 45 | SAYEM ENTERPRISE | 4.18 | 0 | 0 | 97
1739 | MALDAH | Malda Mechanical | Source Augmentation of Dakshin Gouripur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15073 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Dakshin Gouripur, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-501 | 01/02/2024 | 0 | W.B.S.E.D.C.LTD | 5.07 | 0 | 0 | 0
1740 | MALDAH | Malda Division | Source Augmentation of Dakshin Gouripur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15073 | Augmentation | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of DAKSHIN GOURIPUR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 5615/MD | 06/11/2024 | 30 | A. H. ENTERPRISE | 1.7 | 0 | 0 | 100
1741 | MALDAH | Malda Mechanical | Source Augmentation of Dakshin Gouripur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15073 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Dakshin Gouripur Water Supply Scheme in the District of under Malda Mechanical Division, PHE Dte. | 3697/MLMD | 29/11/2023 | 489 | SOVON KUMAR DAS. | 10.95 | 0 | 0 | 100
1742 | MALDAH | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15080 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 3 ( 99.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MABARAKPUR Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | 1165/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 7.79 | 0 | 0 | 100
1743 | MALDAH | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15080 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 ( 99.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at MABARAKPUR Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | 1166/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 7.79 | 0 | 0 | 100
1744 | MALDAH | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15080 | Augmentation | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Mobarakpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | 1204/MD | 21/03/2023 | 45 | M. S. AGENCY | 8.3 | 0 | 0 | 100
1745 | MALDAH | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15080 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for MABARAKPUR Piped Water Supply Scheme (Mouza- Jalkar Bithan, JL No. 115) at Old Malda Dev. Block of Malda District under Malda Division, PHE Dte. | 1164/MD | 20/03/2023 | 45 | AVIK KUMAR GHOSH | 27.37 | 0 | 0 | 85
1746 | MALDAH | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15080 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning,and 3 (three) months Trial Run and 25 cum/hr. capacity of Iron Elimination Plants (Pressure type) with provision of polishing unit alongwith Construction of 3.60 mtr.X 3.00 mtr Blower Room in connection with source Augmentation at 3rd Tube Well site of MABARAKPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | 4112/MD | 10/10/2023 | 120 | M/S AMIT KUMAR GUPTA | 14.74 | 0 | 0 | 90
1747 | MALDAH | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15080 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for MABARAKPUR Piped Water Supply Scheme (Moua Mabrakpur, JL No.- 123 & Mouza-Muchia, JL No. 124) at Old Malda Dev. Block of Malda District under Malda Division, PHE Dte. | 1156/MD | 20/03/2023 | 45 | TARUN KUMAR DEY | 41.74 | 0 | 0 | 100
1748 | MALDAH | Malda Mechanical | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15080 | Augmentation | Supply, installation, commissioning & Trial operation of electro-mechanical components at T/W no III & IV of Source Augmentation Mabarakpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016719) | 2775/MLMD | 14/08/2023 | 180 | SUDIP DEY | 21.81 | 0 | 0 | 100
1749 | MALDAH | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15080 | Augmentation | Construction of Boundary Wall and pathway at 3rd Tube well Site of MOBARAKPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | 286/MD | 11/01/2024 | 45 | M. S. AGENCY | 7.66 | 0 | 0 | 100
1750 | MALDAH | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15080 | Augmentation | Augmentation work of Boundary wall, Pump House, Blower Room RCC Over Head Reservoir and Construction Pathway & Approach Road at Head Work Site of MOBARAKPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | 2707/MD | 04/06/2025 | 75 | SAHA CONSTRUCTION | 19.71 | 0 | 0 | 0
1751 | MALDAH | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15080 | Augmentation | Augmentation work of Boundary wall, Pump House and Construction of Toilet at 2nd Tube Well Site of MOBARAKPUR Water Supply Scheme of Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | 1740/MD | 08/05/2025 | 222 | M/S DEY ENTERPRISE | 5.78 | 0 | 0 | 0
1752 | MALDAH | Malda Division | Source Augmentation of Mabrakpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15080 | Augmentation | Construction of Boundary Wall at 4th Tube well Site of MOBARAKPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, P.H.E.Dte. in the District of Malda. | 712/MD | 09/02/2024 | 45 | S. R. ENTERPRISE | 6.71 | 0 | 0 | 100
1753 | MALDAH | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte , SM/15521 | New | Material Requisition To Resource Division | 666/MAAD | 11/04/2023 | 0 | Resource Division | 25.35 | 0 | 0 | 0
1754 | MALDAH | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte , SM/15521 | New | Construction of 900 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Alipur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. (2nd Call) | 868/MAAD | 04/05/2023 | 698 | NEOGI ENTERPRISE | 364.29 | 0 | 0 | 80
1755 | MALDAH | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte , SM/15521 | New | Laying of Distribution System for Alipur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 281/MAAD | 06/03/2024 | 90 | SOFIQUL ISLAM | 166.6 | 0 | 0 | 30
1756 | MALDAH | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte , SM/15521 | New | Sinking of Three nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Alipur Piped Water supply scheme (Head Work Site, 2nd Tube well site & 3rd Tube well site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda. | 2055/MAAD | 22/11/2023 | 45 | M/S S.S. ENTERPRISE | 22.17 | 0 | 0 | 100
1757 | MALDAH | Malda Mechanical | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte , SM/15521 | New | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I , II & III and Arsenic Iron Removal Plant at Alipur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte | 2614/MLMD | 10/08/2023 | 1022 | DIPALI CONSTRUCTION. | 86.14 | 0 | 0 | 32
1758 | MALDAH | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte , SM/15521 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site of Alipur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 2057/MAAD | 22/11/2023 | 161 | TARUN KANTI BAGCHI | 5.02 | 0 | 0 | 100
1759 | MALDAH | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte , SM/15521 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Alipur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | 2058/MAAD | 22/11/2023 | 547 | MERCURY ENGINEERING COMPANY | 271.74 | 0 | 0 | 10
1760 | MALDAH | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte , SM/15521 | New | Construction of Boundary Wall at Head Work Site , 2nd Tube Well Site and 3rd Tube Well Site, Laying of rising main from 2nd and 3rd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Alipur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 406/MAAD | 12/03/2025 | 90 | NEOGI ENTERPRISE | 125.15 | 0 | 0 | 0
1761 | MALDAH | Malda Mechanical | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte , SM/15521 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 4336/MLMD | 31/12/2024 | 59 | SUBRATA SAHA | 0.77 | 0 | 0 | 0
1762 | MALDAH | Malda Ars Area W/S Division | Alipur Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area water Supply Division, PHE Dte , SM/15521 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 3rd Tube Well site of Alipur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda | 2056/MAAD | 22/11/2023 | 131 | BINA CONSTRUCTION | 5.02 | 0 | 0 | 100
1763 | MALDAH | Malda Mechanical | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15223 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I zone-I of Kandaran PWSS, Malatipur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004382812 | 21/08/2023 | 90 | W.B.S.E.D.C.LTD | 5.67 | 0 | 0 | 100
1764 | MALDAH | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15223 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 157.32 | 0 | 0 | 0
1765 | MALDAH | Malda Mechanical | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15223 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II, III & IV and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Augmentation of Kandaran (Zone- I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011258) | 3424/MLMD | 01/11/2023 | 818 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 45.31 | 0 | 0 | 74
1766 | MALDAH | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15223 | New | Material Requisition To Resource Division | 96/MD | 05/01/2024 | 0 | Resource Division | 38.49 | 0 | 0 | 0
1767 | MALDAH | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15223 | New | Formal work order for the work of Laying Distribution pipe line for KANDARON (ZONE-II) & its adjoining mouzas piped water supply at Chanchal-II Block in the District Malda under Malda Division, PHE Dte. | 818/MD | 20/02/2023 | 681 | UTTAM KUMAR GHOSH | 175.28 | 0 | 0 | 95
1768 | MALDAH | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15223 | New | Formal work order for the work of Augmentation of KANDARAN ZONE-I Piped Water Supply Scheme at Chanchal-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1910/MD | 11/05/2023 | 966 | M/S SINHA CONSTRUCTION CO. | 1071.52 | 0 | 0 | 93
1769 | MALDAH | Malda Mechanical | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15223 | New | Supply, installation, commissioning of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W no. I of Augmentation of Kandaran (Zone-I I) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011258) | 2658/MLMD | 10/08/2023 | 2005 | DILIP MAHATO. | 34.5 | 0 | 0 | 67
1770 | MALDAH | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15223 | New | Formal work order for the work of Construction of OHR and providing Functional Household Tap Connection for Augmentation of Kandaran Zone -II Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 4321/MD | 16/10/2023 | 533 | WELFARE ENGINEERING CO-OPERATIVE CONTRACT & CONSTRUCTION SOCIETY LTD. | 187.94 | 0 | 0 | 75
1771 | MALDAH | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15223 | New | Construction of Boundary Wall at 2nd TW site of KANDARAN ZONE-I Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | 1520/MD | 16/03/2024 | 406 | JUPITAR LABOUR CO-OPERATIVE CONTRACT AND CONSTRUCTION SOCIETY LTD. | 31.42 | 0 | 0 | 80
1772 | MALDAH | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15223 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kandaran Zone-I Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | 701/MD | 21/02/2025 | 45 | M/S SINHA CONSTRUCTION CO. | 33.12 | 0 | 0 | 0
1773 | MALDAH | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15223 | New | Sinking of Tube Well No -I & Replacement of Existing Tube Well at Site No- II each of 200mm Dia all through and 180 Mtr. Deep Big Dia Tube Well at Kandaran Zone-I Piped Water Supply Scheme at Chanchal -II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 3692/MD | 29/07/2025 | 216 | ASHIS CONSTRUCTION | 21.23 | 0 | 0 | 50
1774 | MALDAH | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15223 | New | Restoration of pipe line by concreting of Kandaran Zone -II Water Supply Scheme under Chanchal -II Block under Malda Division, PHE Dte. in the district of Malda. | 3694/MD | 29/07/2025 | 155 | UTTAM KUMAR GHOSH | 41.82 | 0 | 0 | 0
1775 | MALDAH | Malda Division | Ground Water Based for Kandaran Zone-I & II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15223 | New | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Kandaran Zone-I Water Supply Scheme in Chanchol- II block under Malda Division, PHE Dte. | 1745/MD | 15/06/2021 | 14 | INDRANIL DUTTA & ACCOCIATES | 2.86 | 0 | 0 | 0
1776 | MALDAH | Malda Mechanical | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED , SM/15949 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Nabinagar PWSS, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004427272 | 18/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.26 | 0 | 0 | 100
1777 | MALDAH | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED , SM/15949 | New | Material Requisition To Resource Division | 627/MAAD | 05/04/2023 | 0 | Resource Division | 26.27 | 0 | 0 | 0
1778 | MALDAH | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED , SM/15949 | New | Laying of Distribution System at Paschim Chamatola, Bankpara, Layagram, Puratun Tola for Nabinagar Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 640/MAAD | 06/04/2023 | 60 | SOVON KUMAR DAS | 50.45 | 0 | 0 | 95
1779 | MALDAH | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED , SM/15949 | New | Laying of Distribution System at Lashratalla, Madhyapara & Nabinagar for Nabinagar Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 639/MAAD | 06/04/2023 | 451 | DHRITIPALI | 34.15 | 0 | 0 | 85
1780 | MALDAH | Malda Mechanical | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED , SM/15949 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Nabinagar Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017551) | 2687/MLMD | 11/08/2023 | 869 | DEY ENTERPRISE.. | 65.66 | 0 | 0 | 45
1781 | MALDAH | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED , SM/15949 | New | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Nabinagar Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1695/MAAD | 19/11/2024 | 30 | DHRITIPALI | 31.71 | 0 | 0 | 0
1782 | MALDAH | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED , SM/15949 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Nabinagar Piped Water supply scheme (Head Work Site & 2nd Tube well Site ) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda (2nd Call) | 1412/MAAD | 20/07/2023 | 45 | M/S DYNAMIC CONSTRUCTION | 14.64 | 0 | 0 | 100
1783 | MALDAH | Malda Mechanical | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED , SM/15949 | New | QUOTATION PAYMENT FOR NABINAGAR W/S SCHEME T/W NO 1 UNDER KALIACHAK CCC UNDER MALDA DISTRICT | BP-2024-25-397 | 29/07/2024 | 0 | W.B.S.E.D.C.LTD | 3.91 | 0 | 0 | 0
1784 | MALDAH | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED , SM/15949 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site of Nabinagar Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 1470/MAAD | 01/08/2023 | 427 | M/S A.B. CONSTRUCTION | 5.02 | 0 | 0 | 100
1785 | MALDAH | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED , SM/15949 | New | Construction of 450 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation for Nabinagar Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda | 3018/MAAD | 06/12/2023 | 573 | M/S AMIT KUMAR GUPTA | 164.67 | 0 | 0 | 80
1786 | MALDAH | Malda Ars Area W/S Division | Nabinagar mouza Piped water supply Scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED , SM/15949 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Nabinagar Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. (2ND Call) | 3079/MAAD | 14/12/2023 | 365 | SOFIQUL ISLAM | 151.63 | 0 | 0 | 15
1787 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16053 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 82.44 | 0 | 0 | 0
1788 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16053 | Augmentation | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-I Piped Water Supply Scheme at Manikchak Dev. Block of Malda district under Malda Division, PHE Dte. | 1752/MD | 26/04/2023 | 921 | M/S PARIMAL DAS | 154.83 | 0 | 0 | 85
1789 | MALDAH | Malda Mechanical | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16053 | Augmentation | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-XI and Arsenic Iron Removal Plant at UTTAR CHANDIPUR (ZONE-I) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019385) | 2679/MLMD | 11/08/2023 | 540 | MERCURY ENGINEERING COMPANY. | 48.39 | 0 | 0 | 40
1790 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16053 | Augmentation | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-I Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | 2918/MD | 10/06/2024 | 30 | M/S PARIMAL DAS | 26.22 | 0 | 0 | 0
1791 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16053 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Uttar Chandipur Zone-I Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | 6402/MD | 19/12/2024 | 45 | M/S PARIMAL DAS | 12.41 | 0 | 0 | 0
1792 | MALDAH | Malda Mechanical | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16053 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Uttar Chandipur Zone- I, Mathurapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-463 | 17/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.06 | 0 | 0 | 0
1793 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16053 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning of Arsenic cum Iron Removal Plant (Modified SUJAPUR-SADIPUR Model) with Trial run for a period of 3 (three) months after completion of the works and 3 months maintenance after successful trial run of 30.00M³/hr. capacity Arsenic cum Iron Removal Plant for Uttar Chandipur Zone-I Water Supply Scheme of Manikchak Block under Malda Division, P.H.E. Dte. in the district of Malda. | 1276/MD | 15/03/2024 | 728 | GIYASUDDIN SEKH | 133.01 | 0 | 0 | 35
1794 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- I Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/16053 | Augmentation | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | 654/MD | 19/02/2025 | 7 | DHRITIPALI | 0.55 | 0 | 0 | 0
1795 | MALDAH | Malda Mechanical | SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15962 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Sujapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/018437) | 2770/MLMD | 14/08/2023 | 180 | M/S. KUNDU BROTHERS.. | 25.32 | 0 | 0 | 0
1796 | MALDAH | Malda Division | SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15962 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Sujapur Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | 3965/MD | 07/08/2024 | 180 | NEOGI ENTERPRISE | 30.19 | 0 | 0 | 0
1797 | MALDAH | Malda Division | SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15962 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sujapur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 1191/MD | 14/03/2024 | 45 | NEOGI ENTERPRISE | 26.42 | 0 | 0 | 0
1798 | MALDAH | Malda Division | SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15962 | New | Material Requisition To Resource Division | 811/MD | 21/02/2024 | 0 | Resource Division | 31.08 | 0 | 0 | 0
1799 | MALDAH | Malda Division | SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15962 | New | Material Requisition To Resource Division | 406/MD | 18/01/2024 | 0 | Resource Division | 2.22 | 0 | 0 | 0
1800 | MALDAH | Malda Mechanical | SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15962 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Sujapur, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte | BP-2024-25-188 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 2.94 | 0 | 0 | 0
1801 | MALDAH | Malda Division | SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15962 | New | Formal work order for the work of Implementation of SUJAPUR Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2168/MD | 07/06/2023 | 1025 | NEOGI ENTERPRISE | 395.25 | 0 | 0 | 50
1802 | MALDAH | Malda Division | SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15962 | New | Sinking of 200 mm (all through) Big Dia. Tube-Well of 130 M Deep at Rahutgaon (JL No-27) mouza under Sujapur PWSS of Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | 4808/MD | 13/09/2024 | 152 | NEOGI ENTERPRISE | 9.07 | 0 | 0 | 0
1803 | MALDAH | Malda Division | SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15962 | New | Construction of Boundary Wall at 3rd Tubewell Site of Sujapur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 2920/MD | 10/06/2024 | 509 | NEOGI ENTERPRISE | 21.09 | 0 | 0 | 95
1804 | MALDAH | Malda Mechanical | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED , SM/17201 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Sadipur , Mothabari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004390610 | 14/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.45 | 0 | 0 | 100
1805 | MALDAH | Malda Mechanical | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED , SM/17201 | New | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Sadipur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/017477) | 2051/MLMD | 30/06/2023 | 180 | MERCURY ENGINEERING COMPANY. | 63.89 | 0 | 0 | 30
1806 | MALDAH | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED , SM/17201 | New | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Sadipur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1698/MAAD | 19/11/2024 | 60 | SHREE BISHNU CONSTRUCTION | 65.9 | 0 | 0 | 0
1807 | MALDAH | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED , SM/17201 | New | Laying of Distribution System at Kabirajtola, Chowdhury Para for Sadipur Piped Water supply scheme at Kaliachak-II Block under Malda Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 598/MAAD | 30/03/2023 | 60 | M/S MANDAL & SONS | 44.94 | 0 | 0 | 100
1808 | MALDAH | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED , SM/17201 | New | Laying of Distribution System at Pathan Para, Mia Para, Dhanuk Para, Barkattabad, Rishi Para, Molla Para for Sadipur Piped Water supply scheme at Kaliachak-II Block under Malda Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 600/MAAD | 30/03/2023 | 60 | BINA CONSTRUCTION | 43.18 | 0 | 0 | 100
1809 | MALDAH | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED , SM/17201 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Sadipur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | 553/MAAD | 24/03/2023 | 45 | A.L. ENGINEERING SOLUTION | 14.65 | 0 | 0 | 100
1810 | MALDAH | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED , SM/17201 | New | Laying of Distribution System at Kabirajtola, Chowdhury Para for Sadipur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 1460/MAAD | 26/07/2023 | 60 | M/S MANDAL & SONS | 1.83 | 0 | 0 | 100
1811 | MALDAH | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED , SM/17201 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Sadipur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 610/MAAD | 31/03/2023 | 422 | A.L. ENGINEERING SOLUTION | 5.02 | 0 | 0 | 0
1812 | MALDAH | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED , SM/17201 | New | Construction of 450 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Sadipur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda(2ND Call) | 1706/MAAD | 20/09/2023 | 650 | M/S N. C. SARKAR | 203.63 | 0 | 0 | 75
1813 | MALDAH | Malda Ars Area W/S Division | Sadipur mouza Piped water supply Scheme of Kaliachak-II block under Malda arsenic area water supply Division, PHED , SM/17201 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Sadipur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. | 1575/MAAD | 25/08/2023 | 494 | MERCURY ENGINEERING COMPANY | 156.64 | 0 | 0 | 40
1814 | MALDAH | Malda Division | BABUPUR PWSS , SM/18433 | New | Construction of Boundary Wall at 2nd Tube well site of Babupur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6201/MD | 09/12/2024 | 45 | M/S GHOSH CONSTRUCTION | 7.15 | 0 | 0 | 0
1815 | MALDAH | Malda Division | BABUPUR PWSS , SM/18433 | New | Material Requisition To Resource Division | 815/MD | 21/02/2024 | 0 | Resource Division | 49.72 | 0 | 0 | 0
1816 | MALDAH | Malda Division | BABUPUR PWSS , SM/18433 | New | Material Requisition To Resource Division | 6156/MD | 05/12/2024 | 0 | Resource Division | 12.16 | 0 | 0 | 0
1817 | MALDAH | Malda Division | BABUPUR PWSS , SM/18433 | New | Material Requisition To Resource Division | 236/MD | 10/01/2024 | 0 | Resource Division | 19.1 | 0 | 0 | 0
1818 | MALDAH | Malda Mechanical | BABUPUR PWSS , SM/18433 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Babupur, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-666 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.75 | 0 | 0 | 0
1819 | MALDAH | Malda Mechanical | BABUPUR PWSS , SM/18433 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Babupur, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-665 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.41 | 0 | 0 | 0
1820 | MALDAH | Malda Mechanical | BABUPUR PWSS , SM/18433 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Babupur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014434) | 2383/MLMD | 28/07/2023 | 180 | GHOSH BROTHERS... | 41.99 | 0 | 0 | 0
1821 | MALDAH | Malda Division | BABUPUR PWSS , SM/18433 | New | Formal work order for the work of Implementation of BABUPUR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3033/MD | 09/08/2023 | 1023 | M/S UDYOG & CO. | 1331.07 | 0 | 0 | 65
1822 | MALDAH | Malda Division | BABUPUR PWSS , SM/18433 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Babupur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6408/MD | 19/12/2024 | 423 | MANIK CHOUDHURY | 50.96 | 0 | 0 | 0
1823 | MALDAH | Malda Division | BABUPUR PWSS , SM/18433 | New | Erection of Property board related to Jal Jeevan Mission works of Fatepur, Paharpur, Uttar Mahinagar, Arazi Jalsa, Babupur, Rajaramchak & Emamnagar PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 639/MD | 19/02/2025 | 7 | S. N. CONSTRUCTION | 0.95 | 0 | 0 | 0
1824 | MALDAH | Malda Division | HORGOA Piped Water Supply Scheme , SM/13432 | New | Material Requisition To Resource Division | 1810/MD | 27/04/2023 | 0 | Resource Division | 20.8 | 0 | 0 | 0
1825 | MALDAH | Malda Division | HORGOA Piped Water Supply Scheme , SM/13432 | New | Formal work order for the work of Implementation of HORGOA Piped Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1887/MD | 08/05/2023 | 694 | M/S PARIMAL DAS | 418.92 | 0 | 0 | 45
1826 | MALDAH | Malda Division | HORGOA Piped Water Supply Scheme , SM/13432 | New | Sinking of Tubewell, Providing FHTC, Construction of Pump House & Boundary wall at Horgoa Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 5083/MD | 27/09/2024 | 60 | M/S TECHNICO & CO | 44.88 | 0 | 0 | 0
1827 | MALDAH | Malda Mechanical | HORGOA Piped Water Supply Scheme , SM/13432 | New | W.B.S.E.D.C.LTD Quotation charge at Pole shifting at Horgoa, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. |  | 26/01/2024 | 0 | W.B.S.E.D.C.LTD | 0.57 | 0 | 0 | 0
1828 | MALDAH | Malda Mechanical | HORGOA Piped Water Supply Scheme , SM/13432 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Horgoa, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-396 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 7.77 | 0 | 0 | 0
1829 | MALDAH | Malda Division | HORGOA Piped Water Supply Scheme , SM/13432 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at (KM.-18/8-18/9) between Bulbulchandi(BBC) to Singabad(SQB) station for HARGOA and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | BP-2024-25-91 | 13/06/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 0.11 | 0 | 0 | 0
1830 | MALDAH | Malda Mechanical | HORGOA Piped Water Supply Scheme , SM/13432 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Horgoa, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-424 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.6 | 0 | 0 | 0
1831 | MALDAH | Malda Division | HORGOA Piped Water Supply Scheme , SM/13432 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at (KM.-18/8-18/9) between Bulbulchandi(BBC) to Singabad(SQB) station for HARGOA and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | BP-2024-25-194 | 06/08/2024 | 0 | RAIL BHOOMI CROSSING SEVA (IR-RBCS), NORTHEAST FRONTIER RAILWAY KATIHAR DIVISION | 6.2 | 0 | 0 | 0
1832 | MALDAH | Malda Division | HORGOA Piped Water Supply Scheme , SM/13432 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of HORGOA Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 2325/MD | 08/06/2023 | 60 | M/S S. S. ENTERPRISE | 75.74 | 0 | 0 | 40
1833 | MALDAH | Malda Mechanical | HORGOA Piped Water Supply Scheme , SM/13432 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Horgao Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015215) | 2320/MLMD | 26/07/2023 | 840 | M/S CHANDRANATH MUKHERJEE. | 26.64 | 0 | 0 | 80
1834 | MALDAH | Malda Division | HORGOA Piped Water Supply Scheme , SM/13432 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Hargoa Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 5835/MD | 22/11/2024 | 313 | RABIUL ISLAM | 15.25 | 0 | 0 | 0
1835 | MALDAH | Malda Division | HORGOA Piped Water Supply Scheme , SM/13432 | New | Construction of Boundary Wall at Head Work Site of Hargoa Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 5836/MD | 22/11/2024 | 281 | M/S ANKUSH ENTERPRISE | 22.71 | 0 | 0 | 90
1836 | MALDAH | Malda Division | HORGOA Piped Water Supply Scheme , SM/13432 | New | Construction of Boundary Wall at 2nd Tube well site of Hargoa Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 2482/MD | 28/05/2025 | 60 | SAYEM ENTERPRISE | 6.89 | 0 | 0 | 0
1837 | MALDAH | Malda Division | HORGOA Piped Water Supply Scheme , SM/13432 | New | Jack Pushing of M.S. pipe of 200 mm dia. through 600 mm dia M.S. pipe by Hydraulic Jacking Technique method through RLY. Track at KM 18/9-19/0 betweenBulbulchandi (BBC) to Shingabad Station(SQB) Station for HARGOA and it's adjoining Mouzas Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. | 384/MD | 17/01/2024 | 440 | GHOSH CONSTRUCTION | 28.86 | 0 | 0 | 100
1838 | MALDAH | Malda Ars Area W/S Division | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED , SM/15950 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Sakullapur Piped Water supply scheme (Head Work Site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | 554/MAAD | 24/03/2023 | 45 | MD. TALEB ALI | 7.32 | 0 | 0 | 100
1839 | MALDAH | Malda Ars Area W/S Division | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED , SM/15950 | New | Material Requisition To Resource Division | 629/MAAD | 05/04/2023 | 0 | Resource Division | 4.29 | 0 | 0 | 0
1840 | MALDAH | Malda Ars Area W/S Division | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED , SM/15950 | New | Laying of Distribution System for Sakullapur Piped Water supply scheme at Kaliachak-II Block under Malda Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 611/MAAD | 31/03/2023 | 60 | M/S MOON LIGHT CONSTRUCTION & CO. | 57.45 | 0 | 0 | 95
1841 | MALDAH | Malda Mechanical | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED , SM/15950 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I and Arsenic Iron Removal Plant at Sukurullapur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/018013) | 2690/MLMD | 11/08/2023 | 852 | ANIMA ENTERPRISE | 48.84 | 0 | 0 | 40
1842 | MALDAH | Malda Ars Area W/S Division | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED , SM/15950 | New | Construction of Boundary Wall at Head Work Site and Providing Functional House Hold Tap Connection (FHTC) for Sakullapur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1694/MAAD | 19/11/2024 | 45 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 31.56 | 0 | 0 | 0
1843 | MALDAH | Malda Ars Area W/S Division | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED , SM/15950 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Sakullapur Piped Water supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda. (2ND Call) | 1816/MAAD | 05/10/2023 | 605 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 133.47 | 0 | 0 | 80
1844 | MALDAH | Malda Ars Area W/S Division | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED , SM/15950 | New | Construction of 250 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Sakullapur Piped Water Supply scheme at Kaliachak-II Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda | 111/MAAD | 01/02/2024 | 547 | MAHBUB AND SONS | 100.84 | 0 | 0 | 80
1845 | MALDAH | Malda Mechanical | Sukurullapur mouza piped water supply Scheme of Kaliachak-II block under Malda Arsenic Area Water Supply Division, PHED , SM/15950 | New | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 1679/MLMD | 26/06/2024 | 62 | SUBRATA SAHA | 0.78 | 0 | 0 | 0
1846 | MALDAH | Malda Division | Hatinda Piped Water Supply Scheme. , SM/12078 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of HATINDA & its adjoining mouza Water Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | 2193/MD | 22/09/2022 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 6.66 | 0 | 0 | 1
1847 | MALDAH | Malda Division | Hatinda Piped Water Supply Scheme. , SM/12078 | New | Material Requisition To Resource Division | 2754/MD | 22/11/2022 | 0 | Resource Division | 25.94 | 0 | 0 | 0
1848 | MALDAH | Malda Division | Hatinda Piped Water Supply Scheme. , SM/12078 | New | Material Requisition To Resource Division | 1815/MD | 27/04/2023 | 0 | Resource Division | 29.46 | 0 | 0 | 0
1849 | MALDAH | Malda Mechanical | Hatinda Piped Water Supply Scheme. , SM/12078 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I , II & III and making compound lighting arrangement at T/W no. I of Augmentation of Hatinda Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011729) | 2222/MLMD | 18/07/2023 | 924 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 42.68 | 0 | 0 | 78
1850 | MALDAH | Malda Division | Hatinda Piped Water Supply Scheme. , SM/12078 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at HATINDA Piped Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 829/MD | 21/02/2024 | 45 | MD. MANSUR ALI | 4.14 | 0 | 0 | 0
1851 | MALDAH | Malda Mechanical | Hatinda Piped Water Supply Scheme. , SM/12078 | New | Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 3887/MLMD | 20/12/2023 | 60 | SUBRATA SAHA | 0.77 | 0 | 0 | 100
1852 | MALDAH | Malda Division | Hatinda Piped Water Supply Scheme. , SM/12078 | New | Material Requisition To Resource Division | 85/MD | 05/01/2024 | 0 | Resource Division | 13.89 | 0 | 0 | 0
1853 | MALDAH | Malda Division | Hatinda Piped Water Supply Scheme. , SM/12078 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 2 at HATINDA Piped Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 828/MD | 21/02/2024 | 388 | MD. MANSUR ALI | 4.14 | 0 | 0 | 100
1854 | MALDAH | Malda Division | Hatinda Piped Water Supply Scheme. , SM/12078 | New | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160 Mtr. Deep at Head Work Site at HATINDA Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 2410/MD | 27/05/2025 | 45 | MONDAL CONSTRUCTION | 10.65 | 0 | 0 | 0
1855 | MALDAH | Malda Division | Hatinda Piped Water Supply Scheme. , SM/12078 | New | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Hatinda Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 1102/MD | 20/03/2025 | 60 | USHA ENTERPRISE | 119.77 | 0 | 0 | 0
1856 | MALDAH | Malda Division | Hatinda Piped Water Supply Scheme. , SM/12078 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 160 Mtr. Deep Big dia Tube well (2 Nos.) at HATINDA Water Supply Scheme under Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1138/MD | 20/03/2023 | 671 | DUTTA ENTERPRISE | 21.12 | 0 | 0 | 100
1857 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (104 nos. schools in Kaliachak-II Block) , SM/10204 | School | Formal work order for Providing Drinking Water Supply in 17 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak ¿ II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 948/MAAD | 11/05/2022 | 120 | MILLENNIUM ENTERPRISE | 107.08 | 0 | 0 | 100
1858 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (104 nos. schools in Kaliachak-II Block) , SM/10204 | School | Providing Drinking Water Supply in 15 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak -II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 640/MAAD | 01/04/2022 | 120 | MILLENNIUM ENTERPRISE | 94.48 | 0 | 0 | 100
1859 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (104 nos. schools in Kaliachak-II Block) , SM/10204 | School | Supply & delivery of G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for providing Drinking Water Supply in Source Less Schols & ICDS at Kaliachak -II Block (Phase -I) under Malda Arsenic Area Water Supply Division, P.H.E. Dte. | 2043/MAAD | 16/11/2022 | 15 | M/S S.S. ENTERPRISE | 23.55 | 0 | 0 | 0
1860 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (104 nos. schools in Kaliachak-II Block) , SM/10204 | School | Formal work order for Providing Drinking Water Supply in 25 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 835/MAAD | 28/04/2022 | 120 | M/S S.S. ENTERPRISE | 157.47 | 0 | 0 | 0
1861 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (104 nos. schools in Kaliachak-II Block) , SM/10204 | School | Material Requisition To Resource Division | 338/MAAD | 28/02/2022 | 0 | Resource Division | 39.61 | 0 | 0 | 0
1862 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (104 nos. schools in Kaliachak-II Block) , SM/10204 | School | Formal work order for Providing Drinking Water Supply in 47 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - II Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure) | 1071/MAAD | 30/05/2022 | 90 | M/S S.S. ENTERPRISE | 297.8 | 0 | 0 | 100
1863 | MALDAH | Malda Division | INSTALLATION OF 121 Nos. STANDALONE COMMUNITY PURIFICATION PLANTS(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MANGALPURA,AKTOIL,HABIBPUR,BAIDYAPUR & JAJOIL IN HABIBPUR DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10246 | Anganwadi | Material Requisition To Resource Division | 529/MD | 03/03/2022 | 0 | Resource Division | 79.67 | 0 | 0 | 0
1864 | MALDAH | Malda Division | INSTALLATION OF 121 Nos. STANDALONE COMMUNITY PURIFICATION PLANTS(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MANGALPURA,AKTOIL,HABIBPUR,BAIDYAPUR & JAJOIL IN HABIBPUR DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10246 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Aktoil GP of Habibpur Dev. Block under Malda Division, PHE Dte. | 813/MD | 20/02/2023 | 75 | NEOGI ENTERPRISE | 137.07 | 0 | 0 | 70
1865 | MALDAH | Malda Division | INSTALLATION OF 121 Nos. STANDALONE COMMUNITY PURIFICATION PLANTS(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MANGALPURA,AKTOIL,HABIBPUR,BAIDYAPUR & JAJOIL IN HABIBPUR DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10246 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Mangalpura & Jajoil GP of Habibpur Dev. Block under Malda Division, PHE Dte. | 554/MD | 09/02/2023 | 75 | GBM ASSOCIATES | 112.04 | 0 | 0 | 80
1866 | MALDAH | Malda Division | INSTALLATION OF 121 Nos. STANDALONE COMMUNITY PURIFICATION PLANTS(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MANGALPURA,AKTOIL,HABIBPUR,BAIDYAPUR & JAJOIL IN HABIBPUR DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10246 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Baidyapur GP of Habibpur Dev. Block under Malda Division, PHE Dte. | 555/MD | 09/02/2023 | 75 | MILLENNIUM ENTERPRISR | 136.96 | 0 | 0 | 100
1867 | MALDAH | Malda Division | INSTALLATION OF 121 Nos. STANDALONE COMMUNITY PURIFICATION PLANTS(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MANGALPURA,AKTOIL,HABIBPUR,BAIDYAPUR & JAJOIL IN HABIBPUR DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10246 | Anganwadi | Material Requisition To Resource Division | 121/MD | 05/01/2024 | 0 | Resource Division | 6.8 | 0 | 0 | 0
1868 | MALDAH | Malda Division | INSTALLATION OF 121 Nos. STANDALONE COMMUNITY PURIFICATION PLANTS(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP-MANGALPURA,AKTOIL,HABIBPUR,BAIDYAPUR & JAJOIL IN HABIBPUR DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10246 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Habibpur GP of Habibpur Dev. Block under Malda Division, PHE Dte. | 542/MD | 08/02/2023 | 813 | NEOGI ENTERPRISE | 137.06 | 0 | 0 | 40
1869 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN BRINDABANBATI Water Supply Scheme , SM/06857 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of DAKSHIN BRINDABANBATI Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 1525/MD | 05/05/2021 | 30 | M/S DAS CONSTRUCTION | 57.24 | 23.59 | 49.77 | 1
1870 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN BRINDABANBATI Water Supply Scheme , SM/06857 | Retrofitting | Replacement of 200 mm dia. all through Tube Well at Head Work site (75m Deep) by D.R. Rig. Method using P.V.C. pipe & filter including supply of materials of Dakshin Brindabanbati Piped Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. Govt. of West Bengal. | 2274/MD | 21/05/2025 | 30 | A. L. ENGINEERING SOLUTION | 6.9 | 0 | 0 | 0
1871 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme , SM/06867 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme under Malda Division, PHE Dte. | 2439/MD | 12/10/2020 | 120 | M/S AMIT KUMAR GUPTA | 20 | 0 | 0 | 0
1872 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme , SM/06867 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of MAHESHPUR Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | 2442/MD | 12/10/2020 | 30 | M/S PRATIMA CONSTRUCTION | 14.91 | 0 | 0 | 1
1873 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme , SM/06867 | Retrofitting | Acceptance cum formal work order for Laying of UPVC pipe line in place of damaged portion due to the construction of PMGSY road at KANDARAN ZONE-I Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. (Part-III) | 36/CSD | 07/01/2022 | 20 | M/S FOUR STAR CONSTRUCTION | 4.84 | 0 | 0 | 1
1874 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme , SM/06867 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Chandipur Zone-IV Water Supply Scheme at Manikchak Dev. Block under Malda Division, PHE Dte. in the district of Malda. (Phase-III) | 1642/MD | 19/07/2022 | 30 | M/S AMIT KUMAR GUPTA | 16.26 | 0 | 0 | 1
1875 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme , SM/06867 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 2439/MD | 12/10/2020 | 45 | M/S AMIT KUMAR GUPTA | 72.29 | 28.64 | 33.9 | 66
1876 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MIANAGAR Water Supply Scheme , SM/06867 | Retrofitting | Design , Supplying, Fabrication, Erection, & Commissioning including 3 (three) months Trial Run of 25 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Mianagar Water Supply Scheme of Habibpur Dev. Block under Malda Division P.H.E Dte in the District of Malda. | 2760/MD | 09/06/2025 | 296 | UTTAM KUMAR GHOSH | 15.57 | 0 | 0 | 0
1877 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha , SM/09658 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Lakshmipur Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza-Panchanandapur) | 1748/MAAD | 24/11/2021 | 60 | MILLENNIUM ENTERPRISE | 37.54 | 0 | 0 | 1
1878 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha , SM/09658 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Uttar Laxmipur Water Supply Scheme (Mouza- Khanpur) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1025/MAAD | 12/05/2022 | 45 | BENGAL ENGINEERING COMPANY | 10.69 | 0 | 0 | 1
1879 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha , SM/09658 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) under command area of Laxmighat Water Supply Scheme (Mouza- Lakhmighat) extra pipe line at Lakhmipur village at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 2035/MAAD | 16/11/2022 | 45 | ANJIMA CONSTRUCTION CO. | 8.3 | 0 | 0 | 1
1880 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha , SM/09658 | Retrofitting | Laying of 160 mm dia UPVC Pipe line and Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Michhutola, Bhagattola under Uttar Laxmipur distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 328/MAAD | 21/02/2023 | 60 | M/S BABLU ENTERPRISE, | 21.8 | 0 | 0 | 100
1881 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha , SM/09658 | Retrofitting | Laying 63/75/90 mm dia loop Pipe line to connect Chowdhury para and Pichli village to provide sufficient drinking water though FHTC at Pichli Village and construction of approach road and boundary wall at reservoir site with allied work under Laxmighat W/S Scheme under Malda Arsenic Area W/S Division P.H.E Dte. | 1404/MAAD | 26/07/2022 | 45 | FUTURE | 15.68 | 0 | 0 | 1
1882 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha , SM/09658 | Retrofitting | Material Requisition To Resource Division | 1337/MAAD | 18/07/2022 | 0 | Resource Division | 12.3 | 0 | 0 | 0
1883 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Uttar Lakshmipur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliacha , SM/09658 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
1884 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Dariapur Water Supply Scheme(Mouza-Laxmipur,Baisnabnagar) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1728/MAAD | 24/11/2021 | 60 | DEY CONSTRUCTION | 46.22 | 0 | 0 | 1
1885 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Laying of HDPE pipe line of 20 mm dia at Birjutola,Sam Mahamand Tola,Laxmipur Villages Under Laxmipur GP under Dariapur distribution Zone under Malda Arsenic Area W/S Division, P.H.E.Dte. | 363/MAAD | 07/03/2022 | 30 | DEY CONSTRUCTION | 4.81 | 0 | 0 | 1
1886 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Laying of UPVC pipe 90mm dia at Srikasti,Chulkani & others Allied works at Dariapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 350/MAAD | 07/03/2022 | 45 | GIRIDHARI CONSTRUCTION | 2.9 | 0 | 0 | 1
1887 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Laying of HDPE pipe 20mm dia at Munshitola,Tewari Tola under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 908/MAAD | 10/05/2022 | 15 | DEY CONSTRUCTION | 4.81 | 0 | 0 | 1
1888 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Laying of HDPE pipe 20mm dia at Baultola, Bikkol Tola under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 909/MAAD | 10/05/2022 | 15 | DEY CONSTRUCTION | 1.73 | 0 | 0 | 1
1889 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area(Mouza Laxmipur Part, Bedrabad) & others Allied works at Dariapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 820/MAAD | 28/04/2022 | 60 | DEY CONSTRUCTION | 53.78 | 0 | 0 | 1
1890 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Bajapti &Khochpara under command area of Dariapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte | 2005/MAAD | 11/11/2022 | 45 | M/S MOON LIGHT CONSTRUCTION & CO. | 19.84 | 0 | 0 | 1
1891 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Laying of HDPE pipe 20mm dia at Dhulauri ,Hunumannagar & Bedrabad under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 803/MAAD | 24/04/2023 | 15 | DEY CONSTRUCTION | 3.91 | 0 | 0 | 0
1892 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) at Dariapur Mouza under command area of Dariapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1017/MAAD | 12/05/2022 | 60 | M/S PARIMAL DAS | 56.47 | 0 | 0 | 1
1893 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Diferent villages under Bedrabad GP (Dhulauri,Hunumannagar,Bedrabad) under command area of Dariapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 2031/MAAD | 16/11/2022 | 60 | DEY CONSTRUCTION | 56.08 | 0 | 0 | 1
1894 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Laying of HDPE pipe 20mm dia at Bedrabad ,Dulauri ,Srikasti & Manasa Mandir para under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1830MAAD | 27/09/2022 | 30 | DEY CONSTRUCTION | 4.07 | 0 | 0 | 1
1895 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Laying of UPVC Pipe Line of 90mm &75 mm dia at Different part of Dariapur Mouza for coverage of FHTC under Dariapur water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1871/MAAD | 28/09/2022 | 45 | M/S PARIMAL DAS | 4.49 | 0 | 0 | 1
1896 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Laying of UPVC pipeline at Kochpara to faciliate of House connection & others Allied works at Dariapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 70/MAAD | 11/01/2023 | 60 | DHRITIPALI | 6.69 | 0 | 0 | 0
1897 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Laying of UPVC pipe 90mm,75mm dia at Kochpara ,Bajapti & others Allied works at Dariapur W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 887/MAAD. | 11/05/2023 | 45 | MADHUMITA ENTERPRISE | 9.44 | 0 | 0 | 100
1898 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Bajapti &Khochpara under command area of Dariapur Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 2029/MAAD | 16/11/2022 | 45 | M/S MOON LIGHT CONSTRUCTION & CO. | 19.84 | 0 | 0 | 1
1899 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Dariapur Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Bl , SM/09652 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
1900 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) within the command area of Pardeonapur and its adjoining Mouzas in Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/10430 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Alinagar Water Supply Scheme (Mouza- Nabinagar) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1014/MAAD | 12/05/2022 | 60 | M/S ALISA CONSTRUCTION | 82.2 | 0 | 0 | 15
1901 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) within the command area of Pardeonapur and its adjoining Mouzas in Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/10430 | Retrofitting | Continuation Work Order for Placing of diesel driven Car on hire basis for official use of the Executive Engineer, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(for the period from 01.01.2023 to 31.12.2023)= 365 days | 2330/MAAD | 28/12/2022 | 365 | NITAI PANDEY | 1.73 | 0 | 0 | 25
1902 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) within the command area of Pardeonapur and its adjoining Mouzas in Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/10430 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
1903 | MALDAH | Malda Division | INSTALLATION OF 97 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF RATUA -II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10216 | Anganwadi | Acceptance cum formal work order for Supplying G.I. pipe strainer for installation of CWPP at AWC of Ratua-II Dev. Block at Chanchal Stack Yard under Malda Division, PHE Dte. | 1437/MD | 20/06/2022 | 15 | M/S RUBIET HOSSAIN | 17.37 | 0 | 0 | 100
1904 | MALDAH | Malda Division | INSTALLATION OF 97 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF RATUA -II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10216 | Anganwadi | Material Requisition To Resource Division | 522/MD | 03/03/2022 | 0 | Resource Division | 134.01 | 0 | 0 | 0
1905 | MALDAH | Malda Division | INSTALLATION OF 97 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT (CWPP) AT ANGANWADI CENTRES(AWCs) OF RATUA -II DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10216 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) at different Anganwadi Centres (AWCs) of Ratua-II Dev. Block, Malda under Malda Division, PHE Dte. | 1381/MD | 13/06/2022 | 120 | M/S RUBIET HOSSAIN | 688.25 | 0 | 0 | 100
1906 | MALDAH | Malda Division | GAURIA Piped Water Supply Scheme. , SM/12079 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 160 Mtr. deepTube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of GOURIA Water Supply Scheme at Chanchal I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2346/MD | 29/09/2022 | 30 | MECHANO TRADING CO. | 9.96 | 0 | 0 | 100
1907 | MALDAH | Malda Mechanical | GAURIA Piped Water Supply Scheme. , SM/12079 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Gauria PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004302683 | 21/07/2023 | 90 | W.B.S.E.D.C.LTD | 2.63 | 0 | 0 | 100
1908 | MALDAH | Malda Division | GAURIA Piped Water Supply Scheme. , SM/12079 | New | Material Requisition To Resource Division | 2757/MD | 22/11/2022 | 0 | Resource Division | 45.2 | 0 | 0 | 0
1909 | MALDAH | Malda Mechanical | GAURIA Piped Water Supply Scheme. , SM/12079 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Gauria Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011717) | 2318/MLMD | 26/07/2023 | 961 | DIPALI CONSTRUCTION. | 37.94 | 0 | 0 | 90
1910 | MALDAH | Malda Division | GAURIA Piped Water Supply Scheme. , SM/12079 | New | Formal work order for the work of Laying of Distribution pipe line of GAURIA and its adjoining mouzas Pipe Water Supply Scheme at Chanchal-I Block in the District of Malda under Malda Division P.H.E. Dte. | 2412/MD | 17/10/2022 | 473 | S DUTTA | 374.04 | 0 | 0 | 92
1911 | MALDAH | Malda Division | GAURIA Piped Water Supply Scheme. , SM/12079 | New | Construction of Boundary Wall at 3rd Tube Well site of Gauria Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 6197/MD | 09/12/2024 | 45 | M/S DYNAMIC CONSTRUCTION | 7.23 | 0 | 0 | 0
1912 | MALDAH | Malda Division | GAURIA Piped Water Supply Scheme. , SM/12079 | New | Construction of Boundary Wall at 2nd Tube Well site of Gauria Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 6196/MD | 09/12/2024 | 45 | M/S GHOSH ENTERPRISE | 7.23 | 0 | 0 | 0
1913 | MALDAH | Malda Division | GAURIA Piped Water Supply Scheme. , SM/12079 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 160 Mtr. Deep Big dia Tube well (2 Nos.) at GAURIA Water Supply Scheme under Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1137/MD | 20/03/2023 | 30 | ASHIS CONSTRUCTION | 21.11 | 0 | 0 | 50
1914 | MALDAH | Malda Division | GAURIA Piped Water Supply Scheme. , SM/12079 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No.- 3 at Gauria PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 271/MD | 11/01/2024 | 45 | S. M. BUILDER | 4.18 | 0 | 0 | 100
1915 | MALDAH | Malda Division | GAURIA Piped Water Supply Scheme. , SM/12079 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No.- 2 at Gauria PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 165/MD | 08/01/2024 | 45 | SK ENTERPRISE | 4.17 | 0 | 0 | 100
1916 | MALDAH | Malda Division | GAURIA Piped Water Supply Scheme. , SM/12079 | New | Material Requisition To Resource Division | 84/MD | 05/01/2024 | 0 | Resource Division | 13.46 | 0 | 0 | 0
1917 | MALDAH | Malda Mechanical | GAURIA Piped Water Supply Scheme. , SM/12079 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of GAURIA PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-440 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.22 | 0 | 0 | 0
1918 | MALDAH | Malda Mechanical | GAURIA Piped Water Supply Scheme. , SM/12079 | New | New service connection at GAURIA PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.(KUSHIDA c c c) | BP-2024-25-97 | 16/04/2024 | 0 | W.B.S.E.D.C.LTD | 4.27 | 0 | 0 | 0
1919 | MALDAH | Malda Division | GAURIA Piped Water Supply Scheme. , SM/12079 | New | Formal work order for the work of Construction of 600 M3 Capacity Over Head Reservoir with Soil Investigation and FHTC of GAURIA Piped Water Supply Scheme at Chanchal-I Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1036/MD | 13/03/2023 | 750 | SOVAN KUMAR ROY | 293.21 | 0 | 0 | 78
1920 | MALDAH | Malda Division | GAURIA Piped Water Supply Scheme. , SM/12079 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of GOURIA & its adjoining mouza Water Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | 2192/MD | 22/09/2022 | 279 | RAJIB MANI | 6.69 | 0 | 0 | 100
1921 | MALDAH | Malda Division | WARI Piped Water Supply Scheme , SM/12077 | New | Material Requisition To Resource Division | 2753/MD | 22/11/2022 | 0 | Resource Division | 42.01 | 0 | 0 | 0
1922 | MALDAH | Malda Division | WARI Piped Water Supply Scheme , SM/12077 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 150 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of WARI Water Supply Scheme at Harishchandrapur I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2349/MD | 29/09/2022 | 30 | MECHANO TRADING CO. | 9.65 | 0 | 0 | 100
1923 | MALDAH | Malda Division | WARI Piped Water Supply Scheme , SM/12077 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (2 Nos.) at WARI Water Supply Scheme under Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1675/MD | 18/04/2023 | 30 | SAUDAGAR INDIA | 20.31 | 0 | 0 | 100
1924 | MALDAH | Malda Mechanical | WARI Piped Water Supply Scheme , SM/12077 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Wari, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004368704 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.22 | 0 | 0 | 100
1925 | MALDAH | Malda Division | WARI Piped Water Supply Scheme , SM/12077 | New | Formal work order for the work of Laying of Distribution pipe line of WARI and its adjoining mouzas Pipe Water Supply Scheme at Harishchandrapur-I Block in the District of Malda under Malda Division P.H.E. Dte. | 2396/MD | 14/10/2022 | 90 | GHOSH BROTHERS | 379.96 | 0 | 0 | 85
1926 | MALDAH | Malda Division | WARI Piped Water Supply Scheme , SM/12077 | New | Construction of Boundary Wall at 2nd Tube Well site of Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 2944/MD | 10/06/2024 | 30 | MS ENTERPRISE | 9.33 | 0 | 0 | 5
1927 | MALDAH | Malda Division | WARI Piped Water Supply Scheme , SM/12077 | New | Construction of Boundary Wall at 3rd Tube Well site of Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 2945/MD | 10/06/2024 | 30 | MS ENTERPRISE | 9.33 | 0 | 0 | 90
1928 | MALDAH | Malda Division | WARI Piped Water Supply Scheme , SM/12077 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of WARI & its adjoining mouza Water Scheme at Harishchandrapur-I Dev. Block under Malda Division, PHE Dte. In the District of Malda. | 2195/MD | 22/09/2022 | 45 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 6.67 | 0 | 0 | 97
1929 | MALDAH | Malda Division | WARI Piped Water Supply Scheme , SM/12077 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Wari PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 273/MD | 11/01/2024 | 45 | LOKNATH ENTERPRISE | 4.19 | 0 | 0 | 97
1930 | MALDAH | Malda Division | WARI Piped Water Supply Scheme , SM/12077 | New | Material Requisition To Resource Division | 108/MD | 05/01/2024 | 0 | Resource Division | 13 | 0 | 0 | 0
1931 | MALDAH | Malda Mechanical | WARI Piped Water Supply Scheme , SM/12077 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of WARI PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-437 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.44 | 0 | 0 | 0
1932 | MALDAH | Malda Mechanical | WARI Piped Water Supply Scheme , SM/12077 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of WARI PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-438 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 6.56 | 0 | 0 | 0
1933 | MALDAH | Malda Division | WARI Piped Water Supply Scheme , SM/12077 | New | Formal work order for the work of Construction of 600 M3 Capacity OHR with soil Investigation and FHTC of WARI Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1567/MD | 10/04/2023 | 270 | SAMBHU NATH SARKAR | 288.41 | 0 | 0 | 42
1934 | MALDAH | Malda Mechanical | WARI Piped Water Supply Scheme , SM/12077 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Wari Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011955) | 2332/MLMD | 26/07/2023 | 796 | AHALYA ENGINEERING WORKS | 38.61 | 0 | 0 | 90
1935 | MALDAH | Malda Division | WARI Piped Water Supply Scheme , SM/12077 | New | Construction of Boundary Wall at Head Work site of Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 3039/MD | 13/06/2024 | 567 | SAMBHU NATH SARKAR | 36.41 | 0 | 0 | 90
1936 | MALDAH | Malda Division | WARI Piped Water Supply Scheme , SM/12077 | New | Providing Functional Household Tap Connection (FHTC) & Laying of additional Pipeline in connection with Jal Jeevan Mission (JJM) at Wari Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 344/MD | 30/01/2025 | 426 | GOBINDA ENTERPRISE | 107.02 | 0 | 0 | 0
1937 | MALDAH | Malda Division | WARI Piped Water Supply Scheme , SM/12077 | New | Laying of Rising Main including Specials and Valves for WARI Piped Water Supply Scheme at Harischandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 382/MD | 17/01/2024 | 271 | MAHA MAYA CONSTRUCTION | 15.4 | 0 | 0 | 72
1938 | MALDAH | Malda Division | WARI Piped Water Supply Scheme , SM/12077 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 2 at Wari PWSS under Harischandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 166/MD | 08/01/2024 | 45 | M/S SAI RAM ENTERPRISE | 4.19 | 0 | 0 | 98
1939 | MALDAH | Malda Mechanical | Improvement of existing 2 X 250 KVA Substation (11/0.433 Kv) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, P.H.E. Dte. , SM/13237 | Augmentation | Additional work of Improvement of Existing 2 x 250 KVA Substation (11/0.433KV) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, PHE Dte. | 3216/MLMD | 05/10/2023 | 14 | M/S P.P. ELECTRICALS | 4.47 | 0 | 0 | 100
1940 | MALDAH | Malda Mechanical | Improvement of existing 2 X 250 KVA Substation (11/0.433 Kv) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, P.H.E. Dte. , SM/13237 | Augmentation | Formal work order for the work of "Improvement of existing 2 x 250 KVA Substation (11/0.433 KV) with other allied works at Water Treatment Plant of Gour Area and Augmentation of Mahadipur W/S Scheme under Malda Mechanical Division, PHE Dte." | 2736/MLMD | 05/12/2022 | 789 | M/S P.P. ELECTRICALS | 115.25 | 0 | 0 | 100
1941 | MALDAH | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED , SM/13451 | New | Route survey & design for praparation of DPR of Mosimpur, Khaschandpur & Gayeshbari Pipe Water Supply Scheme at Kaliachak-I Development Block under Malda Arsenic Area W/S Division, Phe Dte. | 1666/MAAD | 08/09/2022 | 10 | FUTURE | 0.99 | 0 | 0 | 1
1942 | MALDAH | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED , SM/13451 | New | Continuation work order for Route survey & design for praparation of DPR of Mosimpur, Khaschandpur & Gayeshbari Pipe Water Supply Scheme at Kaliachak-I Development Block under Malda Arsenic Area W/S Division, Phe Dte. | 1670/MAAD | 12/09/2022 | 10 | FUTURE | 0.99 | 0 | 0 | 1
1943 | MALDAH | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED , SM/13451 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Mosimpur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | 155/MAAD | 02/02/2023 | 45 | A ONE ENTERPRISE | 14.72 | 0 | 0 | 100
1944 | MALDAH | Malda Mechanical | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED , SM/13451 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Masimpur, Sujapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004390333 | 10/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.17 | 0 | 0 | 100
1945 | MALDAH | Malda Mechanical | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED , SM/13451 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Masimpur, Sujapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004395276 | 16/08/2023 | 90 | W.B.S.E.D.C.LTD | 5.97 | 0 | 0 | 100
1946 | MALDAH | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED , SM/13451 | New | Material Requisition To Resource Division | 623/MAAD | 05/04/2023 | 0 | Resource Division | 21.69 | 0 | 0 | 0
1947 | MALDAH | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED , SM/13451 | New | Laying of Distribution System at Mosimpur Madrasha Para, Jolakandi Para, Jolakandi Mokdompur Para, Post Office Para, School Para, Baliharpur East, Baliharpur West for Mosimpur Piped Water supply scheme at Kaliachak-I under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. (2nd call) | 399/MAAD | 06/03/2023 | 514 | MANIK CHOUDHURY | 70.26 | 0 | 0 | 80
1948 | MALDAH | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED , SM/13451 | New | Laying of Distribution System at Mosimpur Chama Para, Beltala, Biswas Para, Darga Para, Khursed Para, Wayesh Mistry Para, Balupur, Baliharpur Rilif Pukur Para for Mosimpur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 222/MAAD | 03/02/2023 | 788 | SAHA CONSTRUCTION | 33.71 | 0 | 0 | 95
1949 | MALDAH | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED , SM/13451 | New | Laying of Distribution System at Mosimpur Madrasha Para, Jolakandi Para, Jolakandi Mokdompur Para, Post Office Para, School Para, Baliharpur East, Baliharpur West for Mosimpur Piped Water supply scheme at Kaliachak-I under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. (2nd call) | 222/MAAD | 27/02/2024 | 90 | MANIK CHOUDHURY | 3.73 | 0 | 0 | 90
1950 | MALDAH | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED , SM/13451 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 2nd Tube Well site of Mosimpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 108/MAAD | 30/01/2023 | 60 | MD WARESH ALI | 5.02 | 0 | 0 | 100
1951 | MALDAH | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED , SM/13451 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Mosimpur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | 857/MAAD | 03/05/2023 | 699 | USHA ENTERPRISE | 168.7 | 0 | 0 | 85
1952 | MALDAH | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED , SM/13451 | New | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Mosimpur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. .(3rd Call) | 1705/MAAD | 20/09/2023 | 650 | A. K. CONSTRUCTION | 211.7 | 0 | 0 | 80
1953 | MALDAH | Malda Ars Area W/S Division | Masimpur Mouza Piped Water supply scheme of Kaliachak-I block under Malda Arsenic area Water Supply Division, PHED , SM/13451 | New | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Mosimpur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 13/MAAD | 03/01/2025 | 50 | A. K. CONSTRUCTION | 66.36 | 0 | 0 | 90
1954 | MALDAH | Malda Mechanical | KRISHNAPUR PIPED WATER SUPPLY SCHEME. , SM/13746 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of KRISHNAPUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004508461 | 07/12/2023 | 90 | W.B.S.E.D.C.LTD | 3.89 | 0 | 0 | 100
1955 | MALDAH | Malda Mechanical | KRISHNAPUR PIPED WATER SUPPLY SCHEME. , SM/13746 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of KRISHNAPUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004508446 | 05/12/2023 | 90 | W.B.S.E.D.C.LTD | 7.95 | 0 | 0 | 100
1956 | MALDAH | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. , SM/13746 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 13.07 | 0 | 0 | 0
1957 | MALDAH | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. , SM/13746 | New | Construction of Boundary Wall at 2nd Tube well Site of Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 2939/MD | 10/06/2024 | 30 | PRITAM ENTERPRISE | 7.16 | 0 | 0 | 0
1958 | MALDAH | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. , SM/13746 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of KRISHNAPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 2334/MD | 08/06/2023 | 60 | GOBINDA ENTERPRISE | 90.08 | 0 | 0 | 85
1959 | MALDAH | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. , SM/13746 | New | Construction of Boundary Wall at Head Work site of Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 161/MD | 08/01/2024 | 45 | GOBINDA ENTERPRISE | 18.55 | 0 | 0 | 100
1960 | MALDAH | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. , SM/13746 | New | Placement of fund against the work for road restoration for laying pipe line for Bulbulchandi- Katlapukur road from 0552 KM to 9.943 Km under Talpukur and Krishnapur PWSS under Malda Division,PHE Dte. | BP-2024-25-260 | 13/09/2024 | 0 | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 30.66 | 0 | 0 | 0
1961 | MALDAH | Malda Mechanical | KRISHNAPUR PIPED WATER SUPPLY SCHEME. , SM/13746 | New | PAYMENT FOR SHIFTING OF 11 KV OVER HEAD LINE AT THE SITE OF KRISHNAPUR PHE UNDER RATHBARI CCC UNDER MALDA DISTRICT | BP-2023-24-593 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 3.79 | 0 | 0 | 0
1962 | MALDAH | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. , SM/13746 | New | Formal work order for the work of Implementation of KRISHNAPUR Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1573/MD | 10/04/2023 | 932 | M/S MAA TARA CONSTRUCTION | 570.36 | 0 | 0 | 80
1963 | MALDAH | Malda Mechanical | KRISHNAPUR PIPED WATER SUPPLY SCHEME. , SM/13746 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Krishnapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013458) | 2568/MLMD | 04/08/2023 | 710 | DAS ENTERPRISE. | 28.26 | 0 | 0 | 70
1964 | MALDAH | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. , SM/13746 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70 m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Krishnapur Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | 5837/MD | 22/11/2024 | 266 | VISCOUS ENGINEERS PVT. LTD. | 30.14 | 0 | 0 | 0
1965 | MALDAH | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. , SM/13746 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 5838/MD | 22/11/2024 | 175 | M/S MAA TARA CONSTRUCTION | 60.55 | 0 | 0 | 0
1966 | MALDAH | Malda Division | KRISHNAPUR PIPED WATER SUPPLY SCHEME. , SM/13746 | New | Construction of Boundary Wall at 2nd Tube well site of Krishnapur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 347/MD | 30/01/2025 | 90 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 7.18 | 0 | 0 | 0
1967 | MALDAH | Malda Mechanical | BHADAR Piped Water Supply Scheme , SM/12768 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Bhadar PWSS, Gazole C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004390642 | 16/08/2023 | 90 | W.B.S.E.D.C.LTD | 16.23 | 0 | 0 | 100
1968 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme , SM/12768 | New | Placing of diesel driven Car on hire basis for official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. in good running condition. (Period from 01/07/2023 to 30/09/2023). | 487/MD | 21/06/2023 | 92 | SUBHANKAR SINGH | 0.31 | 0 | 0 | 100
1969 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme , SM/12768 | New | Material Requisition To Resource Division | 1810/MD | 27/04/2023 | 0 | Resource Division | 20.43 | 0 | 0 | 0
1970 | MALDAH | Malda Mechanical | BHADAR Piped Water Supply Scheme , SM/12768 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Bhadar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014278) | 3340/MLMD | 30/10/2023 | 180 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 25.45 | 0 | 0 | 93
1971 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme , SM/12768 | New | Material Requisition To Resource Division | 26/MD | 04/01/2024 | 0 | Resource Division | 12.71 | 0 | 0 | 0
1972 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme , SM/12768 | New | Service Connection charge at P/H No. II of Bhadar Water Supply Scheme under Gazole C.C.C. in the district of Malda. | BP-2023-24-404 | 26/12/2023 | 0 | WBSEDCL | 11.36 | 0 | 0 | 0
1973 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme , SM/12768 | New | Laying of Distribution Sysytem and Providing Functional Household Tap Connection (FHTC) of BHADAR Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2928/MD | 10/06/2024 | 386 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 55.17 | 0 | 0 | 50
1974 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme , SM/12768 | New | Formal work order for the work of Implementation of BHADAR Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1996/MD | 17/05/2023 | 715 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 336.77 | 0 | 0 | 85
1975 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme , SM/12768 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of BHADAR Piped Water Supply Scheme at Gaole Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 2332/MD | 08/06/2023 | 571 | M/S KUNDU CONSTRUCTION | 87.98 | 0 | 0 | 90
1976 | MALDAH | Malda Division | BHADAR Piped Water Supply Scheme , SM/12768 | New | Construction of Boundary Wall at Head Work site of Bhadar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 269/MD | 11/01/2024 | 182 | MOONLIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 22.49 | 0 | 0 | 80
1977 | MALDAH | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme , SM/12764 | New | Material Requisition To Resource Division | 1799/MD | 27/04/2023 | 0 | Resource Division | 42.87 | 0 | 0 | 0
1978 | MALDAH | Malda Mechanical | SRI CHANDRAPUR Piped Water Supply Scheme , SM/12764 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Sri Chandrapur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014411) | 2394/MLMD | 28/07/2023 | 180 | KAMAKHYA ENTERPRISE. | 26.58 | 0 | 0 | 85
1979 | MALDAH | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme , SM/12764 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Sri Chandrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 5923/MD | 26/11/2024 | 45 | M/S ALISA CONSTRUCTIION | 65.18 | 0 | 0 | 0
1980 | MALDAH | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme , SM/12764 | New | Construction of Boundary Wall at 2nd Tube Well site of Sri Chandrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 3951/MD | 07/08/2024 | 45 | M/S ALISA CONSTRUCTIION | 8.68 | 0 | 0 | 0
1981 | MALDAH | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme , SM/12764 | New | Material Requisition To Resource Division | 92/MD | 05/01/2024 | 0 | Resource Division | 12.32 | 0 | 0 | 0
1982 | MALDAH | Malda Mechanical | SRI CHANDRAPUR Piped Water Supply Scheme , SM/12764 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of SRI CHANDRAPUR PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-444 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.78 | 0 | 0 | 0
1983 | MALDAH | Malda Mechanical | SRI CHANDRAPUR Piped Water Supply Scheme , SM/12764 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of SRI CHANDRAPUR PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-445 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 10.15 | 0 | 0 | 0
1984 | MALDAH | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme , SM/12764 | New | Formal work order for the work of Implementation of SRI CHANDRAPUR Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1851/MD | 02/05/2023 | 700 | M/S ALISA CONSTRUCTIION | 389.77 | 0 | 0 | 65
1985 | MALDAH | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme , SM/12764 | New | Laying of Distribution of UPVC Pipeline of SRI CHANDRAPUR Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 4634/MD | 23/11/2023 | 686 | M/S TRILOCHAN CONSTRUCTION CO | 80.4 | 0 | 0 | 100
1986 | MALDAH | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme , SM/12764 | New | Construction of Boundary Wall at Head Work site of Sri Chandrapur Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. (3rd Call). | 2419/MD | 27/05/2025 | 45 | SAHA CONSTRUCTION | 27.27 | 0 | 0 | 0
1987 | MALDAH | Malda Division | SRI CHANDRAPUR Piped Water Supply Scheme , SM/12764 | New | Road Restoration and Laying of parallel/ dedicated pipe line for better functionality of Srichandrapur Water Supply Scheme under Harishchandrapur -I Block under Malda Division, PHE Dte. in the district of Malda. | 5921/MD | 26/11/2025 | 60 | KAUSHIK MAJUMDAR | 10.02 | 0 | 0 | 0
1988 | MALDAH | Malda Mechanical | Uttar Mahinagar Piped Water Supply Scheme , SM/12765 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Uttar Mahinagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004467221 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 4.05 | 0 | 0 | 100
1989 | MALDAH | Malda Mechanical | Uttar Mahinagar Piped Water Supply Scheme , SM/12765 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Uttar Mahinagar PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004467207 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 4 | 0 | 0 | 100
1990 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme , SM/12765 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 21.65 | 0 | 0 | 0
1991 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme , SM/12765 | New | Material Requisition To Resource Division | 241/MD | 10/01/2024 | 0 | Resource Division | 4.53 | 0 | 0 | 0
1992 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme , SM/12765 | New | Formal work order for Implementation of Uttar Mahinagar Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1252/MD | 22/03/2023 | 1249 | M/S DAS CONSTRUCTION | 239.41 | 0 | 0 | 70
1993 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme , SM/12765 | New | Construction of Boundary Wall at Head Work site of Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3226/MD | 28/06/2024 | 552 | M/S DAS CONSTRUCTION | 36.14 | 0 | 0 | 40
1994 | MALDAH | Malda Mechanical | Uttar Mahinagar Piped Water Supply Scheme , SM/12765 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Uttar Mahinagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | 2943/MLMD | 11/09/2024 | 322 | M/S SAJAHAN CHOWDHURY | 25.3 | 0 | 0 | 80
1995 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme , SM/12765 | New | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3211/MD | 27/06/2024 | 551 | M/S DAS CONSTRUCTION | 33.31 | 0 | 0 | 20
1996 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme , SM/12765 | New | Road cutting and road restoration at Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6207/MD | 09/12/2024 | 388 | M/S DAS CONSTRUCTION | 5.06 | 0 | 0 | 0
1997 | MALDAH | Malda Division | Uttar Mahinagar Piped Water Supply Scheme , SM/12765 | New | Providing Balance Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Uttar Mahinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 2891/MD | 17/06/2025 | 60 | M/S AMIT KUMAR GUPTA | 23.59 | 0 | 0 | 0
1998 | MALDAH | Malda Mechanical | OLTARA PIPED WATER SUPPLY SCHEME. , SM/13718 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of OLTARA, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004508478 | 05/12/2023 | 90 | W.B.S.E.D.C.LTD | 9.14 | 0 | 0 | 100
1999 | MALDAH | Malda Division | OLTARA PIPED WATER SUPPLY SCHEME. , SM/13718 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 50.37 | 0 | 0 | 0
2000 | MALDAH | Malda Division | OLTARA PIPED WATER SUPPLY SCHEME. , SM/13718 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 90m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Oltara Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte in the District of Malda. | 2991/MD | 11/06/2024 | 180 | M/S JHA CONSTRUCTION | 32.88 | 0 | 0 | 0
2001 | MALDAH | Malda Division | OLTARA PIPED WATER SUPPLY SCHEME. , SM/13718 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Oltara Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 6405/MD | 19/12/2024 | 45 | M/S JHA CONSTRUCTION | 65.17 | 0 | 0 | 0
2002 | MALDAH | Malda Mechanical | OLTARA PIPED WATER SUPPLY SCHEME. , SM/13718 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of OLTARA, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-419A | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 0.01 | 0 | 0 | 0
2003 | MALDAH | Malda Mechanical | OLTARA PIPED WATER SUPPLY SCHEME. , SM/13718 | New | QUOTATION PAYMENT FOR OLTARA PH3 UNDER AIHO CCC UNDER MALDA DISTRICT | BP-2023-24-586 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 12.19 | 0 | 0 | 0
2004 | MALDAH | Malda Mechanical | OLTARA PIPED WATER SUPPLY SCHEME. , SM/13718 | New | QUOTATION PAYMENT FOR OLTARA PH 2 UNDER AIHO CCC UNDER DISTRICT OF MALDA | BP-2023-24-585 | 22/02/2024 | 0 | W.B.S.E.D.C.LTD | 12.93 | 0 | 0 | 0
2005 | MALDAH | Malda Division | OLTARA PIPED WATER SUPPLY SCHEME. , SM/13718 | New | Formal work order for Implementation of OLTARA Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1253/MD | 22/03/2023 | 943 | DUTTA ENTERPRISE | 919.78 | 0 | 0 | 85
2006 | MALDAH | Malda Mechanical | OLTARA PIPED WATER SUPPLY SCHEME. , SM/13718 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Oltara Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013242) | 2396/MLMD | 28/07/2023 | 883 | PROGRESSIVE ENG'S CO-OP. SOCIETY LTD | 43.33 | 0 | 0 | 60
2007 | MALDAH | Malda Division | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda , SM/12762 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for BHABUK Piped Water Supply Scheme at Habibpur Dev. Block in the District of Malda under Malda Division, PHE Dte. | 2984/MD | 07/12/2022 | 45 | SOVON KUMAR DAS | 43.65 | 0 | 0 | 1
2008 | MALDAH | Malda Division | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda , SM/12762 | Augmentation | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (135 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at BHABUK Piped Water Supply Scheme (Tube Well No-3) of Habibpur Block of Malda District under Malda Division, PHE Dte. | 2705/MD | 17/11/2022 | 30 | A. L. ENGINEERING SOLUTION | 9.14 | 0 | 0 | 100
2009 | MALDAH | Malda Division | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda , SM/12762 | Augmentation | Acceptance cum formal work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/11/2022 to 30/04/2023). | 2474/MD | 21/10/2022 | 365 | SHABNAM ARA | 4.5 | 0 | 0 | 21
2010 | MALDAH | Malda Division | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda , SM/12762 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Bhabuk Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | 1201/MD | 21/03/2023 | 45 | M.S. ENTERPRISE | 4.17 | 0 | 0 | 100
2011 | MALDAH | Malda Mechanical | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda , SM/12762 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Bhabuk, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-420 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 6.71 | 0 | 0 | 0
2012 | MALDAH | Malda Division | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda , SM/12762 | Augmentation | Emergent Laying of different diameter UPVC Pipeline and others allied work for Gap negotiatiomn for BHABUK its adjoining mouzas Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 805/MD | 21/02/2024 | 663 | GOBINDA ENTERPRISE | 12.33 | 0 | 0 | 0
2013 | MALDAH | Malda Division | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda , SM/12762 | Augmentation | Construction of Boundary Wall at 3rd Tube well site of Bhabuk Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 5000/MD | 27/09/2024 | 385 | M/S KUNDU CONSTRUCTION | 18.34 | 0 | 0 | 0
2014 | MALDAH | Malda Division | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda , SM/12762 | Augmentation | Augmentation of work to ensure proper functioning of 250 M³ Capacity 20 Mtr. Staging height RCC Over Head Reservoir of Bhabuk Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1061/MD | 19/03/2025 | 60 | SADHANA CONSTRUCTION | 9.21 | 0 | 0 | 0
2015 | MALDAH | Malda Division | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda , SM/12762 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 25 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Bhabuk Water Supply Scheme of Habibpur Dev. Block under Malda Division P.H.E Dte in the District of Malda. | 2620/MD | 02/06/2025 | 135 | M/S AMIT KUMAR GUPTA | 15.55 | 0 | 0 | 0
2016 | MALDAH | Malda Mechanical | Source Augmentation of Bhabuk Water Supply Scheme of Habibpur Block under Malda Division P.H.E Dte. Malda , SM/12762 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Bhabuk Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014864) | 2311/MLMD | 26/07/2023 | 585 | SUBRATA KUMAR DAS. | 10.52 | 0 | 0 | 70
2017 | MALDAH | Malda Division | UTTAR BHAKURIA Piped Water Supply Scheme. , SM/12881 | New | Material Requisition To Resource Division | 1615/MD | 11/04/2023 | 0 | Resource Division | 1.32 | 0 | 0 | 0
2018 | MALDAH | Malda Mechanical | UTTAR BHAKURIA Piped Water Supply Scheme. , SM/12881 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Uttar Bhakuria Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013230) | 2397/MLMD | 28/07/2023 | 180 | JIBU SINGHA | 12.27 | 0 | 0 | 81
2019 | MALDAH | Malda Mechanical | UTTAR BHAKURIA Piped Water Supply Scheme. , SM/12881 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of UTTAR BHAKURIA PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-446 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 4.22 | 0 | 0 | 0
2020 | MALDAH | Malda Division | UTTAR BHAKURIA Piped Water Supply Scheme. , SM/12881 | New | Acceptance cum formal work order for Implementation of UTTAR BHAKURIA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | 196/MD | 19/01/2023 | 591 | M/S SABANA CONSTRUCTION | 39.58 | 0 | 0 | 90
2021 | MALDAH | Malda Division | UTTAR BHAKURIA Piped Water Supply Scheme. , SM/12881 | New | Construction of Boundary Wall at Uttar Bhakuria Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 3202/MD | 27/06/2024 | 30 | M/S SABANA CONSTRUCTION | 10.34 | 0 | 0 | 100
2022 | MALDAH | Malda Division | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15112 | Augmentation | Acceptance cum formal work order for Laying of additional UPVC Pipe line in connection with Source Augmentation of Sadlichak Piped Water Supply Scheme at Harishchandrapur II Block, under Malda Division, P.H.E. Dte. in the District of Malda. | 765/MD | 17/02/2023 | 30 | RABIUL ISLAM | 6.89 | 0 | 0 | 0
2023 | MALDAH | Malda Division | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15112 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Sadlichak Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | 1302/MD | 23/03/2023 | 45 | SOFIKUL ISLAM | 4.19 | 0 | 0 | 0
2024 | MALDAH | Malda Mechanical | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15112 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Sadlichak Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016501) | 2630/MLMD | 10/08/2023 | 1021 | FUTURE | 11.43 | 0 | 0 | 80
2025 | MALDAH | Malda Division | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15112 | Augmentation | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Sadlichalk Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2900/MD | 07/06/2024 | 30 | SAYEM ENTERPRISE | 2.12 | 0 | 0 | 0
2026 | MALDAH | Malda Division | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15112 | Augmentation | Augmentation work of OHR, Pump House and Boundary Wall of Sadlichak Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 999/MD | 12/03/2025 | 75 | SUBHAS CHANDRA KESHARI | 28.01 | 0 | 0 | 0
2027 | MALDAH | Malda Division | Source Augmentation of Sadlichak Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15112 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 246 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of SADLICHAK Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | 1178/MD | 20/03/2023 | 686 | JAYA ENTERPRISE | 12.03 | 0 | 0 | 95
2028 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme , SM/06853 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme at Englishbazar Block under Malda Division, PHE Dte. | 2719/MD | 10/11/2020 | 30 | MANAS KUMAR SAHA | 50.07 | 0 | 0 | 1
2029 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme , SM/06853 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Anandipur Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | 702/MD | 21/02/2025 | 320 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28.05 | 0 | 0 | 0
2030 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of ANANDIPUR Water Supply Scheme , SM/06853 | Retrofitting | Augmentation work of Boundary wall, Pump House, Blower Room,Over Head Reservoir and Construction Pathway & Approach Road at Head Work Site of ANANDIPUR Water Supply Scheme of Englishbazar Block under Malda Division, P.H.E.Dte. in the District of Malda | 2414/MD | 27/05/2025 | 75 | M/S GHOSH CONSTRUCTION | 20.21 | 0 | 0 | 0
2031 | MALDAH | Malda Division | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15062 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Rampur Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte. | 1301/MD | 23/03/2023 | 45 | SUBINDU PRAMANIK | 4.19 | 0 | 0 | 0
2032 | MALDAH | Malda Division | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15062 | Augmentation | Acceptance cum formal work order for Laying of additional UPVC Pipe line in connection with Source Augmentation of Rampur Piped Water Supply Scheme, Chanchal II Block under Malda Division, P.H.E. Dte. in the District of Malda | 764/MD | 17/02/2023 | 30 | PACIFIC ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 18.18 | 0 | 0 | 100
2033 | MALDAH | Malda Division | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15062 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well ( 250.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at Rampur Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | 1397/MD | 28/03/2023 | 30 | A. L. ENGINEERING SOLUTION | 13.37 | 0 | 0 | 100
2034 | MALDAH | Malda Mechanical | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15062 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Rampur Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte. (TSM/016552) | 2626/MLMD | 10/08/2023 | 836 | JIBON GHOSH. | 11.42 | 0 | 0 | 88
2035 | MALDAH | Malda Division | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15062 | Augmentation | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Rampur Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 5619/MD | 06/11/2024 | 30 | M/S JHA CONSTRUCTION | 2.88 | 0 | 0 | 0
2036 | MALDAH | Malda Division | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15062 | Augmentation | Replacement of existing tube well by 200x200 mm dia. and 250 M Deep by Big Dia Tube Well at 2nd Tube Well site of Rampur Piped Water Supply Scheme at Chanchal-II block of Malda District under Malda Division, PHE Dte. | 4820/MD | 13/09/2024 | 92 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 13.75 | 0 | 0 | 100
2037 | MALDAH | Malda Division | Source Augmentation of Rampur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15062 | Augmentation | Augmentation work of OHR, Pump House and Boundary Wall of Rampur Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2894/MD | 17/06/2025 | 60 | S. N. CONSTRUCTION | 29.67 | 0 | 0 | 0
2038 | MALDAH | Malda Division | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15083 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 138 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of BIHARI Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | 1434/MD | 29/03/2023 | 30 | ABHIJIT PAUL | 8.68 | 0 | 0 | 0
2039 | MALDAH | Malda Division | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15083 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Bihari Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte. | 1195/MD | 21/03/2023 | 45 | M/S MAJAF CONSTRUCTION | 4.17 | 0 | 0 | 0
2040 | MALDAH | Malda Division | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15083 | Augmentation | Acceptance cum formal work order for Laying of Distribution pipe line for Functional Household Tap Connection in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Rampur village of Bihari Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. | 749/MD | 17/02/2023 | 30 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 5.67 | 0 | 0 | 100
2041 | MALDAH | Malda Mechanical | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15083 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Behari Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016679) | 2618/MLMD | 10/08/2023 | 180 | NEOGI ENTERPRISE. | 10.92 | 0 | 0 | 56
2042 | MALDAH | Malda Division | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15083 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bihari Zone-I Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 2422/MD | 27/05/2025 | 60 | PRADIP KUMAR BANIK | 15.71 | 0 | 0 | 0
2043 | MALDAH | Malda Division | Source Augmentation of Bihari Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15083 | Augmentation | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Bihari Zone-II Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 2332/MD | 22/05/2025 | 60 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 29.11 | 0 | 0 | 0
2044 | MALDAH | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme , SM/14190 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 9.73 | 0 | 0 | 0
2045 | MALDAH | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme , SM/14190 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 10.86 | 0 | 0 | 0
2046 | MALDAH | Malda Mechanical | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme , SM/14190 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. II of Augmentation of Jotgopal Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008179) | 2220/MLMD | 18/07/2023 | 90 | TAPAN BISWAS. | 12.3 | 0 | 0 | 40
2047 | MALDAH | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme , SM/14190 | Augmentation | Formal work order for the work of Augmentation of JOTGOPAL Piped Water Supply Scheme at Englishbazar Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2710/MD | 14/07/2023 | 270 | SHREE BISHNU CONSTRUCTION | 192.85 | 0 | 0 | 32
2048 | MALDAH | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme , SM/14190 | Augmentation | Construction of Boundary Wall at head work site of Jotgopal Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | 2988/MD | 11/06/2024 | 30 | SHREE BISHNU CONSTRUCTION | 24.3 | 0 | 0 | 0
2049 | MALDAH | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme , SM/14190 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site. of JOTGOPAL Water Supply Scheme at Englishbazar Block of Malda District under Malda Division, PHE Dte. | 1132/MD | 20/03/2023 | 45 | S. R. ENTERPRISE | 4.14 | 0 | 0 | 100
2050 | MALDAH | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme , SM/14190 | Augmentation | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 95m Deep at Jotegopal PWSS under Englishbazar Block under Malda Division, PHE Dte, Govt. of West Bengal. | 3199/MD | 27/06/2024 | 45 | ABHIJIT PAUL | 8.36 | 0 | 0 | 100
2051 | MALDAH | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme , SM/14190 | Augmentation | Material Requisition To Resource Division | 822/MD | 21/02/2024 | 0 | Resource Division | 7.67 | 0 | 0 | 0
2052 | MALDAH | Malda Mechanical | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme , SM/14190 | Augmentation | Quotation Payment against Jote Gopal JL NO-49 Under Fulbari ccc Under Malda District | BP-2023-24-626 | 04/03/2024 | 0 | W.B.S.E.D.C.LTD | 3.54 | 0 | 0 | 0
2053 | MALDAH | Malda Mechanical | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme , SM/14190 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Augmentation of Jotgopal Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008179) | 2261/MLMD | 18/07/2023 | 831 | SUBRATA KUMAR DAS. | 13.48 | 0 | 0 | 100
2054 | MALDAH | Malda Division | AUGMENTATION OF JOTGOPAL Piped Water Supply Scheme , SM/14190 | Augmentation | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, RWS Malda Sub-Division Division, PHE Dte. (Car-2) (Period from 01/01/2025 to 30/06/2025). | 6637/MD | 31/12/2024 | 181 | RUQAIYA ENTERPRISE | 0.86 | 0 | 0 | 0
2055 | MALDAH | Malda Ars Area W/S Division | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Talimnagar & Adjoining mouzas water supply schemes under Malda Arsenic area water supply Division, PHED , SM/15145 | Augmentation | Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 25.00 M³/ Hr. capacity Iron Elimination Plant (Pressure type) for Talimnagar Water Supply Scheme at Manikchak Dev. Block under Malda Arsenic Area Water Supply Division, PHE Dte. in the district of Malda. | 400/MAAD | 06/03/2023 | 180 | MANASH KUMAR SAHA | 16.01 | 0 | 0 | 81
2056 | MALDAH | Malda Ars Area W/S Division | Improvement of Ground water Based piped water supply scheme by Installation of Arsenic /Iron Removal plant for Talimnagar & Adjoining mouzas water supply schemes under Malda Arsenic area water supply Division, PHED , SM/15145 | Augmentation | Construction of Boundary wall including RBT fencing at arround Talimnagar Zone-I Pump house No.1 under Malda Arsenic Area Water supply Divisin PHED. | 943/MAAD | 23/05/2023 | 45 | MI CONSTRUCTION | 8.91 | 0 | 0 | 100
2057 | MALDAH | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED , SM/15140 | New | Laying of Distribution System including Supply of all type of specials & valves at Saidpur Muslim Para under Purba Saidpur Piped Water Supply Scheme, Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 865/MAAD | 04/05/2023 | 60 | ABHIJIT ENTERPRISE | 9.75 | 0 | 0 | 100
2058 | MALDAH | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED , SM/15140 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at 1st Tube well Site Purbba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 866/MAAD | 04/05/2023 | 45 | M/S DYNAMIC CONSTRUCTION | 7.47 | 0 | 0 | 100
2059 | MALDAH | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED , SM/15140 | New | Material Requisition To Resource Division | 634/MAAD | 05/04/2023 | 0 | Resource Division | 24.86 | 0 | 0 | 0
2060 | MALDAH | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED , SM/15140 | New | Laying of Distribution System including Supply of all type of specials & valves at Saidpur Bazar Para under Purba Saidpur Piped Water Supply Scheme, Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 864/MAAD | 04/05/2023 | 60 | CHARU CONSTRUCTION | 13.56 | 0 | 0 | 100
2061 | MALDAH | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED , SM/15140 | New | Sinking of 250mm. Dia. x 150mm. big dia. Tube Well of 102 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs at Purbha Saidpur Piped Water supply scheme (2nd Tube Well Site) at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. in the District of Malda. (2nd call) | 1916/MAAD | 16/10/2023 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 6.2 | 0 | 0 | 100
2062 | MALDAH | Malda Mechanical | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED , SM/15140 | New | Quotation Payment For Purbasaidpur T/W NO 1 Under The District Of Malda Under Mathurapur CCC | BP-2024-25-43 | 08/04/2024 | 0 | W.B.S.E.D.C.LTD | 5.08 | 0 | 0 | 0
2063 | MALDAH | Malda Mechanical | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED , SM/15140 | New | Quotation Payment For Purbasaidpur T/W NO II For district of Malda Under Mathurapur CCC | BP-2023-24-731 | 28/03/2024 | 0 | W.B.S.E.D.C.LTD | 4.54 | 0 | 0 | 0
2064 | MALDAH | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED , SM/15140 | New | Laying of Distribution System including Supply of all type of specials & valves from Node point at Bhakta Ballavpur (71) mouza under Purbba Saidpur Piped Water Supply Scheme, Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. (2nd Call) | 944/MAAD | 23/05/2023 | 60 | ANJIMA CONSTRUCTION CO. | 25.48 | 0 | 0 | 50
2065 | MALDAH | Malda Mechanical | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED , SM/15140 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I & II and Arsenic Iron Removal Plant at Purba Saidpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/018015) | 2684/MLMD | 11/08/2023 | 843 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 65.01 | 0 | 0 | 98
2066 | MALDAH | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED , SM/15140 | New | Construction of 400 M3 Capacity, 20mtr. staging height RCC Elevated Service Reservoir as per Departmental type design including delivery, inlet & overflow pipe connection etc. all complete for piped water supply scheme at Purba Saidpur Piped Water Supply Scheme & its adjoining mouzas of Manikchak Block in the District of Malda, under Malda Arsenic Area W/S Division, PHE Dte. | 2002/MAAD | 06/11/2023 | 660 | M/S KUNDU CONSTRUCTION | 187.22 | 0 | 0 | 20
2067 | MALDAH | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED , SM/15140 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) at Purba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 3017/MAAD | 06/12/2023 | 665 | ZEOLITE FRESH INDIA | 150.68 | 0 | 0 | 5
2068 | MALDAH | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED , SM/15140 | New | Laying of Distribution System including Supply of all type of specials & valves at Maszid Para under Purba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. In the District of Malda. | 882/MAAD | 11/05/2023 | 298 | SUDIP DEY | 53.75 | 0 | 0 | 10
2069 | MALDAH | Malda Ars Area W/S Division | Purbha Saidpur mouza piped water supply Scheme of Manikchak block under Malda Arsenic Area Water Supply Division, PHED , SM/15140 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site at Purbba Saidpur Piped Water Supply Scheme of Manikchak Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 1480/MAAD | 01/08/2023 | 60 | MAHA MAYA CONSTRUCTION | 5.09 | 0 | 0 | 80
2070 | MALDAH | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme , SM/16383 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 10.94 | 0 | 0 | 0
2071 | MALDAH | Malda Mechanical | Augmentation of Mahishbathani Piped Water Supply Scheme , SM/16383 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III & IV and making compound lighting arrangement at head worksite of Augmentation of Mahishbathani Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017802) | 2692/MLMD | 11/08/2023 | 180 | MOON LIGHT CONSTRUCTION AND STAR GOLD ENTERPRISE | 27.01 | 0 | 0 | 81
2072 | MALDAH | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme , SM/16383 | Augmentation | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/07/2023 to 31/12/2023). | 503/MSD | 30/06/2023 | 180 | ARUN KUMAR DAS | 0.86 | 0 | 0 | 100
2073 | MALDAH | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme , SM/16383 | Augmentation | Road restoration in connection with dismantling of road and renovation the same with balanced allied work to provide FHTC at Maheshbathani Piped Water Supply Scheme under Old Malda Dev Block under Malda Division, P.H.E Dte. | 2471/MD | 28/05/2025 | 45 | M/S DAS CONSTRUCTION | 11.92 | 0 | 0 | 100
2074 | MALDAH | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme , SM/16383 | Augmentation | Acceptance cum formal work order for Sinking of Tubewell, Laying of Distribution System and Providing Functional Household Tap connection (FHTC) of Mahishbathani Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2005/MD | 17/05/2023 | 565 | M/S DAS CONSTRUCTION | 92.6 | 0 | 0 | 50
2075 | MALDAH | Malda Division | Augmentation of Mahishbathani Piped Water Supply Scheme , SM/16383 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Head Work Site of Mahishbathani Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 653/MD | 08/02/2024 | 45 | M/S DAS CONSTRUCTION | 4.15 | 0 | 0 | 100
2076 | MALDAH | Malda Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT , SM/18686 | New | Formal Work Order for Providing Mechanical/Electrical equipment along with all related work at Boosting Pumping Station and Substation for RATUA-II block under Surface water based PWSS of Ratua-I, Ratua-II & Chanchal-II block, Dist. Malda, PHE Dte. | 2668/MLMD | 10/08/2023 | 365 | ORIENTAL ENGINEERING CO. | 602.03 | 0 | 0 | 0
2077 | MALDAH | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT , SM/18686 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 12067.76 | 0 | 0 | 0
2078 | MALDAH | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT , SM/18686 | New | Material Requisition To Resource Division | 5971/MD | 28/11/2024 | 0 | Resource Division | 345.26 | 0 | 0 | 0
2079 | MALDAH | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT , SM/18686 | New | Material Requisition To Resource Division | 3836/MD | 30/07/2024 | 0 | Resource Division | 7172.16 | 0 | 0 | 0
2080 | MALDAH | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT , SM/18686 | New | Harvesting and disposal of 36 number of trees at Ratua-I for Surface water based piped water supply scheme of Chanchal-II, Ratua-I and Ratua -II block of Malda District. | BP-2024-25-253 | 11/09/2024 | 0 | EXECUTIVE ENGINEER | 1.29 | 0 | 0 | 0
2081 | MALDAH | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT , SM/18686 | New | Surveying, Planning, Design, Engineering, Supplying, Construction, Erection, Testing and Commissioning of Raw water Intake and Raw Water Pumping Main, WTP , Primary and Secondary Clear Water Transmission main, Boosting stations and other allied works including all Civil , Electro-Mechanical and IOT based Supervisory monitoring system for Surface water based piped water supply scheme of Chanchal-II, Ratua-I and Ratua -II block of Malda District followed by 3(Three) months Trial Run and Subsequent Operation & Maintenance for 5(five) years | BP-2024-25-223 | 28/08/2024 | 0 | EXECUTIVE ENGINEER | 1.35 | 0 | 0 | 0
2082 | MALDAH | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT , SM/18686 | New | Harvesting and disposal of 36 number of trees at Ratua-I for Surface water based piped water supply scheme of Chanchal-II, Ratua-I and Ratua -II block of Malda District. | BP-2024-25-386 | 19/11/2024 | 0 | EXECUTIVE ENGINEER | 1.29 | 0 | 0 | 0
2083 | MALDAH | Malda Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT , SM/18686 | New | Shifting of LVOH(Low voltage over head) Line at jannagar WTP site under surface based PWSS of Ratua-I , II & Chanchal - II Block Dist- Malda,PHE Dte. | BP-2024-25-295 | 05/06/2024 | 0 | W.B.S.E.D.C.LTD | 3.41 | 0 | 0 | 0
2084 | MALDAH | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT , SM/18686 | New | Formal work order for the work of Construction of Overhead Reservoir on pile or raft foundation based on soil test report, laying of Distribution system, FHTC including pump house, boundary wall, internal road with RCC Culvert, internal pipe connection of Surface Water Based Piped Water Supply Scheme for Chanchal-II, Ratua-I & Ratua-II Block in the district of Malda Under Malda Division, PHE Dte. | 3155/MD | 16/08/2023 | 960 | REAN WATER TECH PRIVATE LIMITED. | 10818.5 | 0 | 0 | 5
2085 | MALDAH | Malda Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT , SM/18686 | New | Providing Mechanical/Electrical equipment along with all related work at Boosting Pumping Station and Substation for RATUA-I block under Surface water based PWSS of Ratua-I, Ratua-II & Chanchal-II block, Dist. Malda, PHE Dte. | 2670/MLMD | 10/08/2023 | 729 | WEST BENGAL ENGINEERING COMPANY. | 628.87 | 0 | 0 | 64
2086 | MALDAH | Malda Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT , SM/18686 | New | Formal Work Order for Providing Mechanical/Electrical equipment along with all related work at Boosting Pumping Station and Substation for Chanchal-II block under Surface water based PWSS of Ratua-I, Ratua-II & Chanchal-II block, Dist. Malda, PHE Dte. | 2666/MLMD | 10/08/2023 | 1086 | DAS ENTERPRISE. | 603.82 | 0 | 0 | 4
2087 | MALDAH | Malda Division | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CHANCHAL-II, RATUA-I & RATUA-II BLOCK OF MALDA DISTRICT , SM/18686 | New | Construction of Flexible Bitumen Roads from Nakkatti Bridge to Y Junction of Irrigation Embankment by Bituminous work under Malda Division PHE Dte, in the District of Malda during the year 2024 - 2025. | 6161/MD | 05/12/2024 | 220 | M/S ANKUSH ENTERPRISE | 64.08 | 0 | 0 | 65
2088 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme , SM/06855 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | 2464/MD | 12/10/2020 | 30 | UTTAM KUMAR GHOSH | 57.92 | 0 | 0 | 0
2089 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme , SM/06855 | Retrofitting | Material Requisition To Resource Division | 3919/MD | 06/08/2024 | 0 | Resource Division | 4 | 0 | 0 | 0
2090 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme , SM/06855 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Bakhra Water Supply Scheme under Ratua-I Block under Malda Division, PHE Dte. in the district of Malda. | 58 | 08/01/2025 | 45 | M/S N. N. ENTERPRISE | 28.26 | 0 | 0 | 0
2091 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BAKHRA Water Supply Scheme , SM/06855 | Retrofitting | Laying of Parallel/ Dedicated Pipeline, Providing Common Manifold & providing Balance FHTC for better Functionality at Bakhra Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 4235/MD | 29/08/2025 | 60 | M/S N. N. ENTERPRISE | 32.31 | 0 | 0 | 0
2092 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOBINDAPUR Water Supply Scheme , SM/06860 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of GOBINDAPUR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | 2262/MD | 29/09/2020 | 45 | UTTAM KUMAR DUTTA | 60.07 | 48.7 | 79.76 | 1
2093 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOBINDAPUR Water Supply Scheme , SM/06860 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gobindapur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3198/MD | 27/06/2024 | 476 | ANJIMA CONSTRUCTION CO. | 10.56 | 0 | 0 | 0
2094 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme , SM/06861 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOUR HANDA Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | 2721/MD | 10/11/2020 | 45 | SUBHAS CHANDRA KESHARI | 74.49 | 22.71 | 100 | 0
2095 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme , SM/06861 | Retrofitting | Material Requisition To Resource Division | 3922/MD | 06/08/2024 | 0 | Resource Division | 8.62 | 0 | 0 | 0
2096 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme , SM/06861 | Retrofitting | Erection of Property board related to Jal Jeevan Mission works of Gourhanda & Jalalpur GP under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | 635/MD | 19/02/2025 | 7 | BIDYUT MAHALDAR | 0.9 | 0 | 0 | 0
2097 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme , SM/06861 | Retrofitting | Augmentation work of OHR, Pump House and Boundary Wall of Gourhanda Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1043/MD | 18/03/2025 | 75 | MATIUR RAHAMAN | 32.5 | 0 | 0 | 0
2098 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of GOURHANDA Water Supply Scheme , SM/06861 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and Laying of Distribution Pipeline in connection with Jal Jeevan Mission (JJM) at Gourhanda Water Supply Scheme under Chanchal-II Block under Malda Division, PHE Dte. in the district of Malda. | 2876/MD | 17/06/2025 | 60 | M/S KUNDU CONSTRUCTION | 60.09 | 0 | 0 | 0
2099 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KADIRPUR Water Supply Scheme , SM/06864 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KADIRPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 1964/MD | 31/08/2020 | 30 | M/S KUNDU CONSTRUCTION | 39.43 | 39 | 100 | 1
2100 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KADIRPUR Water Supply Scheme , SM/06864 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of KADIRPUR Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 4768/MD | 05/12/2023 | 45 | M/S SINHA ENTERPRISE | 16.09 | 0 | 0 | 100
2101 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme , SM/06872 | Retrofitting | Testing of HDPE pipe 20 mm as per IS 4984:2016 reg. | 44 | 07/05/2021 | 0 | CIPET EXTN CENTRE | 0.22 | 0 | 0 | 0
2102 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme , SM/06872 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme at Harishchandrapur-II Block under Malda Division, PHE Dte. | 2436/MD | 12/10/2020 | 120 | M/S TRILOCHAN CONSTRUCTION CO | 12 | 0 | 0 | 1
2103 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme , SM/06872 | Retrofitting | Formal work order for Providing house connection under RANGHAT Water Supply Scheme at Chanchal-II Block under Malda Division, PHE Dte. | 2038/MD | 10/09/2020 | 120 | PROJECT INDIA | 94.64 | 0 | 0 | 100
2104 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme , SM/06872 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of KHANPUR HULASPUR Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, PHE Dte. | 48/1/MD | 13/01/2022 | 30 | BIDYUT MAHALDAR | 0.39 | 0 | 0 | 100
2105 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of TALBANGURA Water Supply Scheme , SM/06872 | Retrofitting | Sinking of 01 (One) Nos. 250mm. Dia. x 200 mm. Big dia. Tube Well 131 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with 2nd Tube Well Site at Talbangura Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda. | 464/DW | 25/09/2024 | 0 | A. L. ENGINEERING SOLUTION | 3.98 | 0 | 0 | 0
2106 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09593 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Baliadanga Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Baliadanga) | 1733/MAAD | 24/11/2021 | 60 | M/S MOON LIGHT CONSTRUCTION & CO. | 44.98 | 0 | 0 | 1
2107 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09593 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Baliadanga Water Supply Scheme (Mouza- Silampur, Maheshpur) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte | 1015/MAAD | 12/05/2022 | 60 | M/S ALISA CONSTRUCTION | 82.93 | 0 | 0 | 1
2108 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09593 | Retrofitting | Laying of 20mm dia HDPE pipe at Mouza: -Baliadanga, Khaschandpur, Silampur Habitations: - Baliadanga, Gharialichak, Kaliachak, Alipur, Kalikapur for installation of FHTC under Baliadanga distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1448/MAAD | 29/07/2022 | 30 | M/S MOON LIGHT CONSTRUCTION & CO. | 3.89 | 0 | 0 | 1
2109 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09593 | Retrofitting | Laying of 90 mm dia uPVC Pipe line at Hajinagar, Meheruddin Munsi Tola & Saifuddin Sardar Tola for installation of FHTC under Baliadanga distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1173/MAAD | 13/06/2022 | 45 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.82 | 0 | 0 | 1
2110 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09593 | Retrofitting | Laying of 75 mm dia uPVC Pipe line at Sonar Para, Thana Para, Namopara, Harkatola & Maksod Tola for installation of FHTC under Baliadanga distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1172/MAAD | 13/06/2022 | 45 | M/S MOON LIGHT CONSTRUCTION & CO. | 4.76 | 0 | 0 | 1
2111 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09593 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Baliadanga Water Supply Scheme (Mouza- Kaliachak, Habitation- Puratun Babur Hat) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1831MAAD | 27/09/2022 | 45 | THREE BROTHERS CONSTRUCTION & CO. | 3.8 | 0 | 0 | 1
2112 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09593 | Retrofitting | Laying of 200 mm, 90 mm dia UPVC Pipe line and Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Rishi Para, Ghosh Para under Baliadanga distribution Zone of Southern sector under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 321/MAAD | 21/02/2023 | 60 | THREE BROTHERS CONSTRUCTION & CO. | 18.91 | 0 | 0 | 100
2113 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09593 | Retrofitting | Laying of 20mm dia HDPE pipe at Nayagram, Silampur & Bahanna Bigha for installation of FHTC under Baliadanga distribution Zone of Southern Sector under Malda Arsenic Area W/S Division, PHE Dte | 881/MAAD | 11/05/2023 | 30 | M/S ALISA CONSTRUCTION | 7.8 | 0 | 0 | 100
2114 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09593 | Retrofitting | Material Requisition To Resource Division | 1789/MAAD | 26/11/2021 | 0 | Resource Division | 66.42 | 0 | 0 | 0
2115 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09593 | Retrofitting | Material Requisition To Resource Division | 1334/MAAD | 18/07/2022 | 0 | Resource Division | 12.3 | 0 | 0 | 0
2116 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09593 | Retrofitting | Material Requisition To Resource Division | 1699/MAAD21 | 21/09/2022 | 0 | Resource Division | 6.05 | 0 | 0 | 0
2117 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Baliadanga Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-I Bl , SM/09593 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
2118 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kumvira Water Supply Scheme(Habitation Nurnagar, Bakhtarband, Sabdulpur, Sukdebpur, Harinagar, Niyoginagar, Mohanpur Khas, Mohanpur) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1739/MAAD | 24/11/2021 | 60 | M/S AMIT KUMAR GUPTA | 59.9 | 0 | 0 | 1
2119 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of UPVC pipe 200mm,160mm,125mm&110mm dia at Sukpara& others Allied works at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 395/MAAD | 08/03/2022 | 45 | DEY CONSTRUCTION | 30.43 | 0 | 0 | 1
2120 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of UPVC pipe 90mm dia at Mahonpur & others Allied works at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 346/MAAD | 07/03/2022 | 45 | ABHIJIT CONSTRUCTION | 3.78 | 0 | 0 | 1
2121 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of UPVC pipe 90mm dia at Manoj Master para & others Allied works at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 347/MAAD | 07/03/2022 | 45 | MAHA MAYA CONSTRUCTION | 3.61 | 0 | 0 | 1
2122 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Kumvira Water Supply Scheme(Habitation-Sukpara,Kumvira&Hatatpara) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 821/MAAD | 28/04/2022 | 60 | FUTURE | 76.04 | 0 | 0 | 1
2123 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Nurnagar under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1151/MAAD | 13/06/2022 | 15 | M/S AMIT KUMAR GUPTA | 3.9 | 0 | 0 | 1
2124 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Bakrabad & Sabdalpur under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1152/MAAD | 13/06/2022 | 15 | M/S AMIT KUMAR GUPTA | 4.16 | 0 | 0 | 1
2125 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Sukdebpur under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1153/MAAD | 13/06/2022 | 15 | M/S AMIT KUMAR GUPTA | 4.04 | 0 | 0 | 1
2126 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Mohanpur khas & Mohanpur under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1155MAAD | 13/06/2022 | 15 | M/S AMIT KUMAR GUPTA | 3.9 | 0 | 0 | 1
2127 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Hadinagar & Neoginagar under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1154/MAAD | 13/06/2022 | 15 | M/S AMIT KUMAR GUPTA | 3.93 | 0 | 0 | 1
2128 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of UPVC Pipe Line of 90mm at Sabdalpur Jamaipara & Kubhira for under Kumbhira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1463/MAAD | 29/07/2022 | 45 | FUTURE | 3.06 | 0 | 0 | 1
2129 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of UPVC Pipe Line of 75 mm dia at Godhantola,Mahis Mandal para,Bakrabad char & Sukpara for under Kumbhira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1464/MAAD | 29/07/2022 | 45 | FUTURE | 4.71 | 0 | 0 | 1
2130 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Sabdalpur, Sukpara under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1837/MAAD | 27/09/2022 | 30 | FUTURE | 4.4 | 0 | 0 | 1
2131 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Mohanpur,Godhantola under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1838/MAAD | 27/09/2022 | 30 | FUTURE | 4.13 | 0 | 0 | 1
2132 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Khasmohanpur,Kumvira under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1836/MAAD | 27/09/2022 | 30 | FUTURE | 4.3 | 0 | 0 | 1
2133 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of HDPE pipe 20mm dia at Hatatpara,Ghospara under Kumvira water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1839MAAD | 27/09/2022 | 30 | FUTURE | 4.36 | 0 | 0 | 1
2134 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bamangram Water Supply Scheme at Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Jalalpur) | 1743/MAAD | 24/11/2021 | 30 | BEE GEE CONSTRUCTION | 70 | 0 | 0 | 1
2135 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Laying of UPVC pipe 140mm dia at Sabdalpur Guntola & others Allied works at Kumvira W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 1401/MAAD | 26/07/2022 | 45 | MAHA MAYA CONSTRUCTION | 8.18 | 0 | 0 | 1
2136 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Sabdalpur Guntola under command area of Kumvira Water Supply Scheme at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 2033/MAAD | 16/11/2022 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 9.35 | 0 | 0 | 1
2137 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | SUPPLY & DELIVERY OF DIFFERENT MATERIALS FOR THE DIFFERENT ON-GOING WATER SUPPLY SCHEME UNDER JJM WORKS. |  | 22/09/2023 | 0 | MALDA DISTRICT SERVICE CUM-MARKETING INDUSTRIAL CO-OPERATIVE UNION LTD. | 1.52 | 0 | 0 | 0
2138 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | SUPPLY OF OFFICE FURNITURE & OTHER STATIONERY ITEM FOR OFFICE USE STATIONERY ARTICLES FOR USE IN THE OFFICE OF THE EXECUTIVE ENGINEER, MALDA ARSENIC AREA W/S DIVISION, P.H.E. DTE. |  | 07/09/2023 | 0 | MALDA DISTRICT SERVICE CUM-MARKETING INDUSTRIAL CO-OPERATIVE UNION LTD. | 1.52 | 0 | 0 | 0
2139 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | SUPPLY OF OFFICE FURNITURE & OTHER STATIONERY ITEM FOR OFFICE USE STATIONERY ARTICLES FOR USE IN THE OFFICE OF THE EXECUTIVE ENGINEER, MALDA ARSENIC AREA W/S DIVISION, P.H.E. DTE. |  | 24/08/2023 | 0 | MALDA DISTRICT SERVICE CUM-MARKETING INDUSTRIAL CO-OPERATIVE UNION LTD. | 1.73 | 0 | 0 | 0
2140 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Kumvira Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III Blo , SM/09648 | Retrofitting | Continuation Work Order for Placing of diesel driven Car on hire basis for the official use of the Assistant Engineer-I, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte. (for the period from 01.01.2023 to 31.12.2023)= 365 days. | 2389/MAAD | 30/12/2022 | 133313 | SUBRATA SAHA | 1.73 | 0 | 0 | 60
2141 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mahadipur and Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in English Bazar , SM/09649 | Retrofitting | Laying of 90 mm dia uPVC Pipe line at Khirki Village for installation of FHTC under Mahadipur & Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1177/MAAD | 13/06/2022 | 45 | BANIK BROTHERS | 4.81 | 0 | 0 | 1
2142 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mahadipur and Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in English Bazar , SM/09649 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Mahadipur & Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Mouza- Mahadipur) | 1738/MAAD | 24/11/2021 | 60 | BANIK BROTHERS | 56.36 | 0 | 0 | 1
2143 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mahadipur and Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in English Bazar , SM/09649 | Retrofitting | Laying of 90 mm dia uPVC Pipe line at Mahadipur Village for installation of FHTC under Mahadipur & Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1176/MAAD | 13/06/2022 | 45 | BANIK BROTHERS | 4.8 | 0 | 0 | 1
2144 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mahadipur and Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in English Bazar , SM/09649 | Retrofitting | Name of the Work :- Laying of 90 mm dia UPVC Pipe line at Mastarpara, Raypara of Mahadipur Village for installation of FHTC under Mahadipur & Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1465/MAAD | 29/07/2022 | 45 | BANIK BROTHERS | 3.21 | 0 | 0 | 1
2145 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mahadipur and Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in English Bazar , SM/09649 | Retrofitting | Laying of 90 mm dia uPVC Pipe line at Parbatipur and Gour Mohali village for installation of FHTC under Mahadipur & Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1872/MAAD | 28/09/2022 | 45 | BANIK BROTHERS | 3.57 | 0 | 0 | 1
2146 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mahadipur and Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in English Bazar , SM/09649 | Retrofitting | Laying of 20mm dia HDPE pipe at Mahadipur Village for installation of FHTC under Mahadipur & Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte | 614/MAAD | 31/03/2023 | 15 | BANIK BROTHERS | 4.46 | 0 | 0 | 100
2147 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mahadipur and Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in English Bazar , SM/09649 | Retrofitting | Laying of 20mm dia HDPE pipe at Garh Mahali & Khirki Village for installation of FHTC under Mahadipur & Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 615/MAAD | 31/03/2023 | 15 | BANIK BROTHERS | 4.02 | 0 | 0 | 100
2148 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Mahadipur and Bholanathpur Distribution Zone under Gour Mahadipur Arsenic Free Water Supply Scheme in English Bazar , SM/09649 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
2149 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 nos )of Harishchandrapur-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10381 | School | Material Requisition To Resource Division | 725/MD | 25/03/2022 | 0 | Resource Division | 73.75 | 0 | 0 | 0
2150 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 nos )of Harishchandrapur-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10381 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Malior-I & Malior-II GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | 37/MD | 16/01/2023 | 75 | A. D. D. ASSOCIATES | 123.99 | 0 | 0 | 100
2151 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 nos )of Harishchandrapur-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10381 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Sadlichak & Bhaluka GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | 91/MD | 17/01/2023 | 75 | M/S TRILOCHAN CONSTRUCTION CO | 107.77 | 0 | 0 | 95
2152 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 nos )of Harishchandrapur-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10381 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Doulatpur & Mashaldaha GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | 86/MD | 17/01/2023 | 75 | M/S TRILOCHAN CONSTRUCTION CO | 107.82 | 0 | 0 | 97
2153 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 nos )of Harishchandrapur-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10381 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Sultannagar GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | 3195/MD | 27/12/2022 | 370 | MUNNA AGROTECH ENTERPRISE | 91.69 | 0 | 0 | 60
2154 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(112 nos )of Harishchandrapur-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10381 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Islampur & Daulatnagar GP of Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | 41/MD | 16/01/2023 | 563 | MILLENNIUM ENTERPRISR | 140.16 | 0 | 0 | 100
2155 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(77 nos.) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10384 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Malatipur GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | 87/MD | 17/01/2023 | 60 | DIPAYAN DEY | 95.49 | 0 | 0 | 67
2156 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(77 nos.) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10384 | School | Material Requisition To Resource Division | 727/MD | 25/03/2022 | 0 | Resource Division | 71.35 | 0 | 0 | 0
2157 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(77 nos.) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10384 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Kshempur GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | 814/MD | 20/02/2023 | 75 | NEOGI ENTERPRISE | 136.67 | 0 | 0 | 80
2158 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(77 nos.) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10384 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Bhakri and Gourhand GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | 812/MD | 20/02/2023 | 75 | NEOGI ENTERPRISE | 136.67 | 0 | 0 | 100
2159 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(77 nos.) of Chanchal-II Dev. Block, Malda under Malda Division, PHE Dte. , SM/10384 | School | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Jalalpur & Chandrapara GP of Chanchal-II Dev. Block under Malda Division, PHE Dte. | 89/MD | 17/01/2023 | 958 | MILLENNIUM ENTERPRISR | 129.75 | 0 | 0 | 100
2160 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (71 nos. AWCs in Kaliachak-I Block) , SM/10236 | Anganwadi | Providing Drinking Water Supply in 6 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 1067/MAAD | 27/05/2022 | 120 | M/S. JHA CONSTRUCTION | 42.35 | 0 | 0 | 100
2161 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (71 nos. AWCs in Kaliachak-I Block) , SM/10236 | Anganwadi | Material Requisition To Resource Division | 331/MAAD | 28/02/2022 | 0 | Resource Division | 52.84 | 0 | 0 | 0
2162 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (71 nos. AWCs in Kaliachak-I Block) , SM/10236 | Anganwadi | Providing Drinking Water Supply in 12 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 646/MAAD | 01/04/2022 | 120 | MILLENNIUM ENTERPRISE | 84.62 | 0 | 0 | 100
2163 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (71 nos. AWCs in Kaliachak-I Block) , SM/10236 | Anganwadi | Providing Drinking Water Supply in 10 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 647/MAAD | 01/04/2022 | 120 | MILLENNIUM ENTERPRISE | 70.52 | 0 | 0 | 100
2164 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (71 nos. AWCs in Kaliachak-I Block) , SM/10236 | Anganwadi | Formal work order for Providing Drinking Water Supply in 43 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Kaliachak - I Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure-l ) | 777/MAAD | 22/04/2022 | 90 | MAMATA USHA ENTERPRISE | 305.05 | 0 | 0 | 80
2165 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10238 | School | Supply G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for Schools of Manikchak Block under Malda Arsenic Area W/S Division, PHE Dte. | 1032/MAAD | 12/05/2022 | 10 | RAMASISH ENTERPRISE | 5 | 0 | 0 | 0
2166 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10238 | School | Providing Drinking Water Supply in 10 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 643/MAAD | 01/04/2022 | 120 | BANIK BROTHERS | 63.04 | 0 | 0 | 0
2167 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10238 | School | Providing Drinking Water Supply in 10 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 642/MAAD | 01/04/2022 | 120 | M/S TRILOCHAN CONSTRUCTION CO. | 62.67 | 0 | 0 | 100
2168 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10238 | School | Formal Work order for Providing Drinking Water Supply in 21 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure) | 781/MAAD | 26/04/2022 | 120 | USHA ENTERPRISE | 132.38 | 0 | 0 | 95
2169 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10238 | School | Material Requisition To Resource Division | 335/MAAD | 28/02/2022 | 0 | Resource Division | 44.07 | 0 | 0 | 0
2170 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10238 | School | Formal work order for Providing Drinking Water Supply in 30 nos. Source Less Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Schools as per Annexure ) | 778/MAAD | 22/04/2022 | 120 | HANNAN BUILDERS PVT. LTD. | 189.14 | 0 | 0 | 61
2171 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10238 | School | Formal work order for Providing Drinking Water Supply in 47 nos. Source Less School Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Manikchak Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure-l ) | 1052/MAAD | 23/05/2022 | 90 | M/S TAPAS KUMAR CHAKRABORTY | 297.8 | 0 | 0 | 82
2172 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in 118 nos. Sourceless Schools Through Grid Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda , SM/10238 | School | Supply & delyvery of G.I. pipe Strainer with brass net & jecketted of approoved Quality ( Heavy Type) for providing Drinking Water Supply in Source Less Schols at Manikchak Block (Phase-I) under Malda Arsenic Area Water Supply Division, P.H.E. Dte. | 1880/MAAD | 28/09/2022 | 15 | M/S TAPAS KUMAR CHAKRABORTY | 4.76 | 0 | 0 | 75
2173 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAHARPUR Water Supply Scheme , SM/06869 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAHARPUR Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. | 2465/MD | 12/10/2020 | 45 | UTTAM KUMAR GHOSH | 70.72 | 30 | 44.89 | 1
2174 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PAHARPUR Water Supply Scheme , SM/06869 | Retrofitting | Acceptance cum formal work order for Additional laying work of DI & UPVC pipe line of SADLICHAK W/S Scheme at HARISHCHANDRAPUR-II Dev. Block under Malda division.P.H.E.Dte. In the District of Malda. | 47/CSD | 14/01/2022 | 30 | BEE GEE CONSTRUCTION | 4.19 | 0 | 0 | 1
2175 | MALDAH | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda , SM/12338 | New | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of DAUDPUR & its adjoining mouza Water Scheme under Malda Division,PHE Dte. In the District of Malda. | 2234/MD | 16/09/2022 | 45 | M/S. TEWARI CONSTRUCTION | 6.19 | 0 | 0 | 0
2176 | MALDAH | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda , SM/12338 | New | Material Requisition To Resource Division | 2756/MD | 22/11/2022 | 0 | Resource Division | 34.78 | 0 | 0 | 0
2177 | MALDAH | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda , SM/12338 | New | Acceptance cum formal work order for Sinking of 01 (One) Nos. 250mm. Dia. x 150mm. Big dia. Tube Well 160 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer at Daudpur Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda . | 2235/MD | 16/09/2022 | 15 | SNEHASISH GHOSH | 8.09 | 0 | 0 | 100
2178 | MALDAH | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda , SM/12338 | New | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 160m Deep at Daudpur PWSS under Chanchal-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 4741/MD | 11/09/2024 | 45 | A. L. ENGINEERING SOLUTION | 10.44 | 0 | 0 | 0
2179 | MALDAH | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda , SM/12338 | New | Sinking of 200 mm (all through) Big dia. Tube Well of 160 m Deep by D.R Rig. Method using P.V.C. pipe & Filter including Supply of materials at head work site under DAUDPUR Water Supply Scheme of Chanchal-I Block under Malda Division, P.H.E Dte in the District of Malda. | 4822/MD | 13/09/2024 | 30 | SAUDAGAR INDIA | 10.21 | 0 | 0 | 0
2180 | MALDAH | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda , SM/12338 | New | Material Requisition To Resource Division | 99/MD | 05/01/2024 | 0 | Resource Division | 4.93 | 0 | 0 | 0
2181 | MALDAH | Malda Mechanical | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda , SM/12338 | New | New service connection at daudpur w/s sch. T/W no I Under EE/ MLMD PHE DTE District - malda. (chanchal c. c. c) | BP-2023-24-562 | 16/02/2024 | 0 | W.B.S.E.D.C.LTD | 14.26 | 0 | 0 | 0
2182 | MALDAH | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda , SM/12338 | New | Formal work order for the work of Implementation of DAUDPUR ZONE-I Piped Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3288/MD | 23/08/2023 | 952 | A. K. CONSTRUCTION | 151.6 | 0 | 0 | 60
2183 | MALDAH | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda , SM/12338 | New | Laying of Distribution Line, Providing FHTC, Construction of Pump House at Daudpur Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2902/MD | 07/06/2024 | 420 | M/S MOON LIGHT CONSTRUCTION & CO. | 93.32 | 0 | 0 | 51
2184 | MALDAH | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda , SM/12338 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Daudpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 71 | 13/01/2025 | 45 | THREE BROTHERS CONSTRUCTION & CO | 31.61 | 0 | 0 | 0
2185 | MALDAH | Malda Division | Daudpur Piped water supply scheme in Chanchal-I Block, Dist-Malda , SM/12338 | New | Construction of Boundary Wall at Head Work site of Daudpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 1223/MD | 26/03/2025 | 30 | M/S MADHU CONSTRUCTION | 19.79 | 0 | 0 | 0
2186 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11589 | New | Acceptance cum formal work order for Route survey, design and preparation of DPR of Kariali Zone-II Piped Water Supply Scheme at Harishchandrapur-II Dev. Block under Malda Division, PHE Dte. | 657/MD | 22/03/2022 | 15 | M/S SOBHA & CO. | 2.76 | 0 | 0 | 1
2187 | MALDAH | Malda Mechanical | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11589 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. (Zone-II) of Kariali PWSS, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004422637 | 22/09/2023 | 90 | W.B.S.E.D.C.LTD | 7.19 | 0 | 0 | 100
2188 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11589 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 16.83 | 0 | 0 | 0
2189 | MALDAH | Malda Mechanical | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11589 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I of Kariali (zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011264) | 2757/MLMD | 14/08/2023 | 180 | DEB CONSTRUCTION. | 21.59 | 0 | 0 | 58
2190 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11589 | New | Additional Laying Distribution of UPVC Pipe line of KARIALI ZONE-II Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 4141/MD | 11/10/2023 | 30 | S.S.GHOSH ENTERPRISE & CO. | 2.13 | 0 | 0 | 80
2191 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11589 | New | Construction of Boundary Wall at 3rd Tube well site of Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 5603/MD | 05/11/2024 | 60 | GULJAR CONSTRUCTION | 6.93 | 0 | 0 | 0
2192 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11589 | New | Sinking of 200mm (all through) Big dia. Tube Well of 150m Deep at 3rd Tube well site of Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | 5605/MD | 05/11/2024 | 45 | SAUDAGAR INDIA | 9.82 | 0 | 0 | 0
2193 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11589 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Kariali Zone-II PWSS under Harishchandrapur-II Block under Malda Division, PHE Dte, Govt. of West Bengal. | 5599/MD | 05/11/2024 | 60 | DIPU DUTTA | 4.53 | 0 | 0 | 0
2194 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11589 | New | Material Requisition To Resource Division | 756/MD | 19/02/2024 | 0 | Resource Division | 4.31 | 0 | 0 | 0
2195 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11589 | New | Formal work order for the work of Augmentation of KARIALI ZONE-II Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1947/MD | 16/05/2023 | 1136 | UTTAM KUMAR GHOSH | 399.3 | 0 | 0 | 75
2196 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11589 | New | Construction of Boundary Wall at Head Work site of Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 699/MD | 09/02/2024 | 843 | UTTAM KUMAR GHOSH | 16.32 | 0 | 0 | 0
2197 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11589 | New | Laying of Rising Main including Specials and Valves for Kandaran Zone-II Piped Water Supply Scheme at Chanchal-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 700/MD | 09/02/2024 | 737 | UTTAM KUMAR GHOSH | 22.42 | 0 | 0 | 0
2198 | MALDAH | Malda Division | Ground Water Based for Kariali Zone-II Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/11589 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kariali Zone-II Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 5914/MD | 26/11/2024 | 521 | UTTAM KUMAR GHOSH | 27.23 | 0 | 0 | 0
2199 | MALDAH | Malda Division | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12314 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No-3 ( 135 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at AKALPUR Water Supply Scheme of Gazole Block .under Malda Division, PHE Dte. in the District of Malda. | 2304/MD | 28/09/2022 | 30 | DUTTA ENTERPRISE | 9.04 | 0 | 0 | 1
2200 | MALDAH | Malda Division | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12314 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for AKALPUR Piped Water Supply Scheme of Gazole Block in the District of Malda under Malda Division, PHE Dte. | 2508/MD | 03/11/2022 | 45 | M/S. TEWARI CONSTRUCTION | 28.05 | 0 | 0 | 1
2201 | MALDAH | Malda Division | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12314 | Augmentation | Acceptance cum formal work order for Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site of AKALPUR Water Supply Scheme of Gazole Block. under Malda Division, PHE Dte. in the District of Malda. | 3113/MD | 20/12/2022 | 45 | THREE BROTHERS CONSTRUCTION & CO | 6.69 | 0 | 0 | 0
2202 | MALDAH | Malda Mechanical | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12314 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Akalpur, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004293392 | 16/05/2023 | 90 | W.B.S.E.D.C.LTD | 5.14 | 0 | 0 | 0
2203 | MALDAH | Malda Division | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12314 | Augmentation | Material Requisition To Resource Division | 2411/MD | 17/10/2022 | 0 | Resource Division | 5.56 | 0 | 0 | 0
2204 | MALDAH | Malda Division | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12314 | Augmentation | Construction of Boundary Wall at Akalpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3030/MD | 13/06/2024 | 30 | BENGAL ENGINEERING COMPANY | 15.69 | 0 | 0 | 0
2205 | MALDAH | Malda Mechanical | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12314 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Source Augmentation Akalpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012797) | 507/MLMD | 20/03/2023 | 120 | SUBHAS CHANDRA KESHORI | 11.42 | 0 | 0 | 100
2206 | MALDAH | Malda Division | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12314 | Augmentation | Placement of fund against the work for road restoration for laying pipe line for Eklakhi to Rashikpur road from 2.400 KM to 7.900 Km under AKALPUR PWSS under Malda Division,PHE Dte. | BP-2024-25-252 | 10/09/2024 | 0 | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 9.95 | 0 | 0 | 0
2207 | MALDAH | Malda Division | Source Augmentation of Akalpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12314 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Akalpur Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 5936/MD | 27/11/2024 | 90 | S. N. CONSTRUCTION | 42.82 | 0 | 0 | 0
2208 | MALDAH | Malda Mechanical | SWARUPGANJ Piped Water Supply Scheme , SM/12185 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of SWARUPGANJ, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004368714 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 4.93 | 0 | 0 | 100
2209 | MALDAH | Malda Mechanical | SWARUPGANJ Piped Water Supply Scheme , SM/12185 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of SWARUPGANJ, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004368721 | 28/07/2023 | 90 | W.B.S.E.D.C.LTD | 5.49 | 0 | 0 | 100
2210 | MALDAH | Malda Division | SWARUPGANJ Piped Water Supply Scheme , SM/12185 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 23.46 | 0 | 0 | 0
2211 | MALDAH | Malda Mechanical | SWARUPGANJ Piped Water Supply Scheme , SM/12185 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Swarupganj Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013249) | 2329/MLMD | 26/07/2023 | 825 | MERCURY ENGINEERING COMPANY. | 30.4 | 0 | 0 | 84
2212 | MALDAH | Malda Division | SWARUPGANJ Piped Water Supply Scheme , SM/12185 | New | Construction of Boundary Wall at Head Work site of SWARUPGANJ Piped Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 379/MD | 17/01/2024 | 45 | BANIK BROTHERS | 21.73 | 0 | 0 | 0
2213 | MALDAH | Malda Division | SWARUPGANJ Piped Water Supply Scheme , SM/12185 | New | Construction of Boundary Wall at 2nd Tube well site of Swarupganj Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 5602/MD | 05/11/2024 | 60 | BANIK BROTHERS | 6.93 | 0 | 0 | 0
2214 | MALDAH | Malda Division | SWARUPGANJ Piped Water Supply Scheme , SM/12185 | New | Material Requisition To Resource Division | 755/MD | 19/02/2024 | 0 | Resource Division | 12.32 | 0 | 0 | 0
2215 | MALDAH | Malda Division | SWARUPGANJ Piped Water Supply Scheme , SM/12185 | New | Formal work order for the work of Implementation of SWARUPGANJ Water Supply Scheme at Chanchal-I Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 952/MD | 28/02/2023 | 1119 | BANIK BROTHERS | 469.75 | 0 | 0 | 75
2216 | MALDAH | Malda Division | SWARUPGANJ Piped Water Supply Scheme , SM/12185 | New | Acceptance cum formal work order for Laying of Distribution of UPVC Pipeline of SWARUPGANJ Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 2333/MD | 08/06/2023 | 60 | ABANI BHUSAN GHOSH | 52.67 | 0 | 0 | 65
2217 | MALDAH | Malda Division | SWARUPGANJ Piped Water Supply Scheme , SM/12185 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Swarupganj Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 74 | 13/01/2025 | 261 | BANIK BROTHERS | 83.72 | 0 | 0 | 0
2218 | MALDAH | Malda Division | DAKSHIN BHAKURIA Piped Water Supply Scheme , SM/12186 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 9.78 | 0 | 0 | 0
2219 | MALDAH | Malda Division | DAKSHIN BHAKURIA Piped Water Supply Scheme , SM/12186 | New | Construction of Boundary Wall at Head Work site of Dakshin Bhakuria Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 5003/MD | 27/09/2024 | 45 | M/S TEWARI CONSTRUCTION | 32.97 | 0 | 0 | 0
2220 | MALDAH | Malda Division | DAKSHIN BHAKURIA Piped Water Supply Scheme , SM/12186 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of UTTAR BHAKURIA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | 2695/MD | 17/11/2022 | 30 | ASHIS CONSTRUCTION | 9.2 | 0 | 0 | 80
2221 | MALDAH | Malda Division | DAKSHIN BHAKURIA Piped Water Supply Scheme , SM/12186 | New | Material Requisition To Resource Division | 114/MD | 05/01/2024 | 0 | Resource Division | 3.7 | 0 | 0 | 0
2222 | MALDAH | Malda Mechanical | DAKSHIN BHAKURIA Piped Water Supply Scheme , SM/12186 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of DAKSHIN BHAKURIA, Bhaluka C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-413 | 03/01/2024 | 0 | W.B.S.E.D.C.LTD | 5.87 | 0 | 0 | 0
2223 | MALDAH | Malda Mechanical | DAKSHIN BHAKURIA Piped Water Supply Scheme , SM/12186 | New | New service connection at Dakshin Bhakuria ph II PWSS T/W NO II Under EE/MLMD PHE DTE DIST. Malda.( Bhaluka c c c) | BP-2024-25-205 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 4.7 | 0 | 0 | 0
2224 | MALDAH | Malda Division | DAKSHIN BHAKURIA Piped Water Supply Scheme , SM/12186 | New | Formal work order for the work of Implementation of DAKSHIN BHAKURIA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2707/MD | 14/07/2023 | 270 | MOTI RAHAMAN | 202.31 | 0 | 0 | 42
2225 | MALDAH | Malda Mechanical | DAKSHIN BHAKURIA Piped Water Supply Scheme , SM/12186 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II and making compound lighting arrangement at T/W no. I of Dakshin Bhakuria Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013248) | 2315/MLMD | 26/07/2023 | 837 | DAS CONSTRUCTION | 25.62 | 0 | 0 | 78
2226 | MALDAH | Malda Division | TALPUKUR Piped Water Supply Scheme , SM/12189 | New | Material Requisition To Resource Division | 3044/MD | 12/12/2022 | 0 | Resource Division | 15.84 | 0 | 0 | 0
2227 | MALDAH | Malda Mechanical | TALPUKUR Piped Water Supply Scheme , SM/12189 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of Talpukur , Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004501325 | 28/11/2023 | 90 | W.B.S.E.D.C.LTD | 3.83 | 0 | 0 | 100
2228 | MALDAH | Malda Mechanical | TALPUKUR Piped Water Supply Scheme , SM/12189 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Talpukur , Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004501336 | 28/11/2023 | 90 | W.B.S.E.D.C.LTD | 6.96 | 0 | 0 | 100
2229 | MALDAH | Malda Division | TALPUKUR Piped Water Supply Scheme , SM/12189 | New | Material Requisition To Resource Division | 1605/MD | 11/04/2023 | 0 | Resource Division | 13.49 | 0 | 0 | 0
2230 | MALDAH | Malda Division | TALPUKUR Piped Water Supply Scheme , SM/12189 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Talpukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 6162/MD | 05/12/2024 | 45 | IDEAL CONSTRUCTION | 26.03 | 0 | 0 | 0
2231 | MALDAH | Malda Division | TALPUKUR Piped Water Supply Scheme , SM/12189 | New | Construction of Boundary Wall at 2nd Tube well Site of Talpukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 2938/MD | 10/06/2024 | 30 | BANIK BROTHERS | 8.99 | 0 | 0 | 100
2232 | MALDAH | Malda Division | TALPUKUR Piped Water Supply Scheme , SM/12189 | New | Formal work order for the work of Implementation of TALPUKUR Water Supply Scheme at Habibpur Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1899/MD | 10/05/2023 | 1025 | BANIK BROTHERS | 523.57 | 0 | 0 | 71
2233 | MALDAH | Malda Mechanical | TALPUKUR Piped Water Supply Scheme , SM/12189 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Talpukur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013199) | 2257/MLMD | 18/07/2023 | 834 | GHOSH BROTHERS... | 28.3 | 0 | 0 | 76
2234 | MALDAH | Malda Division | TALPUKUR Piped Water Supply Scheme , SM/12189 | New | Erection of Property board and dissemination of Property information through wall painting related to Jal Jeevan Mission works of Chaksukur, Dalla, Talpukur, Aiho PWSS under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 644/MD | 19/02/2025 | 7 | SADHANA CONSTRUCTION | 0.81 | 0 | 0 | 0
2235 | MALDAH | Malda Division | TALPUKUR Piped Water Supply Scheme , SM/12189 | New | Construction of Boundary Wall at Head Work site of Talpukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 159/MD | 08/01/2024 | 45 | BANIK BROTHERS | 22.15 | 0 | 0 | 100
2236 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Panchanadapur and Hamidpur Zone Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11913 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
2237 | MALDAH | Malda Mechanical | ARAZI JALSA PIPED WATER SUPPLY SCHEME. , SM/13734 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of ARAZI JALSA , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004481943 | 08/11/2023 | 90 | W.B.S.E.D.C.LTD | 9.23 | 0 | 0 | 100
2238 | MALDAH | Malda Mechanical | ARAZI JALSA PIPED WATER SUPPLY SCHEME. , SM/13734 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of ARAZI JALSA , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004481907 | 08/11/2023 | 90 | W.B.S.E.D.C.LTD | 4.21 | 0 | 0 | 100
2239 | MALDAH | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. , SM/13734 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 11.31 | 0 | 0 | 0
2240 | MALDAH | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. , SM/13734 | New | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 10/05/2024 to 19/06/2024=41 Days). | 2421/MD | 09/05/2024 | 41 | TARUN KUMAR BHATTACHARYA | 0.19 | 0 | 0 | 0
2241 | MALDAH | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. , SM/13734 | New | Construction of Boundary Wall at Head Work site of Arazi Jalsa Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3213/MD | 27/06/2024 | 461 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 21.89 | 0 | 0 | 70
2242 | MALDAH | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. , SM/13734 | New | Material Requisition To Resource Division | 29/MD | 04/01/2024 | 0 | Resource Division | 20.4 | 0 | 0 | 0
2243 | MALDAH | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. , SM/13734 | New | Formal work order for the work of Implementation of ARAZI JALSA Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2008/MD | 17/05/2023 | 1108 | M/S TAPAS KUMAR CHAKRABORTY & CO | 1160.94 | 0 | 0 | 65
2244 | MALDAH | Malda Mechanical | ARAZI JALSA PIPED WATER SUPPLY SCHEME. , SM/13734 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Arazi Jalsa Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013468) | 2575/MLMD | 04/08/2023 | 756 | NIRMAN. | 26.75 | 0 | 0 | 87
2245 | MALDAH | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. , SM/13734 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arazi Jalsa Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 5913/MD | 26/11/2024 | 354 | EUREKA UNEMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 28.74 | 0 | 0 | 0
2246 | MALDAH | Malda Division | ARAZI JALSA PIPED WATER SUPPLY SCHEME. , SM/13734 | New | Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 20/06/2024 to 16/12/2024=180 Days). | 3108/MD | 18/06/2024 | 180 | TARUN KUMAR BHATTACHARYA | 0.86 | 0 | 0 | 0
2247 | MALDAH | Malda Division | SULTANNAGAR PWSS , SM/12196 | New | Material Requisition To Resource Division | 3049/MD | 12/12/2022 | 0 | Resource Division | 25.94 | 0 | 0 | 0
2248 | MALDAH | Malda Division | SULTANNAGAR PWSS , SM/12196 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 135 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of materials at Heads Work Site of SULTANNAGAR Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | 2699/MD | 17/11/2022 | 30 | ASHIS CONSTRUCTION | 9.2 | 0 | 0 | 1
2249 | MALDAH | Malda Division | SULTANNAGAR PWSS , SM/12196 | New | Continuation work order for Hiring of inspection Vehicle (Non-Air-Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long jurney and should be covered any where without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Malda Sadar Sub-Division, PHE Dte. under Malda Division, PHE Dte. (Period from 01/01/2023 to 30/06/2023). | 519/MSD | 30/12/2022 | 182 | ARUN KUMAR DAS | 0.86 | 0 | 0 | 71
2250 | MALDAH | Malda Mechanical | SULTANNAGAR PWSS , SM/12196 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Sultannagar PWSS, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004232824 | 17/05/2023 | 90 | W.B.S.E.D.C.LTD | 5.28 | 0 | 0 | 0
2251 | MALDAH | Malda Division | SULTANNAGAR PWSS , SM/12196 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at SULTANNAGAR Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 923/MD | 27/02/2023 | 30 | DUTTA ENTERPRISE | 10.13 | 0 | 0 | 100
2252 | MALDAH | Malda Mechanical | SULTANNAGAR PWSS , SM/12196 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of SULTANNAGAR, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004353821 | 20/07/2023 | 90 | W.B.S.E.D.C.LTD | 2.66 | 0 | 0 | 100
2253 | MALDAH | Malda Division | SULTANNAGAR PWSS , SM/12196 | New | Material Requisition To Resource Division | 1620/MD | 11/04/2023 | 0 | Resource Division | 10.22 | 0 | 0 | 0
2254 | MALDAH | Malda Mechanical | SULTANNAGAR PWSS , SM/12196 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Sultannagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/012936) | 785/ MLMD | 27/04/2023 | 916 | M/S SAJAHAN CHOWDHURY | 28.18 | 0 | 0 | 85
2255 | MALDAH | Malda Division | SULTANNAGAR PWSS , SM/12196 | New | Formal work order for the work of Implementation of SULTANNAGAR Water Supply Scheme at HARISHCHANDRAPUR-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1845/MD | 02/05/2023 | 1065 | M/S ALISA CONSTRUCTIION | 289.64 | 0 | 0 | 89
2256 | MALDAH | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12763 | Augmentation | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at MEKPUR Piped Water Supply Scheme (Tube Well No-4) of Old Malda Block of Malda District under Malda Division, PHE Dte. | 2703/MD | 17/11/2022 | 30 | A. L. ENGINEERING SOLUTION | 8.42 | 0 | 0 | 1
2257 | MALDAH | Malda Mechanical | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12763 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III, IV & V of Source Augmentation of Mekpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014459) | 509/MLMD | 20/03/2023 | 120 | ORIENTAL ENGINEERING CO. | 34.55 | 0 | 0 | 58
2258 | MALDAH | Malda Mechanical | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12763 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Mekpur PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004243230 | 27/04/2023 | 90 | W.B.S.E.D.C.LTD | 4.5 | 0 | 0 | 0
2259 | MALDAH | Malda Mechanical | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12763 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. IV of Mekpur PWSS, Old Malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004243234 | 27/04/2023 | 90 | W.B.S.E.D.C.LTD | 2.42 | 0 | 0 | 0
2260 | MALDAH | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12763 | Augmentation | Acceptance cum formal work order for Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (120 Mtr. Deep) by D.R. Rig method using P.V.C. pipe and Gravel Filter including supply of Materials at MEKPUR Piped Water Supply Scheme (Tube Well No-3) of Old Malda Block of Malda District under Malda Division, PHE Dte. | 2702/MD | 17/11/2022 | 30 | A. L. ENGINEERING SOLUTION | 8.42 | 0 | 0 | 1
2261 | MALDAH | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12763 | Augmentation | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Mekpur Piped Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | 1985/MD | 17/05/2023 | 45 | HIRAK ROY CHOUDHURY | 8.28 | 0 | 0 | 100
2262 | MALDAH | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12763 | Augmentation | Construction of Boundary Wall at Goalpara Mouza under Mekpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 1514/MD | 16/03/2024 | 30 | S. N. CONSTRUCTION | 11.32 | 0 | 0 | 100
2263 | MALDAH | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12763 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for MEKPUR Piped Water Supply Scheme (JL-15 Samsabad, JL-20 Kadamtali, JL-21 Badanpur, JL-22 Chhotapara, JL-23 Lakshmi Kandar and JL-27 Rahutgaon) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | 2985/MD | 07/12/2022 | 45 | MANIK CHOUDHURY | 55.22 | 0 | 0 | 100
2264 | MALDAH | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12763 | Augmentation | Extension of pipe line and replacing of damage A.C./uPVC pipe line by different dia. UPVC pipe for MEKPUR Piped Water Supply Scheme at Old Malda Block under Malda Division, PHE Dte, Govt. of West Bengal. | 870/MD | 27/02/2024 | 45 | S. R. ENTERPRISE | 6.07 | 0 | 0 | 100
2265 | MALDAH | Malda Mechanical | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12763 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. III of Mekpur, Old malda C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-462 | 17/01/2024 | 0 | W.B.S.E.D.C.LTD | 1.01 | 0 | 0 | 0
2266 | MALDAH | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12763 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for MEKPUR Piped Water Supply Scheme (JL-11 Tutkhan, JL-12 Goalpara, and JL-14 Gotpara) at Old Malda Dev. Block in the District of Malda under Malda Division, PHE Dte. | 2986/MD | 07/12/2022 | 45 | M/S PARIMAL DAS | 56.72 | 0 | 0 | 1
2267 | MALDAH | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12763 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Tube Well No. 3 of Mekpur Water Supply Scheme of Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | 2615/MD | 02/06/2025 | 135 | M/S PARIMAL DAS | 17.27 | 0 | 0 | 0
2268 | MALDAH | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12763 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 35 m³/hr. capacity Pressure type Iron Elimination Plant with Construction of Blower room & backwash water disposal at Tube Well No. 4 of Mekpur Water Supply Scheme of Old Malda Dev. Block under Malda Division P.H.E Dte in the District of Malda. | 2616/MD | 02/06/2025 | 135 | M/S PARIMAL DAS | 17.27 | 0 | 0 | 0
2269 | MALDAH | Malda Division | Source Augmentation of Mekpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/12763 | Augmentation | Augmentation of Head work site Pump House, Pump House No.-2, Earth filling and 2 Nos. Boundary wall at Mekpur Water Supply scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1068/MD | 19/03/2025 | 60 | S. R. ENTERPRISE | 8.04 | 0 | 0 | 0
2270 | MALDAH | Malda Mechanical | SAIDPUR Piped Water Supply Scheme , SM/12766 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at T/W no. I of Saidpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/014263) | 2563/MLMD | 04/08/2023 | 787 | SUBRATA SAHA | 28.62 | 0 | 0 | 78
2271 | MALDAH | Malda Mechanical | SAIDPUR Piped Water Supply Scheme , SM/12766 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. I of Saidpur PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004467185 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 3.87 | 0 | 0 | 100
2272 | MALDAH | Malda Mechanical | SAIDPUR Piped Water Supply Scheme , SM/12766 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Saidpur PWSS , Gazol C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004467024 | 17/10/2023 | 90 | W.B.S.E.D.C.LTD | 6.11 | 0 | 0 | 100
2273 | MALDAH | Malda Division | SAIDPUR Piped Water Supply Scheme , SM/12766 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 20.1 | 0 | 0 | 0
2274 | MALDAH | Malda Division | SAIDPUR Piped Water Supply Scheme , SM/12766 | New | Material Requisition To Resource Division | 240/MD | 10/01/2024 | 0 | Resource Division | 12.66 | 0 | 0 | 0
2275 | MALDAH | Malda Division | SAIDPUR Piped Water Supply Scheme , SM/12766 | New | Formal work order for the work of Implementation of SAIDPUR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2320/MD | 08/06/2023 | 930 | NEOGI ENTERPRISE | 651.25 | 0 | 0 | 60
2276 | MALDAH | Malda Division | SAIDPUR Piped Water Supply Scheme , SM/12766 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Saidpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6168/MD | 05/12/2024 | 345 | ANJIMA CONSTRUCTION CO. | 22.39 | 0 | 0 | 0
2277 | MALDAH | Malda Division | SAIDPUR Piped Water Supply Scheme , SM/12766 | New | Construction of Boundary Wall at 2nd Tube Well site of Saidpur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 2957/MD | 10/06/2024 | 30 | SAYEM ENTERPRISE | 7.16 | 0 | 0 | 100
2278 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIHARI Water Supply Scheme , SM/07007 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIHARI ZONE-II Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | 2445/MD | 12/10/2020 | 30 | M/S SABANA CONSTRUCTION | 31.87 | 14.01 | 43.95 | 1
2279 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIHARI Water Supply Scheme , SM/07007 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of BIHARI ZONE-I Water Supply Scheme at Ratua-I Block under Malda Division, PHE Dte. | 2440/MD | 12/10/2020 | 30 | BEE GEE CONSTRUCTION | 36.34 | 15.66 | 100 | 0
2280 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIHARI Water Supply Scheme , SM/07007 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of BIHARI ZONE-II Water Supply Scheme at Ratua-I Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 4774/MD | 05/12/2023 | 45 | M/S. NAYAMEE ENGINEERING & CONSTRUCTIONS | 10.21 | 0 | 0 | 98
2281 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of BIHARI Water Supply Scheme , SM/07007 | Retrofitting | Laying of Parallel/ Dedicated Pipeline for better Functionality at Bihari Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 4234/MD | 29/08/2025 | 60 | S. R. ENTERPRISE | 12.42 | 0 | 0 | 0
2282 | MALDAH | Malda Mechanical | Jotparan Mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED , SM/15946 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Jotparan PWSS, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004427246 | 18/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.37 | 0 | 0 | 100
2283 | MALDAH | Malda Ars Area W/S Division | Jotparan Mouza piped water supply Scheme of Kaliachak-I block under Malda Arsenic Area water supply Division, PHED , SM/15946 | New | Implementation of Jotparan Mouza Piped Water Supply Scheme of Kaliachak-I Block under Malda Arsenic Area Water Supply Division, PHE Dte, Govt. of West Bengal. | 1388/MAAD | 14/07/2023 | 476 | BANIK BROTHERS | 383.2 | 0 | 0 | 85
2284 | MALDAH | Malda Mechanical | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. , SM/17177 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Khaschandpur PWSS, Kaliachak C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004427011 | 18/09/2023 | 90 | W.B.S.E.D.C.LTD | 11.07 | 0 | 0 | 100
2285 | MALDAH | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. , SM/17177 | New | Material Requisition To Resource Division | 636/MAAD | 05/04/2023 | 0 | Resource Division | 67.64 | 0 | 0 | 0
2286 | MALDAH | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. , SM/17177 | New | Construction of 500 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir as per Departmental Design & Drawing including pipe connection, Soil Investigation and Providing Functional House Hold Tap Connection (FHTC) for Khaschandpur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. .(2nd Call) | 956/MAAD | 29/05/2023 | 583 | BEE GEE CONSTRUCTION | 218.56 | 0 | 0 | 85
2287 | MALDAH | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. , SM/17177 | New | Sinking of Two nos 250mm. Dia. x 150mm. big dia. Tube Well of 150 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Khaschandpur Piped Water supply scheme (Head Work Site & 2nd Tube well site) at Kaliachak-I Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | 597/MAAD | 30/03/2023 | 45 | M/S S.S. ENTERPRISE | 14.72 | 0 | 0 | 100
2288 | MALDAH | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. , SM/17177 | New | Construction of Arsenic-cum-Iron Removal Plant (AIRP) for Khaschandpur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. in the District of Malda.(2nd Call) | 867/MAAD | 04/05/2023 | 698 | NEOGI ENTERPRISE | 168.73 | 0 | 0 | 85
2289 | MALDAH | Malda Mechanical | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. , SM/17177 | New | Supply, delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tube Well No-I & II and Arsenic Iron Removal Plant at Khaschandpur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. | 3389/MLMD | 31/10/2023 | 789 | GHOSH BROTHERS... | 70.55 | 0 | 0 | 0
2290 | MALDAH | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. , SM/17177 | New | Construction of Boundary Wall at Head Work Site & 2nd Tube Well Site, Laying of rising main from 2nd Tube Well Site to HWS including supply of all specials & valves and Providing Functional House Hold Tap Connection (FHTC) for Khaschandpur Piped Water Supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E. Dte, Malda. | 1692/MAAD | 19/11/2024 | 90 | BEE GEE CONSTRUCTION | 70.37 | 0 | 0 | 0
2291 | MALDAH | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. , SM/17177 | New | Laying of Distribution System at Dawan Tola, Charka Tola, Maksaha Tola, Patuatola Chandpur, Haginagar Chandpur for Khaschandpur Piped Water supply scheme at Kaliachak-I Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 575/MAAD | 28/03/2023 | 614 | M/S TRILOCHAN CONSTRUCTION CO. | 104.23 | 0 | 0 | 100
2292 | MALDAH | Malda Ars Area W/S Division | Khaschandpur mouza piped water supply scheme of Kaliachak-I block under Malda arsenic area water supply Division, PHED. , SM/17177 | New | Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at 2nd Tube Well site of Khaschandpur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 2059/MAAD | 22/11/2023 | 100 | HIRAK ROYCHOUDHURY | 5.02 | 0 | 0 | 100
2293 | MALDAH | Malda Mechanical | DAHIL Piped Water Supply Scheme. , SM/18461 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Dahil Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015609) | 2316/MLMD | 26/07/2023 | 120 | DEBJYOTI BASU | 43.38 | 0 | 0 | 0
2294 | MALDAH | Malda Division | DAHIL Piped Water Supply Scheme. , SM/18461 | New | Material Requisition To Resource Division | 199/MD | 09/01/2024 | 0 | Resource Division | 13.62 | 0 | 0 | 0
2295 | MALDAH | Malda Division | DAHIL Piped Water Supply Scheme. , SM/18461 | New | Material Requisition To Resource Division | 820/MD | 21/02/2024 | 0 | Resource Division | 51.73 | 0 | 0 | 0
2296 | MALDAH | Malda Division | DAHIL Piped Water Supply Scheme. , SM/18461 | New | Formal work order for the work of Implementation of DAHIL Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3015/MD | 08/08/2023 | 967 | GHOSH BROTHERS | 1245.3 | 0 | 0 | 55
2297 | MALDAH | Malda Division | DAHIL Piped Water Supply Scheme. , SM/18461 | New | Construction of Boundary Wall at Head Work site of Dahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3050/MD | 13/06/2024 | 654 | GOBINDA ENTERPRISE | 26.25 | 0 | 0 | 70
2298 | MALDAH | Malda Division | DAHIL Piped Water Supply Scheme. , SM/18461 | New | Erection of Property board related to Jal Jeevan Mission works of Bhadar, Deotala, Mahil, Parail, Dahil & Moyna PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 640/MD | 19/02/2025 | 7 | S. N. CONSTRUCTION | 0.95 | 0 | 0 | 0
2299 | MALDAH | Malda Division | DAHIL Piped Water Supply Scheme. , SM/18461 | New | Construction of Boundary Wall at 2nd Tube Well site of Dahil Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 2484/MD | 28/05/2025 | 60 | A. L. ENGINEERING SOLUTION | 6.45 | 0 | 0 | 0
2300 | MALDAH | Malda Mechanical | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No. I of Gazole Zone-III Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017388) | 2748/MLMD | 14/08/2023 | 2005 | GHOSH BROTHERS... | 40.66 | 0 | 0 | 0
2301 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 196.39 | 0 | 0 | 0
2302 | MALDAH | Malda Mechanical | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I and making compound lighting arrangement at head worksite of Gazole Zone-IV Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017388) | 2747/MLMD | 14/08/2023 | 924 | BANIK BROTHERS | 13.21 | 0 | 0 | 67
2303 | MALDAH | Malda Mechanical | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I,II & III and Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. IV and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No. I of Gazole Zone-II Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/017388) | 2817/MLMD | 17/08/2023 | 2005 | H.K. DAS & CO. | 50.67 | 0 | 0 | 59
2304 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Material Requisition To Resource Division | 27/MD | 04/01/2024 | 0 | Resource Division | 56.25 | 0 | 0 | 0
2305 | MALDAH | Malda Mechanical | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Gazole Zone-I, Gazol CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-667 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 8.1 | 0 | 0 | 0
2306 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Formal work order for the work of Augmentation of GAZOLE ZONE-III Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3032/MD | 09/08/2023 | 935 | M/S DAS CONSTRUCTION | 516.04 | 0 | 0 | 27
2307 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Formal work order for the work of Augmentation of GAZOLE ZONE-I Piped Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3117/MD | 11/08/2023 | 991 | M/S TRILOCHAN CONSTRUCTION CO | 405.72 | 0 | 0 | 60
2308 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Formal work order for the work of Augmentation of Gazole Zone-IV Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 4326/MD | 16/10/2023 | 989 | UTTAM KUMAR GHOSH | 243.55 | 0 | 0 | 30
2309 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Formal work order for the work of Augmentation of Gazole Zone-II Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 4325/MD | 16/10/2023 | 898 | MILLENNIUM ENTERPRISR | 426.25 | 0 | 0 | 36
2310 | MALDAH | Malda Mechanical | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and making compound lighting arrangement at head worksite ,Solarisation of WBSEDCL energised pump house with Supply and Installation of Grid-connected Ground Mounted Solar PV systems with Net Metering at T/W No. I of Gazol Zone-I Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | 2942/MLMD | 11/09/2024 | 383 | DEY ENTERPRISE.. | 32.4 | 0 | 0 | 59
2311 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gazole Zone-II Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6414/MD | 19/12/2024 | 316 | MILLENNIUM ENTERPRISE | 73.8 | 0 | 0 | 0
2312 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gazole Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6415/MD | 19/12/2024 | 423 | M/S DAS CONSTRUCTION | 71.69 | 0 | 0 | 0
2313 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Gazole Zone-IV Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6416/MD | 19/12/2024 | 468 | UTTAM KUMAR GHOSH | 24.08 | 0 | 0 | 0
2314 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Construction of Boundary Wall at Head Work Site of Gazole Zone-III Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6532/MD | 27/12/2024 | 447 | M/S DAS CONSTRUCTION | 19.38 | 0 | 0 | 0
2315 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Dismentling & Restoration of Cement Concrete road and Construction of Thrust Block for protection of pipe line within the command area for Gazole Zone-III Water Supply Scheme at Gazole Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. | 2275/MD | 21/05/2025 | 336 | M/S DAS CONSTRUCTION | 55.73 | 0 | 0 | 0
2316 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Erection of Property board related to Jal Jeevan Mission works of Jibjalsar, Bahirgachi, Hatnagar & Gazole PWSS under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 638/MD | 19/02/2025 | 7 | S. N. CONSTRUCTION | 0.95 | 0 | 0 | 0
2317 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Augmentation of PH-2,PH-3,PH-4 &PH-6, at GAZOLE Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 2955/MD | 19/06/2025 | 60 | S. M. BUILDER | 5.21 | 0 | 0 | 0
2318 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Laying of additional Distribution pipeline by different dia. UPVC pipe for GAZOLE ZONE-IV Piped Water Supply Scheme at Gazole Dev. Block in the District of Malda under Malda Division, PHE Dte. | 2257/MD | 21/05/2025 | 406 | UTTAM KUMAR GHOSH | 21.83 | 0 | 0 | 0
2319 | MALDAH | Malda Division | Augmentation of Ground Water Based GAZOLE (Zone-I, II, III & IV) Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/18558 | Augmentation | Construction of Boundary Wall at Head Work site of Gazole Zone-I Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3200/MD | 27/06/2024 | 30 | M/S TRILOCHAN CONSTRUCTION CO | 23.16 | 0 | 0 | 100
2320 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Acceptance cum formal work order for Route survey for distribution network design for augmentation of Mirzapur Water Supply Scheme in Bamongola block under Malda Division, PHE Dte. | 1744/MD | 15/06/2021 | 14 | HORIZEN | 2.86 | 0 | 0 | 1
2321 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Acceptance cum formal work order for Design, Preparation & Submission of DPR as per existing route survey data for Augmentation of Mirzapur Piped Water Supply Scheme under Malda Division, PHE Dte. | 2687/MD | 09/09/2021 | 7 | HORIZEN | 1.25 | 0 | 0 | 1
2322 | MALDAH | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of MIRZAPUR Water Supply Scheme T/W no. II in the District of Malda under Malda Mechanical Division, PHE Dte. | 2950/MLMD | 28/12/2022 | 60 | MERCURY ENGINEERING COMPANY. | 11.06 | 0 | 0 | 1
2323 | MALDAH | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Supply, delivery, installation and commissioning of electro-mechanical components of Augmentation of MIRZAPUR Water Supply Scheme T/W no. I in the District of Malda under Malda Mechanical Division, PHE Dte. | 2949/MLMD | 28/12/2022 | 60 | DEY ENTERPRISE.. | 11.13 | 0 | 0 | 1
2324 | MALDAH | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Mirzapur, Bamongola C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004228429 | 26/04/2023 | 90 | W.B.S.E.D.C.LTD | 6.85 | 0 | 0 | 0
2325 | MALDAH | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. IV of Mirzapur, Bamongola C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004228411 | 26/04/2023 | 90 | W.B.S.E.D.C.LTD | 4.57 | 0 | 0 | 0
2326 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 3 at Mirzapur PWSS of Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | 3394/MD | 31/08/2023 | 45 | DIPU DUTTA | 4.16 | 0 | 0 | 0
2327 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Acceptance cum formal work order for Sinking of 300mm. Dia. x 200 mm. dia. and 140 Mtr. Deep Big dia Tube well (1 No) at Mirzapur Water Supply Scheme under Bamangola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1674/MD | 18/04/2023 | 30 | A. L. ENGINEERING SOLUTION | 12.77 | 0 | 0 | 100
2328 | MALDAH | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 699/MLMD | 10/04/2023 | 61 | SUBRATA SAHA | 0.29 | 0 | 0 | 100
2329 | MALDAH | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Claim for purchase of fuel for hiring of inspection for different site visit use for Assistant Engineer-II ,Under Mechanical Division, P.H.E. Dte. | 270/MLMD. | 24/02/2023 | 59 | SUBRATA SAHA | 0.44 | 0 | 0 | 100
2330 | MALDAH | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Claim for purchase of fuel for hiring of inspection for different site visit use for Assistant Engineer-II ,Under Mechanical Division, P.H.E. Dte. | 699/MLMD. | 10/04/2023 | 7 | SUBRATA SAHA | 0.46 | 0 | 0 | 100
2331 | MALDAH | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 270/MLMD | 24/02/2023 | 59 | SUBRATA SAHA | 0.29 | 0 | 0 | 100
2332 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Material Requisition To Resource Division | 1873/MD | 16/08/2022 | 0 | Resource Division | 132.02 | 0 | 0 | 0
2333 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Placement of fund against the work for Road restoration work for laying of pipe line for Bamongala Habibpur Road (Portion from 7.00 kmp to 7.50 kmp) for Mirzapur Piped Water Supply Scheme under Malda Division, PHE Dte. | BP-2022-23-211 | 16/03/2023 | 0 | EXECUTIVE ENGINEER, MALDA HIGHWAY DIVISION, P.W. (ROADS) DIRECTORATE. | 3.11 | 0 | 0 | 0
2334 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Formal work order for the work of Construction of 600 M3 Capacity OHR with FHTC (Mouza- Jaitan, Mirzapur, Mukuli and Salalpur) of Mirzapur Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2917/MD | 31/07/2023 | 668 | MATIUR RAHAMAN | 281.67 | 0 | 0 | 89
2335 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 120 m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Head Work Site of Mirzapur Water Supply Scheme of Bamangola Block under Malda Division P.H.E Dte in the District of Malda. | 5740/MD | 20/11/2024 | 120 | DEBAPRIYA SAHA | 45.31 | 0 | 0 | 0
2336 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) and Laying of 90 mm dia (OD) uPVC Pipeline under command area of MIRZAPUR Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 3026/MD | 13/06/2024 | 261 | M/S KUNDU CONSTRUCTION | 89.01 | 0 | 0 | 90
2337 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Construction of Boundary Wall at 4th Tubewell Site of Mirzapur Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | 3949/MD | 07/08/2024 | 45 | HIRAK ROY CHOUDHURY | 7.45 | 0 | 0 | 0
2338 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Formal work order for the work of Laying Distribution pipe line for MIRZAPUR & its adjoining mouzas piped water supply at Bamongola Block in the District Malda under Malda Division, PHE Dte. | 1747/MD | 27/07/2022 | 60 | UTTAM KUMAR DUTTA | 163.77 | 0 | 0 | 100
2339 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to tubewell No 4 at Mirzapur PWSS of Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | 3395/MD | 31/08/2023 | 45 | SARANGA SARKAR | 4.17 | 0 | 0 | 100
2340 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Dismentling of Concrete road and Construction the same at different places of road connecting to LDS of Augmentation of MIRZAPUR Water Supply Scheme at Bamangola Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. | 2921/MD | 10/06/2024 | 30 | UTTAM KUMAR DUTTA | 12.53 | 0 | 0 | 100
2341 | MALDAH | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of augmentation of MIRZAPUR Water Supply Scheme T/W no. III in the District of Malda under Malda Mechanical Division, PHE Dte. | 2951/MLMD | 28/12/2022 | 1080 | M/S D.G.B. ENTERPRISE. | 11.25 | 0 | 0 | 1
2342 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Laying of Rising Main including Specials and Valves for Mirzapur Piped Water Supply Scheme at Bamongola Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2617/MD | 02/06/2025 | 45 | ANJIMA CONSTRUCTION CO. | 13.72 | 0 | 0 | 0
2343 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Augmentation work of Pump Houses and Boundary Walls with New Construction of Boundary wall and Pump House (5.40x3.60 m) at Head work site of MIRZAPUR Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2413/MD | 27/05/2025 | 75 | MATIUR RAHAMAN | 38.45 | 0 | 0 | 0
2344 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Sinking of Tubewell No 3 at Mirzapur Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1220/MD | 26/03/2025 | 45 | BABLU MANDAL | 12.17 | 0 | 0 | 0
2345 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Sinking of Tubewell No 4 at Mirzapur Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1221/MD | 26/03/2025 | 45 | BABLU MANDAL | 12.04 | 0 | 0 | 0
2346 | MALDAH | Malda Division | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Emergent work for better functionally of existing FHTC connection on different diameter Pipeline for MIRZAPUR Piped Water Supply Scheme at Bamangola Dev. Block in the District Malda under Malda Division, PHE Dte. | 3628/MD | 24/07/2025 | 60 | SAJEDUR RAHAMAN | 8.76 | 0 | 0 | 0
2347 | MALDAH | Malda Mechanical | Augmentation of Mirzapur Piped Water Supply Scheme , SM/10317 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of augmentation of MIRZAPUR Water Supply Scheme T/W no. IV in the District of Malda under Malda Mechanical Division, PHE Dte. | 2952/MLMD | 28/12/2022 | 811 | DILIP MAHATO. | 11.25 | 0 | 0 | 78
2348 | MALDAH | Malda Division | KALUARI PWSS , SM/18427 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 5922/MD | 26/11/2024 | 45 | USHA ENTERPRISE | 21.7 | 0 | 0 | 0
2349 | MALDAH | Malda Division | KALUARI PWSS , SM/18427 | New | Construction of Boundary Wall at 3rd Tubewell Site of Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 1256//MD | 15/03/2024 | 30 | GOUTAM SAHA | 7.48 | 0 | 0 | 0
2350 | MALDAH | Malda Division | KALUARI PWSS , SM/18427 | New | Laying of Distribution system of Kaluari Piped Water Supply Scheme at Old Malda Block for west part of rail line of mouza Adatpur & Jhanjra of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 3190/MD | 27/06/2024 | 45 | EVEREST INFRATECH INC | 85.91 | 0 | 0 | 0
2351 | MALDAH | Malda Division | KALUARI PWSS , SM/18427 | New | Construction of Boundary Wall at 2nd Tubewell Site of Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 1255/MD | 15/03/2024 | 30 | CHARU CONSTRUCTION | 6.58 | 0 | 0 | 100
2352 | MALDAH | Malda Division | KALUARI PWSS , SM/18427 | New | Material Requisition To Resource Division | 819/MD | 21/02/2024 | 0 | Resource Division | 75.05 | 0 | 0 | 0
2353 | MALDAH | Malda Division | KALUARI PWSS , SM/18427 | New | Material Requisition To Resource Division | 357/MD | 16/01/2024 | 0 | Resource Division | 76.82 | 0 | 0 | 0
2354 | MALDAH | Malda Mechanical | KALUARI PWSS , SM/18427 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Kaluari, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2024-25-183 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 8.32 | 0 | 0 | 0
2355 | MALDAH | Malda Mechanical | KALUARI PWSS , SM/18427 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Kaluari, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte | BP-2024-25-181 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 6.18 | 0 | 0 | 0
2356 | MALDAH | Malda Mechanical | KALUARI PWSS , SM/18427 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Kaluari, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte | BP-2024-25-182 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 4.56 | 0 | 0 | 0
2357 | MALDAH | Malda Division | KALUARI PWSS , SM/18427 | New | Formal work order for the work of Implementation of KALUARI Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 3017/MD | 08/08/2023 | 994 | USHA ENTERPRISE | 709.22 | 0 | 0 | 76
2358 | MALDAH | Malda Mechanical | KALUARI PWSS , SM/18427 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I II & III and Making Compound Lighting arrangement and allied works at T/W No. I of Kaluari Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/018421) | 2755/MLMD | 14/08/2023 | 987 | HANNAN BUILDERS PVT. LTD. | 40.16 | 0 | 0 | 90
2359 | MALDAH | Malda Division | KALUARI PWSS , SM/18427 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 120m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at Kaluari Water Supply Scheme of Old Malda Block under Malda Division P.H.E Dte in the District of Malda. | 3964/MD | 07/08/2024 | 632 | USHA ENTERPRISE | 45.21 | 0 | 0 | 60
2360 | MALDAH | Malda Division | KALUARI PWSS , SM/18427 | New | Construction of Boundary Wall at Head Work site of Kaluari Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 2889/MD | 07/06/2024 | 177 | USHA ENTERPRISE | 19.58 | 0 | 0 | 100
2361 | MALDAH | Malda Division | PARAHAR PWSS , SM/18432 | New | Construction of Boundary Wall at Head Work site of Parahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 3228/MD | 28/06/2024 | 30 | HANNAN BUILDERS PVT. LTD. | 27.72 | 0 | 0 | 0
2362 | MALDAH | Malda Division | PARAHAR PWSS , SM/18432 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Parahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 5912/MD | 26/11/2024 | 45 | HANNAN BUILDERS PVT. LTD. | 71.72 | 0 | 0 | 0
2363 | MALDAH | Malda Division | PARAHAR PWSS , SM/18432 | New | Construction of Boundary Wall at 2nd Tube Well site of Parahar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 2956/MD | 10/06/2024 | 30 | HANNAN BUILDERS PVT. LTD. | 7.92 | 0 | 0 | 0
2364 | MALDAH | Malda Division | PARAHAR PWSS , SM/18432 | New | Material Requisition To Resource Division | 814/MD | 21/02/2024 | 0 | Resource Division | 47.82 | 0 | 0 | 0
2365 | MALDAH | Malda Division | PARAHAR PWSS , SM/18432 | New | Material Requisition To Resource Division | 239/MD | 10/01/2024 | 0 | Resource Division | 14.56 | 0 | 0 | 0
2366 | MALDAH | Malda Mechanical | PARAHAR PWSS , SM/18432 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Parahar, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-675 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 6.41 | 0 | 0 | 0
2367 | MALDAH | Malda Mechanical | PARAHAR PWSS , SM/18432 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Parahar, Pandua CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-674 | 11/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.86 | 0 | 0 | 0
2368 | MALDAH | Malda Division | PARAHAR PWSS , SM/18432 | New | Formal work order for the work of Implementation of PARAHAR Piped Water Supply Scheme at Gazole Dev. Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2951/MD | 02/08/2023 | 1115 | HANNAN BUILDERS PVT. LTD. | 1038.77 | 0 | 0 | 60
2369 | MALDAH | Malda Mechanical | PARAHAR PWSS , SM/18432 | New | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. I & II and Making Compound Lighting arrangement and allied works at T/W No. I of Parahar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | 3730/MLMD | 26/11/2024 | 307 | NABAUDYAG ELECTRICAL ENGINEERING CO-OPERATIV SOCIETY LTD. | 25.68 | 0 | 0 | 83
2370 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jotananta, Jotgopal kagmari, Meherapur and Birahimpur Zone Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11914 | Retrofitting | Sinking of 150mm. big dia. Tube Well of 60 Mtr. deep by Direct Rotary Rig method using UPVC (CM) Pipes & UPVC Medium Well Screen (RMS) Pipes with Ribs for Jote Gopal Kagmari Distribution Zone (Head Work Site) at Kaliachak-II Block under Malda Arsenic Area Water Supply Division , P.H.E. Dte., Malda | 1260/MAAD | 24/06/2024 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 4.79 | 0 | 0 | 100
2371 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) under command area of Jotananta, Jotgopal kagmari, Meherapur and Birahimpur Zone Water Supply Scheme at Kaliachak-II Block under Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11914 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
2372 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme , SM/06866 | Retrofitting | Extension of UPVC pipe line for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Dakshinpaka command area of MAHANANDAPUR Water Supply Scheme at Chanchal-I Block under Malda Division PHE Dte. | 3054MD | 09/08/2023 | 30 | M/S SRINJOYEE | 4.65 | 0 | 0 | 100
2373 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme , SM/06866 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme at Chanchal-I Block under Malda Division, PHE Dte. | 2714/MD | 10/11/2020 | 30 | NEOGI ENTERPRISE | 66.16 | 37.43 | 56.57 | 100
2374 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme , SM/06866 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Dakshinpaka command area of MAHANANDAPUR Water Supply Scheme at Chanchal-I Block under Malda Division PHE Dte. | 3052/MD | 09/08/2023 | 30 | M/S AYUSH BUILDERS | 7.85 | 0 | 0 | 100
2375 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of MAHANANDAPUR Water Supply Scheme , SM/06866 | Retrofitting | Material Requisition To Resource Division | 36/MD | 04/01/2024 | 0 | Resource Division | 1.58 | 0 | 0 | 0
2376 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PANNAPUR Water Supply Scheme , SM/06870 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PANNAPUR Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte. | 2712/MD | 10/11/2020 | 45 | NIRENDRA NATH KUNDU | 77.09 | 35.05 | 45.47 | 0
2377 | MALDAH | Malda Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of PANNAPUR Water Supply Scheme , SM/06870 | Retrofitting | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA ) under command area of Village- Purba Binodpur, JL. No. 44, G.P.-Pandua of PURBA BINODPUR Water Supply Scheme at Gazole Block under Malda Division, PHE Dte. | 2449/MD | 12/10/2020 | 30 | A. B. CONSTRUCTION | 11.75 | 10.86 | 100 | 0
2378 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block and Dakschin Chandipur Water Supply Scheme at Manikchak Block , SM/06848 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1066/MAAD | 14/10/2020 | 30 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 25.23 | 22.17 | 88.99 | 1
2379 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block and Dakschin Chandipur Water Supply Scheme at Manikchak Block , SM/06848 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Ramchandrapur Water Supply Scheme (Habitation- Ramnathpur) English Bazar Block under Malda Arsenic Area Water Supply Division, P.H.E Dte. | 2007/MAAD | 28/12/2021 | 45 | LABANYA ENGINEERS CO-OPERATIVE SOCIETY LTD. | 9.38 | 0 | 0 | 1
2380 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block and Dakschin Chandipur Water Supply Scheme at Manikchak Block , SM/06848 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of DAKSHIN CHANDIPUR Water Supply Scheme at Manikchak Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1121/MAAD | 09/11/2020 | 30 | BHOLANATH CONSTRUCTION | 57.22 | 54.97 | 100 | 0
2381 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of RAMCHANDRAPUR Water Supply Scheme at English Bazar Block and Dakschin Chandipur Water Supply Scheme at Manikchak Block , SM/06848 | Retrofitting | Laying of UPVC pipeline &Construction of Pavement & others Allied Work at Charianantapur W/S Scheme under Malda Arsenic Area W/S Divn.PHE. Dte. | 1060/MAAD | 03/08/2021 | 45 | BANIK BROTHERS | 4.78 | 0.03 | 100 | 0
2382 | MALDAH | Malda Division | Augmentation of Bulbulchandi PWSS. , SM/09422 | Augmentation | Material Requisition To Resource Division | 1105/MD | 17/05/2022 | 0 | Resource Division | 81.12 | 0 | 0 | 0
2383 | MALDAH | Malda Division | Augmentation of Bulbulchandi PWSS. , SM/09422 | Augmentation | Material Requisition To Resource Division | 1586/MD | 28/03/2023 | 0 | Resource Division | 6.43 | 0 | 0 | 0
2384 | MALDAH | Malda Division | Augmentation of Bulbulchandi PWSS. , SM/09422 | Augmentation | Submission of Bill for Hire Charges & HSD & Mobil charges of Vehicle No. - WB 04-H-8254 for the month of MAY, JUNE, JULY 2023 under Malda Division, PHE Dte. | BP-2023-24-157 | 18/08/2023 | 0 | SHABNAM ARA | 1.18 | 0 | 0 | 0
2385 | MALDAH | Malda Division | Augmentation of Bulbulchandi PWSS. , SM/09422 | Augmentation | Formal work order for the work of Augmentation of Bulbulchandi Piped water supply scheme for the work of Geotechnical Study,construction of 700 Cum RCC OHR,Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within Habibpur Block in the District of Malda under Malda Division, PH Engg Dte. | 1125/MD | 19/05/2022 | 365 | ACQUA CONSTRUCTION CONSORTIUM | 551.54 | 0 | 0 | 85
2386 | MALDAH | Malda Mechanical | Augmentation of Bulbulchandi PWSS. , SM/09422 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Augmentation of Bulbulchandi Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008161) | 2229/MLMD | 18/07/2023 | 120 | SUDIP DEY | 14.67 | 0 | 0 | 20
2387 | MALDAH | Malda Division | Augmentation of Bulbulchandi PWSS. , SM/09422 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) and Laying of 90 mm dia (OD) HDPE Pipeline under command area of AUGMENTATION of BULBULCHANDI Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 5741/MD | 20/11/2024 | 45 | MILLENNIUM ENTERPRISE | 86.38 | 0 | 0 | 0
2388 | MALDAH | Malda Division | Augmentation of Bulbulchandi PWSS. , SM/09422 | Augmentation | Dismentling of Concrete road and Construction the same at different places of road connecting to LDS of BULBULCHANDI Water Supply Scheme ( Mouza - Bulbulchandi, Soladanga) at Habibpur Dev. Block under Malda Division, P.H.E.Dte. In the district of Malda. | 3448/MD | 11/07/2024 | 45 | ACQUA CONSTRUCTION CONSORTIUM | 47.09 | 0 | 0 | 90
2389 | MALDAH | Malda Mechanical | Augmentation of Bulbulchandi PWSS. , SM/09422 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W No.- III of Bulbulchandi Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008161) | 596/MLMD | 30/03/2023 | 120 | PABITRA MANDAL | 10.76 | 0 | 0 | 70
2390 | MALDAH | Malda Division | Augmentation of Bulbulchandi PWSS. , SM/09422 | Augmentation | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 110 Mtr. Deep Big dia Tube well (1 Nos.) at BULBULCHANDI Water Supply Scheme under Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1672/MD | 18/04/2023 | 30 | A. L. ENGINEERING SOLUTION | 8.95 | 0 | 0 | 100
2391 | MALDAH | Malda Division | Augmentation of Bulbulchandi PWSS. , SM/09422 | Augmentation | Repairing of boundary wall and Land Development work corresponding to Tube Well No. 3 at BULBULCHANDI Piped Water Supply Scheme at Habibpur Block under Malda Division, PHE Dte, Govt. of West Bengal. | 657/MD | 08/02/2024 | 45 | M/S GHOSH CONSTRUCTION | 2.5 | 0 | 0 | 100
2392 | MALDAH | Malda Division | Augmentation of Bulbulchandi PWSS. , SM/09422 | Augmentation | Shifting of existing water pipeline of different dia (OD) HDPE Pipeline in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) due to New Culvert Construction along the road under command area of AUGMENTATION of BULBULCHANDI Water Supply Scheme at Habibpur Dev. Block under Malda Division, PHE Dte. in the district of Malda | 2682/MD | 04/06/2025 | 45 | ACQUA CONSTRUCTION CONSORTIUM | 5.61 | 0 | 0 | 0
2393 | MALDAH | Malda Division | Augmentation of Bulbulchandi PWSS. , SM/09422 | Augmentation | Providing Functional Household Tap Connection, Dismentling of Concrete road & Restoration and Laying of Rising Main including Specials & Valves for Bulbulchandi Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2761/MD | 09/06/2025 | 60 | ACQUA CONSTRUCTION CONSORTIUM | 86.98 | 0 | 0 | 0
2394 | MALDAH | Malda Mechanical | Augmentation of Bulbulchandi PWSS. , SM/09422 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of Augmentation for T/W no.- II of Bulbulchandi Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008161) | 2230/MLMD | 18/07/2023 | 604 | JOY MAA SANTOSHI ENTERPRISE. | 8.02 | 0 | 0 | 86
2395 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09646 | Retrofitting | Laying of HDPE pipe 20mm dia at Akandabaria, Chakdomai & Umakantatola under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 911/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.71 | 0 | 0 | 1
2396 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09646 | Retrofitting | Laying of HDPE pipe 20mm dia at Bahirbona,Milik sultanpur under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 912/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.67 | 0 | 0 | 1
2397 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09646 | Retrofitting | Laying of HDPE pipe 20mm dia at Suknagar,Fatepur under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 913/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.74 | 0 | 0 | 1
2398 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09646 | Retrofitting | Laying of UPVC pipe line 110mm,90mm&75mm dia at Bholaichak Raghunathtola, Domaichak Nayatola, Natun Shiv mandir para, Sahabajpur Budhamore, Sahabajpur Ghosh para,horismandal para balufaranad Sardaha & others Allied works at Bholaichak W/S scheme under Malda Arsenic Area water supply Divn PHE Dte. | 827/MAAD | 28/04/2022 | 45 | GOBINDA ENTERPRISE | 21.46 | 0 | 0 | 1
2399 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09646 | Retrofitting | Laying of HDPE pipe 20mm dia at Ragunath Tola,Attaramtola& Ramdhantola under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1835MAAD | 27/09/2022 | 30 | BANIK BROTHERS | 4.04 | 0 | 0 | 1
2400 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09646 | Retrofitting | Laying of HDPE pipe 20mm dia at Fetepur Chaipara,Nowda under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 914/MAAD | 10/05/2022 | 15 | BANIK BROTHERS | 4.81 | 0 | 0 | 1
2401 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09646 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA)at Balutola,Akandabaria,Charkatola,Pakakot,Umakanta,Nowda,Ramnagar,Domaichak ,Naldahari&Choyantola under command area of Bholaichak Water Supply Scheme Kaliachak-III Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 826/MAAD | 28/04/2022 | 60 | BANIK BROTHERS | 75.53 | 0 | 0 | 1
2402 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09646 | Retrofitting | Placing of diesel driven Car on hire basis for official use of the Assistant Engineer-II, Malda Arsenic Area W/S Division, PHE Dte. under Malda Arsenic Area W/S Division, PHE Dte.(Period from 01.01.2022 to 31.12.2022) | 2042/MAAD | 29/12/2021 | 365 | M/S PARIMAL DAS | 3.85 | 0 | 0 | 1
2403 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09646 | Retrofitting | Formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Bholaichak Water Supply Scheme (Bholaichak, Pakakot, Chakdomai, Sahabajpur Sailapur, Golapganj, Larchak, Chaklalu, Fatepur) at Kaliachak-III Block under Malda Arsenic Area Water Supply Division, P.H.E Dte. | 1994/MAAD | 27/12/2021 | 90 | BANIK BROTHERS | 128.52 | 0 | 0 | 1
2404 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09646 | Retrofitting | Laying of HDPE pipe 20mm dia at balutola,Kazichak & Srinibashpur under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1833/MAAD | 27/09/2022 | 30 | BANIK BROTHERS | 4.4 | 0 | 0 | 1
2405 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09646 | Retrofitting | Laying of HDPE pipe 20mm dia at Balufara,Banstola & Charkatola under Bholaichak water supply Zone of southern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 1834MAAD | 27/09/2022 | 30 | BANIK BROTHERS | 4 | 0 | 0 | 1
2406 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09646 | Retrofitting | Material Requisition To Resource Division | 195/MAAD | 11/02/2022 | 0 | Resource Division | 38.57 | 0 | 0 | 0
2407 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09646 | Retrofitting | Material Requisition To Resource Division | 1340/MAAD | 18/07/2022 | 0 | Resource Division | 7.01 | 0 | 0 | 0
2408 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Bholaichak Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Southern Sector) in Kaliachak-III , SM/09646 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
2409 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sattari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Blo , SM/09654 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Sattari Mouza of Sattari Piped Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1763/MAAD | 24/11/2021 | 60 | SUDIP DEY | 37.57 | 0 | 0 | 1
2410 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sattari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Blo , SM/09654 | Retrofitting | Laying of HDPE pipe 20mm dia at Mobarakpur , Basantapur under Sattari water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 966/MAAD | 11/05/2022 | 15 | SUDIP DEY | 4.74 | 0 | 0 | 1
2411 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sattari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Blo , SM/09654 | Retrofitting | Laying of HDPE pipe 20mm dia at Madapur , Masjidpara under Sattari water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 967/MAAD | 11/05/2022 | 15 | SUDIP DEY | 2.11 | 0 | 0 | 1
2412 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sattari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Blo , SM/09654 | Retrofitting | Laying of HDPE pipe 20mm dia at Sattari under Sattari water supply Zone of Northern Sector under Malda Arsenic Area W/S Division, PHE Dte. | 965/MAAD | 11/05/2022 | 15 | SUDIP DEY | 4.82 | 0 | 0 | 1
2413 | MALDAH | Malda Ars Area W/S Division | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) within the command area of Sattari Zone under Surface water based Malda Arsenic Area Water Supply Scheme (Northern Sector) in English Bazar Blo , SM/09654 | Retrofitting | Laying of clear water transmission main from existing WTPs (Mathurapur and Dariapur) to different zonal OHR sites of Manikchak and Kaliachak-III Block, construction of OHR on pile or raft foundation based on soil test report, laying of Distribution system and FHTC in Manikchak, Englishbazar, Kaliachak-I,II & III Blocks in the district of Malda. | 1524/MAAD | 14/08/2023 | 1031 | ECO PROTECTION ENGINEERS PRIVATE LIMITED | 23923.24 | 0 | 0 | 30
2414 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Eastern Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (72 nos. AWCs in English Bazar Block , SM/10233 | Anganwadi | Material Requisition To Resource Division | 328/MAAD | 28/02/2022 | 0 | Resource Division | 42.71 | 0 | 0 | 0
2415 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Eastern Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (72 nos. AWCs in English Bazar Block , SM/10233 | Anganwadi | Formal work order for Providing Drinking Water Supply in 45 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure-l ) | 1051/MAAD | 23/05/2022 | 90 | PRADIP KUMAR DAS | 319.21 | 0 | 0 | 80
2416 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Eastern Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (72 nos. AWCs in English Bazar Block , SM/10233 | Anganwadi | Formal work order for Providing Drinking Water Supply in 15 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 1101/MAAD | 03/06/2022 | 120 | MERCURY ENGINEERING COMPANY | 105.83 | 0 | 0 | 52
2417 | MALDAH | Malda Ars Area W/S Division | Providing Drinking Water Supply in Sourceless Anganwadi Centres (Eastern Part of English Bazar Block) Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units under the District of Malda (72 nos. AWCs in English Bazar Block , SM/10233 | Anganwadi | Providing Drinking Water Supply in 12 nos. Source Less Anganwadi Centers Through Solar Power Pump Based Water Supply Schemes with Arsenic Cum Iron Removal Units at Englishbazar Block & Municipality under Malda Arsenic Area W/S Division, P.H.E. Dte. (Name of Anganwadi Centers as per Annexure ) | 661/MAAD | 01/04/2022 | 120 | HANNAN BUILDERS PVT. LTD. | 84.7 | 0 | 0 | 100
2418 | MALDAH | Malda Division | INSTALLATION OF 105 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP -BAHIRGACHHI-I,PANDUA,MAJHRA,RANIGANJ-I & RANIGANJ-II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10303 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) at different Anganwadi Centres (AWCs) of G.P.- Bahirgachhi-I, Pandua, Majhra, Raniganj-I & Raniganj-II in Gazole Dev. Block, Malda under Malda Division, PHE Dte. | 1139/MD | 20/05/2022 | 120 | M/S TAPAS KUMAR CHAKRABORTY | 600.86 | 0 | 0 | 83
2419 | MALDAH | Malda Division | INSTALLATION OF 105 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP -BAHIRGACHHI-I,PANDUA,MAJHRA,RANIGANJ-I & RANIGANJ-II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10303 | Anganwadi | Acceptance cum formal work order for Supplying G.I. pipe strainer for installation of CWPP at AWC of G.P.- Bahirgachhi-I, Pandua, Majhra, Raniganj-I & Raniganj-II in Gazole Dev. Block at Mangalbari Stack Yard under Malda Division, PHE Dte.(Part-I) | 1434/MD | 20/06/2022 | 15 | M/S TAPAS KUMAR CHAKRABORTY | 18.82 | 0 | 0 | 100
2420 | MALDAH | Malda Division | INSTALLATION OF 105 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP -BAHIRGACHHI-I,PANDUA,MAJHRA,RANIGANJ-I & RANIGANJ-II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10303 | Anganwadi | Material Requisition To Resource Division | 518/MD | 03/03/2022 | 0 | Resource Division | 106.49 | 0 | 0 | 0
2421 | MALDAH | Malda Division | INSTALLATION OF 105 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP) AT ANGANWADI CENTRES(AWCs) OF GP -BAHIRGACHHI-I,PANDUA,MAJHRA,RANIGANJ-I & RANIGANJ-II IN GAZOLE DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10303 | Anganwadi | Material Requisition To Resource Division | 117/MD | 05/01/2024 | 0 | Resource Division | 7.74 | 0 | 0 | 0
2422 | MALDAH | Malda Mechanical | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Hiring of Inspection vehicle (Diesel driven) for official use of AE-II for the office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 1490/MLMD | 24/08/2021 | 6 | SUBRATA SAHA | 0.86 | 0 | 0 | 1
2423 | MALDAH | Malda Mechanical | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Modification & upgradation of electro-mechanical installation work at Pump House no.- I, Zone- I of Araidanga water supply scheme in the district of Malda under Malda Mechanical; Division, PHE Dte. | 306 /MLMD | 22/02/2022 | 30 | M/S MANABESH ROY | 7.87 | 0 | 0 | 1
2424 | MALDAH | Malda Mechanical | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Modification & upgradation of electro-mechanical installation work at Pump House no.- I, Zone- II of Araidanga water supply scheme in the district of Malda under Malda Mechanical; Division, PHE Dte. | 308 /MLMD. | 22/02/2022 | 30 | DEVI ENTERPRISE... | 8.26 | 0 | 0 | 1
2425 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 4th Tube Well site of Araidanga Zone-I Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | 1306/MD | 01/06/2022 | 30 | J. M. CONSTRUCTION | 4.76 | 0 | 0 | 0
2426 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Acceptance cum formal work order for Sinking of 01 (One) No. 250mm. Dia. x 150mm. Big dia. Tube Well 120 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Augmentation of Araidanga (Zone-I)Piped Water Supply Scheme under Malda Division, P.H.E. Dte. in the District of Malda. | 1396/MD | 14/06/2022 | 21 | SNEHASISH GHOSH | 6.91 | 0 | 0 | 0
2427 | MALDAH | Malda Mechanical | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Claim for purchase of fuel for hiring of inspection vehicle (diesel driven for official) Use month of November, 2021 to September,2022, of issuance of Fuel & Lubricant to Vehicles bearing nos i) W.B-65-C 8851 ii) W.B-65-C 4392, iii) W.B-65-D 5401 for the office of the Executive Engineer,Malda Mechanical Division, P.H.E. Dte. | 1808/MLMD | 26/10/2021 | 30 | SHAKTI FILLING STATION | 0.62 | 0 | 0 | 1
2428 | MALDAH | Malda Mechanical | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Modification & upgradation of electro-mechanical installation work at Pump House no.- II, Zone- I of Araidanga water supply scheme in the district of Malda under Malda Mechanical; Division, PHE Dte. | 307 /MLMD | 22/02/2022 | 30 | ANIMA ENTERPRISE | 7.91 | 0 | 0 | 1
2429 | MALDAH | Malda Mechanical | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Supply and delivery of Calcium hypochlorite tablets at Araidanga & adjacent water supply schemes in the district of Malda under Malda Mechanical Division, P.H.E. Dte. | 1667/MLMD | 22/09/2021 | 12 | DEY ENTERPRISE.. | 0.89 | 0 | 0 | 1
2430 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Placement of fund against the work for road restoration work for laying of pipe line for Aridanga Piped Water Supply Scheme under Malda Division, PHE Dte. | BP-2022-23-98 | 23/11/2022 | 0 | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 4.67 | 0 | 0 | 0
2431 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of ARAIDANGA (Zone-II) Pipe Water Supply Scheme at Ratua-II Block in the District of Malda under Malda Division P.H.E. Dte. | 1789/MD | 01/08/2022 | 60 | SUBHAS CHANDRA KESHARI | 163.59 | 0 | 0 | 1
2432 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Acceptance cum formal work order for Laying of Distribution pipe line in connection with Augmentation of Araidanga Zone-I ( node from J-69 to J-172, J-73 to 240, J-81 to 331, J-172 to J-73, 240 to J-191, 331 to J-69) Pipe Water Supply Scheme at Ratua-II Block in the District of Malda under Malda Division P.H.E. Dte. | 1932/MD | 23/08/2022 | 15 | SUBRATA SAHA | 6.17 | 0 | 0 | 1
2433 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Continuation work order for the work of Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licence contract carriage permit from Revisional Transport authority for office of the SE/NBC-II under Malda Division, PHE Dte. | 1248/NBC-II | 14/11/2022 | 180 | TARUN KUMAR BHATTACHARYA | 3.79 | 0 | 0 | 78
2434 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of ARIDANGA ZONE-I Piped Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. In the District of Malda. | 1477/MD | 30/03/2023 | 30 | CHARU CONSTRUCTION | 11.09 | 0 | 0 | 0
2435 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Material Requisition To Resource Division | 1872/MD | 16/08/2022 | 0 | Resource Division | 88.26 | 0 | 0 | 0
2436 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Material Requisition To Resource Division | 1606/MD | 11/04/2023 | 0 | Resource Division | 31.54 | 0 | 0 | 0
2437 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 124.23 | 0 | 0 | 0
2438 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Soil Investigation and design of substructure for Over Head Reservoirs for ARIDANGA ZONE-II Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. | BP-2022-23-199 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
2439 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Soil Investigation and design of substructure for Over Head Reservoirs for ARIDANGA ZONE-I Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. In the district of Malda. | BP-2022-23-197 | 09/03/2023 | 0 | INDIAN INSTITUTE OF ENGINEERING SCIENCE AND TECHNOLOGY SHIBPUR. | 2.95 | 0 | 0 | 0
2440 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Araidanga (Zone-I) Pipe Water Supply Scheme at Ratua-II Block in the District of Malda under Malda Division P.H.E. Dte. | 1784/MD | 01/08/2022 | 60 | USHA ENTERPRISE | 282.55 | 0 | 0 | 100
2441 | MALDAH | Malda Mechanical | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Supply, delivery, installation, commissioning and trial operation of electro-mechanical components of Augmentation of Araidanga Water Supply Scheme (Zone-I) TW no IV and external illumination works at Head Works Site(Zone-I&II) in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008180) | 2255/MLMD | 18/07/2023 | 120 | DAS CONSTRUCTION | 19.75 | 0 | 0 | 52
2442 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Acceptance cum formal work order for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of Augmentation of ARIDANGA ZONE-II Piped Water Supply Scheme at Ratua-II Block under Malda Division, PHE Dte. In the District of Malda. | 1476/MD | 30/03/2023 | 30 | UTTAM KUMAR GHOSH | 11.04 | 0 | 0 | 75
2443 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of NIJGANPARANPUR under Araidanga Zone-II Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 4772/MD | 05/12/2023 | 45 | J. M. CONSTRUCTION | 12.15 | 0 | 0 | 70
2444 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Additional Laying Distribution of UPVC Pipeline of Augmentation of ARAIDANGA ZONE-I Piped Water Supply Scheme at Ratua-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 5248/MD | 22/12/2023 | 45 | M/S JHA CONSTRUCTION | 31.99 | 0 | 0 | 80
2445 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Additional Laying Distribution of UPVC Pipeline of Augmentation of ARAIDANGA ZONE-II Piped Water Supply Scheme at Ratua-II Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 5250/MD | 22/12/2023 | 45 | M/S KUNDU CONSTRUCTION | 25.79 | 0 | 0 | 80
2446 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) under command area of ARAIDANGA ZONE-I Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 5249/MD | 22/12/2023 | 45 | CHARU CONSTRUCTION | 20.19 | 0 | 0 | 75
2447 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Village Uportola, Namotola, Radhanagar, Chunakhali and Paranpur under Aridanga Zone-II Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 155/MD | 08/01/2024 | 45 | GOALPARA CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED. | 12.15 | 0 | 0 | 70
2448 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Material Requisition To Resource Division | 38/MD | 04/01/2024 | 0 | Resource Division | 1.85 | 0 | 0 | 0
2449 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Material Requisition To Resource Division | 778/MD | 20/02/2024 | 0 | Resource Division | 1.23 | 0 | 0 | 0
2450 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Araidanga Zone-I Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | 5795/MD | 13/11/2025 | 60 | M/S JHA CONSTRUCTION | 110.7 | 0 | 0 | 0
2451 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Car-2) (Period from 01/02/2025 to 31/07/2025). | 377/MD | 31/01/2025 | 181 | SUBRATA SAHA | 0.86 | 0 | 0 | 0
2452 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Formal work order for the work of Construction of 400 M³ Capacity OHR with FHTC of ARIDANGA ZON-II Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the District of Malda. | 1649/MD | 13/04/2023 | 628 | UTTAM KUMAR GHOSH | 173.92 | 0 | 0 | 93
2453 | MALDAH | Malda Division | AUGMENTATION OF ARIADANGA PIPED WATER SUPPLY SCHEME , SM/10181 | Augmentation | Formal work order for the work of Construction of 900 M³ Capacity OHR with FHTC of Aridanga Zone-I Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte. in the District of Malda. | 1572/MD | 10/04/2023 | 365 | USHA ENTERPRISE | 338.37 | 0 | 0 | 92
2454 | MALDAH | Malda Division | INSTALLATION OF 62 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP)AT ANGANWADI CENTRES (AWCs) OF GP- RATUA,BAHARAL,KAHALA & DEBIPUR IN RATUA -I DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10305 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWCs at Kahala and Baharal GP of Ratua-I Dev. Block under Malda Division, PHE Dte. | 3196/MD | 27/12/2022 | 75 | KANAN CONSTRUCTION ENTERPRISE | 137.91 | 0 | 0 | 100
2455 | MALDAH | Malda Division | INSTALLATION OF 62 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP)AT ANGANWADI CENTRES (AWCs) OF GP- RATUA,BAHARAL,KAHALA & DEBIPUR IN RATUA -I DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10305 | Anganwadi | Material Requisition To Resource Division | 531/MD | 03/03/2022 | 0 | Resource Division | 37.83 | 0 | 0 | 0
2456 | MALDAH | Malda Division | INSTALLATION OF 62 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP)AT ANGANWADI CENTRES (AWCs) OF GP- RATUA,BAHARAL,KAHALA & DEBIPUR IN RATUA -I DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10305 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Debipur GP of Ratua-I Dev. Block under Malda Division, PHE Dte. | 38/MD | 16/01/2023 | 75 | MILLENNIUM ENTERPRISR | 114.95 | 0 | 0 | 100
2457 | MALDAH | Malda Division | INSTALLATION OF 62 Nos. STAND ALONE COMMUNITY PURIFICATION PLANT(CWPP)AT ANGANWADI CENTRES (AWCs) OF GP- RATUA,BAHARAL,KAHALA & DEBIPUR IN RATUA -I DEV BLOCK ,MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10305 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) for AWC's at Ratua GP of Ratua-I Dev. Block under Malda Division, PHE Dte. | 392/MD | 01/02/2023 | 75 | M/S TAPAS KUMAR CHAKRABORTY | 122.55 | 0 | 0 | 100
2458 | MALDAH | Malda Division | INSTALLATION OF 128 Nos. STANDALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-AIHO,BULBULCHANDI,KANTURKA,DHUMPUR,RISHIPUR& SRIRAMPUR IN HABIBPUR DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10306 | Anganwadi | Acceptance cum formal work order for Supplying G.I. pipe strainer for installation of CWPP at AWC of G.P.- Aiho, Bulbulchandi, Kanturka, Dhumpur, Rishipur & Srirampur in Habibpur Dev. Block at Mangalbari Stack Yard under Malda Division, PHE Dte. | 1501/MD | 28/06/2022 | 15 | MERCURY ENGINEERING COMPANY | 23.05 | 0 | 0 | 0
2459 | MALDAH | Malda Division | INSTALLATION OF 128 Nos. STANDALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-AIHO,BULBULCHANDI,KANTURKA,DHUMPUR,RISHIPUR& SRIRAMPUR IN HABIBPUR DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10306 | Anganwadi | Material Requisition To Resource Division | 526/MD | 03/03/2022 | 0 | Resource Division | 84.31 | 0 | 0 | 0
2460 | MALDAH | Malda Division | INSTALLATION OF 128 Nos. STANDALONE COMMUNITY PURIFICATION PLANT (CWPP)AT ANGANWADI CENTRES(AWCs) OF GP-AIHO,BULBULCHANDI,KANTURKA,DHUMPUR,RISHIPUR& SRIRAMPUR IN HABIBPUR DEV BLOCK MALDA UNDER MALDA DIVISION,PHE DTE. , SM/10306 | Anganwadi | Formal work order for the work of Installation of Stand-Alone Community Purification Plant (CWPP) at different Anganwadi Centres (AWCs) of G.P.- Aiho, Bulbulchandi, Kanturka, Dhumpur, Rishipur & Srirampur in Habibpur Dev. Block, Malda under Malda Division, PHE Dte. | 1136/MD | 20/05/2022 | 120 | M/S S. DAS & ENTERPRISE | 732.48 | 0 | 0 | 90
2461 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. , SM/10389 | School | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Pakuahat GP of Bamongola Dev. Block under Malda Division, PHE Dte. (QTY:- 8 Nos.) | 2678/MD | 17/11/2022 | 60 | M/S S. S. ENTERPRISE | 48.42 | 0 | 0 | 90
2462 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. , SM/10389 | School | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Bamongola GP of Bamongola Dev. Block under Malda Division, PHE Dte. (QTY:- 9 Nos.) | 2679/MD | 17/11/2022 | 60 | SOUNAK ENTERPRISE | 54.47 | 0 | 0 | 48
2463 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. , SM/10389 | School | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Gobindapur Moheshpur GP of Bamongola Dev. Block under Malda Division, PHE Dte. (QTY:- 10 Nos.) | 3111/MD | 20/12/2022 | 60 | FIDERE MARINE SERVICES PRIVATE LIMITED | 60.57 | 0 | 0 | 82
2464 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. , SM/10389 | School | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Jogdala GP of Bamongola Dev. Block under Malda Division, PHE Dte. (QTY:- 5 Nos.) | 2681/MD | 17/11/2022 | 60 | M/S AMIT KUMAR GUPTA | 30.27 | 0 | 0 | 90
2465 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. , SM/10389 | School | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Chandpur GP of Bamongola Dev. Block under Malda Division, PHE Dte. (QTY:- 6 Nos.) | 2682/MD | 17/11/2022 | 60 | M/S JHA CONSTRUCTION | 36.33 | 0 | 0 | 90
2466 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. , SM/10389 | School | Material Requisition To Resource Division | 722/MD | 25/03/2022 | 0 | Resource Division | 31.32 | 0 | 0 | 0
2467 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. , SM/10389 | School | Acceptance cum formal work order for Installation of Stand-Alone Community Purification Plant (CWPP) for Schools at Madnaboti GP of Bamongola Dev. Block under Malda Division, PHE Dte. (QTY:- 9 Nos.) | 2680/MD | 17/11/2022 | 60 | M/S S. S. ENTERPRISE | 54.47 | 0 | 0 | 91
2468 | MALDAH | Malda Division | Installation of Stand-Alone Community Purification Plant at Schools(50 nos) of Bamangola Dev. Block, Malda under Malda Division, PHE Dte. , SM/10389 | School | Material Requisition To Resource Division | 119/MD | 05/01/2024 | 0 | Resource Division | 13.26 | 0 | 0 | 0
2469 | MALDAH | Malda Mechanical | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. IV of Maheshpur, Mokdumpur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte | 3004405173 | 28/08/2023 | 90 | W.B.S.E.D.C.LTD | 7.66 | 0 | 0 | 100
2470 | MALDAH | Malda Division | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Material Requisition To Resource Division | 1810/MD | 27/04/2023 | 0 | Resource Division | 28.61 | 0 | 0 | 0
2471 | MALDAH | Malda Division | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 28.61 | 0 | 0 | 0
2472 | MALDAH | Malda Division | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Formal work order for the work of Augmentation of MAHESHPUR Piped water supply scheme for the work of Geotechnical Study,construction of 600 Cum RCC OHR, Laying Distribution of pipe line and providing Functional Household Tap connection (FHTC) within English Bazar Block under Malda Division PH Engg.Dte. In the District of Malda . | 3179/MD | 23/12/2022 | 1121 | M/S NIRAPADA BHATTACHARJEE | 631.46 | 0 | 0 | 95
2473 | MALDAH | Malda Mechanical | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Supply, installation and commissioning of electro-mechanical components at T/W no. II of Augmentation of Maheshpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | 808/MLMD | 15/02/2024 | 682 | BEE GEE CONSTRUCTION. | 12.42 | 0 | 0 | 35
2474 | MALDAH | Malda Division | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Construction of 5.40 mtr.X 3.6mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement at Head Work site at Maheshpur PWSS of Englishbazar Block under Malda Division, PHE Dte, Govt. of West Bengal. | 3396/MD | 31/08/2023 | 45 | SADHANA CONSTRUCTION | 6.52 | 0 | 0 | 100
2475 | MALDAH | Malda Division | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Construction of Boundary Wall at Head Work Site of MAHESHPUR Piped Water Supply Scheme at Englishbazar Block under Malda Division, P.H.E.Dte. in the District of Malda. | 378/MD | 17/01/2024 | 288 | M/S SRINJOYEE | 15.94 | 0 | 0 | 100
2476 | MALDAH | Malda Division | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Additional Laying of Distribution pipe line of MAHESHPUR Water Supply Scheme under Malda Division PHE. Dte in The District of Malda. | 388/MD | 17/01/2024 | 313 | DEBAPRIYA SAHA | 37.78 | 0 | 0 | 100
2477 | MALDAH | Malda Division | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Material Requisition To Resource Division | 823/MD | 21/02/2024 | 0 | Resource Division | 17.76 | 0 | 0 | 0
2478 | MALDAH | Malda Division | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Laying of Rising Main including Specials and Valves for MAHESHPUR Piped Water Supply Scheme at Englishbazar Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 387/MD | 17/01/2024 | 450 | S. N. CONSTRUCTION | 19.15 | 0 | 0 | 35
2479 | MALDAH | Malda Division | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 135m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Maheshpur Water Supply Scheme of Englishbazar Block under Malda Division P.H.E Dte in the District of Malda. | 2926/MD | 10/06/2024 | 295 | MERCURY ENGINEERING COMPANY | 47.11 | 0 | 0 | 18
2480 | MALDAH | Malda Division | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Maheshpur Water Supply Scheme under Englishbazar Block under Malda Division, PHE Dte. in the district of Malda. | 25/MD | 06/01/2025 | 360 | M/S STAR INDIA CONSTRUTION | 60.76 | 0 | 0 | 85
2481 | MALDAH | Malda Division | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Augmentation work of Construction of Boundary Wall at Head Work site of MAHISHBATHANI Water Supply Scheme under Old Malda Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 2411/MD | 27/05/2025 | 75 | M/S EHAN ENTERPRISE | 10.94 | 0 | 0 | 0
2482 | MALDAH | Malda Division | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and laying of 90 mm OD diameter UPVC Pipeline under command area of Augmentation of Maheshpur Piped Water Supply Scheme at Englishbazar Dev. Block in the District Malda under Malda Division, PHE Dte. | 3630/MD | 24/07/2025 | 60 | M/S STAR INDIA CONSTRUTION | 70.86 | 0 | 0 | 0
2483 | MALDAH | Malda Division | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Acceptance cum formal work order for Sinking of 300 mm. Dia. x 200 mm. dia. and 95 Mtr. Deep Big dia Tube well (2 No) at MAHESHPUR Water Supply Scheme under English Bazar Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 921/MD | 27/02/2023 | 555 | ASHIS CONSTRUCTION | 21.48 | 0 | 0 | 100
2484 | MALDAH | Malda Mechanical | Augmentation of Maheshpur piped water supply scheme , SM/12362 | Augmentation | Supply, installation and commissioning of electro-mechanical components at T/W no. I of Augmentation of Maheshpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/005106) | 2262/MLMD | 18/07/2023 | 592 | SUDIP DEY | 12.42 | 0 | 0 | 100
2485 | MALDAH | Malda Division | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 3rd Tube Well site of Kushida Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | 1195/MD | 24/05/2022 | 31 | RANJIT ADHIKARY | 4.8 | 0 | 0 | 0
2486 | MALDAH | Malda Division | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Acceptance cum formal work order for Construction of 3.6mtr.X 3.0mtr Switch Room cum chlorine room with Water Supply and sanitary arragement at 4th Tube Well site of Kushida Water Supply Scheme under Malda Division, PHE Dte. In the District of Malda. | 1196/MD | 24/05/2022 | 31 | RAHANUL ALAM | 4.8 | 0 | 0 | 1
2487 | MALDAH | Malda Division | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 51.58 | 0 | 0 | 0
2488 | MALDAH | Malda Division | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Material Requisition To Resource Division | 115/MD | 05/01/2024 | 0 | Resource Division | 13.49 | 0 | 0 | 0
2489 | MALDAH | Malda Division | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Formal work order for the work of Laying of Distribution pipe line in connection with Augmentation of Kushida Pipe Water Supply Scheme at Harishchandrapur-I Block in the District of Malda under Malda Division P.H.E. Dte. | 1568/MD | 10/04/2023 | 1087 | SUBHAS CHANDRA KESHARI | 434.18 | 0 | 0 | 87
2490 | MALDAH | Malda Division | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Formal work order for the work of Construction of 700 M3 Capacity OHR with Soil Investigation and FHTC of Kushida Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1569/MD | 10/04/2023 | 982 | SUBHAS CHANDRA KESHARI | 333.31 | 0 | 0 | 65
2491 | MALDAH | Malda Mechanical | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Supply, installation, and commissioning of electro-mechanical components at T/W no. III & IV of Augmentation of Khusida Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/008174) | 3686/MLMD | 29/11/2023 | 669 | KARMAKAR CONSTRICTION. | 25.1 | 0 | 0 | 100
2492 | MALDAH | Malda Division | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Laying of Distribution pipe line in connection with Augmentation of Uttar Rampur Mouza (JL-36) under KUSHIDA Piped Water Supply Scheme at Harishchandrapur-I Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 5324/MD | 27/12/2023 | 60 | SUBHAS CHANDRA KESHARI | 91.57 | 0 | 0 | 50
2493 | MALDAH | Malda Mechanical | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Continuation work- Hiring of Inspection vehicle (Diesel driven) for official use of Assistant Engineer-II under office of the Executive Engineer, Malda Mechanical Division, P.H.E. Dte. | 3517/MLMD | 30/10/2024 | 61 | SUBRATA SAHA | 0.78 | 0 | 0 | 100
2494 | MALDAH | Malda Division | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kushida Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 81 | 13/01/2025 | 45 | SUBHAS CHANDRA KESHARI | 78.22 | 0 | 0 | 0
2495 | MALDAH | Malda Division | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 06/02/2024 to 30/06/2024). | 589/MD | 02/02/2024 | 146 | M/S FOUR STAR CONSTRUCTION | 0.71 | 0 | 0 | 0
2496 | MALDAH | Malda Division | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Erection of Property board related to Jal Jeevan Mission works of Khusida, Bhingol, Uttar Harishandrapur, Dakshin Mahendrapur, Konar, Rangaipur PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte. in the district of Malda. | 645/MD | 19/02/2025 | 7 | RAHANUL ALAM | 0.95 | 0 | 0 | 100
2497 | MALDAH | Malda Division | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at KUSHIDA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 581/MD | 02/02/2024 | 417 | RAHANUL ALAM | 4.19 | 0 | 0 | 95
2498 | MALDAH | Malda Division | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 4 at KUSHIDA Piped Water Supply Scheme under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 582/MD | 02/02/2024 | 273 | SR ENTERPRISE | 4.19 | 0 | 0 | 95
2499 | MALDAH | Malda Division | Augmentation of Khusida Piped Water Supply Scheme , SM/10397 | Augmentation | Sinking of 250mm. Dia. x 150 mm. Big dia. Tube Well of 150m Deep at 3rd Tubewell site of Kushida PWSS under Harishchandrapur-I Block under Malda Division, PHE Dte, Govt. of West Bengal. | 3451/MD | 11/07/2024 | 227 | SAUDAGAR INDIA | 10.14 | 0 | 0 | 90
2500 | MALDAH | Malda Division | PUTIA PWSS , SM/12194 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. dia. and 150 Mtr. Deep Big dia Tube well (1 No) at PUTIA Water Supply Scheme under Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 926/MD | 27/02/2023 | 30 | DUTTA ENTERPRISE | 10.13 | 0 | 0 | 100
2501 | MALDAH | Malda Mechanical | PUTIA PWSS , SM/12194 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of Putia, Harishchandrapur C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004353826 | 20/07/2023 | 90 | W.B.S.E.D.C.LTD | 3.3 | 0 | 0 | 100
2502 | MALDAH | Malda Division | PUTIA PWSS , SM/12194 | New | Material Requisition To Resource Division | 1609/MD | 11/04/2023 | 0 | Resource Division | 0.81 | 0 | 0 | 0
2503 | MALDAH | Malda Division | PUTIA PWSS , SM/12194 | New | Acceptance cum formal work order for Implementation of PUTIA Piped Water Supply Scheme at Harishchandrapur-II Block of Malda district under Malda Division, PHE Dte. | 593/MD | 09/02/2023 | 90 | PARIJAT RAY | 41.34 | 0 | 0 | 95
2504 | MALDAH | Malda Mechanical | PUTIA PWSS , SM/12194 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I and making compound lighting arrangement at T/W no. I of Putia Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013011) | 2327/MLMD | 26/07/2023 | 120 | NEOGI ENTERPRISE. | 13.5 | 0 | 0 | 78
2505 | MALDAH | Malda Division | PUTIA PWSS , SM/12194 | New | Material Requisition To Resource Division | 3918/MD | 06/08/2024 | 0 | Resource Division | 0.22 | 0 | 0 | 0
2506 | MALDAH | Malda Division | PUTIA PWSS , SM/12194 | New | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Putia Water Supply Scheme under Harishchandrapur-II Block under Malda Division, PHE Dte. in the district of Malda. | 57 | 08/01/2025 | 45 | CHOWDHURY CONSTRUCTION | 1.61 | 0 | 0 | 0
2507 | MALDAH | Malda Division | CHAKSUKUR PIPED WATER SUPPLY SCHEME. , SM/13719 | New | Material Requisition To Resource Division | 1582/MD | 10/04/2023 | 0 | Resource Division | 17.4 | 0 | 0 | 0
2508 | MALDAH | Malda Division | CHAKSUKUR PIPED WATER SUPPLY SCHEME. , SM/13719 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 25.7 | 0 | 0 | 0
2509 | MALDAH | Malda Mechanical | CHAKSUKUR PIPED WATER SUPPLY SCHEME. , SM/13719 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Chaksukur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013215) | 2313/MLMD | 26/07/2023 | 707 | JAL PRAVAHIKA PVT. LTD. | 29.64 | 0 | 0 | 75
2510 | MALDAH | Malda Division | CHAKSUKUR PIPED WATER SUPPLY SCHEME. , SM/13719 | New | Construction of Boundary Wall at Head Work Site of Chaksukur Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 5833/MD | 22/11/2024 | 45 | HANNAN BUILDERS PVT. LTD. | 19.53 | 0 | 0 | 0
2511 | MALDAH | Malda Division | CHAKSUKUR PIPED WATER SUPPLY SCHEME. , SM/13719 | New | Construction of Boundary Wall at 2nd Tube well site of Chaksukur Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 6203/MD | 09/12/2024 | 45 | HANNAN BUILDERS PVT. LTD. | 8.68 | 0 | 0 | 0
2512 | MALDAH | Malda Mechanical | CHAKSUKUR PIPED WATER SUPPLY SCHEME. , SM/13719 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of CHAKSUKUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-423 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 6.75 | 0 | 0 | 0
2513 | MALDAH | Malda Mechanical | CHAKSUKUR PIPED WATER SUPPLY SCHEME. , SM/13719 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of CHAKSUKUR, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-422 | 04/01/2024 | 0 | W.B.S.E.D.C.LTD | 3.54 | 0 | 0 | 0
2514 | MALDAH | Malda Division | CHAKSUKUR PIPED WATER SUPPLY SCHEME. , SM/13719 | New | Placement of fund against the work for road restoration for laying pipe line for Bulbulchandi- Katlapukur road from 11.645 KM to 13.904 Km and Nimbari to Harishchandrapur road from 0.00 KM to 0.889 KM under Kadirpur and Chaksukur PWSS under Malda Division,PHE Dte. | BP-2024-25-251 | 10/09/2024 | 0 | EXECUTIVE ENGINEER, PUBLIC WORKS (ROADS) DIRECTORATE. | 14.42 | 0 | 0 | 0
2515 | MALDAH | Malda Division | CHAKSUKUR PIPED WATER SUPPLY SCHEME. , SM/13719 | New | Formal work order for the work of Implementation of CHAKSUKUR Piped Water Supply at Habibpur Dev. Block in the District Malda under Malda Division, PHE Dte. Govt. of West Bengal. | 1035/MD | 13/03/2023 | 897 | HANNAN BUILDERS PVT. LTD. | 880.48 | 0 | 0 | 40
2516 | MALDAH | Malda Division | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14420 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Khatil Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte. | 1304/MD | 23/03/2023 | 45 | A. L. ENGINEERING SOLUTION | 4.18 | 0 | 0 | 0
2517 | MALDAH | Malda Division | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14420 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 150.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at KHATIL Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | 1432/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 7.56 | 0 | 0 | 100
2518 | MALDAH | Malda Division | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14420 | Augmentation | Construction of Boundary Wall of Khatil Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | 1181/MD | 14/03/2024 | 30 | M/S EHAN ENTERPRISE | 10.2 | 0 | 0 | 0
2519 | MALDAH | Malda Division | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14420 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Khatil Water Supply Scheme under Bamongola Block under Malda Division, PHE Dte. in the district of Malda. | 1182/MD | 14/03/2024 | 45 | S. N. CONSTRUCTION | 21.18 | 0 | 0 | 0
2520 | MALDAH | Malda Mechanical | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14420 | Augmentation | QUOTATION PAYMENT FOR KHATIL T/W III UNDER BAMONGOLA CCC UNDER MALDA DISTRICT | BP-2024-25-194 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 4.69 | 0 | 0 | 0
2521 | MALDAH | Malda Mechanical | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14420 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Khatil Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015034) | 2390/MLMD | 28/07/2023 | 714 | NEOGI ENTERPRISE. | 11.1 | 0 | 0 | 20
2522 | MALDAH | Malda Division | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14420 | Augmentation | Augmentation of Head work site Pump House, Pump House No.-2, Earth filling and 2 Nos. Boundary wall at Khatil Water Supply Scheme at Bamangola Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 296/MD | 29/01/2025 | 401 | M/S ROY CONSTRUCTION | 8.52 | 0 | 0 | 0
2523 | MALDAH | Malda Division | Source Augmentation of Khatil Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/14420 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage A.C /upvc pipe line by different dia UPVC pipe for KHATIL Piped Water Supply Scheme at Bamangola Dev. Block in the District of Malda under Malda Division, PHE Dte. | 414/MD | 02/02/2023 | 758 | M/S AMIT KUMAR GUPTA | 74.79 | 0 | 0 | 100
2524 | MALDAH | Malda Division | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15111 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 93.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at KADIRPUR Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | 1171/MD | 20/03/2023 | 30 | ABHIJIT PAUL | 6.23 | 0 | 0 | 100
2525 | MALDAH | Malda Division | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15111 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 4 ( 93.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at KADIRPUR Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | 1172/MD | 20/03/2023 | 30 | ABHIJIT PAUL | 6.23 | 0 | 0 | 100
2526 | MALDAH | Malda Mechanical | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15111 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Kadirpur , Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004397521 | 22/08/2023 | 90 | W.B.S.E.D.C.LTD | 6.08 | 0 | 0 | 100
2527 | MALDAH | Malda Mechanical | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15111 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No. IV of Kadirpur, Aiho C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004413382 | 05/09/2023 | 90 | W.B.S.E.D.C.LTD | 4.01 | 0 | 0 | 100
2528 | MALDAH | Malda Division | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15111 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for KADIRPUR Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte. | 1160/MD | 20/03/2023 | 45 | M/S AMIT KUMAR GUPTA | 73.06 | 0 | 0 | 90
2529 | MALDAH | Malda Division | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15111 | Augmentation | Acceptance cum formal work order for Construction of 2 (two) Nos 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Kadirpur Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte. | 1714/MD | 20/04/2023 | 45 | SHANKAR PRASAD BHAGAT | 8.32 | 0 | 0 | 100
2530 | MALDAH | Malda Mechanical | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15111 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III & IV of Kadirpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016285) | 2633/MLMD | 10/08/2023 | 180 | TARUN KUMAR DEY | 21.12 | 0 | 0 | 100
2531 | MALDAH | Malda Division | Source Augmentation of Kadirpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15111 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Kadirpur Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 5945/MD | 28/11/2024 | 277 | M/S SINHA ENTERPRISE | 26.03 | 0 | 0 | 0
2532 | MALDAH | Malda Division | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15091 | Augmentation | Acceptance cum formal work order for Laying of additional UPVC Pipe line in connection with Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme at Harishchandrapur II Block, under Malda Division, P.H.E. Dte. in the District of Malda. | 766/MD | 17/02/2023 | 30 | CHARU CONSTRUCTION | 11.7 | 0 | 0 | 100
2533 | MALDAH | Malda Division | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15091 | Augmentation | Interconnection between New Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2899/MD | 07/06/2024 | 30 | A. L. ENGINEERING SOLUTION | 2.11 | 0 | 0 | 0
2534 | MALDAH | Malda Division | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15091 | Augmentation | Acceptance cum formal work order for Sinking of 01(one) nos. 250mm. Dia. x 150mm. Big dia Tube Well 246 Mtr. deep by D.R. Rig method using UPVC pipe & Strainer in connection with Source Augmentation of UTTAR KUMEDPUR Piped Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | 1441/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 12.03 | 0 | 0 | 60
2535 | MALDAH | Malda Mechanical | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15091 | Augmentation | Quatation for new service connection at Uttar Kumedpur w/s sch. T/W no III UNDER MLMD. Dist Malda. (Harishchandrapur C. C. C) | BP-2023-24-526 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 13.78 | 0 | 0 | 0
2536 | MALDAH | Malda Mechanical | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15091 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. III of Uttar Kumedpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte.(TSM/017125) | 2629/MLMD | 10/08/2023 | 630 | SWAPAN ENTERPRISE, | 11.31 | 0 | 0 | 100
2537 | MALDAH | Malda Division | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15091 | Augmentation | Augmentation work of OHR, Pump House and Boundary Wall of Uttar Kumedpur Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 438/MD | 06/02/2025 | 75 | M/S T. K. CONSTRUCTION | 32.5 | 0 | 0 | 0
2538 | MALDAH | Malda Division | Source Augmentation of Uttar Kumedpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15091 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Uttar Kumedpur Piped Water Supply Scheme at Harishchandrapur-II Block of Malda District under Malda Division, PHE Dte. | 1299/MD | 23/03/2023 | 45 | SOFIKUL ISLAM | 4.19 | 0 | 0 | 95
2539 | MALDAH | Malda Division | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15106 | Augmentation | Acceptance cum formal work order for Extension of UPVC pipe line laying with Withdrawing and relaying of DI pipe line for Providing Functional Household Tap Connection (FHTC) in connection to Source Augmentation of Kendua PWSS, Chanchal I Block Malda Division PHE. Dte in The District of Malda. | 759/MD | 17/02/2023 | 30 | M/S /FAIZUL HAQUE BISWAS | 15.08 | 0 | 0 | 100
2540 | MALDAH | Malda Division | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15106 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well ( 250.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at Kendua Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | 1398/MD | 28/03/2023 | 30 | A. L. ENGINEERING SOLUTION | 12.62 | 0 | 0 | 100
2541 | MALDAH | Malda Division | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15106 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Kendua Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte. | 1197/MD | 21/03/2023 | 45 | RABIUL ISLAM | 4.18 | 0 | 0 | 100
2542 | MALDAH | Malda Mechanical | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15106 | Augmentation | New service connection at KENDUA PWSS T/W NO III Under EE/MLMD PHE DTE DIST. Malda.( CHANCHAL c c c) | BP-2024-25-471 | 28/08/2024 | 0 | W.B.S.E.D.C.LTD | 7.33 | 0 | 0 | 0
2543 | MALDAH | Malda Mechanical | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15106 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Kendua Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016529) | 2693/MLMD | 11/08/2023 | 715 | DAS CONSTRUCTION | 10.97 | 0 | 0 | 100
2544 | MALDAH | Malda Division | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15106 | Augmentation | Augmentation work of OHR, Pump House and Boundary Wall of Kendua Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1050/MD | 18/03/2025 | 75 | M/S DAS CONSTRUCTION | 31.92 | 0 | 0 | 0
2545 | MALDAH | Malda Division | Source Augmentation of Kendua Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15106 | Augmentation | Interconnection between new Tube Well and Existing UPVC/DI/HDPE pipe line in connection with Source Augmentation of Kendua Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte. Govt. of West Bengal. | 3231/MD | 28/06/2024 | 521 | M/S /FAIZUL HAQUE BISWAS | 12.28 | 0 | 0 | 100
2546 | MALDAH | Malda Division | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15110 | Augmentation | Acceptance cum formal work order for Extension of Pipe line by different dia UPVC pipe for PARAMESWARPUR Piped Water Supply Scheme at Bamangola Dev. Block of Malda District under Malda Division, PHE Dte. | 1209/MD | 21/03/2023 | 45 | SOVON KUMAR DAS | 29.32 | 0 | 0 | 80
2547 | MALDAH | Malda Division | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15110 | Augmentation | Acceptance cum formal work order for Sinking of ( 250mm. Dia. x 200mm. Dia ) Big dia Tube Well No - 4 (120.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe & Gravel Filter including supply of Materials at PARAMESWARPUR Water Supply Scheme of Bamongola Block under Malda Division P.H.E Dte in the District of Malda. (2nd Call) | 1430/MD | 29/03/2023 | 30 | ASHIS CONSTRUCTION | 8.85 | 0 | 0 | 100
2548 | MALDAH | Malda Division | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15110 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Parameswarpur Piped Water Supply Scheme at Bamangola Block of Malda District under Malda Division, PHE Dte. | 1305/MD | 23/03/2023 | 45 | A. L. ENGINEERING SOLUTION | 4.17 | 0 | 0 | 99
2549 | MALDAH | Malda Mechanical | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15110 | Augmentation | QUOTATION PAYMENT FOR Parameswarpur T/W III UNDER BAMONGOLA CCC UNDER MALDA DISTRICT | BP-2024-25-192 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 5.86 | 0 | 0 | 0
2550 | MALDAH | Malda Mechanical | Source Augmentation of Parameswarpur Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15110 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components of T/W no. IV of Parameswarpur Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte. (TSM/016354) | 2625/MLMD | 10/08/2023 | 541 | SOVON KUMAR DAS. | 12.73 | 0 | 0 | 100
2551 | MALDAH | Malda Mechanical | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15063 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at P/H No. III of Adhna PWSS, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004387448 | 18/08/2023 | 90 | W.B.S.E.D.C.LTD | 3.51 | 0 | 0 | 100
2552 | MALDAH | Malda Division | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15063 | Augmentation | Acceptance cum formal work order for Extension of Pipe line and replacing of damage uPVC pipe line by different dia UPVC pipe for ADHNA Piped Water Supply Scheme at Gazole Dev. Block of Malda District under Malda Division, PHE Dte. | 1181/MD | 21/03/2023 | 30 | GOBINDA ENTERPRISE | 40.5 | 0 | 0 | 90
2553 | MALDAH | Malda Division | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15063 | Augmentation | Acceptance cum formal work order for Sinking of ( 200mm. Dia. x 150mm. Dia ) Big dia Tube Well No - 3 ( 150.00 Mtr. deep ) by D.R. Rig method using P.V.C. pipe including supply of Materials at ADHNA Water Supply Scheme under Malda Division P.H.E Dte in the District of Malda. | 1173/MD | 20/03/2023 | 30 | JAYA ENTERPRISE | 7.56 | 0 | 0 | 100
2554 | MALDAH | Malda Division | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15063 | Augmentation | Acceptance cum formal work order for Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room with Water Supply and sanitary arrangement in connection with source Augmentation of Adhna Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte. | 1199/MD | 21/03/2023 | 45 | M/S GHOSH ENTERPRISE | 4.17 | 0 | 0 | 100
2555 | MALDAH | Malda Mechanical | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15063 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Source Augmentation Adhna Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/016220) | 2718/MLMD | 14/08/2023 | 180 | JOY ENTERPRISE. | 10.67 | 0 | 0 | 100
2556 | MALDAH | Malda Division | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15063 | Augmentation | Augmentation of Head work site Pump House,Pump House No.-2 ,Earth filling and 2 Nos. Boundary wall at ADHNA Water Supply scheme at Gazole Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1115/MD | 21/03/2025 | 194 | GOBINDA ENTERPRISE | 7.83 | 0 | 0 | 0
2557 | MALDAH | Malda Division | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15063 | Augmentation | Replacement of 200 mm dia. all through Big Dia. Tube Well at Head Work site (150m Deep) by D.R. Rig. Method using P.V.C. pipe & filter including supply of materials of ADHNA Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. Govt. of West Bengal. | 2466/MD | 28/05/2025 | 60 | GOBINDA ENTERPRISE | 9.82 | 0 | 0 | 0
2558 | MALDAH | Malda Division | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15063 | Augmentation | Construction of Boundary Wall of Adhna Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 2267/MD | 21/05/2025 | 45 | M/S. B. K. ASSOCIATES | 10.13 | 0 | 0 | 0
2559 | MALDAH | Malda Division | Source Augmentation of Adhna Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15063 | Augmentation | Sinking of 200 mm (all through) Big Dia. Tube-Well NO-02 (170 ) M Deep by D.R Rig. Method using P.V.C pipe & Filter including supply of materials at ADHNA Water Supply Scheme of Gazol Block under Malda Division, PHE Dte, Govt. of West Bengal | 4812/MD | 13/09/2024 | 156 | A. D. D. ASSOCIATES | 10.6 | 0 | 0 | 100
2560 | MALDAH | Malda Division | MEHERPUR PIPED WATER SUPPLY SCHEME , SM/15222 | New | Acceptance cum formal work order for Sinking of 250mm. Dia. x 150 mm. Big dia. and 140 Mtr. deep Tube Well Drilling by Direct Rotary method with 150 mm dia upvc strainer of 30m length all complete including cost of aterials at Heads Work Site of MEHERPUR Water Supply Scheme at Old Malda Block of Malda District under Malda Division, PHE Dte. | 2511/MD | 03/11/2022 | 30 | A. D. D. ASSOCIATES | 9.34 | 0 | 0 | 100
2561 | MALDAH | Malda Division | MEHERPUR PIPED WATER SUPPLY SCHEME , SM/15222 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 4.83 | 0 | 0 | 0
2562 | MALDAH | Malda Division | MEHERPUR PIPED WATER SUPPLY SCHEME , SM/15222 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room corresponding to Tube Well No 3 at Meherpur Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 2888/MD | 07/06/2024 | 45 | MAA MANASA CONSTRUCTION | 4.15 | 0 | 0 | 0
2563 | MALDAH | Malda Division | MEHERPUR PIPED WATER SUPPLY SCHEME , SM/15222 | New | Construction of Boundary Wall at 3rd Tube well site of Meherpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 6199/MD | 09/12/2024 | 45 | J. M. CONSTRUCTION | 7.52 | 0 | 0 | 0
2564 | MALDAH | Malda Mechanical | MEHERPUR PIPED WATER SUPPLY SCHEME , SM/15222 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- II of Meherpur, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte | BP-2024-25-190 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.56 | 0 | 0 | 0
2565 | MALDAH | Malda Mechanical | MEHERPUR PIPED WATER SUPPLY SCHEME , SM/15222 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Meherpur, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-533 | 15/02/2024 | 0 | W.B.S.E.D.C.LTD | 18.21 | 0 | 0 | 0
2566 | MALDAH | Malda Mechanical | MEHERPUR PIPED WATER SUPPLY SCHEME , SM/15222 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- III of Meherpur, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte | BP-2024-25-191 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 5.84 | 0 | 0 | 0
2567 | MALDAH | Malda Division | MEHERPUR PIPED WATER SUPPLY SCHEME , SM/15222 | New | Formal work order for the work of Laying Distribution pipe line for MEHERPUR and its adjoining mouzas Piped Water Supply at Old Malda Dev. Block in the District Malda under Malda Division, PHE Dte. Govt. of West Bengal. | 1040/MD | 13/03/2023 | 1115 | GHOSH BROTHERS | 529.66 | 0 | 0 | 100
2568 | MALDAH | Malda Division | MEHERPUR PIPED WATER SUPPLY SCHEME , SM/15222 | New | Formal work order for the work of Implementation of MEHERPUR Piped Water Supply Scheme at Old Malda Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2683/MD | 13/07/2023 | 1051 | M/S S. D. ENTERPRISE | 307.58 | 0 | 0 | 75
2569 | MALDAH | Malda Mechanical | MEHERPUR PIPED WATER SUPPLY SCHEME , SM/15222 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I ,II & III and making compound lighting arrangement at T/W no. I of Meherpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/011828) | 2325/MLMD | 26/07/2023 | 926 | GHOSH BROTHERS... | 42.91 | 0 | 0 | 0
2570 | MALDAH | Malda Division | MEHERPUR PIPED WATER SUPPLY SCHEME , SM/15222 | New | Construction of Boundary Wall at 2nd Tube well site of Meherpur Water Supply Scheme under Old Malda Block under Malda Division, PHE Dte. in the district of Malda. | 6198/MD | 09/12/2024 | 90 | RAJIB MANI | 7.52 | 0 | 0 | 0
2571 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15149 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 60.79 | 0 | 0 | 0
2572 | MALDAH | Malda Mechanical | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15149 | Augmentation | QUOTATION PAYMENT FOR UTTARCHANDIPUR W/S TW NO XIII SCHEME UNDER MANIKCHAK CCC UNDER MALDA DISTRICT | BP-2024-25-436 | 07/08/2024 | 0 | W.B.S.E.D.C.LTD | 7.9 | 0 | 0 | 0
2573 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15149 | Augmentation | Formal work order for the work of Augmentation of UTTAR CHANDIPUR ZONE-III Piped Water Supply Scheme at Manikchak Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2708/MD | 14/07/2023 | 1175 | SOVON KUMAR DAS | 355.42 | 0 | 0 | 18
2574 | MALDAH | Malda Mechanical | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15149 | Augmentation | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-XIII and Arsenic Iron Removal Plant at Uttar Chandipur (Zone-III) Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/019388) | 2681/MLMD | 11/08/2023 | 540 | HANNAN BUILDERS PVT. LTD. | 62.63 | 0 | 0 | 40
2575 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15149 | Augmentation | Formal work order for the work of Providing Functional Household Tap Connection (FHTC) & rectification work in connection with Jal Jeevan Mission (JJM) at Uttar Chandipur Zone-III Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | 1104/MD | 20/03/2025 | 225 | SOVON KUMAR DAS | 93.26 | 0 | 0 | 0
2576 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15149 | Augmentation | Construction of Boundary Wall at Head Work Site of Uttar Chandipur Zone-III Water Supply Scheme under Manikchak Block under Malda Division, PHE Dte. in the district of Malda. | 3189/MD | 27/06/2024 | 584 | SOVON KUMAR DAS | 27.49 | 0 | 0 | 0
2577 | MALDAH | Malda Division | Augmentation of Uttar Chandipur Zone- III Piped Water Supply Scheme under Malda Division, PHE Dte. , SM/15149 | Augmentation | Sinking of (250mm. Dia. x 200 mm. dia.) Big dia. Tube Well (90 Mtr. Deep) for UTTAR CHANDIPUR ZONE-III Water Supply Scheme at Head Work Site of Manikchak Block of Malda District under Malda Division, PHE Dte. | 3056/MD | 09/08/2023 | 480 | A. L. ENGINEERING SOLUTION | 9.16 | 0 | 0 | 100
2578 | MALDAH | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME , SM/15188 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 11.34 | 0 | 0 | 0
2579 | MALDAH | Malda Mechanical | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME , SM/15188 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I,II & IV and making compund lighting arrangement at Head Work site of Augmentation of Aiho(zone-II) Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte.(TSM/017677) | 2634/MLMD | 10/08/2023 | 180 | MAA BHABOTARINE ENTERPRISE. | 31.38 | 0 | 0 | 15
2580 | MALDAH | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME , SM/15188 | Augmentation | Continuation work order for the work of Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Executive Engineer, Malda Division, PHE Dte. (Period from 01/05/2024 to 30/06/2024). | 1440/MD | 15/03/2024 | 61 | SHABNAM ARA | 0.29 | 0 | 0 | 100
2581 | MALDAH | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME , SM/15188 | Augmentation | Acceptance cum formal work order for Laying of Distribution system for Augmentation of AIHO ZONE-II Piped Water Supply Scheme at Habibpur Dev. Block of Malda District under Malda Division, PHE Dte., Govt. of West Bengal. | 1180/MD | 21/03/2023 | 45 | FUTURE | 81.51 | 0 | 0 | 34
2582 | MALDAH | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME , SM/15188 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at AIHO ZONE-2 Water Supply Scheme under Habibpur Block under Malda Division, PHE Dte. in the district of Malda. | 980/MD | 04/03/2024 | 298 | FUTURE | 32.22 | 0 | 0 | 100
2583 | MALDAH | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME , SM/15188 | Augmentation | Extension of Pipe line and replacing of damage A.C/uPVC pipe line by different dia UPVC pipe for Aiho Zone-II piped Water Supply scheme of Habibpur Block in the District of Malda under Malda Division, P.H.E.Dte. | 4821/MD | 13/09/2024 | 45 | FUTURE | 10.04 | 0 | 0 | 100
2584 | MALDAH | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME , SM/15188 | Augmentation | Augmentation of 3 Nos. Pump House at AIHO ZONE-2 Water Supply scheme at Habibpur Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 1117/MD | 21/03/2025 | 45 | RATAN KARMAKAR | 5.36 | 0 | 0 | 0
2585 | MALDAH | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME , SM/15188 | Augmentation | Acceptance cum formal work order for Laying of Rising main and Construction of Pump houses for Augmentation of AIHO ZONE-II Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 1396/MD | 28/03/2023 | 704 | UNITED FRIENDS UNEMPLOYED ENGG CO-OPE SOCEITY LTD | 13.01 | 0 | 0 | 100
2586 | MALDAH | Malda Division | AUMENTATION OF AIHO ZONE-II PIPED WATER SUPPLY SCHEME , SM/15188 | Augmentation | Construction of 150 cum capacity 20 mtr. Staging height RCC OHR and Providing Household Tap Connection (FHTC) for Augmentation of AIHO ZONE-II Piped Water Supply Scheme at Habibpur Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 4589/MD | 22/11/2023 | 465 | FUTURE | 90.61 | 0 | 0 | 60
2587 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED , SM/15141 | Augmentation | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM and JAL SWAPNA) under command area of Arapur Water Supply Scheme (Mouza- Jote, Arapur) extra pipe line at Ganipur, Jote and Ghoshpara village at Englishbazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 1829/MAAD | 27/09/2022 | 45 | BANIK BROTHERS | 2.46 | 0 | 0 | 1
2588 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED , SM/15141 | Augmentation | Laying UPVC pipe at Ghoshpara village for FHTC under Arapur W/S Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | 323/MAAD | 21/02/2023 | 60 | M/S RADHA KRISHNA ENTERPRISE | 3.2 | 0 | 0 | 100
2589 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED , SM/15141 | Augmentation | Laying UPVC pipe at Arapur village for FHTC under Arapur W/S Distribution Zone of Malda Arsenic Area Water Supply Division, PHE Dte, Malda. | 322/MAAD | 21/02/2023 | 60 | S. N. CONSTRUCTION | 8.05 | 0 | 0 | 100
2590 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED , SM/15141 | Augmentation | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Arapur village under command area of Arapur Water Supply Scheme at Englis Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 324/MAAD | 21/02/2023 | 60 | S. R. CONSTRUCTION | 8.42 | 0 | 0 | 100
2591 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED , SM/15141 | Augmentation | Sinking of 01 (One) Nos. 250mm. Dia. x 150mm. Big dia. Tube Well 150 Mtr. deep by Direct Rotary method using UPVC pipe & Strainer in connection with Source Augmentation of Arapur Piped Water Supply Scheme under Malda Arsenic Area W/S Division, P.H.E. Dte. in the District of Malda | 616/MAAD | 31/03/2023 | 45 | M/S DYNAMIC CONSTRUCTION | 7.47 | 0 | 0 | 100
2592 | MALDAH | Malda Mechanical | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED , SM/15141 | Augmentation | W.B.S.E.D.C.LTD Quotation charge at T/W No.III of Arapur , Fulbari C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte | 3004409400 | 31/08/2023 | 90 | W.B.S.E.D.C.LTD | 4.18 | 0 | 0 | 100
2593 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED , SM/15141 | Augmentation | Material Requisition To Resource Division | 1690/MAAD | 15/09/2023 | 0 | Resource Division | 9.79 | 0 | 0 | 0
2594 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED , SM/15141 | Augmentation | Providing remaining Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM ) at Ghoshpara village under command area of Arapur Water Supply Scheme at Englis Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 325/MAAD | 21/02/2023 | 60 | S. R. ENTERPRISE | 6.36 | 0 | 0 | 100
2595 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED , SM/15141 | Augmentation | Extension of Pipe line by different dia UPVC pipe for ARAPUR Water Supply Scheme of English Bazar Dev. Block under Malda Arsenic Area W/S Division, P.H.E.Dte. In the District of Malda. | 552/MAAD | 24/03/2023 | 60 | ACHARYYA CONSTRUCTION | 18.74 | 0 | 0 | 100
2596 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED , SM/15141 | Augmentation | Construction of 3.60 mtr X 3.00 Mtr. Bore Hole pump house for Tube well no-3 at Arapur Water Supply Scheme of English Bazar Block under Malda Arsenic Area W/S Division, P.H.E.Dte. | 478/MAAD | 22/03/2023 | 60 | GOALPARA CO OPTV LABOUR CONTRACT AND CONSTN COCIETY LIMITED | 5.32 | 0 | 0 | 100
2597 | MALDAH | Malda Mechanical | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED , SM/15141 | Augmentation | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. III of Souce augmentation of Arapur Water Supply Scheme in the District of Malda under Mechanical Division, PHE Dte.(TSM/017481) | 2616/MLMD | 10/08/2023 | 180 | S.G.ENTERPRISE | 11.52 | 0 | 0 | 100
2598 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED , SM/15141 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Arapur village under command area of Arapur Water Supply Scheme at Englis Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. | 301/MAAD | 11/03/2024 | 30 | GIRIDHARI CONSTRUCTION | 7.9 | 0 | 0 | 100
2599 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED , SM/15141 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning and 3 (three) months Trial Run and 40.00 M³/hr. capacity of Iron Elimination Plants (Pressure type) with provision of polishing unit and Construction of switch room for Arapur Water Supply Scheme at English Bazar Dev Block under Malda Arsenic Area W/S Division. (2nd Call) | 941/MAAD | 23/05/2023 | 180 | GOBINDA ENTERPRISE | 17.92 | 0 | 0 | 100
2600 | MALDAH | Malda Ars Area W/S Division | Source Augmentation of Arapur piped water supply scheme under Malda Arsenic Area w/s Division , PHED , SM/15141 | Augmentation | Construction of Boundary Wall at 3rd Pump House Site, Laying of distribution system and Providing FHTC at Arapur Water Supply Scheme at English Bazar Block under Malda Arsenic Area Water Supply Division, PHE Dte. (Part A & Part B) | 1701/MAAD | 19/11/2024 | 120 | ACHARYYA CONSTRUCTION | 20.59 | 0 | 0 | 100
2601 | MALDAH | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme , SM/15952 | Augmentation | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 50.88 | 0 | 0 | 0
2602 | MALDAH | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme , SM/15952 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 3 at Nashipur Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 656/MD | 08/02/2024 | 45 | RATAN KARMAKAR | 4.76 | 0 | 0 | 0
2603 | MALDAH | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme , SM/15952 | Augmentation | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room and dismantling abandoned pump house corresponding to Tube Well No 4 at Nashipur Piped Water Supply Scheme at Ratua-II Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 655/MD | 08/02/2024 | 45 | ISMAIL ENTERPRISE | 4.76 | 0 | 0 | 0
2604 | MALDAH | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme , SM/15952 | Augmentation | Construction of Boundary Wall at 4th Tube Well site of Nasipur Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | 3954/MD | 07/08/2024 | 45 | RATAN KARMAKAR | 7.1 | 0 | 0 | 0
2605 | MALDAH | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme , SM/15952 | Augmentation | Material Requisition To Resource Division | 833/MD | 21/02/2024 | 0 | Resource Division | 12.62 | 0 | 0 | 0
2606 | MALDAH | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme , SM/15952 | Augmentation | Material Requisition To Resource Division | 3992/MD | 08/08/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
2607 | MALDAH | Malda Mechanical | Augmentation of Nasipur Piped Water Supply Scheme , SM/15952 | Augmentation | New service connection at NASIPUR Pwss pH NO I Under EE/MLMD PHE DTE DIST. Malda.(paranpur c c c) | BP-2023-24-706 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 8.02 | 0 | 0 | 0
2608 | MALDAH | Malda Mechanical | Augmentation of Nasipur Piped Water Supply Scheme , SM/15952 | Augmentation | New service connection at NASIPUR Pwss pH NO II Under EE/MLMD PHE DTE DIST. Malda.(paranpur c c c) | BP-2023-24-705 | 18/03/2024 | 0 | W.B.S.E.D.C.LTD | 5.69 | 0 | 0 | 0
2609 | MALDAH | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme , SM/15952 | Augmentation | Formal work order for the work of Augmentation of NASHIPUR Piped Water Supply Scheme at Ratua-II Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 2711/MD | 14/07/2023 | 806 | MANAS KUMAR SAHA | 452.36 | 0 | 0 | 70
2610 | MALDAH | Malda Mechanical | Augmentation of Nasipur Piped Water Supply Scheme , SM/15952 | Augmentation | Supply,delivery, installation and trial operation of Electro-Mechanical components and allied works at Ground Water Based Tubewell No-I, II, III & IV and Arsenic Iron Removal Plant at Nasipur Piped Water Supply Scheme in the district of Malda Under Malda Mechanical Division, PHE Dte. (TSM/011880) | 2821/MLMD | 17/08/2023 | 889 | DAS CONSTRUCTION | 79.67 | 0 | 0 | 57
2611 | MALDAH | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme , SM/15952 | Augmentation | Continuation work order for Hiring of inspection Vehicle (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for Official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. (Period from 16/02/2024 to 30/06/2024). | 717/MD | 09/02/2024 | 136 | M/S TEWARI CONSTRUCTION | 0.64 | 0 | 0 | 95
2612 | MALDAH | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme , SM/15952 | Augmentation | Erection of Property board related to Jal Jeevan Mission works of Nasipur, Ariadanga Zone-I & II, Pirpur PWSS under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | 662/MD | 19/02/2025 | 7 | J. M. CONSTRUCTION | 0.8 | 0 | 0 | 0
2613 | MALDAH | Malda Division | Augmentation of Nasipur Piped Water Supply Scheme , SM/15952 | Augmentation | Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Nasipur Water Supply Scheme under Ratua-II Block under Malda Division, PHE Dte. in the district of Malda. | 2251/MD | 21/05/2025 | 45 | MANAS KUMAR SAHA | 53.59 | 0 | 0 | 0
2614 | MALDAH | Malda Division | Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 house hold) of Old Malda Block of Malda District under Malda Division, PHE Dte. , SM/15960 | New | Construction of 3.60 mtr.X 3.00 mtr Switch Room cum chlorine room at Aihorani Piped Water Supply Scheme at Old Malda Dev. Block under Malda Division, PHE Dte, Govt. of West Bengal. | 650/MD | 08/02/2024 | 45 | PACIFIC ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 4.3 | 0 | 0 | 100
2615 | MALDAH | Malda Division | Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 house hold) of Old Malda Block of Malda District under Malda Division, PHE Dte. , SM/15960 | New | Material Requisition To Resource Division | 405/MD | 18/01/2024 | 0 | Resource Division | 0.65 | 0 | 0 | 0
2616 | MALDAH | Malda Mechanical | Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 house hold) of Old Malda Block of Malda District under Malda Division, PHE Dte. , SM/15960 | New | W.B.S.E.D.C.LTD Quotation charge at TW No- I of Aihorani, Old Malda CCC in the dist of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-625 | 04/03/2024 | 0 | W.B.S.E.D.C.LTD | 1.03 | 0 | 0 | 0
2617 | MALDAH | Malda Mechanical | Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 house hold) of Old Malda Block of Malda District under Malda Division, PHE Dte. , SM/15960 | New | Supply, installation and commissioning of electro-mechanical components at T/W no. I of Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 households) of Old Malda Block in the District of Malda under Malda Mechanical Division, PHE Dte. | 810/MLMD | 15/02/2024 | 180 | M/S SABANA CONSTRUCTION | 6.92 | 0 | 0 | 100
2618 | MALDAH | Malda Division | Aihorani Ground Water Based Mini Piped Water Supply Scheme (Maximum 100 house hold) of Old Malda Block of Malda District under Malda Division, PHE Dte. , SM/15960 | New | Acceptance cum formal work order for Implementation of AIHORANI Piped Water Supply Scheme at Old Malda Dev. Block of Malda district under Malda Division, PHE Dte. | 1500/MD | 30/03/2023 | 552 | PACIFIC ENGINEER'S CO-OPERATIVE SOCIETY LTD. | 37.17 | 0 | 0 | 90
2619 | MALDAH | Malda Division | ALINAGAR Piped Water Supply Scheme , SM/13431 | New | Placing of diesel driven vehicle on hire basis for official use of the office of the Assistant Engineer, Chanchal Sub-Division, PHE Dte. under Malda Division, PHE Dte. | 667/CSD | 29/12/2022 | 365 | SUDIPTA GHOSH | 0.85 | 0 | 0 | 37
2620 | MALDAH | Malda Mechanical | ALINAGAR Piped Water Supply Scheme , SM/13431 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No.I of Alinagar, Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004496764 | 28/11/2023 | 90 | W.B.S.E.D.C.LTD | 4.45 | 0 | 0 | 100
2621 | MALDAH | Malda Mechanical | ALINAGAR Piped Water Supply Scheme , SM/13431 | New | W.B.S.E.D.C.LTD Quotation charge at T/W No. II of Alinagar , Pandua C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | 3004496739 | 28/11/2023 | 90 | W.B.S.E.D.C.LTD | 4.01 | 0 | 0 | 100
2622 | MALDAH | Malda Division | ALINAGAR Piped Water Supply Scheme , SM/13431 | New | Continuation work order for Hiring of 1 no diesel vehicle in good condition (traffic worthily) having licensed contract carriage permit from Regional Transport Authority for office of the Superintending Engineer, North Bengal Circle-II, PHE Dte. (Period from 12/11/2023 to 09/05/2024=180 Days). | 4566/MD | 10/11/2023 | 180 | TARUN KUMAR BHATTACHARYA | 0.86 | 0 | 0 | 0
2623 | MALDAH | Malda Division | ALINAGAR Piped Water Supply Scheme , SM/13431 | New | Construction of Boundary Wall at Head Work site of Alinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 158/MD | 08/01/2024 | 45 | M/S N. N. ENTERPRISE | 14.51 | 0 | 0 | 100
2624 | MALDAH | Malda Division | ALINAGAR Piped Water Supply Scheme , SM/13431 | New | Construction of Boundary Wall at 2nd Tube Well Site of ALINAGAR Piped Water Supply Scheme at Gazole Dev. Block under Malda Division, PHE Dte. in the district of Malda. | 975/MD | 04/03/2024 | 45 | BANIK BROTHERS | 9.13 | 0 | 0 | 100
2625 | MALDAH | Malda Division | ALINAGAR Piped Water Supply Scheme , SM/13431 | New | Material Requisition To Resource Division | 122/MD | 06/01/2024 | 0 | Resource Division | 28.48 | 0 | 0 | 0
2626 | MALDAH | Malda Division | ALINAGAR Piped Water Supply Scheme , SM/13431 | New | Formal work order for the work of Implementation of ALINAGAR Water Supply Scheme at Gazole Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 940/MD | 27/02/2023 | 1220 | BANIK BROTHERS | 458.54 | 0 | 0 | 75
2627 | MALDAH | Malda Division | ALINAGAR Piped Water Supply Scheme , SM/13431 | New | Providing balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission (JJM) at Alinagar Water Supply Scheme under Gazole Block under Malda Division, PHE Dte. in the district of Malda. | 5408/MD | 21/10/2024 | 130 | BANIK BROTHERS | 36.94 | 0 | 0 | 0
2628 | MALDAH | Malda Division | ALINAGAR Piped Water Supply Scheme , SM/13431 | New | Sinking of Tubewell, Laying of Distribution Line, Providing FHTC, Construction of Pump House & Boundary wall at Alinagar Piped Water Supply Scheme at Gazol Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 2901/MD | 07/06/2024 | 353 | SUDIP DEY | 83.78 | 0 | 0 | 85
2629 | MALDAH | Malda Division | ALINAGAR Piped Water Supply Scheme , SM/13431 | New | Laying of Parallel/ Dedicated Pipeline for better Functionality at Alinagar Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 4348/MD | 10/09/2025 | 440 | BANIK BROTHERS | 26.97 | 0 | 0 | 0
2630 | MALDAH | Malda Mechanical | ALINAGAR Piped Water Supply Scheme , SM/13431 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Alinagar Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/015847) | 2381/MLMD | 28/07/2023 | 702 | M/S. KUNDU CONSTRACTION | 27.37 | 0 | 0 | 100
2631 | MALDAH | Malda Division | ALINAGAR Piped Water Supply Scheme , SM/13431 | New | Bamboo piing, earth filing for protection of pipe line at different places for Alinagar Piped Water Supply Scheme at Gazole Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 5624/MD | 06/11/2024 | 30 | BANIK BROTHERS | 8.66 | 0 | 0 | 100
2632 | MALDAH | Malda Division | PASCHIM BHAGABANPUR Piped Water Supply Scheme , SM/12188 | New | Material Requisition To Resource Division | 1811/MD | 27/04/2023 | 0 | Resource Division | 22.21 | 0 | 0 | 0
2633 | MALDAH | Malda Division | PASCHIM BHAGABANPUR Piped Water Supply Scheme , SM/12188 | New | Additional Laying Distribution of UPVC pipe line of PASCHIM BHAGABANPUR Piped Water Supply Scheme at Chanchal-I Dev. Block under Malda Division, P.H.E Dte. | 711/MD | 09/02/2024 | 45 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 2.15 | 0 | 0 | 90
2634 | MALDAH | Malda Division | PASCHIM BHAGABANPUR Piped Water Supply Scheme , SM/12188 | New | Design, Supplying, Fabrication, Erection & Commissioning including 3 (three) months Trial Run of 70m³/hr. capacity Pressure type IRON ELIMINATION Plant with Construction of Blower room & backwash water disposal at head work site of Paschim Bhagabanpur Water Supply Scheme of Chanchal-I Block under Malda Division P.H.E Dte in the District of Malda. | 3966/MD | 07/08/2024 | 180 | SHREE BISHNU CONSTRUCTION | 30.26 | 0 | 0 | 0
2635 | MALDAH | Malda Division | PASCHIM BHAGABANPUR Piped Water Supply Scheme , SM/12188 | New | Material Requisition To Resource Division | 87/MD | 05/01/2024 | 0 | Resource Division | 11.09 | 0 | 0 | 0
2636 | MALDAH | Malda Mechanical | PASCHIM BHAGABANPUR Piped Water Supply Scheme , SM/12188 | New | Additional quotation for paschim Bhagabanpur ph I DIST- MALDA .(kushida c c c) | BP-2024-25-204 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 0.1 | 0 | 0 | 0
2637 | MALDAH | Malda Mechanical | PASCHIM BHAGABANPUR Piped Water Supply Scheme , SM/12188 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. I of PASCHIM BHAGABANPUR PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-442 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 6.34 | 0 | 0 | 0
2638 | MALDAH | Malda Mechanical | PASCHIM BHAGABANPUR Piped Water Supply Scheme , SM/12188 | New | W.B.S.E.D.C.LTD Quotation charge at P/H No. II of PASCHIM BHAGABANPUR PWSS, Kushida C.C.C in the district of Malda Under Malda Mechanical Division PHE Dte. | BP-2023-24-441 | 10/01/2024 | 0 | W.B.S.E.D.C.LTD | 6.83 | 0 | 0 | 0
2639 | MALDAH | Malda Division | PASCHIM BHAGABANPUR Piped Water Supply Scheme , SM/12188 | New | Formal work order for the work of Implementation of PASCHIM BHAGABANPUR Water Supply Scheme at Chanchal-I Block of Malda district under Malda Division, PHE Dte., Govt. of West Bengal. | 1995/MD | 17/05/2023 | 960 | M/S TECHNICO & CO | 568.26 | 0 | 0 | 90
2640 | MALDAH | Malda Mechanical | PASCHIM BHAGABANPUR Piped Water Supply Scheme , SM/12188 | New | Supply, installation, commissioning and trial operation of electro-mechanical components at T/W no. I & II and making compound lighting arrangement at T/W no. I of Pascham Bhagabanpur Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. (TSM/013216) | 2328/MLMD | 26/07/2023 | 946 | GHOSH BROTHERS... | 28.17 | 0 | 0 | 86
2641 | MALDAH | Malda Division | PASCHIM BHAGABANPUR Piped Water Supply Scheme , SM/12188 | New | Construction of Boundary Wall at 2nd Tube Well site of Paschim Bhagabanpur Water Supply Scheme under Chanchal-I Block under Malda Division, PHE Dte. in the district of Malda. | 4735/MD | 11/09/2024 | 30 | M/S MADHU CONSTRUCTION | 10.76 | 0 | 0 | 15
2642 | MALDAH | Malda Division | PASCHIM BHAGABANPUR Piped Water Supply Scheme , SM/12188 | New | Sinking of Tubewell, Laying of Distribution Line, Providing FHTC, Construction of Pump House at Paschim Bhagabanpur Piped Water Supply Scheme at Chanchal-I Block of Malda District under Malda Division, PHE Dte, Govt. of West Bengal. | 5084/MD | 27/09/2024 | 60 | M/S TEWARI CONSTRUCTION | 92.44 | 0 | 0 | 20
2643 | MALDAH | Malda Division | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block , SM/18685 | New | Material Requisition To Resource Division | 834/MD | 21/02/2024 | 0 | Resource Division | 3626.73 | 0 | 0 | 0
2644 | MALDAH | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block , SM/18685 | New | Quotation Payment For Bamongola Zone-I, T/W-1 Under Bamongola CCC Under the district of Malda. | BP-2024-25-178 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 7 | 0 | 0 | 0
2645 | MALDAH | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block , SM/18685 | New | Quoation Payment For Bamongola Zone-V, T/W-I Under Bamongola CCC Under the district of Malda. | BP-2024-25-174 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 6.26 | 0 | 0 | 0
2646 | MALDAH | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block , SM/18685 | New | Quotation Payment For Bamongola Zone-II, T/W-1 Under Bamongola CCC Under the district of Malda. | BP-2024-25-175 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.94 | 0 | 0 | 0
2647 | MALDAH | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block , SM/18685 | New | Quoation Payment For Bamongola Zone-III, T/W-I Under Bamongola CCC Under the district of Malda. | BP-2024-25-176 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 3.8 | 0 | 0 | 0
2648 | MALDAH | Malda Division | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block , SM/18685 | New | Quotation for feasibility study report on possibility of setting up a 5.97-MLD capacity, radial collector well on Sub Surface Water based Piped Water Supply Scheme from Tangon River for Fluoride affected areas of Bamangola Block (Mouza- Berul, Jl-63, Near Bamongola Kathuadanga Primary School) towards implementation of water supply project based on Sub surface water of River Tangon. | BP-2024-25-284 | 23/09/2024 | 0 | INDUSTRY INSTITUTE PARTNERSHIP CELL JADAVPUR UNIVERSITY | 30.95 | 0 | 0 | 0
2649 | MALDAH | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block , SM/18685 | New | Quoation Payment For Bamongola Zone-IV, T/W-I Under Bamongola CCC Under the district of Malda. | BP-2024-25-177 | 22/05/2024 | 0 | W.B.S.E.D.C.LTD | 6.78 | 0 | 0 | 0
2650 | MALDAH | Malda Mechanical | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block , SM/18685 | New | Providing Electro-Mechanical components and Making compound lighting arrangement at Ground water based Piped W/S Scheme for different Distribution Zone at Tangon River site (zone-I & II) and Punarbhaba river site (zone-III,IV & V) under Bamongola Sub Surface Water Based Piped Water Supply Scheme in the District of Malda under Malda Mechanical Division, PHE Dte. | 2694/MLMD | 11/08/2023 | 869 | DEY ENTERPRISE.. | 80.84 | 0 | 0 | 30
2651 | MALDAH | Malda Division | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block , SM/18685 | New | Formal work order for the work of Surveying, Planning, Designing, Delivery, Erection, Construction, Commissioning and Completion of all civil, electrical and mechanical works including all allied and related works of Sub- Surface Water Based Piped Water Supply Scheme in Bamangola block of Malda district followed by three (3) months trial run and five (05) year operation and maintenance. | 3993/MD | 06/10/2023 | 908 | ENGINEERING PROJECTS (INDIA) LIMITED (A GOVERNMENT OF INDIA ENTERPRISE) | 12347.61 | 0 | 0 | 7
2652 | MALDAH | Malda Division | Sub Surface Water based Piped Water Supply Scheme from Tangon & Punarbhaba River for Fluoride affected areas of Bamangola Block , SM/18685 | New | Sinking of 200mm (all through) Big dia. Tube Well of 30.0 m Deep and RCC Structure for hoisting of MS Pipe for Tube well and Platform at Tangon river bed of bamongola Sub Surface Water based PWSS for Fluride affected areas of Bamongola Block under Malda Division, P.H.E Dte in the district of Malda. (10 Nos Tube Well & 20 Nos RCC Structure) | 5922/MD | 26/11/2025 | 120 | ASHIS CONSTRUCTION | 68.99 | 0 | 0 | 0
2653 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Acceptance cum formal work order for Engagement of Chemist/Bacteriologist and Laboratory Assistant for testing, entry and collection, of New Water Testing Laboratory of BULBULCHANDI Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2021 to 30/09/2022). | 2563/MD | 31/08/2021 | 365 | S. N. CONSTRUCTION | 3.7 | 0 | 0 | 0
2654 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Acceptance cum formal work order for Engagement of personnel for testing, entry and collection of Water Testing Laboratory of BALUPUR Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. (Period from 01/11/2021 to 31/07/2022) | 3035/MD | 26/10/2021 | 273 | HANNAN BUILDERS PVT. LTD. | 4.46 | 0 | 0 | 0
2655 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Acceptance cum formal work order for Engagement of personnel for testing, entry and collection of water for Malda District water Testing Laboratory under Malda Division, PHE Dte. in the district of Malda. (Period From 01/08/2021 to 31/02/2022). | 2257/MD | 30/07/2021 | 180 | SUDEB KARMAKAR | 3.54 | 0 | 0 | 0
2656 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Acceptance cum formal work order for Engagement of Chemist/Bacteriologist and Laboratory Assistant for testing, entry and collection, of New Water Testing Laboratory of GAZOLE Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2021 to 30/09/2022). | 2562/MD | 31/08/2021 | 365 | M/S MAHABIR ENTERPRISE | 3.7 | 0 | 0 | 0
2657 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Acceptance cum formal work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Sahapur Sub-District Laboratory (erstwhile PBVM) under Malda Division, PHE Dte. in the district of Malda. (Period from 01/06/2022 to 31/03/2023). | 1277/MD | 31/05/2022 | 304 | M/S MAA TARA ENTERPRISE | 4.66 | 0 | 0 | 0
2658 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Acceptance cum Formal Work Order of Supply, Delivery, Fitting and Fixing of Vinyl Glow Sign Boards for 8(eight) no. of Laboratories under Malda Division, PHE Dte. | 133/RWS | 31/05/2023 | 30 | M/S PARIMAL DAS | 0.81 | 0 | 0 | 100
2659 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Manikchak Sub-District Laboratory (erstwhile CDTP) under Malda Division, PHE Dte. in the district of Malda. (Period from 01/04/2023 to 30/06/2023). | 1465/MD | 29/03/2023 | 92 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 1.42 | 0 | 0 | 100
2660 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual maintenance of Chanchal Sub-District Laboratory under Malda Division, PHE Dte. (Period from 06/01/2023 to 05/01/2024) | 195/RWS | 05/01/2023 | 365 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 100
2661 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual maintenance of Manikchak Sub-District Laboratory under Malda Division, PHE Dte. (Period from 06/01/2023 to 05/01/2024) | 196/RWS | 05/01/2023 | 365 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 100
2662 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual maintenance of Gazole Sub-District Laboratory under Malda Division, PHE Dte. (Period from 06/01/2023 to 05/01/2024) | 197/RWS | 05/01/2023 | 365 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 100
2663 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual maintenance of Sahapur Sub-District Laboratory under Malda Division, PHE Dte. (Period from 06/01/2023 to 05/01/2024) | 198/RWS | 05/01/2023 | 365 | M/S MAA TARA ENTERPRISE | 0.75 | 0 | 0 | 100
2664 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual maintenance of Balupur WTP Sub-District Laboratory under Malda Division, PHE Dte. (Period from 06/01/2023 to 05/01/2024) | 199/RWS | 05/01/2023 | 365 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 100
2665 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual maintenance of Sanskrity-O-Samaj Unnayan Parishad Sub-District Laboratory. (Period from 06/01/2023 to 05/01/2024) | 200/RWS | 05/01/2023 | 365 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 100
2666 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual maintenance of Bulbulchandi Sub-District Laboratory under Malda Division, PHE Dte. (Period from 06/01/2023 to 05/01/2024) | 201/RWS | 05/01/2023 | 365 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 100
2667 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Manikchak Sub-District Laboratory (erstwhile CDTP) under Malda Division, PHE Dte. In the district of Malda. (Period from 01/10/2023 to 31/03/2024). | 3722/MD | 26/09/2023 | 183 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 2.84 | 0 | 0 | 100
2668 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Engagement of Chemist, Bacteriologist, Laboratory Assistant and Sampling Assistant for testing, entry and collection of Chanchal Sub-District Laboratory under Malda Division, PHE Dte. in the district of Malda (Period from 01/10/2023 to 31/03/2024). | 3723/MD | 26/09/2023 | 183 | GOBINDA ENTERPRISE | 3.81 | 0 | 0 | 100
2669 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Engagement of personnel for testing, entry, collection of water and Double Beam Atomic Absorption Spectrophotometer (AAS) for Malda District water Testing Laboratory under Malda Division, PHE Dte. in the district of Malda (Period from 01/10/2023 to 31/03/2024). | 3727/MD | 26/09/2023 | 183 | SUDEB KARMAKAR | 5.18 | 0 | 0 | 100
2670 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Continuation work order for maintenance of Chanchal Sub-District Laboratory under Malda Division, PHE Dte. for 6(Six) months.(Period from 06/01/2024 to 30/06/2024) | 432/RWS | 29/12/2023 | 183 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.37 | 0 | 0 | 100
2671 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Continuation work order for Maintenance of Manikchak Sub-District Laboratory under Malda Division, PHE Dte. for 6(Six) months(Period from 06/01/2024 to 30/06/2024) | 433/RWS | 29/12/2023 | 183 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.37 | 0 | 0 | 100
2672 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Continuation work order for maintenance of Gazole sub-District Laboratory under Malda Division,PHE Dte. for 6(Six) months (Period from 06/01/2024 to 30/06/20204) | 434/RWS | 29/12/2023 | 183 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.37 | 0 | 0 | 100
2673 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Continuation work order for maintenance of Balupur WTP Sub-District Laboratory under Malda Division, PHE Dte. for 06(Six) months( period from 06/01/2024 to 30/06/2024) | 435/RWS | 29/12/2023 | 183 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.37 | 0 | 0 | 100
2674 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Continuation of work order for maintenance of Sanskrity-O-Samaj Unnayan Parishad Sub-District Laboratory under Malda Division, PHE Dte. for 6(Six) months.(Period from 06/01/2024 to 30/06/2024). | 436/RWS | 29/12/2023 | 183 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.37 | 0 | 0 | 100
2675 | MALDAH | Malda Division | Operational Charges of PHED & NGO Managed Laboratories Related to water quality monitoring & surveillance under Jal Jeevan Mission. , SM/12272 | Support-WQMSP | Acceptance cum formal work order for Annual Maintenance Contract (AMC) for software upgradation, other software related issues in existing computers, refilling of cartridge of the printers, replacement of battery of UPS and other related peripherals in 8 nos. i.e. District, Sub-District & NGO Laboratories under Malda Division, PHE Dte. in the district of Malda. (Period from 01/04/2023 to 31/03/2024). | 1481/MD | 30/03/2023 | 365 | DIGITAL CONSULTANTS | 1.19 | 0 | 0 | 100
2676 | MALDAH | Malda Ars Area W/S Division | Supply, Delivery and Installation of Computer & peripherals through GEMS for official use under office of the Executive Engineer, Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11869 | Support-MIS | Supply, Delivery and Installation of Computer & peripherals through GEMS for official use under office of the Executive Engineer, Malda Arsenic Area Water Supply Division, PHE Dte. | GEMC-511687716441080 | 20/11/2022 | 25 | IONET | 6.93 | 0 | 0 | 0
2677 | MALDAH | Malda Ars Area W/S Division | Supply, Delivery and Installation of Computer & peripherals through GEMS for official use under office of the Executive Engineer, Malda Arsenic Area Water Supply Division, PHE Dte. , SM/11869 | Support-MIS | SUPPLY OF THE FOLLOWING COMPUTER ACCESSORIES WITH SERVICE CHARGE FOR USE IN THE OFFICE OF THE EXECUTIVE ENGINEER, MALDA ARSENIC AREA W/S DIVISION, P.H.E. DTE. | C082336230106 | 24/08/2023 | 0 | DIGITEK SOLUTIONS | 0.25 | 0 | 0 | 0
2678 | MALDAH | Malda Division | Supply, Delivery and Installation of Computer & Peripherals for official use at Sub- Divisions, Laboratories & at Division office under Malda Division, PHE Dte. , SM/10733 | Support-MIS | Canon IR 2625 with Duplex and DADF canon Multifunction Machines Mfm, On site OEM under Malda Division, PHE Dte. | GEM/2022/B/2239135 | 03/07/2022 | 1 | IONET | 1.68 | 0 | 0 | 0
2679 | MALDAH | Malda Division | Supply, Delivery and Installation of Computer & Peripherals for official use at Sub- Divisions, Laboratories & at Division office under Malda Division, PHE Dte. , SM/10733 | Support-MIS | Hp laser mono computer printers for A4 paper size under Malda Division, PHE Dte. | GEMC-511687781112500 | 05/06/2022 | 1 | IONET | 1 | 0 | 0 | 0
2680 | MALDAH | Malda Division | Supply, Delivery and Installation of Computer & Peripherals for official use at Sub- Divisions, Laboratories & at Division office under Malda Division, PHE Dte. , SM/10733 | Support-MIS | Bill for Printer supplied for GEM under Malda Division, PHE Dte. | GEMC-511687739405595 | 02/08/2022 | 1 | IONET | 3.73 | 0 | 0 | 0
2681 | MALDAH | Malda Division | Supply, Delivery and Installation of Computer & Peripherals for official use at Sub- Divisions, Laboratories & at Division office under Malda Division, PHE Dte. , SM/10733 | Support-MIS | Bill for Supply, Delivery and Installation of Computer & Peripherals for official use at Sub- Divisions, Laboratories & at Division office under Malda Division, PHE Dte. | BP-2022-23-120 | 13/12/2022 | 0 | IONET | 6.18 | 0 | 0 | 0
2682 | MALDAH | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19086 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Gazole Sub-District Laboratory under Malda Division, PHE Dte. In the district of Malda. (Period from 01/04/2024 to 30/09/2024). | 1371/MD | 15/03/2024 | 183 | M/S MAHABIR ENTERPRISE | 2.98 | 0 | 0 | 100
2683 | MALDAH | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19086 | Support-WQMSP | Continuation work order for Regular Upkeepment, upgradation of Mobile Laboratory Van complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents, accessories and safety gear for Water Quality Monitoring and Surveillance Program under Malda Division PHE Dte. (Period from 01/01/2025 to 31/01/2025). | 6626/MD | 31/12/2024 | 31 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 2.1 | 0 | 0 | 100
2684 | MALDAH | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19086 | Support-WQMSP | Continuation work order for Regular Upkeepment, upgradation of Mobile Laboratory Van complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents, accessories and safety gear for Water Quality Monitoring and Surveillance Program under Malda Division PHE Dte. (Period from 01/11/2024 to 31/12/2024). | 5549/MD | 29/10/2024 | 61 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 4.19 | 0 | 0 | 100
2685 | MALDAH | Malda Division | Operation & Maintenance of PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19086 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Sahapur Sub-District Laboratory (erstwhile PBVM) under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2024 to 30/09/2025). | 5186/MD | 30/09/2024 | 365 | M/S RAKHI ENTERPRISE | 5.47 | 0 | 0 | 100
2686 | MALDAH | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Malda District. , SM/09645 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Malda District. | 4723/RS | 18/08/2022 | 365 | CHAKVIGU VIDYASAGAR SOCIAL WELFARE SOCIETY | 315.03 | 0 | 0 | 75
2687 | MALDAH | Malda Division | Drinking water samples collection & testing through Field Test Kit (FTKs) & uploading charges related to Water Quality Monitoring & Surveillance programme under JJM in the district of Malda under Malda Division. , SM/08972 | Support-WQMSP | Bill for Resuming training and initiating onsite water quality testing of drinking water sources through Field Test Kits (FTKs) and awareness generation by ASHAs_reg. | BP-2021-22-157 | 30/03/2022 | 0 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 12.23 | 0 | 0 | 0
2688 | MALDAH | Malda Division | Drinking water samples collection & testing through Field Test Kit (FTKs) & uploading charges related to Water Quality Monitoring & Surveillance programme under JJM in the district of Malda under Malda Division. , SM/08972 | Support-WQMSP | Acceptance cum formal work order for Payment for Collection of drinking water sample from sources of 26 nos arsenic affected Gram Panchayet for retesting purpose under Malda Division, PHE Dte. in the district of Malda. | 3688/MD | 03/01/2022 | 15 | S. R. CONSTRUCTION | 7.05 | 0 | 0 | 99
2689 | MALDAH | Malda Mechanical | Procurement of Computer and peripherals for office use in Office of the Executive Engineer, Malda Mechanical Division, PHE Dte. , SM/10479 | Support-MIS | Procurement of Computer and peripherals for office use in the Office of the Executive Engineer, Malda Mechanical Division, PHE Dte. | GEMC-511687740117203 | 22/06/2022 | 15 | IONET | 5.24 | 0 | 0 | 0
2690 | MALDAH | Malda Mechanical | Procurement of Computer and peripherals for office use in Office of the Executive Engineer, Malda Mechanical Division, PHE Dte. , SM/10479 | Support-MIS | Procurement of Computer and peripherals for office use in the Office of the Executive Engineer, Malda Mechanical Division, PHE Dte. | GEMC-511687714988066 | 16/06/2022 | 15 | IONET | 1.31 | 0 | 0 | 0
2691 | MALDAH | Malda Mechanical | Procurement of Computer and peripherals for office use in Office of the Executive Engineer, Malda Mechanical Division, PHE Dte. , SM/10479 | Support-MIS | Procurement of Computer and peripherals for HP smart tank 530 printer, formujet 88A Tonner cartridge CC388A for HP, Dell 19 monitor D1918H, UPS legend 650 VA & Others office use in the Office of the Executive Engineer, Malda Mechanical Division, PHE Dte. | GEMC-511687799467143 | 11/10/2022 | 30 | IONET | 1.02 | 0 | 0 | 0
2692 | MALDAH | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit , SM/07971 | Support-WQMSP | Acceptance cum formal work order for Engagement of Resource person to implement water testing laboratory quality management system as per ISO/IEC: 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instruments & calibration of measuring instruments as per ISO 17025: 2017 protocol for Malda District Water Testing Laboratory under the Executive Engineer, Malda Division, PHE Dte, Government of West Bengal. | 1610/MD | 19/05/2021 | 15 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 16.04 | 9.59 | 80.26 | 100
2693 | MALDAH | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit , SM/07971 | Support-WQMSP | Supply of additionally required chemicals for Gazole Sub- District Laboratory |  | 16/03/2023 | 0 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.09 | 0 | 0 | 0
2694 | MALDAH | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit , SM/07971 | Support-WQMSP | Supply of additionally required chemicals for Gazole Sub- District Laboratory |  | 16/03/2023 | 0 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.09 | 0 | 0 | 0
2695 | MALDAH | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit , SM/07971 | Support-WQMSP | Supply of additionally required chemicals for Gazole Sub- District Laboratory |  | 16/03/2023 | 0 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.09 | 0 | 0 | 0
2696 | MALDAH | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit , SM/07971 | Support-WQMSP | Supply of additionally required chemicals for Gazole Sub- District Laboratory |  | 16/03/2023 | 0 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.1 | 0 | 0 | 0
2697 | MALDAH | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit , SM/07971 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Sahapur Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | 4229/MD | 28/08/2025 | 30 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
2698 | MALDAH | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit , SM/07971 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement forSamsi Sub-District Laboratory (erstwhile SANSKRITY -O- SAMAJ UNNAYAN PARISAD SUB-DISTRICT LABORATORY) under Malda Division, Public Health Engineering Directorate, Government of West Bengal | 4228/MD | 28/08/2025 | 30 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
2699 | MALDAH | Malda Division | Supply, installation & delivery of water quality testing equipment, chemicals, consumables & glassware etc. for continuing NABL accreditation (Chemical Testing of potable water) including routine water testing of 8 nos Water Testing Laboratories along wit , SM/07971 | Support-WQMSP | Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratories by assigning term of competent resource personnel who will be engaged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation, Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement for Manikchak Sub District Laboratory under Malda Division, Public Health Engineering Directorate, Government of West Bengal. | 4227/MD | 28/08/2025 | 30 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.9 | 0 | 0 | 0
2700 | MALDAH | Malda Division | Procurement of chemicals, consumables & glassware etc. for smooth running of water testing of 8 (eight) no. of laboratories under EE, Malda Division, PHE Dte. , SM/06637 | Support-WQMSP | Acceptance cum formal work order for Supply & Delivery of Chemicals, Reagents and Consumables for 8(eight) nos Laboratories under Malda Division, PHE Dte. (Period 6 (Six) months) | 872/MD | 22/02/2023 | 180 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 28.01 | 0 | 0 | 0
2701 | MALDAH | Malda Division | Procurement of chemicals, consumables & glassware etc. for smooth running of water testing of 8 (eight) no. of laboratories under EE, Malda Division, PHE Dte. , SM/06637 | Support-WQMSP | Acceptance cum formal work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Manikchak Sub-District Laboratory (erstwhile CDTP) under Malda Division, PHE Dte. in the district of Malda. (Period from 01/06/2022 to 31/03/2023). | 1278/MD | 31/05/2022 | 304 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 4.67 | 0 | 0 | 0
2702 | MALDAH | Malda Division | Procurement of chemicals, consumables & glassware etc. for smooth running of water testing of 8 (eight) no. of laboratories under EE, Malda Division, PHE Dte. , SM/06637 | Support-WQMSP | Acceptance cum formal work order for Engagement of Chemist/Bacteriologist, Laboratory Assistant and Sampling Assistant for testing, entry and collection, of New Water Testing Laboratory of CHANCHAL Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. (Period From 01/07/2022 to 30/06/2023). | 1563/MD | 30/06/2022 | 365 | GOBINDA ENTERPRISE | 4.8 | 0 | 0 | 100
2703 | MALDAH | Malda Division | Procurement of chemicals, consumables & glassware etc. for smooth running of water testing of 8 (eight) no. of laboratories under EE, Malda Division, PHE Dte. , SM/06637 | Support-WQMSP | Acceptance cum formal work order for Supply & Delivery of Chemicals, Reagents and Consumables for 8(eight) nos Laboratories under Malda Division, PHE Dte. (Period 6 (Six) months) | 874/MD | 22/02/2023 | 180 | M/S MANDAL SCIENTIFIC AND WATER ANALYSIS | 2.48 | 0 | 0 | 100
2704 | MALDAH | Malda Division | Procurement of chemicals, consumables & glassware etc. for smooth running of water testing of 8 (eight) no. of laboratories under EE, Malda Division, PHE Dte. , SM/06637 | Support-WQMSP | Supply of additionally required chemicals for Gazole Sub-District Laboratory. | BP-2023-24-17 | 02/05/2023 | 0 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.37 | 0 | 0 | 0
2705 | MALDAH | Malda Division | Survey & collection of data through Mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Malda District. , SM/08973 | Support-M&E | Acceptance cum formal work order for Payment for Survey & Collection of data through mobile APP regarding availability of drinking water, Sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers with in Malda district under Malda Division, PHE Dte. | 436/MD | 21/02/2022 | 15 | SOVON KUMAR DAS | 9.73 | 0 | 0 | 0
2706 | MALDAH | Malda Division | operational charges FTK testing by lab personnel & ASHA related to swachh jal se suraksha campaign under jal jeevan mission , SM/18275 | Support-WQMSP | Requisition of fund to the Executive Engineer, Malda Division P.H.E. dte for ASHA workers water testing payment using FTK. | BP-2023-24-177 | 24/08/2023 | 0 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 76.58 | 0 | 0 | 0
2707 | MALDAH | Malda Division | operational charges FTK testing by lab personnel & ASHA related to swachh jal se suraksha campaign under jal jeevan mission , SM/18275 | Support-WQMSP | Operational charges for FTK Testing by Lab Personnel & ASHA Related to Swachh Jal Se Suraksha Campaign under Jal Jeevan Mission at different AWCs and Schools under Malda Division, Public Health Engineering Directorate in the district of Malda. | 4785/MD | 06/12/2023 | 30 | M/S AMIT KUMAR GUPTA | 13.52 | 0 | 0 | 100
2708 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum formal work order for Annual Maintence Contract (AMC) for software upgradation, other software related issues in existing computers, refilling of cartridge of the printers, replacement of battery of UPS and other related peripherals in 8 nos. i.e. District, Sub-District & NGO Laboratories under Malda Division, PHE Dte. in the district of Malda, (Period from 01/09/2020 to 31/08/2021). | 1906/MD | 26/08/2020 | 365 | DIGITAL CONSULTANTS | 1.2 | 0 | 0 | 0
2709 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum formal work order for Engagement of resource person for operation of Double Beam Atomic Absorption Spectrophotometer (AAS) in the Malda district water testing laboratory situated in Malda district under Malda Division, PHE Dte. (Period from 01/07/2021 to 30/06/2022). | 1882/MD | 30/06/2021 | 365 | M/S JHA CONSTRUCTION | 2.55 | 0 | 0 | 0
2710 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum formal work order for Maintenance of Malda District Laboratory PHE Dte. under Malda Division PHE Dte. (Period From 01/09/2021 to 31/08/2022). | 2554/MD | 31/08/2021 | 365 | M/S AMIT KUMAR GUPTA | 0.99 | 0 | 0 | 0
2711 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum formal work order for Requirements of Chemicals, Reagents & glasswares for smooth running of Water Tesings for 1. Chanchal SD Laboratory 2. Balupur SD Laboratory 3. Sanskriti o samaj unnayan parishad SD Laboratory under Malda Division, PHE Dte. of Malda District. | 3092/MD | 29/10/2021 | 15 | LAXMI ENTERPRISE | 20.69 | 0 | 0 | 0
2712 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum formal work order for Supply of spares for AAS 3500 & for hydride generator of AAS of malda district laboratory under Malda Division, PHE Dte. | 2913/MD | 28/09/2021 | 10 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 2.87 | 0 | 0 | 0
2713 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum formal work order for Requirements of Chemicals, Reagents & glasswares for smooth running of Water Tesings for 1. Malda District Laboratory 2. Paschim Banga Vigyan Mancha SD Laboratory 3. Community polytechnic cell SD Laboratory 4. Gazole SD Laboratory 5. Bulbulchandi SD Laboratory under Malda Division, PHE Dte. of Malda District. | 2912/MD | 28/09/2021 | 15 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 33.9 | 0 | 0 | 0
2714 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum formal work order for Supply, installation, demonstration, training of all laboratory requirement including assigning resource person for guidance to prepare required documents, records & performing internal calibration, clearing non-compliances related to NABL recognition as a composite work in connection for NABL Accreditation of Chanchal Sub-District Laboratories under Malda Division, PHE Dte., Malda. | 2682/MD | 08/09/2021 | 60 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 4.88 | 0 | 0 | 0
2715 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum formal work order for Procurement of consumables for On-site Mobile Analysis System (OMAS) at 1) Malda District Laboratory, 2) Gazole Sub-District Laboratory, 3) Chanchal Sub-District Laboratory, 4) Community Polytechnic Cell Sub-District Laboratory & 5) Sanskrity - O - Samaj Unnayan Parishad Sub-District Laboratory for water quality testing under Malda Division, PHE Dte. | 625/MD | 15/03/2022 | 21 | SAKTI ENTERPRISE | 12.9 | 0 | 0 | 0
2716 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Supply of 13 Nos. Chemicals, Glassware and Installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of Mobile Laboratory Van stationed in Maldah District under PHE Department, Govt. of West Bengal. | 3247/MD | 22/08/2023 | 15 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 0.63 | 0 | 0 | 0
2717 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Supply & Delivery of Spare for AAS, consumables for AAS, chemicals and allied work required for maintaining NABL for Malda District water testing Laboratory under The Executive Engineer, Malda Division, PHE Dte. | 3248/MD | 22/08/2023 | 7 | LAXMI ENTERPRISE | 2.28 | 0 | 0 | 0
2718 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Supply of 52 Nos. Chemicals, Glassware and Installation of the pre-requisites needed for successful application & recognition from NABL for 11 mandatory water quality parameters of Mobile Laboratory Van stationed in Maldah District under PHE Department, Govt. of West Bengal. | 3246/MD | 22/08/2023 | 15 | LAXMI ENTERPRISE | 1.21 | 0 | 0 | 0
2719 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Sanskrity-O-Samaj Unnayan Parishad Sub-District Laboratory under Malda Division, PHE Dte. In the district of Malda. (Period from 01/10/2023 to 31/03/2024). | 3806/MD | 29/09/2023 | 183 | GOBINDA ENTERPRISE | 2.84 | 0 | 0 | 0
2720 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Sahapur Sub-District Laboratory (erstwhile PBVM) under Malda Division, PHE Dte. in the district of Malda. (Period from 01/07/2023 to 30/09/2023). | 2315/MD | 08/06/2023 | 92 | M/S MAA TARA ENTERPRISE | 1.42 | 0 | 0 | 100
2721 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Engagement and providing arrear of Bacteriologist at Chanchal Sub-District Laboratory, Gazol Sub-District Laboratory and Bulbulchandi Sub-District Laboratory under Malda Division, PHE Dte. in the district of Malda. (Period from 01/06/2023 to 30/09/2023). | 3022/MD | 08/08/2023 | 122 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 2.6 | 0 | 0 | 100
2722 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum formal work order for Engagement of personnel for testing, entry and collection of water for Malda District water Testing Laboratory under Malda Division, PHE Dte. in the district of Malda. (Period From 01/03/2022 to 31/08/2022). | 495/MD | 28/02/2022 | 6 | SUDEB KARMAKAR | 3.55 | 0 | 0 | 100
2723 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum formal work order for Payment of Enhanced Rate for Lab Personnel in Gazole and Manikchak Sub-District Laboratories under Malda Division, PHE Dte. | 121/RWS | 22/05/2023 | 458 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 3.83 | 0 | 0 | 60
2724 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum Formal Work Order for Payment of Enhanced Rate for Lab Personnel in Malda District Laboratory under Malda Division, PHE Dte. | 124/RWS | 22/05/2023 | 458 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 4.33 | 0 | 0 | 60
2725 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum work order for Payment of Enhanced Rate for Lab Personnel in Bulbulchandi and Chanchal Sub-District Laboratories under Malda Division, PHE Dte. | 122/RWS | 22/05/2023 | 458 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 3.44 | 0 | 0 | 60
2726 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum Formal Work Order for Payment of Enhanced Rate for Lab Personnel in Sahapur and Balupur Sub-District Laboratories under Malda Division, PHE Dte | 125/RWS | 22/05/2023 | 458 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 4.72 | 0 | 0 | 60
2727 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum work order for Payment of Enhanced Rate for Lab Personnel in Sanskrity-O-Samaj Unnayan Parishad Sub-District Laboratory under Malda Division, PHE Dte. | 123/RWS | 22/05/2023 | 458 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 2.36 | 0 | 0 | 65
2728 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Manikchak Sub-District Laboratory (erstwhile CDTP) under Malda Division, PHE Dte. in the district of Malda. (Period from 01/07/2023 to 30/09/2023). | 2316/MD | 08/06/2023 | 92 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 1.42 | 0 | 0 | 100
2729 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Sahapur Sub-District Laboratory (erstwhile PBVM) under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2023 to 31/03/2024). | 3721/MD | 26/09/2023 | 183 | M/S RAKHI ENTERPRISE | 2.84 | 0 | 0 | 100
2730 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Balupur WTP Sub-District Laboratory under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2023 to 31/03/2024). | 3724/MD | 26/09/2023 | 183 | M/S RAKHI ENTERPRISE | 2.84 | 0 | 0 | 100
2731 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Bulbulchandi Sub-District Laboratory under Malda Division, PHE Dte. In the district of Malda. (Period from 01/10/2023 to 31/03/2024). | 3726/MD | 26/09/2023 | 183 | S. N. CONSTRUCTION | 3.19 | 0 | 0 | 100
2732 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum formal work order for Engagement of resource person for supervising the protocol / standard operating procedures/ technical documentation of laboratory water testing activities as per ISO/IEC 17025:2017 including performing statutory internal audit, refresher training course and any other required laboratory management process and allied works to comply NABL accreditation system of Malda District Laboratory under Malda Division, PHE Dte. for a period of 06 (six) months. | 873/MD | 22/02/2023 | 180 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 5.5 | 0 | 0 | 100
2733 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Repairing of Samsi Sub-District Laboratory under Malda Division, PHE Dte, Govt. of West Bengal. | 658/MD | 08/02/2024 | 45 | M/S FOUR STAR CONSTRUCTION | 3.68 | 0 | 0 | 100
2734 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Continuation work order for maintenance of Bulbulchandi Sub-District Laboratory under Malda Division, PHE Dte.for 06(Six) months.(Period from 06/01/2024 to 30/06/2024) | 437/RWS | 29/11/2023 | 182 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD. | 0.37 | 0 | 0 | 100
2735 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Bulbulchandi Sub-District Laboratory under Malda Division, PHE Dte. In the district of Malda. (Period from 01/04/2024 to 30/09/2024). | 1372/MD | 15/03/2024 | 183 | S. N. CONSTRUCTION | 2.98 | 0 | 0 | 100
2736 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Continuation work order for Engagement of Chemist, Bacteriologist and Laboratory Assistant including related upkeeping works for Manikchak Sub-District Laboratory (erstwhile CDTP) under Malda Division, PHE Dte. In the district of Malda. (Period from 01/04/2024 to 30/09/2024). | 1368/MD | 15/03/2024 | 183 | NABODAYA MULTIPURPOSE CO-OPERATIVE SOCIETY LTD | 2.63 | 0 | 0 | 100
2737 | MALDAH | Malda Division | Procurement of chemicals, Instruments and glassware including OMAS Consumables and Annual Computer Maintenance and peripherals of both PHED & NGO managed laboratories under Malda Division, PHE Dte. , SM/12741 | Support-WQMSP | Acceptance cum formal work order for Engagement of Chemist/Bacteriologist and Laboratory Assistant for testing, entry and collection, of New Water Testing Laboratory of GAZOLE Water Supply Scheme under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2022 to 30/09/2023). | 2361/MD | 29/09/2022 | 365 | M/S MAHABIR ENTERPRISE | 3.9 | 0 | 0 | 100
2738 | MALDAH | Malda Division | Regular Up-keepment & Up-gradation of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance programme related to Jal Jeevan Mission , SM/19339 | Support-WQMSP | Regular Upkeepment, upgradation of Mobile Laboratory Van complete with internal fabrication, refrigeration, exhaust system, air conditioning system, waste disposal system and fully equipped with instruments, devices, consumables, reagents, accessories and safety gear for Water Quality Monitoring and Surveillance Program under Malda Division PHE Dte. (Period 1 Year). | 313/MD | 30/01/2025 | 365 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT. LTD. | 27.09 | 0 | 0 | 45
2739 | MALDAH | Malda Division | Regular Up-keepment & Up-gradation of Mobile Laboratory Van (MLV) under Water Quality Monitoring & Surveillance programme related to Jal Jeevan Mission , SM/19339 | Support-WQMSP | Operation and Up Keepment of Automobile Van mounted Water Tanker for delivering of drinking water to &fro travelling to various water scarcity areas. under Malda Division, P.H.E. Dte. In the District of Malda, Govt. of West Bengal. (considering 210 days run/Years.) | 2681/MD | 04/06/2025 | 365 | M/S SABANA CONSTRUCTION | 2.02 | 0 | 0 | 0
2740 | MALDAH | Resource | On-site assessment with sample collection & testing of AIRPs & CWPPs installed in Maldah district including supply & delivery of 7956 consumables in compatible with Onsite Mobile Analysis System in addition to monitoring & processing data of AIRPs & CWPPs , SM/19284 | Support-WQMSP | Supply& delivery of consumables for testing Raw & Treated water of Arsenic & Iron Removal Plants (AIRPs) through On-site Mobile Analysis System (OMAS) as per direction of EIC under Public Health Engineering Department, Government of West Bengal | 67/RS | 09/01/2025 | 365 | SUNANDA ENVIROMENTAL INTERNATIONAL PRIVATE LIMITED | 25.56 | 0 | 0 | 94
2741 | MALDAH | Malda Ars Area W/S Division | Operational charges of PHED & NGO Managed Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission. , SM/12119 | Support-WQMSP | Routine/ Regular Chemical /Phjlysico-Chemical/ Bacteriological Testing of Water Quality Parameters in Laboratory at Dariapur , P.S. Baishnabnagar under Malda Arsenic Area W/S Division, PHED. [Period from 01.02.2022 to 31.12.2022= for 11 month] | 76/MAAD | 21/01/2022 | 334 | MILLENNIUM ENTERPRISE | 4.66 | 0 | 0 | 0
2742 | MALDAH | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19321 | Support-WQMSP | Supply & Delivery of Chemicals,reagent for determining Chlorine demand at Sub-District Laboratories under Malda Division, Public Health Engineering Directorate, Govertment of West Bengal. | 2967/MD | 19/06/2025 | 7 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.18 | 0 | 0 | 0
2743 | MALDAH | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19321 | Support-WQMSP | Engagement of Chemist, Bacteriologist, AAS Operator, Laboratory Assistant and Sampling Assistant for testing, entry and collection and annual maintenance of MALDA DISTRICT LABORATORY under Malda Division, PHE Dte. in the district of Malda. (Period from 01/10/2025 to 30/09/2026). | 5065/MD | 22/09/2025 | 365 | SUDEB KARMAKAR | 16.9 | 0 | 0 | 0
2744 | MALDAH | Malda Division | Operation & Maintenance including procurement of Chemical & Glassware for PHED Managed Laboratories under Malda Division for Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19321 | Support-WQMSP | Requirements of Chemicals, Reagents & glasswares for smooth running of Water Tesings at all laboratories of Malda District under Malda Division, PHE Dte, Government of West Bengal in the district of Malda. | 5800/MD | 22/11/2024 | 15 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 57.9 | 0 | 0 | 100
Total | [9 empty] | 965671.5 | 1671.36 | 0.17