## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) , SM/07910 | Retrofitting | Work of Laying of U.P.V.C. Pipe line at Sikdarpur Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. | 387 /JSD | 31/12/2021 | 30 | DEBOJYOTI CONSTRUCTION | 4.63 | 4.63 | 100 | 1
2 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) , SM/07910 | Retrofitting | CONTINUATION ORDER OF CAR HIRING OF AE-LSD 261/LSD DATE- 04/03/2021 | 359-MSD/22-23 | 19/10/2022 | 0 | ARINDAM MAJUMDAR | 0.61 | 0 | 0 | 0
3 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) , SM/07910 | Retrofitting | HIRING OF CAR FOR SE-MC | 358-MSD/22-23 | 19/10/2022 | 0 | HASNA BEWA | 0.6 | 0 | 0 | 0
4 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) , SM/07910 | Retrofitting | Continuation work order for Hiring of 1 no of Car for official use of the eAE LSD PHE DTE. Work Order No 261 / LSD DATE 04.03.2021 | 202-MSD/2022-23 | 07/07/2022 | 0 | ARINDAM MAJUMDAR | 1.08 | 0 | 0 | 0
5 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) , SM/07910 | Retrofitting | Work order for Hiring of 1 no of Car for official use of the AE JSD PHE DTE. Work Order No 302 / JSD. DATE 25.11.2021 | 205-MSD/2022-23 | 08/07/2022 | 0 | MANUAR HOSSAIN | 1.19 | 0 | 0 | 0
6 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) , SM/07910 | Retrofitting | Work order for Hiring of 1 no of Car for official use of the AE ISD PHE DTE. Work Order No 473 / ISD. DATE 03.09.2021 | 206-MSD/22-23 | 12/07/2022 | 0 | M/S SAJAHAN CHOWDHURY | 0.78 | 0 | 0 | 0
7 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) , SM/07910 | Retrofitting | work order for Hiring of 1 no of Car for official use of the SE MC PHE DTE. Work Order No 10 / MC. DATE 05.01.2022 | 203-MSD/2022-23 | 07/07/2022 | 0 | HASNA BEWA | 0.62 | 0 | 0 | 0
8 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) , SM/07910 | Retrofitting | Material Requisition To Resource Division | 540/3/MURD | 25/02/2022 | 0 | Resource Division | 2.7 | 0 | 0 | 0
9 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) , SM/07910 | Retrofitting | Rail Bhoomi Crossing Seva (IR-RBCS) Eastern Railway Howrah Division DEMAND NOTE Application ID: ER-HWH-2024-WL-64 | 545-MSD/2024-25 | 28/10/2024 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 0.11 | 0 | 0 | 0
10 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sikdarpur ( 313858 ) of Sikdarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) , SM/07910 | Retrofitting | Providing Functional Household Tap Connections (FHTC) 492 nos in connection with Jal Swapna (Jal Jeevan Mission ) of Mouza Sikdarpur ( Village Code -313858) under Sikdarpur & adjoining mouzas Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. | 1115/MURD | 29/04/2022 | 30 | N. H. ENTERPRISE (PROP. NAJMUL HOQUE) | 26.22 | 10.34 | 39.42 | 0
11 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mamudpur (314685) & Gobindapur (314687) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( , SM/07918 | Retrofitting | Construction of P.C.C approach road at Head work site of Juginda Zone-I Water Supply Scheme under Domkal Block within Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. | 477/ISD | 03/09/2021 | 30 | M/S SAJAHAN CHOWDHURY | 1.62 | 1.62 | 100 | 1
12 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mamudpur (314685) & Gobindapur (314687) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( , SM/07918 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Mamudpur ( Village Code -314685) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344) | 2438/MURD | 12/08/2021 | 60 | JOY BISHNU ENGINEERING CO. | 28.13 | 21.24 | 75.52 | 0
13 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mamudpur (314685) & Gobindapur (314687) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( , SM/07918 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Gobindapur (Village Code -314687) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344) | 1615/MURD | 28/06/2021 | 60 | BISWAS CONSTRUCTION | 27.63 | 48.73 | 200 | 0
14 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahammadpur ( 315549 ) of Mahammadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District ( PART-I ) , SM/07922 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MAHAMMADPUR (Village Code 315549) under MAHAMMADPUR Ground Water Based Water Supply Scheme for arsenic affected areas of BERHAMPORE Block in the District of Murshidabad. Tender no - 04 of 20-21 by SE MC | 384-MSD/21-22 | 19/03/2022 | 0 | HARAPRASAD DAS | 16.56 | 0 | 0 | 0
15 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahammadpur ( 315549 ) of Mahammadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District ( PART-I ) , SM/07922 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mahammadpur (Village code 315549) under Mahammadpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Nowda Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723172 in the District of Murshidabad. | 1652/MURD | 29/06/2021 | 180 | HARAPRASAD DAS | 75.04 | 115.84 | 154.36 | 100
16 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahammadpur ( 315549 ) of Mahammadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District ( PART-I ) , SM/07922 | Retrofitting | Material Requisition To Resource Division | 539/9/MURD | 25/02/2022 | 0 | Resource Division | 2.54 | 0 | 0 | 0
17 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahammadpur ( 315549 ) of Mahammadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District ( PART-I ) , SM/07922 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) of 462 left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahammadpur (Village code 315549) under Mahammadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 802/MURD | 24/03/2022 | 30 | M/S. UNIQUE BUILDERS | 29.37 | 35.83 | 100 | 1
18 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rampara Faridpur Village (Code-315664) Under Command Area Of Rampara Faridpur Ground Water Supply Scheme (Part-B) , SM/07693 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rampara Foridpur (Village code 315664) under Rampara Foridpur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | 184/BD-I | 04/02/2021 | 30 | DOBAY CONSTRUCTION | 98.77 | 70.91 | 71.79 | 1
19 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rampara Faridpur Village (Code-315664) Under Command Area Of Rampara Faridpur Ground Water Supply Scheme (Part-B) , SM/07693 | Retrofitting | Additional Laying works at village Rampara Foridpur (Village code-315664) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Rampara Foridpur Ground water based Water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | 2310/BD-I | 29/12/2021 | 45 | BENOY DOBEY | 15.18 | 0 | 0 | 0
20 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Gaukhana ground water supply scheme , SM/06982 | Retrofitting | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramna Bagsarai and Others under Gaukhana Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | 277/BD-I | 15/02/2021 | 10 | S.ENTERPRISE | 2.73 | 0 | 0 | 0
21 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Gaukhana ground water supply scheme , SM/06982 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramna Bagsarai (Village code 314160) under Gaukhana Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 960/BD-I | 17/12/2020 | 60 | S.ENTERPRISE | 8.24 | 0 | 0 | 0
22 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Gaukhana ground water supply scheme , SM/06982 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Deoan Sarai (Village code 314161) under Gaukhana Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 961/BD-I | 17/12/2020 | 90 | SAMBHUNATH ROY | 30.8 | 30.75 | 99.84 | 1
23 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Gaukhana ground water supply scheme , SM/06982 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gaukhana (Village code 314162) under Gaukhana Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 972/BD-I | 17/12/2020 | 60 | N.H ENTERPRISE | 12.91 | 18.53 | 170.37 | 100
24 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Gaukhana ground water supply scheme , SM/06982 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Laskarpur (Village code 314167) under Gaukhana Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 973/BD-I | 17/12/2020 | 60 | SUSHANTA MANDAL | 11.01 | 10.4 | 100 | 1
25 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Gaukhana ground water supply scheme , SM/06982 | Retrofitting | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Goukhana and Others under Goukhana Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | 914/BD-I | 19/05/2021 | 7 | N.H ENTERPRISE | 3.62 | 6.32 | 200 | 0
26 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08111 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 24.86 | 1
27 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08111 | Retrofitting | Material Requisition To Resource Division | 62/BD-I | 27/01/2022 | 0 | Resource Division | 7.67 | 0 | 0 | 0
28 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08111 | Retrofitting | Material Requisition To Resource Division | 70/BD-I | 28/01/2022 | 0 | Resource Division | 2.48 | 0 | 0 | 0
29 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08111 | Retrofitting | Material Requisition To Resource Division | 2096/BD-I/9 | 25/11/2024 | 0 | Resource Division | 24.64 | 0 | 0 | 0
30 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08111 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raipur (Village code 315460) under Raipur (Zone-D) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-04) | 1141/BD-I | 07/07/2021 | 180 | M/S JOYDEEP DASGUPTA | 79 | 73.28 | 92.76 | 1
31 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08111 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Masurdanga ( village code 315464 ) under RAIPUR ( Zone - D ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | 1838/BD-I | 05/10/2021 | 70 | NIRMAL UDYOG | 62.56 | 0 | 0 | 0
32 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08111 | Retrofitting | Relaying of different dia DI and UPVC distribution Pipe Line instead of damage portion in between different node point for faciliating FHTC works under Raipur Surface based Water Supply Scheme under Central Sector Part-II of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1989/BD-I | 01/11/2021 | 30 | DEBASIS BOSE | 31.04 | 0 | 0 | 0
33 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08111 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jitarpur (village code 315461) , Harishpur (village code 315462) , Khosalpur ( village code 315463 ) , under RAIPUR ( Zone - D ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | 1837/BD-I | 05/10/2021 | 70 | HOQUEDAR ALI | 61.23 | 41.59 | 67.94 | 1
34 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08111 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nasipur ( village code 315482 ) under RAIPUR ( Zone - D ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | 1839/BD-I | 05/10/2021 | 40 | PARTHA PRATIM DAS | 35.44 | 0 | 0 | 0
35 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08111 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bainpur, Balarampur, Khalshi, Saharbasa, Mamlatpur, Chhota Saharbasa, Hosenpur, Jamira, Fatepur-Gobindapur & Kumipur Patharghata (Village code 315454, 315455, 315456, 315457, 315458, 315459, 315485, 315486, 315487 & 315488) under Raipur (Zone-D) Water Supply Scheme of Central Sector Part-II in Hariharpara Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-08) | 2012/BD-I | 08/11/2021 | 180 | SANJAY BISWAS | 130.03 | 89.24 | 68.63 | 85
36 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08111 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dasturpara (Village code 315484) under Raipur (Zone-D) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE.Dte. (Sl-03) | 1891/BD-I | 07/10/2021 | 180 | M/S S.DAS & ENTERPRISE | 75.05 | 63.52 | 100 | 1
37 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08111 | Retrofitting | Laying of additional extension and parallel pipe line at Mamdalipur,Raipur and Sadananpur village due to smooth functioning of Functional Household Tap Connection (FHTC) at RAIPUR Surface Water based Water Supply Scheme of Central Sector Part - II of Murshidabad District under Berhampore Division - I, PHE Dte. | 1881/BD-I | 07/10/2021 | 90 | M/S JOYDEEP DASGUPTA | 36.18 | 32.68 | 100 | 1
38 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08111 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Raipur Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | 2255/BD-I | 21/12/2021 | 90 | M/S GHOSH ENTERPRISE | 77.39 | 75.21 | 100 | 1
39 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Raipur (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08111 | Retrofitting | Additional Laying works at village Dasturpara (Village code-315484) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Raipur Surface water based Water supply scheme (Hariharpara,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | 106/BD-I | 01/02/2022 | 30 | M/S S.DAS & ENTERPRISE | 24.15 | 16.64 | 100 | 1
40 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Digha (VillageCode-314460) under command area under Digha ground water supply scheme (Part-A) , SM/06975 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Digha (Village code 314460) under Digha Ground Water based Water Supply Scheme for Bhagwangola-I (Part-A) Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 162/BD-I | 03/02/2021 | 30 | M/S. SUKUMAR SINHA | 71.28 | 29.55 | 41.45 | 1
41 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dighirpahar (314794) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-I) , SM/07282 | Retrofitting | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0 | 0
42 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dighirpahar (314794) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-I) , SM/07282 | Retrofitting | Hiring of 01(one) no. Diesel Bolero / Marshal Car for official use having licence for contract carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Islampur Sub-Division, P.H.E. Dte. Murshidabad for the period from 01-10-2021 to 30-09-2022 (i.e. twelve months) | 473/ISD. | 03/09/2021 | 365 | M/S SAJAHAN CHOWDHURY | 2.05 | 0.8 | 38.87 | 1
43 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dighirpahar (314794) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-I) , SM/07282 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dighirpahar (Village code 314794) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005182977 in the District of Murshidabad. (Sl No-08) | 2503/MURD | 17/08/2021 | 120 | SUJIT KUMAR SAHA | 70.56 | 32.43 | 100 | 1
44 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dighirpahar (314794) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-I) , SM/07282 | Retrofitting | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 734 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dighirpahar (Village code 314794) under Islampur Ground water based water supply scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005182977). | 670/MURD | 10/03/2022 | 20 | NATIONAL CONSTRUCTION (MD ASRAFUL SK) | 12.64 | 12.57 | 100 | 0
45 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Maiya Village (Code-314146) In The Command Area Of Maiya Ground Water Supply Scheme (Part-A) , SM/07734 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of MAIA (Village code 314146) under Maia Ground Water Supply Scheme of Lalgola Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 37/BD-I | 13/01/2021 | 180 | H.I ENTERPRISE | 158.61 | 212.9 | 195 | 1
46 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Dakhsin Gopalpur ground water supply scheme , SM/07228 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of DakshinGopalpur (Village code 314797) under DakshinGopalpur Ground Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-06 of 2020 ¿ 2021,SL-06) | 1465/BD-I | 16/08/2021 | 30 | DOBAY CONSTRUCTION | 44.57 | 27.2 | 61.04 | 1
47 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Dakhsin Gopalpur ground water supply scheme , SM/07228 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under Dakshin Gopalpur ground Water based Water Supply Scheme under Raninagar -I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | 437/BD-I | 12/07/2023 | 90 | SOMNATH DEY | 2.32 | 1.31 | 56.57 | 75
48 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Dakhsin Gopalpur ground water supply scheme , SM/07228 | Retrofitting | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Dakhsin Gopalpur ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1219/BD-I | 29/07/2024 | 60 | CHATTERJEE ENTERPRISE | 15.96 | 0 | 0 | 0
49 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Dakhsin Gopalpur ground water supply scheme , SM/07228 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Gajepara (Village code 314796) under DakshinGopalpur Ground Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 829/BD-I | 13/11/2020 | 60 | M/S SAJAHAN CHOWDHURY | 20.51 | 30.67 | 179.12 | 0
50 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgari (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-IV , SM/07283 | Retrofitting | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0 | 0
51 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgari (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-IV , SM/07283 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgiri (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District. | 221-MSD/21-22 | 09/12/2021 | 0 | AMAL KUMAR DAS | 7.7 | 0 | 0 | 0
52 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgari (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-IV , SM/07283 | Retrofitting | Holding Awardness Programme FHTC | 208-MSD/21-22 | 08/12/2021 | 0 | IMAGIN COMMUNICATION | 3.57 | 0 | 0 | 0
53 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgari (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-IV , SM/07283 | Retrofitting | Extension of pipeline at uncovered habitation of Kanthaliapara Year Ali to Fajit Sk house via Ali Box Sk house & Jalit Sk house under command area of Islampur Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period. | 468/ISD | 03/09/2021 | 30 | M/S. DIPTI ENTERPRISE | 3.06 | 2.17 | 100 | 0
54 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Garamgari (314792) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (Part-IV , SM/07283 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village CHAR GARAMGARIDAIR(Village code 314792) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, in the District of Murshidabad. | 259/MURD | 25/01/2021 | 45 | AMAL KUMAR DAS | 29.36 | 0 | 0 | 0
55 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Nandalalpur Arazi (314628) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshid , SM/07284 | Retrofitting | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0 | 0
56 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Nandalalpur Arazi (314628) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshid , SM/07284 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Nandalalpur (Village code 314628) under Barabil Raghunathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723213 in the District of Murshidabad. (Sl No-29) | 961/MURD | 24/03/2021 | 180 | S.M. ENTERPRISE | 50.52 | 50.15 | 49.84 | 1
57 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Nandalalpur Arazi (314628) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshid , SM/07284 | Retrofitting | Re-Laying of U.P.V.C pipe of 140 mm dia on damaged portion in between N.P 1 to 23 & N.P 25 to 33 and 110 mm Dia N.P 20 to 33,90 mm OD N.P 17 to 19 at Dakshin,Uttar Mahadebnagar & Kagchipara for smooth water supply arrangement in Mahadebnagar Zone-1 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | 244/JSD | 27/08/2021 | 10 | PRAVAT KUMAR GHOSH | 4.86 | 0 | 100 | 0
58 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Nandalalpur Arazi (314628) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshid , SM/07284 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
59 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Nandalalpur Arazi (314628) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshid , SM/07284 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
60 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Nalbatta (VillageCode-314801) under command area of Kosbagoas ground water supply scheme (Part-B) , SM/07230 | Retrofitting | Formal Work Order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nalbatta (Village code 314801) under Kasbagoas Ground Water Supply Scheme in Raninagar-I Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-09) | 1598/BD-I | 31/08/2021 | 180 | NOVELTY CONSTRUCTION | 58.29 | 46.21 | 79.28 | 1
61 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Nalbatta (VillageCode-314801) under command area of Kosbagoas ground water supply scheme (Part-B) , SM/07230 | Retrofitting | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION for Village of Nalbatta (VillageCode-314801) under command area of Kosbagoas ground water supply scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1221/BD-I | 29/07/2024 | 60 | SWARUP KUMAR BHATTA | 14.97 | 0 | 0 | 0
62 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jafarganj (313809) of Andhua under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) , SM/07296 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BHANDARA-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- BHANDARA , CODE-314524, TNO- 51/2020-21/SE-MC | 512/W | 30/03/2021 | 0 | DEBASIS BOSE | 30.48 | 0 | 0 | 0
63 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jafarganj (313809) of Andhua under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) , SM/07296 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BHALKUNDI--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 539/2020-21/EE | 512/W | 30/03/2021 | 0 | M/S GUNGUN CONSTRUCTION | 10.66 | 0 | 0 | 0
64 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jafarganj (313809) of Andhua under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) , SM/07296 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BHANDARA--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- KOLAN RADHAKANTAPUR , CODE-314523, TNO- 50/2020-21/SE-MC | 512/W | 30/03/2021 | 0 | M/S GUNGUN CONSTRUCTION | 33.58 | 0 | 0 | 0
65 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jafarganj (313809) of Andhua under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) , SM/07296 | Retrofitting | Material Requisition To Resource Division | 540/7/MURD | 25/02/2022 | 0 | Resource Division | 6.92 | 0 | 0 | 0
66 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jafarganj (313809) of Andhua under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) , SM/07296 | Retrofitting | Providing Functional Household Tap Connections (FHTC) 1261 nos in connection with Jal Swapna (Jal Jeevan Mission ) of Mouza Jafarganj ( Village Code -313809) under Andhua Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. | 1082/MURD | 27/04/2022 | 45 | MARUTI CONSTRUCTION AND CO | 62.56 | 54.08 | 69.4 | 0
67 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) , SM/07767 | Retrofitting | Re-Laying of U.P.V.C pipe of 90 mm dia on damaged portion 90 mm dia U.P.C Pipe in between N.P 3(Pry. School) to N.P 12 via N.P 15 upto N.P 16(Bansabati G.P Member Loton Sara's House) for smooth water supply arrangement in Raturi Zone-2 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | 198/JSD | 30/07/2021 | 30 | GAUTAM KUMAR CHAUDHURI | 3.81 | 3.81 | 100 | 1
68 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) , SM/07767 | Retrofitting | Laying of U.P.V.C New Extention pipeline of 90 mm dia in between N.P 6(Durga Mandir) to N.P 12 Upto Pond for smooth water supply arrangement in Raturi Zone-2 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | 199/JSD | 30/07/2021 | 15 | GAUTAM KUMAR CHAUDHURI | 1.43 | 1.43 | 100 | 1
69 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) , SM/07767 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection of different existing PWSS Scheme, Block-SUTI-I to be Augmentation / Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 402 of 21-22 by EE MURD | 301-MSD/21-22 | 04/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.77 | 0 | 0 | 0
70 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) , SM/07767 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Bamuha, Khidirpur, Khanpur (Nos FHTC-2996 Nos) (Village code-313962,313990,313989) under PRASADPUR Ground Water Based Water Supply Scheme of Suti-II Block and Kalinagar (FHTC-4077 Nos) (Village code-313899) under Raturi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID-0005019110 & 0001723413) | 558/MURD | 28/02/2022 | 180 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 332.59 | 0 | 0 | 0
71 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) , SM/07767 | Retrofitting | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Jangipur Road Station to Gankar Station ( TP NO 210/09 & 211/00) at Kanupur mouza & Connecting with existing 160 mm dia UPVC distribution main line of Jarur Surface based W/S Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. | 547/MURD | 05/02/2021 | 30 | PRADIP KUMAR DAS | 39.01 | 26.23 | 100 | 100
72 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kalinagar ( 313899 ) of Raturi Zone-I under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District ( PART-I) , SM/07767 | Retrofitting | Material Requisition To Resource Division | 3632/C/MURD | 23/11/2021 | 0 | Resource Division | 22.88 | 0 | 0 | 0
73 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dighirpar ( 314125 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PAR , SM/07508 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village DIGHIRPAR (Village Code-314125) under sarface water based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the dist of Murshidabad District under Murshidabad Division, PHE Dte. Scheme ID: 0001756852 in the dist of MSD |  | 06/08/2021 | 0 | JAMIRUL CONSTRUCTION | 38.25 | 0 | 0 | 0
74 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dighirpar ( 314125 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PAR , SM/07508 | Retrofitting | CONT OF AWARENESS PROGRAMME AT DIFFERENT G.PS, TNO- 05/21-22/AE-LSD | 209-MSD/21-22 | 08/12/2021 | 0 | S.S.INFRASTRUCTURE | 2.12 | 0 | 0 | 0
75 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dighirpar ( 314125 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PAR , SM/07508 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dighirpar( Village Code -314125) under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001756852). | 576/MURD | 09/02/2021 | 60 | JAMIRUL CONSTRUCTION | 41.39 | 78.52 | 189.68 | 0
76 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Salar (315742 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murshidabad District ( PART-I ) , SM/07768 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village SALAR (Village Code 315742) under SALAR Ground Water Based Water Supply Scheme for arsenic affected areas of BHARATPUR-II Block in the District of Murshidabad. Tender no - 127 of 21-22 by SE MC | 84-MSD/22-23 | 28/04/2022 | 0 | MAMATA USHA ENTERPRISE | 38.32 | 0 | 0 | 0
77 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Salar (315742 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murshidabad District ( PART-I ) , SM/07768 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SALAR G.P. under Murshidabad Division, P.H.E.Dte. | 236/KSD | 27/08/2021 | 60 | IMAGIN | 4.15 | 0 | 0 | 0
78 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Salar (315742 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murshidabad District ( PART-I ) , SM/07768 | Retrofitting | Holding Awarness Programme / Campaigning programms at Salar G.P, Talibpur G.P, Kagram G.P, Tenya Baidyapur G.P and Simulia G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. (Total nos of Programme = 20 nos) (Part-D). | 252/KSD | 31/08/2021 | 30 | IMAGIN | 4 | 0 | 0 | 0
79 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Salar (315742 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murshidabad District ( PART-I ) , SM/07768 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of SALAR (Village code 315742) under SALAR Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division, PHE Dte.( Scheme ID 0005252601) | 3975/MURD | 21/12/2021 | 180 | MAMATA USHA ENTERPRISE | 153.26 | 102.61 | 100 | 1
80 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Salar (315742 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murshidabad District ( PART-I ) , SM/07768 | Retrofitting | Repairing of rising main & distribution line at Rail gate & Block road etc with construction of thrust block & laying of pipe line of new habitation of Salar Water Supply scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 296/KSD | 07/10/2021 | 30 | DAS CONSTRACTION (MUNNA DAS) | 4.1 | 0 | 0 | 10
81 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Madhya Gobindopur (Code-314485), Maheshpur(Code-314486) In The Command Area Of Bhundar Kismat Ground Water Supply , SM/07794 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Madhya Gobindapur (Village code 314485) ,Mahespur (Village code 314486) under Bhundar Kismat Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | 201/BD-I | 04/02/2021 | 30 | TARUN KUMAR BHATTACHARYA | 63.97 | 48.54 | 75.88 | 1
82 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bausi (Code-314208) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(Part-B) , SM/07714 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of BAUSI (Village code 314208) under Bajupur Madhupur Ground Water based Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. | 266/ BD-I | 12/02/2021 | 180 | M/S JOGMAYA ENTERPRISE | 62.05 | 54.25 | 100 | 100
83 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bausi (Code-314208) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(Part-B) , SM/07714 | Retrofitting | Additional Laying works at village Bausi to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bajipur Madhupur water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 99/BD-I | 01/02/2022 | 20 | M/S JOGMAYA ENTERPRISE | 23.01 | 20.92 | 100 | 100
84 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-I Ground Water Supply Scheme Under Nawda Block In Murshidabad District , SM/07721 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-57C/5576 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2023 to 31.12.2023. | 1385/BD-I | 23/12/2022 | 365 | SEBAYAN CONSTRUCTION | 1.81 | 3.17 | 100 | 71
85 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hasimpur (313861) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District (PART-I) , SM/07771 | Retrofitting | Laying of different dia UPVC pipe line in connection with FHTC work at Jyatkundu, village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-D). | 234/JSD | 05/05/2022 | 30 | APU CONSTRUCTION | 4.83 | 0 | 0 | 1
86 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hasimpur (313861) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District (PART-I) , SM/07771 | Retrofitting | Laying of different dia UPVC pipe line in connection with FHTC work at Jyatkundu, village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-E). | 236/JSD | 05/05/2022 | 30 | NATIONAL CONSTRUCTION (MD ASRAFUL SK) | 4.82 | 0 | 0 | 1
87 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hasimpur (313861) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District (PART-I) , SM/07771 | Retrofitting | Laying of different dia UPVC pipe line in connection with FHTC work at Dhusaripara colony village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-A). | 231/JSD | 05/05/2022 | 30 | DIPAYAN DEY | 4.84 | 0 | 0 | 1
88 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hasimpur (313861) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District (PART-I) , SM/07771 | Retrofitting | Laying of different dia UPVC pipe line in connection with FHTC work at Hasimpur, village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-B). | 232/JSD | 05/05/2022 | 30 | BARMAN ENTERPRISE | 4.82 | 0 | 0 | 1
89 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hasimpur (313861) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District (PART-I) , SM/07771 | Retrofitting | Laying of different dia UPVC pipe line in connection with FHTC work at Hasimpur, village Hasimpur (Village Code-313861) under Hasimpur Ground Water Supply Scheme for Arsenic Affected areas of Samserganj Block under Jangipur Sub-Division under Murshidabad Division, P.H.E Dte. (Part-C). | 233/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.8 | 0 | 0 | 1
90 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hasimpur (313861) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District (PART-I) , SM/07771 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
91 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hasimpur (313861) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District (PART-I) , SM/07771 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
92 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hasimpur (313861) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District (PART-I) , SM/07771 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village RAMAKANTAPUR (Village code 314029) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756489 in the District of Murshidabad. (Sl No-1) | 3115/MURD | 09/12/2020 | 180 | M/S. SINHA & SONS | 65.21 | 0.58 | 100 | 100
93 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hasimpur (313861) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District (PART-I) , SM/07771 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Hasimpur ( Village Code -313861) under Hasimpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723174) | 398/MURD | 16/02/2022 | 60 | DIPAYAN DEY | 71.07 | 65.57 | 92.27 | 1
94 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hasimpur (313861) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District (PART-I) , SM/07771 | Retrofitting | Laying of DI pipeline and supplying of CI specials for interconnection of 2nd Tubewell site at Kankuria Jafrabad & Dogachi(zone-II) and 1st Tubewell site at Hasimpur& Bhasaipaikar(zone-I) and of Jangipur Sub-Division under Murshidabad Division, PHE Dte. | 569/MURD | 28/02/2023 | 30 | MAA CONSTRUCTION | 2.6 | 2.61 | 100 | 100
95 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hosenpur, Hilora & Lalupur (313888, 313898 & 313890) of Kusumgachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murs , SM/07773 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Lalupur ( Village Code -313890) under Kusumgachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723224) | 596/MURD | 09/02/2021 | 60 | PRATAP KUMAR SINHA | 6.24 | 0 | 0 | 1
96 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hosenpur, Hilora & Lalupur (313888, 313898 & 313890) of Kusumgachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murs , SM/07773 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village LALUPUR (Village Code: 313890) under KASUMGACHHI Ground Water Based Water Supply Scheme for arsenic affected areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID- 0001723224). Tender no- 782 of 20-21 by EE / MSD | 10-MSD / 21-22 | 06/08/2021 | 0 | M/S PRATAP KUMAR SINHA | 4.24 | 0 | 0 | 0
97 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hosenpur, Hilora & Lalupur (313888, 313898 & 313890) of Kusumgachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murs , SM/07773 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hosenpur, Hilora & Lalupur (313888, 313898 & 313890) of Kusumgachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District (PART-I), tno- 895/20-21/EE | 171-MSD/21-22 | 28/10/2021 | 0 | HOQUEDAR ALI | 59.07 | 0 | 0 | 0
98 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hosenpur, Hilora & Lalupur (313888, 313898 & 313890) of Kusumgachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murs , SM/07773 | Retrofitting | Construction of allied balance work of ¿¿HILORA ¿..under JSD PHE DTE. Tender no - 66 of 21-22 by AE JSD | 02-MSD/22-23 | 14/04/2022 | 0 | SAMAR MUKHERJEE | 4.97 | 0 | 0 | 0
99 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hosenpur, Hilora & Lalupur (313888, 313898 & 313890) of Kusumgachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murs , SM/07773 | Retrofitting | Interconnection of DI pipe line between allied balance work of ¿¿HILORA ¿..under Murshidabad Div PHE DTE. Tender no - 67 of 21-22 by AE JSD | 01-MSD/22-23 | 14/04/2022 | 0 | SAMAR MUKHERJEE | 4.85 | 0 | 0 | 0
100 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hosenpur, Hilora & Lalupur (313888, 313898 & 313890) of Kusumgachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murs , SM/07773 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Hilora ( Village Code -313898) under Kusumgachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723224) | 593/MURD | 09/02/2021 | 60 | HOQUEDAR ALI | 64.7 | 0 | 0 | 1
101 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Santoshpur Village (Code-315634), Chandpur Village (Code-315635) Under Command Area Of Mashimpur Ground Water Supply Scheme (Part , SM/07889 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Santoshpur (Village code 315634), Chandpur (Village code 315635) under Mashimpur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-B) | 200/BD-I | 04/02/2021 | 20 | MD TALEB ALI | 34.35 | 0 | 0 | 0
102 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Santoshpur Village (Code-315634), Chandpur Village (Code-315635) Under Command Area Of Mashimpur Ground Water Supply Scheme (Part , SM/07889 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Santoshpur Village (Code-315634), Chandpur Village (Code-315635) Under Command Area Of Mashimpur Ground Water Supply Scheme (Part-B)" Under Beldanga-II Block in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1435/BD-I | 04/09/2024 | 30 | M/S ARIYAN ENTERPRISE | 14.6 | 0 | 0 | 0
103 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Kalmegha (Code-314221) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-D) Under Lalgola Block In , SM/07788 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kaimegha(Village code 314221) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-D) | 205/BD-I | 04/02/2021 | 30 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 83.83 | 81.09 | 96.73 | 1
104 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Kalmegha (Code-314221) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-D) Under Lalgola Block In , SM/07788 | Retrofitting | Additional Laying works at village Kaimegha, to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bansgara Ground water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 2292/BD-I | 28/12/2021 | 10 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 6.8 | 6.24 | 100 | 1
105 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bhundar Kismat (Code-314468) In The Command Area Of Bhundar Kismat Ground Water Supply Scheme (Part-A) Under Bhagw , SM/07793 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Bhundar Kismat (Code-314468) In The Command Area Of Bhundar Kismat Ground Water Supply Scheme (Part-A) Under Bhagwangola-I Block)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1203/BD-I | 26/07/2024 | 60 | M/S S.R.K ENTERPRISE | 31.89 | 0 | 0 | 0
106 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-A). | 379/JSD | 31/12/2021 | 30 | S.D PROJECT | 4.77 | 0 | 0 | 0
107 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-B). | 380/JSD | 31/12/2021 | 30 | S.D PROJECT | 4.77 | 0 | 0 | 0
108 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | Sinking of (300 mm x 200 mm) dia Big dia tube well 75 mtr. Deep by direct rotary rig method using UPVC Pipe and RDS filter at Village Kankuria (Village Code-313873) in connection with FHTC work of Kankuria Jafrabad Water Supply Scheme (Scheme ID- 0006303234) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | 239/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.42 | 0 | 0 | 1
109 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | Supply of UPVC Pipe and RDS filter for the work of Sinking of (300 mm x 200 mm) dia Big dia tube well at Village Kankuria (Village Code:-313873) in connection with FHTC work of Kankuria Jafrabad Water Supply Scheme (Scheme Id:-0006303234) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | 240/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.6 | 0 | 0 | 1
110 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | Work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-C) | 395/JSD | 31/12/2021 | 30 | M/S. SRM ENTERPRISE | 4.77 | 4.17 | 100 | 0
111 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | work of Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria & Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006303234) (Part-D) | 377/JSD | 31/12/2021 | 30 | R.K.CONSTRUCTION(SOHEL RANA KHAN) | 4.77 | 4.76 | 100 | 0
112 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-G). | 125/JSD | 22/03/2022 | 30 | YOUSUF ENTERPRISE | 4.8 | 4.6 | 100 | 0
113 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-E) | 118/JSD | 22/03/2022 | 30 | S.D PROJECT | 4.85 | 4.85 | 100 | 0
114 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-F). | 119/JSD | 22/03/2022 | 30 | S.D PROJECT | 4.84 | 4.84 | 100 | 0
115 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kankuria (Village Code-313873) under Kankuria Jafrabad Ground Water Based water supply scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723168) (Part-H). | 120/JSD | 22/03/2022 | 30 | S.D PROJECT | 4.76 | 4.73 | 100 | 0
116 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village KANKURIA (Village Code 313873) under KANKURIA AND JAFRABAD Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 98 of 21-22 by AE JSD | 388-MSD/21-22 | 17/03/2022 | 0 | S.D PROJECT | 4.77 | 0 | 0 | 0
117 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of Village JAFRABAD (Village Code 313872) under KANKURIA and jafrabad Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 475 of 21-22 by EE MURD | 347-MSD/21-22 | 05/03/2022 | 0 | NILKAMAL BASAK | 91.86 | 0 | 0 | 0
118 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village KANKURIA (Village Code 313873) under KANKURIA AND JAFRABAD Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 98 of 21-22 by AE JSD | 389-MSD/21-22 | 17/03/2022 | 0 | S.D PROJECT | 4.77 | 0 | 0 | 0
119 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-I) |  | 17/02/2022 | 0 | NILKAMAL BASAK | 91.86 | 0 | 0 | 0
120 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | Material Requisition To Resource Division | 540/10/MURD | 25/02/2022 | 0 | Resource Division | 12.11 | 0 | 0 | 0
121 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jafrabad ( Village Code -313872) & (adjoining habitation) (Part-IV) under Kankuria & Jafrabad Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006303234) | 2536/MURD | 19/08/2021 | 60 | M/S. M.R. CONSTRUCTION (PROP: MASUD RANA) | 67.49 | 0 | 0 | 0
122 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kankuria (313873) of Kankuria & Jafrabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART- , SM/08195 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Jafrabad ( Village Code -313872 & adjoining habitation (Part-III) under Kankuria&Jafrabad Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006303234) | 2539/MURD | 19/08/2021 | 1680 | IKON CONSTRUCTION | 80.14 | 0 | 0 | 30
123 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Herampur (314799), Goas Kalikapur (314800), Sitanagar (314802) & Raipur (314803 ) of Herampur under Ground Water Based Water Supply Scheme for arsenic affected area , SM/08199 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Raghunathpur (Village code 314783) under Tekaraipara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756480 in the District of Murshidabad. | 321/MURD | 28/01/2021 | 60 | M/S BAPPA ENTERPRISE | 13.73 | 0 | 0 | 1
124 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Herampur (314799), Goas Kalikapur (314800), Sitanagar (314802) & Raipur (314803 ) of Herampur under Ground Water Based Water Supply Scheme for arsenic affected area , SM/08199 | Retrofitting | New laying of different dia UPVC pipeline to restore the distribution system (Besides of Sukdevmati Bridge) in Retrofitting Providing Functional House Hold Tap Connection FHTC in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Chainpara (314804) under Herampur Zone-II) Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. | 302/ISD | 20/07/2022 | 30 | PRATICHI ENTERPRISE | 3.31 | 2.86 | 86.22 | 0
125 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Herampur (314799), Goas Kalikapur (314800), Sitanagar (314802) & Raipur (314803 ) of Herampur under Ground Water Based Water Supply Scheme for arsenic affected area , SM/08199 | Retrofitting | Providing Balance Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Sitanagar ( Village Code -314802) under Herampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005183990) | 857/MURD | 31/03/2022 | 60 | PRIYANKA CONSTRUCTION | 49.23 | 44.68 | 100 | 0
126 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Herampur (314799), Goas Kalikapur (314800), Sitanagar (314802) & Raipur (314803 ) of Herampur under Ground Water Based Water Supply Scheme for arsenic affected area , SM/08199 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Sitanagar ( Village Code -314802) under Herampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005183990). | 590/MURD | 09/02/2021 | 60 | PRIYANKA CONSTRUCTION | 26.4 | 23.39 | 100 | 1
127 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) , SM/08200 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari ( Village Code -314604)(Part-III) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) | 2501/MURD | 17/08/2021 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 88.6 | 36.18 | 40.83 | 1
128 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) , SM/08200 | Retrofitting | Preparation of D.P.R(Consultancy work)in connection with the Functional Household Connection of different existing PWSS (Khairamari PWSS Scheme,Block- Jalangi) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 367 of 21-22 by EE MSD, and Scheme Code: 8200 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 8.31 | 0 | 0 | 0
129 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) , SM/08200 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) |  | 17/02/2022 | 0 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 9.83 | 0 | 0 | 0
130 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) , SM/08200 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari (Village Code -314604)(Part-I) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) Tender no - 244 of 21-22 by EE MURD | 338-MSD/21-22 | 03/03/2022 | 0 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 31.7 | 0 | 0 | 0
131 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) , SM/08200 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Harekrishnapur ( Village Code -314624) under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) Tender no - 243 of 21-22 by EE MURD | 333-MSD/21-22 | 25/02/2022 | 0 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 9.83 | 0 | 0 | 0
132 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) , SM/08200 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | 299/BSD | 13/08/2021 | 30 | IMAGIN COMMUNICATION | 4.34 | 8.67 | 200 | 0
133 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) , SM/08200 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari (Village Code -314604)(Part-I) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) | 2300/MURD | 02/08/2021 | 60 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 90.75 | 103.02 | 113.53 | 0
134 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Khayramari ( 314604) of Khayramari under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad District ( PART-I ) , SM/08200 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khayramari ( Village Code -314604)(Part-II) & adjoining habitation under Khayramari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184125) | 2435/MURD | 12/08/2021 | 60 | BISWAS ENTERPRISE (PROP. JESMIN KHATUN) | 92.84 | 0 | 0 | 1
135 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bajupur Madhapur (Code-314235), Nadaipur (Code-314205), Upar Fatepur (Code-314212) In The Command Area Of Bajupu , SM/08899 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahapur (Village code 315210), Upar Fatepur (Village Code 314212) & Bajupur Madhupur (Village Code 314235) under Bajupur Madhupur Ground Water Supply Scheme for Lalgola Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 994/BD-I | 17/12/2020 | 180 | BIJOY CHOWDHURY | 253.85 | 176.93 | 79.53 | 1
136 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bajupur Madhapur (Code-314235), Nadaipur (Code-314205), Upar Fatepur (Code-314212) In The Command Area Of Bajupu , SM/08899 | Retrofitting | Additional Laying works at village Sahapur, Upar Fatepur and Bajipur Madhupur (Village code-314210,314212 and 314235) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bajipur Madhupur Ground water based Water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | 2314/BD-I | 29/12/2021 | 45 | BIJOY CHOWDHURY | 13.36 | 10.9 | 100 | 1
137 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bajupur Madhapur (Code-314235), Nadaipur (Code-314205), Upar Fatepur (Code-314212) In The Command Area Of Bajupu , SM/08899 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of NADAIPUR (Village code 314205) under Bajupur Madhupur Ground Water based Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. | 921/BD-I | 11/12/2020 | 1846 | H.I ENTERPRISE | 95.04 | 18.68 | 19.66 | 59
138 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kashipur Village (Code-315687), Jhikra Village (Code-315688) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-C) U , SM/08902 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kashipur (Village code 315687) under Kashipur Water Supply Scheme of Beldanga II Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-13) | 1867/BD-I | 07/10/2021 | 180 | TEKNO ENTERPRISE | 122.6 | 107.94 | 88.05 | 1
139 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kashipur Village (Code-315687), Jhikra Village (Code-315688) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-C) U , SM/08902 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhikra (Village code 315688) under Kashipur Water Supply Scheme of Beldanga II Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-12) | 1887/BD-I | 07/10/2021 | 180 | HANNAN BUILDERS PVT. LTD. | 92.96 | 90.95 | 97.83 | 1
140 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kashipur Village (Code-315687), Jhikra Village (Code-315688) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-C) U , SM/08902 | Retrofitting | Additional Laying works at village Kashipur (Village code-315687) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Kashipur Ground water based Water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | 97/BD-I | 01/02/2022 | 30 | TEKNO ENTERPRISE | 9.18 | 8.98 | 100 | 100
141 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Haribhanga Daulatpur, Ramipur, Tekaraipur, Borakuli, Balumati (314785, 314786, 314788, 314789 & 314790) of Tekaraipara under Ground Water Based Water Supply Scheme , SM/08276 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village RAGHUNATHPUR (Village Code 314783) under TEKARAIPUR Ground Water Based Water Supply Scheme for arsenic affected areas of RANINAGAR-II Block in the District of Murshidabad. Tender no - 695 of 20-21 by EE MURD | 105-MSD/22-23 | 06/05/2022 | 0 | M/S BAPPA ENTERPRISE | 13.72 | 0 | 0 | 0
142 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Haribhanga Daulatpur, Ramipur, Tekaraipur, Borakuli, Balumati (314785, 314786, 314788, 314789 & 314790) of Tekaraipara under Ground Water Based Water Supply Scheme , SM/08276 | Retrofitting | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village Tekaraipur (Village code-314788) under Tekaraipara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division P.H.E Dte. (Scheme ID-0001756480) | 2686/MURD | 22/09/2022 | 120 | S.D. PROJECT | 132.63 | 132.24 | 100 | 100
143 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Haribhanga Daulatpur, Ramipur, Tekaraipur, Borakuli, Balumati (314785, 314786, 314788, 314789 & 314790) of Tekaraipara under Ground Water Based Water Supply Scheme , SM/08276 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Borakuli (Village code 314789) under Tekaraipara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756480 in the District of Murshidabad. | 325/MURD | 28/01/2021 | 60 | MADAN MOHAN SASMAL | 14.03 | 20.73 | 200 | 1
144 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Haribhanga Daulatpur, Ramipur, Tekaraipur, Borakuli, Balumati (314785, 314786, 314788, 314789 & 314790) of Tekaraipara under Ground Water Based Water Supply Scheme , SM/08276 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Balumati (Village code 314790) under Tekaraipara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756480 in the District of Murshidabad. | 33/MURD | 05/01/2021 | 60 | DOBAY CONSTRUCTION | 36.55 | 27.86 | 76.22 | 1
145 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mahalandi under Mahalandi (Zone-I)Ground Water Based Water Supply Scheme for Arsenic Affected Area of Kandi Block, under Murshidabad Division, PHE Dte. Scheme ID 0007585495 in the District of Murshidabad. | 692 / MURD | 23/02/2021 | 180 | M/S . SUKUMAR SINHA | 113.1 | 60.7 | 53.67 | 1
146 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Laying of UPVC pipeline at Bagpur and Gantla Village for FHTC work of Gantla Village ( Village Code- 315215) of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. | 06 / KSD | 06/04/2022 | 30 | ABHIJIT MONDAL | 4.85 | 4.84 | 100 | 1
147 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BELUN (Village Code 315216) under MAHALANDI Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. Tender no - 476 of 21-22 by EE MURD | 394-MSD/21-22 | 22/03/2022 | 0 | PRIME CONSTRUCTION | 11.24 | 0 | 0 | 0
148 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Holding Awarness Programme / Campaigning programms at Jasahari Anukha-I & II G.P, Mahalandi-I G.P, Kumarsanda G.P and Gokarna-I G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (Total nos of Programme = 20 nos) (Part-A). | 249/KSD | 31/08/2021 | 30 | IMAGIN | 4 | 0 | 0 | 0
149 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHALANDI-I G.P. under Murshidabad Division, P.H.E.Dte. | 227/KSD | 27/08/2021 | 60 | IMAGIN COMMUNICATION | 4.17 | 0 | 0 | 0
150 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at KUMARSANDA G.P. under Murshidabad Division, P.H.E.Dte. | 228/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.15 | 0 | 0 | 0
151 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | 212/KSD | 11/08/2021 | 30 | IMAGIN | 4.33 | 0 | 0 | 0
152 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Construction of pathway at Head work Site of Mahalandi (Zone-I) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 13 / KSD | 06/04/2022 | 30 | HERITAZE CONSTRUCTION | 3.92 | 3.91 | 100 | 1
153 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Construction of surface drain and development of land at Head work Site of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 123/KSD | 25/07/2022 | 30 | KAKALI ENTERPRISE | 3.58 | 3.58 | 100 | 1
154 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Repairing of leakage & bursting of UPVC pipe line of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 213 / KSD | 17/02/2023 | 30 | A.P. CONSTRUCTION | 0.96 | 0.96 | 100 | 1
155 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Laying of UPVC pipe line from Head work site to near house of Kalimuddin Sk for drain out of OHR overflow water under Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 212 / KSD | 17/02/2023 | 30 | A.P. CONSTRUCTION | 0.97 | 0.97 | 100 | 1
156 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Laying of UPVC pipeline from Danarul Sk Shop to Gantla Ashram for FHTC work of Gantla Village (Village Code- 315215) of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. | 106 / KSD | 17/06/2022 | 30 | DEBJYOTI MUKHERJEE | 4.83 | 4.82 | 100 | 1
157 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Material Requisition To Resource Division | 541/1/MURD | 25/02/2022 | 0 | Resource Division | 6.96 | 0 | 0 | 0
158 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mahalandi under Mahalandi (Zone-I)Ground Water Based Water Supply Scheme for Arsenic Affected Area of Kandi Block, under Murshidabad Division, PHE Dte. Scheme ID ¿ 0007585495 in the District of Murshidabad. | 692/MURD | 23/02/2021 | 180 | M/S . SUKUMAR SINHA | 113.1 | 0 | 0 | 0
159 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal JeevanMission and Jal Swapna under command area of village Gantla under Mahalandi (Zone-II) Ground Based Water Based Water Supply Scheme for Arsenic Affected Area of Kandi Block under Murshidabad Division, PHE Dte. Scheme ID 0007585495 in the District of Murshidabad. (Sl No-20) | 3051/MURD | 08/12/2020 | 180 | M/S. BIMALENDU BOSE | 69.15 | 68.88 | 100 | 95
160 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Sole Para ( Village Code -315217) under Mahalandi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Kandi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0007585495) | 305/MURD | 07/02/2022 | 60 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 61.94 | 14.61 | 23.59 | 1
161 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BELUN (Village Code : 315216) under Mahalandi Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. | 3038/MURD | 07/12/2020 | 1606 | PRIME CONSTRUCTION | 19.31 | 0 | 0 | 50
162 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khordda Narayanpur, Bahadurpur, Gatia, Belun, Solepara, Durlabhpur, Mahalandi (315212, 315214, 315215, 315216, 315217, 315218, 315231) of Mahalandi under Ground Wa , SM/08282 | Retrofitting | Laying of DI pipe in between node point 1A to 29 & supplying of C.I specials of Mahalandi (Zone-I) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the District of Murshidabad. | 211/KSD | 17/02/2023 | 830 | JYOTI TRADERS | 0.97 | 0 | 0 | 60
163 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jigri Kulgachhi ( 313823 ) of Mahadevnagar Zone - I and II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad , SM/09743 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Farakka Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. | 368/JSD | 22/12/2021 | 30 | IMAGIN | 3.1 | 0 | 0 | 0
164 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jigri Kulgachhi ( 313823 ) of Mahadevnagar Zone - I and II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad , SM/09743 | Retrofitting | HIRING OF CAR FOR EE-MSD, MSD DIVN, W/O NO- 293/HQ, DT-29/11/2021 | 186-MSD/22-23 | 24/06/2022 | 0 | DULAL CHOWDHURY | 0.78 | 0 | 0 | 0
165 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jigri Kulgachhi ( 313823 ) of Mahadevnagar Zone - I and II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad , SM/09743 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-10 | 289-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 6.29 | 0 | 0 | 0
166 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jigri Kulgachhi ( 313823 ) of Mahadevnagar Zone - I and II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad , SM/09743 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-11 | 289-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 6.29 | 0 | 0 | 0
167 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jigri Kulgachhi ( 313823 ) of Mahadevnagar Zone - I and II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad , SM/09743 | Retrofitting | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 0 | 0 | 1
168 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jigri Kulgachhi ( 313823 ) of Mahadevnagar Zone - I and II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad , SM/09743 | Retrofitting | Re-Laying of U.P.V.C pipe of 140 mm dia on damaged portion in between N.P 1 to 23 & N.P 25 to 33 and 110 mm Dia N.P 20 to 33,90 mm OD N.P 17 to 19 at Dakshin,Uttar Mahadebnagar & Kagchipara for smooth water supply arrangement in Mahadebnagar Zone-1 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | 244/JSD | 27/08/2021 | 10 | PRAVAT KUMAR GHOSH | 4.86 | 4.86 | 100 | 0
169 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jigri Kulgachhi ( 313823 ) of Mahadevnagar Zone - I and II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad , SM/09743 | Retrofitting | Providing Functional Household Tap Connections (FHTC) (2145 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Mahadeb Nagar ( Village Code -313823) under Mahadebnagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. | 3498/MURD | 08/11/2023 | 90 | N. H. ENTERPRISE (PROP. NAJMUL HOQUE) | 77.63 | 0 | 0 | 0
170 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bara Jumla (314144) Krishna Sail (314143) of Putia & adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II , SM/09746 | Retrofitting | Cleaning & Washing of pipe line at Village Bara Jumla (Village Code-314144) & Krishna Sail (Village Code- 314143) in cinnection with FHTC work under Putia Water Supply Scheme) | 259/JSD | 01/06/2022 | 30 | BISWAS CONSTRUCTION PAN NO : AHNPB6929M | 4.02 | 4.04 | 100 | 0
171 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bara Jumla (314144) Krishna Sail (314143) of Putia & adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II , SM/09746 | Retrofitting | Laying pipe line at village Bara Jumla (Village Code- 314144) & Krishnaa Sail (Village Code-314143) in connection with FHTC work under Putia Water Supply Scheme under Jangipur Sub-Division under Murshidabad Division, P.H.Engineering Dte.https://app2.wbphed.gov.in/phed_v3/FAF00242/openDetail01new.html | 274/JSD | 01/06/2022 | 30 | BISWAS CONSTRUCTION PAN NO : AHNPB6929M | 3.85 | 3.85 | 99.86 | 0
172 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bara Jumla (314144) Krishna Sail (314143) of Putia & adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II , SM/09746 | Retrofitting | Material Requisition To Resource Division | 889/D/MURD | 05/04/2022 | 0 | Resource Division | 30.5 | 0 | 0 | 0
173 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Bhagabanbati (315342) for Bara Satui under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block in Murshidabad District under Murshidabad Divisio , SM/11163 | Augmentation | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Bhagabanbati (315342) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad Division Phe Dte. | 1201/MURD | 10/05/2022 | 60 | DIPAYAN DEY | 32.59 | 9.6 | 29.47 | 0
174 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Bhagabanbati (315342) for Bara Satui under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block in Murshidabad District under Murshidabad Divisio , SM/11163 | Augmentation | Providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission of 810 nos household under command area of village of Bhagabanbati( Village Code -315342) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0001723177) | 1449/MURD | 01/06/2022 | 1127 | S. K. ENTERPRISE (PROP:SHAMIM ISLAM) | 36.57 | 0 | 0 | 0
175 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF AHIRON BLOCK-SUTI - I , SM/11164 | Augmentation | Material Requisition To Resource Division | 1167/MURD/1 | 28/04/2023 | 0 | Resource Division | 68.84 | 0 | 0 | 0
176 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF AHIRON BLOCK-SUTI - I , SM/11164 | Augmentation | Laying distribution pipe lines with allied works in connection With Augmentation of Ahiron Water Supply Scheme In Suti - I Block Of Murshidabad District under Murshidabad Division,P.H.E Dte | 130/MURD | 16/01/2023 | 60 | M/S RUBIET HOSSAIN | 94.31 | 0 | 0 | 0
177 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF AHIRON BLOCK-SUTI - I , SM/11164 | Augmentation | Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works & Repair of Boundary Wall (140m + 50m)=190 m at T/W-I site & T/W-II site and Construction of approach road of 80 m ,3 mtr wide and 150 mm depth with 1:2:4 ordinary cement concrete with 75 mm sand filling and BFS for Augmentation of Ahiron Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte.(Attached as Annexure -I) | 3561/MURD | 21/11/2023 | 60 | ASHEM ENTERPRISE | 8.58 | 8.54 | 100 | 100
178 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF AHIRON BLOCK-SUTI - I , SM/11164 | Augmentation | AHIRON & adjoining mouzas PWSS to accommodate Rising Main with allied Laying Distribution under Jal Jeevan Mission, Block- SUTI-I of JANGIPUR Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | 822/MURD | 15/03/2024 | 60 | S. DUTTA | 6.88 | 6.83 | 100 | 100
179 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Chandabad ( 315517 ) of Ghoramara under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad Di , SM/09837 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission ) at village of Chandabad east side ( Village Code _315517) of Ghoramara Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | 107/BSD | 28/03/2022 | 30 | SUMAN CHOWDHURY | 4.82 | 4.7 | 100 | 0
180 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Chandabad ( 315517 ) of Ghoramara under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad Di , SM/09837 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission ) at village of Chandabad west side ( Village Code _315517) of Ghoramara Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | 150/BSD | 12/04/2022 | 30 | M/S S.R.K.ENTERPPRISE, | 4.7 | 4.59 | 100 | 0
181 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Chandabad ( 315517 ) of Ghoramara under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad Di , SM/09837 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandabad (Village code 315517) under Ghoramara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723483 in the District of Murshidabad. | 3137/MURD | 11/12/2020 | 60 | M/S. CHOWDHURY CONSTRUCTION | 23.85 | 47.23 | 100 | 0
182 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur ( 314775 ) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Mursh , SM/09844 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sinkaipur (Village code 314775) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte Scheme ID 0005019112 in the District of Murshidabad. | 1617 / MURD | 28/06/2021 | 60 | DAS ENTERPRISE (PROP-DIPAK DAS) | 5.14 | 0 | 0 | 0
183 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur ( 314775 ) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Mursh , SM/09844 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur (314775) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no - 241 of 21-22 by EE MURD | 342-MSD/21-22 | 05/03/2022 | 0 | DAS ENTERPRISE (PROP-DIPAK DAS) | 3.97 | 0 | 0 | 0
184 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur ( 314775 ) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Mursh , SM/09844 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sinkaipur (314775) of Azmatpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. ( PART-II ) |  | 17/02/2022 | 0 | DAS ENTERPRISE (PROP-DIPAK DAS) | 3.97 | 0 | 0 | 0
185 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Paraspur ( 314616 ) of Muradpur-Jalangi (Zone-I, Zone - II & Zone - III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block o , SM/09845 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village PARASPUR (Village Code 314616) under Muradpur-Jalangi Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block in the District of Murshidabad. | 3031/MURD | 07/12/2020 | 45 | KALYAN CHAKROBORTY | 10.37 | 8.24 | 79.43 | 0
186 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi , SM/09764 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at CHOA G.P. under Murshidabad Division, P.H.E.Dte. | 347/BSD | 27/08/2021 | 30 | IMAGIN | 4.16 | 4.16 | 100 | 0
187 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi , SM/09764 | Retrofitting | Relaying of UPVC pipe line from the house of Akbar Miya to the house of Yasin Sk under command area of Choa Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | 21/BSD | 20/01/2022 | 15 | SWAPAN DAS | 4.81 | 0 | 0 | 0
188 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi , SM/09764 | Retrofitting | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-B | 173/BSD | 12/04/2022 | 15 | M/S SUKESH GHOSH | 4.95 | 0 | 0 | 0
189 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi , SM/09764 | Retrofitting | Laying of 160mm dia UPVC pipeline and road restrostion work for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 163/BSD | 12/04/2022 | 15 | SUDIPTA GHOSH | 4.84 | 4.84 | 100 | 0
190 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi , SM/09764 | Retrofitting | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 171/BSD | 12/04/2022 | 15 | BARMAN ENTERPRISE | 4.83 | 4.83 | 100 | 0
191 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi , SM/09764 | Retrofitting | Laying of 90mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Choa (village code 315510) under Choa Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 172/BSD | 12/04/2022 | 15 | SOUVIK HALDER | 4.85 | 4.85 | 100 | 0
192 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Choa ( 315510 ) of Choa under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block of Murshidabad District under Murshidabad Divi , SM/09764 | Retrofitting | Relaying of UPVC pipeline from the house of Akbar Miya to the house of Yasin SK under command area of choa W/S Scheme under BSD PHE DTE. Tender no - 176 of 21-22 by AE BSD | 448-MSD/21-22 | 31/03/2022 | 0 | SWAPAN DAS | 4.81 | 0 | 0 | 0
193 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Keyadanga ( 313966 ) of Keyadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District under Murshida , SM/09849 | Retrofitting | Material Requisition To Resource Division | 540/4/MURD | 25/02/2022 | 0 | Resource Division | 3.12 | 0 | 0 | 0
194 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Keyadanga ( 313966 ) of Keyadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District under Murshida , SM/09849 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Keyadanga (Village code 313966) under Keyadanga Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723355 in the District of Murshidabad. | 804/MURD | 24/03/2022 | 30 | AZAD ENTERPRISE | 25.19 | 21.64 | 100 | 0
195 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10629 | Augmentation | Construction of approach road with earth filling at Head Work Site (T/W No. 1) under Momenpur W/s Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. | 604/ISD | 31/12/2021 | 60 | MANAB KUMAR GHOSH | 4.49 | 0 | 0 | 1
196 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10629 | Augmentation | Construction of approch road with earth filling at Head Work Site (T/W No. 1) under Momenpur W/s Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. | 40/ISD | 28/01/2022 | 60 | MANAB KUMAR GHOSH | 4.49 | 4.47 | 100 | 1
197 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10629 | Augmentation | Inter connection with Tubewell and rising main etc. at Head work sites (T/W-1) &(T/W-2) Both & Allied Works Under Momenpur Water Supply scheme under Islampur Sub - Division,Murshidabad Division P.H.E Dte. In the district of Murshidabad | 245-MSD/22-23 | 12/08/2022 | 0 | B.G. ENTERPRISE | 3.04 | 0 | 0 | 0
198 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10629 | Augmentation | Repairing & Renovation of the pump House No-1 & 2 and allied works under Momenpur water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad. | 235-MSD/22-23 | 15/08/2022 | 0 | SOUVIK HALDER | 3.6 | 0 | 0 | 0
199 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10629 | Augmentation | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Momenpur Water Supply Scheme of 2nd TW Site under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3063/MURD | 17/11/2022 | 30 | SUJIT KUMAR SAHA | 9.21 | 8.39 | 90.99 | 0
200 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10629 | Augmentation | Material Requisition To Resource Division | 1180/MURD/09 | 29/04/2023 | 0 | Resource Division | 25.98 | 0 | 0 | 0
201 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10629 | Augmentation | Formal work order Augmentation of MOMENPUR Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 3436/MURD | 23/12/2022 | 365 | M/S. ROY TRADING CO. | 408.18 | 140.76 | 34.48 | 30
202 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10629 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-II of Momenpur ground water based water supply scheme under Block- Domkal, Dist. Murshidabad under MEDB, PHE Dte. | 2319/MEDB | 11/07/2023 | 92 | SRI KRISHNA NIRMAN | 11.66 | 9.51 | 81.52 | 10
203 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10629 | Augmentation | Material Requisition To Resource Division | MURD/2481/04 | 04/09/2024 | 0 | Resource Division | 11.73 | 0 | 0 | 0
204 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MOMENPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10629 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Pump House No. I & II of Zone-II under MOMENPUR AND OTHERS PIPED WATER SUPPLY SCHEME, BLOCK- DOMKAL DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | 1142/MEDB | 14/05/2025 | 92 | DAS CONSTRUCTION | 22.95 | 0 | 0 | 15
205 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10628 | Augmentation | Material Requisition To Resource Division | 3037/B/MURD | 16/11/2022 | 0 | Resource Division | 118.48 | 0 | 0 | 0
206 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10628 | Augmentation | Material Requisition To Resource Division | 2780/B/MURD | 01/10/2022 | 0 | Resource Division | 20.63 | 0 | 0 | 0
207 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10628 | Augmentation | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAGAR PARA ZONE-I Water Supply Scheme at Head Work Site, 2nd Site site at Jalangi Block under Murshidabad Division, P.H. Engineering Dte | 2793/MURD | 04/09/2023 | 21 | A.M. ENTERPRISE | 27.45 | 0 | 0 | 0
208 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10628 | Augmentation | Allied Work of OHR & HDPE Pipe line for Augmentation of Sagarpara Part-A Ground Water Based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block in the District of Murshidabad under Murshidabad Division, P H Engg Dte. | 119/MURD | 11/01/2024 | 180 | M/S.TAPAS KUMAR CHAKRABORTY | 120.98 | 120.98 | 100 | 60
209 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10628 | Augmentation | Formal work order for Augmentation of Sagarpara Part-A Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block in the District of Murshidabad under Murshidabad Division, P H Engg Dte. | 2641/MURD | 19/09/2022 | 365 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 798.75 | 615.48 | 77.05 | 60
210 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - I Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11714 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.75 | 100 | 100
211 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - I Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11714 | Augmentation | Material Requisition To Resource Division | 1167/MURD/4 | 28/04/2023 | 0 | Resource Division | 32.69 | 0 | 0 | 0
212 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - I Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11714 | Augmentation | Formal work order for Laying of Distribution System, Rising Main, Construction of Boundary wall , Repairing & Renovation of Pump House in connection with Augmentation of Dogachhi Zone-I Water Supply Scheme in Samsherganj Block of Murshidabad District under Murshidabad Division, PHE Dte. [(i)Amount for LDS & R.Main: Rs.1,51,21,932.00 & (ii) Amount for Construction of Boundary Wall and repairing of Pump House : Rs. 22,74,098.00] | 128/MURD | 16/01/2023 | 60 | M/S. N. ISLAM AND CO. | 173.87 | 116.45 | 66.98 | 40
213 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Dogachhi Zone - I Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11714 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I , II and III OF ZONE-I under Dogachhi ground water based water supply scheme under Block_ SAMSERGANJ Dist. - Murshidabad under MEDB, PHE Dte. | 2086/MEDB | 19/06/2023 | 92 | M/S SAJAHAN CHOWDHURY | 31.47 | 26.12 | 83 | 10
214 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - I Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11714 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dogachhi Zone - I Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | 1756/MURD | 06/07/2023 | 21 | HARUN ALL RASHID & BROTHERS | 35.28 | 23.66 | 100 | 90
215 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - I Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11714 | Augmentation | Formal work order for Water Supply arrangmenet for arsenic affected habitation with SOLAR Power connection by Construction/ installation of Comiunity Purification Plant (CPP) unit including Tubewell (125 x 50 mm dia ) with Submersible pump (for Population 351-500 & Raw Water As concentration upto 0.15 ppm) at Diffarent habitations [For-8 nos Unit] in different Villages of Block of Suti-I (2 Nos),Shamsherganj (6 nos) under Murshidabad Division , P.H.E. Dte. in the District of Murshidabad. (SITE LIST Of S/L 15) | 3320/MURD | 07/10/2021 | 75 | TEKNO ENTERPRISE | 104.28 | 0 | 0 | 50
216 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - I Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11714 | Augmentation | Overhauling of 450 Cum Capacity, 20 mtr staging height (Shaft Wall) R.C.C. Elevated Reservoir, Repairing of Pump House & Boundary Wall, Laying of Distribution System to accommodate of FHTC work at Alamsahi village, Balbalpara village, Laskarpur, Dogachhi village(80%) & Mahisha Thali Village for Augmentation work of Dogachhi Zone-I Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. | 762/MURD | 02/04/2025 | 90 | H.MONDAL CONSTRUCTION | 89.23 | 0 | 0 | 0
217 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. , SM/12588 | Augmentation | Material Requisition To Resource Division | 196/BD-I/13 | 09/02/2024 | 0 | Resource Division | 8.05 | 0 | 0 | 0
218 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. , SM/12588 | Augmentation | Telia Water Supply Scheme | 348/WBSEDCL-JJM | 15/02/2024 | 0 | WBSEDCL | 4.3 | 0 | 0 | 0
219 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. , SM/12588 | Augmentation | Formal work order for Augmentation of Telia Piped water supply scheme to accommodate construction of OHR, toilet ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1446/BD-I | 17/01/2023 | 911 | MUNNA AGROTECH ENTERPRISE | 338.52 | 134.86 | 39.84 | 80
220 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. , SM/12588 | Augmentation | Allied work for construction of Cast-in-situ Pile (grade M30) (Shaft Length 25 Mtr.) to accommodate construction of OHR, pump house, boundary wall and road restoration of Augmentation of TELIA Piped water supply scheme under Jal Jeevan Mission and Bhagwangola-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | 1629/BD-I | 04/10/2024 | 177 | MUNNA AGROTECH ENTERPRISE | 50.58 | 0 | 0 | 90
221 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. , SM/12588 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for TELIA Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 267/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.63 | 2.63 | 100 | 100
222 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. , SM/12588 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Telia ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | 1360/BD-I | 21/12/2022 | 661 | PRAVAT KUMAR GHOSH | 2.41 | 0 | 0 | 100
223 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. , SM/12588 | Augmentation | Repair And Renovation Works Of R.C.C Elevated Reservoir (250 Cum) for Telia Water Supply Scheme of Bhagwangola-I block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | 1070/BD-I | 21/11/2023 | 30 | M/S S.R.K ENTERPRISE | 6.56 | 5.99 | 100 | 95
224 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. , SM/12588 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Telia Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 157/BD-I | 05/02/2024 | 30 | M/S D. PALIT & CO. | 9 | 4.23 | 36.83 | 100
225 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. , SM/12589 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Hazi Mohammadpur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | 1679/BD-I | 14/03/2023 | 30 | TAHID SK | 2.41 | 2.37 | 100 | 100
226 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. , SM/12589 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of HAZI MAHAMMADPUR, Zone-I ground water based water supply scheme under Block- Lalgola, Dist. Murshidabad under MEDB, PHE Dte. | 3782/MEDB | 03/11/2023 | 458 | ARINDAM MAJUMDAR | 10.45 | 2.37 | 22.7 | 10
227 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. , SM/12589 | Augmentation | Material Requisition To Resource Division | 201/BD-1/14 | 10/02/2024 | 0 | Resource Division | 21.36 | 0 | 0 | 0
228 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. , SM/12589 | Augmentation | Material Requisition To Resource Division | 1510/BD-I/7 | 12/09/2024 | 0 | Resource Division | 2.3 | 0 | 0 | 0
229 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. , SM/12589 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Hazi Mahammadpur Zone-I ground water supply scheme in Lalgola Block, Dist_Murshidabad under MEDB PHE Dte. | 1150/MEDB | 14/05/2025 | 92 | JAL PRAVAHIKA PVT LTD | 39.61 | 0 | 0 | 0
230 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. , SM/12589 | Augmentation | Augmentation of Hazi Mohammadpur Zone-I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1550/BD-I | 17/02/2023 | 180 | N.H ENTERPRISE | 61.96 | 55.63 | 89.79 | 95
231 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. , SM/12589 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Hazi Mahammadpur Zone-I ground water supply scheme in Lalgola Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | 948/BD-I | 18/07/2025 | 300 | M/S S. DAS & ENTERPRISE | 122.8 | 0 | 0 | 0
232 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. , SM/12589 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HAZI MOHAMMADPUR ZONE-I Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 278/BD-I | 08/03/2022 | 10 | ENVIROTECH SOLUTIONS | 2.46 | 2.46 | 100 | 1
233 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. , SM/12589 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Hazi Mohammadpur Zone - I Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 123/BD-I | 12/05/2023 | 30 | HARUN ALL RASHID & BROTHERS | 8.83 | 7.56 | 100 | 100
234 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. , SM/12589 | Augmentation | Repair And Renovation Works Of OHR (100 Cum) of Ground Water Based Supply Scheme for Hazi Mohammadpur Zone-I of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal Jeevan Mission. | 16/BD-I | 04/01/2024 | 240 | AHONA ENTERPRISE | 6.67 | 0 | 0 | 100
235 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. , SM/12590 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Hazi Mohammadpur Zone-II ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | 1443/BD-I | 16/01/2023 | 10 | MIR SABNAM BEGUM | 2.37 | 2.33 | 100 | 100
236 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. , SM/12590 | Augmentation | Material Requisition To Resource Division | 201/BD-1/15 | 10/02/2024 | 0 | Resource Division | 15.25 | 0 | 0 | 0
237 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. , SM/12590 | Augmentation | Material Requisition To Resource Division | 1510/BD-I/12 | 12/09/2024 | 0 | Resource Division | 1.31 | 0 | 0 | 0
238 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. , SM/12590 | Augmentation | Augmentation of Hazi Mohammadpur Z-II Piped water supply scheme to accommodate construction of service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1457/BD-I | 17/01/2023 | 180 | MODERN CONSTRUCTION | 45.93 | 39.48 | 85.97 | 60
239 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. , SM/12590 | Augmentation | Repair And Renovation Works Of OHR (100 Cum) of Ground Water Based Supply Scheme for Hazi Mohammadpur Zone-II of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 997/BD-I | 30/10/2023 | 600 | TANBEER CONSTRUCTION | 6.76 | 5 | 73.86 | 100
240 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. , SM/12590 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HAZI MOHAMMADPUR ZONE-II Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 279/BD-I | 08/03/2022 | 10 | ENVIROTECH SOLUTIONS | 2.46 | 2.45 | 100 | 1
241 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. , SM/12590 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of HAZI MAHAMMADPUR, Zone-II ground water based water supply scheme under Block- Lalgola, Dist. Murshidabad under MEDB, PHE Dte. | 3783/MEDB | 03/11/2023 | 668 | DAS ENTERPRISE (CHOA) | 10.29 | 8.36 | 85.89 | 15
242 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. , SM/12590 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Hazi Mohammadpur Zone - II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 83/BD-I | 03/05/2023 | 30 | HARUN ALL RASHID & BROTHERS | 8.83 | 7.49 | 100 | 100
243 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11563 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS ( SAKTIPUR PWSS Scheme, Block - Beldanga-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3266/MURD | 05/10/2021 | 60 | RADIANT | 10.43 | 4.38 | 100 | 0
244 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11563 | Augmentation | Material Requisition To Resource Division | 1278/MURD/8 | 10/05/2023 | 0 | Resource Division | 58.86 | 0 | 0 | 0
245 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11563 | Augmentation | Formal Work Order for Augmentation of Saktipur Zone-III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Beldanga-II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 2539/MURD | 02/09/2022 | 365 | BIJAY CHOWDHURY | 314.93 | 0 | 0 | 2
246 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11563 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II at Zone-III of Saktipur ground water based water supply scheme under Block- Beldanga-II, Dist. Murshidabad under MEDB, PHE Dte. | 2021/MEDB | 19/06/2023 | 92 | M/S K.P. PRAMANIK | 23.77 | 19.83 | 83.4 | 70
247 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11563 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shaktipur Zone-III Water Supply Scheme at HW Site & 2nd TW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3412/MURD | 22/12/2022 | 45 | R.K. DRILLING SERVICES | 23.56 | 20.53 | 100 | 100
248 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11563 | Augmentation | Material Requisition To Resource Division | 1811/MURD/06 | 20/06/2024 | 0 | Resource Division | 19.32 | 0 | 0 | 0
249 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11563 | Augmentation | Saktipu Zone-3 Ph-1 Application No-3004554532 | 252/WBSEDCL-JJM | 17/01/2024 | 0 | WBSEDCL | 3.44 | 0 | 0 | 0
250 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11563 | Augmentation | Saktipur Zone-3 Ph- 2 Application No- 3004554555 | 251/WBSEDCL-JJM | 17/01/2024 | 0 | WBSEDCL | 3.11 | 0 | 0 | 0
251 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11564 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (CHANDPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3277/MURD | 05/10/2021 | 60 | RADIANT | 14.82 | 4.84 | 100 | 1
252 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11564 | Augmentation | Repairing and Refilling of filter media with allied works of Iron Elemination Plant (I.E.P) at Chandpur W/S Scheme, under Berhampore Sub-Division, P.H.E.Dte. | 12/BSD | 10/01/2022 | 15 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 4.85 | 0 | 0 | 0
253 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11564 | Augmentation | Material Requisition To Resource Division | 1278/MURD/4 | 10/05/2023 | 0 | Resource Division | 92.15 | 0 | 0 | 0
254 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11564 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I & II, Zone-I under CHANDPUR ,PART-A ground water based water supply scheme under Block_ Nowda Dist. - Murshidabad under MEDB, PHE Dte. | 1912/MEDB | 16/06/2023 | 92 | EASTERN INDIA SALES & SERVICE | 22.32 | 15.74 | 70.49 | 60
255 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11564 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Chandpur Zone-I, II Water Supply Scheme at HW Site & 2nd TW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3073/MURD | 17/11/2022 | 60 | MERCURY ENGINEERING COMPANY | 31.74 | 29.25 | 100 | 100
256 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11564 | Augmentation | Material Requisition To Resource Division | 1811/MURD/03 | 20/06/2024 | 0 | Resource Division | 40.95 | 0 | 0 | 0
257 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11564 | Augmentation | CHANDPUR Z-I/A PH-II | 422/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 3.77 | 0 | 0 | 0
258 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11564 | Augmentation | SERVICE CONNECTION AT CHANDPUR Z1 PH1 ID 304265806 | 111/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 4.94 | 0 | 0 | 0
259 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11564 | Augmentation | Repairing of R.C.C. elevated reservoir (375 Cum capacity) of staging hight 18.5 Mtr. At Chandpur Water Supply under Berhampore Sub Division, P.H.E. Dte. in the district of Murshidabad. | 554/MURD | 28/02/2022 | 45 | ULTRA CONSTRUCTION. | 11.25 | 4.77 | 42.41 | 0
260 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11564 | Augmentation | Formal Work Order for :Augmentation of CHANDPUR Zone-I (Part -A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 2083/MURD | 27/07/2022 | 991 | TINA ROY | 355.12 | 151.44 | 48.25 | 85
261 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11564 | Augmentation | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagaipur PWSS TW-I,II, Chandpur Zone-I PWSS T.W.-II, Edrakpur PWSS T.W-II, Surangapur Zone-IA TW-I of Nowda Block under Berhampore Sub-Division,Murshidabad Division, P.H.Engineering Dte. | 663/MURD | 19/03/2025 | 65 | SARKAR WATER SUPPLY AGENCY | 58.87 | 0 | 0 | 0
262 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11564 | Augmentation | Construction of Pump House with chlorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) of 4th Tubewell ,Air Compressor Room with chlorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) , 210 mtr Boundary wall , 86 mtr Drain and Renovation of IEP (Rapid Gravity Filter) at Chandpur W/S Scheme under Berhampore sub-Division , P.H.E. Dte. | 966/MURD | 30/04/2025 | 60 | MODERN CONSTRUCTION | 63.48 | 0 | 0 | 0
263 | MURSHIDABAD | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | Material Requisition To Resource Division | 61/BD-1/36 | 27/04/2023 | 0 | Resource Division | 8607.44 | 0 | 0 | 0
264 | MURSHIDABAD | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | Bulk power connection charge for Nabagram WTP 1047KVA Application No- R000012128 Con Od-950085502 | 199/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 86.39 | 0 | 0 | 0
265 | MURSHIDABAD | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | HYDRAGRAPHIC SURVEY CHARGE FOR SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART BERHAMPORE AND MURSHIDABAD JIAGANJ BLOCKS OF DISTRICT OF MURSHIDABAD | BP-2023-24-127 | 15/09/2023 | 0 | SYAMA PRASAD MOOKERJEE PORT KOLKATA | 55.55 | 0 | 0 | 0
266 | MURSHIDABAD | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | Bulk power connection charge for Nabagram Intake 276KVA Application No-R000012129 Con Id-950086101 | 198/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 28.06 | 0 | 0 | 0
267 | MURSHIDABAD | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | Consultancy charges along with the work order in respect of the project title "EIA and EMP for proposed Intake Jetty of Surface water based piped water supply scheme for entire Nabagram Block and Part of Berhampore & Murshidabad Jiaganj Blocks of District Murshidabad (IPBN) | BP-2023-24-205 | 13/12/2023 | 0 | IIT CONSULTATIVE PRATICE | 5.52 | 0 | 0 | 0
268 | MURSHIDABAD | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | Supply, delivery, installation & commissioning of Substation Equipments and other Accessories at Raw Water Pumping Station under Nabagram Surface Water Based W/S Scheme, Dist. Murshidabad. | 3861/MEDB | 07/11/2023 | 182 | ALOK ENTERPRISE | 258.96 | 141.37 | 54.59 | 10
269 | MURSHIDABAD | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | Material Requisition To Resource Division | 360/BD-1 | 05/03/2024 | 0 | Resource Division | 123.2 | 0 | 0 | 0
270 | MURSHIDABAD | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION NLSF-LCAE AT KM 170/27-29 & 170/28-30 IN KATWA-AZIMGANJ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. | BP-2024-25-114 | 30/07/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 7.19 | 0 | 0 | 0
271 | MURSHIDABAD | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | Way leave permission for using the Railway land for laying water supply pipeline of underground Railway Track crossing of 900 mm dia M.S Casing Pipe through 600 mm dia M.S Carrier pipe by Jack Pushing/HDD method between station Dahapara -Lalbagaat KM, 173/21-22-173/23-24 in Katwa-Azimalong section of Howrah Division E. Rly. under Berhampore Division-I (for Raw Water) | BP-2024-25-65 | 20/06/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 5.32 | 0 | 0 | 0
272 | MURSHIDABAD | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | Third Installment 20% after submission of EIA report in respect of the project title EIA and EMP for Proposed Intake Jetty of Surface water based piped water supply scheme for entire Nabagram Block and Part of Berhampore & Murshidabad Jiaganj Blocks of District Murshidabad | BP-2023-24-291 | 01/03/2024 | 0 | IIT CONSULTATIVE PRATICE | 1.84 | 0 | 0 | 0
273 | MURSHIDABAD | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION JIBANTI HALT-KHAGRAGHAT AT KM 162/32-34 & 162/33-35 IN KWAE-AZ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. (R.A-2) | BP-2024-25-135 | 21/08/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 0 | 0 | 0 | 0
274 | MURSHIDABAD | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | Second Installment 20% after submission of EIA report in respect of the project title EIA and EMP for Proposed Intake Jetty of Surface water based piped water supply scheme for entire Nabagram Block and Part of Berhampore & Murshidabad Jiaganj Blocks of District Murshidabad | BP-2023-24-290 | 01/03/2024 | 0 | IIT CONSULTATIVE PRATICE | 1.84 | 0 | 0 | 0
275 | MURSHIDABAD | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | Way leave permission for using the Railway land for laying water supply pipeline of underground Railway Track crossing of 900 mm dia M.S Casing Pipe through 600 mm dia M.S Carrier pipe by Jack Pushing/HDD method between station Dahapara -Lalbagaat KM, 173/21-22-173/23-24 in Katwa-Azimalong section of Howrah Division E. Rly. under Berhampore Division-I | BP-2024-25-62 | 19/06/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 5.32 | 0 | 0 | 0
276 | MURSHIDABAD | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | Way leave permission for using the Railway land for laying water supply pipeline of underground Railway Track crossing of 600 mm dia M.S Casing Pipe through 250 mm dia M.S Carrier pipe by Jack Pushing/HDD method between station NLSF-LCAE at KM, 166-33/34-166/35/36 in Katwa-Azimalong section of Howrah Division E. Rly. under Berhampore Division-I | BP-2024-25-63 | 19/06/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 5.94 | 0 | 0 | 0
277 | MURSHIDABAD | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION JIBANTI HALT-KHAGRAGHAT AT KM 160/13-15 IN KATWA-AZIMGANJ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. | BP-2024-25-116 | 30/07/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 6.43 | 0 | 0 | 0
278 | MURSHIDABAD | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | WAY LEAVE PERMISSION FOR USING THE RAILWAY LAND FOR LAYING WATER SUPPLY PIPE LINE OF UNDER GROUND RAILWAY TRACK CROSSING OF 600MM DIA M.S. CASING PIPE THROUGH 250 MM DIA M.S. CARRIER PIPE BY JACK PUSHING METHOD BETWEEN STATION JIBANTI HALT-KHAGRAGHAT AT KM 162/32-34 & 162/33-35 IN KWAE-AZ SECTION OF HOWRAH DIVISION, EASTERN RAILWAY. | BP-2024-25-115 | 30/07/2024 | 0 | EASTERN RAILWAY HOWRAH DIVISION | 6.32 | 0 | 0 | 0
279 | MURSHIDABAD | Berhampore Mechanical | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | Supply, delivery, installation & commissioning of Substation Equipments and other Accessories at Water Treatment Plant under Nabagram Surface Water Based W/S Scheme under MEDB, P.H.E. Dte., Dist. Murshidabad. | 3862/MEDB | 07/11/2023 | 542 | ORIENTAL ENGINEERING CO. | 391.5 | 0 | 0 | 5
280 | MURSHIDABAD | Berhampore Division I | SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR ENTIRE NABAGRAM BLOCK AND PART OF BERHAMPORE & MURSHIDABAD-JIAGANJ BLOCKS OF DISTRICT MURSHIDABAD , SM/12360 | New | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Monthly hire basis for official use for the Office of the Assistant Engineer-I,BD-I,PHE Dte. [Period for 03.07.2024 to 30.06.2025]. | 1047/BD-I | 02/07/2024 | 365 | AMAN CONSTRUCTION | 1.81 | 4.3 | 237.12 | 45
281 | MURSHIDABAD | Murshidabad Division | ANDULIA AND ADJOININNG MOUJAS PWSS , SM/13723 | New | Material Requisition To Resource Division | 1004/MURD/12 | 17/04/2023 | 0 | Resource Division | 24.19 | 0 | 0 | 0
282 | MURSHIDABAD | Berhampore Mechanical | ANDULIA AND ADJOININNG MOUJAS PWSS , SM/13723 | New | New service connection charge for Andulia, P/H No.-I. | 111/WBSEDCL-JJM | 29/08/2023 | 0 | WBSEDCL | 5.47 | 0 | 0 | 0
283 | MURSHIDABAD | Berhampore Mechanical | ANDULIA AND ADJOININNG MOUJAS PWSS , SM/13723 | New | New service connection charge for Andulia, P/H No.-II. | 110/WBSEDCL-JJM | 29/08/2023 | 0 | WBSEDCL | 8.54 | 0 | 0 | 0
284 | MURSHIDABAD | Berhampore Mechanical | ANDULIA AND ADJOININNG MOUJAS PWSS , SM/13723 | New | Electric Service Connection at ANDULIA PWSS I, Application NO.3004400021, ID 304117200 | 197/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 5.47 | 0 | 0 | 0
285 | MURSHIDABAD | Berhampore Mechanical | ANDULIA AND ADJOININNG MOUJAS PWSS , SM/13723 | New | SERVICE CONNECTION CHARGES AT ANDULIA PH2 ID304117291 | 208/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 8.54 | 0 | 0 | 0
286 | MURSHIDABAD | Murshidabad Division | ANDULIA AND ADJOININNG MOUJAS PWSS , SM/13723 | New | RESTORATION OF DAMAGED ROAD DUE TO LAYING OF PHE PIPELINE OF MAHADIA-DURGAPUR ROAD FROM 0.30 KM TO 2.10 KM UNDER MSD HIGHWAY DIVISION.-II DURING THE YEAR OF 2024-25 | 393-MSD/2024-25 | 19/09/2024 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 13.77 | 0 | 0 | 0
287 | MURSHIDABAD | Berhampore Mechanical | ANDULIA AND ADJOININNG MOUJAS PWSS , SM/13723 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under ANDULIA ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | 1884/MEDB | 16/06/2023 | 92 | HARA PROSAD DAS | 25.86 | 0 | 0 | 30
288 | MURSHIDABAD | Berhampore Mechanical | BRAHMANDIHI AND ADJOINING MOUJAS PWSS , SM/13729 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under BRAHMANDIHI ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | 1885/MEDB | 16/06/2023 | 92 | M/S S. R. ENTERPRISE | 23.47 | 0 | 0 | 0
289 | MURSHIDABAD | Murshidabad Division | BRAHMANDIHI AND ADJOINING MOUJAS PWSS , SM/13729 | New | Material Requisition To Resource Division | 1043/MURD/14 | 17/04/2023 | 0 | Resource Division | 34.54 | 0 | 0 | 0
290 | MURSHIDABAD | Berhampore Mechanical | BRAHMANDIHI AND ADJOINING MOUJAS PWSS , SM/13729 | New | Quotation for Bamundi PH No-1 | 329/WBSEDCL-JJM | 06/02/2024 | 0 | WBSEDCL | 4.36 | 0 | 0 | 0
291 | MURSHIDABAD | Murshidabad Division | JASOHARI PIPE WATER SUPPLY SCHEME. , SM/13728 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JASOHARI PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3400/MURD | 22/12/2022 | 45 | M/S B.R. SUPPLIERS | 16.8 | 0 | 0 | 0
292 | MURSHIDABAD | Murshidabad Division | JASOHARI PIPE WATER SUPPLY SCHEME. , SM/13728 | New | Formal Work Order For Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of JASOHARI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362341S000) [ (i)Amount for LDS , R. Main & FHTC: Rs. 1,91,63,541.00 & (ii) Amount for OHR,Boundwary Wall & Pump House : Rs. 1,56,48,969.00] | 481/MURD | 20/02/2023 | 365 | M/S. NANDY ENTERPRISE | 347.6 | 0 | 0 | 0
293 | MURSHIDABAD | Murshidabad Division | JASOHARI PIPE WATER SUPPLY SCHEME. , SM/13728 | New | Material Requisition To Resource Division | 1004/MURD/8 | 11/04/2023 | 0 | Resource Division | 24.37 | 0 | 0 | 0
294 | MURSHIDABAD | Berhampore Mechanical | JASOHARI PIPE WATER SUPPLY SCHEME. , SM/13728 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under JASOHARI ground water based water supply scheme under Block_ KANDI Dist. - Murshidabad under MEDB, PHE Dte. | 2081/MEDB | 19/06/2023 | 92 | SARKAR CONSTRUCTION | 23.39 | 19.23 | 82.23 | 60
295 | MURSHIDABAD | Murshidabad Division | GARULIA AND IT'S ADJOINING MOUJAS PWSS , SM/13924 | New | Material Requisition To Resource Division | 1067/MURD/2 | 18/04/2023 | 0 | Resource Division | 27.8 | 0 | 0 | 0
296 | MURSHIDABAD | Murshidabad Division | GARULIA AND IT'S ADJOINING MOUJAS PWSS , SM/13924 | New | Material Requisition To Resource Division | 79/MURD/04 | 09/01/2024 | 0 | Resource Division | 18.58 | 0 | 0 | 0
297 | MURSHIDABAD | Berhampore Mechanical | GARULIA AND IT'S ADJOINING MOUJAS PWSS , SM/13924 | New | NEW SERVICE CONNECTION AT PH1 GURULIA ID 304239442 | 310/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 4.23 | 0 | 0 | 0
298 | MURSHIDABAD | Berhampore Mechanical | GARULIA AND IT'S ADJOINING MOUJAS PWSS , SM/13924 | New | NEW SERVICE CONNECTION AT PH2 GURULIA ID 304239443 | 309/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 4.29 | 0 | 0 | 0
299 | MURSHIDABAD | Berhampore Mechanical | GARULIA AND IT'S ADJOINING MOUJAS PWSS , SM/13924 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under GARULIA ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | 2013/MEDB | 19/06/2023 | 926 | JOGMAYA ENGINEERING | 24.48 | 19.92 | 81.35 | 65
300 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13927 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I & II ,ZONE-II under GHORAPAKHIA GANGIN ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | 1910/MEDB | 16/06/2023 | 92 | ARINDAM MAJUMDAR | 22.81 | 0 | 0 | 0
301 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13927 | Augmentation | Re-Laying of U.P.V.C pipe of 90 mm dia on damaged portion in between N.P 05 to 06 (Prymary school to kriti mondal's House) for smooth water supply arrangement in Ghorapakhiagangin Zone-I W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | 14/JSD | 13/01/2021 | 30 | DEBOJYOTI CONSTRUCTION | 1.64 | 1.56 | 100 | 1
302 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13927 | Augmentation | Re-Laying of U.P.V.C pipe of 90 mm dia on damaged portion in between N.P 04-05-30-07 to 06 (From Dalim Sk house to Sanaul Sk house) for smooth water supply arrangement in Ghorapakhiagangin Zone-I W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | 13/JSD | 13/01/2021 | 30 | LAXMI CONSTRUCTION | 2.88 | 2.58 | 100 | 1
303 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13927 | Augmentation | Material Requisition To Resource Division | 1210/MURD/13 | 02/05/2023 | 0 | Resource Division | 58.4 | 0 | 0 | 0
304 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13927 | Augmentation | Sinking of 1NO. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Ghorapakhiagangin Zone-I Water Supply Scheme at Suti-I Block of Jangipur Division under Murshidabad Division, P.H.Engineering Dte. | 2290/MURD | 09/08/2024 | 15 | JOY GURU ENTERPRISE | 11.67 | 0 | 0 | 95
305 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13927 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Ahiran Halt Station to Jangipur Road Station (TP NO 217/5 & 217/6) at Ghorapakhia Gangin mouza & Connecting with existing 110 mm dia uPVC distribution main line of Ghorapakhia Gangin Zone- II ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | 2484/MURD | 16/08/2021 | 60 | M/S. SINHA & SONS | 21.58 | 21.58 | 100 | 0
306 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13927 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 0 | 21
307 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13927 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for GHORAPAKHIA GANGIN Zone -II Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division , PHE Dte. | 965/MURD | 30/04/2025 | 60 | M/S. UNIQUE BUILDERS | 23.01 | 0 | 0 | 0
308 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13927 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.51 | 100 | 100
309 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13927 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHORA PAKHIA GANGIN ZONE - II Water Supply Scheme at Head Work Site, 2nd Site site at Suti-I Block under Murshidabad Division, P.H. Engineering Dte. | 1756/MURD | 13/06/2024 | 433 | R.K. DRILLING SERVICES | 11.79 | 0 | 0 | 90
310 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand , SM/08191 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Dakshinkhanda Habitation under Dakshinkhanda Village Code-315710 (JL NO-99) Dakshinkhanda Water Supply Scheme (Ground Water Based) under Bharatpur-II Block in the District of Murshidabad. | 2392/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 9.76 | 8.09 | 82.93 | 0
311 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand , SM/08191 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SIMULIA G.P. under Murshidabad Division, P.H.E.Dte. | 237/KSD | 27/08/2021 | 60 | IMAGIN COMMUNICATION | 4.17 | 0 | 0 | 0
312 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand , SM/08191 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of Village of Harinya, Datta Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, DakshinKhanda (Nos FHTC-4251) (Village code-315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) under DAKSHINKHANDA Ground Water Based Water Supply Scheme and Kagram ( Nos FHTC-3297) (Village code-315714) under Kagram Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block, of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID 0007338400 & 0007773828) | 141/MURD | 19/01/2022 | 180 | M/S. S. DAS AND ENTERPRISE | 383.18 | 56.55 | 25.45 | 1
313 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand , SM/08191 | Retrofitting | Material Requisition To Resource Division | 3632/D/MURD | 23/11/2021 | 0 | Resource Division | 23.38 | 0 | 0 | 0
314 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harinya, Dayya Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, Dakshin Khanda (315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) of Dakshinkhand , SM/08191 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Dakshinkhanda Habitation under Dakshinkhanda Village Code-315710 (JL NO-99) Dakshinkhanda Water Supply Scheme (Ground Water Based) under Bharatpur-II Block in the District of Murshidabad. | 2392/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 9.76 | 0.12 | 100 | 1
315 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . , SM/14050 | Augmentation | Material Requisition To Resource Division | 61/BD-1/1 | 27/04/2023 | 0 | Resource Division | 13.4 | 0 | 0 | 0
316 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . , SM/14050 | Augmentation | Repair And Renovation Works Of OHR (35 Cum) of Ground Water Based Supply Scheme for Ramchandrapur of Raninagar-II block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | 1069/BD-I | 21/11/2023 | 30 | MADAN MOHAN SASMAL | 5.13 | 4.68 | 91.3 | 70
317 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . , SM/14050 | Augmentation | Augmentation of Ramchandrapur Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1651/BD-I | 13/03/2023 | 180 | MS BAPPA ENTERPRISE | 49.53 | 28.79 | 58.11 | 71
318 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . , SM/14050 | Augmentation | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at RAMCHANDRAPUR Water Supply Scheme (1st TW site) within RANINAGAR-II Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 280/BD-I | 12/02/2025 | 15 | HAFIZUL SEIKH | 11.56 | 0 | 0 | 0
319 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . , SM/14050 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMCHANDRAPUR Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1391/BD-I | 27/12/2022 | 10 | M/S SOBHA & CO | 2.46 | 2.43 | 100 | 100
320 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . , SM/14050 | Augmentation | Renovation for Existing AIRP of (Capacity 6.57 Cum/hr.) at Ramchandrapur Water Supply Scheme under Jal Jeevan Mission of Berhampore Division-I, PHE Engineering Dte. | 411/BD-I | 13/03/2024 | 30 | SUMAN ENTERPRISE AND SUMAN AQUA | 9.15 | 9.12 | 100 | 80
321 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KODLA BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14832 | Augmentation | Construction of Boundary wall at Head works site for Part-C of Kodla water supply Scheme under Berhampore Sub Division P.H.E Dte. | 3271/MURD | 24/12/2020 | 30 | CHATTERJEE ENTERPRISE | 4.58 | 4.24 | 100 | 0
322 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KODLA BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14832 | Augmentation | Formal Work Order for Construction of 400 CUM capacity 20.00 mtr staging height RCC elevated Over Head Reservoir on raft foundation as per drawing & design reference-PC-I/OHR/11/2012) including supply, delivery and errecting inlet and overflow pipe connection etc all complete at head work site of KODLA water supply scheme of Berhampore Sub-Division under Murshidabad Division Murshidabad District P.H.Engg Dept. | 3114/MURD | 09/12/2020 | 270 | M/S KAMRULA CONSTRUCTION CO. | 98.16 | 63.36 | 100 | 5
323 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KODLA BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14832 | Augmentation | KODLA PH-2 | 401/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 6.91 | 0 | 0 | 0
324 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KODLA BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14832 | Augmentation | Water Supply arrangement for arsenic affected habitation with SOLAR Power connection at different block under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad. (PART-F) | 506/MURD | 02/02/2021 | 60 | PAL TROCKNER (P) LTD. | 37.91 | 0 | 0 | 81
325 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KODLA BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14832 | Augmentation | Water Supply arrangement for arsenic affected habitation with SOLAR Power connection at different block under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad. (PART-J) | 511/MURD | 02/02/2021 | 60 | PAL TROCKNER (P) LTD. | 37.91 | 0 | 0 | 100
326 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KODLA BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14832 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 6.03 | 200 | 1
327 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KODLA BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14832 | Augmentation | Formal Work Order for Laying Distribution System For Augmentation of Kodla (Part-A) PWSS of Beldanga-II Block under Murshidabad Division ,PHE.Dte | 730/MURD | 15/03/2023 | 1086 | SUDIPA SINGHA ROY | 100.66 | 10.02 | 9.96 | 50
328 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KODLA BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14832 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0 | 0
329 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KODLA BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14832 | Augmentation | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 0 | 75
330 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. , SM/14070 | Augmentation | Material Requisition To Resource Division | 201/BD-1/13 | 10/02/2024 | 0 | Resource Division | 60.04 | 0 | 0 | 0
331 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. , SM/14070 | Augmentation | Material Requisition To Resource Division | 1510/BD-I/6 | 12/09/2024 | 0 | Resource Division | 4.99 | 0 | 0 | 0
332 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. , SM/14070 | Augmentation | Augmentation of Nasipur Zone_I Piped water supply scheme to accommodate construction of Pump House and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE Dte. | 1625/BD-I | 02/03/2023 | 180 | DHIMAN SARKAR | 176.03 | 155.11 | 88.11 | 26
333 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. , SM/14070 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NASIPUR ZONE-I PWSS (TW - III Site) within Lalgola Block under JAL JEEVAN MISSION in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (01 No TW) | 758/BD-I | 22/05/2025 | 15 | AZAD ENTERPRISE | 9.01 | 0 | 0 | 0
334 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. , SM/14070 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Nasipur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | 1368/BD-I | 21/12/2022 | 30 | CHATTERJEE ENTERPRISE | 2.46 | 2.42 | 100 | 100
335 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. , SM/14070 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for NASIPUR ZONE-I Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1374/BD-I | 21/12/2022 | 10 | ENVIROTECH SOLUTIONS | 2.94 | 2.62 | 100 | 1
336 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. , SM/14070 | Augmentation | Repair And Renovation Works Of OHR (550 Cum) Ground water supply scheme for Nashipur Zone-I of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 988/BD-I | 30/10/2023 | 30 | SELIM SARKAR | 9.8 | 6.81 | 100 | 90
337 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-I. , SM/14070 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NASIPUR ZONE - I Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 74/BD-I | 17/01/2025 | 44 | AJOY GHOSH | 9.01 | 0 | 0 | 100
338 | MURSHIDABAD | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I , SM/15233 | Augmentation | Material Requisition To Resource Division | 201/BD-1/25 | 10/02/2024 | 0 | Resource Division | 139.52 | 0 | 0 | 0
339 | MURSHIDABAD | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I , SM/15233 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Bajipur Madhupur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | 1671/BD-I | 14/03/2023 | 30 | JAMUNA CONSTRUCTION | 2.85 | 2.82 | 98.84 | 100
340 | MURSHIDABAD | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I , SM/15233 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd TW Site of BAJUPUR MADHUPUR ZONE-I PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 442/BD-I | 20/03/2025 | 60 | ANKITA ENTERPRISE-GOPEJAN (NATHPARA) | 19 | 0 | 0 | 0
341 | MURSHIDABAD | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I , SM/15233 | Augmentation | BAJUPUR MADHUPUR ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 452/BD-I | 15/03/2024 | 747 | ANKITA ENTERPRISE-GOPEJAN (NATHPARA) | 21.46 | 9.7 | 45.2 | 30
342 | MURSHIDABAD | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I , SM/15233 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bajupur Madhupur Zone - I Water Supply Scheme (TW - I & II Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | 320/BD-I | 24/02/2025 | 15 | MERCURY ENGINEERING COMPANY | 18 | 0 | 0 | 0
343 | MURSHIDABAD | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I , SM/15233 | Augmentation | Construction of Pump House Cum Chlorine Room at Head Work Site of BAJUPUR MADHUPUR ZONE -I PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 594/BD-I | 22/04/2025 | 45 | JAKIR HOSSAIN PRAMANIK | 8.66 | 0 | 0 | 1
344 | MURSHIDABAD | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I , SM/15233 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BAJIPUR MADHUPUR ZONE-I Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1689/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 3.14 | 3.17 | 100 | 1
345 | MURSHIDABAD | Berhampore Division I | Augmentation of ground water based pipe water supply scheme for Bajupur Madhupur Zone-I , SM/15233 | Augmentation | Repair And Renovation Works Of OHR (500 Cum) forBajupurMadhupur Zone-I water supply scheme of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | 1067/BD-I | 21/11/2023 | 30 | KAUSHIK MAJUMDAR | 9.74 | 7.19 | 100 | 80
346 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . , SM/15234 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of GAUKHANA ground water based water supply scheme under Block- LALGOLA, Dist. Murshidabad under MEDB, PHE Dte. | 3785/MEDB | 03/11/2023 | 92 | DAS ENTERPRISE (CHOA) | 11.25 | 9.32 | 82.84 | 10
347 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . , SM/15234 | Augmentation | Material Requisition To Resource Division | 201/BD-1/12 | 10/02/2024 | 0 | Resource Division | 36.3 | 0 | 0 | 0
348 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . , SM/15234 | Augmentation | Material Requisition To Resource Division | 1510/BD-I/5 | 12/09/2024 | 0 | Resource Division | 3.44 | 0 | 0 | 0
349 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . , SM/15234 | Augmentation | NEW CONNECTION AT GAUKHANA PH-I | 170/WBSEDCL-JJM | 31/07/2024 | 0 | WBSEDCL | 6.98 | 0 | 0 | 0
350 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . , SM/15234 | Augmentation | Augmentation of Gaukhana Piped water supply scheme to accommodate construction of OHR ,Arsenic cum Iron Removal Plant( AIRP) and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 680/BD-I | 10/08/2023 | 875 | ARABINDA GHOSH | 317.21 | 0 | 0 | 50
351 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . , SM/15234 | Augmentation | GAUKHANA PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 328/BD-I | 29/02/2024 | 542 | SANTA TRADING | 22.94 | 0 | 0 | 60
352 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . , SM/15234 | Augmentation | Improvement of existing AIRP(Gober Danga Model) (Capacity-21.0 Cum/ Hr.) of GAUKHANA Water supply Scheme under Jal Jeevan Mission within Lalgola block under Berhampore Division-I, P.H.E Dte. In the district of Murshidabad. | 721/BD-I | 14/05/2025 | 30 | MS GUNGUN CONSTRUCTION | 20.25 | 0 | 0 | 0
353 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . , SM/15234 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for GOUKHANA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1681/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.46 | 2.48 | 100 | 1
354 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . , SM/15234 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Gaukhana ground Water Supply Scheme under Berhampore Division-I, PHE Dte. (Block-Lalgola) | 60/BD-I | 25/04/2023 | 30 | SAIF TRADERS | 2.25 | 2.21 | 100 | 100
355 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . , SM/15234 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gaukhana Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 125/BD-I | 12/05/2023 | 30 | HARUN ALL RASHID & BROTHERS | 8.92 | 7.93 | 100 | 100
356 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gaukhana . , SM/15234 | Augmentation | Repair And Renovation Works Of OHR (90.8 Cum) of Ground Water Based Supply Scheme for Gaukhana of Lalgola block under Berhampore Division-I PHEDte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 987/BD-I | 30/10/2023 | 30 | KAKALI ENTERPRISE | 6.11 | 6.05 | 100 | 100
357 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Dakshin Sekhhalipur Ground water Based PWSS, Block-Raghunathganj-II , Dist- Murshidabad under MEDB, PHE Dte. , SM/15292 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Dakshin Sekhhalipur Ground water Based PWSS, Block-Raghunathganj-II , Dist- Murshidabad under MEDB, PHE Dte. | 3752/MEDB | 03/11/2023 | 92 | ASSOCIATED ELECTRICAL CO. | 6.39 | 0 | 0 | 0
358 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. , SM/14735 | Augmentation | Augmentation of Moktarpur Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 871/BD-I | 12/09/2023 | 310 | MS RUBIET HOSSAIN | 333.41 | 0 | 0 | 0
359 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. , SM/14735 | Augmentation | Material Requisition To Resource Division | 61/BD-1/7 | 27/04/2023 | 0 | Resource Division | 37.29 | 0 | 0 | 0
360 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. , SM/14735 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Moktarpur ground water based water supply scheme under Block_ Nawda Dist. - Murshidabad under MEDB, PHE Dte. | 2093/MEDB | 19/06/2023 | 92 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 23.45 | 0 | 0 | 20
361 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. , SM/14735 | Augmentation | load enhancement moktarpur pwss |  | 05/03/2024 | 0 | WBSEDCL | 1.03 | 0 | 0 | 0
362 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. , SM/14735 | Augmentation | AT MOKTARPUR PH 2 ID 304244960 | 375/WBSEDCL-JJM | 21/02/2024 | 0 | WBSEDCL | 3.92 | 0 | 0 | 0
363 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. , SM/14735 | Augmentation | LOAD ENHANCEMENT OF MOKTARPUR PWSS ID 312350581 | 460/WBSEDCL-JJM | 18/03/2024 | 0 | WBSEDCL | 1.03 | 0 | 0 | 0
364 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. , SM/14735 | Augmentation | AT MOKTARPUR PH 1 ID 304244961 | 374/WBSEDCL-JJM | 21/02/2024 | 0 | WBSEDCL | 12.51 | 0 | 0 | 0
365 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. , SM/14735 | Augmentation | Construction of Service Road for approach and Pump House at Augnentation of MUKTARPUR PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | 1306/BD-I | 07/08/2024 | 60 | M/S BHAGIRATHI ENTERPRISE | 7.65 | 0 | 0 | 0
366 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. , SM/14735 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of MUKTARPUR ZONE-II PWSS under Jal Jeevan Mission within Raninagar -I Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 842/BD-I | 23/06/2025 | 60 | GOUTAM KUMAR CHAUDHURI | 19 | 0 | 0 | 0
367 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. , SM/14735 | Augmentation | MOKTARPUR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 824/BD-I | 18/06/2025 | 45 | BURIMAA CONSTRUCTION | 23.3 | 0 | 0 | 0
368 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. , SM/14735 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MOKTARPUR Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1758/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.67 | 2.67 | 100 | 100
369 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Moktarpur. , SM/14735 | Augmentation | Improvement of OHR (350 Cum) of Ground Water Based Supply Scheme for Augmentation of Muktarpur of Raninagar-I block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | 889/BD-I | 06/06/2024 | 180 | NOBEL CONSTRUCTION | 9.28 | 6.68 | 100 | 90
370 | MURSHIDABAD | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS , SM/14496 | New | Material Requisition To Resource Division | 1210/MURD/33 | 02/05/2023 | 0 | Resource Division | 24.92 | 0 | 0 | 0
371 | MURSHIDABAD | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS , SM/14496 | New | Retrofitting Functional Household Tap Connection (FHTC) under Jal Jeevan Mission for command area of Uncovered BATI Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | 120/MURD | 13/01/2023 | 30 | DEBASIS BOSE | 71.38 | 0 | 0 | 0
372 | MURSHIDABAD | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS , SM/14496 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bati & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K a n d i Block under Murshidabad Division, P.H. Engineering Dte. | 1216/MURD | 03/05/2023 | 30 | MAMATA USHA ENTERPRISE | 21.38 | 11.25 | 52.62 | 50
373 | MURSHIDABAD | Berhampore Mechanical | BATI AND IT'S ADJOINING MOUJAS PWSS , SM/14496 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under BATI ground water based water supply scheme under Block_ KANDI Dist. - Murshidabad under MEDB, PHE Dte. | 4292/MEDB | 29/12/2023 | 91 | DAS ENTERPRISE ( MANGO LANE) | 22.1 | 0 | 0 | 0
374 | MURSHIDABAD | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS , SM/14496 | New | Material Requisition To Resource Division | MURD/439/12 | 08/02/2024 | 0 | Resource Division | 8.91 | 0 | 0 | 0
375 | MURSHIDABAD | Berhampore Mechanical | BATI AND IT'S ADJOINING MOUJAS PWSS , SM/14496 | New | new service connection at BATI PH1 ID304200864,Application no.3004504556 | 219/WBSEDCL-JJM | 05/01/2024 | 0 | WBSEDCL | 8.77 | 0 | 0 | 0
376 | MURSHIDABAD | Berhampore Mechanical | BATI AND IT'S ADJOINING MOUJAS PWSS , SM/14496 | New | NEW SERVICE CONNECTION AT BATI PH 2 CID 304252900 |  | 16/02/2024 | 0 | WBSEDCL | 3.01 | 0 | 0 | 0
377 | MURSHIDABAD | Berhampore Mechanical | BATI AND IT'S ADJOINING MOUJAS PWSS , SM/14496 | New | AT BATI PH 2 ID 304252900 | 376/WBSEDCL-JJM | 21/02/2024 | 0 | WBSEDCL | 3.01 | 0 | 0 | 0
378 | MURSHIDABAD | Berhampore Mechanical | BATI AND IT'S ADJOINING MOUJAS PWSS , SM/14496 | New | SHIFTING OF A PART OF EXISTING HTOH LINE AT BATI PWSS ID860318411 |  | 25/11/2024 | 0 | WBSEDCL | 0.57 | 0 | 0 | 0
379 | MURSHIDABAD | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS , SM/14496 | New | Formal Work Order for construction of 200 Cum OHR,,Laying Distribution System (PART-A),Rising Main Connection, Boundwary Wall, for Uncovered of BATI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division , PHE.Dte. [(i)Amount for LDS , R.Main: Rs.1,64,06,836.00 & (ii) Amount for OHR & B. Wall : Rs. 1,25,46,499.00] | 484/MURD | 20/02/2023 | 1046 | AJAY MONDAL | 289.48 | 74.39 | 25.7 | 30
380 | MURSHIDABAD | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS , SM/14496 | New | Laying Distribution System (PART-B), Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) & Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) for Uncoveded BATI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte.for [ (i) Amount for Laying Distribution System: Rs.72,79,775.00 & (ii) Amount for Pump House: Rs. 10,55,058.00] | 121/MURD | 13/01/2023 | 838 | M/S. GOURI ENTERPRISE | 84.16 | 72.71 | 86.4 | 50
381 | MURSHIDABAD | Murshidabad Division | BATI AND IT'S ADJOINING MOUJAS PWSS , SM/14496 | New | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Kandi Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(89 Nos.) | 2635/MURD | 23/09/2024 | 281 | SABSAMAY | 9.85 | 0 | 0 | 80
382 | MURSHIDABAD | Berhampore Mechanical | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. , SM/15047 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under MAHENDRAPUR ground water based water supply scheme under Block_ Suti-II Dist. - Murshidabad under MEDB, PHE Dte. | 3811/MEDB | 03/11/2023 | 92 | B. T. PROJECTS PVT. LTD. | 34.2 | 0 | 0 | 0
383 | MURSHIDABAD | Murshidabad Division | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. , SM/15047 | New | Material Requisition To Resource Division | 1230/MURD/33 | 04/05/2023 | 0 | Resource Division | 27.6 | 0 | 0 | 0
384 | MURSHIDABAD | Berhampore Mechanical | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. , SM/15047 | New | NEW CONNECTION AT MAHENDARPUR PH-I | 187/WBSEDCL-JJM | 09/08/2024 | 0 | WBSEDCL | 3.83 | 0 | 0 | 0
385 | MURSHIDABAD | Berhampore Mechanical | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. , SM/15047 | New | NEW CONNECTION AT MAHENDRAPUR PH-II |  | 13/12/2024 | 0 | WBSEDCL | 5.13 | 0 | 0 | 0
386 | MURSHIDABAD | Berhampore Mechanical | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. , SM/15047 | New | NEW CONNECTION AT MAHENDARPUR PH-1 |  | 02/08/2024 | 0 | WBSEDCL | 3.83 | 0 | 0 | 0
387 | MURSHIDABAD | Murshidabad Division | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. , SM/15047 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.18 | 100 | 100
388 | MURSHIDABAD | Murshidabad Division | MAHENDRAPUR PIPED WATER SUPPLY SCHEME. , SM/15047 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MAHENDRAPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti- II Block under Murshidabad Division, P.H. Engineering Dte | 3389/MURD | 01/11/2023 | 541 | TAPAN DAS | 18.56 | 8.35 | 52.35 | 50
389 | MURSHIDABAD | Murshidabad Division | Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad. , SM/15067 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 5.01 | 100 | 1
390 | MURSHIDABAD | Murshidabad Division | Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad. , SM/15067 | Augmentation | Material Requisition To Resource Division | 1219/MURD/41 | 03/05/2023 | 0 | Resource Division | 31.36 | 0 | 0 | 0
391 | MURSHIDABAD | Murshidabad Division | Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad. , SM/15067 | Augmentation | Material Requisition To Resource Division | 526/MURD/06 | 19/02/2024 | 0 | Resource Division | 14.88 | 0 | 0 | 0
392 | MURSHIDABAD | Murshidabad Division | Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad. , SM/15067 | Augmentation | Augmentation of NATIAL RAJANAGAR ZONE-I ,II,& III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | 2724/MURD | 29/08/2023 | 765 | M/S. MOHAN LAL JAIN | 2092.12 | 252.11 | 39.32 | 56
393 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Natial Rajnagar Zone-II Pipe Water Supply Scheme Block - Raninagar -II District - Murshidabad. , SM/15067 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Natial Rajanagar Zone-II Piped water supply scheme Block_Raninagar II Dist_Murshidabad under MEDB PHE Dte. | 351/MEDB | 10/02/2025 | 89 | M/S S. S. ENTERPRISE (DOMKAL) | 45.27 | 0 | 0 | 0
394 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE-II PIPED WATER SUPPLY SCHEME. , SM/16241 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-II under Andhua ground water based water supply scheme under Block_ Farakka Dist. - Murshidabad under MEDB, PHE Dte. | 3662/MEDB | 03/11/2023 | 92 | ARINDAM MAJUMDAR | 11.36 | 0 | 0 | 0
395 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE-II PIPED WATER SUPPLY SCHEME. , SM/16241 | Augmentation | Material Requisition To Resource Division | 1180/MURD/21 | 29/04/2023 | 0 | Resource Division | 46.79 | 0 | 0 | 0
396 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE-II PIPED WATER SUPPLY SCHEME. , SM/16241 | Augmentation | Continuation work order for preparation of D.P.R. for Augmentation of Andhua Zone- II & Zone - III PWSS in Farakka Block in Jangipur Sub-Division under Murshidabad Division, PHE Dte. | 3720/MURD | 05/12/2023 | 30 | M/S SOBHA & CO. | 4.51 | 0 | 0 | 100
397 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE-II PIPED WATER SUPPLY SCHEME. , SM/16241 | Augmentation | NEW SERVICE CONNECTION AT ANDHUA Z2 PH 2 CID 304391007 |  | 02/12/2024 | 0 | WBSEDCL | 14.3 | 0 | 0 | 0
398 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE-II PIPED WATER SUPPLY SCHEME. , SM/16241 | Augmentation | Laying of Rising main , Distribution System, 2183 nos FHTC, construction of OHR (Capacity 350 cum), Repairing of OHR , Sinking of Tube Well , Repairing of pump house, Repairing of Boundary Wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Andhua Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | 138/MURD | 16/01/2024 | 365 | NAYLA CONSTRUCTION | 836.98 | 0 | 0 | 35
399 | MURSHIDABAD | Murshidabad Division | Augmentation of Jaykrishnapur Zone-II piped water supply scheme in Samserganj Block in the District of Murshidabad. , SM/16245 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 8.3 | 200 | 1
400 | MURSHIDABAD | Murshidabad Division | Augmentation of Jaykrishnapur Zone-II piped water supply scheme in Samserganj Block in the District of Murshidabad. , SM/16245 | Augmentation | Material Requisition To Resource Division | 1180/MURD/24 | 29/04/2023 | 0 | Resource Division | 62.68 | 0 | 0 | 0
401 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Jaykrishnapur Zone-II piped water supply scheme in Samserganj Block in the District of Murshidabad. , SM/16245 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-II under Jaykrishnapur ground water based water supply scheme under Block_ Samserganj, Dist. - Murshidabad under MEDB, PHE Dte. | 3686/MEDB | 03/11/2023 | 92 | DIPALI CONSTRUCTION | 22.53 | 18.76 | 83.24 | 12
402 | MURSHIDABAD | Murshidabad Division | Augmentation of Jaykrishnapur Zone-II piped water supply scheme in Samserganj Block in the District of Murshidabad. , SM/16245 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
403 | MURSHIDABAD | Murshidabad Division | Augmentation of Jaykrishnapur Zone-II piped water supply scheme in Samserganj Block in the District of Murshidabad. , SM/16245 | Augmentation | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 300 & 100 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Joykrishnapur Zone-I, Zone- II & Sikdarpur PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 3243/MURD | 15/10/2023 | 365 | BIJAY CHOWDHURY | 894.65 | 0 | 0 | 0
404 | MURSHIDABAD | Murshidabad Division | Augmentation of Jaykrishnapur Zone-II piped water supply scheme in Samserganj Block in the District of Murshidabad. , SM/16245 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jaykrishnapur Zone-II & Giria Zone - I Water Supply Scheme under Jangipur Sub-Division under Murshidabad Division, P.H. Engineering Dte | 1767/MURD | 06/07/2023 | 544 | R.K. DRILLING SERVICES | 23.58 | 0 | 0 | 100
405 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. , SM/16246 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III ,Zone-II under Loknathpur ground water based water supply scheme under Block_ Beldanga-II, Dist. - Murshidabad under MEDB, PHE Dte. | 3690/MEDB | 03/11/2023 | 92 | GOENKA ENTERPRISE | 33.83 | 0 | 0 | 0
406 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. , SM/16246 | Augmentation | Material Requisition To Resource Division | 1180/MURD/29 | 29/04/2023 | 0 | Resource Division | 45.89 | 0 | 0 | 0
407 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. , SM/16246 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | 480/MURD | 22/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 12.36 | 200 | 0
408 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. , SM/16246 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 2.84 | 100 | 80
409 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. , SM/16246 | Augmentation | Material Requisition To Resource Division | 1811/MURD/23 | 20/06/2024 | 0 | Resource Division | 7.29 | 0 | 0 | 0
410 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. , SM/16246 | Augmentation | NEW CONNECTION AT LOKNATHPUR Z-II PH-I | 417/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 4.52 | 0 | 0 | 0
411 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. , SM/16246 | Augmentation | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Lalgola, Beldanga II and Bharatpur I and II block Under District Murshidabad under MEDB PHE Dte. | 45/5 | 29/05/2025 | 92 | M/S S. S. ENTERPRISE (DOMKAL) | 16.41 | 0 | 0 | 0
412 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. , SM/16246 | Augmentation | Laying Distribution System For Augmentation of Loknathpur Zone-II (Part-A) PWSS of Beldanga-II Block under Murshidabad Division ,PHE.Dte | 847/MURD | 24/03/2023 | 950 | SOMA CONSTRUCTION | 154.95 | 0 | 0 | 40
413 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. , SM/16246 | Augmentation | Augmentation of Ground Water Based Loknathpur zone-II PWSS to accommodate FHTC of 600 nos household Laying Rising Main ,Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) & Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement), Construction of Boundary Wall of 170 m and Soil Investigation & 200 Cum Construction of OHR and Special repair and renovation of existing 2 (Two) Nos Pump House and Boundary wall at Berhampore Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-B) | 3147/MURD | 09/10/2023 | 220 | M H SUPPLIERS | 210.2 | 0 | 0 | 8
414 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. , SM/16246 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for LOKNATHPUR ZONE-II Ground Based Water Supply Scheme in Beldanga -II Block under Murshidabad Division , PHE Dte. | 1130/MURD | 16/05/2025 | 60 | MARUTI CONSTRUCTION AND CO. | 23.01 | 0 | 0 | 0
415 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF LOKENATHPUR ZONE-II PIPED WATER SUPPLY SCHEME , BLOCK- BELDANGA-II , DIST- MURSHIDABAD. , SM/16246 | Augmentation | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LOKENATHPUR ZONE-II Water Supply Scheme at Head Work Site, 2nd Site site at Beldanga-II Block under Murshidabad Division, P.H. Engineering Dte | 3812/MURD | 12/12/2023 | 497 | TRIYA CONSTRUCTION | 27.6 | 13.24 | 68.24 | 100
416 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-A) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. , SM/15836 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 7.53 | 100 | 1
417 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-A) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. , SM/15836 | Augmentation | Material Requisition To Resource Division | 1210/MURD/12 | 02/05/2023 | 0 | Resource Division | 110.91 | 0 | 0 | 0
418 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-A) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. , SM/15836 | Augmentation | Material Requisition To Resource Division | 526/MURD/03 | 19/02/2024 | 0 | Resource Division | 5.48 | 0 | 0 | 0
419 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-A) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. , SM/15836 | Augmentation | P T RASULPUR PH-IV | 420/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 5.54 | 0 | 0 | 0
420 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-A) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. , SM/15836 | Augmentation | P T RASULPURE PH-1 | 418/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 3.99 | 0 | 0 | 0
421 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-A) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. , SM/15836 | Augmentation | P T RASULPUR PH-III | 419/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 5.51 | 0 | 0 | 0
422 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-A) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. , SM/15836 | Augmentation | Formal work order for Augmentation of P.T.Rasulpur (Part - A) Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE.Dte. | 602/MURD | 02/03/2023 | 1035 | M/S.TAPAS KUMAR CHAKRABORTY | 521.15 | 363.84 | 69.82 | 30
423 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-A) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. , SM/15836 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II , III ,IV & V under P.T.RASULPUR ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | 3721/MEDB | 03/11/2023 | 669 | EASTERN INDIA SALES & SERVICE | 55.34 | 35.13 | 63.48 | 25
424 | MURSHIDABAD | Murshidabad Division | RAMNA BARAKHARI AND ADJOIMING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16278 | New | Material Requisition To Resource Division | 1043/MURD/7 | 19/04/2023 | 0 | Resource Division | 25.05 | 0 | 0 | 0
425 | MURSHIDABAD | Berhampore Mechanical | RAMNA BARAKHARI AND ADJOIMING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16278 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under RAMNA BARAKHARI ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | 1905/MEDB | 16/06/2023 | 92 | DAS CONSTRUCTION | 22.81 | 16.07 | 70.46 | 8
426 | MURSHIDABAD | Berhampore Mechanical | RAMNA BARAKHARI AND ADJOIMING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16278 | New | NEW CONNECTION AT RAMNABORKHARI PH-I | 66/WBSEDCL-JJM | 09/05/2024 | 0 | WBSEDCL | 3.64 | 0 | 0 | 0
427 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at NABIPUR Ground water Based PWSS, Block-Raninagar-II , Dist- Murshidabad under MEDB, PHE Dte. , SM/15346 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at NABIPUR Ground water Based PWSS, Block-Raninagar-II , Dist- Murshidabad under MEDB, PHE Dte | 3754/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 6.39 | 0 | 0 | 0
428 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Kasiadanga Zone- I & II Ground water Based PWSS, Block-Raghunathganj-II , Dist- Murshidabad under MEDB, PHE Dte. , SM/15349 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Kasiadanga Zone- I&II Ground water Based PWSS, Block-Raghunathganj-II , Dist- Murshidabad under MEDB, PHE Dte. | 3750/MEDB | 03/11/2023 | 92 | SREE RADHA ELECTRICAL | 6.39 | 0 | 0 | 0
429 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Jorgacha Part-I, Ground water Based PWSS, Block-Domkal , Dist- Murshidabad under MEDB, PHE Dte. , SM/15350 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Jorgacha Part-I, Ground water Based PWSS, Block-Domkal , Dist- Murshidabad under MEDB, PHE Dte. | 4348/MEDB | 29/12/2023 | 91 | ELECTRO ENTERPRISES | 6.44 | 0 | 0 | 0
430 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone- III, Block- Lalgola, District- Murshidabad. , SM/16434 | New | Mini Piped Water Supply Scheme for Durgapur zone-III under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 150/BD-I | 15/05/2023 | 90 | SAHA CONSTRUCTION | 30.31 | 0 | 0 | 0
431 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone- III, Block- Lalgola, District- Murshidabad. , SM/16434 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Durgapur Zone-III village, Block:- Lalgola under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3613/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0 | 0
432 | MURSHIDABAD | Berhampore Mechanical | KHORDDA NARAYANPUR PIPED WATER SUPPLY SCHEME, BLOCK- KANDI , DISTRICT- MURSHIDABAD. , SM/16442 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Khordda Narayanpur Part-A village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3066/MEDB | 02/08/2023 | 92 | M/S SAJAHAN CHOWDHURY | 6.27 | 0 | 0 | 0
433 | MURSHIDABAD | Berhampore Mechanical | KHORDDA NARAYANPUR PIPED WATER SUPPLY SCHEME, BLOCK- KANDI , DISTRICT- MURSHIDABAD. , SM/16442 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Khordda Narayanpur Part-B village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3067/MEDB | 02/08/2023 | 92 | JOY BISHNU ENGINEERING CO. | 6.3 | 0 | 0 | 0
434 | MURSHIDABAD | Murshidabad Division | KHORDDA NARAYANPUR PIPED WATER SUPPLY SCHEME, BLOCK- KANDI , DISTRICT- MURSHIDABAD. , SM/16442 | New | Ground Water based piped water supply scheme for Khordda Narayanpur Part- B village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2340/MURD | 03/08/2023 | 60 | CHOWDHURY CONSTRUCTION | 30.55 | 0 | 0 | 0
435 | MURSHIDABAD | Murshidabad Division | KHORDDA NARAYANPUR PIPED WATER SUPPLY SCHEME, BLOCK- KANDI , DISTRICT- MURSHIDABAD. , SM/16442 | New | Ground Water based piped water supply scheme for Khordda Narayanpur Part- A village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2493/MURD | 11/08/2023 | 60 | M/S GREAT INDIA CONSTRUCTION | 30.54 | 0 | 0 | 0
436 | MURSHIDABAD | Berhampore Mechanical | GOPJAN(P) PIPED WATER SUPPLY SCHEME, BLOCK- BERHAMPORE , DISTRICT- MURSHIDABAD. , SM/16444 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Gopjan (P) village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3050/MEDB | 02/08/2023 | 92 | SARKAR CONSTRUCTION | 6.3 | 0 | 0 | 0
437 | MURSHIDABAD | Murshidabad Division | GOPJAN(P) PIPED WATER SUPPLY SCHEME, BLOCK- BERHAMPORE , DISTRICT- MURSHIDABAD. , SM/16444 | New | Ground Water based piped water supply scheme for Gopjan (P) village, Block:- Berhampore, Berhampore Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2321/MURD | 02/08/2023 | 60 | SUBHENDRA MOHAN SARKAR | 30.54 | 0 | 0 | 0
438 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16545 | Augmentation | Material Requisition To Resource Division | 1147/MURD/1 | 27/04/2023 | 0 | Resource Division | 177.04 | 0 | 0 | 0
439 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16545 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 0 | 21
440 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16545 | Augmentation | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Anup Nagar CT T.W-I, , Bhabki T.W-I,II, Harua T.W-I,II,III Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 761/MURD | 02/04/2025 | 80 | TITUMIR INTERNATIONAL | 70.61 | 0 | 0 | 0
441 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16545 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 1.82 | 100 | 100
442 | MURSHIDABAD | Murshidabad Division | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-B) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16554 | Augmentation | Augmentation of Domkal Zone-II (Part-B) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 946/MURD | 05/04/2023 | 1002 | GOUTAM MANDAL | 337.24 | 139.66 | 41.41 | 60
443 | MURSHIDABAD | Berhampore Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS , SM/16454 | New | Material Requisition To Resource Division | 61/BD-1/6 | 27/04/2023 | 0 | Resource Division | 15.38 | 0 | 0 | 0
444 | MURSHIDABAD | Berhampore Mechanical | SAMSASKAR AND ADJOINING MOUJAS PWSS , SM/16454 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SAMSASKAR ground water based water supply scheme under Block_ Berhampore Dist. - Murshidabad under MEDB, PHE Dte. | 4339/MEDB | 29/12/2023 | 91 | DEBJYOTI BASU | 20.87 | 0 | 0 | 10
445 | MURSHIDABAD | Berhampore Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS , SM/16454 | New | Material Requisition To Resource Division | 2096/BD-I/4 | 25/11/2024 | 0 | Resource Division | 10 | 0 | 0 | 0
446 | MURSHIDABAD | Berhampore Mechanical | SAMSASKAR AND ADJOINING MOUJAS PWSS , SM/16454 | New | NEW CONNECTION SAMASKAR PH-I | 10/WBSEDCL-JJM | 09/04/2024 | 0 | WBSEDCL | 7.19 | 0 | 0 | 0
447 | MURSHIDABAD | Berhampore Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS , SM/16454 | New | SAMASKAR PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | 1824/BD-I | 31/03/2023 | 913 | ARINDAM MAJUMDAR | 109.77 | 0 | 0 | 35
448 | MURSHIDABAD | Berhampore Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS , SM/16454 | New | SAMASKAR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 220/BD-I | 17/05/2023 | 960 | BINAPANI ENTERPRISE | 52.7 | 16.88 | 32.03 | 5
449 | MURSHIDABAD | Berhampore Division I | SAMSASKAR AND ADJOINING MOUJAS PWSS , SM/16454 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAMASKAR Water Supply Scheme(TW - II) within Berhampore Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 08/BD-I | 06/01/2025 | 240 | MAMATA USHA ENTERPRISE | 9.01 | 0 | 0 | 100
450 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16455 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 2.44 | 100 | 100
451 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16455 | Augmentation | Material Requisition To Resource Division | 1230/MURD/06 | 04/05/2023 | 0 | Resource Division | 4.02 | 0 | 0 | 0
452 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16455 | Augmentation | Construction of Pump House, Boundary Wall, of BRINDABANPUR ZONE-II Ground water based Piped water supply scheme with in Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 778/MURD | 14/03/2024 | 524 | M/S S M ENTERPRISE | 28.51 | 14.33 | 50.25 | 65
453 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16455 | Augmentation | NEW SERVICE CONNECTION BRINDABANPUR Z2 PH2 ID304232743 | 266/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 4.96 | 0 | 0 | 0
454 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16455 | Augmentation | NEW SERVICE CONNECTION AT BRINDABANPUR Z2 PH I, ID304232742 | 267/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.88 | 0 | 0 | 0
455 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16455 | Augmentation | Formal Work Order for Augmentation of BRINDABANPUR ZONE-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 744/MURD | 16/03/2023 | 1301 | NATIONAL CONSTRUCTION (PROP:NIZAMUL BISWAS) | 487.63 | 358.03 | 73.42 | 45
456 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16455 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Brindabanpur Zone-II Piped water supply scheme Block_Raninagar II Dist_Murshidabad under MEDB PHE Dte. | 349/MEDB | 10/02/2025 | 89 | MERCURY ENGINEERING CO | 37.15 | 0 | 0 | 0
457 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16455 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. under MEDB, PHE Dte. | 316/MEDB | 10/02/2025 | 89 | M/S SAMRIDDHI ENTERPRISE | 34.79 | 0 | 0 | 0
458 | MURSHIDABAD | Murshidabad Division | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16112 | New | Material Requisition To Resource Division | 1129/MURD/1 | 25/04/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
459 | MURSHIDABAD | Murshidabad Division | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16112 | New | PULIA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. | 1698/MURD | 28/06/2023 | 1092 | ESCON INDIA | 134.38 | 42.88 | 31.91 | 10
460 | MURSHIDABAD | Central Drilling | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16112 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 2203/CDD | 01/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 0 | 0 | 10
461 | MURSHIDABAD | Berhampore Mechanical | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16112 | New | Pulia PH-1 Application No-3004547904 | 235/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 5.22 | 0 | 0 | 0
462 | MURSHIDABAD | Berhampore Mechanical | PULIA AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16112 | New | Pulia PH-2 App No- 3004547976 | 236/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 5.46 | 0 | 0 | 0
463 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16407 | Augmentation | Material Requisition To Resource Division | 1147/MURD/9 | 27/04/2023 | 0 | Resource Division | 34.37 | 0 | 0 | 0
464 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16407 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHODARAMPUR (CT) AND PRASADPUR ZONE-II Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | 2721/MURD | 29/08/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0 | 0
465 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16407 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 0 | 5
466 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16407 | Augmentation | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 660/MURD | 19/03/2025 | 90 | JOY GURU ENTERPRISE | 82.5 | 0 | 0 | 0
467 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16407 | Augmentation | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 0 | 20
468 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16407 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 4.02 | 100 | 100
469 | MURSHIDABAD | Murshidabad Division | Augmentation of BHASIPAIKAR ZONE-IIB piped water supply scheme in Samserganj Block in the District of Murshidabad. , SM/16171 | Augmentation | Material Requisition To Resource Division | 1167/MURD/26 | 28/04/2023 | 0 | Resource Division | 61.81 | 0 | 0 | 0
470 | MURSHIDABAD | Murshidabad Division | Augmentation of BHASIPAIKAR ZONE-IIB piped water supply scheme in Samserganj Block in the District of Murshidabad. , SM/16171 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BHASIPAIKAR ZONE-IIB Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | 3194/MURD | 12/10/2023 | 21 | TAPAN DAS | 23.72 | 15.85 | 100 | 50
471 | MURSHIDABAD | Murshidabad Division | Augmentation of BHASIPAIKAR ZONE-IIB piped water supply scheme in Samserganj Block in the District of Murshidabad. , SM/16171 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0 | 0
472 | MURSHIDABAD | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. , SM/16281 | New | Material Requisition To Resource Division | 1230/MURD/22 | 04/05/2023 | 0 | Resource Division | 30.14 | 0 | 0 | 0
473 | MURSHIDABAD | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. , SM/16281 | New | Material Requisition To Resource Division | 495/MURD/03 | 15/02/2024 | 0 | Resource Division | 9.2 | 0 | 0 | 0
474 | MURSHIDABAD | Berhampore Mechanical | GHORSALA PIPED WATER SUPPLY SCHEME. , SM/16281 | New | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Jalangi , Raninagar I and II, Farakka, Raghunathganj I and II block Under District Murshidabad under MEDB PHE Dte. | 45/3 | 29/05/2025 | 92 | M/S K.P. PRAMANIK | 19.57 | 0 | 0 | 0
475 | MURSHIDABAD | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. , SM/16281 | New | Formal work order for GHORSALA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Jivan Mission of raghunathganj-I Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE.Dte | 794/MURD | 21/03/2023 | 833 | DHIRENDRANATH MONDAL | 431.52 | 304.81 | 70.64 | 25
476 | MURSHIDABAD | Berhampore Mechanical | GHORSALA PIPED WATER SUPPLY SCHEME. , SM/16281 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under GHORSALA ground water based water supply scheme under Block_ Raghunathganj- I Dist. - Murshidabad under MEDB, PHE Dte. | 3724/MEDB | 03/11/2023 | 790 | WEST BENGAL ENGINEERING CO. | 33.53 | 0 | 0 | 30
477 | MURSHIDABAD | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. , SM/16281 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHORSALA and KASIADANGA ZONE - I Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | 2722/MURD | 29/08/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0 | 0
478 | MURSHIDABAD | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. , SM/16281 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.36 | 100 | 100
479 | MURSHIDABAD | Murshidabad Division | GHORSALA PIPED WATER SUPPLY SCHEME. , SM/16281 | New | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 4.29 | 100 | 100
480 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Lahari, Block- Bhagwangola-II, District- Murshidabad. , SM/16213 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Lahari village, Block:- Bhagwangola-II under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3615/MEDB | 03/11/2023 | 92 | AVINABA ENGINEERING CONCERN | 6.27 | 0 | 0 | 0
481 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Lahari, Block- Bhagwangola-II, District- Murshidabad. , SM/16213 | New | Mini Piped Water Supply Scheme for Lahari under Bhagwangola-II block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 153/BD-I | 15/05/2023 | 90 | SANTA TRADING | 30.53 | 0 | 0 | 0
482 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08279 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Baramasia (Village code 314622) under Narsinghpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184090 in the District of Murshidabad. | 530/MURD | 04/02/2021 | 60 | RELIABLE ENTERPRISE | 44.77 | 0 | 0 | 1
483 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08279 | Retrofitting | Formal Work Order for ¿Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Narasinghapur (Village code 314620) under Narasinghapur Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184090 in the District of Murshidabad. (Sl No-18) | 697/MURD | 24/02/2021 | 180 | MANAB KUMAR GHOSH | 64.64 | 53.05 | 82.06 | 0
484 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08279 | Retrofitting | Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Raghunathganj-II Block (Giria, Sekendra, Mithipur, Jotkamal, Dayarampur, Sammatinagar, Teghari, Kasiadanga, laxmijhola & Sekhalipur) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. | 371/JSD | 22/12/2021 | 30 | IMAGIN | 3.99 | 0 | 0 | 1
485 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08279 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village GODAGARI (Village Code 314615) under NARSINGHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 664 of 21-22 by EE MURD | 404-MSD/21-22 | 22/03/2022 | 0 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 26.24 | 0 | 0 | 0
486 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08279 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village DAYARAMPUR (Village Code 314617) under NARASINGHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 295 of 21-22 by EE MURD | 418-MSD/21-22 | 23/03/2022 | 0 | M/S. BIMALENDU BOSE | 32.54 | 0 | 0 | 0
487 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08279 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dayarampur (Village code 314617) under Narasinghapur Ground Water Supply Scheme for Arsenic Affected Area of Jalangi Block. under Murshidabad Division, PHE Dte. Scheme ID 0005184090 (SlNo-17) | 3684/MURD | 26/11/2021 | 180 | BENOY DOBAY | 46.91 | 46.85 | 100 | 1
488 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08279 | Retrofitting | Material Requisition To Resource Division | 395/MURD | 16/02/2022 | 0 | Resource Division | 8.08 | 0 | 0 | 0
489 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08279 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baramasia (Village code 314622) under Narasinghapur Ground Water Supply Scheme for Arsenic Affected Area of Jalangi Block. under Murshidabad Division, PHE Dte. Scheme ID 0005184090 | 2418/MURD | 22/08/2022 | 180 | M/S. SINHA & SONS | 49.87 | 0 | 0 | 0
490 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08279 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dayarampur (Village code 314617) under Narsinghpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184090 in the District of Murshidabad. | 531/MURD | 04/02/2021 | 60 | M/S. BIMALENDU BOSE | 44.35 | 0 | 0 | 1
491 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08279 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Godagari ( Village Code -314615) under Narsinghpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184090) | 280/MURD | 03/02/2022 | 60 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 59.67 | 33.89 | 100 | 1
492 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Godagari, Dayarampur, Narsingpur, Baramasia (314615, 314617, 314620, 314622) of Narsinghpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08279 | Retrofitting | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 495 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Narasinghpur (Village code 314620) under Narasinghpur Ground water based water supply scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005184090). | 705/MURD | 14/03/2022 | 15 | M/S. GHOSH ENTERPRISE | 12.87 | 12.42 | 100 | 1
493 | MURSHIDABAD | Murshidabad Division | Augmentation of Ballalpur Water Supply Scheme Block -Farakka, Dist- Murshidabad. , SM/16417 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 6.15 | 200 | 1
494 | MURSHIDABAD | Murshidabad Division | Augmentation of Ballalpur Water Supply Scheme Block -Farakka, Dist- Murshidabad. , SM/16417 | Augmentation | Material Requisition To Resource Division | 1180/MURD/30 | 29/04/2023 | 0 | Resource Division | 91.87 | 0 | 0 | 0
495 | MURSHIDABAD | Murshidabad Division | Augmentation of Ballalpur Water Supply Scheme Block -Farakka, Dist- Murshidabad. , SM/16417 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
496 | MURSHIDABAD | Murshidabad Division | Augmentation of Ballalpur Water Supply Scheme Block -Farakka, Dist- Murshidabad. , SM/16417 | Augmentation | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III, IV of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Ballalpur Water Supply Scheme at Head Work Site, 2nd Site site at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | 3780/MURD | 11/12/2023 | 21 | HARUN ALL RASHID & BROTHERS | 27.6 | 0 | 0 | 0
497 | MURSHIDABAD | Murshidabad Division | Augmentation of Ballalpur Water Supply Scheme Block -Farakka, Dist- Murshidabad. , SM/16417 | Augmentation | Providing balance Functional Household Tap Connections (FHTC) of 405 nos household in connection with Jal Jeevan Mission under command area of village of Ballalpur (Village Code -313811) under Ballalpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division, P.H.E Dte. | 1934/MURD | 18/07/2023 | 30 | TARIKUL SK | 14.95 | 14.95 | 100 | 100
498 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ballalpur Water Supply Scheme Block -Farakka, Dist- Murshidabad. , SM/16417 | Augmentation | POWER CONNECTION AT PWSS PH2 BALLALPUR APPLICATION NO.3004627376 | 37/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 4.83 | 0 | 0 | 0
499 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ballalpur Water Supply Scheme Block -Farakka, Dist- Murshidabad. , SM/16417 | Augmentation | POWER CONNECTION AT PWSS PH3 BALLALPUR APPLICATION NO.3004626223 | 38/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 6.08 | 0 | 0 | 0
500 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ballalpur Water Supply Scheme Block -Farakka, Dist- Murshidabad. , SM/16417 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II under Ballalpur ground water based water supply scheme under Block_ Farakka Dist. - Murshidabad under MEDB, PHE Dte. | 3698/MEDB | 03/11/2023 | 790 | P. K. ENGINEERING | 22.55 | 0 | 0 | 70
501 | MURSHIDABAD | Murshidabad Division | Augmentation of Ballalpur Water Supply Scheme Block -Farakka, Dist- Murshidabad. , SM/16417 | Augmentation | Laying of Rising Main , Distribution System, 279 nos FHTC, construction of OHR (Capacity 400 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Ballalpur PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 3115/MURD | 05/10/2023 | 935 | M/S GANGWAL CONSTRUCTION CO | 338.54 | 16.5 | 4.87 | 85
502 | MURSHIDABAD | Murshidabad Division | Augmentation of Ballalpur Water Supply Scheme Block -Farakka, Dist- Murshidabad. , SM/16417 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 100 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for BALLALPUR Ground Based Water Supply Scheme in Farakka Block under Murshidabad Division , PHE Dte. | 1228/MURD | 28/05/2025 | 60 | MONDAL PRECISION PRIVATE LIMITED | 40.44 | 0 | 0 | 0
503 | MURSHIDABAD | Murshidabad Division | Augmentation of Basudevpur Zone-II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/16180 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.26 | 100 | 100
504 | MURSHIDABAD | Murshidabad Division | Augmentation of Basudevpur Zone-II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/16180 | Augmentation | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month].For the month of 17/07/2024 to 16/01/2025. [ Vehicle No:- WB 58 CD 3758] | 52/JSD | 16/07/2024 | 184 | HASSAN CONSTRUCTION | 0.88 | 1.39 | 158.06 | 0
505 | MURSHIDABAD | Berhampore Mechanical | KOLLA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16395 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Kolla ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | 3710/MEDB | 03/11/2023 | 92 | WEST BENGAL ENGINEERING CO. | 22.12 | 0 | 0 | 0
506 | MURSHIDABAD | Murshidabad Division | KOLLA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16395 | New | Material Requisition To Resource Division | 1075/MURD/13 | 19/04/2023 | 0 | Resource Division | 1.38 | 0 | 0 | 0
507 | MURSHIDABAD | Murshidabad Division | KOLLA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16395 | New | KOLLA PWSS to accommodate FHTC under Jal Jeevan Mission of Block-Bharatpur-I of Kandi Sub Division of Murshidabad District under Murshidabad Division ,PHE.Dte. | 981/MURD | 10/04/2023 | 1022 | SOM CONSTRUCTION AGENCY | 189.17 | 68.13 | 36.02 | 70
508 | MURSHIDABAD | Murshidabad Division | BAHARAGACHI PIPE WATER SUPPLY SCHEME. , SM/15939 | New | Material Requisition To Resource Division | 1230/MURD/16 | 04/05/2023 | 0 | Resource Division | 21.39 | 0 | 0 | 0
509 | MURSHIDABAD | Berhampore Mechanical | BAHARAGACHI PIPE WATER SUPPLY SCHEME. , SM/15939 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I II & III under BAHARAGACHI ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | 1899/MEDB | 16/06/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 32.57 | 25.66 | 78.79 | 20
510 | MURSHIDABAD | Murshidabad Division | BAHARAGACHI PIPE WATER SUPPLY SCHEME. , SM/15939 | New | Formal work order for the Work of BAHARAGACHI PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Samserganj Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | 655/MURD | 06/03/2023 | 1032 | ARINDAM MAJUMDAR | 266.77 | 0 | 0 | 25
511 | MURSHIDABAD | Murshidabad Division | BAHARAGACHI PIPE WATER SUPPLY SCHEME. , SM/15939 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 4.5 | 100 | 100
512 | MURSHIDABAD | Murshidabad Division | BAHARAGACHI PIPE WATER SUPPLY SCHEME. , SM/15939 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAHARAGACHI AND ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | 2720/MURD | 29/08/2023 | 581 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 0 | 100
513 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED MADNA ZONE II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15917 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I & II ,ZONE-II under MADNA ground water based water supply scheme under Block_ Siti-I Dist. - Murshidabad under MEDB, PHE Dte. | 1904/MEDB | 16/06/2023 | 92 | JOY BISHNU ENGINEERING CO. | 23 | 0 | 0 | 0
514 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MADNA ZONE II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15917 | Augmentation | Material Requisition To Resource Division | 1147/MURD/3 | 27/04/2023 | 0 | Resource Division | 128.8 | 0 | 0 | 0
515 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED MADNA ZONE II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15917 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under Madna ground water based water supply scheme under Block_ Suti-I Dist. - Murshidabad under MEDB, PHE Dte. | 1878/MEDB | 16/06/2023 | 92 | M/S. SUPER CONSTRUCTION | 35.74 | 15.06 | 42.13 | 4
516 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MADNA ZONE II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15917 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 0 | 21
517 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MADNA ZONE II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15917 | Augmentation | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0 | 0
518 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MADNA ZONE II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15917 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.85 | 100 | 100
519 | MURSHIDABAD | Murshidabad Division | BASANTAPUR AND ADJOINING MOUJAS PWSS , SM/15940 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BASANTPUR AND ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Khargram Block under Murshidabad Division, P.H. Engineering Dte. | 2656/MURD | 24/08/2023 | 21 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 0 | 0
520 | MURSHIDABAD | Murshidabad Division | BASANTAPUR AND ADJOINING MOUJAS PWSS , SM/15940 | New | Material Requisition To Resource Division | 1075/MURD/7 | 19/04/2023 | 0 | Resource Division | 18.61 | 0 | 0 | 0
521 | MURSHIDABAD | Berhampore Mechanical | BASANTAPUR AND ADJOINING MOUJAS PWSS , SM/15940 | New | NEW SERVICE CONNECTION AT BASANTIPUR PH I, ID304233690 | 274/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 4.96 | 0 | 0 | 0
522 | MURSHIDABAD | Murshidabad Division | BASANTAPUR AND ADJOINING MOUJAS PWSS , SM/15940 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Basantapur & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | 1104/MURD | 24/04/2023 | 30 | NADIA TUBEWELLS | 21.35 | 8.8 | 41.2 | 50
523 | MURSHIDABAD | Berhampore Mechanical | BASANTAPUR AND ADJOINING MOUJAS PWSS , SM/15940 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under BASANTAPUR ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | 1924/MEDB | 16/06/2023 | 746 | MAHADEB ENTERPRISE | 20.81 | 0 | 0 | 50
524 | MURSHIDABAD | Murshidabad Division | BASANTAPUR AND ADJOINING MOUJAS PWSS , SM/15940 | New | Construction of Boundwary Wall , PCC Approach road of Basantapur PWSS in Khargram Block , Kandi Sub-Division under Murshidabad Division , PHE. Dte. | 898/MURD | 23/04/2025 | 60 | M.R. ENTERPRISE (MD. HASANUZZAMAN) | 10.43 | 0 | 0 | 0
525 | MURSHIDABAD | Murshidabad Division | BASANTAPUR AND ADJOINING MOUJAS PWSS , SM/15940 | New | Construction of Pump House , Land Development Work of Basantapur PWSS in Khargram Block , Kandi Sub-Division under Murshidabad Division , PHE. Dte. | 901/MURD | 23/04/2025 | 343 | NOBEL CONSTRUCTION | 10.68 | 0 | 0 | 50
526 | MURSHIDABAD | Murshidabad Division | BASANTAPUR AND ADJOINING MOUJAS PWSS , SM/15940 | New | Laying Distribution System , Rising Main Connection FHTC, Construction of Pump House & Boundary Wall for Basantapur water supply scheme of Khargram Block under Murshidabad Division, PHE Dte. | 929/MURD | 31/03/2023 | 793 | PARTHA PRATIM DAS | 61.73 | 50.48 | 90.46 | 30
527 | MURSHIDABAD | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. , SM/15945 | New | Material Requisition To Resource Division | 1230/MURD/29 | 04/05/2023 | 0 | Resource Division | 22.56 | 0 | 0 | 0
528 | MURSHIDABAD | Berhampore Mechanical | KOHETPUR PIPE WATER SUPPLY SCHEME. , SM/15945 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under KOHETPUR ground water based water supply scheme under Block_ Samsedganj Dist. - Murshidabad under MEDB, PHE Dte. | 4304/MEDB | 29/12/2023 | 91 | BHABANI PRASAD MANNA | 32.99 | 0 | 0 | 0
529 | MURSHIDABAD | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. , SM/15945 | New | Material Requisition To Resource Division | 495/MURD/08 | 15/02/2024 | 0 | Resource Division | 8.37 | 0 | 0 | 0
530 | MURSHIDABAD | Berhampore Mechanical | KOHETPUR PIPE WATER SUPPLY SCHEME. , SM/15945 | New | NEW CONNECTION AT KOHETPUR PH-II | 143/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 4.17 | 0 | 0 | 0
531 | MURSHIDABAD | Berhampore Mechanical | KOHETPUR PIPE WATER SUPPLY SCHEME. , SM/15945 | New | NEW CONNECTION AT KOHETPUR PH-I | 144/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 4.92 | 0 | 0 | 0
532 | MURSHIDABAD | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. , SM/15945 | New | COST OF RESTORATION OF ROAD CONNECTTED TO NH-34 DHULIAN PAKUR ROAD AT CH. 4.275 TO 4.600. | 369-MSD/2024-20 | 12/09/2024 | 0 | MURSHIDABAD HIGHWAY DIVISION-1 | 13.3 | 0 | 0 | 0
533 | MURSHIDABAD | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. , SM/15945 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sagarpara Part-A, Kohetpur and Napara Water Supply Scheme under Islampur & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3409/MURD | 22/12/2022 | 45 | R.K. DRILLING SERVICES | 23.56 | 0 | 0 | 0
534 | MURSHIDABAD | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. , SM/15945 | New | Formal work order for the work of KOHETPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission of SAMSERGANJ Block, Murshidabad District under Murshidabad Division, PHE.Dte. | 670/MURD | 09/03/2023 | 762 | PRAFULLYA CONSTRUCTION | 379.82 | 141.31 | 37.2 | 22
535 | MURSHIDABAD | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. , SM/15945 | New | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 660/MURD | 19/03/2025 | 90 | JOY GURU ENTERPRISE | 82.5 | 0 | 0 | 0
536 | MURSHIDABAD | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. , SM/15945 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.16 | 100 | 100
537 | MURSHIDABAD | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. , SM/15945 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KOHETPUR Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | 2605/MURD | 22/08/2023 | 741 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 0 | 50
538 | MURSHIDABAD | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. , SM/15945 | New | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well,120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at HILORA - II & KOHETPUR Water Supply Scheme at Head Work Site under Murshidabad Division, P.H. Engineering Dte. | 1755/MURD | 13/06/2024 | 464 | R.K. DRILLING SERVICES | 11.79 | 0 | 0 | 100
539 | MURSHIDABAD | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. , SM/15945 | New | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Jangipur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(83 Nos.) | 2636/MURD | 23/09/2024 | 20 | KUNTAL SAHA | 9.28 | 0 | 0 | 100
540 | MURSHIDABAD | Murshidabad Division | KOHETPUR PIPE WATER SUPPLY SCHEME. , SM/15945 | New | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 4.12 | 100 | 100
541 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Salar Zone- II B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. , SM/16424 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II ,Zone-IIB under Salar ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | 3676/MEDB | 03/11/2023 | 457 | DAS ENTERPRISE (CHOA) | 21.42 | 3.85 | 17.96 | 8
542 | MURSHIDABAD | Murshidabad Division | Augmentation of Salar Zone- II B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. , SM/16424 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I , II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone- II B Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Bharatpur - II Block under Murshidabad Division, P.H. Engineering Dte | 3781/MURD | 11/12/2023 | 21 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 0 | 0
543 | MURSHIDABAD | Murshidabad Division | Augmentation of Salar Zone- II B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. , SM/16424 | Augmentation | Sinking of 01 (One) No of 250mm x 150 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHAYRAMARI Part-A and Salar Zone - IIB Water Supply Scheme as required under Murshidabad Division, P.H. Engineering Dte. | 1744/MURD | 06/07/2023 | 14 | SARKAR WATER SUPPLY AGENCY | 9.22 | 7.39 | 100 | 100
544 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Salar Zone- II B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. , SM/16424 | Augmentation | NEW CONNECTION AT SALAR Z-II/B PH-I | 299/WBSEDCL-JJM | 06/12/2024 | 0 | WBSEDCL | 6.15 | 0 | 0 | 0
545 | MURSHIDABAD | Murshidabad Division | Augmentation of Salar Zone- II B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. , SM/16424 | Augmentation | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 0 | 20
546 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone-IB piped water supply scheme in Samserganj Block in the District of Murshidabad. , SM/16169 | Augmentation | Material Requisition To Resource Division | 1167/MURD/25 | 28/04/2023 | 0 | Resource Division | 60.5 | 0 | 0 | 0
547 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone-IB piped water supply scheme in Samserganj Block in the District of Murshidabad. , SM/16169 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
548 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Bhasaipaikar Zone-IB piped water supply scheme in Samserganj Block in the District of Murshidabad. , SM/16169 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II , Zone-IB under Bhasaipaikar ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | 762/MEDB | 20/02/2024 | 90 | SARKAR CONSTRUCTION | 23.13 | 0 | 0 | 0
549 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone-IB piped water supply scheme in Samserganj Block in the District of Murshidabad. , SM/16169 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0 | 0
550 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15746 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (Tajsinghapur PWSS Scheme, Block - Raninagar-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3265/MURD | 05/10/2021 | 60 | RADIANT | 4.74 | 4.74 | 100 | 1
551 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15746 | Augmentation | Material Requisition To Resource Division | 1167/MURD/39 | 28/04/2023 | 0 | Resource Division | 79.35 | 0 | 0 | 0
552 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15746 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dhulauri Water Supply Scheme and Tejsinghapur Water Supply Schem under Murshidabad Division, P.H. Engineering Dte | 1746/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 23.58 | 20.97 | 100 | 100
553 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15746 | Augmentation | Augmentation of TEJSINGHAPUR PWSS under Jal Jivan Mission of RANINAGAR - II Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part-A) | 1383/MURD | 22/05/2023 | 955 | PRADIP KUMAR DAS | 294.57 | 142.98 | 48.54 | 86
554 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15746 | Augmentation | Augmentation of TEJSINGHAPUR PWSS under Jal Jeevan Mission of RANINAGAR - II Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (PART - B) | 1933/MURD | 18/07/2023 | 898 | VOICE CONSTRUCTION | 293.06 | 12.95 | 4.42 | 35
555 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15746 | Augmentation | Balance work of Laying Distribution System , Road Restoration and other ancillary works of Tejsinghapur Water Supply Scheme within Raninagar-II Block under Murshidabad Division, PHE. Dte. | 1259/MURD | 30/05/2025 | 60 | DAS TRADING CO. | 64.29 | 0 | 0 | 0
556 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15746 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED TEJSINGHAPUR PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. Dist. - Murshidabad under MEDB, PHE Dte. | 346/MEDB | 10/02/2025 | 89 | DAS ENTERPRISE (CHOA) | 23.19 | 0 | 0 | 0
557 | MURSHIDABAD | Murshidabad Division | Augmentation of Bharatpur Zone- II A Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. , SM/15747 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 4.06 | 100 | 76
558 | MURSHIDABAD | Murshidabad Division | Augmentation of Bharatpur Zone- II A Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. , SM/15747 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 4.68 | 100 | 80
559 | MURSHIDABAD | Murshidabad Division | Augmentation of Bharatpur Zone- II A Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. , SM/15747 | Augmentation | Augmentation of BHARATPUR (ZONE -IIA) PWSS under Jal Jeevan Mission of Bharatpur-I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | 3088/MURD | 03/10/2023 | 1114 | SOFIQUL ISLAM | 423.46 | 0 | 0 | 50
560 | MURSHIDABAD | Murshidabad Division | DAKSHIN RAYPUR AND ADJOINING MOUJAS PWSS , SM/15942 | New | Material Requisition To Resource Division | 1075/MURD/3 | 19/04/2023 | 0 | Resource Division | 13 | 0 | 0 | 0
561 | MURSHIDABAD | Berhampore Mechanical | DAKSHIN RAYPUR AND ADJOINING MOUJAS PWSS , SM/15942 | New | Electric Service Connection at Dakshin Raypur PH I, Application NO.3004475701, ID 304179843 | 188/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 12.03 | 0 | 0 | 0
562 | MURSHIDABAD | Berhampore Mechanical | DAKSHIN RAYPUR AND ADJOINING MOUJAS PWSS , SM/15942 | New | Electric Service New Connection DAKSHIN RAYPUR PH 2 PWSS Application NO. 3004475666. ID. 304178072 | 172/WBSEDCL-JJM | 05/12/2023 | 0 | WBSEDCL | 9.51 | 0 | 0 | 0
563 | MURSHIDABAD | Murshidabad Division | DAKSHIN RAYPUR AND ADJOINING MOUJAS PWSS , SM/15942 | New | Formal work order for DAKSHIN RAYPUR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of BURWAN Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 623/MURD | 03/03/2023 | 730 | DIPAYAN DEY | 393.85 | 311.99 | 79.21 | 31
564 | MURSHIDABAD | Berhampore Mechanical | DAKSHIN RAYPUR AND ADJOINING MOUJAS PWSS , SM/15942 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Dakshin Raypur ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | 1909/MEDB | 16/06/2023 | 929 | M/S SAMRIDDHI ENTERPRISE | 22.82 | 16.98 | 74.4 | 20
565 | MURSHIDABAD | Murshidabad Division | DAKSHIN RAYPUR AND ADJOINING MOUJAS PWSS , SM/15942 | New | Laying UPVC Pipe line , Road Restoration & FHTCs of Dakshin Raypur PWSS in Khargram Block of Kandi Sub Division under Murshidabad Division, PHE Dte. | 3146/MURD | 03/12/2024 | 30 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 19.79 | 0 | 0 | 0
566 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-IX & X )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . , SM/16672 | Retrofitting | Last mile connectivity and providing 3874 nos Functional House Hold Connection from Zone- IX of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. | 2689/MURD | 25/08/2023 | 120 | SUJIT KUMAR SAHA | 223.42 | 0 | 0 | 0
567 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-IX & X )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . , SM/16672 | Retrofitting | Last mile connectivity and providing 8231 nos Functional House Hold Connection from Zone- X of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . | 2690/MURD | 25/08/2023 | 120 | HANNAN BUILDERS PVT.LTD. | 475.31 | 0 | 0 | 0
568 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16770 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV ,Zone-II under AMINABAD ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | 3763/MEDB | 03/11/2023 | 92 | B. T. PROJECTS PVT. LTD. | 45.69 | 0 | 0 | 0
569 | MURSHIDABAD | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16770 | Augmentation | Material Requisition To Resource Division | 1210/MURD/15 | 02/05/2023 | 0 | Resource Division | 37.48 | 0 | 0 | 0
570 | MURSHIDABAD | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16770 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 4.47 | 100 | 100
571 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16770 | Augmentation | NEW CONNECTION AT AMINABAD Z-II PH-II | 16/WBSEDCL-JJM | 16/04/2024 | 0 | WBSEDCL | 6.25 | 0 | 0 | 0
572 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16770 | Augmentation | NEW CONNECTION AT AMINABAD Z-II PH-I | 15/WBSEDCL-JJM | 16/04/2024 | 0 | WBSEDCL | 13.07 | 0 | 0 | 0
573 | MURSHIDABAD | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16770 | Augmentation | Formal work order for Augmentation of Aminabad Zone-II Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad under Murshidabad Division, PHE.Dte. | 773/MURD | 17/03/2023 | 881 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 726.14 | 161.01 | 22.17 | 35
574 | MURSHIDABAD | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16770 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Aminabad (Zone-II) & Katakobra Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 1762/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 35.37 | 10.11 | 100 | 66
575 | MURSHIDABAD | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-II) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16770 | Augmentation | Supply of different types C.I Specials at Islampur Sub-Divisional Store for different water supply schemes under Islampur sub-Division, under Murshidabad Division, P.H.E. Dte in the District of Murshidabad. | 2674/MURD | 25/09/2024 | 242 | MAKALI ENGINEERING CORPORATION | 32.46 | 8.09 | 50 | 100
576 | MURSHIDABAD | Berhampore Division I | DIAR FATEPUR PWSS , SM/16781 | New | Material Requisition To Resource Division | 61/BD-1/32 | 27/04/2023 | 0 | Resource Division | 38.25 | 0 | 0 | 0
577 | MURSHIDABAD | Berhampore Division I | DIAR FATEPUR PWSS , SM/16781 | New | Material Requisition To Resource Division | 304/BD-1/4 | 22/02/2024 | 0 | Resource Division | 19.21 | 0 | 0 | 0
578 | MURSHIDABAD | Berhampore Mechanical | DIAR FATEPUR PWSS , SM/16781 | New | Quotation for WBSEDCL for Diar Fatepur Application No- 3004544437 | 233/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 4.89 | 0 | 0 | 0
579 | MURSHIDABAD | Berhampore Mechanical | DIAR FATEPUR PWSS , SM/16781 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-III under DIAR FATEPUR ground water based water supply scheme under Block_ LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | 1160/MEDB | 15/05/2025 | 92 | SAMARPITA ENGINEERING | 10.93 | 0 | 0 | 0
580 | MURSHIDABAD | Berhampore Division I | DIAR FATEPUR PWSS , SM/16781 | New | DIAR FATHEPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 205/BD-I | 17/05/2023 | 1091 | ANKITA ENTERPRISE-GOPEJAN(NATHPARA) | 40.93 | 26.96 | 65.86 | 35
581 | MURSHIDABAD | Berhampore Division I | DIAR FATEPUR PWSS , SM/16781 | New | DIAR FATHEPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 450 cum) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | 606/BD-I | 02/08/2023 | 787 | M/S J.S ENTERPRISE | 362.92 | 155.37 | 42.81 | 30
582 | MURSHIDABAD | Berhampore Division I | DIAR FATEPUR PWSS , SM/16781 | New | DIAR FATHEPUR PWSS to accommodate FHTC Laying distribution system under Jal Jeevan Mission of Lalgola Block Murshidabad District under Berhampore Division-I, PHE Dte. (Part-B) | 973/BD-I | 18/10/2023 | 622 | SWAPAN DAS | 95.38 | 29.88 | 31.33 | 30
583 | MURSHIDABAD | Berhampore Division I | DIAR FATEPUR PWSS , SM/16781 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at DIAR FATEPUR PWSS under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidbad. | 839/BD-I | 23/06/2025 | 15 | B.M. ENGINEERING & CONSTRUCTION | 8.99 | 0 | 0 | 0
584 | MURSHIDABAD | Berhampore Division I | SHUKUR PUKUR PWSS , SM/16782 | New | Material Requisition To Resource Division | 61/BD-1/34 | 27/04/2023 | 0 | Resource Division | 8.65 | 0 | 0 | 0
585 | MURSHIDABAD | Berhampore Division I | SHUKUR PUKUR PWSS , SM/16782 | New | Material Requisition To Resource Division | 2096/BD-I/5 | 25/11/2024 | 0 | Resource Division | 3.7 | 0 | 0 | 0
586 | MURSHIDABAD | Berhampore Mechanical | SHUKUR PUKUR PWSS , SM/16782 | New | NEW CONNECTION AT SUKURPUKUR PH-1 | 183/WBSEDCL-JJM | 09/08/2024 | 0 | WBSEDCL | 10.55 | 0 | 0 | 0
587 | MURSHIDABAD | Berhampore Division I | SHUKUR PUKUR PWSS , SM/16782 | New | SHUKUR PUKUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 207/BD-I | 17/05/2023 | 865 | ABIDA CONSTRUCTION | 40.82 | 0 | 0 | 51
588 | MURSHIDABAD | Berhampore Division I | SHUKUR PUKUR PWSS , SM/16782 | New | SHUKUR PUKUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 612/BD-I | 02/08/2023 | 697 | NOVELTY CONSTRUCTION | 52.15 | 14.56 | 27.92 | 60
589 | MURSHIDABAD | Berhampore Division I | SHUKUR PUKUR PWSS , SM/16782 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SUKURPUKUR Water Supply Scheme(2nd TW Site) within Beldanga-II Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | 262/BD-I | 07/02/2025 | 183 | SINGHA AND CO. | 9 | 0 | 0 | 100
590 | MURSHIDABAD | Murshidabad Division | Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. , SM/16863 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.45 | 100 | 80
591 | MURSHIDABAD | Murshidabad Division | Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. , SM/16863 | Augmentation | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHAK RAMPRASAD and Dakshin Khanda Zone - IA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 2778/MURD | 01/09/2023 | 14 | SARKAR WATER SUPPLY AGENCY | 9.21 | 7.86 | 100 | 100
592 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. , SM/16863 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad under MEDB, PHE Dte. | 1146/MEDB | 14/05/2025 | 92 | M/S SAJAHAN CHOWDHURY | 24.86 | 0 | 0 | 0
593 | MURSHIDABAD | Murshidabad Division | Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. , SM/16863 | Augmentation | Augmentation of DAKSHIN KHANDA (ZONE - IA) PWSS under Jal Jeevan Mission of Bharatpur-II Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | 3146/MURD | 09/10/2023 | 815 | DHIRENDRANATH MONDAL | 457.09 | 101.96 | 22.31 | 10
594 | MURSHIDABAD | Murshidabad Division | Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. , SM/16863 | Augmentation | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at, Dakshinkhanda Zone-IA T.W-II, III, Zone-IB T.W-II, Dakshinkhanda Zone-II T.W- I, II Water Supply Scheme of Bharatpur-II Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 718/MURD | 25/03/2025 | 65 | MAMATA USHA ENTERPRISE | 58.95 | 0 | 0 | 0
595 | MURSHIDABAD | Murshidabad Division | Augmentation of Dakshin Kanda Zone- I A Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. , SM/16863 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I , II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dakshin Kanda Zone- I A Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Bharatpur - II Block under Murshidabad Division, P.H. Engineering Dte | 3782/MURD | 11/12/2023 | 630 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 0 | 100
596 | MURSHIDABAD | Berhampore Mechanical | JAGANNATHPUR AND ADJOINING NMOUJAS PWSS , SM/16816 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Jagannathpur ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | 3685/MEDB | 03/11/2023 | 92 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 22.23 | 0 | 0 | 0
597 | MURSHIDABAD | Murshidabad Division | JAGANNATHPUR AND ADJOINING NMOUJAS PWSS , SM/16816 | New | Material Requisition To Resource Division | 1075/MURD/19 | 19/04/2023 | 0 | Resource Division | 1.38 | 0 | 0 | 0
598 | MURSHIDABAD | Berhampore Mechanical | JAGANNATHPUR AND ADJOINING NMOUJAS PWSS , SM/16816 | New | NEW SERVICE CONNECTION AT JAGANNATHPUR PH II, ID304233698 | 262/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 5.04 | 0 | 0 | 0
599 | MURSHIDABAD | Berhampore Mechanical | JAGANNATHPUR AND ADJOINING NMOUJAS PWSS , SM/16816 | New | NEW SERVICE CONNECTION AT JAGANNATHPUR PH I, ID304233735 | 261/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 6.64 | 0 | 0 | 0
600 | MURSHIDABAD | Murshidabad Division | JAGANNATHPUR AND ADJOINING NMOUJAS PWSS , SM/16816 | New | JAGANNATHPUR PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | 3528/MURD | 10/11/2023 | 507 | SOUMYADIP MISRA | 367.89 | 74.99 | 20.38 | 25
601 | MURSHIDABAD | Murshidabad Division | JAGANNATHPUR AND ADJOINING NMOUJAS PWSS , SM/16816 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagannathpur and Burwan Zone- II Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Burwan Block under Murshidabad Division, P.H. Engineering Dte. | 3925/MURD | 21/12/2023 | 395 | NADIA TUBEWELLS | 18.43 | 0 | 0 | 100
602 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. , SM/17389 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-II under Nagar ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | 3714/MEDB | 03/11/2023 | 92 | A.G. ENTERPRISE | 22.35 | 0 | 0 | 0
603 | MURSHIDABAD | Murshidabad Division | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. , SM/17389 | Augmentation | Material Requisition To Resource Division | 1004/MURD/6 | 11/04/2023 | 0 | Resource Division | 24.92 | 0 | 0 | 0
604 | MURSHIDABAD | Murshidabad Division | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. , SM/17389 | Augmentation | Material Requisition To Resource Division | 1167/MURD/15 | 28/04/2023 | 0 | Resource Division | 20.22 | 0 | 0 | 0
605 | MURSHIDABAD | Murshidabad Division | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. , SM/17389 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Nagar Zone- II Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Khargram Block under Murshidabad Division, P.H. Engineering Dte | 3834/MURD | 14/12/2023 | 21 | MAMATA USHA ENTERPRISE | 23.59 | 16.34 | 100 | 50
606 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. , SM/17389 | Augmentation | POWER CONNECTION AT PWSS PH 2 Z 2 NAGAR ID 304250316 | 36/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 4.13 | 0 | 0 | 0
607 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. , SM/17389 | Augmentation | POWER CONNECTION AT PWSS NAGAR PH1 Z2 ID 304250315 | 35/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 7.14 | 0 | 0 | 0
608 | MURSHIDABAD | Murshidabad Division | Augmentation of Nagar Zone- II Water Supply Scheme Block - Khargram , Dist- Murshidabad. , SM/17389 | Augmentation | Augmentation of Ground Water Based Nagar Zone II PWSS of accommodate FHTC( 1909 Nos), Laying Distribution System, Laying Rising Main, Switch Room, Boundary Wall, 300 CUM OHR in Khargram Block within Murshidabad District under Murshidabad Division, PHE Dte. | 3299/MURD | 20/10/2023 | 773 | CREATIVE CONSTRUCTION | 394.26 | 75.2 | 19.07 | 10
609 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Alikpur Village (Code-315626), Mashimpur Village (Code-315627), Sekandarpur (Code-315628) Under Command Area Of Mashimpur Ground , SM/07720 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Alikpur Village (Code-315626), Mashimpur Village (Code-315627), Sekandarpur (Code-315628) Under Command Area Of Mashimpur Ground Water Supply Scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1440/BD-I | 04/09/2024 | 60 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 26.67 | 0 | 0 | 0
610 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Alikpur Village (Code-315626), Mashimpur Village (Code-315627), Sekandarpur (Code-315628) Under Command Area Of Mashimpur Ground , SM/07720 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Alikpur(Village code 315626), Mashimpur (Village code 315627),Sekandarpur(Village code 315628) under Mashimpur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | 1007/BD-I | 21/06/2021 | 30 | KAMIRUL SK AND CO. | 65.2 | 60.17 | 100 | 1
611 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-I , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18543 | Augmentation | Material Requisition To Resource Division | 1167/MURD/16 | 28/04/2023 | 0 | Resource Division | 18.84 | 0 | 0 | 0
612 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-I , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18543 | Augmentation | Continuation Order Hiring of Diesel driven Bolero/Equivalent four wheeler car for the official use of the Assistant Engineer-I under Office of the Executive Engineer, Mechanical/electrical Division, PHE Dte. in the district of Murshidabad. | 3360/AE/MEDB | 26/09/2023 | 182 | M/S SAJAHAN CHOWDHURY | 0.9 | 2.36 | 263.48 | 0
613 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-I , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18543 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-I Water Supply Scheme at Head work Site site at LALGOLA Block under Murshidabad Division, P.H. Engineering Dte | 3783/MURD | 11/12/2023 | 21 | NILAVA GHOSHAL (BUMBA) | 11.77 | 0 | 0 | 0
614 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-I , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18543 | Augmentation | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Block Bhagawangola-I & Lalgola of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Habaspur Water Supply Scheme, Bhandara Water Supply Scheme, Kantanagar Water Supply Scheme, Lalgola Water Supply Scheme. (Annexure-II) | 1928/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 8.78 | 2.23 | 100 | 100
615 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-I , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18543 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-I , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. under MEDB, PHE Dte. | 333/MEDB | 10/02/2025 | 89 | TARUN KUMAR BHATTACHARYA | 23.74 | 0 | 0 | 0
616 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-I , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18543 | Augmentation | Work order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Assistant Engineer, Lalbagh Sub-Division, P.H.E. Dte. For 176 Days i.e. form 08.04.2025 to 30.09.2025. (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order). (Vehicle No.WB58AX9595) | 133/LSD | 07/04/2025 | 176 | BARI ENTERPRISE | 0.86 | 1.1 | 127.83 | 0
617 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-I , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18543 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 0.04 | 1.15 | 100
618 | MURSHIDABAD | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS , SM/18581 | New | GHOLLA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | 647/BD-I | 08/08/2023 | 180 | M/S JHA CONSTRUCTION | 180.62 | 0 | 0 | 0
619 | MURSHIDABAD | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS , SM/18581 | New | Material Requisition To Resource Division | 201/BD-1/1 | 10/02/2024 | 0 | Resource Division | 25 | 0 | 0 | 0
620 | MURSHIDABAD | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS , SM/18581 | New | Material Requisition To Resource Division | 2096/BD-I/1 | 25/11/2024 | 0 | Resource Division | 29.76 | 0 | 0 | 0
621 | MURSHIDABAD | Berhampore Mechanical | GHOLLA AND ADJOINING MOUJAS PWSS , SM/18581 | New | NEW CONNECTION AT GHOLLA PH-I | 14/WBSEDCL-JJM | 16/04/2024 | 0 | WBSEDCL | 5.35 | 0 | 0 | 0
622 | MURSHIDABAD | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS , SM/18581 | New | GHOLLA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 660/BD-I | 08/08/2023 | 1000 | GITA CONSTRUCTION | 69.92 | 8.05 | 11.51 | 40
623 | MURSHIDABAD | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS , SM/18581 | New | GHOLLA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | 648/BD-I | 08/08/2023 | 689 | HARAPRASAD DAS | 118.61 | 0 | 0 | 65
624 | MURSHIDABAD | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS , SM/18581 | New | GHOLLA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART A) | 649/BD-I | 08/08/2023 | 1028 | RAJ KUMAR MONDAL | 404.58 | 0 | 0 | 50
625 | MURSHIDABAD | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS , SM/18581 | New | Allied works for upgradation ,Improvement and laying of "GHOLLA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART A)". | 1644/BD-I | 23/10/2024 | 223 | GITA CONSTRUCTION | 16.79 | 0 | 0 | 90
626 | MURSHIDABAD | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS , SM/18581 | New | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Gholla" ground water supply scheme in Beldanga-II Block, under Berhampore Division-I, P.H.E Dte. (Capacity-119 Cum/hr.) Type-1 - Fully Gravity System with RG Filter | 999/BD-I | 20/06/2024 | 730 | M/S GOUTAM CHAKRABORTY | 272.44 | 0 | 0 | 0
627 | MURSHIDABAD | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS , SM/18581 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHOLLA PWSS (3rd TW Site) under Jal Jeevan Mission in Beldanga-II Block under Berhampore Division-I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | 445/BD-I | 20/03/2025 | 15 | MARUTI CONSTRUCTION & CO. | 9.01 | 0 | 0 | 0
628 | MURSHIDABAD | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS , SM/18581 | New | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of GHOLLA PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 639/BD-I | 25/04/2025 | 60 | SAIF TRADERS | 19 | 0 | 0 | 0
629 | MURSHIDABAD | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS , SM/18581 | New | Fabrication and errection of Display Board including vinyl pasting ( 1.80 x 1.20 mtr) of scheme information by using logo and tag line of Jal Jevan Mission at different work sites in the district of Murshidabad under Berhampore Division-I,PHE Dte. | 446/BD-I | 15/03/2024 | 20 | SUMAN ENTERPRISE AND SUMAN AQUA | 7.18 | 6.69 | 100 | 100
630 | MURSHIDABAD | Berhampore Division I | GHOLLA AND ADJOINING MOUJAS PWSS , SM/18581 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHOLLA Water Supply Scheme(2nd TW Site) within Beldanga-II Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | 101/BD-I | 20/01/2025 | 180 | MAMATA USHA ENTERPRISE | 9.01 | 0 | 0 | 100
631 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, , SM/18775 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 4.25 | 100 | 100
632 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, , SM/18775 | Augmentation | Material Requisition To Resource Division | 1210/MURD/31 | 02/05/2023 | 0 | Resource Division | 64.61 | 0 | 0 | 0
633 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, , SM/18775 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II,III ,IV & V ,Zone-II under ARJUNPUR ground water based water supply scheme under Block_ FARAKKA Dist. - Murshidabad under MEDB, PHE Dte. | 3865/MEDB | 07/11/2023 | 92 | WEST BENGAL ENGINEERING CO. | 52.01 | 0 | 0 | 0
634 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, , SM/18775 | Augmentation | NEW SERVICE CONNECTION AT ARJUNPUR PWSS Z2 PH1 ID 304391006 |  | 27/11/2024 | 0 | WBSEDCL | 4.49 | 0 | 0 | 0
635 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, , SM/18775 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 300 & 900 cum), Sinking of Tube Well and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Arjunpur Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | 3177/MURD | 11/10/2023 | 730 | M/S. CHAKRABORTY & COMPANY | 2041.06 | 0 | 0 | 35
636 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-II ) PWSS, , SM/18775 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 4.46 | 100 | 100
637 | MURSHIDABAD | Murshidabad Division | Augmentation of Natial Rajnagar Zone-III Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/18777 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 2.75 | 100 | 1
638 | MURSHIDABAD | Murshidabad Division | Augmentation of Natial Rajnagar Zone-III Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/18777 | Augmentation | Material Requisition To Resource Division | 1219/MURD/42 | 03/05/2023 | 0 | Resource Division | 27.39 | 0 | 0 | 0
639 | MURSHIDABAD | Murshidabad Division | Augmentation of Natial Rajnagar Zone-III Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/18777 | Augmentation | Material Requisition To Resource Division | 526/MURD/07 | 19/02/2024 | 0 | Resource Division | 18.07 | 0 | 0 | 0
640 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Natial Rajnagar Zone-III Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/18777 | Augmentation | NEW SERVICE CONNECTION AT NATIAL RAJA NAGAR Z3 PH 1 ID 304516689 |  | 27/11/2024 | 0 | WBSEDCL | 9.36 | 0 | 0 | 0
641 | MURSHIDABAD | Murshidabad Division | Augmentation of Natial Rajnagar Zone-III Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/18777 | Augmentation | Augmentation of NATIAL RAJANAGAR ZONE-I ,II,& III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | 2724/MURD | 29/08/2023 | 765 | M/S. MOHAN LAL JAIN | 2092.12 | 232.04 | 29.9 | 56
642 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Natial Rajnagar Zone-III Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/18777 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Natialrajanagar Zone-III Piped water supply scheme Block_Jalangi Dist_Murshidabad under MEDB PHE Dte. " | 352/MEDB | 10/02/2025 | 89 | M/S SAJAHAN CHOWDHURY | 45.41 | 0 | 0 | 25
643 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Natial Rajnagar Zone-III Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/18777 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Natial Rajnagar Zone-III Pipe Water Supply Scheme Block - Jalangi District - Murshidabad under MEDB, PHE Dte. | 319/MEDB | 10/02/2025 | 291 | ORIENTAL ENGINEERING CO. | 45.45 | 0 | 0 | 20
644 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. , SM/19122 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-III & IV under Hasimpur ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | 1876/MEDB | 16/06/2023 | 92 | ABHISEK ENGINEERING CONCERN | 20.73 | 0 | 0 | 0
645 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. , SM/19122 | Augmentation | Material Requisition To Resource Division | 1210/MURD/30 | 02/05/2023 | 0 | Resource Division | 158.82 | 0 | 0 | 0
646 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. , SM/19122 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 0 | 10
647 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. , SM/19122 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Hasimpur PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 185/MURD | 18/01/2024 | 683 | SAMIRAN KUMAR CHAKRABORTY | 485.31 | 24.23 | 4.99 | 60
648 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. , SM/19122 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 90 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for HASIMPUR Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division, PHE Dte. | 964/MURD | 30/04/2025 | 60 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 37.67 | 0 | 0 | 0
649 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HASIMPUR PIPED WATER SUPPLY SCHEME. , SM/19122 | Augmentation | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 0 | 20
650 | MURSHIDABAD | Murshidabad Division | Augmentation of Jot Kamal Zone-III Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/18471 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.68 | 100 | 100
651 | MURSHIDABAD | Murshidabad Division | Augmentation of Jot Kamal Zone-III Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/18471 | Augmentation | Material Requisition To Resource Division | 1219/MURD/35 | 03/05/2023 | 0 | Resource Division | 45.55 | 0 | 0 | 0
652 | MURSHIDABAD | Murshidabad Division | Augmentation of Jot Kamal Zone-III Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/18471 | Augmentation | Augmentation of Ground Water Based JOT KAMAL (ZONE-I), JOTKAMAL (Zone-II) & JOTKAMAL (Zone-III) PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | 2643/MURD | 23/08/2023 | 587 | M/S NIRAPADA BHATTACHARJEE | 1194.05 | 0 | 0 | 10
653 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Jot Kamal Zone-III Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/18471 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Jot Kamal Zone-III Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad under MEDB, PHE Dte. | 317/MEDB | 10/02/2025 | 89 | M/S SAJAHAN CHOWDHURY | 34.06 | 0 | 0 | 0
654 | MURSHIDABAD | Berhampore Mechanical | Source Augumentation& Functional Household Tap Connections (FHTC) of Mouza Radhakrishanapur, Malatipur, Khalifabaj, Sahabazpur, Paharpur, Krishnapur (314148, 314149, 314150, 314151, 314153 ) of Lalgola Under Ground Water Based Water Supply Scheme For Arse , SM/19019 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under Lalgola ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | 4340/MEDB | 29/12/2023 | 91 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 21.62 | 0 | 0 | 0
655 | MURSHIDABAD | Murshidabad Division | BAHAGALPUR PIPED WATER SUPPLY SCHEME. , SM/18516 | New | Material Requisition To Resource Division | 1219/MURD/37 | 03/05/2023 | 0 | Resource Division | 50.34 | 0 | 0 | 0
656 | MURSHIDABAD | Berhampore Mechanical | BAHAGALPUR PIPED WATER SUPPLY SCHEME. , SM/18516 | New | NEW CONNECTION BAHAGALPUR PH-1 |  | 06/03/2024 | 0 | WBSEDCL | 4.25 | 0 | 0 | 0
657 | MURSHIDABAD | Berhampore Mechanical | BAHAGALPUR PIPED WATER SUPPLY SCHEME. , SM/18516 | New | NEW CONNECTION BHAGALPUR PH-II | 411/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 3.3 | 0 | 0 | 0
658 | MURSHIDABAD | Berhampore Mechanical | BAHAGALPUR PIPED WATER SUPPLY SCHEME. , SM/18516 | New | BAHAGALPUR PH-I NEW CONNECTION | 424/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 4.25 | 0 | 0 | 0
659 | MURSHIDABAD | Berhampore Mechanical | BAHAGALPUR PIPED WATER SUPPLY SCHEME. , SM/18516 | New | NEW CONNECTION BAHAGALPUR PH-III | 412/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 3.55 | 0 | 0 | 0
660 | MURSHIDABAD | Murshidabad Division | BAHAGALPUR PIPED WATER SUPPLY SCHEME. , SM/18516 | New | BAHAGALPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE. Dte. | 3053/MURD | 29/09/2023 | 731 | ASTRA | 606.64 | 170.86 | 28.17 | 41
661 | MURSHIDABAD | Murshidabad Division | BAHAGALPUR PIPED WATER SUPPLY SCHEME. , SM/18516 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 8.44 | 100 | 100
662 | MURSHIDABAD | Murshidabad Division | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. , SM/18687 | New | Material Requisition To Resource Division | 1219/MURD/32 | 03/05/2023 | 0 | Resource Division | 22.44 | 0 | 0 | 0
663 | MURSHIDABAD | Berhampore Mechanical | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. , SM/18687 | New | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under SRIKANTABATI, PART B ground water based water supply scheme under Block_ RAGHUNATHGANJ-I Dist. - Murshidabad under MEDB, PHE Dte. | 586/MEDB | 31/01/2024 | 90 | M/S. SUPER CONSTRUCTION | 35.75 | 0 | 0 | 0
664 | MURSHIDABAD | Murshidabad Division | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. , SM/18687 | New | Construction of Ground Water Based Srikantabati Part B PWSS of accommodate FHTC(2619 Nos), Laying Distribution System, Laying Rising Main, 400 CUM OHR, Switch Room, Boundary Wall in Raghunathganj- I Block within Murshidabad District under Murshidabad Division, PHE Dte. | 2675/MURD | 24/08/2023 | 365 | KEYA CONSTRUCTION | 437.95 | 0 | 0 | 0
665 | MURSHIDABAD | Murshidabad Division | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. , SM/18687 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SRIKANTABATI PART B & JOTKAMAL ZONE -II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 3395/MURD | 01/11/2023 | 21 | KALACHAND DAS | 18.4 | 0 | 0 | 100
666 | MURSHIDABAD | Murshidabad Division | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. , SM/18687 | New | Material Requisition To Resource Division | 495/MURD/01 | 15/02/2024 | 0 | Resource Division | 16.13 | 0 | 0 | 0
667 | MURSHIDABAD | Murshidabad Division | SRIKANTABATI PART B PIPED WATER SUPPLY SCHEME. , SM/18687 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 6.43 | 100 | 100
668 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME , SM/16398 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 2.8 | 100 | 100
669 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME , SM/16398 | Augmentation | Material Requisition To Resource Division | 1210/MURD/19 | 02/05/2023 | 0 | Resource Division | 2.25 | 0 | 0 | 0
670 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME , SM/16398 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I II & III ,Zone-II under BIRENDRANAGAR ground water based water supply scheme under Block_ RAGHUNATHGANJ-II Dist. - Murshidabad under MEDB, PHE Dte. | 4332/MEDB | 29/12/2023 | 91 | BHAGIRATHI JUTE AND HOLDINGS PVT LTD | 32.03 | 0 | 0 | 0
671 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME , SM/16398 | Augmentation | Allied work in connection with Augmentation & Rejuvenation of Birendranagar (Zone-II) Pipe water supply scheme, Block- Raghunathganj-II, District-Murshidabad, Under Murshidabad Division P.H.E Dte. | 1842/MURD | 25/06/2024 | 30 | M.R. ENTERPRISE (MD. HASANUZZAMAN) | 17.49 | 14.46 | 100 | 100
672 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME , SM/16398 | Augmentation | Laying of Distribution System with FHTC to 560nos household, Rising Main, OHR Repair of 90 cum capacity, Extension of Boundary Wall &Two Nos. of Pump House Repair for Augmentation of Birendranagar (Zone-II) Pipe water supply scheme in Raghunathganj-II Block under Murshidabad Division, PHE.Dte (i)Amount for Construction Part: 15,60,995.00/ (ii)Amount for Pipeline Part: 57,32,731.00/- (Attached as Annexure -V) | 656/MURD | 06/03/2023 | 900 | HARUN ALL RASHID & BROTHERS | 72.21 | 20.31 | 28.13 | 40
673 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-II) PIPED WATER SUPPLY SCHEME , SM/16398 | Augmentation | Renovation of Existing AIRP (Capacity 15 Cu.M/hr) for changing of filter media of 1 no Polishing Unit (2.50 m dia x 1.5 m HOS) & 1 no Primary Unit (2.50 m dia x 2.00 m HOS) and painting all vessel, pipes etc. all complete at Birendranagar (Zone-II) W/S Scheme under Murshidabad Division P.H.Engineering Dte. | 618/MURD | 28/02/2024 | 240 | S. DUTTA | 16.94 | 4.14 | 20.94 | 100
674 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18831 | Augmentation | Inter connection with Tubewell and rising main etc. at Head work sites of Katakopra Water Supply scheme (Katakopra Z-I & Z-II both) and allied works under Islampur Sub - Division,Murshidabad Division P.H.E Dte. In the district of Murshidabad | 43/ISD | 28/01/2022 | 60 | CLASSIC CONSTRUCTION (ANJAN CHATTERJEE) | 4.33 | 4.25 | 100 | 100
675 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18831 | Augmentation | Material Requisition To Resource Division | 1167/MURD/35 | 28/04/2023 | 0 | Resource Division | 198.12 | 0 | 0 | 0
676 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18831 | Augmentation | Material Requisition To Resource Division | 1167/MURD/33 | 28/04/2023 | 0 | Resource Division | 22 | 0 | 0 | 0
677 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18831 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KATAKOBRA ZONE-I&II Water Supply Scheme and Gokul Chak Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 832/MURD | 15/03/2024 | 21 | NADIA TUBEWELLS | 11.78 | 0 | 0 | 100
678 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18831 | Augmentation | NEW CONNECTION AT KATAKOBRA Z-I PH-II |  | 13/11/2024 | 0 | WBSEDCL | 5.81 | 0 | 0 | 0
679 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18831 | Augmentation | NEW CONNECTION AT KATAKOBRA Z-I PH-I |  | 13/11/2024 | 0 | WBSEDCL | 6.63 | 0 | 0 | 0
680 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18831 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II , Zone-I under Katakobra ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | 3666/MEDB | 03/11/2023 | 666 | HARA PROSAD DAS | 22.58 | 0 | 0 | 15
681 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18831 | Augmentation | Augmentation KATAKOPRA (Zone -I) under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. (PART - B) | 3031/MURD | 27/09/2023 | 600 | M/S HANNAN KHAN CONSTRUCTION | 300.03 | 44.39 | 14.79 | 15
682 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18831 | Augmentation | Laying Distribution System for Augmentation of Katakopra Zone -I & II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkol Block of Murshidabad District under Murshidabad Division,PHE.Dte. | 2994/MURD | 13/11/2024 | 450 | M/S. BIMALENDU BOSE | 389.64 | 0 | 0 | 0
683 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18831 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Aminabad (Zone-II) & Katakobra Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 1762/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 35.37 | 21.67 | 100 | 66
684 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KATAKOBRA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/18831 | Augmentation | Augmentation of KATAKOPRA (Zone-I) PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE Dte. (Part-A) | 3050/MURD | 29/09/2023 | 825 | M/S. BIMALENDU BOSE | 466.19 | 207 | 44.44 | 90
685 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/18602 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KASHIPUR ZONE-I Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 531/BD-I | 27/07/2023 | 10 | TECHVISION | 2.87 | 2.87 | 100 | 100
686 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/18602 | Augmentation | Material Requisition To Resource Division | 201/BD-1/7 | 10/02/2024 | 0 | Resource Division | 101.3 | 0 | 0 | 0
687 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/18602 | Augmentation | NEW CONNECTION AT KASHIPUR Z-I PH-I | 409/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 5.27 | 0 | 0 | 0
688 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/18602 | Augmentation | Augmentation of Kashipur Zone-I Piped water supply scheme to accommodate construction of laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE Dte. | 668/BD-I | 09/08/2023 | 900 | MAMON ENTERPRISE AND CONSTRUCTION | 236.94 | 202.92 | 85.64 | 35
689 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/18602 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 126 Cum/hr.) with allied work at Kashipur Zone-I Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | 1206/BD-I | 26/07/2024 | 300 | M/S SAJAHAN CHOWDHURY | 35.07 | 0 | 0 | 80
690 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/18602 | Augmentation | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of KASHIPUR ZONE-I" ground water supply scheme in BELDANGA-II Block, under Berhampore Division-I, P.H.E Dte(Capacity-30.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing | 995/BD-I | 20/06/2024 | 365 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 143.92 | 0 | 0 | 60
691 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/18602 | Augmentation | KASHIPUR ZONE-I PROPOSED PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1176/BD-I | 25/07/2024 | 180 | HI-TECH ENGINEERS CO-OPERATIVE & CONSTRUCTION SOCIETY LTD. | 20.39 | 0 | 0 | 100
692 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/18602 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of KASHIPUR ZONE-I (Part-B) PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 722/BD-I | 15/05/2025 | 60 | PRAVAT KUMAR GHOSH | 19 | 0 | 0 | 0
693 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/18602 | Augmentation | Construction of Boundary wall at 2nd & 3rd Tube Well Site of KASHIPUR ZONE -I PWSS(Part-A) under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 725/BD-I | 15/05/2025 | 60 | HI-TECH ENGINEERS CO-OPERATIVE & CONSTRUCTION SOCIETY LTD. | 19.02 | 0 | 0 | 0
694 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/18602 | Augmentation | Balance work for Improvement Existing AIRP of (Capacity 126 Cum/hr) with allied work at Kashipur Zone-I water supply scheme under JJM within Beldanga-II under Berhampore Division-I, PHE Dte. In the district of Murshidabad. | 768/BD-I | 22/05/2025 | 45 | M/S SAJAHAN CHOWDHURY | 58.23 | 0 | 0 | 0
695 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/18602 | Augmentation | Balance work for Laying of distribution pipeline of Kashipur Zone-I and allied works under JJM within Beldanga-II Block under Berhampore Division-I, PHE Dte. in the district of Murshidabad. | 848/BD-I | 23/06/2025 | 90 | SOUNAK ENTERPRISE | 84.84 | 0 | 0 | 0
696 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/18602 | Augmentation | Repair And Renovation Works Of OHR (550 Cum) forKasipur Zone-I water supply scheme of Beldanga-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | 1068/BD-I | 21/11/2023 | 30 | CHAND ENTERPRISE | 9.22 | 9.03 | 100 | 100
697 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/18602 | Augmentation | KASHIPUR ZONE-I EXISTING PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1686/BD-I | 28/10/2024 | 60 | CHAND ENTERPRISE | 22.7 | 0 | 0 | 100
698 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/18602 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KASHIPUR ZONE-I (PART-B) Water Supply Scheme (TW-I & II Site) within Beldanga-II Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | 99/BD-I | 20/01/2025 | 240 | SUJIT KUMAR SAHA | 18.02 | 0 | 0 | 100
699 | MURSHIDABAD | Berhampore Mechanical | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Providing Electrical Equipment for 11/0.433 KV Sub-station (LT Bulk & HT Bulk) at Intake and Water Treatment Plant under Augmentation of Central Sector, Part-I Surface Water Based W/S Scheme, Dist. Murshidabad | 973/MEDB | 15/03/2024 | 184 | CONCORD ENGINEERING | 239.82 | 0 | 0 | 0
700 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Material Requisition To Resource Division | 790/BD-I | 09/05/2024 | 0 | Resource Division | 478.82 | 0 | 0 | 0
701 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Material Requisition To Resource Division | 1462/BD-I | 05/09/2024 | 0 | Resource Division | 123.2 | 0 | 0 | 0
702 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Material Requisition To Resource Division | 1148/BD-I | 18/07/2024 | 0 | Resource Division | 817.87 | 0 | 0 | 0
703 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Material Requisition To Resource Division | 1412/BD-I | 30/08/2024 | 0 | Resource Division | 1050.72 | 0 | 0 | 0
704 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Material Requisition To Resource Division | 1341/BD-I/2 | 20/08/2024 | 0 | Resource Division | 246.17 | 0 | 0 | 0
705 | MURSHIDABAD | Berhampore Mechanical | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | SHIFTING OF DTR 25KVA AT MANIKNAGAR CID 860311628 |  | 03/09/2024 | 0 | WBSEDCL | 0.71 | 0 | 0 | 0
706 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Safety Checking of 9 (Nine) nos Over Head Reservoit at various places of Murshidabad District under P.H.Engineering Department, Govt of West Bengal. | BP-2024-25-259 | 27/11/2024 | 0 | SRCC NIT DURGAPUR | 3.54 | 0 | 0 | 0
707 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | EXECUTION OF CLEAR WATER RISING MAIN, OVERHEAD RESERVOIRS WITH ALLIED WORKS, DISTRIBUTION NETWORK WITH FHTC COMPLETE FOR AUGMENTATION OF SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR CENTRAL SECTOR PART-I OF MURSHIDABAD DISTRICT | 387/BD-I | 12/03/2024 | 849 | M/S MOHAN LAL JAIN | 7952.07 | 1331.31 | 16.74 | 60
708 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Withdrawing and Laying of different dia. D.I. pipe along NH12 from Bhakuri to Talbagan more with connection work to Rising Mains of Central Sector Part-II near Bhakuri more and Balarampur Halt Station under Berhampore Division-I, P.H.E. Dte. | 1469/BD-I | 06/09/2024 | 240 | SAMBHUNATH ROY | 53.6 | 0 | 0 | 80
709 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer-II,BD-I,PHE Dte. [Period for 05.07.2024 to 30.06.2025.] Car No-WB58CC 9776 | 1082/BD-I | 04/07/2024 | 365 | MD MUKLESUR RAHAMAN | 1.81 | 4.79 | 264.06 | 0
710 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Allied Work for Supply of different types of specials in connection with execution of Clear Water Rising Main, Overhead Reservoirs, Distribution Network Complete under JJM for Augmentation of Surface Water Based Piped Water Supply Scheme of CENTRAL SECTOR PART-II under BERHAMPORE DIVISION - I in the district of MURSHIDABAD | 2324/BD-I | 26/12/2024 | 30 | ECO PROTECTION ENGINEERS PVT LTD. | 35.3 | 0 | 0 | 0
711 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Survey, Investigation, Planning, Design, Execution commissioning and completion in all respect of all Civil, Electrical and Mechanical work of 11 MLD capacity conventional water treatment plant (WTP) using River Bhagirathi as source including Intake Structures, Raw Water rising main, and Clear Water rising main upto boundary limit of WTP for the Augmentation of surface water based piped water supply scheme for Murshidabad Central Sector (Part-I) in Murshidabad District under PHE Dte. including 12 (Twelve) months of Operation and Maintenance after successful completion of 3 (Three) months Trial Run | 386/BD-I | 12/03/2024 | 549 | CONCORD ENGINEERING | 3354.92 | 0 | 0 | 0
712 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Rejuvanation of 54.11 MLD Capacity Water Treatment Plant (Inlet well ,Flush Mixture,Clarifoculator, Chemical Dosing and Filter House ) at Central Sector Part-II UNDER BERHAMPORE DIVISION - I , IN THE DISTRICT MURSHIDABAD , PHE DTE . | 385/BD-I | 12/03/2024 | 477 | CONCORD ENGINEERING | 296.54 | 0 | 0 | 60
713 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Allied Work for Supply of different types of specials in connection with execution of Clear Water Rising Main, Overhead Reservoirs, Distribution Network Complete under JJM for Augmentation of Surface Water Based Piped Water Supply Scheme of CENTRAL SECTOR PART-I under BERHAMPORE DIVISION - I in the district of MURSHIDABAD. | 2269/BD-I | 16/12/2024 | 30 | M/S MOHAN LAL JAIN | 36.33 | 0 | 0 | 0
714 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Renovation and upgradation of all existing infrastructures (Filter House Building,Chemical House Building,Laboratory/SCADA Building,Clear Water Pump House, Clear Water Reservoir, Outhouse, Staff Quarters and allied Works) of Augumentation of Central Sector Part-II under JJM under Berhampore Division-I, P.H.E Dte. | 2334/BD-I | 30/12/2024 | 45 | CONCORD ENGINEERING | 59.47 | 0 | 0 | 0
715 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Improvement of existing Pump House & Construction of Boundary Wall at different head work sites for Augmentation of different PWSS within MJ & Berhampore Block under Central Sector Part-I under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad. | 1610/BD-I | 03/10/2024 | 240 | M/S J.S ENTERPRISE | 85.47 | 0 | 0 | 40
716 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Renovation and upgradation of all existing infrastructures (Sludge Sump House, Sludge pond, Substation Building,Boundary Wall, Clariflocculator, Flash Mixer, Inlet Well and allied Works) of Augumentation of Central Sector Part-II under JJM under Berhampore Division-I, P.H.E Dte. | 2333/BD-I | 30/12/2024 | 45 | CONCORD ENGINEERING | 42.16 | 0 | 0 | 0
717 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Continuation Work order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer-II,BD-I,PHE Dte. [Period for 01.07.2025 to 31.10.2025.] Car No-WB58CC 9776 | 1082/BD-I | 30/06/2025 | 123 | MD MUKLESUR RAHAMAN | 0.6 | 0 | 0 | 0
718 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Consultancy for Engineering support of six numbers of Suspended OHR constructed in stages initially during 2011-2012 and after 5-6 years gap in Berhampore Division-I of PHE Dte. based on Joint Inspection, Non-destructive Test and subsequent Structural Analysis of their As Built Numerical Models in FEM Platform including Seismic Considerations. | 959/BD-I | 22/07/2025 | 60 | JADAVPUR UNIVERSITY | 49.21 | 0 | 0 | 0
719 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Rejuvanation of of 30.33 MLD Capacity Water Treatment Plant (Inlet well ,Flush Mixture ,Clarifoculator , Chemical Dosing and Filter House ) at Central Sector Part- I (At Lalbagh) Under Berhampore Division - I , In The District Murshidabad , PHE Dte . | 391/BD-I | 12/03/2024 | 540 | DHIMAN SARKAR | 270.68 | 0 | 0 | 80
720 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Repair and overhauling at filter beds including supply and filling of filter media along with allied works at R.G filter bed of Surface Water Based water supply scheme in Central Sector Part-II under Berhampore Division-I ,P.H.E Dte. | 384/BD-I | 12/03/2024 | 450 | CONCORD ENGINEERING | 94.92 | 18.62 | 16.86 | 60
721 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Repair and overhauling at filter beds including supply and filling of filter media along with allied works at R.G filter bed of Surface Water Based water supply scheme in Central Sector Part-I under Berhampore Division-I ,P.H.E Dte. | 389/BD-I | 12/03/2024 | 30 | DHIMAN SARKAR | 55.21 | 53.27 | 100 | 100
722 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Upgradation of all existing infrastructures (Sludge Sump House, Sludge pond, Substation Building, Boundary Wall, Clariflocculator, Flash Mixer, Inlet Well and allied Works) of Augmentation of Central Sector Part-I under JJM under Berhampore Division-I, P.H.E Dte | 1614/BD-I | 03/10/2024 | 30 | DHIMAN SARKAR | 40.99 | 10.85 | 20.94 | 100
723 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Road crossing by Jack Pushing 600mm dia. M.S. pipe to carry 350mm dia. M.S. along NH12 at Chaltia more with connection work to Rising Mains of Central Sector Part-II near Bhakuri more and Balarampur Halt Station under Berhampore Division-I, P.H.E. Dte. | 1466/BD-I | 06/09/2024 | 30 | SAMBHUNATH ROY | 90.58 | 90.58 | 100 | 100
724 | MURSHIDABAD | Berhampore Division I | Augmentation of surface water based piped water supply scheme for arsenic affected areas of Murshidabad District (Central Sector) (Part-I & Part-II) , SM/19189 | Augmentation | Upgradation of all existing infrastructures (Filter House Building,Chemical House Building, Laboratory/SCADA Building,Clear Water Pump House, Clear Water Reservoir, Outhouse, Staff Quarters and allied Works) of Augumentation of Central Sector Part-I under JJM under Berhampore Division-I, P.H.E Dte | 1613/BD-I | 03/10/2024 | 45 | DHIMAN SARKAR | 91.23 | 0 | 0 | 100
725 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pirojpur & Madhurkol (314723 & 314724) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( , SM/07913 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevanMission andJalSwapna under command area of village MadhurKol (Village code 314724) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723334 in the District of Murshidabad. | 88/MURD | 08/01/2021 | 60 | GOUTAM CHAKRABORTY | 44.07 | 0 | 0 | 1
726 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pirojpur & Madhurkol (314723 & 314724) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( , SM/07913 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Pirojpur (Village code 314723) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723334 in the District of Murshidabad. | 87/MURD | 08/01/2021 | 60 | GOUTAM CHAKRABORTY | 23.78 | 10.81 | 100 | 100
727 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pirojpur & Madhurkol (314723 & 314724) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( , SM/07913 | Retrofitting | Extension of Distribution UPVC pipeline for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Pirojpur (Village code 314723) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723334 in the District of Murshidabad. | 1197/MURD | 10/05/2022 | 30 | KESHAB CHANDRA DAS | 7.33 | 7.29 | 100 | 1
728 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Komnagar ground water supply scheme , SM/07223 | Retrofitting | Formal Work order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Komnagar (Village code 314572) under Komnagar Ground Water Supply Scheme in Raninagar-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-08) | 968/BD-I | 07/06/2021 | 180 | S.P CONSTRUCTION | 49.3 | 34.35 | 69.68 | 0
729 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Komnagar ground water supply scheme , SM/07223 | Retrofitting | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Komnagar ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1244/BD-I | 30/07/2024 | 30 | R.S. CONSTRUCTION | 9.36 | 0 | 0 | 0
730 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Sitesnagar ground water supply scheme , SM/07226 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Siteshnagar (Village code 314238) under Lalgola Ground Water Supply Scheme in Lalgola Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-10) | 1142/BD-I | 07/07/2021 | 180 | KAMIRUL SK AND CO. | 70.73 | 62 | 87.65 | 0
731 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Sitesnagar ground water supply scheme , SM/07226 | Retrofitting | Balance & Allied Work for JAL JEEVAN MISSION under command area of Sitesnagar ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1448/BD-I | 04/09/2024 | 60 | GOUTAM KUMAR CHAUDHURI | 16.63 | 0 | 0 | 0
732 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pashupatibati & Bolpara ( 315948 & 315952 ) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis , SM/07925 | Retrofitting | Continuation Work order for Hiring of 1 no of Car for official use of the AE KSD PHE DTE. Period 01.06.2021 to 03.07.2021. Work Order No 185 / BSD. DATE 30.07.2020 | 209-MSD/2022-23 | 15/07/2022 | 0 | SISIR KUMAR DE | 0.42 | 0 | 0 | 0
733 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pashupatibati & Bolpara ( 315948 & 315952 ) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis , SM/07925 | Retrofitting | Continuation Work order for Hiring of 1 no of Car for official use of the AE KSD PHE DTE. Period 01.07.2021 to 03.01.2022. Work Order No 230 / BSD. DATE 02.07.2021 | 209-MSD/2022-23 | 15/07/2022 | 0 | SISIR KUMAR DE | 1.84 | 0 | 0 | 0
734 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pashupatibati & Bolpara ( 315948 & 315952 ) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis , SM/07925 | Retrofitting | Continuation Work order for Hiring of 1 no of Car for official use of the AE KSD PHE DTE. Period 01.01.2022 to 31.03.2022. Work Order No 303 / BSD. DATE 15.12.2021 | 209-MSD/2022-23 | 15/07/2022 | 0 | SISIR KUMAR DE | 0.83 | 0 | 0 | 0
735 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pashupatibati & Bolpara ( 315948 & 315952 ) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis , SM/07925 | Retrofitting | RESTORATION OF DAMAGED BALCK TOP AND ROAD FLANK OCCURED DUE TO CUTTING OF ROAD STRETCHES FOR LAYING OF PHE PIPELINE AT GUNANADABATI WATER SULLY SCHEME UNDER KANDI SUB DIVISION. | 267-MSD/2023-24 | 19/09/2023 | 0 | EXECUTIVE ENGINEER, PWD, BERHAMPORE DIVISION-I | 4.38 | 0 | 0 | 0
736 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pashupatibati & Bolpara ( 315948 & 315952 ) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis , SM/07925 | Retrofitting | Providing Functional Household Tap Connections (FHTC) (241 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Pashupatibati & Bolpara ( Village Code -315948, 315966, 315952) under Panchhipara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block under Murshidabad Division P.H.E Dte. | 3437/MURD | 03/11/2023 | 30 | NATIONAL CONSTRUCTION (MD ASRAFUL SK) | 9.36 | 2.5 | 26.72 | 70
737 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pashupatibati & Bolpara ( 315948 & 315952 ) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis , SM/07925 | Retrofitting | Construction of balance portion office cum godown including sanitary and plumbing work at H.W. Site and laying of UPVC pipeline in between node point 77 to 78, 78 to 89 & 78 to 79 of Pachhipara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 3117/MURD | 05/10/2023 | 30 | M.I CONSTRUCTION | 13.74 | 13.58 | 100 | 70
738 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pashupatibati & Bolpara ( 315948 & 315952 ) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis , SM/07925 | Retrofitting | Continuation Work Order for the work of Hiring of Maxi cab (Non- Air Condition, Bharat Stage III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 05(five)months i.e. 01.10.2024 TO 27.02.2025. VEHICLE NO - WB57F2352 | 136/KSD | 19/09/2024 | 150 | H.MONDAL CONSTRUCTION | 0.87 | 1.95 | 224.41 | 0
739 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Balbalpara (313852) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) , SM/07511 | Retrofitting | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Samserganj Block(Kanchantala, Dogachi-nowpara,Bhasaipaikar,Gagingar,Tinpakuria & Bogdadnagar ) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (PART-A) | 126 /JSD | 26/05/2021 | 30 | IMAGIN COMMUNICATION | 2.38 | 2.38 | 100 | 0
740 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Balbalpara (313852) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) , SM/07511 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BALBALPARA (Village Code 313852) under DOGACHHI (ZONE-II) Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 927 of 21-22 by EE MURD | 20-MSD/22-23 | 20/04/2022 | 0 | ARABINDA GHOSH | 41.65 | 0 | 0 | 0
741 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Balbalpara (313852) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) , SM/07511 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Balbalpara ( Village Code -313852) under Dogachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005019105) . | 634/MURD | 18/02/2021 | 60 | ARABINDA GHOSH | 41.65 | 0 | 0 | 0
742 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Balbalpara (313852) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) , SM/07511 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission ) and under command area of village of Alamsahi ( Village Code -313853) under Dogachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005019105). | 574/MURD | 09/02/2021 | 60 | BARUN DUTTA | 6.31 | 5.14 | 100 | 0
743 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) , SM/07672 | Retrofitting | Replacement of media for Renovation of I.E Plant at Arjunpur W/S Scheme, of Jangipur Sub-Division under Murshidabad Division P.H.E.Dte. | 2941/MURD | 03/11/2022 | 20 | SUMAN ENTERPRISE AND SUMAN AQUA | 10.21 | 8.65 | 100 | 1
744 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) , SM/07672 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID - ER-MLDT-2022-WL-24 | 399-MSD/22-23 | 18/11/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 2.57 | 0 | 0 | 0
745 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) , SM/07672 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID - ER-MLDT-2022-WL-19 | 399-MSD/22-23 | 18/11/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 6.19 | 0 | 0 | 0
746 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) , SM/07672 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) of Mouja Bhabanipur (Village Code-313820), of Arjunpur &adjoining mouja under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District under Murshidabad Division P.H.E Dte. (Scheme ID-0005184170) | 2086/MURD | 27/07/2022 | 120 | DIPAYAN DEY | 88.99 | 0 | 0 | 0
747 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) , SM/07672 | Retrofitting | Continuation work order for Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Shakopara Station to Ballalpur Station (TP NO 247/16 & 247/18) at Bhabanipur mouza & Connecting with existing 140 mm dia UPVC distribution main line of Arjunpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | 1607/MURD | 09/06/2023 | 60 | PRADIP KUMAR DAS | 3.68 | 3.68 | 100 | 0
748 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) , SM/07672 | Retrofitting | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Shakopara Station to Ballalpur Station (TP NO 247/16 & 247/18) at Bhabanipur mouza & Connecting with existing 140 mm dia UPVC distribution main line of Arjunpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | 508/MURD | 23/02/2022 | 60 | PRADIP KUMAR DAS | 36.8 | 36.8 | 100 | 0
749 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhabanipur (313820) of Arjunpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-I) , SM/07672 | Retrofitting | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Shakopara Station to Ballalpur Station (TP NO 247/30 & 247/32) at Bhabanipur mouza & Connecting with existing 110 mm dia UPVC distribution main line of Arjunpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | 509/MURD | 23/02/2022 | 60 | M/S GUHA & ROY ENTERPRISE | 37.5 | 23.75 | 100 | 0
750 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jainagar, Loknathpur, Ekdala (315680, 315681 & 315682) of Loknathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block , SM/07677 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jainagar(Village code 315680) under Loknathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Bedanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723426 in the District of Murshidabad. (Sl No-36) | 3285/MURD | 05/10/2021 | 180 | M/S. BIMAL MISRA | 76.59 | 36.38 | 47.51 | 48
751 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jainagar, Loknathpur, Ekdala (315680, 315681 & 315682) of Loknathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block , SM/07677 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Loknathpur (Village Code -315681) Part-A under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 280/BSD | 24/06/2022 | 30 | MONDAL CONSTRUCTION | 4.59 | 4.02 | 87.63 | 0
752 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jainagar, Loknathpur, Ekdala (315680, 315681 & 315682) of Loknathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block , SM/07677 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Loknathpur (Village Code -315681) Part-B under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 281/BSD | 24/06/2022 | 30 | MONDAL CONSTRUCTION | 4.73 | 4.63 | 97.87 | 0
753 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jainagar, Loknathpur, Ekdala (315680, 315681 & 315682) of Loknathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block , SM/07677 | Retrofitting | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. (i.e 01.06.2023 to 30.11.2023) | 100/HQ | 30/05/2023 | 184 | DULAL CHOWDHURY | 0.91 | 0.6 | 100 | 100
754 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jainagar, Loknathpur, Ekdala (315680, 315681 & 315682) of Loknathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block , SM/07677 | Retrofitting | Continuation Order for Hiring of one no. Diesel Bolero/ Marshal/Ambassador car (WB57B-4454) for official use of the Assistant Engineer, Kandi Sub-Division, P.H.Engineering Dte. for 06(SIX) Months. (Period from 01.07.2023 to 31.12.2023) | 43/BSD | 23/06/2023 | 183 | SISIR KUMAR DE | 0.91 | 0 | 0 | 0
755 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jainagar, Loknathpur, Ekdala (315680, 315681 & 315682) of Loknathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block , SM/07677 | Retrofitting | Repair and renovation work of Boundary wall at Head Work of MahamadpurWater Supply Scheme under Berhampore Sub Division, P.H.E.Dte. in the District of Murshidabad. | 460/BSD | 15/12/2021 | 30 | ARINDAM MAJUMDAR | 4.74 | 4.13 | 100 | 100
756 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jainagar, Loknathpur, Ekdala (315680, 315681 & 315682) of Loknathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block , SM/07677 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Loknathpur (Village code 315681) under Loknathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID 1723426 (Sl No-35) | 960/MURD | 24/03/2021 | 180 | AJAY MONDAL | 68.75 | 68.5 | 100 | 1
757 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jainagar, Loknathpur, Ekdala (315680, 315681 & 315682) of Loknathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block , SM/07677 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ekdala (Village code 315682)under Lokenathpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723426 in the District of Murshidabad | 3142/MURD | 11/12/2020 | 60 | NATIONAL ENTERPRISE | 29.41 | 18.85 | 64.09 | 1
758 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jainagar, Loknathpur, Ekdala (315680, 315681 & 315682) of Loknathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block , SM/07677 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Ekdala ( Village Code -315682) under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 267/BSD | 24/06/2022 | 953 | NATIONAL ENTERPRISE (APU GHOSH) | 4.84 | 0 | 0 | 100
759 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mamenpur (314732) of Momenpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) , SM/07678 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) in Connection with Jal Jeevan Mission & Jal Swapna of village of Momenpur Village Code (314732) Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District. PHE DTE Tender no-117 of 20-21 by SE / MC |  | 13/07/2021 | 0 | M/S. BIMALENDU BOSE | 60.35 | 0 | 0 | 0
760 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mamenpur (314732) of Momenpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) , SM/07678 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mamenpur (Village code 314732) under Mamenpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 000958860 (Sl No-13) | 22-MSD/22-23 | 14/04/2022 | 0 | M/S. BIMALENDU BOSE | 4.42 | 0 | 0 | 0
761 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mamenpur (314732) of Momenpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) , SM/07678 | Retrofitting | Preparation of D.P.R. (Consultancy work) in connection with the Functional Household Connection of different existing PWSS (Bhagirathpur PWSS Scheme,Block- Domkal)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 375 of 21-22 by EE MSD, and Scheme Code: 7678 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.73 | 0 | 0 | 0
762 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Jagarpara (Code-314183), Janardanpur (Code-314184),Chamunda(Code-314171) In The Command Area Of Nasipur Zone-I Gr , SM/07688 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jagarpara (Village code 314183),Chamunda(Village code 314171),Janardanpur( Village code 314184), under Nasipur Zone-I Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-B) | 203/BD-I | 04/02/2021 | 30 | TARUN KUMAR BHATTACHARYA | 79.1 | 55.03 | 69.57 | 1
763 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Jagarpara (Code-314183), Janardanpur (Code-314184),Chamunda(Code-314171) In The Command Area Of Nasipur Zone-I Gr , SM/07688 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Jagarpara (Code-314183), Janardanpur (Code-314184),Chamunda(Code-314171) In The Command Area Of Nasipur Zone-I Ground Water Supply Scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1606/BD-I | 03/10/2024 | 30 | PAMIR ROY | 11.94 | 0 | 0 | 0
764 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr , SM/07691 | Retrofitting | Additional Laying works at village Sahapur, Upar Fatepur and Bajipur Madhupur (Village code-314210,314212 and 314235) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Bajipur Madhupur Ground water based Water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | 2314/BD-I | 29/12/2021 | 45 | BIJOY CHOWDHURY | 13.36 | 2.47 | 100 | 1
765 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr , SM/07691 | Retrofitting | Laying of new pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Narayanpur and others under Bajipur Madhupur Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | 1441/BD-I | 11/08/2021 | 10 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 1.16 | 0.73 | 62.92 | 1
766 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr , SM/07691 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Narayanpur (Village code 314214) under Bajipur Madhupur Ground Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte | 828/BD-I | 13/11/2020 | 60 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 10.28 | 12.88 | 125.34 | 1
767 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr , SM/07691 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1233/BD-I | 30/07/2024 | 60 | PRIME CONSTRUCTION | 28.06 | 0 | 0 | 0
768 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Sahapur (Code-314210), Ekdalla (Code-314213), Narayanpur (Code-314214) In The Command Area Of Bajupur Madhapur Gr , SM/07691 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Egdalia(Village code 314213) under Bajipur Madhupur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 165/BD-I | 03/02/2021 | 20 | LAXMI CONSTRUCTION | 4.93 | 9.48 | 195 | 1
769 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ghoramara (315515) of Ghoramara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshidabad District , SM/07273 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandabad (Village code 315517) under Ghoramara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723483 in the District of Murshidabad. | 3137/MURD | 11/12/2020 | 60 | M/S. CHOWDHURY CONSTRUCTION | 23.85 | 0 | 0 | 1
770 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ghoramara (315515) of Ghoramara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshidabad District , SM/07273 | Retrofitting | Retrofiting of Function al Household Tap Connection FHTC and allied works in connection with Jal Swapna from existing distribution system within the command area of village fatepur under Ghoramara Ground W/S Scheme for arsenic affected areas of Berhampore Block in the Dist of MSD PHE DTE. Tender no 903 of 20+-21 by EE MSD | 45-MSD / 21-22 | 31/08/2021 | 0 | M/S M.S. ENTERPRISE | 17.75 | 0 | 0 | 0
771 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ghoramara (315515) of Ghoramara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshidabad District , SM/07273 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --BHALKUNDI-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- SAMANDI , CODE-315122, TNO- 573/2020-21/EE | 473/W | 08/03/2021 | 0 | APURBA SAHA CHOWDHURY | 16.4 | 0 | 0 | 0
772 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ghoramara (315515) of Ghoramara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshidabad District , SM/07273 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --PANCHTHUPI-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- ACHHOAN, CODE-315979, TNO- 605/2020-21/EE | 473/W | 08/03/2021 | 0 | LAXMI CONSTRUCTION | 6.24 | 0 | 0 | 0
773 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ghoramara (315515) of Ghoramara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshidabad District , SM/07273 | Retrofitting | EXTENSION OF DISTRIBUTION PIPELINE WITHIN THE COMMAND AREA OF BHALKUNDI WSS, TNO- 478/20-21/EE | 473/W | 08/03/2021 | 0 | DEBASISH SARKAR | 4.64 | 0 | 0 | 0
774 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ghoramara (315515) of Ghoramara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshidabad District , SM/07273 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village GHORAMARA (Village Code 315515) under GHORAMARA Ground Water Based Water Supply Scheme for arsenic affected areas of BERHAMPORE Block in the District of Murshidabad. Tender no - 903 of 20-21 by EE MURD | 352-MSD/21-22 | 05/03/2022 | 0 | M/S M.S. ENTERPRISE | 11.41 | 0 | 0 | 0
775 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ghoramara (315515) of Ghoramara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshidabad District , SM/07273 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ghoramara (Village code 315515) under Ghoramara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723483in the District of Murshidabad. | 3143/MURD | 11/12/2020 | 60 | M/S M.S. ENTERPRISE | 31.09 | 0 | 0 | 1
776 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District , SM/07200 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RADHARGHAT-II G.P. under Murshidabad Division, P.H.E.Dte. | 342/BSD | 27/08/2021 | 30 | IMAGIN | 4.17 | 0 | 0 | 1
777 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District , SM/07200 | Retrofitting | EXTENSION OF DISTRIBUTION PIPELINE WITHIN THE COMMAND AREA OF BHALKUNDI WSS, TNO- 478/20-21/EE | 473/W | 08/03/2021 | 0 | DEBASISH SARKAR | 4.64 | 0 | 0 | 0
778 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District , SM/07200 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of SAKTIPUR Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- MAHATA, CODE-315638, TNO- 538/20-21/EE | 473/W | 08/03/2021 | 0 | SO-FINE AQUARIUM | 11.52 | 0 | 0 | 0
779 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District , SM/07200 | Retrofitting | LAYING OF UPVC PIPELINE AT JOYPUR PASCHIMPARA....BHALKUNDI Z-I WSS, TNO- 05/20-21/AEKSD | 473/W | 08/03/2021 | 0 | DEBASISH SARKAR | 1.6 | 0 | 0 | 0
780 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District , SM/07200 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chumarigacha (Village code 315340) under Basabari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723194 in the District of Murshidabad | 3122 / MURD | 09/12/2020 | 60 | TANUSHREE ENTERPRISE | 39.34 | 0.53 | 100 | 1
781 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chumarigacha (315340) of Basabari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District , SM/07200 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | 303/BSD | 13/08/2021 | 30 | IMAGIN | 4.34 | 8.67 | 200 | 0
782 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chayan Nagar, Sankuria, Rainda (315023, 315024 & 315025) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of , SM/07279 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BURWAN- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- GOURINAGAR , CODE-315951 , 631/2020-21/EE | 504/W | 22/03/2021 | 0 | KAMIRUL SK AND CO. | 9.08 | 0 | 0 | 0
783 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chayan Nagar, Sankuria, Rainda (315023, 315024 & 315025) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of , SM/07279 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -JITPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE - PAR RAGHUNATHPUR, CODE- 314677 , TNO- 80/20-21/SEMC | 504/W | 22/03/2021 | 0 | UMWELT ENGINEER PVT LTD | 36.66 | 0 | 0 | 0
784 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chayan Nagar, Sankuria, Rainda (315023, 315024 & 315025) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of , SM/07279 | Retrofitting | Extension of UPVC pipeline construction of RCC stand post with platform at Ghoshkula area (Kanakpara) under Improvement of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. | 414/LSD | 27/12/2021 | 30 | SANJIB KUMAR SINGHA | 4.89 | 0 | 0 | 0
785 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chayan Nagar, Sankuria, Rainda (315023, 315024 & 315025) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of , SM/07279 | Retrofitting | Construction of RCC Stand Post including platforms at AmarkunduVillage, Kanakpara Village, Nandigram Village, Bagor Village & Madhunia Village under Improvement work of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. | 362/LSD | 17/11/2021 | 30 | SARAJIT KUMAR MAJUMDER | 2.43 | 2.43 | 100 | 0
786 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chayan Nagar, Sankuria, Rainda (315023, 315024 & 315025) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of , SM/07279 | Retrofitting | Extension of UPVC pipeline construction of RCC stand post with platform at Ghoshkula area (Kanakpara) under Improvement of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. | 414 /LSD | 27/12/2021 | 30 | SANJIB KUMAR SINGHA | 4.89 | 4.88 | 100 | 0
787 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chayan Nagar, Sankuria, Rainda (315023, 315024 & 315025) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of , SM/07279 | Retrofitting | Extension of distribution system for supply of safe potable drinking water at Charakdanga Adibashi Para, Madhunia Primay School & Madhunia SSKAdibashi Para under Amarkundu Water Supply Scheme under Lalbagh Sub-Division,PHE Dte. | 349/LSD | 09/11/2021 | 30 | GHOSH & COMPANY | 2.74 | 2.74 | 100 | 0
788 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chayan Nagar, Sankuria, Rainda (315023, 315024 & 315025) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of , SM/07279 | Retrofitting | Balance and allied works For Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sankuria (Village code 315024) and Chayan Nagar (Village code 315023) under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nabagram Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 308/MURD | 07/02/2022 | 60 | PARTHA PRATIM DAS | 16.51 | 12.52 | 100 | 1
789 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Opar Orahar (Code-314444) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-A) , SM/07729 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Upar Orahar(Village code 314444) under Sundarpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | 171/BD-I | 03/02/2021 | 30 | KAMIRUL SK AND CO. | 50.99 | 86.53 | 169.69 | 0
790 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Opar Orahar (Code-314444) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-A) , SM/07729 | Retrofitting | Laying of new UPVC pipeline with allied work for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Upar Orahar (Village code 314444) under Sundarpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | 1440/BD-I | 11/08/2021 | 10 | KAMIRUL SK AND CO. | 4.67 | 0 | 0 | 0
791 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Diar Syampur ground water supply scheme , SM/06980 | Retrofitting | Additional laying works at village Diar Syampur (Village Code-314439) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Diar Syampur Ground Water Supply Scheme (Bhagawangola-I Block) under Berhampore Division-I, PHE Dte. in the district of Murshidabad. | 549/BD-I | 13/05/2022 | 10 | BURIMA CONSTRUCTION | 3.37 | 2.63 | 78.03 | 50
792 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Diar Syampur ground water supply scheme , SM/06980 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Diar Syampur (Village code 314439) under Diar Syampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 270/ BD-I | 12/02/2021 | 30 | BURIMA CONSTRUCTION | 44.88 | 42.38 | 94.43 | 1
793 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Diar Syampur ground water supply scheme , SM/06980 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Meoakhana (Village code 314438) under Diar Syampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 68/BD-I | 18/01/2021 | 30 | M/S. DAS ENTERPRISE | 22.56 | 35.45 | 157.18 | 1
794 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Diar Syampur ground water supply scheme , SM/06980 | Retrofitting | Additional Laying works at village Diar Syampur( Village code -314439 ) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Diar Syampur Ground water supply scheme (Bhagwangola-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | 2294/BD-I | 28/12/2021 | 10 | AICH CONSTRUCTION | 6.77 | 0 | 0 | 0
795 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Diar Syampur ground water supply scheme , SM/06980 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Diar Syampur ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1303/BD-I | 07/08/2024 | 30 | DAS ENTERPRISE(GORABAZAR) | 2.91 | 0 | 0 | 0
796 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-II ground water supply scheme , SM/07231 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hurshi (village code 314752), under Hurshi Zone-II Ground water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2206/BD-I | 10/12/2021 | 90 | SRIJON ENTERPRISE | 66.87 | 51.38 | 76.84 | 0
797 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-II ground water supply scheme , SM/07231 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Arazi Kanaipur (village code 314751), under Hurshi Zone-II Ground water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2252/BD-I | 21/12/2021 | 20 | ANUPA ENTERPRISE | 5.11 | 5.03 | 100 | 1
798 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Khemrajpur Village (Code-314761), Srirampur Village (Code-314762), Naodapara Village (Code-314763) Under Command Area Of Lochanpu , SM/07698 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khemrajpur (Village code 314761),Naodapara (Village code 314763),Srirampur(Village code 314762) under Lochanpur Ground Water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 199/BD-I | 04/02/2021 | 30 | M/S S.S ENTERPRISE | 71.38 | 79.87 | 111.9 | 1
799 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Khemrajpur Village (Code-314761), Srirampur Village (Code-314762), Naodapara Village (Code-314763) Under Command Area Of Lochanpu , SM/07698 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Khemrajpur Village (Code-314761), Srirampur Village (Code-314762), Naodapara Village (Code-314763) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte | 1223/BD-I | 29/07/2024 | 60 | M/S. MONDAL ENTERPRISE | 23.39 | 0 | 0 | 0
800 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harisankarpur, Sadipur (314635 & 314640) of Barabil Raghunathpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi B , SM/07287 | Retrofitting | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0 | 0
801 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harisankarpur, Sadipur (314635 & 314640) of Barabil Raghunathpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi B , SM/07287 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Harisankarpur ( Village Code -314635) under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. | 51/ISD | 28/01/2022 | 30 | ABA CONTRACTOR | 4.24 | 4.24 | 100 | 0
802 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harisankarpur, Sadipur (314635 & 314640) of Barabil Raghunathpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi B , SM/07287 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village HARISANKARPUR (Village Code 314635) under BARABIL RAGHUNATHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 127 of 21-22 by AE ISD | 109-MSD/22-23 | 06/05/2022 | 0 | M/S BIREN BHATTACHARYYA | 4.84 | 0 | 0 | 0
803 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harisankarpur, Sadipur (314635 & 314640) of Barabil Raghunathpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi B , SM/07287 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village HARISANKARPUR (Village Code 314635) under BARABIL RAGHUNATHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 126 of 21-22 by AE ISD | 110-MSD/22-23 | 11/05/2022 | 0 | M/S BHATTACHARJEE & CO | 4.84 | 0 | 0 | 0
804 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harisankarpur, Sadipur (314635 & 314640) of Barabil Raghunathpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi B , SM/07287 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Harisankarpur ( Village Code -314635) [Near house of Jobarma Nanda Primary School to Subeder More] under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. | 50/ISD | 28/01/2022 | 30 | M/S BIREN BHATTACHARYYA | 4.85 | 0 | 0 | 0
805 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harisankarpur, Sadipur (314635 & 314640) of Barabil Raghunathpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi B , SM/07287 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Harisankarpur ( Village Code -314635) [Near house of Shiltu fro Rajak Talar More] under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. | 49/ISD | 28/01/2022 | 30 | M/S BHATTACHARJEE & CO | 4.85 | 0 | 0 | 0
806 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harisankarpur, Sadipur (314635 & 314640) of Barabil Raghunathpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi B , SM/07287 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bilaspur Nachharerpara (Village code 314639) under Barabil Raghunathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723213 | 2537/MURD | 19/08/2021 | 180 | M/S. UNIQUE BUILDERS | 74.3 | 8.35 | 100 | 0
807 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harisankarpur, Sadipur (314635 & 314640) of Barabil Raghunathpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi B , SM/07287 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village HARISANKARPUR (Village Code 314635) under Barabil Raghunathpur Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block in the District of Murshidabad. | 3032/MURD | 07/12/2020 | 45 | DOBAY CONSTRUCTION | 20.91 | 17.85 | 100 | 100
808 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hari Sankarpur (314740) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV ) , SM/07908 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village HARI SANKARPUR (Village code 314740) under KATAKOBRA Ground Water Based Water Supply Scheme for Arsenic Affected Area of DOMKAL Block, under Murshidabad Division, PHE Dte. Scheme ID 0005185646 in the District of Murshidabad. Tender no 827 of 20-21 by EE MSD |  | 18/08/2021 | 0 | M/S SUBHA CONSTRUCTION | 32.45 | 0 | 0 | 0
809 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hari Sankarpur (314740) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV ) , SM/07908 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village HARI SANKARPUR (Village code 314740) under KATAKOBRA Ground Water Based Water Supply Scheme for Arsenic Affected Area of DOMKAL Block, under Murshidabad Division, PHE Dte. Scheme ID 0005185646 in the District of Murshidabad. Tender no 827 of 20-21 by EE MSD | 51-MSD/21-22 | 13/09/2021 | 0 | M/S SUBHA CONSTRUCTION | 32.45 | 0 | 0 | 0
810 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hari Sankarpur (314740) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV ) , SM/07908 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Hari Sankarpur ( Village Code -314740) under Katakobra Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005185646). | 651 /MURD | 18/02/2021 | 60 | M/S SUBHA CONSTRUCTION | 43.8 | 10.32 | 100 | 1
811 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni , SM/07663 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Nialispara ( village code: 315317 ) of Budharpara Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. For 18nos FHTC | 202/BSD | 28/04/2022 | 30 | SURAJIT MONDAL | 4.81 | 4.1 | 85.25 | 100
812 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni , SM/07663 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Tikiapara (Village code 315318) under Budharpara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005182920 in the District of Murshidabad. | 281/MURD | 03/02/2022 | 60 | M/S SWAPAN KUMAR NATH AND CO. | 19.7 | 18.08 | 100 | 100
813 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni , SM/07663 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Nialispara ( village code: 315317 ) of Budharpara Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. For 28nos FHTC | 203/BSD | 28/04/2022 | 30 | ABIDA CONSTRUCTION | 4.85 | 3.85 | 100 | 80
814 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni , SM/07663 | Retrofitting | Material Requisition To Resource Division | 539/11/MURD | 25/02/2022 | 0 | Resource Division | 0.49 | 0 | 0 | 0
815 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni , SM/07663 | Retrofitting | Providing Functional Household Tap Connections (FHTC) 69 nos in connection with Jal Swapna (Jal Jeevan Mission ) including Laying of Distribution system of Nialispara ( Village Code -315317) under Budharpara Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. | 1185/MURD | 09/05/2022 | 30 | AMAL KUMAR DAS | 37.93 | 0 | 0 | 0
816 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni , SM/07663 | Retrofitting | Laying distribution pipeline in connection with Jal Swapna (Jal Jeevan Mission) of Nialispara ( village code: 315317 ) and Budhorpara village of Budharpara Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. | 191/BSD | 28/04/2022 | 30 | MOBIDUR RAHAMAN | 4.67 | 4.67 | 100 | 80
817 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni , SM/07663 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Budharpara (Village code 315320) under Budharpara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte.Scheme ID - 5182920 in the District of Murshidabad. | 2644/MURD | 27/08/2021 | 60 | M/S. BIMALENDU BOSE | 21.87 | 0 | 0 | 0
818 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni , SM/07663 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gopjan (Village code 315447) under Budharpara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005182920 in the District of Murshidabad. | 1126/MURD | 29/04/2022 | 45 | PRATICHI ENTERPRISE | 24.48 | 0 | 0 | 40
819 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniswar, Nialishpara, Tikiapara, Budharpara, Gopjan (315314, 315317,315318, 315320 & 315447) of Budharpara under Ground Water Based Water Supply Scheme for Arseni , SM/07663 | Retrofitting | Providing Functional Household Tap Connections (FHTC) 67 nos in connection with Jal Swapna (Jal Jeevan Mission ) including Laying of Distribution system of Raniswar( Village Code -315314) under Budharpara Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. | 1083/MURD | 27/04/2022 | 30 | DEBASISH SARKAR | 33.33 | 0 | 0 | 1
820 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) , SM/07769 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JAGTAI-I G.P. under Murshidabad Division, P.H.E.Dte. | 51/JSD | 25/01/2022 | 30 | IMAGIN | 4.16 | 0 | 0 | 0
821 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) , SM/07769 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JAGTAI-II G.P. under Murshidabad Division, P.H.E.Dte. | 52/JSD | 25/01/2022 | 30 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0 | 0
822 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) , SM/07769 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Swapna Jal Jeevan Mission and under command area of village of JAGTAI (Village code 313979) under JAGTAI Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184165 | 4023/MURD | 24/12/2021 | 180 | HOQUEDAR ALI | 91.83 | 91.45 | 100 | 1
823 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) , SM/07769 | Retrofitting | Allied work for Rising main connection to OHR & AIRP in connection with FHTC work of Village of JAGTAI(Village Code-313979) under JAGTAI Water Supply Scheme (Scheme ID- 0005184165) under Jangipur Sub Division,P.H.E. Dte | 235/JSD | 05/05/2022 | 30 | MAA CONSTRUCTION | 3.84 | 3.84 | 100 | 0
824 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) , SM/07769 | Retrofitting | Allied work of laying of HDPE Pipe line for " Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) under command area of village JAGTAI (Village Code-313979)"( Bara Masjid Para) under command area of Jagtai Ground Water based Water supply scheme for Arsenic Affected Areas of Suti-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0005184165) in the district of Murshidabad. | 241/JSD | 05/05/2022 | 30 | MONDAL CONSTRUCTION | 4.77 | 4.7 | 100 | 0
825 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) , SM/07769 | Retrofitting | EXTENSION OF PIPELINE AT AURANGABAD PHE SUB CENTRE & JAGTAI SUB CENTRE UNDER SUTI -II BLOCK | 228/JSD | 15/01/2020 | 2192 | SUJIT CHOWDHURY | 1.97 | 1.94 | 100 | 100
826 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) , SM/07769 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
827 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) , SM/07769 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
828 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jagtai ( 313979 ) of Jagtai under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block of Murshidabad District ( PART-I ) , SM/07769 | Retrofitting | Laying of HDPE pipeline and FHTC of 191 nos. household for retrofitting works in Jagtai Ground water-based w/s scheme for arsenic affected areas of Suti-II Block under Murshidabad Division, PHE Dte. in the District of Murshidabad. (Scheme ID- 0005184165) | 1935/MURD | 18/07/2023 | 30 | HOQUEDAR ALI | 41.12 | 39.92 | 100 | 100
829 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ahiron (313929) of Ahiron under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - I Block of Murshidabad District (PART-I) , SM/07675 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village AHIRON (Village Code 313929) under AHIRON Ground Water Based Water Supply Scheme for arsenic affected areas of SUTI-I Block in the District of Murshidabad. Tender no - 116 of 21-22 by SE MC | 387-MSD/21-22 | 17/03/2022 | 0 | DHIRENDRANATH MONDAL | 87.54 | 0 | 0 | 0
830 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ahiron (313929) of Ahiron under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - I Block of Murshidabad District (PART-I) , SM/07675 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of AHIRON (Village code 313929) under AHIRON Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184152 | 3756/MURD | 01/12/2021 | 180 | DHIRENDRANATH MONDAL | 87.54 | 0 | 0 | 0
831 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Charkamnagar Village (Code-315620), Nagar Village (Code-315622), Maklishpur Village(Code-315623) Under Command Area Of Charkamnag , SM/07694 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Charkamnagar Village (Code-315620), Nagar Village (Code-315622), Maklishpur Village(Code-315623) Under Command Area Of Charkamnagar Ground Water Supply Scheme (Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1450/BD-I | 04/09/2024 | 60 | SUDIPA SINGHA ROY | 13.53 | 0 | 0 | 0
832 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mohanpur Village (Code-314764), Gopinathpur Village (Code-314765) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part , SM/07718 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Mohanpur Village (Code-314764), Gopinathpur Village (Code-314765) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part-C)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1442/BD-I | 04/09/2024 | 60 | S.K CONSTRUCTION (SUDIP KUMAR SANYAL) | 19.16 | 0 | 0 | 0
833 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mohanpur Village (Code-314764), Gopinathpur Village (Code-314765) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part , SM/07718 | Retrofitting | Additional Laying works at village Mohanpur (village code 314764) and Gopinathpur (village code 314765) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Lochanpur Ground water supply scheme (Raninagar-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 1919/BD-I | 08/10/2021 | 10 | BIMALENDU BOSE | 7.03 | 7.02 | 100 | 1
834 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Raypur (314582) & Khidirpar (314739) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( P , SM/07772 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village DEPUTIPAR (Village Code-314582) under GODHANPARA Ground Water Supply Scheme for Arsenic Affected Area of RANINAGAR-II BLOCK under Murshidabad Division, PHE Dte. | 31-MSD / 21-22 | 27/08/2021 | 0 | M/S ROY & BOSE ENTERPRISE | 10.92 | 0 | 0 | 0
835 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Raypur (314582) & Khidirpar (314739) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( P , SM/07772 | Retrofitting | Repairing & Renovation of the Boundary wall of pump House No-2 Both & Allied works under Katakopra Zone- I & II water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad | 48/ISD | 28/01/2022 | 30 | PARTHA RAJAK | 1.95 | 1.94 | 100 | 1
836 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Raypur (314582) & Khidirpar (314739) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( P , SM/07772 | Retrofitting | Repairing & Renovation of the pump House No-1 & 2 under Katakopra Zone-I water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad | 46/ISD | 28/01/2022 | 60 | PRAVAT KUMAR GHOSH | 3.65 | 3.64 | 100 | 1
837 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Raypur (314582) & Khidirpar (314739) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( P , SM/07772 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Khidir Para ( Village Code -314739) under Katakobra Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005185646). | 580/MURD | 09/02/2021 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 33.55 | 33.54 | 99.99 | 80
838 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Raypur (314582) & Khidirpar (314739) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( P , SM/07772 | Retrofitting | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Raypur (Village code-314582) under KatakobraGround Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division P.H.E Dte. (Scheme ID-0005185646) | 2765/MURD | 29/09/2022 | 120 | SOFIQUL ISLAM | 154.82 | 144.08 | 100 | 100
839 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Jalangi ( 314631 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshi , SM/07774 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Muradpur-Jalangi (Village code 314631) under Muradpur-Jalangi Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723429 in the District of Murshidabad. (Sl No-26), 557/MURD, 08/02/2021 | 186-MSD/21-22 | 12/11/2021 | 0 | MAMATA USHA ENTERPRISE | 35.48 | 0 | 0 | 0
840 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Jalangi ( 314631 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshi , SM/07774 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Muradpur-Jalangi (Village code 314631) under Muradpur-Jalangi Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723429 in the District of Murshidabad. (Sl No-26), TNO-107/20-21/SE-MC | 116-MSD/22-23 | 06/05/2022 | 0 | MAMATA USHA ENTERPRISE | 42.57 | 0 | 0 | 0
841 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Jalangi ( 314631 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshi , SM/07774 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Muradpur-Jalangi (Village code 314631) under Muradpur-Jalangi Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723429 in the District of Murshidabad. (Sl No-26) | 557/MURD | 08/02/2021 | 180 | MAMATA USHA ENTERPRISE | 144.81 | 93.66 | 64.68 | 0
842 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maheshpur (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block I , SM/07890 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) laying pipeline in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Shankarpara, Rameswarpur, Nalkunda & Bhabtakharida (Village Code- 315561, 315581, 315582 and 315583 under Mahespur (ZONE-F) Water Supply Scheme in the district Murshidabad under Berhampore Division - I, PHE Dte. | 946/BD-I | 23/08/2022 | 120 | DHIRENDRA NATH MONDAL | 107.44 | 0 | 0 | 0
843 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maheshpur (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block I , SM/07890 | Retrofitting | Laying of 150 mm dia (K-9),250 mm & 300 mm dia DI (K-7) pipeline with interconnection in between Rising Main and Distribution System and 180 mm dia ,200 mm dia&225 mm dia UPVC pipeline of unlead portion within command area of Mahespur(Zone-F) W/S scheme of Arsenic affected area of Beldanga uncovered W/S scheme under Berhampore Division-I, P.H.E. Dte. | 895/BD-I | 05/10/2023 | 30 | SANTA TRADING | 20.6 | 0 | 0 | 0
844 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Moktarpur, Balarampur, Sahajadpur, Nischintapur, Bahurul (315321, 315322, 315326, 315328 & 315329) of Sahajadpur under Ground Water Based Water Supply Scheme for A , SM/08184 | Retrofitting | Laying of distribution pipeline in connection with FHTC work at North Durgapur area of Sahajadpur village under SAHAJADPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | 257-MSD/22-23 | 17/08/2022 | 0 | MITHUN ROY | 4.8 | 0 | 0 | 0
845 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Moktarpur, Balarampur, Sahajadpur, Nischintapur, Bahurul (315321, 315322, 315326, 315328 & 315329) of Sahajadpur under Ground Water Based Water Supply Scheme for A , SM/08184 | Retrofitting | Laying of distribution pipeline in connection with FHTC work at South Durgapur area of Sahajadpur village under SAHAJADPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | 258-MSD/22-23 | 18/08/2022 | 0 | M/S GUHA AND ROY | 5 | 0 | 0 | 0
846 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Moktarpur, Balarampur, Sahajadpur, Nischintapur, Bahurul (315321, 315322, 315326, 315328 & 315329) of Sahajadpur under Ground Water Based Water Supply Scheme for A , SM/08184 | Retrofitting | Laying of distribution pipeline in connection with FHTC work at Muktarpur area of Sahajadpur village under SAHAJADPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | 258-MSD/22-23 | 18/08/2022 | 0 | M/S GUHA AND ROY | 4.84 | 0 | 0 | 0
847 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Moktarpur, Balarampur, Sahajadpur, Nischintapur, Bahurul (315321, 315322, 315326, 315328 & 315329) of Sahajadpur under Ground Water Based Water Supply Scheme for A , SM/08184 | Retrofitting | Laying of distribution pipeline in connection with FHTC work at Muktarpur area of Sahajadpur village under SAHAJADPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | 257-MSD/22-23 | 17/08/2022 | 0 | MITHUN ROY | 1.54 | 0 | 0 | 0
848 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Moktarpur, Balarampur, Sahajadpur, Nischintapur, Bahurul (315321, 315322, 315326, 315328 & 315329) of Sahajadpur under Ground Water Based Water Supply Scheme for A , SM/08184 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bahurul (Village code 315329) under Sahajadpur Ground Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID 1723365 in the District of Murshidabad.(Sl-4) | 2460/MURD | 26/08/2022 | 180 | SANJAY BISWAS | 70.29 | 0 | 0 | 0
849 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Moktarpur, Balarampur, Sahajadpur, Nischintapur, Bahurul (315321, 315322, 315326, 315328 & 315329) of Sahajadpur under Ground Water Based Water Supply Scheme for A , SM/08184 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Moktarpur (Village code 315321) under Sahajadpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID 1723365 in the District of Murshidabad. (Sl No-34) | 1231/MURD | 13/05/2021 | 180 | M/S GUHA & ROY ENTERPRISE | 80.38 | 112.3 | 139.71 | 1
850 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Moktarpur, Balarampur, Sahajadpur, Nischintapur, Bahurul (315321, 315322, 315326, 315328 & 315329) of Sahajadpur under Ground Water Based Water Supply Scheme for A , SM/08184 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | 304/BSD | 13/08/2021 | 30 | IMAGIN COMMUNICATION | 4.34 | 8.68 | 200 | 0
851 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Moktarpur, Balarampur, Sahajadpur, Nischintapur, Bahurul (315321, 315322, 315326, 315328 & 315329) of Sahajadpur under Ground Water Based Water Supply Scheme for A , SM/08184 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sahajadpur (Village code 315326) under Sahajadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte.Scheme ID 1723365 in the District of Murshidabad. | 3840/MURD | 08/12/2021 | 90 | J.S. CONSTRUCTION | 54.01 | 51.74 | 100 | 1
852 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Moktarpur, Balarampur, Sahajadpur, Nischintapur, Bahurul (315321, 315322, 315326, 315328 & 315329) of Sahajadpur under Ground Water Based Water Supply Scheme for A , SM/08184 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Balarampur (Village code 315322)under Sahajadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of BERHAMPORE Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723365 in the District of Murshidabad. | 3139/MURD | 11/12/2020 | 60 | M/S M.S. ENTERPRISE | 27.16 | 22.25 | 81.91 | 1
853 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Moktarpur, Balarampur, Sahajadpur, Nischintapur, Bahurul (315321, 315322, 315326, 315328 & 315329) of Sahajadpur under Ground Water Based Water Supply Scheme for A , SM/08184 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kandibandha (Village code 315327) under Sahajadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of BERHAMPORE Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723365 in the District of Murshidabad. | 3138/MURD | 11/12/2020 | 60 | MAJUMDER CONSTRUCTION | 24.53 | 14.68 | 100 | 80
854 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Nishindra Para and adjoining habitations under Mahadeb Nagar(CT) (Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) | 27-MSD / 21-22 | 18/08/2021 | 0 | PRIYANKA CONSTRUCTION | 25.58 | 0 | 0 | 0
855 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | Allied work of laying U.P.V.C pipe line for " Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of Village Nishindra Para & adjoining habitation under Mahadebnagar(CT) (Village code 313837) under Mahadebnagar Ground water Based water supply scheme for Arsenic Affected Area of Farakka Block under Murshidabad Division, P.H.E. Dte. Scheme ID-0001723329 in the District Murshidabad. | 389/JSD | 31/12/2021 | 30 | HERITAZE CONSTRUCTION | 4.67 | 4.67 | 100 | 0
856 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | Allied work of laying UPVC Pipe line for " Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) under command area of village Mahadebnagar (CT) (Village Code-313837)" under command area of Mahadevnagar Zone-I Water supply scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723329) in the district of Murshidabad. (Part-I). | 122/JSD | 22/03/2022 | 30 | MOTI RAHAMAN | 4.99 | 4.74 | 100 | 0
857 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | Allied work of laying UPVC Pipe line for " Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) under command area of village Mahadebnagar (CT) (Village Code-313837)" under command area of Mahadevnagar Zone-I Water supply scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001723329) in the district of Murshidabad. (Part-II). | 123/JSD | 22/03/2022 | 30 | APU CONSTRUCTION | 4.98 | 4.73 | 100 | 0
858 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID - ER-MLDT-2022-WL-25 | 398-MSD/22-23 | 11/11/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 4.38 | 0 | 0 | 0
859 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Balidapukur under Mamrejpur(CT) ( Village Code -313835) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) | 1746/MURD | 09/07/2021 | 60 | RAHAMAN CONSTRUCTION | 30.9 | 27.91 | 100 | 0
860 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Uttar Mahadev Nagar under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) | 1726/MURD | 08/07/2021 | 60 | SARASWATI ENTERPRISE | 39.81 | 32.3 | 81.14 | 1
861 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Nishindra Para and adjoining habitations under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) | 1486/MURD | 21/06/2021 | 60 | PRIYANKA CONSTRUCTION | 27.85 | 0 | 0 | 1
862 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jaladipur and adjoining habitations under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) | 1572/MURD | 25/06/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 30.89 | 27.25 | 88.22 | 0
863 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Gopalnagar and adjoining habitations under Mamrejpur(CT) ( Village Code -313835) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) | 1710/MURD | 07/07/2021 | 60 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 28.28 | 24.83 | 87.81 | 1
864 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Tarapur under Mamrejpur(CT) ( Village Code -313835) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) | 1563/MURD | 24/06/2021 | 60 | SUMAN CHOWDHURY | 33.18 | 33.15 | 100 | 0
865 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Karbala and adjoining habitations under Mahadeb Nagar(CT)( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) | 1547/MURD | 23/06/2021 | 60 | MOLLA ENTERPRISE | 27.32 | 50.69 | 200 | 0
866 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Maddham Mahadev Nagar under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) | 1727/MURD | 08/07/2021 | 60 | A.S. CONSTRUCTION | 31.14 | 27.21 | 100 | 0
867 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Pashim Jikri & Natun Momrajpur and adjoining habitations under Mamrejpur(CT) ( Village Code -313835) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) | 1662/MURD | 02/07/2021 | 60 | MONDAL ENTERPRISE | 21.09 | 38.85 | 200 | 0
868 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouzaMahadeb nagar (CT), Mamrejpur (CT) (313837, 313835) of Mahadeb Nagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Mur , SM/08194 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dakshin Mahadev Nagar under Mahadeb Nagar(CT) ( Village Code -313837) under Mahadeb Nagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723329) | 1724/MURD | 08/07/2021 | 60 | NOVELTY CONSTRUCTION | 35.58 | 35.58 | 100 | 0
869 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Aurangabad (313981) of Aurangabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District (PART-I) , SM/08275 | Retrofitting | Material Requisition To Resource Division | 540/9/MURD | 25/02/2022 | 0 | Resource Division | 42.35 | 0 | 0 | 0
870 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Aurangabad (313981) of Aurangabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District (PART-I) , SM/08275 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of AURANGABAD (Village code 313981) under AURANGABAD Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte.Scheme ID 0005184162 | 3976/MURD | 21/12/2021 | 180 | S. ENTERPRISE (PROP: SAIRUL ISLAM) | 309.91 | 137.5 | 44.37 | 1
871 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jitpur, Jotkanai, Par Raghunathpur, Radhakantapur (314669,314674, 314677, 314670) of Jitpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08278 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Radhakantapur(Village code 314670) under Jitpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723374 (Sl No-12) | 3286/MURD | 05/10/2021 | 180 | M/S M.S. ENTERPRISE | 51.18 | 49.14 | 100 | 1
872 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jitpur, Jotkanai, Par Raghunathpur, Radhakantapur (314669,314674, 314677, 314670) of Jitpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08278 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-17 | 361-MSD/22-23 | 19/10/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 35.91 | 0 | 0 | 0
873 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jitpur, Jotkanai, Par Raghunathpur, Radhakantapur (314669,314674, 314677, 314670) of Jitpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08278 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of JITPUR (Village code 314669) under JITPUR Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723374 | 4024/MURD | 24/12/2021 | 180 | SUJIT KUMAR SAHA | 119 | 91.68 | 77.04 | 1
874 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jitpur, Jotkanai, Par Raghunathpur, Radhakantapur (314669,314674, 314677, 314670) of Jitpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08278 | Retrofitting | Material Requisition To Resource Division | 21/MURD | 05/01/2022 | 0 | Resource Division | 15.08 | 0 | 0 | 0
875 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jitpur, Jotkanai, Par Raghunathpur, Radhakantapur (314669,314674, 314677, 314670) of Jitpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08278 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Par Raghunathpur (Village code 314677) under Jitpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723374 in the District of Murshidabad. (Sl No-11) | 181/MURD | 19/01/2021 | 180 | UMWELT ENGINEER PVT LTD | 79.2 | 47.39 | 59.84 | 0
876 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jitpur, Jotkanai, Par Raghunathpur, Radhakantapur (314669,314674, 314677, 314670) of Jitpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08278 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kanai (Village code 314674) under Jitpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID ¿ 0001723374 in the District of Murshidabad. (Sl No-10) | 180/MURD | 19/01/2021 | 180 | UMWELT ENGINEER PVT LTD | 81.67 | 94.41 | 193.87 | 1
877 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jitpur, Jotkanai, Par Raghunathpur, Radhakantapur (314669,314674, 314677, 314670) of Jitpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08278 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Uttar Gopalpur (Village code 314744) under Purusottampur and Jitpur Ground Water Based Water Supply Scheme under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad. | 031/MURD | 05/01/2021 | 60 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 9.28 | 0 | 0 | 0
878 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jitpur, Jotkanai, Par Raghunathpur, Radhakantapur (314669,314674, 314677, 314670) of Jitpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas , SM/08278 | Retrofitting | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 372 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Radhakantapur (Village code 314670) under Jitpur Ground water based water supply scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0001723374) | 704/MURD | 14/03/2022 | 20 | M/S M.S. ENTERPRISE | 14.28 | 12.1 | 100 | 1
879 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Jayenpur (Village code 314900) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1865/BD-I | 07/10/2021 | 90 | AJAY MONDAL | 26.81 | 19.86 | 74.08 | 1
880 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Amaipara (Village code 314910) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1875/BD-I | 07/10/2021 | 90 | AJAY MONDAL | 27.02 | 20.95 | 100 | 1
881 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chaipara (Village code 314896) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2209/BD-I | 10/12/2021 | 20 | PRATIMA CONSTRUCTION | 5.21 | 5 | 100 | 1
882 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 83.63 | 1
883 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Goljarbag (Village code 314893) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1861/BD-I | 07/10/2021 | 90 | M/S. SUKUMAR SINHA | 42.48 | 0 | 0 | 0
884 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under AMAIPARA (Zone-A) Surface Water based Water Supply Scheme of Central Sector (Part-I) under Murshidabad -Jiaganj Block in Murshidabad District under Berhampore Division-I, PHE Dte. | 516/BD-I | 25/07/2023 | 90 | M/S. M.G. CONSTRUCTION | 102.61 | 0 | 0 | 0
885 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub Division, PHE Dte. period for 01.01.2023 to 31.12.2023. | 1388/BD-I | 23/12/2022 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 4.77 | 262.69 | 90
886 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Bahadurpur (Village code 314894) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1860/BD-I | 07/10/2021 | 90 | M/S. SUKUMAR SINHA | 21.72 | 0 | 0 | 0
887 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bilkandi (Village code 314904) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1879/BD-I | 07/10/2021 | 90 | SANJAY BISWAS | 33.81 | 24.37 | 72.09 | 90
888 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Begampur (Village code 314908) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 1910/BD-I | 08/10/2021 | 30 | PRADIP KUMAR SAHA | 2.61 | 0 | 0 | 0
889 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sadek Sarai (Village code 314897) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 118/BD-I | 03/02/2022 | 30 | ANKUSH CONSTRUCTION & CO. | 11.58 | 8.85 | 76.44 | 1
890 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chandipur(Village code 314903) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2210/BD-I | 10/12/2021 | 30 | ASHIS KUMAR BHATTACHARYYA | 24.26 | 22.55 | 92.94 | 100
891 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.01.2023 to 31.07.2023. | 1387/BD-I | 23/12/2022 | 212 | SOUVIK HALDER | 1.06 | 2.47 | 146.98 | 70
892 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Payasti Katiganga (Village code 314891) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 1911/BD-I | 08/10/2021 | 30 | PRAVAT KUMAR GHOSH | 2.97 | 2.27 | 100 | 1
893 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar (Village code 314909) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1876/BD-I | 07/10/2021 | 60 | GOUTAM KUMAR CHAUDHURI | 6.69 | 6.11 | 100 | 1
894 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bagdhar (Village code 314906) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1877/BD-I | 07/10/2021 | 60 | MAA SANKARI ENTERPRISE | 20.03 | 17.93 | 100 | 1
895 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Bhrigurambati (Village code 314892) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1862/BD-I | 07/10/2021 | 60 | AZAD ENTERPRISE | 12.67 | 11.77 | 100 | 1
896 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Tantipara (Village code 314895) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1859/BD-I | 07/10/2021 | 60 | BIJOY SINGHA | 9.03 | 6.19 | 100 | 1
897 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ambarnagar (Village code 314905) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1878/BD-I | 07/10/2021 | 90 | DOBAY CONSTRUCTION | 24.01 | 19.7 | 100 | 1
898 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raichandpur (Village code 314902) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1880/BD-I | 07/10/2021 | 90 | DOBAY CONSTRUCTION | 21.62 | 18.26 | 100 | 1
899 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Gujasti Rampur (Village code 314898) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1864/BD-I | 07/10/2021 | 60 | N.H ENTERPRISE | 13.74 | 11.84 | 100 | 1
900 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kanchannagar (Village code 314907) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 1912/BD-I | 08/10/2021 | 30 | ANKITA ENTERPRISE | 3.35 | 2.8 | 100 | 1
901 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dakshin Ganespur (Village code 314938) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1874/BD-I | 07/10/2021 | 90 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 21.49 | 18.74 | 100 | 1
902 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Narayanpur (Village code 314899) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 117/BD-I | 03/02/2022 | 30 | ANKUSH CONSTRUCTION & CO. | 13.73 | 11.88 | 100 | 100
903 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Amaipara Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | 2223/BD-I | 15/12/2021 | 90 | SOM CONSTRUCTION AGENCY | 83.92 | 83.05 | 100 | 1
904 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baliapukur(Village code 314901) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 217/BD-I | 24/02/2022 | 45 | DAS TRADING CO | 36.42 | 27.95 | 100 | 1
905 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08911 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Uttar Ganeshpur (Village code 314890) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1863/BD-I | 07/10/2021 | 60 | DOBAY CONSTRUCTION | 18.6 | 16.1 | 100 | 100
906 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08914 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Goraipur,Sadipur and Sundalpur (Village code 315417,315418 ,315431) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1830/BD-I | 05/10/2021 | 40 | M/S SINHA & SONS | 40.25 | 26.91 | 66.85 | 1
907 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08914 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 68.93 | 1
908 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08914 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hogaldanga (Village code 315432) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1829/BD-I | 05/10/2021 | 60 | NIRMAL UDYOG | 51.89 | 0 | 0 | 0
909 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08914 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hajidanga,Baradha,Ganti Baisnab Charan,Kaladanga and Charislampur (Village code 315434,315435 ,315437,315436,315438) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1831/BD-I | 05/10/2021 | 80 | KAMIRUL SK AND CO. | 73.49 | 65.78 | 89.51 | 1
910 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08914 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ruharpara,Baliharpur,Habipur,Dhanaipur,Mirpur and Garamgari (Village code 315426,315427 ,315428,315429,315430,315439) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1832/BD-I | 05/10/2021 | 100 | M/S GUHA AND ROY ENTERPRISE | 97.55 | 81.51 | 83.56 | 0
911 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08914 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nutanpara and Madanpur (Village code 315424,315425) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1833/BD-I | 05/10/2021 | 80 | M/S GUHA AND ROY ENTERPRISE | 81.18 | 80.7 | 99.42 | 1
912 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08914 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chhayghari (Village code 315433) under Habibpur (Zone-G) Water Supply Scheme of Central Sector Part-I in Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-08) | 1885/BD-I | 07/10/2021 | 180 | M/S S.DAS & ENTERPRISE | 275.21 | 151.91 | 55.2 | 1
913 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08914 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Habibpur Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | 2226/BD-I | 15/12/2021 | 90 | KUNDU CONSTRUCTION | 72.9 | 60.13 | 82.49 | 1
914 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur , SM/09739 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHULA G.P. under Murshidabad Division, P.H.E.Dte. | 349/BSD | 27/08/2021 | 30 | IMAGIN COMMUNICATION | 4.16 | 4.16 | 100 | 0
915 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur , SM/09739 | Retrofitting | Laying of 160mm dia UPVC pipeline and road restoration work for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Char Mahula (village code 315354) under Char Mahula Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 148/BSD | 12/04/2022 | 30 | SANJIB GHOSH | 4.84 | 4.84 | 100 | 0
916 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur , SM/09739 | Retrofitting | Laying of 110mm dia UPVC pipeline in connection providing Functional Household Tap Connection FHTC in connection with JJM and Jal Swapna under command area of village of Char Mahula Village code 315354 under Char Mahula W/S Scheme in the dist of MSD PHE DTE. Tender no - 182 of 21-22 by AE BSD | 03-MSD/22-23 | 14/04/2022 | 0 | S. DUTTA | 4.81 | 0 | 0 | 0
917 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur , SM/09739 | Retrofitting | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Char Mahula (village code 315354) under Char Mahula Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 91/BSD | 07/03/2022 | 15 | S. DUTTA | 4.81 | 0 | 0 | 0
918 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur , SM/09739 | Retrofitting | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | 480/MURD | 22/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 0 | 0 | 0
919 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Mahula ( 315354 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur , SM/09739 | Retrofitting | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 0 | 0 | 1
920 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Pakamati Mahula ( 315353 ) of Char Mahula under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under , SM/09740 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RADHARGHAT-I G.P. under Murshidabad Division, P.H.E.Dte. | 341/BSD | 27/08/2021 | 30 | IMAGIN COMMUNICATION | 4.16 | 4.16 | 100 | 0
921 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bamuha (313962) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad D , SM/09759 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Bamuha, Khidirpur, Khanpur (Nos FHTC-2996 Nos) (Village code-313962,313990,313989) under PRASADPUR Ground Water Based Water Supply Scheme of Suti-II Block and Kalinagar (FHTC-4077 Nos) (Village code-313899) under Raturi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID-0005019110 & 0001723413) | 558/MURD | 28/02/2022 | 180 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 332.59 | 0 | 0 | 0
922 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Maradighi ( 315674 ) of Rejinagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh , SM/09839 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village MARADIGHI (Village Code 315674) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | 3008/MURD | 04/12/2020 | 45 | SUPIA CONSTRUCTION | 11.14 | 9.93 | 50 | 0
923 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Maradighi ( 315674 ) of Rejinagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh , SM/09839 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Pilkhna ( Village Code -315666) under Rejinagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 274/BSD | 24/06/2022 | 30 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 4.84 | 4.54 | 93.82 | 0
924 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Krishnapur (314153) Habitation Manic Chak of Lalgola & adjoining mouzas of under Ground Water Based Water Supply Scheme for Arsenic affected areas of Lalgola Block of Murshidabad District under Murshidabad Division P.H.E Dte . Part- C. | 236/LSD | 11/05/2022 | 30 | M/S.S.S. ENTERPRISE | 4.89 | 0 | 0 | 0
925 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Lalgola (314224) of Lalgola & adjoining mouzas of under Ground Water Based Water Supply Scheme for Arsenic affected areas of Lalgola Block of Murshidabad District under Murshidabad Division P.H.E Dte . Part- B. | 241/LSD | 11/05/2022 | 30 | SOUVIK HALDER | 4.98 | 0 | 0 | 0
926 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Laying of 200 mm dia DI pipeline from Near Shop of Nazir Sk to Jain Temple More, Lalgola including supply of specials in connection with FHTC work of Village of Lalgola (Village Code 314224 ) under Lalgola Ground Water Based Water Supply Scheme under Lalbagh Sub-Division, P.H.Engineering Dte. (Part-A). | 175/LSD | 06/05/2022 | 20 | MADAN MOHAN SASMAL | 2.32 | 2.32 | 100 | 0
927 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Restoration work by cement concrete (1:1.5:3) after laying of DI pipe in connection with FHTC work of Village of Lalgola (Village Code 314224 ) Lalgola Ground Water Based Water Supply Scheme under Lalbagh Sub-Division, P.H.Engineering Dte. | 222/LSD | 11/05/2022 | 30 | MADAN MOHAN SASMAL | 3.94 | 3.91 | 100 | 0
928 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Laying of diffrent dia UPVC pipe line in connection with(FHTC) work at village Krishnapur (Village Code- 314153) under Lalgola Ground Water Supply Scheme for Arsenic affected areas of Lalgola Block under Lalbagh Sub-Division under Murshidabad Division, P.H.Engineering Dte. Part-B. | 232/LSD | 11/05/2022 | 30 | RIZZ ENTERPRISE | 4.56 | 4.55 | 100 | 0
929 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Laying of different dia UPVC pipeline from M.N. Academy more to Rajgurupara in connection with"Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lalgola( Village Code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. | 221/LSD | 11/05/2022 | 30 | SUGATA CHOWDHURY | 4.06 | 4.05 | 100 | 0
930 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Laying of 200 mm dia DI pipeline from Near Shop to Nazir Sk to Head Work Site Lalgola. including supply of specials in connection with FHTC work of Village of Lalgola (Village Code 314224 ) Lalgola Ground Water Based Water Supply Scheme under Lalbagh Sub-Division, P.H.Engineering Dte. (248.M) (Part-B) | 200/LSD | 11/05/2022 | 25 | SUGATA CHOWDHURY | 2.14 | 2.13 | 100 | 0
931 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Krishnapur (314153) Habitation Madiapara of Lalgola & adjoining mouzas of under Ground Water Based Water Supply Scheme for Arsenic affected areas of Lalgola Block of Murshidabad District under Murshidabad Division P.H.E Dte . Part- C. | 227/LSD | 11/05/2022 | 30 | JYOTSNA PUTATUNDA | 4.93 | 4.8 | 100 | 0
932 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Lalgola (314224) of Lalgola & adjoining mouzas of under Ground Water Based Water Supply Scheme for Arsenic affected areas of Lalgola Block of Murshidabad District under Murshidabad Division P.H.E Dte . Part- E. | 228/LSD | 11/05/2022 | 30 | AEF ENTERPRISE | 4.84 | 3.72 | 100 | 0
933 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Restoration of road for laying of different dia UPVC/CI/DI pipelines in connection with FHTC work from BDO Office More to M.N. Academy Ground area under Lalgola Water Supply Scheme under Lalbagh Sub-Division P.H.E. Dte. | 294/LSD | 12/07/2022 | 30 | MADAN MOHAN SASMAL | 0.96 | 0.96 | 100 | 0
934 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Restoration of road for laying of different dia UPVC/CI/DI pipelines in connection with FHTC work from Jain Mandir to PHE OHR more via Rathbari more, Battala more & PWD (Roads) more under Lalgola Water Supply Scheme under Lalbagh Sub-Division P.H.E. Dte. | 295/LSD | 12/07/2022 | 30 | SUGATA CHOWDHURY | 4.8 | 4.78 | 100 | 0
935 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bilbarakpara (Village code 314225) under Lalgola Ground Water Based water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005186640 in the District of Murshidabad. (Sl No-01) | 168-MSD/22-23 | 17/05/2022 | 0 | AQUATHERM WATER TREATMENT PVT.LTD. | 90.43 | 0 | 0 | 0
936 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Lalgola (Village code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID 5185583 in the District of Murshidabad. (Sl No-02) | 266-MSD/22-23 | 26/08/2022 | 0 | BIJAY CHOWDHURY | 96.48 | 0 | 0 | 0
937 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BILBARAKPARA (Village Code 314225) under LALGOLA Ground Water Based Water Supply Scheme for arsenic affected areas of LALGOLA Block in the District of Murshidabad. Tender no - 106 of 20-21 by EE MURD | 118-MSD/22-23 | 10/05/2022 | 0 | AQUATHERM WATER TREATMENT PVT.LTD. | 31.91 | 0 | 0 | 0
938 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Allied work for Laying of different dia UPVC Pipeline at Radhabagh area in connection with'Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bilborakopra ( Village Code 314225) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. (Part-B). | 112-MSD/22-23 | 06/05/2022 | 0 | SUGATA CHOWDHURY | 4.7 | 0 | 0 | 0
939 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Allied work for laying of different dia UPVC pipeline at radhabagh area in connection with Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BILBORAKOPRA (Village Code 314225) under LALGOLA Ground Water Based Water Supply Scheme for arsenic affected areas of LALGOLA Block in the District of Murshidabad. Tender no - 59 of 21-22 by AE LSD | 113-MSD/22-23 | 06/05/2022 | 0 | MADAN MOHAN SASMAL | 4.84 | 0 | 0 | 0
940 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Lalgola (Village code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID 5185583 in the District of Murshidabad. (Sl No-02) | 123-MSD/22-23 | 07/05/2022 | 0 | BIJAY CHOWDHURY | 37.56 | 0 | 0 | 0
941 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Laying of different dia UPVC Pipeline form Jain Mondir to Fish Market More & H/O of Kailash Vakat to Lalgola P.S. in connection with'Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lalgola( Village Code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. | 189-MSD/22-23 | 29/06/2022 | 0 | MADAN MOHAN SASMAL | 2.98 | 0 | 0 | 0
942 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Allied work for Laying of different dia UPVC Pipeline at Krishnapur area (Near Hospital) in connection with'Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bilborakopra ( Village Code 314225) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. | 214-MSD/22-23 | 20/07/2022 | 0 | PROSENJIT DAS | 4.7 | 0 | 0 | 0
943 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Allied work for laying of different dia UPVC pipeline at radhabagh area in connection with Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BILBORAKOPRA (Village Code 314225) under LALGOLA Ground Water Based Water Supply Scheme for arsenic affected areas of LALGOLA Block in the District of Murshidabad. Tender no - 57 of 21-22 by AE LSD | 115-MSD/22-23 | 06/05/2022 | 0 | DEB SANKER BHATTACHARYA | 4.81 | 0 | 0 | 0
944 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Laying of different dia UPVC Pipeline form H/O of Niaz Biswas to H/O of Moni Saha & H/O of Helal Maulabi to Fish Market More in connection with'Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lalgola( Village Code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Lalgola Block under Murshidabad Division P.H.E. Dte. | 190-MSD/22-23 | 29/06/2022 | 0 | SUGATA CHOWDHURY | 4.28 | 0 | 0 | 0
945 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Laying of diffrent dia UPVC pipe line in connection with (FHTC) work at village Lalgola (Village Code- 314224) under Lalgola Ground Water Supply Scheme for Arsenic affected areas of Lalgola Block under Lalbagh Sub-Division under Murshidabad Division, P.H.Engineering Dte. Part-A. | 233/LSD | 11/05/2022 | 30 | M/S JOY MA BANAMALI | 4.99 | 2.9 | 58.16 | 0
946 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bilbarakpara (Village code 314225) under Lalgola Ground Water Based water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005186640 in the District of Murshidabad. (Sl No-01) | 559/MURD | 08/02/2021 | 180 | AQUATHERM WATER TREATMENT PVT.LTD. | 255.81 | 8.89 | 100 | 0
947 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 0 | 0 | 100
948 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Laying of diffrent dia UPVC pipe line in connection with (FHTC) work at village Krishnapur (Village Code- 314153) under Lalgola Ground Water Supply Scheme for Arsenic affected areas of Lalgola Block under Lalbagh Sub-Division under Murshidabad Division, P.H.Engineering Dte. Part-A. | 231/LSD | 11/05/2022 | 30 | AEF ENTERPRISE | 4.99 | 4.99 | 100 | 0
949 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Lalgola (Village code 314224) under Lalgola Ground Water Based Water Supply Scheme for Arsenic Affected Area of Lalgola Block, under Murshidabad Division, PHE Dte. Scheme ID 5185583 in the District of Murshidabad. (Sl No-02) | 46/MURD | 06/01/2021 | 180 | BIJAY CHOWDHURY | 152 | 0 | 0 | 0
950 | MURSHIDABAD | Murshidabad Division | Functional Household Tap Connections (FHTC) of Mouza Lalgola, Bilborakpara, Durgapur,Arazi Narayanpur of Lalgola Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Lalgola Block of Murshidabad District Under Murshidabad Division Ph , SM/10606 | Retrofitting | Allied work for laying of 110 mm dia upvc pipeline at Minister para-area in connection with " Retrofitting providing FHTC in connection with JJM under command area of village of Lalgola (village code-314224) under Lalgola Ground Water Based Water Supply Scheme for arsenic affected areas of Lalgola Block under Murshidabad Division, PHE Dte. | 3545/MURD | 17/11/2023 | 30 | SUGATA CHOWDHURY | 2.18 | 1.83 | 100 | 70
951 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10610 | Augmentation | Material Requisition To Resource Division | 2507/G/MURD | 31/08/2022 | 0 | Resource Division | 26.31 | 0 | 0 | 0
952 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10610 | Augmentation | Material Requisition To Resource Division | 1180/MURD/08 | 29/04/2023 | 0 | Resource Division | 26.31 | 0 | 0 | 0
953 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10610 | Augmentation | Material Requisition To Resource Division | MURD/2481/10 | 04/09/2024 | 0 | Resource Division | 15.32 | 0 | 0 | 0
954 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10610 | Augmentation | Formal Work Order for Augmentation of Faridpur Zone-I Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | 2085/MURD | 27/07/2022 | 1040 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 477.83 | 370.09 | 77.45 | 75
955 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10610 | Augmentation | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Tikar Bariakalkihara (314642),of Faridpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Division Phe Dte. | 1199/MURD | 10/05/2022 | 45 | NADIA TUBEWELLS | 16.6 | 9.31 | 100 | 100
956 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10011 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (MALIBARI PWSS Scheme, Block - Raninagar-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3264/MURD | 05/10/2021 | 60 | RADIANT | 5.89 | 5.89 | 100 | 1
957 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10011 | Augmentation | Material Requisition To Resource Division | 3052/F/MURD | 17/11/2022 | 0 | Resource Division | 23.33 | 0 | 0 | 0
958 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10011 | Augmentation | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Malibari Water Supply Scheme of 3rd TW Site under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3064/MURD | 17/11/2022 | 30 | SUJIT KUMAR SAHA | 9.21 | 8.09 | 87.84 | 0
959 | MURSHIDABAD | Berhampore Mechanical | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10011 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-III of Malibari ground water based water supply scheme under Block- Raninagar-II, Dist. Murshidabad under MEDB, PHE Dte. | 3774/MEDB | 03/11/2023 | 92 | ARINDAM MAJUMDAR | 11.02 | 0 | 0 | 0
960 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10011 | Augmentation | Formal work order for laying Distribution System (HDPE Pipe) of for AUGMENTATION of Ground Water Based MALIBARI PWSS to Accommadate FHTC at Raninagar- II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | 1316/MURD | 20/05/2022 | 120 | NAYLA CONSTRUCTION | 217.49 | 183.08 | 100 | 100
961 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10011 | Augmentation | Material Requisition To Resource Division | 2507/C/MURD | 31/08/2022 | 0 | Resource Division | 9.22 | 0 | 0 | 0
962 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10011 | Augmentation | Material Requisition To Resource Division | 1167/MURD/3 | 28/04/2023 | 0 | Resource Division | 27.6 | 0 | 0 | 0
963 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10011 | Augmentation | Material Requisition To Resource Division | MURD/2991/03 | 13/11/2024 | 0 | Resource Division | 30.01 | 0 | 0 | 0
964 | MURSHIDABAD | Berhampore Mechanical | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10011 | Augmentation | NEW SERVICE CONNECTION AT MALIBARI PHI, ID304238384 | 287/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 12.87 | 0 | 0 | 0
965 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10011 | Augmentation | Construction of Two nos Pump House cum Chlorine Room with sanitary and Water Supply Arrangement ,Construction of Boundary Wall of 200 m, Construction of RCC approach road (3 Mtr Wide)of 100 mtr length, Laying of Rising Main, Construction of 450 Cum OHR, Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works and Land Development Works for Augmentation of Malibari Water Supply scheme at Raninagar-II Block under Murshidabad Division,PHE Dte. | 1816/MURD | 20/06/2024 | 560 | M/S B.M. INDUSTRIES | 282.92 | 0 | 0 | 50
966 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10011 | Augmentation | Balance & Allied Work for Laying Distribution System , FHTC of Malibari Water Supply Scheme in Raninagar-II Block ,under Murshidabad Division , PHE.Dte. | 1986/MURD | 08/07/2024 | 363 | DAS TRADING CO. | 95.72 | 0 | 0 | 60
967 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10011 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 100 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for MALIBARI Ground Based Water Supply Scheme in Raninagar -II Block under Murshidabad Division , PHE Dte. | 1024/MURD | 05/05/2025 | 60 | M/S. S. DAS AND ENTERPRISE | 40.44 | 0 | 0 | 0
968 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10011 | Augmentation | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bilchatra (Village Code -314568) under Malibari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184027) | 581/MURD | 09/02/2021 | 60 | ULTRA CONSTRUCTION. | 27.7 | 5.11 | 100 | 1
969 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Malibari PWSS To Accommodate FHTC In Raninagar-II Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10011 | Augmentation | Formal work order for Functional Household Tap Connections (FHTC) in Bilchatra & Malibari Village ( Village Code -314568 ,314569 ) in connection with Augmentation of Malibari Ground Water Based Water Supply Scheme Raninagar-II Block under Murshidabad Division P.H.E Dte. | 163/MURD | 17/01/2023 | 60 | KUNDU CONSTRUCTION | 170.31 | 167.79 | 100 | 95
970 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10631 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional Household Connection of different existing PWSS(Jalangi PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 183-MSD/22-23 | 13/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 16.77 | 0 | 0 | 0
971 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10631 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-III/ Part-B Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3057/MURD | 17/11/2022 | 45 | NADIA TUBEWELLS | 23.55 | 20.03 | 100 | 100
972 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10631 | Augmentation | Material Requisition To Resource Division | 2507/B/MURD | 31/08/2022 | 0 | Resource Division | 74.09 | 0 | 0 | 0
973 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10631 | Augmentation | New connection charge for Jalangi W/S Scheme (Part-B) Zone-III, P/H No.-III. | 92/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 0.9 | 0 | 0 | 0
974 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10631 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of JALANGI , Zone- III/Part-B ground water based water supply scheme under Block- Jalangi, Dist. Murshidabad under MEDB, PHE Dte. | 3771/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 20.33 | 15.79 | 77.69 | 50
975 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10631 | Augmentation | NEW SERVICE CONNECTION AT JALANGI PWSS Z3 PLOT LR 538 MURSHIDABAD ID 304238698 | 297/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 9.63 | 0 | 0 | 0
976 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10631 | Augmentation | ADDL SERVICE CONNECTION CHARGES AT JOYKRISHNAPUR ,JALANGI PWSS, PART B,Z-3,PH3, ID 860279298 | 212/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 5.14 | 0 | 0 | 0
977 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10631 | Augmentation | Payment Cost of repairing road from Biswaspara (SH) to Jortala More PWD Road under Jalangi Block in Murshidabad District vide packeage no WB 13-409. | 303-MSD/2024-25 | 29/08/2024 | 0 | EXECUTIVE ENGINER WBSRDA MURSHIDABAD DIVISION | 32.83 | 0 | 0 | 0
978 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10631 | Augmentation | Formal Work Order for Augmentation of Jalangi Zone III Part B Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | 1806/MURD | 11/07/2022 | 1270 | HOQUEDAR ALI | 149.27 | 0 | 0 | 50
979 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10632 | Augmentation | New connection charge for Jalangi W/S Scheme (Part-B) Zone-II, P/H No.-III. | 88/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 1.27 | 0 | 0 | 0
980 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10632 | Augmentation | New connection charge for Jalangi W/S Scheme (Part-B) Zone-II, P/H No.-IV. | 87/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 1.35 | 0 | 0 | 0
981 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10632 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of JALANGI , Zone- II/Part-B ground water based water supply scheme under Block- Jalangi, Dist. Murshidabad under MEDB, PHE Dte. | 3769/MEDB | 03/11/2023 | 92 | P. K. ENGINEERING | 22.5 | 17.94 | 79.74 | 65
982 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10632 | Augmentation | Material Requisition To Resource Division | MURD/2481/09 | 04/09/2024 | 0 | Resource Division | 14.57 | 0 | 0 | 0
983 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10632 | Augmentation | ADDL SERVICE CONNECTION CHARGES AT SAHEBRAMPUR BOLAITALA , JALANGI PWSS PART B,Z2,PH2 ID 860281603 | 211/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 7.15 | 0 | 0 | 0
984 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10632 | Augmentation | addl service connection charges at sahebrampur palpara jalangi pwss part b,z 2,ph 4 ID 860279296 | 210/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 8.59 | 0 | 0 | 0
985 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10632 | Augmentation | Formal Work Order for Augmentation of Jalangi Zone II Part-B Ground Water Based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) within Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | 1691/MURD | 28/06/2022 | 1099 | KISMAT ARA BEGAM | 131.01 | 53.83 | 41.09 | 75
986 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10632 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-II/ Part-B Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3055/MURD | 17/11/2022 | 45 | MAMATA USHA ENTERPRISE | 23.58 | 19.41 | 100 | 1
987 | MURSHIDABAD | Murshidabad Division | Source Augmentation of Functional Household Tap Connections (FHTC) of Mouza Habaspur (314487) of Habaspur under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Bhagwangola-I Block of Murshidabad District Under Murshidabad Division Phe , SM/11162 | Augmentation | Providing Functional Household Tap Connections ( 210 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Habaspur ( Village Code -314487) under Habaspur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhawangola-II Block under Murshidabad Division P.H.E Dte. | 2212/MURD | 02/08/2024 | 272 | NOBEL CONSTRUCTION | 7.61 | 0 | 0 | 100
988 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10679 | Augmentation | Material Requisition To Resource Division | 2780/F/MURD | 01/10/2022 | 0 | Resource Division | 27.07 | 0 | 0 | 0
989 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10679 | Augmentation | Material Requisition To Resource Division | 1180/MURD/05 | 29/04/2023 | 0 | Resource Division | 220.24 | 0 | 0 | 0
990 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10679 | Augmentation | Formal Work Order for Augmentation of KARIMPUR Jalangi Zone-I( Part A) Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | 2047/MURD | 26/07/2022 | 180 | M/S. S. DAS AND ENTERPRISE | 692.97 | 479.45 | 69.19 | 40
991 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10679 | Augmentation | Balance Work for Laying of Distribution System for Augmentation of Karimpur-Jalangi Zone-I Part-A Piped water supply scheme to accommodate FHTC (Functional House Hold Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division, PHE. Dte. | 65/MURD | 08/01/2024 | 60 | S.S.INFRASTRUCTURE | 134.77 | 14.7 | 71.69 | 10
992 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10679 | Augmentation | Material Requisition To Resource Division | MURD/2481/06 | 04/09/2024 | 0 | Resource Division | 27.07 | 0 | 0 | 0
993 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur , SM/12582 | Augmentation | Material Requisition To Resource Division | 196/BD-I/11 | 09/02/2024 | 0 | Resource Division | 70.91 | 0 | 0 | 0
994 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur , SM/12582 | Augmentation | NEW CONNECTION AT KASBA BAHADURPUR PH-1 |  | 03/09/2024 | 0 | WBSEDCL | 5.46 | 0 | 0 | 0
995 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur , SM/12582 | Augmentation | Formal Work order for Augmentation of KASBA BAHADURPUR Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1454/BD-I | 17/01/2023 | 1445 | DECON INDIA | 444.11 | 216.93 | 48.85 | 70
996 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur , SM/12582 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Kasba Bahadurpur ground water based water supply scheme under Block_ Bhagwangola-I Dist. - Murshidabad under MEDB, PHE Dte. | 3732/MEDB | 03/11/2023 | 1300 | S.P. ENTERPRISE (BAGUIHATI) | 22.37 | 0 | 0 | 8
997 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur , SM/12582 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Kasba Bahadurpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | 1361/BD-I | 21/12/2022 | 30 | KAKALI ENTERPRISE | 2.41 | 1.66 | 100 | 100
998 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur , SM/12582 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kasba Bahadurpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | 1809/BD-I | 31/03/2023 | 30 | HARUN ALL RASHID & BROTHERS | 17.66 | 14.75 | 100 | 100
999 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur , SM/12582 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KASBA BAHADURPUR Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 259/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.96 | 2.95 | 100 | 0
1000 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur , SM/12582 | Augmentation | Allied work for the work of Augmentation of KASBA BAHADURPUR Piped water supply scheme to accommodate Bored Cast-in-situ_M30_grade 450 mm.R.C.C pile for construction of OHR, Pump House, Boundary Wall, Service Road and laying of distribution pipeline under Jal Jeevan Mission within Bhagwangola-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | 1470/BD-I | 06/09/2024 | 149 | DECON INDIA | 96.16 | 0 | 0 | 75
1001 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Kasba Bahadurpur , SM/12582 | Augmentation | Improvement of R.C.C Elevated Reservoir (350 Cum) of Ground Water Based Supply Scheme for Augmentation of Kasba Bahadurpur water supply scheme of Bhagwangola-I block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | 894/BD-I | 06/06/2024 | 240 | DEBOJYOTI CONSTRUCTION | 8.26 | 0 | 0 | 100
1002 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-II BLOCK-RAGHUNATHGANJ- II , SM/10797 | Augmentation | Material Requisition To Resource Division | 1167/MURD/7 | 28/04/2023 | 0 | Resource Division | 40.3 | 0 | 0 | 0
1003 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-II BLOCK-RAGHUNATHGANJ- II , SM/10797 | Augmentation | Material Requisition To Resource Division | MURD/2991/01 | 13/11/2024 | 0 | Resource Division | 41.24 | 0 | 0 | 0
1004 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-II BLOCK-RAGHUNATHGANJ- II , SM/10797 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under KASIADANGA ground water based water supply scheme under Block_ RAGHUNATHGANJ-II Dist. - Murshidabad under MEDB, PHE Dte. | 4336/MEDB | 29/12/2023 | 459 | BHAGIRATHI JUTE AND HOLDINGS PVT LTD | 22.92 | 0 | 0 | 40
1005 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-II BLOCK-RAGHUNATHGANJ- II , SM/10797 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 500 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Kasiadanga Zone I & II PWSS in Raghunathganj II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | 3190/MURD | 12/10/2023 | 365 | ASTRA | 861.48 | 0 | 0 | 0
1006 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-II BLOCK-RAGHUNATHGANJ- II , SM/10797 | Augmentation | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 0 | 20
1007 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur , SM/12584 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Hasanpur ground water based water supply scheme under Block- Bhagawangola-II, Dist. Murshidabad under MEDB, PHE Dte. | 3731/MEDB | 03/11/2023 | 92 | GANGULI ELECTRICAL CO. | 11.46 | 0 | 0 | 10
1008 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur , SM/12584 | Augmentation | Material Requisition To Resource Division | 196/BD-I/1 | 09/02/2024 | 0 | Resource Division | 2.08 | 0 | 0 | 0
1009 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur , SM/12584 | Augmentation | Augmentation of Hasanpur Piped water supply scheme to accommodate construction of OHR,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Swapna in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 831/BD-I | 01/09/2023 | 310 | A ONE CONSTRUCTION | 238.41 | 0 | 0 | 0
1010 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur , SM/12584 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HASANPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 272/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.53 | 2.53 | 100 | 0
1011 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur , SM/12584 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Hasanpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | 1366/BD-I | 21/12/2022 | 30 | SARIFUL ISLAM | 2.49 | 2.45 | 100 | 100
1012 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur , SM/12584 | Augmentation | Replacement of sand layers, Activated Alumina & existing gravel for Modified Sujapur Sadipur Model after washing of AIRP allied (Capacity 30.50 Cum/hr) at Hasanpur Water Supply Scheme under Jal Jivan Mission of Bhagwangola-II Block under Berhampore Div-I, Murshidabad PHE Dte. | 925/BD-I | 07/06/2024 | 30 | M/S GOUTAM CHAKRABORTY | 22.46 | 22.43 | 100 | 100
1013 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur , SM/12584 | Augmentation | Improvement of R.C.C Elevaced Reservoir (136 Cum) of Ground Water Based Supply Scheme for Augmentation of Hasanpur Water Supply Scheme of Bhagwangola-II block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | 935/BD-I | 10/06/2024 | 240 | REBEKA MONDAL | 4.85 | 4.71 | 100 | 100
1014 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur , SM/12584 | Augmentation | Balance works for Improvement of existing AIRP ( Modified Sujapur Sadipur Model, Capacity 30.50 Cum/hr) and alled works at Hasanpur Water Supply Scheme under Jal Jeevan Mission within Bhagwangola-II Block under Berhampore Division-I, PHE Dte. in the district of Murshidabad.. | 761/BD-I | 22/05/2025 | 30 | M/S GOUTAM CHAKRABORTY | 2.99 | 0 | 0 | 100
1015 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Sinkaipur (314775) of Azamatpur Ground water based water supply scheme for arsenic affected areas of Raninagar - I Block in Murshidabad District under Murshidabad Division, P.H.E.D , SM/11219 | Augmentation | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sinkaipur (Village code 314775) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte Scheme ID - 0005019112 in the District of Murshidabad. | 1617/MURD | 28/06/2021 | 60 | DAS ENTERPRISE (PROP-DIPAK DAS) | 5.14 | 0 | 0 | 0
1016 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , SM/11568 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (SURANGAPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3274/MURD | 05/10/2021 | 60 | RADIANT | 15.07 | 5.02 | 100 | 1
1017 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , SM/11568 | Augmentation | Material Requisition To Resource Division | 702/MURD | 13/03/2023 | 0 | Resource Division | 48.15 | 0 | 0 | 0
1018 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , SM/11568 | Augmentation | Material Requisition To Resource Division | 1180/MURD/17 | 29/04/2023 | 0 | Resource Division | 48.15 | 0 | 0 | 0
1019 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , SM/11568 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Surangapur Zone-II Water Supply Scheme at HW Site & 2nd TW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte | 383/MURD | 10/02/2023 | 45 | MAMATA USHA ENTERPRISE | 23.58 | 20.51 | 86.97 | 100
1020 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , SM/11568 | Augmentation | Hiring of Diesel driven Bolero/ Equivalent four wheeler car for the official use of the Executive Engineer under Office of the Executive Engineer, Mechanical/Electrical Division, PHE Dte. In the District of Murshidabad. | 886/AE-II/MEDB | 12/08/2022 | 121 | M/S SAJAHAN CHOWDHURY | 0.59 | 1.43 | 241.38 | 10
1021 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , SM/11568 | Augmentation | Hiring of Diesel driven Bolero/Equivalent four wheeler car for the official use of the Assistant Engineer-I under Office of the Executive Engineer, Mechanical/electrical Division, PHE Dte. in the district of Murshidabad. | 656/AE/MEDB | 31/03/2023 | 183 | M/S SAJAHAN CHOWDHURY | 0.9 | 2.36 | 263.38 | 10
1022 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , SM/11568 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I, II & III under SURANGAPUR (ZONE- II ),Part-A ground water based water supply scheme under Block_ Nowda Dist. - Murshidabad under MEDB, PHE Dte. | 1881/MEDB | 16/06/2023 | 92 | GHOSH BROTHERS | 33.54 | 0 | 0 | 40
1023 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , SM/11568 | Augmentation | Construction of Boundary wall at H/O site, land Development & Approach Road in connection with Augmentation of Surangapur Zone - II PWSS under Murshidabad Division , PHE Dte. Length -266 mtr. | 82/MURD | 09/01/2024 | 60 | BENGAL ENTERPRISE (PROP:-HADIKUL MOLLA) | 29.85 | 16.77 | 56.17 | 80
1024 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , SM/11568 | Augmentation | Material Requisition To Resource Division | 1811/MURD/09 | 20/06/2024 | 0 | Resource Division | 38.22 | 0 | 0 | 0
1025 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , SM/11568 | Augmentation | NEW CONNECTION SURANGAPUR Z-II PH-II | 483/WBSEDCL-JJM | 21/03/2024 | 0 | WBSEDCL | 12.41 | 0 | 0 | 0
1026 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , SM/11568 | Augmentation | Laying of distribution pipe line of 280 mm dia. HDPE pipe line From Node Point J-22 to J-27 ,J-6 to J-822 & J-82 to J-83 and Laying of 150, 250 mm dia ( For casing ) at Surangapur Zone -II PWSS under Murshidabad Division , PHE Dte. | 53/MURD | 05/01/2024 | 30 | M/S GUHA AND ROY | 30.62 | 20.61 | 67.3 | 100
1027 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , SM/11568 | Augmentation | Formal Work Order for Augmentation of SURANGAPUR Zone-II (Part -A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 2417/MURD | 22/08/2022 | 922 | M/S GUHA AND ROY | 343.47 | 293.96 | 85.59 | 100
1028 | MURSHIDABAD | Berhampore Mechanical | NABADURGA AND ADJOINING MOUJAS PWSS , SM/13934 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under NABADURGA ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | 3851/MEDB | 06/11/2023 | 92 | M/S MANABESH ROY | 23.45 | 0 | 0 | 0
1029 | MURSHIDABAD | Murshidabad Division | NABADURGA AND ADJOINING MOUJAS PWSS , SM/13934 | New | Material Requisition To Resource Division | 1278/MURD/16 | 10/05/2023 | 0 | Resource Division | 30.04 | 0 | 0 | 0
1030 | MURSHIDABAD | Murshidabad Division | NABADURGA AND ADJOINING MOUJAS PWSS , SM/13934 | New | Formal Work Order for Construction of 350 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Boundwary Wall Rising Main Connection, of NABADURGA PWSS in Burwan Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. (PART-A) | 782/MURD | 20/03/2023 | 1018 | AMAL KUMAR DAS | 181.67 | 68.56 | 37.74 | 32
1031 | MURSHIDABAD | Murshidabad Division | NABADURGA AND ADJOINING MOUJAS PWSS , SM/13934 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Nabadurga & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at B u r w a n Block under Murshidabad Division, P.H. Engineering Dte. | 1217/MURD | 03/05/2023 | 30 | MAMATA USHA ENTERPRISE | 21.38 | 9.2 | 43.05 | 60
1032 | MURSHIDABAD | Murshidabad Division | NABADURGA AND ADJOINING MOUJAS PWSS , SM/13934 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 0 | 80
1033 | MURSHIDABAD | Berhampore Mechanical | NABADURGA AND ADJOINING MOUJAS PWSS , SM/13934 | New | NEW CONNECTION AT NABADURGA PH-I | 433/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 3.7 | 0 | 0 | 0
1034 | MURSHIDABAD | Berhampore Mechanical | NABADURGA AND ADJOINING MOUJAS PWSS , SM/13934 | New | NEW CONNECTION AT NABADURGA PH-II | 432/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 3.72 | 0 | 0 | 0
1035 | MURSHIDABAD | Murshidabad Division | NABADURGA AND ADJOINING MOUJAS PWSS , SM/13934 | New | Functional Household Tap Connection (FHTC) under Jal Jeevan Mission in the command area of NABADURGA Water Supply Scheme under Murshidabad Division, P.H.E.Dte. (PART-B) | 945/MURD | 05/04/2023 | 667 | M/S. UNIQUE BUILDERS | 152.42 | 0 | 0 | 0
1036 | MURSHIDABAD | Murshidabad Division | NABADURGA AND ADJOINING MOUJAS PWSS , SM/13934 | New | Laying Distribution System of NABADURGA PWSS in Burwan Block , under Murshidabad Division ,PHE.Dte. .(PART-C) | 1138/MURD | 26/04/2023 | 706 | DHIRENDRANATH MONDAL | 341.13 | 119.33 | 34.98 | 60
1037 | MURSHIDABAD | Murshidabad Division | MUNIGRAM AND ADJOINING MOUJAS PWSS , SM/13935 | New | Material Requisition To Resource Division | 1067/MURD/7 | 18/04/2023 | 0 | Resource Division | 1.38 | 0 | 0 | 0
1038 | MURSHIDABAD | Berhampore Mechanical | MUNIGRAM AND ADJOINING MOUJAS PWSS , SM/13935 | New | Electric Service Connection at MUNIGRAM, Application NO.3004466957, ID 304171251 | 194/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 5.16 | 0 | 0 | 0
1039 | MURSHIDABAD | Berhampore Mechanical | MUNIGRAM AND ADJOINING MOUJAS PWSS , SM/13935 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under MUNIGRAM ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | 2017/MEDB | 19/06/2023 | 92 | T. S. CONSTRUCTION | 22.22 | 6.62 | 29.81 | 60
1040 | MURSHIDABAD | Murshidabad Division | MUNIGRAM AND ADJOINING MOUJAS PWSS , SM/13935 | New | Sinking of 02 (Two) Nos. of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MUNIGARM AND ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at KANDI Block under Murshidabad Division, P.H. Engineering Dte. | 2588/MURD | 21/08/2023 | 21 | MAMATA USHA ENTERPRISE | 18.45 | 13.14 | 100 | 80
1041 | MURSHIDABAD | Murshidabad Division | MUNIGRAM AND ADJOINING MOUJAS PWSS , SM/13935 | New | Material Requisition To Resource Division | MURD/439/13 | 08/02/2024 | 0 | Resource Division | 6.34 | 0 | 0 | 0
1042 | MURSHIDABAD | Berhampore Mechanical | MUNIGRAM AND ADJOINING MOUJAS PWSS , SM/13935 | New | AT MUNIGRAM PH 2 ID 304252906 | 362/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 4.88 | 0 | 0 | 0
1043 | MURSHIDABAD | Murshidabad Division | MUNIGRAM AND ADJOINING MOUJAS PWSS , SM/13935 | New | Formal work order for the work of MUNIGRAM & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall, IEP and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | 106/MURD | 13/01/2023 | 931 | PRANAB KUMAR GHOSH | 279.43 | 124.7 | 44.63 | 30
1044 | MURSHIDABAD | Murshidabad Division | SINGADDA AND ADJOINING MOUJAS PWSS , SM/13722 | New | Material Requisition To Resource Division | 1004/MURD/18 | 17/04/2023 | 0 | Resource Division | 24.48 | 0 | 0 | 0
1045 | MURSHIDABAD | Berhampore Mechanical | SINGADDA AND ADJOINING MOUJAS PWSS , SM/13722 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SINGADDA ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | 1897/MEDB | 16/06/2023 | 777 | ABHISEK ENGINEERING CONCERN | 22.61 | 0 | 0 | 30
1046 | MURSHIDABAD | Berhampore Mechanical | SINGADDA AND ADJOINING MOUJAS PWSS , SM/13722 | New | NEW SERVICE CONNECTION PH 2 SINGADDA PWSS ID 304256291 | 343/WBSEDCL-JJM | 12/02/2024 | 0 | WBSEDCL | 4.78 | 0 | 0 | 0
1047 | MURSHIDABAD | Berhampore Mechanical | SINGADDA AND ADJOINING MOUJAS PWSS , SM/13722 | New | NEW SERVICE CONNECTION PH 1 SINGADDA PWSS ID 30425678 | 342/WBSEDCL-JJM | 12/02/2024 | 0 | WBSEDCL | 5.13 | 0 | 0 | 0
1048 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. , SM/14047 | Augmentation | Augmentation of Kazipara zone_II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in JALANGI Block of Murshidabad District under Berhampore Division-I,PHE Dte. | 96/BD-I | 04/05/2023 | 365 | MS JAKIR HOSSAIN | 291.08 | 189.31 | 65.04 | 70
1049 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. , SM/14047 | Augmentation | Material Requisition To Resource Division | 194/BD-I/8 | 09/02/2024 | 0 | Resource Division | 31.41 | 0 | 0 | 0
1050 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. , SM/14047 | Augmentation | NEW SERVICE CONNECTION AT KAJIPARA PH2 Z2 ID 304244955 | 405/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 6.56 | 0 | 0 | 0
1051 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. , SM/14047 | Augmentation | NEW SERVICE CONNECTION AT KAJIPARA PH1 Z2 ID304244954 | 404/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 5.18 | 0 | 0 | 0
1052 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. , SM/14047 | Augmentation | Construction of Service Road for approach and Pump House at Augmentation of KAZIPARA ZONE-II PWSS of Jalangi Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | 1136/BD-I | 15/07/2024 | 60 | U.S BUILDERS | 7.92 | 0 | 0 | 0
1053 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. , SM/14047 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KAJIPARA Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1777/BD-I | 27/03/2023 | 10 | M/S SOBHA & CO | 2.74 | 2.7 | 100 | 100
1054 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- II Piped Water Supply Scheme. , SM/14047 | Augmentation | KAZIPARA ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of JALANGI Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 463/BD-I | 15/03/2024 | 60 | M/S. MONDAL ENTERPRISE 12/6/1, OLD POLICE LINE ROAD, GORABAZAR | 23.55 | 7.41 | 26.7 | 100
1055 | MURSHIDABAD | Murshidabad Division | KANDARA AND ADJOINING MOUJAS PWSS , SM/13487 | New | Material Requisition To Resource Division | 1043/MURD/2 | 17/04/2023 | 0 | Resource Division | 38.45 | 0 | 0 | 0
1056 | MURSHIDABAD | Berhampore Mechanical | KANDARA AND ADJOINING MOUJAS PWSS , SM/13487 | New | New connection charge for Kandara, PWSS, P/H No.- I. | 119/WBSEDCL-JJM | 27/09/2023 | 0 | WBSEDCL | 4.04 | 0 | 0 | 0
1057 | MURSHIDABAD | Berhampore Mechanical | KANDARA AND ADJOINING MOUJAS PWSS , SM/13487 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under KANDARA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | 1877/MEDB | 16/06/2023 | 92 | M/S SAJAHAN CHOWDHURY | 35.2 | 26.87 | 76.33 | 7
1058 | MURSHIDABAD | Berhampore Mechanical | KANDARA AND ADJOINING MOUJAS PWSS , SM/13487 | New | Kandara PH-II Application No- 3004409912 | 250/WBSEDCL-JJM | 16/01/2024 | 0 | WBSEDCL | 7.12 | 0 | 0 | 0
1059 | MURSHIDABAD | Berhampore Mechanical | KANDARA AND ADJOINING MOUJAS PWSS , SM/13487 | New | Kandra PH-III Application No- 3004547697 | 249/WBSEDCL-JJM | 16/01/2024 | 0 | WBSEDCL | 3.98 | 0 | 0 | 0
1060 | MURSHIDABAD | Berhampore Mechanical | KANDARA AND ADJOINING MOUJAS PWSS , SM/13487 | New | Kandara PH-1 Application no-3004409936 |  | 11/01/2024 | 0 | WBSEDCL | 4.04 | 0 | 0 | 0
1061 | MURSHIDABAD | Murshidabad Division | KANDARA AND ADJOINING MOUJAS PWSS , SM/13487 | New | Formal work order for the work of KANDARA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte.( Scheme ID -PH222362286S000) | 89/MURD | 10/01/2023 | 365 | MAHAVIR PUMPS MANUFACTRURING PVT. LTD. | 649.94 | 80.17 | 12.34 | 18
1062 | MURSHIDABAD | Murshidabad Division | KANDARA AND ADJOINING MOUJAS PWSS , SM/13487 | New | Laying of Distribution Pipeline and Land Development work at Kandra PWSS of Bharatpur-II Block, Kandi Sub-Division under Murshidabad Division, P.H.E. Dte. | 889/MURD | 22/04/2025 | 45 | PAL CONSTRUCTION (SUBHAM PAL) | 12.06 | 0 | 0 | 0
1063 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. , SM/14431 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MASHIMPUR Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1591/BD-I | 28/02/2023 | 10 | TECHVISION | 2.6 | 2.6 | 100 | 0
1064 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. , SM/14431 | Augmentation | Proposed balance work for office room at 1st floor over AIRP pump house with staircase at Mashimpur ground water supply scheme under JJM under Berhampore Division-I, P.H.E Dte. | 441/BD-I | 15/03/2024 | 30 | CLASSIC CONSTRUCTION | 2.61 | 0 | 0 | 0
1065 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. , SM/14431 | Augmentation | Material Requisition To Resource Division | 196/BD-I/22 | 09/02/2024 | 0 | Resource Division | 14.87 | 0 | 0 | 0
1066 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. , SM/14431 | Augmentation | Augmentation of Mashimpur Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 81/BD-I | 28/04/2023 | 180 | SUJIT KUMAR SAHA | 241.41 | 73.06 | 30.26 | 40
1067 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. , SM/14431 | Augmentation | Allied works of Laying of distribution pipeline of MASHIMPUR piped water supply scheme under JJM within Beldanga-II Block in the district of Murshidabad under Berhampore Division-I, PHE Dte. | 1478/BD-I | 06/09/2024 | 30 | SANTANU BISWAS | 16.93 | 0 | 0 | 0
1068 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. , SM/14431 | Augmentation | Improvement of Existing AIRP of (Capacity 51 Cum/hr.) with allied works at Mashimpur Water Supply Scheme under Jal Jeevan Mission within Beldanga - II under Berhampore Division-I, P.H.Eengineering Dte. In the district of Murshidabad. | 846/BD-I | 23/06/2025 | 30 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 6.4 | 0 | 0 | 0
1069 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. , SM/14431 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) forMashimpur water supply scheme of Beldanga-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 1015/BD-I | 31/10/2023 | 30 | SOUMEN ADHIKARY | 7.83 | 7.29 | 100 | 100
1070 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. , SM/14431 | Augmentation | MASHIMPUR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 461/BD-I | 15/03/2024 | 300 | JALALUDDIN SHAH | 21.7 | 5.38 | 20.94 | 100
1071 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. , SM/14431 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 51 Cum/hr.) with allied work at Mashimpur Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | 910/BD-I | 07/06/2024 | 120 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 17.45 | 14.85 | 46.5 | 100
1072 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SYPPLY SCHEME FOR KANKURIA JAFRABAD ZONE-II BLOCK SAMSERGANJ DIST - MURSHIDABAD. , SM/13114 | Augmentation | Augmentation Work for Construction of 900 Cum OHR, Laing of Rising Main, Laing Distribution System, Construction of 3 Nos Pump House & Construction of Boundary Wall of Kankuria Jafrabad (Zone-II) PWSS under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | 2697/MURD | 25/08/2023 | 365 | SAMIRAN KUMAR CHAKRABORTY | 446.57 | 0 | 0 | 0
1073 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SYPPLY SCHEME FOR KANKURIA JAFRABAD ZONE-II BLOCK SAMSERGANJ DIST - MURSHIDABAD. , SM/13114 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED PIPED WATER SYPPLY SCHEME FOR KANKURIA JAFRABAD ZONE-II BLOCK SAMSERGANJ DIST - MURSHIDABAD. . under MEDB, PHE Dte. | 344/MEDB | 10/02/2025 | 89 | MONI ELECTRICAL WORKS | 37.01 | 0 | 0 | 0
1074 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13994 | Augmentation | Material Requisition To Resource Division | 1210/MURD/28 | 02/05/2023 | 0 | Resource Division | 1.51 | 0 | 0 | 0
1075 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13994 | Augmentation | Providing FHTC to 1034 no household, Laying Distribution System, Vertical extension of Boundary wall and repairing Pump House and Overhauling of R.C.C. elevated reservoir 350 Cum capacity of staging height 20 mtr. (Shaft wall) for Augmentation work of Prosadpur (Zone-I) PWSS under Murshidabad Division,PHE.Dte. | 905/MURD | 29/03/2023 | 887 | M/S. S.S. ENTERPRISE( PROP: SANDIP SAHA) | 139.2 | 59.16 | 42.5 | 50
1076 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13994 | Augmentation | Laying of Distribution System (Part-A) & FHTC work at Khanpur, Bhairabpur, Khidirpur, Parulia village of PROSADPUR (ZONE-I) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | 18/MURD | 03/01/2024 | 729 | BISWAS ENTERPRISE (PROP. SAMIUL ISLAM)) | 84.13 | 26.59 | 31.61 | 41
1077 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13994 | Augmentation | Allied work for Laying of UPVC pipeline, Construction of Culvert and Approach road for PROSADPUR (ZONE-I) Piped Water Supply Scheme in Suti-II Block of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | 3213/MURD | 09/12/2024 | 30 | M/S. S.S. ENTERPRISE( PROP: SANDIP SAHA) | 36.51 | 0 | 0 | 0
1078 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13994 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for PRASADPUR ZONE-I Ground Based Water Supply Scheme in Suti-II Block under Murshidabad Division, PHE Dte. | 983/MURD | 02/05/2025 | 60 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 19.61 | 0 | 0 | 0
1079 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13994 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 225/3 & 225/4) at Khanpur mouza & Connecting with existing 110 mm dia UPVC distribution main line of Prosadpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | 2482/MURD | 16/08/2021 | 60 | DECON INDIA | 20.38 | 15.68 | 100 | 100
1080 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13994 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.86 | 100 | 100
1081 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/13996 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 7.92 | 100 | 100
1082 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/13996 | Augmentation | Material Requisition To Resource Division | 1278/MURD/19 | 10/05/2023 | 0 | Resource Division | 34.76 | 0 | 0 | 0
1083 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/13996 | Augmentation | Repairing of 550Cum OHR and FHTC for Augmentation of PUTIA (ZONE-I) ground water based piped water supply scheme within Raghunathganj-II Block under Murshidabad Division P.H.E. Dte. | 507/MURD | 22/02/2023 | 60 | CLASSIC CONSTRUCTION (ANJAN CHATTERJEE) | 60.86 | 40.52 | 66.57 | 50
1084 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/13996 | Augmentation | Renovation of Filter media of Existing AIRP (Capacity 135 Cum/hr.) of Putia (Zone-I) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | 1892/MURD | 01/07/2024 | 60 | M/S BAPPA ENTERPRISE | 47.01 | 0 | 0 | 0
1085 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/13996 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PUTIA ZONE - I Water Supply Scheme at Head Work Site, 2nd Site, 3 r d , 4th site at RAGHUNATHGANJ - II Block under Murshidabad Division, P.H. Engineering Dte. | 1759/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 25.42 | 100 | 80
1086 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/13996 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD Dist. - Murshidabad under MEDB, PHE Dte. | 339/MEDB | 10/02/2025 | 323 | M/S S. S. ENTERPRISE (DOMKAL) | 22.79 | 0 | 0 | 60
1087 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/13996 | Augmentation | Construction of approach road from pucca road to Head Work site of Putia Water Supply Scheme of Jangipur Sub-Division under Murshidabad Division P.H.E Dte. | 3375/MURD | 20/12/2022 | 940 | JAMIRUL CONSTRUCTION | 4.62 | 0 | 0 | 50
1088 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF PUTIA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/13996 | Augmentation | Formal work order for the construction of Pump House, Vertical extension of Boundary wall and Pump House repairing , Laying Distribution System, Rising Main Connection for Augmentation of PUTIA ( ZONE-I ) Ground water based Piped water supply scheme Raghunathganj -II Block under Murshidabad Division, P.H.E. Dte. [ (i)Amount for LDS, R.Main : Rs. 1,47,25,982.00 & (ii) Amount for Vertical B.Wall Extention & P.House Repairing : Rs. 13,13,446.00] | 810/MURD | 22/03/2023 | 710 | JAYANTA KUMAR CHANDRA | 160.12 | 87.97 | 54.97 | 50
1089 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . , SM/14049 | Augmentation | Material Requisition To Resource Division | 61/BD-1/8 | 27/04/2023 | 0 | Resource Division | 29.2 | 0 | 0 | 0
1090 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . , SM/14049 | Augmentation | NEW SERVICE CONNECTION AT KOMNAGAR PH 1 ID 304268985 |  | 26/11/2024 | 0 | WBSEDCL | 3.49 | 0 | 0 | 0
1091 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . , SM/14049 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Komnagar ground water supply scheme in Raninagar-II Block Dist_Murshidabad under MEDB PHE Dte. | 1133/MEDB | 13/05/2025 | 92 | M/S K.P. PRAMANIK | 39.98 | 0 | 0 | 0
1092 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . , SM/14049 | Augmentation | Augmentation of Komnagar Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 506/BD-I | 24/07/2023 | 647 | PRATICHI ENTERPRISE | 194.85 | 130.92 | 67.19 | 83
1093 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . , SM/14049 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Komnagar ground water supply scheme in Raninagar-II Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | 56/BD-I | 14/01/2025 | 300 | SUMAN ENTERPRISE AND SUMAN AQUA | 122.79 | 0 | 0 | 0
1094 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . , SM/14049 | Augmentation | Construction of Boundary Wall With Main Entrance gate and barbed wire facing ,Service Road for approach and Pump House at Augmentation of Komnagar PWSS of Raninagar-II Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. (2nd Site)/New OHR Site | 1119/BD-I | 11/07/2024 | 335 | MODERN CONSTRUCTION (DOMKAL) | 25.76 | 0 | 0 | 75
1095 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . , SM/14049 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KOMNAGAR Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1763/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.53 | 2.49 | 100 | 100
1096 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . , SM/14049 | Augmentation | Improvement of OHR (90.8 Cum) of Ground Water Based Supply Scheme for Augmentation of Komnagar of Raninagar-I block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | 1118/BD-I | 11/07/2024 | 180 | M/S S.R.K ENTERPRISE | 6.48 | 4.88 | 100 | 100
1097 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . , SM/14049 | Augmentation | Renovation for Filter media of Existing AIRP of (Capacity 18 Cum/hr.) at Komnagar Water Supply Scheme under Jal Jeevan Mission of Berhampore Division-I, PHEengineering Dte. | 412/BD-I | 13/03/2024 | 30 | SUMAN ENTERPRISE AND SUMAN AQUA | 13.04 | 12.95 | 100 | 100
1098 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . , SM/14049 | Augmentation | KOMNAGAR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1130/BD-I | 11/07/2024 | 243 | TAIMUR SK | 19.33 | 0 | 0 | 100
1099 | MURSHIDABAD | Murshidabad Division | Detailed Project Report for Augmentation of Dhulauri Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/14722 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 6.91 | 100 | 1
1100 | MURSHIDABAD | Murshidabad Division | Detailed Project Report for Augmentation of Dhulauri Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/14722 | Augmentation | Formal work order for the Work of Augmentation of Dhulauri Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 350/MURD | 08/02/2023 | 180 | M/S. S. DAS AND ENTERPRISE | 419.15 | 266.85 | 63.66 | 48
1101 | MURSHIDABAD | Murshidabad Division | Detailed Project Report for Augmentation of Dhulauri Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/14722 | Augmentation | Material Requisition To Resource Division | 1278/MURD/13 | 10/05/2023 | 0 | Resource Division | 34.6 | 0 | 0 | 0
1102 | MURSHIDABAD | Berhampore Mechanical | Detailed Project Report for Augmentation of Dhulauri Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/14722 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under DHULAURI ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | 4295/MEDB | 29/12/2023 | 91 | SUBHRA ENTERPRISE | 22.13 | 0 | 0 | 0
1103 | MURSHIDABAD | Murshidabad Division | Detailed Project Report for Augmentation of Dhulauri Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/14722 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dhulauri Water Supply Scheme and Tejsinghapur Water Supply Schem under Murshidabad Division, P.H. Engineering Dte | 1746/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 23.58 | 0 | 0 | 100
1104 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III , SM/15231 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I and II ,Zone-III under Bansgara ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | 632/MEDB | 02/02/2024 | 90 | M/S K.P. PRAMANIK | 22.17 | 0 | 0 | 0
1105 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III , SM/15231 | Augmentation | Material Requisition To Resource Division | 201/BD-1/23 | 10/02/2024 | 0 | Resource Division | 66.74 | 0 | 0 | 0
1106 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III , SM/15231 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1742/BD-I | 22/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.55 | 0 | 0 | 95
1107 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III , SM/15231 | Augmentation | Formal work order for Augmentation of Bansgara Zone-III Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP), pump house, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | 463/BD-I | 17/07/2023 | 899 | SAMBHUNATH ROY | 291.11 | 0 | 0 | 15
1108 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground water based pipe water supply scheme for Bansgara Zone-III , SM/15231 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bansgara Zone-III Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte ( For 2 nos Tubewell) | 138/BD-I | 12/05/2023 | 631 | HARUN ALL RASHID & BROTHERS | 17.66 | 9.64 | 57.23 | 100
1109 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. , SM/15519 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for ANDULBERIA Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1593/BD-I | 28/02/2023 | 10 | TECHVISION | 3.15 | 2.92 | 92.65 | 0
1110 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. , SM/15519 | Augmentation | Material Requisition To Resource Division | 196/BD-I/24 | 09/02/2024 | 0 | Resource Division | 46.35 | 0 | 0 | 0
1111 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. , SM/15519 | Augmentation | Augmentation of Andulberia Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1821/BD-I | 31/03/2023 | 1007 | KAMIRUL SK AND CO. | 399.58 | 125.59 | 31.43 | 70
1112 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. , SM/15519 | Augmentation | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of ANDULBERIA ZONE-II" ground water supply scheme in BELDANGA-II Block under Berhampore Division-I, P.H.E Dte(Capacity-72.00 Cum/hr.) Type-1: Fully Gravity System with RG Filter | 994/BD-I | 20/06/2024 | 365 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 197.4 | 0 | 0 | 0
1113 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. , SM/15519 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ANDULBERIA ZONE - II Water Supply Scheme(3rd TW Site) within Beldanga - II Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | 103/BD-I | 20/01/2025 | 15 | HARUN ALL RASHID & BROTHERS | 8.95 | 0 | 0 | 0
1114 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. , SM/15519 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of ANDULBERIA ZONE-II PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 724/BD-I | 15/05/2025 | 120 | M/S. MONDAL ENTERPRISE | 19 | 0 | 0 | 100
1115 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-II PIPED WATER SUPPLY SCHEME. , SM/15519 | Augmentation | ANDULBERIA ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1109/BD-I | 10/07/2024 | 180 | SARODA CONSTRUCTION & CO | 22.74 | 5.79 | 20.94 | 100
1116 | MURSHIDABAD | Berhampore Mechanical | BATHUR AND ADJOINING MOUJAS PWSS , SM/15265 | New | Service connection charge for Bathur PH-I, Appl. no.3004523927. ID- 304212545. | 201/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 2.66 | 0 | 0 | 0
1117 | MURSHIDABAD | Berhampore Mechanical | BATHUR AND ADJOINING MOUJAS PWSS , SM/15265 | New | Service connection charge for Bathur PH-II, Appl. no.3004523910. ID- 304212540. | 202/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 3.43 | 0 | 0 | 0
1118 | MURSHIDABAD | Murshidabad Division | BATHUR AND ADJOINING MOUJAS PWSS , SM/15265 | New | Material Requisition To Resource Division | 79 | 09/01/2024 | 0 | Resource Division | 3.37 | 0 | 0 | 0
1119 | MURSHIDABAD | Berhampore Mechanical | BATHUR AND ADJOINING MOUJAS PWSS , SM/15265 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under BATHUR ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | 1923/MEDB | 16/06/2023 | 92 | JOY BISHNU ENGINEERING CO. | 21.42 | 13.32 | 62.19 | 20
1120 | MURSHIDABAD | Murshidabad Division | BATHUR AND ADJOINING MOUJAS PWSS , SM/15265 | New | Allied work for Construction of Pump House at Head Works Site &2nd T.W. Site,FHTC, Boundary Wall,Rising Main Connection, Laying Distribution System for Bathur PWSS in Khargram Block under Murshidabad Division, PHE Dte. | 1929/MURD | 03/07/2024 | 272 | NOVELTY CONSTRUCTION | 43.95 | 17.06 | 38.81 | 10
1121 | MURSHIDABAD | Murshidabad Division | BATHUR AND ADJOINING MOUJAS PWSS , SM/15265 | New | Formal work order for construction of Pump House at Head Work Site & 2nd Tube well site ,FHTC, Boundwary Wall, Rising Main Connection, Laying Distribution System for BATHUR PWSS in Khargram Block under Murshidabad Division ,PHE.Dte [ (i)Amount for LDS , R. Main, FHTC : Rs. 73,83,365.00 &(ii) Amount for Pump House, B.Wall : Rs. 35,86,277.00] | 593/MURD | 01/03/2023 | 615 | NOVELTY CONSTRUCTION | 109.53 | 109.08 | 99.45 | 37
1122 | MURSHIDABAD | Murshidabad Division | BATHUR AND ADJOINING MOUJAS PWSS , SM/15265 | New | Sinking of 02 (Two) Nos of 300 mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bathur & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | 1100/MURD | 24/04/2023 | 30 | NADIA TUBEWELLS | 21.35 | 16.02 | 100 | 100
1123 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. , SM/14734 | Augmentation | Material Requisition To Resource Division | 194/BD-I/7 | 09/02/2024 | 0 | Resource Division | 32.78 | 0 | 0 | 0
1124 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. , SM/14734 | Augmentation | LOAD ENHANCEMENT AT BANSGARA Z2 PH1 ID 312397840 | 481/WBSEDCL-JJM | 21/03/2024 | 0 | WBSEDCL | 1.8 | 0 | 0 | 0
1125 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. , SM/14734 | Augmentation | LOAD ENHANCEMENT BANSGARA AIRP ID 3004571720 | 482/WBSEDCL-JJM | 21/03/2024 | 0 | WBSEDCL | 1.11 | 0 | 0 | 0
1126 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. , SM/14734 | Augmentation | load enhancement bansgara z2 ph 1 |  | 05/03/2024 | 0 | WBSEDCL | 1.8 | 0 | 0 | 0
1127 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. , SM/14734 | Augmentation | Augmentation of Bansgara Zone-II Piped water supply scheme to accommodate construction of Arsenic cum Iron Removal Plant(AIRP), pump house, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | 313/BD-I | 14/06/2023 | 1012 | MODERN CONSTRUCTION | 261.29 | 91.62 | 35.06 | 70
1128 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. , SM/14734 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Raninagar-II under MEDB, PHE Dte. | 324/MEDB | 10/02/2025 | 324 | JOGMAYA ENGINEERING | 24.94 | 0 | 0 | 25
1129 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. , SM/14734 | Augmentation | Construction of Service Road, Improvement of RCC OHR and Pump House of Bansgara Zone-II PWSS under Jal Jeevan Mission within Raninagar-II block under Berhampore Division-I PHE Dte. in the district of Murshidabad. | 1014/BD-I | 06/08/2025 | 45 | GOUTAM MANDAL | 32.21 | 0 | 0 | 0
1130 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. , SM/14734 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA ZONE-II Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1760/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.46 | 2.46 | 100 | 100
1131 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II. , SM/14734 | Augmentation | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bansgara Zone-II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte | 1149/BD-I | 04/12/2023 | 30 | NADIA TUBEWELLS | 11.56 | 10.14 | 100 | 100
1132 | MURSHIDABAD | Murshidabad Division | AMJUA AND ADJOINING MOUJAS PWSS , SM/14495 | New | Material Requisition To Resource Division | 1210/MURD/35 | 02/05/2023 | 0 | Resource Division | 21.05 | 0 | 0 | 0
1133 | MURSHIDABAD | Murshidabad Division | AMJUA AND ADJOINING MOUJAS PWSS , SM/14495 | New | Formal work order for Laying Distribution System (PART-C), FHTC (PART-C), for Uncovered of AMJUA PWSS at AMJUA ( Village Code-315107) , CHURIGRAM ( Village Code-315108) , DURGARAMPUR ( Village Code-315109) in Khargram Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | 339/MURD | 08/02/2023 | 90 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 146.33 | 77.64 | 53.06 | 34
1134 | MURSHIDABAD | Murshidabad Division | AMJUA AND ADJOINING MOUJAS PWSS , SM/14495 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 0 | 80
1135 | MURSHIDABAD | Murshidabad Division | AMJUA AND ADJOINING MOUJAS PWSS , SM/14495 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia Replacement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at AMJUA PWSS at Head Work Site & 2nd Tube Well Site in Khargram Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 380/MURD | 10/02/2023 | 45 | SUJIT KUMAR SAHA | 16.81 | 14.08 | 100 | 100
1136 | MURSHIDABAD | Berhampore Mechanical | AMJUA AND ADJOINING MOUJAS PWSS , SM/14495 | New | NEW SERVICE CONNECTION AT AMJUA PH1 ID 304158525 | 220/WBSEDCL-JJM | 05/01/2024 | 0 | WBSEDCL | 8.29 | 0 | 0 | 0
1137 | MURSHIDABAD | Murshidabad Division | AMJUA AND ADJOINING MOUJAS PWSS , SM/14495 | New | Formal work order for Laying Distribution System (PART-B), FHTC (PART-B), Boundary wall for Uncovered of AMJUA PWSS at UTTAR GANGARAMPUR ( Village Code-315100) , SADAL ( Village Code-315101) , BHAT KANDA ( Village Code-315102) in Khargram Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. [(i)Amount for LDS & FHTC: Rs.2,54,73,199.00 & (ii) Amount for Boundwary Wall: Rs. 31,33,915.00] | 453/MURD | 17/02/2023 | 960 | PRADIP KUMAR DAS | 285.93 | 31.09 | 10.87 | 5
1138 | MURSHIDABAD | Murshidabad Division | AMJUA AND ADJOINING MOUJAS PWSS , SM/14495 | New | Formal work order for Construction of 400 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, FHTC (PART-A), for Uncovered of AMJUA PWSS at RAHIGRAM Village in Khargram Block, Kandi Sub-Division under Murshidabad Division, PHE.Dte. | 414/MURD | 15/02/2023 | 1141 | M/S.TAPAS KUMAR CHAKRABORTY | 306.3 | 68.67 | 22.42 | 10
1139 | MURSHIDABAD | Berhampore Mechanical | AMJUA AND ADJOINING MOUJAS PWSS , SM/14495 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under AMJUA ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | 3787/MEDB | 03/11/2023 | 1686 | KASHINATH PAL & CO. | 24.35 | 0 | 0 | 40
1140 | MURSHIDABAD | Murshidabad Division | SADPUR PIPE WATER SUPPLY SCHEME. , SM/14946 | New | Material Requisition To Resource Division | 1210/MURD/38 | 02/05/2023 | 0 | Resource Division | 29.54 | 0 | 0 | 0
1141 | MURSHIDABAD | Murshidabad Division | SADPUR PIPE WATER SUPPLY SCHEME. , SM/14946 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SADPUR PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 542/MURD | 24/02/2023 | 45 | INDRAJIT MAZUMDAR | 16.8 | 14.61 | 100 | 80
1142 | MURSHIDABAD | Murshidabad Division | SADPUR PIPE WATER SUPPLY SCHEME. , SM/14946 | New | Material Requisition To Resource Division | 112/MURD/02 | 11/01/2024 | 0 | Resource Division | 11.89 | 0 | 0 | 0
1143 | MURSHIDABAD | Murshidabad Division | SADPUR PIPE WATER SUPPLY SCHEME. , SM/14946 | New | Material Requisition To Resource Division | MURD/439/11 | 08/02/2024 | 0 | Resource Division | 5.94 | 0 | 0 | 0
1144 | MURSHIDABAD | Berhampore Mechanical | SADPUR PIPE WATER SUPPLY SCHEME. , SM/14946 | New | NEW SERVICE CONNECTION AT PH 1 SADPUR ID 304252899 | 360/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 3.59 | 0 | 0 | 0
1145 | MURSHIDABAD | Murshidabad Division | SADPUR PIPE WATER SUPPLY SCHEME. , SM/14946 | New | Formal work order for Laying Distribution system (PART-A) at SADPUR PWSS of Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | 382/MURD | 10/02/2023 | 811 | S.K. ENTERPRISE (SANDIP GHOSH) | 136.23 | 115.84 | 85.03 | 85
1146 | MURSHIDABAD | Murshidabad Division | SADPUR PIPE WATER SUPPLY SCHEME. , SM/14946 | New | Formal work order for Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of SADPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362342S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,30,41,399.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,56,32,356.00] | 475/MURD | 20/02/2023 | 771 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 286.71 | 69.44 | 24.22 | 21
1147 | MURSHIDABAD | Berhampore Mechanical | SADPUR PIPE WATER SUPPLY SCHEME. , SM/14946 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of SADPUR ground water based water supply scheme under Block- Kandi Dist. Murshidabad under MEDB, PHE Dte. | 3790/MEDB | 03/11/2023 | 668 | S. P. CONSTRUCTION | 20.89 | 0 | 0 | 40
1148 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14920 | Augmentation | Material Requisition To Resource Division | 61/BD-1/5 | 27/04/2023 | 0 | Resource Division | 49.26 | 0 | 0 | 0
1149 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14920 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , Zone-I under Hurshi ground water based water supply scheme under Block_ Raninagar-I Dist. - Murshidabad under MEDB, PHE Dte. | 4297/MEDB | 29/12/2023 | 91 | SREE RADHA ELECTRICAL | 34.27 | 28.43 | 82.96 | 80
1150 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14920 | Augmentation | Construction of Service Road for approach and Pump House at Augmentation of Hurshi New PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | 1110/BD-I | 10/07/2024 | 60 | PRADIP DAS | 8.04 | 0 | 0 | 0
1151 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14920 | Augmentation | NEW SERVICE CONNECTION AT HURSHI z1 ph2 id 304247241 |  | 26/11/2024 | 0 | WBSEDCL | 9.34 | 0 | 0 | 0
1152 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14920 | Augmentation | NEW CONNECTION HURSHI Z-1 PH-I | 469/WBSEDCL-JJM | 19/03/2024 | 0 | WBSEDCL | 7.8 | 0 | 0 | 0
1153 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14920 | Augmentation | Augmentation of Hurshi Zone-I Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant( AIRP), pump house and boundary wall , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 844/BD-I | 05/09/2023 | 620 | M/S B.M. INDUSTRIES | 423.99 | 190.56 | 44.94 | 70
1154 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14920 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HURSHI ZONE-I Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1691/BD-I | 14/03/2023 | 10 | RADIANT | 2.6 | 2.6 | 100 | 100
1155 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14920 | Augmentation | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Hurshi Zone-I Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte ( For 3 nos Tubewell) | 1147/BD-I | 04/12/2023 | 30 | MAMATA USHA ENTERPRISE | 34.71 | 9.7 | 34.27 | 50
1156 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14920 | Augmentation | Repair And Renovation Works Of OHR (180 Cum) of Ground Water Based Supply Scheme for Hurshi Zone-I of Raninagar-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | 1066/BD-I | 21/11/2023 | 418 | M/S ADHIKARI CONSTRUCTION | 7.79 | 5.62 | 100 | 100
1157 | MURSHIDABAD | Berhampore Mechanical | KUMAR SANDA AND ADJOINING MOUJAS PWSS , SM/14238 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II and III under KUMAR SANDA ground water based water supply scheme under Block_ KANDI Dist. - Murshidabad under MEDB, PHE Dte. | 2082/MEDB | 19/06/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 36.82 | 0 | 0 | 0
1158 | MURSHIDABAD | Murshidabad Division | KUMAR SANDA AND ADJOINING MOUJAS PWSS , SM/14238 | New | Material Requisition To Resource Division | 1043/MURD/9 | 17/04/2023 | 0 | Resource Division | 32.79 | 0 | 0 | 0
1159 | MURSHIDABAD | Murshidabad Division | KUMAR SANDA AND ADJOINING MOUJAS PWSS , SM/14238 | New | Formal work order for the work of KUMAR SANDA & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362351S000) | 92/MURD | 11/01/2023 | 1086 | ACQUA CONSTRACTION CONSORTIAM | 678.7 | 54.74 | 8.07 | 20
1160 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/16244 | Augmentation | Material Requisition To Resource Division | 1180/MURD/18 | 29/04/2023 | 0 | Resource Division | 179.05 | 0 | 0 | 0
1161 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/16244 | Augmentation | New connection charge for Khairamari W/S Scheme (Part-A), P/H No.-II. | 95/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 0.7 | 0 | 0 | 0
1162 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/16244 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,Part-A under Khayramari ground water based water supply scheme under Block_ Jalangi Dist. - Murshidabad under MEDB, PHE Dte. | 3687/MEDB | 03/11/2023 | 92 | SUBHRA ENTERPRISE | 11.18 | 7.16 | 64.06 | 70
1163 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/16244 | Augmentation | Sinking of 01 (One) No of 250mm x 150 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHAYRAMARI Part-A and Salar Zone - IIB Water Supply Scheme as required under Murshidabad Division, P.H. Engineering Dte. | 1744/MURD | 06/07/2023 | 14 | SARKAR WATER SUPPLY AGENCY | 9.22 | 0 | 0 | 100
1164 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/16244 | Augmentation | Material Requisition To Resource Division | MURD/2481/04 | 04/09/2024 | 0 | Resource Division | 5.07 | 0 | 0 | 0
1165 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/16244 | Augmentation | ADDL SERVICE CONNECTION CHARGES KHAIRAMARI PWSS PART A PH 2,ID860281602 | 207/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 3.24 | 0 | 0 | 0
1166 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/16244 | Augmentation | Formal work order for the Work of Augmentation of KHAYRAMARI PART-A Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE. Dte. | 657/MURD | 06/03/2023 | 843 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 466.36 | 285.91 | 61.31 | 95
1167 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/16244 | Augmentation | Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 01.02.2024 to 30.05.2024) | 17/KSD | 16/01/2024 | 120 | SOUMYADIP MISRA | 0.69 | 1.53 | 220.6 | 70
1168 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at SURANGAPUR PWSS (ZONE- I ) Ground water Based PWSS, Block-Nowda , Dist- Murshidabad under MEDB, PHE Dte. , SM/15352 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at SURANGAPUR PWSS (ZONE- I ) Ground water Based PWSS, Block-Nowda , Dist- Murshidabad under MEDB, PHE Dte. | 3748/MEDB | 03/11/2023 | 92 | SARKAR CONSTRUCTION | 6.39 | 0 | 0 | 0
1169 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at KARIMPUR JALANGI Zone-I Ground water Based PWSS, Block-Jalangi , Dist- Murshidabad under MEDB, PHE Dte. , SM/15353 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at KARIMPUR JALANGI Zone-I Ground water Based PWSS, Block-Jalangi , Dist- Murshidabad under MEDB, PHE Dte.¿ | 3745/MEDB | 03/11/2023 | 92 | HARA PROSAD DAS | 6.39 | 0 | 0 | 0
1170 | MURSHIDABAD | Murshidabad Division | PETARI AND ADJOINING MOUJAS PWSS , SM/14237 | New | Material Requisition To Resource Division | 1004/MURD/16 | 17/04/2023 | 0 | Resource Division | 23.72 | 0 | 0 | 0
1171 | MURSHIDABAD | Berhampore Mechanical | PETARI AND ADJOINING MOUJAS PWSS , SM/14237 | New | Electric Service New Connection PETARI PH- 2 PWSS Application NO. 3004404553. ID. 304120628 | 169/WBSEDCL-JJM | 05/12/2023 | 0 | WBSEDCL | 3.13 | 0 | 0 | 0
1172 | MURSHIDABAD | Berhampore Mechanical | PETARI AND ADJOINING MOUJAS PWSS , SM/14237 | New | Electric Service New Connection PETARI PH-1 PWSS Application NO. 3004494692. ID. 304193611 | 170/WBSEDCL-JJM | 05/12/2023 | 0 | WBSEDCL | 6.35 | 0 | 0 | 0
1173 | MURSHIDABAD | Berhampore Mechanical | PETARI AND ADJOINING MOUJAS PWSS , SM/14237 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under PETARI ground water based water supply scheme under Block_ BURWAN, Dist. - Murshidabad under MEDB, PHE Dte. | 2085/MEDB | 19/06/2023 | 926 | JOGMAYA ENGINEERING | 23.47 | 19.34 | 82.39 | 20
1174 | MURSHIDABAD | Murshidabad Division | PETARI AND ADJOINING MOUJAS PWSS , SM/14237 | New | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 4.23 | 100 | 100
1175 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Manigram Ground water Based PWSS, Block-Sagardighi , Dist- Murshidabad under MEDB, PHE Dte. , SM/15345 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Manigram Ground water Based PWSS, Block-Sagardighi , Dist- Murshidabad under MEDB, PHE Dte | 3756/MEDB | 03/11/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.39 | 0 | 0 | 0
1176 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KUSUMGACHI PIPED WATER SUPPLY SCHEME. , SM/16427 | Augmentation | Material Requisition To Resource Division | 1210/MURD/05 | 02/05/2023 | 0 | Resource Division | 50.19 | 0 | 0 | 0
1177 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KUSUMGACHI PIPED WATER SUPPLY SCHEME. , SM/16427 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 0 | 10
1178 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KUSUMGACHI PIPED WATER SUPPLY SCHEME. , SM/16427 | Augmentation | Providing FHTC Connection to 800 nos household, Laying of Rising Main, Laying of Distribution System, Overhauling of RCC 180 Cum OHR, Construction Pump House with sanitary and Water Supply Arrangement (T/W-I), Special repair and renovation of existing 1 (One) Nos Pump House and Alied Works, Construction of Boundary Wall, Repair of Boundary Wall & Construction of RCC approach road for Augmentation of KUSUMGACHI Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. | 904/MURD | 29/03/2023 | 881 | S. ENTERPRISE (PROP: SAIRUL ISLAM) | 174.93 | 35.35 | 20.21 | 50
1179 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KUSUMGACHI PIPED WATER SUPPLY SCHEME. , SM/16427 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for KUSUMGACHI Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division , PHE Dte. | 982/MURD | 02/05/2025 | 60 | M/S SAJAHAN CHOWDHURY | 22.96 | 0 | 0 | 0
1180 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KUSUMGACHI PIPED WATER SUPPLY SCHEME. , SM/16427 | Augmentation | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhasaipaikar Zone- I A & Kusumgachi Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 1772/MURD | 06/07/2023 | 544 | R.K. DRILLING SERVICES | 27.67 | 11.81 | 67.39 | 100
1181 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (maximum 100 households) Village-Char Halalpur Zone-IV, Block-Berhampore, District- Murshidabad. , SM/16433 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Halalpur Zone-IV village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3076/MEDB | 02/08/2023 | 92 | SURAKSHA | 6.3 | 0 | 0 | 0
1182 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (maximum 100 households) Village-Char Halalpur Zone-IV, Block-Berhampore, District- Murshidabad. , SM/16433 | New | Mini Piped Water Supply Scheme for Char Halalpur Zone-IV under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 172/BD-I | 16/05/2023 | 90 | JALALUDDIN SHAH | 22.51 | 0 | 0 | 0
1183 | MURSHIDABAD | Berhampore Mechanical | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE CHAR NARAYANPUR , BLOCK- BERHAMPORE, DISTRICT MURSHIDABAD. , SM/16441 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Narayanpur village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3037/MEDB | 02/08/2023 | 92 | SREE RADHA ELECTRICAL | 6.32 | 0 | 0 | 0
1184 | MURSHIDABAD | Berhampore Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE CHAR NARAYANPUR , BLOCK- BERHAMPORE, DISTRICT MURSHIDABAD. , SM/16441 | New | Mini Piped Water Supply Scheme for Char Narayanpur under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 175/BD-I | 16/05/2023 | 90 | SANTANU BISWAS | 28.53 | 0 | 0 | 0
1185 | MURSHIDABAD | Berhampore Mechanical | SEHALAI PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-I , DISTRICT- MURSHIDABAD. , SM/16443 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Sehalai Part-A village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3070/MEDB | 02/08/2023 | 92 | T. N. BANERJEE | 6.15 | 0 | 0 | 0
1186 | MURSHIDABAD | Berhampore Mechanical | SEHALAI PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-I , DISTRICT- MURSHIDABAD. , SM/16443 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Sehalai Part-B village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3071/MEDB | 02/08/2023 | 92 | GANGULI ELECTRICAL CO. | 6.3 | 0 | 0 | 0
1187 | MURSHIDABAD | Murshidabad Division | SEHALAI PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-I , DISTRICT- MURSHIDABAD. , SM/16443 | New | Ground Water based piped water supply scheme for Sehalai Part- A village, Block:- Bharatpur- I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2418/MURD | 08/08/2023 | 744 | M/S RELIABLE | 30.55 | 0 | 0 | 64
1188 | MURSHIDABAD | Murshidabad Division | SEHALAI PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-I , DISTRICT- MURSHIDABAD. , SM/16443 | New | Ground Water based piped water supply scheme for Sehalai Part- B village, Block:- Bharatpur- I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2491/MURD | 11/08/2023 | 60 | M/S. GHOSH ENTERPRISE RAJ GHOSH | 30.54 | 0 | 0 | 0
1189 | MURSHIDABAD | Murshidabad Division | SERPUR (CT) PIPE WATER SUPPLY SCHEME. , SM/16481 | New | Material Requisition To Resource Division | 1230/MURD/21 | 04/05/2023 | 0 | Resource Division | 25.58 | 0 | 0 | 0
1190 | MURSHIDABAD | Murshidabad Division | SERPUR (CT) PIPE WATER SUPPLY SCHEME. , SM/16481 | New | Formal work order for SERPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission, Block- SAMSERGANJ of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | 594/MURD | 01/03/2023 | 1036 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 446.76 | 88.09 | 19.72 | 15
1191 | MURSHIDABAD | Berhampore Mechanical | SERPUR (CT) PIPE WATER SUPPLY SCHEME. , SM/16481 | New | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I II & III under SERPUR(CT) ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | 759/MEDB | 20/02/2024 | 90 | M/S SAJAHAN CHOWDHURY | 32.53 | 0 | 0 | 0
1192 | MURSHIDABAD | Murshidabad Division | SERPUR (CT) PIPE WATER SUPPLY SCHEME. , SM/16481 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SERPUR (CT) Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | 3386/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 16.97 | 100 | 45
1193 | MURSHIDABAD | Murshidabad Division | SERPUR (CT) PIPE WATER SUPPLY SCHEME. , SM/16481 | New | Material Requisition To Resource Division | 495/MURD/12 | 15/02/2024 | 0 | Resource Division | 13.47 | 0 | 0 | 0
1194 | MURSHIDABAD | Berhampore Mechanical | SERPUR (CT) PIPE WATER SUPPLY SCHEME. , SM/16481 | New | NEW CONNECTION AT SERPUR PH-I | 139/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 3.44 | 0 | 0 | 0
1195 | MURSHIDABAD | Murshidabad Division | SERPUR (CT) PIPE WATER SUPPLY SCHEME. , SM/16481 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.87 | 100 | 100
1196 | MURSHIDABAD | Murshidabad Division | SERPUR (CT) PIPE WATER SUPPLY SCHEME. , SM/16481 | New | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at TEGHARI ZONE - I, MAHESAIL ZONE-III & SERPUR (CT) Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 2407/MURD | 07/08/2023 | 552 | NADIA TUBEWELLS | 35.34 | 5.08 | 39.48 | 100
1197 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. , SM/16176 | Augmentation | Material Requisition To Resource Division | 1210/MURD/08 | 02/05/2023 | 0 | Resource Division | 9.5 | 0 | 0 | 0
1198 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. , SM/16176 | Augmentation | Providing FHTC Connection to 268 nos household, Laying of Rising Main, Laying of Distribution System, overhauling of RCC 45 Cum OHR, Construction of Boundary Wall (For T/W-I) =100mtr, Special repair and renovation of existing 1 (One) Nos Pump House and Allied Works and Construction of RCC approach road =140 mtr for Augmentation of Jadabpur Nimtala Piped Water Supply Scheme in Farakka Block under Murshidabad Division, PHE.Dte. | 740/MURD | 12/03/2024 | 60 | PAL CONSTRUCTION | 57.61 | 26.63 | 46.23 | 50
1199 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. , SM/16176 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 0 | 10
1200 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. , SM/16176 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JADABPUR NIMTALA and KANKURIA JAFRABAD ZONE- I Water Supply Scheme as required at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | 3813/MURD | 12/12/2023 | 21 | HARUN ALL RASHID & BROTHERS | 11.77 | 0 | 0 | 100
1201 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. , SM/16176 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME District - Murshidabad. under MEDB, PHE Dte. | 335/MEDB | 10/02/2025 | 89 | QUAZI NOZRUL ISLAM (PARTNERSHIP) | 21.52 | 0 | 0 | 0
1202 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADABPUR NIMTALA PIPED WATER SUPPLY SCHEME. , SM/16176 | Augmentation | Sinking of 04 (Four) Nos 200 mm dia tube well by DTH method using UPVC Pipe at Adwaita Nagar CT T.W-I,II & Jadabpur Nimtala T.W-I,II Water Supply Scheme of Samserganj , Farakka under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 665/MURD | 19/03/2025 | 160 | KHOKAN BISWAS | 24.89 | 0 | 0 | 100
1203 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for CHANDKATI Block - Nawda District - Murshidabad. , SM/15638 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-III & IV under CHANDKATI ground water based water supply scheme under Block_ NAWDA Dist. - Murshidabad under MEDB, PHE Dte. | 1894/MEDB | 16/06/2023 | 92 | S. G. TECHNICAL SERTIVCE | 22.25 | 0 | 0 | 0
1204 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for CHANDKATI Block - Nawda District - Murshidabad. , SM/15638 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0 | 0
1205 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for CHANDKATI Block - Nawda District - Murshidabad. , SM/15638 | Augmentation | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandkati (Village code 315533) under Chandkati Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723218 in the District of Murshidabad. | 79/MURD | 08/01/2021 | 60 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 12.25 | 7.97 | 100 | 90
1206 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for CHANDKATI Block - Nawda District - Murshidabad. , SM/15638 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 4.99 | 100 | 1
1207 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for CHANDKATI Block - Nawda District - Murshidabad. , SM/15638 | Augmentation | Repair and renovation work of Boundary wall and allied work at Head Work site of Chandkathi Water Supply Scheme under Berhampore Sub Division, P.H.E.Dte. in the District of Murshidabad. | 201/BSD | 28/04/2022 | 30 | LATIFUDDIN | 4.78 | 4.16 | 100 | 1
1208 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for CHANDKATI Block - Nawda District - Murshidabad. , SM/15638 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under CHANDKATI ground water based water supply scheme under Block_ NAWDA Dist. - Murshidabad under MEDB, PHE Dte. | 4293/MEDB | 29/12/2023 | 91 | DAS ENTERPRISE ( MANGO LANE) | 22.21 | 0 | 0 | 0
1209 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for CHANDKATI Block - Nawda District - Murshidabad. , SM/15638 | Augmentation | Providing FHTC Connection to 986 nos household , Laying of Distribution System (Part_B) NODE 198 TO NODE 385, Repairing & Vertical Extention of Boundary Wall, Special repair and renovation of existing 1 (One) Nos Pump House and Alied Works for for Augmentation work of CHANDKATI PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. (part_B) | 907/MURD | 29/03/2023 | 180 | DAS TRADING CO. | 136.61 | 127.44 | 100 | 90
1210 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for CHANDKATI Block - Nawda District - Murshidabad. , SM/15638 | Augmentation | Construction 2 (Two ) Nos Pump House with clorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement and 210 mtr Boundary wall at Head Work site and 55Mtr at 2nd site of Sarbangapur Zone -IB , Bara Satui & Chandkati Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | 1930/MURD | 03/07/2024 | 537 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 52.14 | 0 | 0 | 75
1211 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for CHANDKATI Block - Nawda District - Murshidabad. , SM/15638 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for CHANDKATHI Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | 1189/MURD | 23/05/2025 | 60 | PRADIP KUMAR DAS | 23.01 | 0 | 0 | 0
1212 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for CHANDKATI Block - Nawda District - Murshidabad. , SM/15638 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAGAR PARA PART-B Water Supply Scheme and Chandkati Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 3907/MURD | 20/12/2023 | 392 | NADIA TUBEWELLS | 18.43 | 0 | 0 | 100
1213 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (maximum 100 households) Village-Sonadiar Zone-I, Block-Berhampore, District- Murshidabad. , SM/16500 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Sonadiar Zone-I village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3048/MEDB | 02/08/2023 | 92 | HARA PROSAD DAS | 6.27 | 0 | 0 | 0
1214 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- I C Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16173 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 6.62 | 200 | 1
1215 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Mahadebnagar Zone- I C Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16173 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IC under Mahadebnagar ground water based water supply scheme under Block_ Farakka Dist. - Murshidabad under MEDB, PHE Dte. | 3671/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 22.92 | 4.18 | 18.24 | 50
1216 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- I C Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16173 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
1217 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- I C Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16173 | Augmentation | Renovation of Modified Sujapur Sadhipur Model of AIRP (Capacity 123 Cum/hr.) at Mahadebnagar Zone I Water Supply Scheme of Farakka Block Jangipur Sub-Division under Murshidabad Division, PHE Dte. | 226/MURD | 27/01/2025 | 45 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 77.24 | 0 | 0 | 0
1218 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- I C Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16173 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tubewell i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I C, Anup Nagar (CT) & Chachanda Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 1771/MURD | 06/07/2023 | 684 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 0 | 40
1219 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. , SM/16175 | Augmentation | Material Requisition To Resource Division | 1167/MURD/38 | 28/04/2023 | 0 | Resource Division | 5.48 | 0 | 0 | 0
1220 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. , SM/16175 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | 1925/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 9.6 | 2.79 | 50 | 100
1221 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. , SM/16175 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tubewell i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at P.T RASULPUR (PART - A), Kupila and Baniakhali Water Supply Scheme at DOMKAL Block under Murshidabad Division,P.H. Engineering Dte | 1749/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 10.27 | 100 | 40
1222 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. , SM/16175 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KUPILA Water Supply Scheme and Herampur Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 3768/MURD | 08/12/2023 | 21 | MAMATA USHA ENTERPRISE | 11.79 | 0 | 0 | 100
1223 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. , SM/16175 | Augmentation | Material Requisition To Resource Division | 526/MURD/08 | 19/02/2024 | 0 | Resource Division | 2.46 | 0 | 0 | 0
1224 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. , SM/16175 | Augmentation | NEW CONNECTION KUPILA PH-1 | 438/WBSEDCL-JJM | 13/03/2024 | 0 | WBSEDCL | 6 | 0 | 0 | 0
1225 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. , SM/16175 | Augmentation | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Juginda, Kupila and Narsinghpur Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | 1193/MURD | 10/05/2022 | 1360 | MAMATA USHA ENTERPRISE | 32.62 | 0 | 0 | 20
1226 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. , SM/16175 | Augmentation | Augmentation of KUPILA PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. | 1380/MURD | 22/05/2023 | 1044 | S.S. ENTERPRISE | 413.75 | 238.83 | 57.72 | 30
1227 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. , SM/16175 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under Kupila ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | 3689/MEDB | 03/11/2023 | 1246 | EASTERN INDIA SALES & SERVICE | 22.33 | 15.74 | 70.5 | 10
1228 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KUPILA PIPED WATER SUPPLY SCHEME. , SM/16175 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Islampur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | 2637/MURD | 23/09/2024 | 150 | INDRAJIT DUBEY | 8.72 | 0 | 0 | 100
1229 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone-I Block- Lalgola, District- Murshidabad. , SM/16210 | New | Mini Piped Water Supply Scheme for Durgapur zone-I under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 148/BD-I | 15/05/2023 | 90 | KAUSHIK MAJUMDAR | 30.23 | 0 | 0 | 0
1230 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone-I Block- Lalgola, District- Murshidabad. , SM/16210 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Durgapur Zone-I village, Block:- Lalgola under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3791/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0 | 0
1231 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. , SM/16380 | Augmentation | Material Requisition To Resource Division | 201/BD-1/19 | 10/02/2024 | 0 | Resource Division | 23.75 | 0 | 0 | 0
1232 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. , SM/16380 | Augmentation | Material Requisition To Resource Division | 1510/BD-I/13 | 12/09/2024 | 0 | Resource Division | 7.2 | 0 | 0 | 0
1233 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. , SM/16380 | Augmentation | NEW CONNECTION MAIYA PH-1 | 396/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 9.31 | 0 | 0 | 0
1234 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. , SM/16380 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of Maia Zone - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 599/BD-I | 22/04/2025 | 60 | SUJAUDDIN SHAIKH | 18.99 | 0 | 0 | 0
1235 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. , SM/16380 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of Maia Zone-II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 441/BD-I | 20/03/2025 | 60 | SHIBAM ENTERPRISE | 19 | 0 | 0 | 0
1236 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. , SM/16380 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MAIA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 47/BD-I | 25/04/2023 | 10 | ENVIROTECH SOLUTIONS | 2.49 | 2.49 | 100 | 100
1237 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. , SM/16380 | Augmentation | MAYA ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 456/BD-I | 15/03/2024 | 420 | DHRITIPALI | 21.91 | 0 | 0 | 100
1238 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Maia Zone- II Block - Lalgola, Dist- Murshidabad. , SM/16380 | Augmentation | Construction Pump House Cum Chlorine Room at Head Work site of Maia Zone -II Water Supply Scheme , under Jal Jevan Mission of Lalgola Block of Murshidabad District under Berhampore Division -I, PHE.Dte. | 07/BD-I | 06/01/2025 | 45 | BARUN DUTTA | 8.11 | 0 | 0 | 90
1239 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16419 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-II under Rejinagar ground water based water supply scheme under Block_ Beldanga_II Dist. - Murshidabad under MEDB, PHE Dte. | 3673/MEDB | 03/11/2023 | 92 | MASSK ENGINEERING WORKS | 22.62 | 0 | 0 | 0
1240 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16419 | Augmentation | Material Requisition To Resource Division | 1167/MURD/42 | 28/04/2023 | 0 | Resource Division | 34.04 | 0 | 0 | 0
1241 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16419 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 2.58 | 100 | 100
1242 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16419 | Augmentation | Material Requisition To Resource Division | 1811/MURD/20 | 20/06/2024 | 0 | Resource Division | 5.36 | 0 | 0 | 0
1243 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16419 | Augmentation | Augmentation of Ground Water Based Rejinagar Zone II PWSS of accommodate with Switch Room, Boundary Wall, 300 CUM OHR in Beldanga II Block within Murshidabad District under Murshidabad Division, PHE Dte. [ Part B ] | 3318/MURD | 22/10/2023 | 544 | MODERN CONSTRUCTION | 163.25 | 0 | 0 | 0
1244 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-II piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16419 | Augmentation | Providing FHTC Connection to 870 nos household , Laying of Distribution System, Rising Main for Augmentation work of Rejinagar Zone-II PWSS within Beldanga-II Block under Murshidabad Division , PHE.Dte. ( PART - A) | 3317/MURD | 22/10/2023 | 708 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 195.25 | 59.36 | 30.4 | 85
1245 | MURSHIDABAD | Berhampore Mechanical | DHANDANGA AMD IT'S ADJOINING MOUJAS , SM/16392 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Dhandanga ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | 3705/MEDB | 03/11/2023 | 92 | QUAZI NOZRUL ISLAM | 22.44 | 0 | 0 | 0
1246 | MURSHIDABAD | Murshidabad Division | DHANDANGA AMD IT'S ADJOINING MOUJAS , SM/16392 | New | Material Requisition To Resource Division | 1075/MURD/15 | 19/04/2023 | 0 | Resource Division | 14.18 | 0 | 0 | 0
1247 | MURSHIDABAD | Murshidabad Division | DHANDANGA AMD IT'S ADJOINING MOUJAS , SM/16392 | New | Formal Work Order for Laying Distribution System of DHANDANGA PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Murshidabad Circle ,PHE.Dte. | 741/MURD | 16/03/2023 | 747 | APORUPA CONSTRUCTION | 180.78 | 16.43 | 9.09 | 10
1248 | MURSHIDABAD | Berhampore Mechanical | DHANDANGA AMD IT'S ADJOINING MOUJAS , SM/16392 | New | NEW CONNECTION AT DHANDANGA PH-I | 65/WBSEDCL-JJM | 09/05/2024 | 0 | WBSEDCL | 4.09 | 0 | 0 | 0
1249 | MURSHIDABAD | Murshidabad Division | DHANDANGA AMD IT'S ADJOINING MOUJAS , SM/16392 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAIDYNATHPUR , DHANDANGA & SANTOSHPUR Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 2806/MURD | 05/09/2023 | 589 | INDRAJIT MAZUMDAR | 27.64 | 0 | 0 | 100
1250 | MURSHIDABAD | Murshidabad Division | UJUNIA SISUA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16394 | New | Material Requisition To Resource Division | 1230/MURD/15 | 04/05/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
1251 | MURSHIDABAD | Murshidabad Division | UJUNIA SISUA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16394 | New | BERBARI & UJUNIA adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block-BHARATPUR-I & II of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE Dte. | 882/MURD | 28/03/2023 | 280 | BANAMALI ENTERPRISES | 224.42 | 0 | 0 | 35
1252 | MURSHIDABAD | Berhampore Mechanical | UJUNIA SISUA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16394 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Ujunia Sisua ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | 3717/MEDB | 03/11/2023 | 92 | SUNIL RABIDAS | 22.54 | 13.98 | 62 | 10
1253 | MURSHIDABAD | Murshidabad Division | UJUNIA SISUA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16394 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UJUNIA SISUA AND GUNDIRIA Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur I & II Block under Murshidabad Division, P.H. Engineering Dte | 3409/MURD | 02/11/2023 | 472 | GENUINE | 18.43 | 0 | 0 | 100
1254 | MURSHIDABAD | Murshidabad Division | Augmentation of Bharatpur Zone -IIB Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. , SM/15728 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 0 | 75
1255 | MURSHIDABAD | Murshidabad Division | Augmentation of Bharatpur Zone -IIB Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. , SM/15728 | Augmentation | Augmentation of BHARATPUR (ZONE - II B) PWSS under Jal Jeevan Mission of Bharatpur-I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | 184/MURD | 18/01/2024 | 1014 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 415.23 | 0 | 0 | 43
1256 | MURSHIDABAD | Murshidabad Division | Augmentation of Bharatpur Zone -IIB Water Supply Scheme Block - Bharatpur -I, Dist- Murshidabad. , SM/15728 | Augmentation | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage VI on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Murshidabad RWS Sub Division, PHE Dte. [ Period for 181 Days] w.e.f 02/04/2025 to 30/09/2025. Vehicle No [WB58CA/1034] | 607/MSD | 28/03/2025 | 181 | SUMAN ENTERPRISE AND SUMAN AQUA | 0.89 | 1.2 | 135.2 | 0
1257 | MURSHIDABAD | Murshidabad Division | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16113 | New | Repair and renovation work of Switch room and Boundary wall at Head Work and 2nd TW site of Fatepur Water Supply Scheme under Berhampore Sub Division, P.H.E.Dte. in the District of Murshidabad. | 17/BSD | 10/01/2022 | 30 | MADAN MOHAN SASMAL | 4.85 | 4.41 | 100 | 100
1258 | MURSHIDABAD | Murshidabad Division | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16113 | New | Material Requisition To Resource Division | 1936/MURD/6 | 19/07/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
1259 | MURSHIDABAD | Central Drilling | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16113 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 2203/CDD | 01/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 8.13 | 73.18 | 10
1260 | MURSHIDABAD | Murshidabad Division | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16113 | New | Laying and distribution of UPVC pipeline for Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of FATEPUR ( Village Code _315310) under Fatepur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 192/BSD | 28/04/2022 | 30 | SURAJIT MONDAL | 4.77 | 4.65 | 100 | 100
1261 | MURSHIDABAD | Berhampore Mechanical | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16113 | New | POWER CONNECTION AT PWSS FATEPUR PH 1 ID 304248214 | 43/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 4.71 | 0 | 0 | 0
1262 | MURSHIDABAD | Murshidabad Division | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16113 | New | FATEPUR PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | 1867/MURD | 14/07/2023 | 968 | ABIDA CONSTRUCTION | 124.31 | 50.47 | 40.6 | 65
1263 | MURSHIDABAD | Murshidabad Division | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16113 | New | Allied works for laying pipeline and construction of approach road for Fatepur Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | 1978/MURD | 08/07/2024 | 542 | ABIDA CONSTRUCTION | 19.77 | 0 | 0 | 70
1264 | MURSHIDABAD | Murshidabad Division | FATEPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16113 | New | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Satitara T.W- IV,V,VI, Fatepur T.W.-II, Kapasdanga T.W-II Water Supply Scheme of Burwan Block under Kandi Sub- Division, Murshidabad Division, P.H.Engineering Dte. | 664/MURD | 19/03/2025 | 65 | NADIA TUBEWELLS | 70.43 | 0 | 0 | 0
1265 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16624 | Augmentation | Material Requisition To Resource Division | 1210/MURD/17 | 02/05/2023 | 0 | Resource Division | 34.57 | 0 | 0 | 0
1266 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16624 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under GHORA PAKHIA GANGIN ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | 4342/MEDB | 29/12/2023 | 91 | SREE RADHA ELECTRICAL | 21.44 | 0 | 0 | 0
1267 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16624 | Augmentation | Continuation work order for Hiring of maxi cab (Non Air conditioned ,Bharat stage III) on or after 31.10.2023 with diesel/LPG/CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Assistant Engineer (HQ), Murshidabad Division, P.H.E. Dte. For 06(Six) Months (on and from 01/05/2025 to 31/10/2025) having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the Date of 1st Registration on monthly Hire rate basis ( The cost inclusive of all charges due to the wages of Driver, Taxes , Insurance , Fees etc. as applicable Excluding fuel, lubricant etc. as per order) Vehicle No.WB-58BV-8767 | 946/MURD | 29/04/2025 | 183 | M/S JOY MA BANAMALI | 0.9 | 0 | 0 | 20
1268 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16624 | Augmentation | Continuation work order for Hiring of maxi cab (Non Air conditioned ,Bharat stage III) on or after 31.10.2023 with diesel/LPG/CNG Engine) in perfect good condition of performing very long journey and should cover anywhere with in any trouble on daily wage basis for official used under the control of the Assistant Engineer (HQ), Murshidabad Division, P.H.E. Dte. For 06(Six) Months (on and from 01/11/2025 to 30/04/2026) having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the Date of 1st Registration on monthly Hire rate basis ( The cost inclusive of all charges due to the wages of Driver, Taxes ,Insurance , Fees etc. as applicable Excluding fuel, lubricant etc. as per order) Vehicle No.WB-58BV-8767 | 2239/MURD | 31/10/2025 | 181 | M/S JOY MA BANAMALI | 0.89 | 0 | 0 | 0
1269 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16624 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.08 | 100 | 100
1270 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED GHORA PAKHIA GANGIN ZONE-I PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16624 | Augmentation | Laying M.S pipe for interconnection Between A.I.R.P & O.H.R and Clearing chokage of Rising main at GHORAPAKIAGANGING Zone-I Water Supply Scheme under Jangipur Sub-Division under Murshidabad Division, PHE Dte. | 652/MURD | 06/03/2023 | 30 | LAXMI CONSTRUCTION | 1.86 | 1.84 | 100 | 100
1271 | MURSHIDABAD | Berhampore Division I | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/16783 | New | Material Requisition To Resource Division | 61/BD-1/33 | 27/04/2023 | 0 | Resource Division | 13.12 | 0 | 0 | 0
1272 | MURSHIDABAD | Berhampore Division I | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/16783 | New | PURBA GOBINDAPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 200 cum) under Jal Jivan Mission of BHAGWANGOLA -II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 967/BD-I | 17/10/2023 | 840 | SAMBHUNATH ROY | 298.57 | 96.39 | 32.28 | 35
1273 | MURSHIDABAD | Berhampore Mechanical | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/16783 | New | NEW CONNECTION AT PURBA GOBINDAPUR PH-1 | 102/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 6.06 | 0 | 0 | 0
1274 | MURSHIDABAD | Berhampore Division I | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/16783 | New | PURBA GOBINDAPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 217/BD-I | 17/05/2023 | 90 | SUPTI ENTERPRISE | 40.92 | 22.25 | 54.36 | 50
1275 | MURSHIDABAD | Berhampore Division I | PURBA GOBINDAPUR AND ADJOINING MOUJAS PWSS , SM/16783 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PURBA GOBINDAPUR and Adjoining Mouzas PWSS (TW-II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division-I, P.H.Engineering Dte. (01 Nos TW) | 770/BD-I | 22/05/2025 | 15 | M/S UNIVERSAL TRADING | 9.01 | 0 | 0 | 0
1276 | MURSHIDABAD | Murshidabad Division | KIRTTIPUR AND ADJOINING MOUJAS PWSS , SM/15691 | New | Material Requisition To Resource Division | 1129/MURD/6 | 25/04/2023 | 0 | Resource Division | 10.76 | 0 | 0 | 0
1277 | MURSHIDABAD | Berhampore Mechanical | KIRTTIPUR AND ADJOINING MOUJAS PWSS , SM/15691 | New | Electric Service Connection at KRITTIPUR PWSS PH I, Application NO.3004450962, ID 304158425 | 189/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 4.87 | 0 | 0 | 0
1278 | MURSHIDABAD | Murshidabad Division | KIRTTIPUR AND ADJOINING MOUJAS PWSS , SM/15691 | New | Material Requisition To Resource Division | 79/MURD/08 | 09/01/2024 | 0 | Resource Division | 9.85 | 0 | 0 | 0
1279 | MURSHIDABAD | Berhampore Mechanical | KIRTTIPUR AND ADJOINING MOUJAS PWSS , SM/15691 | New | NEW SERVICE CONNECTION AT PWSS PH2 KIRTIPUR ID304239452 | 304/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 3.41 | 0 | 0 | 0
1280 | MURSHIDABAD | Murshidabad Division | KIRTTIPUR AND ADJOINING MOUJAS PWSS , SM/15691 | New | Formal work order for KIRTTIPUR & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- KHARGRAM of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | 781/MURD | 20/03/2023 | 1144 | ARIZ ENTERPRISE | 343.69 | 182.35 | 53.05 | 11
1281 | MURSHIDABAD | Berhampore Mechanical | KIRTTIPUR AND ADJOINING MOUJAS PWSS , SM/15691 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Kirttipur ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | 3709/MEDB | 03/11/2023 | 790 | WEST BENGAL ENGINEERING CO. | 22.18 | 0 | 0 | 50
1282 | MURSHIDABAD | Murshidabad Division | KIRTTIPUR AND ADJOINING MOUJAS PWSS , SM/15691 | New | Allied work for Construction of Boundary wall, Road repair & 1 no. Box Culvert at Kirtipur PWSS at Khargram Block under Kandi Sub-Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 1990/MURD | 08/07/2024 | 597 | ARIZ ENTERPRISE | 36.54 | 0 | 0 | 10
1283 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone- III & Zone- XI) to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte. , SM/16673 | Retrofitting | Last mile connectivity and providing 6309 nos Functional House Hold Connection from Zone- XI of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. | 3076/MURD | 26/11/2024 | 90 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 265.37 | 0 | 0 | 0
1284 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone- III & Zone- XI) to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte. , SM/16673 | Retrofitting | Last mile connectivity and providing 6292 nos Funcational House Hold Connection from Zone- III of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . | 2687/MURD | 25/08/2023 | 120 | J.S. CONSTRUCTION | 348.56 | 0 | 0 | 0
1285 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone- III & Zone- XI) to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte. , SM/16673 | Retrofitting | Allied work for Construction of Annular Combined Pile Raft Foundation for R.C.C Elevated Reservoir of Capacity 1000 Cu.M of staging height 20 Meter at Head Work site within BUZRAK FATEPUR (Zone XI) W/S Scheme, Block-Saghardighi, District-Murshidabad Under Murshidabad Division P.H.E Dte. | 2023/MURD | 11/07/2024 | 90 | BIJAY CHOWDHURY | 85.49 | 20.99 | 24.55 | 85
1286 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone- I & Zone- V) to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte. , SM/16674 | Retrofitting | Last mile connectivity and providing 5090 nos Functional House Hold Connection from Zone- V of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. | 2688/MURD | 25/08/2023 | 120 | SARAJIT KUMAR MAJUMDER | 270.74 | 0 | 0 | 0
1287 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone- I & Zone- V) to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte. , SM/16674 | Retrofitting | Last mile connectivity and providing 7512 nos Funcational House Hold Connection from Zone- I of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte | 2685/MURD | 25/08/2023 | 120 | MANASH GHOSH | 376.07 | 0 | 0 | 0
1288 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16769 | Augmentation | Material Requisition To Resource Division | 1219/MURD/19 | 03/05/2023 | 0 | Resource Division | 15.13 | 0 | 0 | 0
1289 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16769 | Augmentation | Augmentation Work of Raturi Zone II Piped Water Supply Scheme to accommodate with FHTC (297 Nos), Laying of Rising Main , Laying of Distribution System , construction of 100 CUM OHR, Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE.Dte | 2699/MURD | 25/08/2023 | 560 | SAMBHU NATH ROY | 161.08 | 11.14 | 6.92 | 30
1290 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16769 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 2.76 | 100 | 100
1291 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16769 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II, Zone-II under RATURI ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | 1919/MEDB | 16/06/2023 | 869 | SARKAR CONSTRUCTION | 21.42 | 4.6 | 18.46 | 10
1292 | MURSHIDABAD | Murshidabad Division | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. , SM/16899 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 4.69 | 100 | 76
1293 | MURSHIDABAD | Murshidabad Division | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. , SM/16899 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 1.67 | 100 | 80
1294 | MURSHIDABAD | Murshidabad Division | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. , SM/16899 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone- I A Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Bharatpur -II Block under Murshidabad Division, P.H. Engineering Dte | 3835/MURD | 14/12/2023 | 21 | MAMATA USHA ENTERPRISE | 23.58 | 20.59 | 100 | 100
1295 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. , SM/16899 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of SALAR ZONE 1 A Piped Water Supply Scheme Block BHARATPUR-II District - Murshidabad. under MEDB, PHE Dte. | 1161/MEDB | 15/05/2025 | 92 | JOY BISHNU ENGINEERING CO. | 21.35 | 0 | 0 | 0
1296 | MURSHIDABAD | Murshidabad Division | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. , SM/16899 | Augmentation | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kagram & Salar Zone - IA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 1102/MURD | 24/04/2023 | 20 | INDRAJIT MAZUMDAR | 10.68 | 0 | 0 | 0
1297 | MURSHIDABAD | Murshidabad Division | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. , SM/16899 | Augmentation | Continuation Work Order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage ¿ III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months.(Period From 31.05.2024 to 27.09.2024) | 92/KSD | 27/05/2024 | 120 | SOUMYADIP MISRA | 0.69 | 1.52 | 218.89 | 0
1298 | MURSHIDABAD | Murshidabad Division | Augmentation of Salar Zone- I A Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. , SM/16899 | Augmentation | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 0 | 20
1299 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. , SM/16765 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 3.5 | 100 | 76
1300 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. , SM/16765 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , Zone-II under TENYA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | 1901/MEDB | 16/06/2023 | 92 | S. G. ENTERPRISE | 33.51 | 0 | 0 | 0
1301 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. , SM/16765 | Augmentation | Material Requisition To Resource Division | 969 | 06/04/2023 | 0 | Resource Division | 28.48 | 0 | 0 | 0
1302 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. , SM/16765 | Augmentation | Material Requisition To Resource Division | 1004/MURD | 11/04/2023 | 0 | Resource Division | 28.48 | 0 | 0 | 0
1303 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. , SM/16765 | Augmentation | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Tenya Zone - II Water Supply Scheme and Kurulia Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte | 1751/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 27.64 | 0 | 0 | 50
1304 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. , SM/16765 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 6.57 | 100 | 80
1305 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. , SM/16765 | Augmentation | Laying Distribution System and FHTC at Bara Biadyapur Village (Village Code-315733), Tenya Village (Village-315737), Ghoshpara Village ( Village Code- 315735), Kechunia Village (Village Code-315722), Korgram Village (Village Code- 315736) & Nowapara Village (Village Code-315734) & Repairing of Over Head Reservoir (350 Cum), Pump House & Boundary wall for Augmentation of TENYA Zone-II PWSS in BHARATPUR-II Block , under Murshidabad Division,PHE.Dte | 1139/MURD | 26/04/2023 | 1122 | TANUSHREE ENTERPRISE | 172.7 | 3.31 | 1.92 | 20
1306 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. , SM/16765 | Augmentation | Augmentation of MURADPUR JALANGI ZONE-III /Tenya Zone-II & Zone-III PWSS Laying Distribution System, of JALANGI /Bharatpur-II Block , under Murshidabad Division PHE. Dte. | 2755/MURD | 01/09/2023 | 720 | ULTRA CONSTRUCTION. | 100.45 | 0 | 0 | 95
1307 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. , SM/16765 | Augmentation | Continuation for work order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 01.02.2025 to 31.05.2025) VEHICLE NO - WB 57E 5422 | 25/KSD | 24/01/2025 | 120 | SOUMYADIP MISRA | 0.69 | 0 | 0 | 0
1308 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- II Piped Water Supply Scheme Block - Bharatpur -II , Dist- Murshidabad. , SM/16765 | Augmentation | Continuation for work order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 04 (Four) months. (Period from 28.09.2024 to 31.01.2025) VEHICLE NO - WB 57E 5422 | 141/KSD | 26/09/2024 | 120 | SOUMYADIP MISRA | 0.69 | 0 | 0 | 0
1309 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. , SM/16870 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III ,Zone-III under Bhasaipaikar ground water based water supply scheme under Block_ Samserganj ,Dist. - Murshidabad under MEDB, PHE Dte. | 3660/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 34.39 | 0 | 0 | 0
1310 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. , SM/16870 | Augmentation | Material Requisition To Resource Division | 1167/MURD/30 | 28/04/2023 | 0 | Resource Division | 33.07 | 0 | 0 | 0
1311 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. , SM/16870 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
1312 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. , SM/16870 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0 | 0
1313 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. , SM/16870 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Basudevpur halt Station (TP NO 240/8 & 240/9) at Ratanpur mouza & Connecting with existing 110 mm dia uPVC distribution main line of Bhasipaikar Zone - III ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | 2479/MURD | 16/08/2021 | 60 | ACQUA CONSTRACTION CONSORTIAM | 22.97 | 22.31 | 100 | 90
1314 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone-III Water Supply Scheme Block - Samserganj , Dist- Murshidabad. , SM/16870 | Augmentation | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhasaipaikar Zone-III Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | 3767/MURD | 08/12/2023 | 480 | MAMATA USHA ENTERPRISE | 27.67 | 0 | 0 | 50
1315 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15752 | Augmentation | Material Requisition To Resource Division | 1219/MURD/22 | 03/05/2023 | 0 | Resource Division | 20.71 | 0 | 0 | 0
1316 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15752 | Augmentation | Harua PH-3 Application No- 3004555905 | 275/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 8.65 | 0 | 0 | 0
1317 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15752 | Augmentation | Harua PH-1 Application No- 3004555901 | 276/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 2.16 | 0 | 0 | 0
1318 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15752 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. . under MEDB, PHE Dte. | 332/MEDB | 10/02/2025 | 89 | QUAZI NOZRUL ISLAM (PARTNERSHIP) | 12.71 | 0 | 0 | 0
1319 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15752 | Augmentation | Augmentation Work of Harua Part A Piped Water Supply Scheme to accommodate with Laying of Rising Main , Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE.Dte. | 1868/MURD | 14/07/2023 | 902 | PAL CONSTRUCTION | 31 | 24 | 77.41 | 28
1320 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15752 | Augmentation | Refilling of sand layers, Activated Alumina & existing gravel for Modified Sujapur Sadipur Model after washing of AIRP allied (Capacity 72.00Cum/hr.) at Harua Water Supply Scheme under Jal Jivan Mission of Suti-I Block under Jangipur Sub-Division under Murshidabad Division, PHE Dte. | 743/MURD | 12/03/2024 | 535 | SUMAN ENTERPRISE AND SUMAN AQUA | 63.59 | 0 | 0 | 50
1321 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15752 | Augmentation | Balance work for Repair & Renovation of Existing AIRP (Modified Sujapur Sadhipur Model) of (Capacity 72 Cu.M/hr) at Harua Water Supply Scheme at Suti-I Block, of Jangipur Sub-Division under Murshidabad Division P.H.Engineering Dte. | 1243/MURD | 29/05/2025 | 60 | SUMAN ENTERPRISE AND SUMAN AQUA | 27.06 | 0 | 0 | 0
1322 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15752 | Augmentation | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Anup Nagar CT T.W-I, , Bhabki T.W-I,II, Harua T.W-I,II,III Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 761/MURD | 02/04/2025 | 80 | TITUMIR INTERNATIONAL | 70.61 | 0 | 0 | 0
1323 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HARUA PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15752 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 2.73 | 100 | 100
1324 | MURSHIDABAD | Berhampore Division I | NAMOORAHAR AND ADJOINING MOUJAS PWSS , SM/18186 | New | Material Requisition To Resource Division | 61/BD-1/28 | 27/04/2023 | 0 | Resource Division | 16.52 | 0 | 0 | 0
1325 | MURSHIDABAD | Berhampore Division I | NAMOORAHAR AND ADJOINING MOUJAS PWSS , SM/18186 | New | Material Requisition To Resource Division | 304/BD-1/11 | 22/02/2024 | 0 | Resource Division | 6.42 | 0 | 0 | 0
1326 | MURSHIDABAD | Berhampore Mechanical | NAMOORAHAR AND ADJOINING MOUJAS PWSS , SM/18186 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-III under NAMOORAHAR ground water based water supply scheme under Block_ LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | 1159/MEDB | 15/05/2025 | 92 | MASSK ENGINEERING WORKS | 10.65 | 0 | 0 | 0
1327 | MURSHIDABAD | Berhampore Division I | NAMOORAHAR AND ADJOINING MOUJAS PWSS , SM/18186 | New | NAMOORAHAR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 732/BD-I | 16/08/2023 | 90 | MASOOM TRADERS | 34.64 | 0 | 0 | 25
1328 | MURSHIDABAD | Berhampore Division I | NAMOORAHAR AND ADJOINING MOUJAS PWSS , SM/18186 | New | NAMOORAHAR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 150 cum) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte | 746/BD-I | 17/08/2023 | 868 | M/S. UNIQUE BUILDERS | 244.5 | 103.36 | 42.27 | 10
1329 | MURSHIDABAD | Berhampore Division I | NAMOORAHAR AND ADJOINING MOUJAS PWSS , SM/18186 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NAMOORAHAR PWSS (2nd TW Site) under Jal Jeevan Mission in Lalgola Block under Berhampore Division-I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | 547/BD-I | 09/04/2025 | 15 | BHOWMIK CONSTRUCTION | 8.99 | 0 | 0 | 0
1330 | MURSHIDABAD | Berhampore Division I | NAMOORAHAR AND ADJOINING MOUJAS PWSS , SM/18186 | New | Bored Cast-in-situ_ M30 _ grade 600 mm dia 22.00 m (shaft Length) R.C.C. pile for Construction of OHR at Head Work site of NAMOORAHAR Ground Piped Water Supply Scheme under Jal ivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 270/BD-I | 11/02/2025 | 140 | M/S. UNIQUE BUILDERS | 19.08 | 0 | 0 | 100
1331 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. , SM/18542 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-II under Bhandara ground water based water supply scheme under Block_Bhagwangola - I Dist. - Murshidabad under MEDB, PHE Dte. | 3663/MEDB | 03/11/2023 | 92 | TARUN KUMAR BHATTACHARYA | 35.9 | 0 | 0 | 0
1332 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. , SM/18542 | Augmentation | Continuation Order Hiring of Diesel driven Bolero/Equivalent four wheeler car for the official use of the Executive Engineer under Office of the Executive Engineer, Mechanical/Electrical Division, PHE Dte. in the district of Murshidabad. | 3364/AE/MEDB | 27/09/2023 | 182 | M/S SAJAHAN CHOWDHURY | 0.9 | 2.23 | 248.95 | 0
1333 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. , SM/18542 | Augmentation | Augmentation of BHANDARA (ZONE - II A) & Augmentation of BHAGIRATHPUR PWSS under Jal Jeevan Mission of Bhagawangola-I & Domkal Block, Murshidabad District under Murshidabad Division, PHE. Dte. | 3372/MURD | 31/10/2023 | 270 | MAMATA USHA ENTERPRISE | 902.27 | 0 | 0 | 0
1334 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. , SM/18542 | Augmentation | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Nabagram of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Amarkundu Water Supply Scheme, Nabagram Zone-I & II Water Supply Scheme, Panchgram Water Supply Scheme. (Annexure-II) | 1929/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 7.92 | 2.67 | 83.64 | 100
1335 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. , SM/18542 | Augmentation | Augmentation of BHANDARA (ZONE - II B) PWSS under Jal Jeevan Mission of Bhagawangola-I Block, Lalbagh Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | 829/MURD | 15/03/2024 | 300 | CHAKRABORTY CONSTRUCTION | 407.22 | 0 | 0 | 0
1336 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. , SM/18542 | Augmentation | Laying of distribution system for the left out portion of Bhandara Mouza Rising Main with DI pipe and interconnection with DI pipe at Head Work Site of Bhandara Zone - I & II Water Supply Scheme and Ancillary works in Lalbagh Sub Divisional Office under Lalbagh Sub Division, Murshidabad Division ,PHE Dte. | 1829/MURD | 18/08/2025 | 60 | MARUTI CONSTRUCTION AND CO. | 47.57 | 0 | 0 | 0
1337 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. , SM/18542 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 0.61 | 19.53 | 100
1338 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-II. , SM/18542 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Lalbagh Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | 2638/MURD | 23/09/2024 | 251 | ARJU CONSTRUCTION | 6.14 | 0 | 0 | 40
1339 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Rejuvenation of Arjunpur (Zone-I ) PWSS. , SM/18774 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-I under ARJUNPUR ground water based water supply scheme under Block_ FARAKKA Dist. - Murshidabad under MEDB, PHE Dte. | 3720/MEDB | 03/11/2023 | 92 | AVINABA ENGINEERING CONCERN | 31.54 | 0 | 0 | 0
1340 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-I ) PWSS. , SM/18774 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 4.85 | 100 | 100
1341 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-I ) PWSS. , SM/18774 | Augmentation | Material Requisition To Resource Division | 1167/MURD/41 | 28/04/2023 | 0 | Resource Division | 25.97 | 0 | 0 | 0
1342 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-I ) PWSS. , SM/18774 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 8.36 | 100 | 80
1343 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-I ) PWSS. , SM/18774 | Augmentation | Allied works for Laying of U.P.V.C Pipeline of 160 mm,125 mm & 90 mm dia at Head work site of Arjunpur Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | 50/MURD | 05/01/2024 | 30 | SK CONSTRUCTION (NAJIR SK.) | 5.71 | 5.7 | 100 | 100
1344 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-I ) PWSS. , SM/18774 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 300 & 900 cum), Sinking of Tube Well and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Arjunpur Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | 3177/MURD | 11/10/2023 | 730 | M/S. CHAKRABORTY & COMPANY | 2041.06 | 107.56 | 12.44 | 35
1345 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-I ) PWSS. , SM/18774 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 4.4 | 100 | 100
1346 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-IA PIPED WATER SUPPLY SCHEME BLOCK -NAWDA , DISTRICT - MURSHIDABAD . , SM/19123 | Augmentation | Material Requisition To Resource Division | 1180/MURD/27 | 29/04/2023 | 0 | Resource Division | 97.75 | 0 | 0 | 0
1347 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-IA PIPED WATER SUPPLY SCHEME BLOCK -NAWDA , DISTRICT - MURSHIDABAD . , SM/19123 | Augmentation | Construction of Boundary wall at Sarbangapur Zone-I, P.H-2 under Sarbangapur Zone-I Water Supply Scheme under Berhampore Sub-Division , P.H.E. Dte. in the District Murshidabad. ( 55.0MTR.)_PART-A | 131/MURD | 15/01/2024 | 30 | PAL CONSTRUCTION | 4.44 | 4.42 | 100 | 100
1348 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-IA PIPED WATER SUPPLY SCHEME BLOCK -NAWDA , DISTRICT - MURSHIDABAD . , SM/19123 | Augmentation | Augmentation of Ground Water Based Sarbangapur Zone-IA PWSS of accommodate FHTC, Laying Distribution System, Laying Rising Main, Repairing of Switch Room, Repairing of Boundary Wall, Repairing of 450 CUM OHR in Nawda Block within Murshidabad District under Murshidabad Division, PHE Dte. | 130/MURD | 15/01/2024 | 411 | NILKAMAL BASAK | 323.16 | 47.84 | 14.8 | 70
1349 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-II , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18384 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-II Water Supply Scheme at Head Work Site, 2nd Site site 3RD Site at LALGOLA Block under Murshidabad Division, P.H. Engineering Dte. | 3784/MURD | 11/12/2023 | 21 | GENUINE | 35.34 | 0 | 0 | 0
1350 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-II , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18384 | Augmentation | Material Requisition To Resource Division | 1167/MURD/17 | 28/04/2023 | 0 | Resource Division | 30.59 | 0 | 0 | 0
1351 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-II , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18384 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-II under Lalgola ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | 3667/MEDB | 03/11/2023 | 92 | M/S K.P. PRAMANIK | 36.25 | 30.42 | 83.9 | 10
1352 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-II , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18384 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 200 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone- II PWSS in Lalgola Block & Mirzapur (Except Gankar Mouza) PWSS Raghunathganj-I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 3377/MURD | 31/10/2023 | 1095 | M/S GHOSH & CO. | 1181.6 | 0 | 0 | 20
1353 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-II , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18384 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 2.99 | 66.24 | 100
1354 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF PURUSOTTAMPUR PIPED WATER SUPPLY SCHEME. , SM/18590 | Augmentation | Construction of 250 Cum OHR, Pump House, Boundary wall & Repairing of Pump House, B.W, Rising Main Connection & FHTC for Augmentation of PURUSOTTAMPUR PWSS in Raninagar-I Block , Islampur Sub-Division under Murshidabad Division ,PHE. Dte.PART_A | 2674/MURD | 24/08/2023 | 365 | M/S BIKASH ENTERPRISE | 342.01 | 0 | 0 | 0
1355 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF PURUSOTTAMPUR PIPED WATER SUPPLY SCHEME. , SM/18590 | Augmentation | Material Requisition To Resource Division | 1219/MURD/18 | 03/05/2023 | 0 | Resource Division | 198.03 | 0 | 0 | 0
1356 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF PURUSOTTAMPUR PIPED WATER SUPPLY SCHEME. , SM/18590 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 2.86 | 99.9 | 100
1357 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF PURUSOTTAMPUR PIPED WATER SUPPLY SCHEME. , SM/18590 | Augmentation | Augmentation of Ground Water Based Purushottampur PWSS of accommodate Laying Distribution System, in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte.PART_B | 2667/MURD | 24/08/2023 | 180 | J.S. CONSTRUCTION | 346.34 | 0 | 0 | 0
1358 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF PURUSOTTAMPUR PIPED WATER SUPPLY SCHEME. , SM/18590 | Augmentation | Supply of different types C.I Specials at Islampur Sub-Divisional Store for different water supply schemes under Islampur sub-Division, under Murshidabad Division, P.H.E. Dte in the District of Murshidabad. | 2674/MURD | 25/09/2024 | 242 | MAKALI ENGINEERING CORPORATION | 32.46 | 7.66 | 50 | 100
1359 | MURSHIDABAD | Berhampore Division I | KHAMARDIAR AND ADJOINING MOUJAS PWSS , SM/18690 | New | Material Requisition To Resource Division | 201/BD-1/4 | 10/02/2024 | 0 | Resource Division | 12.11 | 0 | 0 | 0
1360 | MURSHIDABAD | Berhampore Mechanical | KHAMARDIAR AND ADJOINING MOUJAS PWSS , SM/18690 | New | NEW CONNECTION AT KHAMARDIAR PH-I | 100/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 3.37 | 0 | 0 | 0
1361 | MURSHIDABAD | Berhampore Division I | KHAMARDIAR AND ADJOINING MOUJAS PWSS , SM/18690 | New | KHAMARDIAR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | 690/BD-I | 10/08/2023 | 180 | SARAJIT KUMAR MAJUMDAR | 289.91 | 209.31 | 72.2 | 60
1362 | MURSHIDABAD | Berhampore Division I | KHAMARDIAR AND ADJOINING MOUJAS PWSS , SM/18690 | New | KHAMARDIAR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART - A) | 689/BD-I | 10/08/2023 | 980 | MD MAIDUL ISLAM | 330.82 | 112.73 | 34.08 | 65
1363 | MURSHIDABAD | Berhampore Division I | KHAMARDIAR AND ADJOINING MOUJAS PWSS , SM/18690 | New | KHAMARDIAR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART -C) | 691/BD-I | 10/08/2023 | 900 | M/S BIMALENDU BOSE | 214.12 | 185.32 | 86.55 | 90
1364 | MURSHIDABAD | Berhampore Division I | KHAMARDIAR AND ADJOINING MOUJAS PWSS , SM/18690 | New | KHAMARDIAR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 734/BD-I | 16/08/2023 | 90 | NATIONAL CONSTRUCTION | 50.37 | 11.84 | 23.5 | 25
1365 | MURSHIDABAD | Berhampore Division I | KHAMARDIAR AND ADJOINING MOUJAS PWSS , SM/18690 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Khamardiar Water Supply Scheme under JJM under Berhampore Division - I, P.H.Engineering Dte. | 2331/BD-I | 30/12/2024 | 30 | KAMIRUL SK AND CO. | 18.01 | 0 | 0 | 0
1366 | MURSHIDABAD | Murshidabad Division | GAYSABAD AND ADJOINING MOUJAS PWSS , SM/18453 | New | Material Requisition To Resource Division | 1067/MURD/11 | 18/04/2023 | 0 | Resource Division | 77.6 | 0 | 0 | 0
1367 | MURSHIDABAD | Berhampore Mechanical | GAYSABAD AND ADJOINING MOUJAS PWSS , SM/18453 | New | Electric Service Connection at GYASABAD PWSS PH I, Application NO.3004407323, ID 304123114 | 186/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 6.81 | 0 | 0 | 0
1368 | MURSHIDABAD | Berhampore Mechanical | GAYSABAD AND ADJOINING MOUJAS PWSS , SM/18453 | New | NEW CONNECTION AT GAYSABAD PH-II | 163/WBSEDCL-JJM | 29/07/2024 | 0 | WBSEDCL | 4.14 | 0 | 0 | 0
1369 | MURSHIDABAD | Berhampore Mechanical | GAYSABAD AND ADJOINING MOUJAS PWSS , SM/18453 | New | NEW CONNECTION AT GAYSABAD PH-II |  | 08/07/2024 | 0 | WBSEDCL | 4.14 | 0 | 0 | 0
1370 | MURSHIDABAD | Murshidabad Division | GAYSABAD AND ADJOINING MOUJAS PWSS , SM/18453 | New | GAYSABAD (Part-A) & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Rising Main, FHTC work, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | 2059/MURD | 27/07/2023 | 644 | DHIRENDRANATH MONDAL | 438.55 | 66.69 | 15.21 | 5
1371 | MURSHIDABAD | Berhampore Mechanical | GAYSABAD AND ADJOINING MOUJAS PWSS , SM/18453 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I , II & III under GAYSABAD ground water based water supply scheme under Block_ Bharatpur-I, Dist. - Murshidabad under MEDB, PHE Dte. | 4065/MEDB | 04/12/2023 | 91 | M/S SAJAHAN CHOWDHURY | 36.54 | 23.13 | 63.32 | 5
1372 | MURSHIDABAD | Murshidabad Division | GAYSABAD AND ADJOINING MOUJAS PWSS , SM/18453 | New | Balance work for laying of CI/DI pipe line including supporting structure at Gaysabad PWSS at Bharatpur - I Block under Kandi Sub-Division, Murshidabad Division, PHE Dte in the District of Murshidabad. | 888/MURD | 22/04/2025 | 344 | M/S BHUBAN DAS | 122.18 | 0 | 0 | 0
1373 | MURSHIDABAD | Murshidabad Division | GAYSABAD AND ADJOINING MOUJAS PWSS , SM/18453 | New | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 4.23 | 100 | 100
1374 | MURSHIDABAD | Murshidabad Division | GAYSABAD AND ADJOINING MOUJAS PWSS , SM/18453 | New | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gaysabad, Kagram, Ranagram, Augmentation of Islampur & Augmentation of Shibnagar Laskarpur Zone - II Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | 661/MURD | 19/03/2025 | 170 | M/S GUHA AND ROY | 35.27 | 0 | 0 | 100
1375 | MURSHIDABAD | Murshidabad Division | KUNDAL AND ADJOINING MOUJAS PWSS , SM/18454 | New | Material Requisition To Resource Division | 1210/MURD/39 | 02/05/2023 | 0 | Resource Division | 39.23 | 0 | 0 | 0
1376 | MURSHIDABAD | Murshidabad Division | KUNDAL AND ADJOINING MOUJAS PWSS , SM/18454 | New | Laying Distribution System (PART-B), FHTC (PART-A) , Boundary wall for Uncovered of KUNDAL PWSS at JHIKARHATI (PART) (Village Code- 315835) , KUNDAL (Village Code- 315846), PADMALABHBATI (Village Code315845) and JHIKARHATI (PART)in Burwan Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | 2023/MURD | 25/07/2023 | 120 | DIPAYAN DEY | 182.24 | 14.65 | 8.04 | 50
1377 | MURSHIDABAD | Murshidabad Division | KUNDAL AND ADJOINING MOUJAS PWSS , SM/18454 | New | Laying Distribution System (PART-C) and FHTC for KUNDAL PWSS in Burwan Block under Murshidabad Division ,PHE. Dte. | 1997/MURD | 21/07/2023 | 120 | KISMAT ARA BEGAM | 214.39 | 63.55 | 29.64 | 60
1378 | MURSHIDABAD | Berhampore Mechanical | KUNDAL AND ADJOINING MOUJAS PWSS , SM/18454 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under KUNDAL ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | 2770/MEDB | 25/07/2023 | 92 | JAL PRAVAHIKA PVT LTD | 35.06 | 0 | 0 | 0
1379 | MURSHIDABAD | Murshidabad Division | KUNDAL AND ADJOINING MOUJAS PWSS , SM/18454 | New | Construction of 450 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, for Uncovered of KUNDAL PWSS at KUNDAL (Village Code- 315846), PADMALABHBATI (Village Code- 315845) in Burwan Block , Kandi Sub-Division under Murshidabad Division , PHE. Dte. | 1993/MURD | 21/07/2023 | 773 | M/S UNIVERSAL TRADING | 361.74 | 128.44 | 35.51 | 60
1380 | MURSHIDABAD | Murshidabad Division | KUNDAL AND ADJOINING MOUJAS PWSS , SM/18454 | New | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kundal & adjoining mouzas Water Supply Scheme at Head Work Site, 2nd Site & 3 rd site at Burwan Block under Murshidabad Division, P.H. Engineering Dte. | 2071/MURD | 28/07/2023 | 585 | NADIA TUBEWELLS | 32.03 | 8.5 | 26.55 | 60
1381 | MURSHIDABAD | Murshidabad Division | Augmentation of Juginda Piped Water Supply Scheme Zone-I Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/18773 | Augmentation | Augmentation of JUGINDA (Zone - I) Piped Water Supply Scheme under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE. Dte. | 2772/MURD | 01/09/2023 | 180 | PRADIP KUMAR DAS (PROPRIETORSHIP) | 600.58 | 0 | 0 | 0
1382 | MURSHIDABAD | Murshidabad Division | Augmentation of Juginda Piped Water Supply Scheme Zone-I Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/18773 | Augmentation | Material Requisition To Resource Division | 1210/MURD/22 | 02/05/2023 | 0 | Resource Division | 133.91 | 0 | 0 | 0
1383 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Juginda Piped Water Supply Scheme Zone-I Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/18773 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under JUGINDA ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | 4311/MEDB | 29/12/2023 | 91 | M/S DILIP MITRA | 23.67 | 0 | 0 | 0
1384 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Juginda Piped Water Supply Scheme Zone-I Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/18773 | Augmentation | JUGINDA PH-IV | 408/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 4.24 | 0 | 0 | 0
1385 | MURSHIDABAD | Murshidabad Division | Augmentation of Juginda Piped Water Supply Scheme Zone-I Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/18773 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 4.12 | 100 | 100
1386 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-IV, BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18662 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-IV under Lalgola ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | 3712/MEDB | 03/11/2023 | 92 | ORIENTAL ENGINEERING CO. | 35.18 | 0 | 0 | 0
1387 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-IV, BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18662 | Augmentation | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 600 cum) and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone- IV PWSS in Lalgola Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | 3466/MURD | 06/11/2023 | 365 | M/S. SINHA & SONS | 796.64 | 0 | 0 | 0
1388 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-IV, BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18662 | Augmentation | Material Requisition To Resource Division | 1180/MURD/19 | 29/04/2023 | 0 | Resource Division | 27.58 | 0 | 0 | 0
1389 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-IV, BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18662 | Augmentation | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Nabagram of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Amarkundu Water Supply Scheme, Nabagram Zone-I & II Water Supply Scheme, Panchgram Water Supply Scheme. (Annexure-II) | 1929/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 7.92 | 2.11 | 79.2 | 100
1390 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-IV, BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18662 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 3.09 | 76.73 | 100
1391 | MURSHIDABAD | Murshidabad Division | Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/18694 | Augmentation | Augmentation of Teghari zone II PWSS Construction of 500 Cum OHR with subsoil investigation, Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) (1no)& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) (3 no) & construction of boundary wall of 250 mtr of Raghunathganj - II Block, under Murshidabad Division, PHE.Dte. | 3315/MURD | 22/10/2023 | 250 | VISION ENTERPRISE | 235.76 | 0 | 0 | 0
1392 | MURSHIDABAD | Murshidabad Division | Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/18694 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.96 | 100 | 100
1393 | MURSHIDABAD | Murshidabad Division | Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/18694 | Augmentation | Material Requisition To Resource Division | 1167/MURD/11 | 28/04/2023 | 0 | Resource Division | 77.93 | 0 | 0 | 0
1394 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/18694 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad under MEDB, PHE Dte. | 322/MEDB | 10/02/2025 | 89 | SARKAR CONSTRUCTION | 22.73 | 0 | 0 | 0
1395 | MURSHIDABAD | Murshidabad Division | Augmentation of Teghari Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/18694 | Augmentation | Laying Distribution System, Rising Main Connection, FHTC connections, for Augmentation of Teghari Zone-II PWSS of Raghunathganj-II Block within Murshidabad District under Murshidabad Division, PHE Dte. | 2127/MURD | 23/09/2025 | 90 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 279.55 | 0 | 0 | 0
1396 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18756 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 2.84 | 100 | 100
1397 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18756 | Augmentation | Material Requisition To Resource Division | 1219/MURD/13 | 03/05/2023 | 0 | Resource Division | 13.89 | 0 | 0 | 0
1398 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18756 | Augmentation | : NEW CONNECTION HERAMPUR PWSS Z2 PH1 ID 304495838 |  | 25/11/2024 | 0 | WBSEDCL | 4.34 | 0 | 0 | 0
1399 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18756 | Augmentation | Construction of 250 Cum OHR, Pump House, Boundary wall & Repairing of Pump House for Augmentation of Herampur Zone-I PWSS in Raninagar-I Block , Islampur Sub-Division under Murshidabad Division ,PHE.Dte. | 2672/MURD | 24/08/2023 | 769 | M/S. UNI TRADERS | 143.17 | 26.43 | 18.46 | 30
1400 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18756 | Augmentation | Augmentation of Ground Water Based Herampur Zone-II PWSS in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte.PART_A | 2671/MURD | 24/08/2023 | 586 | CAPITAL CONSTRUCTION | 279.7 | 137.63 | 49.21 | 30
1401 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18756 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. under MEDB, PHE Dte. | 347/MEDB | 10/02/2025 | 89 | SUNIL RABIDAS | 21.38 | 0 | 0 | 0
1402 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . , SM/18529 | Augmentation | Repair And Renovation Works Of OHR (350 Cum) of Ground Water Based Supply Scheme for Bishnupur Zone-I of Raninagar-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | 1034/BD-I | 01/11/2023 | 30 | ARJU CONSTRUCTION | 8.5 | 6.71 | 100 | 100
1403 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . , SM/18529 | Augmentation | Material Requisition To Resource Division | 194/BD-I/5 | 09/02/2024 | 0 | Resource Division | 56.41 | 0 | 0 | 0
1404 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . , SM/18529 | Augmentation | NEW CONNECTION AT BISHNUPUR PRATAPUR Z-I PH-I | 468/WBSEDCL-JJM | 19/03/2024 | 0 | WBSEDCL | 6.75 | 0 | 0 | 0
1405 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . , SM/18529 | Augmentation | NEW CONNECTION BISHNUPUR PRATAPUR Z-I PH-II | 467/WBSEDCL-JJM | 19/03/2024 | 0 | WBSEDCL | 1.74 | 0 | 0 | 0
1406 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . , SM/18529 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Bishnupur Zone-I ground water supply scheme in Raninagar-I Block Dist_Murshidabad under MEDB PHE Dte. | 1130/MEDB | 13/05/2025 | 92 | SREE RADHA ELECTRICAL | 39.95 | 0 | 0 | 0
1407 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . , SM/18529 | Augmentation | Augmentation of Bishnupur Zone-I Piped water supply scheme to accommodate construction of OHR, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | 627/BD-I | 04/08/2023 | 1123 | NATIONAL CONSTRUCTION | 452.24 | 347.4 | 76.82 | 25
1408 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . , SM/18529 | Augmentation | BISHNUPUR ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1265/BD-I | 01/08/2024 | 300 | SHIBAM ENTERPRISE | 21.91 | 0 | 0 | 80
1409 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . , SM/18529 | Augmentation | Construction of Service Road for approach and Pump House at Augmentation of Bishnupur Zone-I PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | 1304/BD-I | 07/08/2024 | 60 | M/S BHAGIRATHI ENTERPRISE | 7.65 | 0 | 0 | 0
1410 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . , SM/18529 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 80 Cum/hr.) with allied work at Bishnupur Zone-I Water Supply Scheme under Jal Jeevan Mission of Raninagar-I under Berhampore Division-I, PHEengineering Dte. | 903/BD-I | 06/06/2024 | 209 | SUMAN ENTERPRISE AND SUMAN AQUA | 40.09 | 25.37 | 63.29 | 85
1411 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . , SM/18529 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Bishnupur Zone-I ground water supply scheme in Raninagar-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | 506/BD-I | 03/04/2025 | 300 | NATIONAL CONSTRUCTION | 122.54 | 0 | 0 | 90
1412 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- I . , SM/18529 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BISHNUPUR ZONE-I Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 605/BD-I | 02/08/2023 | 10 | M/S SOBHA & CO | 2.74 | 2.74 | 100 | 100
1413 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagdanga ( 314725 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-IV , SM/07916 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bagdanga (Village code 314725) under Shibnagar Laskarpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723328 in the District of Murshidabad. | 84/MURD | 08/01/2021 | 60 | DOBAY CONSTRUCTION | 41.95 | 41.33 | 98.53 | 0
1414 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric , SM/07917 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village DAKSHIN NAGAR (Village Code: 314728) under JUGINDA Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 003 of 20-21 by EE / MSD | 17-MSD / 21-22 | 13/08/2021 | 0 | SUJIT KUMAR SAHA | 36.26 | 0 | 0 | 0
1415 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric , SM/07917 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Jal Swapna (JJM) of village JHAUBARIA (Village Code: 314729) under JUGINDA Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL, Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID : 0001723344) Tender no- 825 of 20-21 by EE / MURD | 15-MSD / 21-22 | 10/08/2021 | 0 | DAS ENTERPRISE (SUBRATA DAS) | 14.24 | 0 | 0 | 0
1416 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric , SM/07917 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jhaubaria ( Village Code -314729) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344). | 584/MURD | 09/02/2021 | 60 | DAS ENTERPRISE (SUBRATA DAS) | 21.07 | 4.78 | 100 | 1
1417 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric , SM/07917 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dakshin Nagar ( Village Code -314728) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001723344). | 594 / MURD | 09/02/2021 | 60 | SUJIT KUMAR SAHA | 46.24 | 0 | 0 | 1
1418 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric , SM/07917 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Dakshin Nagar ( Village Code -314728) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001723344). | 594/MURD | 09/02/2021 | 60 | SUJIT KUMAR SAHA | 46.24 | 8.62 | 100 | 1
1419 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Nagar (314728) & Jhaubaria (314729) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Distric , SM/07917 | Retrofitting | Relaying of different dia UPVC pipeline for Balance Providing Functional Household Tap connection (FHTC) of 94 nos in connection with Jal Swapna (Jal Jeevan Mission) and under command areas of village of Jhaubaria (Village Code-314729) under Juginda Ground water based water suply scheme for Arsenic affected areas of DomkalBlock, under Murshidabad Division, P.H.E. Dte. (scheme ID- 0001723344) | 767/MURD | 22/03/2022 | 20 | MONDAL ENTERPRISE | 6.65 | 5.74 | 100 | 1
1420 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mridadpur (314570) of Brindabanpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART-II , SM/07920 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Mridadpur ( Village Code -314570) under Brindabanpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0005019111). | 597/MURD | 09/02/2021 | 60 | SANJAY BISWAS | 67.55 | 68.85 | 101.93 | 0
1421 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mridadpur (314570) of Brindabanpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART-II , SM/07920 | Retrofitting | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 493 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Mridadpur (Village code 314570) under Brindabanpur Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005019111) | 855/MURD | 31/03/2022 | 20 | SUBHENDRA MOHAN SARKAR | 12.24 | 0 | 0 | 100
1422 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Sahebnagar (VillageCode-314609) under command area of Kazipara ground water supply scheme (Part-A) , SM/07222 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahebnagar (village code 314609) under KAZIPARA (Part-A) Ground water based Water Supply Scheme for Jalangi Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2207/BD-I | 10/12/2021 | 90 | SRIJON ENTERPRISE | 61.97 | 0 | 0 | 0
1423 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagharpur Ramna ( 314665 ) of Bagharpur Ramna under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART- , SM/07923 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagharpur Ramna ( 314665 ) of Bagharpur Ramna under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) | 07/MSD/21-22 | 16/07/2021 | 0 | M/S NIRAPADA BHATTACHARJEE | 38.35 | 0 | 0 | 0
1424 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagharpur Ramna ( 314665 ) of Bagharpur Ramna under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART- , SM/07923 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bagharpur Ramna (Village code 314665) under Domkal Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. (Sl No-12) | 3117 / MURD | 09/12/2020 | 180 | M/S NIRAPADA BHATTACHARJEE | 95.68 | 0 | 0 | 0
1425 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagharpur Ramna ( 314665 ) of Bagharpur Ramna under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART- , SM/07923 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BAGHARPUR RAMNA (Village Code 314665) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 66 of 20-21 by SE MC | 402-MSD/21-22 | 23/03/2022 | 0 | M/S NIRAPADA BHATTACHARJEE | 28.13 | 0 | 0 | 0
1426 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bagharpur Ramna ( 314665 ) of Bagharpur Ramna under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART- , SM/07923 | Retrofitting | Continuation order for Holding Awarness Programme / Campaigning programs at Nowda G.P, Raypur G.P, Madhupur G.P, Sarbangapur G.P, Choa G.P, Hariharpara G.P, Mahula G.P, & Rangamati Chandpara G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | 690/MURD | 23/02/2021 | 30 | S.S.INFRASTRUCTURE | 3.18 | 6.35 | 200 | 0
1427 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Kulgachi (Code-314169), Bilnasipur (Code-314170), Singa (Code-314181), Salmara(Code-3174182),Haripur(Code-314185) , SM/07687 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bilnasipur (Village code 314170),Salmara(Village code 314182),Kulgachi( Village code 314169), Haripur( Village code 314185),Singa ( Village code 314181 ) under Nasipur Zone-I Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | 202/BD-I | 04/02/2021 | 30 | TARUN KUMAR BHATTACHARYA | 78.52 | 73.75 | 93.93 | 0
1428 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Kulgachi (Code-314169), Bilnasipur (Code-314170), Singa (Code-314181), Salmara(Code-3174182),Haripur(Code-314185) , SM/07687 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Kulgachi (Code-314169), Bilnasipur (Code-314170), Singa (Code-314181), Salmara(Code-3174182),Haripur(Code-314185) In The Command Area Of Nasipur Zone-I Ground Water Supply Scheme (Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1445/BD-I | 04/09/2024 | 60 | HI-LIGHT ELECTRONICS | 19.95 | 0 | 0 | 0
1429 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Telia Village (Code-314466) In The Command Area Of Telia Ground Water Supply Scheme (Part-B) , SM/07732 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Telia (Village code 314466) under Telia Ground Water Supply Scheme in Bhagawangola-I Block under Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-2) | 1906/BD-I | 08/10/2021 | 180 | RAJ KUMAR MONDAL | 103.96 | 95.85 | 100 | 1
1430 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Barabil Raghunathpur (314626) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murs , SM/07686 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village BARABIL RAGHUNATHPUR (Village Code-314626) under BARABIL RAGHUNATHPUR Ground Water Supply Scheme Arsenic Affected Area of Jalangi Block of Murshidabad District under Murshidabad Division, PHE Dte. Scheme ID 0001723213 | 26-MSD / 21-22 | 19/08/2021 | 0 | MITRA CONSTRUCTION | 52.92 | 0 | 0 | 0
1431 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Barabil Raghunathpur (314626) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murs , SM/07686 | Retrofitting | Additional work for Providing of Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village JOYRAMPUR (Village Code 314693) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 99 of 21-22 by EE MURD | 372-MSD/21-22 | 18/03/2022 | 0 | SAHABUDDIN BISWAS | 18.52 | 0 | 0 | 0
1432 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Barabil Raghunathpur (314626) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murs , SM/07686 | Retrofitting | Formal Work Order for Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Barabil Raghunathpur ( Village Code -314626) under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723213) in the District of Murshidabad.(Sl-30) | 525/MURD | 04/02/2021 | 180 | MITRA CONSTRUCTION | 138.32 | 14.85 | 100 | 0
1433 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Barabil Raghunathpur (314626) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murs , SM/07686 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Domkal (Village code 314695) under Domkal Ground Water Based Water Supply Scheme & & Barabil Raghunathpur (Village code 314626) for Arsenic Affected Area of Domkal & Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. (Sl No-15) | 3110/MURD | 09/12/2020 | 180 | ARINDAM MAJUMDAR | 48.25 | 0 | 0 | 80
1434 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Juranpur (314720) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) , SM/07909 | Retrofitting | Extension of pipeline from different (Juranpur & Tekaraipur) water supply scheme forn connection of Health Centre under Domkal & Raninagar-I Block under Islampur Sub-Division under Murshidabad Division, PHE Dte. | 380/1/ISD | 26/07/2021 | 30 | M/S. SAJEDA ENTERPRISE | 4.02 | 4.01 | 100 | 1
1435 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Juranpur (314720) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) , SM/07909 | Retrofitting | Extension of pipeline from different (Shibnagar laskarpur, juranpur, Juginda Zone-II, Tekaraipur, Garibpur Z-I, Aminabad) water supply scheme forn connection of Health Centre under Domkal & Raninagar-I Block under Islampur Sub-Division under Murshidabad Division, PHE Dte | 381/1/ISD | 26/07/2021 | 30 | NABIRUL ISLAM | 4.14 | 3.95 | 100 | 0
1436 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Juranpur (314720) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) , SM/07909 | Retrofitting | Providing Functional Household Tap Connections (FHTC) of 1467 nos in connection with (Jal Jeevan Mission ) and under command area of village of Juranpur ( Village Code -314720) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. | 1380/MURD | 26/05/2022 | 60 | M/S. S. DAS AND ENTERPRISE | 72.04 | 35.34 | 49.05 | 40
1437 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi , SM/07506 | Retrofitting | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Raghunathganj-II Block(Teghori, Kasiadanga,Laxmijhola & Sekhalipur) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (PART-B) | 125 /JSD | 25/05/2021 | 30 | S.S.INFRASTRUCTURE | 1.58 | 1.58 | 100 | 0
1438 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi , SM/07506 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00" x 4'00") which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Lalgola G.P, Paharpur G.P, Amdahara G.P, Kolan G.P, Kantanagar G.P, Mahammodpur G.P,Amarkundu G.P. & Shibpur G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. , tno- 13/21-22/AE LSD | 131-MSD/21-22 | 07/10/2021 | 0 | S.S.INFRASTRUCTURE | 2.32 | 0 | 0 | 0
1439 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi , SM/07506 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Lalbagh Sub-Division under Murshidabad Division, P.H.E Dte.(Amdahara GP, Mahammadpur GP & Kantanagar GP), TNO-14/21-22/EE | 131-MSD/21-22 | 07/10/2021 | 0 | S.S.INFRASTRUCTURE | 3.26 | 0 | 0 | 0
1440 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi , SM/07506 | Retrofitting | IEC PROGRAM AND VIDEO DOCUMENTARY AND OTHER AWARENESS WORK OF FHTC AT DIFFERENT PLACES UNDER LSD |  | 24/09/2021 | 0 | S.S.INFRASTRUCTURE | 9.91 | 0 | 0 | 0
1441 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi , SM/07506 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection (FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Lalbagh Sub-Division under Murshidabad Division, P.H.E Dte. (Shibpur G.P, Amarkundu G.P, Lalgola G.P. & Bilborakopra G.P., TNO- 15/21-22/AELSD | 131-MSD/21-22 | 07/10/2021 | 0 | S.S.INFRASTRUCTURE | 4.34 | 0 | 0 | 0
1442 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi , SM/07506 | Retrofitting | Allied work for rectrofitting providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Babupur (Village Code-314126) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. | 391/JSD | 31/12/2021 | 30 | BENGAL ENTERPRISE | 4.83 | 0 | 0 | 0
1443 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi , SM/07506 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village LAKSHIJALA (Village Code 314127) under KASIADANGA Ground Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-II Block in the District of Murshidabad. Tender no - 550 of 21-22 by EE MURD | 362-MSD/21-22 | 11/03/2022 | 0 | MARUTI CONSTRUCTION AND CO | 35.66 | 0 | 0 | 0
1444 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi , SM/07506 | Retrofitting | Laying of UPVC pipeline at village LAXMIJOLA WEST SIDE in connection with FHTC work under KASIADANGA (ZONE-I) W/S Scheme under JSD PHE DTE. Tender no - 55 of 21-22 by AE LSD | 25-MSD/22-23(RE | 28/04/2022 | 0 | PRADIP DAS | 4.67 | 0 | 0 | 0
1445 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi , SM/07506 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babupur ( Village Code 314126) under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001756852) | 380-MSD/21-22 | 16/03/2022 | 0 | BENGAL ENTERPRISE | 18.97 | 0 | 0 | 0
1446 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi , SM/07506 | Retrofitting | Laying of UPVC pipeline at village LAXMIJOLA WEST SIDE in connection with FHTC work under KASIADANGA (ZONE-I) W/S Scheme under JSD PHE DTE. Tender no - 55 of 21-22 by AE LSD | 25-MSD/22-23 | 11/04/2022 | 0 | PRADIP DAS | 4.67 | 0 | 0 | 0
1447 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Babupur ( 314126 ) & Lakshijala (314127) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshi , SM/07506 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Lakshijala ( Village Code -314127) under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) | 1468/MURD | 21/06/2021 | 60 | MARUTI CONSTRUCTION AND CO | 35.66 | 0 | 0 | 0
1448 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe , SM/07667 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village LAHARPARA (Village Code 315282) under Bahara Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. | 2880/MURD | 12/11/2020 | 45 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 32.21 | 8.94 | 27.77 | 0
1449 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe , SM/07667 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00'' x 4'00'') which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Gokarna-II G.P, Mahalandi-I G.P, Kumarsanda G.P, Jasahari Anukha-I & II G.P, Burwan- I & II G.P, Panchthupi G.P & Sohara G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | 176/KSD | 28/05/2021 | 30 | IMAGIN | 2.61 | 2.61 | 100 | 1
1450 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe , SM/07667 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BAHARA (Village Code 315291) under Bahara Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. | 3021/MURD | 04/12/2020 | 45 | M/S. BIMALENDU BOSE | 25.13 | 24.83 | 100 | 0
1451 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe , SM/07667 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of BHANDIRA habitation under Bhandira (Village Code: 315292) under BAHARA Surface Water Based Water Supply Scheme for arsenic affected areas of KANDI Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 398 of 20-21 by EE / MSD | 08 -MSD / 21-22 | 04/08/2021 | 0 | M/S GUNGUN CONSTRUCTION | 22.54 | 0 | 0 | 0
1452 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe , SM/07667 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) of Bahara & Ghoshbati habitation under command area of Bahara village (Village Code- 315291) of Bahara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Kandi Block under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad.(SL_03) | 156/KSD | 31/08/2022 | 45 | SIMA ENTERPRISE | 4.84 | 4.8 | 100 | 1
1453 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe , SM/07667 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | 215/KSD | 11/08/2021 | 30 | IMAGIN COMMUNICATION | 4.33 | 0 | 0 | 0
1454 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe , SM/07667 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JASAHARI ANUKHA-I G.P. under Murshidabad Division, P.H.E.Dte. | 225/KSD | 27/08/2021 | 60 | IMAGIN | 4.17 | 0 | 0 | 0
1455 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe , SM/07667 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at GOKARNA-I G.P. under Murshidabad Division, P.H.E.Dte. | 242/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0 | 0
1456 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe , SM/07667 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JASAHARI ANUKHA-II G.P. under Murshidabad Division, P.H.E.Dte. | 226/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.17 | 0 | 0 | 0
1457 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe , SM/07667 | Retrofitting | Laying of rising main (DI) from tube well to 300 Cum OHR and laying of distribution main (DI) from OHR to distribution system including supply of C.I. specials and restoration work of concrete road of Bahara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 05/KSD | 06/04/2022 | 30 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 4.85 | 4.59 | 100 | 1
1458 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe , SM/07667 | Retrofitting | Construction of valve chamber & laying of upvc pipe line including supply of C.I. specials and valves in connection with FHTC work of Bahara village (Village Code-315810) under Bahara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. (SL-01) | 154/KSD | 31/08/2022 | 30 | BISWAS CONSTRUCTION | 4.55 | 4.54 | 100 | 1
1459 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe , SM/07667 | Retrofitting | Laying of pipe line for distribution system from node point 1B to 1C & laying of rising main from H.W Site to 2nd tube well site under Improvement work of Bahara water supply scheme under Kandi Sub Division, P.H.E.Dte in the district of Murshidabad. | 3109/MURD | 09/12/2020 | 30 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 4.84 | 4.81 | 99.47 | 0
1460 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Laharpara, Brahmanpara, Bahara, Bhandira, Dohalia (315282, 315290, 315291, 315292 & 315294) of Bahara under Ground Water Based Water Supply Scheme for Arsenic Affe , SM/07667 | Retrofitting | Laying of different dia UPVC pipe line from node point 45 to node point 3 & node point 45 to node point 1E for distribution network with supply of materials for pipe line under Improvement work of Bahara water supply scheme under Kandi Sub Division, P.H.E.Dte in the district of Murshidabad. | 3222/MURD | 18/12/2020 | 30 | KUNTAL SAHA | 4.86 | 4.85 | 100 | 1
1461 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh , SM/07510 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Accoan of Togra (Village Code 315978) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no-736 of 20-21 by EE / MSD |  | 01/07/2021 | 0 | SUPTI ENTERPRISE | 7.26 | 0 | 0 | 0
1462 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh , SM/07510 | Retrofitting | Retrofitting functional hoyusehold tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of Village MUNIADIHI under PANCHTHUPI Ground Based W/S Scheme for Arsenic Affected area of Burwan Block under MSD PHE DTE. Scheme Id:0007335523 in the dist of Murshidabad. Sl. No.23 Tender no 63 SE/MC 20-21 | 03/MSD/21-22 | 16/07/2021 | 0 | DECON INDIA | 23.9 | 0 | 0 | 0
1463 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh , SM/07510 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of Togra ( 315978 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-II ) TNO- 736/20-21/EE | 04/MSD/21-22 | 16/07/2021 | 0 | SUPTI ENTERPRISE | 7.26 | 0 | 0 | 0
1464 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh , SM/07510 | Retrofitting | Restoration work of UPVC pipeline & road restoration work including laying of CI/DI pipeline for smooth supply of drinking water at Panchthuppi Bus Stand area under Panchthuppi Water Supply Scheme under Kandi Sub-Division, P.H.E. Dte.in the District Murshidabad | 320/KSD | 16/11/2021 | 30 | SUPTI ENTERPRISE | 4.83 | 4.82 | 100 | 0
1465 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh , SM/07510 | Retrofitting | Balance estimate for the laying of UPVC distribution pipeline for FHTC work at Muslim Para in the Village of Muniadihi of Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E Dte.in the district of Murshidabad. | 322/KSD | 16/11/2021 | 30 | APURBA SAHA CHOWDHURY | 4.83 | 4.79 | 100 | 0
1466 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh , SM/07510 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Muniadihi (Village Code- 315982) under Panchthupi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block under Murshidabad Division, P.H.E.Dte. (SL-02) | 155/KSD | 31/08/2022 | 45 | SARTHAK SK. | 4.81 | 3.17 | 100 | 0
1467 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh , SM/07510 | Retrofitting | Laying of UPVC distribution pipeline for FHTC work at Mirjapara & Bagdipara in the Village of Muniadihi Panchthupi W/S Scheme under KSD PHE DTE. Tender no - 40 of 21-22 by AE KSD | 354-MSD/21-22 | 05/03/2022 | 0 | DECON INDIA | 4.81 | 0 | 0 | 0
1468 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh , SM/07510 | Retrofitting | Balance estimate for the laying of UPVC distribution pipeline for FHTC work at Chatterjee Para in the Village of Muniadihi of Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E Dte.in the district of Murshidabad. Tender no: 39 of 21-22 by AE KSD | 356-MSD/21-22 | 05/03/2022 | 0 | DECON INDIA | 4.82 | 0 | 0 | 0
1469 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh , SM/07510 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MUNIADIHI under PANCHTHUPUI Ground Water Based Water Supply Scheme for arsenic affected areas of BURWAN Block under Murshidabad Div PHE DTE in the District of Murshidabad. Tender no - 63 of 20-21 by SE MC | 355-MSD/21-22 | 07/03/2022 | 0 | DECON INDIA | 15.99 | 0 | 0 | 0
1470 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh , SM/07510 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with JALSWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village TOGRA (Village Code 315978) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. | 192-MSD/22-23 | 29/06/2022 | 0 | SUPTI ENTERPRISE (PROP.DEBAPRIYA SAHA) | 3.11 | 0 | 0 | 0
1471 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh , SM/07510 | Retrofitting | Balance estimate for the laying of UPVC distribution pipeline for FHTC work at Mirjapara & Bagdipara in the Village of Muniadihi of Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E Dte.in the district of Murshidabad. | 324/KSD | 16/11/2021 | 30 | DECON INDIA | 4.84 | 0 | 0 | 0
1472 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh , SM/07510 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | 214/KSD | 11/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.34 | 0 | 0 | 0
1473 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Phupra, Togra & Muniadihi ( 315977, 315978 & 315982 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Mursh , SM/07510 | Retrofitting | Continuation order for Holding Awarness Programme / Campaigning programs at Chandpur-I II G.P, Bali G.P, Patikabari G.P, Madhupur G.P, Kedar Chandpur-I G.P, Khidirpur G.P, Humaipur G.P, Rampara-I G.P, Andulberia G.P, Dadpur G.P, Rampara-II G.P, Mirzapur-I & II G.P, Kumarpur Sujapur G.P, Debkunda G.P, Madda G.P, Sahajadpur G.P, Niyallishpara G.P, Satui Chowrigachha G.P, Shaktipur G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | 691/MURD | 23/02/2021 | 30 | IMAGIN | 4.77 | 9.53 | 200 | 0
1474 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Benipur (Code-314546) In The Command Area Of Benipur Ground Water Supply Scheme (Part-A) Under Bhagwangola-II Bloc , SM/07789 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Benipur (Village code 314546) under Benipur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | 191/BD-I | 04/02/2021 | 30 | SRIJON ENTERPRISE | 92.74 | 153.74 | 195 | 1
1475 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Siddhikhali(Village Code 314021) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block in the District of Murshidabad. | 2395/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 11.73 | 8.43 | 71.88 | 1
1476 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of KANKARIA VILLAGE OF Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I), TNO- 761/2020-21/EE | 01/MSD/21-22 | 15/07/2021 | 0 | MAMATA USHA ENTERPRISE | 20.68 | 0 | 0 | 0
1477 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Holding Awarness Progmramme /Campaigning programms at Chandpur-I , II GP, Bali GP, Patikabari GP, Madhupur GP, Kedar Chandpur GP, Khidirpur GP, Humaipur GP, Rampara-I GP, Andulberia GP, Dadpur GP Rampara-II GP Mirjapur GP Kumarpur Sujapur GP in connection with Functional Household Tap Connection FHTC under MSD PHE DTE. Tender no 155 of 21-22 by EE | 34-MSD/21-22 | 23/08/2021 | 0 | IMAGIN | 4.77 | 0 | 0 | 0
1478 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna OF DEULI VILLAGE (313998)(JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District. TNO- | 136-MSD/21-22 | 07/10/2021 | 0 | SANJAY BISWAS | 41.68 | 0 | 0 | 0
1479 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) RAMAKANTAPUR VILLAGE CODE 314029 of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I), TNO- 65/20-21/SE-MC | 125-MSD/21-22 | 07/10/2021 | 0 | M/S. SINHA & SONS | 17.47 | 0 | 0 | 0
1480 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village SUJAPUR (Village Code: 313996) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 114 of 20-21 by SE / MC | 22-MSD / 21-22 | 11/08/2021 | 0 | SAMBHU NATH ROY | 13.29 | 0 | 0 | 0
1481 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village Ramakantapur (Village Code- 314029) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 65 of 20-21 by SE / MC | 08 -MSD / 21-22 | 06/08/2021 | 0 | MS SINHA AND SONS | 39.66 | 0 | 0 | 0
1482 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Holding Awarness programme / Campaigning programs at Chandpur GP Radharghar I & II GP Ramnagar Bachhara GP Somprra =I GP Doulabad GP & Chhaighari GP connection with functional household tap connection FHTC under MSD PHE DTE. Tenter no 154 of 21-22 by EE | 33-MSD/21-22 | 23/08/2021 | 0 | IMAGIN COMMUNICATION | 3.17 | 0 | 0 | 0
1483 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Holding Awarness programme / Campaigning programs at Nowda GP, Roypur GP, Madhupur GP, Sarbangpur GP, Choa GP, Hariharpara GP, Mahula GP & Rangamati Chandpara GP connection with functional household tap connection FHTC under MSD PHE DTE. Tenter no 153 of 21-22 by EE | 32-MSD/21-22 | 23/08/2021 | 0 | S.S.INFRASTRUCTURE | 3.18 | 0 | 0 | 0
1484 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) VILLAGE CODE- 314009, TNO- 75/20-21/SE-MC | 194-MSD/21-22 | 18/11/2021 | 0 | M/S UNIVERSAL TRADING | 41.08 | 0 | 0 | 0
1485 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION )' from existing Distribution system within the Command area of village SONATIKRI ( Village Code -313995) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. 2566/MURD, 01/10/2020 | 175-MSD/21-22 | 02/11/2021 | 0 | J.S. CONSTRUCTION | 16.47 | 0 | 0 | 0
1486 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village DAFARPUR (Village Code: 314055) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 113 of 20-21 by SE / MC | 23-MSD / 21-22 | 11/08/2021 | 0 | SAMBHU NATH ROY | 23.13 | 0 | 0 | 0
1487 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of Village JARUR (Village Code: 314011) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 47 of 20-21 by SE / MC | 19-MSD / 21-22 | 06/08/2021 | 0 | NOVELTY CONSTRUCTION | 39.68 | 0 | 0 | 0
1488 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Jal Swapna (JJM) from existing distribution system within the command area of village JEETHIA (Village Code: 314030) under surface Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 488 of 20-21 by EE / MSD | 21-MSD / 21-22 | 13/08/2021 | 0 | DEBASIS BOSE | 15.79 | 0 | 0 | 0
1489 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of VILLAGE SANTOSHPUR UNDER Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District, TNO- 502/20-21/EE | 06/MSD/21-22 | 16/07/2021 | 0 | MODERN CONSTRUCTION | 10.59 | 0 | 0 | 0
1490 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with Jal Swapna (Jal Jeevan Mission) from existing Distribution system within the command area of village AMGACHHI (Village Code -314031) under surface Water Based Water Supply Scheme for Arsenic Affected Areas of RAGHUNATHGANJ-I Block in the Dist of MSD under Murshidabad Division P.H.E Dte. | 57-MSD/21-22 | 14/09/2021 | 0 | M/S. GHOSH ENTERPRISE | 4.47 | 0 | 0 | 0
1491 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Talai (Village code 314018) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. Tender no - 57 of SE/MC OF 20-21 | 54-MSD/21-22 | 14/09/2021 | 0 | DECON INDIA | 26.12 | 0 | 0 | 0
1492 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) VILALGE NAIT BAIDHARA CODE-314004 of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I), TNO- 53/20-21/EE | 126-MSD/21-22 | 11/10/2021 | 0 | SANJAY BISWAS | 17.94 | 0 | 0 | 0
1493 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jarur(Village code 314011) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-8) | 3066 / MURD | 08/12/2020 | 180 | NOVELTY CONSTRUCTION | 54.9 | 0 | 0 | 1
1494 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village BIJOYPUR (Village Code 314032) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. | 2562/MURD | 01/10/2020 | 45 | SAMBHU NATH ROY | 19.69 | 15.96 | 100 | 0
1495 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna Jal Jeevan Mission and Jal Swapna under command area of village of Sujapur(P) ( Village Code -313996) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. Scheme I.D.-0001756489 in the District of Murshidabad. | 162-MSD/22-23 | 17/05/2022 | 0 | SAMBHU NATH ROY | 20.19 | 0 | 0 | 0
1496 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village SANTOSHPUR (Village Code 314045) under surface Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the District of Murshidabad. Tender no - 502 of 20-21 by EE MURD | 32-MSD/21-22 | 21/04/2022 | 0 | MODERN CONSTRUCTION | 2.37 | 0 | 0 | 0
1497 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of RAMNAGAR VILLAGE CODE 314056 Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District | 207-MSD/21-22 | 08/12/2021 | 0 | TRIDIP MAZUMDER | 25.05 | 0 | 0 | 0
1498 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) |  | 17/02/2022 | 0 | S. DUTTA | 13.24 | 0 | 0 | 0
1499 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission) " from existing Distribution system within the Command area of village BAIDPUR (Village Code 314026) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. Tender no - 501 of 20-21 by EE MURD | 325-MSD/21-22 | 22/02/2022 | 0 | S. DUTTA | 13.24 | 0 | 0 | 0
1500 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of SEKENDRA (Village code 314064) under SEKENDRA Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184141 | 91-MSD/22-23 | 02/05/2022 | 0 | DOBAY CONSTRUCTION | 54.19 | 0 | 0 | 0
1501 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. WORK ORDER NO & DT. - 223 / HQ DATE- 26/05/2022 | 325-MSD/22-23 | 30/09/2022 | 0 | DULAL CHOWDHURY | 0.78 | 0 | 0 | 0
1502 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | CONT OF AWARENESS PROGRAMME AT DIFFERENT G.PS, TNO- 57/21-22/EE | 205-MSD/21-22 | 08/12/2021 | 0 | IMAGIN | 3.98 | 0 | 0 | 0
1503 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with 'JAL SWAPNA(JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of Khidirpur(Village Code 313993) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block in the District of Murshidabad. | 326-MSD/21-22 | 24/02/2022 | 0 | M/S. SABANA CONSTRUCTION (PROP:MD. SAIDUR RAHAMAN) | 30.82 | 0 | 0 | 0
1504 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village NISTA (Village Code 314017) under Surface Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the District of Murshidabad. Tender no - 619 of 21-22 by EE MURD | 328-MSD/21-22 | 25/02/2022 | 0 | M/S. S. DAS AND ENTERPRISE | 15.54 | 0 | 0 | 0
1505 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village CHAR DAFARPUR (Village Code 314047) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block in the District of Murshidabad. Tender no - 497 of 20-21 by EE MURD | 409-MSD/21-22 | 23/03/2022 | 0 | GOUTAM CHAKRABORTY | 36.1 | 0 | 0 | 0
1506 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | PAYMENT OF FEES OF ONLINE APPLICATION OF RAIL CROSSING PROCESS. | 363-MSD/21-22 | 11/03/2022 | 0 | FA & CAO EASTERN RAILWAY | 2.02 | 0 | 0 | 0
1507 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village NATUN (Village Code 314043) and adjoining habitation under Raghunathganj-I Surface Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the District of Murshidabad. Tender no - 56 of 21-22 by SE MC | 34-MSD/22-23 | 14/04/2022 | 0 | AJOY MONDAL | 37.08 | 0 | 0 | 0
1508 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Deposit of way leave charges for-Way leave permission for crossing of 200 mm dia water pipeline raising main through 600 mm dia MS Casing pipe under Railway track between stations Ahiron Halt & Jangipur Road at km. 216/9-217/0 under Malda Division of Eastern Railway, Way leave permission for crossing of 200 mm dia water pipeline raising main through 600 mm dia MS Casing pipe under Railway track between stations Ahiron Halt & Jangipur Road at km. 212/0-1 under Malda Division of Eastern Railway, Way leave permission for crossing of 150 mm dia water pipeline raising main through 600 mm dia MS Casing pipe under Railway track between stations Ahiron Halt & Jangipur Road at km. 210/9-211/0 under Malda Division of Eastern Railway and Way leave permission for crossing of 100 mm dia water pipeline raising main through 600 mm dia MS Casing pipe under Railway track between station Ahiron Halt & Jangipur Road at km. 204/2-3 under Malda Division of Eastern Rail. REF:MEMO NO-1050/MURD, DT- 05/04/21. | 292-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 32.2 | 0 | 0 | 0
1509 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Continuation work order for Hiring of one no. Bolero Car/Marshal (CAR 57- 9120) Same category for official use of the Assistant Engineer, JSD, P.H.Engineering Dte. Berhampore, Murshidabad. WORK ORDER NO & DT. - 88 / JSD DATE- 22/02/2022. | 334-MSD/22-23 | 30/09/2022 | 0 | MANUAR HOSSAIN | 0.4 | 0 | 0 | 0
1510 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Laying of 200 mm dia MS Water Carring pipe with 600 mm dia MS PIPE as casing at chainge Raghunathganj Surface Water Based W/S Scheme block Raghunathganj-I Block under MSD PHE DTE. Tender no - 930 of 20-21 by EE MURD | 37-MSD/22-23 | 14/04/2022 | 0 | SAMBHU NATH ROY | 24.74 | 0 | 0 | 0
1511 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with 'Jal Swapna (Jal Jeevan Mission ) 'from existing Distribution system within the Command area of village BARALA (Village Code 314009) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. Tender no - 75 of 20-21 by SE MC | 330-MSD/21-22 | 25/02/2022 | 0 | M/S UNIVERSAL TRADING | 7.36 | 0 | 0 | 0
1512 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna Jal Jeevan Mission and Jal Swapna under command area of village of Dafarpur (C.T.) ( Village Code -314055) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. Scheme I.D.-0001756489 in the District of Murshidabad. | 383-MSD/21-22 | 17/03/2022 | 0 | SAMBHU NATH ROY | 59.53 | 0 | 0 | 0
1513 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village JARUR (Village Code 314011) under Surface Based Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-I Block in the District of Murshidabad. Tender no - 47 of 20-21 by SE MC (NEW) | 36-MSD/22-23 | 23/04/2022 | 0 | NOVELTY CONSTRUCTION | 5.22 | 0 | 0 | 0
1514 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION )' from existing Distribution system within the Command area of village SONATIKRI ( Village Code -313995) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. | 72-MSD/22-23 | 26/04/2022 | 0 | J.S. CONSTRUCTION | 27.59 | 0 | 0 | 0
1515 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission ) "from existing Distribution system within the Command area of village JAGADANANDABATI(Village Code 314028) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad . | 2559 /MURD | 01/10/2020 | 45 | SUDIPA SINGHA ROY | 16.27 | 14.4 | 88.49 | 0
1516 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Work of Extension of Existing Boundary wall along with painting work at Jotkamal (Zone-I) water supply scheme , under Raghunathganj-II Block, under Jangipur Sub-Division, P.H.E. Dte in the District Murshidabad. | 383/JSD | 31/12/2021 | 30 | MOLLA ENTERPRISE | 4.83 | 4.68 | 100 | 1
1517 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission ) "from existing Distribution system within the Command area of village KULRI (Village Code 314022) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad . | 2554/MURD | 01/10/2020 | 45 | JAMIRUL CONSTRUCTION | 14.17 | 6.11 | 100 | 0
1518 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village BAINDA (Village Code 314003) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad | 2552/MURD | 01/10/2020 | 45 | SAMBHU NATH ROY | 21.88 | 9.57 | 100 | 0
1519 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Material Requisition To Resource Division | 540/1/MURD | 25/02/2022 | 0 | Resource Division | 15.28 | 0 | 0 | 0
1520 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Rajnagar (Village code 314041) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. | 1653/MURD | 29/06/2021 | 90 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 45.88 | 0 | 0 | 80
1521 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna Jal Jeevan Mission and Jal Swapna under command area of village of Sujapur(P) ( Village Code -313996) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. Scheme I.D.-0001756489 in the District of Murshidabad. | 958/MURD | 24/03/2021 | 180 | SAMBHU NATH ROY | 46.33 | 9.96 | 21.49 | 0
1522 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna Jal Jeevan Mission and Jal Swapna under command area of village of Dafarpur (C.T.) ( Village Code -314055) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. Scheme I.D.-0001756489 in the District of Murshidabad. | 959/MURD | 24/03/2021 | 180 | SAMBHU NATH ROY | 107.46 | 35.72 | 33.24 | 0
1523 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Natun(Village code 314043) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-5) | 3056/MURD | 08/12/2020 | 180 | AJAY MONDAL | 46.31 | 0 | 0 | 1
1524 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Deuli(Village code 313998) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-11) | 3065/MURD | 08/12/2020 | 180 | SANJAY BISWAS | 57.02 | 0 | 0 | 1
1525 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Road Restoration work because of damaging due to laying of different dia UPVC pipe line in connection with FHTC Work at Khidirpur (Village code- 313993) under Surface water based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block of Jangipur Sub-Division under Murshidabad Division, P.H.E Dte in the district of Murshidabad. | 19/MURD | 03/01/2024 | 30 | M/S. SABANA CONSTRUCTION (PROP:MD. SAIDUR RAHAMAN) | 3.78 | 0 | 0 | 0
1526 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Talai(Village code 314018) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-7) | 3118/MURD | 09/12/2020 | 180 | DECON INDIA | 55.72 | 17.95 | 50 | 1
1527 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jarur(Village code 314011) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-8) | 3066/MURD | 08/12/2020 | 180 | NOVELTY CONSTRUCTION | 54.9 | 9.98 | 100 | 1
1528 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Laying of 250 mm D.I Pipe for clear water rising main by Open-Cut method from Umarpur more (Chainage 0.00 KM) to Mitrapur (Chainage 7.50 KM) along right hand flank of bituminous road,PWD for Raghunathganj Surface Water Based Water Supply Scheme (Raghunathganj-I Block) of Jangipur Sub-Division under Murshidabad Division, P.H.Engineering Dte. | 397/MURD | 16/02/2022 | 45 | SANJAY BISWAS | 31.87 | 20.28 | 100 | 100
1529 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Allied work of pipeline and Platform at DEULI village under Raghunathganj Surface Based Water Supply Scheme for HGJ of Jangipur Sub-Division under Murshidabad Division, PHE Dte. | 3033/MURD | 27/09/2023 | 30 | SAMBHU NATH ROY | 6.17 | 6.17 | 100 | 100
1530 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mirzapur (Village code 314057) under Surface Water Based water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. | 1580/MURD | 25/06/2021 | 180 | APURBA SAHA CHOWDHURY | 45.85 | 0 | 0 | 80
1531 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission) " from existing Distribution system within the Command area of village BAIDPUR (Village Code 314026) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. | 2553/MURD | 01/10/2020 | 45 | S. DUTTA | 13.25 | 0 | 0 | 0
1532 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village GANKAR (Village Code 314037) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. | 2561/MURD | 01/10/2020 | 45 | DECON INDIA | 41.51 | 37.3 | 89.86 | 1
1533 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Providing Functional Household Tap Connections (FHTC) of 1579 nos in connection with Jal Swapna (Jal Jeevan Mission ) under Command area of Village of Selalpur, Uttar Ramna, Simla, Dhalo, Kanchanpur, Paikar & Panchanpara ( Village Code -314023,314051,314020,314036,314049,314038,314044) under Raghunathganj-I Surface Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. | 895/MURD | 05/04/2022 | 60 | MOTI RAHAMAN | 97.06 | 95.54 | 98.44 | 1
1534 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Siddhikhali (Village Code 314021) under Surface Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj-I Block in the District of Murshidabad. | 2395/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 11.73 | 3.26 | 100 | 0
1535 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village of Jethia( Village Code-314030)under Surface Water Based Water Supply Scheme form Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad. | 2527/MURD | 30/09/2020 | 45 | DEBASIS BOSE | 34.11 | 7.1 | 100 | 100
1536 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Providing Functional Household Tap Connections (FHTC) of 1190 nos in connection with Jal Swapna (Jal Jeevan Mission ) under Command area of Village of Birthamba, Sendajamuar & Mandalpur ( Village Code -314006, 314007, 314008) under Raghunathganj-I Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block under Murshidabad Division P.H.E Dte. . | 1137/MURD | 02/05/2022 | 60 | PRADIP KUMAR DAS | 64.77 | 60.06 | 100 | 0
1537 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Raghunathganj-I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I Block of Murshidabad District (PART-I) , SM/08189 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission )" from existing Distribution system within the Command area of village AMGACHHI (Village Code 314031) under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-I Block in the District of Murshidabad . | 2557/MURD | 01/10/2020 | 45 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 19.24 | 0.24 | 100 | 100
1538 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhagirathpur (314699) of Bhagirathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) , SM/08272 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna Mission under command area of village of BHAGIRATHPUR (VILLAGE CODE 314699) under BHAGIRATHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block of Murshidabad District under Murshidabad Division, PHE Dte. Tender no- 105 of 20-21 by SE / MC | 20-MSD / 21-22 | 06/08/2021 | 0 | PROJECT INDIA | 47.31 | 0 | 0 | 0
1539 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhagirathpur (314699) of Bhagirathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) , SM/08272 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Bhagirathpur (Village Code -314699) under Bhagirathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. | 3342/MURD | 15/12/2022 | 30 | PROSENJIT DAS | 34.64 | 0 | 0 | 0
1540 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhagirathpur (314699) of Bhagirathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) , SM/08272 | Retrofitting | Preparation of D.P.R(Consultancy work) in connection with the Functional Household Connection of different existing PWSS (Momenpur PWSS Scheme,Block- Domkal)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 376 of 21-22 by EE MSD, and Scheme Code: 8272 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 4.88 | 0 | 0 | 0
1541 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhagirathpur (314699) of Bhagirathpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) , SM/08272 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BHAGIRATHPUR (Village Code 314699) under BHAGIRATHPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 105 of 20-21 by SE MC | 358-MSD/21-22 | 09/03/2022 | 0 | PROJECT INDIA | 56.97 | 0 | 0 | 0
1542 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sekendra (314064) of Sekendra under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) , SM/08280 | Retrofitting | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Raghunathganj-II Block (Giria,Sekendra, Mithipur,Jotkamal,Dayarampur & Sammatinagar ) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte.(PART-A) | 122 /JSD | 22/05/2021 | 30 | S.S.INFRASTRUCTURE | 2.38 | 2.38 | 100 | 1
1543 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sekendra (314064) of Sekendra under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) , SM/08280 | Retrofitting | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS SEKENDRA PWSS Scheme, Block-RAGHUNATHGAUNGE-II to be Augmention/Rejuvination under Murshidabad Division, P.H.E. Dte. | 3256/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 6.68 | 13.36 | 200 | 1
1544 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sekendra (314064) of Sekendra under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) , SM/08280 | Retrofitting | Material Requisition To Resource Division | 540/13/MURD | 25/02/2022 | 0 | Resource Division | 21.96 | 0 | 0 | 0
1545 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sekendra (314064) of Sekendra under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) , SM/08280 | Retrofitting | SHIFTING OF HT OVERHEAD LINE BR ERECTION XLPE UG CABLE AT GHANSHYAM CHAK PUMP HOUSE NO-I, ZONE-II | 588-MSD/22-23 | 06/03/2023 | 0 | WBSEDCL | 3.92 | 0 | 0 | 0
1546 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sekendra (314064) of Sekendra under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) , SM/08280 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of SEKENDRA (Village code 314064) under SEKENDRA Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184141 | 3977/MURD | 21/12/2021 | 180 | DOBAY CONSTRUCTION | 159.44 | 80.23 | 100 | 1
1547 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sekendra (314064) of Sekendra under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) , SM/08280 | Retrofitting | Formal work order for Laying Distribution System ,FHTC, Construction of 1 (one) no Pump House (4.25m x 3.60m with sanitary and Water Supply Arrangement), Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement and 2(two) nos Pump House repairing. Repairing of Existing OHR Part for Augmentation of SEKENDRA PWSS in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE. Dte. | 445/MURD | 17/02/2023 | 846 | NAYLA CONSTRUCTION | 255.21 | 16.08 | 100 | 90
1548 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ratanpur ( 313841 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Mursh , SM/09745 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL- 05 | 309-MSD/22-23 | 29/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 13.05 | 0 | 0 | 0
1549 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Alampur ( 313932 ) of Ghorapakhiagangin Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District u , SM/09738 | Retrofitting | Material Requisition To Resource Division | 540/5/MURD | 25/02/2022 | 0 | Resource Division | 3.95 | 0 | 0 | 0
1550 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Alampur ( 313932 ) of Ghorapakhiagangin Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Block of Murshidabad District u , SM/09738 | Retrofitting | Providing Functional Household Tap Connections (FHTC) 720 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Alampur ( Village Code -313932) under Ghorapakhiagangin Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. | 1054/MURD | 25/04/2022 | 30 | PROSENJIT DAS | 34.86 | 32.33 | 50 | 0
1551 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No , SM/10036 | Retrofitting | Laying of 140mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 169/BSD | 12/04/2022 | 15 | M/S.S.S. ENTERPRISE | 4.84 | 0 | 0 | 0
1552 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No , SM/10036 | Retrofitting | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-I | 170/BSD | 12/04/2022 | 15 | SOUNAK ENTERPRISE | 4.85 | 0 | 0 | 0
1553 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No , SM/10036 | Retrofitting | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-B | 162BSD | 12/04/2022 | 15 | A.S. MONDAL ENTERPRISE | 4.84 | 4.84 | 100 | 0
1554 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No , SM/10036 | Retrofitting | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-II | 168/BSD | 12/04/2022 | 15 | SOUVIK HALDER | 4.86 | 4.86 | 100 | 0
1555 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No , SM/10036 | Retrofitting | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raypur (village code 315531) under Surangapur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-A | 160/BSD | 12/04/2022 | 15 | BARMAN ENTERPRISE | 4.84 | 4.84 | 100 | 0
1556 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No , SM/10036 | Retrofitting | LAYING OF 140MM DIA FHTC ........ RAYPUR UNDER SURANGAPUR W/S SCHEME UNDER MSD PHE DTE. TENDER NO 213 OF 21-22 | 177-MSD/22-23 | 17/05/2022 | 0 | M/S SS ENTERPRISE (SUKESH GHOSH) | 4.84 | 0 | 0 | 0
1557 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No , SM/10036 | Retrofitting | Material Requisition To Resource Division | 889/A/MURD | 05/04/2022 | 0 | Resource Division | 58.9 | 0 | 0 | 0
1558 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raypur (315531), Madhupur (315532) Kanapara (315541) and Sakua (315542) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of No , SM/10036 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village of Raypur, Kanapara, Sakua, Madhupur (Village code 315531, 315541, 315542, 315532) under Surangapur Ground Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0005182885) | 479/MURD | 22/02/2022 | 1348 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 398.73 | 30.22 | 7.58 | 30
1559 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhandata (314524) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad District under , SM/09755 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bhandara(Village code 314524) under Bhandara Ground Water Based water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl No-07) | 3047/MURD | 07/12/2020 | 180 | DEBASIS BOSE | 57.23 | 26.71 | 100 | 0
1560 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bhandata (314524) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad District under , SM/09755 | Retrofitting | Laying of UPVC pipeline for allied works of retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Jeevan mission and Jal Swapna under command area of village of BHANDARA(village code- 314524) under Bhandara Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola-I & II Block under Murshidabad Division ,PHE Dte. in the district of Murshidabad.(Schemre ID- 0005104709) | 1240/MURD | 11/05/2022 | 30 | DEBASIS BOSE | 9.86 | 7.62 | 100 | 0
1561 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Palasi Sonadanga (314527) and Ramnapara (314496) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Bloc , SM/09756 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Palasi Sonadanga(Village code 314527) under Bhandara Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division,PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl No-06) | 3131/MURD | 10/12/2020 | 180 | M/S. SINHA & SONS | 46.65 | 40.79 | 100 | 0
1562 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Basabari ( 315345 ) of Basabari under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Murshidabad , SM/09836 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at HUMAIPUR G.P. under Murshidabad Division, P.H.E.Dte. | 336/BSD | 27/08/2021 | 30 | IMAGIN COMMUNICATION | 4.16 | 4.16 | 100 | 0
1563 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Basabari ( 315345 ) of Basabari under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Murshidabad , SM/09836 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Basabari (Village code 315340) under Basabari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723194 in the District of Murshidabad. | 2643 /MURD | 27/08/2021 | 60 | AZAD ENTERPRISE | 21.66 | 20.16 | 55.23 | 0
1564 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Basabari ( 315345 ) of Basabari under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Murshidabad , SM/09836 | Retrofitting | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. for Augmentation of Ground Water Based Malibari PWSS under Murshidabad Division, PHE Dte. | 154/ISD | 17/03/2022 | 30 | MABCO GEOTEST ASSOCIATES | 1.48 | 1.48 | 100 | 1
1565 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Basabari ( 315345 ) of Basabari under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Murshidabad , SM/09836 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
1566 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10010 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (Edrakpur PWSS Scheme, Block - Nowda) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3275/MURD | 05/10/2021 | 60 | RADIANT | 6.22 | 6.22 | 100 | 1
1567 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10010 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Edrakpur Water Supply Scheme of TW-I at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3067/MURD | 17/11/2022 | 30 | M/S B.R. SUPPLIERS | 10.6 | 9.98 | 100 | 100
1568 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10010 | Augmentation | Material Requisition To Resource Division | 1210/MURD/01 | 02/05/2023 | 0 | Resource Division | 11.39 | 0 | 0 | 0
1569 | MURSHIDABAD | Berhampore Mechanical | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10010 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Edrakpur ground water based water supply scheme under Block- Nowda, Dist. Murshidabad under MEDB, PHE Dte. | 1887/MEDB | 16/06/2023 | 92 | SRI KRISHNA NIRMAN | 11.66 | 10.05 | 86.25 | 50
1570 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10010 | Augmentation | Material Requisition To Resource Division | 305/MURD/3 | 29/01/2024 | 0 | Resource Division | 9.58 | 0 | 0 | 0
1571 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10010 | Augmentation | Material Requisition To Resource Division | 112/MURD/06 | 11/01/2024 | 0 | Resource Division | 26.32 | 0 | 0 | 0
1572 | MURSHIDABAD | Berhampore Mechanical | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10010 | Augmentation | NEW CONNECTION EDRAKPU PH-I | 471/WBSEDCL-JJM | 20/03/2024 | 0 | WBSEDCL | 20.76 | 0 | 0 | 0
1573 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10010 | Augmentation | Construction Pump House with chlorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) and 55 mtr. Boundary wall at 3rd Tubewell site of Gangadhari & Edrakpur Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | 2152/MURD | 29/07/2024 | 480 | PARUL ELECTRICAL INSTALLER | 16.6 | 0 | 0 | 80
1574 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10010 | Augmentation | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagaipur PWSS TW-I,II, Chandpur Zone-I PWSS T.W.-II, Edrakpur PWSS T.W-II, Surangapur Zone-IA TW-I of Nowda Block under Berhampore Sub-Division,Murshidabad Division, P.H.Engineering Dte. | 663/MURD | 19/03/2025 | 65 | SARKAR WATER SUPPLY AGENCY | 58.87 | 0 | 0 | 0
1575 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Edrakpur PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10010 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 100 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for EDRAKPUR Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | 1021/MURD | 05/05/2025 | 60 | SANJAY BISWAS | 40.44 | 0 | 0 | 0
1576 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10012 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (GANGADHARI PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3276/MURD | 05/10/2021 | 60 | RADIANT | 3.51 | 3.51 | 100 | 1
1577 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10012 | Augmentation | Formal work order for Augmentation of laying Rising main & Distribution System of GANGADHARI Water Supply Scheme under Berhampore Sub-Division, Murshidabad Division, P.H.Engg Dte. In the District Murshidabad. | 1303/MURD | 20/05/2022 | 120 | PRADIP KUMAR DAS | 300.61 | 299.96 | 100 | 0
1578 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10012 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gangadhari Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3069/MURD | 17/11/2022 | 30 | A.M. ENTERPRISE | 10.6 | 9.39 | 100 | 100
1579 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10012 | Augmentation | Material Requisition To Resource Division | MURD/514 | 16/02/2024 | 0 | Resource Division | 21.35 | 0 | 0 | 0
1580 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10012 | Augmentation | Construction of 200 Cum OHR, Boundary Wall, Pump House for Augmentation of GANGADHARI PWSS in NAWDA Block, Berhampore Sub-Division under Murshidabad Division ,PHE.Dte. | 825/MURD | 15/03/2024 | 566 | SOM CONSTRUCTION AGENCY | 93.75 | 0 | 0 | 25
1581 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10012 | Augmentation | Construction Pump House with chlorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) and 55 mtr. Boundary wall at 3rd Tubewell site of Gangadhari & Edrakpur Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | 2152/MURD | 29/07/2024 | 480 | PARUL ELECTRICAL INSTALLER | 16.6 | 0 | 0 | 80
1582 | MURSHIDABAD | Berhampore Mechanical | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10012 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Gangadhari ground water based water supply scheme under Block- Nowda, Dist. Murshidabad under MEDB, PHE Dte. | 400/MEDB | 12/02/2025 | 89 | M/S. T.K. BASU RAY | 12.18 | 0 | 0 | 70
1583 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10012 | Augmentation | Retrofitting Providing Functional Household Tap Connections (FHTC) of 1786 nos in connection with (Jal Jeevan Mission ) and under command area of village of Gangadhari ( Village Code -315534) under Gangadhari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block under Murshidabad Division P.H.E Dte. | 1232/MURD | 11/05/2022 | 60 | PRADIP KUMAR DAS | 78.92 | 19.76 | 100 | 0
1584 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Gangadhari PWSS To Accommodate FHTC In Nawda Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10012 | Augmentation | Balance work for Laying of Distribution Pipeline, Repair and Renovation of OHR of 200 cum Capacity and Providing Functional Household Connection of 590 nos household of Gangadhari (village code-314589) of Berhampore Sub-Division under Murshidabad Division,P.H.E Dte. | 2969/MURD | 20/09/2023 | 559 | DAS TRADING CO. | 80.23 | 71.47 | 72.26 | 100
1585 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10634 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-IV Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3058/MURD | 17/11/2022 | 45 | NADIA TUBEWELLS | 23.55 | 17.06 | 100 | 1
1586 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10634 | Augmentation | Material Requisition To Resource Division | 2780/J/MURD | 01/10/2022 | 0 | Resource Division | 14.2 | 0 | 0 | 0
1587 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10634 | Augmentation | Material Requisition To Resource Division | 2507/E/MURD | 31/08/2022 | 0 | Resource Division | 12.41 | 0 | 0 | 0
1588 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10634 | Augmentation | Material Requisition To Resource Division | 1180/MURD/12 | 29/04/2023 | 0 | Resource Division | 11.14 | 0 | 0 | 0
1589 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10634 | Augmentation | New connection charge for Jalangi W/S Scheme (Part-B) Zone-IV, P/H No.-I. |  | 04/08/2023 | 0 | WBSEDCL | 0.87 | 0 | 0 | 0
1590 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10634 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of JALANGI , Zone- IV ground water based water supply scheme under Block- Jalangi, Dist. Murshidabad under MEDB, PHE Dte. | 3772/MEDB | 03/11/2023 | 605 | QUAZI NOZRUL ISLAM | 23.34 | 0 | 0 | 60
1591 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10634 | Augmentation | Material Requisition To Resource Division | MURD/2482 | 04/09/2024 | 0 | Resource Division | 14.2 | 0 | 0 | 0
1592 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10634 | Augmentation | new service connection at Arji Muradpur ID304173525 | 246/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 4.3 | 0 | 0 | 0
1593 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10634 | Augmentation | NEW SERVICE CONNECTION AT ZONE 4 MOUZA MURADPUR JL NO 30 PLOT NO LR 748,749 MURSHIDABAD ID 304240386 | 296/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 12.21 | 0 | 0 | 0
1594 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- IV to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10634 | Augmentation | Formal work order for Augmentation of Jalangi Zone-IV Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | 1807/MURD | 11/07/2022 | 993 | H.I.ENTERPRISE | 351.37 | 220.51 | 89.26 | 95
1595 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHAGIRATHPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10626 | Augmentation | Sinking of replacement tube well of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhagirathpur Water Supply Scheme of TW-I, P.H-1 under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3591/MURD | 17/11/2021 | 15 | A ONE ENTERPRISE | 8.39 | 7.2 | 100 | 1
1596 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHAGIRATHPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10626 | Augmentation | Material Requisition To Resource Division | 1236/MURD | 11/05/2022 | 0 | Resource Division | 46.42 | 0 | 0 | 0
1597 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHAGIRATHPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10626 | Augmentation | Material Requisition To Resource Division | 2507/A/MURD | 31/08/2022 | 0 | Resource Division | 11.3 | 0 | 0 | 0
1598 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHAGIRATHPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10626 | Augmentation | Material Requisition To Resource Division | 2508/A/MURD | 31/08/2022 | 0 | Resource Division | 1.45 | 0 | 0 | 0
1599 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHAGIRATHPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10626 | Augmentation | Material Requisition To Resource Division | 1180/MURD/13 | 29/04/2023 | 0 | Resource Division | 16.75 | 0 | 0 | 0
1600 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHAGIRATHPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10626 | Augmentation | Augmentation of BHANDARA (ZONE - II A) & Augmentation of BHAGIRATHPUR PWSS under Jal Jeevan Mission of Bhagawangola-I & Domkal Block, Murshidabad District under Murshidabad Division, PHE. Dte. | 3372/MURD | 31/10/2023 | 270 | MAMATA USHA ENTERPRISE | 902.27 | 0 | 0 | 0
1601 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHAGIRATHPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10626 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 1.95 | 100 | 80
1602 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BHAGIRATHPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10626 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No._I under Bhagirathpur ground water based water supply scheme under Block_ Domkal Dist. Murshidabad under MEDB, PHE Dte. | 770/MEDB | 20/02/2024 | 90 | ANUPAMA ENGINEERING WORKS | 11.06 | 0 | 0 | 0
1603 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHAGIRATHPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10626 | Augmentation | Formal Work Order for Augmentation of BHAGIRATHPUR Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE Dte. | 1722/MURD | 04/07/2022 | 365 | M/S BHUBAN DAS | 331.21 | 300.86 | 100 | 65
1604 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for BHAGIRATHPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10626 | Augmentation | Material Requisition To Resource Division | MURD/2481/12 | 04/09/2024 | 0 | Resource Division | 19.48 | 0 | 0 | 0
1605 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for BHAGIRATHPUR to Accommodate FHTC Block Domkal District - Murshidabad. , SM/10626 | Augmentation | SHIFTING OF 11KV HT OH LINE AT BHAGIRATHPUR | 167/WBSEDCL-JJM | 29/07/2024 | 0 | WBSEDCL | 3.79 | 0 | 0 | 0
1606 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Pukhuria (Code-314547) In The Command Area Of Benipur Ground Water Supply Scheme (Part-B) Under Bhagwangola-II Blo , SM/07790 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Pukhuria (Village code 314547) under Benipur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | 192/BD-I | 04/02/2021 | 30 | M/S S.S ENTERPRISE | 71.4 | 44.98 | 63 | 1
1607 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Pukhuria (Code-314547) In The Command Area Of Benipur Ground Water Supply Scheme (Part-B) Under Bhagwangola-II Blo , SM/07790 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at The Village Of Pukhuria (Code-314547) In The Command Area Of Benipur Ground Water Supply Scheme (Part-B) Under Bhagwangola-II Block " in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1437/BD-I | 04/09/2024 | 30 | M/S ROY & BOSE ENTERPRISE | 17.87 | 0 | 0 | 0
1608 | MURSHIDABAD | Berhampore Division I | MOKTARPUR PIPED WATER SUPPLY SCHEME , SM/11620 | New | Material Requisition To Resource Division | 201/BD-1/3 | 10/02/2024 | 0 | Resource Division | 2.51 | 0 | 0 | 0
1609 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANKURIA JAFRABAD ZONE- I BLOCK SAMSERGANJ DIST - MURSHIDABAD. , SM/11967 | Augmentation | Boundary wall at 2-nd Tube Well Site of Kankuria Jafrabad Water supply Scheme under Jangipur Sub-Division, P.H.Engg. Dte. in the District of Murshidabad.Length of Boundary Wall- 96 Mtr. | 663/MURD | 19/02/2021 | 45 | HARUN ALL RASHID & BROTHERS | 4.49 | 4.62 | 100 | 0
1610 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANKURIA JAFRABAD ZONE- I BLOCK SAMSERGANJ DIST - MURSHIDABAD. , SM/11967 | Augmentation | Supply of UPVC pipe and RDS filter for the work of Sinking of (300 mm x 200 mm ) dia Big Dia tube well at Village Kankuria(Village Code:-313873) in connection with FHTC work of Kankuria Jafrabad Water SupplyScheme(Scheme Id:0006303234) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | 240/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.6 | 2.62 | 100 | 1
1611 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANKURIA JAFRABAD ZONE- I BLOCK SAMSERGANJ DIST - MURSHIDABAD. , SM/11967 | Augmentation | Supply of (300 mm x 200 mm ) dia Big Dia tube well 75 mtr. Deep by direct rotary rig method using UPVC pipe and RDS filter at Village Kankuria(Village Code:-313873) in connection with FHTC work of Kankuria Jafrabad Water Supply Scheme(SchemeId:0006303234) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | 239/JSD | 05/05/2022 | 30 | MOTI RAHAMAN | 4.42 | 4.01 | 100 | 1
1612 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANKURIA JAFRABAD ZONE- I BLOCK SAMSERGANJ DIST - MURSHIDABAD. , SM/11967 | Augmentation | Material Requisition To Resource Division | 1295/MURD/01 | 11/05/2023 | 0 | Resource Division | 11.5 | 0 | 0 | 0
1613 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANKURIA JAFRABAD ZONE- I BLOCK SAMSERGANJ DIST - MURSHIDABAD. , SM/11967 | Augmentation | Laying of pipeline at Babupur village adjacent to OHR of Kankuria Jafrabad Water Supply Scheme under Murshidabad Division, PHE Dte. | 1974/MURD | 20/07/2023 | 30 | JOY BISHNU ENGINEERING CO. | 2.07 | 0 | 0 | 100
1614 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANKURIA JAFRABAD ZONE- I BLOCK SAMSERGANJ DIST - MURSHIDABAD. , SM/11967 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JADABPUR NIMTALA and KANKURIA JAFRABAD ZONE- I Water Supply Scheme as required at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | 3813/MURD | 12/12/2023 | 21 | HARUN ALL RASHID & BROTHERS | 11.77 | 2.27 | 20.94 | 100
1615 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANKURIA JAFRABAD ZONE- I BLOCK SAMSERGANJ DIST - MURSHIDABAD. , SM/11967 | Augmentation | Material Requisition To Resource Division | MURD/2481/11 | 04/09/2024 | 0 | Resource Division | 57.32 | 0 | 0 | 0
1616 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANKURIA JAFRABAD ZONE- I BLOCK SAMSERGANJ DIST - MURSHIDABAD. , SM/11967 | Augmentation | Renovation of Filter Media of Existing IEP of (Capacity 45 Cum/hr.) at Kankuria Jafrabad Water Supply Scheme under Murshidabad Division , PHE engineering Dte. | 230/MURD | 27/01/2025 | 30 | M/S.DAS ENTERPRISE | 16.84 | 0 | 0 | 0
1617 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11569 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (SURANGAPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3274/MURD | 05/10/2021 | 60 | RADIANT | 15.07 | 5.02 | 100 | 1
1618 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11569 | Augmentation | Material Requisition To Resource Division | 1278/MURD/9 | 10/05/2023 | 0 | Resource Division | 68.77 | 0 | 0 | 0
1619 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11569 | Augmentation | Sinking of 01 (Three) Nos of 300mm x 200 mm dia tubewell i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen(RDS) filter at SURANGAPUR PWSS (ZONE- II ) PART-B Water Supply Scheme at Head Work Site at Nawda Block under Murshidabad Division, P.H. Engineering Dte | 1754/MURD | 06/07/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 11.79 | 10.78 | 100 | 100
1620 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11569 | Augmentation | Material Requisition To Resource Division | 112/MURD/05 | 11/01/2024 | 0 | Resource Division | 38.22 | 0 | 0 | 0
1621 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11569 | Augmentation | Material Requisition To Resource Division | 305/MURD/01 | 29/01/2024 | 0 | Resource Division | 65.38 | 0 | 0 | 0
1622 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- II ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11569 | Augmentation | Formal work order for Augmentation of SURANGAPUR Zone-II / Part-B Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 2493/MURD | 30/08/2022 | 365 | SUJIT KUMAR SAHA | 203.27 | 150.84 | 74.21 | 85
1623 | MURSHIDABAD | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS , SM/13732 | New | Material Requisition To Resource Division | 1936/MURD/3 | 18/07/2023 | 0 | Resource Division | 25.21 | 0 | 0 | 0
1624 | MURSHIDABAD | Berhampore Mechanical | BUNDI AND ADJOINING MOUJAS PWSS , SM/13732 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Bundi ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | 1886/MEDB | 16/06/2023 | 92 | M/S SAJAHAN CHOWDHURY | 22.54 | 14.31 | 63.52 | 5
1625 | MURSHIDABAD | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS , SM/13732 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 0 | 80
1626 | MURSHIDABAD | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS , SM/13732 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BUNDAI PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3403/MURD | 22/12/2022 | 45 | M/S SUBHAJIT BISWAS | 16.8 | 15.2 | 100 | 75
1627 | MURSHIDABAD | Berhampore Mechanical | BUNDI AND ADJOINING MOUJAS PWSS , SM/13732 | New | SHIFTING OF 11KV AT BUNDAI | 449/WBSEDCL-JJM | 15/03/2024 | 0 | WBSEDCL | 0.98 | 0 | 0 | 0
1628 | MURSHIDABAD | Berhampore Mechanical | BUNDI AND ADJOINING MOUJAS PWSS , SM/13732 | New | BUNDI PH 1 ID 304259360 | 365/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 3.48 | 0 | 0 | 0
1629 | MURSHIDABAD | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS , SM/13732 | New | Formal Work Order for construction of 250 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of BUNDAI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362420S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,40,40,803.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,49,29,128.00] | 413/MURD | 15/02/2023 | 1263 | M/S TRADE ASSOCIATE | 289.47 | 39.33 | 13.59 | 20
1630 | MURSHIDABAD | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS , SM/13732 | New | Formal work order for the work of Laying Distribution System (PART-A) for Augmentation of BUNDAI PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362420S000) | 130./MURD | 16/01/2023 | 897 | PRASANTA SANA | 108.95 | 65.02 | 59.67 | 60
1631 | MURSHIDABAD | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS , SM/13732 | New | Balance work of road restoration damaged during laying of pipeline and laying of distribution pipe line of Bundai Piped Water Supply Scheme, Kandi Block, Kandi Sub-Division under Murshidabad Division, P.H.E dte. | 827/MURD | 15/03/2024 | 15 | PRASANTA SANA | 20.72 | 6.51 | 31.4 | 50
1632 | MURSHIDABAD | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS , SM/13732 | New | Balance work for repair of road, construction of approach road & land development of Hizole-I & II & Bundai Water Supply Scheme of Kandi Block under Murshidabad Division, P.H.Engineering Dte. | 835/MURD | 11/04/2025 | 234 | M/S JATIN | 69.3 | 0 | 0 | 5
1633 | MURSHIDABAD | Murshidabad Division | BUNDI AND ADJOINING MOUJAS PWSS , SM/13732 | New | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 3.68 | 100 | 100
1634 | MURSHIDABAD | Murshidabad Division | SERPUR AND ADJOINING MOUJAS PWSS , SM/13930 | New | Material Requisition To Resource Division | 1067/MURD/3 | 18/04/2023 | 0 | Resource Division | 25.58 | 0 | 0 | 0
1635 | MURSHIDABAD | Murshidabad Division | SERPUR AND ADJOINING MOUJAS PWSS , SM/13930 | New | Formal work order for the work of SERPUR & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | 78/MURD | 10/01/2023 | 1118 | RADIANT | 557.06 | 48.03 | 8.62 | 35
1636 | MURSHIDABAD | Berhampore Mechanical | SERPUR AND ADJOINING MOUJAS PWSS , SM/13930 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SERPUR ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | 2015/MEDB | 19/06/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 23.67 | 19.11 | 80.77 | 50
1637 | MURSHIDABAD | Murshidabad Division | SERPUR AND ADJOINING MOUJAS PWSS , SM/13930 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 0 | 80
1638 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balia Hasennagar, Arazi Nista (31447 & 314526) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of , SM/07280 | Retrofitting | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0 | 0
1639 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balia Hasennagar, Arazi Nista (31447 & 314526) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of , SM/07280 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BURWAN- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- GOURINAGAR , CODE-315951 , 631/2020-21/EE | 504/W | 22/03/2021 | 0 | KAMIRUL SK AND CO. | 9.08 | 0 | 0 | 0
1640 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balia Hasennagar, Arazi Nista (31447 & 314526) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of , SM/07280 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -PANCHTHUPI- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- JANARDHANPUR , CODE-315981 , 632 /2020-21/EE | 504/W | 22/03/2021 | 0 | KAMIRUL SK AND CO. | 21.08 | 0 | 0 | 0
1641 | MURSHIDABAD | Berhampore Mechanical | PUNRAPARA AND ADJOINING MOUJAS PWSS , SM/13932 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II,III ,IV & V under PUNRAPARA ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | 1932/MEDB | 16/06/2023 | 92 | MAHADEB ENTERPRISE | 55.86 | 0 | 0 | 0
1642 | MURSHIDABAD | Murshidabad Division | PUNRAPARA AND ADJOINING MOUJAS PWSS , SM/13932 | New | Material Requisition To Resource Division | 1210/MURD/33 | 02/05/2023 | 0 | Resource Division | 16.9 | 0 | 0 | 0
1643 | MURSHIDABAD | Murshidabad Division | PUNRAPARA AND ADJOINING MOUJAS PWSS , SM/13932 | New | Laying Distribution System (PART-B), FHTC for PUNRAPARA Water Supply Scheme in Khargram Block , under Murshidabad Division ,PHE.Dte. | 3656/MURD | 29/11/2023 | 120 | AJAY MONDAL | 270.3 | 81.52 | 30.16 | 30
1644 | MURSHIDABAD | Berhampore Mechanical | PUNRAPARA AND ADJOINING MOUJAS PWSS , SM/13932 | New | NEW CONNECTION AT PURAOARA PH 1 ID 304342318 | 108/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 6.06 | 0 | 0 | 0
1645 | MURSHIDABAD | Murshidabad Division | PUNRAPARA AND ADJOINING MOUJAS PWSS , SM/13932 | New | Formal Work Order for Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, Boundwary Wall for PUNRAPARA PWSS in Khargram Block , under Murshidabad Division ,PHE.Dte. | 756/MURD | 16/03/2023 | 747 | JIT CONSTRUCTION | 194.6 | 85.37 | 43.87 | 10
1646 | MURSHIDABAD | Murshidabad Division | PUNRAPARA AND ADJOINING MOUJAS PWSS , SM/13932 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Punrapara & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte | 1099/MURD | 24/04/2023 | 30 | NADIA TUBEWELLS | 21.35 | 18.97 | 100 | 100
1647 | MURSHIDABAD | Murshidabad Division | PUNRAPARA AND ADJOINING MOUJAS PWSS , SM/13932 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PUNRAPARA, Augmentation of Bahara & Pacchipara Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 2587/MURD | 21/08/2023 | 438 | INDRAJIT MAZUMDAR | 18.43 | 0 | 0 | 60
1648 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . , SM/14051 | Augmentation | Material Requisition To Resource Division | 194/BD-I/9 | 09/02/2024 | 0 | Resource Division | 14.79 | 0 | 0 | 0
1649 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . , SM/14051 | Augmentation | Augmentation of Sarkarpara Piped water supply scheme to accommodate construction of boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Jalangi Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1557/BD-I | 20/02/2023 | 1212 | AZAD ENTERPRISE | 63.96 | 53.83 | 84.16 | 75
1650 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . , SM/14051 | Augmentation | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SARKARPARA Water Supply Scheme within Jalangi Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 430/BD-I | 19/03/2025 | 15 | TAPESH MONDAL | 11.56 | 0 | 0 | 100
1651 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . , SM/14051 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SARKARPARA Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1370/BD-I | 21/12/2022 | 10 | M/S SOBHA & CO | 2.46 | 2.39 | 100 | 100
1652 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . , SM/14051 | Augmentation | Repair And Renovation Works Of OHR (45 Cum) of Ground Water Based Supply Scheme for Sarkarpara of Jalangi block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | 1092/BD-I | 24/11/2023 | 479 | PARUL ELECTRICAL INSTALLER | 5.41 | 0 | 0 | 100
1653 | MURSHIDABAD | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14432 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under RAJARAMPUR ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | 3781/MEDB | 03/11/2023 | 92 | M/S S. R. ENTERPRISE | 23.47 | 0 | 0 | 0
1654 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14432 | Augmentation | RAJARAMPUR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 457/BD-I | 15/03/2024 | 60 | MAA DURGA ENTERPRISE | 22.87 | 0 | 0 | 0
1655 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14432 | Augmentation | Material Requisition To Resource Division | 201/BD-1/21 | 10/02/2024 | 0 | Resource Division | 50.95 | 0 | 0 | 0
1656 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14432 | Augmentation | Material Requisition To Resource Division | 1510/BD-I/4 | 12/09/2024 | 0 | Resource Division | 8.03 | 0 | 0 | 0
1657 | MURSHIDABAD | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14432 | Augmentation | SHIFTING OF LT OH LINE AT RAJARAMPUR PH-I |  | 27/06/2024 | 0 | WBSEDCL | 0.89 | 0 | 0 | 0
1658 | MURSHIDABAD | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14432 | Augmentation | SHIFTING OF LT OH LINE AT RAJARAMPUR PH-I | 145/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 0.89 | 0 | 0 | 0
1659 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14432 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Rajarampur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | 1678/BD-I | 14/03/2023 | 30 | SOMNATH DEY | 2.35 | 2.31 | 98.44 | 100
1660 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14432 | Augmentation | Augmentation of Rajarampur Piped water supply scheme to accommodate construction of OHR ,Pump House and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1618/BD-I | 02/03/2023 | 310 | DHIRENDRA NATH MONDAL | 366.26 | 0 | 0 | 0
1661 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14432 | Augmentation | Repair And Renovation Works Of OHR (350 Cum) of Ground Water Supply Scheme for Rajarampur of Lalgola block under Berhampore Division-I PHEDte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 994/BD-I | 30/10/2023 | 639 | DAS CONSTRUCTION 13/1/2 UKILABAD ROAD, BERHAMPORE | 8.12 | 0 | 0 | 0
1662 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14432 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAJARAMPUR Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1684/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.66 | 2.69 | 100 | 1
1663 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14432 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Rajarampur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte ( For 2 nos Tubewell) | 139/BD-I | 12/05/2023 | 30 | HARUN ALL RASHID & BROTHERS | 17.82 | 15.62 | 100 | 100
1664 | MURSHIDABAD | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14434 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of MAKIMNAGAR ground water based water supply scheme under Block- LALGOLA, Dist. Murshidabad under MEDB, PHE Dte. | 3780/MEDB | 03/11/2023 | 92 | JOY BISHNU ENGINEERING CO. | 11.98 | 10.05 | 83.88 | 10
1665 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14434 | Augmentation | Repair And Renovation Works Of OHR (180 Cum) of Ground Water Based Supply Scheme for Makimnagar of Lalgola block under Berhampore Division-I PHEDte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 992/BD-I | 30/10/2023 | 30 | MATIUR RAHAMAN | 8.07 | 3.67 | 45.44 | 65
1666 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14434 | Augmentation | Material Requisition To Resource Division | 201/BD-1/11 | 10/02/2024 | 0 | Resource Division | 36.15 | 0 | 0 | 0
1667 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14434 | Augmentation | Material Requisition To Resource Division | 1510/BD-I/2 | 12/09/2024 | 0 | Resource Division | 6.78 | 0 | 0 | 0
1668 | MURSHIDABAD | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14434 | Augmentation | MAKIMNAGAR PH-1 | 403/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 12.14 | 0 | 0 | 0
1669 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14434 | Augmentation | Augmentation of Makimnagar Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP) and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | 682/BD-I | 10/08/2023 | 728 | M/S BIMALENDU BOSE | 427.29 | 0 | 0 | 30
1670 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14434 | Augmentation | MAKIMNAGAR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 455/BD-I | 15/03/2024 | 60 | M/S UNIVERSAL TRADING | 22.87 | 18.79 | 82.16 | 50
1671 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14434 | Augmentation | Construction of Pump House Cum Chlorine Room at Head Work site of MOKIMNAGAR PWSS (H/W Site & 2nd Site) under Jal Jevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | 595/BD-I | 22/04/2025 | 60 | M/S MEGHNA CONSTRUCTION | 12.78 | 0 | 0 | 0
1672 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14434 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MOKIMNAGAR Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 318/BD-I | 24/02/2025 | 15 | MAMATA USHA ENTERPRISE | 9.01 | 0 | 0 | 0
1673 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14434 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MAKIMNAGAR Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1686/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.59 | 2.62 | 100 | 1
1674 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAKIMNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14434 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Makimnagar Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte | 127/BD-I | 12/05/2023 | 30 | HARUN ALL RASHID & BROTHERS | 8.91 | 7.76 | 100 | 100
1675 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14828 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 2.56 | 100 | 100
1676 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14828 | Augmentation | Material Requisition To Resource Division | 1219/MURD/15 | 03/05/2023 | 0 | Resource Division | 26 | 0 | 0 | 0
1677 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14828 | Augmentation | Augmentation of MURADPUR JALANGI ZONE-I PWSS Laing Distribution System, Rising Main Connection Repairing P.H, B.W, Construction of P.H of JALANGI Block , under Murshidabad Division PHE. Dte. | 3114/MURD | 05/10/2023 | 543 | ARINDAM MAJUMDAR | 187.44 | 0 | 0 | 60
1678 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14828 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. under MEDB, PHE Dte. | 325/MEDB | 10/02/2025 | 89 | JOY BISHNU ENGINEERING CO. | 11.35 | 0 | 0 | 0
1679 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-I IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14828 | Augmentation | Refilling of sand layers, Activated Alumina & existing gravel after washing along with allied works of AIRP at Saikhpara Area (Capacity 100 Cum/hr.) & Muradpur Jalangi Z-I (Capacity 54.00 Cum/hr.) Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. | 820/MURD | 15/03/2024 | 244 | M/S. S. DAS AND ENTERPRISE | 70.68 | 34.18 | 50 | 40
1680 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-II IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14829 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 1.87 | 100 | 100
1681 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-II IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14829 | Augmentation | Material Requisition To Resource Division | 1219/MURD/27 | 03/05/2023 | 0 | Resource Division | 12.69 | 0 | 0 | 0
1682 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-II IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14829 | Augmentation | Augmentation of MURADPUR JALANGI ZONE-II PWSS Laing Distribution System, Rising Main Connection Repairing P.H, B.W, Construction of P.H of JALANGI Block , under Murshidabad Division PHE.Dte. | 1901/MURD | 17/07/2023 | 180 | AZAD ENTERPRISE | 75.52 | 12.41 | 16.44 | 30
1683 | MURSHIDABAD | Murshidabad Division | KHESAR AND IT'S ADJOINING MOUJAS PWSS , SM/13937 | New | Material Requisition To Resource Division | 1067/MURD | 18/04/2023 | 0 | Resource Division | 15.98 | 0 | 0 | 0
1684 | MURSHIDABAD | Berhampore Mechanical | KHESAR AND IT'S ADJOINING MOUJAS PWSS , SM/13937 | New | Electric Service Connection at KESHAR PH I, Application NO.3004403775, ID 304120001 | 192/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 5.11 | 0 | 0 | 0
1685 | MURSHIDABAD | Berhampore Mechanical | KHESAR AND IT'S ADJOINING MOUJAS PWSS , SM/13937 | New | Electric Service Connection at KHESAR PWSS PH II, Application NO.3004403805, ID 304120021 | 193/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 4.51 | 0 | 0 | 0
1686 | MURSHIDABAD | Murshidabad Division | KHESAR AND IT'S ADJOINING MOUJAS PWSS , SM/13937 | New | Formal work order for the work of KHESAR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | 38/MURD | 04/01/2023 | 818 | PRADIP KUMAR DAS | 720.99 | 362.73 | 50.31 | 35
1687 | MURSHIDABAD | Murshidabad Division | KHESAR AND IT'S ADJOINING MOUJAS PWSS , SM/13937 | New | Allied work for KHESAR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | 1977/MURD | 08/07/2024 | 60 | DAS TRADING CO. | 70.58 | 0 | 0 | 0
1688 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14046 | Augmentation | Material Requisition To Resource Division | 194/BD-I/2 | 09/02/2024 | 0 | Resource Division | 30.59 | 0 | 0 | 0
1689 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14046 | Augmentation | NEW CONNECTION AT RAMNAGAR DOEMKANUN Z2 PH 2 ID 304268982 |  | 25/11/2024 | 0 | WBSEDCL | 10.13 | 0 | 0 | 0
1690 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14046 | Augmentation | Augmentation of Ramnagar Doemkanun ZoneII Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE Dte. | 1660/BD-I | 13/03/2023 | 180 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 186.74 | 82.9 | 44.39 | 30
1691 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14046 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNAGAR DOEMKANON ZONE-II Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1380/BD-I | 22/12/2022 | 10 | RADIANT | 2.6 | 2.6 | 100 | 100
1692 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14046 | Augmentation | Improvement of OHR (350 Cum) of Ground Water Based Supply Scheme for Augmentation of Ramnagar Domkanun Zone-II of Raninagar-I block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | 892/BD-I | 06/06/2024 | 236 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 8.61 | 0 | 0 | 100
1693 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14046 | Augmentation | Construction of Boundary Wall with Main Entrance gate and barbed wire facing and service road for approach at Augmentation of Ramnagar Doemkanun Zone-II PWSS of Raninagar-II Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | 1067/BD-I | 03/07/2024 | 241 | MUNNA AGROTECH ENTERPRISE | 20.72 | 0 | 0 | 100
1694 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE , SM/14629 | Augmentation | Material Requisition To Resource Division | 1210/MURD/27 | 02/05/2023 | 0 | Resource Division | 26.32 | 0 | 0 | 0
1695 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE , SM/14629 | Augmentation | Providing FHTC to 754 nos. household, Rising Main, Repairing Vertical extension of Boundary wall and repairing of Pump House and overhauling of R.C.C. elevated reservoir 450 Cum capacity of staging height 20 mtr. (Shaft wall) for Augmentation work of Mahesail (Zone-II) PWSS in Suti-II Block under Murshidabad Division, PHE.Dte. | 564/MURD | 28/02/2023 | 180 | BISWAS ENTERPRISE. | 63.88 | 58.43 | 91.46 | 95
1696 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE , SM/14629 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,ZONE-II under MAHESAIL ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | 4315/MEDB | 29/12/2023 | 91 | BHAGIRATHI JUTE AND HOLDINGS PVT LTD | 22.93 | 0 | 0 | 0
1697 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE , SM/14629 | Augmentation | Formal work order for Laying of Distribution System for Augmentation work of Mahesail (Zone-II) PWSS in Suti-II Block under Murshidabad Division,PHE.Dte. | 806/MURD | 22/03/2023 | 180 | M/S. BIMALENDU BOSE | 190.73 | 186.94 | 100 | 100
1698 | MURSHIDABAD | Murshidabad Division | MIRHATI AND ADJOINING MOUJAS PWSS , SM/14869 | New | Material Requisition To Resource Division | 1129/MURD/7 | 25/04/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
1699 | MURSHIDABAD | Berhampore Mechanical | MIRHATI AND ADJOINING MOUJAS PWSS , SM/14869 | New | Electric Service Connection at MIRHATI PWSS PH I, Application NO.3004467235, ID 304171280 | 190/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 6.97 | 0 | 0 | 0
1700 | MURSHIDABAD | Murshidabad Division | MIRHATI AND ADJOINING MOUJAS PWSS , SM/14869 | New | Material Requisition To Resource Division | 79/MURD/07 | 09/01/2024 | 0 | Resource Division | 3.63 | 0 | 0 | 0
1701 | MURSHIDABAD | Murshidabad Division | MIRHATI AND ADJOINING MOUJAS PWSS , SM/14869 | New | Material Requisition To Resource Division | MURD/439/03 | 08/02/2024 | 0 | Resource Division | 0.13 | 0 | 0 | 0
1702 | MURSHIDABAD | Berhampore Mechanical | MIRHATI AND ADJOINING MOUJAS PWSS , SM/14869 | New | NEW SERVICE CONNECTION AT PH2 MIRHATI ID304239447 | 308/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 4.81 | 0 | 0 | 0
1703 | MURSHIDABAD | Murshidabad Division | MIRHATI AND ADJOINING MOUJAS PWSS , SM/14869 | New | Formal work order for Laying Distribution System of MIRHATI PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Murshidabad Circle ,PHE.Dte. | 789/MURD | 21/03/2023 | 742 | SUBHANKAR ROY | 139.07 | 81.81 | 58.83 | 30
1704 | MURSHIDABAD | Berhampore Mechanical | MIRHATI AND ADJOINING MOUJAS PWSS , SM/14869 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under MIRHATI ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | 3713/MEDB | 03/11/2023 | 790 | B. T. PROJECTS PVT. LTD. | 21.24 | 0 | 0 | 70
1705 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at KHAYRAMARI Part-B Ground water Based PWSS, Block-Jalangi , Dist- Murshidabad under MEDB, PHE Dte. , SM/15293 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at KHAYRAMARI Part-B Ground water Based PWSS, Block-Jalangi , Dist- Murshidabad under MEDB, PHE Dte. | 3744/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.39 | 0 | 0 | 0
1706 | MURSHIDABAD | Murshidabad Division | SITARAMPUR PIPED WATER SUPPLY SCHEME. , SM/15048 | New | Material Requisition To Resource Division | 1230/MURD/20 | 04/05/2023 | 0 | Resource Division | 29.01 | 0 | 0 | 0
1707 | MURSHIDABAD | Murshidabad Division | SITARAMPUR PIPED WATER SUPPLY SCHEME. , SM/15048 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SITARAMPUR Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | 3393/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 16.54 | 100 | 50
1708 | MURSHIDABAD | Berhampore Mechanical | SITARAMPUR PIPED WATER SUPPLY SCHEME. , SM/15048 | New | NEW CONNECTION AT SITARAMPORE PH-II | 61/WBSEDCL-JJM | 06/05/2024 | 0 | WBSEDCL | 4.17 | 0 | 0 | 0
1709 | MURSHIDABAD | Murshidabad Division | SITARAMPUR PIPED WATER SUPPLY SCHEME. , SM/15048 | New | SITARAMPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission, Block- SAMSERGANJ of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | 978/MURD | 10/04/2023 | 1279 | HOQUEDAR ALI | 389.19 | 151.48 | 38.92 | 15
1710 | MURSHIDABAD | Berhampore Mechanical | SITARAMPUR PIPED WATER SUPPLY SCHEME. , SM/15048 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube well in connection to Accommodate FHTC at Pump House No.-I , II & III under SITARAMPUR ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | 3807/MEDB | 03/11/2023 | 790 | JAL PRAVAHIKA PVT LTD | 31.3 | 0 | 0 | 15
1711 | MURSHIDABAD | Murshidabad Division | SITARAMPUR PIPED WATER SUPPLY SCHEME. , SM/15048 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.41 | 100 | 100
1712 | MURSHIDABAD | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/15051 | New | Material Requisition To Resource Division | 1230/MURD/11 | 04/05/2023 | 0 | Resource Division | 22.61 | 0 | 0 | 0
1713 | MURSHIDABAD | Berhampore Mechanical | NAPARA PIPED WATER SUPPLY SCHEME. , SM/15051 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under NAPARA ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | 3808/MEDB | 03/11/2023 | 92 | ORIENTAL ENGINEERING CO. | 20.86 | 12.05 | 57.78 | 10
1714 | MURSHIDABAD | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/15051 | New | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NAPARA Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | 3408/MURD | 02/11/2023 | 21 | TAPAN DAS | 9.28 | 7.95 | 100 | 100
1715 | MURSHIDABAD | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/15051 | New | Material Requisition To Resource Division | 495/MURD/14 | 15/02/2024 | 0 | Resource Division | 5.03 | 0 | 0 | 0
1716 | MURSHIDABAD | Berhampore Mechanical | NAPARA PIPED WATER SUPPLY SCHEME. , SM/15051 | New | NEW CONNECTION AT NAPARA PH-II | 60/WBSEDCL-JJM | 06/05/2024 | 0 | WBSEDCL | 11.52 | 0 | 0 | 0
1717 | MURSHIDABAD | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/15051 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sagarpara Part-A, Kohetpur and Napara Water Supply Scheme under Islampur & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3409/MURD | 22/12/2022 | 45 | R.K. DRILLING SERVICES | 23.56 | 0 | 0 | 0
1718 | MURSHIDABAD | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/15051 | New | Formal work order for the work of NAPARA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Samserganj Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | 376/MURD | 10/02/2023 | 902 | MANDAL CONSTRUCTION AND CO. | 241.91 | 122.24 | 50.53 | 45
1719 | MURSHIDABAD | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/15051 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 4.75 | 100 | 100
1720 | MURSHIDABAD | Murshidabad Division | NAPARA PIPED WATER SUPPLY SCHEME. , SM/15051 | New | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well, 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KADOA Zone -II & NAPARA Water Supply Scheme at Head Work Site under Murshidabad Division, P.H. Engineering Dte | 1754/MURD | 13/06/2024 | 434 | R.K. DRILLING SERVICES | 11.79 | 0 | 0 | 100
1721 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15061 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,ZONE-III under MAHESAIL ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | 3810/MEDB | 03/11/2023 | 92 | M/S JIT ENTERPRISE | 22.25 | 0 | 0 | 0
1722 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15061 | Augmentation | Material Requisition To Resource Division | 1219/MURD/07 | 03/05/2023 | 0 | Resource Division | 16.33 | 0 | 0 | 0
1723 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15061 | Augmentation | MAHESAIL Z-III PH-1 | 336/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 5.57 | 0 | 0 | 0
1724 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15061 | Augmentation | Augmentation Work of Mahesail Zone-III Piped Water Supply Scheme to accommodate with FHTC (1034 Nos), Laying of Rising Main , Laying of Distribution System , construction of 350 CUM OHR, Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE. Dte. | 2466/MURD | 09/08/2023 | 754 | GHOSH ENTERPRISE | 337.02 | 54.19 | 16.08 | 60
1725 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15061 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at TEGHARI ZONE - I, MAHESAIL ZONE-III & SERPUR (CT) Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 2407/MURD | 07/08/2023 | 552 | NADIA TUBEWELLS | 35.34 | 7.7 | 33.55 | 100
1726 | MURSHIDABAD | Murshidabad Division | JHILLI AND ADJOINING MOUJAS PWSS , SM/14505 | New | Material Requisition To Resource Division | 1067/MURD/1 | 18/04/2023 | 0 | Resource Division | 21.94 | 0 | 0 | 0
1727 | MURSHIDABAD | Berhampore Mechanical | JHILLI AND ADJOINING MOUJAS PWSS , SM/14505 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at P.H. No.-I & II under JHILLI ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | 4061/MEDB | 04/12/2023 | 91 | SREE RADHA ELECTRICAL | 24.06 | 17.74 | 73.75 | 50
1728 | MURSHIDABAD | Berhampore Mechanical | JHILLI AND ADJOINING MOUJAS PWSS , SM/14505 | New | NEW SERVICE CONNECTION AT JHILLI PH 2 ID 304171278 | 218/WBSEDCL-JJM | 05/01/2024 | 0 | WBSEDCL | 10.53 | 0 | 0 | 0
1729 | MURSHIDABAD | Berhampore Mechanical | JHILLI AND ADJOINING MOUJAS PWSS , SM/14505 | New | NEW SERVICE CONNECTION AT JHILLI PWSS PH1 ID304171275 | 217/WBSEDCL-JJM | 05/01/2024 | 0 | WBSEDCL | 6.95 | 0 | 0 | 0
1730 | MURSHIDABAD | Murshidabad Division | JHILLI AND ADJOINING MOUJAS PWSS , SM/14505 | New | Formal work order for the work of JHILLI & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | 123/MURD | 16/01/2023 | 867 | M/S RUBIET HOSSAIN | 616.31 | 104.78 | 17 | 10
1731 | MURSHIDABAD | Berhampore Mechanical | MARURA AND ADJOINING MOUJAS PWSS , SM/14235 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under MARURA ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | 3789/MEDB | 03/11/2023 | 92 | A.G. ENTERPRISE | 36.83 | 0 | 0 | 0
1732 | MURSHIDABAD | Murshidabad Division | MARURA AND ADJOINING MOUJAS PWSS , SM/14235 | New | Material Requisition To Resource Division | 1043/MURD/10 | 17/04/2023 | 0 | Resource Division | 76.92 | 0 | 0 | 0
1733 | MURSHIDABAD | Murshidabad Division | MARURA AND ADJOINING MOUJAS PWSS , SM/14235 | New | Formal work order for the work of MARURA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte.( Scheme ID -PH222362239S000) | 93/MURD | 11/01/2023 | 365 | M/S.TAPAS KUMAR CHAKRABORTY | 815.38 | 0 | 0 | 0
1734 | MURSHIDABAD | Murshidabad Division | MARURA AND ADJOINING MOUJAS PWSS , SM/14235 | New | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 3.9 | 100 | 100
1735 | MURSHIDABAD | Berhampore Mechanical | SANTOSHPUR AND ADJOINING MOUJAS PWSS , SM/16248 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Santoshpur ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | 2092/MEDB | 19/06/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 21.11 | 0 | 0 | 0
1736 | MURSHIDABAD | Berhampore Mechanical | SANTOSHPUR AND ADJOINING MOUJAS PWSS , SM/16248 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SANTOSHPUR ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | 1892/MEDB | 16/06/2023 | 92 | S. P. CONSTRUCTION | 22.53 | 0 | 0 | 0
1737 | MURSHIDABAD | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS , SM/16248 | New | SANTOSHPUR PWSS under Jal Jeevan Mission of BHARATPUR - I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | 3179/MURD | 11/10/2023 | 553 | GARAI INFRA PROJECT | 260.08 | 0 | 0 | 45
1738 | MURSHIDABAD | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS , SM/16248 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAIDYNATHPUR , DHANDANGA & SANTOSHPUR Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 2806/MURD | 05/09/2023 | 589 | INDRAJIT MAZUMDAR | 27.64 | 0 | 0 | 100
1739 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Mirzapur Ground water Based PWSS, Block-Raghunathganj-I , Dist- Murshidabad under MEDB, PHE Dte. , SM/15351 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Mirzapur Ground water Based PWSS, Block-Raghunathganj-I , Dist- Murshidabad under MEDB, PHE Dte. | 3749/MEDB | 03/11/2023 | 92 | SREE RADHA ELECTRICAL | 6.39 | 0 | 0 | 0
1740 | MURSHIDABAD | Murshidabad Division | Augmentation of Bharatpur Zone- I A Water Supply Scheme Block -Bharatpur-I, Dist- Murshidabad. , SM/16240 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bharatpur Zone- I A Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur -I Block under Murshidabad Division, P.H. Engineering Dte. | 1770/MURD | 06/07/2023 | 21 | SUJIT KUMAR SAHA | 18.45 | 0 | 0 | 0
1741 | MURSHIDABAD | Murshidabad Division | Augmentation of Bharatpur Zone- I A Water Supply Scheme Block -Bharatpur-I, Dist- Murshidabad. , SM/16240 | Augmentation | Augmentation of BHARATPUR (ZONE - IA) PWSS under Jal Jeevan Mission of Bharatpur Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. | 2078/MURD | 31/07/2023 | 300 | BERHAMPORE CONSTRUCTION SYNDICATE PVT. LTD. | 478.38 | 0 | 0 | 0
1742 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Bharatpur Zone- I A Water Supply Scheme Block -Bharatpur-I, Dist- Murshidabad. , SM/16240 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IA under Bharatpur ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | 3680/MEDB | 03/11/2023 | 92 | MERCURY ENGINEERING CO | 23.01 | 17.65 | 76.72 | 8
1743 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jorgachha, Ganra Baria, Malatipur (314690, 314697 & 314698) of Jorgachha under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of , SM/07676 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village JORGACHA (Village Code 314690) under JORGACHA Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 847 of 20-21 by EE MURD | 391-MSD/21-22 | 22/03/2022 | 0 | M/S. GHOSH ENTERPRISE | 28.9 | 0 | 0 | 0
1744 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jorgachha, Ganra Baria, Malatipur (314690, 314697 & 314698) of Jorgachha under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of , SM/07676 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MALATIPUR (Village Code 314698) under JORGACHA Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 846 of 20-21 by EE MURD | 106-MSD/22-23 | 07/05/2022 | 0 | M/S. GHOSH ENTERPRISE | 23.7 | 0 | 0 | 0
1745 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jorgachha, Ganra Baria, Malatipur (314690, 314697 & 314698) of Jorgachha under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of , SM/07676 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevanMission andJalSwapna under command area of village Malatipur (Village code 314698) under Jorgacha Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723176 in the District of Murshidabad. | 80/MURD | 08/01/2021 | 60 | M/S. GHOSH ENTERPRISE | 26.36 | 0 | 0 | 1
1746 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jorgachha, Ganra Baria, Malatipur (314690, 314697 & 314698) of Jorgachha under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of , SM/07676 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevanMission andJalSwapna under command area of village Joragacha (Village code 314690) under Jorgacha Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723176 in the District of Murshidabad. | 81/MURD | 08/01/2021 | 60 | M/S. GHOSH ENTERPRISE | 30.67 | 0 | 0 | 1
1747 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-III, Block- Nawda, District- Murshidabad. , SM/16436 | New | Mini Piped Water Supply Scheme for Sibnagar Zone-III under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 156/BD-I | 15/05/2023 | 90 | NATIONAL ENTERPRISES | 30.54 | 0 | 0 | 0
1748 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-III, Block- Nawda, District- Murshidabad. , SM/16436 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Shibnagar Zone-III village, Block:- Nawda under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3078/MEDB | 02/08/2023 | 92 | M/S SAJAHAN CHOWDHURY | 6.27 | 0 | 0 | 0
1749 | MURSHIDABAD | Murshidabad Division | SUNUTI AND ADJIONING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16549 | New | Material Requisition To Resource Division | 1075/MURD/1 | 19/04/2023 | 0 | Resource Division | 19.17 | 0 | 0 | 0
1750 | MURSHIDABAD | Berhampore Mechanical | SUNUTI AND ADJIONING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16549 | New | Sunuti PH-1 Application No- 3004528432 | 265/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.59 | 0 | 0 | 0
1751 | MURSHIDABAD | Berhampore Mechanical | SUNUTI AND ADJIONING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16549 | New | NEW CONNECTION AT SUNUTI PH-II | 103/WBSEDCL-JJM | 06/06/2024 | 0 | WBSEDCL | 4.22 | 0 | 0 | 0
1752 | MURSHIDABAD | Berhampore Mechanical | SUNUTI AND ADJIONING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16549 | New | NEW CONNECTION AT SUNUTI PH-II |  | 28/05/2024 | 0 | WBSEDCL | 4.22 | 0 | 0 | 0
1753 | MURSHIDABAD | Berhampore Mechanical | SUNUTI AND ADJIONING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16549 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SUNUTI ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | 1908/MEDB | 16/06/2023 | 822 | M/S S. R. ENTERPRISE | 23.39 | 0 | 0 | 10
1754 | MURSHIDABAD | Murshidabad Division | Augmentation of Aurangabad Zone-I Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. , SM/16456 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.68 | 100 | 100
1755 | MURSHIDABAD | Murshidabad Division | Augmentation of Aurangabad Zone-I Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. , SM/16456 | Augmentation | Laying Distribution System, Rising Main Connection, FHTC connections, Construction of 2 Nos Pump House Room, 100 Mtr Boundary Wall, for Augmentation of Aurangabad Zone-I PWSS of Suti-II Block within Murshidabad District under Murshidabad Division, PHE Dte. | 1510/MURD | 03/07/2025 | 90 | H.I.ENTERPRISE | 133.86 | 0 | 0 | 0
1756 | MURSHIDABAD | Murshidabad Division | Augmentation of Aurangabad Zone-I Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. , SM/16456 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Jangipur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(83 Nos.) | 2636/MURD | 23/09/2024 | 20 | KUNTAL SAHA | 9.28 | 0 | 0 | 100
1757 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (maximum 100 households) Village-Sona Diar Zone-II, Block-Berhampore, District- Murshidabad. , SM/16047 | New | Mini Piped Water Supply Scheme for Sonar Diar Zone-II under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte | 174/BD-I | 16/05/2023 | 90 | SHIBAM ENTERPRISE | 26.55 | 0 | 0 | 0
1758 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (maximum 100 households) Village-Sona Diar Zone-II, Block-Berhampore, District- Murshidabad. , SM/16047 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Sonadiar Zone-II village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3049/MEDB | 02/08/2023 | 92 | HARA PROSAD DAS | 6.27 | 0 | 0 | 0
1759 | MURSHIDABAD | Berhampore Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - MOHESPUR , BLOCK BELDANGA -I ,DISTRICT - MURSHIDABAD. , SM/16050 | New | Mini Piped Water Supply Scheme for Mohespur under Beldanga -I block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 159/BD-I | 15/05/2023 | 90 | TITLI ENTERPRISE | 27.81 | 0 | 0 | 0
1760 | MURSHIDABAD | Berhampore Mechanical | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - MOHESPUR , BLOCK BELDANGA -I ,DISTRICT - MURSHIDABAD. , SM/16050 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Mohespur village, Block:- Beldanga-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3079/MEDB | 02/08/2023 | 92 | DIPALI CONSTRUCTION | 6.12 | 0 | 0 | 0
1761 | MURSHIDABAD | Murshidabad Division | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . , SM/16217 | New | Material Requisition To Resource Division | 1219/MURD/14 | 03/05/2023 | 0 | Resource Division | 19.83 | 0 | 0 | 0
1762 | MURSHIDABAD | Berhampore Mechanical | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . , SM/16217 | New | NEW CONNECTION AT CHANDNIDAHA PH-I | 142/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 11.52 | 0 | 0 | 0
1763 | MURSHIDABAD | Berhampore Mechanical | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . , SM/16217 | New | NEW CONNECTION AT CHANDNIDAHA PH-II | 141/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 10.1 | 0 | 0 | 0
1764 | MURSHIDABAD | Murshidabad Division | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . , SM/16217 | New | CHANDNI DAHA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main ,Construction of OHR of 300 cum capacity, Construction Pump House cum Chlorine Room (5.90m x 4.1m) & Pump House (4.10m x 3.5m) with sanitary and Water Supply Arrangement) & Construction of 190 m Boundary wall under Jal Jeevan Mission of Samserganj Block, Murshidabad District under Murshidabad Division, PHE.Dte. | 2968/MURD | 20/09/2023 | 752 | M/S GOLAM KIBRIA | 431.64 | 0 | 0 | 12
1765 | MURSHIDABAD | Murshidabad Division | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . , SM/16217 | New | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 660/MURD | 19/03/2025 | 90 | JOY GURU ENTERPRISE | 82.5 | 0 | 0 | 0
1766 | MURSHIDABAD | Murshidabad Division | CHANDNI DAHA PIPED WATER SUPPLY SCHEME . , SM/16217 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.62 | 100 | 100
1767 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Alighata, Block- Lalgola, District- Murshidabad. , SM/16496 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Alighata village, Block:- Lalgola under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3158/MEDB | 08/08/2023 | 92 | ARINDAM MAJUMDAR | 6.27 | 0 | 0 | 0
1768 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Alighata, Block- Lalgola, District- Murshidabad. , SM/16496 | New | Mini Piped Water Supply Scheme for Alighata under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 146/BD-I | 15/05/2023 | 899 | M/S. DAS ENTERPRISE MAHULA, DASPARA, VILL +P.O-GOPINATHPUR, MURSHIDABAD. | 30.54 | 0 | 0 | 15
1769 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (maximum 100 households) Village-Sibnagar Zone-V, Block-Nawda, District- Murshidabad. , SM/16501 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Shibnagar Zone-V village, Block:- Nawda under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3047/MEDB | 02/08/2023 | 92 | M/S. SUPER CONSTRUCTION | 6.32 | 0 | 0 | 0
1770 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (maximum 100 households) Village-Sibnagar Zone-V, Block-Nawda, District- Murshidabad. , SM/16501 | New | Mini Piped Water Supply Scheme for Sibnagar Zone-V under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 158/BD-I | 15/05/2023 | 90 | SUJAUDDIN SHAIKH | 23.91 | 0 | 0 | 0
1771 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME , SM/16400 | Augmentation | Work of Extension of Existing Boundary Wall and Painting of the same at Birendranagar (Zone-I) Water supply scheme , under Jangipur Sub-Division, P.H.E. Dte in the District Murshidabad. | 392/JSD | 31/12/2021 | 30 | S. ROY & CO. | 4.79 | 3.9 | 100 | 0
1772 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME , SM/16400 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 3.13 | 100 | 100
1773 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME , SM/16400 | Augmentation | Material Requisition To Resource Division | 1210/MURD/21 | 02/05/2023 | 0 | Resource Division | 2.46 | 0 | 0 | 0
1774 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME , SM/16400 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I II & III ,Zone-I under BIRENDRANAGAR ground water based water supply scheme under Block_ Raghunathganj-II Dist. - Murshidabad under MEDB, PHE Dte. | 4346/MEDB | 29/12/2023 | 641 | JOGMAYA ENGINEERING | 32 | 0 | 0 | 30
1775 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME , SM/16400 | Augmentation | Allied works for Renovation of Existing AIRP, Gobordanga Model (Capacity 16 Cu.M/hr) at Birendranagar (Zone-I) W/S Scheme in connection with Augmentation of Birendranagar (Zone-I) PWSS under Murshidabad Division P.H.Engineering Dte. | 782/MURD | 14/03/2024 | 20 | M/S BAPPA ENTERPRISE | 10.09 | 0 | 0 | 0
1776 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME , SM/16400 | Augmentation | Renovation of Existing AIRP (Capacity 16 Cu.M/hr) for changing of filter media of 1 no Polishing Unit (2.50 m dia x 1.5 m HOS) & 1 no Primary Unit (2.50 m dia x 2.00 m HOS) and painting all vessel, pipes etc. all complete at Birendranagar (Zone-I) W/S Scheme under Murshidabad Division P.H.Engineering Dte. | 617/MURD | 28/02/2024 | 30 | M/S BAPPA ENTERPRISE | 16.7 | 0 | 0 | 0
1777 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME , SM/16400 | Augmentation | Allied works In connection with Bypass line connection from AIRP to Distribution main at Birendranagar (Zone-I) Water Supply Scheme for the work of Augmentation of Birendranagar (Zone-I) PWSS under Murshidabad Division P.H.E Dte. | 821/MURD | 15/03/2024 | 30 | MAA CONSTRUCTION (MUJIBOR, MAJDIYA SEKHPARA) | 3.27 | 3.16 | 100 | 100
1778 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF BIRENDRA NAGAR (ZONE-I) PIPED WATER SUPPLY SCHEME , SM/16400 | Augmentation | Laying of Distribution System with FHTC to 752 nos household, Rising Main & OHR Repair of 90 cum capacity for Augmentation of Birendranagar (Zone-I) Pipe water supply scheme in Raghunathganj-II Block under Murshidabad Division ,PHE.Dte | 830/MURD | 23/03/2023 | 1080 | MAA CONSTRUCTION (MUJIBOR, MAJDIYA SEKHPARA) | 103.52 | 92.93 | 96.46 | 30
1779 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MADNA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16405 | Augmentation | Material Requisition To Resource Division | 1147/MURD/8 | 27/04/2023 | 0 | Resource Division | 128.8 | 0 | 0 | 0
1780 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MADNA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16405 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 0 | 5
1781 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MADNA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16405 | Augmentation | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0 | 0
1782 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MADNA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16405 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for MADNA Zone-I Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division, PHE Dte. | 1156/MURD | 20/05/2025 | 60 | AUDY ENGINEERING | 23 | 0 | 0 | 0
1783 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MADNA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16405 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 4.06 | 100 | 100
1784 | MURSHIDABAD | Berhampore Mechanical | ROSORA(P) PIPED WATER SUPPLY SCHEME , BLOCK- KANDI , DISTRICT- MURSHIDABAD. , SM/16504 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Rosora (P) Part-A village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3068/MEDB | 02/08/2023 | 92 | DAS ENTERPRISE (CHOA) | 6.3 | 0 | 0 | 0
1785 | MURSHIDABAD | Berhampore Mechanical | ROSORA(P) PIPED WATER SUPPLY SCHEME , BLOCK- KANDI , DISTRICT- MURSHIDABAD. , SM/16504 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Rosora (P) Part-B village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3069/MEDB | 02/08/2023 | 92 | A. S. ENGINEERING | 6.32 | 0 | 0 | 0
1786 | MURSHIDABAD | Murshidabad Division | ROSORA(P) PIPED WATER SUPPLY SCHEME , BLOCK- KANDI , DISTRICT- MURSHIDABAD. , SM/16504 | New | Ground Water based piped water supply scheme for Rosora (P) Part- A village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2423/MURD | 08/08/2023 | 60 | C. R. CONSTRUCTION | 30.55 | 0 | 0 | 0
1787 | MURSHIDABAD | Murshidabad Division | ROSORA(P) PIPED WATER SUPPLY SCHEME , BLOCK- KANDI , DISTRICT- MURSHIDABAD. , SM/16504 | New | Ground Water based piped water supply scheme for Rosora (P) Part- B village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2417/MURD | 08/08/2023 | 1027 | SUKUMAR ROY | 30.55 | 0 | 0 | 50
1788 | MURSHIDABAD | Berhampore Mechanical | CHANDAMARI PIPED WATER SUPPLY SCHEME. , SM/16218 | New | NEW CONNECTION AT CHANDAMARI PH-I | 140/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 7.27 | 0 | 0 | 0
1789 | MURSHIDABAD | Berhampore Mechanical | CHANDAMARI PIPED WATER SUPPLY SCHEME. , SM/16218 | New | NEW CONNECTION AT CHANDAMARI PH-II |  | 11/12/2024 | 0 | WBSEDCL | 4.31 | 0 | 0 | 0
1790 | MURSHIDABAD | Murshidabad Division | CHANDAMARI PIPED WATER SUPPLY SCHEME. , SM/16218 | New | CHANDMARI , BAHUTALI & FATELLAPUR PWSS to accommodate FHTC under Jal Jeevan Mission, Block- SUTI-I of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | 3176/MURD | 11/10/2023 | 813 | CHAKRABORTY CONSTRUCTION | 2258.18 | 0 | 0 | 10
1791 | MURSHIDABAD | Murshidabad Division | CHANDAMARI PIPED WATER SUPPLY SCHEME. , SM/16218 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 3.26 | 100 | 100
1792 | MURSHIDABAD | Murshidabad Division | Augmentation of Garibpur Piped Water Supply Scheme (Zone-I)PART-B Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16556 | Augmentation | Cleaning the chokage of AC/DI/CI/UPVC pipes in the existing pipeline by split bamboo for Garibpur Zone-II PWSS under Islampur Sub-Division, PHE Dte. | 401/ISD | 29/09/2023 | 7 | RAJAKINI ENTERPRISE | 0.81 | 0 | 0 | 100
1793 | MURSHIDABAD | Murshidabad Division | Augmentation of Garibpur Piped Water Supply Scheme (Zone-I)PART-B Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16556 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 4.47 | 100 | 100
1794 | MURSHIDABAD | Murshidabad Division | Augmentation of Garibpur Piped Water Supply Scheme (Zone-I)PART-B Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16556 | Augmentation | Augmentation of SHIBNAGAR LASKARPUR (Zone-I) Part-B & Garibpur (Zone-I) Part-B PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | 2888/MURD | 12/09/2023 | 750 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 226.15 | 0 | 0 | 75
1795 | MURSHIDABAD | Murshidabad Division | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16389 | New | Material Requisition To Resource Division | 1075/MURD/5 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
1796 | MURSHIDABAD | Berhampore Mechanical | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16389 | New | New connection charge for Padamkandi, P/H No.- II. | 121/WBSEDCL-JJM | 27/09/2023 | 0 | WBSEDCL | 4.19 | 0 | 0 | 0
1797 | MURSHIDABAD | Berhampore Mechanical | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16389 | New | Electric Service New Connection PADAMKANDI PH-1 PWSS Application NO. 3004403540. ID. 304119863 | 171/WBSEDCL-JJM | 05/12/2023 | 0 | WBSEDCL | 10.39 | 0 | 0 | 0
1798 | MURSHIDABAD | Murshidabad Division | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16389 | New | Allied work of Laying rising main and distribution system with FHTC including Construction Pump House Cum Chlorine Room , Boundary wall at 2nd Tube Well Site and Earth filling at both site of Padamkandi Water Supply Scheme , under Jal Jeevan Mission of KHARGRAM Block of Murshidabad District under Murshidabad Division, PHE. Dte. | 1926/MURD | 03/07/2024 | 60 | ARJIMA CONSTRUCTION | 19.18 | 18.55 | 100 | 80
1799 | MURSHIDABAD | Murshidabad Division | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16389 | New | Formal work order for PADAM KANDI & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of KHARGRAM Block of Murshidabad District under Murshidabad Division, PHE. Dte. | 732/MURD | 15/03/2023 | 749 | APURBA SAHA CHOWDHURY | 145.12 | 92.06 | 63.44 | 90
1800 | MURSHIDABAD | Berhampore Mechanical | PADAMKANDI AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16389 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under PADAMKANDI ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | 1927/MEDB | 16/06/2023 | 92 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 20.81 | 12.34 | 59.33 | 50
1801 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16560 | Augmentation | Material Requisition To Resource Division | 1147/MURD/7 | 27/04/2023 | 0 | Resource Division | 0.69 | 0 | 0 | 0
1802 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16560 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 2.39 | 100 | 100
1803 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16560 | Augmentation | NEW CONNECTION AT BAJEGAJIPUR PH-1 | 186/WBSEDCL-JJM | 09/08/2024 | 0 | WBSEDCL | 4.52 | 0 | 0 | 0
1804 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16560 | Augmentation | NEW CONNECTION AT BAJEGAJIPUR PH-1 |  | 02/08/2024 | 0 | WBSEDCL | 4.52 | 0 | 0 | 0
1805 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16560 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under BAZEGAZIPUR ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | 1920/MEDB | 16/06/2023 | 930 | SARKAR CONSTRUCTION | 21.42 | 17.54 | 81.87 | 10
1806 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16560 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 0 | 5
1807 | MURSHIDABAD | Murshidabad Division | Augmentation of Dakshin Kanda Zone - II Water Supply Scheme Block - Bharatpur-II , Dist- Murshidabad. , SM/15741 | Augmentation | Augmentation of DAKSHIN KHANDA ZONE - II PWSS under Jal Jeevan Mission of Bharatpur-II Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | 3301/MURD | 20/10/2023 | 300 | M/S GHOSH & CO. | 536.15 | 0 | 0 | 0
1808 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Dakshin Kanda Zone - II Water Supply Scheme Block - Bharatpur-II , Dist- Murshidabad. , SM/15741 | Augmentation | NEW CONNECTION AT DAKSHINKHANDA Z-II PH-III |  | 02/12/2024 | 0 | WBSEDCL | 4.08 | 0 | 0 | 0
1809 | MURSHIDABAD | Murshidabad Division | Augmentation of Dakshin Kanda Zone - II Water Supply Scheme Block - Bharatpur-II , Dist- Murshidabad. , SM/15741 | Augmentation | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at, Dakshinkhanda Zone-IA T.W-II, III, Zone-IB T.W-II, Dakshinkhanda Zone-II T.W- I, II Water Supply Scheme of Bharatpur-II Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 718/MURD | 25/03/2025 | 65 | MAMATA USHA ENTERPRISE | 58.95 | 0 | 0 | 0
1810 | MURSHIDABAD | Murshidabad Division | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16111 | New | Material Requisition To Resource Division | 1219/MURD/10 | 03/05/2023 | 0 | Resource Division | 0.76 | 0 | 0 | 0
1811 | MURSHIDABAD | Berhampore Mechanical | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16111 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Matua ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | 4317/MEDB | 29/12/2023 | 91 | H.K. DAS & CO. | 8.93 | 5.69 | 63.76 | 10
1812 | MURSHIDABAD | Murshidabad Division | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16111 | New | Construction of Pump House, Boundary Wall , Path Way of Matua PWSS in Bhratpur-II Block , KANDI Sub-Division under Murshidabad Division ,PHE.Dte. | 780/MURD | 14/03/2024 | 45 | SANTA TRADING | 14.19 | 3.75 | 20.94 | 90
1813 | MURSHIDABAD | Berhampore Mechanical | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16111 | New | Matwa PH-1 Application no- 3004547182 | 237/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 7.87 | 0 | 0 | 0
1814 | MURSHIDABAD | Berhampore Mechanical | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16111 | New | NEW CONNECTION AT MATWA PH-II | 69/WBSEDCL-JJM | 09/05/2024 | 0 | WBSEDCL | 2.96 | 0 | 0 | 0
1815 | MURSHIDABAD | Murshidabad Division | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16111 | New | Providing FHTC Connection to 274 nos household , Laying of Distribution System,Rising Main , Construction of Pump House with sanitary and Water Supply Arrangement , Pump House cum Blower room And Boundary Wall for work of MATUA PWSS Bharatpur II Block under Murshidabad Division , PHE.Dte. | 1932/MURD | 18/07/2023 | 602 | SANTA TRADING | 60.51 | 29.09 | 48.44 | 60
1816 | MURSHIDABAD | Murshidabad Division | MATUA AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16111 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at AMLAI and MATHUA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 2795/MURD | 04/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 5.86 | 29.5 | 100
1817 | MURSHIDABAD | Murshidabad Division | BERBARI AND ADJOINING MOUJAS PWSS , SM/15694 | New | Material Requisition To Resource Division | 1075/MURD/9 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
1818 | MURSHIDABAD | Murshidabad Division | BERBARI AND ADJOINING MOUJAS PWSS , SM/15694 | New | BERBARI & UJUNIA adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block-BHARATPUR-I & II of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE Dte. | 882/MURD | 28/03/2023 | 280 | BANAMALI ENTERPRISES | 224.42 | 18.12 | 20.63 | 35
1819 | MURSHIDABAD | Berhampore Mechanical | BERBARI AND ADJOINING MOUJAS PWSS , SM/15694 | New | Berbari PH-2 Application No- 3004528419 | 277/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.24 | 0 | 0 | 0
1820 | MURSHIDABAD | Berhampore Mechanical | BERBARI AND ADJOINING MOUJAS PWSS , SM/15694 | New | BERBARI PH-1 | 399/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 13.01 | 0 | 0 | 0
1821 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chaltia (Village code 315450) under Bairgachi (Zone-C) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE.Dte. (Sl-01) | 1955/BD-I | 27/10/2021 | 180 | UNICON INDIA | 267.92 | 90.56 | 33.8 | 1
1822 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 49.61 | 1
1823 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Additional laying work of 300 mm dia DI Pipe Line at pond side of near Chumrigacha Primary School due to damage of UPVC Pipe line and with allied works of Distribution pipe line under Bairgachi Surface Water based Water Supply Scheme under Berhampore Division - I, PHE Dte.in Murshidabad District | 547/BD-I | 13/05/2022 | 10 | JIBENDRA NARAYAN SUKUL | 4.54 | 4.31 | 100 | 45
1824 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Math Binkar (Village code 315366) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1870/BD-I | 07/10/2021 | 60 | M/S ADHIKARI CONSTRUCTION | 6.47 | 0 | 0 | 0
1825 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Fate Sing Diar and Char Narayanpur (Village code 315364,315384) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 1841/BD-I | 05/10/2021 | 60 | UNIVERSE UNEMPLOYED ENGINEERS CO. OPT. & CONSTRUCTION SOCIETY LTD. | 55.84 | 18.71 | 33.51 | 40
1826 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baikunthapur (Village code 315369) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1871/BD-I | 07/10/2021 | 90 | M/S BIMALENDU BOSE | 22.56 | 21.5 | 95.32 | 1
1827 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bairgachi Village- village code-315382, Habitation-Char Begpur (ID-0001295651) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | 1872/BD-I | 07/10/2021 | 60 | TANUSHREE ENTERPRISE | 14.92 | 0 | 0 | 0
1828 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mankara, Bezpara, Baragachi, Paschim Narayanpur (Village code 315365, 315368, 315382 & 315383) respectively under Bairgachi (Zone-C) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-15) | 1889/BD-I | 07/10/2021 | 180 | M/S S.S ENTERPRISE ALAMPUR, NODAKHALI, SOUTH 24 PARGANAS | 296.55 | 139.52 | 47.05 | 1
1829 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ajodhyanagar village-Village Code-315449, Habitation-Belia khari (ID-0001295654) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID ? 0001756485 | 1873/BD-I | 07/10/2021 | 90 | J.S. CONSTRUCTION | 22.08 | 21.87 | 99.06 | 0
1830 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.08.2023 to 31.01.2024. | 517/BD-I | 25/07/2023 | 184 | SOUVIK HALDER | 0.91 | 2.39 | 263.26 | 10
1831 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.02.2024 to 31.07.2024. | 131/BD-I | 31/01/2024 | 182 | SOUVIK HALDER | 0.91 | 2.39 | 263.53 | 100
1832 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.08.2024 to 31.01.2025. | 1195/BD-I | 26/07/2024 | 184 | SOUVIK HALDER | 0.91 | 2.38 | 262.55 | 0
1833 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.02.2025 to 31.07.2025. | 193/BD-I | 30/01/2025 | 181 | SOUVIK HALDER | 0.91 | 1.6 | 176.02 | 0
1834 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.08.2025 to 31.10.2025. | 991/BD-I | 31/07/2025 | 92 | SOUVIK HALDER | 0.45 | 0 | 0 | 0
1835 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baninathpur (Village code 315367) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 1842/BD-I | 05/10/2021 | 50 | JIBENDRA NARAYAN SUKUL | 41.36 | 41.73 | 100 | 1
1836 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bhatpara (Village code 315370) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 1843/BD-I | 05/10/2021 | 30 | PROSENJIT DAS | 24.41 | 21.86 | 100 | 1
1837 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Formal Work order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under Command area of village of Haridasmati (Village code 315451) under Bairgachi (Zone-C) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-06) | 1882/BD-I | 07/10/2021 | 180 | DHIMAN SARKAR | 88.21 | 78.75 | 100 | 50
1838 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Laying of different dia UPVC distribution pipeline with allied works along with attached sheet of node point over command area of Chaltia village of Bhakuri-I gram panchayat under Bairgachi Water Supply Scheme,Central Sector Part-II under Berhampore Division-I ,P.H.E Dte. | 1463/BD-I | 16/08/2021 | 60 | MITRA & SARKAR CONSTRUCTION | 51.34 | 10.12 | 100 | 0
1839 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Bairgachi Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | 2227/BD-I | 15/12/2021 | 90 | JIBENDRA NARAYAN SUKUL | 74.65 | 77.64 | 100 | 1
1840 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Additional Laying works at village Bhatpara ( Village code-315370) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission & JalSwapna under Bairgachi (Zone-C) Surface water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 98/BD-I | 01/02/2022 | 15 | MINA DAS | 8.88 | 7.63 | 100 | 1
1841 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Laying of 350 mm dia DI (K-7) distribution Pipeline including allied works along with attached sheet of node point over command area of Bhakuri-I G.P under Bairgachi W/S scheme under Berhampore Division -I ,P.H.E Dte. | 552/BD-I | 13/05/2022 | 45 | DHIMAN SARKAR | 20.59 | 6.02 | 100 | 100
1842 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Additional Laying works at village Ajodhya Nagar & Chumrigacha to faciliate Functional Household Tap connection(FHTC) works in connection to Jal Jeevan Mission under Bairgachi (Zone-C) surface water based Water Supply Scheme of Central Sector Part-II under Murshidabad District under Berhampore Division-I,PHE.Dte. | 21/BD-I | 11/04/2023 | 30 | JIBENDRA NARAYAN SUKUL | 50.51 | 50.5 | 100 | 100
1843 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Laying of different dia DI pipe Line in connection with JJM (Jal Jeevan Mission) over damaged portion with allied works at Karim more and near Balarampur High School for smooth running of FHTC Work under Bairgachi (Zone-C) surface based water supply scheme under CS Part-II of BD-I, P.H.E Dte | 85/BD-I | 03/05/2023 | 30 | JIBENDRA NARAYAN SUKUL | 5.69 | 4.97 | 100 | 100
1844 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ajodhya Nagar (Village code 315449) under Bairgachi (Zone-C) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-05) | 1883/BD-I | 07/10/2021 | 180 | TARUN KUMAR BHATTACHARYA | 133.38 | 121.89 | 100 | 50
1845 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Laying of UPVC pipe Line in connection with JJM (Jal Jeevan Mission) with allied works near Balarampur Halt Station under Bairgachi (Zone-C) surface based water supply scheme under CS Part-II of BD-I, P.H.E Dte. | 88/BD-I | 03/05/2023 | 30 | KAUSHIK MAJUMDAR | 3.5 | 3.48 | 100 | 100
1846 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Balance Laying and allied works at village Ajodha nagar & Chumrigacha to facilitate Functional Household Tap connection (FHTC) Works in connection to Jal Jeevan Mission under Bairgachi(ZONE-C) surface water based Water Supply Scheme of Central Sector Part-II under Murshidabad District under Berhampore Division-I,PHE Dte. | 119/BD-I | 30/01/2024 | 60 | JIBENDRA NARAYAN SUKUL | 10.28 | 10.26 | 100 | 100
1847 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Balance and Additional Work of Laying and Improvement of Office cum Godown building at OHR site of Bairgachhi Water Supply Scheme of Central Sector Part-II, under JJM within Berhampore block in the district of Murshidabad under Berhampore Division-I, P.H.Engineering Dte. | 1464/BD-I | 06/09/2024 | 87 | JIBENDRA NARAYAN SUKUL | 26.42 | 6.98 | 20.94 | 100
1848 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Improvement of Rising main and distribution system for providing drinking water facility to the local habitation within command area of Purbanarayanpur Zone of Central Sector Part-II under JJM within Berhampore block of Murshidabad district under Berhampore Division-I, P.H.E. Dte. | 1473/BD-I | 06/09/2024 | 60 | JAMIRUL CONSTRUCTION | 11.25 | 2.88 | 20.94 | 100
1849 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08916 | Retrofitting | Addittional work for retrofitting and Laying of distribution pipeline of BAIRAGACHI and allied works under JJM within Berhampore Block under Berhampore Division-I, PHE Dte. in the district of Murshidabad. | 1612/BD-I | 03/10/2024 | 15 | JIBENDRA NARAYAN SUKUL | 2.48 | 0 | 0 | 100
1850 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-I PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16768 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,ZONE-I under MAHESAIL ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | 1917/MEDB | 16/06/2023 | 92 | BHAGIRATHI JUTE AND HOLDINGS PVT LTD | 22.92 | 0 | 0 | 0
1851 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-I PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16768 | Augmentation | Material Requisition To Resource Division | 1147/MURD | 27/04/2023 | 0 | Resource Division | 32.39 | 0 | 0 | 0
1852 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-I PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16768 | Augmentation | Material Requisition To Resource Division | 1147/MURD | 27/04/2023 | 0 | Resource Division | 32.39 | 0 | 0 | 0
1853 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-I PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16768 | Augmentation | NEW CONNECTION AT MAHESAIL Z-I PH-I |  | 12/11/2024 | 0 | WBSEDCL | 3.47 | 0 | 0 | 0
1854 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-I PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16768 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 0 | 21
1855 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHESAIL ZONE-I PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16768 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.84 | 100 | 100
1856 | MURSHIDABAD | Murshidabad Division | MANDALSAR AND ADJOINING MOUJAS PWSS , SM/15938 | New | Material Requisition To Resource Division | 1075/MURD/2 | 19/04/2023 | 0 | Resource Division | 31.87 | 0 | 0 | 0
1857 | MURSHIDABAD | Berhampore Mechanical | MANDALSAR AND ADJOINING MOUJAS PWSS , SM/15938 | New | NEW SERVICE CONNECTION AT PWSS PH1 MANDALSAR ID 304239451 | 303/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 3.41 | 0 | 0 | 0
1858 | MURSHIDABAD | Berhampore Mechanical | MANDALSAR AND ADJOINING MOUJAS PWSS , SM/15938 | New | POWER CONNECTION AT PWSS PH2 MANDALSARPOWER CONNECTION AT PWSS PH2 MANDALSAR ID 304250313 | 44/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 7.8 | 0 | 0 | 0
1859 | MURSHIDABAD | Murshidabad Division | MANDALSAR AND ADJOINING MOUJAS PWSS , SM/15938 | New | Formal work order for MANDALSAR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Khargram Block of Murshidabad District under Kandi Sub-Division, Murshidabad Division, PHE.Dte. | 625/MURD | 03/03/2023 | 972 | MOTI RAHAMAN | 359.46 | 188.36 | 52.4 | 30
1860 | MURSHIDABAD | Berhampore Mechanical | MANDALSAR AND ADJOINING MOUJAS PWSS , SM/15938 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under MANDALSAR ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | 4309/MEDB | 29/12/2023 | 731 | JOGMAYA ENGINEERING | 21.5 | 18.03 | 83.86 | 80
1861 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16767 | Augmentation | Material Requisition To Resource Division | 1180/MURD/15 | 29/04/2023 | 0 | Resource Division | 61.77 | 0 | 0 | 0
1862 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16767 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-III, BHANDARA ZONE - I and SURANGAPUR ZONE -I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 3785/MURD | 11/12/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 35.34 | 10.46 | 100 | 80
1863 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16767 | Augmentation | Material Requisition To Resource Division | 1811/MURD/07 | 20/06/2024 | 0 | Resource Division | 34.58 | 0 | 0 | 0
1864 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16767 | Augmentation | Material Requisition To Resource Division | 711/MURD | 07/03/2024 | 0 | Resource Division | 26 | 0 | 0 | 0
1865 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16767 | Augmentation | SURANGAPURPH-1 Z-I | 414/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 3.67 | 0 | 0 | 0
1866 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16767 | Augmentation | SURANGAPUR Z-I PH-II | 413/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 7.85 | 0 | 0 | 0
1867 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16767 | Augmentation | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagaipur PWSS TW-I,II, Chandpur Zone-I PWSS T.W.-II, Edrakpur PWSS T.W-II, Surangapur Zone-IA TW-I of Nowda Block under Berhampore Sub-Division,Murshidabad Division, P.H.Engineering Dte. | 663/MURD | 19/03/2025 | 65 | SARKAR WATER SUPPLY AGENCY | 58.87 | 0 | 0 | 0
1868 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16767 | Augmentation | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490 another 160 days from 12/01/2025 to 20/06/2025. | 06/BSD | 08/01/2025 | 160 | ABIDA CONSTRUCTION | 0.93 | 1.59 | 171.68 | 0
1869 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16767 | Augmentation | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490,91days from 01/09/2025 to 30/11/2025. | 125/BSD | 01/09/2025 | 91 | ABIDA CONSTRUCTION | 0.53 | 0 | 0 | 0
1870 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16767 | Augmentation | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490 another 91days from 21/06/2025 to 19/09/2025. | 122/BSD | 20/06/2025 | 91 | ABIDA CONSTRUCTION | 0.53 | 0 | 0 | 0
1871 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-A TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16767 | Augmentation | Augmentation of SURANGAPUR Zone-I (Part -A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 952/MURD | 05/04/2023 | 696 | M/S NIRAPADA BHATTACHARJEE | 329.64 | 286.64 | 86.96 | 100
1872 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BILASPUR PIPED WATER SUPPLY SCHEME. , SM/16866 | Augmentation | Material Requisition To Resource Division | 1180/MURD/04 | 29/04/2023 | 0 | Resource Division | 19.59 | 0 | 0 | 0
1873 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BILASPUR PIPED WATER SUPPLY SCHEME. , SM/16866 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | 1925/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 9.6 | 1.72 | 50 | 100
1874 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BILASPUR PIPED WATER SUPPLY SCHEME. , SM/16866 | Augmentation | Augmentation of BILASPUR PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | 1385/MURD | 22/05/2023 | 650 | ULTRA CONSTRUCTION. | 227.02 | 178.12 | 84.2 | 45
1875 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BILASPUR PIPED WATER SUPPLY SCHEME. , SM/16866 | Augmentation | Renovation for Filter media of Existing IEP of (Capacity 51.38 Cum/hr.) in Bilaspur Water Supply Scheme of Domkal Block under Murshidabad Division, PHE Dte. | 1342/MURD | 11/06/2025 | 180 | SK CONSTRUCTION (NAJIR SK.) | 11.97 | 0 | 0 | 100
1876 | MURSHIDABAD | Murshidabad Division | SIDDHESWARI & ADJOINING MOUJAS PWSS , SM/18312 | New | Material Requisition To Resource Division | 1075/MURD/7 | 19/04/2023 | 0 | Resource Division | 20.78 | 0 | 0 | 0
1877 | MURSHIDABAD | Berhampore Mechanical | SIDDHESWARI & ADJOINING MOUJAS PWSS , SM/18312 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under SIDDHESWARI ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | 2299/MEDB | 04/07/2023 | 92 | DAS ENTERPRISE (CHOA) | 23.39 | 19.61 | 83.85 | 60
1878 | MURSHIDABAD | Murshidabad Division | SIDDHESWARI & ADJOINING MOUJAS PWSS , SM/18312 | New | SIDDHESWARI PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | 1721/MURD | 04/07/2023 | 638 | M/S. S. DAS AND ENTERPRISE | 443.38 | 279.38 | 63.01 | 80
1879 | MURSHIDABAD | Murshidabad Division | SIDDHESWARI & ADJOINING MOUJAS PWSS , SM/18312 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SIDDHESWARI & ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | 2776/MURD | 01/09/2023 | 21 | MAMATA USHA ENTERPRISE | 18.44 | 7.8 | 42.31 | 60
1880 | MURSHIDABAD | Murshidabad Division | SIDDHESWARI & ADJOINING MOUJAS PWSS , SM/18312 | New | SIDDHESWARI PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (Part-B) | 3116/MURD | 05/10/2023 | 300 | MOTI RAHAMAN | 407.86 | 85.98 | 21.08 | 10
1881 | MURSHIDABAD | Murshidabad Division | SAHAPUR AND ADJOINING MOUJAS PWSS , SM/18396 | New | Material Requisition To Resource Division | 1067/MURD/10 | 18/04/2023 | 0 | Resource Division | 52.37 | 0 | 0 | 0
1882 | MURSHIDABAD | Murshidabad Division | SAHAPUR AND ADJOINING MOUJAS PWSS , SM/18396 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAHAPUR AND ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at BHARATPUR -I Block under Murshidabad Division, P.H. Engineering Dte | 2808/MURD | 05/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 15.24 | 100 | 100
1883 | MURSHIDABAD | Berhampore Mechanical | SAHAPUR AND ADJOINING MOUJAS PWSS , SM/18396 | New | Quotation for Sahapur PH No-1 | 324/WBSEDCL-JJM | 06/02/2024 | 0 | WBSEDCL | 12.71 | 0 | 0 | 0
1884 | MURSHIDABAD | Berhampore Mechanical | SAHAPUR AND ADJOINING MOUJAS PWSS , SM/18396 | New | NEW CONNECTION AT SAHAPUR PH-II | 101/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 3.55 | 0 | 0 | 0
1885 | MURSHIDABAD | Murshidabad Division | SAHAPUR AND ADJOINING MOUJAS PWSS , SM/18396 | New | Sahapur (Part-A) & adjoining mouzas PWSS to accommodate Construction Tube Well, OHR, Pump House Cum Chlorine Room, Rising Main, FHTC work, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | 1885/MURD | 17/07/2023 | 1264 | HOQUEDAR ALI | 256.56 | 35.46 | 13.82 | 25
1886 | MURSHIDABAD | Murshidabad Division | SAHAPUR AND ADJOINING MOUJAS PWSS , SM/18396 | New | SAHAPUR (Part-B) & adjoining mouzas PWSS to accommodate Of T/W,LDS, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | 1897/MURD | 17/07/2023 | 968 | M/S JAN MAHAMMAD | 520.42 | 188.12 | 36.15 | 20
1887 | MURSHIDABAD | Berhampore Mechanical | SAHAPUR AND ADJOINING MOUJAS PWSS , SM/18396 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I , II & III under SAHAPUR ground water based water supply scheme under Block_ Bharatpur-I, Dist. - Murshidabad under MEDB, PHE Dte. | 4064/MEDB | 04/12/2023 | 607 | CONCORD ENGINEERING | 36.55 | 0 | 0 | 5
1888 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GAIRAMARI PIPED WATER SUPPLY SCHEME. , SM/19124 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | 1925/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 9.6 | 2.22 | 50 | 100
1889 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GAIRAMARI PIPED WATER SUPPLY SCHEME. , SM/19124 | Augmentation | NEW CONNECTION AT GARAIMARI Z-II PH-II |  | 26/11/2024 | 0 | WBSEDCL | 7.33 | 0 | 0 | 0
1890 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GAIRAMARI PIPED WATER SUPPLY SCHEME. , SM/19124 | Augmentation | NEW CONNECTION AT GARAIMARI Z-II PH-I |  | 26/11/2024 | 0 | WBSEDCL | 4.01 | 0 | 0 | 0
1891 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GAIRAMARI PIPED WATER SUPPLY SCHEME. , SM/19124 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under Gairamari ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | 591/MEDB | 31/01/2024 | 1008 | M/S. SUPER CONSTRUCTION | 36 | 0 | 0 | 70
1892 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GAIRAMARI PIPED WATER SUPPLY SCHEME. , SM/19124 | Augmentation | Renovation of Filter Media of Existing Modified AIRP of (Capacity 180 Cum/hr.) at Garaimari Zone-I Water Supply Scheme of Domkal Block under Murshidabad Division, P.H.Eengineering Dte. | 228/MURD | 27/01/2025 | 45 | SOM CONSTRUCTION AGENCY | 28.21 | 0 | 0 | 0
1893 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME OF MANIGRAM-BALARAMBATI BLOCK-SAGARDIGHI , SM/19017 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional Household Connection of different existing PWSS MANIGRAM-BALARAMBATI PWSS Scheme, Block-SAGARDIGHI to be Augmentation/Rejuvination under Murshidabad Division P.H.E Dte. | 3250/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 4.48 | 4.48 | 100 | 50
1894 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME OF MANIGRAM-BALARAMBATI BLOCK-SAGARDIGHI , SM/19017 | Augmentation | Material Requisition To Resource Division | 1180/MURD/28 | 29/04/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
1895 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPLY SCHEME OF MANIGRAM-BALARAMBATI BLOCK-SAGARDIGHI , SM/19017 | Augmentation | Providing FHTC Connection to 322 nos household , Laying of Distribution System, Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works for Augmentation work of Manigram Balarambati PWSS within Sagardighi Block under Murshidabad Division , PHE.Dte. | 3340/MURD | 28/10/2023 | 520 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 96.91 | 0 | 0 | 45
1896 | MURSHIDABAD | Berhampore Mechanical | BAIDYNATHPUR ADJOINING MOUJA PWSS , SM/18580 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Baidynathpur ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | 3697/MEDB | 03/11/2023 | 92 | P. K. ENGINEERING | 23.71 | 0 | 0 | 0
1897 | MURSHIDABAD | Murshidabad Division | BAIDYNATHPUR ADJOINING MOUJA PWSS , SM/18580 | New | Material Requisition To Resource Division | 1219/MURD/16 | 03/05/2023 | 0 | Resource Division | 9.79 | 0 | 0 | 0
1898 | MURSHIDABAD | Berhampore Mechanical | BAIDYNATHPUR ADJOINING MOUJA PWSS , SM/18580 | New | Baidyanathpur PH-2 Application No- 3004548228 | 232/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 4.26 | 0 | 0 | 0
1899 | MURSHIDABAD | Berhampore Mechanical | BAIDYNATHPUR ADJOINING MOUJA PWSS , SM/18580 | New | Baidyanathpur PH1 Application no-3004548117 | 231/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 4.05 | 0 | 0 | 0
1900 | MURSHIDABAD | Murshidabad Division | BAIDYNATHPUR ADJOINING MOUJA PWSS , SM/18580 | New | BAIDYNATHPUR & adjoining mouzas PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE. Dte. | 2366/MURD | 04/08/2023 | 1001 | M/S.TAPAS KUMAR CHAKRABORTY | 867.57 | 173.07 | 19.95 | 10
1901 | MURSHIDABAD | Murshidabad Division | BAIDYNATHPUR ADJOINING MOUJA PWSS , SM/18580 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAIDYNATHPUR , DHANDANGA & SANTOSHPUR Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 2806/MURD | 05/09/2023 | 589 | INDRAJIT MAZUMDAR | 27.64 | 0 | 0 | 100
1902 | MURSHIDABAD | Murshidabad Division | Retrofitting of Ground Water Based Water Supply Scheme for Kamalakantapur and its Adjoining Mouzas to provided last mile connectivety and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . , SM/18488 | Retrofitting | Kamalakantapur PWSS to accommodate FHTC of 1518 nos household under Jal Jeevan Mission of Bharatpur-I Block, Murshidabad District under Murshidabad Division, PHE. Dte. | 2492/MURD | 11/08/2023 | 60 | RATAN DUTTA | 80.18 | 36.32 | 45.3 | 15
1903 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sibnagar Laskarpur (314702) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District (P , SM/07906 | Retrofitting | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 0 | 0 | 1
1904 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sibnagar Laskarpur (314702) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District (P , SM/07906 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna ( Jal Jeevan Mission) Mouja Sibnagar Laskarpur (Village code 314702)under Sibnagar Laskarpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723328) | 1562/MURD | 16/06/2022 | 120 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 151.41 | 149.55 | 98.77 | 1
1905 | MURSHIDABAD | Berhampore Mechanical | SURFACE WATER BASED WATER SUPPLY SCHEME IN THE UNCOVERED ARSENIC AFFECTED AREAS OF BELDANGA-I BLOCK OF MURSHIDABAD , SM/18896 | Augmentation | Providing Electrical Equipment for 11/0.433 KV Sub-station (LT Bulk & HT Bulk ) at Intake and WTP under Augmentation of Beldanga Surface Water Based W/S Scheme in the Dist. of Murshidabad. | 1495/MEDB | 26/06/2024 | 183 | MAHADEV ENTERPRISE | 320.85 | 0 | 0 | 0
1906 | MURSHIDABAD | Murshidabad Division | SURFACE WATER BASED WATER SUPPLY SCHEME IN THE UNCOVERED ARSENIC AFFECTED AREAS OF BELDANGA-I BLOCK OF MURSHIDABAD , SM/18896 | Augmentation | Material Requisition To Resource Division | MSD/1735 | 11/06/2024 | 0 | Resource Division | 6.55 | 0 | 0 | 0
1907 | MURSHIDABAD | Murshidabad Division | SURFACE WATER BASED WATER SUPPLY SCHEME IN THE UNCOVERED ARSENIC AFFECTED AREAS OF BELDANGA-I BLOCK OF MURSHIDABAD , SM/18896 | Augmentation | Feasibility study to select a suitable location for proposed intake jetty for drawal of 23.00 MLD raw water from River Bhagirathi at Kumarpur, Beldanga-I Block. For surface water supply Scheme under Murshidabad Division in Murshidabad District. | 380-MSD/2024-25 | 18/09/2024 | 0 | SYAMA PRASAD MOOKERJEE PORT, KOLKATA | 60.66 | 0 | 0 | 0
1908 | MURSHIDABAD | Murshidabad Division | SURFACE WATER BASED WATER SUPPLY SCHEME IN THE UNCOVERED ARSENIC AFFECTED AREAS OF BELDANGA-I BLOCK OF MURSHIDABAD , SM/18896 | Augmentation | Surveying, Sub Soil investigation , Design, Engineering, Supplying, Construction, Erection, Testing, Commissioning of Raw Water Pump House over M.S Intake barge (Floating), Bank Protection, Raw Water Rising Main, Construction of 22.1 MLD capacity Water Treatment Plant based on Conventional Technologies including Administrative Building, Substation Building ,Electro- Mechanical Works , Staff quarter & other components and SCADA on EPC turnkey basis in a single package as per detail scope of work / direction by E-I-C including 3 (Three) months Trial Run and Operation & Maintenance for 1(One) year for Surface Water Based piped W/S scheme in the uncovered areas of arsenic affected Beldanga-I Block in the district of Murshidabad. | 1883/MURD | 28/06/2024 | 822 | GBC INFRASTRUCTURE PRIVATE LIMITED | 4480 | 0 | 0 | 0
1909 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Kalikapur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3612/MURD | 24/11/2023 | 60 | KUNTAL SAHA | 31.83 | 0 | 0 | 0
1910 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Srinarayanpur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3060/MURD | 29/09/2023 | 60 | DAS ENTERPRISE (SUBRATA DAS) | 32.43 | 0 | 0 | 0
1911 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Mamudpur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3121/MURD | 05/10/2023 | 60 | ASIT KUMAR ROY | 34.58 | 0 | 0 | 0
1912 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Chak Palasi village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3120/MURD | 05/10/2023 | 60 | SUJIT CHOWDHURY | 19.89 | 0 | 0 | 0
1913 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Saheb Nagar village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3080/MURD | 03/10/2023 | 60 | NOBEL CONSTRUCTION | 32.52 | 0 | 0 | 0
1914 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Durajjay Palsa village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3100/MURD | 04/10/2023 | 60 | SOUMYA KANTI SINHA | 32.21 | 0 | 0 | 0
1915 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Talbona village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3081/MURD | 03/10/2023 | 60 | ARJU CONSTRUCTION | 32.52 | 0 | 0 | 0
1916 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Padmalabhbati village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3102/MURD | 04/10/2023 | 60 | SANJAY DUTTA | 28.02 | 0 | 0 | 0
1917 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Bansbere village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3061/MURD | 29/09/2023 | 60 | AGNIBESH CHATTERJEE | 24.79 | 0 | 0 | 0
1918 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Khansama Danga village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3642/MEDB | 03/11/2023 | 92 | MASSK ENGINEERING WORKS | 6.15 | 0 | 0 | 0
1919 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Mamudpur village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3644/MEDB | 03/11/2023 | 92 | JOY BISHNU ENGINEERING CO. | 6.3 | 0 | 0 | 0
1920 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hari Nagar village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3645/MEDB | 03/11/2023 | 92 | EASTERN INDIA SALES & SERVICE | 6.27 | 0 | 0 | 0
1921 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Name of Work: Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Pachim Srikrishnapur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3647/MEDB | 03/11/2023 | 92 | ALAK KUMAR CHAKRABORTY | 6.15 | 0 | 0 | 0
1922 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chak Palasi village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3627/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0 | 0
1923 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Rasulpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3364/MURD | 31/10/2023 | 60 | SUDIPTA GHOSH | 34.01 | 0 | 0 | 0
1924 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Gopalpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3352/MURD | 30/10/2023 | 60 | M/S ATISH SINHA | 30.15 | 0 | 0 | 0
1925 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Srikrishnapur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3366/MURD | 31/10/2023 | 60 | M/S MONDAL ASSOCIATES | 32.52 | 0 | 0 | 0
1926 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Khansama Danga village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3350/MURD | 30/10/2023 | 60 | CREATIVE | 24.03 | 0 | 0 | 0
1927 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Bajitpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3351/MURD | 30/10/2023 | 60 | SOUNAK ENTERPRISE | 34.62 | 0 | 0 | 0
1928 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Talbona village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3658/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 6.3 | 0 | 0 | 0
1929 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Srinarayanpur village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3656/MEDB | 03/11/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0 | 0
1930 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Name of Work: Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Rasulpur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3653/MEDB | 03/11/2023 | 92 | SURAKSHA | 6.3 | 0 | 0 | 0
1931 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Saheb Nagar village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3654/MEDB | 03/11/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0 | 0
1932 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kalidaspur village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3637/MEDB | 03/11/2023 | 92 | DAS ENTERPRISE (CHOA) | 6.3 | 0 | 0 | 0
1933 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Pachim Kalidaspur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3638/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 6.3 | 0 | 0 | 0
1934 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Chak Gupura-Part- B village, Block:- Bharatpur-II, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3276/MURD | 17/10/2023 | 60 | FIROJ AHAMMED BISWAS | 22.09 | 0 | 0 | 0
1935 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Daspara village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3630/MEDB | 03/11/2023 | 92 | MERCURY ENGINEERING CO | 6.33 | 0 | 0 | 0
1936 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Durajjay Palsa village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3631/MEDB | 03/11/2023 | 92 | ASSOCIATED ELECTRICAL CO. | 6.3 | 0 | 0 | 0
1937 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kalikapur village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3639/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 6.3 | 0 | 0 | 0
1938 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Gopalpur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3634/MEDB | 03/11/2023 | 92 | SARKAR CONSTRUCTION | 6.3 | 0 | 0 | 0
1939 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Kalidaspur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3135/MURD | 06/10/2023 | 1117 | M/S ROY & BOSE ENTERPRISE | 34.81 | 13.37 | 38.41 | 10
1940 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Name of Work: Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Padmalabhbati village, Block- Burwan under ground water based mini piped water supply scheme, Dist- Murshidabad. under MEDB PHE Dte. | 768/MEDB | 20/02/2024 | 90 | ARINDAM MAJUMDAR | 6.14 | 0 | 0 | 0
1941 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | NEW SERVICE CONNECTION AT PH1 AT RAGHUNATHPUR PO SADAI PS KHARGRAM C ID 304439890 | 218/WBSEDCL-JJM | 13/09/2024 | 0 | WBSEDCL | 0.83 | 0 | 0 | 0
1942 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | NEW SERVICE CONNECTION AT KATIGRAM, MOUZA KATIGRAM PH 1 MOUZA GURULIA C ID 304440127 |  | 11/09/2024 | 0 | WBSEDCL | 0.55 | 0 | 0 | 0
1943 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | NEW SERVICE CONNECTION AT KATIGRAM, MOUZA KATIGRAM PH 1 PS KHARGRAM GURULIA ID 304440127 | 219/WBSEDCL-JJM | 13/09/2024 | 0 | WBSEDCL | 0.55 | 0 | 0 | 0
1944 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | NEW SERVICE CONNECTION AT SAHEBNAGAR MINI PWSS PH 1 ID 304489077 |  | 27/11/2024 | 0 | WBSEDCL | 0.67 | 0 | 0 | 0
1945 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | NEW SERVICE CONNECTION AT GANGARAMPUR, MOUZA RAHIGRAM PH 1 C ID 304440129 |  | 11/09/2024 | 0 | WBSEDCL | 0.79 | 0 | 0 | 0
1946 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | NEW SERVICE CONNECTION AT GANGARAMPUR, MOUZA RAHIGRAM PH 1 C ID 304440129 | 220/WBSEDCL-JJM | 13/09/2024 | 0 | WBSEDCL | 0.79 | 0 | 0 | 0
1947 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | NEW SERVICE CONNECTION AT PH1 AT RAGHUNATHPUR PO SADAI PS KHARGRAM C ID 304439890 |  | 11/09/2024 | 0 | WBSEDCL | 0.83 | 0 | 0 | 0
1948 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Chak Ramprasad village, Block:- Jalangi, Islampur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3082/MURD | 03/10/2023 | 60 | CHATTERJEE ENTERPRISE | 30.55 | 0 | 0 | 0
1949 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Hari Nagar village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3122/MURD | 05/10/2023 | 1033 | SANDESH CONSTRUCTION | 26.83 | 0 | 0 | 0
1950 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Daspara village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3150/MURD | 09/10/2023 | 996 | MONDAL CONSTRUCTION | 31.8 | 0 | 0 | 70
1951 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Raghunathpur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3367/MURD | 31/10/2023 | 883 | DEBEN RAJAK | 27.1 | 19.23 | 70.94 | 10
1952 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Kalidaspur village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3277/MURD | 17/10/2023 | 793 | JIYAUL HAQUE | 32.83 | 0 | 0 | 0
1953 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Gangarampur village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3368/MURD | 31/10/2023 | 793 | M/S HALDAR CONSTRUCTION (PROP:- ANIRBAN HALDAR ) | 32.52 | 0 | 0 | 90
1954 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-B , SM/18768 | New | Ground Water based mini piped water supply scheme for Katigram village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3365/MURD | 31/10/2023 | 640 | M/S. BOJLUR RAHAMAN | 26.08 | 22.29 | 85.48 | 40
1955 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18736 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 4.44 | 100 | 100
1956 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18736 | Augmentation | Material Requisition To Resource Division | 1219/MURD/20 | 03/05/2023 | 0 | Resource Division | 109.49 | 0 | 0 | 0
1957 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18736 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KUPILA Water Supply Scheme and Herampur Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 3768/MURD | 08/12/2023 | 21 | MAMATA USHA ENTERPRISE | 11.79 | 10.55 | 100 | 100
1958 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18736 | Augmentation | QUOTATION FOR SHIFTING OF 1 NO PHE 25KVA DTR AT HERAMPUR REF ID. 860310611 |  | 16/08/2024 | 0 | WBSEDCL | 7.2 | 0 | 0 | 0
1959 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18736 | Augmentation | QUOTATION FOR SHIFTING OF 1 NO PHE 25KVA DTR AT HERAMPUR REF ID. 860310611 | 197/WBSEDCL-JJM | 22/08/2024 | 0 | WBSEDCL | 7.2 | 0 | 0 | 0
1960 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18736 | Augmentation | Construction of 700 Cum OHR, Pump House, Boundary wall & Repairing of Pump House for Augmentation of Herampur Zone-I PWSS in Raninagar-I Block , Islampur Sub-Division under Murshidabad Division ,PHE.Dte._PART_B | 2647/MURD | 23/08/2023 | 819 | SATELLITE CONSTRUCTION | 257.98 | 0 | 0 | 20
1961 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18736 | Augmentation | Augmentation Work Laying Distribution System, Rising Main Connection, FHTC of Herampur Zone-I PWS in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte. (PART - A) | 3296/MURD | 20/10/2023 | 893 | J.S. CONSTRUCTION | 443.2 | 213.95 | 48.28 | 20
1962 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18736 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Islampur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | 2637/MURD | 23/09/2024 | 150 | INDRAJIT DUBEY | 8.72 | 0 | 0 | 100
1963 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HERAMPUR ZONE-I PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18736 | Augmentation | Supply of different types C.I Specials at Islampur Sub-Divisional Store for different water supply schemes under Islampur sub-Division, under Murshidabad Division, P.H.E. Dte in the District of Murshidabad. | 2674/MURD | 25/09/2024 | 242 | MAKALI ENGINEERING CORPORATION | 32.46 | 4.27 | 33.08 | 100
1964 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Ramchandrapur (Code-314219) In The Command Area Of Bansgara Ground Water Supply Scheme(Part-B) , SM/07733 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Ramchandrapur (Habitation ID-0001294189 ) in the village of Ramchandrapur (Village code 314219) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 987/BD-I | 17/12/2020 | 90 | KAMIRUL SK AND CO. | 28.26 | 0 | 0 | 0
1965 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18830 | Augmentation | Material Requisition To Resource Division | 1043/MURD/7 | 17/04/2023 | 0 | Resource Division | 84.58 | 0 | 0 | 0
1966 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18830 | Augmentation | Material Requisition To Resource Division | 1936/MURD | 18/07/2023 | 0 | Resource Division | 84.58 | 0 | 0 | 0
1967 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18830 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV ,Zone-I under MAHALANDI ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | 583/MEDB | 31/01/2024 | 336 | CONCORD ENGINEERING | 48.03 | 0 | 0 | 40
1968 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18830 | Augmentation | Construction of Boundary Wall & Pump House with sanitary & plumbing work (H.W & 4th T/W Site) of Mahalandi (Zone-I) Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | 2088/MURD | 23/07/2024 | 60 | AHAMMED ENTERPRISE | 21.22 | 0 | 0 | 0
1969 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18830 | Augmentation | CONSTRUCTION OF ROAD FROM GOKARNA TO ASOLAMPUR, PACKAGE NO- WB-13 -365, LENG- 10.215 KM , BLOCK KANDI, IN THE DIST MUSHIDABAD | 403-MSD/2024-25 | 23/09/2024 | 0 | EXECUTIVE ENGINER WBSRDA MURSHIDABAD DIVISION | 5.19 | 0 | 0 | 0
1970 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18830 | Augmentation | AT MAHALANDI PH 3 ID 304239410 | 371/WBSEDCL-JJM | 21/02/2024 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
1971 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18830 | Augmentation | NEW SER VICE CONNECTION AT MAHALANDI PH 3 ID 304239410 |  | 16/02/2024 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
1972 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18830 | Augmentation | Laying of Distribution System (Part-A), Construction of Over Head Reservoir (400 Cum), Pump House (3rd Site), Boundary wall (3rd Site), Repairing of Pump House & Boundary wall (H.W & 2nd Site), Repairing of Over Head Reservoir (250 Cum) and accommodate FHTC work at Mahalandi Village (Village Code-315231) for Augmentation of MAHALANDI (ZONE-I) Water Supply Scheme of Kandi Block under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | 3014/MURD | 26/09/2023 | 1132 | PREKSHITA CONSTRUCTION | 248.32 | 12.19 | 4.91 | 10
1973 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18830 | Augmentation | Laying of Distribution System (Part-B) and FHTC work at Mahalandi Village (Village Code-315231) & Durlabhpur Village (Village Code-315218) for Augmentation of MAHALANDI (ZONE-I) Water Supply Scheme in Kandi Block under Murshidabad Division, P.H.E.Dte. | 3052/MURD | 29/09/2023 | 1053 | PRIYANKA CONSTRUCTION | 286.61 | 44.8 | 15.63 | 20
1974 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- I Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18830 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well, 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone - I , Mahalandi Zone - II & Bhalkundi Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 1758/MURD | 06/07/2023 | 576 | R.K. DRILLING SERVICES | 23.58 | 0 | 0 | 70
1975 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar , SM/12579 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of DAKSHIN HANUMANTNAGAR ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | 3767/MEDB | 03/11/2023 | 92 | ASSOCIATED ELECTRICAL CO. | 11.19 | 9.3 | 83.1 | 10
1976 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar , SM/12579 | Augmentation | Material Requisition To Resource Division | 196/BD-I/10 | 09/02/2024 | 0 | Resource Division | 102.96 | 0 | 0 | 0
1977 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar , SM/12579 | Augmentation | Augmentation of DAKSHIN HANUMANTANAGAR Piped water supply scheme to accommodate construction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 744/BD-I | 17/08/2023 | 1059 | M/S SINHA & SONS | 478.03 | 0 | 0 | 45
1978 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar , SM/12579 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DAKSHIN HANUMANTANAGAR Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 261/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.77 | 2.77 | 100 | 100
1979 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar , SM/12579 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Dakshin Hanumantanagar ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | 1359/BD-I | 21/12/2022 | 30 | PRANAB KUMAR GHOSH | 3.8 | 2.19 | 100 | 72
1980 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar , SM/12579 | Augmentation | Repair And Renovation Works Of OHR (450 Cum) forDakshinHanumantanagar water supply scheme of Bhagwangola-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 1028/BD-I | 01/11/2023 | 30 | SANTANU BISWAS | 9.48 | 0 | 0 | 100
1981 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . , SM/14736 | Augmentation | Material Requisition To Resource Division | 61/BD-1/10 | 27/04/2023 | 0 | Resource Division | 30.97 | 0 | 0 | 0
1982 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . , SM/14736 | Augmentation | Material Requisition To Resource Division | 201/BD-1/22 | 10/02/2024 | 0 | Resource Division | 83.89 | 0 | 0 | 0
1983 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . , SM/14736 | Augmentation | NEW SERVICE CONNECTION AT BANSGARA Z1 PH 1 ID 304268983 |  | 26/11/2024 | 0 | WBSEDCL | 11.36 | 0 | 0 | 0
1984 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . , SM/14736 | Augmentation | Augmentation of BANSGARA ZONE-I Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 628/BD-I | 04/08/2023 | 310 | SUNIL RABI DAS | 388.8 | 242.14 | 62.28 | 10
1985 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . , SM/14736 | Augmentation | Repair And Renovation Works Of OHR (100 Cum) of Ground Water Based Supply Scheme for Bansgara Zone-I of Raninagar-II block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | 1032/BD-I | 01/11/2023 | 30 | ALOK BANERJEE ENTERPRISE | 6.83 | 4.46 | 65.31 | 80
1986 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . , SM/14736 | Augmentation | Construction of Service Road for approach and Pump House at Augmentation of Bansgara Zone-I PWSS of Raninagar-II Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | 1068/BD-I | 03/07/2024 | 300 | MAHATO ENTERPRISE | 9 | 0 | 0 | 75
1987 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . , SM/14736 | Augmentation | BANSGARA ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1245/BD-I | 30/07/2024 | 180 | M.K.CONSTRUCTION | 22.29 | 0 | 0 | 30
1988 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . , SM/14736 | Augmentation | Construction of Service Road & extension of boundary wall of Bansgara Zone-I PWSS under Jal Jeevan Mission within Raninagar-II block under Berhampore Division-I PHE Dte. in the district of Murshidabad. | 843/BD-I | 23/06/2025 | 45 | SUBHRANIL DAS | 17.81 | 0 | 0 | 0
1989 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . , SM/14736 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1687/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.73 | 2.76 | 100 | 1
1990 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- I . , SM/14736 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA ZONE-I Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte | 1759/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.6 | 2.6 | 100 | 100
1991 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. , SM/18603 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMPARA FORIDPUR Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 720/BD-I | 14/08/2023 | 10 | TECHVISION | 2.81 | 2.81 | 100 | 100
1992 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. , SM/18603 | Augmentation | Material Requisition To Resource Division | 201/BD-1/8 | 10/02/2024 | 0 | Resource Division | 36.69 | 0 | 0 | 0
1993 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. , SM/18603 | Augmentation | NEW CONNECTION AT RAMPARA FARIDPUR PH-1 | 182/WBSEDCL-JJM | 09/08/2024 | 0 | WBSEDCL | 3.66 | 0 | 0 | 0
1994 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. , SM/18603 | Augmentation | Augmentation of Rampara Faridpur Piped water supply scheme to accommodate construction of OHR ,Arsenic cum Iron Removal Plant(AIRP) and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga -II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1017/BD-I | 31/10/2023 | 793 | SANJAY BISWAS | 558.97 | 10.45 | 1.87 | 65
1995 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. , SM/18603 | Augmentation | RAMPARA FARIDPUR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 460/BD-I | 15/03/2024 | 480 | SAHA CONSTRUCTION | 22.63 | 0 | 0 | 75
1996 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. , SM/18603 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Rampara Faridpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte | 2249/BD-I | 10/12/2024 | 30 | M/S B.R. SUPPLIERS | 9 | 0 | 0 | 0
1997 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. , SM/18603 | Augmentation | RAMPARA FARIDPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, under Jal Jeevan Mission within BELDANGA-II Block in the district of Murshidabad under Berhampore Division-I, PHE.Dte. | 444/BD-I | 20/03/2025 | 45 | DATA ENTERPRISE | 9.84 | 0 | 0 | 0
1998 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. , SM/18603 | Augmentation | Improvement of Existing AIRP (Capacity 68 Cum/hr.) with allied work at Rampara Faridpur (Zone-I) Water Supply Scheme under Jal Jeevan Mission within Beldanga - II under Berhampore Division-I, P.H.Engineering Dte. In the district of Murshidabad. | 759/BD-I | 22/05/2025 | 30 | SANJAY BISWAS | 27.45 | 0 | 0 | 0
1999 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. , SM/18603 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of RAMPARA FARIDPUR ZONE - II PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 638/BD-I | 25/04/2025 | 60 | MASTER CONSTRUCTION | 18.98 | 0 | 0 | 0
2000 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMPARA FARIDPUR PIPED WATER SUPPLY SCHEME. , SM/18603 | Augmentation | Improvement of existing Pump House & Construction of New Boundary Wall (2nd Site) for Augmentation of Rampara Faridpur PWSS within Beldanga-II under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad | 1111/BD-I | 10/07/2024 | 60 | ABA CONTRACTOR | 12.06 | 3.18 | 20.94 | 100
2001 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. , SM/18700 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under Islampur ground water based water supply scheme under Block_ Raninagar-I Dist. - Murshidabad under MEDB, PHE Dte. | 3708/MEDB | 03/11/2023 | 92 | R.M.D TRADING | 34.48 | 0 | 0 | 0
2002 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. , SM/18700 | Augmentation | Augmentation of Islampur PWSS Repairing of Boundary Wall, Pump House & Existing OHR, Construction of 900 Cum OHR, P.H, B.W in Raninagar-I Block , under Murshidabad Division , PHE.Dte.PART_B | 2673/MURD | 24/08/2023 | 365 | M/S. UDYOG AND CO | 335.68 | 0 | 0 | 0
2003 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. , SM/18700 | Augmentation | Material Requisition To Resource Division | 1219/MURD/07 | 03/05/2023 | 0 | Resource Division | 551.66 | 0 | 0 | 0
2004 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. , SM/18700 | Augmentation | Augmentation of Ground Water Based Islampur PWSS of accommodate Providing Functional Household Tap Connection (1394 Nos) in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte.PART_C | 2669/MURD | 24/08/2023 | 90 | M/S B.M. INDUSTRIES | 182.87 | 36.65 | 20.04 | 31
2005 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. , SM/18700 | Augmentation | Engagement of Consultant for Field Data collection, pipeline network analysis by analyzing actual household demand in pipeline sections, identification of low pressure areas with in the pipe network system and proposing probable solution of the same in 2(Two) nos water supply schemes in Murshidabad Division P.H.E. Dte. | 2022/MURD | 11/07/2024 | 345 | DHPE | 15.34 | 0 | 0 | 25
2006 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. , SM/18700 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Domkol & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Kupila Water Supply Scheme, Bilaspur Water Supply Scheme, Garaimari Water Supply Scheme, Islampur Water Supply Scheme. (Annexure-II) | 1925/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 9.6 | 1.96 | 50 | 100
2007 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. , SM/18700 | Augmentation | LOAD ENHANCEMENT ISLAMPUR APPLICATION NO.3004629164 | 13/WBSEDCL-JJM | 16/04/2024 | 0 | WBSEDCL | 0.28 | 0 | 0 | 0
2008 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. , SM/18700 | Augmentation | Restoretion of Road State Highway at Najairpur to Islampore Road from chainge 0.00 kmp to 1.350 km shoulder damage amounting to Rs 637462.00 and Akheriganj to Katlamari road from chainge 8.00 km to 9.30 km. | 492-MSD/2024-25 | 04/10/2024 | 0 | EXECUTIVE ENGINEER , MURSHIDABAD HIGHWAY DIVISION -I, PWD (ROADS) DIRECT. GOV OF W.B | 34.8 | 0 | 0 | 0
2009 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. , SM/18700 | Augmentation | Augmentation of Ground Water Based Islampur PWSS Laying Distribution System, Laying Rising Main in Raninagar - I Block within Murshidabad District under Murshidabad Division, PHE Dte. PART_A | 2465/MURD | 09/08/2023 | 719 | M/S GUHA AND ROY | 333.65 | 110.8 | 33.21 | 25
2010 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. , SM/18700 | Augmentation | Supply of different types C.I Specials at Islampur Sub-Divisional Store for different water supply schemes under Islampur sub-Division, under Murshidabad Division, P.H.E. Dte in the District of Murshidabad. | 2674/MURD | 25/09/2024 | 242 | MAKALI ENGINEERING CORPORATION | 32.46 | 8.07 | 50 | 100
2011 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF ISLAMPUR PIPED WATER SUPPLY SCHEME. , SM/18700 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gaysabad, Kagram, Ranagram, Augmentation of Islampur & Augmentation of Shibnagar Laskarpur Zone - II Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | 661/MURD | 19/03/2025 | 170 | M/S GUHA AND ROY | 35.27 | 0 | 0 | 100
2012 | MURSHIDABAD | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Satitara Block - Burwan, Dist- Murshidabad. , SM/18701 | Augmentation | Demolition of damaged R.C.C. Elevated Reservoir (Capacity 2,72,400 Ltr) at Satitara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 3874/MURD | 18/12/2023 | 30 | DIPAYAN DEY | 5.35 | 5.35 | 100 | 100
2013 | MURSHIDABAD | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Satitara Block - Burwan, Dist- Murshidabad. , SM/18701 | Augmentation | Material Requisition To Resource Division | MURD/439/05 | 08/02/2024 | 0 | Resource Division | 4.1 | 0 | 0 | 0
2014 | MURSHIDABAD | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Satitara Block - Burwan, Dist- Murshidabad. , SM/18701 | Augmentation | Augmentation of SATITARA under Jal Jeevan Mission of BURWAN Block, Kandi Sub Division, Murshidabad District under Murshidabad Division, PHE Dte. | 3291/MURD | 19/10/2023 | 713 | M/S. S. DAS AND ENTERPRISE | 1459.34 | 357.09 | 24.47 | 10
2015 | MURSHIDABAD | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Satitara Block - Burwan, Dist- Murshidabad. , SM/18701 | Augmentation | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Satitara T.W- IV,V,VI, Fatepur T.W.-II, Kapasdanga T.W-II Water Supply Scheme of Burwan Block under Kandi Sub- Division, Murshidabad Division, P.H.Engineering Dte. | 664/MURD | 19/03/2025 | 65 | NADIA TUBEWELLS | 70.43 | 0 | 0 | 0
2016 | MURSHIDABAD | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Satitara Block - Burwan, Dist- Murshidabad. , SM/18701 | Augmentation | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS SATITARA PWSS Scheme, Block- KANDI to be Augmentation/Rejuvination under Murshidabad Division P.H.E.Dte. | 3260/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 9.19 | 8.96 | 100 | 100
2017 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Illampur Village (Code-314175) In The Command Area Of Maiya Ground Water Supply Scheme (Part-B) Under Lalgola Block In Murshidaba , SM/07784 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ilimpur (Village code 314175) under Maia Ground Water Supply Scheme of Lalgola Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 239/BD-I | 10/02/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 66.88 | 122.7 | 183.46 | 10
2018 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Illampur Village (Code-314175) In The Command Area Of Maiya Ground Water Supply Scheme (Part-B) Under Lalgola Block In Murshidaba , SM/07784 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Illampur Village (Code-314175) In The Command Area Of Maiya Ground Water Supply Scheme (Part-B) Under Lalgola Block In Murshidabad District" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1436/BD-I | 04/09/2024 | 30 | DAS CONSTRUCTION 13/1/2 UKILABAD ROAD, BERHAMPORE | 15.6 | 0 | 0 | 0
2019 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kazipara Village (Code-314608) Under Command Area Of Kazipara Ground Water Supply Scheme (Part-B) , SM/07700 | Retrofitting | Material Requisition To Resource Division | 143/BD-I | 10/02/2022 | 0 | Resource Division | 13.51 | 0 | 0 | 0
2020 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kazipara Village (Code-314608) Under Command Area Of Kazipara Ground Water Supply Scheme (Part-B) , SM/07700 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kazipara (Village code 314608) under Kazipara Water Supply Scheme of Jalangi Block and village of Ramnagar Doemkanun (Village code 314578) under Ramnagar Doemkanun Water Supply Scheme of Raninagar-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. | 49/BD-I | 27/01/2022 | 180 | M/S S.DAS & ENTERPRISE | 337.04 | 0 | 0 | 1
2021 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kazipara Village (Code-314608) Under Command Area Of Kazipara Ground Water Supply Scheme (Part-B) , SM/07700 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Kazipara Village (Code-314608) Under Command Area Of Kazipara Ground Water Supply Scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1228/BD-I | 29/07/2024 | 60 | M/S S. DAS & ENTERPRISE | 74.15 | 0 | 0 | 0
2022 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sabdalpur ( 314704 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II , SM/07915 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Jal Swapna (JJM) of mouza Sabdalpur ( 314704 ) under Shibnagar Laskarpur Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad Division. PHE DTE.(SCHEME ID : 0001723328) TENDER NO 89 OF 20-21 BY SE / MC | 09 - MSD/21-22 | 04/08/2021 | 0 | M/S. GOUTAM CHAKRABORTY | 38.65 | 0 | 0 | 0
2023 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sabdalpur ( 314704 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II , SM/07915 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sabdalpur (Village code 314704) under Shibnagar Laskarpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723328 in the District of Murshidabad. (Sl No-20) | 218-MSD/22-23 | 27/07/2022 | 0 | M/S. GOUTAM CHAKRABORTY | 26.57 | 0 | 0 | 0
2024 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Udaynagar Diar ground water supply scheme , SM/07224 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Udaynagar Diar (Village code 314613) under Udaynagar Diar Ground Water based Water Supply Scheme for Jalangi Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 918/BD-I | 10/12/2020 | 90 | M/S S.DAS & ENTERPRISE | 34.84 | 39.5 | 113.36 | 0
2025 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Udaynagar Diar ground water supply scheme , SM/07224 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Azimpur (Village code 314612) under Udaynagar Diar Ground Water based Water Supply Scheme for Jalangi Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-09 of 2020 - 2021,SL-01). | 73 /BD-I | 19/01/2021 | 20 | M/S ROY & BOSE ENTERPRISE | 7.67 | 6.18 | 80.58 | 0
2026 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area Jumra Nayagram (VillageCode-314190) in Jumra Nayagram ground water supply scheme (Part-A) , SM/06973 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL JEEVAN MISSION under command area Jumra Nayagram (VillageCode-314190) in Jumra Nayagram ground water supply scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 2196/BD-I | 02/12/2024 | 15 | MAHAMAYA ENTERPRISE | 1.95 | 0 | 0 | 0
2027 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area Jumra Nayagram (VillageCode-314190) in Jumra Nayagram ground water supply scheme (Part-A) , SM/06973 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jumra Nayagram (Village code 314190) under Jumra Nayagram Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 966/BD-I | 17/12/2020 | 90 | MODERN CONSTRUCTION | 43.07 | 78.14 | 195 | 1
2028 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area Jumra Nayagram (VillageCode-314190) in Jumra Nayagram ground water supply scheme (Part-A) , SM/06973 | Retrofitting | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jumra Nayagram (Village Code-314190) and others under Jumra Nayagram Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | 917/BD-I | 19/05/2021 | 20 | MODERN CONSTRUCTION | 4.63 | 0 | 0 | 0
2029 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-I ground water supply scheme , SM/06984 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Daulatpur (Village code 314749) under Hurshi Zone-I Ground Water Supply Scheme in Raninagar-I Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-11) | 1143/BD-I | 07/07/2021 | 180 | KAMIRUL SK AND CO. | 71.98 | 20.6 | 28.62 | 0
2030 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-I ground water supply scheme , SM/06984 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Hurshi zone-I ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte | 2089/BD-I | 22/11/2024 | 30 | REDSEA CONSTRUCTION | 3.79 | 0 | 0 | 0
2031 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-I ground water supply scheme , SM/06984 | Retrofitting | Additional Laying works at village BEGAMPUR (village code 314750) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Hurshi Zone-I Ground water supply scheme (Raninagar-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 1920/BD-I | 08/10/2021 | 10 | M/S SAJAHAN CHOWDHURY | 5.99 | 4.59 | 100 | 1
2032 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hurshi zone-I ground water supply scheme , SM/06984 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Begampur (Village code 314750) under Hurshi Zone-I Ground Water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 69/BD-I | 18/01/2021 | 20 | M/S SAJAHAN CHOWDHURY | 17.92 | 13.45 | 100 | 75
2033 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilashpur (314681) of Bilashpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) , SM/07274 | Retrofitting | LAYING OF UPVC PIPELINE FOR DIST SYSTEM...VULNERABLE POINT OF GOPAL NAGAR PRY.. SCHOOL.. UNDER DEULI OHR, RAGHUNATHGANJ SURFACE WSS, TNO- 072/20-21/EE | 479/W | 12/03/2021 | 0 | DEBASIS BOSE | 3.2 | 0 | 0 | 0
2034 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilashpur (314681) of Bilashpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) , SM/07274 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --BHALKUNDI-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- SAMANDI , CODE-315122, TNO- 573/2020-21/EE | 473/W | 08/03/2021 | 0 | APURBA SAHA CHOWDHURY | 16.4 | 0 | 0 | 0
2035 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilashpur (314681) of Bilashpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) , SM/07274 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of ---BHALKUNDI--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE - MATAI CODE- 315090 , TNO- 625/20-21/EE | 479/W | 12/03/2021 | 0 | M/S UNIQUE BUILDERS | 11.41 | 0 | 0 | 0
2036 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilashpur (314681) of Bilashpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) , SM/07274 | Retrofitting | LAND DEVELOPMENT AT HW SITE OF MAHALANDI Z-II WSS, TNO- 551/20-21/EE | 479/W | 12/03/2021 | 0 | APURBA SAHA CHOWDHURY | 4.76 | 0 | 0 | 0
2037 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilashpur (314681) of Bilashpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) , SM/07274 | Retrofitting | SANITARY & PLUMBING ARRANGEMENT....HW SITE OF BAHARA WSS, TNO- 06/20-21/AE-KSD | 479/W | 12/03/2021 | 0 | AYAN ENTERPRISE | 1.19 | 0 | 0 | 0
2038 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilashpur (314681) of Bilashpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) , SM/07274 | Retrofitting | HIRING OF CAR BILL FOR AE-ISD, W/O NO- 200/ISD, DT- 25/09/2020 | 479/W | 12/03/2021 | 0 | MADAN MOHAN SASMAL | 0.77 | 0 | 0 | 0
2039 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilashpur (314681) of Bilashpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) , SM/07274 | Retrofitting | Protection of Head work site premises by raising Boundary wall height by R.B.T fencing with Approach Road under Bilashpur Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. | 44/ISD | 28/01/2022 | 30 | PARUL ELECTRICAL INSTALLER | 3.95 | 3.86 | 100 | 1
2040 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilashpur (314681) of Bilashpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) , SM/07274 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bilaspur (Village code 314681 ) under Bilaspur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723482 (Sl No-05) | 3334/MURD | 07/10/2021 | 1354 | SUDIPA SINGHA ROY | 60.39 | 53.01 | 91.07 | 50
2041 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Naudaparavillage (Code-314456) In The Command Area Of Paschim Rampur Ground Water Supply Scheme (Part-B) , SM/07727 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naodapara(Village code 314456) under Paschim Rampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | 169/BD-I | 03/02/2021 | 20 | M/S SINHA & SONS | 38.69 | 29.48 | 76.2 | 1
2042 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Naudaparavillage (Code-314456) In The Command Area Of Paschim Rampur Ground Water Supply Scheme (Part-B) , SM/07727 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Naudaparavillage (Code-314456) In The Command Area Of Paschim Rampur Ground Water Supply Scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1439/BD-I | 04/09/2024 | 30 | KUNTAL SAHA | 10.13 | 0 | 0 | 0
2043 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Lakshminathpur (314696) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) , SM/07290 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --AMARKUNDU-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- RAINDA , CODE- 315025, TNO- 684/2020-21/EE | 512/W | 30/03/2021 | 0 | SAMAR MUKHERJEE | 21.62 | 0 | 0 | 0
2044 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Lakshminathpur (314696) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) , SM/07290 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SARBANGAPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- PARESNATHPUR , CODE-315529, TNO- 604/2020-21/EE | 512/W | 30/03/2021 | 0 | RATAN DUTTA | 25.78 | 0 | 0 | 0
2045 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Lakshminathpur (314696) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) , SM/07290 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Lakshminathpur (Village code 314696) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. (Sl No-01) | 2500/MURD | 17/08/2021 | 120 | SUJIT KUMAR SAHA | 65.1 | 64.44 | 98.98 | 0
2046 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Lakshminathpur (314696) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-I) , SM/07290 | Retrofitting | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 329 in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Lakshminathpur (Village code 314696) under Domkal Ground water based water supply scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005184127). | 693/MURD | 14/03/2022 | 30 | SUJIT KUMAR SAHA | 19.11 | 0 | 0 | 1
2047 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Domkal, Kalabaria (314695 & 314662) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part , SM/07293 | Retrofitting | Additional works for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Kalabaria ( Village Code -314662) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0005184127) | 1932/MURD | 22/07/2021 | 60 | N. H. ENTERPRISE (PROP. NAJMUL HOQUE) | 13.35 | 13.24 | 100 | 0
2048 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Domkal, Kalabaria (314695 & 314662) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part , SM/07293 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village DOMKAL (Village Code-314695) under DOMKAL Ground based Water Supply Scheme for Aesenic Affected area of Domkal Block under Murshidabad District under Murshidabad Division, PHE Dte. (Scheme Id 0005184127) in the dist of MSD. | 28-MSD / 21-22 | 25/08/2021 | 0 | ARINDAM MAJUMDAR | 14.32 | 0 | 0 | 0
2049 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Domkal, Kalabaria (314695 & 314662) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part , SM/07293 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BARABIL RAGHUNAR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 87 /2020-21/SE-MC | 512/W | 30/03/2021 | 0 | MITRA CONSTRUCTION | 55.47 | 0 | 0 | 0
2050 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Domkal, Kalabaria (314695 & 314662) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part , SM/07293 | Retrofitting | Balanced and Allied Works for Providing Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Domkol (Village code 314695) under Domkol Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184127 in the District of Murshidabad. | 309/MURD | 07/02/2022 | 60 | ARINDAM MAJUMDAR | 35.08 | 14.06 | 40.08 | 0
2051 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Domkal, Kalabaria (314695 & 314662) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part , SM/07293 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village KALABARIA (Village Code 314662) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad. | 2572/MURD | 01/10/2020 | 45 | NATIONAL ENTERPRISE | 20.28 | 0 | 0 | 0
2052 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur , SM/07664 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Firojpur (Village code 314774) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. | 92 /MURD | 08/01/2021 | 60 | DEBEN RAJAK | 5.58 | 4.68 | 83.75 | 1
2053 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur , SM/07664 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mision (JJM) from existing distribution system within the command area of Village ICHHABPUR (Village Code- 314777) under AZMATPUR Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - I Block under Murshidabad District under Murshidabad Division, PHE Dte. Scheme id - 0005019112. Tender no- 797 of 20-21 by EE / MURD | 14-MSD / 21-22 | 06/08/2021 | 0 | NOBEL CONSTRUCTION | 4.66 | 0 | 0 | 0
2054 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur , SM/07664 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village NATKULI (Village Code 314779) under AZMATPUR Ground Water Based Water Supply Scheme for arsenic affected areas of RANINAGAR-I Block in the District of Murshidabad. Tender no - 941 of 20-21 by EE MURD | 422-MSD/21-22 | 23/03/2022 | 0 | PAL TROCKNER (P) LTD. | 20.51 | 0 | 0 | 0
2055 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur , SM/07664 | Retrofitting | Extension of Distribution UPVC pipeline and allied works for providing balance Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of mouzaAzmatpur ( Village Code -314776) of Azmatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme I.D.- 0005019112). (PART-II) | 277/ISD | 27/06/2022 | 30 | JAYANTA KUMAR ROY | 4.72 | 4.05 | 100 | 1
2056 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur , SM/07664 | Retrofitting | Extension of Distribution UPVC pipeline and allied works for providing balance Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of mouzaAzmatpur ( Village Code -314776) of Azmatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme I.D.- 0005019112). (PART-I) | 276/ISD | 27/06/2022 | 30 | ROY CONSTRUCTION (PROP:AVIJIT ROY) | 4.75 | 4.17 | 100 | 1
2057 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur , SM/07664 | Retrofitting | Laying of distribution system pipe line and connection with street stand post and Construction of soak well in connection with Dengue control for different Anganwadi Centres under Nowda Development Block 1 Chandpur kuthipara 2. Kulaichandi 3. Rathtalapara 4. Goghata uttarpara 5. Ghoghata ghatpara 6. Ghoghata halderpara 7.Chandpur Halderpara 8.Chandpur dey biswaspara. under Berhampore Sub division. P.H.E.Dte. | 3202/MURD | 18/12/2020 | 15 | PRANAB KUMAR GHOSH | 4.87 | 4.24 | 100 | 1
2058 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur , SM/07664 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ichhabpur (Village code 314777) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005019112 in the District of Murshidabad. | 326/MURD | 28/01/2021 | 60 | NOBEL CONSTRUCTION | 6.11 | 0 | 0 | 0
2059 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur , SM/07664 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Raosannagar (Village code 314771) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. | 91./MURD | 08/01/2021 | 60 | AJAY MONDAL | 9.01 | 0 | 0 | 0
2060 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur , SM/07664 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village Char Hulaspur (Village code 314770) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. | 90./MURD | 08/01/2021 | 60 | SAMRAT MAZUMDER | 6.96 | 0 | 0 | 0
2061 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur , SM/07664 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Natkuli (Village code 314779) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. | 3230/MURD | 22/12/2020 | 60 | PAL TROCKNER (P) LTD. | 24.64 | 0 | 0 | 1
2062 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur , SM/07664 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Firojpur (Village code 314774) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. | 92/MURD | 08/01/2021 | 60 | DEBEN RAJAK | 5.58 | 0 | 0 | 1
2063 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur , SM/07664 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandpur (Village code 314772) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. | 89/MURD | 08/01/2021 | 60 | HARUN ALL RASHID & BROTHERS | 7.25 | 0 | 0 | 0
2064 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Hulaspur, Raosannagar, Chandpur, Paharpur, Firojpur, Ichhabpur, Natkuli, Azmatpur (314770, 314771, 314772, 314773, 314774, 314777,314779 & 314776) of Azmatpur , SM/07664 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village Paharpur (Village code 314773) under Azmatpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005019112 in the District of Murshidabad. | 3231/MURD | 22/12/2020 | 60 | PAL TROCKNER PVT. LTD. | 33.51 | 0 | 0 | 0
2065 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of , SM/07674 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bachhara ( Village Code -315653) under Bachhara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga_II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | 1571/MURD | 25/06/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 68.02 | 56.21 | 82.64 | 1
2066 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of , SM/07674 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Mohammadpur ( Village Code -315650) under Bachhara Ground WaterBased Water Supply Scheme for Arsenic Affected Areas of Beldanga_II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | 1569 /MURD | 25/06/2021 | 60 | M/S GUHA & ROY ENTERPRISE | 43.43 | 20.21 | 46.52 | 1
2067 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of , SM/07674 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bidupara ( Village Code -315659) under Bachhara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | 1568/MURD | 25/06/2021 | 60 | M/S GUHA & ROY ENTERPRISE | 36.04 | 71.85 | 200 | 1
2068 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of , SM/07674 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RAMNAGAR BACHHARA G.P. under Murshidabad Division, P.H.E.Dte. | 343/BSD | 27/08/2021 | 30 | M/S. S. DAS AND ENTERPRISE | 4.16 | 4.16 | 100 | 1
2069 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of , SM/07674 | Retrofitting | Laying of 110 mm dia UPVC pipeline in connection providing FHTC in connection with JJM and JS under command area of vilage of Ramnagar (Village code 315658) under Bachhara W/S Scheme in MSD PH DTE. Tender no - 185 of 21-22 by AE BSD | 17-MSD/22-23 | 21/04/2022 | 0 | SUMAN CHOWDHURY | 4.83 | 0 | 0 | 0
2070 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of , SM/07674 | Retrofitting | Laying of different dia 75 mm and 90mm dia UPVC pipeline in connection providing FHTC in connection with JJM and JS under command area of vilage of Ramnagar (Village code 315658) under Bachhara W/S Scheme in MSD PH DTE. Tender no - 186 of 21-22 by AE BSD | 18-MSD/22-23 | 21/04/2022 | 0 | SUMAN CHOWDHURY | 4.84 | 0 | 0 | 0
2071 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of , SM/07674 | Retrofitting | Additional work of providing Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BIDUPARA (Village Code 315659) under BACHHARA Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block in the District of Murshidabad. Tender no - 344 of 21-22 by EE MURD | 365-MSD/21-22 | 12/03/2022 | 0 | MITHUN ROY | 26.44 | 0 | 0 | 0
2072 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of , SM/07674 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BACHHARA (Village Code 315653) under BACHHARA Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block in the District of Murshidabad. Tender no - 342 of 21-22 by EE MURD | 151-MSD/22-23 | 11/05/2022 | 0 | SWAPAN DAS | 39.79 | 0 | 0 | 0
2073 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of , SM/07674 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village RAMNAGAR HABITATION (Village Code 315658) under BACHHARA Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block in the District of Murshidabad. Tender no - 274 of 21-22 by EE MURD | 361-MSD/21-22 | 11/03/2022 | 0 | M/S. CHOWDHURY CONSTRUCTION | 14.54 | 0 | 0 | 0
2074 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of , SM/07674 | Retrofitting | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar (village code 315658) under Bachhara Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 92/BSD | 07/03/2022 | 15 | SUMAN CHOWDHURY | 4.83 | 0 | 0 | 0
2075 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of , SM/07674 | Retrofitting | Laying of different dia (75mm & 90mm) UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar (village code 315658) under Bachhara Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 93/BSD | 07/03/2022 | 15 | SUMAN CHOWDHURY | 4.85 | 0 | 0 | 0
2076 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of , SM/07674 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | 300/BSD | 13/08/2021 | 30 | IMAGIN | 4.34 | 8.68 | 200 | 0
2077 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bachhara, Ramnagar, Bidupara, Mahammadpur (315653, 315658, 315659 & 315650) of Bachhara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of , SM/07674 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Ramnagar ( Village Code -315658) under Bachhara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga_II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | 1562/MURD | 24/06/2021 | 60 | M/S. CHOWDHURY CONSTRUCTION | 41.52 | 26.92 | 64.85 | 1
2078 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kamnagar Village (Code-315621), Saharbati Village (Code-315625) Under Command Area Of Charkamnagar Ground Water Supply Scheme (Pa , SM/07695 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Kamnagar Village (Code-315621), Saharbati Village (Code-315625) Under Command Area Of Charkamnagar Ground Water Supply Scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1226/BD-I | 29/07/2024 | 60 | SARKAR BROTHERS | 12.07 | 0 | 0 | 0
2079 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kamnagar Village (Code-315621), Saharbati Village (Code-315625) Under Command Area Of Charkamnagar Ground Water Supply Scheme (Pa , SM/07695 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kamnagar (Village code 315621),Saharbati (Village code 315624) under Charkamnagar Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | 194/BD-I | 04/02/2021 | 30 | RAJ KUMAR MONDAL | 98.71 | 98.1 | 100 | 97
2080 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kamnagar Village (Code-315621), Saharbati Village (Code-315625) Under Command Area Of Charkamnagar Ground Water Supply Scheme (Pa , SM/07695 | Retrofitting | Additional Laying works at village Saharbati of Kamnagar G.P to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Charkamnagar Ground water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 2291/BD-I | 28/12/2021 | 10 | RAJ KUMAR MONDAL | 7.63 | 7.61 | 100 | 1
2081 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Jhaudanga (Code-314195) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-B) , SM/07716 | Retrofitting | Additional Laying works at village Jhau Danga to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Rajarampur Ground water supply scheme (Lalgola,,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | 1921/BD-I | 08/10/2021 | 10 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 0.6 | 0.6 | 100 | 1
2082 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Jhaudanga (Code-314195) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-B) , SM/07716 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhau Danga (Village code 314195), under Rajarampur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-B) | 186/BD-I | 04/02/2021 | 20 | S. K. ENTERPRISE | 8.41 | 15.57 | 194.25 | 1
2083 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Gobindotala Village (Code-314454), Paschim Rampur (Code-314455) In The Command Area Of Paschim Rampur Ground Water Supply Scheme , SM/07783 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gobindotala(Village code 314454) ,Paschim Rampur(Village code 314455) under Paschim Rampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 164/BD-I | 03/02/2021 | 30 | M/S SINHA & SONS | 70.39 | 66.78 | 100 | 100
2084 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) , SM/07680 | Retrofitting | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS MITHIPUR PWSS Scheme, Block-RAGHUNATHGAUNGE-II to be Augmention/Rejuvination under Murshidabad Division, P.H.E. Dte. | 3252/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.65 | 11.29 | 200 | 1
2085 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) , SM/07680 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of MITHIPUR (Village code 314136) under MITHIPUR Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005186173 | 3974/MURD | 21/12/2021 | 180 | M/S. SINHA & SONS | 108.7 | 0 | 0 | 0
2086 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) , SM/07680 | Retrofitting | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KASIADANGA ZONE-II PWSS Scheme, Block - Raghunathganj-II to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 420 of 21-22 by EE MURD | 301-MSD/21-22 | 07/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.65 | 0 | 0 | 0
2087 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) , SM/07680 | Retrofitting | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KASIADANGA ZONE-II PWSS Scheme, Block - Raghunathganj-II to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 419 of 21-22 by EE MURD | 301-MSD/21-22 | 07/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.54 | 0 | 0 | 0
2088 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) , SM/07680 | Retrofitting | HIRING OF CAR FOR JANGIPUR SUB DIVISION, PHE DTE. |  | 09/12/2022 | 0 | MADAN MOHAN SASMAL | 0.42 | 0 | 0 | 0
2089 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) , SM/07680 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Barala (Village code 314009) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-9) | 48/MURD | 06/01/2021 | 180 | M/S UNIVERSAL TRADING | 63.12 | 14.5 | 100 | 100
2090 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mithipur (314136) of Mithipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block of Murshidabad District (PART-I) , SM/07680 | Retrofitting | Material Requisition To Resource Division | 540/12/MURD | 25/02/2022 | 0 | Resource Division | 15.81 | 0 | 0 | 0
2091 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Rajinagar (Village code 315663) under Rejinagar Ground Water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHEDte. Scheme ID 0001723375 in the District of Murshidabad. | 3960/MURD | 20/12/2021 | 120 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 64.06 | 60.49 | 94.42 | 1
2092 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with JALSWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village JANPUR (Village Code 315676) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. NIeT No- WBPHED/EE/MSD/03 OF 2020-2021 _SL_04, 3009/MURD | 169-MSD/2021-22 | 01/11/2021 | 0 | KUNDU CONSTRUCTION | 19.96 | 0 | 0 | 0
2093 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village AMARPUR (Village Code 315675) under REJINAGAR Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block in the District of Murshidabad. Tender no - 618 of 21-22 by EE MURD | 348-MSD/21-22 | 05/03/2022 | 0 | M/S. S. DAS AND ENTERPRISE | 36.35 | 0 | 0 | 0
2094 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Takipur (Village code 315667) under Rejinagar Ground Water Based water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID 1723375 in the District of Murshidabad. (Sl No-10). Tender no - 52 of 21-22 by SE MC | 335-MSD/21-22 | 25/02/2022 | 0 | RAJKUMAR MONDAL | 35.53 | 0 | 0 | 0
2095 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur (315668) of Rejinagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block of Murshidabad District under Murshidabad Division PHE DTE. Tender no - 830 of 20-21 by EE MURD | 345-MSD/21-22 | 05/03/2022 | 0 | R.R. CONSTRUCTION | 27.41 | 0 | 0 | 0
2096 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Additional works for Providing Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village PILKHANA (Village Code 315666) under REJINAGAR Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-II Block under Murshidabad Division PHE DTE. Tender no - 544 of 20-21 by EE MURD | 349-MSD/21-22 | 05/03/2022 | 0 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 12.47 | 0 | 0 | 0
2097 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur (315668) of Rejinagar under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - II Block of Murshidabad District (PART-I) |  | 17/02/2022 | 0 | R.R. CONSTRUCTION | 27.41 | 0 | 0 | 0
2098 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Ramna Dadpur ( Village Code -315668) Part-A under Rejinagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 266/BSD | 24/06/2022 | 30 | R.R. CONSTRUCTION | 4.52 | 4.47 | 98.84 | 0
2099 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Ramna Dadpur (Village Code -315668) Part-B under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 265/BSD | 24/06/2022 | 30 | R.R. CONSTRUCTION | 4.74 | 4.46 | 94.22 | 0
2100 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village PILKHANA (Village Code 315666) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | 3011/MURD | 04/12/2020 | 45 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 20.18 | 5.78 | 100 | 1
2101 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Material Requisition To Resource Division | 539/8/MURD | 25/02/2022 | 0 | Resource Division | 1.14 | 0 | 0 | 0
2102 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with JALSWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village JANPUR (Village Code 315676) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | 3009/MURD | 04/12/2020 | 45 | KUNDU CONSTRUCTION | 20.35 | 0 | 0 | 0
2103 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Takipur(Village code 315667) under Rejinagar Ground Water Based water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. Scheme ID 1723375 in the District of Murshidabad. (Sl No-10) | 3049/MURD | 08/12/2020 | 180 | RAJKUMAR MONDAL | 80.54 | 39.2 | 100 | 1
2104 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | 301/BSD | 13/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.34 | 8.67 | 200 | 0
2105 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village AMARPUR (Village Code 315675) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | 3006/MURD | 04/12/2020 | 45 | M/S. S. DAS AND ENTERPRISE | 39.98 | 0 | 0 | 0
2106 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) of 208 left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Janpur (Village code 315676) under Rejinagar Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad.(Scheme ID- 0001723470) | 784/MURD | 23/03/2022 | 20 | KUNDU CONSTRUCTION | 15 | 11.78 | 78.51 | 1
2107 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village RAMNA DADPUR (Village Code 315668) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | 3007/MURD | 04/12/2020 | 45 | R.R. CONSTRACTION | 31.15 | 3.74 | 100 | 0
2108 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ramna Dadpur, Amarpur, Janpur, Jagamohanpur, Rejinagar, Pilkhana, Takipur (315668,315675,315676,315677 ,315663, 315666 & 315667) of Rejinagar under Ground Water Ba , SM/08183 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village JAGAMOHANPUR (Village Code 315677) under Rejinagar Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | 3010/MURD | 04/12/2020 | 45 | PARTHA BHASKAR | 15.79 | 15.79 | 100 | 1
2109 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bazarsau, Kataikona, Mian, Saktipur, Mahata (315629, 315631, 315632, 315633 & 315638) of Saktipur under Ground Water Based Water Supply Scheme for Arsenic Affected , SM/08185 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with " JALSWAPNA (JAL JEEVAN MISSION)" from existing Distribution system within the Command area of village KATAIKONA (Village Code 315631) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block in the District of Murshidabad. | 3013/MURD | 04/12/2020 | 45 | MAJUMDER CONSTRUCTION | 35.53 | 0 | 0 | 50
2110 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bazarsau, Kataikona, Mian, Saktipur, Mahata (315629, 315631, 315632, 315633 & 315638) of Saktipur under Ground Water Based Water Supply Scheme for Arsenic Affected , SM/08185 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with " JALSWAPNA (JAL JEEVAN MISSION)" from existing Distribution system within the Command area of village MAIN(Village Code 315632) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block in the District of Murshidabad. | 3018/MURD | 04/12/2020 | 45 | MAJUMDER CONSTRUCTION | 34.29 | 14.68 | 38.2 | 40
2111 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bazarsau, Kataikona, Mian, Saktipur, Mahata (315629, 315631, 315632, 315633 & 315638) of Saktipur under Ground Water Based Water Supply Scheme for Arsenic Affected , SM/08185 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BAZAESAU (Village Code 315629) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | 3012/MURD | 04/12/2020 | 45 | SANJAY BISWAS | 26.55 | 18.03 | 67.91 | 0
2112 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bazarsau, Kataikona, Mian, Saktipur, Mahata (315629, 315631, 315632, 315633 & 315638) of Saktipur under Ground Water Based Water Supply Scheme for Arsenic Affected , SM/08185 | Retrofitting | Formal work order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Saktipur ( Village Code -315633) under Saktipur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-II Block, under Murshidabad Division, P.H.E Dte. Scheme Id - 5185583 in the District of Murshidabad. | 45/MURD | 06/01/2021 | 1547 | CHAKRABORTY CONSTRUCTION | 119.73 | 63.55 | 53.08 | 45
2113 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bazarsau, Kataikona, Mian, Saktipur, Mahata (315629, 315631, 315632, 315633 & 315638) of Saktipur under Ground Water Based Water Supply Scheme for Arsenic Affected , SM/08185 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village MAHATA (Village Code 315638) under Saktipur Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga-II Block in the District of Murshidabad. | 3014/MURD | 04/12/2020 | 45 | SO-FINE AQUARIUM | 12.76 | 0 | 0 | 0
2114 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Taraf Rasulpur (314679) of P.T. Rasulpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) , SM/08186 | Retrofitting | Providing Functional Household Tap Connections ( 200 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Taraf Rasulpur ( Village Code -314679) and Sekendra ( Village Code -314064) under P.T Rasulpur & Sekendra Ground Water Based Water Supply Scheme under Murshidabad Division P.H.E Dte. | 2211/MURD | 02/08/2024 | 30 | PRAVAT KUMAR GHOSH | 7.3 | 0 | 0 | 0
2115 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Garaimari ( 314734 ) of Garaimari under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) , SM/08201 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village GORAIMARI (Village Code 314734) under GORAIMARI Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. | 421-MSD/21-22 | 23/03/2022 | 0 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 137.73 | 0 | 0 | 0
2116 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Garaimari ( 314734 ) of Garaimari under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) , SM/08201 | Retrofitting | Formal work order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Garaimari (Village code 314734) under Garaimari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. (Scheme ID 0005019114) | 665/MURD | 19/02/2021 | 180 | ALOK ENTERPRISE | 390.36 | 78.33 | 20.07 | 1
2117 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dayanagar (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block , SM/08906 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) laying pipeline in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahespur, Ratnagopbati, Sujapur, Radhaballabhpur, Banamalipur, Harinarayanpur, Sibpur, Srikrishnapur, Arazi Giridharpur, Dayanagar, Arazi Jalalpur, Jhunka and Jalalpur under DAYANAGAR (ZONE-E) Water Supply Scheme in the district Murshidabad under Berhampore Division - I, PHE Dte. | 979/BD-I | 18/10/2023 | 180 | M/S. SUKUMAR SINHA | 402.21 | 0 | 0 | 0
2118 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dayanagar (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block , SM/08906 | Retrofitting | Laying of 150 mm dia (K-9), 200 mm,250 mm & 300 mm dia DI (K-7) pipeline with interconnection in between Rising Main and Distribution System and 200 mm dia UPVC pipeline of unlead portion within command area of Dayanagar (Zone-E) W/S scheme of Arsenic affected area of Beldanga uncovered W/S scheme under Berhampore Division-I, P.H.E. Dte. | 954/BD-I | 13/10/2023 | 30 | JAMIRUL CONSTRUCTION | 33.95 | 5.88 | 17.33 | 10
2119 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kuchemora, Sahadiar, Aminabad (314735, 314736, 314730) of Aminabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Mursh , SM/08271 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahadiar (Village code 314736) under Aminabad Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723383 (Sl No-6) | 1550/MURD | 23/06/2021 | 180 | MAHAVIR PUMPS MANUFACTRURING PVT. LTD. | 75.82 | 22.19 | 100 | 0
2120 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kuchemora, Sahadiar, Aminabad (314735, 314736, 314730) of Aminabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Mursh , SM/08271 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kuchemora, Sahadiar, Aminabad (314735, 314736, 314730) of Aminabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I), TNO- 112/20-21/SE-MC | 150-MSD/21-22 | 10/10/2021 | 0 | MAHAVIR PUMPS MANUFACTRURING PVT. LTD. | 53.58 | 0 | 0 | 0
2121 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kuchemora, Sahadiar, Aminabad (314735, 314736, 314730) of Aminabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Mursh , SM/08271 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna ( Jal Jeevan Mission) under command area of Aminabad (Village code 314730), under Aminabad Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723383) | 1699/MURD | 29/06/2022 | 120 | M/S. BIMALENDU BOSE | 113.8 | 66.93 | 58.82 | 0
2122 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kuchemora, Sahadiar, Aminabad (314735, 314736, 314730) of Aminabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Mursh , SM/08271 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kuchemora (Village code 314735) under Aminabad Ground Water Supply Scheme for Arsenic Affected Area of DomkalBlock, under Murshidabad Division, PHE Dte. Scheme ID: 0001723383 (Sl-05) | 2533/MURD | 19/08/2021 | 180 | M/S UNIVERSAL TRADING | 89.39 | 25.99 | 29.07 | 0
2123 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kuchemora, Sahadiar, Aminabad (314735, 314736, 314730) of Aminabad under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Mursh , SM/08271 | Retrofitting | Material Requisition To Resource Division | 541/4/MURD | 25/02/2022 | 0 | Resource Division | 1.2 | 0 | 0 | 0
2124 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part , SM/08912 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 60.29 | 1
2125 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part , SM/08912 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Ayesbag Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | 2224/BD-I | 15/12/2021 | 90 | TANUSHREE ENTERPRISE | 78.96 | 76.91 | 100 | 1
2126 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part , SM/08912 | Retrofitting | Material Requisition To Resource Division | 146/BD-I | 10/02/2022 | 0 | Resource Division | 4.67 | 0 | 0 | 0
2127 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part , SM/08912 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sani Baharapara (Village code 314841) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1811/BD-I | 05/10/2021 | 50 | M/S. SUKUMAR SINHA | 42.52 | 0 | 0 | 36
2128 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part , SM/08912 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baramganj and Tiktikipara (Village code 314828,314831) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1815/BD-I | 05/10/2021 | 50 | KAMIRUL SK AND CO. | 50.58 | 42.78 | 84.58 | 1
2129 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part , SM/08912 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kalikapur Kadamkhandi (Village code 315389) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1816/BD-I | 05/10/2021 | 60 | M/S GUHA AND ROY ENTERPRISE | 59.54 | 15.67 | 26.31 | 1
2130 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part , SM/08912 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gopinathpur and Chunakhali (Village code 314829,314830) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1817/BD-I | 05/10/2021 | 90 | SANJAY BISWAS | 90.82 | 56.22 | 61.91 | 85
2131 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part , SM/08912 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khanpur,Hamdampur,Pilkhana and Matijhil (Village code 314845,314846,314850,314848) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1812/BD-I | 05/10/2021 | 100 | M/S GUHA AND ROY ENTERPRISE | 95.07 | 27.15 | 65.58 | 1
2132 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part , SM/08912 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bali (Village code 314832) under Ayesbag (Zone-E) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-01) | 1866/BD-I | 07/10/2021 | 180 | RAJ KUMAR MONDAL | 100.22 | 86.37 | 86.18 | 1
2133 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part , SM/08912 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chainpara, Sanyasidanga & Talgachi (Village code 314821, 314822 & 314823) under Ayesbag (Zone-E) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-02) | 1888/BD-I | 07/10/2021 | 180 | M/S SINHA & SONS | 211.59 | 95.29 | 45.04 | 65
2134 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part , SM/08912 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-51B/5774 Bolero Diesel car for official use of Assistant Engineer-I, under Berhampore Division-I, PHE Dte. period for 01.01.2023 to 31.12.2023. | 1386/BD-I | 23/12/2022 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 4.67 | 257.24 | 100
2135 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part , SM/08912 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gobindapur Lakheraj,Sahamatganj and Bansbari (Village code 314826,314849,314827) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1813/BD-I | 05/10/2021 | 631 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 78.62 | 66.83 | 89.99 | 100
2136 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part , SM/08912 | Retrofitting | Laying of UPVC distribution pipe Line in connection with JJM (Jal Jeevan Mission) on damaged portion from SBCO brick field to near house Mintu Sen and near house of Ased Sk of Ayesbag water supply scheme under CS Part-I of BD-I, P.H.E Dte. | 129/BD-I | 12/05/2023 | 30 | KAUSHIK MAJUMDAR | 2.1 | 2.11 | 100 | 100
2137 | MURSHIDABAD | Berhampore Division I | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION AND JAL SWAPNA IN THE COMMAND AREA OF BRAHIMOTTAR MANIKCKCHAK GROUND WATER SUPPLY SCHEME UNDER LALGOLA BLOCK IN MURSHIDABAD DISTRICT UNDER BERHAM , SM/08919 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Bramhottor (Habitation ID-0001294213 ) and Ilishmari (Habitation ID-0001792563) in the village of Bramhottor Manikchak (Village code 314234) under Bramhottor Manikchak Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 990/BD-I | 17/12/2020 | 60 | S. K. ENTERPRISE | 11.8 | 18.21 | 195 | 1
2138 | MURSHIDABAD | Berhampore Division I | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION AND JAL SWAPNA IN THE COMMAND AREA OF BRAHIMOTTAR MANIKCKCHAK GROUND WATER SUPPLY SCHEME UNDER LALGOLA BLOCK IN MURSHIDABAD DISTRICT UNDER BERHAM , SM/08919 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Kaharpara (Habitation ID-0001294214 ) and Santalpara (Habitation ID-0001792540) in the village of Bramhottor Manikchak (Village code 314234) under Bramhottor Manikchak Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 986/BD-I | 17/12/2020 | 90 | MS RUBIET HOSSAIN | 42.55 | 0 | 0 | 0
2139 | MURSHIDABAD | Berhampore Division I | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION AND JAL SWAPNA IN THE COMMAND AREA OF BRAHIMOTTAR MANIKCKCHAK GROUND WATER SUPPLY SCHEME UNDER LALGOLA BLOCK IN MURSHIDABAD DISTRICT UNDER BERHAM , SM/08919 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of B.M. Para,Bausmari and Bramhottor Manikchak (Habitation ID 0001792822,0001792589,0001294212) under Bramhottor Manikchak Ground Water based Water Supply Scheme in Lalgola Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1855/BD-I | 07/10/2021 | 50 | KAMIRUL SK AND CO. | 48.43 | 42.31 | 100 | 1
2140 | MURSHIDABAD | Berhampore Division I | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION AND JAL SWAPNA IN THE COMMAND AREA OF BRAHIMOTTAR MANIKCKCHAK GROUND WATER SUPPLY SCHEME UNDER LALGOLA BLOCK IN MURSHIDABAD DISTRICT UNDER BERHAM , SM/08919 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Paschim Diarmanik chak (village code 314228) under BRAHIMOTTAR MANIKCHAK Ground water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2250/BD-I | 21/12/2021 | 45 | ARINDAM MAJUMDAR | 30.87 | 12.15 | 39.37 | 1
2141 | MURSHIDABAD | Berhampore Division I | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION AND JAL SWAPNA IN THE COMMAND AREA OF BRAHIMOTTAR MANIKCKCHAK GROUND WATER SUPPLY SCHEME UNDER LALGOLA BLOCK IN MURSHIDABAD DISTRICT UNDER BERHAM , SM/08919 | Retrofitting | Repairing of pipe line portion of rising main in connection with JJM (Jal Jeevan Mission) which used to draw water in OHR ,dismantled from reservoir basin under Bramhottor Manikchak Ground Water based water supply scheme under BD-I, P.H.E Dte | 91/BD-I | 03/05/2023 | 30 | PROSENJIT DAS | 1.02 | 1 | 100 | 100
2142 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District , SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- C. | 208/LSD | 11/05/2022 | 30 | SOUVIK HALDER | 4.86 | 0 | 0 | 0
2143 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District , SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Fatejanpur Diar (P) (314911) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District of Lalbagh Sub-Division under Murshidabad Division Phe Dte . Part- A. | 217/LSD | 11/05/2022 | 30 | SOUVIK HALDER | 4.91 | 0 | 0 | 0
2144 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District , SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Fatejanpur Diar (P) (314911) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District of Lalbagh Sub-Division under Murshidabad Division Phe Dte . Part- B. | 218/LSD | 11/05/2022 | 30 | SOUNAK ENTERPRISE | 4.98 | 0 | 0 | 0
2145 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District , SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- G. | 244/LSD | 11/05/2022 | 30 | SOUNAK ENTERPRISE | 4.98 | 0 | 0 | 0
2146 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District , SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- I. | 246/LSD | 11/05/2022 | 30 | SOUVIK HALDER | 4.86 | 0 | 0 | 0
2147 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District , SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- K. | 248/LSD | 11/05/2022 | 30 | SOUNAK ENTERPRISE | 4.75 | 0 | 0 | 0
2148 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District , SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- A. | 206/LSD | 11/05/2022 | 30 | SOUNAK ENTERPRISE | 4.98 | 0 | 0 | 0
2149 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District , SM/10459 | Retrofitting | Providing Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Mouza Mahinagar (314918) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) & adjoining mouzas of Mukundobag Gram Panchayat of Murshidabad Jiaganj Block of Murshidabad District under Murshidabad Division Phe Dte . Part- B. | 207/LSD | 11/05/2022 | 30 | AMIT KUMAR SAHA | 4.91 | 0 | 0 | 0
2150 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District , SM/10459 | Retrofitting | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/26 & 179/27) at Cabin Para mouza & Connecting with existing 250 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. | 544/MURD | 05/02/2021 | 30 | J.S. CONSTRUCTION | 15.55 | 15.55 | 100 | 0
2151 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District , SM/10459 | Retrofitting | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Dahapara Dham Station ( TP NO 174/24 & 174/22) at Aminabazar Rail Gumit mouza & Connecting with existing 250 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. | 543/MURD | 05/02/2021 | 30 | M/S. GOUTAM CHAKRABORTY | 33.47 | 33.47 | 100 | 0
2152 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District , SM/10459 | Retrofitting | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/11 & 179/10) at Bash Bagan mouza & Connecting with existing 300 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. | 545/MURD | 05/02/2021 | 30 | M/S. S. DAS AND ENTERPRISE | 12.26 | 12.26 | 100 | 0
2153 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District , SM/10459 | Retrofitting | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/26 & 179/27) at Cabin Para mouza & Connecting with existing 250 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. | 409/MURD | 15/02/2023 | 30 | J.S. CONSTRUCTION | 15.55 | 15.55 | 100 | 0
2154 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District , SM/10459 | Retrofitting | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/11 & 179/10) at Bash Bagan mouza & Connecting with existing 300 mm dia UPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. _2 | 408/MURD | 15/02/2023 | 30 | M/S. S. DAS AND ENTERPRISE | 12.26 | 12.26 | 100 | 0
2155 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna(JJM) of Surface Water Based Water Supply Scheme for Jiaganj Azimganj Municipality (Azimganj Portion) and its Adjoining Mouzas of Mukundobag Gram Panchayet of Murshidabad District , SM/10459 | Retrofitting | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Azimganj City Station to Azimganj link cable Station ( TP NO 179/11 & 179/10) at Bash Bagan mouza & Connecting with existing 300 mm diaUPVC distribution main line of Azimganj Surface based W/S Scheme of Lalbagh Sub Division under Murshidabad Division, P.H.E. Dte. _1 | 407/MURD | 15/02/2023 | 30 | M/S. S. DAS AND ENTERPRISE | 12.26 | 12.26 | 100 | 0
2156 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khidirpur (313990) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidaba , SM/09758 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID - ER-MLDT-2022-WL-20 | 400-MSD/22-23 | 18/11/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 2.57 | 0 | 0 | 0
2157 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khidirpur (313990) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidaba , SM/09758 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Bamuha, Khidirpur, Khanpur (Nos FHTC-2996 Nos) (Village code-313962,313990,313989) under PRASADPUR Ground Water Based Water Supply Scheme of Suti-II Block and Kalinagar (FHTC-4077 Nos) (Village code-313899) under Raturi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID-0005019110 & 0001723413) | 558/MURD | 28/02/2022 | 180 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 332.59 | 0 | 0 | 0
2158 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khidirpur (313990) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidaba , SM/09758 | Retrofitting | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 227/3 & 227/4) at Khidirpur mouza & Connecting with existing 200 mm dia uPVC distribution main line of Prosadpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | 511/MURD | 23/02/2022 | 60 | PRADIP KUMAR DAS | 32.67 | 32.58 | 100 | 0
2159 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RAMPUR-I G.P. under Murshidabad Division, P.H.E.Dte. | 350/BSD | 27/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.16 | 4.16 | 100 | 0
2160 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village KANDIBANDHA (Village Code 315327) under SAHAJADPUR Ground Water Based Water Supply Scheme for arsenic affected areas of BERHAMPORE Block in the District of Murshidabad. Tender no - 832 of 20-21 by EE MURD | 256-MSD/22-23 | 12/08/2022 | 0 | MAJUMDER CONSTRUCTION | 9.67 | 0 | 0 | 0
2161 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | Continuation Order for Hiring of 01(one) no. Diesel Bolero /Marshal Car for official use having license for contract carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Murshidabad RWS Sub-Division, for 06(Six) months. (i.e. 01/04/2022 to 30/09/2022) | 151/HQ | 25/03/2022 | 6 | SISIR KUMAR DE | 0.91 | 0 | 0 | 0
2162 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | Continuation Order for Hiring of one no. Diesel Bolero/Marshal/Ambassador car (WB57B4454) for official use of the Assistant Engineer, Kandi Sub-Division, P. H. Engineering Dte. for 03(Three)Months.(Period from 01.04.2022 to 30.06.2022) | 98/BSD | 22/03/2022 | 3 | SISIR KUMAR DE | 0.91 | 0 | 0 | 0
2163 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. (i.e 01.12.2022 to 31.05.2023) | 326/HQ | 25/11/2022 | 181 | DULAL CHOWDHURY | 0.91 | 1.6 | 100 | 0
2164 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | HIRING OF CAR OF SE-MC | 435-MSD/22-23 | 10/12/2022 | 0 | HASNA BEWA | 1.02 | 0 | 0 | 0
2165 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | HIRING OF CAR EE-MSD, OCT-22 NOV-22 | 434-MSD/22-23 | 08/12/2022 | 0 | DULAL CHOWDHURY | 0.78 | 0 | 0 | 0
2166 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
2167 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
2168 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | HIRING OF VEHICLE OF AE-JSD...FROM 01/09/2022 TO 26/10/2022 | 444-MSD/22-23 | 15/12/2022 | 0 | MADAN MOHAN SASMAL | 0.42 | 0 | 0 | 0
2169 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | HIRING OF CAR FOR AE-KSD | 524-MSD/22-23 | 03/02/2023 | 0 | SISIR KUMAR DE | 5.4 | 0 | 0 | 0
2170 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | HIRING OF CAR FOR AE-JSD, W/O NO- 29/MURD, 06/01/2022 | 526-MSD/22-23 | 11/02/2023 | 0 | MADAN MOHAN SASMAL | 0.48 | 0 | 0 | 0
2171 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | Continuation Order for Hiring of one no. Diesel Bolero/Marshal/Ambassador car (WB57B4454) for official use of the Assistant Engineer, Kandi Sub-Division, P. H. Engineering Dte. for 06(SIX)Months.(Period from 01.07.2022 to 31.12.2022) | 264/BSD | 22/06/2022 | 183 | SISIR KUMAR DE | 0.91 | 0 | 0 | 100
2172 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) of 462 left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahammadpur (Village code 315549) under Mahammadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 802/MURD | 24/03/2022 | 30 | M/S. UNIQUE BUILDERS | 29.37 | 0.01 | 100 | 1
2173 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kandibandha ( 315327 ) of Sahajadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District under Mursh , SM/09841 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kandibandha (Village code 315327) under Sahajadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of BERHAMPORE Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723365 in the District of Murshidabad. | 3138/MURD | 11/12/2020 | 60 | MAJUMDER CONSTRUCTION | 24.53 | 0 | 0 | 80
2174 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadupur ( 315357 ) of Jadupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad , SM/09761 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at CHHAIGHARI G.P. under Murshidabad Division, P.H.E.Dte. | 355/LSD | 27/08/2021 | 30 | IMAGIN | 4.17 | 4.17 | 100 | 0
2175 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadupur ( 315357 ) of Jadupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad , SM/09761 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jadupur (Village code 315357) under Jadupur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184179 in the District of Murshidabad. | 816/MURD | 25/03/2022 | 30 | M/S. CHOWDHURY CONSTRUCTION | 24.32 | 0 | 0 | 0
2176 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadupur ( 315357 ) of Jadupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad , SM/09761 | Retrofitting | Material Requisition To Resource Division | 539/5/MURD | 25/02/2022 | 0 | Resource Division | 2.92 | 0 | 0 | 0
2177 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Madhupur ( 315333 ) of Arazi Madhupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur , SM/09768 | Retrofitting | Material Requisition To Resource Division | 539/2/MURD | 25/02/2022 | 0 | Resource Division | 5.23 | 0 | 0 | 0
2178 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Madhupur ( 315333 ) of Arazi Madhupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur , SM/09768 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Arazi Madhupur(VILLAGE CODE-315333) Ground Based piped water supply scheme of Arazi Madhupur (south portion) & its adjoining mouzas under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. | 152/BSD | 12/04/2022 | 30 | PARUL ELECTRICAL INSTALLER | 3.99 | 2.29 | 100 | 80
2179 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Madhupur ( 315333 ) of Arazi Madhupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur , SM/09768 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Arazi Madhupur (Village code 315333) under Arazi Madhupur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184184 in the District of Murshidabad. | 873/MURD | 01/04/2022 | 30 | M/S SAJAHAN CHOWDHURY | 35.47 | 0 | 0 | 0
2180 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Madhupur ( 315333 ) of Arazi Madhupur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mur , SM/09768 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Arazi Madhupur (315333) Ground Based piped water supply scheme of south portion of the scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. | 109/BSD | 28/03/2022 | 853 | DATA ENTERPRISE | 4.29 | 0 | 0 | 90
2181 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10611 | Augmentation | Material Requisition To Resource Division | 1219/MURD/28 | 03/05/2023 | 0 | Resource Division | 65.29 | 0 | 0 | 0
2182 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10611 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of JALANGI , Zone- III/Part-A ground water based water supply scheme under Block- Jalangi, Dist. Murshidabad under MEDB, PHE Dte. | 3770/MEDB | 03/11/2023 | 92 | SURAKSHA | 10.39 | 8.68 | 83.59 | 20
2183 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10611 | Augmentation | AT JALANGI PWSS Z3 PH 1 ID 304238694 | 377/WBSEDCL-JJM | 21/02/2024 | 0 | WBSEDCL | 14.46 | 0 | 0 | 0
2184 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10611 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-III/ Part-A Water Supply Scheme of TW-I under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3056/MURD | 17/11/2022 | 30 | MAMATA USHA ENTERPRISE | 11.79 | 10.58 | 100 | 1
2185 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- III/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10611 | Augmentation | Formal work order for Augmentation of JALANGI ZONE-III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 671/MURD | 09/03/2023 | 906 | MAMATA USHA ENTERPRISE | 637.19 | 427.1 | 69.42 | 100
2186 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Balijana (Code-314514), Nandanpur (Code-314515), Jibanpur (Code-314516) In The Command Area Of Jhikra Ground Wate , SM/07796 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Balijana (Village code 314514) ,Nandanpur (Village code 314515) ,Jibanpur (Village code 314516) under Jhikra Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | 183/BD-I | 04/02/2021 | 30 | JAHANGIR ALAM | 73.4 | 57.79 | 78.74 | 1
2187 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Balijana (Code-314514), Nandanpur (Code-314515), Jibanpur (Code-314516) In The Command Area Of Jhikra Ground Wate , SM/07796 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Balijana (Code-314514), Nandanpur (Code-314515), Jibanpur (Code-314516) In The Command Area Of Jhikra Ground Water Supply Scheme (Part-B)" Under Bhagwangola-II Block in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1553/BD-I | 24/09/2024 | 30 | M/S. OBAIDUR RAHAMAN | 18.33 | 0 | 0 | 0
2188 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. , SM/10015 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (NABIPUR PWSS Scheme, Block - Raninagar-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3263/MURD | 05/10/2021 | 60 | RADIANT | 6.45 | 6.43 | 100 | 1
2189 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. , SM/10015 | Augmentation | Material Requisition To Resource Division | 3052/G/MURD | 17/11/2022 | 0 | Resource Division | 23.03 | 0 | 0 | 0
2190 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. , SM/10015 | Augmentation | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BILPACHAKOPRA (Village Code 314584) under NABIPUR Ground Water Based Water Supply Scheme for arsenic affected areas of RANINAGAR-II Block in the District of Murshidabad. Tender no - 54 of 20-21 by EE MURD | 36-MSD/22-23 | 23/04/2022 | 0 | NOVELTY CONSTRUCTION | 6.31 | 0 | 0 | 0
2191 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. , SM/10015 | Augmentation | Formal work order for laying Distribution System (HDPE Pipe) of for AUGMENTATION of Ground Water Based NABIPUR PWSS to Accommadate FHTC at Raninagar- II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | 1116/MURD | 29/04/2022 | 120 | CHAKRABORTY CONSTRUCTION | 317.51 | 74.49 | 100 | 1
2192 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. , SM/10015 | Augmentation | Material Requisition To Resource Division | 2507/D/MURD | 31/08/2022 | 0 | Resource Division | 11.45 | 0 | 0 | 0
2193 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. , SM/10015 | Augmentation | Soil Investigation for determination the safe bearing capacity and other relevant parameters of soil for construction of O.H.R. for Augmentation of Ground Water Based Nabipur PWSS under Murshidabad Division, PHE Dte. | 153/ISD | 17/03/2022 | 30 | G MITRA & ASSOCIATES | 1.48 | 1.48 | 100 | 100
2194 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. , SM/10015 | Augmentation | Restoration of Road which were damaged during laying of Pipeline under Islampore Sub Division PHE DTE. under Murshidabad Division PHE DTE. Ref Memo No: 488/ISD Dt. 26.09.2024 of the AE/ISD PHE DTE. | 493-MSD/2024-25 | 04/10/2024 | 0 | EXECUTIVE ENGINEER , MURSHIDABAD HIGHWAY DIVISION -I, PWD (ROADS) DIRECT. GOV OF W.B | 9.19 | 0 | 0 | 0
2195 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. , SM/10015 | Augmentation | NEW SERVICE CONNECTION AT NABIPUR PH 3, ID304232739 | 302/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 3.29 | 0 | 0 | 0
2196 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. , SM/10015 | Augmentation | Providing Functional Household Tap Connections (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Nabipur, Bilpachakopra (Village Code -314590,314584) under Nabipur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. | 3337/MURD | 15/12/2022 | 1140 | AZAD ENTERPRISE | 58.72 | 0 | 0 | 70
2197 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. , SM/10015 | Augmentation | Formal work order for laying Distribution System (HDPE Pipe) of for AUGMENTATION of Ground Water Based NABIPUR PWSS to Accommadate FHTC at Raninagar- II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | 1116 /MURD | 29/04/2022 | 1120 | CHAKRABORTY CONSTRUCTION | 317.51 | 118.78 | 37.41 | 80
2198 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based NABIPUR PWSS to Accommodate FHTC in Raninagar-II Block within Murshidabad District Under Murshidabad Division Phe Dte. , SM/10015 | Augmentation | Construction of One no Pump House cum Chlorine Room with sanitary and Water Supply Arrangement ,Construction of Boundary Wall of 200 m, Laying of Rising Main, Construction of 450 Cum OHR, Land Development Works at Nabipur Water Supply scheme at Raninagar-II Block under Murshidabad Division, PHE Dte. | 2302/MURD | 12/08/2024 | 250 | PRAFULLYA CONSTRUCTION | 207.59 | 0 | 0 | 0
2199 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | Protection of Head work site premises by raising Boundary wall height by R.B.T fencing with Entrance Gate under Karimpur Jalangi (Zone-I) Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. | 276/ISD | 03/06/2021 | 60 | ROBIN ROY | 3.32 | 3.26 | 100 | 1
2200 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | Renovation of Pump House No. 1 of Karimpur Jalangi (Zone-I) Water Supply Scheme under Jalangi Block within Islampur Sub Division, under Murshidabad Division, P.H.E. Dte.in the District Murshidabad. | 382/A/ISD | 26/07/2021 | 60 | ROBIN ROY | 2.25 | 2.23 | 100 | 1
2201 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | Relaying of distribution pipeline on damaged line from Node Point 24 to 25 under command area of Karimpur Jalangi Zone-I Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period | 388/ISD | 26/07/2021 | 30 | ROBIN ROY | 4.83 | 4.79 | 100 | 1
2202 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | Relaying of distribution pipeline on damaged line from Node Point 21 to 22 under command area of Karimpur Jalangi Zone-I Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period | 382/ISD | 26/07/2021 | 30 | R.S CONSTRUCTION (PROP- ROBIN ROY) | 4.82 | 4.79 | 100 | 1
2203 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | Preparation of D.P.R (Consultancy work)in connection with the Functional Household Connection of different existing PWSS (Karimpur- Jalangi Zone-I PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 370 of 21-22 by EE MSD. | 185-MSD/22-23 | 13/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 9.77 | 0 | 0 | 0
2204 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional Household Connection of different existing PWSS(Karimpur- Jalangi Zone-II PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 371 of 21-22 by EE MSD. | 185-MSD/22-23 | 13/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 3.24 | 0 | 0 | 0
2205 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | Preparation of D.P.R (Consultancy work)in connection with the Functional Household Connection of different existing PWSS(Karimpur- Jalangi Zone-III PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 372 of 21-22 by EE MSD. | 185-MSD/22-23 | 13/06/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 2.38 | 0 | 0 | 0
2206 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | Material Requisition To Resource Division | 2780/L/MURD | 01/10/2022 | 0 | Resource Division | 18.05 | 0 | 0 | 0
2207 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | Material Requisition To Resource Division | 1180/MURD/10 | 29/04/2023 | 0 | Resource Division | 64.63 | 0 | 0 | 0
2208 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | New connection charge for Karimpur-Jalangi W/S Scheme (Part-B) Zone-I, P/H No.-III. | 94/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 0.78 | 0 | 0 | 0
2209 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | New connection charge for Karimpur-Jalangi W/S Scheme (Part-B) Zone-I, P/H No.-IV. | 93/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 0.78 | 0 | 0 | 0
2210 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | Formal Work Order for Augmentation of Karimpur Jalangi Zone-I(Part-B) Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | 1996/MURD | 21/07/2022 | 1430 | M/S. BIMALENDU BOSE | 267.14 | 210.74 | 78.89 | 81
2211 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under Karimpur-Jalangi (Part-B) ground water based water supply scheme under Block_ Jalangi Dist. - Murshidabad under MEDB, PHE Dte. | 3734/MEDB | 03/11/2023 | 92 | KAMAKHYA ENTERPRISE | 24.23 | 17.96 | 74.13 | 50
2212 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | Balance Work for Laying of Distribution System for Augmentation of Karimpur-Jalangi Zone-I Part-A Piped water supply scheme to accommodate FHTC (Functional House Hold Tap Connection ) under Jalangi Block of Murshidabad District under Murshidabad Division, PHE. Dte. | 65/MURD | 08/01/2024 | 60 | S.S.INFRASTRUCTURE | 134.77 | 99.88 | 87.41 | 10
2213 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | Material Requisition To Resource Division | MURD/2481/07 | 04/09/2024 | 0 | Resource Division | 18.05 | 0 | 0 | 0
2214 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | ADDL SERVICE CONNECTION CHARGES AT KUTUBPUR VILLAGE ,KARIMPUR JALANGI PWSS PART B, Z 1, PH 3 ID860279295 | 214/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 2.93 | 0 | 0 | 0
2215 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-I Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10627 | Augmentation | ADDL SERVICE CONNECTION CHARGES AT KUTUBPUR VILLAGE ,KARIMPUR PWSS PART B, Z 1, PH 4.ID 860281600 | 215/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 2.89 | 0 | 0 | 0
2216 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadhukali (VillageCode-315672) under command area of Sadhukhali ground water supply scheme (Part-A) , SM/07221 | Retrofitting | Formal Work order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sadhukhali (Village code 315672) under Sadhukhali Ground Water Supply Scheme in Beldanga-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-07) | 1635/BD-I | 02/09/2021 | 180 | TARUN KUMAR BHATTACHARYA | 51.96 | 48.51 | 93.36 | 0
2217 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadhukali (VillageCode-315672) under command area of Sadhukhali ground water supply scheme (Part-A) , SM/07221 | Retrofitting | Additional Laying works at villages within Dadpur G.P areas to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Sadhukhali Ground water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 157/BD-I | 11/02/2022 | 30 | ANKUSH CONSTRUCTION & CO. | 16.17 | 0 | 0 | 0
2218 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Panchgachhia, Arazi Ramakantapur, Gotha, Sadikpur, (313919, 313910, 313912, 313920) of Madna under Ground water based water supply scheme for arsenic affected areas of Suti-I Block , SM/11217 | Augmentation | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Panchgachhia (Village code 313919) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756899 in the District of Murshidabad. | 526/MURD | 04/02/2021 | 60 | DIPAYAN DEY | 17.32 | 0 | 0 | 0
2219 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Panchgachhia, Arazi Ramakantapur, Gotha, Sadikpur, (313919, 313910, 313912, 313920) of Madna under Ground water based water supply scheme for arsenic affected areas of Suti-I Block , SM/11217 | Augmentation | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Panchgachhia, Arazi Ramakantapur, Gotha, Sadikpur (313919,313910,313912,313920) of Madna Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division Phe Dte. | 1230/MURD | 11/05/2022 | 60 | MOTI RAHAMAN | 32.62 | 0 | 0 | 0
2220 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11562 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS ( SAKTIPUR PWSS Scheme, Block - Beldanga-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3266/MURD | 05/10/2021 | 60 | RADIANT | 10.43 | 2.77 | 100 | 0
2221 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11562 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shaktipur Zone-I &II Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3072/MURD | 17/11/2022 | 45 | NADIA TUBEWELLS | 21.18 | 8.11 | 100 | 1
2222 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11562 | Augmentation | Material Requisition To Resource Division | 1278/MURD/7 | 10/05/2023 | 0 | Resource Division | 41.67 | 0 | 0 | 0
2223 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11562 | Augmentation | Formal Work Order for Augmentation of Saktipur Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Beldanga-II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 2497/MURD | 30/08/2022 | 1007 | CHAKRABORTY CONSTRUCTION | 286.01 | 128.57 | 44.95 | 60
2224 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11562 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I (H.W Site) at Zone-I and Pump House No.-I (H.W Site) at Zone-II of Saktipur ground water based water supply scheme under Block- Beldanga-II, Dist. Murshidabad under MEDB, PHE Dte. | 2020/MEDB | 19/06/2023 | 92 | INDTECH ASSOCIATES | 23.14 | 0 | 0 | 8
2225 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11562 | Augmentation | Allied work of Pipeline Laying of Distribution system and Construction of Pump House, Boundary Wall, of Shaktipur Zone-II Ground Based piped water supply scheme of Shaktipur Zone-II under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. | 1928/MURD | 03/07/2024 | 60 | HOQUEDAR ALI | 65.09 | 5.51 | 8.47 | 30
2226 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11562 | Augmentation | Material Requisition To Resource Division | 1811/MURD/05 | 20/06/2024 | 0 | Resource Division | 17.54 | 0 | 0 | 0
2227 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11562 | Augmentation | Saktipur Zone-2 Ph-1 Application No- 3004554483 | 253/WBSEDCL-JJM | 17/01/2024 | 0 | WBSEDCL | 3.28 | 0 | 0 | 0
2228 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR , SM/11457 | Augmentation | Material Requisition To Resource Division | 1295/MURD/06 | 11/05/2023 | 0 | Resource Division | 6.13 | 0 | 0 | 0
2229 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR , SM/11457 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of MITHIPUR ground water based water supply scheme under Block- RAGHUNATHGANJ-II, Dist. Murshidabad under MEDB, PHE Dte. | 585/MEDB | 31/01/2024 | 90 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 12.8 | 0 | 0 | 0
2230 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR , SM/11457 | Augmentation | Engagement of Consultant for Field Data collection, pipeline network analysis by analyzing actual household demand in pipeline sections, identification of low pressure areas with in the pipe network system and proposing probable solution of the same in 2(Two) nos water supply schemes in Murshidabad Division P.H.E. Dte. | 2022/MURD | 11/07/2024 | 345 | DHPE | 15.34 | 2.3 | 30 | 25
2231 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR , SM/11457 | Augmentation | Material Requisition To Resource Division | MURD/2481 | 04/09/2024 | 0 | Resource Division | 23.69 | 0 | 0 | 0
2232 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR , SM/11457 | Augmentation | Laying Distribution System and Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement & 2(two) nos Pump House Office cum godown repairing., for Augmentation of MITHIPUR PWSS in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | 145/MURD | 17/01/2023 | 90 | MONDAL ENTERPRISE | 82.55 | 69.23 | 83.86 | 80
2233 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR , SM/11457 | Augmentation | Installation of flow measuring devices on distribution network of MITHIPUR WATER SUPPLY SCHEME OF JANGIPUR SUB-DIVISION UNDER MURSHIDABAD DIVISION, PHE DTE. | 1245/MURD | 29/05/2025 | 30 | DHPE | 3.21 | 0 | 0 | 0
2234 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR , SM/11457 | Augmentation | Retrofitting Functional Household Tap Connection (FHTC) under Jal Jeevan Mission for command area of Augmentation MITHIPUR Water Supply Scheme in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | 119/MURD | 13/01/2023 | 30 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 49.44 | 49.44 | 100 | 100
2235 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR , SM/11457 | Augmentation | Construction of 250 Cum OHR for Augmentation of Mithipur Water Supply Scheme in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | 172/MURD | 18/01/2023 | 1079 | SANJIB GHOSH | 94.37 | 40.77 | 44.68 | 100
2236 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MITHIPUR , SM/11457 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mithipur Water Supply Scheme as required at Raghunathganj-II Block under Murshidabad Division, P.H. Engineering Dte | 1743/MURD | 06/07/2023 | 619 | NADIA TUBEWELLS | 11.78 | 0 | 0 | 100
2237 | MURSHIDABAD | Murshidabad Division | PARULIA AND ADJOINING MOUJAS PWSS , SM/13726 | New | Material Requisition To Resource Division | 1004/MURD/15 | 17/04/2023 | 0 | Resource Division | 46.68 | 0 | 0 | 0
2238 | MURSHIDABAD | Berhampore Mechanical | PARULIA AND ADJOINING MOUJAS PWSS , SM/13726 | New | NEW SERVICE CONNECTION AT PH1 PARULIA PWSS ID 304187861 | 222/WBSEDCL-JJM | 05/01/2024 | 0 | WBSEDCL | 11.66 | 0 | 0 | 0
2239 | MURSHIDABAD | Berhampore Mechanical | PARULIA AND ADJOINING MOUJAS PWSS , SM/13726 | New | NEW SERVICE CONNECTION AT PARULIA PH II, ID304233543 | 295/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 4.74 | 0 | 0 | 0
2240 | MURSHIDABAD | Murshidabad Division | PARULIA AND ADJOINING MOUJAS PWSS , SM/13726 | New | Formal work order for the work of PARULIA & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362284S000) | 165/MURD | 17/01/2023 | 1353 | M/S.TAPAS KUMAR CHAKRABORTY | 677.2 | 322.33 | 47.6 | 41
2241 | MURSHIDABAD | Murshidabad Division | PARULIA AND ADJOINING MOUJAS PWSS , SM/13726 | New | Allied work of PARULIA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | 66/MURD | 08/01/2024 | 479 | M/S.TAPAS KUMAR CHAKRABORTY | 53.37 | 0 | 0 | 10
2242 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Chak Bhikhari,(314686) of Juginda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division PheDte. , SM/11231 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Juginda (Zone-II) Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | 1766/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 35.34 | 32.07 | 100 | 90
2243 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Chak Bhikhari,(314686) of Juginda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division PheDte. , SM/11231 | Augmentation | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Juginda, Kupila and Narsinghpur Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | 1193/MURD | 10/05/2022 | 1360 | MAMATA USHA ENTERPRISE | 32.62 | 0 | 0 | 20
2244 | MURSHIDABAD | Berhampore Mechanical | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Chak Bhikhari,(314686) of Juginda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District under Murshidabad Division PheDte. , SM/11231 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Pump House No. I & II of Zone-II under MOMENPUR AND OTHERS PIPED WATER SUPPLY SCHEME, BLOCK- DOMKAL DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | 1142/MEDB | 14/05/2025 | 92 | DAS CONSTRUCTION | 22.95 | 0 | 0 | 15
2245 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Tikar Bariakalkihara (314642) of Faridpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Divisi , SM/11232 | Augmentation | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Tikar Bariakalkihara ( Village Code -314642) under Faridpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184121) | 579/MURD | 09/02/2021 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 40.1 | 29.94 | 100 | 100
2246 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Tikar Bariakalkihara (314642) of Faridpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Divisi , SM/11232 | Augmentation | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Tikar Bariakalkihara (314642),of Faridpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Division Phe Dte. | 1199/MURD | 10/05/2022 | 45 | NADIA TUBEWELLS | 16.6 | 5.71 | 100 | 100
2247 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Tikar Bariakalkihara (314642) of Faridpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Divisi , SM/11232 | Augmentation | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Faridpur and Indrani Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | 3411/MURD | 22/12/2022 | 984 | R.K. DRILLING SERVICES | 8.4 | 0 | 0 | 100
2248 | MURSHIDABAD | Berhampore Mechanical | GUNANANDABATI AND ADJOINING MOUJAS PWSS , SM/13731 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under GUNANANDABATI ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | 1888/MEDB | 16/06/2023 | 92 | ASHUTOSH DAS & CO. | 23.47 | 0 | 0 | 0
2249 | MURSHIDABAD | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS , SM/13731 | New | Material Requisition To Resource Division | 1210/MURD/43 | 02/05/2023 | 0 | Resource Division | 20.97 | 0 | 0 | 0
2250 | MURSHIDABAD | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS , SM/13731 | New | Formal work order for Laying Distribution System (PART-A) of Gunanandabati PWSS at Bharatpur-I Block, Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362380S000) | 131/MURD | 16/01/2023 | 697 | HARAPRASAD DAS | 132.64 | 120.71 | 91.01 | 85
2251 | MURSHIDABAD | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS , SM/13731 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GUNANANDABATI PWSS at Head Work Site & 2nd Tube Well Site in Bharatpur-I Block under Kandi SubDivision, Murshidabad Division, P.H.Engineering Dte. | 3404/MURD | 22/12/2022 | 45 | M/S D. PALIT & CO. | 16.81 | 13.8 | 100 | 100
2252 | MURSHIDABAD | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS , SM/13731 | New | Laying Distribution system, of Gunanadabati PWSS in Bharatpur-I Block of Kandi Sub-Division under Murshidabad Division, P.H.E. Dte. | 3147/MURD | 03/12/2024 | 179 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 21.46 | 0 | 0 | 80
2253 | MURSHIDABAD | Murshidabad Division | GUNANANDABATI AND ADJOINING MOUJAS PWSS , SM/13731 | New | Construction of RCC Retaining Wall for Gunanandabati PWSS at Bharatpur-I Block under Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | 767/MURD | 13/03/2024 | 483 | M.R. ENTERPRISE (MD. HASANUZZAMAN) | 20.69 | 19.34 | 97.21 | 100
2254 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11791 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Godhanpara PWSS Scheme, Block - Raninagar-II) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | 2744/MURD | 03/09/2021 | 60 | RADIANT | 11.27 | 3.76 | 100 | 0
2255 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11791 | Augmentation | Restoration work of pipeline by relaying of UPVC pipeline of Godhanpara area (Deputipara paniparia Gram Node Point 9 of 17(A), Raninagar Bazarpara Node Point 3(A) to 4) under command area of Godhanpara Zone-I Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period. | 505/ISD | 25/10/2021 | 30 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 4.79 | 4.78 | 100 | 1
2256 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11791 | Augmentation | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Deputipara (Village Code -314582) under Godhanpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.EDte. (Scheme I.D.-0005186259). | 578/ MURD | 09/02/2021 | 60 | M/S ROY & BOSE ENTERPRISE | 17.93 | 5.38 | 100 | 1
2257 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11791 | Augmentation | Material Requisition To Resource Division | 3037/A/MURD | 16/11/2022 | 0 | Resource Division | 31.28 | 0 | 0 | 0
2258 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11791 | Augmentation | Restoration work of pipeline by relaying of UPVC pipeline of Godhanpara area (Kacharipara Gram Node Point 46 of 47) under command area of Godhanpara Zone-I Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period | 503/ISD | 25/10/2021 | 30 | DEBEN RAJAK | 4.48 | 4.47 | 100 | 1
2259 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11791 | Augmentation | Material Requisition To Resource Division | 3052/A/MURD | 17/11/2022 | 0 | Resource Division | 12.45 | 0 | 0 | 0
2260 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11791 | Augmentation | Material Requisition To Resource Division | 1278/MURD/10 | 10/05/2023 | 0 | Resource Division | 25.62 | 0 | 0 | 0
2261 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11791 | Augmentation | Formal work order for Laying of Distribution system,Rising Main, Sub-soil Investigation and construction of OHR (300 cum) and construction of Boundary wall and repairing of Pump-House in connection wih Augmentation of Godhanpara Zone-I water supply scheme under Murshidabad Division, PHE Dte. | 2716/MURD | 26/09/2022 | 365 | M/S. TAPAS KUMAR CHAKRABORTY | 334.37 | 334.35 | 100 | 95
2262 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11791 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Islampur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | 2637/MURD | 23/09/2024 | 150 | INDRAJIT DUBEY | 8.72 | 0 | 0 | 100
2263 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/13928 | Augmentation | Material Requisition To Resource Division | 1210/MURD/24 | 02/05/2023 | 0 | Resource Division | 4.36 | 0 | 0 | 0
2264 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/13928 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | 480/MURD | 22/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 22.29 | 200 | 0
2265 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/13928 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , ZONE-I under BACHHRA ground water based water supply scheme under Block_ BELDANGA-II Dist. - Murshidabad under MEDB, PHE Dte. | 758/MEDB | 20/02/2024 | 90 | KARTICK BAL | 36.55 | 0 | 0 | 0
2266 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/13928 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 5.68 | 100 | 80
2267 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/13928 | Augmentation | Material Requisition To Resource Division | 1811/MURD/11 | 20/06/2024 | 0 | Resource Division | 6.03 | 0 | 0 | 0
2268 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/13928 | Augmentation | NEW CONNECTION AT BACHRA Z-I PH-I | 18/WBSEDCL-JJM | 16/04/2024 | 0 | WBSEDCL | 3.76 | 0 | 0 | 0
2269 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/13928 | Augmentation | Construction of 100 Cum OHR, Laying of Distribution System (part_A), Rising Main , Special repair and renovation of existing 1 (One) Nos PumpHouse and Allied Works, repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity for Augmentation work of BACHHRA ZONE-I PWSS in BELDANGA-II Block under Murshidabad Division , PHE.Dte.(part_A) | 1820/MURD | 12/07/2023 | 720 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 330.74 | 0 | 0 | 5
2270 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/13928 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0 | 0
2271 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/13928 | Augmentation | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For(05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05 (Five) Months].for the month of December 2024 to April 2025 [Vehicle No.WB25M1561] (i.e. from 01/12/2024 to 30/04/2025) | 3127/MURD | 30/11/2024 | 151 | M/S B K ENTERPRISE | 0.87 | 0 | 0 | 0
2272 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/13928 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for BACHHRA ZONE-II Ground Based Water Supply Scheme in Beldanga -II Block underMurshidabad Division , PHE Dte. | 1194/MURD | 23/05/2025 | 60 | M/S UNIVERSAL TRADING | 19.62 | 0 | 0 | 0
2273 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/13928 | Augmentation | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 0 | 75
2274 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/13928 | Augmentation | Providing FHTC Connection to 573 nos household , Laying of Distribution System (Part_B), Repairing & Vertical Extention of Boundary Wall for Augmentation work of BACHHARA ZONE-I PWSS in Beldanga-II Block under Murshidabad Division , PHE.Dte. (part_B) | 913/MURD | 30/03/2023 | 694 | AYUSH ENTERPRISE | 103.18 | 91.79 | 86.97 | 80
2275 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/13928 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BACHHRA ZONE ¿ I Water Supply Scheme at Head Work Site, 2nd Site site at Beldanga-II Block under Murshidabad Division, P.H. Engineering Dte | 3193/MURD | 12/10/2023 | 482 | NADIA TUBEWELLS | 23.56 | 10.29 | 49.36 | 100
2276 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-I PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/13928 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 3.62 | 100 | 100
2277 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14048 | Augmentation | Material Requisition To Resource Division | 61/BD-1/7 | 27/04/2023 | 0 | Resource Division | 19.67 | 0 | 0 | 0
2278 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14048 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under Hurshi ground water based water supply scheme under Block_ Raninagar_I Dist. - Murshidabad under MEDB, PHE Dte. | 4296/MEDB | 29/12/2023 | 91 | MONI ELECTRICAL WORKS | 20.92 | 0 | 0 | 0
2279 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14048 | Augmentation | shifting ltoh hurshi z2 ph 1 | 431/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 0.34 | 0 | 0 | 0
2280 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14048 | Augmentation | Augmentation of Hurshi Zone-II Piped water supply scheme to accommodate construction of OHR, pump house and boundary wall , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 615/BD-I | 02/08/2023 | 790 | ROY AND ROY CONSTRUCTION | 246.81 | 110.57 | 44.8 | 30
2281 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14048 | Augmentation | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Hurshi Zone-II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (For 2 nos. Tubewell) | 1148/BD-I | 04/12/2023 | 30 | NADIA TUBEWELLS | 23.12 | 0 | 0 | 0
2282 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14048 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HURSHI ZONE-II Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1330/BD-I | 16/12/2022 | 10 | RADIANT | 2.53 | 2.53 | 100 | 100
2283 | MURSHIDABAD | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. , SM/13926 | Augmentation | Material Requisition To Resource Division | 1043/MURD/2 | 17/04/2023 | 0 | Resource Division | 8.9 | 0 | 0 | 0
2284 | MURSHIDABAD | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. , SM/13926 | Augmentation | Material Requisition To Resource Division | 1295/MURD/02 | 11/05/2023 | 0 | Resource Division | 8.9 | 0 | 0 | 0
2285 | MURSHIDABAD | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. , SM/13926 | Augmentation | Laying Distribution System PART-B,FHTC for Augmentation of GOBARHATI PWSS in KANDI Block , under Murshidabad Division ,PHE.Dte.Part-B | 991/MURD | 11/04/2023 | 120 | S.K. ENTERPRISE (SANDIP GHOSH) | 175.23 | 172.6 | 98.64 | 35
2286 | MURSHIDABAD | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. , SM/13926 | Augmentation | Construction of surface drain of length 50 m at the Head work site of Gobarhati PWSS and Southern side of Kandi Stack Yard under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 1971/MURD | 20/07/2023 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 3.88 | 3.85 | 100 | 100
2287 | MURSHIDABAD | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. , SM/13926 | Augmentation | Supplying fitting and fixing of R.B. T Concertina fencing on wall top of Gobarhati PWSS and Kandi Stack Yard under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad. | 1972/MURD | 20/07/2023 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 5.14 | 4.91 | 100 | 80
2288 | MURSHIDABAD | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. , SM/13926 | Augmentation | Construction of surface drain of length 40.35 m at the Head work site of Gobarhati PWSS and eastern side of Kandi Stack Yard under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 106/MURD | 10/01/2024 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 3.06 | 2.92 | 100 | 100
2289 | MURSHIDABAD | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. , SM/13926 | Augmentation | Demolition of damaged R.C.C. Elevated Reservoir (Capacity 2,72,400 Ltr) at Gokarna /Gobarhati Water Supply Scheme under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad | 61/MURD | 08/01/2024 | 30 | MD SAJAHAN ALI | 5.47 | 5.47 | 100 | 100
2290 | MURSHIDABAD | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. , SM/13926 | Augmentation | Construction of 350 Cum OHR, Boundwary Wall, Rising Main Connection, Laying Distribution System PART-A,FHTC for Augmentation of GOBARHATI PWSS in KANDI Block , under Murshidabad Division ,PHE.Dte | 1087/MURD | 20/04/2023 | 730 | MOTI RAHAMAN | 301.83 | 128.16 | 42.46 | 25
2291 | MURSHIDABAD | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. , SM/13926 | Augmentation | Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Deputy Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For (05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05(Five) Months i.e. from 13/02/2025 to 12/07/2025].for the month of February 2025 to July2025 [Vehicle No.WB58AR5026] | 390/MURD | 13/02/2025 | 150 | MD MUKLESUR RAHAMAN | 0.87 | 1.9 | 218.87 | 0
2292 | MURSHIDABAD | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. , SM/13926 | Augmentation | Continuation work order for Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Executive Engineer, Murshidabad Division, P.H.E. Dte. For (06) Six Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order) [Period for 06 (Six) Months].for the month of April 2025 to October 2025 [Vehicle No.WB93B0287] (i.e. from 05/04/2025 to 04/10/2025) | 784/MURD | 03/04/2025 | 183 | M/S. S. DAS AND ENTERPRISE | 0.75 | 0 | 0 | 25
2293 | MURSHIDABAD | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. , SM/13926 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (GABARHATI PWSS Scheme, Block - KANDI) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3257/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 6.51 | 4.43 | 100 | 1
2294 | MURSHIDABAD | Murshidabad Division | Augmentation of Gobarhati Piped Water Supply Scheme Block - Kandi District - Murshidabad. , SM/13926 | Augmentation | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well , 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gobarhati & Hizole Water Supply Scheme at Kandi Block under Murshidabad Division, P.H. Engineering Dte. | 1109/MURD | 24/04/2023 | 723 | INDRAJIT MAZUMDAR | 10.68 | 0 | 0 | 100
2295 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground water based piped water supply scheme for Bansgara Zone-I , SM/14924 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd/3rd/4th site) and Allied Works for Bansgara ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | 1669/BD-I | 14/03/2023 | 30 | JIYARUL SK | 4.19 | 2.35 | 100 | 100
2296 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground water based piped water supply scheme for Bansgara Zone-I , SM/14924 | Augmentation | Augmentation of Bansgara Zone-I Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE Dte. | 312/BD-I | 14/06/2023 | 1078 | MODERN CONSTRUCTION | 281.33 | 112.91 | 40.14 | 30
2297 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground water based piped water supply scheme for Bansgara Zone-I , SM/14924 | Augmentation | Balance and Allied work for Laying Rising Main (DI K-9) and Distribution System (DI-K7) including inter connection with supply of necessary CI special and valve at Head Work Site including road restoration for augmentation work of Bansgrara Zone -I Water Supply Scheme , under Jal Jeevan Mission within Lalgola block under Berhampore DIvision -I , PHE.Dte. in the district of Murshidabad. | 844/BD-I | 23/06/2025 | 180 | MODERN CONSTRUCTION | 57.56 | 0 | 0 | 80
2298 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground water based piped water supply scheme for Bansgara Zone-I , SM/14924 | Augmentation | Repair And Renovation Works Of OHR (800 Cum) of Ground Water Based Supply Scheme for Basgara Zone-I of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad For Augmentation of PWSS under Jal jeevan Mission. | 990/BD-I | 30/10/2023 | 30 | MAA CONSTRUCTION | 10.52 | 9.84 | 100 | 90
2299 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . , SM/14066 | Augmentation | Construction of Boundary Wall with Main Entrance gate and barbed wire facing and service road for approach at Augmentation of Dakshin Gopalpur PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | 1113/BD-I | 10/07/2024 | 45 | KHANDAKAR CONSTRUCTION | 22.05 | 0 | 0 | 0
2300 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . , SM/14066 | Augmentation | Material Requisition To Resource Division | 194/BD-I/4 | 09/02/2024 | 0 | Resource Division | 36.44 | 0 | 0 | 0
2301 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . , SM/14066 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Dakshin Gopalpur ground water supply scheme in Raninagar-I Block Dist_Murshidabad under MEDB PHE Dte. | 1129/MEDB | 13/05/2025 | 92 | SUNIL RABIDAS | 39.97 | 0 | 0 | 0
2302 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . , SM/14066 | Augmentation | Renovation for Modified Sujapur Sadipur Model after washing of AIRP (Capacity 29.06 Cum/hr.) at Dakshin Gopalpur Water Supply Scheme under Jal Jivan Mission of Raninagar-I Block under Raghunathganj Sub-Division under Berhampore Division-I, PHE Dte. | 410/BD-I | 13/03/2024 | 60 | SUMAN ENTERPRISE AND SUMAN AQUA | 51.69 | 44.75 | 86.56 | 75
2303 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . , SM/14066 | Augmentation | Continuation work order for Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub Division, PHE Dte. period for 01.01.2025 to 30.06.2025. | 2326/BD-I | 27/12/2024 | 182 | TARUN KUMAR BHATTACHARYA | 0.91 | 1.59 | 175.4 | 0
2304 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . , SM/14066 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Dakshin Gopalpur ground water supply scheme in Raninagar-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | 704/BD-I | 13/05/2025 | 300 | BISWAS ENTERPRISE (PROP. JESMIN KHATUN) | 122.64 | 0 | 0 | 0
2305 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . , SM/14066 | Augmentation | Augmentation of DAKSHIN GOPALPUR Piped water supply scheme for laying of design pipeline, rising main and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | 1598/BD-I | 28/02/2023 | 733 | GOUTAM CHAKRABORTY | 134.6 | 134.53 | 100 | 32
2306 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . , SM/14066 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DAKSHIN GOPALPUR Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1504/BD-I | 07/02/2023 | 10 | M/S SOBHA & CO | 2.67 | 2.57 | 100 | 100
2307 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . , SM/14066 | Augmentation | Improvement of OHR (136.2 Cum) of Ground Water Based Supply Scheme for Augmentation of Dakshin Gopalpur of Raninagar-I block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | 890/BD-I | 06/06/2024 | 135 | RAJEN DAS | 7.27 | 5.33 | 100 | 100
2308 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Gopalpur . , SM/14066 | Augmentation | Allied work of Dakshin Gopalpur Piped Water Supply Scheme for laying of Pipeline ,Rising Main, Pump House Repairing under Jal Jeevan Mission within Raninagar - I Block under Berhampore Division - I PHE Dte in Murshidabad District. | 2270/BD-I | 16/12/2024 | 227 | M/S GOUTAM CHAKRABORTY | 4.31 | 0 | 0 | 100
2309 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- II Block - Khargram , Dist- Murshidabad. , SM/14631 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 5.33 | 100 | 76
2310 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- II Block - Khargram , Dist- Murshidabad. , SM/14631 | Augmentation | Material Requisition To Resource Division | 1043/MURD/4 | 17/04/2023 | 0 | Resource Division | 1.46 | 0 | 0 | 0
2311 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- II Block - Khargram , Dist- Murshidabad. , SM/14631 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhalkundi Zone - II Water Supply Scheme at Head Work Site, 2nd Site site at KHARGRAM Block under Murshidabad Division, P.H.Engineering Dte | 1752/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 23.56 | 0 | 0 | 0
2312 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- II Block - Khargram , Dist- Murshidabad. , SM/14631 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under BHALKUNDI ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | 4300/MEDB | 29/12/2023 | 91 | SREE RADHA ELECTRICAL | 22.89 | 0 | 0 | 0
2313 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- II Block - Khargram , Dist- Murshidabad. , SM/14631 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 0 | 75
2314 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bele Block - Khargram , Dist- Murshidabad. , SM/14632 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 5.33 | 100 | 76
2315 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bele Block - Khargram , Dist- Murshidabad. , SM/14632 | Augmentation | Material Requisition To Resource Division | 1936/MURD/1 | 18/07/2023 | 0 | Resource Division | 30.08 | 0 | 0 | 0
2316 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bele Block - Khargram , Dist- Murshidabad. , SM/14632 | Augmentation | Material Requisition To Resource Division | 1936/MURD/2 | 18/07/2023 | 0 | Resource Division | 2.74 | 0 | 0 | 0
2317 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bele Block - Khargram , Dist- Murshidabad. , SM/14632 | Augmentation | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bele & adjoining mouzas Water Supply Scheme at 3rd work site at K h a r g r a m Block under Murshidabad Division, P.H.Engineering Dte. | 1107/MURD | 24/04/2023 | 20 | SARKAR WATER SUPPLY AGENCY | 10.68 | 9.65 | 100 | 100
2318 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bele Block - Khargram , Dist- Murshidabad. , SM/14632 | Augmentation | Laying Distribution System, Rising Main Connection, FHTC, Repairing of Existing OHR, Pump House, Construction of New Boundary Wall for Augmentation of BELE Ground water based Piped water supply scheme in Khargram Block under Murshidabad Division, PHE. Dte. | 1076/MURD | 19/04/2023 | 1139 | M/S. BIMALENDU BOSE | 270.95 | 66.42 | 24.51 | 25
2319 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bele Block - Khargram , Dist- Murshidabad. , SM/14632 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 0 | 75
2320 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bele Block - Khargram , Dist- Murshidabad. , SM/14632 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 4.9 | 100 | 100
2321 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14633 | Augmentation | Material Requisition To Resource Division | 1230/MURD/09 | 04/05/2023 | 0 | Resource Division | 18.97 | 0 | 0 | 0
2322 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14633 | Augmentation | Material Requisition To Resource Division | 495/MURD/06 | 15/02/2024 | 0 | Resource Division | 7.85 | 0 | 0 | 0
2323 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14633 | Augmentation | HAFANIA Z-II PH-II | 338/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 6.04 | 0 | 0 | 0
2324 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14633 | Augmentation | HAFANIA Z-II PH-I | 337/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 7.12 | 0 | 0 | 0
2325 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14633 | Augmentation | Augmentation of Ground Water Based HAFANIA (ZONE-II) & KEYADANGA PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | 801/MURD | 22/03/2023 | 831 | ATIKUL SAIKH | 367.41 | 129.52 | 49.26 | 100
2326 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14633 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 2.81 | 100 | 100
2327 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-II PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/14633 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-II of HAFANIA ground water based water supply scheme under Block- Suti-II Dist. Murshidabad under MEDB, PHE Dte. | 4308/MEDB | 29/12/2023 | 612 | DAS ENTERPRISE (CHOA) | 11.5 | 9.17 | 79.74 | 20
2328 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . , SM/15229 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-III Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1594/BD-I | 28/02/2023 | 10 | TECHVISION | 2.53 | 2.53 | 100 | 0
2329 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . , SM/15229 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II , ZONE-III under RAMNACHANDPUR_ ground water based water supply scheme under Block_ NOWDA Dist. - Murshidabad under MEDB, PHE Dte. | 4344/MEDB | 29/12/2023 | 91 | SUNIL RABIDAS | 19.44 | 0 | 0 | 0
2330 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . , SM/15229 | Augmentation | Improvement of OHR (180 Cum) Extension of Boundary Wall & Service Road for Augmentation of Ramnachandpur Zone-III PWSS within Nawda block under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad. | 983/BD-I | 19/06/2024 | 60 | U.S BUILDERS | 9.46 | 0 | 0 | 0
2331 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . , SM/15229 | Augmentation | Allied works of Laying of distribution pipeline of RAMNACHANDPUR ZONE-III under JJM within Nowda Block in the district of Murshidabad under Berhampore Division-I, PHE Dte. | 1615/BD-I | 03/10/2024 | 30 | MD ENTERPRISE | 12.65 | 0 | 0 | 0
2332 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . , SM/15229 | Augmentation | Material Requisition To Resource Division | 196/BD-I/17 | 09/02/2024 | 0 | Resource Division | 14.91 | 0 | 0 | 0
2333 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . , SM/15229 | Augmentation | Augmentation of Ramnachandpur Zone-III Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1622/BD-I | 02/03/2023 | 670 | SAMAR MUKHERJEE | 112.68 | 105.45 | 100 | 99
2334 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . , SM/15229 | Augmentation | Repair And Renovation Works Of OHR (180 Cum) for Ramnachandpur Zone-III water supply scheme of Nawda block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 1016/BD-I | 31/10/2023 | 30 | NATIONAL ENTERPRISES | 7.4 | 6.88 | 100 | 100
2335 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . , SM/15229 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Ramnachandpur Zone-III Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 150/BD-I | 05/02/2024 | 30 | NADIA TUBEWELLS | 9 | 6.33 | 100 | 100
2336 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . , SM/15229 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 34 Cum/hr.) with allied work at Ramnachandrapur Zone-III Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | 913/BD-I | 07/06/2024 | 30 | SAMAR MUKHERJEE | 13.04 | 12.25 | 100 | 90
2337 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-III pipe water supply scheme . , SM/15229 | Augmentation | Balance work i.c.w. Improvement of Existing AIRP of (Capacity 34 Cum/hr.) along with required allied work at Ramnachandpur Zone-III Water Supply Scheme under JJM within Nawda block under Berhampore Division-I, PHE Dte.in the district of Murshidabad. | 769/BD-I | 22/05/2025 | 30 | SAMAR MUKHERJEE | 13.15 | 0 | 0 | 90
2338 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at GODHANPARA PWSS (ZONE- I ) Ground water Based PWSS, Block-Raninagar-II , Dist- Murshidabad under MEDB, PHE Dte. , SM/15291 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at GODHANPARA PWSS (ZONE- I ) Ground water Based PWSS, Block-Raninagar-II , Dist- Murshidabad under MEDB, PHE Dte | 3755/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 6.39 | 0 | 0 | 0
2339 | MURSHIDABAD | Murshidabad Division | GAFULIA AND ADJOINING MOUJAS PWSS , SM/14626 | New | Material Requisition To Resource Division | 1278/MURD/17 | 10/05/2023 | 0 | Resource Division | 27.87 | 0 | 0 | 0
2340 | MURSHIDABAD | Berhampore Mechanical | GAFULIA AND ADJOINING MOUJAS PWSS , SM/14626 | New | Electric Service Connection at GAFULIA RAJHAT SIULI PWSS PH II, Application NO.3004502793, ID 304199818 | 191/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 6.85 | 0 | 0 | 0
2341 | MURSHIDABAD | Berhampore Mechanical | GAFULIA AND ADJOINING MOUJAS PWSS , SM/14626 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under GAFULIA ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | 4354/MEDB | 29/12/2023 | 91 | WEST BENGAL ENGINEERING CO. | 23.39 | 0 | 0 | 0
2342 | MURSHIDABAD | Murshidabad Division | GAFULIA AND ADJOINING MOUJAS PWSS , SM/14626 | New | Laying Distribution System (PART-B), FHTC in GAFULIA Water at Supply Scheme in Burwan Block , under Murshidabad Division ,PHE. Dte. | 1900/MURD | 17/07/2023 | 120 | MITRA CONSTRUCTION | 263.45 | 67.63 | 25.67 | 31
2343 | MURSHIDABAD | Murshidabad Division | GAFULIA AND ADJOINING MOUJAS PWSS , SM/14626 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gafulia & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at B u r w a n Block under Murshidabad Division, P.H. Engineering Dte. | 1218/MURD | 03/05/2023 | 30 | MAMATA USHA ENTERPRISE | 21.38 | 18.94 | 100 | 100
2344 | MURSHIDABAD | Murshidabad Division | GAFULIA AND ADJOINING MOUJAS PWSS , SM/14626 | New | Material Requisition To Resource Division | 79/MURD/01 | 09/01/2024 | 0 | Resource Division | 12.43 | 0 | 0 | 0
2345 | MURSHIDABAD | Murshidabad Division | GAFULIA AND ADJOINING MOUJAS PWSS , SM/14626 | New | Material Requisition To Resource Division | MURD/439/10 | 08/02/2024 | 0 | Resource Division | 0.56 | 0 | 0 | 0
2346 | MURSHIDABAD | Berhampore Mechanical | GAFULIA AND ADJOINING MOUJAS PWSS , SM/14626 | New | New service connection at SULI PH1 ID 304199844 | 225/WBSEDCL-JJM | 08/01/2024 | 0 | WBSEDCL | 5.06 | 0 | 0 | 0
2347 | MURSHIDABAD | Murshidabad Division | GAFULIA AND ADJOINING MOUJAS PWSS , SM/14626 | New | Formal work order for construction of 250 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System (PART-A), Rising Main, Boundwary Wall of GAFULIA PWSS, in Burwan Block under Murshidabad Division ,PHE.Dte. [ (i)Amount for LDS , R. Main : Rs. 52,45,981.00 & (ii) Amount for OHR, & Pump House : Rs. 1,56,36,015.00] | 592/MURD | 01/03/2023 | 853 | H.L. CONSTRUCTION (TITAN BISWAS) | 208.8 | 120.47 | 57.7 | 53
2348 | MURSHIDABAD | Murshidabad Division | Augmentation of Tekaraipara Pipe Water Supply Scheme Block - Raninagar -I District - Murshidabad. , SM/15064 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 2.92 | 100 | 1
2349 | MURSHIDABAD | Murshidabad Division | Augmentation of Tekaraipara Pipe Water Supply Scheme Block - Raninagar -I District - Murshidabad. , SM/15064 | Augmentation | Construction of Pump House, Boundary Wall, Rising Main Connection, Laying Distribution System and FHTC & Special Reaparing of 02 (Two) Nos Pump House for Augmentation of Tekaraipara Ground water based piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) with Raninagar -I Block of Murshidabad District under Murshidabad Division, P.H.Engineering Dte. | 1814/MURD | 20/06/2024 | 560 | S.D. PROJECT | 448.97 | 54.65 | 12.17 | 50
2350 | MURSHIDABAD | Murshidabad Division | Augmentation of Tekaraipara Pipe Water Supply Scheme Block - Raninagar -I District - Murshidabad. , SM/15064 | Augmentation | Rising Main Connection (D.I-K9) , Laying Distribution System (D.I-K7 & HDPE PE-100), and Balance Portion of Functional Household Tap Connection (1052 Nos) and Reconnection of Functional Household Tap Connection (4370 Nos) for Augmentation of Tekaraipara Ground water based Piped water supply scheme within Raninagar-I Block of Murshidabad District under Murshidabad Division, PHE. Dte. | 1671/MURD | 24/07/2025 | 240 | S.D. PROJECT | 219.58 | 0 | 0 | 50
2351 | MURSHIDABAD | Berhampore Division I | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme , SM/16263 | New | Material Requisition To Resource Division | 61/BD-1/35 | 27/04/2023 | 0 | Resource Division | 13.43 | 0 | 0 | 0
2352 | MURSHIDABAD | Berhampore Division I | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme , SM/16263 | New | Material Requisition To Resource Division | 304/BD-1/8 | 22/02/2024 | 0 | Resource Division | 9.83 | 0 | 0 | 0
2353 | MURSHIDABAD | Berhampore Mechanical | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme , SM/16263 | New | AMARKUNDU PH-1 | 398/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 9.75 | 0 | 0 | 0
2354 | MURSHIDABAD | Berhampore Division I | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme , SM/16263 | New | AMARKUNDA PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | 1825/BD-I | 31/03/2023 | 180 | AJOY GHOSH | 96.88 | 58.27 | 60.15 | 20
2355 | MURSHIDABAD | Berhampore Division I | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme , SM/16263 | New | AMARKUNDA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 206/BD-I | 17/05/2023 | 744 | G M ENTERPRISE | 53.43 | 27.52 | 51.51 | 20
2356 | MURSHIDABAD | Berhampore Division I | AMARKUNDA AND ADJONING MOUJAS Pipe Water Supply Scheme , SM/16263 | New | AMARKUNDA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jeevan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART -A) | 94/BD-I | 04/05/2023 | 1063 | TANUSHREE ENTERPRISE | 240.28 | 89.12 | 37.09 | 100
2357 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at JITPUR (ZONE II) Ground water Based PWSS, Block-Domkal , Dist- Murshidabad under MEDB, PHE Dte. , SM/15354 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at JITPUR (ZONE II) Ground water Based PWSS, Block-Domkal , Dist- Murshidabad under MEDB, PHE Dte. | 4351/MEDB | 29/12/2023 | 91 | SONSOLITE INFRA AND POWER SOLUTIONS PRIVATE LIMITED | 6.43 | 0 | 0 | 0
2358 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply , SM/06974 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rianpur (Village code 314192) under Jumra Nayagram Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 968/BD-I | 17/12/2020 | 90 | JAHANGIR ALAM | 38.56 | 38.03 | 98.63 | 1
2359 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply , SM/06974 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1193/BD-I | 25/07/2024 | 180 | SOUMEN ADHIKARY | 10.19 | 0 | 0 | 0
2360 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply , SM/06974 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Panisala (Village code 314191) under Jumra Nayagram Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 965/BD-I | 17/12/2020 | 90 | SAMBHUNATH ROY | 37.24 | 33.5 | 100 | 1
2361 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Village Panisala (VillageCode-314191) & Rianpur (VillageCode-314192) under Jumra Nayagram ground water supply , SM/06974 | Retrofitting | Additional Laying works at village Rianpur (village code 315397) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Jumra Nayagram ground water supply scheme (Block-Lalgola)under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 632/BD-I | 31/05/2022 | 10 | CHATTERJEE ENTERPRISE | 8.92 | 4.55 | 100 | 1
2362 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at EDRAKPUR Ground water Based PWSS, Block-Nowda , Dist- Murshidabad under MEDB, PHE Dte. , SM/15327 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at EDRAKPUR Ground water Based PWSS, Block-Nowda , Dist- Murshidabad under MEDB, PHE Dte. | 3746/MEDB | 03/11/2023 | 92 | M/S SAJAHAN CHOWDHURY | 6.38 | 0 | 0 | 0
2363 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at KAKRAMARI ZONE I Ground water Based PWSS, Block-Suti-II , Dist- Murshidabad under MEDB, PHE Dte. , SM/15343 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at KAKRAMARI ZONE I Ground water Based PWSS, Block-Suti-II , Dist- Murshidabad under MEDB, PHE Dte | 3758/MEDB | 03/11/2023 | 92 | M/S. SUPER CONSTRUCTION | 6.39 | 0 | 0 | 0
2364 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Dogachhi Zone - I Ground water Based PWSS, Block-Samserganj , Dist- Murshidabad under MEDB, PHE Dte. , SM/15344 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Dogachhi Zone - I Ground water Based PWSS, Block-Samserganj , Dist- Murshidabad under MEDB, PHE Dte | 3757/MEDB | 03/11/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.39 | 0 | 0 | 0
2365 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahisha Thali ( 313851 ) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-III , SM/07514 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MAHISHA THALI (Village Code 313851) under DOGACHHI Ground Water Based Water Supply Scheme for arsenic affected areas of SAMSERGANJ Block in the District of Murshidabad. Tender no - 828 of 20-21 by EE MURD | 360-MSD/21-22 | 10/03/2022 | 0 | HARUN-AL-RASHID & BROTHERS | 17 | 0 | 0 | 0
2366 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahisha Thali ( 313851 ) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-III , SM/07514 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of MahishaThali( Village Code -313851) under Dogachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005019105) | 598/MURD | 09/02/2021 | 60 | HARUN ALL RASHID & BROTHERS | 30.42 | 7.36 | 24.18 | 1
2367 | MURSHIDABAD | Berhampore Mechanical | MAHISHASTHALI AND ADJOINING MOUJAS PWSS , SM/16015 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Mahishasthali ground water based water supply scheme under Block_ Bhagwangola-I Dist. - Murshidabad under MEDB, PHE Dte. | 3691/MEDB | 03/11/2023 | 92 | GOENKA ENTERPRISE | 20.9 | 0 | 0 | 0
2368 | MURSHIDABAD | Berhampore Division I | MAHISHASTHALI AND ADJOINING MOUJAS PWSS , SM/16015 | New | Material Requisition To Resource Division | 61/BD-1/21 | 27/04/2023 | 0 | Resource Division | 15.38 | 0 | 0 | 0
2369 | MURSHIDABAD | Berhampore Division I | MAHISHASTHALI AND ADJOINING MOUJAS PWSS , SM/16015 | New | MAHISHASTHALI PWSS to accommodate FHTC, Laying Distribution System, under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | 143/BD-I | 15/05/2023 | 893 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 96.62 | 0 | 0 | 5
2370 | MURSHIDABAD | Berhampore Division I | MAHISHASTHALI AND ADJOINING MOUJAS PWSS , SM/16015 | New | MAHISHASTHALI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 350 cum) under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | 116/BD-I | 30/01/2024 | 620 | RANADHIR SINHA | 268.39 | 0 | 0 | 30
2371 | MURSHIDABAD | Berhampore Division I | MAHISHASTHALI AND ADJOINING MOUJAS PWSS , SM/16015 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MAHISASTHALI and Adjoining Mouzas PWSS (TW-I & II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-I Block under Berhampore Division-I, P.H.Engineering Dte. (02 Nos TW) | 847/BD-I | 23/06/2025 | 30 | WATER TECH | 17.75 | 0 | 0 | 0
2372 | MURSHIDABAD | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. , SM/15955 | New | Formal work order for MADHUPUR PWSS Construction OHR, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jiban Mission, Block- SAMSERGANJ of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE. Dte. | 686/MURD | 10/03/2023 | 365 | M/S KHAN CHOWDHURY BROTHERS AND CO | 224.5 | 0 | 0 | 0
2373 | MURSHIDABAD | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. , SM/15955 | New | Material Requisition To Resource Division | 1230/MURD/28 | 04/05/2023 | 0 | Resource Division | 33.76 | 0 | 0 | 0
2374 | MURSHIDABAD | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. , SM/15955 | New | MADHUPUR PWSS Construction to accommodate FHTC, Laying Distribution System , Rising Main under Jal Jivan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | 883/MURD | 28/03/2023 | 918 | SHYAMAL KUMAR SAHA | 231.54 | 0 | 0 | 40
2375 | MURSHIDABAD | Murshidabad Division | MADHUPUR PIPED WATER SUPPLY SCHEME. , SM/15955 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.63 | 100 | 100
2376 | MURSHIDABAD | Berhampore Mechanical | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. , SM/16445 | New | NEW CONNECTION AT JAULIA PH-II | 64/WBSEDCL-JJM | 09/05/2024 | 0 | WBSEDCL | 3.29 | 0 | 0 | 0
2377 | MURSHIDABAD | Berhampore Mechanical | JAULIA PIPED WATER SUPPLY SCHEME, BLOCK- BHARATPUR-II, DISTRICT- MURSHIDABAD. , SM/16445 | New | NEW CONNECTION AT JAULIA PH-I | 77/WBSEDCL-JJM | 20/05/2024 | 0 | WBSEDCL | 4.25 | 0 | 0 | 0
2378 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JAGAIAPUR Block - Nawda District - Murshidabad. , SM/16543 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0 | 0
2379 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JAGAIAPUR Block - Nawda District - Murshidabad. , SM/16543 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 6.59 | 100 | 1
2380 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JAGAIAPUR Block - Nawda District - Murshidabad. , SM/16543 | Augmentation | Material Requisition To Resource Division | 1219/MURD/04 | 03/05/2023 | 0 | Resource Division | 26.87 | 0 | 0 | 0
2381 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JAGAIAPUR Block - Nawda District - Murshidabad. , SM/16543 | Augmentation | Material Requisition To Resource Division | 1811/MURD/10 | 20/06/2024 | 0 | Resource Division | 11.14 | 0 | 0 | 0
2382 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JAGAIAPUR Block - Nawda District - Murshidabad. , SM/16543 | Augmentation | Providing FHTC Connection to 1118 nos household ,Laying of Distribution System, Rising Main , Repairing & Vertical Extension of Boundary Wall, Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works ,for Augmentation work of JAGAIPUR , NAWDA Block under Murshidabad Division , PHE.Dte | 2666/MURD | 24/08/2023 | 949 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 265.09 | 110.53 | 41.7 | 70
2383 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JAGAIAPUR Block - Nawda District - Murshidabad. , SM/16543 | Augmentation | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jagaipur PWSS TW-I,II, Chandpur Zone-I PWSS T.W.-II, Edrakpur PWSS T.W-II, Surangapur Zone-IA TW-I of Nowda Block under Berhampore Sub-Division,Murshidabad Division, P.H.Engineering Dte. | 663/MURD | 19/03/2025 | 65 | SARKAR WATER SUPPLY AGENCY | 58.87 | 0 | 0 | 0
2384 | MURSHIDABAD | Berhampore Division I | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Chhalimpur, Block- Murshidabad Jiaganj, District- Murshidabad. , SM/16048 | New | Mini Piped Water Supply Scheme for Chhalimpur under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 163/BD-I | 16/05/2023 | 90 | DEBJIT DAS | 22.79 | 0 | 0 | 100
2385 | MURSHIDABAD | Berhampore Mechanical | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Chhalimpur, Block- Murshidabad Jiaganj, District- Murshidabad. , SM/16048 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chhalimpur village, Block:- Murshidabad - Jiaganj under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3043/MEDB | 02/08/2023 | 92 | M/S. SUPER CONSTRUCTION | 6.32 | 0 | 0 | 0
2386 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar Chhoemkanun (village code 314579) under Ramnagar Doemkanun Ground water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2208/BD-I | 10/12/2021 | 120 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 89.24 | 59.76 | 66.97 | 1
2387 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Continuation Work Order for Hiring of one no. Car No. W.B-51B/5774 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer-II, Berhampore Division-I, PHE Dte. for the period from 01.10.2021 to 31.12.2021 | 1780/BD-I | 30/09/2021 | 92 | AVINABA ENGINEERING CONCERN | 0.45 | 1.14 | 100 | 1
2388 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Continuation Work Order for Hiring of one no. Car No. W.B-51B/6299 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer, Raghunathganj Sub Division, PHE Dte. for the period from 01.10.2021 to 31.12.2021. | 1779/BD-I | 30/09/2021 | 92 | AVINABA ENGINEERING CONCERN | 0.45 | 0 | 0 | 1
2389 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub-Division, PHE Dte. period for 01.01.2022 to 31.12.2022. | 2281/BD-I | 27/12/2021 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 0 | 0 | 1
2390 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Hiring of one no. Car No. W.B-57C/5576 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2022 to 31.12.2022. | 2280/BD-I | 27/12/2021 | 365 | SEBAYAN CONSTRUCTION | 1.81 | 4.76 | 100 | 1
2391 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Material Requisition To Resource Division | 140/BD-I | 10/02/2022 | 0 | Resource Division | 15.4 | 0 | 0 | 0
2392 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Hiring of one no. Car No. W.B-51B/5774 Bolero Diesel car for official use of Assistant Engineer-I, under Berhampore Division-I, PHE Dte. period for 01.01.2022 to 31.12.2022. | 2279/BD-I | 27/12/2021 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 2.65 | 100 | 1
2393 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khastaluk (Village code 314575) under Ramnagar Doemkanum Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 983/BD-I | 17/12/2020 | 60 | AZAD ENTERPRISE | 11.16 | 2.24 | 20.09 | 1
2394 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Continuation Work Order for Hiring of one no. Car No. W.B-51B/6299 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer, Raghunathganj Sub Division, PHE Dte. for the period from 01.04.2021 to 30.09.2021 | 443/BD-I | 30/03/2021 | 184 | AVINABA ENGINEERING CONCERN | 0.91 | 2.11 | 100 | 1
2395 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kazipara (Village code 314608) under Kazipara Water Supply Scheme of Jalangi Block and village of Ramnagar Doemkanun (Village code 314578) under Ramnagar Doemkanun Water Supply Scheme of Raninagar-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. | 49/BD-I | 27/01/2022 | 180 | M/S S.DAS & ENTERPRISE | 337.04 | 82.3 | 31.36 | 1
2396 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Hiring of one no. Car No- W.B-57E/2525 Scorpio Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.01.2022 to 31.12.2022. | 2278/BD-I | 27/12/2021 | 365 | M/S SAJAHAN CHOWDHURY | 1.81 | 1.82 | 100 | 1
2397 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under RAMNAGAR DOEMKANUN ,KOMNAGAR and BANSGARA ZONE-II ground Water based Water Supply Scheme under Raninagar-II Block in Murshidabad District under Berhampore Division-I, PHE Dte. | 438/BD-I | 12/07/2023 | 692 | MAA CONSTRUCTION | 93.76 | 24.1 | 25.71 | 30
2398 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Egrarashi (Village code 314576) under Ramnagar Doemkanum Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 982/BD-I | 17/12/2020 | 60 | MAA CONSTRUCTION | 5.73 | 4.6 | 100 | 1
2399 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Laying of new pipeline for Providing Balanced Functional Household Tap Connection (FHTC) which is not covered by existing distribution pipeline from nearest Ground water supply scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar Khastaluk (Village code 314586) under Ramnagar Doemkanun Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 1464/BD-I | 16/08/2021 | 15 | SANTANU BISWAS | 8.61 | 6.57 | 100 | 0
2400 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Continuation Work Order for Hiring of one no. Car No. W.B-51B/5774 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer-II, Berhampore Division-I, PHE Dte. for the period from 01.04.2021 to 30.09.2021 | 444/ BD-I | 30/03/2021 | 184 | AVINABA ENGINEERING CONCERN | 0.91 | 2.37 | 100 | 1
2401 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Laying of new pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khastaluk (Village code 314575) under Ramnagar Doemkanun Ground Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. (Block-Raninagar-II) | 1442/BD-I | 11/08/2021 | 10 | AZAD ENTERPRISE | 4.61 | 3.86 | 100 | 1
2402 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor , SM/08900 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar Khastaluk (Village code 314586) under Ramnagar Doemkanum Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 984/BD-I | 17/12/2020 | 90 | M/S SINHA & SONS | 39.31 | 18.27 | 180.65 | 1
2403 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-I, Block- Nawda, District- Murshidabad. , SM/16499 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Shibnagar Zone-I village, Block:- Nawda under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3077/MEDB | 02/08/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0 | 0
2404 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-I, Block- Nawda, District- Murshidabad. , SM/16499 | New | Mini Piped Water Supply Scheme for Sibnagar Zone-I under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 154/BD-I | 15/05/2023 | 90 | DATA ENTERPRISE | 30.53 | 0 | 0 | 0
2405 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHULA PWSS BELDANGA -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16406 | Augmentation | Construction of 450 Cum OHR, Pump House with sanitary and Water Supply Arrangement , Pump House cum Blower room And Boundary Wall for Augmentation work MAHULA of Beldanga -I Block under Murshidabad Division , PHE.Dte. PART_B | 2405/MURD | 07/08/2023 | 365 | ABHISHEK BHATTACHARYA | 198.86 | 0 | 0 | 0
2406 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHULA PWSS BELDANGA -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16406 | Augmentation | Providing FHTC Connection to 3199 nos household , Laying of Distribution System, Rising Main for Augmentation work MAHULA of Beldanga -I Block under Murshidabad Division , PHE.Dte. PART _A. | 2467/MURD | 09/08/2023 | 180 | SARAJIT KUMAR MAJUMDER | 306.82 | 0 | 0 | 0
2407 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHULA PWSS BELDANGA -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16406 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (MOHULA PWSS Scheme, Block - Beldanga-I) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3273/MURD | 05/10/2021 | 60 | RADIANT | 10.24 | 10.24 | 100 | 1
2408 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHULA PWSS BELDANGA -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16406 | Augmentation | Material Requisition To Resource Division | 1290/MURD/02 | 03/05/2023 | 0 | Resource Division | 0.41 | 0 | 0 | 0
2409 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MAHULA PWSS BELDANGA -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16406 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.29 | 100 | 80
2410 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-III PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE , SM/16408 | Augmentation | Material Requisition To Resource Division | 1147/MURD/10 | 27/04/2023 | 0 | Resource Division | 25.8 | 0 | 0 | 0
2411 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-III PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE , SM/16408 | Augmentation | NEW CONNECTION AT HILORA Z-III PH-I |  | 08/07/2024 | 0 | WBSEDCL | 10.62 | 0 | 0 | 0
2412 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-III PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE , SM/16408 | Augmentation | NEW CONNECTION AT HILORA Z-III PH-I | 165/WBSEDCL-JJM | 29/07/2024 | 0 | WBSEDCL | 10.62 | 0 | 0 | 0
2413 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-III PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE , SM/16408 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 0 | 5
2414 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-III PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE , SM/16408 | Augmentation | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0 | 0
2415 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-III PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE , SM/16408 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for HILORA Zone-III Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division, PHE Dte. | 984/MURD | 02/05/2025 | 60 | M/S J.S. ENTERPRISE | 22.99 | 0 | 0 | 0
2416 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-III PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE , SM/16408 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.29 | 100 | 100
2417 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. , SM/15921 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0 | 0
2418 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. , SM/15921 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 5.77 | 100 | 1
2419 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. , SM/15921 | Augmentation | Material Requisition To Resource Division | 1219/MURD/05 | 03/05/2023 | 0 | Resource Division | 46.14 | 0 | 0 | 0
2420 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. , SM/15921 | Augmentation | Construction Pump House with clorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement) and 55 mtr Boundary wall at 3rd Tubewell site of Sarbangapur Zone -II Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | 1927/MURD | 03/07/2024 | 60 | M/S S.R.K. ENTERPRISE | 16.6 | 0 | 0 | 0
2421 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. , SM/15921 | Augmentation | Material Requisition To Resource Division | 1811/MURD/13 | 20/06/2024 | 0 | Resource Division | 4.08 | 0 | 0 | 0
2422 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. , SM/15921 | Augmentation | Providing FHTC Connection to 193 nos household for Augmentation of SARBANGAPUR ZONE-II PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division ,PHE.Dte.(Part_C) | 1819/MURD | 12/07/2023 | 60 | A.M. CONSTRUCTION | 21.14 | 0 | 0 | 0
2423 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. , SM/15921 | Augmentation | Laying of Distribution System, Rising Main for Augmentation of SARBANGAPUR ZONE-II PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division , PHE.Dte.(Part_B) | 2646/MURD | 23/08/2023 | 709 | DOBAY CONSTRUCTION | 229.82 | 145.35 | 63.25 | 70
2424 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SARBANGAPUR ZONE-II PIPE WATER SUPPLY SCHEME BLOCK- NAWDA , DIST- MURSHIDABAD. , SM/15921 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for SARBANGAPUR ZONE-II Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | 1227/MURD | 28/05/2025 | 240 | M/S.S.S. ENTERPRISE | 19.62 | 0 | 0 | 0
2425 | MURSHIDABAD | Berhampore Mechanical | SUJAPUR PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. , SM/16214 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Sujapur Part-B village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3072/MEDB | 02/08/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0 | 0
2426 | MURSHIDABAD | Murshidabad Division | SUJAPUR PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. , SM/16214 | New | Ground Water based water supply scheme for Sujapur Part- B village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2320/MURD | 02/08/2023 | 822 | SOUVIK HALDER | 30.54 | 0 | 0 | 60
2427 | MURSHIDABAD | Murshidabad Division | SUJAPUR PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. , SM/16214 | New | Ground Water based piped water supply scheme for Sujapur Part- A village, Block:- Khargram, Kandi Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3054/MURD | 29/09/2023 | 824 | M/S BHATTACHARJEE & CO | 30.55 | 2.85 | 9.34 | 42
2428 | MURSHIDABAD | Murshidabad Division | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. , SM/16411 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 1.91 | 65.69 | 76
2429 | MURSHIDABAD | Murshidabad Division | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. , SM/16411 | Augmentation | Material Requisition To Resource Division | 1230/MURD/02 | 04/05/2023 | 0 | Resource Division | 36.51 | 0 | 0 | 0
2430 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. , SM/16411 | Augmentation | Electric Service Connection at SABARMBATI PWSS ph ii, Application NO.3004494928, ID 304193739 | 187/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 4.81 | 0 | 0 | 0
2431 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. , SM/16411 | Augmentation | NEW SERVICE CONNECTION AT PWSS PANCHTHUPI PH 1 Z2 ID 304247057 | 313/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 7.38 | 0 | 0 | 0
2432 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Panchthupi Zone -II Water Supply Scheme Block - Burwan , Dist- Murshidabad. , SM/16411 | Augmentation | NEW SERVICE CONNECTION AT PWSS PANCHTHUPI PH3 Z2 ID 304247149 | 325/WBSEDCL-JJM | 06/02/2024 | 0 | WBSEDCL | 7.28 | 0 | 0 | 0
2433 | MURSHIDABAD | Murshidabad Division | Augmentation of Salar Zone- I B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. , SM/16423 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 1.62 | 100 | 80
2434 | MURSHIDABAD | Murshidabad Division | Augmentation of Salar Zone- I B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. , SM/16423 | Augmentation | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 0 | 20
2435 | MURSHIDABAD | Berhampore Division I | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS , SM/15996 | New | BELIA SYAMPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 611/BD-I | 02/08/2023 | 180 | ROY CONSTRUCTION (AVIJIT ROY) | 69 | 0 | 0 | 0
2436 | MURSHIDABAD | Berhampore Division I | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS , SM/15996 | New | Material Requisition To Resource Division | 61/BD-1/17 | 27/04/2023 | 0 | Resource Division | 11.74 | 0 | 0 | 0
2437 | MURSHIDABAD | Berhampore Mechanical | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS , SM/15996 | New | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Berhampore, Bhagawangola I and II, Domkal, Samserganj, Suti I and II block Under District Murshidabad under MEDB PHE Dte. | 45/2/MEDB | 29/05/2025 | 92 | M/S SAJAHAN CHOWDHURY | 21.32 | 0 | 0 | 0
2438 | MURSHIDABAD | Berhampore Division I | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS , SM/15996 | New | BELIA SYAMPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 214/BD-I | 17/05/2023 | 1081 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 40.8 | 13.26 | 32.5 | 50
2439 | MURSHIDABAD | Berhampore Mechanical | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS , SM/15996 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Belia Shyampur Pipe Water Supply Scheme Block - Bhagwangola-I District - Murshidabad Dist. - Murshidabad under MEDB, PHE Dte. | 320/MEDB | 10/02/2025 | 89 | SUNIL RABIDAS | 21.38 | 0 | 0 | 0
2440 | MURSHIDABAD | Berhampore Division I | BELIA SYAMPUR AND ADJOINING MOUJAS PWSS , SM/15996 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BELIA SHYAMPUR and Adjoining Mouzas PWSS (TW-I & II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-I Block under Berhampore Division-I, P.H.Engineering Dte. (02 Nos TW) | 849/BD-I | 23/06/2025 | 30 | JOY GURU ENTERPRISE | 17.75 | 0 | 0 | 0
2441 | MURSHIDABAD | Murshidabad Division | MASLA AND ADJOINING MOUJAS PWSS , SM/16529 | New | Material Requisition To Resource Division | 1075/MURD/14 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
2442 | MURSHIDABAD | Central Drilling | MASLA AND ADJOINING MOUJAS PWSS , SM/16529 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 2203/CDD | 01/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 0 | 0 | 10
2443 | MURSHIDABAD | Berhampore Mechanical | MASLA AND ADJOINING MOUJAS PWSS , SM/16529 | New | MASLA PH-1 | 392/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 4.25 | 0 | 0 | 0
2444 | MURSHIDABAD | Berhampore Mechanical | MASLA AND ADJOINING MOUJAS PWSS , SM/16529 | New | MASLA PH-2 | 393/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 4.28 | 0 | 0 | 0
2445 | MURSHIDABAD | Berhampore Mechanical | MASLA AND ADJOINING MOUJAS PWSS , SM/16529 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under MASLA ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | 2089/MEDB | 19/06/2023 | 896 | M/S S. S. ENTERPRISE (DOMKAL) | 21.56 | 15.89 | 73.74 | 10
2446 | MURSHIDABAD | Murshidabad Division | MASLA AND ADJOINING MOUJAS PWSS , SM/16529 | New | MASLA PWSS under Jal Jeevan Mission of BHARATPUR - I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | 1996/MURD | 21/07/2023 | 300 | A.K. INSDUSTRIES | 239.5 | 58.19 | 24.3 | 75
2447 | MURSHIDABAD | Berhampore Mechanical | KALGRAM AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16388 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under KALGRAM ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | 1926/MEDB | 16/06/2023 | 92 | BHABANI PRASAD MANNA | 21.1 | 0 | 0 | 0
2448 | MURSHIDABAD | Murshidabad Division | KALGRAM AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16388 | New | Material Requisition To Resource Division | 1075/MURD/4 | 19/04/2023 | 0 | Resource Division | 20.47 | 0 | 0 | 0
2449 | MURSHIDABAD | Berhampore Mechanical | KALGRAM AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16388 | New | NEW SERVICE CONNECTION AT KALGRAM PH 2 ID 304158479 | 216/WBSEDCL-JJM | 05/01/2024 | 0 | WBSEDCL | 6.37 | 0 | 0 | 0
2450 | MURSHIDABAD | Murshidabad Division | KALGRAM AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16388 | New | Formal work order for KALGRAM & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of KHARGRAM Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 780/MURD | 20/03/2023 | 1278 | SOFIQUL ISLAM | 329.98 | 152.5 | 46.22 | 20
2451 | MURSHIDABAD | Murshidabad Division | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. , SM/16391 | New | Formal work order for Khodarampur CT PWSS Construction OHR, Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission, Block- Raghunathganj-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | 674/MURD | 09/03/2023 | 365 | R.K. CONSTRUCTTION | 227.03 | 0 | 0 | 0
2452 | MURSHIDABAD | Murshidabad Division | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. , SM/16391 | New | Material Requisition To Resource Division | 1230/MURD/25 | 04/05/2023 | 0 | Resource Division | 29.19 | 0 | 0 | 0
2453 | MURSHIDABAD | Murshidabad Division | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. , SM/16391 | New | Khodarampur CT PWSS to accommodate FHTC, Laying Distribution System, Rising Main, under Jal Jivan Mission, Block- Raghunathganj-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | 930/MURD | 31/03/2023 | 180 | TEKNO ENTERPRISE | 345.69 | 0 | 0 | 0
2454 | MURSHIDABAD | Berhampore Mechanical | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. , SM/16391 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under KHODARAMPUR(CT) ground water based water supply scheme under Block_ Raghunathganj- II Dist. - Murshidabad under MEDB, PHE Dte. | 4314/MEDB | 29/12/2023 | 91 | M/S S. G. ENTERPRISE | 22.57 | 0 | 0 | 0
2455 | MURSHIDABAD | Murshidabad Division | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. , SM/16391 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHODARAMPUR (CT) AND PRASADPUR ZONE-II Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | 2721/MURD | 29/08/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0 | 0
2456 | MURSHIDABAD | Murshidabad Division | KHODARAMPUR (CT) PIPED WATER SUPPLY SCHEME. , SM/16391 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.8 | 100 | 100
2457 | MURSHIDABAD | Berhampore Mechanical | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16396 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under AMLAI ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | 3694/MEDB | 03/11/2023 | 92 | B. T. PROJECTS PVT. LTD. | 26.12 | 0 | 0 | 0
2458 | MURSHIDABAD | Murshidabad Division | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16396 | New | Material Requisition To Resource Division | 1219/MURD/26 | 03/05/2023 | 0 | Resource Division | 19.9 | 0 | 0 | 0
2459 | MURSHIDABAD | Berhampore Mechanical | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16396 | New | Quotation for Amlai PH No-1 | 326/WBSEDCL-JJM | 06/02/2024 | 0 | WBSEDCL | 5.41 | 0 | 0 | 0
2460 | MURSHIDABAD | Berhampore Mechanical | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16396 | New | Quotation for Amlai PH No-2 | 327/WBSEDCL-JJM | 06/02/2024 | 0 | WBSEDCL | 11.27 | 0 | 0 | 0
2461 | MURSHIDABAD | Murshidabad Division | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16396 | New | Laying Distribution System of AMLAI PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Bharatpur-I Block, Kandi Sub-Division of Murshidabad Division ,PHE Dte. | 2886/MURD | 12/09/2023 | 842 | DHIRENDRANATH MONDAL | 591.68 | 327.74 | 55.39 | 10
2462 | MURSHIDABAD | Murshidabad Division | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16396 | New | Allied & Balance Work for Laying of Distribution System, Approach Service Road, Construction of Box Culvert and Land Development of AMLAI PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Bharatpur-I Block, Kandi Sub-Division of Murshidabad Division ,PHE Dte. | 55/MURD | 05/01/2024 | 605 | DHIRENDRANATH MONDAL | 53.07 | 28.72 | 54.11 | 10
2463 | MURSHIDABAD | Murshidabad Division | AMLAI AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16396 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at AMLAI and MATHUA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 2795/MURD | 04/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0 | 100
2464 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/16353 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under KOASBAGOAS ground water based water supply scheme under Block_ Raninagar-I Dist. - Murshidabad under MEDB, PHE Dte. | 3762/MEDB | 03/11/2023 | 92 | A.G. ENTERPRISE | 35.21 | 0 | 0 | 0
2465 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/16353 | Augmentation | Material Requisition To Resource Division | 194/BD-I/3 | 09/02/2024 | 0 | Resource Division | 55.6 | 0 | 0 | 0
2466 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/16353 | Augmentation | Meter shifting kasba goas pwss | 416/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 0.28 | 0 | 0 | 0
2467 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/16353 | Augmentation | NEW CONNECTION KASBAGOAS Z-I PH-I | 480/WBSEDCL-JJM | 21/03/2024 | 0 | WBSEDCL | 10.02 | 0 | 0 | 0
2468 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/16353 | Augmentation | NEW CONNECTION KASBAGOAS Z-I PH-II | 479/WBSEDCL-JJM | 21/03/2024 | 0 | WBSEDCL | 3.43 | 0 | 0 | 0
2469 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/16353 | Augmentation | Augmentation of Koasbagoas Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP), pump house and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | 375/BD-I | 28/06/2023 | 730 | MAMATA USHA ENTERPRISE | 534.97 | 287.74 | 53.79 | 75
2470 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/16353 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of KASBAGOAS ZONE-II PWSS under Jal Jeevan Mission within Raninagar -I Block under Berhampore Division-I, PHE.Dte.in the district of Murshidabad. | 875/BD-I | 01/07/2025 | 60 | TAIMUR SK | 16.51 | 0 | 0 | 0
2471 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/16353 | Augmentation | Construction Pump House Cum Chlorine Room at KASBAGOAS Water Supply Scheme under Jal Jevan Mission within Raninagar-I Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | 272/BD-I | 11/02/2025 | 60 | TAIMUR SK | 7.5 | 0 | 0 | 0
2472 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/16353 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KASBAGOAS Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1692/BD-I | 14/03/2023 | 10 | RADIANT | 2.67 | 2.67 | 100 | 100
2473 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/16353 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) of Ground Water Based Supply Scheme for Kasbagoas of Raninagar-I block under Berhampore Division-I PHEDte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 1030/BD-I | 01/11/2023 | 30 | M/S. MONDAL ENTERPRISE 12/6/1, OLD POLICE LINE ROAD, GORABAZAR | 8.01 | 6.3 | 100 | 100
2474 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED KOASBAGOAS PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/16353 | Augmentation | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kasbagoas Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte.(For 3 nos. Tubewell) | 1146/BD-I | 04/12/2023 | 30 | MAMATA USHA ENTERPRISE | 34.71 | 29.87 | 100 | 100
2475 | MURSHIDABAD | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. , SM/15734 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0 | 0
2476 | MURSHIDABAD | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. , SM/15734 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 4.97 | 100 | 1
2477 | MURSHIDABAD | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. , SM/15734 | Augmentation | Material Requisition To Resource Division | 1219/MURD/01 | 03/05/2023 | 0 | Resource Division | 9.73 | 0 | 0 | 0
2478 | MURSHIDABAD | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. , SM/15734 | Augmentation | Laying of Distribution System for Augmentation of SARBANGAPUR ZONE-IB PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division ,PHE.Dte.(Part_C) | 1745/MURD | 06/07/2023 | 180 | BENGAL ENTERPRISE | 84.67 | 49.86 | 58.88 | 70
2479 | MURSHIDABAD | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. , SM/15734 | Augmentation | Construction of Boundary wall at Sarbangapur Zone-I, P.H-2 under Sarbangapur Zone-I Water Supply Scheme under Berhampore Sub-Division , P.H.E. Dte. in the District Murshidabad. (PART B- 55.0MTR.)_Part-B | 1028/MURD | 13/04/2023 | 30 | ABA CONTRACTOR | 4.63 | 4.2 | 100 | 100
2480 | MURSHIDABAD | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. , SM/15734 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I , II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sarbangapur Zone -IB Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Nawda Block under Murshidabad Division, P.H. Engineering Dte. | 3806/MURD | 12/12/2023 | 21 | MAMATA USHA ENTERPRISE | 18.45 | 16.05 | 100 | 100
2481 | MURSHIDABAD | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. , SM/15734 | Augmentation | Material Requisition To Resource Division | 1811/MURD/17 | 20/06/2024 | 0 | Resource Division | 9.93 | 0 | 0 | 0
2482 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. , SM/15734 | Augmentation | NEW SERVICE CONNECTION AT SARBANGAPUR PWSS Z1 PART B PH 2 C ID 304506962 | 333/WBSEDCL-JJM | 19/12/2024 | 0 | WBSEDCL | 3.44 | 0 | 0 | 0
2483 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. , SM/15734 | Augmentation | NEW SERVICE CONNECTION AT SARBANGAPUR PWSS Z1 PART B PH 2 C ID 304506962 |  | 11/12/2024 | 0 | WBSEDCL | 3.44 | 0 | 0 | 0
2484 | MURSHIDABAD | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. , SM/15734 | Augmentation | Construction 2 (Two ) Nos Pump House with clorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement and 210 mtr Boundary wall at Head Work site and 55Mtr at 2nd site of Sarbangapur Zone -IB , Bara Satui & Chandkati Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | 1930/MURD | 03/07/2024 | 537 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 52.14 | 0 | 0 | 75
2485 | MURSHIDABAD | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. , SM/15734 | Augmentation | Construction of Boundwary Wall , Pump House (Two nos), Construction of PCC approach road for Augmentation of SARBANGAPUR ZONE-IB PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division ,PHE.Dte. | 779/MURD | 14/03/2024 | 624 | STARK ENTERPRISE | 43.61 | 4.54 | 10.41 | 70
2486 | MURSHIDABAD | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. , SM/15734 | Augmentation | Providing 1612 nos FHTC Connection for Augmentation of SARBANGAPUR ZONE-IB PWSS in NAWDA Block , Berhampore Sub-Division under Murshidabad Division, PHE. Dte. | 1976/MURD | 08/07/2024 | 45 | DIPAK BHOWMIK | 84.07 | 0 | 0 | 0
2487 | MURSHIDABAD | Murshidabad Division | Augmentation of Sarbangapur Zone -IB Piped Water Supply Scheme Block - Nawda , Dist- Murshidabad. , SM/15734 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for SARBANGAPUR ZONE-I(Part -B) Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division, PHE Dte. | 1023/MURD | 05/05/2025 | 60 | TANUSHREE ENTERPRISE | 23.01 | 0 | 0 | 0
2488 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. , SM/16623 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0 | 0
2489 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. , SM/16623 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 5.27 | 100 | 1
2490 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. , SM/16623 | Augmentation | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MAHAMMADPUR Water Supply Scheme at Head Work Site, 2nd Site & 3 r d site at Nawda Block under Murshidabad Division, P.H. Engineering Dte | 1750/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 27.67 | 17.11 | 61.84 | 67
2491 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. , SM/16623 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV under MAHAMMADPUR ground water based water supply scheme under Block_ NAWDA Dist. - Murshidabad under MEDB, PHE Dte. | 1911/MEDB | 16/06/2023 | 92 | HANNAN BUILDERS PVT LTD | 44.47 | 30.65 | 68.92 | 70
2492 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. , SM/16623 | Augmentation | Providing FHTC Connection to 390 nos household , Laying of Distribution System, Rising Main , Construction of Pump House & Boundary Wall, repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity of staging height 20 mtr, Special repair and renovation of existing Pump House and Alied Works, Repairing & Vertical Extention of Boundary Wall for Augmentation work of MAHAMMADPUR PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. | 898/MURD | 29/03/2023 | 1073 | AJOY GHOSH | 171.58 | 88.59 | 51.63 | 40
2493 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. , SM/16623 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for MAHAMMADPUR Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division , PHE Dte. | 1022/MURD | 05/05/2025 | 60 | SUMAN ENTERPRISE AND SUMAN AQUA | 23 | 0 | 0 | 0
2494 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for MAHAMMADPUR Block - Nawda District - Murshidabad. , SM/16623 | Augmentation | Providing Balance Functional Household Tap Connection (FHTC) of 462 left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahammadpur (Village code 315549) under Mahammadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 802/MURD | 24/03/2022 | 30 | M/S. UNIQUE BUILDERS | 29.37 | 3.12 | 100 | 1
2495 | MURSHIDABAD | Berhampore Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS , SM/16789 | New | Material Requisition To Resource Division | 61/BD-1/22 | 27/04/2023 | 0 | Resource Division | 13.36 | 0 | 0 | 0
2496 | MURSHIDABAD | Berhampore Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS , SM/16789 | New | Material Requisition To Resource Division | 304/BD-1/10 | 22/02/2024 | 0 | Resource Division | 2.82 | 0 | 0 | 0
2497 | MURSHIDABAD | Berhampore Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS , SM/16789 | New | KALIAGACHI PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1258/BD-I | 22/12/2023 | 630 | SATELLITE CONSTRUCTION | 39.24 | 0 | 0 | 25
2498 | MURSHIDABAD | Berhampore Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS , SM/16789 | New | KALIAGACHI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 975/BD-I | 18/10/2023 | 531 | PRANAB KUMAR GHOSH | 61.78 | 4.5 | 7.29 | 25
2499 | MURSHIDABAD | Berhampore Mechanical | KALIAGACHHI AND ADJOINING MOUJAS PWSS , SM/16789 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Kaliagachhi Piped Water Supply Scheme Block Lalgola, District - Murshidabad. under MEDB, PHE Dte. | 314/MEDB | 10/02/2025 | 89 | P. K. ENGINEERING | 21.38 | 0 | 0 | 0
2500 | MURSHIDABAD | Berhampore Division I | KALIAGACHHI AND ADJOINING MOUJAS PWSS , SM/16789 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KALIGACHHI Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 13/BD-I | 06/01/2025 | 90 | HARUN ALL RASHID & BROTHERS | 8.91 | 0 | 0 | 100
2501 | MURSHIDABAD | Murshidabad Division | KELAI AND IT'S ADJOINING MOUJAS , SM/15680 | New | Laying Distribution System Part-A , Rising Main Connection FHTC, for Kelai water supply scheme of Khargram Block under Murshidabad Division, PHE Dte. | 1257/MURD | 08/05/2023 | 180 | M/S CARE | 352.42 | 112.26 | 31.85 | 10
2502 | MURSHIDABAD | Berhampore Mechanical | KELAI AND IT'S ADJOINING MOUJAS , SM/15680 | New | SHIFTING OF 11KV AT KELAI | 439/WBSEDCL-JJM | 13/03/2024 | 0 | WBSEDCL | 3.39 | 0 | 0 | 0
2503 | MURSHIDABAD | Murshidabad Division | KELAI AND IT'S ADJOINING MOUJAS , SM/15680 | New | Formal work order for KELAI (PART-B) & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- KHARGRAM of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | 753/MURD | 16/03/2023 | 1022 | NURTAJ SHAIKH | 217.79 | 96.35 | 44.24 | 18
2504 | MURSHIDABAD | Berhampore Mechanical | KELAI AND IT'S ADJOINING MOUJAS , SM/15680 | New | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Kelai ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | 763/MEDB | 20/02/2024 | 680 | M/S S. S. ENTERPRISE (DOMKAL) | 23.25 | 0 | 0 | 40
2505 | MURSHIDABAD | Murshidabad Division | KELAI AND IT'S ADJOINING MOUJAS , SM/15680 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kelai & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | 1105/MURD | 24/04/2023 | 30 | NADIA TUBEWELLS | 21.35 | 17.32 | 100 | 100
2506 | MURSHIDABAD | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. , SM/16051 | New | Ground Water based piped water supply scheme for Kharsa Part- E village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2343/MURD | 03/08/2023 | 60 | SUGATA CHOWDHURY | 30.55 | 25.82 | 84.53 | 10
2507 | MURSHIDABAD | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. , SM/16051 | New | Ground Water based piped water supply scheme for Kharsa Part- C village, Block:- Khargram, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2342/MURD | 03/08/2023 | 60 | M/S SAJAHAN CHOWDHURY | 30.48 | 12.67 | 41.56 | 10
2508 | MURSHIDABAD | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. , SM/16051 | New | Ground Water based piped water supply scheme for Kharsa Part- B village, Block:- Khargram, Kandi Sub Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2341/MURD | 03/08/2023 | 1033 | J.S. CONSTRUCTION | 30.54 | 0 | 0 | 15
2509 | MURSHIDABAD | Murshidabad Division | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. , SM/16051 | New | Ground Water based piped water supply scheme for Kharsa Part- D village, Block:- Khargram, Kandi Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3035/MURD | 27/09/2023 | 852 | S.N. ENTERPRISE | 29.6 | 10.16 | 34.31 | 10
2510 | MURSHIDABAD | Berhampore Mechanical | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. , SM/16051 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works in connection to Accommodate FHTC at Kharsa Pump House-I ground water based water supply scheme under Block_ Khargram Dist. Murshidabad under MEDB, PHE Dte. | 51/MEDB | 09/01/2025 | 90 | M/S SAMRIDDHI ENTERPRISE | 11.28 | 0 | 0 | 0
2511 | MURSHIDABAD | Berhampore Mechanical | KHARSA PIPED WATER SUPPLY SCHEME, BLOCK- KHARGRAM , DISTRICT- MURSHIDABAD. , SM/16051 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works in connection to Accommodate FHTC at Kharsa Pump House-II ground water based water supply scheme under Block_ Khargram Dist. Murshidabad under MEDB, PHE Dte. | 52/MEDB | 09/01/2025 | 90 | M/S SAMRIDDHI ENTERPRISE | 11.28 | 0 | 0 | 0
2512 | MURSHIDABAD | Murshidabad Division | ALAMPUR AND ADJOINING MOPUJAS PWSS , SM/16813 | New | Material Requisition To Resource Division | 1129/MURD/2 | 25/04/2023 | 0 | Resource Division | 22.13 | 0 | 0 | 0
2513 | MURSHIDABAD | Murshidabad Division | ALAMPUR AND ADJOINING MOPUJAS PWSS , SM/16813 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BIPRA SEKHAR AND ADJOINING MOUJAS Water Supply Scheme & ALAMPUR Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 2807/MURD | 05/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 16.79 | 100 | 100
2514 | MURSHIDABAD | Berhampore Mechanical | ALAMPUR AND ADJOINING MOPUJAS PWSS , SM/16813 | New | AT ALAMPUR PH 1 ID 304239409 | 357/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 8.13 | 0 | 0 | 0
2515 | MURSHIDABAD | Berhampore Mechanical | ALAMPUR AND ADJOINING MOPUJAS PWSS , SM/16813 | New | AT ALAMPUR PH 2 ID 304239407 | 356/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 6.44 | 0 | 0 | 0
2516 | MURSHIDABAD | Berhampore Mechanical | ALAMPUR AND ADJOINING MOPUJAS PWSS , SM/16813 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Alampur ground water based water supply scheme under Block-Kandi Dist. - Murshidabad under MEDB, PHE Dte. | 3679/MEDB | 03/11/2023 | 789 | SURAKSHA | 22.8 | 0 | 0 | 70
2517 | MURSHIDABAD | Murshidabad Division | ALAMPUR AND ADJOINING MOPUJAS PWSS , SM/16813 | New | Construction of Ground Water Based ALAMPUR AND ADJOINING MOUZAS PWSS of accommodate FHTC( 960 Nos), Laying Distribution System, Laying Rising Main,, Switch Room, Boundary Wall, 150 CUM OHR in Kandi Block within Murshidabad District under Murshidabad Division, PHE Dte. | 3316/MURD | 22/10/2023 | 710 | H.MONDAL CONSTRUCTION | 234.45 | 96.44 | 41.13 | 50
2518 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/15748 | Augmentation | Material Requisition To Resource Division | 1219/MURD/24 | 03/05/2023 | 0 | Resource Division | 51.16 | 0 | 0 | 0
2519 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/15748 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IV under Rejinagar ground water based water supply scheme under Block_ Beldanga_II Dist. - Murshidabad under MEDB, PHE Dte. | 3675/MEDB | 03/11/2023 | 92 | SREE RADHA ELECTRICAL | 25.04 | 18.82 | 75.18 | 7
2520 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/15748 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 2.57 | 100 | 100
2521 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/15748 | Augmentation | Material Requisition To Resource Division | 1811/MURD/22 | 20/06/2024 | 0 | Resource Division | 6.47 | 0 | 0 | 0
2522 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/15748 | Augmentation | NEW CONNECTION REJINAGAR Z-IV PH-I | 421/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 3.61 | 0 | 0 | 0
2523 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/15748 | Augmentation | Providing FHTC Connection to 1050 nos household , Construction of 450 Cum OHR, Laying of Distribution System, Rising Main ,Construction of Boundary Wall and Pump House with sanitary and Water Supply Arrangement for Augmentation work of REJINAGAR ZONE-IV Beldanga -II Block under Murshidabad Division , PHE. Dte. | 2469/MURD | 09/08/2023 | 1006 | M/S. S.C. CIVIL ENTERPRISES | 482.41 | 90.73 | 18.81 | 45
2524 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-IV piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/15748 | Augmentation | Construction of Approach Road , Drain and Drum sheet walling work at Rejinagar Zone - IV PWSS in Beldanga-II Block of Berhampore Sub-Division under Murshidabad P.H.E. Dte. | 3176/MURD | 05/12/2024 | 30 | MUKTI ENTERPRISE | 15.17 | 0 | 0 | 0
2525 | MURSHIDABAD | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. , SM/15749 | Augmentation | Material Requisition To Resource Division | 1043/MURD/3 | 17/04/2023 | 0 | Resource Division | 31.92 | 0 | 0 | 0
2526 | MURSHIDABAD | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. , SM/15749 | Augmentation | Material Requisition To Resource Division | 1295/MURD/05 | 11/05/2023 | 0 | Resource Division | 61.11 | 0 | 0 | 0
2527 | MURSHIDABAD | Berhampore Mechanical | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. , SM/15749 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III under Gokarna ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | 3665/MEDB | 03/11/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 34.39 | 25.63 | 74.52 | 60
2528 | MURSHIDABAD | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. , SM/15749 | Augmentation | Material Requisition To Resource Division | 79/MURD/09 | 09/01/2024 | 0 | Resource Division | 31.88 | 0 | 0 | 0
2529 | MURSHIDABAD | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. , SM/15749 | Augmentation | Laying Distribution System & Functional Household Tap Connection (FHTC) for Augmentation of GOKARNA Water Supply Scheme under Murshidabad Division, P.H.E.Dte. | 1141/MURD | 26/04/2023 | 1071 | M/S.TAPAS KUMAR CHAKRABORTY | 252.26 | 32.42 | 12.85 | 30
2530 | MURSHIDABAD | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. , SM/15749 | Augmentation | Laying Distribution System & Functional Household Tap Connection (FHTC) for Augmentation of GOKARNA Water Supply Scheme under Murshidabad Division, P.H.E.Dte.(PART-C) | 1140/MURD | 26/04/2023 | 1071 | M/S.TAPAS KUMAR CHAKRABORTY | 358.04 | 154.01 | 43.02 | 30
2531 | MURSHIDABAD | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. , SM/15749 | Augmentation | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS GOKARNA PWSS Scheme, Block-KANDI to be Augmention/Rejuvination under Murshidabad Division, P.H.E. Dte. | 3258/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 8.11 | 8.11 | 100 | 1
2532 | MURSHIDABAD | Murshidabad Division | Augmentation of ground water based piped water sypply scheme for Gokarna Block - Kandi, Dist- Murshidabad. , SM/15749 | Augmentation | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-I of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gokarna & adjoining mouzas Water Supply Scheme at Head work site at Kandi Block under Murshidabad Division, P.H. Engineering Dte. | 1106/MURD | 24/04/2023 | 526 | INDRAJIT MAZUMDAR | 10.68 | 0 | 0 | 90
2533 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-XV & XVII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . , SM/16985 | Retrofitting | Last mile connectivity and providing 3451 nos Functional House Hold Connection from Zone- XVII of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . | 2696/MURD | 25/08/2023 | 120 | M/S. BIMALENDU BOSE | 206.76 | 0 | 0 | 0
2534 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-XV & XVII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . , SM/16985 | Retrofitting | Last mile connectivity and providing 7237 nos Functional House Hold Connection from Zone- XV of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . | 2694/MURD | 25/08/2023 | 120 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 427.97 | 0 | 0 | 0
2535 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-VI & VII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . , SM/16988 | Retrofitting | Last mile connectivity and providing 4285 nos Functional House Hold Connection from Zone- VI of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. | 2920/MURD | 14/09/2023 | 120 | DOBAY CONSTRUCTION | 244.28 | 0 | 0 | 0
2536 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-VI & VII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . , SM/16988 | Retrofitting | Last mile connectivity and providing 5696 nos Funcational House Hold Connection from Zone-VII of Surface water based BALIA water supply scheme in Sagardighi Block under Murshidabad Division PHE Dte . | 1848/MURD | 25/06/2024 | 120 | M/S BOSE & CO. | 334.91 | 0 | 0 | 0
2537 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-VIII & XII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . , SM/16989 | Retrofitting | Last mile connectivity and providing 8317 nos Functional House Hold Connection from Zone- XII of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte | 2691/MURD | 25/08/2023 | 120 | MAMATA USHA ENTERPRISE | 487.03 | 0 | 0 | 0
2538 | MURSHIDABAD | Murshidabad Division | CHHATRAPUR AND IT'S ADJOINING MOUJAS PWSS , SM/16867 | New | Material Requisition To Resource Division | 1075/MURD/10 | 19/04/2023 | 0 | Resource Division | 2.47 | 0 | 0 | 0
2539 | MURSHIDABAD | Murshidabad Division | CHHATRAPUR AND IT'S ADJOINING MOUJAS PWSS , SM/16867 | New | CHHATRAPUR PWSS under Jal Jeevan Mission of BHARATPUR -I Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | 3034/MURD | 27/09/2023 | 705 | MONDAL ENTERPRISE | 133.95 | 0 | 0 | 30
2540 | MURSHIDABAD | Murshidabad Division | CHHATRAPUR AND IT'S ADJOINING MOUJAS PWSS , SM/16867 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHHATRAPUR AND IT'S ADJOINING MOUJAS PWSS Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur - I Block under Murshidabad Division, P.H. Engineering Dte | 3410/MURD | 02/11/2023 | 500 | GENUINE | 18.43 | 0 | 0 | 100
2541 | MURSHIDABAD | Murshidabad Division | PASCHIM PUNROPARA (CT) ZONE-I PIPED WATER SUPPLY SCHEME. , SM/19121 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 2.06 | 100 | 80
2542 | MURSHIDABAD | Murshidabad Division | PASCHIM PUNROPARA (CT) ZONE-I PIPED WATER SUPPLY SCHEME. , SM/19121 | New | Paschim Punropara Zone - I PWSS to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 1 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 2nos, Construction of Boundary Wall of 220 m, Construction 750 Cum OHR with sub soil investigation Jal Jivan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE. Dte. (part-B) | 105/MURD | 10/01/2024 | 934 | M/S. A.T.D. PROJECTS | 289.17 | 0 | 0 | 0
2543 | MURSHIDABAD | Murshidabad Division | PASCHIM PUNROPARA (CT) ZONE-I PIPED WATER SUPPLY SCHEME. , SM/19121 | New | Paschim Punropara Zone - I PWSS to accommodate FHTC of 4363 nos household, Laying Distribution System, Laying Rising Main under Jal Jivan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (part-1) | 83/MURD | 09/01/2024 | 365 | M/S. BIMALENDU BOSE | 432.11 | 0 | 0 | 0
2544 | MURSHIDABAD | Murshidabad Division | PASCHIM PUNROPARA (CT) ZONE-I PIPED WATER SUPPLY SCHEME. , SM/19121 | New | Allied work for construction of culvert at Paschim Puranpara(CT) Zone -I H/W site and approach road for H/W site Augmentation work under Jangipur sub division P.H.E Dte. | 2182/MURD | 31/07/2024 | 335 | M/S MONDAL CONSTRUCTION | 16.73 | 0 | 0 | 100
2545 | MURSHIDABAD | Murshidabad Division | PASCHIM PUNROPARA (CT) ZONE-I PIPED WATER SUPPLY SCHEME. , SM/19121 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 10.44 | 100 | 100
2546 | MURSHIDABAD | Murshidabad Division | AOCHA AND ADJJOINING MOUJAS PWSS , SM/18470 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at AOCHA AND ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur - II Block under Murshidabad Division, P.H. Engineering Dte. | 2633/MURD | 23/08/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 27.64 | 23.52 | 100 | 30
2547 | MURSHIDABAD | Murshidabad Division | AOCHA AND ADJJOINING MOUJAS PWSS , SM/18470 | New | Allied & Balance work for Road Restoration of Damaged During Laying of pipeline and Laying of distribution pipe line of AOCHA Piped Water Supply Scheme, Bharatpur-II Block, Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | 818/MURD | 15/03/2024 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 33.81 | 32.68 | 100 | 10
2548 | MURSHIDABAD | Berhampore Mechanical | AOCHA AND ADJJOINING MOUJAS PWSS , SM/18470 | New | NEW CONNECTION AT AOUCHA PH-I | 138/WBSEDCL-JJM | 09/07/2024 | 0 | WBSEDCL | 3.13 | 0 | 0 | 0
2549 | MURSHIDABAD | Berhampore Mechanical | AOCHA AND ADJJOINING MOUJAS PWSS , SM/18470 | New | NEW CONNECTION AT AOUCHA PH-I |  | 02/07/2024 | 0 | WBSEDCL | 3.13 | 0 | 0 | 0
2550 | MURSHIDABAD | Berhampore Mechanical | AOCHA AND ADJJOINING MOUJAS PWSS , SM/18470 | New | SHIFTING OF 11 KV AT AOCHA | 427/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 4.29 | 0 | 0 | 0
2551 | MURSHIDABAD | Berhampore Mechanical | AOCHA AND ADJJOINING MOUJAS PWSS , SM/18470 | New | NEW CONNECTION AT AOCHA PH-II | 179/WBSEDCL-JJM | 06/08/2024 | 0 | WBSEDCL | 3.7 | 0 | 0 | 0
2552 | MURSHIDABAD | Berhampore Mechanical | AOCHA AND ADJJOINING MOUJAS PWSS , SM/18470 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under AOCHA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | 2768/MEDB | 25/07/2023 | 707 | EASTERN INDIA SALES & SERVICE | 35.18 | 19.39 | 55.11 | 100
2553 | MURSHIDABAD | Murshidabad Division | Augmentation of Putia Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/19016 | Augmentation | Augmentation of Ground Water Based Putia Zone-II PWS accommodate FHTC, Laying Distribution System, Laying Rising Main in Raghunathganj - II Block within Murshidabad District under Murshidabad Division, PHE Dte.(PART-A) | 3343/MURD | 28/10/2023 | 365 | MARUTI CONSTRUCTION AND CO. | 143.58 | 0 | 0 | 0
2554 | MURSHIDABAD | Murshidabad Division | Augmentation of Putia Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/19016 | Augmentation | Augmentation of Putia Zone - II PWSS to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 1 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 1no, Construction of Boundary Wall of 150 m & Construction of 400 Cum OHR with sub soil investigation under Jal Jeevan Mission of Raghunathganj II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (PART-B) | 3341/MURD | 28/10/2023 | 365 | DADA BHAI CONSTRUCTION | 185.23 | 0 | 0 | 0
2555 | MURSHIDABAD | Murshidabad Division | Augmentation of Putia Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/19016 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.47 | 100 | 100
2556 | MURSHIDABAD | Murshidabad Division | Augmentation of Putia Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/19016 | Augmentation | Material Requisition To Resource Division | 1167/MURD/10 | 28/04/2023 | 0 | Resource Division | 24.14 | 0 | 0 | 0
2557 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Putia Zone-II Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/19016 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV ,Zone-II under PUTIA ground water based water supply scheme under Block_ Raghunathganj-II Dist. - Murshidabad under MEDB, PHE Dte. | 3722/MEDB | 03/11/2023 | 3 | GHOSH BROTHERS | 41.63 | 0 | 0 | 40
2558 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BEWA-II PIPED WATER SUPPLY SCHEME. , SM/19018 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 0 | 10
2559 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BEWA-II PIPED WATER SUPPLY SCHEME. , SM/19018 | Augmentation | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0 | 0
2560 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BEWA-II PIPED WATER SUPPLY SCHEME. , SM/19018 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BEWA -II Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Farakka Block under Murshidabad Division, P.H. Engineering Dte | 3769/MURD | 08/12/2023 | 540 | HARUN ALL RASHID & BROTHERS | 35.3 | 17.77 | 73.88 | 100
2561 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BEWA-II PIPED WATER SUPPLY SCHEME. , SM/19018 | Augmentation | Balance Work of Road restoration damaged during laying of pipeline of Bewa Zone-II Piped Water Supply Scheme, Farakka Block, Jangipur Sub-Division under Murshidabad Division, P.H.E dte. | 824/MURD | 15/03/2024 | 624 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 11.51 | 0 | 0 | 100
2562 | MURSHIDABAD | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/19111 | Augmentation | Material Requisition To Resource Division | 1210/MURD/07 | 02/05/2023 | 0 | Resource Division | 69.83 | 0 | 0 | 0
2563 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/19111 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-I under AMINABAD ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | 4306/MEDB | 29/12/2023 | 91 | M/S SAMRIDDHI ENTERPRISE | 34.41 | 0 | 0 | 0
2564 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/19111 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Exsisting Pump House No. I and II under BALLALPUR PIPED WATER SUPPLY SCHEME, BLOCK- FARAKKA, DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | 1144/MEDB | 14/05/2025 | 92 | M/S SAMRIDDHI ENTERPRISE | 24.17 | 0 | 0 | 0
2565 | MURSHIDABAD | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/19111 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 0 | 0 | 100
2566 | MURSHIDABAD | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/19111 | Augmentation | Augmentation of AMINABAD ZONE-I Piped Water Supply Scheme under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE. Dte. | 3952/MURD | 26/12/2023 | 724 | M/S GUHA & ROY ENTERPRISE | 446.08 | 278.28 | 62.38 | 75
2567 | MURSHIDABAD | Murshidabad Division | Augmentation of Aminabad Piped Water Supply Scheme (Zone-I) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/19111 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 4.29 | 100 | 100
2568 | MURSHIDABAD | Berhampore Mechanical | SRIKANTABATI (CT) PART -A PIPED WATER SUPPLY SCHEME. , SM/18691 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under SRIKANTABATI(CT) ,PART-A ground water based water supply scheme under Block_ Raghunathganj-I Dist. - Murshidabad under MEDB, PHE Dte. | 3727/MEDB | 03/11/2023 | 92 | MENAKA ENTERPRISE | 33.53 | 0 | 0 | 0
2569 | MURSHIDABAD | Murshidabad Division | SRIKANTABATI (CT) PART -A PIPED WATER SUPPLY SCHEME. , SM/18691 | New | SRIKANTABATI (Part A) PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- RAGHUNATHGANJ-I of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | 2644/MURD | 23/08/2023 | 365 | BIJAY CHOWDHURY | 941.07 | 0 | 0 | 0
2570 | MURSHIDABAD | Murshidabad Division | SRIKANTABATI (CT) PART -A PIPED WATER SUPPLY SCHEME. , SM/18691 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SRIKANTABATI (CT) PART- A Water Supply Scheme at Head Work Site, 2nd Site site at Raghunathganj - I Block under Murshidabad Division, P.H. Engineering Dte. | 2824/MURD | 07/09/2023 | 21 | M. R. ENTERPRISE | 18.54 | 0 | 0 | 0
2571 | MURSHIDABAD | Murshidabad Division | SRIKANTABATI (CT) PART -A PIPED WATER SUPPLY SCHEME. , SM/18691 | New | Material Requisition To Resource Division | 1219/MURD/36 | 03/05/2023 | 0 | Resource Division | 29.51 | 0 | 0 | 0
2572 | MURSHIDABAD | Murshidabad Division | SRIKANTABATI (CT) PART -A PIPED WATER SUPPLY SCHEME. , SM/18691 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 6.9 | 100 | 100
2573 | MURSHIDABAD | Murshidabad Division | DAFAHAT (CT) PIPED WATER SUPPLY SCHEME. , SM/18692 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at DAFAHAT (CT) Water Supply Scheme at Head Work Site, 2nd Site site at Suti -II Block under Murshidabad Division, P.H. Engineering Dte. | 2822/MURD | 07/09/2023 | 21 | M. R. ENTERPRISE | 27.81 | 0 | 0 | 0
2574 | MURSHIDABAD | Murshidabad Division | DAFAHAT (CT) PIPED WATER SUPPLY SCHEME. , SM/18692 | New | Material Requisition To Resource Division | 1230/MURD/12 | 04/05/2023 | 0 | Resource Division | 57.56 | 0 | 0 | 0
2575 | MURSHIDABAD | Berhampore Mechanical | DAFAHAT (CT) PIPED WATER SUPPLY SCHEME. , SM/18692 | New | NEW CONNECTION DAFAHAT PH-I |  | 27/03/2024 | 0 | WBSEDCL | 5 | 0 | 0 | 0
2576 | MURSHIDABAD | Berhampore Mechanical | DAFAHAT (CT) PIPED WATER SUPPLY SCHEME. , SM/18692 | New | NEW CONNECTION DAFAHAT PH-I | 5/WBSEDCL-JJM | 09/04/2024 | 0 | WBSEDCL | 5 | 0 | 0 | 0
2577 | MURSHIDABAD | Berhampore Mechanical | DAFAHAT (CT) PIPED WATER SUPPLY SCHEME. , SM/18692 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV under DAFAHAT(CT) ground water based water supply scheme under Block_ Suti- II Dist. - Murshidabad under MEDB, PHE Dte. | 3723/MEDB | 03/11/2023 | 881 | M/S SAJAHAN CHOWDHURY | 44.69 | 36.89 | 82.55 | 35
2578 | MURSHIDABAD | Murshidabad Division | DAFAHAT (CT) PIPED WATER SUPPLY SCHEME. , SM/18692 | New | DAFAHAT CT PWSS to accommodate FHTC, Laying Distribution System, Rising Main, under Jal Jeevan Mission of Suti-II Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE. Dte | 2403/MURD | 07/08/2023 | 720 | MOTI RAHAMAN | 378.32 | 337.49 | 89.21 | 95
2579 | MURSHIDABAD | Murshidabad Division | DAFAHAT (CT) PIPED WATER SUPPLY SCHEME. , SM/18692 | New | DAFAHAT CT PWSS to accommodate 700 cum OHR ( Dept Drg No.PC-I/OHR/6/2012), 2 Nos Pump House, 2 No Boundary Wall & Path Way under Jal Jeevan Mission of Suti - II Block, Murshidabad District under Jangipur SubDivision Murshidabad Division, PHE. Dte. | 2410/MURD | 07/08/2023 | 725 | M/S. MAYA CONSTRUCTION | 270.75 | 67.8 | 25.04 | 5
2580 | MURSHIDABAD | Murshidabad Division | DAFAHAT (CT) PIPED WATER SUPPLY SCHEME. , SM/18692 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 9.39 | 100 | 100
2581 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Bhairab Danga village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2869/MURD | 11/09/2023 | 60 | SAIF TRADERS | 34.71 | 0 | 0 | 0
2582 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Gangin village, Block:- Suti- I, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2835/MURD | 07/09/2023 | 60 | PRASANTA BISWAS | 24.4 | 0 | 0 | 0
2583 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Raghupur village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2832/MURD | 07/09/2023 | 60 | MINA DAS | 34.79 | 0 | 0 | 0
2584 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Raghunathpur village, Block:- Suti- I, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2837/MURD | 07/09/2023 | 60 | JYOTI TRADERS | 26.44 | 0 | 0 | 0
2585 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Berbari village, Block:- Bharatpur-I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2986/MURD | 21/09/2023 | 60 | PAMIR ROY | 33.05 | 0 | 0 | 0
2586 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Mas Danga village, Block:- Domkal, Islampur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2987/MURD | 21/09/2023 | 60 | SHIBAM ENTERPRISE | 28.21 | 0 | 0 | 0
2587 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Bilkurul village, Block:- Bharatpur-I, Kandi Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3464/MURD | 06/11/2023 | 60 | SK CONSTRUCTION (NAJIR SK.) | 30.77 | 0 | 0 | 0
2588 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Par Debidaspur village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3648/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0 | 0
2589 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Saheb Nagar village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3655/MEDB | 03/11/2023 | 92 | T. N. BANERJEE | 6.15 | 0 | 0 | 0
2590 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bhairab Danga village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3624/MEDB | 03/11/2023 | 92 | M/S S. S. ENTERPRISE (DOMKAL) | 6.15 | 0 | 0 | 0
2591 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bilkurul village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3625/MEDB | 03/11/2023 | 92 | P. K. ENGINEERING | 6.14 | 0 | 0 | 0
2592 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Baje Chuator village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3617/MEDB | 03/11/2023 | 92 | HARA PROSAD DAS | 6.27 | 0 | 0 | 0
2593 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Gangin village, Block:- Suti-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3633/MEDB | 03/11/2023 | 92 | ASSOCIATED ELECTRICAL CO. | 6.3 | 0 | 0 | 0
2594 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Jot Sundar village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3636/MEDB | 03/11/2023 | 92 | DAS ENTERPRISE (CHOA) | 6.3 | 0 | 0 | 0
2595 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bamandasbati village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3620/MEDB | 03/11/2023 | 92 | ARINDAM MAJUMDAR | 6.27 | 0 | 0 | 0
2596 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bazeosmanpur village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3622/MEDB | 03/11/2023 | 92 | M/S S. S. ENTERPRISE (DOMKAL) | 6.15 | 0 | 0 | 0
2597 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Ramdova village, Block:- Suti-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3652/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 6.3 | 0 | 0 | 0
2598 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Abbhla village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3616/MEDB | 03/11/2023 | 92 | HARA PROSAD DAS | 6.27 | 0 | 0 | 0
2599 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Sunda village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3657/MEDB | 03/11/2023 | 92 | ASSOCIATED ELECTRICAL CO. | 6.3 | 0 | 0 | 0
2600 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Abbhla village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 3465/MURD | 06/11/2023 | 60 | RURAL CONSTRUCTION | 31.63 | 0 | 0 | 0
2601 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Raghunathpur village, Block:- Suti-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3650/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0 | 0
2602 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Raghupur village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3651/MEDB | 03/11/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0 | 0
2603 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bajitpur village, Block:- Khargram under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3618/MEDB | 03/11/2023 | 92 | JOY BISHNU ENGINEERING CO. | 6.3 | 0 | 0 | 0
2604 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Balichuna village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3619/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 6.3 | 0 | 0 | 0
2605 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Bansbere village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3621/MEDB | 03/11/2023 | 92 | ASSOCIATED ELECTRICAL CO. | 6.3 | 0 | 0 | 0
2606 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chator village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3629/MEDB | 03/11/2023 | 92 | MERCURY ENGINEERING CO | 6.33 | 0 | 0 | 0
2607 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Berbari village, Block:- Bharatpur-I under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3623/MEDB | 03/11/2023 | 92 | M/S S. S. ENTERPRISE (DOMKAL) | 6.15 | 0 | 0 | 0
2608 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chak Gupura Part-B village, Block:- Bharatpur-II under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3626/MEDB | 03/11/2023 | 92 | P. K. ENGINEERING | 6.14 | 0 | 0 | 0
2609 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kayemba village, Block:- Kandi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3641/MEDB | 03/11/2023 | 92 | MASSK ENGINEERING WORKS | 6.15 | 0 | 0 | 0
2610 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Jot Raghu village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3635/MEDB | 03/11/2023 | 92 | DAS ENTERPRISE (CHOA) | 6.3 | 0 | 0 | 0
2611 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Lakshmipur village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3643/MEDB | 03/11/2023 | 92 | JOY BISHNU ENGINEERING CO. | 6.3 | 0 | 0 | 0
2612 | MURSHIDABAD | Berhampore Mechanical | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Name of Work: Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Nagri village, Block:- Farakka under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3646/MEDB | 03/11/2023 | 92 | ALAK KUMAR CHAKRABORTY | 6.15 | 0 | 0 | 0
2613 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Lakshmipur village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2828/MURD | 07/09/2023 | 847 | DEBOJYOTI CONSTRUCTION | 24.68 | 16.16 | 65.49 | 60
2614 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Sudna village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2871/MURD | 11/09/2023 | 60 | SO-FINE AQUARIUM | 36.59 | 5.15 | 14.08 | 50
2615 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Bazeosmanpur village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2829/MURD | 07/09/2023 | 60 | KALAM SK. | 24.4 | 3.64 | 14.9 | 60
2616 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Jot Raghu village, Block:- Farakka, Jangipur Sub-Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2984/MURD | 21/09/2023 | 833 | RAJIB SAHA | 28.21 | 6.55 | 23.21 | 30
2617 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Char Juranpur village, Block:- Domkal, Islampur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2872/MURD | 11/09/2023 | 60 | R.S CONSTRUCTION (PART- ROBIN ROY) | 23.3 | 0 | 0 | 0
2618 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Ramdova village, Block:- Suti- I, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2836/MURD | 07/09/2023 | 1027 | K. B. CONSTRUCTION (PROP.KUNTAL BHATTACHARYA) | 26.05 | 9.15 | 35.12 | 65
2619 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Jot Sundar village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2830/MURD | 07/09/2023 | 907 | FRIENDS CONSTRUCTION | 34.71 | 0 | 0 | 40
2620 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Chator village, Block:- Kandi, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2834/MURD | 07/09/2023 | 725 | SUMAN ENTERPRISE AND SUMAN AQUA | 39.37 | 5.08 | 12.91 | 25
2621 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Par Debidaspur village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2988/MURD | 21/09/2023 | 527 | PRADIP MAHATO | 37.08 | 2.69 | 7.24 | 60
2622 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Nagri village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2970/MURD | 20/09/2023 | 834 | DAS CONSTRACTION (MUNNA DAS) | 28.21 | 0 | 0 | 40
2623 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Baje Chuator village, Block:- Bharatpur-I, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2985/MURD | 21/09/2023 | 680 | PARTHA BHASKAR | 36.59 | 0 | 0 | 10
2624 | MURSHIDABAD | Murshidabad Division | IMPLEMENTATION OF STANDALONE WATER SUPPLY SYSTEM IN THE VILLAGES HAVING LESS THAN 100 HOUSEHOLD UNDER MURSHIDABAD DISTRICT PIPED WATER SUPPLY SCHEME PART-A , SM/18767 | New | Ground Water based mini piped water supply scheme for Saheb Nagar village, Block:- Farakka, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte | 3215/MURD | 13/10/2023 | 811 | BISWAJIT ROY | 29.49 | 6.54 | 22.16 | 80
2625 | MURSHIDABAD | Murshidabad Division | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. , SM/18737 | Augmentation | Material Requisition To Resource Division | 1278/MURD/15 | 10/05/2023 | 0 | Resource Division | 26.34 | 0 | 0 | 0
2626 | MURSHIDABAD | Murshidabad Division | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. , SM/18737 | Augmentation | Material Requisition To Resource Division | 79/MURD/10 | 09/01/2024 | 0 | Resource Division | 28.5 | 0 | 0 | 0
2627 | MURSHIDABAD | Murshidabad Division | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. , SM/18737 | Augmentation | Material Requisition To Resource Division | MURD/439/14 | 08/02/2024 | 0 | Resource Division | 25.58 | 0 | 0 | 0
2628 | MURSHIDABAD | Berhampore Mechanical | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. , SM/18737 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of KHARGRAM ground water based water supply scheme under Block- KHARGRAM Dist. Murshidabad under MEDB, PHE Dte. | 3239/MEDB | 22/08/2023 | 679 | DAS ENTERPRISE (CHOA) | 12.27 | 0 | 0 | 40
2629 | MURSHIDABAD | Murshidabad Division | Augmentation of KHARGRAM Piped Water Supply Scheme Block -Khargram District - Murshidabad. , SM/18737 | Augmentation | Sinking of 02 (Two) Nos of 300 mm x 200 mm dia tube well i.e. TW-I,III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Khargram & adjoining mouzas Water Supply Scheme at Head work site & 3rd Site at Khargram Block under Murshidabad Division, P.H. Engineering Dte. | 2702/MURD | 25/08/2023 | 585 | MAMATA USHA ENTERPRISE | 21.38 | 0 | 0 | 100
2630 | MURSHIDABAD | Murshidabad Division | KHARJJUNA AND ITS ADJOINING MOUJAS PWSS , SM/18464 | New | Material Requisition To Resource Division | 1219/MURD/19 | 03/05/2023 | 0 | Resource Division | 35.82 | 0 | 0 | 0
2631 | MURSHIDABAD | Berhampore Mechanical | KHARJJUNA AND ITS ADJOINING MOUJAS PWSS , SM/18464 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV under KHARJJUNA ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | 2769/MEDB | 25/07/2023 | 92 | DAS ENTERPRISE ( MANGO LANE) | 46.73 | 0 | 0 | 0
2632 | MURSHIDABAD | Berhampore Mechanical | KHARJJUNA AND ITS ADJOINING MOUJAS PWSS , SM/18464 | New | NEW SERVICE CONNECTION AT KHARJUNA PH 1 C ID 304391659 |  | 03/09/2024 | 0 | WBSEDCL | 3.34 | 0 | 0 | 0
2633 | MURSHIDABAD | Murshidabad Division | KHARJJUNA AND ITS ADJOINING MOUJAS PWSS , SM/18464 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHARJJUNA Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | 2635/MURD | 23/08/2023 | 587 | MAMATA USHA ENTERPRISE | 27.67 | 14.57 | 52.65 | 67
2634 | MURSHIDABAD | Murshidabad Division | KHARJJUNA AND ITS ADJOINING MOUJAS PWSS , SM/18464 | New | KHARJJUNA & adjoining mouzas PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | 2885/MURD | 12/09/2023 | 1024 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 1366.57 | 298.17 | 21.82 | 35
2635 | MURSHIDABAD | Murshidabad Division | BAHUTULI PIPRD WATER SUPPLY SCHEME. , SM/18693 | New | Material Requisition To Resource Division | 1219/MURD/36 | 03/05/2023 | 0 | Resource Division | 48.16 | 0 | 0 | 0
2636 | MURSHIDABAD | Berhampore Mechanical | BAHUTULI PIPRD WATER SUPPLY SCHEME. , SM/18693 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV under BAHUTULI ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | 4318/MEDB | 29/12/2023 | 91 | EASTERN INDIA SALES & SERVICE | 46.88 | 26.47 | 56.46 | 10
2637 | MURSHIDABAD | Murshidabad Division | BAHUTULI PIPRD WATER SUPPLY SCHEME. , SM/18693 | New | Sinking of 2NOS. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Raturi Zone-II Water Supply Scheme and Bahutuli Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | 2195/MURD | 31/07/2024 | 30 | SARKAR WATER SUPPLY AGENCY | 23.56 | 7.32 | 100 | 50
2638 | MURSHIDABAD | Murshidabad Division | BAHUTULI PIPRD WATER SUPPLY SCHEME. , SM/18693 | New | Material Requisition To Resource Division | 495/MURD/05 | 15/02/2024 | 0 | Resource Division | 23.89 | 0 | 0 | 0
2639 | MURSHIDABAD | Berhampore Mechanical | BAHUTULI PIPRD WATER SUPPLY SCHEME. , SM/18693 | New | NEW CONNECTION AT BAHUTALI PH-II | 34/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 5.25 | 0 | 0 | 0
2640 | MURSHIDABAD | Berhampore Mechanical | BAHUTULI PIPRD WATER SUPPLY SCHEME. , SM/18693 | New | NEW CONNECTION AT BAHUTALI PH-II |  | 02/08/2024 | 0 | WBSEDCL | 4.4 | 0 | 0 | 0
2641 | MURSHIDABAD | Berhampore Mechanical | BAHUTULI PIPRD WATER SUPPLY SCHEME. , SM/18693 | New | NEW CONNECTION AT BAHUTULI PH-II | 189/WBSEDCL-JJM | 12/08/2024 | 0 | WBSEDCL | 4.4 | 0 | 0 | 0
2642 | MURSHIDABAD | Berhampore Mechanical | BAHUTULI PIPRD WATER SUPPLY SCHEME. , SM/18693 | New | NEW CONNECTION AT BAHUTALI PH-III |  | 11/12/2024 | 0 | WBSEDCL | 6.18 | 0 | 0 | 0
2643 | MURSHIDABAD | Murshidabad Division | BAHUTULI PIPRD WATER SUPPLY SCHEME. , SM/18693 | New | CHANDMARI , BAHUTALI & FATELLAPUR PWSS to accommodate FHTC under Jal Jeevan Mission, Block- SUTI-I of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | 3176/MURD | 11/10/2023 | 813 | CHAKRABORTY CONSTRUCTION | 2258.18 | 159.88 | 14.47 | 10
2644 | MURSHIDABAD | Murshidabad Division | BAHUTULI PIPRD WATER SUPPLY SCHEME. , SM/18693 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 10.98 | 100 | 100
2645 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME , SM/18699 | Augmentation | Providing Vertical clear water pumping machinery atop extended Steel structure for feeding newly add Zone-I B and Zone-II B of Augmentation at Beniagram Surface Water Based water supply scheme. | 2596/MEDB | 30/09/2024 | 182 | B. T. PROJECTS PVT. LTD. | 88.81 | 0 | 0 | 0
2646 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME , SM/18699 | Augmentation | Material Requisition To Resource Division | 1341/BD-I/1 | 20/08/2024 | 0 | Resource Division | 89.82 | 0 | 0 | 0
2647 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME , SM/18699 | Augmentation | Material Requisition To Resource Division | 194/BD-I/1 | 09/02/2024 | 0 | Resource Division | 89.82 | 0 | 0 | 0
2648 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME , SM/18699 | Augmentation | Wayleave Facility Charge FOR Laying of 600MM Dia. Casing Pipe FOR Passing of 350MM Dia. Carrier Water Pipeline B/W KM-254/2-254/3 Between Station Ballalpur-New Farakka under Malda Division of Eastern Railway. | BP-2024-25-207 | 03/10/2024 | 0 | EASTERN RAILWAY MALDA DIVISION | 5.35 | 0 | 0 | 0
2649 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME , SM/18699 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Sundarpur ground water supply scheme in Bhagwabgola-I Block, Dist_Murshidabad under MEDB PHE Dte. | 1138/MEDB | 13/05/2025 | 92 | QUAZI NOZRUL ISLAM (PARTNERSHIP) | 39.58 | 0 | 0 | 0
2650 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME , SM/18699 | Augmentation | Augmentation of Beniagram Surface water based water supply scheme to accommodate construction of OHR, pump house and boundary wall, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Farakka Block of Murshidabad District under Berhampore Division-I,PHE.Dte. in the district Murshidabad. | 841/BD-I | 05/09/2023 | 365 | CHAKRABORTY CONSTRUCTION | 3038.97 | 305.29 | 10.05 | 50
2651 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME , SM/18699 | Augmentation | Augmentation of different units of WTP premises of Beniagram Water Supply scheme under, Berhampore Division -I PHE.Dte. under JJM | 945/BD-I | 11/06/2024 | 60 | P.M CONSTRUCTION | 97.98 | 17.2 | 17.55 | 25
2652 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME , SM/18699 | Augmentation | Repair and overhauling at filter beds including supply and filling of filter media alongwith allied works at R.G filter bed of Beniagram Surface Water Based water supply scheme in Farrakka block under Raghunathganj Sub division under Berhampore Division-I ,P.H.E Dte. | 849/BD-I | 05/09/2023 | 30 | P.M CONSTRUCTION | 21.01 | 21.01 | 100 | 10
2653 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BENIAGRAM SURFACE WATER BASED WATER SUPPLY SCHEME , SM/18699 | Augmentation | Rejuvenation of of 7.8 MLD Capacity Water Treatment Plant (Inlet well ,Flush Mixture ,Clarifoculator, Chemical Dosing and Filter House ) at Beniagram Under Berhampore Division - I , In The District Murshidabad , PHE Dte . | 117/BD-I | 30/01/2024 | 60 | P.M CONSTRUCTION | 144.24 | 137.72 | 100 | 10
2654 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. , SM/18703 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 4.51 | 100 | 80
2655 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. , SM/18703 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-III, BHANDARA ZONE - I and SURANGAPUR ZONE -I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 3785/MURD | 11/12/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 35.34 | 20.4 | 100 | 80
2656 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. , SM/18703 | Augmentation | NEW CONNECTION AT BHANDARA PH-II | 198/WBSEDCL-JJM | 22/08/2024 | 0 | WBSEDCL | 3.86 | 0 | 0 | 0
2657 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. , SM/18703 | Augmentation | NEW CONNECTION AT BHANDARA PH-II |  | 13/08/2024 | 0 | WBSEDCL | 3.86 | 0 | 0 | 0
2658 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. , SM/18703 | Augmentation | NEW CONNECTION AT BHANDARA PH-1 |  | 03/09/2024 | 0 | WBSEDCL | 5.5 | 0 | 0 | 0
2659 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. , SM/18703 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under Bhandara ground water based water supply scheme under Block_ Bhagwangola-I Dist. - Murshidabad under MEDB, PHE Dte. | 3701/MEDB | 03/11/2023 | 762 | A.G. ENTERPRISE | 23.33 | 0 | 0 | 12
2660 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. , SM/18703 | Augmentation | Construction of 600 Cum OHR, Rising Main, Pump House cum Chlorine Room with Sanitary and Water Supply Arrangement & Boundary Wall with R.C.C. column at Head Work Site & 2nd Tube Well Site for Augmentation of BHANDARA Zone-I Ground Based Water Supply Scheme under Bhawangola-I Block under Lalbagh Sub Division, Murshidabad Division ,P.H.E. Dte. In the District Murshidabad. | 3089/MURD | 03/10/2023 | 699 | NAMITA ENTERPRISE | 257.87 | 24.33 | 9.43 | 2
2661 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. , SM/18703 | Augmentation | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Block Bhagawangola-I & Lalgola of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Habaspur Water Supply Scheme, Bhandara Water Supply Scheme, Kantanagar Water Supply Scheme, Lalgola Water Supply Scheme. (Annexure-II) | 1928/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 8.78 | 2.23 | 100 | 100
2662 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. , SM/18703 | Augmentation | Laying Distribution System , FHTC for Augmentation of Bhandara Zone-I Water Supply Scheme in Bhawangola-II Block , under Murshidabad Division , PHE. Dte. | 1841/MURD | 25/06/2024 | 554 | DHIMAN SARKAR | 336.88 | 37.75 | 11.21 | 2
2663 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. , SM/18703 | Augmentation | Laying of distribution system for the left out portion of Bhandara Mouza Rising Main with DI pipe and interconnection with DI pipe at Head Work Site of Bhandara Zone - I & II Water Supply Scheme and Ancillary works in Lalbagh Sub Divisional Office under Lalbagh Sub Division, Murshidabad Division ,PHE Dte. | 1829/MURD | 18/08/2025 | 60 | MARUTI CONSTRUCTION AND CO. | 47.57 | 0 | 0 | 0
2664 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. , SM/18703 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 2.75 | 57.61 | 100
2665 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. , SM/18703 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Lalbagh Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | 2638/MURD | 23/09/2024 | 251 | ARJU CONSTRUCTION | 6.14 | 0 | 0 | 40
2666 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHANDARA ZONE-I. , SM/18703 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 4.79 | 100 | 100
2667 | MURSHIDABAD | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. , SM/18704 | Augmentation | Augmentation of Ground Water Based Loknathpur zone-I PWSS to accommodate FHTC of 922 nos household Laying Rising Main ,Construction Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) & Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement), Construction of Boundary Wall of 250 m and Soil Investigation & 150 Cum Construction of OHR and Special repair and renovation of existing 2 (Two) Nos Pump House and Boundary wall at Beldanga-II Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-B) | 3290/MURD | 19/10/2023 | 365 | VISION ENTERPRISE | 215.41 | 0 | 0 | 0
2668 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. , SM/18704 | Augmentation | Providing , installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I, Zone-I under Loknathpur ground water based water supply scheme under Block_ Beldanga_II Dist. - Murshidabad under MEDB, PHE Dte. | 3668/MEDB | 03/11/2023 | 92 | M/S SAJAHAN CHOWDHURY | 11.33 | 8.59 | 75.8 | 10
2669 | MURSHIDABAD | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. , SM/18704 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 2.55 | 100 | 100
2670 | MURSHIDABAD | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. , SM/18704 | Augmentation | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Lokenathpur Zone -I Water Supply Scheme at Head Work Site, 2nd Site site at Beldanga-II Block under Murshidabad Division, P.H. Engineering Dte. | 3863/MURD | 15/12/2023 | 305 | KHOKAN BISWAS | 27.6 | 21.16 | 100 | 100
2671 | MURSHIDABAD | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. , SM/18704 | Augmentation | Material Requisition To Resource Division | 514/MURD/01 | 16/02/2024 | 0 | Resource Division | 90.69 | 0 | 0 | 0
2672 | MURSHIDABAD | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. , SM/18704 | Augmentation | Material Requisition To Resource Division | 1811/MURD/18 | 20/06/2024 | 0 | Resource Division | 5.51 | 0 | 0 | 0
2673 | MURSHIDABAD | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. , SM/18704 | Augmentation | Laying Distribution System for Augmentation of Loknathpur Zone-I (Part-A) PWSS of Beldanga-II Block under Murshidabad Division, PHE Dte. | 2575/MURD | 18/08/2023 | 180 | SAMBHU NATH ROY | 239.31 | 236.87 | 98.98 | 85
2674 | MURSHIDABAD | Murshidabad Division | Augmentation of Lokenathpur Zone -I Piped Water Supply Scheme Block - Beldanga-II , Dist- Murshidabad. , SM/18704 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0 | 0
2675 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Krishnapur (Code-314218), Bansgara (Code-314222) In The Command Area Of Bansgara Ground Water Supply Scheme(Part- , SM/08106 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Chataidubi ( Habitation ID: 0001294180) in the village of Bansgara (Village code 314222) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 241/BD-I | 10/02/2021 | 90 | SANJAY BISWAS | 29.77 | 22.86 | 76.78 | 85
2676 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Krishnapur (Code-314218), Bansgara (Code-314222) In The Command Area Of Bansgara Ground Water Supply Scheme(Part- , SM/08106 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Bansgara ( Habitation ID: 0001294178) in the village of Bansgara (Village code 314222) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.¿ | 240/BD-I | 10/02/2021 | 90 | SARAJIT KUMAR MAJUMDAR | 25.45 | 24.24 | 95.27 | 1
2677 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Krishnapur (Code-314218), Bansgara (Code-314222) In The Command Area Of Bansgara Ground Water Supply Scheme(Part- , SM/08106 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of Krishnapur village (Village code 314218) under Bansgara Ground Water Supply Scheme in Lalgola Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-13) | 1145/BD-I | 07/07/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 200.42 | 50.52 | 25.21 | 1
2678 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Krishnapur (Code-314218), Bansgara (Code-314222) In The Command Area Of Bansgara Ground Water Supply Scheme(Part- , SM/08106 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Krishnapur (Code-314218), Bansgara (Code-314222) In The Command Area Of Bansgara Ground Water Supply Scheme(Part-A)" Under Lalgola Block in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1554/BD-I | 24/09/2024 | 189 | TANUSHREE ENTERPRISE | 66.93 | 0 | 0 | 0
2679 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Krishnapur (Code-314218), Bansgara (Code-314222) In The Command Area Of Bansgara Ground Water Supply Scheme(Part- , SM/08106 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Latiberpara(HabitationID: 0001294181),Naldahari ( Habitation ID: 0001294179) ,Uttar Latiberpara ( Habitation ID: 0001796720) in the village of Bansgara (Village code 314222) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 250/BD-I | 11/02/2021 | 90 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 32.47 | 31.99 | 100 | 0
2680 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kusbaria (314722) of Juranpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II ) , SM/07912 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kusbaria (Village code 314722) under Juranpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723334 | 2596/MURD | 25/08/2021 | 180 | M/S NIRAPADA BHATTACHARJEE | 73.51 | 68.95 | 93.79 | 1
2681 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brindabanpur (314567) of Brindabanpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART- , SM/07921 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Brindabanpur (Village Code -314567) under Brindabanpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005019111). | 582/MURD | 09/02/2021 | 60 | M/S. BIMALENDU BOSE | 64.07 | 89.41 | 167.47 | 0
2682 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brindabanpur (314567) of Brindabanpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART- , SM/07921 | Retrofitting | Extension of Distribution UPVC pipeline for providing balance Functional Household Tap Connections (FHTC) of 437 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Brindabanpur (Village code 314567) under Brindabanpur Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005019111). | 856/MURD | 31/03/2022 | 15 | BIMALENDU BOSE | 9.64 | 9.62 | 100 | 0
2683 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bilaspur (314681) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-II ) , SM/07516 | Retrofitting | Repairing & Renovation of the pump House No-1 & 2 under Katakopra Zone-II water Supply scheme ,Block-Domkal,Under Islampur Sub Division,Under Murshidabad Division, P.H.E Dte. In the District of Murshidabad. | 47/ISD | 28/01/2022 | 60 | R.S CONSTRUCTION (PROP- ROBIN ROY) | 3.46 | 3.46 | 100 | 0
2684 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azimganjagola (314692) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-III) , SM/07670 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Azimganjagola(Village code 314692) under Domkal Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. (Sl No-14) | 3064/MURD | 08/12/2020 | 180 | MAMATA USHA ENTERPRISE | 96.39 | 29.92 | 31.04 | 1
2685 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azimganjagola (314692) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-III) , SM/07670 | Retrofitting | Additional works for Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Azimganjagola( Village Code -314692) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0005184127) | 1725/MURD | 08/07/2021 | 60 | MAMATA USHA ENTERPRISE | 35.34 | 0 | 0 | 1
2686 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azimganjagola (314692) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-III) , SM/07670 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-52 | 360-MSD/22-23 | 19/10/2022 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 3.42 | 0 | 0 | 0
2687 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azimganjagola (314692) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-III) , SM/07670 | Retrofitting | Additional works of Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village AZIMGANJGOLA (Village Code 314692) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 377 of 210-22 by EE MURD | 357-MSD/21-22 | 09/03/2022 | 0 | MAMATA USHA ENTERPRISE | 29.56 | 0 | 0 | 0
2688 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azimganjagola (314692) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-III) , SM/07670 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-53 |  | 21/09/2022 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 4.91 | 0 | 0 | 0
2689 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azimganjagola (314692) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-III) , SM/07670 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-HWH-2021-WL-54 | 371-MSD/22-23 | 21/10/2022 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 4.97 | 0 | 0 | 0
2690 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azimganjagola (314692) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-III) , SM/07670 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-53 | 360-MSD/22-23 | 19/10/2022 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 4.91 | 0 | 0 | 0
2691 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dhulauri (314671) of Dhulauri under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-I) , SM/07673 | Retrofitting | Providing Functional Household Tap Connections ( 250 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Dhulauri ( Village Code -314671) under Dhulauri Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. | 2213/MURD | 02/08/2024 | 30 | SUJAUDDIN SHAIKH | 8.8 | 0 | 0 | 0
2692 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarambati, Manigram (314285, 314284) of Monigram Balarambati under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block of Mursh , SM/07679 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Manigram (Village code 314284) under Monigram Balarambati Ground Water Based Water Supply Scheme for Arsenic Affected Area of Sagardighi Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005252584 in the District of Murshidabad. | 527/MURD | 04/02/2021 | 60 | AMAL KUMAR DAS | 43.9 | 43.65 | 100 | 1
2693 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarambati, Manigram (314285, 314284) of Monigram Balarambati under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block of Mursh , SM/07679 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Balarambati ( Village Code -314285) under Monigram Balarambati Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005252584) | 1210/MURD | 10/05/2021 | 60 | TARIKUL SK | 43.33 | 43.32 | 100 | 1
2694 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District , SM/07692 | Retrofitting | Material Requisition To Resource Division | 142/BD-I | 10/02/2022 | 0 | Resource Division | 4.56 | 0 | 0 | 0
2695 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District , SM/07692 | Retrofitting | Formal Work Order Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dakshin Hanumantanagar (Village code 314436) under Dakshin Hanumantanagar Ground Water based Water Supply Scheme in Bhagawangola-I Block under Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-03) | 1488/BD-I | 18/08/2021 | 180 | H.I ENTERPRISE | 217.42 | 172.18 | 79.19 | 1
2696 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District , SM/07692 | Retrofitting | Additional Laying works at village Dakhshin Hanumantanagar (Village code-314436) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Dakhshin Hanumantanagar Ground water based Water supply scheme (Bhagwangola-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | 2311/BD-I | 29/12/2021 | 60 | H.I ENTERPRISE | 30.49 | 25.99 | 85.24 | 1
2697 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District , SM/07692 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Dakshin Hanumantanagar Ground Water Supply Scheme Under Bhagwangola-I Block In Murshidabad District in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1307/BD-I | 07/08/2024 | 60 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 28.84 | 0 | 0 | 0
2698 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme , SM/06985 | Retrofitting | Additional laying works at village Daulatabad to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna for the village of Hasanpur (Habitation Id-0001294589) at village of Hasanpur (Village Code-314405) under Hasanpur Ground Water Supply Scheme (Bhagawangola-II Block) under Murshidabad District under Berhampore Division-I, PHE Dte. | 548/BD-I | 13/05/2022 | 10 | JAHANGIR ALAM | 2.83 | 1.87 | 100 | 1
2699 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme , SM/06985 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under HASANPUR ground Water based Water Supply Scheme of Bhagawangola-II Block in Murshidabad District under Berhampore Division-I, PHE Dte. | 976/BD-I | 18/10/2023 | 90 | PRAVAT KUMAR GHOSH | 11.83 | 0 | 0 | 0
2700 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme , SM/06985 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahapur (Village code 314536) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 964/BD-I | 17/12/2020 | 60 | M/S J.A CONSTRUCTION | 4.46 | 0 | 0 | 0
2701 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme , SM/06985 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hasanpur (Habitation ID-0001294589 ) at village of Hasanpur (Village code 314505) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 967/BD-I | 17/12/2020 | 90 | JAHANGIR ALAM | 21.8 | 18.01 | 82.63 | 35
2702 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme , SM/06985 | Retrofitting | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahapur and Others under Hasanpur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | 915/BD-I | 19/05/2021 | 7 | M/S J.A CONSTRUCTION | 0.77 | 0 | 0 | 0
2703 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme , SM/06985 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Arazi Alaipur (village code 314537) under HASANPUR Ground water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2260/BD-I | 22/12/2021 | 20 | KUNTAL SAHA | 6.91 | 0 | 0 | 0
2704 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme , SM/06985 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Hasanpur ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1227/BD-I | 29/07/2024 | 60 | M/S JOY MA BANAMALI | 15.89 | 0 | 0 | 0
2705 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme , SM/06985 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Shibnagar (Habitation ID-0001294590 ) at village of Hasanpur (Village code 314505) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 975/BD-I | 17/12/2020 | 90 | KAMIRUL SK AND CO. | 24.37 | 36.68 | 173.49 | 1
2706 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme , SM/06985 | Retrofitting | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nazirpur and others under Hasanpur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | 275/ BD-I | 15/02/2021 | 10 | SWARUP KUMAR BHATTA | 2.26 | 0.75 | 100 | 1
2707 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hasanpur ground water supply scheme , SM/06985 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nazirpur (Village code 314510) under Hasanpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 963/BD-I | 17/12/2020 | 60 | SWARUP KUMAR BHATTA | 8.42 | 8.28 | 100 | 1
2708 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadabpur Nimtala (313796) of Jadabpur Nimtala under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Par , SM/07275 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SAHAJADPUR- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- NISCHINTAPUR , CODE- 315328 , 600 /2020-21/EE | 489/W | 17/03/2021 | 0 | SAMBHUNATH ROY | 29.21 | 0 | 0 | 0
2709 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadabpur Nimtala (313796) of Jadabpur Nimtala under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Par , SM/07275 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of ---BHALKUNDI--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE - MATAI CODE- 315090 , TNO- 625/20-21/EE | 479/W | 12/03/2021 | 0 | M/S UNIQUE BUILDERS | 11.41 | 0 | 0 | 0
2710 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadabpur Nimtala (313796) of Jadabpur Nimtala under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Par , SM/07275 | Retrofitting | Providing Functional Household Tap Connections (FHTC) 267 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jadabpur Nimtala ( Village Code -313796) under Jadabpur Nimtala Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. | 1089 /MURD | 27/04/2022 | 20 | A.P. CONSTRUCTION | 11.9 | 1.41 | 100 | 0
2711 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadabpur Nimtala (313796) of Jadabpur Nimtala under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Par , SM/07275 | Retrofitting | Material Requisition To Resource Division | 540/2/MURD | 25/02/2022 | 0 | Resource Division | 1.47 | 0 | 0 | 0
2712 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jadabpur Nimtala (313796) of Jadabpur Nimtala under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Par , SM/07275 | Retrofitting | Providing Functional Household Tap Connections (FHTC) 267 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jadabpur Nimtala ( Village Code -313796) under Jadabpur Nimtala Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. | 1089/MURD | 27/04/2022 | 20 | A.P. CONSTRUCTION | 11.9 | 9.52 | 100 | 0
2713 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Maniknagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block , SM/07701 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Maniknagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In Murshidabad District in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1204/BD-I | 26/07/2024 | 60 | AZAD ENTERPRISE | 43.72 | 0 | 0 | 0
2714 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Chandipur Ramkantapur (Code-314483), Rasulpur (Code-314492) In The Command Area Of Kasba Bahadurpur Ground Water , SM/07726 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kasba Bahadurpur (Village code 314488) , under Kasba Bahadurpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 167/BD-I | 03/02/2021 | 728 | M/S SINHA & SONS | 95.89 | 19.57 | 91.24 | 1
2715 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Chandipur Ramkantapur (Code-314483), Rasulpur (Code-314492) In The Command Area Of Kasba Bahadurpur Ground Water , SM/07726 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rasulpur (Village code 314492) , Chandipur Ramkantapur (Village code 314483) under Kasba Bahadurpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | 168/BD-I | 03/02/2021 | 20 | KAMIRUL SK AND CO. | 33.2 | 38.46 | 146.97 | 1
2716 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Malipara Village (Code-314452), Saaragachi Village (Code-314453),Chainpara Village (Code-314457),Rameswarbati Village (Code-31445 , SM/07728 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Saaragachhi(Village code 314453),Chainpara(Village code 314457),Rameswarbati(Village code 314458),Maliapara(Village code 314452) under Paschim Rampur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | 170/BD-I | 03/02/2021 | 30 | M/S. SUKUMAR SINHA | 49.93 | 37.79 | 75.69 | 0
2717 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tekpara and Jagannathpur (Village code 315472,315477) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1030/BD-I | 21/06/2021 | 90 | NEOGI ENTERPRISE | 87.92 | 59.34 | 67.49 | 1
2718 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khidirpur & Simulia Jot (Village code 315466) under Pradipdanga (Zone-H)Water Supply Scheme of Central Sector Part-II in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-06) | 1595/BD-I | 31/08/2021 | 180 | NAYLA CONSTRUCTION | 105.36 | 91.58 | 86.93 | 1
2719 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baruipara (Village code 315465) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1033/BD-I | 21/06/2021 | 70 | DECON INDIA | 62.7 | 21.06 | 33.58 | 1
2720 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 37.29 | 1
2721 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under Pradipdanga(Zone-H) Surface Water based Water Supply Scheme of Central Sector (Part-II) under Hariharpara Block in Murshidabad District under Berhampore Division-I, PHE Dte. | 441/BD-I | 12/07/2023 | 90 | S DUTTA | 48.85 | 0 | 0 | 0
2722 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kismat Imadpur (Village code 315468) under Pradipdanga (Zone-H) Water Supply Scheme of Central Sector Part-II in Murshidabad Jiaganj Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-05) | 1904/BD-I | 08/10/2021 | 180 | MS RUBIET HOSSAIN | 176.97 | 0 | 0 | 0
2723 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naopara,Simulia and Panch Baria (Village code 315372,315373,315374) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1028/BD-I | 21/06/2021 | 80 | M/S JHA CONSTRUCTION | 76.94 | 18.86 | 24.51 | 1
2724 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lal Nagar and Bil Bhandardaha (Village code 315471,315473) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1031/BD-I | 21/06/2021 | 90 | SUBHAS CHANDRA KESHARI | 86.54 | 42.48 | 49.08 | 1
2725 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahishmara (Village code 315474) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1027/BD-I | 21/06/2021 | 50 | SARAJIT KUMAR MAJUMDAR | 42.39 | 0 | 0 | 0
2726 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rampara and Bhandardaha (Village code 315475,315476) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1029/BD-I | 21/06/2021 | 70 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 65.72 | 85.65 | 130.33 | 1
2727 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Pradipdanga Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | 2222/BD-I | 15/12/2021 | 90 | APURBA SAHA CHOWDHURY | 82.14 | 79.33 | 96.58 | 1
2728 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jamalpur and Pradipdanga (Village code 315469,315470) under Pradipdanga (Zone-H) Surface Water based Water Supply Scheme of Central Sector Part-II in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1032/BD-I | 21/06/2021 | 70 | M/S AMIT KUMAR GUPTA | 69.96 | 26.19 | 37.44 | 60
2729 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II) Under Hariharpara Block " in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1647/BD-I | 23/10/2024 | 181 | NOVELTY CONSTRUCTION | 68.93 | 0 | 0 | 70
2730 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-58 BU-9284 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2025 to 30.06.2025. | 2335/BD-I | 30/12/2024 | 182 | SEBAYAN CONSTRUCTION | 0.91 | 2.4 | 264.14 | 0
2731 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-58 BU-9284 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.07.2025 to 31.10.2025. | 855/BD-I | 30/06/2025 | 123 | SEBAYAN CONSTRUCTION | 0.6 | 0 | 0 | 0
2732 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Pradipdanga (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector ( , SM/08110 | Retrofitting | Additional Laying works at village Jamalpur and Pradipdanga (Village code-315469 and 315470) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Pradipdanga Surface water based Water supply scheme (Hariharpara,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | 2290/BD-I | 28/12/2021 | 20 | M/S AMIT KUMAR GUPTA | 12.67 | 8.95 | 100 | 1
2733 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08116 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dangapara,Bati & Char Ramipur (Village code 314887,314888 & 314889) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1048/BD-I | 21/06/2021 | 60 | BOSE & CO | 98.62 | 77.92 | 79.01 | 1
2734 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08116 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 72.87 | 1
2735 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08116 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tentulia & Char Chatra (Village code 314873 & 314874) under Rampur (Zone-C) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-03) | 1180/BD-I | 16/07/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 114.26 | 98.18 | 85.93 | 1
2736 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08116 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hasenpur (Village code 314886) under Rampur (Zone-C) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-04) | 1181/BD-I | 16/07/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 117.76 | 105.56 | 89.64 | 1
2737 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08116 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Neoai Khamarpara, Purba Gobindapur & Rampur (Village code 314876,314883 & 314884) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1047/BD-I | 21/06/2021 | 60 | A ONE CONSTRUCTION | 83.87 | 71.41 | 85.14 | 1
2738 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08116 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dharmmapur (Village code 314875) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1169/BD-I | 15/07/2021 | 90 | SHYAMAL KUMAR SAHA | 84.96 | 72.88 | 85.78 | 1
2739 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08116 | Retrofitting | Laying of CI/DI pipeline and sluice valve with chamber at different places under Rampur Zone-C,central sector part-I under JJM under Berhampore Division-I ,P.H.E Dte. In the district of Murshidabad. | 2271/BD-I | 16/12/2024 | 30 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 5.02 | 0 | 0 | 0
2740 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08116 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kanksa & Hulaspur (Village code 314882 & 314885) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1019/BD-I | 21/06/2021 | 60 | RAJ KUMAR MONDAL | 78.07 | 65.04 | 100 | 1
2741 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08116 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nesta & Kumirdaha (Village code 314871 & 314872) under Rampur (Zone-C) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1018/BD-I | 21/06/2021 | 60 | MODERN CONSTRUCTION | 80.88 | 76.68 | 100 | 85
2742 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rampur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part- , SM/08116 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Rampur Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | 133/BD-I | 08/02/2022 | 90 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 79.8 | 77.93 | 100 | 100
2743 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarampur, Palasbati (314475 & 314476) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Murshi , SM/07281 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at AMDAHARA G.P. under Murshidabad Division, P.H.E.Dte. | 246/LSD | 18/08/2021 | 30 | TINA ROY | 4.18 | 0 | 0 | 1
2744 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarampur, Palasbati (314475 & 314476) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Murshi , SM/07281 | Retrofitting | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0 | 0
2745 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarampur, Palasbati (314475 & 314476) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Murshi , SM/07281 | Retrofitting | Providing Functional Household Tap Connections (1296 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Balarampur (Village Code -3144756) & Palasbati (Village Code-314476) under Bhandara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhawangola I & II Block under Murshidabad Division P.H.E Dte. | 3457/MURD | 06/11/2023 | 45 | SALAUDDIN MD SIRAJI | 35.76 | 0 | 0 | 0
2746 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarampur, Palasbati (314475 & 314476) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Murshi , SM/07281 | Retrofitting | Pipe connection from new tube well to rising main including supply of material at Head Work Site of Bhandara Water Supply Scheme under Lalbagh Sub-Division, under Murshidabad Division, P.H.Engineering Dte. | 104/LSD | 13/04/2022 | 30 | MAA CONSTRUCTION | 2.1 | 2.09 | 100 | 1
2747 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Balarampur, Palasbati (314475 & 314476) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Murshi , SM/07281 | Retrofitting | Repair and Renovation of office cum godown at Head work site for Improvement work of Bhandara Water Supply Scheme under Lalbagh Sub Division,P.H.E. Dte.in the District Murshidabad | 560/MURD | 08/02/2021 | 45 | ARNAB SAHA | 5.93 | 1.09 | 100 | 0
2748 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Sundarpur (Code-314445) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-B) , SM/07730 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sundarpur(Village code 314445) under Sundarpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-B) | 172/BD-I | 03/02/2021 | 30 | KAMIRUL SK AND CO. | 53.12 | 92.99 | 175.04 | 0
2749 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Muradpur Arazi, Paranpur, Sadikhan Diar (314627, 314637 & 314638) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Aff , SM/07285 | Retrofitting | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0 | 0
2750 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Muradpur Arazi, Paranpur, Sadikhan Diar (314627, 314637 & 314638) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Aff , SM/07285 | Retrofitting | SUPPLY, OF GUN METAL FERRULE...FOR THE WORK OF ISLAMPUR SUB DIVISION FOR FHTC, TNO- 45/SE/MC/2020-21 | 505/W | 27/03/2021 | 0 | S.P CONSTRUCTION | 117.33 | 0 | 0 | 0
2751 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Muradpur Arazi, Paranpur, Sadikhan Diar (314627, 314637 & 314638) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Aff , SM/07285 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sadikhanr Diar (Village code 314638) under Barabil Raghunathpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723213 in the District of Murshidabad | 1654/MURD | 29/06/2021 | 90 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 52.11 | 52.08 | 100 | 0
2752 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Bansgara ground water supply scheme , SM/07233 | Retrofitting | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Bansgara ground water supply scheme within Raninagar-II block in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1320/BD-I | 12/08/2024 | 60 | JEWS CONSTRUCTION &CO | 16.78 | 0 | 0 | 0
2753 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Bansgara ground water supply scheme , SM/07233 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bansgara (Village code 314587) and Majhardiar (Village code 314588) under Bansgara Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 271/ BD-I | 12/02/2021 | 30 | M/S S.S ENTERPRISE | 79.51 | 58.68 | 73.8 | 0
2754 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kantanagar ( 314437 ) of Kantanagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola - I Block of Murshidabad District ( PART- , SM/07907 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at KANTANAGAR G.P. under Murshidabad Division, P.H.E.Dte. | 247/LSD | 18/08/2021 | 30 | IMAGIN | 4.18 | 0 | 0 | 1
2755 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kantanagar ( 314437 ) of Kantanagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola - I Block of Murshidabad District ( PART- , SM/07907 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at BILBORAKOPRA G.P. under Murshidabad Division, P.H.E.Dte. | 244/LSD | 18/08/2021 | 30 | IMAGIN COMMUNICATION | 4.18 | 0 | 0 | 0
2756 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kantanagar ( 314437 ) of Kantanagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola - I Block of Murshidabad District ( PART- , SM/07907 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at LALGOLA G.P. under Murshidabad Division, P.H.E.Dte. | 243/LSD | 18/08/2021 | 30 | IMAGIN | 4.18 | 0 | 0 | 0
2757 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kantanagar ( 314437 ) of Kantanagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola - I Block of Murshidabad District ( PART- , SM/07907 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Kantanagar ( Village Code -314437) (Part-II) & adjoining habitation under Kantanagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.- 0005186155) | 2534/MURD | 19/08/2021 | 60 | J.S. CONSTRUCTION | 94.61 | 153.42 | 163.43 | 0
2758 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kantanagar ( 314437 ) of Kantanagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola - I Block of Murshidabad District ( PART- , SM/07907 | Retrofitting | Restoration of road for laying of different dia UPVC/CI/DI pipelines at jali Bagicha area under the Improvement work of Kantanagar Water Supply Scheme under Lalbagh Sub-Division P.H.E. Dte. | 417/LSD | 31/12/2021 | 7 | ANUPA ENTERPRISE | 0.94 | 0.94 | 100 | 0
2759 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kantanagar ( 314437 ) of Kantanagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola - I Block of Murshidabad District ( PART- , SM/07907 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village KANTANAGAR (Village Code 314437) PART-I under KANTANAGAR Ground Water Based Water Supply Scheme for arsenic affected areas of BHGWANGOLA-I Block in the District of Murshidabad. Tender no - 271 of 21-22 by EE MURD | 392-MSD/21-22 | 23/03/2022 | 0 | M/S. GHOSH ENTERPRISE | 61.6 | 0 | 0 | 0
2760 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kantanagar ( 314437 ) of Kantanagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola - I Block of Murshidabad District ( PART- , SM/07907 | Retrofitting | Allied work for Laying of different dia UPVC Pipeline at Chaipara, Kupkandi, Kalinagar, Dararkandi, Ashan para & Tikor para area of village Kantanagar ( Village Code 314437) in connection with "Retrofitting Providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kantanagar ( Village Code 314437) (Part-I) & adjoining habitation under Kantanagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola-I Block under Murshidabad Division P.H.E. Dte. (Scheme I.D.- 0005186155)" (Part-C). | 296/LSD | 12/07/2022 | 30 | DEBASISH SARKAR | 4.76 | 4.73 | 99.28 | 0
2761 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kantanagar ( 314437 ) of Kantanagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola - I Block of Murshidabad District ( PART- , SM/07907 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Kantanagar ( Village Code -314437) (Part-I) & adjoining habitation under Kantanagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005186155) | 2396/MURD | 10/08/2021 | 60 | M/S. GHOSH ENTERPRISE | 94.58 | 0 | 0 | 0
2762 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kantanagar ( 314437 ) of Kantanagar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bhagwangola - I Block of Murshidabad District ( PART- , SM/07907 | Retrofitting | Laying of Different dia UPVC Pipeline at Jalibagicha, Kupkandi, Kalinagar, Dararkandi, Ashan para & Tikor para area of village Kantanagar (Village Code-314437) in connection with " Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Kantanagr (Village code 314437) Part-II & adjoining habitation under Kantanagar Ground water based water supply scheme for Arsenic Affected Area of Bhagwangola-I Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0005186155). | 706/MURD | 14/03/2022 | 60 | J.S. CONSTRUCTION | 37.51 | 37.47 | 50 | 0
2763 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I , SM/07507 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-II ) TNO- 786/20-21/EE | 206-MSD/21-22 | 25/11/2021 | 0 | MOTI RAHAMAN | 2.76 | 0 | 0 | 0
2764 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I , SM/07507 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) under Jal Swapna (JJM) of mouza Jhamra ( 314121 ) under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - I Block of Murshidabad District PHE DTE. (Scheme ID: 0001756852). Tender no 786 of 20-21 by EE | 16-MSD / 21-22 | 04/08/2021 | 0 | MOTI RAHAMAN | 30.49 | 0 | 0 | 0
2765 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I , SM/07507 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Raghunathganj-II Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. | 364/JSD | 22/12/2021 | 30 | S.S.INFRASTRUCTURE | 3.13 | 0 | 0 | 0
2766 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I , SM/07507 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-IV). | 127/JSD | 22/03/2022 | 30 | MOTI RAHAMAN | 3.5 | 2.94 | 84.18 | 0
2767 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I , SM/07507 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-I). | 121/JSD | 22/03/2022 | 30 | DIPAYAN DEY | 4.2 | 3.59 | 100 | 0
2768 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I , SM/07507 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-III). | 126/JSD | 22/03/2022 | 30 | DIPAYAN DEY | 3.73 | 3.53 | 100 | 0
2769 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I , SM/07507 | Retrofitting | CONT OF AWARENESS PROGRAMME AT DIFFERENT G.PS, TNO- 06/21-22/AE-LSD | 205-MSD/21-22 | 08/12/2021 | 0 | IMAGIN | 2.93 | 0 | 0 | 0
2770 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I , SM/07507 | Retrofitting | Material Requisition To Resource Division | 540/11/MURD | 25/02/2022 | 0 | Resource Division | 2.2 | 0 | 0 | 0
2771 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jhamra ( 314121 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj - II Block of Murshidabad District ( PART-I , SM/07507 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Jhamra (Village Code-314121) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-II). | 128/JSD | 22/03/2022 | 30 | MURSHID ALOM | 3.87 | 3.83 | 100 | 90
2772 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kagram (315714) of Kagram under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block of Murshidabad District (PART-I) , SM/07668 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of Khagram under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Murshidabad District. T NO- 626/20-21/EE | 05/MSD/21-22 | 16/07/2021 | 0 | SOUMYADIP MISRA | 15.24 | 0 | 0 | 0
2773 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kagram (315714) of Kagram under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block of Murshidabad District (PART-I) , SM/07668 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of Village of Harinya, Datta Barutia, Erera, Sirpara, Sonarundi, Jalsuti, Punasi, DakshinKhanda (Nos FHTC-4251) (Village code-315712, 315702, 315704, 315705, 315707, 315708, 315709, 315710) under DAKSHINKHANDA Ground Water Based Water Supply Scheme and Kagram ( Nos FHTC-3297) (Village code-315714) under Kagram Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block, of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID 0007338400 & 0007773828) | 141/MURD | 19/01/2022 | 180 | M/S. S. DAS AND ENTERPRISE | 383.18 | 78.01 | 48.47 | 1
2774 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kagram (315714) of Kagram under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block of Murshidabad District (PART-I) , SM/07668 | Retrofitting | Material Requisition To Resource Division | 3632/B/MURD | 23/11/2021 | 0 | Resource Division | 18.67 | 0 | 0 | 0
2775 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kagram (315714) of Kagram under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block of Murshidabad District (PART-I) , SM/07668 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
2776 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kagram (315714) of Kagram under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block of Murshidabad District (PART-I) , SM/07668 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
2777 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kagram (315714) of Kagram under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block of Murshidabad District (PART-I) , SM/07668 | Retrofitting | Continuation order for Holding Awarness Programme / Campaigning programs at Chandpur G.P, Radharghat I & II G.P. Ramnagar Bachhara G.P, Sompara-I G.P, Doulatabad G.P, & Chhaighari G.P connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | 689/MURD | 23/02/2021 | 30 | IMAGIN COMMUNICATION | 3.17 | 6.35 | 200 | 0
2778 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Jhikra (Code-314512), Ranitala (Code-314513) In The Command Area Of Jhikra Ground Water Supply Scheme (Part-A) Un , SM/07795 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhikra (Village code 314512) ,Ranitala (Village code 314513) under Jhikra Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | 182/BD-I | 04/02/2021 | 30 | DECON INDIA | 66.83 | 91.14 | 136.38 | 1
2779 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Manganpara Village (Code-315662) Under Command Area Of Rampara Faridpur Ground Water Supply Scheme (Part-A) , SM/07717 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramganpara (Village code 315662) under Rampara Faridpur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 991/BD-I | 17/12/2020 | 90 | M/S S.DAS & ENTERPRISE | 38.85 | 29.89 | 76.92 | 75
2780 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Bikalnagar Village (Code-315678) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-A) , SM/07719 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Bikalnagar Village (Code-315678) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1443/BD-I | 04/09/2024 | 60 | SUPTI ENTERPRISE | 17.42 | 0 | 0 | 0
2781 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Bikalnagar Village (Code-315678) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-A) , SM/07719 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bikal Nagar (Village code 315678), under Kashipur Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | 188/BD-I | 04/02/2021 | 30 | HANNAN BUILDERS PVT. LTD. | 60.34 | 49.9 | 82.69 | 1
2782 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Bikalnagar Village (Code-315678) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-A) , SM/07719 | Retrofitting | Additional Laying works at village BIKALNAGAR( Village code-315678) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Kashipur Ground water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 1923/BD-I | 08/10/2021 | 10 | AHS (R) INFRA PRIVATE LIMITED | 7.21 | 6.55 | 90.89 | 1
2783 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Moktarpur Village (Code-314766), Under Command Area Of Moktarpur Ground Water Supply Scheme(Part-A) Under Raninagar-I Block In M , SM/07888 | Retrofitting | Formal Work Order Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Moktarpur (Village code 314766) under Moktarpur Ground Water based Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. (Block-Raninagar-I)(Sl-06) | 1471/BD-I | 17/08/2021 | 1454 | M/S GOUTAM CHAKRABORTY | 122.27 | 96.08 | 78.58 | 75
2784 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Moktarpur Village (Code-314766), Under Command Area Of Moktarpur Ground Water Supply Scheme(Part-A) Under Raninagar-I Block In M , SM/07888 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Alampur (village code 315519) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1853/BD-I | 07/10/2021 | 90 | SRIJON ENTERPRISE | 88.19 | 0 | 0 | 1
2785 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri , SM/08198 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Laskarpur ( Village Code -313850) under Dogachhi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0005019105) | 595/MURD | 09/02/2021 | 60 | ARABINDA GHOSH | 71.56 | 67.42 | 94.21 | 1
2786 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri , SM/08198 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Samserganj Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. | 365/JSD | 22/12/2021 | 30 | IMAGIN COMMUNICATION | 2.77 | 0 | 0 | 1
2787 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri , SM/08198 | Retrofitting | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KANKURIA-JAFRABAD ZONE-I PWSS Scheme, Block - SAMSERGANJ to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 415 of 21-22 by EE MURD | 301-MSD/21-22 | 07/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 8.73 | 0 | 0 | 0
2788 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri , SM/08198 | Retrofitting | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing KANKURIA-JAFRABAD ZONE-II PWSS Scheme, Block - SAMSERGANJ to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 408 of 21-22 by EE MURD | 301-MSD/21-22 | 07/02/2022 | 0 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.72 | 0 | 0 | 0
2789 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri , SM/08198 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of DOGACHHI (Village code 313848) under DOGACHHI under Ground Water Based Water Supply Scheme (SAMSERGANJ Block) and BAHADURPUR (Village Code-313924) under BAHADURPUR Ground Water Based Water Supply Scheme for (SUTI-I BLOCK) Arsenic Affected Areas of under Murshidabad Division, PHE Dte. | 557/MURD | 28/02/2022 | 180 | M/S. NANDY ENTERPRISE | 268.47 | 73.74 | 100 | 1
2790 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dogachhi (313848) & Laskarpur (313850) of Dogachhi under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad Distri , SM/08198 | Retrofitting | Material Requisition To Resource Division | 3632/A/MURD | 23/11/2021 | 0 | Resource Division | 18.39 | 0 | 0 | 0
2791 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Mohula (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In , SM/08907 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) laying pipeline in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Halalpur, Mohula, Binkar, Mahishasthali, Gopinathpur & Bhabta under Mohula (ZONE-A) Water Supply Scheme in the district Murshidabad under Berhampore Division - I, PHE Dte. | 1641/BD-I | 09/03/2023 | 180 | M/S JAN MAHAMMAD | 558.19 | 0 | 0 | 0
2792 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Mohula (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In , SM/08907 | Retrofitting | Laying of 150 mm dia (K-9), 250 mm & 300 mm dia DI (K-7) pipeline with interconnection in between Rising Main and Distribution System and 200 mm, 225 mm dia UPVC pipeline of unlead portion within command area of Mohula (Zone-A) W/S scheme of Arsenic affected area of Beldanga uncovered W/S scheme under Berhampore Division-I, P.H.E. Dte. | 953/BD-I | 13/10/2023 | 30 | JAMIRUL CONSTRUCTION | 14.09 | 3.16 | 100 | 100
2793 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water , SM/08281 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Madna(CT) (Village code 313940) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756899 in the District of Murshidabad. | 2476/MURD | 16/08/2021 | 60 | NOVELTY CONSTRUCTION | 39.3 | 35.25 | 100 | 1
2794 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water , SM/08281 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gotha (Village code 313912) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756899 in the District of Murshidabad. | 542 / MURD | 05/02/2021 | 60 | SHIRSHENDU MUKHERJEE | 7.73 | 0 | 0 | 1
2795 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water , SM/08281 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission of 1837nos household under command area of village of Panchgachhia, Arazi Ramakantapur,Gotha,Sadkpur( Village Code-313919, 313910, 313912, 313920) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0001756899) | 1214/MURD | 10/05/2022 | 60 | SWAPAN DAS | 79.18 | 0 | 0 | 1
2796 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water , SM/08281 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sujanipara (313923) of Madna under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District (PART-I) |  | 17/02/2022 | 0 | R.K. CONSTRUCTION | 33.77 | 0 | 0 | 0
2797 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water , SM/08281 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village PANCHGACHHIA (Village Code 313919) under MADNA Ground Water Based Water Supply Scheme for arsenic affected areas of SUTI-I Block in the District of Murshidabad. Tender no - 790 of 20-21 by EE MURD | 104-MSD/22-23 | 06/05/2022 | 0 | DIPAYAN DEY | 15.99 | 0 | 0 | 0
2798 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water , SM/08281 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village SUJANIPARA (Village Code 313923) under MADNA Ground Water Based Water Supply Scheme for arsenic affected areas of SUTI-I Block in the District of Murshidabad. Tender no - 44 of 21-22 by EE MURD | 350-MSD/21-22 | 04/03/2022 | 0 | R.K. CONSTRUCTION | 33.77 | 0 | 0 | 0
2799 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water , SM/08281 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sujanipara (Village code 313923) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756899 in the District of Murshidabad. | 528/MURD | 04/02/2021 | 60 | R.K. CONSTRUCTION | 33.78 | 0 | 0 | 0
2800 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water , SM/08281 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gotha (Village code 313912) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID : 0001756899 in the District of Murshidabad. | 542/MURD | 05/02/2021 | 60 | SHIRSHENDU MUKHERJEE | 7.73 | 7.46 | 100 | 1
2801 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water , SM/08281 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Arazi Ramakantapur (Village code 313910) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756899 in the District of Murshidabad. | 533/MURD | 04/02/2021 | 60 | M H SUPPLIERS | 16.7 | 33.4 | 199.93 | 1
2802 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Azazi Gotha, Arazi Ramakantapur, Gotha, Madna (CT), Sadikpur, Sujanipara (313909, 313910, 313912, 313940, 313920 & 313923) of Madna under Ground Water Based Water , SM/08281 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sadikpur (Village code 313920) under Madna Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756899 in the District of Murshidabad. | 524/MURD | 04/02/2021 | 60 | N. H. ENTERPRISE (PROP. NAJMUL HOQUE) | 33.02 | 32.9 | 100 | 1
2803 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Hatinagar (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08915 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 25.58 | 1
2804 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Hatinagar (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08915 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Banjetia (Village code 315445), Sibpur (Village Code 315391) & Nagpara (Village Code 315390) under Hatinagar (Zone-A) Surface Water Supply Scheme of Central Sector Part-II, Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 978/BD-I | 17/12/2020 | 979 | ACQUA CONSTRUCTION CONSORTIUM | 272.06 | 161.82 | 59.48 | 85
2805 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Hatinagar (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08915 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Cossimbazar (Village code 315444), Sibnagar Badarpur (Village Code-315446) under Hatinagar (Zone-A) Surface Water Supply Scheme of Central Sector Part-II, Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 980/BD-I | 17/12/2020 | 180 | CHAKRABORTY CONSTRUCTION | 307.25 | 43.36 | 22.85 | 69
2806 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Hatinagar (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08915 | Retrofitting | Additional Laying works at village Janmahammadpur (village code 315398),Ustia(village code315399),Hatinagar (village code 315397) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Hatinagar (Zone-A) Surface water supply scheme (Block-Berhampore)under Berhampore Division-I, PHE Dte. In the District of Murshidabad. (Part-I) | 1856/BD-I | 07/10/2021 | 40 | M/S JAN MAHAMMAD | 32.92 | 32.92 | 100 | 1
2807 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Hatinagar (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08915 | Retrofitting | Additional Laying works at village Banjetia, Sibpur and Nagpara (Village code-315445,315391 and 315390) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Hatinagar (Zone-A)Surface water based Water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 11/BD-I | 05/01/2022 | 20 | ACQUA CONSTRUCTION CONSORTIUM | 25.71 | 0 | 0 | 0
2808 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Hatinagar (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08915 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Janmahammadpur (Village code 315398), Ustia (Village Code-315399) & Hatinagar (Village Code-315397) under Hatinagar (Zone-A) Surface Water Supply Scheme of Central Sector Part-II, Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 979/BD-I | 17/12/2020 | 826 | M/S JAN MAHAMMAD | 264.94 | 91.9 | 96.09 | 100
2809 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Hatinagar (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08915 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Madapur ( village code 315392 ) under HATINAGAR ( Zone - A ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | 1840/BD-I | 05/10/2021 | 30 | MAA CONSTRUCTION | 24.5 | 23.96 | 100 | 1
2810 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Hatinagar (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa , SM/08915 | Retrofitting | Laying of connection for supply of drinking water at Tiktikipara Baharul Ulum Madrasah Kendra in connection with JJM (Jal Jeevan Mission) under different Berhampore Block under different water supply scheme of Behampore Division-I, P.H.E Dte. | 89/BD-I | 03/05/2023 | 30 | SO-FINE AQUARIUM | 1.5 | 1.5 | 100 | 100
2811 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joykrishnapur (313880) of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under M , SM/09742 | Retrofitting | Material Requisition To Resource Division | 889/F/MURD | 05/04/2022 | 0 | Resource Division | 5.44 | 0 | 0 | 0
2812 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joykrishnapur (313880) of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under M , SM/09742 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-27 | 471-MSD/22-23 | 29/12/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 6.18 | 0 | 0 | 0
2813 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joykrishnapur (313880) of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under M , SM/09742 | Retrofitting | Preparation of design, Drawing and approval from the N.H.A.I Authorities including supply of 200 mm dia 8 mm thick MS Water Carring Pipe, 600 mm dia 10 mm thick MS casing Pipe & Pushing of casing pipe by Hydraulic Jacking Technique Method across the Chainage 270+550 of the N.H.-34 of at Mouza-Basudebpur of Basudebpur adjoining mouza W/S Scheme & across at chainage 273+100 of the N.H.-34 of at Mouza-Joykrishnapur of Joykrishnapur W/S Scheme in Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. | 755/MURD | 16/03/2023 | 90 | SAMBHU NATH ROY | 62.1 | 36.07 | 100 | 0
2814 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joykrishnapur (313880) of Joykrishnapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under M , SM/09742 | Retrofitting | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Basudevpur halt Station (TP NO 235/8 & 235/9) on railway land of mouza Joykrishnapur & Connecting with existing 160 mm dia UPVC distribution main line of Joykrishnapur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | 510/MURD | 23/02/2022 | 60 | SAMBHU NATH ROY | 27.25 | 27.25 | 100 | 0
2815 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kanupur ( 314992 ) and Ramchandrabati (313992) of Raghunathganj - I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I B , SM/09750 | Retrofitting | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Raghunathganj-II Block (Gria,Sekendra, Mithipur,Jotkomal,Dayarampur & Samatinagar) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. | 68 /JSD | 25/02/2021 | 30 | S.S.INFRASTRUCTURE | 2.38 | 2.38 | 100 | 0
2816 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kanupur ( 314992 ) and Ramchandrabati (313992) of Raghunathganj - I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I B , SM/09750 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Raghunathganj-I Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. | 367/JSD | 22/12/2021 | 30 | IMAGIN | 1.88 | 0 | 0 | 0
2817 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kanupur ( 314992 ) and Ramchandrabati (313992) of Raghunathganj - I under Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj - I B , SM/09750 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kanupur(Village code 313992) under Surface Based Water Supply Scheme for Arsenic Affected Area of Raghunathganj-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756489 in the District of Murshidabad. (Sl No-12) | 3067/MURD | 08/12/2020 | 180 | MODERN CONSTRUCTION | 75.3 | 0 | 0 | 0
2818 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kolan Radhakantapur (314523) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad Dis , SM/09754 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kolan Radhakantapur(Village code 314523) under Bhandara Ground Water Based water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl No-04) | 207-MSD/22-23 | 15/07/2022 | 0 | M/S GUNGUN CONSTRUCTION | 31.97 | 0 | 0 | 0
2819 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khanpur (313989) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad , SM/09757 | Retrofitting | Renovation of U.P.V.C of pipe line from Shib Mandir to Kartik Mandir due to widening of Bituminous Road of Prosadpur Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. | 3328 / MURD | 31/12/2020 | 45 | ARJU CONSTRUCTION | 4.99 | 4.99 | 100 | 0
2820 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khanpur (313989) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad , SM/09757 | Retrofitting | Renovation of UPVC pipe line from Dulal kali to Kartik Mandir due to widening of Bituminous Road of Prosadpur W/S Scheme in an emergency basis under Jangipur Sub-Division under Murshidabad Division, PHE Dte. | 79/JSD | 26/02/2021 | 30 | T.R. CONSTRUCTION | 5 | 5 | 100 | 0
2821 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Khanpur (313989) of Prasadpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad District under Murshidabad , SM/09757 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Bamuha, Khidirpur, Khanpur (Nos FHTC-2996 Nos) (Village code-313962,313990,313989) under PRASADPUR Ground Water Based Water Supply Scheme of Suti-II Block and Kalinagar (FHTC-4077 Nos) (Village code-313899) under Raturi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID-0005019110 & 0001723413) | 558/MURD | 28/02/2022 | 180 | ALOK ENTERPRISE( A UNIT OF SAKET TREXIM PVT.LTD.) | 332.59 | 0 | 0 | 0
2822 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10014 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (ARAJI MADHUPUR PWSS Scheme, Block - Berhampore) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3269/MURD | 05/10/2021 | 60 | RADIANT | 3.15 | 3.15 | 100 | 1
2823 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10014 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Arazi Madhupur Water Supply Scheme of TW-I at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3066/MURD | 17/11/2022 | 30 | NADIA TUBEWELLS | 10.6 | 9.23 | 100 | 0
2824 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10014 | Augmentation | Material Requisition To Resource Division | 1210/MURD/02 | 02/05/2023 | 0 | Resource Division | 4.99 | 0 | 0 | 0
2825 | MURSHIDABAD | Berhampore Mechanical | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10014 | Augmentation | Quotaion for Shifting of LT overhead line at Araji Madhupur head work site. | 206/WBSEDCL | 14/03/2023 | 0 | WBSEDCL | 0.79 | 0 | 0 | 0
2826 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10014 | Augmentation | Rail Bhoomi Crossing Seva (IR-RBCS) Eastern Railway Howrah Division DEMAND NOTE Application ID: ER-HWH-2023-WL-01 | 157-MSD/2023-24 | 28/06/2023 | 0 | EASTERN RAILWAY (HOWRAH DIVISION) | 5.5 | 0 | 0 | 0
2827 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10014 | Augmentation | Allied work of Laying Distribution System, Rising Main, Construction of Boundary wall, Service Road of Arazi Madhupur & adjoining moujas PWSS under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte | 1911/MURD | 02/07/2024 | 403 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 79.82 | 9.4 | 11.78 | 65
2828 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10014 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 2.79 | 100 | 80
2829 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10014 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ARAZI MADHUPUR Water Supply Scheme at 2nd Site site at BERHAMPORE Block under Murshidabad Division, P.H. Engineering Dte. | 3809/MURD | 12/12/2023 | 21 | NADIA TUBEWELLS | 11.78 | 10.52 | 100 | 90
2830 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10014 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Kanthalia Road (KTLR) Station to Karna Subarna (KNSN) (TP NO 151/33 & 151/36) at Karna Subarna Station Gumti mouza & Connecting with existing 140mm dia HDPE distribution main line of Arazi Madhupur Ground Based W/S Scheme , Berhampore Sub Division, PHE Dte. | 742/MURD | 12/03/2024 | 363 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 34.02 | 7.71 | 20.94 | 80
2831 | MURSHIDABAD | Berhampore Mechanical | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10014 | Augmentation | NEW CONNECTION AT ARAJI MADHUPUR PH-II |  | 08/07/2024 | 0 | WBSEDCL | 5.17 | 0 | 0 | 0
2832 | MURSHIDABAD | Berhampore Mechanical | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10014 | Augmentation | NEW CONNECTION AT ARAJI MADHUPUR PH-II | 166/WBSEDCL-JJM | 29/07/2024 | 0 | WBSEDCL | 5.17 | 0 | 0 | 0
2833 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10014 | Augmentation | Formal work order for Augmentation of Arazi Madhupur & its adjoining mouzas Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Berhampore Block within Berhampore Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | 3171/MURD | 30/11/2022 | 1036 | M/S. GHOSH ENTERPRISE (MANAB KR GHOSH) | 200.36 | 97.75 | 48.79 | 80
2834 | MURSHIDABAD | Berhampore Mechanical | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10014 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Araji-Madhupur ground water based water supply scheme under Block- Berhampore, Dist. Murshidabad under MEDB, PHE Dte. | 2019/MEDB | 19/06/2023 | 811 | SARKAR CONSTRUCTION | 11.08 | 9.73 | 87.77 | 80
2835 | MURSHIDABAD | Murshidabad Division | Augmentation Of Ground Water Based Arazi Madhupur PWSS To Accommodate FHTC In Berhampore Block Within Murshidabad District Under Murshidabad Division, PHE DTE. , SM/10014 | Augmentation | Relaying of pipe line for connection of Gobindapur Junior High School and 29, Gobindapur Junior Basic School under command area of ARAJIMADHUPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | 3176/MURD | 16/12/2020 | 15 | DATA ENTERPRISE | 4.58 | 4.55 | 100 | 0
2836 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10630 | Augmentation | Restoration work of Distribution Pipeline by laying of UPVC pipe at different location of Vulnerable Area of command area of Faridpur-II W/S Scheme under Islampur Sub-Division, PHE Dte. in the district of Murshidabad. | 277/ISD | 03/06/2022 | 30 | SHIBAM ENTERPRISE | 4.8 | 4.75 | 100 | 1
2837 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10630 | Augmentation | Material Requisition To Resource Division | 3037/C/MURD | 16/11/2022 | 0 | Resource Division | 107.03 | 0 | 0 | 0
2838 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10630 | Augmentation | Material Requisition To Resource Division | 2780/C/MURD | 01/10/2022 | 0 | Resource Division | 24.7 | 0 | 0 | 0
2839 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10630 | Augmentation | Material Requisition To Resource Division | 2508/B/MURD | 31/08/2022 | 0 | Resource Division | 3.41 | 0 | 0 | 0
2840 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10630 | Augmentation | Material Requisition To Resource Division | 1180/MURD/03 | 29/04/2023 | 0 | Resource Division | 107.03 | 0 | 0 | 0
2841 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10630 | Augmentation | New connection charge for Faridpur W/S Scheme, Zone-II, P/H No.-II. | 91/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 0.8 | 0 | 0 | 0
2842 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10630 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-II , Zone-II of Faridpur, ground water based water supply scheme under Block- Raninagar-II, Dist. Murshidabad under MEDB, PHE Dte. | 3773/MEDB | 03/11/2023 | 92 | JOY BISHNU ENGINEERING CO. | 11.74 | 7.62 | 64.9 | 20
2843 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10630 | Augmentation | Material Requisition To Resource Division | MURD/2481/03 | 04/09/2024 | 0 | Resource Division | 34.04 | 0 | 0 | 0
2844 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10630 | Augmentation | Addl service connection charges ID 860279294 | 213/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 2.8 | 0 | 0 | 0
2845 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for FARIDPUR Zone- II to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10630 | Augmentation | Formal work order for Augmentation of Faridpur Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 2642/MURD | 19/09/2022 | 1096 | PRADIP KUMAR DAS | 742.15 | 357.32 | 48.15 | 45
2846 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat , SM/12578 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of BUNDHAR KISMAT ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | 3766/MEDB | 03/11/2023 | 92 | GANGULI ELECTRICAL CO. | 11.19 | 9.3 | 83.1 | 10
2847 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat , SM/12578 | Augmentation | Material Requisition To Resource Division | 196/BD-I/6 | 09/02/2024 | 0 | Resource Division | 48.07 | 0 | 0 | 0
2848 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat , SM/12578 | Augmentation | BHUNDAR KISMAT PWSS | 350/WBSEDCL-JJM | 15/02/2024 | 0 | WBSEDCL | 7.83 | 0 | 0 | 0
2849 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat , SM/12578 | Augmentation | Augmentation of Bhundar kismat Piped water supply scheme to accommodate construction of pump house ,boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1617/BD-I | 02/03/2023 | 180 | DHIRENDRA NATH MONDAL | 222.61 | 186.56 | 83.8 | 60
2850 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat , SM/12578 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BHUNDAR KISMAT Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 268/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.7 | 2.7 | 100 | 0
2851 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat , SM/12578 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Bhundar Kismat ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | 1362/BD-I | 21/12/2022 | 630 | GHOSH BUILDERS | 2.41 | 0 | 0 | 100
2852 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat , SM/12578 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) forBhundarKismat water supply scheme of Bhagwangola-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal Jeevan Mission. | 1162/BD-I | 05/12/2023 | 391 | SUBHENDRA MOHAN SARKAR | 8.56 | 0 | 0 | 100
2853 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat , SM/12578 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhundar Kismat Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 161/BD-I | 05/02/2024 | 30 | M/S D. PALIT & CO. | 9 | 0 | 0 | 100
2854 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gokulpur Gobindapur (314659) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-II , SM/07669 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gokulpur Gobindapur(Village code 314659) under Baniakhai Ground Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723470 in the District of Murshidabad. | 2619/MURD | 26/08/2021 | 180 | M/S PARIMAL DAS | 105.05 | 0 | 0 | 1
2855 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gokulpur Gobindapur (314659) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-II , SM/07669 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gokulpur Gobindapur (314659) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-III) |  | 17/02/2022 | 0 | M/S PARIMAL DAS | 103.01 | 0 | 0 | 0
2856 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gokulpur Gobindapur (314659) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-II , SM/07669 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Gokulpur Gobindapur (314659) under Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under MSD PHE DTE. Tender No - 15 of 21-22 by SE MC | 344-MSD/21-22 | 04/03/2022 | 0 | M/S PARIMAL DAS | 103.01 | 0 | 0 | 0
2857 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- II , SM/12580 | Augmentation | Material Requisition To Resource Division | 196/BD-I/8 | 09/02/2024 | 0 | Resource Division | 10.99 | 0 | 0 | 0
2858 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- II , SM/12580 | Augmentation | Augmentation of Diar Syampur Zone-II Piped water supply scheme to accommodate construction of OHR, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1623/BD-I | 02/03/2023 | 670 | SANDHAN ADHIKARY | 152.01 | 56.56 | 37.21 | 40
2859 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- II , SM/12580 | Augmentation | Balance work for the work of Laying distribution pipe line of Diar Syampur Zone-II PWSS under Jal Jeevan Mission within Bhagwangola-I block in connection with Augmentation under Berhampore Division-I,PHE.Dte. In the district of Murshidabad. | 767/BD-I | 22/05/2025 | 90 | SANDHAN ADHIKARI | 69.54 | 0 | 0 | 0
2860 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- II , SM/12580 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DIAR SYAMPUR ZONE-II Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 264/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.44 | 2.39 | 100 | 100
2861 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- II , SM/12580 | Augmentation | Repair And Renovation Works Of RCC Elevated Reservoir (100 Cum) for Diar Shyampur Zone-II water supply scheme of Bhagwangola-I block under Berhampore Division-I PHE Dte. in the district Murshidabad.For Augmentation of PWSS under Jal jeevan Mission. | 995/BD-I | 30/10/2023 | 30 | MD TOUSIF AHMED | 4.19 | 4.13 | 100 | 100
2862 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/11197 | Augmentation | Material Requisition To Resource Division | 2780/K/MURD | 01/10/2022 | 0 | Resource Division | 5.07 | 0 | 0 | 0
2863 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KHAYRAMARI Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/11197 | Augmentation | Material Requisition To Resource Division | MURD/2481/05 | 04/09/2024 | 0 | Resource Division | 5.07 | 0 | 0 | 0
2864 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF MIRZAPUR (EXCEPT GANKAR MOUZA) BLOCK-RAGHUNATHGANJ-I , SM/11220 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS MIRZAPUR (Except Gankar Mouza) PWSS Scheme,Block-Raghunathgaunge-I) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | 2743/MURD | 03/09/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.54 | 7.54 | 100 | 1
2865 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF MIRZAPUR (EXCEPT GANKAR MOUZA) BLOCK-RAGHUNATHGANJ-I , SM/11220 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 200 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone- II PWSS in Lalgola Block & Mirzapur (Except Gankar Mouza) PWSS Raghunathganj-I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 3377/MURD | 31/10/2023 | 1095 | M/S GHOSH & CO. | 1181.6 | 0 | 0 | 20
2866 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11567 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (SURANGAPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3274/MURD | 05/10/2021 | 60 | RADIANT | 15.07 | 5.02 | 100 | 1
2867 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11567 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Surangapur Zone-I Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3070/MURD | 17/11/2022 | 30 | A.M. ENTERPRISE | 10.6 | 9.46 | 100 | 100
2868 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11567 | Augmentation | Material Requisition To Resource Division | 1278/MURD/1 | 10/05/2023 | 0 | Resource Division | 75.24 | 0 | 0 | 0
2869 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11567 | Augmentation | Formal work order for Augmentation of SURANGAPUR Zone-I / Part-B Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 2087/MURD | 27/07/2022 | 365 | MOTI RAHAMAN | 222.6 | 74.47 | 33.45 | 50
2870 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11567 | Augmentation | Material Requisition To Resource Division | 305/MURD/02 | 29/01/2024 | 0 | Resource Division | 62.68 | 0 | 0 | 0
2871 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SURANGAPUR PWSS (ZONE- I ) PART-B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11567 | Augmentation | Material Requisition To Resource Division | 1811/MURD/08 | 20/06/2024 | 0 | Resource Division | 34.58 | 0 | 0 | 0
2872 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. , SM/12740 | Augmentation | Material Requisition To Resource Division | 196/BD-I/3 | 09/02/2024 | 0 | Resource Division | 1.74 | 0 | 0 | 0
2873 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. , SM/12740 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNAPARA Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 270/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.45 | 2.41 | 100 | 1
2874 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. , SM/12740 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Ramnapara ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | 1410/BD-I | 04/01/2023 | 30 | KAKALI ENTERPRISE | 2.23 | 1.23 | 100 | 100
2875 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. , SM/12740 | Augmentation | Augmentation of RAMNAPARA Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1456/BD-I | 17/01/2023 | 180 | S.K ENTERPRISE (RANITALA) | 34.01 | 33.78 | 100 | 100
2876 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. , SM/12740 | Augmentation | Repair And Renovation Works Of RCC Elevated Reservoir (30 Cum) for Ramnapara water supply scheme of Bhagwangola-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 989/BD-I | 30/10/2023 | 30 | DAYAMAYEE CO-OPERATIVE LABOUR CONTRACT & CONSTRUCTION SOCIETY LIMITED | 3.06 | 2.84 | 100 | 100
2877 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramnapara. , SM/12740 | Augmentation | Replacement of sand layers, Activated Alumina & existing gravel for Modified Sujapur Sadipur Model after washing of AIRP allied (Capacity 07.00 Cum/hr) at Ramnapara Water Supply Scheme under Jal Jeevan Mission of Bhagwangola-II Block under Berhampore Div-I, Murshidabad PHE Dte. | 972/BD-I | 18/06/2024 | 30 | ULTRA CONSTRUCTION | 14.12 | 14.11 | 100 | 100
2878 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Jamna (315232) of Mahalandi Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Kandi Block of Murshidabad District Under Murshidabad Division PheDte. , SM/11233 | Augmentation | Sinking of 02 (Two) Nos of 300 mm x 200 mm dia tube well i.e. TW-I, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone-I & adjoining mouzas Water Supply Scheme at Head work site & 3 r d Site at Kandi Block under Murshidabad Division, P.H. Engineering Dte. | 1775/MURD | 06/07/2023 | 21 | NILAVA GHOSHAL (BUMBA) | 23.52 | 20.69 | 100 | 100
2879 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Jamna (315232) of Mahalandi Under Ground Water Based Water Supply Scheme For Arsenic Affected Areas of Kandi Block of Murshidabad District Under Murshidabad Division PheDte. , SM/11233 | Augmentation | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone-II & adjoining mouzas Water Supply Scheme at 3rd work site at K a n d i Block under Murshidabad Division, P.H. Engineering Dte. | 1110/MURD | 24/04/2023 | 708 | HARUN ALL RASHID & BROTHERS | 10.58 | 0 | 0 | 60
2880 | MURSHIDABAD | Berhampore Mechanical | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Ramnarayanpur (314614) of Narasinghpur Ground water based water supply scheme for Arsenic Affected Areas of Jalangi Block in Murshidabad District under Murshidabad Division, P.H.E. , SM/11234 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Ramnarayanpur (314614) Pump House No.-I and II under Narasinghpur Ground water based water supply scheme for Arsenic Affected Areas of Jalangi Block in Murshidabad District under Murshidabad Division, P.H.E. Dte. | 767/MEDB | 20/02/2024 | 90 | CHAKRABORTY MINING AND ENGINEERING | 22.9 | 0 | 0 | 0
2881 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Ramnarayanpur (314614) of Narasinghpur Ground water based water supply scheme for Arsenic Affected Areas of Jalangi Block in Murshidabad District under Murshidabad Division, P.H.E. , SM/11234 | Augmentation | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ramnarayanpara (Village code 314614) under Narsinghpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184090 in the District of Murshidabad. | 86/MURD | 08/01/2021 | 60 | M/S. MONDAL ENTERPRISE | 12.66 | 10.39 | 100 | 0
2882 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Ramnarayanpur (314614) of Narasinghpur Ground water based water supply scheme for Arsenic Affected Areas of Jalangi Block in Murshidabad District under Murshidabad Division, P.H.E. , SM/11234 | Augmentation | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Ramnarayanpara (314614) of Narasinghapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District under Murshidabad Division Phe Dte. | 1198/MURD | 10/05/2022 | 60 | NADIA TUBEWELLS | 32.63 | 27.39 | 100 | 100
2883 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Garibpur, Chandpur, Pardiar (314710, 314711, 314712) of Garibpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Bl , SM/08277 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chandpur(Village code 314711) under Garibpur (Zone I and Zone II) Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723342 | 3577 / MURD | 16/11/2021 | 100 | M/S BHUBAN DAS | 52.35 | 31.51 | 60.2 | 1
2884 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Garibpur, Chandpur, Pardiar (314710, 314711, 314712) of Garibpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Bl , SM/08277 | Retrofitting | Extension of Distribution UPVC pipeline for providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan mission and Jal Swapna under command area of village of Pardiar (village code-314712)under Garibpur(Zone-I & Zone - II)Ground Water Based Water supply Scheme for arsenic affected areas of Domkal Block in Murshidabad District under Murshidabad Division PHE Dte.(scheme ID-0001723342) | 1196/MURD | 10/05/2022 | 30 | ADITYA ENTERPRISE | 11.7 | 11.74 | 100 | 1
2885 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Garibpur, Chandpur, Pardiar (314710, 314711, 314712) of Garibpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Bl , SM/08277 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village PARDIAR (Village Code 314712) under GORIBPUR (ZONE-I AND ZONE-II) Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 107 of 21-22 by SE MC | 385-MSD/21-22 | 16/03/2022 | 0 | M/S. M.G. CONSTRUCTION | 36.63 | 0 | 0 | 0
2886 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Garibpur, Chandpur, Pardiar (314710, 314711, 314712) of Garibpur (Zone-I & II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Bl , SM/08277 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Pardiar (Village code 314712) under Goribpur (Zone-I and Zone-II) Ground Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723342 | 3631/MURD | 23/11/2021 | 120 | M/S. M.G. CONSTRUCTION | 58.5 | 21.67 | 100 | 1
2887 | MURSHIDABAD | Murshidabad Division | TENTULIA AND ADJOINING MOUJAS PWSS , SM/13998 | New | Material Requisition To Resource Division | 1067/MURD/8 | 18/04/2023 | 0 | Resource Division | 1.31 | 0 | 0 | 0
2888 | MURSHIDABAD | Berhampore Mechanical | TENTULIA AND ADJOINING MOUJAS PWSS , SM/13998 | New | ADDITIONAL QUOTATION AMOUNT FOR MODIFIED ROUTE TO EFFECTING THE CONNECTION AT TENTULIA PH 1 ID 860320302 |  | 11/12/2024 | 0 | WBSEDCL | 4.45 | 0 | 0 | 0
2889 | MURSHIDABAD | Berhampore Mechanical | TENTULIA AND ADJOINING MOUJAS PWSS , SM/13998 | New | AT TENTULIA PH 1 ID 304239411 | 361/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 3.48 | 0 | 0 | 0
2890 | MURSHIDABAD | Berhampore Mechanical | TENTULIA AND ADJOINING MOUJAS PWSS , SM/13998 | New | ADDITIONAL QUOTATION AMOUNT FOR MODIFIED ROUTE TO EFFECTING THE CONNECTION AT TENTULIA PH 1 ID 860320302 | 338/WBSEDCL-JJM | 17/12/2024 | 0 | WBSEDCL | 4.45 | 0 | 0 | 0
2891 | MURSHIDABAD | Murshidabad Division | TENTULIA AND ADJOINING MOUJAS PWSS , SM/13998 | New | Formal work order for the work of TENTULIA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall, IEP and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | 122/MURD | 13/01/2023 | 1173 | SOUNAK ENTERPRISE | 271.09 | 113.69 | 41.94 | 10
2892 | MURSHIDABAD | Berhampore Mechanical | TENTULIA AND ADJOINING MOUJAS PWSS , SM/13998 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under TENTULIA ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | 2018/MEDB | 19/06/2023 | 928 | S. G. ENTERPRISE | 20.29 | 0 | 0 | 50
2893 | MURSHIDABAD | Murshidabad Division | TENTULIA AND ADJOINING MOUJAS PWSS , SM/13998 | New | Balance work of Construction of Boundary wall of 55 m length at Tentulia PWSS in Kandi block of Murshidabad District under Murshidabad Division, PHE. Dte. | 1345/MURD | 11/06/2025 | 60 | AMIT KUMAR SAHA | 6.83 | 0 | 0 | 0
2894 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. , SM/14069 | Augmentation | Material Requisition To Resource Division | 201/BD-1/16 | 10/02/2024 | 0 | Resource Division | 303.88 | 0 | 0 | 0
2895 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. , SM/14069 | Augmentation | Material Requisition To Resource Division | 1510/BD-I/11 | 12/09/2024 | 0 | Resource Division | 5.48 | 0 | 0 | 0
2896 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. , SM/14069 | Augmentation | Augmentation of Nasipur zone_II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 625/BD-I | 03/08/2023 | 790 | M/S BIMALENDU BOSE | 374.96 | 194.24 | 51.8 | 10
2897 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. , SM/14069 | Augmentation | NASIPUR ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 454/BD-I | 15/03/2024 | 60 | INDRAJIT DUBEY | 22.41 | 14.28 | 63.71 | 50
2898 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. , SM/14069 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NASIPUR ZONE-II Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 319/BD-I | 24/02/2025 | 15 | MAMATA USHA ENTERPRISE | 9.01 | 0 | 0 | 0
2899 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. , SM/14069 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of NASIPUR ZONE - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 431/BD-I | 19/03/2025 | 60 | ABA CONTRACTOR | 18.98 | 0 | 0 | 0
2900 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. , SM/14069 | Augmentation | Construction Pump House Cum Chlorine Room at Head Work site of Nasipur Zone -II Water Supply Scheme under Jal Jevan Mission of Lalgola Block of Murshidabad District under Berhampore Division -I, PHE.Dte. | 823/BD-I | 18/06/2025 | 45 | M/S B. P. ENTERPRISE | 8.47 | 0 | 0 | 50
2901 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. , SM/14069 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for NASIPUR ZONE-I Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 48/BD-I | 25/04/2023 | 10 | ENVIROTECH SOLUTIONS | 2.45 | 2.45 | 100 | 100
2902 | MURSHIDABAD | Murshidabad Division | JAJAN AND ADJOINING MOUJAS PWSS , SM/13925 | New | Material Requisition To Resource Division | 1075/MURD/8 | 19/04/2023 | 0 | Resource Division | 22.01 | 0 | 0 | 0
2903 | MURSHIDABAD | Berhampore Mechanical | JAJAN AND ADJOINING MOUJAS PWSS , SM/13925 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under JAJAN ground water based water supply scheme under Block_ BHARATPUR-I Dist. - Murshidabad under MEDB, PHE Dte. | 1895/MEDB | 16/06/2023 | 92 | HANNAN BUILDERS PVT LTD | 22.18 | 15.62 | 70.42 | 10
2904 | MURSHIDABAD | Berhampore Mechanical | JAJAN AND ADJOINING MOUJAS PWSS , SM/13925 | New | New connection jajan ph-I | 109/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 4.06 | 0 | 0 | 0
2905 | MURSHIDABAD | Murshidabad Division | JAJAN AND ADJOINING MOUJAS PWSS , SM/13925 | New | JAJAN & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- BHARATPUR-I of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | 758/MURD | 16/03/2023 | 777 | GOURANGA MONDAL | 343.34 | 147.42 | 42.94 | 10
2906 | MURSHIDABAD | Murshidabad Division | JAJAN AND ADJOINING MOUJAS PWSS , SM/13925 | New | Allied work for Laying Distribution System, Construction of Boundary Wall, Approach Road & Land Development of Jajan PWSS in Bhratpur-I Block , KANDI Sub-Division under Murshidabad Division ,PHE. Dte. | 768/MURD | 13/03/2024 | 366 | GOURANGA MONDAL | 59.79 | 49.24 | 82.36 | 10
2907 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF SADHUKHALI ZONE-II PIPED WATER SUPPLY SCHEME. , SM/14951 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SADHUKHALI Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 41/BD-I | 20/04/2023 | 10 | TECHVISION | 2.63 | 2.56 | 100 | 100
2908 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF SADHUKHALI ZONE-II PIPED WATER SUPPLY SCHEME. , SM/14951 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,ZONE-II of SADHUKHALI ground water based water supply scheme under Block- Beldanga-II, Dist. Murshidabad under MEDB, PHE Dte. | 3786/MEDB | 03/11/2023 | 92 | SARKAR CONSTRUCTION | 11.37 | 0 | 0 | 7
2909 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF SADHUKHALI ZONE-II PIPED WATER SUPPLY SCHEME. , SM/14951 | Augmentation | Material Requisition To Resource Division | 196/BD-I/26 | 09/02/2024 | 0 | Resource Division | 3.7 | 0 | 0 | 0
2910 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF SADHUKHALI ZONE-II PIPED WATER SUPPLY SCHEME. , SM/14951 | Augmentation | Augmentation of Sadhukhali Zone-II Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant( AIRP ), pump house ,boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga -II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. [2nd Call for WBPHED/EE/BD-I/NIeT-20 of 2022 ¿ 2023(sl-02)] | 845/BD-I | 05/09/2023 | 620 | RAJ KUMAR MONDAL | 302.11 | 0 | 0 | 0
2911 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUNGAI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14833 | Augmentation | Construction of Boundary wall (East Side) at SUNGAI Water Supply Scheme under Berhampore Sub-Division, P.H.E. Dte. in the District Murshidabad. | 65/BSD | 24/02/2022 | 30 | PRASANTA BISWAS | 4.82 | 4.72 | 100 | 100
2912 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUNGAI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14833 | Augmentation | Material Requisition To Resource Division | 1219/MURD/06 | 03/05/2023 | 0 | Resource Division | 14.2 | 0 | 0 | 0
2913 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUNGAI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14833 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.01 | 100 | 80
2914 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUNGAI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14833 | Augmentation | Construction of Boundary wall (Fornt Side) at SUNAI Water Supply Scheme under Berhampore Sub-Division, P.H.E. Dte. in the District Murshidabad. | 63/BSD | 24/02/2022 | 45 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 4.85 | 4.23 | 100 | 100
2915 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUNGAI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14833 | Augmentation | Construction of Boundary wall (North Side) at SUNAI Water Supply Scheme under Berhampore Sub-Division, P.H.E. Dte. in the District Murshidabad. | 64/BSD | 24/02/2022 | 45 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 4.84 | 4.36 | 100 | 100
2916 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUNGAI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14833 | Augmentation | FHTC Connection to 349 nos household, Laying of Distribution System for Augmentation of SUNGAI PWSS in Berhampore Block , Berhampore Sub-Division under Murshidabad Division , PHE. Dte.(Part_B) | 2406/MURD | 07/08/2023 | 205 | ANKITA ENTERPRISE | 58.83 | 56.15 | 100 | 60
2917 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUNGAI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14833 | Augmentation | Material Requisition To Resource Division | 1811/MURD/14 | 20/06/2024 | 0 | Resource Division | 2.55 | 0 | 0 | 0
2918 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUNGAI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14833 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 3.73 | 200 | 1
2919 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SUNGAI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14833 | Augmentation | Construction of 100 Cum OHR, Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 65 Cum capacity for Augmentation of SUNGAI PWSS in Berhampore Block , Berhampore Sub-Division under Murshidabad Division , PHE.Dte.(Part_A) | 1869/MURD | 14/07/2023 | 764 | BABLU ENTERPRISE | 94.57 | 0 | 0 | 30
2920 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-A) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13995 | Augmentation | Material Requisition To Resource Division | 1147/MURD/12 | 27/04/2023 | 0 | Resource Division | 110.07 | 0 | 0 | 0
2921 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-A) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13995 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I and II ,ZONE-I under BAZEGAZIPUR ,PART-A ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | 2080/MEDB | 19/06/2023 | 92 | M/S S. S. ENTERPRISE (DOMKAL) | 25.46 | 19.42 | 76.28 | 8
2922 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-A) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13995 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 1.06 | 100 | 100
2923 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-A) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13995 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 0 | 21
2924 | MURSHIDABAD | Berhampore Division I | Augmentation of Bali Zone-III pipe water supply scheme . , SM/15228 | Augmentation | Material Requisition To Resource Division | 196/BD-I/19 | 09/02/2024 | 0 | Resource Division | 18.26 | 0 | 0 | 0
2925 | MURSHIDABAD | Berhampore Division I | Augmentation of Bali Zone-III pipe water supply scheme . , SM/15228 | Augmentation | Augmentation of Bali Zone-III Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 972/BD-I | 18/10/2023 | 532 | BISWAJYOTI BHATTACHARYYA | 322.8 | 104.56 | 32.39 | 95
2926 | MURSHIDABAD | Berhampore Division I | Augmentation of Bali Zone-III pipe water supply scheme . , SM/15228 | Augmentation | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of Bali Zone-III" ground water supply scheme in NAWDA Block,under Berhampore Division-I, P.H.E Dte(Capacity-57.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing | 993/BD-I | 20/06/2024 | 365 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 165.61 | 0 | 0 | 0
2927 | MURSHIDABAD | Berhampore Division I | Augmentation of Bali Zone-III pipe water supply scheme . , SM/15228 | Augmentation | BALI ZONE-III PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of NAWDA Block, Murshidabad District under Berhampore Division-I, PHE.Dte | 450/BD-I | 15/03/2024 | 338 | ANUPA ENTERPRISE | 21.03 | 3.84 | 18.27 | 100
2928 | MURSHIDABAD | Berhampore Division I | Augmentation of Bali Zone-III pipe water supply scheme . , SM/15228 | Augmentation | Construction Pump House Cum Chlorine Room at Head Work site of BALI ZONE-III Water Supply Scheme, under Jal Jevan Mission within Nawda Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | 271/BD-I | 11/02/2025 | 239 | M/S MUKTI CONSTRUCTION | 8.55 | 0 | 0 | 90
2929 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- I Piped Water Supply Scheme. , SM/14950 | Augmentation | Material Requisition To Resource Division | 61/BD-1/12 | 27/04/2023 | 0 | Resource Division | 35.26 | 0 | 0 | 0
2930 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- I Piped Water Supply Scheme. , SM/14950 | Augmentation | Augmentation of Kazipara Zone_I Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Jalangi Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 505/BD-I | 24/07/2023 | 180 | M/S S.DAS & ENTERPRISE | 178 | 0 | 0 | 10
2931 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- I Piped Water Supply Scheme. , SM/14950 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KAJIPARA Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1764/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.74 | 2.74 | 100 | 100
2932 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- I Piped Water Supply Scheme. , SM/14950 | Augmentation | Construction of Boundary Wall with Main Entrance gate and barbed wire facing and service road for approach at Augmentation of KAZIPARA ZONE-I PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | 1059/BD-I | 03/07/2024 | 241 | MUNNA AGROTECH ENTERPRISE | 16.5 | 9.71 | 90.95 | 90
2933 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Kajipara Zone- I Piped Water Supply Scheme. , SM/14950 | Augmentation | Improvement of OHR (450 Cum) of Ground Water Based Supply Scheme for Augmentation of Kazipara Zone-I of Jalangi block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | 934/BD-I | 10/06/2024 | 30 | M/S. MONDAL ENTERPRISE | 11.42 | 0 | 0 | 100
2934 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at JALANGI Zone-I, Ground water Based PWSS, Block-Jalangi , Dist- Murshidabad under MEDB, PHE Dte. , SM/15282 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at JALANGI Zone-I, Ground water Based PWSS, Block-Jalangi , Dist- Murshidabad under MEDB, PHE Dte.¿. | 3743/MEDB | 03/11/2023 | 92 | HARA PROSAD DAS | 6.39 | 0 | 0 | 0
2935 | MURSHIDABAD | Murshidabad Division | GHORAMARA PIPED WATER SUPPLY SCHEME. , SM/15049 | New | Material Requisition To Resource Division | 1230/MURD/14 | 04/05/2023 | 0 | Resource Division | 14.54 | 0 | 0 | 0
2936 | MURSHIDABAD | Murshidabad Division | GHORAMARA PIPED WATER SUPPLY SCHEME. , SM/15049 | New | Formal work order for the work of GHORAMARA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Samserganj Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | 375/MURD | 10/02/2023 | 365 | PRODEEP KUMAR GHOSH | 295.5 | 0 | 0 | 0
2937 | MURSHIDABAD | Berhampore Mechanical | GHORAMARA PIPED WATER SUPPLY SCHEME. , SM/15049 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I II & III under GHORAMARA ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | 1929/MEDB | 16/06/2023 | 183 | ORIENTAL ENGINEERING CO. | 31.23 | 0 | 0 | 0
2938 | MURSHIDABAD | Murshidabad Division | GHORAMARA PIPED WATER SUPPLY SCHEME. , SM/15049 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHORAMARA Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | 3394/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 15.24 | 100 | 50
2939 | MURSHIDABAD | Murshidabad Division | GHORAMARA PIPED WATER SUPPLY SCHEME. , SM/15049 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 4.4 | 100 | 100
2940 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/14942 | Augmentation | Material Requisition To Resource Division | 1210/MURD/18 | 02/05/2023 | 0 | Resource Division | 24.99 | 0 | 0 | 0
2941 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/14942 | Augmentation | Providing FHTC Connection to 1823 no household, Overhauling of RCC 350 Cum OHR & Repair of Boundary Wall =150 m at T/W-I site & T/W-II site for Augmentation of FATELLAPUR Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte | 903/MURD | 29/03/2023 | 180 | M/S M.S. ENTERPRISE | 106.37 | 0 | 0 | 0
2942 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/14942 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at FATELLAPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti-I Block under Murshidabad Division, P.H. Engineering Dte. | 3837/MURD | 14/12/2023 | 21 | SUJIT KUMAR SAHA | 11.79 | 0 | 0 | 100
2943 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/14942 | Augmentation | Laying of Rising Main & Distribution System for Augmentation of FATELLAPUR Piped Water Supply in SUTI-I Block under Murshidabad Division, PHE. Dte. | 743/MURD | 16/03/2023 | 1151 | RAJU ENTERPRISE | 66.32 | 32.52 | 49.03 | 36
2944 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/14942 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 60 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for FATELLAPUR Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division , PHE Dte. | 1155/MURD | 20/05/2025 | 60 | WATER TECH | 33.62 | 0 | 0 | 0
2945 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/14942 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.25 | 100 | 100
2946 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED FATELLAPUR PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/14942 | Augmentation | Sinking of 1NO. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Fatellapur Water Supply Scheme at Suti-I Block of Jangipur Sub-Division under Murshidabad Division, P.H.Engineering Dte. | 2131/MURD | 26/07/2024 | 224 | KHOKAN BISWAS | 11.76 | 0 | 0 | 100
2947 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 69.38 | 1
2948 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhanjha (village code 315503) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 242/BD-I | 03/03/2022 | 20 | ANKITA ENTERPRISE | 4.64 | 3.4 | 73.24 | 1
2949 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dharampur Ramna (village code 315497) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 153/BD-I | 11/02/2022 | 70 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 59.15 | 41.11 | 69.5 | 1
2950 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramkrishnapur (village code 315490) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2251/BD-I | 21/12/2021 | 45 | S DUTTA | 28.82 | 0 | 0 | 0
2951 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Swaruppur (Village code 315505) under Lochanmati (Zone-E) Water Supply Scheme of Central Sector Part-II in Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-10) | 1905/BD-I | 08/10/2021 | 180 | M/S RUBIET HOSSAIN | 144.19 | 0 | 0 | 0
2952 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lochanmati Dangapara (village code 315498) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2201/BD-I | 10/12/2021 | 90 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 85.79 | 81.81 | 95.36 | 1
2953 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kaludiar (village code 315501) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 154/BD-I | 11/02/2022 | 45 | MUNNA AGROTECH ENTERPRISE | 34.19 | 0 | 0 | 0
2954 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tekona (village code 315492) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 186/BD-I | 18/02/2022 | 1279 | DAS ENTERPRISE | 32.28 | 0 | 0 | 70
2955 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sankarpur (village code 315489) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2202/BD-I | 10/12/2021 | 689 | UTTAM MUKHERJEE | 76.01 | 65.33 | 85.96 | 87
2956 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dharampur (village code 315496) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2304/BD-I | 28/12/2021 | 30 | SUKUMAR ROY | 22.73 | 21.68 | 100 | 1
2957 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Janarddanpur (village code 315493) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 155/BD-I | 11/02/2022 | 30 | ANKITA ENTERPRISE-GOPEJAN(NATHPARA) | 10.56 | 10.17 | 100 | 1
2958 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Siddhi Nandi (village code 315504) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 241/BD-I | 03/03/2022 | 45 | PRANAB KUMAR GHOSH | 36.64 | 30.74 | 100 | 85
2959 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jamlabad (village code 315495) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 156/BD-I | 11/02/2022 | 20 | U.S BUILDERS | 7.58 | 5.6 | 100 | 1
2960 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sundalpur (village code 315502) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2204/BD-I | 10/12/2021 | 30 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 24.6 | 22.86 | 100 | 1
2961 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khamarbati (village code 315494) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2253/BD-I | 21/12/2021 | 30 | RAJEN DAS | 24.27 | 22.02 | 100 | 1
2962 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Taritpur (Village code 315499) under Lochanmati (Zone-E) Water Supply Scheme of Central Sector Part-II in Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-09) | 1903/BD-I | 08/10/2021 | 180 | MS RUBIET HOSSAIN | 116.3 | 79.26 | 100 | 69
2963 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarbangapur (village code 315509) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2203/BD-I | 10/12/2021 | 45 | DEBASISH SARKAR | 30.19 | 21.15 | 100 | 1
2964 | MURSHIDABAD | Murshidabad Division | Augmentation of Sikdarpur water supply scheme in Samserganj Block of Murshidabad District . , SM/16242 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 7.64 | 200 | 1
2965 | MURSHIDABAD | Murshidabad Division | Augmentation of Sikdarpur water supply scheme in Samserganj Block of Murshidabad District . , SM/16242 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
2966 | MURSHIDABAD | Murshidabad Division | Augmentation of Sikdarpur water supply scheme in Samserganj Block of Murshidabad District . , SM/16242 | Augmentation | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 300 & 100 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Joykrishnapur Zone-I, Zone- II & Sikdarpur PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 3243/MURD | 15/10/2023 | 365 | BIJAY CHOWDHURY | 894.65 | 0 | 0 | 0
2967 | MURSHIDABAD | Murshidabad Division | Augmentation of Sikdarpur water supply scheme in Samserganj Block of Murshidabad District . , SM/16242 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sikdarpur Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte | 3833/MURD | 14/12/2023 | 627 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 0 | 40
2968 | MURSHIDABAD | Murshidabad Division | Augmentation of Sikdarpur water supply scheme in Samserganj Block of Murshidabad District . , SM/16242 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for SIKDARPUR Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division, PHE Dte. | 962/MURD | 30/04/2025 | 60 | SAMAR MUKHERJEE | 19.62 | 0 | 0 | 0
2969 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Sikdarpur water supply scheme in Samserganj Block of Murshidabad District . , SM/16242 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Sikdarpur water supply scheme in Samserganj Block of Murshidabad District under MEDB, PHE Dte. | 321/MEDB | 10/02/2025 | 89 | M/S S. R. ENTERPRISE | 22.71 | 0 | 0 | 0
2970 | MURSHIDABAD | Berhampore Division I | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16266 | New | Material Requisition To Resource Division | 61/BD-1/18 | 27/04/2023 | 0 | Resource Division | 11.87 | 0 | 0 | 0
2971 | MURSHIDABAD | Berhampore Mechanical | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16266 | New | NEW CONNECTION AT KHAGJANA PH-I | 105/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 4.03 | 0 | 0 | 0
2972 | MURSHIDABAD | Berhampore Mechanical | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16266 | New | NEW CONNECTION AT KHAGJANA PH-II |  | 26/11/2024 | 0 | WBSEDCL | 4.29 | 0 | 0 | 0
2973 | MURSHIDABAD | Berhampore Division I | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16266 | New | KHAGJANA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 218/BD-I | 17/05/2023 | 630 | S.K ENTERPRISE (RANITALA) | 53.17 | 7.81 | 14.68 | 65
2974 | MURSHIDABAD | Berhampore Division I | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16266 | New | KHAGJANA PWSS to accommodate FHTC, Laying Distribution System,, under Jal Jeevan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | 118/BD-I | 11/05/2023 | 180 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 96.97 | 32.53 | 33.55 | 50
2975 | MURSHIDABAD | Berhampore Division I | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16266 | New | Allied work of Laying of Distribution system for the work of Khagjana PWSS to accommodate FHTC, OHR, Laying distribution system, Rising Main under Jal Jeevan Mission of Bhagwangola- II Block, Murshidabad District under Berhampore Division-I, PHE Dte. (Part-A) | 1684/BD-I | 28/10/2024 | 155 | S.K ENTERPRISE (RANITALA) | 68.11 | 0 | 0 | 96
2976 | MURSHIDABAD | Berhampore Division I | KHAGJANA AND ITS ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16266 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KHAGJANA and Adjoining Mouzas PWSS (TW - II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division - I, P.H.Engineering Dte. (01 No TW). | 754/BD-I | 22/05/2025 | 15 | AJOY GHOSH | 9.01 | 0 | 0 | 0
2977 | MURSHIDABAD | Murshidabad Division | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16277 | New | Material Requisition To Resource Division | 1043/MURD/12 | 18/04/2023 | 0 | Resource Division | 13.2 | 0 | 0 | 0
2978 | MURSHIDABAD | Berhampore Mechanical | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16277 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SALU ground water based water supply scheme under Block_ Bharatpur-IIDist. - Murshidabad under MEDB, PHE Dte. | 1906/MEDB | 16/06/2023 | 92 | S. K. ENTERPRISE | 23.82 | 19.53 | 82 | 15
2979 | MURSHIDABAD | Berhampore Mechanical | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16277 | New | NEW CONNECTION AT SALU PH-I |  | 02/05/2024 | 0 | WBSEDCL | 4.09 | 0 | 0 | 0
2980 | MURSHIDABAD | Berhampore Mechanical | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16277 | New | NEW CONNECTION AT SALU PH-I | 67/WBSEDCL-JJM | 09/05/2024 | 0 | WBSEDCL | 4.09 | 0 | 0 | 0
2981 | MURSHIDABAD | Murshidabad Division | SALU AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16277 | New | SALU & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- BHARATPUR-II of Murshidabad District under Murshidabad Division, PHE. Dte. | 2642/MURD | 23/08/2023 | 584 | M/S. CHAKRABORTY & COMPANY | 601.12 | 257.39 | 42.82 | 20
2982 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Dhulauri Part-I Ground water Based PWSS, Block-Domkal , Dist- Murshidabad under MEDB, PHE Dte. , SM/15355 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Dhulauri Part-I Ground water Based PWSS, Block-Domkal , Dist- Murshidabad under MEDB, PHE Dte. | 4350/MEDB | 29/12/2023 | 91 | SWITCHING AVO ELECTRO POWER LTD | 6.44 | 0 | 0 | 0
2983 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at CHANDPUR PWSS (ZONE- I ) Ground water Based PWSS, Block-Nowda , Dist- Murshidabad under MEDB, PHE Dte. , SM/15331 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at CHANDPUR PWSS (ZONE- I ) Ground water Based PWSS, Block-Nowda , Dist- Murshidabad under MEDB, PHE Dte. | 3747/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.39 | 0 | 0 | 0
2984 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone- II A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. , SM/16239 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 8.3 | 200 | 1
2985 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone- II A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. , SM/16239 | Augmentation | Material Requisition To Resource Division | 1167/MURD/13 | 28/04/2023 | 0 | Resource Division | 122.55 | 0 | 0 | 0
2986 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Bhasaipaikar Zone- II A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. , SM/16239 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III ,Zone-IIA under Bhasaipaikar ground water based water supply scheme under Block_ Samserganj ,Dist. - Murshidabad under MEDB, PHE Dte. | 3683/MEDB | 03/11/2023 | 92 | DAS ENTERPRISE (CHOA) | 34.39 | 28.35 | 82.44 | 15
2987 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone- II A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. , SM/16239 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
2988 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone- II A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. , SM/16239 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0 | 0
2989 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (maximum 100 households) Village-Arazi Saikuli, Block-Murshidabad -Jiaganj, District- Murshidabad. , SM/16431 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Arazi Saikuli village, Block:- Murshidabad - Jiaganj under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3034 | 02/08/2023 | 92 | GANGULI ELECTRICAL CO. | 6.3 | 0 | 0 | 0
2990 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (maximum 100 households) Village-Arazi Saikuli, Block-Murshidabad -Jiaganj, District- Murshidabad. , SM/16431 | New | Mini Piped Water Supply Scheme for Arazi Saikuli under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 160/BD-I | 15/05/2023 | 90 | ABA CONTRACTOR | 28.97 | 0 | 0 | 0
2991 | MURSHIDABAD | Berhampore Division I | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Pashchim Gobindapur, Block- Murshidabad Jiaganj, District- Murshidabad. , SM/16438 | New | Mini Piped Water Supply Scheme for Paschim Gobindapur under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 739/BD-I | 17/08/2023 | 90 | M/S MODERN CONSTRUCTION AND CO | 23.95 | 0 | 0 | 0
2992 | MURSHIDABAD | Berhampore Mechanical | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Pashchim Gobindapur, Block- Murshidabad Jiaganj, District- Murshidabad. , SM/16438 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Pashchim Gobindapur village, Block:- Murshidabad Jiaganj under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3159/MEDB | 08/08/2023 | 92 | MITRA ASSOCIATE | 6.15 | 0 | 0 | 0
2993 | MURSHIDABAD | Berhampore Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE ¿ BILGOBRA , BLOCK- BHAGAWANGOLA-I, DISTRICT MURSHIDABAD. , SM/16439 | New | Mini Piped Water Supply Scheme for Bilgobra under Bhagwangola-I block of Murshidabad district under Berhampore division-I,P.H.E Dte | 185/BD-I | 17/05/2023 | 90 | BIJOY SINGHA | 26.73 | 0 | 0 | 0
2994 | MURSHIDABAD | Murshidabad Division | GOKUL CHAK PIPED WATER SUPPLY SCHEME . , SM/16043 | New | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 2.41 | 100 | 90
2995 | MURSHIDABAD | Murshidabad Division | GOKUL CHAK PIPED WATER SUPPLY SCHEME . , SM/16043 | New | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KATAKOBRA ZONE-I&II Water Supply Scheme and Gokul Chak Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 832/MURD | 15/03/2024 | 21 | NADIA TUBEWELLS | 11.78 | 10.93 | 100 | 100
2996 | MURSHIDABAD | Berhampore Mechanical | GOKUL CHAK PIPED WATER SUPPLY SCHEME . , SM/16043 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Gokul Chak ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | 3684/MEDB | 03/11/2023 | 92 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 22.14 | 0 | 0 | 15
2997 | MURSHIDABAD | Murshidabad Division | GOKUL CHAK PIPED WATER SUPPLY SCHEME . , SM/16043 | New | Construction of Ground Water Based Gokul Chak PWSS of accommodate FHTC(834 Nos), Laying Distribution System, Laying Rising Main, Switch Room, Boundary Wall in Domkal Block within Murshidabad District under Murshidabad Division, PHE Dte. | 3953/MURD | 26/12/2023 | 573 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 108.82 | 0 | 0 | 60
2998 | MURSHIDABAD | Murshidabad Division | GOKUL CHAK PIPED WATER SUPPLY SCHEME . , SM/16043 | New | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Islampur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | 2637/MURD | 23/09/2024 | 150 | INDRAJIT DUBEY | 8.72 | 0 | 0 | 100
2999 | MURSHIDABAD | Murshidabad Division | SYAMPUR AND ADJOINING MOUJAS PWSS , SM/16475 | New | Material Requisition To Resource Division | 1075/MURD/6 | 19/04/2023 | 0 | Resource Division | 10.59 | 0 | 0 | 0
3000 | MURSHIDABAD | Berhampore Mechanical | SYAMPUR AND ADJOINING MOUJAS PWSS , SM/16475 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Syampur ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | 2091/MEDB | 19/06/2023 | 92 | ARINDAM MAJUMDAR | 21.72 | 17.52 | 80.68 | 15
3001 | MURSHIDABAD | Berhampore Mechanical | SYAMPUR AND ADJOINING MOUJAS PWSS , SM/16475 | New | Shyampur PH-1 Application no- 300454852 | 234/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 5.34 | 0 | 0 | 0
3002 | MURSHIDABAD | Murshidabad Division | SYAMPUR AND ADJOINING MOUJAS PWSS , SM/16475 | New | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Kandi Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(89 Nos.) | 2635/MURD | 23/09/2024 | 281 | SABSAMAY | 9.85 | 0 | 0 | 80
3003 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- I B Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16172 | Augmentation | Material Requisition To Resource Division | 1167/MURD/29 | 28/04/2023 | 0 | Resource Division | 24.86 | 0 | 0 | 0
3004 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- I B Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16172 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I B Water Supply Scheme at Head Work Site, 2nd Site site at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | 1774/MURD | 06/07/2023 | 21 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 0 | 0
3005 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Mahadebnagar Zone- I B Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16172 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IB under Mahadebnagar ground water based water supply scheme under Block_ Farakka Dist. - Murshidabad under MEDB, PHE Dte. | 3670/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 22.94 | 17.56 | 76.53 | 60
3006 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- I B Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16172 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
3007 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Mahadebnagar Zone- I B Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16172 | Augmentation | NEW SERVICE CONNECTION AT MAHADEBNAGAR ZIB, PH1 C ID 304390379 |  | 03/09/2024 | 0 | WBSEDCL | 9.48 | 0 | 0 | 0
3008 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Mahadebnagar Zone- I B Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16172 | Augmentation | NEW SERVICE CONNECTION AT MAHADEBNAGAR ZIB, PH1 C ID 304390379 | 215/WBSEDCL-JJM | 11/09/2024 | 0 | WBSEDCL | 9.48 | 0 | 0 | 0
3009 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Mahadebnagar Zone- I B Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16172 | Augmentation | POWER CONNECTION AT PWSS Z 1B PH2 MAHADEBNAGAR APPLICATION NO.3004627439 | 41/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 3.5 | 0 | 0 | 0
3010 | MURSHIDABAD | Murshidabad Division | Augmentation of Jaykrishnapur Zone- I Water Supply Scheme Block - Samserganj , Dist- Murshidabad. , SM/16174 | Augmentation | Material Requisition To Resource Division | 1180/MURD/25 | 29/04/2023 | 0 | Resource Division | 39.84 | 0 | 0 | 0
3011 | MURSHIDABAD | Murshidabad Division | Augmentation of Jaykrishnapur Zone- I Water Supply Scheme Block - Samserganj , Dist- Murshidabad. , SM/16174 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
3012 | MURSHIDABAD | Murshidabad Division | Augmentation of Jaykrishnapur Zone- I Water Supply Scheme Block - Samserganj , Dist- Murshidabad. , SM/16174 | Augmentation | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 300 & 100 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Joykrishnapur Zone-I, Zone- II & Sikdarpur PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 3243/MURD | 15/10/2023 | 365 | BIJAY CHOWDHURY | 894.65 | 0 | 0 | 0
3013 | MURSHIDABAD | Murshidabad Division | Augmentation of Jaykrishnapur Zone- I Water Supply Scheme Block - Samserganj , Dist- Murshidabad. , SM/16174 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jaykrishnapur Zone- I & Hilora Zone-II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 1769/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 18.45 | 0 | 0 | 100
3014 | MURSHIDABAD | Murshidabad Division | Augmentation of Jaykrishnapur Zone- I Water Supply Scheme Block - Samserganj , Dist- Murshidabad. , SM/16174 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 4.96 | 100 | 100
3015 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15919 | Augmentation | Material Requisition To Resource Division | 1210/MURD/06 | 02/05/2023 | 0 | Resource Division | 137.87 | 0 | 0 | 0
3016 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15919 | Augmentation | Material Requisition To Resource Division | 495/MURD/11 | 15/02/2024 | 0 | Resource Division | 25.47 | 0 | 0 | 0
3017 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15919 | Augmentation | Laying of Distribution System for Augmentation of KADOA (ZONE-I) Part B PWSS in SUTI-I Block under Murshidabad Division, PHE.Dte. | 807/MURD | 22/03/2023 | 741 | M/S GUNGUN CONSTRUCTION | 137.96 | 110.9 | 80.38 | 92
3018 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15919 | Augmentation | Providing FHTC Connection to 923 no household and Overhauling of RCC 450 Cum OHR for Augmentation of KADOA (ZONE-I) Part B Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. | 829/MURD | 23/03/2023 | 1099 | SAMAR MUKHERJEE | 127.28 | 67.94 | 53.38 | 90
3019 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART B PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15919 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 1.74 | 100 | 100
3020 | MURSHIDABAD | Murshidabad Division | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16280 | New | Material Requisition To Resource Division | 1075/MURD/16 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
3021 | MURSHIDABAD | Murshidabad Division | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16280 | New | Material Requisition To Resource Division | 79/MURD/05 | 09/01/2024 | 0 | Resource Division | 3.82 | 0 | 0 | 0
3022 | MURSHIDABAD | Murshidabad Division | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16280 | New | Material Requisition To Resource Division | MURD/439/02 | 08/02/2024 | 0 | Resource Division | 0.03 | 0 | 0 | 0
3023 | MURSHIDABAD | Berhampore Mechanical | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16280 | New | NEW SERVICE CONNECTION AT TALBONA , BHAGULIA PH I, ID304233557 | 269/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 12.52 | 0 | 0 | 0
3024 | MURSHIDABAD | Berhampore Mechanical | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16280 | New | NEW SERVICE CONNECTION AT BHAGULIA PH II, ID304233683 | 270/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 7.24 | 0 | 0 | 0
3025 | MURSHIDABAD | Murshidabad Division | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16280 | New | Formal work order for BHAGULIA & adjoining mouzas PWSS to accommodate FHTC under Jal Jeevan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | 619/MURD | 03/03/2023 | 760 | SUMAN ENTERPRISE AND SUMAN AQUA | 183.62 | 160.09 | 87.19 | 50
3026 | MURSHIDABAD | Berhampore Mechanical | BHAGULIA AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16280 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under BHAGULIA ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | 3700/MEDB | 03/11/2023 | 790 | A.G. ENTERPRISE | 20.9 | 3.09 | 14.78 | 70
3027 | MURSHIDABAD | Berhampore Mechanical | CHAK RAMPRASAD PIPED WATER SUPPLY SCHEME, BLOCK -JALANGI ,DIST - MURSHIDABAD. , SM/16209 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chak Ramprasad village, Block:- Jalangi under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3628/MEDB | 03/11/2023 | 92 | SREE RADHA ELECTRICAL | 6.32 | 0 | 0 | 0
3028 | MURSHIDABAD | Murshidabad Division | CHAK RAMPRASAD PIPED WATER SUPPLY SCHEME, BLOCK -JALANGI ,DIST - MURSHIDABAD. , SM/16209 | New | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 2.37 | 100 | 90
3029 | MURSHIDABAD | Murshidabad Division | CHAK RAMPRASAD PIPED WATER SUPPLY SCHEME, BLOCK -JALANGI ,DIST - MURSHIDABAD. , SM/16209 | New | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHAK RAMPRASAD and Dakshin Khanda Zone - IA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 2778/MURD | 01/09/2023 | 14 | SARKAR WATER SUPPLY AGENCY | 9.21 | 0 | 0 | 100
3030 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Arrangement of drinking water facilities of different Anganwadi Centers by sinking of tube well with installation of submersible pump & construction of soak well of Kandi block under Kandi Sub-Division, P.H.E Dte. in the district of Murshidabad. (Part-A). (For 2 nos AWC). | 79/KSD | 22/02/2021 | 30 | BHOWMIK CONSTRUCTION | 3.87 | 3.77 | 100 | 1
3031 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Arrangement of drinking water facilitates of different Anganwadi Centers by sinking of tube well with installation of submersible pump & construction of soak well of Kandi block under Kandi Sub-Division, P.H.E Dte. in the district of Murshidabad. (Part-B). (For 2 nos AWC). | 80/KSD | 22/02/2021 | 30 | BIJOY SINGHA | 3.87 | 3.82 | 100 | 1
3032 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Arrangement of drinking water facilities of different Anganwadi Centers by sinking of tube well with installation of submersible pump & construction of soak well of Burwan block under Kandi Sub-Division, P.H.E Dte. in the district of Murshidabad. (Part-A). (For 2 nos AWC). | 85/KSD | 22/02/2021 | 30 | PRAVAT KUMAR GHOSH | 3.87 | 0 | 0 | 1
3033 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Arrangement of drinking water facilities of different Anganwadi Centers by sinking of tube well with installation of submersible pump & construction of soak well of Burwan block under Kandi Sub-Division, P.H.E Dte. in the district of Murshidabad. (Part-B). (For 2 nos AWC). | 86/KSD | 22/02/2021 | 30 | PARTHA PRATIM DAS | 3.87 | 0 | 0 | 1
3034 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Extension of UPVC Pipeline from existing piped water supply scheme & connection of street stand post & construction of soak well to different Anganwadi centers of Burwan block under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. (Part-A).( For 9 nos AWC). | 76/KSD | 22/02/2021 | 30 | DAS CONSTRACTION | 4.82 | 4.8 | 100 | 1
3035 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Laying of distribution system pipe line and connection with street stand post and Construction of soak well in connection with Dengue control for different Anganwadi Centres under Nowda Development Block (1) Tiakata daspara .2.) Tiakata . 3) Jamalpur 4) Tiakata Halderpara under Berhampore Sub division. P.H.E.Dte. | 3298/MURD | 29/12/2020 | 15 | MAA SANKARI ENTERPRISE | 3.33 | 2.63 | 100 | 1
3036 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Extension of UPVC Pipeline from existing piped water supply scheme & connection of street stand post & construction of soak well to different Anganwadi centers of Burwan block under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. (Part-B).( For 9 nos AWC). | 77/KSD | 22/02/2021 | 30 | U.S BUILDERS | 4.83 | 4.8 | 100 | 1
3037 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Arrangement of drinking water facilities of different Anganwadi Centers by sinking of tube well with installation of submersible pump & construction of soak well of Bharatpur-I block under Kandi Sub-Division, P.H.E Dte. in the district of Murshidabad. (Part-B). (For 2 nos AWC). | 82/KSD | 22/02/2021 | 30 | PRADIP MAHATO | 3.87 | 3.71 | 100 | 1
3038 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Repairing & renovation of existing Sajaldhara (AIRP), including sinking of 125 mm x 50 mm dia 60.0 mtr. Deep tubewell at 34 No Harekrishnapur ICDS Center Sajaldhara Prakalpa, Jalangi Block under Islampur Sub-Division under Murshidabad Division, PHE Dte | 42/ISD. | 28/01/2022 | 30 | ARJU CONSTRUCTION | 4.47 | 0 | 0 | 1
3039 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Arrangement of drinking water facilieites of different Anganwandi centers by sinking of tube well instllation of submersible pump and construction of soad well of Burwan Blok under Kandi Sub Div Phe DTE. Tender no - 09 of 21-22 by AE KSD | 351-MSD/21-22 | 04/03/2022 | 0 | PARTHA PRATIM DAS | 1.19 | 0 | 0 | 0
3040 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Arrangement of drinking water facilities of different Anganwadi Centers by sinking of tube well with installation of submersible pump & construction of soak well of BHARATPUR-II BLOCK under Kandi Sub-Division, P.H.E Dte. in the district of Murshidabad. Tender no - 18 of 21-22 by AE KSD | 312-MSD/21-22 | 17/02/2022 | 0 | GOUTAM KUMAR CHAUDHURI | 3.82 | 0 | 0 | 0
3041 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Arrangement of drinking water facilieites of different Anganwandi centers by sinking of tube well instllation of submersible pump and construction of soak well of Burwan Blok under Kandi Sub Div Phe DTE. Tender no - 35 of 21-22 by AE KSD | 397-MSD/21-22 | 29/03/2022 | 0 | PRAVAT KUMAR GHOSH | 3.59 | 0 | 0 | 0
3042 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Extension of UPVC Pipeline from existing piped water supply scheme & connection of street stand post & construction of soak well to different Anganwadi centers of Bharatpur-II block under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. (Part-B). ( For 9 nos AWC). | 26-MSD/22-23 | 14/04/2022 | 0 | DIPAK BHOWMIK | 4.82 | 0 | 0 | 0
3043 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Extension of UPVC pipeline from existing piped water supply scheme and connection of street stand post and construction of soak well to diff Anganwadi centers of KSD PHE DTE. PART-A (FOR 9 NOS AWC). Tender no - 09 of 22-23 by AE KSD. | 211-MSD/22-23 | 18/07/2022 | 0 | MARUTI CONSTRUCTION AND CO | 4.74 | 0 | 0 | 0
3044 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Arrangement of drinking water facilities of different Anganwadi Centers by sinking of tube well with installation of submersible pump & construction of soak well of Bharatpur-II block under Kandi Sub-Division, P.H.E Dte. in the district of Murshidabad. (Part-A). (For 2 nos AWC). | 313-MSD/21-22 | 17/02/2022 | 0 | M/S. ADHIKARY CONSTRUCTION | 3.79 | 0 | 0 | 0
3045 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Extension of piped water supply to Anganwadi Centres(AWCs) located within the command area of PWS scheme at i) Suti -II block, (ii) Sagardighi block,(iii) Bharatpur -II block, (iv) Bharatpur -I block ,(v) Raghunathganj-I Block, (vi) Suti-I Block (vii) Raninagar -II Block,(viii) Raghunathganj-II Block ,(ix) Nabagram block, (x) Samserganj Block & (xi) Kandi block under Murshidabad Division, P.H.E. Dte. In the district Murshidabad. Tender no - 20 of 21-22 by SE MC | 367-MSD/21-22 | 11/03/2022 | 0 | MAHAVIR PUMPS MANUFACTRURING PVT. LTD. | 129.4 | 0 | 0 | 0
3046 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Extension of UPVC Pipeline from existing piped water supply scheme & connection of street stand post & construction of soak well to different Anganwadi centers of Bharatpur-I block under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. (Part-A). (For 9 nos AWC). | 73/KSD | 22/02/2021 | 30 | GHOSH BUILDERS | 4.81 | 3.03 | 62.99 | 0
3047 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Formal work order for extension of piped water supply to Anganwadi Centres (AWCs) located within the command area of PWS scheme at i) Domkal block,(ii) Jalangi block,(iii) Burwan block, (iv) Nowda block & (v) Raninagar-I Block under Murshidabad Division,P.H.E. Dte. In the district Murshidabad. | 2597/MURD | 25/08/2021 | 180 | NAYLA CONSTRUCTION | 262.69 | 174.59 | 100 | 1
3048 | MURSHIDABAD | Murshidabad Division | Extension of PWS to Anganwadi Centers (AWCs), located within the command area of PWSS under Murshidabad Division. , SM/08721 | Anganwadi | Formal work order for Extension of piped water supply to Anganwadi Centres(AWCs) located within the commandarea of PWS scheme at i) Suti -II block,(ii) Sagardighi block,(iii) Bharatpur -II block, (iv) Bharatpur -I block ,(v)Raghunathganj-I Block,(vi) Suti-I Block (vii) Raninagar -II Block,(viii) Raghunathganj-II Block ,(ix) Nabagram block, (x)Samserganj Block & (xi) Kandi block under Murshidabad Division,P.H.E. Dte. In the district Murshidabad | 1933/MURD | 22/07/2021 | 180 | MAHAVIR PUMPS MANUFACTRURING PVT. LTD. | 466.68 | 161.56 | 100 | 1
3049 | MURSHIDABAD | Murshidabad Division | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16397 | Augmentation | Material Requisition To Resource Division | 1219/MURD/39 | 03/05/2023 | 0 | Resource Division | 78.66 | 0 | 0 | 0
3050 | MURSHIDABAD | Murshidabad Division | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16397 | Augmentation | Formal work order for Augmentation of Domkal Zone-I (Part-B) & Domkal Zone - II (Part - A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 692/MURD | 10/03/2023 | 280 | M/S. J. A. CONSTRUCTION | 107.58 | 9.89 | 28.26 | 10
3051 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16397 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,ZONE-II, Part-A under DOMKAL ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | 3718/MEDB | 03/11/2023 | 92 | M/S S. R. ENTERPRISE | 33.53 | 0 | 0 | 5
3052 | MURSHIDABAD | Murshidabad Division | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16397 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 4.47 | 100 | 100
3053 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16397 | Augmentation | NEW CONNECTION AT DOMKALI Z-II PH-II |  | 14/11/2024 | 0 | WBSEDCL | 5.48 | 0 | 0 | 0
3054 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16397 | Augmentation | Domkal Zone-2 PH_1 Application No-3004548731 | 268/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 5.4 | 0 | 0 | 0
3055 | MURSHIDABAD | Murshidabad Division | Augmentation of Domkal Piped Water Supply Scheme Zone-II (Part-A) Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16397 | Augmentation | Augmentation of Domkal Zone-II (Part-A) Ground Water Based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 1311/MURD | 11/05/2023 | 916 | MAHMOOD ASSOCIATES PRIVATE LIMITED | 593.84 | 362.96 | 61.12 | 10
3056 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-I) PIPED WATER SUPPLY SCHEME. , SM/16566 | Augmentation | Material Requisition To Resource Division | 1180/MURD/31 | 29/04/2023 | 0 | Resource Division | 55.46 | 0 | 0 | 0
3057 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-I) PIPED WATER SUPPLY SCHEME. , SM/16566 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 0.53 | 24.38 | 100
3058 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-I) PIPED WATER SUPPLY SCHEME. , SM/16566 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Barabil Raghunathpur Water Supply Scheme of TW-I under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3062/MURD | 17/11/2022 | 30 | GENUINE | 11.75 | 8.53 | 72.63 | 100
3059 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-I) PIPED WATER SUPPLY SCHEME. , SM/16566 | Augmentation | Augmentation of Ground Water Based Barabil Raghunathpur zone-I PWSS to accommodate FHTC of 105 nos household, Laying Distribution System, Laying Rising Main , Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works,Repair of Boundary Wall at T/W-I site & T/W-II site &Overhauling of R.C.C. elevated reservoir 350 Cum capacity of staging hight 20 mtr. for Barabil Raghunathpur ( ZONE-I ) Ground water based Piped water supply scheme at Jalangi Block within Murshidabad District under Murshidabad Division, PHE Dte. | 3355/MURD | 30/10/2023 | 150 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 155.66 | 0 | 0 | 30
3060 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. , SM/16622 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 12(Forteen) nos existing commisioned PWSS Nawda & Hariharpara Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jagaipur, Chandkati, Mahammadpur, Ghoramara, Sarbangapur Zone-IA, Zone-IB. Zone-II, Kismat Imadpur Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division. | 2790/MURD | 04/09/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 29.41 | 0 | 0 | 0
3061 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. , SM/16622 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Hariharpara & Nawda Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | 286/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 53.26 | 4.92 | 100 | 1
3062 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. , SM/16622 | Augmentation | Balance and allied works for providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission) and under command area of village of GHORAMARA (Village Code -315515) under Ghoramara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 154/BSD | 12/04/2022 | 30 | M/S M.S. ENTERPRISE | 4.69 | 4.59 | 100 | 1
3063 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. , SM/16622 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under GHORAMARA ground water based water supply scheme under Block_ NAWDA Dist. - Murshidabad under MEDB, PHE Dte. | 4347/MEDB | 29/12/2023 | 91 | BHABANI PRASAD MANNA | 33.55 | 0 | 0 | 0
3064 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. , SM/16622 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen(RDS) filter at GHORAMARA Water Supply Scheme atHead Work Site, 2nd Site site at Nawda Block under Murshidabad Division, P.H. Engineering Dte. | 1760/MURD | 06/07/2023 | 21 | SUJIT KUMAR SAHA | 18.45 | 12.97 | 100 | 100
3065 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. , SM/16622 | Augmentation | Providing FHTC Connection to 176 nos household ,Construction of 200 Cum OHR, Rising Main , for Augmentation work of GHORAMARA PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. (part_A) | 906/MURD | 22/03/2023 | 1320 | PRATICHI ENTERPRISE | 120.97 | 53.18 | 43.96 | 80
3066 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. , SM/16622 | Augmentation | Laying of Distribution System, Repairing & Vertical Extention of Boundary Wall, Special repair and renovation of existing 1 (One) Nos Pump House and Alied Works for Augmentation work of GHORAMARA PWSS in NAWDA Block under Murshidabad Division , PHE.Dte. (part_B) | 901/MURD | 29/03/2023 | 917 | M/S RUBIET HOSSAIN | 172.57 | 4.85 | 2.81 | 20
3067 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. , SM/16622 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0 | 0
3068 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for GHORAMARA Block - Nawda District - Murshidabad. , SM/16622 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for GHORAMARA Ground Based Water Supply Scheme in Nawda Block under Murshidabad Division ,PHE Dte. | 1190/MURD | 23/05/2025 | 60 | M/S. GOUTAM CHAKRABORTY | 23.01 | 0 | 0 | 0
3069 | MURSHIDABAD | Berhampore Division I | GOBINDAPUR PWSS , SM/16784 | New | Material Requisition To Resource Division | 61/BD-1/14 | 27/04/2023 | 0 | Resource Division | 17.81 | 0 | 0 | 0
3070 | MURSHIDABAD | Berhampore Division I | GOBINDAPUR PWSS , SM/16784 | New | Material Requisition To Resource Division | 2096/BD-I/6 | 25/11/2024 | 0 | Resource Division | 4.65 | 0 | 0 | 0
3071 | MURSHIDABAD | Berhampore Mechanical | GOBINDAPUR PWSS , SM/16784 | New | NEW CONNECTION GOBINDAPUR PH-1 | 459/WBSEDCL-JJM | 18/03/2024 | 0 | WBSEDCL | 7.49 | 0 | 0 | 0
3072 | MURSHIDABAD | Berhampore Division I | GOBINDAPUR PWSS , SM/16784 | New | GOBINDAPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jeevan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 142/BD-I | 15/05/2023 | 1047 | DEBASISH SARKAR | 73.41 | 10.51 | 14.31 | 30
3073 | MURSHIDABAD | Berhampore Division I | GOBINDAPUR PWSS , SM/16784 | New | GOBINDAPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Berhampore Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 219/BD-I | 17/05/2023 | 716 | AZAD CONSTRUCTION & CO. | 40.55 | 11.5 | 28.36 | 90
3074 | MURSHIDABAD | Berhampore Division I | GOBINDAPUR PWSS , SM/16784 | New | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Gobindrapur" ground water supply scheme in Berhampore Block, under Berhampore Division-I, P.H.E Dte. (Capacity-34 Cum/hr.) Type-4- Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing Unit | 997/BD-I | 20/06/2024 | 365 | ACQUA CONSTRUCTION CONSORTIUM | 146.58 | 0 | 0 | 0
3075 | MURSHIDABAD | Berhampore Division I | GOBINDAPUR PWSS , SM/16784 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GOBINDAPUR Water Supply Scheme(TW -II) within Berhampore Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | 100/BD-I | 20/01/2025 | 180 | SUJIT KUMAR SAHA | 9.01 | 0 | 0 | 100
3076 | MURSHIDABAD | Berhampore Mechanical | KISMATTATLA AND ADJOINING MOUJAS PWSS , SM/16786 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Kismattatla ground water based water supply scheme under Block_ Bhagwangola-I Dist. - Murshidabad under MEDB, PHE Dte. | 3688/MEDB | 03/11/2023 | 92 | EASTERN INDIA SALES & SERVICE | 20.69 | 0 | 0 | 0
3077 | MURSHIDABAD | Berhampore Division I | KISMATTATLA AND ADJOINING MOUJAS PWSS , SM/16786 | New | Material Requisition To Resource Division | 61/BD-1/24 | 27/04/2023 | 0 | Resource Division | 7.05 | 0 | 0 | 0
3078 | MURSHIDABAD | Berhampore Mechanical | KISMATTATLA AND ADJOINING MOUJAS PWSS , SM/16786 | New | KISMATTALA PWSS | 345/WBSEDCL-JJM | 15/02/2024 | 0 | WBSEDCL | 3.54 | 0 | 0 | 0
3079 | MURSHIDABAD | Berhampore Division I | KISMATTATLA AND ADJOINING MOUJAS PWSS , SM/16786 | New | KISMATTATLA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 215/BD-I | 17/05/2023 | 990 | RUDRA NARAYAN GHOSH | 40.74 | 0 | 0 | 25
3080 | MURSHIDABAD | Berhampore Division I | KISMATTATLA AND ADJOINING MOUJAS PWSS , SM/16786 | New | KISMATTATLA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 150 cum) under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. [ 2ND Call for WBPHED/EE/BD-I/NIeT-30 of 2022 ¿ 2023 (sl no-02)] | 514/BD-I | 25/07/2023 | 930 | U TURN CONSTRUCTION | 172.1 | 32.42 | 18.84 | 15
3081 | MURSHIDABAD | Berhampore Division I | KISMATTATLA AND ADJOINING MOUJAS PWSS , SM/16786 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KISMATTATLA and Adjoining Mouzas PWSS (TW-II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-I Block under Berhampore Division-I, P.H.Engineering Dte. (01 Nos TW). | 773/BD-I | 22/05/2025 | 15 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 9.01 | 0 | 0 | 0
3082 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-III, Block- Berhampore, District- Murshidabad. , SM/16812 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Sujapur Zone-III village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3042/MEDB | 02/08/2023 | 92 | M/S. SUPER CONSTRUCTION | 6.32 | 0 | 0 | 0
3083 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-III, Block- Berhampore, District- Murshidabad. , SM/16812 | New | Mini Piped Water Supply Scheme for Char Sujapur Zone-III under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 168/BD-I | 16/05/2023 | 90 | CHAND ENTERPRISE | 24.78 | 0 | 0 | 0
3084 | MURSHIDABAD | Murshidabad Division | ADWAITA NAGAR PIPE WATER SUPPLY SCHEME. , SM/15943 | New | Material Requisition To Resource Division | 1230/MURD/23 | 04/05/2023 | 0 | Resource Division | 37.63 | 0 | 0 | 0
3085 | MURSHIDABAD | Berhampore Mechanical | ADWAITA NAGAR PIPE WATER SUPPLY SCHEME. , SM/15943 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under ADWAITA ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | 1898/MEDB | 16/06/2023 | 1021 | MENAKA ENTERPRISE | 33.56 | 0 | 0 | 8
3086 | MURSHIDABAD | Berhampore Mechanical | ADWAITA NAGAR PIPE WATER SUPPLY SCHEME. , SM/15943 | New | NEW CONNECTION AT ADAIYTANAGAR PH-II | 59/WBSEDCL-JJM | 06/05/2024 | 0 | WBSEDCL | 11.69 | 0 | 0 | 0
3087 | MURSHIDABAD | Murshidabad Division | ADWAITA NAGAR PIPE WATER SUPPLY SCHEME. , SM/15943 | New | Formal work order for the work of ADWAITA NAGAR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Jiban Mission of Samserganj Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE.Dte. | 621/MURD | 03/03/2023 | 758 | ARPAN PANDIT | 342.16 | 223.02 | 65.18 | 40
3088 | MURSHIDABAD | Murshidabad Division | ADWAITA NAGAR PIPE WATER SUPPLY SCHEME. , SM/15943 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.31 | 100 | 100
3089 | MURSHIDABAD | Murshidabad Division | ADWAITA NAGAR PIPE WATER SUPPLY SCHEME. , SM/15943 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ADWAITA NAGAR Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | 2631/MURD | 23/08/2023 | 495 | INDRAJIT MAZUMDAR | 18.44 | 4.11 | 20.94 | 100
3090 | MURSHIDABAD | Murshidabad Division | ADWAITA NAGAR PIPE WATER SUPPLY SCHEME. , SM/15943 | New | Sinking of 04 (Four) Nos 200 mm dia tube well by DTH method using UPVC Pipe at Adwaita Nagar CT T.W-I,II & Jadabpur Nimtala T.W-I,II Water Supply Scheme of Samserganj , Farakka under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 665/MURD | 19/03/2025 | 160 | KHOKAN BISWAS | 24.89 | 0 | 0 | 100
3091 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/16766 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-II of Mahalandi ground water based water supply scheme under Block- Kandi Dist. Murshidabad under MEDB, PHE Dte. | 3227/MEDB | 17/08/2023 | 92 | SURAKSHA | 11.92 | 10.54 | 88.43 | 60
3092 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/16766 | Augmentation | Construction of boundary wall at Front side of Head work site including gate of Mahalandi (Zone-II) water supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 336/KSD | 30/11/2021 | 45 | A.P. CONSTRUCTION | 4.92 | 4.91 | 100 | 1
3093 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/16766 | Augmentation | Construction of pathway and development of land at Head work Site of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 08 / KSD | 06/04/2022 | 45 | BIMALENDU BOSE | 4.84 | 4.83 | 100 | 1
3094 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/16766 | Augmentation | Supplying fitting and fixing of R.B.T Concertina fencing on wall top and construction of surface drain at Head work site of Mahalandi (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 12 / KSD | 06/04/2022 | 45 | DEBJYOTI MUKHERJEE | 4.73 | 4.71 | 100 | 1
3095 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/16766 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone-II Water Supply Scheme at HW Site under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3071/MURD | 17/11/2022 | 30 | A.M. ENTERPRISE | 10.6 | 9.95 | 100 | 100
3096 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/16766 | Augmentation | Material Requisition To Resource Division | 1043/MURD/6 | 17/04/2023 | 0 | Resource Division | 150.69 | 0 | 0 | 0
3097 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/16766 | Augmentation | Construction of Boundary Wall & Pump House with sanitary & plumbing work (3rd & 4th T/W Site) of Mahalandi (Zone-II) Water Supply Scheme of Kandi Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | 2075/MURD | 19/07/2024 | 60 | AHAMMED ENTERPRISE | 28.77 | 0 | 0 | 0
3098 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/16766 | Augmentation | Providing FHTC Connection to 818 nos. household , Construction of 300 Cum OHR, Laying of Distribution System, Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 200 Cum capacity of staging height 20 mtr. Repairing & Vertical Extention of Boundary Wall, Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works , Construction of Pump House with sanitary and Water Supply Arrangement & Boundary Wall, for Augmentation work of MAHALANDI ZONE-II Kandi Block under Murshidabad Division , PHE. Dte. | 2468/MURD | 09/08/2023 | 876 | M/S. BIMALENDU BOSE | 451.48 | 141.77 | 31.4 | 10
3099 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/16766 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well, 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone - I , Mahalandi Zone - II & Bhalkundi Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 1758/MURD | 06/07/2023 | 576 | R.K. DRILLING SERVICES | 23.58 | 0 | 0 | 70
3100 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahalandi Zone- II Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/16766 | Augmentation | Construction of boundary wall at Northern side of Head work site of Mahalandi (Zone-I) water supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad | 2976/MURD | 01/12/2020 | 45 | JYOTI TRADERS | 4.14 | 4.13 | 100 | 1
3101 | MURSHIDABAD | Berhampore Division I | BHAGWANGOLA AND ADJOING MOUJAS PWSS , SM/16780 | New | BHAGWANGOLA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 213/BD-I | 17/05/2023 | 90 | ARJIMA CONSTRUCTION | 39.48 | 0 | 0 | 0
3102 | MURSHIDABAD | Berhampore Division I | BHAGWANGOLA AND ADJOING MOUJAS PWSS , SM/16780 | New | BHAGWANGOLA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 450 cum) under Jal Jivan Mission of BHAGWANGOLA -I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | 974/BD-I | 18/10/2023 | 280 | GIRIDHARI SAHA | 359.56 | 0 | 0 | 0
3103 | MURSHIDABAD | Berhampore Division I | BHAGWANGOLA AND ADJOING MOUJAS PWSS , SM/16780 | New | Material Requisition To Resource Division | 61/BD-1/27 | 27/04/2023 | 0 | Resource Division | 13.43 | 0 | 0 | 0
3104 | MURSHIDABAD | Berhampore Mechanical | BHAGWANGOLA AND ADJOING MOUJAS PWSS , SM/16780 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BHAGWANGOLA , BLOCK - BHAGWANGOLA -I , DISTRICT - MURSHIDABAD. under MEDB, PHE Dte. | 1181/MEDB | 16/05/2025 | 92 | M/S K.P. PRAMANIK | 23.66 | 0 | 0 | 0
3105 | MURSHIDABAD | Berhampore Division I | BHAGWANGOLA AND ADJOING MOUJAS PWSS , SM/16780 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BHAGWANGOLA PWSS(TW-I&II) under Jal Jeevan Mission in Bhagwangola-I Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (2 Nos TW) | 617/BD-I | 23/04/2025 | 30 | JOY HIND TUBEWELLS | 17.99 | 0 | 0 | 0
3106 | MURSHIDABAD | Berhampore Division I | BHAGWANGOLA AND ADJOING MOUJAS PWSS , SM/16780 | New | Construction Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of BHAGWANGOLA PWSS under Jal Jeevan Mission within Bhagwangola-I Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 593/BD-I | 22/04/2025 | 180 | AMAN CONSTRUCTION | 15.2 | 0 | 0 | 82
3107 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramnapara ground water supply scheme , SM/07229 | Retrofitting | Additional Laying works at villages to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Ramnapara Ground water supply scheme (Bhagwangola-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | 2297/BD-I | 28/12/2021 | 15 | MS BAPPA ENTERPRISE | 6.01 | 5 | 100 | 0
3108 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramnapara ground water supply scheme , SM/07229 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Romnapara (Village code 314496) under Romnapara Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-09 of 2020 ¿ 2021,SL-11). | 75/BD-I | 19/01/2021 | 20 | MAA CONSTRUCTION | 12.9 | 16.68 | 129.34 | 0
3109 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -III PIPED WATER SUPPLY SCHEME. , SM/19125 | Augmentation | Material Requisition To Resource Division | 1180/MURD/19 | 29/04/2023 | 0 | Resource Division | 65.79 | 0 | 0 | 0
3110 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -III PIPED WATER SUPPLY SCHEME. , SM/19125 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II , Zone-III under ANDHUA ground water based water supply scheme under Block_ Farakka Dist. - Murshidabad under MEDB, PHE Dte. | 589/MEDB | 31/01/2024 | 90 | ARINDAM MAJUMDAR | 22.97 | 0 | 0 | 0
3111 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -III PIPED WATER SUPPLY SCHEME. , SM/19125 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ANDHUA ZONE -III Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Farakka Block under Murshidabad Division, P.H. Engineering Dte. | 114/MURD | 11/01/2024 | 21 | HARUN ALL RASHID & BROTHERS | 23.53 | 8.49 | 36.06 | 50
3112 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -III PIPED WATER SUPPLY SCHEME. , SM/19125 | Augmentation | Continuation work order for preparation of D.P.R. for Augmentation of Andhua Zone- II & Zone - III PWSS in Farakka Block in Jangipur Sub-Division under Murshidabad Division, PHE Dte. | 3720/MURD | 05/12/2023 | 30 | M/S SOBHA & CO. | 4.51 | 0 | 0 | 100
3113 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -III PIPED WATER SUPPLY SCHEME. , SM/19125 | Augmentation | Laying of Rising main , Distribution System, 2183 nos FHTC, construction of OHR (Capacity 350 cum), Repairing of OHR , Sinking of Tube Well , Repairing of pump house, Repairing of Boundary Wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Andhua Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | 138/MURD | 16/01/2024 | 365 | NAYLA CONSTRUCTION | 836.98 | 0 | 0 | 35
3114 | MURSHIDABAD | Berhampore Mechanical | CHACHANDA PIPED WATER SUPPLY SCHEME. , SM/18382 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV under CHACHANDA ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | 4301/MEDB | 29/12/2023 | 91 | ORIENTAL ENGINEERING CO. | 44.71 | 0 | 0 | 0
3115 | MURSHIDABAD | Murshidabad Division | CHACHANDA PIPED WATER SUPPLY SCHEME. , SM/18382 | New | CHACHANDA PWSS to accommodate FHTC under Jal Jeevan Mission of SAMSERGANJ Block, Sub Division - Jangipur of Murshidabad District under Murshidabad Division, PHE. Dte. | 2983/MURD | 21/09/2023 | 558 | M/S NIRAPADA BHATTACHARJEE | 567.03 | 5.14 | 0.91 | 15
3116 | MURSHIDABAD | Murshidabad Division | CHACHANDA PIPED WATER SUPPLY SCHEME. , SM/18382 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 7.09 | 100 | 100
3117 | MURSHIDABAD | Murshidabad Division | CHACHANDA PIPED WATER SUPPLY SCHEME. , SM/18382 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tubewell i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I C, Anup Nagar (CT) & Chachanda Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 1771/MURD | 06/07/2023 | 684 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 0 | 40
3118 | MURSHIDABAD | Murshidabad Division | CHACHANDA PIPED WATER SUPPLY SCHEME. , SM/18382 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHACHANDA Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | 2589/MURD | 21/08/2023 | 587 | MAMATA USHA ENTERPRISE | 27.67 | 0 | 0 | 100
3119 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME. , SM/18982 | Augmentation | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 2.39 | 100 | 90
3120 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SIKARPUR PIPED WATER SUPPLY SCHEME. , SM/18982 | Augmentation | Laying Distribution system, Rising Main Connection, FHTC(834 Nos) Construction of Boundary Wall , Pump House,Sinking of 300 x 200 mm dia Rig Bore Tubewell of Sikarpur PWSS in Farakka Block , Jangipur Sub-Division under Murshidabad Division ,PHE.Dte. | 60/MURD | 08/01/2024 | 724 | S.S. ENTERPRISE | 98.78 | 0 | 0 | 30
3121 | MURSHIDABAD | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS , SM/18517 | New | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | 698/BD-I | 11/08/2023 | 180 | JAHANGIR ALAM | 263.59 | 0 | 0 | 0
3122 | MURSHIDABAD | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS , SM/18517 | New | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , OHR (Capacity 750 cum) under Jal Jeevan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | 846/BD-I | 05/09/2023 | 310 | JAHANGIR ALAM | 466.95 | 0 | 0 | 0
3123 | MURSHIDABAD | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS , SM/18517 | New | Material Requisition To Resource Division | 201/BD-1/5 | 10/02/2024 | 0 | Resource Division | 86.32 | 0 | 0 | 0
3124 | MURSHIDABAD | Berhampore Mechanical | NASIPUR AND ADJOINIONG MOUJAS PWSS , SM/18517 | New | NEW CONNECTION NASIPUR PH-1 | 410/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 21.19 | 0 | 0 | 0
3125 | MURSHIDABAD | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS , SM/18517 | New | NASIPUR PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | 701/BD-I | 11/08/2023 | 900 | RAJ KUMAR MONDAL | 193.43 | 0 | 0 | 5
3126 | MURSHIDABAD | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS , SM/18517 | New | NASIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1254/BD-I | 22/12/2023 | 90 | MASOOM TRADERS | 56.23 | 3.94 | 7.02 | 25
3127 | MURSHIDABAD | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS , SM/18517 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NASIPUR and Adjoining Mouzas PWSS (TW- I, II, III & IV Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division-I, P.H.Engineering Dte. (04 Nos TW) | 774/BD-I | 22/05/2025 | 45 | SARKAR WATER SUPPLY AGENCY | 36.02 | 0 | 0 | 0
3128 | MURSHIDABAD | Berhampore Division I | NASIPUR AND ADJOINIONG MOUJAS PWSS , SM/18517 | New | Designing, making and errection of Display Board for Scheme information by using Logo and tag line of Jal Jeevan Mission at different PWSS work sites in the district of Murshidabad under Berhampore Division-I, PHE Dte. (Block :- Lalgola, Bhagwangola - I, Bhagwangola - II, Farakka, Berhampore, Murshidabad-Jiaganj, Nabagram & Hariharpara). | 1531/BD-I | 19/09/2024 | 30 | AJOY GHOSH | 21.44 | 21.01 | 100 | 70
3129 | MURSHIDABAD | Murshidabad Division | INDRANI AND ADJOINING MOUJAS PWSS , SM/18466 | New | Material Requisition To Resource Division | 1067/MURD/9 | 18/04/2023 | 0 | Resource Division | 69.6 | 0 | 0 | 0
3130 | MURSHIDABAD | Berhampore Mechanical | INDRANI AND ADJOINING MOUJAS PWSS , SM/18466 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-III, IV under INDRANI ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | 4068/MEDB | 04/12/2023 | 91 | DAS ENTERPRISE ( MANGO LANE) | 23.44 | 0 | 0 | 0
3131 | MURSHIDABAD | Berhampore Mechanical | INDRANI AND ADJOINING MOUJAS PWSS , SM/18466 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I , II under INDRANI ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | 4063/MEDB | 04/12/2023 | 91 | HARA PROSAD DAS | 23.47 | 0 | 0 | 0
3132 | MURSHIDABAD | Central Drilling | INDRANI AND ADJOINING MOUJAS PWSS , SM/18466 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 2203/CDD | 01/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 0 | 0 | 10
3133 | MURSHIDABAD | Murshidabad Division | INDRANI AND ADJOINING MOUJAS PWSS , SM/18466 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 0 | 0 | 80
3134 | MURSHIDABAD | Berhampore Mechanical | INDRANI AND ADJOINING MOUJAS PWSS , SM/18466 | New | NEW SERVICE CONNECTION AT INDRANI PH II, ID304233643 | 292/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 14.12 | 0 | 0 | 0
3135 | MURSHIDABAD | Berhampore Mechanical | INDRANI AND ADJOINING MOUJAS PWSS , SM/18466 | New | NEW SERVICE INDRANI PH1 ID304222223 | 227/WBSEDCL-JJM | 09/01/2024 | 0 | WBSEDCL | 4.41 | 0 | 0 | 0
3136 | MURSHIDABAD | Berhampore Mechanical | INDRANI AND ADJOINING MOUJAS PWSS , SM/18466 | New | NEW SERVICE CONNECTION AT INDRANI PH III, ID304233664 | 291/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 3.36 | 0 | 0 | 0
3137 | MURSHIDABAD | Murshidabad Division | INDRANI AND ADJOINING MOUJAS PWSS , SM/18466 | New | INDRANI (Part-A) & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Rising Main, FHTC work, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | 1988/MURD | 21/07/2023 | 865 | DHIRENDRANATH MONDAL | 569.67 | 91.31 | 16.03 | 10
3138 | MURSHIDABAD | Murshidabad Division | INDRANI AND ADJOINING MOUJAS PWSS , SM/18466 | New | Sinking of 01 (One) No of 250mm x 150 mm dia Repalcement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Faridpur and Indrani Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | 3411/MURD | 22/12/2022 | 984 | R.K. DRILLING SERVICES | 8.4 | 0 | 0 | 100
3139 | MURSHIDABAD | Murshidabad Division | INDRANI AND ADJOINING MOUJAS PWSS , SM/18466 | New | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 4.35 | 100 | 100
3140 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . , SM/18536 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-II Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 538/BD-I | 27/07/2023 | 10 | TECHVISION | 2.87 | 2.87 | 100 | 100
3141 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . , SM/18536 | Augmentation | Material Requisition To Resource Division | 201/BD-1/6 | 10/02/2024 | 0 | Resource Division | 48.66 | 0 | 0 | 0
3142 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . , SM/18536 | Augmentation | Laying of UPVC pipeline at damaged portion of distribution system and rising main pipe line (CI/DI/UPVC) of Ramnachandpur Zone-II water supply scheme under Berhampore Division-I,PHE Dte. For Augmentation of PWSS under Jal Jeevan Mission. | 140/BD-I | 01/02/2024 | 60 | SO-FINE AQUARIUM | 4.62 | 4.2 | 100 | 100
3143 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . , SM/18536 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Ramnachandpur Zone-II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte ( For 2 nos Tubewell) | 153/BD-I | 05/02/2024 | 245 | INDRAJIT MAZUMDER | 18 | 3.86 | 20.94 | 90
3144 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . , SM/18536 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 79 Cum/hr.) with allied work at Ramnachandrapur Zone-II Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | 915/BD-I | 07/06/2024 | 30 | J.S. CONSTRUCTION | 25.84 | 25.42 | 100 | 100
3145 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . , SM/18536 | Augmentation | Improvement of OHR (350 Cum) Extension of Boundary Wall & Service Road for Augmentation of Ramnachandpur Zone-II PWSS within Nawda block under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad. | 1127/BD-I | 11/07/2024 | 203 | TITLI ENTERPRISE | 15.58 | 4.01 | 20.94 | 90
3146 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-II pipe water supply scheme . , SM/18536 | Augmentation | Balance work i.c.w. Improvement of Existing AIRP of (Capacity 79 Cum/hr.) with allied works at Ramnachandpur Zone-II Water Supply Scheme under Jal Jeevan Mission within Nawda block under Berhampore Division-I, PHE Dte. In the district of Murshidabad. | 771/BD-I | 22/05/2025 | 30 | J.S. CONSTRUCTION | 17.81 | 0 | 0 | 100
3147 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. , SM/18702 | Augmentation | Material Requisition To Resource Division | 1167/MURD/24 | 28/04/2023 | 0 | Resource Division | 17.33 | 0 | 0 | 0
3148 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. , SM/18702 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 2.17 | 100 | 80
3149 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. , SM/18702 | Augmentation | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Block Bhagawangola-I & Lalgola of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Habaspur Water Supply Scheme, Bhandara Water Supply Scheme, Kantanagar Water Supply Scheme, Lalgola Water Supply Scheme. (Annexure-II) | 1928/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 8.78 | 2.23 | 100 | 100
3150 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. , SM/18702 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 200 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Kantanagar PWSS in Bhagwangola-I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 3321/MURD | 22/10/2023 | 557 | M/S GUHA AND ROY | 625.7 | 26.72 | 4.27 | 40
3151 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. , SM/18702 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 2.57 | 52.28 | 100
3152 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KANTANAGAR , BLOCK - BHAGAONGOLA-I , DISTRICT - MURSHIDABAD. , SM/18702 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Lalbagh Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | 2638/MURD | 23/09/2024 | 251 | ARJU CONSTRUCTION | 6.14 | 0 | 0 | 40
3153 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brindabanpur Chak ( 314703 ) of Shibnagar Laskarpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District , SM/07914 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Brindabanpur Chak (Village code 314703) under Shibnagar Laskarpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723328 in the District of Murshidabad. | 83./MURD | 08/01/2021 | 60 | ULTRA CONSTRUCTION. | 43.61 | 0 | 0 | 0
3154 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Parsalika, Pachhipara & Andulia (315953, 315966 & 315967) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of M , SM/07924 | Retrofitting | Hiring of one no car use of the JSD PHE DTE. Note sheet approved date 07/01/2022. | 264-MSD/22-23 | 18/08/2022 | 0 | MADAN MOHAN SASMAL | 0.59 | 0 | 0 | 0
3155 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Parsalika, Pachhipara & Andulia (315953, 315966 & 315967) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of M , SM/07924 | Retrofitting | Work Order for hiring of one no car use of the Superintending Engineer Murshidabad Circle PHE DTE. NIB 02/MC/PHE/20-21. W/O - 289-MC dated 01.04.2021 | 263-MSD/22-23 | 18/08/2022 | 0 | SOUMYADIP MISRA | 1.17 | 0 | 0 | 0
3156 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Parsalika, Pachhipara & Andulia (315953, 315966 & 315967) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of M , SM/07924 | Retrofitting | Continuatioin order for hiring of one no car use of the Executive Engineer Murshidabad Div PHE DTE. Vechle no 57-D - 9090. W/O - 223-HQ dated 26.05.2022 | 262-MSD/22-23 | 18/08/2022 | 0 | DULAL CHOWDHURY | 0.79 | 0 | 0 | 0
3157 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Parsalika, Pachhipara & Andulia (315953, 315966 & 315967) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of M , SM/07924 | Retrofitting | Formal Work Order for Construction of 300 Cum capacity 20.00 mtr staging hight RCC elevated Over Head Reservoir on pile foundation (Ref:- DRG. NO. PC-I/OHR/7/2012 & D D-II/OHR/957/III/JAN 2020) including delivery, inlet and overflow pipe connection etc all complete of BAHARA Water Supply Scheme of Kandi Sub-Division under Murshidabad Division , P.H.E. Dte. | 3053/MURD | 08/12/2020 | 270 | ROY ENTERPRISE | 78.02 | 16.68 | 100 | 100
3158 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Parsalika, Pachhipara & Andulia (315953, 315966 & 315967) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of M , SM/07924 | Retrofitting | Construction of boundary wall at Front side of Head work site including gate & R.B.T concertina fencing on wall top of Bahara Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 378/KSD | 19/01/2022 | 45 | ROY ENTERPRISE | 4.29 | 4.28 | 100 | 100
3159 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Parsalika, Pachhipara & Andulia (315953, 315966 & 315967) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of M , SM/07924 | Retrofitting | Development of land at Head Work Site of Bahara Water Supply Scheme under Kandi Sub-Division, P.H.Engg. Dte. in the District of Murshidabad. | 375/KSD | 19/01/2022 | 30 | ROY ENTERPRISE | 4.53 | 4.52 | 100 | 100
3160 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Parsalika, Pachhipara & Andulia (315953, 315966 & 315967) of Panchhipara under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of M , SM/07924 | Retrofitting | Laying of rising main of Pachhipara W/S scheme and protection of Head Work site at Kamalakantapur under Murshidabad Division, P.H.Engineering Dte. in the District of Murshidabad. | 2310/MURD | 01/08/2023 | 632 | APU CONSTRUCTION | 10.42 | 10.14 | 97.47 | 97
3161 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Durgapur (313864) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) , SM/07512 | Retrofitting | Retrofitting providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of DURGAPUR (Village Code -313864) under HASIMPUR Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block in the Dist of MSD under Murshidabad Division P.H.E Dte. Scheme ID 0001723174 |  | 25/08/2021 | 0 | HOQUEDAR ALI | 33.41 | 0 | 0 | 0
3162 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Durgapur (313864) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) , SM/07512 | Retrofitting | Retrofitting providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of DURGAPUR (Village Code -313864) under HASIMPUR Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block in the Dist of MSD under Murshidabad Division P.H.E Dte. Scheme ID 0001723174 Tender No 858/20-21/EE | 49- MSD / 21-22 | 13/09/2021 | 0 | HOQUEDAR ALI | 33.41 | 0 | 0 | 0
3163 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Durgapur (313864) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District ( PART-II ) , SM/07512 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Durgapur ( Village Code -313864) under Hasimpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D. 0001723174). | 633/MURD | 18/02/2021 | 60 | HOQUEDAR ALI | 43.59 | 10.17 | 100 | 0
3164 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis , SM/07513 | Retrofitting | Fault defection of Repairing or replacing the damaged material Pannel board submerssible pump existing chlorinetaror of other direc existing chlonator and other direc Mahadebnagar Z-II W/S Scheme under JSD PHE DTE. TNO- 41 of 21-22 by AE/JSD | 104-MSD/2021-22 | 20/09/2021 | 0 | ARYA CONSTRUCTION | 3.81 | 0 | 0 | 0
3165 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis , SM/07513 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-III ) TNO- 764/20-21/EE |  | 12/04/2021 | 0 | SOUMYA KANTI SINHA | 17.54 | 0 | 0 | 0
3166 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis , SM/07513 | Retrofitting | Safe Drinking Water Supply (Modified ATU) arrangement for Char Sarandajpur Primary School under ISD under Murshidabad Div PHE DTE. Tender no - 74 of 21-22 by AE / ISD | 92-MSD/2021-22 | 20/09/2021 | 0 | SARTHAK SK. | 4.76 | 0 | 0 | 0
3167 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis , SM/07513 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village SHIBARAMBATI (Village Code 315980) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. | 3034/MURD | 07/12/2020 | 45 | SOUMYA KANTI SINHA | 18.57 | 0 | 0 | 1
3168 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis , SM/07513 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00 x 4'00") which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Nowda G.P, Raypur G.P, Madhupur G.P, Sarbangapur G.P, Choa G.P, Hariharpara G.P, Mahula G.P, Rampur-I & II G.P Rangamati Chandpara G.P. Satui Chowrigachha G.P, Shaktipur G.P. & Chhaighari G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | 142/BSD | 21/06/2021 | 30 | IMAGIN | 3.77 | 7.54 | 200 | 0
3169 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis , SM/07513 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00"x 4"00") which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Radharghat I & II G.P. Ramnagar Bachhara G.P, Sompara-I & II G.P, Doulatabad G.P, Mirzapur-I & II G.P, Kumarpur Sujapur G.P, Debkunda G.P, Madda G.P, Sahajadpur G.P & Niyallishpara G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | 233/BSD | 14/07/2021 | 30 | S.S.INFRASTRUCTURE | 3.77 | 2.85 | 200 | 0
3170 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati & Janardanpur (315980 & 315981) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad Dis , SM/07513 | Retrofitting | Balance Retrofitting Work of Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under at Janardanpur & adjoining mouzas (JL NO-147) ( Village Code -315981) from the exiting distribution system of Panchthupi Water Supply Scheme (Ground Water Based) in Burwan Block under Kandi Sub Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 534/MURD | 04/02/2021 | 60 | J.S. CONSTRUCTION | 44.75 | 88.73 | 200 | 1
3171 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Sekhalipara (314580) of Katakobra under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) , SM/07517 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission of 1005 nos household under command area of village of Sekhalipara ( Village Code -314580) under Katakobra Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0005185646) | 1238/MURD | 11/05/2022 | 60 | BRISTI CONSTRUCTION | 52.34 | 50.08 | 50 | 1
3172 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagharpur Ramna (314665) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (PART-V) , SM/07671 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of BAGHARPUR RAMNA (Village Code -314665) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. . Tender no - 66 of 20-21 by SE MC. | 254-MSD/22-23 | 12/08/2022 | 0 | M/S NIRAPADA BHATTACHARJEE | 10.04 | 0 | 0 | 0
3173 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Sarpakia (Code-314194) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-A) , SM/07689 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarpakhia (Village code 314194) under Rajarampur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | 1168/BD-I | 15/07/2021 | 30 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 21.65 | 19.52 | 100 | 1
3174 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Sarpakia (Code-314194) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-A) , SM/07689 | Retrofitting | Additional Laying works at village Sarpakhia( Village code-314194) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Rajarampur Ground water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 243/BD-I | 03/03/2022 | 10 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 4.9 | 3.81 | 100 | 1
3175 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Sarpakia (Code-314194) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-A) , SM/07689 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Sarpakia (Code-314194) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1529/BD-I | 19/09/2024 | 30 | M/S. THE LOTUS ENTERPRISE | 5.12 | 0 | 0 | 0
3176 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Makimnagar ground water supply scheme , SM/06981 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Simulia (Village code 314155) under Mokimnagar Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 970/BD-I | 17/12/2020 | 60 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 6.79 | 5.24 | 100 | 1
3177 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Makimnagar ground water supply scheme , SM/06981 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mokimnagar (Village code 314172) under Mokimnagar Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 969/BD-I | 17/12/2020 | 90 | MS RUBIET HOSSAIN | 40.85 | 23.23 | 56.85 | 1
3178 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Makimnagar ground water supply scheme , SM/06981 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mridapur(Village code 314157) under Mokimnagar Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 971/BD-I | 17/12/2020 | 90 | MS RUBIET HOSSAIN | 33.94 | 28.8 | 84.86 | 1
3179 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Makimnagar ground water supply scheme , SM/06981 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Makimnagar ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1198/BD-I | 26/07/2024 | 60 | BURIMAA CONSTRUCTION | 12.74 | 0 | 0 | 0
3180 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Kosbagoas (VillageCode-314795) under command area of Kosbagoas ground water supply scheme (Part-A) , SM/06983 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kasbagoas (Village code 314795) under Kasbagoas Ground Water based Water Supply Scheme for Raninagar-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 338/BD-I | 24/02/2021 | 120 | DOBAY CONSTRUCTION | 81.22 | 95.58 | 117.69 | 0
3181 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Kosbagoas (VillageCode-314795) under command area of Kosbagoas ground water supply scheme (Part-A) , SM/06983 | Retrofitting | Additional Laying works at village Kasbagoas (Village code-314795) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Kasbagoas Ground water based Water supply scheme (Raninagar-I,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | 2312/BD-I | 29/12/2021 | 45 | BENOY DOBEY | 14.34 | 0 | 0 | 0
3182 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Godhanpara ( 314581) & Babaltali ( 314583 ) of Godhanpara under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshida , SM/08100 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Godhanpara PWSS Scheme, Block - Raninagar-II) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | 2744/MURD | 03/09/2021 | 60 | RADIANT | 11.27 | 0 | 0 | 0
3183 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Godhanpara ( 314581) & Babaltali ( 314583 ) of Godhanpara under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshida , SM/08100 | Retrofitting | Providing Functional Household Tap Connections (FHTC) (1676 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Babaltali ( Village Code -314583) under Godhanpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. | 3423/MURD | 02/11/2023 | 60 | SUMAN CHOWDHURY | 55.3 | 14.03 | 25.37 | 40
3184 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Godhanpara ( 314581) & Babaltali ( 314583 ) of Godhanpara under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshida , SM/08100 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babaltali ( Village Code -314583) (Shaikh para & Babultali ) & adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) | 2386/MURD | 09/08/2021 | 60 | MITRA CONSTRUCTION | 98.09 | 0 | 0 | 1
3185 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Naopukuria (Zone-K) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block , SM/07702 | Retrofitting | Retrofitting Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of villages of NAOAPUKURIA (village code 315617), under NAOAPUKURIA (Zone-K) Water Supply Scheme of Beldanga-I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | 104/BD-I | 04/05/2023 | 120 | RAJ KUMAR MONDAL | 179.66 | 0 | 0 | 0
3186 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Kasba Bahadurpur (Code-314488) In The Command Area Of Kasba Bahadurpur Ground Water Supply Scheme (Part-B) , SM/07725 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kasba Bahadurpur (Village code 314488) , under Kasba Bahadurpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 167/BD-I | 03/02/2021 | 728 | M/S SINHA & SONS | 95.89 | 116.96 | 157.11 | 1
3187 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Kasba Bahadurpur (Code-314488) In The Command Area Of Kasba Bahadurpur Ground Water Supply Scheme (Part-B) , SM/07725 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under KASBA BAHADURPUR ground Water based Water Supply Scheme of Bhagawangola-I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | 977/BD-I | 18/10/2023 | 90 | NAMDAR ALI | 15.83 | 0 | 0 | 0
3188 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Kasba Bahadurpur (Code-314488) In The Command Area Of Kasba Bahadurpur Ground Water Supply Scheme (Part-B) , SM/07725 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at The Village Of Kasba Bahadurpur (Code-314488) In The Command Area Of Kasba Bahadurpur Ground Water Supply Scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1441/BD-I | 04/09/2024 | 362 | A.P CONSTRUCTION | 27.91 | 0 | 0 | 70
3189 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect , SM/08108 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kharsadanga, Putijol, Sundhipur & Rajdharpara (Village code 315377, 315395, 315371 & 315375) respectively under Purba Narayanpur (Zone-B) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. | 242/BD-I | 10/02/2021 | 180 | MADE & TRADE CO. | 306.14 | 323.76 | 105.75 | 1
3190 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect , SM/08108 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naoda Panur, Tarakpur, Kaya & Purba Narayanpur (Village code 315378, 315380, 315379 & 315376) under Purba narayanpur (Zone-B) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. | 249/BD-I | 11/02/2021 | 180 | J.D.J ENTERPRISE | 393.6 | 268.7 | 68.27 | 1
3191 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect , SM/08108 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 56.47 | 1
3192 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect , SM/08108 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Paschim Gopinathpur (Village code 315393) under Purba Narayanpur (Zone-B) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 296/BD-I | 19/02/2021 | 30 | M/S BIMALENDU BOSE | 9.59 | 9.18 | 95.78 | 1
3193 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect , SM/08108 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kariagachhi (Village code 315394) under Purba Narayanpur (Zone-B) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 297/BD-I | 19/02/2021 | 30 | A.P CONSTRUCTION | 7.15 | 6.69 | 93.68 | 1
3194 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect , SM/08108 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Uday Nagar (village code 315396) , Gar Baharampur ( village code 315388 ) and Pakuria ( village code 315381 ) under PURBONARAYANPUR ( Zone - B ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | 1836/BD-I | 05/10/2021 | 70 | HOQUEDAR ALI | 58.64 | 0 | 0 | 0
3195 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect , SM/08108 | Retrofitting | Additional Laying works at village Kharsadanga, Putijol,Sundhipur and Rajdharpara (Village code-315377,315395,315371 and 315375) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Purba Narayanpur (Zone-B)Surface water based Water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | 2302/BD-I | 28/12/2021 | 90 | SOUNAK ENTERPRISE | 73.56 | 73.26 | 99.59 | 1
3196 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect , SM/08108 | Retrofitting | Supply of safe drinking water by laying of pipe line at Tikiapara primary school ,Madapur Adibasi Junior High School and Nagrajal High School with arrangement of safe drinking water from surface water based water supply scheme ,Central sector Part-II (Hatinagar and Purbonarayanpur as per zone) at Tikiapara P.S and Madapur P.S. in connection with JJM (Jal Jeevan Mission) under Berhampore Division-I ,P.H.E Dte. | 92/BD-I | 03/05/2023 | 30 | MAA CONSTRUCTION | 2.82 | 2.81 | 100 | 100
3197 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Purbonarayanpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sect , SM/08108 | Retrofitting | Allied work for the work of Improvement of Distribution piped water line for providing drinking water facility to the local habitation within command area of Purbo Narayanpur Water supply scheme (Central Sector, Part-II) under Berhampore Division-I,PHE Dte | 1472/BD-I | 06/09/2024 | 180 | SARAJIT KUMAR MAJUMDAR | 21.24 | 0 | 0 | 50
3198 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) , SM/07276 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SAHAJADPUR- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- NISCHINTAPUR , CODE- 315328 , 600 /2020-21/EE | 489/W | 17/03/2021 | 0 | SAMBHUNATH ROY | 29.21 | 0 | 0 | 0
3199 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) , SM/07276 | Retrofitting | Planning, design, investigation, construction, erection, installation, completion, testing and commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & iron present in ground water in diff. connection to acceptable limit as recommended by CPHEEO manual on basis of departmental process drawing (Modified Sujapur Sadipur Model) incld. 3 months Trail Run & 9 months O&M of diff. blocks in the district of Murshidabad, PHE Dte., (JAGAIPUR W/S SCHEME) | 478/W | 12/03/2021 | 0 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 27.52 | 0 | 0 | 0
3200 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) , SM/07276 | Retrofitting | Material Requisition To Resource Division | 540/6/MURD | 25/02/2022 | 0 | Resource Division | 7.16 | 0 | 0 | 0
3201 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) , SM/07276 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
3202 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) , SM/07276 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
3203 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ballalpur (313811) of Ballalpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (Part-I) , SM/07276 | Retrofitting | Providing Functional Household Tap Connections (FHTC) 1305 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Ballalpur ( Village Code -313811) under Ballalpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. | 1052/MURD | 25/04/2022 | 45 | TARIKUL SK | 60.99 | 54.93 | 49.97 | 10
3204 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri , SM/07278 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SHIBPUR G.P. under Murshidabad Division, P.H.E.Dte. | 249/LSD | 18/08/2021 | 30 | IMAGIN COMMUNICATION | 4.18 | 0 | 0 | 0
3205 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri , SM/07278 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -JITPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE - PAR RAGHUNATHPUR, CODE- 314677 , TNO- 80/20-21/SEMC | 504/W | 22/03/2021 | 0 | UMWELT ENGINEER PVT LTD | 36.66 | 0 | 0 | 0
3206 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri , SM/07278 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SAHAJADPUR- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- NISCHINTAPUR , CODE- 315328 , 600 /2020-21/EE | 489/W | 17/03/2021 | 0 | SAMBHUNATH ROY | 29.21 | 0 | 0 | 0
3207 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri , SM/07278 | Retrofitting | Operation & Maintenance of distribution system and allied works of Siddhikhali (Zone-III)Surface W/S Scheme Raghunathganj-I Block from 01.05.2019 to 29.02.2020 | 489/W | 17/03/2021 | 0 | SUDIPA SINGHA ROY | 4.99 | 0 | 0 | 0
3208 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri , SM/07278 | Retrofitting | CONT WORK OF OPERATION & GUARDING OF PUMPING MACHINERY FOR MAHESAIL W/S SCHEME PH-I , TNO- 894/19-20/EE | 489/W | 17/03/2021 | 0 | RELIABLE ENTERPRISE | 1.41 | 0 | 0 | 0
3209 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri , SM/07278 | Retrofitting | Additional extension of UPVC pipeline at Sankuria and Madhunia (Adibashipara) under the Improvement work of Amarkundu Water Supply Scheme under Lalbagh Sub-Division, P.H.E. Dte.in the District Murshidabad. | 361/LSD | 17/11/2021 | 45 | SARAJIT KUMAR MAJUMDER | 4.43 | 4.42 | 100 | 0
3210 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri , SM/07278 | Retrofitting | Laying of different dia U.P.V.C Pipeline for Distribution Network (Remaining Portion) and construction of RCC Stand Post including platform at Sankuria Village under Improvement work of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. | 413/LSD | 27/12/2021 | 30 | SARAJIT KUMAR MAJUMDER | 4.88 | 4.85 | 100 | 0
3211 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri , SM/07278 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (JalJeevan Mission ) "from existing Distribution system within the Command area of village AMARKUNDU (Village Code 315017) under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block in the District of Murshidabad . | 2570/MURD | 01/10/2020 | 45 | MAJUMDER CONSTRUCTION | 38.26 | 34.35 | 89.76 | 1
3212 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amarkunda, Kanakpara (315017 & 315018) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murshidabad Distri , SM/07278 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) of 200 left out in connection with Jal Jeevan Mission and Jal Swapna under command area of village Amarkundu (Village code 315017) and under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nabagram Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 803/MURD | 24/03/2022 | 20 | S.K. CONSTRUCTION (TABLU) | 11.79 | 0 | 0 | 0
3213 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Basantapur Village (Code-314446),Lalitakuri (Code-314449) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-C) , SM/07731 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Basantapur(Village code 314446),Lalitakuri(Village code 314449) under Sundarpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | 173/BD-I | 03/02/2021 | 30 | DECON INDIA | 76.45 | 32.65 | 42.7 | 1
3214 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Basantapur Village (Code-314446),Lalitakuri (Code-314449) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-C) , SM/07731 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Basantapur Village (Code-314446),Lalitakuri (Code-314449) In The Command Area Of Sundarpur Ground Water Supply Scheme (Part-C)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1530/BD-I | 19/09/2024 | 60 | HAFIZUL SEIKH | 17.26 | 0 | 0 | 0
3215 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Chengta (VillageCode-314463), Gobra (Village code- 314470)& Ramnagobra (Village Code-314461) under command area o , SM/07235 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gobra (Village code 314470) under Gobra Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 65/BD-I | 18/01/2021 | 30 | DECON INDIA | 44.55 | 43.75 | 100 | 100
3216 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Chengta (VillageCode-314463), Gobra (Village code- 314470)& Ramnagobra (Village Code-314461) under command area o , SM/07235 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagobra (Village code 314461) under Gobra Ground Water based Water Supply Scheme for Bhagawangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 920/BD-I | 10/12/2020 | 60 | SHIBAM ENTERPRISE THAKURPARA VILL BHAKURI CHALTIA | 11.5 | 18.33 | 159.37 | 0
3217 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Chengta (VillageCode-314463), Gobra (Village code- 314470)& Ramnagobra (Village Code-314461) under command area o , SM/07235 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION for Village of Chengta (VillageCode-314463), Gobra (Village code- 314470)& Ramnagobra (Village Code-314461) under command area of Gobra ground water supply scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1663/BD-I | 25/10/2024 | 30 | LAKSHMI IRON | 16.77 | 0 | 0 | 0
3218 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Chengta (VillageCode-314463), Gobra (Village code- 314470)& Ramnagobra (Village Code-314461) under command area o , SM/07235 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chengta (Village code 314463) under Gobra Ground Water based Water Supply Scheme for Bhagawangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 919/BD-I | 10/12/2020 | 60 | PRATICHI ENTERPRISE | 10.11 | 15.22 | 180 | 100
3219 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Kulberia Village (Code-315685) Under Command Area Of Andulberia Ground Water Supply Scheme (Part-A) , SM/07696 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kulberia (Village code 315685) under Andulberia Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | 185/BD-I | 04/02/2021 | 20 | HANNAN BUILDERS PVT. LTD. | 43.67 | 31.27 | 71.61 | 0
3220 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Panchnanpur, Baniakhali (314655 & 314660) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Dist , SM/07288 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "Jal Swapna (Jal Jeevan Mission ) "from existing Distribution system within the Command area of village BANIAKHALI (Village Code 314660) under Baniakhali Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad . | 2578/MURD | 01/10/2020 | 45 | M/S NIRAPADA BHATTACHARJEE | 35.6 | 11.13 | 31.26 | 1
3221 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Panchnanpur, Baniakhali (314655 & 314660) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Dist , SM/07288 | Retrofitting | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0 | 0
3222 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Panchnanpur, Baniakhali (314655 & 314660) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Dist , SM/07288 | Retrofitting | ADITIONAL WORK OF FHTC OF BANIAKHALI (314660) WSS, TNO- 641/21-22/EE, WO- 2181/MURD | 130-MSD/22-23 | 11/05/2022 | 0 | M/S NIRAPADA BHATTACHARJEE | 5.91 | 0 | 0 | 0
3223 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Panchnanpur, Baniakhali (314655 & 314660) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Dist , SM/07288 | Retrofitting | Additional works for Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Baniakhali( Village Code -314660) under Baniakhali Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723470) | 2181/MURD | 28/07/2021 | 60 | M/S NIRAPADA BHATTACHARJEE | 12.08 | 0 | 0 | 0
3224 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Manik Nagar (314694) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-II) , SM/07291 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -JURANPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- PIROJPUR , CODE-314723, TNO- 667/2020-21/EE | 512/W | 30/03/2021 | 0 | GOUTAM CHAKRABORTY | 10.4 | 0 | 0 | 0
3225 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Manik Nagar (314694) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-II) , SM/07291 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BARABIL RAGHUNAR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 87 /2020-21/SE-MC | 512/W | 30/03/2021 | 0 | MITRA CONSTRUCTION | 55.47 | 0 | 0 | 0
3226 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Manik Nagar (314694) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-II) , SM/07291 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --AMARKUNDU-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- RAINDA , CODE- 315025, TNO- 684/2020-21/EE | 512/W | 30/03/2021 | 0 | SAMAR MUKHERJEE | 21.62 | 0 | 0 | 0
3227 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Manik Nagar (314694) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-II) , SM/07291 | Retrofitting | Providing Functional Household Tap Connections ( 665 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Manik Nagar (Village Code -314694) under Domkol Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. | 3458/MURD | 06/11/2023 | 30 | MOLLA ENTERPRISE (REHENA BIBI) | 18.71 | 0 | 0 | 0
3228 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sambhu Nagar, Ramna Etbarnagar Basantapur (314628) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad , SM/07295 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ramna Etbarnagar Basantapur (Village code 314691) under Domkal Ground Water Based water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0005184127 in the District of Murshidabad. | 3615/MURD | 22/11/2021 | 100 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 53.5 | 0 | 0 | 0
3229 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sambhu Nagar, Ramna Etbarnagar Basantapur (314628) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad , SM/07295 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BHANDARA--Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- KOLAN RADHAKANTAPUR , CODE-314523, TNO- 50/2020-21/SE-MC | 512/W | 30/03/2021 | 0 | M/S GUNGUN CONSTRUCTION | 33.58 | 0 | 0 | 0
3230 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sambhu Nagar, Ramna Etbarnagar Basantapur (314628) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad , SM/07295 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --BHALKUNDI Z-II-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE-BHALKUNDI , CODE- 315091, TNO- 43/2020-21/SEMC | 512/W | 30/03/2021 | 0 | M/S BHUBAN DAS | 28.84 | 0 | 0 | 0
3231 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sambhu Nagar, Ramna Etbarnagar Basantapur (314628) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad , SM/07295 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village RAMNA ETBARNAGAR (Village Code 314691) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 106 of 21-22 by EE MURD | 410-MSD/21-22 | 22/03/2022 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 22.28 | 0 | 0 | 0
3232 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chhakka Nagar, Kochgiria (314478 & 314481) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Mur , SM/07684 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village CHHAKA NAGAR (Village code 314478) under BHANDARA Ground water based Water Supply Scheme for Arsenic Affected Area of Bhagwangola - I & II Block, under Murshidabad Division, PHE Dte. Tender no 492 of 20-21 by EE MSD | 50- MSD / 21-22 | 14/09/2021 | 0 | PRANAB KUMAR GHOSH | 21.76 | 0 | 0 | 0
3233 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chhakka Nagar, Kochgiria (314478 & 314481) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Mur , SM/07684 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village CHHAKA NAGAR (Village code 314478) under BHANDARA Ground water based Water Supply Scheme for Arsenic Affected Area of Bhagwangola - I & II Block, under Murshidabad Division, PHE Dte. Tender no 492 of 20-21 by EE MSD |  | 18/08/2021 | 0 | PRANAB KUMAR GHOSH | 21.76 | 0 | 0 | 0
3234 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Chhakka Nagar, Kochgiria (314478 & 314481) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I & II Block of Mur , SM/07684 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kochgiria(Village code 314481) under Bhandara Ground Based Water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl No-03) | 3130/MURD | 10/12/2020 | 180 | M/S OBAIDUR RAHAMAN | 54.51 | 21.97 | 40.31 | 70
3235 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Raniara Masadda (VILL CODE-315905) of Burwan under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block of Murshidabad Distric (PART-I) tNO- 791/20-21/EE | 41-MSD / 21-22 | 24/08/2021 | 0 | DEBASISH SARKAR | 9.94 | 0 | 0 | 0
3236 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | Laying of parallel UPVC pipeline from Masadda Shib Mandir to Masadda Durga Mandir for FHTC work of Raniara Masadda village (Village Code- 315905) of Burwan Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. | 09 / KSD | 06/04/2022 | 30 | S.K. ENTERPRISE (PROP:SHAMIM ISLAM) | 4.82 | 4.56 | 100 | 1
3237 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dhanghara (315950) of Burwan under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block of Murshidabad Distric. Tender no - 850 of 20-21 by EE MURD | 343-MSD/21-22 | 05/03/2022 | 0 | DAS CONSTRACTION (MUNNA DAS) | 5.48 | 0 | 0 | 0
3238 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | Hiring of 1 (One) no Diesel Scorpio car for fJangipur Sub Div. under MSD PHE DTE. Period 01.04.2022 to 10.06.2022 | 200-MSD/2022-23 | 06/07/2022 | 0 | MADAN MOHAN SASMAL | 0.41 | 0 | 0 | 0
3239 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dhanghara (315950) of Burwan under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block of Murshidabad Distric (PART-I) |  | 17/02/2022 | 0 | DAS CONSTRACTION | 5.48 | 0 | 0 | 0
3240 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | Laying of parallel UPVC pipeline from Masadda Bus Stand to Masadda Shib Mandir for FHTC work of Raniara Masadda village (Village Code- 315905) of Burwan Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. | 194-MSD/22-23 | 30/06/2022 | 0 | MAA CONSTRUCTION (NAJMUL HAQUE) | 4.58 | 0 | 0 | 0
3241 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | 216/KSD | 11/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.34 | 0 | 0 | 0
3242 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at BURWAN-I G.P. under Murshidabad Division, P.H.E.Dte. | 231/KSD | 27/08/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 4.17 | 0 | 0 | 0
3243 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at BURWAN-II G.P. under Murshidabad Division, P.H.E.Dte. | 232/KSD | 27/08/2021 | 60 | IMAGIN COMMUNICATION | 4.17 | 0 | 0 | 0
3244 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | Holding Awarness Programme / Campaigning programms at Burwan-I & II G.P, Sahora G.P, Panchthupi G.P and Sabalpur G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (Total nos of Programme = 20 nos) (Part-C). | 251/KSD | 31/08/2021 | 30 | IMAGIN COMMUNICATION | 3.99 | 0 | 0 | 0
3245 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SAHORA G.P. under Murshidabad Division, P.H.E.Dte. | 243/KSD | 27/08/2021 | 60 | IMAGIN | 4.17 | 0 | 0 | 0
3246 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Rameswarpur habitation under Rameswarpur Village Code-315954(JL NO-120) Burwan Water Supply Scheme (Ground Water Based) under Burwan Block in the District of Murshidabad. | 2391/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 11.77 | 0.53 | 100 | 1
3247 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
3248 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
3249 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with JAL SWAPNA (JAL JEEVAN MISSION) from existing Distribution system within the Command area of village RANIARA MASADDA (Village Code 315905) under Burwan Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. | 3219/MURD | 18/12/2020 | 60 | DEBASISH SARKAR | 12.49 | 2.49 | 100 | 0
3250 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gopipur, Barwan, Raniara Masadda, Babarpur, Dhanghara, Gouri Nagar, Rameswarpur (315874, 315890, 315905, 315907, 315950, 315951, 315954) of Burwan under Ground Wat , SM/07666 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Rameswarpur habitation under Rameswarpur Village Code-315954(JL NO-120) Burwan Water Supply Scheme (Ground Water Based) under Burwan Block in the District of Murshidabad. | 2391/MURD | 18/09/2020 | 45 | CLIFFORD FACILITY SERVICES PVT. LTD. | 11.77 | 8.47 | 71.89 | 1
3251 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Hamidhati Pilkhandi & Purbbagram (315713 & 315718 ) of Salar under Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur - II Block of Murs , SM/07509 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4'00'' x 4'00'') which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC at Balia G.P, Joypur G.P, Alugram G.P, bharatpur G.P, Sijgram G.P, Salar G.P, Simulia G.P, Kagram G.P, Talibpur G.P & Tenya Baidyapur G.P. in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division P.H.E. Dte. | 177/KSD | 28/05/2021 | 30 | IMAGIN COMMUNICATION | 2.9 | 2.9 | 100 | 0
3252 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bhikan (Code-314211), Ganespur (Code-314215) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(P , SM/07715 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jot Bhikan (Village code 314211) under Bajipur Madhupur Ground Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 992/BD-I | 17/12/2020 | 90 | SANJAY BISWAS | 26.93 | 10.91 | 40.5 | 1
3253 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bhikan (Code-314211), Ganespur (Code-314215) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(P , SM/07715 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ganespur (Village code 314215) under Bajipur Madhupur Ground Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 993/BD-I | 17/12/2020 | 90 | M/S. NIRAPADA BHATTACHARJEE | 29.45 | 37.64 | 140.33 | 1
3254 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Bhikan (Code-314211), Ganespur (Code-314215) In The Command Area Of Bajupur Madhapur Ground Water Supply Scheme(P , SM/07715 | Retrofitting | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ganespur (Village Code-314215) under Bajipur Madhupur Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | 913/BD-I | 19/05/2021 | 7 | SHIBAM ENTERPRISE | 4.81 | 4.24 | 100 | 1
3255 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bewa (P) (313794) of Bewa-II under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block of Murshidabad District (PART-II) , SM/07681 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village Bewa (P)(Village code 313794), of Bewa Zone-II Ground Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723418) | 1458/MURD | 02/06/2022 | 120 | KISMAT ARA BEGUM | 104.36 | 63.06 | 100 | 0
3256 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Char Molladanga (Code-314558) In The Command Area Of Benipur Ground Water Supply Scheme (Part-C) Under Bhagwangola , SM/07791 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Char Molladanga (Village code 314558) under Benipur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | 193/BD-I | 04/02/2021 | 30 | NIRMAL UDYOG | 50.18 | 65.92 | 131.35 | 1
3257 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Village Of Char Molladanga (Code-314558) In The Command Area Of Benipur Ground Water Supply Scheme (Part-C) Under Bhagwangola , SM/07791 | Retrofitting | Additional Laying works at village Char Molladanga (Village code-314558) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Benipur Ground water supply scheme (Bhagwangola-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad | 2295/BD-I | 28/12/2021 | 15 | NIRMAL UDYOG | 7.52 | 6.91 | 100 | 1
3258 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari (314589) of Katlamari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block of Murshidabad District (PART-I) , SM/08188 | Retrofitting | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Katlamari PWSS Scheme, Block - Raninagar-II) to be Augmentation / Rejuvination under Murshidabad Division P.H.E. Dte. | 2745/MURD | 03/09/2021 | 60 | RADIANT | 11.14 | 0 | 0 | 1
3259 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 , SM/08192 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Joypur (Village code 315086) under Bhalkundi (Zone-I) Ground Water Based water Supply Scheme for Arsenic Affected Area of Khargram Block, under Murshidabad Division, PHE Dte. Scheme ID 0006154928 in the District of Murshidabad. (Sl No-08) | 165/MURD | 15/01/2021 | 180 | SOUMYADIP MISRA | 56.13 | 50.3 | 89.61 | 1
3260 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 , SM/08192 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BAUTIPARA (Village Code 315089) under Bhalkundi Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. | 3026/MURD | 04/12/2020 | 45 | SOM CONSTRUCTION AGENCY | 15.45 | 0 | 0 | 0
3261 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 , SM/08192 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bhalkundi(Village code 315091) under Bhalkundi (Zone-II)Ground Water Based Water Supply Scheme for Arsenic Affected Area of Khargram Block, under Murshidabad Division, PHE Dte. Scheme ID 0006154928 in the District of Murshidabad. (Sl No-09) | 3045/MURD | 07/12/2020 | 180 | M/S BHUBAN DAS | 47.51 | 0 | 0 | 1
3262 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 , SM/08192 | Retrofitting | Balance FHTC works of extension of distribution pipeline and restoration works of damage pipeline at Bhalkundi (Zone-II) Water Supply Scheme under Kandi Sub-Division, PHE Dte. in the district of Murshidabad | 318/KSD | 16/11/2021 | 30 | M/S BHUBAN DAS | 4.77 | 4.77 | 100 | 1
3263 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 , SM/08192 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) from existing distribution system within the command area of village Palsanda (315119) of Bhalkundi under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram Block of Murshidabad District . Tender no 540 of 20-21 by EE | 143-MSD/21-22 | 11/10/2021 | 0 | M/S. GOURI ENTERPRISE | 32.46 | 0 | 0 | 0
3264 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 , SM/08192 | Retrofitting | Balance work of distribution pipeline at Shri Krishnapur Village under Bhalkundi (Zone-I) Water Supply Scheme under Kandi Sub-Division, PHE Dte. in the district of Murshidabad. | 337/KSD | 30/11/2021 | 30 | SOUMYADIP MISRA | 4.8 | 4.8 | 100 | 1
3265 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 , SM/08192 | Retrofitting | Laying of HDPE (Materials grade PE-100 & Pressure Rating: PN6) pipe line & allied works of Retrofitting of Functional Household Tap Connections (FHTC) at village Bhalkundi (Village code-315091) Bhalkundi water supply scheme for FHTC work under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 29/KSD | 08/04/2022 | 30 | TIRUPATI CONSTRUCTION | 4.59 | 4.11 | 100 | 1
3266 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 , SM/08192 | Retrofitting | Laying of HDPE (Materials grade PE -100 & Pressure Rating : PN 6) Pipe Line due to widening of PWD Roads & construction of drain at village Bhalkundi (Village Code-315091) under Bhalkundi Water Supply Scheme of Kandi Sub Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 98 / KSD | 06/06/2022 | 30 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 4.83 | 4.56 | 100 | 1
3267 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 , SM/08192 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with 'JALSWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BAUTIPARA (Village Code 315089) under Bhalkundi Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. Tender no - 694 of 20-21 by EE MURD | 334-MSD/21-22 | 05/03/2022 | 0 | SOM CONSTRUCTION AGENCY | 3.38 | 0 | 0 | 0
3268 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 , SM/08192 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at JOYPUR G.P. under Murshidabad Division, P.H.E.Dte. | 230/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.17 | 0 | 0 | 0
3269 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 , SM/08192 | Retrofitting | Material Requisition To Resource Division | 541/3/MURD | 25/02/2022 | 0 | Resource Division | 2.7 | 0 | 0 | 0
3270 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 , SM/08192 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village TELSUNDI (Village Code 315121) under Bhalkundi Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. | 3020/MURD | 04/12/2020 | 45 | M/S GUNGUN CONSTRUCTION | 19.58 | 0 | 0 | 1
3271 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Joypur, Purbba Srikrishnapur, Nabipur, Bautipara, Matai, Bhalkundi, Matanda, Kandra, Palsanda, Chandibati, Telsundi, Samandi (315086, 315087,315088, 315089, 315090 , SM/08192 | Retrofitting | Providing Balance Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of PALSANDA ( Village Code -315119) under Bhalkundi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram Block under Murshidabad Division P.H.E Dte. | 818/MURD | 25/03/2022 | 30 | M/S. GOURI ENTERPRISE | 9.52 | 9.38 | 100 | 1
3272 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bishnupur Ground Water Supply Scheme Under Raninagar-I Block In Murshidabad District Under Berhampore Division , SM/08904 | Retrofitting | Material Requisition To Resource Division | 141/BD-I | 10/02/2022 | 0 | Resource Division | 5.82 | 0 | 0 | 0
3273 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bishnupur Ground Water Supply Scheme Under Raninagar-I Block In Murshidabad District Under Berhampore Division , SM/08904 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Pratappur (village code 314757) under Bishnupur Ground Water based Water Supply Scheme in Raninagar-I Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1850/BD-I | 07/10/2021 | 100 | SRIJON ENTERPRISE | 96.18 | 43.74 | 45.48 | 1
3274 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bishnupur Ground Water Supply Scheme Under Raninagar-I Block In Murshidabad District Under Berhampore Division , SM/08904 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kamalpur (village code 314778) under Bishnupur Ground Water based Water Supply Scheme in Raninagar-I Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1851/BD-I | 07/10/2021 | 100 | SRIJON ENTERPRISE | 96.73 | 30.24 | 31.26 | 1
3275 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Brahmanigram ( 314319 ) and Bergram ( 314328 ) of Sagardighi Zone - I under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of , SM/09747 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Sagardighi-I Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. | 369/JSD | 22/12/2021 | 30 | S.S.INFRASTRUCTURE | 3.46 | 0 | 0 | 0
3276 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malancha (313840), Ratanpur (313841) and Bhasaipaikar ( 313879 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for arsenic affected areas of Samsergan , SM/09737 | Retrofitting | Continuation Work Order for Holding Awarness Progamme/campaigning programme at Gram Panchayet Level under Samserganj Block(Protapganj,Nimtita & Chachonda) in Murshidabad District in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (PART-B) | 127 /JSD | 27/05/2021 | 30 | IMAGIN COMMUNICATION | 1.19 | 1.19 | 100 | 0
3277 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malancha (313840), Ratanpur (313841) and Bhasaipaikar ( 313879 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for arsenic affected areas of Samsergan , SM/09737 | Retrofitting | Material Requisition To Resource Division | 540/8/MURD | 25/02/2022 | 0 | Resource Division | 67.97 | 0 | 0 | 0
3278 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malancha (313840), Ratanpur (313841) and Bhasaipaikar ( 313879 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for arsenic affected areas of Samsergan , SM/09737 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village of Ratanpur (Village code 313841) , Malancha (Village code 313840) ,under Bhasaipaikar Zone-I,II & III Ground Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723333) | 31/MURD | 06/01/2022 | 180 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 301.33 | 61.22 | 20.32 | 0
3279 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malancha (313840), Ratanpur (313841) and Bhasaipaikar ( 313879 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for arsenic affected areas of Samsergan , SM/09737 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village of Bhasaipaikar (Village code 313879) under Bhasaipaikar Zone-I,II & III Ground Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723333) | 16/MURD | 05/01/2022 | 180 | BANDHAB ENGINEERS CO-OPERATIVE SOCIETY LTD. | 235.91 | 45.81 | 19.42 | 0
3280 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malancha (313840), Ratanpur (313841) and Bhasaipaikar ( 313879 ) of Bhasaipaikar under Ground Water Based Water Supply Scheme for arsenic affected areas of Samsergan , SM/09737 | Retrofitting | Laying of Different dia UPVC pipeline at South Krishnanagar & Krishnanagar area in connection with Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) under command area of village of Ratanpur ( Village Code -313841) & Malancha (village code-313840) under Bhasaipaikar Zone-I,II &III Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samsherganj Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0001723333) | 1381/MURD | 26/05/2022 | 60 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 41.19 | 0 | 0 | 0
3281 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 313951 ) and Kadamtala ( 313953 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Bl , SM/09752 | Retrofitting | IEC Activity Through Poster / Banner/ Hoarding etc. on awareness of JAL SWAPNA (JJM), banner are fixed with of a frame( Frame Size:- 4¿00¿ x 4¿00¿) which made of 25 mm x 25 mm and 2.60 mm thick hollow square section, carriage of the same to the site, fitting, fixing all complete as per direction of EIC.for different G.P under Suti-II Block of Jangipur Sub -Division under Murshidabad Division,P.H.E Dte. | 366/JSD | 22/12/2021 | 30 | S.S.INFRASTRUCTURE | 3.13 | 0 | 0 | 0
3282 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 313951 ) and Kadamtala ( 313953 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Bl , SM/09752 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kadamtala (Village code 313953) under Mahisali Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723341 in the District of Murshidabad. | 304/MURD | 07/02/2022 | 60 | M/S. M.G. CONSTRUCTION | 27.86 | 0 | 0 | 0
3283 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10609 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional Household Connection of different existing PWSS (Sagarpara PWSS Scheme,Block- Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 260-MSD/22-23 | 18/08/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 11.08 | 0 | 0 | 0
3284 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10609 | Augmentation | Material Requisition To Resource Division | 2780/A/MURD | 01/10/2022 | 0 | Resource Division | 30.95 | 0 | 0 | 0
3285 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10609 | Augmentation | Material Requisition To Resource Division | 3037/MURD/2 | 27/09/2023 | 0 | Resource Division | 111.86 | 0 | 0 | 0
3286 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10609 | Augmentation | Formal Work Order for Augmentation of Sagarpara Part-B Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 2540/MURD | 02/09/2022 | 1052 | M/S GUHA AND ROY | 333.77 | 161.84 | 48.49 | 8
3287 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10609 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sagarpara Part-B Water Supply Scheme of TW-I,II,III at Head Work Site & 2nd Tube Well Site under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte | 3410/MURD | 22/12/2022 | 60 | R.K. DRILLING SERVICES | 35.34 | 30.68 | 100 | 90
3288 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10609 | Augmentation | NEW SERVICE CONNECTION ATSAGARPARA PWSS JL NO 10 PLOT NO RS 2294,2295 MURSHIDABAD ID 304240390 | 301/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 3.68 | 0 | 0 | 0
3289 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10609 | Augmentation | NEW SERVICE CONNECTION AT SAGARPARA PH ID 304244957 | 406/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 7.89 | 0 | 0 | 0
3290 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10609 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I,II & III of Sagarpara Part-B ground water based water supply scheme under Block- Jalangi, Dist. Murshidabad under MEDB, PHE Dte | 3776/MEDB | 03/11/2023 | 668 | ORIENTAL ENGINEERING CO. | 34.92 | 0 | 0 | 0
3291 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for SAGARPARA Part-B to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10609 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAGAR PARA PART-B Water Supply Scheme and Chandkati Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 3907/MURD | 20/12/2023 | 392 | NADIA TUBEWELLS | 18.43 | 0 | 0 | 100
3292 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Srikrishnapur ( 314737 ) of Aminabad under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshid , SM/09846 | Retrofitting | ¿ Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village Srikrishnapur (Village Code 314737) under Aminabad Ground Water Based Water Supply Scheme for arsenic affected areas of Domkol Block in the District of Murshidabad¿. | 3227/MURD | 22/12/2020 | 60 | PAL TROCKNER (P) LTD. | 43.57 | 38.99 | 100 | 100
3293 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pairmari ( 314672 ) of Dhulauri under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad Di , SM/09847 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Paikmari (Village code 314672) under Dhulauri Ground Water Based Water SupplyScheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723245 in the District of Murshidabad. | 32/MURD | 05/01/2021 | 60 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 44.55 | 20.15 | 153.25 | 0
3294 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pairmari ( 314672 ) of Dhulauri under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad Di , SM/09847 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Ja lSwapna under command area of village Paikmari (Village code 314672) under Dhulauri Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723245 in the District of Murshidabad. | 32/MURD | 05/01/2021 | 60 | MUNNA AGROTECH ENTERPRISE PRO: MIRAJUL ISLAM | 44.55 | 0 | 0 | 0
3295 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-II to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10997 | Augmentation | Material Requisition To Resource Division | 2780/G/MURD | 01/10/2022 | 0 | Resource Division | 11.59 | 0 | 0 | 0
3296 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-II to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10997 | Augmentation | Material Requisition To Resource Division | 1180/MURD/14 | 29/04/2023 | 0 | Resource Division | 11.83 | 0 | 0 | 0
3297 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sripatipur, Dakshin Panchnanpur, Char Syampur (314661, 314657 & 314658) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Do , SM/07289 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SARBANGAPUR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE- PARESNATHPUR , CODE-315529, TNO- 604/2020-21/EE | 512/W | 30/03/2021 | 0 | RATAN DUTTA | 25.78 | 0 | 0 | 0
3298 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sripatipur, Dakshin Panchnanpur, Char Syampur (314661, 314657 & 314658) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Do , SM/07289 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Char Syampur (314658) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District (Part-II), TNO- 737/2020-21/EE | 130-MSD/21-22 | 11/10/2021 | 0 | RAJU ENTERPRISE | 4.33 | 0 | 0 | 0
3299 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sripatipur, Dakshin Panchnanpur, Char Syampur (314661, 314657 & 314658) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Do , SM/07289 | Retrofitting | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0 | 0
3300 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sripatipur, Dakshin Panchnanpur, Char Syampur (314661, 314657 & 314658) of Baniakhali under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Do , SM/07289 | Retrofitting | Extension of Distribution UPVC pipeline for Providing Balance Functional Household Tap Connection (FHTC) of 69 nos left out household in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Char Syampur (Village code 314658) under Beniakhali Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad.(Scheme ID- 0001723470) | 878/MURD | 01/04/2022 | 30 | RAJU ENTERPRISE | 18.78 | 0 | 0 | 0
3301 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. , SM/12587 | Augmentation | Material Requisition To Resource Division | 196/BD-I/12 | 09/02/2024 | 0 | Resource Division | 3.11 | 0 | 0 | 0
3302 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. , SM/12587 | Augmentation | Gobra Water Supply Scheme | 349/WBSEDCL-JJM | 15/02/2024 | 0 | WBSEDCL | 3.07 | 0 | 0 | 0
3303 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. , SM/12587 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Gobra ground water supply scheme in Bhagwabgola-I Block Dist_Murshidabad under MEDB PHE Dte. | 1136/MEDB | 13/05/2025 | 92 | DEY ENTERPRISE (MALDA) | 39.59 | 0 | 0 | 0
3304 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. , SM/12587 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of GOBRA ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | 3730/MEDB | 03/11/2023 | 668 | SARKAR CONSTRUCTION | 11.46 | 9.53 | 83.14 | 15
3305 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. , SM/12587 | Augmentation | Augmentation of GOBRA Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road,laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 745/BD-I | 17/08/2023 | 715 | DAS TRADING CO | 315.08 | 16.72 | 5.31 | 21
3306 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. , SM/12587 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC, Block Bhagwangola-I of Murshidabad District under MEDB, PHE Dte. | 329/MEDB | 10/02/2025 | 89 | MASSK ENGINEERING WORKS | 11.36 | 0 | 0 | 0
3307 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. , SM/12587 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after successful completion of 3 (Three) months Trial Run of "Augmentation of Gobra ground water supply scheme in Bhagwabgola-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | 286/BD-I | 12/02/2025 | 300 | MODERN CONSTRUCTION | 122.8 | 0 | 0 | 0
3308 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. , SM/12587 | Augmentation | Improvement of Existing AIRP (Modified Sujapur Sadipur Model, Capacity 30.00 cum/hr) including required allied works of GOBRA PWSS under Jal Jeevan Mission within Bhagwangola-I interconnection with Augmentation under Berhampore Division-I, P.H.E. Dte. In the districtof Murshidabad.. | 762/BD-I | 22/05/2025 | 30 | ANKITA ENTERPRISE-GOPEJAN (NATHPARA) | 9.68 | 0 | 0 | 0
3309 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. , SM/12587 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for GOBRA Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 266/ BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.71 | 2.61 | 100 | 1
3310 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. , SM/12587 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) for Gobra water supply scheme of Bhagwangola-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 1010/BD-I | 31/10/2023 | 30 | ANKITA ENTERPRISE-GOPEJAN (NATHPARA) | 6.7 | 6.42 | 100 | 100
3311 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. , SM/12587 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gobra Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 159/BD-I | 05/02/2024 | 30 | M/S D. PALIT & CO. | 9 | 0 | 0 | 100
3312 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Harirampur to Accommodate FHTC. , SM/12586 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Harirampur ground water based water supply scheme under Block- BHAGAWANGOLA-II Dist. Murshidabad under MEDB, PHE Dte. | 761/MEDB | 20/02/2024 | 90 | ASSOCIATED ELECTRICAL CO. | 10.35 | 0 | 0 | 0
3313 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Harirampur to Accommodate FHTC. , SM/12586 | Augmentation | Material Requisition To Resource Division | 196/BD-I/4 | 09/02/2024 | 0 | Resource Division | 116.19 | 0 | 0 | 0
3314 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Harirampur to Accommodate FHTC. , SM/12586 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HARIRAMPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 273/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.45 | 2.45 | 100 | 1
3315 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Harirampur to Accommodate FHTC. , SM/12586 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Harirampur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | 1440/BD-I | 16/01/2023 | 30 | K.B CONSTRUCTION | 2.41 | 2.39 | 100 | 100
3316 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. , SM/11712 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.4 | 100 | 100
3317 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. , SM/11712 | Augmentation | Material Requisition To Resource Division | 1147/MURD/11 | 27/04/2023 | 0 | Resource Division | 19.36 | 0 | 0 | 0
3318 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. , SM/11712 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 0 | 5
3319 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. , SM/11712 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Bahadurpur Piped Water Supply Scheme Block Suti-I District - Murshidabad. under MEDB, PHE Dte. | 331/MEDB | 10/02/2025 | 89 | M/S. T.K. BASU RAY | 21.53 | 0 | 0 | 50
3320 | MURSHIDABAD | Berhampore Mechanical | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Nimtita (313863) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District under Murshidabad Division PheDte. , SM/11215 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Hasimpur ground water based water supply scheme under Block_ Samserganj Dist. - Murshidabad under MEDB, PHE Dte. | 1875/MEDB | 16/06/2023 | 92 | DEY ENTERPRISE | 20.82 | 0 | 0 | 0
3321 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Nimtita (313863) of Hasimpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Samserganj Block of Murshidabad District under Murshidabad Division PheDte. , SM/11215 | Augmentation | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Nimtita ( Village Code -313863) under Hasimpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of SAMSERGANJ Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723174). | 639/MURD | 18/02/2021 | 60 | AZAD ENTERPRISE | 25.44 | 24.27 | 100 | 1
3322 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11571 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Katlamari PWSS Scheme, Block - Raninagar-II) to be Augmentation / Rejuvination under Murshidabad Division P.H.E. Dte. | 2745/MURD | 03/09/2021 | 60 | RADIANT | 11.14 | 5.57 | 100 | 1
3323 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11571 | Augmentation | Material Requisition To Resource Division | 3052/E/MURD | 17/11/2022 | 0 | Resource Division | 9.64 | 0 | 0 | 0
3324 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11571 | Augmentation | Material Requisition To Resource Division | 1167/MURD | 28/04/2023 | 0 | Resource Division | 57.64 | 0 | 0 | 0
3325 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11571 | Augmentation | Formal work order for Laying of Distribution (part-III) and Providing Functional Household Connection to 670 nos household & Construction of Boundary wall of Katlamari Zone -II of Islampur Sub Division under Murshidabad Division,P.H.E Dte.[(i)Amount for LDS & FHTC: Rs.14312870.00 & (ii)Amount for Construction of Boundary wall : Rs.897464.00] | 57/MURD | 06/01/2023 | 60 | SOM CONSTRUCTION AGENCY | 132.94 | 0 | 0 | 10
3326 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11571 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-II under KATLAMARI ground water based water supply scheme under Block_ RANINAGAR-II Dist. - Murshidabad under MEDB, PHE Dte. | 4051/MEDB | 01/12/2023 | 91 | M/S K.P. PRAMANIK | 34.44 | 27.94 | 81.11 | 20
3327 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11571 | Augmentation | NEW SERVICE CONNECTION AT KATLAMARI Z2 PH2, ID304232741 | 282/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 5.04 | 0 | 0 | 0
3328 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11571 | Augmentation | NEW SERVICE CONNECTION AT KATLAMARI Z2 PH 3, ID304232745 | 284/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 4.37 | 0 | 0 | 0
3329 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11571 | Augmentation | NEW SERVICE CONNECTION AT KATLAMRI Z2 PH I, ID304232748 | 283/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.2 | 0 | 0 | 0
3330 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11571 | Augmentation | Formal work order for Laying of Distribution System (part-II) and Providing Functional Household Tap Connection to 550 nos household & Sub-soil Investigation and Construction of OHR (500 cum) of Katlamari Zone -II of Islampur Sub-Division under Murshidabad Division,P.H.E Dte | 3244/MURD | 06/12/2022 | 1116 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 214.83 | 143.72 | 66.9 | 18
3331 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11571 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Katlamari Zone-II Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3060/MURD | 17/11/2022 | 45 | GENUINE | 23.5 | 18.95 | 80.65 | 0
3332 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11571 | Augmentation | Formal work order Laying of Distribution System (part-I) , Rising Main and Providing Functional Household Tap Connection to 790 nos household & Construction of Pump House of Katlamari Zone -II of Islampur Sub-Division under Murshidabad Division,P.H.E Dte [ (i)Amount for LDS,R. Main & FHTC:: Rs.1,38,47,328.00 & (ii)Amount for Construction of Pump House : Rs.15,28,347.00] | 162/MURD | 17/01/2023 | 1111 | SOUNAK ENTERPRISE | 153.68 | 80.12 | 52.13 | 10
3333 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11571 | Augmentation | Allied work for Construction of Boundary Wall & Approach Road at Katlamari ZONE-II Ground water based Piped water supply scheme within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | 1948/MURD | 04/07/2024 | 330 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 38.57 | 0 | 0 | 80
3334 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11560 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Godhanpara PWSS Scheme, Block - Raninagar-II) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | 2744/MURD | 03/09/2021 | 60 | RADIANT | 11.27 | 3.76 | 100 | 0
3335 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11560 | Augmentation | Material Requisition To Resource Division | 3037/D/MURD | 16/11/2022 | 0 | Resource Division | 40.31 | 0 | 0 | 0
3336 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11560 | Augmentation | Material Requisition To Resource Division | 3052/C/MURD | 17/11/2022 | 0 | Resource Division | 17.71 | 0 | 0 | 0
3337 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11560 | Augmentation | Material Requisition To Resource Division | 1278/MURD/12 | 10/05/2023 | 0 | Resource Division | 37.4 | 0 | 0 | 0
3338 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11560 | Augmentation | NEW SERVICE CONNECTION AT GODHANPARA Z3 PH I, ID304232740 | 286/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 6.75 | 0 | 0 | 0
3339 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11560 | Augmentation | Formal work order for Laying of Distribution system,Rising Main, Sub-soil Investigation and construction of OHR (300 cum) and construction of Boundary wall and repairing of Pump-House in connection wih Augmentation of Godhanpara Zone-III water supply scheme under Murshidabad Division, PHE Dte. | 2729/MURD | 27/09/2022 | 1435 | PRIYANKA CONSTRUCTION | 270.88 | 183.93 | 67.9 | 80
3340 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11560 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works forAugmentation in connention to Accommodate FHTC at Pump House No.-I, Zone-III under Godhanpara Ground Water Based Piped Water Supply Scheme under Block- Raninagar-II Dist. - Murshidabad under MEDB, PHE Dte. | 342/MEDB | 10/02/2025 | 89 | J. S. CONSTRUCTION | 11.36 | 0 | 0 | 0
3341 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- III ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11560 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Godhanpara Zone-III Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3059/MURD | 17/11/2022 | 45 | GENUINE | 23.5 | 20.83 | 100 | 100
3342 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. , SM/12823 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Jhikra ground water based water supply scheme under Block- Bhagwangola-II, Dist. Murshidabad under MEDB, PHE Dte. | 4320/MEDB | 29/12/2023 | 91 | A.G. ENTERPRISE | 11.17 | 0 | 0 | 0
3343 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. , SM/12823 | Augmentation | Material Requisition To Resource Division | 196/BD-I/5 | 09/02/2024 | 0 | Resource Division | 5.7 | 0 | 0 | 0
3344 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. , SM/12823 | Augmentation | JHIKRA PWSS | 347/WBSEDCL-JJM | 15/02/2024 | 0 | WBSEDCL | 2.14 | 0 | 0 | 0
3345 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. , SM/12823 | Augmentation | Augmentation of JHIKRA Piped water supply scheme to accommodate construction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1615/BD-I | 02/03/2023 | 310 | KAMIRUL SK AND CO. | 418.14 | 68.93 | 16.49 | 35
3346 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. , SM/12823 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for JHIKRA Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 271//BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.75 | 2.75 | 100 | 100
3347 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. , SM/12823 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Jhikra ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | 1365/BD-I | 21/12/2022 | 30 | AZAD ENTERPRISE | 2.41 | 2.37 | 100 | 100
3348 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. , SM/12823 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jhikra Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 1806/BD-I | 31/03/2023 | 30 | SUJIT KUMAR SAHA | 8.99 | 0 | 0 | 100
3349 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. , SM/12823 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) forJhikra water supply scheme of Bhagwangola-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 1029/BD-I | 01/11/2023 | 30 | MARUTI CONSTRUCTION & CO. | 7.67 | 7.6 | 100 | 100
3350 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. , SM/12823 | Augmentation | Allied work for the work of Augmentation of Jhikra Piped water supply scheme to accommodate construction of OHR, Pump House, Boundary wall and service road, laying of design pipeline and providing FHTC (Fanctional Household Tap Connection) under Jal Jeevan Mission in Bhagwangola-II Block in Murshidabad District under Berhampore Division-I,PHE Dte. | 927/BD-I | 07/06/2024 | 30 | KAMIRUL SK AND CO. | 28.79 | 23 | 45.29 | 100
3351 | MURSHIDABAD | Berhampore Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. , SM/12824 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BENIPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1076/BD-I | 29/09/2022 | 10 | NATSOL CONSULTANT | 2.92 | 2.92 | 100 | 0
3352 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. , SM/12824 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of BENIPUR ground water based water supply scheme under Block- Bhagawangola- II, Dist. Murshidabad under MEDB, PHE Dte. | 3765/MEDB | 03/11/2023 | 92 | TARUN KUMAR BHATTACHARYA | 25.87 | 0 | 0 | 0
3353 | MURSHIDABAD | Berhampore Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. , SM/12824 | Augmentation | Material Requisition To Resource Division | 61/BD-1/3 | 27/04/2023 | 0 | Resource Division | 36.06 | 0 | 0 | 0
3354 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. , SM/12824 | Augmentation | NEW CONNECTION AT BENIPUR PH-I | 147/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 11.24 | 0 | 0 | 0
3355 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. , SM/12824 | Augmentation | NEW CONNECTION AT BENIPUR PH-I |  | 27/06/2024 | 0 | WBSEDCL | 11.24 | 0 | 0 | 0
3356 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. , SM/12824 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Benipur ground water supply scheme in Bhagwabgola-II Block, Dist_Murshidabad under MEDB PHE Dte." | 1139/MEDB | 13/05/2025 | 92 | DIPALI CONSTRUCTION | 39.95 | 0 | 0 | 0
3357 | MURSHIDABAD | Berhampore Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. , SM/12824 | Augmentation | Formal work order for Augmentation of Benipur Piped water supply scheme to accommodate construction of OHR, toilet, pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1448/BD-I | 17/01/2023 | 1000 | KAMIRUL SK AND CO. | 472.43 | 66.33 | 14.04 | 40
3358 | MURSHIDABAD | Berhampore Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. , SM/12824 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Benipur ground water supply scheme in Bhagwabgola-II Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | 327/BD-I | 25/02/2025 | 300 | J.S. CONSTRUCTION | 122.8 | 0 | 0 | 0
3359 | MURSHIDABAD | Berhampore Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. , SM/12824 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Benipur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | 1810/BD-I | 31/03/2023 | 898 | SUJIT KUMAR SAHA | 18.01 | 6.42 | 49.27 | 100
3360 | MURSHIDABAD | Berhampore Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. , SM/12824 | Augmentation | Repair And Renovation Works Of RCC Elevated Reservoir (450 Cum) for Benipur water supply scheme of Bhagwangola-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 985/BD-I | 30/10/2023 | 450 | SHIBAM ENTERPRISE | 8.54 | 8.39 | 100 | 100
3361 | MURSHIDABAD | Berhampore Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. , SM/12824 | Augmentation | Allied work for the work of Augmentation of Benipur Piped water supply scheme to accommodate construction of OHR, Pump House, Boundary wall and service road, laying of design pipeline and providing FHTC (Fanctional Household Tap Connection) under Jal Jeevan Mission in Bhagwangola-II Block in Murshidabad District under Berhampore Division-I,PHE Dte. | 928/BD-I | 07/06/2024 | 30 | KAMIRUL SK AND CO. | 28.79 | 27.78 | 100 | 100
3362 | MURSHIDABAD | Murshidabad Division | SIJGRAM AND ADJOINING MOUJAS PWSS , SM/13730 | New | Material Requisition To Resource Division | 1210/MURD/34 | 02/05/2023 | 0 | Resource Division | 42.92 | 0 | 0 | 0
3363 | MURSHIDABAD | Murshidabad Division | SIJGRAM AND ADJOINING MOUJAS PWSS , SM/13730 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SIJGRAM PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3405/MURD | 22/12/2022 | 45 | M/S D. PALIT & CO. | 16.81 | 15.42 | 100 | 100
3364 | MURSHIDABAD | Berhampore Mechanical | SIJGRAM AND ADJOINING MOUJAS PWSS , SM/13730 | New | NEW SERVICE CONNECTION AT SIJGRAM PH 1 PWSS ID 304201248 | 221/WBSEDCL-JJM | 05/01/2024 | 0 | WBSEDCL | 5.03 | 0 | 0 | 0
3365 | MURSHIDABAD | Berhampore Mechanical | SIJGRAM AND ADJOINING MOUJAS PWSS , SM/13730 | New | Sijgram ph-2 Application No- 3004401470 | 242/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 8.65 | 0 | 0 | 0
3366 | MURSHIDABAD | Berhampore Mechanical | SIJGRAM AND ADJOINING MOUJAS PWSS , SM/13730 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SIJGRAM ground water based water supply scheme under Block_ Bharatpur-I, Dist. - Murshidabad under MEDB, PHE Dte. | 1893/MEDB | 16/06/2023 | 899 | SUNIL RABIDAS | 22.58 | 16.22 | 71.81 | 5
3367 | MURSHIDABAD | Murshidabad Division | SIJGRAM AND ADJOINING MOUJAS PWSS , SM/13730 | New | Formal work order for Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of SIJGRAM PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362356S000) [ (i) Amount for LDS , R.Main & FHTC: Rs.1,23,22,548.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs.1,57,06,711.00] | 412/MURD | 15/02/2023 | 1020 | S. ENTERPRISE (PROP: SAIRUL ISLAM) | 280.01 | 70.72 | 25.26 | 11
3368 | MURSHIDABAD | Murshidabad Division | SIJGRAM AND ADJOINING MOUJAS PWSS , SM/13730 | New | Allied work of Construction of 2nos. Box Culvert, approach road at Sijgram PWSS at Bharatpur -I Block under Kandi Sub-Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 1893/MURD | 01/07/2024 | 242 | RIM CONSTRUCTION | 44.07 | 3.28 | 7.44 | 10
3369 | MURSHIDABAD | Murshidabad Division | SIJGRAM AND ADJOINING MOUJAS PWSS , SM/13730 | New | Formal work order for Laying Distribution System (PART -A) of SIJGRAM PWSS of Bharatpur - I Block, Kandi Sub Division under Murshidabad District, PHE Dte. | 132 / MURD | 16/01/2023 | 775 | JIBENDRA NARAYAN SUKUL | 136.47 | 134.68 | 98.49 | 67
3370 | MURSHIDABAD | Murshidabad Division | SIJGRAM AND ADJOINING MOUJAS PWSS , SM/13730 | New | Balance work for laying of distribution pipe line and allied works of Sijgram Water Supply Scheme, Bharatpur - I Block, Kandi Sub-Division under Murshidabad Division, PHE Dte. | 3441/MURD | 03/11/2023 | 698 | JIBENDRA NARAYAN SUKUL | 28.37 | 11.97 | 67.68 | 50
3371 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF DHUSARIPARA BLOCK-SAMSHERGANJ , SM/11229 | Augmentation | Preparation of D.p.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (DHUSARIPARA PWSS Scheme,Block- SAMSERGAUNGE to be Augmentation/Rejuvination under Murshidabad Division P.H.E.Dte. | 3251/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.94 | 5.94 | 100 | 1
3372 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF DHUSARIPARA BLOCK-SAMSHERGANJ , SM/11229 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under DHUSARIPARA ground water based water supply scheme under Block_ Samsherganj, Dist. - Murshidabad under MEDB, PHE Dte. | 1874/MEDB | 16/06/2023 | 92 | ARINDAM MAJUMDAR | 22.1 | 0 | 0 | 0
3373 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF DHUSARIPARA BLOCK-SAMSHERGANJ , SM/11229 | Augmentation | Material Requisition To Resource Division | 1167/MURD/27 | 28/04/2023 | 0 | Resource Division | 11.5 | 0 | 0 | 0
3374 | MURSHIDABAD | Murshidabad Division | LOHADAHA AND ADJOINING MOUJAS PWSS , SM/13727 | New | Material Requisition To Resource Division | 1004/MURD/17 | 17/04/2023 | 0 | Resource Division | 36.62 | 0 | 0 | 0
3375 | MURSHIDABAD | Berhampore Mechanical | LOHADAHA AND ADJOINING MOUJAS PWSS , SM/13727 | New | Lohadaha PH-1 Application No- 3004528444 | 280/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.67 | 0 | 0 | 0
3376 | MURSHIDABAD | Berhampore Mechanical | LOHADAHA AND ADJOINING MOUJAS PWSS , SM/13727 | New | Quotation for Lohadaha PH-2 | 331/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 5.54 | 0 | 0 | 0
3377 | MURSHIDABAD | Murshidabad Division | LOHADAHA AND ADJOINING MOUJAS PWSS , SM/13727 | New | Formal work order for the work of LOHADAHA & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362288S000) | 146/MURD | 17/01/2023 | 1445 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 492.18 | 300.22 | 61 | 78
3378 | MURSHIDABAD | Berhampore Mechanical | LOHADAHA AND ADJOINING MOUJAS PWSS , SM/13727 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under LOHADAHA ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | 1890/MEDB | 16/06/2023 | 853 | M/S SWAPAN BANERJEE | 24.36 | 20.59 | 84.58 | 15
3379 | MURSHIDABAD | Murshidabad Division | PUNIA AND ADJOINING MOUJAS PWSS , SM/13933 | New | Material Requisition To Resource Division | 1067/MURD/4 | 18/04/2023 | 0 | Resource Division | 12.28 | 0 | 0 | 0
3380 | MURSHIDABAD | Berhampore Mechanical | PUNIA AND ADJOINING MOUJAS PWSS , SM/13933 | New | Electric Service New Connection PUNIA PH- 2 PWSS Application NO. 3004403727. ID. 304119979 | 174/WBSEDCL-JJM | 05/12/2023 | 0 | WBSEDCL | 4.94 | 0 | 0 | 0
3381 | MURSHIDABAD | Berhampore Mechanical | PUNIA AND ADJOINING MOUJAS PWSS , SM/13933 | New | Electric Service New Connection PUNIA PH- 1 PWSS Application NO. 3004403691. ID. 304119961 | 173/WBSEDCL-JJM | 05/12/2023 | 0 | WBSEDCL | 6.85 | 0 | 0 | 0
3382 | MURSHIDABAD | Berhampore Mechanical | PUNIA AND ADJOINING MOUJAS PWSS , SM/13933 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under PUNIA ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | 2014/MEDB | 19/06/2023 | 92 | M/S S. S. ENTERPRISE (DOMKAL) | 22.32 | 14.31 | 64.09 | 50
3383 | MURSHIDABAD | Murshidabad Division | PUNIA AND ADJOINING MOUJAS PWSS , SM/13933 | New | Material Requisition To Resource Division | 79/MURD/02 | 09/01/2024 | 0 | Resource Division | 17.24 | 0 | 0 | 0
3384 | MURSHIDABAD | Murshidabad Division | PUNIA AND ADJOINING MOUJAS PWSS , SM/13933 | New | Formal work order for the work of PUNIA & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | 164/MURD | 17/01/2023 | 1404 | M/S.TAPAS KUMAR CHAKRABORTY | 561.45 | 326.12 | 58.08 | 26
3385 | MURSHIDABAD | Murshidabad Division | PUNIA AND ADJOINING MOUJAS PWSS , SM/13933 | New | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 4.01 | 100 | 100
3386 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- II . , SM/14429 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-II of Bishnupur ground water based water supply scheme under Block- RANINAGAR-I Dist. Murshidabad under MEDB, PHE Dte. | 4316/MEDB | 29/12/2023 | 91 | S.P. ENTERPRISE (BAGUIHATI) | 10.62 | 0 | 0 | 0
3387 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- II . , SM/14429 | Augmentation | Material Requisition To Resource Division | 194/BD-I/6 | 09/02/2024 | 0 | Resource Division | 42.69 | 0 | 0 | 0
3388 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- II . , SM/14429 | Augmentation | Formal work order for Augmentation of Bishnupur Zone-II Piped water supply scheme to accommodate construction of Pump house, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | 1541/BD-I | 16/02/2023 | 925 | NATIONAL CONSTRUCTION | 190.09 | 181.89 | 96.32 | 95
3389 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- II . , SM/14429 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BISHNUPUR ZONE-II Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte | 1761/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.6 | 2.6 | 100 | 100
3390 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- II . , SM/14429 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) of Ground Water Based Supply Scheme for Bishnupur Zone-II of Raninagar-I block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | 1031/BD-I | 01/11/2023 | 30 | KUNTAL SAHA | 8.46 | 6.78 | 100 | 100
3391 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- II . , SM/14429 | Augmentation | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bishnupur Zone-II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte | 1150/BD-I | 04/12/2023 | 30 | MAMATA USHA ENTERPRISE | 11.57 | 9.34 | 100 | 100
3392 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/14430 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for CHARKAMNAGAR Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1592/BD-I | 28/02/2023 | 10 | TECHVISION | 2.74 | 2.74 | 100 | 0
3393 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/14430 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under CHARKAMNAGAR ground water based water supply scheme under Block_ Beldanga-II Dist. - Murshidabad under MEDB, PHE Dte. | 3778/MEDB | 26/05/2023 | 92 | WEST BENGAL ENGINEERING CO. | 35.2 | 0 | 0 | 0
3394 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/14430 | Augmentation | Material Requisition To Resource Division | 196/BD-I/20 | 09/02/2024 | 0 | Resource Division | 77.09 | 0 | 0 | 0
3395 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/14430 | Augmentation | Augmentation of Charkamnagar Piped water supply scheme to accommodate construction of OHR, Pump House, Boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | 681/BD-I | 10/08/2023 | 990 | MERCURY ENGINEERING COMPANY | 418.24 | 0 | 0 | 7
3396 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/14430 | Augmentation | Allied work for Laying of distribution pipeline of CHARKAMNAGAR and allied works within Beldanga-II Block under Berhampore Division-I, PHE Dte. in the district of Murshidabad. | 2122/BD-I | 27/11/2024 | 45 | NOVELTY CONSTRUCTION | 46.47 | 0 | 0 | 0
3397 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/14430 | Augmentation | Bored Cast-in-situ_ M30 _ grade 500 mm dia. R.C.C. pile for Construction of OHR at Head Work site of CHARKAMNAGAR Ground Piped Water Supply Scheme under Jal Jeevan Mission within Beldanga - II Block under Berhampore Division-I, PHE.Dte. in the district of Murshidabad. | 279/BD-I | 12/02/2025 | 30 | MERCURY ENGINEERING COMPANY | 25.63 | 0 | 0 | 0
3398 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/14430 | Augmentation | Construction of Boundary wall at 2nd Tube Well Site of CHARKAMNAGAR ZONE-I PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 672/BD-I | 29/04/2025 | 45 | JAMUNA CONSTRUCTION | 10.18 | 0 | 0 | 0
3399 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/14430 | Augmentation | Repair And Renovation Works Of OHR (350 Cum) forCharkamnagar water supply scheme of Beldanga-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 1011/BD-I | 31/10/2023 | 450 | PARTHA PRATIM DAS | 8.36 | 0 | 0 | 100
3400 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. , SM/14430 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Charkamnagar Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte ( For 2 nos Tubewell) | 155/BD-I | 05/02/2024 | 30 | NADIA TUBEWELLS | 18.01 | 14.57 | 100 | 100
3401 | MURSHIDABAD | Murshidabad Division | HAMIDPUR AND ADJOINING MOUJAS PWSS , SM/14867 | New | Material Requisition To Resource Division | 1075/MURD/12 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
3402 | MURSHIDABAD | Berhampore Mechanical | HAMIDPUR AND ADJOINING MOUJAS PWSS , SM/14867 | New | NEW CONNECTION AT HAMIDPUR PH-II | 107/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 8.94 | 0 | 0 | 0
3403 | MURSHIDABAD | Berhampore Mechanical | HAMIDPUR AND ADJOINING MOUJAS PWSS , SM/14867 | New | NEW CONNECTION AT HAMIDPUR PH-I | 106/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 9.71 | 0 | 0 | 0
3404 | MURSHIDABAD | Murshidabad Division | HAMIDPUR AND ADJOINING MOUJAS PWSS , SM/14867 | New | HAMIDPUR & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- BHARATPUR-I of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte | 872/MURD | 27/03/2023 | 857 | PRATIMA CONSTRUCTION | 159.76 | 79.99 | 50.07 | 5
3405 | MURSHIDABAD | Berhampore Mechanical | HAMIDPUR AND ADJOINING MOUJAS PWSS , SM/14867 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Hamidpur ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | 3707/MEDB | 03/11/2023 | 1096 | CONCORD ENGINEERING | 23.56 | 0 | 0 | 10
3406 | MURSHIDABAD | Murshidabad Division | BIPRA SEKHAR AND ADJOING MOUJAS PWSS , SM/14868 | New | Material Requisition To Resource Division | 1219/MURD/11 | 03/05/2023 | 0 | Resource Division | 21.03 | 0 | 0 | 0
3407 | MURSHIDABAD | Murshidabad Division | BIPRA SEKHAR AND ADJOING MOUJAS PWSS , SM/14868 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BIPRA SEKHAR AND ADJOINING MOUJAS Water Supply Scheme & ALAMPUR Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 2807/MURD | 05/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0 | 100
3408 | MURSHIDABAD | Berhampore Mechanical | BIPRA SEKHAR AND ADJOING MOUJAS PWSS , SM/14868 | New | NEW SERVICE CONNECTION AT PWSS PH 2 BIPRASEKHAR ID 304247692 | 316/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 7.95 | 0 | 0 | 0
3409 | MURSHIDABAD | Berhampore Mechanical | BIPRA SEKHAR AND ADJOING MOUJAS PWSS , SM/14868 | New | NEW SERVICE CONNECTION AT PWSS BIPRASEKHAR PH1 ID 304247611 | 315/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 9.43 | 0 | 0 | 0
3410 | MURSHIDABAD | Murshidabad Division | BIPRA SEKHAR AND ADJOING MOUJAS PWSS , SM/14868 | New | BIPRA SEKHAR PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Burwan Block , Kandi Sub-Division, of Murshidabad Division ,PHE.Dte. | 823/MURD | 23/03/2023 | 831 | DILIP KUMAR MONDAL | 657.71 | 480.27 | 73.02 | 50
3411 | MURSHIDABAD | Berhampore Mechanical | BIPRA SEKHAR AND ADJOING MOUJAS PWSS , SM/14868 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Bipra Sekhar ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | 3702/MEDB | 03/11/2023 | 791 | M/S S. S. ENTERPRISE (DOMKAL) | 22.55 | 14.53 | 64.45 | 50
3412 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14044 | Augmentation | Material Requisition To Resource Division | 61/BD-1/9 | 27/04/2023 | 0 | Resource Division | 57.59 | 0 | 0 | 0
3413 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14044 | Augmentation | RAMNAGAR DOEMKANUN ZONE-I PART-B PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1552/BD-I | 24/09/2024 | 60 | M/S B.M. INDUSTRIES | 20.64 | 0 | 0 | 0
3414 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14044 | Augmentation | NEW CONNECTION RAMNAGAR DEOMKANUN Z-1 PH-I | 470/WBSEDCL-JJM | 19/03/2024 | 0 | WBSEDCL | 12.56 | 0 | 0 | 0
3415 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14044 | Augmentation | Augmentation of Ramnagar Doemkanun Zone-I(Part-B) Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 695/BD-I | 11/08/2023 | 627 | M/S SINHA & SONS | 408.86 | 0 | 0 | 25
3416 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14044 | Augmentation | Construction of Service Road for approach and Pump House at Augmentation of Ramnagar Doemkanon Zone-I (Part-B) PWSS of Raninagar-II Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | 1120/BD-I | 11/07/2024 | 60 | S.K ENTERPRISE (RANITALA) | 7.92 | 0 | 0 | 0
3417 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14044 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of Ramnagar Doemkanun Zone-I (Part-B) PWSS under Jal Jeevan Mission within Raninagar -II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 840/BD-I | 23/06/2025 | 60 | PRADIP MAHATO | 19 | 0 | 0 | 0
3418 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14044 | Augmentation | Continuation for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNAGAR DOEMKANON ZONE-I Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1384/BD-I | 23/12/2022 | 10 | RADIANT | 2.94 | 2.79 | 100 | 100
3419 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14045 | Augmentation | Material Requisition To Resource Division | 61/BD-1/25 | 27/04/2023 | 0 | Resource Division | 29.78 | 0 | 0 | 0
3420 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14045 | Augmentation | Allied work for Laying of Distribution pipeline of Ramnagar Doemkanon Zone - I PWSS within Raninagar - II Block under JJM of Murshidabad district under Berhampore Division - I P.H.Engg Dte. | 1471/BD-I | 06/09/2024 | 225 | MAA CONSTRUCTION | 26.47 | 0 | 0 | 85
3421 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14045 | Augmentation | Construction Pump House Cum Chlorine Room at RAMNAGAR DOEMKANUN ZONE-I Water Supply Scheme under Jal Jevan Mission within Raninagar-II Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | 273/BD-I | 11/02/2025 | 60 | TAIMUR SK | 7.5 | 0 | 0 | 0
3422 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14045 | Augmentation | Improvement of OHR (350 Cum) of Ground Water Based Supply Scheme for Augmentation of Ramnagar Domkanun Zone-I Part-A of Raninagar-I block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | 891/BD-I | 06/06/2024 | 30 | PRAVAT KUMAR GHOSH | 8.66 | 6.89 | 79.55 | 100
3423 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14045 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of Ramnagar Doemkanun Zone- I(Part-A) PWSS under Jal Jeevan Mission within Raninagar -II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 876/BD-I | 01/07/2025 | 60 | BISWAS CONSTRUCTION | 18.97 | 0 | 0 | 0
3424 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14045 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNAGAR DOEMKANON ZONE-I Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1379/BD-I | 22/12/2022 | 10 | RADIANT | 2.94 | 2.85 | 100 | 100
3425 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. , SM/14045 | Augmentation | Construction of Boundary Wall with Main Entrance gate and barbed wire facing and service road for approach at Augmentation of Ramnagar Doemkanun Zone-I (Part-A) PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | 1066/BD-I | 03/07/2024 | 273 | MUNNA AGROTECH ENTERPRISE | 20.5 | 11.29 | 62.75 | 55
3426 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME , SM/14067 | Augmentation | Augmentation of Bajipur Madhupur Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte.(PART-A) | 697/BD-I | 11/08/2023 | 310 | UNIVERSE UNEMPLOYED ENGINEERS CONSTRUCTION CO. | 335.43 | 0 | 0 | 0
3427 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME , SM/14067 | Augmentation | Material Requisition To Resource Division | 201/BD-1/17 | 10/02/2024 | 0 | Resource Division | 280.69 | 0 | 0 | 0
3428 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME , SM/14067 | Augmentation | Material Requisition To Resource Division | 1510/BD-I/8 | 12/09/2024 | 0 | Resource Division | 9.8 | 0 | 0 | 0
3429 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME , SM/14067 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF BAJUPUR MADHUPUR ZONE-II PIPED WATER SUPPLY SCHEME Block - Lalgola under MEDB, PHE Dte. | 326/MEDB | 10/02/2025 | 89 | KARTICK BAL | 25.03 | 0 | 0 | 0
3430 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME , SM/14067 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BAJIPUR MADHUPUR ZONE-II Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1383/BD-I | 23/12/2022 | 10 | ENVIROTECH SOLUTIONS | 2.87 | 2.9 | 100 | 1
3431 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME , SM/14067 | Augmentation | Repair And Renovation Works Of OHR (450 Cum) for Bajupur Madhupur Zone-II water supply scheme of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal Jeevan Mission. | 15/BD-I | 04/01/2024 | 330 | MAA SANKARI ENTERPRISE | 8.61 | 0 | 0 | 100
3432 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14068 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-I Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1320/BD-I | 13/12/2022 | 10 | TECHVISION | 2.81 | 2.81 | 99.98 | 0
3433 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14068 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , Zone-I under RAMNACHANDPUR ground water based water supply scheme under Block_ Nowda Dist. - Murshidabad under MEDB, PHE Dte. | 1883/MEDB | 16/06/2023 | 92 | CONCORD ENGINEERING | 35.22 | 0 | 0 | 0
3434 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14068 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-I Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 40/BD-I | 20/04/2023 | 10 | TECHVISION | 2.81 | 2.81 | 100 | 100
3435 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14068 | Augmentation | Material Requisition To Resource Division | 196/BD-I/18 | 09/02/2024 | 0 | Resource Division | 7.99 | 0 | 0 | 0
3436 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14068 | Augmentation | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of Ramnachandpur Zone-I" ground water supply scheme in NAWDA Block, under Berhampore Division-I, P.H.E Dte(Capacity-98.00 Cum/hr.) Type-1: Fully Gravity System with RG Filter | 1037/BD-I | 28/06/2024 | 365 | ACQUA CONSTRUCTION CONSORTIUM | 234.01 | 0 | 0 | 0
3437 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14068 | Augmentation | Augmentation of Ramnachandpur Zone_I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I, PHE Dte. | 1655/BD-I | 13/03/2023 | 752 | SOFIQUL ISLAM | 371.52 | 316.8 | 85.68 | 95
3438 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14068 | Augmentation | Improvement of OHR (550 Cum) Extension of Boundary Wall & Service Road for Augmentation of Ramnachandpur Zone-I PWSS within Nawda block under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad. | 973/BD-I | 18/06/2024 | 213 | KAMIRUL SK AND CO. | 16.56 | 4.09 | 20.94 | 100
3439 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. , SM/14922 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BALI ZONE-II Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1596/BD-I | 28/02/2023 | 10 | TECHVISION | 2.81 | 2.81 | 100 | 0
3440 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. , SM/14922 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BALI ZONE-II Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 32/BD-I | 19/04/2023 | 10 | TECHVISION | 2.81 | 2.81 | 100 | 100
3441 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. , SM/14922 | Augmentation | Material Requisition To Resource Division | 1156/BD-I | 05/12/2023 | 0 | Resource Division | 47.43 | 0 | 0 | 0
3442 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. , SM/14922 | Augmentation | Construction Pump House Cum Chlorine Room at Head Work site of BALI ZONE-II Water Supply Scheme under Jal Jevan Mission within Nawda Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | 148/BD-I | 29/01/2025 | 60 | SUPRIYA DEY | 8.77 | 0 | 0 | 60
3443 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. , SM/14922 | Augmentation | Augmentation of Bali Zone_II Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I,PHE.Dte. [2nd Call for WBPHED/EE/BD-I/NIeT-27 of 2022 ¿ 2023(sl-19)] | 376/BD-I | 28/06/2023 | 180 | S.D PROJECT | 385.38 | 310.84 | 75.45 | 43
3444 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. , SM/14922 | Augmentation | Relaying of different dia upvc distribution system inbetween unlaid portion Shyamnagar, kamrapara, Dargatala, Mathpara, Haldarpara, Munsipara and near Shyamnagar H.S. and Shymnagar Bridge of Bali Zone-II Water supply scheme under JJM under Berhampore Division-I, PHE Dte. | 442/BD-I | 15/03/2024 | 30 | SUJAUDDIN SHAIKH | 4.59 | 4.37 | 100 | 100
3445 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BALI ZONE-II PIPED WATER SUPPLY SCHEME. , SM/14922 | Augmentation | Improvement of OHR (550 Cum) Extension of Boundary Wall & Service Road for Augmentation of Bali Zone-II PWSS within Nawda block under Jal Jeevan Mission under Berhampore Division-I PHE Dte. in the district Murshidabad | 1179/BD-I | 25/07/2024 | 238 | SUMAN CHOWDHURY | 19.54 | 0 | 0 | 90
3446 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Saktipur (ZONE- I ) Ground water Based PWSS, Block-Beldanga-II , Dist- Murshidabad under MEDB, PHE Dte. , SM/15294 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Saktipur (ZONE- I ) Ground water Based PWSS, Block-Beldanga-II , Dist- Murshidabad under MEDB, PHE Dte. | 4349/MEDB | 29/12/2023 | 91 | A. K. INDUSTRIES | 6.44 | 0 | 0 | 0
3447 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . , SM/14738 | Augmentation | Material Requisition To Resource Division | 61/BD-1/2 | 27/04/2023 | 0 | Resource Division | 29.7 | 0 | 0 | 0
3448 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . , SM/14738 | Augmentation | LOCHANPUR ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1175/BD-I | 25/07/2024 | 60 | DEBJIT DAS | 21.57 | 0 | 0 | 0
3449 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . , SM/14738 | Augmentation | Construction of Service Road for approach and Pump House at Augmentation of Lochanpur Zone-I PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | 1125/BD-I | 11/07/2024 | 60 | KHANDAKAR CONSTRUCTION | 8.19 | 0 | 0 | 0
3450 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . , SM/14738 | Augmentation | NEW SERVICE CONNECTION AT LOCHANPUR Z1 PH 1 ID 304268981 |  | 26/11/2024 | 0 | WBSEDCL | 16.76 | 0 | 0 | 0
3451 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . , SM/14738 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Lochanpur Zone-I ground water supply scheme in Raninagar-I Block Dist_Murshidabad under MEDB PHE Dte. | 1131/MEDB | 13/05/2025 | 92 | HARA PROSAD DAS | 39.97 | 0 | 0 | 0
3452 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . , SM/14738 | Augmentation | Augmentation of Lochanpur Zone-I Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar -I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 696/BD-I | 11/08/2023 | 310 | ARABINDA GHOSH | 323.45 | 69.64 | 21.53 | 10
3453 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . , SM/14738 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Lochanpur Zone-I ground water supply scheme in Raninagar-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | 950/BD-I | 18/07/2025 | 300 | HARBAUER INDIA (P) LTD. | 122.79 | 0 | 0 | 0
3454 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- I . , SM/14738 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for LOCHANPUR ZONE-I Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte | 1762/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.6 | 2.6 | 100 | 100
3455 | MURSHIDABAD | Murshidabad Division | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS , SM/14503 | New | Material Requisition To Resource Division | 1230/MURD/17 | 04/05/2023 | 0 | Resource Division | 2.89 | 0 | 0 | 0
3456 | MURSHIDABAD | Berhampore Mechanical | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS , SM/14503 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for NEWLY SUNK TUBE WELL in connection to Accommodate FHTC at Pump House No.-I & II under GOURI NAGAR ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | 4341/MEDB | 29/12/2023 | 611 | M/S S. S. ENTERPRISE (DOMKAL) | 18.46 | 0 | 0 | 40
3457 | MURSHIDABAD | Berhampore Mechanical | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS , SM/14503 | New | NEW SERVICE CONNECTION AT PWSS GOURINAGAR PH2 ID 304247757 | 318/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 6.9 | 0 | 0 | 0
3458 | MURSHIDABAD | Berhampore Mechanical | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS , SM/14503 | New | NEW SERVICE CONNECTION AT PWSS PH1 GOURINAGAR ID 304248173 | 317/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 8.13 | 0 | 0 | 0
3459 | MURSHIDABAD | Murshidabad Division | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS , SM/14503 | New | Formal work order for GOURI NAGAR & adjoining mouzas PWSS to accommodate FHTC under Jal Jiban Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE. Dte. | 607/MURD | 02/03/2023 | 1255 | ABDUL JABBAR DEWAN | 218.13 | 138.54 | 63.51 | 65
3460 | MURSHIDABAD | Murshidabad Division | GOURI NAGAR AND IT'S ADJOINING MOUJAS PWSS , SM/14503 | New | Allied works for Construction of Approach road, Guard Wall and Laying UPVC Pipeline & Soil Investigation Study of Gourinagar Water Supply Scheme in Burwan Block of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. | 3144/MURD | 03/12/2024 | 180 | ABDUL JABBAR DEWAN | 27.17 | 0 | 0 | 60
3461 | MURSHIDABAD | Murshidabad Division | KOGRAM AND ADJOINING MOUJAS PWSS , SM/14507 | New | Material Requisition To Resource Division | 1219/MURD/17 | 03/05/2023 | 0 | Resource Division | 14.53 | 0 | 0 | 0
3462 | MURSHIDABAD | Berhampore Mechanical | KOGRAM AND ADJOINING MOUJAS PWSS , SM/14507 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under KOGRAM ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | 4303/MEDB | 29/12/2023 | 91 | DAS ENTERPRISE (CHOA) | 23.66 | 18.39 | 77.73 | 60
3463 | MURSHIDABAD | Berhampore Mechanical | KOGRAM AND ADJOINING MOUJAS PWSS , SM/14507 | New | Kogram PH-1 Application No- 3004543655 | 239/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 5.47 | 0 | 0 | 0
3464 | MURSHIDABAD | Berhampore Mechanical | KOGRAM AND ADJOINING MOUJAS PWSS , SM/14507 | New | Kogram PH-2 Application No-3004543754 | 238/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 4.36 | 0 | 0 | 0
3465 | MURSHIDABAD | Murshidabad Division | KOGRAM AND ADJOINING MOUJAS PWSS , SM/14507 | New | KOGRAM & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- BURWAN of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | 983/MURD | 10/04/2023 | 631 | HIRANMAY GHOSH | 599.93 | 187.56 | 31.26 | 50
3466 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Bharatpur Zone-IB Water Supply Scheme Block - Bharatpur - I , Dist- Murshidabad. , SM/16247 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IB under Bharatpur ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | 3681/MEDB | 03/11/2023 | 92 | CONCORD ENGINEERING | 22.78 | 0 | 0 | 0
3467 | MURSHIDABAD | Murshidabad Division | Augmentation of Bharatpur Zone-IB Water Supply Scheme Block - Bharatpur - I , Dist- Murshidabad. , SM/16247 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bharatpur Zone-IB Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur - I Block under Murshidabad Division, P.H. Engineering Dte. | 1768/MURD | 06/07/2023 | 21 | SUJIT KUMAR SAHA | 23.58 | 0 | 0 | 0
3468 | MURSHIDABAD | Murshidabad Division | Augmentation of Bharatpur Zone-IB Water Supply Scheme Block - Bharatpur - I , Dist- Murshidabad. , SM/16247 | Augmentation | Augmentation of BHARATPUR (ZONE - I B) PWSS under Jal Jeevan Mission of Bharatpur Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. | 2070/MURD | 28/07/2023 | 300 | BERHAMPORE CONSTRUCTION SYNDICATE PVT. LTD. | 478.38 | 0 | 0 | 0
3469 | MURSHIDABAD | Murshidabad Division | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/15839 | Augmentation | Material Requisition To Resource Division | 1167/MURD/9 | 28/04/2023 | 0 | Resource Division | 5.26 | 0 | 0 | 0
3470 | MURSHIDABAD | Murshidabad Division | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/15839 | Augmentation | Providing FHTC to 1200 nos household and OHR Repair of 45 cum capacity for Augmentation of Giria Zone -I and Zone-II Piped water supply scheme in Raghunathganj-II Block under Murshidabad Division, PHE.Dte . | 2090/MURD | 23/07/2024 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 60.76 | 0 | 0 | 0
3471 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/15839 | Augmentation | EW SERVICE CONNECTION AT GIRIA Z1 PH3 ID 304512470 | 304/WBSEDL-JJM | 06/12/2024 | 0 | WBSEDCL | 3.53 | 0 | 0 | 0
3472 | MURSHIDABAD | Murshidabad Division | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/15839 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Raghunathganj-II of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Giriya Kismat Water supply Scheme, Jotsundar Water Supply Scheme, Giria Water Supply Scheme Zone-I & II. | 2912/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 12.39 | 2.52 | 72.58 | 100
3473 | MURSHIDABAD | Murshidabad Division | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/15839 | Augmentation | Augmentation of Ground Water Based Giria Zone-I PWS accommodate FHTC of 2614 nos household, Laying Distribution System, Laying Rising Main,Construction of Pump House (4.10m x 3.5m with sanitary and Water Supply Arrangement) 1no, Construction of Boundary Wall of length 48 m, Repairing & maintenance of 2(two) nos Pump House ,existing boundary wall and Overhauling of R.C.C. elevated reservoir of 450 Cum capacity of staging hight 20 mtr. in Raghunathganj - II Block within Murshidabad District under Murshidabad Division, PHE Dte. | 3320/MURD | 22/10/2023 | 964 | S.B. ASSOCIATES | 245.83 | 30.01 | 12.21 | 75
3474 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/15839 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Source Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. P.H.E. Dte. under MEDB, PHE Dte. | 340/MEDB | 10/02/2025 | 89 | M/S SAMRIDDHI ENTERPRISE | 36.36 | 0 | 0 | 0
3475 | MURSHIDABAD | Murshidabad Division | Augmentation of Giria Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/15839 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jaykrishnapur Zone-II & Giria Zone - I Water Supply Scheme under Jangipur Sub-Division under Murshidabad Division, P.H. Engineering Dte | 1767/MURD | 06/07/2023 | 544 | R.K. DRILLING SERVICES | 23.58 | 7.74 | 38.58 | 100
3476 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Fatepur ( 315310 ) of Fatepur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District ( PART-I ) , SM/07926 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Fatepur (Village code 315310) under Fatepur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723484 in the District of Murshidabad. | 78/MURD | 08/01/2021 | 60 | RELIABLE ENTERPRISE | 26.51 | 46.96 | 100 | 0
3477 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Fatepur ( 315310 ) of Fatepur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District ( PART-I ) , SM/07926 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at KHIDIRPUR G.P. under Murshidabad Division, P.H.E.Dte. | 335/BSD | 27/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.16 | 4.16 | 100 | 0
3478 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Fatepur ( 315310 ) of Fatepur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District ( PART-I ) , SM/07926 | Retrofitting | Additional Laying and distribution of UPVC pipiline for Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of FATEPUR ( Village Code _315310) under Fatepur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 193/BSD | 28/04/2022 | 30 | S.G CONSTRUCTION , | 4.36 | 0 | 0 | 0
3479 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Fatepur ( 315310 ) of Fatepur under Ground Water Based Water Supply Scheme for arsenic affected areas of Berhampore Block of Murshidabad District ( PART-I ) , SM/07926 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | 297/BSD | 13/08/2021 | 30 | IMAGIN | 4.34 | 8.68 | 200 | 0
3480 | MURSHIDABAD | Berhampore Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAK KATALIA , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. , SM/16429 | New | Mini Piped Water Supply Scheme for Chak Kathalia (Part-C) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 184/BD-I | 17/05/2023 | 90 | GOUTAM KUMAR CHAUDHURI | 28.32 | 0 | 0 | 0
3481 | MURSHIDABAD | Berhampore Mechanical | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAK KATALIA , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. , SM/16429 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Katalia village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3036/MEDB | 02/08/2023 | 92 | SREE RADHA ELECTRICAL | 6.32 | 0 | 0 | 0
3482 | MURSHIDABAD | Berhampore Mechanical | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAK KATALIA , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. , SM/16429 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chak Katalia village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 588/MEDB | 31/01/2024 | 90 | JOGMAYA ENGINEERING | 6.3 | 0 | 0 | 0
3483 | MURSHIDABAD | Berhampore Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAK KATALIA , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. , SM/16429 | New | Mini Piped Water Supply Scheme for Chak Kathalia (Part-B) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 183/BD-I | 17/05/2023 | 989 | PRADIP DAS | 28.45 | 0 | 0 | 60
3484 | MURSHIDABAD | Berhampore Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAK KATALIA , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. , SM/16429 | New | Mini Piped Water Supply Scheme for Chak Kathalia (Part-A) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 182/BD-I | 17/05/2023 | 1000 | ANKITA ENTERPRISE-GOPEJAN(NATHPARA) | 28.45 | 0 | 0 | 82
3485 | MURSHIDABAD | Berhampore Mechanical | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAR SUJAPUR , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. , SM/16430 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Sujapur village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3039/MEDB | 02/08/2023 | 92 | MERCURY ENGINEERING CO | 6.33 | 0 | 0 | 0
3486 | MURSHIDABAD | Berhampore Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAR SUJAPUR , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. , SM/16430 | New | Mini Piped Water Supply Scheme for Char Sujapur (Part-B) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 166/BD-I | 16/05/2023 | 90 | DEBJYOTI MUKHERJEE | 27.91 | 0 | 0 | 0
3487 | MURSHIDABAD | Berhampore Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - CHAR SUJAPUR , BLOCK- BERHAMPORE ,DISTRICT - MURSHIDABAD. , SM/16430 | New | Mini Piped Water Supply Scheme for Char Sujapur (Part-A) under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 165/BD-I | 16/05/2023 | 822 | MAHATO ENTERPRISE | 28.44 | 0 | 0 | 80
3488 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-I, Block- Berhampore, District- Murshidabad. , SM/16432 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Sujapur Zone-I village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3040/MEDB | 02/08/2023 | 92 | M/S. SUPER CONSTRUCTION | 6.32 | 0 | 0 | 0
3489 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-I, Block- Berhampore, District- Murshidabad. , SM/16432 | New | Mini Piped Water Supply Scheme for Char Sujapur Zone-I under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 145/BD-I | 15/05/2023 | 822 | RAWSHAN FOUNDATION | 30.49 | 0 | 0 | 80
3490 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Chandabag, Block- Murshidabad-Jiagunj, District- Murshidabad. , SM/16435 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chandabag village, Block:- Murshidabad - Jiaganj under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3035 | 02/08/2023 | 92 | SREE RADHA ELECTRICAL | 6.32 | 0 | 0 | 0
3491 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Chandabag, Block- Murshidabad-Jiagunj, District- Murshidabad. , SM/16435 | New | Mini Piped Water Supply Scheme for Chandabag under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 162/BD-I | 16/05/2023 | 90 | PRAVAT KUMAR GHOSH | 24.63 | 0 | 0 | 0
3492 | MURSHIDABAD | Murshidabad Division | Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/16544 | Augmentation | Material Requisition To Resource Division | 1230/MURD/05 | 04/05/2023 | 0 | Resource Division | 46.51 | 0 | 0 | 0
3493 | MURSHIDABAD | Murshidabad Division | Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/16544 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Raghunathganj-II of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Giriya Kismat Water supply Scheme, Jotsundar Water Supply Scheme, Giria Water Supply Scheme Zone-I & II. | 2912/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 12.39 | 2.48 | 44.31 | 100
3494 | MURSHIDABAD | Murshidabad Division | Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/16544 | Augmentation | Augmentation of Ground Water Based GIRIA KISMAT PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | 951/MURD | 05/04/2023 | 1002 | SUNRISE CONSTRUCTION | 354.38 | 0 | 0 | 0
3495 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/16544 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Giria Kismat Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. under MEDB, PHE Dte." | 383/MEDB | 12/02/2025 | 89 | SUNIL RABIDAS | 34.09 | 0 | 0 | 0
3496 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-III ) PIPED WATER SUPPLY SCHEME , SM/16555 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Raghunathganj-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-C | 1216/MURD | 10/05/2022 | 30 | ALLIANCE INDIA | 25.34 | 3.38 | 100 | 100
3497 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-III ) PIPED WATER SUPPLY SCHEME , SM/16555 | Augmentation | Material Requisition To Resource Division | 1167/MURD/40 | 28/04/2023 | 0 | Resource Division | 3.79 | 0 | 0 | 0
3498 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Rejuvenation of Arjunpur (Zone-III ) PIPED WATER SUPPLY SCHEME , SM/16555 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,ZONE-III under ARJUNPUR ground water based water supply scheme under Block_ FARAKKA Dist. - Murshidabad under MEDB, PHE Dte. | 4307/MEDB | 29/12/2023 | 91 | M/S SAMRIDDHI ENTERPRISE | 34.16 | 25.37 | 74.27 | 60
3499 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Rejuvenation of Arjunpur (Zone-III ) PIPED WATER SUPPLY SCHEME , SM/16555 | Augmentation | NEW SERVICE CONNECTION AT ARJUNPUR Z3 PH1 ID 304390315 |  | 27/11/2024 | 0 | WBSEDCL | 5.66 | 0 | 0 | 0
3500 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejuvenation of Arjunpur (Zone-III ) PIPED WATER SUPPLY SCHEME , SM/16555 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 300 & 900 cum), Sinking of Tube Well and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Arjunpur Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | 3177/MURD | 11/10/2023 | 730 | M/S. CHAKRABORTY & COMPANY | 2041.06 | 0 | 0 | 35
3501 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-I, Block- Berhampore, District- Murshidabad. , SM/16044 | New | Mini Piped Water Supply Scheme for Char Hallalpur Zone-I under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 169/BD-I | 16/05/2023 | 90 | SAMRAT MAZUMDAR | 30.5 | 0 | 0 | 0
3502 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-I, Block- Berhampore, District- Murshidabad. , SM/16044 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Halalpur Zone-I village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3074/MEDB | 02/08/2023 | 92 | SURAKSHA | 6.3 | 0 | 0 | 0
3503 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-II, Block- Berhampore, District- Murshidabad. , SM/16046 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at CharHalalpur - Zone-II village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3038/MEDB | 02/08/2023 | 92 | MERCURY ENGINEERING CO | 6.33 | 0 | 0 | 0
3504 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-II, Block- Berhampore, District- Murshidabad. , SM/16046 | New | Mini Piped Water Supply Scheme for Char Hallalpur Zone-II under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 170/BD-I | 16/05/2023 | 90 | M/S. MONDAL ENTERPRISE 12/6/1, OLD POLICE LINE ROAD, GORABAZAR | 30.49 | 0 | 0 | 0
3505 | MURSHIDABAD | Murshidabad Division | Augmentation of JOT KAMAL Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/16178 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 7.5 | 100 | 100
3506 | MURSHIDABAD | Murshidabad Division | Augmentation of JOT KAMAL Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/16178 | Augmentation | Material Requisition To Resource Division | 1219/MURD/34 | 03/05/2023 | 0 | Resource Division | 2.92 | 0 | 0 | 0
3507 | MURSHIDABAD | Murshidabad Division | Augmentation of JOT KAMAL Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/16178 | Augmentation | Augmentation of Ground Water Based JOT KAMAL (ZONE-I), JOTKAMAL (Zone-II) & JOTKAMAL (Zone-III) PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | 2643/MURD | 23/08/2023 | 587 | M/S NIRAPADA BHATTACHARJEE | 1194.05 | 0 | 0 | 10
3508 | MURSHIDABAD | Murshidabad Division | Augmentation of JOT KAMAL Zone-I Pipe Water Supply Scheme Block - Raghunathganj-II District - Murshidabad. , SM/16178 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Jangipur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(83 Nos.) | 2636/MURD | 23/09/2024 | 20 | KUNTAL SAHA | 9.28 | 0 | 0 | 100
3509 | MURSHIDABAD | Murshidabad Division | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/16283 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 5.67 | 100 | 1
3510 | MURSHIDABAD | Murshidabad Division | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/16283 | Augmentation | Material Requisition To Resource Division | 1219/MURD/21 | 03/05/2023 | 0 | Resource Division | 104.53 | 0 | 0 | 0
3511 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/16283 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II ,III & IV ,Zone-I under Narsinghpur ground water based water supply scheme under Block_ JALANGI Dist. - Murshidabad under MEDB, PHE Dte. | 4338/MEDB | 29/12/2023 | 91 | B. T. PROJECTS PVT. LTD. | 42.78 | 0 | 0 | 0
3512 | MURSHIDABAD | Murshidabad Division | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/16283 | Augmentation | Augmentation of NARASINGHAPUR ZONE-I PWSS Laying Distribution System, Rising Main Connection of JALANGI Block, under Murshidabad Division PHE. Dte. PART_A | 3219/MURD | 13/10/2023 | 180 | M/S UNIVERSAL TRADING | 273.87 | 190.22 | 69.46 | 20
3513 | MURSHIDABAD | Murshidabad Division | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/16283 | Augmentation | Construction of Pump House, Boundary wall & Providing Functional Household Tap Connection for Augmentation of Narasinghapur Zone-I PWSS in Jalangi Block , Islampur Sub-Division under Murshidabad Division , PHE. Dte. Part-B | 3330/MURD | 23/10/2023 | 120 | TRIYA CONSTRUCTION | 105.54 | 27.09 | 25.67 | 30
3514 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/16283 | Augmentation | SHIFTING OF A PORTION OF DHANIRAMPUR 11 KV HTOH LINE ALONG WITH 25KVA DTR FOR NARASINGHAPUR PWSS ID 860315776 |  | 08/11/2024 | 0 | WBSEDCL | 3.83 | 0 | 0 | 0
3515 | MURSHIDABAD | Murshidabad Division | Augmentation of Narsinghpur Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/16283 | Augmentation | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Juginda, Kupila and Narsinghpur Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | 1193/MURD | 10/05/2022 | 1360 | MAMATA USHA ENTERPRISE | 32.62 | 9.38 | 57.53 | 20
3516 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone-II, Block- Lalgola, District- Murshidabad. , SM/16211 | New | Mini Piped Water Supply Scheme for Durgapur zone-II under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 149/BD-I | 15/05/2023 | 90 | DHRITIPALI | 30.23 | 0 | 0 | 0
3517 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Durgapur Zone-II, Block- Lalgola, District- Murshidabad. , SM/16211 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Durgapur Zone-II village, Block:- Lalgola under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3612/MEDB | 03/11/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 6.3 | 0 | 0 | 0
3518 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 314641 ) & Bhaduria Para ( 314643 ) of Faridpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad Di , SM/07919 | Retrofitting | Extension of Distribution UPVC pipeline for Providing Functional Household Tap connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command areas of village of Bhaduriapara (Village Code-314643) under Faridpur Ground water based water suply scheme for Arsenic affected areas of Jalangi Block, under Murshidabad Division, P.H.E. Dte. (scheme ID- 0005184121) | 766/MURD | 22/03/2022 | 30 | M/S. SINHA & SONS | 36.38 | 36.07 | 100 | 0
3519 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 314641 ) & Bhaduria Para ( 314643 ) of Faridpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad Di , SM/07919 | Retrofitting | Preparation of D.P.R(Consultancy work) inconnection with the Functional Household Connection of different existing PWSS(Faridpur Zone-II PWSS Scheme,Block-Jalangi)to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 369 of 21-22 by EE MSD, and Scheme Code: 7919 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 7.25 | 0 | 0 | 0
3520 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 314641 ) & Bhaduria Para ( 314643 ) of Faridpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad Di , SM/07919 | Retrofitting | Preparation of D.P.R(Consultancy work) in connection with the Functional Household Connection of different existing PWSS(Faridpur Zone-I PWSS Scheme,Block-Jalangi) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. Tender no - 368 of 21-22 by EE MSD, and Scheme Code: 7919 | 13-MSD/22-23 | 14/04/2022 | 0 | SRIJAN ECOLOGICAL UPLIFTMENT PVT.LTD. | 5.36 | 0 | 0 | 0
3521 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 314641 ) & Bhaduria Para ( 314643 ) of Faridpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad Di , SM/07919 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION)' from existing Distribution system within the Command area of village FARIDPUR (Village Code 314641) under FARIDPUR Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 246 of 21-22 by EE MURD | 395-MSD/21-22 | 23/03/2022 | 0 | NATIONAL CONSTRUCTION (PROP:NIZAMUL BISWAS) | 11.79 | 0 | 0 | 0
3522 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 314641 ) & Bhaduria Para ( 314643 ) of Faridpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad Di , SM/07919 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bhaduria Para( Village Code -314643) under Faridpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184121) | 655/MURD | 18/02/2021 | 60 | ASHOK KUMAR SINHA | 81.32 | 36.62 | 45.04 | 0
3523 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Faridpur ( 314641 ) & Bhaduria Para ( 314643 ) of Faridpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block of Murshidabad Di , SM/07919 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Faridpur ( Village Code -314641) under Faridpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184121) | 2349/MURD | 05/08/2021 | 60 | NATIONAL CONSTRUCTION (PROP:NIZAMUL BISWAS) | 87.31 | 71.82 | 82.26 | 1
3524 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADUPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION PHE.DTE , SM/10013 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (JADUPUR PWSS Scheme, Block - Berhampore) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3268/MURD | 05/10/2021 | 60 | RADIANT | 2.28 | 2.28 | 100 | 1
3525 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADUPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION PHE.DTE , SM/10013 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jadupur Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3068/MURD | 17/11/2022 | 30 | NADIA TUBEWELLS | 10.6 | 0 | 0 | 0
3526 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADUPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION PHE.DTE , SM/10013 | Augmentation | Relaying of pipe line at Chandpara village under command area of JADUPUR Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | 119/BSD | 19/02/2021 | 15 | M/S.S.S. ENTERPRISE | 4.85 | 4.85 | 100 | 0
3527 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADUPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION PHE.DTE , SM/10013 | Augmentation | Material Requisition To Resource Division | 1167/MURD/2 | 28/04/2023 | 0 | Resource Division | 3.11 | 0 | 0 | 0
3528 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADUPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION PHE.DTE , SM/10013 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.9 | 100 | 80
3529 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADUPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION PHE.DTE , SM/10013 | Augmentation | Material Requisition To Resource Division | 1811/MURD/01 | 20/06/2024 | 0 | Resource Division | 4.49 | 0 | 0 | 0
3530 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADUPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION PHE.DTE , SM/10013 | Augmentation | Formal work order for Construction 200 Cum OHR, Laying Distribution System & Rising Main in Connection with Augmentation of Jadupur Ground water based Piped water supply scheme within Berhampore Block of Murshidabad District under Murshidabad Division, PHE.Dte | 129/MURD | 16/01/2023 | 1061 | SOFIQUL ISLAM | 135.86 | 8.29 | 6.1 | 5
3531 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED JADUPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION PHE.DTE , SM/10013 | Augmentation | Construction of Boundary wall at JADUPUR Water Supply Scheme, Rangamati Chandpara G.P under Berhampore Sub-Division, P.H.E. Dte. in the District Murshidabad. Length-55.0Mtr. | 3171/MURD | 16/12/2020 | 30 | SOM CONSTRUCTION AGENCY | 4.98 | 4.98 | 100 | 100
3532 | MURSHIDABAD | Berhampore Division I | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Kuchidanga, Block- Lalgola, District- Murshidabad. , SM/16503 | New | Mini Piped Water Supply Scheme for Kuchiadanga under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 152/BD-I | 15/05/2023 | 90 | ANUPA ENTERPRISE | 22.59 | 0 | 0 | 0
3533 | MURSHIDABAD | Berhampore Mechanical | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Kuchidanga, Block- Lalgola, District- Murshidabad. , SM/16503 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Kuchidanga village, Block:- Lalgola under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3614/MEDB | 03/11/2023 | 92 | AVINABA ENGINEERING CONCERN | 6.26 | 0 | 0 | 0
3534 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- II B Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16416 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
3535 | MURSHIDABAD | Murshidabad Division | BAJITPUR PIPED WATER SUPPLY SCHEME. , SM/16216 | New | Material Requisition To Resource Division | 1230/MURD/18 | 04/05/2023 | 0 | Resource Division | 29.58 | 0 | 0 | 0
3536 | MURSHIDABAD | Murshidabad Division | BAJITPUR PIPED WATER SUPPLY SCHEME. , SM/16216 | New | Material Requisition To Resource Division | 495/MURD/04 | 15/02/2024 | 0 | Resource Division | 5.54 | 0 | 0 | 0
3537 | MURSHIDABAD | Murshidabad Division | BAJITPUR PIPED WATER SUPPLY SCHEME. , SM/16216 | New | BAJITPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Raghunathganj-II Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | 959/MURD | 05/04/2023 | 850 | CHABDAR ALI TRADERS | 233.79 | 74.67 | 31.94 | 85
3538 | MURSHIDABAD | Berhampore Mechanical | BAJITPUR PIPED WATER SUPPLY SCHEME. , SM/16216 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for BAJITPUR PIPED WATER SUPPLY SCHEME. District - Murshidabad. under MEDB, PHE Dte. | 337/MEDB | 10/02/2025 | 323 | M/S SAJAHAN CHOWDHURY | 21.38 | 0 | 0 | 60
3539 | MURSHIDABAD | Murshidabad Division | BAJITPUR PIPED WATER SUPPLY SCHEME. , SM/16216 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 3.11 | 100 | 100
3540 | MURSHIDABAD | Murshidabad Division | BAJITPUR PIPED WATER SUPPLY SCHEME. , SM/16216 | New | Sinking of 2NOS. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bajitpur Water Supply Scheme at Raghunathganj-II Block of Jangipur Sub Division under Murshidabad Division, P.H.Engineering Dte. | 2132/MURD | 26/07/2024 | 218 | TARIKUL SK | 20.52 | 0 | 0 | 100
3541 | MURSHIDABAD | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16376 | New | Material Requisition To Resource Division | 61/BD-1/20 | 27/04/2023 | 0 | Resource Division | 15.38 | 0 | 0 | 0
3542 | MURSHIDABAD | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16376 | New | Material Requisition To Resource Division | 2096/BD-I/7 | 25/11/2024 | 0 | Resource Division | 8.46 | 0 | 0 | 0
3543 | MURSHIDABAD | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16376 | New | KATALIA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 221/BD-I | 17/05/2023 | 865 | NURUL HASAN BISWAS | 52.76 | 0 | 0 | 66
3544 | MURSHIDABAD | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16376 | New | KATALIA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BERHAMPORE Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 685/BD-I | 10/08/2023 | 1113 | C.X.CONSTRUCTION & CO. | 259.02 | 13.63 | 5.26 | 30
3545 | MURSHIDABAD | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16376 | New | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Katalia" ground water supply scheme in Berhampore Block, under Berhampore Division-I, P.H.E Dte. (Capacity-36 Cum/hr.) Type-4- Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing Unit | 1000/BD-I | 20/06/2024 | 365 | ACQUA CONSTRUCTION CONSORTIUM | 147.9 | 0 | 0 | 0
3546 | MURSHIDABAD | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16376 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KATALIA Water Supply Scheme(TW-II) within Berhampore Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | 15/BD-I | 06/01/2025 | 85 | SARKAR WATER SUPPLY AGENCY | 9 | 0 | 0 | 100
3547 | MURSHIDABAD | Berhampore Division I | KATALIA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16376 | New | Bored Cast-in-situ_ M30 _ grade 500 mm dia. R.C.C. pile for Construction of OHR at Head Work site of KATALIA Ground Piped Water Supply Scheme under Jal Jeevan Mission within Berhampore Block under Berhampore Division-I, PHE.Dte. in the district of Murshidabad. | 278/BD-I | 12/02/2025 | 88 | C.X.CONSTRUCTION & CO. | 30.71 | 0 | 0 | 100
3548 | MURSHIDABAD | Berhampore Division I | KULGACHI AND ITS ADJOINING MOUJAS PWSS , SM/16302 | New | Material Requisition To Resource Division | 61/BD-1/29 | 27/04/2023 | 0 | Resource Division | 12.73 | 0 | 0 | 0
3549 | MURSHIDABAD | Berhampore Mechanical | KULGACHI AND ITS ADJOINING MOUJAS PWSS , SM/16302 | New | KULGACHI PWSS | 346/WBSEDCL-JJM | 15/02/2024 | 0 | WBSEDCL | 3.25 | 0 | 0 | 0
3550 | MURSHIDABAD | Berhampore Division I | KULGACHI AND ITS ADJOINING MOUJAS PWSS , SM/16302 | New | KULGACHI PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 212/BD-I | 17/05/2023 | 630 | NATIONAL CONSTRUCTION | 36.84 | 19.95 | 54.16 | 85
3551 | MURSHIDABAD | Murshidabad Division | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16393 | New | Material Requisition To Resource Division | 1129/MURD/3 | 25/04/2023 | 0 | Resource Division | 15.8 | 0 | 0 | 0
3552 | MURSHIDABAD | Berhampore Mechanical | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16393 | New | Service connection charge for Parbbatipur SM/ 16393 | 200/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 19.26 | 0 | 0 | 0
3553 | MURSHIDABAD | Murshidabad Division | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16393 | New | Sinking of 01 (One) Nos of 250mm x 150 mm dia tube well i.e. TW- III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PARBATIPUR AND ADJOINING MOUJAS Water Supply Scheme at 3rd Site site at KANDI Block under Murshidabad Division, P.H. Engineering Dte | 2821/MURD | 07/09/2023 | 421 | INDRAJIT MAZUMDAR | 9.22 | 0 | 0 | 100
3554 | MURSHIDABAD | Murshidabad Division | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16393 | New | Allied work for road restoration work liable to be damaged due to pipeline laying at Parbotipur PWSS under Kandi sub-Division, PHE Dte. | 1912/MURD | 02/07/2024 | 60 | DIPAK KUMAR GHOSH | 42.14 | 0 | 0 | 100
3555 | MURSHIDABAD | Murshidabad Division | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16393 | New | Material Requisition To Resource Division | 79/MURD/06 | 09/01/2024 | 0 | Resource Division | 12.55 | 0 | 0 | 0
3556 | MURSHIDABAD | Berhampore Mechanical | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16393 | New | NEW SERVICE CONNECTION AT PARBATIPUR PH II, ID304236105 | 293/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 3.28 | 0 | 0 | 0
3557 | MURSHIDABAD | Murshidabad Division | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16393 | New | Formal work order for PARBATIPUR & adjoining moujas PWSS to accommodate FHTC under Jal Jivan Mission, Block- KANDI of Kandi Sub Division of Murshidabad District under Murshidabad Division, PHE.Dte. | 675/MURD | 09/03/2023 | 1029 | DIPAK KUMAR GHOSH | 467.48 | 264.95 | 56.68 | 25
3558 | MURSHIDABAD | Berhampore Mechanical | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16393 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Parbbatipur ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | 3715/MEDB | 03/11/2023 | 790 | M/S SAJAHAN CHOWDHURY | 23.87 | 19.75 | 82.76 | 15
3559 | MURSHIDABAD | Murshidabad Division | PARBBATIPUR AND IT'S ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16393 | New | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Kandi Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(89 Nos.) | 2635/MURD | 23/09/2024 | 281 | SABSAMAY | 9.85 | 0 | 0 | 80
3560 | MURSHIDABAD | Murshidabad Division | Augmentation of Dakshin Kanda Zone- I B Water Supply Scheme Block -Bharatpur-II, Dist- Murshidabad. , SM/16425 | Augmentation | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at, Dakshinkhanda Zone-IA T.W-II, III, Zone-IB T.W-II, Dakshinkhanda Zone-II T.W- I, II Water Supply Scheme of Bharatpur-II Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 718/MURD | 25/03/2025 | 65 | MAMATA USHA ENTERPRISE | 58.95 | 0 | 0 | 0
3561 | MURSHIDABAD | Berhampore Division I | KESABPUR AND ADJOINING MOUJAS PWSS , SM/16788 | New | Material Requisition To Resource Division | 61/BD-1/31 | 27/04/2023 | 0 | Resource Division | 15.38 | 0 | 0 | 0
3562 | MURSHIDABAD | Berhampore Division I | KESABPUR AND ADJOINING MOUJAS PWSS , SM/16788 | New | Material Requisition To Resource Division | 304/BD-1/2 | 22/02/2024 | 0 | Resource Division | 7.74 | 0 | 0 | 0
3563 | MURSHIDABAD | Berhampore Mechanical | KESABPUR AND ADJOINING MOUJAS PWSS , SM/16788 | New | NEW CONNECTION KESABPUR PH-1 | 425/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 6.22 | 0 | 0 | 0
3564 | MURSHIDABAD | Berhampore Mechanical | KESABPUR AND ADJOINING MOUJAS PWSS , SM/16788 | New | KESABPUR PH-1 |  | 28/02/2024 | 0 | WBSEDCL | 6.22 | 0 | 0 | 0
3565 | MURSHIDABAD | Berhampore Division I | KESABPUR AND ADJOINING MOUJAS PWSS , SM/16788 | New | KESABPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 199/BD-I | 17/05/2023 | 1041 | AZAD ENTERPRISE | 40.95 | 17.52 | 42.79 | 20
3566 | MURSHIDABAD | Berhampore Division I | KESABPUR AND ADJOINING MOUJAS PWSS , SM/16788 | New | KESABPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main , Construction of OHR (Capacity - 200 cum ) under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 664/BD-I | 09/08/2023 | 784 | D.N SARKAR AND SONS | 294.7 | 130.11 | 44.15 | 30
3567 | MURSHIDABAD | Berhampore Mechanical | RANAGRAM AND ADJOINIG MOUJAS PWSS , SM/16052 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Ranagram ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | 3693/MEDB | 03/11/2023 | 92 | B. T. PROJECTS PVT. LTD. | 21.24 | 0 | 0 | 0
3568 | MURSHIDABAD | Murshidabad Division | RANAGRAM AND ADJOINIG MOUJAS PWSS , SM/16052 | New | Material Requisition To Resource Division | 1129/MURD | 25/04/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
3569 | MURSHIDABAD | Murshidabad Division | RANAGRAM AND ADJOINIG MOUJAS PWSS , SM/16052 | New | Providing FHTC Connection to 510 nos household , Laying of Distribution System, Rising Main ,Construction of Boundary Wall and Pump House with sanitary and Water Supply Arrangement & Construction Pump House cum Blower room cum Chlorine room with out sanitary and Water Supply Arrangement RANAGRAM PWSS KANDI Block under Murshidabad Division , PHE. Dte. | 2432/MURD | 08/08/2023 | 180 | R.R. CONSTRUCTION | 70.39 | 29.34 | 41.69 | 30
3570 | MURSHIDABAD | Central Drilling | RANAGRAM AND ADJOINIG MOUJAS PWSS , SM/16052 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 2203/CDD | 01/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 7.59 | 68.36 | 10
3571 | MURSHIDABAD | Berhampore Mechanical | RANAGRAM AND ADJOINIG MOUJAS PWSS , SM/16052 | New | NEW SERVICE CONNECTION AT RANAGRAM PH I, ID304236076 | 271/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 8.48 | 0 | 0 | 0
3572 | MURSHIDABAD | Murshidabad Division | RANAGRAM AND ADJOINIG MOUJAS PWSS , SM/16052 | New | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gaysabad, Kagram, Ranagram, Augmentation of Islampur & Augmentation of Shibnagar Laskarpur Zone - II Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | 661/MURD | 19/03/2025 | 170 | M/S GUHA AND ROY | 35.27 | 0 | 0 | 100
3573 | MURSHIDABAD | Murshidabad Division | BABARPUR AND ADJOINING MOUJAS PWSS , SM/16814 | New | Material Requisition To Resource Division | 1075/MURD/17 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
3574 | MURSHIDABAD | Murshidabad Division | BABARPUR AND ADJOINING MOUJAS PWSS , SM/16814 | New | BABARPUR PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | 1899/MURD | 17/07/2023 | 120 | DIPAYAN DEY | 157.25 | 85.18 | 54.17 | 40
3575 | MURSHIDABAD | Central Drilling | BABARPUR AND ADJOINING MOUJAS PWSS , SM/16814 | New | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | 2203/CDD | 01/03/2024 | 153 | JHARGRAM SPV PRIVATE LIMITED | 111.06 | 0 | 0 | 10
3576 | MURSHIDABAD | Berhampore Mechanical | BABARPUR AND ADJOINING MOUJAS PWSS , SM/16814 | New | NEW CONNECTION AT BABARPUR PH-I | 430/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 4.31 | 0 | 0 | 0
3577 | MURSHIDABAD | Berhampore Mechanical | BABARPUR AND ADJOINING MOUJAS PWSS , SM/16814 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Ground Water Based Piped Water Supply Scheme for BABARPUR AND ADJOINING MOUJAS PWSS Block Burwan of Murshidabad District under MEDB, PHE Dte. | 330/MEDB | 10/02/2025 | 89 | M/S G.P. ENTERPRISE | 21.38 | 0 | 0 | 0
3578 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. , SM/16764 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 3.06 | 86.22 | 76
3579 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. , SM/16764 | Augmentation | Material Requisition To Resource Division | 1043/MURD/5 | 17/04/2023 | 0 | Resource Division | 0.69 | 0 | 0 | 0
3580 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. , SM/16764 | Augmentation | Laying Distribution System, Rising Main, FHTC, Repairing of Boundary Wall, Pump House & Existing OHR for Augmentation of Bhalkundi Zone-III Water at Supply Scheme in Khargram Block , under Murshidabad Division ,PHE.Dte. | 1077/MURD | 19/04/2023 | 861 | SUJIT KUMAR SAHA | 162.99 | 107.1 | 65.71 | 30
3581 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. , SM/16764 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-III under BHALKUNDI ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | 3850/MEDB | 06/11/2023 | 92 | S. K. ENTERPRISE | 22.8 | 19.42 | 85.19 | 70
3582 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. , SM/16764 | Augmentation | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhalkundi Zone-III & adjoining mouzas Water Supply Scheme at 3rd work site at K h a r g r a m Block under Murshidabad Division, P.H. Engineering Dte. | 1108/MURD | 24/04/2023 | 20 | SARKAR WATER SUPPLY AGENCY | 10.67 | 9.69 | 100 | 100
3583 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- III Block - Khargram , Dist- Murshidabad. , SM/16764 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 0 | 75
3584 | MURSHIDABAD | Berhampore Mechanical | FATELLAPUR(CT) PIPE WATER SUPPLY SCHEME. , SM/18413 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under FATELLAPUR(CT) ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | 3864MEDB | 07/11/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 23.02 | 0 | 0 | 0
3585 | MURSHIDABAD | Murshidabad Division | FATELLAPUR(CT) PIPE WATER SUPPLY SCHEME. , SM/18413 | New | CHANDMARI , BAHUTALI & FATELLAPUR PWSS to accommodate FHTC under Jal Jeevan Mission, Block- SUTI-I of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | 3176/MURD | 11/10/2023 | 813 | CHAKRABORTY CONSTRUCTION | 2258.18 | 0 | 0 | 10
3586 | MURSHIDABAD | Murshidabad Division | FATELLAPUR(CT) PIPE WATER SUPPLY SCHEME. , SM/18413 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 6.44 | 100 | 100
3587 | MURSHIDABAD | Murshidabad Division | FATELLAPUR(CT) PIPE WATER SUPPLY SCHEME. , SM/18413 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at FATELLAPUR (CT) Water Supply Scheme at Head Work Site, 2nd Site site at Suti-I Block under Murshidabad Division, P.H. Engineering Dte. | 2604/MURD | 22/08/2023 | 741 | MAMATA USHA ENTERPRISE | 18.44 | 4.78 | 25.94 | 30
3588 | MURSHIDABAD | Berhampore Mechanical | BAYRA AND ITS ADJOINING MOUJAS PWSS , SM/18414 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BAYRA ground water based water supply scheme under Block_LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | 4313/MEDB | 29/12/2023 | 91 | HARA PROSAD DAS | 33.24 | 0 | 0 | 0
3589 | MURSHIDABAD | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS , SM/18414 | New | Material Requisition To Resource Division | 304/BD-1/6 | 22/02/2024 | 0 | Resource Division | 24.04 | 0 | 0 | 0
3590 | MURSHIDABAD | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS , SM/18414 | New | Material Requisition To Resource Division | 201/BD-1/26 | 10/02/2024 | 0 | Resource Division | 39.6 | 0 | 0 | 0
3591 | MURSHIDABAD | Berhampore Mechanical | BAYRA AND ITS ADJOINING MOUJAS PWSS , SM/18414 | New | NEW CONNECTION BAYRA PH-1 | 388/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 6.05 | 0 | 0 | 0
3592 | MURSHIDABAD | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS , SM/18414 | New | BAYRA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | 634/BD-I | 04/08/2023 | 1095 | M/S GHOSH AND CO | 383.82 | 0 | 0 | 50
3593 | MURSHIDABAD | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS , SM/18414 | New | BAYRA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | 512/BD-I | 25/07/2023 | 885 | SRIJON ENTERPRISE | 244.14 | 0 | 0 | 30
3594 | MURSHIDABAD | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS , SM/18414 | New | BAYRA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | 620/BD-I | 03/08/2023 | 548 | RAJEN DAS | 55.72 | 11.76 | 21.11 | 50
3595 | MURSHIDABAD | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS , SM/18414 | New | BAYRA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte.. | 1255/BD-I | 22/12/2023 | 445 | MASOOM TRADERS | 61.36 | 4.85 | 7.9 | 30
3596 | MURSHIDABAD | Central Drilling | BAYRA AND ITS ADJOINING MOUJAS PWSS , SM/18414 | New | Continuation for Hiring of Diesel driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Store & Workshop Sub-division, Central Drilling Division, P.H.E. Dte. | 238/S&WSD | 24/12/2024 | 182 | NAGENDRA PATRA | 0.86 | 2.1 | 242.74 | 0
3597 | MURSHIDABAD | Berhampore Division I | BAYRA AND ITS ADJOINING MOUJAS PWSS , SM/18414 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BAYRA PWSS(TW-I&II) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (2 Nos TW) | 438/BD-I | 20/03/2025 | 30 | HARUN ALL RASHID & BROTHERS | 17.97 | 0 | 0 | 0
3598 | MURSHIDABAD | Murshidabad Division | BHATPARA AND ADJOINING MOUJAS , SM/18430 | New | BHATPARA & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte.( Scheme ID -PH222362289S000) | 1989/MURD | 21/07/2023 | 365 | ASTRA | 789.69 | 0 | 0 | 0
3599 | MURSHIDABAD | Murshidabad Division | BHATPARA AND ADJOINING MOUJAS , SM/18430 | New | Material Requisition To Resource Division | 1043/MURD/3 | 17/04/2023 | 0 | Resource Division | 208.28 | 0 | 0 | 0
3600 | MURSHIDABAD | Berhampore Mechanical | BHATPARA AND ADJOINING MOUJAS , SM/18430 | New | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BHATPARA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | 592/MEDB | 31/01/2024 | 90 | HANNAN BUILDERS PVT LTD | 36.83 | 0 | 0 | 0
3601 | MURSHIDABAD | Murshidabad Division | UMARPUR PIPED WATER SUPPLY SCHEME . , SM/18472 | New | Material Requisition To Resource Division | 1230/MURD/24 | 04/05/2023 | 0 | Resource Division | 132.07 | 0 | 0 | 0
3602 | MURSHIDABAD | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . , SM/18472 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under UMARPUR ground water based water supply scheme under Block_ Suti_II Dist. - Murshidabad under MEDB, PHE Dte. | 3852/MEDB | 06/11/2023 | 92 | SURAKSHA | 34.47 | 27.47 | 79.7 | 10
3603 | MURSHIDABAD | Murshidabad Division | UMARPUR PIPED WATER SUPPLY SCHEME . , SM/18472 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UMARPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti-II Block under Murshidabad Division, P.H. Engineering Dte | 2606/MURD | 22/08/2023 | 21 | INDRAJIT MAZUMDAR | 27.66 | 19.1 | 100 | 70
3604 | MURSHIDABAD | Murshidabad Division | UMARPUR PIPED WATER SUPPLY SCHEME . , SM/18472 | New | Material Requisition To Resource Division | 495/MURD/02 | 15/02/2024 | 0 | Resource Division | 31.56 | 0 | 0 | 0
3605 | MURSHIDABAD | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . , SM/18472 | New | NEW CONNECTION UMRAPUR PH-III | 6/WBSEDCL-JJM | 09/04/2024 | 0 | WBSEDCL | 3.49 | 0 | 0 | 0
3606 | MURSHIDABAD | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . , SM/18472 | New | NEW CONNECTION UMRAPUR PH-III |  | 27/03/2024 | 0 | WBSEDCL | 3.49 | 0 | 0 | 0
3607 | MURSHIDABAD | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . , SM/18472 | New | NEW CONNECTION UMRAPUR PH-I | 8/WBSEDCL-JJM | 09/04/2024 | 0 | WBSEDCL | 3.5 | 0 | 0 | 0
3608 | MURSHIDABAD | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . , SM/18472 | New | NEW CONNECTION UMRAPUR PH-II | 7/WBSEDCL-JJM | 09/04/2024 | 0 | WBSEDCL | 3.73 | 0 | 0 | 0
3609 | MURSHIDABAD | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . , SM/18472 | New | NEW CONNECTION UMRAPUR PH-II |  | 27/03/2024 | 0 | WBSEDCL | 3.73 | 0 | 0 | 0
3610 | MURSHIDABAD | Berhampore Mechanical | UMARPUR PIPED WATER SUPPLY SCHEME . , SM/18472 | New | NEW CONNECTION UMRAPUR PH-I |  | 27/03/2024 | 0 | WBSEDCL | 3.5 | 0 | 0 | 0
3611 | MURSHIDABAD | Murshidabad Division | UMARPUR PIPED WATER SUPPLY SCHEME . , SM/18472 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 12.12 | 100 | 100
3612 | MURSHIDABAD | Murshidabad Division | BHABKI PIPED WATER SUPPLY SCHEME. , SM/18555 | New | Material Requisition To Resource Division | 1230/MURD/18 | 04/05/2023 | 0 | Resource Division | 33.71 | 0 | 0 | 0
3613 | MURSHIDABAD | Murshidabad Division | BHABKI PIPED WATER SUPPLY SCHEME. , SM/18555 | New | Material Requisition To Resource Division | 495/MURD/10 | 15/02/2024 | 0 | Resource Division | 13.53 | 0 | 0 | 0
3614 | MURSHIDABAD | Berhampore Mechanical | BHABKI PIPED WATER SUPPLY SCHEME. , SM/18555 | New | BHABKI PH-1 | 334/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 7.72 | 0 | 0 | 0
3615 | MURSHIDABAD | Berhampore Mechanical | BHABKI PIPED WATER SUPPLY SCHEME. , SM/18555 | New | BHABKI PH-II | 335/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 6.55 | 0 | 0 | 0
3616 | MURSHIDABAD | Murshidabad Division | BHABKI PIPED WATER SUPPLY SCHEME. , SM/18555 | New | BHABKI PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- SUTI-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE. Dte. | 2368/MURD | 04/08/2023 | 606 | B.B.R.C. INFRASTRUCTURE PVT. LTD. | 495.36 | 46.14 | 9.31 | 12
3617 | MURSHIDABAD | Murshidabad Division | BHABKI PIPED WATER SUPPLY SCHEME. , SM/18555 | New | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Anup Nagar CT T.W-I, , Bhabki T.W-I,II, Harua T.W-I,II,III Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 761/MURD | 02/04/2025 | 80 | TITUMIR INTERNATIONAL | 70.61 | 0 | 0 | 0
3618 | MURSHIDABAD | Murshidabad Division | BHABKI PIPED WATER SUPPLY SCHEME. , SM/18555 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 6.55 | 100 | 100
3619 | MURSHIDABAD | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS , SM/18579 | New | PAIKPARA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1256/BD-I | 22/12/2023 | 90 | SATELLITE CONSTRUCTION | 67.11 | 0 | 0 | 0
3620 | MURSHIDABAD | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS , SM/18579 | New | Material Requisition To Resource Division | 304/BD-1/3 | 22/02/2024 | 0 | Resource Division | 27.92 | 0 | 0 | 0
3621 | MURSHIDABAD | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS , SM/18579 | New | Material Requisition To Resource Division | 201/BD-1/28 | 10/02/2024 | 0 | Resource Division | 66.86 | 0 | 0 | 0
3622 | MURSHIDABAD | Berhampore Mechanical | PAIKPARA AND ADJOINING MOUJAS PWSS , SM/18579 | New | PAIKPARA PH-1 | 387/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 3.3 | 0 | 0 | 0
3623 | MURSHIDABAD | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS , SM/18579 | New | PAIKPARA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | 631/BD-I | 04/08/2023 | 970 | H.I ENTERPRISE | 440.19 | 188.98 | 42.93 | 17
3624 | MURSHIDABAD | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS , SM/18579 | New | PAIKPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | 633/BD-I | 04/08/2023 | 180 | NIRMAL UDYOG | 116.86 | 25.85 | 22.13 | 20
3625 | MURSHIDABAD | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS , SM/18579 | New | PAIKPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | 632/BD-I | 04/08/2023 | 720 | SRIJON ENTERPRISE | 240.5 | 148.76 | 61.85 | 15
3626 | MURSHIDABAD | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS , SM/18579 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PAIKPARA Water Supply Scheme(2nd & 3rd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 274/BD-I | 11/02/2025 | 30 | NADIA TUBEWELLS | 17.99 | 0 | 0 | 0
3627 | MURSHIDABAD | Berhampore Division I | PAIKPARA AND ADJOINING MOUJAS PWSS , SM/18579 | New | Fabrication and errection of Display Board including vinyl pasting ( 1.80 x 1.20 mtr) of scheme information by using logo and tag line of Jal Jevan Mission at different work sites in the district of Murshidabad under Berhampore Division-I, PHE Dte. (Block :- Nabagram, Murshidabad-Jiaganj & Berhampore) | 1533/BD-I | 19/09/2024 | 7 | SUMAN ENTERPRISE AND SUMAN AQUA | 0.78 | 0 | 0 | 100
3628 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/18663 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under Barabil Raghunathpur ground water based water supply scheme under Block_ Jalangi Dist. - Murshidabad under MEDB, PHE Dte. | 3699/MEDB | 09/08/2023 | 92 | R.N.S. TRADING | 23.69 | 0 | 0 | 0
3629 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/18663 | Augmentation | Material Requisition To Resource Division | 1180/MURD/22 | 29/04/2023 | 0 | Resource Division | 290.13 | 0 | 0 | 0
3630 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/18663 | Augmentation | NEW SERVICE CONNECTION AT BARABIL RAGHUNATHPUR PWSS JL 37 PLOT NO 171 ID 304238695 | 290/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 4.27 | 0 | 0 | 0
3631 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/18663 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 2.1 | 96.87 | 100
3632 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BARA BIL RAGHUNATHPUR (ZONE-II) PIPED WATER SUPPLY SCHEME. , SM/18663 | Augmentation | Augmentation of Barabil Raghunathpur Zone-II PWSS to accommodate Construction of Pump House cum Chlorine Room (5.90m x 4.1m with sanitary and Water Supply Arrangement) 1 no& Pump House (4.10m x 3.5m without sanitary and Water Supply Arrangement) 1no, Construction of Boundary Wall of 200 m, Construction of 400 Cum OHR(1 no) with sub soil investigation , Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works, Repair of Boundary Wall at T/W-I site & T/W-II site &Overhauling of R.C.C. elevated reservoir 450 Cum capacity of staging hight 20 mtr under Jal Jeevan Mission of Jalangi Block, Murshidabad District under Murshidabad Division, PHE.Dte. (Part-B) | 3332/MURD | 23/10/2023 | 766 | ORKID CONSTRUCTION | 217.95 | 63.12 | 28.96 | 50
3633 | MURSHIDABAD | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. , SM/18832 | New | Paschim Purnopara Zone - II PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main under Jal Jeevan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (part C) | 3297/MURD | 20/10/2023 | 180 | M H SUPPLIERS | 305.91 | 0 | 0 | 0
3634 | MURSHIDABAD | Berhampore Mechanical | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. , SM/18832 | New | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-II |  | 13/12/2024 | 0 | WBSEDCL | 10.75 | 0 | 0 | 0
3635 | MURSHIDABAD | Berhampore Mechanical | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. , SM/18832 | New | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-I |  | 13/12/2024 | 0 | WBSEDCL | 7.82 | 0 | 0 | 0
3636 | MURSHIDABAD | Berhampore Mechanical | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. , SM/18832 | New | NEW CONNECTION AT PASCHIM PURNAPARA Z-II PH-III |  | 13/12/2024 | 0 | WBSEDCL | 7.42 | 0 | 0 | 0
3637 | MURSHIDABAD | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. , SM/18832 | New | Paschim Purnopara Zone - II PWSS to accommodate Laying Distribution System & Laying Rising Main under Jal Jeevan Mission of Suti-II Block, Murshidabad District under Murshidabad Division, PHE.Dte. (Part-A) | 3051/MURD | 29/09/2023 | 477 | SOFIQUL ISLAM | 293.57 | 0 | 0 | 0
3638 | MURSHIDABAD | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. , SM/18832 | New | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Purnopara Zone-II T.W-I,II,III Chandnidaha T.W-II, Kohetpur T.W-III, Prosadpur Zone-II T.W-I,II, Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 660/MURD | 19/03/2025 | 90 | JOY GURU ENTERPRISE | 82.5 | 0 | 0 | 0
3639 | MURSHIDABAD | Murshidabad Division | PASCHIM PUNROPARA ZONE-II (CT) PIPED WATER SUPPLY SCHEME. , SM/18832 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 13.19 | 100 | 100
3640 | MURSHIDABAD | Murshidabad Division | SAHAJADPUR (CT) PIPED WATER SUPPLY SCHEME. , SM/18689 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SAHAJADPUR (CT) Water Supply Scheme at Head Work Site, 2nd Site site at Raghunathganj - II Block under Murshidabad Division, P.H. Engineering Dte. | 2796/MURD | 04/09/2023 | 21 | M. R. ENTERPRISE | 18.53 | 0 | 0 | 0
3641 | MURSHIDABAD | Murshidabad Division | SAHAJADPUR (CT) PIPED WATER SUPPLY SCHEME. , SM/18689 | New | Material Requisition To Resource Division | 1230/MURD/31 | 04/05/2023 | 0 | Resource Division | 65.31 | 0 | 0 | 0
3642 | MURSHIDABAD | Murshidabad Division | SAHAJADPUR (CT) PIPED WATER SUPPLY SCHEME. , SM/18689 | New | SAHAJADPUR CT PWSS to accommodate FHTC, Laying Rising Main , OHR as per Departmental type design (Ref :- DRG.No. PC/-I/OHR/17/2012), 4 Nos Pump House, Boundary Wall (5Nos Site) , Approach Road (5Nos Site) & FHTC of SAHAJADPUR CT PWSS at RAGHUNATHGANJ-II Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | 2402/MURD | 07/08/2023 | 365 | NAYLA CONSTRUCTION | 353.57 | 0 | 0 | 0
3643 | MURSHIDABAD | Murshidabad Division | SAHAJADPUR (CT) PIPED WATER SUPPLY SCHEME. , SM/18689 | New | SAHAJADPUR CT PWSS to accommodate FHTC, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Jeevan Mission of Raghunathganj-II Block, Murshidabad District under Jangipur Sub Division, Murshidabad Division ,PHE.Dte | 2401/MURD | 07/08/2023 | 782 | M/S.TAPAS KUMAR CHAKRABORTY | 499.42 | 81.79 | 16.38 | 5
3644 | MURSHIDABAD | Berhampore Mechanical | SAHAJADPUR (CT) PIPED WATER SUPPLY SCHEME. , SM/18689 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II , III ,IV ,V & VI under SAHAJADPUR(CT) ground water based water supply scheme under Block_ Raghunathganj-II Dist. - Murshidabad under MEDB, PHE Dte. | 3863/MEDB | 07/11/2023 | 664 | ORIENTAL ENGINEERING CO. | 67.07 | 0 | 0 | 25
3645 | MURSHIDABAD | Murshidabad Division | SAHAJADPUR (CT) PIPED WATER SUPPLY SCHEME. , SM/18689 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 13.06 | 100 | 100
3646 | MURSHIDABAD | Murshidabad Division | BHARWAN AND ADJOINING MOUJAS PWSS , SM/18452 | New | Material Requisition To Resource Division | 1210/MURD/36 | 02/05/2023 | 0 | Resource Division | 27.73 | 0 | 0 | 0
3647 | MURSHIDABAD | Murshidabad Division | BHARWAN AND ADJOINING MOUJAS PWSS , SM/18452 | New | BHARWAN (Part-A) & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | 1991/MURD | 21/07/2023 | 365 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 389 | 51.98 | 13.36 | 25
3648 | MURSHIDABAD | Murshidabad Division | BHARWAN AND ADJOINING MOUJAS PWSS , SM/18452 | New | BHARWAN (Part-B) & adjoining mouzas PWSS to accommodate Of LDS, and FHTC, under Jal Jeevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | 1990/MURD | 21/07/2023 | 180 | M/S. S. DAS AND ENTERPRISE | 672.95 | 358.69 | 53.3 | 40
3649 | MURSHIDABAD | Berhampore Mechanical | BHARWAN AND ADJOINING MOUJAS PWSS , SM/18452 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under BHARWAN ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | 4066/MEDB | 04/12/2023 | 91 | WEST BENGAL ENGINEERING CO. | 25.76 | 0 | 0 | 0
3650 | MURSHIDABAD | Murshidabad Division | BHARWAN AND ADJOINING MOUJAS PWSS , SM/18452 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.01 | 100 | 80
3651 | MURSHIDABAD | Murshidabad Division | BHARWAN AND ADJOINING MOUJAS PWSS , SM/18452 | New | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 3.96 | 100 | 100
3652 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-I PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18740 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 2.83 | 100 | 100
3653 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-I PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18740 | Augmentation | Material Requisition To Resource Division | 1230/MURD/03 | 04/05/2023 | 0 | Resource Division | 20.39 | 0 | 0 | 0
3654 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BRINDABANPUR ZONE-I PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/18740 | Augmentation | Augmentation of BRINDABANPUR Zone-I Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | 2607/MURD | 22/08/2023 | 741 | J.S. CONSTRUCTION | 288.62 | 121.98 | 42.26 | 10
3655 | MURSHIDABAD | Murshidabad Division | CHARKA PIPE WATER SUPPLY SCHEME. , SM/18465 | New | CHARKA PWSS to accommodate FHTC under Jal Jeevan Mission of Murshidabad District under Raghunathganj-I Block, Jangipur Sub Division of Murshidabad Division, PHE.Dte. | 2058/MURD | 27/07/2023 | 280 | DECON INDIA | 482.22 | 0 | 0 | 0
3656 | MURSHIDABAD | Murshidabad Division | CHARKA PIPE WATER SUPPLY SCHEME. , SM/18465 | New | Material Requisition To Resource Division | 1230/MURD/13 | 04/05/2023 | 0 | Resource Division | 33.69 | 0 | 0 | 0
3657 | MURSHIDABAD | Berhampore Mechanical | CHARKA PIPE WATER SUPPLY SCHEME. , SM/18465 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under CHARKA ground water based water supply scheme under Block_ Raghunathganj-I Dist. - Murshidabad under MEDB, PHE Dte. | 4302/MEDB | 29/12/2023 | 91 | DEBJYOTI BASU | 33.53 | 0 | 0 | 0
3658 | MURSHIDABAD | Murshidabad Division | CHARKA PIPE WATER SUPPLY SCHEME. , SM/18465 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 6.39 | 100 | 100
3659 | MURSHIDABAD | Murshidabad Division | CHARKA PIPE WATER SUPPLY SCHEME. , SM/18465 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at CHARKA Water Supply Scheme at Head Work Site, 2nd Site site at Raghunathganj ¿ I Block under Murshidabad Division, P.H. Engineering Dte. | 2603/MURD | 22/08/2023 | 741 | MAMATA USHA ENTERPRISE | 18.45 | 7.32 | 53.6 | 30
3660 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. , SM/18705 | Augmentation | Material Requisition To Resource Division | 1167/MURD/37 | 28/04/2023 | 0 | Resource Division | 153.51 | 0 | 0 | 0
3661 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. , SM/18705 | Augmentation | Augmentation of BANIAKHALI PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (Part-B) | 2677/MURD | 24/08/2023 | 600 | AEF ENTERPRISE (PROP: MAHBUB AKHTAR) | 222.14 | 41 | 18.46 | 20
3662 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. , SM/18705 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold Tap Connection of 03(Three) nos existing commisioned PWSS Domkol Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Katakopra Water Supply Scheme Zone-I & II, Bhagarpur Ramna Water Supply Scheme,Baniakhali & Its Adjoining Mouzas Water Supply Scheme. (Annexure-II) | 1924/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.09 | 9.06 | 100 | 100
3663 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. , SM/18705 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tubewell i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at P.T RASULPUR (PART - A), Kupila and Baniakhali Water Supply Scheme at DOMKAL Block under Murshidabad Division,P.H. Engineering Dte | 1749/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 20.38 | 100 | 40
3664 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. , SM/18705 | Augmentation | NEW CONNECTION AT BANIAKHALI Z-II PH-II |  | 14/11/2024 | 0 | WBSEDCL | 5.03 | 0 | 0 | 0
3665 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. , SM/18705 | Augmentation | NEW CONNECTION AT BANIAKHALI Z-II PH-I |  | 14/11/2024 | 0 | WBSEDCL | 6.74 | 0 | 0 | 0
3666 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. , SM/18705 | Augmentation | Augmentation BANIAKHALI PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part -A) | 2676/MURD | 24/08/2023 | 1317 | J.S. CONSTRUCTION | 459.33 | 238.37 | 51.9 | 40
3667 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. , SM/18705 | Augmentation | Providing Functional Household Tap Connections ( 665 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Manik Nagar (Village Code -314694) under Domkol Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkol Block under Murshidabad Division P.H.E Dte. | 3458/MURD | 06/11/2023 | 30 | MOLLA ENTERPRISE (REHENA BIBI) | 18.71 | 0 | 0 | 0
3668 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. , SM/18705 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Ground Water Based Baniakhali Piped Water Supply Scheme District - Murshidabad. under MEDB, PHE Dte. | 345/MEDB | 10/02/2025 | 89 | M/S S. S. ENTERPRISE (DOMKAL) | 21.24 | 0 | 0 | 10
3669 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BANIAKHALI PIPED WATER SUPPLY SCHEME. , SM/18705 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Islampur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | 2637/MURD | 23/09/2024 | 150 | INDRAJIT DUBEY | 8.72 | 0 | 0 | 100
3670 | MURSHIDABAD | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS , SM/18709 | New | PALITPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | 688/BD-I | 10/08/2023 | 180 | M/S AMIT KUMAR GUPTA | 167.04 | 0 | 0 | 0
3671 | MURSHIDABAD | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS , SM/18709 | New | Material Requisition To Resource Division | 201/BD-1/2 | 10/02/2024 | 0 | Resource Division | 56.21 | 0 | 0 | 0
3672 | MURSHIDABAD | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS , SM/18709 | New | Material Requisition To Resource Division | 2096/BD-I/3 | 25/11/2024 | 0 | Resource Division | 27.02 | 0 | 0 | 0
3673 | MURSHIDABAD | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS , SM/18709 | New | PALITPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | 687/BD-I | 10/08/2023 | 180 | BANIK BROTHERS | 89.01 | 0 | 0 | 0
3674 | MURSHIDABAD | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS , SM/18709 | New | PALITPARA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | 686/BD-I | 10/08/2023 | 730 | SUJIT KUMAR SAHA | 401.71 | 91.16 | 22.69 | 55
3675 | MURSHIDABAD | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS , SM/18709 | New | PALITPARA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Beldanga-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 736/BD-I | 16/08/2023 | 716 | S.K CONSTRUCTION (SUDIP KUMAR SANYAL) | 72.82 | 12.05 | 16.54 | 40
3676 | MURSHIDABAD | Central Drilling | PALITPARA AND ADJOINING MOUJAS PWSS , SM/18709 | New | Hiring of Diesel Driven Motor Cab (BS-IV & Above) (Non AC) having contract carriage permit along with driver for the office of The Assistant Engineer, Mech./Elect. Planning Wing, P.H.E. Dte. | 136/S&WSD | 24/06/2024 | 184 | NEMAI CHANDRA NAIYA | 0.87 | 2.06 | 236.22 | 0
3677 | MURSHIDABAD | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS , SM/18709 | New | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Palitpara" ground water supply scheme in Beldanga-II Block, under Berhampore Division-I, P.H.E Dte. (Capacity-111 Cum/hr.) Type-1 - Fully Gravity System with RG Filter | 998/BD-I | 20/06/2024 | 730 | M/S GOUTAM CHAKRABORTY | 257.77 | 0 | 0 | 0
3678 | MURSHIDABAD | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS , SM/18709 | New | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of PALITPARA PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 596/BD-I | 22/04/2025 | 60 | S.K CONSTRUCTION (SUDIP KUMAR SANYAL) | 19 | 0 | 0 | 0
3679 | MURSHIDABAD | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS , SM/18709 | New | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of PALITPARA PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 666/BD-I | 29/04/2025 | 60 | INDIAN TRADING CORPORATION | 19 | 0 | 0 | 0
3680 | MURSHIDABAD | Berhampore Division I | PALITPARA AND ADJOINING MOUJAS PWSS , SM/18709 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PALITPARA Water Supply Scheme (TW - II & III Site) within Beldanga-II Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 14/BD-I | 06/01/2025 | 120 | SARKAR WATER SUPPLY AGENCY | 18 | 0 | 0 | 100
3681 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kupila ( 314741 ) of Kupila under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) , SM/07911 | Retrofitting | Material Requisition To Resource Division | 395/A/MURD | 16/02/2022 | 0 | Resource Division | 11.77 | 0 | 0 | 0
3682 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kupila ( 314741 ) of Kupila under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( PART-I ) , SM/07911 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kupila (Village code 314741) under Kupila Ground Based Water Supply Scheme for Arsenic Affected Area of Domkal Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723481 (Sl-1) | 3675/MURD | 25/11/2021 | 1588 | M/S. SINHA & SONS | 119.26 | 0 | 0 | 75
3683 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malibbari ( 314569 ) of Malibari under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART-I ) , SM/07927 | Retrofitting | Material Requisition To Resource Division | 576/MURD | 03/03/2022 | 0 | Resource Division | 1.17 | 0 | 0 | 0
3684 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Malibbari ( 314569 ) of Malibari under Ground Water Based Water Supply Scheme for arsenic affected areas of Raninagar - II Block of Murshidabad District ( PART-I ) , SM/07927 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Malibari (Village code 314569) under Malibari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005184027 in the District of Murshidabad. | 307/MURD | 07/02/2022 | 60 | ULTRA CONSTRUCTION. | 31.15 | 28.85 | 100 | 0
3685 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Diar & Paraspur Diar ( 314651 & 314650 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of , SM/07515 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MURADPUR DAIR (Village Code 314651) under MURADPUR JALANGI Ground Water Based Water Supply Scheme for arsenic affected areas of JALANGI Block in the District of Murshidabad. Tender no - 294 of 21-22 by EE MURD | 373-MSD/21-22 | 15/03/2022 | 0 | PRANAB KUMAR SAHA | 10.13 | 0 | 0 | 0
3686 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Diar & Paraspur Diar ( 314651 & 314650 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of , SM/07515 | Retrofitting | Additional works for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Muradpur Dair ( Village Code -314651) under Muradpur-Jalangi Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723429) | 1681/MURD | 05/07/2021 | 60 | PRANAB KUMAR SAHA | 12.14 | 0 | 0 | 0
3687 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Muradpur Diar & Paraspur Diar ( 314651 & 314650 ) of Muradpur-Jalangi (Zone-I, II & III) under Ground Water Based Water Supply Scheme for arsenic affected areas of , SM/07515 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village MURADPUR DAIR (Village Code 314651) under Muradpur-Jalangi Ground Water Based Water Supply Scheme for arsenic affected areas of Jalangi Block in the District of Murshidabad. | 3033/MURD | 07/12/2020 | 45 | PRANAB KUMAR SAHA | 19.83 | 15.06 | 100 | 1
3688 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nasipur (Code-314186) In The Command Area Of Nasipur Zone-I Ground Water Supply Scheme (Part-C) , SM/07690 | Retrofitting | Formal Work Order Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nasipur (Village code 314186) under Nasipur Zone-I Ground Water based Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division - I, PHE Dte.(Part-III) (Sl-02) | 1133/BD-I | 06/07/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 97.21 | 88.6 | 91.15 | 1
3689 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nasipur (Code-314186) In The Command Area Of Nasipur Zone-I Ground Water Supply Scheme (Part-C) , SM/07690 | Retrofitting | Additional Laying works at village Nasipur ( Village code-314186) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Nasipur Ground water supply scheme (Lalgola,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 2303/BD-I | 28/12/2021 | 30 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 17.79 | 14.29 | 100 | 1
3690 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Mirzapur (Zone-H) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In , SM/07704 | Retrofitting | Retrofitting Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of village of Char Mirzapur (village code 315616), under Mirzapur (Zone-H) Water Supply Scheme of Beldanga-I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | 978/BD-I | 18/10/2023 | 90 | M/S. DAS ENTERPRISE MAHULA, DASPARA, VILL +P.O-GOPINATHPUR, MURSHIDABAD. | 43.31 | 0 | 0 | 0
3691 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rajarampur (Code-314196) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-C) Under Lalgola Block In Murshidaba , SM/07705 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Rajarampur (Code-314196) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-C) Under Lalgola Block In Murshidabad District Under Berhampore Division-I,PHE Dte. in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1446/BD-I | 04/09/2024 | 60 | PRANAB KUMAR GHOSH | 32.27 | 0 | 0 | 0
3692 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Rajarampur (Code-314196) In The Command Area Of Rajarampur Ground Water Supply Scheme (Part-C) Under Lalgola Block In Murshidaba , SM/07705 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rajarampur (Village code 314196) under Rajarampur Ground Water based Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) (Sl-05) | 1134/BD-I | 06/07/2021 | 180 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 104.87 | 109.88 | 100 | 1
3693 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Mathbarenda (Code-314480), Madapur (Code-314482), Sultanpur (Code-314490),Patti Bahadurpur (Code-314489) In The C , SM/07724 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at the Villages Of Mathbarenda (Code-314480), Madapur (Code-314482), Sultanpur (Code-314490),Patti Bahadurpur (Code-314489) In The Command Area Of Kasba Bahadurpur Ground Water Supply Scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1444/BD-I | 04/09/2024 | 60 | BHOWMIK CONSTRUCTION | 18.28 | 0 | 0 | 0
3694 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Mathbarenda (Code-314480), Madapur (Code-314482), Sultanpur (Code-314490),Patti Bahadurpur (Code-314489) In The C , SM/07724 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mathbarenda (Village code 314480) , Patti Bahadurpur (Village code 314489) Sultanpur (Village code 314490),Madapur (Village code 314482) under Kasba Bahadurpur Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | 166/BD-I | 03/02/2021 | 30 | DECON INDIA | 80.84 | 66.39 | 100 | 1
3695 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block , SM/08114 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block " in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1434/BD-I | 04/09/2024 | 60 | MOLLA ENTERPRISE | 34.65 | 0 | 0 | 0
3696 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block , SM/08114 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gangapur, Binkar, Mahisasthali, Gopinathpur, Gopalpur & Pulinda (Village code 315562, 315563, 315564, 315565, 315566 & 315567) under Gopinathpur (Zone-B) Water Supply Scheme of Beldanga -I Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 103/BD-I | 01/02/2022 | 1390 | DOBAY CONSTRUCTION | 261.58 | 162.27 | 62.03 | 92
3697 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block , SM/08114 | Retrofitting | Formal Work Order for laying of balance portion and relaying of damage portion in different dia on different nodes of UPVC and DI (K-7) pipe line under Gopinathpur (Zone-B) Surface based water supply scheme under uncovered arsenic areas of Beldanga-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. (Phase-I) | 100/BD-I | 01/02/2022 | 90 | C.X.CONSTRUCTION & CO. | 119.44 | 0 | 0 | 100
3698 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Gopinathpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block , SM/08114 | Retrofitting | Trial run of distribution system pipeline(CI/DI/UPVC/HDPE) and allied works at Gopinathpur Zone of Surface based water supply (under Central Sector Part-II) Scheme under JJM for uncovered arsenic affected area of Beldanga-I under Berhampore Division-I, PHE Dte Period for 3 Months. | 284/BD-I | 20/02/2024 | 90 | JAMIRUL CONSTRUCTION | 6.67 | 6.6 | 100 | 100
3699 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begamnagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08115 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 100 | 1
3700 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begamnagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08115 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gudhia (Village code 314870) under Begamnagar (Zone-D) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-07) | 1908/BD-I | 08/10/2021 | 180 | DECON INDIA | 134.39 | 108.31 | 80.59 | 90
3701 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begamnagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08115 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Pashchim Gobindapur,Hanribhanga & Biranpur (Village code 314844,314833 & 314834) under Begamnagar (Zone-D) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1015/BD-I | 21/06/2021 | 60 | KAMIRUL SK AND CO. | 71.45 | 64.58 | 100 | 1
3702 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begamnagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08115 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Prasadpur,Arazi Mathurapur,Gouripur Khastaluk, Mathurapur & Bele (Village code 314835,314836,314837,314842 & 314843) under Begamnagar (Zone-D) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1013/BD-I | 21/06/2021 | 1440 | M/S. SUKUMAR SINHA | 53.54 | 0 | 0 | 100
3703 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begamnagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08115 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gauripur (Village code 315412) under Begamnagar (Zone-D) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1014/BD-I | 21/06/2021 | 45 | SARAJIT KUMAR MAJUMDAR | 51.33 | 42.45 | 100 | 1
3704 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begamnagar (Zone-D) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08115 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gopalnagar,Singa & Banoaripur (Village code 314869,314877 & 314878) under Begamnagar (Zone-D) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1017/BD-I | 21/06/2021 | 60 | ULTRA CONSTRUCTION | 66.11 | 51.85 | 100 | 1
3705 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Sashidharpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector , SM/08117 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 100 | 1
3706 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Sashidharpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector , SM/08117 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-51B/5774 Bolero Diesel car for official use of Assistant Engineer-I, under Berhampore Division-I, PHE Dte. period for 01.01.2024 to 31.12.2024 | 1280/BD-I | 27/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 1.81 | 4.68 | 258.17 | 21
3707 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Sashidharpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector , SM/08117 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dilalpur & Baranda Sibnagar (Village code 314859 & 314860) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1009/BD-I | 21/06/2021 | 60 | DECON INDIA | 88.47 | 73.95 | 100 | 0
3708 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Sashidharpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector , SM/08117 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kapasdanga (Village code 314868) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1010/BD-I | 21/06/2021 | 60 | M/S JAN MAHAMMAD | 68.61 | 44.6 | 100 | 1
3709 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Sashidharpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector , SM/08117 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kalikapur,Hasnabad & Sashidharpur (Village code 314861,314862 & 314863) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1008/BD-I | 21/06/2021 | 701 | M/S JAN MAHAMMAD | 77.98 | 44.9 | 87.16 | 100
3710 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Sashidharpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector , SM/08117 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rambhadrapur & Gouribag (Village code 314839 & 314838) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1011/BD-I | 21/06/2021 | 45 | SANDHAN ADHIKARY | 46.7 | 41.27 | 100 | 0
3711 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Sashidharpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector , SM/08117 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bhatpara,Ramdaspur,Kamalpur & Jafrabad (Village code 314864,314865,314866 & 314867) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1012/BD-I | 21/06/2021 | 60 | M/S JAN MAHAMMAD | 68.64 | 55.59 | 100 | 1
3712 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Sashidharpur (Zone-B) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector , SM/08117 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ransagar, Aliganj,Akherighata ,Chirakuti,Samserganj, Noada,Akbarpur,Sabjikatra, Topkhana, Kadamsarif (Village code 314853,314854,314855,314856,314857,314858,314852,314840 & 314851) under Sashidharpur (Zone-B) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1170/BD-I | 15/07/2021 | 60 | ARINDAM MAJUMDAR | 59.21 | 49.86 | 100 | 100
3713 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for the Village of Aragi Kulgachi (VillageCode-314471) , Subarnamrigi (VillageCode-314473) under command area of Digha ground wate , SM/06976 | Retrofitting | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Subarna Mrigi (Village Code-314473) under Digha Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | 276/ BD-I | 15/02/2021 | 10 | DAS TRADING CO | 4.87 | 0 | 0 | 0
3714 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for the Village of Aragi Kulgachi (VillageCode-314471) , Subarnamrigi (VillageCode-314473) under command area of Digha ground wate , SM/06976 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Aragi Kulgachi (Village code 314471) under Digha Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 163/BD-I | 03/02/2021 | 20 | SARAJIT KUMAR MAJUMDAR | 33.52 | 0 | 0 | 0
3715 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for the Village of Aragi Kulgachi (VillageCode-314471) , Subarnamrigi (VillageCode-314473) under command area of Digha ground wate , SM/06976 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Subarna Mrigi (Village code 314473) under Digha Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 842/BD-I | 23/11/2020 | 90 | PRADIP KUMAR DAS | 25.8 | 19.56 | 75.8 | 0
3716 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Harirampur ground water supply scheme , SM/06979 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION under command area of Harirampur ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte.. | 1220/BD-I | 29/07/2024 | 30 | PRADIP DAS | 5.61 | 0 | 0 | 0
3717 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Harirampur ground water supply scheme , SM/06979 | Retrofitting | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Joyrampur (Village Code-314553) and others under Harirampur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | 916/BD-I | 19/05/2021 | 20 | M/S. M.G. CONSTRUCTION | 4.31 | 2.59 | 60.14 | 0
3718 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Harirampur ground water supply scheme , SM/06979 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Harirampur (Village code 314554) under Harirampur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 974/BD-I | 17/12/2020 | 90 | KAMIRUL SK AND CO. | 22.63 | 42.51 | 199.24 | 1
3719 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Harirampur ground water supply scheme , SM/06979 | Retrofitting | Laying of new pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Harirampur and others under Harirampur Ground Water Supply Scheme in Lalgola Block under Murshidabad District under Berhampore Division-I, PHE Dte. | 1452/BD-I | 13/08/2021 | 10 | KAMIRUL SK AND CO. | 4.62 | 2.51 | 100 | 1
3720 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagor, Nandigram, Madhunia (315019, 315020 & 315022) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murs , SM/07277 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at AMARKUNDU G.P. under Murshidabad Division, P.H.E.Dte. | 248/LSD | 18/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.18 | 0 | 0 | 1
3721 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagor, Nandigram, Madhunia (315019, 315020 & 315022) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murs , SM/07277 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --SAHAJADPUR- Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District. VILLAGE- NISCHINTAPUR , CODE- 315328 , 600 /2020-21/EE | 489/W | 17/03/2021 | 0 | SAMBHUNATH ROY | 29.21 | 0 | 0 | 0
3722 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagor, Nandigram, Madhunia (315019, 315020 & 315022) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murs , SM/07277 | Retrofitting | Extension of UPVC pipeline construction of RCC stand post with platform at Darerdanga under Improvement works of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. | 415/LSD | 27/12/2021 | 30 | SARAJIT KUMAR MAJUMDER | 3.79 | 3.78 | 100 | 1
3723 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagor, Nandigram, Madhunia (315019, 315020 & 315022) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murs , SM/07277 | Retrofitting | Material Requisition To Resource Division | 542/MURD | 25/02/2022 | 0 | Resource Division | 2.47 | 0 | 0 | 0
3724 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagor, Nandigram, Madhunia (315019, 315020 & 315022) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murs , SM/07277 | Retrofitting | Balance and allied works For Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Madhunia (Village code 315022) and under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nabagram Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 345/MURD | 11/02/2022 | 60 | S.K. ENTERPRISE (SANDIP GHOSH) | 14.32 | 13.21 | 100 | 0
3725 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bagor, Nandigram, Madhunia (315019, 315020 & 315022) of Amarkunda under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nabagram Block of Murs , SM/07277 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bagore (Village code 315019) and under Amarkundu Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nabagram Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 817/MURD | 25/03/2022 | 30 | M/S. CHOWDHURY CONSTRUCTION | 12.2 | 11.81 | 100 | 0
3726 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilaspur Nachharerpara (314639) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Mu , SM/07286 | Retrofitting | SUPPLY OF GUN METAL FERRULE CONFORMING...WORK O LALBAGH SUBDIVISION FOR FHTC, TNO- 44/20-21/SEMC | 505/W | 27/03/2021 | 0 | AZAD ENTERPRISE ( KOLKATA) | 94.63 | 0 | 0 | 0
3727 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilaspur Nachharerpara (314639) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Mu , SM/07286 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bilaspur Nachharerpara (314639) of Barabil Raghunathpur (Zone-I& II) under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Jalangi Block of Murshidabad District (Part-IV) |  | 17/02/2022 | 0 | M/S. UNIQUE BUILDERS | 74.29 | 0 | 0 | 0
3728 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramchandrapur ground water supply scheme , SM/07232 | Retrofitting | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Ramchandrapur ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1607/BD-I | 03/10/2024 | 30 | SUJIT CHOWDHURY | 5.13 | 0 | 0 | 0
3729 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Ramchandrapur ground water supply scheme , SM/07232 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramchandrapur (Village code 314592) under Ramchandrapur Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 985/BD-I | 17/12/2020 | 60 | SOM CONSTRUCTION AGENCY | 16.15 | 19.07 | 138.46 | 1
3730 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Paschim Gobindapur (VillageCode-314448)& Barbaria(Village Code-314462) under command area of Gobra ground water s , SM/07234 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Paschim Gobindapur (Village code 314448) under Gobra Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 66/BD-I | 18/01/2021 | 30 | JAHANGIR ALAM | 32.15 | 25.67 | 79.84 | 1
3731 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA for Village of Paschim Gobindapur (VillageCode-314448)& Barbaria(Village Code-314462) under command area of Gobra ground water s , SM/07234 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Barbaria (Village code 314462) under Gobra Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 67/BD-I | 18/01/2021 | 30 | M/S SINHA & SONS | 40.34 | 35.18 | 100 | 0
3732 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harharia Chak (CT) (314806) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PA , SM/07685 | Retrofitting | Connection of Rising Main at Pump House No. II & Newly Sunk tubewell of Pump House No. I and other allied works under Islampur Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad | 275/ISD | 27/06/2022 | 30 | PARTHA PRATIM DAS | 3.74 | 3.62 | 100 | 0
3733 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Harharia Chak (CT) (314806) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PA , SM/07685 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Harharia Chak (Village code 314806 ) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005182977 in the District of Murshidabad. (Sl No-06) | 2599/MURD | 25/08/2021 | 1621 | SHYAMAL KUMAR SAHA | 101.35 | 54.94 | 54.21 | 40
3734 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadatpur(VillageCode-315671) ,Chhatiani (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) , SM/07236 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sadatpur (Village code 315671) under Sadhukhali Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 1046/BD-I | 28/12/2020 | 60 | MAHATO ENTERPRISE | 4.04 | 0 | 0 | 0
3735 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadatpur(VillageCode-315671) ,Chhatiani (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) , SM/07236 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chhatiani (Village code 315673) under Sadhukhali Ground Water based Water Supply Scheme for Beldanga-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 1045/BD-I | 28/12/2020 | 90 | MS RUBIET HOSSAIN | 43.95 | 39.68 | 90.3 | 0
3736 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadatpur(VillageCode-315671) ,Chhatiani (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) , SM/07236 | Retrofitting | Additional Laying works at villages within Dadpur G.P areas to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Sadhukhali Ground water supply scheme (Beldanga-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 157/BD-I | 11/02/2022 | 30 | ANKUSH CONSTRUCTION & CO. | 16.17 | 0 | 0 | 0
3737 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA at Sadatpur(VillageCode-315671) ,Chhatiani (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) , SM/07236 | Retrofitting | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION at Sadatpur(VillageCode-315671) ,Chhatiai (Village Code-315673) under command area of Sadhukhali ground water supply scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1451/BD-I | 04/09/2024 | 30 | K.S.ENTERPRISE (PROP. SAMIM SK.) | 3.55 | 0 | 0 | 0
3738 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Islampur (CT) (314805) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PART-II , SM/07683 | Retrofitting | Restoration work of distribution pipeline by using UPVC pipeline from Nashipur Graveyard to Kathal bariya Jumma Masjid and new construction of street stand post under Islampur Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period. | 467/ISD | 03/09/2021 | 30 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 4.8 | 4.04 | 84.11 | 0
3739 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Islampur (CT) (314805) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PART-II , SM/07683 | Retrofitting | Extension of pipeline at uncovered habitation of Nashipur Biswaspara from Enamul Biswas house to Khalek Biswas house and Rafikul Sk house to Mokbul Mondal house at Nashipur Panthipara under command area of Islampur Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. during COVID - 19 affected period. | 469/ISD | 03/09/2021 | 30 | S. DUTTA | 4.7 | 3.56 | 100 | 0
3740 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Islampur (CT) (314805) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PART-II , SM/07683 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dighirpahar (Village code 314794) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005182977 in the District of Murshidabad. (Sl No-08) | 2503/MURD | 17/08/2021 | 120 | SUJIT KUMAR SAHA | 70.56 | 23.56 | 61.77 | 1
3741 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Islampur (CT) (314805) of Islampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PART-II , SM/07683 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Islampur(CT) (Village code 314805) under Islampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0005182977 in the District of Murshidabad. | 2506/MURD | 17/08/2021 | 1629 | NAYLA CONSTRUCTION | 109.99 | 0 | 0 | 40
3742 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) , SM/07770 | Retrofitting | Retrofitting functional hoyusehold tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of Village PANCHTHUPI under PANCHTHUPI Ground Based W/S Scheme for Arsenic Affected area of Burwan Block under MSD PHE DTE. Scheme Id:0007335523 in the dist of Murshidabad. Sl. No.24 Tender no 70 SE/MC 20-21 | 02/MSD/21-22 | 16/07/2021 | 0 | M/S GUHA & ROY ENTERPRISE | 37.93 | 0 | 0 | 0
3743 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) , SM/07770 | Retrofitting | Laying of Distribution pipeline in connection with FHTC work at PANCHTHUPI Village (Ghosh Para) under PANCHTHUPI W/Sb Scheme under KSD PHE DTE. Tender no - 58 of 21-22 by AE KSD | 111-MSD/22-23 | 07/05/2022 | 0 | M/S GUHA & ROY ENTERPRISE | 4.5 | 0 | 0 | 0
3744 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) , SM/07770 | Retrofitting | BALANCE work of Distribution pipeline in connection with FHTC work at SHIBRAMBATI Village under PANCHTHUPI W/S Scheme under KSD PHE DTE. Tender no - 56 of 21-22 by AE KSD | 111-MSD/22-23 | 07/05/2022 | 0 | M/S GUHA & ROY ENTERPRISE | 4.73 | 0 | 0 | 0
3745 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) , SM/07770 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village PANCHTHUPI under PANCHTHUPI Ground Water Based Water Supply Scheme for arsenic affected areas of BURWAN Block in the District of Murshidabad. Tender no - 70 of 20-21 by SE MC | 369-MSD/21-22 | 18/03/2022 | 0 | M/S GUHA & ROY ENTERPRISE | 49.54 | 0 | 0 | 0
3746 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) , SM/07770 | Retrofitting | Laying of Distribution pipeline in connection with FHTC work at PANCHTHUPI Village (DAKSHIN PARA AND KESI PARA) under PANCHTHUPI W/S Scheme under KSD PHE DTE. Tender no - 57of 21-22 by AE KSD | 143-MSD/22-23 | 11/05/2022 | 0 | M/S GUHA AND ROY | 4.81 | 0 | 0 | 0
3747 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) , SM/07770 | Retrofitting | Balance work of distribution pipeline in connection with FHTC work at Shibrambati Village under Panchthupi Water Supply Scheme under Kandi Sub Division , P.H.E. Dte. In the district of Murshidabad. | 374/KSD | 19/01/2022 | 30 | M/S GUHA AND ROY | 4.73 | 0 | 0 | 0
3748 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) , SM/07770 | Retrofitting | Laying of distribution pipeline in connection with FHTC work at Panchthupi Village (Ghosh Para) under Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E. Dte. In the district of Murshidabad. | 380/KSD | 19/01/2022 | 30 | M/S GUHA AND ROY | 4.51 | 0 | 0 | 0
3749 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) , SM/07770 | Retrofitting | Laying of distribution pipeline in connection with FHTC work at Panchthupi Village (Dakshin Para & Kesi Para) under Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E. Dte. In the district of Murshidabad. | 376/KSD | 19/01/2022 | 30 | M/S GUHA AND ROY | 4.81 | 0 | 0 | 0
3750 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) , SM/07770 | Retrofitting | Construction of Sluice valve chamber & laying of upvc pipeline in connection with retrofitting work at Panchthupi Village (315983) under Panchthupi Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 27/KSD | 08/04/2022 | 30 | CHAND ENTERPRISE | 4.72 | 4.38 | 100 | 100
3751 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) , SM/07770 | Retrofitting | Laying of distribution pipeline in connection with FHTC work at Panchthupi Village (Village Code-315983)(Mokanpara) under Panchthupi Water Supply Scheme under Kandi Sub Division , P.H.E. Dte. In the district of Murshidabad. | 97 / KSD | 06/06/2022 | 30 | M/S GUHA AND ROY | 4.83 | 4.72 | 100 | 1
3752 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) , SM/07770 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Shibrambati (315980) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District, TNO- 764/2020-21/EE | 172-MSD/2024-25 | 21/06/2024 | 0 | SOUMYA KANTI SINHA | 1.02 | 0 | 0 | 0
3753 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) , SM/07770 | Retrofitting | Balance Retrofitting Work of Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under at Janardanpur & adjoining mouzas (JL NO-147) ( Village Code -315981) from the exiting distribution system of Panchthupi Water Supply Scheme (Ground Water Based) in Burwan Block under Kandi Sub Division under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 173-MSD/2024-25 | 21/06/2024 | 0 | J.S. CONSTRUCTION | 0.05 | 0 | 0 | 0
3754 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Panchthupi ( 315983 ) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block of Murshidabad District ( PART-I ) , SM/07770 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Panchthupi ( Village Code -315983) under Panchthupi Ground Based Water Supply Scheme for Arsenic Affected Area of Burwan Block, under Murshidabad Division, PHE Dte. Scheme ID 0007335523 in the District of Murshidabad. (Sl No-24) | 3050 / MURD | 08/12/2020 | 1850 | M/S GUHA & ROY ENTERPRISE | 113.53 | 17.96 | 15.82 | 90
3755 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dangapara, Banpur, Bele, Chandsingbati (315190, 315191, 315208, 315210) of Bele under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram , SM/07682 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna Mission (JJM) from existing distribution system within the command area of Village CHANDBATI (Village Code- 315210) under BELE Water Supply Scheme of KHORGARM BLOCK Murshidabad District under Murshidabad Division, PHE Dte. TNO- 54/20-21/EE | 18-MSD / 21-22 | 10/08/2021 | 0 | M/S . SUKUMAR SINHA | 23.36 | 0 | 0 | 0
3756 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dangapara, Banpur, Bele, Chandsingbati (315190, 315191, 315208, 315210) of Bele under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram , SM/07682 | Retrofitting | Balance works of laying of UPVC distribution pipeline at Chandra Singha Bati village in connection of FHTC work of Bele Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. | 319/KSD | 16/11/2021 | 30 | BHOLEBABA CONSTRUCTION CO | 4.84 | 0 | 0 | 0
3757 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dangapara, Banpur, Bele, Chandsingbati (315190, 315191, 315208, 315210) of Bele under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram , SM/07682 | Retrofitting | Balance work for extention og distibution pipeline form Bainpara, Kandapara, burwan & Seikhpara area under Bele W/S Scheme under Kandi Sub Div. PHE DTE. Tender no - 41 of 21-22 by AE KSD | 386-MSD/21-22 | 23/03/2022 | 0 | SUKUMAR ROY | 4.82 | 0 | 0 | 0
3758 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dangapara, Banpur, Bele, Chandsingbati (315190, 315191, 315208, 315210) of Bele under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram , SM/07682 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BANPUR (Village Code 315191) under BELE Ground Water Based Water Supply Scheme for arsenic affected areas of KHARGRAM Block in the District of Murshidabad. Tender no - 831 of 20-21 by EE MURD | 364-MSD/21-22 | 11/03/2022 | 0 | M/S. SINHA & SONS | 27.15 | 0 | 0 | 0
3759 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dangapara, Banpur, Bele, Chandsingbati (315190, 315191, 315208, 315210) of Bele under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram , SM/07682 | Retrofitting | BALALNCE WORK OF LAYING OF UPVC PIPE LIN E AT CHANDRASINGHA BATI IN CONNECTION OF FHTC WORK UNDER BELE WSS, TNO- 36/21-22/AEKSD | 340 -MSD/21-22 | 03/03/2022 | 0 | BHOLEBABA CONSTRUCTION CO | 4.84 | 0 | 0 | 0
3760 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dangapara, Banpur, Bele, Chandsingbati (315190, 315191, 315208, 315210) of Bele under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram , SM/07682 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at BALIA G.P. under Murshidabad Division, P.H.E.Dte. | 235/KSD | 27/08/2021 | 60 | IMAGIN COMMUNICATION | 4.17 | 0 | 0 | 0
3761 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dangapara, Banpur, Bele, Chandsingbati (315190, 315191, 315208, 315210) of Bele under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram , SM/07682 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Kandi Sub-Division under Murshidabad Division, P.H.E Dte. | 213/KSD | 11/08/2021 | 30 | IMAGIN COMMUNICATION | 3.25 | 0 | 0 | 0
3762 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dangapara, Banpur, Bele, Chandsingbati (315190, 315191, 315208, 315210) of Bele under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram , SM/07682 | Retrofitting | Balance work for extension of distribution pipeline from Bainpara, Kandapara, Banur & Seikhpara area under Bele Water Supply Scheme under Kandi Sub-Division, PHE Dte. in the district of Murshidabad. | 321/KSD | 16/11/2021 | 30 | SUKUMAR ROY | 4.83 | 0 | 0 | 0
3763 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dangapara, Banpur, Bele, Chandsingbati (315190, 315191, 315208, 315210) of Bele under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram , SM/07682 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village BANPUR (Village Code.315191) under Bele Ground Water Based Water Supply Scheme for arsenic affected areas of Khargram Block in the District of Murshidabad. | 3030/MURD | 07/12/2020 | 45 | M/S. SINHA & SONS | 28.3 | 0 | 0 | 0
3764 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Dangapara, Banpur, Bele, Chandsingbati (315190, 315191, 315208, 315210) of Bele under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Khargram , SM/07682 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of Bele Habitation under Bele Village(JL NO-152) of Bele Water Supply Scheme(Ground Water Based) under Kandi Block in the District of Murshidabad. | 2526/MURD | 30/09/2020 | 45 | R.M. BHATTA | 39.32 | 1.98 | 200 | 0
3765 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Mahatpur (Code-314442) In The Command Area Of Telia Ground Water Supply Scheme (Part-A) Under Bhagwangola-I Block In Murshidabad , SM/07786 | Retrofitting | Additional of different dia of UPVC pipeline for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahatpur (Village code 314442) under Telia Ground Water based Water Supply Scheme for Bhagwangola-I Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-A) | 1453/BD-I | 13/08/2021 | 10 | KAMIRUL SK AND CO. | 1.03 | 0 | 0 | 0
3766 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Karttikpur (Code-314220) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-C) Under Lalgola Block , SM/07787 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Karttikpur(Village code 314220) under Bansgara Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | 204/BD-I | 04/02/2021 | 30 | SARAJIT KUMAR MAJUMDAR | 61.23 | 45.46 | 74.25 | 1
3767 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Karttikpur (Code-314220) In The Command Area Of Bansgara Ground Water Supply Scheme (Part-C) Under Lalgola Block , SM/07787 | Retrofitting | Laying of different dia UPVC Pipeline for uncovered Habitation and damage portion at Bansgara Ground Water based Water Supply Scheme under Lalgola Block under Berhampore Division-I ,P.H.E Dte. (Phase-I) | 1634/BD-I | 02/09/2021 | 30 | SANTA TRADING | 18.56 | 18.79 | 100 | 1
3768 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of , SM/08196 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BISHANNAGAR (Village Code 315605) under BELDANGA MUNICIPALITY Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-I Block in the District of Murshidabad. Tender no - 905 of 21-22 by EE MURD | 346-MSD/21-22 | 05/03/2022 | 0 | NAYLA CONSTRUCTION | 79.01 | 0 | 0 | 0
3769 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of , SM/08196 | Retrofitting | Material Requisition To Resource Division | 539/10/MURD | 25/02/2022 | 0 | Resource Division | 10.18 | 0 | 0 | 0
3770 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of , SM/08196 | Retrofitting | Formal work order for Retrofitting Functional Household Tap Connections (FHTC) under Jal Swapna (Jal Jeevan Mission) and under command area of village of Debkunda (Village code-315602) under Madda Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga-I Block of Murshidabad District under Murshidabad Division P.H.E Dte. | 2833/MURD | 17/10/2022 | 120 | AMAL KUMAR DAS | 119.55 | 0 | 0 | 0
3771 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of , SM/08196 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bishannagar ( Village Code -315605) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | 599/MURD | 09/02/2021 | 60 | NAYLA CONSTRUCTION | 95.64 | 0 | 0 | 0
3772 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of , SM/08196 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) of 1851 nos in connection with (Jal Jeevan Mission ) and under command area of village of Debkunda ( Village Code -315602) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | 1195/MURD | 10/05/2022 | 60 | SOURAV DEY | 82.09 | 0 | 0 | 0
3773 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of , SM/08196 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Madda ( Village Code -315603) & adjoining habitation (Part-I) under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | 2385/MURD | 09/08/2021 | 60 | MITRA & SARKAR CONSTRUCTION | 65.45 | 50.92 | 99.74 | 10
3774 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Debkunda, Dalua, Madda & Bishannagar (315602, 315580, 315603 & 315605) of Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga - I Block of , SM/08196 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Madda ( Village Code -315603)adjoining habitation under Beldanga Municipality Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga - I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756904) | 2384/MURD | 09/08/2021 | 60 | MITRA & SARKAR CONSTRUCTION | 63.64 | 61.02 | 100 | 0
3775 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-II Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, , SM/08903 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bali (Village code 315524) under Bali Zone-II Ground Water Supply Scheme in Nawda Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-01) | 1886/BD-I | 07/10/2021 | 180 | SANJAY BISWAS | 248.74 | 133.42 | 53.64 | 85
3776 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, , SM/08905 | Retrofitting | Additional Laying works at village Kedarchandpur, Bundai Nagar and Alampur (Village code-315518,315530, and 315519) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Ramnachandpur Ground water based Water supply scheme (Nawda,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | 2309/BD-I | 29/12/2021 | 90 | SRIJON ENTERPRISE | 43.88 | 35.92 | 100 | 1
3777 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, , SM/08905 | Retrofitting | Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub-Division, PHE Dte. period for 01.01.2022 to 31.12.2022. | 2281/BD-I | 27/12/2021 | 365 | TARUN KUMAR BHATTACHARYA | 1.81 | 1.58 | 100 | 1
3778 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, , SM/08905 | Retrofitting | Material Requisition To Resource Division | 144/BD-I | 10/02/2022 | 0 | Resource Division | 16.44 | 0 | 0 | 0
3779 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, , SM/08905 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kedarchandpur (village code 315518) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1854/BD-I | 07/10/2021 | 100 | SRIJON ENTERPRISE | 98.62 | 63.5 | 64.38 | 1
3780 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, , SM/08905 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bundai Nagar (village code 315530) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1852/BD-I | 07/10/2021 | 100 | SRIJON ENTERPRISE | 96.17 | 68.46 | 71.18 | 1
3781 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, , SM/08905 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnachandpur (Village code 315520) under Ramnachandpur Water Supply Scheme of Nawda Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-14) | 1924/BD-I | 08/10/2021 | 180 | M/S GUHA AND ROY ENTERPRISE | 217.79 | 123.15 | 56.54 | 1
3782 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, , SM/08905 | Retrofitting | Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.06.2022 to 31.12.2022. | 628/BD-I | 30/05/2022 | 214 | SOUVIK HALDER | 1.06 | 2.56 | 100 | 1
3783 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, , SM/08905 | Retrofitting | Laying of Extension and parallel pipeline at Ramnachandpur village due to smooth Functioning of Functional Hosehold Tap Connection at Ramnachandpur zone-I ground Water based water Supply Scheme Under Berhampore Division-I,P.H.E Dte. | 551/BD-I | 13/05/2022 | 45 | ULTRA CONSTRUCTION | 40.55 | 29.76 | 73.4 | 1
3784 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, , SM/08905 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Alampur (village code 315519) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1853/BD-I | 07/10/2021 | 90 | SRIJON ENTERPRISE | 88.19 | 65.18 | 100 | 1
3785 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Begunbari (Zone-I) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block , SM/08909 | Retrofitting | Retrofitting Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of villages of Hareknagar, Andiran ,Begunbari and Chakhijli (village code 315604,315610,315608 and 315609), under BEGUNBARI (Zone-I) Water Supply Scheme of Beldanga-I Block in Murshidabad District under Berhampore Division-I, PHED | 1804/BD-I | 31/03/2023 | 120 | SARAJIT KUMAR MAJUMDAR | 350.09 | 0 | 0 | 0
3786 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kulbaria (Village code 315414) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1820/BD-I | 05/10/2021 | 90 | USHA ENTERPRISE | 84.7 | 61.07 | 100 | 1
3787 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Additional Laying works at village Daulatabad to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Daulatabad Surface water based water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 244/BD-I | 03/03/2022 | 15 | MONDAL ENTERPRISE VILL. + P.O.- CHALTIA, P.S.- BERHAMPORE | 8.58 | 7.05 | 100 | 1
3788 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 62.23 | 1
3789 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under DAULATABAD(Zone-F) Surface Water based Water Supply Scheme of Central Sector (Part-I) under Murshidabad -Jiaganj Block in Murshidabad District under Berhampore Division-I, PHE Dte. | 440/BD-I | 12/07/2023 | 90 | A.P CONSTRUCTION | 42.93 | 0 | 0 | 0
3790 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Material Requisition To Resource Division | 71/BD-I | 28/01/2022 | 0 | Resource Division | 0.4 | 0 | 0 | 0
3791 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Material Requisition To Resource Division | 64/BD-I | 27/01/2022 | 0 | Resource Division | 1.24 | 0 | 0 | 0
3792 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Purandarpur (Village code 315403) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1825/BD-I | 05/10/2021 | 60 | M/S SINHA & SONS | 55.92 | 51.43 | 100 | 100
3793 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dadpur (Village code 315422) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1818/BD-I | 05/10/2021 | 100 | DOBAY CONSTRUCTION | 98.25 | 72.16 | 73.45 | 1
3794 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gauripur and Ruhia (Village code 315412,315413) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1821/BD-I | 05/10/2021 | 90 | MAMATA USHA ENTERPRISE | 90.65 | 40.97 | 45.19 | 1
3795 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Daulatabad (Village code 315415) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1819/BD-I | 05/10/2021 | 90 | PRADIP KUMAR DAS | 88.49 | 79.01 | 89.28 | 1
3796 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Muliarazi,Harirampur and Balia Danga (Village code 315400,315401,315402) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1823/BD-I | 05/10/2021 | 80 | KAMIRUL SK AND CO. | 76.53 | 39.07 | 51.04 | 1
3797 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Doulatabad Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | 2225/BD-I | 15/12/2021 | 90 | AJOY GHOSH | 74.29 | 74.76 | 100 | 1
3798 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chutipur (village code 315419), under Doulatabad (Zone-F) Surface water based Water Supply Scheme of Central Sector Part-I for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 2205/BD-I | 10/12/2021 | 120 | SAMRIDDHI ASSOCIATED | 96 | 90.17 | 93.93 | 1
3799 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhanjha,Benidaspur,Garabasa,Maharajpur and Hanumanta Nagar (Village code 315407,315408,315409,315410,315411) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1822/BD-I | 05/10/2021 | 100 | BANIK BROTHERS | 97.4 | 82.14 | 100 | 100
3800 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Muli and Gangaprasad (Village code 315406,315423) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1824/BD-I | 05/10/2021 | 20 | ROY AND ROY CONSTRUCTION | 10.62 | 8.6 | 100 | 1
3801 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P , SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mukundapur and Purbagopinathpur (Village code 315416,315420) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1826/BD-I | 05/10/2021 | 30 | SUDIPA SINGHA ROY | 23.87 | 18.26 | 100 | 1
3802 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Popara ( 314326 ) of Sagardighi Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of Murshidabad District under M , SM/09748 | Retrofitting | Material Requisition To Resource Division | 889/E/MURD | 05/04/2022 | 0 | Resource Division | 15.53 | 0 | 0 | 0
3803 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Popara ( 314326 ) of Sagardighi Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of Murshidabad District under M , SM/09748 | Retrofitting | Providing Functional Household Tap Connections (FHTC) (1250 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Popara under Sagardighi Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block under Murshidabad Division P.H.E Dte. | 3713/MURD | 05/12/2023 | 60 | SANDIP KUMAR BISWAS | 44.69 | 0 | 0 | 0
3804 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dudhsar ( 315521 ) of Sarbangapur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad D , SM/09840 | Retrofitting | Supplying and Laying of 110mm dia UPVC pipe line at Dudhsar Habitaion (village -code-315521) for FHTC work under SARBANGAPUR ZONE-I Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | 123/BSD | 19/02/2021 | 15 | NATIONAL ENTERPRISE | 4.83 | 4.83 | 99.95 | 0
3805 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dudhsar ( 315521 ) of Sarbangapur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad D , SM/09840 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dudhsar (Village code 315521) under Sarbangapur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723279 in the District of Murshidabad. | 34/MURD | 05/01/2021 | 60 | CHATTERJEE ENTERPRISE | 19.26 | 8.94 | 46.42 | 0
3806 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dudhsar ( 315521 ) of Sarbangapur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad D , SM/09840 | Retrofitting | Supplying and Laying of 160mm dia UPVC pipe line at Dudhsar Habitaion (village -code-315521) for FHTC work under SARBANGAPUR ZONE-I Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. | 121/BSD | 19/02/2021 | 15 | CHATTERJEE ENTERPRISE | 4.83 | 4.82 | 100 | 0
3807 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dudhsar ( 315521 ) of Sarbangapur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad D , SM/09840 | Retrofitting | Supplying and Laying of 90mm dia UPVC pipe line at Dudhsar Habitaion (village -code-315521) for FHTC work under SARBANGAPUR ZONE-I Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. (Part-II) | 122/BSD | 19/02/2021 | 15 | DAS CONSTRACTION | 4.83 | 4.83 | 50 | 0
3808 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dudhsar ( 315521 ) of Sarbangapur under Ground Water Based Water Supply Scheme for arsenic affected areas of Nawda Block of Murshidabad District under Murshidabad D , SM/09840 | Retrofitting | Supplying and Laying of 90mm dia UPVC pipe line at Dudhsar Habitaion (village -code-315521) for FHTC work under SARBANGAPUR ZONE-I Water Supply Scheme under Berhampore Sub Division,P.H.E. Dte. In the District Murshidabad. (Part-I) | 124/BSD | 19/02/2021 | 15 | LONDON WHARFIES | 4.85 | 4.85 | 100 | 0
3809 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kishorpur (313961) of Kishorpur and adjonining mouzas under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad Dis , SM/09760 | Retrofitting | Material Requisition To Resource Division | 889/C/MURD | 05/04/2022 | 0 | Resource Division | 5.21 | 0 | 0 | 0
3810 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Kishorpur (313961) of Kishorpur and adjonining mouzas under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti - II Block of Murshidabad Dis , SM/09760 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kishorpur (Village code 313961) under Kishorpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Suti-II Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723400 in the District of Murshidabad. | 426/MURD | 17/02/2022 | 60 | BISWAS CONSTRUCTION | 40.15 | 38.52 | 100 | 0
3811 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Jitpur ( 314713 ) of Garibpur (Zone- I & Zone - II) under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad D , SM/09848 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dakshin Jitpur (Village code 314713) under Garibpur (Zone-I & Zone-II) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723342 in the District of Murshidabad. | 322 /MURD | 28/01/2021 | 60 | MOLLA ENTERPRISE (REHENA BIBI) | 22.64 | 31.19 | 152.81 | 0
3812 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Dakshin Jitpur ( 314713 ) of Garibpur (Zone- I & Zone - II) under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad D , SM/09848 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Nandalalpur (Village code 314628) under Barabil Raghunathpur Ground Water Based water Supply Scheme for Arsenic Affected Area of Jalangi Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723213 in the District of Murshidabad. (Sl No-29) | 961/MURD | 24/03/2021 | 180 | S.M. ENTERPRISE | 50.52 | 0.32 | 100 | 1
3813 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Santoshpur (314329) &Chandanbati ( 314330 ) of Sagardighi Zone - I under Ground Water Based Water Supply Scheme for arsenic affected areas of Sagardighi Block of M , SM/09850 | Retrofitting | Providing Functional Household Tap Connections (FHTC) (1173 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Santoshpur ( Village Code -314329) & Chandanbati ( Village code-314330) under Sagardighi Zone-I Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Sagardighi Block under Murshidabad Division P.H.E Dte. | 3438/MURD | 03/11/2023 | 45 | MAA SANKARI ENTERPRISE | 36.58 | 0 | 0 | 0
3814 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pradipdanga ( 315470 ) of Kismat Imadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Hariharpara Block of Murshidabad District under , SM/09851 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at HARIHARPARA G.P. under Murshidabad Division, P.H.E.Dte. | 348/BSD | 27/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.17 | 4.17 | 100 | 0
3815 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Pradipdanga ( 315470 ) of Kismat Imadpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Hariharpara Block of Murshidabad District under , SM/09851 | Retrofitting | Work of Re-Laying of U.P.V.C pipe of 140 mm dia on damaged portion in between N.P 22 to 23 & 125 mm Dia N.P 23 to 24 and 110 mm Dia N.P 24 to 25,N.P 25 to 26, 90mmOD N.P 26 to27,27 to 28 ;200mm dia N.P 3 to 4,N.P 19 to 20;160 mm OD N.P 21 to 22 at Kanaighat area at uncovered Habitation for smooth water supply arrangement in Kadoa W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. during COVID-19 affected period (Part-B). | 388/JSD | 31/12/2021 | 30 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 4.84 | 4.84 | 100 | 100
3816 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10633 | Augmentation | Material Requisition To Resource Division | 3294/MURD | 12/12/2022 | 0 | Resource Division | 21.86 | 0 | 0 | 0
3817 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10633 | Augmentation | Material Requisition To Resource Division | 2780/D/MURD | 01/10/2022 | 0 | Resource Division | 21.86 | 0 | 0 | 0
3818 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10633 | Augmentation | Material Requisition To Resource Division | 1180/MURD/6 | 29/04/2023 | 0 | Resource Division | 143.36 | 0 | 0 | 0
3819 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10633 | Augmentation | Material Requisition To Resource Division | 3849/MURD/1 | 14/12/2023 | 0 | Resource Division | 1.98 | 0 | 0 | 0
3820 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10633 | Augmentation | New connection charge for Jalangi W/S Scheme (Part-A) Zone-II, P/H No.-I. | 90/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 1.61 | 0 | 0 | 0
3821 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10633 | Augmentation | New connection charge for Jalangi W/S Scheme (Part-A) Zone-II, P/H No.-II. | 89/WBSEDCL-JJM | 11/08/2023 | 0 | WBSEDCL | 0.91 | 0 | 0 | 0
3822 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10633 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of JALANGI , Zone- II/Part-A ground water based water supply scheme under Block- Jalangi, Dist. | 3768/MEDB | 03/11/2023 | 92 | EASTERN INDIA SALES & SERVICE | 22.55 | 16.77 | 74.37 | 60
3823 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10633 | Augmentation | Allied work of OHR & HDPE Pipeline for Augmentation of Jalangi Zone-II Part-A ground water based PWSS to accommodate FHTC in Jalangi Block in the district of Murshidabad under Murshidabad Division P.H.E. Dte. | 183/MURD | 18/01/2024 | 90 | MAMATA USHA ENTERPRISE | 123.49 | 121.21 | 100 | 90
3824 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10633 | Augmentation | Material Requisition To Resource Division | 305/MURD | 29/01/2024 | 0 | Resource Division | 22.47 | 0 | 0 | 0
3825 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10633 | Augmentation | Material Requisition To Resource Division | MURD/2481/02 | 04/09/2024 | 0 | Resource Division | 24.04 | 0 | 0 | 0
3826 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10633 | Augmentation | addl service connection charges at sahebrampur colony ,jalangi pwss part A,,z 2, ph 2, ID 860279299 | 209/WBSEDCL-JJM | 02/01/2024 | 0 | WBSEDCL | 3.77 | 0 | 0 | 0
3827 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10633 | Augmentation | Addl quotation for sahebrampur jalangi CCC ID860281601 | 247/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 11.14 | 0 | 0 | 0
3828 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10633 | Augmentation | Formal Work Order for Augmentation of Jalangi Zone-II / Part-A Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Jalangi Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 2372/MURD | 16/08/2022 | 958 | MAMATA USHA ENTERPRISE | 670.9 | 475.67 | 70.9 | 100
3829 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- II/A to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10633 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-II/ Part-A Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3054/MURD | 17/11/2022 | 45 | MAMATA USHA ENTERPRISE | 23.58 | 18.81 | 100 | 1
3830 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11715 | Augmentation | Formal Work order for Hiring of Maxicab ( Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on Daily hire basis for official use of the Dy Superintending Engineer, Murshidabad Circle,PHE Dte.[Period for 01(One) Year] for the month of April?2022 to March?2023 | 894/MURD | 05/04/2022 | 365 | SOUMYADIP MISRA | 4.78 | 1.83 | 38.19 | 1
3831 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11715 | Augmentation | Formal work order for Construction 250 Cum OHR & Rising Main in Connection with Augmentation of Dogachhi Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Samserganj Block of Murshidabad District under Murshidabad Division, PHE.Dte. [ (i)Amount for R. Main: Rs. 6,69,620.00 & (ii) Amount for OHR : Rs. 98,29,869.00] | 134/MURD | 16/01/2023 | 365 | IOTA CONSTRUCTION | 104.46 | 0 | 0 | 0
3832 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11715 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I , II and III OF ZONE-II under Dogachhi ground water based water supply scheme under Block_ SAMSERGANJ Dist. - Murshidabad under MEDB, PHE Dte. | 2087/MEDB | 19/06/2023 | 92 | ORIENTAL ENGINEERING CO. | 31.45 | 0 | 0 | 0
3833 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11715 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 4.03 | 100 | 100
3834 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11715 | Augmentation | Geotechnical study of underground formation of the proposed Over Head Reservoir of Dogachhi (Zone-II) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | 139/MURD | 16/01/2024 | 30 | IOTA CONSTRUCTION | 2.48 | 0 | 0 | 0
3835 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11715 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dogachhi Zone -II Water Supply Scheme at Head Work Site, 2nd Site & 3 r d site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | 1742/MURD | 06/07/2023 | 635 | NADIA TUBEWELLS | 35.34 | 0 | 0 | 33
3836 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11715 | Augmentation | Overhauling of 350 Cum Capacity, 20 mtr staging height (Shaft Wall) R.C.C. Elevated Reservoir, Repairing of Pump House & Boundary Wall, Laying of Distribution System to accommodate of FHTC work at Alamsahi village, Balbalpara village, Laskarpur village(80%) & Mahisha Thali Village for Augmentation work of Dogachhi Zone-II Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | 1949/MURD | 04/07/2024 | 303 | MOTI INDUSTRIES | 93.51 | 15.35 | 16.41 | 40
3837 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11715 | Augmentation | Laying of Distribution System for Augmentation of DOGACHHI (ZONE-II) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | 1891/MURD | 01/07/2024 | 365 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 77.48 | 0 | 0 | 40
3838 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11715 | Augmentation | Laying of Rising Main & Distribution System (PART-B) for Augmentation of DOGACHHI (ZONE-II) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad. | 229/MURD | 27/01/2025 | 90 | M/S GUNGUN CONSTRUCTION | 89.6 | 0 | 0 | 0
3839 | MURSHIDABAD | Murshidabad Division | Augmentation of Dogachhi Zone - II Pipe Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/11715 | Augmentation | Laying of balance work of HDPE pipe Risingmain and construction of approach road at Head Works Site of Dogachhi ( Zone-I) Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. | 282/MURD | 27/01/2021 | 30 | HARUN ALL RASHID & BROTHERS | 4.96 | 5.11 | 100 | 1
3840 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Chaitanyapur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Blo , SM/08908 | Retrofitting | Material Requisition To Resource Division | 139/BD-I | 10/02/2022 | 0 | Resource Division | 28.46 | 0 | 0 | 0
3841 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Chaitanyapur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Blo , SM/08908 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naoda, Sahapur, Ratanpur, Betberia, Kheali, Palaighata, Jafrabad, Sattarpur, Chaitanyapur & Bhadur (Village code 315568, 315569, 315570, 315571, 315572, 315574, 315575, 315576, 315577 & 315579) under Chaitanyapur (Zone-C) Water Supply Scheme of Beldanga -I Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 104/BD-I | 01/02/2022 | 180 | M/S JAN MAHAMMAD | 318.48 | 300.19 | 94.26 | 1
3842 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Chaitanyapur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Blo , SM/08908 | Retrofitting | Trial run of distribution system pipeline (CI/DI/UPVC/HDPE) and allied works at Chaitanyapur Surface based water supply (under Central Sector Part-II) Scheme under JJM for uncovered arsenic affected area of Beldanga-I under Berhampore Division-I, PHE Dte Period for 3 Months. | 283/BD-I | 20/02/2024 | 90 | JAMIRUL CONSTRUCTION | 6.67 | 6.62 | 100 | 100
3843 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. , SM/10811 | Augmentation | Construction 400 Cum OHR for Augmentation of Sekendra Ground water based Piped water supply scheme in Raghunathganj -II Block under Murshidabad Division, PHE.Dte | 944/MURD | 05/04/2023 | 365 | PRODEEP KUMAR GHOSH | 132.12 | 52.91 | 40.05 | 50
3844 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. , SM/10811 | Augmentation | Material Requisition To Resource Division | 495/MURD/09 | 15/02/2024 | 0 | Resource Division | 33.66 | 0 | 0 | 0
3845 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. , SM/10811 | Augmentation | Formal work order for Laying Distribution System ,FHTC, Construction of 1 (one) no Pump House (4.25m x 3.60m with sanitary and Water Supply Arrangement), Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement and 2(two) nos Pump House repairing. Repairing of Existing OHR Part for Augmentation of SEKENDRA PWSS in Raghunathganj-II Block , Jangipur Sub-Division under Murshidabad Division ,PHE. Dte. | 445/MURD | 17/02/2023 | 846 | NAYLA CONSTRUCTION | 255.21 | 164.88 | 68.95 | 90
3846 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. , SM/10811 | Augmentation | Providing Functional Household Tap Connections ( 200 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Taraf Rasulpur ( Village Code -314679) and Sekendra ( Village Code -314064) under P.T Rasulpur & Sekendra Ground Water Based Water Supply Scheme under Murshidabad Division P.H.E Dte. | 2211/MURD | 02/08/2024 | 30 | PRAVAT KUMAR GHOSH | 7.3 | 0 | 0 | 0
3847 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. , SM/10811 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. Dist. - Murshidabad under MEDB, PHE Dte. | 336/MEDB | 10/02/2025 | 89 | DAS ENTERPRISE (CHOA) | 23.19 | 0 | 0 | 0
3848 | MURSHIDABAD | Murshidabad Division | AUGMENTATION & REJUVENATION OF SEKENDARA WATER SUPLY SCHEME OF RAGHUNATHGANJ-II BLOCK OF MUSHIDABAD DISTRICT. , SM/10811 | Augmentation | Construction of Boundary wall of 60 m length and pumphouse (5.9 m x 4.825 m) at site no 4 at Sekendra Pwss in Raghunathganj-II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 1246/MURD | 29/05/2025 | 60 | KALACHAND DAS | 19.25 | 0 | 0 | 0
3849 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. , SM/12585 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DAKSHIN SAHAR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1077/BD-I | 29/09/2022 | 10 | NATSOL CONSULTANT | 2.71 | 2.71 | 100 | 0
3850 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. , SM/12585 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of DAKSHIN SAHAR ground water based water supply scheme under Block- Bhagawangola-II, Dist. Murshidabad under MEDB, PHE Dte. | 3728/MEDB | 03/11/2023 | 92 | JOY BISHNU ENGINEERING CO. | 12.42 | 0 | 0 | 0
3851 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. , SM/12585 | Augmentation | Repair And Renovation Works Of OHR (450 Cum) forDakshinSahar water supply scheme of Bhagwangola-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 1027/BD-I | 01/11/2023 | 30 | DEBJIT DAS | 7.5 | 0 | 0 | 0
3852 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. , SM/12585 | Augmentation | Dakshin Sahar PWSS to accommodate construction of Pump House Cum Chlorine Room, Boundary Wall and Service Road, under Jal Jivan Mission of BHAGWANGOLA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1528/BD-I | 19/09/2024 | 60 | GITA CONSTRUCTION | 32.4 | 0 | 0 | 0
3853 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. , SM/12585 | Augmentation | Material Requisition To Resource Division | 196/BD-I/2 | 09/02/2024 | 0 | Resource Division | 41.96 | 0 | 0 | 0
3854 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. , SM/12585 | Augmentation | Augmentation of Dakshin Sahar Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagawangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte.(PART-A) | 103/BD-I | 04/05/2023 | 1098 | RAJ KUMAR MONDAL | 352.91 | 0 | 0 | 10
3855 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. , SM/12585 | Augmentation | Augmentation of Dakshin Sahar Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagawangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte.(Part-B) | 105/BD-I | 08/05/2023 | 1089 | A ONE CONSTRUCTION | 303.14 | 92.05 | 30.37 | 50
3856 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. , SM/12585 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Dakshin Sahar ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | 1412/BD-I | 04/01/2023 | 10 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 3.61 | 2.46 | 100 | 100
3857 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. , SM/12585 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Dakshin Sahar Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 67/BD-I | 27/04/2023 | 30 | SUJIT KUMAR SAHA | 9 | 0 | 0 | 100
3858 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Sahar to Accommodate FHTC. , SM/12585 | Augmentation | DAKSHINSAHAR PART-A PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BHAGAWANGOLA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 462/BD-I | 15/03/2024 | 480 | RELIABLE ENTERPRISE | 21.99 | 0 | 0 | 100
3859 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Melanpur, Durgapur (314744,314745,314746,314747,314753,314754,314755,314756) of Purusottampur under ground w , SM/11216 | Augmentation | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Melanpur, Durgapur (314744, 314745, 314746, 314747, 314753, 314754, 314755, 314756 of Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block of Murshidabad District under Murshidabad Division Phe Dte. | 1211/MURD | 10/05/2022 | 60 | SOURAV DEY | 32.44 | 0 | 0 | 0
3860 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) of Mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Melanpur, Durgapur (314744,314745,314746,314747,314753,314754,314755,314756) of Purusottampur under ground w , SM/11216 | Augmentation | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Melanpur (Village code 314755) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad. | 532/MURD | 04/02/2021 | 60 | BHOWMIK CONSTRUCTION | 3.72 | 0 | 0 | 0
3861 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Bilpachakopra (314584) of Nabipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block of Murshidabad District under Murshidabad Divisio , SM/11218 | Augmentation | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bilpachakopra ( Village Code -314584) under Nabipur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184055). | 575/MURD | 09/02/2021 | 60 | NOVELTY CONSTRUCTION | 29.68 | 0 | 0 | 0
3862 | MURSHIDABAD | Berhampore Mechanical | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Bilpachakopra (314584) of Nabipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block of Murshidabad District under Murshidabad Divisio , SM/11218 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation & Functional Household Tap Connections (FHTC) of Mouza Bilpachakopra (314584) Pump House No.-I and II under Nabipur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block of Murshidabad District. | 769/MEDB | 20/02/2024 | 647 | JOY BISHNU ENGINEERING CO. | 23.48 | 0 | 0 | 50
3863 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Bilpachakopra (314584) of Nabipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - II Block of Murshidabad District under Murshidabad Divisio , SM/11218 | Augmentation | Sinking of 300x200 mm dia Rig Bore Tube Well With Pumphouse of Mouza Bilpachakopra (314584) of Nabipur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block of Murshidabad District under Murshidabad Division Phe Dte. | 1239/MURD | 11/05/2022 | 1056 | MAMATA USHA ENTERPRISE | 33.22 | 19.56 | 73.42 | 100
3864 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11565 | Augmentation | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Goghata ( Village Code -315526) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005186507) | 1699 / MURD | 07/07/2021 | 60 | M/S JAN MAHAMMAD | 52.35 | 19.67 | 37.58 | 1
3865 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11565 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (CHANDPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3277/MURD | 05/10/2021 | 60 | RADIANT | 14.82 | 4.84 | 100 | 1
3866 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11565 | Augmentation | Material Requisition To Resource Division | 1278/MURD/6 | 10/05/2023 | 0 | Resource Division | 34.53 | 0 | 0 | 0
3867 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11565 | Augmentation | Material Requisition To Resource Division | 112/MURD/04 | 11/01/2024 | 0 | Resource Division | 40.95 | 0 | 0 | 0
3868 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11565 | Augmentation | Material Requisition To Resource Division | 305/MURD/05 | 29/01/2024 | 0 | Resource Division | 22.9 | 0 | 0 | 0
3869 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- I ) PART -B TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11565 | Augmentation | Formal work order for Augmentation of CHANDPUR Zone-I / Part-B Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 1808/MURD | 11/07/2022 | 905 | MODERN CONSTRUCTION | 178.55 | 131.4 | 82.59 | 100
3870 | MURSHIDABAD | Murshidabad Division | JUGASWARA AND ADJOINING MOUJAS PWSS , SM/13724 | New | Material Requisition To Resource Division | 1210/MURD/37 | 02/05/2023 | 0 | Resource Division | 1.42 | 0 | 0 | 0
3871 | MURSHIDABAD | Murshidabad Division | JUGASWARA AND ADJOINING MOUJAS PWSS , SM/13724 | New | Material Requisition To Resource Division | 112/MURD/03 | 11/01/2024 | 0 | Resource Division | 4.88 | 0 | 0 | 0
3872 | MURSHIDABAD | Berhampore Mechanical | JUGASWARA AND ADJOINING MOUJAS PWSS , SM/13724 | New | NEW SERVICE CONNECTION AT PWSS PH 2 JUGASWARA ID 304240283 | 312/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 9.89 | 0 | 0 | 0
3873 | MURSHIDABAD | Berhampore Mechanical | JUGASWARA AND ADJOINING MOUJAS PWSS , SM/13724 | New | NEW SERVICE CONNECTION AT PWSS PH1 JUGASWARA ID 304240312 | 311/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 4.88 | 0 | 0 | 0
3874 | MURSHIDABAD | Murshidabad Division | JUGASWARA AND ADJOINING MOUJAS PWSS , SM/13724 | New | Formal Work Order ForConstruction of 100 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of JUGASWARA PWSS in Burwan Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362271S000) [(i)Amount for LDS , R.Main & FHTC: Rs.1,38,33,206.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs. 1,13,02,060.00] | 416/MURD | 15/02/2023 | 730 | SHYAMAL KUMAR SAHA | 251.3 | 106.37 | 42.33 | 90
3875 | MURSHIDABAD | Murshidabad Division | JUGASWARA AND ADJOINING MOUJAS PWSS , SM/13724 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JUGASWARA PWSS at Head Work Site & 2nd Tube Well Site in Burwan Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 485/MURD | 20/02/2023 | 45 | NADIA TUBEWELLS | 16.81 | 15.07 | 100 | 100
3876 | MURSHIDABAD | Murshidabad Division | JUGASWARA AND ADJOINING MOUJAS PWSS , SM/13724 | New | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Kandi Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(89 Nos.) | 2635/MURD | 23/09/2024 | 281 | SABSAMAY | 9.85 | 0 | 0 | 80
3877 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11792 | Augmentation | Construction of new Boundary wall with R.B.T fencing with approach road (Pump No-II) under Godhanpara Zone-II Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. | 275/ISD. | 03/06/2021 | 60 | AJOY GHOSH | 4.52 | 4.52 | 99.94 | 1
3878 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11792 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Godhanpara PWSS Scheme, Block - Raninagar-II) to be Augmentation/ Rejuvination under Murshidabad Division P.H.E. Dte. | 2744/MURD | 03/09/2021 | 60 | RADIANT | 11.27 | 3.76 | 100 | 0
3879 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11792 | Augmentation | Material Requisition To Resource Division | 3052/B/MURD | 17/11/2022 | 0 | Resource Division | 18.01 | 0 | 0 | 0
3880 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11792 | Augmentation | Material Requisition To Resource Division | 1278/MURD/11 | 10/05/2023 | 0 | Resource Division | 14.88 | 0 | 0 | 0
3881 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11792 | Augmentation | Shifting of 11KV HTOH line at Godhanpara W/S scheme, P.H-I, Z-II. | 70/WBSEDCL-JJM | 18/07/2023 | 0 | WBSEDCL | 3.27 | 0 | 0 | 0
3882 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11792 | Augmentation | NEW SERVICE CONNECTION AT GODHANPARA Z2 PH 2, ID304232744 | 281/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.68 | 0 | 0 | 0
3883 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11792 | Augmentation | NEW SERVICE CONNECTION GODHANPARA Z2 PH3 ID 304495842 |  | 25/11/2024 | 0 | WBSEDCL | 8.95 | 0 | 0 | 0
3884 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED GODHANPARA PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11792 | Augmentation | Formal work order for Laying of Distribution system, Rising Main, Sub-soil Investigation and construction of OHR (400 cum) and construction of Boundary wall and repairing of Pump-House in connection with Augmentation of Godhanpara Zone-II water supply scheme under Murshidabad Division, PHE Dte. | 3032/MURD | 16/11/2022 | 1094 | M/S GUHA & ROY ENTERPRISE | 412.1 | 316.82 | 76.88 | 80
3885 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08112 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of RUKUNPUR (Village code 315481) under Rukunpur (Zone-G) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte | 976/BD-I | 17/12/2020 | 180 | PRADIP KUMAR DAS | 235.52 | 246.56 | 104.69 | 1
3886 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08112 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 77.23 | 1
3887 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08112 | Retrofitting | Material Requisition To Resource Division | 2096/BD-I/10 | 25/11/2024 | 0 | Resource Division | 12.32 | 0 | 0 | 0
3888 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08112 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Pratappur (Village code 315480) under Rukunpur (Zone-G) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 232/BD-I | 10/02/2021 | 1993 | M/S GOUTAM CHAKRABORTY | 130.13 | 103.4 | 79.46 | 1
3889 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08112 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Biharia (Village code 315478) under Rukunpur (Zone-G) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 237/BD-I | 10/02/2021 | 180 | UNIVERSAL CONSTRUCTION | 160.94 | 154.25 | 95.84 | 0
3890 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08112 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khanpur,Hamdampur,Pilkhana and Matijhil (Village code 314845,314846,314850,314848) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 1812/BD-I | 05/10/2021 | 100 | M/S GUHA AND ROY ENTERPRISE | 95.07 | 53.67 | 100 | 1
3891 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08112 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tehatta (village code 315479) under RUKUNPUR ( Zone - G ) Surface Water based Water Supply Scheme of Central Sector Part - II Murshidabad District under Berhampore Division - I, PHE Dte. | 1835/BD-I | 05/10/2021 | 60 | PARTHA PRATIM DAS | 49.71 | 26.51 | 53.32 | 1
3892 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08112 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-57C/5576 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2024 to 31.12.2024. | 1282/BD-I | 27/12/2023 | 366 | SEBAYAN CONSTRUCTION | 1.81 | 4.79 | 264.03 | 30
3893 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08112 | Retrofitting | Additional and balance work of HDPE pipe for house service connection for retrofitting FHTC and relaying of damage and Laying of extension different dia UPVC pipeline in connection to Jal Jeevan Mission & Jal Swapna under command area of village Rukunpur ( village code-315481 ) under Rukunpur (Zone -G )Surface Water Supply Scheme of Central Sector Part-II of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1846/BD-I | 07/10/2021 | 60 | DAS TRADING CO | 50.67 | 50.64 | 100 | 1
3894 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08112 | Retrofitting | Laying of different dia UPVC distribution pipe Line in connection with JJM (Jal Jeevan Mission) on damaged portion and Rukunpur Satsang Kandra with alied works of Rukunpur (Zone-G) based water supply scheme under CS Part-II of BD-I, P.H.E Dte | 86/BD-I | 03/05/2023 | 30 | CHATTERJEE ENTERPRISE | 2.89 | 2.81 | 100 | 100
3895 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08112 | Retrofitting | Additional work of providing retrofitting functional household tap connetion (FHTC) in connection with JJM and Jal Swapna under command area of village Tehatta (village code 315479) under Rukunpur (Zone-G) surface water based water supply scheme of central sector part-II under Berhampore Division-I PHE Dte. | 147/BD-I | 05/02/2024 | 60 | PARTHA PRATIM DAS | 3.36 | 3.34 | 100 | 100
3896 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Rukunpur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par , SM/08112 | Retrofitting | Interconnection between delivery of OHR main and distribution system at OHR site and construction of different dia sluice valve chamber under Rukunpur water supply scheme of central sector part-II under JJM under Berhampore Division-I, PHE Dte. | 443/BD-I | 15/03/2024 | 30 | CHATTERJEE ENTERPRISE | 1.94 | 1.73 | 100 | 50
3897 | MURSHIDABAD | Berhampore Mechanical | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS , SM/13488 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under UDAYCHANDPUR ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte | 1882/MEDB | 16/06/2023 | 92 | MENAKA ENTERPRISE | 24.41 | 0 | 0 | 0
3898 | MURSHIDABAD | Murshidabad Division | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS , SM/13488 | New | Material Requisition To Resource Division | 1210/MURD/40 | 02/05/2023 | 0 | Resource Division | 26.76 | 0 | 0 | 0
3899 | MURSHIDABAD | Murshidabad Division | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS , SM/13488 | New | Formal work order for Construction of 300 Cum OHR, Laying Distribution System (PART-A), Rising Main, FHTC, for Uncovered of UDAY CHANDPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | 793/MURD | 21/03/2023 | 365 | M/S. SINHA & SONS | 363.73 | 42.49 | 11.68 | 10
3900 | MURSHIDABAD | Murshidabad Division | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS , SM/13488 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UDAY CHANDPUR PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte.. | 3407/MURD | 22/12/2022 | 45 | MAMATA USHA ENTERPRISE | 16.82 | 14.97 | 100 | 80
3901 | MURSHIDABAD | Berhampore Mechanical | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS , SM/13488 | New | NEW CONNECTION AT UDAYCHANDPUR PH-I | 461/WBSEDCL-JJM | 18/03/2024 | 0 | WBSEDCL | 5.84 | 0 | 0 | 0
3902 | MURSHIDABAD | Murshidabad Division | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS , SM/13488 | New | Formal work order for Construction of Boundwary Wall, Pump House & Laying Distribution System(PART-B) Uncovered of UDAY CHANDPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE. Dte. | 385/MURD | 10/02/2023 | 964 | MARUTI CONSTRUCTION AND CO. | 158.53 | 116.9 | 73.74 | 35
3903 | MURSHIDABAD | Murshidabad Division | UDAYCHANDPUR AND ADJOINING MOUJAS PWSS , SM/13488 | New | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 3.9 | 100 | 100
3904 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. , SM/12822 | Augmentation | Material Requisition To Resource Division | 196/BD-I/14 | 09/02/2024 | 0 | Resource Division | 34.78 | 0 | 0 | 0
3905 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. , SM/12822 | Augmentation | NEW CONNECTION AT SUNDARPUR PH-I | 110/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 7.33 | 0 | 0 | 0
3906 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. , SM/12822 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Sundarpur ground water based water supply scheme under Block_ Bhagwangola-I Dist. - Murshidabad under MEDB, PHE Dte. | 3735/MEDB | 03/11/2023 | 182 | M/S JIT ENTERPRISE | 22.36 | 9.98 | 44.62 | 7
3907 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. , SM/12822 | Augmentation | Balance work for the work of Augmentation of Sundarpur Piped water supply scheme to accommodate construction of Pump House ,Boundary Wall, Service Road and laying of distribution of pipeline under Jal Jeevan Mission within Bhagwangola -I Block of Murshidabad District under Berhampore Division -I PHE. Dte. | 1474/BD-I | 06/09/2024 | 60 | M/S TAPAS KUMAR CHAKRABORTY | 89.63 | 0 | 0 | 0
3908 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. , SM/12822 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Sundarpur ground water supply scheme in Bhagwabgola-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | 949/BD-I | 18/07/2025 | 300 | M/S S. DAS & ENTERPRISE | 122.8 | 0 | 0 | 0
3909 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. , SM/12822 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SUNDARPUR Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 265/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.68 | 2.68 | 100 | 100
3910 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. , SM/12822 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Sundarpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | 1439/BD-I | 16/01/2023 | 30 | M/S RAMI CONSTRUCTION | 1.81 | 0 | 0 | 100
3911 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. , SM/12822 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sundarpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | 1807/BD-I | 31/03/2023 | 900 | SUJIT KUMAR SAHA | 18.01 | 6.99 | 48.18 | 50
3912 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. , SM/12822 | Augmentation | Allied work for the work of Augmentation of Sundarpur Piped water supply scheme to accommodate construction of OHR, pump house, boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission and Bhagwangola-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | 859/BD-I | 07/09/2023 | 30 | M/S TAPAS KUMAR CHAKRABORTY | 29.77 | 29.75 | 100 | 100
3913 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. , SM/12822 | Augmentation | Repair And Renovation Works Of R.C.C Elevated Reservoir (350 Cum) for Sundarpur water supply scheme of Bhagwangola-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | 1071/BD-I | 21/11/2023 | 30 | HAFIZUL SK | 8.51 | 8.35 | 100 | 100
3914 | MURSHIDABAD | Murshidabad Division | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/13486 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 4.68 | 100 | 1
3915 | MURSHIDABAD | Berhampore Mechanical | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/13486 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Jorgachha ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | 3737/MEDB | 03/11/2023 | 182 | JAGANNATH ENTERPRISE | 22.14 | 0 | 0 | 0
3916 | MURSHIDABAD | Murshidabad Division | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/13486 | Augmentation | Material Requisition To Resource Division | 1278/MURD/14 | 10/05/2023 | 0 | Resource Division | 74.66 | 0 | 0 | 0
3917 | MURSHIDABAD | Berhampore Mechanical | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/13486 | Augmentation | JORGACHA PH-III | 434/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 8.45 | 0 | 0 | 0
3918 | MURSHIDABAD | Murshidabad Division | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/13486 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jorgacha Water Supply Scheme at Head Work Site, 2nd Site site at DOMKAL Block under Murshidabad Division, P.H. Engineering Dte | 1757/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 23.58 | 8.77 | 37.2 | 50
3919 | MURSHIDABAD | Murshidabad Division | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/13486 | Augmentation | Construction of Boundwary Wall , Pump House , PCC approach road , Land Development for Augmentation of Jorgacha PWSS in Domkol Block , Islampur Sub-Division under Murshidabad Division ,PHE. Dte. | 899/MURD | 23/04/2025 | 90 | EMCO CONSTRUCTION | 23 | 0 | 0 | 0
3920 | MURSHIDABAD | Murshidabad Division | Detailed Project Report for Augmentation of Jorgachha Piped Water Supply Scheme of Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/13486 | Augmentation | Formal work order for the work of Augmentation of JORGACHA Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE.Dte. | 365/MURD | 09/02/2023 | 926 | ULTRA CONSTRUCTION. | 272.97 | 153.1 | 79.7 | 100
3921 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. , SM/12738 | Augmentation | Augmentation of Diar Syampur Zone-I Piped water supply scheme to accommodate construction of OHR, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 671/BD-I | 09/08/2023 | 310 | S.K. CONSTRUCTION DEBKUNDU , P.S.- BELDANGA, | 121.57 | 0 | 0 | 0
3922 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. , SM/12738 | Augmentation | Material Requisition To Resource Division | 196/BD-I/7 | 09/02/2024 | 0 | Resource Division | 10.99 | 0 | 0 | 0
3923 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. , SM/12738 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DIAR SYAMPUR ZONE-I Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 263/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.37 | 2.35 | 100 | 100
3924 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. , SM/12738 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Diar Shyampur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | 1413/BD-I | 04/01/2023 | 10 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 2.36 | 1.52 | 100 | 100
3925 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. , SM/12738 | Augmentation | Improvement Works for RCC Elevated Reservoir (45 Cum) of Diar Shyampur Zone-I piped water supply scheme under JJM within Bhagwangola-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. | 1622/BD-I | 03/10/2024 | 97 | M/S. SOUMITRA MONDAL | 3.4 | 3.38 | 100 | 100
3926 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. , SM/12738 | Augmentation | Replacement of sand layers,Activated Alumina & existing gravel for Modified Sujapur Sadipur Model after washing of AIRP allied (Capacity 11.00 Cum/hr) at Diar Syampur Zone-I Water Supply Scheme under Jal Jivan Mission of Bhagwangola-II Block under Berhampore Div-I,Murshidabad PHE Dte. | 926/BD-I | 07/06/2024 | 30 | M/S GHOSH ENTERPRISE | 16.45 | 15.41 | 100 | 50
3927 | MURSHIDABAD | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS , SM/13931 | New | Material Requisition To Resource Division | 1210/MURD/32 | 02/05/2023 | 0 | Resource Division | 23.42 | 0 | 0 | 0
3928 | MURSHIDABAD | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS , SM/13931 | New | Material Requisition To Resource Division | 1936/MURD/5 | 19/07/2023 | 0 | Resource Division | 23.42 | 0 | 0 | 0
3929 | MURSHIDABAD | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS , SM/13931 | New | Material Requisition To Resource Division | 112/MURD/01 | 11/01/2024 | 0 | Resource Division | 13.66 | 0 | 0 | 0
3930 | MURSHIDABAD | Berhampore Mechanical | SANTOSHPUR AND ADJOINING MOUJAS PWSS , SM/13931 | New | AT SANTOSHPUR PH 1 ID 304252904 | 364/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 4.7 | 0 | 0 | 0
3931 | MURSHIDABAD | Berhampore Mechanical | SANTOSHPUR AND ADJOINING MOUJAS PWSS , SM/13931 | New | SANTOSHPUR PH 2 C ID 304252909 | 363/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 3.33 | 0 | 0 | 0
3932 | MURSHIDABAD | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS , SM/13931 | New | Formal work order for construction of 250 Cum OHR , Laying Distribution System (PART-A), Rising Main, FHTC, for Uncovered SANTOSHPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. [ (i) Amount for LDS , R.Main & FHTC: Rs.2,44,40,742.00 & (ii) Amount for OHR: Rs.1,03,92,477.00] | 480/MURD | 20/02/2023 | 1092 | S.&P. ENTERPRISE | 348.26 | 93.02 | 26.71 | 15
3933 | MURSHIDABAD | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS , SM/13931 | New | Formal work order for Laying Distribution System (PART-B), Construction of Boundary Wall & Pump house for Uncovered SANTOSHPUR PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. [ (i) Amount for Laying Distribution System: Rs.1,54,12,147.00 & (ii) Amount for Boundary Wall & Pump House: Rs. 41,19,886.00] | 176/MURD | 18/01/2023 | 1018 | MOTI RAHAMAN | 195.28 | 0 | 0 | 35
3934 | MURSHIDABAD | Murshidabad Division | SANTOSHPUR AND ADJOINING MOUJAS PWSS , SM/13931 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia Replacement tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SANTOSHPUR PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3415/MURD | 22/12/2022 | 45 | HARUN ALL RASHID & BROTHERS | 16.64 | 13.69 | 100 | 80
3935 | MURSHIDABAD | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14433 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of BRAHAMOTTAR MANIKCHAK ground water based water supply scheme under Block- LALGOLA, Dist. Murshidabad under MEDB, PHE Dte. | 3777/MEDB | 03/11/2023 | 92 | GANGULI ELECTRICAL CO. | 12.01 | 0 | 0 | 10
3936 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14433 | Augmentation | Material Requisition To Resource Division | 201/BD-1/9 | 10/02/2024 | 0 | Resource Division | 31.4 | 0 | 0 | 0
3937 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14433 | Augmentation | Material Requisition To Resource Division | 1510/BD-I/1 | 12/09/2024 | 0 | Resource Division | 4.13 | 0 | 0 | 0
3938 | MURSHIDABAD | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14433 | Augmentation | Quotation for Brahamatter PH-1 Application No- 3004544380 Ref ID- 304228570 | 240/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 7.62 | 0 | 0 | 0
3939 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14433 | Augmentation | Augmentation of Brohmottar Manikchak Piped water supply scheme to accommodate construction of OHR, Arsenic cum Iron Removal Plant (AIRP), boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | 848/BD-I | 05/09/2023 | 574 | M/S TAPAS KUMAR CHAKRABORTY | 458.37 | 103.88 | 22.66 | 50
3940 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14433 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BRAHIMOTTAR MANIKCHAK Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 10/BD-I | 06/01/2025 | 15 | HARUN ALL RASHID & BROTHERS | 8.92 | 0 | 0 | 0
3941 | MURSHIDABAD | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14433 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | 385/MEDB | 12/02/2025 | 89 | SAMARPITA ENGINEERING | 12.11 | 0 | 0 | 0
3942 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14433 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BRAHAMOTTAR MANIKCHAK Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1685/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.6 | 2.62 | 100 | 1
3943 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14433 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Brahamottar Manikchak Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 126/BD-I | 12/05/2023 | 30 | HARUN ALL RASHID & BROTHERS | 8.9 | 7.76 | 100 | 100
3944 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BRAHAMOTTAR MANIKCHAK ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14433 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) of Ground water supply scheme for Brahamottar Manikchak of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 986/BD-I | 30/10/2023 | 479 | PROSENJIT DAS | 8.57 | 0 | 0 | 100
3945 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14830 | Augmentation | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chumarigacha (Village code 315340) under Basabari Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723194 in the District of Murshidabad | 3122 / MURD | 09/12/2020 | 60 | TANUSHREE ENTERPRISE | 39.34 | 1.16 | 100 | 1
3946 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14830 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BASABARI & CHHAIGHARI Water Supply Scheme at Head work site at BERHAMPORE Block under Murshidabad Division, P.H. Engineering Dte | 3875/MURD | 18/12/2023 | 21 | NADIA TUBEWELLS | 11.78 | 9.22 | 100 | 100
3947 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14830 | Augmentation | BASABARI PH-1 | 402/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 4.36 | 0 | 0 | 0
3948 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14830 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 4.3 | 200 | 1
3949 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14830 | Augmentation | Augmentation of Ground Water Based Basabari PWSS to accommodate FHTC of 673 nos household Laying Rising Main , Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works, Construction of Boundary Wall of 270 m and Soil Investigation & 250 Cum Construction of OHR at Berhampore Block within Murshidabad District under Murshidabad Division, PHE Dte.(Part-B) | 3180/MURD | 11/10/2023 | 730 | SAMBHU NATH ROY | 223.72 | 13.35 | 5.97 | 10
3950 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14830 | Augmentation | Water Supply arrangmenet for arsenic affected habitation with SOLAR Power connection at different block under Murshidabad Division, P.H.E. Dte. in the District of Murshidabad. (PART-C). | 503/MURD | 02/02/2021 | 60 | PAL TROCKNER (P) LTD. | 37.91 | 0 | 0 | 100
3951 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14830 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Berhampore Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | 3119/MURD | 29/11/2024 | 20 | SUJIT MONDAL | 7.27 | 0 | 0 | 0
3952 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14830 | Augmentation | Laying of Distribution System including Refixing the existing FHTCs connection on new distribution system of Basabari Ground Based piped water supply scheme of in Berhampore Block of Berhampore Sub-Division under Murshidabad Division, PHE Dte. | 511/MURD | 28/02/2025 | 60 | M/S. M.G. CONSTRUCTION | 40.27 | 0 | 0 | 0
3953 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14830 | Augmentation | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 0 | 75
3954 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14830 | Augmentation | Laying Distribution System For Augmentation of Basabari (Part-A) PWSS of Berhampore Block under Murshidabad Division ,PHE.Dte | 496/MURD | 21/02/2023 | 727 | SANDHAN ADHIKARI | 73.69 | 55.37 | 70.11 | 85
3955 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BASABARI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/14830 | Augmentation | Construction of Pump House cum Chlorine Room with sanitary and Water Supply Arrangement at Basabari PWSS at Berhampore Block under Berhampore Sub-Division under Murshidabad Division, PHE Dte. | 1989/MURD | 08/07/2024 | 186 | ANIRBAN CHATTERJEE | 7.39 | 0 | 0 | 100
3956 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13992 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,ZONE-I under HAFANIA ground water based water supply scheme under Block_ Suti-II Dist. - Murshidabad under MEDB, PHE Dte. | 1913/MEDB | 16/06/2023 | 92 | CONCORD ENGINEERING | 33.22 | 0 | 0 | 0
3957 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13992 | Augmentation | Material Requisition To Resource Division | 1230/MURD/04 | 04/05/2023 | 0 | Resource Division | 10.57 | 0 | 0 | 0
3958 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13992 | Augmentation | HAFANIA PH-I Z-1 | 339/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 3.64 | 0 | 0 | 0
3959 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13992 | Augmentation | SHIFTING OF HT LINE AT HAFANIA Z-I | 146/WBSEDCL-JJM | 08/07/2024 | 0 | WBSEDCL | 7.3 | 0 | 0 | 0
3960 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13992 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 231/4 & 231/5) on railway land of mouza Hafania & Connecting with existing 160 mm dia uPVC distribution main line of Hafania ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | 2480/MURD | 16/08/2021 | 60 | M/S NIRAPADA BHATTACHARJEE | 28.91 | 25.46 | 88.06 | 100
3961 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13992 | Augmentation | Formal Work Order for Augmentation of Ground Water Based HAFANIA (ZONE-I) PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | 745/MURD | 16/03/2023 | 747 | PAROMITA DEB | 416.04 | 188.63 | 45.34 | 40
3962 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13992 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Sujnipara Station to Nimtita Station (TP NO 230/6 & 230/7) at Hafania mouza & Connecting with existing 110 mm dia uPVC distribution main line of Hafania ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | 2481/MURD | 16/08/2021 | 60 | M/S NIRAPADA BHATTACHARJEE | 21.58 | 19.07 | 100 | 100
3963 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13992 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.51 | 100 | 100
3964 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HAFANIA ZONE-I PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13992 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 3.84 | 100 | 100
3965 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/13997 | Augmentation | Material Requisition To Resource Division | 1210/MURD/20 | 02/05/2023 | 0 | Resource Division | 27.82 | 0 | 0 | 0
3966 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/13997 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II, Zone-I under RATURI ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | 1918/MEDB | 16/06/2023 | 92 | MENAKA ENTERPRISE | 20.8 | 9.15 | 43.97 | 5
3967 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/13997 | Augmentation | Allied work for Road restoration damaged during laying of pipeline of Raturi Zone-I Piped Water Supply Scheme, Suti Block, Jangipur Sub-Division under Murshidabad Division, P.H.E dte. | 769/MURD | 13/03/2024 | 30 | S. DUTTA | 48.28 | 0 | 0 | 0
3968 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/13997 | Augmentation | Sinking of 1NO. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Raturi Zone-I Water Supply Scheme at Suti-I Block of Jangipur Division under Murshidabad Division, P.H.Engineering Dte. | 2957/MURD | 11/11/2024 | 15 | GAYEN ENTERPRISE | 11.73 | 0 | 0 | 0
3969 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/13997 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at RATURI ZONE -I Water Supply Scheme at Head Work Site, 2nd Site site at Suti-I Block under Murshidabad Division, P.H. Engineering Dte. | 3838/MURD | 14/12/2023 | 21 | SUJIT KUMAR SAHA | 11.79 | 8.82 | 100 | 50
3970 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/13997 | Augmentation | Sinking of 2NOS. 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Raturi Zone-II Water Supply Scheme and Bahutuli Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | 2195/MURD | 31/07/2024 | 30 | SARKAR WATER SUPPLY AGENCY | 23.56 | 9.8 | 100 | 50
3971 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/13997 | Augmentation | Rectification work from Raturi to Kalinagar in the road of Dangapara more to Raturi via HILORA, Kalinagar Road under berhampore Division-I PWD during the year of 2023-2024. | 468-MSD/2023-24 | 04/01/2024 | 0 | EXECUTIVE ENGINEER, PWD, BERHAMPORE DIVISION-I | 78.16 | 0 | 0 | 0
3972 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/13997 | Augmentation | Providing FHTC of 1415 nos. household, Laying of Rising Main, Repair & Renovation of RCC 130 Cum OHR, special repair and renovation of existing 2 (Two) Nos Pump House and Allied Works Augmentation work of Raturi (Zone-I) PWSS in SUTI-I Block under Murshidabad Division, PHE. Dte. | 1455/MURD | 01/06/2023 | 1080 | R.M. BHATTA | 91.23 | 12.74 | 13.97 | 15
3973 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED RATURI ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/13997 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.21 | 100 | 100
3974 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . , SM/15227 | Augmentation | Material Requisition To Resource Division | 196/BD-I/27 | 09/02/2024 | 0 | Resource Division | 31.44 | 0 | 0 | 0
3975 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . , SM/15227 | Augmentation | Augmentation of Ramnachandpur zone_IV Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in NAWDA Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 622/BD-I | 03/08/2023 | 821 | AJAY MONDAL | 277.49 | 0 | 0 | 20
3976 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . , SM/15227 | Augmentation | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of Ramnachandpur Zone-IV" ground water supply scheme in NAWDA Block,under Berhampore Division-I, P.H.E Dte(Capacity-52.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing | 996/BD-I | 20/06/2024 | 365 | M/S RUBIET HOSSAIN | 159.77 | 0 | 0 | 0
3977 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . , SM/15227 | Augmentation | RAMNACHANDRAPUR ZONE-IV to accommodate construction of Boundary Wall under Jal Jivan Mission of NAWDA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 451/BD-I | 15/03/2024 | 539 | PRAVAT KUMAR GHOSH | 21.46 | 0 | 0 | 95
3978 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . , SM/15227 | Augmentation | Construction Pump House Cum Chlorine Room at Head Work site of RAMNACHANDPUR ZONE-IV Water Supply Scheme under Jal Jevan Mission within Nawda Block under Berhampore Division-I, PHE.Dte. In the district of Murshidabad. | 282/BD-I | 12/02/2025 | 60 | MD NAJRUL ISLAM | 7.5 | 0 | 0 | 0
3979 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . , SM/15227 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at RAMNACHANDPUR ZONE - IV Water Supply Scheme( 1st & 2nd TW Site) within Nawda Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | 429/BD-I | 19/03/2025 | 30 | GENUINE | 18.02 | 0 | 0 | 0
3980 | MURSHIDABAD | Berhampore Division I | Augmentation of Ramnachandpur Zone-IV pipe water supply scheme . , SM/15227 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of RAMNACHANDPUR ZONE - IV PWSS under Jal Jeevan Mission within Nawda Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 598/BD-I | 22/04/2025 | 60 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 19 | 0 | 0 | 0
3981 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14923 | Augmentation | Material Requisition To Resource Division | 201/BD-1/10 | 10/02/2024 | 0 | Resource Division | 43.36 | 0 | 0 | 0
3982 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14923 | Augmentation | Material Requisition To Resource Division | 1510/BD-I/3 | 12/09/2024 | 0 | Resource Division | 2.27 | 0 | 0 | 0
3983 | MURSHIDABAD | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14923 | Augmentation | JUMRA NAYAGRAM PH-1 | 400/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 5.31 | 0 | 0 | 0
3984 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14923 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) of Ground water supply scheme for Jumra Nayagram of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 984/BD-I | 30/10/2023 | 30 | AJOY GHOSH | 8.56 | 0 | 0 | 0
3985 | MURSHIDABAD | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14923 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM (PART-B) ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | 328/MEDB | 10/02/2025 | 89 | MERCURY ENGINEERING CO | 22.71 | 0 | 0 | 0
3986 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14923 | Augmentation | Bored Cast-in-situ_M30_grade 450 mm. dia. 22.00 m (Shaft Length) R.C.C pile for construction of OHR at Head work site of Jhumra Nayagram Ground Piped Water Supply Scheme under Jal Jeevan Mission of Lalgola Block, Murshidabad district under Berhampore Division - I, PHE Dte. | 1302/BD-I | 07/08/2024 | 210 | AICH CONSTRUCTION | 26.19 | 0 | 0 | 100
3987 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14923 | Augmentation | Balance works i.c.w of Existing AIRP (Modified Sujapur Sadipur Model) capacity 53.12 cum/hr at Head Work Site of Jhumra Nayagram Water Supply Scheme under JJM within Lalgola block under Berhampore Division -I, P.H.E. Dte. In the district of Murshidabad. | 841/BD-I | 23/06/2025 | 30 | GITA CONSTRUCTION | 26.5 | 0 | 0 | 0
3988 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14923 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for JUMRA NAYAGRAM Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1683/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.6 | 2.6 | 100 | 1
3989 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14923 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jumra Nayagram Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte ( For 2 nos Tubewell) | 140/BD-I | 12/05/2023 | 695 | HARUN ALL RASHID & BROTHERS | 17.82 | 8.41 | 51.11 | 50
3990 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR JUMRA NAYAGRAM ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14923 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Jumra Nayagram ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) Augmentation of PWSS under Jal Jeevan Mission. | 1161/BD-I | 05/12/2023 | 30 | M/S. RAY ORDER SUPPLIER AND CONTRACTOR | 2.92 | 1.23 | 100 | 75
3991 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . , SM/14739 | Augmentation | Material Requisition To Resource Division | 61/BD-1/11 | 27/04/2023 | 0 | Resource Division | 26.29 | 0 | 0 | 0
3992 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . , SM/14739 | Augmentation | AT UDAY NAGAR DIAR PH 2 ID 304244356 | 373/WBSEDCL-JJM | 21/02/2024 | 0 | WBSEDCL | 3.85 | 0 | 0 | 0
3993 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . , SM/14739 | Augmentation | Augmentation of Udaynagar Diar Piped water supply scheme to accommodate construction of Pump House ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Jalangi Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1551/BD-I | 17/02/2023 | 720 | BISWAS CONSTRUCTION | 82.74 | 56.19 | 67.9 | 75
3994 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . , SM/14739 | Augmentation | Balance work of Boundary Wall at Augmentation of Udaynagar Diar PWSS of Jalangi Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | 984/BD-I | 19/06/2024 | 45 | BISWAS CONSTRUCTION | 11.94 | 0 | 0 | 0
3995 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . , SM/14739 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for UDAYNAGARDIAR Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1559/BD-I | 20/02/2023 | 10 | M/S SOBHA & CO | 2.53 | 2.48 | 100 | 100
3996 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . , SM/14739 | Augmentation | Repair And Renovation Works Of OHR (100 Cum) of Ground Water Based Supply Scheme for UdaynagarDiar of Jalangi block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | 1037/BD-I | 03/11/2023 | 665 | PRANAB KUMAR SAHA | 6.34 | 0 | 0 | 100
3997 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Udaynagar Diar . , SM/14739 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 21.62 Cum/hr.) with allied work at Udaynagar Diar Water Supply Scheme under Jal Jeevan Mission of Jalangi under Berhampore Division-I, PHEengineering Dte. | 924/BD-I | 07/06/2024 | 240 | SOUNAK ENTERPRISE | 15.21 | 0 | 0 | 100
3998 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KAKRAMARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK - SUTI-II , DISTRICT - MURSHIDABAD. , SM/14945 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 7.5 | 100 | 100
3999 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KAKRAMARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK - SUTI-II , DISTRICT - MURSHIDABAD. , SM/14945 | Augmentation | Material Requisition To Resource Division | 1219/MURD/29 | 03/05/2023 | 0 | Resource Division | 53.62 | 0 | 0 | 0
4000 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KAKRAMARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK - SUTI-II , DISTRICT - MURSHIDABAD. , SM/14945 | Augmentation | Augmentation of Ground Water Based KAKRAMARI (ZONE-I) &KAKRAMARI (ZONE-II) PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | 3288/MURD | 19/10/2023 | 180 | BIJAY CHOWDHURY | 861.6 | 93.88 | 23.92 | 35
4001 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KAKRAMARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK - SUTI-II , DISTRICT - MURSHIDABAD. , SM/14945 | Augmentation | Replacing of Filter media of Existing AIRP (Modified Sujapur Sadhipur Model ) of (Capacity 120 Cum/hr.) at Kankramari Water Supply Scheme of Jangipur Sub-Division under Murshidabad Division, PHEngineering Dte. | 744/MURD | 12/03/2024 | 60 | SUMAN ENTERPRISE AND SUMAN AQUA | 42.03 | 41.42 | 100 | 100
4002 | MURSHIDABAD | Murshidabad Division | MOLLA PIPED WATER SUPPLY SCHEME , SM/14947 | New | Material Requisition To Resource Division | 1210/MURD/42 | 02/05/2023 | 0 | Resource Division | 32.6 | 0 | 0 | 0
4003 | MURSHIDABAD | Berhampore Mechanical | MOLLA PIPED WATER SUPPLY SCHEME , SM/14947 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under MOLLA ground water based water supply scheme under Block_ Kandi, Dist. - Murshidabad under MEDB, PHE Dte. | 1891/MEDB | 16/06/2023 | 776 | S.P. ENTERPRISE (SILIGURI) | 23.4 | 0 | 0 | 30
4004 | MURSHIDABAD | Berhampore Mechanical | MOLLA PIPED WATER SUPPLY SCHEME , SM/14947 | New | AT MOLLA PH2 ID 304252910 | 359/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 5.41 | 0 | 0 | 0
4005 | MURSHIDABAD | Berhampore Mechanical | MOLLA PIPED WATER SUPPLY SCHEME , SM/14947 | New | AT MOLLA PH 1 ID 304252903 | 358/WBSEDCL-JJM | 20/02/2024 | 0 | WBSEDCL | 3.88 | 0 | 0 | 0
4006 | MURSHIDABAD | Murshidabad Division | MOLLA PIPED WATER SUPPLY SCHEME , SM/14947 | New | Formal Work Order For Construction of 150 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Laying Distribution System, Rising Main, FHTC, Boundary wall of MOLLA PWSS in Kandi Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. ( Scheme ID -PH222362345S000) [(i)Amount for LDS , R.Main & FHTC: Rs.1,98,91,791.00 & (ii) Amount for OHR, Boundwary Wall & Pump House : Rs. 1,23,31,559.00] | 415/MURD | 15/02/2023 | 1141 | M/S NIRAPADA BHATTACHARJEE | 322.07 | 15.96 | 4.95 | 5
4007 | MURSHIDABAD | Murshidabad Division | MOLLA PIPED WATER SUPPLY SCHEME , SM/14947 | New | Sinking of 02(Two) Nos 250mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MOLLA PWSS at Head Work Site & 2nd Tube Well Site in Kandi Block under Kandi Sub-Division, Murshidabad Division,P.H.Engineering Dte. | 381/MURD | 10/02/2023 | 45 | NADIA TUBEWELLS | 16.81 | 15.53 | 100 | 95
4008 | MURSHIDABAD | Murshidabad Division | MOLLA PIPED WATER SUPPLY SCHEME , SM/14947 | New | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 3.79 | 100 | 100
4009 | MURSHIDABAD | Murshidabad Division | Augmentation of Natial Rajnagar Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/15069 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 5.23 | 100 | 1
4010 | MURSHIDABAD | Murshidabad Division | Augmentation of Natial Rajnagar Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/15069 | Augmentation | Material Requisition To Resource Division | 1219/MURD/40 | 03/05/2023 | 0 | Resource Division | 69.3 | 0 | 0 | 0
4011 | MURSHIDABAD | Murshidabad Division | Augmentation of Natial Rajnagar Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/15069 | Augmentation | Material Requisition To Resource Division | 526/MURD/05 | 19/02/2024 | 0 | Resource Division | 14.88 | 0 | 0 | 0
4012 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Natial Rajnagar Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/15069 | Augmentation | SHIFTING OF HT LINE AT RAJAPUR ID 860296030 | 17/WBSEDCL-JJM | 16/04/2024 | 0 | WBSEDCL | 4.36 | 0 | 0 | 0
4013 | MURSHIDABAD | Murshidabad Division | Augmentation of Natial Rajnagar Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/15069 | Augmentation | Augmentation of NATIAL RAJANAGAR ZONE-I ,II,& III Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Raninagar -II Block of Murshidabad District under Murshidabad Division, PHE. Dte. | 2724/MURD | 29/08/2023 | 765 | M/S. MOHAN LAL JAIN | 2092.12 | 615.3 | 91.17 | 56
4014 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Natial Rajnagar Zone-I Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/15069 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Natial Rajanagar Zone-I Piped water supply scheme Block_Jalangi Dist_Murshidabad under MEDB PHE Dte. | 350/MEDB | 10/02/2025 | 89 | KARTICK BAL | 45.27 | 0 | 0 | 0
4015 | MURSHIDABAD | Berhampore Mechanical | EROALI AND ADJOINING MOUJAS PWSS , SM/14236 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under EROALI ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | 3788/MEDB | 03/11/2023 | 92 | DEBJYOTI BASU | 35.17 | 0 | 0 | 0
4016 | MURSHIDABAD | Murshidabad Division | EROALI AND ADJOINING MOUJAS PWSS , SM/14236 | New | Material Requisition To Resource Division | 1004/MURD/11 | 17/04/2023 | 0 | Resource Division | 47.05 | 0 | 0 | 0
4017 | MURSHIDABAD | Murshidabad Division | EROALI AND ADJOINING MOUJAS PWSS , SM/14236 | New | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 7.69 | 100 | 80
4018 | MURSHIDABAD | Murshidabad Division | EROALI AND ADJOINING MOUJAS PWSS , SM/14236 | New | Material Requisition To Resource Division | MURD/439/1 | 08/02/2024 | 0 | Resource Division | 27.28 | 0 | 0 | 0
4019 | MURSHIDABAD | Berhampore Mechanical | EROALI AND ADJOINING MOUJAS PWSS , SM/14236 | New | Eroali PH-1 Application No- 3004536843 | 241/WBSEDCL-JJM | 15/01/2024 | 0 | WBSEDCL | 3.74 | 0 | 0 | 0
4020 | MURSHIDABAD | Berhampore Mechanical | EROALI AND ADJOINING MOUJAS PWSS , SM/14236 | New | POWER CONNECTION AT PWSS PH 2 EROLI ID 304250314 | 45/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 4.22 | 0 | 0 | 0
4021 | MURSHIDABAD | Berhampore Mechanical | EROALI AND ADJOINING MOUJAS PWSS , SM/14236 | New | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Khargram and Nawda block Under District Murshidabad under MEDB PHE Dte. | 45/4 | 29/05/2025 | 92 | EASTERN INDIA SALES & SERVICE | 15.17 | 0 | 0 | 0
4022 | MURSHIDABAD | Murshidabad Division | EROALI AND ADJOINING MOUJAS PWSS , SM/14236 | New | Formal work order for the work of EROALI & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362274S000) | 90/MURD | 11/01/2023 | 841 | M/S. S. DAS AND ENTERPRISE | 833.44 | 306.53 | 36.78 | 38
4023 | MURSHIDABAD | Murshidabad Division | Augmentation of Jot Sundar Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/16243 | Augmentation | Work of Interconnection of D.I pipe line between 2nd Tube well Pump house to Rising main at Jot Sundar Water Supply Scheme under Jangipur Sub-Division P.H.Engineering Dte. | 386/JSD | 31/12/2021 | 30 | SAMAR MUKHERJEE | 1.9 | 1.9 | 100 | 0
4024 | MURSHIDABAD | Murshidabad Division | Augmentation of Jot Sundar Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/16243 | Augmentation | Material Requisition To Resource Division | 1167/MURD/50 | 28/04/2023 | 0 | Resource Division | 9.38 | 0 | 0 | 0
4025 | MURSHIDABAD | Murshidabad Division | Augmentation of Jot Sundar Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/16243 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 100 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and Boundary wall and approach road for Augmentation of Jotsundar PWSS in Raghunathganj-II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | 2771/MURD | 01/09/2023 | 730 | M/S AFSHAN CONSTRUCTION | 265.01 | 35.37 | 13.35 | 21
4026 | MURSHIDABAD | Murshidabad Division | Augmentation of Jot Sundar Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/16243 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jot Sundar Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Raghunathganj-II Block under Murshidabad Division, P.H.Engineering Dte. | 3808/MURD | 12/12/2023 | 21 | NILAVA GHOSHAL (BUMBA) | 23.54 | 21.23 | 100 | 100
4027 | MURSHIDABAD | Murshidabad Division | Augmentation of Jot Sundar Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/16243 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Raghunathganj-II of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Giriya Kismat Water supply Scheme, Jotsundar Water Supply Scheme, Giria Water Supply Scheme Zone-I & II. | 2912/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 12.39 | 2.49 | 74.81 | 100
4028 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Jot Sundar Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/16243 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Jot Sundar Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad Dist. - Murshidabad under MEDB, PHE Dte. | 338/MEDB | 10/02/2025 | 89 | HANNAN BUILDERS PVT LTD | 22.72 | 0 | 0 | 0
4029 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-III IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16265 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-III under MURADPUR JALANGI ground water based water supply scheme under Block_ JALANGI Dist. - Murshidabad under MEDB, PHE Dte. | 3719/MEDB | 03/11/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 21.43 | 0 | 0 | 0
4030 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-III IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16265 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(SIX) Nos existing commissioned PWSS of Jalangi, Raninagar-I & Raninagar-II Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-B | 297/MURD | 03/02/2022 | 60 | SAI GEOMETRIC SOLUTION | 28.62 | 1.86 | 100 | 100
4031 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-III IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16265 | Augmentation | Material Requisition To Resource Division | 1219/MURD/25 | 03/05/2023 | 0 | Resource Division | 10.21 | 0 | 0 | 0
4032 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED MURADPUR JALANGI ZONE-III IN JALANGI BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16265 | Augmentation | Augmentation of MURADPUR JALANGI ZONE-III /Tenya Zone-II & Zone-III PWSS Laying Distribution System, of JALANGI /Bharatpur-II Block , under Murshidabad Division PHE. Dte. | 2755/MURD | 01/09/2023 | 720 | ULTRA CONSTRUCTION. | 100.45 | 0 | 0 | 95
4033 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-B) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/15267 | Augmentation | Material Requisition To Resource Division | 1210/MURD/26 | 02/05/2023 | 0 | Resource Division | 149.38 | 0 | 0 | 0
4034 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-B) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/15267 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 1.62 | 100 | 100
4035 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED BAZEGAZIPUR ZONE-I (PART-B) PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/15267 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 0 | 21
4036 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/15268 | Augmentation | Laying of Distribution System, Construction Pump House with sanitary and Water Supply Arrangement, Repairing & Vertical Extension of Boundary Wall, Special repair and renovation of existing Pump House and Allied Works for Augmentation work of BARA SATUI PWSS in BERHAMPORE Block under Murshidabad Division , PHE. Dte.(part _B) | 2037/MURD | 26/07/2023 | 180 | AMIT KUMAR GUPTA | 176.87 | 0 | 0 | 0
4037 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/15268 | Augmentation | Material Requisition To Resource Division | 1219/MURD/03 | 03/05/2023 | 0 | Resource Division | 22.93 | 0 | 0 | 0
4038 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/15268 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.12 | 100 | 80
4039 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/15268 | Augmentation | Material Requisition To Resource Division | 1811/MURD/15 | 20/06/2024 | 0 | Resource Division | 8.19 | 0 | 0 | 0
4040 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/15268 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 5.36 | 200 | 1
4041 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/15268 | Augmentation | Providing FHTC Connection to 1159 nos household for Augmentation work of BARA SATUI PWSS in BERHAMPORE Block under Murshidabad Division , PHE.Dte. (part_C) | 1699/MURD | 28/06/2023 | 277 | S. ROY & CO. | 67.64 | 0 | 0 | 0
4042 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/15268 | Augmentation | Construction of 300 Cum OHR, Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 180 Cum capacity, Construction of Boundary Wall for Augmentation work of BARA SATUI PWSS in BERHAMPORE Block under Murshidabad Division , PHE. Dte. (part_A) | 2038/MURD | 26/07/2023 | 730 | SATELLITE CONSTRUCTION | 177.33 | 0 | 0 | 0
4043 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/15268 | Augmentation | Construction 2 (Two ) Nos Pump House with clorine Room (5.90 m X 4.825m) with sanitary and Water Supply Arrangement and 210 mtr Boundary wall at Head Work site and 55Mtr at 2nd site of Sarbangapur Zone -IB , Bara Satui & Chandkati Pipe water supply scheme under Berhampore Sub Division within Murshidabad Division . | 1930/MURD | 03/07/2024 | 537 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 52.14 | 0 | 0 | 75
4044 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/15268 | Augmentation | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 0 | 75
4045 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BARA SATUI BLOCK - BERHAMPORE , DISTRICT - MURSHIDABAD . , SM/15268 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 3.34 | 100 | 100
4046 | MURSHIDABAD | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . , SM/15518 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sadhukhali Zone-I Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 939/BD-I | 11/10/2023 | 30 | B.R SUPPLIERS | 9 | 0 | 0 | 0
4047 | MURSHIDABAD | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . , SM/15518 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SADHUKHALI Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1690/BD-I | 14/03/2023 | 10 | TECHVISION | 2.67 | 2.67 | 100 | 100
4048 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Sadhukhali Zone-I pipe water supply scheme . , SM/15518 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,ZONE-I under SADHUKHALI ground water based water supply scheme under Block_ Beldanga-II Dist. - Murshidabad under MEDB, PHE Dte. | 4353/MEDB | 29/12/2023 | 369 | C.M. ENTERPRISE | 19.4 | 0 | 0 | 8
4049 | MURSHIDABAD | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . , SM/15518 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 46 Cum/hr.) with allied work at Sadhukhali Zone-I Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | 911/BD-I | 07/06/2024 | 30 | MS BAPPA ENTERPRISE | 17 | 0 | 0 | 0
4050 | MURSHIDABAD | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . , SM/15518 | Augmentation | Material Requisition To Resource Division | 196/BD-I/21 | 09/02/2024 | 0 | Resource Division | 33.74 | 0 | 0 | 0
4051 | MURSHIDABAD | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . , SM/15518 | Augmentation | Construction of Boundary wall at 2nd Tube Well Site of SADHUKHALI ZONE -I PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 603/BD-I | 22/04/2025 | 45 | BARUN DUTTA | 10.19 | 0 | 0 | 0
4052 | MURSHIDABAD | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . , SM/15518 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) forSadhukhali Zone-I water supply scheme of Beldanga-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 1014/BD-I | 31/10/2023 | 30 | SUKUMAR ROY | 7.69 | 7.59 | 100 | 20
4053 | MURSHIDABAD | Berhampore Division I | Augmentation of Sadhukhali Zone-I pipe water supply scheme . , SM/15518 | Augmentation | SADHUKHALI ZONE-I PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 459/BD-I | 15/03/2024 | 420 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 22.95 | 0 | 0 | 100
4054 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Bahadurpur Ground water Based PWSS, Block-Suti-I , Dist- Murshidabad under MEDB, PHE Dte. , SM/15341 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Bahadurpur Ground water Based PWSS, Block-Suti-I , Dist- Murshidabad under MEDB, PHE Dte | 3759/MEDB | 03/11/2023 | 92 | M/S. SUPER CONSTRUCTION | 6.39 | 0 | 0 | 0
4055 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at MALIBARI Ground water Based PWSS, Block-Raninagar-II , Dist- Murshidabad under MEDB, PHE Dte. , SM/15347 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at MALIBARI Ground water Based PWSS, Block-Raninagar-II , Dist- Murshidabad under MEDB, PHE Dte. | 3753/MEDB | 03/11/2023 | 92 | TARUN KUMAR BHATTACHARYA | 6.39 | 0 | 0 | 0
4056 | MURSHIDABAD | Berhampore Division I | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Sibnagar Zone IV, Block- Nawda, District- Murshidabad. , SM/16437 | New | Mini Piped Water Supply Scheme for Sibnagar Zone-IV under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 157/BD-I | 15/05/2023 | 90 | GANGULY ENTERPRISE | 30.54 | 0 | 0 | 0
4057 | MURSHIDABAD | Berhampore Mechanical | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Sibnagar Zone IV, Block- Nawda, District- Murshidabad. , SM/16437 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Shibnagar Zone-IV village, Block:- Nawda under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3046/MEDB | 02/08/2023 | 92 | TARUN KUMAR BHATTACHARYA | 6.26 | 0 | 0 | 0
4058 | MURSHIDABAD | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -B Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16546 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 4.47 | 100 | 100
4059 | MURSHIDABAD | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -B Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/16546 | Augmentation | Augmentation of SHIBNAGAR LASKARPUR (Zone-I) Part-B & Garibpur (Zone-I) Part-B PWSS under Jal Jeevan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. | 2888/MURD | 12/09/2023 | 750 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 226.15 | 0 | 0 | 75
4060 | MURSHIDABAD | Berhampore Mechanical | BAURIPUNI PIPED WATER SUPPLY SCHEME. , SM/16551 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BAURIPUNI ground water based water supply scheme under Block_ Suti_II Dist. - Murshidabad under MEDB, PHE Dte. | 1900/MEDB | 16/06/2023 | 92 | DAS ENTERPRISE ( MANGO LANE) | 33.5 | 0 | 0 | 0
4061 | MURSHIDABAD | Murshidabad Division | BAURIPUNI PIPED WATER SUPPLY SCHEME. , SM/16551 | New | Material Requisition To Resource Division | 1230/MURD/30 | 04/05/2023 | 0 | Resource Division | 21.71 | 0 | 0 | 0
4062 | MURSHIDABAD | Murshidabad Division | BAURIPUNI PIPED WATER SUPPLY SCHEME. , SM/16551 | New | Formal work order for BAURIPUNI PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission, Block- Suti-II of Jangipur Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | 788/MURD | 21/03/2023 | 365 | KISMAT ARA BEGAM | 355.05 | 23.69 | 6.67 | 10
4063 | MURSHIDABAD | Murshidabad Division | BAURIPUNI PIPED WATER SUPPLY SCHEME. , SM/16551 | New | Material Requisition To Resource Division | 495/MURD/13 | 15/02/2024 | 0 | Resource Division | 7.53 | 0 | 0 | 0
4064 | MURSHIDABAD | Berhampore Mechanical | BAURIPUNI PIPED WATER SUPPLY SCHEME. , SM/16551 | New | NEW CONNECTION BAURIPUNI PH-II | 390/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 11.71 | 0 | 0 | 0
4065 | MURSHIDABAD | Berhampore Mechanical | BAURIPUNI PIPED WATER SUPPLY SCHEME. , SM/16551 | New | BAURIPUNI PH-1 NEW CONNECTION | 391/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 3.47 | 0 | 0 | 0
4066 | MURSHIDABAD | Murshidabad Division | BAURIPUNI PIPED WATER SUPPLY SCHEME. , SM/16551 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 5.09 | 100 | 100
4067 | MURSHIDABAD | Berhampore Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - DURGAPUR ZONE-IV, BLOCK - LALGOLA, DISTRICT - MURSHIDABAD. , SM/16049 | New | Mini Piped Water Supply Scheme for Durgapur zone-IV under Lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 151/BD-I | 15/05/2023 | 90 | RISHIKA GHOSH | 30.23 | 0 | 0 | 0
4068 | MURSHIDABAD | Berhampore Mechanical | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE - DURGAPUR ZONE-IV, BLOCK - LALGOLA, DISTRICT - MURSHIDABAD. , SM/16049 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Durgapur Zone-IV village, Block:- Lalgola under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3659/MEDB | 03/11/2023 | 92 | DIPALI CONSTRUCTION | 6.12 | 0 | 0 | 0
4069 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16402 | Augmentation | Material Requisition To Resource Division | 1147/MURD/6 | 27/04/2023 | 0 | Resource Division | 0.55 | 0 | 0 | 0
4070 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16402 | Augmentation | NEW CONNECTION PRASADPUR Z-III PH-I | 395/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 3.71 | 0 | 0 | 0
4071 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16402 | Augmentation | PRASADPUR Z-III PH-II | 394/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 3.78 | 0 | 0 | 0
4072 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16402 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 56.38 | 15.76 | 5
4073 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16402 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for PRASADPUR ZONE-III Ground Based Water Supply Scheme in Suti-II Block under Murshidabad Division , PHE Dte. | 1226/MURD | 28/05/2025 | 60 | INDRAJIT DUBEY | 19.62 | 0 | 0 | 0
4074 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PRASADPUR ZONE-III PWSS SUTI-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/16402 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.05 | 100 | 100
4075 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. , SM/16409 | Augmentation | Material Requisition To Resource Division | 1004/MURD/A | 11/04/2023 | 0 | Resource Division | 122.58 | 0 | 0 | 0
4076 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. , SM/16409 | Augmentation | Material Requisition To Resource Division | 1004/MURD/7 | 11/04/2023 | 0 | Resource Division | 42.04 | 0 | 0 | 0
4077 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. , SM/16409 | Augmentation | Augmentation of MURADPUR JALANGI ZONE-III /Tenya Zone-II & Zone-III PWSS Laying Distribution System, of JALANGI /Bharatpur-II Block , under Murshidabad Division PHE. Dte. | 2755/MURD | 01/09/2023 | 720 | ULTRA CONSTRUCTION. | 100.45 | 0 | 0 | 95
4078 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. , SM/16409 | Augmentation | Laying of Rising main , Distribution System, FHTC, OHR Repairing (Capacity 600 cum), , Sinking of Tube Well , Construction of pump house & Boundary wall and approach road for Augmentation of Tenya Zone-III PWSS in Bharatpur-II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 3375/MURD | 31/10/2023 | 793 | H.ENTERPRISE | 499.38 | 23.42 | 4.69 | 53
4079 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. , SM/16409 | Augmentation | Continuation Work Order for the work of Hiring of Maxi cab (Non- Air Condition, Bharat Stage III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 05(five)months i.e. 28.02.2025 TO 31.07.2025. VEHICLE NO - WB57F2352 | 41/KSD | 25/02/2025 | 150 | H.MONDAL CONSTRUCTION | 0.87 | 1.2 | 138.33 | 0
4080 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone- III Water Supply Scheme Block -Bharatpur -II, Dist- Murshidabad. , SM/16409 | Augmentation | Continuation Work Order for the work of Hiring of Maxi cab (Non- Air Condition, Bharat Stage III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 05(five)months i.e. 01.08.2025 TO 31.12.2025. VEHICLE NO - WB57F2352 | 97/KSD | 17/07/2025 | 150 | H.MONDAL CONSTRUCTION | 0.87 | 0 | 0 | 0
4081 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16170 | Augmentation | Re-Laying of U.P.V.C pipe of 140 mm dia on damaged portion in between N.P 1 to 23 & N.P 25 to 33 and 110 mm Dia N.P 20 to 33,90 mm OD N.P 17 to 19 at Dakshin,Uttar Mahadebnagar & Kagchipara for smooth water supply arrangement in Mahadebnagar Zone-1 W.S.S under Jangipur sub division under Murshidabad Division, PHE Dte. | 244/JSD | 27/08/2021 | 10 | PRAVAT KUMAR GHOSH | 4.86 | 0 | 0 | 0
4082 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16170 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II , Zone-IA under Mahadebnagar ground water based water supply scheme under Block_ Farakka Dist. - Murshidabad under MEDB, PHE Dte. | 3669/MEDB | 03/11/2023 | 92 | M/S SAJAHAN CHOWDHURY | 22.78 | 18.66 | 81.94 | 70
4083 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16170 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
4084 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16170 | Augmentation | POWER CONNECTION AT PWSS PH1 Z 1A MADEBNAGAR APPLICATION NO.3004627412 | 42/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 7.09 | 0 | 0 | 0
4085 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16170 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Sankopara halt Station (TP NO 243/5 & 243/6) on railway land of mouza-Jigari kulgachi & Connecting with existing 150 mm dia Rising main line of Mahadevnagar Zone - I ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | 2478/MURD | 16/08/2021 | 60 | DECON INDIA | 26.25 | 25.17 | 95.89 | 100
4086 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16170 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I A & Uttar Mahammadpur Water Supply Scheme at Head Work Site, 2nd Site under Murshidabad Division, P.H. Engineering Dte. | 1773/MURD | 06/07/2023 | 695 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 0 | 80
4087 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16170 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Jangipur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(83 Nos.) | 2636/MURD | 23/09/2024 | 20 | KUNTAL SAHA | 9.28 | 0 | 0 | 100
4088 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- I A Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16170 | Augmentation | Continuation work order for Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 1641/MURD | 29/05/2024 | 60 | IMAGIN | 95.53 | 4.12 | 100 | 100
4089 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. , SM/16177 | Augmentation | Providing Functional Household Tap Connections (FHTC) 1261 nos in connection with Jal Swapna (Jal Jeevan Mission ) of Mouza Jafarganj ( Village Code -313809) under Andhua Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Farakka Block under Murshidabad Division P.H.E Dte. | 1082/ MURD | 27/04/2022 | 45 | MARUTI CONSTRUCTION AND CO. | 62.56 | 7.17 | 11.47 | 0
4090 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. , SM/16177 | Augmentation | Material Requisition To Resource Division | 1180/MURD/26 | 29/04/2023 | 0 | Resource Division | 52.49 | 0 | 0 | 0
4091 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. , SM/16177 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 05(Five) nos existing commisioned PWSS Block Farakka, Samserganj, Suti-I of JANGIPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Jadabpur Nimtala Water supply Scheme, Andhua Water Supply Scheme, Bewa Zone-II Water Supply Scheme, Hasimpur Water Supply Scheme, Kusumgachi & Its Adjoining Water Supply Scheme (Annexure-II) | 1927/MURD | 19/07/2022 | 30 | M/S SOBHA & CO. | 9.79 | 0 | 0 | 10
4092 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. , SM/16177 | Augmentation | Laying of Rising main , Distribution System, 2183 nos FHTC, construction of OHR (Capacity 350 cum), Repairing of OHR , Sinking of Tube Well , Repairing of pump house, Repairing of Boundary Wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Andhua Zone- I,II & III PWSS in Farakka Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | 138/MURD | 16/01/2024 | 365 | NAYLA CONSTRUCTION | 836.98 | 0 | 0 | 35
4093 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. , SM/16177 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. Dist. - Murshidabad under MEDB, PHE Dte. | 334/MEDB | 10/02/2025 | 89 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 23.19 | 0 | 0 | 0
4094 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED ANDHUA ZONE -I PIPED WATER SUPPLY SCHEME. , SM/16177 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ANDHUA ZONE -I Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Farakka Block under Murshidabad Division, P.H. Engineering Dte | 3814/MURD | 12/12/2023 | 537 | HARUN ALL RASHID & BROTHERS | 23.52 | 7.69 | 50.66 | 100
4095 | MURSHIDABAD | Murshidabad Division | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. , SM/16410 | Augmentation | Material Requisition To Resource Division | 1230/MURD/08 | 04/05/2023 | 0 | Resource Division | 19.32 | 0 | 0 | 0
4096 | MURSHIDABAD | Murshidabad Division | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. , SM/16410 | Augmentation | Repair work of concrete road between node point 52-53 at Godapara of Panchthupi Zone -III Piped Water Supply Scheme under Jal Jeevan Mission under Kandi Sub Division, P.H.Engineering Dte. in the district of Murshidabad. | 149/KSD | 28/10/2024 | 30 | M/S BHUBAN DAS | 0.96 | 0 | 0 | 0
4097 | MURSHIDABAD | Murshidabad Division | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. , SM/16410 | Augmentation | Repair work of concrete road between node point 28-41-45-50 at Godapara of Panchthupi Zone -III Piped Water Supply Scheme under Jal Jeevan Mission under Kandi Sub Division, P.H.Engineering Dte. in the district of Murshidabad | 150/KSD | 28/10/2024 | 30 | M/S BHUBAN DAS | 0.97 | 0 | 0 | 0
4098 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. , SM/16410 | Augmentation | ADDITIONAL QTN FOR PANCHTHUPI ZONE III PHI |  | 06/09/2024 | 0 | WBSEDCL | 7.3 | 0 | 0 | 0
4099 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. , SM/16410 | Augmentation | POWER CONNECTION AT PWSS PH1 Z3 PANCHTHUPI ID 304256293 | 39/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 10.15 | 0 | 0 | 0
4100 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Panchthupi Zone -III Water Supply Scheme Block - Burwan , Dist- Murshidabad. , SM/16410 | Augmentation | POWER CONNECTION AT PWSS PH 2 Z 3 PANCHTHUPI ID 304256294 | 40/WBSEDCL-JJM | 22/04/2024 | 0 | WBSEDCL | 7.1 | 0 | 0 | 0
4101 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15920 | Augmentation | Material Requisition To Resource Division | 1147/MURD/2 | 27/04/2023 | 0 | Resource Division | 26.13 | 0 | 0 | 0
4102 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15920 | Augmentation | Quotation for Kadoa PH No-II | 328/WBSEDCL-JJM | 06/02/2024 | 0 | WBSEDCL | 11.21 | 0 | 0 | 0
4103 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15920 | Augmentation | NEW SERVICE CONNECTION AT KADOA Z2 PH1 ID304242107, Application NO 3004557257 | 330/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 4.38 | 0 | 0 | 0
4104 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15920 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-II of KADOA ground water based water supply scheme under Block- Suti-II Dist. Murshidabad under MEDB, PHE Dte. | 1921/MEDB | 16/06/2023 | 92 | A.K. SIKDAR | 11.17 | 0 | 0 | 0
4105 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15920 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation of Ghorapakhia Gangin Z-II, Bajegazipur Zone-I (Part-A), Bajegazipur Zone-I (Part-B), Mahesail Zone-I, Harua (Part B), Kadoa Zone-II, Madna Zone-II Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | 3191/MURD | 12/10/2023 | 812 | CHAKRABORTY CONSTRUCTION | 2564.41 | 0 | 0 | 21
4106 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15920 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for KADOA Zone ¿II Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division, PHE Dte. | 985/MURD | 02/05/2025 | 60 | ARINDAM MAJUMDAR | 23.01 | 0 | 0 | 0
4107 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15920 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.16 | 100 | 100
4108 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE-II PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15920 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well, 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KADOA Zone -II & NAPARA Water Supply Scheme at Head Work Site under Murshidabad Division, P.H. Engineering Dte | 1754/MURD | 13/06/2024 | 434 | R.K. DRILLING SERVICES | 11.79 | 0 | 0 | 100
4109 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15923 | Augmentation | Material Requisition To Resource Division | 1147/MURD/5 | 27/04/2023 | 0 | Resource Division | 31.5 | 0 | 0 | 0
4110 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15923 | Augmentation | Laying of Distribution System, Rising Main Connection,FHTC Work , Repair & Renovation of RCC OHR, Construction of OHR, Bounwary Wall, Pump House & Sinking of 300 x 200 mm diaTubewell for Augmentation Work of Hilora Zone-I,Prosadpur Zone-III, Bazegazipur Zone-II, Madna Zone-I, Prosadpur Zone-II, Hilora Zone-III, Bahadurpur Piped Water Supply Scheme in Jangipur Sub-Division under Murshidabad Division, PHE.Dte. | 3218/MURD | 13/10/2023 | 365 | BIJAY CHOWDHURY | 2120.16 | 0 | 0 | 5
4111 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15923 | Augmentation | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0 | 0
4112 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15923 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.16 | 100 | 100
4113 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA ZONE-I PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15923 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Jangipur Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(83 Nos.) | 2636/MURD | 23/09/2024 | 20 | KUNTAL SAHA | 9.28 | 0 | 0 | 100
4114 | MURSHIDABAD | Berhampore Mechanical | BINDARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16274 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under BINDARPUR ground water based water supply scheme under Block_ BHARATPUR-I Dist. - Murshidabad under MEDB, PHE Dte. | 1925/MEDB | 16/06/2023 | 92 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 35.06 | 0 | 0 | 0
4115 | MURSHIDABAD | Murshidabad Division | BINDARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16274 | New | Material Requisition To Resource Division | 1075/MURD | 19/04/2023 | 0 | Resource Division | 31.02 | 0 | 0 | 0
4116 | MURSHIDABAD | Murshidabad Division | BINDARPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16274 | New | BINDARPUR & adjoining mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- BHARATPUR-I of Murshidabad District under Murshidabad Division, PHE Dte. | 2641/MURD | 23/08/2023 | 740 | BERHAMPORE CONSTRUCTION SYNDICATE PVT. LTD. | 606.88 | 0 | 0 | 20
4117 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Accoan (315979) of Panchthupi under Ground Water Based Water Supply Scheme for arsenic affected areas of Buwan Block of Murshidabad District under Murshidabad Divisi , SM/09835 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village ACHHOAN (Village Code 315979) under Panchthupi Ground Water Based Water Supply Scheme for arsenic affected areas of Burwan Block in the District of Murshidabad. | 3036/MURD | 07/12/2020 | 45 | LAXMI CONSTRUCTION | 7.78 | 0 | 0 | 0
4118 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-I BLOCK-RAGHUNATHGANJ- II , SM/11198 | Augmentation | Painting Boundary wall and under ground pipe line for OHR wash out water of Kashiadanga (Zone-I) Water supply Scheme under Jangipur Sub-Division, PHE Dte. | 23/JSD | 25/01/2021 | 30 | SUJIT KR DEY | 2.24 | 2.24 | 100 | 1
4119 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-I BLOCK-RAGHUNATHGANJ- II , SM/11198 | Augmentation | Material Requisition To Resource Division | 1167/MURD/8 | 28/04/2023 | 0 | Resource Division | 34.82 | 0 | 0 | 0
4120 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-I BLOCK-RAGHUNATHGANJ- II , SM/11198 | Augmentation | Painting Boundary wall and under ground pipe line for OHR wash out water of Kashiadanga (Zone-I) Water supply Scheme under Jangipur Sub-Division, PHE Dte. |  | 29/11/2022 | 0 | SUJIT KANTI DEY | 2.24 | 0 | 0 | 0
4121 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-I BLOCK-RAGHUNATHGANJ- II , SM/11198 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under KASIADANGA ground water based water supply scheme under Block_ RAGHUNATHGANJ-II Dist. - Murshidabad under MEDB, PHE Dte. | 4335/MEDB | 29/12/2023 | 183 | CREATIVE WATER & PROCESS TECHNOLOGIES PRIVATE LIMITED. | 21.6 | 0 | 0 | 0
4122 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-I BLOCK-RAGHUNATHGANJ- II , SM/11198 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotaryrig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kasiadanga Zone- I Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Raghunathganj-II Block under Murshidabad Division, P.H. Engineering Dte | 1753/MURD | 06/07/2023 | 21 | KALACHAND DAS | 35.27 | 25.93 | 73.52 | 70
4123 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-I BLOCK-RAGHUNATHGANJ- II , SM/11198 | Augmentation | Material Requisition To Resource Division | MURD/2991/02 | 13/11/2024 | 0 | Resource Division | 42.68 | 0 | 0 | 0
4124 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-I BLOCK-RAGHUNATHGANJ- II , SM/11198 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GHORSALA and KASIADANGA ZONE - I Water Supply Scheme at Head Work Site, 2nd Site site under Murshidabad Division, P.H. Engineering Dte. | 2722/MURD | 29/08/2023 | 21 | INDRAJIT MAZUMDAR | 18.44 | 0 | 0 | 0
4125 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-I BLOCK-RAGHUNATHGANJ- II , SM/11198 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 500 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Kasiadanga Zone I & II PWSS in Raghunathganj II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | 3190/MURD | 12/10/2023 | 365 | ASTRA | 861.48 | 0 | 0 | 0
4126 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME OF KASIADANGA ZONE-I BLOCK-RAGHUNATHGANJ- II , SM/11198 | Augmentation | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 0 | 20
4127 | MURSHIDABAD | Murshidabad Division | Augmentation of Simulia Jaulia Water Supply Scheme Block - Bharatpur -II, Dist- Murshidabad. , SM/16412 | Augmentation | Material Requisition To Resource Division | 1004/MURD/1 | 11/04/2023 | 0 | Resource Division | 13.32 | 0 | 0 | 0
4128 | MURSHIDABAD | Murshidabad Division | Augmentation of Simulia Jaulia Water Supply Scheme Block - Bharatpur -II, Dist- Murshidabad. , SM/16412 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 2.62 | 100 | 80
4129 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Simulia Jaulia Water Supply Scheme Block - Bharatpur -II, Dist- Murshidabad. , SM/16412 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II under Simulia Jaulia ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | 3678/MEDB | 03/11/2023 | 790 | SARKAR CONSTRUCTION | 21.39 | 16.4 | 76.68 | 15
4130 | MURSHIDABAD | Murshidabad Division | Augmentation of Simulia Jaulia Water Supply Scheme Block - Bharatpur -II, Dist- Murshidabad. , SM/16412 | Augmentation | Augmentation of Ground Water Based SIMULIA & JAULIA PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission, Block- BHARATPUR-II of Kandi Sub-Division, Murshidabad District under Murshidabad Division, PHE Dte. | 3322/MURD | 22/10/2023 | 649 | VISION ENTERPRISE | 355.14 | 0 | 0 | 10
4131 | MURSHIDABAD | Murshidabad Division | Augmentation of Simulia Jaulia Water Supply Scheme Block - Bharatpur -II, Dist- Murshidabad. , SM/16412 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional HouseHold Connection of different existing PWSS (SIMULIA & JAMULIA PWSS Scheme, Block- BHARATPUR-II to be Augmentation/Rejuvination under Murshidabad Division P.H.E.Dte. | 3261/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 5.78 | 2.97 | 100 | 1
4132 | MURSHIDABAD | Murshidabad Division | Augmentation of Simulia Jaulia Water Supply Scheme Block - Bharatpur -II, Dist- Murshidabad. , SM/16412 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I , II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Simulia Jaulia Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Bharatpur - II Block under Murshidabad Division, P.H. Engineering Dte. | 3807/MURD | 12/12/2023 | 629 | MAMATA USHA ENTERPRISE | 18.45 | 0 | 0 | 100
4133 | MURSHIDABAD | Murshidabad Division | Augmentation of Panchthupi Zone-I Water Supply Scheme Block - Burwan, Dist- Murshidabad. , SM/16413 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 3.11 | 75.67 | 76
4134 | MURSHIDABAD | Murshidabad Division | Augmentation of Panchthupi Zone-I Water Supply Scheme Block - Burwan, Dist- Murshidabad. , SM/16413 | Augmentation | Material Requisition To Resource Division | 1230/MURD/01 | 04/05/2023 | 0 | Resource Division | 30.12 | 0 | 0 | 0
4135 | MURSHIDABAD | Murshidabad Division | Augmentation of Panchthupi Zone-I Water Supply Scheme Block - Burwan, Dist- Murshidabad. , SM/16413 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 1.67 | 100 | 80
4136 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Panchthupi Zone-I Water Supply Scheme Block - Burwan, Dist- Murshidabad. , SM/16413 | Augmentation | ADDITIONAL QUOTATION FOR PANCHTHUPI ZONE-I |  | 24/09/2024 | 0 | WBSEDCL | 7.3 | 0 | 0 | 0
4137 | MURSHIDABAD | Murshidabad Division | Augmentation of Panchthupi Zone-I Water Supply Scheme Block - Burwan, Dist- Murshidabad. , SM/16413 | Augmentation | Formal work order for Augmentation of PANCHTHUPI ZONE-I PWSS to accommodate FHTC ,under Jal Jeevan Mission, Block- BURWAN of Kandi Sub-Division, Murshidabad District under Murshidabad Division, PHE.Dte. | 673/MURD | 09/03/2023 | 1029 | ESCON INDIA | 338.35 | 334.29 | 98.81 | 100
4138 | MURSHIDABAD | Berhampore Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16377 | New | Material Requisition To Resource Division | 61/BD-1/16 | 27/04/2023 | 0 | Resource Division | 12.25 | 0 | 0 | 0
4139 | MURSHIDABAD | Berhampore Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16377 | New | Material Requisition To Resource Division | 2096/BD-I/2 | 25/11/2024 | 0 | Resource Division | 5.01 | 0 | 0 | 0
4140 | MURSHIDABAD | Berhampore Mechanical | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16377 | New | NEW CONNECTION AT HARIGANJ PH-I | 184/WBSEDCL-JJM | 09/08/2024 | 0 | WBSEDCL | 5.15 | 0 | 0 | 0
4141 | MURSHIDABAD | Berhampore Mechanical | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16377 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-III under HARIGANJA ground water based water supply scheme under Block_LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | 1152/MEDB | 14/05/2025 | 92 | ASSOCIATED ELECTRICAL CO. | 10.83 | 0 | 0 | 0
4142 | MURSHIDABAD | Berhampore Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16377 | New | HARIGANJA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jeevan Mission of BELDANGA - II Block, Murshidabad District under Berhampore Division-I, PHE Dte. | 74/BD-I | 28/04/2023 | 730 | M/S SAJEDA ENTERPRISE | 141.8 | 26.5 | 18.69 | 65
4143 | MURSHIDABAD | Berhampore Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16377 | New | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Hariganja" ground water supply scheme in Beldanga-II Block, under Berhampore Division-I, P.H.E Dte. (Capacity-30 Cum/hr.) Type-4- Partial Gravity System with Pressure Filter and Pressurized Upflow Polishing Unit | 992/BD-I | 20/06/2024 | 730 | NATIONAL CONSTRUCTION | 142.73 | 0 | 0 | 5
4144 | MURSHIDABAD | Berhampore Division I | HARIGANJA AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16377 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at HARIGANJ PWSS (H/W Site) under Jal Jeevan Mission in Beldanga-II Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | 443/BD-I | 20/03/2025 | 15 | M/S S. DAS & ENTERPRISE | 9 | 0 | 0 | 0
4145 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAR MOHULA. , SM/16418 | Augmentation | Material Requisition To Resource Division | 1180/MURD/02 | 29/04/2023 | 0 | Resource Division | 18.43 | 0 | 0 | 0
4146 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAR MOHULA. , SM/16418 | Augmentation | Allied work of connection of Rising and Distribution main with supply of materials and construction of sluice valve chamber at Char Mahula water supply scheme under Berhampore sub division, P.H.E Dte. in the District of Murshidabad. | 1985/MURD | 08/07/2024 | 60 | SUPIA CONSTRUCTION | 4.47 | 0.7 | 20.94 | 85
4147 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAR MOHULA. , SM/16418 | Augmentation | Material Requisition To Resource Division | 1811/MURD/16 | 20/06/2024 | 0 | Resource Division | 20.22 | 0 | 0 | 0
4148 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAR MOHULA. , SM/16418 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Berhampore Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 298/MURD | 03/02/2022 | 60 | ENVIROTECH SOLUTIONS | 32.69 | 4.78 | 200 | 1
4149 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR CHAR MOHULA. , SM/16418 | Augmentation | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 0 | 75
4150 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Rejinagar Zone-I piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16565 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III ,Zone-I under Rejinagar ground water based water supply scheme under Block_ Beldanga-II Dist. - Murshidabad under MEDB, PHE Dte. | 3672/MEDB | 03/11/2023 | 92 | MASSK ENGINEERING WORKS | 33.88 | 0 | 0 | 0
4151 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-I piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16565 | Augmentation | Augmentation of Ground Water Based Rejinagar Zone-I PWSS of accommodate with Repairing of Switch Room, Repairing of Boundary Wall, 400 CUM OHR, in Beldanga II Block within Murshidabad District under Murshidabad Division, PHE Dte. [Part B] | 3118/MURD | 05/10/2023 | 180 | JIT CONSTRUCTION | 155.69 | 0 | 0 | 0
4152 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-I piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16565 | Augmentation | Material Requisition To Resource Division | 1167/MURD/51 | 28/04/2023 | 0 | Resource Division | 127.23 | 0 | 0 | 0
4153 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-I piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16565 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 06(Six) Nos existing commissioned PWSS of Beldanga-I & II Block under Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | 480/MURD | 22/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 47.33 | 10.77 | 201.08 | 0
4154 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-I piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16565 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.01 | 100 | 80
4155 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-I piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16565 | Augmentation | Material Requisition To Resource Division | 1811/MURD/19 | 20/06/2024 | 0 | Resource Division | 6.64 | 0 | 0 | 0
4156 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-I piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16565 | Augmentation | Providing FHTC Connection to 279 nos household , Laying of Distribution System, Rising Main for Augmentation work of Rejinagar Zone-I PWSS within Beldanga-II Block under Murshidabad Division , PHE.Dte. ( PART - A) | 3334/MURD | 23/10/2023 | 520 | AJAY MONDAL | 201.09 | 77.65 | 38.61 | 70
4157 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15918 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III ,Zone-I under KADOA ,Part-A ground water based water supply scheme under Block_ Suti-I Dist. - Murshidabad under MEDB, PHE Dte. | 1916/MEDB | 16/06/2023 | 92 | S. G. TECHNICAL SERTIVCE | 35.09 | 0 | 0 | 0
4158 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15918 | Augmentation | Material Requisition To Resource Division | 1210/MURD/16 | 02/05/2023 | 0 | Resource Division | 7.37 | 0 | 0 | 0
4159 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15918 | Augmentation | Laying of Rising Main, Construction Pump House with sanitary and Water Supply Arrangement (T/W-I), Special repair and renovation of existing 2 (Two) Nos Pump House and Allied Work, Construction of Boundary Wall (For T/W-I) =100 mtrs & Repair of Boundary Wall (50m +50m) =100 m at T/W-II site for Augmentation of KADOA (Zone - I) Part-A Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte. (i)Amount for Construction Part: 5,87,696.00/ (ii)Amount for Pipeline Part: 22,96,300.00/- (Attached as Annexure -XII) | 685/MURD | 10/03/2023 | 180 | M/S BAPPA ENTERPRISE | 28.81 | 0 | 0 | 0
4160 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15918 | Augmentation | Allied work of construction of culvert at kadoa Zone-I 2nd T.W site and approach road for H/W site & 2nd T.W site for Augmentation work under Jangipur sub division P.H.E Dte. | 1988/MURD | 08/07/2024 | 60 | M/S BAPPA ENTERPRISE | 16.72 | 0 | 0 | 0
4161 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15918 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 2.61 | 100 | 100
4162 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KADOA ZONE I PART A PWSS SUTI-I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION, PHE DTE. , SM/15918 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KADOA Zone -I A Water Supply Scheme at Head Work Site, 2nd Site site at Suti-I Block under Murshidabad Division, P.H. Engineering Dte. | 1753/MURD | 13/06/2024 | 201 | R.K. DRILLING SERVICES | 35.37 | 0 | 0 | 100
4163 | MURSHIDABAD | Murshidabad Division | GUNDIRIA AND ADJIONING MOUJAS PWSS , SM/16110 | New | Material Requisition To Resource Division | 1075/MURD/11 | 19/04/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
4164 | MURSHIDABAD | Berhampore Mechanical | GUNDIRIA AND ADJIONING MOUJAS PWSS , SM/16110 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under GUNDIRIA ground water based water supply scheme under Block_ Bharatpur-I Dist. - Murshidabad under MEDB, PHE Dte. | 3706/MEDB | 03/11/2023 | 92 | M/S SAJAHAN CHOWDHURY | 21.21 | 11.7 | 55.14 | 35
4165 | MURSHIDABAD | Murshidabad Division | GUNDIRIA AND ADJIONING MOUJAS PWSS , SM/16110 | New | GUNDIRIA PWSS under Jal Jeevan Mission of BHARATPUR - I Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. | 1898/MURD | 17/07/2023 | 1003 | MAA MANSAHA CONSTRUCTION | 119.11 | 0 | 0 | 65
4166 | MURSHIDABAD | Murshidabad Division | GUNDIRIA AND ADJIONING MOUJAS PWSS , SM/16110 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UJUNIA SISUA AND GUNDIRIA Water Supply Scheme at Head Work Site, 2nd Site site at Bharatpur I & II Block under Murshidabad Division, P.H. Engineering Dte | 3409/MURD | 02/11/2023 | 472 | GENUINE | 18.43 | 0 | 0 | 100
4167 | MURSHIDABAD | Berhampore Division I | MALIPUR PIPED WATER SUPPLY SCHEME. , SM/16785 | New | Material Requisition To Resource Division | 61/BD-1/30 | 27/04/2023 | 0 | Resource Division | 18.6 | 0 | 0 | 0
4168 | MURSHIDABAD | Berhampore Mechanical | MALIPUR PIPED WATER SUPPLY SCHEME. , SM/16785 | New | NEW CONNECTION MALIPUR PH-1 | 372/WBSEDCL-JJM | 21/02/2024 | 0 | WBSEDCL | 5.26 | 0 | 0 | 0
4169 | MURSHIDABAD | Berhampore Division I | MALIPUR PIPED WATER SUPPLY SCHEME. , SM/16785 | New | MALIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Bhagwangola-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 209/BD-I | 17/05/2023 | 720 | PRANAB KUMAR GHOSH | 39.48 | 22.82 | 57.79 | 55
4170 | MURSHIDABAD | Berhampore Division I | MALIPUR PIPED WATER SUPPLY SCHEME. , SM/16785 | New | MALIPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main , under Jal Jivan Mission of BHAGWANGOLA - II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. . | 610/BD-I | 02/08/2023 | 900 | ROY CONSTRUCTION (AVIJIT ROY) | 85.64 | 51.33 | 59.94 | 90
4171 | MURSHIDABAD | Berhampore Division I | MALIPUR PIPED WATER SUPPLY SCHEME. , SM/16785 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at MALIPUR and Adjoining Mouzas PWSS (TW-II Site) under JAL JEEVAN MISSION within BHAGWANGOLA-II Block under Berhampore Division-I, P.H.Engineering Dte. (01 Nos TW) | 772/BD-I | 22/05/2025 | 15 | M/S GUHA AND ROY ENTERPRISE | 9 | 0 | 0 | 0
4172 | MURSHIDABAD | Berhampore Division I | MALIPUR PIPED WATER SUPPLY SCHEME. , SM/16785 | New | Preparation of DPR for drinking water supply scheme to facilitate 1 No Uncovered mouzas of Malipur under Amradaha G.P of Bhagwangola - II Block which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Berhampore Division-I P.H.E. Dte. | 1693/BD-I | 14/03/2023 | 15 | RADIANT | 2.51 | 2.51 | 100 | 100
4173 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Salar Zone-IIA Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. , SM/15743 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II ,Zone-IIA under Salar ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | 3677/MEDB | 03/11/2023 | 92 | SARKAR CONSTRUCTION | 21.35 | 15.63 | 73.21 | 10
4174 | MURSHIDABAD | Murshidabad Division | Augmentation of Salar Zone-IIA Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. , SM/15743 | Augmentation | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Salar Zone-IA, Zone IB, Zone-IIA, Zone-II B, Kasidanga Zone - I & Zone - II, Prasadpur Zone - II & Hasimpur Water Supply Scheme of under Kandi & Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 717/MURD | 25/03/2025 | 282 | MAMATA USHA ENTERPRISE | 70.74 | 0 | 0 | 20
4175 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A , SM/08687 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jamalpur (Village code 315469) under Kismat Imadpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Hariharpara Block, under Murshidabad Division, PHE Dte. Scheme ID - 5186280 in the District of Murshidabad. | 3141 /MURD | 11/12/2020 | 60 | MEGHNA CONSTRUCTION (PROP.: ASARUL HOQUE) | 38.95 | 65.41 | 167.93 | 1
4176 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A , SM/08687 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kismat Imadpur (Village code 315468) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Hariharpara Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad.Scheme ID 5186280 (Sl-37) | 696/MURD | 24/02/2021 | 180 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 162.04 | 138.1 | 85.23 | 1
4177 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A , SM/08687 | Retrofitting | HOLDING AWARENESS PROGRESS AT DIFFERENT G.P, TNO- 339/21-22/EE | 205-MSD/21-22 | 08/12/2021 | 0 | IMAGIN | 3.51 | 0 | 0 | 0
4178 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A , SM/08687 | Retrofitting | Boundary wall at Head works site for part (B) of Kismat Emadpur water supply Scheme under Berhampore Sub Division P.H.E Dte. | 99/BSD | 22/03/2022 | 30 | AZAD ENTERPRISE | 4.52 | 0 | 0 | 0
4179 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A , SM/08687 | Retrofitting | Extension of UPVC pipeline for Functional Household Tap Connections (FHTC) under village of Baruipara (Village Code -315465) under KismatImadpur Water Supply Scheme under Berhampore Sub-Division under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 155/BSD | 12/04/2022 | 30 | SAMAR MUKHERJEE | 4.82 | 3.39 | 100 | 1
4180 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A , SM/08687 | Retrofitting | Extension of UPVC pipeline for Functional Household Tap Connections (FHTC) under village of Baruipara (Village Code -315465) under Kismat Imadpur Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 256/BSD | 31/05/2022 | 30 | SAMAR MUKHERJEE | 4.51 | 4.5 | 100 | 1
4181 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A , SM/08687 | Retrofitting | Material Requisition To Resource Division | 539/4/MURD | 25/02/2022 | 0 | Resource Division | 18.8 | 0 | 0 | 0
4182 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A , SM/08687 | Retrofitting | Providing Functional Household Tap Connections (FHTC) of 1428 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Lalnagar ( Village Code -315471) under Kismat Emadpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block under Murshidabad Division P.H.E Dte. | 1055/MURD | 25/04/2022 | 60 | M/S GUHA & ROY ENTERPRISE | 75.91 | 0 | 0 | 0
4183 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A , SM/08687 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Baruipara (Village code 315465) under Kismat Imadpur Ground Based Water Supply Scheme for Arsenic Affected Area of Hariharpara Block, under Murshidabad Division, PHE Dte. Scheme ID 5186280 in the District of Murshidabad. (Sl No-38) | 728/MURD | 25/02/2021 | 180 | SAMAR MUKHERJEE | 53.09 | 49.81 | 100 | 1
4184 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Baruipara, Khidirpur, Kismat Imadpur, Jamalpur, Lal Nagar (315465, 315466, 315468, 315469 & 315471) of Ghoramara under Ground Water Based Water Supply Scheme for A , SM/08687 | Retrofitting | Providing Functional Household Tap Connections (FHTC) of 1994 nos in connection with Jal Swapna (Jal Jeevan Mission ) under command area of Village of Khidirpur ( Village Code -315469) under Kismat Emadpur Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Hariharpara Block under Murshidabad Division P.H.E Dte. | 1056/MURD | 25/04/2022 | 60 | MAMATA USHA ENTERPRISE | 99.92 | 0 | 0 | 1
4185 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone-I Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. , SM/15745 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 4.23 | 100 | 76
4186 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone-I Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. , SM/15745 | Augmentation | Material Requisition To Resource Division | 1004/MURD/2 | 11/04/2023 | 0 | Resource Division | 49.59 | 0 | 0 | 0
4187 | MURSHIDABAD | Murshidabad Division | Augmentation of Tenya Zone-I Water Supply Scheme Block - Bharatpur - II , Dist- Murshidabad. , SM/15745 | Augmentation | Laying of Rising Main , Distribution System, FHTC, OHR Repairing (Capacity 450 cum), , Sinking of Tube Well , Repairing of pump house & Boundary wall and approach road for Augmentation of Tenya Zone-I PWSS in Bharatpur-II Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte | 2887/MURD | 12/09/2023 | 150 | BURIMA CONSTRUCTION | 250.71 | 85.13 | 33.96 | 20
4188 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. , SM/16864 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II and III ,Zone-IA under Bhasaipaikar ground water based water supply scheme under Block_ Samserganj, Dist. - Murshidabad under MEDB, PHE Dte. | 3682/MEDB | 03/11/2023 | 92 | CONCORD ENGINEERING | 34.17 | 0 | 0 | 0
4189 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. , SM/16864 | Augmentation | Supply of UPVC Pipe and RDS filter for the work of Sinking of (300 mm x 200 mm) dia Big dia tube well at Village Bhasaipaikar(313879) in connection with FHTC work of Bhasaipaikar(Zone-I) Water Supply Scheme of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | 238/JSD | 05/05/2022 | 30 | DIPAYAN DEY | 4.61 | 2.32 | 100 | 0
4190 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. , SM/16864 | Augmentation | Sinking of (300 mm x 200 mm) dia Big dia tube well 75 mtr. Deep by direct rotary rig method using UPVC Pipe and RDS filter at Village Bhasaipaikar(313879) in connection with FHTC work of Bhasaipaikar(Zone-I) Water Supply Scheme (Scheme ID- 0001723333) of Jangipur Sub-Division, Under Murshidabad Division, P.H.Engineering Dte. | 237/JSD | 05/05/2022 | 30 | DIPAYAN DEY | 4.42 | 3.99 | 100 | 0
4191 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. , SM/16864 | Augmentation | Material Requisition To Resource Division | 1167/MURD/12 | 28/04/2023 | 0 | Resource Division | 73.37 | 0 | 0 | 0
4192 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. , SM/16864 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
4193 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. , SM/16864 | Augmentation | Preparation of Design, Drawing and Approved from the N.H.A.I Authorities including supply of 200 mm dia 8 mm thick MS Water Carrying Pipe, 600 mm dia 10 mm thick MS casing pipe and pushing of casing pipe by Hydraulic Jacking Technique method across at chainage 276+100 of the N.H- 34 of at Mouza-Ratanpur of Bhasaipaikar W/S Scheme under Jangipur Sub Division, PHE Dte. | 745/MURD | 12/03/2024 | 90 | M/S. GOUTAM ROY | 37 | 0 | 0 | 0
4194 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. , SM/16864 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 450,400,250 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approch road for Bhasipaikar Zone-I A ,Bhasipaikar Zone-I B, Bhasipaikar Zone-II A , Bhasipaikar Zone-II B & Bhasipaikar Zone-III PWSS in Samserganj Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 3374/MURD | 31/10/2023 | 365 | SANJAY BISWAS | 2012.72 | 0 | 0 | 0
4195 | MURSHIDABAD | Murshidabad Division | Augmentation of Bhasaipaikar Zone- I A Water Supply Scheme Block -Samserganj, Dist- Murshidabad. , SM/16864 | Augmentation | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bhasaipaikar Zone- I A & Kusumgachi Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 1772/MURD | 06/07/2023 | 544 | R.K. DRILLING SERVICES | 27.67 | 3.18 | 33.6 | 100
4196 | MURSHIDABAD | Berhampore Mechanical | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . , SM/16815 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hazipur Part-A village, Block:- Suti-II under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3055/MEDB | 02/08/2023 | 92 | M/S MANABESH ROY | 6.15 | 0 | 0 | 0
4197 | MURSHIDABAD | Murshidabad Division | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . , SM/16815 | New | Material Requisition To Resource Division | 1219/MURD/12 | 03/05/2023 | 0 | Resource Division | 14.34 | 0 | 0 | 0
4198 | MURSHIDABAD | Murshidabad Division | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . , SM/16815 | New | Ground Water based piped water supply scheme for Hazipur Part- B village, Block:- Suti-II, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2329/MURD | 02/08/2023 | 60 | SHIRSHENDU MUKHERJEE | 30.55 | 0 | 0 | 0
4199 | MURSHIDABAD | Berhampore Mechanical | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . , SM/16815 | New | NEW CONNECTION AT HAZIPUR MINI PH-I |  | 10/07/2024 | 0 | WBSEDCL | 0.13 | 0 | 0 | 0
4200 | MURSHIDABAD | Berhampore Mechanical | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . , SM/16815 | New | NEW CONNECTION AT HAZIPUR MINI PH-II |  | 12/11/2024 | 0 | WBSEDCL | 0.59 | 0 | 0 | 0
4201 | MURSHIDABAD | Berhampore Mechanical | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . , SM/16815 | New | NEW CONNECTION AT HAZIPUR MINI PH-I | 164/WBSEDCL-JJM | 29/07/2024 | 0 | WBSEDCL | 0.13 | 0 | 0 | 0
4202 | MURSHIDABAD | Berhampore Mechanical | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . , SM/16815 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hazipur Part-B village, Block:- Suti-II under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3056/MEDB | 02/08/2023 | 792 | MONI ELECTRICAL WORKS | 6.27 | 0 | 0 | 20
4203 | MURSHIDABAD | Murshidabad Division | HAZIPUR PIPED WATER SUPPLY SCHEME, BLOCK - SUTI-II DIST- MURSHIDABAD . , SM/16815 | New | Ground Water based piped water supply scheme for Hazipur Part- A village, Block:- Suti-II, Jangipur Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2495/MURD | 11/08/2023 | 510 | MUKTI ENTERPRISE | 30.47 | 29.64 | 100 | 100
4204 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Char Alampur Village (Code-314767), Maheswarpur Village (Code-314768), Chatra Village (Code-314769) Under Command Area Of Moktarp , SM/07703 | Retrofitting | Relaying of Different dia UPVC pipeline instead of damage portion in between node point (mouza - Maheswarpur, Chatra, Char Alampur) under Muktarpur ground water supply scheme of Raghunathganj Sub- Division under Berhampore Division - I, P.H.E. Dte. | 1109/BD-I | 28/06/2021 | 30 | S.P CONSTRUCTION | 35.66 | 28 | 78.53 | 1
4205 | MURSHIDABAD | Berhampore Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS , SM/18695 | New | Material Requisition To Resource Division | 304/BD-1/1 | 22/02/2024 | 0 | Resource Division | 21.31 | 0 | 0 | 0
4206 | MURSHIDABAD | Berhampore Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS , SM/18695 | New | Material Requisition To Resource Division | 201/BD-1/27 | 10/02/2024 | 0 | Resource Division | 34.21 | 0 | 0 | 0
4207 | MURSHIDABAD | Berhampore Mechanical | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS , SM/18695 | New | NEW CONNECTION AT KRISHNAPUR DINURPARA PH-1 |  | 03/09/2024 | 0 | WBSEDCL | 3.4 | 0 | 0 | 0
4208 | MURSHIDABAD | Berhampore Mechanical | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS , SM/18695 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR KRISHNAPUR DINURPARA PUMP HOUSE III , BLOCK - LALGOLA , DISTRICT - MURSHIDABAD. under MEDB, PHE Dte. | 1153/MEDB | 14/05/2025 | 92 | DAS ENTERPRISE (CHOA) | 11.82 | 0 | 0 | 0
4209 | MURSHIDABAD | Berhampore Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS , SM/18695 | New | KRISHNAPUR DINURPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | 654/BD-I | 08/08/2023 | 549 | ULTRA CONSTRUCTION | 91.86 | 0 | 0 | 50
4210 | MURSHIDABAD | Berhampore Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS , SM/18695 | New | KRISHNAPUR DINURPARA PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - A) | 653/BD-I | 08/08/2023 | 601 | SOUMYADIP MISRA | 326.54 | 0 | 0 | 10
4211 | MURSHIDABAD | Berhampore Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS , SM/18695 | New | KRISHNAPUR DINURPARA PWSS to accommodate FHTC, Laying Distribution System, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - C) | 652/BD-I | 08/08/2023 | 1030 | M/S GOUTAM CHAKRABORTY | 232.47 | 72.29 | 31.1 | 10
4212 | MURSHIDABAD | Berhampore Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS , SM/18695 | New | KRISHNAPURDINURPARA PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jivan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 730/BD-I | 16/08/2023 | 90 | M/S SWAPAN KUAMR NATH & CO | 72.82 | 21.2 | 29.11 | 41
4213 | MURSHIDABAD | Berhampore Division I | KRISHNAPUR DINURPARA AND ADJIONING MOUJAS PWSS , SM/18695 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KRISHNAPUR DINURPARA PWSS (2nd TW Site) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidbad. | 604/BD-I | 22/04/2025 | 15 | M/S BIMALENDU BOSE | 9.01 | 0 | 0 | 0
4214 | MURSHIDABAD | Murshidabad Division | PASCHIM CHAR MAJHARDIAR PIPED WATER SUPPLY SCHEME. , SM/19126 | New | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 2.57 | 100 | 90
4215 | MURSHIDABAD | Berhampore Mechanical | PASCHIM CHAR MAJHARDIAR PIPED WATER SUPPLY SCHEME. , SM/19126 | New | NEW SERVICE CONNECTION AT PASCHIMCHAR CHAR MAJHARDIAR ID 304495841 | 267/WBSEDCL-JJM | 28/11/2024 | 0 | WBSEDCL | 3.4 | 0 | 0 | 0
4216 | MURSHIDABAD | Berhampore Mechanical | PASCHIM CHAR MAJHARDIAR PIPED WATER SUPPLY SCHEME. , SM/19126 | New | NEW SERVICE CONNECTION AT PASCHIMCHAR CHAR MAJHARDIAR ID 304495841 |  | 25/11/2024 | 0 | WBSEDCL | 3.4 | 0 | 0 | 0
4217 | MURSHIDABAD | Murshidabad Division | PASCHIM CHAR MAJHARDIAR PIPED WATER SUPPLY SCHEME. , SM/19126 | New | Construction of Ground Water Based Paschim Char Majhardiar PWSS of accommodate FHTC(2246 Nos), Laying Distribution System, Laying Rising Main,Over Head Reservoir ( 500 CUM Capacity), Switch Room, Boundary Wall in Raninagar - II Block within Murshidabad District under Murshidabad Division, PHE Dte. | 140/MURD | 16/01/2024 | 716 | M/S. SARKAR CONSTRUCTION | 468.58 | 125.37 | 26.76 | 80
4218 | MURSHIDABAD | Murshidabad Division | PASCHIM CHAR MAJHARDIAR PIPED WATER SUPPLY SCHEME. , SM/19126 | New | Allied & Balance Work for Construction of Boundary wall, Land Development ,Road restoration damaged during laying of pipeline, Path Way & Soil Test for Over Head Reservoir of Paschim Char Majhardiar & Adjoining Mouzas Water Supply Scheme in Rani Nagar-I Block of Islampur Sub-Division, under Murshidabad Division P.H.E. Dte. | 3230/MURD | 10/12/2024 | 369 | M/S. SARKAR CONSTRUCTION | 71.53 | 0 | 0 | 0
4219 | MURSHIDABAD | Murshidabad Division | KURULIA AND ADJOINING MOUJAS PWSS , SM/18324 | New | Providing Functional Household Tap Connections (FHTC) (1222 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Parsalika, Panchhipara & Andulia ( Village Code -315953, 315966, 315967) under Kurulia & Panchhipara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Burwan Block under Murshidabad Division P.H.E Dte. | 3657/MURD | 29/11/2023 | 45 | S. DUTTA | 36.75 | 0 | 0 | 0
4220 | MURSHIDABAD | Murshidabad Division | KURULIA AND ADJOINING MOUJAS PWSS , SM/18324 | New | Material Requisition To Resource Division | 1129/MURD/8 | 25/04/2023 | 0 | Resource Division | 38.73 | 0 | 0 | 0
4221 | MURSHIDABAD | Murshidabad Division | KURULIA AND ADJOINING MOUJAS PWSS , SM/18324 | New | Sinking of 03 (Three) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Tenya Zone - II Water Supply Scheme and Kurulia Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte | 1751/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 27.64 | 13.59 | 49.24 | 50
4222 | MURSHIDABAD | Berhampore Mechanical | KURULIA AND ADJOINING MOUJAS PWSS , SM/18324 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under KURULIA ground water based water supply scheme under Block_ BURWAN Dist. - Murshidabad under MEDB, PHE Dte. | 2771/MEDB | 25/07/2023 | 92 | MENAKA ENTERPRISE | 35.06 | 0 | 0 | 0
4223 | MURSHIDABAD | Berhampore Mechanical | KURULIA AND ADJOINING MOUJAS PWSS , SM/18324 | New | NEW CONNECTION AT KURULIA PH-2 | 429/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 9.62 | 0 | 0 | 0
4224 | MURSHIDABAD | Berhampore Mechanical | KURULIA AND ADJOINING MOUJAS PWSS , SM/18324 | New | NEW CONNECTION AT KURULIA PH-1 | 428/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 3.82 | 0 | 0 | 0
4225 | MURSHIDABAD | Berhampore Mechanical | KURULIA AND ADJOINING MOUJAS PWSS , SM/18324 | New | Installation of two tank chlorination system and Supply delivery and erection of Scheme Name Board , Safety items at Different Ground based PWSS under Burwan and Kandi block Under District Murshidabad under MEDB PHE Dte. | 45/1 | 29/05/2025 | 92 | HARA PROSAD DAS | 17.87 | 0 | 0 | 0
4226 | MURSHIDABAD | Murshidabad Division | KURULIA AND ADJOINING MOUJAS PWSS , SM/18324 | New | KURULIA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE. Dte. (Part-A) | 2367/MURD | 04/08/2023 | 300 | M/S. S. DAS AND ENTERPRISE | 859.33 | 415.3 | 48.33 | 40
4227 | MURSHIDABAD | Murshidabad Division | KURULIA AND ADJOINING MOUJAS PWSS , SM/18324 | New | KURULIA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part-B) | 3300/MURD | 20/10/2023 | 804 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 261.54 | 0 | 0 | 35
4228 | MURSHIDABAD | Murshidabad Division | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. , SM/18556 | New | ANUP NAGAR CT PWSS to accommodate FHTC, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of SAMSERGANJ Block, Murshidabad District under Jangipur Sub Division Murshidabad Division, PHE Dte. | 2404/MURD | 07/08/2023 | 180 | SUJIT KUMAR SAHA | 428.3 | 0 | 0 | 0
4229 | MURSHIDABAD | Murshidabad Division | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. , SM/18556 | New | ANUPNAGAR CT PWSS to accommodate FHTC, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jeevan Mission of SAMSERGANJ Block, Murshidabad District under Jangipur SubDivision Murshidabad Division, PHE Dte. | 2464/MURD | 09/08/2023 | 365 | M/S RUBIET HOSSAIN | 230.08 | 0 | 0 | 0
4230 | MURSHIDABAD | Murshidabad Division | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. , SM/18556 | New | Material Requisition To Resource Division | 1230/MURD/32 | 04/05/2023 | 0 | Resource Division | 35.78 | 0 | 0 | 0
4231 | MURSHIDABAD | Murshidabad Division | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. , SM/18556 | New | Sinking of 06 (Six) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Anup Nagar CT T.W-I, , Bhabki T.W-I,II, Harua T.W-I,II,III Water Supply Scheme under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 761/MURD | 02/04/2025 | 80 | TITUMIR INTERNATIONAL | 70.61 | 0 | 0 | 0
4232 | MURSHIDABAD | Murshidabad Division | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. , SM/18556 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 8.66 | 100 | 100
4233 | MURSHIDABAD | Murshidabad Division | ANUP NAGAR ( CT ) PIPED WATER SUPPLY SCHEME. , SM/18556 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tubewell i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I C, Anup Nagar (CT) & Chachanda Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 1771/MURD | 06/07/2023 | 684 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 0 | 40
4234 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-III , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18515 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,II ,III ,IV & V ,Zone-III under Lalgola ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | 3711/MEDB | 03/11/2023 | 92 | WEST BENGAL ENGINEERING CO. | 58.31 | 0 | 0 | 0
4235 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-III , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18515 | Augmentation | Material Requisition To Resource Division | 1167/MURD/18 | 28/04/2023 | 0 | Resource Division | 49.7 | 0 | 0 | 0
4236 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-III , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18515 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LALGOLA ZONE-III, BHANDARA ZONE - I and SURANGAPUR ZONE -I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 3785/MURD | 11/12/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 35.34 | 0 | 0 | 80
4237 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-III , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18515 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 1250 cum), Sinking of Tube Well , and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Lalgola Zone -III PWSS in Lalgola Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE. Dte. | 3475/MURD | 07/11/2023 | 545 | HANNAN BUILDERS PVT.LTD. | 1434.58 | 0 | 0 | 1
4238 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-III , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18515 | Augmentation | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E. Dte. for 03 (Three) Months i.e. from 08.01.2025 to 07.04.2025. (Vehicle No.WB-58AX-9595). | 05/LSD | 06/01/2025 | 90 | BARI ENTERPRISE | 0.44 | 1.18 | 267.59 | 0
4239 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR LALGOLA ZONE-III , BLOCK -LALGOLA , DISTRICT - MURSHIDABAD. , SM/18515 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 3.52 | 90.45 | 100
4240 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SEIKHPARA PIPED WATER SUPPLY SCHEME. , SM/18665 | Augmentation | Material Requisition To Resource Division | 1180/MURD/23 | 29/04/2023 | 0 | Resource Division | 256.66 | 0 | 0 | 0
4241 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF SEIKHPARA PIPED WATER SUPPLY SCHEME. , SM/18665 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Seikhpara ground water based water supply scheme under Block_ Raninagar-II Dist. - Murshidabad under MEDB, PHE Dte. | 3716/MEDB | 03/11/2023 | 92 | SUNIL RABIDAS | 22.77 | 14.43 | 63.4 | 50
4242 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SEIKHPARA PIPED WATER SUPPLY SCHEME. , SM/18665 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Jalangi & Raninagar-I & II Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Azmatpur Water Supply Scheme, Purusottampur Water Supply Scheme, Seikhpara Water Supply Scheme, Barabil Raghunathpur Zone-I & II Water Supply Scheme .(Annexure-II) | 1926/MURD | 19/07/2022 | 30 | APEX ENGINEERING | 10.79 | 2.17 | 99.9 | 100
4243 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SEIKHPARA PIPED WATER SUPPLY SCHEME. , SM/18665 | Augmentation | Augmentation of Ground Water Based Seikhpara PWSS of accommodate FHTC, Laying Distribution System, Laying Rising Main, Repairing & Construction of Switch Room, Repairing of Boundary Wall, Repairing of 600 CUM OHR, Construction of 400 CUM OHR in Raninagar II Block within Murshidabad District under Murshidabad Division, PHE Dte. | 3373/MURD | 31/10/2023 | 974 | M/S.TAPAS KUMAR CHAKRABORTY | 1378.3 | 337.81 | 24.51 | 20
4244 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF SEIKHPARA PIPED WATER SUPPLY SCHEME. , SM/18665 | Augmentation | Refilling of sand layers, Activated Alumina & existing gravel after washing along with allied works of AIRP at Saikhpara Area (Capacity 100 Cum/hr.) & Muradpur Jalangi Z-I (Capacity 54.00 Cum/hr.) Water Supply Scheme under Islampur Sub-Division under Murshidabad Division, PHE Dte. | 820/MURD | 15/03/2024 | 244 | M/S. S. DAS AND ENTERPRISE | 70.68 | 0.15 | 0.44 | 40
4245 | MURSHIDABAD | Murshidabad Division | Augmentation of Kakramari Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. , SM/18755 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.89 | 100 | 100
4246 | MURSHIDABAD | Murshidabad Division | Augmentation of Kakramari Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. , SM/18755 | Augmentation | Material Requisition To Resource Division | 1219/MURD/31 | 03/05/2023 | 0 | Resource Division | 49.41 | 0 | 0 | 0
4247 | MURSHIDABAD | Murshidabad Division | Augmentation of Kakramari Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. , SM/18755 | Augmentation | Augmentation of Ground Water Based KAKRAMARI (ZONE-I) &KAKRAMARI (ZONE-II) PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | 3288/MURD | 19/10/2023 | 180 | BIJAY CHOWDHURY | 861.6 | 0 | 0 | 35
4248 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Kakramari Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. , SM/18755 | Augmentation | KANKRA MARI Z-II PH-II | 332/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 8.71 | 0 | 0 | 0
4249 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Kakramari Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. , SM/18755 | Augmentation | KANKRAMARI Z-II PH-1 | 333/WBSEDCL-JJM | 07/02/2024 | 0 | WBSEDCL | 5.26 | 0 | 0 | 0
4250 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR SURFACE WATER BASED PIPED WATER SUPPLY SCHEME FOR BEWA (JJM REVISION) , SM/18916 | New | Providing Electrical Equipment for 11/0.433 KV Sub-station at Water Treatment Plant under surface based water supply scheme for Bewa and its adjoining mouzas, Block - Farraka, District - Murshidabad. | 107/MEDB | 17/01/2024 | 182 | CONCORD ENGINEERING | 252.48 | 0 | 0 | 0
4251 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Sarkarpara ground water supply scheme , SM/07225 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarkarpara (Village code 314647) under Sarkarpara Ground Water based Water Supply Scheme for Jalangi Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-18 of 2020 ¿ 2021,SL-03). | 77/BD-I | 19/01/2021 | 30 | SARAJIT KUMAR MAJUMDAR | 24.4 | 16.81 | 68.91 | 0
4252 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Sarkarpara ground water supply scheme , SM/07225 | Retrofitting | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Sarkarpara ground water supply scheme" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1646/BD-I | 23/10/2024 | 30 | PRATAP KUMAR SINHA | 5.92 | 0 | 0 | 0
4253 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II , SM/08109 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of SRIPUR (Village code 315511) under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 265/ BD-I | 12/02/2021 | 180 | MS RUBIET HOSSAIN | 107.3 | 87.96 | 81.98 | 1
4254 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II , SM/08109 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 88/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 67.7 | 1
4255 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II , SM/08109 | Retrofitting | Material Requisition To Resource Division | 2096/BD-I/8 | 25/11/2024 | 0 | Resource Division | 24.64 | 0 | 0 | 0
4256 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II , SM/08109 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of GAZNIPUR (Village code 315512)under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 261/ BD-I | 12/02/2021 | 180 | RAJ KUMAR MONDAL | 78.63 | 113.73 | 144.64 | 1
4257 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II , SM/08109 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of PADMANABHPUR (Village code 315507)under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 264/ BD-I | 12/02/2021 | 180 | SARAJIT KUMAR MAJUMDAR | 113.25 | 87.25 | 77.04 | 80
4258 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II , SM/08109 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevanMission andJalSwapna under command area of village of Joykrishnapur (Village code 315508) under Choa (Zone-F) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 252/BD-I | 11/02/2021 | 90 | DOBAY CONSTRUCTION | 42.77 | 34.79 | 81.34 | 1
4259 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II , SM/08109 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sahajadpur (Village code 315513) under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 238/BD-I | 10/02/2021 | 180 | M/S UNIVERSAL TRADING | 91.12 | 87.7 | 96.24 | 1
4260 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II , SM/08109 | Retrofitting | Additional and balance work of HDPE pipe for house service connection and relaying of damage and Laying of extension different dia UPVC pipeline in connection to Jal Jeevan Mission & Jal Swapna from Choa Thana more towards Sahebnagar & Tangramari Village and at Borakhali village and Pirtala village of Choa G.P of Choa Water Supply Scheme of Central Sector Part-II of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1847/BD-I | 07/10/2021 | 50 | M/S RUBIET HOSSAIN | 44.49 | 0 | 0 | 0
4261 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II , SM/08109 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of CHOA (Village code 315510) under Choa (Zone-F) Surface Water Supply Scheme of Central Sector Part-II, Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 977/BD-I | 17/12/2020 | 180 | MS RUBIET HOSSAIN | 240.3 | 288.79 | 120.18 | 1
4262 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Choa (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part-II , SM/08109 | Retrofitting | Additional Laying works at village GAZNIPUR ( Village code-315512) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Choa (Zone-F) Surface water supply scheme of Central Sector Part-II (Hariharpara,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | 2289/BD-I | 28/12/2021 | 20 | RAJ KUMAR MONDAL | 12.42 | 12.42 | 100 | 1
4263 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Kalyannagar (VillageCode-314519) , Faridpur (VillageCode-314520) & Jot sahabaj (Village Code , SM/06977 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION under command area for the Village of Kalyannagar (VillageCode-314519) , Faridpur (VillageCode-314520) & Jot sahabaj (Village Code-314521) in Faridpur ground water supply scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1243/BD-I | 30/07/2024 | 30 | NOBEL CONSTRUCTION | 4.82 | 0 | 0 | 0
4264 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Kalyannagar (VillageCode-314519) , Faridpur (VillageCode-314520) & Jot sahabaj (Village Code , SM/06977 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Foridpur (Village code 314520) under Foridpur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 1005/BD-I | 21/06/2021 | 20 | AICH CONSTRUCTION | 45.66 | 40.29 | 88.23 | 1
4265 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Kalyannagar (VillageCode-314519) , Faridpur (VillageCode-314520) & Jot sahabaj (Village Code , SM/06977 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kalyan Nagar (Village code 314519) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 840/BD-I | 23/11/2020 | 60 | DOBAY CONSTRUCTION | 18.39 | 25.67 | 200 | 0
4266 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Kalyannagar (VillageCode-314519) , Faridpur (VillageCode-314520) & Jot sahabaj (Village Code , SM/06977 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jot Sahabaj (Village code 314521) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 841/BD-I | 23/11/2020 | 60 | DOBAY CONSTRUCTION | 20.69 | 35.31 | 200 | 0
4267 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Kalyannagar (VillageCode-314519) , Faridpur (VillageCode-314520) & Jot sahabaj (Village Code , SM/06977 | Retrofitting | Additional Laying works at village Foridpur (Village code-314520) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under ForidpurGround water supply scheme (Bhagwangola-II,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | 2296/BD-I | 28/12/2021 | 15 | AICH CONSTRUCTION | 9.57 | 9.06 | 100 | 1
4268 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Topidanga (VillageCode-314522) , Dhwajamat (VillageCode-314528) ,Kamal Chak (Village Code-3 , SM/06978 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kamal Chak (Village code 314529) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 839/BD-I | 23/11/2020 | 60 | AJAY MONDAL | 11.86 | 9.18 | 100 | 1
4269 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Topidanga (VillageCode-314522) , Dhwajamat (VillageCode-314528) ,Kamal Chak (Village Code-3 , SM/06978 | Retrofitting | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kamal Chak and others under Faridpur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | 274/ BD-I | 15/02/2021 | 10 | AJAY MONDAL | 3.12 | 1.7 | 100 | 1
4270 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Topidanga (VillageCode-314522) , Dhwajamat (VillageCode-314528) ,Kamal Chak (Village Code-3 , SM/06978 | Retrofitting | Balance & Allied Work for the work of "Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION under command area for the Village of Topidanga (VillageCode-314522) , Dhwajamat (VillageCode-314528) ,Kamal Chak (Village Code-314529) , Boalia (Village Code-314530) in Faridpur ground water supply scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1369/BD-I | 22/08/2024 | 30 | ANIRBAN CHATTERJEE | 7.59 | 0 | 0 | 0
4271 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Topidanga (VillageCode-314522) , Dhwajamat (VillageCode-314528) ,Kamal Chak (Village Code-3 , SM/06978 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dhwajamat (Village code 314528) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 817/BD-I | 12/11/2020 | 60 | KAKALI ENTERPRISE | 10.81 | 17.54 | 194.36 | 1
4272 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Topidanga (VillageCode-314522) , Dhwajamat (VillageCode-314528) ,Kamal Chak (Village Code-3 , SM/06978 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Boalia (Village code 314530) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 816/BD-I | 12/11/2020 | 60 | SAMBHUNATH ROY | 19.03 | 27.25 | 152.51 | 1
4273 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Topidanga (VillageCode-314522) , Dhwajamat (VillageCode-314528) ,Kamal Chak (Village Code-3 , SM/06978 | Retrofitting | Laying of additional pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dhwajamat (Village Code-314528) under Faridpur Ground Water Supply Scheme in Bhagawangola-II Block under Murshidabad District under Berhampore Division-I, PHE Dte. | 278/BD-I | 15/02/2021 | 10 | KAKALI ENTERPRISE | 2.02 | 3.12 | 200 | 0
4274 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection(FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area for the Village of Topidanga (VillageCode-314522) , Dhwajamat (VillageCode-314528) ,Kamal Chak (Village Code-3 , SM/06978 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Topi Danga (Village code 314522) under Foridpur Ground Water based Water Supply Scheme for Bhagawangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-09 of 2020 ¿ 2021,SL-06). | 74/BD-I | 19/01/2021 | 30 | SANDIP KUMAR BISWAS | 35.16 | 28.7 | 100 | 100
4275 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Lochanpur Village (Code-314758), Char Pirojpur Village (Code-314760) Under Command Area Of Lochanpur Ground Water Supply Scheme(P , SM/07697 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Lochanpur Village (Code-314758), Char Pirojpur Village (Code-314760) Under Command Area Of Lochanpur Ground Water Supply Scheme(Part-A) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1224/BD-I | 29/07/2024 | 60 | SOM CONSTRUCTION AGENCY | 44.6 | 0 | 0 | 0
4276 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Lochanpur Village (Code-314758), Char Pirojpur Village (Code-314760) Under Command Area Of Lochanpur Ground Water Supply Scheme(P , SM/07697 | Retrofitting | Formal Work Order Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lochanpur (Village code 314758), Char Pirojpur (Village Code-314760) under Lochanpur Ground Water based Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. (Block-Raninagar-I) (Sl-01) | 1475/BD-I | 17/08/2021 | 1810 | M/S GOUTAM CHAKRABORTY | 121.97 | 57.28 | 46.96 | 1
4277 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Gopalpur Village (Code-315686) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-B) , SM/07699 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gopalpur (Village code 315686) under Kashipur Ground Water Supply Scheme in Beldanga-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-12) | 1144/BD-I | 07/07/2021 | 180 | KAMIRUL SK AND CO. | 70.23 | 62.88 | 89.53 | 0
4278 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Gopalpur Village (Code-315686) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-B) , SM/07699 | Retrofitting | Balance & Allied Work for the work of Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Gopalpur Village (Code-315686) Under Command Area Of Kashipur Ground Water Supply Scheme (Part-B) in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1222/BD-I | 29/07/2024 | 60 | SANTA TRADING | 25.6 | 0 | 0 | 0
4279 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mahadub Nagar, Jayrampur (314668 & 314693) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Distric , SM/07292 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BARABIL RAGHUNAR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 87 /2020-21/SE-MC | 512/W | 30/03/2021 | 0 | MITRA CONSTRUCTION | 55.47 | 0 | 0 | 0
4280 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mahadub Nagar, Jayrampur (314668 & 314693) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Distric , SM/07292 | Retrofitting | ADDITIONAL WORKS FOR FHTC OF VILLAGE CODE MAHABUBNAGAR (CODE- 314668) UNDER DOMKAL WSS, TNO- 98/21-22/EE | 189-MSD/21-22 | 12/11/2021 | 0 | H.L. CONSTRUCTION (TITAN BISWAS) | 33.18 | 0 | 0 | 0
4281 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mahadub Nagar, Jayrampur (314668 & 314693) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Distric , SM/07292 | Retrofitting | ADDITIONAL WORKS FOR FHTC OF VILLAGE CODE MAHABUBNAGAR (CODE- 314668) UNDER DOMKAL WSS, TNO- 98/21-22/EE |  | 29/10/2021 | 0 | H.L. CONSTRUCTION (TITAN BISWAS) | 33.18 | 0 | 0 | 0
4282 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mahadub Nagar, Jayrampur (314668 & 314693) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Distric , SM/07292 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of villageMAHABUR (Village Code 314668) under DOMKAL Ground Water Based Water Supply Scheme for arsenic affected areas of Kandi Block in the District of Murshidabad. Tender no - 500 of 20-21 by EE MURD | 323-MSD/21-22 | 21/02/2022 | 0 | DECON INDIA | 9.57 | 0 | 0 | 0
4283 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mahadub Nagar, Jayrampur (314668 & 314693) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Distric , SM/07292 | Retrofitting | Additional works for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of JOYRAMPUR( Village Code -314693) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184127) | 1548/MURD | 23/06/2021 | 60 | SAHABUDDIN BISWAS | 28.24 | 0 | 0 | 0
4284 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Mahadub Nagar, Jayrampur (314668 & 314693) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad Distric , SM/07292 | Retrofitting | Additional works for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of MAHABUBNAGAR ( Village Code -314668) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005184127) | 1549/MURD | 23/06/2021 | 60 | H.L. CONSTRUCTION (TITAN BISWAS) | 38.29 | 0 | 0 | 0
4285 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Masimpur, Hetanpur, Bajitpur (314663, 314664 & 314666) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshid , SM/07294 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of --BHALKUNDI Z-II-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, VILLAGE-BHALKUNDI , CODE- 315091, TNO- 43/2020-21/SEMC | 512/W | 30/03/2021 | 0 | M/S BHUBAN DAS | 28.84 | 0 | 0 | 0
4286 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Masimpur, Hetanpur, Bajitpur (314663, 314664 & 314666) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshid , SM/07294 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of -BARABIL RAGHUNAR-Ground Water Based Water Supply Scheme for arsenic affected areas of Murshidabad District, TNO- 87 /2020-21/SE-MC | 512/W | 30/03/2021 | 0 | MITRA CONSTRUCTION | 55.47 | 0 | 0 | 0
4287 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Masimpur, Hetanpur, Bajitpur (314663, 314664 & 314666) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshid , SM/07294 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION ) "from existing Distribution system within the Command area of village MASIMPUR (Village Code 314663) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad. | 2575/MURD | 01/10/2020 | 45 | CHATTERJEE ENTERPRISE | 19.86 | 0 | 0 | 0
4288 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Masimpur, Hetanpur, Bajitpur (314663, 314664 & 314666) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshid , SM/07294 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Hetanpur (314664) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshidabad District(Part-VII) |  | 17/02/2022 | 0 | SUDIPA SINGHA ROY | 19.98 | 0 | 0 | 0
4289 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Masimpur, Hetanpur, Bajitpur (314663, 314664 & 314666) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshid , SM/07294 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with ';Jal Swapna (Jal Jeevan Mission ) 'from existing Distribution system within the Command area of village HETANPUR (Village Code 314664) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad . Tender no - 504 of 20-21 by EE MURD | 337-MSD/21-22 | 03/03/2022 | 0 | SUDIPA SINGHA ROY | 13.68 | 0 | 0 | 0
4290 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Masimpur, Hetanpur, Bajitpur (314663, 314664 & 314666) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshid , SM/07294 | Retrofitting | Additional works for Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of HETANPUR ( Village Code -314664) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. Tender no - 365 of 21-22 by EE MURD | 336-MSD/21-22 | 03/03/2022 | 0 | SUDIPA SINGHA ROY | 6.3 | 0 | 0 | 0
4291 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Masimpur, Hetanpur, Bajitpur (314663, 314664 & 314666) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshid , SM/07294 | Retrofitting | Additional works for Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of HETANPUR( Village Code -314664) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0005184127) | 1693/MURD | 06/07/2021 | 60 | SUDIPA SINGHA ROY | 13.33 | 0 | 0 | 0
4292 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Masimpur, Hetanpur, Bajitpur (314663, 314664 & 314666) of Domkal under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block of Murshid , SM/07294 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) and allied works in connection with ";Jal Swapna (Jal Jeevan Mission ) "from existing Distribution system within the Command area of village HETANPUR (Village Code 314664) under Domkal Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block in the District of Murshidabad . | 2576/MURD | 01/10/2020 | 45 | SUDIPA SINGHA ROY | 17.38 | 0 | 0 | 0
4293 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Fulpur (Code-314511), Rajabati (Code-314552) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-B) , SM/07722 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Fulpur (Code-314511), Rajabati (Code-314552) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-B)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1685/BD-I | 28/10/2024 | 30 | ARJU CONSTRUCTION | 10.34 | 0 | 0 | 0
4294 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Fulpur (Code-314511), Rajabati (Code-314552) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-B) , SM/07722 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Rajabati (Village code 314552),Fulpur (Village code 314511) under Dakshin Sahar Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-B) | 189/BD-I | 04/02/2021 | 20 | GOUTAM CHAKRABORTY | 32.54 | 45.63 | 140.2 | 1
4295 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Jogopur (Code-314533), Kamari (Code-314551) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-A) , SM/07723 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Jogopur (Code-314533), Kamari (Code-314551) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-A)" in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1449/BD-I | 04/09/2024 | 60 | S DUTTA | 21.89 | 0 | 0 | 0
4296 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Jogopur (Code-314533), Kamari (Code-314551) In The Command Area Of Dakshin Sahar Ground Water Supply Scheme (Part-A) , SM/07723 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jogopur (Village code 314533),Kamari (Village code 314551) under Dakshin Sahar Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte.(Part-A) | 190/BD-I | 04/02/2021 | 30 | DECON INDIA | 66.63 | 48.98 | 73.51 | 1
4297 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Paranpur Village (Code-314173), Fatepur(Code-314174) In The Command Area Of Maiya Ground Water Supply Scheme (Part-C) Under Lalgo , SM/07785 | Retrofitting | Balance & Allied Work for the work of "Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission at Paranpur Village (Code-314173), Fatepur(Code-314174) In The Command Area Of Maiya Ground Water Supply Scheme (Part-C) Under Lalgola Block " in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1438/BD-I | 04/09/2024 | 30 | ALOK BANERJEE ENTERPRISE | 8.85 | 0 | 0 | 0
4298 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Paranpur Village (Code-314173), Fatepur(Code-314174) In The Command Area Of Maiya Ground Water Supply Scheme (Part-C) Under Lalgo , SM/07785 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Paranpur(Village code 314173),Fatepur(Village code 314174) under Maia Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (Part-C) | 174/BD-I | 03/02/2021 | 20 | SAMAR MUKHERJEE | 35.05 | 50.51 | 179.79 | 1
4299 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Saralpur (Code-314538), Debaipur (Code-314548) In The Command Area Of Benipur Ground Water Supply Scheme (Part-D) , SM/07792 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Saralpur (Village code 314538) under Benipur Ground Water based Water Supply Scheme for Bhagwangola-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 38/BD-I | 13/01/2021 | 90 | JAHANGIR ALAM | 41.33 | 32.43 | 78.48 | 1
4300 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At The Villages Of Saralpur (Code-314538), Debaipur (Code-314548) In The Command Area Of Benipur Ground Water Supply Scheme (Part-D) , SM/07792 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area Of village of Debaipur (Village code 314548) under Benipur Ground Water based Water Supply Scheme for Bhagwangola- II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 988/BD-I | 17/12/2020 | 90 | DOBAY CONSTRUCTION | 37.11 | 54.62 | 147.19 | 0
4301 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa , SM/08187 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and connection with Jal Jeevan Mission (JJM) under command area of Village TENYA (Village Code-315737) under TENYA (ZONE-I) Ground Water Based Water Supply Scheme for arsenic affected area of Bharatpur-II Block under Murshidabad Division, PHE Dte. | 29-MSD / 21-22 | 27/08/2021 | 0 | CHAKRABORTY CONSTRUCTION | 18.07 | 0 | 0 | 0
4302 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa , SM/08187 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Ghoshpara 315735 OF Tenya under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur - II Block of Murshidabad District (PART-I) TNO- 633/20-21/EE | 129-MSD/21-22 | 11/10/2021 | 0 | MAA DURGA ENTERPRISE | 2.49 | 0 | 0 | 0
4303 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa , SM/08187 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna Mission (JJM) from existing distribution system within the command area of village Ghoshpara (Village code - 315735) of Tenya under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur - II Block of Murshidabad District. PHE DTE. Tender no-633 / 20-21 by EE / MURD | 13-MSD / 21-22 | 10/08/2021 | 0 | MAA DURGA ENTERPRISE | 6.4 | 0 | 0 | 0
4304 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa , SM/08187 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village TENYA (Village Code 315737) under TENYA (ZONE-I) Ground Water Based Water Supply Scheme for arsenic affected areas of BHARATPUR-II Block in the District of Murshidabad. Tender no - 77 of 20-21 by SE MC | 427-MSD/21-22 | 31/03/2022 | 0 | CHAKRABORTY CONSTRUCTION | 11.93 | 0 | 0 | 0
4305 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa , SM/08187 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at TENYA BAIDYAPUR G.P. under Murshidabad Division, P.H.E.Dte. | 238/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0 | 0
4306 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa , SM/08187 | Retrofitting | Material Requisition To Resource Division | 889/B/MURD | 05/04/2022 | 0 | Resource Division | 5.08 | 0 | 0 | 0
4307 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa , SM/08187 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bara Baidyapur (Village code 315733) under Tenya(Zone-II) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division,PHE Dte. Scheme ID 0006154932 in the District of Murshidabad.(sl-02) | 3487/MURD | 03/11/2021 | 100 | SOM CONSTRUCTION AGENCY | 45 | 16.43 | 36.51 | 1
4308 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa , SM/08187 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JAL SWAPNA(JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village GHOSHPARA(Village Code 315735) under Tenya Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur-II Block in the District of Murshidabad. | 3035/MURD | 07/12/2020 | 45 | MAA DURGA ENTERPRISE | 8.95 | 0 | 0 | 0
4309 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa , SM/08187 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Tenya (Village code 315737) under Tenya(Zone-I) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0006154932 in the District of Murshidabad. (Sl No-21) | 47/MURD | 06/01/2021 | 180 | CHAKRABORTY CONSTRUCTION | 58.49 | 8.07 | 100 | 1
4310 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa , SM/08187 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village NAWAPARA (Village Code : 315734) under Tenya Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur-II Block in the District of Murshidabad. | 3221/MURD | 18/12/2020 | 60 | HARUN ALL RASHID & BROTHERS | 6.26 | 5.56 | 100 | 1
4311 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa , SM/08187 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Bara Hati ( Village Code -315738) Korgram ( Village Code -315736) under Tenya Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006154932) | 306/MURD | 07/02/2022 | 60 | DAS ASSOCIATED | 38.03 | 36.83 | 100 | 100
4312 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa , SM/08187 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) of 219 left out in connection with Jal Jeevan Mission and Jal Swapna under command area of village Ghoshpara (Village code 315735) under Tenya Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 813/MURD | 25/03/2022 | 20 | MAA DURGA ENTERPRISE | 15.69 | 15.17 | 100 | 100
4313 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Talibpur, Bara Baidyapur, Nawapara, Ghoshpara, Korgram, Tenya, Bara Hati (315717, 315733, 315734, 315735,315736,315737,315738) of Tenya under Ground Water Based Wa , SM/08187 | Retrofitting | Laying of pipe line at Nawapara Village (Village Code-315734) in connection with FHTC work at Tenya (Zone-II) Water Supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 26/KSD | 08/04/2022 | 1030 | PARTHA RAJAK | 4.52 | 0 | 0 | 1
4314 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - , SM/08190 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village BABALTALI (Village Code 314583) under (SAIKHPARA AND BABALTALI adjoining habitation SAIKHPARA Ground Water Based Water Supply Scheme for arsenic affected areas of RANINAGAR-II Block in the District of Murshidabad. Tender no - 360 of 21-22 by EE MURD | 415-MSD/21-22 | 22/03/2022 | 0 | MITRA CONSTRUCTION | 45.89 | 0 | 0 | 0
4315 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - , SM/08190 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babaltali ( Village Code -314583) (Kartekerpara & Lalchandabad) & adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) | 438-MSD/21-22 | 30/03/2022 | 0 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 51.77 | 0 | 0 | 0
4316 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - , SM/08190 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Babaltali ( Village Code -314583)( Nojorana&Panipia& adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) | 2680/MURD | 31/08/2021 | 60 | TIPU CONSTRUCTION (PROP. SUJAUDDIN ) | 97.62 | 93.61 | 100 | 0
4317 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - , SM/08190 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | 298/BSD | 13/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.34 | 8.67 | 200 | 0
4318 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - , SM/08190 | Retrofitting | Extension of Distribution UPVC pipeline and providing balance Functional Household Tap Connections (FHTC) of 633 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Katlamari (Villagecode-314589)(Katlamari, Ramnagarpara & adjoining habitation) under Seikhpara Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0006086670) | 854/MURD | 31/03/2022 | 15 | HIRANMAY GHOSH | 8.27 | 5.7 | 100 | 100
4319 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - , SM/08190 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Katlamari ( Village Code -314589) (Mohongonj &Kaharpara & adjoining habitation) under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) | 716/MURD | 15/03/2022 | 60 | SOFIQUL ISLAM | 80.52 | 66.03 | 82 | 0
4320 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - , SM/08190 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Jhaubaria (Village Code -314585) under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0006086670) | 2297/MURD | 02/08/2021 | 60 | ROY CONSTRUCTION (PROP:AVIJIT ROY) | 97.86 | 135.02 | 147.84 | 1
4321 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - , SM/08190 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Katlamari (Village Code -314589)(Katlamari & Ramnagarpara& adjoining habitation) under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) | 2298/MURD | 02/08/2021 | 60 | HIRANMAY GHOSH | 97.89 | 132.79 | 179.92 | 100
4322 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - , SM/08190 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Babaltali ( Village Code -314583) (Kartekerpara & Lalchandabad) & adjoining habitation under Seikhpara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0006086670) | 2641/MURD | 27/08/2021 | 60 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 97.88 | 45.04 | 100 | 70
4323 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Katlamari, Babaltali & Jhaubaria (314589, 314583 & 314585) of Seikhpara Area under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - , SM/08190 | Retrofitting | Extension of Distribution UPVC pipeline for providing Balance Functional Household Tap Connections (FHTC) of 1180 nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Jhaubaria (Village code 314585) under Saikhpara Area Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 0006086670). | 703/MURD | 14/03/2022 | 15 | AZAD ENTERPRISE | 12.2 | 11.69 | 100 | 0
4324 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nazirpur Village (Code-315684), Andulberia Village (Code-315690) Under Command Area Of Andulberia Ground Water Supply Scheme (P , SM/08901 | Retrofitting | Material Requisition To Resource Division | 72/BD-I | 28/01/2022 | 0 | Resource Division | 4.44 | 0 | 0 | 0
4325 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nazirpur Village (Code-315684), Andulberia Village (Code-315690) Under Command Area Of Andulberia Ground Water Supply Scheme (P , SM/08901 | Retrofitting | Material Requisition To Resource Division | 63/BD-I | 27/01/2022 | 0 | Resource Division | 13.74 | 0 | 0 | 0
4326 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nazirpur Village (Code-315684), Andulberia Village (Code-315690) Under Command Area Of Andulberia Ground Water Supply Scheme (P , SM/08901 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Andulberia (Village code 315690) under Andulberia Ground Water Supply Scheme in Beldanga-II Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-15) | 1907/BD-I | 08/10/2021 | 180 | M/S JAN MAHAMMAD | 161.38 | 161.22 | 99.9 | 1
4327 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna At Nazirpur Village (Code-315684), Andulberia Village (Code-315690) Under Command Area Of Andulberia Ground Water Supply Scheme (P , SM/08901 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nazirpur (village code 315684) under ANDULBERIA Ground Water based Water Supply Scheme in Beldanga-II Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | 2016/BD-I | 08/11/2021 | 652 | MANASH GHOSH | 96.77 | 50.73 | 64.79 | 100
4328 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj , SM/08197 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-E). | 178/JSD | 01/04/2022 | 30 | M/S JOY MA BANAMALI | 4.8 | 3.85 | 80.19 | 1
4329 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj , SM/08197 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-A). | 167/JSD | 01/04/2022 | 30 | S.D PROJECT | 4.85 | 0 | 0 | 1
4330 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj , SM/08197 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-B). | 168/JSD | 01/04/2022 | 30 | S.D PROJECT | 4.81 | 8.19 | 100 | 1
4331 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj , SM/08197 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-C). | 169/JSD | 01/04/2022 | 30 | M/S G.M ENTERPRISE (MD. GOLAM MEHABUB) | 4.84 | 4.83 | 100 | 1
4332 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj , SM/08197 | Retrofitting | Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bahara (Village Code-314123) under Kasiadanga Ground Water Based water supply scheme for Arsenic Affected Areas of Raghunathgang-II Block under Murshidabad Division P.H.E Dte.(Scheme I.D.-0001756852) (Part-D). | 170/JSD | 01/04/2022 | 30 | SUMAN ENTERPRISE AND SUMAN AQUA | 4.84 | 3.66 | 100 | 1
4333 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj , SM/08197 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) laying pipeline in connection with under command area of village of BAHARA (Village Code-314123) & KULGACHHI (Village Code-314119) under KASIADANGA Ground water Based Water Supply Scheme for Arsenic Affected Areas of RAGHUNATHGANJ-II Block, under Murshidabad Division,PHE Dte. | 1837/MURD | 13/07/2022 | 150 | DHIRENDRANATH MONDAL | 192.87 | 192.68 | 100 | 0
4334 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj , SM/08197 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Kasiadanga ( Village Code -314124) (Part-II) & adjoining habitation under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756852) | 2595/MURD | 25/08/2021 | 60 | M/S. S.S. ENTERPRISE( PROP: SANDIP SAHA) | 70.36 | 67.32 | 100 | 0
4335 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj , SM/08197 | Retrofitting | Laying of UPVC pipeline at village Laxmijola (East Side) in connection with FHTC work under Kasiadanga (Zone-II) Water Supply Scheme under Jangipur Sub-Division,P.H.E. Dte. in the District of Murshidabad. | 419./LSD | 31/12/2021 | 30 | MARUTI CONSTRUCTION AND CO | 3.8 | 3.79 | 100 | 70
4336 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Kulgachhi ( 314119 ), Bahara (314123) & Kasiadanga ( 314124 ) of Kasiadanga under Ground Water Based Water Supply Scheme for arsenic affected areas of Raghunathganj , SM/08197 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal JeevanMission ) and under command area of village of Kasiadanga (Village Code -314124) (Part-I) & adjoining habitation under Kasiadanga Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raghunathganj-II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756852) | 2299/MURD | 02/08/2021 | 60 | KISMAT ARA BEGUM | 69.04 | 116.51 | 170.47 | 0
4337 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mahyampur (Village code 315612) under Mahyampur Surface Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte.(Sl No-02) | 2538/MURD | 19/08/2021 | 180 | TEKNO ENTERPRISE | 216.16 | 0 | 0 | 1
4338 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Mirzapur(Village code 315615) under Mahyampur Surface Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte. (Scheme ID 000958825) | 3328/MURD | 07/10/2021 | 180 | S. ENTERPRISE (PROP: SAIRUL ISLAM) | 225.77 | 0 | 0 | 0
4339 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Retrofitting of Functional Household Tap Connection (FHTC) and allied works in connection with Jal Swapna (JJM) from existing distribution system within the command area of village Kumarpur (Villagae Code 315597) under MAHYAMPUR surface based water supply scheme for arsenic affected aread of Beldanga-I Block in the dist of MSD PHE DTE. Tender no 88 of 21-21 by SE MC | 35-MSD / 21-22 | 27/08/2021 | 0 | DECON INDIA | 31.77 | 0 | 0 | 0
4340 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Barua (P) (Village code 315619) under Mahyampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte.Scheme ID 000958825 in the District of Murshidabad.3135/MURD, 11/12/2020 | 173-MSD/21-22 | 01/11/2021 | 0 | AMAL KUMAR DAS | 21.03 | 0 | 0 | 0
4341 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Supply of different dia Sluice Valve, CI Specials & Different dia jeffy coupling under LSD PHE DTE. Tender no - 27 of 21-22 by AE LSD | 317-MSD/21-22 | 17/02/2022 | 0 | MADAN MOHAN SASMAL | 3.86 | 0 | 0 | 0
4342 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of Village MIRZAPUR (Village Code 315615) under MAHYAMPUR Ground Water Based Water Supply Scheme for arsenic affected areas of BELDANGA-I Block under Murshidabad Div Phe DTE in the District of Murshidabad. Tender no - 65 of 21-22 by SE MC | 05-MSD/22-23 | 20/04/2022 | 0 | S.ENTERPRISE | 78.9 | 0 | 0 | 0
4343 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION)' from existing Distribution system within the Command area of village MAHYAMPUR (Village Code 315612) under MAHYAMPUR Surface Water Based Water Supply Scheme for arsenic affected areas of Beldanga-I Block in the District of Murshidabad. Tender no - 18 of 21-22 by SE MC | 425-MSD/21-22 | 31/03/2022 | 0 | TEKNO ENTERPRISE | 96.69 | 0 | 0 | 0
4344 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Additional work of laying of distribution system pipe line for providing Funtional Household Tap connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Kumarpur (village code 315597) under Mahyampur surface Water Supply Scheme for Arsenic affected areas of Beldanga-I Block in Murshidabad Division PHE Dte. in the District of Murshidabad. | 102/BSD | 28/03/2022 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 4.68 | 4.63 | 98.84 | 0
4345 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Formal work order for Hiring of Maxicab ( Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on Daily hire basis for official use of the Superintending Engineer, Murshidabad Circle,PHE Dte.[Period for 01(One) Year] for the month of February 2022 to January 2023 | 168/MURD | 24/01/2022 | 365 | HASNA BEWA | 4.8 | 1.05 | 21.92 | 0
4346 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Name of Work:- Hiring of Maxi cab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E Dte. for 01 (One) year. | 291/LSD | 08/07/2022 | 365 | BARI ENTERPRISE | 1.78 | 4.52 | 100 | 40
4347 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission under command area of village of Jalalpur (Village Code -315595) Part-B under Mahyampur surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. In the District of Murshidabad. | 260/BSD | 31/05/2022 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 4.36 | 4.32 | 99.08 | 0
4348 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kumarpur (Village Code -315597) Part B under Mahyampur surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 262/BSD | 31/05/2022 | 30 | S.K. CONSTRUCTION (SUDIP KUMAR SANYAL) | 4.14 | 4.1 | 98.98 | 0
4349 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Kumarpur (Village Code -315597) Part C under Mahyampur surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 268/BSD | 24/06/2022 | 30 | BIJOY KUMAR SANYAL | 4.14 | 4.13 | 99.59 | 0
4350 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Work Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Jangipur Sub-Division,P.H.E Dte. [Period for 01 (One) Year] i.e. from 18.04.2022 to 17.04.2023.[Vehicle No-WB57E7960] | 205/JSD | 18/04/2022 | 365 | MAJIBUR RAHAMAN | 4.76 | 3.05 | 96.29 | 0
4351 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Barua (P) (Village code 315619) under Mahyampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte.Scheme ID 000958825 in the District of Murshidabad. | 3135/MURD | 11/12/2020 | 60 | AMAL KUMAR DAS | 41.32 | 18.65 | 100 | 1
4352 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) Part-E under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 275/BSD | 24/06/2022 | 30 | MASTER CONSTRUCTION | 4.72 | 4.62 | 100 | 100
4353 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) Part-A under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 277/BSD | 24/06/2022 | 30 | NAYLA CONSTRUCTION | 4.67 | 4.58 | 100 | 100
4354 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Barua (p) (Village Code -315619) under Mahyampur Surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 284/BSD | 24/06/2022 | 30 | MD. MASUD SK. | 4.43 | 4.27 | 100 | 100
4355 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Further to Hiring of one no. Mahindra & Mahindra make Bolero Diesel passenger car for official use of the Assistant Engineer, Berhampore Sub-Division,P. H. Engineering Dte. for 06(Six) Months. (Period from 01.07.2022 to 31.12.2022) | 283/BSD | 24/06/2022 | 183 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 0.91 | 2.22 | 100 | 0
4356 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Laying of distribution system pipe line and connection with street stand post and Construction of soat well in connection with Dengue control for different Health Sub Centre (1) Miezapur Mid section Sc 2) Mirzapur Sitalpara Sc.3) Mahyampur SC.4) Notunpara RCH SC under Berhampore Sub division. P.H.E.Dte. | 269/BSD | 13/10/2020 | 15 | PRADIP MAHATO | 1.97 | 1.91 | 100 | 1
4357 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) PART-B under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 279/BSD | 30/06/2022 | 30 | NAYLA CONSTRUCTION | 4.72 | 4.69 | 100 | 100
4358 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) Part-D under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 278/BSD | 24/06/2022 | 30 | NAYLA CONSTRUCTION | 4.67 | 4.61 | 100 | 100
4359 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Bishnnagar (Village Code -315605) Part-C under Beldanga Municipality surface Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -I Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 276/BSD | 24/06/2022 | 30 | NAYLA CONSTRUCTION | 4.68 | 4.37 | 100 | 100
4360 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months (120 days) | 164/ISD | 31/03/2023 | 183 | HAMIDUL ISLAM | 0.69 | 1.93 | 100 | 100
4361 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Hiring of 01 (One) no . Diesel Bolero /Marshal Car for official use having for contract carriage permit from the Reginal Transport Authority for the office of the Assistant Engineer , Islampur Sub-Division, P.HE Dte, Murshidabad for the period from 01/10/2022 to 31/03/2023 (i.e six months). (Vechicle No. W.B-57E-9142) | 415/ISD | 29/09/2022 | 181 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 2.35 | 100 | 0
4362 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Further to Hiring of one no. Mahindra & Mahindra make Bolero Diesel passenger car for official use of the Assistant Engineer, Berhampore Sub-Division,P. H. Engineering Dte. for 06(Six) Months. (Period from 01.01.2023 to 30.06.2023) | 291/BSD | 16/12/2022 | 182 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 0.91 | 2.39 | 100 | 100
4363 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Construction of approach road with Cement Concrete for Head works site of Loknathpur Zone-II Water Supply Scheme under Berhampore Sub-Division, P.H.E. Dte. | 259/BSD | 31/05/2022 | 30 | MONDAL CONSTRUCTION | 2.33 | 2.32 | 100 | 100
4364 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
4365 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
4366 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Physical site visit to check the okd RC overhead water tank at satitara and Gokarna at Kandi under MSD PHE DTE. | 31-MSD/2023-24 | 05/05/2023 | 0 | SRCC NIT DURGAPUR | 1.18 | 0 | 0 | 0
4367 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Formal work order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Kumarpur (Village code 315597) under Mahyampur Surface Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 000958825 in the District of Murshidabad. | 541/MURD | 05/02/2021 | 180 | DECON INDIA | 56.35 | 23.35 | 100 | 1
4368 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Repairing of Rising main pipe line and allied works along the Rising main pipe line at western side of Beldanga C.R.G.S School , Diamond Nursing home, Beside Beldanga Rural Hospital and Panchraha More connection with FHTC work in the village Madda( Village Code-315603) Under Beldanga Municipality Water Supply scheme under Berhampore Sub Division P.H.E.Dte. | 2942/MURD | 03/11/2022 | 20 | PRADIP DAS | 3.05 | 2.75 | 90.29 | 0
4369 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Jalalpur (Village code 315595) under Mahyampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Beldanga-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 000958825 in the District of Murshidabad. | 2535/MURD | 19/08/2021 | 60 | M/S. BIMALENDU BOSE | 19.82 | 19.72 | 100 | 0
4370 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Barua(P), Meliani, Mirzapur, Kumarpur, Mahyampur, Giridharipur & Jalalpur (315619, 315614, 315615, 315597, 315612, 315613 & 315595) of Mahyampur under Ground Water B , SM/08202 | Retrofitting | Repairing And Renovation of R.C.C. elevated reservoir (1.50 Lakh Gallon capacity) of staging hight 24.0 Mtr. At Mahyampur Water Supply under Berhampore Sub Division, P.H.E. Dte. in the district of Murshidabad. | 555/MURD | 28/02/2022 | 45 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 17.67 | 15.87 | 100 | 0
4371 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Material Requisition To Resource Division | 3233/B/MURD | 02/12/2022 | 0 | Resource Division | 46.99 | 0 | 0 | 0
4372 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-16 | 290-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 4.08 | 0 | 0 | 0
4373 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-18 | 290-MSD/22-23 | 20/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 40.56 | 0 | 0 | 0
4374 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Material Requisition To Resource Division | 2780/H/MURD | 01/10/2022 | 0 | Resource Division | 40.23 | 0 | 0 | 0
4375 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Material Requisition To Resource Division | 2662/MURD | 20/09/2022 | 0 | Resource Division | 98.85 | 0 | 0 | 0
4376 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Material Requisition To Resource Division | 1167/MURD/6 | 28/04/2023 | 0 | Resource Division | 99.41 | 0 | 0 | 0
4377 | MURSHIDABAD | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Quotation payment for New Connection (Hizol P/H No.- II). | 36/DW-JJM | 18/05/2023 | 0 | WBSEDCL | 0.84 | 0 | 0 | 0
4378 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | rESTORATION OF DAMAGE PORTION LYING OF PHE PIPE LINE OF HIZOLE UNDER MSD HIGHWAY DIV-II |  | 12/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
4379 | MURSHIDABAD | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Quotation for New Connection for Hizol W/S Scheme (Zone-I, Pump-II). | 26/DW-JJM | 10/05/2023 | 0 | WBSEDCL | 0.83 | 0 | 0 | 0
4380 | MURSHIDABAD | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Quotation payment for New Connection (Hizol P/H No.- I). | 35/DW-JJM | 18/05/2023 | 0 | WBSEDCL | 0.84 | 0 | 0 | 0
4381 | MURSHIDABAD | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Quotation for New Connection for Hizol W/S Scheme (Zone-I, Pump-III). | 27/DW-JJM | 10/05/2023 | 0 | WBSEDCL | 0.83 | 0 | 0 | 0
4382 | MURSHIDABAD | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Quotation for New Connection for Hizol W/S Scheme (Zone-I, Pump-I). | 28/DW-JJM | 10/05/2023 | 0 | WBSEDCL | 0.83 | 0 | 0 | 0
4383 | MURSHIDABAD | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Quotation payment for New Connection (Hizol P/H No.- III). | 37/DW-JJM | 18/05/2023 | 0 | WBSEDCL | 0.84 | 0 | 0 | 0
4384 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Formal Work Order for Laying of Distribution System & rising main including all type of specials,valves,street stand post and FHTC Work in all complete for Hizole (Zone-II) Water Supply Scheme under Murshidabad Division, P.H.Engg Dte.at Kandi Block, Murshidabad District. | 1992/MURD | 21/07/2022 | 120 | M/S. S. DAS AND ENTERPRISE | 501.06 | 338.5 | 67.56 | 1
4385 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Formal Work Order for Laying of Distribution System & rising main including all type of specials,valves,street stand post and FHTC Work in all complete for Hizole (Zone-I) Water Supply Scheme under Murshidabad Division, P.H.Engg Dte.at Kandi Block, Murshidabad District. | 1723/MURD | 04/07/2022 | 1277 | M/S. TAPAS KUMAR CHAKRABORTY | 676.45 | 329.64 | 48.73 | 1
4386 | MURSHIDABAD | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | SHIFTING OF 11KV AT HIZOL | 450/WBSEDCL-JJM | 15/03/2024 | 0 | WBSEDCL | 0.97 | 0 | 0 | 0
4387 | MURSHIDABAD | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I , II & III , Zone-I under Hizole ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | 1933/MEDB | 16/06/2023 | 566 | CONCORD ENGINEERING | 33.21 | 0 | 0 | 40
4388 | MURSHIDABAD | Berhampore Mechanical | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.- I , II & III , Zone-II under Hizole ground water based water supply scheme under Block_ Kandi Dist. - Murshidabad under MEDB, PHE Dte. | 1934/MEDB | 16/06/2023 | 929 | M/S SAJAHAN CHOWDHURY | 33.19 | 26.68 | 80.38 | 42
4389 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Construction of 700 Cum OHR, Boundary Wall (H.W, 2nd & 3rd Site), Pump House (H.W, 2nd & 3rd Site), Land Development (H.W, 2nd & 3rd Site) and office cum godown of HIZOLE (Zone- I) & its adjoining mouzas water supply scheme of Kandi Block under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 3342/MURD | 28/10/2023 | 886 | M/S JATIN | 374.61 | 69.73 | 18.61 | 5
4390 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Construction of 600 Cum OHR, Boundary Wall (H.W, 2nd & 3rd Site), Pump House (H.W, 2nd & 3rd Site), Land Development (H.W, 2nd & 3rd Site) and office cum godown of HIZOLE (Zone- II) & its adjoining mouzas water supply scheme of Kandi Block under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 3344/MURD | 28/10/2023 | 885 | M/S JATIN | 345.77 | 187.74 | 54.3 | 20
4391 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Allied works Pertaining to Construction of Cross Drain , Surface Drain, Office cum godown, Steel Structure Shade of Hizole-I PWSS at Kandi of Kandi-Sub Division under Murshidabad Division, P.H. Engineering Dte. | 3211/MURD | 09/12/2024 | 357 | M/S JATIN | 53.73 | 0 | 0 | 10
4392 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Balance work for repair of road, construction of approach road & land development of Hizole-I & II & Bundai Water Supply Scheme of Kandi Block under Murshidabad Division, P.H.Engineering Dte. | 835/MURD | 11/04/2025 | 234 | M/S JATIN | 69.3 | 0 | 0 | 5
4393 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Sinking of 3 nos of 200 mm dia (through) and 80.0 mtr. deep tube well drilling by direct rotary method at Head work site ,2nd Site & 3rd site of Hizole( Zone-I) Water Supply Scheme of Kandi Sub-Division under Murshidabad Division, P.H.Engineering Dte. in the district of Murshidabad. | 782/MURD | 23/03/2022 | 30 | MAMATA USHA ENTERPRISE | 16.77 | 15.6 | 100 | 1
4394 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Sinking of 3 nos of 200 mm dia (through) and 80.0 mtr. deep tube well drilling by direct rotary method at Head work site, 2nd Site & 3rd site of Hizole( Zone-II) Water Supply Scheme of Kandi Sub-Division under Murshidabad Division, P.H.Engineering Dte. in the district of Murshidabad. | 783/MURD | 23/03/2022 | 30 | NADIA TUBEWELLS | 16.75 | 16.36 | 100 | 1
4395 | MURSHIDABAD | Murshidabad Division | Project on HIZOLE Piped W/S Scheme under Kandi block under Murshidabad District Ground Water Based Piped W/S Scheme June 2020 , SM/08867 | New | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well , 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gobarhati & Hizole Water Supply Scheme at Kandi Block under Murshidabad Division, P.H. Engineering Dte. | 1109/MURD | 24/04/2023 | 723 | INDRAJIT MAZUMDAR | 10.68 | 0 | 0 | 100
4396 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid , SM/08273 | Retrofitting | AND REFILLING OF FILTER MEDIA WITH ALLIED WORKS OF IEP OF CHANDPUR WSS, TNO- 143/21-22/EE | 38-MSD/22-23 | 21/04/2022 | 0 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 4.85 | 0 | 0 | 0
4397 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid , SM/08273 | Retrofitting | Repairing and Refilling of filter media with allied works of Iron Elemination Plant (I.E.P) at Chandpur W/S Scheme, under Berhampore Sub-Division, P.H.E.Dte. | 12/BSD | 10/01/2022 | 15 | EFFLUENT AND WATER TREATMENT ENGINEERS PVT LTD. | 4.85 | 0 | 0 | 0
4398 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid , SM/08273 | Retrofitting | Material Requisition To Resource Division | 539/7/MURD | 25/02/2022 | 0 | Resource Division | 1.46 | 0 | 0 | 0
4399 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid , SM/08273 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) village of Patikabari (Village Code-315550) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 2498/MURD | 30/08/2022 | 120 | M/S. SINHA & SONS | 183.88 | 0 | 0 | 0
4400 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid , SM/08273 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Tungi ( Village Code -315525) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005186507) | 1211/MURD | 10/05/2021 | 60 | MOTI RAHAMAN | 90.75 | 165.39 | 182.25 | 0
4401 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid , SM/08273 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Goghata ( Village Code -315526) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0005186507) | 1699/MURD | 07/07/2021 | 60 | M/S JAN MOHAMMAD | 52.35 | 0 | 0 | 40
4402 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid , SM/08273 | Retrofitting | Providing 365 nos Balance Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna within command area of village Tungi (Village code 315525) under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nowda Block, under Murshidabad Division, PHE Dte. Scheme ID - 0005186507 in the District of Murshidabad. | 701/MURD | 14/03/2022 | 60 | MOTI RAHAMAN | 98.18 | 49.92 | 50.85 | 0
4403 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid , SM/08273 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna ( Jal Jeevan Mission) and under command area of village of Chandpur (Village code 315552)under Chandpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division, PHE Dte. in the district of Murshidabad. | 1561/MURD | 16/06/2022 | 1348 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 126.1 | 0 | 0 | 40
4404 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Tungi, Chandpur, Patikabari (315525, 315552 & 315550) of Chandpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshid , SM/08273 | Retrofitting | Formal Work Order for :Augmentation of CHANDPUR Zone-I (Part -A) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 2083/MURD | 27/07/2022 | 991 | TINA ROY | 355.12 | 41.23 | 100 | 85
4405 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under , SM/08274 | Retrofitting | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bota, 314754 of Purushottampur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar - I Block of Murshidabad District (PART-I), TNO- 929/20-21/EE | 127-MSD/21-22 | 07/10/2021 | 0 | SINHA & COMPANY | 12.65 | 0 | 0 | 0
4406 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under , SM/08274 | Retrofitting | Additional Works for Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of BOTA ( Village Code -314754) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756484) | 52/ISD | 28/01/2022 | 30 | SINGHA AND CO.(PROP:PARTHA PROTIM SINGHA) | 4.8 | 4.11 | 100 | 1
4407 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under , SM/08274 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village MOLLADANGA (Village Code 314745) under PURUSOTTAMPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 17 of 21-22 by SE MC | 420-MSD/21-22 | 23/03/2022 | 0 | M/S TRADE ASSOCIATE | 46.29 | 0 | 0 | 0
4408 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under , SM/08274 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village DURGAPUR (Village Code 314756) under PURUSOTTAMPUR Ground Water Based Water Supply Scheme for arsenic affected areas of DOMKAL Block in the District of Murshidabad. Tender no - 291 of 20-21 by EE MURD | 405-MSD/21-22 | 23/03/2022 | 0 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 31.84 | 0 | 0 | 0
4409 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under , SM/08274 | Retrofitting | Extension of Distribution UPVC pipeline for Providing Balance Functional Household Tap Connections (FHTC) of 559 Nos in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Molladanga (Village code 314745) under Purusattampur Ground water based water supply scheme for Arsenic Affected Area of Raninagar-II Block, under Murshidabad Division, P.H.E. Dte. (Scheme I.D.- 000175684). | 671/MURD | 10/03/2022 | 30 | S.K. ENTERPRISE (PROP:SHAMIM ISLAM) | 17.21 | 16.53 | 96.03 | 1
4410 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under , SM/08274 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Purushottampur (Village code 314753) under Purushottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756484 in the District of Murshidabad. (Sl No-04) | 2502/MURD | 17/08/2021 | 120 | SUJIT KUMAR SAHA | 85.13 | 134.17 | 166.58 | 1
4411 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under , SM/08274 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Molladanga (Village code 314745) under Purushottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0001756484 | 2556/MURD | 23/08/2021 | 120 | M/S TRADE ASSOCIATE | 69.82 | 15.24 | 100 | 1
4412 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under , SM/08274 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Arizpur (Village code 314746) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad.¿ | 36/MURD | 05/01/2021 | 60 | ARJU CONSTRUCTION | 5.82 | 5.43 | 100 | 1
4413 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under , SM/08274 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Jeevan Mission of 235 nos household under command area of village of Uttar Gopalpur, Molladanga, Arizpur, Purandanpur, Purushottampur, Bota,Durgapur ( Village Code-314744, 314745, 314746, 314747, 314753, 314754, 314756) under Purushottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar-I Block under Murshidabad Division P.H.E Dte. (Scheme ID- 0001756484) | 1212/MURD | 10/05/2022 | 30 | BARMAN ENTERPRISE | 12.4 | 0 | 0 | 1
4414 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under , SM/08274 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Uttar Gopalpur (Village code 314744) under Purusottampur and Jitpur Ground Water Based Water Supply Scheme under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad. | 031/MURD | 05/01/2021 | 60 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 9.28 | 0 | 0 | 0
4415 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under , SM/08274 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Durgapur( Village Code -314756) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Raninagar_I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001756484) | 1747/MURD | 09/07/2021 | 60 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 52.77 | 19.02 | 100 | 1
4416 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Uttar Gopalpur, Molladanga, Arizpur, Purandarpur, Purushottampur, Bota, Durgapur (314744, 314745, 314746, 314747, 314753, 314754 & 314756) of Purushottampur under , SM/08274 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bota (Village code 314754) under Purusottampur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Raninagar-I Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001756484 in the District of Murshidabad. | 35/MURD | 05/01/2021 | 60 | SINGHA AND CO. | 14.46 | 0.28 | 100 | 1
4417 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In Murshid , SM/08910 | Retrofitting | Retrofitting Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of village of Sarulia (village code 315611) ,Mirzapur (village code 315615)under (Zone-G) and additional remaining villages under Begunbari (Part) ,Maniknagar (Part) and Naoapukhuria (Part) Water Supply Scheme of Beldanga-I Block in Murshidabad District under Berhampore Division-I, PHE Dte. | 1803/BD-I | 31/03/2023 | 120 | M/S GUHA & ROY | 373.58 | 0 | 0 | 0
4418 | MURSHIDABAD | Berhampore Division I | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLDTAP CONNECTION (FHTC) IN CONNECTION WITH JALJEEVAN MISSION AND JAL SWAPNA AT KASIMBAZAR CT(CODE-315444) UNDER COMMAND AREA OF (ZONE-A) OFSURFACE WATER BASED WATER SUPPLY SCHEME IN THEARSENIC AFFECTED AREAS OF , SM/08918 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 19.13 | 100 | 1
4419 | MURSHIDABAD | Berhampore Division I | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLDTAP CONNECTION (FHTC) IN CONNECTION WITH JALJEEVAN MISSION AND JAL SWAPNA AT KASIMBAZAR CT(CODE-315444) UNDER COMMAND AREA OF (ZONE-A) OFSURFACE WATER BASED WATER SUPPLY SCHEME IN THEARSENIC AFFECTED AREAS OF , SM/08918 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Cossimbazar (Village code 315444), Sibnagar Badarpur (Village Code-315446) under Hatinagar (Zone-A) Surface Water Supply Scheme of Central Sector Part-II, Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. | 980/BD-I | 17/12/2020 | 180 | CHAKRABORTY CONSTRUCTION | 307.25 | 117.5 | 100 | 69
4420 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Surangapur (315540) of Surangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad , SM/09741 | Retrofitting | Providing Functional Household Tap Connections ( 50 Nos) (FHTC) in connection with (Jal Jeevan Mission ) and under command area of village of Surangapur ( Village Code -315540) under Surangapur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. | 2210/MURD | 02/08/2024 | 486 | SARKAR WATER SUPPLY AGENCY | 2.58 | 0 | 0 | 100
4421 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jaladipur ( 313860 ) of Basudebpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Murshi , SM/09744 | Retrofitting | Laying of balance work of HDPE pipe Risingmain of Basudebpur Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte. | 654/MURD | 18/02/2021 | 60 | JOY BISHNU ENGINEERING CO. | 7.91 | 7.83 | 100 | 0
4422 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jaladipur ( 313860 ) of Basudebpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Murshi , SM/09744 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL- 15 | 370-MSD/22-23 | 21/10/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 20.99 | 0 | 0 | 0
4423 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jaladipur ( 313860 ) of Basudebpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Murshi , SM/09744 | Retrofitting | Providing Functional Household Tap Connections (FHTC) (1974 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Jaladipur ( Village Code -313860) under Basudebpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block under Murshidabad Division P.H.E Dte. | 3440/MURD | 03/11/2023 | 60 | BHOWMIK CONSTRUCTION | 67.6 | 0 | 0 | 0
4424 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Jaladipur ( 313860 ) of Basudebpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Samserganj Block of Murshidabad District under Murshi , SM/09744 | Retrofitting | Preparation of design, Drawing and approval from the N.H.A.I Authorities including supply of 200 mm dia 8 mm thick MS Water Carring Pipe, 600 mm dia 10 mm thick MS casing Pipe & Pushing of casing pipe by Hydraulic Jacking Technique Method across the Chainage 270+550 of the N.H.-34 of at Mouza-Basudebpur of Basudebpur adjoining mouza W/S Scheme & across at chainage 273+100 of the N.H.-34 of at Mouza-Joykrishnapur of Joykrishnapur W/S Scheme in Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. | 755/MURD | 16/03/2023 | 90 | SAMBHU NATH ROY | 62.1 | 26.03 | 100 | 0
4425 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc , SM/08688 | Retrofitting | Additional work of providing Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) from existing distribution system within the command area of village of Sonatikri Village Code (315528) under SARBANGAPUR ZONE-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block of Murshidabad District under Murshidabad Division, PHE Dte. tender No - 343 of 21-22 by EE | 118-MSD/21-22 | 05/10/2021 | 0 | M/S. S. DAS AND ENTERPRISE | 46.02 | 0 | 0 | 0
4426 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc , SM/08688 | Retrofitting | Supplying and Laying of 110mm dia UPVC pipeline in connection providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarbangapur (village code 315522) under Sarbangapur Zone-I Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 78/BSD | 07/03/2022 | 15 | SWAPAN DAS | 4.83 | 0 | 0 | 1
4427 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc , SM/08688 | Retrofitting | Supplying and Laying of 160mm dia UPVC pipeline in connection providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarbangapur (village code 315522) under Sarbangapur Zone-I Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 79/BSD | 07/03/2022 | 15 | SWAPAN DAS | 4.85 | 0 | 0 | 1
4428 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc , SM/08688 | Retrofitting | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarbangapur (village code 315522) under Sarbangapur Zone-I Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 180/BSD | 12/04/2022 | 15 | AMIT KUMAR SAHA | 4.83 | 4.83 | 100 | 1
4429 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc , SM/08688 | Retrofitting | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sarbangapur (village code 315522) under Sarbangapur Zone-I Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 181/BSD | 12/04/2022 | 15 | SOUNAK ENTERPRISE | 4.86 | 4.86 | 100 | 1
4430 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc , SM/08688 | Retrofitting | Supplying and Laying of 110mm dia UPVC pipeline in connection providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission and jal swapna under command area of village of Sarbangapur under Sarbangapur Zone-I W/S Scheme un MSD PHE DTE. Tender No- 178 of 2021-2022 BY AE BSD | 449-MSD/21-22 | 31/03/2022 | 0 | SWAPAN DAS | 4.83 | 0 | 0 | 0
4431 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc , SM/08688 | Retrofitting | Supplying and Laying of 110mm dia UPVC pipeline in connection providing Functional Household Tap Connection FHTC in connection with Jal Jeevan Mission and jal swapna under command area of village of Sarbangapur under Sarbangapur Zone-I W/S Scheme un MSD PHE DTE. Tender No- 177 of 2021-2022 BY AE BSD | 449-MSD/21-22 | 31/03/2022 | 0 | SWAPAN DAS | 4.85 | 0 | 0 | 0
4432 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc , SM/08688 | Retrofitting | Formal work order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sonatikri (Village code 315528) under Sarbangapur Ground Water Based water Supply Scheme for Arsenic Affected Area of Nowda Block, under Murshidabad Division, PHE Dte. Scheme ID 00051723279 in the District of Murshidabad. (Sl No-02) | 291/MURD | 27/01/2021 | 180 | M/S. S. DAS AND ENTERPRISE | 99.82 | 0 | 0 | 0
4433 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc , SM/08688 | Retrofitting | Additional work of providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sonatikuri (village code 315528) under Sarbangapur Zone-II Water Supply Scheme of Nowda Block in Murshidabad District under Murshidabad Division, PHE Dte. | 2436/MURD | 12/08/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 46.04 | 0 | 0 | 0
4434 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc , SM/08688 | Retrofitting | Material Requisition To Resource Division | 539/1/MURD | 25/02/2022 | 0 | Resource Division | 10.31 | 0 | 0 | 0
4435 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc , SM/08688 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Pareshnathpur (Village code 315529) under Sarbangapur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723279 in the District of Murshidabad. | 3239/MURD | 22/12/2020 | 60 | RATAN DUTTA | 33.87 | 9.45 | 200 | 0
4436 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc , SM/08688 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Dudhsar (Village code 315521) under Sarbangapur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Nawda Block, under Murshidabad Division, PHE Dte. Scheme ID 0001723279 in the District of Murshidabad. | 34/MURD | 05/01/2021 | 60 | CHATTERJEE ENTERPRISE | 19.26 | 8.44 | 100 | 1
4437 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sarbangapur, Sonatikri, Paresnathpur (3145522, 315528, 315529) of Sarbangapur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Bloc , SM/08688 | Retrofitting | Providing Functional Household Tap Connections (FHTC) of 1878 nos in connection with Jal Swapna (Jal Jeevan Mission ) under command area of Village of Sarbangapur Partrly ( Village Code -315522) under Sarbangapur Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Nowda Block under Murshidabad Division P.H.E Dte. | 1057/MURD | 25/04/2022 | 60 | MAMATA USHA ENTERPRISE | 93.87 | 93.23 | 100 | 1
4438 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amdahara Haziganja ( 314497) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad Dis , SM/09749 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHAMMADPUR G.P. under Murshidabad Division, P.H.E.Dte. | 245/LSD | 18/08/2021 | 30 | S.S.INFRASTRUCTURE | 4.18 | 0 | 0 | 0
4439 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Amdahara Haziganja ( 314497) of Bhandara under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bhagwangola - I and II Block of Murshidabad Dis , SM/09749 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Amdahara Haziganja (Village code 314497) under Bhandara Ground Water Based water Supply Scheme for Arsenic Affected Area of Bhagwangola-I & II Block, under Murshidabad Division, PHE Dte. Scheme ID 0005104709 in the District of Murshidabad. (Sl -05) | 596/MURD | 03/03/2022 | 180 | M/S. S. DAS AND ENTERPRISE | 57.24 | 34.05 | 59.48 | 0
4440 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jehelinagar ( 313928 ) and Rosanpur ( 313930 )of Ghorapakhiagangin Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Bloc , SM/09751 | Retrofitting | APPLICATION ID: ER-MLDT-2022-WL-12, SCHEME CODE: 9751, SCHEME NAME: GHORAPAKHIAGANGIN ZONE - II, IMIS CODE: 40019398 (SINHA AND SONS) PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-12 | 369-MSD/22-23 | 21/10/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 54.26 | 0 | 0 | 0
4441 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jehelinagar ( 313928 ) and Rosanpur ( 313930 )of Ghorapakhiagangin Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Bloc , SM/09751 | Retrofitting | PAYMENT AGAINST DEMAND NOTE APPLICATION ID :ER-MLDT-2022-WL-12 |  | 21/09/2022 | 0 | EASTERN RAILWAY (MALDA DIVISION) | 54.26 | 0 | 0 | 0
4442 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Jehelinagar ( 313928 ) and Rosanpur ( 313930 )of Ghorapakhiagangin Zone - II under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - I Bloc , SM/09751 | Retrofitting | Providing Functional Household Tap Connections (FHTC) (963 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Jehelinagar ( Village Code -313928) & Rosanpur ( Village Code -313930) under Ghorapakhiagangin Zone-II Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Suti-I Block under Murshidabad Division P.H.E Dte. | 3439/MURD | 03/11/2023 | 45 | SHIRSHENDU MUKHERJEE | 33.92 | 0 | 0 | 0
4443 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block , SM/09753 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHESHAIL-II G.P. under Murshidabad Division, P.H.E.Dte. | 56/JSD | 25/01/2022 | 30 | IMAGIN | 4.16 | 0 | 0 | 0
4444 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block , SM/09753 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at MAHESHAIL-I G.P. under Murshidabad Division, P.H.E.Dte. | 55/JSD | 25/01/2022 | 30 | S.S.INFRASTRUCTURE | 4.16 | 0 | 0 | 0
4445 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block , SM/09753 | Retrofitting | Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Jangipur Road Station to Gankar Station ( TP NO 210/09 & 211/00) at Kanupur mouza & Connecting with existing 160 mm dia UPVC distribution main line of Jarur Surface based W/S Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. | 547/MURD | 05/02/2021 | 30 | PRADIP KUMAR DAS | 39.01 | 12.79 | 100 | 100
4446 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block , SM/09753 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village of Mahesail (Village code 313954) & Amuha (Village code 313955) under Mahisail Ground Based Water Supply Scheme for Arsenic Affected Areas of Suti-II Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723341) | 502/MURD | 23/02/2022 | 180 | DECON INDIA | 239.71 | 179.88 | 75.04 | 80
4447 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block , SM/09753 | Retrofitting | Continuation work order for Preparation of design, Drawing and approval from the Railway authorities including supply of MS casing Pipe pushing of casing pipe by Hydraulic Jacking Method across the Railway track between Jangipur Road Station to Gankar Station ( TP NO 210/09 & 211/00) at Kanupur mouza & Connecting with existing 160 mm dia UPVC distribution main line of Jarur Surface based W/S Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. | 2862/MURD | 08/09/2023 | 30 | PRADIP KUMAR DAS | 5.94 | 5.94 | 100 | 100
4448 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Mahesail ( 313954 ) and Amuha ( 913955 ) of Mahisail and adjoining mouzas under Ground Water Based Water Supply Scheme for arsenic affected areas of Suti - II Block , SM/09753 | Retrofitting | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 7.4 | 100 | 100
4449 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh , SM/09838 | Retrofitting | Providing Functional Household Tap Connections (FHTC) (323 Nos) in connection with (Jal Jeevan Mission ) and under command area of village of Tegharia ( Village Code -315683) under Loknathpur Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga-II Block under Murshidabad Division P.H.E Dte. | 3563/MURD | 21/11/2023 | 30 | ARJU CONSTRUCTION | 11.66 | 0 | 0 | 0
4450 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh , SM/09838 | Retrofitting | Hiring of one no. Mahindra & Mahindra make Bolero Diesel Passenger car for official use of the Assistant Engineer, Berhampore Sub-Division, P.H.Engineering Dte. for 06 (six) Months. (Period from 01/01/2024 to 30/06/2024) | 128/BSD | 28/12/2023 | 183 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 0.91 | 2.38 | 262.72 | 0
4451 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh , SM/09838 | Retrofitting | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 180 (One Hundred Eighty) Days].For the month of 16/07/2024 to 11/01/2025. [ Vehicle No:- WB 58 BU 9284] | 48/JSD | 15/07/2024 | 180 | ABIDA CONSTRUCTION | 0.88 | 1.58 | 178.86 | 0
4452 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh , SM/09838 | Retrofitting | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 180 (One Hundred Eighty) Days].For the month of 18/01/2024 to 15/07/2024. [ Vehicle No:- WB 58 BU 9284] | 430-MSD/2024-25 | 01/10/2024 | 0 | ABIDA CONSTRUCTION | 0.24 | 0 | 0 | 0
4453 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh , SM/09838 | Retrofitting | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month].For the month of 17/07/2024 to 16/01/2025. [ Vehicle No:- WB 58 CD 3758] | 577-MSD/2024-25 | 29/11/2024 | 0 | HASSAN CONSTRUCTION | 0.4 | 0 | 0 | 0
4454 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh , SM/09838 | Retrofitting | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Daily hire basis for official use for the Office of the Dy Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01 (One) Year]. Period from i.e. 07/02/2024 to 05/02/2025 [Vehicle No.WB58AR/5026] | 575-MSD/2024-25 | 29/11/2024 | 0 | MD MUKLESUR RAHAMAN | 0.29 | 0 | 0 | 0
4455 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh , SM/09838 | Retrofitting | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/04/2024 to 30/09/2024 = 120 days | 569-MSD/2024-25 | 26/11/2024 | 0 | HAMIDUL ISLAM | 0.35 | 0 | 0 | 0
4456 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh , SM/09838 | Retrofitting | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/04/2024 to 30/09/2024 = 120 days | 569-MSD/2024-25 | 26/11/2024 | 0 | HAMIDUL ISLAM | 0.34 | 0 | 0 | 0
4457 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh , SM/09838 | Retrofitting | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E Dte.for 06 (Six) Months i.e. from 08.07.2024 to 07.01.2025. | 54/LSD | 02/07/2024 | 184 | BARI ENTERPRISE | 0.89 | 2.31 | 260.37 | 0
4458 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh , SM/09838 | Retrofitting | Hiring of Maxi cab (Non- Air Condition, Bharat Stage - III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Berhampore Sub Division, P.H.E Dte. Vehicle No : WB02AQ1490 | 237/BSD | 05/08/2024 | 160 | ABIDA CONSTRUCTION | 0.93 | 1.85 | 199.5 | 0
4459 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh , SM/09838 | Retrofitting | Continuation work order for Hiring of maxi cab (Non Air conditioned ,Bharat stage III) on or after 31.10.2023 with diesel/LPG/CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Assistant Engineer (HQ), Murshidabad Division, P.H.E. Dte. For 06(Six) Months (on and from 01/11/2024 to 30/04/2025) having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the Date of 1st Registration on monthly Hire rate basis ( The cost inclusive of all charges due to the wages of Driver, Taxes , Insurance , Fees etc. as applicable Excluding fuel, lubricant etc as per order) | 2911/MURD | 29/10/2024 | 182 | M/S JOY MA BANAMALI | 1.05 | 2.39 | 227.53 | 100
4460 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Tegharia ( 315683 ) of Loknathpur under Ground Water Based Water Supply Scheme for arsenic affected areas of Beldanga - II Block of Murshidabad District under Mursh , SM/09838 | Retrofitting | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage VI on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Murshidabad RWS Sub Division, PHE Dte. [ Period for 182 Days] w.e.f 01/11/2024 to 01/04/2025. Vehicle No [WB58CA/1034] | 390/MSD | 29/10/2024 | 182 | SUMAN ENTERPRISE AND SUMAN AQUA | 0.89 | 1.99 | 223.5 | 0
4461 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Batkamari ( 314689 ) of Jorgachha under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District under Murshidabad , SM/09842 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Batkamari (Village code 314689) under Jorgacha Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723176 in the District of Murshidabad. Tender no - 44 of 20-21 by EE MURD | 332-MSD/21-22 | 25/02/2022 | 0 | DAS TRADING CO. | 22.28 | 0 | 0 | 0
4462 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gangadhari ( 315534 ) of Gangadhari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidaba , SM/09762 | Retrofitting | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gangadhari (village code 315534) under Gangadhari Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 176/BSD | 12/04/2022 | 15 | M/S LOKNATH CONSTRUCTION | 4.85 | 0 | 0 | 0
4463 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gangadhari ( 315534 ) of Gangadhari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidaba , SM/09762 | Retrofitting | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gangadhari (village code 315534) under Gangadhari Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 174/BSD | 12/04/2022 | 15 | SWAPAN DAS | 4.83 | 4.83 | 100 | 0
4464 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gangadhari ( 315534 ) of Gangadhari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidaba , SM/09762 | Retrofitting | Laying of 90mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gangadhari (village code 315534) under Gangadhari Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 175/BSD | 12/04/2022 | 15 | SOUNAK ENTERPRISE | 4.84 | 4.84 | 100 | 0
4465 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gangadhari ( 315534 ) of Gangadhari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidaba , SM/09762 | Retrofitting | Balanced work of Boundary wall and R.B.T fencing work at Gangadhari Water Supply Scheme under Berhampore Sub Division,Murshidabad Division P.H.E. Dte. In the District Murshidabad. | 27/BSD | 14/01/2022 | 30 | MAA DURGA ENTERPRISE | 4.46 | 4.46 | 99.97 | 0
4466 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gangadhari ( 315534 ) of Gangadhari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidaba , SM/09762 | Retrofitting | Material Requisition To Resource Division | 539/6/MURD | 25/02/2022 | 0 | Resource Division | 9.82 | 0 | 0 | 0
4467 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gangadhari ( 315534 ) of Gangadhari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidaba , SM/09762 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
4468 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gangadhari ( 315534 ) of Gangadhari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidaba , SM/09762 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
4469 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Gangadhari ( 315534 ) of Gangadhari under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidaba , SM/09762 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) of 1786 nos in connection with (Jal Jeevan Mission ) and under command area of village of Gangadhari ( Village Code -315534) under Gangadhari Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nawda Block under Murshidabad Division P.H.E Dte. | 1232/MURD | 11/05/2022 | 60 | PRADIP KUMAR DAS | 78.92 | 59.04 | 50 | 0
4470 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di , SM/09763 | Retrofitting | Laying of 90mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Edrakpur (village code 315547) under EdrakpurWater Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 179/BSD | 12/04/2022 | 15 | SWAPAN DAS | 4.83 | 0 | 0 | 0
4471 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di , SM/09763 | Retrofitting | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Edrakpur (village code 315547) under Edrakpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 177/BSD | 12/04/2022 | 15 | SOUVIK HALDER | 4.85 | 0 | 0 | 0
4472 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di , SM/09763 | Retrofitting | Distribution system 110mm, 90mm and 75mm dia pipe in connection with FHTC of Edrakpur piped water supply scheme at Raghunathpur village of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | 187/BSD | 28/04/2022 | 30 | RAFIKUL HASAN | 4.51 | 4.15 | 100 | 0
4473 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di , SM/09763 | Retrofitting | Distribution system 110mm, 90mm and 75mm dia pipe in connection with FHTC of Edrakpur piped water supply scheme of Nawda village of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | 190/BSD | 28/04/2022 | 30 | MOINAK CHATTOPADHYAY | 4.76 | 4.76 | 100 | 0
4474 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di , SM/09763 | Retrofitting | LAYING OF 110 MM DIA UPVC PIPELINE FOR PROVIDING FHTC IN CONNECTION WITH JJM EDRAKPUR UNDER EDRAKPUR W/S SCHEME UNDER MSD. PHE DTE TENDER NO 222 OF 21-22 AE BSD | 177-MSD/22-23 | 17/05/2022 | 0 | M/S SS ENTERPRISE (SUKESH GHOSH) | 4.83 | 0 | 0 | 0
4475 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di , SM/09763 | Retrofitting | Supply of C.I specials to join existing AC pipe with UPVC pipe in connection with FHTC of Edrakpur piped water supply scheme of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | 188/BSD | 28/04/2022 | 30 | PM CONSTRUCTION | 3.39 | 0 | 0 | 0
4476 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di , SM/09763 | Retrofitting | Sinking of 300 X 200mm Dia Tube Well 82 mtr. Deep by D.R. Rig Method using UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) for piped water supply scheme of EDRAKPUR & its adjoining mouzas at Berhampore Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | 196/BSD | 28/04/2022 | 30 | KISMAT ARA BEGAM | 3.95 | 0 | 0 | 0
4477 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di , SM/09763 | Retrofitting | Supply and Delivery for Sinking of 300 X 200mm Dia Tube Well 82 mtr. Deep by D.R. Rig Method using UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) for piped water supply scheme of EDRAKPUR & its adjoining mouzas at Berhampore Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | 197/BSD | 28/04/2022 | 30 | KISMAT ARA BEGAM | 4.65 | 0 | 0 | 0
4478 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di , SM/09763 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna (Jal Jeevan Mission) of mouza Edrakpur (Village code 315547), of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block, of Murshidabad District under Murshidabad Division, PHE Dte.(Scheme ID 0005182896) | 17/MURD | 05/01/2022 | 180 | KISMAT ARA BEGUM | 99.02 | 94.76 | 100 | 0
4479 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di , SM/09763 | Retrofitting | Distribution system 110mm, 90mm and 75mm dia pipe in connection with FHTC of Edrakpur piped water supply scheme at Raghunathpur village of EDRAKPUR & its adjoining mouzas at Nowda Block in the District of Murshidabad, under Murshidabad Division, PHE Dte. | 189/BSD | 28/04/2022 | 30 | RAFIKUL HASAN | 4.76 | 4.77 | 100 | 0
4480 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Edrakpur ( 315547 ) of Edrakpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Nowda Block of Murshidabad District under Murshidabad Di , SM/09763 | Retrofitting | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Edrakpur (village code 315547) under Edrakpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 178/BSD | 12/04/2022 | 15 | M/S.S.S. ENTERPRISE | 4.83 | 0 | 0 | 90
4481 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at RANGAMATI CHANDPARA G.P. under Murshidabad Division, P.H.E.Dte. | 352/BSD | 27/08/2021 | 30 | IMAGIN | 4.17 | 4.17 | 100 | 0
4482 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) at village of FATEPUR West side ( Village Code _315310) of Fatepur Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | 106/BSD | 28/03/2022 | 30 | CHOWDHURY CONSTRUCTION | 4.79 | 0 | 0 | 0
4483 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Construction of pathway & painting of boundary wall including gate at Head work Site and development of land at 2nd tubewell site of Bahara water supply Scheme under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 381 / KSD | 19/01/2022 | 30 | SUGATA CHOWDHURY | 4.82 | 4.78 | 100 | 100
4484 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
4485 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | 2914/MURD | 01/11/2022 | 30 | MERCHANDISE-INDIA | 14.45 | 0 | 0 | 90
4486 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months. Vehicle No. WB-57E-9142 | 415/ISD | 29/09/2022 | 181 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 1.12 | 126.14 | 50
4487 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Continuation Order for Hiring of 01(one) no. Diesel Bolero /Marshal Car for official use having license for contract carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Murshidabad RWS Sub-Division, for 06(Six) months. (i.e. 01/04/2023 to 30/09/2023) | 55/HQ | 28/03/2023 | 184 | SISIR KUMAR DE | 0.91 | 2.14 | 236.21 | 100
4488 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Continuation Work Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Jangipur Sub-Division,P.H.E Dte. [Period for 01 (One) Year] i.e. from 18.04.2023 to 17.04.2024.[Vehicle No-WB57E7960] | 437-/AA/JSD | 17/04/2023 | 365 | MAJIBUR RAHAMAN | 4.76 | 1.38 | 70.04 | 70
4489 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Hiring of maxi cab (Non Air conditioned ,Bharat stage III) on or after 31.10.2023 with diesel/LPG/CNG Engine) in perfect good condition of performing very long journey and should cover anywere within any trouble on daily wage basis for official used under the control of the Assistant engineer (HQ), Murshidabad Division, P.H.E. Dte. For 1(One) year (on and from 01/11/2023 to 31/10/2024) having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the Date of 1st Registration on monthly Hire rate basis ( The cost inclusive of all charges due to the wages of Driver , Taxes , Insurance , Fees etc..as applicable Excluding fuel, lubricant etc as per order) | 3381/MURD | 31/10/2023 | 365 | M/S JOY MA BANAMALI | 2.11 | 4.39 | 208.16 | 28
4490 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. (i.e 01.12.2023 to 31.05.2024) | 170/HQ | 29/11/2023 | 182 | DULAL CHOWDHURY | 0.91 | 2.4 | 264.02 | 50
4491 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/10/2023 to 31/03/2024 (120 days) | 404/ISD | 29/09/2023 | 120 | HAMIDUL ISLAM | 0.69 | 2.03 | 292.31 | 30
4492 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Continuation Work Order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E Dte. for 06 (Six) Months. i.e. from 08.01.2024 to 07.07.2024. | 02/LSD | 02/01/2024 | 182 | BARI ENTERPRISE | 0.89 | 2.39 | 269.12 | 51
4493 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/10/2023 to 31/03/2024 | 403/ISD | 29/09/2023 | 182 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 1.13 | 126.96 | 100
4494 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Hiring of Maxi cab (Non- Air Condition, Bharat Stage VI on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Murshidabad RWS Sub Division, PHE Dte. [ Period for 168Days] i.e period form 17/11/2023 to 02/05/2024. Vehicle No [WB58CA/1034] | 398/MSD | 17/11/2023 | 168 | SUMAN ENTERPRISE AND SUMAN AQUA | 0.82 | 1.08 | 131.75 | 25
4495 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 180 (One Hundred Eighty) Days].For the month of 18/01/2024 to 15/07/2024. [ Vehicle No:- WB 58 BU 9284] | 892/JSD | 17/01/2024 | 180 | ABIDA CONSTRUCTION | 0.88 | 2.21 | 250.56 | 0
4496 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/04/2024 to 30/09/2024 = 120 days | 166/ISD | 28/03/2024 | 120 | HAMIDUL ISLAM | 0.69 | 1.37 | 197.3 | 50
4497 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Continuation order for Hiring of Maxi cab (Non- Air Condition, Bharat Stage VI on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Murshidabad RWS Sub Division, PHE Dte. [ Period for 182 Days] w.e.f 03/05/2024 to 31/10/2024. Vehicle No [WB58CA/1034] | 158/MSD | 29/04/2024 | 182 | SUMAN ENTERPRISE AND SUMAN AQUA | 0.89 | 2.36 | 264.79 | 0
4498 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/04/2024 to 30/09/2024 = 182 days | 165/ISD | 28/03/2024 | 183 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 2.39 | 268.05 | 50
4499 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Hiring of Maxi cab (Non- Air Condition, Bharat Stage ¿ III on or after 01/05/2008 with Diesel / LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on daily hire basis for official use for the office of the Assistant Engineer, Kandi Sub Division, PHE Dte. For 05(five)months. | 77/KSD | 25/04/2024 | 150 | H.MONDAL CONSTRUCTION | 0.87 | 2.39 | 275.02 | 0
4500 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Tenya (Village code 315737) under Tenya(Zone-I) Ground Water Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-II Block, under Murshidabad Division, PHE Dte. Scheme ID 0006154932 in the District of Murshidabad. (Sl No-21) | 47/MURD | 06/01/2021 | 180 | CHAKRABORTY CONSTRUCTION | 58.49 | 9.32 | 100 | 1
4501 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month].For the month of 17/04/2023 to 16/10/2023. | 437./A/JSD | 17/04/2023 | 183 | M/S JOY MA BANAMALI | 0.88 | 2.4 | 100 | 100
4502 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Hiring of one no. Mahindra & Mahindra make Bolero Diesel Passenger car for official use of the Assistant Engineer, Berhampore Sub-Division, P.H.Engineering Dte. for 06 (six) Months.(Period from 01/07/2023 to 31/12/2023 | 44/A/BSD | 23/06/2023 | 183 | DEBIPROSAD DE (PROP:- SOMNATH DEY) | 0.91 | 2.4 | 100 | 100
4503 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | HIRE OF CAR FOR AE-JSD, W/O NO- 52/MURD, DT-16/07/2024 | 341-MSD/2024-25 | 30/08/2024 | 0 | HASSAN CONSTRUCTION | 0.33 | 0 | 0 | 0
4504 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Preparation of D.P.R Consultancy work for 04(Four) nos PWSS Block Domkol , Jalangi & Raninagar-II of Islampur SUB-DIVISION under Murshidabad Division P.H.E. Dte.Name of Schemes- Gokul Chak Water Supply Scheme, Chak Ramprasad Water Supply Scheme, Sagarpara Water Supply Scheme Zone-I & II, Pachim Char Majhadiar Water Supply Scheme. | 630-MSD/2023-24 | 19/03/2024 | 0 | MERCHANDISE-INDIA | 2.39 | 0 | 0 | 0
4505 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Hiring of Maxicab ( Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on Daily hire basis for official use of the Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01(One) Year] (period for i.e 07/02/2023 to 06/02/2024). | 559-MSD/2023-24 | 20/02/2024 | 0 | MD MUKLESUR RAHAMAN | 0.79 | 0 | 0 | 0
4506 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Daily hire basis for official use for the Office of the Dy Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01 (One) Year]. Period from i.e. 07/02/2024 to 05/02/2025 [Vehicle No.WB58AR/5026] | 392/MURD | 06/02/2024 | 365 | MD MUKLESUR RAHAMAN | 2.11 | 4.58 | 217.17 | 50
4507 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Hiring of maxi cab (Non Air conditioned, Bharat Stage III) on or after 31.10.2023 with diesel/LPG/ CNG Engine) in perfect good condition of performing very long journey and should cover anywhere within any trouble on daily wage basis for official used under the control of the Superintending Engineer, Murshidabad Circle, P.H.E. Dte. For (05) Five Months. Having contract carriage permit from the regional Transport Authority valid for the State of West Bengal not older than 2 year from the date of 1st Registration on monthly Hire rate basis (The cost inclusive of all charges due to the wages of Driver, Taxes, Insurance, Fees etc. as applicable Excluding fuel, lubricant etc. as per order)[Period for 05 (Five) Months].for the month of July2024 to November2024 [Vehicle No.WB25M1561] | 1887/MURD | 29/06/2024 | 150 | M/S B K ENTERPRISE | 0.87 | 1.78 | 205.09 | 100
4508 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. 01/10/2024 to 31/03/2025 | 490/ISD | 30/09/2024 | 120 | HAMIDUL ISLAM | 0.69 | 1.62 | 233.77 | 0
4509 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Continuation work order for Hiring of one no. Diesel Maxi Cab/ Bolero Car/Marshal/Same category for official use of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. Berhampore, Murshidabad for the period for 6(Six) Months. (i.e 01.06.2024 to 30.11.2024) | 80/HQ | 31/05/2024 | 183 | DULAL CHOWDHURY | 0.91 | 1.99 | 219.38 | 30
4510 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 03 (three) months i.e. from 01/10/2024 to 31/12/2024 | 489/ISD | 30/09/2024 | 92 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.45 | 1.06 | 234.94 | 0
4511 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Andhar Manik ( 315323 ) of Andhar Manik under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under M , SM/09765 | Retrofitting | Continuation Order for Hiring of 01(one) no. Diesel Bolero /Marshal Car for official use having license for contract carriage permit from the Regional Transport Authority for the office of the Assistant Engineer, Murshidabad RWS Sub-Division, for 06(Six) months. (i.e. 01/10/2022 to 31/03/2023) | 295./HQ | 21/09/2022 | 181 | SISIR KUMAR DE | 0.91 | 1.81 | 100 | 100
4512 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sungai ( 315363 ) of Sungai under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad D , SM/09766 | Retrofitting |  | 48-MSD/2023-24 | 11/05/2023 | 0 | BURIMA TELECOM SYSTEM | 0.39 | 0 | 0 | 0
4513 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sungai ( 315363 ) of Sungai under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Murshidabad D , SM/09766 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sungai (Village code 315363 under Sungai Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723237 in the District of Murshidabad. | 278/MURD | 03/02/2022 | 60 | MAHATO ENTERPRISE | 9.29 | 9.28 | 100 | 0
4514 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh , SM/09767 | Retrofitting | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-B | 164/BSD | 12/04/2022 | 15 | M/S SUKESH GHOSH | 4.84 | 4.84 | 100 | 0
4515 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh , SM/09767 | Retrofitting | Laying of 110mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 166/BSD | 12/04/2022 | 15 | M/S LOKENATH CONSTRUCTION | 4.83 | 0 | 0 | 0
4516 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh , SM/09767 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission) and Laying of Distribution system of Selamatpur ( village code: 315421 ) Ground Based piped water supply scheme under Berhampore Sub-Division ; Murshidabad Division, PHE Dte. For 35nos FHTC. | 156/BSD | 12/04/2022 | 30 | ALOK BANERJEE ENTERPRISE | 4.84 | 3.27 | 100 | 0
4517 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh , SM/09767 | Retrofitting | Laying of 125mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. PART-A | 161/BSD | 12/04/2022 | 15 | SWAPAN DAS | 4.84 | 4.84 | 100 | 0
4518 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh , SM/09767 | Retrofitting | Laying of 160mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 165/BSD | 12/04/2022 | 15 | AMIT KUMAR SAHA | 4.85 | 4.85 | 100 | 0
4519 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh , SM/09767 | Retrofitting | Laying of 140mm dia UPVC pipeline for providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Selamatpur (village code 315421) under Selamatpur Water Supply Scheme in Murshidabad District under Murshidabad Division, PHE Dte. | 167/BSD | 12/04/2022 | 15 | SWAPAN DAS | 4.84 | 4.84 | 100 | 0
4520 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh , SM/09767 | Retrofitting | Laying of 110mm dia upvc ppeline FHTC .......................SELAMATPUR UNDER SELAMATPUR W/S SCHEME. TENDER NO 210 -21-22 | 179-MSD/22-23 | 26/05/2022 | 0 | M/S LOKNATH CONSTRUCTION | 4.83 | 0 | 0 | 0
4521 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh , SM/09767 | Retrofitting | Providing Functional Household Tap Connections (FHTC) of 1329 nos in connection with Jal Swapna (Jal Jeevan Mission ) & Laying of Distribution system of Selamatpur ( Village Code -315421) under Selamatpur Ground Based Piped Water Supply Scheme for Arsenic Affected Areas of Berhampore Block under Murshidabad Division P.H.E Dte. | 1058/MURD | 25/04/2022 | 60 | M/S. S. DAS AND ENTERPRISE | 94.54 | 61 | 64.52 | 90
4522 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh , SM/09767 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and Laying of Distribution system of Selamatpur ( village code: 315421 ) of Ground Based piped water supply scheme under Berhampore Sub-Division, Murshidabad Division, PHE Dte. For 35 nos FHTC. | 156/BSD | 12/04/2022 | 30 | ALOK BANERJEE ENTERPRISE | 4.84 | 0 | 0 | 100
4523 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh , SM/09767 | Retrofitting | Material Requisition To Resource Division | 539/3/MURD | 25/02/2022 | 0 | Resource Division | 7.3 | 0 | 0 | 0
4524 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh , SM/09767 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL | 441-MSD/2023-24 | 15/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
4525 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Selamatpur ( 315421 ) of Selamatpur under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad District under Mursh , SM/09767 | Retrofitting | RESTORATION OF DAMAGE PORTION OF ROAD DUE TO LAYING OF PHE PIPE LINE OF PURANDAPUR HIZOL |  | 14/12/2023 | 0 | EXECUTIVE ENGINEER, PWD, MURSHIDABAD HIGHWAY DIVISION-II | 45.36 | 0 | 0 | 0
4526 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10612 | Augmentation | Material Requisition To Resource Division | 2780/E/MURD | 01/10/2022 | 0 | Resource Division | 13.39 | 0 | 0 | 0
4527 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10612 | Augmentation | Material Requisition To Resource Division | 1180/MURD/16 | 29/04/2023 | 0 | Resource Division | 235.38 | 0 | 0 | 0
4528 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10612 | Augmentation | Material Requisition To Resource Division | MURD/2481/01 | 04/09/2024 | 0 | Resource Division | 13.39 | 0 | 0 | 0
4529 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10612 | Augmentation | Formal Work Order for Augmentation of Jalangi Zone-I Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection ) under Jal Swapna in Jalangi Block of Murshidabad District under Murshidabad Division,PHE.Dte. | 1875/MURD | 15/07/2022 | 1165 | DOBAY CONSTRUCTION | 250.61 | 80.67 | 32.19 | 40
4530 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for JALANGI Zone- I to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/10612 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jalangi Zone-I Water Supply Scheme of TW-I,II under Islampur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3053/MURD | 17/11/2022 | 45 | MAMATA USHA ENTERPRISE | 23.58 | 21.5 | 91.18 | 1
4531 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-III to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/11008 | Augmentation | Material Requisition To Resource Division | 2780/I/MURD | 01/10/2022 | 0 | Resource Division | 7.57 | 0 | 0 | 0
4532 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-III to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/11008 | Augmentation | Material Requisition To Resource Division | 1180/MURD/11 | 29/04/2023 | 0 | Resource Division | 8.83 | 0 | 0 | 0
4533 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-III to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/11008 | Augmentation | Material Requisition To Resource Division | 1210/MURD/29 | 02/05/2023 | 0 | Resource Division | 10.21 | 0 | 0 | 0
4534 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for KARIMPUR JALANGI Zone-III to Accommodate FHTC Block Jalangi District - Murshidabad. , SM/11008 | Augmentation | Material Requisition To Resource Division | MURD/2481/08 | 04/09/2024 | 0 | Resource Division | 7.57 | 0 | 0 | 0
4535 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) under Mouza Kadkhali (315657)of Bachhara Ground water based water supply scheme for arsenic affected areas of Beldanga - II Block in Murshidabad District under Murshidabad Division, P.H.E. , SM/11161 | Augmentation | Additional work of providing Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kadkhali (village code 315657) under Bachhara Water Supply Scheme of Beldanga-II Block in Murshidabad District under Murshidabad Division, PHE Dte. | 2594/MURD | 25/08/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 16.76 | 0 | 0 | 0
4536 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional House Hold tap Connection (FHTC) under Mouza Kadkhali (315657)of Bachhara Ground water based water supply scheme for arsenic affected areas of Beldanga - II Block in Murshidabad District under Murshidabad Division, P.H.E. , SM/11161 | Augmentation | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Kadkhali ( Village Code -315657) under Bachhara Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga_II Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723431) | 1570/MURD | 25/06/2021 | 60 | M/S. S. DAS AND ENTERPRISE | 23.43 | 0 | 0 | 0
4537 | MURSHIDABAD | Berhampore Mechanical | Source Augmentation & Functional House Hold tap Connection (FHTC) under Mouza Kadkhali (315657)of Bachhara Ground water based water supply scheme for arsenic affected areas of Beldanga - II Block in Murshidabad District under Murshidabad Division, P.H.E. , SM/11161 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under Bachhara ground water based water supply scheme under Block_ Beldanga-II Dist. - Murshidabad under MEDB, PHE Dte. | 4331/MEDB | 29/12/2023 | 91 | NABAUDYAG ELECTRICAL ENGINEERING CO OP. SOC. LTD. | 22.69 | 0 | 0 | 0
4538 | MURSHIDABAD | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. , SM/11713 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.26 | 100 | 100
4539 | MURSHIDABAD | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. , SM/11713 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jotkomol Zone-II Water Supply Scheme of TW-I HW Site under Jangipur Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3065/MURD | 17/11/2022 | 30 | M/S B.R. SUPPLIERS | 10.6 | 9.12 | 50 | 100
4540 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. , SM/11713 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Jotkamal , Zone-II ground water based water supply scheme under Block- Raghunathganj-II Dist. Murshidabad under MEDB, PHE Dte. | 3784/MEDB | 03/11/2023 | 92 | DAS ENTERPRISE (CHOA) | 11.29 | 8.97 | 79.48 | 20
4541 | MURSHIDABAD | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. , SM/11713 | Augmentation | Allied works for Renovation of Existing IEP (Capacity 54 Cu.M/hr) at Jotkamal Zone-II W/S Scheme in connection with Augmentation of Jotkamal (Zone-II) PWSS under Murshidabad Division P.H.Engineering Dte. | 784/MURD | 14/03/2024 | 20 | M/S BAPPA ENTERPRISE | 11.26 | 0 | 0 | 0
4542 | MURSHIDABAD | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. , SM/11713 | Augmentation | Renovation of Existing IEP (Capacity 58 Cu.M/hr) for changing of 01 No Iron Removal Filter media unit of (3.30 m dia x 1.50 M HOS) & 01 No Oxidation Chember of (1.00 M dia x 1.00 M HOS) and painting all vessel, pipes etc. all complete for Augumentation of JOTKOMAL ZONE-II Pipe Water supply scheme, Block-Raghunathganj-II, under Murshidabad Division P.H.E Dte. in the district of Murshidabad. | 3560/MURD | 21/11/2023 | 30 | M/S BAPPA ENTERPRISE | 4.89 | 3.94 | 100 | 100
4543 | MURSHIDABAD | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. , SM/11713 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SRIKANTABATI PART B & JOTKAMAL ZONE -II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 3395/MURD | 01/11/2023 | 21 | KALACHAND DAS | 18.4 | 12.8 | 100 | 100
4544 | MURSHIDABAD | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. , SM/11713 | Augmentation | Sinking of 01 (One) No of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JOTKOMAL ZONE-II Water Supply Scheme as required at Suti-II Block under Murshidabad Division, P.H. Engineering Dte | 3425/MURD | 02/11/2023 | 21 | SUJIT KUMAR SAHA | 11.79 | 8.65 | 48.36 | 100
4545 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. , SM/11713 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well of Pump House No. II and NEW OHR SITE of Zone-II under JOTKAMAL PIPED WATER SUPPLY SCHEME, BLOCK- DOMKAL RAGHUNATHGANJ-II DISTRICT- MURSHIDABAD under MEDB, PHE Dte. | 1143/MEDB | 14/05/2025 | 92 | HANNAN BUILDERS PVT LTD | 22.73 | 0 | 0 | 0
4546 | MURSHIDABAD | Murshidabad Division | Augmentation of Jotkamal Zone - II Piped Water Supply Scheme Block Raghunathganj- II District - Murshidabad. , SM/11713 | Augmentation | Augmentation of Ground Water Based JOT KAMAL (ZONE-I), JOTKAMAL (Zone-II) & JOTKAMAL (Zone-III) PWSS, Block- RAGHUNATHGANJ-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | 2643/MURD | 23/08/2023 | 587 | M/S NIRAPADA BHATTACHARJEE | 1194.05 | 107.41 | 23.83 | 10
4547 | MURSHIDABAD | Murshidabad Division | Augmentation of Dakshin Sekhhalipur Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/11716 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.19 | 100 | 100
4548 | MURSHIDABAD | Murshidabad Division | Augmentation of Dakshin Sekhhalipur Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/11716 | Augmentation | Material Requisition To Resource Division | 1167/MURD/5 | 28/04/2023 | 0 | Resource Division | 0.33 | 0 | 0 | 0
4549 | MURSHIDABAD | Murshidabad Division | Augmentation of Dakshin Sekhhalipur Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/11716 | Augmentation | Renovation of Existing AIRP (Capacity 11 Cu.M) for changing of filter media of 1 No Polishing unit (2.17 M dia x 1.50 M HOS) & 1 No Primary Unit ( 2.17 M dia x 2.00 M HOS) and painting all vessel, pipes etc. all complete for Augumentation of Dakshin Sekhhalipur Pipe Water supply scheme, Block-Raghunathganj-II, under Murshidabad Division P.H.E Dte. in the district of Murshidabad. | 616/MURD | 28/02/2024 | 30 | M/S BAPPA ENTERPRISE | 13.7 | 0 | 0 | 0
4550 | MURSHIDABAD | Murshidabad Division | Augmentation of Dakshin Sekhhalipur Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/11716 | Augmentation | Allied works for Renovation of Existing AIRP, Gobordanga Model (Capacity 11 Cu.M/hr) at Dakhin Sekhalipur W/S Scheme in connection with Augmentation of Dakhin Sekhalipur PWSS under Murshidabad Division P.H.Engineering Dte. | 783/MURD | 14/03/2024 | 20 | M/S BAPPA ENTERPRISE | 7.56 | 0 | 0 | 0
4551 | MURSHIDABAD | Murshidabad Division | Augmentation of Dakshin Sekhhalipur Pipe Water Supply Scheme Block - Raghunathganj -II District - Murshidabad. , SM/11716 | Augmentation | Providing Functional Household Tap Connections (FHTC) with laying of Pipeline for last mile connectivity in village Dakshin Sekhalipur (314102) & Paschim Khandua(314103) Village in connection with Augumentation of Dakshin Sekhhalipur Pipe Water supply scheme, Block-Raghunathganj-II, under Murshidabad Division P.H.E Dte. | 914/MURD | 30/03/2023 | 120 | PROSENJIT DAS | 72.6 | 38.7 | 100 | 85
4552 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( , SM/08099 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (Jal Jeevan Mission ) and under command area of village of Bhatsala ( Village Code -314688) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344) TNO- 165/21-22/EE | 413-MSD/21-22 | 22/03/2022 | 0 | MAMON ENTERPRISE AND CONSTRUCTION (MASIUR RAHAMAN MOLLA) | 27.35 | 0 | 0 | 0
4553 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( , SM/08099 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) under Jal Swapna ( Jal Jeevan Mission) and under command area of village Juginda (Village code 314727)under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block, of Murshidabad District under Murshidabad Division, PHE Dte. (Scheme ID 0001723344) | 1468/MURD | 03/06/2022 | 120 | SUJIT KUMAR SAHA | 130.65 | 78.95 | 60.43 | 0
4554 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( , SM/08099 | Retrofitting | Protection of Over Head Reservoir by Masonry wall & construction of entrance gate of Head work site premises under Juginda Z-I Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. | 475/ISD | 03/09/2021 | 60 | BISWAS CONSTRUCTION PAN NO : AHNPB6929M | 3.64 | 3.64 | 100 | 0
4555 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( , SM/08099 | Retrofitting | Protection of Head work site & Pump House No-II premises by raising Boundary wall height by R.B.T fencing under Juginda Z-I Water Supply Scheme under Islampur Sub Division, under Murshidabad Division, P.H.E. Dte. | 474/ISD | 03/09/2021 | 60 | M/S. SAJEDA ENTERPRISE(ABDUL KUDDUS SK) | 4.7 | 4.69 | 100 | 0
4556 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( , SM/08099 | Retrofitting | Retrofitting Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (Jal Jeevan Mission ) and under command area of village of Bhatsala ( Village Code -314688) under Juginda Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Domkal Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0001723344) | 1349/MURD | 09/06/2021 | 60 | MAMON ENTERPRISE AND CONSTRUCTION (MASIUR RAHAMAN MOLLA) | 77.6 | 82.67 | 106.55 | 0
4557 | MURSHIDABAD | Murshidabad Division | Retrofitting of Functional Household Tap Connection (FHTC) unde Jal Swapna (JJM) of mouza Bhatsala ( 314688) & Juginda ( 314727 ) of Juginda under Ground Water Based Water Supply Scheme for arsenic affected areas of Domkal Block of Murshidabad District ( , SM/08099 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | 305/BSD | 13/08/2021 | 30 | IMAGIN COMMUNICATION | 4.33 | 8.67 | 200 | 0
4558 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha , SM/12581 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of DIGHA ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | 3729/MEDB | 03/11/2023 | 92 | SURAKSHA | 11.18 | 0 | 0 | 0
4559 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha , SM/12581 | Augmentation | Material Requisition To Resource Division | 196/BD-I/9 | 09/02/2024 | 0 | Resource Division | 3.75 | 0 | 0 | 0
4560 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha , SM/12581 | Augmentation | Formal work order for Augmentation of DIGHA Piped water supply scheme to accommodate contruction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1822/BD-I | 31/03/2023 | 642 | SUJIT KUMAR SAHA | 255.85 | 27.9 | 10.91 | 10
4561 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha , SM/12581 | Augmentation | Improvement of Existing AIRP (Modified Sujapur Sadipur Model, Capacity 30.00 cum/hr) including required allied works of DIGHA PWSS under Jal Jeevan Mission within Bhagwangola-I inconnection with Augmentation under Berhampore Division-I , P.H.E. Dte. In the districtof Murshidabad. | 755/BD-I | 22/05/2025 | 30 | DEBASISH SARKAR | 24.4 | 0 | 0 | 0
4562 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha , SM/12581 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DIGHA Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 262/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.43 | 2.43 | 100 | 0
4563 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha , SM/12581 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Digha ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | 1364/BD-I | 21/12/2022 | 30 | SELIM SARKAR | 2.27 | 1.73 | 100 | 100
4564 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha , SM/12581 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Digha Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 160/BD-I | 05/02/2024 | 30 | M/S D. PALIT & CO. | 9 | 7.74 | 100 | 100
4565 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha , SM/12581 | Augmentation | Improvement of R.C.C Elevaced Reservoir (225 Cum) of Ground Water Based Supply Scheme for Augmentation of Digha Water Supply Scheme under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | 895/BD-I | 06/06/2024 | 30 | K.B CONSTRUCTION | 6.7 | 0 | 0 | 100
4566 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur , SM/12583 | Augmentation | Hiring of Diesel driven Bolero/Equivalent four wheeler car for the official use of the Executive Engineer under Office of the Executive Engineer, Mechanical/electrical Division, PHE Dte. in the district of Murshidabad. | 658/AE/MEDB | 31/03/2023 | 183 | M/S SAJAHAN CHOWDHURY | 0.9 | 2.27 | 253.7 | 10
4567 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur , SM/12583 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of PASCHIM RAMPUR ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | 3775/MEDB | 03/11/2023 | 92 | MERCURY ENGINEERING CO | 22.4 | 19.13 | 85.38 | 8
4568 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur , SM/12583 | Augmentation | Continuation Order Hiring of Diesel driven Bolero/Equivalent four wheeler car for the official use of the Assistant Engineer-I under Office of the Executive Engineer, Mechanical/electrical Division, PHE Dte. in the district of Murshidabad. | 237/MEDB | 27/01/2023 | 59 | M/S SAJAHAN CHOWDHURY | 0.29 | 0.77 | 267.78 | 10
4569 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur , SM/12583 | Augmentation | Material Requisition To Resource Division | 196/BD-I/15 | 09/02/2024 | 0 | Resource Division | 41.52 | 0 | 0 | 0
4570 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur , SM/12583 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Paschim Rampur ground water supply scheme in Bhagwabgola-I Block Dist_Murshidabad under MEDB PHE Dte. " | 1134/MEDB | 13/05/2025 | 92 | M/S SAJAHAN CHOWDHURY | 49.94 | 0 | 0 | 0
4571 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur , SM/12583 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PASCHIMRAMPUR PWSS (TW-III Site) within BHAGWANGOLA-I Block under JAL JEEVAN MISSION in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. (01 No TW) | 776/BD-I | 22/05/2025 | 15 | M/S GHOSH ENTERPRISE | 9 | 0 | 0 | 0
4572 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur , SM/12583 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Paschim Rampur ground water supply scheme in Bhagwangola-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-90.00 Cum/Hr.) | 614/BD-I | 22/04/2025 | 300 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 207.69 | 0 | 0 | 0
4573 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur , SM/12583 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for PASCHIM RAMPUR Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 260/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.82 | 2.82 | 100 | 100
4574 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur , SM/12583 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Paschim Rampur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | 59/BD-I | 25/04/2023 | 30 | SAIF TRADERS | 2.05 | 2.01 | 100 | 100
4575 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur , SM/12583 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Rampur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | 124/BD-I | 12/05/2023 | 780 | HARUN ALL RASHID & BROTHERS | 17.74 | 7.36 | 47.12 | 50
4576 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur , SM/12583 | Augmentation | Repair And Renovation Works Of R.C.C Elevated Reservoir (350 Cum) for Paschim Rampur water supply scheme of Bhagwangola-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 996/BD-I | 30/10/2023 | 283 | B.M. ENTERPRISE | 8.53 | 8.47 | 100 | 100
4577 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME OF RAMKANTAPUR, BLOCK- SUTI - I, DIST- MURSHIDABAD , SM/10812 | Augmentation | Preparation of D.P.R(Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (RAMAKANTAPUR PWSS Scheme,Block- SUTI-I to be Augmentation/Rejuvination under Murshidabad Division P.H.E.Dte. | 3253/MURD | 05/10/2021 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 7.1 | 7.1 | 100 | 1
4578 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME OF RAMKANTAPUR, BLOCK- SUTI - I, DIST- MURSHIDABAD , SM/10812 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Ramkantapur ground water based water supply scheme under Block_ Suti-I, Dist. - Murshidabad under MEDB, PHE Dte. | 1879/MEDB | 16/06/2023 | 92 | M/S SAMRIDDHI ENTERPRISE | 22.77 | 0 | 0 | 0
4579 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME OF RAMKANTAPUR, BLOCK- SUTI - I, DIST- MURSHIDABAD , SM/10812 | Augmentation | Material Requisition To Resource Division | 1210/MURD/03 | 02/05/2023 | 0 | Resource Division | 60.48 | 0 | 0 | 0
4580 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME OF RAMKANTAPUR, BLOCK- SUTI - I, DIST- MURSHIDABAD , SM/10812 | Augmentation | Sinking of 07 (Seven) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Madna Zone-I T.W-II, Ramakantapur T.W-I, Hilora Zone-I T.W-II, Zone-III T.W.-II, Madna Zone-II T.W-II, Bewa T.W- I,II, Water Supply Scheme under Jangipur Sub- Division, Murshidabad Division, P.H.Engineering Dte. | 659/MURD | 19/03/2025 | 90 | R.K. DRILLING SERVICES | 82.53 | 0 | 0 | 0
4581 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME OF RAMKANTAPUR, BLOCK- SUTI - I, DIST- MURSHIDABAD , SM/10812 | Augmentation | Construction of 200 Cum OHR, Pump House at Head Work Site Laying Distribution System, Rising Main Connection, FHTC Connection, for Augmentation of Ramakantapur PWSS in Suti-I Block, under Murshidabad Division, PHE. Dte. | 2374/MURD | 19/11/2025 | 365 | MOTI RAHAMAN | 278.11 | 0 | 0 | 0
4582 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11561 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS ( SAKTIPUR PWSS Scheme, Block - Beldanga-II) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3266/MURD | 05/10/2021 | 60 | RADIANT | 10.43 | 3.28 | 100 | 0
4583 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11561 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shaktipur Zone-I &II Water Supply Scheme at HW Site under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3072/MURD | 17/11/2022 | 45 | NADIA TUBEWELLS | 21.18 | 10 | 100 | 1
4584 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11561 | Augmentation | Material Requisition To Resource Division | 1278/MURD/3 | 10/05/2023 | 0 | Resource Division | 129.08 | 0 | 0 | 0
4585 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11561 | Augmentation | Formal Work Order for Augmentation of Saktipur Zone-I Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Beldanga-II Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 2860/MURD | 19/10/2022 | 895 | M/S. ROY TRADING CO. | 302.59 | 241.27 | 79.74 | 80
4586 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11561 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I (H.W Site) at Zone-I and Pump House No.-I (H.W Site) at Zone-II of Saktipur ground water based water supply scheme under Block- Beldanga-II, Dist. Murshidabad under MEDB, PHE Dte. | 2020/MEDB | 19/06/2023 | 92 | INDTECH ASSOCIATES | 23.14 | 18.99 | 100 | 8
4587 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SAKTIPUR PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN BELDANGA -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11561 | Augmentation | Saktipur Zone-1 Ph-1 Application No-3004554369 | 254/WBSEDCL-JJM | 17/01/2024 | 0 | WBSEDCL | 2.98 | 0 | 0 | 0
4588 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11566 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (CHANDPUR PWSS Scheme, Block - NOWDA) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3277/MURD | 05/10/2021 | 60 | RADIANT | 14.82 | 5.15 | 100 | 1
4589 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11566 | Augmentation | Repair and Renovation of Pump high lift pupm house at head works site of Chandpur water supply scheme under Berhampore Sub Division, P.H.E. Dte. | 13/BSD | 10/01/2022 | 30 | MASUM CONSTRUCTION | 3.55 | 2.89 | 100 | 0
4590 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11566 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No._I ,II and III ,Zone-II under Chandpur ground water based water supply scheme under Block_ Nowda Dist. Murshidabad under MEDB, PHE Dte. | 1873/MEDB | 16/06/2023 | 92 | B. T. PROJECTS PVT. LTD. | 34.2 | 0 | 0 | 0
4591 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11566 | Augmentation | Material Requisition To Resource Division | 1278/MURD/5 | 10/05/2023 | 0 | Resource Division | 11.58 | 0 | 0 | 0
4592 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11566 | Augmentation | Formal Work Order for Augmentation of CHANDPUR Zone-II Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Nawda Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 2496/MURD | 30/08/2022 | 945 | BISWAS ENTERPRISE (PROP. JESMIN KHATUN) | 388.72 | 157.62 | 40.55 | 80
4593 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11566 | Augmentation | Material Requisition To Resource Division | 305/MURD/04 | 29/01/2024 | 0 | Resource Division | 10.27 | 0 | 0 | 0
4594 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11566 | Augmentation | Material Requisition To Resource Division | 1811/MURD/04 | 20/06/2024 | 0 | Resource Division | 21.13 | 0 | 0 | 0
4595 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED CHANDPUR PWSS (ZONE- II ) TO ACCOMMODATE FHTC IN NAWDA BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11566 | Augmentation | CHANDPUR Z-II PH-I | 426/WBSEDCL-JJM | 12/03/2024 | 0 | WBSEDCL | 22.73 | 0 | 0 | 0
4596 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11570 | Augmentation | Preparation of D.P.R (Consultancy work) in connection with the Functional House Hold Connection of different existing PWSS (Katlamari PWSS Scheme, Block - Raninagar-II) to be Augmentation / Rejuvination under Murshidabad Division P.H.E. Dte. | 2745/MURD | 03/09/2021 | 60 | RADIANT | 11.14 | 5.57 | 100 | 1
4597 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11570 | Augmentation | Material Requisition To Resource Division | 3052/D/MURD | 17/11/2022 | 0 | Resource Division | 27.08 | 0 | 0 | 0
4598 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11570 | Augmentation | Formal work order for Laying of Distribution system(Part-A) , Rising Main, Providing Functional Household Tap Connection to 670 nos household & Repair and Renovation of OHR of 500 cum Capacity of Katlamari Zone -I Water Supply Scheme of Islampur Sub-Division under Murshidabad Division, P.H.E Dte. | 3278/MURD | 09/12/2022 | 60 | ARINDAM MAJUMDAR | 135.29 | 45.97 | 33.97 | 30
4599 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11570 | Augmentation | Formal work order for Laying of Distribution system (Part-B) and Providing Functional Household Tap Connection to 665 nos household & Construction of Boundary Wall and repairing of Pump House of Katlamari Zone -I of Islampur Sub-Division under Murshidabad Division,P.H.E Dte [(i)Amount for LDS & FHTC: Rs.14057282.00 & (ii) Amount for Construction of Boundary Wall and repairing of Pump House : Rs. 2963929.00] | 3150/MURD | 28/11/2022 | 60 | J.S. CONSTRUCTION | 170.18 | 148.74 | 87.4 | 50
4600 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11570 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-I of KATLAMARI ground water based water supply scheme under Block- RANINAGAR-II, Dist. Murshidabad under MEDB, PHE Dte. | 4345/MEDB | 29/12/2023 | 91 | ARINDAM MAJUMDAR | 8.96 | 0 | 0 | 0
4601 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11570 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at KATLAMARI PWSS (ZONE- I ) Water Supply Scheme at Head Work Site, 2nd Site site at Raninagar-II Block under Murshidabad Division, P.H. Engineering Dte. | 1755/MURD | 06/07/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 18.44 | 17 | 100 | 100
4602 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11570 | Augmentation | NEW SERVICE CONNECTION AT KATLAMARI Z1 PH3, ID APPLICATION NO.3004548905 | 285/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.38 | 0 | 0 | 0
4603 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11570 | Augmentation | Formal work order for Laying of Distribution system (Part-C) and Providing Functional Household Tap Connection to 670 nos household & Construction of Pump House of Katlamari Zone-I of Islampur Sub-Division under Murshidabad Division, P.H.E Dte. | 3191/MURD | 01/12/2022 | 1038 | ULTRA CONSTRUCTION. | 110.88 | 64.28 | 57.97 | 92
4604 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED KATLAMARI PWSS (ZONE- I ) TO ACCOMMODATE FHTC IN RANINAGAR-II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/11570 | Augmentation | Construction of Boundwary Wall , Pump House T.W-III , PCC approach road , Land Development for Augmentation of Katlamari PWSS in Raninagar-II Block , Islampur Sub-Division under Murshidabad Division ,PHE. Dte. | 1460/MURD | 26/06/2025 | 90 | SANJITA CONSTRUCTION | 22.83 | 0 | 0 | 0
4605 | MURSHIDABAD | Murshidabad Division | MAHISAR AND ADJOINING MOUJAS PWSS , SM/13725 | New | Material Requisition To Resource Division | 1043/MURD/13 | 17/04/2023 | 0 | Resource Division | 26.09 | 0 | 0 | 0
4606 | MURSHIDABAD | Berhampore Mechanical | MAHISAR AND ADJOINING MOUJAS PWSS , SM/13725 | New | Electric Service Connection at MAHISAR PWSS PH I, Application NO.3004403589, ID 304119890 | 195/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 10.21 | 0 | 0 | 0
4607 | MURSHIDABAD | Berhampore Mechanical | MAHISAR AND ADJOINING MOUJAS PWSS , SM/13725 | New | Electric Service Connection at MAHISAR PWSS PH II, Application NO.3004403661, ID 304119931 | 196/WBSEDCL-JJM | 19/12/2023 | 0 | WBSEDCL | 10.29 | 0 | 0 | 0
4608 | MURSHIDABAD | Murshidabad Division | MAHISAR AND ADJOINING MOUJAS PWSS , SM/13725 | New | Formal work order for the work of MAHISAR & Adjoining Mouzas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Laying Distribution System, Rising Main, boundary wall and service road , under Jal Swapna of Murshidabad District under Murshidabad Division ,PHE.Dte.( Scheme ID -PH222362278S000 | 37/MURD | 04/01/2023 | 1062 | NAYLA CONSTRUCTION | 611.61 | 123.44 | 20.18 | 50
4609 | MURSHIDABAD | Berhampore Mechanical | MAHISAR AND ADJOINING MOUJAS PWSS , SM/13725 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under MAHISAR ground water based water supply scheme under Block_ KHARGRAM Dist. - Murshidabad under MEDB, PHE Dte. | 2083/MEDB | 19/06/2023 | 926 | JOGMAYA ENGINEERING | 23.47 | 17.97 | 76.54 | 50
4610 | MURSHIDABAD | Berhampore Mechanical | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Amarkunda, Bagor, Nandigram, Madhunia, Chayan Nagar, Sankuria, Rainda ( ) of Amarkundu under Ground Water Based Water Supply Scheme for arsenic affected areas of Nabagram Block of , SM/11230 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under Amarkundu ground water based water supply scheme under Block_ Nabagram, Dist. - Murshidabad under MEDB, PHE Dte. | 1922/MEDB | 16/06/2023 | 92 | MAA TARA ENTERPRISE | 21.12 | 0 | 0 | 0
4611 | MURSHIDABAD | Murshidabad Division | Source Augmentation & Functional Household Tap Connections (FHTC) of Mouza Amarkunda, Bagor, Nandigram, Madhunia, Chayan Nagar, Sankuria, Rainda ( ) of Amarkundu under Ground Water Based Water Supply Scheme for arsenic affected areas of Nabagram Block of , SM/11230 | Augmentation | Laying of different dia U.P.V.C Pipeline for Distribution Network (Remaining Portion) and construction of RCC Stand Post including platform at Sankuria Village under Improvement work of Amarkundu Water Supply Scheme under Lalbagh Sub-Division,P.H.E. Dte.in the District Murshidabad. | 413/LSD | 27/12/2021 | 30 | SARAJIT KUMAR MAJUMDER | 4.88 | 0 | 0 | 0
4612 | MURSHIDABAD | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS , SM/13620 | New | Material Requisition To Resource Division | 1210/MURD/41 | 02/05/2023 | 0 | Resource Division | 46.94 | 0 | 0 | 0
4613 | MURSHIDABAD | Berhampore Mechanical | SALINDA AND ADJOINING MOUJAS PWSS , SM/13620 | New | New connection charge for Salinda PWSS, P/H No.-II. | 120/WBSEDCL-JJM | 27/09/2023 | 0 | WBSEDCL | 4.94 | 0 | 0 | 0
4614 | MURSHIDABAD | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS , SM/13620 | New | Formal Work Order For Laying of Distribution System (Part-B) and Construction of Pump House for Augmentation of SALINDA PWSS of Kandi Sub-Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad | 160/MURD | 16/01/2023 | 989 | SOM CONSTRUCTION AGENCY | 146.49 | 87.47 | 59.71 | 39
4615 | MURSHIDABAD | Berhampore Mechanical | SALINDA AND ADJOINING MOUJAS PWSS , SM/13620 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SALINDA ground water based water supply scheme under Block_ Bharatpur-II Dist. - Murshidabad under MEDB, PHE Dte. | 1880/MEDB | 16/06/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 24.14 | 19.48 | 80.69 | 11
4616 | MURSHIDABAD | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS , SM/13620 | New | Additional & Balance Work Laying of Distribution System , Land Devolapement of SALINDA PWSS in Bharatpur-II Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | 54/MURD | 05/01/2024 | 30 | DHIRENDRANATH MONDAL | 17.25 | 13.15 | 76.19 | 80
4617 | MURSHIDABAD | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS , SM/13620 | New | Construction of Pump House Cum Chlorine Room, Boundary Wall, Approach Road & Land Development of Salinda PWSS in Bhratpur-II Block , KANDI Sub-Division under Murshidabad Division , PHE. Dte. | 823/MURD | 15/03/2024 | 60 | M/S RELIABLE | 27.67 | 0 | 0 | 0
4618 | MURSHIDABAD | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS , SM/13620 | New | Sinking of 02(Two) Nos 250 mm x 150 mm dia tube well 100.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SALINDA PWSS at Head Work Site & 2nd Tube Well Site in Bharatpur-II Block under Kandi Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 3406/MURD | 22/12/2022 | 45 | INDRAJIT MAZUMDAR | 16.8 | 14.32 | 100 | 100
4619 | MURSHIDABAD | Berhampore Mechanical | SALINDA AND ADJOINING MOUJAS PWSS , SM/13620 | New | Salinda PH-1 Application no- 3004547659 | 248/WBSEDCL-JJM | 16/01/2024 | 0 | WBSEDCL | 3.52 | 0 | 0 | 0
4620 | MURSHIDABAD | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS , SM/13620 | New | Formal work order for Construction of 350 Cum OHR,Laying Distribution System (PART-C),Rising Main Connection, FHTC , for Uncovered of SALINDA PWSS in Bharatpur-II Block , Kandi Sub-Division under Murshidabad Division ,PHE.Dte. | 340/MURD | 08/02/2023 | 1301 | DHIRENDRANATH MONDAL | 387.6 | 365.84 | 94.38 | 25
4621 | MURSHIDABAD | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS , SM/13620 | New | Formal Work Order For Laying of Distribution System (Part-A) and Construction of Boundary wall of SALINDA PWSS of Kandi Sub-Division under Murshidabad Division, P.H.E.Dte. in the district of Murshidabad | 161/MURD | 17/01/2023 | 952 | TANUSHREE ENTERPRISE | 145.06 | 97.7 | 67.35 | 35
4622 | MURSHIDABAD | Murshidabad Division | SALINDA AND ADJOINING MOUJAS PWSS , SM/13620 | New | Allied & Balance Work for Laying of Distribution System, Approach Service Road, Construction of Box Culvert and Land Development of SALINDA PWSS in Bharatpur-I Block, of Kandi Sub-Division under Murshidabad Division ,PHE Dte. | 3143/MURD | 03/12/2024 | 90 | DHIRENDRANATH MONDAL | 38.56 | 0 | 0 | 30
4623 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at CHOWRIGACHHA G.P. under Murshidabad Division, P.H.E.Dte. | 353/BSD | 27/08/2021 | 30 | TINA ROY | 4.16 | 4.16 | 100 | 1
4624 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bara Satui (Village code 315341) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723177 in the District of Murshidabad.3136/MURD, 11/12/2020 | 172-MSD/21-22 | 01/11/2021 | 0 | UTTAM MUKHERJEE | 32.45 | 0 | 0 | 0
4625 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) at village of FATEPUR West side ( Village Code _315310) of Fatepur Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | 106/BSD | 28/03/2022 | 30 | CHOWDHURY CONSTRUCTION | 4.79 | 0.75 | 100 | 0
4626 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Work Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Jangipur Sub-Division,P.H.E Dte. [Period for 01 (One) Year] i.e. from 18.04.2022 to 17.04.2023.[Vehicle No-WB57E7960] | 205/JSD | 18/04/2022 | 365 | MAJIBUR RAHAMAN | 4.76 | 1.6 | 100 | 0
4627 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Continuation work for Hiring of 1 (one) no. Diesel Bolero/Marshal car (WB-57C 9120) for official use of the Assistant Engineer, Jangipur Sub Division, Murshidabad Division P.H.E. Dte. for the period from 01.03.2022 to 31.05.2022 (i.e) 3 (Three) months (vehicle No.-WB-57C/9120). | 88/JSD | 22/02/2022 | 89 | MANUAR HOSSAIN | 0.45 | 0.23 | 100 | 100
4628 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months | 165/ISD | 01/04/2023 | 183 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 2.37 | 100 | 100
4629 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting |  | 97-MSD/2023-24 | 08/06/2023 | 0 | DULAL CHOWDHURY | 0.8 | 0 | 0 | 0
4630 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel / LPG / CNG Engine) in perfect good running condition of performing a very long journey and should be covered anywhere without any trouble on Daily hire basis for official use for the Office of the Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01 (One) Year].for the month of April¿2023 to March¿2024 | 330/MURD | 07/02/2023 | 365 | SOUMYADIP MISRA | 4.78 | 4.57 | 95.51 | 32
4631 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Continuation Work Order for Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Jangipur Sub-Division,P.H.E Dte. [Period for 01 (One) Year] i.e. from 18.04.2023 to 17.04.2024.[Vehicle No-WB57E7960] | 437-/AA/JSD | 17/04/2023 | 365 | MAJIBUR RAHAMAN | 4.76 | 2.79 | 100 | 70
4632 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Chhota Satui (Village code 315343) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID- 1723177 in the District of Murshidabad. | 1651/MURD | 29/06/2021 | 180 | DAS TRADING CO. | 80.05 | 104.67 | 161.23 | 1
4633 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Preparation of an Audio Video docomentory programme for Awarness of Functional Household Tape Connection(FHTC) under Jal Swapna Programme at different Gram Panchayet which covered by different water supply scheme under Berhampore Sub-Division under Murshidabad Division, P.H.E Dte. | 306/BSD | 13/08/2021 | 30 | IMAGIN | 3.26 | 6.51 | 200 | 0
4634 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Providing Functional Household Tap Connections (FHTC) in connection with JalSwapna (JalJeevan Mission ) at village of FATEPUR West side ( Village Code _315310) of Fatepur Ground Water Based Water Supply Scheme Under Berhampore Sub-Division ; Mushidabad Division PHE Dte. | 106/BSD | 28/03/2022 | 30 | CHOWDHURY CONSTRUCTION | 4.79 | 0 | 0 | 90
4635 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Hiring of Maxicab ( Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/LPG/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on Daily hire basis for official use of the Superintending Engineer, Murshidabad Circle, PHE Dte. [Period for 01(One) Year] (period for i.e 07/02/2023 to 06/02/2024). | 329/MURD | 07/02/2023 | 365 | MD MUKLESUR RAHAMAN | 4.78 | 2.45 | 63.53 | 1
4636 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Continuation Order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Lalbagh Sub-Division, P.H.E Dte. for 06 (Six) Months i.e. from 08.07.2023 to 07.01.2024. | 24/LSD | 30/06/2023 | 184 | BARI ENTERPRISE | 0.9 | 2.24 | 100 | 100
4637 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | ENGAGEMENT OF CAR FOR SE-MC, PHE DTE. | 342-MSD/2024-25 | 06/09/2024 | 0 | SOUMYADIP MISRA | 0.21 | 0 | 0 | 0
4638 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Bara Satui (Village code 315341) under Bara Satui Ground Water Based Water Supply Scheme for Arsenic Affected Area of Berhampore Block, under Murshidabad Division, PHE Dte. Scheme ID - 1723177 in the District of Murshidabad. | 3136/MURD | 11/12/2020 | 60 | UTTAM MUKHERJEE | 39.68 | 2.19 | 100 | 1
4639 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Bara Satui, Chhota Satui (315341 & 315343) of Bara Satui under Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Berhampore Block of Murshidabad , SM/07662 | Retrofitting | Extension of Distribution UPVC pipeline at Hanumandanga, Poradanga & Haldepara area for Providing Balance Functional Household Tap connection (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command areas of village of Choto Satui (Village Code-315343) under Bara Satui Ground water based water suply scheme for Arsenic affected areas of Berhampore Block, under Murshidabad Division, P.H.E. Dte. | 768/MURD | 22/03/2022 | 30 | DAS TRADING CO. | 42.34 | 27.11 | 100 | 1
4640 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur , SM/12739 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Faridpur ground water based water supply scheme under Block- Bhagawangola-II, Dist. Murshidabad under MEDB, PHE Dte. | 4333/MEDB | 29/12/2023 | 91 | ASSOCIATED ELECTRICAL CO. | 11.41 | 9.48 | 83.07 | 20
4641 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur , SM/12739 | Augmentation | Material Requisition To Resource Division | 196/BD-I/16 | 09/02/2024 | 0 | Resource Division | 38.7 | 0 | 0 | 0
4642 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur , SM/12739 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Faridpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 44/BD-I | 24/04/2023 | 30 | SUJIT KUMAR SAHA | 8.99 | 0 | 0 | 0
4643 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur , SM/12739 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for FARIDPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 269/BD-I | 08/03/2022 | 10 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.7 | 2.7 | 100 | 1
4644 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur , SM/12739 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Foridpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | 1411/BD-I | 04/01/2023 | 10 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 2.23 | 1.41 | 100 | 100
4645 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur , SM/12739 | Augmentation | Improvement of OHR (350 Cum) of Ground Water Based Supply Scheme for Augmentation of Faridpur water supply scheme of Bhagwangola-II block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | 893/BD-I | 06/06/2024 | 30 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 8.56 | 8.04 | 100 | 100
4646 | MURSHIDABAD | Berhampore Mechanical | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13936 | New | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under MAHAMMADPUR ground water based water supply scheme under Block_ Khargram, Dist. - Murshidabad under MEDB, PHE Dte. | 2016/MEDB | 19/06/2023 | 92 | A.G. ENTERPRISE | 20.38 | 0 | 0 | 0
4647 | MURSHIDABAD | Murshidabad Division | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13936 | New | Material Requisition To Resource Division | 1067/MURD/6 | 18/04/2023 | 0 | Resource Division | 24.66 | 0 | 0 | 0
4648 | MURSHIDABAD | Murshidabad Division | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13936 | New | Material Requisition To Resource Division | 79/MURD/03 | 09/01/2024 | 0 | Resource Division | 8.45 | 0 | 0 | 0
4649 | MURSHIDABAD | Murshidabad Division | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13936 | New | Material Requisition To Resource Division | 112/MURD/07 | 11/01/2024 | 0 | Resource Division | 8.45 | 0 | 0 | 0
4650 | MURSHIDABAD | Berhampore Mechanical | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13936 | New | NEW SERVICE CONNECTION AT MAHHAMMADPUR PH1 ID304222178 | 229/WBSEDCL-JJM | 09/01/2024 | 0 | WBSEDCL | 2.7 | 0 | 0 | 0
4651 | MURSHIDABAD | Berhampore Mechanical | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13936 | New | new service connection at MAHAMMADPUR PH2 ID304222150 | 228/WBSEDCL-JJM | 09/01/2024 | 0 | WBSEDCL | 4.75 | 0 | 0 | 0
4652 | MURSHIDABAD | Murshidabad Division | MAHAMMADPUR AND IT'S ADJOINING MOUJAS PWSS , SM/13936 | New | Formal work order for the work of MAHAMMADPUR & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | 143/MURD | 17/01/2023 | 1094 | SUJIT KUMAR SAHA | 315.18 | 114.4 | 36.3 | 70
4653 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BALI (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/14426 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BALI ZONE-I Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1595/BD-I | 28/02/2023 | 10 | TECHVISION | 2.46 | 2.46 | 99.95 | 0
4654 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BALI (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/14426 | Augmentation | Material Requisition To Resource Division | 94/BD1 | 22/01/2024 | 0 | Resource Division | 3.29 | 0 | 0 | 0
4655 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF BALI (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/14426 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Bali Zone-I ground water supply scheme in Nawda Block, Dist_Murshidabad under MEDB PHE Dte. | 1151/MEDB | 14/05/2025 | 92 | M/S SAJAHAN CHOWDHURY | 39.62 | 0 | 0 | 0
4656 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BALI (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/14426 | Augmentation | Construction of Boundary Wall with Main Entrance gate and barbed wire facing at Augmentation of BALI ZONE-I PWSS of Nawda Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | 1129/BD-I | 11/07/2024 | 45 | KHANDAKAR CONSTRUCTION | 18.69 | 0 | 0 | 0
4657 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF BALI (ZONE I) PIPED WATER SUPPLY SCHEME. , SM/14426 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Bali Zone-I ground water supply scheme in Nawda Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | 322/BD-I | 24/02/2025 | 300 | M/S SAJAHAN CHOWDHURY | 122.62 | 0 | 0 | 0
4658 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. , SM/14427 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KASHIPUR ZONE-II Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1590/BD-I | 28/02/2023 | 10 | TECHVISION | 2.6 | 2.6 | 99.99 | 0
4659 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. , SM/14427 | Augmentation | Material Requisition To Resource Division | 196/BD-I/25 | 09/02/2024 | 0 | Resource Division | 48.51 | 0 | 0 | 0
4660 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. , SM/14427 | Augmentation | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of KASHIPUR ZONE-II" ground water supply scheme in BELDANGA-II Block, under Berhampore Division-I, P.H.E Dte(Capacity-48.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Up flow Polishing | 1038/BD-I | 28/06/2024 | 365 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 156.07 | 0 | 0 | 60
4661 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. , SM/14427 | Augmentation | KASHIPUR ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1117/BD-I | 11/07/2024 | 180 | HI-TECH ENGINEERS CO-OPERATIVE & CONSTRUCTION SOCIETY LTD. | 20.67 | 0 | 0 | 100
4662 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. , SM/14427 | Augmentation | Allied Work for Road Restoration, Laying of Balance portion of UPVC and Rising Mains at Kashipur Zone-II PWSS under Jal Jeevan Mission within Beldanga-II block under Berhampore Division-I, P.H.E. Dte. In the district of Murshidabad. | 777/BD-I | 22/05/2025 | 90 | MARUTI CONSTRUCTION & CO. | 64.87 | 0 | 0 | 0
4663 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. , SM/14427 | Augmentation | Construction of Boundary wall at 2nd Tube Well Site of KASHIPUR ZONE - II PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 667/BD-I | 29/04/2025 | 175 | DEBEN RAJAK | 10.18 | 0 | 0 | 100
4664 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. , SM/14427 | Augmentation | Augmentation of Kashipur zone_II Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE Dte. | 1599/BD-I | 28/02/2023 | 900 | MARUTI CONSTRUCTION & CO. | 150.14 | 122.97 | 81.93 | 95
4665 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. , SM/14427 | Augmentation | Repair And Renovation Works Of OHR (550 Cum) for Kasipur Zone-II water supply scheme of Beldanga-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 991/BD-I | 30/10/2023 | 361 | PRAVAT KUMAR GHOSH | 9.15 | 7.73 | 100 | 100
4666 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14428 | Augmentation | Material Requisition To Resource Division | 201/BD-1/18 | 10/02/2024 | 0 | Resource Division | 16.95 | 0 | 0 | 0
4667 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14428 | Augmentation | Material Requisition To Resource Division | 1510/BD-I/10 | 12/09/2024 | 0 | Resource Division | 2.19 | 0 | 0 | 0
4668 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14428 | Augmentation | Augmentation of Sitesnagar Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 1542/BD-I | 17/02/2023 | 988 | M/S JOGMAYA ENTERPRISE | 87.18 | 54.67 | 63.17 | 30
4669 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14428 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SITESNAGAR Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1682/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.53 | 2.53 | 100 | 1
4670 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14428 | Augmentation | Repair And Renovation Works Of OHR (204 Cum) of Ground Water Based Supply Scheme for Sitesnagar of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 998/BD-I | 30/10/2023 | 506 | M/S SAJAL KUMAR NATH AND CO. | 7.99 | 0 | 0 | 100
4671 | MURSHIDABAD | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. , SM/14428 | Augmentation | Balance and allied Work Laying Rising Main with DI (K-9) and distribution system with UPVC pipe including supply of necessary special for augmentation work of Siteshnagar Water Supply Scheme , under Jal Jevan Mission under Berhampore Division -I , PHE.Dte. of LALGOLA Block of Murshidabad District. | 09/BD-I | 06/01/2025 | 179 | M/S. JOGMAYA ENTERPRISE | 23.22 | 0 | 0 | 30
4672 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KISHOREPUR PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13993 | Augmentation | Material Requisition To Resource Division | 1230/MURD/07 | 04/05/2023 | 0 | Resource Division | 25.86 | 0 | 0 | 0
4673 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KISHOREPUR PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13993 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 2.46 | 100 | 100
4674 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KISHOREPUR PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13993 | Augmentation | Augmentation of KISHOREPUR(PART-A) Pipe water supply scheme, to accommodate FHTC under Jal Jeevan Mission under Jangipur Sub Division Block- SUTI-II, of Murshidabad Division,District-Murshidabad PHE.Dte. | 980/MURD | 10/04/2023 | 1032 | A ONE CONSTRUCTION | 203.06 | 51.89 | 25.55 | 50
4675 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KISHOREPUR PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/13993 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGUMENTATION in connection to Accommodate FHTC at Pump House No.-I & II under KISHOREPUR ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | 1903/MEDB | 16/06/2023 | 930 | DAS CONSTRUCTION | 21.27 | 0 | 0 | 10
4676 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. , SM/13824 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 12.3 | 100 | 1
4677 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. , SM/13824 | Augmentation | Formal work order for the Work of Augmentation of JITPUR ZONE-I & its adjoining mouzas Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE.Dte. | 124/MURD | 16/01/2023 | 180 | M/S. S. DAS AND ENTERPRISE | 488.01 | 184.14 | 37.73 | 15
4678 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. , SM/13824 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under JITPUR ground water based water supply scheme under Block_ DOMKAL Dist. - Murshidabad under MEDB, PHE Dte. | 3760/MEDB | 03/11/2023 | 92 | JAGANNATH ENTERPRISE | 23.28 | 0 | 0 | 0
4679 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. , SM/13824 | Augmentation | Material Requisition To Resource Division | 1210/MURD/10 | 02/05/2023 | 0 | Resource Division | 2.76 | 0 | 0 | 0
4680 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. , SM/13824 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 2.62 | 100 | 80
4681 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. , SM/13824 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JITPUR (ZONE I) Water Supply Scheme at Head Work Site, 2nd Site site at DOMKAL Block under Murshidabad Division, P.H. Engineering Dte | 1748/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 23.58 | 20.18 | 100 | 100
4682 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-I) OF DOMKAL Block UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. , SM/13824 | Augmentation | Material Requisition To Resource Division | 526/MURD/01 | 19/02/2024 | 0 | Resource Division | 9.83 | 0 | 0 | 0
4683 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. , SM/13825 | Augmentation | Material Requisition To Resource Division | 1180/MURD/20 | 30/04/2023 | 0 | Resource Division | 30.1 | 0 | 0 | 0
4684 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. , SM/13825 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II,III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at JITPUR (ZONE II) Water Supply Scheme at Head Work Site, 2nd & 3rd Site site at DOMKAL Block under Murshidabad Division, P.H. Engineering Dte | 1747/MURD | 06/07/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 31.12 | 100 | 100
4685 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. , SM/13825 | Augmentation | Material Requisition To Resource Division | 526/MURD/02 | 19/02/2024 | 0 | Resource Division | 6.83 | 0 | 0 | 0
4686 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. , SM/13825 | Augmentation | Jitpur Zone-2 PH-1 Application No- 3004547411 | 279/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 10.38 | 0 | 0 | 0
4687 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. , SM/13825 | Augmentation | Jitpur Zone-2 PH-2 Application No-3004547163 | 278/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 4.89 | 0 | 0 | 0
4688 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. , SM/13825 | Augmentation | NEW CONNECTION AT JITPUR Z-II PH-III |  | 13/11/2024 | 0 | WBSEDCL | 6.3 | 0 | 0 | 0
4689 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF JITPUR PIPED WATER SUPPLY SCHEME (ZONE-II) OF DOMKAL BLOCK UNDER MURSHIDABAD DIVISION , PHE Dte. UNDER MURSHIDABAD DISTRICT. , SM/13825 | Augmentation | Formal work order for Augmentation of JITPUR (Zone-II) Ground water based Piped water supply scheme to accommodate FHTC (Functional Household Tap Connection) within Domkal Block of Murshidabad District under Murshidabad Division, PHE. Dte. | 603/MURD | 02/03/2023 | 1036 | M/S.TAPAS KUMAR CHAKRABORTY | 752.45 | 520.72 | 69.2 | 40
4690 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- I Block - Khargram , Dist- Murshidabad. , SM/14630 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 5.33 | 100 | 76
4691 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- I Block - Khargram , Dist- Murshidabad. , SM/14630 | Augmentation | Material Requisition To Resource Division | 1004/MURD/9 | 11/04/2023 | 0 | Resource Division | 2.38 | 0 | 0 | 0
4692 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- I Block - Khargram , Dist- Murshidabad. , SM/14630 | Augmentation | Material Requisition To Resource Division | 1043/MURD/1 | 17/04/2023 | 0 | Resource Division | 2.38 | 0 | 0 | 0
4693 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- I Block - Khargram , Dist- Murshidabad. , SM/14630 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under BHALKUNDI ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | 4299/MEDB | 29/12/2023 | 91 | A.K. SIKDAR | 24.12 | 0 | 0 | 0
4694 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- I Block - Khargram , Dist- Murshidabad. , SM/14630 | Augmentation | Laying Distribution System, Rising Main, FHTC, Repairing of Boundary Wall, Pump House & Existing OHR for Augmentation of Bhalkundi Zone-I Water at Supply Scheme in Khargram Block , under Murshidabad Division ,PHE.Dte. | 994/MURD | 11/04/2023 | 720 | SUJIT KUMAR SAHA | 222.84 | 125.21 | 56.19 | 60
4695 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- I Block - Khargram , Dist- Murshidabad. , SM/14630 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 0 | 75
4696 | MURSHIDABAD | Murshidabad Division | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhalkundi Zone- I Block - Khargram , Dist- Murshidabad. , SM/14630 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well, 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahalandi Zone - I , Mahalandi Zone - II & Bhalkundi Zone - I Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte | 1758/MURD | 06/07/2023 | 576 | R.K. DRILLING SERVICES | 23.58 | 0 | 0 | 70
4697 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAIA ZONE-I , SM/15230 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-I under MAIA ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | 4337/MEDB | 29/12/2023 | 183 | SUNIL RABIDAS | 23.45 | 15.05 | 64.15 | 10
4698 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAIA ZONE-I , SM/15230 | Augmentation | Material Requisition To Resource Division | 201/BD-1/20 | 10/02/2024 | 0 | Resource Division | 34.89 | 0 | 0 | 0
4699 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAIA ZONE-I , SM/15230 | Augmentation | Material Requisition To Resource Division | 1510/BD-I/9 | 12/09/2024 | 0 | Resource Division | 6.73 | 0 | 0 | 0
4700 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAIA ZONE-I , SM/15230 | Augmentation | Augmentation of Maia Zone-I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 511/BD-I | 25/07/2023 | 900 | SOM CONSTRUCTION AGENCY | 208.44 | 19.28 | 9.25 | 20
4701 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAIA ZONE-I , SM/15230 | Augmentation | Balance i.c.w Improvement of Existing AIRP (Modified Sujapur Sadipur Model) capacity 130.00 cum/hr at Head Work Site of Maia Zone-I Water Supply Scheme under JJM within Lalgola under Berhampore Division -I, P.H.E. Dte. In the district of Murshidabad. | 778/BD-I | 22/05/2025 | 30 | M/S J.S ENTERPRISE | 30.11 | 0 | 0 | 0
4702 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAIA ZONE-I , SM/15230 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Maia ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | 1676/BD-I | 14/03/2023 | 30 | RAJIB SAHA | 3.62 | 2.38 | 100 | 80
4703 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAIA ZONE-I , SM/15230 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MAIA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1688/BD-I | 14/03/2023 | 10 | ENVIROTECH SOLUTIONS | 2.87 | 2.69 | 100 | 1
4704 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR MAIA ZONE-I , SM/15230 | Augmentation | Repair And Renovation Works Of OHR (550 Cum) of Ground water based supply scheme for Maia Zone-I of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | 993/BD-I | 30/10/2023 | 30 | ZEST INFRACON | 9.93 | 2.09 | 20.94 | 90
4705 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. , SM/15232 | Augmentation | Augmentation of Bansgara Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | 621/BD-I | 03/08/2023 | 310 | BURIMA CONSTRUCTION | 367.54 | 0 | 0 | 0
4706 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. , SM/15232 | Augmentation | BANSGARA ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 453/BD-I | 15/03/2024 | 60 | KAUSHIK MAJUMDAR | 21.78 | 0 | 0 | 0
4707 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. , SM/15232 | Augmentation | Material Requisition To Resource Division | 201/BD-1/24 | 10/02/2024 | 0 | Resource Division | 13.68 | 0 | 0 | 0
4708 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. , SM/15232 | Augmentation | Construction of Pump House Cum Chlorine Room at Head Work Site of BANSGARA ZONE - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 613/BD-I | 22/04/2025 | 45 | BIJOY SINGHA | 8.81 | 0 | 0 | 0
4709 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. , SM/15232 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd TW Site of BANSGARA ZONE - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 626/BD-I | 24/04/2025 | 60 | SUSHANTA MANDAL | 18.91 | 0 | 0 | 0
4710 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. , SM/15232 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BANSGARA-II PWSS(TW-I&II) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (2 Nos TW) | 432/BD-I | 19/03/2025 | 30 | SARKAR WATER SUPPLY AGENCY | 18 | 0 | 0 | 0
4711 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. , SM/15232 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad under MEDB, PHE Dte. | 323/MEDB | 10/02/2025 | 89 | ARINDAM MAJUMDAR | 24.68 | 0 | 0 | 0
4712 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bansgara Zone- II Block - Lalgola, Dist- Murshidabad. , SM/15232 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BANSGARA Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 58/BD-I | 25/04/2023 | 10 | ENVIROTECH SOLUTIONS | 2.6 | 2.6 | 100 | 100
4713 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14921 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for ANDULBERIA Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1648/BD-I | 10/03/2023 | 10 | TECHVISION | 2.81 | 2.8 | 100 | 100
4714 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14921 | Augmentation | Allied works of Laying of distribution pipeline of ANDULBERIA ZONE-I piped water supply scheme under JJM within Beldanga-II Block in the district of Murshidabad under Berhampore Division-I, PHE Dte. | 1477/BD-I | 06/09/2024 | 60 | SUSHANTA MANDAL | 45.66 | 0 | 0 | 0
4715 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14921 | Augmentation | Material Requisition To Resource Division | 196/BD-I/23 | 09/02/2024 | 0 | Resource Division | 64.29 | 0 | 0 | 0
4716 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14921 | Augmentation | Augmentation of Andulberia Zone_I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE Dte. | 1661/BD-I | 13/03/2023 | 720 | M/S BIMALENDU BOSE | 433.78 | 433.17 | 99.86 | 100
4717 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14921 | Augmentation | Construction of Boundary wall at 2nd & 3rd Tube Well Site of ANDULBERIYA ZONE -I PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 600/BD-I | 22/04/2025 | 60 | AICH CONSTRUCTION | 20.36 | 0 | 0 | 0
4718 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14921 | Augmentation | Repair And Renovation Works Of R.C.C Elevated Reservoir (700 Cum) for Andulberia Zone-I water supply scheme of Beldanga-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal Jeevan Mission. | 18/BD-I | 04/01/2024 | 328 | A.S CONSTRUCTION | 11.02 | 0 | 0 | 100
4719 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14921 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at ANDULBERIA ZONE-I Water Supply Scheme(TW-II) within Beldanga-II Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 12/BD-I | 06/01/2025 | 195 | MAMATA USHA ENTERPRISE | 9.01 | 0 | 0 | 100
4720 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14921 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 139 Cum/hr.) with allied work at Andulberia Zone-I Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | 916/BD-I | 07/06/2024 | 150 | M/S GOUTAM CHAKRABORTY | 47.44 | 12.56 | 20.94 | 100
4721 | MURSHIDABAD | Berhampore Division I | AUGMENTATION OF ANDULBERIA ZONE-I PIPED WATER SUPPLY SCHEME. , SM/14921 | Augmentation | Balance work for Improvement of Existing AIRP of (Capacity 139 Cum/hr,with allied work at Andulberia Zone-IWater Supply Scheme under Jal Jeevan Mission within Beldanga - II under Berhampore Division-I,P.H.Engineering Dte. In the district of Murshidabad. | 763/BD-I | 22/05/2025 | 30 | M/S GOUTAM CHAKRABORTY | 11.84 | 0 | 0 | 100
4722 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Bachhara Ground water Based PWSS, Block-Beldanga-II , Dist- Murshidabad under MEDB, PHE Dte. , SM/15295 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Bachhara Ground water Based PWSS, Block-Beldanga-II , Dist- Murshidabad under MEDB, PHE Dte. | 3738/MEDB | 03/11/2023 | 790 | M/S SAJAHAN CHOWDHURY | 6.38 | 0 | 0 | 50
4723 | MURSHIDABAD | Murshidabad Division | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS , SM/14497 | New | Material Requisition To Resource Division | 1067/MURD/5 | 18/04/2023 | 0 | Resource Division | 25.69 | 0 | 0 | 0
4724 | MURSHIDABAD | Murshidabad Division | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS , SM/14497 | New | Formal work order for the work of EKPAHARIA( Part-B) & adjoining moujas PWSS to accommodate Construction Tube Well, Pump House Cum Chlorine Room & Blower room and Laying Distribution System under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE.Dte. | 105/MURD | 13/01/2023 | 180 | MOTI RAHAMAN | 203.57 | 137.51 | 67.55 | 45
4725 | MURSHIDABAD | Berhampore Mechanical | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS , SM/14497 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under EKPAHARIA ground water based water supply scheme under Block_ Burwan, Dist. - Murshidabad under MEDB, PHE Dte. | 4062/MEDB | 04/12/2023 | 91 | PADMA ENGINEERING CO | 24.19 | 0 | 0 | 30
4726 | MURSHIDABAD | Berhampore Mechanical | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS , SM/14497 | New | NEW SERVICE CONNECTION AT PWSS PH1 EKPAHARIA ID 304248191 | 320/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 5.56 | 0 | 0 | 0
4727 | MURSHIDABAD | Berhampore Mechanical | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS , SM/14497 | New | ADDITIONAL QUOTATION AGAINST PHE EKPAHARIA WS SCHEME PH 1 ID 860313275 |  | 25/11/2024 | 0 | WBSEDCL | 0.82 | 0 | 0 | 0
4728 | MURSHIDABAD | Berhampore Mechanical | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS , SM/14497 | New | NEW SERVICE CONNECTION AT PWSS PH 2 EKPAHARIA ID 304247011 | 319/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 6.8 | 0 | 0 | 0
4729 | MURSHIDABAD | Murshidabad Division | EKPAHARIA AND IT'S ADJOINING MOUJAS PWSS , SM/14497 | New | Formal work order for the work of EKPAHARIA (Part-A) & adjoining moujas PWSS to accommodate FHTC, Construction Tube Well, OHR, Pump House Cum Chlorine Room , Rising Main, boundary wall and service road, under Jal Jevan Mission of Murshidabad District under Murshidabad Division, PHE. Dte. | 104/MURD | 13/01/2023 | 1084 | DOBAY CONSTRUCTION | 422.08 | 137.46 | 32.57 | 18
4730 | MURSHIDABAD | Murshidabad Division | KAPASDANGA & ADJOINING MOUJAS PWSS , SM/15054 | New | Material Requisition To Resource Division | 1936/MURD/5 | 18/07/2023 | 0 | Resource Division | 17.68 | 0 | 0 | 0
4731 | MURSHIDABAD | Berhampore Mechanical | KAPASDANGA & ADJOINING MOUJAS PWSS , SM/15054 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under KAPASDANGA ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | 2088/MEDB | 19/06/2023 | 793 | M/S S. S. ENTERPRISE (DOMKAL) | 21.56 | 0 | 0 | 40
4732 | MURSHIDABAD | Berhampore Mechanical | KAPASDANGA & ADJOINING MOUJAS PWSS , SM/15054 | New | NEW SERVICE CONNECTION AT PH1 KAPASDANGA ID 304239449 | 307/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 3.18 | 0 | 0 | 0
4733 | MURSHIDABAD | Murshidabad Division | KAPASDANGA & ADJOINING MOUJAS PWSS , SM/15054 | New | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kapasdanga & adjoining mouzas Water Supply Scheme at Head Work Site & 2nd Site at B u r w a n Block under Murshidabad Division, P.H. Engineering Dte. | 1103/MURD | 24/04/2023 | 30 | MAMATA USHA ENTERPRISE | 21.38 | 11.06 | 51.73 | 65
4734 | MURSHIDABAD | Murshidabad Division | KAPASDANGA & ADJOINING MOUJAS PWSS , SM/15054 | New | Laying Distribution System Part-A, Rising Main, Construction of 200 Cum OHR, Boundwary Wall, Pump House, for Kapasdanga water supply scheme of Burwan Block under Murshidabad Division, PHE Dte. PART_A | 993/MURD | 11/04/2023 | 996 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 189.09 | 77.45 | 40.96 | 70
4735 | MURSHIDABAD | Murshidabad Division | KAPASDANGA & ADJOINING MOUJAS PWSS , SM/15054 | New | Sinking of 05 (Five) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Satitara T.W- IV,V,VI, Fatepur T.W.-II, Kapasdanga T.W-II Water Supply Scheme of Burwan Block under Kandi Sub- Division, Murshidabad Division, P.H.Engineering Dte. | 664/MURD | 19/03/2025 | 65 | NADIA TUBEWELLS | 70.43 | 0 | 0 | 0
4736 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- II . , SM/14737 | Augmentation | Material Requisition To Resource Division | 61/BD-1/23 | 27/04/2023 | 0 | Resource Division | 24.65 | 0 | 0 | 0
4737 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- II . , SM/14737 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Lochanpur Zone-II ground water supply scheme in Raninagar-I Block Dist_Murshidabad under MEDB PHE Dte. | 1132/MEDB | 13/05/2025 | 92 | CHOWDHURY & BASU ENTERPRISE | 39.61 | 0 | 0 | 0
4738 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- II . , SM/14737 | Augmentation | Augmentation of Lochanpur Zone-II Piped water supply scheme to accommodate construction of OHR, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | 679/BD-I | 10/08/2023 | 964 | APU CONSTRUCTION | 273.83 | 136.47 | 49.84 | 5
4739 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- II . , SM/14737 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Lochanpur Zone-II ground water supply scheme in Raninagar-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | 508/BD-I | 03/04/2025 | 300 | NATIONAL CONSTRUCTION | 122.74 | 0 | 0 | 0
4740 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- II . , SM/14737 | Augmentation | Construction Service Road for approach and Pump House at Augmentation of LOCHANPUR ZONE-II PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | 786/BD-I | 26/05/2025 | 60 | BHOLEBABA CONSTRUCTION CO | 7.34 | 0 | 0 | 0
4741 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- II . , SM/14737 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for LOCHANPUR ZONE-II Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | 1757/BD-I | 24/03/2023 | 10 | M/S SOBHA & CO | 2.6 | 2.6 | 100 | 100
4742 | MURSHIDABAD | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Lochanpur Zone- II . , SM/14737 | Augmentation | LOCHANPUR ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1064/BD-I | 03/07/2024 | 300 | APU CONSTRUCTION | 21.05 | 0 | 0 | 100
4743 | MURSHIDABAD | Murshidabad Division | Augmentation of Jagtai Piped Water Supply Scheme Block - Suti-II District - Murshidabad. , SM/14943 | Augmentation | Repair of Pump Houses , Construction of toilet , Reinforced Barbed Tape (R.B.T) Concertina fencing on Boundary wall top & approach road for JAGTAI Water Supply Scheme under Jangipur Sub Division,P.H.E. Dte.in the District Murshidabad. | 3167/MURD | 30/11/2022 | 30 | M/S JOY MA BANAMALI | 7.11 | 7 | 98.53 | 0
4744 | MURSHIDABAD | Murshidabad Division | Augmentation of Jagtai Piped Water Supply Scheme Block - Suti-II District - Murshidabad. , SM/14943 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 7.22 | 100 | 100
4745 | MURSHIDABAD | Murshidabad Division | Augmentation of Jagtai Piped Water Supply Scheme Block - Suti-II District - Murshidabad. , SM/14943 | Augmentation | Material Requisition To Resource Division | 1219/MURD/29 | 03/05/2023 | 0 | Resource Division | 18.03 | 0 | 0 | 0
4746 | MURSHIDABAD | Murshidabad Division | Augmentation of Jagtai Piped Water Supply Scheme Block - Suti-II District - Murshidabad. , SM/14943 | Augmentation | Material Requisition To Resource Division | MURD/2991 | 13/11/2024 | 0 | Resource Division | 25.25 | 0 | 0 | 0
4747 | MURSHIDABAD | Murshidabad Division | Augmentation of Jagtai Piped Water Supply Scheme Block - Suti-II District - Murshidabad. , SM/14943 | Augmentation | Augmentation Work of Jagtai Piped Water Supply Scheme to accommodate with FHTC (1730 Nos), Laying of Rising Main , Laying of Distribution System , construction of 200 CUM OHR, Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE. Dte. | 2670/MURD | 24/08/2023 | 730 | GREENLEAF CONSTRUCTION | 336.47 | 17.72 | 5.27 | 40
4748 | MURSHIDABAD | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/14944 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 7.36 | 100 | 100
4749 | MURSHIDABAD | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/14944 | Augmentation | Material Requisition To Resource Division | 1167/MURD/47 | 28/04/2023 | 0 | Resource Division | 11.06 | 0 | 0 | 0
4750 | MURSHIDABAD | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/14944 | Augmentation | Material Requisition To Resource Division | 1210/MURD/23 | 02/05/2023 | 0 | Resource Division | 4.02 | 0 | 0 | 0
4751 | MURSHIDABAD | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/14944 | Augmentation | Providing FHTC Connection to 650 nos household , Repairing & Vertical Extention of Boundary Wall ,Construction of 1 (one) no Toilet Block with sanitary and Water Supply Arrangement & Pump House repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity of staging height 20 mtr. (Shaft wall ) for Augmentation work of Basudebpur (Zone-I) PWSS in Samsherganj Block under Murshidabad Division ,PHE.Dte. | 541/MURD | 24/02/2023 | 1110 | MOLLA ENTERPRISE | 49.98 | 14.23 | 28.46 | 25
4752 | MURSHIDABAD | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/14944 | Augmentation | Laying of Distribution System for Augmentation work of Basudebpur(Zone-I) PWSS in Samsherganj Block under Murshidabad Division ,PHE.Dte. | 902/MURD | 29/03/2023 | 1080 | JAI BHARAT COMMERCIAL CORPORATION | 112.15 | 41.15 | 36.69 | 40
4753 | MURSHIDABAD | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/14944 | Augmentation | Balance work of Laying of UPVC Pipe , Construction of approach road , Modification of R.C.C. Elevated Reservoir and Pump House, Boundary wall, for Augmentation of Basudevpur (Zone-I) Water Supply Scheme in Suti-I Block of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | 191/MURD | 21/01/2025 | 223 | MOLLA ENTERPRISE | 40.58 | 0 | 0 | 35
4754 | MURSHIDABAD | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/14944 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for BASUDEBPUR Zone ¿I Ground Based Water Supply Scheme in Samserganj Block under Murshidabad Division, PHE Dte. | 986/MURD | 02/05/2025 | 60 | J.S. CONSTRUCTION | 23.01 | 0 | 0 | 0
4755 | MURSHIDABAD | Murshidabad Division | Augmentation of Basudevpur Zone-I Piped Water Supply Scheme Block - Samserganj District - Murshidabad. , SM/14944 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Basudevpur Halt Station to Dhulianganga Station (TP NO 235/2 & 235/3) at Basudevpur mouza & Connecting with existing 110 mm dia uPVC distribution main line of Basudevpur ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | 2483/MURD | 16/08/2021 | 60 | SANJAY BISWAS | 22.75 | 14.61 | 100 | 100
4756 | MURSHIDABAD | Murshidabad Division | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/15066 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Jalangi & Raninagar-I Block of ISLAMPUR SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Narsinghpur Water Supply Scheme , Tekaraipara Water Supply Scheme, Natial Rajanagar Water Supply Scheme. | 2913/MURD | 01/11/2022 | 30 | STEELCONC AND ASSOCIATES | 16.51 | 5.23 | 100 | 1
4757 | MURSHIDABAD | Murshidabad Division | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/15066 | Augmentation | Material Requisition To Resource Division | 1219/MURD/23 | 03/05/2023 | 0 | Resource Division | 16.53 | 0 | 0 | 0
4758 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/15066 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under Narsinghpur ground water based water supply scheme under Block_ Jalangi Dist. - Murshidabad under MEDB, PHE Dte. | 584/MEDB | 31/01/2024 | 517 | QUAZI NOZRUL ISLAM (PARTNERSHIP) | 20.81 | 0 | 0 | 70
4759 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/15066 | Augmentation | NEW SERVICE CONNECTION AT NARASINGHAPUR PWSS Z2 JL NO14 PLOT NO 970,1030,974 ID 304238697 | 294/WBSEDCL-JJM | 01/02/2024 | 0 | WBSEDCL | 4.17 | 0 | 0 | 0
4760 | MURSHIDABAD | Murshidabad Division | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/15066 | Augmentation | SUBMISSION OF ONE NO REPAIRING ESTIMATE OF ROAD WHICH IS DAMAGED DURING PHE PIPE LINE LAYING IE. | 282-MSD/2024-25 | 13/08/2024 | 0 | EXECUTIVE ENGINER WBSRDA MURSHIDABAD DIVISION | 20.84 | 0 | 0 | 0
4761 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/15066 | Augmentation | AT NARASINGHAPUR PWSS Z2 PH 1 ID 304238696 | 448/WBSEDCL-JJM | 15/03/2024 | 0 | WBSEDCL | 9.32 | 0 | 0 | 0
4762 | MURSHIDABAD | Murshidabad Division | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/15066 | Augmentation | Augmentation of Ground Water Based Narsinghpur Zone-II PWS accommodate FHTC, Laying Distribution System, Laying Rising Main in Jalangi Block within Murshidabad District under Murshidabad Division, PHE Dte. PART_A | 2617/MURD | 22/08/2023 | 793 | RAJKUMAR MONDAL | 202.06 | 122.14 | 60.45 | 55
4763 | MURSHIDABAD | Murshidabad Division | Augmentation of Narsinghpur Zone-II Pipe Water Supply Scheme Block - Jalangi District - Murshidabad. , SM/15066 | Augmentation | Construction of 300 Cum OHR, Pump House at Head Work Site & 2nd Tube well site , Boundary wall for Augmentation of NARASINGHAPUR Zone-II PWSS in Jalangi Block , Islampur Sub-Division under Murshidabad Division ,PHE.Dte.PART_B | 3333/MURD | 23/10/2023 | 555 | GOUTAM MANDAL | 142.16 | 78.89 | 55.49 | 40
4764 | MURSHIDABAD | Murshidabad Division | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15070 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 1.15 | 12.41 | 1
4765 | MURSHIDABAD | Murshidabad Division | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15070 | Augmentation | Material Requisition To Resource Division | 1180/MURD/07 | 29/04/2023 | 0 | Resource Division | 134.73 | 0 | 0 | 0
4766 | MURSHIDABAD | Murshidabad Division | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15070 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Juranpur ( PART-A) Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | 1764/MURD | 06/07/2023 | 1045 | NADIA TUBEWELLS | 35.34 | 15.89 | 44.92 | 90
4767 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15070 | Augmentation | Juranpur PH No-V | 341/WBSEDCL-JJM | 12/02/2024 | 0 | WBSEDCL | 4.44 | 0 | 0 | 0
4768 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15070 | Augmentation | Juranpur PH No-IV | 340/WBSEDCL-JJM | 15/02/2024 | 0 | WBSEDCL | 8.13 | 0 | 0 | 0
4769 | MURSHIDABAD | Murshidabad Division | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15070 | Augmentation | Augmentation of JURANPUR (PART-A) PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Sub Division , Murshidabad District under Murshidabad Division, PHE. Dte. | 1384/MURD | 22/05/2023 | 1147 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 456.53 | 361.23 | 79.12 | 20
4770 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Juranpur Piped Water Supply Scheme PART-A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15070 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under JURANPUR ,PART-A ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | 4312/MEDB | 29/12/2023 | 91 | DAS CONSTRUCTION | 22.6 | 18.18 | 80.46 | 10
4771 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-B) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. , SM/15837 | Augmentation | Material Requisition To Resource Division | 526/MURD/04 | 19/02/2024 | 0 | Resource Division | 3.66 | 0 | 0 | 0
4772 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF P.T RASULPUR PIPED WATER SUPPLY SCHEME (PART-B) OF DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE Dte. , SM/15837 | Augmentation | Formal work order for Augmentation of P T Rasulpur (Part - B) Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE.Dte. | 608/MURD | 02/03/2023 | 975 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 363.24 | 181.78 | 50.04 | 20
4773 | MURSHIDABAD | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15838 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 10.28 | 100 | 1
4774 | MURSHIDABAD | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15838 | Augmentation | Material Requisition To Resource Division | 1210/MURD/11 | 02/05/2023 | 0 | Resource Division | 147.5 | 0 | 0 | 0
4775 | MURSHIDABAD | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15838 | Augmentation | Formal work order for Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part- A under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE Dte. | 622/MURD | 03/03/2023 | 180 | M/S. S. DAS AND ENTERPRISE | 508 | 351.34 | 69.16 | 20
4776 | MURSHIDABAD | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15838 | Augmentation | Sinking of 02 (Two) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shibnagar Laskarpur (Zone - I ) Part - A Water Supply Scheme at Head Work Site, 2nd Site site at Domkal Block under Murshidabad Division, P.H. Engineering Dte | 1761/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 23.58 | 20.58 | 100 | 50
4777 | MURSHIDABAD | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-I) Part -A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15838 | Augmentation | Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Sultanpur (Village code 314726) under Shibnagar Laskarpur Ground Water Based Water Supply Scheme for Arsenic Affected Area of Domkol Block, under Murshidabad Division, PHE Dte. Scheme ID - 0001723328 in the District of Murshidabad. | 85/MURD | 08/01/2021 | 60 | DECON INDIA | 33.63 | 5.8 | 17.25 | 1
4778 | MURSHIDABAD | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16267 | New | Material Requisition To Resource Division | 61/BD-1/4 | 27/04/2023 | 0 | Resource Division | 9.47 | 0 | 0 | 0
4779 | MURSHIDABAD | Berhampore Mechanical | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16267 | New | NEW CONNECTION AT PURBA KASHIPUR PH-I | 104/WBSEDCL-JJM | 05/06/2024 | 0 | WBSEDCL | 5.84 | 0 | 0 | 0
4780 | MURSHIDABAD | Berhampore Mechanical | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16267 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Purba Kasipur and adjoining mouzas piped Water Supply Scheme Dist- Murshidabad under MEDB, PHE Dte. | 1145/MEDB | 14/05/2025 | 92 | MONI ELECTRICAL WORKS | 22.95 | 0 | 0 | 0
4781 | MURSHIDABAD | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16267 | New | PURBA KASHIPUR PWSS to accommodate FHTC, Laying Distribution System under Jal Jeevan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. (PART - B) | 1823/BD-I | 31/03/2023 | 180 | MARUTI CONSTRUCTION & CO. | 112.84 | 49.88 | 44.21 | 85
4782 | MURSHIDABAD | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16267 | New | PURBA KASIPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Bhagwangola-I Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 210/BD-I | 17/05/2023 | 905 | MARUTI CONSTRUCTION & CO. | 53.43 | 0 | 0 | 70
4783 | MURSHIDABAD | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16267 | New | PURBA KASHIPUR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of BHAGWANGOLA - I Block, Murshidabad District under Berhampore Division-I, PHE Dte. (PART - A) | 407/BD-I | 06/07/2023 | 1000 | SANKAR KUMAR BISWAS | 290.34 | 105.33 | 36.28 | 40
4784 | MURSHIDABAD | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16267 | New | Balance work of distribution pipe line under Jal Jeevan Mission for Purba Kashipur Piped Water Supply scheme under Berhampore Division - I , P.H.Engg Dte. In the district of Murshidabad. | 1207/BD-I | 26/07/2024 | 60 | MARUTI CONSTRUCTION & CO. | 42.9 | 0 | 0 | 85
4785 | MURSHIDABAD | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16267 | New | Construction Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of PURBA KASHIPUR PWSS under Jal Jeevan Mission within Bhagwangola-I Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | 625/BD-I | 24/04/2025 | 60 | SHIV SHAKTI CONSTRUCTION | 18.82 | 0 | 0 | 80
4786 | MURSHIDABAD | Berhampore Division I | PURBA KASIPUR AND ADJOINING MOUJAS Piped Water Supply Scheme , SM/16267 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PURBA KASHIPUR Water Supply Scheme(2nd TW site) within Bhagwangola-I Block under JJM in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. | 102/BD-I | 20/01/2025 | 181 | HARUN ALL RASHID & BROTHERS | 8.93 | 0 | 0 | 100
4787 | MURSHIDABAD | Berhampore Mechanical | Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Jotkamal Zone - II Ground water Based PWSS, Block-Raghunathganj-II , Dist- Murshidabad under MEDB, PHE Dte. , SM/15348 | Solarisation | Name of Work: Providing Solarization of WBSEDCL Energised Pumping installation with net metering at Jotkamal Zone - II Ground water Based PWSS, Block-Raghunathganj-II , Dist- Murshidabad under MEDB, PHE Dte. | 3751/MEDB | 03/11/2023 | 92 | SURAKSHA | 6.39 | 0 | 0 | 0
4788 | MURSHIDABAD | Berhampore Mechanical | GAYSEPUR PIPED WATER SUPPLY SCHEME , SM/16018 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under Gaysepur ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | 3661/MEDB | 03/11/2023 | 92 | DAS ENTERPRISE ( MANGO LANE) | 20.87 | 0 | 0 | 0
4789 | MURSHIDABAD | Berhampore Division I | GAYSEPUR PIPED WATER SUPPLY SCHEME , SM/16018 | New | Material Requisition To Resource Division | 61/BD-1/15 | 27/04/2023 | 0 | Resource Division | 6.62 | 0 | 0 | 0
4790 | MURSHIDABAD | Berhampore Division I | GAYSEPUR PIPED WATER SUPPLY SCHEME , SM/16018 | New | Material Requisition To Resource Division | 304/BD-1/7 | 22/02/2024 | 0 | Resource Division | 3.02 | 0 | 0 | 0
4791 | MURSHIDABAD | Berhampore Division I | GAYSEPUR PIPED WATER SUPPLY SCHEME , SM/16018 | New | GAYESPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising main under Jal Jeevan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 144/BD-I | 15/05/2023 | 809 | SAPTADIP CONSTRUCTION | 58.85 | 0 | 0 | 30
4792 | MURSHIDABAD | Berhampore Division I | GAYSEPUR PIPED WATER SUPPLY SCHEME , SM/16018 | New | GAYESPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 1257/BD-I | 22/12/2023 | 544 | M/S HUMAYUN BISWAS | 39.06 | 0 | 0 | 60
4793 | MURSHIDABAD | Berhampore Division I | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE CHAK CHANDPARA , BLOCK- BERHAMPORE, DISTRICT MURSHIDABAD. , SM/16440 | New | Mini Piped Water Supply Scheme for Chak Chandpara under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 181/BD-I | 17/05/2023 | 90 | ADITYA ENTERPRISE | 29.09 | 0 | 0 | 0
4794 | MURSHIDABAD | Berhampore Mechanical | MINI PIPED WATER SUPPLY SCHEME (MAXIMUM 100 HOUSE HOLDS ) VILLAGE CHAK CHANDPARA , BLOCK- BERHAMPORE, DISTRICT MURSHIDABAD. , SM/16440 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Chak Chandpara village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3073/MEDB | 02/08/2023 | 92 | ARINDAM MAJUMDAR | 6.27 | 0 | 0 | 0
4795 | MURSHIDABAD | Murshidabad Division | Augmentation of Aurangabad Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. , SM/16547 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 3.75 | 100 | 100
4796 | MURSHIDABAD | Murshidabad Division | Augmentation of Aurangabad Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. , SM/16547 | Augmentation | Material Requisition To Resource Division | 1219/MURD/08 | 03/05/2023 | 0 | Resource Division | 47.69 | 0 | 0 | 0
4797 | MURSHIDABAD | Murshidabad Division | Augmentation of Aurangabad Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. , SM/16547 | Augmentation | Augmentation Work of Aurangabad Zone-II Piped Water Supply Scheme to accommodate with FHTC (586 Nos), Laying of Rising Main , Laying of Distribution System , construction of 600 CUM OHR, Construction of Switch Room, Boundary Wall under Jal Jeevan Mission of Jangipur Sub Division in the District Murshidabad District under Murshidabad Division, PHE. Dte. | 2668/MURD | 24/08/2023 | 365 | KUNDU CONSTRUCTION | 371.15 | 0 | 0 | 0
4798 | MURSHIDABAD | Murshidabad Division | Augmentation of Aurangabad Zone-II Pipe Water Supply Scheme Block - Suti -II District - Murshidabad. , SM/16547 | Augmentation | Hiring of Maxicab (Non-Air Condition, Bharat stage-III on or after 01/05/2008 with Diesel/L.P.G/CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the office of the Assistant Engineer, Jangipur Sub-Division, P.H.E Dte. [ Period for 06 (Six) Month].For the month of 17/01/2025 to 16/07/2025. [ Vehicle No:- WB 58 CD 3758] | 15/JSD | 17/01/2025 | 181 | HASSAN CONSTRUCTION | 0.88 | 0.59 | 66.77 | 0
4799 | MURSHIDABAD | Murshidabad Division | UTTAR MAHAMMADPUR PIPE WATER SUPPLY SCHEME. , SM/16550 | New | Material Requisition To Resource Division | 1230/MURD/27 | 04/05/2023 | 0 | Resource Division | 47.71 | 0 | 0 | 0
4800 | MURSHIDABAD | Berhampore Mechanical | UTTAR MAHAMMADPUR PIPE WATER SUPPLY SCHEME. , SM/16550 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I ,II & III under UTTAR MAHAMMADPUR ground water based water supply scheme under Block_ SAMSERGANJ Dist. - Murshidabad under MEDB, PHE Dte. | 1902/MEDB | 16/06/2023 | 92 | M/S. SUPER CONSTRUCTION | 34.05 | 13.72 | 40.3 | 10
4801 | MURSHIDABAD | Murshidabad Division | UTTAR MAHAMMADPUR PIPE WATER SUPPLY SCHEME. , SM/16550 | New | Formal work order for UTTAR MAHAMMADPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jivan Mission of SAMSERGANJ Block, Murshidabad District under Jangipur Sub Division Murshidabad Division, PHE.Dte. | 742/MURD | 16/03/2023 | 1021 | CREATIVE CONSTRUCTION | 413.33 | 0 | 0 | 20
4802 | MURSHIDABAD | Murshidabad Division | UTTAR MAHAMMADPUR PIPE WATER SUPPLY SCHEME. , SM/16550 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Mahadebnagar Zone- I A & Uttar Mahammadpur Water Supply Scheme at Head Work Site, 2nd Site under Murshidabad Division, P.H. Engineering Dte. | 1773/MURD | 06/07/2023 | 695 | HARUN ALL RASHID & BROTHERS | 18.4 | 0 | 0 | 80
4803 | MURSHIDABAD | Murshidabad Division | UTTAR MAHAMMADPUR PIPE WATER SUPPLY SCHEME. , SM/16550 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 6.13 | 100 | 100
4804 | MURSHIDABAD | Murshidabad Division | UTTAR MAHAMMADPUR PIPE WATER SUPPLY SCHEME. , SM/16550 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at UTTAR MAHAMMADPUR Water Supply Scheme at Head Work Site, 2nd Site site at Samserganj Block under Murshidabad Division, P.H. Engineering Dte. | 2632/MURD | 23/08/2023 | 587 | MAMATA USHA ENTERPRISE | 18.44 | 0 | 0 | 50
4805 | MURSHIDABAD | Murshidabad Division | LOKAIPUR PIPED WATER SUPPLY SCHEME. , SM/16552 | New | Material Requisition To Resource Division | 1230/MURD/26 | 04/05/2023 | 0 | Resource Division | 18.15 | 0 | 0 | 0
4806 | MURSHIDABAD | Murshidabad Division | LOKAIPUR PIPED WATER SUPPLY SCHEME. , SM/16552 | New | Formal Work Order for LOKAIPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Raghunathganj-II Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, PHE.Dte. | 694/MURD | 10/03/2023 | 365 | ROY CONSTRUCTION (PROP:AVIJIT ROY) | 239.71 | 108.71 | 45.35 | 30
4807 | MURSHIDABAD | Murshidabad Division | LOKAIPUR PIPED WATER SUPPLY SCHEME. , SM/16552 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at LOKAIPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti - II Block under Murshidabad Division, P.H. Engineering Dte. | 3388/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 14.75 | 100 | 80
4808 | MURSHIDABAD | Murshidabad Division | LOKAIPUR PIPED WATER SUPPLY SCHEME. , SM/16552 | New | Material Requisition To Resource Division | 495/MURD/07 | 15/02/2024 | 0 | Resource Division | 4.1 | 0 | 0 | 0
4809 | MURSHIDABAD | Berhampore Mechanical | LOKAIPUR PIPED WATER SUPPLY SCHEME. , SM/16552 | New | NEW CONNECTION LOKAIPUR PH-II |  | 27/03/2024 | 0 | WBSEDCL | 4.73 | 0 | 0 | 0
4810 | MURSHIDABAD | Berhampore Mechanical | LOKAIPUR PIPED WATER SUPPLY SCHEME. , SM/16552 | New | LOKAIPUR PH-1 NEW CONNECTION | 389/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 3.85 | 0 | 0 | 0
4811 | MURSHIDABAD | Berhampore Mechanical | LOKAIPUR PIPED WATER SUPPLY SCHEME. , SM/16552 | New | NEW CONNECTION LOKAIPUR PH-II | 9/WBSEDCL-JJM | 09/04/2024 | 0 | WBSEDCL | 4.73 | 0 | 0 | 0
4812 | MURSHIDABAD | Berhampore Mechanical | LOKAIPUR PIPED WATER SUPPLY SCHEME. , SM/16552 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube well in connection to Accommodate FHTC at Pump House No.-I II & III under LOKAIPUR ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | 3809/MEDB | 03/11/2023 | 790 | DEBJYOTI BASU | 31.24 | 20.02 | 64.09 | 10
4813 | MURSHIDABAD | Murshidabad Division | LOKAIPUR PIPED WATER SUPPLY SCHEME. , SM/16552 | New | Additional work for Laying of UPVC pipeline, Construction of Culvert and Approach road of LOKHAIPUR Piped Water Supply Scheme in Suti-II Block of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | 783/MURD | 03/04/2025 | 45 | AZAD ENTERPRISE | 47.72 | 0 | 0 | 0
4814 | MURSHIDABAD | Murshidabad Division | LOKAIPUR PIPED WATER SUPPLY SCHEME. , SM/16552 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 4.13 | 100 | 100
4815 | MURSHIDABAD | Murshidabad Division | BISWANATHPUR PIPED WATER SUPPLY SCHEME. , SM/16553 | New | Material Requisition To Resource Division | 1129/MURD/4 | 25/04/2023 | 0 | Resource Division | 1.78 | 0 | 0 | 0
4816 | MURSHIDABAD | Berhampore Mechanical | BISWANATHPUR PIPED WATER SUPPLY SCHEME. , SM/16553 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Biswanathpur ground water based water supply scheme under Block_ Khargram Dist. - Murshidabad under MEDB, PHE Dte. | 3703/MEDB | 03/11/2023 | 668 | M/S S. S. ENTERPRISE (DOMKAL) | 20.82 | 0 | 0 | 30
4817 | MURSHIDABAD | Murshidabad Division | BISWANATHPUR PIPED WATER SUPPLY SCHEME. , SM/16553 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BISWANATHPUR Water Supply Scheme at Head Work Site, 2nd Site site at Khargram Block under Murshidabad Division, P.H. Engineering Dte | 2777/MURD | 01/09/2023 | 21 | MAMATA USHA ENTERPRISE | 18.44 | 14.11 | 100 | 90
4818 | MURSHIDABAD | Berhampore Mechanical | BISWANATHPUR PIPED WATER SUPPLY SCHEME. , SM/16553 | New | NEW SERVICE CONNECTION AT BISWANATHPUR PH I, ID304233599 | 264/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 3.24 | 0 | 0 | 0
4819 | MURSHIDABAD | Berhampore Mechanical | BISWANATHPUR PIPED WATER SUPPLY SCHEME. , SM/16553 | New | NEW SERVICE CONNECTION AT BISWANATHPUR PH II, ID304233616 | 262/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 7.78 | 0 | 0 | 0
4820 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-III, Block- Berhampore, District- Murshidabad. , SM/16045 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Char Halalpur Zone-III village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3075/MEDB | 02/08/2023 | 92 | SURAKSHA | 6.3 | 0 | 0 | 0
4821 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Halalpur Zone-III, Block- Berhampore, District- Murshidabad. , SM/16045 | New | Mini Piped Water Supply Scheme for Char Hallalpur Zone-III under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 171/BD-I | 16/05/2023 | 90 | HI-LIGHT ELECTRONICS | 30.32 | 0 | 0 | 0
4822 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-II, Block- Berhampore, District- Murshidabad. , SM/16497 | New | Mini Piped Water Supply Scheme for Char Sujapur Zone-II under Berhampore block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 167/BD-I | 16/05/2023 | 90 | ALOK BANERJEE ENTERPRISE | 30.49 | 0 | 0 | 0
4823 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Char Sujapur Zone-II, Block- Berhampore, District- Murshidabad. , SM/16497 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at CharSujapur Zone-II village, Block:- Berhampore under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3041/MEDB | 02/08/2023 | 92 | M/S. SUPER CONSTRUCTION | 6.32 | 0 | 0 | 0
4824 | MURSHIDABAD | Berhampore Mechanical | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-II, Block- Nawda, District- Murshidabad. , SM/16498 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Shibnagar Zone-II village, Block:- Nawda under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3045/MEDB | 02/08/2023 | 92 | TARUN KUMAR BHATTACHARYA | 6.26 | 0 | 0 | 0
4825 | MURSHIDABAD | Berhampore Division I | Mini piped water supply scheme (Maximum 100 house holds) Village- Sibnagar Zone-II, Block- Nawda, District- Murshidabad. , SM/16498 | New | Mini Piped Water Supply Scheme for Sibnagar Zone-II under Nawda block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 155/BD-I | 15/05/2023 | 90 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 30.53 | 0 | 0 | 0
4826 | MURSHIDABAD | Berhampore Mechanical | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Arazi Narayanpur, Block- Lalgola, District- Murshidabad. , SM/16502 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Arazi Narayanpur village, Block- Lalgola under ground water based mini piped water supply scheme, Dist- Murshidabad. under MEDB PHE Dte. | 587/MEDB | 31/01/2024 | 90 | GANGULI ELECTRICAL CO. | 6.3 | 0 | 0 | 0
4827 | MURSHIDABAD | Berhampore Division I | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Arazi Narayanpur, Block- Lalgola, District- Murshidabad. , SM/16502 | New | Mini Piped Water Supply Scheme for Arazi Narayanpur under lalgola block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 147/BD-I | 15/05/2023 | 90 | INDRAJIT DUBEY | 28.9 | 0 | 0 | 0
4828 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KAGRAM WATER SUPPLY SCHEME BLOCK- BHARATPUR -II , DIST- MURSHIDABAD. , SM/16179 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 5.6 | 100 | 76
4829 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KAGRAM WATER SUPPLY SCHEME BLOCK- BHARATPUR -II , DIST- MURSHIDABAD. , SM/16179 | Augmentation | Material Requisition To Resource Division | 1004/MURD/9 | 11/04/2023 | 0 | Resource Division | 66.52 | 0 | 0 | 0
4830 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KAGRAM WATER SUPPLY SCHEME BLOCK- BHARATPUR -II , DIST- MURSHIDABAD. , SM/16179 | Augmentation | Material Requisition To Resource Division | 1043/MURD | 17/04/2023 | 0 | Resource Division | 37.46 | 0 | 0 | 0
4831 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KAGRAM WATER SUPPLY SCHEME BLOCK- BHARATPUR -II , DIST- MURSHIDABAD. , SM/16179 | Augmentation | Construction of 300 Cum OHR, Pump House, Boundwary Wall, Rising Main Connection & Repairing work of Existing OHR, Boundwary Wall , Pump House for Augmentation of Kagram water supply scheme of Bharatpur-II Block under Murshidabad Division, PHE Dte. PART_A | 992/MURD | 11/04/2023 | 721 | DALIM BISWAS ENTERPRISE | 157.49 | 80.42 | 51.06 | 15
4832 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KAGRAM WATER SUPPLY SCHEME BLOCK- BHARATPUR -II , DIST- MURSHIDABAD. , SM/16179 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 3.06 | 100 | 80
4833 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KAGRAM WATER SUPPLY SCHEME BLOCK- BHARATPUR -II , DIST- MURSHIDABAD. , SM/16179 | Augmentation | Material Requisition To Resource Division | MURD/439/04 | 08/02/2024 | 0 | Resource Division | 4.1 | 0 | 0 | 0
4834 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF KAGRAM WATER SUPPLY SCHEME BLOCK- BHARATPUR -II , DIST- MURSHIDABAD. , SM/16179 | Augmentation | NEW CONNECTION AT KAGRAM PH-III | 68/WBSEDCL-JJM | 09/05/2024 | 0 | WBSEDCL | 5.22 | 0 | 0 | 0
4835 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KAGRAM WATER SUPPLY SCHEME BLOCK- BHARATPUR -II , DIST- MURSHIDABAD. , SM/16179 | Augmentation | Sinking of 01 (One) No. of 300 mm x 200 mm dia tube well i.e. TW-III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Kagram & Salar Zone - IA Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 1102/MURD | 24/04/2023 | 20 | INDRAJIT MAZUMDAR | 10.68 | 0 | 0 | 0
4836 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KAGRAM WATER SUPPLY SCHEME BLOCK- BHARATPUR -II , DIST- MURSHIDABAD. , SM/16179 | Augmentation | Laying Distribution System & FHTC, for Augmentation of Kagram water supply scheme of Bharatpur-II Block under Murshidabad Division, PHE Dte. PART_B | 1232/MURD | 04/05/2023 | 365 | M/S NIRAPADA BHATTACHARJEE | 272.58 | 18.84 | 6.91 | 30
4837 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF KAGRAM WATER SUPPLY SCHEME BLOCK- BHARATPUR -II , DIST- MURSHIDABAD. , SM/16179 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gaysabad, Kagram, Ranagram, Augmentation of Islampur & Augmentation of Shibnagar Laskarpur Zone - II Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | 661/MURD | 19/03/2025 | 170 | M/S GUHA AND ROY | 35.27 | 0 | 0 | 100
4838 | MURSHIDABAD | Murshidabad Division | AUGUMENTATION OF GARIBPUR PIPE WATER SUPPLY SCHEME (ZONE- II) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/15922 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 4.84 | 100 | 1
4839 | MURSHIDABAD | Murshidabad Division | AUGUMENTATION OF GARIBPUR PIPE WATER SUPPLY SCHEME (ZONE- II) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/15922 | Augmentation | Material Requisition To Resource Division | 1167/MURD/36 | 28/04/2023 | 0 | Resource Division | 44.55 | 0 | 0 | 0
4840 | MURSHIDABAD | Berhampore Mechanical | AUGUMENTATION OF GARIBPUR PIPE WATER SUPPLY SCHEME (ZONE- II) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/15922 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under Garibpur ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | 3764/MEDB | 03/11/2023 | 92 | JOGMAYA ENGINEERING | 23.96 | 0 | 0 | 10
4841 | MURSHIDABAD | Murshidabad Division | AUGUMENTATION OF GARIBPUR PIPE WATER SUPPLY SCHEME (ZONE- II) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/15922 | Augmentation | Augmentation of GARIBPUR (Zone-II) PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Subdivision , Murshidabad District under Murshidabad Division, PHE. Dte. | 1381/MURD | 22/05/2023 | 1123 | DOBAY CONSTRUCTION | 241.39 | 144.38 | 59.81 | 85
4842 | MURSHIDABAD | Murshidabad Division | AUGUMENTATION OF GARIBPUR PIPE WATER SUPPLY SCHEME (ZONE- II) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/15922 | Augmentation | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for official use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.,e. from 01/01/2025 to 30/06/2025 (Vehicle No. W.B-57E-9142) | 626/ISD | 31/12/2024 | 181 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 0.89 | 1.18 | 133.1 | 0
4843 | MURSHIDABAD | Murshidabad Division | AUGUMENTATION OF GARIBPUR PIPE WATER SUPPLY SCHEME (ZONE- II) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/15922 | Augmentation | Continuation order for Hiring of Maxicab (Non-Air Condition, Bharat Stage-III on or after 01/05/2008 with Diesel/ LPG/ CNG Engine) in perfect good running condition of performing a very long journey and should be covered without any trouble on monthly hire basis for offical use for the Office of the Assistant Engineer, Islampur Sub-Division, P.H.E Dte. for 06 (Six) months i.e. from 01/10/2025 to 31/03/2026 (120 days) [WB-26T-1742] | 390/ISD | 25/09/2025 | 181 | HAMIDUL ISLAM | 0.59 | 0 | 0 | 0
4844 | MURSHIDABAD | Berhampore Division I | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Darura, Block- Murshidabad Jiaganj, District- Murshidabad. , SM/16212 | New | Mini Piped Water Supply Scheme for Darura under Murshidabad -Jiaganj block of Murshidabad district under Berhampore division-I,P.H.E Dte. | 161/BD-I | 16/05/2023 | 90 | PRITAM KUMAR PAUL | 23.62 | 0 | 0 | 0
4845 | MURSHIDABAD | Berhampore Mechanical | Mini Piped Water Supply Scheme (Maximum 100 Households) Village- Darura, Block- Murshidabad Jiaganj, District- Murshidabad. , SM/16212 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Darura village, Block:- Murshidabad - Jiaganj under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3044/MEDB | 02/08/2023 | 92 | M/S. SUPER CONSTRUCTION | 6.32 | 0 | 0 | 0
4846 | MURSHIDABAD | Berhampore Mechanical | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. , SM/16215 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hatisala Part-A village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3051/MEDB | 02/08/2023 | 92 | SARKAR CONSTRUCTION | 6.3 | 0 | 0 | 0
4847 | MURSHIDABAD | Berhampore Mechanical | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. , SM/16215 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hatisala Part-C village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3053/MEDB | 02/08/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0 | 0
4848 | MURSHIDABAD | Berhampore Mechanical | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. , SM/16215 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hatisala Part-D village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3054/MEDB | 02/08/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0 | 0
4849 | MURSHIDABAD | Berhampore Mechanical | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. , SM/16215 | New | Providing and installation of pumping machinery and other electromechanical equipments at Newly sunk Tube Well at Hatisala Part-B village, Block:- Burwan under ground water based mini piped water supply scheme, Dist:- Murshidabad. under MEDB PHE Dte. | 3052/MEDB | 02/08/2023 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 6.3 | 0 | 0 | 0
4850 | MURSHIDABAD | Murshidabad Division | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. , SM/16215 | New | Ground Water based piped water supply scheme for Hatisala Part- C village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2323/MURD | 02/08/2023 | 60 | M/S. MONDAL ENTERPRISE | 30.25 | 0 | 0 | 0
4851 | MURSHIDABAD | Murshidabad Division | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. , SM/16215 | New | Ground Water based piped water supply scheme for Hatisala Part- D village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2327/MURD | 02/08/2023 | 60 | U.S BUILDERS | 30.54 | 0 | 0 | 0
4852 | MURSHIDABAD | Murshidabad Division | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. , SM/16215 | New | Ground Water based piped water supply scheme for Hatisala Part- B village, Block:- Burwan, Kandi Sub- Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2322/MURD | 02/08/2023 | 60 | KESHAB CHANDRA DAS | 30.54 | 0 | 0 | 0
4853 | MURSHIDABAD | Murshidabad Division | HATISALA PIPED WATER SUPPLY SCHEME, BLOCK- BURWAN , DISTRICT- MURSHIDABAD. , SM/16215 | New | Ground Water based piped water supply scheme for Hatisala Part- A village, Block:- Burwan, Kandi Sub Division in Murshidabad district under Murshidabad Division, P.H.E Dte. | 2024/MURD | 25/07/2023 | 60 | M/S S.R.K. ENTERPRISE | 30.55 | 0 | 0 | 0
4854 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara , SM/08193 | Retrofitting | Retrofitting of Functional Household Tap Connections(FHTC) and allied works in connection with "JALSWAPNA (JAL JEEVAN MISSION) " from existing Distribution system within the Command area of village SUNIA (Village Code 315806) under Bharatpur Ground Water Based Water Supply Scheme for arsenic affected areas of Bharatpur-I Block in the District of Murshidabad. | 3037/MURD | 07/12/2020 | 45 | NAMDAR ALI | 8.6 | 0 | 0 | 1
4855 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara , SM/08193 | Retrofitting | Retrofitting of Functional Household Tap Connections (FHTC) and allied works in connection with 'JAL SWAPNA (JAL JEEVAN MISSION) ' from existing Distribution system within the Command area of village LAKSHIJALA (Village Code 314127) under KASIADANGA Ground Water Based Water Supply Scheme for arsenic affected areas of RAGHUNATHGANJ-II Block in the District of Murshidabad. Tender no - 550 of 21-22 by EE MURD | 366-MSD/21-22 | 11/03/2022 | 0 | NAMDAR ALI | 4.55 | 0 | 0 | 0
4856 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara , SM/08193 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at ALUGRAM G.P. under Murshidabad Division, P.H.E.Dte. | 234/KSD | 27/08/2021 | 60 | IMAGIN | 4.17 | 0 | 0 | 0
4857 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara , SM/08193 | Retrofitting | Holding Awarness Programme / Campaigning programms at Alugram G.P, Bharatpur G.P and Sijgram G.P in connection with Functional Household Tap Connection (FHTC) under Murshidabad Division, P.H.E. Dte. (Total nos of Programme = 12 nos) (Part-E). | 253/KSD | 31/08/2021 | 30 | S.S.INFRASTRUCTURE | 2.4 | 0 | 0 | 0
4858 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara , SM/08193 | Retrofitting | Formation & Functioning of Women & Girls for water (JAL YODHA) in connection with IEC Activty for FHTC work at SIJGRAM G.P. under Murshidabad Division, P.H.E.Dte. | 240/KSD | 27/08/2021 | 60 | S.S.INFRASTRUCTURE | 4.17 | 0 | 0 | 0
4859 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara , SM/08193 | Retrofitting | Extension of UPVC pipeline for FHTC work at Daspara, Ghoshpara, Kurulpara, Anchalpara, Gobardhanpara and Bagdipara in the Village of Alugram of Bharatpur Water Supply Scheme under Kandi Sub Division, P.H.E Dte. in the district of Murshidabad. | 11 / KSD | 06/04/2022 | 30 | M/S. RAHAMAN CONSTRUCTION CO | 4.84 | 4.83 | 100 | 0
4860 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara , SM/08193 | Retrofitting | Laying of parallel distribution pipe line in between node point 15F to 23A and extension of distribution pipe line left & right side of canal of Alugram village (Village Code-315806) of Bharatpur water supply scheme for FHTC work under Kandi Sub Division, P.H.E.Dte. in the district of Murshidabad. | 07 / KSD | 06/04/2022 | 30 | AGNIBESH CHATTERJEE | 4.84 | 4.84 | 100 | 1
4861 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara , SM/08193 | Retrofitting | Repairing of rising main pipe line including supplying of C.I specials, valves, construction of valve chamber & surface drain for the FHTC work of Bharatpur water Supply Scheme under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad. (SL-04) | 157/KSD | 31/08/2022 | 30 | PRANAB KUMAR GHOSH | 4.77 | 4.74 | 100 | 0
4862 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara , SM/08193 | Retrofitting | Material Requisition To Resource Division | 541/2/MURD | 25/02/2022 | 0 | Resource Division | 5.12 | 0 | 0 | 0
4863 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara , SM/08193 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village Alugram under Bharatpur Ground Based Water Supply Scheme for Arsenic Affected Area of Bharatpur-I Block, under Murshidabad Division, PHE Dte. Scheme ID 0007336059 in the District of Murshidabad. (Sl No-18) | 3270/MURD | 24/12/2020 | 180 | M/S . SUKUMAR SINHA | 109.97 | 129.52 | 118.84 | 100
4864 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara , SM/08193 | Retrofitting | Supplying of C.I specials, valves & construction of valve chamber of different location for FHTC work of Alugram village of Bharatpur water Supply Scheme under Kandi Sub Division, P.H.E. Dte. in the district of Murshidabad. | 3182/MURD | 30/11/2022 | 20 | U.S BUILDERS | 4.97 | 4.77 | 100 | 100
4865 | MURSHIDABAD | Murshidabad Division | Retrofitting of functional Household Tap Connections (FHTC) under Jal Swapna (JJM) of mouza Sankarmarui, Bharatpur, Alugram, Sunia, Madanpur Dafarpur, Karea (315772, 315805, 315806, 315807, 315810, 315816) of Bharatpur under Ground WBWSS for AAAA of Bhara , SM/08193 | Retrofitting | Retrofitting Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission ) and under command area of village of Madanpur Dafarpur ( Village Code -315810) under BHARATPUR Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Bharatpur-I Block under Murshidabad Division P.H.E Dte. (Scheme I.D.-0007336059) | 731/MURD | 16/03/2022 | 45 | MOTI RAHAMAN | 40.35 | 14.97 | 37.09 | 45
4866 | MURSHIDABAD | Murshidabad Division | Augmentation of Garibpur Piped Water Supply Scheme (Zone-I ) Part - A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15916 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Domkol Block under Islampur Sub-Division Murshidabad Division P.H.E. Dte. PART-A | 284/MURD | 03/02/2022 | 60 | MERCHANDISE-INDIA | 105.32 | 10.84 | 100 | 1
4867 | MURSHIDABAD | Murshidabad Division | Augmentation of Garibpur Piped Water Supply Scheme (Zone-I ) Part - A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15916 | Augmentation | Material Requisition To Resource Division | 1210/MURD/25 | 02/05/2023 | 0 | Resource Division | 217 | 0 | 0 | 0
4868 | MURSHIDABAD | Murshidabad Division | Augmentation of Garibpur Piped Water Supply Scheme (Zone-I ) Part - A Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/15916 | Augmentation | Formal work order for Augmentation of Garibpur Zone-I (Part - A) Piped Water Supply Scheme under Jal Jevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE.Dte. | 624/MURD | 03/03/2023 | 1123 | M/S. S. DAS AND ENTERPRISE | 590.43 | 412.83 | 69.92 | 40
4869 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- II A Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16415 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 07(Seven) Nos existing commissioned PWSS of Farakka & Samserganj Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-A | 1191/MURD | 10/05/2022 | 30 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 37.77 | 7.75 | 200 | 1
4870 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- II A Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16415 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14(Forteen) nos existing commisioned PWSS Samserganj & Farakka Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Ballalpur , Mahadebnagar Zone-IA, Zone-IB, Zone-IC, Zone-IIA, Zone-IIB, Jaikrishnapur Zone-I, Zone-II, Bhasaipaikar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Zone-III, Sikdarpur Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2788/MURD | 04/09/2023 | 800 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 34.97 | 0 | 0 | 30
4871 | MURSHIDABAD | Murshidabad Division | Augmentation of Mahadebnagar Zone- II A Water Supply Scheme Block - Farakka, Dist- Murshidabad. , SM/16415 | Augmentation | Preparation of Design, Drawing, and approval from the Railway authorities including supply of MS casing pipe and pushing of Casing pipe by Hydraulic Jacking Technique method across the railway track between Dhuliyan Ganga Station to Sankopara halt Station (TP NO 244/5 & 244/6) at Monrajpur mouza & Connecting with existing 110 mm dia uPVC distribution main line of Mahadevnagar Zone - II ground based W/S Scheme , Jangipur Sub Division, PHE Dte. | 2477/MURD | 16/08/2021 | 60 | ACQUA CONSTRACTION CONSORTIAM | 23.65 | 21.37 | 100 | 0
4872 | MURSHIDABAD | Berhampore Division I | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16375 | New | Material Requisition To Resource Division | 61/BD-1/19 | 27/04/2023 | 0 | Resource Division | 15.51 | 0 | 0 | 0
4873 | MURSHIDABAD | Berhampore Division I | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16375 | New | Material Requisition To Resource Division | 304/BD-1/5 | 22/02/2024 | 0 | Resource Division | 7.38 | 0 | 0 | 0
4874 | MURSHIDABAD | Berhampore Mechanical | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16375 | New | SHYAMPUR PH-1 | 397/WBSEDCL-JJM | 04/03/2024 | 0 | WBSEDCL | 6.46 | 0 | 0 | 0
4875 | MURSHIDABAD | Berhampore Mechanical | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16375 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-III under SYAMPUR ground water based water supply scheme under Block_ LALGOLA Dist. - Murshidabad under MEDB, PHE Dte. | 1154/MEDB | 14/05/2025 | 92 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 10.92 | 0 | 0 | 0
4876 | MURSHIDABAD | Berhampore Division I | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16375 | New | SYAMPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 222/BD-I | 17/05/2023 | 639 | SKY CONSTRUCTION | 50.19 | 28.32 | 56.43 | 40
4877 | MURSHIDABAD | Berhampore Division I | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16375 | New | SYAMPUR PWSS to accommodate FHTC, OHR, Laying Distribution System, Rising Main, under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | 663/BD-I | 09/08/2023 | 784 | M/S ABDUL MATIN | 290.59 | 115.52 | 39.76 | 30
4878 | MURSHIDABAD | Berhampore Division I | SYAMPUR AND ADJOINING MOUJAS PIPED WATER SUPPLY SCHEME , SM/16375 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SHYAMPUR PWSS (2nd TW Site) under Jal Jeevan Mission in Lalgola Block under Berhampore Division - I, P.H.Engineering Dte. in the district of Murshidabad. (01 Nos TW) | 838/BD-I | 23/06/2025 | 15 | B.M. ENGINEERING & CONSTRUCTION | 9 | 0 | 0 | 0
4879 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-III piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16420 | Augmentation | Material Requisition To Resource Division | 1167/MURD/48 | 28/04/2023 | 0 | Resource Division | 33.47 | 0 | 0 | 0
4880 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Rejinagar Zone-III piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16420 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I and II ,Zone-III under REJINAGAR ground water based water supply scheme under Block_ BELDANGA-II Dist. - Murshidabad under MEDB, PHE Dte. | 3674/MEDB | 03/11/2023 | 92 | SREE RADHA ELECTRICAL | 21.42 | 15.21 | 70.99 | 6
4881 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-III piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16420 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 4.07 | 100 | 80
4882 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-III piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16420 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 2.59 | 100 | 100
4883 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-III piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16420 | Augmentation | Allied work of laying of distribution system pipe line for providing Functional Household Tap Connections (FHTC) in connection with Jal Swapna (Jal Jeevan Mission) and under command area of village of Maradighi ( Village Code -315674) under Rejinagar Ground Water Based Water Supply Scheme for Arsenic Affected Areas of Beldanga -II Block under Murshidabad Division P.H.E Dte. in the District of Murshidabad. | 1984/MURD | 08/07/2024 | 176 | SUPIA CONSTRUCTION | 15.86 | 4.18 | 20.94 | 80
4884 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-III piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16420 | Augmentation | Material Requisition To Resource Division | 1811/MURD/21 | 20/06/2024 | 0 | Resource Division | 8.44 | 0 | 0 | 0
4885 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Rejinagar Zone-III piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16420 | Augmentation | NEW CONNECTION AT REJINAGAR Z-III PH-I | 415/WBSEDCL-JJM | 06/03/2024 | 0 | WBSEDCL | 5.8 | 0 | 0 | 0
4886 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-III piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16420 | Augmentation | Providing FHTC connection to 1016 nos household , Laying of Distribution System, Rising Main for Augmentation work of Rejinagar Zone-III PWSS within Beldanga-II Block under Murshidabad Division , PHE.Dte. ( PART - A) | 2769/MURD | 01/09/2023 | 731 | MITRA CONSTRUCTION | 159.63 | 0 | 0 | 100
4887 | MURSHIDABAD | Murshidabad Division | Augmentation of Rejinagar Zone-III piped water supply scheme in Beldanga -II Block in the District of Murshidabad. , SM/16420 | Augmentation | Augmentation of Ground Water Based Rejinagar Zone III PWSS of accommodate with Boundary Wall, 400 CUM OHR in Beldanga II Block within Murshidabad District under Murshidabad Division, PHE Dte. [ Part B ] | 3331/MURD | 23/10/2023 | 844 | NEW INDIA CONSTRUCTION | 188.69 | 29.86 | 15.83 | 80
4888 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF JURANPUR PIPE WATER SUPPLY SCHEME (PART-B) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16558 | Augmentation | Material Requisition To Resource Division | 1180/MURD/01 | 29/04/2023 | 0 | Resource Division | 1.11 | 0 | 0 | 0
4889 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF JURANPUR PIPE WATER SUPPLY SCHEME (PART-B) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16558 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Juranpur ( PART-B) Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | 1765/MURD | 06/07/2023 | 21 | NADIA TUBEWELLS | 35.34 | 31.71 | 100 | 80
4890 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF JURANPUR PIPE WATER SUPPLY SCHEME (PART-B) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16558 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 4.47 | 100 | 100
4891 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF JURANPUR PIPE WATER SUPPLY SCHEME (PART-B) DOMKAL BLOCK IN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16558 | Augmentation | Augmentation of JURANPUR (Part-B) PWSS under Jal Jivan Mission of DOMKAL Block, ISLAMPUR Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. | 1382/MURD | 22/05/2023 | 955 | BISWAS CONSTRUCTION (GOLAM MURTAJA, BABLABONA AAIFB7956Q) | 122.02 | 30.68 | 25.14 | 20
4892 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-II PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/16621 | Augmentation | Material Requisition To Resource Division | 1278/MURD/18 | 10/05/2023 | 0 | Resource Division | 13.02 | 0 | 0 | 0
4893 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-II PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/16621 | Augmentation | Providing FHTC Connection to 324 nos household , Laying of Distribution System (Part_B), Repairing & Vertical Extention of Boundary Wall for for Augmentation work of BACHHRA ZONE-II PWSS in Beldanga-II Block under Murshidabad Division , PHE.Dte. (part_B) | 848/MURD | 24/03/2023 | 180 | GHOSH BUILDERS (PROP-CHAITANYA GHOSH) | 103.19 | 20.74 | 20.1 | 50
4894 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-II PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/16621 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 08(Eight) nos existing commisioned PWSS Beldanga-II Block of Berhampore Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Bachra Zone-I, Zone-II, Loknathpur Zone-I, Zone-II, Rejinagar Zone-I, Zone-II, Zone-III, Zone-IV Water Supply Schemes of Berhampore Sub- Division under Murshidabad Division | 2657/MURD | 24/08/2023 | 20 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 19.95 | 2.6 | 100 | 100
4895 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-II PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/16621 | Augmentation | Renovation of Existing IEP (Capacity 50 Cu.M/hr) for changing of 01 No Iron Removal Filter media unit of (3.30 m dia x 1.50 M HOS) & 01 No Oxidation Chamber of (1.00 M dia x 1.00 M HOS) and painting all vessel, pipes etc. all complete for Augmentation of Bachara Z-II Pipe Water supply scheme under Murshidabad Division P.H.E Dte. in the district of Murshidabad. | 2074/MURD | 19/07/2024 | 30 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 4.84 | 0.82 | 20.94 | 100
4896 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-II PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/16621 | Augmentation | Material Requisition To Resource Division | 1811/MURD/12 | 20/06/2024 | 0 | Resource Division | 1.4 | 0 | 0 | 0
4897 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-II PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/16621 | Augmentation | Construction of 100 Cum OHR, Laying of Distribution System (part_A) , Rising Main , repairing & Overhauling of R.C.C. elevated reservoir 250 Cum capacity, Repairing & Vertical Extention of Boundary Wall for Augmentation work of BACHHARA ZONE-II PWSS in BELDANGA-II Block under Murshidabad Division , PHE.Dte. (part_A) | 1870/MURD | 14/07/2023 | 795 | M/S. S.C. CIVIL ENTERPRISES | 280 | 80.62 | 28.79 | 30
4898 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF BACHHRA ZONE-II PIPED WATER SUPPLY SCHEME BLOCK BELDANGA -II DISTRICT MURSHIDABAD. , SM/16621 | Augmentation | Sinking of 04 (Four) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bachhra Zone - II PWSS, Bara Satui PWSS, Kodla PWSS , Bachra Zone - I PWSS, Basabari PWSS & Char Mohula PWSS under Berhampore Sub-Division, Murshidabad Division, P.H.Engineering Dte. | 662/MURD | 19/03/2025 | 135 | M/S. BIMALENDU BOSE | 46.93 | 0 | 0 | 75
4899 | MURSHIDABAD | Berhampore Division I | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS , SM/16787 | New | Material Requisition To Resource Division | 61/BD-1/26 | 27/04/2023 | 0 | Resource Division | 11.84 | 0 | 0 | 0
4900 | MURSHIDABAD | Berhampore Division I | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS , SM/16787 | New | Material Requisition To Resource Division | 304/BD-1/9 | 22/02/2024 | 0 | Resource Division | 4.82 | 0 | 0 | 0
4901 | MURSHIDABAD | Berhampore Division I | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS , SM/16787 | New | GOURIDASPUR PWSS to accommodate construction of Pump House Cum Chlorine Room, boundary wall and service road, under Jal Jeevan Mission of Lalgola Block, Murshidabad District under Berhampore Division-I, PHE.Dte.. | 202/BD-I | 17/05/2023 | 1254 | M/S ROY & BOSE ENTERPRISE | 41.09 | 2.65 | 6.45 | 75
4902 | MURSHIDABAD | Berhampore Mechanical | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS , SM/16787 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Gouridaspur Piped Water Supply Scheme Block Lalgola, District - Murshidabad. under MEDB, PHE Dte. | 382/MEDB | 12/02/2025 | 89 | CHAKRABORTY MINING AND ENGINEERING | 22.73 | 0 | 0 | 0
4903 | MURSHIDABAD | Berhampore Division I | GOURIDASPUR AND ADJOINIONG MOUJAS PWSS , SM/16787 | New | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GOURIDASPUR Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | 11/BD-I | 06/01/2025 | 90 | HARUN ALL RASHID & BROTHERS | 8.91 | 0 | 0 | 100
4904 | MURSHIDABAD | Murshidabad Division | Augmentation of Nagar Zone- I Water Supply Scheme Block - Khargram , Dist- Murshidabad. , SM/15726 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 2.62 | 72.41 | 76
4905 | MURSHIDABAD | Murshidabad Division | Augmentation of Nagar Zone- I Water Supply Scheme Block - Khargram , Dist- Murshidabad. , SM/15726 | Augmentation | Material Requisition To Resource Division | 1004/MURD/5 | 11/04/2023 | 0 | Resource Division | 62.48 | 0 | 0 | 0
4906 | MURSHIDABAD | Murshidabad Division | Augmentation of Nagar Zone- I Water Supply Scheme Block - Khargram , Dist- Murshidabad. , SM/15726 | Augmentation | Material Requisition To Resource Division | MURD/439/07 | 08/02/2024 | 0 | Resource Division | 20.57 | 0 | 0 | 0
4907 | MURSHIDABAD | Murshidabad Division | Augmentation of Nagar Zone- I Water Supply Scheme Block - Khargram , Dist- Murshidabad. , SM/15726 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 0 | 0 | 75
4908 | MURSHIDABAD | Murshidabad Division | Augmentation of Nagar Zone- I Water Supply Scheme Block - Khargram , Dist- Murshidabad. , SM/15726 | Augmentation | Laying of Rising Main , Distribution System, FHTC, construction of OHR (Capacity 450 cum), , Sinking of Tube Well , Repairing of pump house and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Nagar Zone-I PWSS in Khargram Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, P.H.E. Dte. | 3298/MURD | 20/10/2023 | 805 | SAMIMA ENTERPRISE | 492.21 | 58.92 | 11.97 | 10
4909 | MURSHIDABAD | Murshidabad Division | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. , SM/15750 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 12(Twelve) Nos Existing commissioned PWSS of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. | 285/MURD | 03/02/2022 | 60 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 89.28 | 4.37 | 100 | 76
4910 | MURSHIDABAD | Murshidabad Division | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. , SM/15750 | Augmentation | Material Requisition To Resource Division | 1004/MURD/3 | 11/04/2023 | 0 | Resource Division | 70.9 | 0 | 0 | 0
4911 | MURSHIDABAD | Murshidabad Division | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. , SM/15750 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well i.e. TW-I of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Burwan Zone- I Water Supply Scheme at Head Work Site, 2nd Site,3 r d site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | 3917/MURD | 21/12/2023 | 21 | MAMATA USHA ENTERPRISE | 11.79 | 0 | 0 | 0
4912 | MURSHIDABAD | Murshidabad Division | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. , SM/15750 | Augmentation | Wall writing on smooth, durable wall surface (preferably of Govt. premises/Boundary wall) by cleaning the surface thoroughly, removing old paints, preparing with one coat good quality exterior primer and painting the surface with best quality synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc of multiple colour as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Murshidabad all complete as per direction of EIC. | 517/MURD | 16/02/2024 | 60 | IMAGIN | 97.48 | 1.73 | 100 | 80
4913 | MURSHIDABAD | Murshidabad Division | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. , SM/15750 | Augmentation | Augmentation of Ground Water Based Burwan Zone-I PWSS of accommodate FHTC( 1848 Nos), Laying Distribution System, Laying Rising Main, Repairing of Switch Room, Boundary Wall, 200 CUM OHR, Repairing of 272 CUM OHR in Burwan Block within Murshidabad District under Murshidabad Division, PHE Dte. | 2678/MURD | 24/08/2023 | 586 | MOTI RAHAMAN | 360.93 | 64.27 | 17.81 | 10
4914 | MURSHIDABAD | Murshidabad Division | Augmentation of Burwan Zone- I Water Supply Scheme Block - Burwan, Dist- Murshidabad. , SM/15750 | Augmentation | Additional work for Augmentation of Burwan (Zone-I) PWSS of accommodate FHTC, Laying of Distribution System, Road Restoration work and Land Development in Burwan Block of Kandi Sub Division under Murshidabad Division, P.H.E.Dte. | 1111/MURD | 15/05/2025 | 60 | MOTI RAHAMAN | 87.4 | 0 | 0 | 0
4915 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SELAMATIPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16752 | Augmentation | Preparation of D.P.R(Consultancy work)in connection with the Functional House Hold Connection of different existing PWSS (Selamatipur PWSS Scheme, Block - Berhampore) to be Augmentation/Rejuvination under Murshidabad Division P.H.E. Dte. | 3267/MURD | 05/10/2021 | 60 | RADIANT | 3.23 | 3.23 | 100 | 0
4916 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SELAMATIPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16752 | Augmentation | Material Requisition To Resource Division | 1278/MURD/2 | 10/05/2023 | 0 | Resource Division | 10.58 | 0 | 0 | 0
4917 | MURSHIDABAD | Murshidabad Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SELAMATIPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16752 | Augmentation | Material Requisition To Resource Division | 1811/MURD/02 | 20/06/2024 | 0 | Resource Division | 16.77 | 0 | 0 | 0
4918 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SELAMATIPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16752 | Augmentation | QUOTATION FOR SHIFTING OF PHE25KVA DTR AT SALAMATPUR REF ID. 860308681 |  | 16/08/2024 | 0 | WBSEDCL | 4.47 | 0 | 0 | 0
4919 | MURSHIDABAD | Berhampore Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF GROUND WATER BASED SELAMATIPUR PWSS TO ACCOMMODATE FHTC IN BERHAMPORE BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16752 | Augmentation | QUOTATION FOR SHIFTING OF PHE 25KVA DTR AT SALAMATPUR REF ID. 860308681 | 199/WBSEDCL-JJM | 22/08/2024 | 0 | WBSEDCL | 4.47 | 0 | 0 | 0
4920 | MURSHIDABAD | Murshidabad Division | BADDA AND IT'S ADJOINING MOUJAS , SM/15678 | New | Material Requisition To Resource Division | 1075/MURD/18 | 19/04/2023 | 0 | Resource Division | 24.74 | 0 | 0 | 0
4921 | MURSHIDABAD | Murshidabad Division | BADDA AND IT'S ADJOINING MOUJAS , SM/15678 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at BADDA AND IT'S ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | 2794/MURD | 04/09/2023 | 21 | INDRAJIT MAZUMDAR | 18.45 | 15.55 | 100 | 100
4922 | MURSHIDABAD | Berhampore Mechanical | BADDA AND IT'S ADJOINING MOUJAS , SM/15678 | New | NEW SERVICE CONNECTION AT PWSS BADDA PH1 ID 304248207 | 314/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 10.01 | 0 | 0 | 0
4923 | MURSHIDABAD | Berhampore Mechanical | BADDA AND IT'S ADJOINING MOUJAS , SM/15678 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Badda ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | 3695/MEDB | 03/11/2023 | 699 | ORIENTAL ENGINEERING CO. | 22.53 | 0 | 0 | 70
4924 | MURSHIDABAD | Murshidabad Division | BADDA AND IT'S ADJOINING MOUJAS , SM/15678 | New | BADDA PWSS under Jal Jeevan Mission of BURWAN Block, Kandi Sub division , Murshidabad District under Murshidabad Division, PHE.Dte. (Part A) | 1866/MURD | 14/07/2023 | 902 | DHIRENDRANATH MONDAL | 344.64 | 304.62 | 88.39 | 10
4925 | MURSHIDABAD | Murshidabad Division | BADDA AND IT'S ADJOINING MOUJAS , SM/15678 | New | BADDA PWSS under Jal Jivan Mission of BURWAN Block, Kandi Subdivision , Murshidabad District under Murshidabad Division, PHE.Dte. (Part B) | 1692/MURD | 28/06/2023 | 1004 | KAMIRUL SK AND CO. (PART: KAMIRUL SK. & OTHERS) | 226.02 | 21.15 | 9.36 | 10
4926 | MURSHIDABAD | Berhampore Mechanical | BADUA AND IT'S ADJOINING MOUJAS , SM/15682 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I and II under Badua ground water based water supply scheme under Block_ Burwan Dist. - Murshidabad under MEDB, PHE Dte. | 3696/MEDB | 03/11/2023 | 92 | ORIENTAL ENGINEERING CO. | 23.45 | 0 | 0 | 0
4927 | MURSHIDABAD | Murshidabad Division | BADUA AND IT'S ADJOINING MOUJAS , SM/15682 | New | Material Requisition To Resource Division | 1219/MURD/33 | 03/05/2023 | 0 | Resource Division | 18.54 | 0 | 0 | 0
4928 | MURSHIDABAD | Murshidabad Division | GAYESPUR AND ADJOINING MOUJAS PWSS , SM/15690 | New | Material Requisition To Resource Division | 1129/MURD/5 | 25/04/2023 | 0 | Resource Division | 13.5 | 0 | 0 | 0
4929 | MURSHIDABAD | Murshidabad Division | GAYESPUR AND ADJOINING MOUJAS PWSS , SM/15690 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at GAYESPUR AND ADJOINING MOUJAS Water Supply Scheme at Head Work Site, 2nd Site site at Khargram Block under Murshidabad Division, P.H. Engineering Dte | 3424/MURD | 02/11/2023 | 21 | NADIA TUBEWELLS | 18.43 | 15.04 | 100 | 100
4930 | MURSHIDABAD | Berhampore Mechanical | GAYESPUR AND ADJOINING MOUJAS PWSS , SM/15690 | New | NEW SERVICE CONNECTION AT PH2 GAYESHPUR ID 304239446 | 305/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 3.78 | 0 | 0 | 0
4931 | MURSHIDABAD | Berhampore Mechanical | GAYESPUR AND ADJOINING MOUJAS PWSS , SM/15690 | New | NEW SERVICE CONNECTION AT PWSS PH1 GAYESHPUR ID 304239445 | 306/WBSEDCL-JJM | 05/02/2024 | 0 | WBSEDCL | 10.95 | 0 | 0 | 0
4932 | MURSHIDABAD | Murshidabad Division | GAYESPUR AND ADJOINING MOUJAS PWSS , SM/15690 | New | Construction of Drain, Laying of UPVC pipeline and road restoration work of Gayespur Water Supply Scheme in Khargram Block of Kandi Sub-Division, under Murshidabad Division, PHE Dte. | 3285/MURD | 16/12/2024 | 30 | DAS ENTERPRISE (SUBRATA DAS) | 38.28 | 0 | 0 | 0
4933 | MURSHIDABAD | Berhampore Mechanical | GAYESPUR AND ADJOINING MOUJAS PWSS , SM/15690 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for GAYESPUR AND ADJOINING MOUJAS PWSS District - Murshidabad. under MEDB, PHE Dte. | 348/MEDB | 10/02/2025 | 89 | M/S SAJAHAN CHOWDHURY | 21.38 | 0 | 0 | 0
4934 | MURSHIDABAD | Murshidabad Division | SUKURIA AND ADJOINING MOUJAS PWSS , SM/15941 | New | Material Requisition To Resource Division | 1936/MURD/4 | 18/07/2023 | 0 | Resource Division | 15.94 | 0 | 0 | 0
4935 | MURSHIDABAD | Berhampore Mechanical | SUKURIA AND ADJOINING MOUJAS PWSS , SM/15941 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under SUKURIA ground water based water supply scheme under Block_ Barwan Dist. - Murshidabad under MEDB, PHE Dte. | 1907/MEDB | 16/06/2023 | 92 | B. T. PROJECTS PVT. LTD. | 22.42 | 0 | 0 | 50
4936 | MURSHIDABAD | Murshidabad Division | SUKURIA AND ADJOINING MOUJAS PWSS , SM/15941 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SUKURIA AND ADJOINING MOUJJAS Water Supply Scheme at Head Work Site, 2nd Site site at Burwan Block under Murshidabad Division, P.H. Engineering Dte | 2634/MURD | 23/08/2023 | 21 | SARKAR WATER SUPPLY AGENCY | 18.43 | 15.44 | 100 | 100
4937 | MURSHIDABAD | Berhampore Mechanical | SUKURIA AND ADJOINING MOUJAS PWSS , SM/15941 | New | NEW SERVICE CONNECTION AT SUKURIA PH II, ID304233502 | 273/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 6.06 | 0 | 0 | 0
4938 | MURSHIDABAD | Berhampore Mechanical | SUKURIA AND ADJOINING MOUJAS PWSS , SM/15941 | New | NEW SERVICE CONNECTION AT SUKURIA PH I, ID 304233761 | 272/WBSEDCL-JJM | 24/01/2024 | 0 | WBSEDCL | 6.22 | 0 | 0 | 0
4939 | MURSHIDABAD | Murshidabad Division | SUKURIA AND ADJOINING MOUJAS PWSS , SM/15941 | New | Laying Distribution System, FHTC of SUKURIA water supply scheme of Burwan Block under Murshidabad Division, PHE Dte. in the District of Murshidabad Part-B | 1032/MURD | 13/04/2023 | 872 | DIPAYAN DEY | 188.8 | 167.11 | 88.51 | 10
4940 | MURSHIDABAD | Murshidabad Division | SUKURIA AND ADJOINING MOUJAS PWSS , SM/15941 | New | Construction of 200 Cum OHR, Pump House Boundwary Wall, , Rising Main Connection, Laying Distribution System of SUKURIA water supply scheme of Burwan Block under Murshidabad Division, PHE Dte. Part-A | 995/MURD | 11/04/2023 | 1086 | APORUPA CONSTRUCTION | 226.95 | 113.24 | 49.9 | 65
4941 | MURSHIDABAD | Murshidabad Division | SUKURIA AND ADJOINING MOUJAS PWSS , SM/15941 | New | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Kandi Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. Board=(89 Nos.) | 2635/MURD | 23/09/2024 | 281 | SABSAMAY | 9.85 | 0 | 0 | 80
4942 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KEYADANGA PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16754 | Augmentation | Material Requisition To Resource Division | 1230/MURD/10 | 04/05/2023 | 0 | Resource Division | 9.94 | 0 | 0 | 0
4943 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED KEYADANGA PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16754 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under KEYADANGA ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | 1915/MEDB | 16/06/2023 | 92 | SUBHRA ENTERPRISE | 21.01 | 14.08 | 67.04 | 15
4944 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KEYADANGA PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16754 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Suti-I & II Block of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Keyadanga, Kishorepore, Bazegazipur ZI-A, Bazegazipur ZI-B, Bazegazipur-II, Water Supply Schemes of Jangipur Sub- Division under Murshidabad Division. | 2713/MURD | 28/08/2023 | 20 | RADIANT | 10.42 | 2.44 | 100 | 100
4945 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KEYADANGA PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16754 | Augmentation | Augmentation of Ground Water Based HAFANIA (ZONE-II) & KEYADANGA PWSS, Block- SUTI-II, District-Murshidabad, Under Murshidabad Division, P.H.Engineering Dte. | 801/MURD | 22/03/2023 | 831 | ATIKUL SAIKH | 367.41 | 70.77 | 67.74 | 100
4946 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED KEYADANGA PWSS IN SUTI - II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/16754 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 30 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for KEYADANGA Ground Based Water Supply Scheme in Suti-II Block under Murshidabad Division , PHE Dte. | 1225/MURD | 28/05/2025 | 60 | M/S . SUKUMAR SINHA | 19.62 | 0 | 0 | 0
4947 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-II & XIII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . , SM/16986 | Retrofitting | Last mile connectivity and providing 1803 nos Funcational House Hold Connection from Zone- II of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte. | 2686/MURD | 25/08/2023 | 120 | AJAY MONDAL | 114.49 | 0 | 0 | 0
4948 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-II & XIII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . , SM/16986 | Retrofitting | Last mile connectivity and providing 5600 nos Functional House Hold Connection from Zone- XIII of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . | 2692/MURD | 25/08/2023 | 120 | M/S. TAPAS KUMAR CHAKRABORTY & CO. | 352.9 | 0 | 0 | 0
4949 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-II & XIII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . , SM/16986 | Retrofitting | Allied work for Construction of Annular Combined Pile Raft Foundation for R.C.C Elevated Reservoir of Capacity 900 CuM of staging height 20 Meter at Head Work site within BANYESWAR(Zone-XIII) W/S Scheme, Block-Sagardighi, District-Murshidabad Under Murshidabad Division P.H.E Dte. | 785/MURD | 14/03/2024 | 60 | BIJAY CHOWDHURY | 84.81 | 76.21 | 89.87 | 85
4950 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-II & XIII )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . , SM/16986 | Retrofitting | Permission for laying pipeline (200 mm dia) along the NH-12 within the utility corridor from Moregram to gangadda of sagardighi surface water based drinking water supply scheme block sagardighi, district-Murshidabad under Murshidabad Division, P.H.E.Dte. | 543-MSD/2023-24 | 16/02/2024 | 0 | CHIEF ENGINEER CIVIL MINISTRY OF ROAD TRANSPORT AND HIGHWAYS KOLKATA | 3.18 | 0 | 0 | 0
4951 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-XIV & XVI )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . , SM/16990 | Retrofitting | Last mile connectivity and providing 6918 nos Functional House Hold Connection from Zone- XIV of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte | 2693/MURD | 25/08/2023 | 120 | M/S GUHA AND ROY | 413.64 | 0 | 0 | 0
4952 | MURSHIDABAD | Murshidabad Division | Retrofitting of Surface Water Based Water Supply Scheme for Balia and its Adjoining Mouzas (Zone-XIV & XVI )to provided last mile connectivity and FHTCs in Murshidabad District under Murshidabad Division PHE Dte . , SM/16990 | Retrofitting | Last mile connectivity and providing 3452 nos Functional House Hold Connection from Zone- XVI of Surface water based BALIA water supply scheme in Sagardighi block under Murshidabad Division PHE Dte . | 2695/MURD | 25/08/2023 | 120 | TEKNO ENTERPRISE | 207.53 | 0 | 0 | 0
4953 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hazi Mahammadpur ground water supply scheme , SM/07227 | Retrofitting | Balance & Allied Work for the work of Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION under command area of Hazi Mahammadpur ground water supply scheme in the district of Murshidabad under Berhampore Division - I, PHE Dte. | 1479/BD-I | 06/09/2024 | 60 | MURSHID ALOM | 11.94 | 0 | 0 | 0
4954 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hazi Mahammadpur ground water supply scheme , SM/07227 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Hazi Mahammadpur ( Habitation ID: 0001294220) in the village of Hazi Mahammadpur (Village code 314231) under Hazi Mahammadpur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | 1048/BD-I | 28/12/2020 | 90 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 32.81 | 30.16 | 100 | 1
4955 | MURSHIDABAD | Berhampore Division I | Retrofitting for Providing Functional Household Tap Connection (FHTC) in connection with JAL JEEVAN MISSION and JAL SWAPNA under command area of Hazi Mahammadpur ground water supply scheme , SM/07227 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area Of village of Dakshin Ashariadaha (Village code 314229) under Hazi Mohammadpur Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. (2nd call for WBPHED/EE/BD-I/NIeT-16 of 2020 ¿ 2021,SL-10) | 76/BD-I | 19/01/2021 | 30 | JIBENDRA NARAYAN SUKUL | 24.9 | 39.42 | 194.76 | 0
4956 | MURSHIDABAD | Berhampore Mechanical | NEZAMPUR PIPED WATER SUPPLY SCHEME. , SM/18185 | New | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Newly Sunk Tube Well in connection to Accommodate FHTC at Pump House No.-I & II under NEZAMPUR ground water based water supply scheme under Block_ SUTI-II Dist. - Murshidabad under MEDB, PHE Dte. | 1930/MEDB | 16/06/2023 | 92 | M/S S. G. ENTERPRISE | 21 | 0 | 0 | 0
4957 | MURSHIDABAD | Murshidabad Division | NEZAMPUR PIPED WATER SUPPLY SCHEME. , SM/18185 | New | Material Requisition To Resource Division | 1230/MURD/19 | 04/05/2023 | 0 | Resource Division | 15.35 | 0 | 0 | 0
4958 | MURSHIDABAD | Murshidabad Division | NEZAMPUR PIPED WATER SUPPLY SCHEME. , SM/18185 | New | NEZAMPUR PWSS to accommodate FHTC, OHR, Pump House Cum Chlorine Room, Laying Distribution System, Rising Main, boundary wall and service road, under Jal Jevan Mission, Suti-II Block of Murshidabad District under Jangipur Sub-Division, Murshidabad Division, | 979/MURD | 10/04/2023 | 723 | M/S. M.S. ENTERPRISE | 207.04 | 9.63 | 4.65 | 30
4959 | MURSHIDABAD | Murshidabad Division | NEZAMPUR PIPED WATER SUPPLY SCHEME. , SM/18185 | New | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NEZAMPUR Water Supply Scheme at Head Work Site, 2nd Site site at Suti - II Block under Murshidabad Division, P.H. Engineering Dte. | 3387/MURD | 01/11/2023 | 21 | TAPAN DAS | 18.56 | 14.94 | 100 | 100
4960 | MURSHIDABAD | Berhampore Mechanical | NEZAMPUR PIPED WATER SUPPLY SCHEME. , SM/18185 | New | NEW CONNECTION AT NEZAMPUR PH-II |  | 13/12/2024 | 0 | WBSEDCL | 4.22 | 0 | 0 | 0
4961 | MURSHIDABAD | Berhampore Mechanical | NEZAMPUR PIPED WATER SUPPLY SCHEME. , SM/18185 | New | NEW CONNECTION AT NEJAMPUR PH-1 | 185/WBSEDCL-JJM | 09/08/2024 | 0 | WBSEDCL | 3.92 | 0 | 0 | 0
4962 | MURSHIDABAD | Berhampore Mechanical | NEZAMPUR PIPED WATER SUPPLY SCHEME. , SM/18185 | New | NEW CONNECTION AT NEZAMPUR PH-1 |  | 02/08/2024 | 0 | WBSEDCL | 3.92 | 0 | 0 | 0
4963 | MURSHIDABAD | Murshidabad Division | NEZAMPUR PIPED WATER SUPPLY SCHEME. , SM/18185 | New | Preparation of DPR for drinking water supply scheme to facilitate 63 Nos (List Enclosed) Uncovered mouzas of Jangipur Sub-Division [Raghunathganj-I, Raghunathganj-II, Suti-I, Suti-II, Farakka, Samserganj Block] which includes Route survey using DGPS/Drone/Total Station etc. & all related field work for technical data collection, Household Survey using PHED developed mobile application, Preparation and supply of Geo reference drawing / layout plan of the zone-wise Command area of water distribution and transmission Pipeline network of the schemes showing all requisite features, design of Pipeline Network. Design (if necessary), drawing & estimation of all necessary structures, Preparation & Submission of DPR booklets & Bid Document ( in both hard and soft copies) including Preparation of Booklet for SLSSC for individual PWSS, all complete in consultation with the EIC under Murshidabad Division P.H.E. Dte. | 3001/MURD | 11/11/2022 | 45 | RADIANT | 253.25 | 3.83 | 100 | 100
4964 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/17850 | Augmentation | Material Requisition To Resource Division | 1210/MURD/09 | 02/05/2023 | 0 | Resource Division | 48.45 | 0 | 0 | 0
4965 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/17850 | Augmentation | Laying of Rising Main, Laying of Distribution System and Overhauling of RCC 180 Cum OHR for Augmentation of HILORA ZONE II Piped Water Supply Scheme in SUTI-I Block in Murshidabad Division, PHE.Dte. | 850/MURD | 24/03/2023 | 1066 | M H SUPPLIERS | 71.55 | 55.99 | 78.24 | 70
4966 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/17850 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II, of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jaykrishnapur Zone- I & Hilora Zone-II Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 1769/MURD | 06/07/2023 | 21 | R.K. DRILLING SERVICES | 18.45 | 18.18 | 100 | 100
4967 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/17850 | Augmentation | Providing FHTC Connection to 1424 nos household, Special repair and renovation of existing 2 (Two) Nos Pump House & Alied Works and Repair of Boundary Wall (140m + 50m) =190 m at T/W-I site & T/W-II site for Augmentation of HILORA ZONE II Piped Water Supply Scheme in SUTI-I Block under Murshidabad Division, PHE.Dte | 849/MURD | 24/03/2023 | 889 | JAMIRUL CONSTRUCTION | 79.6 | 5.1 | 6.41 | 85
4968 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/17850 | Augmentation | Allied work of laying of additional pipeline of 125 mm dia, Land Development, connecting road and construction of soakwell and construction of surface drain of 150 m lenth at Hilora zone 2 PWSS at suti -1 Block under Murshidabad Division, PHE Dte. | 1812/MURD | 20/06/2024 | 587 | M H SUPPLIERS | 53.94 | 0 | 0 | 50
4969 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/17850 | Augmentation | Design, Fabrication, Supplying, Installation, Commissioning & Trial Run of 50 Cum/ Hr. capacity of Iron Elimination Plant (IEP) as per PHED Approved Model (Pressure type) including 1 (one) No. Compressor Room, sludge disposal arrangement with Surface Drain and Platform for HILORA Zone-II Ground Based Water Supply Scheme in Suti-I Block under Murshidabad Division, PHE Dte. | 1224/MURD | 28/05/2025 | 60 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 23.01 | 0 | 0 | 0
4970 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/17850 | Augmentation | Laying Distribution System and Road Restoration of Hilora Zone-II PWSS in Suti-I Block , Jangipur Sub-Division under Murshidabad Division,PHE.Dte. | 1332/MURD | 10/06/2025 | 60 | PARTHA PRATIM DAS | 22.91 | 0 | 0 | 0
4971 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/17850 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 13(Thirteen) Nos existing commissioned PWSS of Suti-I & Suti-II Block under Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. PART-B | 1215/MURD | 10/05/2022 | 30 | RADIANT | 73.97 | 3.23 | 100 | 100
4972 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/17850 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under HILORA ground water based water supply scheme under Block_ SUTI-I Dist. - Murshidabad under MEDB, PHE Dte. | 1914/MEDB | 16/06/2023 | 899 | JOGMAYA ENGINEERING | 21.42 | 18.16 | 90.69 | 20
4973 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED HILORA- II PWSS IN SUTI - I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER MURSHIDABAD DIVISION , PHE DTE. , SM/17850 | Augmentation | Sinking of 01 (One) Nos of 300mm x 200 mm dia tube well,120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at HILORA - II & KOHETPUR Water Supply Scheme at Head Work Site under Murshidabad Division, P.H. Engineering Dte. | 1755/MURD | 13/06/2024 | 464 | R.K. DRILLING SERVICES | 11.79 | 0 | 0 | 100
4974 | MURSHIDABAD | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/18732 | Augmentation | Material Requisition To Resource Division | 1210/MURD/14 | 02/05/2023 | 0 | Resource Division | 241.41 | 0 | 0 | 0
4975 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/18732 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II , III ,IV & V ,Zone-II under SHIBNAGAR LASKARPUR ground water based water supply scheme under Block_ Domkal Dist. - Murshidabad under MEDB, PHE Dte. | 4305/MEDB | 29/12/2023 | 91 | HARA PROSAD DAS | 55.57 | 25.87 | 46.55 | 5
4976 | MURSHIDABAD | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/18732 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Shibnagar Laskarpur (Zone - II ) Water Supply Scheme at Head Work Site, 2nd Site, 3 r d site at Domkal Block under Murshidabad Division, P.H. Engineering Dte. | 2701/MURD | 25/08/2023 | 21 | MAMATA USHA ENTERPRISE | 35.37 | 32.1 | 100 | 95
4977 | MURSHIDABAD | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/18732 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 11(Eleven) nos existing commisioned PWSS Domkol Block of Islampur Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Jitpur Zone-II, PT Rasulpur Zone-I Part-B, Shib Nagar Laskarpur Zone-I Part-B, Zone-II, Aminabad Zone-II, Garibpur Zone-I Part-B, Juranpur Part-B, Domkol Zone-I Part-B, Zone-II Part-A, Zone-II Part-B, Zone-III Water Supply Schemes of Islampur Sub- Division under Murshidabad Division. | 2791/MURD | 04/09/2023 | 20 | MERCHANDISE-INDIA | 26.8 | 4.43 | 100 | 100
4978 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/18732 | Augmentation | NEW CONNECTION SHIBNAGAR LASKARPUR Z-II PH-II | 436/WBSEDCL-JJM | 13/03/2024 | 0 | WBSEDCL | 6.64 | 0 | 0 | 0
4979 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/18732 | Augmentation | NEW CONNECTION SHIBNAGAR LASKARPUR Z-II PH-I | 435/WBSEDCL-JJM | 13/03/2024 | 0 | WBSEDCL | 3.81 | 0 | 0 | 0
4980 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/18732 | Augmentation | NEW CONNECTION SHIBNAGAR LASKARPUR Z-II PH-III | 437/WBSEDCL-JJM | 13/03/2024 | 0 | WBSEDCL | 6.16 | 0 | 0 | 0
4981 | MURSHIDABAD | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/18732 | Augmentation | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II) under Jal Jeevan Mission of DOMKAL Block in the District Murshidabad District under Murshidabad Division, PHE. Dte. | 4005/MURD | 28/12/2023 | 735 | M/S. BIMAL MISRA | 838.96 | 0 | 0 | 35
4982 | MURSHIDABAD | Murshidabad Division | Augmentation of Shibnagar Laskarpur Piped Water Supply Scheme (Zone-II )Domkal Block in Murshidabad District under Murshidabad Division , PHE Dte. , SM/18732 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gaysabad, Kagram, Ranagram, Augmentation of Islampur & Augmentation of Shibnagar Laskarpur Zone - II Water Supply Scheme under Murshidabad Division, P.H.Engineering Dte. | 661/MURD | 19/03/2025 | 170 | M/S GUHA AND ROY | 35.27 | 0 | 0 | 100
4983 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. , SM/18364 | Augmentation | Material Requisition To Resource Division | 1167/MURD/19 | 28/04/2023 | 0 | Resource Division | 22.34 | 0 | 0 | 0
4984 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. , SM/18364 | Augmentation | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 03(Three) nos existing commisioned PWSS Block Nabagram of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Amarkundu Water Supply Scheme, Nabagram Zone-I & II Water Supply Scheme, Panchgram Water Supply Scheme. (Annexure-II) | 1929/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 7.92 | 2.04 | 99.48 | 100
4985 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. , SM/18364 | Augmentation | Preparation of D.P.R Consultancy work Augmentation in connection with the Functional House Hold TapConnection of 04(Four) nos existing commisioned PWSS Block Bhagawangola-I & Lalgola of LALBAGH SUB-DIVISION under Murshidabad Division P.H.E. Dte. Name of Schemes-Habaspur Water Supply Scheme, Bhandara Water Supply Scheme, Kantanagar Water Supply Scheme, Lalgola Water Supply Scheme. (Annexure-II) | 1928/MURD | 19/07/2022 | 928 | ENVIROTECH SOLUTIONS | 8.78 | 0.43 | 20.7 | 100
4986 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. , SM/18364 | Augmentation | Laying of Rising main , Distribution System, FHTC, construction of OHR (Capacity 400 cum), Repairing of existing OHR, Sinking of Tube Well , Repairing of pump house and boundary wall, and Construction of Pump house cum chlorine Room , Boundary wall and approach road for Augmentation of Habaspur PWSS in Bhagwagola- I Block, Murshidabad District under under Jal Jeevan Mission under Murshidabad Division, PHE.Dte. | 3516/MURD | 09/11/2023 | 1239 | M/S. GOUTAM CHAKRABORTY | 717.52 | 322.44 | 44.94 | 10
4987 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. , SM/18364 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 14 (fourteen) nos existing commisioned PWSS Bhagwangola, Nabagram, Lalgola Block of Lalbagh Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes- Amarkundu, Bhandara zone-I, Bhandara zone-II, Habaspur, Kanta nagar Nabagram Zone-I , Nabagram Zone-II , Panchgram Zone-I, Panchgram Zone-II,Panchgram Zone-III, Lalgola Zone-I, Lalgola Zone-II, Lalgola Zone-III , Lalgola Zone-IV Water Supply Schemes of Lalbagh Sub- Division under Murshidabad Division | 2792/MURD | 04/09/2023 | 515 | ENVIROTECH SOLUTIONS | 39.85 | 4.43 | 100 | 100
4988 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR HABASPUR BLOCK- BHAGAWANGOLA-I , DISTRICT - MURSHIDABAD. , SM/18364 | Augmentation | Fabrication and errection of display board including vinyl pasting (1200 mm x 900 mm) of scheme information under JJM at different places under Lalbagh Sub-Division within the scheme area under Murshidabad Division, P.H.E.Dte. | 2638/MURD | 23/09/2024 | 251 | ARJU CONSTRUCTION | 6.14 | 0 | 0 | 40
4989 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F , SM/08113 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-I) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | 85/ BD-I | 20/01/2021 | 180 | FNC CONSTRUCTION AND CO. | 132.44 | 8.34 | 33.68 | 1
4990 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F , SM/08113 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Beniagram Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | 2228/BD-I | 15/12/2021 | 90 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 71 | 68.22 | 100 | 1
4991 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F , SM/08113 | Retrofitting | Material Requisition To Resource Division | 145/BD-I | 10/02/2022 | 0 | Resource Division | 18.66 | 0 | 0 | 0
4992 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F , SM/08113 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Beniagram (Village code 313832) under Beniagram Water Supply Scheme of Farakka Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-05) | 2011/BD-I | 08/11/2021 | 180 | M/S S.DAS & ENTERPRISE | 162.77 | 0 | 0 | 1
4993 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F , SM/08113 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chauki, Kashinagar, Samaspur & Imamnagar (Village code 313803, 313806, 313810 & 313815) under Beniagram Water Supply Scheme of Farakka Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-07) | 2050/BD-I | 17/11/2021 | 900 | DOBAY CONSTRUCTION | 142.86 | 118.84 | 83.19 | 80
4994 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F , SM/08113 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub Division, PHE Dte. period for 01.01.2024 to 31.12.2024. | 1281/BD-I | 27/12/2023 | 366 | TARUN KUMAR BHATTACHARYA | 1.81 | 3.94 | 217.28 | 33
4995 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F , SM/08113 | Retrofitting | Relaying of different dia UPVC Pipe line in connection with JJM (Jal Jeevan Mission) over damaged portion and Interconnection between over flow line and Delivery Line at Beniagram Zone-II OHR Site under Beniagram Surface Based water supply scheme of Zone-II of Murshidabad District under Berhampore Division-I PHE Dte. | 90/BD-I | 03/05/2023 | 30 | BABAI GHOSH | 3.05 | 3.01 | 100 | 100
4996 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F , SM/08113 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under Beniagram & its adjoining Mouzas Surface Water based Water Supply Scheme of Farakka Block in Murshidabad District under Berhampore Division-I, PHE Dte. | 439/BD-I | 12/07/2023 | 90 | CHAND ENTERPRISE | 2.32 | 2.15 | 100 | 100
4997 | MURSHIDABAD | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Beniagram & Its Adjoining Mouzas Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Under F , SM/08113 | Retrofitting | Rejuvenation of of 7.8 MLD Capacity Water Treatment Plant (Inlet well ,Flush Mixture ,Clarifoculator, Chemical Dosing and Filter House ) at Beniagram Under Berhampore Division - I , In The District Murshidabad , PHE Dte . | 117/BD-I | 30/01/2024 | 60 | P.M CONSTRUCTION | 144.24 | 0 | 0 | 10
4998 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18688 | Augmentation | Development of land at Head Work Site of Bahara Water Supply Scheme under Kandi Sub-Division, P.H.Engg. Dte. in the District of Murshidabad. | 375/KSD | 19/01/2022 | 30 | ROY ENTERPRISE | 4.53 | 0 | 0 | 100
4999 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18688 | Augmentation | Material Requisition To Resource Division | 1004/MURD/9 | 11/04/2023 | 0 | Resource Division | 95.05 | 0 | 0 | 0
5000 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18688 | Augmentation | Material Requisition To Resource Division | 1043/MURD/8 | 17/04/2023 | 0 | Resource Division | 95.05 | 0 | 0 | 0
5001 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18688 | Augmentation | Laying Distribution System (PART-B), FHTC work at Dohalia Village (Village Code-315294), Baje Dohalia Village (Village Code-315293) & Bhandira Village (Village Code-315292) for Augmentation of of BAHARA Ground water based Piped water supply scheme in KANDI Block under Murshidabad Division, PHE.Dte | 2462/MURD | 09/08/2023 | 150 | M/S.S.S. ENTERPRISE | 215.67 | 68.93 | 31.96 | 20
5002 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18688 | Augmentation | Material Requisition To Resource Division | MURD/439/06 | 08/02/2024 | 0 | Resource Division | 4.9 | 0 | 0 | 0
5003 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18688 | Augmentation | Construction 200 Cum OHR, Laying Distribution System Part-A, FHTC at Brahmanpara Village (Village Code-315290), Bahara Village (Village Code-315291) & Bhandira Village (Village Code-315292), Repairing of Existing Pump house (H.W), Boundary Wall, Existing OHR for Augmentation of BAHARA Ground water based Piped water supply scheme in KANDI Block under Murshidabad Division, PHE. Dte Part-A | 2463/MURD | 09/08/2023 | 1180 | ROY ENTERPRISE | 182.7 | 78.67 | 43.06 | 21
5004 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18688 | Augmentation | Preparation of D.P.R Consultancy work Augmentation/Augmentation with Retrofitting in connection with the Functional House Hold TapConnection of 29(Twenty Nine) nos existing commisioned PWSS Kandi, Burwan, Khargram, Bharatpur-I & II Block of Kandi Sub-Division under Murshidabad Division P.H.E. Dte. Name of Schemes-Bahara, Mahalandi Zone-I, Zone-II, Bhalkundi Zone-I, Zone-II, Zone-III, Bele,Nagar Zone-I, Zone-II, Bharatpur Zone-I(A), Zone-I(B), Zone-II(A), Zone-II(B), Dakshinkanda Zone-IA, Zone-IB, Zone-II, Kagram,Tenya Zone-I, Zone-II, Zone-III, Salar Zone-IA, Zone-IB, Zone-IIA, Zone-IIB, Panchthupi Zone-I, Zone-II, Zone-III, Burwan Zone-I, Zone-II Water Supply Schemes of Kandi Sub- Division under Murshidabad Division. | 2789/MURD | 04/09/2023 | 605 | GEOTECHNICAL ENGINEERS CONSORTIUM (PROP:MANASIJ DUTTA) | 74.87 | 10.81 | 101.05 | 75
5005 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18688 | Augmentation | Construction of Valve Chamber, M.S Gate, Laying Distribution System of UPVC Pipeline for Augmentation of Kamalakantapur / Bahara Water Supply Scheme in Bharatpur- I Block, of Kandi Sub-Division under Murshidabad Division, P.H.Engineering Dte. | 3148/MURD | 03/12/2024 | 45 | ABDUL ENTERPRISE | 45.91 | 0 | 0 | 0
5006 | MURSHIDABAD | Berhampore Mechanical | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18688 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under BAHARA ground water based water supply scheme under Block_ KANDI Dist. - Murshidabad under MEDB, PHE Dte. | 760/MEDB | 20/02/2024 | 90 | M/S SAJAHAN CHOWDHURY | 36.36 | 0 | 0 | 25
5007 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18688 | Augmentation | Construction of Boundary wall at 1st Tubewell site of Khasra PWSS & Bahara PWSS of Kandi Block in Kandi Sub-Division under Murshidabad Division, PHE. Dte. | 3214/MURD | 09/12/2024 | 266 | MUNNA AGROTECH ENTERPRISE ( PRO: MIRAJUL ISLAM) | 12.9 | 0 | 0 | 5
5008 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18688 | Augmentation | Design, Drawing, Fabrication, Erection Iron Elimination Plant (IEP) of 45 m3/hr & 40m3/hr Capacity as per Departmental approved model including comossing trial run (3months) of 2 nos Construction of Blower Room (H.W.Site), Pump House (3rd Site), Boundary Wall (3rd Site), Laying of UPVC Pipe of Bahara Water Supply Scheme in Kandi Block of Kandi Sub Division, under Murshidabad Division P.H.E.Dte. | 190/MURD | 21/01/2025 | 420 | ANIRUDDHYA BOSE | 94.01 | 0 | 0 | 30
5009 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18688 | Augmentation | Sinking of 02 (Two) Nos of 300 mm x 200 mm dia tube well i.e. TW-II,III of 90.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Bahara & adjoining mouzas Water Supply Scheme at 2nd & 3 r d Site at K a n d i Block under Murshidabad Division, P.H. Engineering Dte. | 2679/MURD | 24/08/2023 | 586 | HARUN ALL RASHID & BROTHERS | 21.15 | 0 | 0 | 60
5010 | MURSHIDABAD | Murshidabad Division | Augmentation of Bahara Piped Water Supply Scheme Block - Kandi, Dist- Murshidabad. , SM/18688 | Augmentation | Sinking of 02 (Two) Nos of 250mm x 150 mm dia tube well i.e. TW-I, II of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PUNRAPARA, Augmentation of Bahara & Pacchipara Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 2587/MURD | 21/08/2023 | 438 | INDRAJIT MAZUMDAR | 18.43 | 0 | 0 | 60
5011 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/18444 | Augmentation | Providing FHTC to 2516 nos. household for Augmentation work of Teghari (Zone-I) PWSS(PART-A) in Raghunathganj-II Block under Murshidabad Division, PHE. Dte. | 2022/MURD | 25/07/2023 | 180 | ARABINDA GHOSH | 124.91 | 0 | 0 | 0
5012 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/18444 | Augmentation | Preparation of D.P.R Consultancy work ( Augmentation/With Retrofitting/Retrofitting Only) in connection with the Functional House Hold Tap Connection of 10(Ten) Nos existing commissioned PWSS of Jangipur Sub-Division under Murshidabad Division P.H.E. Dte. | 287/MURD | 03/02/2022 | 60 | STEELCONC AND ASSOCIATES | 81.43 | 4.31 | 100 | 100
5013 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/18444 | Augmentation | Material Requisition To Resource Division | 1167/MURD/52 | 28/04/2023 | 0 | Resource Division | 115.2 | 0 | 0 | 0
5014 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/18444 | Augmentation | Allied work for Repairing & Renovation of 800 Cum Capacity and 20 mtr staging height R.C.C. Elevated Reservoir & construction of surface drain for Augmentation work of TEGHARI (Zone-I) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E. Dte. in the district of Murshidabad. | 819/MURD | 15/03/2024 | 60 | BABUSONA CONSTRUCTION | 10.9 | 0 | 0 | 0
5015 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/18444 | Augmentation | Allied work for vertical extension of head works site boundary wall , Reinforced Barbed Tape (R.B.T) Concertina fencing on Boundary wall top and construction of Wash out pipe line from OHR to pond of Teghari Water Supply Scheme of Raghunathganj-II Block under Murshidabad Division, PHE Dte. | 2409/MURD | 07/08/2023 | 30 | MOLLA ENTERPRISE | 9.43 | 9.21 | 100 | 100
5016 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/18444 | Augmentation | Laying of Distribution System for Augmentation work of Teghari (Zone-I) PWSS (PART-B) in Raghunathganj-II Block under Murshidabad Division , PHE. Dte. | 1995/MURD | 21/07/2023 | 180 | M/S. CHOWDHURY CONSTRUCTION | 112.17 | 58.42 | 52.08 | 20
5017 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/18444 | Augmentation | Providing FHTC to 2500 nos household for Augmentation work of Teghari (Zone-I) PWSS (PART-B) in Raghunathganj-II Block under Murshidabad Division, PHE.Dte. | 2756/MURD | 01/09/2023 | 845 | DEBASIS BOSE | 124.54 | 0 | 0 | 30
5018 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/18444 | Augmentation | Allied works for Laying of Rising Main & Distribution System (Part-B) of TEGHARI (ZONE-I) Water Supply Scheme of Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | 192/MURD | 21/01/2025 | 60 | SUMAN CHOWDHURY | 43.88 | 0 | 0 | 0
5019 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/18444 | Augmentation | Allied work for Renovation of Pump House and Boundary Wall at 2nd Site of Teghari (Zone-I) Water Supply Scheme under Jangipur Sub Division, P.H.E. Dte. in the district of Murshidabad. | 828/MURD | 15/03/2024 | 30 | NIRMAN ENTERPRISE | 5.29 | 0 | 0 | 0
5020 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/18444 | Augmentation | Allied work of Repair & Renovation of Pump House and Boundary Wall at Head Work Site of Teghari (Zone-I) Water Supply Scheme under Jangipur Sub Division, P.H.E.Dte. in the district of Murshidabad. | 2014/MURD | 11/07/2024 | 444 | AZAD ENTERPRISE | 17.13 | 0 | 0 | 80
5021 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/18444 | Augmentation | Allied works for Laying of Rising Main & Distribution System (Part-A) of TEGHARI (ZONE-I) Water Supply Scheme of Raghunathgani-II Block in Jangipur Sub Division under Murshidabad Division, P.H.E.Dte. | 2908/MURD | 29/10/2024 | 154 | RIDAUAN ENTERPRISE | 55.78 | 0 | 0 | 60
5022 | MURSHIDABAD | Berhampore Mechanical | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/18444 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD under MEDB, PHE Dte. | 384/MEDB | 12/02/2025 | 89 | CHOWDHURY & BASU ENTERPRISE | 45.46 | 0 | 0 | 0
5023 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/18444 | Augmentation | Sinking of 03 (Three) Nos of 300mm x 200 mm dia tube well i.e. TW-I, II, III of 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at TEGHARI ZONE - I, MAHESAIL ZONE-III & SERPUR (CT) Water Supply Scheme under Murshidabad Division, P.H. Engineering Dte. | 2407/MURD | 07/08/2023 | 552 | NADIA TUBEWELLS | 35.34 | 0 | 0 | 100
5024 | MURSHIDABAD | Murshidabad Division | AUGMENTATION OF TEGHARI ZONE-I PIPED WATER SUPPLY SCHEME BLOCK RAGHUNATHGANJ -II DISTRICT MURSHIDABAD. , SM/18444 | Augmentation | Laying of Distribution System and Overhauling of R.C.C. elevated reservoir 800 Cum capacity of staging height 20 mtr for Augmentation work of Teghari (Zone-I) PWSS (PART-A) in Raghunathganj-II Block under Murshidabad Division, PHE.Dte. | 1994/MURD | 21/07/2023 | 626 | BABUSONA CONSTRUCTION | 100.73 | 52.95 | 52.58 | 30
5025 | MURSHIDABAD | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Murshidabad District Under Murshidabad Division (16 nos) Block , SM/09856 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Murshidabad. | 5773/RS | 09/11/2022 | 365 | IMAGIN | 497.97 | 333.41 | 100 | 75
5026 | MURSHIDABAD | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En , SM/13045 | Support-WQMSP | Transfer of fund for ASHA in connection with WQ Testing of Drinking Water Sample using Field Testing Kit (FTK). Ref Memo No - HFW-27099/408/2022-MSD. MB NO - 7068 | 407-MSD/22-23 | 23/11/2022 | 0 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 25.5 | 0 | 0 | 0
5027 | MURSHIDABAD | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En , SM/13045 | Support-WQMSP | Printing and supply of 20572 nos. FTK data sheet at sub-district water testing laboratories of Murshidabad on A4 size good quality paper (GSM75) as per format supply by the department for the purpose of water sample data collection by ASHA Workers. To be engaged in gram panchayat under different block for testing of water samples through FTK under Murshidabad Division, PHE Dte.(Soft copy of printing material will be supplied by the office). | 343/HQ | 29/12/2022 | 10 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 0.98 | 0.98 | 100 | 100
5028 | MURSHIDABAD | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En , SM/13045 | Support-WQMSP | Water Quality test by FTK and data uploading to water quality dashboard of School & Anganwadi Centres w.r.t." Swachh Jal se Surakhha" campaign in Kandi Sub-Division under Murshidabad Division, PHE Dte. | 1941/MURD | 18/07/2023 | 15 | M/S BAPPA ENTERPRISE | 3.29 | 3.14 | 100 | 100
5029 | MURSHIDABAD | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En , SM/13045 | Support-WQMSP | Water Quality test by FTK and data uploading to water quality dashboard of School & Anganwadi Centres w.r.t." Swachh Jal se Surakhha" campaign in Jangipur Sub-Division under Murshidabad Division, PHE Dte. | 1937/MURD | 18/07/2023 | 15 | M/S BAPPA ENTERPRISE | 4.72 | 4.38 | 100 | 100
5030 | MURSHIDABAD | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En , SM/13045 | Support-WQMSP | Water Quality test by FTK and data uploading to water quality dashboard of School & Anganwadi Centres w.r.t." Swachh Jal se Surakhha" campaign in Berhampore Sub-Division under Murshidabad Division, PHE Dte. | 1938/MURD | 18/07/2023 | 15 | M/S BAPPA ENTERPRISE | 3.66 | 3.5 | 100 | 100
5031 | MURSHIDABAD | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En , SM/13045 | Support-WQMSP | Water Quality test by FTK and data uploading to water quality dashboard of School & Anganwadi Centres w.r.t." Swachh Jal se Surakhha" campaign in Islampur Sub-Division under Murshidabad Division, PHE Dte. | 1939/MURD | 18/07/2023 | 15 | M/S BAPPA ENTERPRISE | 1.97 | 1.91 | 100 | 100
5032 | MURSHIDABAD | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En , SM/13045 | Support-WQMSP | Water Quality test by FTK and data uploading to water quality dashboard of School & Anganwadi Centres w.r.t." Swachh Jal se Surakhha" campaign in Lalbagh Sub-Division under Murshidabad Division, PHE Dte. | 1940/MURD | 18/07/2023 | 15 | M/S BAPPA ENTERPRISE | 3.49 | 2.96 | 100 | 100
5033 | MURSHIDABAD | Murshidabad Division | Drinking water sample collection & testing through Field Test Kits (FTKs) & up loading charges for the same related to water Quality Monitoring & Surveillance Programme Under Jal Jeevan Mission in the district Murshidabad under Murshidabad Division P.H.En , SM/13045 | Support-WQMSP | Uploading, Development upgradation of all FTK phase-II collected & tested data and special features along with reorientation of PHED WQ Dashboard, Murshidabad Division, PHE Dte. | 3145/MURD | 03/12/2024 | 241 | M/S. S.S. ENTERPRISE (SANTU GHOSH) | 5.2 | 0 | 0 | 100
5034 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Maintenance & Servicing of Computer & its accessories and Laboratories maintenance (Sweeping & Cleaning)of 9 numbers sub district water testing laboratories under Murshidabad Division. P.H. Engineering Dte. 4,C.R.Das Road Berhampore, Murshidabad. for 12(Twelve) months (Period from 03-11-2021 to 02-11-2022) | 270/HQ | 03/11/2021 | 12 | A.S. COMPUTER | 4.84 | 4.84 | 100 | 0
5035 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Chemical, glassware & instrumments requirment for NABL accreditation at Murshidabad District Water Testing Laboratory as per ISO/IEC: 17025: 2017 under Murshidabad Division, PHE Dte. in the district of Murshidabad. | 2728/MURD | 03/09/2021 | 10 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 14.36 | 1.49 | 100 | 0
5036 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking Water Quality Testing Monitoring & Surveillance programme in State of West Bengal under Murshidabad Division, P.H.E.Dte. ( For Six months) | 340/MURD | 10/02/2022 | 15 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 2.9 | 2.9 | 100 | 0
5037 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents & Glassware to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking Water Quality Testing Monitoring & Surveillance programme in State of West Bengal under Murshidabad Division, P.H.E.Dte. ( For Six months) | 443/MURD | 18/02/2022 | 15 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 3.89 | 3.88 | 100 | 0
5038 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Maintenance & servicing of Computer and Computer accessories of 10 nos Old Water Testing Laboratories(Sub District Laboratories -03 nos. NGO Managed Laboratories- 06 and District Water Testing Laboratories) and supply of 10 nos UPS 600 VA under the Office of the Executive Engineer , Murshidabad Division , P.H. Engineering Dte. 4, C.R.Das Road Berhampore, Murshidabad. for. 12(Twelve) months . | 367-MSD/22-23 | 21/10/2022 | 0 | ARINDAM MAJUMDAR | 1.44 | 0 | 0 | 0
5039 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | ASDFA |  | 04/11/2022 | 0 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 2.9 | 0 | 0 | 0
5040 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | PROVIDE THE ELECTRICFICATION OF SALAR SUB DISTRICT LAB, TNO- 10/2022-23/AEHQ | 383-MSD/22-23 | 23/10/2022 | 0 | ARINDAM MAJUMDAR | 2.35 | 0 | 0 | 0
5041 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | SUPPLYING & DELIVERY OF LAB EQUIPMENTS FOR WT LAB INCLUDING DELIVERY OF CHEMICALS OF SURFACE WATER SUPPLY OF JIAGANJ AZIMGANJ & ITS ADJ MOUJAS. | 368-MSD/22-23 | 21/10/2022 | 0 | A.S. COMPUTER | 1.86 | 0 | 0 | 0
5042 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents and Glassware to Murshidabad District Water Testing Laboratory for AAS Operation under Murshidabad Division, P.H.E. Dte. | 2536/MURD | 30/09/2020 | 31 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.17 | 2.45 | 58.83 | 10
5043 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Supply & delivery of Reagents & Consumables for On-Site Mobile Analysis System for Murshidabad district of West Bengal as per scope and direction of EIC under Public Health Engineering Department, Government of West Bengal. | 80/HQ | 15/02/2022 | 30 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT LTD. | 4.98 | 4.98 | 100 | 0
5044 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | CARRYING REFERRAL WATER SAMPLES TO STATE LABORATORY. | 259-MSD/2023-24 | 19/09/2023 | 0 | M/S. DIPTI ENTERPRISE | 0.07 | 0 | 0 | 0
5045 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Repairing & Renovation work of Jangipur Sub District Laboratory building under Murshidabad Division P.H.E Dte. | 562/MURD | 28/02/2023 | 20 | SARKAR BROTHERS | 5.62 | 5.53 | 98.39 | 0
5046 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents & Glassware to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking Water Quality Testing Monitoring & Surveillance programme in State of West Bengal under Murshidabad Division, P.H.E.Dte. ( For Six months) | 113/MURD | 13/01/2023 | 20 | M/S LAXMI ENTERPRISE | 14.84 | 14.84 | 100 | 100
5047 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking Water Quality Testing Monitoring & Surveillance programme in State of West Bengal under Murshidabad Division, P.H.E.Dte. ( For Six months) | 112/MURD | 13/01/2023 | 20 | M/S LAXMI ENTERPRISE | 10.84 | 10.84 | 100 | 100
5048 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Supply & delivery of water quality parameter testing Chemicals, Reagents, Consumables & Glassware for 19 (Nineteen) laboratories for the period of 6 months under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 440/MURD | 08/02/2024 | 30 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 46.07 | 46.07 | 100 | 100
5049 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Carrying WTP water sample to Kalyani State Referral Laboratory for Pesticide testing and analysis through GCMS | 500-MSD/2023-24 | 17/01/2024 | 0 | M/S. DIPTI ENTERPRISE | 0.02 | 0 | 0 | 0
5050 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Carrying referral water samples to state laboratory | 506-MSD/2023-24 | 21/01/2024 | 0 | M/S. DIPTI ENTERPRISE | 0.06 | 0 | 0 | 0
5051 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Continuation work order for Sample collection form different AIRP & CPP at different Blocks in the District of Murshidabad under Murshidabad Division, P.H.Engineering Dte. for the period of 01-11-2022 to 30-10-2023 | 2904/MURD | 28/10/2022 | 365 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 2.36 | 2.17 | 91.75 | 92
5052 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents & Glassware to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking Water Quality Testing Monitoring & Surveillance programme in State of West Bengal under Murshidabad Division, P.H.E.Dte. ( For Six months) | 115/MURD | 13/01/2023 | 20 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 3.36 | 3.36 | 100 | 100
5053 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking Water Quality Testing Monitoring & Surveillance programme in State of West Bengal under Murshidabad Division, P.H.E.Dte. ( For Six months) | 111/MURD | 13/01/2023 | 20 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 28.05 | 28.05 | 100 | 100
5054 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents & Glassware to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking Water Quality Testing Monitoring & Surveillance programme in State of West Bengal under Murshidabad Division, P.H.E.Dte. ( For Six months) | 114/MURD | 13/01/2023 | 20 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 10.06 | 10.06 | 100 | 100
5055 | MURSHIDABAD | Murshidabad Division | Procurement of Chemicals , Consumables , Glassware and Annual Maintenance contact (AMC) of computers and its peripherals etc. Required for smooth running of the different laboratories under Murshidabad Division P.H.E , Dte. , SM/12985 | Support-WQMSP | Supply & delivery of water quality parameter testing Chemicals, Reagents, Consumables & Glassware for 19 (Nineteen) laboratories for the period of 6 months under Murshidabad Division, PHE Dte. in the District of Murshidabad. | 430/MURD | 07/02/2024 | 30 | M/S LAXMI ENTERPRISE | 27.17 | 7.19 | 20.94 | 100
5056 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | CLAIM REMUNERATION 01/07/23 TO 31/08/2023 | 419-MSD/2023-24 | 07/12/2023 | 0 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.9 | 0 | 0 | 0
5057 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the period 01/06/2023 to 31/08/2023. | 421-MSD/2023-24 | 07/12/2023 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 1.7 | 0 | 0 | 0
5058 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | REIMBURSEMENT OF 2ND INSTALLMENT OF LAB 2023 | 419-MSD/2023-24 | 07/12/2023 | 0 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.4 | 0 | 0 | 0
5059 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of September 2023. | 418-MSD/2023-24 | 07/12/2023 | 0 | R.N CLUB LAB | 0.45 | 0 | 0 | 0
5060 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/08/2023 to 30/09/2023. | 420-MSD/2023-24 | 07/12/2023 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.9 | 0 | 0 | 0
5061 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the period July 2023 to August 2023. | 418-MSD/2023-24 | 07/12/2023 | 0 | R.N CLUB LAB | 0.9 | 0 | 0 | 0
5062 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of October 2023 | 418-MSD/2023-24 | 07/12/2023 | 0 | R.N CLUB LAB | 0.45 | 0 | 0 | 0
5063 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/07/2023 to 31/07/2023 | 420-MSD/2023-24 | 07/12/2023 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.45 | 0 | 0 | 0
5064 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/09/2023 to 30/09/2023. | 421-MSD/2023-24 | 07/12/2023 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
5065 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | CLAIM REMUNERATION 01/09/23 TO 30/09/23 | 419-MSD/2023-24 | 07/12/2023 | 0 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.45 | 0 | 0 | 0
5066 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Engagement of 01 no. Computer Operator / Data Entry Operator / Customer Service Cell Manager with certificate in computer application on contractual Basis through Agency for District Water Testing Laboratory under the Office of the Executive Engineer, Murshidabad Division, P.H.Engineering Dte. For a period of 12 months.(i.e. 01.02.2024 to 31.01.2025) | 353/MURD | 31/01/2024 | 365 | RIZZ ENTERPRISE | 2.25 | 0.8 | 35.37 | 5
5067 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Continuation work order for Engagement of Resource Person & Sampling Assistant at the Laboratory Site to Operate AAS Spectrophotometer System for a Period of One Year under Murshidabad Division, PHE Dte. in the district of Murshidabad. (Period from 15/10/2020 to 14/10/2021) | 2625/MURD | 08/10/2020 | 365 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.54 | 4.54 | 100 | 100
5068 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Continuation work order for Engagement of Resource Person & Sampling Assistant at the Laboratory Site to Operate AAS Spectrophotometer System for a Period of One Year under Murshidabad Division, PHE Dte. in the district of Murshidabad. (Period from 15/10/2021 to 14/04/2022) | 3361/MURD | 11/10/2021 | 182 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 2.56 | 2.41 | 100 | 100
5069 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Continuation work order for Engagement of Resource Person & Sampling Assistant at the Laboratory Site to Operate AAS Spectrophoto meter System for a Period of 06(Six) Months under Murshidabad Division, PHE Dte. in the district of Murshidabad. (Period from 15/04/2022 to 14/09/2022) | 925/MURD | 11/04/2022 | 183 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 2.56 | 0 | 0 | 100
5070 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Engagement of 07(Seven) nos. Chemist (01 no. District Laboratory and 06nos. Sub-District Laboratory) , 06(Six)nos.Bacteriologist(01 no. District Laboratory and 05nos. Sub-District Laboratory), 11(Eleven)nos. Lab Assitant(01 no. District Laboratory and 10nos. Sub-District Laboratory) and 10(Ten)nos. Sampling Assistant(01 no. District Laboratory and 09nos. Sub-District Laboratory) in each of 11(Eleven) nos. District & Sub-District Water Testing Laboratories under Murshidabad Division, P.H.Engineering Dte. for 01(One) year. (i.e. period form 01/03/2023 to 28/02/2024) | 455/MURD | 17/02/2023 | 365 | CLIFFORD FACILITY SERVICES PVT. LTD. | 82.31 | 63.65 | 100 | 100
5071 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Arrear salary and arrear festival bonus for Chemist, Bacteriologist, Lab- Assistant and Sampling- Assistant of NABL Accredited/Recognized District and Sub-District Water testing Laboratories for January and February 2023 under Murshidabad Division, PHE Dte.(The details of personnel are attached as annexure -B) | 3714/MURD | 05/12/2023 | 15 | S. DUTTA | 4.14 | 4.14 | 100 | 100
5072 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Allied work for Electrification in Murshidabad District Laboratory at Berhampore Under Murshidabad Division PHE Dte .(Electric Portion) | 2633/MURD | 23/09/2024 | 20 | S. DUTTA | 2.57 | 2.57 | 100 | 100
5073 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Continuation work order for Engagement of 07(Seven) nos. Chemist (01 no. District Laboratory and 06nos. Sub-District Laboratory) , 06(Six)nos. Bacteriologist(01 no. District Laboratory and 05nos. Sub-District Laboratory), 11(Eleven)nos. Lab Assitant(01 no. District Laboratory and 10nos. Sub-District Laboratory) and 10(Ten)nos. Sampling Assistant(01 no. District Laboratory and 09nos. Sub-District Laboratory) in each of 11(Eleven) nos. District & Sub-District Water Testing Laboratories under Murshidabad Division, P.H.Engineering Dte. for 03(Three) Months. (i.e. period form 01/03/2024 to 31/05/2024) | 609/MURD | 27/02/2024 | 90 | CLIFFORD FACILITY SERVICES PVT. LTD. | 17.32 | 17.32 | 100 | 35
5074 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Continuation work order for Engagement of 02(Two) nos. Chemist (01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) , 02(Two)nos.Bacteriologist(01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) and 02(Two)nos. Lab Assitant(01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) Sub-District Water Testing Laboratories under Murshidabad Division, P.H.Engineering Dte. in the district of Murshidabad for 03(Three) Months. i.e. period form 01/03/2024 to 31/05/2024 | 610/MURD | 27/02/2024 | 90 | BISWAS ENGINEERING & WATER TESTING. | 4.03 | 3.38 | 100 | 100
5075 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/12/2023 to 31/12/2023 & 1st installment for the year 2024 of Lab Maintenance | 501-MSD/2023-24 | 17/01/2024 | 0 | R.N CLUB LAB | 0.85 | 0 | 0 | 0
5076 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab personnel for the period 01/09/2023 to 30/11/2023. | 457-MSD/2023-24 | 28/12/2023 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.9 | 0 | 0 | 0
5077 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period of 01/09/2024 to 30/09/2024 and festive bonus for the year 2024-2025. | 537-MSD/2024-25 | 06/10/2024 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.63 | 0 | 0 | 0
5078 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period | 332-MSD/2024-25 | 30/08/2024 | 0 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.8 | 0 | 0 | 0
5079 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of April 2024 to July 2024. | 333-MSD/2024-25 | 30/08/2024 | 0 | COMMUNITY POLITECHNIC SCHEME, MIT | 2.2 | 0 | 0 | 0
5080 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of August 2024. | 396-MSD/2024-25 | 20/09/2024 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
5081 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for Bonus of Lab personnel for the period from 2023-24. |  | 04/10/2023 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.16 | 0 | 0 | 0
5082 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for festival Bonus of Lab Personnel for the period 2022-23 |  | 10/10/2023 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.16 | 0 | 0 | 0
5083 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab-Personnel for the month of January-2024 | 563-MSD/2023-24 | 21/02/2024 | 0 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
5084 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL AND OFFICE EXPENSES FROM 01/02/2024 TO 29/02/2024 | 638-MSD/2023-24 | 17/03/2024 | 0 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 1.01 | 0 | 0 | 0
5085 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab-Personnel for the period of 01.03.2024 to 31.03.2024 | 52-MSD/2024-25 | 26/04/2024 | 0 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.45 | 0 | 0 | 0
5086 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Remuneration of Lab Personnel for the month of April 2024 | 132-MSD/2024-25 | 06/06/2024 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.85 | 0 | 0 | 0
5087 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Festival Bonus |  | 06/10/2023 | 0 | R.N CLUB LAB | 0.16 | 0 | 0 | 0
5088 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Bill for Internet Recharge of the Laboratories under Murshidabad Division, PHE Dte for September 2023 | 516-MSD/2023-24 | 29/01/2024 | 0 | BISWAS ENGINEERING & WATER TESTING. | 0.05 | 0 | 0 | 0
5089 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab personnel for the period of 01/01/2024 to 31/01/2024. | 564-MSD/2023-24 | 21/02/2024 | 0 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
5090 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of September 2024 and festival bonus for the period 2024-2025. | 538-MSD/2024-25 | 06/10/2024 | 0 | RURAL NATIONAL CLUB | 0.63 | 0 | 0 | 0
5091 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/08/2024 to 31/08/2024. | 399-MSD/2024-25 | 20/09/2024 | 0 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
5092 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Internet recharge of 09 nos. Laboratory under Murshidabad Division, PHE Dte for the month of August 2023 | 516-MSD/2023-24 | 29/01/2024 | 0 | BISWAS ENGINEERING & WATER TESTING. | 0.05 | 0 | 0 | 0
5093 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/10/2023 to 30/11/2023 | 461-MSD/2023-24 | 28/12/2023 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.9 | 0 | 0 | 0
5094 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for Remuneration of Lab Personel for the period of 01.12.2023 to 31.01.2024 | 576-MSD/2023-24 | 22/02/2024 | 0 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.9 | 0 | 0 | 0
5095 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | CALIM OF REMUNERATION OF LAB PERSONNEL FROM DECEMBER 2023 TO FEBRUARY 2024 | 634-MSD/2023-24 | 17/03/2024 | 0 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.35 | 0 | 0 | 0
5096 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/12/2023 to 31/01/2024 | 565-MSD/2023-24 | 21/02/2024 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.9 | 0 | 0 | 0
5097 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab personnel for the period 01/10/2024 to 31/10/2024. | 572-MSD/2024-25 | 25/11/2024 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.8 | 0 | 0 | 0
5098 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for bonus of Lab personnel for the period 01/09/2024 to 30/09/2024 and festival bonus for the period 2024-2025. | 560-MSD/2024-25 | 30/10/2024 | 0 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.63 | 0 | 0 | 0
5099 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the Period 01/06/2024 to 30/06/2024 | 279-MSD/2024-25 | 12/08/2024 | 0 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
5100 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/06/24 to 30/06/24 | 278-MSD/2024-25 | 12/08/2024 | 0 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.45 | 0 | 0 | 0
5101 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL AND OFFICE EXPENSES FROM 01/02/2024 29/02/2024 | 636-MSD/2023-24 | 17/03/2024 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.61 | 0 | 0 | 0
5102 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL AND OFFICE EXPENSES FROM 01/02/2024 29/02/2024 | 635-MSD/2023-24 | 17/03/2024 | 0 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.61 | 0 | 0 | 0
5103 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/03/2024 to 31/03/2024 | 35-MSD/2024-202 | 19/04/2024 | 0 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
5104 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Remuneration of Lab Personnel for the month of April 2024 | 99-MSD/2024-25 | 22/05/2024 | 0 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
5105 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Carrying referral water samples to state laboratory. | 329-MSD/2024-25 | 30/08/2024 | 0 | M/S. DIPTI ENTERPRISE | 0.07 | 0 | 0 | 0
5106 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the month of August 2024. | 397-MSD/2024-25 | 20/09/2024 | 0 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
5107 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/09/24 to 30/09/24 and Claim for Festival Bonus of Lab-Personnel for the period 2023-2024. | 536-MSD/2024-25 | 06/10/2024 | 0 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.63 | 0 | 0 | 0
5108 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim of 1st installment of Jal management expenses for the year 2024. | 502-MSD/2023-24 | 17/01/2024 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.4 | 0 | 0 | 0
5109 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Bill for Internet Recharge of the Laboratories under Murshidabad Division, PHE Dte for September 2023 | 516-MSD/2023-24 | 29/01/2024 | 0 | BISWAS ENGINEERING & WATER TESTING. | 0.05 | 0 | 0 | 0
5110 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | CLAIM REMUNERATION OF LAB PERSONNEL FROM JUNE 23 TO AUGUST 23 | 460-MSD/2023-24 | 28/12/2023 | 0 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.75 | 0 | 0 | 0
5111 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab personnel for the month of September 2023 to November 2023 | 460-MSD/2023-24 | 28/12/2023 | 0 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.35 | 0 | 0 | 0
5112 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the Period 01/12/2023 to 31/12/2023 | 502-MSD/2023-24 | 17/01/2024 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.45 | 0 | 0 | 0
5113 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remmuneration of Lab - Personnel for the period 01/03/2024 to 31/03/2024 | 37-MSD/2024-25 | 19/04/2024 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
5114 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of March 2024 and 2nd installment for Lab maintenance of 2023. | 63-MSD/2024-25 | 30/04/2024 | 0 | COMMUNITY POLITECHNIC SCHEME, MIT | 0.8 | 0 | 0 | 0
5115 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | CLAIM FOR REMUERATION OF LAB PERSONNEL FOR THE PERIOD 01/04/2024 TO 30/04/2024 | 92-MSD/2024-25 | 22/05/2024 | 0 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
5116 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab- Personnel for the period 01/10/2024 to 31/10/2024. | 583-MSD/2024-25 | 06/12/2024 | 0 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
5117 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab- personnel for the month of September 2024 to November 2024. | 596-MSD/2024-20 | 16/12/2024 | 0 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.7 | 0 | 0 | 0
5118 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month for month of May 2024. | 136-MSD/2024-25 | 12/06/2024 | 0 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
5119 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/05/2024 to 31/05/2024 | 208-MSD/2024-25 | 02/07/2024 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
5120 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of November 2023 | 459-MSD/2023-24 | 28/12/2023 | 0 | R.N CLUB LAB | 0.45 | 0 | 0 | 0
5121 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL AND OFFICE EXPENSES FROM 01/02/2024 29/02/2024 | 637-MSD/2023-24 | 17/03/2024 | 0 | RURAL NATIONAL CLUB | 0.61 | 0 | 0 | 0
5122 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/10/24 to 30/11/24. | 595-MSD/2024-20 | 16/12/2024 | 0 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.9 | 0 | 0 | 0
5123 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of November 2024 | 582-MSD/2024-25 | 06/12/2024 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
5124 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of July 2024 | 330-MSD/2024-25 | 30/08/2024 | 0 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
5125 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of November 2024 | 581-MSD/2024-25 | 06/12/2024 | 0 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
5126 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of August 2024. | 398-MSD/2024-25 | 20/09/2024 | 0 | COMMUNITY POLITECHNIC SCHEME, MIT | 0.45 | 0 | 0 | 0
5127 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/05/2024 to 31/05/2024. | 209-MSD/2024-25 | 02/07/2024 | 0 | HARIPUR DR. AMBEDKAR JANASEBA MISSION | 0.45 | 0 | 0 | 0
5128 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | REMUNERATION OF LAB PERSONNEL FROM 01/10/23 TO 30/11/23 | 458-MSD/2023-24 | 28/12/2023 | 0 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.9 | 0 | 0 | 0
5129 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | CLAIM OF FESTIVE BONUS 22-23 |  | 05/12/2023 | 0 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.16 | 0 | 0 | 0
5130 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE MMONTH OF MARCH 2024 | 36-MSD/2024-25 | 19/04/2024 | 0 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
5131 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/04/24 to 31/05/24. | 135-MSD/2024-25 | 12/06/2024 | 0 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.9 | 0 | 0 | 0
5132 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of lab personnel for the month of October 2024. | 571-MSD/2024-25 | 25/11/2024 | 0 | RURAL NATIONAL CLUB | 0.45 | 0 | 0 | 0
5133 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/06/2024 to 31/07/2024. | 331-MSD/2024-25 | 30/08/2024 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.9 | 0 | 0 | 0
5134 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of June 2024 & 2nd installment of lab management expenses in advance for the year 2024. | 280-MSD/2024-25 | 12/08/2024 | 0 | RURAL NATIONAL CLUB | 0.8 | 0 | 0 | 0
5135 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Claim for Remuneration of Lab-Personnel for the period 01/07/24 to 31/08/24. | 395-MSD/2024-25 | 20/09/2024 | 0 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 1.25 | 0 | 0 | 0
5136 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Continuation work order for Engagement of Chemist and Bacteriologist for water testing laboratories under Murshidabad Division. P.H.Engineering Dte. 4,C.R.Das Road Berhampore, Murshidabad for one year.(i.e. period from 01/03/2025 to 28/02/2026) | 496/MURD | 27/02/2025 | 365 | M/S. S. DAS AND ENTERPRISE | 25.6 | 7.6 | 29.71 | 30
5137 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Continuation work order for Engagement of 1(one) AAS operator/Additional Chemist, 1(one) AAS Sampling Assistant including salary, festival bonus arrear portion of enhanced salary if applicable etc one year technical support for AAS (Thermo Scientific). (For 11.5 months) (i.e. 01/06/2025 to 15/05/2026) | 1216/MURD | 27/05/2025 | 365 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 5.62 | 0 | 0 | 0
5138 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Payment of monthly salaries of Chemist , Bacteriologist, Laboratory assistant, Sampling assistant & Data entry operator/CSM for District laboratory and 13 nos sub-district water testing laboratories under Murshidabad Division. P.H. Engineering Dte. for one year. (Period form 01/12/2025 to 30/11/2026) | 2373/MURD | 19/11/2025 | 365 | M/S JAN MAHAMMAD | 168.84 | 0 | 0 | 0
5139 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Supply & delivery of PT Test Charge for 11 mandatory parameters for 6 nos sub-District water Testing Laboratory as per PT Plan of NABL-139 at least once in a year for Sub Distt Lab & as per PT Plan for District Lab. | 2095/MURD | 23/07/2024 | 7 | M/S LAXMI ENTERPRISE | 0.09 | 0 | 0 | 0
5140 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Continuation work order for Computer Maintenance, UPS Maintenance, Printer maintenance ,Broad band Net recharge, Sweeping ,Cleaning & laboratories maintenance and minor repair of 14 nos water testing laboratories & stationary goods of 14 nos water testing laboratories for one year under Murshidabad Division. P.H. Engineering Dte.(i.e. Period from 01-12-2025 to 30-11-2026) | 2375/MURD | 19/11/2025 | 365 | MURARI JHA | 20.86 | 0 | 0 | 0
5141 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Supply & delivery of 5 nos Tin(II) chloride dihydrate GR(gm), 100 gm pack for Murshidabad District water testing laboratory. | 266/MURD | 24/01/2024 | 7 | M/S LAXMI ENTERPRISE | 0.04 | 0 | 0 | 0
5142 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Engagement of 02(Two) nos. Chemist (01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) , 02(Two)nos.Bacteriologist(01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) and 02(Two)nos. Lab Assitant(01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) Sub-District Water Testing Laboratories under Murshidabad Division, P.H.Engineering Dte. in the district of Murshidabad for 01(One) year. i.e. period form 01/03/2023 to 28/02/2024 | 451/MURD | 17/02/2023 | 365 | BISWAS ENGINEERING & WATER TESTING. | 16.5 | 9.1 | 100 | 67
5143 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Continuation work order for Engagement of Resource Person & Sampling Assistant at the Laboratory Site to Operate AAS Spectrophotometer System for a Period of Six Months under Murshidabad Division, PHE Dte. in the district of Murshidabad. (Period from 15/09/2023 to 14/03/2024) | 2916/MURD | 14/09/2023 | 182 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 2.56 | 2.56 | 100 | 100
5144 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Engagement of Chemist and Bacteriologist for water testing laboratories under Murshidabad Division. P.H. Engineering Dte. 4,C.R.Das Road Berhampore, Murshidabad for one year.(i.e. period form 01/03/2024 to 28/02/2025) | 602/MURD | 27/02/2024 | 365 | M/S. S. DAS AND ENTERPRISE | 25.6 | 15.52 | 100 | 100
5145 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Broad band Net recharge and Sweeping & Cleaning of 11 nos water testing laboratories for one year and arrear for Sweeping & Cleaning of 11 nos water testing laboratories for 12 months under Murshidabad Division. P.H. Engineering Dte. 4,C.R.Das Road Berhampore, Murshidabad for one year. (i.e. period form 01/02/2024 to 31/01/2025) | 359/MURD | 01/02/2024 | 365 | MURARI JHA | 4.49 | 4.49 | 100 | 10
5146 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Continuation work order for Engagement of Resource Person & Sampling Assistant at the Laboratory Site to Operate AAS Spectrophotometer System for a Period of Three Months under Murshidabad Division, PHE Dte. in the district of Murshidabad. (Period from 15/03/2024 to 14/06/2024) | 772/MURD | 13/03/2024 | 92 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
5147 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Payment of month salaries of Chemist , Bacteriologist, Laboratory assistant, Sampling assistant & Data entry operator/CSM for District laboratory and 12 nos sub-district water testing laboratories under Murshidabad Division. P.H. Engineering Dte. For a period of 12 months (i.e. 01.06.2024 to 31.05.2025) | 1585/MURD | 21/05/2024 | 365 | CFS MANAGEMENT PRIVATE LIMITED | 96.96 | 75.75 | 78.88 | 35
5148 | MURSHIDABAD | Murshidabad Division | Operational charges of drinking water testing laboratories related to water quality monitoring surveillance activities under JJM of different water testing laboratories under Murshidabad Division PHE Dte. , SM/19076 | Support-WQMSP | Engagement of 1(one) AAS operator/Additional Chemist, 1(one) AAS Sampling Assistant including salary, festival bonus arrear portion of enhanced salary if applicable etc one year technical support for AAS (Thermo Scientific). (For 12 months) (i.e. 01/10/2024 to 30/09/2025) | 2666/MURD | 25/09/2024 | 365 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 6.46 | 0 | 0 | 100
5149 | MURSHIDABAD | Resource | PROCUREMENT OF SERVICE OF CONSULTANTS FOR PREPARATION OF DPR OF NEW PIPED WATER SUPPLY SCHEME FOR UNCOVERD RURAL AREA OF MURSHIDABAD DISTRICT IN WEST BENGAL , SM/14638 | Support-MIS | Formal order for Preparation of DPR for Schemes under Jal Jeevan Mission in West Bengal. | 1997/RS | 03/11/2021 | 180 | NABCONS PRIVATE LIMITED | 5500 | 624.24 | 100 | 80
5150 | MURSHIDABAD | Berhampore Mechanical | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Executive Engineer, Mechanical/Electrical Division Berhampore, PHE Dte. , SM/17192 | Support-MIS | hp Intel Core i5 12400 8GB/ 1000GB HDD/ Windows11 Professional, Model- HP 280 G9 MT i5 12400 Win11P 8512SSD15 21.5inc, Desktop Computer 6 pieces. | 133/PFMS-JJM | 11/10/2023 | 0 | EASY DAY ENTERPRISE | 4.59 | 0 | 0 | 0
5151 | MURSHIDABAD | Berhampore Mechanical | Supply, delivery, installation of Computer and peripheral for the official use under the Office of the Executive Engineer, Mechanical/Electrical Division Berhampore, PHE Dte. , SM/17192 | Support-MIS | HP LaserJet Pro MFP 4104fdw Printer 4 pieces. | 134/PFMS-JJM | 11/10/2023 | 0 | IONET | 1.82 | 0 | 0 | 0
5152 | MURSHIDABAD | Murshidabad Division | Supply, installation & delivery of water quality testing equipment's, chemicals, consumables & glassware etc. for continuing NABL accrediation ( chemical testing of potable water) of Murshidabad District Water Testing Laboratory in the District of Murshid , SM/08685 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents and Glassware for NABL accreditation at Murshidabad District Water Testing Laboratory under Murshidabad Division, P.H.E.Dte. | 274 /HQ | 08/11/2021 | 30 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 3.17 | 0 | 0 | 0
5153 | MURSHIDABAD | Murshidabad Division | Supply, installation & delivery of water quality testing equipment's, chemicals, consumables & glassware etc. for continuing NABL accrediation ( chemical testing of potable water) of Murshidabad District Water Testing Laboratory in the District of Murshid , SM/08685 | Support-WQMSP | Chemical, glassware & instrumments requirment for NABL accreditation at Murshidabad District Water Testing Laboratory as per ISO/IEC: 17025: 2017 under Murshidabad Division, PHE Dte. in the district of Murshidabad. | 2728/MURD | 03/09/2021 | 10 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 14.36 | 12.87 | 100 | 0
5154 | MURSHIDABAD | Murshidabad Division | Supply, installation & delivery of water quality testing equipment's, chemicals, consumables & glassware etc. for continuing NABL accrediation ( chemical testing of potable water) of Murshidabad District Water Testing Laboratory in the District of Murshid , SM/08685 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents and Glassware for NABL accreditation at Murshidabad District Water Testing Laboratory under Murshidabad Division, P.H.E.Dte. | 40-MSD/22-23 | 21/04/2022 | 0 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 3.17 | 0 | 0 | 0
5155 | MURSHIDABAD | Murshidabad Division | Supply, installation & delivery of water quality testing equipment's, chemicals, consumables & glassware etc. for continuing NABL accrediation ( chemical testing of potable water) of Murshidabad District Water Testing Laboratory in the District of Murshid , SM/08685 | Support-WQMSP | Continuation Work Order for Engaging Chemist, Bacteriologist and Laboratory Assistant for test of Water samples at Jangipur (WTP) Laboratory under Murshidabad Division, P. H. Engineering Dte for 06(Six) months (Period from 01-06-2022 to 30-11-2022) | 1351/MURD | 24/05/2022 | 184 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 3.06 | 0 | 0 | 0
5156 | MURSHIDABAD | Murshidabad Division | Procurement Computers and peripherals for 19 Water Testing Laboratories and Sub-Divisional offices under Murshidabad Division. , SM/15310 | Support-MIS | HP multifunction machines mfm, On site OEM warranty 5 Years | 172-MSD/2023-24 | 14/07/2023 | 0 | IONET | 0.95 | 0 | 0 | 0
5157 | MURSHIDABAD | Murshidabad Division | Procurement Computers and peripherals for 19 Water Testing Laboratories and Sub-Divisional offices under Murshidabad Division. , SM/15310 | Support-MIS | Hp Intel Core i5 14 inch Laptop (Windows 11 Professional) | 172-MSD/2023-24 | 14/07/2023 | 0 | IONET | 1.93 | 0 | 0 | 0
5158 | MURSHIDABAD | Murshidabad Division | Procurement Computers and peripherals for 19 Water Testing Laboratories and Sub-Divisional offices under Murshidabad Division. , SM/15310 | Support-MIS | HP Intel Core I5 12500 16GB/0GB HDD/Windows 10 Professional | 172-MSD/2023-24 | 14/07/2023 | 0 | IONET | 4.97 | 0 | 0 | 0
5159 | MURSHIDABAD | Murshidabad Division | Procurement Computers and peripherals for 19 Water Testing Laboratories and Sub-Divisional offices under Murshidabad Division. , SM/15310 | Support-MIS | Canon Laser Mono Computer Printers for A4 paper size. Model : Canon LBP6030w | 522-MSD/2023-24 | 31/01/2024 | 0 | IONET | 1.19 | 0 | 0 | 0
5160 | MURSHIDABAD | Murshidabad Division | Procurement Computers and peripherals for 19 Water Testing Laboratories and Sub-Divisional offices under Murshidabad Division. , SM/15310 | Support-MIS | Model : Microtek Line Interactive UPS with AVR of rating 0.65 KVA (Legend 650) Serial No. 23JOU1104703135619 23JOU1104703135620 23JOU1104703135621 23JOU1104703135622 23JOU1104703135604 23JOU1104703135566 23JOU1104703135605 23JOU1104703135606 | 522-MSD/2023-24 | 31/01/2024 | 0 | IONET | 0.24 | 0 | 0 | 0
5161 | MURSHIDABAD | Murshidabad Division | Procurement Computers and peripherals for 19 Water Testing Laboratories and Sub-Divisional offices under Murshidabad Division. , SM/15310 | Support-MIS | PURCHASE OF UPS FOR MSD DIVN, INVOICE NO- 23/07/24-25, 23/07/24 |  | 24/09/2024 | 0 | SHIVAM ENTERRPISE | 0.23 | 0 | 0 | 0
5162 | MURSHIDABAD | Murshidabad Division | Procurement Computers and peripherals for 19 Water Testing Laboratories and Sub-Divisional offices under Murshidabad Division. , SM/15310 | Support-MIS | PURCHASE OF UPS FOR MSD DIVN, 6 NOS, GEMC-511687752876039 | 451-MSD/2023-24 | 02/10/2024 | 0 | SHIVAM ENTERRPISE | 0.15 | 0 | 0 | 0
5163 | MURSHIDABAD | Murshidabad Division | Procurement Computers and peripherals for 19 Water Testing Laboratories and Sub-Divisional offices under Murshidabad Division. , SM/15310 | Support-MIS | HP Intel Core i5 10600 16GB/0GB HDD/Windows 11 Professional Model: HP 280 Pro G6 Micro Tower i5 (3E7R9PA#ACJ) with 21.5" monitor | 522-MSD/2023-24 | 31/01/2024 | 0 | IONET | 4.39 | 0 | 0 | 0
5164 | MURSHIDABAD | Murshidabad Division | Procurement Computers and peripherals for 19 Water Testing Laboratories and Sub-Divisional offices under Murshidabad Division. , SM/15310 | Support-MIS | PURCHASE OF UPS FOR MSD DIVN, INVOICE NO- 23/07/24-25, 23/07/24 | 576-MSD/2024-25 | 29/11/2024 | 0 | SHIVAM ENTERRPISE | 0.04 | 0 | 0 | 0
5165 | MURSHIDABAD | Murshidabad Division | Procurement Computers and peripherals for 19 Water Testing Laboratories and Sub-Divisional offices under Murshidabad Division. , SM/15310 | Support-MIS | PURCHASE OF 3 NOS COMPUTER FOR MSD DIVISION, INVOICE NO- JDE/24-25/47, 25/07/2024 | 450-MSD/2024-25 | 02/10/2024 | 0 | JD ENGINEERING | 2.05 | 0 | 0 | 0
5166 | MURSHIDABAD | Murshidabad Division | Procurement Computers and peripherals for 19 Water Testing Laboratories and Sub-Divisional offices under Murshidabad Division. , SM/15310 | Support-MIS | PURCHASE OF 7 NOS CONMPUTER SET FOR LABORATORY UNDER MSD DIVISION. INVOICE NO- JDE/24-25/46 | 450-MSD/2024-25 | 02/10/2024 | 0 | JD ENGINEERING | 4.79 | 0 | 0 | 0
5167 | MURSHIDABAD | Murshidabad Division | Procurement Computers and peripherals for 19 Water Testing Laboratories and Sub-Divisional offices under Murshidabad Division. , SM/15310 | Support-MIS | PURCHASE OF UPS FOR MSD DIVN, INVOICE NO-23/07/24-25, 23/07/2024 | 451-MSD/2024-25 | 02/10/2024 | 0 | SHIVAM ENTERRPISE | 0.2 | 0 | 0 | 0
5168 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Payment of bonus for different laboratory personnel in the District of Murshidabad under Murshidabad Division, P.H.Engineering Dte.( Murshidabad District Laboratory, Jangipur WTP Laboratory & Mahyampur WTP Laboratory). | 112 / HQ | 02/03/2022 | 10 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 0.59 | 0.53 | 100 | 0
5169 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Engaging Chemist, Bacteriologist, Laboratory Assistant and Sampling Assistant for test of Water samples at District Laboratory under Murshidabad Division, P. H. Engineering Dte. | 113/HQ | 02/03/2022 | 6 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 4.23 | 4.23 | 100 | 0
5170 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Sample collection, submission and analysis of Total Arsenic for 12(Twelve) nos. Gram Panchayat located in 04 (Four) nos Block under Murshidabad Division, P.H.Engineering Dte. in the District of Murshidabad. | 126/HQ | 08/03/2022 | 45 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 3.7 | 3.58 | 100 | 0
5171 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | STATE LEVEL REFERRAL CROSS CHECKING OF WATER SAMPLE TO MSD. PAYMENT OF ACTUAL FAIR AND TRANSPORTING. | 384-MSD/22-23 | 23/10/2022 | 0 | M/S. DIPTI ENTERPRISE | 0.03 | 0 | 0 | 0
5172 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period for July 2022 to August 2022 | 353-MSD/22-23 | 18/10/2022 | 0 | R.N CLUB LAB | 0.66 | 0 | 0 | 0
5173 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL FOR THE PERIOD 01/07/2022 TO 30/09/2022 | 411-MSD/22-23 | 30/11/2022 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.99 | 0 | 0 | 0
5174 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim of 2nd Installation of Lab management expenses for the year 2022 | 352-MSD/22-23 | 18/10/2022 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.35 | 0 | 0 | 0
5175 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab -Personnel for the period MARCH 2022 to JUNE 2022 and 1ST Installment of lab management expenses of 2022. | 355-MSD/22-23 | 18/10/2022 | 0 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.72 | 0 | 0 | 0
5176 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of May 2022 | 353-MSD/22-23 | 18/10/2022 | 0 | R.N CLUB LAB | 0.33 | 0 | 0 | 0
5177 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for Remuneration of Lab - Personnel for the period 01.04.2022 to 31.05.2022 | 352-MSD/22-23 | 18/10/2022 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.66 | 0 | 0 | 0
5178 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period for 01.04.2022 to 31.05.2022 | 350-MSD/22-23 | 18/10/2022 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.66 | 0 | 0 | 0
5179 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for Remuneration of Lab - Personnel for the period 01.06.2022 to 30.06.2022 | 352 | 18/10/2022 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.33 | 0 | 0 | 0
5180 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of lab personnel for the period of 01.04.2022 to 31.05.2022 | 354-MSD/22-23 | 18/10/2022 | 0 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.66 | 0 | 0 | 0
5181 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL FOR THE MONTH OCT-2022 | 412-MSD/22-23 | 30/11/2022 | 0 | R.N CLUB LAB | 0.33 | 0 | 0 | 0
5182 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab -Personnel for the period 01.06.2022 to 30.06.2022 and 2nd installment for the year 2022 of Lab Management Expenses. | 353-MSD/22-23 | 18/10/2022 | 0 | R.N CLUB LAB | 0.68 | 0 | 0 | 0
5183 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab -Personnel for the period 01.04.2022 to 31.05.2022 and lab management expenses from January 2022 to May 2022. | 351-MSD/22-23 | 18/10/2022 | 0 | AMTALA VILLAGE ORGANISATION SOCIETY | 1.13 | 0 | 0 | 0
5184 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period of July 2022 to August 2022 | 355-MSD/22-23 | 18/10/2022 | 0 | COMMUNITY POLITECHNIC SCHEME, MIT | 0.66 | 0 | 0 | 0
5185 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | claim of remuneration of lab personnel for year 2021-22 | 410-MSD/22-23 | 30/11/2022 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.14 | 0 | 0 | 0
5186 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL FOR THE MONTH SEP-2022 | 412-MSD/22-23 | 30/11/2022 | 0 | R.N CLUB LAB | 0.33 | 0 | 0 | 0
5187 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of April 2022 | 353-MSD/22-23 | 18/10/2022 | 0 | R.N CLUB LAB | 0.33 | 0 | 0 | 0
5188 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM OF FESTIVE BONUS OF LAB PERSONNEL FOR 22-23 | 411-MSD/22-23 | 30/11/2022 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.14 | 0 | 0 | 0
5189 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FROM- 01/06/2022 TO 30/09/2022 | 410-MSD/22-23 | 30/11/2022 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 1.67 | 0 | 0 | 0
5190 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM OF FESTIVE BOUNS OF LAB PERSONNEL FOR THE YEAR 2021-22 | 412-MSD/22-23 | 30/11/2022 | 0 | R.N CLUB LAB | 0.14 | 0 | 0 | 0
5191 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Continuation Work Order for Engaging Chemist, Bacteriologist and Laboratory Assistant for test of Water samples at Mahyampur (WTP) Laboratory under Murshidabad Division, P. H. Engineering Dte. for 06(Six) months (Period from 01-12-2022 to 31-05-2023) | 3145/MURD | 25/11/2022 | 181 | BISWAS ENGINEERING & WATER TESTING. | 3.06 | 1.53 | 50 | 0
5192 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Engagement of 01(One) no Chemist,01(One) no Bacteriologist and 01(One) no Laboratory Assistant for test of Water samples at Surangapur Sub-District Water Testing Laboratory under Murshidabad Division, P.H. Engineering Dte. for 01 (One) year (Period from 01.09.2022 to 31.08.2023) | 2989/MURD | 22/09/2022 | 365 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 7.58 | 4.53 | 59.7 | 0
5193 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Continuation work order for Engagement of 02 (Two) Nos Sampling Assistant for newly set up 2 (Two)nos. Sub-District laboratories (Salar& Jagtai) in Murshidabad District for the period of 01(One) Year (i.e. 01/04/2022 to 31/03/2023) under Murshidabad Division, Public Health Engineering Dte. | 154/HQ | 28/03/2022 | 1 | MANDAL SCIENTIFIC AND WATER ANALYSIS | 2.29 | 2.11 | 92.06 | 0
5194 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Continuation work order for Engagement of Resource Person & Sampling Assistant at the Laboratory Site to Operate AAS Spectrophotometer System for a Period of Six Months under Murshidabad Division, PHE Dte. in the district of Murshidabad. (Period from 15/03/2023 to 14/09/2023) | 679/MURD | 10/03/2023 | 184 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 2.56 | 0 | 0 | 0
5195 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Continuation work order for Engaging Chemist, Bacteriologist, Laboratory Assistant and Sampling Assistant for test of Water samples at District Laboratory under Murshidabad Division, P. H. Engineering Dte.For 06(Six)Months i.e.from 01/09/2022 to 29/02/2023 | 113/HQ | 22/08/2022 | 6 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 4.23 | 4.23 | 100 | 0
5196 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PEROSNNEL FOR NOVEMBER 2022 | 445-MSD/22-23 | 15/12/2022 | 0 | R.N CLUB LAB | 0.33 | 0 | 0 | 0
5197 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab-Personnel for the month of March - 2023 |  | 05/04/2023 | 0 | R.N CLUB LAB | 0.45 | 0 | 0 | 0
5198 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period 01/06/2023 to 30/06/2023 and 2nd Installment for the year 23 of Lab Management Expenses. | 201-MSD/2023-24 | 11/08/2023 | 0 | R.N CLUB LAB | 0.8 | 0 | 0 | 0
5199 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab-Personnel for the month of March - 2023 | 14-MSD/2023-24 | 28/04/2023 | 0 | R.N CLUB LAB | 0.43 | 0 | 0 | 0
5200 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL FROM 01/06/2022 TO 31/10/2022, OFFICE EXPENSES (1ST INSTALLMENT) AND FESTIVAL BONUS (99000+66000+40000+14400)= 219400/- | 441-MSD/22-23 | 15/12/2022 | 0 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 2.19 | 0 | 0 | 0
5201 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM REMUNERATION OF LAB PERSONNEL FOR JANUARY 2023 | 578-MSD/22-23 | 02/03/2023 | 0 | R.N CLUB LAB | 0.45 | 0 | 0 | 0
5202 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP |  |  | 04/05/2023 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.45 | 0 | 0 | 0
5203 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | remuneration of lab personnel from 01/04/23 to 30/04/2023 | 82-MSD/2023-24 | 01/06/2023 | 0 | R.N CLUB LAB | 0.45 | 0 | 0 | 0
5204 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM FOR EMUNERATION OF LAB PERSONNEL FOR THE MONTH OF JANUARY 2023 TO FEBRUARY 2023 | 644-MSD/22-23 | 29/03/2023 | 0 | COMMUNITY POLITECHNIC SCHEME, MIT | 0.9 | 0 | 0 | 0
5205 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE PERIOD OF SEPTEMBER 2022 TO DECEMBER 2022 AND 2ND INSTALLMENT OF LAB MANAGEMENT EXPENSES OF 2022. | 644-MSD/22-23 | 29/03/2023 | 0 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.67 | 0 | 0 | 0
5206 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | remuneration of lab personnel from 01/04/23 to 30/04/2023 | 83-MSD/2023-24 | 01/06/2023 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.45 | 0 | 0 | 0
5207 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM REMUNERATION OF LAB PERSONNEL FROM 01/12/22 TO 31/12/22 | 579-MSD/22-23 | 02/03/2023 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.33 | 0 | 0 | 0
5208 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab personnel for the period of 01.02.23 to 31.03.2023 | 116-MSD/2023-24 | 10/06/2023 | 0 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.9 | 0 | 0 | 0
5209 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | REMUNERATION OF LAB PERSONNEL FROM 01/05/23 TO 31/05/2023 | 149-MSD/2023-24 | 22/06/2023 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.45 | 0 | 0 | 0
5210 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Appeal for Reimbursement of 1st instalment of fLab Charges for the Year 2023 and submission of utilization certificate of 2nd Installment of 2022 | 116-MSD/2023-24 | 10/06/2023 | 0 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.35 | 0 | 0 | 0
5211 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | LAB PERSONNEL SALARY- 01/03/23 TO 30/04/23 | 84-MSD/2023-24 | 01/06/2023 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 1.3 | 0 | 0 | 0
5212 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM OF REMUNERATION FOR MAY 2023 | 147-MSD/2023-24 | 22/06/2023 | 0 | R.N CLUB LAB | 0.45 | 0 | 0 | 0
5213 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | REMUNERATION OF LAB PERSONNEL FROM 01/05/23 TO 30/06/23 | 176-MSD/2023-24 | 19/07/2023 | 0 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.9 | 0 | 0 | 0
5214 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of lab personnel for the month of June 2023 to August 2023 |  | 21/09/2023 | 0 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.75 | 0 | 0 | 0
5215 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | claim for remuneration f fLab personnel for the priod 01/12/22 to 31/12/22 | 610-MSD/22-23 | 15/03/2023 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.33 | 0 | 0 | 0
5216 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab Personnel for the period of 01.01.2023 to 31.01.2023 | 610-MSD/22-23 | 15/03/2023 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.45 | 0 | 0 | 0
5217 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB-PERSONNEL FOR THE PERIOD 01/02/2023 TO 28/02/2023. | 645-MSD/22-23 | 29/03/2023 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.45 | 0 | 0 | 0
5218 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab - Personnel for the Period 01/06/2023 to 30/06/2023. Claim of 2nd installment of lab management expenses for the year 2023 (Kandi water testing laboratory) | 200-MSD/2023-24 | 11/08/2023 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.8 | 0 | 0 | 0
5219 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL FOR THE PERIOD 01/10/22 TO 30/11/2022 | 497-MSD/22-23 | 11/01/2023 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.66 | 0 | 0 | 0
5220 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE PERIOD 01/10/2022 TO 30/11/2022 | 496-MSD/22-23 | 11/01/2023 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.66 | 0 | 0 | 0
5221 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CALIM FOR REMUNERATION OF LAB PERSONNEL FOR THE PERIOD 01/03/2023 TO 31/03/2023. | 21-MSD/23-24 | 29/04/2023 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.45 | 0 | 0 | 0
5222 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | STATE LEVEL REFFERRAL CROSS CHECKING OF WATER SAMPLES TO MURSHIDABAD DISTRICT. | 136-MSD/2023-24 | 17/06/2023 | 0 | M/S. DIPTI ENTERPRISE | 0.08 | 0 | 0 | 0
5223 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP |  |  | 04/05/2023 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 1.3 | 0 | 0 | 0
5224 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for remuneration of Lab Personnel for the month of February 2023 | 611-MSD/22-23 | 14/03/2023 | 0 | R.N CLUB LAB | 0.45 | 0 | 0 | 0
5225 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM FOR REMUNERATION OF LAB PERSONNEL FOR THE PERIOD 01/01/2023 TO 28/02/2023 | 646-MSD/22-23 | 29/03/2023 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.9 | 0 | 0 | 0
5226 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | REMUNERATION OF LAB FOR MARCH 2023 TO MAY 2023 | 150-MSD/2023-24 | 22/06/2023 | 0 | COMMUNITY POLITECHNIC SCHEME, MIT | 1.35 | 0 | 0 | 0
5227 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM OF LAB PERSONNEL SALARY FOR MAY 2023 | 148-MSD/2023-24 | 22/06/2023 | 0 | FARAKKA BEEDI SHRAMIK KALYAN SAMITY | 0.45 | 0 | 0 | 0
5228 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | SALARY OF LAB PERSONNAL FOR THE MONTH OF 01.04.02023 TO 30.04.2023 | 116-MSD/2023-24 | 10/06/2023 | 0 | RAMKRISHNA MISSION ASHRAM (SEVABRATA), BAIRGACHHI | 0.45 | 0 | 0 | 0
5229 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | CLAIM OF REMUNERATION FOR JULY 2023 TO AUGUST 2023 |  | 15/09/2023 | 0 | R.N CLUB LAB | 0.9 | 0 | 0 | 0
5230 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim of 1st Installment of lab management expenses for the year 2023 under kandi water testing lab | 610-MSD/22-23 | 15/03/2023 | 0 | HARIPUR DR. AMBEDKAR JANASEVA MISSION | 0.4 | 0 | 0 | 0
5231 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Engagement of 07(Seven) nos. Chemist (01 no. District Laboratory and 06nos. Sub-District Laboratory) , 06(Six)nos.Bacteriologist(01 no. District Laboratory and 05nos. Sub-District Laboratory), 11(Eleven)nos. Lab Assitant(01 no. District Laboratory and 10nos. Sub-District Laboratory) and 10(Ten)nos. Sampling Assistant(01 no. District Laboratory and 09nos. Sub-District Laboratory) in each of 11(Eleven) nos. District & Sub-District Water Testing Laboratories under Murshidabad Division, P.H.Engineering Dte. for 01(One) year. (i.e. period form 01/03/2023 to 28/02/2024) | 455/MURD | 17/02/2023 | 365 | CLIFFORD FACILITY SERVICES PVT. LTD. | 82.31 | 5.64 | 100 | 100
5232 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Claim for Remunearation of Lab-Personnel for the period of 01.12.2023 to 31.01.2024 |  | 02/02/2024 | 0 | RAMAKRISHNA MISSION ASHRAMA (SEVAVRATA), BAIRGACHI | 0.9 | 0 | 0 | 0
5233 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Engagement of 02(Two) nos. personnel (One Chemist/Bacteriologist and One Lab Assitant) in each of 09(Nine) nos. new Sub-District Water Testing Laboratories & 7 nos Sampling Assistant (01 no. each) of 07 (Seven) nos. new Sub-District Laboratories under Murshidabad Division, P.H.Engineering Dte. in the district of Murshidabad for 01(One) year. (i.e. period from 01/04/2022 to 31/03/2023) | 702/MURD | 14/03/2022 | 365 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 39.01 | 35.88 | 91.98 | 0
5234 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Continuation Work Order for Engaging Chemist, Bacteriologist and Laboratory Assistant for test of Water samples at Jangipur (WTP) Laboratory under Murshidabad Division, P. H. Engineering Dte for 03(Thee) months (Period from 01-12-2022 to 28-02-2023) | 3155/MURD | 29/11/2022 | 91 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 1.53 | 1.06 | 69.43 | 0
5235 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Continuation Work Order for Engaging Chemist, Bacteriologist and Laboratory Assistant for test of Water samples at Mahyampur (WTP) Laboratory under Murshidabad Division, P. H. Engineering Dte. for 03(Three) months (Period from 01-03-2022 to 31-05-2022) | 513/MURD | 23/02/2022 | 3 | BISWAS ENGINEERING & WATER TESTING. | 1.53 | 1.53 | 100 | 0
5236 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Continuation Work Order for Engaging Chemist, Bacteriologist and Laboratory Assistant for test of Water samples at Jangipur (WTP) Laboratory under Murshidabad Division, P. H. Engineering Dte for 06(Six) months (Period from 01-12-2021 to 31-05-2022) | 3730/MURD | 30/11/2021 | 6 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 3.06 | 2.12 | 100 | 0
5237 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Continuation Work Order for Engaging Chemist, Bacteriologist and Laboratory Assistant for test of Water samples at Jangipur (WTP) Laboratory under Murshidabad Division, P. H. Engineering Dte for 06(Six) months (Period from 01-06-2022 to 30-11-2022) | 3730/MURD | 24/05/2022 | 184 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 3.06 | 2.12 | 100 | 0
5238 | MURSHIDABAD | Murshidabad Division | Recurring Expenditure , Salary and Festival bonus of Laboratory Personnel of different water Testing Laboratories under Murshidabad Division P.H.E Dte. , SM/13044 | Support-WQMSP | Engagement of 02(Two) nos. Chemist (01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) , 02(Two)nos.Bacteriologist(01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) and 02(Two)nos. Lab Assitant(01 no. Mahyampur WTP Laboratory and 01no. Jangipur WTP Sub-District Laboratory) Sub-District Water Testing Laboratories under Murshidabad Division, P.H.Engineering Dte. in the district of Murshidabad for 01(One) year. i.e. period form 01/03/2023 to 28/02/2024 | 451/MURD | 17/02/2023 | 365 | BISWAS ENGINEERING & WATER TESTING. | 16.5 | 4.12 | 100 | 67
5239 | MURSHIDABAD | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . , SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part - C) | 36/KSD | 07/07/2023 | 25 | IMAGIN | 4.95 | 0 | 0 | 0
5240 | MURSHIDABAD | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . , SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part -D) | 40/KSD | 18/07/2023 | 25 | IMAGIN COMMUNICATION | 4.95 | 0 | 0 | 0
5241 | MURSHIDABAD | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . , SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part -F) | 42/KSD | 18/07/2023 | 25 | IMAGIN COMMUNICATION | 4.95 | 0 | 0 | 0
5242 | MURSHIDABAD | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . , SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part -E) | 41/KSD | 18/07/2023 | 25 | IMAGIN | 4.95 | 0 | 0 | 0
5243 | MURSHIDABAD | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . , SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part -G) | 44/KSD | 20/07/2023 | 25 | IMAGIN | 4.93 | 0 | 0 | 0
5244 | MURSHIDABAD | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . , SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part -H) | 45/KSD | 20/07/2023 | 25 | IMAGIN | 4.94 | 0 | 0 | 0
5245 | MURSHIDABAD | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . , SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part - B) | 33/KSD | 25/06/2023 | 25 | S.S.INFRASTRUCTURE | 4.96 | 4.94 | 100 | 100
5246 | MURSHIDABAD | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . , SM/18272 | Support-IEC | Use of logo & tagline of Jal Jeevan Mission for IEC & Training activities and design of display board to be placed at different work sites under Kandi Sub Division, P.H.Engineering Dte.(Part -A) | 32/KSD | 25/06/2023 | 25 | IMAGIN | 4.96 | 4.95 | 100 | 100
5247 | MURSHIDABAD | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . , SM/18272 | Support-IEC | Infrastructure support for Information Education & Communication (IEC) activities reached to judicious and safe way of drinking water adopting different modes e.g. display lands, magic show/folk song, leaflet/booklet, school IEC and their documentation through still photography. | 3683/MURD | 01/12/2023 | 30 | IMAGIN | 40.53 | 40.53 | 100 | 100
5248 | MURSHIDABAD | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . , SM/18272 | Support-IEC | Infrastructure support for Information Education & Communication (IEC) activities reached to judicious and safe way of drinking water adopting different modes eg display lands, magic show/folk song, leaflet/booklet, school IEC, formation . and their documentation through still photography in different Gram Panchayat under Murshidabad Division P.H.E. Dte. | 2386/MURD | 23/08/2024 | 30 | IMAGIN | 92.67 | 92.65 | 100 | 100
5249 | MURSHIDABAD | Murshidabad Division | Infrastructure support for Information Education & Communication (IEC) activities in Murshidabad District under Murshidabad Division PHE Dte . , SM/18272 | Support-IEC | Infrastructure support for Information Education & Communication (IEC) activities reached to judicious and safe way of drinking water adopting different modes eg display lands, magic show/folk song, leaflet/booklet, school IEC,formation . and their documentation through still photography in different Gram Panchayat under Murshidabad Division P.H.E. Dte. | 484/MURD | 25/02/2025 | 30 | IMAGIN | 39.23 | 0 | 0 | 100
5250 | MURSHIDABAD | Murshidabad Division | Assessment of total Household and Total FHTC Provided (Functional/ Non Functional) by conducting field Survey in different Villages through mobile application associated with PHED website engaging expart personnel's. , SM/18195 | Support-MIS | Assessment of total Household and Total FHTC Provided (Functional/ Non-Functional) as per field Survey and Community mobilization for taking up tap connection of the different Village of Berhampore Sub-Division, under Murshidabad Division by online updating in Google Spread Sheet. | 949/MURD | 05/04/2023 | 30 | IMAGIN | 89.36 | 42.33 | 100 | 100
5251 | MURSHIDABAD | Murshidabad Division | Assessment of total Household and Total FHTC Provided (Functional/ Non Functional) by conducting field Survey in different Villages through mobile application associated with PHED website engaging expart personnel's. , SM/18195 | Support-MIS | Assessment of total Household and Total FHTC Provided (Functional/ Non-Functional) as per field Survey and Community mobilization for taking up tap connection of the different Village of Islampur Sub-Division, under Murshidabad Division by online updating in Google Spread Sheet | 948/MURD | 05/04/2023 | 30 | IMAGIN | 86.95 | 52.53 | 100 | 100
5252 | MURSHIDABAD | Murshidabad Division | Assessment of total Household and Total FHTC Provided (Functional/ Non Functional) by conducting field Survey in different Villages through mobile application associated with PHED website engaging expart personnel's. , SM/18195 | Support-MIS | Assessment of total Household and Total FHTC Provided (Functional/ Non-Functional) as per field Survey and Community mobilization for taking up tap connection of the different Village of Berhampore Block &Kandi Block by online updating in Google Spread Sheet. | 950/MURD | 05/04/2023 | 30 | S.S.INFRASTRUCTURE | 60.33 | 46.3 | 100 | 100
5253 | MURSHIDABAD | Murshidabad Division | Assessment of total Household and Total FHTC Provided (Functional/ Non Functional) by conducting field Survey in different Villages through mobile application associated with PHED website engaging expart personnel's. , SM/18195 | Support-MIS | Assessment of total Household and Total FHTC Provided (Functional/ Non-Functional) as per field Survey and Community mobilization for taking up tap connection of the different Village of Kandi Sub-Division by online updating in Google Spread Sheet under Murshidabad Division, PHE Dte. | 961/MURD | 05/04/2023 | 30 | IMAGIN | 64.62 | 47.31 | 100 | 100
5254 | MURSHIDABAD | Murshidabad Division | Assessment of total Household and Total FHTC Provided (Functional/ Non Functional) by conducting field Survey in different Villages through mobile application associated with PHED website engaging expart personnel's. , SM/18195 | Support-MIS | Assessment of total Household and Total FHTC Provided (Functional/ Non-Functional) as per field Survey and Community mobilization for taking up tap connection of the different Village of Jangipur Sub-Division by online updating in Google Spread Sheet under Murshidabad Division, PHE Dte. | 960/MURD | 05/04/2023 | 30 | S.S.INFRASTRUCTURE | 101.4 | 88.21 | 100 | 100
5255 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | supplying & delivering chemical/ reagents and glassware to Sevabrata and Jangipur water testing lab under Tno- 352/20-21/EE |  | 11/12/2020 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.87 | 0 | 0 | 0
5256 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | supplying & delivering chemical/ reagents and glassware to Jalangi and Domkal SD nos water testing lab under Tno- 350/20-21/EE |  | 11/12/2020 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.86 | 0 | 0 | 0
5257 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | supplying & delivering chemical/ reagents and glassware to different water testing lab under Tno- 351/20-21/EE |  | 11/12/2020 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.9 | 0 | 0 | 0
5258 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | Continuation w/o for supplying & delivering chemical/ reagents and glassware to 20 nos water testing lab under Tno- 353/20-21/EE |  | 11/12/2020 | 0 | A.S. COMPUTER | 4.88 | 0 | 0 | 0
5259 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | supplying & delivering chemical/ reagents and glassware to Ambedkar and salar water testing lab under Tno- 349/20-21/EE |  | 11/12/2020 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.85 | 0 | 0 | 0
5260 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | COMPUTER OPERATOR BILL OF AE-ISD, TNO- 41/19-20/AEISD | 506/NP | 23/03/2021 | 0 | MINA DAS | 0.22 | 0 | 0 | 0
5261 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | CONT ORDER FOR SUPPLYING & DELIVERY OF LABORATORY CHEMICALS AND GLASS WARE...W.T LABS PHE DTE, TNO- 465/20-21/EE | 469/W | 03/03/2021 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.78 | 0 | 0 | 0
5262 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. |  | 18/03/2021 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.9 | 0 | 0 | 0
5263 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | Cont. Order of Supply, delivery of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad., TNO- 755/20-21/EE | 10/CHE | 22/04/2021 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.9 | 0 | 0 | 0
5264 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | Holding Awarness programme/campaingning programms at lalgolal GP Billborakopara GP Amdahara GP Kolan GP Kantanagar Mahammadpur GP Amarkundu GP & Shibpur GP in connection with Functional Household Tap Connection FHTC under Murshidabad Div PHE DTE. Tender no-576 of 20-21 by EE | 458/W | 24/02/2021 | 0 | IMAGIN | 3.51 | 0 | 0 | 0
5265 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. |  | 18/03/2021 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 3.52 | 0 | 0 | 0
5266 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | Restoration of Road for laying of different dia UPVC/DI/CI pipeline at KANTANAGAR area under Improvement work of Kantanagar W/S Scheme under LSD PHE DTE. Tender no-14 of 20-21 by AE/LSD | 458/W | 24/02/2021 | 0 | SK CONSTRUCTION (NAJIR SK.) | 1.23 | 0 | 0 | 0
5267 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad., |  | 18/03/2021 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.87 | 0 | 0 | 0
5268 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | Cont. Order of Supply, delivery of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad., TNO- 754/20-21/EE | 10/CHE | 22/04/2021 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 3.52 | 0 | 0 | 0
5269 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | Cont. Order of Supply, delivery of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad., TNO- 756/20-21/EE | 10/CHE | 22/04/2021 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 4.87 | 0 | 0 | 0
5270 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | Day to Day O & M of 3205 KLD and 5820 KLD water treatme t plant of Mahyampur W/S Scheme and surface based W/S Scheme Bweldanga Municipality mouza W/S Scheme under MURD under BSD PHE DTE. period from 01.09.20 to 31.08.21 Tender no-49 of 20-21 by SE/MC | 458/W | 24/02/2021 | 0 | RAY ENTERPRISES | 16.35 | 0 | 0 | 0
5271 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | COMPUTER OPERATOR BILL OF AE LSD, TNO- 28/20-21/EE | 506/NP | 23/03/2021 | 0 | A.K.A ENTERPRISE | 0.46 | 0 | 0 | 0
5272 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | CONT ORDER FOR SUPPLYING & DELIVERY OF LABORATORY CHEMICALS AND GLASS WARE...W.T LABS PHE DTE, TNO- 466/20-21/EE | 469/W | 03/03/2021 | 0 | MS MANDAL SCIENTIFIC AND WATER ANALYSIS | 3.52 | 0 | 0 | 0
5273 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | CLAIM OF REMUNERATION OF LAB PERSONNEL FOR MONTH FEBRUARY-2021 | 506/NP | 23/03/2021 | 0 | R.N CLUB LAB | 0.33 | 0 | 0 | 0
5274 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | Further to work order for Extension o Llaying of UPVC pipeleine from Mohidul Molla houses to Jamal Sk house of Jagaipur W/S Scheme under Berhampore Sub Division PHE DTE. Tender no-588 of 20-21 by EE | 458/W | 24/02/2021 | 0 | DEBIPROSAD DE | 4.98 | 0 | 0 | 0
5275 | MURSHIDABAD | Murshidabad Division | Procurement of chemicals & consumables, glassware etc. required for smooth running of laboratories in different blocks under Murshidabad Div, PHE Dte. in the dist of Murshidabad. , SM/06630 | Support-WQMSP | Supplying and Delivery of laboratory Chemicals/reagents and Glassware to 19(Nineteen) nos. Water Testing Laboratory for National Rural Drinking water Quality Testing Monitoring & Surveillance programme related to Operation & Maintenance in the State of West Bengal under Murshidabad Division, P.H.E.Dte. | 1207/MURD | 10/05/2021 | 90 | M/S MANDAL SCIENTIFIC & WATER ANALYSIS. | 26.37 | 19.67 | 100 | 0
5276 | MURSHIDABAD | Berhampore Division I | Procurement computers and peripherals for 3 Water Testing Laboratories, Divisional office and sub divisional office under Berhampore Division-I. P.H.Engineering Dte. , SM/16268 | Support-MIS | Purchase HP INTEL i5 12600 16GB /1000 GB HDD/Windows 11 Professional for the office of the Executive Engineer, Berhampore Divsion-I, PHE Dte | BP-2023-24-153 | 11/10/2023 | 0 | IONET | 4.45 | 0 | 0 | 0
5277 | MURSHIDABAD | Berhampore Division I | Procurement computers and peripherals for 3 Water Testing Laboratories, Divisional office and sub divisional office under Berhampore Division-I. P.H.Engineering Dte. , SM/16268 | Support-MIS | PURCHASE VOLTRIQ SMART TELEVISION TV 50 INCH ULTRA HD FOR THE OFFICE OF THE EXECUTIVE ENGINEER, BERHAMPORE DIVISION-I PHE DTE | BP-2023-24-152 | 11/10/2023 | 0 | NEXUS ENTERPRISE | 0.38 | 0 | 0 | 0
5278 | MURSHIDABAD | Berhampore Division I | Procurement computers and peripherals for 3 Water Testing Laboratories, Divisional office and sub divisional office under Berhampore Division-I. P.H.Engineering Dte. , SM/16268 | Support-MIS | Supply Canon IR C3226 SL No.32V 07047 DADF BA1 SL nO.4TU 60971 for the office of the Executive Engineer, Berhampore Division-I, PHE Dte. | BP-2023-24-91 | 08/08/2023 | 0 | IONET | 2.87 | 0 | 0 | 0
5279 | MURSHIDABAD | Berhampore Division I | Procurement computers and peripherals for 3 Water Testing Laboratories, Divisional office and sub divisional office under Berhampore Division-I. P.H.Engineering Dte. , SM/16268 | Support-MIS | Supply 4 nos. HP AMD Ryzen 5.14 inch Laptop (Windows Professional) Model HP 445 G9 RS 5625U Win11P 8512SSD35 wifi 14"FHD for the office of the Executive Engineer, Berhampore Division-I, PHE Dte. | BP-2023-24-90 | 08/08/2023 | 0 | IONET | 3.2 | 0 | 0 | 0
5280 | MURSHIDABAD | Berhampore Division I | Procurement computers and peripherals for 3 Water Testing Laboratories, Divisional office and sub divisional office under Berhampore Division-I. P.H.Engineering Dte. , SM/16268 | Support-MIS | Supply 5 nos. HP Intel Core IS 12400 8GB/1000 GB HDD/ Windows 11 Home Model HP 280 G9SF is 12400 Win11H 8512SSD13 21.5 for the office of the Executive Engineer, Berhampore Division-I, PHE Dte. | BP-2023-24-92 | 08/08/2023 | 0 | EASY DAY ENTERPRISE | 4.09 | 0 | 0 | 0
5281 | MURSHIDABAD | Berhampore Division I | Procurement computers and peripherals for 3 Water Testing Laboratories, Divisional office and sub divisional office under Berhampore Division-I. P.H.Engineering Dte. , SM/16268 | Support-MIS | Procurement of 03 no hp Intel Core i5 12400 8 GB/ 0 GB HDD/ Windows 11 Professional. | BP-2024-25-139 | 21/08/2024 | 0 | IONET | 2.22 | 0 | 0 | 0
5282 | MURSHIDABAD | Berhampore Division I | Procurement computers and peripherals for 3 Water Testing Laboratories, Divisional office and sub divisional office under Berhampore Division-I. P.H.Engineering Dte. , SM/16268 | Support-MIS | PURCHASING HP MULTIFICATION MACHINES MTC ON SITE OEM WARRANTY 5 YEAR | BP-2023-24-251 | 30/01/2024 | 0 | EASY DAY ENTERPRISE | 3.04 | 0 | 0 | 0
5283 | MURSHIDABAD | Berhampore Division I | Procurement computers and peripherals for 3 Water Testing Laboratories, Divisional office and sub divisional office under Berhampore Division-I. P.H.Engineering Dte. , SM/16268 | Support-MIS | PURCHASING HP INTEL CORE I5 10500 8GB /1000 GB HDD/WINDOWS 11 HOME | BP-2023-24-250 | 30/01/2024 | 0 | EASY DAY ENTERPRISE | 2.99 | 0 | 0 | 0
5284 | MURSHIDABAD | Berhampore Division I | Procurement computers and peripherals for 3 Water Testing Laboratories, Divisional office and sub divisional office under Berhampore Division-I. P.H.Engineering Dte. , SM/16268 | Support-MIS | Procurement of 01 no Canon Multification Machines Mfm, on siteOEM Warranty 01 year, Model : iR C3326 with Media Kit DADF with extra tray, Toner. | BP-2024-25-167 | 23/09/2024 | 0 | IONET | 2.7 | 0 | 0 | 0
Total | [9 empty] | 408882.52 | 84068.92 | 20.56