## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | BIRBHUM | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area , SM/06944 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre and left out Household at Narayanpur and Daronda village existing distribution System within Nachansaha W/S Scheme and Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | 402/BSD | 25/10/2021 | 10 | NAZIR HOSSAIN | 0.96 | 0 | 0 | 0
2 | BIRBHUM | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area , SM/06944 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Saldanga, Dhalla, Lakshmipur, Daranda & Ramnagar of Daranda w/s Scheme at Illambazar Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No.10) | 1024/BHM | 04/11/2020 | 45 | S.S. BHATTACHARJEE. | 13.82 | 5.45 | 100 | 35
3 | BIRBHUM | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area , SM/06944 | Retrofitting | Hiring of SWIFT DIZER (Diesel) or equivalent luxury car for office of the Assistant Engineer, Nalhati Sub - Division under Birbhum Division, PHE Dte. (Period from 01.04.2023 to 30.09.2023) 183-Days. | 130/AE/NSD | 31/03/2023 | 183 | JOY CHAND MAL | 0.86 | 0.77 | 66.73 | 85
4 | BIRBHUM | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area , SM/06944 | Retrofitting | Continution work for Supply of one no. Diesel Motor Cab/Maxi Cub (Air Condition) on hire basis under the Executive Engineer Birbhum Division P.H.E Dte (Period From 01.05.2023 to 31.10.2023) | 1618/BHM | 27/04/2023 | 183 | PREMANANDA ROY BISWAS | 0.96 | 0 | 0 | 60
5 | BIRBHUM | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area , SM/06944 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre and left out Household at Narayanpur and Daronda village existing distribution System within Nachansaha W/S Scheme and Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | 402/ BSD | 25/10/2021 | 10 | NAZIR HOSSAIN | 0.96 | 0.66 | 100 | 100
6 | BIRBHUM | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area , SM/06944 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Illambazar (Illambazar & Daronda) within Ruppur & Illambazar G.P.under Bolpur Sub-Division within Birbhum Division, PHED | 16/BSD | 11/01/2022 | 15 | GANAPATI ENGINEERING CORP. | 1.97 | 0 | 0 | 48
7 | BIRBHUM | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area , SM/06944 | Retrofitting | Replacement of UPVC pipe line damaged due to widening of road from Bubahat More towards Chella road along with extension of UPVC pipe line for habitation of Daranda Palpara, Chasapara, Malpara, Bauripara, Darjipara, Suripara, High School Para etc. for Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. 01) | 241/BSD | 16/07/2021 | 30 | S.S. BHATTACHARJEE. | 4.99 | 4.98 | 100 | 100
8 | BIRBHUM | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area , SM/06944 | Retrofitting | Replacement of damaged UPVC pipe line due to widening of road from Bubahat More towards Chella along with extension of UPVC pipe line for the habitation of Halsidanga, Chella, etc. of Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | 457/BSD | 13/12/2021 | 30 | S.S. BHATTACHARJEE. | 4.34 | 4.34 | 100 | 50
9 | BIRBHUM | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area , SM/06944 | Retrofitting | Providing Household Tap Connection (FHTC) at Daronda Mouja ( J.L No 129) at different Location from existing distribution system within the command area of Daronda and adjoining Mouza W/S Scheme at Illambazar Block under Bolpur Sub-Division P.H.E Dte within Birbhum Division P.H.E Dte. | 1087/BHM | 05/09/2020 | 30 | S.S. BHATTACHARJEE. | 4.71 | 9.38 | 200 | 0
10 | BIRBHUM | Birbhum Division | Retrofitting works of Daronda (Phase-II) water supply scheme under at Illambazar Block for providing Functional Household Tap Connection(FHTC) within command area , SM/06944 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chella, Ramnagar, Bonovilla, Lakshipur, Daronda, Dhalla, Saldanga, Usurdihi, Ushahar etc. in different locations under Daronda Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.1) | 1569/BHM | 26/07/2022 | 60 | HOQUEDAR ALI | 43.32 | 34.53 | 72.09 | 100
11 | BIRBHUM | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area , SM/06947 | Retrofitting | Allied works of extension pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Sakadda (in the habitation SERPUR AND SAKADDA) of Khujutipara W/S Scheme at Nanoor Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 306/BSD | 19/08/2021 | 30 | MS B N ENTERPRISES | 4.9 | 7.07 | 200 | 100
12 | BIRBHUM | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area , SM/06947 | Retrofitting | Survey for Functional Household Tap Connection (FHTC) at different School and Anganwadi Centre in Labpur Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 335/ BSD | 06/09/2021 | 15 | NAZIR HOSSAIN | 0.1 | 0 | 0 | 50
13 | BIRBHUM | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area , SM/06947 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Nabasta of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (2nd Call) (Sl. No.24) | 31/BHM | 13/01/2021 | 60 | MANAS KUMAR MONDAL | 28.93 | 0 | 0 | 45
14 | BIRBHUM | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area , SM/06947 | Retrofitting | Survey for Functional Household Tap Connection (FHTC) at different School and Anganwadi Centre in Nanoor Block, Bolpur-Sriniketan Block (Part) under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 312/ BSD | 25/08/2021 | 15 | NAZIR HOSSAIN | 0.1 | 0.1 | 100 | 100
15 | BIRBHUM | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area , SM/06947 | Retrofitting | Survey for Functional Household Tap (FHTC) at different School and Anganwadi Centre in Labpur Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 335/ BSD | 06/09/2021 | 15 | NAZIR HOSSAIN | 0.1 | 0.1 | 100 | 50
16 | BIRBHUM | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area , SM/06947 | Retrofitting | Allied works of extension pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages KHUJUTIPARA of Khujutipara W/S Scheme at Nanoor Block under Bolpur Sub-Division within Birbhum Division, PHED. | 373/ BSD | 05/10/2021 | 30 | M/S BUILDWELL | 3.82 | 3.81 | 100 | 100
17 | BIRBHUM | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area , SM/06947 | Retrofitting | Retrofitting of pipe lines from Khujutipara Fishary Market to Smashan Kali Mandir, Khujutipar on Basapara-Nanoor Road for Providing Functional Household Tap Connection (FHTC) from existing distribution system at the village Sakadda within the command area of Khujutipara Water Supply Scheme (Part -B) of Bolpur Sub-Division under Birbhum Division, PHED. (Sl. - 08) | 452/BSD | 13/12/2021 | 30 | MANAS KUMAR MONDAL | 3.96 | 3.96 | 100 | 100
18 | BIRBHUM | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area , SM/06947 | Retrofitting | Retrofitting of pipe lines From OHR to Khujutipara Fishary Market, Khujutipara for Providing suficient water to Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages SAKKADA of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Part -A). | 426/BSD | 22/11/2021 | 30 | MANAS KUMAR MONDAL | 4.85 | 4.85 | 100 | 100
19 | BIRBHUM | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area , SM/06947 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Sakadda of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (Sl. No.05) | 1459/BHM | 12/11/2020 | 60 | MS B N ENTERPRISES | 27.38 | 40.14 | 200 | 0
20 | BIRBHUM | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area , SM/06947 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Chhatingram of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (Sl. No.6) | 1422/BHM | 04/11/2020 | 45 | INDRAJIT DAS | 15.08 | 22.36 | 200 | 0
21 | BIRBHUM | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area , SM/06947 | Retrofitting | Allied works of extension pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Nabasta (in the habitation NABASTA) Khujutipara W/S Scheme at Nanoor Block within Bolpur Sub-Division under Birbhum Division P.H.E. Dte. (Mouja: Nabastha Node point 01 to 02) | 327/BSD | 01/09/2021 | 30 | MANAS KUMAR MONDAL | 4.84 | 9.22 | 200 | 0
22 | BIRBHUM | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area , SM/06947 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Khujutipara of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (Sl. No.07) | 1460/BHM | 12/11/2020 | 45 | MS BUILDWELL | 21.21 | 37.75 | 200 | 0
23 | BIRBHUM | Birbhum Division | Retrofitting works of Khujutipara (Phase-II) water supply scheme under Nanoor Block for providing Functional Household Tap Connection(FHTC) within the command area , SM/06947 | Retrofitting | Allied works of extension of pipe line for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages of Baitara (in the habitation Suchpur & Baitara) of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. | 376/BSD | 05/10/2021 | 30 | M/S KRIPASINDHU GHOSH & CO. | 4.85 | 0 | 0 | 100
24 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) , SM/06743 | Retrofitting | Providing Tap Connection for Existing School & AWC in Naryanpur PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. | 278/RSD | 16/07/2021 | 10 | SHIB GANGA CONSTRUCTION | 0.5 | 0 | 0 | 0
25 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) , SM/06743 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Balia Mrityunjoypur of Narayanpur w/s Scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl. No.3) | 1706 /BHM | 23/12/2020 | 60 | SANJUKTA ENGINEERS | 36.44 | 17.42 | 100 | 100
26 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) , SM/06743 | Retrofitting | Additional FHTC works from existing distribution system at Narayanpur mouza within Narayanpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-30) | 273/RSD | 16/08/2022 | 30 | SUNIL RABI DAS | 4.85 | 4.75 | 100 | 100
27 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) , SM/06743 | Retrofitting | Additional FHTC works from existing distribution system at Narayanpur habitation within Narayanpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-31) | 277/RSD | 18/08/2022 | 30 | SUNIL RABI DAS | 4.89 | 4.83 | 100 | 100
28 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) , SM/06743 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Narayanghati w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-2) | 1915/BHM | 24/11/2021 | 60 | TAPAN KUMAR DATTA | 82.11 | 0 | 0 | 53
29 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) , SM/06743 | Retrofitting | Sinking of o1 (one) No 200mm dia.X 42.0 mtr deep Tube Well with UPVC pipe & strainer for Narayanpur W/s scheme under Birbhum Division, P.H.E. Dte. | 30/RSD | 04/01/2022 | 30 | ISLAM CONSTRUCTION | 2.92 | 0 | 0 | 50
30 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) , SM/06743 | Retrofitting | Laying Bypass UPVC Pipe line from CWR to Suripara more for providing drinking water Hattala surrounding Area of Narayanpur W/S Scheme under Rampurhat Sub-Division, P.H.E. Dte within Birbhum Division, P.H.E. Dte. (Sl. No.2) | 2069/BHM | 13/12/2021 | 60 | ISLAM CONSTRUCTION | 13.26 | 0 | 0 | 50
31 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Narayanpur PWSS(Phase-I) , SM/06743 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Balia Mrityunjoypur of Narayanpur w/s Scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl. No.3) | 1706/BHM | 23/12/2020 | 60 | SANJUKTA ENGINEERS | 36.44 | 50.02 | 200 | 27
32 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. , SM/08896 | Retrofitting | Providing Functional Household Tap Connection(FHTC) at Lalitakundu Purba Par within the command area of Bishnupur Water Supply Scheme under RWS Birbhum Sub-Division within Birbhum Division, PHE Dte. (Sl. No.08) | 137/BH | 15/06/2022 | 20 | BIJOY KUMAR CHOUDHURY | 3.56 | 3.54 | 100 | 100
33 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. , SM/08896 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur Water Supply Scheme within Rampurhat Sub-Division under Birbhum Division, PHE Dte¿ (Sl. No.2) | 2033/ BHM | 09/12/2021 | 60 | TAPAN KUMAR DATTA | 94.18 | 67.27 | 100 | 40
34 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. , SM/08896 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Baroipara and its adjoining area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | 177/BH | 03/11/2021 | 15 | TAPAN ENTERPRISE | 4.83 | 0 | 0 | 50
35 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. , SM/08896 | Retrofitting | Providing Functional Household Tap Connection(FHTC) at Baswa Lat Para within the command area of Bishnupur Water Supply Scheme under RWS Birbhum Sub-Divition within Birbhum Division PHE Dte.(Sl. No.09) | 138/BH | 15/06/2022 | 20 | BIJOY KUMAR CHOUDHURY | 3.6 | 3.58 | 100 | 50
36 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. , SM/08896 | Retrofitting | Distribution System including providing Functional Household Tap Connection(FHTC) at Lalitakundu Paschim Par within the command area of Bishnupur Water Supply Scheme Under RWS Birbhum Sub-Division,within Birbhum Division,PHE Dte.(Sl. No.07) | 136/BH | 15/06/2022 | 30 | BIJOY KUMAR CHOUDHURY | 4.71 | 4.69 | 100 | 50
37 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BISHNUPUR (PHASE-II) WATER SUPPLY SCHEME of Rampurhat-II Block under Birbhum Division, PHE Dte. , SM/08896 | Retrofitting | Material Requisition To Resource Division | 218/BHM | 02/02/2022 | 0 | Resource Division | 26.49 | 0 | 0 | 0
38 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. , SM/08898 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tarapit Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte. (Sl. No.11) | 1770/BHM | 29/10/2021 | 60 | SUNIL RABI DAS | 80.28 | 75.81 | 100 | 100
39 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. , SM/08898 | Retrofitting | Providing FHTC from existing distribution system with Allied works at Karkaria mouza within Improvement of Tarapith w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-23) | 278/RSD | 18/08/2022 | 30 | SHIB GANGA CONSTRUCTION | 4.99 | 4.99 | 100 | 100
40 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. , SM/08898 | Retrofitting | Providing FHTC from existing distribution system with Allied works at Tarapur mouza within Improvement of Tarapith w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-24) | 280/RSD | 22/08/2022 | 30 | SHIB GANGA CONSTRUCTION | 4.98 | 4.98 | 100 | 100
41 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. , SM/08898 | Retrofitting | Laying of Distribution Main pipeline through crossing of PWD road at Karkaria more East side by adopting Jack Pushing method for Improvement of Tarapith PWSS under Rampurhat Sub-Division, PHE Dte. | 08/RSD | 04/01/2022 | 15 | SUNIL RABI DAS | 4.14 | 0 | 0 | 100
42 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TARAPITH WATER SUPPLY SCHEME of RAMPURHAT-II Block under Birbhum Division, PHE Dte. , SM/08898 | Retrofitting | Laying, joining and interconnecting the tubewells (5 nos.) to OHR with HDPE pipes and Specials including Bypass arrangement for Improvement of Tarapith piped W/S Scheme under Birbhum Division, PHE Dte. (Sl. No.2) | 1333/BHM | 18/08/2021 | 45 | SACHIN KUMAR SARKAR | 16.23 | 0 | 0 | 100
43 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sekhpur PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. , SM/09363 | Retrofitting | Sinking of 01 Nos (3 rd ) Tubewell 200mm dia 96 m. deep tube well fitted with PVC pipe and fiber glass Strainer at Sekhpur PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 106/RSD | 07/03/2022 | 30 | ISLAM CONSTRUCTION | 4.98 | 0 | 0 | 100
44 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sekhpur PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. , SM/09363 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sekhpur under Sekhpur Water Supply Scheme within Birbhum Division, PHE Dte.¿ (Sl. No.6) | 1611/BHM | 28/07/2022 | 60 | M/S KRIPASINDHU GHOSH & CO. | 95.28 | 51.97 | 50.58 | 100
45 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sekhpur PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. , SM/09363 | Retrofitting | Rising main with DI pipe line for SHEKPUR Piped Water Supply Scheme under Rampurhat Sub-Division under Birbhum Division, PHE Dte. | 183/RSD | 02/05/2022 | 30 | AJIMUL ISLAM | 3.98 | 0 | 0 | 100
46 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sekhpur PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. , SM/09363 | Retrofitting | Retrofitting works for Providing Balance Functional Household Tap Connection (FHTC) by Sinking of 2 nos. additional Tubewells at Rukumpur & Dumra mouza (200mm dia all through & 150 Mtr Deep) along with Connecting Line, Boundary wall & related works for Sekhpur Piped Water Supply Scheme under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 1027/BHM | 15/03/2024 | 451 | GOLAM RASUL | 86.37 | 0 | 0 | 0
47 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. , SM/09491 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kurumgram Water Supply Scheme within Nalhati Sub-Division Birbhum Division, PHE Dte. (2nd Call) (Sl. No.13) | 2109/BHM | 17/12/2021 | 60 | M/S MD AMINUL ISLAM | 76.13 | 76.13 | 100 | 100
48 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. , SM/09491 | Retrofitting | Replacement including extension of pipe line with FHTC to different habitations of kurumgram village including 200 mm PVC tube well & restoration of roads at Kurumgram Water Supply Scheme under Nalhati Sub-Division within Birbhum Division PHE Dte. | 1429/BHM | 05/07/2022 | 60 | MD SURAJ ALI | 40.52 | 30.97 | 76.43 | 95
49 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. , SM/09491 | Retrofitting | Surging of 2 nos. existing Tube wells and other ancillary works at Kurumgram Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | 694/AE/NSD | 30/12/2021 | 15 | MD SURAJ ALI | 0.94 | 0 | 0 | 100
50 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) with in the Command Area of KURUMGRAM Water supply scheme under Birbhum Division P.H.E. Dte. , SM/09491 | Retrofitting | Sinking of 200 mm dia & 87mtr.deep Tube well fitted with PVC pipe and fibre glass Strainer of Head Work site of Kurumgram Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 361/AE/NSD | 21/07/2022 | 45 | MD SURAJ ALI | 4.84 | 0 | 0 | 100
51 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health Centre, Govt. institution & Household of Habitation-Damonpur, Mouja Ramkantapur (139) from existing distribution system within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) Zone - X & Zone - XIII within Sian Muluk G.P. of Bolpur Sub -Division under Birbhum Division, PHED. | 447 /BSD | 10/12/2021 | 30 | SUBHRADIP SARKAR | 4.85 | 5.72 | 100 | 100
52 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone- XI Indo -German Water Supply Scheme in Bolpur Sub-Division within Birbhum Division, PHED. | 2165/BHM | 24/12/2021 | 60 | SYED HASMAT ALI | 26.72 | 16.29 | 60.96 | 80
53 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at MULUK (121) village and Arazi Muluk (125) Village (Part) within the command area of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) (Zone- XIII) under Bolpur Sub-Division within Birbhum Division, PHED. | 385/BSD | 07/10/2021 | 30 | SYED HASMAT ALI | 4.85 | 4.71 | 100 | 100
54 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone-XIII (Indo-German) Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte (Sl. No. 09) | 2163/BHM | 24/12/2021 | 60 | BISWARUP GHOSH | 30.65 | 28.73 | 100 | 99
55 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) at Zone - XII of Sian Muluk G.P. under Bolpur Sub-Division within Birbhum Division, PHED | 400/BSD | 25/10/2021 | 10 | JAYANTA BARAL | 0.96 | 0.96 | 100 | 100
56 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre from existing distribution System of (Zone ¿ VIII & Zone ¿ IX) under Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHED | 398/BSD | 25/10/2021 | 10 | GANAPATI ENGINEERING CORP. | 0.97 | 0.76 | 100 | 100
57 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone-IX (Indo German) water supply w/s Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.11) | 1659 / BHM | 30/09/2021 | 60 | HIMANGSU SEKHAR SARKAR | 37.25 | 15.28 | 100 | 100
58 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Survey for Functional Household Tap Connection (FHTC) at various places within coverage area of Bolpur Externally Aided Project Water Supply Scheme (Zone-VII) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No. - 02) | 239/BSD | 16/07/2021 | 30 | M/S HORIZEN | 0.97 | 0 | 0 | 0
59 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Leftout School & Aganwadi Centre with extension of pipeline from existing distribution system within (Zone-VII) of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 07). | 70/BSD | 03/03/2022 | 15 | MS AD ENTERPRISE | 2.53 | 0 | 0 | 100
60 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) at Zone - X and Zone - XIII of Sian Muluk G.P. under Bolpur Sub-Division within Birbhum Division, PHED. | 401/BSD | 25/10/2021 | 10 | SUBHRADIP SARKAR | 0.97 | 0 | 0 | 0
61 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Survey for Functional Household Tap Connection (FHTC) at various places within coverage area of Bolpur Externally Aided Project Water Supply Scheme (Zone-VI) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No. - 01) | 237/BSD | 16/07/2021 | 30 | M/S HORIZEN | 0.97 | 0 | 0 | 100
62 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Survey for Functional Household Tap Connection (FHTC) at various places within coverage area of Bolpur Externally Aidded Project Water Supply Scheme (Zone-VI) under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 231/BSD | 07/07/2021 | 15 | M/S HORIZEN | 0.1 | 0.1 | 100 | 100
63 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) at Zone - XI of Sian Muluk G.P.under Bolpur Sub-Division within Birbhum Division, PHED. | 399/BSD | 25/10/2021 | 10 | SK.RUHUL AMIN | 0.97 | 0.65 | 100 | 100
64 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Tap Connection (FHTC) from existing distribution System in in Sian MULUK G.P. (Vill. Baidyanathpur, Dwarkanathpur, Purba Islampur, Sahajpur, Sian) within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) (Zone - XI) under Bolpur Sub-Division within Birbhum Division, PHED. | 382/BSD | 07/10/2021 | 30 | ARABINDA GHOSH | 4.83 | 4.82 | 100 | 100
65 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Survey for Functional Household Tap Connection (FHTC) at Gayeshpur and Bergram under Sian-Muluk Gram Panchayet within coverage area of Bolpur Externally Aided Project Water Supply Scheme (Zone - XI) under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 310/BSD | 24/08/2021 | 20 | IMAGIN | 0.38 | 0.38 | 100 | 100
66 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Surul Mouza, JL : 104 (Habitation - MOLDANGA) within the command area of for Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) Zone - VIII under Bolpur Sub-Division within Birbhum Division, PHED. | 380/BSD | 07/10/2021 | 30 | PRATICK KUMAR GHOSH | 4.22 | 3.38 | 100 | 100
67 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in SHYAMBATI Mouza JL : 67 (Habitation - Shyambati, Subhaspally, Munnapara etc.) within the command area of for Augmentation of Bolpur Water Supply Sanitation & Health Education Project ( Indo- German ) Zone - IX under Bolpur Sub-Division within Birbhum Division, PHED. | 383/BSD | 07/10/2021 | 30 | B. B. CONSTRUCTION | 4.69 | 4.3 | 100 | 100
68 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Tap Connection (FHTC) at School & Anganwadi Centre from existing distribution System within (Zone ¿ VII) of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHED. | 397/BSD | 25/10/2021 | 10 | MS AD ENTERPRISE | 0.97 | 2.8 | 100 | 100
69 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at habitation - Ramchandrapur, Village -Raipur, G.P. - Raipur-Supur from existing distribution system within the command area of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) (Zone-VI) under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 05). | 75/BSD | 03/03/2022 | 30 | MAA KANKALI ENTERPRISE | 4.83 | 4.7 | 100 | 100
70 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Additional remaining work of C.W.R .and development of land of C.W.R. site at Rasulpur (Near Ajoy River Bank) for Augmentation of Bolpur Water Supply, Sanitation & Health Education Project (Indo-German). Zone - X under Bolpur Sub-Division within Birbhum Division PHED. (Sl. No. - 12) | 456/BSD | 13/12/2021 | 30 | MS B N ENTERPRISES | 4.14 | 0 | 0 | 100
71 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone - XII Indo German Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No. 08) | 78/BHM | 18/01/2022 | 60 | SOUMEN CHATTERJEE | 26.72 | 25.55 | 100 | 100
72 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone - VIII Indo German Water Supply Scheme in Bolpur Sub-Division undr Birbhum Division PHED. (Sl. 15) | 597/BHM | 21/03/2022 | 45 | RADHARANI ENTERPRISE | 25.23 | 22.67 | 100 | 100
73 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at habitation - Raipur Village -Raipur, G.P. - Raipur-Supur from existing distribution system within the command area of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) (Zone-VI) under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 06). | 76/BSD | 03/03/2022 | 30 | SEKH MAMTAZ HOSSAIN | 4.77 | 4.63 | 100 | 100
74 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Survey for Functional Household Tap Connection (FHTC) at various places within coverage area of Bolpur Externally Aided Project Water Supply Scheme (Zone - X) (2nd Phase : - Jay Krishnapur, Ramakantapur, Ramganj, Gulandi, Gahara etc.) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (2nd Call). (Sl. No.: 09) | 347/BSD | 15/09/2021 | 30 | IMAGIN | 0.97 | 0.97 | 100 | 100
75 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone-VII Indo German Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.14) | 578/bhm | 17/03/2022 | 45 | ASHA ENTERPRISE | 25.13 | 25.02 | 100 | 100
76 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at NURPUR (Part) & Gheropara (Part) with extension of pipeline from existing distribution system within (Zone-VII) of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, P.H.E. Deptt. (Sl. No.: 03). | 252/BSD | 04/07/2022 | 30 | CHAYAN KUMAR MONDAL | 4.81 | 4.81 | 100 | 100
77 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from the existing distribution system within the command area of Mouja Durgapur (143), Gitgram (144), Bara Simulia (145), Chota Simulia (145), Dakshin Gobindapur (151), Ramganja (152) & Panchshoa (142) etc. of Zone - X under Augmentation of Bolpur Water Supply, Sanitation & Health Education Project (Indo - German) in Bolpur Sub-Division within Birbhum Division PHE Dte. (Sl. No. - 3) | 1469/BHM | 11/07/2022 | 60 | SACHIN KUMAR SARKAR | 38.19 | 22.88 | 67.99 | 100
78 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Retrofitting of pipe lines at Laichili Pukurpara, Mirdhapara, Mosjidpara and Korapara of GAYESHPUR Mouja for Providing sufficient water to Functional Household Tap Connection (FHTC) from existing distribution system for Augmentation of Bolpur Water Supply, Sanitation & Health Education Project (Indo-German), under Bolpur Sub-Division within Birbhum Division, P.H.E. Deptt. (Sl. No.: 04). | 258/BSD | 07/07/2022 | 30 | PRATICK KUMAR GHOSH | 4.82 | 4.8 | 100 | 100
79 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Habitation- Kankutia, village -KANKUTIA, G.P. - Raipur-Supur from existing Distribution System within the command area of Augmentation for Bolpur Water Supply, Sanitation & Health Education Project (Indo-German) (Zone-VI) under Bolpur Sub-Division within Birbhum Division, Public Health Engineering Department. (Sl. No.: 05). | 308/BSD | 16/08/2022 | 30 | SEKH MAMTAZ HOSSAIN | 4.81 | 4.69 | 100 | 100
80 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Laying of Rising Main pipeline from Tube-well no. - II to new O.H.R. of Layekbazar with D.I. (K-9) pipe including inter-connection and extension of pipe line at Paruldanga, Choto Canalpar, Paruldanga Nishapati Colony, Nildanga Adibasipara, Rintoladanga (Dangapara), Jharnadanga etc. for providing FHTC within the command area for Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo- German) Zone - XII under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. noo. - 11) | 455/BSD | 13/12/2021 | 30 | GANAPATI ENGINEERING CORP. | 4.55 | 3.64 | 100 | 100
81 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Extension of pipeline to Madhakhara, Rasulpur & Haripur mouzas and Supplying & Laying of Rising Main & Distribution main with ERWMS pipe at Golamighat Bridge under ZONE-X for Augmentation of BOLPUR WATER SUPPLY, Sanitation & Health Education Project (INDO-GERMAN), within Bolpur Sub-Division under Birbhum Division, PHED.?(Sl. No.1) | 1590/BHM | 22/09/2021 | 60 | PRABHAT KUMAR MONDAL. | 43.05 | 0 | 0 | 100
82 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Retrofitting work of columns bracings shell wall top Dom etc and overall painting of overhead reservoir situated at boipur sub division phe campus of surul WS Scheme under Bolpur Sub Division within Birbhum Division PHE Dte. | 1682/BHM | 21/12/2020 | 60 | M/S KRIPASINDHU GHOSH & CO. | 14.59 | 13.04 | 100 | 100
83 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Construction of Boundary Wall at CWR site Head Work site of Zone-III of Augmentation of Bolpur Water Supply, Sanitation and Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (124.00m long). (Sl.no. 07) | 2016/BHM | 31/12/2021 | 30 | ABDUL SALEK MALLIK | 8 | 0 | 0 | 100
84 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Tap Connection (FHTC) from existing distribution System in KANKALITALA G.P. Vill.: Layek Bazar, Adityapur, Uttar Narayanpur, Khosh Kadampur (Purbapara) within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) (Zone -XII) under Bolpur Sub-Division within Birbhum Division, PHED. | 381/BSD | 07/10/2021 | 30 | ARNAB CHANDRA | 4.83 | 4.83 | 100 | 100
85 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Construction of Boundary Wall at CWR site (Goalpara) of Zone-IX of Augmentation of Bolpur Water Supply, Sanitation and Health Education Project (Indo-German) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (155.00m long). (Sl.no. 08) | 2013/BHM | 31/12/2021 | 30 | ABDUL SALEK MALLIK | 10.35 | 0 | 0 | 100
86 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Restoration of Cement Concrete road damage due to providing Functional Household Tap Connection (FHTC) from existing distribution system within Kankalitala Gram Panchayet (Vill. - Layek Bazar, Nildanga, Adityapur etc.) within the command area of Augmentation of Bolpur Water Supply Sanitation & Health Education Project (Indo-German) Zone-XII under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 09). | 58/BSD | 22/02/2022 | 7 | ARNAB CHANDRA | 0.8 | 0.55 | 100 | 92
87 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Material Requisition To Resource Division | 220/BHM | 02/02/2022 | 0 | Resource Division | 54.98 | 0 | 0 | 0
88 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Material Requisition To Resource Division | 2209/BHM | 12/10/2022 | 0 | Resource Division | 0.02 | 0 | 0 | 0
89 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Extension of 90 Mtr. dia. HDPE pipeline near Udyanpally OHR at Ward no. 6 (Six) under Zone - I for Augmentation of Bolpur Water Supply, Sanitation & Health Education Project (Indo-German), within Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No. - 01) | 301/BSD | 19/08/2021 | 30 | INDRAJIT DAS | 4.97 | 0 | 0 | 100
90 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Augmentation of Bolpur Water Supply, Sanitation & health education project (Indo-German) Zone-XII in Bolpur Sub-Division under Birbhum Division, PHE Dte. | 2271/BHM | 18/10/2022 | 30 | SUPRIYA RAY | 25.56 | 0 | 0 | 100
91 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) in Mehidipur (105) village under Raipur-Supur Gram Panchayat within the Command area of Bolpur Water Supply, Sanitation & Health Education Project (Indo-German), Zone - VIII for Swajal Gram under Bolpur-Sriniketan Block of Bolpur Sub-Division within Birbhum Division P.H.E. Deptt. (Sl. No.7) | 224/BHM | 20/01/2023 | 45 | B RAI CONSTRUCTION COMPANY | 57.78 | 0 | 0 | 100
92 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone - IX Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No. - 06) | 380/BHM | 21/02/2022 | 120 | INDRAJIT DAS | 36.29 | 9.22 | 64.83 | 100
93 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bolpur Zone -X Indo-German Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No. 13) | 280/BHM | 09/02/2022 | 162 | PINTU KHAN | 33.49 | 24.48 | 100 | 92
94 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mouja Haripur,(146), Rasulpur (147) and Upparkhara etc. Zone-X under Augmentation of Bolpur W/S Sanitation & Health Education Project (Indo-German) in Bolpur Sub-Division within Birbhum Division, PHE Dte. | 2244/BHM | 17/10/2022 | 30 | SUPRIYA RAY | 26.69 | 0 | 0 | 100
95 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Bolpur water supply scheme under Bolpur Sriniketan Block District Birbhum under Birbhum Division, PHE Dte. , SM/09792 | Retrofitting | Retrofitting works for providing functional household tap connection (FHTC) at Mahidapur village of Zone-VIII by Surging of existing 01 no tube well (Indo-German) along with connecting pipe line & Construction of Switch Room Cum Chlorine Room 2.25 mtr.X 3.00 mtr. Size near BITM (Gopalnagar mouzas) of Bolpur water supply scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 2614/BHM | 11/09/2024 | 90 | INDRANIL DUTTA | 5.23 | 0 | 0 | 100
96 | BIRBHUM | Birbhum Division | Ekpara Piped Water Supply Scheme. , SM/12690 | New | Different works related to water supply scheme at EKPARA & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 2067/BHM | 08/06/2023 | 452 | CHOWDHURY ENTERPRISE | 237.87 | 0 | 0 | 0
97 | BIRBHUM | Birbhum Division | Ekpara Piped Water Supply Scheme. , SM/12690 | New | Material Requisition To Resource Division | 1541/BHM | 26/04/2023 | 0 | Resource Division | 9.27 | 0 | 0 | 0
98 | BIRBHUM | Bolpur Mechanical | Ekpara Piped Water Supply Scheme. , SM/12690 | New | Providing Electro-mechanical accessories and others for Ekpara & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 3531/Bol.MD | 29/11/2023 | 60 | BIRBHUM ELECTRIC WORKS | 22.77 | 0 | 0 | 30
99 | BIRBHUM | Birbhum Division | Ekpara Piped Water Supply Scheme. , SM/12690 | New | Material Requisition To Resource Division | 229/BHM | 24/01/2024 | 0 | Resource Division | 0.62 | 0 | 0 | 0
100 | BIRBHUM | Birbhum Division | Monai Piped Water Supply Scheme. , SM/12701 | New | Material Requisition To Resource Division | 1419/BHM | 24/04/2023 | 0 | Resource Division | 20.44 | 0 | 0 | 0
101 | BIRBHUM | Bolpur Mechanical | Monai Piped Water Supply Scheme. , SM/12701 | New | Providing Electro-mechanical accessories and others for Monai & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 3308/BOL.MD | 29/09/2023 | 641 | H.K.DAS & CO. | 28.74 | 0 | 0 | 75
102 | BIRBHUM | Bolpur Mechanical | Monai Piped Water Supply Scheme. , SM/12701 | New | WBSEDCL QUOTATION FOR MONAI PH II WS SCHEME | BP-2023-24-296 | 12/03/2024 | 0 | WBSEDCL | 3.45 | 0 | 0 | 0
103 | BIRBHUM | Bolpur Mechanical | Monai Piped Water Supply Scheme. , SM/12701 | New | WBSEDCL QUIOTATION FOR MONAI PH NO-I | BP-23-24-273 | 15/02/2024 | 0 | WBSEDCL | 3.97 | 0 | 0 | 0
104 | BIRBHUM | Birbhum Division | Monai Piped Water Supply Scheme. , SM/12701 | New | Different works related to water supply scheme at MONAI & its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1427/BHM | 25/04/2023 | 845 | GHOSH ENTERPRISE | 316.44 | 0 | 0 | 80
105 | BIRBHUM | Birbhum Division | Monai Piped Water Supply Scheme. , SM/12701 | New | Road crossing, Repairing & restoration of damaged pipe lines & PCC roads, sluice valve chambers including all allied works for Monai Piped Water Supply Scheme under Birbhum Division, P.H.E Dte. | 1512/BHM | 23/05/2025 | 90 | GHOSH ENTERPRISE | 54.1 | 0 | 0 | 0
106 | BIRBHUM | Bolpur Mechanical | Asenga Piped Water Supply Scheme. , SM/12680 | New | Providing Electro-mechanical accessories and others for ASENGA and Adjoining moujas water supply scheme in Md Bazar Block under Bolpur Mechanical Division PHE Dte. | 2078/BOL.MD. | 21/08/2023 | 60 | UNIVERSAL ENTERPRISES | 28.8 | 0 | 0 | 70
107 | BIRBHUM | Birbhum Division | Asenga Piped Water Supply Scheme. , SM/12680 | New | Material Requisition To Resource Division | 1433/BHM | 25/04/2023 | 0 | Resource Division | 95.69 | 0 | 0 | 0
108 | BIRBHUM | Birbhum Division | Asenga Piped Water Supply Scheme. , SM/12680 | New | Different works related to water supply scheme at ASENGA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1342/BHM | 20/04/2023 | 275 | M/S GOUTAM DAS | 409.61 | 0 | 0 | 65
109 | BIRBHUM | Bolpur Mechanical | Asenga Piped Water Supply Scheme. , SM/12680 | New | WBSEDCL QUOTATION FOR ASENGA P H NO.I WS SCHEME | BP-23-24-172 | 07/12/2023 | 0 | WBSEDCL | 6.71 | 0 | 0 | 0
110 | BIRBHUM | Bolpur Mechanical | Asenga Piped Water Supply Scheme. , SM/12680 | New | WBSEDCL QUOTATION FOR ASENGA TW-I (OHR SITE) |  | 14/03/2024 | 0 | WBSEDCL | 3.22 | 0 | 0 | 0
111 | BIRBHUM | Bolpur Mechanical | Asenga Piped Water Supply Scheme. , SM/12680 | New | New Service connection at Asenga WSS, Block- Khoyrasole under Bolpur Mechanical Division, PHE Dte |  | 13/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.22 | 0 | 0 | 0
112 | BIRBHUM | Bolpur Mechanical | Asenga Piped Water Supply Scheme. , SM/12680 | New | WBSEDCL QUOTATION FOR ASENGA PH NO.2 WS SCHEME | BP-23-24-171 | 07/12/2023 | 0 | WBSEDCL | 3.82 | 0 | 0 | 0
113 | BIRBHUM | Birbhum Division | Asenga Piped Water Supply Scheme. , SM/12680 | New | Jack pushing for crossing PWD Road at different locations including all other allied works for Asenga piped Water Supply Scheme (Md.Bazar Development Block) under Birbhum Division P.H.E. Dte. | 863/BHM | 26/03/2025 | 75 | M/S GOUTAM DAS | 65.5 | 0 | 0 | 40
114 | BIRBHUM | Bolpur Mechanical | Lakshmi Narayanpur and Adjoining Mouzas PWSS , SM/12696 | New | Providing electro-mechanical accessories and others for Lakshmi Narayanpur & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | 1916/Bol.MD | 10/08/2023 | 366 | S.P. CONSTRUCTION | 72.38 | 0 | 0 | 0
115 | BIRBHUM | Birbhum Division | Lakshmi Narayanpur and Adjoining Mouzas PWSS , SM/12696 | New | Material Requisition To Resource Division | 1395/BHM | 24/04/2023 | 0 | Resource Division | 168.11 | 0 | 0 | 0
116 | BIRBHUM | Bolpur Mechanical | Lakshmi Narayanpur and Adjoining Mouzas PWSS , SM/12696 | New | Supply Delivery & Installation of open well Sub-Mersable Pumping Machinery and allied electro-mechanical works at CWR under Lakshminarayanpur water supply scheme (Block-Nalhati-I) under Bolpur Mechanical Division, PHE Dte. | 298/AE-III | 22/02/2024 | 21 | QUAZI NOZRUL ISLAM | 3.32 | 0 | 0 | 100
117 | BIRBHUM | Birbhum Division | Lakshmi Narayanpur and Adjoining Mouzas PWSS , SM/12696 | New | Different works related to water supply scheme at LAKSHMI NARAYANPUR & its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 4176/BHM | 31/10/2023 | 274 | APURBA MONDAL | 472.43 | 0 | 0 | 0
118 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ARAZI TAKIPUR AND OTHER 11 NOS. MOUZAS UNDER SURI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11900 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 248.23 | 63 | 92
119 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ARAZI TAKIPUR AND OTHER 11 NOS. MOUZAS UNDER SURI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11900 | New | Supply of one no. diesel driven car(Diesel) on hire basis office uses for the officials of the Assistant Engineer, RWS, Birbhum Sub-Division, PHE Dte.(Period from 28.06.2024 to 26.12.2024) | 96/RWS | 27/06/2024 | 179 | ADIL CONSTRUCTION | 0.85 | 0 | 0 | 0
120 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ARAZI TAKIPUR AND OTHER 11 NOS. MOUZAS UNDER SURI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11900 | New | Supply of one no. diesel driven car(diesel) on hire basis office uses for the officials of the Assistant Engineer, RWS,Birbhum Sub-Division, PHE Dte.(Period from 27/12/2024 to 24/07/2025) | 204/RWS | 27/12/2024 | 210 | ADIL CONSTRUCTION | 1 | 0 | 0 | 0
121 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BAMUNDIHA AND OTHER 14 NOS. MOUZAS UNDER MD BAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/12068 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 81.93 | 16.82 | 92
122 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Basudebpur Phase-II Water Supply Scheme. , SM/12662 | Retrofitting | Allied works for Laying of distribution Pipe line for providing FHTC at Pukurpara, Gopinathpur, Narayanpur,Uchpur, Gragara and Hatin mouza within Basudebpur PWSS under Birbhum Division, P.H.E. Dte. | 1640/BHM | 02/05/2023 | 45 | M/S BUILDWELL | 7.58 | 0 | 0 | 0
123 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Jhikadda Phase-II Water Supply Scheme. , SM/12667 | Retrofitting | Additional FHTC works along with Laying pipelines at different mouzas within Jhikadda W/S under Rampurhat Sub Division, Birbhum, Division, P.H.E Dte. | 2507/BHM | 17/11/2022 | 45 | KAZI EMDADUL HAQUE | 12.78 | 12.73 | 100 | 100
124 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Jhikadda Phase-II Water Supply Scheme. , SM/12667 | Retrofitting | Additional laying of UPVC Pipe line for Maharapur, Routara, Mirpur diff mouzas for providing FHTC under JHIKADDA Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte | 1086/BHM | 06/04/2023 | 60 | KAZI ZAKIR HOSSAIN | 6.72 | 6.7 | 100 | 100
125 | BIRBHUM | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/13710 | New | Material Requisition To Resource Division | 1493/BHM | 25/04/2023 | 0 | Resource Division | 17.09 | 0 | 0 | 0
126 | BIRBHUM | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/13710 | New | Providing Electro-mechanical accessories and others for Chhamna PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | 3283/BOL.MD | 29/09/2023 | 60 | SUNIL RABIDAS | 55.68 | 0 | 0 | 40
127 | BIRBHUM | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/13710 | New | Operation and Guarding of pumping machinery and others at Chhamna PWSS, Block: Mayureswar- II (Pump House No. I), under Bolpur MechanicalDivision, P.H.E Dte. | 1636./AE-III | 21/10/2024 | 92 | SUNIL RABIDAS | 0.89 | 0 | 0 | 0
128 | BIRBHUM | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/13710 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Chamna PWSS, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte. | 401/Bol.MD | 07/03/2024 | 45 | M/S SWAPAN BANERJEE | 25.28 | 0 | 0 | 90
129 | BIRBHUM | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/13710 | New | Operation and Guarding of pumping machinery and others at Chhamna PWSS,Block: Mayureswar- II (Pump House No. II), under Bolpur MechanicalDivision, P.H.E Dte. | 1637./AE-III | 21/10/2024 | 92 | SUNIL RABIDAS | 0.89 | 0 | 0 | 0
130 | BIRBHUM | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/13710 | New | Continuation Work Order for Preparation & Submission of DPR for (CHHAMNA) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | 287/RSD | 31/08/2022 | 45 | ENVIROTECH SOLUTIONS | 3.43 | 0 | 0 | 100
131 | BIRBHUM | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/13710 | New | Continuation Work Order for Preparation & Submission of DPR for (CHHAMNA) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | 371/RSD | 21/09/2022 | 45 | ENVIROTECH SOLUTIONS | 2.5 | 0 | 0 | 100
132 | BIRBHUM | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/13710 | New | Material Requisition To Resource Division | 233/BHM | 24/01/2024 | 0 | Resource Division | 8.62 | 0 | 0 | 0
133 | BIRBHUM | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/13710 | New | NEW SERVICE CONNECTION AT CHHAMNA PWSS PH-I UNDER BOLPUR MECHANICAL DIVISION, PHE Dte... | BP-24-25-11 | 25/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.1 | 0 | 0 | 0
134 | BIRBHUM | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/13710 | New | New service connection at Chhamna Pump House-3, under Bolpur Mech. Division, P.H.e. Dte. | BP-2024-2025-28 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.13 | 0 | 0 | 0
135 | BIRBHUM | Bolpur Mechanical | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/13710 | New | NEW SERVICE CONNECTION AT CHHAMNA PWSS PH-II UNDER BOLPUR MECHANICAL DIVISION PHE Dte... | BP-24-25-10 | 25/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.41 | 0 | 0 | 0
136 | BIRBHUM | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/13710 | New | Different works related to Water Supply Scheme at CHHAMNA & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3020/BHM | 14/07/2023 | 718 | S K CONSTRUCTION | 557.28 | 0 | 0 | 40
137 | BIRBHUM | Birbhum Division | Chhamna Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/13710 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
138 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GHOGAN AND OTHER 11 NOS. MOUZAS UNDER NANOOR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11905 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 177.2 | 43.86 | 92
139 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GHOGAN AND OTHER 11 NOS. MOUZAS UNDER NANOOR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11905 | New | Road restoration work at different villages under implementation of Mini Piped Water Supply Scheme within Suri-II,Nanoor,Md Bazar Block having less than 100 Households under Birbhum Division PHE Dte. | 2094/BHM | 14/08/2025 | 90 | BHASKAR MANDAL | 29.4 | 0 | 0 | 35
140 | BIRBHUM | Birbhum Division | Kanaipur piped water supply scheme. , SM/13640 | New | Continuation Work Order for Preparation & Submission of DPR for (Kanaipur) Water Supply Scheme under Mayureswar-I Development Block. | 220/RSD | 21/06/2022 | 90 | ENVIROTECH SOLUTIONS | 4.93 | 0 | 0 | 100
141 | BIRBHUM | Birbhum Division | Kanaipur piped water supply scheme. , SM/13640 | New | Material Requisition To Resource Division | 1513/BHM | 26/04/2023 | 0 | Resource Division | 57.41 | 0 | 0 | 0
142 | BIRBHUM | Birbhum Division | Kanaipur piped water supply scheme. , SM/13640 | New | Material Requisition To Resource Division | 235/BHM | 24/01/2024 | 0 | Resource Division | 9.27 | 0 | 0 | 0
143 | BIRBHUM | Bolpur Mechanical | Kanaipur piped water supply scheme. , SM/13640 | New | New service connection at Kanaipur PH-II PWSS ,Mayureswar- I , under Bolpur mechanical Division, P.H.E Dte. | BP-2024-2025-48 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.27 | 0 | 0 | 0
144 | BIRBHUM | Bolpur Mechanical | Kanaipur piped water supply scheme. , SM/13640 | New | New service connection at Kanaipur PH-I PWSS , Mayureswar-I Block under Bolpur Mechanical Division,P.H.E Dte. | BP-2024-2025-49 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.8 | 0 | 0 | 0
145 | BIRBHUM | Birbhum Division | Kanaipur piped water supply scheme. , SM/13640 | New | Different works related to water supply scheme at KANAIPUR & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3251/BHM | 26/07/2023 | 705 | BENGAL ENGINEERING | 564.7 | 0 | 0 | 30
146 | BIRBHUM | Bolpur Mechanical | Kanaipur piped water supply scheme. , SM/13640 | New | Providing Electro-mechanical accessories (H/L and L/L) and others for Kanaipur & Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 2168/Bol.MD | 31/08/2023 | 578 | SATYAJIT GHOSH | 77.69 | 0 | 0 | 48
147 | BIRBHUM | Birbhum Division | Kanaipur piped water supply scheme. , SM/13640 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, Boundary wall, High Lift Pump house (11 m x 6 m) and Sinking of 200 mm Dia all Through Tube Well related to water supply scheme at Kanaipur Piped Water Supply Scheme within Rampurhat-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 1581/BHM | 02/06/2025 | 90 | BENGAL ENGINEERING | 69.7 | 0 | 0 | 0
148 | BIRBHUM | Birbhum Division | Kayera Water Supply Scheme , SM/13641 | New | Material Requisition To Resource Division | 1489/BHM | 25/04/2023 | 0 | Resource Division | 11.95 | 0 | 0 | 0
149 | BIRBHUM | Birbhum Division | Kayera Water Supply Scheme , SM/13641 | New | Preparation & Submission of Detail Project Report (DPR) for KAYERA Water Supply Scheme & SHRICHANDRAPUR Piped Water Supply Scheme under Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. | 99/BSD | 15/03/2022 | 90 | M/S R DUTTA & CO. | 4.65 | 0 | 0 | 100
150 | BIRBHUM | Bolpur Mechanical | Kayera Water Supply Scheme , SM/13641 | New | New Service connection of Kayera PWSS P/H- I (Block- Illambazar) | BP-2024-2025-54 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.83 | 0 | 0 | 0
151 | BIRBHUM | Bolpur Mechanical | Kayera Water Supply Scheme , SM/13641 | New | Additional Quotation for extra involvement of materials against consumer ID 503652443 at Koyra site under Illambazar ccc | BP-2024-25-266 | 25/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.54 | 0 | 0 | 0
152 | BIRBHUM | Birbhum Division | Kayera Water Supply Scheme , SM/13641 | New | Different works related to water supply scheme at KAYERA Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1214/BHM | 12/04/2023 | 275 | USHA ENTERPRISE | 334.74 | 0 | 0 | 5
153 | BIRBHUM | Central Drilling | Kayera Water Supply Scheme , SM/13641 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
154 | BIRBHUM | Birbhum Division | Kayera Water Supply Scheme , SM/13641 | New | Hiring of 01 (One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, P.H.E Dte. under Birbhum Division, P.H.E Dte. For the period of 01.04.2024 to 30.09.2024. | 269/BSD | 15/03/2024 | 184 | SK AKRAM HOSSAIN | 0.86 | 0 | 0 | 100
155 | BIRBHUM | Birbhum Division | Taloan Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13653 | New | Continuation Work Order for Preparation & Submission of DPR for (Talowan) Water Supply Scheme under Mayureswar-I Development Block. | 264/RSD | 29/07/2022 | 90 | ENVIROTECH SOLUTIONS | 3.58 | 0 | 0 | 100
156 | BIRBHUM | Bolpur Mechanical | Taloan Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13653 | New | Providing Electro-mechanical accessories and others for Taloan PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | 3471/Bol.MD | 07/11/2023 | 60 | QUAZI NOZRUL ISLAM | 43.81 | 0 | 0 | 40
157 | BIRBHUM | Bolpur Mechanical | Taloan Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13653 | New | Quotation money for new service connection at Talowan PWSS P/H- I under Mollarpur CCC | BP-24-25-184 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.75 | 0 | 0 | 0
158 | BIRBHUM | Birbhum Division | Taloan Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13653 | New | Different works related to water supply scheme at TALWAN & its adjoining mouzas water supply scheme within Mayureswar-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (3rd Call) | 601/BHM | 09/02/2024 | 733 | PRALAY ROY | 309.43 | 0 | 0 | 35
159 | BIRBHUM | Birbhum Division | Simgram Piped Water Supply Scheme. , SM/12908 | New | Material Requisition To Resource Division | 1530/BHM | 26/04/2023 | 0 | Resource Division | 10.16 | 0 | 0 | 0
160 | BIRBHUM | Bolpur Mechanical | Simgram Piped Water Supply Scheme. , SM/12908 | New | Providing Electro-mechanical accessories and others for SIMGRAM piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | 2144/Bol.MD | 25/08/2023 | 60 | S.G.TECHNICAL SERVICES | 25.67 | 0 | 0 | 60
161 | BIRBHUM | Bolpur Mechanical | Simgram Piped Water Supply Scheme. , SM/12908 | New | Quotation deposit for empowering Simgram Water Supply Scheme P/H -II in Paikar CCC under Bolpur Mechanical Division, PHE Dte | BP-2024-2025-53 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.08 | 0 | 0 | 0
162 | BIRBHUM | Bolpur Mechanical | Simgram Piped Water Supply Scheme. , SM/12908 | New | Quotation deposit for empowering Simgram Water Supply Scheme P/H -I in Paikar CCC under Bolpur Mechanical Division, PHE Dte | BP-2024-2025-42 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.97 | 0 | 0 | 0
163 | BIRBHUM | Birbhum Division | Simgram Piped Water Supply Scheme. , SM/12908 | New | Different works related to water supply scheme at SIMGRAM & its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1719/BHM | 12/05/2023 | 615 | M/S MD AMINUL ISLAM | 69.99 | 0 | 0 | 65
164 | BIRBHUM | Birbhum Division | Naoadangal and Adjoining Mouzas PWSS , SM/12904 | New | Material Requisition To Resource Division | 1400/BHM | 24/04/2023 | 0 | Resource Division | 240.3 | 0 | 0 | 0
165 | BIRBHUM | Birbhum Division | Naoadangal and Adjoining Mouzas PWSS , SM/12904 | New | Material Requisition To Resource Division | 3278/BHM | 27/07/2023 | 0 | Resource Division | 5.69 | 0 | 0 | 0
166 | BIRBHUM | Birbhum Division | Naoadangal and Adjoining Mouzas PWSS , SM/12904 | New | Material Requisition To Resource Division | 2171/BHM | 23/06/2023 | 0 | Resource Division | 3.42 | 0 | 0 | 0
167 | BIRBHUM | Birbhum Division | Naoadangal and Adjoining Mouzas PWSS , SM/12904 | New | Different works related to water supply scheme at NAOADANGAL & its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 935/BHM | 23/03/2023 | 275 | SYED KHORSED ALAM | 434.91 | 0 | 0 | 15
168 | BIRBHUM | Bolpur Mechanical | Naoadangal and Adjoining Mouzas PWSS , SM/12904 | New | Providing Electro-mechanical accessories and others for Naoadangal & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | 1842/Bol.MD | 01/08/2023 | 90 | ORIENTAL ENGINEERING CO. | 54.58 | 0 | 0 | 50
169 | BIRBHUM | Bolpur Mechanical | Naoadangal and Adjoining Mouzas PWSS , SM/12904 | New | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, PHE Dte | ..1299/Bol.MD | 28/06/2023 | 123 | SATYAJIT GHOSH | 1.58 | 0 | 0 | 100
170 | BIRBHUM | Bolpur Mechanical | Naoadangal and Adjoining Mouzas PWSS , SM/12904 | New | WBSEDCL QUOTATION FOR NAOADANGAL | BP-23-24-204 | 04/01/2024 | 0 | WBSEDCL | 8.4 | 0 | 0 | 0
171 | BIRBHUM | Bolpur Mechanical | Naoadangal and Adjoining Mouzas PWSS , SM/12904 | New | Supply, Delivery and Installation of 1 M.T. HOT crane at High Lift Pump House of Noadangal water supply scheme under Bolpur Mechanical Division, PHE. Dte | 537/BOL.MD | 14/03/2024 | 383 | ORIENTAL ENGINEERING CO. | 8.48 | 0 | 0 | 100
172 | BIRBHUM | Birbhum Division | Charkalgram Piped Water Supply Scheme , SM/13481 | New | Material Requisition To Resource Division | 1470/BHM | 25/04/2023 | 0 | Resource Division | 26.63 | 0 | 0 | 0
173 | BIRBHUM | Birbhum Division | Charkalgram Piped Water Supply Scheme , SM/13481 | New | Different works related to water supply scheme at CHARKALGRAM PIPED WATER SUPPLY SCHEME(TSM/016091) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 2608/BHM | 11/09/2024 | 365 | GARGO TRADERS | 432.8 | 0 | 0 | 0
174 | BIRBHUM | Birbhum Division | Charkalgram Piped Water Supply Scheme , SM/13481 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for CHARKALGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - B). | 310/BSD | 16/08/2022 | 180 | RADIANT | 2.18 | 0 | 0 | 100
175 | BIRBHUM | Birbhum Division | Charkalgram Piped Water Supply Scheme , SM/13481 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for CHARKALGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | 235/BSD | 15/06/2022 | 180 | RADIANT | 4.94 | 0 | 0 | 100
176 | BIRBHUM | Central Drilling | Charkalgram Piped Water Supply Scheme , SM/13481 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
177 | BIRBHUM | Bolpur Mechanical | Charkalgram Piped Water Supply Scheme , SM/13481 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Angora & Charkalgram Water supply Scheme, Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | 4537/BOL.MD | 20/12/2024 | 285 | MENAKA ENTERPRISE | 73.34 | 0 | 0 | 100
178 | BIRBHUM | Birbhum Division | SARIHA PIPED WATER SUPPLY SCHEME , SM/12900 | New | Material Requisition To Resource Division | 2177/BHM | 23/06/2023 | 0 | Resource Division | 14.08 | 0 | 0 | 0
179 | BIRBHUM | Birbhum Division | SARIHA PIPED WATER SUPPLY SCHEME , SM/12900 | New | Different works related to water supply scheme at Majhkaltia, Sahira & KANAPIUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 1348/BHM | 20/04/2023 | 835 | M/S GOUTAM DAS | 1594.34 | 0 | 0 | 28
180 | BIRBHUM | Bolpur Mechanical | SARIHA PIPED WATER SUPPLY SCHEME , SM/12900 | New | Providing Electro-mechanical accessories and others for Sariha PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | 3366/BOL.MD | 11/10/2023 | 627 | T.D.K. ENTERPRISE | 27.35 | 0 | 0 | 40
181 | BIRBHUM | Birbhum Division | SARIHA PIPED WATER SUPPLY SCHEME , SM/12900 | New | Restoration of Roads, pucca drain including Jack pushing & Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Sariha piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | 1509/BHM | 23/05/2025 | 90 | M/S GOUTAM DAS | 83.28 | 0 | 0 | 10
182 | BIRBHUM | Birbhum Division | Demurtita Piped Water Supply Scheme. , SM/14981 | New | Preparation & Submission of DPR for Demurtita & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 96/BSSD | 06/06/2022 | 45 | RADIANT | 1.59 | 0 | 0 | 100
183 | BIRBHUM | Birbhum Division | Demurtita Piped Water Supply Scheme. , SM/14981 | New | Material Requisition To Resource Division | 441/BHM | 01/02/2024 | 0 | Resource Division | 54.82 | 0 | 0 | 0
184 | BIRBHUM | Birbhum Division | Demurtita Piped Water Supply Scheme. , SM/14981 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
185 | BIRBHUM | Birbhum Division | Demurtita Piped Water Supply Scheme. , SM/14981 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
186 | BIRBHUM | Birbhum Division | MONACHITURA PIPED WATER SUPPLY SCHEME , SM/14450 | New | Different works related to water supply scheme at MONACHITURA PIPED WATER SUPPLY SCHEME (TSM/017000) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 3155/BHM | 19/11/2024 | 365 | M/S TAPAS KUMAR CHAKRABORTY | 574 | 0 | 0 | 0
187 | BIRBHUM | Birbhum Division | MONACHITURA PIPED WATER SUPPLY SCHEME , SM/14450 | New | Preparation & Submission of Detail Project Report (DPR) for MONACHITURA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. | 100/BSD | 15/03/2022 | 180 | APEX ENGINEERING | 4.92 | 0 | 0 | 100
188 | BIRBHUM | Central Drilling | MONACHITURA PIPED WATER SUPPLY SCHEME , SM/14450 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
189 | BIRBHUM | Bolpur Mechanical | MONACHITURA PIPED WATER SUPPLY SCHEME , SM/14450 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Mona Chaitura PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | 332/BOL.MD | 19/02/2025 | 120 | OSMAN SEKH | 76.25 | 0 | 0 | 50
190 | BIRBHUM | Birbhum Division | BALIARA PIPED WATER SUPPLY SCHEME , SM/14847 | New | Different works related to water supply scheme at BALIARA & its adjoining mouzas water supply scheme within NANOOR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1426/BHM | 25/04/2023 | 275 | M/S REBATI SANKAR SINHA | 378.55 | 0 | 0 | 0
191 | BIRBHUM | Birbhum Division | BALIARA PIPED WATER SUPPLY SCHEME , SM/14847 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BALIARA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 103/BSD | 16/03/2022 | 90 | RADIANT | 4.36 | 0 | 0 | 100
192 | BIRBHUM | Birbhum Division | BALIARA PIPED WATER SUPPLY SCHEME , SM/14847 | New | Material Requisition To Resource Division | 1559/BHM | 26/04/2023 | 0 | Resource Division | 22.71 | 0 | 0 | 0
193 | BIRBHUM | Bolpur Mechanical | BALIARA PIPED WATER SUPPLY SCHEME , SM/14847 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Baliara WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | 4531/BOL.MD | 20/12/2024 | 120 | SATYAJIT GHOSH | 75.08 | 0 | 0 | 0
194 | BIRBHUM | Central Drilling | BALIARA PIPED WATER SUPPLY SCHEME , SM/14847 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
195 | BIRBHUM | Birbhum Division | Noapara Piped Water Supply Scheme (Khoyrasole G.P.) , SM/14854 | New | Preparation & Submission of DPR for Noapara & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 86/BSSD | 19/05/2022 | 45 | RADIANT | 3.33 | 0 | 0 | 100
196 | BIRBHUM | Birbhum Division | Noapara Piped Water Supply Scheme (Khoyrasole G.P.) , SM/14854 | New | Material Requisition To Resource Division | 432/BHM | 01/02/2024 | 0 | Resource Division | 142.08 | 0 | 0 | 0
197 | BIRBHUM | Birbhum Division | Noapara Piped Water Supply Scheme (Khoyrasole G.P.) , SM/14854 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
198 | BIRBHUM | Birbhum Division | Noapara Piped Water Supply Scheme (Khoyrasole G.P.) , SM/14854 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
199 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Baliharpur(Phase-I) PWSS , SM/07648 | Retrofitting | Work Order for Sinking of 2 (Two) nos. 200 mm dia. Tubewell of 6m depth with horizontal strainer on the river Bed of Dwarka River and Connecting Pipe line from Tubewells to C.W.R under Baliharpur Piped Water Supply Scheme in Mahammad Bazar Block, Dist: Birbhum under Birbhum Division, P.H.E. Dte. (Sl. No.-01) | 418/BHM | 24/02/2022 | 30 | BHABATARAN SADHU | 4.29 | 0 | 0 | 100
200 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Baliharpur(Phase-I) PWSS , SM/07648 | Retrofitting | Laying remaining portion DI(K9) clear water rising main Pipe Line from CWR towards OHR under Baliharpur Piped Water Supply Scheme in Mahammad Bazar Block, Dist: Birbhum under Birbhum Division P.H.E. Dte. (Sl. No.-02) | 417/BHM | 24/02/2022 | 30 | LAXMI NARAYAN ENGINEERS CO-OP SOCIETY LTD | 1.78 | 0 | 0 | 100
201 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Baliharpur(Phase-I) PWSS , SM/07648 | Retrofitting | Dressing and levelling of over undulated existing land of CWR & pump house site by earth cutting at plot no.295 mouza-Hinglo, JL No.40 for Baliharpur Piped Water Supply Scheme of Block-Md. Bazar under Birbhum Division, PHE Dte, (Sl. No.7) | 762/BHM | 06/04/2022 | 10 | GOUTAM DAS | 0.96 | 0 | 0 | 100
202 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Baliharpur(Phase-I) PWSS , SM/07648 | Retrofitting | Trial Bore for Sinking of 200mm dia. Tubewell on the river Bank & Bed of Dwaraka under Baliharpur Piped Water Supply Scheme under Birbhum Division P.H.E. Dte. (Sl. No.-01) | 2025 /BHM | 04/01/2022 | 30 | BHABATARAN SADHU | 0.45 | 0 | 0 | 100
203 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Baliharpur(Phase-I) PWSS , SM/07648 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Baliharpur Water Supply Scheme within Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.5) | 820/BHM | 13/04/2022 | 60 | S S ENTERPRISE | 93.73 | 45.35 | 100 | 100
204 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Baliharpur(Phase-I) PWSS , SM/07648 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Baliharpur Piped Water Supply Scheme within Birbhum Sadar Sub-Division under Birbhum Division, P.H.E Dte. | 1048/BHM | 31/03/2023 | 647 | M/S GOUTAM DAS | 15.07 | 0 | 0 | 100
205 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Baliharpur(Phase-I) PWSS , SM/07648 | Retrofitting | Balance work for Providing Functional Household tap connections (FHTC) from existing distribution system within the command area of Baliharpur piped water supply scheme (Palan and rest of Baliharpur , Muralpur, Kusumkandar, Salchatra , Kendsarail, Dhatrabandhi,Hosaipur & bhagabandha ) under Birbhum Sadar sub division P.H.E Dte. | 1645/BHM | 02/05/2023 | 712 | BIJOY KUMAR CHOUDHURY | 57.82 | 0 | 0 | 96
206 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raghunathpur(Phase-II) Water Supply Scheme , SM/13372 | Retrofitting | Extension of pipe line including FHTC for left out habitations along with FHTC at Raghunathpur PWSS under Nalhati Sub Division P.H.ED.. (Sl.No.05) | 875/BHM | 21/03/2023 | 75 | DUBE ENTERPRISE | 60.43 | 0 | 0 | 85
207 | BIRBHUM | Birbhum Division | BHUBANESWAR PIPED WATER SUPPLY SCHEME , SM/13387 | New | Material Requisition To Resource Division | 1450/BHM | 25/04/2023 | 0 | Resource Division | 129.25 | 0 | 0 | 0
208 | BIRBHUM | Birbhum Division | BHUBANESWAR PIPED WATER SUPPLY SCHEME , SM/13387 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHUBANESWAR Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - A) | 162/BSD | 25/04/2022 | 90 | M/S R DUTTA & CO. | 4.93 | 0 | 0 | 100
209 | BIRBHUM | Birbhum Division | BHUBANESWAR PIPED WATER SUPPLY SCHEME , SM/13387 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHUBANESWAR Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - B) | 267/BSD | 14/07/2022 | 90 | M/S R DUTTA & CO. | 1.07 | 0 | 0 | 100
210 | BIRBHUM | Central Drilling | BHUBANESWAR PIPED WATER SUPPLY SCHEME , SM/13387 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
211 | BIRBHUM | Birbhum Division | BHUBANESWAR PIPED WATER SUPPLY SCHEME , SM/13387 | New | Different works related to water supply scheme at DHANASAHA, CHHATAR-BANDI, BHABANIPUR, BHUBANESWAR Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | 4141/BHM | 19/10/2023 | 709 | B RAI CONSTRUCTION COMPANY | 2996.46 | 0 | 0 | 5
212 | BIRBHUM | Birbhum Division | Bagahola Piped Water Supply Scheme , SM/14084 | New | Preparation & Submission of DPR for Baghasola & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 77/BSSD | 05/05/2022 | 45 | RADIANT | 2.22 | 0 | 0 | 100
213 | BIRBHUM | Birbhum Division | Bagahola Piped Water Supply Scheme , SM/14084 | New | Material Requisition To Resource Division | 434/BHM | 01/02/2024 | 0 | Resource Division | 109.46 | 0 | 0 | 0
214 | BIRBHUM | Birbhum Division | Bagahola Piped Water Supply Scheme , SM/14084 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
215 | BIRBHUM | Birbhum Division | Bagahola Piped Water Supply Scheme , SM/14084 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
216 | BIRBHUM | Birbhum Division | Chandrapur Piped Water Supply Scheme , SM/14893 | New | Material Requisition To Resource Division | 1455/BHM | 25/04/2023 | 0 | Resource Division | 110.67 | 0 | 0 | 0
217 | BIRBHUM | Bolpur Mechanical | Chandrapur Piped Water Supply Scheme , SM/14893 | New | Supply & delivery of different electrical accessories at Chandrapur Piped water supply scheme under Bolpur Mechanical Division, PHE Dte.(Rajnagar Block) | 1478./AE-III | 11/09/2024 | 7 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 2.11 | 0 | 0 | 100
218 | BIRBHUM | Bolpur Mechanical | Chandrapur Piped Water Supply Scheme , SM/14893 | New | WBSEDCL QUOTATION FOR CHANDRAPUR WATER SUPPLY SCHEME | BP-23-24-260 | 06/02/2024 | 0 | WBSEDCL | 15.71 | 0 | 0 | 0
219 | BIRBHUM | Birbhum Division | Chandrapur Piped Water Supply Scheme , SM/14893 | New | Different works related to water supply scheme at CHANDRAPUR & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 1093/BHM | 06/04/2023 | 720 | SADANANDA CHATTARAJ | 377 | 0 | 0 | 100
220 | BIRBHUM | Bolpur Mechanical | Chandrapur Piped Water Supply Scheme , SM/14893 | New | Providing electro-mechanical accessories and others for Chanddrapur water supply scheme in Rajnagar block under Bolpur Mechanical Division, PHE Dte | 1918/Bol.MD | 10/08/2023 | 662 | A.K. INDUSTRIES | 90.43 | 0 | 0 | 80
221 | BIRBHUM | Birbhum Division | Augmentation of ground water based piped water supply scheme for Hazarpur (Zone-I & Zone-II), Block-Rampurhat-II, Dist- Birbhum within Birbhum Division PHE Dte. , SM/14960 | Augmentation | Material Requisition To Resource Division | 974/BHM | 27/03/2023 | 0 | Resource Division | 183.82 | 0 | 0 | 0
222 | BIRBHUM | Bolpur Mechanical | Augmentation of ground water based piped water supply scheme for Hazarpur (Zone-I & Zone-II), Block-Rampurhat-II, Dist- Birbhum within Birbhum Division PHE Dte. , SM/14960 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Wells and allieds works at Augmentation of Hazarpur [( Zone-I, Pump House No - II ) and ( Zone-II, Pump House No - I & II )] Piped Water Supply Scheme, Block-Rampurhat-II under Bolpur Mechanical Division, PHE Dte | 2131/Bol.MD | 25/08/2023 | 646 | QUAZI NOZRUL ISLAM | 68.76 | 0 | 0 | 30
223 | BIRBHUM | Birbhum Division | Augmentation of ground water based piped water supply scheme for Hazarpur (Zone-I & Zone-II), Block-Rampurhat-II, Dist- Birbhum within Birbhum Division PHE Dte. , SM/14960 | Augmentation | Sinking of 200 mm dia Alll through and 150 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements,, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration for Zone-I & Zone- II and Providing functional household tap connection related to water supply scheme at Augmentation Of Ground Water Based Hazarpur Zone-I & Zone-II Piped Water Supply Scheme within RAMPURHAT-II Block underBIRBHUM Division, PHE Dte | 3432/BHM | 16/12/2024 | 365 | MONDAL& CO | 434.56 | 0 | 0 | 25
224 | BIRBHUM | Birbhum Division | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT , SM/14894 | New | Continuation Work Order for Preparation & Submission of DPR for (Rautgara) Water Supply Scheme under Mayureswar-I Development Block. | 236/RSD | 05/07/2022 | 90 | ENVIROTECH SOLUTIONS | 2.15 | 0 | 0 | 100
225 | BIRBHUM | Birbhum Division | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT , SM/14894 | New | Material Requisition To Resource Division | 1567/BHM | 26/04/2023 | 0 | Resource Division | 4.49 | 0 | 0 | 0
226 | BIRBHUM | Bolpur Mechanical | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT , SM/14894 | New | Supply and Delivery of Pumping Machinery for Routgara water supply scheme Block Mayureswar ¿ I under Bolpur Mechanical Division PHE. Dte. | 946./AE-III | 27/06/2024 | 7 | M. S. ENTERPRISE | 1.49 | 0 | 0 | 100
227 | BIRBHUM | Bolpur Mechanical | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT , SM/14894 | New | Supply & delivery of different electrical accessories at Routgara Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | 1308./AE-III | 28/08/2024 | 7 | TAPAN ENTERPRISE | 2.95 | 0 | 0 | 100
228 | BIRBHUM | Bolpur Mechanical | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT , SM/14894 | New | Supply & delivery of submersible cable accessories at Routgara Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | 1296./AE-III | 27/08/2024 | 7 | RAJIB GHOSH | 2.52 | 0 | 0 | 100
229 | BIRBHUM | Bolpur Mechanical | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT , SM/14894 | New | Supply and Delivery of Sub-Mersible Pump Controllers for Routgara water supply scheme under Bolpur Mechanical Division, PHE Dte. | 1453./AE-III | 09/09/2024 | 7 | M/S. YOUTH ENGINEERS' ENTERPRISE | 2.86 | 0 | 0 | 100
230 | BIRBHUM | Bolpur Mechanical | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT , SM/14894 | New | Supply & delivery of Submersible Cable acceessories for Routgara Piped water supply scheme. under Bolpur Mechanical Division, PHE. Dte. | 1183./AE-III | 09/08/2024 | 10 | RAJIB GHOSH | 0.99 | 0 | 0 | 100
231 | BIRBHUM | Birbhum Division | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT , SM/14894 | New | Material Requisition To Resource Division | 196/BHM | 22/01/2024 | 0 | Resource Division | 0.12 | 0 | 0 | 0
232 | BIRBHUM | Bolpur Mechanical | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT , SM/14894 | New | WBSEDCL QUOTATION FOR RAUTGARA PUMP HOUSE NO-I& II | BP-2023-24-291 | 06/03/2024 | 0 | WBSEDCL | 2.78 | 0 | 0 | 0
233 | BIRBHUM | Bolpur Mechanical | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT , SM/14894 | New | Providing Electro-mechanical accessories and others for Rautgara PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | 1748/Bol.MD | 27/07/2023 | 891 | M. S. ENTERPRISE | 45.04 | 13.1 | 29.08 | 90
234 | BIRBHUM | Birbhum Division | RAUTGARA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT , SM/14894 | New | Different works related to water supply scheme at RAUTGARA & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 902/BHM | 22/03/2023 | 651 | PULAK KUMAR PAL | 173.47 | 0 | 0 | 100
235 | BIRBHUM | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME , SM/14897 | New | Different works related to water supply scheme at GOPINATHPUR PIPED WATER SUPPLY SCHEME (TSM/016258) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1091/BHM | 06/04/2023 | 275 | M/S R B ENTERPRISE | 495.22 | 0 | 0 | 0
236 | BIRBHUM | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME , SM/14897 | New | Material Requisition To Resource Division | 1601/BHM | 27/04/2023 | 0 | Resource Division | 19.19 | 0 | 0 | 0
237 | BIRBHUM | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME , SM/14897 | New | Continuation work Order for "Preparation & Submission of Detail Project Report (DPR) for GOPINATHPUR Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | 214/BSD | 31/05/2022 | 180 | APEX ENGINEERING | 4.22 | 0 | 0 | 100
238 | BIRBHUM | Central Drilling | GOPINATHPUR PIPED WATER SUPPLY SCHEME , SM/14897 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
239 | BIRBHUM | Bolpur Mechanical | GOPINATHPUR PIPED WATER SUPPLY SCHEME , SM/14897 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Gopinathpur PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | 328/BOL.MD | 19/02/2025 | 120 | M/S. UTTAM KUMAR CHATTERJEE | 74.48 | 0 | 0 | 0
240 | BIRBHUM | Birbhum Division | THIBA PIPEED WATER SUPPLY SCHEME , SM/14968 | New | Material Requisition To Resource Division | 1603/BHM | 27/04/2023 | 0 | Resource Division | 20 | 0 | 0 | 0
241 | BIRBHUM | Birbhum Division | THIBA PIPEED WATER SUPPLY SCHEME , SM/14968 | New | Different works related to water supply scheme at THIBA PIPEED WATER SUPPLY SCHEME (TSM/017115) within Labpur Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte | 2662/BHM | 13/09/2024 | 365 | PATHIK PABAN NANDI | 243.95 | 0 | 0 | 0
242 | BIRBHUM | Birbhum Division | THIBA PIPEED WATER SUPPLY SCHEME , SM/14968 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for THIBA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | 208/BSD | 25/05/2022 | 180 | APEX ENGINEERING | 3.16 | 0 | 0 | 100
243 | BIRBHUM | Central Drilling | THIBA PIPEED WATER SUPPLY SCHEME , SM/14968 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
244 | BIRBHUM | Bolpur Mechanical | THIBA PIPEED WATER SUPPLY SCHEME , SM/14968 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Thiba PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | 337/BOL.MD | 19/02/2025 | 239 | PADMA ENGINEERING CO. | 75.59 | 0 | 0 | 40
245 | BIRBHUM | Birbhum Division | Chora Piped Water Supply Scheme , SM/15523 | New | Material Requisition To Resource Division | 1500/BHM | 25/04/2023 | 0 | Resource Division | 0.22 | 0 | 0 | 0
246 | BIRBHUM | Birbhum Division | Chora Piped Water Supply Scheme , SM/15523 | New | Preparation & Submission of DPR for Chora & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 92/BSSD | 27/05/2022 | 45 | RADIANT | 1.41 | 0 | 0 | 100
247 | BIRBHUM | Birbhum Division | Chora Piped Water Supply Scheme , SM/15523 | New | Material Requisition To Resource Division | 439/BHM | 01/02/2024 | 0 | Resource Division | 54.82 | 0 | 0 | 0
248 | BIRBHUM | Birbhum Division | Chora Piped Water Supply Scheme , SM/15523 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
249 | BIRBHUM | Birbhum Division | Chora Piped Water Supply Scheme , SM/15523 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
250 | BIRBHUM | Birbhum Division | Amlachaturi Piped Water Supply Scheme , SM/16387 | New | Material Requisition To Resource Division | 1574/BHM | 26/04/2023 | 0 | Resource Division | 20.07 | 0 | 0 | 0
251 | BIRBHUM | Bolpur Mechanical | Amlachaturi Piped Water Supply Scheme , SM/16387 | New | QUOTATION FOR AMLACHATURI PWSS | BP-24-25-05 | 09/04/2024 | 0 | WBSEDCL | 5.03 | 0 | 0 | 0
252 | BIRBHUM | Bolpur Mechanical | Amlachaturi Piped Water Supply Scheme , SM/16387 | New | Providing Electro-mechanical accessories and others for Amlachaturi & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | 2167/Bol.MD | 31/08/2023 | 584 | SATYAJIT GHOSH | 88.42 | 0 | 0 | 85
253 | BIRBHUM | Birbhum Division | Amlachaturi Piped Water Supply Scheme , SM/16387 | New | Different works related to water supply scheme at AMLACHATURI & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 4136/BHM | 18/10/2023 | 806 | M/S KRIPASINDHU GHOSH & CO. | 531.73 | 0 | 0 | 20
254 | BIRBHUM | Birbhum Division | Amlachaturi Piped Water Supply Scheme , SM/16387 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
255 | BIRBHUM | Birbhum Division | Budhigram Piped Water Supply Scheme , SM/16762 | New | Continuation Work Order for Preparation & Submission of DPR for (Budhigram) Water Supply Scheme under Rampurhat-II Development Block. | 276/RSD | 18/08/2022 | 45 | ECO CARE | 4.73 | 0 | 0 | 100
256 | BIRBHUM | Birbhum Division | Budhigram Piped Water Supply Scheme , SM/16762 | New | Material Requisition To Resource Division | 1490/BHM | 25/04/2023 | 0 | Resource Division | 17.6 | 0 | 0 | 0
257 | BIRBHUM | Bolpur Mechanical | Budhigram Piped Water Supply Scheme , SM/16762 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Budhigram PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 519/BOL.MD | 14/03/2024 | 349 | TAPAN ENTERPRISE | 7.61 | 0 | 0 | 60
258 | BIRBHUM | Bolpur Mechanical | Budhigram Piped Water Supply Scheme , SM/16762 | New | Providing Electro-mechanical accessories and others for Budhigram PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 2227/Bol.MD | 12/09/2023 | 688 | SUNIL RABIDAS | 44.41 | 0 | 0 | 30
259 | BIRBHUM | Birbhum Division | Budhigram Piped Water Supply Scheme , SM/16762 | New | Sinking of 250 X 150 mm Dia (through) and 180 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Budhigram & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3315/BHM | 04/12/2024 | 730 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 346.49 | 0 | 0 | 30
260 | BIRBHUM | Bolpur Mechanical | Sahapur Piped water Supply Scheme. , SM/13649 | New | Providing electro-mechanical accessories and others for Shapaur & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | 307/Bol.MD | 23/03/2023 | 366 | A. G. ENTERPRISE | 93.34 | 0 | 0 | 0
261 | BIRBHUM | Birbhum Division | Sahapur Piped water Supply Scheme. , SM/13649 | New | Material Requisition To Resource Division | 1556/BHM | 26/04/2023 | 0 | Resource Division | 138.02 | 0 | 0 | 0
262 | BIRBHUM | Bolpur Mechanical | Sahapur Piped water Supply Scheme. , SM/13649 | New | Providing electro mechanical accessories and others for Sahapur and Adjoining Mouzas Water Supply Scheme under Bolpur Mechanical Division, PHE Dte | 319/Bol.MD | 27/03/2023 | 366 | A. G. ENTERPRISE | 93.34 | 0 | 0 | 50
263 | BIRBHUM | Birbhum Division | Sahapur Piped water Supply Scheme. , SM/13649 | New | Material Requisition To Resource Division | 219/BHM | 24/01/2024 | 0 | Resource Division | 5.24 | 0 | 0 | 0
264 | BIRBHUM | Bolpur Mechanical | Sahapur Piped water Supply Scheme. , SM/13649 | New | Quotation for new service connection at Sahapur TW No-I (Block-Rampurhat-II) |  | 13/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.89 | 0 | 0 | 0
265 | BIRBHUM | Bolpur Mechanical | Sahapur Piped water Supply Scheme. , SM/13649 | New | WBSEDCL QUOTATION FOR SAHAPUR TW-II |  | 14/03/2024 | 0 | WBSEDCL | 3.21 | 0 | 0 | 0
266 | BIRBHUM | Birbhum Division | Sahapur Piped water Supply Scheme. , SM/13649 | New | Different works related to water supply scheme at NABAGRAM, SAHAPUR & SHASPUR and its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3522/BHM | 11/08/2023 | 821 | SUNIL RABI DAS | 1157.77 | 0 | 0 | 40
267 | BIRBHUM | Bolpur Mechanical | Masra Piped Water Supply Scheme. , SM/18463 | New | Providing Electro-mechanical accessories and others for Masra Zone - II PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 3520/BOL.MD | 29/11/2023 | 60 | CINZANO | 28.82 | 0 | 0 | 0
268 | BIRBHUM | Bolpur Mechanical | Masra Piped Water Supply Scheme. , SM/18463 | New | Providing Electro-mechanical accessories and others for Masra Zone - I PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 3521/Bol.MD | 29/11/2023 | 60 | DEY ENTERPRISE | 27.71 | 0 | 0 | 0
269 | BIRBHUM | Birbhum Division | Masra Piped Water Supply Scheme. , SM/18463 | New | Material Requisition To Resource Division | 1571/BHM | 26/04/2023 | 0 | Resource Division | 14.85 | 0 | 0 | 0
270 | BIRBHUM | Birbhum Division | Masra Piped Water Supply Scheme. , SM/18463 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuMOHR (ZONE-I) & 350 CuM (ZONE-II) ,Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at MASHRA & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 2514/BHM | 04/09/2024 | 365 | GARGO TRADERS | 915.63 | 0 | 0 | 0
271 | BIRBHUM | Birbhum Division | Masra Piped Water Supply Scheme. , SM/18463 | New | Material Requisition To Resource Division | 3264/BHM | 02/12/2024 | 0 | Resource Division | 24.27 | 0 | 0 | 0
272 | BIRBHUM | Birbhum Division | Dadpur Piped Water Supply Scheme. , SM/12684 | New | Material Requisition To Resource Division | 1537/BHM | 26/04/2023 | 0 | Resource Division | 31.16 | 0 | 0 | 0
273 | BIRBHUM | Bolpur Mechanical | Dadpur Piped Water Supply Scheme. , SM/12684 | New | Providing Electro-mechanical accessories and others for DADPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 3289/Bol.MD | 29/09/2023 | 784 | QUAZI NOZRUL ISLAM | 27.77 | 0 | 0 | 60
274 | BIRBHUM | Bolpur Mechanical | Dadpur Piped Water Supply Scheme. , SM/12684 | New | Additional Quotation charges for Modification of Dadpur, Murarai CCC under Bolpur Mechanical Division, PHE Dte. | BP-2024-2025-17 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.69 | 0 | 0 | 0
275 | BIRBHUM | Bolpur Mechanical | Dadpur Piped Water Supply Scheme. , SM/12684 | New | WBSEDCL QUOTATION MONEY FOR DADPUR P H NO.I WS SCHEME | BP-23-24-253 | 06/02/2024 | 0 | WBSEDCL | 2.72 | 0 | 0 | 0
276 | BIRBHUM | Bolpur Mechanical | Dadpur Piped Water Supply Scheme. , SM/12684 | New | Quotation deposit for empowering Dadpur Water Supply Scheme P/H -III in Murarai CCC under Bolpur Mechanical Division, PHE Dte. | BP-24-25-106 | 02/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.7 | 0 | 0 | 0
277 | BIRBHUM | Bolpur Mechanical | Dadpur Piped Water Supply Scheme. , SM/12684 | New | WBSEDCL QUOTATION MONEY FOR DADPUR P H NO.II WS SCHEME | BP-23-24-254 | 06/02/2024 | 0 | WBSEDCL | 2.7 | 0 | 0 | 0
278 | BIRBHUM | Birbhum Division | Dadpur Piped Water Supply Scheme. , SM/12684 | New | Different works related to water supply scheme at DADPUR & its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 839/BHM | 16/03/2023 | 1234 | NABIN DEBNATH | 315.84 | 0 | 0 | 80
279 | BIRBHUM | Birbhum Division | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area , SM/06943 | Retrofitting | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Rajnagar Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 10) | 382/BSSD | 10/12/2021 | 20 | SUBHANKAR ROY | 0.99 | 0 | 0 | 49
280 | BIRBHUM | Birbhum Division | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area , SM/06943 | Retrofitting | Additional work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages of Madarpur, Joypur, Talpukur, Ruhida, Ranigram, Hirapur, Mursabani, Lauberia of Aligarh Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.¿ (Sl. No.2) | 2152/BHM | 28/09/2022 | 60 | M/S KRIPASINDHU GHOSH & CO. | 13.95 | 13.78 | 100 | 100
281 | BIRBHUM | Birbhum Division | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area , SM/06943 | Retrofitting | Additional work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villagesTilabani, Ramnagar, Dhaka, Gangapur, Aligarh of Aligarh Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte. | 2177/BHM | 29/09/2022 | 60 | M/S GOUTAM DAS | 12.16 | 11.58 | 49.07 | 100
282 | BIRBHUM | Birbhum Division | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area , SM/06943 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Tilabani, Ramnagar, Dhaka, Gangapur, Aligarh of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte | 1168 /BHM | 21/09/2020 | 60 | M/S GOUTAM DAS | 37.14 | 66.24 | 178.41 | 0
283 | BIRBHUM | Birbhum Division | Retrofitting works for Aligarh (Phase-II) water supply scheme for providing Functional Household Tap Connection (FHTC) within the command area , SM/06943 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages (Murgathali, Ashna, Sundarkhela, Jahanbal) of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. | 1169/BHM | 21/09/2020 | 60 | PRANAB KUMAR GHOSH | 40.55 | 57.44 | 178.55 | 0
284 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block , SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rasa w/s Scheme in Suri Sadar Sub-Division under Birbhum Division, PHE Dte. (2nd Call) (Sl. No.15) | 2166/BHM | 24/12/2021 | 60 | RICK CONSTRUCTION | 48.67 | 43.63 | 100 | 100
285 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block , SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Dompara & Colony under Rasa Mouza (J.L. No.107) under Khoyrasole Block within the command area of RASA Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.28) | 203 /BSSD | 15/06/2021 | 30 | SACHIN KUMAR SARKAR | 4.96 | 0 | 0 | 0
286 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block , SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Muchipara under Rasa Mouza (J.L. No.107) under Khoyrasole Block within the command area of RASA Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.24) | 201 /BSSD | 15/06/2021 | 30 | ASIT GHOSH | 4.95 | 0 | 0 | 0
287 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block , SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Kayastaparaunder Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 22) | 199/BSSD | 15/06/2021 | 30 | B.M.SARKAR | 4.95 | 9.82 | 200 | 100
288 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block , SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Bauriparaunder Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 21) | 198/BSSD | 15/06/2021 | 30 | DIPAK SARKAR | 4.85 | 9.4 | 200 | 100
289 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block , SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Muchiparaunder Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte.(Sl. No. - 24)) | 201/BSSD | 15/06/2021 | 30 | ASIT GHOSH | 4.95 | 9.9 | 200 | 100
290 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block , SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Dompara & Coloney under Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 28) | 203/BSSD | 15/06/2021 | 30 | SACHIN KUMAR SARKAR | 4.96 | 9.93 | 200 | 100
291 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block , SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Keotparaunder Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 23) | 200/BSSD | 15/06/2021 | 30 | BHABATARAN SADHU | 4.98 | 9.91 | 200 | 100
292 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block , SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Chasapara under RASA Mouza (J.L. No.107) under Khoyrasole Block within the command area of RASA Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.26) | 202/BSSD | 15/06/2021 | 30 | ARKA JYOTI GHOSH | 4.79 | 4.77 | 100 | 100
293 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block , SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Jamrand Chasapara under Jamrand Mouza (JL No. - 136) under Khoyrasole Block, within the command area of Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 31) | 206 /BSSD | 15/06/2021 | 30 | SUMEN CHOWDHURY | 4.97 | 0 | 0 | 100
294 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block , SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Acharjyapara under Rasa Mouza (JL No. - 107) under Khoyrasole Block, within the command area of Rasa Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte.(Sl. No. - 25) | 212/BSSD | 15/06/2021 | 30 | GOUTAM MONDAL | 4.95 | 9.88 | 200 | 0
295 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Rasa (Phase-I ) PWSS within Khoyrasole Block , SM/07651 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rasa in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte.(Sl. No.9) | 2587/BHM | 22/11/2022 | 60 | HIRANMAY GHOSH | 58.98 | 19.21 | 100 | 49
296 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) , SM/06737 | Retrofitting | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Chandpara Habitation of Chandpara Village under Dunigram Gram Panchayet, Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte. | 287/RSD | 31/12/2020 | 15 | ABUL HASNAT | 0.1 | 0.1 | 100 | 100
297 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) , SM/06737 | Retrofitting | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Different places of Mayureswar-I & Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte. | 290/RSD | 31/12/2020 | 15 | ABUL HASNAT | 0.07 | 0.07 | 100 | 100
298 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) , SM/06737 | Retrofitting | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Chandpara Habitation of Chandpara Village under Dunigram Gram Panchayet, Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte | 286/RSD | 31/12/2020 | 15 | ABUL HASNAT | 0.1 | 0.1 | 100 | 100
299 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) , SM/06737 | Retrofitting | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Kamra, Kayemba, Shilgram Habitation of Kamra, Kayemba, Shilgram Village under Dunigram Gram Panchayet, Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte. | 288/RSD | 31/12/2020 | 15 | ABUL HASNAT | 0.09 | 0.09 | 100 | 100
300 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) , SM/06737 | Retrofitting | Collection of data on availability of water sources of Household details through Manual Form or Mobile App including Geo-reference and submission of the same in soft copy against completed FHTC work at the command area of Dunigram, Harirampur Habitation of Dunigram Village under Dunigram Gram Panchayet, Rampurhat-II Block under Rampurhat Sub-Division, PHE Dte. | 289/RSD | 31/12/2020 | 15 | ABUL HASNAT | 0.1 | 0.1 | 100 | 100
301 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) , SM/06737 | Retrofitting | Providing Tap Connection for Existing School & AWC under Shilogram, Kamra,Kayemba,Chandpara, Harirampur Mouzas in Dunigram PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. | 275/RSD | 16/07/2021 | 10 | MD ABSAR ALI | 0.99 | 0 | 0 | 50
302 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) , SM/06737 | Retrofitting | Laying of Distribution System with UPVC Pipes and Providing Tap Connection for Existing School & AWC under Dunigram Mouza in Dunigram PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. | 274/RSD | 16/07/2021 | 10 | MD ABSAR ALI | 1 | 1 | 100 | 50
303 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) , SM/06737 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kayemba, Bara Chauki of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.5) | 1239/BHM | 28/09/2020 | 60 | KAZI EMDADUL HAQUE | 32.58 | 50.35 | 200 | 0
304 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) , SM/06737 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Shigram of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. | 1177 /BHM | 21/09/2020 | 60 | M/S MD AMINUL ISLAM | 31.84 | 52.61 | 200 | 0
305 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-I) , SM/06737 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kamra, Harirampur of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.4) | 1238 /BHM | 28/09/2020 | 45 | UMWELT ENGINEER PVT. LTD | 29.57 | 51.01 | 200 | 0
306 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum , SM/07530 | Retrofitting | Laying of distribution system including FHTC for village Geruapahari, J.L No.74, G.P Babuijore, Block Khorasole for ensuing draught like situation within Birbhum Division, PHE Dte.? (Sl. No.5) | 507 / BHM | 03/03/2022 | 45 | DIPAK SARKAR | 12.24 | 12.22 | 100 | 100
307 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum , SM/07530 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Babuijore Zone-II Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, PHE Dte. (2nd Call) (Sl. No.12) | 819/BHM | 13/04/2022 | 60 | PRAVAT SARKAR | 76.14 | 72.78 | 95.58 | 87
308 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum , SM/07530 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area village of Barrah, Kadamdanga & Dhulkumro of Babuijore (Zone-II) Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No.1) | 2433/BHM | 02/11/2022 | 60 | PRAVAT SARKAR | 87.09 | 80.36 | 92.27 | 82
309 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum , SM/07530 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Babuijore Zone-I Water Supply Scheme within Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.9) | 136/BHM | 25/01/2022 | 60 | HIRANMAY GHOSH | 76.5 | 76.16 | 100 | 100
310 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum , SM/07530 | Retrofitting | Additional work for Construction of 300 Cum Capacity and 20.0m Staging Height RCC Over Head Reservoir & Laying Distribution System including all allied Works as per departmental drawing at Zone-I of Babuijore Piped Water Supply Scheme under Birbhum Sadar Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. (2nd Phase)(Sl. No. - 05) | 402/BSSD | 14/12/2021 | 15 | SUNDAR CONSTRUCTION | 4.63 | 0 | 0 | 100
311 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum , SM/07530 | Retrofitting | Construction of drain & repairing of Culvert for 300 mm dia. rising main crossing under Culvert at Bara village of Babuijore Piped Water Supply Scheme under Birbhum Sadar Sub-Dvision, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. (Sl. No. - 03) | 401/BSSD | 14/12/2021 | 15 | HIRANMAY GHOSH | 2.03 | 0 | 0 | 100
312 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Babuijore PWSS within Khoyrasole Block, Dist.- Birbhum , SM/07530 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area village of Barrah, Kadamdanga and Kaithi of Babuijore (Zone-II) Piped Water Supply Scheme under Birbhum Sadar Sub Division , P.H.E Dte within Birbhum Division P.H.E Dte. | 1635/BHM | 02/05/2023 | 60 | THREE MAA ENTERPRISE | 70 | 0 | 0 | 100
313 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum , SM/07532 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maldanga Zone-I Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, PHE Dte¿(Sl. No.7) | 278/BHM | 09/02/2022 | 60 | APORUPA CONSTRUCTION | 63.41 | 63.34 | 100 | 100
314 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum , SM/07532 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maldanga Zone-II Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.8) | 281/BHM | 09/02/2022 | 60 | BIJOY KUMAR CHOUDHURY | 52.83 | 43.55 | 82.44 | 95
315 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum , SM/07532 | Retrofitting | Connection of distribution pipeline at node 6-40, rising main at MDMC main canal crossing node 147-148 & construction of sluice valve chambers & all other allied works at different locations under Maldanga Piped Water Supply Scheme of Birbhum Division, P.H.E. Dte.(Sl. No.1) | 2031/BHM | 09/12/2021 | 60 | ARPAN PANDIT | 9.53 | 0 | 0 | 100
316 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum , SM/07532 | Retrofitting | Surveying, Planning etc. including obtaining permission on behalf of PHE Dte Supply, Laying & Pushing of 600 mm dia. 10 mm thick M.S Spiral Welded Casing Pipe by of Fe 410 grade as per IS: 3589-2001 Adopting Trenchless Technologies (Jack Pushing Method) under in between NH road crossing for 200 mm dia. Distribution Line at Joypur More (Node Point 25) under Maldanga W/S Scheme within Birbhum Division, PHE Dte.¿ (Sl. No.1) | 524/BHM | 11/03/2022 | 45 | MANASH GHOSH | 19.61 | 0 | 0 | 50
317 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum , SM/07532 | Retrofitting | Supply & delivery of sluice valve for Maldanga Zone-I W/S scheme under Birbhum Division, PHE Dte including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. (Sl. No.-01) | 419/BHM | 24/02/2022 | 15 | BIJOY KUMAR CHOUDHURY | 0.92 | 0 | 0 | 100
318 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum , SM/07532 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for balance Household from existing distribution system within the command area of Maldanga under Maldanga Water Supply Scheme within Birbhum Division, PHE Dte. | 1452/BHM | 07/07/2022 | 60 | APORUPA CONSTRUCTION | 64.41 | 0 | 0 | 100
319 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Maldanga PWSS within Md.Bazar Block, Dist.- Birbhum , SM/07532 | Retrofitting | Withdrawing & restroration of 100 mm & 200 mm dia distribution & rising main pipe line at bridge crossing near Maldanga village & providing FHTC for the village of Moulpur, Bhututa & chatrama to declre "SAJAL GRAM" of Maldanga piped water supply scheme under Birbhum division P.H.E Dte. | 1172/BHM | 11/04/2023 | 15 | SOURAV MONDAL | 0.98 | 0 | 0 | 100
320 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09371 | Retrofitting | Laying & distribution system with UPVC pipes including FHTC (Functional Household Tap Connection) for Belera PWSS under Birbhum, Division, PHE Dte. (Sl. No.1) | 2165/BHM | 28/09/2022 | 30 | OM ENTERPRISE | 34.22 | 29.62 | 100 | 90
321 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09371 | Retrofitting | Laying of Rising main with DI pipe line for inter connection of 3 Nos TW for Belera Piped Water Supply Scheme under Rampurhat sub division under Birbhum Division, PHE Dte. | 110/RSD | 07/03/2022 | 60 | MD. SHAHA JAMAL | 4.52 | 0 | 0 | 100
322 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09371 | Retrofitting | Sinking of 01 Nos (3rd TW) Tube well 200mm dia 90 m. deep tube well fitted with PVC pipe and fiber glass Strainer at Belera PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 108/RSD | 07/03/2022 | 30 | SK FAQHRUL AMIN | 4.85 | 0 | 0 | 100
323 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09371 | Retrofitting | Sinking of 01 Nos (1st TW) Tube well 200mm dia 90 m. deep tube well fitted with PVC pipe and fiber glass Strainer at Belera PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 107/RSD | 07/03/2022 | 30 | SK FAQHRUL AMIN | 4.85 | 0 | 0 | 100
324 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09371 | Retrofitting | Supply and delivery of Sluice Valve & Duck Foot Bend for Belera W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.¿ (Sl. No.2) | 376/BHM | 21/02/2022 | 15 | SSPR VALVE MANUFACTURING PVT LTD | 6.71 | 0 | 0 | 100
325 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Belera PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09371 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Belera Water Supply Scheme within Rampurhat Sub-Division, Birbhum Division, PHE Dte. (Sl. No.4) | 747/BHM | 05/04/2022 | 60 | S K CONSTRUTION | 73.03 | 72.43 | 100 | 100
326 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Bhatra, Abdullapur and adjacent area under Rajgram W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 592/AE/NSD | 23/11/2021 | 45 | MD ASIF ALI | 4.82 | 0 | 0 | 50
327 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | repairing of the Pump house & C.W.R of the Rajnagar Pipe Water Supply Scheme under Birbhum Division, P.H.E .Dte, Suri , Birbhum. | 33/BH | 09/03/2022 | 30 | RANJIT GHOSH | 0.76 | 0 | 0 | 50
328 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Repairing of the Pump House & CWR of the Rajnagar Pipe Water Supply under RWS Birbhum Sub-Division,PHE Dte. Suri, Birbhum. | 33/BH | 09/03/2022 | 30 | RANJIT GHOSH | 0.76 | 0.7 | 100 | 50
329 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Supply & delivery of sluice valve for Augmentation of Rajnagar W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex Dist.-Birbhum under Birbhum Division, PHE Dte. (Sl. No.-01) | 421/BHM | 24/02/2022 | 15 | UJJWAL DAS | 4.86 | 4.86 | 100 | 100
330 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Laying distribution system for proposed augmentation scheme for Rajnagar Piped Water Supply Scheme under Rajnagar Block, under Birbhum Division, PHE Dte. (Sl. No.8) | 94/BHM | 21/01/2022 | 180 | UJJWAL DAS | 315.1 | 292.97 | 92.98 | 100
331 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Construction of 500cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Rajnagar W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | 1256/BHM | 17/04/2023 | 275 | M/S KRIPASINDHU GHOSH & CO. | 128.12 | 0 | 0 | 0
332 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Additional pipe line for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area except Daspara & Idgacha village of Rajnagar Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | 1724/BHM | 12/05/2023 | 45 | UJJWAL DAS | 14.53 | 0 | 0 | 0
333 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Providing Electro-mechanical accessories and others at low lift site for Augmentation of Rajnagar water supply scheme under Bolpur Mechanical Division PHE Dte | 1412/Bol.MD | 10/07/2023 | 45 | AMITAVA CHAKRABORTY | 18.99 | 18.99 | 100 | 0
334 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Supply and Installation of Pumping Machineries at Matiara Village (within Augmentation of Rajnagar PWSS) Under Bolpur Mechanical Division, PHED. | 1420/Bol.MD | 10/07/2023 | 30 | M/S SANTI CONSTRUCTION | 6.68 | 5.79 | 86.74 | 0
335 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Construction of Boundary Wall with drain at Pump House & CWR of Rajnagar Piped Water Supply Scheme, under RWS Birbhum Sub-Division within Birbhum Division, P.H.E. Dte. (Sl. No.10) | 32/BHM | 04/01/2023 | 45 | SYED GOLAM ZILANI | 9.18 | 8.2 | 100 | 100
336 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Trial Bore and Sinking for 03 nos. 200mm dia. Tubewell of 5m depth with horizontal strainer on the river Bed of Kuskorini under Rajnagar Piped Water Supply Scheme within Birbhum Sadar Sub-Division, P.H.E. Dte. under Birbhum Division P.H.E. Dte. (Sl. No. - 04) | 270/BSSD | 11/11/2022 | 15 | INDRANIL DUTTA | 4.84 | 4.84 | 100 | 100
337 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system at Daspara under Nakash Village within the command area of Rajnagar Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte.(Sl. No. -07) | 219/BSSD | 21/09/2022 | 15 | UJJWAL DAS | 4.98 | 4.98 | 100 | 100
338 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system at Idgacha under Nakash village within the command area of Rajnagar Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. (Sl. No. -01) | 213/BSSD | 21/09/2022 | 15 | UJJWAL DAS | 4.95 | 4.94 | 100 | 100
339 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Supply and Installation of Pumping Machineries at ISGARA Village (within Augmentation of Rajnagar PWSS) Under Bolpur Mechanical Division, PHED | 1413/BOL.MD | 10/07/2023 | 30 | RAJIB GHOSH | 6.73 | 6.67 | 100 | 30
340 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Material Requisition To Resource Division | 487/BHM | 02/03/2022 | 0 | Resource Division | 30.25 | 0 | 0 | 0
341 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Material Requisition To Resource Division | 193/BHM | 01/02/2022 | 0 | Resource Division | 25.77 | 0 | 0 | 0
342 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Material Requisition To Resource Division | 214/BHM | 02/02/2022 | 0 | Resource Division | 21.82 | 0 | 0 | 0
343 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Material Requisition To Resource Division | 1110/BHM | 10/04/2023 | 0 | Resource Division | 14.64 | 0 | 0 | 0
344 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Supply, delivery and installation of of Voltage correction device at panchiara water supply scheme( with in Rajnagar Augmentation Water Supply , Block : Rajnagar), under Bolpur Mechanical Division, P.H.E. Dte. | 2245/Bol.MD | 13/09/2023 | 60 | M/S P.P ELECTRICALS | 23.98 | 0 | 0 | 30
345 | BIRBHUM | Birbhum Division | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Balance work for laying of pipe line including FHTC for augmentation of Rajnagar Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | 1876/BHM | 31/05/2023 | 60 | OM ENTERPRISE | 56.94 | 0 | 0 | 100
346 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Supply delivery & installation of voltage correction device at Augmentation of Rajnagar water supply scheme under Bolpur Mechanical Division, PHE Dte | 2264/Bol.MD | 14/09/2023 | 45 | CINZANO | 15.85 | 0 | 0 | 100
347 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Replacement of voltage correction device at Khoyrasole (Churur) water supply scheme (AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME) under Bolpur Mechanical Division, PHE Dte | 33/BOL.MD | 10/01/2024 | 30 | S.DUTTA | 15.87 | 0 | 0 | 100
348 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Modification of MCC panel of Isgara Mini water supply scheme under Bolpur Mechanical Division, PHE. Dte. | 1658/AE-III | 22/12/2023 | 6 | RAJIB GHOSH | 0.16 | 0 | 0 | 100
349 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Supply & delivery of Cable for Aug. Rajnagar water supply scheme under Bolpur Mechanical Division, PHE. Dte. | 296/AE-III | 22/02/2024 | 10 | SATYAJIT GHOSH | 3.86 | 0 | 0 | 100
350 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Supply and Delivery of Sub-Mersible Pump Controllers for Augmentation of Rajnagar water supply scheme (Block- Rajnagar) under Bolpur Mechanical Division, PHE Dte. | 301/AE-III | 22/02/2024 | 10 | HINDOL ROY | 4.56 | 0 | 0 | 100
351 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Supply & delivery of High lift pumping machinery at store for Aug. Rajnagar and others water supply scheme under Bolpur Mechanical Division, PHE. Dte. | 300/AE-III | 22/02/2024 | 10 | SWAPAN BANERJEE | 2.75 | 0 | 0 | 100
352 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Supply , delivery and installation of Submersible pumping machinery and others allied work at newly sunk T/W of Aligarh & Adjoining mouzas Water Supply Scheme at Aug. of Rajnagar PWSS under Bolpur Mechanical Division, PHE. Dte. | 4344/BOL.MD | 13/11/2024 | 30 | M/S M3 SOLUTION | 8.11 | 0 | 0 | 100
353 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Replacement of voltage correction device at Augmentation of Rajnagar water supply scheme under Bolpur Mechanical Division, PHE Dte. | 368/BOL.MD | 06/03/2024 | 30 | GOENKA ENTERPRISE | 14.34 | 0 | 0 | 100
354 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Supply and delivery of outdoor type pump controller unit for Augmentation of Rajnagar under Ahmadpur PWSS in Rajnagar block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 1345/Bol.MD | 03/05/2024 | 45 | M/S. UTTAM KUMAR CHATTERJEE | 20.06 | 0 | 0 | 100
355 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Supply and Delivery of high lift pumping Machinery for Augmentation of Rajnagar and other water supply scheme under Bolpur Mechanical Division PHE Dte. | 605/AE-III | 27/03/2024 | 7 | M/S M3 SOLUTION | 2.75 | 0 | 0 | 100
356 | BIRBHUM | Bolpur Mechanical | AUGMENTATION OF RAJNAGAR PIPE WATER SUPPLY SCHEME. , SM/09438 | Augmentation | Testing and refilling of empty chlorine gas cylinder of Rajnagar and adjoining mouzas & Different Rural water supply scheme under Bolpur Mechanical Division, PHE. Dte. | 302/AE-III | 22/02/2024 | 247 | UNIVERSAL ENTERPRISES | 4.84 | 0 | 0 | 100
357 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. , SM/08892 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area at Dakshin Tilpara Nutanpara, Sukantapally & Mudidangal of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte.(Sl. No. ¿ 04) | 90/BSSD | 27/05/2022 | 20 | RAJKUMAR DAS | 4.95 | 4.58 | 100 | 100
358 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. , SM/08892 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Laldighipara under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte.(Sl. No. -09) | 167/BSSD | 16/08/2022 | 20 | SACHIN KUMAR SARKAR | 2.72 | 2.3 | 100 | 100
359 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. , SM/08892 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Kalpatarupally under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. -08) | 262/BSSD | 20/10/2022 | 20 | M/S SARADA CONSTRUCTION. | 2.67 | 2.1 | 100 | 91
360 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. , SM/08892 | Retrofitting | Extension of 75 mm dia.UPVC distribution pipe line from Hatzen Bazar Post Office Para at Zone - IV (Part-B) under Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 01) | 319/BSSD. | 13/09/2021 | 20 | ARPAN PANDIT | 4.09 | 0 | 0 | 0
361 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. , SM/08892 | Retrofitting | Laying of Distribution Pipe line of Tilpara Piped Water Supply Scheme from OHR towards Kalitala (Tilpara) under Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. (Sl. No. - 19) | 274/BSSD | 06/08/2021 | 20 | PUSPAJIT MONDAL | 4.94 | 4.91 | 100 | 100
362 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. , SM/08892 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Kalpatarupally under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl.No. -02) | 336/BSSD | 23/09/2021 | 20 | M/S SARADA CONSTRUCTION. | 4.02 | 4.01 | 100 | 100
363 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. , SM/08892 | Retrofitting | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Suri- I Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 05) | 380/BSSD | 10/12/2021 | 20 | AATHARVA CONSTRUCTION | 0.99 | 0 | 0 | 50
364 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. , SM/08892 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Laldighipara under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 03) | 353/BSSD. | 25/10/2021 | 20 | SACHIN KUMAR SARKAR | 3.88 | 3.88 | 100 | 100
365 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. , SM/08892 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tilpara w/s Scheme (Left out House Hold) in Suri Sadar Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.1) | 1506/BHM | 09/09/2021 | 60 | RAJKUMAR DAS | 39.43 | 39.29 | 100 | 50
366 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. , SM/08892 | Retrofitting | Laying of Distribution Pipe line of Tilpara Piped Water Supply Scheme from Kalitala(Tilpara) towards PWD (Roads) office under Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. (Sl. No. - 02) | 273/BSSD | 06/08/2021 | 20 | UTPAL DEY | 4.92 | 4.91 | 100 | 0
367 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. , SM/08892 | Retrofitting | Trial Bore and Sinking of 200 mm dia. replacement tubewell 3 (Three) nos. each 39 m. Deep fitted with PVC Housing pipe and Fibre Glass Strainer on the river bank of Mayurakshi including connecting pipe line under Tilpara Piped Water Supply Scheme within Birbhum Division, PHE Dte. | 2506/BHM | 03/09/2024 | 45 | AMIT KUMAR ROY | 7.63 | 0 | 0 | 100
368 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. , SM/08892 | Retrofitting | Laying of UPVC Pipeline including all allied works for By passs arrangement at Kamalpur village for smooth supply of drinking water through existing FHTC under Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. | 205/BHM | 16/01/2025 | 45 | RAJ KUMAR DAS | 1.29 | 0 | 0 | 100
369 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area TILPARA (Phase-II) WATER SUPPLY SCHEME of Suri-I Block under Birbhum Division, PHE Dte. , SM/08892 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area village of Laldighipara under Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. | 909/BHM | 13/03/2024 | 45 | RAJKUMAR DAS | 2.89 | 0 | 0 | 100
370 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Panchra PWSS within Khoyrasole Block District Birbhum under Birbhum Division, PHE Dte. , SM/09490 | Retrofitting | Construction of boundary wall at Panchara OHR site of Panchara PWSS under Birbhum Sadar Sub-Division, PHE Dte. (Sl. No.09) | 949/BHM | 12/08/2020 | 45 | BHABANI ENTERPRISE | 4.97 | 0 | 0 | 100
371 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Panchra PWSS within Khoyrasole Block District Birbhum under Birbhum Division, PHE Dte. , SM/09490 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of Panchra under Panchra Water Supply Water Supply Scheme within Birbhum Division, PHE Dte. (Sl. No.9) | 2773/BHM | 14/12/2022 | 60 | MANASH GHOSH | 93.92 | 0 | 0 | 65
372 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Panchra PWSS within Khoyrasole Block District Birbhum under Birbhum Division, PHE Dte. , SM/09490 | Retrofitting | Balance work of Laying distribution pipe line, FHTC & Jack Pushing for the work at Panchra under the Panchra Piped Water Supply Scheme within Khoyrasole Development Block under Birbhum Division, PHE Dte. | 1095/BHM | 06/04/2023 | 548 | MANASH GHOSH | 464.71 | 0 | 0 | 50
373 | BIRBHUM | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme , SM/10343 | Augmentation | Material Requisition To Resource Division | 2556/BHM | 21/11/2022 | 0 | Resource Division | 288.93 | 0 | 0 | 0
374 | BIRBHUM | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme , SM/10343 | Augmentation | Laying distribution system including FHTC for proposed augmentation scheme for Khayrasole Zone-I Piped Water Supply Scheme, Khayrasole Block, under Birbhum Division, PHE Dte.¿ (Sl. No.4) | 1157/BHM | 23/05/2022 | 180 | M/S S.S. ENTERPRISE | 372.63 | 372.32 | 99.92 | 80
375 | BIRBHUM | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme , SM/10343 | Augmentation | Laying distribution system including FHTC for proposed augmentation scheme for Khayrasole Zone-II Piped Water Supply Scheme, Khayrasole Block, under Birbhum Division, PHE Dte? (Sl. No.5) | 1149/BHM | 23/05/2022 | 180 | TIRUPATI ENTERPRISES | 229.96 | 223.47 | 97.18 | 85
376 | BIRBHUM | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme , SM/10343 | Augmentation | Trial Bore and Sinking of 200 mm dia. 2(Two) nos.tubewell 30m. (avg.) depth fitted with PVC pipes & fittings Schedule 80 (medium duty) and Fibre Glass Strainer on the river bank of Ajoy under Khayrasole Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, PHE Dte. (Sl. No. -01) | 73/BSSD | 02/05/2022 | 15 | SK FAQHRUL AMIN | 3.8 | 2.89 | 100 | 100
377 | BIRBHUM | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme , SM/10343 | Augmentation | Laying of Distribution Pipe line from Dihipara Hanuman Mandir to Kendragaria Railway crossing under Khoyrasole Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. (Sl. No. - 04) | 398/BSSD | 10/12/2021 | 15 | B.M.SARKAR | 4.99 | 4.97 | 100 | 100
378 | BIRBHUM | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme , SM/10343 | Augmentation | Construction of PCC Pillar for laying of 250 mm dia. rising main pipe line over Hinglow River near Pansuili for Khayrasole Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | 1043/BHM | 31/03/2023 | 30 | HIRANMAY GHOSH | 4.55 | 4.46 | 100 | 100
379 | BIRBHUM | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme , SM/10343 | Augmentation | Replacement of rising main pipe line from AC Pipe line to DI K9 and concreting work in the premesis of CWR site and other allied works under Augmentation of Khayrasole Piped Water Supply Scheme (Zone-I) under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division PHE Dte.(Sl. No. -16) | 227/BSSD | 21/09/2022 | 20 | HIRANMAY GHOSH | 4.88 | 4.73 | 100 | 0
380 | BIRBHUM | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme , SM/10343 | Augmentation | Material Requisition To Resource Division | 900/BHM | 26/04/2022 | 0 | Resource Division | 9.93 | 0 | 0 | 0
381 | BIRBHUM | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme , SM/10343 | Augmentation | Material Requisition To Resource Division | 2292/BHM | 20/10/2022 | 0 | Resource Division | 64.91 | 0 | 0 | 0
382 | BIRBHUM | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme , SM/10343 | Augmentation | Construction of 700cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Khyarasole Zone I W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | 1255/BHM | 17/04/2023 | 275 | M/S KRIPASINDHU GHOSH & CO. | 151.36 | 0 | 0 | 70
383 | BIRBHUM | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme , SM/10343 | Augmentation | Construction of 200cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Khyarasole Zone II W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | 1646/BHM | 02/05/2023 | 276 | U TURN CONSTRUCTION | 71.24 | 0 | 0 | 89
384 | BIRBHUM | Birbhum Division | Augmentation of Khoyrasole Piped Water Supply Scheme , SM/10343 | Augmentation | Balance work for Laying distribution system including FHTC for proposed augmentation scheme for Khayrasole Zone-I Piped Water Supply Scheme, Khayrasole Block, under Birbhum Division, P.H.E. Dte | 3440/BHM | 03/08/2023 | 485 | ARABINDA GUPTA | 298.61 | 0 | 0 | 52
385 | BIRBHUM | Bolpur Mechanical | Abhirampur and Adjoining Mouzas PWSS , SM/12536 | New | Providing Electro-mechanical accessories and others for Abhirampur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2098/Bol.MD | 22/08/2023 | 60 | MONI ELECTRICAL WORKS | 27.98 | 0 | 0 | 50
386 | BIRBHUM | Birbhum Division | Abhirampur and Adjoining Mouzas PWSS , SM/12536 | New | Material Requisition To Resource Division | 1371/BHM | 24/04/2023 | 0 | Resource Division | 50.48 | 0 | 0 | 0
387 | BIRBHUM | Birbhum Division | Abhirampur and Adjoining Mouzas PWSS , SM/12536 | New | Different works related to water supply scheme at ABHIRAMPUR, BEHIRA, SAMSA & UTTAR BANGAON and its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | 1437/BHM | 25/04/2023 | 820 | ASHOK KUMAR GHOSH | 1446.74 | 0 | 0 | 55
388 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMDAHARA AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11902 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 330.16 | 47.17 | 92
389 | BIRBHUM | Birbhum Division | Melanpur Piped Water Supply Scheme. , SM/12699 | New | Material Requisition To Resource Division | 1411/BHM | 24/04/2023 | 0 | Resource Division | 19.04 | 0 | 0 | 0
390 | BIRBHUM | Bolpur Mechanical | Melanpur Piped Water Supply Scheme. , SM/12699 | New | Providing Electro-mechanical accessories and others for Melanpur PWSS at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2107/BOL.MD. | 22/08/2023 | 680 | M/S. DILIP MITRA | 28.74 | 0 | 0 | 50
391 | BIRBHUM | Bolpur Mechanical | Melanpur Piped Water Supply Scheme. , SM/12699 | New | New service connection at Melanpur PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte | BP-2023-24-315 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.76 | 0 | 0 | 0
392 | BIRBHUM | Birbhum Division | Melanpur Piped Water Supply Scheme. , SM/12699 | New | Different works related to water supply scheme at MELANPUR & its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1340/BHM | 20/04/2023 | 987 | BRAHMA CONSTRUCTION COMPANY | 412.68 | 0 | 0 | 37
393 | BIRBHUM | Bolpur Mechanical | PAKURIA PIPED WATER SUPPLY SCHEME. , SM/12596 | New | Providing Electro-mechanical accessories and others for Pakuria & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2094/Bol.MD | 22/08/2023 | 60 | CHAKRABORTY MINING & ENGINERING | 28.81 | 0 | 0 | 50
394 | BIRBHUM | Birbhum Division | PAKURIA PIPED WATER SUPPLY SCHEME. , SM/12596 | New | Material Requisition To Resource Division | 1413/BHM | 24/04/2023 | 0 | Resource Division | 17.28 | 0 | 0 | 0
395 | BIRBHUM | Birbhum Division | PAKURIA PIPED WATER SUPPLY SCHEME. , SM/12596 | New | Different works related to water supply scheme at NETURI, PAIKPARA & PAKURIA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 3441/BHM | 03/08/2023 | 940 | SHREE J.M. CONSTRUCTION | 1236.08 | 0 | 0 | 54
396 | BIRBHUM | Birbhum Division | PAKURIA PIPED WATER SUPPLY SCHEME. , SM/12596 | New | Road crossing, repairing & restoration of damaged pipe lines & PCC roads, sluice valve chambers including all allied works for Pakuria Piped Water Supply Scheme under Birbhum Division, P.H.E Dte. | 1511/BHM | 23/05/2025 | 90 | SHREE J.M. CONSTRUCTION | 18.25 | 0 | 0 | 0
397 | BIRBHUM | Birbhum Division | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. , SM/12591 | New | Material Requisition To Resource Division | 1472/BHM | 25/04/2023 | 0 | Resource Division | 53.39 | 0 | 0 | 0
398 | BIRBHUM | Bolpur Mechanical | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. , SM/12591 | New | Providing Electro-mechanical accessories and others for Bonha PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | 3301/BOL.MD | 29/09/2023 | 580 | QUAZI NOZRUL ISLAM | 28.83 | 0 | 0 | 60
399 | BIRBHUM | Bolpur Mechanical | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. , SM/12591 | New | WBSEDCL QUOTATION FOR BONHA P H NO.I WS SCHEME | BP-23-24-228 | 15/01/2024 | 0 | WBSEDCL | 3.6 | 0 | 0 | 0
400 | BIRBHUM | Bolpur Mechanical | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. , SM/12591 | New | Quotation deposit for Bonha Water Supply Scheme P/H-II in Paikar CCC under Bolpur Mechanical division, PHE Dte | BP-24-25-178 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.01 | 0 | 0 | 0
401 | BIRBHUM | Birbhum Division | BONHA PIPED WATER SUPPLY SCHEME at Murarai-II Block,District Birbhum Division. , SM/12591 | New | Different Works related to water supply scheme at Bonha & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 1216/BHM | 12/04/2023 | 749 | TAPAN KUMAR DATTA | 293.99 | 0 | 0 | 20
402 | BIRBHUM | Birbhum Division | Mahurapur and Adjoining Mouzas PWSS , SM/12697 | New | Material Requisition To Resource Division | 1435/BHM | 25/04/2023 | 0 | Resource Division | 48.04 | 0 | 0 | 0
403 | BIRBHUM | Birbhum Division | Mahurapur and Adjoining Mouzas PWSS , SM/12697 | New | Acceptance Cum Work Order for Supply and delivery of Sluice Valve for Mahurapur and Adjoining Mouzas PWSS under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte | 948/BHM | 14/03/2024 | 30 | MAKALI ENGINEERING CORPORATION | 9.71 | 0 | 0 | 0
404 | BIRBHUM | Birbhum Division | Mahurapur and Adjoining Mouzas PWSS , SM/12697 | New | Estimate for restoration charges for laying PHE pipeline from 3.5 KM to 6.5 KM of rajgram Maharapur road under rampurhat highway sub division of Birbhum highway Division-Iin the dist of Birbhum during the year 2023-24 | BP-2024-25-223 | 12/09/2024 | 0 | EXECUTIVE ENGINEER BIRBHUM HIGHWAY DIVISION-I P.W (ROADS) DIRECTORATE | 22 | 0 | 0 | 0
405 | BIRBHUM | Bolpur Mechanical | Mahurapur and Adjoining Mouzas PWSS , SM/12697 | New | Providing Electro-mechanical accessories and others for MAHURAPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 3297/Bol.MD | 29/09/2023 | 575 | MITRA ENTERPRISE | 30.63 | 0 | 0 | 0
406 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR SIMJURI AND OTHER 19 NOS. MOUZAS UNDER KHOYRASOLE BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/12072 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 314.47 | 47.79 | 92
407 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Harisara Phase-II Water Supply Scheme , SM/12658 | Retrofitting | Extension of pipeline including restoration of roads along with balance FHTC of HARISARA W/S Scheme under Nalhati Sub-Division within Birbhum Division,PHE Dte. | 1314/BHM | 20/04/2023 | 60 | MD SURAJ ALI | 42.72 | 0 | 0 | 100
408 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme , SM/12663 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raipur Zone-II Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.13) | 24/BHM | 06/01/2022 | 60 | SK ALIM | 75.03 | 4.34 | 100 | 97
409 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme , SM/12663 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raipur Zone-I Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.12) | 279/BHM | 09/02/2022 | 60 | PRADIP KUMAR SHARMA | 76.52 | 47.04 | 100 | 50
410 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme , SM/12663 | Retrofitting | Providing Left out FHTC for declaration of Swajal Gram Village at Raypur & Rupganj Mouzas under Raypur Zone I Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. (Sl. No. - 01) | 451/RSD | 11/09/2024 | 15 | GOURANGA MONDAL | 0.75 | 0 | 0 | 0
411 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme , SM/12663 | Retrofitting | Providing Left out FHTC for declaration of Swajal Gram Village at Gamira & Sehala Mouzas under Raypur Zone I Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. (Sl. No. - 02) | 452/RSD | 11/09/2024 | 15 | GOURANGA MONDAL | 0.68 | 0 | 0 | 0
412 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Raypur Phase-II Water Supply Scheme , SM/12663 | Retrofitting | Providing Left out FHTC and allied work for declaration of Swajal Gram Village at Tajpur Mouzas under Raypur Zone I Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. (Sl. No. -03) | 453/RSD | 11/09/2024 | 385 | SOUMEN DAS | 0.97 | 0 | 0 | 100
413 | BIRBHUM | Bolpur Mechanical | Gokrui Piped Water Supply Scheme. , SM/13631 | New | Providing Electro-mechanical accessories and others for Gokrui & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | 3382/Bol.MD | 16/10/2023 | 90 | SATYAJIT GHOSH | 51.95 | 0 | 0 | 0
414 | BIRBHUM | Birbhum Division | Gokrui Piped Water Supply Scheme. , SM/13631 | New | Material Requisition To Resource Division | 1392/BHM | 24/04/2023 | 0 | Resource Division | 54.79 | 0 | 0 | 0
415 | BIRBHUM | Birbhum Division | Gokrui Piped Water Supply Scheme. , SM/13631 | New | Material Requisition To Resource Division | 2453/BHM | 30/08/2024 | 0 | Resource Division | 5.09 | 0 | 0 | 0
416 | BIRBHUM | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150 MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR DERPUR W/S SCHEME (TW-I), SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | 1426/CDD | 29/11/2022 | 30 | C.M. ENTERPRISE | 10.49 | 8.6 | 81.95 | 0
417 | BIRBHUM | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR DERPUR W/S SCH (TW-II), SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | 1427/CDD | 29/11/2022 | 30 | C.M. ENTERPRISE | 10.49 | 0 | 0 | 0
418 | BIRBHUM | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR DERPUR W/S SCHEME, UNDER CDD, PHE DTE. | 1429/CDD | 29/11/2022 | 30 | C.M. ENTERPRISE | 10.49 | 0 | 0 | 100
419 | BIRBHUM | Birbhum Division | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | Material Requisition To Resource Division | 1480/BHM | 25/04/2023 | 0 | Resource Division | 24.21 | 0 | 0 | 0
420 | BIRBHUM | Bolpur Mechanical | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | WBSEDCL QUOTATION FOR DERPUR WS SCHEME | BP-2023-2024-56 | 02/08/2023 | 0 | WBSEDCL | 3.31 | 0 | 0 | 0
421 | BIRBHUM | Bolpur Mechanical | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | QUOTATION BILL FOR DERPUR WS SCHEME | BP-23-24-149 | 28/11/2023 | 0 | WBSEDCL | 5.48 | 0 | 0 | 0
422 | BIRBHUM | Bolpur Mechanical | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | Providing Electro-mechanical accessories and others for Derpur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 313/Bol.MD | 24/03/2023 | 739 | EMCON | 28.71 | 16.33 | 56.88 | 50
423 | BIRBHUM | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | Hiring of Diesel driven motor cab (BS-III & Above) (Non AC) having contract carriage permit along with driver for the office of the DIC/ CMSD-I P.H.E. Dte. Under CMSD-I(D), CDD, P.H.E. Dte. | 290/CMSD-I(D) | 18/12/2023 | 182 | SUJATA BHOWMICK | 0.86 | 0 | 0 | 30
424 | BIRBHUM | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | Supply & Delivery of Consumables with other works at site for construction of tubewell in Derpur (TW-II), Block - Sainthia, Birbhum District under CDD , PHE Dte. | 495/CMSD-I | 28/09/2022 | 15 | C.M. ENTERPRISE | 2.66 | 0 | 0 | 100
425 | BIRBHUM | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | Supply & Delivery of Consumables with other works at site for construction of tubewell in Derpur (TW-IV) , Block - Sainthia, Birbhum District under CDD , PHE Dte. | 493/CMSD-I | 28/09/2022 | 15 | C.M. ENTERPRISE | 2.66 | 0 | 0 | 100
426 | BIRBHUM | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | Providing Tube well materials , conforming to IS : 12818 2010 with other works at site for construction of Tube Well in Derpur (TW-I), Block -Sainthia, Birbhum District under CDD, PHE Dte. | 486/CMSD-I | 23/09/2022 | 15 | C.M. ENTERPRISE | 4.18 | 0 | 0 | 100
427 | BIRBHUM | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | Providing drilling crews for construction of Tube Well by departmental Rig machine in Derpur (TW-II), Block Sainthia , Birbhum District under CDD, P.H.E. Dte. | 487/CMSD-I | 23/09/2022 | 15 | C.M. ENTERPRISE | 3.77 | 0 | 0 | 100
428 | BIRBHUM | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | Providing Tube well materials , conforming to IS : 12818 2010 with other works at site for construction of Tube Well in Derpur (TW-III) , Block-Sainthia, Birbhum District under CDD, PHE Dte. | 488/CMSD-I | 23/09/2022 | 15 | C.M. ENTERPRISE | 4.18 | 0 | 0 | 100
429 | BIRBHUM | Central Drilling | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | Providing drilling crews for construction of Tube Well by departmental Rig machine in Derpur (TW-IV), Block - Sainthia, Birbhum District under CDD, P.H.E. Dte. | 494/CMSD-I | 28/09/2022 | 15 | C.M. ENTERPRISE | 3.77 | 0 | 0 | 100
430 | BIRBHUM | Birbhum Division | DERPUR PIPED WATER SUPPLY SCHEME. , SM/12832 | New | Different works related to water supply scheme at DERPUR, KURUMSAHA & MATIARA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 1245/BHM | 17/04/2023 | 1074 | BRAHMA CONSTRUCTION COMPANY | 978.83 | 57.34 | 13.72 | 65
431 | BIRBHUM | Birbhum Division | Bidhyadharpur Piped Water Supply Scheme. , SM/13708 | New | Material Requisition To Resource Division | 1357/BHM | 24/04/2023 | 0 | Resource Division | 13.87 | 0 | 0 | 0
432 | BIRBHUM | Central Drilling | Bidhyadharpur Piped Water Supply Scheme. , SM/13708 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
433 | BIRBHUM | Birbhum Division | Bidhyadharpur Piped Water Supply Scheme. , SM/13708 | New | Different works related to water supply scheme at ALBANDHA, BERGRAM & BIDYADHARPUR Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (2nd Call) | 4146/BHM | 19/10/2023 | 805 | AMAL DUTTA ROY | 1648.21 | 0 | 0 | 12
434 | BIRBHUM | Birbhum Division | BANSANKHA PIPED WATER SUPPLY SCHEME. , SM/12889 | New | Material Requisition To Resource Division | 1385/BHM | 24/04/2023 | 0 | Resource Division | 6.68 | 0 | 0 | 0
435 | BIRBHUM | Bolpur Mechanical | BANSANKHA PIPED WATER SUPPLY SCHEME. , SM/12889 | New | New service connection at Bansankha PH-I W/S scheme Block-Suri II under Bolpur Mechanical Division,PHE Dte. | BP-2024-2025-57 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7 | 0 | 0 | 0
436 | BIRBHUM | Bolpur Mechanical | BANSANKHA PIPED WATER SUPPLY SCHEME. , SM/12889 | New | New service connection at Bansankha PH-II W/S scheme Block-Suri II under Bolpur Mechanical Division,PHE Dte. | BP-2024-2025-58 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.74 | 0 | 0 | 0
437 | BIRBHUM | Birbhum Division | BANSANKHA PIPED WATER SUPPLY SCHEME. , SM/12889 | New | Different works related to water supply scheme at BANSHANKA & HATIKARA its adjoining mouzas water supply scheme within SURI - II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1181/BHM | 12/04/2023 | 1041 | MAHAVIR PUMPS MFG PVT LTD | 773.9 | 0 | 0 | 5
438 | BIRBHUM | Bolpur Mechanical | BANSANKHA PIPED WATER SUPPLY SCHEME. , SM/12889 | New | Providing Electro-mechanical accessories and others for Banshanka & Adjoining moujas water supply scheme at Suri -II Block under Bolpur Mechanical Division PHE Dte. | 3361/Bol.MD | 10/10/2023 | 60 | M/S. S.S. ENTERPRISE | 27.27 | 0 | 0 | 45
439 | BIRBHUM | Birbhum Division | BHEPUR PIPED WATER SUPPLY SCHEME , SM/13759 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHEPUR Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 144/BSD | 12/04/2022 | 90 | RADIANT | 4.36 | 0 | 0 | 100
440 | BIRBHUM | Birbhum Division | BHEPUR PIPED WATER SUPPLY SCHEME , SM/13759 | New | Material Requisition To Resource Division | 2178/BHM | 23/06/2023 | 0 | Resource Division | 8.91 | 0 | 0 | 0
441 | BIRBHUM | Birbhum Division | BHEPUR PIPED WATER SUPPLY SCHEME , SM/13759 | New | Material Requisition To Resource Division | 2450/BHM | 30/08/2024 | 0 | Resource Division | 9.25 | 0 | 0 | 0
442 | BIRBHUM | Central Drilling | BHEPUR PIPED WATER SUPPLY SCHEME , SM/13759 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
443 | BIRBHUM | Birbhum Division | BHEPUR PIPED WATER SUPPLY SCHEME , SM/13759 | New | Construction of 200 CuM.capacity OHR with Soil Investigation,5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements,laying Rising Main,Distribution System with FHTC and different works related to BHEPUR PIPED WATER SUPPLY SCHEME (TSM/015433) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | 2109/BHM | 29/07/2024 | 730 | MAMATA USHA ENTERPRISE | 382.93 | 0 | 0 | 35
444 | BIRBHUM | Bolpur Mechanical | BHEPUR PIPED WATER SUPPLY SCHEME , SM/13759 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Bhepur WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | 4528/BOL.MD | 20/12/2024 | 120 | SATYAJIT GHOSH | 75.08 | 0 | 0 | 60
445 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMRITAPUR AND MAJHARA MOUZAS UNDER MURARAI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11908 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 0 | 92
446 | BIRBHUM | Birbhum Division | CHUNPALASHI PIPED WATER SUPPLY SCHEME , SM/13637 | New | Material Requisition To Resource Division | 1533/BHM | 26/04/2023 | 0 | Resource Division | 47.92 | 0 | 0 | 0
447 | BIRBHUM | Birbhum Division | CHUNPALASHI PIPED WATER SUPPLY SCHEME , SM/13637 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for CHUNPALASHI Piped Water Supply Scheme within command area of Illambazar Development Block under Bolpur Sub-Division within Birbhum Division, PHE Dte.". | 121/BSD | 31/03/2022 | 90 | M/S R DUTTA & CO. | 4.29 | 0 | 0 | 100
448 | BIRBHUM | Central Drilling | CHUNPALASHI PIPED WATER SUPPLY SCHEME , SM/13637 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
449 | BIRBHUM | Birbhum Division | CHUNPALASHI PIPED WATER SUPPLY SCHEME , SM/13637 | New | Different works related to water supply scheme at MATIKONA, NOHONA, SHIRSHA & CHUNPALASHI Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 3598/BHM | 21/08/2023 | 949 | BIPIN KUMAR SINGH | 2395.67 | 0 | 0 | 4
450 | BIRBHUM | Birbhum Division | NOHNA PIPED WATER SUPPLY SCHEME , SM/13645 | New | Material Requisition To Resource Division | 2174/BHM | 23/06/2023 | 0 | Resource Division | 136.35 | 0 | 0 | 0
451 | BIRBHUM | Bolpur Mechanical | NOHNA PIPED WATER SUPPLY SCHEME , SM/13645 | New | New service connection for Nohona PWSS (Block- Illambazar) | BP-2024-2025-55 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.61 | 0 | 0 | 0
452 | BIRBHUM | Central Drilling | NOHNA PIPED WATER SUPPLY SCHEME , SM/13645 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
453 | BIRBHUM | Birbhum Division | NOHNA PIPED WATER SUPPLY SCHEME , SM/13645 | New | Different works related to water supply scheme at MATIKONA, NOHONA, SHIRSHA & CHUNPALASHI Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 3598/BHM | 21/08/2023 | 949 | BIPIN KUMAR SINGH | 2395.67 | 0 | 0 | 4
454 | BIRBHUM | Bolpur Mechanical | NOHNA PIPED WATER SUPPLY SCHEME , SM/13645 | New | Providing Electro-mechanical accessories and others for Nohana & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2172/Bol.MD | 01/09/2023 | 519 | M/S. UTTAM KUMAR CHATTERJEE | 14.97 | 0 | 0 | 80
455 | BIRBHUM | Bolpur Mechanical | Sekupur piped water supply scheme. , SM/13650 | New | Providing Electro-mechanical accessories and others for Sekupur PWSS at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | 2108/BOL.MD. | 22/08/2023 | 60 | QUAZI NOZRUL ISLAM | 28 | 0 | 0 | 0
456 | BIRBHUM | Birbhum Division | Sekupur piped water supply scheme. , SM/13650 | New | Material Requisition To Resource Division | 1403/BHM | 24/04/2023 | 0 | Resource Division | 9.14 | 0 | 0 | 0
457 | BIRBHUM | Birbhum Division | Sekupur piped water supply scheme. , SM/13650 | New | Material Requisition To Resource Division | 2449/BHM | 30/08/2024 | 0 | Resource Division | 4.69 | 0 | 0 | 0
458 | BIRBHUM | Birbhum Division | Sekupur piped water supply scheme. , SM/13650 | New | Sinking of 150 mm. X 100 mm Dia deep tubewell , construction of 100 CuM capacity O.H.R.with soil Investigation, Pump room/ Chlorine room with/without sanitary arrangements( different size),and laying of Rising main, Laying distribution with FHTC and different works related to SEKUPUR & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | 2111/BHM | 29/07/2024 | 365 | MAMATA USHA ENTERPRISE | 243.97 | 0 | 0 | 20
459 | BIRBHUM | Birbhum Division | Kukutia piped water supply scheme. , SM/13601 | New | Material Requisition To Resource Division | 1394/BHM | 24/04/2023 | 0 | Resource Division | 67.88 | 0 | 0 | 0
460 | BIRBHUM | Bolpur Mechanical | Kukutia piped water supply scheme. , SM/13601 | New | Providing Electro-mechanical accessories and others for Kukutia & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | 3393/Bol.MD | 17/10/2023 | 90 | S.K.ELECTRICALS | 52.82 | 0 | 0 | 60
461 | BIRBHUM | Birbhum Division | Kukutia piped water supply scheme. , SM/13601 | New | Material Requisition To Resource Division | 2487/BHM | 03/09/2024 | 0 | Resource Division | 8.26 | 0 | 0 | 0
462 | BIRBHUM | Birbhum Division | PANCHPARA PIPED WATER SUPPLY SCHEME , SM/13951 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for PANCHPARA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | 179/BSD | 05/05/2022 | 180 | APEX ENGINEERING | 3.87 | 0 | 0 | 100
463 | BIRBHUM | Birbhum Division | PANCHPARA PIPED WATER SUPPLY SCHEME , SM/13951 | New | Material Requisition To Resource Division | 2395/BHM | 27/08/2024 | 0 | Resource Division | 11.4 | 0 | 0 | 0
464 | BIRBHUM | Central Drilling | PANCHPARA PIPED WATER SUPPLY SCHEME , SM/13951 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
465 | BIRBHUM | Birbhum Division | PANCHPARA PIPED WATER SUPPLY SCHEME , SM/13951 | New | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1948/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0 | 0
466 | BIRBHUM | Bolpur Mechanical | PANCHPARA PIPED WATER SUPPLY SCHEME , SM/13951 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Panchpara PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | 333/BOL.MD | 19/02/2025 | 240 | PADMA ENGINEERING CO. | 75.59 | 0 | 0 | 50
467 | BIRBHUM | Birbhum Division | PURBA BANKATI PIPED WATER SUPPLY SCHEME. , SM/13470 | New | Material Requisition To Resource Division | 1383/BHM | 24/04/2023 | 0 | Resource Division | 8.65 | 0 | 0 | 0
468 | BIRBHUM | Birbhum Division | PURBA BANKATI PIPED WATER SUPPLY SCHEME. , SM/13470 | New | Different Works for PURBA BANKATI & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. Sl No 03 | 675/BHM | 01/03/2023 | 670 | MUKHERJEE ENTERPRISE | 152.12 | 48.17 | 31.67 | 68
469 | BIRBHUM | Bolpur Mechanical | PURBA BANKATI PIPED WATER SUPPLY SCHEME. , SM/13470 | New | WBSEDCL QUOTATION FOR PURBA BANKATI WS SCHEME | BP-23-24-248 | 29/01/2024 | 0 | WBSEDCL | 10.18 | 0 | 0 | 0
470 | BIRBHUM | Bolpur Mechanical | PURBA BANKATI PIPED WATER SUPPLY SCHEME. , SM/13470 | New | Providing Electro-mechanical accessories and others for Purba Bankati & Adjoining moujas water supply scheme at Suri - I Block under Bolpur Mechanical Division PHE Dte. | 3314/BOL.MD | 29/09/2023 | 579 | BENGAL CONSTRUCTION | 19.05 | 0 | 0 | 45
471 | BIRBHUM | Bolpur Mechanical | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/13480 | New | Providing Electro-mechanical accessories and others for Dabuk PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | 2154/Bol.MD | 28/08/2023 | 60 | M/S SAJAHAN CHOWDHURY | 44.02 | 0 | 0 | 30
472 | BIRBHUM | Birbhum Division | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/13480 | New | Continuation Work Order for Preparation & Submission of DPR for (Dabuk) Water Supply Scheme under Mayureswar-I Development Block. | 205/RSD | 13/06/2022 | 90 | ENVIROTECH SOLUTIONS | 3.58 | 0 | 0 | 100
473 | BIRBHUM | Birbhum Division | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/13480 | New | Material Requisition To Resource Division | 1508/BHM | 26/04/2023 | 0 | Resource Division | 21.69 | 0 | 0 | 0
474 | BIRBHUM | Bolpur Mechanical | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/13480 | New | Supply & delivery of UPVC Column pipes at store for Dabuk piped water supply scheme under Bolpur Mechanical Division, PHE. Dte. | 1479./AE-III | 11/09/2024 | 7 | MAA TARA ENTERPRISE | 1.53 | 0 | 0 | 100
475 | BIRBHUM | Birbhum Division | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/13480 | New | Material Requisition To Resource Division | 199/BHM | 22/01/2024 | 0 | Resource Division | 4.13 | 0 | 0 | 0
476 | BIRBHUM | Bolpur Mechanical | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/13480 | New | WBSEDCL QUOTATION FOR DABUK P H NO 1 WS SCHEME UNDER BOL MD PHE DTE | BP-23-24-177 | 07/12/2023 | 0 | WBSEDCL | 3.77 | 0 | 0 | 0
477 | BIRBHUM | Bolpur Mechanical | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/13480 | New | New service connection at Dabuk PH-II PWSS, Mayureswar -I Block, Under Bolpur Mechanical Division , P.H.E Dte. | BP-2024-2025-52 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.01 | 0 | 0 | 0
478 | BIRBHUM | Birbhum Division | Dabuk Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/13480 | New | Different works related to water supply scheme at DABUK & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1083/BHM | 06/04/2023 | 1000 | ZEBA CONSTRUCTION | 270.01 | 0 | 0 | 60
479 | BIRBHUM | Birbhum Division | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13983 | New | Continuation Work Order for Preparation & Submission of DPR for (Bajitpur) Water Supply Scheme under Mayureswar-I Development Block. | 185/RSD | 06/05/2022 | 90 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 0 | 100
480 | BIRBHUM | Birbhum Division | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13983 | New | Material Requisition To Resource Division | 1532/BHM | 26/04/2023 | 0 | Resource Division | 6.01 | 0 | 0 | 0
481 | BIRBHUM | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13983 | New | WBSEDCL QUOTATION BILL FOR BAJITPUR WS SCHEME | BP-23-24-94 | 26/09/2023 | 0 | WBSEDCL | 2.93 | 0 | 0 | 0
482 | BIRBHUM | Birbhum Division | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13983 | New | Different works related to water supply scheme at BAJITPUR & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (SL NO 05) | 618/BHM | 27/02/2023 | 733 | S.D CONSTRUCTION | 278.84 | 0 | 0 | 60
483 | BIRBHUM | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13983 | New | Operation and Guarding of pumping machinery and others at Bajitpur warer Supply scheme,Pump House No-I under Bolpur Mechanical Division,P.H.E Dte. | 1079./AE-III | 29/07/2024 | 31 | MAHADEV ENTERPRISE | 0.3 | 0 | 0 | 0
484 | BIRBHUM | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13983 | New | Supply & delivery of Chlorinat0r at Bajitpur Piped Water Supply Scheme under Bolpur Mechanical Division ,P.H.E. Dte. | 1192./AE-III | 12/08/2024 | 10 | R.K.ENTERPRISE | 0.9 | 0 | 0 | 100
485 | BIRBHUM | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13983 | New | Supply & delivery of UPVC Column pipes at store for Bajitpur water supply scheme under Bolpur Mechanical Division, PHE. Dte. | 1298./AE-III | 27/08/2024 | 7 | MS SM ELECTRICAL | 1.9 | 0 | 0 | 100
486 | BIRBHUM | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13983 | New | Supply and Delivery of Pumping Machinery for Bajitpur Water Supply Scheme Block Mayureswar ¿I under Bolpur Mechanical Division PHE. Dte. | 615/AE-III | 27/03/2024 | 7 | MAHADEV ENTERPRISE | 1.49 | 0 | 0 | 100
487 | BIRBHUM | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13983 | New | Supply & delivery of openwell submersible pumping machinery for Bajitpur Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | 1457./AE-III | 09/09/2024 | 7 | M/S. UTTAM KUMAR CHATTERJEE | 2.87 | 0 | 0 | 100
488 | BIRBHUM | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13983 | New | Supply & delivery of Submersible Cable acceessories for Bajitpur Piped water supply scheme. under Bolpur Mechanical Division, PHE. Dte. | 1202./AE-III | 16/08/2024 | 10 | J.K.ENGINEERING CO | 0.92 | 0 | 0 | 100
489 | BIRBHUM | Birbhum Division | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13983 | New | Material Requisition To Resource Division | 197/BHM | 22/01/2024 | 0 | Resource Division | 2.18 | 0 | 0 | 0
490 | BIRBHUM | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13983 | New | WBSEDCL QUOTATION FOR RBAJITPUR ws scheme | BP-23-24-264 | 07/02/2024 | 0 | WBSEDCL | 1.7 | 0 | 0 | 0
491 | BIRBHUM | Bolpur Mechanical | Bajitpur Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13983 | New | Providing Electro-mechanical accessories and others for Bajitpur PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | 1747/Bol.MD | 27/07/2023 | 609 | MAHADEV ENTERPRISE | 43.79 | 0 | 0 | 97
492 | BIRBHUM | Bolpur Mechanical | SHRICHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/13516 | New | NEW SERVICE CONNECTION AT SHRICHNDRAPUR PWSS PH-I | BP-24-25-190 | 24/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.57 | 0 | 0 | 0
493 | BIRBHUM | Bolpur Mechanical | SHRICHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/13516 | New | Additional quotation for extra involvement of materials against application no - 5004294122 at Shrichandrapur PWSS, P/H- I under Illambazar CCC | BP-24-25-273 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.54 | 0 | 0 | 0
494 | BIRBHUM | Bolpur Mechanical | SHRICHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/13516 | New | NEW SERVICE CONNECTION FOR AT SHRICHANDRAPUR PWSS PH-II | BP-24-25-267 | 25/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.22 | 0 | 0 | 0
495 | BIRBHUM | Birbhum Division | SHRICHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/13516 | New | Different works related to water supply scheme at SHRICHANDRAPUR Piped Water Supply Scheme within Illambazar Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1345/BHM | 20/04/2023 | 833 | RADHARANI ENTERPRISE | 165.15 | 0 | 0 | 5
496 | BIRBHUM | Central Drilling | SHRICHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/13516 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
497 | BIRBHUM | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14675 | New | Material Requisition To Resource Division | 1518/BHM | 26/04/2023 | 0 | Resource Division | 36.07 | 0 | 0 | 0
498 | BIRBHUM | Bolpur Mechanical | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14675 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Duna PWSS under Mayureswar - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 521/BOL.MD | 14/03/2024 | 60 | PRADIP KUMAR DHABAL | 7.62 | 0 | 0 | 0
499 | BIRBHUM | Bolpur Mechanical | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14675 | New | Supply, Delivewry and storage of vacuum operated gaseous Chlorination system for Duna PWSS, Block : Mayureswar-II under Bolpur Mechanical Division.PHE.DTE. | 3761/Bol.MD | 12/09/2024 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 28.84 | 0 | 0 | 0
500 | BIRBHUM | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14675 | New | Continuation Work Order for Preparation & Submission of DPR for (DUNA) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | 423/RSD | 03/11/2022 | 45 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 0 | 100
501 | BIRBHUM | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14675 | New | Continuation Work Order for Preparation & Submission of DPR for (DUNA) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | 296/RSD | 07/09/2022 | 45 | ENVIROTECH SOLUTIONS | 3.22 | 0 | 0 | 100
502 | BIRBHUM | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14675 | New | Material Requisition To Resource Division | 208/BHM | 22/01/2024 | 0 | Resource Division | 1.54 | 0 | 0 | 0
503 | BIRBHUM | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14675 | New | Different works related to Water Supply Scheme at DUNA & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1249/BHM | 17/04/2023 | 806 | CREATIVE CONSTRUCTION | 473.21 | 0 | 0 | 50
504 | BIRBHUM | Bolpur Mechanical | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14675 | New | Providing Electro-mechanical accessories and others for Duna PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | 3281/BOL.MD | 29/09/2023 | 702 | DEY ENTERPRISE | 55.7 | 0 | 0 | 61
505 | BIRBHUM | Birbhum Division | DUNA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14675 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
506 | BIRBHUM | Birbhum Division | RANIBAZAR PIPED WATER SUPPLY SCHEME , SM/14850 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for RANIBAZAR Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 187/BSD | 11/05/2022 | 90 | RADIANT | 4 | 0 | 0 | 100
507 | BIRBHUM | Birbhum Division | RANIBAZAR PIPED WATER SUPPLY SCHEME , SM/14850 | New | Material Requisition To Resource Division | 1514/BHM | 26/04/2023 | 0 | Resource Division | 14.12 | 0 | 0 | 0
508 | BIRBHUM | Birbhum Division | RANIBAZAR PIPED WATER SUPPLY SCHEME , SM/14850 | New | Construction of 200 CuM capacity O.H.R.with Soil Investigation,5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements,laying of Rising Main,Distribution System with FHTC and different works related to RANIBAZAR PIPED WATER SUPPLY SCHEME (TSM/017432) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte. | 2664/BHM | 13/09/2024 | 365 | PATHIK PABAN NANDI | 417.11 | 0 | 0 | 0
509 | BIRBHUM | Central Drilling | RANIBAZAR PIPED WATER SUPPLY SCHEME , SM/14850 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
510 | BIRBHUM | Bolpur Mechanical | RANIBAZAR PIPED WATER SUPPLY SCHEME , SM/14850 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Ranibazar WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | 4527/BOL.MD | 20/12/2024 | 120 | SATYAJIT GHOSH | 75.08 | 0 | 0 | 50
511 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Tarapith Phase-II Water Supply Scheme. , SM/13375 | Retrofitting | Balance work for Laying & distribution system with HDPE pipes and Specials including FHTC (Functional Household Tap Connection ) at Chandipur mouza for Improvement of Tarapith piped W/S Scheme under Birbhum Division, PHE Dte. (Sl. No.15) | 286/BHM | 01/02/2023 | 45 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 99.59 | 0 | 0 | 0
512 | BIRBHUM | Birbhum Division | TATINAPARA PIPED WATER SUPPLY SCHEME , SM/13979 | New | Different works related to water supply scheme at TATINAPARA PIPED WATER SUPPLY SCHEME (TSM/015894) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte.(2nd Call) | 4150/BHM | 21/10/2023 | 274 | TEKNO ENTERPRISE | 606.61 | 0 | 0 | 0
513 | BIRBHUM | Birbhum Division | TATINAPARA PIPED WATER SUPPLY SCHEME , SM/13979 | New | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for TATINAPARA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.¿. | 268/BSD | 15/07/2022 | 90 | APEX ENGINEERING | 4.92 | 0 | 0 | 100
514 | BIRBHUM | Central Drilling | TATINAPARA PIPED WATER SUPPLY SCHEME , SM/13979 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
515 | BIRBHUM | Birbhum Division | Khamedda Piped Water Supply Scheme , SM/13980 | New | Continuation Work Order for Preparation & Submission of DPR for (Khamedda) Water Supply Scheme under Rampurhat-II Development Block. | 262/RSD | 27/07/2022 | 45 | ECO CARE | 4.73 | 0 | 0 | 100
516 | BIRBHUM | Birbhum Division | Khamedda Piped Water Supply Scheme , SM/13980 | New | Material Requisition To Resource Division | 1583/BHM | 26/04/2023 | 0 | Resource Division | 26.44 | 0 | 0 | 0
517 | BIRBHUM | Birbhum Division | Khamedda Piped Water Supply Scheme , SM/13980 | New | Different works related to water supply scheme at Madhupur, Khamedda & Bara-Karttikchungri and its adjoining mouzas water supply scheme within Rampurhat-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte.(2nd Call) | 4163/BHM | 30/10/2023 | 560 | M/S ASHA CONSTRUCTION | 1089.94 | 0 | 0 | 40
518 | BIRBHUM | Birbhum Division | Khamedda Piped Water Supply Scheme , SM/13980 | New | Material Requisition To Resource Division | 225/BHM | 24/01/2024 | 0 | Resource Division | 3.08 | 0 | 0 | 0
519 | BIRBHUM | Bolpur Mechanical | Khamedda Piped Water Supply Scheme , SM/13980 | New | Quotation for new service connection at Khamedda P/H-II PWSS (Mouza- Khamedda) at Block-Rampurhat-II | BP-24-25-283 | 17/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.58 | 0 | 0 | 0
520 | BIRBHUM | Bolpur Mechanical | Khamedda Piped Water Supply Scheme , SM/13980 | New | Quotation for new service connection at Khamedda PWSS P.H No-I (Block-Rampurhat - II), Margram CCC, WBSEDCL | BP-2024-2025-61 | 05/06/2024 | 0 | WBSEDCL | 2.75 | 0 | 0 | 0
521 | BIRBHUM | Bolpur Mechanical | Khamedda Piped Water Supply Scheme , SM/13980 | New | Providing Electro-mechanical accessories and others for Khameda PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 2224/Bol.MD | 12/09/2023 | 567 | HINDOL ROY | 45.7 | 0 | 0 | 50
522 | BIRBHUM | Birbhum Division | Augmentation of Mathpalsa Piped Water Supply Scheme , SM/10315 | Augmentation | Trial Bore and Sinking of 200 mm dia. tubewell (2 nos.) 30 m. Deep fitted with M.S.E.R.W. Housing pipe and Fibre Glass Strainer on the river bank of Mayurakshi for the Augmentation of Mathpalsa Piped Water Supply Scheme under Birbhum Sadar Sub-Division PHE Dte. with Birbhum Division, P.H.E. Dte. | 1984/BHM | 05/06/2023 | 30 | INDRAJIT DUTTA. | 3.38 | 0 | 0 | 0
523 | BIRBHUM | Birbhum Division | Augmentation of Mathpalsa Piped Water Supply Scheme , SM/10315 | Augmentation | Laying distribution system including FHTC for proposed Augmentation scheme for Mathpalsa Piped Water Supply Scheme , Sainthia Block under Birbhum Dvisision PHE DTE (Sl.No.2) | 1160/BHM | 23/05/2022 | 180 | APURBA MONDAL | 144.13 | 141.16 | 100 | 100
524 | BIRBHUM | Birbhum Division | Augmentation of Mathpalsa Piped Water Supply Scheme , SM/10315 | Augmentation | Material Requisition To Resource Division | 3276/BHM | 27/07/2023 | 0 | Resource Division | 1.14 | 0 | 0 | 0
525 | BIRBHUM | Birbhum Division | Augmentation of Mathpalsa Piped Water Supply Scheme , SM/10315 | Augmentation | Material Requisition To Resource Division | 2244/BHM | 07/07/2023 | 0 | Resource Division | 2.09 | 0 | 0 | 0
526 | BIRBHUM | Bolpur Mechanical | Augmentation of Mathpalsa Piped Water Supply Scheme , SM/10315 | Augmentation | Supply and delivery and installation of MCC panel at NOHANA PWSS (Mathpalsa) in Sainthia block under Bolpur Mechanical Division, P.H.E. Dte | 561/BOL.MD | 15/03/2024 | 180 | BIRBHUM ELECTRIC WORKS | 8.74 | 0 | 0 | 100
527 | BIRBHUM | Bolpur Mechanical | Augmentation of Mathpalsa Piped Water Supply Scheme , SM/10315 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Mathpalsa water supply scheme (P.H. No.-III) under Bolpur Mechanical Division PHE Dte. | 715/Bol.MD | 19/04/2023 | 45 | BIRBHUM ELECTRIC WORKS | 12.72 | 0 | 0 | 60
528 | BIRBHUM | Birbhum Division | Augmentation of Mathpalsa Piped Water Supply Scheme , SM/10315 | Augmentation | Providing FHTC and laying of pipe line for the villages rest portion of Rongaipur & Mathpalsa & all other allied works under Augmentation of Mathpalsa Piped Water Supply Scheme, Sainthia Block under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | 2516/BHM | 04/09/2024 | 363 | JAGADANANDAPUR CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 35.86 | 0 | 0 | 70
529 | BIRBHUM | Birbhum Division | Augmentation of Mathpalsa Piped Water Supply Scheme , SM/10315 | Augmentation | Balance work for laying of pipe line including FHTC for augmentation of Mathpalsa Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. . | 2075/BHM | 08/06/2023 | 602 | JAGADANANDAPUR CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 45.68 | 0 | 0 | 100
530 | BIRBHUM | Bolpur Mechanical | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division , SM/14119 | New | Providing Electro-mechanical accessories and others for Kanksa PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | 2155/Bol.MD | 28/08/2023 | 60 | GOENKA ENTERPRISE | 44.03 | 0 | 0 | 50
531 | BIRBHUM | Birbhum Division | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division , SM/14119 | New | Continuation Work Order for Preparation & Submission of DPR for (Kanska) Water Supply Scheme under Mayureswar-I Development Block. | 230/RSD | 27/06/2022 | 90 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 0 | 100
532 | BIRBHUM | Birbhum Division | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division , SM/14119 | New | Material Requisition To Resource Division | 1447/BHM | 25/04/2023 | 0 | Resource Division | 5.45 | 0 | 0 | 0
533 | BIRBHUM | Bolpur Mechanical | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division , SM/14119 | New | Supplly & delivery of pumping machinery Kanksa water supply scheme Block- Mayureswar-I under Bolpur Mechanical Division, PHE Dte. | 690./AE-III | 08/04/2024 | 14 | GOENKA ENTERPRISE | 1.48 | 0 | 0 | 100
534 | BIRBHUM | Birbhum Division | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division , SM/14119 | New | Material Requisition To Resource Division | 206/BHM | 22/01/2024 | 0 | Resource Division | 3.91 | 0 | 0 | 0
535 | BIRBHUM | Bolpur Mechanical | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division , SM/14119 | New | WBSEDCL QUOTATION FOR PURBA KANKSA P H NO II WS SCHEME | BP-23-24-256 | 06/02/2024 | 0 | WBSEDCL | 5.76 | 0 | 0 | 0
536 | BIRBHUM | Bolpur Mechanical | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division , SM/14119 | New | WBSEDCL QUOTATION FOR KANKSA P H NO -2 WS SCHEME | BP-23-24-178 | 07/12/2023 | 0 | WBSEDCL | 3.82 | 0 | 0 | 0
537 | BIRBHUM | Birbhum Division | Kanksa piped water supply scheme under Mayureswar-I block within Birbhum Division , SM/14119 | New | Different works related to water supply scheme at KANKSA & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1879/BHM | 31/05/2023 | 761 | PRANAB KUMAR GHOSH | 229 | 0 | 0 | 65
538 | BIRBHUM | Birbhum Division | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14141 | New | Material Requisition To Resource Division | 1540/BHM | 26/04/2023 | 0 | Resource Division | 51.95 | 0 | 0 | 0
539 | BIRBHUM | Bolpur Mechanical | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14141 | New | Additional work in connection with Providing and Installation of Submersible pumping Machineries at newly sunk Tube Wells and allieds works at Birchandrapur Piped Water Supply Scheme, Block-Mayureswar-I, under Bolpur Mechanical Division. | 372/BOL.MD | 06/03/2024 | 30 | SARKAR ELECTRICAL | 18.22 | 0 | 0 | 77
540 | BIRBHUM | Birbhum Division | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14141 | New | Continuation Work Order for Preparation & Submission of DPR for (BIRCHANDRAPUR) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | 286/RSD | 29/08/2022 | 90 | ENVIROTECH SOLUTIONS | 3.5 | 0 | 0 | 100
541 | BIRBHUM | Birbhum Division | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14141 | New | Continuation Work Order for Preparation & Submission of DPR for (BIRCHANDRAPUR) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | 360/RSD | 20/09/2022 | 90 | ENVIROTECH SOLUTIONS | 3.43 | 0 | 0 | 100
542 | BIRBHUM | Bolpur Mechanical | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14141 | New | New service connection charges at Birchandrapur PH-III PWSS. | BP-24-25-186 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.65 | 0 | 0 | 0
543 | BIRBHUM | Bolpur Mechanical | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14141 | New | Providing Electro-mechanical accessories and others for Birchandrapur PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | 3477/Bol.MD | 07/11/2023 | 602 | EASTERN INDIA SALES & SERVICE | 67.61 | 0 | 0 | 60
544 | BIRBHUM | Birbhum Division | Birchandrapur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14141 | New | Different works related to water supply scheme at BIRCHANDRAPUR, ASURLAYA, BARATURIGRAM & KANAIPUR and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | 505/BHM | 05/02/2024 | 603 | B RAI CONSTRUCTION COMPANY | 2071.77 | 0 | 0 | 20
545 | BIRBHUM | Bolpur Mechanical | Albandha Piped Water Supply Scheme. , SM/14533 | New | Providing Electro-mechanical accessories and others for Albandha & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | 2238/BOL.MD. | 13/09/2023 | 90 | DEY ENTERPRISE | 73.35 | 0 | 0 | 50
546 | BIRBHUM | Birbhum Division | Albandha Piped Water Supply Scheme. , SM/14533 | New | Material Requisition To Resource Division | 1547/BHM | 26/04/2023 | 0 | Resource Division | 219.35 | 0 | 0 | 0
547 | BIRBHUM | Bolpur Mechanical | Albandha Piped Water Supply Scheme. , SM/14533 | New | Supply and delivery of 80 mm UPVC standard type column pipe (Cream colour) for albandha water supply scheme(T/W-II) under BOL MD, PHE Dte.. | 4195/BOL.MD | 22/10/2024 | 20 | M. S. ENTERPRISE | 2.6 | 0 | 0 | 100
548 | BIRBHUM | Bolpur Mechanical | Albandha Piped Water Supply Scheme. , SM/14533 | New | Supply and delivery of column pipe for albandha water supply scheme(T/W-I) under BOL MD, PHE Dte.. | 3805/BOL.MD | 12/09/2024 | 20 | SATYAJIT GHOSH | 2.52 | 0 | 0 | 100
549 | BIRBHUM | Bolpur Mechanical | Albandha Piped Water Supply Scheme. , SM/14533 | New | Supply and delivery of Submersible pump for albandha Water Supply under Bolpur Mechanical Divn. PHE Dte. | 3806/BOL.MD | 12/09/2024 | 20 | M/S. YOUTH ENGINEERS' ENTERPRISE | 2.48 | 0 | 0 | 100
550 | BIRBHUM | Bolpur Mechanical | Albandha Piped Water Supply Scheme. , SM/14533 | New | Supply & delivery of submersible cable accessories at albandha Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | 3843/BOL.MD | 18/09/2024 | 20 | UNITED TRADERS | 2.15 | 0 | 0 | 100
551 | BIRBHUM | Bolpur Mechanical | Albandha Piped Water Supply Scheme. , SM/14533 | New | WBSEDCL QUOTATION FOR ALBANDHA WS SCHEME | BP-23-24-221 | 15/01/2024 | 0 | WBSEDCL | 5.28 | 0 | 0 | 0
552 | BIRBHUM | Central Drilling | Albandha Piped Water Supply Scheme. , SM/14533 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
553 | BIRBHUM | Birbhum Division | Albandha Piped Water Supply Scheme. , SM/14533 | New | Different works related to water supply scheme at ALBANDHA, BERGRAM & BIDYADHARPUR Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (2nd Call) | 4146/BHM | 19/10/2023 | 805 | AMAL DUTTA ROY | 1648.21 | 0 | 0 | 12
554 | BIRBHUM | Birbhum Division | Albandha Piped Water Supply Scheme. , SM/14533 | New | Hiring of 01(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, PHE Dte. under Birbhum Division, PHE Dte. For the period of 01.01.2025 to 30.06.2025. | 1237/BSD | 31/12/2024 | 181 | RAJIYA BIBI | 0.85 | 0 | 0 | 0
555 | BIRBHUM | Central Drilling | Albandha Piped Water Supply Scheme. , SM/14533 | New | Hiring of Diesel driven motor cab (BS-III & Above) (Non AC) having contract carriage permit along with driver for the office of the DIC/ CMSD-I P.H.E. Dte. Under CMSD-I(D), CDD, P.H.E. Dte. | 378/CMSD-I | 24/12/2024 | 182 | SUJATA BHOWMICK | 0.86 | 0 | 0 | 0
556 | BIRBHUM | Birbhum Division | Albandha Piped Water Supply Scheme. , SM/14533 | New | Continuation work order for "Hiring of 01(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, PHE Dte. under Birbhum Division, PHE Dte. For the period of 01.01.2025 to 30.06.2025" for another 03(Three) months i.e. 01.07.2025 to 30.09.2025. | 640/BSD | 20/06/2025 | 92 | RAJIYA BIBI | 0.43 | 0 | 0 | 0
557 | BIRBHUM | Birbhum Division | Dhalla Piped Water Supply Scheme , SM/15256 | New | Material Requisition To Resource Division | 1521/BHM | 26/04/2023 | 0 | Resource Division | 55.13 | 0 | 0 | 0
558 | BIRBHUM | Bolpur Mechanical | Dhalla Piped Water Supply Scheme , SM/15256 | New | Providing Electro-mechanical accessories and others for Dhalla PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 2225/Bol.MD | 12/09/2023 | 628 | QUAZI NOZRUL ISLAM | 44.4 | 0 | 0 | 30
559 | BIRBHUM | Bolpur Mechanical | Dhalla Piped Water Supply Scheme , SM/15256 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Dhalla PWSS under Illambazar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 520/BOL.MD | 14/03/2024 | 60 | AMITAVA CHAKRABORTY | 7.61 | 0 | 0 | 0
560 | BIRBHUM | Birbhum Division | Dhalla Piped Water Supply Scheme , SM/15256 | New | Continuation Work Order for Preparation & Submission of DPR for (DHALLA) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | 294/RSD | 07/09/2022 | 45 | ECO CARE | 2.76 | 0 | 0 | 100
561 | BIRBHUM | Birbhum Division | Dhalla Piped Water Supply Scheme , SM/15256 | New | Continuation Work Order for Preparation & Submission of DPR for (DHALLA) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | 383/RSD | 27/09/2022 | 45 | ECO CARE | 3.27 | 0 | 0 | 100
562 | BIRBHUM | Birbhum Division | Dhalla Piped Water Supply Scheme , SM/15256 | New | Material Requisition To Resource Division | 2484/BHM | 03/09/2024 | 0 | Resource Division | 13.92 | 0 | 0 | 0
563 | BIRBHUM | Birbhum Division | Dhalla Piped Water Supply Scheme , SM/15256 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR , Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at DHALLA & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 2180/BHM | 06/08/2024 | 365 | RADIANT | 497.94 | 0 | 0 | 40
564 | BIRBHUM | Birbhum Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/14895 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for SANTOSHPUR Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 209/BSD | 25/05/2022 | 90 | RADIANT | 4.73 | 0 | 0 | 100
565 | BIRBHUM | Birbhum Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/14895 | New | Material Requisition To Resource Division | 1464/BHM | 25/04/2023 | 0 | Resource Division | 19.69 | 0 | 0 | 0
566 | BIRBHUM | Birbhum Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/14895 | New | Material Requisition To Resource Division | 2383/BHM | 27/08/2024 | 0 | Resource Division | 10.16 | 0 | 0 | 0
567 | BIRBHUM | Central Drilling | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/14895 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
568 | BIRBHUM | Birbhum Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/14895 | New | Construction of 250 & 150 CuM. Capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements Laying of Rising Main, Distribution System with FHTC including different works related to SANTOSHPUR / NAWADA PALANDI /PAPURI / SAJNOR / RAYEN PIPED WATER SUPPLY SCHEME (5 Nos Scheme) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division PHE DTE. | 1951/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2322.64 | 0 | 0 | 5
569 | BIRBHUM | Bolpur Mechanical | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/14895 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Santoshpur Water supply Scheme (T/W-I & II), Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | 4533/BOL.MD | 20/12/2024 | 120 | PADMA ENGINEERING CO. | 73.34 | 0 | 0 | 0
570 | BIRBHUM | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division , SM/14160 | New | Providing Electro-mechanical accessories and others for Sultanpur PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | 3275/BOL.MD | 29/09/2023 | 60 | M. S. ENTERPRISE | 67.76 | 0 | 0 | 40
571 | BIRBHUM | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division , SM/14160 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Sultanpur PWSS, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte.. | 405/Bol.MD | 07/03/2024 | 45 | SATYAJIT GHOSH | 25.78 | 0 | 0 | 40
572 | BIRBHUM | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division , SM/14160 | New | Continuation Work Order for Preparation & Submission of DPR for (SULTANPUR) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | 334/RSD | 08/09/2022 | 45 | ENVIROTECH SOLUTIONS | 3.54 | 0 | 0 | 100
573 | BIRBHUM | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division , SM/14160 | New | Continuation Work Order for Preparation & Submission of DPR for (SULTANPUR) Water Supply Scheme (Part-B) under Mayureswar-II Development Block | 438/RSD | 29/11/2022 | 45 | ENVIROTECH SOLUTIONS | 3.5 | 0 | 0 | 100
574 | BIRBHUM | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division , SM/14160 | New | Material Requisition To Resource Division | 200/BHM | 22/01/2024 | 0 | Resource Division | 11.4 | 0 | 0 | 0
575 | BIRBHUM | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division , SM/14160 | New | NEW SERVICE CONNECTION AT SULTANPUR PWSS PH-I UNDER BOLPUR MECHANICAL DIVISION PHE Dte... | BP-24-25-09 | 25/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 11.36 | 0 | 0 | 0
576 | BIRBHUM | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division , SM/14160 | New | Quotation for new service connection at Sultanpur PWSS P/H- IV (Block- Mayureswar -II) | BP-2024-2025-80 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.56 | 0 | 0 | 0
577 | BIRBHUM | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division , SM/14160 | New | New service connection at Sultanpur PWSS ( P/H- 3) | BP-2024-2025-51 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.94 | 0 | 0 | 0
578 | BIRBHUM | Bolpur Mechanical | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division , SM/14160 | New | Quotation for New Service connection at Sultanpur PWSS P/H-3 (Bolck- Mayureswar-II) | BP-2024-2025-81 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.25 | 0 | 0 | 0
579 | BIRBHUM | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division , SM/14160 | New | Different works related to Water Supply Scheme at SULTANPUR & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 2065/BHM | 08/06/2023 | 1027 | M/S.SUMAN CONSTRUCTION | 575.26 | 0 | 0 | 45
580 | BIRBHUM | Birbhum Division | Sultanpur Piped Water Supply Scheme Under Mayureswar -II Block Within Birbhum Division , SM/14160 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
581 | BIRBHUM | Birbhum Division | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. , SM/14744 | Augmentation | Material Requisition To Resource Division | 1125/BHM | 10/04/2023 | 0 | Resource Division | 14.94 | 0 | 0 | 0
582 | BIRBHUM | Birbhum Division | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. , SM/14744 | Augmentation | Material Requisition To Resource Division | 972/BHM | 27/03/2023 | 0 | Resource Division | 102.97 | 0 | 0 | 0
583 | BIRBHUM | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. , SM/14744 | Augmentation | Supply and installation of Submersible pumping Machineries and HL Pumping Machineries with allied works at Augmentation of Narayanpur (Zone - II) PWSS, Block-Rampurhat- II under Bolpur Mechanical Division PHED. | 2117/Bol.MD | 23/08/2023 | 648 | SINHA ELECTRICALS | 98.04 | 0 | 0 | 30
584 | BIRBHUM | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. , SM/14744 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk River Bed Tube Wells and allieds works at Augmentation of Narayanpur water supply scheme under Bolpur Mechanical Division, PHE Dte. | 373/BOL.MD | 06/03/2024 | 30 | QUAZI NOZRUL ISLAM | 13.39 | 0 | 0 | 70
585 | BIRBHUM | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. , SM/14744 | Augmentation | Supply and Delivery of Sub-Mersible Pumping Machineries for Ground Based Tube Well for Narayanpur water supply scheme (Block- Rampurhat - I) under Bolpur Mechanical Division, PHE Dte. | 1622/AE-III | 18/12/2023 | 21 | M/S. YOUTH ENGINEERS' ENTERPRISE | 1.87 | 0 | 0 | 100
586 | BIRBHUM | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. , SM/14744 | Augmentation | Supply and Delivery of Voltage Correction Devices for Augmentation of Narayanpur (Zone-II) PWSS, (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | 3778/BOL.MD | 12/09/2024 | 30 | SINHA ELECTRICALS | 41.51 | 0 | 0 | 100
587 | BIRBHUM | Birbhum Division | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. , SM/14744 | Augmentation | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at NARAYANPUR (Zone-I & Zone-II) & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materialsunder BIRBHUM Division, PHE Dte. | 2769/BHM | 30/09/2024 | 730 | M/S GHOSH AND CO. | 518.25 | 0 | 0 | 20
588 | BIRBHUM | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. , SM/14744 | Augmentation | Supply,delivery and Installation of PDB cum MCC Panel and allieds works at Mayureswar water supply scheme ( under Augmentation of Narayanpur Piped Water Supply Scheme, Block-Rampurhat-II) under Bolpur Mechanical Division, P.H.E.Dte. | 2243/BOL.MD. | 13/09/2023 | 566 | UTTAM KUMAR CHATTERJEE | 15.71 | 14.35 | 91.42 | 100
589 | BIRBHUM | Bolpur Mechanical | Augmentation of Sub surface water based Narayanpur (Zone-I & II) piped water supply scheme under Birbhum Division, Rampurhat -I Block, district - Birbhum within Birbhum Division. PHE. Dte. , SM/14744 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well at Augmentation of Narayanpur (Zone-II) PWSS, (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | 400/Bol.MD | 07/03/2024 | 420 | SINHA ELECTRICALS | 79.02 | 0 | 0 | 90
590 | BIRBHUM | Birbhum Division | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/16373 | New | Continuation Work Order for Preparation & Submission of DPR for (Ramnagar) Water Supply Scheme under Mayureswar-II Development Block. | 203/RSD | 10/06/2022 | 45 | ENVIROTECH SOLUTIONS | 4.29 | 0 | 0 | 100
591 | BIRBHUM | Birbhum Division | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/16373 | New | Material Requisition To Resource Division | 1485/BHM | 25/04/2023 | 0 | Resource Division | 18.81 | 0 | 0 | 0
592 | BIRBHUM | Bolpur Mechanical | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/16373 | New | Providing Electro-mechanical accessories and others for Ramnagar PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | 3513/Bol.MD | 24/11/2023 | 60 | ORIENTAL ENGINEERING CO. | 55.45 | 0 | 0 | 65
593 | BIRBHUM | Bolpur Mechanical | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/16373 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Ramnagar PWSS under Mayureswar - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 532/BOL.MD | 14/03/2024 | 60 | S.B.ENTERPRISE(BOLPUR) | 7.6 | 0 | 0 | 66
594 | BIRBHUM | Birbhum Division | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/16373 | New | Material Requisition To Resource Division | 202/BHM | 22/01/2024 | 0 | Resource Division | 5.83 | 0 | 0 | 0
595 | BIRBHUM | Bolpur Mechanical | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/16373 | New | WBSEDCL QUOTATION FOR RAMNAGAR P H NO I | BP-23-24-265 | 07/02/2024 | 0 | WBSEDCL | 12.33 | 0 | 0 | 0
596 | BIRBHUM | Bolpur Mechanical | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/16373 | New | NEW POWER CONNECTION AT RAMNAGAR PWSS P/H No-II | BP-2024-2025-59 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.97 | 0 | 0 | 0
597 | BIRBHUM | Bolpur Mechanical | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/16373 | New | NEW SERVICE CONNECTION AT RAMNAGAR PWSS P/H No-III | BP-2024-2025-60 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 16.33 | 0 | 0 | 0
598 | BIRBHUM | Birbhum Division | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/16373 | New | Different works related to Water Supply Scheme at RAMNAGAR & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 903/BHM | 22/03/2023 | 741 | M/S.SUMAN CONSTRUCTION | 433.92 | 0 | 0 | 65
599 | BIRBHUM | Birbhum Division | Ramnagar Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/16373 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
600 | BIRBHUM | Birbhum Division | Hatikata Piped Water Supply Scheme , SM/16198 | New | Preparation & Submission of DPR for Hatikata & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 87/BSSD | 19/05/2022 | 45 | RADIANT | 1.88 | 0 | 0 | 100
601 | BIRBHUM | Birbhum Division | Hatikata Piped Water Supply Scheme , SM/16198 | New | Material Requisition To Resource Division | 433/BHM | 01/02/2024 | 0 | Resource Division | 54.82 | 0 | 0 | 0
602 | BIRBHUM | Birbhum Division | Hatikata Piped Water Supply Scheme , SM/16198 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
603 | BIRBHUM | Birbhum Division | Hatikata Piped Water Supply Scheme , SM/16198 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
604 | BIRBHUM | Bolpur Mechanical | Radipur Piped Water Supply Scheme. , SM/14027 | New | Providing Electro-mechanical accessories and others for Radipur & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 3528/Bol.MD | 29/11/2023 | 60 | ASHIM UDYOG | 27.61 | 0 | 0 | 0
605 | BIRBHUM | Birbhum Division | Radipur Piped Water Supply Scheme. , SM/14027 | New | Material Requisition To Resource Division | 1576/BHM | 26/04/2023 | 0 | Resource Division | 13.07 | 0 | 0 | 0
606 | BIRBHUM | Birbhum Division | Radipur Piped Water Supply Scheme. , SM/14027 | New | Sinking of 250 mm.X 150 mm.Dia Tube Well (2 nos) Drilling by Direct Rotary method ,Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 200 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Radipur & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division,PHE Dte | 2644/BHM | 12/09/2024 | 365 | DIAMOND ENGINEERS CO-OPERATIVE SOCIETY LTD | 379.68 | 0 | 0 | 0
607 | BIRBHUM | Birbhum Division | Radipur Piped Water Supply Scheme. , SM/14027 | New | Material Requisition To Resource Division | 3259/BHM | 02/12/2024 | 0 | Resource Division | 10.57 | 0 | 0 | 0
608 | BIRBHUM | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07155 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Hatina, Uchpur, Narayanpur, Gopinathpur ,Basudebpur in Basudebpur w/s Scheme under Rampurhat Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl. No.2) | 1286/BHM | 10/08/2021 | 60 | BANERJEE CONSTRUCTION | 36.47 | 35.5 | 97.35 | 100
609 | BIRBHUM | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07155 | Retrofitting | Allied works for Providing FHTC from existing distributin system at Hatina mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. | 05/RSD | 04/01/2022 | 30 | M/S BUILDWELL | 4.99 | 0 | 0 | 100
610 | BIRBHUM | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07155 | Retrofitting | Allied works for Providing FHTC from existing distributin system at Narayanpur mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte | 06/RSD | 04/01/2022 | 30 | M/S BUILDWELL | 4.99 | 0 | 0 | 0
611 | BIRBHUM | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07155 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for providing FHTC at mouza Chotto Bataspur, Gopinathpur & Uchpur within Basudebpur PWSS under Rampurhat Sub-Division, P.H.E. Dte. | 03/RSD | 04/01/2022 | 30 | SOIL STORY | 4.95 | 4.95 | 100 | 100
612 | BIRBHUM | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07155 | Retrofitting | Allied works for Providing FHTC from existing distributin system at Hatina mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. | 05/RSD | 04/01/2021 | 30 | M/S BUILDWELL | 4.99 | 7.77 | 100 | 100
613 | BIRBHUM | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07155 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for providing FHTC at Basudebpur mouza under Basudebpur PWSS under Rampurhat Sub- Division, P.H.E. Dte. | 02/RSD | 04/01/2022 | 30 | BANERJEE CONSTRUCTION | 2.62 | 2.61 | 100 | 100
614 | BIRBHUM | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07155 | Retrofitting | Providing FHTC from existing distributin system at Gargara mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. | 27/RSD | 04/01/2022 | 30 | JAYANTA BARAL | 4.99 | 4.99 | 100 | 80
615 | BIRBHUM | Birbhum Division | Retrofitting works of Basudebpurt Water Supply Scheme under Mayureswar-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07155 | Retrofitting | Providing FHTC from existing distributin system at Pukhur Para mouza within Basudebpur w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. | 28/RSD | 04/01/2022 | 30 | ABUL HASNAT | 5 | 4.99 | 100 | 100
616 | BIRBHUM | Bolpur Mechanical | HATIKRA PIPED WATER SUPPLY SCHEME. , SM/12893 | New | Providing Electro-mechanical accessories and others for Hatikara PWSS at Suri - II Block under Bolpur Mechanical Division PHE Dte. | 2105/BOL.MD. | 22/08/2023 | 60 | HINDOL ROY | 29.37 | 0 | 0 | 60
617 | BIRBHUM | Birbhum Division | HATIKRA PIPED WATER SUPPLY SCHEME. , SM/12893 | New | Material Requisition To Resource Division | 1386/BHM | 24/04/2023 | 0 | Resource Division | 19.08 | 0 | 0 | 0
618 | BIRBHUM | Birbhum Division | HATIKRA PIPED WATER SUPPLY SCHEME. , SM/12893 | New | Different works related to water supply scheme at BANSHANKA & HATIKARA its adjoining mouzas water supply scheme within SURI - II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1181/BHM | 12/04/2023 | 1041 | MAHAVIR PUMPS MFG PVT LTD | 773.9 | 0 | 0 | 5
619 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ALALCHAK AND OTHER 28 NOS. MOUZAS UNDER DUBRAJPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/12074 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 231.45 | 24.52 | 92
620 | BIRBHUM | Birbhum Division | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. , SM/18366 | Augmentation | Material Requisition To Resource Division | 1116/BHM | 10/04/2023 | 0 | Resource Division | 9.43 | 0 | 0 | 0
621 | BIRBHUM | Birbhum Division | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. , SM/18366 | Augmentation | Material Requisition To Resource Division | 971/BHM | 27/03/2023 | 0 | Resource Division | 363.95 | 0 | 0 | 0
622 | BIRBHUM | Birbhum Division | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. , SM/18366 | Augmentation | Extension of distribution pipe line from Kushmasol to Chandpur, Nichupara and English Medium School and all other allied works for augmentation of Patharchapuri Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte. | 671/BHM | 20/02/2024 | 45 | SOURAV MONDAL | 5.23 | 0 | 0 | 100
623 | BIRBHUM | Bolpur Mechanical | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. , SM/18366 | Augmentation | Supply and Delivery of Sub-Mersible Pumping Machineries & others for Augmentation of Patharchapuri PWSS, (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. | 3786/BOL.MD | 12/09/2024 | 80 | DEY ENTERPRISE | 50.29 | 0 | 0 | 100
624 | BIRBHUM | Birbhum Division | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. , SM/18366 | Augmentation | Sinking of Tubewell, Construction of OHR, Construction of Boundary wall, pump house and laying distribution system along with FHTC works at Augmentation of Patharchapri & its adjoining mouzas water supply scheme within Suri - I Block under Birbhum Division PHE Dte | 4143/BHM | 19/10/2023 | 787 | M/S GOUTAM DAS | 513.52 | 0 | 0 | 80
625 | BIRBHUM | Bolpur Mechanical | Augmentation of Sub Surface Water based Pathar Chapri (Zone-I & Zone-II), Pipe Water Supply Scheme, under Block- Suri-I within Birbhum Division, PHE Dte. , SM/18366 | Augmentation | Supply & installation of High Lift Pumping Machinery for (Zone - I & II) with other Electro-Mechanical accessories at Augmentation of Pathar Chapri Piped Water Supply Scheme, Block-Suri - I under Bolpur Mechanical Division, PHE Dte. | 2247/Bol.MD | 13/09/2023 | 615 | S.K.ELECTRICALS | 29.88 | 0 | 0 | 100
626 | BIRBHUM | Bolpur Mechanical | KAHINAGAR PIPED WATER SUPPLY SCHME , SM/12887 | New | Providing Electro-mechanical accessories and others for Kahinagar PWSS at Murarai - I Block under Bolpur Mechanical Division PHE Dte. | 3286/BOL.MD | 29/09/2023 | 60 | MASSK ENGINEERING WORKS | 27.62 | 0 | 0 | 0
627 | BIRBHUM | Birbhum Division | KAHINAGAR PIPED WATER SUPPLY SCHME , SM/12887 | New | Material Requisition To Resource Division | 1434/BHM | 25/04/2023 | 0 | Resource Division | 9.84 | 0 | 0 | 0
628 | BIRBHUM | Birbhum Division | KAHINAGAR PIPED WATER SUPPLY SCHME , SM/12887 | New | Different works related to water supply scheme at Dalima, Kahinagar & Dumurgram and its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1423/BHM | 25/04/2023 | 1090 | AKASH CONSTRUCTION | 1377.29 | 0 | 0 | 16
629 | BIRBHUM | Bolpur Mechanical | KAHINAGAR PIPED WATER SUPPLY SCHME , SM/12887 | New | Providing Electro-mechanical accessories and others at Pump House- I & II for Bahadurpur W/S Scheme (Kahinagar PWSS) at Murarai -I Block under Bolpur Mechanical Division PHE Dte | 464/BOL.MD | 07/03/2025 | 30 | SUNIL RABIDAS | 5.5 | 0 | 0 | 0
630 | BIRBHUM | Birbhum Division | Mostala Piped Water Supply Scheme. , SM/18519 | New | Material Requisition To Resource Division | 1362/BHM | 24/04/2023 | 0 | Resource Division | 133.81 | 0 | 0 | 0
631 | BIRBHUM | Bolpur Mechanical | Mostala Piped Water Supply Scheme. , SM/18519 | New | Providing Electro-mechanical accessories and others for Mostala & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | 2241/BOL.MD. | 13/09/2023 | 476 | SINHA ELECTRICALS | 85.42 | 0 | 0 | 78
632 | BIRBHUM | Bolpur Mechanical | Mostala Piped Water Supply Scheme. , SM/18519 | New | Supply and delivery of Submersible pump for ikshudhara Water Supply Scheme(T/W - I) under Bolpur Mechanical Divn. PHE Dte. | 3850/BOL.MD | 18/09/2024 | 20 | SWAPAN BANERJEE | 2.62 | 0 | 0 | 100
633 | BIRBHUM | Bolpur Mechanical | Mostala Piped Water Supply Scheme. , SM/18519 | New | Supply and delivery of Submersible pump for ikshudhara Water Supply Scheme (T/W-II) under Bolpur Mechanical Divn. PHE Dte. | 3873/BOL.MD | 19/09/2024 | 20 | M/S. S.S. ENTERPRISE | 2.75 | 0 | 0 | 0
634 | BIRBHUM | Bolpur Mechanical | Mostala Piped Water Supply Scheme. , SM/18519 | New | Supply and delivery of M.S. seamless column pipe for Mostala water supply Scheme under BOL MD, PHE Dte.. | 4194/BOL.MD | 22/10/2024 | 20 | EASTERN INDIA SALES & SERVICE | 2.94 | 0 | 0 | 100
635 | BIRBHUM | Bolpur Mechanical | Mostala Piped Water Supply Scheme. , SM/18519 | New | Supply & delivery of submersible cable accessories at mostala water supply scheme T.W No-II under Bolpur Mechanical Division, PHE Dte. | 3822/BOL.MD | 18/09/2024 | 20 | STANDARD ELECTRICALS | 2.8 | 0 | 0 | 100
636 | BIRBHUM | Bolpur Mechanical | Mostala Piped Water Supply Scheme. , SM/18519 | New | Supply & delivery of submersible cable accessories at Mostala water supply scheme T.W No-I under Bolpur Mechanical Division, PHE Dte. | 3820/BOL.MD | 18/09/2024 | 20 | RAJIB GHOSH | 3.07 | 0 | 0 | 100
637 | BIRBHUM | Bolpur Mechanical | Mostala Piped Water Supply Scheme. , SM/18519 | New | WBSEDCL QUOTATION FOR MOSTALA WS SCHEME | BP-23-24-219 | 15/01/2024 | 0 | WBSEDCL | 5.37 | 0 | 0 | 0
638 | BIRBHUM | Central Drilling | Mostala Piped Water Supply Scheme. , SM/18519 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
639 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS , SM/06736 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Jamrand Bauripara, Fullaichack & Bartikuri under Jamrand Mouza (JL No. - 136) under Khoyrasole Block, within the command area of Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 32)) | 207/BSSD | 15/06/2021 | 30 | RICK CONSTRUCTION | 4.97 | 4.97 | 100 | 100
640 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS , SM/06736 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Isgara, Narayanpur, Beldanga & Rajnagar in Jamrand w/s Scheme under Suri Sadar Sub Division within Birbhum Division, PHE Dte. (Sl. No.18) | 1708 /BHM | 23/12/2020 | 60 | PRAVAT SARKAR | 29.59 | 50.84 | 177.67 | 100
641 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS , SM/06736 | Retrofitting | Relaying of UPVC distribution Pipe line due to damage for construction of drain and reconnection of existing Household Tap Connection (FHTC) from Kendragaria Gram Panchayat Office towards Sarafat Khan house under Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H. E Dte. (Sl. No. - 07) | 405/BSSD | 14/12/2021 | 15 | GOUTAM MONDAL | 1.28 | 1.28 | 100 | 100
642 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS , SM/06736 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Jamrand Chasapara under Jamrand Mouza (JL No.-136) under Khoyrasole Block,within the command area of Jamrand Piped w/s Scheme in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte. (SL No.-31) | 206/BSSD | 15/06/2021 | 30 | SUMAN CHOWDHURY | 4.97 | 4.5 | 100 | 100
643 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS , SM/06736 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Jamrand, Matiala Bhimgara in Jamrand w/s Scheme under Suri Sadar Sub Division within Birbhum Division, PHE Dte. (Sl. No.17) | 1709/BHM | 23/12/2020 | 60 | RICK CONSTRUCTION | 30.49 | 20 | 105.57 | 100
644 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS , SM/06736 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte. (Sl. No. ¿ 01) | 89/BSSD | 27/05/2022 | 20 | SK FAQHRUL AMIN | 4.99 | 4.98 | 100 | 100
645 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS , SM/06736 | Retrofitting | Restoration of distribution pipe line at various location nearby Kabbarsthan, Bimgarh Bus Stand etc. for smooth running of FHTC under Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte.(Sl. No. - 15) | 226/BSSD | 21/09/2022 | 20 | GOUTAM MONDAL | 4.91 | 4.91 | 100 | 100
646 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Jamrand PWSS , SM/06736 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Beledanga area (J.L :- 142) Habitation of Rathtala under Beledanga Mouza under Suri- Khayrasole Block, within the command area of Jamrand Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 07) | 285/BSSD | 13/08/2021 | 30 | B.M.SARKAR | 4.04 | 0 | 0 | 100
647 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Bikandi, Saora in Raghunathpur w/s Scheme under Nahati Sub Division within Birbhum Division, PHE Dte. (Sl. No.5) | 141/BHM | 05/02/2021 | 60 | QUAZI SIRAJUL ISLAM. | 34.7 | 69.4 | 200 | 100
648 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Dharampur in Raghunathpur w/s Scheme under Nahati Sub Division within Birbhum Division, PHE Dte. (Sl. No.7) | 143/BHM | 05/02/2021 | 60 | G. B. CONSTRUCTION AND CO. | 41.87 | 40.86 | 100 | 100
649 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area in the villages kadya raghunathpur in Raghunathpur WS Scheme (Sl.No.06) |  | 19/03/2021 | 0 | M/S MD AMINUL ISLAM | 26.68 | 0 | 0 | 0
650 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system with the command areain the villages bilkandi saora in Raghunathpur WS Scheme (Sl.No.05) |  | 18/03/2021 | 0 | QUAZI SIRAJUL ISLAM. | 34.7 | 0 | 0 | 0
651 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Tailpara in Raghunathpur w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. (Sl. No.2) |  | 16/03/2021 | 0 | S R ENTERPRISE | 25.48 | 0 | 0 | 0
652 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kadya, Raghunathpur in Raghunathpur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.6) | 142/BHM | 05/02/2021 | 60 | M/S MD AMINUL ISLAM | 36.49 | 72.98 | 200 | 100
653 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Tailpara in Raghunathpur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.4) | 78/BHM | 27/01/2021 | 60 | S R ENTERPRISE | 25.48 | 10.95 | 200 | 50
654 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raghunathpur w/s Scheme (Left out House Hold) in Nalhati Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.10) | 1507/BHM | 09/09/2021 | 60 | M/S MD AMINUL ISLAM | 37.25 | 37.25 | 50 | 100
655 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Miyapur, Barla, Thengapara, Bagbari raghunathpur habitation and adjacent area under Raghunathpur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 607/AE/NSD | 26/11/2021 | 45 | ENAMUL ISLAM | 4.82 | 4.82 | 100 | 100
656 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Laying distribution system From NP-58 towards Dharampur(079) under Raghunathpur PWSS under Nalhati Sub Division PHED. | 277/A/AE/NSD | 16/04/2021 | 30 | SUNIL RABI DAS | 0.97 | 0 | 0 | 0
657 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Laying distribution system From NP-135 towards NP-136 under Raghunathpur PWSS under Nalhati Sub Division PHED. | 277/B/AE/NSD | 16/04/2021 | 30 | SUNIL RABI DAS | 0.97 | 0 | 0 | 0
658 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Annual Maintenance of Tube wells, Raw water rising main pipe line and CWR for the daily supply of water to the consumers under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. as mentioned below for 03 (Three) months only (from 16.06.2021 to 15.09.2021) of Raghunathpur Water Supply Scheme. | 318/AE/NSD | 15/06/2021 | 92 | SHIB GANGA CONSTRUCTION | 0.7 | 0 | 0 | 0
659 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Continuation work order for Annual Maintenance of Tube wells, Raw water rising main pipe line and CWR for the daily supply of water to the consumers under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. as mentioned below for 03 (Three) months only (from 18.03.2022 to 17.06.2022) of Raghunathpur Water Supply Scheme. | 157/NSD | 17/03/2022 | 92 | SHIB GANGA CONSTRUCTION | 0.7 | 0 | 0 | 0
660 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Balance estimate for construction of boundary wall near C.W.R Site including M.S. Ornamental grill railing at Raghunathpur Water Supply Scheme under Nalhati Sub Division P.H.E. Dte. | 589/AE/NSD | 22/11/2021 | 30 | BHARAT CONSTRUCTION | 2.85 | 0 | 0 | 100
661 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Sinking of replacement the tubewell of 200mm dia & 60 m. deep with PVC pipe and fibre glass Strainer at Raghunathpur (near head work side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | 209/AE/NSD | 05/04/2022 | 30 | MD AMINUL ISLAM | 3.74 | 0 | 0 | 100
662 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Work Order for Construction of boundary wall near OHR site at Raghunathpur Water Supply Scheme under Nalhati Sub-Division, PHE Dte. (Sl. No.1) | 1119/BHM | 09/09/2020 | 60 | MD. SHAHA JAMAL | 4.97 | 0 | 0 | 100
663 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Extension of 63 & 75 mm Dia. UPVC Pipe line in Miapur,Barla,Bagbari & Barmaroi habitations for providing FHTC within Raghunathpur Piped Water Supply Scheme under Nalhati Sub-Division P.H.E Dte. | 226/NSD | 19/04/2022 | 45 | ENAMUL ISLAM | 3.59 | 3.59 | 100 | 100
664 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Continuation Work Order for Maintenance of Tube wells, Raw water rising main pipe line and CWR for the daily supply of water to the consumers under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. as mentioned below for 03 (Three) months only (from 18.06.2022 to 17.09.2022) of Raghunathpur Water Supply Scheme. | 314/AE/NSD | 17/06/2022 | 92 | SHIB GANGA CONSTRUCTION | 0.7 | 0 | 0 | 100
665 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raghunathpur PWSS within Nalhati-I Block, Dist.- Birbhum under Birbhum Division. PHEDte , SM/07533 | Retrofitting | Collection of Household Data Through Mobile APP/Hardcopy including Geo-reference and submission of the same in soft copy against completed FHTC works at the command area of Kaitha W/S Scheme under Birbhum Division. | 138/BH | 19/08/2021 | 10 | ENAMUL ISLAM | 0.1 | 0.32 | 200 | 0
666 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. , SM/09368 | Retrofitting | Laying of Rising main with DI pipe line for inter connection and bypass arrangement for Jhikadda water supply scheme under Rampurhat sub division under Birbhum Division, PHE Dte. | 21/RSD | 04/01/2022 | 30 | KALYAN PAL | 1.65 | 0 | 0 | 100
667 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. , SM/09368 | Retrofitting | Construction of Boundary Wall & Internal path way at 2nd Site for JHIKADDA PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 22/RSD | 04/01/2022 | 45 | ABHOY CHARAN GHOSH | 4.33 | 0 | 0 | 100
668 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. , SM/09368 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jikadda Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte (Sl. No.3) | 821/BHM | 13/04/2022 | 60 | KAZI EMDADUL HAQUE | 55.12 | 54.62 | 100 | 100
669 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. , SM/09368 | Retrofitting | Laying of HDPE Pipe line for Krishnanagar mouzas under Jhikadda Piped Water Supply Scheme under Rampurhat sub-Division, under Birbhum Division, PHE Dte. | 103/RSD | 07/03/2022 | 30 | ABHOY CHARAN GHOSH | 4.96 | 0 | 0 | 100
670 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. , SM/09368 | Retrofitting | Material Requisition To Resource Division | 216/BHM | 02/02/2022 | 0 | Resource Division | 6.64 | 0 | 0 | 0
671 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Jhikadda PWSS within Mayureswar-I Block District Birbhum under Birbhum Division, PHE Dte. , SM/09368 | Retrofitting | Allied works for construction of pipe culvart, land development and temporary approach road at H/W site of JHIKADDA PWSS under Rampurhat Sub Division.PHE Dte. | 20/RSD | 04/01/2022 | 30 | ABHOY CHARAN GHOSH | 4.74 | 0 | 0 | 100
672 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Hajrapur PWSS within Dubrajpur Block District Birbhum under Birbhum Division, PHE Dte. , SM/09369 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Hajarpur under Hajarpur Water Supply Scheme within Birbhum Division, PHE Dte.¿ (Sl. No.10) | 1453/BHM | 07/07/2022 | 60 | SAPTADIP CONSTRUCTION | 25.25 | 25.18 | 100 | 100
673 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Dubrajpur Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 08) | 381/BSSD | 10/12/2021 | 20 | RANJIT GHOSH | 0.99 | 0.72 | 100 | 100
674 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing Functional Household Tap Connection (FHTC) for AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Labpur Zone-I & Zone-II Water Supply Scheme within Labpur Block under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 08). | 71/BSD | 03/03/2022 | 10 | ANKITA CHAKRABORTY | 1.09 | 1.08 | 100 | 50
675 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 18 (Eighteen) Nos Anganwadi Center having no Electric Power Connection within the command area of Bolpur Sriniketan Development Block under Birbhum Division P.H.E.Dte. (Sl. No.17) | 2794/BHM | 15/12/2022 | 45 | PRATIMA CONSTRUCTION | 11.1 | 0 | 0 | 10
676 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 21 (Twenty One) Nos Anganwadi Center having no Electric Power Connection under Alunda & Nagari G.P. within the command area of Suri-I Development Block under Birbhum Division P.H.E.Dte. (Sl. No.1) | 2796/BHM | 15/12/2022 | 45 | MITA DAS DOM | 12.96 | 1.9 | 14.66 | 0
677 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 28 (Twenty Eight) Nos Anganwadi Center having no Electric Power Connection under Kaitha-I within the command area of Nalhati-I Development Block under Birbhum Division P.H.E.Dte. (SL.No.5) | 2308/BHM | 21/10/2022 | 45 | DUBE ENTERPRISE | 17.3 | 15.52 | 89.68 | 97
678 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 27 (Twenty Seven) Nos Anganwadi Center having no Electric Power Connection under Illambazar, Bilati & Nanasole GP within the command area of Illambazar Development Block under Birbhum Division P.H.E. Dte. | 2510/BHM | 17/11/2022 | 45 | PRATICK KUMAR GHOSH | 17.02 | 0 | 0 | 0
679 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 28 (Twenty Eight) Nos Anganwadi Center having no Electric Power Connection under Barla G.P. within the command area of Nalhati-I Development Block under Birbhum Division P.H.E.Dte. | 2499/BHM | 17/11/2022 | 45 | MAHALAXMI CONSTRUCTION | 17.31 | 7.49 | 43.25 | 0
680 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 27 (Twenty Seven) Nos. Anganwadi Center having no Electric Power Connection JOydev Kenduli, Ghurisha, & Batikar G.P. within the command area of Illambazar Development Block under Birbhum Division, P.H.E.Dte. (Sl. No.14) | 2489/BHM | 16/11/2022 | 45 | JAGADANANDAPUR CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 16.63 | 4.55 | 27.38 | 39
681 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 10 (Ten) Nos Anganwadi Center having no Electric Power Connection within the command area of Murarai-II Development Block under Birbhum Division P.H.E.Dte. (Sl. No.13) | 2886/BHM | 22/12/2022 | 45 | HARUN AR RASHID | 6.18 | 0 | 0 | 0
682 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 16 (Sixteen) Nos Anganwadi Center having no Electric Power Connection within the command area of Murarai-I Development Block under Birbhum Division P.H.E.Dte. (Sl. No.12) | 2918/BHM | 27/12/2022 | 45 | MD ASIF ALI | 9.88 | 0 | 0 | 0
683 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 26 (Twenty Six) Nos Anganwadi Center having no Electric Power Connection within the command area of Dubrajpur Development Block under Birbhum Division P.H.E.Dte. (Sl. No.18) | 2916/BHM | 27/12/2022 | 45 | RUBAL CONSTRACTION | 16.06 | 0 | 0 | 0
684 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 12 (Twelve) Nos Anganwadi Center having no Electric Power Connection within the command area of Nalhati-II Development Block under Birbhum Division P.H.E.Dte.(Sl. No.14) | 2917/BHM | 27/12/2022 | 45 | HIMANGSU SEKHAR SARKAR | 7.47 | 0 | 0 | 0
685 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 28 (Twenty Eight) Nos Anganwadi Center having no Electric Power Connection under Pachra & Parsundi G.P. within the command area of Khoyrasole Development Block under Birbhum Division P.H.E.Dte. Total Number of Anganwadi Center -28, (Sl. No.13) | 2607/BHM | 24/11/2022 | 45 | UTPAL DEY | 17.81 | 0 | 0 | 0
686 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 23 (Twenty Three) Nos. Anganwadi Center having no Electric Power Connection under within Banior, Bautia, Kalitha & Kaitha-II G.P. the command area of Nalhati-I Development Block under Birbhum Division P.H.E.Dte. | 2502/BHM | 17/11/2022 | 45 | RAJA CONSTRUCTION | 14.61 | 6.44 | 44.04 | 48
687 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 19 (Nineteen) nos. Anganwadi Center having no Electric Power Connection under Ahmadpur and Mathpalsa G.P. within the command area of Sainthia Development Block under Birbhum Division P.H.E.Dte. | 2599/BHM | 23/11/2022 | 45 | JAYANTA BARAL | 11.73 | 0 | 0 | 0
688 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 19 (Nineteen) Nos Anganwadi Center having no Electric Power Connection under Barasota within the command area of Nanoor Development Block under Birbhum Division P.H.E.Dte. (Sl. No.5) | 27/BHM | 04/01/2023 | 45 | GOURANGA MONDAL | 11.73 | 6.25 | 53.29 | 0
689 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 26 (Twenty Six) Nos Anganwadi Center having no Electric Power Connection under Labpur-I & Labpur-II GP within the command area of Labpur Development Block under Birbhum Division P.H.E.Dte. | 2608/BHM | 24/11/2022 | 45 | MS KAZIMEHERUDDIN | 16.35 | 0 | 0 | 0
690 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 20 (Twenty) Nos Anganwadi Center having no Electric Power Connection under Deriapur G.P. within the command area of Sainthia Development Block under Birbhum Division P.H.E.Dte. (Sl. No.7) | 292/BHM | 01/02/2023 | 45 | M/S S.N CONSTRUCTION | 12.36 | 0 | 0 | 0
691 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 4 (Four) Nos Anganwadi Center having no Electric Power Connection within the command area of Rampurhat-II Development Block under Birbhum Division P.H.E.Dte. (Sl. No.16) | 522/BHM | 20/02/2023 | 45 | MS SANTI CONSTRUCTION | 2.47 | 0 | 0 | 0
692 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Survey for Functional Household Tap Connection (FHTC) at different School and Aganwadi Centre in Nalhati-I & Nalhati-II Block under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 423/AE/NSD | 23/08/2021 | 15 | JOY CHAND MAL | 0.09 | 0.09 | 100 | 13
693 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Survey for Functional Household Tap Connection (FHTC) at different School and Aganwadi Centre in Murarai-I & Murarai-II Block under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 424/AE/NSD | 23/08/2021 | 15 | JOY CHAND MAL | 0.09 | 0.09 | 100 | 37
694 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Sainthia Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 07) | 400/BSSD | 14/12/2021 | 20 | SUBHRADIP SARKAR | 0.99 | 0.8 | 100 | 50
695 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Rajnagar Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 10) | 382/BSSD | 10/12/2021 | 20 | SUBHANKAR ROY | 0.99 | 0.72 | 100 | 49
696 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing Functional Household Tap Connection (FHTC) for School, AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Illambazar (Illambazar & Daronda) within Ruppur & Illambazar G.P.under Bolpur Sub-Division within Birbhum Division, PHED | 16/BSD | 11/01/2022 | 15 | GANAPATI ENGINEERING CORP. | 1.97 | 1.3 | 100 | 48
697 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 20 (Twenty) Nos Primary School having Electric Power Connection within the command area of MD. Bazar Development Block under Birbhum Division P.H.E.Dte.(Sl. No.4) | 2708/BHM | 07/12/2022 | 45 | SOUMEN CHATTERJEE | 18.6 | 0 | 0 | 100
698 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 16 (Sixteen) Nos. Primary School having Electric Power Connection within the command area of Nanoor Development Block under Birbhum Division, P.H.E.Dte. (Sl. No.1) | 2846/BHM | 22/12/2022 | 45 | JAGADANANDAPUR CO-OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 14.31 | 0 | 0 | 100
699 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 20 (Twenty) Nos Primary School having Electric Power Connection within the command area of Sainthia Development Block under Birbhum Division P.H.E.Dte. (Sl. No.2) | 204/BHM | 19/01/2023 | 45 | PARTHA PRATIM ACHARYA | 18.21 | 0 | 0 | 100
700 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Extension of Pipe line at Husnabad and Lambodarpur for providing connection to 3 nos A.W.C's, supply water to Husnabad Muslimpara & restoration of damaged pipeline at Sabujpally (JL No. - 106) of Karidhya Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. (Sl. No. - 08) | 389/BSSD | 10/12/2021 | 15 | M/S C.P. CONCERN | 1.67 | 1.65 | 100 | 100
701 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 14 (Fourteen) Nos Anganwadi Center having no Electric Power Connection within the command area of Mayureswar-II Development Block under Birbhum Division P.H.E.Dte.Total Number of Anganwadi Center -14, (Sl. No.18) | 2606/BHM | 24/11/2022 | 45 | PRANAB KUMAR MONDAL | 8.08 | 2.69 | 33.31 | 100
702 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 21 (Twenty One) Nos Anganwadi Center having no Electric Power Connection under Mallickpur & Khatanga G.P. within the command area of Suri-I Development Block under Birbhum Division P.H.E.Dte. (Sl. No.3) | 2793/BHM | 15/12/2022 | 45 | SRAMIC MANGAL CO OP LABOUR CONT AND CONST SOCIETY LTD | 12.97 | 0 | 0 | 100
703 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 24 (Twenty Four) Nos. Primary School having Electric Power Connection within the command area of Bolpur Sriniketan, Dubrajpur, Nalhati-I & Suri-II Development Block under Birbhum Division, P.H.E.Dte. (Sl. No.6) | 2443/BHM | 03/11/2022 | 45 | G.S CONSTRUCTION AND CO. | 21.73 | 0 | 0 | 85
704 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 27 (Twenty Seven) Nos. Anganwadi Center having no Electric Power Connection under Kendgore, Khoyrasole & Hazratpur G.P. within the command area of Khoyrasole Development Block under Birbhum Division P.H.E.Dte. | 2434/BHM | 02/11/2022 | 45 | B.M.SARKAR | 16.55 | 4.97 | 78.1 | 42
705 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 20 (Twenty) Nos Anganwadi Center having no Electric Power Connection under Kendua & Domdoma within the command area of Suri-II Development Block under Birbhum Division P.H.E.Dte(Sl. No.10) | 2786/BHM | 14/12/2022 | 45 | M/S.CHANDRANATH MUKHERJEE | 12.36 | 5.86 | 100 | 0
706 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 21 (Twenty One) Nos. Primary School having Electric Power Connection within the command area of Murarai-I Development Block under Birbhum Division P.H.E.Dte. | 2653/BHM | 01/12/2022 | 45 | KAZI EMDADUL HAQUE | 19.51 | 8.37 | 46.14 | 100
707 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 21 (Twenty One) Nos Anganwadi Center having no Electric Power Connection under Kirnahar-I, Kirnahar-II & Nonnagar Kadda within the command area of Nanoor Development Block under Birbhum Division P.H.E.Dte.(Sl. No.6) | 33/BHM | 04/01/2023 | 45 | KHOKAN SAHA | 12.98 | 5.25 | 100 | 0
708 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 19 (Nineteen) Nos Anganwadi Center having no Electric Power Connection under Koma and Purandarpur within the command area of Suri-II Development Block under Birbhum Division P.H.E.Dte. | 2656/BHM | 01/12/2022 | 45 | BARDHAMAN AQUA ENGINEERING | 11.5 | 6.91 | 100 | 0
709 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing necessary water supply arrangement at 17 (Seventeen) Nos Primary School having Electric Power Connection within the command area of Labpur Development Block under Birbhum Division P.H.E.Dte.(Sl. No.5) | 223/BHM | 20/01/2023 | 45 | AVIJIT CHANDA | 15.88 | 0 | 0 | 45
710 | BIRBHUM | Birbhum Division | Extension of PWS to Anganwadi Centers (AWCs) located within command area of PWSS under Birbhum Division , SM/09559 | Anganwadi | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Khayrasole Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. | 383/BSSD | 10/12/2021 | 20 | HIRANMAY GHOSH | 0.99 | 0 | 0 | 100
711 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) , SM/06742 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Saldanga, Dhalla, Lakshmipur, Daranda & Ramnagar of Daranda w/s Scheme at Illambazar Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No.10) | 1024/BHM | 04/11/2020 | 45 | S.S. BHATTACHARJEE. | 13.82 | 0 | 0 | 35
712 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) , SM/06742 | Retrofitting | Hiring of SWIFT DIZER (Diesel) or equivalent luxury car for office of the Assistant Engineer, Nalhati Sub - Division under Birbhum Division, PHE Dte. (Period from 01.04.2023 to 30.09.2023) 183-Days. | 130/AE/NSD | 31/03/2023 | 183 | JOY CHAND MAL | 0.86 | 0.39 | 100 | 85
713 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) , SM/06742 | Retrofitting | Replacement of damaged UPVC pipe line due to widening of road from Bubahat More towards Chella along with extension of UPVC pipe line for the habitation of Halsidanga, Chella, etc. of Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | 457/BSD | 13/12/2021 | 30 | S.S. BHATTACHARJEE. | 4.34 | 0 | 0 | 50
714 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) , SM/06742 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Daronda w/s Scheme (Left out House Hold) in Bolpur Sub-Division under Birbhum Division, PHE Dte. (2nd Call).¿ (Sl. No.7) | 2059/BHM | 10/12/2021 | 60 | RAJKUMAR DAS | 38.89 | 29.29 | 100 | 85
715 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) , SM/06742 | Retrofitting | Payment for Supply of diesel | BP-2023-24-127 | 25/08/2023 | 0 | JAYRAM FILLING STATION | 0.72 | 0 | 0 | 0
716 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) , SM/06742 | Retrofitting | Preparation of Audio clip single of 5 minute aand telecast the same through FM (Air) for a period of 3 month 4 times in a day under Birbhum Diviison PHE Dte. (Sl.No.02) | 1571/BHM | 07/12/2020 | 60 | IMAGIN | 0.89 | 1.77 | 200 | 0
717 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) , SM/06742 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kamarpara & Chella of Daranda w/s Scheme at Illambazar Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (Sl. No.11) | 1425/BHM | 04/11/2020 | 45 | SYED KHORSID ALAM | 17.6 | 31.22 | 200 | 0
718 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Daronda PWSS(Phase-I) , SM/06742 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chella, Ramnagar, Bonovilla, Lakshipur, Daronda, Dhalla, Saldanga, Usurdihi, Ushahar etc. in different locations under Daronda Water Supply Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.1) | 1569/BHM | 26/07/2022 | 60 | HOQUEDAR ALI | 43.32 | 21.01 | 100 | 100
719 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block , SM/07645 | Retrofitting | Providing Tap Connection for Existing School & AWC in Atla PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 273/RSD | 16/07/2021 | 10 | PROLOY KUMAR MONDAL | 0.22 | 0.22 | 100 | 100
720 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block , SM/07645 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in Kabichandrapur letpara area under Habitation under Atla Mouzas of Atla Water Ssupply Scheme (Sl.No.03) |  | 17/03/2021 | 0 | MD NUREL HOQUE. | 4.02 | 0 | 0 | 0
721 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block , SM/07645 | Retrofitting | Sinking of 02 (Two) No 200mm dia.X 36 mtr deep Tube Well with UPVC pipe & strainer for strengthening of Atla W/S scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl.No-35) | 338/RSD | 08/09/2022 | 30 | SUMAN CHOWDHURY | 3.66 | 0 | 0 | 0
722 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block , SM/07645 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in kabichandrapur area under kobichandrapur under Atla mouza under Rampurhat -I block at ATLA WS scheme.(Sl.No.01) | 13/RSD | 11/01/2021 | 30 | SUBODH KR MANDAL | 4.98 | 9.97 | 100 | 100
723 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block , SM/07645 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in kabichandrapur area under kobichandrapur under Atla mouza under Rampurhat -I block at ATLA WS scheme.(Sl.No.02) | 14/RSD | 11/01/2021 | 30 | MUKADDUMUL MOULA | 4.59 | 9.02 | 200 | 100
724 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block , SM/07645 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Atla W/S Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. | 1324/BHM | 16/08/2021 | 60 | BIJOY KUMAR CHOUDHURY | 35.94 | 33.87 | 100 | 99
725 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block , SM/07645 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for providing FHTC at Kabichandrapur (Adibasipara) at Atla Mouzas under Atla PWSS under Rampurhat SubDivision, within Birbhum Division P.H.E Dte. | 09/RSD | 04/01/2022 | 30 | BIJOY KUMAR CHOUDHURY | 4.98 | 4.97 | 100 | 100
726 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block , SM/07645 | Retrofitting | Connection with DI pipe from new Tubewell to CWR for Atla PWSS under Rampurhat Sub-Division, P.H.E Dte. | 68/RSD | 08/02/2022 | 30 | PROLOY KUMAR MONDAL | 0.64 | 0 | 0 | 0
727 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block , SM/07645 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for providing FHTC for Atla Water Supply Scheme at Atla Mouza towards Mollarpur Road, under Rampurhat Sub-Division, within Birbhum Division P.H.E Dte. | 11/RSD | 04/01/2022 | 30 | BIJOY KUMAR CHOUDHURY | 2.92 | 2.89 | 100 | 100
728 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block , SM/07645 | Retrofitting | Additional Laying of Distribution System for strengthening of Atla Water Supply Scheme for Atla Mouza under Rampurhat Sub-Division, within Birbhum Division P.H.E Dte. | 226/RSD | 23/06/2022 | 30 | SUMAN CHOWDHURY | 2.84 | 2.82 | 100 | 100
729 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block , SM/07645 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for providing FHTC for Atla Water Supply Scheme at Atla Mouza Towards Tarapith Roadunder Rampurhat Sub-Division within Birbhum Division P.H.E Dte. | 10/RSD | 04/01/2022 | 30 | BIJOY KUMAR CHOUDHURY | 4.92 | 4.92 | 100 | 100
730 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block , SM/07645 | Retrofitting | Providing FHTC from existing distributin system in Junidpur, Kamdebpur and Atla mouza within Atla w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. | 360/RSD | 28/09/2021 | 30 | PROLOY KUMAR MONDAL | 2.21 | 0 | 0 | 0
731 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block , SM/07645 | Retrofitting | Providing Functional Household Tap connection (FHTC) from existing distribution system in Kabichandrapur under Kabichandrapur Habitation under Atla Mouzas under Rampurhat Sub Division PHE Dte. | 15/RSD | 11/01/2021 | 60 | MD NUREL HOQUE. | 4.02 | 8.05 | 200 | 0
732 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Atla PWSS within Rampurhat-I Block , SM/07645 | Retrofitting | Laying of Distribution System for Atla Water Supply Scheme from Mukti Hotel and Residency to Sri Sri Mohananda Brahamchari Sevasharam at Atla Mouzas under Rampurhat Sub-Division, within Birbhum Division P.H.E. Dte. | 291/RSD | 26/07/2021 | 30 | BIJOY KUMAR CHOUDHURY | 4.83 | 0.43 | 100 | 0
733 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Datababa mazar water supply scheme , SM/10665 | Retrofitting | Extension of distribution pipe line near Nichupara Kabar Sthan, besides of Khokon House, near Imam Saheb and infornt of Gate of Park and all other allied works under Data Baba Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte. (Sl. No. - 03) | 215/BSSD | 21/09/2022 | 15 | AMIT KUMAR ROY | 2.98 | 2.97 | 100 | 100
734 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Datababa mazar water supply scheme , SM/10665 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Data Baba Water Supply Scheme in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte. (2nd Call) | 2509/BHM | 17/11/2022 | 30 | AMIT KUMAR ROY | 38.19 | 38 | 99.5 | 100
735 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Datababa mazar water supply scheme , SM/10665 | Retrofitting | Balance work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Data Baba Water Supply Scheme in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte. | 1720/BHM | 12/05/2023 | 30 | ARPAN PANDIT | 22.34 | 15.57 | 44.66 | 100
736 | BIRBHUM | Birbhum Division | Gaganpur piped water supply scheme. , SM/12691 | New | Material Requisition To Resource Division | 1451/BHM | 25/04/2023 | 0 | Resource Division | 76.79 | 0 | 0 | 0
737 | BIRBHUM | Birbhum Division | Gaganpur piped water supply scheme. , SM/12691 | New | Different works related to water supply scheme at KASHIMNAGAR, KAMARKHUL & GAGANPUR and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3647/BHM | 25/08/2023 | 274 | BENGAL ENGINEERING | 1204.06 | 0 | 0 | 30
738 | BIRBHUM | Bolpur Mechanical | Gaganpur piped water supply scheme. , SM/12691 | New | Providing Electro-mechanical accessories and others for GAGANPUR piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | 2140/Bol.MD | 25/08/2023 | 671 | MONI ELECTRICAL WORKS | 29.63 | 0 | 0 | 60
739 | BIRBHUM | Bolpur Mechanical | Gaganpur piped water supply scheme. , SM/12691 | New | Quotation deposit for empowering Gaganpur Water Supply Scheme P/H - I in Paikar CCC under Bolpur Mechanical Division, PHE Dte. | BP-2024-2025-41 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.13 | 0 | 0 | 0
740 | BIRBHUM | Birbhum Division | Kamdebnala piped water supply scheme. , SM/12694 | New | Material Requisition To Resource Division | 1534/BHM | 26/04/2023 | 0 | Resource Division | 12.86 | 0 | 0 | 0
741 | BIRBHUM | Birbhum Division | Kamdebnala piped water supply scheme. , SM/12694 | New | Different works related to water supply scheme at Kamdebnala & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1302/BHM | 19/04/2023 | 927 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 282.44 | 0 | 0 | 42
742 | BIRBHUM | Bolpur Mechanical | Kamdebnala piped water supply scheme. , SM/12694 | New | WBSEDCL QUOITATION FOR KAMDEBNALA PH NO-I | BP-2023-24-269 | 07/02/2024 | 0 | WBSEDCL | 3.12 | 0 | 0 | 0
743 | BIRBHUM | Bolpur Mechanical | Kamdebnala piped water supply scheme. , SM/12694 | New | Providing Electro-mechanical accessories and others for KAMDEBNALA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 3295/Bol.MD | 29/09/2023 | 795 | M/S. UTTAM KUMAR CHATTERJEE | 25.93 | 0 | 0 | 90
744 | BIRBHUM | Birbhum Division | Majhara piped water supply scheme , SM/12698 | New | Material Requisition To Resource Division | 1492/BHM | 25/04/2023 | 0 | Resource Division | 20.41 | 0 | 0 | 0
745 | BIRBHUM | Bolpur Mechanical | Majhara piped water supply scheme , SM/12698 | New | Supply, delivery and installation of servo motor operated copper wound line voltage corrector for Majhara water supply scheme (Amdol Pump House-I) of Murarai-II Block under Bolpur Mechanical Division, PHE Dte. | 177/BMSD(D) | 18/03/2024 | 30 | NITESH MANAGEMENT | 3.18 | 0 | 0 | 100
746 | BIRBHUM | Birbhum Division | Majhara piped water supply scheme , SM/12698 | New | Different works related to water supply scheme at Majhara & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1301/BHM | 19/04/2023 | 1078 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 281.52 | 0 | 0 | 30
747 | BIRBHUM | Bolpur Mechanical | Majhara piped water supply scheme , SM/12698 | New | Providing Electro-mechanical accessories and others for MAJHARA piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | 2143/Bol.MD | 25/08/2023 | 60 | UNIVERSAL ENTERPRISES | 25.93 | 0 | 0 | 70
748 | BIRBHUM | Bolpur Mechanical | Majhara piped water supply scheme , SM/12698 | New | Supply and installation of manual operated Motor control panel for Majhara water supply scheme (Amdol Pump House-I) of Murarai-II Block under Bolpur Mechanical Division, PHE Dte. | 176/BMSD(D) | 18/03/2024 | 318 | QUAZI NOZRUL ISLAM | 2.66 | 0 | 0 | 100
749 | BIRBHUM | Birbhum Division | SAMSA PIPED WATER SUPPLY SCHEME. , SM/12597 | New | Material Requisition To Resource Division | 1368/BHM | 24/04/2023 | 0 | Resource Division | 37.96 | 0 | 0 | 0
750 | BIRBHUM | Bolpur Mechanical | SAMSA PIPED WATER SUPPLY SCHEME. , SM/12597 | New | New service connection at Samsa PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-24-25-107 | 02/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3 | 0 | 0 | 0
751 | BIRBHUM | Bolpur Mechanical | SAMSA PIPED WATER SUPPLY SCHEME. , SM/12597 | New | New service connection at Samsa PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-24-25-279 | 17/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.3 | 0 | 0 | 0
752 | BIRBHUM | Birbhum Division | SAMSA PIPED WATER SUPPLY SCHEME. , SM/12597 | New | Different works related to water supply scheme at ABHIRAMPUR, BEHIRA, SAMSA & UTTAR BANGAON and its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | 1437/BHM | 25/04/2023 | 820 | ASHOK KUMAR GHOSH | 1446.74 | 0 | 0 | 55
753 | BIRBHUM | Bolpur Mechanical | SAMSA PIPED WATER SUPPLY SCHEME. , SM/12597 | New | Providing Electro-mechanical accessories and others for Samsa & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2096/Bol.MD | 22/08/2023 | 913 | M/S SWAPAN BANERJEE | 28.57 | 0 | 0 | 80
754 | BIRBHUM | Birbhum Division | Dakshin Chandipur Piped Water Supply Scheme. , SM/12685 | New | Material Requisition To Resource Division | 1410/BHM | 24/04/2023 | 0 | Resource Division | 41.76 | 0 | 0 | 0
755 | BIRBHUM | Bolpur Mechanical | Dakshin Chandipur Piped Water Supply Scheme. , SM/12685 | New | Providing Electro-mechanical accessories and others for Dakshin Chandipur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 3307/BOL.MD | 29/09/2023 | 365 | PP CONCERN | 28.24 | 0 | 0 | 50
756 | BIRBHUM | Bolpur Mechanical | Dakshin Chandipur Piped Water Supply Scheme. , SM/12685 | New | New service connection at Dakshin Chandipur PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-24-25-276 | 06/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.1 | 0 | 0 | 0
757 | BIRBHUM | Birbhum Division | Dakshin Chandipur Piped Water Supply Scheme. , SM/12685 | New | Road crossing, repairing & restoration of damage pipe lines & PCC roads, sluice valve chambers including all allied works for Dakshin Chandipur Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | 1638/BHM | 11/06/2025 | 293 | M/S KRIPASINDHU GHOSH & CO. | 43.46 | 0 | 0 | 80
758 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BABUPUR AND OTHER 5 NOS. MOUZAS UNDER SURI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11899 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 152.96 | 88.71 | 92
759 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Belera Phase-II Water Supply Scheme. , SM/12660 | Retrofitting | Allied Functional Household Tap Connection along with laying additional distribution pipeline at different mouzas under Belera Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. | 1304/BHM | 19/04/2023 | 45 | OM ENTERPRISE | 17.33 | 17.31 | 100 | 0
760 | BIRBHUM | Bolpur Mechanical | Majuria Piped Water Supply Scheme. , SM/13632 | New | Providing Electro-mechanical accessories and others for Majuri & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | 3383/Bol.MD | 16/10/2023 | 90 | SATYAJIT GHOSH | 72.19 | 0 | 0 | 0
761 | BIRBHUM | Birbhum Division | Majuria Piped Water Supply Scheme. , SM/13632 | New | Material Requisition To Resource Division | 1397/BHM | 24/04/2023 | 0 | Resource Division | 195.98 | 0 | 0 | 0
762 | BIRBHUM | Birbhum Division | Majuria Piped Water Supply Scheme. , SM/13632 | New | Material Requisition To Resource Division | 3268/BHM | 02/12/2024 | 0 | Resource Division | 15.42 | 0 | 0 | 0
763 | BIRBHUM | Birbhum Division | Majuria Piped Water Supply Scheme. , SM/13632 | New | Sinking of 250 X 200 mm Dia and 125 m deep tubewell, Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 8.00 m X 8.00 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM capacity O.H.R. and respectively, 150 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to MAJURIA & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 2770/BHM | 30/09/2024 | 365 | JALPRAVAHIKA PVT. LTD. | 609.71 | 0 | 0 | 20
764 | BIRBHUM | Birbhum Division | CHAUTI PIPED WATER SUPPLY SCHEME. , SM/12835 | New | Material Requisition To Resource Division | 1573/BHM | 26/04/2023 | 0 | Resource Division | 10.89 | 0 | 0 | 0
765 | BIRBHUM | Birbhum Division | CHAUTI PIPED WATER SUPPLY SCHEME. , SM/12835 | New | Different works related to water supply scheme at Chauti & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 674/BHM | 01/03/2023 | 1127 | QUAZI SIRAJUL ISLAM. | 365.44 | 0 | 0 | 40
766 | BIRBHUM | Bolpur Mechanical | CHAUTI PIPED WATER SUPPLY SCHEME. , SM/12835 | New | Quotation deposit for empowering Chauti P/H-II Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. | BP-2024-2025-75 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.92 | 0 | 0 | 0
767 | BIRBHUM | Bolpur Mechanical | CHAUTI PIPED WATER SUPPLY SCHEME. , SM/12835 | New | Quotation deposit for empowering Chauti P/H-I Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. | BP-2024-2025-76 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.82 | 0 | 0 | 0
768 | BIRBHUM | Birbhum Division | CHAUTI PIPED WATER SUPPLY SCHEME. , SM/12835 | New | Restoration of Roads, pucca drain including Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chember for Chaiti piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | 1594/BHM | 03/06/2025 | 90 | QUAZI SIRAJUL ISLAM | 96.35 | 0 | 0 | 0
769 | BIRBHUM | Bolpur Mechanical | CHAUTI PIPED WATER SUPPLY SCHEME. , SM/12835 | New | Providing Electro-mechanical accessories and others for Chauti PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | 3302/BOL.MD | 29/09/2023 | 671 | MONI ELECTRICAL WORKS | 27.59 | 0 | 0 | 60
770 | BIRBHUM | Birbhum Division | CHAUTI PIPED WATER SUPPLY SCHEME. , SM/12835 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
771 | BIRBHUM | Birbhum Division | Monoharpur Piped Water Supply Scheme. , SM/13511 | New | Material Requisition To Resource Division | 1361/BHM | 24/04/2023 | 0 | Resource Division | 16.8 | 0 | 0 | 0
772 | BIRBHUM | Bolpur Mechanical | Monoharpur Piped Water Supply Scheme. , SM/13511 | New | NEW SERVICE CONNECTION AT MONOHORPUR WATER SUPPLY SCHEME | BP-2024-25-141 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.41 | 0 | 0 | 0
773 | BIRBHUM | Central Drilling | Monoharpur Piped Water Supply Scheme. , SM/13511 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
774 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR DHEKA AND OTHER 21 NOS. MOUZAS UNDER MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11910 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 161.15 | 20.57 | 92
775 | BIRBHUM | Birbhum Division | Kasba Piped Water Supply Scheme. , SM/13713 | New | Material Requisition To Resource Division | 1359/BHM | 24/04/2023 | 0 | Resource Division | 13.67 | 0 | 0 | 0
776 | BIRBHUM | Central Drilling | Kasba Piped Water Supply Scheme. , SM/13713 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
777 | BIRBHUM | Birbhum Division | Kasba Piped Water Supply Scheme. , SM/13713 | New | Different works related to water supply scheme at IKSHUDHARA, KANKALITALA, KASBA & KENDANGAL Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 4139/BHM | 18/10/2023 | 896 | M/S TAPAS KUMAR CHAKRABORTY | 2684.99 | 0 | 0 | 60
778 | BIRBHUM | Birbhum Division | Kasba Piped Water Supply Scheme. , SM/13713 | New | Continuation order against "Hiring of 01(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, PHE. Dte. under Birbhum Division, PHE Dte. For the period of 01.04.2023 to 30.09.2023". For another 06 (Six) months i.e. from 01.10.2024 to 31.03.2025. | 873/BSD | 27/09/2024 | 182 | SK AKRAM HOSSAIN | 0.86 | 0 | 0 | 0
779 | BIRBHUM | Birbhum Division | JIUI PIPED WATER SUPPLY SCHEME. , SM/12902 | New | Material Requisition To Resource Division | 1367/BHM | 24/04/2023 | 0 | Resource Division | 17.14 | 0 | 0 | 0
780 | BIRBHUM | Bolpur Mechanical | JIUI PIPED WATER SUPPLY SCHEME. , SM/12902 | New | Providing Electro-mechanical accessories and others for Jiui & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2087/Bol.MD | 22/08/2023 | 679 | M/S. YOUTH ENGINEERS' ENTERPRISE | 28.76 | 0 | 0 | 50
781 | BIRBHUM | Bolpur Mechanical | JIUI PIPED WATER SUPPLY SCHEME. , SM/12902 | New | WBSEDCL QUIOTATION FOR JIUI PH NO-II | BP-23-24-276 | 15/02/2024 | 0 | WBSEDCL | 5 | 0 | 0 | 0
782 | BIRBHUM | Bolpur Mechanical | JIUI PIPED WATER SUPPLY SCHEME. , SM/12902 | New | WBSEDCL QUOTATION FOR JIUI PH I WS SCHEME | BP-2023-24-295 | 12/03/2024 | 0 | WBSEDCL | 3.79 | 0 | 0 | 0
783 | BIRBHUM | Birbhum Division | JIUI PIPED WATER SUPPLY SCHEME. , SM/12902 | New | Different works related to water supply scheme at DEOASH, JASODA & JIUI and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 1194/BHM | 12/04/2023 | 792 | M/S. JAN MAHAMMAD | 1367.24 | 0 | 0 | 75
784 | BIRBHUM | Birbhum Division | KOGRAM PIPED WATER SUPPLY SCHEME. , SM/12894 | New | Material Requisition To Resource Division | 1572/BHM | 26/04/2023 | 0 | Resource Division | 16.61 | 0 | 0 | 0
785 | BIRBHUM | Bolpur Mechanical | KOGRAM PIPED WATER SUPPLY SCHEME. , SM/12894 | New | Providing Electro-mechanical accessories and others for Kogram PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | 3541/BOL.MD | 30/11/2023 | 60 | A.S.ENTERPRISE | 27.56 | 0 | 0 | 50
786 | BIRBHUM | Bolpur Mechanical | KOGRAM PIPED WATER SUPPLY SCHEME. , SM/12894 | New | WBSEDCL QUOTATION FOR SKOGRAM WS SCHEME | BP-23-24-236 | 29/01/2024 | 0 | WBSEDCL | 2.85 | 0 | 0 | 0
787 | BIRBHUM | Birbhum Division | KOGRAM PIPED WATER SUPPLY SCHEME. , SM/12894 | New | Different works related to water supply scheme at KANIOR, KOGRAM & KUSHIPUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1059/BHM | 31/03/2023 | 915 | SK ALIM | 1229.19 | 0 | 0 | 25
788 | BIRBHUM | Birbhum Division | PHULUR PIPED WATER SUPPLY SCHEME. , SM/12901 | New | Material Requisition To Resource Division | 1416/BHM | 24/04/2023 | 0 | Resource Division | 24.19 | 0 | 0 | 0
789 | BIRBHUM | Bolpur Mechanical | PHULUR PIPED WATER SUPPLY SCHEME. , SM/12901 | New | Providing Electro-mechanical accessories and others for Phulur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2085/Bol.MD | 22/08/2023 | 410 | MASSK ENGINEERING WORKS | 28.91 | 0 | 0 | 55
790 | BIRBHUM | Bolpur Mechanical | PHULUR PIPED WATER SUPPLY SCHEME. , SM/12901 | New | Quotation deposit for Phulur Water Supply Scheme P/H-II in Sainthia CCC under Bolpur Mechanical division, PHE Dte | BP-24-25-284 | 17/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.36 | 0 | 0 | 0
791 | BIRBHUM | Bolpur Mechanical | PHULUR PIPED WATER SUPPLY SCHEME. , SM/12901 | New | WBSEDCL QUIOTATION FOR PHULUR PH NO-I | BP-23-24-275 | 15/02/2024 | 0 | WBSEDCL | 0.53 | 0 | 0 | 0
792 | BIRBHUM | Birbhum Division | PHULUR PIPED WATER SUPPLY SCHEME. , SM/12901 | New | Different works related to water supply scheme at PASCHIM NAOPARA, PHULUR & PURBA SIUR its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | 2262/BHM | 12/07/2023 | 993 | B RAI CONSTRUCTION COMPANY | 1402.44 | 0 | 0 | 45
793 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. , SM/08893 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amdole w/s Scheme (Leftout House Hold) in Nalhati Sub-Division under Birbhum Division, PHE Dte. (Sl. No.5) | 2098/BHM | 16/12/2021 | 60 | MD ABSAR ALI | 94.06 | 94.06 | 100 | 100
794 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. , SM/08893 | Retrofitting | Road crossing under Kalahapur village by adopting Augor Boring method along with pipe carrying structure & other ancillary works for Improvement of AMDOL PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 19/AE/NSD | 17/01/2022 | 30 | MD ABSAR ALI | 4.85 | 0 | 0 | 100
795 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. , SM/08893 | Retrofitting | Extension of pipe line at Kalahapur village of Amdol Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | 490/AE/NSD | 27/09/2021 | 45 | MD ABSAR ALI | 4.52 | 0 | 0 | 100
796 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. , SM/08893 | Retrofitting | ¿Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amdole Water Supply Scheme within Nalhati Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.17) | 1771/BHM | 29/10/2021 | 60 | UJJWAL DAS | 78.86 | 78.86 | 100 | 100
797 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. , SM/08893 | Retrofitting | Road crossing near Bhimpur Health Center by adopting Jack Pushing method for Improvement of AMDOL PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 20/NSD | 17/01/2022 | 30 | UJJWAL DAS | 4.84 | 0 | 0 | 100
798 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. , SM/08893 | Retrofitting | Laying of additional distribution system at Harishpur (JL.No.-60) and its adjoining areas for proposed Improvement of Amdol Piped Water Supply Scheme under Murarai-II Block, under Birbhum Division, PHE Dte. | 536/A/AE/NSD | 08/10/2021 | 45 | UJJWAL DAS | 4.98 | 0 | 0 | 0
799 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. , SM/08893 | Retrofitting | Restoration of PCC Road, damaged by laying of pipe line at different habitations under Narottampur village (JL.No.-63) and its adjoining areas under Amdol PWSS within Nalhati Sub-Division, PHE Dte. | 539/AE/NSD | 08/10/2021 | 15 | TEKNO ENTERPRISE | 4.46 | 0 | 0 | 100
800 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. , SM/08893 | Retrofitting | Restoration of PCC Road, damaged by laying of pipe line at different habitations under Hariapur village (JL.No.-60) and its adjoining areas under Amdol PWSS within Nalhati Sub-Division, PHE Dte. | 536/AE/NSD | 08/10/2021 | 15 | UJJWAL DAS | 4.84 | 0 | 0 | 100
801 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. , SM/08893 | Retrofitting | Restoration of PCC Road, damaged by laying of pipe line at different habitations under Kalahapur village (JL.No.-56) and its adjoining areas under Amdol PWSS within Nalhati Sub-Division, PHE Dte. | 534/AE/NSD | 08/10/2021 | 15 | MD ABSAR ALI | 4.85 | 0 | 0 | 100
802 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. , SM/08893 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amdole under Amdole Water Supply Scheme (Left out House Hold) within Birbhum Division, PHE Dte. (Sl. No.11) | 885/BHM | 22/04/2022 | 60 | KHANDAKAR CONSTRUCTION | 66.42 | 66.11 | 100 | 100
803 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area AMDOLE (PHASE-I) WATER SUPPLY SCHEME of Murarai-II Block under Birbhum Division, PHE Dte. , SM/08893 | Retrofitting | Extension of pipeline of different left out habitations including FHTC along with 1 no. Pump House as boosting of water supply of Amdol water supply scheme under Nalhati Sub-Division, within Birbhum Division PHE Dte (Sl. No.7) | 2780/BHM | 14/12/2022 | 900 | KAMIRUL SK AND CO | 211.6 | 45.93 | 100 | 75
804 | BIRBHUM | Bolpur Mechanical | Sandhyajol Piped Water Supply Scheme , SM/13981 | New | Providing Electro-mechanical accessories and others for Sandhyajol PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 2228/Bol.MD | 12/09/2023 | 60 | P. K. ENGINEERING | 44.41 | 0 | 0 | 0
805 | BIRBHUM | Birbhum Division | Sandhyajol Piped Water Supply Scheme , SM/13981 | New | Continuation Work Order for Preparation & Submission of DPR for (Sandhyajol) Water Supply Scheme under Rampurhat-II Development Block. | 241/RSD | 13/07/2022 | 45 | ECO CARE | 4.73 | 0 | 0 | 100
806 | BIRBHUM | Birbhum Division | Sandhyajol Piped Water Supply Scheme , SM/13981 | New | Material Requisition To Resource Division | 1568/BHM | 26/04/2023 | 0 | Resource Division | 45.61 | 0 | 0 | 0
807 | BIRBHUM | Birbhum Division | Sandhyajol Piped Water Supply Scheme , SM/13981 | New | Material Requisition To Resource Division | 2492/BHM | 03/09/2024 | 0 | Resource Division | 12.42 | 0 | 0 | 0
808 | BIRBHUM | Birbhum Division | Sandhyajol Piped Water Supply Scheme , SM/13981 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR , Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at SANDHYAJOL & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 2224/BHM | 12/08/2024 | 730 | SUNIL RABI DAS | 386.48 | 0 | 0 | 20
809 | BIRBHUM | Birbhum Division | Parsundi Piped Water Supply Scheme , SM/14855 | New | Preparation & Submission of DPR for Parsundi & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 143/BSSD | 21/07/2022 | 45 | RADIANT | 2.9 | 0 | 0 | 100
810 | BIRBHUM | Birbhum Division | Parsundi Piped Water Supply Scheme , SM/14855 | New | Withdrawing and re-sinking for 02 nos. working 200mm dia. Tubewell of 10 m depth with horizontal strainer on the river Bed of Ajoy under Parsundi Mini Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division P.H.E. Dte. | 654/BHM | 20/02/2024 | 45 | NEEL ENTERPRISE | 2.87 | 0 | 0 | 100
811 | BIRBHUM | Birbhum Division | Parsundi Piped Water Supply Scheme , SM/14855 | New | Material Requisition To Resource Division | 430/BHM | 01/02/2024 | 0 | Resource Division | 131.6 | 0 | 0 | 0
812 | BIRBHUM | Birbhum Division | Parsundi Piped Water Supply Scheme , SM/14855 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
813 | BIRBHUM | Birbhum Division | Parsundi Piped Water Supply Scheme , SM/14855 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
814 | BIRBHUM | Birbhum Division | Hazaripur Piped Water Supply Scheme , SM/14679 | New | Preparation and submission of DPR for (Hazaripur) Water Supply Scheme under Nalhati-II Development Block. | 222/AE/NSD | 18/04/2022 | 45 | MS SOBHA AND CO | 4.71 | 0 | 0 | 100
815 | BIRBHUM | Birbhum Division | Hazaripur Piped Water Supply Scheme , SM/14679 | New | Material Requisition To Resource Division | 2173/BHM | 23/06/2023 | 0 | Resource Division | 25.03 | 0 | 0 | 0
816 | BIRBHUM | Bolpur Mechanical | Hazaripur Piped Water Supply Scheme , SM/14679 | New | Supply and Delivery of Electro mechanical Accessories for Hazaripur PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | 3779/BOL.MD | 12/09/2024 | 30 | KAMAKHYA ENTERPRISE | 28.62 | 0 | 0 | 100
817 | BIRBHUM | Birbhum Division | Hazaripur Piped Water Supply Scheme , SM/14679 | New | Different works for works related to water supply scheme at HAZARIPUR, Beloa & its adjoining mouzas water supply scheme within NALHATI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3425/BHM | 02/08/2023 | 883 | M/S NATIONAL CONSTRUCTION | 1099.34 | 0 | 0 | 15
818 | BIRBHUM | Bolpur Mechanical | Hazaripur Piped Water Supply Scheme , SM/14679 | New | Providing Electro-mechanical accessories and others for Hazaripur PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | 2136/Bol.MD | 25/08/2023 | 554 | SINHA ELECTRICALS | 45.52 | 18.35 | 40.32 | 30
819 | BIRBHUM | Birbhum Division | Hazaripur Piped Water Supply Scheme , SM/14679 | New | Restoration of Roads, pucca drain including Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Hazaripur piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. | 2064/BHM | 12/08/2025 | 90 | M/S NATIONAL CONSTRUCTION | 61.62 | 0 | 0 | 0
820 | BIRBHUM | Birbhum Division | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District , SM/14016 | New | Sinking of 02 Nos Tube wells 200 mm dia depth 36.0 mm each depth, fitted with PVC pipe and fiber glass Strainer at Salbani River bank for Khadamara PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 448/RSD | 08/12/2022 | 30 | ANKITA CHAKRABORTY | 4.68 | 0 | 0 | 100
821 | BIRBHUM | Bolpur Mechanical | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District , SM/14016 | New | WBSEDCL QUOATATION FOR kHENDAMARA WS SCHEME | BP-2023-2024-54 | 17/07/2023 | 0 | WBSEDCL | 3.39 | 0 | 0 | 0
822 | BIRBHUM | Birbhum Division | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District , SM/14016 | New | Laying of Rising Main , Distribution system and Providing FHTC including all allied Works for Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat - I Block within Birbhum District. (Sl. No.8) | 2689/BHM | 06/12/2022 | 60 | M/S MD AMINUL ISLAM | 98.43 | 65.77 | 66.82 | 90
823 | BIRBHUM | Bolpur Mechanical | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District , SM/14016 | New | Providing and Installation of Submersible pumping machinaries at newly sunk Tube Wells and allied works at Khedamara PWSS Block-Rampurhat-I under Bolpur Mechanical Division. | 1501/Bol.MD | 17/07/2023 | 60 | MUKHERJEE ART CENTRE | 19.28 | 0 | 0 | 80
824 | BIRBHUM | Birbhum Division | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District , SM/14016 | New | Sinking of 01 nos. additional Tubewell, 200mm dia all through 120 mt. deep tubewell with Rising Main along with Construction of Switch Room 3.60 m X 3.0 m with Sanitary arrangement and balance FHTC for Khedamara PWSS under Rampurhat Sub-Division under Birbhum Division, PHE Dte. | 1028/BHM | 15/03/2024 | 45 | M/S MD AMINUL ISLAM | 40.81 | 0 | 0 | 0
825 | BIRBHUM | Birbhum Division | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District , SM/14016 | New | Construction of Switch Room size 5.40 mtr. X 3.65 mtr with Sanitary and water supply arrangement For Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat Sub-Division, P.H.E. Dte. | 447/RSD | 08/12/2022 | 45 | SUBHRANIL DAS | 4.98 | 4.82 | 100 | 0
826 | BIRBHUM | Birbhum Division | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District , SM/14016 | New | Sinking of Rig Bored Tube well by DTH method of drilling (125 mm X 115 mm) dia including connecting main for Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District under Rampurhat Sub-Division, Birbhum Division, P.H.E Dte | 2268/BHM | 13/07/2023 | 30 | JAYANTA BARAL | 4.53 | 0 | 0 | 100
827 | BIRBHUM | Bolpur Mechanical | Piped Water Supply Scheme for Khedamara Mouza (Paikpara Village) under Rampurhat -I Block within Birbhum District , SM/14016 | New | WBSEDCL QUOTATION FOR UTTAR BAKHEDAMARA WS SCHEME | BP-23-24-196 | 14/12/2023 | 0 | WBSEDCL | 1.96 | 0 | 0 | 0
828 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Sekhpur Phase-II Water Supply Scheme. , SM/13374 | Retrofitting | Retrofitting works for Providing Balance Functional Household Tap Connection (FHTC) by Sinking of 2 nos. additional Tubewells at Rukumpur & Dumra mouza (200mm dia all through & 150 Mtr Deep) along with Connecting Line, Boundary wall & related works for Sekhpur Piped Water Supply Scheme under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 1027/BHM | 15/03/2024 | 451 | GOLAM RASUL | 86.37 | 0 | 0 | 0
829 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR TALA AND OTHER 25 NOS. MOUZAS UNDER LABPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/14039 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 81.93 | 8.9 | 92
830 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR CHANDANPUR AND OTHER 5 NOS. MOUZAS UNDER MURARAI-I & NALHATI-I BLOCKS UNDER BIRBHUM DIVISION, PHE DTE. , SM/14043 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 0 | 92
831 | BIRBHUM | Birbhum Division | ANGORA PIPED WATER SUPPLY SCHEME , SM/13971 | New | Material Requisition To Resource Division | 1535/BHM | 26/04/2023 | 0 | Resource Division | 14.49 | 0 | 0 | 0
832 | BIRBHUM | Birbhum Division | ANGORA PIPED WATER SUPPLY SCHEME , SM/13971 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for ANGORA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte". (PART - A) | 215/BSD | 31/05/2022 | 180 | RADIANT | 4.94 | 0 | 0 | 100
833 | BIRBHUM | Birbhum Division | ANGORA PIPED WATER SUPPLY SCHEME , SM/13971 | New | Material Requisition To Resource Division | 3266/BHM | 02/12/2024 | 0 | Resource Division | 11.22 | 0 | 0 | 0
834 | BIRBHUM | Central Drilling | ANGORA PIPED WATER SUPPLY SCHEME , SM/13971 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
835 | BIRBHUM | Birbhum Division | ANGORA PIPED WATER SUPPLY SCHEME , SM/13971 | New | Different works related to water supply scheme at ANGORA PIPED WATER SUPPLY SCHEME (TSM/016091) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte. | 2599/BHM | 10/09/2024 | 365 | CHIRANJIB DAS | 419.76 | 0 | 0 | 25
836 | BIRBHUM | Bolpur Mechanical | ANGORA PIPED WATER SUPPLY SCHEME , SM/13971 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Angora & Charkalgram Water supply Scheme, Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | 4537/BOL.MD | 20/12/2024 | 285 | MENAKA ENTERPRISE | 73.34 | 0 | 0 | 100
837 | BIRBHUM | Birbhum Division | Banhat Piped Water Supply Scheme. , SM/14029 | New | Material Requisition To Resource Division | 1592/BHM | 26/04/2023 | 0 | Resource Division | 18.13 | 0 | 0 | 0
838 | BIRBHUM | Birbhum Division | Banhat Piped Water Supply Scheme. , SM/14029 | New | Different works related to water supply scheme at BANHAT & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 904/BHM | 22/03/2023 | 683 | PRALAY ROY | 331.4 | 0 | 0 | 38
839 | BIRBHUM | Birbhum Division | Banhat Piped Water Supply Scheme. , SM/14029 | New | Material Requisition To Resource Division | 230/BHM | 24/01/2024 | 0 | Resource Division | 0.12 | 0 | 0 | 0
840 | BIRBHUM | Bolpur Mechanical | Banhat Piped Water Supply Scheme. , SM/14029 | New | WBSEDCL QUOTATION FOR BONHAT W S P H NO I WS SCHEME | BP-23-24-249 | 29/01/2024 | 0 | WBSEDCL | 3.53 | 0 | 0 | 0
841 | BIRBHUM | Bolpur Mechanical | Banhat Piped Water Supply Scheme. , SM/14029 | New | QUOTATION FOR BANHAT PH-II RAMPURHAT-I BLOCK | BP-24-25-06 | 09/04/2024 | 0 | WBSEDCL | 3.23 | 0 | 0 | 0
842 | BIRBHUM | Bolpur Mechanical | Banhat Piped Water Supply Scheme. , SM/14029 | New | Providing Electro-mechanical accessories and others for Banhat & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 1750/Bol.MD | 27/07/2023 | 614 | PADMA ENGINEERING CO. | 27.7 | 0 | 0 | 100
843 | BIRBHUM | Birbhum Division | GOALDIHI PIPED WATER SUPPLY SCHEME , SM/15528 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for GOALDIHI Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 110/BSD | 22/03/2022 | 90 | RADIANT | 3.27 | 0 | 0 | 100
844 | BIRBHUM | Birbhum Division | GOALDIHI PIPED WATER SUPPLY SCHEME , SM/15528 | New | Material Requisition To Resource Division | 1479/BHM | 25/04/2023 | 0 | Resource Division | 6.64 | 0 | 0 | 0
845 | BIRBHUM | Birbhum Division | GOALDIHI PIPED WATER SUPPLY SCHEME , SM/15528 | New | Construction of 150 Cum. capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, laying of Rising Main ,Distribution System with FHTC and different works related to GOALDIHI PIPED WATER SUPPLY SCHEME (TSM/016090) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | 2317/BHM | 21/08/2024 | 365 | DILIP KUMAR MONDAL | 333.62 | 0 | 0 | 0
846 | BIRBHUM | Bolpur Mechanical | GOALDIHI PIPED WATER SUPPLY SCHEME , SM/15528 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Goaldihi WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | 4523/BOL.MD | 20/12/2024 | 120 | SATYAJIT GHOSH | 75.08 | 0 | 0 | 0
847 | BIRBHUM | Birbhum Division | GOALDIHI PIPED WATER SUPPLY SCHEME , SM/15528 | New | Material Requisition To Resource Division | 2482/BHM | 03/09/2024 | 0 | Resource Division | 6.42 | 0 | 0 | 0
848 | BIRBHUM | Central Drilling | GOALDIHI PIPED WATER SUPPLY SCHEME , SM/15528 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
849 | BIRBHUM | Birbhum Division | PARKUTA PIPED WATER SUPPLY SCHEME , SM/14959 | New | Continuation Work Order for Preparation & Submission of DPR for (Perkuta) Water Supply Scheme under Rampurhat-II Development Block. | 281/RSD | 24/08/2022 | 45 | ECO CARE | 2.18 | 0 | 0 | 100
850 | BIRBHUM | Birbhum Division | PARKUTA PIPED WATER SUPPLY SCHEME , SM/14959 | New | Material Requisition To Resource Division | 1445/BHM | 25/04/2023 | 0 | Resource Division | 7.01 | 0 | 0 | 0
851 | BIRBHUM | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME , SM/14959 | New | Providing Electro-mechanical accessories and others for Parkuta PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 2226/Bol.MD | 12/09/2023 | 565 | SINHA ELECTRICALS | 45.18 | 0 | 0 | 90
852 | BIRBHUM | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME , SM/14959 | New | Operation and Guarding of pumping machinery and others at Parkuta Piped Water supply Scheme (Pump House No-I(Block- Rampurhat-II) under Bolpur Mechanical Division,P.H.E Dte. | 1090./AE-III | 29/07/2024 | 31 | STANDARD ELECTRICALS | 0.3 | 0 | 0 | 0
853 | BIRBHUM | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME , SM/14959 | New | Operation and Guarding of pumping machinery and others at Parkuta Piped Water supply Scheme (Pump House No-II(Block- Rampurhat-II) under Bolpur Mechanical Division,P.H.E Dte. | 1091./AE-III | 29/07/2024 | 31 | STANDARD ELECTRICALS | 0.3 | 0 | 0 | 0
854 | BIRBHUM | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME , SM/14959 | New | Supply and Delivery of Sub-Mersible Pumping Machineries inconection with Providing Electro-mechanical accessories and others for Parkuta PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 686./AE-III | 08/04/2024 | 14 | SINHA ELECTRICALS | 1.74 | 0 | 0 | 100
855 | BIRBHUM | Birbhum Division | PARKUTA PIPED WATER SUPPLY SCHEME , SM/14959 | New | Material Requisition To Resource Division | 221/BHM | 24/01/2024 | 0 | Resource Division | 2.46 | 0 | 0 | 0
856 | BIRBHUM | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME , SM/14959 | New | wbsedcl quotation money for parkuta pwss | BP-23-24-150 | 04/12/2023 | 0 | WBSEDCL | 3.99 | 0 | 0 | 0
857 | BIRBHUM | Bolpur Mechanical | PARKUTA PIPED WATER SUPPLY SCHEME , SM/14959 | New | WBSEDCL QUOTATION FOR PARKUTA P H NO.II WS SCHEME | BP-23-24-279 | 20/02/2024 | 0 | WBSEDCL | 4.98 | 0 | 0 | 0
858 | BIRBHUM | Birbhum Division | PARKUTA PIPED WATER SUPPLY SCHEME , SM/14959 | New | Different works related to water supply scheme at PARKUTA & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1341/BHM | 20/04/2023 | 183 | KAZI EMDADUL HAQUE | 118.27 | 0 | 0 | 90
859 | BIRBHUM | Birbhum Division | Majhkanda Piped Water Supply Scheme. , SM/14896 | New | Material Requisition To Resource Division | 1597/BHM | 26/04/2023 | 0 | Resource Division | 13.24 | 0 | 0 | 0
860 | BIRBHUM | Bolpur Mechanical | Majhkanda Piped Water Supply Scheme. , SM/14896 | New | Providing Electro-mechanical accessories and others for Majhkanda & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 3527/Bol.MD | 29/11/2023 | 60 | SUBHRA ENTERPRISE | 27.83 | 0 | 0 | 30
861 | BIRBHUM | Birbhum Division | Majhkanda Piped Water Supply Scheme. , SM/14896 | New | Sinking of 250 X 150 mm Dia tubewell Drilling by Direct Rotary method (Two nos), Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Majkhanda & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 2226/BHM | 12/08/2024 | 365 | SUNIL RABI DAS | 518.93 | 0 | 0 | 0
862 | BIRBHUM | Birbhum Division | Majhkanda Piped Water Supply Scheme. , SM/14896 | New | Material Requisition To Resource Division | 2489/BHM | 03/09/2024 | 0 | Resource Division | 16.69 | 0 | 0 | 0
863 | BIRBHUM | Birbhum Division | Singari Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/14208 | New | Continuation Work Order for Preparation & Submission of DPR for (Singari) Water Supply Scheme under Mayureswar-II Development Block. | 222/RSD | 23/06/2022 | 45 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 0 | 100
864 | BIRBHUM | Birbhum Division | Singari Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/14208 | New | Material Requisition To Resource Division | 1503/BHM | 25/04/2023 | 0 | Resource Division | 4.08 | 0 | 0 | 0
865 | BIRBHUM | Bolpur Mechanical | Singari Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/14208 | New | Providing Electro-mechanical accessories and others for Singari PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | 3276/Bol.MD | 29/09/2023 | 60 | PADMA ENGINEERING CO. | 33.06 | 0 | 0 | 30
866 | BIRBHUM | Birbhum Division | Singari Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/14208 | New | Material Requisition To Resource Division | 2443/BHM | 30/08/2024 | 0 | Resource Division | 5.24 | 0 | 0 | 0
867 | BIRBHUM | Birbhum Division | Singari Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division. , SM/14208 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 150 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection, related to water supply scheme at Singari & its adjoining mouzas water supply scheme within Mayureswar-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | 2105/BHM | 29/07/2024 | 365 | KAZI EMDADUL HAQUE | 270.02 | 0 | 0 | 30
868 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS , SM/06738 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Uttar Narayanpur, Kurula Ambha of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-A) | 1178 /BHM | 21/09/2020 | 60 | SUNIL RABI DAS | 41.99 | 37.91 | 200 | 79
869 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS , SM/06738 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Mara Basahar, Jagadispur of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-B) | 1179 /BHM | 21/09/2020 | 60 | SANJUKTA ENGINEERS | 32.72 | 56.7 | 184.88 | 100
870 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS , SM/06738 | Retrofitting | Construction of supporting arrangement for Solar pump at Uttar Narayanpur under Rampurhat Sub- division PHE Dte. | 18/RSD | 04/01/2022 | 30 | SHIB GANGA CONSTRUCTION | 1.54 | 0 | 0 | 100
871 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS , SM/06738 | Retrofitting | Additional Laying of UPVC Pipe line for providing FHTC at Kaluha, Dighuli & Malpara Habitations under Kaluha PWSS under Rampurhat Sub- Division, P.H.E. Dte. | 372/RSD | 28/09/2021 | 30 | PULAK KUMAR PAL | 3.4 | 3.4 | 100 | 100
872 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS , SM/06738 | Retrofitting | Additional Laying of UPVC Pipe line for providing FHTC at Jagadishpur & Marbasahar village under Kaluha PWSS within Birbhum Division, P.H.E. Dte. (Sl. No.3) | 2005/BHM | 08/12/2021 | 60 | SANJUKTA ENGINEERS | 6.82 | 0 | 0 | 50
873 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Kalhua PWSS , SM/06738 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kaluha, Malpara of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.6) | 1240/BHM | 28/09/2020 | 60 | PULAK KUMAR PAL | 38.12 | 69.79 | 200 | 0
874 | BIRBHUM | Birbhum Division | Shrirampur Piped Water Supply Scheme (Khoyrasole Block) , SM/16272 | New | Preparation & Submission of DPR for Srirampur & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 69/BSSD | 21/04/2022 | 45 | RADIANT | 1.95 | 0 | 0 | 100
875 | BIRBHUM | Birbhum Division | Shrirampur Piped Water Supply Scheme (Khoyrasole Block) , SM/16272 | New | Material Requisition To Resource Division | 431/BHM | 01/02/2024 | 0 | Resource Division | 27.12 | 0 | 0 | 0
876 | BIRBHUM | Birbhum Division | Shrirampur Piped Water Supply Scheme (Khoyrasole Block) , SM/16272 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
877 | BIRBHUM | Birbhum Division | Shrirampur Piped Water Supply Scheme (Khoyrasole Block) , SM/16272 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
878 | BIRBHUM | Birbhum Division | Mayandal Piped Water Supply Scheme , SM/16273 | New | Preparation & Submission of DPR for Maynadal & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 102/BSSD | 17/06/2022 | 45 | RADIANT | 1.22 | 0 | 0 | 100
879 | BIRBHUM | Birbhum Division | Mayandal Piped Water Supply Scheme , SM/16273 | New | Material Requisition To Resource Division | 423/BHM | 01/02/2024 | 0 | Resource Division | 27.12 | 0 | 0 | 0
880 | BIRBHUM | Birbhum Division | Mayandal Piped Water Supply Scheme , SM/16273 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
881 | BIRBHUM | Birbhum Division | Mayandal Piped Water Supply Scheme , SM/16273 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
882 | BIRBHUM | Bolpur Mechanical | Solarisation for NET metering of different PWSS at different Blocks under Bolpur Mechanical Division,PHED , SM/16381 | IOT | Solarization for NET metering of 18 Nos. PWSS at different blocks under Bolpur Mechanical Division, PHE Dte | 1134/Bol.MD | 14/06/2023 | 183 | PERFECT RENEWABLE AGENCY | 107.85 | 0 | 0 | 100
883 | BIRBHUM | Bolpur Mechanical | Chormara Piped Water Supply Scheme. , SM/14030 | New | Providing Electro-mechanical accessories and others for Chormara PWSS at Suri - I Block under Bolpur Mechanical Division PHE Dte. | 2103/BOL.MD. | 22/08/2023 | 60 | RMD TRADING | 27.44 | 0 | 0 | 0
884 | BIRBHUM | Birbhum Division | Chormara Piped Water Supply Scheme. , SM/14030 | New | Material Requisition To Resource Division | 1380/BHM | 24/04/2023 | 0 | Resource Division | 13.47 | 0 | 0 | 0
885 | BIRBHUM | Bolpur Mechanical | Chormara Piped Water Supply Scheme. , SM/14030 | New | Lowering of 5HP Submersible Pumpining Machinery at nwely yield Tube Well and other allied works at Purba Bankathi water supply scheme (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. | 1675./AE-III | 24/10/2024 | 21 | SATYAJIT GHOSH | 2.67 | 0 | 0 | 100
886 | BIRBHUM | Birbhum Division | Chormara Piped Water Supply Scheme. , SM/14030 | New | Different works for CHORMARA & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1878/BHM | 31/05/2023 | 794 | SPIRIT ENGINEERS CO OP SOCIETY LTD | 307.6 | 0 | 0 | 15
887 | BIRBHUM | Bolpur Mechanical | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME , SM/18514 | New | Providing Electro-mechanical accessories and others for Bara Kartik Chungri PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 3597/Bol.MD | 08/12/2023 | 60 | A. G. ENTERPRISE | 55.74 | 0 | 0 | 0
888 | BIRBHUM | Birbhum Division | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME , SM/18514 | New | Material Requisition To Resource Division | 1515/BHM | 26/04/2023 | 0 | Resource Division | 112.15 | 0 | 0 | 0
889 | BIRBHUM | Birbhum Division | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME , SM/18514 | New | Different works related to water supply scheme at Madhupur, Khamedda & Bara-Karttikchungri and its adjoining mouzas water supply scheme within Rampurhat-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte.(2nd Call) | 4163/BHM | 30/10/2023 | 560 | M/S ASHA CONSTRUCTION | 1089.94 | 0 | 0 | 40
890 | BIRBHUM | Bolpur Mechanical | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME , SM/18514 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Wells and allieds works at Bara Kartik Chungri Piped Water Supply Scheme, Block-Rampurhat-II under Bolpur Mechanical Division. | 3782/BOL.MD | 12/09/2024 | 30 | ORIENTAL ENGINEERING CO. | 24.94 | 0 | 0 | 0
891 | BIRBHUM | Birbhum Division | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME , SM/18514 | New | Continuation Work Order for Preparation & Submission of DPR for (BARA KARTIK CHUNGRI) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | 297/RSD | 07/09/2022 | 45 | ECO CARE | 3.13 | 0 | 0 | 100
892 | BIRBHUM | Birbhum Division | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME , SM/18514 | New | Continuation Work Order for Preparation & Submission of DPR for (BARA KARTIK CHUNGRI) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | 417/RSD | 18/10/2022 | 45 | ECO CARE | 2.91 | 0 | 0 | 100
893 | BIRBHUM | Birbhum Division | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME , SM/18514 | New | Continuation Work Order for Preparation & Submission of DPR for (BARA KARTIK CHUNGRI) Water Supply Scheme (Part-C) under Rampurhat-II Development Block. | 439/RSD | 29/11/2022 | 45 | ECO CARE | 1.82 | 0 | 0 | 100
894 | BIRBHUM | Birbhum Division | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME , SM/18514 | New | Material Requisition To Resource Division | 226/BHM | 24/01/2024 | 0 | Resource Division | 3.7 | 0 | 0 | 0
895 | BIRBHUM | Bolpur Mechanical | BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME , SM/18514 | New | WBSEDCL QUOTATION MONEY FOR BARA KARTIK CHUNGRI PIPED WATER SUPPLY SCHEME | BP-23-24-223 | 15/01/2024 | 0 | WBSEDCL | 16.88 | 0 | 0 | 0
896 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR NAYIT AND OTHER 3 NOS. MOUZAS UNDER MURARAI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11907 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 0 | 92
897 | BIRBHUM | Bolpur Mechanical | KANAIPUR PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT , SM/18489 | New | Providing Submersible pumping machineries and other electromechanical equipments and installation at KANAIPUR PWSS under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | 404/Bol.MD | 07/03/2024 | 45 | M. S. ENTERPRISE | 29 | 0 | 0 | 70
898 | BIRBHUM | Bolpur Mechanical | KANAIPUR PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT , SM/18489 | New | Providing Electro-mechanical accessories and others for Kanaipur PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte | 3475/Bol.MD | 07/11/2023 | 601 | SINHA ELECTRICALS | 57.22 | 0 | 0 | 80
899 | BIRBHUM | Birbhum Division | KANAIPUR PIPED WATER SUPPLY SCHEME OF MAYURESWAR-I BLOCK UNDER BIRBHUM DISTRICT , SM/18489 | New | Different works related to water supply scheme at BIRCHANDRAPUR, ASURLAYA, BARATURIGRAM & KANAIPUR and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | 505/BHM | 05/02/2024 | 603 | B RAI CONSTRUCTION COMPANY | 2071.77 | 0 | 0 | 20
900 | BIRBHUM | Birbhum Division | PAIKPARA WATER SUPPLY SCHEME. , SM/12836 | New | Material Requisition To Resource Division | 1415/BHM | 24/04/2023 | 0 | Resource Division | 6.36 | 0 | 0 | 0
901 | BIRBHUM | Bolpur Mechanical | PAIKPARA WATER SUPPLY SCHEME. , SM/12836 | New | Providing Electro-mechanical accessories and others for Paikpara PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | 3538/BOL.MD | 30/11/2023 | 549 | BIRBHUM ELECTRIC WORKS | 27.38 | 0 | 0 | 70
902 | BIRBHUM | Birbhum Division | PAIKPARA WATER SUPPLY SCHEME. , SM/12836 | New | Hiring of SWIFT DZIRE (diesel) registered luxury car for the office of the Assistant Engineer, Nalhati Sub-Division P.H.E. Dte. for 24 hours service including Driver and the cost of fuel & lubricants as per terms & condition with effect from 01.04.2024 to 30.09.2024. | 57/NSD | 14/03/2024 | 183 | JOY CHAND MAL | 0.86 | 0 | 0 | 0
903 | BIRBHUM | Bolpur Mechanical | PAIKPARA WATER SUPPLY SCHEME. , SM/12836 | New | New service connection at Paikpara PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-2023-24-314 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.79 | 0 | 0 | 0
904 | BIRBHUM | Bolpur Mechanical | PAIKPARA WATER SUPPLY SCHEME. , SM/12836 | New | New service connection at Paikpara PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-2023-24-313 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.94 | 0 | 0 | 0
905 | BIRBHUM | Bolpur Mechanical | PAIKPARA WATER SUPPLY SCHEME. , SM/12836 | New | WBSEDCL QUOTATION FOR PAIKPARA W S P H NO II WS SCHEME | BP-23-24-244 | 29/01/2024 | 0 | WBSEDCL | 0.23 | 0 | 0 | 0
906 | BIRBHUM | Bolpur Mechanical | PAIKPARA WATER SUPPLY SCHEME. , SM/12836 | New | WBSEDCL QUOTATION FOR PAIKPARA W S P H NO I WS SCHEME | BP-23-24-243 | 29/01/2024 | 0 | WBSEDCL | 6.08 | 0 | 0 | 0
907 | BIRBHUM | Birbhum Division | PAIKPARA WATER SUPPLY SCHEME. , SM/12836 | New | Different works related to water supply scheme at MADHURA & PAIKPARA PWSS its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 1173/BHM | 12/04/2023 | 995 | SK ABDUL HALIM | 921.73 | 0 | 0 | 90
908 | BIRBHUM | Birbhum Division | BANGJITA PIPED WATER SUPPLY SCHEME. , SM/12829 | New | Material Requisition To Resource Division | 1372/BHM | 24/04/2023 | 0 | Resource Division | 15.09 | 0 | 0 | 0
909 | BIRBHUM | Bolpur Mechanical | BANGJITA PIPED WATER SUPPLY SCHEME. , SM/12829 | New | Providing Electro-mechanical accessories and others for Bangjita & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2089/Bol.MD | 22/08/2023 | 60 | INDTECH ASSOCIATES | 28.7 | 0 | 0 | 50
910 | BIRBHUM | Bolpur Mechanical | BANGJITA PIPED WATER SUPPLY SCHEME. , SM/12829 | New | WBSEDCL QUOTATION BANGJITA PIPED WATER SUPPLY SCHEME. | BP-23-24-277 | 15/02/2024 | 0 | WBSEDCL | 5.41 | 0 | 0 | 0
911 | BIRBHUM | Bolpur Mechanical | BANGJITA PIPED WATER SUPPLY SCHEME. , SM/12829 | New | Quotation deposit for Banjita Water Supply Scheme P/H-II in Suri East CCC under Bolpur Mechanical division, PHE Dte. | BP-24-25-271 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.28 | 0 | 0 | 0
912 | BIRBHUM | Birbhum Division | BANGJITA PIPED WATER SUPPLY SCHEME. , SM/12829 | New | Different works related to water supply scheme at BHALIAN, BANGJITA & BIRSINGHA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 1258/BHM | 17/04/2023 | 806 | NAUTANDAS AND CO | 1377.28 | 0 | 0 | 35
913 | BIRBHUM | Birbhum Division | Beloa Piped Water Supply Scheme , SM/18522 | New | Preparation and submission of DPR for (Beloa) Water Supply Scheme under Nalhati-II Development Block. | 219/AE/NSD | 18/04/2022 | 45 | MS SOBHA AND CO | 4.92 | 0 | 0 | 100
914 | BIRBHUM | Birbhum Division | Beloa Piped Water Supply Scheme , SM/18522 | New | Material Requisition To Resource Division | 1511/BHM | 26/04/2023 | 0 | Resource Division | 55.88 | 0 | 0 | 0
915 | BIRBHUM | Bolpur Mechanical | Beloa Piped Water Supply Scheme , SM/18522 | New | Supply and Delivery of Valves, Cetrifugal Pumping Machineries and allied accessories for Beloa PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | 3781/BOL.MD | 12/09/2024 | 30 | SATYAJIT GHOSH | 32.39 | 0 | 0 | 0
916 | BIRBHUM | Bolpur Mechanical | Beloa Piped Water Supply Scheme , SM/18522 | New | Quotation for new service connection at Beloa TW No-III (Block-Nalhati-II) | BP-24-25-12 | 25/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.38 | 0 | 0 | 0
917 | BIRBHUM | Bolpur Mechanical | Beloa Piped Water Supply Scheme , SM/18522 | New | WBSEDCL QUOTATION FOR BELOA P H .II WS SCHEME | BP-23-24-161 | 15/01/2024 | 0 | WBSEDCL | 3.73 | 0 | 0 | 0
918 | BIRBHUM | Bolpur Mechanical | Beloa Piped Water Supply Scheme , SM/18522 | New | WBSEDCL QUOTATION FOR BELOA WS SCHEME | BP-23-24-231 | 15/01/2024 | 0 | WBSEDCL | 4.7 | 0 | 0 | 0
919 | BIRBHUM | Birbhum Division | Beloa Piped Water Supply Scheme , SM/18522 | New | Different works for works related to water supply scheme at HAZARIPUR, Beloa & its adjoining mouzas water supply scheme within NALHATI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3425/BHM | 02/08/2023 | 883 | M/S NATIONAL CONSTRUCTION | 1099.34 | 0 | 0 | 15
920 | BIRBHUM | Bolpur Mechanical | Beloa Piped Water Supply Scheme , SM/18522 | New | Providing Electro-mechanical accessories and others for Beloa PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | 2135/Bol.MD | 25/08/2023 | 554 | QUAZI NOZRUL ISLAM | 56.05 | 0 | 0 | 40
921 | BIRBHUM | Birbhum Division | Beloa Piped Water Supply Scheme , SM/18522 | New | Restoration of Roads, pucca drain including Jack pushing & Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Beloa piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | 2135/BHM | 18/08/2025 | 180 | M/S S. CHOUDHURY | 53.37 | 0 | 0 | 70
922 | BIRBHUM | Birbhum Division | Retrofitting works of Kot Water Supply Scheme under Mayureswar-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07154 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kot w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-4) | 1323/ BHM | 16/08/2021 | 60 | M/S GOUTAM DAS | 93.02 | 26.85 | 100 | 65
923 | BIRBHUM | Birbhum Division | Retrofitting works of Kot Water Supply Scheme under Mayureswar-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07154 | Retrofitting | Supply and delivery of Sluice Valve & Duck Foot Bend for Kot W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.? (Sl. No.4) | 377/BHM | 21/02/2022 | 15 | SSPR VALVE MANUFACTURING PVT LTD | 6.99 | 0 | 0 | 100
924 | BIRBHUM | Birbhum Division | Retrofitting works of Kot Water Supply Scheme under Mayureswar-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07154 | Retrofitting | Allied works for Providing FHTC from existing distribution system under Kot Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | 2059/BHM | 08/06/2023 | 405 | SAPTADIP CONSTRUCTION | 54.29 | 0 | 0 | 91
925 | BIRBHUM | Birbhum Division | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area , SM/06945 | Retrofitting | Providing Tap Connection for Existing School & AWC under Shilogram, Kamra,Kayemba,Chandpara, Harirampur Mouzas in Dunigram PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. | 275/RSD | 16/07/2021 | 10 | MD ABSAR ALI | 0.99 | 0 | 0 | 50
926 | BIRBHUM | Birbhum Division | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area , SM/06945 | Retrofitting | Laying & distribution system with UPVC pipes including FHTC (Functional Household Tap Connection) for Belera PWSS under Birbhum, Division, PHE Dte | 2165./BHM | 28/09/2022 | 30 | OM ENTERPRISE | 34.22 | 4.48 | 100 | 30
927 | BIRBHUM | Birbhum Division | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area , SM/06945 | Retrofitting | Supply of one no. diesel driven car(Diesel) on hire basis office uses for the officials of the Assistant Engineer, RWS, Birbhum Sub-Division, PHE Dte. (Period from 01.01.2024 to 27.06.2024) | 481/RWS | 28/12/2023 | 179 | AADIL CONSTRUCTION | 0.85 | 0 | 0 | 52
928 | BIRBHUM | Birbhum Division | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area , SM/06945 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Dunigram of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. | 1176 /BHM | 21/09/2020 | 60 | QUAZI SIRAJUL ISLAM. | 38.07 | 71.17 | 172.87 | 0
929 | BIRBHUM | Birbhum Division | Retrofitting works of Dunigram (Phase-II) water supply scheme under Rampurhat-II Block for providing Functional Household Tap Connection (FHTC) within the command area , SM/06945 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Chandanpara) of Dunigram w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte | 1175 /BHM | 21/09/2020 | 60 | MD ABSAR ALI | 34.27 | 62.84 | 200 | 0
930 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block , SM/07650 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system for left out Households of the village Hate-Serandi under Hate-Serandi Water Supply Scheme of Bolpur Sub-Division under Birbhum Division, PHED. | 448/BSD | 10/12/2021 | 30 | BISWARUP GHOSH | 4.85 | 4.84 | 100 | 100
931 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block , SM/07650 | Retrofitting | Retrofitting of pipe lines at Paschimpara, Daspara, Thanderpar and Dakshinpara for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of the village Hate-Serandi under Hate-Serandi Water Supply Scheme of Bolpur Sub-Division within Birbhum Division, PHED. | 450/BSD | 10/12/2021 | 30 | PRATICK KUMAR GHOSH | 4.14 | 4.14 | 100 | 100
932 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block , SM/07650 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Hateserandi w/s Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-7) | 1462/BHM | 02/09/2021 | 60 | BISWARUP GHOSH | 42.56 | 39.92 | 100 | 98
933 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block , SM/07650 | Retrofitting | Additional pipe line works against laying distribution system of Hate Sarandi Piped Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, P.H.E. Dte | 586 /BHM | 09/06/2020 | 30 | GOUTAM DAS | 4.97 | 0 | 0 | 100
934 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block , SM/07650 | Retrofitting | Supply and delivery of 80mm. dia. Sluice Valves, including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Hateserandi Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 01). | 26/BSD | 21/01/2022 | 15 | M/S GOUTAM DAS | 0.65 | 0 | 0 | 100
935 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block , SM/07650 | Retrofitting | Retrofitting of parallel pipe lines From Node point 34 to Node point 16 for Providing sufficient water to Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages HateSerandi of HateSerandi Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 11). | 53/BSD | 17/02/2022 | 30 | BISWARUP GHOSH | 4.43 | 0 | 0 | 100
936 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block , SM/07650 | Retrofitting | Construction of Boundary Wall with Drain at west side of HateSerandi OHR site of HateSerandi Scheme under Bolpur Sub-Division within Birbhum Division PHE Dte. (Length 55 Mtr.) (Part -II). (Sl. No.: 10). | 59/BSD | 22/02/2022 | 60 | PRATICK KUMAR GHOSH | 4.85 | 0 | 0 | 100
937 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block , SM/07650 | Retrofitting | Additional Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Hateserandi of Hateserandi Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 01). | 188/BSD | 11/05/2022 | 30 | BISWARUP GHOSH | 3.68 | 1.69 | 100 | 100
938 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Hate Serandi PWSS within Nanoor Block , SM/07650 | Retrofitting | Retrofitting of pipe lines at Habitation Natungram for Providing sufficient water to Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Hateserandi of Hateserandi Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 05). | 186/BSD | 11/05/2022 | 30 | PRATICK KUMAR GHOSH | 4.43 | 1.1 | 100 | 100
939 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BIPROTIKURI WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. , SM/08897 | Retrofitting | ¿Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bipratikuri w/s Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.4) | 1693/BHM | 07/10/2021 | 60 | M/S KRIPASINDHU GHOSH & CO. | 72.44 | 71.71 | 100 | 100
940 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BIPROTIKURI WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. , SM/08897 | Retrofitting | Supply and delivery of 80mm dia Sluice Valves, including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Bipratikuri Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED.. (Sl. No.: 02). | 36/BSD | 02/02/2022 | 15 | MAKALI ENGINEERING CORPORATION | 0.65 | 0 | 0 | 100
941 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BIPROTIKURI WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. , SM/08897 | Retrofitting | Laying, Fitting, Fixing and jointing of Rising Main from 1st & 2nd Tube-well to O.H.R of D.I. (K-9) pipe at Bipratikuri Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. 02) | 242/BSD | 16/07/2021 | 30 | SYED HASMAT ALI | 2.71 | 0 | 0 | 100
942 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area BIPROTIKURI WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. , SM/08897 | Retrofitting | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) in Lalbazar, Malitpur, Saripa and Talbana within the Command area of Bipratikuri Water Supply Scheme (Phase-I) for Swajal Gram under Labpur Block of Bolpur Sub-Division within Birbhum Division, P.H.E. Deptt. (Sl. No.5) | 288/BHM | 01/02/2023 | 45 | M/S KRIPASINDHU GHOSH & CO. | 21.33 | 0 | 0 | 100
943 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | ¿Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VIII under Suri-I, Suri-II & Sainthia Water Supply Scheme within Birbhum Sadar Sub- Division Birbhum Division, PHE Dte.¿(Sl. No.6) | 1773/BHM | 28/10/2021 | 60 | M/S GOUTAM DAS | 79.89 | 69.39 | 86.85 | 100
944 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | ¿Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-V under Suri-I, Suri-II & Sainthia Water Supply Scheme Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte.¿(Sl. No.3) | 1772/BHM | 29/10/2021 | 60 | PRANAB KUMAR GHOSH | 79.83 | 79.2 | 99.2 | 100
945 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VI under Suri-I, Suri-II & Sainthia Water Supply Scheme within Birbhum Sadar Sub- Division Birbhum Division, PHE Dte.¿(Sl. No.4) | 1820/BHM | 03/11/2021 | 60 | MD. HASIN | 79.86 | 72.91 | 100 | 100
946 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV under Suri-I, Suri-II & Sainthia Water Supply Scheme Birbhum Sadar Sub=Division within Birbhum Division, P.H.E. Dte. (Sl. No. 2) | 1851/BHM | 09/11/2021 | 60 | SAKTI ENTERPRISE | 79.88 | 79.55 | 100 | 100
947 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VII under Suri-I, Suri-II & Sainthia Water Supply Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.5) | 1774/BHM | 29/10/2021 | 60 | M/S KRIPASINDHU GHOSH & CO. | 79.85 | 79.64 | 100 | 100
948 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone III under Suri-I, Suri II & Sainthia Water Supply Scheme under Birbhum Sadar Sub- Division within Birbhum Division, PHE Dte. (2nd Call). (Sl. No.11) | 2170/BHM | 28/12/2021 | 60 | M/S BUILDWELL | 79.48 | 76.28 | 100 | 100
949 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Hatzen Bazar Post Office Para at Zone-IV under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 05) | 07/BSSD | 17/01/2022 | 20 | PRANAB KUMAR MONDAL | 4.56 | 4.39 | 100 | 100
950 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Hatzen Bazar Dutta Para, Co-Operative Coloney & Hatzen Bazar Das Para at Zone-IV under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 04) | 06/BSSD | 17/01/2022 | 20 | INDRANIL DUTTA | 4.56 | 4.29 | 100 | 100
951 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area for village of Deshalpur, Gopalpur, Maliha, Ekdala, Haripur, Khosnatore, Jamal, Fathepur and Kubirpur (Zone-IV) under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No.6) | 2218/BHM | 13/10/2022 | 60 | THREE MAA ENTERPRISE | 51.45 | 51.44 | 100 | 100
952 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Sainthia Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 07) | 400/BSSD | 14/12/2021 | 20 | SUBHRADIP SARKAR | 0.99 | 0 | 0 | 50
953 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing Functional School/Institution/AWC Tap Connection from existing Piped Water Supply Scheme distribution system in situated at different location of Suri- I Block under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 05) | 380/BSSD | 10/12/2021 | 20 | AATHARVA CONSTRUCTION | 0.99 | 0.8 | 100 | 50
954 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Hatzen Bazar Goala Para at Zone-IV under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 03) | 05/BSSD | 17/01/2022 | 20 | PUSPAJIT MONDAL | 4.58 | 4.12 | 100 | 100
955 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Extension of 75 mm dia.UPVC distribution pipe line from Hatzen Bazar Co-Operative Coloney at Zone - IV (Part-B) under Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 04) | 322/BSSD. | 13/09/2021 | 20 | RANJIT GHOSH | 4.09 | 2.89 | 100 | 100
956 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Construction of Operator Cum Switch Room 5.00mtr. X 4.00mtr.Size at Zone-IV for the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block under Birbhum Sadar Sub-Division, PHE Dte. within Birbhum Division, P.H.E. Dte (Sl. No.04) | 1083/BHM | 02/07/2021 | 75 | PRANAB KUMAR MONDAL | 4.96 | 0 | 0 | 100
957 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-I under Suri-I, Suri-II & Sainthia Water Supply Scheme within Birbhum Division, PHE Dte.¿ (Sl. No.1) | 1063/BHM | 13/05/2022 | 60 | SYED KHORSID ALAM | 59.55 | 59.45 | 100 | 72
958 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system with the command area of Zone-II under Suri-I, Suri-II & Sainthia Water Supply Scheme with Birbhum Sadar Sub Division Birbhum Division, P.H.E Dte. | 2654/BHM | 01/12/2022 | 45 | APURBA MONDAL | 17.61 | 17.55 | 100 | 100
959 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Allied work for Providing additional Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VI under Suri-I, Suri-II & Sainthia Piped Water Supply Scheme within Birbhum Sadar Sub Division Birbhum Division, P.H.E Dte. | 1160/BHM | 11/04/2023 | 45 | MD. HASIN | 12.73 | 0 | 0 | 100
960 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-VIII under Suri-I, Suri-II and Sainthia Water Supply Scheme within Birbhum Sadar Sub-Division Birbhum Division, P.H.E Dte. | 1049/BHM | 31/03/2023 | 45 | M/S GOUTAM DAS | 29.73 | 0 | 0 | 100
961 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV & V under Suri-I, Suri-II & Sainthia W/S Scheme Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. | 1259/BHM | 17/04/2023 | 45 | PRANAB KUMAR GHOSH | 24.87 | 0 | 0 | 100
962 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Allied work for Providing additional Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV under Suri-I, Suri-II and Sainthia Water Supply Scheme Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. | 1642/BHM | 02/05/2023 | 45 | S R ENTERPRISE | 8.37 | 0 | 0 | 100
963 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-III under Suri-I, Suri-II & Sainthia W/S Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. | 1634/BHM | 02/05/2023 | 45 | M/S BUILDWELL | 19 | 0 | 0 | 100
964 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Allied work for Providing additional Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV under Suri-I, Suri-II and Sainthia Water Supply Scheme Birbhum Sadar Sub-Division within Birbhum Division P.H.E. Dte. | 1641/BHM | 02/05/2023 | 45 | SAKTI ENTERPRISE | 7.04 | 0 | 0 | 100
965 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Extension of 75 mm dia.UPVC distribution pipe line from Hatzen Bazar Post Office Para at Zone - IV (Part-B) under Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 01) | 319/BSSD.. | 13/09/2021 | 20 | ARPAN PANDIT | 4.09 | 3.63 | 100 | 100
966 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Extension of 75 mm dia.UPVC distribution pipe line from Hatzen Bazar Dutta Para at Zone - IV (Part-B) under Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 02) | 320/BSSD. | 13/09/2021 | 20 | DIPAK SARKAR | 4.09 | 3.67 | 100 | 100
967 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-II under Suri-I, Suri-II & Sainthia Water Supply Scheme within Birbhum Division, PHE Dte¿ (Sl. No.2) | 1062/BHM | 13/05/2022 | 60 | APURBA MONDAL | 59.53 | 56.42 | 100 | 100
968 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area for village of Monpur, Kulera, Kukurdihi & Kendua (Zone-III) under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. | 2652/BHM | 01/12/2022 | 45 | AVIJIT CHANDA | 17.72 | 16.49 | 100 | 0
969 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system with the command area of Zone-VII under Suri-I, Suri-II & Sainthia Water Supply Scheme with Birbhum Sadar Sub Division Birbhum Division, P.H.E Dte. | 1044/BHM | 31/03/2023 | 45 | ARKA JYOTI GHOSH | 20.49 | 0 | 0 | 100
970 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Allied work for Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Hatzen Bazar Dutta Para, Co-Operative Coloney & Hatzen Bazar Das Para at Zone-IV under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. (Sl. No. - 04) | 298/BSSD | 15/12/2022 | 20 | NEEL ENTERPRISE | 1 | 0.99 | 100 | 0
971 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing Balance FHTC for the villages of Karimpur & rest portion of Dhalla, Kunuri & all other allied works for Zone-II of Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II & Sainthia Block within Birbhum Division, P.H.E. Dte. | 1039/BHM | 15/03/2024 | 30 | PRONAB KUMAR DEY | 11.79 | 0 | 0 | 85
972 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Fluoride affected mouzas under Suri-I,Suri-II &Sainthia Blocks PWSS within Suri-I,Suri-II & Sainthia Block , SM/08286 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area for village of Monpur, Kulera, Kukurdihi & Kendua (Zone-III) under the Piped Water Supply Scheme for Fluoride Affected Mouzas under Suri-I, Suri-II and Sainthia Block, Dist: Birbhum under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division P.H.E. Dte. | 1043/BHM | 15/03/2024 | 443 | ANIRUDDHA FARUQUE | 20.12 | 0 | 0 | 100
973 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Distribution System Relating to Augmentation of Joydev-Kenduli Water Supply Scheme , Block Illambazar, District, Birbhum, under Birbhum Division, PHE Dte. (Sl. No. - 04) | 1729/BHM | 25/10/2021 | 120 | PRANAB KUMAR GHOSH | 84.66 | 22.93 | 27.09 | 45
974 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Repairing & Renovation of Pump House No.1, boundary wall, construction of drain, painting of pump house & boundary wall etc. of Labpur(Zone-I)W/S scheme situated at Dwarka under Bolpur Sub-Division, within Birbhum Division,PHE Dte.(Sl.No.03) | 55BH | 17/03/2022 | 90 | SYED HASMAT ALI | 4.01 | 0 | 0 | 0
975 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Repairing and renovation of the Boundary Wall of Labpur Zone-II Water Supply Scheme at Laghata under RWS, Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. Suri, Birbhum(Phase-I) Sl.No.-1. | 130/BH | 15/06/2022 | 45 | SOURAV MONDAL | 4.23 | 0 | 0 | 0
976 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Construction of 900cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Illmbazar W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing)? (Sl. No.2) | 20003/BHM | 22/09/2022 | 273 | APURBA MONDAL | 185.75 | 0 | 0 | 0
977 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Repairing & Renovation of 2 nos. Pump House with operator room, store room, etc. with coloring of Labpur(Zone-II) W/S Scheme under RWS,Birbhum Sub-Division within Birbhum Division, PHE Dte.(Sl.No.-01) | 53/BH | 17/03/2022 | 90 | ARNAB CHANDRA | 4.53 | 0 | 0 | 100
978 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Annual Mtc. of pipeline (Distribution and rising main) for the water supply schemes related to the daily supply of water to the consumers under Birbhum Division, PHE Dte.¿ Chandidas Nanoor Water Supply Scheme (Sl. No.-26) | 1842/BHM | 31/12/2020 | 12 | MS KAZIMEHERUDDIN | 2.98 | 0 | 0 | 0
979 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Repairing & Renovation of Pump House No.2 & Boundary Wall at Dwarka of Labpur(Zone-I) Water Supply Scheme under RWS Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. | 38/BH | 09/03/2022 | 30 | ARPAN PANDIT | 2.34 | 0 | 0 | 100
980 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Repairing & Renovation of Pump House, construction of Approach road with culvert,etc. of Labpur (zone-II) W/S Scheme situated at Laghata under RWS Birbhum Sub-Division within Birrbhum Division,PHE Dte.(Sl No. 02) | 54/BH | 17/03/2022 | 90 | ANIRUDDHA FARUQUE | 2.31 | 2.23 | 100 | 100
981 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Distribution System Relating To Augmentation Of Joydev-Kenduli Water Supply Scheme, Block -Illambazar, District - Birbhum, Under Birbhum Division, P.H.E. Dte.. (Sl. No.-4) | 1724/BHM | 25/10/2021 | 120 | PRANAB KUMAR GHOSH | 84.66 | 26.12 | 100 | 62
982 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Providing Balance Functional Tap Connection (FHTC) from existing distribution system within the command area for Augmentation of Joydev- Kendhuli Water Supply Scheme (For Swajal Gram) within Bolpur Sub - Division PHE Dte. | 2498/BHM | 17/11/2022 | 45 | RANJIT GHOSH | 13.69 | 13.55 | 100 | 100
983 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Materials Payment | BP-2021-22-355 | 14/03/2022 | 0 | RESOURCES DIVISION | 602.7 | 0 | 0 | 0
984 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Providing Functional Household Tap Connection (FHTC) for AWC, Health centre, Govt. institution & others from existing distribution system within the command area of Labpur Zone-I & Zone-II Water Supply Scheme within Labpur Block under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 08). | 71/BSD | 03/03/2022 | 10 | ANKITA CHAKRABORTY | 1.09 | 0 | 0 | 50
985 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Lavpur Zone - II Water Supply Scheme under Bolpur Mechanical Division PHE Dte. | 1433/Bol.MD | 11/07/2023 | 45 | M/S SWAPAN BANERJEE | 28.36 | 0 | 0 | 70
986 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Lavpur Zone - I Water Supply Scheme under Bolpur Mechanical Division PHE Dte | 1432/Bol.MD | 11/07/2023 | 45 | MITRA ENTERPRISE | 18.87 | 0 | 0 | 70
987 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Providing Electro-mechanical accessories including other allied works for Augmentation of TINOOR Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. Block : Illambazar, Dist : Birbhum. | 2249/Bol.MD | 13/09/2023 | 60 | DEY ENTERPRISE | 21.4 | 0 | 0 | 0
988 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Providing Electro-mechanical accessories including other allied works for Augmentation of JOYDEV-KENDULI Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. Block : Illambazar, Dist : Birbhum. | 3600/BOL.MD | 12/12/2023 | 90 | RSA ENTERPRISE | 21.19 | 0 | 0 | 0
989 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Laying of Distribution system for proposed Augmetation Scheme for Kirnahar ( Zone - II ) and Chandidas Nanoor water Supply scheme on Katowa - Suri Road from Ch. 20.5 to 22.4 km and Naoor - Basapara Road From Node point J34 to J186, J186 to J124, J124 to J33, J33 to J200, J200 to J16, J16 to J9 and J9 to J5 ( by HDD Process with Mechanical Devices and Machinaries required for Treanchless Pipe within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.5) | 92/BHM | 10/01/2023 | 75 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 148.83 | 145.55 | 100 | 100
990 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Sinking of 02 (Two) no. 250 mm x 200 mm dia. 250 Mtr deep Tube well by Direct Rotary Rig method for Augmentation of Kirnahar Zone - II Water Supply Scheme at Parota Mouja under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No.5) (2nd Call) | 662/BHM | 28/02/2023 | 30 | ANIRUDDHA FARUQUE | 34.05 | 0 | 0 | 100
991 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250 mm x 150 mm x 300 Mtrs. Depth ) by utilising Hired Rig Machine at Illambazar and Tinoor PWSS (at Head Works site) , Block - Illambazar (under Augmentation of 6 nos. schemes of Lavpur PWSS, Illambazar PWSS, Joydev Kenduli PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS) under Bolpur Mechanical Division, P.H.E. Dte. | 1648/Bol.MD | 25/07/2023 | 60 | SATYAJIT GHOSH | 42.86 | 37.75 | 100 | 100
992 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Supply and delivery of Sluice Valve for Augmentation of Kirnahar Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-3) | 3952/BHM | 03/10/2023 | 30 | RAMESH AND SHANTI ENGINEERING WORKS | 8.19 | 0 | 0 | 100
993 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Supply and delivery of Sluice Valve for Augmentation of Labpur Zone-I W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-4) | 3951/BHM | 03/10/2023 | 30 | RAMESH AND SHANTI ENGINEERING WORKS | 7.69 | 0 | 0 | 100
994 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Material Requisition To Resource Division | 595/BHM | 09/03/2022 | 0 | Resource Division | 751.34 | 0 | 0 | 0
995 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Material Requisition To Resource Division | 909/BHM | 26/04/2022 | 0 | Resource Division | 21.38 | 0 | 0 | 0
996 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Material Requisition To Resource Division | 2293/BHM | 20/10/2022 | 0 | Resource Division | 68.75 | 0 | 0 | 0
997 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Material Requisition To Resource Division | 2206/BHM | 12/10/2022 | 0 | Resource Division | 82.06 | 0 | 0 | 0
998 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Material Requisition To Resource Division | 1112/BHM | 10/04/2023 | 0 | Resource Division | 34.68 | 0 | 0 | 0
999 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Material Requisition To Resource Division | 2072/BHM | 14/06/2023 | 0 | Resource Division | 43.12 | 0 | 0 | 0
1000 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Material Requisition To Resource Division | 2279/BHM | 13/07/2023 | 0 | Resource Division | 142.55 | 0 | 0 | 0
1001 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Construction of 750cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Kirnahar Zone-I W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing)¿ (Sl. No.8) | 2769/BHM | 14/12/2022 | 274 | TEKNO ENTERPRISE | 165.61 | 33.12 | 20 | 97
1002 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Laying distribution system including all types of specials valves street stand post and functional household connection all complete for Augmentation of Chandidas Nanoor Water Supply Scheme in Nanoor Block under Birbhum Division PHE Dte. (Sl.No.4) | 1070/BHM | 13/05/2022 | 963 | G.D. CONSTRUCTION & CO | 484.01 | 167.29 | 34.56 | 88
1003 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Construction of 900cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Labhpur Zone-II W/S Scheme under Birbhum Division, PHE Dte. (As per Departmental Drawing) | 2466/BHM | 11/11/2022 | 273 | SATYANARAYAN ENGINEER'S CO-OP.SOCIETY LTD. | 185.52 | 0 | 0 | 20
1004 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Providing Electro-mechanical accessories including other allied works for Augmentation of ILLAMBAZAR PWSS under Bolpur Mechanical Division PHE Dte. Block : Illambazar, Dist : Birbhum. | 2248/Bol.MD | 13/09/2023 | 60 | EASTERN INDIA SALES & SERVICE | 30.28 | 0 | 0 | 60
1005 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Allied works for Dismantling of PCC road for Laying of Distribution pipeline and inter-connection to existing pipe line of TINOR Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, Public Health Engineering Department. | 282/BSD | 25/07/2022 | 20 | G.D. CONSTRUCTION & CO | 4.55 | 0 | 0 | 0
1006 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Laying of Inter-Connection Pipe Line From T/W No. - 3 to OHR & Repairing of Old Staff Room for the Purpose of Pannel Room of Tubewell No.- 3 Under Tinor W/S Scheme of Bolpur Sub-Division with-In Birbhum Division, PHE Dte. | 3433/BHM | 16/12/2024 | 45 | MS AD ENTERPRISE | 1.8 | 0 | 0 | 0
1007 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250 mm x 150 mm x 300 Mtrs. Depth ) by utilising Hired Rig Machine at Bipratikuri PWSS (at defunct 2nd tube well site) , Block - Labhpur, (under Retrofitting of Lavpur Block) under Bolpur Mechanical Division, P.H.E. Dte | 1645/Bol.MD | 25/07/2023 | 60 | SATYAJIT GHOSH | 21.43 | 0 | 0 | 100
1008 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250 mm x 150 mm x 300 Mtrs. Depth ) by utilising Hired Rig Machine at Kirnahar Zone - I PWSS (at Debogram) , Block - Nanoor, (under Augmentation of 6 nos. schemes of Lavpur PWSS, Illambazar PWSS, Joydev Kenduli PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS) under Bolpur Mechanical Division, P.H.E. Dte | 1646/Bol.MD | 25/07/2023 | 60 | SATYAJIT GHOSH | 42.86 | 0 | 0 | 100
1009 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Providing drilling crew and other allied works for construction of Tube Well (250 mm x 150 mm x 300 Mtrs. Depth ) by utilising Hired Rig Machine at Lavpur Zone - I & Zone - II PWSS (at Dwarka & Zone - II at Head Works site) , Block - Lavpur, (under Augmentation of 6 nos. schemes of Lavpur PWSS, Illambazar PWSS, Joydev Kenduli PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS) under Bolpur Mechanical Division, P.H.E. Dte | 1647/Bol.MD | 25/07/2023 | 60 | SATYAJIT GHOSH | 42.86 | 0 | 0 | 100
1010 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Supply and delivery of Sluice Valve for Augmentation of Labpur Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-5) | 3945/BHM | 03/10/2023 | 30 | KALPANA VALVES MFG CO PVT LTD | 8.68 | 0 | 0 | 100
1011 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Supply and delivery of Sluice Valve for Augmentation of Kirnahar Zone-I W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-2) | 3946/BHM | 03/10/2023 | 30 | SSPR VALVE MANUFACTURING PVT LTD | 9.43 | 0 | 0 | 100
1012 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Laying distribution system for proposed augmentation scheme for Labpur (Zone - I) Piped Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1028/BHM | 12/05/2022 | 180 | ROY ENTERPRISE | 420.9 | 319.03 | 65.92 | 100
1013 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Continuation work order for Supply and delivery of Sluice Valve for Augmentation of Labpur Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte | 21/BHM | 04/01/2024 | 30 | KALPANA VALVES MFG CO PVT LTD | 8.68 | 0 | 0 | 100
1014 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Continuation work order for Supply and delivery of Sluice Valve for Augmentation of Labpur Zone-I W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-4) | 485/BHM | 02/02/2024 | 30 | RAMESH AND SHANTI ENGINEERING WORKS | 7.69 | 0 | 0 | 100
1015 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Continuation Work Order for Supply and delivery of Sluice Valve for Augmentation of Kirnahar Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-3) | 503/BHM | 02/02/2024 | 30 | RAMESH AND SHANTI ENGINEERING WORKS | 8.19 | 0 | 0 | 100
1016 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Continuation Work Order for Supply and delivery of Sluice Valve for Augmentation of Kirnahar Zone-I W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-2) | 907/BHM | 13/03/2024 | 30 | SSPR VALVE MANUFACTURING PVT LTD | 9.43 | 0 | 0 | 100
1017 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Supply & Installation of Motor control Panels at the Kirnahar Water Supply Scheme under Bolpur Mechanical Division, PHE Dte. | 559/BOL.MD | 15/03/2024 | 30 | SINHA ELECTRICALS | 2.92 | 0 | 0 | 100
1018 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Allied works for Dismantling of PCC road for Laying of Distribution pipeline and inter-connection to existing pipeline of Joydev Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, P.H.E. Deptt. | 238/BSD | 17/06/2022 | 15 | PRANAB KUMAR GHOSH | 4.84 | 0 | 0 | 100
1019 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | NEW SERVICE CONNECTION FOR KIRNAHAR WATER SUPPPLY SCHEME Z0NE-I, PH-I. | BP-2024-2025-32 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.08 | 0 | 0 | 0
1020 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | NEW SERVICE CONNECTION FOR KIRNAHAR WATER SUPPLY SCHEME ZONE-I, PH-II. | BP-24-25-112 | 02/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.38 | 0 | 0 | 0
1021 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Laying Distribution System for proposed augmentation Scheme for Kirnahar (Zone-II) piped Water Supply Scheme under Nanoor Block, under Birbhum Division, PHE Dte. (Sl. -06) | 648/BHM | 25/03/2022 | 1225 | M/S ASHA CONSTRUCTION | 325.5 | 208.82 | 64.51 | 70
1022 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Construction of 750cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Chandidas W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing) | 2592/BHM | 23/11/2022 | 273 | CHIRANJIB DAS | 165.15 | 0 | 0 | 95
1023 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Kirnahar Zone - II Water Supply Scheme under Bolpur Mechanical Division PHE Dte.. | 1435/Bol.MD | 11/07/2023 | 45 | EASTERN INDIA SALES & SERVICE | 18.86 | 12.59 | 66.77 | 72
1024 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Supply and installation of Pumps and other electro-mechanical accessories for Augmentation of Nanoor water supply scheme T.W. No.- 1 under Bolpur Mechanical Division PHE Dte. | 2250/Bol.MD | 13/09/2023 | 60 | STANDARD ELECTRICALS | 5.78 | 0 | 0 | 100
1025 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Laying of Rising Mains from TW-III and TW-IV to OHR in Labpur Zone-II Augmentation Scheme at Labpur Block within Bolpur Sub-Division under BIRBHUM Division, PHE Dte. | 438/BHM | 10/02/2025 | 60 | ARNAB CHANDRA | 5.88 | 0 | 0 | 0
1026 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Construction of Pump House at Head Work Sites of Zone-II under Augmentation of Kirnahar Water Supply Scheme with laying of rising main from TW- 1 and TW- 2 to CWR and repairing of CWR, Boundary Wall including development of land at Parota under Bolpur Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte | 2710/BHM | 24/09/2024 | 90 | ARABINDA GHOSH | 12.71 | 0 | 0 | 100
1027 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Laying of rising main from new Tubewell at Plot No.-5016, JL No. 65, Mouja-Chandidas Nanoor, Block- Nanoor to newly constructed OHR at Head Works site and construction of 1 no. Pump House (Size - 3.0 M x 3.6 M) along with boundary wall (Length - 30 Mtr.) under Augmentation of Chandisas Nanoor PWSS within Bolpur Sub-Division under Birbhum Division, PHE Dte. | 258/BHM | 21/01/2025 | 60 | MS KAZIMEHERUDDIN | 8.24 | 0 | 0 | 80
1028 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Laying distribution system with FHTC for proposed augmentation scheme for Illambazar Piped Water Supply Scheme, Illambazar Block, under Birbhum Division, PHE Dte | 2113/BHM | 29/07/2024 | 430 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 625.69 | 0 | 0 | 10
1029 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Restoration of Road & Balance Laying of Pipeline through Jack pushing Near (Illambazar Traffic More, Illambazar Post Office, Payer School along the NH Road) at Illambazar PWSS due to Laying of Rising & Distribution Pipeline within Bolpur Sub-Division under Birbhum Division, PHE Dte. | 1595/BHM | 03/06/2025 | 180 | EFFLUENT AND WATERTREATMENT ENGINEERS PVT. LTD | 309.11 | 0 | 0 | 10
1030 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Repairing of damage pipeline due to construction of Drain work, restoration of road, repairing of FHTC, construction of valve chamber and repairing of pump house boundary wall within the command area of Illambazar, Batikar, Nachansaha, Tinor, Joydev-Kenduli PWSS of Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 724/BSD | 31/07/2025 | 30 | APURBA MONDAL | 7.09 | 0 | 0 | 0
1031 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Road restoration work for augmentation scheme for Kirnahar Zone-Il Piped Water Supply Scheme, Nanoor Block, under Birbhum Division, PHE Dte. | 2127/BHM | 18/08/2025 | 90 | M/S ASHA CONSTRUCTION | 16.77 | 0 | 0 | 0
1032 | BIRBHUM | Birbhum Division | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Road restoration work for augmentation scheme for Kirnahar Zone- I Piped Water Supply Scheme, Nanoor Block, under Birbhum Division, PHE Dte. | 2131/BHM | 18/08/2025 | 90 | TEKNO ENTERPRISE | 15.02 | 0 | 0 | 0
1033 | BIRBHUM | Bolpur Mechanical | Augmentation of Labhpur PWSS, Illambazar PWSS, Joydev-kenduly PWSS, Tinoor PWSS, Kirnahar PWSS, Chandidas Nanoor PWSS ) under Birbhum Division , SM/10320 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Kirnahar Zone - I Water Supply Scheme under Bolpur Mechanical Division PHE Dte. | 1434/Bol.MD | 11/07/2023 | 448 | SINHA ELECTRICALS | 19.43 | 12.06 | 62.1 | 100
1034 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Repairing Renovation and up-gradation of Resting Room of Security Guard of Mayureswar Piped Water Supply Scheme under RWS Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. | 36/BH | 09/03/2022 | 30 | SUBHANKAR ROY | 3.61 | 0 | 0 | 100
1035 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | SUPPLY DELIVERY & INSTALLATION OF ELECTRO MECHANICAL ACCESSORIES AND OTHER ALLIED WORKS AT BISHNUPUR WATER SUPPLY SCHEME. UNDER BOLPUR MECHANICAL DIVISION PHE DTE. | 740/AE-III | 24/06/2022 | 20 | SUNIL RABIDAS | 4.85 | 4.78 | 98.51 | 0
1036 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Repairing Work Of Bishnupur 1 No Pump House & 2 No Pump House Unedr RWS,Birbhum Sub-Division,PHE Dte, Within Birbhum Division,PHE Dte.(Sl. No.02) | 87/BH | 05/05/2022 | 20 | RIPAN CONSTRUCTION | 2.72 | 0 | 0 | 0
1037 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Supply delivery & Installation of Voltage correction device at Bishnapur Augmentation water supply scheme under Bolpur Mechanical Division, PHE. Dte. | 1150/AE-III | 24/11/2022 | 45 | SUNIL RABIDAS | 3.37 | 3.32 | 98.49 | 0
1038 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Sinking of 1 No. 200 mm dia 72 Metre deep tubewell fitted with 200 mm dia PVC pipe and fibre glass stainer etc under Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | 176/BH | 03/11/2021 | 15 | AMIT KUMAR ROY | 3.5 | 2.24 | 100 | 82
1039 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Sinking of one unmber 200mm dia 50m. deep tubewell fitted with 200mm dia. PVC pipe and Strainer etc. at Bishnupur W/S Scheme under RWS, Birbhum Sub-Division,PHE Dte. | 20/BH | 18/02/2022 | 20 | TAPAN ENTERPRISE | 2.65 | 2.43 | 100 | 100
1040 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Annual Mtc. of pipeline (Distribution and rising main) for the water supply schemes related to the daily supply of water to the consumers under Birbhum Division, PHE Dte.¿ Bishnupur W/S Scheme (Sl. No.-49) | 1865/BHM | 31/12/2020 | 365 | TAPAN ENTERPRISE | 2.99 | 0 | 0 | 0
1041 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Connecting pipe line from ground bore tube well to existing distribution system of Bishnupur W/S Scheme under Bishnupur water supply scheme, Dist-Birbhum under Birbhum Division,PHE.Dte.(Part-II) | 22/BH | 18/02/2022 | 20 | BHASKAR MANDAL | 2.02 | 1.73 | 100 | 92
1042 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Connecting pipe line from ground bore tube well to existing distribution system of Bishnupur W/S Scheme under Bishnupur W/S Scheme dist. birbhum division, PHE Dte.(Part-I) | 21/BH | 18/02/2022 | 20 | TAPAN ENTERPRISE | 4.83 | 4.63 | 100 | 100
1043 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Allied Work in connection with Laying of UPVC pipe line at Kharia village for Md. Bazar Piped Water Supply Scheme under RWS Birbhum Sub Division,within Birbhum Division PHEDte ,Suri, Birbhum..(Sl. No.04) | 133/BH | 15/06/2022 | 20 | SAI BABA CONSTRUCTION | 0.94 | 0.93 | 100 | 100
1044 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Distribution System within the command area of Bishnupur Water Supply Scheme (Baswa Latpara & Lalitakundu Purba Para) under RWS Birbhum Sub-Division, within Birbhum Division, PHE Dte.(Sl. No.06) | 135/BH | 15/06/2022 | 30 | BIJOY KUMAR CHOUDHURY | 4.58 | 4.52 | 100 | 100
1045 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Laying of UPVC pipe line at Kharia village for Md. Bazar Piped Water supply scheme under RWS Birbhum Sub-Division within Birbhum Division, PHE Dte. (sl. no.) | 56/BH | 17/03/2022 | 20 | SAI BABA CONSTRUCTION | 1.07 | 1.07 | 100 | 100
1046 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Repairing and Renovation of Bargachha Pump House and Boundary Wall under Md. Bazar Piped Water Supply Scheme under RWS, Birbhum Sub-Division within Birbhum Division, PHE Dte. | 34/BH | 09/03/2022 | 30 | ARYAN CONSTRUCTION | 3.9 | 0 | 0 | 100
1047 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Repairing Work Of Bishnupur 1 No Pump House & 2 No Pump House Unedr RWS,Birbhum Sub-Division,PHE Dte, Within Birbhum Division,PHE Dte.(Sl. No.02) | 87/BH | 05/05/2022 | 20 | RIPAN CONSTRUCTION | 2.73 | 0 | 0 | 0
1048 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Laying of UPVC pipe line for supply of drinking water at Damra Namupara village under Md. Bazar Block within Birbhum Division, P.H. E Dte. (Sl. No. - 05) | 50/BSSD | 18/02/2021 | 15 | B.M.SARKAR | 4.86 | 4.85 | 100 | 100
1049 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Materials Payment | BP-2021-22-355 | 14/03/2022 | 0 | RESOURCES DIVISION | 497.76 | 0 | 0 | 0
1050 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | quotation for Aug. of Bishnupur water supply scheme | BP-2022-2023-79 | 20/12/2022 | 0 | WBSEDCL | 1.98 | 0 | 0 | 0
1051 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Repairing and Renovation of R.C.C. Over Head Reservoir for Md. Bazar Piped Water Supply Scheme, under Birbhum Division, P.H.E. Dte.(Sl. No.05) | 89/BH | 05/05/2022 | 30 | BHASKAR MANDAL | 4.05 | 0 | 0 | 100
1052 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Laying distribution System including providing Functional Household Tap Connection(FHTC) within the command area Augmentation of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.14) | 285/BHM | 01/02/2023 | 45 | TAPAN KUMAR DATTA | 74.19 | 11.11 | 14.98 | 16
1053 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development (PH No-1) for Augumentation of Mollarpur Zone-I Piped Water Supply Scheme, Block-Mayureswar-I within Birbhum Division, PHE Dte. (Sl. No.1) | 334/BHM | 02/02/2023 | 60 | JAHIR HOSSAIN | 10.42 | 0 | 0 | 0
1054 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Supply & delivery of Chlorination System at store for Augmentation of Bishnupur and other water supply scheme under Bolpur Mechanical Division, PHE. Dte. | 528/AE-III | 28/03/2023 | 20 | M/S S.R. ENTERPRISE | 2.7 | 2.7 | 100 | 0
1055 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Supply delivery & Installation of Voltage correction device at Mollarpur Zone-II (Kamraghat) water supply scheme under Bolpur Mechanical Division, PHE. Dte. | 1036/Bol.MD | 05/06/2023 | 45 | S.K.ELECTRICALS | 12.8 | 12.02 | 93.86 | 0
1056 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Supply and Installation of Submersible pumping machineries and other electro mechanical equipments at Augmentation of Hatgacha Piped water supply scheme under MD Bazar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 1437/Bol.MD | 11/07/2023 | 45 | TAPAN ENTERPRISE | 5.24 | 0 | 0 | 0
1057 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development (PH No-2) for Augumentation of Mollarpur Zone-I Part -C Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. | 3994/BHM | 05/10/2023 | 60 | ABDUL MOTALIB | 11.13 | 0 | 0 | 0
1058 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development (PH No-1) for Augumentation of Mollarpur Zone-I Part -C Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. | 3955/BHM | 03/10/2023 | 183 | AINUL SHAIKH | 9.98 | 0 | 0 | 0
1059 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Sinking of 01 Nos Tube well 200 mm dia 96 m. deep tube well fitted with PVC pipe and fiber glass Strainer at Augmentation of Mollarpur Zone-II PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 184/RSD | 02/05/2022 | 30 | HARUN AR RASHID | 4.97 | 4.7 | 100 | 100
1060 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Providing Functional Household Tap Connection(FHTC) at Baswa Lat Para within the command area of Bishnupur Water Supply Scheme under RWS Birbhum Sub-Divition within Birbhum Division PHE Dte.(Sl. No.09) | 138/BH | 15/06/2022 | 20 | BIJOY KUMAR CHOUDHURY | 3.6 | 0 | 0 | 50
1061 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Laying distribution system including functional household connection for proposed Augmentation of Hatgacha Piped Water Supply Scheme in Md. Bazar Block under Birbhum Division, P.H.E Dte.¿ (Sl. No.1) | 1027/BHM | 12/05/2022 | 180 | S S ENTERPRISE | 428.01 | 286.92 | 67.05 | 100
1062 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Distribution System including providing Functional Household Tap Connection(FHTC) at Lalitakundu Paschim Par within the command area of Bishnupur Water Supply Scheme Under RWS Birbhum Sub-Division,within Birbhum Division,PHE Dte.(Sl. No.07) | 136/BH | 15/06/2022 | 30 | BIJOY KUMAR CHOUDHURY | 4.71 | 0 | 0 | 50
1063 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall, PCC approach Road, Land Development (PH No-3) for Augmentation of Mayureswar Piped Water Supply Scheme, Block-Mayureswar-II within Birbhum Division, PHE Dte. (Sl. No.7) | 39/BHM | 04/01/2023 | 60 | SK GOLAM MORTUJA | 11.37 | 0 | 0 | 100
1064 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Construction of Switch room cum chlorine room with sanitary and water supply arrangement 5.40mtr.x 3.65mtr. size Bishnupur W/S Scheme under Rumpurhat Sub- Division,P.H.E. Dte. | 23/BH | 18/02/2022 | 20 | TAPAN ENTERPRISE | 4.98 | 4.65 | 100 | 100
1065 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Alided work of Connecting pipe line from Ground Bore Tube Well to Existing distribution system of Bishnupur Piped Water Supply Scheme, under RWS Birbhum Sub-Division within Birbhum Division, P.H.E. Dte. (Sl. No.2) | 226/BHM | 20/01/2023 | 15 | SEVAK CO - OP LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD | 2.42 | 0 | 0 | 100
1066 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Sinking of 04 (Four) Nos Tubewell 250 mm X 150 mm dia X 300 m. deep tubewells by Rotary Rig at Augmentation of Mayureswar PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. (Sl. No.1) (2nd Call) | 810/BHM | 14/03/2023 | 60 | SATYAJIT GHOSH | 74.84 | 51.07 | 100 | 100
1067 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Sinking of 03 (Three) Nos Tubewell 250 mm X 150 mm dia X 300 m. deep tubewells by Rotary Rig at Augumentation of Mollarpur Zone-I PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. (Sl. No.3) (2nd Call) | 713/BHM | 02/03/2023 | 45 | SUNIL RABI DAS | 56.14 | 25.13 | 100 | 100
1068 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Construction of Switch room at Head work Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development for (PH No-1) for Augumentation of Mollarpur Zone-II Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. (Sl. No.4) | 518/BHM | 20/02/2023 | 60 | ANARUL HOQUE | 14.5 | 0 | 0 | 100
1069 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Supply & delivery of Cable at store for Augmentation of Bishnupur and other water supply scheme under Bolpur Mechanical Division, PHE. Dte. | 519/AE-III | 28/03/2023 | 20 | SATYAJIT GHOSH | 3.21 | 3.21 | 100 | 0
1070 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Supply & delivery of Column pipe & others at store for Augmentation of Bishnupur and other water supply scheme under Bolpur Mechanical Division, PHE. Dte. | 515/AE-III | 28/03/2023 | 20 | S.K.ELECTRICALS | 2.46 | 2.46 | 100 | 0
1071 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Md. Bazar water supply scheme under Bolpur Mechanical Division PHE Dte. | 718/Bol.MD | 19/04/2023 | 45 | HINDOL ROY | 35.27 | 34.97 | 100 | 100
1072 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Painting of R.C.C. Over Head Reservoir for Md. Bazar Piped Water Supply Scheme, under RWS Birbhum Sub-Division within Birbhum Division, P.H.E. Dte. (Sl. No.8) | 229/BHM | 20/01/2023 | 15 | BHASKAR MANDAL | 1.76 | 1.73 | 100 | 100
1073 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Laying of bypass Connection line and Land Development at Khorasinpur Ohr site under Mollarpur Zone-II W/S Scheme under Rampurhat Sub- Division, P.H.E. Dte. | 371/RSD | 28/09/2021 | 30 | SHIB GANGA CONSTRUCTION | 4.24 | 4.17 | 100 | 100
1074 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Material Requisition To Resource Division | 596/BHM | 09/03/2022 | 0 | Resource Division | 525.88 | 0 | 0 | 0
1075 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Material Requisition To Resource Division | 2208/BHM | 12/10/2022 | 0 | Resource Division | 6.02 | 0 | 0 | 0
1076 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Material Requisition To Resource Division | 2294/BHM | 20/10/2022 | 0 | Resource Division | 5.82 | 0 | 0 | 0
1077 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Material Requisition To Resource Division | 1123/BHM | 10/04/2023 | 0 | Resource Division | 32.67 | 0 | 0 | 0
1078 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Material Requisition To Resource Division | 2071/BHM | 14/06/2023 | 0 | Resource Division | 30.8 | 0 | 0 | 0
1079 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Material Requisition To Resource Division | 2277/BHM | 13/07/2023 | 0 | Resource Division | 54.13 | 0 | 0 | 0
1080 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | WBSEDCL QUOATAION FOR MUYURESWAR WS SCHEME | BP-2023-2024-74 | 23/08/2023 | 0 | WBSEDCL | 2.64 | 0 | 0 | 0
1081 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | WBSEDCL QUOTATION FOR RAJCHANDRAPUR P.H.NO. 4 PWSS FOR AUG. OF MAYURESWAR WS SCHEME | BP-23-24-132 | 17/10/2023 | 0 | WBSEDCL | 5.26 | 0 | 0 | 0
1082 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | WBSEDCL QUOTATION FOR MAYURESWAR WS SCHEME | BP-2023-2024-75 | 24/08/2023 | 0 | WBSEDCL | 4.48 | 0 | 0 | 0
1083 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | WBSEDCL QUOTATION FOR AUG OF MOLLARPUR | BP-2023-2024-80 | 18/09/2023 | 0 | WBSEDCL | 2.99 | 0 | 0 | 0
1084 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | WBSEDCL QUOATATION MONEY FOR MOLLARPUR ZONE-II WS SCHEME | BP-2023-2024-33 | 18/05/2023 | 0 | WBSEDCL | 2.9 | 0 | 0 | 0
1085 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | WBSEDCL QUOTATION FOR AUG OF MOLLARPUR | BP-2023-2024-81 | 18/09/2023 | 0 | WBSEDCL | 4.98 | 0 | 0 | 0
1086 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for 1 no OHR site at Augmentation of Mollarpur Zone-II Piped Water Supply Scheme under Rampurhat Sub-Division within Birbhum Division, P.H.E. Dte. | 174/RSD | 29/04/2022 | 30 | GEOCON INDIA | 0.99 | 0 | 0 | 100
1087 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Sinking of 03 (Three) nos. Rig Bored Tube well by DTH method of drilling (125 mm X 115 mm) dia for source Augmentation of Hatgacha PWSS under Rampurhat Sub-Division, Birbhum Division P.H.E Dte. | 3156/BHM | 19/11/2024 | 45 | BHABATARAN SADHU | 9.87 | 0 | 0 | 0
1088 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall,PCC approach Road,Land Development (PH No-2) for Augmentation of Mayureswar Piped Water Supply Scheme, Block -Mayureswar-II within Birbhum Division, PHE Dte. (Sl. No.6) | 2842/BHM | 21/12/2022 | 60 | NOBI SEIKH | 13.39 | 0 | 0 | 100
1089 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall,PCC approach Road, Land Development (PH No-3) for Augmentation of Mollarpur Zone-I Piped Water Supply Scheme, Block-Mayureswar-I within Birbhum Division, PHE Dte. (Sl. No.3) | 2914/BHM | 27/12/2022 | 60 | SAFIUDDIN SEKH | 11.25 | 0 | 0 | 100
1090 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Laying of Balance Distribution Main pipeline through road crossing of SH 11 and Md Bazar-Kulkuri Road (Node R1-1, 4-47, 7-87, 9-108, 18-24, 28-29, 30-270 & 34-317) and NH-14 (Node 33-34) by adopting Jack Pushing method for Augmentation of Md Bazar Piped Water Supply Scheme under Md Bazar Block, under Birbhum Division P.H.E Dte. | 1046/BHM | 31/03/2023 | 60 | M/S GOUTAM DAS | 57.55 | 57.55 | 100 | 0
1091 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Additional Laying distribution system at different mouzas including Functional Household Tap Connection under Augmentation of Hatgacha Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte | 1097/BHM | 06/04/2023 | 90 | S S ENTERPRISE | 273.65 | 0 | 0 | 50
1092 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Allied work for balance portions of Laying distribution system for proposed augmentation scheme of Md.Bazar Piped Water Supply Scheme under Md.Bazar Block, Sinking of 200 mm dia. tubewell (03 nos.) 28 m. Deep fitted with PVC Housing pipe and Fibre Glass Strainer with connecting pipe line with surging of existing 2 (Two) nos. Tube well including renovation of boundary wall at Head Work Site of Md. Bazar Piped Water Supply Scheme under Birbhum Division PHE Dte. | 2079/BHM | 08/06/2023 | 60 | M/S GOUTAM DAS | 52.61 | 0 | 0 | 100
1093 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Sinking of 01 (One) No. Tube well 200 mm X 200 mm dia X180m. deep tube wells by Rotary Rig including connecting main at Augmentation of Mollarpur Zone-II PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 3673/BHM | 29/08/2023 | 45 | HARUN AR RASHID | 13.71 | 0 | 0 | 100
1094 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah), Boundary Wall, PCC approach Road, Land Development (PH No-3) for Augumentation of Mollarpur Zone-I Part -C Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. | 3948/BHM | 03/10/2023 | 183 | ABUL HASNATH | 11.59 | 0 | 0 | 100
1095 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Supply & Delivery of power cable for Augmentation of Bishnupur (Block-Rampurhat-II) under Bolpur Mechanical Division, P.H.E Dte. | 1362/AE-III | 17/10/2023 | 15 | M. S. ENTERPRISE | 4.32 | 0 | 0 | 100
1096 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Sinking of 2 Nos. 200 mm dia X 66 mtr. deep Tubewell with UPVC pipe and strainer for Bishnupur W/S Scheme under Birbhum Division, PHE Dte. | 09/BHM | 03/01/2024 | 240 | HARUN AR RASHID | 8.38 | 0 | 0 | 97
1097 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Supply and delivery of kit kat fuse, Main switch, change over switch, bushbar for Hatgacha Water Supply Scheme of Md. Bazar block under Bolpur Mechanical Division PHE Dte. | 650/BMSD(D) | 02/09/2024 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 2.51 | 0 | 0 | 100
1098 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Additional work for connecting pipeline from ground bore tubewell 03 nos. existing distribution system of Bishnupur pipe water supply scheme under RWS, Birbhum Sub-Division within Birbhum Divsion, PHE Dte.(Sl.No.1) | 184/RWS | 21/11/2024 | 15 | BHASKAR MANDAL | 0.97 | 0 | 0 | 70
1099 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Additional estimate for installation Augmentation Mollarpur water supply scheme under Bolpur Mechanical Division, PHE Dte. | 299/AE-III | 22/02/2024 | 7 | SUNIL RABIDAS | 4.89 | 0 | 0 | 100
1100 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Replacement of voltage correction device at Mollarpur zone-I(Ph-III) (at Block compound) water supply scheme under under Bolpur Mechanical Division, PHE Dte.(Aug. of Mollarpur W/S Scehem) | 309/AE-III | 23/02/2024 | 15 | BIRBHUM ELECTRIC WORKS | 2.97 | 0 | 0 | 100
1101 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | PROVIDING ELECTRO MECHANICAL ACCESSORIES AND OTHERS FOR Augmentation of Hatgacha water supply scheme UNDER BOLPUR MECHANICAL DIVISION IN THE DISTRICT OF BIRBHUM. | 667/Bol.MD | 22/03/2024 | 30 | HINDOL ROY | 22.96 | 0 | 0 | 100
1102 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Supply and delivery of Submersible pump motor set, Slluice valve,NRV for Hatgacha Water Supply Scheme of Md. Bazar block under Bolpur Mechanical Division PHE Dte. | 659/BMSD/(D) | 02/09/2024 | 30 | B. P. TRADING CORPORATION | 1.52 | 0 | 0 | 100
1103 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Quotation for new connection at Augmentation Mollarpur PWSS (Malanchi), block- Mayureswar-I | BP-2024-2025-36 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.85 | 0 | 0 | 0
1104 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | New Power Connection at Delora PWSS under Bolpur mechanical Division, PHE Dte. | BP-24-25-130 | 29/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.84 | 0 | 0 | 0
1105 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Laying distribution system for proposed augmentation scheme for Mollarpur Zone-II Piped Water Supply Scheme, Block-Mayureswar-I under Birbhum Division, PHE Dte. (Sl. No.3) | 1152/BHM | 23/05/2022 | 719 | SUNIL RABI DAS | 401.72 | 248.97 | 61.98 | 100
1106 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall,PCC approach Road,Land Development (PH No-2) for Augumentation of Mollarpur Zone-I Piped Water Supply Scheme, Block -Mayureswar-I within Birbhum Division, PHE Dte. (Sl. No.2) | 2915/BHM | 27/12/2022 | 60 | SAFIUDDIN SEKH | 11.31 | 0 | 0 | 100
1107 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Construction of 900cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Mollarpur Zone-I W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing)¿ (Sl. No.5) | 2247/BHM | 17/10/2022 | 273 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 185.79 | 37.16 | 20 | 85
1108 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Additional Laying distribution system at different mouzas including Functional Household Tap Connection under Augmentation of Mollarpur Zone-I (Part-A) Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. | 2630/BHM | 12/09/2024 | 454 | M/S GOUTAM DAS | 90.71 | 0 | 0 | 55
1109 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Sinking of 02 nos. (01 Additional + 01 Replaced) Tube well (200mm dia, all through 150 mt. Deep) along with Rising Main and Construction of 01 no. Pump House for Mollarpur Zone-II PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 2729/BHM | 25/09/2024 | 272 | SUNIL RABI DAS | 23.99 | 0 | 0 | 70
1110 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Additional Laying distribution system at Kotasur and Adjoining Mouzas including Functional Household Tap Connection under Augmentation of Mayureswar Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. | 400/BHM | 06/02/2025 | 90 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 97.7 | 0 | 0 | 0
1111 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Providing Balance Functional Household Tap Connection (FHTC) by Adopting Jack Pushing Technique for laying Additional distribution system and Laying of Rising Main under Mollarpur Zone-II Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte | 2730/BHM | 25/09/2024 | 446 | SUNIL RABI DAS | 96 | 0 | 0 | 30
1112 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Rising Main with 200mm dia DI pipe and Delivery main with 200mm dia HDPE pipe for OHR under Bishnupur Piped Supply Scheme of Birbhum RWS Sub-Division, Block- Rampurhat-II, P.H.E. Dte. within Birbhum Division PHE Dte. | 865/BHM | 26/03/2025 | 60 | TAPAN KUMAR DATTA | 40.58 | 0 | 0 | 0
1113 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Jack pushing & Augur boring along with extension of pipeline, restoration of Roads and all allied works for Mohammad Bazar piped Water Supply Scheme under Birbhum Division P.H.E. Dte. | 862/BHM | 26/03/2025 | 157 | M/S GOUTAM DAS | 69.84 | 0 | 0 | 100
1114 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Supply and Installation of Submersible pumping machineries and other electro mechanical equipments at Augmentation of Hatgacha Piped water supply scheme under MD Bazar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 736/BOL.MD | 29/04/2025 | 45 | TAPAN ENTERPRISE | 5.24 | 0 | 0 | 0
1115 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Additional Laying distribution system at different mouzas, including the Functional Household Tap Connection under Augmentation of Mollarpur Zone I (Part-B & C) Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, P.H.E. Dte. | 1452/BHM | 19/05/2025 | 181 | M/S GOUTAM DAS | 121.47 | 0 | 0 | 40
1116 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Sinking of 03 (Three) Nos Tubewell 200 mm X 200 mm dia X180m. deep tubewells by Rotary Rig including connecting rising main at Augmentation of Mollarpur Zone-I (Part-C) PWSS under Rampurhat Sub-Division within Birbhum Division, P.H.E. Dte. | 634/RSD | 15/07/2025 | 60 | PULAK KUMAR PAL | 38.38 | 0 | 0 | 0
1117 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Sinking of 01 (One) No. replacement & 01 (One) new Tube well 200 mm X 200 mm dia X 180m. deep tube wells by Rotary Rig including connecting DI rising main along with allied civil works for Augmentation of Mollarpur Zone-I (Part-A) PWSS under Rampurhat Sub-Division within Birbhum Division, P.H.E. Dte. | 737/RSD | 20/08/2025 | 60 | RAJ ASSOCIATES | 40.56 | 0 | 0 | 0
1118 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Sinking of 02 (Two) Nos. new Tube well 200 mm X 200 mm dia X 180m. deep tube wells by Rotary Rig including connecting DI rising main along with allied civil works for Augmentation of Mollarpur Zone-I (Part-B) PWSS under Rampurhat Sub-Division within Birbhum Division, P.H.E. Dte. | 2206/BHM | 26/08/2025 | 90 | RADHARANI ENTERPRISE | 51.13 | 0 | 0 | 0
1119 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Additional Laying distribution system at Mayureswar, Kushtor and Adjoining Mouzas including Functional Household Tap Connection under Augmentation of Mayureswar Piped Water Supply Scheme under Rampurhat sub-Division, under Birbhum Division, PHE Dte. | 2360/BHM | 11/09/2025 | 90 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 130.05 | 0 | 0 | 0
1120 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Different works such as Pump House, Boundary wall, Rising main, LDS, repairing works and allied works related to Augmentation of Bishnupur PWSS within Birbhum RWS Sub-Division, under Birbhum Division, PHE Dte. | 2197/BHM | 22/08/2025 | 90 | SUBHANKAR ROY | 109.95 | 0 | 0 | 0
1121 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Laying distribution system for proposed augmentation scheme for Mayureswar Piped Water Supply Scheme, Mayureswar-II Block under Birbhum Division, PHE Dte. (Sl. No.2) | 1010/BHM | 11/05/2022 | 1061 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 502.2 | 275.24 | 54.82 | 100
1122 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Laying distribution system for proposed augmentation scheme for Md. Bazar Piped Water Supply Scheme under Md. Bazar Block, under Birbhum Division, PHE Dte (Sl. No.7) | 859/BHM | 20/04/2022 | 498 | M/S GOUTAM DAS | 319.7 | 272.25 | 87.26 | 95
1123 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Construction of 750cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Bishnupur W/S Scheme under Birbhum Division, PHE Dte.(As per Departmental Drawing)¿ (Sl. No.7) | 2727/BHM | 08/12/2022 | 274 | S K CONSTRUCTION | 165.71 | 0 | 0 | 100
1124 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Laying distribution system including FHTC for proposed augmentation scheme for Mollarpur Zone-I Piped Water Supply Scheme, Mayureswar-I Block, under Birbhum Division, PHE Dte. (2nd Call)¿ (SL.No.1) | 2246/BHM | 17/10/2022 | 951 | M/S GOUTAM DAS | 908.98 | 675.43 | 74.31 | 78
1125 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement to departmental drawing (Size 3.60 mtr x 3.30 mtr room with 1.2 Mtr. wide verandah),Boundary Wall, PCC approach Road, Land Development (PH No-1) for Augmentation of Mayureswar Piped Water Supply Scheme, Block-Mayureswar-II within Birbhum Division, PHE Dte. (Sl. No.5) | 228/BHM | 20/01/2023 | 60 | CHOWDHURY ENTERPRISE | 11.39 | 0 | 0 | 100
1126 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Miscellaneous works including painting, earthling, repairing of entrance gate etc at head work site at Kharasinpur of OHR, Boundary Wall etc of Mollarpur Zone-II at Mollarpur Zone -II PWSS under Rampurhat Sub Division P.H.E Dte. | 1254/BHM | 17/04/2023 | 45 | MD SURAJ ALI | 3.15 | 0 | 0 | 100
1127 | BIRBHUM | Bolpur Mechanical | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Supply and Installation of Submersible pumping machineries and other electro mechanical equipments at Augmentation of Mollarpur Zone-I and Zone-II Piped water supply scheme under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | 1436/Bol.MD | 11/07/2023 | 419 | SUNIL RABIDAS | 47.6 | 31.57 | 72.53 | 100
1128 | BIRBHUM | Birbhum Division | Augmentation of Hatgacha PWSS, Mahammadbazar PWSS, Bishnupur PWSS, Mayureswar PWSS, Mollarpur (Zone I & Zone II) PWSS under Birbhum Division , SM/10321 | Augmentation | Construction of Switch room at Pump House Site with sanitary and water supply arrangement as per departmental drawing (Size 3.60 mtr. x 3.30 mtr. room with 1.2 mtr. wide verandah), Boundary Wall, PCC approach Road (PH No.-4) for Augmentation of Mayureswar Piped Water Supply Scheme, Block-Mayureswar-II within Birbhum Division, PHE Dte. | 757/BHM | 01/03/2024 | 354 | M/S ZEBA | 10.17 | 0 | 0 | 65
1129 | BIRBHUM | Birbhum Division | Paschim Naopara and Adjoining Mouzas PWSS , SM/12458 | New | Material Requisition To Resource Division | 1422/BHM | 24/04/2023 | 0 | Resource Division | 40.92 | 0 | 0 | 0
1130 | BIRBHUM | Bolpur Mechanical | Paschim Naopara and Adjoining Mouzas PWSS , SM/12458 | New | Providing Electro-mechanical accessories and others for Paschim Naopara & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2095/Bol.MD | 22/08/2023 | 588 | BIRBHUM ELECTRIC WORKS | 27.94 | 0 | 0 | 50
1131 | BIRBHUM | Bolpur Mechanical | Paschim Naopara and Adjoining Mouzas PWSS , SM/12458 | New | New service connection at Paschim Nowapara PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-2023-24-320 | 19/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.62 | 0 | 0 | 0
1132 | BIRBHUM | Bolpur Mechanical | Paschim Naopara and Adjoining Mouzas PWSS , SM/12458 | New | New service connection at Paschim Nowapara PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-2023-24-319 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.69 | 0 | 0 | 0
1133 | BIRBHUM | Bolpur Mechanical | Paschim Naopara and Adjoining Mouzas PWSS , SM/12458 | New | WBSEDCL QUOTATION FOR PASCHIM NOWAPARA PH NO-I |  | 14/03/2024 | 0 | WBSEDCL | 5.62 | 0 | 0 | 0
1134 | BIRBHUM | Birbhum Division | Paschim Naopara and Adjoining Mouzas PWSS , SM/12458 | New | Different works related to water supply scheme at PASCHIM NAOPARA, PHULUR & PURBA SIUR its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | 2262/BHM | 12/07/2023 | 993 | B RAI CONSTRUCTION COMPANY | 1402.44 | 0 | 0 | 45
1135 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR SABASIDANGA AND OTHER 4 NOS. MOUZAS UNDER NALHATI-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11904 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 0 | 92
1136 | BIRBHUM | Birbhum Division | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. , SM/12595 | New | Material Requisition To Resource Division | 1516/BHM | 26/04/2023 | 0 | Resource Division | 13.93 | 0 | 0 | 0
1137 | BIRBHUM | Birbhum Division | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. , SM/12595 | New | Different works related to water supply scheme at KASHIMNAGAR, KAMARKHUL & GAGANPUR and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3647/BHM | 25/08/2023 | 274 | BENGAL ENGINEERING | 1204.06 | 0 | 0 | 30
1138 | BIRBHUM | Bolpur Mechanical | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. , SM/12595 | New | WBSEDCL QUOTATION FOR KASHIMNAGAR P H NI.I WS SCHEME | BP-23-24-251 | 06/02/2024 | 0 | WBSEDCL | 3.1 | 0 | 0 | 0
1139 | BIRBHUM | Birbhum Division | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. , SM/12595 | New | Restoration charges for laying of PHE pipeline from Chainage 5.80 KM (Hiytnagar) to 9.5 KM of Murarai Mitrapur Road under Rampurhat Highway Sub Division of Birbhum Highway Division-_ in the Dist of Birbhum during the year 2023-24 | BP-2024-25-223 | 12/09/2024 | 0 | EXECUTIVE ENGINEER BIRBHUM HIGHWAY DIVISION-I P.W (ROADS) DIRECTORATE | 17.21 | 0 | 0 | 0
1140 | BIRBHUM | Bolpur Mechanical | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. , SM/12595 | New | WBSEDCL QUOTATION FOR KASHIMNAGAR P H NO.Ii WS SCHEME | BP-23-24-252 | 06/02/2024 | 0 | WBSEDCL | 3.21 | 0 | 0 | 0
1141 | BIRBHUM | Bolpur Mechanical | KASHIMNAGAR PIPED WATER SUPPLY SCHEME. , SM/12595 | New | Providing Electro-mechanical accessories and others for Kashimnagar PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | 3304/BOL.MD | 29/09/2023 | 540 | CHAKRABORTY MINING & ENGINERING | 30.42 | 0 | 0 | 80
1142 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Providing FHTC including laying of distribution system within the command area of villages Jethia, Haridaspur, Jinderpur, Kapista. Gagha & Debogram,G.P - Bharkata, Kapista, Ganpur & Rampur, Block - Md.Bazar for ensuing draught like situation within Birbhum Division, PHE Dte. (Phase-II) | 1732/BHM | 12/05/2023 | 60 | HIMANGSU SEKHAR SARKAR | 78.36 | 0 | 0 | 0
1143 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of village Rajganja, Hazrapur, Chinpai and Balijuri under Block Dubrajpur for ensuing draught like situation within Birbhum Division, PHE Dte. (Sl. No.2) | 2605/BHM | 24/11/2022 | 60 | RICK CONSTRUCTION | 78.18 | 0 | 0 | 100
1144 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of village Asanjola, Bamnigao under Block Rampurhat- I for ensuing draught like situation within Birbhum Division, PHE Dte. (Sl. No.3) | 2585/BHM | 22/11/2022 | 30 | INDRAJIT DUTTA. | 21.46 | 0 | 0 | 100
1145 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Additional work for providing Balance FHTC including laying of distribution system for village Geruapahari JL NO 74,G.P Babuijore, Block- Khoirasole for ensuing draught line situation within Birbhum Division PHE Dte. (Sl. No.8) | 222/BHM | 20/01/2023 | 45 | MA KANKALI ENTERPRISE | 7.51 | 0 | 0 | 84
1146 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of village Muktipur & Kuralmetia under Rajnagar Block for ensuing draught like situation within Birbhum Division, PHE Dte. | 1725/BHM | 12/05/2023 | 45 | BHABANI ENTERPRISE | 16.76 | 0 | 0 | 100
1147 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Providing FHTC including laying of distribution system within the command area of villages Rajganja, Hajrapur, Chinpai & Balijuri , G.P - Parulia, Chinpai & Balijuri, Block - Dubrajpur for ensuing draught like situation within Birbhum Division, PHE Dte. (Phase-II) | 1647/BHM | 02/05/2023 | 45 | RICK CONSTRUCTION | 28.38 | 11.66 | 41.09 | 43
1148 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Allied work of Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of village Raotara J.L No 76 , G.P Parulia , Block Dubrajpur for ensuing draught like situation within Birbhum Division, PHE Dte. | 3260/BHM | 26/07/2023 | 45 | GOUTAM MONDAL | 3.02 | 0 | 0 | 100
1149 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Allied work of Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of village Sagarbhanga, J.L No 63, G.P Nakraconda, Block -Khoyrasole for ensuing draught like situation within Birbhum Division, PHE Dte. | 4287/BHM | 10/11/2023 | 45 | DATA CONSTRUCTION | 7.41 | 0 | 0 | 100
1150 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Restoration of distribution pipe line (HDPE), Construction of Sluice Valve Chamber & concreting including FHTC for augmentation of Khayrasole (Zone-II) Piped Water Supply Scheme, Khayrasole Block, under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | 2154/BHM | 01/08/2024 | 45 | RANJIT GHOSH | 4.57 | 0 | 0 | 100
1151 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Allied work of Installation of Sluice Valve along with restoration of road and Land development at new OHR site under Augmentation of Murarai w/s Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | 2354/BHM | 22/08/2024 | 163 | SK ALIM | 44.38 | 0 | 0 | 90
1152 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Extension work of HDPE pipeline for providing FHTC of Kanakpur Mini W/S Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | 2160/BHM | 05/08/2024 | 45 | BROTHERS ENTERPIRSE | 5.74 | 0 | 0 | 100
1153 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Allied work of Laying Rising main including extension of pipeline with restoration of road for Paikar Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | 2353/BHM | 22/08/2024 | 45 | SK ALIM | 94.64 | 0 | 0 | 100
1154 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Allied Work of Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of village Gaisara, J.L No 46, G.P Tantipara, Block Rajnagar for ensuing draught like situation within Birbhum Division, PHE Dte. | 752/BHM | 29/02/2024 | 45 | AVIJIT CHANDA | 4.89 | 0 | 0 | 100
1155 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Construction of 20 Nos Water Supply Overhead Structure at Different places under Draught Prone area at Dubrajpur Block (14 Nos.)and MD. Bazar (6 Nos) under RWS Birbhum Sub Division within Birbhum Division PHE Dte.. | 3163/BHM | 24/07/2023 | 585 | PREMANANDA ROY BISWAS | 93.11 | 0 | 0 | 95
1156 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Balance work of distribution pipeline including extension of pipeline for left out habitation (Purbo gopalpur)along with FHTC and restoration of roads for Bhadrapur Z-II w/s Scheme under Nalhati Sub-Division within Birbhum Division,P.H.E. Dte. | 2415/BHM | 28/08/2024 | 60 | SHIB GANGA CONSTRUCTION | 42.63 | 0 | 0 | 45
1157 | BIRBHUM | Birbhum Division | Retrofitting works for providing 10178 Nos. Functional Household Tap Connection (FHTC) to 41 Nos. draught prone villages within Birbhum District under Birbhum Division, PHE. Dte. , SM/12677 | Retrofitting | Allied Works related to FHTC for village Putka JL No 04 G.P Lokepur Block Khoirasole for ensuing draught line situation within Birbhum Division PHE Dte.( Sl. No.-05) | 188/RWS | 21/11/2024 | 30 | BHABANI ENTERPRISE | 0.95 | 0 | 0 | 90
1158 | BIRBHUM | Bolpur Mechanical | Dakshin Madanpur Piped Water Supply Scheme. , SM/12687 | New | Providing Electro-mechanical accessories and others for Dakshin Madanpur & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | 3385/Bol.MD | 16/10/2023 | 90 | R. N. S. TRADING | 54.02 | 0 | 0 | 0
1159 | BIRBHUM | Birbhum Division | Dakshin Madanpur Piped Water Supply Scheme. , SM/12687 | New | Material Requisition To Resource Division | 1391/BHM | 24/04/2023 | 0 | Resource Division | 32.83 | 0 | 0 | 0
1160 | BIRBHUM | Bolpur Mechanical | Dakshin Madanpur Piped Water Supply Scheme. , SM/12687 | New | Supply delivery of voltage correction device at head work site of Dakshin Madanpur PWSS in the district of Birbhum, under P.H.E. Dte | 3796/BOL.MD | 12/09/2024 | 30 | M/S A.D.ENTERPRISE | 5.88 | 0 | 0 | 0
1161 | BIRBHUM | Birbhum Division | Dakshin Madanpur Piped Water Supply Scheme. , SM/12687 | New | Material Requisition To Resource Division | 3260/BHM | 02/12/2024 | 0 | Resource Division | 6.91 | 0 | 0 | 0
1162 | BIRBHUM | Birbhum Division | Dakshin Madanpur Piped Water Supply Scheme. , SM/12687 | New | Sinking of 250 X 200 mm Dia, 125 m deep tubewell, 5.90 m X 4.10 m Pump room / Chlorine room with sanitary arrangements, 8.00 m X 8.00 m Pump room / Chlorine room with sanitary arrangements, 150 CuM capacity O.H.R., 100 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at DAKSHIN MADANPUR & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3130/BHM | 18/11/2024 | 365 | MALLICK CONSTRUCTION | 288.15 | 0 | 0 | 20
1163 | BIRBHUM | Bolpur Mechanical | Dakshin Madanpur Piped Water Supply Scheme. , SM/12687 | New | Supply delivery of voltage correction device at head work site of Augmentation of Ahmadpur (At Dakshin Madanpur) PWSS of Sainthia Block in the district of Birbhum, under P.H.E. Dte. | 3795/BOL.MD | 12/09/2024 | 247 | M/S SWAPAN BANERJEE | 15.07 | 0 | 0 | 80
1164 | BIRBHUM | Birbhum Division | Deoash and Adjoining Mouzas PWSS , SM/12670 | New | Material Requisition To Resource Division | 1375/BHM | 24/04/2023 | 0 | Resource Division | 34.3 | 0 | 0 | 0
1165 | BIRBHUM | Bolpur Mechanical | Deoash and Adjoining Mouzas PWSS , SM/12670 | New | Name of Work: Supply delivery of voltage correction device & laying of cable through underground trench at head work site of Deoash PWSS in the district of Birbhum, under P.H.E. Dte. | 3801/BOL.MD | 12/09/2024 | 30 | SATYAJIT GHOSH | 4.41 | 0 | 0 | 100
1166 | BIRBHUM | Bolpur Mechanical | Deoash and Adjoining Mouzas PWSS , SM/12670 | New | New service connection at Dewas PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-2023-24-316 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.41 | 0 | 0 | 0
1167 | BIRBHUM | Bolpur Mechanical | Deoash and Adjoining Mouzas PWSS , SM/12670 | New | New service connection at Dewas PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-24-25-278 | 06/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.73 | 0 | 0 | 0
1168 | BIRBHUM | Birbhum Division | Deoash and Adjoining Mouzas PWSS , SM/12670 | New | Different works related to water supply scheme at DEOASH, JASODA & JIUI and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 1194/BHM | 12/04/2023 | 792 | M/S. JAN MAHAMMAD | 1367.24 | 0 | 0 | 75
1169 | BIRBHUM | Bolpur Mechanical | Deoash and Adjoining Mouzas PWSS , SM/12670 | New | Providing Electro-mechanical accessories and others for Deoash & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2086/Bol.MD | 22/08/2023 | 589 | SUNIL RABIDAS | 28.9 | 0 | 0 | 40
1170 | BIRBHUM | Birbhum Division | Deoash and Adjoining Mouzas PWSS , SM/12670 | New | Repairing and renovation of existing Pump House, Chlorine room, Security guard room and Boundary wall for Deoash and Adjoining Mouzas PWSS Under Birbhum Division, P.H.E Dte. | 1583/BHM | 02/06/2025 | 90 | SUBHRADIP SARKAR | 18.7 | 0 | 0 | 0
1171 | BIRBHUM | Birbhum Division | Dumugram piped water supply scheme. , SM/12689 | New | Material Requisition To Resource Division | 2176/BHM | 23/06/2023 | 0 | Resource Division | 13.65 | 0 | 0 | 0
1172 | BIRBHUM | Birbhum Division | Dumugram piped water supply scheme. , SM/12689 | New | Different works related to water supply scheme at Dalima, Kahinagar & Dumurgram and its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1423/BHM | 25/04/2023 | 1090 | AKASH CONSTRUCTION | 1377.29 | 0 | 0 | 16
1173 | BIRBHUM | Bolpur Mechanical | Dumugram piped water supply scheme. , SM/12689 | New | Providing Electro-mechanical accessories and others for DURUMGRAM piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 3293/Bol.MD | 29/09/2023 | 580 | QUAZI NOZRUL ISLAM | 31.48 | 0 | 0 | 60
1174 | BIRBHUM | Bolpur Mechanical | Dumugram piped water supply scheme. , SM/12689 | New | Quotation deposit for empowering Dumurgram P/H-I Scheme in Murarai CCC under Bolpur Mechanical Division, PHE Dte. | BP-2024-25-20 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.55 | 0 | 0 | 0
1175 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR UJALPUR AND OTHER 6 NOS. MOUZAS UNDER LABPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/12069 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 0 | 92
1176 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR UJALPUR AND OTHER 6 NOS. MOUZAS UNDER LABPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/12069 | New | Road restoration work at different villages under implementation of Mini Piped Water Supply Scheme within Labpur Block having less than 100 Households under Birbhum Division PHE Dte. | 2095/BHM | 14/08/2025 | 90 | ARABINDA GHOSH | 27.75 | 0 | 0 | 60
1177 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR MAJURIA AND OTHER 19 NOS. MOUZAS UNDER DUBRAJPUR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/12073 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 81.93 | 11.36 | 92
1178 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Beja Phase-II Water Supply Scheme. , SM/12657 | Retrofitting | Additional laying of distribution system at Beja and Chuatari Mouzas for providing FHTC for Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. (Sl.No.04) | 307/RSD | 08/09/2022 | 30 | GOURANGA MONDAL | 4.77 | 0 | 0 | 100
1179 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Beja Phase-II Water Supply Scheme. , SM/12657 | Retrofitting | Additional Laying of distribution system at Terateri Mouza for providing FHTC for Beja Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. (Sl.No-06) | 309/RSD | 08/09/2022 | 30 | GOURANGA MONDAL | 4.98 | 4.98 | 100 | 50
1180 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Beja Phase-II Water Supply Scheme. , SM/12657 | Retrofitting | Providing FHTC from existing distribution system at Beja,Taratari,Chuatari & Selahat mouzas within Beja w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-03) | 306/RSD | 08/09/2022 | 30 | GOURANGA MONDAL | 4.55 | 4.53 | 100 | 50
1181 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Beja Phase-II Water Supply Scheme. , SM/12657 | Retrofitting | Additional laying of distribution system At Beja Village for providing FHTC for Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. (Sl. No-05) | 308/RSD | 08/09/2022 | 30 | GOURANGA MONDAL | 4.95 | 4.95 | 100 | 50
1182 | BIRBHUM | Birbhum Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. , SM/12659 | Retrofitting | Continution work for Supply of one no. Diesel driven Motor Cab / Maxi Cab (Air Condition) on hire Basis under the Assitant Engineer (H.Q) Birbhum Division P.H.E Dte. (Period from 01.11.2023 to 30.04.2024) | 4180/BHM | 31/10/2023 | 182 | JAMSED ALI KHAN | 0.95 | 0 | 0 | 100
1183 | BIRBHUM | Birbhum Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. , SM/12659 | Retrofitting | Continution work for Supply of one no. Diesel driven Motor Cab / Maxi Cab (Air Condition) on hire Basis under the Assitant Engineer (H.Q) Birbhum Division P.H.E Dte. (Period from 01.05.2024 to 31.10.2024) | 1373/BHM | 26/04/2024 | 183 | JAMSED ALI KHAN | 0.96 | 0 | 0 | 0
1184 | BIRBHUM | Birbhum Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. , SM/12659 | Retrofitting | Allied Functional Household Tap Connection from existing distribution system at different mouzas under Puranagram Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | 3453/BHM | 03/08/2023 | 466 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 80.63 | 0 | 0 | 65
1185 | BIRBHUM | Birbhum Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. , SM/12659 | Retrofitting | Certified that entire quantity of HSD actually purchased and consumer for the purpose of office works as per context Log Book | BP-2023-24-483 | 27/03/2024 | 0 | JAYRAM FILLING STATION | 0.48 | 0 | 0 | 0
1186 | BIRBHUM | Birbhum Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. , SM/12659 | Retrofitting | Certified that the total quantity of fuel supplied for the vehicle No. WB53B-8630 of Consumer for official purpose under Assistant Engineer (HQ) Birbhum Division for the month of Nov'23 and Dec'23 | BP-2023-24-422 | 07/03/2024 | 0 | JAYRAM FILLING STATION | 0.48 | 0 | 0 | 0
1187 | BIRBHUM | Birbhum Division | Retrofitting work for providing Functional Household Tap Connection(FHTC) within the Command area PURANAGRAM(PHASE-II) WATER SUPPLY SCHEME of MD Bazar Block under Birbhum Division, P.H.E. Dte. , SM/12659 | Retrofitting | Continuation work for Supply of one no. Diesel-driven Motor Cab / Maxi Cab (Air Condition) on hire Basis under the Assitant Engineer (H.Q) Birbhum Division P.H.E Dte. (Period from 01.11.2024 to 30.04.2025) | 2969/BHM | 30/10/2024 | 182 | JAMSED ALI KHAN | 0.96 | 0 | 0 | 100
1188 | BIRBHUM | Birbhum Division | KANAIPUR and Adjoining Mouzas PWSS , SM/12672 | New | Material Requisition To Resource Division | 1429/BHM | 25/04/2023 | 0 | Resource Division | 15.61 | 0 | 0 | 0
1189 | BIRBHUM | Bolpur Mechanical | KANAIPUR and Adjoining Mouzas PWSS , SM/12672 | New | Providing Electro-mechanical accessories and others for KANAIPUR piped water supply scheme, Nalhati - I block, under Bolpur Mechanical Division PHE Dte. | 3561/BOL.MD | 04/12/2023 | 60 | PRADIP KUMAR DHABAL | 27.77 | 0 | 0 | 90
1190 | BIRBHUM | Bolpur Mechanical | KANAIPUR and Adjoining Mouzas PWSS , SM/12672 | New | WBSEDCL QUOTATION FOR KANAIPUR W S P H NO I WS SCHEME | BP-23-24-240 | 29/01/2024 | 0 | WBSEDCL | 5.09 | 0 | 0 | 0
1191 | BIRBHUM | Bolpur Mechanical | KANAIPUR and Adjoining Mouzas PWSS , SM/12672 | New | WBSEDCL QUOTATION FOR KANAIPUR P H NO.II WS SCHEME | BP-23-24-241 | 29/01/2024 | 0 | WBSEDCL | 0.23 | 0 | 0 | 0
1192 | BIRBHUM | Birbhum Division | KANAIPUR and Adjoining Mouzas PWSS , SM/12672 | New | Different works related to water supply scheme at Majhkaltia, Sahira & KANAPIUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 1348/BHM | 20/04/2023 | 835 | M/S GOUTAM DAS | 1594.34 | 0 | 0 | 28
1193 | BIRBHUM | Birbhum Division | KANAIPUR and Adjoining Mouzas PWSS , SM/12672 | New | Restoration of Roads, pucca drain including Jack pushing & Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Kanaipur piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | 1507/BHM | 23/05/2025 | 90 | M/S GOUTAM DAS | 41.79 | 0 | 0 | 10
1194 | BIRBHUM | Birbhum Division | Math Basori Piped Water Supply Scheme. , SM/13627 | New | Material Requisition To Resource Division | 1549/BHM | 26/04/2023 | 0 | Resource Division | 18.63 | 0 | 0 | 0
1195 | BIRBHUM | Bolpur Mechanical | Math Basori Piped Water Supply Scheme. , SM/13627 | New | Quotation deposit for empowering Math Basuri Water Supply Scheme P/H -II in Paikar CCC under Bolpur Mechanical Division, PHE Dte | BP-2024-2025-47 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.21 | 0 | 0 | 0
1196 | BIRBHUM | Bolpur Mechanical | Math Basori Piped Water Supply Scheme. , SM/13627 | New | Quotation deposit for empowering Math Basuri Water Supply Scheme P/H -I in Paikar CCC under Bolpur Mechanical Division, PHE Dte | BP-2024-2025-46 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.03 | 0 | 0 | 0
1197 | BIRBHUM | Birbhum Division | Math Basori Piped Water Supply Scheme. , SM/13627 | New | Different works related to water supply scheme at Jijigram, Math Basori & Bilaspur and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3019/BHM | 14/07/2023 | 961 | SUNIL RABI DAS | 1250.5 | 0 | 0 | 60
1198 | BIRBHUM | Birbhum Division | Math Basori Piped Water Supply Scheme. , SM/13627 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
1199 | BIRBHUM | Central Drilling | Kurumsaha Piped Water Supply Scheme. , SM/13628 | New | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL BY DEPARTMENTAL RIG MACHINE IN KURUMSAHA PWSS (TW-I), BLOCK-SAINTHIA, BIRBHUM DISTRICT UNDER CDD, PHE DTE. | 398/CMSD-I | 05/08/2022 | 15 | C.M. ENTERPRISE | 3.77 | 2.5 | 66.28 | 0
1200 | BIRBHUM | Central Drilling | Kurumsaha Piped Water Supply Scheme. , SM/13628 | New | PROVIDING DRLLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR Kurumsaha W/S SCHEME (TW-II), SAINTHIA BLOCK, UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | 1428/CDD | 29/11/2022 | 30 | C.M. ENTERPRISE | 10.49 | 9.15 | 87.23 | 0
1201 | BIRBHUM | Central Drilling | Kurumsaha Piped Water Supply Scheme. , SM/13628 | New | PROVIDING TUBE WELL MATERIALS, CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL IN KURUMSAHA PWSS (TW-I), SAINTHIA BLOCK, BIRBHUM DISTRICT UNDER CDD, PHE DTE. | 382/CMSD-I | 05/08/2022 | 15 | C.M. ENTERPRISE | 4.18 | 3.79 | 90.77 | 0
1202 | BIRBHUM | Central Drilling | Kurumsaha Piped Water Supply Scheme. , SM/13628 | New | SUPPLY & DELIVERY OF CONSUMBLES WITH OTHER WORKS AT SITE FOR CONSTTRUCTION OF TUBE WELL IN KURUMSAHA PWSS (TW-I), BLOCK-SAINTHIA, BIRBHUM DISTRICT UNDER CDD, PHE DTE. | 390/CMSD-I | 05/08/2022 | 15 | C.M. ENTERPRISE | 2.66 | 2.64 | 99.38 | 0
1203 | BIRBHUM | Birbhum Division | Kurumsaha Piped Water Supply Scheme. , SM/13628 | New | Material Requisition To Resource Division | 1366/BHM | 24/04/2023 | 0 | Resource Division | 19.69 | 0 | 0 | 0
1204 | BIRBHUM | Bolpur Mechanical | Kurumsaha Piped Water Supply Scheme. , SM/13628 | New | WBSEDCL QUOTATION FOR KURUMSAHA P.H.NO.I | BP-2023-2024-63 | 02/08/2023 | 0 | WBSEDCL | 3.85 | 0 | 0 | 0
1205 | BIRBHUM | Bolpur Mechanical | Kurumsaha Piped Water Supply Scheme. , SM/13628 | New | wbsedcl quotation for kurumsaha p.h.no.ii ws scheme | BP-23-24-70 | 09/08/2023 | 0 | WBSEDCL | 3.91 | 0 | 0 | 0
1206 | BIRBHUM | Bolpur Mechanical | Kurumsaha Piped Water Supply Scheme. , SM/13628 | New | Providing Electro-mechanical accessories and others for Kurumsaha & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2090/Bol.MD | 22/08/2023 | 679 | MITRA ENTERPRISE | 28.04 | 0 | 0 | 80
1207 | BIRBHUM | Birbhum Division | Kurumsaha Piped Water Supply Scheme. , SM/13628 | New | Different works related to water supply scheme at DERPUR, KURUMSAHA & MATIARA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 1245/BHM | 17/04/2023 | 1074 | BRAHMA CONSTRUCTION COMPANY | 978.83 | 0 | 0 | 65
1208 | BIRBHUM | Birbhum Division | RAUTARA PIPED WATER SUPPLY SCHEME. , SM/12888 | New | Material Requisition To Resource Division | 1565/BHM | 26/04/2023 | 0 | Resource Division | 5.78 | 0 | 0 | 0
1209 | BIRBHUM | Bolpur Mechanical | RAUTARA PIPED WATER SUPPLY SCHEME. , SM/12888 | New | WBSEDCL QUOTATION BILL FOR RAUTARA WS SCHEME P.H.NO.I | BP-23-24-95 | 26/09/2023 | 0 | WBSEDCL | 4.22 | 0 | 0 | 0
1210 | BIRBHUM | Bolpur Mechanical | RAUTARA PIPED WATER SUPPLY SCHEME. , SM/12888 | New | WBSEDCL QUOTATION FOR RAUTARA WS SCHEME P H .NO.2 | BP-23-24-197 | 19/12/2023 | 0 | WBSEDCL | 4.53 | 0 | 0 | 0
1211 | BIRBHUM | Birbhum Division | RAUTARA PIPED WATER SUPPLY SCHEME. , SM/12888 | New | Different works related to water supply scheme at RAUTARA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 900/BHM | 22/03/2023 | 710 | M/S.KHAN CHOWDHURY BROTHERS AND CO. | 216.16 | 0 | 0 | 80
1212 | BIRBHUM | Bolpur Mechanical | RAUTARA PIPED WATER SUPPLY SCHEME. , SM/12888 | New | Providing Electro-mechanical accessories and others for Rautara PWSS at Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | 1496/Bol.MD | 17/07/2023 | 870 | M/S SWAPAN BANERJEE | 27.11 | 0 | 0 | 80
1213 | BIRBHUM | Birbhum Division | Chakpara piped water supply scheme. , SM/13638 | New | Material Requisition To Resource Division | 1558/BHM | 26/04/2023 | 0 | Resource Division | 32.34 | 0 | 0 | 0
1214 | BIRBHUM | Birbhum Division | Chakpara piped water supply scheme. , SM/13638 | New | Material Requisition To Resource Division | 228/BHM | 24/01/2024 | 0 | Resource Division | 3.08 | 0 | 0 | 0
1215 | BIRBHUM | Bolpur Mechanical | Chakpara piped water supply scheme. , SM/13638 | New | Quotation for Chakpara PWSS P/H no-2 ( block: Rampurhat I) | BP-2024-2025-22 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.83 | 0 | 0 | 0
1216 | BIRBHUM | Bolpur Mechanical | Chakpara piped water supply scheme. , SM/13638 | New | Quotation for new service connection at Chakpara PWSS P/H -1 ( Block : Rampurhat -1) | BP-2024-2025-24 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.09 | 0 | 0 | 0
1217 | BIRBHUM | Bolpur Mechanical | Chakpara piped water supply scheme. , SM/13638 | New | Providing Electro-mechanical accessories and others for Chakpara & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 3525/Bol.MD | 29/11/2023 | 759 | M. S. ENTERPRISE | 39.06 | 0 | 0 | 60
1218 | BIRBHUM | Birbhum Division | Chakpara piped water supply scheme. , SM/13638 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, Boundary wall related to water supply scheme at Chakpara Piped Water Supply Scheme within Rampurhat-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 1584/BHM | 02/06/2025 | 90 | ABUL HASNATH | 26.1 | 0 | 0 | 0
1219 | BIRBHUM | Birbhum Division | Nabagram Piped Water Supply Scheme. , SM/13646 | New | Continuation Work Order for Preparation & Submission of DPR for (Nabagram) Water Supply Scheme under Rampurhat-II Development Block. | 217/RSD | 21/06/2022 | 45 | ECO CARE | 4 | 0 | 0 | 100
1220 | BIRBHUM | Birbhum Division | Nabagram Piped Water Supply Scheme. , SM/13646 | New | Material Requisition To Resource Division | 1554/BHM | 26/04/2023 | 0 | Resource Division | 26.05 | 0 | 0 | 0
1221 | BIRBHUM | Birbhum Division | Nabagram Piped Water Supply Scheme. , SM/13646 | New | Material Requisition To Resource Division | 227/BHM | 24/01/2024 | 0 | Resource Division | 0.92 | 0 | 0 | 0
1222 | BIRBHUM | Bolpur Mechanical | Nabagram Piped Water Supply Scheme. , SM/13646 | New | Quotation for new service connection at Nabagram TW No-I (Block-Rampurhat-II) |  | 13/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.85 | 0 | 0 | 0
1223 | BIRBHUM | Bolpur Mechanical | Nabagram Piped Water Supply Scheme. , SM/13646 | New | Quotation for new service connection at Nabagram TW No-II (Block-Rampurhat-II) |  | 13/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.49 | 0 | 0 | 0
1224 | BIRBHUM | Bolpur Mechanical | Nabagram Piped Water Supply Scheme. , SM/13646 | New | WBSEDCL QUOTATION FOR NABAGRAM TW-II | BP-2023-24-311 | 18/03/2024 | 0 | WBSEDCL | 3.49 | 0 | 0 | 0
1225 | BIRBHUM | Bolpur Mechanical | Nabagram Piped Water Supply Scheme. , SM/13646 | New | WBSEDCL QUOTATION FOR NABAGRAM TW-1 | BP-2023-24-312 | 18/03/2024 | 0 | WBSEDCL | 2.85 | 0 | 0 | 0
1226 | BIRBHUM | Birbhum Division | Nabagram Piped Water Supply Scheme. , SM/13646 | New | Different works related to water supply scheme at NABAGRAM, SAHAPUR & SHASPUR and its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3522/BHM | 11/08/2023 | 821 | SUNIL RABI DAS | 1157.77 | 0 | 0 | 40
1227 | BIRBHUM | Bolpur Mechanical | Nabagram Piped Water Supply Scheme. , SM/13646 | New | Providing Electro-mechanical accessories and others for Nabagram PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 2233/Bol.MD | 12/09/2023 | 658 | M. S. ENTERPRISE | 45.35 | 0 | 0 | 80
1228 | BIRBHUM | Bolpur Mechanical | Nabagram Piped Water Supply Scheme. , SM/13646 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Nabagram PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 526/BOL.MD | 14/03/2024 | 383 | MENAKA ENTERPRISE | 7.62 | 0 | 0 | 40
1229 | BIRBHUM | Birbhum Division | SHIRSHA PIPED WATER SUPPLY SCHEME , SM/13647 | New | Material Requisition To Resource Division | 1527/BHM | 26/04/2023 | 0 | Resource Division | 19.61 | 0 | 0 | 0
1230 | BIRBHUM | Birbhum Division | SHIRSHA PIPED WATER SUPPLY SCHEME , SM/13647 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for SHIRSHA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - B) | 311/BSD | 17/08/2022 | 90 | M/S R DUTTA & CO. | 1.43 | 0 | 0 | 100
1231 | BIRBHUM | Birbhum Division | SHIRSHA PIPED WATER SUPPLY SCHEME , SM/13647 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for SHIRSHA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - A) | 284/BSD | 25/07/2022 | 90 | M/S R DUTTA & CO. | 4.93 | 0 | 0 | 100
1232 | BIRBHUM | Central Drilling | SHIRSHA PIPED WATER SUPPLY SCHEME , SM/13647 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1233 | BIRBHUM | Birbhum Division | SHIRSHA PIPED WATER SUPPLY SCHEME , SM/13647 | New | Different works related to water supply scheme at MATIKONA, NOHONA, SHIRSHA & CHUNPALASHI Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 3598/BHM | 21/08/2023 | 949 | BIPIN KUMAR SINGH | 2395.67 | 0 | 0 | 4
1234 | BIRBHUM | Birbhum Division | ULANDI PIPED WATER SUPPLY SCHEME , SM/13654 | New | Material Requisition To Resource Division | 1575/BHM | 26/04/2023 | 0 | Resource Division | 15.86 | 0 | 0 | 0
1235 | BIRBHUM | Birbhum Division | ULANDI PIPED WATER SUPPLY SCHEME , SM/13654 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for ULANDI Piped Water Supply Scheme under Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte" | 154/BSD | 18/04/2022 | 90 | M/S R DUTTA & CO. | 3.93 | 0 | 0 | 100
1236 | BIRBHUM | Birbhum Division | ULANDI PIPED WATER SUPPLY SCHEME , SM/13654 | New | Material Requisition To Resource Division | 2381/BHM | 27/08/2024 | 0 | Resource Division | 9.66 | 0 | 0 | 0
1237 | BIRBHUM | Central Drilling | ULANDI PIPED WATER SUPPLY SCHEME , SM/13654 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1238 | BIRBHUM | Birbhum Division | ULANDI PIPED WATER SUPPLY SCHEME , SM/13654 | New | Construction of 150 CUM capacity OHR including Soil Investigation, 5.09 m X 4.1 m Pump House/Chlorine Room with Sanitary, Laying of Rising Main and Distribution System and FHTC and Construction of Boundary Wall Approach Road and Land Development works at H/W site and 2 nd T/W site under Ulandi PIPED WATER SUPPLY SCHEME within Illambazar Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 2037/BHM | 19/07/2024 | 365 | SHIBU BISWAS, BADARTALA , BASIRHAT, PIN - 743292 | 413.14 | 0 | 0 | 5
1239 | BIRBHUM | Birbhum Division | Podda Piped Water Supply Scheme , SM/13714 | New | Preparation & Submission of DPR for (Podda) Water Supply Scheme under Rampurhat-II Development Block. | 171/RSD | 29/04/2022 | 45 | ECO CARE | 2.91 | 0 | 0 | 100
1240 | BIRBHUM | Birbhum Division | Podda Piped Water Supply Scheme , SM/13714 | New | Material Requisition To Resource Division | 1542/BHM | 26/04/2023 | 0 | Resource Division | 12.98 | 0 | 0 | 0
1241 | BIRBHUM | Bolpur Mechanical | Podda Piped Water Supply Scheme , SM/13714 | New | Providing Electro-mechanical accessories and others for Podda PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 1749/Bol.MD | 27/07/2023 | 60 | S.K.ELECTRICALS | 44.24 | 0 | 0 | 90
1242 | BIRBHUM | Bolpur Mechanical | Podda Piped Water Supply Scheme , SM/13714 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Podda PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 528/BOL.MD | 14/03/2024 | 60 | M/S. S.G ENTERPRISE | 7.62 | 0 | 0 | 0
1243 | BIRBHUM | Bolpur Mechanical | Podda Piped Water Supply Scheme , SM/13714 | New | Supply and Delivery of Sub-Mersible Pumping Machineries inconection with Providing Electro-mechanical accessories and others for Podda PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 687/AE-III | 08/04/2024 | 14 | S.K.ELECTRICALS | 1.58 | 0 | 0 | 0
1244 | BIRBHUM | Birbhum Division | Podda Piped Water Supply Scheme , SM/13714 | New | Material Requisition To Resource Division | 222/BHM | 24/01/2024 | 0 | Resource Division | 3.26 | 0 | 0 | 0
1245 | BIRBHUM | Bolpur Mechanical | Podda Piped Water Supply Scheme , SM/13714 | New | wbsedcl quotation money for poddsa p.h.no.1 pwss | BP-23-24-154 | 04/12/2023 | 0 | WBSEDCL | 4.8 | 0 | 0 | 0
1246 | BIRBHUM | Bolpur Mechanical | Podda Piped Water Supply Scheme , SM/13714 | New | wbsedcl quotation money for podda pwss | BP-23-24-153 | 04/12/2023 | 0 | WBSEDCL | 2.91 | 0 | 0 | 0
1247 | BIRBHUM | Birbhum Division | Podda Piped Water Supply Scheme , SM/13714 | New | Different works related to water supply scheme at PODDA & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under Birbhum Division, PHE Dte | 1310/BHM | 19/04/2023 | 973 | P. C. CONSTRUCTION | 210.99 | 0 | 0 | 80
1248 | BIRBHUM | Birbhum Division | Purba Anantapur Piped Water Supply Scheme , SM/13715 | New | Continuation Work Order for Preparation & Submission of DPR for (Purba Anantapur) Water Supply Scheme under Rampurhat-II Development Block. | 235/RSD | 04/07/2022 | 45 | ECO CARE | 3.63 | 0 | 0 | 100
1249 | BIRBHUM | Birbhum Division | Purba Anantapur Piped Water Supply Scheme , SM/13715 | New | Material Requisition To Resource Division | 1539/BHM | 26/04/2023 | 0 | Resource Division | 56.84 | 0 | 0 | 0
1250 | BIRBHUM | Birbhum Division | Purba Anantapur Piped Water Supply Scheme , SM/13715 | New | Material Requisition To Resource Division | 223/BHM | 24/01/2024 | 0 | Resource Division | 4.31 | 0 | 0 | 0
1251 | BIRBHUM | Bolpur Mechanical | Purba Anantapur Piped Water Supply Scheme , SM/13715 | New | WBSEDCL QUOTATION FOR PURBA ANANTAPUR WS SCHEME UNDER BOL MD | BP-23-24-200 | 28/12/2023 | 0 | WBSEDCL | 3.81 | 0 | 0 | 0
1252 | BIRBHUM | Bolpur Mechanical | Purba Anantapur Piped Water Supply Scheme , SM/13715 | New | WBSEDCL QUOTATION FOR PURBA ANANTAPUR W S P H NO I WS SCHEME | BP-23-24-255 | 06/02/2024 | 0 | WBSEDCL | 5.65 | 0 | 0 | 0
1253 | BIRBHUM | Bolpur Mechanical | Purba Anantapur Piped Water Supply Scheme , SM/13715 | New | Providing Electro-mechanical accessories and others for Purba Anantapur PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 2231/Bol.MD | 12/09/2023 | 293 | ORIENTAL ENGINEERING CO. | 44.37 | 0 | 0 | 40
1254 | BIRBHUM | Birbhum Division | Purba Anantapur Piped Water Supply Scheme , SM/13715 | New | Different works related to water supply scheme at PURBA ANANTAPUR & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 1193/BHM | 12/04/2023 | 450 | MEHEBUB RAHAMAN | 257.78 | 0 | 0 | 80
1255 | BIRBHUM | Birbhum Division | KASHERHAT PIPED WATER SUPPLY SCHEME. , SM/12903 | New | Material Requisition To Resource Division | 1387/BHM | 24/04/2023 | 0 | Resource Division | 20.85 | 0 | 0 | 0
1256 | BIRBHUM | Bolpur Mechanical | KASHERHAT PIPED WATER SUPPLY SCHEME. , SM/12903 | New | New service connection at Kasherhat PH-II W/S scheme Block-Suri II under Bolpur Mechanical Division,PHE Dte. | BP-2024-2025-64 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.21 | 0 | 0 | 0
1257 | BIRBHUM | Bolpur Mechanical | KASHERHAT PIPED WATER SUPPLY SCHEME. , SM/12903 | New | New service connection at Kasherhat PH-I W/S scheme Block-Suri II under Bolpur Mechanical Division,PHE Dte. | BP-2024-2025-63 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.72 | 0 | 0 | 0
1258 | BIRBHUM | Birbhum Division | KASHERHAT PIPED WATER SUPPLY SCHEME. , SM/12903 | New | Different works for KASHERHAT & Sehana and its adjoining mouzas water supply scheme within SURI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 4138/BHM | 18/10/2023 | 1079 | PASCON | 975.41 | 0 | 0 | 60
1259 | BIRBHUM | Bolpur Mechanical | KASHERHAT PIPED WATER SUPPLY SCHEME. , SM/12903 | New | Providing Electro-mechanical accessories and others for Kasherhat PWSS at Suri - II Block under Bolpur Mechanical Division PHE Dte. | 2076/BOL.MD. | 21/08/2023 | 667 | MITRA ENTERPRISE | 28.66 | 0 | 0 | 90
1260 | BIRBHUM | Birbhum Division | FEUGRAM PIPED WATER SUPPLY SCHEME , SM/13477 | New | Preparation & Submission of Detail Project Report (DPR) for FEUGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. | 89/BSD | 10/03/2022 | 90 | RADIANT | 4.87 | 0 | 0 | 100
1261 | BIRBHUM | Birbhum Division | FEUGRAM PIPED WATER SUPPLY SCHEME , SM/13477 | New | Material Requisition To Resource Division | 1449/BHM | 25/04/2023 | 0 | Resource Division | 24.16 | 0 | 0 | 0
1262 | BIRBHUM | Birbhum Division | FEUGRAM PIPED WATER SUPPLY SCHEME , SM/13477 | New | "Construction of 200CuM. capacity O.H.R. with Soil Investigation,5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements.laying of Rising Main,Distribution System with FHTC and different works related to FEUGRAM PIPED WATER SUPPLY SCHEME (TSM/015471) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte." | 2115/BHM | 29/07/2024 | 365 | BANI ENGINEERING CO. | 483.16 | 0 | 0 | 0
1263 | BIRBHUM | Birbhum Division | FEUGRAM PIPED WATER SUPPLY SCHEME , SM/13477 | New | Material Requisition To Resource Division | 2441/BHM | 30/08/2024 | 0 | Resource Division | 10.68 | 0 | 0 | 0
1264 | BIRBHUM | Central Drilling | FEUGRAM PIPED WATER SUPPLY SCHEME , SM/13477 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1265 | BIRBHUM | Bolpur Mechanical | FEUGRAM PIPED WATER SUPPLY SCHEME , SM/13477 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Feugram Water supply Scheme (T/W-I & II), Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | 4532/BOL.MD | 20/12/2024 | 120 | SATYAJIT GHOSH | 75.35 | 0 | 0 | 40
1266 | BIRBHUM | Birbhum Division | RAMKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/13950 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for RAMKRISHNAPUR Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte. ". | 180/BSD | 05/05/2022 | 90 | RADIANT | 4.8 | 0 | 0 | 100
1267 | BIRBHUM | Birbhum Division | RAMKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/13950 | New | Material Requisition To Resource Division | 2480/BHM | 03/09/2024 | 0 | Resource Division | 11.16 | 0 | 0 | 0
1268 | BIRBHUM | Central Drilling | RAMKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/13950 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1269 | BIRBHUM | Bolpur Mechanical | RAMKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/13950 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Benga Chatra & Ramkrishnapur Water supply Scheme, Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | 4538/BOL.MD | 20/12/2024 | 120 | MENAKA ENTERPRISE | 73.34 | 0 | 0 | 50
1270 | BIRBHUM | Birbhum Division | RAMKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/13950 | New | Construction of 250 CuM. Capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, laying of Rising Main, Distribution System with FHTC and different works related to RAMKRISHNAPUR PIPED WATER SUPPLY SCHEME (TSM/016099) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte. | 2239/BHM | 13/08/2024 | 594 | DILIP KUMAR MONDAL | 480.2 | 0 | 0 | 15
1271 | BIRBHUM | Birbhum Division | RAMKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/13950 | New | Restoration of Road, damaged during laying of pipe line under Ramkrishnapur PWSS of Bolpur Sub-Division within Birbhum Division, P.H.E. Dte. | 2763/BHM | 29/10/2025 | 90 | DILIP KUMAR MONDAL | 19.25 | 0 | 0 | 0
1272 | BIRBHUM | Birbhum Division | Paniara Piped Water Supply Scheme. , SM/12907 | New | Material Requisition To Resource Division | 1585/BHM | 26/04/2023 | 0 | Resource Division | 8.69 | 0 | 0 | 0
1273 | BIRBHUM | Bolpur Mechanical | Paniara Piped Water Supply Scheme. , SM/12907 | New | Providing Electro-mechanical accessories and others for PANIARA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 3299/Bol.MD | 29/09/2023 | 550 | M/S. UTTAM KUMAR CHATTERJEE | 26 | 0 | 0 | 70
1274 | BIRBHUM | Birbhum Division | Paniara Piped Water Supply Scheme. , SM/12907 | New | Different works related to water supply scheme at PANIARA & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 1040/BHM | 15/03/2024 | 60 | ANIRUDDHA FARUQUE | 65.65 | 0 | 0 | 0
1275 | BIRBHUM | Birbhum Division | KHAYERBANI PIPED WATER SUPPLY SCHEME , SM/14677 | New | Material Requisition To Resource Division | 1599/BHM | 27/04/2023 | 0 | Resource Division | 19.67 | 0 | 0 | 0
1276 | BIRBHUM | Birbhum Division | KHAYERBANI PIPED WATER SUPPLY SCHEME , SM/14677 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for KHAYERBANI Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | 163/BSD | 25/04/2022 | 180 | APEX ENGINEERING | 3.16 | 0 | 0 | 100
1277 | BIRBHUM | Birbhum Division | KHAYERBANI PIPED WATER SUPPLY SCHEME , SM/14677 | New | Material Requisition To Resource Division | 2387/BHM | 27/08/2024 | 0 | Resource Division | 7.2 | 0 | 0 | 0
1278 | BIRBHUM | Central Drilling | KHAYERBANI PIPED WATER SUPPLY SCHEME , SM/14677 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1279 | BIRBHUM | Birbhum Division | KHAYERBANI PIPED WATER SUPPLY SCHEME , SM/14677 | New | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1948/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0 | 0
1280 | BIRBHUM | Bolpur Mechanical | KHAYERBANI PIPED WATER SUPPLY SCHEME , SM/14677 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Khayerbani PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | 330/BOL.MD | 19/02/2025 | 120 | SARVATAH PROJECTS PRIVATE LIMITED | 74.48 | 0 | 0 | 0
1281 | BIRBHUM | Bolpur Mechanical | Khanpur Piped Water Supply Scheme. , SM/14085 | New | Providing Electro-mechanical accessories and others for KHANPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 3296/Bol.MD | 29/09/2023 | 60 | DEY ENTERPRISE | 27.42 | 0 | 0 | 0
1282 | BIRBHUM | Birbhum Division | Khanpur Piped Water Supply Scheme. , SM/14085 | New | Material Requisition To Resource Division | 1624/BHM | 28/04/2023 | 0 | Resource Division | 18.95 | 0 | 0 | 0
1283 | BIRBHUM | Bolpur Mechanical | Khanpur Piped Water Supply Scheme. , SM/14085 | New | New service connection at Khanpur PWSS under Dubrajpur Block, under Bolpur Mech. Division,PHE. Dte. |  | 13/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.35 | 0 | 0 | 0
1284 | BIRBHUM | Bolpur Mechanical | Khanpur Piped Water Supply Scheme. , SM/14085 | New | wbsedcl quotation for khanpur pump house no-i | BP-2023-24-288 | 04/03/2024 | 0 | WBSEDCL | 3.35 | 0 | 0 | 0
1285 | BIRBHUM | Birbhum Division | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14125 | New | Material Requisition To Resource Division | 1460/BHM | 25/04/2023 | 0 | Resource Division | 103.64 | 0 | 0 | 0
1286 | BIRBHUM | Bolpur Mechanical | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14125 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Lachhiator PWSS under Rampurhat - I Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 525/BOL.MD | 14/03/2024 | 60 | ABHISEK ENGTNEERING CONCERN | 7.61 | 0 | 0 | 0
1287 | BIRBHUM | Birbhum Division | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14125 | New | Continuation Work Order for Preparation & Submission of DPR for (Lachhiator) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | 295/RSD | 07/09/2022 | 90 | ENVIROTECH SOLUTIONS | 3.22 | 0 | 0 | 100
1288 | BIRBHUM | Birbhum Division | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14125 | New | Continuation Work Order for Preparation & Submission of DPR for (Lachhiator) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | 403/RSD | 13/10/2022 | 90 | ENVIROTECH SOLUTIONS | 3.5 | 0 | 0 | 100
1289 | BIRBHUM | Birbhum Division | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14125 | New | Material Requisition To Resource Division | 204/BHM | 22/01/2024 | 0 | Resource Division | 8.19 | 0 | 0 | 0
1290 | BIRBHUM | Bolpur Mechanical | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14125 | New | New service connection at Lachiatore PH-IV PWSS under Bol.MD, P.H.E Dte. | BP-24-25-185 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.14 | 0 | 0 | 0
1291 | BIRBHUM | Bolpur Mechanical | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14125 | New | WBSEDCL QUOTATION FOR LACHIATORE PIPED WS SCHEME PH NO.II | BP-23-24-282 | 22/02/2024 | 0 | WBSEDCL | 2.54 | 0 | 0 | 0
1292 | BIRBHUM | Bolpur Mechanical | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14125 | New | WBSEDCL QUOTATION FOR LOCHIATORE PIPED WS SCHEME PH NO.I | BP-23-24-284 | 22/02/2024 | 0 | WBSEDCL | 4.19 | 0 | 0 | 0
1293 | BIRBHUM | Bolpur Mechanical | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14125 | New | WBSEDCL QUOTATION FOR LACHIATOR W/S SCHEME PH-3 | BP-24-25-03 | 09/04/2024 | 0 | WBSEDCL | 3.39 | 0 | 0 | 0
1294 | BIRBHUM | Birbhum Division | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14125 | New | Different works related to water supply scheme at LACHHIATOR, DAKSHINGRAM, SONJ & SHIBGRAM and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 4142/BHM | 19/10/2023 | 805 | B RAI CONSTRUCTION COMPANY | 2003.84 | 0 | 0 | 60
1295 | BIRBHUM | Bolpur Mechanical | Lachhiator Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/14125 | New | Providing Electro-mechanical accessories and others for Lachhiator PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | 3479/Bol.MD | 07/11/2023 | 60 | DEY ENTERPRISE | 65.96 | 0 | 0 | 80
1296 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR ALALPUR AND OTHER 5 NOS. MOUZAS UNDER NALHATI-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/14038 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 0 | 92
1297 | BIRBHUM | Birbhum Division | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. , SM/15236 | Augmentation | Material Requisition To Resource Division | 1120/BHM | 10/04/2023 | 0 | Resource Division | 20.81 | 0 | 0 | 0
1298 | BIRBHUM | Birbhum Division | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. , SM/15236 | Augmentation | Material Requisition To Resource Division | 973/BHM | 27/03/2023 | 0 | Resource Division | 81.55 | 0 | 0 | 0
1299 | BIRBHUM | Birbhum Division | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. , SM/15236 | Augmentation | Material Requisition To Resource Division | 234/BHM | 24/01/2024 | 0 | Resource Division | 1.85 | 0 | 0 | 0
1300 | BIRBHUM | Bolpur Mechanical | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. , SM/15236 | Augmentation | Quotation for new service connection at Dunigram (Zone-II) TW No-I (Block-Rampurhat-II) | bp-23-24-566 | 20/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.83 | 0 | 0 | 0
1301 | BIRBHUM | Bolpur Mechanical | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. , SM/15236 | Augmentation | Quotation for new service connection at Dunigram (Zone-I) TW No-III (Block-Rampurhat-II) | BP-23-24-307 | 21/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.64 | 0 | 0 | 0
1302 | BIRBHUM | Bolpur Mechanical | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. , SM/15236 | Augmentation | Providing and Installation of Submersible pumping Machinaries at newly sunk Ground Water Based Tube Wells and allied works at Augmentation of Dunigram [( Zone-I, Pump House No - II ) and ( Zone-II, Pump House No - I & II )] Piped Water Supply Scheme, Block-Rampurhat-II under Bolpur Mechanical Division.. | 2130/Bol.MD | 25/08/2023 | 675 | M. S. ENTERPRISE | 76.88 | 0 | 0 | 65
1303 | BIRBHUM | Birbhum Division | Augmentation of Ground water Based piped water supply scheme for Dunigram (Zone-I & II), Block- Rampurhat-II, Dist- Birbhum, Within Birbhum Division, PHE Dte. , SM/15236 | Augmentation | Sinking of Tubewell, Construction of OHR, Construction of Boundary wall, pump house and laying distribution system along with FHTC works at Augmentation of Ground Water Based Dunigram Zone-I & Zone-II Piped Water Supply Scheme within Rampurhat-II Block under Birbhum Division, PHE Dte. (2nd Call) | 4161/BHM | 30/10/2023 | 790 | M/S GOUTAM DAS | 509.85 | 0 | 0 | 50
1304 | BIRBHUM | Birbhum Division | RAYEN PIPED WATER SUPPLY SCHEME , SM/14957 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for RAYEN Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 196/BSD | 19/05/2022 | 90 | RADIANT | 2.91 | 0 | 0 | 100
1305 | BIRBHUM | Birbhum Division | RAYEN PIPED WATER SUPPLY SCHEME , SM/14957 | New | Material Requisition To Resource Division | 1551/BHM | 26/04/2023 | 0 | Resource Division | 13.45 | 0 | 0 | 0
1306 | BIRBHUM | Birbhum Division | RAYEN PIPED WATER SUPPLY SCHEME , SM/14957 | New | Material Requisition To Resource Division | 2385/BHM | 27/08/2024 | 0 | Resource Division | 4.3 | 0 | 0 | 0
1307 | BIRBHUM | Central Drilling | RAYEN PIPED WATER SUPPLY SCHEME , SM/14957 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1308 | BIRBHUM | Birbhum Division | RAYEN PIPED WATER SUPPLY SCHEME , SM/14957 | New | Construction of 250 & 150 CuM. Capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements Laying of Rising Main, Distribution System with FHTC including different works related to SANTOSHPUR / NAWADA PALANDI /PAPURI / SAJNOR / RAYEN PIPED WATER SUPPLY SCHEME (5 Nos Scheme) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division PHE DTE. | 1951/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2322.64 | 0 | 0 | 5
1309 | BIRBHUM | Birbhum Division | Dhamara Piped Water Supply Scheme. , SM/14898 | New | Material Requisition To Resource Division | 1621/BHM | 28/04/2023 | 0 | Resource Division | 9.04 | 0 | 0 | 0
1310 | BIRBHUM | Bolpur Mechanical | Dhamara Piped Water Supply Scheme. , SM/14898 | New | WBSEDCL Quotation for Dhamara Piped Water Supply Scheme. | BP-23-24-266 | 07/02/2024 | 0 | WBSEDCL | 3.01 | 0 | 0 | 0
1311 | BIRBHUM | Bolpur Mechanical | Dhamara Piped Water Supply Scheme. , SM/14898 | New | Empowering for new connection at Chakraipur Pump House -II in Mollarpur CCC under Bolpur Mechanical Division, PHE,Dte. | BP-2024-2025-50 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.52 | 0 | 0 | 0
1312 | BIRBHUM | Birbhum Division | Dhamara Piped Water Supply Scheme. , SM/14898 | New | Different works related to water supply scheme at DHAMARA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 1244/BHM | 17/04/2023 | 807 | ASHIM KUMAR CHAKRABORTY | 341.34 | 0 | 0 | 65
1313 | BIRBHUM | Bolpur Mechanical | Dhamara Piped Water Supply Scheme. , SM/14898 | New | Providing Electro-mechanical accessories and others for DHAMARA piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | 1499/Bol.MD | 17/07/2023 | 624 | UTTAM KUMAR CHATTERJEE | 28.15 | 20.97 | 74.49 | 70
1314 | BIRBHUM | Birbhum Division | Barshal piped water supply scheme. , SM/14535 | New | Material Requisition To Resource Division | 1557/BHM | 26/04/2023 | 0 | Resource Division | 407.86 | 0 | 0 | 0
1315 | BIRBHUM | Bolpur Mechanical | Barshal piped water supply scheme. , SM/14535 | New | Supply & Installation of Low lift Pumping Mchinery and other allied work for BARSHAL & Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 3388/BOL.MD | 16/10/2023 | 90 | UNIVERSAL ENTERPRISES | 50.94 | 0 | 0 | 30
1316 | BIRBHUM | Birbhum Division | Barshal piped water supply scheme. , SM/14535 | New | Accetance cum Work Order For Supply and delivery of Sluice Valve for Barshal piped water supply scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte | 947/BHM | 14/03/2024 | 30 | SSPR VALVE MANUFACTURING PVT LTD | 9.32 | 0 | 0 | 100
1317 | BIRBHUM | Birbhum Division | Barshal piped water supply scheme. , SM/14535 | New | Material Requisition To Resource Division | 236/BHM | 24/01/2024 | 0 | Resource Division | 3.08 | 0 | 0 | 0
1318 | BIRBHUM | Birbhum Division | Barshal piped water supply scheme. , SM/14535 | New | Different works related to water supply scheme at BARSHAL & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3506/BHM | 10/08/2023 | 767 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 1024.06 | 0 | 0 | 30
1319 | BIRBHUM | Bolpur Mechanical | Barshal piped water supply scheme. , SM/14535 | New | Supply & Installation of High lift Pumping Mchinery and other allied work for BARSHAL & Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 3370/BOL.MD | 11/10/2023 | 659 | SUNIL RABIDAS | 87.29 | 0 | 0 | 0
1320 | BIRBHUM | Birbhum Division | RANIPARA PIPED WATER SUPPLY SCHEME , SM/16276 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for RANIPARA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | 185/BSD | 11/05/2022 | 180 | APEX ENGINEERING | 3.52 | 0 | 0 | 100
1321 | BIRBHUM | Birbhum Division | RANIPARA PIPED WATER SUPPLY SCHEME , SM/16276 | New | Material Requisition To Resource Division | 2396/BHM | 27/08/2024 | 0 | Resource Division | 5.4 | 0 | 0 | 0
1322 | BIRBHUM | Central Drilling | RANIPARA PIPED WATER SUPPLY SCHEME , SM/16276 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1323 | BIRBHUM | Birbhum Division | RANIPARA PIPED WATER SUPPLY SCHEME , SM/16276 | New | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1948/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0 | 0
1324 | BIRBHUM | Bolpur Mechanical | RANIPARA PIPED WATER SUPPLY SCHEME , SM/16276 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Ranipara PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | 335/BOL.MD | 19/02/2025 | 120 | SATYAJIT GHOSH | 76.45 | 0 | 0 | 7
1325 | BIRBHUM | Birbhum Division | DHANASAHA PIPED WATER SUPPLY SCHEME , SM/18352 | New | Material Requisition To Resource Division | 1524/BHM | 26/04/2023 | 0 | Resource Division | 194.02 | 0 | 0 | 0
1326 | BIRBHUM | Birbhum Division | DHANASAHA PIPED WATER SUPPLY SCHEME , SM/18352 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for DHANASAHA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - B) | 299/BSD | 10/08/2022 | 90 | M/S R DUTTA & CO. | 2.5 | 0 | 0 | 100
1327 | BIRBHUM | Birbhum Division | DHANASAHA PIPED WATER SUPPLY SCHEME , SM/18352 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for DHANASAHA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - A) | 216/BSD | 31/05/2022 | 90 | M/S R DUTTA & CO. | 4.93 | 0 | 0 | 100
1328 | BIRBHUM | Central Drilling | DHANASAHA PIPED WATER SUPPLY SCHEME , SM/18352 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1329 | BIRBHUM | Birbhum Division | DHANASAHA PIPED WATER SUPPLY SCHEME , SM/18352 | New | Different works related to water supply scheme at DHANASAHA, CHHATAR-BANDI, BHABANIPUR, BHUBANESWAR Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | 4141/BHM | 19/10/2023 | 709 | B RAI CONSTRUCTION COMPANY | 2996.46 | 0 | 0 | 5
1330 | BIRBHUM | Birbhum Division | DHANASAHA PIPED WATER SUPPLY SCHEME , SM/18352 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
1331 | BIRBHUM | Birbhum Division | CHHATAR BANDI PIPED WATER SUPPLY SCHEME , SM/18354 | New | Material Requisition To Resource Division | 1545/BHM | 26/04/2023 | 0 | Resource Division | 51.45 | 0 | 0 | 0
1332 | BIRBHUM | Birbhum Division | CHHATAR BANDI PIPED WATER SUPPLY SCHEME , SM/18354 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for CHHATAR BANDI Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - A) | 183/BSD | 05/05/2022 | 90 | M/S R DUTTA & CO. | 4.93 | 0 | 0 | 100
1333 | BIRBHUM | Birbhum Division | CHHATAR BANDI PIPED WATER SUPPLY SCHEME , SM/18354 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for CHHATAR BANDI Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - B) | 292/BSD | 29/07/2022 | 90 | M/S R DUTTA & CO. | 2.15 | 0 | 0 | 100
1334 | BIRBHUM | Bolpur Mechanical | CHHATAR BANDI PIPED WATER SUPPLY SCHEME , SM/18354 | New | New Power Connection at Chhatarbandi PWSS under Bolpur Mechanical division, PHE Dte. | BP-24-25-132 | 29/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.83 | 0 | 0 | 0
1335 | BIRBHUM | Central Drilling | CHHATAR BANDI PIPED WATER SUPPLY SCHEME , SM/18354 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1336 | BIRBHUM | Birbhum Division | CHHATAR BANDI PIPED WATER SUPPLY SCHEME , SM/18354 | New | Different works related to water supply scheme at DHANASAHA, CHHATAR-BANDI, BHABANIPUR, BHUBANESWAR Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | 4141/BHM | 19/10/2023 | 709 | B RAI CONSTRUCTION COMPANY | 2996.46 | 0 | 0 | 5
1337 | BIRBHUM | Birbhum Division | CHHATAR BANDI PIPED WATER SUPPLY SCHEME , SM/18354 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
1338 | BIRBHUM | Birbhum Division | Retrofitting works of Hazarpur (Phase-II) water supply scheme under Rampurhat-II Block PWSS for providing Functional Household Tap Connection(FHTC) within command area , SM/06946 | Retrofitting | Laying of Distribution System with UPVC Pipes and Providing Tap Connection for Existing School & AWC under Hazarpur PWSS under Rampurhat Sub Division within Birbhum Division, PHE Dte. | 276/RSD | 16/07/2021 | 10 | ABUL HASNAT | 1 | 0 | 0 | 100
1339 | BIRBHUM | Birbhum Division | Retrofitting works of Hazarpur (Phase-II) water supply scheme under Rampurhat-II Block PWSS for providing Functional Household Tap Connection(FHTC) within command area , SM/06946 | Retrofitting | Additional laying of UPVC Pipe line at Hazarpur, Kanakpur & Ekdala Mouzas along with other allied works for providing FHTC under Hazarpur Piped W/S Scheme under Rampurhat Sub- Division, P.H.E. Dte within Birbhum Division P.H.E. Dte. | 373/RSD | 28/09/2021 | 30 | UJJWAL DAS | 2.79 | 2.76 | 100 | 100
1340 | BIRBHUM | Birbhum Division | Retrofitting works of Hazarpur (Phase-II) water supply scheme under Rampurhat-II Block PWSS for providing Functional Household Tap Connection(FHTC) within command area , SM/06946 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Uttarpur, Shinpur, Pariharpur, Jashahari of Hazarpur w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Sl. No.8) | 1242 /BHM | 28/09/2020 | 60 | NANDANIK ENGINEERS C. OP. SOC. LTD. | 36.52 | 71.48 | 200 | 0
1341 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block , SM/07646 | Retrofitting | Providing Functional Household Tap Connection (FHTC) in Purba Narayanpur Mouza from existing distribution system within the command area of Nachansaha & Adjoining Mouzas Water Supply Scheme under Bolpur Sub-Division of Birbhum Division, PHE Dte. (Sl. No.3) | 257/BHM | 26/02/2021 | 45 | NAZIR HOSSAIN | 4.66 | 7.59 | 166.11 | 100
1342 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block , SM/07646 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in within the command area of village Nachansaha Water Supply Scheme. |  | 17/03/2021 | 0 | PINTU KHAN | 4.28 | 0 | 0 | 0
1343 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block , SM/07646 | Retrofitting | Providing functional Household tap connection (FHTC) in village Nachansaha (part) from existing distribution system within the command area of Nachansaha & Adjoining mouzas water supply scheme under Bolpur Sub Division PHE (Sl.No.05) |  | 19/03/2021 | 0 | SUBHRADIP SARKAR | 4.45 | 0 | 0 | 0
1344 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block , SM/07646 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nachansa w/s Scheme (Leftout House Hold) in Bolpur Sub-Division under Birbhum Division, PHE Dte.(Sl. No.7) | 1526/BHM | 13/09/2021 | 60 | S R ENTERPRISE | 48.52 | 48.02 | 100 | 100
1345 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block , SM/07646 | Retrofitting | Retrofitting of existing distribution Pipeline with Sluice Valve at different Locations of PURBA NARAYANPUR Mouza within the command area of Nachansaha and its Adjoining Mouzas W/S Scheme for providing FHTC under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No. -14) | 377/ BSD | 05/10/2021 | 30 | PINTU KHAN | 4.83 | 4.82 | 100 | 100
1346 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block , SM/07646 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre and left out Household at Narayanpur and Daronda village existing distribution System within Nachansaha W/S Scheme and Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | 402/BSD | 25/10/2021 | 10 | NAZIR HOSSAIN | 0.96 | 0 | 0 | 0
1347 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block , SM/07646 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at School & Anganwadi Centre and left out Household at Narayanpur and Daronda village existing distribution System within Nachansaha W/S Scheme and Daronda W/S Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | 402/ BSD | 25/10/2021 | 10 | NAZIR HOSSAIN | 0.96 | 0 | 0 | 100
1348 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block , SM/07646 | Retrofitting | Retrofitting works to the existing distribution System for providing FHTC within the coverage area of Nachansaha & its Adj. Moujas Water Supply Scheme at Shibpur Mouja and Jagdalpur village (Part) of Bilati G.P. under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 05) | 449/BSD | 10/12/2021 | 30 | S R ENTERPRISE | 4.81 | 4.63 | 100 | 100
1349 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block , SM/07646 | Retrofitting | Retrofitting works to the existing distribution System for FHTC within the coverage area of Nachansaha & Adj. Moujas Water Supply Scheme at GOLTIKURI village (Part) and Nachansaha Mouja (Part) of Bilati G.P. within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 03) | 424/BSD | 18/11/2021 | 30 | S R ENTERPRISE | 4.84 | 4.63 | 100 | 100
1350 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block , SM/07646 | Retrofitting | Restoration of Cement concrete Road, damaged due to laying of Pipeline during FHTC work at NACHANSAHA and Purba-Narayanpur Moujas at Bilati G.P. within the coverage area of Nachansaha & Adj. Moujas Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 05). | 102/BSD | 16/03/2022 | 10 | S R ENTERPRISE | 0.93 | 0.93 | 100 | 100
1351 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block , SM/07646 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in within the command area of village Nachansaha Water Supply Scheme. | 95/BHM | 29/01/2021 | 90 | PINTU KHAN | 4.66 | 9.32 | 200 | 0
1352 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block , SM/07646 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in within the command area of village Nachansaha Water Supply Scheme.(Sl No. 05) | 256/BHM | 26/02/2021 | 90 | SUBHRADIP SARKAR | 4.67 | 8.96 | 198.81 | 0
1353 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Nachansaha PWSS within Ilambazar Block , SM/07646 | Retrofitting | Extension of Pipeline from existing distribution System for providing FHTC at Jagdalpur village of Shibpur Mouza within the coverage area of Nachansaha & Adj. Moujas Water Supply Scheme at Bilati G.P. within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.10) | 2164/BHM | 24/12/2021 | 60 | M/S.CHANDRANATH MUKHERJEE | 18.6 | 2.88 | 15.48 | 100
1354 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Construction of PCC approach Road at Head Work Site for Raypur Zone-I Piped Water Supply Scheme under under Rampurhat Sub-Division under Birbhum Division, PHE Dte. | 225/RSD | 23/06/2022 | 30 | GOURANGA MONDAL | 2.6 | 0 | 0 | 100
1355 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Supply & delivery of CIDF Sluice Valves for Laying of Rising Main DI K9 from Deucha CWR site to Raypur Zone-I & II OHRs under Raypur Piped Water Supply Scheme under Rampurhat Sub Division, P.H.E Dte. under Birbhum Division, P.H.E. Dte. | 119/RSD | 11/03/2022 | 30 | ASIT GHOSH | 0.55 | 0 | 0 | 50
1356 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raipur Zone-II Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.13) | 24/BHM | 06/01/2022 | 60 | SK ALIM | 75.03 | 66.41 | 100 | 97
1357 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Raipur Zone-I Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte.¿(Sl. No.12) | 279/BHM | 09/02/2022 | 60 | PRADIP KUMAR SHARMA | 76.52 | 30.16 | 100 | 50
1358 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Additional Laying & joining with UPVC pipes within distribution system From near OHR Site to Deucha Masjid of Raipur (Zone-II) piped W/S Scheme under Birbhum Division, PHE Dte. | 32/RSD | 04/01/2022 | 30 | GOURANGA MONDAL | 4.96 | 0 | 0 | 100
1359 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Additional Laying & joining with UPVC pipes within distribution system From near Deucha Bus Stand to Deucha Bridge of Raipur (Zone-II) piped W/S Scheme under Birbhum Division, PHE Dte. | 34/RSD | 04/01/2022 | 30 | GOURANGA MONDAL | 4.95 | 0 | 0 | 100
1360 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Supply & delivery of CI/DI Specials for Laying of Rising Main DI K9 from Deucha CWR site to Raypur Zone-I & II OHRs under Raypur Piped Water Supply Scheme under Rampurhat Sub Division, P.H.E Dte. under Birbhum Division, P.H.E. Dte. | 117/RSD | 10/03/2022 | 30 | ASIT GHOSH | 0.46 | 0 | 0 | 100
1361 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Supply & delivery of CIDF Sluice Valves for Laying of Rising Main DI K9 from Deucha CWR site to Raypur Zone-I & II OHRs under Raypur Piped Water Supply Scheme under Rampurhat Sub Division, P.H.E Dte. under Birbhum Division, P.H.E. Dte | 119/RSD | 11/03/2022 | 30 | ASIT GHOSH | 0.55 | 0 | 0 | 50
1362 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Laying of UPVC pipes within distribution system from Deucha to Harinsingha Road at Sahapara of Raipur (Zone-II) piped W/S Scheme under Birbhum Division, PHE Dte. | 100/RSD | 07/03/2022 | 30 | GOURANGA MONDAL | 2.34 | 0 | 0 | 100
1363 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Laying of HDPE Pipe line for Deucha, Dubrajpur mouzas for providing FHTC under Raypur Zone II Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. | 179/RSD | 02/05/2022 | 30 | SK ABDUL HALIM | 4.67 | 0 | 0 | 100
1364 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Laying of HDPE Pipe line for Deucha mouza for providing FHTC under Raypur Zone II Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. | 180/RSD | 02/05/2022 | 30 | SK ABDUL HALIM | 5 | 0 | 0 | 100
1365 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Laying of HDPE Pipe line for Uska, Tentulia, Dubrajpur, Raghunathpur mouzas for providing FHTC under Raypur Zone II Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. | 178/RSD | 02/05/2022 | 30 | SK ABDUL HALIM | 4.99 | 0 | 0 | 100
1366 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Supply & delivery of sluice valve for Raipur W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex Dist.-Birbhum under Birbhum Division, PHE Dte. (Sl. No.-02) | 420/BHM | 24/02/2022 | 15 | UJJWAL DAS | 4.59 | 0 | 0 | 100
1367 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Additional Laying & joining with UPVC pipes within distribution system From near Deucha Masjid to Deucha Eid Gaha of Raipur (Zone-II) piped W/S Scheme under Birbhum Division, PHE Dte. | 33/RSD | 04/01/2022 | 30 | GOURANGA MONDAL | 4.96 | 0 | 0 | 100
1368 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Sinking for 3 nos. 200 mm dia. Tubewell with horizontal strainer on the River Bed of Dwarka under Raypur Piped Water Supply Scheme under Birbhum Division P.H.E. Dte. | 31/RSD | 04/01/2022 | 30 | SUNIL RABI DAS | 4.91 | 0 | 0 | 100
1369 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Connection between New Tubewells to existing CWR by DI pipe near Dwarka River Bank site for Raypur Piped Water Supply Scheme under Rampurhat Sub-Division, within Birbhum Division P.H.E Dte. | 14/RSD | 04/01/2022 | 30 | ASIT GHOSH | 3.34 | 0 | 0 | 100
1370 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Raypur PWSS (Phase-I) within Md. Bazar Block , SM/07649 | Retrofitting | Laying of Rising Main DI K9 from Deucha CWR site to Raypur Zone-I and II OHRs under Raypur Piped Water Supply Scheme under Rampurhat Sub-Division, P.H.E Dte. under Birbhum Division, P.H.E. Dte. (Sl. No.1) | 1339/BHM | 18/08/2021 | 221 | ASIT GHOSH | 7.34 | 0 | 0 | 100
1371 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) , SM/06732 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Kendgara Village (JL No.-120) of different locations from existing distribution system within the command area of Khoyrasole Piped Water Supply Scheme at Khoyrasole Block under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte (Sl. No.-2) | 1476/BHM | 06/09/2021 | 60 | NUR MOBINUL ISLAM | 27.58 | 27.25 | 98.79 | 100
1372 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) , SM/06732 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Mahammadpur Village (JL No.-115) of different locations from existing distribution system within the command area of Khoyrasole Piped Water Supply Scheme at Khoyrasole Block under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte. (Sl. No.21) | 203/BHM | 18/02/2021 | 45 | BHAGYADHAR GHOSH | 14.28 | 12.93 | 90.55 | 100
1373 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) , SM/06732 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Churar Village (JL No.-137) of different locations from existing distribution system within the command area of Khoyrasole Piped Water Supply Scheme at Khoyrasole Block under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte. (Sl. No.-1) | 1096/BHM | 07/07/2021 | 60 | PRAVAT SARKAR | 35.23 | 34.02 | 96.67 | 100
1374 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) , SM/06732 | Retrofitting | Supply and delivery of Sluice Valve for Augmentation of Khoyrasole Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-6) | 4625/BHM | 18/12/2023 | 30 | BAHIR CONSTRUCTION PRIVATE LIMITED | 9.3 | 0 | 0 | 100
1375 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Khoyrasole PWSS (Phase-I) , SM/06732 | Retrofitting | Continuation Work Order for Supply and delivery of Sluice Valve for Augmentation of Khoyrasole Zone-II W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-6) | 737/BHM | 28/02/2024 | 30 | BAHIR CONSTRUCTION PRIVATE LIMITED | 9.3 | 0 | 0 | 100
1376 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Aligarh PWSS (Phase-I) , SM/06733 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Sahabad, Azimnagar, Natangram, Gobra of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. (Sl. No.1) | 1236 /BHM | 28/09/2020 | 45 | RAJ KUMAR DAS | 25.65 | 4.41 | 100 | 40
1377 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Aligarh PWSS (Phase-I) , SM/06733 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Madanpur, Jaypur, Talpur, Rahida, Ranigram, Hirapur, Marbuni, Laubani) of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. | 1167 /BHM | 21/09/2020 | 60 | M/S KRIPASINDHU GHOSH & CO. | 42.21 | 71.21 | 168.89 | 100
1378 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Aligarh PWSS (Phase-I) , SM/06733 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Gangmuri, of Aligarh w/s Scheme at Suri-I Block under Birbhum Division, PHE Dte. (Sl. No.2) | 1237 /BHM | 28/09/2020 | 45 | S R ENTERPRISE | 21.49 | 41.31 | 147.8 | 0
1379 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Hazarpur PWSS(Phase-I) , SM/06739 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Hazarpur of Hazarpur w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-A) | 1180 /BHM | 21/09/2020 | 60 | UJJWAL DAS | 41.06 | 84.25 | 200 | 0
1380 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Hazarpur PWSS(Phase-I) , SM/06739 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Kanakpur, Bholadanga, Ekdala of Hazarpur w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. | 1181 /BHM | 21/09/2020 | 60 | APORUPA CONSTRUCTION | 42.76 | 87.33 | 200 | 0
1381 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Allied works of extension pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages BAITARA & KHUJUTIPARA of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No. - 08) | 375/BSD | 05/10/2021 | 30 | MANAS KUMAR MONDAL | 4.56 | 4.36 | 100 | 98
1382 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Providing Functional Household Tap Connection (FHTC) and Retrofitting of pipe lines From Khujutipara Fishery Market to Petrol pump, Chatimgram on Basapara Nanoor Road for Providing sufficient water to Nanagar Kodda Village from existing distribution system within the command area of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED | 2586/BHM | 22/11/2022 | 30 | M/S.CHANDRANATH MUKHERJEE | 23.26 | 0 | 0 | 0
1383 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Supply of one no. Diesel driven Motor Cab/Maxi Cab(Air Condition) on hire basis under the Assistant Engineer (H.Q), Birbhum Division PHE Dte.(Period from 01.11.2022 to 30.04.2023) | 2320/BHM | 28/10/2022 | 184 | JAMSED ALI KHAN | 0.96 | 0.16 | 100 | 100
1384 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Supply of one no. diesel driven Car (Diesel) on hire basis office uses for the officials of the Assistant Engineer, RWS, Birbhum Sub-Division, P.H.E. Dte. [Period from (01.02.2023 to 05.07.2023) | 185/RWS | 31/01/2023 | 155 | AADIL CONSTRUCTION | 0.73 | 1.59 | 100 | 100
1385 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Payment of Deisel Oil and fuel for the month of July23 to Sept'23 | BP-2023-24-235 | 01/11/2023 | 0 | JAYRAM FILLING STATION | 0.72 | 0 | 0 | 0
1386 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Payment for Supply of diesel | BP-2023-24-127 | 25/08/2023 | 0 | JAYRAM FILLING STATION | 0.72 | 0 | 0 | 0
1387 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Hiring of 01(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, P.H.E. Dte under Birbhum Division, P.H.E Dte. for the period of 01.04.2023 to 30.09.2023 | 154/BSD | 30/03/2023 | 183 | SK AKRAM HOSSAIN | 0.86 | 1.59 | 100 | 87
1388 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Continution work for Supply of one no. Diesel driven Motor Cab / Maxi Cab (Air Condition) on hire Basis under the Assitant Engineer (H.Q) Birbhum Division P.H.E Dte. (Period from 01.05.2023 to 31.10.2023) | 1607/BHM | 27/04/2023 | 184 | JAMSED ALI KHAN | 0.96 | 0.31 | 32.4 | 100
1389 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Continuation Work of Hiring of Ambassador Car (Diesel) registered Luxury Taxi for the office of the Assistant Engineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition for 364 days (from 02.07.2021 to 30.06.2022) for 364 days (from 02.07.2022 to 30.06.2023) for 31 Days (from 01.07.2023 to 31.07.2023). | 155/RSD | 28/06/2023 | 31 | SOUMITA PAL | 0.17 | 0 | 0 | 0
1390 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Supply of one no. diesel driven car(Diesel) on hire basis office uses for the official of the Assistant Engineer, RWS, Birbhum Sub-Division, PHE Dte.(Period from 06.07.2023 to 31.12.2023) | 337/RWS | 05/07/2023 | 179 | AADIL CONSTRUCTION | 0.85 | 0.4 | 46.72 | 15
1391 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Continuation order against "Hiring of 1(One) no. vehicle for the Office of the Assistant Engineer, Bolpur Sub-Division, PHE Dte. under Birbhum Division, PHE Dte. For the period of 01.04.2023 to 30.09.2023". For another 06 (Six) months i.e. from 01.10.2023 to 31.03.2024. | 436/BSD | 29/09/2023 | 182 | SK AKRAM HOSSAIN | 0.86 | 0 | 0 | 100
1392 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Khujutipara Mouja (JL No.-127) at different locations from existing distribution system within the command area of Khujutipapara and Adjoining Mouzas W/S Scheme at Nanoor Block under Bolpur Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte | 1088 /BHM | 05/09/2020 | 30 | BHAGYADHAR GHOSH | 4.7 | 9.4 | 200 | 0
1393 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Nabasta of Khujutipara w/s Scheme at Nanoor Block within Bolpur Sub Division under Birbhum Division, PHE Dte. (2nd Call) (Sl. No.24) | 31/BHM | 13/01/2021 | 60 | MANAS KUMAR MONDAL | 28.93 | 27.17 | 200 | 45
1394 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Preparation and broadcasting of 10 minutes programme (PHE Manusaher sathe) planned for Awarness generation through (Audio visual Documentation) TV and social media of covering the area of Birbhum Distric under Birbhum Division PHE Dte. (Sl.No.01) | 1570/BHM | 07/12/2020 | 60 | TARANGA ONLINE | 0.89 | 1.77 | 200 | 0
1395 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Cleaning the Chokage of 150mm. DI pipe line, repairing of UPVC pipe, retrofitting of pipeline for Providing sufficient water to Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages of Baitara, Sehela and Nabsata of Khujutipara Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, Public Health Engineering Department. | 309/BSD | 16/08/2022 | 30 | BHAGYADHAR GHOSH | 4.42 | 0 | 0 | 100
1396 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Khujutipara PWSS(Phase-I) , SM/06741 | Retrofitting | Certified that the total quantity of fuel supplied for the vehicle no. WB53B-8630 consumed for official purpose under Assistant Engineer (HQ), Birbhum Division PHE Dte. for the month of Oct'23. | BP-2023-24-407 | 01/03/2024 | 0 | JAYRAM FILLING STATION | 0.2 | 0 | 0 | 0
1397 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Haridaspur in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.10) | 1006/BHM | 11/06/2021 | 60 | M/S KRIPASINDHU GHOSH & CO. | 36.62 | 73.22 | 200 | 100
1398 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Bhagabatipur in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.12) | 1015/BHM | 15/06/2021 | 60 | TAPAN KUMAR DATTA | 30.21 | 30.21 | 100 | 100
1399 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Jungul,Gunua in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.11) | 274 / BHM | 26/02/2021 | 45 | KAZI EMDADUL HAQUE | 23.6 | 42.08 | 200 | 95
1400 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Jhaupara, Dattakaya, Shingdohari in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte (Sl. No.9) | 681/BHM | 01/06/2021 | 60 | BELAL SK | 43.79 | 77.21 | 200 | 92
1401 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Chachka-Balarampur habitations under Haridaspur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 530/AE/NSD | 08/10/2021 | 45 | SUBHRANIL DAS | 4.74 | 4.74 | 100 | 100
1402 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Chachka habitations under Haridaspur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 531/AE/NSD | 08/10/2021 | 45 | HUMAYUN KABIR | 4.75 | 4.75 | 50 | 100
1403 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Gunia Habitation under Haridaspur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 594/AE/NSD | 23/11/2021 | 45 | AJIMUL ISLAM | 4.82 | 4.82 | 100 | 100
1404 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Dasturpur (South) Habitation under Haridaspur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 595/AE/NSD | 23/11/2021 | 45 | DATA CONSTRUCTION | 4.82 | 4.82 | 100 | 100
1405 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Kalyanpur Habitation under Haridaspur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 593/AE/NSD | 23/11/2021 | 45 | M/S S.N CONSTRUCTION | 4.82 | 4.81 | 100 | 100
1406 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Extention of pipeline by HDPE pipe at Gunia and Kalyanpur habitation for providing FHTC of Haridaspur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division PHED. | 200/AE/NSD | 01/04/2022 | 45 | M/S S.N CONSTRUCTION | 3.15 | 2.44 | 100 | 100
1407 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Sanakpur in Haridaspur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.8) | 910/BHM | 10/06/2021 | 60 | MS B N ENTERPRISES | 32.66 | 32.22 | 50 | 100
1408 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Balance work for construction of High Lift Pump house including stainless steel railing at Haridaspur PWSS Under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. | 357/AE/NSD | 20/07/2022 | 45 | SUNIL RABI DAS | 5 | 0 | 0 | 0
1409 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Dasturpur (North) Habitation under Haridaspur W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 596/AE/NSD | 23/11/2021 | 45 | SURJASISH DATTA | 4.82 | 0 | 0 | 100
1410 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Sinking of 200mm 50 m. deep replacement (No.-1) Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at Haridaspur Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 122/AE/NSD | 04/03/2022 | 30 | SURJASISH DATTA | 3.3 | 0 | 0 | 100
1411 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Land development including strengthening of River side filling HARIDASPUR PWSS under Nalhati Sub-Division, PHE Dte. | 22/NSD | 17/01/2022 | 21 | SUNIL RABI DAS | 4.84 | 0 | 0 | 100
1412 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Construction of Boundary Wall at OHR site at Haridaspur Piped Water Supply Scheme (South side) under Nalhati Sub-Division within Birbhum Division, PHED. | 224/AE/NSD | 19/04/2022 | 60 | RAJA CONSTRUCTION | 4.84 | 0 | 0 | 45
1413 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Sinking and replacement of 200mm dia 60 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Haridaspur (near head work side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | 208/AE/NSD | 05/04/2022 | 30 | SURJASISH DATTA | 3.74 | 0 | 0 | 100
1414 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Haridaspur PWSS within Nalhati-I Block, Dist.- Birbhum , SM/07531 | Retrofitting | Extention of pipeline by HDPE pipe at Bhagabatipur and Chachka habitations for providing FHTC of Haridaspur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHED. | 211/AE/NSD | 07/04/2022 | 45 | HUMAYUN KABIR | 4.84 | 0 | 0 | 100
1415 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) , SM/10543 | Retrofitting | Replacement of UPVC pipe line & Inter connection of D.I. pipeline from new tube well to rising main at Guskira village of Gopalpur (Zone-II) Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 408/AE/NSD | 06/09/2022 | 30 | SUPRABHAT RABIDAS | 4.84 | 4.65 | 100 | 100
1416 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) , SM/10543 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply Scheme (Zone-II) under Nalhati Sub Division within Birbhum Division PHED. | 229/AE/NSD | 21/04/2022 | 45 | MD ZIAUL ISLAM | 3.34 | 0 | 0 | 0
1417 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) , SM/10543 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 508/AE/NSD | 01/10/2021 | 45 | SHIB GANGA CONSTRUCTION | 4.67 | 4.67 | 100 | 67
1418 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) , SM/10543 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Ramchandrapur and Kestora under Murarai-I Block within the command area of Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 509/AE/NSD | 01/10/2021 | 45 | SUPRABHAT RABIDAS | 4.66 | 4.66 | 100 | 33
1419 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) , SM/10543 | Retrofitting | Replacement with Extension of 63 & 75 mm Dia. UPVC Pipe line in different habitations within Gopalpur (Zone-II) Piped Water Supply Scheme under Nalhati Sub-Division P.H.E Dte. | 206/AE/NSD | 05/04/2022 | 45 | SUPRABHAT RABIDAS | 4.22 | 4.22 | 100 | 50
1420 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) , SM/10543 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply Scheme (Zone-II) under Nalhati Sub Division within Birbhum Division PHED. | 383/AE/NSD | 10/08/2022 | 45 | MD ZIAUL ISLAM | 3.34 | 3.33 | 100 | 50
1421 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) , SM/10543 | Retrofitting | Extension of pipeline for left out habitations along with FHTC at Gopalpur PWSS (Zone-I) under Nalhati Sub Division P.H.E.D (Sl. No.12) | 28/BHM | 04/01/2023 | 45 | SUBHRANIL DAS | 11.64 | 11.6 | 100 | 100
1422 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) , SM/10543 | Retrofitting | Approaching path to Pump House along with Land Development at OHR site of Gopalpur PWSS (Zone-II) under Nalhati Sub-Division, PHED. | 131/NSD | 31/03/2023 | 30 | SUPRABHAT RABIDAS | 0.97 | 0.97 | 100 | 100
1423 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) , SM/10543 | Retrofitting | Extension of pipeline for left out habitations along with FHTC at Gopalpur PWSS( Zone-II)under Nalhati Sub Division P.H.E.D. (Sl. No.11) | 31/BHM | 04/01/2023 | 45 | ISLAM CONSTRUCTION | 17.06 | 16.88 | 100 | 0
1424 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) for household within the command area of Gopalpur water supply scheme (Phase-II) , SM/10543 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in left out habitations , under Ramchandrapur & Kestara Village (J.L:-100) under Murarai - I Block, within the command area of Gopalpur Zone II W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 370/AE/NSD | 22/07/2021 | 45 | SUPRABHAT RABIDAS | 4.97 | 0 | 0 | 50
1425 | BIRBHUM | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme , SM/10314 | Augmentation | Construction of Boundary wall at Pump House River Bank site under Pachiara Piped Water Supply Scheme within Birbhum Sadar Sub-Division, P.H.E. Dte. under Birbhum Division, P.H.E. Dte. (Sl. No. -19) | 250/BSSD | 03/08/2021 | 45 | RANJIT GHOSH | 2.69 | 2.52 | 100 | 100
1426 | BIRBHUM | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme , SM/10314 | Augmentation | Construction of 500cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Pachiara W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | 1290/BHM | 18/04/2023 | 275 | M/S GOUTAM DAS | 128.83 | 0 | 0 | 0
1427 | BIRBHUM | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme , SM/10314 | Augmentation | Material Requisition To Resource Division | 907/BHM | 26/04/2022 | 0 | Resource Division | 4.36 | 0 | 0 | 0
1428 | BIRBHUM | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme , SM/10314 | Augmentation | Material Requisition To Resource Division | 946/BHM | 24/03/2023 | 0 | Resource Division | 68.5 | 0 | 0 | 0
1429 | BIRBHUM | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme , SM/10314 | Augmentation | Material Requisition To Resource Division | 1119/BHM | 10/04/2023 | 0 | Resource Division | 10.48 | 0 | 0 | 0
1430 | BIRBHUM | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme , SM/10314 | Augmentation | Material Requisition To Resource Division | 3282/BHM | 27/07/2023 | 0 | Resource Division | 1.37 | 0 | 0 | 0
1431 | BIRBHUM | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme , SM/10314 | Augmentation | Material Requisition To Resource Division | 2245/BHM | 07/07/2023 | 0 | Resource Division | 2.85 | 0 | 0 | 0
1432 | BIRBHUM | Bolpur Mechanical | Augmentation of Panchiara Piped Water Supply Scheme , SM/10314 | Augmentation | WBSEDCL QUOTATION FOR PACHAIARA WS SCHEME | BP-23-24-146 | 28/11/2023 | 0 | WBSEDCL | 0.02 | 0 | 0 | 0
1433 | BIRBHUM | Bolpur Mechanical | Augmentation of Panchiara Piped Water Supply Scheme , SM/10314 | Augmentation | Providing and Installation of Electro-Mechanical equipments and other allied Works for Augmentation of PANCHIARA PWSS under Bolpur Mechanical Division PHE Dte. | 2129/Bol.MD | 25/08/2023 | 90 | SATYAJIT GHOSH | 96.79 | 0 | 0 | 50
1434 | BIRBHUM | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme , SM/10314 | Augmentation | Laying of Rising Main Pipe line for the Augmentation of Pachiara Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte within Birbhum Division, P.H.E. Dte. | 768/BHM | 01/03/2024 | 45 | M/S JOY MAA BANAMALI | 6.37 | 0 | 0 | 0
1435 | BIRBHUM | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme , SM/10314 | Augmentation | Construction of Drain and Valve Chamber Pachiara Water Supply Scheme at Rampur under RWS Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte.(Sl.No.5) | 134/BH | 15/06/2022 | 30 | UTPAL DEY | 3.03 | 2.98 | 100 | 0
1436 | BIRBHUM | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme , SM/10314 | Augmentation | Trial Bore and Sinking of 200 mm dia. tubewell (04 nos.) 30 m. Deep fitted with M.S.E.R.W. Housing pipe and Fibre Glass Strainer on the river bank of Sal for the Augmentation of Panchiara Piped Water Supply Scheme under Birbhum Sadar Sub-Division PHE Dte. with Birbhum Division, P.H.E. Dte. | 1982/BHM | 05/06/2023 | 30 | AMIT KUMAR ROY | 5.7 | 0 | 0 | 100
1437 | BIRBHUM | Bolpur Mechanical | Augmentation of Panchiara Piped Water Supply Scheme , SM/10314 | Augmentation | WBSEDCL QUOTATION FOR PACHHIARA | BP-23-24-203 | 04/01/2024 | 0 | WBSEDCL | 5.75 | 0 | 0 | 0
1438 | BIRBHUM | Birbhum Division | Augmentation of Panchiara Piped Water Supply Scheme , SM/10314 | Augmentation | Laying distribution system including FHTC for proposed augmentation scheme for Pachiara Piped Water Supply Scheme, Dubrajpur Block, under Birbhum Division, PHE Dte.? (Sl. No.1) | 1161/BHM | 23/05/2022 | 1166 | M/S GOUTAM DAS | 467.38 | 322.59 | 73.3 | 92
1439 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Laying distribution system including functional household for proposed augmentation scheme for Murarai Piped Water Supply Scheme under Murarai ¿ I Block, under Birbhum Division, PHE Dte.¿ (Sl. No.4) | 555/BHM | 08/04/2022 | 180 | SK ALIM | 392.31 | 381.28 | 97.19 | 72
1440 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Repairing & renovation of Boundary Wall with Land filling at Head Work site (Murarai-1 Dev. Block) at Murarai Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHED. | 199/AE/NSD | 01/04/2022 | 30 | M/S S.N CONSTRUCTION | 4.85 | 4.82 | 99.48 | 100
1441 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Providing Functional Household Tap Connection(FHTC) from existing distribution system in Rudranagar Pathanpara (Chatra Zone-II) W/S Scheme (Rudranagar) under RWS Birbhum Sub-Divition within Birbhum Division PHE Dte. (Sl. No.10) | 139/BH | 15/06/2022 | 20 | ISLAM CONSTRUCTION | 4.75 | 0 | 0 | 0
1442 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Renovation of Boundary Wall near Switch Room at Rajgram Water Supply Scheme under Nalhati Sub-Division, PHE Dte. (2nd Call) | 394/AE/NSD | 18/08/2022 | 60 | MD ASIF ALI | 4.85 | 0 | 0 | 0
1443 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Repairng, Renovation of Pump house & repairing of CWR of Murarai Piped Water Supply Scheme at RWS,Birbhum Sub-Division under Birbhum Division, PHE Dte.(Sl. No.01) | 86/BH | 05/05/2022 | 20 | M/S S.N CONSTRUCTION | 4.77 | 0 | 0 | 0
1444 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Rajgram (Zone-II) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 65/AE/NSD | 11/02/2022 | 15 | MOYTEC | 0.99 | 0.99 | 100 | 100
1445 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Chatra Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 66/AE/NSD | 11/02/2022 | 15 | MOYTEC | 0.99 | 0.99 | 100 | 100
1446 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Kaytha Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 67/AE/NSD | 11/02/2022 | 15 | MOYTEC | 0.99 | 0.99 | 100 | 100
1447 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Bara (Zone-I) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 68/AE/NSD | 11/02/2022 | 15 | G.MITRA & ASSOCIATE | 0.98 | 0.98 | 100 | 100
1448 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Bara (Zone-II) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 69/AE/NSD | 11/02/2022 | 15 | GEOCON INDIA | 0.99 | 0.99 | 100 | 100
1449 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Surging of 2 nos. existing Tube wells of Lohapur Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | 695/AE/NSD | 31/12/2021 | 15 | GOLAM RASUL | 0.63 | 0.63 | 100 | 100
1450 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Bhadrapur (Zone-I) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 691/AE/NSD | 30/12/2021 | 15 | G.MITRA & ASSOCIATE | 0.99 | 0.99 | 100 | 100
1451 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Bhatra, Abdullapur and adjacent area under Rajgram W/S Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 592/AE/NSD | 23/11/2021 | 45 | MD ASIF ALI | 4.82 | 4.72 | 100 | 50
1452 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply & delivery of sluice valve for Augmentation of Rajgram W/S scheme under Birbhum Division, PHE Dte including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. (Sl. No.-01) | 561/BHM | 15/03/2022 | 15 | SSPR VALVE MANUFACTURING PVT LTD | 0.97 | 0.97 | 100 | 100
1453 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Repairing of Pump House of Bara Water Supply Scheme under RWS Birbhum Sub-Division, PHE Dte. within Birbhum Division, PHE Dte. | 35/BH | 09/03/2022 | 30 | RANJIT GHOSH | 0.86 | 0 | 0 | 0
1454 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Laying of 160mm dia. HDPE pipe line from CWR site to Dhabuni village, of Laxshminarayan Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. (2nd Call)¿(Sl. No.9) | 1708/BHM | 07/10/2020 | 45 | HUMAYUN KABIR | 39.25 | 39.25 | 100 | 100
1455 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Construction of Pump House of 5.40 mtr X 3.6 mtr. Size with sanitary and water supply arrangements at new Head work site of Lohapur PWSS under Nalhati Sub-Division within Birbhum division, P.H.E. Dte. | 354/AE/NSD | 20/07/2022 | 60 | GOLAM RASUL | 4.84 | 4.84 | 100 | 100
1456 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking of 200mm 50 m. deep (Replacement No.-1) Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at Laxminarayanpur Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 124/AE/NSD | 04/03/2022 | 30 | BELAL SK | 3.3 | 2.82 | 100 | 98
1457 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking of 200 mm dia & 87mtr.deep Tube well fitted with PVC pipe and fibre glass Strainer for Augmentation of Lohapur Water Supply Scheme at New Head Work site under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 362/AE/NSD | 21/07/2022 | 45 | HARUN AR RASHID | 4.83 | 4.34 | 100 | 99
1458 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking of 200mm 90 m. deep Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at New Head Work site of Bara (Zone-I) Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 120/AE/NSD | 03/03/2022 | 30 | DATA CONSTRUCTION | 4.8 | 4.37 | 100 | 100
1459 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking of 200mm 90 m. deep Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at New Head Work site of Murarai Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 125/AE/NSD | 04/03/2022 | 30 | NUR MOBINUL ISLAM | 4.79 | 3.54 | 100 | 100
1460 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Construction of Pump House of 5.40 mtr. x 3.6 mtr. size with sanitary and water supply arrangement at Bara (Zone-I) Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHED. | 351/AE/NSD | 19/07/2022 | 60 | NUR MOBINUL ISLAM | 4.99 | 4.98 | 100 | 100
1461 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Restoration of concrete road including dismantling of concrete at Node point 26,27,28,97 & 99 for Augmentation of Murarai and its adjoining mouzas Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 344/AE/NSD | 18/07/2022 | 30 | SK ABDUL HALIM | 4.97 | 4.95 | 100 | 100
1462 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Re-Construction of damaged Boundary Wall at 1 no. Tube well site of Lohapur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 407/AE/NSD | 05/09/2022 | 45 | GOLAM RASUL | 4.99 | 4.98 | 100 | 100
1463 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply & delivery of Sluice Valve for augmentation of Bhadrapur W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, PHE Dte. (Sl. No.-02) | 1242/BHM | 03/06/2022 | 15 | APORUPA CONSTRUCTION | 4.99 | 4.99 | 100 | 100
1464 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply & delivery of Sluice Valve for augmentation of Rajgram W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, PHE Dte (Sl. No.-01) | 1241/BHM | 03/06/2022 | 15 | SSPR VALVE MANUFACTURING PVT LTD | 4.99 | 4.99 | 100 | 100
1465 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Collection Household details including Geo reference in habitations named Jagannathpur, Sonarpur, Natun Abdullahapur, Puratan Abdullahapur & Vatra under Rajgram Water Supply Scheme under Nalhati Sub-Division, P.H.E. Dte. | 311/AE/NSD | 29/05/2021 | 15 | MD ASIF ALI | 0.32 | 0.18 | 100 | 72
1466 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Laying of Distribution pipeline through road crossing by adopting Jack Pushing method near Natun Bazar more to Augmentation of Murarai Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 405/AE/NSD | 05/09/2022 | 30 | M/S PROCHESTA ENTERPRISE | 4.97 | 4.89 | 100 | 100
1467 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking of 200 mm dia. & 87 mtr. deep Tube well fitted with PVC pipe and fibre glass Strainer at new Head Work site (Tube well-2) Augmentation of Murarai Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 389/AE/NSD | 16/08/2022 | 60 | NUR MOBINUL ISLAM | 4.83 | 3.9 | 100 | 97
1468 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking of 200mm dia 87 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Kaitha PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | 636/AE/NSD | 03/12/2021 | 45 | ENAMUL ISLAM | 4.79 | 4.04 | 100 | 96
1469 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Construction of RCC Retaining Wall including Land filling towards approach of Pump House at Head Work site of Bara Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 412/AE/NSD | 08/09/2022 | 45 | DATA CONSTRUCTION | 4.99 | 4.98 | 100 | 100
1470 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Construction of Pump House of 5.40 mtr X 3.6 mtr. Size with sanitary and water supply arrangements at new Head work site of Murarai PWSS under Nalhati Sub-Division within Birbhum division, P.H.E. Dte. | 353/AE/NSD | 20/07/2022 | 60 | M/S S.N CONSTRUCTION | 4.84 | 4.78 | 100 | 100
1471 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply & Installation of Submersible Pumping machinery at newly sunk Tubewell & others allied works at Kaitha Augmentation water supply scheme under Bolpur Mechanical Division P.H.E. Dte. | 570/AE-III | 10/05/2022 | 20 | WEST BENGAL ENGINEERING CO. | 2.35 | 2.33 | 100 | 0
1472 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking of 200 mm dia & 87 mtr. deep Tube well fitted with PVC pipe and fibre glass Strainer for Augmentation of Bara (Zone-I) Water Supply Scheme at New Head Work site (Tube well-2) under Nalhati Sub-Division within Birbhum Division, PHE Dte.(Sl No - 06) | 440/NSD | 19/09/2022 | 45 | KAZI ZAKIR HOSSAIN | 4.82 | 4.41 | 100 | 0
1473 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking of 200 mm dia. & 87 mtr. deep Tube well fitted with PVC pipe and fibre glass Strainer at new Head Work site (Tube well-2) Augmentation of Lohapur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 485/AE/NSD | 20/10/2022 | 60 | GOLAM RASUL | 4.84 | 4.28 | 100 | 100
1474 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Replacement of existing pipeline by UPVC in Chatra Zone-I Water Supply Scheme under Nalhati Sub-Division under Birbhum Division, PHE Dte. | 371/AE/NSD | 23/07/2021 | 45 | ISLAM CONSTRUCTION | 4.84 | 4.46 | 100 | 100
1475 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Repairing and renovation of boundary wall near OHR site at Paikar Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 447/AE/NSD | 26/08/2021 | 45 | SHIB GANGA CONSTRUCTION | 4.84 | 4.82 | 100 | 100
1476 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | electric quotation bill for Aug of Bhadrapur | BP/2022-23-09 | 02/06/2022 | 0 | WBSEDCL | 1.39 | 0 | 0 | 0
1477 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | WBSEDCL quotation for Lohapur PWSS WS SCHEME under BOL MD PHE DTE | BP-2022-23-63 | 03/11/2022 | 0 | WBSEDCL | 4.94 | 0 | 0 | 0
1478 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Materials Payment | BP-2021-22-355 | 14/03/2022 | 0 | RESOURCES DIVISION | 1265.56 | 0 | 0 | 0
1479 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | WBSEDCL QUOTATION BILL FOR Bara WS SCHEME |  | 18/07/2022 | 0 | WBSEDCL | 4.02 | 0 | 0 | 0
1480 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | WBSEDCL QUOTATION FOR AUG.MURARAI WS SCHEME | BP-2022-23-53 | 20/09/2022 | 0 | WBSEDCL | 2.52 | 0 | 0 | 0
1481 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | WBSEDCL QUOTATION FOR AUG.MURARAI WS SCHEME | BP-2022-23-54 | 20/09/2022 | 0 | WBSEDCL | 1.35 | 0 | 0 | 0
1482 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | WBSEDCL Quotation bill for Bara ws scheme | BP-2022-23-21 | 04/08/2022 | 0 | WBSEDCL | 4.02 | 0 | 0 | 0
1483 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | WBSEDCL Quoation bill for Rajgram W/S Scheme | BP-2022-23-01 | 01/06/2022 | 0 | WBSEDCL | 10.48 | 0 | 0 | 0
1484 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | WBSEDCL Quoation bill for Rajgram W/S Scheme | BP-2022-23-03 | 01/06/2022 | 0 | WBSEDCL | 1.58 | 0 | 0 | 0
1485 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Laxminarayanpur Water Supply Scheme within Nalhati Sub-Division Birbhum Division, PHE Dte. (2nd Call). (Sl. No.14) | 562/BHM | 09/03/2022 | 60 | BELAL SK | 76.15 | 75.9 | 99.68 | 100
1486 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Distribution system relating to argumentation of Rajgram Zone-I Piped Water Supply Scheme under Murarai-I Block, District - Birbhum, under Birbhum Division, PHE Dte. (Sl. No.-2) | 647/BHM | 25/03/2022 | 180 | MANASH GHOSH | 309.72 | 309.72 | 100 | 100
1487 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Extension by HDPE Pipeline for the left out villages for proposed Augmentation of Bhadrapur Zone-I Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte.(Sl. No.2) | 1934/BHM | 06/09/2022 | 60 | M/S GOUTAM DAS | 160.74 | 159.95 | 99.51 | 100
1488 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Murarai water supply scheme (T.W No.-I), under Bolpur Mechanical Division PHE Dte | 964/Bol.MD | 13/10/2022 | 60 | S.K.ELECTRICALS | 20.95 | 19.72 | 94.13 | 60
1489 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Bhadrapur Zone-I water supply scheme (T.W. No.-II), under Bolpur Mechanical Division PHE Dte. within Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | 104/Bol.MD | 07/02/2023 | 30 | M/S A.D.ENTERPRISE | 9.82 | 7.84 | 79.88 | 91
1490 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Providing electro-mechanical accessories and others for Augmentation of Murarai water supply scheme T.W. No.-II, under Bolpur Mechanical Division PHE Dte within Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | 103/Bol.M.D | 07/02/2023 | 30 | M/S SANTI CONSTRUCTION | 12.93 | 10.62 | 82.12 | 95
1491 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Allied works for extension of HDPE pipe line including FHTC of Bhadrapur (Zone-I) PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 1047/BHM | 31/03/2023 | 60 | M/S GOUTAM DAS | 96.04 | 61.29 | 63.82 | 0
1492 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and installation of Pumps and other electro-mechanical accessories for Augmentation of Bara Zone-I water supply scheme (T.W. No.-II), under Bolpur Mechanical Division PHE Dte. | 428/AE-III | 22/03/2023 | 20 | MASSK ENGINEERING WORKS | 3.48 | 0 | 0 | 0
1493 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and installation of Voltage Correction device & other allied work for Augmentation of Laxminarayanpur water supply scheme under Bolpur Mechanical Division PHE Dte | 713/Bol.MD | 19/04/2023 | 45 | QUAZI NOZRUL ISLAM | 14.45 | 14.45 | 100 | 0
1494 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | OPERATION AND GUARDING OF PUMPING MACHINERY AND OTHERS AT AUGMENTATION OF MURARAI WATER SUPPLY SCHEME.UNDER CENTRAL MECHANICAL DIVISION P.H .E DTE. | 778/AE-III | 27/06/2023 | 92 | S. K. ENTERPRISE | 0.75 | 0 | 0 | 0
1495 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Operation and Guarding of Pumping Machinery and others at Augmentation of Bhadrapur Zone-I Water Supply Scheme under Bolpur Mechanical Division, P.H.E. Dte. | 415/AE-III | 21/03/2023 | 91 | M/S A.D.ENTERPRISE | 0.74 | 0 | 0 | 0
1496 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | OPERATION AND GUARDING OF PUMPING MACHINERY AND OTHERS AT AUGMENTATION OF BARA Zone-I WATER SUPPLY SCHEME UNDER CENTRAL MECHANICAL DIVISION P.H .E DTE. | 653/AE-III | 26/04/2023 | 61 | SINHA ELECTRICALS | 0.5 | 0 | 0 | 0
1497 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply, delivery and installation of flow meter at for Augmentation of Laxminarayanpur water Supply under Bolpur Mechanical Division, P.H.E. Dte. | 1043/AE-III | 07/08/2023 | 15 | QUAZI NOZRUL ISLAM | 2.65 | 0 | 0 | 0
1498 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Repairing of pump foundation and allied works at pump House under Augmentation of Bara piped water supply scheme.(Block Nalhati-II) under Bolpur Mechanical Division, PHE. Dte. | 1076/AE-III | 21/08/2023 | 10 | SINHA ELECTRICALS | 0.28 | 0 | 0 | 0
1499 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking of 200 mm dia. 87 mtr. deep Tube well by rotary rig method using UPVC deep well screen (RDS) pipes with Ribs 200 mm dia. At Chatra Zone-II Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 444/AE/NSD | 26/08/2021 | 60 | ISLAM CONSTRUCTION | 4.79 | 3.45 | 100 | 100
1500 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Paikar W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 532/AE/NSD | 08/10/2021 | 45 | SHIB GANGA CONSTRUCTION | 4.74 | 4.74 | 100 | 100
1501 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Paikar Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte | 507/AE/NSD | 01/10/2021 | 45 | SHIB GANGA CONSTRUCTION | 4.67 | 4.66 | 100 | 100
1502 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking of 200mm dia 87 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Bhadrapur Zone-I (near OHR side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | 634/AE/NSD | 03/12/2021 | 45 | MD. SHAHA JAMAL | 4.79 | 3.48 | 100 | 50
1503 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking of 200mm dia 87 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Bhadrapur Zone-I (near river side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | 635/AE/NSD | 03/12/2021 | 45 | GOLAM RASUL | 4.79 | 3.49 | 100 | 100
1504 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking of 200mm dia 87 m. deep tubewell fitted with PVC pipe and fibre glass Strainer at Bhadrapur Zone-II PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | 633/AE/NSD | 03/12/2021 | 45 | RAJA CONSTRUCTION | 4.79 | 3.86 | 100 | 100
1505 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Renovation of Boundary wall at Head Work Site (West Side) at Paikar Water Supply Scheme under Nalhati Sub Division within Birbhum Division Phe.Dte. | 348/AE/NSD | 19/07/2022 | 45 | BISWAJIT RABIDAS | 3.09 | 3.04 | 100 | 0
1506 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and installation of Pumps and other electro-mechanical accessories for Augmentation of Rajgram water supply scheme under Bolpur Mechanical Division PHE Dte | 421/Bol.M.D | 12/05/2022 | 45 | QUAZI NOZRUL ISLAM | 18.29 | 18.08 | 100 | 0
1507 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Bara Zone-I water supply scheme (T.W No.-I), under Bolpur Mechanical Division PHE Dte | 856/Bol.MD | 15/09/2022 | 60 | SINHA ELECTRICALS | 21.35 | 19.63 | 97.14 | 100
1508 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Laying distribution system for proposed augmentation scheme for Bara Zone-II Piped Water Supply Scheme under Nalhati-II Block, under Birbhum Division, PHE Dte.(Sl. No.1) | 805/BHM | 12/04/2022 | 180 | MANASH GHOSH | 397.16 | 395.53 | 100 | 100
1509 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Inter-connection between 2 nos. Tube wells to Pump House at Lohapur Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | 570/NSD | 19/12/2022 | 45 | GOLAM RASUL | 0.97 | 0 | 0 | 100
1510 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Laying distribution system for proposed augmentation scheme for Kaytha piped water supply scheme nalhati-I Block under Birbhum Division PHE Dte. (2nd Call) (Sl.No1) | 1159/BHM | 23/05/2022 | 312 | PRANAB KUMAR GHOSH | 278.72 | 229.02 | 82.23 | 95
1511 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Inter-connection between 2 nos. Tube wells to Pump House near new Head Work site at Augmentation of Murarai Piped Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | 572/NSD | 19/12/2022 | 45 | NUR MOBINUL ISLAM | 0.97 | 0.67 | 100 | 100
1512 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Laying distribution system for proposed augmentation scheme for Chatra Piped Water Supply Scheme under Murarai ? I Block, under Birbhum Division, PHE Dte.?(Sl. No.3) | 957/BHM | 28/04/2022 | 180 | M/S GOUTAM DAS | 427.38 | 378.26 | 88.52 | 100
1513 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Bhadrapur Zone-I water supply scheme (T.W No.-I), under Bolpur Mechanical Division PHE Dte | 965/Bol.MD | 13/10/2022 | 60 | RAJIB COMPANY | 21.92 | 20.7 | 100 | 80
1514 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and delivery of Sluice Valve for Augmentation of Rajgram W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. (2nd Call) (Sl No-1) | 666//BHM | 28/02/2023 | 30 | AMRT INDUSTRIES PRIVATE LIMITED | 8.42 | 8.42 | 100 | 100
1515 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Lohapur water supply scheme (T.W No.-I), under Bolpur Mechanical Division PHE Dte within Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division | 105/Bol.M.D | 07/02/2023 | 60 | SHIVAM ENTERPRISE | 21.47 | 19.47 | 96.09 | 100
1516 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Emergent repairing & relaying of 150 mm dia. DI Rising main of Laxminarayanpur PWSS under Nalhati Sub-Division within Birbhum Division, PHED. | 132/NSD | 31/03/2023 | 30 | HUMAYUN KABIR | 0.96 | 0.69 | 100 | 100
1517 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Material Requisition To Resource Division | 559/BHM | 08/03/2022 | 0 | Resource Division | 1638.42 | 0 | 0 | 0
1518 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Material Requisition To Resource Division | 2291/BHM | 20/10/2022 | 0 | Resource Division | 187.32 | 0 | 0 | 0
1519 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Material Requisition To Resource Division | 2295/BHM | 20/10/2022 | 0 | Resource Division | 15.26 | 0 | 0 | 0
1520 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Material Requisition To Resource Division | 2289/BHM | 20/10/2022 | 0 | Resource Division | 115.36 | 0 | 0 | 0
1521 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Material Requisition To Resource Division | 2207/BHM | 12/10/2022 | 0 | Resource Division | 251.49 | 0 | 0 | 0
1522 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Material Requisition To Resource Division | 1121/BHM | 10/04/2023 | 0 | Resource Division | 32.67 | 0 | 0 | 0
1523 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Material Requisition To Resource Division | 817/BHM | 15/03/2023 | 0 | Resource Division | 36.51 | 0 | 0 | 0
1524 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Material Requisition To Resource Division | 2070/BHM | 14/06/2023 | 0 | Resource Division | 36.96 | 0 | 0 | 0
1525 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Material Requisition To Resource Division | 945/BHM | 24/03/2023 | 0 | Resource Division | 157.64 | 0 | 0 | 0
1526 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Material Requisition To Resource Division | 2278/BHM | 13/07/2023 | 0 | Resource Division | 118.06 | 0 | 0 | 0
1527 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Material Requisition To Resource Division | 3575/ BHM | 18/08/2023 | 0 | Resource Division | 1.91 | 0 | 0 | 0
1528 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | ELECTRIC QUOTATION BILL FOR BARA WS SCHEME | BP-2023-2024-07 | 13/04/2023 | 0 | WBSEDCL | 1.8 | 0 | 0 | 0
1529 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sarda Bujung road from 0.00 km to 3.20 km under Birbhum Highway Division-I in the District of Birbhum Restoration work of hard shoulder portion with Jhama metal consolidation and moorum damaged by the PHE Dte. | BP-2023-24-64 | 08/06/2023 | 0 | SAMSHER HOSSAIN | 5.16 | 0 | 0 | 0
1530 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Lohapur Gumani setu with a link to lohapur railway station from 0.00 kmp and from 2.00 kmp to 6.40km under Birbhum Highway Division-I in the district of Birbhum Restoration of Widening. | BP-2023-24-61 | 07/06/2023 | 0 | NATIONAL CONSTRUCTION | 9.65 | 0 | 0 | 0
1531 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | wbsedcl quotation for amdol ws scheme |  | 28/07/2023 | 0 | WBSEDCL | 3.65 | 0 | 0 | 0
1532 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Construction of 1000 Cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for Augmentation of Lohapur Water Supply Scheme under Birbhum Division, PHE Dte. (As per Departmental Drawing). | 2203/BHM | 12/10/2022 | 9 | SUNIL RABI DAS | 200.79 | 40.16 | 20 | 40
1533 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Allied work for Extension of Pipe line including FHTC Work along with restoration of PWD & Other Connecting roads for Augmentation of Chatra Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. (Sl. No.2) | 46/BHM | 04/01/2023 | 1050 | M/S GOUTAM DAS | 222.76 | 90.69 | 40.71 | 61
1534 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Construction of 700 cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Pile foundation including pipe connection & allied works for augmentation of Chatra W/S Scheme under Nalhati Sub Division with Birbhum Division, PHE Dte.(As per Departmental Drawing | 1289/BHM | 18/04/2023 | 275 | RAJGRAM FAV CO OPT LAB CON AND CONST SO LTD | 152.19 | 30.44 | 20 | 82
1535 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and Installation of open well submersible Pumping machinery at existing CWR for Augmentation of Lakshminarayanpur water supply scheme under Bolpur Mechanical Division, PHE. Dte. | 1006/AE-III | 25/07/2023 | 15 | QUAZI NOZRUL ISLAM | 1.63 | 0 | 0 | 100
1536 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for new OHR site at Bhadrapur (Zone-II) Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 71/AE/NSD | 11/02/2022 | 15 | GEOCON INDIA | 0.99 | 0.99 | 100 | 0
1537 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Distribution system Relating to argumentation of Bhadrapur Zone-I Water Supply Scheme under Nalhati - I Block, District- Birbhum, under Birbhum Division, PHE Dte. (Sl. No.-1) | 548/BHM | 07/03/2022 | 240 | M/S GOUTAM DAS | 505.15 | 165.87 | 66.9 | 100
1538 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Construction of 1000 Cum Capacity and 20.0m Staging Height RCC Over Head Reservoir along with Soil Test and Laying of HDPE pipeline from node point 6 to 13 and node point 272 to 378 and cutting & restoration of concrete road for laying of extension pipeline including FHTC for Augmentation of Murarai w/s Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | 2277/BHM | 19/10/2022 | 365 | SK ALIM | 720.71 | 530.44 | 73.6 | 100
1539 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Construction of 900cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC pile foundation including pipe connection & allied works for augmentation of Bhadrapur Zone-I W/S Scheme under Birbhum Division, PHE Dte. (As per Departmental Drawing)¿ (Sl. No.1) | 2467/BHM | 11/11/2022 | 273 | M/S. JAN MAHAMMAD | 185.25 | 74.1 | 40 | 100
1540 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Inter-connection between 2 nos. Tube wells to Pump House at Bara Zone-I Piped Water Supply Scheme under Nalhati Sub-Division, PHE Dte. | 569/NSD | 19/12/2022 | 135 | DATA CONSTRUCTION | 0.97 | 0 | 0 | 100
1541 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and installation of Pumps and other electro-mechanical accessories for Augmentation of Lohapur water supply scheme (T.W. No.-II), under Bolpur Mechanical Division PHE Dte. | 426/AE-III | 22/03/2023 | 20 | SUNIL RABIDAS | 4.34 | 1.91 | 84.07 | 100
1542 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Emergent repair and replacement of Pipeline below the Railway culvert near Murarai Railway Station with allied works including extension of Pipe line of Murarai Aug. w/s Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | 1723/BHM | 12/05/2023 | 45 | SK ALIM | 20.14 | 0 | 0 | 100
1543 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Allied for balance work of distribution pipeline for Dhitora (Part) village including FHTC under Augmentation of Murarai W/S Scheme under Nalhati Sub-division within Birbhum Division P.H.E. Dte. | 1722/BHM | 12/05/2023 | 30 | M/S PROCHESTA ENTERPRISE | 35.04 | 21.76 | 62.43 | 100
1544 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Construction of 550 cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Kaytha W/S Scheme under Na Division hati Sub Division with Birbhum Division, PHE Dte.(As per Departmental Drawing | 1183/BHM | 12/04/2023 | 275 | S K CONSTRUCTION | 142.19 | 56.88 | 40 | 100
1545 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Construction of 900 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and Allied for balance work of distribution pipeline including 315mm dia HDPE pipeline instead of 350mm dia DI pipeline along with restoration of roads and providing FHTC for Paikar w/s Scheme under Nalhati Sub-Division within Birbhum Division,P.H.E. Dte | 1100/BHM | 06/04/2023 | 636 | SK ALIM | 455.72 | 171.32 | 37.59 | 100
1546 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Allied work for Laying HDPE pipeline instead of DI Pipeline including Dismantling and restoration of Cement Concrete road for Augmentation of Bara Zone-I Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | 1978/BHM | 05/06/2023 | 45 | PASCON | 27.73 | 27.73 | 100 | 100
1547 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Balance work for 160 mm dia HDPE Distribution main for Laksminarayanpur W/S Scheme, under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. | 1945/BHM | 01/06/2023 | 45 | HUMAYUN KABIR | 37.63 | 33.15 | 88.44 | 100
1548 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking replacement of 200mm dia Tube Well of UPVC pipe 90m deep with fibre glass strainer including connecting main for Lakshminaraynpur PWSS under Nalhati Sub- Division within Birbhum Division PHED. | 1947/BHM | 01/06/2023 | 45 | A R ENTERPRISE | 7.95 | 0 | 0 | 100
1549 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking of 1 no. new 200mm dia Tube Well of UPVC pipe 90m deep with fibre glass strainer including connecting main for Rajgram PWSS at Jagannathpur CWR site under Nalhati Sub- Division within Birbhum Division PHED. | 2073/BHM | 08/06/2023 | 30 | AJIMUL ISLAM | 6.7 | 0 | 0 | 100
1550 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Laying distribution system for proposed augmentation scheme for Bhadrapur Zone-II Piped Water Supply Scheme under Nalhati-II Block, under Birbhum Division, PHE Dte. (Sl. No.2) | 806/BHM | 12/04/2022 | 180 | SUNIL RABI DAS | 407.95 | 385.53 | 96.2 | 100
1551 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply delivery ,installation of MCC Panel and allied works at High Lift Site of Murarai water supply scheme [within Augmentation of Murarai Water Supply Scheme] under Bolpur Mechanical Division PHE Dte.. | 2251/BOL.MD. | 13/09/2023 | 60 | M/S SAJAHAN CHOWDHURY | 11.4 | 0 | 0 | 100
1552 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and installation of manual operated Motor control panel at Pump House No. II of Chatra (Zone-II) water supply scheme under Bolpur Mechanical Division, PHE Dte. | 549/BMSD(D) | 24/11/2023 | 30 | S.P. CONSTRUCTION | 2.97 | 0 | 0 | 100
1553 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and installation of manual operated Motor control panel at Pump House No. II of Chatra (Zone-I) water supply scheme under Bolpur Mechanical Division, PHE Dte. | 551/BMSD(D) | 24/11/2023 | 30 | ABHISEK ENGTNEERING CONCERN | 2.05 | 0 | 0 | 100
1554 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and installation of manual operated Motor control panel at Pump House No. I of Chatra (Zone-II) water supply scheme under Bolpur Mechanical Division, PHE Dte. | 548/BMSD(D) | 24/11/2023 | 30 | SARKAR ELECTRICAL | 2.05 | 0 | 0 | 100
1555 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply, delivery and installation of servo motor operated copper wound line voltage corrector at Pump House No. I of Chatra (Zone-I) water supply scheme under Bolpur Mechanical Division, PHE Dte. | 553/BMSD(D) | 24/11/2023 | 30 | SINHA ELECTRICALS | 4.18 | 0 | 0 | 100
1556 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and installation of manual operated Motor control panel at Pump House No. I of Chatra (Zone-I) water supply scheme under Bolpur Mechanical Division, PHE Dte. | 552/BMSD(D) | 24/11/2023 | 30 | UTTAM KUMAR CHATTERJEE | 2.33 | 0 | 0 | 100
1557 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Erection of Cable on O.H pole and other allied works at Augmentation of Lohapur water supply scheme (T.W No- II) (Block-Nalhati-II) under Bolpur Mechanical Division, PHE Dte. | 1657/AE-III | 22/12/2023 | 7 | SUNIL RABIDAS | 0.68 | 0 | 0 | 100
1558 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and installation of manual operated Motor control panel and other allied works for Pump House No.III of Murarai Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. | 018/BMSD(D) | 22/01/2024 | 30 | QUAZI NOZRUL ISLAM | 2.44 | 0 | 0 | 100
1559 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply, delivery and installation of servo motor operated copper wound line voltage corrector and other allied works at Pump House No.III of Murarai water supply scheme under Bolpur Mechanical Division, PHE Dte. | 019/BMSD(D) | 22/01/2024 | 30 | M/S. UTTAM KUMAR CHATTERJEE | 3.62 | 0 | 0 | 100
1560 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Replacement of power cable of distance pump of PH-I at Lohapur Water Supply Scheme (P.H.-I) (Block-Nalhati-II) under Bolpur Mechanical Division, PHE Dte. | 510/BOL.MD | 13/03/2024 | 30 | SINHA ELECTRICALS | 9.13 | 0 | 0 | 100
1561 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and delivery of Kit kat fuse, Main switch, change over, Busbar switch for Augmentation of Murarai Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. | 649/BMSD(D) | 02/09/2024 | 30 | BIRBHUM ELECTRIC WORKS | 2.42 | 0 | 0 | 100
1562 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and delivery of electro-mechanical accessories for Rajgram Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. | 651/BMSD(D) | 02/09/2024 | 30 | TAPAN ENTERPRISE | 1.89 | 0 | 0 | 100
1563 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and delivery of Submersible pump motor set and accesssories for Rajgram Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. | 662/BMSD(D) | 03/09/2024 | 30 | M/S. UTTAM KUMAR CHATTERJEE | 2.16 | 0 | 0 | 100
1564 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply and Delivery of Sub-Mersible Pump Controllers for Augmentation of Kaytha water supply scheme (Block- Nalhati - I) under Bolpur Mechanical Division, PHE Dte. | 688./AE-III | 08/04/2024 | 21 | M/S. YOUTH ENGINEERS' ENTERPRISE | 2.98 | 0 | 0 | 100
1565 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | wbsedcl quotation for lohapur ws scheme | BP-23-24-278 | 29/02/2024 | 0 | WBSEDCL | 3.4 | 0 | 0 | 0
1566 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Quotation deposit for empowering Sadashibpur Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. | BP-24-25-135 | 29/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.51 | 0 | 0 | 0
1567 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | WBSEDCL QUOTATION FOR LOKEPUR DAS PARA SCHEME UNDER RAJGRAM WS SCHEME | BP-23-24-322 | 18/03/2024 | 0 | WBSEDCL | 0.09 | 0 | 0 | 0
1568 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | WBSEDCL QUOTATION FOR KARULIA MINI SCHEME UNDER RAJGRAM WS SCHEME | BP-23-24-321 | 18/03/2024 | 0 | WBSEDCL | 0.45 | 0 | 0 | 0
1569 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | WBSEDCL QUOTATION FOR ASENGA PH NO I UNDER RAJGRAM WS SCHEME | BP-23-24-323 | 18/03/2024 | 0 | WBSEDCL | 3.22 | 0 | 0 | 0
1570 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Quotation for new service connection at Kaitha PWSS (Block-Nalhati - I), Lohapur CCC, WBSEDCL | BP-24-25-100 | 02/07/2024 | 0 | WBSEDCL | 6.71 | 0 | 0 | 0
1571 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Additional Quotation deposit for empowering Augmentation of Rajgram Water Supply Scheme in Murarai CCC under Bolpur Mechanical Division, PHE Dte. | BP-24-25-99 | 02/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.24 | 0 | 0 | 0
1572 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Sinking of 200 mm dia 51.0 m deep Tube wells, Construction of Pump-House with retaining wall & inspection path including Land development and Laying of 250 mm dia HDPE rising main with interconnection of Rajgram w/s Scheme, under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte.¿ (Sl. No.2) | 1072/BHM | 13/05/2022 | 161 | SUNIL RABI DAS | 108.04 | 98.47 | 91.14 | 100
1573 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Laying of Rising main from existing OHR (Zone-I) to proposed OHR (Zone-II) of Rajgram for Augmentation of Rajgram (Zone-II) Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 457/NSD | 27/09/2022 | 210 | S P CONSTRUCTION | 4.98 | 0 | 0 | 100
1574 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Allied work for Laying of Balance pipe line of different dia as per revised drawing including Jack pushing with restoration of road and pipe carrying stracture along with extension of pipe line and balance FHTC of Augmentation of Lohapur Water Supply Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte.(Sl. No.1) | 259/BHM | 30/01/2023 | 600 | SUNIL RABI DAS | 325.53 | 203.29 | 62.45 | 93
1575 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Withrawing, Lowering & Cable laying of Submersible Pumping machinery at Laxminarayanpur water supply scheme, under Bolpur Mechanical Division P.H.E. Dte. within Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division. | 553/AE-III | 05/04/2023 | 20 | MONI ELECTRICAL WORKS | 2.83 | 2.81 | 99.1 | 100
1576 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Allied works for Laying of 315 mm dia. HDPE pipe line instead of 350 mm dia. D.I. pipe line along with laying of 90 mm dia. HDPE pipe line to the left-out habitations along with restoration of road including Jack Pushing/augor boring of Rajgram (Zone-I) PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 1246/BHM | 17/04/2023 | 806 | MANASH GHOSH | 177.06 | 94.91 | 53.6 | 96
1577 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Construction of 600 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including raft foundation and Balance work of distribution pipeline including extension of pipeline along with FHTC and restoration of roads for Bhadrapur Z-II w/s Scheme under Nalhati Sub-Division within Birbhum Division,P.H.E. Dte. | 1107/BHM | 10/04/2023 | 549 | SUNIL RABI DAS | 229.46 | 119.73 | 52.18 | 100
1578 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Construction of 400 cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Pile foundation including pipe connection & allied works for augmentation of Bara Zone I W/S Scheme under Nalhati Sub Division with Birbhum Division, PHE Dte.(As per Departmental Drawing | 1184/BHM | 12/04/2023 | 275 | TAPAN KUMAR DATTA | 112 | 0 | 0 | 65
1579 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Providing Electro-mechanical accessories including other allied works for Augmentation of Paikar Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte | 2246/Bol.MD | 13/09/2023 | 571 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 32.14 | 0 | 0 | 70
1580 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Distribution system relating to argumentation of Rajgram Zone-II Water Supply Scheme under Murarai-I Block, District- Birbhum, under Birbhum Division, PHE Dte. (Sl. No.-3) | 550/BHM | 07/03/2022 | 360 | S P CONSTRUCTION | 401.32 | 341.17 | 87.39 | 99
1581 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Laying distribution system for proposed augmentation scheme for Laxminarayanpur Piped Water Supply Scheme under Nalhati-I Block, under Birbhum Division, PHE Dte.(Sl. No.3) | 803/BHM | 12/04/2022 | 549 | PASCON | 297.86 | 254.09 | 93.17 | 100
1582 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Laying distribution system including functional household connection for proposed augmentation scheme for BARA Zone-I Piped Water Supply Scheme under Nalhati-II Block under Birbhum Division, PHE Dte.? (Sl. No.2) | 860/BHM | 20/04/2022 | 922 | PASCON | 392.49 | 347.65 | 88.65 | 80
1583 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Allied works for replacement of MS pipe line in place of DI pipe,including restortion of road of Augmentation of Rjgram Water Supply Scheme (Zone-II) under Nalhati Sub-Division within Birbhum Division, PHE Dte. (Sl. No.4) | 2690/BHM | 06/12/2022 | 150 | S P CONSTRUCTION | 195.67 | 143.47 | 94.78 | 91
1584 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Laying distribution system including FHTC for proposed augmentation scheme for Paikar Piped Water Supply Scheme Mararai-II Block under Birbhum Division PHE Dte (Sl.No. 2) | 1456/BHM | 07/07/2022 | 968 | SK ALIM | 663.22 | 455.75 | 68.72 | 80
1585 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Allied work for Balance work of distribution Pipe line including FHTC Work along with restoration of PMGSY road Flank & Other Connecting road including dismantling work with Augur Boring for Augmentation of Bara Zone-I Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | 1243/BHM | 17/04/2023 | 562 | PASCON | 97.58 | 37.08 | 38.01 | 55
1586 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Allied work for Balance work of distribution Pipe line including FHTC Work along with restoration of PWD road Flank & Other Connecting road including dismantling work with jack pushing, Augur Boring for Augmentation of Bara Zone-II Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | 1099/BHM | 06/04/2023 | 180 | MANASH GHOSH | 199.45 | 183.16 | 91.89 | 95
1587 | BIRBHUM | Birbhum Division | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Allied work for Balance work of distribution Pipe line including FHTC Work along with restoration of PWD road Flank & Other Connecting road including dismantling work with jack pushing, Augur Boring for Augmentation of Kaytha Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | 1428/BHM | 25/04/2023 | 270 | PRANAB KUMAR GHOSH | 133.64 | 54.85 | 41.16 | 55
1588 | BIRBHUM | Bolpur Mechanical | Augmentation of Rajgram PWSS, Murarai PWSS, Chatra PWSS, Paikar PWSS, Bhadrapur (Zone-I) PWSS, Kaytha PWSS, Lakshinarayanpur PWSS, Bara PWSS, Lohapur PWSS, Bhadrapur (Zone-II) PWSS under Birbhum Division , SM/10319 | Augmentation | Supply, delivery and installation of servo motor operated copper wound line voltage corrector at P/H-II for Paikar water supply scheme of Murarai-II Block under Bolpur Mechanical Division, PHE | 3878/BOL.MD | 20/09/2024 | 227 | RSA ENTERPRISE | 6.89 | 0 | 0 | 100
1589 | BIRBHUM | Birbhum Division | KUSHIPUR PIPES WATER SUPPLY SCHEME. , SM/12599 | New | Material Requisition To Resource Division | 1452/BHM | 25/04/2023 | 0 | Resource Division | 8.28 | 0 | 0 | 0
1590 | BIRBHUM | Bolpur Mechanical | KUSHIPUR PIPES WATER SUPPLY SCHEME. , SM/12599 | New | Providing Electro-mechanical accessories and others for Kushipur PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | 3540/BOL.MD | 30/11/2023 | 60 | S.G.TECHNICAL SERVICES | 27.3 | 0 | 0 | 40
1591 | BIRBHUM | Bolpur Mechanical | KUSHIPUR PIPES WATER SUPPLY SCHEME. , SM/12599 | New | QUOTATION FOR KUHSIPUR PH 2 NALHATI-I BLOCK | BP-24-25-04 | 09/04/2024 | 0 | WBSEDCL | 5.3 | 0 | 0 | 0
1592 | BIRBHUM | Bolpur Mechanical | KUSHIPUR PIPES WATER SUPPLY SCHEME. , SM/12599 | New | WBSEDCL QUOTATION FOR KUSHIPUR W/S SCHEME PH-2 (NALHATI-1) |  | 27/03/2024 | 0 | WBSEDCL | 5.3 | 0 | 0 | 0
1593 | BIRBHUM | Birbhum Division | KUSHIPUR PIPES WATER SUPPLY SCHEME. , SM/12599 | New | Different works related to water supply scheme at KANIOR, KOGRAM & KUSHIPUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1059/BHM | 31/03/2023 | 915 | SK ALIM | 1229.19 | 0 | 0 | 25
1594 | BIRBHUM | Birbhum Division | Abdullahpur Piped Water Supply Scheme. , SM/12679 | New | Material Requisition To Resource Division | 1436/BHM | 25/04/2023 | 0 | Resource Division | 40.75 | 0 | 0 | 0
1595 | BIRBHUM | Bolpur Mechanical | Abdullahpur Piped Water Supply Scheme. , SM/12679 | New | Supply and delivery of Submersible pump motor set for Abdullapur Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. | 653/BMSD(D) | 02/09/2024 | 30 | HINDOL ROY | 1.51 | 0 | 0 | 100
1596 | BIRBHUM | Bolpur Mechanical | Abdullahpur Piped Water Supply Scheme. , SM/12679 | New | Supply and delivery of Al. armoured cable, Sluice Valve, NRV for Abdullapur Water Supply Scheme of Murarai-I block under Bolpur Mechanical Division PHE Dte. | 654/BMSD(D) | 02/09/2024 | 30 | SATYAJIT GHOSH | 2.55 | 0 | 0 | 100
1597 | BIRBHUM | Bolpur Mechanical | Abdullahpur Piped Water Supply Scheme. , SM/12679 | New | Quotation deposit for empowering Abdullapur Water Supply Scheme P/H-II in Paikar CCC under Bolpur Mechanical division, PHE Dte. | BP-2024-25-268 | 27/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.97 | 0 | 0 | 0
1598 | BIRBHUM | Bolpur Mechanical | Abdullahpur Piped Water Supply Scheme. , SM/12679 | New | Providing Electro-mechanical accessories and others for ABDULLAPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 3287/Bol.MD | 29/09/2023 | 641 | MENAKA ENTERPRISE | 41.33 | 0 | 0 | 65
1599 | BIRBHUM | Birbhum Division | Chanchali piped water supply scheme. , SM/12683 | New | Material Requisition To Resource Division | 1487/BHM | 25/04/2023 | 0 | Resource Division | 157.22 | 0 | 0 | 0
1600 | BIRBHUM | Bolpur Mechanical | Chanchali piped water supply scheme. , SM/12683 | New | Quotation deposit for empowering Chanchali P/H-I Water Supply Scheme, Nandigram Kalitala in Paikar CCC under Bolpur Mechanical Division, PHE Dte | BP-2024-2025-79 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.5 | 0 | 0 | 0
1601 | BIRBHUM | Bolpur Mechanical | Chanchali piped water supply scheme. , SM/12683 | New | Quotation deposit for Chanchali Water Supply Scheme P/H-II in Paikar CCC under Bolpur Mechanical division, PHE Dte. | BP-24-25-180 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.04 | 0 | 0 | 0
1602 | BIRBHUM | Bolpur Mechanical | Chanchali piped water supply scheme. , SM/12683 | New | Providing Electro-mechanical accessories and others for CHANCHALI piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 2173/Bol.MD | 01/09/2023 | 608 | M/S. SREEJIT ENTERPRISE | 30.68 | 0 | 0 | 70
1603 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BISERGHATA AND OTHER 23 NOS. MOUZAS UNDER BOLPUR SRINIKETAN BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/12070 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 330.16 | 38.98 | 92
1604 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR BISERGHATA AND OTHER 23 NOS. MOUZAS UNDER BOLPUR SRINIKETAN BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/12070 | New | Road restoration work at different villages under implementation of Mini Piped Water Supply Scheme within Bolpur Sriniketan Block having less than 100 Households under Birbhum Division PHE Dte. | 2209/BHM | 26/08/2025 | 90 | SOURAV MONDAL | 21.17 | 0 | 0 | 0
1605 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Amdole Phase-II Water Supply Scheme , SM/12664 | Retrofitting | Extension of pipeline of different left out habitations including FHTC along with 1 no. Pump House as boosting of water supply of Amdol water supply scheme under Nalhati Sub-Division, within Birbhum Division PHE Dte (Sl. No.7) | 2780/BHM | 14/12/2022 | 900 | KAMIRUL SK AND CO | 211.6 | 56.95 | 100 | 75
1606 | BIRBHUM | Birbhum Division | Paikpara Piped Water Supply Scheme. , SM/12669 | New | Material Requisition To Resource Division | 1587/BHM | 26/04/2023 | 0 | Resource Division | 8.06 | 0 | 0 | 0
1607 | BIRBHUM | Bolpur Mechanical | Paikpara Piped Water Supply Scheme. , SM/12669 | New | Providing Electro-mechanical accessories and others for Paikpara & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2100/Bol.MD | 22/08/2023 | 588 | SATYAJIT GHOSH | 27.98 | 0 | 0 | 70
1608 | BIRBHUM | Birbhum Division | Paikpara Piped Water Supply Scheme. , SM/12669 | New | Different works related to water supply scheme at NETURI, PAIKPARA & PAKURIA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 3441/BHM | 03/08/2023 | 940 | SHREE J.M. CONSTRUCTION | 1236.08 | 0 | 0 | 54
1609 | BIRBHUM | Birbhum Division | Paikpara Piped Water Supply Scheme. , SM/12669 | New | Road crossing, repairing & restoration of damage pipe lines & PCC roads, sluice valve chambers including all allied works for Paikpara Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | 1510/BHM | 23/05/2025 | 90 | SHREE J.M. CONSTRUCTION | 8.94 | 0 | 0 | 0
1610 | BIRBHUM | Bolpur Mechanical | Paikpara Piped Water Supply Scheme. , SM/12669 | New | Supply & Installation of 20kVA Votage Correction Devices at Paikpara water supply scheme (P/H-1 & P/H-II) (Block- Nalhati - I) under Bolpur Mechanical Division, PHE Dte. | 2029./AE-III | 19/12/2024 | 21 | BIRBHUM ELECTRIC WORKS | 4.97 | 0 | 0 | 100
1611 | BIRBHUM | Birbhum Division | MATIARA PIPED WATER SUPPLY SCHEME. , SM/12674 | New | Material Requisition To Resource Division | 1365/BHM | 24/04/2023 | 0 | Resource Division | 12.93 | 0 | 0 | 0
1612 | BIRBHUM | Bolpur Mechanical | MATIARA PIPED WATER SUPPLY SCHEME. , SM/12674 | New | Supply delivery of voltage correction device & laying of cable through underground trench at head work site of Matiara PWSS in the district of Birbhum, under P.H.E. Dte. | 3872/BOL.MD | 19/09/2024 | 30 | TULIP ENGINEERS CO OP. SOCIETY LTD. | 4.35 | 0 | 0 | 0
1613 | BIRBHUM | Bolpur Mechanical | MATIARA PIPED WATER SUPPLY SCHEME. , SM/12674 | New | New service connection at Matiara PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-24-25-90 | 19/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.48 | 0 | 0 | 0
1614 | BIRBHUM | Birbhum Division | MATIARA PIPED WATER SUPPLY SCHEME. , SM/12674 | New | Different works related to water supply scheme at DERPUR, KURUMSAHA & MATIARA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 1245/BHM | 17/04/2023 | 1074 | BRAHMA CONSTRUCTION COMPANY | 978.83 | 0 | 0 | 65
1615 | BIRBHUM | Bolpur Mechanical | MATIARA PIPED WATER SUPPLY SCHEME. , SM/12674 | New | Providing Electro-mechanical accessories and others for Matiara & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2091/Bol.MD | 22/08/2023 | 754 | CINZANO | 27.89 | 0 | 0 | 50
1616 | BIRBHUM | Birbhum Division | MATIARA PIPED WATER SUPPLY SCHEME. , SM/12674 | New | Repairing of Pump House & construction of drain under Matiara Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | 2141/BHM | 19/08/2025 | 90 | BRAHMA CONSTRUCTION COMPANY | 17.25 | 0 | 0 | 0
1617 | BIRBHUM | Birbhum Division | UTTAR BANGAON PIPED WATER SUPPLY SCHEME. , SM/13626 | New | Material Requisition To Resource Division | 1369/BHM | 24/04/2023 | 0 | Resource Division | 37.66 | 0 | 0 | 0
1618 | BIRBHUM | Bolpur Mechanical | UTTAR BANGAON PIPED WATER SUPPLY SCHEME. , SM/13626 | New | Providing Electro-mechanical accessories and others for Uttar Bangaon & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 1927/Bol.MD | 11/08/2023 | 412 | P. K. ENGINEERING | 27.89 | 0 | 0 | 90
1619 | BIRBHUM | Bolpur Mechanical | UTTAR BANGAON PIPED WATER SUPPLY SCHEME. , SM/13626 | New | WBSEDCL QUOTATION FOR UTTAR BANGAOUN WS SCHEME | BP-23-24-303 | 15/03/2024 | 0 | WBSEDCL | 6.69 | 0 | 0 | 0
1620 | BIRBHUM | Bolpur Mechanical | UTTAR BANGAON PIPED WATER SUPPLY SCHEME. , SM/13626 | New | WBSEDCL QUOTATION FOR UTTAR BANGAON P H NO.I WS SCHEME | BP-23-24-199 | 12/12/2023 | 0 | WBSEDCL | 7.29 | 0 | 0 | 0
1621 | BIRBHUM | Birbhum Division | UTTAR BANGAON PIPED WATER SUPPLY SCHEME. , SM/13626 | New | Different works related to water supply scheme at ABHIRAMPUR, BEHIRA, SAMSA & UTTAR BANGAON and its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | 1437/BHM | 25/04/2023 | 820 | ASHOK KUMAR GHOSH | 1446.74 | 0 | 0 | 55
1622 | BIRBHUM | Central Drilling | BHALIAN PIPED WATER SUPPLY SCHME. , SM/12834 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X 200mm X 150Mtrs. depth) by utilising Departmental Machineries for Bhalian W/S Scheme (T/W-II) Sainthia Block under Birbum District, Central Drilling Division, PHE Dte. | 1131/CDD | 04/11/2022 | 30 | C.M. ENTERPRISE | 9.04 | 0 | 0 | 100
1623 | BIRBHUM | Birbhum Division | BHALIAN PIPED WATER SUPPLY SCHME. , SM/12834 | New | Material Requisition To Resource Division | 1379/BHM | 24/04/2023 | 0 | Resource Division | 41.06 | 0 | 0 | 0
1624 | BIRBHUM | Bolpur Mechanical | BHALIAN PIPED WATER SUPPLY SCHME. , SM/12834 | New | Providing Electro-mechanical accessories and others for Bhalian & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2088/Bol.MD | 22/08/2023 | 679 | MENAKA ENTERPRISE | 28.76 | 0 | 0 | 80
1625 | BIRBHUM | Bolpur Mechanical | BHALIAN PIPED WATER SUPPLY SCHME. , SM/12834 | New | WBSEDCL QUIOTATION FOR BHALIAN PH NO-I | BP-23-24-274 | 15/02/2024 | 0 | WBSEDCL | 0.96 | 0 | 0 | 0
1626 | BIRBHUM | Bolpur Mechanical | BHALIAN PIPED WATER SUPPLY SCHME. , SM/12834 | New | WBSEDCL QUOTATION FOR BHALIAN PWSS PUMP HOUSE NO-II | BP-2023-24-294 | 20/03/2024 | 0 | WBSEDCL | 4.72 | 0 | 0 | 0
1627 | BIRBHUM | Birbhum Division | BHALIAN PIPED WATER SUPPLY SCHME. , SM/12834 | New | Different works related to water supply scheme at BHALIAN, BANGJITA & BIRSINGHA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 1258/BHM | 17/04/2023 | 806 | NAUTANDAS AND CO | 1377.28 | 0 | 0 | 35
1628 | BIRBHUM | Birbhum Division | Tilai piped water supply scheme. , SM/13127 | New | Material Requisition To Resource Division | 1531/BHM | 26/04/2023 | 0 | Resource Division | 13.56 | 0 | 0 | 0
1629 | BIRBHUM | Bolpur Mechanical | Tilai piped water supply scheme. , SM/13127 | New | Providing Electro-mechanical accessories and others for Tilai & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 3529/Bol.MD | 29/11/2023 | 60 | MITRA ENTERPRISE | 26.05 | 0 | 0 | 30
1630 | BIRBHUM | Birbhum Division | Tilai piped water supply scheme. , SM/13127 | New | Material Requisition To Resource Division | 2483/BHM | 03/09/2024 | 0 | Resource Division | 7.68 | 0 | 0 | 0
1631 | BIRBHUM | Birbhum Division | Tilai piped water supply scheme. , SM/13127 | New | Sinking of 250 X 150 mm Dia tubewell Drilling by Direct Rotary method (Two Nos ), Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 150 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Tilai & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 2316/BHM | 21/08/2024 | 365 | S D CONSTRUCTION | 349.88 | 0 | 0 | 15
1632 | BIRBHUM | Bolpur Mechanical | Paratpur Piped Water Supply Scheme. , SM/13474 | New | Providing Electro-mechanical accessories and others for Paratpur & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | 3394/Bol.MD | 17/10/2023 | 90 | EASTERN INDIA SALES & SERVICE | 79.72 | 0 | 0 | 0
1633 | BIRBHUM | Birbhum Division | Paratpur Piped Water Supply Scheme. , SM/13474 | New | Material Requisition To Resource Division | 1401/BHM | 24/04/2023 | 0 | Resource Division | 70.19 | 0 | 0 | 0
1634 | BIRBHUM | Birbhum Division | Paratpur Piped Water Supply Scheme. , SM/13474 | New | Material Requisition To Resource Division | 3279/BHM | 27/07/2023 | 0 | Resource Division | 2.05 | 0 | 0 | 0
1635 | BIRBHUM | Birbhum Division | Paratpur Piped Water Supply Scheme. , SM/13474 | New | Different works related to water supply scheme at CHINPAI, LOBA & PARATPUR and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 3476/BHM | 08/08/2023 | 816 | B RAI CONSTRUCTION COMPANY | 2497.19 | 0 | 0 | 45
1636 | BIRBHUM | Birbhum Division | Kendangal Piped Water Supply Scheme. , SM/13642 | New | Material Requisition To Resource Division | 1360/BHM | 24/04/2023 | 0 | Resource Division | 16.65 | 0 | 0 | 0
1637 | BIRBHUM | Bolpur Mechanical | Kendangal Piped Water Supply Scheme. , SM/13642 | New | NEW SERVICE CONNECTION AT KENDRADANGAL WATER SUPPLY SCHEME. | BP-2024-25-140 | 06/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.31 | 0 | 0 | 0
1638 | BIRBHUM | Central Drilling | Kendangal Piped Water Supply Scheme. , SM/13642 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1639 | BIRBHUM | Birbhum Division | Kendangal Piped Water Supply Scheme. , SM/13642 | New | Different works related to water supply scheme at IKSHUDHARA, KANKALITALA, KASBA & KENDANGAL Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 4139/BHM | 18/10/2023 | 896 | M/S TAPAS KUMAR CHAKRABORTY | 2684.99 | 0 | 0 | 60
1640 | BIRBHUM | Birbhum Division | Srikantapur piped water supply scheme. , SM/13652 | New | Material Requisition To Resource Division | 1578/BHM | 26/04/2023 | 0 | Resource Division | 26.45 | 0 | 0 | 0
1641 | BIRBHUM | Birbhum Division | Srikantapur piped water supply scheme. , SM/13652 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 300 CuM capacity O.H.R. Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to SRIKANTAPUR water supply scheme at & its adjoining mouzas water supply scheme within Md. Bazar Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | 2112/BHM | 29/07/2024 | 365 | M/S R B ENTERPRISE | 571.1 | 0 | 0 | 0
1642 | BIRBHUM | Birbhum Division | Srikantapur piped water supply scheme. , SM/13652 | New | Material Requisition To Resource Division | 2448/BHM | 30/08/2024 | 0 | Resource Division | 13.19 | 0 | 0 | 0
1643 | BIRBHUM | Bolpur Mechanical | Srikantapur piped water supply scheme. , SM/13652 | New | Providing Electro-mechanical accessories and others for SRIKANTAPUR piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | 3387/Bol.MD | 16/10/2023 | 60 | SARKAR ELECTRICAL | 28.28 | 0 | 0 | 20
1644 | BIRBHUM | Birbhum Division | Srikantapur piped water supply scheme. , SM/13652 | New | Sinking of 3 nos. 200mm X 165mm dia x 300 mtr. deep Tube Well by Rig boring method including connecting pipeline and all other allied works under Srikantapur Piped Water Supply Scheme under Birbhum Division, P.H.E. Dte. (2nd Call) | 437/BHM | 10/02/2025 | 60 | M/S R B ENTERPRISE | 20.14 | 0 | 0 | 0
1645 | BIRBHUM | Birbhum Division | Palsa piped water supply scheme. , SM/12906 | New | Material Requisition To Resource Division | 1441/BHM | 25/04/2023 | 0 | Resource Division | 11.75 | 0 | 0 | 0
1646 | BIRBHUM | Bolpur Mechanical | Palsa piped water supply scheme. , SM/12906 | New | Providing Electro-mechanical accessories and others for PALSA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 3298/Bol.MD | 29/09/2023 | 338 | CINZANO | 27.21 | 0 | 0 | 75
1647 | BIRBHUM | Bolpur Mechanical | Palsa piped water supply scheme. , SM/12906 | New | WBSEDCL QUOTATION MONEY FOR PALSA P H NO.II WS SCHEME | BP-2023-24-258 | 06/02/2024 | 0 | WBSEDCL | 3.04 | 0 | 0 | 0
1648 | BIRBHUM | Bolpur Mechanical | Palsa piped water supply scheme. , SM/12906 | New | WBSEDCL QUOTATION FOR PALSA PUMP HOUSE NO I | BP-23-24-257 | 06/02/2024 | 0 | WBSEDCL | 3.06 | 0 | 0 | 0
1649 | BIRBHUM | Birbhum Division | Palsa piped water supply scheme. , SM/12906 | New | Different works related to water supply scheme at Palsa & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1639/BHM | 02/05/2023 | 1214 | GHOSH & BROTHERS DEVCON PRIVATE LIMITED | 290.19 | 0 | 0 | 30
1650 | BIRBHUM | Birbhum Division | BENGA CHATRA PIPED WATER SUPPLY SCHEME , SM/13408 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BENGACHATRA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 156/BSD | 20/04/2022 | 90 | RADIANT | 4.36 | 0 | 0 | 100
1651 | BIRBHUM | Birbhum Division | BENGA CHATRA PIPED WATER SUPPLY SCHEME , SM/13408 | New | Material Requisition To Resource Division | 1523/BHM | 26/04/2023 | 0 | Resource Division | 33.24 | 0 | 0 | 0
1652 | BIRBHUM | Birbhum Division | BENGA CHATRA PIPED WATER SUPPLY SCHEME , SM/13408 | New | Construction of 200 Cum capacity O.H.R. with soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, laying of Rising Main, Distribution System with FHTC and different works related to BENGA CHATRA PIPED WATER SUPPLY SCHEME (TSM/015476) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte. | 2576/BHM | 09/09/2024 | 365 | M/S R B ENTERPRISE | 367.97 | 0 | 0 | 0
1653 | BIRBHUM | Birbhum Division | BENGA CHATRA PIPED WATER SUPPLY SCHEME , SM/13408 | New | Material Requisition To Resource Division | 3258/BHM | 02/12/2024 | 0 | Resource Division | 9.4 | 0 | 0 | 0
1654 | BIRBHUM | Central Drilling | BENGA CHATRA PIPED WATER SUPPLY SCHEME , SM/13408 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1655 | BIRBHUM | Bolpur Mechanical | BENGA CHATRA PIPED WATER SUPPLY SCHEME , SM/13408 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Benga Chatra & Ramkrishnapur Water supply Scheme, Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | 4538/BOL.MD | 20/12/2024 | 120 | MENAKA ENTERPRISE | 73.34 | 0 | 0 | 50
1656 | BIRBHUM | Birbhum Division | Prasadpur Piped Water Supply Scheme , SM/13478 | New | Preparation and submission of DPR for (Prasadpur) Water Supply Scheme under Nalhati-II Development Block. | 232/AE/NSD | 21/04/2022 | 45 | MS SOBHA AND CO | 4.81 | 0 | 0 | 100
1657 | BIRBHUM | Birbhum Division | Prasadpur Piped Water Supply Scheme , SM/13478 | New | Material Requisition To Resource Division | 1509/BHM | 26/04/2023 | 0 | Resource Division | 9.92 | 0 | 0 | 0
1658 | BIRBHUM | Bolpur Mechanical | Prasadpur Piped Water Supply Scheme , SM/13478 | New | Supply and Delivery of Open well Submersible Pumping Machineries and allied accessories for Prasadpur PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | 3783/BOL.MD | 12/09/2024 | 30 | M/S. UTTAM KUMAR CHATTERJEE | 28.98 | 0 | 0 | 100
1659 | BIRBHUM | Birbhum Division | Prasadpur Piped Water Supply Scheme , SM/13478 | New | Different works related to water supply scheme at NAWAPARA & PRASADPUR and its adjoining mouzas water supply scheme within NALHATI-II Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 3257/BHM | 26/07/2023 | 275 | MANASH GHOSH | 866.09 | 0 | 0 | 5
1660 | BIRBHUM | Bolpur Mechanical | Prasadpur Piped Water Supply Scheme , SM/13478 | New | Providing Electro-mechanical accessories and others for Prasadpur PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | 2138/Bol.MD | 25/08/2023 | 615 | QUAZI NOZRUL ISLAM | 44.39 | 0 | 0 | 40
1661 | BIRBHUM | Birbhum Division | Prasadpur Piped Water Supply Scheme , SM/13478 | New | Extension of pipeline (DI & HDPE) with FHTC, Restoration of Roads including Augur boring along with supply of sluice valve with construction of valve chamber for Prasadpur piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. | 2144/BHM | 19/08/2025 | 90 | APORUPA CONSTRUCTION | 46.38 | 0 | 0 | 0
1662 | BIRBHUM | Birbhum Division | Shankarpur Piped Water Scheme , SM/14082 | New | Material Requisition To Resource Division | 1586/BHM | 26/04/2023 | 0 | Resource Division | 111.93 | 0 | 0 | 0
1663 | BIRBHUM | Bolpur Mechanical | Shankarpur Piped Water Scheme , SM/14082 | New | Providing Electro-mechanical accessories and others for Shankarpur & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | 3551/Bol.MD | 01/12/2023 | 90 | QUAZI NOZRUL ISLAM | 85.3 | 0 | 0 | 20
1664 | BIRBHUM | Bolpur Mechanical | Shankarpur Piped Water Scheme , SM/14082 | New | Modification works on Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Shankarpur PWSS under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | 536/BOL.MD | 14/03/2024 | 60 | DEY ENTERPRISE | 5.77 | 0 | 0 | 0
1665 | BIRBHUM | Bolpur Mechanical | Shankarpur Piped Water Scheme , SM/14082 | New | Modification works on Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Shankarpur PWSS under Rajnagar Block in the Dist of Birbhum under Bolpur Mechanical Division,PHEDte | 535/BOL.MD | 14/03/2024 | 60 | TULIP ENTERPRISE | 5.41 | 0 | 0 | 30
1666 | BIRBHUM | Bolpur Mechanical | Shankarpur Piped Water Scheme , SM/14082 | New | WBSEDCL QUOTATION FOR SHANKARPUR WATER SUPPLY SCHEME | BP-23-24-259 | 06/02/2024 | 0 | WBSEDCL | 21.4 | 0 | 0 | 0
1667 | BIRBHUM | Birbhum Division | Shankarpur Piped Water Scheme , SM/14082 | New | Different works related to water supply scheme at SHANKARPUR & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte.150 | 1094/BHM | 06/04/2023 | 909 | SYED GOLAM ZILANI | 353.43 | 0 | 0 | 30
1668 | BIRBHUM | Bolpur Mechanical | Shankarpur Piped Water Scheme , SM/14082 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Sankarpur PWSS under Rajnagar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | 534/BOL.MD | 14/03/2024 | 449 | SINHA ELECTRICALS | 7.8 | 0 | 0 | 100
1669 | BIRBHUM | Birbhum Division | Shankarpur Piped Water Scheme , SM/14082 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
1670 | BIRBHUM | Birbhum Division | Bergram Piped Water Supply Scheme. , SM/13482 | New | Material Requisition To Resource Division | 1356/BHM | 24/04/2023 | 0 | Resource Division | 16.74 | 0 | 0 | 0
1671 | BIRBHUM | Birbhum Division | Bergram Piped Water Supply Scheme. , SM/13482 | New | Material Requisition To Resource Division | 1538/BHM | 26/04/2023 | 0 | Resource Division | 16.74 | 0 | 0 | 0
1672 | BIRBHUM | Central Drilling | Bergram Piped Water Supply Scheme. , SM/13482 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1673 | BIRBHUM | Birbhum Division | Bergram Piped Water Supply Scheme. , SM/13482 | New | Different works related to water supply scheme at ALBANDHA, BERGRAM & BIDYADHARPUR Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (2nd Call) | 4146/BHM | 19/10/2023 | 805 | AMAL DUTTA ROY | 1648.21 | 0 | 0 | 12
1674 | BIRBHUM | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. , SM/12831 | New | Material Requisition To Resource Division | 1430/BHM | 25/04/2023 | 0 | Resource Division | 14.24 | 0 | 0 | 0
1675 | BIRBHUM | Bolpur Mechanical | KANIOR PIPED WATER SUPPLY SCHEME. , SM/12831 | New | Providing Electro-mechanical accessories and others for Kanior PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | 3542/BOL.MD | 30/11/2023 | 60 | GOENKA ENTERPRISE | 30.69 | 0 | 0 | 60
1676 | BIRBHUM | Bolpur Mechanical | KANIOR PIPED WATER SUPPLY SCHEME. , SM/12831 | New | Supply and Delivery of Sub-Mersible Pumping Machineries inconection with Providing Electro-mechanical accessories and others for Kanior PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | 685./AE-III | 08/04/2024 | 14 | GOENKA ENTERPRISE | 1.58 | 0 | 0 | 100
1677 | BIRBHUM | Bolpur Mechanical | KANIOR PIPED WATER SUPPLY SCHEME. , SM/12831 | New | WBSEDCL QUOTATION FOR KANIOR | BP-23-24-208 | 04/01/2024 | 0 | WBSEDCL | 0.44 | 0 | 0 | 0
1678 | BIRBHUM | Bolpur Mechanical | KANIOR PIPED WATER SUPPLY SCHEME. , SM/12831 | New | WBSEDCL QUOTATION FOR KANIOR | BP-23-24-209 | 04/01/2024 | 0 | WBSEDCL | 3.26 | 0 | 0 | 0
1679 | BIRBHUM | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. , SM/12831 | New | Different works related to water supply scheme at KANIOR, KOGRAM & KUSHIPUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1059/BHM | 31/03/2023 | 915 | SK ALIM | 1229.19 | 0 | 0 | 25
1680 | BIRBHUM | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. , SM/12831 | New | Hiring of SWIFT DZIRE (diesel) registered luxury car for the office of the Assistant Engineer, Nalhati Sub-Division P.H.E. Dte. for 24 hours service including Driver and the cost of fuel & lubricants as per terms & condition with effect from 01.10.2024 to 31.12.2024.Hiring charges of Ambassador Car (Diesel) Fuel :- Diesel : 1 liter for every 12 KM. Lubricants : Mobil: 1 liter for every 500 KM. | 312/NSD | 30/09/2024 | 92 | JOY CHAND MAL | 0.43 | 0 | 0 | 0
1681 | BIRBHUM | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. , SM/12831 | New | Hiring of Swift Dizer (Diesel) or equivalent luxury car for office of the Assistant Engineer, Nalhati Sub-Division under Birbhum Division, PHE Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & with effect from 01.02.2025 to 31.07.2025 | 40/NSD | 31/01/2025 | 181 | JOY CHAND MAL | 0.85 | 0 | 0 | 0
1682 | BIRBHUM | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. , SM/12831 | New | Hiring of SWIFT DZIRE (diesel) registered luxury car for the office of the Assistant Engineer, Nalhati Sub-Division P.H.E. Dte. for 24 hours service including Driver and the cost of fuel & lubricants as per terms & condition with effect from 01.01.2025 to 31.01.2025.Hiring charges of Ambassador Car (Diesel) Fuel :- Diesel : 1 liter for every 12 KM. Lubricants : Mobil: 1 liter for every 500 KM. | 429/NSD | 31/12/2024 | 31 | JOY CHAND MAL | 0.15 | 0 | 0 | 0
1683 | BIRBHUM | Birbhum Division | KANIOR PIPED WATER SUPPLY SCHEME. , SM/12831 | New | Jack pushing including Augur boring for extension of pipeline (DI & HDPE ) including supply of sluice valve with construction of valve chamber and restoration of Roads, pucca drain for KANIOR piped Water Supply Scheme (Nalhati-I Block) under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | 3536/BHM | 23/12/2024 | 58 | SK ALIM | 73.24 | 0 | 0 | 95
1684 | BIRBHUM | Bolpur Mechanical | Patalpur Piped Water Supply Scheme , SM/14955 | New | Providing Electro-mechanical accessories and others for Patalpur & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | 3552/Bol.MD | 01/12/2023 | 90 | A. G. ENTERPRISE | 55.59 | 0 | 0 | 0
1685 | BIRBHUM | Bolpur Mechanical | Patalpur Piped Water Supply Scheme , SM/14955 | New | New service connection at patalpur water supply scheme under Bolpur Mechanical Division, P.H.E Dte. | BP-2024-25-274 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.68 | 0 | 0 | 0
1686 | BIRBHUM | Birbhum Division | Patalpur Piped Water Supply Scheme , SM/14955 | New | Different works related to water supply scheme at PATALPUR & its adjoining mouzas water supply scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte | 3949/BHM | 03/10/2023 | 270 | RAJKUMAR DAS | 89.99 | 0 | 0 | 30
1687 | BIRBHUM | Birbhum Division | Patalpur Piped Water Supply Scheme , SM/14955 | New | Sinking of 2 nos. (Two) 200 mm dia x 30 mtr deep Tubewell for Patalpur & its adjoining mouzas water supply scheme within Rajnagar Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 4339/BHM | 23/11/2023 | 30 | RAJKUMAR DAS | 2.74 | 0 | 0 | 100
1688 | BIRBHUM | Birbhum Division | Bhadulia Piped Water Supply Scheme , SM/14674 | New | Preparation & Submission of DPR for Bhadulia & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 99/BSSD | 14/06/2022 | 45 | RADIANT | 2.71 | 0 | 0 | 100
1689 | BIRBHUM | Birbhum Division | Bhadulia Piped Water Supply Scheme , SM/14674 | New | Material Requisition To Resource Division | 438/BHM | 01/02/2024 | 0 | Resource Division | 131.6 | 0 | 0 | 0
1690 | BIRBHUM | Birbhum Division | Bhadulia Piped Water Supply Scheme , SM/14674 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
1691 | BIRBHUM | Birbhum Division | Bhadulia Piped Water Supply Scheme , SM/14674 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
1692 | BIRBHUM | Birbhum Division | SAJNOR PIPED WATER SUPPLY SCHEME , SM/14678 | New | Material Requisition To Resource Division | 1456/BHM | 25/04/2023 | 0 | Resource Division | 16.14 | 0 | 0 | 0
1693 | BIRBHUM | Birbhum Division | SAJNOR PIPED WATER SUPPLY SCHEME , SM/14678 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for SAJNOR Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | 279/BSD | 21/07/2022 | 90 | RADIANT | 4.94 | 0 | 0 | 100
1694 | BIRBHUM | Birbhum Division | SAJNOR PIPED WATER SUPPLY SCHEME , SM/14678 | New | Material Requisition To Resource Division | 2394/BHM | 27/08/2024 | 0 | Resource Division | 12.08 | 0 | 0 | 0
1695 | BIRBHUM | Central Drilling | SAJNOR PIPED WATER SUPPLY SCHEME , SM/14678 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1696 | BIRBHUM | Birbhum Division | SAJNOR PIPED WATER SUPPLY SCHEME , SM/14678 | New | Construction of 250 & 150 CuM. Capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements Laying of Rising Main, Distribution System with FHTC including different works related to SANTOSHPUR / NAWADA PALANDI /PAPURI / SAJNOR / RAYEN PIPED WATER SUPPLY SCHEME (5 Nos Scheme) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division PHE DTE. | 1951/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2322.64 | 0 | 0 | 5
1697 | BIRBHUM | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division , SM/14088 | New | Material Requisition To Resource Division | 1444/BHM | 25/04/2023 | 0 | Resource Division | 36.79 | 0 | 0 | 0
1698 | BIRBHUM | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division , SM/14088 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Prayagpur PWSS under Mayureswar - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | 529/BOL.MD | 14/03/2024 | 60 | SWAPAN ENTERPRISE | 7.62 | 0 | 0 | 0
1699 | BIRBHUM | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division , SM/14088 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Prayagpur Piped Water Supply Scheme, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte. | 3756/Bol.MD | 12/09/2024 | 30 | M/S P.P ELECTRICALS | 25.25 | 0 | 0 | 0
1700 | BIRBHUM | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division , SM/14088 | New | Continuation Work Order for Preparation & Submission of DPR for (PRAYAGPUR) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | 333/RSD | 08/09/2022 | 45 | ENVIROTECH SOLUTIONS | 3.22 | 0 | 0 | 100
1701 | BIRBHUM | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division , SM/14088 | New | Continuation Work Order for Preparation & Submission of DPR for (PRAYAGPUR) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | 437/RSD | 25/11/2022 | 45 | ENVIROTECH SOLUTIONS | 2.5 | 0 | 0 | 100
1702 | BIRBHUM | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division , SM/14088 | New | Material Requisition To Resource Division | 231/BHM | 24/01/2024 | 0 | Resource Division | 5.61 | 0 | 0 | 0
1703 | BIRBHUM | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division , SM/14088 | New | Quotation money for new service connection at Prayagpur PWSS P/H- III under Mayureswar CCC | BP-24-25-183 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.12 | 0 | 0 | 0
1704 | BIRBHUM | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division , SM/14088 | New | Different works related to Water Supply Scheme at PRAYAGPUR & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3596/BHM | 21/08/2023 | 813 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 516.3 | 0 | 0 | 55
1705 | BIRBHUM | Bolpur Mechanical | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division , SM/14088 | New | Providing Electro-mechanical accessories and others for Prayagpur PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | 3278/Bol.MD | 29/09/2023 | 825 | ORIENTAL ENGINEERING CO. | 55.59 | 0 | 0 | 50
1706 | BIRBHUM | Birbhum Division | Prayagpur Piped Water Supply Scheme under Mayureswar-II Block Within Birbhum Division , SM/14088 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
1707 | BIRBHUM | Bolpur Mechanical | Ninga Piped Water Supply Scheme , SM/14089 | New | Providing Electro-mechanical accessories and others for Ninga PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 2230/Bol.MD | 12/09/2023 | 60 | DEY ENTERPRISE | 44.43 | 0 | 0 | 0
1708 | BIRBHUM | Birbhum Division | Ninga Piped Water Supply Scheme , SM/14089 | New | Material Requisition To Resource Division | 1550/BHM | 26/04/2023 | 0 | Resource Division | 58.2 | 0 | 0 | 0
1709 | BIRBHUM | Bolpur Mechanical | Ninga Piped Water Supply Scheme , SM/14089 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Ninga PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 527/BOL.MD | 14/03/2024 | 60 | DIPALI CONSTRUCTION | 7.61 | 0 | 0 | 0
1710 | BIRBHUM | Birbhum Division | Ninga Piped Water Supply Scheme , SM/14089 | New | Continuation Work Order for Preparation & Submission of DPR for (NINGA) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | 289/RSD | 31/08/2022 | 45 | ECO CARE | 2.4 | 0 | 0 | 100
1711 | BIRBHUM | Birbhum Division | Ninga Piped Water Supply Scheme , SM/14089 | New | Continuation Work Order for Preparation & Submission of DPR for (NINGA) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | 373/RSD | 22/09/2022 | 45 | ECO CARE | 2.91 | 0 | 0 | 100
1712 | BIRBHUM | Birbhum Division | Ninga Piped Water Supply Scheme , SM/14089 | New | Material Requisition To Resource Division | 3261/BHM | 02/12/2024 | 0 | Resource Division | 12.4 | 0 | 0 | 0
1713 | BIRBHUM | Birbhum Division | Ninga Piped Water Supply Scheme , SM/14089 | New | Sinking of 250 X 150 mm Dia (through) and 180 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Ninga & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUMDivision, PHE Dte | 3116/BHM | 13/11/2024 | 365 | M/S DATTA ENTERPRISE | 375.28 | 0 | 0 | 20
1714 | BIRBHUM | Bolpur Mechanical | Bautia piped water supply scheme , SM/14536 | New | Supply & Installation of High lift pumping machineries and other allied works for Bautia piped water supply scheme within Nalhati-I block, under Bolpur Mechanical Division PHE Dte. | 3558/BOL.MD | 04/12/2023 | 90 | R. N. S. TRADING | 91.5 | 0 | 0 | 0
1715 | BIRBHUM | Birbhum Division | Bautia piped water supply scheme , SM/14536 | New | Material Requisition To Resource Division | 1505/BHM | 25/04/2023 | 0 | Resource Division | 433.77 | 0 | 0 | 0
1716 | BIRBHUM | Bolpur Mechanical | Bautia piped water supply scheme , SM/14536 | New | Supply & Installation of Low lift pumping machineries and other allied works for Bautia piped water supply scheme within Nalhati-I block, under Bolpur Mechanical Division PHE Dte | 3559/BOL.MD | 04/12/2023 | 484 | M/S. UTTAM KUMAR CHATTERJEE | 24.37 | 0 | 0 | 40
1717 | BIRBHUM | Birbhum Division | Bautia piped water supply scheme , SM/14536 | New | Material Requisition To Resource Division | 3262/BHM | 02/12/2024 | 0 | Resource Division | 21.17 | 0 | 0 | 0
1718 | BIRBHUM | Birbhum Division | Bautia piped water supply scheme , SM/14536 | New | Sinking of 200 X 200 mm Dia (through) and 125 m deep tubewell, 02 nos, 5.90 m X 4.10 m Chlorine room with sanitary arrangements, 300 CuM OHR & 150 cum OHR, 200 Cum CWR, Boundary wall with Gate, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Bautia & its adjoining mouzas water supply scheme within Nalhati-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 2772/BHM | 30/09/2024 | 365 | M/S GHOSH AND CO. | 887.39 | 0 | 0 | 2
1719 | BIRBHUM | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME , SM/15253 | New | Material Requisition To Resource Division | 1528/BHM | 26/04/2023 | 0 | Resource Division | 30.37 | 0 | 0 | 0
1720 | BIRBHUM | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME , SM/15253 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for GOPINATHPUR Piped Water Supply Scheme under Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 137/BSD | 07/04/2022 | 90 | M/S R DUTTA & CO. | 3.93 | 0 | 0 | 100
1721 | BIRBHUM | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME , SM/15253 | New | Material Requisition To Resource Division | 2445/BHM | 30/08/2024 | 0 | Resource Division | 10.06 | 0 | 0 | 0
1722 | BIRBHUM | Central Drilling | GOPINATHPUR PIPED WATER SUPPLY SCHEME , SM/15253 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1723 | BIRBHUM | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME , SM/15253 | New | Construction 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements.Laying of Rising Main,Distribution system,including FHTC and different works related to water supply scheme at GOPINATHPUR PIPED WATER SUPPLY SCHEME (TSM/015544) within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 2165/BHM | 05/08/2024 | 365 | KINGS & CO. | 396.77 | 0 | 0 | 10
1724 | BIRBHUM | Birbhum Division | GOPINATHPUR PIPED WATER SUPPLY SCHEME , SM/15253 | New | Construction of 250 cum capacity 20 Mtr. staging height RCC Over Head Reservoir (Superstructure part as per Departmental Drawing), pipe connection and cost of pipes & specials with necessary soil investigation with foundation design as per soil test report for GOPINATHPUR PIPED WATER SUPPLY SCHEMEwithin ILLAMBAZAR Block under BIRBHUM Division, PHE Dte. | 2350/BHM | 10/09/2025 | 365 | SYED KHORSED ALAM | 85.64 | 0 | 0 | 0
1725 | BIRBHUM | Birbhum Division | MADDA PIPED WATER SUPPLY SCHEME , SM/15255 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for MADDA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 122/BSD | 31/03/2022 | 90 | RADIANT | 4 | 0 | 0 | 100
1726 | BIRBHUM | Bolpur Mechanical | MADDA PIPED WATER SUPPLY SCHEME , SM/15255 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Madda WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | 4525/BOL.MD | 20/12/2024 | 120 | SATYAJIT GHOSH | 75.08 | 0 | 0 | 0
1727 | BIRBHUM | Birbhum Division | MADDA PIPED WATER SUPPLY SCHEME , SM/15255 | New | "Construction of 200CuM. capacity O.H.R. with Soil Investigation,5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements Laying of Rising Main ,Distribution Systemwith FHTC including different works related to MADDA PIPED WATER SUPPLY SCHEME (TSM/016100) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte." | 2106/BHM | 29/07/2024 | 365 | M/S NIBHAS SINHA | 434.39 | 0 | 0 | 0
1728 | BIRBHUM | Birbhum Division | MADDA PIPED WATER SUPPLY SCHEME , SM/15255 | New | Material Requisition To Resource Division | 2391/BHM | 27/08/2024 | 0 | Resource Division | 8.56 | 0 | 0 | 0
1729 | BIRBHUM | Central Drilling | MADDA PIPED WATER SUPPLY SCHEME , SM/15255 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1730 | BIRBHUM | Birbhum Division | Ahmadpur Piped Water Supply Scheme , SM/14889 | New | Material Requisition To Resource Division | 1591/BHM | 26/04/2023 | 0 | Resource Division | 182.11 | 0 | 0 | 0
1731 | BIRBHUM | Bolpur Mechanical | Ahmadpur Piped Water Supply Scheme , SM/14889 | New | Supply and delivery of outdoor type pump controller unit for Ahamedpur and others PWSS under Rajnagar block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 406/Bol.MD | 07/03/2024 | 45 | M/S. UTTAM KUMAR CHATTERJEE | 20.06 | 0 | 0 | 100
1732 | BIRBHUM | Bolpur Mechanical | Ahmadpur Piped Water Supply Scheme , SM/14889 | New | WBSEDCL QUOTATION FOR AHMADPUR WS SCHEME | BP-23-24-250 | 06/02/2024 | 0 | WBSEDCL | 0.26 | 0 | 0 | 0
1733 | BIRBHUM | Bolpur Mechanical | Ahmadpur Piped Water Supply Scheme , SM/14889 | New | WBSEDCL QUOTATION FOR AHAMADPUR WATER SUPPLY SCHEME | BP-23-24-261 | 06/02/2024 | 0 | WBSEDCL | 15.58 | 0 | 0 | 0
1734 | BIRBHUM | Birbhum Division | Ahmadpur Piped Water Supply Scheme , SM/14889 | New | Different works related to water supply scheme at AHAMADPUR & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte. 150 | 1877/BHM | 31/05/2023 | 840 | B.B.C ENTERPRISE | 411.79 | 0 | 0 | 75
1735 | BIRBHUM | Bolpur Mechanical | Ahmadpur Piped Water Supply Scheme , SM/14889 | New | Providing Electro-mechanical accessories and others for Ahamadpur & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | 2157/Bol.MD | 29/08/2023 | 828 | SINHA ELECTRICALS | 92.12 | 0 | 0 | 70
1736 | BIRBHUM | Birbhum Division | Ahmadpur Piped Water Supply Scheme , SM/14889 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
1737 | BIRBHUM | Bolpur Mechanical | Siur Piped Water Supply Scheme. , SM/14537 | New | Providing electro-mechanical accessories and others for Siur & Adjoining Moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | 306/Bol.MD | 23/03/2023 | 366 | M. S. ENTERPRISE | 90.15 | 0 | 0 | 0
1738 | BIRBHUM | Birbhum Division | Siur Piped Water Supply Scheme. , SM/14537 | New | Material Requisition To Resource Division | 1384/BHM | 24/04/2023 | 0 | Resource Division | 193.96 | 0 | 0 | 0
1739 | BIRBHUM | Birbhum Division | Siur Piped Water Supply Scheme. , SM/14537 | New | Material Requisition To Resource Division | 3280/BHM | 27/07/2023 | 0 | Resource Division | 2.56 | 0 | 0 | 0
1740 | BIRBHUM | Bolpur Mechanical | Siur Piped Water Supply Scheme. , SM/14537 | New | Providing electro mechanical accessories and others for Siur and Adjoining Mouzas Water Supply Scheme under Bolpur Mechanical Division, PHE Dte | 318/BOL.M.D | 27/03/2023 | 366 | M. S. ENTERPRISE | 90.15 | 31.1 | 34.5 | 60
1741 | BIRBHUM | Birbhum Division | Siur Piped Water Supply Scheme. , SM/14537 | New | Different works for SIUR & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1440/BHM | 25/04/2023 | 1131 | MUKHERJEE CONSTRUCTION | 777.14 | 0 | 0 | 15
1742 | BIRBHUM | Bolpur Mechanical | HANSAN PIPED WATER SUPPLY SCHEME , SM/14900 | New | Providing Electro-mechanical accessories and others for Hansan PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 2229/Bol.MD | 12/09/2023 | 60 | P. K. ENGINEERING | 44.33 | 0 | 0 | 0
1743 | BIRBHUM | Birbhum Division | HANSAN PIPED WATER SUPPLY SCHEME , SM/14900 | New | Material Requisition To Resource Division | 1520/BHM | 26/04/2023 | 0 | Resource Division | 25.75 | 0 | 0 | 0
1744 | BIRBHUM | Bolpur Mechanical | HANSAN PIPED WATER SUPPLY SCHEME , SM/14900 | New | Supply & delivery of Main Swich, Change over switch,Busbar for Hasan water supply scheme (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. " | 1454./AE-III | 09/09/2024 | 7 | SATYAJIT GHOSH | 0 | 0 | 0 | 0
1745 | BIRBHUM | Bolpur Mechanical | HANSAN PIPED WATER SUPPLY SCHEME , SM/14900 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Hansan PWSS under Rampurhat - II Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | 522/BOL.MD | 14/03/2024 | 60 | KAMAKHYA ENTERPRISE | 7.62 | 0 | 0 | 0
1746 | BIRBHUM | Birbhum Division | HANSAN PIPED WATER SUPPLY SCHEME , SM/14900 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR , Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at HANSAN & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 2179/BHM | 06/08/2024 | 365 | RADIANT | 490.17 | 0 | 0 | 30
1747 | BIRBHUM | Birbhum Division | HANSAN PIPED WATER SUPPLY SCHEME , SM/14900 | New | Continuation Work Order for Preparation & Submission of DPR for (HANSAN) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | 326/RSD | 08/09/2022 | 45 | ECO CARE | 3.05 | 0 | 0 | 100
1748 | BIRBHUM | Birbhum Division | HANSAN PIPED WATER SUPPLY SCHEME , SM/14900 | New | Continuation Work Order for Preparation & Submission of DPR for (HANSAN) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | 426/RSD | 04/11/2022 | 45 | ECO CARE | 2.91 | 0 | 0 | 100
1749 | BIRBHUM | Bolpur Mechanical | HANSAN PIPED WATER SUPPLY SCHEME , SM/14900 | New | Supply & delivery of Main Swich, Change over switch,Busbar for Hasan water supply scheme (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. " | 1454./AE-III | 09/09/2024 | 7 | SATYAJIT GHOSH | 2.83 | 0 | 0 | 100
1750 | BIRBHUM | Birbhum Division | HANSAN PIPED WATER SUPPLY SCHEME , SM/14900 | New | Material Requisition To Resource Division | 2485/BHM | 03/09/2024 | 0 | Resource Division | 11.9 | 0 | 0 | 0
1751 | BIRBHUM | Bolpur Mechanical | HANSAN PIPED WATER SUPPLY SCHEME , SM/14900 | New | Supply & delivery of Sub-Mersible Pump Controllers for Hasan water supply scheme (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | 1295./AE-III | 27/08/2024 | 65 | SWAPAN BANERJEE | 2.84 | 0 | 0 | 100
1752 | BIRBHUM | Birbhum Division | FARIDPUR PIPED WATER SUPPLY SCHEME , SM/14971 | New | Material Requisition To Resource Division | 1590/BHM | 26/04/2023 | 0 | Resource Division | 65.61 | 0 | 0 | 0
1753 | BIRBHUM | Birbhum Division | FARIDPUR PIPED WATER SUPPLY SCHEME , SM/14971 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for FARIDPUR Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | 146/BSD | 12/04/2022 | 180 | APEX ENGINEERING | 4.22 | 0 | 0 | 100
1754 | BIRBHUM | Birbhum Division | FARIDPUR PIPED WATER SUPPLY SCHEME , SM/14971 | New | Material Requisition To Resource Division | 2397/BHM | 27/08/2024 | 0 | Resource Division | 8.9 | 0 | 0 | 0
1755 | BIRBHUM | Central Drilling | FARIDPUR PIPED WATER SUPPLY SCHEME , SM/14971 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1756 | BIRBHUM | Birbhum Division | FARIDPUR PIPED WATER SUPPLY SCHEME , SM/14971 | New | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1948/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0 | 0
1757 | BIRBHUM | Bolpur Mechanical | FARIDPUR PIPED WATER SUPPLY SCHEME , SM/14971 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Faridpur PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | 327/BOL.MD | 19/02/2025 | 120 | OSMAN SEKH | 76.33 | 0 | 0 | 0
1758 | BIRBHUM | Birbhum Division | RAGHABPUR PIPED WATER SUPPLY SCHEME , SM/14747 | New | Different works related to water supply scheme at RAGHABPUR PIPED WATER SUPPLY SCHEME (TSM/016570) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 899/BHM | 22/03/2023 | 275 | M/S.KHAN CHOWDHURY BROTHERS AND CO. | 210.82 | 0 | 0 | 0
1759 | BIRBHUM | Birbhum Division | RAGHABPUR PIPED WATER SUPPLY SCHEME , SM/14747 | New | Material Requisition To Resource Division | 1628/BHM | 28/04/2023 | 0 | Resource Division | 20.44 | 0 | 0 | 0
1760 | BIRBHUM | Birbhum Division | RAGHABPUR PIPED WATER SUPPLY SCHEME , SM/14747 | New | Material Requisition To Resource Division | 1594/BHM | 26/04/2023 | 0 | Resource Division | 20.44 | 0 | 0 | 0
1761 | BIRBHUM | Birbhum Division | RAGHABPUR PIPED WATER SUPPLY SCHEME , SM/14747 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for RAGHABPUR Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | 123/BSD | 31/03/2022 | 180 | APEX ENGINEERING | 2.11 | 0 | 0 | 100
1762 | BIRBHUM | Central Drilling | RAGHABPUR PIPED WATER SUPPLY SCHEME , SM/14747 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1763 | BIRBHUM | Birbhum Division | Penchalia Piped Water Supply Scheme , SM/16282 | New | Preparation & Submission of DPR for Penchalia & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 126/BSSD | 12/07/2022 | 45 | RADIANT | 2.43 | 0 | 0 | 100
1764 | BIRBHUM | Birbhum Division | Penchalia Piped Water Supply Scheme , SM/16282 | New | Material Requisition To Resource Division | 429/BHM | 01/02/2024 | 0 | Resource Division | 87.68 | 0 | 0 | 0
1765 | BIRBHUM | Birbhum Division | Penchalia Piped Water Supply Scheme , SM/16282 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
1766 | BIRBHUM | Birbhum Division | Penchalia Piped Water Supply Scheme , SM/16282 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
1767 | BIRBHUM | Birbhum Division | Sagarbhanga Piped Water Supply Scheme (Khoyrasole Block) , SM/16270 | New | Preparation & Submission of DPR for Sagarbanga & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 131/BSSD | 14/07/2022 | 45 | RADIANT | 1.23 | 0 | 0 | 100
1768 | BIRBHUM | Birbhum Division | Sagarbhanga Piped Water Supply Scheme (Khoyrasole Block) , SM/16270 | New | Material Requisition To Resource Division | 422/BHM | 01/02/2024 | 0 | Resource Division | 15.47 | 0 | 0 | 0
1769 | BIRBHUM | Birbhum Division | Sagarbhanga Piped Water Supply Scheme (Khoyrasole Block) , SM/16270 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
1770 | BIRBHUM | Birbhum Division | Sagarbhanga Piped Water Supply Scheme (Khoyrasole Block) , SM/16270 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
1771 | BIRBHUM | Birbhum Division | Chhora Piped Water Supply Scheme. , SM/16761 | New | Material Requisition To Resource Division | 1593/BHM | 26/04/2023 | 0 | Resource Division | 13.6 | 0 | 0 | 0
1772 | BIRBHUM | Birbhum Division | Chhora Piped Water Supply Scheme. , SM/16761 | New | Material Requisition To Resource Division | 2451/BHM | 30/08/2024 | 0 | Resource Division | 11.19 | 0 | 0 | 0
1773 | BIRBHUM | Bolpur Mechanical | Chhora Piped Water Supply Scheme. , SM/16761 | New | Providing Electro-mechanical accessories and others for Chhora & Adjoining PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 3530/Bol.MD | 29/11/2023 | 623 | S.K.ELECTRICALS | 27.63 | 0 | 0 | 70
1774 | BIRBHUM | Birbhum Division | Chhora Piped Water Supply Scheme. , SM/16761 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 200 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at CHHORA & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | 2116/BHM | 29/07/2024 | 611 | ASIM KUMAR MONDAL | 400.06 | 0 | 0 | 30
1775 | BIRBHUM | Birbhum Division | Aliat Piped Water Supply Scheme , SM/14083 | New | Preparation & Submission of DPR for Aliat & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 142/BSSD | 21/07/2022 | 45 | RADIANT | 2.37 | 0 | 0 | 100
1776 | BIRBHUM | Birbhum Division | Aliat Piped Water Supply Scheme , SM/14083 | New | Material Requisition To Resource Division | 440/BHM | 01/02/2024 | 0 | Resource Division | 109.46 | 0 | 0 | 0
1777 | BIRBHUM | Birbhum Division | Aliat Piped Water Supply Scheme , SM/14083 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
1778 | BIRBHUM | Birbhum Division | Aliat Piped Water Supply Scheme , SM/14083 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
1779 | BIRBHUM | Bolpur Mechanical | Kashtagara Piped Water Supply Scheme. , SM/18733 | New | Providing Electro-mechanical accessories and others for Kashtagara Zone - II PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 3523/Bol.MD | 29/11/2023 | 60 | M/S. DILIP MITRA | 27.61 | 0 | 0 | 0
1780 | BIRBHUM | Bolpur Mechanical | Kashtagara Piped Water Supply Scheme. , SM/18733 | New | Providing Electro-mechanical accessories and others for Kashtagara Zone - I PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 3524/Bol.MD | 29/11/2023 | 60 | WEST BENGAL ENGINEERING CO. | 27.68 | 0 | 0 | 0
1781 | BIRBHUM | Birbhum Division | Kashtagara Piped Water Supply Scheme. , SM/18733 | New | Material Requisition To Resource Division | 1589/BHM | 26/04/2023 | 0 | Resource Division | 13.11 | 0 | 0 | 0
1782 | BIRBHUM | Birbhum Division | Kashtagara Piped Water Supply Scheme. , SM/18733 | New | Sinking of 200 mm dia all through and 150 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements,, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration for Zone-I and II and Providing functional household tap connection related to water supply scheme at Kashtagara and Adjoining Moujas Piped Water Supply Scheme within RAMPURHAT-I Block underBIRBHUM Division, PHE Dte. | 3141/BHM | 19/11/2024 | 365 | M/S DIPAK ENTERPRISE | 895.59 | 0 | 0 | 0
1783 | BIRBHUM | Bolpur Mechanical | Kashtagara Piped Water Supply Scheme. , SM/18733 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Kastagara PWSS under Rampurhat - I Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 524/BOL.MD | 14/03/2024 | 60 | S.G.TECHNICAL SERVICES | 7.61 | 0 | 0 | 40
1784 | BIRBHUM | Birbhum Division | Kashtagara Piped Water Supply Scheme. , SM/18733 | New | Material Requisition To Resource Division | 3263/BHM | 02/12/2024 | 0 | Resource Division | 26.95 | 0 | 0 | 0
1785 | BIRBHUM | Birbhum Division | Kusumba Piped Water Supply Scheme. , SM/18362 | New | Material Requisition To Resource Division | 1466/BHM | 25/04/2023 | 0 | Resource Division | 13.68 | 0 | 0 | 0
1786 | BIRBHUM | Bolpur Mechanical | Kusumba Piped Water Supply Scheme. , SM/18362 | New | Providing Electro-mechanical accessories and others for Kusumba Zone - I PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 3522/Bol.MD | 29/11/2023 | 60 | PRADIP KUMAR DHABAL | 27.77 | 0 | 0 | 30
1787 | BIRBHUM | Birbhum Division | Kusumba Piped Water Supply Scheme. , SM/18362 | New | Material Requisition To Resource Division | 2481/BHM | 03/09/2024 | 0 | Resource Division | 24.98 | 0 | 0 | 0
1788 | BIRBHUM | Bolpur Mechanical | Kusumba Piped Water Supply Scheme. , SM/18362 | New | Providing Electro-mechanical accessories and others for Kusumba Zone - II PWSS at Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 2101/Bol.MD | 22/08/2023 | 598 | MENAKA ENTERPRISE | 28.5 | 0 | 0 | 41
1789 | BIRBHUM | Birbhum Division | Kusumba Piped Water Supply Scheme. , SM/18362 | New | Construction of 200 CuM OHR (ZONE-I) & 350 CuM OHR (ZONE-II) with Soil Investigation,5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, Rising main, Laying distribution( Z-I & II), Boundary wall,Land development,road restoration and Providing functional household tap connection and different works related to KUSUMBA & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 2225/BHM | 12/08/2024 | 729 | SUNIL RABI DAS | 800.42 | 0 | 0 | 20
1790 | BIRBHUM | Birbhum Division | Augmentation of Margram piped water supply scheme. , SM/18372 | Augmentation | Continuation Work Order For Supply and delivery of Sluice Valve for Augmentation of Margram W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. | 1632/BHM | 28/04/2023 | 30 | MAKALI ENGINEERING CORPORATION | 9.57 | 0 | 0 | 100
1791 | BIRBHUM | Birbhum Division | Augmentation of Margram piped water supply scheme. , SM/18372 | Augmentation | Renovation of Existing Switch Room (Old head work site) size 5.40 mtr. X 3.65 mtr with Sanitary and water supply arrangement at Margram Piped Water Supply Scheme under Rampurhat Sub-Division, P.H.E. Dte. | 201/RSD | 28/07/2023 | 15 | TAPAN ENTERPRISE | 0.97 | 0 | 0 | 100
1792 | BIRBHUM | Birbhum Division | Augmentation of Margram piped water supply scheme. , SM/18372 | Augmentation | Restoration works of concrete Road along with culverts (4nos) for Augmentation MARGRAM Water Supply Scheme under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 3516/BHM | 10/08/2023 | 60 | PULAK KUMAR PAL | 16.34 | 0 | 0 | 100
1793 | BIRBHUM | Bolpur Mechanical | Augmentation of Margram piped water supply scheme. , SM/18372 | Augmentation | Providing and Installation of Starter Feeder Panel at existing Pump House Beside OHR and allied works at Margram ( Pump House No - IV ) Piped Water Supply Scheme, Block-Rampurhat-II [within Augmentation of Margram] under Bolpur Mechanical Division. PHE Dte | 2133/Bol.MD | 25/08/2023 | 60 | GOENKA ENTERPRISE | 6.55 | 0 | 0 | 100
1794 | BIRBHUM | Bolpur Mechanical | Augmentation of Margram piped water supply scheme. , SM/18372 | Augmentation | Supply & delivery of Sluice Valve & Non-Return Valve for Augmentation of Margram water supply scheme (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | 1299./AE-III | 27/08/2024 | 7 | SUNIL RABIDAS | 2.87 | 0 | 0 | 0
1795 | BIRBHUM | Bolpur Mechanical | Augmentation of Margram piped water supply scheme. , SM/18372 | Augmentation | Supply & delivery of Electrical accessories ie Main switch change over switch etc for Augmentation of Margram water supply scheme (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | 1456./AE-III | 09/09/2024 | 7 | BIRBHUM ELECTRIC WORKS | 2.88 | 0 | 0 | 100
1796 | BIRBHUM | Birbhum Division | Augmentation of Margram piped water supply scheme. , SM/18372 | Augmentation | Laying of Rising main with DI pipe line for MARGRAM water supply scheme under Rampurhat Sub-Division under Birbhum Division, PHE Dte. | 99/RSD | 07/03/2022 | 30 | TAPAS KUMAR SARKHEL | 2.41 | 0 | 0 | 100
1797 | BIRBHUM | Bolpur Mechanical | Augmentation of Margram piped water supply scheme. , SM/18372 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Wells and allieds works at Augmentation of Margram ( Pump House No - I, II & III ) Piped Water Supply Scheme, Block-Rampurhat-II under Bolpur Mechanical Division, PHE Dte. | 2132/Bol.MD | 25/08/2023 | 707 | SUNIL RABIDAS | 90.64 | 0 | 0 | 50
1798 | BIRBHUM | Birbhum Division | Augmentation of Margram piped water supply scheme. , SM/18372 | Augmentation | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, Boundary wall, Land development, Laying distribution, road restoration and Providing functional household tap connection related to AUGMENTATION OF MARGRAM & Its adjoining Mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | 2006/BHM | 12/07/2024 | 546 | PROJECT INDIA , 38/A, KHELAT BABU LANE, KOLKATA - 700037. | 692.88 | 0 | 0 | 35
1799 | BIRBHUM | Birbhum Division | Augmentation of Margram piped water supply scheme. , SM/18372 | Augmentation | Balance Laying of rising main along with road restoration other allied works for AUGMENTATION of MARGRAM & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1750/BHM | 02/07/2025 | 90 | PROJECT INDIA | 391.67 | 0 | 0 | 35
1800 | BIRBHUM | Birbhum Division | Augmentation of Margram piped water supply scheme. , SM/18372 | Augmentation | Hiring of Ambassador Car (Diesel/Petrol/Electric) registered Luxury Taxi for the office of the Assistant Engineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition with effect from 01.02.2025 to 31.01.2026 i.e. (365 Days) (For JJM Works) (SL. No. 01) | 133/RSD | 31/01/2025 | 365 | PULAK KUMAR PAL | 1.72 | 0 | 0 | 0
1801 | BIRBHUM | Bolpur Mechanical | Dhananjaypur Piped Water Supply Scheme. , SM/12688 | New | Providing Electro-mechanical accessories and others for DHANANJAYPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 3292/Bol.MD | 29/09/2023 | 60 | ABHISEK ENGTNEERING CONCERN | 27.4 | 0 | 0 | 0
1802 | BIRBHUM | Birbhum Division | Dhananjaypur Piped Water Supply Scheme. , SM/12688 | New | Material Requisition To Resource Division | 1443/BHM | 25/04/2023 | 0 | Resource Division | 20.68 | 0 | 0 | 0
1803 | BIRBHUM | Birbhum Division | Dhananjaypur Piped Water Supply Scheme. , SM/12688 | New | Material Requisition To Resource Division | 2442/BHM | 30/08/2024 | 0 | Resource Division | 10.92 | 0 | 0 | 0
1804 | BIRBHUM | Birbhum Division | Dhananjaypur Piped Water Supply Scheme. , SM/12688 | New | Sinking of 300 X 200 mm Dia (through) and 180 m deep tubewell , 02 nos, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 250 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to water supply scheme at Dhananjaypur & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | 2114/BHM | 29/07/2024 | 730 | QUAZI SIRAJUL ISLAM | 435.37 | 0 | 0 | 1
1805 | BIRBHUM | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district , SM/18510 | New | Providing Electro-mechanical accessories and others for Mahesha PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | 3279/Bol.MD | 29/09/2023 | 60 | WEST BENGAL ENGINEERING CO. | 66.12 | 0 | 0 | 0
1806 | BIRBHUM | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district , SM/18510 | New | Material Requisition To Resource Division | 1446/BHM | 25/04/2023 | 0 | Resource Division | 50.7 | 0 | 0 | 0
1807 | BIRBHUM | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district , SM/18510 | New | Supply, delivery and storage of different Electro-Mechanical accessories at Mahesha PWSS under Bolpur Mmechanical Dsivision, PHE Dte. | 3759/Bol.MD | 12/09/2024 | 30 | P. K. ENGINEERING | 16.05 | 0 | 0 | 0
1808 | BIRBHUM | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district , SM/18510 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Well and allieds works at Mahesha Piped Water Supply Scheme, Block-Mayureswar-II under Bolpur Mechanical Division, P.H.E.Dte. | 3762/Bol.MD | 12/09/2024 | 30 | QUAZI NOZRUL ISLAM | 25.33 | 0 | 0 | 0
1809 | BIRBHUM | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district , SM/18510 | New | Continuation Work Order for Preparation & Submission of DPR for (MAHESHA) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | 324/RSD | 08/09/2022 | 45 | ENVIROTECH SOLUTIONS | 3.54 | 0 | 0 | 100
1810 | BIRBHUM | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district , SM/18510 | New | Continuation Work Order for Preparation & Submission of DPR for (MAHESHA) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | 435/RSD | 21/11/2022 | 45 | ENVIROTECH SOLUTIONS | 3.54 | 0 | 0 | 100
1811 | BIRBHUM | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district , SM/18510 | New | Supply, delivery and Installation of Centrifugal pumping machinery at Mahesha PWSS under Bolpur Mechanical Division, P.H.E. Dte. of Mayureswar - II Block | 376/Bol.MD | 06/03/2024 | 45 | MITRA ENTERPRISE | 7.69 | 0 | 0 | 100
1812 | BIRBHUM | Bolpur Mechanical | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district , SM/18510 | New | Replacement of PDB cum MCC Panel including other allieds works at Mahesha PWSS under Bolpur Mechanical Division, P.H.E. Dte. Of Mayureswar - II block. | 378/Bol.MD | 06/03/2024 | 45 | J.K.ENGINEERING CO | 7.25 | 0 | 0 | 100
1813 | BIRBHUM | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district , SM/18510 | New | Material Requisition To Resource Division | 2390/BHM | 27/08/2024 | 0 | Resource Division | 16.84 | 0 | 0 | 0
1814 | BIRBHUM | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district , SM/18510 | New | Sinking of 250 X 150 mm Dia, 150 m deep Tube Well Drilling by Direct Rotary method, Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing FHTC, related to water supply scheme at Mahesha & its adjoining mouzas water supply scheme within Mayureswar-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | 1952/BHM | 04/07/2024 | 850 | S K CONSTRUCTION VILL& POST - DEBKUNDA, P.S - BELDANGA, DIST - MURSHIDABAD | 609.18 | 0 | 0 | 60
1815 | BIRBHUM | Birbhum Division | Mahesha Piped water supply scheme of Mayureswar-II block in birbhum district , SM/18510 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
1816 | BIRBHUM | Birbhum Division | Gulalgachi Piped Supply Scheme , SM/18419 | New | Material Requisition To Resource Division | 1453/BHM | 25/04/2023 | 0 | Resource Division | 435.57 | 0 | 0 | 0
1817 | BIRBHUM | Bolpur Mechanical | Gulalgachi Piped Supply Scheme , SM/18419 | New | QUOTATION FOR GULALGACHI PWSS RAJNAGAR BLOCK | BP-24-25-07 | 09/04/2024 | 0 | WBSEDCL | 6.1 | 0 | 0 | 0
1818 | BIRBHUM | Bolpur Mechanical | Gulalgachi Piped Supply Scheme , SM/18419 | New | Providing electro-mechanical accessories and others for Gulalgachi water supply scheme in Rajnagar Block under Bolpur Mechanical Division, PHE Dte | 1917/Bol.MD | 10/08/2023 | 756 | DEY ENTERPRISE | 105.62 | 0 | 0 | 84
1819 | BIRBHUM | Birbhum Division | Gulalgachi Piped Supply Scheme , SM/18419 | New | Different works related to water supply scheme at GULALGACHI & its adjoining mouzas Water Supply Scheme within RAJNAGAR Block including supply of all labour & materials under Birbhum Division, PHE Dte | 4145/BHM | 19/10/2023 | 744 | M/S SAHA AND MONDAL CONSTRUCTION | 635.78 | 0 | 0 | 10
1820 | BIRBHUM | Bolpur Mechanical | Gulalgachi Piped Supply Scheme , SM/18419 | New | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, P.H.E.Dte. | 1662/BOL.MD | 28/06/2024 | 200 | SATYAJIT GHOSH | 0.57 | 0 | 0 | 100
1821 | BIRBHUM | Bolpur Mechanical | Gulalgachi Piped Supply Scheme , SM/18419 | New | Hiring of Luxury Car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division, PHE. Dte. | 4229/Bol.MD | 24/10/2024 | 121 | RAJIB GHOSH | 0.57 | 0 | 0 | 100
1822 | BIRBHUM | Birbhum Division | Construction of Intake, CWR, Pump House, Raw & Clear Water Pumping Main and Booster Station for Sub-surface Based PWSS (Zone No. 1 to 20) in Koyrasole Block under Birbhum division, PHE Dte , SM/18425 | New | Material Requisition To Resource Division | 3810/BHM | 12/09/2023 | 0 | Resource Division | 1630.08 | 0 | 0 | 0
1823 | BIRBHUM | Birbhum Division | Construction of Intake, CWR, Pump House, Raw & Clear Water Pumping Main and Booster Station for Sub-surface Based PWSS (Zone No. 1 to 20) in Koyrasole Block under Birbhum division, PHE Dte , SM/18425 | New | Material Requisition To Resource Division | 623/BHM | 15/02/2024 | 0 | Resource Division | 301.46 | 0 | 0 | 0
1824 | BIRBHUM | Bolpur Mechanical | Construction of Intake, CWR, Pump House, Raw & Clear Water Pumping Main and Booster Station for Sub-surface Based PWSS (Zone No. 1 to 20) in Koyrasole Block under Birbhum division, PHE Dte , SM/18425 | New | New service connection at Intake site for sub-surface based piped water supply scheme at Khoyrasole . | BP-2024-2025-21 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.9 | 0 | 0 | 0
1825 | BIRBHUM | Birbhum Division | Construction of Intake, CWR, Pump House, Raw & Clear Water Pumping Main and Booster Station for Sub-surface Based PWSS (Zone No. 1 to 20) in Koyrasole Block under Birbhum division, PHE Dte , SM/18425 | New | Survey, Planning, Design, Supply, Delivery, Erection, Construction, Commissioning and Completion in all respect all Civil and E&M Works including all allied, related and Enabling Works for 5.0 MGD capacity Radial Collector Well, Access Bridge, Substation Building, 1000 Cum capacity UGR with high lift Pump House and Raw Water Rising Main from Collector Well to River Bank UGR including 03(Three) months Trial Run and subsequent Operation & Maintenance for 1(One) year for Sub-Surface Water Based Piped Water Supply Scheme in Khairasole Block, District Birbhum on Turnkey basis under Birbhum Division, PHE Dte. | 445/BHM | 01/02/2024 | 547 | G B CONSTRUCTION | 2150.9 | 0 | 0 | 70
1826 | BIRBHUM | Bolpur Mechanical | Construction of Intake, CWR, Pump House, Raw & Clear Water Pumping Main and Booster Station for Sub-surface Based PWSS (Zone No. 1 to 20) in Koyrasole Block under Birbhum division, PHE Dte , SM/18425 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at 20 nos. OHR site Piped water supply scheme of Khoyrasole project under Khoyrasole Block in the Dist. of Birbhum under Bolpur Mechanical Division, P.H.E. Dte. | 3892/Bol.MD | 23/09/2024 | 365 | SATYAJIT GHOSH | 145.74 | 0 | 0 | 68
1827 | BIRBHUM | Birbhum Division | Ayas Piped Water Supply Scheme. , SM/18669 | New | Material Requisition To Resource Division | 1495/BHM | 25/04/2023 | 0 | Resource Division | 249.36 | 0 | 0 | 0
1828 | BIRBHUM | Bolpur Mechanical | Ayas Piped Water Supply Scheme. , SM/18669 | New | Supply and Installation of High lift Pumping Machinery and other allied work for AYAS and Adjoining moujas water supply scheme under within Rampurhat - I Block Bolpur Mechanical Division PHE Dte | 3372/Bol.MD | 12/10/2023 | 628 | SINHA ELECTRICALS | 95.35 | 0 | 0 | 30
1829 | BIRBHUM | Birbhum Division | Ayas Piped Water Supply Scheme. , SM/18669 | New | Material Requisition To Resource Division | 2389/BHM | 27/08/2024 | 0 | Resource Division | 42.26 | 0 | 0 | 0
1830 | BIRBHUM | Bolpur Mechanical | Ayas Piped Water Supply Scheme. , SM/18669 | New | Supply & Installation of Low lift Pumping Mchinery and other allied work for AYAS & Adjoining moujas water supply scheme under within Rampurhat - I Block Bolpur Mechanical Division PHE Dte. | 3389/BOL.MD | 16/10/2023 | 533 | S.K.ELECTRICALS | 59.94 | 0 | 0 | 50
1831 | BIRBHUM | Birbhum Division | Ayas Piped Water Supply Scheme. , SM/18669 | New | Sinking of 250 X 150 mm Dia (through) and 25 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 8.00 m X 8.00 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM, 300 CuM, 150 CuM capacity O.H.R. for Zone-I, II and III respectively, 300 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration for Zone-I, II and III and Providing functional household tap connection related to water supply scheme at AYAS & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | 1949/BHM | 04/07/2024 | 635 | PRADIP KUMAR DEB, 103/4 NAINAN PARA LANE , KOLKATA-700036 | 1332.94 | 0 | 0 | 55
1832 | BIRBHUM | Birbhum Division | Tamra Piped Water Supply Scheme , SM/18739 | New | Preparation & Submission of DPR for Tamra & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 122/BSSD | 05/07/2022 | 45 | RADIANT | 1.62 | 0 | 0 | 100
1833 | BIRBHUM | Birbhum Division | Tamra Piped Water Supply Scheme , SM/18739 | New | Material Requisition To Resource Division | 436/BHM | 01/02/2024 | 0 | Resource Division | 54.82 | 0 | 0 | 0
1834 | BIRBHUM | Birbhum Division | Tamra Piped Water Supply Scheme , SM/18739 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
1835 | BIRBHUM | Birbhum Division | Tamra Piped Water Supply Scheme , SM/18739 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
1836 | BIRBHUM | Birbhum Division | Bahadurpur Piped Water Supply Scheme. , SM/12681 | New | Material Requisition To Resource Division | 1529/BHM | 26/04/2023 | 0 | Resource Division | 23.48 | 0 | 0 | 0
1837 | BIRBHUM | Bolpur Mechanical | Bahadurpur Piped Water Supply Scheme. , SM/12681 | New | Quotation deposit for empowering Bahadurpur Water Supply Scheme P/H -I in Murarai CCC under Bolpur Mechanical Division, PHE Dte. | BP-24-25-113 | 02/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.61 | 0 | 0 | 0
1838 | BIRBHUM | Birbhum Division | Bahadurpur Piped Water Supply Scheme. , SM/12681 | New | Different works related to water supply scheme at Bahadurpur & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. Sl No 01 | 884/BHM | 21/03/2023 | 1229 | ABUL KALAM | 380.11 | 0 | 0 | 70
1839 | BIRBHUM | Bolpur Mechanical | Bahadurpur Piped Water Supply Scheme. , SM/12681 | New | Providing Electro-mechanical accessories and others for BAHADURPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 3291/Bol.M.D | 29/09/2023 | 550 | SUNIL RABIDAS | 27.54 | 0 | 0 | 60
1840 | BIRBHUM | Bolpur Mechanical | Bahadurpur Piped Water Supply Scheme. , SM/12681 | New | Name of Work: Supply, delivery and installation of servo motor operated copper wound line voltage corrector at T/W-I&II for Bahadurpur water supply scheme of Murarai-I Block under Bolpur Mechanical Division, PHE Dte.. | 3802/BOL.MD | 12/09/2024 | 111 | SUNIL RABIDAS | 5.02 | 0 | 0 | 100
1841 | BIRBHUM | Bolpur Mechanical | Chinpai Piped Water Supply Scheme. , SM/18462 | New | Providing electro-mechanical accessories and others for Chinpai & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | 1914/Bol.MD | 10/08/2023 | 366 | M/S P.P ELECTRICALS | 106.93 | 0 | 0 | 50
1842 | BIRBHUM | Birbhum Division | Chinpai Piped Water Supply Scheme. , SM/18462 | New | Material Requisition To Resource Division | 1390/BHM | 24/04/2023 | 0 | Resource Division | 179.71 | 0 | 0 | 0
1843 | BIRBHUM | Birbhum Division | Chinpai Piped Water Supply Scheme. , SM/18462 | New | Material Requisition To Resource Division | 3281/BHM | 27/07/2023 | 0 | Resource Division | 1.02 | 0 | 0 | 0
1844 | BIRBHUM | Bolpur Mechanical | Chinpai Piped Water Supply Scheme. , SM/18462 | New | Supply and Delivery of Pump Starter, Diaphragm type Chlorinator dosing pump and Colum pipes at Chinpai and Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | 707/Bol.MD | 27/03/2024 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 7.99 | 0 | 0 | 100
1845 | BIRBHUM | Birbhum Division | Chinpai Piped Water Supply Scheme. , SM/18462 | New | Different works related to water supply scheme at CHINPAI, LOBA & PARATPUR and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 3476/BHM | 08/08/2023 | 816 | B RAI CONSTRUCTION COMPANY | 2497.19 | 0 | 0 | 45
1846 | BIRBHUM | Birbhum Division | Chinpai Piped Water Supply Scheme. , SM/18462 | New | Construction of 100 Cum Capacity CWR as per departmental drawing nearer to Kochujore for collection of water from Chinpai Head work site under Chinpai Piped Water Supply Scheme under Birbhum Sadar Sub- Division within Birbhum Division, PHE Dte. | 308/BSSD | 22/05/2025 | 120 | HIRANMAY GHOSH | 17.82 | 0 | 0 | 100
1847 | BIRBHUM | Birbhum Division | Chinpai Piped Water Supply Scheme. , SM/18462 | New | Laying of rising main pipe line, Jack Pushing of Railway & NH-14 for Chinpai Piped Water Supply Scheme in Rajnagar Block under Birbhum Sadar Sub-Division, PHE Dte. within Birbhum Division, P.H.E. Dte. | 2164/BHM | 20/08/2025 | 90 | B RAI CONSTRUCTION COMPANY | 73.46 | 0 | 0 | 0
1848 | BIRBHUM | Birbhum Division | Ekura Piped Water Supply Scheme. , SM/13949 | New | Preparation & Submission of DPR for Ekura & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 115/BSSD | 28/06/2022 | 45 | RADIANT | 2.64 | 0 | 0 | 100
1849 | BIRBHUM | Birbhum Division | Ekura Piped Water Supply Scheme. , SM/13949 | New | Material Requisition To Resource Division | 426/BHM | 01/02/2024 | 0 | Resource Division | 109.46 | 0 | 0 | 0
1850 | BIRBHUM | Birbhum Division | Ekura Piped Water Supply Scheme. , SM/13949 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
1851 | BIRBHUM | Birbhum Division | Ekura Piped Water Supply Scheme. , SM/13949 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
1852 | BIRBHUM | Birbhum Division | Kankalitala piped water supply scheme. , SM/18518 | New | Material Requisition To Resource Division | 1546/BHM | 26/04/2023 | 0 | Resource Division | 214.47 | 0 | 0 | 0
1853 | BIRBHUM | Bolpur Mechanical | Kankalitala piped water supply scheme. , SM/18518 | New | Supply and delivery of chlorinator dosing pump for kankalitala Water Supply Project under Bolpur Mechanical Divn. P.H.E. Dte. | 3819/BOL.MD | 18/09/2024 | 20 | SINHA ELECTRICALS | 3.24 | 0 | 0 | 100
1854 | BIRBHUM | Bolpur Mechanical | Kankalitala piped water supply scheme. , SM/18518 | New | WBSEDCL QUOTATION FOR KANKALITALA PWSS | BP-23-24-222 | 15/01/2024 | 0 | WBSEDCL | 10.64 | 0 | 0 | 0
1855 | BIRBHUM | Central Drilling | Kankalitala piped water supply scheme. , SM/18518 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
1856 | BIRBHUM | Birbhum Division | Kankalitala piped water supply scheme. , SM/18518 | New | Different works related to water supply scheme at IKSHUDHARA, KANKALITALA, KASBA & KENDANGAL Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 4139/BHM | 18/10/2023 | 896 | M/S TAPAS KUMAR CHAKRABORTY | 2684.99 | 0 | 0 | 60
1857 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum , SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur Water Supply Scheme within Rampurhat Sub-Division under Birbhum Division, PHE Dte¿ (Sl. No.2) | 2033/BHM | 09/12/2021 | 60 | TAPAN KUMAR DATTA | 94.18 | 0 | 0 | 0
1858 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum , SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-5) | 1019/BHM | 17/06/2021 | 60 | SUNIL RABI DAS | 50.07 | 99.56 | 100 | 100
1859 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum , SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Talipara within the command area of Bishnupur Water Supply Scheme of Rampurhat - II Block under Brbhum Division, PHE Dte. (Sl. No.04) | 36 / BH | 26/02/2021 | 20 | BIJOY KUMAR CHOWDHURY | 4.84 | 9.67 | 200 | 100
1860 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum , SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Talipara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | 179/BH | 03/11/2021 | 15 | BIJOY KUMAR CHOUDHURY | 3.73 | 3.72 | 100 | 100
1861 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum , SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bishnupur Water Supply Scheme within Rampurhat Sub-Division under Birbhum Division, PHE Dte¿ (Sl. No.2) | 2033/ BHM | 09/12/2021 | 60 | TAPAN KUMAR DATTA | 94.18 | 0 | 0 | 40
1862 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum , SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Sashtitalapara and its adjoining area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | 178/BH | 03/11/2021 | 15 | M/S K.S. GHOSH | 3.64 | 3.61 | 100 | 100
1863 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum , SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Bishnupur Panchayatpara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | 180/BH | 03/11/2021 | 15 | MUKADDUMUL MOULA | 3.86 | 3.85 | 100 | 100
1864 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum , SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Baroipara and its adjoining area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | 177/BH | 03/11/2021 | 15 | TAPAN ENTERPRISE | 4.83 | 4.83 | 100 | 50
1865 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum , SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Bishnupur Konaipara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | 34/BH | 26/02/2021 | 20 | MUKADDUMUL MOULA | 4.84 | 9.67 | 200 | 0
1866 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum , SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Sashtitalapara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | 37/BH | 26/02/2021 | 20 | M/S K.S. GHOSH | 4.84 | 9.68 | 200 | 0
1867 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum , SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Bishnupur Panchayatpara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | 35/BH | 26/02/2021 | 20 | M/S S.N CONSTRUCTION | 4.84 | 9.67 | 200 | 0
1868 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bishnupur (Phase-I) PWSS within Ilambazar Block, Dist.- Birbhum , SM/08172 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in habitation of Basoa Baroipara within the command area of Bishnupur Water Supply Scheme of Rampurhat-II Block under Birbhum Division, P.H.E. Dte. | 38/BH | 26/02/2021 | 20 | TAPAN ENTERPRISE | 4.84 | 9.67 | 200 | 0
1869 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-III) , SM/07647 | Retrofitting | Hiring of Ambassador Car (Diesel) registered Luxury Taxi for the office of the Assistant Engineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition with effect from 01.08.2023 to 31.01.2024 i.e. (184 Days). | 199/RSD | 28/07/2023 | 184 | SOUMITA PAL | 0.86 | 0 | 0 | 100
1870 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-III) , SM/07647 | Retrofitting | Hiring of Ambassador Car (Diesel) registered Luxury Taxi for the office of the Assistant Engineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition with effect from 01.02.2024 to 31.07.2024 i.e. (182 Days). | 27/RSD | 22/01/2024 | 182 | SOUMITA PAL | 0.86 | 0 | 0 | 0
1871 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Dunigram PWSS (Phase-III) , SM/07647 | Retrofitting | Continuation Work Order for Hiring of Ambassador Car (Diesel) registered Luxury Taxi for the office of the Assistant Engineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition with effect from 01.02.2024 to 31.07.2024 i.e. (182 Days) "from 01.08.2024 to 31.01.2025 i.e. (184 Days)" | 354/RSD | 31/07/2024 | 184 | SOUMITA PAL | 0.86 | 0 | 0 | 0
1872 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for remaining household at UTTAR SULTANPUR Mouza from existing distribution System within the command area of Batikar Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. | 403/BSD | 25/10/2021 | 10 | INDRAJIT DAS | 0.96 | 0.6 | 100 | 100
1873 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Karchadihi Mouza within the command area of for Batikar Water Supply Scheme under Bolpur Sub Division of Birbhum Division, PHE Dte.(Sl. No.2) | 255/BHM | 26/02/2021 | 45 | MS KAZIMEHERUDDIN | 4.67 | 9.33 | 199.86 | 100
1874 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Narasonda, Ikshusara, Anaipur of Batikar w/s Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHE Dte | 1563/BHM | 17/12/2020 | 60 | MS B N ENTERPRISES | 4.91 | 0 | 0 | 0
1875 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Balta Mouza (Part) within the command area of Batikar Water Supply Scheme under Bolpur Sub Division of Birbhum Division, PHE Dte. (Sl. No.1) | 280/BHM | 26/02/2021 | 45 | HIMANGSU SEKHAR SARKAR | 4.67 | 9.01 | 200 | 100
1876 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) within the Command area of Batikar Water Supply Scheme in Anaipur (Purbo Para) village for Swajal Gram under Illambazar Block of Bolpur Sub-Division within Birbhum Division P.H.E. Deptt. | 381/BSD | 29/09/2022 | 10 | M/S SARADA CONSTRUCTION. | 0.96 | 0.82 | 100 | 91
1877 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) within the Command area of Batikar Water Supply Scheme in Karchadihi, Ikshusara and Anaipur (Paschim Para) village for Swajal Gram under Illambazar Block of Bolpur Sub-Division within Birbhum Division P.H.E. Deptt. | 382/BSD | 29/09/2022 | 10 | M/S SARADA CONSTRUCTION. | 0.97 | 0.86 | 100 | 91
1878 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Construction of remaining Boundary Wall at Head Work site of BATIKAR Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Length: 123 Mtr.). (Sl. 04) | 425/BSD | 18/11/2021 | 60 | GANAPATI ENGINEERING CORP. | 4.85 | 0 | 0 | 0
1879 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Khushtikuri of Batikar w/s Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. (6a) | 1172 /BHM | 21/09/2020 | 45 | INDRAJIT DAS | 24.28 | 35.25 | 191.42 | 89
1880 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Balance work of Laying Rising main with inter connection pipe line from Tube Well No. - 2 to Tube Well No. - 1 including OHR with Distribution main of BATIKAR Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No. -10) | 320/BSD | 31/08/2021 | 15 | PRANAB KUMAR GHOSH | 0.93 | 0 | 0 | 0
1881 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Batikar Gram Panchayet under Batikar Water Supply Scheme in Batikar Jagpalla and Batikar Bus Stand and Repairing of pipeline due to leakage of house connection in distributions pipeline in different area (i.e. Kustikuri, Nabagram and Charakdanga) under Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 02). | 201/BSD | 20/05/2022 | 30 | M/S SARADA CONSTRUCTION. | 3.98 | 3.02 | 100 | 75
1882 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Allied works of extension boosting pipe lines for Providing Functional Household Tap Connection (FHTC) from existing distribution system in various node point (From 03 to 11,110 to 120, 144 to 158, 9 to 168 174 to 175), of Batikar village within the command area in the villages Batikar (JL No.- 02.) Water Supply Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. - 03) | 11/BSD | 11/01/2022 | 30 | HIMANGSU SEKHAR SARKAR | 4.38 | 4.26 | 100 | 100
1883 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Retrofitting works to the existing distribution system within the command area of Batikar Water Supply Scheme at Khustikuri and Narasonda Moujas under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 324/BSD | 01/09/2021 | 30 | INDRAJIT DAS | 4.85 | 2.75 | 100 | 74
1884 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing Distribution System within the command area of Batikar Water Supply Scheme at Mouja: KHUSTIKURI & UTTAR SULTANPUR under Bolpur Sub Division within Birbhum Division, PHED. (Sl. - 01) | 379/ BSD | 07/10/2021 | 30 | MS KAZIMEHERUDDIN | 4.77 | 4.77 | 100 | 100
1885 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Narasonda, Ikshusara, Anaipur of Batikar w/s Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1171 /BHM | 21/09/2020 | 60 | MS B N ENTERPRISES | 39.49 | 45.2 | 200 | 0
1886 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Batikor of Batikar w/s Scheme at Illambazar Block under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1170 /BHM | 21/09/2020 | 60 | HIMANGSU SEKHAR SARKAR | 31.27 | 47.33 | 200 | 0
1887 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at habitation Batikor, village-Batikor (JL No.02) at different locations from existing distribution system within the command area of Batikor piped water supply scheme at Illambazar Block under Bolpur Sub Division within Birbhum Division, PHE Dte. (Phase-1) | 1089/BHM | 05/09/2020 | 30 | PRANAB KUMAR GHOSH | 4.71 | 9.42 | 200 | 0
1888 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Batikar PWSS(Phase-I) , SM/06740 | Retrofitting | Retrofitting work for Providing Balance Functional Household Tap Connection (FHTC) in Batikar (02) under BATIKAR Gram Panchayat within the Command area of Batikar Water Supply, Scheme for Swajal Gram under Illambazar Block of Bolpur Sub-Division within BIRBHUM DIVISION P.H.E. Deptt.(Sl. No.12) | 332/BHM | 02/02/2023 | 45 | KAUSHIK RAY | 18.74 | 0 | 0 | 100
1889 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bansjore PWSS (Phase-I) , SM/07006 | Retrofitting | Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bansjore w/s Scheme in Suri Sadar Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.2) | 1865/ BHM | 16/11/2021 | 60 | PRANAB KUMAR GHOSH | 65.87 | 41.76 | 63.41 | 85
1890 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bansjore PWSS (Phase-I) , SM/07006 | Retrofitting | Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bansjore W/S Scheme in Suri Sadar Sub-Division under Birbhum Division, P.H.E. Dte. (Sl. No.- 2) | 1865/BHM | 16/11/2021 | 60 | PRANAB KUMAR GHOSH | 65.87 | 20.25 | 100 | 45
1891 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Bansjore PWSS (Phase-I) , SM/07006 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bansjore W/S Scheme in Suri Sadar Sub-Division under Birbhum Division, PHE Dte. | 1248/BHM | 17/04/2023 | 45 | PRANAB KUMAR GHOSH | 33.15 | 0 | 0 | 100
1892 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. , SM/09362 | Retrofitting | Laying of Rising Main from Tube Well - I & Tube Well - II to O.H.R. for Tilutia Zone - II Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 04). | 87/BSD | 10/03/2022 | 20 | SYED HASMAT ALI | 2.65 | 0 | 0 | 100
1893 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. , SM/09362 | Retrofitting | Construction of Pump House (Size - 5.40 Mtr. x 3.60 Mtr.) at Tilutia Zone -I Head work site of Tilutia water supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (2nd Call). (Sl. 04) | 12/BSD | 11/01/2022 | 60 | SANTU SEKH | 4.84 | 0 | 0 | 100
1894 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. , SM/09362 | Retrofitting | Laying of Rising Main pipeline from Tube-well No. - I & II to O.H.R at Mahanpur of Tilutia Zone - I Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED.. (Sl. No.: 15). | 86/BSD | 10/03/2022 | 15 | INDRAJIT DAS | 2.52 | 0 | 0 | 100
1895 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. , SM/09362 | Retrofitting | Construction of Pump House (Size - 5.40 Mtr. x 3.60 Mtr.) at Tilutia Zone - II Head Works site of Tilutia Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (2nd Call). (Sl. - 02) | 17/BSD | 11/01/2022 | 60 | MD SAFIUL HASSAN | 4.82 | 0 | 0 | 100
1896 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. , SM/09362 | Retrofitting | Sinking of 02(Two) nos. 300mm X 200mm dia. X 300m deep Tube Wells by Rotary Rig for Tilutia-II Piped Water Supply Scheme in Nanoor Block under Bolpur Sub-Division within Birbhum Division, P.H.E Dte.(2nd Call) (Sl. No.5) | 1503/BHM | 26/11/2020 | 60 | PASCON | 32.45 | 0 | 0 | 100
1897 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. , SM/09362 | Retrofitting | Supply and delivery of 300mm dia., 3.0 Mtr. long UPVC slotted pipe (Strainer) (CD) for sinking of 02 nos deep Tube-wells of Tilutia Zone - II Piped Water Supply Scheme in Nanoor Block under Bolpur Sub-Division within Birbhum Division PHED. (Sl. No.: 01). | 479/BSD | 27/12/2021 | 15 | PASCON | 2.05 | 0 | 0 | 100
1898 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. , SM/09362 | Retrofitting | Adopting Jack Pushing of Hume Pipe (NP3/ NP4) as Cashing to Cross Water carrier Pipe in front of OHR at TILUTIA ZONE - II Water Supply Scheme under Bolpur Sub-Division, P.H.E. Deptt. (Sl. No.: 10). | 242/BSD | 22/06/2022 | 20 | S. S. CONSTRUCTION | 3.1 | 0 | 0 | 100
1899 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. , SM/09362 | Retrofitting | Supply and delivery of 150mm and 100mm. dia. Sluice Valves including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Tilutia Zone - I & II Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 02). | 93/BSD | 11/03/2022 | 15 | MAKALI ENGINEERING CORPORATION | 1.81 | 0 | 0 | 100
1900 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. , SM/09362 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from the existing distribution system within the command area of "Tilutia Zone - II under Tilutia Zone - II Water Supply Scheme within Birbhum Division PHE Dte." (Sl. No. - 8) | 1476/BHM | 12/07/2022 | 60 | RAJKUMAR DAS | 66.75 | 66.67 | 100 | 100
1901 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. , SM/09362 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tilutia Zone-I under Tilutia Zone-I Water Supply Scheme within Birbhum Division, PHE Dte. | 2245/BHM | 17/10/2022 | 60 | MANAS KUMAR MONDAL | 66.75 | 52.59 | 78.79 | 100
1902 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. , SM/09362 | Retrofitting | Balance FHTC works at different Villages within coverage area of Tilutia Water Supply Scheme (Zone-II) under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No.10) | 665/BHM | 28/02/2023 | 135 | INDRAJIT DAS | 25.54 | 0 | 0 | 100
1903 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. , SM/09362 | Retrofitting | Dismantling & Restoration of cement concrete road for laying of distribution pipeline of Tilutia Zone - I Piped Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 01) | 446/BSD | 10/12/2021 | 30 | M/S KRIPASINDHU GHOSH & CO. | 4.82 | 0 | 0 | 100
1904 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Tilutia PWSS within Nanoor Block District Birbhum under Birbhum Division, PHE Dte. , SM/09362 | Retrofitting | Withdrawing of existing pipe for previous Head Work Site and relaying of 250mm. dia. DI pipes From OHR to Node point 192A due to Change of Head Work Site at Tilutia Zone - I Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHED. (Sl. No.: 07). | 204/BSD | 23/05/2022 | 192 | ARABINDA GHOSH | 3.65 | 0 | 0 | 100
1905 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Margram in Rampurhat Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.7) | 1567/BHM | 26/07/2022 | 60 | PULAK KUMAR PAL | 44.05 | 44.04 | 100 | 100
1906 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | Providing FHTC from existing distribution system with Allied works at Hospital para, Chot dangal within Margram w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-13) | 316/RSD | 08/09/2022 | 30 | M/S TAPAN ENTERPRISE | 4.98 | 4.96 | 100 | 100
1907 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Margram in Rampurhat Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.7) | .1567/BHM | 26/07/2022 | 60 | PULAK KUMAR PAL | 44.05 | 0 | 0 | 0
1908 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | Sinking of o1 (one) No 200mm dia.X 66.0 mtr deep Tube Well with UPVC pipe & strainer for Margram W/s scheme under Birbhum Division, P.H.E. Dte. | 29/RSD | 04/01/2022 | 30 | TAPAN ENTERPRISE | 4.29 | 0 | 0 | 100
1909 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | Laying of HDPE (110mm and 90mm dia) distribution line and concreting works etc at Hospital para, khanpara, Benegram of Margram water supply scheme under Rampurhat sub division under Birbhum Division PHE Dte. | 102/RSD | 07/03/2022 | 30 | RUBAL CONSTRACTION | 4.99 | 0 | 0 | 100
1910 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Margram Water Supply Scheme within Birbhum Rampurhat Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.4) | 739/BHM | 04/04/2022 | 60 | PULAK KUMAR PAL | 52.82 | 52.57 | 100 | 100
1911 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | Additional concreting works (Fulmali para, Baganpara(Part) for LDS of Margram pipe water supply scheme under Rampurhat Sub-Division under Birbhum Division PHE Dte. | 101/RSD | 07/03/2022 | 30 | PULAK KUMAR PAL | 4.96 | 0 | 0 | 100
1912 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | Laying of Distribution Main pipeline through crossing of PWD road at Margram Hospital More by adopting Jack Pushing method for Margram PWSS under Rampurhat Sub-Division, PHE Dte. | 112/RSD | 07/03/2022 | 15 | PULAK KUMAR PAL | 4.33 | 0 | 0 | 100
1913 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | Providing FHTC from existing distribution system with Allied works at Benegram & Mazarpara within Margram w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-12) | 315/RSD | 08/09/2022 | 30 | RUBAL CONSTRACTION | 4.97 | 4.97 | 100 | 100
1914 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | Providing FHTC from existing distribution system with Allied works at Khanpur within Margram w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-14) | 317/RSD | 08/09/2022 | 30 | RUBAL CONSTRACTION | 4.97 | 4.96 | 100 | 100
1915 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | Material Requisition To Resource Division | 219/BHM | 02/02/2022 | 0 | Resource Division | 16.47 | 0 | 0 | 0
1916 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | Material Requisition To Resource Division | 2205/BHM | 12/10/2022 | 0 | Resource Division | 0.05 | 0 | 0 | 0
1917 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | Additional Laying distribution system at Margram mouza including FHTC under Augmentation of Margram Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. | 1343/BHM | 20/04/2023 | 90 | PULAK KUMAR PAL | 145.64 | 0 | 0 | 50
1918 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | DI Relaying & Concrete Road Restoration work at Benegram Mouza under MARGRAM Water Supply Scheme within Rampurhat Sub-Division Birbhum Division PHE Dte. | 691/RSD | 31/07/2025 | 90 | RUBAL CONSTRACTION | 2.03 | 0 | 0 | 0
1919 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Margram PWSS within Rampurhat-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09367 | Retrofitting | Laying UPVC Pipe line in place of AC line due to strengthenig of Rampurhat--Parulia PWD Road at Margram Mouza of existing MARGRAM Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. (Sl. No.3) | 231/BHM | 20/01/2023 | 30 | MAINUL ISLAM | 3.72 | 0 | 0 | 100
1920 | BIRBHUM | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07153 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Balia Mrityunjoypur of Narayanpur w/s Scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. (Sl. No.3) | 1706/BHM | 23/12/2020 | 60 | SANJUKTA ENGINEERS | 36.44 | 6.91 | 100 | 27
1921 | BIRBHUM | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07153 | Retrofitting | Laying of Distribution System by HDPE pipe below heavy duty PWD concrete Road at Narayanpur for Narayanpur Water Supply Scheme Form Bhawani Padmabati Pry School to Narayanpur High School under Rampurhat Sub-Division, within Birbhum Division P.H.E Dte. (Sl. No.4) | 622/BHM | 11/03/2022 | 60 | SANJUKTA ENGINEERS | 6.96 | 0 | 0 | 0
1922 | BIRBHUM | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07153 | Retrofitting | Sinking of o1 (one) No 200mm dia.X 42.0 mtr deep Tube Well with UPVC pipe & strainer for Narayanpur W/s scheme under Birbhum Division, P.H.E. Dte. | 30/RSD | 04/01/2022 | 30 | ISLAM CONSTRUCTION | 2.92 | 0 | 0 | 50
1923 | BIRBHUM | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07153 | Retrofitting | Laying Bypass UPVC Pipe line from CWR to Suripara more for providing drinking water Hattala surrounding Area of Narayanpur W/S Scheme under Rampurhat Sub-Division, P.H.E. Dte within Birbhum Division, P.H.E. Dte. (Sl. No.2) | 2069/BHM | 13/12/2021 | 60 | ISLAM CONSTRUCTION | 13.26 | 12.86 | 100 | 50
1924 | BIRBHUM | Central Drilling | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07153 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR NARAYANPUR W/S SCHEME, SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | 1132/CDD | 04/11/2022 | 30 | MENAKA ENTERPRISE | 11.09 | 8.61 | 100 | 92
1925 | BIRBHUM | Central Drilling | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07153 | Retrofitting | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR NARAYANPUR W/S SCH, SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | 1133/CDD | 04/11/2022 | 30 | MENAKA ENTERPRISE | 8.09 | 8.09 | 100 | 100
1926 | BIRBHUM | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07153 | Retrofitting | Payment for Supply of diesel | BP-2023-24-127 | 25/08/2023 | 0 | JAYRAM FILLING STATION | 0.72 | 0 | 0 | 0
1927 | BIRBHUM | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07153 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Narayanpur of Narayanpur w/s Scheme at Rampurhat-I Block under Birbhum Division, PHE Dte. (Sl. No.12) | 1426 / BHM | 04/11/2020 | 60 | SUNIL RABI DAS | 35.91 | 71.15 | 172.9 | 0
1928 | BIRBHUM | Birbhum Division | Retrofitting works of Narayanpur(Phase-II) Water Supply Scheme under Rampurhat-I Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07153 | Retrofitting | PCC Work for road restoration at Hattala due to laying of 160mm dia HDPE Bypass Pipe line from CWR to Suripara more for providing drinking water at Hattala surrounding Area of Narayanpur W/S Scheme under Rampurhat Sub- Division, P.H.E. Dte within Birbhum Division P.H.E. Dte | 1012/BHM | 30/03/2023 | 45 | ISLAM CONSTRUCTION | 4.17 | 4.15 | 100 | 0
1929 | BIRBHUM | Bolpur Mechanical | Augmentation of Tejhati PWSS , SM/10166 | Augmentation | Supply and installation of Voltage Correction device & other allied work at Augmentation of Tejhati water supply scheme under Bolpur Mechanical Division PHE Dte | 714/Bol.MD | 19/04/2023 | 45 | STANDARD ELECTRICALS | 14.18 | 14.18 | 100 | 0
1930 | BIRBHUM | Birbhum Division | Augmentation of Tejhati PWSS , SM/10166 | Augmentation | Material Requisition To Resource Division | 486/BHM | 02/03/2022 | 0 | Resource Division | 4.21 | 0 | 0 | 0
1931 | BIRBHUM | Birbhum Division | Augmentation of Tejhati PWSS , SM/10166 | Augmentation | Material Requisition To Resource Division | 1111/BHM | 10/04/2023 | 0 | Resource Division | 14.64 | 0 | 0 | 0
1932 | BIRBHUM | Birbhum Division | Augmentation of Tejhati PWSS , SM/10166 | Augmentation | Construction of 300 cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Tejhati W/S Scheme under Nalhati Sub Division with Birbhum Division, PHE Dte.(As per Departmental Drawing) | 1636/BHM | 02/05/2023 | 276 | GOLAM RASUL | 86.89 | 0 | 0 | 40
1933 | BIRBHUM | Birbhum Division | Augmentation of Tejhati PWSS , SM/10166 | Augmentation | Soil Investigation for determination of the safe bearing capacity and other relevant parameters of soil for 1 no OHR site at Tejhati Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | 167/AE/NSD | 22/03/2022 | 15 | MOYTEC | 0.99 | 0.99 | 100 | 100
1934 | BIRBHUM | Birbhum Division | Augmentation of Tejhati PWSS , SM/10166 | Augmentation | Sinking replacement of 200mm dia Tube Well of UPVC pipe 90m deep with fibre glass strainer including connecting main for Tejhati PWSS under Nalhati Sub- Division within Birbhum Division PHED | 2017/BHM | 06/06/2023 | 45 | BHARAT CONSTRUCTION | 6.85 | 0 | 0 | 80
1935 | BIRBHUM | Birbhum Division | Augmentation of Tejhati PWSS , SM/10166 | Augmentation | Allied work of distribution Pipe line including FHTC Work along with restoration of road including dismantling work with jack pushing & Augur Boring for Augmentation of Tejhati Water Supply Scheme under Nalhati Sub-Division within Birbhum Division P.H.E. Dte. | 3653/BHM | 25/08/2023 | 60 | QUAZI SIRAJUL ISLAM. | 67.81 | 0 | 0 | 70
1936 | BIRBHUM | Bolpur Mechanical | Augmentation of Tejhati PWSS , SM/10166 | Augmentation | Supply Delivery and Installation of automatically Voltage Correction Device at Augmentation of Tejhati water supply scheme (Block- Nalhati - I) under Bolpur Mechanical Division, PHE Dte. | 1363/AE-III | 17/10/2023 | 15 | SINHA ELECTRICALS | 3.38 | 0 | 0 | 100
1937 | BIRBHUM | Bolpur Mechanical | Augmentation of Tejhati PWSS , SM/10166 | Augmentation | Supply and Delivery of automatically controlled Chlorinator for Augmentation of Tejhati water supply scheme (Block- Nalhati - I) under Bolpur Mechanical Division, PHE Dte. | 1449/AE-III | 17/11/2023 | 10 | CINZANO | 3.27 | 0 | 0 | 100
1938 | BIRBHUM | Birbhum Division | Augmentation of Tejhati PWSS , SM/10166 | Augmentation | Laying distribution system including FHTC for proposed augmentation scheme for Tezhati Piped Water Supply Scheme, Nalhati-I Block, under Birbhum Division, PHE Dte.¿ (Sl. No.7) | 1150/BHM | 23/05/2022 | 1012 | QUAZI SIRAJUL ISLAM. | 168.84 | 75.58 | 44.77 | 62
1939 | BIRBHUM | Birbhum Division | Kulara Piped Water Supply Scheme. , SM/12695 | New | Material Requisition To Resource Division | 1504/BHM | 25/04/2023 | 0 | Resource Division | 8.75 | 0 | 0 | 0
1940 | BIRBHUM | Bolpur Mechanical | Kulara Piped Water Supply Scheme. , SM/12695 | New | Supply and installation of manual operated Motor control panel for Kulara water supply scheme (Amdol Pump House-III) of Murarai-II Block under Bolpur Mechanical Division, PHE Dte. | 178/BMSD(D) | 18/03/2024 | 30 | M/S M3 SOLUTION | 2.6 | 0 | 0 | 100
1941 | BIRBHUM | Bolpur Mechanical | Kulara Piped Water Supply Scheme. , SM/12695 | New | Quotation deposit for empowering Kulora Water Supply Scheme P/H -II in Paikar CCC under Bolpur Mechanical Division, PHE Dte | BP-2024-2025-43 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.48 | 0 | 0 | 0
1942 | BIRBHUM | Bolpur Mechanical | Kulara Piped Water Supply Scheme. , SM/12695 | New | WBSEDCL QUOTATION FOR KULARA P H NO.I WS SCHEME | BP-23-24-227 | 15/01/2024 | 0 | WBSEDCL | 2.99 | 0 | 0 | 0
1943 | BIRBHUM | Birbhum Division | Kulara Piped Water Supply Scheme. , SM/12695 | New | Different works related to water supply scheme at KULARA & its adjoining mouzas water supply scheme within Murarai-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte.(2nd Call) | 1098/BHM | 06/04/2023 | 275 | M/S H. R. CONSTRUCTION | 263.91 | 0 | 0 | 45
1944 | BIRBHUM | Bolpur Mechanical | Kulara Piped Water Supply Scheme. , SM/12695 | New | Providing Electro-mechanical accessories and others for KULARA piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | 2142/Bol.MD | 25/08/2023 | 585 | KAMAKHYA ENTERPRISE | 27.21 | 0 | 0 | 70
1945 | BIRBHUM | Bolpur Mechanical | Kulara Piped Water Supply Scheme. , SM/12695 | New | Supply, delivery and installation of servo motor operated copper wound line voltage corrector for Kulara water supply scheme (Amdol Pump House-III) of Murarai-II Block under Bolpur Mechanical Division, PHE Dte. | 179/BMSD(D) | 18/03/2024 | 30 | SUNIL RABIDAS | 3.18 | 0 | 0 | 100
1946 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Aligarh Water supply scheme (Phase-III) , SM/12637 | Retrofitting | Balance work for laying of pipe line including FHTC within the command area of Aligarh (Phase III) Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | 2272/BHM | 13/07/2023 | 45 | PARTHA PRATIM ACHARYYA | 32.89 | 0 | 0 | 40
1947 | BIRBHUM | Birbhum Division | JOGAI PIPED WATER SUPPLY SCHEME. , SM/12593 | New | Material Requisition To Resource Division | 1458/BHM | 25/04/2023 | 0 | Resource Division | 10.24 | 0 | 0 | 0
1948 | BIRBHUM | Bolpur Mechanical | JOGAI PIPED WATER SUPPLY SCHEME. , SM/12593 | New | WBSEDCL QUOTATION FOR JOGAI P H NO .II WS SCHEME | BP-23-24-230 | 15/01/2024 | 0 | WBSEDCL | 3.16 | 0 | 0 | 0
1949 | BIRBHUM | Bolpur Mechanical | JOGAI PIPED WATER SUPPLY SCHEME. , SM/12593 | New | WBSEDCL QUOTATION FOR JOGAI P H NO. I WS SCHEME | BP-23-24-229 | 15/01/2024 | 0 | WBSEDCL | 3.25 | 0 | 0 | 0
1950 | BIRBHUM | Birbhum Division | JOGAI PIPED WATER SUPPLY SCHEME. , SM/12593 | New | Restoration of Roads, pucca drain including Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Jogai Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division P.H.E. Dte. | 1593/BHM | 03/06/2025 | 90 | QUAZI SIRAJUL ISLAM | 95.37 | 0 | 0 | 0
1951 | BIRBHUM | Bolpur Mechanical | JOGAI PIPED WATER SUPPLY SCHEME. , SM/12593 | New | Providing Electro-mechanical accessories and others for Jagoi PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | 3303/BOL.MD | 29/09/2023 | 550 | SUNRISE ENGINEERING CORPORATION | 28.91 | 0 | 0 | 100
1952 | BIRBHUM | Bolpur Mechanical | Metegaon and Adjoining Mouzas PWSS , SM/12700 | New | Providing Electro-mechanical accessories and others for Metegaon & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | 3384/Bol.MD | 16/10/2023 | 90 | SATYAJIT GHOSH | 52.86 | 0 | 0 | 0
1953 | BIRBHUM | Birbhum Division | Metegaon and Adjoining Mouzas PWSS , SM/12700 | New | Material Requisition To Resource Division | 1398/BHM | 24/04/2023 | 0 | Resource Division | 114.57 | 0 | 0 | 0
1954 | BIRBHUM | Birbhum Division | Metegaon and Adjoining Mouzas PWSS , SM/12700 | New | Acceptance cum Work Order for Supply and delivery of Sluice Valve for Metegaon and Adjoining Mouzas PWSS under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte. | 949/BHM | 14/03/2024 | 30 | SSPR VALVE MANUFACTURING PVT LTD | 9.2 | 0 | 0 | 100
1955 | BIRBHUM | Birbhum Division | Metegaon and Adjoining Mouzas PWSS , SM/12700 | New | Different works related to water supply scheme at METEGAON & its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1085/BHM | 06/04/2023 | 1121 | M/S S.S. ENTERPRISE | 432.4 | 0 | 0 | 42
1956 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Kot Phase-II Water Supply Scheme. , SM/12661 | Retrofitting | Allied works for Providing FHTC from existing distribution system under Kot Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | 2059/BHM | 08/06/2023 | 405 | SAPTADIP CONSTRUCTION | 54.29 | 0 | 0 | 91
1957 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Haridaspur(Phase-II) Water Supply Scheme of Nalhati-I Block under Nalhati Sub Division within Birbhum Division P.H.E. Dte. , SM/12666 | Retrofitting | Extention of pipeline by HDPE pipe at Gunia and Kalyanpur habitation for providing FHTC of Haridaspur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division PHED. | 200/AE/NSD | 01/04/2022 | 45 | M/S S.N CONSTRUCTION | 3.15 | 0 | 0 | 100
1958 | BIRBHUM | Birbhum Division | NARAYANPUR PIPED WATER SUPPLY SCHEME. , SM/13625 | New | Material Requisition To Resource Division | 1421/BHM | 24/04/2023 | 0 | Resource Division | 68.68 | 0 | 0 | 0
1959 | BIRBHUM | Bolpur Mechanical | NARAYANPUR PIPED WATER SUPPLY SCHEME. , SM/13625 | New | WBSEDCL QUOTATION FOR NARAYANPUR WS SCHEME | BP-2023-2024-57 | 02/08/2023 | 0 | WBSEDCL | 4.31 | 0 | 0 | 0
1960 | BIRBHUM | Bolpur Mechanical | NARAYANPUR PIPED WATER SUPPLY SCHEME. , SM/13625 | New | WBSEDCL QUOTATION FOR NARAYAN PUR WS SCHEME | BP-2023-2024-58 | 02/08/2023 | 0 | WBSEDCL | 10.03 | 0 | 0 | 0
1961 | BIRBHUM | Birbhum Division | NARAYANPUR PIPED WATER SUPPLY SCHEME. , SM/13625 | New | Material Requisition To Resource Division | 2488/BHM | 03/09/2024 | 0 | Resource Division | 9.52 | 0 | 0 | 0
1962 | BIRBHUM | Bolpur Mechanical | NARAYANPUR PIPED WATER SUPPLY SCHEME. , SM/13625 | New | Providing Electro-mechanical accessories and others for Narayanpur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 314/Bol.MD | 24/03/2023 | 889 | RAJIB COMPANY | 28.9 | 13.32 | 46.1 | 90
1963 | BIRBHUM | Birbhum Division | NARAYANPUR PIPED WATER SUPPLY SCHEME. , SM/13625 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 250 CuM capacity O.H.R., Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at NARAYANPUR & its adjoining mouzas wate supply scheme within Sainthia Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 2238/BHM | 13/08/2024 | 565 | DILIP KUMAR MONDAL | 383.91 | 0 | 0 | 80
1964 | BIRBHUM | Birbhum Division | BHEJENA PIPED WATER SUPPLY SCHEME. , SM/12833 | New | Material Requisition To Resource Division | 1439/BHM | 25/04/2023 | 0 | Resource Division | 23.01 | 0 | 0 | 0
1965 | BIRBHUM | Birbhum Division | BHEJENA PIPED WATER SUPPLY SCHEME. , SM/12833 | New | Different works related to water supply scheme at BHEJENA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1980/BHM | 05/06/2023 | 274 | APURBA MONDAL | 205.69 | 0 | 0 | 50
1966 | BIRBHUM | Bolpur Mechanical | BHEJENA PIPED WATER SUPPLY SCHEME. , SM/12833 | New | Providing Electro-mechanical accessories and others for Bhejena PWSS at Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | 3386/Bol.MD | 16/10/2023 | 60 | INDTECH ASSOCIATES | 28.01 | 0 | 0 | 60
1967 | BIRBHUM | Bolpur Mechanical | BHEJENA PIPED WATER SUPPLY SCHEME. , SM/12833 | New | Quotation deposit for Bhejena Water Supply Scheme P/H-I in Md Bazar CCC under Bolpur Mechanical division, PHE Dte | BP-24-25-236 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.66 | 0 | 0 | 0
1968 | BIRBHUM | Bolpur Mechanical | Madhupur Water Supply Scheme , SM/13644 | New | Providing Electro-mechanical accessories and others for Madhupur PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 3596/BOL.MD | 08/12/2023 | 60 | DAS ENTERPRISE | 44.5 | 0 | 0 | 0
1969 | BIRBHUM | Birbhum Division | Madhupur Water Supply Scheme , SM/13644 | New | Continuation Work Order for Preparation & Submission of DPR for (Madhupur) Water Supply Scheme under Rampurhat-II Development Block. | 188/RSD | 12/05/2022 | 45 | ECO CARE | 4.36 | 0 | 0 | 100
1970 | BIRBHUM | Birbhum Division | Madhupur Water Supply Scheme , SM/13644 | New | Material Requisition To Resource Division | 1552/BHM | 26/04/2023 | 0 | Resource Division | 66.54 | 0 | 0 | 0
1971 | BIRBHUM | Birbhum Division | Madhupur Water Supply Scheme , SM/13644 | New | Different works related to water supply scheme at Madhupur, Khamedda & Bara-Karttikchungri and its adjoining mouzas water supply scheme within Rampurhat-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte.(2nd Call) | 4163/BHM | 30/10/2023 | 560 | M/S ASHA CONSTRUCTION | 1089.94 | 0 | 0 | 40
1972 | BIRBHUM | Birbhum Division | Madhupur Water Supply Scheme , SM/13644 | New | Material Requisition To Resource Division | 218/BHM | 24/01/2024 | 0 | Resource Division | 2.46 | 0 | 0 | 0
1973 | BIRBHUM | Bolpur Mechanical | Madhupur Water Supply Scheme , SM/13644 | New | Quotation for new service connection at Madhupur PWSS P.H No-I (Block-Rampurhat - II), Margram CCC, WBSEDCL | BP-2024-2025-62 | 05/06/2024 | 0 | WBSEDCL | 3.44 | 0 | 0 | 0
1974 | BIRBHUM | Birbhum Division | Sadanandapur piped water supply scheme. , SM/13648 | New | Material Requisition To Resource Division | 1548/BHM | 26/04/2023 | 0 | Resource Division | 9.67 | 0 | 0 | 0
1975 | BIRBHUM | Bolpur Mechanical | Sadanandapur piped water supply scheme. , SM/13648 | New | Providing Electro-mechanical accessories and others for SADANANDAPUR piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | 1500/Bol.MD | 17/07/2023 | 60 | SATYAJIT GHOSH | 27.88 | 20.74 | 74.4 | 85
1976 | BIRBHUM | Bolpur Mechanical | Sadanandapur piped water supply scheme. , SM/13648 | New | Supply, delivery and installation of servo motor operated copper wound line voltage corrector at sadanandapur W/S scheme (Asenga I & II) of Md. Bazar block under Bolpur Mechanical Division, P.H.E.Dte. | 769/BMSD(D) | 26/09/2024 | 30 | DEY ENTERPRISE | 4.33 | 0 | 0 | 100
1977 | BIRBHUM | Bolpur Mechanical | Sadanandapur piped water supply scheme. , SM/13648 | New | WBSEDCL QUOTATION FOR SADANANDAPUR PH NO-1 | BP-23-24-224 | 15/01/2024 | 0 | WBSEDCL | 0.31 | 0 | 0 | 0
1978 | BIRBHUM | Birbhum Division | SEHANA PIPED WATER SUPPLY SCHEME. , SM/12890 | New | Material Requisition To Resource Division | 1388/BHM | 24/04/2023 | 0 | Resource Division | 27.21 | 0 | 0 | 0
1979 | BIRBHUM | Bolpur Mechanical | SEHANA PIPED WATER SUPPLY SCHEME. , SM/12890 | New | New service connection at Sehana PH-II, Suri-II Block | BP-2024-2025-66 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.59 | 0 | 0 | 0
1980 | BIRBHUM | Bolpur Mechanical | SEHANA PIPED WATER SUPPLY SCHEME. , SM/12890 | New | New service connection at Sehana PH-I PWSS, under Suri-II Block. | BP-2024-2025-65 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.87 | 0 | 0 | 0
1981 | BIRBHUM | Birbhum Division | SEHANA PIPED WATER SUPPLY SCHEME. , SM/12890 | New | Different works for KASHERHAT & Sehana and its adjoining mouzas water supply scheme within SURI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 4138/BHM | 18/10/2023 | 1079 | PASCON | 975.41 | 0 | 0 | 60
1982 | BIRBHUM | Bolpur Mechanical | SEHANA PIPED WATER SUPPLY SCHEME. , SM/12890 | New | Providing Electro-mechanical accessories and others for Sehana PWSS at Suri - II Block under Bolpur Mechanical Division PHE Dte. | 2106/BOL.MD. | 22/08/2023 | 678 | STANDARD ELECTRICALS | 28.52 | 17.36 | 65.72 | 100
1983 | BIRBHUM | Central Drilling | Jashoda Piped Water Supply Scheme. , SM/12891 | New | Supply & Delivery of Consumables with other works at site for construction of Tube Well in Jashoda PWSS , TW-I, Sainthia Block, Birbhum District under CDD, PHE Dte. | 391/CMSD-I | 05/08/2022 | 15 | C.M. ENTERPRISE | 2.66 | 2.21 | 100 | 100
1984 | BIRBHUM | Central Drilling | Jashoda Piped Water Supply Scheme. , SM/12891 | New | Providing drilling crews for construction of Tube Well by departmental Rig machine in Jashoda W/S Scheme, TW-I, Sainthia Block, Birbhum District under CDD, PHE Dte. | 397/CMSD-I | 05/08/2022 | 15 | C.M. ENTERPRISE | 3.77 | 2.5 | 100 | 100
1985 | BIRBHUM | Central Drilling | Jashoda Piped Water Supply Scheme. , SM/12891 | New | Providing Tube Well materials, conforming to IS: 12818 2010 with other works at site for construction of Tube Well in Jashoda W/S Scheme, TW-I, Sainthia Block, Birbhum District under CDD, PHE Dte. | 385/CMSD-I | 05/08/2022 | 15 | C.M. ENTERPRISE | 4.18 | 3.06 | 100 | 100
1986 | BIRBHUM | Birbhum Division | Jashoda Piped Water Supply Scheme. , SM/12891 | New | Material Requisition To Resource Division | 1378/BHM | 24/04/2023 | 0 | Resource Division | 47.2 | 0 | 0 | 0
1987 | BIRBHUM | Bolpur Mechanical | Jashoda Piped Water Supply Scheme. , SM/12891 | New | Providing Electro-mechanical accessories and others for Jashoda & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 1057/Bol.MD | 08/06/2023 | 663 | SATYAJIT GHOSH | 29 | 21.81 | 75.19 | 70
1988 | BIRBHUM | Bolpur Mechanical | Jashoda Piped Water Supply Scheme. , SM/12891 | New | WBSEDCL QUOTATION FOR UTTAR JASHODA P H NO.I WS SCHEME | BP-23-24-195 | 14/12/2023 | 0 | WBSEDCL | 7.21 | 0 | 0 | 0
1989 | BIRBHUM | Birbhum Division | Jashoda Piped Water Supply Scheme. , SM/12891 | New | Different works related to water supply scheme at DEOASH, JASODA & JIUI and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 1194/BHM | 12/04/2023 | 792 | M/S. JAN MAHAMMAD | 1367.24 | 0 | 0 | 75
1990 | BIRBHUM | Birbhum Division | Barua Gopalpur Piped Water Supply Scheme. , SM/14421 | New | Different works related to water supply scheme at BARUA GOPALPUR & its adjoining mouzas water supply scheme within Murarai-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | 4162/BHM | 30/10/2023 | 274 | SUNIL RABI DAS | 781.48 | 0 | 0 | 0
1991 | BIRBHUM | Bolpur Mechanical | Barua Gopalpur Piped Water Supply Scheme. , SM/14421 | New | Providing Electro-mechanical accessories and others for BARUA GOPALPUR piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 3288/Bol.MD | 29/09/2023 | 60 | PADMA ENGINEERING CO. | 45.96 | 0 | 0 | 0
1992 | BIRBHUM | Birbhum Division | Barua Gopalpur Piped Water Supply Scheme. , SM/14421 | New | Material Requisition To Resource Division | 1579/BHM | 26/04/2023 | 0 | Resource Division | 155.49 | 0 | 0 | 0
1993 | BIRBHUM | Bolpur Mechanical | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. , SM/14424 | New | Providing Electro-mechanical accessories and others for Baraturigram PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | 3478/Bol.MD | 07/11/2023 | 60 | R. N. S. TRADING | 66.79 | 0 | 0 | 0
1994 | BIRBHUM | Birbhum Division | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. , SM/14424 | New | Material Requisition To Resource Division | 1543/BHM | 26/04/2023 | 0 | Resource Division | 222.46 | 0 | 0 | 0
1995 | BIRBHUM | Birbhum Division | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. , SM/14424 | New | Continuation Work Order for Preparation & Submission of DPR for (Bara Turigram) Water Supply Scheme (Part-C) under Mayureswar-I Development Block. | 443/RSD | 02/12/2022 | 90 | ENVIROTECH SOLUTIONS | 2.22 | 0 | 0 | 100
1996 | BIRBHUM | Birbhum Division | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. , SM/14424 | New | Continuation Work Order for Preparation & Submission of DPR for (Bara Turigram) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | 310/RSD | 08/09/2022 | 90 | ENVIROTECH SOLUTIONS | 3.58 | 0 | 0 | 100
1997 | BIRBHUM | Birbhum Division | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. , SM/14424 | New | Continuation Work Order for Preparation & Submission of DPR for (Bara Turigram) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | 422/RSD | 03/11/2022 | 90 | ENVIROTECH SOLUTIONS | 3.29 | 0 | 0 | 100
1998 | BIRBHUM | Bolpur Mechanical | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. , SM/14424 | New | Supply, delivery & Installation of Submersible Pumping Machinery and other allied work for newly sunk T/W at Baraturigram water supply scheme(Block-Mayureswar-I) under Bolpur Mechanical Division, P.H.E. Dte. | 369/BOL.MD | 06/03/2024 | 30 | RAJIB GHOSH | 8.79 | 0 | 0 | 100
1999 | BIRBHUM | Bolpur Mechanical | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. , SM/14424 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Baraturigram Piped water supply scheme(PH-III) under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 370/BOL.MD | 06/03/2024 | 30 | MASSK ENGINEERING WORKS | 7.19 | 0 | 0 | 100
2000 | BIRBHUM | Bolpur Mechanical | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. , SM/14424 | New | Quotation for new service connection at Baraturigram PWSS P/H -III under Mayureswar ccc (Block-Mayureswar -I) | BP-2024-25-260 | 18/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.28 | 0 | 0 | 0
2001 | BIRBHUM | Bolpur Mechanical | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. , SM/14424 | New | New service connection for Baraturigram PH-I Water supply scheme under Bolpur Mechanical Division, P.H.E Dte. | BP-24-25-282 | 17/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.29 | 0 | 0 | 0
2002 | BIRBHUM | Birbhum Division | Baraturi Gram Piped Water Supply Scheme under Mayureswar -I Block within Birbhum Division PHE Dte. , SM/14424 | New | Different works related to water supply scheme at BIRCHANDRAPUR, ASURLAYA, BARATURIGRAM & KANAIPUR and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | 505/BHM | 05/02/2024 | 603 | B RAI CONSTRUCTION COMPANY | 2071.77 | 0 | 0 | 20
2003 | BIRBHUM | Birbhum Division | Kanduri Piped Water Supply Scheme. , SM/14824 | New | Material Requisition To Resource Division | 1577/BHM | 26/04/2023 | 0 | Resource Division | 9.64 | 0 | 0 | 0
2004 | BIRBHUM | Birbhum Division | Kanduri Piped Water Supply Scheme. , SM/14824 | New | Material Requisition To Resource Division | 2452/BHM | 30/08/2024 | 0 | Resource Division | 12.18 | 0 | 0 | 0
2005 | BIRBHUM | Birbhum Division | Kanduri Piped Water Supply Scheme. , SM/14824 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 200 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to KANDURI & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | 2110/BHM | 29/07/2024 | 611 | PULAK KUMAR PAL | 409.54 | 0 | 0 | 35
2006 | BIRBHUM | Birbhum Division | BHETER PIPED WATER SUPPLY SCHEME , SM/14848 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHETER Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 132/BSD | 05/04/2022 | 90 | RADIANT | 3.27 | 0 | 0 | 100
2007 | BIRBHUM | Birbhum Division | BHETER PIPED WATER SUPPLY SCHEME , SM/14848 | New | Material Requisition To Resource Division | 1553/BHM | 26/04/2023 | 0 | Resource Division | 27.28 | 0 | 0 | 0
2008 | BIRBHUM | Birbhum Division | BHETER PIPED WATER SUPPLY SCHEME , SM/14848 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 150 CuM OHR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration and Providing functional household tap connection related to Piped Water supply scheme at Bheter & its adjoining mouzas within NANOOR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 2164/BHM | 05/08/2024 | 365 | PALCON | 301.86 | 0 | 0 | 0
2009 | BIRBHUM | Birbhum Division | BHETER PIPED WATER SUPPLY SCHEME , SM/14848 | New | Material Requisition To Resource Division | 2446/BHM | 30/08/2024 | 0 | Resource Division | 6.97 | 0 | 0 | 0
2010 | BIRBHUM | Central Drilling | BHETER PIPED WATER SUPPLY SCHEME , SM/14848 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2011 | BIRBHUM | Bolpur Mechanical | BHETER PIPED WATER SUPPLY SCHEME , SM/14848 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Bheter WSS (TW No. I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | 4522/BOL.MD | 20/12/2024 | 377 | SATYAJIT GHOSH | 75.08 | 0 | 0 | 50
2012 | BIRBHUM | Birbhum Division | Palashbuni Piped Water Supply Scheme (Khoyrasole Block) , SM/14851 | New | Preparation & Submission of DPR for Palashbuni & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 134/BSSD | 18/07/2022 | 45 | RADIANT | 2.72 | 0 | 0 | 100
2013 | BIRBHUM | Birbhum Division | Palashbuni Piped Water Supply Scheme (Khoyrasole Block) , SM/14851 | New | Material Requisition To Resource Division | 425/BHM | 01/02/2024 | 0 | Resource Division | 131.6 | 0 | 0 | 0
2014 | BIRBHUM | Birbhum Division | Palashbuni Piped Water Supply Scheme (Khoyrasole Block) , SM/14851 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
2015 | BIRBHUM | Birbhum Division | Palashbuni Piped Water Supply Scheme (Khoyrasole Block) , SM/14851 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
2016 | BIRBHUM | Birbhum Division | Haripur Piped Water Supply Scheme , SM/14853 | New | Preparation & Submission of DPR for Pump House cum Chlorine Room, Boundary Wall, Soil Investigation Report, Construction Over Head Reservoir (OHR), Construction of Pipe carrying structure, Service Road at Head Work Site & Land Development, FHTC Connection of Haripur & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 93/BSSD | 27/05/2022 | 45 | RADIANT | 2.22 | 0 | 0 | 100
2017 | BIRBHUM | Birbhum Division | Haripur Piped Water Supply Scheme , SM/14853 | New | Preparation & Submission of DPR for laying distribution of Haripur & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 88/BSSD | 20/05/2022 | 45 | RADIANT | 3.18 | 0 | 0 | 100
2018 | BIRBHUM | Birbhum Division | Haripur Piped Water Supply Scheme , SM/14853 | New | Material Requisition To Resource Division | 427/BHM | 01/02/2024 | 0 | Resource Division | 328.76 | 0 | 0 | 0
2019 | BIRBHUM | Birbhum Division | Haripur Piped Water Supply Scheme , SM/14853 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
2020 | BIRBHUM | Birbhum Division | Haripur Piped Water Supply Scheme , SM/14853 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
2021 | BIRBHUM | Bolpur Mechanical | Sekedda Piped Water Supply Scheme. , SM/14683 | New | Supply & Installation of Low lift Pumping Mchinery and other allied work for SEKADDAHA & Adjoining moujas water supply scheme within Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | 2145/Bol.MD | 25/08/2023 | 90 | WEST BENGAL ENGINEERING CO. | 75.81 | 0 | 0 | 0
2022 | BIRBHUM | Birbhum Division | Sekedda Piped Water Supply Scheme. , SM/14683 | New | Material Requisition To Resource Division | 1497/BHM | 25/04/2023 | 0 | Resource Division | 484.43 | 0 | 0 | 0
2023 | BIRBHUM | Bolpur Mechanical | Sekedda Piped Water Supply Scheme. , SM/14683 | New | Supply & Installation of High lift Pumping Mchinery and other allied work for SEKADDAHA & Adjoining moujas water supply scheme within Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | 2148/Bol.MD | 25/08/2023 | 90 | ORIENTAL ENGINEERING CO. | 92.33 | 0 | 0 | 10
2024 | BIRBHUM | Bolpur Mechanical | Sekedda Piped Water Supply Scheme. , SM/14683 | New | Providing Electro-mechanical accessories and others for Sekedda PWSS (New Tube Well) at Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | 367/BOL.MD | 06/03/2024 | 30 | HINDOL ROY | 13.96 | 0 | 0 | 100
2025 | BIRBHUM | Birbhum Division | Sekedda Piped Water Supply Scheme. , SM/14683 | New | Different works related to water supply scheme at SEKEDDAHA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 2139/BHM | 31/07/2024 | 730 | M/S GOUTAM DAS | 1425.93 | 0 | 0 | 25
2026 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. , SM/13371 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Narayanghati w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-2) | 1915/BHM | 24/11/2021 | 60 | TAPAN KUMAR DATTA | 82.11 | 2.75 | 32.13 | 53
2027 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. , SM/13371 | Retrofitting | Additional FHTC works from existing distribution system at Narayanghati & Bidyadhari habitation under Narayanghati mouzas within Narayanghati w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte. (Sl.No-29) | 332/RSD | 08/09/2022 | 30 | TAPAN KUMAR DATTA | 4.97 | 4.97 | 100 | 100
2028 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. , SM/13371 | Retrofitting | Additional FHTC works from existing distribution system at different mouzas ie Bhabaghati, Hatinagar, Mahalas, Bandha, Balur & Akna within Narayanghati w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte.(Sl.No-28) | 331/RSD | 08/09/2022 | 30 | TAPAN KUMAR DATTA | 4.95 | 4.95 | 100 | 100
2029 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. , SM/13371 | Retrofitting | Additional FHTC works from existing distribution system at Kalikapur,Kajipara,& Narayanghati habitations under Narayanghati mouza within Narayanghati w/s Scheme under Rampurhat Sub- Division, P.H.E. Dte.(Sl.No-27) | 330/RSD | 08/09/2022 | 30 | TAPAN KUMAR DATTA | 4.98 | 4.98 | 100 | 100
2030 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area of Narayanghati Phase-II Water Supply Scheme. , SM/13371 | Retrofitting | Providing 01 No. additional FHTC along with allied works from existing distribution system at Narayanghati (Konai Para) Jl. No. 92 under Kundala G.P. within Narayanghati W/S Scheme under Rampurhat Sub- Division, P.H.E. Dte. | 200/RSD | 28/07/2023 | 7 | ASHUTOSH BISWAS | 0.29 | 0 | 0 | 100
2031 | BIRBHUM | Bolpur Mechanical | PARULIA PIPED WATER SUPPLY SCHEME. , SM/14538 | New | Providing electro-mechanical accessories and others for Parulia & adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | 1060/Bol.MD | 08/06/2023 | 366 | CINZANO | 69.83 | 0 | 0 | 0
2032 | BIRBHUM | Birbhum Division | PARULIA PIPED WATER SUPPLY SCHEME. , SM/14538 | New | Material Requisition To Resource Division | 1402/BHM | 24/04/2023 | 0 | Resource Division | 193.54 | 0 | 0 | 0
2033 | BIRBHUM | Birbhum Division | PARULIA PIPED WATER SUPPLY SCHEME. , SM/14538 | New | Different works related to water supply scheme at PARULIA, KHANPUR & PADUMA and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1425/BHM | 25/04/2023 | 982 | BIPIN KUMAR SINGH | 2248.63 | 0 | 0 | 55
2034 | BIRBHUM | Birbhum Division | PARULIA PIPED WATER SUPPLY SCHEME. , SM/14538 | New | Laying of distribution system and road restoration at Parulia Piped Water Supply Scheme, Dubrajpur Block, under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | 2417/BHM | 18/09/2025 | 90 | BIPIN KUMAR SINGH | 68.09 | 0 | 0 | 0
2035 | BIRBHUM | Bolpur Mechanical | Paduma Piped Water Supply Scheme. , SM/14544 | New | Providing Electro-mechanical accessories and others for Paduma PWSS at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | 2075/BOL.MD. | 21/08/2023 | 90 | S.P. CONSTRUCTION | 80.24 | 0 | 0 | 40
2036 | BIRBHUM | Birbhum Division | Paduma Piped Water Supply Scheme. , SM/14544 | New | Different works related to water supply scheme at PARULIA, KHANPUR & PADUMA and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1425/BHM | 25/04/2023 | 982 | BIPIN KUMAR SINGH | 2248.63 | 0 | 0 | 55
2037 | BIRBHUM | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME , SM/14903 | New | Material Requisition To Resource Division | 1627/BHM | 28/04/2023 | 0 | Resource Division | 35.82 | 0 | 0 | 0
2038 | BIRBHUM | Bolpur Mechanical | PUNNA PIPED WATER SUPPLY SCHEME , SM/14903 | New | Supply Delivery and Installation of automatically Voltage Correction Device at Augmentation for Bolpur SD Hospital & Bolpur water supply scheme under Bolpur Mechanical Divn. PHE Dte. | 3794/BOL.MD | 12/09/2024 | 30 | EVEREST INFRATECH INC | 6.77 | 0 | 0 | 0
2039 | BIRBHUM | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME , SM/14903 | New | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for PUNNA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 305/BSD | 12/08/2022 | 90 | APEX ENGINEERING | 1.41 | 0 | 0 | 100
2040 | BIRBHUM | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME , SM/14903 | New | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for PUNNA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.¿. | 266/BSD | 11/07/2022 | 180 | APEX ENGINEERING | 4.92 | 0 | 0 | 100
2041 | BIRBHUM | Bolpur Mechanical | PUNNA PIPED WATER SUPPLY SCHEME , SM/14903 | New | Quotation for new service connection at Punna PWSS P/H- I under Ahmedpur CCC | BP-24-25-281 | 17/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.75 | 0 | 0 | 0
2042 | BIRBHUM | Central Drilling | PUNNA PIPED WATER SUPPLY SCHEME , SM/14903 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2043 | BIRBHUM | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME , SM/14903 | New | Different works related to water supply scheme at PUNNA PIPED WATER SUPPLY SCHEME(TSM/016169) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 3668/BHM | 28/08/2023 | 794 | TEKNO ENTERPRISE | 729.3 | 0 | 0 | 20
2044 | BIRBHUM | Birbhum Division | PUNNA PIPED WATER SUPPLY SCHEME , SM/14903 | New | Road restoration work for Punna Piped Water Supply Scheme, Labpur Block, under Birbhum Division, PHE Dte. | 2132/BHM | 18/08/2025 | 90 | TEKNO ENTERPRISE | 29.63 | 0 | 0 | 0
2045 | BIRBHUM | Birbhum Division | DULA SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14746 | New | Material Requisition To Resource Division | 1598/BHM | 26/04/2023 | 0 | Resource Division | 23.88 | 0 | 0 | 0
2046 | BIRBHUM | Birbhum Division | DULA SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14746 | New | Different works related to water supply scheme at DULA SAHAPUR PIPED WATER SUPPLY SCHEME (TSM017017) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 3022/BHM | 30/10/2024 | 365 | M/S S. CHOUDHURY | 597.84 | 0 | 0 | 0
2047 | BIRBHUM | Birbhum Division | DULA SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14746 | New | Continuation work for "Preparation & Submission of additional Detail Project Report (DPR) for DULASAHAPARA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 293/BSD | 29/07/2022 | 90 | APEX ENGINEERING | 1.41 | 0 | 0 | 100
2048 | BIRBHUM | Birbhum Division | DULA SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14746 | New | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for DULASAHAPARA Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 232/BSD | 10/06/2022 | 180 | APEX ENGINEERING | 4.92 | 0 | 0 | 100
2049 | BIRBHUM | Central Drilling | DULA SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14746 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2050 | BIRBHUM | Bolpur Mechanical | DULA SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14746 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Dula Sahapur PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | 326/BOL.MD | 19/02/2025 | 120 | SUNRISE ENGINEERING CORPORATION | 74.48 | 0 | 0 | 0
2051 | BIRBHUM | Birbhum Division | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area , SM/06949 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Beja W/S Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. | 1325/BHM | 16/08/2021 | 60 | PRADIP KUMAR SHARMA | 38.54 | 82.12 | 100 | 92
2052 | BIRBHUM | Birbhum Division | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area , SM/06949 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for Chuatari,Bandihat and Selhat mouzas under Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. | 16/RSD | 04/01/2022 | 30 | PRADIP KUMAR SHARMA | 4.15 | 4.14 | 100 | 100
2053 | BIRBHUM | Birbhum Division | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area , SM/06949 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for Chuatari and Kumarpur Mouzas under Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. | 17/RSD | 04/01/2022 | 30 | PRADIP KUMAR SHARMA | 4.06 | 4.05 | 100 | 100
2054 | BIRBHUM | Birbhum Division | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area , SM/06949 | Retrofitting | Allied works for Additional Laying of UPVC Pipe line for providing FHTC at Dheka and Hapina Mouzas under Beja Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | 15/RSD | 04/01/2022 | 30 | PRADIP KUMAR SHARMA | 4.27 | 4.26 | 100 | 100
2055 | BIRBHUM | Birbhum Division | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area , SM/06949 | Retrofitting | Construction of Temporary road including removing of bushes & vegetation for Beja W/S Scheme under Rampurhat Sub-Division, P.H.E. Dte. | 177/RSD | 29/04/2022 | 30 | NEEL ENTERPRISE | 1.84 | 0 | 0 | 100
2056 | BIRBHUM | Birbhum Division | Retrofitting works of Beja PWSS for providing Functional Household Tap Connection (FHTC) within command area , SM/06949 | Retrofitting | Additional laying of distribution system at Beja and Chuatari Mouzas for providing FHTC for Beja Piped Water Supply Scheme under Rampurhat sub -Division , under Birbhum Division, PHE Dte. (Sl.No.04) | 307/RSD | 08/09/2022 | 30 | GOURANGA MONDAL | 4.77 | 0 | 0 | 100
2057 | BIRBHUM | Bolpur Mechanical | MASTALI PIPED WATER SUPPLY SCHEME , SM/16275 | New | -Hiring of Luxury Car (B-S-IV)Diesel-53-C 3045. for the office of the Assistant Engineer-III/Central Mechanical Division, PHE Dte Suri,Birbhum. | 1286./AE-III | 23/08/2024 | 31 | RAJIB GHOSH | 0.15 | 0 | 0 | 0
2058 | BIRBHUM | Bolpur Mechanical | MASTALI PIPED WATER SUPPLY SCHEME , SM/16275 | New | Hiring of Car (B.S.-IV) WB-53 C 3045. for the Office of the Assistant Engineer- III, Central Mechanical Division, PHE. Dte. Under Bolpur Mechanical Division, P.H.E. Dte. | 119/AE-III | 22/01/2024 | 92 | RAJIB GHOSH | 0.44 | 0 | 0 | 100
2059 | BIRBHUM | Bolpur Mechanical | MASTALI PIPED WATER SUPPLY SCHEME , SM/16275 | New | Hiring of Car (B.S.-IV) WB-53 C 3045. for the Office of the Assistant Engineer- III, Central Mechanical Division, PHE. Dte. Under Bolpur Mechanical Division, P.H.E. Dte. | 1132./AE-III | 12/09/2023 | 92 | RAJIB GHOSH | 0.44 | 0 | 0 | 100
2060 | BIRBHUM | Bolpur Mechanical | MASTALI PIPED WATER SUPPLY SCHEME , SM/16275 | New | Hiring of Car (B.S.-IV) WB-53 C 3045. for the Office of the Assistant Engineer- III, Central Mechanical Division, PHE. Dte. Under Bolpur Mechanical Division, P.H.E. Dte. | 760/AE-III | 27/06/2023 | 92 | RAJIB GHOSH | 0.44 | 0 | 0 | 100
2061 | BIRBHUM | Bolpur Mechanical | MASTALI PIPED WATER SUPPLY SCHEME , SM/16275 | New | Hiring of Luxury Car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division. PHE. Dte. | 3397/BOL.MD | 31/10/2023 | 121 | RAJIB GHOSH | 0.57 | 0 | 0 | 100
2062 | BIRBHUM | Bolpur Mechanical | MASTALI PIPED WATER SUPPLY SCHEME , SM/16275 | New | Hiring of Car (B.S.-IV) WB-53 C 3045. for the Office of the Assistant Engineer- III, Central Mechanical Division, PHE. Dte. Under Bolpur Mechanical Division, P.H.E. Dte. | 748./AE-III | 29/04/2024 | 59 | RAJIB GHOSH | 0.28 | 0 | 0 | 100
2063 | BIRBHUM | Birbhum Division | MASTALI PIPED WATER SUPPLY SCHEME , SM/16275 | New | Continuation work Order for "Preparation & Submission of Detail Project Report (DPR) for MASTALI Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | 172/BSD | 29/04/2022 | 360 | APEX ENGINEERING | 3.16 | 0 | 0 | 100
2064 | BIRBHUM | Bolpur Mechanical | MASTALI PIPED WATER SUPPLY SCHEME , SM/16275 | New | New power connection at Mastali PWSS(P/H-I) | BP-24-25-162 | 27/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.35 | 0 | 0 | 0
2065 | BIRBHUM | Central Drilling | MASTALI PIPED WATER SUPPLY SCHEME , SM/16275 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2066 | BIRBHUM | Birbhum Division | MASTALI PIPED WATER SUPPLY SCHEME , SM/16275 | New | Different works related to water supply scheme at MASTALI Piped Water Supply Scheme (TSM/017207) within Labpur Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. (3rd Call) | 523/BHM | 05/02/2024 | 517 | PREMANANDA ROY BISWAS | 302.55 | 0 | 0 | 20
2067 | BIRBHUM | Bolpur Mechanical | Charicha Piped Water Supply Scheme. , SM/18512 | New | Supply & Installation of Low lift Pumping Mchinery and other allied work for CHARICHA & Adjoining moujas water supply scheme within Md. Bazar Block under Bolpur Mechanical Division PHE | 2146/Bol.MD | 25/08/2023 | 90 | KAMAKHYA ENTERPRISE | 31.63 | 0 | 0 | 0
2068 | BIRBHUM | Bolpur Mechanical | Charicha Piped Water Supply Scheme. , SM/18512 | New | Supply & Installation of High lift Pumping Mchinery and other allied work for CHARICHA & Adjoining moujas water supply scheme within Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | 2147/Bol.MD | 25/08/2023 | 90 | DEY ENTERPRISE | 90.92 | 0 | 0 | 0
2069 | BIRBHUM | Birbhum Division | Charicha Piped Water Supply Scheme. , SM/18512 | New | Material Requisition To Resource Division | 1622/BHM | 28/04/2023 | 0 | Resource Division | 248.27 | 0 | 0 | 0
2070 | BIRBHUM | Birbhum Division | Charicha Piped Water Supply Scheme. , SM/18512 | New | Different works related to water supply scheme at CHARICHA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. (2nd Call) | 4164/BHM | 30/10/2023 | 609 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 970.91 | 0 | 0 | 35
2071 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Rasa Phase-II water supply scheme, Block-Khoyrasole, District- Birbhum , SM/18783 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rasa in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte.(Sl. No.9) | 2587/BHM | 22/11/2022 | 60 | HIRANMAY GHOSH | 58.98 | 0 | 0 | 49
2072 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Rasa Phase-II water supply scheme, Block-Khoyrasole, District- Birbhum , SM/18783 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area of Rasa W/S Scheme in Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte. | 3895/BHM | 21/09/2023 | 60 | HIRANMAY GHOSH | 74.96 | 0 | 0 | 72
2073 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) within the command area of Rasa Phase-II water supply scheme, Block-Khoyrasole, District- Birbhum , SM/18783 | Retrofitting | Allied work for Providing Functional Household Tap Connection (FHTC) from exixting distribution system within the command area of Rasa W/S Scheme in Suri Sadar Sub-Division under Birbhum Division, PHE Dte. | 3750/BHM | 05/09/2023 | 45 | RICK CONSTRUCTION | 9.92 | 0 | 0 | 100
2074 | BIRBHUM | Bolpur Mechanical | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. , SM/18787 | Augmentation | Providing and installation of Low Lift Pumping Machineries including other works for Augmentation of Dubrajpur (Rural) Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. Block : Dubrajpur, Dist : Birbhum | 06/BOL.MD | 03/01/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 41.18 | 0 | 0 | 40
2075 | BIRBHUM | Bolpur Mechanical | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. , SM/18787 | Augmentation | Providing and installation of High Lift Pumping Machineries including others at Augmentation of Dubrajpur (Rural) Piped Water Supply Scheme under Bolpur Mechanical Division PHE Dte. Block : Dubrajpur, Dist : Birbhum. | 05/BOL.MD | 03/01/2024 | 90 | SATYAJIT GHOSH | 78.65 | 0 | 0 | 40
2076 | BIRBHUM | Bolpur Mechanical | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. , SM/18787 | Augmentation | Supply and Delivery of 100 KG , baby chlorine cylinder for different water supply scheme under Bolpur Mechanical Division PHE. Dte | 613./AE-III | 27/03/2024 | 21 | UNIVERSAL ENTERPRISES | 4.77 | 0 | 0 | 100
2077 | BIRBHUM | Birbhum Division | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. , SM/18787 | Augmentation | Allied work for Construction of Boundary wall near Mama Bhagne Pahar & Shifting of Rising main pipe line near Sal River Bridge due to pipe line beneath the NH Road under the Augmentation of Dubrajpur Rural Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. Within Birbhum Division, P.H.E. Dte | 662/BHM | 20/02/2024 | 45 | RICK CONSTRUCTION | 4.04 | 0 | 0 | 100
2078 | BIRBHUM | Bolpur Mechanical | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. , SM/18787 | Augmentation | Replacement of PDB cum MCC Panel including other allieds works at Augmentation of Dubrajpur Water Supply Scheme under Bolpur Mechanical Division, P.H.E. Dte. | 374/BOL.MD | 06/03/2024 | 30 | BIRBHUM ELECTRIC WORKS | 8.61 | 0 | 0 | 100
2079 | BIRBHUM | Bolpur Mechanical | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. , SM/18787 | Augmentation | Supply & Delivery at site of 10 H.P Submersible Pumping Machinery for Beluti PWSS at Mayureswar-II Block under Bolpur Mechanical Division, PHE Dte. | 612./AE-III | 27/03/2024 | 7 | DEY ENTERPRISE | 1.82 | 0 | 0 | 100
2080 | BIRBHUM | Bolpur Mechanical | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. , SM/18787 | Augmentation | Repairing of Gasious Chlorination system and others at Dubrajpur Aug. water supply scheme under Bolpur Mechanical Division PHE, Dte | 604./AE-III | 27/03/2024 | 21 | ORIENTAL ENGINEERING CO. | 3.84 | 0 | 0 | 100
2081 | BIRBHUM | Birbhum Division | Augmentation of Dubrajpur (Rural) and its adjoining areas to accommodate FHTC in Dubrajpur Block, District Birbhum. , SM/18787 | Augmentation | Sinking of Tubewell, Construction of OHR, Construction of Boundary wall, pump house and laying distribution system along with FHTC works at Augmentation of Dubrajpur (Rural) & its adjoining mouzas water supply scheme within Dubrajpur under Birbhum Division, PHE Dte. (2nd Call) | 524/BHM | 05/02/2024 | 574 | KOUSIK DAS | 457.67 | 0 | 0 | 64
2082 | BIRBHUM | Birbhum Division | Daskalgram Piped Water Supply Scheme , SM/18353 | New | Material Requisition To Resource Division | 1488/BHM | 25/04/2023 | 0 | Resource Division | 74.7 | 0 | 0 | 0
2083 | BIRBHUM | Birbhum Division | Daskalgram Piped Water Supply Scheme , SM/18353 | New | Work order for the work of construction of 300 Cum capacity O.H.R with soil investigation, 5.90 X 4.10 m pump room/ Chlorine room with sanitary arrangements. Laying of rising main, Distribution system with FHTC and different works related to DASKALGRAM PIPED WATER SUPPLY SCHEME (TSM/015491) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1784/BHM | 14/06/2024 | 365 | NEW APOLLO HARDWARE | 663.67 | 0 | 0 | 0
2084 | BIRBHUM | Birbhum Division | Daskalgram Piped Water Supply Scheme , SM/18353 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for DASKALGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - B) | 341/BSD | 05/09/2022 | 90 | RADIANT | 2.54 | 0 | 0 | 100
2085 | BIRBHUM | Birbhum Division | Daskalgram Piped Water Supply Scheme , SM/18353 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for DASKALGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | 255/BSD | 05/07/2022 | 90 | RADIANT | 4.73 | 0 | 0 | 100
2086 | BIRBHUM | Birbhum Division | Daskalgram Piped Water Supply Scheme , SM/18353 | New | Material Requisition To Resource Division | 2392/BHM | 27/08/2024 | 0 | Resource Division | 15.79 | 0 | 0 | 0
2087 | BIRBHUM | Central Drilling | Daskalgram Piped Water Supply Scheme , SM/18353 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2088 | BIRBHUM | Birbhum Division | LAYEKPUR PIPED WATER SUPPLY SCHEME , SM/18361 | New | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for LAYEKPUR Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 237/BSD | 17/06/2022 | 180 | APEX ENGINEERING | 4.92 | 0 | 0 | 100
2089 | BIRBHUM | Birbhum Division | LAYEKPUR PIPED WATER SUPPLY SCHEME , SM/18361 | New | Continuation work for "Preparation & Submission of additional Detail Project Report (DPR) for LAYEKPUR Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 300/BSD | 10/08/2022 | 90 | APEX ENGINEERING | 2.46 | 0 | 0 | 100
2090 | BIRBHUM | Birbhum Division | LAYEKPUR PIPED WATER SUPPLY SCHEME , SM/18361 | New | Construction of 400 Cum. OHR with Soil Investigation,Pump Room/Chlorine Room with sanitary arrangement,Laying of Rising Main Distribution System with FHTC and different works related to LAYEKPUR PIPED WATER SUPPLY SCHEME (TSM/016003) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 2771/BHM | 30/09/2024 | 365 | SS ENTERPRISE | 663.03 | 0 | 0 | 0
2091 | BIRBHUM | Central Drilling | LAYEKPUR PIPED WATER SUPPLY SCHEME , SM/18361 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2092 | BIRBHUM | Bolpur Mechanical | LAYEKPUR PIPED WATER SUPPLY SCHEME , SM/18361 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Layekpur PWSS (TW No III), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | 334/BOL.MD | 19/02/2025 | 327 | M/S. UTTAM KUMAR CHATTERJEE | 37.24 | 0 | 0 | 0
2093 | BIRBHUM | Birbhum Division | LAYEKPUR PIPED WATER SUPPLY SCHEME , SM/18361 | New | Road restoration work for Layekpur Piped Water Supply Scheme, Labpur Block, under Birbhum Division, PHE Dte. | 2242/BHM | 29/08/2025 | 90 | ARUP HAZRA | 27.91 | 0 | 0 | 0
2094 | BIRBHUM | Birbhum Division | Retrofitting works of Kalhua(Phase-II) Water Supply Scheme under Rampurhat-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07152 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Uttar Narayanpur, Kurula Ambha of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-A) | 1178 /BHM | 21/09/2020 | 60 | SUNIL RABI DAS | 41.99 | 18.58 | 100 | 79
2095 | BIRBHUM | Birbhum Division | Retrofitting works of Kalhua(Phase-II) Water Supply Scheme under Rampurhat-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07152 | Retrofitting | Additional Laying of UPVC Pipe line for providing FHTC at Jagadishpur & Marbasahar village under Kaluha PWSS within Birbhum Division, P.H.E. Dte. (Sl. No.3) | 2005/BHM | 08/12/2021 | 60 | SANJUKTA ENGINEERS | 6.82 | 6.71 | 100 | 50
2096 | BIRBHUM | Birbhum Division | Retrofitting works of Kalhua(Phase-II) Water Supply Scheme under Rampurhat-II Block for providing Functional Household Tap Connection(FHTC) within the command area of the scheme , SM/07152 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Mara Basahar, Jagadispur of Kaluha w/s Scheme at Rampurhat-II Block under Birbhum Division, PHE Dte. (Part-B) | 1179 /BHM | 21/09/2020 | 60 | SANJUKTA ENGINEERS | 32.72 | 56.01 | 200 | 100
2097 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS , SM/06734 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Laldighipara under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 03) | 353/BSSD | 25/10/2021 | 20 | SACHIN KUMAR SARKAR | 3.88 | 0 | 0 | 0
2098 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS , SM/06734 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Malian, Joka & Kamalpur of Tilpara w/s Scheme at Suri-I Block within Suri Sadar Sub Division under Birbhum Division, PHE Dte. (Sl. No.1) | 1420/BHM | 04/11/2020 | 45 | B.M.SARKAR | 17.18 | 29.65 | 186.33 | 97
2099 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS , SM/06734 | Retrofitting | Providing functional house tap connection (FHTC) from existing distribution system within the command area of Tilpara Water Supply Scheme. | 1707/BHM | 23/12/2020 | 60 | RAJ KUMAR DAS | 47.57 | 47.86 | 175.66 | 65
2100 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS , SM/06734 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Araipur of Tilpara w/s Scheme at Suri I Block within Suri Sadar Sub Division under Birbhum Division, PHE Dte. (2nd Call) (Sl. No.22) | 1713/BHM | 23/12/2020 | 45 | PRANAB KUMAR GHOSH | 21.28 | 37.05 | 181.59 | 100
2101 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS , SM/06734 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Kalpatarupally under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl.No. -02) | 336/BSSD | 23/09/2021 | 20 | M/S SARADA CONSTRUCTION. | 4.02 | 0 | 0 | 100
2102 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS , SM/06734 | Retrofitting | Providing additional Functional Household Tap Connection (FHTC) from existing distribution system in Habitation of Laldighipara under Araipur Mouza (JL No. - 6) under Suri- I Block, within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub Division within Birbhum Division, P.H.E Dte. (Sl. No. - 03) | 353/BSSD. | 25/10/2021 | 20 | SACHIN KUMAR SARKAR | 3.88 | 0 | 0 | 100
2103 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS , SM/06734 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tilpara w/s Scheme (Left out House Hold) in Suri Sadar Sub-Division under Birbhum Division, PHE Dte.¿(Sl. No.1) | 1506/BHM | 09/09/2021 | 60 | RAJKUMAR DAS | 39.43 | 0 | 0 | 50
2104 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Tilpara PWSS , SM/06734 | Retrofitting | Providing Functional Household Tap Connection (FHTC)from existing distribution system in habitaiton of Kamapur Nutunpara under Kamalpur Mouza (Jl. NO.4) under Suri-I Block within the command area of Tilpara Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.01) | 191/BSSD | 02/06/2021 | 20 | BAMDEB CONSTRUCTION | 4.92 | 4.91 | 100 | 0
2105 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) , SM/06735 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area (Moldihi, Koma, Kanslpai, Muradpur) of Chatra-Koma w/s Scheme at Suri-II Block under Birbhum Division, PHE Dte. | 1174/BHM | 21/09/2020 | 60 | SYED KHORSID ALAM | 32.84 | 0 | 0 | 0
2106 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) , SM/06735 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area (Januri, Uttar Metegram, Rajnagar, Shibpur) of Chatra-Koma w/s Scheme at Suri-II Block under Birbhum Division, PHE Dte. (Sl. No.3) | 1282/BHM | 01/10/2020 | 45 | ISLAM CONSTRUCTION | 12.08 | 20.07 | 173.68 | 100
2107 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) , SM/06735 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area (Moldihi, Koma, Kanslpai, Muradpur) of Chatra-Koma w/s Scheme at Suri-II Block under Birbhum Division, PHE Dte. | 1174/BHM | 21/09/2020 | 60 | SYED KHORSID ALAM | 32.84 | 49.09 | 153.14 | 100
2108 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) , SM/06735 | Retrofitting | Extension of pipe line for Providing Functional Household Tap Connection (FHTC) at Kanspai (JL No.82) Muradpur Adibasipara (Jl. No.83), Maldihi Adibashipara (Sl. No.80) & Khanna (Jl. No.) Villages of different locations from existing distribution system within the command area of Chatra-Koma Piped Water Supply Scheme at Suri-II Block under Birbhum Sadar Sub-Division within Birbhum Division, PHE Dte. (Sl. No.09) | 71/ BSSD | 26/02/2021 | 15 | SYED KHORSID ALAM | 3.82 | 7.8 | 100 | 100
2109 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) , SM/06735 | Retrofitting | Providing balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chatra-Koma Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E Dte. (Sl. No. - 05) | 91/BSSD | 27/05/2022 | 20 | INDRAJIT MONDAL | 4.05 | 3.37 | 100 | 92
2110 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) , SM/06735 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area (Januri, Uttar Metegram, Rajnagar, Shibpur) of Chatra-Koma w/s Scheme at Suri-II Block under Birbhum Division, PHE Dte. (Sl. No.3) | 1281/BHM | 07/10/2020 | 45 | NUR MOBINUL ISLAM | 12.08 | 2.62 | 100 | 75
2111 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) , SM/06735 | Retrofitting | Extension of pipe line for Providing Functional Household Tap Connection (FHTC) at Kanspai( JL No. - 82) Muradpur Adibasipara (JL No. 83), Maldihi Adibasipara (JL No.-80) & Khanna (JL No.-) Villages of different locations from existing distribution system within the command area of Chatra-Koma Piped Water Supply Scheme at Suri-II Block under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte. (Sl. No. - 09) | 71/BSSD. | 26/02/2021 | 15 | SYED KHORSID ALAM | 3.82 | 0 | 0 | 0
2112 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Chatra-Koma PWSS (Phase-I) , SM/06735 | Retrofitting | Laying Distribution pipeline from MSK school towards main road under Charta- Coma Piped Water Suply Scheme under Birbhum Sadar Sub Division, P.H.E Dte. within Birbhum Division PHE Dte. | 1637/BHM | 02/05/2023 | 30 | SUBHANKAR ROY | 5.3 | 0 | 0 | 100
2113 | BIRBHUM | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme , SM/09437 | Augmentation | Annual Mtc. of pipeline (Distribution and rising main) for the water supply schemes related to the daily supply of water to the consumers under Birbhum Division, PHE Dte.¿ Purandarpur W/S Scheme (Sl. No.-06) | 1826/BHM | 31/12/2020 | 365 | PRANAB KUMAR MONDAL | 2.91 | 0 | 0 | 0
2114 | BIRBHUM | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme , SM/09437 | Augmentation | Allied work for Laying distribution system for proposed augmentation scheme for Purandarpur Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | 2076/BHM | 08/06/2023 | 60 | M/S GOUTAM DAS | 56.35 | 0 | 0 | 100
2115 | BIRBHUM | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme , SM/09437 | Augmentation | Material Requisition To Resource Division | 489/BHM | 02/03/2022 | 0 | Resource Division | 25.74 | 0 | 0 | 0
2116 | BIRBHUM | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme , SM/09437 | Augmentation | Material Requisition To Resource Division | 215/BHM | 02/02/2022 | 0 | Resource Division | 16.6 | 0 | 0 | 0
2117 | BIRBHUM | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme , SM/09437 | Augmentation | Material Requisition To Resource Division | 2290/BHM | 20/10/2022 | 0 | Resource Division | 5.93 | 0 | 0 | 0
2118 | BIRBHUM | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme , SM/09437 | Augmentation | Material Requisition To Resource Division | 1115/BHM | 10/04/2023 | 0 | Resource Division | 10.28 | 0 | 0 | 0
2119 | BIRBHUM | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme , SM/09437 | Augmentation | Construction of 500cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Purandarpur W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte.(As per Departmental Drawing) | 1215/BHM | 12/04/2023 | 275 | M/S GOUTAM DAS | 128.59 | 0 | 0 | 100
2120 | BIRBHUM | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme , SM/09437 | Augmentation | Trial Bore and Sinking of 200 mm dia. tubewell (02 nos.) 125 m. Deep fitted with M.S.E.R.W. Housing pipe and Fibre Glass Strainer on the river bank of Mayurakshi for the Augmentation of Purandarpur Piped Water Supply Scheme under Birbhum Sadar Sub-Division PHE Dte. with Birbhum Division, P.H.E. Dte. | 2269/BHM | 13/07/2023 | 30 | PRANAB KUMAR MONDAL | 5.6 | 0 | 0 | 100
2121 | BIRBHUM | Bolpur Mechanical | Augmentation of Purandarpur Piped Water Supply Scheme , SM/09437 | Augmentation | Replacement of voltage correction device at Purandarpur PH-I water supply scheme under under Bolpur Mechanical Division, PHE Dte.(Aug. of Purandarpur W/S Scehem) | 1360/AE-III | 17/10/2023 | 15 | QUAZI NOZRUL ISLAM | 2.05 | 0 | 0 | 100
2122 | BIRBHUM | Bolpur Mechanical | Augmentation of Purandarpur Piped Water Supply Scheme , SM/09437 | Augmentation | Additional works for installation of submersible pumping machineries at Aug. of purandarpur water supply scheme Block- Suri-II under Bolpur Mechanical Division, PHE Dte. | 1880/BOL.MD | 05/08/2024 | 45 | SATYAJIT GHOSH | 7.27 | 0 | 0 | 100
2123 | BIRBHUM | Bolpur Mechanical | Augmentation of Purandarpur Piped Water Supply Scheme , SM/09437 | Augmentation | New service connection at aug. of Purandarpur PWSS. | BP-23-24-358 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.59 | 0 | 0 | 0
2124 | BIRBHUM | Birbhum Division | Augmentation of Purandarpur Piped Water Supply Scheme , SM/09437 | Augmentation | Laying distribution system for proposed augmentation scheme for purandarpur piped water supply scheme under Birbhum Sadar sub division PHE Dte. | 1026/BHM | 12/05/2022 | 1352 | M/S GOUTAM DAS | 387.66 | 290.54 | 74.95 | 95
2125 | BIRBHUM | Bolpur Mechanical | Augmentation of Purandarpur Piped Water Supply Scheme , SM/09437 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Purandarpur water supply scheme under Bolpur Mechanical Division PHE Dte. | 716/Bol.MD | 19/04/2023 | 866 | SATYAJIT GHOSH | 24.44 | 16.88 | 78.92 | 100
2126 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area DERIAPUR WATER SUPPLY SCHEME of Sainthia Block under Birbhum Division, PHE Dte. , SM/08894 | Retrofitting | Trial Bore and Sinking of 200 mm dia. 2(Two) nos.tubewell 30m. (avg.) depth fitted with PVC pipes & fittings Schedule 80 (medium duty) and Fibre Glass Strainer on the river bank of Mayurakshi under Deriapur Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, PHE Dte. (Sl. No. - 01) | 403/BSSD | 14/12/2021 | 15 | BHABATARAN SADHU | 4.53 | 0 | 0 | 100
2127 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area DERIAPUR WATER SUPPLY SCHEME of Sainthia Block under Birbhum Division, PHE Dte. , SM/08894 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Deriapur Water Supply Scheme within Birbhum Sadar Sub-Division under Birbhum Division, PHE Dte.¿ (Sl. No.1) | 738/BHM | 04/04/2022 | 60 | M/S GOUTAM DAS | 96 | 60.27 | 72.48 | 80
2128 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area DERIAPUR WATER SUPPLY SCHEME of Sainthia Block under Birbhum Division, PHE Dte. , SM/08894 | Retrofitting | Laying of Distribution Main pipeline through road crossing of Suri-Sainthia via Patelnagar Road by adopting Jack Pushing method at Gournagar (Node 179-180), Punur (Node 53-54), Dhaikota (Node 2-3) and Bagdola More (Node 71-72) under Deriapur Piped Water Supply Scheme at Sainthia Development Block within Birbhum Division, PHE Dte. (SL.No.3) | 503/BHM | 02/03/2022 | 45 | M/S GOUTAM DAS | 28.33 | 0 | 0 | 0
2129 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area DERIAPUR WATER SUPPLY SCHEME of Sainthia Block under Birbhum Division, PHE Dte. , SM/08894 | Retrofitting | Supply and delivery of Sluice Valve & Duck Foot Bend for Deriapur W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.¿ (Sl. No.3) | 378/BHM | 21/02/2022 | 15 | SSPR VALVE MANUFACTURING PVT LTD | 6.59 | 0 | 0 | 100
2130 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area DERIAPUR WATER SUPPLY SCHEME of Sainthia Block under Birbhum Division, PHE Dte. , SM/08894 | Retrofitting | Balance work for for Uttar Gobindapur area, Connecting pipe line, rest portion laying of pipe line for Functional Household Tap Connection (FHTC) of Deriapur Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E. Dte. within Birbhum Division, P.H.E. Dte. | 1979/BHM | 05/06/2023 | 45 | PINTU KHAN | 39.24 | 0 | 0 | 62
2131 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area DERIAPUR WATER SUPPLY SCHEME of Sainthia Block under Birbhum Division, PHE Dte. , SM/08894 | Retrofitting | Structural Bridge for 200 mm dia. pipe line at Bagdola village under Deriapur Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division, P.H.E. Dte. (Sl. No. - 09) | 221/BSSD | 21/09/2022 | 30 | M/S GOUTAM DAS | 4.01 | 0 | 0 | 100
2132 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. , SM/08891 | Retrofitting | Construction of Switch Room Cum Chlorine Room 3.60 mtr. x 3.00 mtr. Size at 2nd Tube well site of CHAUHATTA Piped Water Supply Scheme at Labpur Block under Bolpur Sub-Division , P.H.E Dte. within Birbhum Division P.H.E. Dte. (Pump House No. - 2). (Sl. No.: 8) | 328/BSD | 01/09/2021 | 60 | NAZIR HOSSAIN | 4.09 | 0 | 0 | 100
2133 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. , SM/08891 | Retrofitting | Supply and delivery of 80mm dia Sluice Valves, including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Chowhatta Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 04). | 37/BSD | 02/02/2022 | 15 | MAKALI ENGINEERING CORPORATION | 0.65 | 0 | 0 | 100
2134 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. , SM/08891 | Retrofitting | Construction of Switch Room Cum Chlorine Room 3.60mtr. x 3.00mtr. Size under Piped Water Supply Scheme for CHAUHATTA Water Supply Scheme at Labpur Block under Bolpur Sub-Division, P.H.E Deptt. within Birbhum Division P.H.E. Deptt.. ( Pump House No.- III). (Sl. No.: 02). | 256/BSD | 07/07/2022 | 60 | NAZIR HOSSAIN | 4.05 | 0 | 0 | 100
2135 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. , SM/08891 | Retrofitting | Repairing of existing road and construction of new approach road towards O.H.R. in front of Head Works site of Chowhatta Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 03) | 458/BSD | 13/12/2021 | 30 | NAZIR HOSSAIN | 1.94 | 0 | 0 | 100
2136 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. , SM/08891 | Retrofitting | Laying of Distribution Pipeline with FHTC work at Chowhatta village of Chowhatta Water Supply Scheme due to CMRO Grievance (Grievance Lodging Date: 15.12.2023, Complainant Name: Sk Indadul) in Chowhatta Mohodori - I Gram Panchayet under Bolpur Sub-Division within Birbhum Division, PHE. Dte | 166/BSD | 15/02/2024 | 7 | SK.RUHUL AMIN | 0.96 | 0 | 0 | 100
2137 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command areaof CHAUHATA WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. , SM/08891 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of Chowhata Water Supply Scheme within Bolpur Sub-Division under Birbhum Division, PHE Dte. | 1850/BHM | 30/08/2022 | 60 | JDJ ENTERPRISE. A UNIT OF JDJ TRADERS PRIVATE LIMITED | 99.46 | 0 | 0 | 80
2138 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Dantura PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09364 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Dantura under Dantura Water Supply Scheme within Birbhum Division, PHE Dte¿ (Sl. No.5) | 2005/BHM | 15/09/2022 | 60 | PRAVAT SARKAR | 95.17 | 93.87 | 100 | 100
2139 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Dantura PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09364 | Retrofitting | Construction of Pump House of 5.40mtr. X 3.6mtr. Size with sanitary and water supply arrangements at DANTURA PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 16/AE/NSD | 17/01/2022 | 60 | SHIB GANGA CONSTRUCTION | 4.99 | 0 | 0 | 100
2140 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Dantura PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09364 | Retrofitting | Sinking of 200mm 90 m. deep Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at Head Work site of Dantura Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 130/AE/NSD | 09/03/2022 | 30 | SUNIL RABI DAS | 4.8 | 0 | 0 | 100
2141 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Dantura PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09364 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Dantura Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | 1014/BHM | 30/03/2023 | 60 | NUR MOBINUL ISLAM | 64.15 | 0 | 0 | 70
2142 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09365 | Retrofitting | Construction of Boundary Wall at 2nd Pump House Site for Bara- Akalpur PWSS under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 23/RSD | 04/01/2022 | 45 | INDRAJIT SAHA | 3.23 | 0 | 0 | 100
2143 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09365 | Retrofitting | Laying of HDPE Pipe line on right side of Sainthia Sultanpur Road for Bara Akalpur, Gumta & Akalpur mouzas for providing FHTC under Bara-Akalpur Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | 129/RSD | 11/03/2022 | 30 | M/S UNIT CONSTRUCTION | 4.98 | 3.82 | 100 | 100
2144 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09365 | Retrofitting | Laying of HDPE 160 mm dia distribution line near Head work site in Pachim Panchberia mouza under Bara Akulpur water supply scheme under Rampurhat sub division under Birbhum Division PHE Dte. | 111/RSD | 07/03/2022 | 30 | ALPHA PROJECT | 4.68 | 0 | 0 | 100
2145 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09365 | Retrofitting | Laying of Distribution Main pipeline through crossing of PMGSY road within Pachim Panchberia mouza (in front of Kundala K.S.G.C High School) Western side by adopting Jack Pushing method for Bara Akulpur PWSS under Rampurhat Sub-Division, PHE Dte. | 114/RSD | 07/03/2022 | 15 | M/S UNIT CONSTRUCTION | 4.34 | 0 | 0 | 100
2146 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09365 | Retrofitting | Laying of Distribution Main pipeline through crossing of PMGSY road within Pachim Panchberia mouza (in front of Kundala K.S.G.C High School) Eastern side by adopting Jack Pushing method for Bara Akulpur PWSS under Rampurhat Sub-Division, PHE Dte. | 113/RSD | 07/03/2022 | 15 | M/S UNIT CONSTRUCTION | 4.96 | 0 | 0 | 0
2147 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09365 | Retrofitting | Laying of HDPE Pipe line for Akalpur, Gumta mouzas for providing FHTC under Bara Akalpur Piped Water Supply Scheme under Rampurhat Sub-Division, under Birbhum Division, PHE Dte. | 127/RSD | 11/03/2022 | 30 | M/S UNIT CONSTRUCTION | 4.95 | 4.68 | 100 | 100
2148 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09365 | Retrofitting | Allied FHTC works along with laying pipe lines at diff mouzas within BARA-AKULPUR w/s Scheme under Rampurhat Sub- Division ,Birbhum Divition P.H.E. Dte | 1132/BHM | 10/04/2023 | 45 | ABUL HASNAT | 6.97 | 6.93 | 100 | 100
2149 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09365 | Retrofitting | Laying of HDPE Pipe line for Bara Akalpur & Benegram mouzas for providing FHTC under Bara-Akalpur Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | 128/RSD | 11/03/2022 | 30 | M/S UNIT CONSTRUCTION | 4.97 | 4.69 | 100 | 100
2150 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09365 | Retrofitting | Laying of HDPE Pipe line for ,Kundala, Itahata etc mouzas for providing FHTC under Bara-Akalpur Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | 126/RSD | 11/03/2022 | 30 | M/S UNIT CONSTRUCTION | 4.94 | 4.68 | 100 | 100
2151 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09365 | Retrofitting | Material Requisition To Resource Division | 217/BHM | 02/02/2022 | 0 | Resource Division | 10.17 | 0 | 0 | 0
2152 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09365 | Retrofitting | Laying of Rising main with DI K9 for inter connection & bypass arrangement of DI pipe line for Bara- Akalpur PWSS under Rampurhat sub division under Birbhum Division, PHE Dte. | 26/RSD | 04/01/2022 | 30 | TAPAS KUMAR SARKHEL | 1.76 | 0 | 0 | 100
2153 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional house hold tap connection (FHTC) under Bara Akalpur PWSS within Mayureswar-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09365 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bara Akalpur Water Supply Scheme within Rampurhat Sub-Division Birbhum Division, PHE Dte. (Sl. No.2) | 748/BHM | 05/04/2022 | 1060 | TAPAS KUMAR SARKHEL | 80.34 | 57.37 | 71.65 | 100
2154 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum , SM/08171 | Retrofitting | Additional Supply of UPVC Pipe & strainer 200 mm dia for Sinking of 09 Nos 200mm dia. X 30 mtr deep River bed Tube Well including trial bore for Puranagram Piped Water Supply Scheme under Rampurhat Sub Division within Birbhum Division, PHE Dte. | 118/RSD | 11/03/2022 | 30 | RUBAL CONSTRACTION | 1.48 | 0 | 0 | 0
2155 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum , SM/08171 | Retrofitting | Balance Work for Construction of High Lift Pump House Construction of Ramp,PCC Apporch Road at CWR site for Puranagram Piped Water Supply Scheme under Rampurhat Sub-Division withen Birbhum Division, P.H.E. Dte. | 19/RSD | 04/01/2022 | 30 | GOLAM RASUL | 3.88 | 0 | 0 | 100
2156 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum , SM/08171 | Retrofitting | Construction of Boundary Wall at Puranagram Piped Water Supply Scheme under under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 1636/BHM | 15/12/2020 | 60 | GOLAM RASUL | 4.27 | 0 | 0 | 35
2157 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum , SM/08171 | Retrofitting | Construction of Boundary Wall at Puranagram CWR Site for Puranagram Piped Water Supply Scheme under Md. Bazar block under Rampurhat Sub-Division within Birbhum Division, PHE Dte. | 20/RSD | 11/01/2021 | 60 | GOLAM RASUL | 4.05 | 0 | 0 | 100
2158 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) under Puranagram (Phase-I)PWSS within Rampurhat-I Block, Dist.- Birbhum , SM/08171 | Retrofitting | ¿Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Puratangram Water Supply Scheme within Rampurhat Sub-Division under Birbhum Division, PHE Dte¿(Sl. No.14) | 134/BHM | 25/01/2021 | 60 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 82.45 | 65.7 | 80.01 | 100
2159 | BIRBHUM | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme , SM/10313 | Augmentation | Supply and delivery of Sluice Valve for Augmentation of Ahmadpur W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-1) | 4292/BHM | 10/11/2023 | 30 | MAKALI ENGINEERING CORPORATION | 9 | 0 | 0 | 100
2160 | BIRBHUM | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme , SM/10313 | Augmentation | Material Requisition To Resource Division | 913/BHM | 26/04/2022 | 0 | Resource Division | 4.97 | 0 | 0 | 0
2161 | BIRBHUM | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme , SM/10313 | Augmentation | Material Requisition To Resource Division | 3274/BHM | 27/07/2023 | 0 | Resource Division | 0.34 | 0 | 0 | 0
2162 | BIRBHUM | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme , SM/10313 | Augmentation | Continuation work order for Supply and delivery of Sluice Valve for Augmentation of Ahmadpur W/S Scheme under Birbhum Division, P.H.E. Dte. including loading, carriage and unloading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, P.H.E. Dte.(Sl No-1) | 500/BHM | 02/02/2024 | 30 | MAKALI ENGINEERING CORPORATION | 9 | 0 | 0 | 100
2163 | BIRBHUM | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme , SM/10313 | Augmentation | Laying distribution system including FHTC for proposed augmentation scheme for Ahmedpur Piped Water Supply Scheme, Sainthia Block, under Birbhum Division, PHE Dte. (Sl. No.6) | 1158/BHM | 23/05/2022 | 496 | PASCON | 445.38 | 419.67 | 94.23 | 95
2164 | BIRBHUM | Bolpur Mechanical | Augmentation of Ahmedpur Piped Water Supply Scheme , SM/10313 | Augmentation | Providing Electro-mechanical accessories and others for Augmentation of Ahmedpur water supply scheme under Bolpur Mechanical Division PHE Dte. | 717/Bol.MD | 19/04/2023 | 45 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 27.19 | 0 | 0 | 0
2165 | BIRBHUM | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme , SM/10313 | Augmentation | Construction of 700cum capacity 20mtr. Staging height RCC Over Head Reservoir over RCC Raft foundation including pipe connection & allied works for augmentation of Ahmedpur W/S Scheme under Birbhum Sadar Sub Division within Birbhum Division, PHE Dte. | 1103/BHM | 10/04/2023 | 275 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 152 | 0 | 0 | 20
2166 | BIRBHUM | Birbhum Division | Augmentation of Ahmedpur Piped Water Supply Scheme , SM/10313 | Augmentation | Trial Bore and Sinking of 200 mm dia. tubewell (02 no.) 170 m. Deep fitted with M.S.E.R.W. Housing pipe and Fibre Glass Strainer on the river bank of Mayurakshi for the Augmentation of Ahmedpur Piped Water Supply Scheme under Birbhum Sadar Sub-Division PHE Dte. with Birbhum Division, P.H.E. Dte. | 1981/BHM | 05/06/2023 | 524 | NEEL ENTERPRISE | 6.94 | 0 | 0 | 100
2167 | BIRBHUM | Birbhum Division | PURBA SIUR PIPED WATER SUPPLY SCHEME. , SM/12598 | New | Material Requisition To Resource Division | 1414/BHM | 24/04/2023 | 0 | Resource Division | 18.66 | 0 | 0 | 0
2168 | BIRBHUM | Bolpur Mechanical | PURBA SIUR PIPED WATER SUPPLY SCHEME. , SM/12598 | New | New service connection at Purba Siur PH-II W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-2023-24-318 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.77 | 0 | 0 | 0
2169 | BIRBHUM | Bolpur Mechanical | PURBA SIUR PIPED WATER SUPPLY SCHEME. , SM/12598 | New | New service connection at Purba Siur PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-2023-24-317 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.95 | 0 | 0 | 0
2170 | BIRBHUM | Birbhum Division | PURBA SIUR PIPED WATER SUPPLY SCHEME. , SM/12598 | New | Different works related to water supply scheme at PASCHIM NAOPARA, PHULUR & PURBA SIUR its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | 2262/BHM | 12/07/2023 | 993 | B RAI CONSTRUCTION COMPANY | 1402.44 | 0 | 0 | 45
2171 | BIRBHUM | Bolpur Mechanical | PURBA SIUR PIPED WATER SUPPLY SCHEME. , SM/12598 | New | Providing Electro-mechanical accessories and others for Purba Siur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2084/Bol.MD | 22/08/2023 | 802 | STANDARD ELECTRICALS | 29.66 | 19.52 | 65.79 | 80
2172 | BIRBHUM | Bolpur Mechanical | PURBA SIUR PIPED WATER SUPPLY SCHEME. , SM/12598 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Purba Siur PWSS under Sainthia Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte | 530/BOL.MD | 14/03/2024 | 307 | RN ELECTRO POWER PVT. LTD. | 7.54 | 0 | 0 | 100
2173 | BIRBHUM | Birbhum Division | DALIMA PIPED WATER SUPPLY SCHEME. , SM/12592 | New | Material Requisition To Resource Division | 1438/BHM | 25/04/2023 | 0 | Resource Division | 36.19 | 0 | 0 | 0
2174 | BIRBHUM | Birbhum Division | DALIMA PIPED WATER SUPPLY SCHEME. , SM/12592 | New | Different works related to water supply scheme at Dalima, Kahinagar & Dumurgram and its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1423/BHM | 25/04/2023 | 1090 | AKASH CONSTRUCTION | 1377.29 | 0 | 0 | 16
2175 | BIRBHUM | Bolpur Mechanical | DALIMA PIPED WATER SUPPLY SCHEME. , SM/12592 | New | Providing Electro-mechanical accessories and others for Dalima PWSS at Murarai - I Block under Bolpur Mechanical Division PHE Dte. | 3285/BOL.MD | 29/09/2023 | 550 | S.K.ELECTRICALS | 30.88 | 0 | 0 | 70
2176 | BIRBHUM | Birbhum Division | ANDHARGRAM PIPED WATER SUPPLY SCHEME. , SM/12676 | New | Material Requisition To Resource Division | 1519/BHM | 26/04/2023 | 0 | Resource Division | 17.4 | 0 | 0 | 0
2177 | BIRBHUM | Bolpur Mechanical | ANDHARGRAM PIPED WATER SUPPLY SCHEME. , SM/12676 | New | Providing Electro-mechanical accessories and others for Andhargram PWSS at Md. Bazar Block under Bolpur Mechanical Division PHE Dte. | 1497/Bol.MD | 17/07/2023 | 60 | WEST BENGAL ENGINEERING CO. | 27.21 | 0 | 0 | 80
2178 | BIRBHUM | Bolpur Mechanical | ANDHARGRAM PIPED WATER SUPPLY SCHEME. , SM/12676 | New | WBSEDCL QUOTATION FOR ANDHARGRAM P H NO 2 WS SCHEME | BP-23-24-174 | 07/12/2023 | 0 | WBSEDCL | 3.65 | 0 | 0 | 0
2179 | BIRBHUM | Bolpur Mechanical | ANDHARGRAM PIPED WATER SUPPLY SCHEME. , SM/12676 | New | WBSEDCL quotation for Andhargram ws scheme | BP-23-24-173 | 07/12/2023 | 0 | WBSEDCL | 4.58 | 0 | 0 | 0
2180 | BIRBHUM | Birbhum Division | ANDHARGRAM PIPED WATER SUPPLY SCHEME. , SM/12676 | New | Different works related to water supply scheme at ANDHARGRAM & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 1191/BHM | 12/04/2023 | 477 | NISITH BARAN SARKAR | 255.87 | 0 | 0 | 65
2181 | BIRBHUM | Birbhum Division | Dakshin Kasila Piped Water Supply Scheme. , SM/12686 | New | Material Requisition To Resource Division | 1442/BHM | 25/04/2023 | 0 | Resource Division | 16.44 | 0 | 0 | 0
2182 | BIRBHUM | Bolpur Mechanical | Dakshin Kasila Piped Water Supply Scheme. , SM/12686 | New | Quotation deposit for empowering Dakshin Kashila P/H-I Scheme in Murarai CCC under Bolpur Mechanical Division, PHE Dte | BP-2024-2025-19 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.03 | 0 | 0 | 0
2183 | BIRBHUM | Bolpur Mechanical | Dakshin Kasila Piped Water Supply Scheme. , SM/12686 | New | Quotation deposit for empowering Dakshin Kashila P/H-II Scheme in Murarai CCC under Bolpur Mechanical Division, PHE Dte | BP-2024-2025-18 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.92 | 0 | 0 | 0
2184 | BIRBHUM | Bolpur Mechanical | Dakshin Kasila Piped Water Supply Scheme. , SM/12686 | New | Providing Electro-mechanical accessories and others for DAKSHIN KASHILA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 3290/Bol.MD | 29/09/2023 | 550 | S.K.ELECTRICALS | 30.47 | 0 | 0 | 65
2185 | BIRBHUM | Birbhum Division | Madhura and Adjoining mouzas PWSS , SM/12671 | New | Material Requisition To Resource Division | 1471/BHM | 25/04/2023 | 0 | Resource Division | 113.39 | 0 | 0 | 0
2186 | BIRBHUM | Bolpur Mechanical | Madhura and Adjoining mouzas PWSS , SM/12671 | New | Providing Electro-mechanical accessories and others for MADHURA piped water supply scheme, Nalhati - I block, under Bolpur Mechanical Division PHE Dte. | 3562/BOL.MD | 04/12/2023 | 60 | INDRANI ENTERPRISE | 27.43 | 0 | 0 | 80
2187 | BIRBHUM | Bolpur Mechanical | Madhura and Adjoining mouzas PWSS , SM/12671 | New | ,Operation and Guarding of pumping machinery and others at Madhura Piped Water supply Scheme (Pump House No-I(Block- Nalhati-I) under Bolpur Mechanical Division,P.H.E Dte | 1077./AE-III | 29/07/2024 | 31 | INDRANI ENTERPRISE | 0.3 | 0 | 0 | 0
2188 | BIRBHUM | Bolpur Mechanical | Madhura and Adjoining mouzas PWSS , SM/12671 | New | Operation and Guarding of pumping machinery and others at Madhura Piped water supply scheme,(Pump House No-II)Block; Nalhati-I) under Bolpur Mechanical Division,P.H.E Dte. | 1078./AE-III | 29/07/2024 | 31 | INDRANI ENTERPRISE | 0.3 | 0 | 0 | 0
2189 | BIRBHUM | Bolpur Mechanical | Madhura and Adjoining mouzas PWSS , SM/12671 | New | WBSEDCL QUOTATION FOR MODHURA W S P H NO I WS SCHEME | BP-23-24-239 | 29/01/2024 | 0 | WBSEDCL | 2.79 | 0 | 0 | 0
2190 | BIRBHUM | Bolpur Mechanical | Madhura and Adjoining mouzas PWSS , SM/12671 | New | WBSEDCL QUOTATION FOR MODHURA P H NO 2 | BP-23-24-238 | 29/01/2024 | 0 | WBSEDCL | 0.23 | 0 | 0 | 0
2191 | BIRBHUM | Birbhum Division | Madhura and Adjoining mouzas PWSS , SM/12671 | New | Different works related to water supply scheme at MADHURA & PAIKPARA PWSS its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 1173/BHM | 12/04/2023 | 995 | SK ABDUL HALIM | 921.73 | 0 | 0 | 90
2192 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR NISHPARUN AND OTHER 4 NOS. MOUZAS UNDER RAMPURHAT-II BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11901 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 95.27 | 91.44 | 92
2193 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR UTTAR BHAGABATIPUR AND OTHER 8 NOS. MOUZAS UNDER MAYURESWAR-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/12071 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 177.2 | 61.31 | 92
2194 | BIRBHUM | Central Drilling | NETURI PIPED WATER SUPPLY SCHEME. , SM/12656 | New | Providing drilling crew and other allied works for construction of Tube Well(250mm X 200mmx 150mtrs Depth) by utilising Departmental Machineries for Neturi W/S scheme (TW-I), Sainthia Block under Birbhum District , CDD,PHE DTE. | 1134/CDD | 04/11/2022 | 30 | C.M. ENTERPRISE | 10.99 | 8.77 | 100 | 0
2195 | BIRBHUM | Central Drilling | NETURI PIPED WATER SUPPLY SCHEME. , SM/12656 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 200MM X 150 MTRS DEPTH) BY UTILIZING DEPARTMENTAL MACHINERIES FOR NETURI W/S SCH (TW-II), SAINTHIA BLOCK, UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | 1135/CDD | 04/11/2022 | 30 | C.M. ENTERPRISE | 10.99 | 8.31 | 100 | 0
2196 | BIRBHUM | Birbhum Division | NETURI PIPED WATER SUPPLY SCHEME. , SM/12656 | New | Material Requisition To Resource Division | 1418/BHM | 24/04/2023 | 0 | Resource Division | 11.04 | 0 | 0 | 0
2197 | BIRBHUM | Bolpur Mechanical | NETURI PIPED WATER SUPPLY SCHEME. , SM/12656 | New | WBSEDCL QUOTATION FOR NETURI WS SCHEME | BP-2023-2024-60 | 02/08/2023 | 0 | WBSEDCL | 4.86 | 0 | 0 | 0
2198 | BIRBHUM | Bolpur Mechanical | NETURI PIPED WATER SUPPLY SCHEME. , SM/12656 | New | WBSEDCL QUOTATION FOR NETURI WS SCHEME P.H NO.I | BP-2023-2024-59 | 02/08/2023 | 0 | WBSEDCL | 4.95 | 0 | 0 | 0
2199 | BIRBHUM | Bolpur Mechanical | NETURI PIPED WATER SUPPLY SCHEME. , SM/12656 | New | Providing Electro-mechanical accessories and others for Neturi & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 322/BOL.M.D | 27/03/2023 | 677 | ABHISEK ENGTNEERING CONCERN | 28.92 | 15.61 | 53.98 | 35
2200 | BIRBHUM | Birbhum Division | NETURI PIPED WATER SUPPLY SCHEME. , SM/12656 | New | Different works related to water supply scheme at NETURI, PAIKPARA & PAKURIA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 3441/BHM | 03/08/2023 | 940 | SHREE J.M. CONSTRUCTION | 1236.08 | 0 | 0 | 54
2201 | BIRBHUM | Birbhum Division | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division , SM/13630 | New | Material Requisition To Resource Division | 1465/BHM | 25/04/2023 | 0 | Resource Division | 51.71 | 0 | 0 | 0
2202 | BIRBHUM | Bolpur Mechanical | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division , SM/13630 | New | Providing Electro-mechanical accessories and others for Sonj PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | 3472/Bol.MD | 07/11/2023 | 60 | HINDOL ROY | 57.29 | 0 | 0 | 40
2203 | BIRBHUM | Bolpur Mechanical | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division , SM/13630 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Sonj PWSS under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 403/Bol.MD | 07/03/2024 | 45 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 24.55 | 0 | 0 | 80
2204 | BIRBHUM | Birbhum Division | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division , SM/13630 | New | Continuation Work Order for Preparation & Submission of DPR for (Sonj) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | 428/RSD | 09/11/2022 | 90 | ENVIROTECH SOLUTIONS | 2.5 | 0 | 0 | 100
2205 | BIRBHUM | Birbhum Division | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division , SM/13630 | New | Continuation Work Order for Preparation & Submission of DPR for (Sonj) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | 327/RSD | 08/09/2022 | 90 | ENVIROTECH SOLUTIONS | 3.29 | 0 | 0 | 100
2206 | BIRBHUM | Birbhum Division | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division , SM/13630 | New | Material Requisition To Resource Division | 207/BHM | 22/01/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
2207 | BIRBHUM | Bolpur Mechanical | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division , SM/13630 | New | WBSEDCL QUOTATION FOR SONJ W/S SCHEME PH-3 | BP-24-25-01 | 09/04/2024 | 0 | WBSEDCL | 2.8 | 0 | 0 | 0
2208 | BIRBHUM | Bolpur Mechanical | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division , SM/13630 | New | WBSEDCL QUOTATION FOR SONJ W/S SCHEME PH-2 | BP-24-25-02 | 09/04/2024 | 0 | WBSEDCL | 3.18 | 0 | 0 | 0
2209 | BIRBHUM | Bolpur Mechanical | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division , SM/13630 | New | WBSEDCL QUOTATION FOR SONJPIPED WS SCHEME PH NO.I | BP-23-24-283 | 22/02/2024 | 0 | WBSEDCL | 3.74 | 0 | 0 | 0
2210 | BIRBHUM | Birbhum Division | Sonj Piped Water Supply Scheme under Mayureswar-I within Birbhum Division , SM/13630 | New | Different works related to water supply scheme at LACHHIATOR, DAKSHINGRAM, SONJ & SHIBGRAM and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 4142/BHM | 19/10/2023 | 805 | B RAI CONSTRUCTION COMPANY | 2003.84 | 0 | 0 | 60
2211 | BIRBHUM | Bolpur Mechanical | MAJHKALITHA PIPED WATER SUPPLY SCHEME. , SM/12838 | New | Providing Electro-mechanical accessories and others for Majhkalitha PWSS at Nalhati - I Block under Bolpur Mechanical Division PHE Dte. | 3539/BOL.MD | 30/11/2023 | 60 | RUBY ENTERPRISE | 29.28 | 0 | 0 | 0
2212 | BIRBHUM | Birbhum Division | MAJHKALITHA PIPED WATER SUPPLY SCHEME. , SM/12838 | New | Material Requisition To Resource Division | 1431/BHM | 25/04/2023 | 0 | Resource Division | 13.69 | 0 | 0 | 0
2213 | BIRBHUM | Bolpur Mechanical | MAJHKALITHA PIPED WATER SUPPLY SCHEME. , SM/12838 | New | WBSEDCL QUOTATION FOR MAJHKALITHA PUMP HOUSE NO-I | BP-2023-24-293 | 07/03/2024 | 0 | WBSEDCL | 2.08 | 0 | 0 | 0
2214 | BIRBHUM | Bolpur Mechanical | MAJHKALITHA PIPED WATER SUPPLY SCHEME. , SM/12838 | New | WBSEDCL QUOTATION FOR MAJHKALITHA P H NO.I WS SCHEME | BP-23-24-246 | 29/01/2024 | 0 | WBSEDCL | 3.91 | 0 | 0 | 0
2215 | BIRBHUM | Bolpur Mechanical | MAJHKALITHA PIPED WATER SUPPLY SCHEME. , SM/12838 | New | WBSEDCL QUOTATION FOR MAJHKALITHA P H NO 2 | BP-23-24-161 | 29/01/2024 | 0 | WBSEDCL | 0.23 | 0 | 0 | 0
2216 | BIRBHUM | Birbhum Division | MAJHKALITHA PIPED WATER SUPPLY SCHEME. , SM/12838 | New | Different works related to water supply scheme at Majhkaltia, Sahira & KANAPIUR PWSS & its adjoining mouzas water supply scheme within Nalhati I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 1348/BHM | 20/04/2023 | 835 | M/S GOUTAM DAS | 1594.34 | 0 | 0 | 28
2217 | BIRBHUM | Birbhum Division | MAJHKALITHA PIPED WATER SUPPLY SCHEME. , SM/12838 | New | Restoration of Roads, pucca drain including Jack pushing & Augur boring along with extension of pipeline (DI & HDPE) with FHTC and supply of sluice valve with construction of valve chamber for Mathkalitha piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | 1508/BHM | 23/05/2025 | 90 | M/S GOUTAM DAS | 70.96 | 0 | 0 | 10
2218 | BIRBHUM | Bolpur Mechanical | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13475 | New | Providing Electro-mechanical accessories and others for Bhagabatipur PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | 1746/Bol.MD | 27/07/2023 | 60 | P. K. ENGINEERING | 43.95 | 0 | 0 | 30
2219 | BIRBHUM | Birbhum Division | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13475 | New | Continuation Work Order for Preparation & Submission of DPR for (Bhagabatipur) Water Supply Scheme under Mayureswar-I Development Block | 202/RSD | 08/06/2022 | 90 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 0 | 100
2220 | BIRBHUM | Birbhum Division | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13475 | New | Material Requisition To Resource Division | 1506/BHM | 25/04/2023 | 0 | Resource Division | 10.66 | 0 | 0 | 0
2221 | BIRBHUM | Bolpur Mechanical | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13475 | New | WBSEDCL QUOTATION MONEY FOR BHAGABATIPUR WS SCHEME | BP-2023-2024-76 | 24/08/2023 | 0 | WBSEDCL | 3.28 | 0 | 0 | 0
2222 | BIRBHUM | Bolpur Mechanical | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13475 | New | WBSEDCL QUOTATION FOR BHAGABATIPUR WS SCHEME | BP-23-24-121 | 12/10/2023 | 0 | WBSEDCL | 3.64 | 0 | 0 | 0
2223 | BIRBHUM | Bolpur Mechanical | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13475 | New | Supply and Delivery of Pumping Machinery for Bhagabatipur water supply scheme Block Mayureswar ¿I under Bolpur Mechanical Division PHE. Dte. | 607/AE-III | 27/03/2024 | 7 | P. K. ENGINEERING | 1.49 | 0 | 0 | 100
2224 | BIRBHUM | Birbhum Division | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13475 | New | Material Requisition To Resource Division | 209/BHM | 22/01/2024 | 0 | Resource Division | 3.34 | 0 | 0 | 0
2225 | BIRBHUM | Bolpur Mechanical | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13475 | New | WBSEDCL QUOTATION FOR BHAGABATIPUR PUMP HOUSE NO-II | BP-2023-24-289 | 04/03/2024 | 0 | WBSEDCL | 0.9 | 0 | 0 | 0
2226 | BIRBHUM | Birbhum Division | Bhagabatipur Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13475 | New | Different works related to water supply scheme at BHAGABATIPUR & its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1082/BHM | 06/04/2023 | 636 | ZEBA CONSTRUCTION | 253.52 | 0 | 0 | 100
2227 | BIRBHUM | Birbhum Division | Gaytha Piped Water Supply Scheme , SM/13712 | New | Continuation Work Order for Preparation & Submission of DPR for (Gaytha) Water Supply Scheme under Rampurhat-II Development Block. | 229/RSD | 24/06/2022 | 45 | ECO CARE | 3.63 | 0 | 0 | 100
2228 | BIRBHUM | Birbhum Division | Gaytha Piped Water Supply Scheme , SM/13712 | New | Material Requisition To Resource Division | 1544/BHM | 26/04/2023 | 0 | Resource Division | 13.99 | 0 | 0 | 0
2229 | BIRBHUM | Birbhum Division | Gaytha Piped Water Supply Scheme , SM/13712 | New | Different works related to water supply scheme at GAYTHA & its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under Birbhum Division, PHE Dte | 1311/BHM | 19/04/2023 | 275 | RAJ ASSOCIATES | 226.66 | 0 | 0 | 65
2230 | BIRBHUM | Bolpur Mechanical | Gaytha Piped Water Supply Scheme , SM/13712 | New | Supply delivery of voltage correction device at head work site of Gaytha PWSS in the district of Birbhum, under P.H.E. Dte. | 3797/BOL.MD | 12/09/2024 | 30 | SARKAR ELECTRICAL | 6.27 | 0 | 0 | 0
2231 | BIRBHUM | Bolpur Mechanical | Gaytha Piped Water Supply Scheme , SM/13712 | New | Supply & delivery ofSluice Valve & Non-Return Valve for Gaytha water supply scheme (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. | 1458./AE-III | 09/09/2024 | 7 | B. P. TRADING CORPORATION | 2.83 | 0 | 0 | 100
2232 | BIRBHUM | Bolpur Mechanical | Gaytha Piped Water Supply Scheme , SM/13712 | New | Supply & delivery of 16 mm² x 3 core Al.Ar. Cable of Gaytha water supply scheme (Block- Rampurhat - II) under Bolpur Mechanical Division, PHE Dte. " | 1307./AE-III | 28/08/2024 | 7 | SINHA ELECTRICALS | 4.87 | 0 | 0 | 100
2233 | BIRBHUM | Bolpur Mechanical | Gaytha Piped Water Supply Scheme , SM/13712 | New | Supply and Delivery of Sub-Mersible Pumping Machineries inconection with Providing Electro-mechanical accessories and others for Gaytha PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 684./AE-III | 08/04/2024 | 14 | WEST BENGAL ENGINEERING CO. | 1.58 | 0 | 0 | 100
2234 | BIRBHUM | Birbhum Division | Gaytha Piped Water Supply Scheme , SM/13712 | New | Material Requisition To Resource Division | 224/BHM | 24/01/2024 | 0 | Resource Division | 4 | 0 | 0 | 0
2235 | BIRBHUM | Bolpur Mechanical | Gaytha Piped Water Supply Scheme , SM/13712 | New | wbsedcl quotation money for gaytha p.h.no.1 pwss | BP-23-24-152 | 04/12/2023 | 0 | WBSEDCL | 2.74 | 0 | 0 | 0
2236 | BIRBHUM | Bolpur Mechanical | Gaytha Piped Water Supply Scheme , SM/13712 | New | wbsedcl quotation money for gaytha p.h.no.2 pwss | BP-23-24-151 | 04/12/2023 | 0 | WBSEDCL | 2.36 | 0 | 0 | 0
2237 | BIRBHUM | Bolpur Mechanical | Gaytha Piped Water Supply Scheme , SM/13712 | New | Providing Electro-mechanical accessories and others for Gaytha PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 2232/Bol.MD | 12/09/2023 | 597 | WEST BENGAL ENGINEERING CO. | 44.34 | 0 | 0 | 40
2238 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR CHICHUNRI AND OTHER 3 NOS. MOUZAS UNDER RAMPURHAT-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11906 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 0 | 92
2239 | BIRBHUM | Birbhum Division | Ikshudhara piped water supply scheme. , SM/13639 | New | Material Requisition To Resource Division | 1358/BHM | 24/04/2023 | 0 | Resource Division | 119 | 0 | 0 | 0
2240 | BIRBHUM | Bolpur Mechanical | Ikshudhara piped water supply scheme. , SM/13639 | New | Supply and delivery of Starter and other materials for ikshudhara water supply scheme under Bolpur Mechanical Division PHE Dte. | 3803/BOL.MD | 12/09/2024 | 20 | STANDARD ELECTRICALS | 6.54 | 0 | 0 | 100
2241 | BIRBHUM | Bolpur Mechanical | Ikshudhara piped water supply scheme. , SM/13639 | New | Supply & delivery of submersible cable accessories at ikshudhara Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | 3821/BOL.MD | 18/09/2024 | 20 | MITRA ENTERPRISE | 2.8 | 0 | 0 | 100
2242 | BIRBHUM | Bolpur Mechanical | Ikshudhara piped water supply scheme. , SM/13639 | New | Supply and delivery of chlorinator dosing pump for ikshudhara Water Supply Project under Bolpur Mechanical Divn. P.H.E. Dte. | 3818/BOL.MD | 18/09/2024 | 20 | M/S. UTTAM KUMAR CHATTERJEE | 3.24 | 0 | 0 | 100
2243 | BIRBHUM | Bolpur Mechanical | Ikshudhara piped water supply scheme. , SM/13639 | New | WBSEDCL QUOTATION FOR Ikshudhara piped water supply scheme. | BP-23-24-220 | 15/01/2024 | 0 | WBSEDCL | 6.17 | 0 | 0 | 0
2244 | BIRBHUM | Central Drilling | Ikshudhara piped water supply scheme. , SM/13639 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2245 | BIRBHUM | Bolpur Mechanical | Ikshudhara piped water supply scheme. , SM/13639 | New | Providing Electro-mechanical accessories and others for Ikshudhara & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | 2239/BOL.MD. | 13/09/2023 | 627 | QUAZI NOZRUL ISLAM | 80.69 | 0 | 0 | 85
2246 | BIRBHUM | Birbhum Division | Ikshudhara piped water supply scheme. , SM/13639 | New | Different works related to water supply scheme at IKSHUDHARA, KANKALITALA, KASBA & KENDANGAL Piped Water Supply Scheme within BOLPUR-SRINIKETAN Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 4139/BHM | 18/10/2023 | 896 | M/S TAPAS KUMAR CHAKRABORTY | 2684.99 | 0 | 0 | 60
2247 | BIRBHUM | Bolpur Mechanical | Ikshudhara piped water supply scheme. , SM/13639 | New | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, P.H.E.Dte. | 4216/BOL.MD | 23/10/2024 | 200 | SATYAJIT GHOSH | 0.57 | 0 | 0 | 100
2248 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR KATUNIA AND OTHER 2 NOS. MOUZAS UNDER MD. BAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11909 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 95.73 | 137.63 | 92
2249 | BIRBHUM | Birbhum Division | Shaspur Piped Water Supply Scheme. , SM/13651 | New | Continuation Work Order for Preparation & Submission of DPR for (Shaspur) Water Supply Scheme under Rampurhat-II Development Block. | 204/RSD | 13/06/2022 | 45 | ECO CARE | 4.73 | 0 | 0 | 100
2250 | BIRBHUM | Birbhum Division | Shaspur Piped Water Supply Scheme. , SM/13651 | New | Material Requisition To Resource Division | 1555/BHM | 26/04/2023 | 0 | Resource Division | 94.6 | 0 | 0 | 0
2251 | BIRBHUM | Birbhum Division | Shaspur Piped Water Supply Scheme. , SM/13651 | New | Material Requisition To Resource Division | 220/BHM | 24/01/2024 | 0 | Resource Division | 4 | 0 | 0 | 0
2252 | BIRBHUM | Bolpur Mechanical | Shaspur Piped Water Supply Scheme. , SM/13651 | New | Quotation for new service connection at Shaspur TW No-II (Block-Rampurhat-II) |  | 13/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.87 | 0 | 0 | 0
2253 | BIRBHUM | Bolpur Mechanical | Shaspur Piped Water Supply Scheme. , SM/13651 | New | WBSEDCL QUOTATION FOR SHASPUR TW-II | BP-2023-24-310 | 18/03/2024 | 0 | WBSEDCL | 2.87 | 0 | 0 | 0
2254 | BIRBHUM | Bolpur Mechanical | Shaspur Piped Water Supply Scheme. , SM/13651 | New | WBSEDCL QUOTATION FOR SHASPUR TW-1 | BP-2023-24-309 | 18/03/2024 | 0 | WBSEDCL | 2.73 | 0 | 0 | 0
2255 | BIRBHUM | Bolpur Mechanical | Shaspur Piped Water Supply Scheme. , SM/13651 | New | Quotation for new service connection at Shaspur TW No-I (Block-Rampurhat-II) |  | 13/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.73 | 0 | 0 | 0
2256 | BIRBHUM | Birbhum Division | Shaspur Piped Water Supply Scheme. , SM/13651 | New | Different works related to water supply scheme at NABAGRAM, SAHAPUR & SHASPUR and its adjoining mouzas water supply scheme within RAMPURHAT-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3522/BHM | 11/08/2023 | 821 | SUNIL RABI DAS | 1157.77 | 0 | 0 | 40
2257 | BIRBHUM | Bolpur Mechanical | Shaspur Piped Water Supply Scheme. , SM/13651 | New | Providing Electro-mechanical accessories and others for Shaspur PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 2234/Bol.MD | 12/09/2023 | 658 | SINHA ELECTRICALS | 45.39 | 0 | 0 | 90
2258 | BIRBHUM | Bolpur Mechanical | Shaspur Piped Water Supply Scheme. , SM/13651 | New | Supply & delivery of UPVC Column pipes at store for Sahapur water supply scheme under Bolpur Mechanical Division, PHE. Dte. | 1452./AE-III | 09/09/2024 | 114 | S.B ENTERPRISE | 2.69 | 0 | 0 | 100
2259 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR AMLACHATURI AND OTHER 10 NOS. MOUZAS UNDER RAJNAGAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11936 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 248.23 | 73.01 | 92
2260 | BIRBHUM | Birbhum Division | Nawapara Piped Water Supply Scheme , SM/13479 | New | Preparation and submission of DPR for (Nawapara) Water Supply Scheme under Nalhati-II Development Block. | 231/AE/NSD | 21/04/2022 | 45 | MS SOBHA AND CO | 4.6 | 0 | 0 | 100
2261 | BIRBHUM | Birbhum Division | Nawapara Piped Water Supply Scheme , SM/13479 | New | Material Requisition To Resource Division | 1502/BHM | 25/04/2023 | 0 | Resource Division | 65.11 | 0 | 0 | 0
2262 | BIRBHUM | Bolpur Mechanical | Nawapara Piped Water Supply Scheme , SM/13479 | New | Supply and Delivery of Volage correction device, Cetrifugal Pumping Machineries and allied accessories for Nawapara PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | 3780/BOL.MD | 12/09/2024 | 111 | S.K.ELECTRICALS | 33.77 | 0 | 0 | 50
2263 | BIRBHUM | Bolpur Mechanical | Nawapara Piped Water Supply Scheme , SM/13479 | New | WBSEDCL QUOTATION FOR NOAPARA P H .II WS SCHEME | BP-23-24-234 | 29/01/2024 | 0 | WBSEDCL | 3.42 | 0 | 0 | 0
2264 | BIRBHUM | Bolpur Mechanical | Nawapara Piped Water Supply Scheme , SM/13479 | New | WBSEDCL QUOTATION FOR NOAPARA WS SCHEME | BP-23-24-233 | 15/01/2024 | 0 | WBSEDCL | 4.14 | 0 | 0 | 0
2265 | BIRBHUM | Birbhum Division | Nawapara Piped Water Supply Scheme , SM/13479 | New | Different works related to water supply scheme at NAWAPARA & PRASADPUR and its adjoining mouzas water supply scheme within NALHATI-II Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 3257/BHM | 26/07/2023 | 275 | MANASH GHOSH | 866.09 | 0 | 0 | 5
2266 | BIRBHUM | Bolpur Mechanical | Nawapara Piped Water Supply Scheme , SM/13479 | New | Providing Electro-mechanical accessories and others for Nawpara PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | 2137/Bol.MD | 25/08/2023 | 676 | M. S. ENTERPRISE | 45.52 | 0 | 0 | 70
2267 | BIRBHUM | Birbhum Division | Nawapara Piped Water Supply Scheme , SM/13479 | New | Extension of pipeline (DI & HDPE) with FHTC, Restoration of Roads including Augur boring along with supply of sluice valve with construction of valve chamber for Nawapara piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division, P.H.E. Dte. | 2143/BHM | 19/08/2025 | 90 | APORUPA CONSTRUCTION | 54.08 | 0 | 0 | 0
2268 | BIRBHUM | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. , SM/12892 | New | Material Requisition To Resource Division | 1432/BHM | 25/04/2023 | 0 | Resource Division | 40.94 | 0 | 0 | 0
2269 | BIRBHUM | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. , SM/12892 | New | Material Requisition To Resource Division | 1496/BHM | 25/04/2023 | 0 | Resource Division | 40.94 | 0 | 0 | 0
2270 | BIRBHUM | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. , SM/12892 | New | Restoration charges for laying of PHE pipeline from Chainage 9.50 KM (Barsliapukur) to 12.24 KM (end point) of Murarai Mitrapur Road under Rampurhat Highrway Sub-Division of Birbhunr Highrvay Division-1. in the District of Bir.bhurn during the year 2024-25 | BP-2024-25-223 | 12/09/2024 | 0 | EXECUTIVE ENGINEER BIRBHUM HIGHWAY DIVISION-I P.W (ROADS) DIRECTORATE | 9.82 | 0 | 0 | 0
2271 | BIRBHUM | Bolpur Mechanical | MITRAPUR WATER SUPPLY SCHEME. , SM/12892 | New | Quotation deposit for Mitrapur Water Supply Scheme P/H-II in Paikar CCC under Bolpur Mechanical division, PHE Dte. | BP-24-25-179 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.82 | 0 | 0 | 0
2272 | BIRBHUM | Bolpur Mechanical | MITRAPUR WATER SUPPLY SCHEME. , SM/12892 | New | Quotation deposit for empowering Mitrapur P/H-I Water Supply Scheme in Paikar CCC under Bolpur Mechanical Division, PHE Dte. | BP-2024-2025-77 | 13/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.64 | 0 | 0 | 0
2273 | BIRBHUM | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. , SM/12892 | New | Different works related to water supply scheme at MITRAPUR & its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 3597/BHM | 21/08/2023 | 742 | SUNIL RABI DAS | 635.29 | 0 | 0 | 55
2274 | BIRBHUM | Bolpur Mechanical | MITRAPUR WATER SUPPLY SCHEME. , SM/12892 | New | Providing Electro-mechanical accessories and others for Mitrapur PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | 3306/BOL.MD | 29/09/2023 | 703 | MITRA ENTERPRISE | 30.25 | 0 | 0 | 80
2275 | BIRBHUM | Birbhum Division | MITRAPUR WATER SUPPLY SCHEME. , SM/12892 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
2276 | BIRBHUM | Birbhum Division | Modapa Piped Water Supply Scheme. , SM/13517 | New | Material Requisition To Resource Division | 1399/BHM | 24/04/2023 | 0 | Resource Division | 12.63 | 0 | 0 | 0
2277 | BIRBHUM | Bolpur Mechanical | Modapa Piped Water Supply Scheme. , SM/13517 | New | Providing Electro-mechanical accessories and others for Modapa & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | 2242/BOL.MD | 13/09/2023 | 60 | SWAPAN ENTERPRISE | 10.16 | 0 | 0 | 100
2278 | BIRBHUM | Birbhum Division | Modapa Piped Water Supply Scheme. , SM/13517 | New | Submission of Wayleave/Track crossing proposal in IR-RBCS station from Dubrajpur to Chinpai (38-39) KM | BP-2024-25-67 | 30/05/2024 | 0 | EASTERN RAILWAY | 5.35 | 0 | 0 | 0
2279 | BIRBHUM | Bolpur Mechanical | Modapa Piped Water Supply Scheme. , SM/13517 | New | WBSEDL QUOTATION FOR MODAPA PUMP HOUSEN NO II | BP-23-24-262 | 06/02/2024 | 0 | WBSEDCL | 4.42 | 0 | 0 | 0
2280 | BIRBHUM | Bolpur Mechanical | Modapa Piped Water Supply Scheme. , SM/13517 | New | WBSEDCL QUOIT ION FOR MODAPA PUMP HOUSE NO I | BP-23-24-263 | 06/02/2024 | 0 | WBSEDCL | 3.59 | 0 | 0 | 0
2281 | BIRBHUM | Birbhum Division | Modapa Piped Water Supply Scheme. , SM/13517 | New | Different works related to water supply scheme at MODAPA & its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1303/BHM | 19/04/2023 | 743 | J.P.ENTERPRISE | 280.53 | 0 | 0 | 78
2282 | BIRBHUM | Birbhum Division | KADOA PIPED WAYER SUPPLY SCHEME , SM/14668 | New | Material Requisition To Resource Division | 1595/BHM | 26/04/2023 | 0 | Resource Division | 28.19 | 0 | 0 | 0
2283 | BIRBHUM | Birbhum Division | KADOA PIPED WAYER SUPPLY SCHEME , SM/14668 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for KADOA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | 155/BSD | 18/04/2022 | 180 | APEX ENGINEERING | 3.52 | 0 | 0 | 100
2284 | BIRBHUM | Birbhum Division | KADOA PIPED WAYER SUPPLY SCHEME , SM/14668 | New | Material Requisition To Resource Division | 2388/BHM | 27/08/2024 | 0 | Resource Division | 6.4 | 0 | 0 | 0
2285 | BIRBHUM | Central Drilling | KADOA PIPED WAYER SUPPLY SCHEME , SM/14668 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2286 | BIRBHUM | Birbhum Division | KADOA PIPED WAYER SUPPLY SCHEME , SM/14668 | New | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1948/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0 | 0
2287 | BIRBHUM | Bolpur Mechanical | KADOA PIPED WAYER SUPPLY SCHEME , SM/14668 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Kadoa PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte. | 329/BOL.MD | 19/02/2025 | 239 | OSMAN SEKH | 76.29 | 0 | 0 | 40
2288 | BIRBHUM | Birbhum Division | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14676 | New | Continuation Work Order for Preparation & Submission of DPR for (Khagra) Water Supply Scheme under Mayureswar-II Development Block. | 186/RSD | 10/05/2022 | 45 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 0 | 100
2289 | BIRBHUM | Birbhum Division | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14676 | New | Material Requisition To Resource Division | 1536/BHM | 26/04/2023 | 0 | Resource Division | 10.76 | 0 | 0 | 0
2290 | BIRBHUM | Bolpur Mechanical | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14676 | New | Supply & delivery of submersible Pumping Machineries & cable at Khagra Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | 1455./AE-III | 09/09/2024 | 7 | PRADIP KUMAR DHABAL | 2.83 | 0 | 0 | 100
2291 | BIRBHUM | Birbhum Division | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14676 | New | Material Requisition To Resource Division | 201/BHM | 22/01/2024 | 0 | Resource Division | 2.03 | 0 | 0 | 0
2292 | BIRBHUM | Bolpur Mechanical | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14676 | New | New Power connection at Khagra PWSS (P/H-I) under Mayureswar-II Block | BP-2024-2025-56 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.9 | 0 | 0 | 0
2293 | BIRBHUM | Bolpur Mechanical | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14676 | New | New Power connection at Khagra (PH-II) PWSS, under Bolpur Mechanical Division, P.H.e.Dte. | BP-2024-2025-27 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.88 | 0 | 0 | 0
2294 | BIRBHUM | Birbhum Division | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14676 | New | Different works related to Water Supply Scheme at KHAGRA & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 2066/BHM | 08/06/2023 | 938 | MALLICK CONSTRUCTION | 243.5 | 0 | 0 | 65
2295 | BIRBHUM | Bolpur Mechanical | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14676 | New | Providing Electro-mechanical accessories and others for Khagra PWSS at Mayurreswar - II Block under Bolpur Mechanical Division PHE Dte | 3280/BOL.MD | 29/09/2023 | 611 | QUAZI NOZRUL ISLAM | 44.01 | 0 | 0 | 40
2296 | BIRBHUM | Bolpur Mechanical | KHAGRA PIPED WATER SUPPLY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DISTRICT , SM/14676 | New | Supply & delivery of different electrical accessories at Khagra Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | 1300./AE-III | 27/08/2024 | 7 | QUAZI NOZRUL ISLAM | 2.96 | 0 | 0 | 100
2297 | BIRBHUM | Birbhum Division | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13376 | New | Preparation & Submission of DPR for (Asuralay) Water Supply Scheme under Mayureswar-I Development Block. | 158/RSD | 18/04/2022 | 90 | ENVIROTECH SOLUTIONS | 4.65 | 0 | 0 | 100
2298 | BIRBHUM | Birbhum Division | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13376 | New | Material Requisition To Resource Division | 1526/BHM | 26/04/2023 | 0 | Resource Division | 17.89 | 0 | 0 | 0
2299 | BIRBHUM | Bolpur Mechanical | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13376 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Asuralaya PWSS under Mayureswar - I Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 518/BOL.MD | 14/03/2024 | 60 | M/S. YOUTH ENGINEERS' ENTERPRISE | 7.62 | 0 | 0 | 60
2300 | BIRBHUM | Bolpur Mechanical | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13376 | New | Quotation for new service connection at Asuralya PWSS, P.H- II under Mollarpur CCC (Mayureswar-I Block) | BP-2024-2025-25 | 18/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.6 | 0 | 0 | 0
2301 | BIRBHUM | Bolpur Mechanical | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13376 | New | New service connection at Asuralaya PH-I PWSS under Bolpur Mechanical Division, P.H.E Dte. | BP-24-25-189 | 24/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.58 | 0 | 0 | 0
2302 | BIRBHUM | Bolpur Mechanical | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13376 | New | Providing Electro-mechanical accessories and others for Asuralaya PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | 3474/Bol.MD | 07/11/2023 | 582 | S. S. ENTERPRISES | 43.56 | 0 | 0 | 50
2303 | BIRBHUM | Birbhum Division | Asuralay Piped Water Supply Scheme under mayureswar-I Block within Birbhum Division. , SM/13376 | New | Different works related to water supply scheme at BIRCHANDRAPUR, ASURLAYA, BARATURIGRAM & KANAIPUR and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. (2nd Call) | 505/BHM | 05/02/2024 | 603 | B RAI CONSTRUCTION COMPANY | 2071.77 | 0 | 0 | 20
2304 | BIRBHUM | Birbhum Division | DELORA PIPED WATER SUPPLY SCHEME , SM/13600 | New | Material Requisition To Resource Division | 1459/BHM | 25/04/2023 | 0 | Resource Division | 12.35 | 0 | 0 | 0
2305 | BIRBHUM | Bolpur Mechanical | DELORA PIPED WATER SUPPLY SCHEME , SM/13600 | New | New Power Connection at Delora PWSS under Bolpur mechanical Division, PHE Dte. | BP-24-25-130 | 29/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.84 | 0 | 0 | 0
2306 | BIRBHUM | Birbhum Division | DELORA PIPED WATER SUPPLY SCHEME , SM/13600 | New | Different works related to water supply scheme at DELORA Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1192/BHM | 12/04/2023 | 1082 | M/S SANDIP CONSTRUCTION | 278.71 | 0 | 0 | 5
2307 | BIRBHUM | Central Drilling | DELORA PIPED WATER SUPPLY SCHEME , SM/13600 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2308 | BIRBHUM | Birbhum Division | Nohana and Adjoining Mouzas PWSS , SM/12905 | New | Material Requisition To Resource Division | 1412/BHM | 24/04/2023 | 0 | Resource Division | 10.86 | 0 | 0 | 0
2309 | BIRBHUM | Birbhum Division | Nohana and Adjoining Mouzas PWSS , SM/12905 | New | Different works related to water supply scheme at NOHANA & its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1643/BHM | 02/05/2023 | 276 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 266.53 | 0 | 0 | 30
2310 | BIRBHUM | Birbhum Division | Nohana and Adjoining Mouzas PWSS , SM/12905 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for NOHANA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 236/BSD | 17/06/2022 | 90 | M/S R DUTTA & CO. | 4.99 | 0 | 0 | 100
2311 | BIRBHUM | Bolpur Mechanical | Nohana and Adjoining Mouzas PWSS , SM/12905 | New | New service connection at Nohana and Adjoining Moujas W/S scheme, PH-II, Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-24-25-89 | 19/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.29 | 0 | 0 | 0
2312 | BIRBHUM | Bolpur Mechanical | Nohana and Adjoining Mouzas PWSS , SM/12905 | New | Quotation for new service connection at Nohana PWSS, P/H- II under Illambazar CCC | BP-24-25-272 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.74 | 0 | 0 | 0
2313 | BIRBHUM | Bolpur Mechanical | Nohana and Adjoining Mouzas PWSS , SM/12905 | New | New service connection at Nohana and Adjoining Moujas W/S scheme, PH-I, Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-24-25-88 | 19/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.93 | 0 | 0 | 0
2314 | BIRBHUM | Bolpur Mechanical | Nohana and Adjoining Mouzas PWSS , SM/12905 | New | Providing Electro-mechanical accessories and others for Nohana & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2172/Bol.MD | 01/09/2023 | 519 | M/S. UTTAM KUMAR CHATTERJEE | 14.97 | 0 | 0 | 80
2315 | BIRBHUM | Birbhum Division | Satpalsa Piped Water Supply Scheme Under Mayureswar-II Block Within Birbhum Division , SM/13982 | New | Continuation Work Order for Preparation & Submission of DPR for (Satpalsa) Water Supply Scheme under Mayureswar-II Development Block. | 211/RSD | 16/06/2022 | 45 | ENVIROTECH SOLUTIONS | 4.29 | 0 | 0 | 100
2316 | BIRBHUM | Birbhum Division | Satpalsa Piped Water Supply Scheme Under Mayureswar-II Block Within Birbhum Division , SM/13982 | New | Material Requisition To Resource Division | 1454/BHM | 25/04/2023 | 0 | Resource Division | 17.5 | 0 | 0 | 0
2317 | BIRBHUM | Bolpur Mechanical | Satpalsa Piped Water Supply Scheme Under Mayureswar-II Block Within Birbhum Division , SM/13982 | New | Providing Electro-mechanical accessories and others for Satpalsa PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | 3277/Bol.MD | 29/09/2023 | 60 | GHOSH ENGINEERING SYNDICATE | 44.05 | 0 | 0 | 40
2318 | BIRBHUM | Birbhum Division | Satpalsa Piped Water Supply Scheme Under Mayureswar-II Block Within Birbhum Division , SM/13982 | New | Material Requisition To Resource Division | 232/BHM | 24/01/2024 | 0 | Resource Division | 5.5 | 0 | 0 | 0
2319 | BIRBHUM | Birbhum Division | Satpalsa Piped Water Supply Scheme Under Mayureswar-II Block Within Birbhum Division , SM/13982 | New | Different works related to Water Supply Scheme at SATPALSA & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 4135/BHM | 18/10/2023 | 809 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 394.79 | 0 | 0 | 35
2320 | BIRBHUM | Birbhum Division | BENAGRAM PIPED WATER SUPPLY SCHEME , SM/13377 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BENAGRAM Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 171/BSD | 27/04/2022 | 90 | RADIANT | 4 | 0 | 0 | 100
2321 | BIRBHUM | Birbhum Division | BENAGRAM PIPED WATER SUPPLY SCHEME , SM/13377 | New | Material Requisition To Resource Division | 1469/BHM | 25/04/2023 | 0 | Resource Division | 37.92 | 0 | 0 | 0
2322 | BIRBHUM | Bolpur Mechanical | BENAGRAM PIPED WATER SUPPLY SCHEME , SM/13377 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Benagram WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | 4530/BOL.MD | 20/12/2024 | 120 | MENAKA ENTERPRISE | 73 | 0 | 0 | 0
2323 | BIRBHUM | Birbhum Division | BENAGRAM PIPED WATER SUPPLY SCHEME , SM/13377 | New | Different works related to water supply scheme at BENAGRAM PIPED WATER SUPPLY SCHEME (TSM/015486) within NANOOR Block including supply of all labour & materials under Bolpur Sub- Division within Birbhum Division, PHE Dte." | 2428/BHM | 29/08/2024 | 365 | M/S. A K ENTERPRISE | 355.96 | 0 | 0 | 0
2324 | BIRBHUM | Birbhum Division | BENAGRAM PIPED WATER SUPPLY SCHEME , SM/13377 | New | Material Requisition To Resource Division | 2486/BHM | 03/09/2024 | 0 | Resource Division | 8.22 | 0 | 0 | 0
2325 | BIRBHUM | Central Drilling | BENAGRAM PIPED WATER SUPPLY SCHEME , SM/13377 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2326 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection(FHTC) under Danghara PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09370 | Retrofitting | Sinking of 200mm 90 m. deep Tube well fitted with 200 mm dia. PVC pipe and fibre glass Strainer etc. all complete at Head Work site of Danghara Piped Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 131/AE/NSD | 09/03/2022 | 30 | QUAZI SIRAJUL ISLAM. | 4.8 | 0 | 0 | 100
2327 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection(FHTC) under Danghara PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09370 | Retrofitting | Construction of Pump House of 5.40mtr. x 3.6mtr. size with sanitary and water supply arrangements at DHANGHARA PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 17/AE/NSD | 17/01/2022 | 60 | QUAZI SIRAJUL ISLAM. | 4.99 | 0 | 0 | 100
2328 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection(FHTC) under Danghara PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09370 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of Danghara under Danghara Water Supply Scheme within Birbhum Division, PHE Dte¿ (Sl. No.4) | 2002/BHM | 15/09/2022 | 60 | NUR MOBINUL ISLAM | 70.94 | 70.77 | 100 | 100
2329 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection(FHTC) under Danghara PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09370 | Retrofitting | Extension of distribution Pipe line including FHTC Work along with restoration of road of Danghara Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte (Sl.No.4) | 874/BHM | 21/03/2023 | 60 | QUAZI SIRAJUL ISLAM. | 29.28 | 0 | 0 | 50
2330 | BIRBHUM | Birbhum Division | Shitalgram Piped Water Supply Scheme , SM/14087 | New | Preparation and submission of DPR for (Shitalgram) Water Supply Scheme under Nalhati-II Development Block. | 233/AE/NSD | 21/04/2022 | 45 | MS SOBHA AND CO | 4.14 | 0 | 0 | 100
2331 | BIRBHUM | Birbhum Division | Shitalgram Piped Water Supply Scheme , SM/14087 | New | Material Requisition To Resource Division | 2175/BHM | 23/06/2023 | 0 | Resource Division | 19.69 | 0 | 0 | 0
2332 | BIRBHUM | Bolpur Mechanical | Shitalgram Piped Water Supply Scheme , SM/14087 | New | Providing Electro-mechanical accessories and others for Shitalgram PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | 2109/Bol.MD | 22/08/2023 | 60 | HINDOL ROY | 45.44 | 0 | 0 | 50
2333 | BIRBHUM | Bolpur Mechanical | Shitalgram Piped Water Supply Scheme , SM/14087 | New | WBSEDCL QUOTATION FOR SHITALGRAM WS SCHEME | BP-23-24-235 | 29/01/2024 | 0 | WBSEDCL | 3.62 | 0 | 0 | 0
2334 | BIRBHUM | Birbhum Division | Shitalgram Piped Water Supply Scheme , SM/14087 | New | Jack pushing & Augur boring along with restoration of Roads, extension of pipeline (DI & HDPE) etc including all allied works for Shitalgram piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | 798/BHM | 24/03/2025 | 360 | M/S S. CHOUDHURY | 38.07 | 0 | 0 | 70
2335 | BIRBHUM | Birbhum Division | Rajpur Piped Water Supply Scheme , SM/14026 | New | Material Requisition To Resource Division | 3283/BHM | 27/07/2023 | 0 | Resource Division | 0.51 | 0 | 0 | 0
2336 | BIRBHUM | Bolpur Mechanical | Rajpur Piped Water Supply Scheme , SM/14026 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Rajpur PWSS under Rajnagar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 531/BOL.MD | 14/03/2024 | 60 | NITESH MANAGEMENT | 7.58 | 0 | 0 | 60
2337 | BIRBHUM | Bolpur Mechanical | Rajpur Piped Water Supply Scheme , SM/14026 | New | Supply & delivery of Al.Ar cable for Rajpur Piped water supply scheme under Bolpur Mechanical Division(Block-Rajnagar), PHE Dte. | 1477./AE-III | 11/09/2024 | 7 | M. S. ENTERPRISE | 4.31 | 0 | 0 | 100
2338 | BIRBHUM | Bolpur Mechanical | Rajpur Piped Water Supply Scheme , SM/14026 | New | QUOTATION FOR RAJPUR PWSS AT RAJNAGAR BLOCK | BP-24-25-08 | 09/04/2024 | 0 | WBSEDCL | 9.47 | 0 | 0 | 0
2339 | BIRBHUM | Birbhum Division | Rajpur Piped Water Supply Scheme , SM/14026 | New | Different works related to water supply scheme at RAJPUR & its adjoining mouzas water supply scheme within RAJNAGAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1346/BHM | 20/04/2023 | 796 | MUSKAN ENTERPRISE | 410.62 | 0 | 0 | 25
2340 | BIRBHUM | Bolpur Mechanical | Rajpur Piped Water Supply Scheme , SM/14026 | New | Providing Electro-mechanical accessories and others for Rajpur & Adjoining moujas water supply scheme at Rajnagar Block under Bolpur Mechanical Division PHE Dte. | 3550/Bol.MD | 01/12/2023 | 647 | GLACIER ENGINEERING CO. | 87.05 | 0 | 0 | 89
2341 | BIRBHUM | Birbhum Division | Rajpur Piped Water Supply Scheme , SM/14026 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
2342 | BIRBHUM | Bolpur Mechanical | Haridaspur Piped Water Supply Scheme. , SM/14028 | New | Supply and delivery of Column pipe and other at Haridaspur water supply scheme under Bolpur Mechanical Division, PHE. Dte. | 950/AE-III | 04/07/2023 | 7 | J.K.ENGINEERING CO | 0.97 | 0 | 0 | 100
2343 | BIRBHUM | Birbhum Division | Haridaspur Piped Water Supply Scheme. , SM/14028 | New | Material Requisition To Resource Division | 1623/BHM | 28/04/2023 | 0 | Resource Division | 42.21 | 0 | 0 | 0
2344 | BIRBHUM | Bolpur Mechanical | Haridaspur Piped Water Supply Scheme. , SM/14028 | New | Providing Electro-mechanical accessories and others for HARIDASPUR piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | 1498/Bol.MD | 17/07/2023 | 60 | C M ENTERPRISE | 41.17 | 0 | 0 | 40
2345 | BIRBHUM | Bolpur Mechanical | Haridaspur Piped Water Supply Scheme. , SM/14028 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Haridaspur PWSS under Md. Bazar Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 523/BOL.MD | 14/03/2024 | 60 | S. K. ENTERPRISE | 7.6 | 0 | 0 | 100
2346 | BIRBHUM | Birbhum Division | MAHESWARPUR PIPED WATER SUPPLY SCHEME , SM/15254 | New | Material Requisition To Resource Division | 1584/BHM | 26/04/2023 | 0 | Resource Division | 20.97 | 0 | 0 | 0
2347 | BIRBHUM | Birbhum Division | MAHESWARPUR PIPED WATER SUPPLY SCHEME , SM/15254 | New | Different works related to water supply scheme at MAHESWARPUR Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1133/BHM | 10/04/2023 | 275 | GUPTA CONSTRUCTION | 339.98 | 0 | 0 | 1
2348 | BIRBHUM | Birbhum Division | MAHESWARPUR PIPED WATER SUPPLY SCHEME , SM/15254 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for MAHESHWARPUR Piped Water Supply Scheme under Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 108/BSD | 21/03/2022 | 90 | M/S R DUTTA & CO. | 2.86 | 0 | 0 | 100
2349 | BIRBHUM | Central Drilling | MAHESWARPUR PIPED WATER SUPPLY SCHEME , SM/15254 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2350 | BIRBHUM | Birbhum Division | Banior Piped Water Supply Scheme. , SM/14688 | New | Material Requisition To Resource Division | 1625/BHM | 28/04/2023 | 0 | Resource Division | 654.06 | 0 | 0 | 0
2351 | BIRBHUM | Bolpur Mechanical | Banior Piped Water Supply Scheme. , SM/14688 | New | Supply & Installation of Low lift pumping machineries and other allied works for Banior piped water supply scheme within Nalhati-I block, under Bolpur Mechanical Division PHE Dte. | 3560/BOL.MD | 04/12/2023 | 485 | QUAZI NOZRUL ISLAM | 74.52 | 0 | 0 | 30
2352 | BIRBHUM | Bolpur Mechanical | Banior Piped Water Supply Scheme. , SM/14688 | New | Supply & Installation of High lift pumping machineries and other allied works for Banior piped water supply scheme within Nalhati-I block, under Bolpur Mechanical Division PHE Dte.. | 3557/BOL.MD | 04/12/2023 | 302 | MACHINE SUPPLIERS SYNDUCATE (P) LTD. | 95.52 | 0 | 0 | 40
2353 | BIRBHUM | Bolpur Mechanical | Banior Piped Water Supply Scheme. , SM/14688 | New | Hiring of Luxury Car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division, PHE. Dte. | 205/Bol.MD | 27/02/2024 | 121 | RAJIB GHOSH | 0.57 | 0 | 0 | 0
2354 | BIRBHUM | Bolpur Mechanical | Banior Piped Water Supply Scheme. , SM/14688 | New | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, P.H.E.Dte. | 3317/BOL.MD | 29/09/2023 | 121 | SATYAJIT GHOSH | 0.57 | 0 | 0 | 100
2355 | BIRBHUM | Bolpur Mechanical | Banior Piped Water Supply Scheme. , SM/14688 | New | Hiring of vehicle for the office of the Executive Engineer, Bolpur Mechanical Division, P.H.E.Dte. | 174/BOL.MD | 21/02/2024 | 121 | SATYAJIT GHOSH | 0.57 | 0 | 0 | 0
2356 | BIRBHUM | Bolpur Mechanical | Banior Piped Water Supply Scheme. , SM/14688 | New | Hiring of Luxury car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division, P.H.E.Dte. | 1221/BOL.MD. | 26/06/2023 | 123 | RAJIB GHOSH | 0.58 | 0 | 0 | 0
2357 | BIRBHUM | Birbhum Division | Banior Piped Water Supply Scheme. , SM/14688 | New | Different works related to water supply scheme at BANIOR & its adjoining mouzas water supply scheme within NALHATI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3777/BHM | 08/09/2023 | 724 | TUSHAR KANTI GHOSH | 1573.21 | 0 | 0 | 12
2358 | BIRBHUM | Bolpur Mechanical | Banior Piped Water Supply Scheme. , SM/14688 | New | Hiring of Luxury Car (Diesel) for the office of the Assistant Engineer, Bolpur Mechanical Division, PHE. Dte. | 1675/BOL.MD | 28/06/2024 | 121 | RAJIB GHOSH | 0.57 | 0 | 0 | 100
2359 | BIRBHUM | Birbhum Division | PAPURI PIPED WATER SUPPLY SCHEME , SM/14691 | New | Material Requisition To Resource Division | 1467/BHM | 25/04/2023 | 0 | Resource Division | 36.41 | 0 | 0 | 0
2360 | BIRBHUM | Birbhum Division | PAPURI PIPED WATER SUPPLY SCHEME , SM/14691 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for PAPURI Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | 269/BSD | 15/07/2022 | 90 | RADIANT | 4.94 | 0 | 0 | 100
2361 | BIRBHUM | Birbhum Division | PAPURI PIPED WATER SUPPLY SCHEME , SM/14691 | New | Material Requisition To Resource Division | 2393/BHM | 27/08/2024 | 0 | Resource Division | 12.11 | 0 | 0 | 0
2362 | BIRBHUM | Central Drilling | PAPURI PIPED WATER SUPPLY SCHEME , SM/14691 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2363 | BIRBHUM | Birbhum Division | PAPURI PIPED WATER SUPPLY SCHEME , SM/14691 | New | Construction of 250 & 150 CuM. Capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements Laying of Rising Main, Distribution System with FHTC including different works related to SANTOSHPUR / NAWADA PALANDI /PAPURI / SAJNOR / RAYEN PIPED WATER SUPPLY SCHEME (5 Nos Scheme) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division PHE DTE. | 1951/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2322.64 | 0 | 0 | 5
2364 | BIRBHUM | Bolpur Mechanical | PAPURI PIPED WATER SUPPLY SCHEME , SM/14691 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Papuri Water supply Scheme (T/W-I & II), Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | 4534/BOL.MD | 20/12/2024 | 120 | PADMA ENGINEERING CO. | 73.34 | 0 | 0 | 45
2365 | BIRBHUM | Birbhum Division | KURUMBA PIPED WATER SUPPLY SCHEME , SM/14743 | New | Material Requisition To Resource Division | 1566/BHM | 26/04/2023 | 0 | Resource Division | 27.55 | 0 | 0 | 0
2366 | BIRBHUM | Birbhum Division | KURUMBA PIPED WATER SUPPLY SCHEME , SM/14743 | New | Material Requisition To Resource Division | 1600/BHM | 27/04/2023 | 0 | Resource Division | 27.55 | 0 | 0 | 0
2367 | BIRBHUM | Birbhum Division | KURUMBA PIPED WATER SUPPLY SCHEME , SM/14743 | New | Different works related to water supply scheme at KURUMBA PIPED WATER SUPPLY SCHEME (TSM016231) within LABPUR Block including supply of all Labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 901/BHM | 22/03/2023 | 275 | ESCON INDIA | 440.1 | 0 | 0 | 10
2368 | BIRBHUM | Birbhum Division | KURUMBA PIPED WATER SUPPLY SCHEME , SM/14743 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for KURUMBA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | 112/BSD | 25/03/2022 | 180 | APEX ENGINEERING | 3.87 | 0 | 0 | 100
2369 | BIRBHUM | Central Drilling | KURUMBA PIPED WATER SUPPLY SCHEME , SM/14743 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2370 | BIRBHUM | Birbhum Division | Nichinta Piped Water Supply Scheme (Khoyrasole Block) , SM/16271 | New | Preparation & Submission of DPR for Nichinta & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 136/BSSD | 20/07/2022 | 45 | RADIANT | 1.16 | 0 | 0 | 100
2371 | BIRBHUM | Birbhum Division | Nichinta Piped Water Supply Scheme (Khoyrasole Block) , SM/16271 | New | Material Requisition To Resource Division | 424/BHM | 01/02/2024 | 0 | Resource Division | 18.31 | 0 | 0 | 0
2372 | BIRBHUM | Birbhum Division | Nichinta Piped Water Supply Scheme (Khoyrasole Block) , SM/16271 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
2373 | BIRBHUM | Birbhum Division | Nichinta Piped Water Supply Scheme (Khoyrasole Block) , SM/16271 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
2374 | BIRBHUM | Bolpur Mechanical | Dakhalbati Piped Water Supply Scheme. , SM/18363 | New | Supply and Installation of Low lift Pumping Machinery and other allied work for DHAKALBATI and Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte | 3377/Bol.MD | 13/10/2023 | 90 | M. S. ENTERPRISE | 65.12 | 0 | 0 | 30
2375 | BIRBHUM | Bolpur Mechanical | Dakhalbati Piped Water Supply Scheme. , SM/18363 | New | Supply & Installation of High lift Pumping Mchinery and other allied work for DHAKALBATI & Adjoining moujas water supply scheme within Rampurhat - I Block under Bolpur Mechanical Division PHE Dte. | 3367/BOL.MD | 11/10/2023 | 90 | M. S. ENTERPRISE | 98.53 | 0 | 0 | 50
2376 | BIRBHUM | Birbhum Division | Dakhalbati Piped Water Supply Scheme. , SM/18363 | New | Material Requisition To Resource Division | 2447/BHM | 30/08/2024 | 0 | Resource Division | 40.44 | 0 | 0 | 0
2377 | BIRBHUM | Birbhum Division | Dakhalbati Piped Water Supply Scheme. , SM/18363 | New | Sinking of 200 mm dia Alll through and 25 m deep tubewell , 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 8.00 m X 8.00 m Pump room/ Chlorine room with sanitary arrangements, 350 CuM, 300 CuM, 250 CuM capacity O.H.R. for Zone-I, II and III respectively, 300 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, road restoration for Zone-I, II and III and Providing functional household tap connection related to water supply scheme at DAKHALBATI & its adjoining mouzas water supply scheme within RAMPURHAT-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | 2117/BHM | 29/07/2024 | 365 | M/S GOUTAM DAS | 1419.03 | 0 | 0 | 15
2378 | BIRBHUM | Birbhum Division | MANIKPUR PIPED WATER SUPPLY SCHEME , SM/18509 | New | Material Requisition To Resource Division | 1626/BHM | 28/04/2023 | 0 | Resource Division | 103.84 | 0 | 0 | 0
2379 | BIRBHUM | Birbhum Division | MANIKPUR PIPED WATER SUPPLY SCHEME , SM/18509 | New | Continuation work for "Preparation & Submission of additional Detail Project Report (DPR) for MANIKPUR Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.¿. | 301/BSD | 10/08/2022 | 180 | APEX ENGINEERING | 2.11 | 0 | 0 | 100
2380 | BIRBHUM | Birbhum Division | MANIKPUR PIPED WATER SUPPLY SCHEME , SM/18509 | New | Continuation work for "Preparation & Submission of Detail Project Report (DPR) for MANIKPUR Piped Water Supply Scheme within the command area of Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 244/BSD | 24/06/2022 | 90 | APEX ENGINEERING | 4.92 | 0 | 0 | 100
2381 | BIRBHUM | Central Drilling | MANIKPUR PIPED WATER SUPPLY SCHEME , SM/18509 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2382 | BIRBHUM | Birbhum Division | MANIKPUR PIPED WATER SUPPLY SCHEME , SM/18509 | New | Different works related to water supply scheme at MANIKPUR PIPED WATER SUPPLY SCHEME (TSM/016147) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte.(2nd Call) | 4144/BHM | 19/10/2023 | 712 | M/S SAHA AND MONDAL CONSTRUCTION | 785.13 | 0 | 0 | 15
2383 | BIRBHUM | Bolpur Mechanical | Loba Piped Water Supply Scheme. , SM/18511 | New | Providing electro-mechanical accessories and others for Loba & Adjoining moujas water supply scheme under Bolpur Mechanical Division, PHE Dte | 1915/Bol.MD | 10/08/2023 | 366 | SINHA ELECTRICALS | 129.72 | 0 | 0 | 70
2384 | BIRBHUM | Birbhum Division | Loba Piped Water Supply Scheme. , SM/18511 | New | Material Requisition To Resource Division | 1396/BHM | 24/04/2023 | 0 | Resource Division | 454.99 | 0 | 0 | 0
2385 | BIRBHUM | Bolpur Mechanical | Loba Piped Water Supply Scheme. , SM/18511 | New | Supply & delivery of openwell submersible pumping machinery for Loba Piped water supply scheme under Bolpur Mechanical Division, PHE Dte | 1676./AE-III | 24/10/2024 | 7 | MASSK ENGINEERING WORKS | 2.75 | 0 | 0 | 0
2386 | BIRBHUM | Bolpur Mechanical | Loba Piped Water Supply Scheme. , SM/18511 | New | Supply & delivery of different electrical accessories at Loba Piped water supply scheme under Bolpur Mechanical Division, PHE Dte. | 1310./AE-III | 28/08/2024 | 126 | RMD TRADING | 2.78 | 0 | 0 | 100
2387 | BIRBHUM | Bolpur Mechanical | Loba Piped Water Supply Scheme. , SM/18511 | New | Supply & delivery of different electrical accessories at Loba Piped water supply scheme under Bolpur Mechanical Division P,H,E,Dte. | 1203./AE-III | 16/08/2024 | 10 | J.K.ENGINEERING CO | 0.97 | 0 | 0 | 100
2388 | BIRBHUM | Birbhum Division | Loba Piped Water Supply Scheme. , SM/18511 | New | Different works related to water supply scheme at CHINPAI, LOBA & PARATPUR and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte | 3476/BHM | 08/08/2023 | 816 | B RAI CONSTRUCTION COMPANY | 2497.19 | 0 | 0 | 45
2389 | BIRBHUM | Birbhum Division | Loba Piped Water Supply Scheme. , SM/18511 | New | Road crossing, Repairing & restoration of damaged pipe lines & PCC roads, sluice valve chambers, Construction of 300 Cum OHR, Pump House, Laying Distribution System, Rising Main Connection including all allied works for Loba Piped Water Supply Scheme under Birbhum division, PHE Dte". | 2828/BHM | 11/11/2025 | 365 | S S ENTERPRISE | 260.79 | 0 | 0 | 0
2390 | BIRBHUM | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION , SM/18513 | New | Material Requisition To Resource Division | 1448/BHM | 25/04/2023 | 0 | Resource Division | 72.7 | 0 | 0 | 0
2391 | BIRBHUM | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION , SM/18513 | New | Continuation Work Order for Preparation & Submission of DPR for (CHHOTA TURIGRAM) Water Supply Scheme (Part-B) under Mayureswar-II Development Block. | 380/RSD | 26/09/2022 | 45 | ENVIROTECH SOLUTIONS | 3.29 | 0 | 0 | 100
2392 | BIRBHUM | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION , SM/18513 | New | Continuation Work Order for Preparation & Submission of DPR for (CHHOTA TURIGRAM ) Water Supply Scheme (Part-A) under Mayureswar-II Development Block. | 292/RSD | 02/09/2022 | 45 | ENVIROTECH SOLUTIONS | 3.36 | 0 | 0 | 100
2393 | BIRBHUM | Bolpur Mechanical | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION , SM/18513 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Well and other allied works at Chototurigram PWSS under Bolpur Mechanical Division., Block - Mayureswar - II. | 377/Bol.MD | 06/03/2024 | 45 | CINZANO | 7.75 | 0 | 0 | 100
2394 | BIRBHUM | Bolpur Mechanical | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION , SM/18513 | New | Providing and Installation of Submersible pumping Machineries at newly sunk Ground Water Based Tube Well and other allied works at Chototurigram PWSS under Bolpur Mechanical Division., Block - Mayureswar - II. | 375/Bol.MD | 06/03/2024 | 45 | STANDARD ELECTRICALS | 7.41 | 0 | 0 | 100
2395 | BIRBHUM | Bolpur Mechanical | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION , SM/18513 | New | Supply, Delivery and storage of different Electro-Mechanical Accessories at Chhoto Tuligram PWSS under Bolpur Mechanical Division, PHE,Dte. | 3760/Bol.MD | 12/09/2024 | 111 | HINDOL ROY | 40.82 | 0 | 0 | 100
2396 | BIRBHUM | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION , SM/18513 | New | Material Requisition To Resource Division | 2382/BHM | 27/08/2024 | 0 | Resource Division | 14.74 | 0 | 0 | 0
2397 | BIRBHUM | Bolpur Mechanical | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION , SM/18513 | New | Providing Electro-mechanical accessories and others for Chhoto Turigram PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | 3282/BOL.MD | 29/09/2023 | 763 | SINHA ELECTRICALS | 67.61 | 0 | 0 | 40
2398 | BIRBHUM | Birbhum Division | CHHOTA TULIGRAM PIPED WATER SUPPKY SCHEME OF MAYURESWAR-II BLOCK UNDER BIRBHUM DIVISION , SM/18513 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
2399 | BIRBHUM | Birbhum Division | Bhabani Water Supply Scheme , SM/18351 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHABANIPUR Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - B) | 280/BSD | 22/07/2022 | 90 | M/S R DUTTA & CO. | 4.29 | 0 | 0 | 100
2400 | BIRBHUM | Birbhum Division | Bhabani Water Supply Scheme , SM/18351 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BHABANIPUR Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". (PART - A) | 176/BSD | 29/04/2022 | 90 | M/S R DUTTA & CO. | 4.93 | 0 | 0 | 100
2401 | BIRBHUM | Bolpur Mechanical | Bhabani Water Supply Scheme , SM/18351 | New | New service connection at Bhabanipur PWSS P.H.- I (Block- Illambazar) | BP-2024-2025-86 | 14/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.93 | 0 | 0 | 0
2402 | BIRBHUM | Central Drilling | Bhabani Water Supply Scheme , SM/18351 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2403 | BIRBHUM | Birbhum Division | Bhabani Water Supply Scheme , SM/18351 | New | Different works related to water supply scheme at DHANASAHA, CHHATAR-BANDI, BHABANIPUR, BHUBANESWAR Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | 4141/BHM | 19/10/2023 | 709 | B RAI CONSTRUCTION COMPANY | 2996.46 | 0 | 0 | 5
2404 | BIRBHUM | Birbhum Division | Bhabani Water Supply Scheme , SM/18351 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
2405 | BIRBHUM | Birbhum Division | Sahapur Piped Water Supply Scheme. , SM/18520 | New | Material Requisition To Resource Division | 1512/BHM | 26/04/2023 | 0 | Resource Division | 154.79 | 0 | 0 | 0
2406 | BIRBHUM | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. , SM/18520 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Sahapur PWSS under Dubrajpur Block in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 533/BOL.MD | 14/03/2024 | 60 | M/S.S.S. ENTERPRISE | 7.62 | 0 | 0 | 0
2407 | BIRBHUM | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. , SM/18520 | New | Supply and delivery of 6 mm2 x3 core Al.Ar XLPE Cable for Sahapur water supply scheme.(Block-Dubrajpur) under Bolpur Mechanical Division, PHE. Dte. | 1191./AE-III | 12/08/2024 | 10 | R.K.ENTERPRISE | 0.98 | 0 | 0 | 0
2408 | BIRBHUM | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. , SM/18520 | New | Providing Electro-mechanical accessories and others for Sahapur and Adjoining moujas water supply scheme under Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | 562/BOL.MD | 15/03/2024 | 30 | BENGAL CONSTRUCTION | 3.84 | 0 | 0 | 0
2409 | BIRBHUM | Birbhum Division | Sahapur Piped Water Supply Scheme. , SM/18520 | New | Continuation Work Order for Preparation & Submission of DPR for (SAHAPUR) Water Supply Scheme (Part-B) under Rampurhat-II Development Block. | 358/RSD | 15/09/2022 | 45 | ECO CARE | 2.91 | 0 | 0 | 100
2410 | BIRBHUM | Birbhum Division | Sahapur Piped Water Supply Scheme. , SM/18520 | New | Continuation Work Order for Preparation & Submission of DPR for (SAHAPUR) Water Supply Scheme (Part-A) under Rampurhat-II Development Block. | 285/RSD | 26/08/2022 | 45 | ECO CARE | 3.63 | 0 | 0 | 100
2411 | BIRBHUM | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. , SM/18520 | New | Installation of Submersible pumping Machineries at newly sunk Tube Wells and allied works at Sahapur PWSS, Block- Dubrajpur under Bolpur Mechanical Division. | 3800/BOL.MD | 12/09/2024 | 30 | SWAPAN ENTERPRISE | 6.82 | 0 | 0 | 100
2412 | BIRBHUM | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. , SM/18520 | New | Supply, Delivery & Installation of Submersible Pumpining Machinery at newly sunk River Bed Tube well no - 1, 2 ,3 and other allied works at Sahapur Piped water supply scheme (Block- Rampurhat II) | 371/BOL.MD | 06/03/2024 | 30 | CINZANO | 16.91 | 0 | 0 | 100
2413 | BIRBHUM | Birbhum Division | Sahapur Piped Water Supply Scheme. , SM/18520 | New | Material Requisition To Resource Division | 2444/BHM | 30/08/2024 | 0 | Resource Division | 29.08 | 0 | 0 | 0
2414 | BIRBHUM | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. , SM/18520 | New | Quotation for new service connection at Sahapur TW No-II (Block-Rampurhat-II) | BP-2023-24-305 | 18/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.21 | 0 | 0 | 0
2415 | BIRBHUM | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. , SM/18520 | New | WBSEDCL QUOTATION FOR SAHAPUR TW-1 | BP-2023-24-306 | 18/03/2024 | 0 | WBSEDCL | 4.89 | 0 | 0 | 0
2416 | BIRBHUM | Bolpur Mechanical | Sahapur Piped Water Supply Scheme. , SM/18520 | New | Providing Electro-mechanical accessories and others for Sahapur PWSS at Rampurhat - II Block under Bolpur Mechanical Division PHE Dte. | 2235/Bol.MD | 12/09/2023 | 597 | QUAZI NOZRUL ISLAM | 44.39 | 0 | 0 | 50
2417 | BIRBHUM | Birbhum Division | Sahapur Piped Water Supply Scheme. , SM/18520 | New | Sinking of 250 mm. X 200 mm Dia deep tubewell ,250 CuM capacity CWR, Pump room/ Chlorine room with/without sanitary arrangements( different size),and laying of Rising main,Distribution System (Zone -I & II ) with FHTC and different works related to SAHAPUR & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 2126/BHM | 30/07/2024 | 365 | KINGS & CO. | 685.99 | 0 | 0 | 20
2418 | BIRBHUM | Birbhum Division | Sahapur Piped Water Supply Scheme. , SM/18520 | New | Soil Investigation & Construction of Over Head Reservoir of capacity 350 Cum (Zone-I) & 300 Cum (Zone-II) related to water supply scheme at SAHAPUR & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 2160/BHM | 20/08/2025 | 365 | ARPAN PANDIT | 215.34 | 0 | 0 | 0
2419 | BIRBHUM | Birbhum Division | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/18521 | New | Material Requisition To Resource Division | 1461/BHM | 25/04/2023 | 0 | Resource Division | 84.55 | 0 | 0 | 0
2420 | BIRBHUM | Bolpur Mechanical | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/18521 | New | Providing Electro-mechanical accessories and others for Dakshingram PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte | 3476/Bol.MD | 07/11/2023 | 60 | S.P. CONSTRUCTION | 55.2 | 0 | 0 | 40
2421 | BIRBHUM | Bolpur Mechanical | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/18521 | New | Supply and Installation of Submersible pumping machineries and other electromechanical equipments at Dakhingram PWSS under Mayureswar Block-I in the Dist of Birbhum under Bolpur Mechanical Division,P.H.E.Dte. | 402/Bol.MD | 07/03/2024 | 45 | EASTERN INDIA SALES & SERVICE | 24.53 | 0 | 0 | 0
2422 | BIRBHUM | Birbhum Division | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/18521 | New | Continuation Work Order for Preparation & Submission of DPR for (DAKSHIN GRAM) Water Supply Scheme (Part-B) under Mayureswar-I Development Block. | 376/RSD | 23/09/2022 | 90 | ENVIROTECH SOLUTIONS | 2.86 | 0 | 0 | 100
2423 | BIRBHUM | Birbhum Division | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/18521 | New | Continuation Work Order for Preparation & Submission of DPR for (DAKSHIN GRAM) Water Supply Scheme (Part-A) under Mayureswar-I Development Block. | 291/RSD | 02/09/2022 | 90 | ENVIROTECH SOLUTIONS | 3.43 | 0 | 0 | 100
2424 | BIRBHUM | Birbhum Division | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/18521 | New | Material Requisition To Resource Division | 205/BHM | 22/01/2024 | 0 | Resource Division | 7.15 | 0 | 0 | 0
2425 | BIRBHUM | Bolpur Mechanical | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/18521 | New | WBSEDCL QUOTATION FOR DAKSHINGRAM PUMP HOUSE NO-I | BP-2023-24-287 | 04/03/2024 | 0 | WBSEDCL | 6.44 | 0 | 0 | 0
2426 | BIRBHUM | Bolpur Mechanical | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/18521 | New | Quotation for new connection at Dakshingram PWSS P/H-2 (Block-Mayureswar -I) | BP-2024-2025-26 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.53 | 0 | 0 | 0
2427 | BIRBHUM | Bolpur Mechanical | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/18521 | New | Quotation For new connection at Dakshingram PWSS P/H -3 (Block- Mayureswar-I) | BP-2024-2025-25 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.32 | 0 | 0 | 0
2428 | BIRBHUM | Birbhum Division | Dakshin Gram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division , SM/18521 | New | Different works related to water supply scheme at LACHHIATOR, DAKSHINGRAM, SONJ & SHIBGRAM and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 4142/BHM | 19/10/2023 | 805 | B RAI CONSTRUCTION COMPANY | 2003.84 | 0 | 0 | 60
2429 | BIRBHUM | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area , SM/06948 | Retrofitting | Work order for collection of Household Data through Mobile App/Hard copy including Geo-reference and submission of the same in soft copy against completed FHTC works at the command area of Murarai W/S Scheme under Birbhum Division | 145/BH | 07/09/2021 | 10 | M/S S.N CONSTRUCTION | 0.1 | 0 | 0 | 0
2430 | BIRBHUM | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area , SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 508/AE/NSD | 01/10/2021 | 45 | SHIB GANGA CONSTRUCTION | 4.67 | 0 | 0 | 67
2431 | BIRBHUM | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area , SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Gopalpur in Gopalpur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.15) | 1710/BHM | 23/12/2020 | 60 | SUNIL RABI DAS | 29.13 | 58.25 | 100 | 100
2432 | BIRBHUM | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area , SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Ramchandrapur, Kestara in Gopalpur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.14) | 1712/BHM | 23/12/2020 | 60 | MLG CONSTRUCTION | 37.12 | 74.96 | 200 | 100
2433 | BIRBHUM | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area , SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Ramchandrapur and Kestora under Murarai-I Block within the command area of Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 509/AE/NSD | 01/10/2021 | 45 | SUPRABHAT RABIDAS | 4.66 | 0 | 0 | 33
2434 | BIRBHUM | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area , SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area in the villages Ramchandrapur in Gopalpur w/s Scheme at under Nalhat Sub Division, PHE Dte. (Sl. No.13) | 1711/BHM | 23/12/2020 | 60 | UMWELT ENGINEER PVT. LTD | 31.5 | 62.59 | 200 | 100
2435 | BIRBHUM | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area , SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply Scheme (Zone-II) under Nalhati Sub Division within Birbhum Division PHED. | 229/AE/NSD | 21/04/2022 | 45 | MD ZIAUL ISLAM | 3.34 | 0 | 0 | 0
2436 | BIRBHUM | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area , SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 508/AE/NSD | 01/10/2021 | 45 | SHIB GANGA CONSTRUCTION | 4.67 | 0 | 0 | 67
2437 | BIRBHUM | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area , SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Ramchandrapur and Kestora under Murarai-I Block within the command area of Gopalpur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 509/AE/NSD | 01/10/2021 | 45 | SUPRABHAT RABIDAS | 4.66 | 0 | 0 | 33
2438 | BIRBHUM | Birbhum Division | Retrofitting works of Gopalpur (Phase-I) water supply scheme under Murarai Block for providing Functional Household Tap Connection (FHTC) within command area , SM/06948 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Gopalpur Water Supply Scheme (Zone-II) under Nalhati Sub Division within Birbhum Division PHED. | 383/AE/NSD | 10/08/2022 | 45 | MD ZIAUL ISLAM | 3.34 | 0 | 0 | 50
2439 | BIRBHUM | Birbhum Division | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area , SM/06950 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Narayanghati w/s Scheme in Rampurhat Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-2) | 1915 /BHM | 24/11/2021 | 60 | TAPAN KUMAR DATTA | 82.11 | 78.79 | 100 | 100
2440 | BIRBHUM | Birbhum Division | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area , SM/06950 | Retrofitting | Laying of HDPE Pipe line for Akna, Balur, Nima dangal at diff mouzas for providing FHTC under Narayanghati Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | 123/RSD | 11/03/2022 | 30 | TAPAN KUMAR DATTA | 4.93 | 0 | 0 | 0
2441 | BIRBHUM | Birbhum Division | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area , SM/06950 | Retrofitting | Laying of HDPE Pipe line for Narayanghati mouza for providing FHTC under Narayanghati Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | 125/RSD | 11/03/2022 | 30 | TAPAN KUMAR DATTA | 4.98 | 4.66 | 100 | 100
2442 | BIRBHUM | Birbhum Division | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area , SM/06950 | Retrofitting | Laying of HDPE Pipe line for Induripara at Balur mouza for providing FHTC under Narayanghati Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | 122/RSD | 11/03/2022 | 30 | TAPAN KUMAR DATTA | 4.94 | 9.02 | 100 | 100
2443 | BIRBHUM | Birbhum Division | Retrofitting works of Narayanghati under Mayureswar-II Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area , SM/06950 | Retrofitting | Laying of HDPE Pipe line for Kalikapur, Mahalas at Kalikapur mouza for providing FHTC under Narayanghati Piped Water Supply Scheme under Rampurhat sub -Division, under Birbhum Division, PHE Dte. | 124/RSD | 11/03/2022 | 30 | TAPAN KUMAR DATTA | 4.96 | 4.45 | 100 | 100
2444 | BIRBHUM | Birbhum Division | Retrofitting works of Harisara under Nalhati - I Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area , SM/06951 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Harisara w/s Scheme in Nalhati Sub-Division under Birbhum Division, PHE Dte. (Sl. No.-6) | 1334/BHM | 18/08/2021 | 60 | PRAVAT SARKAR | 55.76 | 53.11 | 50 | 100
2445 | BIRBHUM | Birbhum Division | Retrofitting works of Harisara under Nalhati - I Block PWSS for providing Functional Household Tap Connection (FHTC) within the command area , SM/06951 | Retrofitting | Extention of UPVC pipe line to the Harisara habitation within Harisara PWSS under Nalhati Sub-Division within Birbhum Division, PHE Dte. | 524/AE/NSD | 08/10/2021 | 30 | B.M.SARKAR | 4.82 | 0 | 0 | 0
2446 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Bhabanandapur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 510/AE/NSD | 01/10/2021 | 45 | SURJASISH DATTA | 4.67 | 0 | 0 | 50
2447 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Nasipur Dakshinpara and its adjoining areas, under Nasipur Habitation within Bhabanandapur village (J.L.-24) under Nalhati-1 Block within the command area of Bhabanandapur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division, P.H.E. Dte. | 53/AE/NSD | 08/02/2021 | 60 | MD SHAHAJAMAL | 4.98 | 4.98 | 100 | 100
2448 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Bhabanandapur Paschimpara and it's adjoining areas, under Bhabanandapur Habitation under Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 50/AE/NSD | 08/02/2021 | 60 | SURJASISH DATTA | 4.59 | 9.18 | 200 | 50
2449 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Jerapara, Nachpahari,Sialdanga, Tarapur Hbitations and it's adjoining areas, under Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 51/AE/NSD | 08/02/2021 | 60 | KAZI ZAKIR HOSSAIN | 4.97 | 0 | 0 | 100
2450 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Nasihapur uttarpara and adjoining areas under Nasihapur Habitation, within Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 52/AE/NSD | 08/02/2021 | 60 | NUR MOBINUL ISLAM | 4.98 | 0 | 0 | 0
2451 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Bhabanandapur Paschimpara and it's adjoining areas, under Bhabanandapur Habitation under Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 50/AE/NSD | 08/02/2021 | 60 | SURJASISH DATTA | 4.59 | 0 | 0 | 50
2452 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Nasipur Uttarpara and its and adjoining areas under Nasipur Habitaiton within Bhabanandapur villages (JL no 24)under Nalhati I Block within the command area of Bhabandaapur water supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (SL no. 03) | 52/NSD | 08/02/2021 | 60 | NUR MOBINUL ISLAM | 4.98 | 9.96 | 200 | 100
2453 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Nasihapur Purba para and it's adjoining areas, under Nasihapur Habitation under Bhabanandapur Village (J.L:-24) under Nalhati - I Block, within the command area of Bhabanandapur W/S scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 54/AE/NSD | 08/02/2021 | 60 | GOLAM RASUL | 4.98 | 9.96 | 200 | 100
2454 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in different habitations under Bhabanandapur Water Supply scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. | 510/AE/NSD | 01/10/2021 | 45 | SURJASISH DATTA | 4.67 | 4.67 | 100 | 50
2455 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Supply of one No. Diesel driven Motor Cab/Maxi Car (Air Condition) on hire basis under the Executive Engineer, Birbhum Division, P.H.E Dte. (Period from 01.11.2022 to 30.04.2023) | 2322/BHM | 28/10/2022 | 184 | PREMANANDA ROY BISWAS | 0.96 | 2.38 | 100 | 84
2456 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Extention of UPVC pipeline for providing FHTC in different habitation under Bhabanandapur Water Supply Scheme under Nalhati Sub-Division within Birbhum Division PHED. | 264/AE/NSD | 11/05/2022 | 45 | ASGAR SK | 4.84 | 4.81 | 100 | 100
2457 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Extension of UPVC pipe line for providing FHTC at Bhabanandapur habitation under Bhabanandapur PWSS under Nalhati Sub-Division, within Birbhum Division P.H.E Dte. | 281/NSD | 20/05/2022 | 30 | SURJASISH DATTA | 1.45 | 1.42 | 100 | 100
2458 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Sinking of replacement the tubewell 200mm dia & 87 m. deep with PVC pipe and fibre glass Strainer at Bhabanandapur (near head work side) PWSS under Nalhati Sub-Division within Birbhum Division,PHE Dte. | 207/AE/NSD | 05/04/2022 | 30 | A R ENTERPRISE | 4.79 | 0 | 0 | 100
2459 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Extention of pipeline by HDPE pipe at Nasipur habitation for providing FHTC of Bhabanandapur W/S Scheme, under Nalhati Sub-Division within Birbhum Division P.H.E. Dte. | 279/NSD | 20/05/2022 | 30 | MD ASIF ALI | 2.16 | 2.15 | 100 | 100
2460 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Laying distribution system for proposed augmentation scheme for Bara Zone-II Piped Water Supply Scheme under Nalhati-II Block, under Birbhum Division, PHE Dte.(Sl. No.1) | 805/BHM | 12/04/2022 | 180 | MANASH GHOSH | 397.16 | 1.55 | 100 | 100
2461 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Continuation Work Order for Supply of one no. diesel driven Motor Cab (Non Air-conditioned) on hire basis for official uses of the Assistant Engineer, Birbhum Sadar Sub-Division, P.H.E Dte. (Period from 01.09.2021 to 28.02.2022) | 305/BSSD | 31/05/2021 | 183 | RITA RABIDAS | 0.71 | 1.73 | 100 | 60
2462 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Hiring of SWIFT DIZER (Diesel) or equivalent luxury car for office of the Assistant Engineer, Nalhati Sub - Division under Birbhum Division, PHE Dte. (Period from 01.10.2023 to 31.03.2024) 182-Days. | 353/NSD | 29/09/2023 | 182 | JOY CHAND MAL | 0.86 | 0 | 0 | 100
2463 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Continuation Work of Hiring of Ambassador Car (Diesel) registered Luxury Taxi for the office of the Assistant Egineer, Rampurhat Sub-Division P.H.E. Dte. for 24 hours service including Driver and also including the cost of fuel & lubricants as per terms & condition for 364 days (from 02.07.2021 to 30.06.2022) for 364 days (from 02.07.2022 to 30.06.2023). | 223/RSD | 23/06/2022 | 364 | SOUMITA PAL | 2.04 | 2.36 | 100 | 50
2464 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system in Jerapara, Nachpahari, Sialdanga & Tarapur habitation & its adj. areas under Bhabanandapur Village (JL No.24) under Nalhati-I Block, within the command area of Bhabanandapur w/s Scheme under Nalhati Sub Division within Birbhum Division, PHE Dte. (Sl. No.03) | 51/NSD | 08/02/2021 | 30 | KAZI ZAKIR HOSSAIN | 4.97 | 9.95 | 200 | 0
2465 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Providing functional house hold tap connection (FHTC) form existing distribution system in Bhabanandapur Dakshinpara and its adjoining areas of Bhabanandapur Habitation under Bhabanandapur Mouza (J.L.24) under Nalhati-I Block within the command area of Bhabanandapur WS Scheme.(Sl.No.02) | 1649/BHM | 18/12/2020 | 90 | ASGAR SK | 4.7 | 9.4 | 200 | 0
2466 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in Bhabanandapur purbapara and its adjoining areas of Bhabanandapur Habitation under Bhabanandapur Mouzas (Jl.24) under Nalhati -I of Bhabanandapur Wsater Supply scheme (Sl.no.03) | 1650/BHM | 18/12/2020 | 120 | SURJASISH DATTA | 4.67 | 9.33 | 100.84 | 0
2467 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system in Bhabanandapur Uttarpara and Its adjoining areas of Bhabanandapur Habitation under Bhabanandapur Mouza (JL.24) under Nalhati -I Block. of Bhabanandapur Water Supply Scheme (Sl.No.01) | 1648/BHM | 18/12/2020 | 90 | A R ENTERPRISE | 4.74 | 9.49 | 200 | 0
2468 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection(FHTC) under Bhabanandapur PWSS , SM/06744 | Retrofitting | Extention of Pipeline along with FHTC at left out habitations of BHABANANDAPUR PWSS under Nalhati Sub-Division within Birbhum Division P.H.E. Dte. (Sl. No.11) | 289/BHM | 01/02/2023 | 225 | M/S SARADA CONSTRUCTION. | 16.48 | 9.46 | 57.36 | 100
2469 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area INDUS WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. , SM/08895 | Retrofitting | Rising Main Pipe line from TW1, TW2 to OHR including of CI specials for proposed INDUS piped Water Supply Scheme, under Bolpur Sub-Division within Birbhum Division, PHE Dte. (Sl. No.: 1) | 21/BSD | 29/01/2021 | 30 | SYED HASMAT ALI | 1.45 | 0 | 0 | 100
2470 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area INDUS WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. , SM/08895 | Retrofitting | Supply and delivery of 80mm dia. Sluice Valves, including loading, carriage and unloading at Bolpur Sub-Divisional Store at PHE Complex, Surul, Bolpur, Dist. - Birbhum for Indas Water Supply Scheme under Bolpur Sub-Division within Birbhum Division, PHED. (Sl. No.: 03). | 27/BSD | 21/01/2022 | 15 | MAKALI ENGINEERING CORPORATION | 0.65 | 0 | 0 | 100
2471 | BIRBHUM | Birbhum Division | Retrofitting works for providing Functional Household Tap Connection (FHTC) within the command area INDUS WATER SUPPLY SCHEME of Labpur Block under Birbhum Division, PHE Dte. , SM/08895 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of "INDUS W/S Scheme in Bolpur Sub-Division under Birbhum Division, PHE Dte. " (Sl. No. 05) | 2065/BHM | 13/12/2021 | 60 | QUAZI SIRAJUL ISLAM. | 61.02 | 35.46 | 83.81 | 100
2472 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09366 | Retrofitting | Supply & delivery of Sluice Valve for augmentation of Sadashibpur (Bisor) W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, PHE Dte. (Sl. No.-03) | 715/BHM | 31/03/2022 | 15 | MAKALI ENGINEERING CORPORATION | 4.99 | 0 | 0 | 100
2473 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09366 | Retrofitting | Balance works of Laying Distribution system at Sadasibpur, Kendishta, Chhatina and Amudda habitations under Sadashibpur W/S Scheme under Nalhati Sub-Division, within Birbhum Division P.H.E Dte.. (SL.No.5) | 498/BHM | 02/03/2022 | 45 | SUPER SKILL | 47 | 0 | 0 | 100
2474 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09366 | Retrofitting | Restoration of concrete road including dismantling of Water Supply Scheme For Sadashibpur and it's adjoining Mouzas under Nalhati Sub-Division, within Birbhum Division P.H.E Dte. | 356/AE/NSD | 20/07/2022 | 60 | SUPER SKILL | 4.83 | 0 | 0 | 100
2475 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09366 | Retrofitting | Supply & delivery of Sluice Valve for Sadashibpur (Bishor) W/S Scheme under Birbhum Division, PHE Dte including loading, carriage and uploading at Birbhum Divisional Store at PHE Complex, Dist.-Birbhum under Birbhum Division, PHE Dte (Sl. No.-03) | 1243/BHM | 03/06/2022 | 15 | MAKALI ENGINEERING CORPORATION | 4.99 | 0 | 0 | 100
2476 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09366 | Retrofitting | Balance work for Pump House at Head Work site of Sadashibpur PWSS under Nalhati Sub-Division within Birbhum Division, PHED. | 168/AE/NSD | 22/03/2022 | 15 | SUBHRANIL DAS | 0.83 | 0 | 0 | 100
2477 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09366 | Retrofitting | Material Requisition To Resource Division | 213/BHM | 02/02/2022 | 0 | Resource Division | 15.63 | 0 | 0 | 0
2478 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09366 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sadashibpur (Bisor) Water Supply Scheme within Nalhati Sub-Division Birbhum Division, PHE Dte. (Sl. No.1) | 822/BHM | 13/04/2022 | 60 | QUAZI SIRAJUL ISLAM. | 94.04 | 59.79 | 97.54 | 100
2479 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Sadasibpur (Bisor) PWSS within Murarai-II Block District Birbhum under Birbhum Division, PHE Dte. , SM/09366 | Retrofitting | Balance work of distribution pipeline including extention of pipeline along with FHTC and restoration of roads alongwith Construction of 500 M³ capacity 20.00 Mtr. staging height RCC Over Head Reservoir at Sadasibhpur W/S Scheme within Nalhati Sub-Division under Birbhum Division, P.H.E. Dte.(Sl. No.3) | 2857/BHM | 22/12/2022 | 557 | SUPER SKILL | 175.35 | 43.77 | 47.93 | 100
2480 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. , SM/09341 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of village Kuralmita, Muktipur under Block Rajnagar for ensuing draught like situation within Birbhum Division, PHE Dte. (Sl. No. - 02) | 000079 | 28/09/2022 | 30 | ROY BISWAS CONSTRUCTION | 0 | 0 | 0 | 0
2481 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. , SM/09341 | Retrofitting | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Bandirban Zone-VI Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte | 2709/BHM | 24/09/2024 | 90 | BISWARUP GHOSH | 95 | 0 | 0 | 0
2482 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. , SM/09341 | Retrofitting | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Junedpur in Suri I, II & Sainthia covered under Bhandirbon Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte. | 1023/BHM | 15/03/2024 | 60 | ARKA JYOTI GHOSH | 31.99 | 0 | 0 | 25
2483 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. , SM/09341 | Retrofitting | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Itagoria in Suri I covered under Bandirban Water Supply Scheme under Suri Sadar-Sub Division within Birbhum Division, PHE Dte. | 1021/BHM | 15/03/2024 | 60 | RANJIT GHOSH | 29.38 | 0 | 0 | 40
2484 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. , SM/09341 | Retrofitting | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Choto Alaunda in Suri I covered under Bandirban Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte. | 1025/BHM | 15/03/2024 | 123 | BHABANI ENTERPRISE | 30.93 | 0 | 0 | 35
2485 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. , SM/09341 | Retrofitting | Distribution System including providing Functional Household Tap Connection (FHTC) within the command area of Bandirban Zone-V Water Supply Scheme under Suri Sadar Sub-Division within Birbhum Division, PHE Dte. | 1038/BHM | 15/03/2024 | 487 | SOUMEN CHATTERJEE | 48.94 | 0 | 0 | 35
2486 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. , SM/09341 | Retrofitting | Laying of distribution system including FHTC at Bandirban (Kanmara) Zone I, II, III Tasarkata, Ranpur & Lambodarpur Zone IV, Zone- V, VI Piped Water Supply Scheme, Suri-I Block under Birbhum Sadar Sub-Division, P.H.E. Dte. Within Birbhum Division P.H.E. Dte. | 611/BHM | 03/03/2025 | 90 | SYED KHORSED ALAM | 183.69 | 0 | 0 | 0
2487 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. , SM/09341 | Retrofitting | Laying of distribution system including FHTC at Karidhya, Kalipur, Amaipur, Laksmindarpur, Baramahula Chhora & Brojergram Mouza for Bandirban (Kanmara) Zone IV Piped Water Supply Scheme, Suri-I Block under Birbhum Sadar Sub-Division, P.H.E. Dte. Within Birbhum Division P.H.E. Dte. | 431/BHM | 10/02/2025 | 203 | PREMANANDA ROY BISWAS | 189.3 | 0 | 0 | 75
2488 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. , SM/09341 | Retrofitting | Construction of 300 Cum capacity and 20.0m staging height RCC Over Head Reservoir & Laying distribution system including all allied works as per departmental drawing (DRG. No. PC-I/OHR/07/2012) at Zone-V under the Piped Water Supply Scheme for Bandirban (Kanmara) Suri-I & Rajnagar Block under Birbhum Division, PHE Dte (Sl. No.5) | 1994/BHM | 07/12/2021 | 1093 | APURBA MONDAL | 180.84 | 0 | 0 | 87
2489 | BIRBHUM | Birbhum Division | Retrofitting works for providing functional household tap connection (FHTC) under Bhandirban (Kanmara) PWSS within Suri-I Block & Rajnagar District Birbhum under Birbhum Division, PHE Dte. , SM/09341 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Zone-IV under Bandirban Water Supply Water Supply Scheme within Birbhum Division, PHE Dte | 729/BHM | 28/02/2024 | 361 | S R ENTERPRISE | 83.89 | 0 | 0 | 95
2490 | BIRBHUM | Bolpur Mechanical | Augmentation of Nagari Piped Water Supply Scheme , SM/10312 | Augmentation | Providing and Installation of Submersible pumping Machineries at newly sunk Tube Wells and allied works at Augmentation of Nagari Piped Water Supply Scheme, Block-Suri-I under Bolpur Mechanical Division, PHE Dte. | 2223/Bol.MD | 12/09/2023 | 60 | HINDOL ROY | 23.52 | 0 | 0 | 50
2491 | BIRBHUM | Birbhum Division | Augmentation of Nagari Piped Water Supply Scheme , SM/10312 | Augmentation | Material Requisition To Resource Division | 1114/BHM | 10/04/2023 | 0 | Resource Division | 2.73 | 0 | 0 | 0
2492 | BIRBHUM | Birbhum Division | Augmentation of Nagari Piped Water Supply Scheme , SM/10312 | Augmentation | Material Requisition To Resource Division | 970/BHM | 27/03/2023 | 0 | Resource Division | 11.88 | 0 | 0 | 0
2493 | BIRBHUM | Birbhum Division | Augmentation of Nagari Piped Water Supply Scheme , SM/10312 | Augmentation | Material Requisition To Resource Division | 3275/BHM | 27/07/2023 | 0 | Resource Division | 0.34 | 0 | 0 | 0
2494 | BIRBHUM | Birbhum Division | Augmentation of Nagari Piped Water Supply Scheme , SM/10312 | Augmentation | Construction of 150 Cum Capacity and 20.0m Staging Height RCC Over Head Reservoir along with Soil Test and Laying pipeline for Augmentation of Nagari w/s Scheme under Birbhum Sadar Sub-Division within Birbhum Division,P.H.E. Dte. (Sl. No.6) | 105/BHM | 11/01/2023 | 180 | M/S KRIPASINDHU GHOSH & CO. | 189.64 | 81.15 | 42.79 | 75
2495 | BIRBHUM | Bolpur Mechanical | Augmentation of Nagari Piped Water Supply Scheme , SM/10312 | Augmentation | Replacement of Centrifugal Pumping Machinery and allide works at Karidhya water supply scheme (Suri-I) under Bolpur Mechanical Division, P.H.E. Dte. | 3799/BOL.MD | 12/09/2024 | 30 | WEST BENGAL ENGINEERING CO. | 10.68 | 0 | 0 | 0
2496 | BIRBHUM | Birbhum Division | Augmentation of Nagari Piped Water Supply Scheme , SM/10312 | Augmentation | Trial Bore and Sinking for 03 nos. working 200mm dia. Tubewell of 6m depth each with horizontal strainer on the river Bed of Kuskurini and connecting pipe line etc. complete under Augmentation of Nagari Piped Water Supply Scheme under Birbhum Sadar Sub-Division, P.H.E Dte. within Birbhum Division P.H.E. Dte. | 652/BHM | 20/02/2024 | 45 | INDRANIL DUTTA | 7.99 | 0 | 0 | 100
2497 | BIRBHUM | Bolpur Mechanical | Augmentation of Nagari Piped Water Supply Scheme , SM/10312 | Augmentation | Supply & delivery of 80mm dia Column Pipe for Augmentation of Nagari water supply scheme (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. " | 1450./AE-III | 09/09/2024 | 7 | VIBGYOR INFOTECH | 2.96 | 0 | 0 | 100
2498 | BIRBHUM | Bolpur Mechanical | Augmentation of Nagari Piped Water Supply Scheme , SM/10312 | Augmentation | Quotation for new service connection at Augmentation of Nagari PWSS at SURI-I Block | BP-24-25-270 | 04/12/2024 | 0 | WBSEDCL | 6.24 | 0 | 0 | 0
2499 | BIRBHUM | Bolpur Mechanical | Augmentation of Nagari Piped Water Supply Scheme , SM/10312 | Augmentation | Supply & delivery of Electrical accessories for Augmentation of Nagari water supply scheme (Block- Suri - I) under Bolpur Mechanical Division, PHE Dte. | 1301./AE-III | 27/08/2024 | 111 | HINDOL ROY | 2.8 | 0 | 0 | 100
2500 | BIRBHUM | Birbhum Division | Meherpur and Adjoining Mouzas PWSS , SM/12457 | New | Material Requisition To Resource Division | 1417/BHM | 24/04/2023 | 0 | Resource Division | 21.84 | 0 | 0 | 0
2501 | BIRBHUM | Birbhum Division | Meherpur and Adjoining Mouzas PWSS , SM/12457 | New | Material Requisition To Resource Division | 2491/BHM | 03/09/2024 | 0 | Resource Division | 9.36 | 0 | 0 | 0
2502 | BIRBHUM | Bolpur Mechanical | Meherpur and Adjoining Mouzas PWSS , SM/12457 | New | Providing Electro-mechanical accessories and others for Meherpur & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2092/Bol.MD | 22/08/2023 | 647 | A.S.ENTERPRISE | 28.01 | 0 | 0 | 60
2503 | BIRBHUM | Birbhum Division | Meherpur and Adjoining Mouzas PWSS , SM/12457 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house without sanitary arrangements, 200 CuM capacity O.H.R, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at MEHERPUR & its adjoining mouzas water supply scheme within Sainthia Block including supply of all labour & materials under BIRBHUM Division, PHE Dte" | 2264/BHM | 14/08/2024 | 715 | PRANAB KUMAR GHOSH | 327.36 | 0 | 0 | 0
2504 | BIRBHUM | Birbhum Division | Meherpur and Adjoining Mouzas PWSS , SM/12457 | New | Sinking of 02(Two) nos. 200mm X 200 mm X 174m deep Tube Wells Fitted With M.S Housing & Well Pipe by Direct Rotary Rig for Meharpur and Adjacent areas Piped Water Supply Scheme, Block: Sainthia under Birbhum Division, P.H.E Dte. | 259/BHM | 21/01/2025 | 60 | WEIR AND DECK CONSTRUCTION ENGINEERS CO OP SOCIETY LTD | 24.15 | 0 | 0 | 0
2505 | BIRBHUM | Birbhum Division | Meherpur and Adjoining Mouzas PWSS , SM/12457 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
2506 | BIRBHUM | Birbhum Division | Kamarkhul Piped Water Supply Scheme. , SM/12693 | New | Material Requisition To Resource Division | 1517/BHM | 26/04/2023 | 0 | Resource Division | 13.34 | 0 | 0 | 0
2507 | BIRBHUM | Birbhum Division | Kamarkhul Piped Water Supply Scheme. , SM/12693 | New | Different works related to water supply scheme at KASHIMNAGAR, KAMARKHUL & GAGANPUR and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3647/BHM | 25/08/2023 | 274 | BENGAL ENGINEERING | 1204.06 | 0 | 0 | 30
2508 | BIRBHUM | Bolpur Mechanical | Kamarkhul Piped Water Supply Scheme. , SM/12693 | New | Quotation deposit for Kamarkhur Water Supply Scheme P/H-I in Paikar CCC under Bolpur Mechanical division, PHE Dte | BP-24-25-182 | 23/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.97 | 0 | 0 | 0
2509 | BIRBHUM | Bolpur Mechanical | Kamarkhul Piped Water Supply Scheme. , SM/12693 | New | Providing Electro-mechanical accessories and others for KAMARKHUL piped water supply scheme, Murarai-II block, under Bolpur Mechanical Division PHE Dte. | 2141/Bol.MD | 25/08/2023 | 950 | M. S. ENTERPRISE | 27.82 | 0 | 0 | 40
2510 | BIRBHUM | Birbhum Division | Kamarkhul Piped Water Supply Scheme. , SM/12693 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
2511 | BIRBHUM | Birbhum Division | Harinduba Piped Water Supply Scheme. , SM/12692 | New | Material Requisition To Resource Division | 1570/BHM | 26/04/2023 | 0 | Resource Division | 27.14 | 0 | 0 | 0
2512 | BIRBHUM | Bolpur Mechanical | Harinduba Piped Water Supply Scheme. , SM/12692 | New | Providing Electro-mechanical accessories and others for HARINDUBA piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 3294/Bol.MD | 29/09/2023 | 550 | M/S SWAPAN BANERJEE | 27.4 | 0 | 0 | 0
2513 | BIRBHUM | Birbhum Division | Balijuri Piped Water Supply Scheme. , SM/12682 | New | Material Requisition To Resource Division | 1389/BHM | 24/04/2023 | 0 | Resource Division | 137.77 | 0 | 0 | 0
2514 | BIRBHUM | Birbhum Division | Balijuri Piped Water Supply Scheme. , SM/12682 | New | Material Requisition To Resource Division | 3267/BHM | 02/12/2024 | 0 | Resource Division | 15.81 | 0 | 0 | 0
2515 | BIRBHUM | Bolpur Mechanical | Balijuri Piped Water Supply Scheme. , SM/12682 | New | Providing Electro-mechanical accessories and others for Balijuri & Adjoining moujas water supply scheme at Dubrajpur Block under Bolpur Mechanical Division PHE Dte. | 3381/Bol.MD | 16/10/2023 | 90 | SATYAJIT GHOSH | 80.85 | 0 | 0 | 100
2516 | BIRBHUM | Birbhum Division | Balijuri Piped Water Supply Scheme. , SM/12682 | New | Construction of 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 8.00 m X 8.00 m Pump room/ Chlorine room with sanitary arrangements, 300 CuM capacity O.H.R., 150 CuM CWR, Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at BALIJURI & its adjoining mouzas water supply scheme within Dubrajpur Block including supply of all labour & materials under BIRBHUM Division, PHE Dte". | 2663/BHM | 13/09/2024 | 365 | PATHIK PABAN NANDI | 513.18 | 0 | 0 | 25
2517 | BIRBHUM | Birbhum Division | Nanubazar Piped Water Supply Scheme , SM/12673 | New | Material Requisition To Resource Division | 1420/BHM | 24/04/2023 | 0 | Resource Division | 115.81 | 0 | 0 | 0
2518 | BIRBHUM | Bolpur Mechanical | Nanubazar Piped Water Supply Scheme , SM/12673 | New | Providing Electro-mechanical accessories and others for Nanubazar & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2093/Bol.MD | 22/08/2023 | 679 | ASHUTOSH DAS & CO. | 28.65 | 0 | 0 | 45
2519 | BIRBHUM | Birbhum Division | Nanubazar Piped Water Supply Scheme , SM/12673 | New | Material Requisition To Resource Division | 2490/BHM | 03/09/2024 | 0 | Resource Division | 9.46 | 0 | 0 | 0
2520 | BIRBHUM | Bolpur Mechanical | Nanubazar Piped Water Supply Scheme , SM/12673 | New | New service connection at Nanubazar PH-I W/S scheme Block-Sainthia under Bolpur Mechanical Division,PHE Dte. | BP-24-25-277 | 06/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.13 | 0 | 0 | 0
2521 | BIRBHUM | Birbhum Division | Nanubazar Piped Water Supply Scheme , SM/12673 | New | Sinking of 02(Two) nos. 200mm X 200 mm X 174m deep Tube Wells Fitted With M.S Housing & Well Pipe by Direct Rotary Rig for Nanubazar and Adjacent areas Piped Water Supply Scheme, Block:Sainthia under Birbhum Division, P.H.E Dte | 315/BHM | 28/01/2025 | 60 | WATER TECH | 25.26 | 0 | 0 | 0
2522 | BIRBHUM | Birbhum Division | Nanubazar Piped Water Supply Scheme , SM/12673 | New | Construction of, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements, 4.10 m X 3.50 m Pump house , 200 CuM, capacity O.H.R. , Boundary wall, Soil Investigation, Land development, Rising main, Laying distribution, Approach Road and Providing functional household tap connection related to water supply scheme at NANUBAZAR & its adjoining mouzas water supply scheme within Sainthia Blocki ncluding supply of all labour & materials under BIRBHUM Division, PHE Dte". | 2263/BHM | 14/08/2024 | 715 | PRANAB KUMAR GHOSH | 366.36 | 0 | 0 | 20
2523 | BIRBHUM | Birbhum Division | Nanubazar Piped Water Supply Scheme , SM/12673 | New | Road crossing, repairing & restoration of damage pipe lines & PCC roads, sluice valve chambers including all allied works for Nanubazar Piped Water Supply Scheme under Birbhum Sadar Sub-Division within Birbhum Division, P.H.E Dte. | 1646/BHM | 12/06/2025 | 90 | PRANAB KUMAR GHOSH | 49.37 | 0 | 0 | 0
2524 | BIRBHUM | Birbhum Division | KAMARDANGAL PIPED WATER SUPPLY SCHEME. , SM/12675 | New | Material Requisition To Resource Division | 1382/BHM | 24/04/2023 | 0 | Resource Division | 16.97 | 0 | 0 | 0
2525 | BIRBHUM | Bolpur Mechanical | KAMARDANGAL PIPED WATER SUPPLY SCHEME. , SM/12675 | New | Providing Electro-mechanical accessories and others for Kamardangal PWSS at Suri - I Block under Bolpur Mechanical Division PHE Dte. | 2104/BOL.MD. | 22/08/2023 | 60 | M/S S.R. ENTERPRISE | 27.85 | 0 | 0 | 30
2526 | BIRBHUM | Bolpur Mechanical | KAMARDANGAL PIPED WATER SUPPLY SCHEME. , SM/12675 | New | WBSEDCL QUOTATION FOR PURBA KAMARDANGAL WS SCHEME | BP-23-24-242 | 29/01/2024 | 0 | WBSEDCL | 6.19 | 0 | 0 | 0
2527 | BIRBHUM | Birbhum Division | KAMARDANGAL PIPED WATER SUPPLY SCHEME. , SM/12675 | New | Different works for KAMAR DANGAL & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. Sl No 02 | 885/BHM | 21/03/2023 | 275 | M/S.KHAN CHOWDHURY BROTHERS AND CO. | 208.71 | 0 | 0 | 80
2528 | BIRBHUM | Birbhum Division | Behira and Adjoining Mouzas PWSS , SM/12456 | New | Material Requisition To Resource Division | 1376/BHM | 24/04/2023 | 0 | Resource Division | 22.58 | 0 | 0 | 0
2529 | BIRBHUM | Bolpur Mechanical | Behira and Adjoining Mouzas PWSS , SM/12456 | New | Quotation deposit for Behira Water Supply Scheme P/H-II in Sainthia CCC under Bolpur Mechanical division, PHE Dte | BP-24-25-285 | 17/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.44 | 0 | 0 | 0
2530 | BIRBHUM | Birbhum Division | Behira and Adjoining Mouzas PWSS , SM/12456 | New | Different works related to water supply scheme at ABHIRAMPUR, BEHIRA, SAMSA & UTTAR BANGAON and its adjoining mouzas water supply scheme within SAINTHIA Block under Birbhum Division, PHE Dte. | 1437/BHM | 25/04/2023 | 820 | ASHOK KUMAR GHOSH | 1446.74 | 0 | 0 | 55
2531 | BIRBHUM | Bolpur Mechanical | Behira and Adjoining Mouzas PWSS , SM/12456 | New | Providing Electro-mechanical accessories and others for Behira & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 2099/Bol.MD | 22/08/2023 | 738 | C M ENTERPRISE | 24.27 | 0 | 0 | 50
2532 | BIRBHUM | Birbhum Division | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division , SM/13634 | New | Preparation & Submission of DPR for (Beluti) Water Supply Scheme under Mayureswar-II Development Block. | 161/RSD | 20/04/2022 | 45 | ENVIROTECH SOLUTIONS | 2.15 | 0 | 0 | 100
2533 | BIRBHUM | Birbhum Division | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division , SM/13634 | New | Material Requisition To Resource Division | 1486/BHM | 25/04/2023 | 0 | Resource Division | 2.93 | 0 | 0 | 0
2534 | BIRBHUM | Birbhum Division | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division , SM/13634 | New | Material Requisition To Resource Division | 203/BHM | 22/01/2024 | 0 | Resource Division | 2.56 | 0 | 0 | 0
2535 | BIRBHUM | Bolpur Mechanical | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division , SM/13634 | New | WBSEDCL QUOTATION FOR RBELUTI P H NO.II WS SCHEME | BP-23-24-198 | 19/12/2023 | 0 | WBSEDCL | 2.91 | 0 | 0 | 0
2536 | BIRBHUM | Bolpur Mechanical | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division , SM/13634 | New | WBSEDCL QUOITATION FOR BELUTI PH NO-I | BP-23-24-267 | 07/02/2024 | 0 | WBSEDCL | 8.05 | 0 | 0 | 0
2537 | BIRBHUM | Bolpur Mechanical | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division , SM/13634 | New | Providing Electro-mechanical accessories and others for Beluti PWSS at Mayureswar - II Block under Bolpur Mechanical Division PHE Dte. | 3284/Bol.MD | 29/09/2023 | 550 | DEY ENTERPRISE | 43.64 | 0 | 0 | 90
2538 | BIRBHUM | Birbhum Division | Beluti Piped Water Supply Scheme under Mayureswar-II Block within Birbhum Division , SM/13634 | New | Different works related to Water Supply Scheme at BELUTI & its adjoining mouzas Water Supply Scheme within MAYURESWAR-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 673/BHM | 01/03/2023 | 671 | ESCON INDIA | 208.6 | 0 | 0 | 100
2539 | BIRBHUM | Central Drilling | JIJIGRAM PIPED WATER SUPPLY SCHEME. , SM/12837 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm x 200mm x 150mtrs depth) by utilising Departmental Machineries for Jijigram PWSS,TW-I , Murarai-II Block under Birbhum District ,CDD,P.H.E. Dte. | 1379/CDD | 24/11/2022 | 30 | OSMAN SEKH | 10.67 | 8.27 | 100 | 100
2540 | BIRBHUM | Central Drilling | JIJIGRAM PIPED WATER SUPPLY SCHEME. , SM/12837 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm x 200mm x 150mtrs depth) by utilising Departmental Machineries for Jijigram PWSS,TW-II , Murarai-II Block under Birbhum District ,CDD,P.H.E. Dte. | 1380/CDD | 24/11/2022 | 30 | OSMAN SEKH | 10.67 | 8.27 | 100 | 100
2541 | BIRBHUM | Birbhum Division | JIJIGRAM PIPED WATER SUPPLY SCHEME. , SM/12837 | New | Material Requisition To Resource Division | 1491/BHM | 25/04/2023 | 0 | Resource Division | 53.18 | 0 | 0 | 0
2542 | BIRBHUM | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. , SM/12837 | New | Providing Electro-mechanical accessories and others for Jijigram PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | 1928/Bol.MD | 11/08/2023 | 60 | SUNIL RABIDAS | 27.41 | 0 | 0 | 100
2543 | BIRBHUM | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. , SM/12837 | New | WBSEDCL QUOTATION FOR UTTAR JIJIGRAM P H NO.I WS SCHEME | BP-23-24-193 | 14/12/2023 | 0 | WBSEDCL | 3.58 | 0 | 0 | 0
2544 | BIRBHUM | Bolpur Mechanical | JIJIGRAM PIPED WATER SUPPLY SCHEME. , SM/12837 | New | WBSEDCL QUOTATION FOR UTTAR JIJIGRAM P H NO.II WS SCHEME | BP-23-24-194 | 14/12/2023 | 0 | WBSEDCL | 3.14 | 0 | 0 | 0
2545 | BIRBHUM | Birbhum Division | JIJIGRAM PIPED WATER SUPPLY SCHEME. , SM/12837 | New | Different works related to water supply scheme at Jijigram, Math Basori & Bilaspur and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3019/BHM | 14/07/2023 | 961 | SUNIL RABI DAS | 1250.5 | 0 | 0 | 60
2546 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GANUTIA AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11903 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 177.2 | 22.29 | 92
2547 | BIRBHUM | Birbhum Division | MATIKONA PIPED WATER SUPPLY SCHEME , SM/13643 | New | Material Requisition To Resource Division | 1525/BHM | 26/04/2023 | 0 | Resource Division | 14.35 | 0 | 0 | 0
2548 | BIRBHUM | Birbhum Division | MATIKONA PIPED WATER SUPPLY SCHEME , SM/13643 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for MATIKONA Piped Water Supply Scheme under command area of Illambazar Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte.". | 224/BSD | 08/06/2022 | 90 | M/S R DUTTA & CO. | 4.99 | 0 | 0 | 100
2549 | BIRBHUM | Bolpur Mechanical | MATIKONA PIPED WATER SUPPLY SCHEME , SM/13643 | New | New power connection at Matikona PWSS under Bolpur Mechanical Division.PHE.Dte. | BP-24-25-131 | 29/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.04 | 0 | 0 | 0
2550 | BIRBHUM | Central Drilling | MATIKONA PIPED WATER SUPPLY SCHEME , SM/13643 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2551 | BIRBHUM | Birbhum Division | MATIKONA PIPED WATER SUPPLY SCHEME , SM/13643 | New | Different works related to water supply scheme at MATIKONA, NOHONA, SHIRSHA & CHUNPALASHI Piped Water Supply Scheme within ILLAMBAZAR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 3598/BHM | 21/08/2023 | 949 | BIPIN KUMAR SINGH | 2395.67 | 0 | 0 | 4
2552 | BIRBHUM | Birbhum Division | MATIKONA PIPED WATER SUPPLY SCHEME , SM/13643 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
2553 | BIRBHUM | Birbhum Division | Kachujore Piped Water Supply Scheme. , SM/13016 | New | Material Requisition To Resource Division | 1381/BHM | 24/04/2023 | 0 | Resource Division | 9.47 | 0 | 0 | 0
2554 | BIRBHUM | Bolpur Mechanical | Kachujore Piped Water Supply Scheme. , SM/13016 | New | Providing Electro-mechanical accessories and others for Kachujor PWSS at Suri -I Block under Bolpur Mechanical Division PHE Dte. | 2102/BOL.MD. | 22/08/2023 | 588 | UNITED TRADERS | 27.62 | 0 | 0 | 50
2555 | BIRBHUM | Bolpur Mechanical | Kachujore Piped Water Supply Scheme. , SM/13016 | New | WBSEDCL QUOTATION FOR KACHUJORE PWSS | BP-23-24-247 | 29/01/2024 | 0 | WBSEDCL | 4.01 | 0 | 0 | 0
2556 | BIRBHUM | Bolpur Mechanical | Kachujore Piped Water Supply Scheme. , SM/13016 | New | Quotation for new service connection at Kachujore Water Supply Scheme (TW No-II) under Suri-I Block. | BP-2024-2025-31 | 20/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 5.09 | 0 | 0 | 0
2557 | BIRBHUM | Birbhum Division | Kachujore Piped Water Supply Scheme. , SM/13016 | New | Different Works for KACHUJOR & its adjoining mouzas water supply scheme within SURI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1084/BHM | 06/04/2023 | 1033 | HIRANMAY GHOSH | 149.6 | 0 | 0 | 35
2558 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES (MAXIMUM 100 HOUSEHOLD) FOR PARKANDI AND OTHER 7 NOS. MOUZAS UNDER RAMPURHAT-I BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/11935 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 95.27 | 36.78 | 92
2559 | BIRBHUM | Bolpur Mechanical | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13476 | New | Providing Electro-mechanical accessories and others for Shibgram PWSS at Mayureswar - I Block under Bolpur Mechanical Division PHE Dte. | 3473/Bol.MD | 07/11/2023 | 60 | R. N. S. TRADING | 44.5 | 0 | 0 | 0
2560 | BIRBHUM | Birbhum Division | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13476 | New | Continuation Work Order for Preparation & Submission of DPR for (Shibgram) Water Supply Scheme under Mayureswar-I Development Block. | 244/RSD | 14/07/2022 | 90 | ENVIROTECH SOLUTIONS | 4.65 | 0 | 0 | 100
2561 | BIRBHUM | Birbhum Division | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13476 | New | Material Requisition To Resource Division | 1522/BHM | 26/04/2023 | 0 | Resource Division | 10.37 | 0 | 0 | 0
2562 | BIRBHUM | Birbhum Division | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13476 | New | Material Requisition To Resource Division | 198/BHM | 22/01/2024 | 0 | Resource Division | 4 | 0 | 0 | 0
2563 | BIRBHUM | Bolpur Mechanical | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13476 | New | Quotation For new connection at Shibgram PWSS P/H-1 (block -Mayureswar -I) | BP-2024-2025-30 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.21 | 0 | 0 | 0
2564 | BIRBHUM | Bolpur Mechanical | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13476 | New | New service connection at Shibgram PH-II under Mayureswar -I block. | BP-2024-2025-29 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.84 | 0 | 0 | 0
2565 | BIRBHUM | Birbhum Division | Shibgram Piped Water Supply Scheme under Mayureswar-I Block within Birbhum Division. , SM/13476 | New | Different works related to water supply scheme at LACHHIATOR, DAKSHINGRAM, SONJ & SHIBGRAM and its adjoining mouzas water supply scheme within MAYURESWAR-I Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 4142/BHM | 19/10/2023 | 805 | B RAI CONSTRUCTION COMPANY | 2003.84 | 0 | 0 | 60
2566 | BIRBHUM | Central Drilling | BIRSINGHA PIPED WATER SUPPLY SCHEME. , SM/12830 | New | PROVIDING DRILLING CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BIRSINGHA W/S SCHEME (TW-I), SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | 1430/CDD | 29/11/2022 | 30 | C.M. ENTERPRISE | 10.49 | 8.69 | 82.81 | 0
2567 | BIRBHUM | Central Drilling | BIRSINGHA PIPED WATER SUPPLY SCHEME. , SM/12830 | New | PROVIDING DRILLIG CREW AND OTHER ALLIED WORKS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM X 150 MTRS DEPTH) BY UTILISING DEPARTMENTAL MACHINERIES FOR BIRSINGHA W/S SCH (TW-II), SAINTHIA BLOCK UNDER BIRBHUM DISTRICT, CDD, PHE DTE. | 1431/CDD | 29/11/2022 | 30 | C.M. ENTERPRISE | 10.49 | 8.79 | 100 | 0
2568 | BIRBHUM | Birbhum Division | BIRSINGHA PIPED WATER SUPPLY SCHEME. , SM/12830 | New | Material Requisition To Resource Division | 1377/BHM | 24/04/2023 | 0 | Resource Division | 9.12 | 0 | 0 | 0
2569 | BIRBHUM | Bolpur Mechanical | BIRSINGHA PIPED WATER SUPPLY SCHEME. , SM/12830 | New | WBSEDCL QUOTATION FOR BIRSINGA PAHARPUR WS SCHEME | BP-2023-2024-62 | 02/08/2023 | 0 | WBSEDCL | 2.3 | 0 | 0 | 0
2570 | BIRBHUM | Bolpur Mechanical | BIRSINGHA PIPED WATER SUPPLY SCHEME. , SM/12830 | New | WBSEDCL QUOTATION FOR BIRSINGHA PAHARPUR P.H.NO.II | BP-2023-2024-61 | 02/08/2023 | 0 | WBSEDCL | 2.3 | 0 | 0 | 0
2571 | BIRBHUM | Bolpur Mechanical | BIRSINGHA PIPED WATER SUPPLY SCHEME. , SM/12830 | New | Providing Electro-mechanical accessories and others for Birsingha & Adjoining moujas water supply scheme at Sainthia Block under Bolpur Mechanical Division PHE Dte. | 1058 | 08/06/2023 | 60 | S.G.TECHNICAL SERVICES | 28.79 | 0 | 0 | 85
2572 | BIRBHUM | Birbhum Division | BIRSINGHA PIPED WATER SUPPLY SCHEME. , SM/12830 | New | Different works related to water supply scheme at BHALIAN, BANGJITA & BIRSINGHA and its adjoining mouzas water supply scheme within SAINTHIA Block including supply of all labour & materials under Birbhum Division, PHE Dte. | 1258/BHM | 17/04/2023 | 806 | NAUTANDAS AND CO | 1377.28 | 0 | 0 | 35
2573 | BIRBHUM | Birbhum Division | Khanpur piped water supply scheme. , SM/13539 | New | Material Requisition To Resource Division | 1393/BHM | 24/04/2023 | 0 | Resource Division | 113.77 | 0 | 0 | 0
2574 | BIRBHUM | Bolpur Mechanical | Khanpur piped water supply scheme. , SM/13539 | New | Supply, delivery and storage of different Electro-Mechanical accessories at Khanpur PWSS under Bolpur Mmechanical Division, PHE Dte. | 3849/BOL.MD | 18/09/2024 | 30 | CINZANO | 31.2 | 0 | 0 | 0
2575 | BIRBHUM | Bolpur Mechanical | Khanpur piped water supply scheme. , SM/13539 | New | Providing Electro-mechanical accessories and others for Khanpur and Adjoining moujas water supply scheme under Bolpur Mechanical Division PHE Dte., Block : Dubrajpur, Dist : Birbhum | 07/BOL.MD | 03/01/2024 | 90 | AHALYA ENGINEERING WORKS | 21.75 | 0 | 0 | 100
2576 | BIRBHUM | Bolpur Mechanical | Khanpur piped water supply scheme. , SM/13539 | New | Supply Delivery & Installation of Electro-mechanical accessories at Khanpur & Adjoining moujas water supply scheme under Bolpur Mechanical Division PHE Dte. | 4408/Bol.MD | 28/11/2024 | 45 | AHALYA ENGINEERING WORKS | 16.93 | 0 | 0 | 100
2577 | BIRBHUM | Bolpur Mechanical | Khanpur piped water supply scheme. , SM/13539 | New | Providing Electro-mechanical accessories and others for Khanpur & Adjoining moujas water supply scheme under Bolpur Mechanical Division PHE Dte., Block : Dubrajpur, Dist : Birbhum. | 3763/Bol.MD | 12/09/2024 | 30 | AHALYA ENGINEERING WORKS | 19.44 | 0 | 0 | 100
2578 | BIRBHUM | Birbhum Division | Khanpur piped water supply scheme. , SM/13539 | New | Different works related to water supply scheme at PARULIA, KHANPUR & PADUMA and its adjoining mouzas water supply scheme within DUBRAJPUR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1425/BHM | 25/04/2023 | 982 | BIPIN KUMAR SINGH | 2248.63 | 0 | 0 | 55
2579 | BIRBHUM | Birbhum Division | Baraban Piped Water Supply Scheme (Khoyrasole Block) , SM/14852 | New | Preparation & Submission of DPR for Baraban & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 76/BSSD | 05/05/2022 | 45 | RADIANT | 3.35 | 0 | 0 | 100
2580 | BIRBHUM | Birbhum Division | Baraban Piped Water Supply Scheme (Khoyrasole Block) , SM/14852 | New | Material Requisition To Resource Division | 435/BHM | 01/02/2024 | 0 | Resource Division | 164.74 | 0 | 0 | 0
2581 | BIRBHUM | Birbhum Division | Baraban Piped Water Supply Scheme (Khoyrasole Block) , SM/14852 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
2582 | BIRBHUM | Birbhum Division | Baraban Piped Water Supply Scheme (Khoyrasole Block) , SM/14852 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
2583 | BIRBHUM | Birbhum Division | NAWADA PALANDI PIPED WATER SUPPLY SCHEME , SM/14682 | New | Material Requisition To Resource Division | 1468/BHM | 25/04/2023 | 0 | Resource Division | 23.68 | 0 | 0 | 0
2584 | BIRBHUM | Birbhum Division | NAWADA PALANDI PIPED WATER SUPPLY SCHEME , SM/14682 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for NAWDA PALANDI Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | 263/BSD | 11/07/2022 | 90 | RADIANT | 4.94 | 0 | 0 | 100
2585 | BIRBHUM | Birbhum Division | NAWADA PALANDI PIPED WATER SUPPLY SCHEME , SM/14682 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for NAWDA PALUNDI Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - B) | 344/BSD | 12/09/2022 | 90 | RADIANT | 1.82 | 0 | 0 | 100
2586 | BIRBHUM | Birbhum Division | NAWADA PALANDI PIPED WATER SUPPLY SCHEME , SM/14682 | New | Material Requisition To Resource Division | 2384/BHM | 27/08/2024 | 0 | Resource Division | 13.57 | 0 | 0 | 0
2587 | BIRBHUM | Central Drilling | NAWADA PALANDI PIPED WATER SUPPLY SCHEME , SM/14682 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2588 | BIRBHUM | Birbhum Division | NAWADA PALANDI PIPED WATER SUPPLY SCHEME , SM/14682 | New | Construction of 250 & 150 CuM. Capacity O.H.R. with Soil Investigation, 5.90 m X 4.10 m Pump room/ Chlorine room with sanitary arrangements Laying of Rising Main, Distribution System with FHTC including different works related to SANTOSHPUR / NAWADA PALANDI /PAPURI / SAJNOR / RAYEN PIPED WATER SUPPLY SCHEME (5 Nos Scheme) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division PHE DTE. | 1951/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2322.64 | 0 | 0 | 5
2589 | BIRBHUM | Bolpur Mechanical | NAWADA PALANDI PIPED WATER SUPPLY SCHEME , SM/14682 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Nawada Palandi WSS (TW No I and II), Block- Nanoor, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | 4529/BOL.MD | 20/12/2024 | 377 | SATYAJIT GHOSH | 75.08 | 0 | 0 | 40
2590 | BIRBHUM | Birbhum Division | Ruppur and adjoining mouzas Piped Water Supply Scheme. , SM/14686 | New | Material Requisition To Resource Division | 1363/BHM | 24/04/2023 | 0 | Resource Division | 263.55 | 0 | 0 | 0
2591 | BIRBHUM | Bolpur Mechanical | Ruppur and adjoining mouzas Piped Water Supply Scheme. , SM/14686 | New | Providing Electro-mechanical accessories and others for Ruppur & Adjoining moujas water supply scheme at Bolpur Sriniketan Block under Bolpur Mechanical Division PHE Dte. | 3514/Bol.MD | 24/11/2023 | 90 | M. S. ENTERPRISE | 88.27 | 0 | 0 | 85
2592 | BIRBHUM | Central Drilling | Ruppur and adjoining mouzas Piped Water Supply Scheme. , SM/14686 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2593 | BIRBHUM | Birbhum Division | Rupaspur Piped Water Supply Scheme. , SM/14081 | New | Preparation & Submission of DPR for Rupaspur & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 72/BSSD | 28/04/2022 | 45 | RADIANT | 2.49 | 0 | 0 | 100
2594 | BIRBHUM | Birbhum Division | Rupaspur Piped Water Supply Scheme. , SM/14081 | New | Material Requisition To Resource Division | 428/BHM | 01/02/2024 | 0 | Resource Division | 109.46 | 0 | 0 | 0
2595 | BIRBHUM | Birbhum Division | Rupaspur Piped Water Supply Scheme. , SM/14081 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
2596 | BIRBHUM | Birbhum Division | Rupaspur Piped Water Supply Scheme. , SM/14081 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
2597 | BIRBHUM | Birbhum Division | Bhaddi Piped Water Supply Scheme , SM/14114 | New | Preparation & Submission of DPR for Bhaddi & its adjoining mouzas Piped Water Supply Scheme under Khayrasole Development Block. | 80/BSSD | 10/05/2022 | 45 | RADIANT | 2.42 | 0 | 0 | 100
2598 | BIRBHUM | Birbhum Division | Bhaddi Piped Water Supply Scheme , SM/14114 | New | Material Requisition To Resource Division | 437/BHM | 01/02/2024 | 0 | Resource Division | 109.46 | 0 | 0 | 0
2599 | BIRBHUM | Birbhum Division | Bhaddi Piped Water Supply Scheme , SM/14114 | New | Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & Different works including Laying of Distribution System, providing FHTCs and construction of switch rooms & Boundary wallswith gates in connection with Sub Surface based water Supply Scheme (Zone-I to XX) at Khayrasole Block under Birbhum Division, PHE Dte., District:-Birbhum. | 4123/BHM | 17/10/2023 | 1006 | LUMINO SMC JV | 4221.25 | 0 | 0 | 81
2600 | BIRBHUM | Birbhum Division | Bhaddi Piped Water Supply Scheme , SM/14114 | New | Construction of 19 nos. 50 Cum capacity CWR and 1 no. 100 Cum capacity CWR with Soil Investigation for all & Construction of Boundary Wall and Rising Main Pipe line for 20 nos. PWSS at Khoyrasol block under Birbhum Division, PHE Dte. | 1851/BHM | 19/06/2024 | 740 | LUMINO SMC JV | 1056.1 | 0 | 0 | 100
2601 | BIRBHUM | Birbhum Division | HATKALUA PIPED WATER SUPPLY SCHEME , SM/14115 | New | Material Requisition To Resource Division | 1457/BHM | 25/04/2023 | 0 | Resource Division | 20.15 | 0 | 0 | 0
2602 | BIRBHUM | Birbhum Division | HATKALUA PIPED WATER SUPPLY SCHEME , SM/14115 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for HATKALUA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | 105/BSD | 21/03/2022 | 180 | APEX ENGINEERING | 3.87 | 0 | 0 | 100
2603 | BIRBHUM | Birbhum Division | HATKALUA PIPED WATER SUPPLY SCHEME , SM/14115 | New | Different works related to water supply scheme at HATKALUA PIPED WATER SUPPLY SCHEME (TSM/016242) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1096/BHM | 06/04/2023 | 545 | M/S R B ENTERPRISE | 446.12 | 0 | 0 | 5
2604 | BIRBHUM | Bolpur Mechanical | HATKALUA PIPED WATER SUPPLY SCHEME , SM/14115 | New | Quotation for new service connection at Hatkaluha PWSS(P/H-I) | BP-24-25-275 | 06/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 8.62 | 0 | 0 | 0
2605 | BIRBHUM | Central Drilling | HATKALUA PIPED WATER SUPPLY SCHEME , SM/14115 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2606 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR GOPALPUR AND OTHER 20 NOS. MOUZAS UNDER SAINTHIA BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/14037 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 0 | 0 | 92
2607 | BIRBHUM | Birbhum Division | SHEKHAMPUR PIPED WATER SUPPLY SCHEME , SM/14956 | New | Material Requisition To Resource Division | 1602/BHM | 27/04/2023 | 0 | Resource Division | 22.21 | 0 | 0 | 0
2608 | BIRBHUM | Birbhum Division | SHEKHAMPUR PIPED WATER SUPPLY SCHEME , SM/14956 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for SHEKHAMPUR Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | 193/BSD | 17/05/2022 | 180 | APEX ENGINEERING | 4.29 | 0 | 0 | 100
2609 | BIRBHUM | Birbhum Division | SHEKHAMPUR PIPED WATER SUPPLY SCHEME , SM/14956 | New | Material Requisition To Resource Division | 2386/BHM | 27/08/2024 | 0 | Resource Division | 10.3 | 0 | 0 | 0
2610 | BIRBHUM | Central Drilling | SHEKHAMPUR PIPED WATER SUPPLY SCHEME , SM/14956 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2611 | BIRBHUM | Birbhum Division | SHEKHAMPUR PIPED WATER SUPPLY SCHEME , SM/14956 | New | Construction of Different capacity O.H.R.,with Soil investigation, 5.90 m X 4.10 mPump room/ Chlorine room with sanitary arrangements, and laying of Rising main,Distribution system, with FHTC .and Construction of boundary wall including approach road and land development at Head work site and 2 nd under different (6 nos).PIPED WATER SUPPLY SCHEME within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte. | 1948/BHM | 04/07/2024 | 730 | UMWELT ENGINEER PVT. LTD. | 2014.73 | 0 | 0 | 0
2612 | BIRBHUM | Bolpur Mechanical | SHEKHAMPUR PIPED WATER SUPPLY SCHEME , SM/14956 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Sekhampur PWSS (TW No I and II), Block- Labpur, in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | 336/BOL.MD | 19/02/2025 | 120 | SATYAJIT GHOSH | 76.45 | 0 | 0 | 0
2613 | BIRBHUM | Birbhum Division | BHATRA PIPED WATER SUPPLY SCHEME , SM/14958 | New | Material Requisition To Resource Division | 1596/BHM | 26/04/2023 | 0 | Resource Division | 69.42 | 0 | 0 | 0
2614 | BIRBHUM | Birbhum Division | BHATRA PIPED WATER SUPPLY SCHEME , SM/14958 | New | Different works related to water supply scheme at BHATRA PIPED WATER SUPPLY SCHEME (TSM017151) within LABPUR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | 3020/BHM | 30/10/2024 | 365 | DIPAYAN DEY | 441.62 | 0 | 0 | 0
2615 | BIRBHUM | Birbhum Division | BHATRA PIPED WATER SUPPLY SCHEME , SM/14958 | New | Continuation work order for "Preparation & Submission of Detail Project Report (DPR) for BHATRA Piped Water Supply Scheme under Labpur Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." | 141/BSD | 07/04/2022 | 180 | APEX ENGINEERING | 4.57 | 0 | 0 | 100
2616 | BIRBHUM | Central Drilling | BHATRA PIPED WATER SUPPLY SCHEME , SM/14958 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2617 | BIRBHUM | Bolpur Mechanical | BHATRA PIPED WATER SUPPLY SCHEME , SM/14958 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Bhatra PWSS (TW No I and II), Block- Labpur in Birbhum District under Bolpur Mechanical Division, P.H.E Dte | 325/BOL.MD | 19/02/2025 | 120 | OSMAN SEKH | 76.34 | 0 | 0 | 0
2618 | BIRBHUM | Birbhum Division | Moubelia Piped Water Supply Scheme. , SM/14899 | New | Material Requisition To Resource Division | 1620/BHM | 28/04/2023 | 0 | Resource Division | 13.88 | 0 | 0 | 0
2619 | BIRBHUM | Birbhum Division | Moubelia Piped Water Supply Scheme. , SM/14899 | New | Material Requisition To Resource Division | 3075/BHM | 19/07/2023 | 0 | Resource Division | 4.35 | 0 | 0 | 0
2620 | BIRBHUM | Bolpur Mechanical | Moubelia Piped Water Supply Scheme. , SM/14899 | New | Providing Electro-mechanical accessories and others for MOUBELIA piped water supply scheme, Md. Bazar block, under Bolpur Mechanical Division PHE Dte. | 2077/BOL.MD. | 21/08/2023 | 60 | DIPALI CONSTRUCTION | 27.4 | 0 | 0 | 80
2621 | BIRBHUM | Bolpur Mechanical | Moubelia Piped Water Supply Scheme. , SM/14899 | New | WBSEDCL QUOTATION FOR MOUBELIA WS SCHEME | BP-23-24-176 | 07/12/2023 | 0 | WBSEDCL | 0.39 | 0 | 0 | 0
2622 | BIRBHUM | Bolpur Mechanical | Moubelia Piped Water Supply Scheme. , SM/14899 | New | WBSEDCL QUOTATION FOR MOUBELIA WS SCHEME | BP-23-24-175 | 07/12/2023 | 0 | WBSEDCL | 4.48 | 0 | 0 | 0
2623 | BIRBHUM | Birbhum Division | Moubelia Piped Water Supply Scheme. , SM/14899 | New | Different works related to water supply scheme at MOUBELIA & its adjoining mouzas water supply scheme within MD BAZAR Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1182/BHM | 12/04/2023 | 537 | M/S R B ENTERPRISE | 304.55 | 0 | 0 | 100
2624 | BIRBHUM | Birbhum Division | Moubelia Piped Water Supply Scheme. , SM/14899 | New | Sinking of additional T.W, Road crossing, Repairing & restoration of damaged pipe lines, sluice valve chambers, including all allied works for Moubelia PWSS of Md.Bazar Development Block Under Birbhum Division, P.H.E Dte | 1639/BHM | 11/06/2025 | 90 | M/S R B ENTERPRISE | 46.39 | 0 | 0 | 0
2625 | BIRBHUM | Birbhum Division | Salan Piped Water Supply Scheme. , SM/14207 | New | Material Requisition To Resource Division | 1364/BHM | 24/04/2023 | 0 | Resource Division | 19.72 | 0 | 0 | 0
2626 | BIRBHUM | Central Drilling | Salan Piped Water Supply Scheme. , SM/14207 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2627 | BIRBHUM | Birbhum Division | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME , SM/14534 | New | Material Requisition To Resource Division | 1494/BHM | 25/04/2023 | 0 | Resource Division | 41.61 | 0 | 0 | 0
2628 | BIRBHUM | Birbhum Division | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME , SM/14534 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BRAHAMAKHANDA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - A) | 221/BSD | 07/06/2022 | 180 | RADIANT | 4.94 | 0 | 0 | 100
2629 | BIRBHUM | Birbhum Division | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME , SM/14534 | New | Continuation Work Order for "Preparation & Submission of Detail Project Report (DPR) for BRAHAMAKHANDA Piped Water Supply Scheme under Nanoor Development Block within Bolpur Sub-Division under Birbhum Division, PHE Dte." (PART - B) | 298/BSD | 10/08/2022 | 90 | RADIANT | 1.82 | 0 | 0 | 100
2630 | BIRBHUM | Birbhum Division | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME , SM/14534 | New | Material Requisition To Resource Division | 3265/BHM | 02/12/2024 | 0 | Resource Division | 14.05 | 0 | 0 | 0
2631 | BIRBHUM | Central Drilling | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME , SM/14534 | New | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) | 1415/CDD | 21/09/2023 | 304 | JHARGRAM SPV PRIVATE LIMITED | 21339.76 | 0 | 0 | 11
2632 | BIRBHUM | Birbhum Division | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME , SM/14534 | New | Different works related to water supply scheme at BRAHMANKHANDA PIPED WATER SUPPLY SCHEME (TSM/015460) within NANOOR Block including supply of all labour & materials under Bolpur Sub-Division within Birbhum Division, PHE Dte | 2598/BHM | 10/09/2024 | 365 | ASHOK MITRA | 463.91 | 0 | 0 | 20
2633 | BIRBHUM | Bolpur Mechanical | BRAHMANKHANDA PIPED WATER SUPPLY SCHEME , SM/14534 | New | Construction of Tube Well (300 MM x 200 MM x Depth 450 Mtr) for Brahmankhnda Water supply Scheme (T/W-I & II), Block- Nanoor, in Birbhum District by Bolpur Mechanical Division, P.H.Engineering Dte. | 4535/BOL.MD | 20/12/2024 | 120 | SATYAJIT GHOSH | 75.35 | 0 | 0 | 50
2634 | BIRBHUM | Birbhum Division | Dhitora Right side and adjoining mouzas piped water supply scheme. , SM/17633 | New | Material Requisition To Resource Division | 1501/BHM | 25/04/2023 | 0 | Resource Division | 10.63 | 0 | 0 | 0
2635 | BIRBHUM | Bolpur Mechanical | Dhitora Right side and adjoining mouzas piped water supply scheme. , SM/17633 | New | QUOTATION BILL FOR DHITORA WS SCHEME P H NO.II | BP-23-24-148 | 28/11/2023 | 0 | WBSEDCL | 2.61 | 0 | 0 | 0
2636 | BIRBHUM | Bolpur Mechanical | Dhitora Right side and adjoining mouzas piped water supply scheme. , SM/17633 | New | QUOTATION BILL FOR DHITORA WS SCHEME P H NO.I | BP-23-24-147 | 28/11/2023 | 0 | WBSEDCL | 3.81 | 0 | 0 | 0
2637 | BIRBHUM | Bolpur Mechanical | Dhitora Right side and adjoining mouzas piped water supply scheme. , SM/17633 | New | Providing Electro-mechanical accessories and others for DHITORA RIGHT SIDE piped water supply scheme, Murarai-I block, under Bolpur Mechanical Division PHE Dte. | 1929/Bol.MD | 11/08/2023 | 325 | ORIENTAL ENGINEERING CO. | 27.2 | 0 | 0 | 80
2638 | BIRBHUM | Bolpur Mechanical | Dhitora Right side and adjoining mouzas piped water supply scheme. , SM/17633 | New | WBSEDCL QUOITATION FOR DHITORA PH NO-I | BP-23-24-268 | 08/02/2024 | 0 | WBSEDCL | 1.3 | 0 | 0 | 0
2639 | BIRBHUM | Birbhum Division | Dhitora Right side and adjoining mouzas piped water supply scheme. , SM/17633 | New | Different works related to water supply scheme at DHITORA & its adjoining mouzas water supply scheme within MURARAI-I Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 1108/BHM | 10/04/2023 | 691 | M/S PROCHESTA ENTERPRISE | 215.75 | 0 | 0 | 100
2640 | BIRBHUM | Birbhum Division | Atkulia Piped Water Supply Scheme , SM/18301 | New | Preparation and submission of DPR for (Atkulia) Water Supply Scheme under Nalhati-II Development Block. | 218/AE/NSD | 18/04/2022 | 45 | MS SOBHA AND CO | 4.89 | 0 | 0 | 100
2641 | BIRBHUM | Birbhum Division | Atkulia Piped Water Supply Scheme , SM/18301 | New | Material Requisition To Resource Division | 1510/BHM | 26/04/2023 | 0 | Resource Division | 62.89 | 0 | 0 | 0
2642 | BIRBHUM | Bolpur Mechanical | Atkulia Piped Water Supply Scheme , SM/18301 | New | Supply and Delivery of Open well Submersible Pumping Machineries and allied accessories for Atkulia PWSS, (Block- Nalhati - II) under Bolpur Mechanical Division, PHE Dte. | 3784/BOL.MD | 12/09/2024 | 30 | EASTERN INDIA SALES & SERVICE | 37.46 | 0 | 0 | 0
2643 | BIRBHUM | Bolpur Mechanical | Atkulia Piped Water Supply Scheme , SM/18301 | New | WBSEDCL QUOTATION FOR Atkulia Piped Water Supply Scheme | BP-23-24-237 | 29/01/2024 | 0 | WBSEDCL | 3.29 | 0 | 0 | 0
2644 | BIRBHUM | Bolpur Mechanical | Atkulia Piped Water Supply Scheme , SM/18301 | New | Providing Electro-mechanical accessories and others for Atkulia PWSS at Nalhati - II Block under Bolpur Mechanical Division PHE Dte. | 2134/Bol.MD | 25/08/2023 | 582 | SINHA ELECTRICALS | 57.83 | 26.72 | 46.2 | 30
2645 | BIRBHUM | Birbhum Division | Atkulia Piped Water Supply Scheme , SM/18301 | New | Jack pushing along with extension of pipeline (DI & HDPE), Restoration of Roads etc for Atkulia piped Water Supply Scheme under Nalhati Sub Division within Birbhum Division P.H.E. Dte. | 799/BHM | 24/03/2025 | 360 | M/S S. CHOUDHURY | 76.4 | 0 | 0 | 0
2646 | BIRBHUM | Birbhum Division | BILASPUR PIPED WATER SUPPLY SCHEME. , SM/12594 | New | Material Requisition To Resource Division | 1569/BHM | 26/04/2023 | 0 | Resource Division | 24.53 | 0 | 0 | 0
2647 | BIRBHUM | Bolpur Mechanical | BILASPUR PIPED WATER SUPPLY SCHEME. , SM/12594 | New | WBSEDCL QUOATION FOR BILASPUR P H NO.II WS SCHEME | BP-23-24-226 | 15/01/2024 | 0 | WBSEDCL | 3.45 | 0 | 0 | 0
2648 | BIRBHUM | Bolpur Mechanical | BILASPUR PIPED WATER SUPPLY SCHEME. , SM/12594 | New | WBSEDCL QUOTATION FOR BILASPUR PIPED WATER SUPPLY SCHEME.P H NO.I WS SCHEME | BP-23-24-225 | 15/01/2024 | 0 | WBSEDCL | 4.45 | 0 | 0 | 0
2649 | BIRBHUM | Birbhum Division | BILASPUR PIPED WATER SUPPLY SCHEME. , SM/12594 | New | Different works related to water supply scheme at Jijigram, Math Basori & Bilaspur and its adjoining mouzas water supply scheme within MURARAI-II Block including supply of all labour & materials under BIRBHUM Division, PHE Dte. | 3019/BHM | 14/07/2023 | 961 | SUNIL RABI DAS | 1250.5 | 0 | 0 | 60
2650 | BIRBHUM | Bolpur Mechanical | BILASPUR PIPED WATER SUPPLY SCHEME. , SM/12594 | New | Providing Electro-mechanical accessories and others for Bilaspur PWSS at Murarai - II Block under Bolpur Mechanical Division PHE Dte. | 3300/BOL.MD | 29/09/2023 | 550 | SUNIL RABIDAS | 28.71 | 0 | 0 | 100
2651 | BIRBHUM | Birbhum Division | BILASPUR PIPED WATER SUPPLY SCHEME. , SM/12594 | New | Wall writing on smooth wall surface (preferably of Govt. premises/Boundary Wall) by cleaning the surface thoroughly, removing old paint, preparing with one coat good quality exterior primer and Two cost best quality exterior synthetic enamel paint of approved shed and writing IEC message along with logo, picture etc. of multiple color as will be supplied by PHE Dte. by engaging skilled artist and helper artist in different location within the district of Birbhum all completed as per direction of EIC. (Size- 8'-4') 2215 nos. village (2 nos. each) | 203/BHM | 16/01/2025 | 90 | IMAGIN | 67.84 | 0 | 0 | 100
2652 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR HARISHCHANDRAPUR AND OTHER 14 NOS. MOUZAS UNDER ILLAMBAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/14015 | New | Implementation of MINI PIPED WATER SUPPLY SCHEME through Waterjet & DTH Boring in 334 (Three Hundred and Thirty Four) no. villages under different blocks having less than 100 households under Birbhum Division PHE Dte. | 2624/BHM | 28/11/2022 | 1187 | BIRBHUM INFRAPARK PRIVATE LIMITED | 11110.46 | 81.93 | 15.88 | 92
2653 | BIRBHUM | Birbhum Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES(MAXIMUM 100 HOUSEHOLD) FOR HARISHCHANDRAPUR AND OTHER 14 NOS. MOUZAS UNDER ILLAMBAZAR BLOCK UNDER BIRBHUM DIVISION, PHE DTE. , SM/14015 | New | Road restoration work at different villages under implementation of Mini Piped Water Supply Scheme within Illambazar Block having less than 100 Households under Birbhum Division PHE Dte. | 2152/BHM | 19/08/2025 | 90 | SOURAV MONDAL | 17.41 | 0 | 0 | 0
2654 | BIRBHUM | Birbhum Division | New Pipe Testing Laboratory for testing of UPVC and HDPE pipes at Suri, Birbhum under Birbhum Division. , SM/16483 | Support-WQMSP | Supply, installation and commissioning of UPVC and HDPE pipes testing equipments including 1 year Operation & Maintenance of the same as per IS specification at Birbhum Divisional Office Complex at Suri , Birbhum. | 3239/BHM | 25/07/2023 | 92 | SUNIL RABI DAS | 94.98 | 0 | 0 | 100
2655 | BIRBHUM | Birbhum Division | Preparation of DPR for Drinking Water Supply Schemes within the different blocks of Birbhum District under Birbhum Division, PHE Dte. , SM/18987 |  | Preparation of DPR for drinking water supply schemes within the different blocks of Birbhum district under Birbhum Division, PHE Dte. | 1950/BHM | 04/07/2024 | 60 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD. | 542.57 | 0 | 0 | 97
2656 | BIRBHUM | Bolpur Mechanical | Procurement of Computer and Peripherals for the office use in Bolpur Mechanical Division, AE-III Central Mechanical Division, Birbhum Mechanical Sub-Division (Drilling) PHE Dte. , SM/18141 | Support-MIS | Procurement of computer and peripherals for the office of the Bolpur Mechanical Division PHE Dte, Ae-III Central Mechanical Division, BMSD(D) under BOL MD PHE DTE | BP-2023-24-133 | 09/11/2023 | 0 | APPLET PROJECTS & ENGINEERING PVT. LTD. | 20.84 | 0 | 0 | 0
2657 | BIRBHUM | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM , SM/15636 | Support-WQMSP | Extension/Continuation work order for Engagement of Lab Personnel for the period from 01.04.2024 to 30.09.2024. | 138/BSSD | 28/03/2024 | 184 | KHAYRASOLE PALLY MANGAL SAMITY | 2.55 | 0 | 0 | 30
2658 | BIRBHUM | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM , SM/15636 | Support-WQMSP | Deployment/ Engagement for 5 Nos Sub- District Laboratory Personnel (5 nos. Chemist/Bacteriologist & 5 nos. Laboratory Assistant) & 1 no. Sampling Assistant (Ahmedpur Sub-Dist. Lab.) for a period of 06 months (01.07.2023 to 31.12.2023) for 5 nos. PHED Laboratories named Mayureswar Sub-District Laboratory, Patel Nagar Sub-District Laboratory, Ahmedpur Sub-District Laboratory , Murarai Sub-District Laboratory & Nalhati Sub district under Birbhum Didvision, P.H.E Dte | 2220/BHM | 30/06/2023 | 184 | DULAL MAJUMDAR | 12.14 | 0 | 0 | 100
2659 | BIRBHUM | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM , SM/15636 | Support-WQMSP | Operation and Mtc. of Water Testing Laboratory activities of the Birbhum District Laboratory at Suri under Birbhum Division, P.H.E. Dte. for the period of 06 (Six) months with effect from 01.07.2023 to 31.12.2023. | 2219/BHM | 30/06/2023 | 184 | DULAL MAJUMDAR | 6.49 | 0 | 0 | 100
2660 | BIRBHUM | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM , SM/15636 | Support-WQMSP | Engagement of Lab Personals for the Kanachi Khadi Bhandar (period from 01.04.2024 to 30.09.2024). | 197/RSD | 28/03/2024 | 183 | KANACHI KHADI BHANDAR | 2.7 | 0 | 0 | 70
2661 | BIRBHUM | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM , SM/15636 | Support-WQMSP | Engagement of Lab Personals for the Rampurhat Paribesh Pariseva (period from 01.04.2024 to 30.09.2024). | 198/RSD | 28/03/2024 | 183 | RAMPURHAT PARIBESH PARISEVA | 2.7 | 0 | 0 | 70
2662 | BIRBHUM | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM , SM/15636 | Support-WQMSP | Bill for Remuneration of Chemist, Bacteriologist, Lab-Assistant Under Rampurhat Paribesh pariseva Sub-District Laboratory (Name of NGO) for the period of April-2024 | BP-2024-25-56 | 17/05/2024 | 0 | RAMPURHAT PARIBESH PARISEVA | 0.45 | 0 | 0 | 0
2663 | BIRBHUM | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM , SM/15636 | Support-WQMSP | Bill for Remuneration of Chemist, Bacteriologist, Lab-Assistant Under Kanachi Khadi Bhandar Sub-District Laboratory (Name of NGO) for the period of MAY- 2024 | BP-2024-25-99 | 14/06/2024 | 0 | KANACHI KHADI BHANDAR | 0.45 | 0 | 0 | 0
2664 | BIRBHUM | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM , SM/15636 | Support-WQMSP | Bill for Remuneration of Chemist, Bacteriologist, Lab-Assistant Under Rampurhat Paribesh pariseva Sub-District Laboratory (Name of NGO) for the period of MAY-2024 | BP-2024-25-100 | 14/06/2024 | 0 | RAMPURHAT PARIBESH PARISEVA | 0.45 | 0 | 0 | 0
2665 | BIRBHUM | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM , SM/15636 | Support-WQMSP | Bill for Remuneration of Chemist, Bacteriologist, Lab-Assistant Under Kanachi Khadi Bhandar Sub-District Laboratory (Name of NGO) for the period of April - 2024. | BP-2024-25-57 | 17/05/2024 | 0 | KANACHI KHADI BHANDAR | 0.45 | 0 | 0 | 0
2666 | BIRBHUM | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM , SM/15636 | Support-WQMSP | Continuation Work OrderOperation and Mtc. of Water Testing Laboratory activities of the Birbhum District Laboratory at Suri under Birbhum Division, P.H.E. Dte. for the period of 01 (One) months with effect from 01.01.2024 to 31.01.2024. | 4731/BHM | 29/12/2023 | 31 | DULAL MAJUMDAR | 1.06 | 0 | 0 | 60
2667 | BIRBHUM | Birbhum Division | Operational charges of PHED and NGO Managed Laboratories related to water Quality Monitoring and Surveillance under JJM , SM/15636 | Support-WQMSP | Extension/Continuation work order for Engagement of Lab Personnel for the period from 01.10.2024 to 31.03.2025. | 357/BSSD | 27/09/2024 | 182 | KHAYRASOLE PALLY MANGAL SAMITY | 1.56 | 0 | 0 | 31
2668 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Patelnagar Sub-District Water Testing Laboratory under Birbhum Division, P.H.E. Dte. as per direction & satisfaction of EIC as per tender stipulations including all taxes. | 225/AE/BSSD | 05/07/2021 | 3 | SAKTI ENTERPRISE | 4.81 | 4.81 | 100 | 0
2669 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Mayureswar Sub-District Water Testing Laboratory under Birbhum Division, P.H.E. Dte. as per direction & satisfaction of EIC as per tender stipulations including all taxes. | 266/RSD | 07/07/2021 | 92 | SAKTI ENTERPRISE | 4.81 | 4.81 | 100 | 0
2670 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Ahamedpur Sub-District Water Testing Laboratory under Birbhum Division, P.H.E. Dte. as per direction & satisfaction of EIC as per tender stipulations including all taxes. | 226/AE/BSSD | 05/07/2021 | 3 | SAKTI ENTERPRISE | 4.81 | 4.81 | 100 | 0
2671 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation there off for Murarai Sub-District Water Testing Laboratory under Birbhum Division, P.H.E. Dte. as per direction & satisfaction of EIC as per tender stipulations including all taxes. | 360/NSD | 15/07/2021 | 90 | SAKTI ENTERPRISE | 4.82 | 4.82 | 100 | 0
2672 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Engagement of Resource person to implement water testing laboratory quality management system as per ISO/IEC: 17025 including supply of required equipments, laboratory glassware, reagents, standard reference materials traceable to NIST, measuring instruments & calibration of measuring instruments as per ISO 17025: 2017 protocol for Birbhum District Water Testing Laboratory under the Executive Engineer, Birbhum Division, PHE Dte, Government of West Bengal. (Sl. No.1) | 1850/BHM | 09/11/2021 | 181 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 19.13 | 16.74 | 87.55 | 0
2673 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Supply of consumables for on site mobile analysis system (OMAS) including cost of facilitating and co-ordinating for onsite testing of drinking water source through OMAS app ensuing 50 test / month by data up-dation on state water quality dash board (Sl. No.-01) | 127/BHM | 04/02/2021 | 15 | SAKTI ENTERPRISE | 3.98 | 7.73 | 200 | 0
2674 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Payment for survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability of drining water sanitation facility and other parameters in primary, upper primary school, anganwadi centres under Patel Nagar Sub-District laboratory within Birbhum Division, PHE Dte. (Sl No. 02) | 239/BH | 31/12/2020 | 15 | BHASKAR MANDAL | 0.75 | 0 | 0 | 0
2675 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Payment for survey and collection of data to the facilitor and Lab personnel for IMIS entry through mobile app regarding availability of drinking water station facility and other parameters in primary, upper primary school. anganwadi centers under Murarai Sub-District Laboratory within Birbhum Division, PHE Dte.(Sl.No.-03) | 240/BH | 31/12/2020 | 15 | DULAL MAJUMDAR | 0.85 | 0 | 0 | 0
2676 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Payment for survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability drinking water sanittation facility and other parameter in primary, upper primary school, anganwadi centres under Birbhum District Laboratory within Birbhum Division, PHE Dte.(Sl.No.01) | 238/BH | 31/12/2020 | 15 | DULAL MAJUMDAR | 0.7 | 0 | 0 | 0
2677 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability of drinking water sanitation facility and other parameters in primary, upper primary school, anganwadi entre underTubgram Sub-Distirct Lab within Birbhum Division, PHE Dte. within Birbhum Division,PHE Dte.(Sl.No.-09) | 246/BH | 31/12/2020 | 15 | DULAL MAJUMDAR | 0.85 | 0 | 0 | 0
2678 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Payment for survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability of drining water sanitation facility and other parameters in primary, upper primary school, anganwadi centres under Ahmedpur Sub-District laboratory within Birbhum Division, PHE Dte. (Sl No. 06) | 243/BH | 31/12/2020 | 15 | BHASKAR MANDAL | 0.69 | 0 | 0 | 0
2679 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Payment for survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability of drining water sanitation facility and other parameters in primary, upper primary school, anganwadi centres under Kanachi Sub-District laboratory within Birbhum Division, PHE Dte. (Sl No. 08) | 245/BH | 31/12/2020 | 15 | BHASKAR MANDAL | 0.66 | 0 | 0 | 0
2680 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Payment for survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability of drining water sanitation facility and other parameters in primary, upper primary school, anganwadi centres under Khoyrasole Sub-District laboratory within Birbhum Division, PHE Dte. (Sl No. 04) | 241/BH | 31/12/2021 | 15 | BHASKAR MANDAL | 0.9 | 0 | 0 | 0
2681 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Payment for survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability of drinking water sanitation facility and other parameters in primary, upper primary school, anganwadi centres under Mayureswar Sub-District laboratory within Birbhum Division, PHE Dte. (Sl No. 10) | 247/BH | 31/12/2020 | 15 | BHASKAR MANDAL | 0.6 | 0 | 0 | 0
2682 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Construction of Bacteriological Room adjacant to the Tubgram Grammyak Unnayan Laboratory under Nalhati Sub-Division within Birbhum Division, PHED. | 190/AE/NSD | 31/03/2022 | 45 | MD MONIRUL ISLAM | 3.36 | 0 | 0 | 0
2683 | BIRBHUM | Birbhum Division | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of PHE Managed Laboratories and NGO Managed Laboratories (Software) under Birbhum Division. , SM/06632 | Support-WQMSP | Supply of standard reference materials & safety item for attaining against NABL G-LAP assessment from NABL authority for Sub-District Laboratories of Birbhum District under the Executive Engineer, Birbhum Division, PHE Dte. | 376 /BHM | 21/02/2022 | 10 | SAKTI ENTERPRISE | 0.84 | 0 | 0 | 0
2684 | BIRBHUM | Birbhum Division | Supply and delivery of Desktop Computer and Multifunction machine (Printer including Scanner) under Birbhum Division P.H.E. Dte. , SM/18278 | Support-MIS | Supply and delivery of stationary articles under office of the assistant engineer, RWS Birbhum Division PHE Dte. (HP ink cartridge oem ribbon cartridge length 12.12 meter)) | BP-2023-24-167 | 19/09/2023 | 0 | R S TECHNOLOGY | 0.04 | 0 | 0 | 0
2685 | BIRBHUM | Birbhum Division | Supply and delivery of Desktop Computer and Multifunction machine (Printer including Scanner) under Birbhum Division P.H.E. Dte. , SM/18278 | Support-MIS | Supply and delivery of stationary articles under office of the assistant engineer, RWS Birbhum Division PHE Dte. (2nos 18A tonner received in good condition) | BP-2023-24-169 | 19/09/2023 | 0 | DISHA GARMENT | 0.05 | 0 | 0 | 0
2686 | BIRBHUM | Birbhum Division | Supply and delivery of Desktop Computer and Multifunction machine (Printer including Scanner) under Birbhum Division P.H.E. Dte. , SM/18278 | Support-MIS | Payment of GEM for Supply of HP Desktop 280G9 (6x3W3PA), Canon Printer LBP6030B APC UPS 600VA HP Pendrive 32GB and Quick heal total Security 3 user 3 year | BP-2023-24-214 | 17/10/2023 | 0 | PC CONCERN | 2.25 | 0 | 0 | 0
2687 | BIRBHUM | Birbhum Division | Supply and delivery of Desktop Computer and Multifunction machine (Printer including Scanner) under Birbhum Division P.H.E. Dte. , SM/18278 | Support-MIS | Supply and delivery of stationary articles under the office of the A.E RWS, Birbhum Sub Division PHE Dte (HP CC388A tonner HP CC3888A tonner HP CC388A tonner HP) | BP-2023-24-168 | 19/09/2023 | 0 | DISHA GARMENT | 0.05 | 0 | 0 | 0
2688 | BIRBHUM | Birbhum Division | Supply and delivery of Desktop Computer and Multifunction machine (Printer including Scanner) under Birbhum Division P.H.E. Dte. , SM/18278 | Support-MIS | Supply of Plain Copier Paper Bindal A4 Size with 75 G Per Through GEM (quantity 100) | BP-2023-24-400 | 21/02/2024 | 0 | URBAN ROOTS | 0.25 | 0 | 0 | 0
2689 | BIRBHUM | Birbhum Division | Supply and delivery of Desktop Computer and Multifunction machine (Printer including Scanner) under Birbhum Division P.H.E. Dte. , SM/18278 | Support-MIS | Supply and Delivery of HP Desktop 280G9 (6x3W3PA) and desktop PC (10 pc) canon printer LBP6030B and Printer(1Pc) APC UPS 600VA and UPS (10Pc), Canon Printer imageclass MF275DW and Printer (1pc) and Quick Heal total security 10 user 3years and antivirus (1Pc) under Birbhum Division PHE Dte. | BP-2023-24-419 | 07/03/2024 | 0 | PC CONCERN | 6.63 | 0 | 0 | 0
2690 | BIRBHUM | Birbhum Division | Supply and delivery of Desktop Computer and Multifunction machine (Printer including Scanner) under Birbhum Division P.H.E. Dte. , SM/18278 | Support-MIS | supply of HP 21.5" led monitor p22VB (3C0E6A7) APC UPS 600VA HP toner 88A Black Cartridge 88AD and Brother toner TNB021 under Birbhum Division PHE Dte | BP-2024-25-72 | 30/05/2024 | 0 | PCCONCERN | 0.59 | 0 | 0 | 0
2691 | BIRBHUM | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Birbhum District. , SM/09198 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Birbhum District. | 4731/RS | 19/08/2022 | 365 | IMAGIN | 271.87 | 271.87 | 100 | 100
2692 | BIRBHUM | Birbhum Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission , SM/19083 | Support-WQMSP | Collection & testing of drinking water sample and details information like geographical location GP name /Mouja/habitation location of source with reference household & institution viz schools. angawaris etc. through FTKs & uploading charges related to water quality monitoring and surveillance under JJM, (1) Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. (Phase-II) | BP-2024-25-110 | 20/06/2024 | 0 | DISTRICT HEALTH & FAMILY WELFARE SAMITI RAMPURHAT HEALTH DISTRICT | 20.16 | 0 | 0 | 0
2693 | BIRBHUM | Birbhum Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission , SM/19083 | Support-WQMSP | Collection & testing of drinking water sample and details information like geographical location GP name /Mouja/habitation location of source with reference household & institution viz schools. angawaris etc. through FTKs & uploading charges related to water quality monitoring and surveillance under JJM, (1) Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. (Phase-II) | BP-2024-25-109 | 20/06/2024 | 0 | DISTRICT HEALTH AND FAMILY WELFARE SAMITY (DHFWS), BIRBHUM | 21.3 | 0 | 0 | 0
2694 | BIRBHUM | Birbhum Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & surveillance under JJM under Birbhum Division PHE Dte. , SM/19263 | Support-WQMSP | Deployment/ Engagement for 5 Nos Sub- District Laboratory Personnel (5 nos. Chemist/Bacteriologist & 5 nos. Laboratory Assistant) & 1 no. Sampling Assistant (Ahmedpur Sub-Dist. Lab.) for a period of 01(One) years with effect from 01.01.2024 to 31.12.2024 for 5 nos. PHED Laboratories named Mayureswar Sub-District Laboratory, Patel Nagar Sub-District Laboratory, Ahmedpur Sub-District Laboratory, Murarai Sub-District Laboratory & Nalhati Sub district under Birbhum Division, P.H.E Dte. | 383/BHM | 29/12/2023 | 366 | DULAL MAJUMDAR | 35.34 | 0 | 0 | 92
2695 | BIRBHUM | Bolpur Mechanical | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratory. , SM/06628 | Support-WQMSP | Providing service by assigning Resource Person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing Sub-district level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereoff for Bolpur Mechanical Division Sub-District Water Testing Laboratory under Bolpur Mechanical Division PHE Dte. | 804/Bol.MD | 23/07/2021 | 92 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 0 | 0 | 0
2696 | BIRBHUM | Bolpur Mechanical | Procurement of Chemicals & Consumables, Glassware etc. required for smooth running of the Laboratory. , SM/06628 | Support-WQMSP | NABL | BP-2021-22-70 | 17/03/2022 | 0 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 4.83 | 0 | 0 | 0
2697 | BIRBHUM | Birbhum Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. , SM/08981 | Support-WQMSP | Collection & testing of drinking water sample and details information like geographical location GP name /Mouja/habitation location of source with reference household & institution viz schools. angawaris etc. through FTKs & uploading charges related to water quality monitoring and surveillance under JJM, (1) Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. | BP-2022-23-209 | 24/08/2022 | 0 | DISTRICT HEALTH AND FAMILY WELFARE SAMITY (DHFWS), BIRBHUM | 11.96 | 0 | 0 | 0
2698 | BIRBHUM | Birbhum Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. , SM/08981 | Support-WQMSP | Collection & testing of drinking water sample and details information like geographical location GP name /Mouja/habitation location of source with reference household & institution viz schools. angawaris etc. through FTKs & uploading charges related to water quality monitoring and surveillance under JJM, (1) Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. | BP-2022-23-180 | 10/08/2022 | 0 | DISTRICT HEALTH & FAMILY WELFARE SAMITI RAMPURHAT HEALTH DISTRICT | 7.25 | 0 | 0 | 0
2699 | BIRBHUM | Birbhum Division | Survey & collection of Data Through mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Birbhum District. , SM/09199 | Support-M&E | Payment for survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability of drining water sanitation facility and other parameters in primary, upper primary school, anganwadi centres under Patel Nagar Sub-District laboratory within Birbhum Division, PHE Dte. (Sl No. 02) | 239/BH | 31/12/2020 | 15 | BHASKAR MANDAL | 0.75 | 0.75 | 100 | 0
2700 | BIRBHUM | Birbhum Division | Survey & collection of Data Through mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Birbhum District. , SM/09199 | Support-M&E | Payment for survey and collection of data to the facilitor and Lab personnel for IMIS entry through mobile app regarding availability of drinking water station facility and other parameters in primary, upper primary school. anganwadi centers under Murarai Sub-District Laboratory within Birbhum Division, PHE Dte.(Sl.No.-03) | 240/BH | 31/12/2020 | 15 | DULAL MAJUMDAR | 0.85 | 0.85 | 100 | 0
2701 | BIRBHUM | Birbhum Division | Survey & collection of Data Through mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Birbhum District. , SM/09199 | Support-M&E | Payment for survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability drinking water sanittation facility and other parameter in primary, upper primary school, anganwadi centres under Birbhum District Laboratory within Birbhum Division, PHE Dte.(Sl.No.01) | 238/BH | 31/12/2020 | 15 | DULAL MAJUMDAR | 0.7 | 0.7 | 100 | 0
2702 | BIRBHUM | Birbhum Division | Survey & collection of Data Through mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Birbhum District. , SM/09199 | Support-M&E | Survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability of drinking water sanitation facility and other parameters in primary, upper primary school, anganwadi entre underTubgram Sub-Distirct Lab within Birbhum Division, PHE Dte. within Birbhum Division,PHE Dte.(Sl.No.-09) | 246/BH | 31/12/2020 | 15 | DULAL MAJUMDAR | 0.85 | 0.85 | 100 | 0
2703 | BIRBHUM | Birbhum Division | Survey & collection of Data Through mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Birbhum District. , SM/09199 | Support-M&E | Survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability of drinking water sanitation facility and other parameters in primary, upper primary school, anganwadi entre under Bolpur Mechanical Sub-Distirct Lab within Birbhum Division, PHE Dte. within Birbhum Division,PHE Dte.(Sl.No.-05) | 242/BH | 31/12/2020 | 15 | DULAL MAJUMDAR | 0.95 | 0.96 | 100 | 0
2704 | BIRBHUM | Birbhum Division | Survey & collection of Data Through mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Birbhum District. , SM/09199 | Support-M&E | Payment for survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability of drining water sanitation facility and other parameters in primary, upper primary school, anganwadi centres under Ahmedpur Sub-District laboratory within Birbhum Division, PHE Dte. (Sl No. 06) | 243/BH | 31/12/2020 | 15 | BHASKAR MANDAL | 0.69 | 0.69 | 100 | 0
2705 | BIRBHUM | Birbhum Division | Survey & collection of Data Through mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Birbhum District. , SM/09199 | Support-M&E | Payment for survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability of drining water sanitation facility and other parameters in primary, upper primary school, anganwadi centres under Kanachi Sub-District laboratory within Birbhum Division, PHE Dte. (Sl No. 08) | 245/BH | 31/12/2020 | 15 | BHASKAR MANDAL | 0.66 | 0.65 | 100 | 0
2706 | BIRBHUM | Birbhum Division | Survey & collection of Data Through mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Birbhum District. , SM/09199 | Support-M&E | Payment for survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability of drining water sanitation facility and other parameters in primary, upper primary school, anganwadi centres under Khoyrasole Sub-District laboratory within Birbhum Division, PHE Dte. (Sl No. 04) | 241/BH | 31/12/2021 | 15 | BHASKAR MANDAL | 0.9 | 0.9 | 100 | 0
2707 | BIRBHUM | Birbhum Division | Survey & collection of Data Through mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Birbhum District. , SM/09199 | Support-M&E | Payment for survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability of drinking water sanitation facility and other parameters in primary, upper primary school, anganwadi centres under Mayureswar Sub-District laboratory within Birbhum Division, PHE Dte. (Sl No. 10) | 247/BH | 31/12/2020 | 15 | BHASKAR MANDAL | 0.6 | 0.6 | 100 | 0
2708 | BIRBHUM | Birbhum Division | Survey & collection of Data Through mobile App regarding availability of drinking water, sanitation facilities & other parameters in Primary & Upper Primary Schools, Anganwadi Centers within Birbhum District. , SM/09199 | Support-M&E | Survey and collection of data to the facilitor and lab personnel for IMIS entry through mobile app regarding availability of drinking water sanitation facility and other parameters in primary, upper primary school, anganwadi entre under Rampurhat Sub-Distirct Lab within Birbhum Division, PHE Dte. within Birbhum Division,PHE Dte.(Sl.No.-07) | 244/BH | 31/12/2020 | 15 | DULAL MAJUMDAR | 0.98 | 0.98 | 100 | 0
2709 | BIRBHUM | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. , SM/15637 | Support-WQMSP | Procurement of chemical & consumable for BirbhumDistrict Laboratory PHE Dte managed Laboratory (4 Nos) & NGo managed Laboratory(4 Nos) under Birbhum Division PHE Dte. For a period 03 months under Birbhum Division Phe Dte. | 125/BHM | 24/01/2022 | 30 | LAXMI ENTERPRISE | 15.7 | 15.7 | 100 | 0
2710 | BIRBHUM | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. , SM/15637 | Support-WQMSP | Procurement of chemical & consumable for Birbhum District Laboratory and 5 nos PHED managed Laboratory namely Mayureswar Sub-District Lab, Patel Nagar Sub Dist-District Lab, Ahmedpur Sub-District Lab, Nalhati Sub-District Lab and Murarai Sub- District Lab under Birbhum Division, PHE Dte. | 762/BHM | 09/03/2023 | 30 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 42.62 | 0 | 0 | 100
2711 | BIRBHUM | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. , SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Paribesh Pariseva Sub District Laboratory under Birbhum Division, PHE Dte. | 102/RWS | 06/05/2025 | 10 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.94 | 0 | 0 | 95
2712 | BIRBHUM | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. , SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Mayureswar Sub District Laboratory under Birbhum Division, PHE Dte. | 101/RWS | 06/05/2025 | 10 | DULAL MAJUMDAR | 0.97 | 0 | 0 | 95
2713 | BIRBHUM | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. , SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Khayrasole Pally Mongal Samity Sub District Laboratory under Birbhum Division, PHE Dte. | 108/RWS | 06/05/2025 | 10 | LAB ANALYTICS | 0.97 | 0 | 0 | 95
2714 | BIRBHUM | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. , SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Kanachi Khadi Bhandar Sub District Laboratory under Birbhum Division, PHE Dte. | 107/RWS | 06/05/2025 | 10 | DULAL MAJUMDAR | 0.96 | 0 | 0 | 95
2715 | BIRBHUM | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. , SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Nalhati Sub District Laboratory under Birbhum Division, PHE Dte. | 103/RWS | 06/05/2025 | 10 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.98 | 0 | 0 | 95
2716 | BIRBHUM | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. , SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Murarai Sub District Laboratory under Birbhum Division, PHE Dte. | 106/RWS | 06/05/2025 | 10 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.93 | 0 | 0 | 95
2717 | BIRBHUM | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. , SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Birbhum District Water Testing Laboratory under Birbhum Division, PHE Dte | 100/RWS | 06/05/2025 | 10 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.96 | 0 | 0 | 95
2718 | BIRBHUM | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. , SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Ahmedpur Sub District Laboratory under Birbhum Division, PHE Dte. | 104/RWS | 06/05/2025 | 10 | LAB ANALYTICS | 0.98 | 0 | 0 | 95
2719 | BIRBHUM | Birbhum Division | Procurement of chemicals and consumables, glassware etc. required for smooth running of the different laboratories under Birbhum Division, PHE Dte. , SM/15637 | Support-WQMSP | Supply of Chemicals & Consumables etc. required for smooth running of Patelnagar Sub District Laboratory under Birbhum Division, PHE Dte. | 105/RWS | 06/05/2025 | 10 | LAB ANALYTICS | 0.98 | 0 | 0 | 95
Total | [9 empty] | 2032986.12 | 23008.95 | 1.13