## List of issued work order (Rs.
List of issued work order (Rs. in Lakh)
Sl No. | District | Division | Scheme | Scheme Category | Work Name | WO Number | WO Date | Days of Completion | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman , SM/08103 | Retrofitting | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 1ST TW Site of SRIRAMPUR & its adjoining mouzas Piped Water Supply Scheme, Block ? Purbasthali ? I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 5127/BWD | 21/11/2022 | 30 | M/S SYCHROTECH INDUSTRY | 8.73 | 0 | 0 | 0
2 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman , SM/08103 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Srirampur Piped Water Supply Scheme at Srirampur (Srirampur & Srirampur East Para Habitation) Village (Mouza), Purbasthali-I Block under Burdwan Division, PHE Dte. | 3654/BWD | 14/07/2021 | 60 | ASHOK KUMAR GHOSH | 102.42 | 84 | 100 | 1
3 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman , SM/08103 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Srirampur Piped Water Supply Scheme at Srirampur Northpara, Srirampur Southpara & Srirampur Westpara within Srirampur (P) Village (Mouza), Purbasthali-I Block under Burdwan Division, PHE Dte. | 7002/BWD | 16/12/2021 | 60 | HAMID SK | 71.23 | 70.84 | 100 | 1
4 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman , SM/08103 | Retrofitting | Bypass arrangement of rising main and providing Functional house hold tap connections at Srirampur GP within Purbasthali-I Block under SRIRAMPUR PWSS under Burdwan Division, PHE Dte. | 889/BWD | 01/03/2023 | 30 | JAMALUDDIN SK | 13.01 | 12.88 | 99 | 0
5 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman , SM/08103 | Retrofitting | Work order for " Providing Functional house hold tap connections for Sajal Gram Village within Purbasthali-I Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Nadanghat & others scheme) Sl No-7" | 103/KSD | 08/02/2023 | 28 | MOMINUL ISLAM MONDAL | 0.88 | 0 | 0 | 0
6 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman , SM/08103 | Retrofitting | Laying of additional UPVC pipeline for interconnection with main line to branch line of SRIRAMPUR Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 4522/BWD | 12/10/2023 | 30 | JAMALUDDIN SK | 6.16 | 5.78 | 100 | 100
7 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman , SM/08103 | Retrofitting | NAME OF THE WORK -RESTORATION WORK OF BIDYANAGAR TO VIA DAMODAR PARA TO BOGPUR ROAD,PACKAGE NO-WB-22-27,BLOCK-PURBASTHALI-1,GP-SRIRAMPUR & JAHANNAGAR. | 893/JJM | 25/09/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 5.21 | 0 | 0 | 0
8 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Srirampur Piped Water Supply Scheme, Purbasthali-I, Purba Bardhaman , SM/08103 | Retrofitting | Different types of works involve in connection with Augmentation of SRIRAMPUR (Zone I & II) (SM/08103), MANGANPUR (SM/13327), KAMALPUR (SM/13453) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2429/BWD | 27/06/2024 | 480 | S.P. CONSTRUCTION | 500.89 | 128.67 | 87.53 | 2
9 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme , SM/07201 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Pt-A) village of Sahapur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [SL.No : 11A] (Agreement no. 500/BWD of 2020-21) | 2608/BWD | 04/08/2020 | 30 | RAINBOW CONSTRUCTION | 4.92 | 9.84 | 200 | 1
10 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme , SM/07201 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Pt-A) village of Sahapur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [SL.No : 11A] (Agreement no.505/BWD of 2020-21) | 2607/BWD | 04/08/2020 | 30 | DUBE ENTERPRISE | 4.92 | 9.84 | 200 | 1
11 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme , SM/07201 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Pt-B) village of Sahapur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [SL.No : ¿11B¿](Agreement no.-497/BWD of 2020-21) | 4913/BWD | 08/12/2020 | 30 | DUBE ENTERPRISE | 2.84 | 0 | 0 | 1
12 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme , SM/07201 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Part-A) village of Sahapur piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-503/BWD/20-21) | 238/KTS | 30/09/2020 | 4 | RAINBOW CONSTRUCTION | 1.45 | 2.89 | 200 | 1
13 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme , SM/07201 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in SAHAPUR (Part-B) village of Sahapur piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-494/BWD/2020-21) | 239/KTS | 30/09/2020 | 4 | DUBE ENTERPRISE | 1.42 | 2.82 | 200 | 1
14 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme , SM/07201 | Retrofitting | Publication charges bill for the office of the Executive Engineer, Burdwan Division, PHE Dte.[Invoice No.-BCWB20RV-0001293, dt.-19/05/20, BCWB20RV-0001770, dt.-31/05/20, BCWB20RV-0001920, dt.-05/06/20, BCWB20RV-0001860, dt.-03/06/20, BCWB20RV-0001861, dt.-03/06/20, BCWB20RV-0001928, dt.-05/06/20, BCWB20RV-0001820, dt.-03/06/20, BCWB19RV-0059455, dt.-20/03/20, BCWB19RV-0059454. dt.-20/03/20, BCWB19RV-0057682, dt.-12/03/20, BCWB20RV-0003210, dt.-26/06/20, BCWB20RV-0000918, dt.-07/05/20, BCWB20RV-0001352, dt.-22/05/20, BCWB19RV-0050592, dt.-30/01/20] | 240/DW/22-23 | 04/07/2022 | 0 | BENNETT COLEMAN & COMPANY LIMITED | 1.89 | 0 | 0 | 0
15 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme , SM/07201 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the month of May & June'23. | 632/JJM | 13/09/2023 | 0 | PARTHA PRATIM ACHARYA | 0.77 | 0 | 0 | 0
16 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme , SM/07201 | Retrofitting | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme AGRADWIP, KHETPUR PALASHI, SAHAPUR PWSS (Sl No-1) | 393/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 3.71 | 1.24 | 100 | 100
17 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme , SM/07201 | Retrofitting | Augmentation of SAHAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & renovation of switch-rooms & boundary walls at different TW site under Katwa-II Block, District:- Purba-Bardhaman. | 2343/BWD | 22/05/2023 | 120 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 137.76 | 8.74 | 100 | 95
18 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Sahapurr Piped Water Supply Scheme , SM/07201 | Retrofitting | Continuation work order for Supply of 1 (one) No. Diesel driven Ambassador Car (Luxury Taxi) / Motor Cab on hire basis for the Office of the Assistant Engineer, under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.07.2024 to 31.12.2024]. | 788/KTS | 28/06/2024 | 183 | KRISHNA MONDAL | 2.4 | 2.32 | 96.65 | 80
19 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS , SM/06751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of MANIKHAR Piped Water Supply Scheme at Kalna-I Block under Burdwan Division, PHE Dte. (Agreement No. 47/2020-2021 OF SE/CC/PHE. DTE.) | 4787/BWD | 02/12/2020 | 90 | H SAMANTA | 96.04 | 0 | 0 | 1
20 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS , SM/06751 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of March to September'2022. | 866/VEH | 09/12/2022 | 0 | PARTHA PRATIM ACHARYA | 2.79 | 0 | 0 | 0
21 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS , SM/06751 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PANUHAT Piped Water Supply Scheme at different villages, Katwa-I Block under Burdwan Division, PHE Dte. (Part-A).[Agreement No. 727/BWD OF 2020-2021.] | 1688/BWD | 24/02/2021 | 45 | HAMID SK | 35.66 | 32.68 | 200 | 0
22 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS , SM/06751 | Retrofitting | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-5]. | 3590/BWD | 13/07/2021 | 30 | PREMANANDA ROY BISWAS | 127.5 | 82.29 | 200 | 1
23 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS , SM/06751 | Retrofitting | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-4]. | 3117/BWD | 02/06/2021 | 30 | PREMANANDA ROY BISWAS | 76.65 | 27.07 | 200 | 0
24 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Manikhar PWS , SM/06751 | Retrofitting | Supply of 10 mm NB Gun-Metal Ferrule conforming to IS:2692-1989 for water tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-4] | 3186/BWD | 08/06/2021 | 30 | R.K. INDUSTRIES | 76.05 | 50.06 | 200 | 0
25 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Abujhati village of Abujhati piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-312/BWD/2020-21) | 2739/BWD | 10/08/2020 | 30 | INDRAJIT MONDAL | 4.92 | 9.84 | 200 | 1
26 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of Abujhati piped water supply scheme at Astai, Dastanpur & Keotara village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Tr No.-624/BWD/20-21] | 955/BWD | 03/02/2021 | 45 | BHARAT CONSTRUCTION | 41.04 | 79.36 | 200 | 1
27 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Providing functional household tap connection from existing distribution system within the command area of Abujhati piped water supply scheme at Napara, Panchshimul & Siromani village Jamalpur Block under Burdwan Division, PHE Dte. (Tr No.-627/BWD/2020-21) | 954/BWD | 03/02/2021 | 45 | KOUSIK MALLICK | 38.9 | 77.15 | 200 | 1
28 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Abujhati village of Abujhati piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-456/BWD/2020-21) | 3740/BWD | 07/10/2020 | 30 | INDRAJIT MONDAL | 4.92 | 9.84 | 200 | 1
29 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ajhapur village of Abujhati piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-331/BWD/2020-21) | 2748/BWD | 10/08/2020 | 30 | E-WORLD | 4.92 | 9.84 | 200 | 1
30 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) of ABUJHATI & its adjoining mouzas Piped Water Supply Scheme, Block - Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 5125/BWD | 21/11/2022 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 11.23 | 10.88 | 96.85 | 1
31 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). | 40/BWD | 05/01/2022 | 30 | PREMANANDA ROY BISWAS | 22.68 | 7.4 | 100 | 1
32 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. | 1454/BWD | 11/03/2022 | 30 | PREMANANDA ROY BISWAS | 18.83 | 6 | 100 | 1
33 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Withdrawing and Relaying of Rising main line and Bullah pilling (60.0 mtr) at HD Works Site (near pond) due to Road widening from 4lane to 6 lane of NH2 at chanage 601+951 and 601+650 of ABUJHATI PWSS to in Jamalpur Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1290/BWD | 20/03/2023 | 30 | SOUMYAVASH DAS | 5.77 | 5.74 | 100 | 100
34 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ajhapur village of Abujhati piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-429/BWD/2020-21) | 3803/BWD | 08/10/2020 | 30 | E-WORLD | 4.92 | 9.84 | 200 | 1
35 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Improvement of 300cum. OHR (Concreting,Plastering,Primer and Painting) for Abujhati PWSS under Jamalpur Block under Burdwan Division PHE Dte. | 1015/BSD | 07/06/2024 | 45 | DEBASHISH ENTERPRISE | 2.01 | 0 | 0 | 0
36 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Abujhati Piped Water Supply Scheme at Abujhati (Part) (3 Nos Habitation Part) & Ajapur (Part) (Abujhati Part Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. _2ND CALL. [Agreement No. 754/BWD OF 2020-2021] | 1740/BWD | 25/02/2021 | 45 | T.K. BANERJEE & CO. | 34.87 | 70.22 | 200 | 0
37 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Extension of pipeline for providing functional household tap connection at Dastanpur & Keotara village (Mouza) of ABUJHATI piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Gr.-D) | 1091/BSD | 18/08/2021 | 45 | BHARAT CONSTRUCTION | 3.36 | 6.69 | 200 | 0
38 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Laying different dia UPVC Pipeline for inter connection of existing FHTC near Kayastyaparan of Abujhati Flyover i.c.w. Road widening from 4 lane to 6 lane of NH-2 at chane 601+9521+960 under ABUIHATI PWSS in jamalpur Block within Burdwan Sub Divn. under Burdwan Division, P.H.E. Dte. | 517/BSD | 13/03/2024 | 30 | SOUMYAVASH DAS | 0.89 | 0.88 | 100 | 100
39 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ABUJHATI Piped Water Supply Scheme at Jamalpur Block , SM/07861 | Retrofitting | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 0 | 40
40 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block , SM/07804 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dirghapara village and Dirghapara (Part-B) habitation of Dirghapara piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-484/BWD/2020-21) | 4119/BWD | 16/10/2020 | 30 | SK NUR ALAM | 4.86 | 9.73 | 200 | 1
41 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block , SM/07804 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [Sl. No. : ¿11¿] | 61/BWD | 05/01/2021 | 15 | SK NUR ALAM | 4.86 | 9.71 | 200 | 1
42 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block , SM/07804 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village , Kharashgram (Part) habitation of Dirghapara piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Part-C][SL NO.-12] | 62/BWD | 05/01/2021 | 15 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.84 | 9.68 | 200 | 1
43 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block , SM/07804 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [Sl. No. : ¿10¿] | 6231/BWD | 01/11/2021 | 15 | HAFIJUR RAHAMAN MIDYA | 4.86 | 4.86 | 100 | 1
44 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block , SM/07804 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [Sl. No. : ¿11¿] | 6232/BWD | 01/11/2021 | 15 | SK NUR ALAM | 4.86 | 4.76 | 100 | 1
45 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block , SM/07804 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dirghapara village and Dirghapara (Part-A) habitation of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿8A¿] | 4391/BWD | 31/08/2021 | 30 | HAFIJUR RAHAMAN MIDYA | 4.55 | 8.2 | 200 | 1
46 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block , SM/07804 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [Sl. No. : ¿10¿] | 60/BWD | 05/01/2021 | 15 | HAFIJUR RAHAMAN MIDYA | 4.86 | 9.72 | 200 | 1
47 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block , SM/07804 | Retrofitting | Extension of 63 mm dia UPVC pipeline to provide house connection at different leftout portion of Dirghapara w/s scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Sl-E] | 171/KSD | 19/02/2021 | 30 | SK RAJU | 1.78 | 1.62 | 100 | 1
48 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block , SM/07804 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kharashgram (Part) village (Kharashgram (Part) habitation) of Dirghapara Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part - C) [Sl. No. : ¿12¿] | 6401/BWD | 16/11/2021 | 15 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.84 | 4.84 | 100 | 1
49 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block , SM/07804 | Retrofitting | Restoration of UPVC pipeline which damaged during construction of PCC road & providing FHTC work at DIRGHAPARA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 5594/BWD | 20/12/2023 | 30 | UTPAL NANDI | 8.31 | 0 | 0 | 0
50 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block , SM/07804 | Retrofitting | Extension of different dia UPVC pipeline at the leftout portion of Kharoshgram village of Dirghapara PWSS within Kalna Sub-Division under Burdwan Division, PHE Dte. | 6106/BWD | 08/10/2021 | 30 | M/S UNIQUE | 6.67 | 6.86 | 100 | 1
51 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block , SM/07804 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jagarpur & Mugura village of Mugura Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿3B¿] (Agreement no.238/BWD of 2020-21) | 4118/BWD | 16/10/2020 | 30 | HAFIJUR RAHAMAN MIDYA | 4.92 | 9.73 | 200 | 1
52 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Dirghapara Piped Water Supply Scheme at Purbasthali-I Block , SM/07804 | Retrofitting | Different types of works involve in connection with Augmentation of DIRGHAPARA (SM/07804) Water Supply Scheme, MOUDANGA (SM/ 14020) Water supply Scheme & BHANDARTIKURI (SM/14925) Water Supply Scheme under Burdwan Division, PHE Dte. | 2912/BWD | 25/07/2024 | 431 | BANSBERIA CONSTRUCTION CO. | 293.38 | 0 | 0 | 22
53 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS , SM/06768 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Purba Sahapur (Pt-B) village of Purba Sahapur Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 7B] | 2584/BWD | 09/07/2020 | 30 | SETH ENTERPRISE | 4.92 | 0 | 0 | 1
54 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS , SM/06768 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Purba Sahapur (Pt-A) village of Purba Sahapur Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 7A] | 2585/BWD | 09/07/2020 | 30 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.92 | 0 | 0 | 1
55 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS , SM/06768 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Purba Sahapur (Pt-B) village of Purba Sahapur Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 7B] | 2587/BWD | 04/08/2020 | 30 | SETH ENTERPRISE | 4.92 | 4.92 | 100 | 1
56 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS , SM/06768 | Retrofitting | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] | 4318/BWD | 04/11/2020 | 10 | MD HASIN | 4.93 | 2.55 | 100 | 1
57 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS , SM/06768 | Retrofitting | Extension of pipeline at Purbasahapur mouza under Purbasahapur water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Sl-A] | 29/KSD | 11/01/2021 | 45 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.84 | 4.73 | 100 | 1
58 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS , SM/06768 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Pt-A) village of Sahapur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [SL.No : ¿11A¿] (Agreement no.-501/BWD of 2020-21) | 4083/BWD | 16/10/2020 | 30 | RAINBOW CONSTRUCTION | 2.23 | 4.46 | 200 | 1
59 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS , SM/06768 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur (Part-B) village of Sahapur piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-497/BWD/2020-21) | 4007/BWD | 14/10/2020 | 30 | DUBE ENTERPRISE | 2.84 | 5.67 | 200 | 0
60 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS , SM/06768 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahapur, Char Sahapur and Natungram village of Sahapur piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. (Tr No.-789/BWD/2020-21) | 365/KTS | 15/12/2020 | 7 | DUBE ENTERPRISE | 2.46 | 4.92 | 200 | 0
61 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Purba Sahapur PWSS , SM/06768 | Retrofitting | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 03 Nos. Piped W/S. Schemes under Kalna II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3016/BWD | 05/08/2024 | 20 | HORIZEN | 7.55 | 2.52 | 100 | 100
62 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Adra village (Adrahati habitation) of ADRA Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 05] [Agr. No. 745/BWD of 2020-2021] | 584/BWD | 25/01/2021 | 15 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 4.86 | 0 | 0 | 1
63 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Adra village (Adrahati habitation) of ADRA Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 05] | 6264/BWD | 02/11/2021 | 15 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 4.86 | 4.86 | 100 | 1
64 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Adra village (Adrahati habitation) of ADRA Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - C) [SL. No. : 07] | 6194/BWD | 28/10/2021 | 15 | LAKSHMIKANTA DAS | 4.86 | 4.86 | 100 | 1
65 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mohara vilage (Mohara habitation) of ADRA Piped W/S Scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-E] | 673/DSD | 29/11/2021 | 21 | KOUSIK MALLICK | 4.83 | 4.83 | 100 | 1
66 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from distribution system within the command area of ADRA Water Supply Scheme at Adra (Part), Mohara (Part), Kaitara and Patrahati village under JAL SAPNO MISSION under Galsi-II Block in Purba Bardhanan District under Burdwan Division, P.H.E. Dte. | 384/BWD | 20/01/2022 | 60 | SHUBHRA KANTI GHOSH | 69.37 | 69.38 | 100 | 1
67 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Extension of UPVC pipe line of LDS at Khanhati and Patrahati Mouza for providing FHTC of Adra and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte.[SL-23] | 706/DSD | 31/12/2022 | 30 | UTPAL NANDI | 4.46 | 4.44 | 99.48 | 0
68 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Adra village (Adrahati habitation) of ADRA Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [SL. No. : 06] | 585/BWD | 25/01/2021 | 15 | BASUNDHARA SOLUTION | 4.86 | 4.86 | 100 | 1
69 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila Habitation) of Bagila piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Part-B)[SL NO.-09] | 585./BWD | 25/01/2021 | 15 | HAMID SK | 4.87 | 0 | 0 | 1
70 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Relaying and repairing of distribution after widening of PWD road in between Chainage 8.40 km to 10.74 km of Galsi Gohogram road between Node 74 to Node 117 within Adra W/S Scheme at Durgapur Sub-Division in Galsi-II Block under Burdwan Division, P.H.E. Dte.[Gr.-D] | 03/DSD | 03/01/2022 | 30 | SHUBHRA KANTI GHOSH | 4.82 | 0 | 0 | 1
71 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Connecting, relaying and repairing of distribution main towards Irkona (Node 4 to Node 18) and Mohora village Node 157 to Node 163 with newly reoriented line (from Chainage 8.40 km to 10.74 km of Galsi Gohogram road and from Node 152 to Node 157 beside PMGSY road) within Adra W/S Scheme at Durgapur Sub-Division in Galsi-II Block under Burdwan Division, P.H.E. Dte. (Gr.-'E') | 554/DSD | 22/12/2020 | 21 | PAL CONSTRUCTION | 2.1 | 0 | 0 | 1
72 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mohara (Part), Kaitara (Part) and Khanhati (Part) Village of Adra Piped W/S Scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-A] | 342/DSD | 30/06/2022 | 21 | SHUBHRA KANTI GHOSH | 4.82 | 4.82 | 100 | 1
73 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Sinking of 200 mm dia. River Bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Gohogram village Block -Galsi-II, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-A] | 494/DSD | 12/08/2022 | 21 | KOUSIK MALLICK | 4.35 | 0 | 0 | 1
74 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Sinking of 200 mm dia River Bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Simasimi village Block -Galsi-I, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-B] | 495/DSD | 12/08/2022 | 21 | MUNSHI JAVEDUR JAMAN | 4.35 | 0 | 0 | 1
75 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Extension of UPVC pipe line of LDS at Kaitara, Patrahati and Mahara Mouza for providing FHTC of Adra and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-E] | 498/DSD | 12/08/2022 | 30 | SHUBHRA KANTI GHOSH | 4.81 | 4.78 | 100 | 1
76 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Carriage of withdrawal stacked DI pipes of rising main from Adrahati to Barsul Divisional store and restoration of damaged pipeline of distribution main for construction of drain, concrete road etc at various point at Khanhati village for providing FHTC within Adra W/S Scheme in Galsi-II Block under Durgapur Sub Division, P.H.E. Dte. [SL-06] | 732/DSD | 30/12/2022 | 21 | SHUBHRA KANTI GHOSH | 0.61 | 0 | 0 | 25
77 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Restoration and relaying of damaged pipeline of distribution main for construction of drain, concrete road etc at Ruidaspara (South end) of Adra village for providing left out FHTC at Ruidaspara (South end) within Adra W/S Scheme in Galsi-II Block under Burdwan Division, P.H.E. Dte.[SL-12] | 160/DSD | 13/04/2023 | 21 | SHUBHRA KANTI GHOSH | 0.96 | 0.96 | 100 | 100
78 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Providing left out FHTC for making Swajal Gram at Khanhati village within Adra Water supply Scheme in Galsi-II Block under Burdwan Division, P.H.E. Dte.[SL-09] | 157/DSD | 13/04/2023 | 21 | SHUBHRA KANTI GHOSH | 0.97 | 0.96 | 100 | 100
79 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ADRA Piped Water Supply Scheme at Kaitara village, Galsi-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-9] | 735/DSD | 30/12/2022 | 21 | SHUBHRA KANTI GHOSH | 0.97 | 0.95 | 100 | 100
80 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mohara (Part) Village of Adra Piped W/S Scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [SL-12] | 737/DSD | 30/12/2022 | 21 | SHUBHRA KANTI GHOSH | 0.94 | 0.93 | 100 | 100
81 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Adra Piped Water Supply Scheme at Galsi-II Block , SM/07829 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kaitara (Part) Village of Adra Piped W/S Scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [SL-11] | 736/DSD | 30/12/2022 | 21 | SHUBHRA KANTI GHOSH | 0.96 | 0.96 | 100 | 100
82 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS , SM/06770 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madanagar habitation of Madanagar piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Tr No.-531/BWD/2020-21) | 3741/BWD | 07/10/2020 | 30 | PABITRA KUMAR SAMANTA | 4.92 | 9.84 | 200 | 1
83 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS , SM/06770 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madanagar village of Madanagar piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-716/BWD/2020-21) | 1224/BWD | 11/02/2021 | 30 | PABITRA KUMAR SAMANTA | 3.76 | 7.53 | 200 | 1
84 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS , SM/06770 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madanagar (Part) village (Madanagar Mejhpur Habitation) of Madanagar piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 69/BWD | 05/01/2021 | 15 | PABITRA KUMAR SAMANTA | 4.86 | 8.11 | 200 | 1
85 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS , SM/06770 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ I Block under Burdwan Division, PHE. Dte. | 39/BWD | 05/01/2022 | 30 | HAFIJUR RAHAMAN MIDYA | 15.62 | 0 | 0 | 1
86 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS , SM/06770 | Retrofitting | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of MADANAGAR Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1935/BWD | 24/04/2023 | 30 | S.C. ENTERPRISE | 20.87 | 20.64 | 100 | 100
87 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS , SM/06770 | Retrofitting | Preparation and Submission of DPR for Augmentation of Ground Water Based Piped Water Supply Scheme for MADHANAGAR, Block:Raina-I under Burdwan Division, P.H.E Dte. | 1912/BSD | 28/08/2024 | 15 | MEASURE LAND | 0.78 | 0 | 0 | 0
88 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Madanagar PWSS , SM/06770 | Retrofitting | Restore of damaged Pipeline at Madanagar Dakshin Para under MADANAGAR Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | 823/BWD | 28/02/2024 | 424 | UTPAL NANDI | 6.18 | 0 | 0 | 100
89 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District , SM/09403 | Augmentation | Preparation of DPR for augmentation of Anukhal W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-D) | 206/KSD | 23/02/2022 | 21 | INDRANIL DUTTA & ASSOCIATES | 2.86 | 2.82 | 100 | 1
90 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District , SM/09403 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
91 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District , SM/09403 | Augmentation | Material Requisition To Resource Division | 1533/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
92 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District , SM/09403 | Augmentation | Material Requisition To Resource Division | 531/BWD | 27/01/2022 | 0 | Resource Division | 14.56 | 0 | 0 | 0
93 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District , SM/09403 | Augmentation | Material Requisition To Resource Division | 1242/BWD | 07/03/2022 | 0 | Resource Division | 4.93 | 0 | 0 | 0
94 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District , SM/09403 | Augmentation | Material Requisition To Resource Division | 1320/BWD | 08/03/2022 | 0 | Resource Division | 32.89 | 0 | 0 | 0
95 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District , SM/09403 | Augmentation | Material Requisition To Resource Division | 4627/BWD | 17/10/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
96 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District , SM/09403 | Augmentation | Augmentation of ANUKHAL Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation with construction of boundary wall at Headworks site under Kalna-II Block, District:- Purba-Burdwan. | 2741/BWD | 08/06/2022 | 365 | SINGHA ROY AND CO. | 374.09 | 327.71 | 87.6 | 70
97 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District , SM/09403 | Augmentation | Additional work to implement augmentation of ANUKHAL Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 4998/BWD | 21/11/2023 | 30 | UDYOG CONSTRUCTION | 7.48 | 3.91 | 100 | 100
98 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District , SM/09403 | Augmentation | Quotation from WBSEDCL for Augmentation of Anukhal w/s scheme under Burdwan Division, PHE Dte. P.H. No.-3 & 4. | 1046/JJM | 30/10/2024 | 0 | WBSEDCL | 17.05 | 0 | 0 | 0
99 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District , SM/09403 | Augmentation | Sinking of tube well, Laying dist. system, Providing FHTC, construction of Pump House & Boundary and Laying rising main of ANUKHAL Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. | 5206/BWD | 29/11/2023 | 120 | SINGHA ROY AND CO. | 119.49 | 19.33 | 16.18 | 15
100 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ANUKHAL PWSS for providing Functional Household Tap Connection (FHTC) KALNA-II block under KALNA Sub Division of Burdwan Division in Purba Bardhaman District , SM/09403 | Augmentation | Work Order for Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory under The Assistant Engineer, Kalna Sub-Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation,Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL : Anukhal Sub District Water Testing Laboratory under Kalna Sub Division.) | 1335/KSD | 28/08/2023 | 30 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.91 | 0 | 0 | 100
101 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09405 | Augmentation | Route Survey & Preparation of DPR for Sankari W/S Scheme under Khandaghosh Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.10. | 185/BSD | 31/01/2022 | 30 | RADIANT | 2.52 | 2.52 | 100 | 1
102 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09405 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
103 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09405 | Augmentation | Augmentation of SANKARI Piped Water Supply Scheme with LDS, Rising Main, Constn. of 250 cum capacity OHR with 20.0 Mtr. staging height inclusive of soil test & FHTC under Khandaghosh Block, District - Purba Bardhaman. | 1119/BWD | 28/02/2022 | 365 | UNIQUE AGENCY | 208.48 | 186.67 | 89.54 | 100
104 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09405 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of SANKARI Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte._SL No. 06 | 140/AE/HQ | 16/03/2022 | 10 | MAKALI ENGINEERING CORPORATION | 4.52 | 0 | 0 | 0
105 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09405 | Augmentation | Material Requisition To Resource Division | 1527/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
106 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09405 | Augmentation | Material Requisition To Resource Division | 529/BWD | 27/01/2022 | 0 | Resource Division | 6.82 | 0 | 0 | 0
107 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SANKARI PWSS to accommodate FHTC in KHANDOGHOSH block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09405 | Augmentation | Material Requisition To Resource Division | 903/BWD | 15/02/2022 | 0 | Resource Division | 18.21 | 0 | 0 | 0
108 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman , SM/09408 | Augmentation | Route Survey & Preparation of DPR for Sehara W/S Scheme under Raina-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.9 | 184/BSD | 31/01/2022 | 30 | RADIANT | 2.85 | 2.85 | 100 | 1
109 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman , SM/09408 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
110 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman , SM/09408 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of SEHARA & its adjoining mouzas Piped Water Supply Scheme, Block ¿ Raina ¿ I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 5025/BWD | 10/11/2022 | 30 | M/S D. PALIT & CO. | 10.06 | 8.26 | 100 | 1
111 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman , SM/09408 | Augmentation | Material Requisition To Resource Division | 1535/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
112 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman , SM/09408 | Augmentation | Material Requisition To Resource Division | 536/BWD | 27/01/2022 | 0 | Resource Division | 15.56 | 0 | 0 | 0
113 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman , SM/09408 | Augmentation | Material Requisition To Resource Division | 902/BWD | 15/02/2022 | 0 | Resource Division | 13.85 | 0 | 0 | 0
114 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman , SM/09408 | Augmentation | Augmentation of SEHARA Piped Water Supply Scheme with LDS, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & FHTC under Raina ¿ I Block, District - Purba Bardhaman. | 1473/BWD | 14/03/2022 | 365 | M/S PIONEER CONSTRUCTION | 430.73 | 394.99 | 91.7 | 100
115 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SEHARA PWSS to accommodate FHTC in RAINA-I Block under Burdwan Suv Division of Burdwan Division in Purba Bardhaman , SM/09408 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at TubeWell Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17 (Size3.60mtr x 3.00mtr room) for SEHARA its Adjoining Mouza W/S Scheme, Block -Raina-I within Burdwan Sub-Division, PHE Dte. (Mouza- Sehara)_2ND CALL | 2041/BSD | 24/08/2023 | 45 | ANWESHA CONSTRUCTION | 3.21 | 2.87 | 100 | 100
116 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kalyanbati, Narayapur and Radhakrishnapur mouzas within the command area of Sudpur piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08717 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Head Work Site to departmental drawing (Size 3.60 mtr x 3.00 mtr room) for SUDPUR water supply schemes under Katwa Sub-Division within Burdwan Division, PHE Dte.(Sl No-7) | 595/KTS | 06/09/2021 | 45 | BABUL SK | 2.99 | 2.62 | 100 | 1
117 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kalyanbati, Narayapur and Radhakrishnapur mouzas within the command area of Sudpur piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08717 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Rayerpara, Purba and Paschim Bijoynagar village under SUDPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte [Sl - 5 ] | 565/KTS | 31/08/2021 | 15 | HAMID SK | 3.6 | 3.59 | 100 | 1
118 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kalyanbati, Narayapur and Radhakrishnapur mouzas within the command area of Sudpur piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08717 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Sudpur, Lokpur & Narayanpur village under SUDPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte [Sl - 4 ] | 564/KTS | 31/08/2021 | 15 | BABUL SK | 2.42 | 2.42 | 100 | 1
119 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kalyanbati, Narayapur and Radhakrishnapur mouzas within the command area of Sudpur piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08717 | Retrofitting | Supplying and laying of valves along with construction of valve chamber at the existing distribution pipe line of Sudpur PWSS under Katwa Sub-Division under Burdwan Division, PHE Dte [Sl No-05] | 441/KTS | 27/06/2022 | 30 | MD HASIN | 0.86 | 0.85 | 100 | 1
120 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kalyanbati, Narayapur and Radhakrishnapur mouzas within the command area of Sudpur piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08717 | Retrofitting | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme SRIKHANDA, SUDPUR PWSS (Sl No-3) | 395/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 2.48 | 2.48 | 100 | 100
121 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kalyanbati, Narayapur and Radhakrishnapur mouzas within the command area of Sudpur piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08717 | Retrofitting | Supplying and laying inter-connection from Pump no.-3 to rising main of Sudpur PWSS under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No-5] | 672/KTS | 22/06/2023 | 30 | HAMID SK | 0.93 | 0.93 | 100 | 100
122 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10058 | Augmentation | Preparation of DPR for augmentation of Kusumgram W/S Scheme (Zone-I & II) within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | 204/KSD | 23/02/2022 | 21 | ROY CHOWDHURY ASSOCIATES | 3.93 | 3.91 | 100 | 1
123 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10058 | Augmentation | Material Requisition To Resource Division | 5521/BWD | 23/12/2022 | 0 | Resource Division | 32.81 | 0 | 0 | 0
124 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10058 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
125 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10058 | Augmentation | Supply , delivery & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 3 of Kulut [ Kusumgram ] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1172/CMD | 27/06/2022 | 30 | M/S. DAS ELECTRIC CO. | 9.33 | 8.93 | 100 | 1
126 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10058 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 1ST TW Site of Aug. of KUSUMGRAM (Z-II) & its adjoining mouzas Piped Water Supply Scheme, Block ? Monteswar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. _2ND CALL. | 371/BWD | 31/01/2023 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 7.33 | 6.84 | 100 | 1
127 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10058 | Augmentation | Installation of Electro-mechanical accessories at Kusungram zone-1 PH-2 (replacement T.W) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman | 4361/CMD | 21/09/2023 | 30 | BENGAL ELECTRICAL CONSTRUCTION | 1.97 | 1.97 | 100 | 100
128 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10058 | Augmentation | Material Requisition To Resource Division | 1547/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
129 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED KUSUMGRAM (ZONE I AND ZONE II) PWSS TO ACCOMMODATE FHTC IN MANTESWAR BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10058 | Augmentation | Augmentation of Kusumgram Zone-I & II Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 450 & 300 cum capacity OHR with 20.0 mtr. Staging height including construction of switch-room without sanitary & water supply arrangement, boundary wall including repairing of boundary wall under Monteswar Block, District:- Purba-Bardhaman. | 5079/BWD | 17/11/2022 | 866 | MANASH GHOSH | 778.07 | 693.66 | 89.15 | 66
130 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell site for Augmentation of BAROBELUN Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | 1961/BWD | 12/04/2022 | 45 | ACME CONSTRUCTION | 22.05 | 16.18 | 100 | 1
131 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Route Survey & Preparation of DPR for BARABELUN PWSS under Durgapur(Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-E] | 105/DSD | 18/02/2022 | 15 | RISHAN ENGINEERING CONSULTANCY | 2.72 | 2.72 | 100 | 1
132 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | New connection charges bill for Barabelun water supply scheme under Burdwan Division, PHE Dte.[Application No.-5003437581, Ref ID-503142125] | 596/DW/22-23 | 21/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.9 | 0 | 0 | 0
133 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
134 | PURBA BARDHAMAN | Central Mechanical | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation of Barabelun Water Supply Scheme [ Block- Bhatar ] at 1st Tube well Site( Tube well No.-3) at under CMD, PHE Dte., Dist.- Purba-Bardhaman | 2095/CMD | 08/09/2022 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 10.9 | 10.57 | 96.95 | 0
135 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Augmentation of BARABELUN Piped Water Supply Scheme with LDS, FHTC work, Rising Main, Switch Room (with water supply & sanitary arrangements), 400 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Boundary wall construction (HW, 2nd TW & 4th TW Site) with repairing of switch room cum chlorine room, Block - Bhatar, Dist. - Purba Bardhaman under Burdwan Division, PHE. Dte. | 571/BWD | 27/01/2022 | 365 | MD HASIN | 406.41 | 385.05 | 100 | 100
136 | PURBA BARDHAMAN | Central Mechanical | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation of Barabelun Water Supply Scheme [ Block- Bhatar ] at 2nd Tube well Site( Tube well No.-4) at under CMD, PHE Dte., Dist.- Purba-Bardhaman | 2094/CMD | 08/09/2022 | 30 | M/S. SWAPAN BANERJEE | 11.4 | 11.14 | 100 | 100
137 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Dignagar, Galsi, Barabelun & Kotachandipur Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. Dte. _2ND CALL | 3624/BWD | 22/08/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.76 | 3.69 | 100 | 1
138 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Material Requisition To Resource Division | 556/BWD | 27/01/2022 | 0 | Resource Division | 13.64 | 0 | 0 | 0
139 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Material Requisition To Resource Division | 770/BWD | 07/02/2022 | 0 | Resource Division | 26.55 | 0 | 0 | 0
140 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Material Requisition To Resource Division | 1560/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
141 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Material Requisition To Resource Division | 1381/BWD | 09/03/2022 | 0 | Resource Division | 4.35 | 0 | 0 | 0
142 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Material Requisition To Resource Division | 1328/BWD | 08/03/2022 | 0 | Resource Division | 39.89 | 0 | 0 | 0
143 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Material Requisition To Resource Division | 4854/BWD | 20/10/2022 | 0 | Resource Division | 6.16 | 0 | 0 | 0
144 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Quotation for new connection charges of Augmentation of Barbelun w/s scheme under Burdwan Division, PHE Dte. T.W. No.-4 [Memo No.-5003603611/Quot/03, dt.-10/02/2023][App No.-5003603611, Ref. ID-503282585] | 1115/JJM | 27/02/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.4 | 0 | 0 | 0
145 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Making connection with 4th tube well, Construction of Plinth protection of OHR, Restoration of road and FHTC (The rest portion) of Bara Belun Water Supply Scheme at Bara Belun village & Providing Functional Household Tap Connection (FHTC) within the command area of NASIGRAM Piped W/S. Scheme within Bhatar Block under Burdwan Division, PHE. Dte. | 3685/BWD | 23/10/2024 | 120 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 91.48 | 0 | 0 | 0
146 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Providing Functional Household Tap Connection (FHTC)from distribution system within the command area of Barobelun water supply scheme at Baneswarpur village under JJM under Bhatar Block in Purba Bardhanan District undrer Burdwan Division, P.H.E. Dte. | 130/DSD | 07/02/2024 | 45 | JAMALUDDIN SK | 3.02 | 1.57 | 100 | 100
147 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Providing Functional Household Tap Connection (FHTC)from distribution system within the command area of Barobelun water supply scheme at Khulla village under JJM under Bhatar Block in Purba Bardhanan District undrer Burdwan Division, P.H.E. Dte. | 131/DSD | 07/02/2024 | 45 | JAMALUDDIN SK | 1.81 | 1.26 | 100 | 100
148 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Land development and beautification with plant and Construction of connecting road from Gate to Pumphouse, OHR at 1st tubewell site of Barobelun Water Supply Scheme within Durgapur Sub Division Under Burdwan Division, PHE Dte. | 42/DSD | 17/01/2024 | 366 | MUNSHI JAVEDUR JAMAN | 4.82 | 4.81 | 100 | 72
149 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Beautification of PWSS with Arboriculture, Recharge Pit including shaft at Head Works site and anciliary works at 1st & 4th Tubewell site of BARABELUN (Bhatar Block) P.W.S.S under Burdwan Division, PHE Dte. | 238/RWS | 30/07/2024 | 10 | GHOSH ENTERPRISE | 0.97 | 0 | 0 | 100
150 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based piped water supply scheme for Barabelun to accommodated FHTC under Jal Sapno Mission under Bhatar Block. , SM/09700 | Augmentation | Laying of HDPE pipe line at Baneswarpur near Barabelun Bazar under Barabelun PWSS within ,Durgapur (Burdwan North) Sub-Division under Burdwan Division, PHE Dte. (2nd Call) | 383/DSD | 10/03/2025 | 30 | GHOSH ENTERPRISE | 0.8 | 0 | 0 | 100
151 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 42 (Forty Two) Nos. Anganwadi Center having Electric Power connection within the command area of Memari - II Block under Burdwan Division, P.H.E. Dte. (Part - A). | 4550/BWD | 06/09/2021 | 30 | SETH ENTERPRISE | 17.71 | 5.48 | 30.93 | 1
152 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 57 (Fifty Seven) Nos. Anganwadi Center having no Electric Power connection within the command area of Ausgram - II Block under Burdwan Division, P.H.E. Dte. (Part-B). | 281/BWD | 17/01/2022 | 30 | RELIABLE ENGINEERS CO.-OPERATIVE CONSTRUCTION SOCIETY LTD. | 23.46 | 16.25 | 69.3 | 1
153 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 50 (Fifty) Nos. Anganwadi Center having Electric Power connection within the command area of Katwa - I Block (22 Nos.) & Katwa - II Block (28 Nos.) under Burdwan Division, P.H.E. Dte. | 3344/BWD | 21/06/2021 | 30 | TAPAS KUMAR ROY | 23.88 | 13.32 | 100 | 1
154 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 50 (Fifty) Nos. Anganwadi Center having Electric Power connection within the command area of Memari - I Block under Burdwan Division, P.H.E. Dte. (Part - B). | 3299/BWD | 15/06/2021 | 30 | JAGADANANDAPUR CO. OP. LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 23.93 | 20.97 | 100 | 1
155 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 50 (Fifty) Nos. Anganwadi Center having Electric Power connection within the command area of Memari - I Block under Burdwan Division, P.H.E. Dte. (Part - A). | 3334/BWD | 18/06/2021 | 30 | BRINDABAN KONAR | 23.9 | 20.74 | 100 | 1
156 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 20 (Twenty) Nos. Anganwadi Center having Electric Power connection within the command area of Kalna - I Block (09 Nos.) & Kalna - II Block (11 Nos.) under Burdwan Division, P.H.E. Dte. | 4549/BWD | 06/09/2021 | 30 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 8.53 | 6.02 | 100 | 1
157 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 36 (Thirty Six) Nos. Anganwadi Center having Electric Power connection within the command area of Monteswar Block (17 Nos.) & Mongalkote Block (19 Nos.) under Burdwan Division, P.H.E. Dte. | 4552/BWD | 06/09/2021 | 30 | ASMA ENTERPRISE | 17.18 | 12.92 | 100 | 1
158 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 18 (Eighteen) Nos. Anganwadi Center having Electric Power connection within the command area of Khandaghosh Block under Burdwan Division, P.H.E. Dte. | 4546/BWD | 06/09/2021 | 30 | SHUBHRA KANTI GHOSH | 8.62 | 5.42 | 100 | 1
159 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 54 (Fifty Four) Nos. Anganwadi Center having Electric Power connection within the command area of Jamalpur Block under Burdwan Division, P.H.E. Dte. (Part-B). | 4544/BWD | 06/09/2021 | 30 | KOUSIK MALLICK | 25.88 | 19.21 | 100 | 1
160 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 20 (Twenty) Nos. Anganwadi Center having no Electric Power connection within the command area of Galsi - II Block under Burdwan Division, P.H.E. Dte. | 282/BWD | 17/01/2022 | 30 | J. K. CORPORATION | 8.11 | 7.94 | 100 | 1
161 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 30 (Thirty) Nos. Anganwadi Center having no Electric Power connection within the command area of Bhatar Block under Burdwan Division, P.H.E. Dte. | 212/BWD | 11/01/2022 | 30 | BAMDEB CONSTRUCTION & CO | 12.29 | 10.27 | 100 | 1
162 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 58 (Fifty Eight) Nos. Anganwadi Center having no Electric Power connection within the command area of Ausgram - II Block under Burdwan Division, P.H.E. Dte. (Part-A). | 106/BWD | 06/01/2022 | 30 | ANWESHA CONSTRUCTION | 23.05 | 21.89 | 100 | 1
163 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 69 (Sixty Nine) Nos. Anganwadi Center having no Electric Power connection within the command area of Ausgram - I Block under Burdwan Division, P.H.E. Dte. | 107/BWD | 06/01/2022 | 30 | DUBE ENTERPRISE | 27.96 | 26.2 | 100 | 1
164 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 54 (Fifty Four) Nos. Anganwadi Center having no Electric Power connection within the command area of Jamalpur Block under Burdwan Division, P.H.E. Dte. (Part-A). | 38/BWD | 05/01/2022 | 30 | HAFIJUR RAHAMAN MIDYA | 22.1 | 15.58 | 100 | 1
165 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 58 Nos Anganwari Centre having Electric Power connection within the command area of Memari-I Block under Burdwan Division, PHE Dte. [Part-C] | 3203/BWD | 09/06/2021 | 30 | G.S. CONSTRUCTION & CO. | 27.75 | 26.07 | 100 | 1
166 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 51 (Fifty One) Nos. Anganwadi Center having Electric Power connection within the command area of Galsi - I Block under Burdwan Division, P.H.E. Dte. | 4545./BWD | 06/09/2021 | 30 | SHUBHRA KANTI GHOSH | 24.42 | 15.45 | 100 | 1
167 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 53 (Fifty Three) Nos. Anganwadi Center having no Electric Power connection within the command area of Purbasthali - I Block (36 Nos.) & Purbasthali - II Block (17 Nos.) under Burdwan Division, P.H.E. Dte. | 754/BWD | 07/02/2022 | 30 | BIPLAB GUHA | 21.61 | 18.34 | 100 | 1
168 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 24 (Twenty Four) Nos. Anganwadi Center having Electric Power connection within the command area of Raina - I Block under Burdwan Division, P.H.E. Dte. | 4547/BWD | 06/09/2021 | 30 | BARDHAMAN AQUA ENGINEERING | 11.29 | 7.43 | 100 | 100
169 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 42 (Forty Two) Nos. Anganwadi Center having Electric Power connection within the command area of Memari - II Block under Burdwan Division, P.H.E. Dte. (Part - B). | 4548/BWD | 06/09/2021 | 30 | BARDHAMAN AQUA ENGINEERING | 19.71 | 11.7 | 100 | 100
170 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 55 (Fifty Five) Nos. Anganwadi Center having no Electric Power connection within the command area of Raina - II Block under Burdwan Division, P.H.E. Dte. | 69/BWD | 06/01/2022 | 30 | PREMANANDA ROY BISWAS | 22.28 | 18.61 | 100 | 1
171 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Providing necessary water supply arrangement at 14 (Fourteen) Nos. Anganwadi Center having no Electric Power connection within the command area of Burdwan - I Block (04 Nos.) & Burdwan - II Block (10 Nos.) under Burdwan Division, P.H.E. Dte._2ND CALL. | 2035/BWD | 19/04/2022 | 30 | GOUTAM KUMAR MITRA | 5.73 | 4.64 | 100 | 1
172 | PURBA BARDHAMAN | Burdwan Division | Extension of PWS to Anganwadi Centers (AWCs) located within the command area of PWSS under Burdwan Division. , SM/10016 | Anganwadi | Work order for " Providing of Balance FHTC at Different AWC(SM/10016) under Hatkalna GP under under Kalna-I Block under Kalna Sub-Division under Burdwan Division, PHE Dte." | 596/KSD | 30/04/2025 | 43 | SAYAK DEY | 1.72 | 0 | 0 | 100
173 | PURBA BARDHAMAN | Burdwan Division | SILUT PIPED WATER SUPPLY SCHEME , SM/13903 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 69.42 | 0 | 0 | 0
174 | PURBA BARDHAMAN | Burdwan Division | SILUT PIPED WATER SUPPLY SCHEME , SM/13903 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.36 | 0 | 0 | 0
175 | PURBA BARDHAMAN | Burdwan Division | SILUT PIPED WATER SUPPLY SCHEME , SM/13903 | New | Material Requisition To Resource Division | 4900/BWD | 10/11/2023 | 0 | Resource Division | 34.27 | 0 | 0 | 0
176 | PURBA BARDHAMAN | Central Mechanical | SILUT PIPED WATER SUPPLY SCHEME , SM/13903 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
177 | PURBA BARDHAMAN | Central Mechanical | SILUT PIPED WATER SUPPLY SCHEME , SM/13903 | New | Quotation for new service connection at Silut W/S Scheme for PH No-1 | BP-2023-24-327 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.07 | 0 | 0 | 0
178 | PURBA BARDHAMAN | Central Mechanical | SILUT PIPED WATER SUPPLY SCHEME , SM/13903 | New | Quotation for new service connection at Silut PWSS PH-2. | BP-2024-25-234 | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.65 | 0 | 0 | 0
179 | PURBA BARDHAMAN | Burdwan Division | SILUT PIPED WATER SUPPLY SCHEME , SM/13903 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways at different TW sites for SILUT Piped Water Supply Scheme under Ausgram-I Block, District:- Purba Bardhaman [NEW SCHEME] | 3323/BWD | 02/08/2023 | 730 | TAAS ENTERPRISE | 474.73 | 307.33 | 64.74 | 50
180 | PURBA BARDHAMAN | Central Mechanical | SILUT PIPED WATER SUPPLY SCHEME , SM/13903 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Silut Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4179/CMD | 29/08/2023 | 580 | SOUMEN ELECTRIC | 27.67 | 13.56 | 54.65 | 48
181 | PURBA BARDHAMAN | Burdwan Division | BIJRA PIPED WATER SUPPLY SCHEME , SM/13426 | New | Material Requisition To Resource Division | 3988/BWD | 08/09/2023 | 0 | Resource Division | 1.04 | 0 | 0 | 0
182 | PURBA BARDHAMAN | Burdwan Division | BIJRA PIPED WATER SUPPLY SCHEME , SM/13426 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.43 | 0 | 0 | 0
183 | PURBA BARDHAMAN | Burdwan Division | BIJRA PIPED WATER SUPPLY SCHEME , SM/13426 | New | Material Requisition To Resource Division | 5115/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
184 | PURBA BARDHAMAN | Burdwan Division | BIJRA PIPED WATER SUPPLY SCHEME , SM/13426 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte." [Period from 01.12.2023 to 31.01.2024] | 921/AE/HQ | 30/11/2023 | 62 | SOURAV JANA | 0.8 | 0.8 | 99.85 | 50
185 | PURBA BARDHAMAN | Central Mechanical | BIJRA PIPED WATER SUPPLY SCHEME , SM/13426 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
186 | PURBA BARDHAMAN | Central Mechanical | BIJRA PIPED WATER SUPPLY SCHEME , SM/13426 | New | New electric connection for Bijra PWSS, PH-2. | BP-2023-24-342 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.97 | 0 | 0 | 0
187 | PURBA BARDHAMAN | Central Mechanical | BIJRA PIPED WATER SUPPLY SCHEME , SM/13426 | New | Additional quotation for new service connection at Bijra PWSS | BP-2024-25-383 | 14/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.24 | 0 | 0 | 0
188 | PURBA BARDHAMAN | Central Mechanical | BIJRA PIPED WATER SUPPLY SCHEME , SM/13426 | New | Electric quotation for New Service Connection at Bijra W/S Scehem PH-I. | BP-2023-24-282 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.34 | 0 | 0 | 0
189 | PURBA BARDHAMAN | Central Mechanical | BIJRA PIPED WATER SUPPLY SCHEME , SM/13426 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BIJRA Water Supply Scheme [ Block- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4091/CMD | 29/08/2023 | 491 | ORIENTAL ENGINEERING CO. | 29.39 | 0 | 0 | 100
190 | PURBA BARDHAMAN | Burdwan Division | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/13947 | New | Material Requisition To Resource Division | 3992/BWD | 08/09/2023 | 0 | Resource Division | 12.78 | 0 | 0 | 0
191 | PURBA BARDHAMAN | Burdwan Division | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/13947 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 15.58 | 0 | 0 | 0
192 | PURBA BARDHAMAN | Burdwan Division | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/13947 | New | Material Requisition To Resource Division | 5089/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
193 | PURBA BARDHAMAN | Burdwan Division | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/13947 | New | Continuation Work Order supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2023 to 31-01-2024) | 2561/BSD | 30/10/2023 | 66 | MD HASIN | 0.85 | 0 | 0 | 0
194 | PURBA BARDHAMAN | Central Mechanical | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/13947 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System, Internal House Wiring and Compound lighting arrangement for Tube well No.- 1 & 2 at GHOSHPUR Water Supply Scheme [BLOCK- MEMARI- 2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1533/CMD | 05/03/2024 | 60 | CHOUDHURY ENTERPRISE | 28.82 | 22.94 | 79.6 | 75
195 | PURBA BARDHAMAN | Central Mechanical | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/13947 | New | New service connection at Ghoshpur PWSS TW -1 | BP-2023-24-446 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.28 | 0 | 0 | 0
196 | PURBA BARDHAMAN | Central Mechanical | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/13947 | New | NEW SERVICE CONNECTION FOR GHOSHPUR PWSS. | BP-2023-24-566 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.97 | 0 | 0 | 0
197 | PURBA BARDHAMAN | Burdwan Division | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/13947 | New | GHOSHPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 2299/BWD | 19/05/2023 | 958 | MLG CONSTRUCTION | 441.87 | 126.76 | 28.69 | 52
198 | PURBA BARDHAMAN | Burdwan Division | GHOSHPUR PIPED WATER SUPPLY SCHEME , SM/13947 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2024 to 31-01-2025) | 2438/BSD | 29/10/2024 | 66 | PARVIN BEGAM | 0.85 | 0.28 | 100 | 100
199 | PURBA BARDHAMAN | Burdwan Division | BHOTA PIPED WATER SUPPLY SCHEME , SM/13293 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 3.99 | 0 | 0 | 0
200 | PURBA BARDHAMAN | Burdwan Division | BHOTA PIPED WATER SUPPLY SCHEME , SM/13293 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 18.44 | 0 | 0 | 0
201 | PURBA BARDHAMAN | Burdwan Division | BHOTA PIPED WATER SUPPLY SCHEME , SM/13293 | New | Material Requisition To Resource Division | 4019/BWD | 08/09/2023 | 0 | Resource Division | 4.01 | 0 | 0 | 0
202 | PURBA BARDHAMAN | Burdwan Division | BHOTA PIPED WATER SUPPLY SCHEME , SM/13293 | New | Material Requisition To Resource Division | 5108/BWD | 23/11/2023 | 0 | Resource Division | 20.18 | 0 | 0 | 0
203 | PURBA BARDHAMAN | Central Mechanical | BHOTA PIPED WATER SUPPLY SCHEME , SM/13293 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
204 | PURBA BARDHAMAN | Durgapur W/S Division | BHOTA PIPED WATER SUPPLY SCHEME , SM/13293 | New | Material Requisition To Resource Division | 1724/C/DWSD | 10/12/2024 | 0 | Resource Division | 3.52 | 0 | 0 | 0
205 | PURBA BARDHAMAN | Central Mechanical | BHOTA PIPED WATER SUPPLY SCHEME , SM/13293 | New | Quotation for new service connection at Bhota W/S Scheme for PH No-2 | BP-2023-24-326 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.81 | 0 | 0 | 0
206 | PURBA BARDHAMAN | Central Mechanical | BHOTA PIPED WATER SUPPLY SCHEME , SM/13293 | New | Quotation for new service connection at Bhota W/S Scheme for PH No-1 | BP-2023-24-325 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.77 | 0 | 0 | 0
207 | PURBA BARDHAMAN | Burdwan Division | BHOTA PIPED WATER SUPPLY SCHEME , SM/13293 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AUSGRAM & BHOTA Piped Water Supply Scheme under Ausgram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3324/BWD | 02/08/2023 | 776 | DUTTA ENTERPRISE | 763.14 | 96.65 | 42.55 | 70
208 | PURBA BARDHAMAN | Central Mechanical | BHOTA PIPED WATER SUPPLY SCHEME , SM/13293 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bhota Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4051/CMD | 29/08/2023 | 615 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 29.56 | 11.77 | 47.84 | 48
209 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 3.1 | 0 | 0 | 0
210 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | Material Requisition To Resource Division | 4947/BWD | 10/11/2023 | 0 | Resource Division | 35.92 | 0 | 0 | 0
211 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | Material Requisition To Resource Division | 4309/BWD | 29/09/2023 | 0 | Resource Division | 11.47 | 0 | 0 | 0
212 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/08/2024 to 30/09/2024) | 602/DSD | 30/07/2024 | 61 | SUJAUDDIN SEKH | 0.8 | 0.31 | 76.26 | 100
213 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/10/2024 to 30/11/2024) | 772/DSD | 18/09/2024 | 61 | SUJAUDDIN SEKH | 0.8 | 0.28 | 69.75 | 0
214 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | NEW SERVICE CONNECTION FOR BELENDA PWSS TW -2. | BP-2023-24-639 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.64 | 0 | 0 | 0
215 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | Quotation for new service connection for Belenda PWSS PH 1. | BP-2024-25-119 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.29 | 0 | 0 | 0
216 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BELENDA, JAMNA, PIPLON & PARGUNA Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | 4388/BWD | 05/10/2023 | 667 | AKASH CONSTRUCTION | 2296.4 | 228.25 | 50.49 | 50
217 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
218 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/12/2024 to 31/12/2024) | 992/DSD | 25/11/2024 | 61 | SUJAUDDIN SEKH | 0.4 | 0.17 | 86.45 | 0
219 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | CONTINUATION ORDER- Hiring of inspection vehicle (Diesel/CNG/LPG Driven)for supervision of site for the office of the Assisatnt Engineer,under CMD,PHE,Dte.[W.E.F-01.04.2025 to 31.05.2025] | 367/CMSD | 26/03/2025 | 61 | PRODYUT GHOSH | 0.8 | 0.8 | 100.08 | 0
220 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | Continuation for Supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/04/2025 to 31/05/2025) | 483/DSD | 21/03/2025 | 61 | SK ALACK JANDER | 0.8 | 0.29 | 71.78 | 0
221 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | Supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/02/2025 to 31/03/2025) | 142/DSD | 24/01/2025 | 59 | SK ALACK JANDER | 0.8 | 0.31 | 77.05 | 0
222 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | Work Order for "DESIGNING,MAKING AND ERECTION OF SIGN BOARD FOR SAJAL GRAM IN ¿¿1 No...VILLAGE, ¿MANTESWAR BLOCK UNDER KALNA SUB DIVISION WITHIN BURDWAN DIVISION PHE DTE. (3nos board)" | 1920/KSD | 02/12/2024 | 10 | OMKAR ENTERPRISE | 0.42 | 0 | 0 | 100
223 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR BELENDA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/13340 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Belenda Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4175/CMD | 29/08/2023 | 703 | SOUNAK ENTERPRISE | 28.48 | 0 | 0 | 95
224 | PURBA BARDHAMAN | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte , SM/14425 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khule Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4186/CMD | 29/08/2023 | 30 | CINZANO | 29.1 | 0 | 0 | 0
225 | PURBA BARDHAMAN | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte , SM/14425 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 56.68 | 0 | 0 | 0
226 | PURBA BARDHAMAN | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte , SM/14425 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 18.09 | 0 | 0 | 0
227 | PURBA BARDHAMAN | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte , SM/14425 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR ANUKHAL PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 1236/KSD | 30/09/2024 | 15 | SINGHA ROY AND CO. | 0.66 | 0 | 0 | 0
228 | PURBA BARDHAMAN | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte , SM/14425 | New | Work order for " CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR DOGACHHIA PWSS UNDER KALNA SUBDIVISION UNDER BURDWAN DIVISION, PHE DTE." | 1237/KSD | 30/09/2024 | 15 | MITRA CONSTRUCTION | 0.66 | 0 | 0 | 0
229 | PURBA BARDHAMAN | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte , SM/14425 | New | NEW SERVICE CONNECTION FOR KHULE PWSS. | BP-2023-24-569 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.69 | 0 | 0 | 0
230 | PURBA BARDHAMAN | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte , SM/14425 | New | NEW SERVICE CONNECTION FOR KHULE PWSS. | BP-2023-24-570 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.79 | 0 | 0 | 0
231 | PURBA BARDHAMAN | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte , SM/14425 | New | KHULE Piped Water Supply Scheme with sinking of Tube-well, LDS,Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1618/BWD | 05/04/2023 | 1093 | AZAD ENTERPRISE | 598.72 | 386.02 | 64.47 | 55
232 | PURBA BARDHAMAN | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte , SM/14425 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
233 | PURBA BARDHAMAN | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte , SM/14425 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
234 | PURBA BARDHAMAN | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For KHULE PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte , SM/14425 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR KHULE PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE.". | 1232/KSD | 27/09/2024 | 15 | WESTON ENGINEERS | 0.66 | 0 | 0 | 100
235 | PURBA BARDHAMAN | Central Mechanical | KALAIJHUTI PIPED WATER SUPPLY SCHEME , SM/14954 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KALAIJHUTI Water Supply Scheme [ Block- AUSGRAM-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2509/CMD | 02/06/2023 | 30 | SOUNAK ENTERPRISE | 27.79 | 10.38 | 37.34 | 30
236 | PURBA BARDHAMAN | Burdwan Division | KALAIJHUTI PIPED WATER SUPPLY SCHEME , SM/14954 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.78 | 0 | 0 | 0
237 | PURBA BARDHAMAN | Burdwan Division | KALAIJHUTI PIPED WATER SUPPLY SCHEME , SM/14954 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 16.15 | 0 | 0 | 0
238 | PURBA BARDHAMAN | Burdwan Division | KALAIJHUTI PIPED WATER SUPPLY SCHEME , SM/14954 | New | Material Requisition To Resource Division | 4876/BWD | 10/11/2023 | 0 | Resource Division | 30.36 | 0 | 0 | 0
239 | PURBA BARDHAMAN | Central Mechanical | KALAIJHUTI PIPED WATER SUPPLY SCHEME , SM/14954 | New | New service connection charges for Kalaijhuti PWSS TW-1 | BP-2023-24-60 | 17/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.51 | 0 | 0 | 0
240 | PURBA BARDHAMAN | Burdwan Division | KALAIJHUTI PIPED WATER SUPPLY SCHEME , SM/14954 | New | KALAIJHUTI [Kalaijhuti Village (Node Point 1 to 84)] Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under AUSGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1565/BWD | 30/03/2023 | 90 | PABITRA KUMAR SAMANTA | 93 | 95.61 | 100 | 100
241 | PURBA BARDHAMAN | Durgapur W/S Division | KALAIJHUTI PIPED WATER SUPPLY SCHEME , SM/14954 | New | Acceptance cum Formal Work Order for Additional work for laying of Extension or Laying of parallel pipeline,providing FHTC,Road Restoration work, Land development under Kalaijhuti PWSS in Ausgram -II Block under Durgapur Water Supply Division, PHE Dte. | 1622/DWSD | 26/11/2024 | 95 | ROY CONSTRUCTION | 27.08 | 0 | 0 | 40
242 | PURBA BARDHAMAN | Burdwan Division | KONRAPUR PIPED WATER SUPPLY SCHEME , SM/13419 | New | Material Requisition To Resource Division | 3995/BWD | 08/09/2023 | 0 | Resource Division | 11.87 | 0 | 0 | 0
243 | PURBA BARDHAMAN | Burdwan Division | KONRAPUR PIPED WATER SUPPLY SCHEME , SM/13419 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 8.28 | 0 | 0 | 0
244 | PURBA BARDHAMAN | Burdwan Division | KONRAPUR PIPED WATER SUPPLY SCHEME , SM/13419 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KONRAPUR & MASGARIA Piped Water Supply Scheme under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 1765/BWD | 17/04/2023 | 365 | M/S ASHA CONSTRUCTION | 710.72 | 123.45 | 30.45 | 43
245 | PURBA BARDHAMAN | Central Mechanical | KONRAPUR PIPED WATER SUPPLY SCHEME , SM/13419 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at KONRAPUR Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4198/CMD | 29/08/2023 | 30 | MITRA ASSOCIATES | 21.47 | 9.64 | 44.88 | 50
246 | PURBA BARDHAMAN | Burdwan Division | KONRAPUR PIPED WATER SUPPLY SCHEME , SM/13419 | New | Material Requisition To Resource Division | 309/BWD | 24/01/2024 | 0 | Resource Division | 16.1 | 0 | 0 | 0
247 | PURBA BARDHAMAN | Central Mechanical | KONRAPUR PIPED WATER SUPPLY SCHEME , SM/13419 | New | NEW SERVICE CONNECTION FOR KONRAPUR PWSS | BP-2023-24-567 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.54 | 0 | 0 | 0
248 | PURBA BARDHAMAN | Central Mechanical | KONRAPUR PIPED WATER SUPPLY SCHEME , SM/13419 | New | NEW SERVICE CONNECTION FOR KONRAPUR PWSS. | BP-2023-24-568 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.76 | 0 | 0 | 0
249 | PURBA BARDHAMAN | Central Mechanical | KONRAPUR PIPED WATER SUPPLY SCHEME , SM/13419 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 30
250 | PURBA BARDHAMAN | Burdwan Division | KONRAPUR PIPED WATER SUPPLY SCHEME , SM/13419 | New | Different types of balance works involve in connection with KONRAPUR (SM/13419) & MASGORIA (SM/13318) Piped water supply scheme under Purbasthali-I Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | 142/BWD | 08/01/2025 | 120 | M/S ASHA CONSTRUCTION | 65.74 | 0 | 0 | 0
251 | PURBA BARDHAMAN | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13942 | New | Material Requisition To Resource Division | 1965/BWD | 26/04/2023 | 0 | Resource Division | 5.64 | 0 | 0 | 0
252 | PURBA BARDHAMAN | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13942 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 14.43 | 0 | 0 | 0
253 | PURBA BARDHAMAN | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13942 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 19.29 | 0 | 0 | 0
254 | PURBA BARDHAMAN | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13942 | New | Material Requisition To Resource Division | 5266/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
255 | PURBA BARDHAMAN | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13942 | New | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | 995/DSD | 29/12/2023 | 183 | SUJAUDDIN SEKH | 2 | 0.4 | 100 | 60
256 | PURBA BARDHAMAN | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13942 | New | NEW SERVICE CONNECTION FOR KAMALPUR PWSS PH-2. | BP-2023-24-602 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.8 | 0 | 0 | 0
257 | PURBA BARDHAMAN | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13942 | New | NEW SERVICE CONNECTION FOR KAMALPUR PWSS PH-1. | BP-2023-24-601 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.95 | 0 | 0 | 0
258 | PURBA BARDHAMAN | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13942 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SARANGA & KAMALPUR Piped Water Supply Scheme under Khandaghosh Block, District:- Purba Bardhaman [NEW SCHEME] | 2078/BWD | 04/05/2023 | 698 | KHAN ENTERPRISE | 820.73 | 381.84 | 75.85 | 42
259 | PURBA BARDHAMAN | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13942 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
260 | PURBA BARDHAMAN | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13942 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
261 | PURBA BARDHAMAN | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13942 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kamalpur Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4043/CMD | 29/08/2023 | 30 | M/S. SWAPAN BANERJEE | 28.97 | 22.93 | 95.24 | 100
262 | PURBA BARDHAMAN | Burdwan Division | Katnabil Piped Water Supply Scheme , SM/13338 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.23 | 0 | 0 | 0
263 | PURBA BARDHAMAN | Burdwan Division | Katnabil Piped Water Supply Scheme , SM/13338 | New | Material Requisition To Resource Division | 4036/BWD | 08/09/2023 | 0 | Resource Division | 4.83 | 0 | 0 | 0
264 | PURBA BARDHAMAN | Burdwan Division | Katnabil Piped Water Supply Scheme , SM/13338 | New | Material Requisition To Resource Division | 5050/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
265 | PURBA BARDHAMAN | Central Mechanical | Katnabil Piped Water Supply Scheme , SM/13338 | New | New service connection charges for Katnabil PWSS TW-1 | BP-2023-24-231 | 20/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.27 | 0 | 0 | 0
266 | PURBA BARDHAMAN | Central Mechanical | Katnabil Piped Water Supply Scheme , SM/13338 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
267 | PURBA BARDHAMAN | Central Mechanical | Katnabil Piped Water Supply Scheme , SM/13338 | New | New Service connection for Katnabil W/S Scheme PH No.-II | BP-2023-24-300 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.15 | 0 | 0 | 0
268 | PURBA BARDHAMAN | Central Mechanical | Katnabil Piped Water Supply Scheme , SM/13338 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Katnabil Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4038/CMD | 29/08/2023 | 581 | AHALYA ENGINEERING WORKS | 28.95 | 23.1 | 95.52 | 96
269 | PURBA BARDHAMAN | Burdwan Division | Katnabil Piped Water Supply Scheme , SM/13338 | New | Supply of various D.I. Mechanical joints & specials for KATNABIL & BANTIR Piped W/S. Scheme within Burdwan Sub-Division under Burdwan Division, PHE. Dte. [Part-B]. | 2825/BWD | 19/07/2024 | 216 | KEJRIWAL CASTINGS LIMITED | 4.82 | 0 | 0 | 100
270 | PURBA BARDHAMAN | Burdwan Division | Katnabil Piped Water Supply Scheme , SM/13338 | New | Supply of various D.I. Mechanical joints & specials for KATNABIL & BANTIR Piped W/S. Scheme within Burdwan Sub-Division under Burdwan Division, PHE. Dte. [Part-A]. | 2837/BWD | 19/07/2024 | 215 | ELECTROSTEEL CASTING LIMITED | 4.95 | 0 | 0 | 100
271 | PURBA BARDHAMAN | Burdwan Division | Katnabil Piped Water Supply Scheme , SM/13338 | New | Supply of various D.I. Mechanical joints & specials for KATNABIL & BANTIR Piped W/S. Scheme within Burdwan Sub-Division under Burdwan Division, PHE. Dte. [Part-C]. | 2829/BWD | 19/07/2024 | 225 | JINDAL SAW LTD. | 4.63 | 0 | 0 | 100
272 | PURBA BARDHAMAN | Burdwan Division | RAJUR PIPED WATER SUPPLY SCHEME , SM/15238 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 16.04 | 0 | 0 | 0
273 | PURBA BARDHAMAN | Burdwan Division | RAJUR PIPED WATER SUPPLY SCHEME , SM/15238 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 10.9 | 0 | 0 | 0
274 | PURBA BARDHAMAN | Burdwan Division | RAJUR PIPED WATER SUPPLY SCHEME , SM/15238 | New | Material Requisition To Resource Division | 4013/BWD | 08/09/2023 | 0 | Resource Division | 15.19 | 0 | 0 | 0
275 | PURBA BARDHAMAN | Burdwan Division | RAJUR PIPED WATER SUPPLY SCHEME , SM/15238 | New | Material Requisition To Resource Division | 4881/BWD | 10/11/2023 | 0 | Resource Division | 29.6 | 0 | 0 | 0
276 | PURBA BARDHAMAN | Central Mechanical | RAJUR PIPED WATER SUPPLY SCHEME , SM/15238 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
277 | PURBA BARDHAMAN | Central Mechanical | RAJUR PIPED WATER SUPPLY SCHEME , SM/15238 | New | Quotation for new service connection at RAJUR W/S Scheme PH-II. | BP-2023-24-317 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.22 | 0 | 0 | 0
278 | PURBA BARDHAMAN | Central Mechanical | RAJUR PIPED WATER SUPPLY SCHEME , SM/15238 | New | New service connection charges for Rajur PWSS TW-1 | BP-2023-24-278 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.15 | 0 | 0 | 0
279 | PURBA BARDHAMAN | Burdwan Division | RAJUR PIPED WATER SUPPLY SCHEME , SM/15238 | New | RAJUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 1701/BWD | 12/04/2023 | 365 | TEKNO ENTERPRISE | 471.14 | 430.57 | 91.39 | 77
280 | PURBA BARDHAMAN | Central Mechanical | RAJUR PIPED WATER SUPPLY SCHEME , SM/15238 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at RAJUR Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4102/CMD | 29/08/2023 | 30 | S DUTTA | 28.98 | 22.78 | 95.21 | 90
281 | PURBA BARDHAMAN | Burdwan Division | RAJUR PIPED WATER SUPPLY SCHEME , SM/15238 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Chakta, Mahula, Rajoor and Srigram PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2721/BWD | 11/07/2024 | 447 | ESCON INDIA | 139.35 | 23.75 | 66.63 | 70
282 | PURBA BARDHAMAN | Burdwan Division | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. , SM/15581 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 10.04 | 0 | 0 | 0
283 | PURBA BARDHAMAN | Burdwan Division | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. , SM/15581 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 10.94 | 0 | 0 | 0
284 | PURBA BARDHAMAN | Central Mechanical | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. , SM/15581 | New | New service connection charges for Bara Baharkuli PWSS TW-2 | BP-2023-24-219 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.15 | 0 | 0 | 0
285 | PURBA BARDHAMAN | Burdwan Division | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. , SM/15581 | New | BARA BAHARKULI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 2597/BWD | 02/06/2023 | 365 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 236.3 | 145.52 | 61.58 | 65
286 | PURBA BARDHAMAN | Burdwan Division | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. , SM/15581 | New | Material Requisition To Resource Division | 328/BWD | 24/01/2024 | 0 | Resource Division | 24.62 | 0 | 0 | 0
287 | PURBA BARDHAMAN | Central Mechanical | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. , SM/15581 | New | Quotation for new electric service connection at Bara Baharkhuli PH NO.-1 | BP-2023-24-268 | 11/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.87 | 0 | 0 | 0
288 | PURBA BARDHAMAN | Burdwan Division | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. , SM/15581 | New | Restoration work of Barabaharkuli to Badla village road with a bridge over river Behula road from 0.0 km to 1.3 km and 1.8 km to 2.2 km damadged due to laying of underground water pipeline by PHE with box cutting and jhama with moorum consolidation under kalna highway subdivision of Burdwan south highway division ,P.W(Roads)dte ,during the year 2023-2024 | 825/JJM | 13/09/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 5.36 | 0 | 0 | 0
289 | PURBA BARDHAMAN | Burdwan Division | BARA BAHARKULI PIPED WATER SUPPLY SCHEME. , SM/15581 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
290 | PURBA BARDHAMAN | Burdwan Division | CHAKDAHA PIPED WATER SUPPLY SCHEME , SM/15582 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 4.39 | 0 | 0 | 0
291 | PURBA BARDHAMAN | Burdwan Division | CHAKDAHA PIPED WATER SUPPLY SCHEME , SM/15582 | New | Material Requisition To Resource Division | 3843/BWD | 01/09/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
292 | PURBA BARDHAMAN | Burdwan Division | CHAKDAHA PIPED WATER SUPPLY SCHEME , SM/15582 | New | Material Requisition To Resource Division | 4895/BWD | 10/11/2023 | 0 | Resource Division | 4.76 | 0 | 0 | 0
293 | PURBA BARDHAMAN | Central Mechanical | CHAKDAHA PIPED WATER SUPPLY SCHEME , SM/15582 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
294 | PURBA BARDHAMAN | Central Mechanical | CHAKDAHA PIPED WATER SUPPLY SCHEME , SM/15582 | New | New service connection charges for Chakdaha PWSS TW-1 | BP-2023-24-279 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.1 | 0 | 0 | 0
295 | PURBA BARDHAMAN | Central Mechanical | CHAKDAHA PIPED WATER SUPPLY SCHEME , SM/15582 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at CHAKDAHA [KETUGRAM-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4153/CMD | 29/08/2023 | 640 | AMUSAR IMPEX PVT. LTD. | 21.26 | 9.69 | 45.57 | 47
296 | PURBA BARDHAMAN | Burdwan Division | CHAKDAHA PIPED WATER SUPPLY SCHEME , SM/15582 | New | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2741/BWD | 12/07/2024 | 538 | M/S M.M. ENTERPRISE | 205.15 | 6.98 | 48.02 | 65
297 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Hatgobindapur village of Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿6A¿] (T.R. No. 156/BWD/2020-21) | 2743/BWD | 10/08/2020 | 30 | M/S ASHA CONSTRUCTION | 4.92 | 9.84 | 200 | 1
298 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Hatgobindapur village of Hatgobindapur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-317/BWD/2020-21) | 3702/BWD | 05/10/2020 | 30 | M/S ASHA CONSTRUCTION | 4.92 | 9.84 | 200 | 1
299 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Banagram village of Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿6B¿] (T.R. No.-155/BWD/2020-21) | 2744/BWD | 10/08/2020 | 30 | M/S ASHA CONSTRUCTION | 4.92 | 4.92 | 100 | 1
300 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Hatgobindapur village (Part) of Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 01] | 4390/BWD | 31/08/2021 | 15 | M/S ASHA CONSTRUCTION | 4.86 | 4.77 | 100 | 1
301 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Extension of UPVC distribution pipeline in connection with FHTC for Hatgobindapur and its adjoining mouzas water supply scheme at Bardhaman-II Development Block under Burdwan Division, PHE Dte.[Gr-A] | 989/BSD | 30/07/2021 | 30 | M/S ASHA CONSTRUCTION | 4.82 | 4.74 | 100 | 1
302 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Construction of boundary wall at Pump house no - 3 Site of Hatgobindapur Water Supply Scheme under Bardhaman-II Dev. Block of Burdwan Division, PHE Dte. (Length -40.00 Mtr, Col-16 Nos). Group : B | 701/BSD | 27/04/2022 | 45 | ANIRUDDHA FARUQUE | 2.61 | 2.61 | 100 | 1
303 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Laying of interconnection of the Pump No.-3 with distribution line 100 mm dia for Hatgobindapur piped water supply scheme of Burdwan-II Block under Burdwan Division, PHE Dte.[Gr.-B] | 1027/BSD | 05/08/2021 | 30 | ANWESHA CONSTRUCTION | 1.67 | 1.5 | 100 | 1
304 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Sinking of additional Tube well 250 x 200 mm dia Tube well 150 mtr depth by D.R. Rig method using UPVC pipe (CD) and fibre glass strainer for Hatgobindapur piped water supply scheme (3rd tube well site), Block-Burdwan-II under Burdwan Division, PHE Dte. | 1493/BWD | 18/02/2021 | 30 | C.M. ENTERPRISE | 8.68 | 6.99 | 100 | 1
305 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 900/DW | 03/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 34.54 | 0 | 0 | 0
306 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage in Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ II Block under Burdwan Division, PHE. Dte. | 385/BWD | 20/01/2022 | 30 | BISWAS ENTERPRISE | 11.97 | 3.71 | 100 | 100
307 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Additional work for Construction of boundary wall at Pump house no - 3 Site of Hatgobindapur Water Supply Scheme under Bardhaman-II Dev. Block of Burdwan Division, PHE Dte. (Length -18.00 Mtr, Col-2 Nos). Group - A. | 722/BSD | 02/05/2022 | 30 | MOHAMMAD ISSA | 1.48 | 1.48 | 100 | 1
308 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of HATGOBINDAPUR Piped Water Supply Scheme and its adjoining mouzas at Burdwan - II Block under Burdwan Division, PHE. Dte. | 2232/BWD | 29/04/2022 | 30 | M/S ASHA CONSTRUCTION | 19.32 | 18.67 | 100 | 1
309 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Left out FHTC (Hatgobindapur, Banagram, Ramnagar & Hatkanda village) of HATGOBINDAPUR PWSS under Burdwan-II Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 2302/BWD | 19/05/2023 | 30 | M/S SAYAN CHAKRABORTY | 9.6 | 9.63 | 100 | 100
310 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Material Requisition To Resource Division | 6800/BWD | 07/12/2021 | 0 | Resource Division | 2.85 | 0 | 0 | 0
311 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Providing left out FHTC for 100% covarage in different village within Hatgobindapur PWSS , Bardhhaman-II Development Block under Burdwan Division, PHE Dte | 1275/BSD | 12/07/2024 | 45 | PAL CONSTRUCTION | 4.78 | 0 | 0 | 0
312 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Hatgobindapur village (Part) of Hatgobindapur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 01] | 1413/BWD | 18/02/2021 | 15 | M/S ASHA CONSTRUCTION | 4.86 | 9.71 | 200 | 0
313 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 3rd tube well site (Size-3.60 mtr x 3.00 mtr) for HATGOBINDAPUR water supply scheme under Burdwan-II development Block under Burdwan Sub-Division, under Burdwan Division, PHE Dte.[Gr.-A] | 665/BSD | 07/06/2021 | 45 | KAJAL MUKHERJEE | 2.76 | 2.71 | 100 | 0
314 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hatgobindapur Piped Water Supply Scheme , SM/06971 | Retrofitting | Providing LDS in place of AC pipe line for HATGOBINDAPUR PWSS under Bardhaman-II Block within Burdwan Div. PHE Dte. | 874/BWD | 06/03/2025 | 177 | DEY NIRMAN | 35.37 | 0 | 0 | 100
315 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme , SM/07549 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ITLA Piped Water Supply Scheme at Itla (Itla Adibasipara Habitation) & Sudipur (Sudipur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 583/BWD OF 2020-2021.) | 545/BWD | 22/01/2021 | 60 | ANWESHA CONSTRUCTION | 17.35 | 0 | 0 | 1
316 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme , SM/07549 | Retrofitting | Interconnection between inlet & delivery pipe with main distribution pipeline within command area of ITLA Piped W/S. Scheme, Jamalpur Block under Burdwan Division, PHE. Dte. | 213/AE/HQ | 31/03/2023 | 30 | BHARAT CONSTRUCTION | 0.87 | 0 | 0 | 0
317 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme , SM/07549 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ITLA Piped Water Supply Scheme at Bahadurpur (Bahadurpur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. | 617/BWD | 25/01/2021 | 60 | A R TRADERS | 19.81 | 0 | 0 | 1
318 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme , SM/07549 | Retrofitting | Laying of uPVC pipe for providing FHTC at Itla Village within Itla Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte. [Group : E] | 66/AE/HQ | 11/02/2022 | 30 | MAUVE ENGINEERING AND SERVICES PVT LTD | 4.73 | 4.73 | 100 | 100
319 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme , SM/07549 | Retrofitting | Repairing and restoration of damaged and chokaged various dia UPVC pipeline and Construction of Valve chambers to control flow of water for providing FHTC in ITLA Piped W/S. Scheme at Jamalpur Dev Block under Burdwan Division ,P.H.E Dte._Gr-I | 147/AE/HQ | 16/03/2022 | 20 | BHARAT CONSTRUCTION | 4.55 | 4.33 | 100 | 1
320 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme , SM/07549 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ITLA Piped Water Supply Scheme at Itla (Itla Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 593/BWD OF 2020-2021] | 618/BWD | 25/01/2021 | 60 | JAYANTA CHAKRABORTY | 18.36 | 11.65 | 100 | 1
321 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme , SM/07549 | Retrofitting | Re-Laying of UPVC Pipeline (damaged by Local Irrigation Work) for providing FHTC at Bag Kalapahar Mouza (Habitation) under ITLA Piped Water Supply Scheme, Jamalpur Development Block under Burdwan Division, PHE Dte. | 5513/BWD | 14/12/2023 | 30 | UTPAL NANDI | 8.61 | 8.33 | 100 | 100
322 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme , SM/07549 | Retrofitting | Interconnection between OHR & Delivery line at Head Works site under ITLA PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 747/AE/HQ | 13/09/2024 | 30 | DEBJYOTI GOSWAMI | 0.8 | 0 | 0 | 100
323 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Itla Piped Water Supply Scheme , SM/07549 | Retrofitting | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 0 | 40
324 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN , SM/15309 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at Head Works & 2nd Tube well Site for BORSHUL (Zone-I) Piped Water Supply Scheme, Block - Burdwan - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. | 2691/BWD | 08/06/2023 | 45 | J K CORPORATION | 19.84 | 18.99 | 100 | 100
325 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN , SM/15309 | Augmentation | New service connection charges for Borshul PWSS Z-I TW-2 | BP-2023-24-142 | 28/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.63 | 0 | 0 | 0
326 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN , SM/15309 | Augmentation | New service connection charges for Borshul PWSS Z-I TW-1 | BP-2023-24-141 | 28/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0 | 0
327 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN , SM/15309 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 2nd Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17 (Size3.60mtrx3.00mtr room) for Barsul Zone-1 its Adjoining Mouza W/S Scheme, Block -Burdwan-II within Burdwan Sub-Division, PHE Dte. | 2040/BSD | 24/08/2023 | 45 | DEBJYOTI GOSWAMI | 3.19 | 2.61 | 100 | 100
328 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN , SM/15309 | Augmentation | Allied work for construction of pump house including plinth protection with surface drain at head work TW site for Borshul Z-I PWSS under Bardhaman-II block within Burdwan Div.PHE Dte. | 1470/BSD | 23/06/2025 | 60 | DAWN ASSOCIATES | 2.57 | 0 | 0 | 0
329 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN , SM/15309 | Augmentation | Augmentation of Borshul (Zone-I) Piped Water Supply Scheme (Mouzas:- Barshul, Tatkhanda & Dakshin Goplapur) with LDS, FHTC, Rising main, Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under BARDHAMAN- II Block, District:- Purba-Burdwan. | 616/BWD | 17/02/2023 | 683 | ASHOK KUMAR GHOSH | 331.77 | 251.14 | 75.7 | 51
330 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN , SM/15309 | Augmentation | Construction of pump house including plinth protection with surface drain at Head Work TW site for (3.6 mtr. x 3.0 mtr. Size) Borshul Zone-I water supply schemes, Block-Burdwan-II within Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | 006/BWD | 02/01/2024 | 364 | DAWN ASSOCIATES | 4.53 | 0 | 0 | 100
331 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN , SM/15309 | Augmentation | Construction of boundary wall at 1ST TUBE WALL (HEAD WORK) Site of BARSUL Zone-I Piped W/S. Scheme under Burdwan-II Block of Burdwan Division, PHE Dte. Length =100.00 Mtr, Col-35 Nos). | 2692/BWD | 10/07/2024 | 172 | RAHAMAN ENTERPRISE | 6.8 | 0 | 0 | 100
332 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL ZONE I PWSS BURDWAN II PURBA BARDHAMAN , SM/15309 | Augmentation | Construction of boundary wall at 2ND TUBE WELL Site & Sanitary of BARSUL Zone-I Piped W/S. Scheme under Burdwan-II Block of Burdwan Division, PHE Dte. (Length =80.00 Mtr, Col-27 Nos). | 3133/BWD | 16/08/2024 | 212 | SK BADIUZZAMAL | 5.77 | 0 | 0 | 100
333 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME , SM/15557 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Srikhanda Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2582/CMD | 07/06/2023 | 580 | AMUSAR IMPEX PVT. LTD. | 11.25 | 0 | 0 | 95
334 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME , SM/15557 | Augmentation | Balance work of OHR, construction Concrete Road, Functional Household Tap Connection, Road restoration etc. for Nanagar PWSS, Srikhanda PWSS, under KATWA -I Block under Katwa Sub-Divn under Burdwan Division, PHE Dte. District:- Purba-Bardhaman. | 3655/BWD | 21/10/2024 | 120 | HAMID SK | 121.69 | 0 | 0 | 0
335 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME , SM/15557 | Augmentation | Quotation for new service connection at Augmentation of Srikhanda PWSS, PH-1. | BP-2024-25-249 | 01/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.73 | 0 | 0 | 0
336 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME , SM/15557 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT AUGMENTATION OF SRIKHANDA PWSS TW 2 | BP-2024-25-188 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.98 | 0 | 0 | 0
337 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME , SM/15557 | Augmentation | Augmentation of SRIKHANDA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-II Block, District:- Purba-Bardhaman. | 3508/BWD | 10/08/2023 | 875 | GUPTA ENTERPRISE | 656.48 | 252.17 | 38.41 | 18
338 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME , SM/15557 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 2 at Augumentation of Srikhanda Water Supply Scheme [ BLOCK- Katwa-I ]under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1626/CMD | 15/03/2024 | 30 | D.K. ELECTRIC | 11.62 | 10.52 | 90.5 | 88
339 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SRIKHANDA PIPED WATER SUPPLY SCHEME , SM/15557 | Augmentation | Construction of Pump House, Boundary walls and Raising Main for Aug. of SRIKHANDA Piped Water Supply Scheme under Katwa-I Block, District:- Purba-Bardhaman. | 5486/BWD | 13/12/2023 | 391 | BABUL SK | 9.77 | 0 | 0 | 75
340 | PURBA BARDHAMAN | Burdwan Division | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Material Requisition To Resource Division | 4912/BWD | 10/11/2023 | 0 | Resource Division | 32.92 | 0 | 0 | 0
341 | PURBA BARDHAMAN | Burdwan Division | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Material Requisition To Resource Division | 4314/BWD | 29/09/2023 | 0 | Resource Division | 1.38 | 0 | 0 | 0
342 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.02.2024 to 31.07.2024).(Sl-01) | 106/DWSD | 31/01/2024 | 182 | SUJIT ROY | 0.82 | 2.4 | 290.96 | 25
343 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Hiring of Luxury Diesel Ambassadar Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.03.2024 to 31.08.2024 (6 Months).(Sl-01) | 267/DWSD | 29/02/2024 | 184 | PRAMIT CHATTERJEE | 0.82 | 2.37 | 288.04 | 0
344 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Continuation order for Acceptance cum formal order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the Executive Engineer, DWSD,PHE Dte ADDA Administrative building 2nd Floor, EPIP Complex, Banskopa,DGP-12 (w.e.f 18.02.2024 to 29.02.2024). (SL-02) | 186/DWSD | 15/02/2024 | 12 | PRAMIT CHATTERJEE | 0.05 | 0.16 | 303.77 | 100
345 | PURBA BARDHAMAN | Central Mechanical | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
346 | PURBA BARDHAMAN | Burdwan Division | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Material Requisition To Resource Division | 193/BWD | 10/01/2024 | 0 | Resource Division | 6.7 | 0 | 0 | 0
347 | PURBA BARDHAMAN | Central Mechanical | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | QUOTATION FOR NEW SERVICE CONNECTION AT ALIGRAM PWSS TW 2 | BP-2024-25-193 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.58 | 0 | 0 | 0
348 | PURBA BARDHAMAN | Central Mechanical | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | New service connection at Aligram W/S PWSS PH-1 | BP-2023-24-431 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.53 | 0 | 0 | 0
349 | PURBA BARDHAMAN | Burdwan Division | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ALIGRAM, JAYKRISHNAPUR, JADABGANJ & KALYANPUR Piped Water Supply Scheme under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 4581/BWD | 16/10/2023 | 965 | SAFECO ENTERPRISES | 1551.98 | 182.42 | 88.62 | 60
350 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.09.2024 to 28.02.2025 (6 Months).(Sl-01) | 1244/DWSD | 30/08/2024 | 182 | PRAMIT CHATTERJEE | 0.82 | 2.39 | 290.19 | 0
351 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Continuation Order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.08.2024 to 31.01.2025).(Sl-01) | 1079/DWSD | 30/07/2024 | 184 | SUJIT ROY | 0.82 | 2.39 | 290.79 | 0
352 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Continuation Order for the work of Hiring of LUXURY Diesel Ambassador Car including higher model 2012 onwards of Diesel Ambassador or equivalent for official use for the office of the Executive Engineer ,Durgapur Water Supply Division, Public Health Engineering (w.e.f 01.02.2025 to 31.07.2025). | 163/DWSD | 27/01/2025 | 181 | SUJIT ROY | 0.82 | 0.4 | 48.49 | 0
353 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.03.2025 to 31.05.2025 (3 Months). | 340/DWSD | 27/02/2025 | 89 | PRAMIT CHATTERJEE | 0.41 | 0.79 | 192.94 | 0
354 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.06.2025 to 31.08.2025 (3 Months). | 853/DWSD | 29/05/2025 | 90 | PRAMIT CHATTERJEE | 0.41 | 0 | 0 | 0
355 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Name of Work:- Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 16.09.2025 to 31.10.2025 (46 days) (Sl-01) | 1532/DWSD | 16/09/2025 | 46 | TKB ENTERPRISE | 0.22 | 0 | 0 | 0
356 | PURBA BARDHAMAN | Durgapur W/S Division | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhaman on daily basis (as and when required including Govt. holidays) period of 01.09.2025 to 28.02.2026 (181 days) (Sl-04) | 1381/DWSD | 26/08/2025 | 181 | PRAMIT CHATTERJEE | 0.86 | 0 | 0 | 0
357 | PURBA BARDHAMAN | Central Mechanical | ALIGRAM PIPED WATER SUPPLY SCHEME , SM/14927 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Aligram Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4057/CMD | 29/08/2023 | 642 | EASTERN INDIA SALES & SERVICE | 27.78 | 10.73 | 47.28 | 48
358 | PURBA BARDHAMAN | Burdwan Division | MOSHRA PIPED WATER SUPPLY SCHEME , SM/14931 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.91 | 0 | 0 | 0
359 | PURBA BARDHAMAN | Burdwan Division | MOSHRA PIPED WATER SUPPLY SCHEME , SM/14931 | New | Material Requisition To Resource Division | 3993/BWD | 08/09/2023 | 0 | Resource Division | 7.17 | 0 | 0 | 0
360 | PURBA BARDHAMAN | Burdwan Division | MOSHRA PIPED WATER SUPPLY SCHEME , SM/14931 | New | Material Requisition To Resource Division | 5053/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
361 | PURBA BARDHAMAN | Burdwan Division | MOSHRA PIPED WATER SUPPLY SCHEME , SM/14931 | New | Continuation Work Order supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2023 to 31-01-2024) | 2561/BSD | 30/10/2023 | 66 | MD HASIN | 0.85 | 0 | 0 | 0
362 | PURBA BARDHAMAN | Central Mechanical | MOSHRA PIPED WATER SUPPLY SCHEME , SM/14931 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
363 | PURBA BARDHAMAN | Central Mechanical | MOSHRA PIPED WATER SUPPLY SCHEME , SM/14931 | New | Electric quotation for New Service Connection at Moshra W/S Scehem PH-I. | BP-2023-24-289 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.54 | 0 | 0 | 0
364 | PURBA BARDHAMAN | Central Mechanical | MOSHRA PIPED WATER SUPPLY SCHEME , SM/14931 | New | Quotation for new service connection for Mashra PWSS TW-2 | BP-2024-25-147 | 19/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.84 | 0 | 0 | 0
365 | PURBA BARDHAMAN | Burdwan Division | MOSHRA PIPED WATER SUPPLY SCHEME , SM/14931 | New | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related (schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-05-2025 to 31-07-2025) | 960/BSD | 30/04/2025 | 66 | PARVIN BEGAM | 0.85 | 0 | 0 | 100
366 | PURBA BARDHAMAN | Central Mechanical | MOSHRA PIPED WATER SUPPLY SCHEME , SM/14931 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Moshra Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4025/CMD | 29/08/2023 | 642 | MAA KALI ENTERPRISE | 29.37 | 11.67 | 47.82 | 100
367 | PURBA BARDHAMAN | Burdwan Division | MAHARUTBA PIPED WATER SUPPLY SCHEME , SM/14970 | New | Material Requisition To Resource Division | 1965/BWD | 26/04/2023 | 0 | Resource Division | 2.48 | 0 | 0 | 0
368 | PURBA BARDHAMAN | Burdwan Division | MAHARUTBA PIPED WATER SUPPLY SCHEME , SM/14970 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 1.47 | 0 | 0 | 0
369 | PURBA BARDHAMAN | Central Drilling | MAHARUTBA PIPED WATER SUPPLY SCHEME , SM/14970 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilising Departmental Machineries for MAHARUTBA W/S Scheme (T/W-I), Mongalkote Block under Purba Bardhaman District, Central Drilling Division, P.H.E. Dte. | 1819/CDD | 07/12/2023 | 30 | M/S PRACHI ENGINEERING | 13.67 | 13.12 | 100 | 100
370 | PURBA BARDHAMAN | Central Drilling | MAHARUTBA PIPED WATER SUPPLY SCHEME , SM/14970 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for MAHARUTBA W/S Scheme (T/W-II) Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | 1338/CDD | 13/09/2023 | 30 | C.M. ENTERPRISE | 11.46 | 4.59 | 31.87 | 100
371 | PURBA BARDHAMAN | Burdwan Division | MAHARUTBA PIPED WATER SUPPLY SCHEME , SM/14970 | New | Material Requisition To Resource Division | 296/BWD | 24/01/2024 | 0 | Resource Division | 20.47 | 0 | 0 | 0
372 | PURBA BARDHAMAN | Central Mechanical | MAHARUTBA PIPED WATER SUPPLY SCHEME , SM/14970 | New | NEW SERVICE CONNECTION FOR MAHARTUBA PWSS. | BP-2023-24-610 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.94 | 0 | 0 | 0
373 | PURBA BARDHAMAN | Central Mechanical | MAHARUTBA PIPED WATER SUPPLY SCHEME , SM/14970 | New | Quotation for new service connection at Mahartuba PWSS PH-1 | BP-2024-25-206 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7 | 0 | 0 | 0
374 | PURBA BARDHAMAN | Burdwan Division | MAHARUTBA PIPED WATER SUPPLY SCHEME , SM/14970 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BHATPARA & MAHARUTBA Piped Water Supply Scheme under Mangolkote Block, District:-Purba-Bardhaman [NEW SCHEME] | 3328/BWD | 02/08/2023 | 791 | KAMIRUL SK & CO. | 815.64 | 266.02 | 74.7 | 10
375 | PURBA BARDHAMAN | Central Mechanical | MAHARUTBA PIPED WATER SUPPLY SCHEME , SM/14970 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Maharutba Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4069/CMD | 29/08/2023 | 30 | GLACIER ENGINEERING CO | 26.98 | 0 | 0 | 44
376 | PURBA BARDHAMAN | Central Mechanical | MAHARUTBA PIPED WATER SUPPLY SCHEME , SM/14970 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
377 | PURBA BARDHAMAN | Burdwan Division | MAHARUTBA PIPED WATER SUPPLY SCHEME , SM/14970 | New | Balance work of MAHARTUTBA Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman | 722/BWD | 24/02/2025 | 120 | KAMIRUL SK & CO. | 147.19 | 0 | 0 | 0
378 | PURBA BARDHAMAN | Burdwan Division | AUSGRAM PIPED WATER SUPPLY SCHEME , SM/14905 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 29.49 | 0 | 0 | 0
379 | PURBA BARDHAMAN | Burdwan Division | AUSGRAM PIPED WATER SUPPLY SCHEME , SM/14905 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 15.16 | 0 | 0 | 0
380 | PURBA BARDHAMAN | Burdwan Division | AUSGRAM PIPED WATER SUPPLY SCHEME , SM/14905 | New | Material Requisition To Resource Division | 4018/BWD | 08/09/2023 | 0 | Resource Division | 29.12 | 0 | 0 | 0
381 | PURBA BARDHAMAN | Burdwan Division | AUSGRAM PIPED WATER SUPPLY SCHEME , SM/14905 | New | Material Requisition To Resource Division | 4903/BWD | 10/11/2023 | 0 | Resource Division | 33.07 | 0 | 0 | 0
382 | PURBA BARDHAMAN | Central Mechanical | AUSGRAM PIPED WATER SUPPLY SCHEME , SM/14905 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
383 | PURBA BARDHAMAN | Durgapur W/S Division | AUSGRAM PIPED WATER SUPPLY SCHEME , SM/14905 | New | Material Requisition To Resource Division | 1724/P/DWSD | 10/12/2024 | 0 | Resource Division | 8.51 | 0 | 0 | 0
384 | PURBA BARDHAMAN | Central Mechanical | AUSGRAM PIPED WATER SUPPLY SCHEME , SM/14905 | New | Quotation for new service connection at Aushgram W/S Scheme for PH No-2 | BP-2023-24-329 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.96 | 0 | 0 | 0
385 | PURBA BARDHAMAN | Central Mechanical | AUSGRAM PIPED WATER SUPPLY SCHEME , SM/14905 | New | Quotation for new service connection for Ausgram PWSS PH 1. | BP-2024-25-115 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.27 | 0 | 0 | 0
386 | PURBA BARDHAMAN | Central Mechanical | AUSGRAM PIPED WATER SUPPLY SCHEME , SM/14905 | New | Quotation for new service connection at Ausgram PWSS PH-2 | BP-2024-25-204 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.87 | 0 | 0 | 0
387 | PURBA BARDHAMAN | Burdwan Division | AUSGRAM PIPED WATER SUPPLY SCHEME , SM/14905 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AUSGRAM & BHOTA Piped Water Supply Scheme under Ausgram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3324/BWD | 02/08/2023 | 776 | DUTTA ENTERPRISE | 763.14 | 318.86 | 59.49 | 70
388 | PURBA BARDHAMAN | Durgapur W/S Division | AUSGRAM PIPED WATER SUPPLY SCHEME , SM/14905 | New | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 0 | 1
389 | PURBA BARDHAMAN | Durgapur W/S Division | AUSGRAM PIPED WATER SUPPLY SCHEME , SM/14905 | New | Sinking of(300X200X150 Mtr deapth) of TW by DR rig method construction of 1 No PH cum Cholorine Room and interconnection and other allied works at Ausgram under Ausgram PWSS ,Ausgram-I,Dist-Purba Bardhaman under DWSD,PHE Dte. | 1276/DWSD | 08/08/2025 | 90 | SUPRIYA RAY | 33.97 | 0 | 0 | 0
390 | PURBA BARDHAMAN | Central Mechanical | AUSGRAM PIPED WATER SUPPLY SCHEME , SM/14905 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Ausgram Water Supply Scheme [ Block-Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4054/CMD | 29/08/2023 | 614 | MENAKA ENTERPRISE. | 27.75 | 10.84 | 47.73 | 48
391 | PURBA BARDHAMAN | Burdwan Division | SUATA PIPED WATER SUPPLY SCHEME , SM/14974 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 46.65 | 0 | 0 | 0
392 | PURBA BARDHAMAN | Burdwan Division | SUATA PIPED WATER SUPPLY SCHEME , SM/14974 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.13 | 0 | 0 | 0
393 | PURBA BARDHAMAN | Burdwan Division | SUATA PIPED WATER SUPPLY SCHEME , SM/14974 | New | Material Requisition To Resource Division | 4887/BWD | 10/11/2023 | 0 | Resource Division | 30.36 | 0 | 0 | 0
394 | PURBA BARDHAMAN | Central Mechanical | SUATA PIPED WATER SUPPLY SCHEME , SM/14974 | New | New service connection charges for Suata PWSS TW-2 | BP-2023-24-233 | 20/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.29 | 0 | 0 | 0
395 | PURBA BARDHAMAN | Durgapur W/S Division | SUATA PIPED WATER SUPPLY SCHEME , SM/14974 | New | Acceptance cum Formal Work Order for Balance works of 160 mm dia HDPE rising main at JOYRAMPUR area and etc. allied works at SUATA of Ausgram -II Block of SUATA W/S Scheme (JJM) under Durgapur Water Supply Division, PHE Dte. | 1012/DWSD | 16/07/2024 | 90 | SAIKAT RAY | 67.88 | 0 | 0 | 100
396 | PURBA BARDHAMAN | Durgapur W/S Division | SUATA PIPED WATER SUPPLY SCHEME , SM/14974 | New | Acceptance cum Formal Work Order for the work of " Balance work for sinking of 250 x 150mm dia T/W, P/H, Boundary wall, DI RM and LLDS for proposed 3rd T/W and other allied works under Sauta PWSS, Block- Aushgram-II, Dist-Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 768/DWSD | 06/06/2024 | 45 | SAIKAT RAY | 94.93 | 54.47 | 58.59 | 70
397 | PURBA BARDHAMAN | Durgapur W/S Division | SUATA PIPED WATER SUPPLY SCHEME , SM/14974 | New | Material Requisition To Resource Division | 1724/I/DWSD | 10/12/2024 | 0 | Resource Division | 2.16 | 0 | 0 | 0
398 | PURBA BARDHAMAN | Central Mechanical | SUATA PIPED WATER SUPPLY SCHEME , SM/14974 | New | QUOTATION FOR NEW SERVICE CONNECTION FOR SUATA (ADDL TW)PWSS, TW 2 | BP-2024-25-162 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.68 | 0 | 0 | 0
399 | PURBA BARDHAMAN | Central Mechanical | SUATA PIPED WATER SUPPLY SCHEME , SM/14974 | New | Quotation for new service connection at Suata W/S Scheme for PH No-1. | BP-2023-24-331 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.43 | 0 | 0 | 0
400 | PURBA BARDHAMAN | Burdwan Division | SUATA PIPED WATER SUPPLY SCHEME , SM/14974 | New | SUATA Piped Water Supply Scheme with sinking of Tube-well, LDS,Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3524/BWD | 10/08/2023 | 629 | SAIKAT RAY | 615.97 | 399.21 | 57.61 | 45
401 | PURBA BARDHAMAN | Central Mechanical | SUATA PIPED WATER SUPPLY SCHEME , SM/14974 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Suata Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4058/CMD | 29/08/2023 | 30 | DEY ENTERPRISE | 27.79 | 22.05 | 95.31 | 96
402 | PURBA BARDHAMAN | Durgapur W/S Division | SUATA PIPED WATER SUPPLY SCHEME , SM/14974 | New | Acceptance cum Formal Work Order for Balance Work for Suata PWSS with LDS,FHTC Under Ausgram- II Block, Diastrict- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 1618/DWSD | 26/11/2024 | 90 | SAIKAT RAY | 28 | 7.41 | 20.94 | 100
403 | PURBA BARDHAMAN | Central Mechanical | SUATA PIPED WATER SUPPLY SCHEME , SM/14974 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at SUATA Water Supply Scheme [ BLOCK- AUSGRAM-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3090/CMD | 10/12/2024 | 233 | SWAPAN BANERJEE | 12.79 | 3.21 | 20.22 | 90
404 | PURBA BARDHAMAN | Burdwan Division | BHATPARA PIPE WATER SUPPLY SCHEME , SM/14975 | New | Material Requisition To Resource Division | 3984/BWD | 08/09/2023 | 0 | Resource Division | 1.21 | 0 | 0 | 0
405 | PURBA BARDHAMAN | Burdwan Division | BHATPARA PIPE WATER SUPPLY SCHEME , SM/14975 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.75 | 0 | 0 | 0
406 | PURBA BARDHAMAN | Central Mechanical | BHATPARA PIPE WATER SUPPLY SCHEME , SM/14975 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
407 | PURBA BARDHAMAN | Central Drilling | BHATPARA PIPE WATER SUPPLY SCHEME , SM/14975 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for Bhatpara W/S Scheme (T/W-I & II), Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | 1820/CDD | 07/12/2023 | 268 | UTTAM KUMAR CHATTERJEE | 23.35 | 22.5 | 100 | 100
408 | PURBA BARDHAMAN | Burdwan Division | BHATPARA PIPE WATER SUPPLY SCHEME , SM/14975 | New | Material Requisition To Resource Division | 311/BWD | 24/01/2024 | 0 | Resource Division | 20.47 | 0 | 0 | 0
409 | PURBA BARDHAMAN | Central Mechanical | BHATPARA PIPE WATER SUPPLY SCHEME , SM/14975 | New | Quotation for new service connection at Bhatpara PWSS PH-1. | BP-2024-25-171 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.58 | 0 | 0 | 0
410 | PURBA BARDHAMAN | Central Mechanical | BHATPARA PIPE WATER SUPPLY SCHEME , SM/14975 | New | Quotation for new service connection at Bhatpara PWSS PH-2. | BP-2024-25-170 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.38 | 0 | 0 | 0
411 | PURBA BARDHAMAN | Burdwan Division | BHATPARA PIPE WATER SUPPLY SCHEME , SM/14975 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BHATPARA & MAHARUTBA Piped Water Supply Scheme under Mangolkote Block, District:-Purba-Bardhaman [NEW SCHEME] | 3328/BWD | 02/08/2023 | 791 | KAMIRUL SK & CO. | 815.64 | 375.49 | 81.71 | 10
412 | PURBA BARDHAMAN | Central Mechanical | BHATPARA PIPE WATER SUPPLY SCHEME , SM/14975 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BHATPARA Water Supply Scheme [ Block- MANGALKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4108/CMD | 29/08/2023 | 580 | JAL PRAVAHIKA PVT LTD | 28.97 | 0 | 0 | 42
413 | PURBA BARDHAMAN | Burdwan Division | GOHAGRAM PIPED WATER SUPPLY SCHEME , SM/14910 | New | Material Requisition To Resource Division | 1244/BWD | 17/03/2023 | 0 | Resource Division | 7.44 | 0 | 0 | 0
414 | PURBA BARDHAMAN | Burdwan Division | GOHAGRAM PIPED WATER SUPPLY SCHEME , SM/14910 | New | Material Requisition To Resource Division | 1965/BWD | 26/04/2023 | 0 | Resource Division | 2.89 | 0 | 0 | 0
415 | PURBA BARDHAMAN | Central Mechanical | GOHAGRAM PIPED WATER SUPPLY SCHEME , SM/14910 | New | New service connection charges of Gohagram W/S Scheme TW-2 | BP-2023-24-32 | 26/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.55 | 0 | 0 | 0
416 | PURBA BARDHAMAN | Central Mechanical | GOHAGRAM PIPED WATER SUPPLY SCHEME , SM/14910 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
417 | PURBA BARDHAMAN | Burdwan Division | GOHAGRAM PIPED WATER SUPPLY SCHEME , SM/14910 | New | Material Requisition To Resource Division | 300/BWD | 24/01/2024 | 0 | Resource Division | 20.47 | 0 | 0 | 0
418 | PURBA BARDHAMAN | Central Mechanical | GOHAGRAM PIPED WATER SUPPLY SCHEME , SM/14910 | New | NEW SERVICE CONNECTION FOR GOHAGRAM PWSS TW 1. | BP-2023-24-539 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.94 | 0 | 0 | 0
419 | PURBA BARDHAMAN | Burdwan Division | GOHAGRAM PIPED WATER SUPPLY SCHEME , SM/14910 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOHAGRAM, KHERUA & JABAGRAM Piped Water Supply Scheme under Mangalkote Block, District:- Purba Bardhaman [NEW SCHEME] | 582/BWD | 17/02/2023 | 1049 | PUSPA ENTERPRISE | 1185.88 | 197.48 | 54.95 | 75
420 | PURBA BARDHAMAN | Central Mechanical | GOHAGRAM PIPED WATER SUPPLY SCHEME , SM/14910 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at GOHAGRAM Water Supply Scheme [ Block- MANGALKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2640/CMD | 14/06/2023 | 740 | CHOUDHURY ENTERPRISE | 27.48 | 0 | 0 | 82
421 | PURBA BARDHAMAN | Burdwan Division | GOHAGRAM PIPED WATER SUPPLY SCHEME , SM/14910 | New | Different types of works involve in connection with implementation of Gohgram, Jabagram, Kherua, Lakshmipur & Simulia Piped Water Supply Scheme under Mongolkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. | 936/BWD | 11/03/2025 | 180 | M/S GHOSH CONSTRUCTION | 360.68 | 0 | 0 | 0
422 | PURBA BARDHAMAN | Central Mechanical | GOHAGRAM PIPED WATER SUPPLY SCHEME , SM/14910 | New | Supply and delivery of 10 HP pump motor set at T.W. No - 1 of Gohagram water supply scheme under CMD, PHE Dte. | 930/DIC/BMSD(D) | 27/12/2024 | 7 | CHOUDHURY ENTERPRISE | 0.81 | 0 | 0 | 100
423 | PURBA BARDHAMAN | Burdwan Division | NIGAN PIPE WATER SUPPLY SCHEME , SM/14912 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.74 | 0 | 0 | 0
424 | PURBA BARDHAMAN | Burdwan Division | NIGAN PIPE WATER SUPPLY SCHEME , SM/14912 | New | Material Requisition To Resource Division | 3983/BWD | 08/09/2023 | 0 | Resource Division | 3.91 | 0 | 0 | 0
425 | PURBA BARDHAMAN | Burdwan Division | NIGAN PIPE WATER SUPPLY SCHEME , SM/14912 | New | Material Requisition To Resource Division | 303/BWD | 24/01/2024 | 0 | Resource Division | 20.47 | 0 | 0 | 0
426 | PURBA BARDHAMAN | Central Mechanical | NIGAN PIPE WATER SUPPLY SCHEME , SM/14912 | New | Quotation for new service connection at Nigan PWSS TW-1 | BP-2024-25-394 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.95 | 0 | 0 | 0
427 | PURBA BARDHAMAN | Central Mechanical | NIGAN PIPE WATER SUPPLY SCHEME , SM/14912 | New | Quotation for new service connection at Nigan PWSS TW-2 | BP-2024-25-395 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.15 | 0 | 0 | 0
428 | PURBA BARDHAMAN | Burdwan Division | NIGAN PIPE WATER SUPPLY SCHEME , SM/14912 | New | NIGAN Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 250 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | 2386/BWD | 23/05/2023 | 365 | AKASH CONSTRUCTION | 400.98 | 27.53 | 6.87 | 15
429 | PURBA BARDHAMAN | Central Mechanical | NIGAN PIPE WATER SUPPLY SCHEME , SM/14912 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Nigan Water Supply Scheme [ Block- MONGOLKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4068/CMD | 29/08/2023 | 710 | AHALYA ENGINEERING WORKS | 27.78 | 0 | 0 | 44
430 | PURBA BARDHAMAN | Central Mechanical | NIGAN PIPE WATER SUPPLY SCHEME , SM/14912 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
431 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at H.W, 2nd and 3rd Tubewell site for GALSI Piped Water Supply Scheme, Block - Galsi ¿ II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [3 Nos. GTW]. | 1622/BWD | 21/03/2022 | 60 | AUXILIARY TUBE WELL DRILLERS | 35.56 | 18.65 | 52.44 | 1
432 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Route Survey & Preparation of DPR for GALSI PWSS under Durgapur(Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-D] | 102/DSD | 18/02/2022 | 15 | SIRCON ENGINEERING SERVICES | 2.74 | 2.74 | 100 | 1
433 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Retrofitting of RCC Elevated Reservoir (Capacity 450 Cum) by Shortcreting, Guniting etc. in connection with Augmentation of Galsi W/S. Scheme under Burdwan Division, PHE. Dte. | 6042/BWD | 07/10/2021 | 45 | SUDIPTO GORAIN | 10 | 10 | 100 | 1
434 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
435 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. | 1194/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0 | 0
436 | PURBA BARDHAMAN | Central Mechanical | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 3 (SL no.5) at Augumentation of Galsi Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2563/CMD | 06/06/2023 | 30 | C.M. ENTERPRISE | 10.78 | 0 | 0 | 0
437 | PURBA BARDHAMAN | Central Mechanical | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation of Galsi Water Supply Scheme [ Block- Galsi-ii ] at pwss-2/3 site, Tube well No.-4 under CMD, PHE Dte., Dist.- Purba-Bardhaman | 2097/CMD | 08/09/2022 | 30 | UNIVERSAL ENTERPRISES | 11.07 | 10.79 | 100 | 1
438 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Dignagar, Galsi, Barabelun & Kotachandipur Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. Dte. _2ND CALL | 3624/BWD | 22/08/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.76 | 3.69 | 100 | 1
439 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Dismantling of concrete road in connection of Laying Distribution Network of Ground Water based Piped Water Supply Scheme for Augmentation of GALSI Piped Water Supply Scheme under Galsi-II in Purba Bardhaman District under Burdwan Division, P.H.E. Dte. | 1084/BWD | 13/03/2023 | 30 | M/S EL-CON | 13.75 | 13.67 | 100 | 0
440 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Construction of Toilet (Female) at Durgapur (Burdwan North) Sub Division premises under Augmentation of Galsi piped water supply scheme under Burdwan Division PHE Dte. [SL-08] | 183/DSD | 18/04/2023 | 21 | ANWESHA CONSTRUCTION | 0.91 | 0.89 | 100 | 100
441 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Material Requisition To Resource Division | 7346/BWD | 30/12/2021 | 0 | Resource Division | 13.73 | 0 | 0 | 0
442 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Material Requisition To Resource Division | 554/BWD | 27/01/2022 | 0 | Resource Division | 23.26 | 0 | 0 | 0
443 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Material Requisition To Resource Division | 772/BWD | 07/02/2022 | 0 | Resource Division | 43.86 | 0 | 0 | 0
444 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Material Requisition To Resource Division | 1380/BWD | 09/03/2022 | 0 | Resource Division | 3.86 | 0 | 0 | 0
445 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Material Requisition To Resource Division | 1559/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
446 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Material Requisition To Resource Division | 1327/BWD | 08/03/2022 | 0 | Resource Division | 55.09 | 0 | 0 | 0
447 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Material Requisition To Resource Division | 4629/BWD | 17/10/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
448 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Quotation for new connection charges for Augmentation of Galsi w/s scheme under Burdwan Division, PHE Dte. T.W. No.-5 [Application No.-5003534483, dt.-28/11/2022, Ref. ID-503226320] | 915/DW | 30/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.67 | 0 | 0 | 0
449 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Restoration of damages caused by PHE Dte. at Galsi Gohogram Road between 0.00 Km & 1.50 Km. (NH-2 Junction) from laying of underground pipeline under Asansol Highway Division, PW Roads Dte. | 24/JJM | 18/04/2023 | 0 | EXECUTIVE ENGINEER, ASANSOL HIGHWAY DIVISION, P.W.(ROADS) DTE. | 4.56 | 0 | 0 | 0
450 | PURBA BARDHAMAN | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | FORMAL WORK ORDER FOR Additional work for laying of extension or laying of paralled pipeline construction of boundary wall providing left out FHTC road restoration work inter connection of tube well with allied work for Augmentation of Galsi PWSS Galsi-II Block, Dist- Purba Bardhaman under DURGAPUR W/S DIVISION, PHE DTE. | 533/DWSD | 25/03/2025 | 90 | J D CONSTRUCTION | 159.4 | 0 | 0 | 0
451 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for GALSI to accommodate FHTC under Jal Sapno Mission underGalsi-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09712 | Augmentation | Augmentation of GALSI Water Supply Scheme with LDS, Rising Main, FHTC Work, Pump House & Boundary Wall of Galsi - II Block in Durgapur (Burdwan North) Sub-Division, District - Purba Bardhaman under Burdwan Division, PHE. Dte. | 257/BWD | 13/01/2022 | 725 | M/S EL-CON | 425.49 | 99.89 | 88.62 | 40
452 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME , SM/15159 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme GANGATIKURI PWSS (Sl No-04) | 396/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 2.49 | 2.49 | 100 | 100
453 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME , SM/15159 | Augmentation | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | 1009/KTS | 19/07/2024 | 60 | AJIT SAMANTA | 0.77 | 0.15 | 90.67 | 100
454 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME , SM/15159 | Augmentation | Yard lighting arrangement & allied works at Gangatikuri water supply scheme under Ketugram-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2788/CMD | 01/10/2024 | 60 | DILIP MAHATO | 15.98 | 0 | 0 | 0
455 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME , SM/15159 | Augmentation | Quotation for new service connection at Augmentation of Gangatikuri PWSS TW-1 | BP-2024-25-402 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.88 | 0 | 0 | 0
456 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME , SM/15159 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Gangatikuri Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2584/CMD | 07/06/2023 | 730 | M/S, S.S. ENTERPRISE. | 22.6 | 0 | 0 | 44
457 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME , SM/15159 | Augmentation | Augmentation of GANGATIKURI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM-II Block, District:- Purba-Bardhaman. | 5375/BWD | 07/12/2023 | 756 | S.S. ENTERPRISE | 194.38 | 93.32 | 48.01 | 56
458 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GANGAGTIKURI PIPED WATER SUPPLY SCHEME , SM/15159 | Augmentation | Protection work for construction of concrete road along with other allied work in connection with Gangatikuri PWSs (SM/15159) under Ketugram II Block under Katwa Sub Division within Burdwan Division, PHE. Dte. | 258/BWD | 14/01/2025 | 352 | S.S. ENTERPRISE | 34.25 | 0 | 0 | 0
459 | PURBA BARDHAMAN | Burdwan Division | SITAHATI PIPE WATER SUPPLY SCHEME , SM/15161 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.1 | 0 | 0 | 0
460 | PURBA BARDHAMAN | Burdwan Division | SITAHATI PIPE WATER SUPPLY SCHEME , SM/15161 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.24 | 0 | 0 | 0
461 | PURBA BARDHAMAN | Burdwan Division | SITAHATI PIPE WATER SUPPLY SCHEME , SM/15161 | New | Material Requisition To Resource Division | 5233/BWD | 30/11/2023 | 0 | Resource Division | 20.37 | 0 | 0 | 0
462 | PURBA BARDHAMAN | Central Mechanical | SITAHATI PIPE WATER SUPPLY SCHEME , SM/15161 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SITAHATI Water Supply Scheme [ Block- MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4138/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 27.7 | 22.72 | 100 | 46
463 | PURBA BARDHAMAN | Burdwan Division | SITAHATI PIPE WATER SUPPLY SCHEME , SM/15161 | New | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | 907/BWD | 04/03/2024 | 30 | MANASH GHOSH | 23.87 | 4.76 | 100 | 100
464 | PURBA BARDHAMAN | Burdwan Division | SITAHATI PIPE WATER SUPPLY SCHEME , SM/15161 | New | Material Requisition To Resource Division | 4118/BWD | 25/11/2024 | 0 | Resource Division | 18.62 | 0 | 0 | 0
465 | PURBA BARDHAMAN | Central Mechanical | SITAHATI PIPE WATER SUPPLY SCHEME , SM/15161 | New | NEW SERVICE CONNECTION FOR SITAHATI PWSS. | BP-2023-24-611 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.68 | 0 | 0 | 0
466 | PURBA BARDHAMAN | Central Mechanical | SITAHATI PIPE WATER SUPPLY SCHEME , SM/15161 | New | NEW SERVICE CONNECTION FOR SITAHATI PWSS. | BP-2023-24-612 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.43 | 0 | 0 | 0
467 | PURBA BARDHAMAN | Central Mechanical | SITAHATI PIPE WATER SUPPLY SCHEME , SM/15161 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
468 | PURBA BARDHAMAN | Burdwan Division | SITAHATI PIPE WATER SUPPLY SCHEME , SM/15161 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PALISGRAM, PURBA NAYAPARA & SITAHATI Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] | 4364/BWD | 04/10/2023 | 910 | M/S S. CHOUDHURY | 1505.07 | 243.95 | 62.53 | 77
469 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for NABABHAT its Adjoining Mouza W/S Scheme, Block -Bardhaman-I within Burdwan Sub-Division, PHE Dte. (Mouza- KRISHNAPUR) | 499/BSD | 21/03/2023 | 45 | BHASKAR NANDY | 3.16 | 2.73 | 100 | 100
470 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | Balance work for Augmentation of Nababhat PWSS in connection with renovation and modification of administrative office complex building under Burdwan Division PHE Dte. | 3400/BWD | 03/08/2023 | 30 | SANDIPAN SENGUPTA | 7.78 | 7.76 | 100 | 100
471 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | New service connection charges of Aug. Nababhat W/S Scheme TW-3 | BP-2023-24-31 | 23/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.58 | 0 | 0 | 0
472 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of NABABHAT( Part-B)[BURDWAN-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3899/CMD | 18/08/2023 | 30 | CINZANO | 22.41 | 11.18 | 49.9 | 50
473 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | Allied work for Augmentation of NABABHAT PWSS under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 3360/BWD | 02/08/2023 | 60 | M/S ANAND CONSTRUCTION | 40.09 | 40.07 | 100 | 100
474 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | Laying of inter connection between 3rd tube well site (Mouza-Krishnapur) and distribution system for Nababhat PWSS within Bardhaman-I Block , under Burdwan Division, PHE Dte | 2951/BSD | 19/12/2023 | 45 | I.S. ENTERPRISE | 2.91 | 2.9 | 100 | 100
475 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | Providing laying distrfrrrrribution pipe line at Amtala-Sukantapally due to construction of Road by gp for Nababhat PWSS under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1031/BSD | 10/06/2024 | 30 | SANDIPAN SENGUPTA | 0.96 | 0.92 | 100 | 100
476 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | Providing laying distribution pipe line due to Constructioon of road by GP for NABABHAT PWSS under Burdwan-I Block of within Burdwan Sub Division under Burdwan Division PHE Dte. | 536/BSD | 14/03/2024 | 30 | NABAKUMAR DAS | 0.86 | 0.85 | 100 | 100
477 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | Balance Work for extension of pipe lines to provide FHTC With Sinking of Tub well , Construction of pump house with Boundary wall & other related work for TALIT-SIMDAL (SM/18112), NABABHAT (SM-15166) and DEWANDIGHI-MIRJAPUR (SM/09494) PWSS under Burdwan Sub-Div., Block -Bwn-1, under Burdwan Division PHE Dte. | 793/BWD | 03/03/2025 | 120 | M/S S.S. ENTERPRISE | 227.66 | 0 | 0 | 0
478 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | Balance work for Augmentation of Nababhat PWSS in connection with upgradation of Approach Road, Land Development, etc for Head Works Site of Nababhat PWSS under Burdwan Division PHE Dte. | 661/BWD | 18/02/2025 | 30 | M/S S. CHOUDHURY | 19.92 | 0 | 0 | 100
479 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | Supply & Installation of submersible pumping machinery, different electro-mechanical works for Nababhat w/s scheme, T.W. No.-I (Replacement tubewell) and Power Backup arrangement at the office of the Burdwan Division & Durgapur w/s Division including RWS, Purba Bardhaman under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2695/CMD | 11/09/2024 | 263 | CHOUDHURY ENTERPRISE | 24.83 | 0 | 0 | 100
480 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | Restoration of Road damaged by laying of Pipeline with ballah piling work at different location for NABABHAT Piped Water Supply Scheme, Block- Burdwan -I, within Burdwan Sub Division under Burdwan Division PHE Dte. | 2714/BWD | 11/07/2024 | 174 | GENUINE ENGINEERS CO-OP. SOCIETY LTD. | 17.93 | 3.62 | 16.93 | 100
481 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | Sinking of 250 X 200 mm dia Tube Well (Replace) 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Head works TW site of NABABHAT Scheme under Burdwan - I Block within Burdwan Sub-Division, PHE Dte. | 372/BWD | 16/01/2025 | 30 | DAS CONSTRUCTION | 12.27 | 0 | 0 | 100
482 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | Providing laying parallal distribution pipe line from Krishnapur pump to Kishnapur Baganpara for Nababhat PWSS under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 373/BWD | 16/01/2025 | 135 | M/S ANAND CONSTRUCTION | 5.97 | 0 | 0 | 100
483 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NABABHAT PWSS (PART B) , SM/15166 | Augmentation | Laying of inter connection between Replace tube well H/W site and distribution system for NABABHAT PWSS within Bardhaman-I Block, under Burdwan Division, PHE Dte. | 1548/BSD | 02/07/2025 | 75 | M/S PURBASHA | 0.51 | 0 | 0 | 100
484 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHANDUTIA , SM/15205 | Augmentation | Preparation and Submission of DPR for Augmentation of Chandutia PWSS under Burdwan-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1475/BSD | 12/07/2023 | 15 | MEASURE LAND | 0.78 | 0.77 | 100 | 100
485 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHANDUTIA , SM/15205 | Augmentation | Providing 22 Nos.FHTC at CHANDUTIA & JAMALPUR village for declearation of SWAJALGRAM under CHANDUTIA Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. | 1033/BSD | 10/06/2024 | 108 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.97 | 0 | 0 | 100
486 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SUDPUR PIPED WATER SUPPLY SCHEME , SM/15573 | Augmentation | Balance work of OHR at Head Work site, construction of HUME Pipe culvert , Road restoration work and boundary wall at 2nd TW site with Gate, land development at Head work site and 2nd TW site under KAITHAN, SUDPUR & PANUHAT Piped Water Supply Scheme under KATWA -I Block, under Katwa Sub-Division within Burdwan Division, PHE Dte. | 3141/BWD | 20/08/2024 | 120 | VISHAL CONSTRUCTION CO. | 126.29 | 31.92 | 42.57 | 50
487 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SUDPUR PIPED WATER SUPPLY SCHEME , SM/15573 | Augmentation | Augmentation of SUDPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-II Block, District:- Purba-Bardhaman._2ND CALL | 4122/BWD | 14/09/2023 | 840 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 442.27 | 42.09 | 9.52 | 63
488 | PURBA BARDHAMAN | Burdwan Division | SHUKUR PIPED WATER SUPPLY SCHEME , SM/16255 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 5.01 | 0 | 0 | 0
489 | PURBA BARDHAMAN | Burdwan Division | SHUKUR PIPED WATER SUPPLY SCHEME , SM/16255 | New | Material Requisition To Resource Division | 4004/BWD | 08/09/2023 | 0 | Resource Division | 7.71 | 0 | 0 | 0
490 | PURBA BARDHAMAN | Burdwan Division | SHUKUR PIPED WATER SUPPLY SCHEME , SM/16255 | New | Material Requisition To Resource Division | 5072/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
491 | PURBA BARDHAMAN | Central Mechanical | SHUKUR PIPED WATER SUPPLY SCHEME , SM/16255 | New | New service connection charges for Shukur PWSS TW-2 | BP-2023-24-272 | 15/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.71 | 0 | 0 | 0
492 | PURBA BARDHAMAN | Central Mechanical | SHUKUR PIPED WATER SUPPLY SCHEME , SM/16255 | New | Continuation order-Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven ) for supervision of site for the office of the Assistant Engineer,under CMD,PHE,Dte. [W.e.f-01/10/2024 to 30/11/2024) [UNDER JJM WORKS] | 1248/CMSD | 30/09/2024 | 61 | PRODYUT GHOSH | 0.8 | 0.77 | 96.28 | 0
493 | PURBA BARDHAMAN | Central Mechanical | SHUKUR PIPED WATER SUPPLY SCHEME , SM/16255 | New | New Service connection for Sukur W/S Scheme PH No.-I | BP-2023-24-318 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.06 | 0 | 0 | 0
494 | PURBA BARDHAMAN | Burdwan Division | SHUKUR PIPED WATER SUPPLY SCHEME , SM/16255 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAJITPUR, SHUKUR & HARISHNAPUR Piped Water Supply Scheme under RAINA-I Block, District:- Purba Bardhaman [NEW SCHEME] | 3197/BWD | 24/07/2023 | 907 | MRITYUNJOY MUKHERJEE & CO. | 1242.03 | 105.22 | 21.12 | 55
495 | PURBA BARDHAMAN | Burdwan Division | SHUKUR PIPED WATER SUPPLY SCHEME , SM/16255 | New | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related(schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-02-2025 to 30-04-2025) | 240/BSD | 31/01/2025 | 66 | PARVIN BEGAM | 0.85 | 0.28 | 100 | 100
496 | PURBA BARDHAMAN | Central Mechanical | SHUKUR PIPED WATER SUPPLY SCHEME , SM/16255 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Shukur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4035/CMD | 29/08/2023 | 642 | S.P. CONSTRUCTION | 28.98 | 0 | 0 | 95
497 | PURBA BARDHAMAN | Burdwan Division | PATHAR GHATA PIPED WATER SUPPLY SCHEME , SM/16029 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 32.19 | 0 | 0 | 0
498 | PURBA BARDHAMAN | Burdwan Division | PATHAR GHATA PIPED WATER SUPPLY SCHEME , SM/16029 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.93 | 0 | 0 | 0
499 | PURBA BARDHAMAN | Burdwan Division | PATHAR GHATA PIPED WATER SUPPLY SCHEME , SM/16029 | New | Work Order for "Restoration of pipeline with other allied works at different places of Akalposh, singa, kadiara, panchrakhi mouja under Patahrghata Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-II panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte. | 1843/KSD | 27/11/2024 | 15 | SUPRITI ENTERPRISE | 2.86 | 0 | 0 | 0
500 | PURBA BARDHAMAN | Burdwan Division | PATHAR GHATA PIPED WATER SUPPLY SCHEME , SM/16029 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR PATHARGHATA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 2149/KSD | 07/03/2024 | 10 | DEL DELTA CONSTRUCTION | 0.66 | 0.66 | 100 | 100
501 | PURBA BARDHAMAN | Central Mechanical | PATHAR GHATA PIPED WATER SUPPLY SCHEME , SM/16029 | New | New electric connection for Patharghata PWSS, PH-1. | BP-2023-24-351 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.41 | 0 | 0 | 0
502 | PURBA BARDHAMAN | Central Mechanical | PATHAR GHATA PIPED WATER SUPPLY SCHEME , SM/16029 | New | New electric connection for Patharghata PWSS, PH-2. | BP-2023-24-351 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.33 | 0 | 0 | 0
503 | PURBA BARDHAMAN | Burdwan Division | PATHAR GHATA PIPED WATER SUPPLY SCHEME , SM/16029 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KASIPUR, PATHAR GHATA & SABIDPUR Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3697/BWD | 24/08/2023 | 770 | SUPRITI ENTERPRISE | 1185.67 | 122.67 | 33.22 | 42
504 | PURBA BARDHAMAN | Central Mechanical | PATHAR GHATA PIPED WATER SUPPLY SCHEME , SM/16029 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PATHAR GHATA Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4165/CMD | 29/08/2023 | 735 | J.S. CONSTRUCTION. | 28.48 | 0 | 0 | 45
505 | PURBA BARDHAMAN | Central Mechanical | PATHAR GHATA PIPED WATER SUPPLY SCHEME , SM/16029 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
506 | PURBA BARDHAMAN | Burdwan Division | PATHAR GHATA PIPED WATER SUPPLY SCHEME , SM/16029 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
507 | PURBA BARDHAMAN | Central Mechanical | SHANKRA PIPE WATER SUPPLY SCHEME , SM/16032 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at SHANKRA [PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4150/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 21.22 | 0 | 0 | 0
508 | PURBA BARDHAMAN | Burdwan Division | SHANKRA PIPE WATER SUPPLY SCHEME , SM/16032 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.59 | 0 | 0 | 0
509 | PURBA BARDHAMAN | Burdwan Division | SHANKRA PIPE WATER SUPPLY SCHEME , SM/16032 | New | Material Requisition To Resource Division | 4898/BWD | 10/11/2023 | 0 | Resource Division | 13.06 | 0 | 0 | 0
510 | PURBA BARDHAMAN | Burdwan Division | SHANKRA PIPE WATER SUPPLY SCHEME , SM/16032 | New | Material Requisition To Resource Division | 4311/BWD | 29/09/2023 | 0 | Resource Division | 8.44 | 0 | 0 | 0
511 | PURBA BARDHAMAN | Burdwan Division | SHANKRA PIPE WATER SUPPLY SCHEME , SM/16032 | New | Work order for "Service for land acquisition for different PWSS under JJM of Purbasthali-I block under Kalna Sub-Division, PHE Dte." | 1721/KSD | 05/12/2023 | 91 | PARTHA PRATIM ACHARYA | 0.96 | 0 | 0 | 5
512 | PURBA BARDHAMAN | Burdwan Division | SHANKRA PIPE WATER SUPPLY SCHEME , SM/16032 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMPUR, GAHAK & SHANKRA Piped Water Supply Scheme under Purbasthali I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3957/BWD | 07/09/2023 | 1051 | M/S B. NANDI | 758.52 | 0 | 0 | 20
513 | PURBA BARDHAMAN | Central Mechanical | SHANKRA PIPE WATER SUPPLY SCHEME , SM/16032 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
514 | PURBA BARDHAMAN | Burdwan Division | DWARIATAN PIPED WATER SUPPLY SCHEME , SM/16285 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 33.94 | 0 | 0 | 0
515 | PURBA BARDHAMAN | Burdwan Division | DWARIATAN PIPED WATER SUPPLY SCHEME , SM/16285 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 21.09 | 0 | 0 | 0
516 | PURBA BARDHAMAN | Burdwan Division | DWARIATAN PIPED WATER SUPPLY SCHEME , SM/16285 | New | Work Order "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR DWARIATON PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 2021/KSD | 06/03/2024 | 10 | BISWAS ENTERPRISE | 0.66 | 0.66 | 100 | 2
517 | PURBA BARDHAMAN | Central Mechanical | DWARIATAN PIPED WATER SUPPLY SCHEME , SM/16285 | New | New Service connection at Dwariatan PWSS PH-1 | BP-2023-24-459 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.24 | 0 | 0 | 0
518 | PURBA BARDHAMAN | Central Mechanical | DWARIATAN PIPED WATER SUPPLY SCHEME , SM/16285 | New | New electric connection for Dwariatan PWSS, PH-2. | BP-2023-24-353 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.95 | 0 | 0 | 0
519 | PURBA BARDHAMAN | Burdwan Division | DWARIATAN PIPED WATER SUPPLY SCHEME , SM/16285 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALINDAR, CHAK SHIMLA & DWARIATAN Piped Water Supply Scheme under Kalna II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3700/BWD | 24/08/2023 | 770 | SUPRITI ENTERPRISE | 1424.22 | 29.87 | 5.61 | 30
520 | PURBA BARDHAMAN | Burdwan Division | DWARIATAN PIPED WATER SUPPLY SCHEME , SM/16285 | New | Different types of works involve in connection with Augmentation of TEHATA Zone-I & II (SM/16301) Water Supply Scheme, CHAKSIMLA (SM/15586) Water Supply Scheme & DWARIATON (SM/16285) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2201/BWD | 13/06/2024 | 752 | M/S ASHA CONSTRUCTION | 449.98 | 64.42 | 29.28 | 25
521 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF MANIKHAR PIPED WATER SUPPLY SCHEME PART-C , SM/16289 | Retrofitting | Augmentation of MANIKHAR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Kalna - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | 2453/BWD | 31/05/2023 | 60 | SETH ENTERPRISE | 34.49 | 34.32 | 100 | 100
522 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF MANIKHAR PIPED WATER SUPPLY SCHEME PART-C , SM/16289 | Retrofitting | Work Oder for "Laying of Rising Main and alied work such as brick work, P.C.C. work and dismantling work etc. for Manikhar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | 1706/KSD | 01/12/2023 | 7 | BISWAS ENTERPRISE | 0.51 | 0.47 | 100 | 100
523 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF MANIKHAR PIPED WATER SUPPLY SCHEME PART-C , SM/16289 | Retrofitting | Arrangement of drinking water supply by installation of solar submersible pump including sinking of 200 mm. dia. Tube well 150 Mtr. Deep by direct rotary rig method, Laying dist. System, FHTC and 2 Nos. 5000 Ltr. PVC tank installation with construction of RCC structure for BHAGABATITALA Habitation which is uncovered of MANIKHAR Piped W/S. Scheme, Block KALNA-1 under Burdwan Division, PHE Dte. | 1245/BWD | 23/04/2025 | 45 | A.R. TRADERS | 30.74 | 0 | 0 | 75
524 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF MANIKHAR PIPED WATER SUPPLY SCHEME PART-C , SM/16289 | Retrofitting | Work order for 'Restoration of Concrete work and land development at Head Work Site of Manikhar PWSS under Kalna Sub-Division under Burdwan Division, PHE Dte.'. | 1771/KSD | 20/11/2024 | 30 | BISWAS ENTERPRISE | 3.26 | 0.96 | 24.34 | 100
525 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) , SM/16290 | Retrofitting | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 2nd TW Site of Aug. of MAJHERGRAM & its adjoining mouzas Piped Water Supply Scheme, Block Monteswar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 5094/BWD | 17/11/2022 | 30 | DAS CONSTRUCTION | 8.71 | 7.77 | 100 | 1
526 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) , SM/16290 | Retrofitting | Interconnection in distribution system from OHR to in between 1st and 2nd Tube Well site for smooth functioning of FHTC work of MAJHERGRAM W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2575/BWD | 01/06/2023 | 30 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 22.54 | 20.07 | 100 | 100
527 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) , SM/16290 | Retrofitting | Laying of UPVC pipeline & providing FHTC work at Dhanyakherur, Majhergram bazar & Hattola village of MAJHERGRAM Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2456/BWD | 31/05/2023 | 30 | PRONAB KUMAR DEY | 9.68 | 5.61 | 100 | 100
528 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) , SM/16290 | Retrofitting | Laying of 75 mm dia HDPE Pipe of Majhergram PWSS of Madhyamgram uttarpara village under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | 908/DSD | 28/10/2024 | 30 | M/S GOSWAMI CONSTRUCTION | 0.96 | 0.95 | 100 | 100
529 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) , SM/16290 | Retrofitting | Providing FHTC & laying of HDPE pipe line for village of Madhyamgram, Dakshinpara, Binnerpar, Dhanyakherur of MAJHERGRAM PWSS of Manteswer Block under Burdwan Division, PHE Dte. | 2251/BWD | 18/06/2024 | 120 | A.R. TRADERS | 40.92 | 23.49 | 53.15 | 100
530 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF MAJHERGRAM PIPED WATER SUPPLY SCHEME(PART-B) , SM/16290 | Retrofitting | Painting and others ancillary works related to OHR of MAJHERGRAM PWSS under Durgapur Sub Division of MANTESWER Block under Burdwan Division P.H.E.Dte. | 728/BWD | 24/02/2025 | 45 | A.R. TRADERS | 7.02 | 0 | 0 | 0
531 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF JHAUDANGA (PART-B) PIPED WATER SUPPLY SCHEME , SM/16293 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 1ST TW Site of JHAUDANGA & its adjoining mouzas Piped Water Supply Scheme, Block Purbasthali II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 273/BWD | 16/01/2024 | 30 | AUXILIARY TUBE WELL DRILLERS | 8.64 | 7.85 | 100 | 1
532 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF JHAUDANGA (PART-B) PIPED WATER SUPPLY SCHEME , SM/16293 | Augmentation | Construction Pump house and construction (As per drawing no-PHE/SE/CC/PH/DWG-01/ 2022-2023) of new (In same place) Pump House No-2 of JHAUDANGA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 4521/BWD | 12/10/2023 | 60 | IYASIN DAFADAR | 6.76 | 6.58 | 100 | 15
533 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF JHAUDANGA (PART-B) PIPED WATER SUPPLY SCHEME , SM/16293 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 09 Nos. Piped W/S. Schemes under Purbasthali II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3018/BWD | 05/08/2024 | 50 | HORIZEN | 23.7 | 6.17 | 100 | 10
534 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF JHAUDANGA (PART-B) PIPED WATER SUPPLY SCHEME , SM/16293 | Augmentation | Different types of works involve in connection with Augmentation of JHAUDANGA (SM/16293), KASHIPUR (SM/16297), PATULI (SM/09718) & PARULIA (SM/09719) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | 2202/BWD | 13/06/2024 | 631 | MONDAL PRECISION PVT LTD | 570 | 78.03 | 41.07 | 2
535 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF JHAUDANGA (PART-B) PIPED WATER SUPPLY SCHEME , SM/16293 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of JHAUDANGA( Part-B)[ PURBASTHALI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4475/CMD | 05/10/2023 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 24.19 | 0 | 0 | 100
536 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF PURBASAHAPUR PIPED WATER SUPPLY SCHEME , SM/16193 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of PURBA SAHAPUR[KALNA-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4477/CMD | 05/10/2023 | 30 | DUTTA ENTERPRISE | 24.4 | 0 | 0 | 0
537 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASAHAPUR PIPED WATER SUPPLY SCHEME , SM/16193 | Augmentation | Augmentation of PURBA SAHAPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Kalna - II Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | 3273/BWD | 28/07/2023 | 60 | PARTHA PRATIM ACHARYA | 21.94 | 15.27 | 69.59 | 80
538 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASAHAPUR PIPED WATER SUPPLY SCHEME , SM/16193 | Augmentation | Providing leftout FHTC at different location of Purba Sahapur Mouza under the command area of PURBA SAHAPUR PWSS (SM/16193) in order to declare Purba Sahapur village as Sajalgram under Kalna Sub Division, PHE. Dte. | 912/BWD | 10/03/2025 | 15 | SAYAK DEY | 5.79 | 0 | 0 | 100
539 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF SONARUDRA PIPED WATER SUPPLY SCHEME , SM/16349 | Retrofitting | Augmentation of SONARUDRA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jivan Mission of Purbasthali - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | 2442/BWD | 30/05/2023 | 60 | ROHAN MONDAL | 43.32 | 34.66 | 80.02 | 20
540 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF SONARUDRA PIPED WATER SUPPLY SCHEME , SM/16349 | Retrofitting | Sinking of additional Tube Well, construction of pump house & boundary wall & laying interconnection of SONARUDRA Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (PP Site- Shyambati Baidyapur). | 5295/BWD | 01/12/2023 | 60 | HI-LIGHT ELECTRONICS | 27.37 | 14.41 | 52.66 | 60
541 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF SONARUDRA PIPED WATER SUPPLY SCHEME , SM/16349 | Retrofitting | Laying of 140 mm dia HDPE Pipeline from Sonarudra Head Work Site more to upto Shyambati & Baidyapur more (Sec 34-2-3-6-10-12-14-16-16A-16B) of SONARUDRA W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 1486/BWD | 14/03/2022 | 30 | HAMID SK | 18.85 | 10.47 | 100 | 100
542 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF SONARUDRA PIPED WATER SUPPLY SCHEME , SM/16349 | Retrofitting | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 14 Nos. Piped W/S. Schemes under Purbasthali I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3017/BWD | 05/08/2024 | 75 | HORIZEN | 38 | 3.24 | 100 | 100
543 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF SONARUDRA PIPED WATER SUPPLY SCHEME , SM/16349 | Retrofitting | Different Types of work involved in connection with Augmentation of SONARUDRA (SM/16349) & KACHUA (SM/13497) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2430/BWD | 27/06/2024 | 480 | R.G. INFRASTRUCTURE | 240.7 | 23.03 | 52.34 | 2
544 | PURBA BARDHAMAN | Burdwan Division | NERAGOHALIA PIPED WATER SUPPLY SCHEME , SM/16617 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 18.38 | 0 | 0 | 0
545 | PURBA BARDHAMAN | Burdwan Division | NERAGOHALIA PIPED WATER SUPPLY SCHEME , SM/16617 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 20.45 | 0 | 0 | 0
546 | PURBA BARDHAMAN | Burdwan Division | NERAGOHALIA PIPED WATER SUPPLY SCHEME , SM/16617 | New | Material Requisition To Resource Division | 5273/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
547 | PURBA BARDHAMAN | Burdwan Division | NERAGOHALIA PIPED WATER SUPPLY SCHEME , SM/16617 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch room, boundary walls with gates, land development, surface drains and internal pathways at different TW site for NERAGOHALIA Piped Water Supply Scheme under BURDWAN-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3493/BWD | 09/08/2023 | 365 | M/S ASHA CONSTRUCTION | 577.52 | 207.48 | 35.93 | 35
548 | PURBA BARDHAMAN | Central Mechanical | NERAGOHALIA PIPED WATER SUPPLY SCHEME , SM/16617 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
549 | PURBA BARDHAMAN | Central Mechanical | NERAGOHALIA PIPED WATER SUPPLY SCHEME , SM/16617 | New | Quotation for new service connection at NARAGOHALIA W/S Scheme PH-I. | BP-2023-24-321 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.28 | 0 | 0 | 0
550 | PURBA BARDHAMAN | Central Mechanical | NERAGOHALIA PIPED WATER SUPPLY SCHEME , SM/16617 | New | New service connection charges for Neragohalia PWSS TW-2 | BP-2023-24-391 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.09 | 0 | 0 | 0
551 | PURBA BARDHAMAN | Central Mechanical | NERAGOHALIA PIPED WATER SUPPLY SCHEME , SM/16617 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Neragohalia Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4003/CMD | 29/08/2023 | 30 | DUTTA ENTERPRISE | 28.98 | 0 | 0 | 60
552 | PURBA BARDHAMAN | Burdwan Division | NERAGOHALIA PIPED WATER SUPPLY SCHEME , SM/16617 | New | Restoration of Conc. road, Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for MAGRA, SANUI, SATGACHIA Zone-I & NARAGOHALIA PIPED WATER SUPPLY SCHEME, Block-Memari-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | 611/BWD | 11/02/2025 | 180 | M/S ASHA CONSTRUCTION | 354.13 | 0 | 0 | 25
553 | PURBA BARDHAMAN | Burdwan Division | BALIDANGA PIPE WATER SUPPLY SCHEME , SM/18315 | New | Material Requisition To Resource Division | 3871/BWD | 01/09/2023 | 0 | Resource Division | 88.34 | 0 | 0 | 0
554 | PURBA BARDHAMAN | Burdwan Division | BALIDANGA PIPE WATER SUPPLY SCHEME , SM/18315 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.45 | 0 | 0 | 0
555 | PURBA BARDHAMAN | Burdwan Division | BALIDANGA PIPE WATER SUPPLY SCHEME , SM/18315 | New | Material Requisition To Resource Division | 5097/BWD | 23/11/2023 | 0 | Resource Division | 19.96 | 0 | 0 | 0
556 | PURBA BARDHAMAN | Burdwan Division | BALIDANGA PIPE WATER SUPPLY SCHEME , SM/18315 | New | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. | 22/KTS | 05/01/2024 | 70 | AJIT SAMANTA | 0.9 | 0.3 | 100 | 100
557 | PURBA BARDHAMAN | Central Mechanical | BALIDANGA PIPE WATER SUPPLY SCHEME , SM/18315 | New | NEW SERVICE CONNECTION FOR BALIDANGA PWSS. | BP-2023-24-530 | 13/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.7 | 0 | 0 | 0
558 | PURBA BARDHAMAN | Central Mechanical | BALIDANGA PIPE WATER SUPPLY SCHEME , SM/18315 | New | NEW SERVICE CONNECTION FOR BALIDANGA PWSS. | BP-2023-24-531 | 13/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.76 | 0 | 0 | 0
559 | PURBA BARDHAMAN | Burdwan Division | BALIDANGA PIPE WATER SUPPLY SCHEME , SM/18315 | New | BALIDANGA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongolkote Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | 3439/BWD | 08/08/2023 | 967 | M/S S.S. ENTERPRISE | 567.39 | 242.94 | 42.82 | 27
560 | PURBA BARDHAMAN | Central Mechanical | BALIDANGA PIPE WATER SUPPLY SCHEME , SM/18315 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BALIDANGA Water Supply Scheme [ Block- MANGOLKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4146/CMD | 29/08/2023 | 563 | CHOUDHURY ENTERPRISE | 29.7 | 11.54 | 38.85 | 46
561 | PURBA BARDHAMAN | Central Mechanical | BALIDANGA PIPE WATER SUPPLY SCHEME , SM/18315 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
562 | PURBA BARDHAMAN | Central Mechanical | BALIDANGA PIPE WATER SUPPLY SCHEME , SM/18315 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Balidanga Water Supply Scheme [ BLOCK- Mangalkote ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 884/CMD | 26/03/2025 | 60 | M/S, S.S. ENTERPRISE. | 12.3 | 0 | 0 | 0
563 | PURBA BARDHAMAN | Burdwan Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/14977 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 5.77 | 0 | 0 | 0
564 | PURBA BARDHAMAN | Burdwan Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/14977 | New | Material Requisition To Resource Division | 4286/BWD | 29/09/2023 | 0 | Resource Division | 1.53 | 0 | 0 | 0
565 | PURBA BARDHAMAN | Burdwan Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/14977 | New | Material Requisition To Resource Division | 5101/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
566 | PURBA BARDHAMAN | Burdwan Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/14977 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BHAGABATIPUR, MACHKHARA & UDGARA Piped Water Supply Scheme under Raina ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] | 4386/BWD | 05/10/2023 | 365 | SK ALIM | 1378.97 | 251.83 | 49.06 | 55
567 | PURBA BARDHAMAN | Burdwan Division | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/14977 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-05-2024 to 31-07-2024) | 807/BSD | 29/04/2024 | 66 | PARVIN BEGAM | 0.85 | 0.28 | 99.58 | 100
568 | PURBA BARDHAMAN | Central Mechanical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/14977 | New | New electric connection for Bhagabatipur PWSS, PH-1 | BP-2023-24-343 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.15 | 0 | 0 | 0
569 | PURBA BARDHAMAN | Central Mechanical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/14977 | New | New Service connection for BHAGABATIPUR W/S Scheme PH No.-1 | BP-2023-24-312 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.93 | 0 | 0 | 0
570 | PURBA BARDHAMAN | Central Mechanical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/14977 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
571 | PURBA BARDHAMAN | Central Mechanical | BHAGABATIPUR PIPED WATER SUPPLY SCHEME , SM/14977 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bhagabatipur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4172/CMD | 29/08/2023 | 595 | SOUNAK ENTERPRISE | 29.71 | 0 | 0 | 90
572 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09873 | Augmentation | Preparation of DPR for augmentation of Radhanagar-Baghnapara W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | 214/KSD | 24/02/2022 | 21 | ROY CHOUDHURI CONSTRUCTION | 2.96 | 0 | 0 | 1
573 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09873 | Augmentation | Preparation of DPR for augmentation of Radhanagar-Baghnapara W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | 214/KSD | 24/02/2022 | 21 | ROY CHOWDHURY ASSOCIATES | 2.96 | 2.95 | 100 | 0
574 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09873 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
575 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09873 | Augmentation | Material Requisition To Resource Division | 537/BWD | 27/01/2022 | 0 | Resource Division | 17.54 | 0 | 0 | 0
576 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09873 | Augmentation | Material Requisition To Resource Division | 1544/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
577 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09873 | Augmentation | Material Requisition To Resource Division | 1375/BWD | 09/03/2022 | 0 | Resource Division | 4.85 | 0 | 0 | 0
578 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09873 | Augmentation | Material Requisition To Resource Division | 3277/BWD | 29/07/2022 | 0 | Resource Division | 65.16 | 0 | 0 | 0
579 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09873 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 3 at Augumentation of Radhanagar Baghnapara Water Supply Scheme [ BLOCK- Kalna-I ]under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1625/CMD | 15/03/2024 | 30 | JOYGURU ENTERPRISE | 12.31 | 0 | 0 | 0
580 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09873 | Augmentation | Augmentation of Radhanagar Baghnapara Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 200 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation & repairing of existing 180 cum OHR with repairing of switch rooms, boundary walls at different TW site under Kalna-I Block, District:- Purba-Burdwan | 3511/BWD | 10/08/2023 | 598 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 458.55 | 165.42 | 36.08 | 70
581 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RADGANAGAR BAGHANAPARA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09873 | Augmentation | Sinking of additional Tube Well, construction of pump house & boundary wall & laying interconnection of RADHANAGAR BAGHNAPARA Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (PP Site- Khaspur Karim Gachhi). | 5483/BWD | 13/12/2023 | 416 | MUKHERJEE ENTERPRISE | 26.91 | 14.32 | 53.21 | 45
582 | PURBA BARDHAMAN | Burdwan Division | BIJUR PIPED WATER SUPPLY SCHEME , SM/18605 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 3.36 | 0 | 0 | 0
583 | PURBA BARDHAMAN | Burdwan Division | BIJUR PIPED WATER SUPPLY SCHEME , SM/18605 | New | Material Requisition To Resource Division | 5116/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
584 | PURBA BARDHAMAN | Central Mechanical | BIJUR PIPED WATER SUPPLY SCHEME , SM/18605 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
585 | PURBA BARDHAMAN | Central Mechanical | BIJUR PIPED WATER SUPPLY SCHEME , SM/18605 | New | New service connection for BIJUR PWSS TW 2. | BP-2023-24-526 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.86 | 0 | 0 | 0
586 | PURBA BARDHAMAN | Central Mechanical | BIJUR PIPED WATER SUPPLY SCHEME , SM/18605 | New | New service connection at Bijur PWSS PH-1 | BP-2023-24-469 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.66 | 0 | 0 | 0
587 | PURBA BARDHAMAN | Central Mechanical | BIJUR PIPED WATER SUPPLY SCHEME , SM/18605 | New | New service connection for BIJUR PWSS TW 1. | BP-2023-24-527 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.7 | 0 | 0 | 0
588 | PURBA BARDHAMAN | Central Mechanical | BIJUR PIPED WATER SUPPLY SCHEME , SM/18605 | New | New service connection at Bijur PWSS PH-2 | BP-2023-24-470 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.63 | 0 | 0 | 0
589 | PURBA BARDHAMAN | Burdwan Division | BIJUR PIPED WATER SUPPLY SCHEME , SM/18605 | New | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1116/BWD | 03/04/2025 | 120 | SOFIQUL ISLAM | 176.89 | 0 | 0 | 0
590 | PURBA BARDHAMAN | Central Mechanical | BIJUR PIPED WATER SUPPLY SCHEME , SM/18605 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bijur Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4024/CMD | 29/08/2023 | 30 | MS DAS ELECTRIC CO | 29.4 | 23.77 | 97.52 | 95
591 | PURBA BARDHAMAN | Central Mechanical | CHANCHAL PIPED WATER SUPPLY SCHEME , SM/18609 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at CHANCHAL Water Supply Scheme [ Block- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4078/CMD | 29/08/2023 | 30 | UNIVERSAL ENTERPRISES | 44.1 | 0 | 0 | 0
592 | PURBA BARDHAMAN | Burdwan Division | CHANCHAL PIPED WATER SUPPLY SCHEME , SM/18609 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.41 | 0 | 0 | 0
593 | PURBA BARDHAMAN | Burdwan Division | CHANCHAL PIPED WATER SUPPLY SCHEME , SM/18609 | New | Material Requisition To Resource Division | 4294/BWD | 29/09/2023 | 0 | Resource Division | 1.69 | 0 | 0 | 0
594 | PURBA BARDHAMAN | Burdwan Division | CHANCHAL PIPED WATER SUPPLY SCHEME , SM/18609 | New | Material Requisition To Resource Division | 4922/BWD | 10/11/2023 | 0 | Resource Division | 41.11 | 0 | 0 | 0
595 | PURBA BARDHAMAN | Central Mechanical | CHANCHAL PIPED WATER SUPPLY SCHEME , SM/18609 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
596 | PURBA BARDHAMAN | Central Mechanical | CHANCHAL PIPED WATER SUPPLY SCHEME , SM/18609 | New | New Service connection for Chanchal PWSS TW-1. | BP-2023-24-476 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.26 | 0 | 0 | 0
597 | PURBA BARDHAMAN | Central Mechanical | CHANCHAL PIPED WATER SUPPLY SCHEME , SM/18609 | New | New Service connection for Chanchal PWSS TW-2. | BP-2023-24-477 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 14.29 | 0 | 0 | 0
598 | PURBA BARDHAMAN | Burdwan Division | CHANCHAL PIPED WATER SUPPLY SCHEME , SM/18609 | New | Shifting of 11KV HTOH Line for construction of new OHR of Chanchal pwss under Burdwan Division, PHE Dte. [Ref ID-860319929, App ID-100000124989, dt.-10/12/2024] | 1172/JJM | 17/12/2024 | 0 | WBSEDCL | 7 | 0 | 0 | 0
599 | PURBA BARDHAMAN | Burdwan Division | CHANCHAL PIPED WATER SUPPLY SCHEME , SM/18609 | New | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related (schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-05-2025 to 31-07-2025) | 960/BSD | 30/04/2025 | 66 | PARVIN BEGAM | 0.85 | 0 | 0 | 100
600 | PURBA BARDHAMAN | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME , SM/18482 | New | Material Requisition To Resource Division | 3861/BWD | 01/09/2023 | 0 | Resource Division | 15.75 | 0 | 0 | 0
601 | PURBA BARDHAMAN | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME , SM/18482 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 15 | 0 | 0 | 0
602 | PURBA BARDHAMAN | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME , SM/18482 | New | Material Requisition To Resource Division | 5087/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
603 | PURBA BARDHAMAN | Central Mechanical | DIGHRA PIPED WATER SUPPLY SCHEME , SM/18482 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
604 | PURBA BARDHAMAN | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME , SM/18482 | New | Material Requisition To Resource Division | 4113/BWD | 25/11/2024 | 0 | Resource Division | 17.04 | 0 | 0 | 0
605 | PURBA BARDHAMAN | Central Mechanical | DIGHRA PIPED WATER SUPPLY SCHEME , SM/18482 | New | NEW SERVICE CONNECTION FOR DIGHRA PWSS | BP-2023-24-556 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.16 | 0 | 0 | 0
606 | PURBA BARDHAMAN | Central Mechanical | DIGHRA PIPED WATER SUPPLY SCHEME , SM/18482 | New | New Service connection for Dighra W/S Scheme PH No.-I | BP-2023-24-322 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.03 | 0 | 0 | 0
607 | PURBA BARDHAMAN | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME , SM/18482 | New | DIGHRA Piped Water Supply Scheme with sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of 350 cum capacity RCC OHRs with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site under RAINA-II Block, District:- Purba Bardhaman [NEW SCHEME] | 3506/BWD | 10/08/2023 | 875 | M/S PIONEER CONSTRUCTION | 661.73 | 273.47 | 41.33 | 75
608 | PURBA BARDHAMAN | Central Mechanical | DIGHRA PIPED WATER SUPPLY SCHEME , SM/18482 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at DIGHRA Water Supply Scheme [ Block- RAINA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4113/CMD | 29/08/2023 | 642 | GOENKA ENTERPRISE | 28.98 | 0 | 0 | 85
609 | PURBA BARDHAMAN | Burdwan Division | DIGHRA PIPED WATER SUPPLY SCHEME , SM/18482 | New | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at KONARPUR (3rd TW site) under DIGHRA Piped Water Supply Scheme under RAINA-II Block, District:- Purba-Bardhaman. | 1212/BWD | 21/04/2025 | 45 | A.R. TRADERS | 13.63 | 0 | 0 | 100
610 | PURBA BARDHAMAN | Burdwan Division | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.39 | 0 | 0 | 0
611 | PURBA BARDHAMAN | Burdwan Division | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | Material Requisition To Resource Division | 3847/BWD | 01/09/2023 | 0 | Resource Division | 460.56 | 0 | 0 | 0
612 | PURBA BARDHAMAN | Central Drilling | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | Construction of Tube Well (300 MM x 200 MM x Depth 500 Mtr) for Shilla W/S Scheme(T/W -I) Zone-IV, Block- Galsi-I, Purba Bardhaman District by Central Drilling Division, P.H. Engineering Dte. | 2236/CDD | 11/03/2024 | 60 | SATYAJIT GHOSH | 39.72 | 0 | 0 | 0
613 | PURBA BARDHAMAN | Burdwan Division | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. | 5324/BWD | 01/12/2023 | 120 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 21.53 | 100 | 100
614 | PURBA BARDHAMAN | Burdwan Division | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | Material Requisition To Resource Division | 207/BWD | 10/01/2024 | 0 | Resource Division | 57.55 | 0 | 0 | 0
615 | PURBA BARDHAMAN | Central Mechanical | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | Quotation for new service connection at Shilla PWSS (Naba Khanda) Zone-I. | BP-2024-25-290 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.26 | 0 | 0 | 0
616 | PURBA BARDHAMAN | Central Mechanical | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | Quotation for new service connection Shilla PWSS TW No. 3. | BP-2024-25-291 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.32 | 0 | 0 | 0
617 | PURBA BARDHAMAN | Central Mechanical | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | Providing Mechanical/Electrical equipment with all ancillaries and auxiliaries including intake (Low lift) pumping machineries, illumination arrangement of Shilla Sub-Surface Based Piped Water Supply Scheme under Purba Bardhaman District PHE Dte. | 481/CMD | 06/02/2025 | 75 | JAL PRAVAHIKA PVT LTD | 0 | 0 | 0 | 0
618 | PURBA BARDHAMAN | Central Mechanical | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for OHR SITE of Zone-1, 2, 3 & 4 at SHILLA Water Supply Scheme [ BLOCK- Galsi-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3101/CMD | 11/12/2024 | 200 | S.K. ELECTRICALS | 50.24 | 0 | 0 | 46
619 | PURBA BARDHAMAN | Durgapur W/S Division | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | Formal Work Order for Laying of Rising Main including Jack Pushing and construction of Pipe Carring Bridge with Pipe supporting structure under SHILLA PIPED W/S SCHMEME under Durgapur W/S Division, PHE Dte. | 1500/DWSD | 05/11/2024 | 422 | M/S S. CHOUDHURY | 1099 | 136.91 | 12.46 | 45
620 | PURBA BARDHAMAN | Durgapur W/S Division | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | Acceptance cum Formal Work Order for the work of Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Junior Engineers for the office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.08.2024 to 31.01.2025 (6 Months) | 1108/DWSD | 01/08/2024 | 184 | SIDDHARTH ENTERPRISE | 0.82 | 2.39 | 290.81 | 0
621 | PURBA BARDHAMAN | Durgapur W/S Division | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | CONTINUTION ORDER FOR Hiring of LUXURY Disel Ambassador Car (Inspection Vehicle) for using of the Junior Engineers for the Office of the EE, Durgapur W/S Division, PHE Dte at Nababhat, Fagupur, Purba Bardhaman for the period of 01.02.2025 to 30.04.2025. (VEHICLE NO WB/04H-5935) | 184/DWSD | 28/01/2025 | 90 | SIDDHARTH ENTERPRISE | 0.41 | 1.2 | 290.58 | 33
622 | PURBA BARDHAMAN | Durgapur W/S Division | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | Acceptance cum Formal Work Order for Preparation and Submission of Structural Design Calculation (Civil) & Structural drawing of Proposed CWR with M.S Structural Pump House over cwr, WBSEDCL Mettering Room and - PDB Room -2 Nos, Transformer yeard -2 nos, Chlorin Room -1 No with General Arrangement Drawing of InternalRoad - Drain & necessary Soil investigation at Intake Site of "SHILLA (Zone-I, II, III &IV ) PWSS under Durgapur W/s Division, PHE Dte. | 1606/DWSD | 26/11/2024 | 45 | M/S S. CHOUDHURY | 9.48 | 0 | 0 | 100
623 | PURBA BARDHAMAN | Durgapur W/S Division | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | Acceptance cum Formal Work Order for Design Engineering Services of Survey, General arrangement drawing, Pile foundation design and drawings, Pipe Pedestal and BOM, Structural design design and drawing, Fabrication drawings for 26 Numbers different dia meter pipe crossing Pipe Bridge at "PURANGAN (Zone-I, II, III), 11 Nos. Mouzas under PURSHA and UCHCHGRAM, SHILLA (Zone-I, II, III, IV), TAHER PUR (Zone-I, II, III) and KHANO (Zone-I and II) sites under Durgapur W/S Division,PHE Dte. | 1058/DWSD | 25/07/2024 | 270 | ASTER CONSULTANCY | 47.43 | 2.77 | 13.91 | 70
624 | PURBA BARDHAMAN | Durgapur W/S Division | SHILLA PIPED WATER SUPPLY SCHEME , SM/18344 | New | Formal Work Order for the work of Sinking of 3 nos 300 x 200mm dia Tube Well-150 mtr and 10 Nos 200 x 200 mm dia River Bank Tube Well- 51 mtr with Construction of Pump House Cum Switch Room Chlorine Room under SHILLA PWSS (JJM) Block- Galsi-I, Distric- Purba Bardhaman under Durgapur W/S Division, PHE Dte | 885/DWSD | 26/06/2024 | 120 | M/S S. CHOUDHURY | 120.44 | 31.34 | 20.94 | 100
625 | PURBA BARDHAMAN | Burdwan Division | KASIGRAM PIPE WATER SUPPLY SCHEME , SM/18367 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.67 | 0 | 0 | 0
626 | PURBA BARDHAMAN | Burdwan Division | KASIGRAM PIPE WATER SUPPLY SCHEME , SM/18367 | New | Material Requisition To Resource Division | 3855/BWD | 01/09/2023 | 0 | Resource Division | 68.67 | 0 | 0 | 0
627 | PURBA BARDHAMAN | Burdwan Division | KASIGRAM PIPE WATER SUPPLY SCHEME , SM/18367 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAGHTONA, & KASIGRAM Piped Water Supply Scheme under Katwa ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3199/BWD | 24/07/2023 | 1257 | MANASH GHOSH | 1161.82 | 610.45 | 91.55 | 95
628 | PURBA BARDHAMAN | Central Mechanical | KASIGRAM PIPE WATER SUPPLY SCHEME , SM/18367 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
629 | PURBA BARDHAMAN | Central Mechanical | KASIGRAM PIPE WATER SUPPLY SCHEME , SM/18367 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KASIGRAM Water Supply Scheme [ Block-KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4144/CMD | 29/08/2023 | 492 | M/S. SWAPAN BANERJEE | 45.09 | 37.53 | 100 | 90
630 | PURBA BARDHAMAN | Burdwan Division | KASIGRAM PIPE WATER SUPPLY SCHEME , SM/18367 | New | Material Requisition To Resource Division | 4104/BWD | 25/11/2024 | 0 | Resource Division | 6.95 | 0 | 0 | 0
631 | PURBA BARDHAMAN | Central Mechanical | KASIGRAM PIPE WATER SUPPLY SCHEME , SM/18367 | New | New service connection for Kasigram PWSS PH-1. | BP-2023-24-616 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.69 | 0 | 0 | 0
632 | PURBA BARDHAMAN | Central Mechanical | KASIGRAM PIPE WATER SUPPLY SCHEME , SM/18367 | New | New service connection for Kasigram PWSS PH-3. | BP-2023-24-618 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.73 | 0 | 0 | 0
633 | PURBA BARDHAMAN | Central Mechanical | KASIGRAM PIPE WATER SUPPLY SCHEME , SM/18367 | New | New service connection for Kashigram PWSS PH-2. | BP-2023-24-617 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.06 | 0 | 0 | 0
634 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS PART-II at different Blocks under CentralMechanical Division,PHED District Purba Bardhaman , SM/18991 | Solarisation | WBSEDCL solar quotation for Sajiara PH-1, PWSS. | BP-2024-25-64 | 06/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.31 | 0 | 0 | 0
635 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS PART-II at different Blocks under CentralMechanical Division,PHED District Purba Bardhaman , SM/18991 | Solarisation | Application for solar power connection at Nabagram PWSS TW-2. | BP-2024-25-414 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
636 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS PART-II at different Blocks under CentralMechanical Division,PHED District Purba Bardhaman , SM/18991 | Solarisation | Quotation for new electric solar service connection at Kaity PWSS TW-1 | BP-2024-25-399 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.22 | 0 | 0 | 0
637 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS PART-II at different Blocks under CentralMechanical Division,PHED District Purba Bardhaman , SM/18991 | Solarisation | Quotation for solar power at Bhatar Z-I TW-1 PWSS | BP-2024-25-330 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
638 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS PART-II at different Blocks under CentralMechanical Division,PHED District Purba Bardhaman , SM/18991 | Solarisation | Quotation for installation of solar plant at Natu W/S Scheme for PH-1 | BP-2024-25-329 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.22 | 0 | 0 | 0
639 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS PART-II at different Blocks under CentralMechanical Division,PHED District Purba Bardhaman , SM/18991 | Solarisation | Quotation for installation of Solar Plant (Net Billing) at Tendul W/S Scheme PH-1. | BP-2024-25-328 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.22 | 0 | 0 | 0
640 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS PART-II at different Blocks under CentralMechanical Division,PHED District Purba Bardhaman , SM/18991 | Solarisation | Quotation for installation of Solar Plant (Net billing) at Murga W/S Scheme PH-2. | BP-2024-25-327 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.22 | 0 | 0 | 0
641 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS PART-II at different Blocks under CentralMechanical Division,PHED District Purba Bardhaman , SM/18991 | Solarisation | Application for solar power connection at Raipur PWSS TW-1. | BP-2024-25-415 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
642 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS PART-II at different Blocks under CentralMechanical Division,PHED District Purba Bardhaman , SM/18991 | Solarisation | WBSEDCL Solar quotation for Lohana PH-1, PWSS. | BP-2024-25-65 | 06/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.31 | 0 | 0 | 0
643 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS PART-II at different Blocks under CentralMechanical Division,PHED District Purba Bardhaman , SM/18991 | Solarisation | Quotation for new Solar service connection at Khandaghosh PWSS TW-1 | BP-2024-25-400 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.22 | 0 | 0 | 0
644 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS PART-II at different Blocks under CentralMechanical Division,PHED District Purba Bardhaman , SM/18991 | Solarisation | Application for solar power connection at Rasulpur PWSS TW-1. | BP-2024-25-416 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
645 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS PART-II at different Blocks under CentralMechanical Division,PHED District Purba Bardhaman , SM/18991 | Solarisation | Solarisation of WBSEDCL energised electrical installations at PWSS of different Blocks in the district Purba Bardhaman under Central Mechanical Division, PHE Dte. | 4675/CMD | 02/11/2023 | 182 | A K INDUSTRIES | 85.51 | 0 | 0 | 100
646 | PURBA BARDHAMAN | Burdwan Division | BARADOBA PIPED WATER SUPPLY SCHEME , SM/18230 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.17 | 0 | 0 | 0
647 | PURBA BARDHAMAN | Burdwan Division | BARADOBA PIPED WATER SUPPLY SCHEME , SM/18230 | New | Material Requisition To Resource Division | 3849/BWD | 01/09/2023 | 0 | Resource Division | 1.22 | 0 | 0 | 0
648 | PURBA BARDHAMAN | Burdwan Division | BARADOBA PIPED WATER SUPPLY SCHEME , SM/18230 | New | Material Requisition To Resource Division | 4933/BWD | 10/11/2023 | 0 | Resource Division | 16.68 | 0 | 0 | 0
649 | PURBA BARDHAMAN | Central Mechanical | BARADOBA PIPED WATER SUPPLY SCHEME , SM/18230 | New | New service connection charges for Baradoba PWSS TW-1 | BP-2023-24-129 | 21/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.34 | 0 | 0 | 0
650 | PURBA BARDHAMAN | Durgapur W/S Division | BARADOBA PIPED WATER SUPPLY SCHEME , SM/18230 | New | Acceptance cum Formal Work Order for BARADOBA Piped Water Supply Scheme with FHTC ,Road restoration under AUSGRAM-II Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte | 1619/DWSD | 26/11/2024 | 60 | SAIKAT RAY | 15.24 | 0 | 0 | 0
651 | PURBA BARDHAMAN | Durgapur W/S Division | BARADOBA PIPED WATER SUPPLY SCHEME , SM/18230 | New | Material Requisition To Resource Division | 1724/R/DWSD | 10/12/2024 | 0 | Resource Division | 0.77 | 0 | 0 | 0
652 | PURBA BARDHAMAN | Central Mechanical | BARADOBA PIPED WATER SUPPLY SCHEME , SM/18230 | New | New service connection charges for Baradoba PWSS TW-2 | BP-2023-24-334 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.77 | 0 | 0 | 0
653 | PURBA BARDHAMAN | Central Mechanical | BARADOBA PIPED WATER SUPPLY SCHEME , SM/18230 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at BARADOBA Water Supply Scheme [Block - AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3699/CMD | 07/08/2023 | 999 | M/S, S.DAS AND ENTERPRISE. | 21.33 | 0 | 0 | 90
654 | PURBA BARDHAMAN | Burdwan Division | BARADOBA PIPED WATER SUPPLY SCHEME , SM/18230 | New | BARADOBA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under AUSHGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 2677/BWD | 08/06/2023 | 446 | THREE MAA ENTERPRISE | 109.1 | 102.79 | 94.81 | 100
655 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL , SM/18439 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of SIMLON (ZONE-I & II) [KALNA-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 259/CMD | 19/01/2024 | 30 | DUTTA ENTERPRISE | 24.4 | 0 | 0 | 0
656 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL , SM/18439 | Augmentation | Illumination arrangement and miscellaneous works at Simlon water supply scheme under Kalna-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2781/CMD | 01/10/2024 | 60 | SUDIPTA GHOSH | 9.5 | 0 | 0 | 0
657 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL , SM/18439 | Augmentation | Laying of rising main along with crossing of pipe line by HDD/Jack pushing method due to widening of Bardhaman-Kalna Road via Simlon in connection with Augmentation of SIMLON Piped Water Supply Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte. | 2070/BWD | 07/06/2024 | 120 | MANASH GHOSH | 199.36 | 199.36 | 100 | 100
658 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL , SM/18439 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 11 Nos. Piped W/S. Schemes under Kalna I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3015/BWD | 05/08/2024 | 60 | HORIZEN | 29.6 | 11.1 | 100 | 10
659 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL , SM/18439 | Augmentation | Quotation from WBSEDCL for Shifting of 33 KV & LTOH line at Briddhapara village against 1st T.W. of Simlon w/s scheme. | 270/JJM | 21/05/2024 | 0 | WBSEDCL | 14.29 | 0 | 0 | 0
660 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL , SM/18439 | Augmentation | Quotation for new service connection at Simlon Zone-2 PWSS TW-1. | BP-2024-25-411 | 11/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.61 | 0 | 0 | 0
661 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL , SM/18439 | Augmentation | AUGMENTATION OF SIMLON Piped Water Supply Scheme with sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of 500 cum capacity RCC OHRs with 20.0 mtr. Staging height including soil investigation (2 Nos.) & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site OF ZONE-I & ZONE-II under KALNA-I Block, District:- Purba Bardhaman. | 3442/BWD | 08/08/2023 | 603 | MANASH GHOSH | 1406.99 | 980.63 | 69.7 | 60
662 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SIMLON PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK KALNA I PURBA BARDHAMAN WEST BENGAL , SM/18439 | Augmentation | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
663 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/18422 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 19.69 | 0 | 0 | 0
664 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/18422 | New | Material Requisition To Resource Division | 3971/BWD | 08/09/2023 | 0 | Resource Division | 129.95 | 0 | 0 | 0
665 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/18422 | New | New service connection charges for Ujna PWSS TW-2 | BP-2023-24-235 | 06/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.34 | 0 | 0 | 0
666 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/18422 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at UJNA Water Supply Scheme [ Block- MONTESWAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4074/CMD | 29/08/2023 | 30 | CONCORD ENGINEERING | 44.42 | 35.37 | 79.62 | 90
667 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/18422 | New | Material Requisition To Resource Division | 316/BWD | 24/01/2024 | 0 | Resource Division | 47.08 | 0 | 0 | 0
668 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/18422 | New | New service connection charges for Ujna PWSS TW-3 | BP-2023-24-406 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.7 | 0 | 0 | 0
669 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/18422 | New | New service connection charges for Ujna PWSS TW-1 | BP-2023-24-406 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.99 | 0 | 0 | 0
670 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/18422 | New | ADDITIONAL QUOTATION FOR NEW SERVICE CONNECTION FOR UJNA PWSS PH-3 | BP-2024-25-88 | 15/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.3 | 0 | 0 | 0
671 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/18422 | New | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3105/CMD | 11/12/2024 | 60 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0 | 0
672 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR UJNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/18422 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
673 | PURBA BARDHAMAN | Burdwan Division | AMUL PIPED WATER SUPPLY SCHEME , SM/18458 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 4.61 | 0 | 0 | 0
674 | PURBA BARDHAMAN | Burdwan Division | AMUL PIPED WATER SUPPLY SCHEME , SM/18458 | New | Material Requisition To Resource Division | 3851/BWD | 01/09/2023 | 0 | Resource Division | 43.58 | 0 | 0 | 0
675 | PURBA BARDHAMAN | Central Mechanical | AMUL PIPED WATER SUPPLY SCHEME , SM/18458 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
676 | PURBA BARDHAMAN | Burdwan Division | AMUL PIPED WATER SUPPLY SCHEME , SM/18458 | New | Material Requisition To Resource Division | 4106/BWD | 25/11/2024 | 0 | Resource Division | 14.47 | 0 | 0 | 0
677 | PURBA BARDHAMAN | Central Mechanical | AMUL PIPED WATER SUPPLY SCHEME , SM/18458 | New | Quotation for new service connection at Amul PWSS PH-3 | BP-2024-25-207 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.67 | 0 | 0 | 0
678 | PURBA BARDHAMAN | Central Mechanical | AMUL PIPED WATER SUPPLY SCHEME , SM/18458 | New | New Service connection for Amul PWSS TW-2 | BP-2023-24-465 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.77 | 0 | 0 | 0
679 | PURBA BARDHAMAN | Central Mechanical | AMUL PIPED WATER SUPPLY SCHEME , SM/18458 | New | New Service connection for Amul PWSS TW-1 | BP-2023-24-464 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.91 | 0 | 0 | 0
680 | PURBA BARDHAMAN | Burdwan Division | AMUL PIPED WATER SUPPLY SCHEME , SM/18458 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMUL & AURIA Piped Water Supply Scheme under Katwa ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3198/BWD | 24/07/2023 | 1257 | MANASH GHOSH | 1418.89 | 642.87 | 91.71 | 48
681 | PURBA BARDHAMAN | Central Mechanical | AMUL PIPED WATER SUPPLY SCHEME , SM/18458 | New | Hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte ,wef : 01/ 09/ 20 24 to 31/10/2024. | 528/DIC/BMSD(D) | 23/08/2024 | 61 | SUBRATA BHADRA | 0.81 | 0.74 | 91.54 | 0
682 | PURBA BARDHAMAN | Central Mechanical | AMUL PIPED WATER SUPPLY SCHEME , SM/18458 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at AMUL Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4083/CMD | 29/08/2023 | 615 | JAL PRAVAHIKA PVT LTD | 44.4 | 11.74 | 31.76 | 31
683 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  | 21/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
684 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Payment for supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 934/DW | 31/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
685 | PURBA BARDHAMAN | Central Drilling | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Providing drilling crew and other allied works for construction of tube well (300mm x 200mm x 120 mtrs. depth) by utilising Departmental machineries for Bhatar W/S Scheme (Z-II) Bhatar block under Purba bardhaman district, CDD, PHE Dte. | 64/CDD | 06/04/2023 | 30 | C.M. ENTERPRISE | 9.91 | 8.31 | 83.8 | 0
686 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bhatar Piped Water Supply Scheme at Kapshar, Bamsor & Belenda (3nos) Village (Mouza) under Burwan Division, PHE Dte. | 3301/BWD | 15/06/2021 | 60 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 141.14 | 137.29 | 100 | 1
687 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bhatar Piped Water Supply Scheme at Bhatar, Kantar, Kulchanda, Kulnagar, Palar, Satkhali & Chandipur (7nos) Village (Mouza) under Burwan Division, PHE Dte. | 3300/BWD | 15/06/2021 | 60 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 143.17 | 215.32 | 168.76 | 1
688 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS at Bhatar Alinagar for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte.[Gr.-G] | 721/DSD | 17/12/2021 | 30 | DHIRENDRANATH SOM | 4.69 | 4.68 | 100 | 1
689 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS at Vivekanandapally for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-F] | 720/DSD | 17/12/2021 | 30 | DHIRENDRANATH SOM | 2.24 | 2.21 | 100 | 1
690 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Extension of uPVC pipe line of LDS at Kalpukur Dakshin Para to Palar Lal para for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-H] | 722/DSD | 17/12/2021 | 30 | DHIRENDRANATH SOM | 1.99 | 1.99 | 100 | 1
691 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS at Bhatar Maldanga road to Kalpukur Purbapar for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-I] | 723/DSD | 17/12/2021 | 30 | DHIRENDRANATH SOM | 4.26 | 3.7 | 100 | 1
692 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Sinking of additional 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell Site for Augmentation of BHATAR (Zone-I) Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | 2240/BWD | 02/05/2022 | 45 | AUXILIARY TUBE WELL DRILLERS | 28.54 | 20.72 | 100 | 1
693 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Retrofitting of RCC Elevated Reservoir (Capacity 300 cum) by shortcreting, Guniting etc. in connection with Augmentation of Bhatar w/s scheme (Zone-I) under Burdwan Division, PHE Dte. | 1793./BWD | 26/02/2021 | 45 | LAGNAJITA & CO. | 20.57 | 0 | 0 | 1
694 | PURBA BARDHAMAN | Central Mechanical | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 4 at Augmentation of Bhatar (Zone - I) (Bamsor) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1311/CMD | 22/03/2023 | 30 | SRI KRISHNA NIRMAN | 11.88 | 10.93 | 100 | 99
695 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Providing Left-Out FHTC to Katari Habitation within Bhatar Zone-II PWSS, within Durgapur (Burdwan North) Sub-Division, PHE Dte, under Burdwan Division, PHE Dte. | 556/DSD | 20/07/2023 | 30 | BIPLAB SAMANTA | 3.98 | 3.98 | 100 | 100
696 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Quotation of Bhatar water supply scheme, Zone-II, PHE Dte. [Quotation No.-5003600235/Quot/03, dt.-10/02/2023] | 1168/JJM | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.37 | 0 | 0 | 0
697 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Quotation of new connection charges for Bhatar (Zone-I) water supply scheme. P.H. No.-4 | 942/JJM/22-23 | 09/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.67 | 0 | 0 | 0
698 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Sinking of 200 mm dia River Bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Norja village Block -Bhatar, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-C] | 496/DSD | 12/08/2022 | 21 | DHIRENDRANATH SOM | 4.35 | 4.35 | 100 | 100
699 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS at Kapshor village for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-2] | 728/DSD | 30/12/2022 | 21 | DHIRENDRANATH SOM | 0.95 | 0.95 | 100 | 100
700 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS at Belenda Purbapara for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-03] | 729/DSD | 30/12/2022 | 21 | DHIRENDRANATH SOM | 0.95 | 0.95 | 100 | 100
701 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS at Bamshor and Belenda Purbapara for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-04] | 730/DSD | 30/12/2022 | 21 | DHIRENDRANATH SOM | 0.96 | 0.96 | 100 | 100
702 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS at Balsidanga village for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-05] | 731/DSD | 30/12/2022 | 21 | DHIRENDRANATH SOM | 0.89 | 0.89 | 100 | 100
703 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Providing Left-Out FHTC to Pallar Habitation within Bhatar Zone-I PWSS, within Durgapur (Burdwan North) Sub-Division, PHE Dte, under Burdwan Division, PHE Dte. | 555/DSD | 20/07/2023 | 30 | TARAMA AGENCY | 4.22 | 4.22 | 100 | 100
704 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Laying of UPVC pipeline in Pallar habitation (Palar Asram Para North side) with Bhatar Zone-I PWSS within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | 907/DSD | 15/12/2023 | 45 | PAPRI HAZRA | 0.8 | 0.77 | 100 | 100
705 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Laying of UPVC pipeline in Pallar habitation (Palar Asram Para South side) with Bhatar Zone-I PWSS within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | 908/DSD | 15/12/2023 | 45 | TARAMA AGENCY | 0.39 | 0.39 | 100 | 100
706 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Providing Left Out FHTC to Sansotosh Sayar Par within Bhatar Zone-II PWSS WITHIN Durgapur (Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | 240/DSD | 12/03/2024 | 30 | BIPLAB SAMANTA | 0.94 | 0.83 | 100 | 100
707 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Providing Left Out FHTC to Area Adjacent to Railway Station within Bhatar Zone-II PWSS WITHIN Durgapur (Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | 241/DSD | 12/03/2024 | 30 | BIPLAB SAMANTA | 0.95 | 0.79 | 100 | 100
708 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Laying of UPVC pipeline in Katari Habitation within Bhatar Zone- II PWSS WITHIN Durgapur (Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | 239/DSD | 12/03/2024 | 30 | BIPLAB SAMANTA | 0.56 | 0.52 | 100 | 100
709 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Providing Left Out FHTC to Ashram Paschimpara within Bhatar Zone-I PWSS WITHIN Durgapur (Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | 270/DSD | 15/03/2024 | 30 | PAPRI HAZRA | 0.92 | 0.77 | 100 | 100
710 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design and drawings of overall LDS for Bhatar Piped Water Supply Scheme Zone I & Zone II under Bhatar Block. | 3350/BWD | 11/09/2024 | 15 | HORIZEN | 5.23 | 5.23 | 100 | 100
711 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Quotation from WBSEDCL for load enhancement of Augmentation of Bhatar Zone-II (Kulnagar) w/s scheme for P.H.-6. | 1036/JJM | 25/10/2024 | 0 | WBSEDCL | 3.57 | 0 | 0 | 0
712 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Quotation of new service connection charges of Aug. of Bhatar (Zone-II) TW-6 water supply scheme under Burdwan Division, PHE Dte. | 1275/JJM | 18/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.53 | 0 | 0 | 0
713 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Land demarcation and preparation of sketch map including legal charges for different PWSS under JJM of Bhatar Block under Duragapur (Burdwan North) Sub-Division, P.H.E. DTE. [Part-A] | 157/DSD | 27/01/2025 | 180 | SHUBHRA KANTI GHOSH | 0.81 | 0 | 0 | 70
714 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Extension of UPVC pipe line of LDS near rail crossing at Balsidanga for providing FHTC of Bhatar and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-8] | 734/DSD | 30/12/2022 | 21 | DHIRENDRANATH SOM | 0.96 | 0 | 0 | 100
715 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Laying of connecting pipeline in between Tube Well to pipeline at Bamsore village for Bhatar Zone 1 Pipe Water Supply scheme in Bhatar Block under Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. | 1073/DSD | 10/12/2024 | 30 | TARAMA AGENCY | 1.07 | 0.88 | 100 | 100
716 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Supply of various D.I. Mechanical joints & specials for Aug. of BHATAR & Aug. of BALGONA Piped W/S. Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, PHE. Dte. [Part-B]. | 2828/BWD | 19/07/2024 | 216 | KEJRIWAL CASTINGS LIMITED | 4.82 | 0 | 0 | 100
717 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Supply of various D.I. Mechanical joints & specials for Aug. of BHATAR & Aug. of BALGONA Piped W/S. Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, PHE. Dte. [Part-C]. | 2832/BWD | 19/07/2024 | 225 | JINDAL SAW LTD. | 4.63 | 0 | 0 | 100
718 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Supply of various D.I. Mechanical joints & specials for Aug. of BHATAR & Aug. of BALGONA Piped W/S. Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, PHE. Dte. [Part-A]. | 2840/BWD | 19/07/2024 | 215 | ELECTROSTEEL CASTING LIMITED | 4.95 | 0 | 0 | 100
719 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of Bhatar Piped Water Supply Scheme Block-Bhatar , SM/08033 | Retrofitting | Laying Of UPVC Pipe Line in Pallar Daspara Near BusStand within Bhatar Zone-I PWSS Under Durgapur (Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | 477/DSD | 21/03/2025 | 20 | TARA MA AGENCY | 0.44 | 0 | 0 | 100
720 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mankar Piped Water Supply Scheme at Bagabanpur (Part), Budbud (Part) & Mallikpur (Part) Village (Mouza) under Burwan Division, PHE Dte. | 3372/BWD | 23/06/2021 | 60 | SAMRAT REALPROJECTS PRIVATE LIMITED | 79.3 | 67.49 | 85.11 | 1
721 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Providing Functional House Hold Tap connection (FHTC) from existing distribution system within the command area of MANKAR piped water supply scheme at Budbud (Part) village Budbud (Part) habitation (Mouza), Galsi-I Block under Burdwan Division, PHE Dte. | 547/BWD | 22/01/2021 | 30 | SAIKAT RAY | 22.24 | 44.47 | 200 | 1
722 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mankar Piped Water Supply Scheme at Sukdal Village (Mouza) 5 nos Habitation under Burwan Division, PHE Dte. | 3878/BWD | 27/07/2021 | 60 | SUJAY KUMAR RAY | 151.77 | 107.68 | 70.95 | 1
723 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mankar Piped Water Supply Scheme at Mankar (Part) Village (Mouza) under Burwan Division, PHE Dte. | 3591/BWD | 13/07/2021 | 60 | SAMRAT REALPROJECTS PRIVATE LIMITED | 140.03 | 73.57 | 100 | 1
724 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Extension of pipeline in connection with FHTC for MANKAR Piped W/S Scheme under Galsi-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. (Gr.-B) | 446/DSD | 14/07/2021 | 30 | N.B. CONSTRUCTION | 1.81 | 1.78 | 100 | 1
725 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Restoration of village Road dismantled by laying pipeline for providing FHTC at SUKDAL Village, near Sukdal Petrol and near Hindi School under Mankar (Zone-I) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte._2nd call SL-04 | 649/DSD | 03/11/2022 | 21 | PRATIVA CONSTRUCTION | 4.72 | 4.67 | 100 | 1
726 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Retrofitting of RCC Elevated Reservoir (Capacity 450 Cum) by Shortcreting, Guniting etc. in connection with Augmentation of Mankar W/S. Scheme (Zone - I) under Burdwan Division, PHE. Dte. | 6043/BWD | 07/10/2021 | 45 | SUDIPTO GORAIN | 19.85 | 19.85 | 100 | 1
727 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Payment for supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 934/DW | 31/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
728 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  | 21/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
729 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Replacement of damaged AC pipeline at Raipur under Mankar (Zone-II) piped water supply scheme within Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-06] | 182/DSD | 18/04/2023 | 21 | MONDAL CONSTRUCTION | 0.97 | 0 | 0 | 0
730 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Mankar piped water supply scheme at Budbud (Part), Budbud habitation, Malikpara village (Malikpara habitation) & Bagabanpur village (Bagabanpur habitation), Galsi-I Block under Burdwan Division, PHE Dte. | 308/BWD | 14/01/2021 | 30 | RELIABLE ENGINEERS CO.-OPERATIVE CONSTRUCTION SOCIETY LTD. | 21.83 | 11.63 | 100 | 1
731 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Replacement of damage A.C. Pipeline from Mankar Dani Pukur to Purbasa colony via Post Office & Annapurnatala to Panchakalitala under Mankar (Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte._2ND CALL. | 6633/BWD | 29/11/2021 | 30 | PREMANANDA ROY BISWAS | 11.43 | 11.26 | 100 | 1
732 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Dismantling of encroachments within Head work site of Mankar (Zone-II) Pipe Water Supply Scheme, at Galsi-I Block within Durgapur(Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [SL-A] | 130/DSD | 02/03/2022 | 3 | PARTHA RAY | 0.19 | 0 | 0 | 1
733 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Laying of pipe line at North side Canal Bank for construction of diversion road by PWD Dept. under Mankar(Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-F] | 167/DSD | 16/03/2022 | 30 | N.B. CONSTRUCTION | 0.65 | 0 | 0 | 1
734 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Connection from newly Retrofitted Over Head Reservoir to Distribution System & Rising main Pipe Line of MANKAR (Zone-I) Water Supply Scheme under Galsi-I Block under within Durgapur Sub Division PHE Dte. Under Burdwan Division PHE Dte. [Gr.-D] | 497/DSD | 12/08/2022 | 30 | SHUBHRA KANTI GHOSH | 4.77 | 4.52 | 100 | 1
735 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Modification to Rising main and D.I. distribution to ensure more controll of water supply of MANKAR water Supply Scheme under Durgapur (Burdwan North) Sub-Division in Galsi-I Block under Burdwan Division, P.H.E. Dte. [SL-E] | 336/DSD | 27/06/2022 | 21 | SHUBHRA KANTI GHOSH | 2.82 | 2.67 | 100 | 1
736 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Replacement of damage A.C. Pipeline at Mankar Bhattacharya Para & New royel club to Battala under Mankar(Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. SL-06 | 651/DSD | 03/11/2022 | 30 | OM ENTERPRISE | 4.72 | 4.68 | 100 | 1
737 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Restoration of village Road dismantled by laying pipeline for providing FHTC Budbud Village, Girls School Para, Sukanta Nagar etc. under Mankar (Zone-I) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. SL-02 | 647/DSD | 03/11/2022 | 21 | DEY NIRMAN | 4.8 | 4.76 | 100 | 1
738 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Restoration of village Road dismantled by laying pipeline for providing FHTC near north side of Budbub Canal par colony under Mankar (Zone-I) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. SL-01 | 646/DSD | 03/11/2022 | 21 | ROY CONSTRUCTION | 4.79 | 4.65 | 100 | 1
739 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Ground development, vertical extension of valve chamber, construction of pathway, drain etc. at Head work site of Mankar (Z-II) water supply scheme, Block-Galsi-I under Durgapur (Bardhaman North)Sub-Division under Burdwan Division, PHE Dte. SL-05 | 650/DSD | 03/11/2022 | 30 | SAIKAT RAY | 3.42 | 2.98 | 100 | 100
740 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Replacement of damage A.C. Pipeline Mankar Pal Para & Nayakpara under Mankar(Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. SL-07 | 652/DSD | 03/11/2022 | 30 | SOUMYAVASH DAS | 4.55 | 4.41 | 100 | 1
741 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) within the command area of Augmentation of MANKAR Piped Water Supply Scheme Near Mankar Masjitala, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-03] | 178/DSD | 18/04/2023 | 21 | SOUMYAVASH DAS | 0.96 | 0.94 | 100 | 100
742 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) within the command area of Augmentation of MANKAR Piped Water Supply Scheme at back side of Mankar Girls School, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-04] | 179/DSD | 18/04/2023 | 21 | SHUBHRA KANTI GHOSH | 0.96 | 0.94 | 100 | 100
743 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of Augmentation of MANKAR Piped Water Supply Scheme at backside of Mankar Girls School, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-01] | 176/DSD | 18/04/2023 | 21 | SHUBHRA KANTI GHOSH | 0.95 | 0.94 | 100 | 95
744 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Augmentation of MANKAR Piped Water Supply Scheme at Mankar Palpara, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-05] | 153/DSD | 13/04/2023 | 21 | SOUMYAVASH DAS | 0.95 | 0.93 | 100 | 100
745 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of Augmentation of MANKAR Piped Water Supply Scheme at Mankar Nayekpara, Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-02] | 177/DSD | 18/04/2023 | 21 | SOUMYAVASH DAS | 0.96 | 0.94 | 100 | 100
746 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Crossing of Mankar-Guskara Bolgona Road at Head works site of Mankar (Z-I) W/S Scheme for laying distribution and rising main through pushing of 750mm.dia. RCC casing pipe by hydraulic jacking method for Mankar (Z-I) W/S Scheme under Durgapur (Bardhaman North) Sub Division, Burdwan Division, PHE Dte.[SL-12] | 712/DSD | 30/12/2022 | 30 | SHUBHRA KANTI GHOSH | 4.74 | 4.63 | 100 | 100
747 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Replacement of damage UPVC Pipeline at Mankar Masjit Tala under Mankar (Zone-II) Piped Water Supply Scheme under Galsi-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-F] | 693/DSD | 08/12/2021 | 21 | SURATH DEY | 1.47 | 1.37 | 100 | 1
748 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Shifting of 300 MM dia D.I. pipe and laying of 12 mtr 150 mm dia D.I.pipe for widening of NH2 at Budbud more and supply of 80 mm dia Sluice valve and construction of valve chamber of Mankar Water supply scheme within Galsi -I Block,under Durgapur Sub Division,PHE Dte. | 658/DSD | 24/08/2023 | 15 | SHANKHA GHOSH | 0.96 | 0.96 | 100 | 100
749 | PURBA BARDHAMAN | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Formal Work Order for Sinking of 300 x 200 mm x 150mtr depth by DR Rig, Construction of 01 (One) no 5.25 x 3.25 m Pump House cum Chlorine room with sanitary arrangement, Boundary wall, including laying UPVC distribution system (LDS) and Providing FHTC and other allied works at Mankar under Retrofitting of Mankar PWSS, Block- Galsi-I, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. (Zone-I/Part-B) | 1114/DWSD | 02/08/2024 | 120 | MANASH GHOSH | 163.89 | 0 | 0 | 0
750 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Laying of new 300 & 200 mm dia sluice valve with valve chamber and replacement of 200 & 150 mm dia sluice valve with valve chamber at Budbud bazar and near NH2 and sukdal within Durgapur Sub-Division under Burdwan Division, PHE Dte. | 657/DSD | 24/08/2023 | 15 | SOUMYAVASH DAS | 0.96 | 0.95 | 100 | 100
751 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Laying Parallel pipeline from Mankar Hattala to Bhattacharya para & restore to damage pipeline at difference location of Mallickpara for water supply smoothly of MANKAR (Z-II) and its adjoining mouza's Piped W/S Scheme at Galsi-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. | 4819/BWD | 08/11/2023 | 60 | SHUBHRA KANTI GHOSH | 24.08 | 0.38 | 100 | 100
752 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Laying of hume pipe 600 MM dia and laying of 48 mtr 315 mm dia HDPE pipe for widening of NH2 crossing at Budbud more fly over of Mankar Water supply scheme within Galsi -I Block,under Durgapur Sub Division,PHE Dte. | 43/DSD | 17/01/2024 | 60 | SOUMYAVASH DAS | 4.77 | 4.66 | 100 | 100
753 | PURBA BARDHAMAN | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Acceptance cum Formal Work Order for the work of Balance Work for Distribution System and Rising Main Pipeline (CV/DVAC/UPVC), Construction of different dia Sluice valve /Air valve/Washout chamber in different sizes, Concrete Road renovation, Mechanical joints for MANKAR (ZONE-II) Water Supply Schemes of GALSI-I Block under Durgapur Water Supply Division, PHE Dte. | 769/DWSD | 06/06/2024 | 25 | SHANKHA GHOSH | 2.06 | 2.06 | 100 | 100
754 | PURBA BARDHAMAN | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Acceptance cum Formal Work Order for the work of Balance work for Distribution System and Rising Main Pipeline (UPVC/HDPE), Construction of different dia Sluice valve /Air valve/Washout chamber in different sizes,Concrete road renovation for MANKAR (ZONE-I) Water Supply Schemes of GALSI-I Block under Durgapur Water Supply Division, PHE Dte. | 766/DWSD | 06/06/2024 | 25 | SOUMYAVASH DAS | 1.4 | 1.4 | 100 | 100
755 | PURBA BARDHAMAN | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Acceptance cum Formal Work Order for Drain Constriction & Repairing works For Mankar Water Supply Scheme (Zone-II) at Nayak Para, Dist:- Purba Bardhaman under DWSD, PHE Dte. | 1211/DWSD | 23/08/2024 | 10 | SOUMYAVASH DAS | 0.66 | 0.65 | 100 | 100
756 | PURBA BARDHAMAN | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | QUOTATION FOR NEW SERVICE CONNECTION AT MANKAR PWSS ZONE-2 T.W-1 UNDER C.M.D, P.H.E Dte. |  | 31/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.72 | 0 | 0 | 0
757 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Galsi ¿ I Block under Burdwan Division, PHE. Dte._2ND CALL. | 1738/BWD | 28/03/2022 | 1101 | JYOTI ENTERPRISE | 5.72 | 0 | 0 | 100
758 | PURBA BARDHAMAN | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Acceptance cum Formal Work Order for the work of "Sinking of 300 X 200mm x 150mtr depth by DR Rig Tube Wells, Construction of 01 (One) no 5.25 x 3.25m Pump House cum Chlorine Room with sanitary arrangement, Boundary Wall including laying UPVC distribution system (LDS) and providing FHTC and allied works at Mankar under Retrofitting of Mankar PWSS (Zone-II, Part-A), under Galsi-I Block, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 760/DWSD | 06/06/2024 | 360 | G.S CONSTRUCTION AND CO | 92.69 | 0 | 0 | 10
759 | PURBA BARDHAMAN | Durgapur W/S Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | FORMAL WORK ORDER FOR Sinking of 300 x 200 mm x 150 mtr deapth by DR Rig, Construction of 1 (One) no 5.25 x 3.25 m Pump House cum Chlorine room with sanitary arrangement, Boundary wall including laying UPVC distribution system (LDS) and providing FHTC and other allied works at Mankar under Retrofitting of Mankar PWSS, Block- Galsi-I under DURGAPUR W/S DIVISION, PHE DTE. | 260/DWSD | 11/02/2025 | 418 | M/S. GOUTAM ROY | 105.88 | 0 | 0 | 5
760 | PURBA BARDHAMAN | Central Mechanical | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of MANKAR Piped Water Supply Scheme Block-Galsi-I , SM/08034 | Retrofitting | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1&2 (ZONE:-1&2) at Augmentation MANKAR Water Supply Scheme [ BLOCK- GALSI-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1003/CMD | 17/04/2025 | 60 | DAS CONSTRUCTION | 51.38 | 0 | 0 | 30
761 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dogachia village of Amra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-232/BWD/2020-21) | 2737/BWD | 10/08/2020 | 30 | KALYAN CHOWDHURY | 4.92 | 9.84 | 200 | 1
762 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amra village of Amra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-404/BWD/2020-21) | 3531/BWD | 25/09/2020 | 30 | DEBASHISH ENTERPRISE | 4.92 | 9.84 | 200 | 1
763 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Teli Nuri village of Amra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-427/BWD/2020-21) | 3530/BWD | 25/09/2020 | 30 | KALYAN CHOWDHURY | 4.92 | 9.84 | 200 | 1
764 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amra village of Amra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-208/BWD/2020-21) | 2734/BWD | 10/08/2020 | 30 | DEBASHISH ENTERPRISE | 4.92 | 9.84 | 200 | 1
765 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Supply of SS316 grade flow control valve for FHTC at different water supply schemes within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional store.[Part-2] | 1792 /BWD | 26/02/2021 | 10 | INDIA PIPE FITTING CO | 9.7 | 1.11 | 100 | 1
766 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amra Piped Water Supply Scheme at Amra (2 Nos Habitation Part) & Dogachia Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte._3rd CALL. | 3138/BWD | 03/06/2021 | 45 | D.M. ENTERPRISE | 57.42 | 41.54 | 200 | 1
767 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AMRA Piped Water Supply Scheme (Vill-Dogechia, Habitation- Dogechia ) at Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte.Gr.A. | 57/BSD | 13/01/2022 | 30 | DEY NIRMAN | 4.81 | 4.78 | 100 | 1
768 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Extension of pipeline at AMRA water supply scheme at different villages (Tengaberia, Badpur & Kolupukur) FHTC of Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-F] | 1374/BSD | 05/10/2021 | 30 | D.M. ENTERPRISE | 4.74 | 0 | 0 | 1
769 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Construction of Boundary wall at 3rd Tube well site of Dogachia Mouza of Amra water supply scheme under Jamalpur block under Burdwan Division, PHE Dte. [Length-59 Mtr][Gr.-F] | 1028/BSD | 05/08/2021 | 45 | MUKHERJEE ENTERPRISE | 4.45 | 0 | 0 | 1
770 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Providing FHTC for Dogachia Mouza [(Habitation (Village)] for AMRA piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 2019/BWD | 28/04/2023 | 30 | DEY NIRMAN | 20.61 | 10.4 | 100 | 100
771 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-C) [SL. No. : 11] | 3408/BWD | 25/06/2021 | 15 | N.S. ENTERPRISE | 4.86 | 8.53 | 200 | 1
772 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dattapur village (Adampur habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 11] | 590/BWD | 25/01/2021 | 15 | N.S. ENTERPRISE | 4.86 | 6.59 | 200 | 0
773 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-B) [SL. No. : 13] | 592/BWD | 25/01/2021 | 15 | DEY NIRMAN | 4.84 | 9.68 | 200 | 0
774 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-A) [SL. No. : 12] (Agreement No. 671/BWD of 2020-21) | 591/BWD | 25/01/2021 | 15 | MUKHERJEE ENTERPRISE | 4.86 | 9.72 | 200 | 0
775 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-A) [SL. No. : 12] (Agreement no. 839/BWD of 2020-21) | 1397/BWD | 15/02/2021 | 15 | MUKHERJEE ENTERPRISE | 4.86 | 9.72 | 200 | 0
776 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amra Piped Water Supply Scheme , SM/06969 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jajanpur village and Jajanpur-Tangaberia habitation of JAUGRAM piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Gr.-6B] | 3331/BWD | 18/09/2020 | 30 | DEY NIRMAN | 4.86 | 9.73 | 200 | 0
777 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS , SM/06747 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mugura village of Mugura piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-163/BWD/2020-21) | 2690/BWD | 07/08/2020 | 30 | LAKSHMIKANTA DAS | 4.92 | 9.84 | 200 | 1
778 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS , SM/06747 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jagarpur & Mugura village of Mugura piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-238/BWD/2020-21) | 2689/BWD | 07/08/2020 | 30 | HAFIJUR RAHAMAN MIDYA | 4.92 | 9.84 | 200 | 1
779 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS , SM/06747 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mugura village of Mugura Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿3A¿] (Agreement no. 163/BWD,2020-2021) | 3535/BWD | 25/09/2020 | 30 | LAKSHMIKANTA DAS | 2.69 | 0 | 0 | 1
780 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS , SM/06747 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jagarpur & Mugura village of Mugura Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿3B¿] (Agreement no.238/BWD of 2020-21) | 4118/BWD | 16/10/2020 | 30 | HAFIJUR RAHAMAN MIDYA | 4.92 | 0 | 0 | 1
781 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS , SM/06747 | Retrofitting | Laying Parallel Pipeline to improve drinking water supply, Construction of Boundary wall, Path Way, Drain at Head Work Site & 2nd TW Site and providing leftout FHTC, Road Restoration with allied work for MUGRA Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | 2711/BWD | 11/07/2024 | 2720 | M/S PURBASHA | 40.24 | 0 | 0 | 90
782 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Mugura PWSS , SM/06747 | Retrofitting | Providing 7 Nos.FHTC at Mugura Dakshinpara village under MUGURA Piped Water Supply Scheme,Block:Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | 08/BSD | 02/01/2025 | 15 | RUPALI ENTERPRISE | 0.76 | 0.74 | 100 | 100
783 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS , SM/06748 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sultanpur village of Sultanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-373/BWD/2020-21) | 2602/BWD | 04/08/2020 | 30 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.91 | 9.83 | 200 | 1
784 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS , SM/06748 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gopalpur village of Sultanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-338/BWD/2020-21) | 2609/BWD | 04/08/2020 | 30 | BISWAS ENTERPRISE | 4.91 | 9.82 | 200 | 1
785 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS , SM/06748 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gopalpur village of Sultanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-339/BWD/2020-21) | 3700/BWD | 05/10/2020 | 30 | BISWAS ENTERPRISE | 4.91 | 9.82 | 200 | 1
786 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS , SM/06748 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sultanpur village of Sultanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-374/BWD/2020-21) | 3701/BWD | 05/10/2020 | 30 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.19 | 8.38 | 200 | 1
787 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS , SM/06748 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sultanpur Piped Water Supply Scheme at Halbele, Hridaypur, Isabpur, Nowapara & Uplati Village (Mouza), Kalna ¿ I Block under Burdwan Division, PHE Dte.(Agreement No. 56/2020-2021 OF SE/CC/PHE. DTE.) | 4901/BWD | 07/12/2020 | 90 | MAJILA ENTERPRISE | 94.67 | 151.02 | 187.57 | 1
788 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS , SM/06748 | Retrofitting | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-5]. | 3590/BWD | 13/07/2021 | 30 | PREMANANDA ROY BISWAS | 127.5 | 0.48 | 200 | 1
789 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS , SM/06748 | Retrofitting | Protection work of distribution system (200 mm dia) of 35 Mtr length near the head work site (Right Side) of Sultanpur & its adjoining mouzas water supply scheme by UC Bullah including Drum Sheet within Kalna Sub-Division under Burdwan Division, PHE Dte.[Gr.-E] | 20/KSD | 07/01/2021 | 30 | DEBASHISH ENTERPRISE | 0.75 | 0 | 0 | 1
790 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sultanpur PWSS , SM/06748 | Retrofitting | Providing FHTC in each household from dist. System within Scheme jurisdiction in Hridaypur, Upalati, Belerhat, Gopalpur, Sultanpur, Isabpur & Naopara Village of SULTANPUR W/S. Scheme under Burdwan Division, PHE Dte. | 1357/BWD | 09/03/2022 | 30 | TAPAS KUMAR ROY | 16.69 | 0 | 0 | 1
791 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Anguna village of Anguna Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿1A¿] | 2694/BWD | 10/07/2020 | 30 | ANWESHA CONSTRUCTION | 4.91 | 0 | 0 | 1
792 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Anguna village of Anguna Piped Water Supply Scheme within Headquarters under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿1A¿] (Agreement no. 171/BWD of 2020-21) | 2698/BWD | 07/08/2020 | 30 | ANWESHA CONSTRUCTION | 4.91 | 0 | 0 | 1
793 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Anguna village of Anguna piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-171/BWD/2020-21) | 2684/BWD | 07/08/2020 | 30 | ANWESHA CONSTRUCTION | 4.91 | 9.82 | 200 | 1
794 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gunar village of Anguna piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-203/BWD/2020-21) | 2693/BWD | 07/08/2020 | 30 | M/S ANAND CONSTRUCTION | 4.92 | 9.84 | 200 | 1
795 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Anguna village of Anguna piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-302/BWD/2020-21) | 3355/BWD | 21/09/2020 | 30 | ANWESHA CONSTRUCTION | 4.59 | 9.18 | 200 | 1
796 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gunar village of Anguna piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-369/BWD/2020-21) | 3515/BWD | 25/09/2020 | 30 | M/S ANAND CONSTRUCTION | 2.17 | 4.34 | 200 | 1
797 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Anguna Piped Water Supply Scheme at Anguna (Part), Gunar (Part) & Sakita Village (Mouza), Raina-I Block under Burdwan Division, PHE Dte. | 517/BWD | 21/01/2021 | 45 | SK ALIM | 33.4 | 46.82 | 171.1 | 1
798 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Extension of pipe line of existing distribution system within the command area of Anguna Piped Water Supply Scheme, Anguna village within Raina-1 Block of Burdwan Sub Division under Burdwan Division,PHE Dte".Gr.A. | 1465/BSD | 25/08/2022 | 45 | ANWESHA CONSTRUCTION | 4.97 | 4.93 | 100 | 1
799 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
800 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ I Block under Burdwan Division, PHE. Dte. | 39/BWD | 05/01/2022 | 30 | HAFIJUR RAHAMAN MIDYA | 15.62 | 0 | 0 | 1
801 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Extension of pipeline of Anguna water supply scheme at Anguna, Sanktia and Gunar village within Raina-I Block under Burdwan division, PHE Dte.[Gr.-A] | 1480/BSD | 09/11/2021 | 30 | SK ABDUL HALIM | 4.44 | 4.35 | 100 | 1
802 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Extension of pipeline for Anguna water supply scheme at Anguna, Sanktia and Gunar village within Raina-I Block under Burdwan Division, PHE Dte.[Gr.-B] | 1429/BSD | 28/10/2021 | 30 | SK ABDUL HALIM | 4.38 | 3.11 | 100 | 1
803 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Material Requisition To Resource Division | 1108/BWD | 26/02/2022 | 0 | Resource Division | 25.78 | 0 | 0 | 0
804 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Engineer, Head Quarters, Burdwan Division, PHE Dte. for the month of March'23. | 201/JJM | 01/06/2023 | 0 | SK. ASRAFUDDIN | 0.39 | 0 | 0 | 0
805 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Vehicle bill for the office of the Assistant Engineer, Head Quarters Burdwan Division, PHE Dte. for the month of June'23. | 482/JJM | 09/08/2023 | 0 | SK. ASRAFUDDIN | 0.4 | 0 | 0 | 0
806 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Anguna, Sanktia, Gunar village of ANGUNA Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1575/BWD | 31/03/2023 | 60 | JAGADANANDAPUR CO. OP. LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 33.16 | 0 | 0 | 100
807 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Vehicle bill for the month of november'2023. | 1140/JJM | 29/12/2023 | 0 | SK. ASRAFUDDIN | 0.4 | 0 | 0 | 0
808 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | MAINTENANCE OF ROAD (WHISH IS DAMAGED FOR LAYING PIPELINE BY PHE DEPTT) NAMELY NARUGRAM H.C TO BADSHI ROAD VIDE- PACKAGE NO- WB 22 12 UNDER PMGSY-III UNDER NARUGRAM GP. & RAINA-I BLOCK, IN PURBA BARDHAMAN DISTRICT | 894/JJM | 25/09/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 3.86 | 0 | 0 | 0
809 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Vehicle bill for the month of October & November'2023. | 1145/JJM | 29/12/2023 | 0 | SOURAV JANA | 0.79 | 0 | 0 | 0
810 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Anguna PWSS , SM/06752 | Retrofitting | Vehicle bill for the month of november'2023. | 1141/JJM | 29/12/2023 | 0 | SK.ASFIA | 0.4 | 0 | 0 | 0
811 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme , SM/07545 | Retrofitting | Continuation order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Rameswarpur village and Rameswarpur habitation of Dharmadanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Group-1B] | 4743/BWD | 01/12/2020 | 30 | TAPAS KUMAR ROY | 3.2 | 0 | 0 | 1
812 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme , SM/07545 | Retrofitting | Water tap connection in each household from existing distribution system within scheme jurisdiction in Koldanga-Mirpur village (35 Nos) & Rameswarpur village (50 Nos) (Total-85 Nos) of Dharmadanga water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL NO.-C] | 1026/KSD | 01/10/2021 | 15 | SETH ENTERPRISE | 2.95 | 2.95 | 100 | 1
813 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme , SM/07545 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Dharmadanga Piped Water Supply Scheme at Dharmadanga (P) Village (Mouza), Kalna-I Block under Burdwan Division, PHE Dte. | 6641/BWD | 29/11/2021 | 30 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 14.94 | 15.39 | 100 | 1
814 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme , SM/07545 | Retrofitting | Extension of different dia UPVC pipeline at Rameswarpur village of Dharmadanga water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Sl No.-A] | 167/KSD | 19/02/2021 | 30 | BISHWAJIT DAS | 3.97 | 0 | 0 | 1
815 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme , SM/07545 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhuban village of Dharmadanga Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 6B] | 4745/BWD | 01/12/2020 | 30 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 2.66 | 2.66 | 100 | 1
816 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme , SM/07545 | Retrofitting | Work order for "Providing Functional house hold tap connections for Sajal Gram Village within Kalna-I Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Dharmadanga Water Supply Scheme) Sl No- 5 | 101/KSD | 08/02/2023 | 28 | BUILD-TECH | 0.88 | 0.88 | 100 | 100
817 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme , SM/07545 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of March'23. | 204/JJM | 01/06/2023 | 0 | M/S MUNMUN DEY | 0.28 | 0 | 0 | 0
818 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme , SM/07545 | Retrofitting | Work Order for "Laying distribution system including providing FHTC in the leftout portion of Dharmadanga (SM/07545) water supply scheme under Kalna Sub-Division under Burdwan Division, PHE Dte.". | 1921/KSD | 02/12/2024 | 30 | H SAMANTA | 2.02 | 0 | 0 | 0
819 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme , SM/07545 | Retrofitting | Work Order for "Providing Functional house hold tap connections within command ares of Dharmadanga water supply scheme within Kalna-I Block under Kalna Sub-Division under Burdwan Division, PHE Dte." | 1305/KSD | 23/08/2023 | 15 | BISWAS ENTERPRISE | 2.81 | 1.81 | 100 | 100
820 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme , SM/07545 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Rameswarpur (P) Village, Kalna - I Block within Dharma Danga PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 836/AE/HQ | 31/10/2023 | 30 | MUNSHI JAVEDUR JAMAN | 0.76 | 0.72 | 100 | 100
821 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme , SM/07545 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Madhuban (P) Village, Kalna - I Block within Dharma Danga PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 873/AE/HQ | 07/11/2023 | 30 | PAPRI HAZRA | 0.76 | 0.72 | 100 | 100
822 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme , SM/07545 | Retrofitting | Rest portion of OHR work (Plastering, Priming & Painting and interconnection of Rising Main with Specials) & Construction of Boundary wall with Smriti Saudha at Aug. of DHARMADANGA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Length - 81.01 Mtr, No of Columns=28 Nos. Centre to Centre- 3.0 Mtr.). | 267/BWD | 15/01/2024 | 60 | S.K. CONSTRUCTION | 27.45 | 26.2 | 100 | 100
823 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dharma Danga Piped Water Supply Scheme , SM/07545 | Retrofitting | Work Order for 'Laying distribution system including providing FHTC in the left out portion of Dharmadanga piped water supply scheme under Kalna Sub-Division under Burdwan Division, PHE Dte.'. | 1770/KSD | 20/11/2024 | 30 | BISWAS ENTERPRISE | 1.67 | 1.37 | 100 | 100
824 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Purbasthali-II Block , SM/07802 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  | 21/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
825 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Purbasthali-II Block , SM/07802 | Retrofitting | Payment for supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 934/DW | 31/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
826 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Purbasthali-II Block , SM/07802 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur (Part) village (Kashipur habitation) of Kashipur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 18] [Agr. No. 720/BWD of 2020-2021] | 1441/BWD | 18/02/2021 | 15 | PREMANANDA ROY BISWAS | 4.48 | 0 | 0 | 1
827 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Purbasthali-II Block , SM/07802 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur village (Kashipur habitation) of Kashipur Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 20] | 596/BWD | 25/01/2021 | 15 | IYASIN DAFADAR | 4.86 | 6.57 | 135 | 1
828 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jarogram village and Jarogram habitation of Madhabpur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-662/BWD/2020-21) | 4911/BWD | 08/12/2020 | 30 | SUPRIYA RAY | 4.87 | 9.73 | 200 | 1
829 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gureghar village and Gureghar habitation of Madhabpur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-557/BWD/2020-21) | 4910/BWD | 08/12/2020 | 30 | KAUSHIK RAY | 4.87 | 9.73 | 200 | 1
830 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gureghar village and Gureghar habitation of Madhabpur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-440/BWD/2020-21) | 3332/BWD | 18/09/2020 | 30 | KAUSHIK RAY | 4.87 | 9.73 | 200 | 1
831 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jarogram village and Jaragram habitation of Madhabpur piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-441/BWD/2020-21) | 3333/BWD | 18/09/2020 | 30 | SUPRIYA RAY | 4.87 | 9.73 | 200 | 1
832 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dumo village (Dumo habitation) & Satgoria village (Satgoria habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 07] [Agr. No.721/BWD of 2020-2021] | 1418/BWD | 18/02/2021 | 15 | BRINDABAN KONAR | 4.86 | 9.72 | 200 | 1
833 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhabpur village and Madhabpur habitation of MADHABPUR Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿7C¿] | 3334/BWD | 18/09/2020 | 30 | KAJAL MUKHERJEE | 4.86 | 4.86 | 100 | 1
834 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mirzapur village (Mirzapur habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 10] | 6189/BWD | 28/10/2021 | 15 | JAI MAA DURGA & CO. | 2.19 | 2.19 | 100 | 1
835 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhabpur (Part) village (Madhabpur (P) habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 06] | 1417/BWD | 18/02/2021 | 15 | KAJAL MUKHERJEE | 4.86 | 3.28 | 67.34 | 1
836 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jargram (Part) village (Jargram (P) habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 05] | 1416/BWD | 18/02/2021 | 15 | LAKSHMIKANTA DAS | 4.86 | 4.86 | 100 | 1
837 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Repairing of damaged 180 mm dia UPVC pipeline at Madhabpur village for Madhabpur water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-I] | 79/BSD | 19/01/2021 | 30 | KOUSIK MALLICK | 4.82 | 4.7 | 100 | 1
838 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhabpur village and Madhabpur habitation of MADHABPUR Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿7C¿] | 7050/BWD | 22/12/2020 | 30 | KAJAL MUKHERJEE | 4.86 | 4.49 | 100 | 1
839 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Laying of damaged UPVC pipeline with HDPE pipes at Madhabpur village for Madhabpur Zone-I water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-G] | 1478/BSD | 09/11/2021 | 30 | KOUSIK MALLICK | 3.57 | 3.56 | 100 | 1
840 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jargram (Part) village (Jargram (P) habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 05] | 2058/BWD | 19/04/2022 | 15 | LAKSHMIKANTA DAS | 4.86 | 4.86 | 100 | 1
841 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Extension of uPVC pipeline regarding FHTC for Gureghar, Dumo, Basantabati habitation under Madhabpur (Zone-II) W/S. Scheme at Jamalpur Development Block under Burdwan Division, PHE Dte. | 3139/BWD | 19/07/2022 | 30 | PRATIMA CONSTRUCTION | 5.64 | 5.53 | 100 | 1
842 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Extension of uPVC pipeline for providing FHTC from existing distribution pipe line system within command area of MADHABPUR (Zone-II) W/S Scheme at Khalerpar under Gureghar village, Jamalpur Development Block under Burdwan Division, PHE Dte". Gr,B. | 2099/BSD | 28/11/2022 | 30 | PRATIMA CONSTRUCTION | 0.9 | 0.9 | 100 | 1
843 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of MADHABPUR (Z-I) W/S Scheme under Jamalpur Block within Burdwan Sub-Division, PHE Dte. | 2704/BWD | 08/06/2023 | 30 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.26 | 12.53 | 100 | 100
844 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Preparation and Submission of DPR for Augmentation of MADHABPUR PWSS under Jamalpur Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1525/BSD | 17/07/2023 | 15 | CARTO | 0.78 | 0.77 | 100 | 100
845 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gureghar village (Gureghar habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A). [SL. No. : 08] | 1419/BWD | 18/02/2021 | 15 | KAUSHIK RAY | 4.87 | 9.73 | 200 | 0
846 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mirzapur village (Mirzapur habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 10] | 1421/BWD | 18/02/2021 | 15 | JAI MAA DURGA & CO. | 4.86 | 9.73 | 200 | 0
847 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Gureghar village (Gureghar habitation) of Madhabpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B). [SL. No. : 09] | 1420/BWD | 18/02/2021 | 15 | SAIKAT RAY | 4.87 | 4.87 | 100 | 0
848 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Extension of pipeline for providing functional household tap connection at Gureghar village of MADHABPUR Zone-II piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Gr.-A] | 1128/BSD | 26/08/2021 | 45 | SAIKAT RAY | 1.4 | 1.25 | 100 | 0
849 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MADHABPUR Piped Water Supply Scheme , SM/07862 | Retrofitting | Construction of switch rooms & Rising main at different TW site for MADHABPUR (Zone-I) Piped Water Supply Scheme under Jamalpur Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | 3629/BWD | 21/08/2023 | 60 | DEBJYOTI GOSWAMI | 9.11 | 7.42 | 100 | 80
850 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of ERUAR piped water supply scheme at Muratipur (Part) (Muratipur Part Habitation) village (Mouza) within Bhatar Block under Burdwan Division, PHE Dte._2nd Call. | 1266/BWD | 11/02/2021 | 30 | S.N. ENTERPRISE | 18.71 | 8.73 | 46.67 | 1
851 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ERUAR Piped Water Supply Scheme at Eruar (Part-A) (Eruar (Part-A) Habitation) village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. (Agreement no. 569/BWD of 2020-2021) | 356/BWD | 15/01/2021 | 30 | HAFIJUR RAHAMAN MIDYA | 19.95 | 12.15 | 200 | 1
852 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ERUAR Piped Water Supply Scheme at Eruar (Part-D) (Eruar (Part-D) Habitation) village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. ._2ND CALL (Agreement No.703/BWD of 2020-2021) | 1569/15/BWD | 22/02/2021 | 30 | DUBE ENTERPRISE | 18.61 | 23 | 143.83 | 1
853 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Providing Functional Household Tap Connection (FHTC) & Restoration of pipeline at Sixteen Nos. samsad of Eruar Gram Panchayat from ERUAR Piped Water Supply Scheme at Bhatar Block under Burdwan Division, PHE Dte. | 7033/BWD | 17/12/2021 | 60 | IJABUL SEKH | 92.08 | 76.47 | 100 | 1
854 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Providing Left-Out FHTC to Eruar Habitation within ERUAR PWSS, within Durgapur (Burdwan North) Sub-Division, PHE Dte, under Burdwan Division, PHE Dte. | 557/DSD | 20/07/2023 | 30 | SANDIPAN SENGUPTA | 4.44 | 0 | 0 | 0
855 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of ERUAR piped water supply scheme at Eruar (Part-B) (Eruar (Part-B) Habitation) village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. [Tr No.-678/BWD/20-21] | 1264/BWD | 11/02/2021 | 30 | S.T. ENTERPRISE | 22.24 | 0.82 | 100 | 100
856 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Providing Functional House hold Tap connection (FHTC) from existing distribution system within the command area of ERUAR piped water supply scheme at Erusr (Part-C) (Eruar Part-C Habitation) village (Mouza) within Bhatar Block under Burdwan Division, PHE Dte. | 1265 /BWD | 11/02/2021 | 30 | S.T. ENTERPRISE | 18.05 | 30.08 | 170.16 | 1
857 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Extension of pipeline at "Sansad No. 10, 11 and 24" of Eruar and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur (Bardhaman North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-N] | 607/DSD | 07/10/2021 | 30 | DUBE ENTERPRISE | 3.15 | 2.3 | 100 | 1
858 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41D-4561) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of September & October'2022. | 823/VEH | 02/12/2022 | 0 | SUJAUDDIN SEKH | 0.73 | 0 | 0 | 0
859 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of November'2022. | 954/JJM/22-23 | 13/01/2023 | 0 | SUJAUDDIN SEKH | 0.38 | 0 | 0 | 0
860 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Laying of pipeline for ERUAR Piped Water Supply Scheme in Bhatar Block under Burdwan Division, PHE. Dte. | 3079/BWD | 09/08/2024 | 90 | SOUMYAVASH DAS | 5.01 | 0 | 0 | 0
861 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site(ERRUAR4 TH Pump House),Kaluttak under ERUAR PWSS, Bhatar Dev. Block, within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. DTE. | 1082/DSD | 11/12/2024 | 60 | SWAPAN KUMAR ROY | 3.72 | 0 | 0 | 0
862 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Muratipur village and Muratipur habitation of ERUAR Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿11B¿] | 4748/BWD | 01/12/2020 | 30 | S. MONDAL | 4.86 | 9.73 | 200 | 0
863 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Replacing of existing damaged pipe line at KALUTAK and repairing of 4th Pump house and changing of 2 nos. valve at ERUAR village of ERAUR PWSS of Bhatar Block within Durgapur (Burdwan North) Sub- Division under Burdwan Division PHE Dte. | 909/DSD | 15/12/2023 | 45 | SWAPAN KUMAR ROY | 0.93 | 0.61 | 100 | 100
864 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Eruar Piped Water Supply Scheme at Bhatar Block , SM/07780 | Retrofitting | Replacing of existing damaged pipe line at Nareshpara and changing of 4 nos valve near OHR and Kaluttak Village of Eraur PWSS under Bhatar Development Block within Durgapur Sub Division under Burdwan Division PHE Dte. | 620/DSD | 05/08/2024 | 30 | SWAPAN KUMAR ROY | 2.17 | 2.09 | 100 | 100
865 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sudpur PWSS , SM/06769 | Retrofitting | Urgent repairing work at Sudpur piped water supply scheme to ensuring FHTC work under Katwa-I Block under Katwa Sub-Division, under Burdwan Division, PHE Dte.[Tr No.-875/BWD/20-21] | 91/KTS | 12/02/2021 | 3 | HAMID SK | 0.92 | 1.84 | 200 | 1
866 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sudpur PWSS , SM/06769 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Rayerpara, Purba and Paschim Bijoynagar village under SUDPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte [Sl - 5 ] | 565/KTS | 31/08/2021 | 15 | HAMID SK | 3.6 | 0 | 0 | 1
867 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sudpur PWSS , SM/06769 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Sudpur, Lokpur & Narayanpur village under SUDPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte [Sl - 4 ] | 564/KTS | 31/08/2021 | 15 | BABUL SK | 2.42 | 0 | 0 | 1
868 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sudpur PWSS , SM/06769 | Retrofitting | Balance work of OHR at Head Work site, construction of HUME Pipe culvert , Road restoration work and boundary wall at 2nd TW site with Gate, land development at Head work site and 2nd TW site under KAITHAN, SUDPUR & PANUHAT Piped Water Supply Scheme under KATWA -I Block, under Katwa Sub-Division within Burdwan Division, PHE Dte. | 3141/BWD | 20/08/2024 | 120 | VISHAL CONSTRUCTION CO. | 126.29 | 0 | 0 | 50
869 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sudpur PWSS , SM/06769 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SUDPUR Piped Water Supply Scheme (PART-A) at Katwa-I Block under Burdwan Division, PHE Dte. [Agreement No. 44/2020-2021 OF SE/CC/PHE. DTE.] | 4290/BWD | 03/11/2020 | 90 | MD HASIN | 86.85 | 137.68 | 200 | 1
870 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Purba Krishnapur village of Suhari piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Phase-I] | 1326/BWD | 12/02/2021 | 30 | SAMANTA CONSTRUCTION | 4.92 | 3.5 | 100 | 1
871 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Providing FHTC (650 Nos.) from dist. System within the command area of SUHARI piped water supply scheme at Masjidpara, Allahadipara, Varpally, Saktigarh Utttar Bazar Habitation (Putunda & Saktigarh Mouza) at Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | 7027/BWD | 17/12/2021 | 30 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 19.58 | 19.58 | 100 | 1
872 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Providing FHTC in Jarul village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte.(Part-A). Gr.K. | 1381/BWD | 05/08/2022 | 5 | SAMANTA CONSTRUCTION | 0.96 | 0 | 0 | 0
873 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Providing FHTC in Jarul village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte.(Part-B).Gr.L. | 1382/BSD | 05/08/2022 | 5 | SAMANTA CONSTRUCTION | 0.96 | 0 | 0 | 0
874 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Providing FHTC in Shuhari village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte.(Part-A).Gr.M. | 1383/BSD | 05/08/2022 | 5 | SAMANTA CONSTRUCTION | 0.97 | 0 | 0 | 0
875 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Providing FHTC in Shuhari village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS Bardhhaman-II Development Block under Burdwan Division, PHE Dte.(Part-B). Gr.N. | 1384/BSD | 05/08/2022 | 5 | SAMANTA CONSTRUCTION | 0.96 | 0 | 0 | 0
876 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Providing FHTC in Atagar village for 100% coverage in Sajal Gram from existing distribution system within SUHARI PWSS Bardhhaman-II Development Block under Burdwan Division, PHE Dte. Gr.O. | 1390/BSD | 08/08/2022 | 5 | SAMANTA CONSTRUCTION | 0.56 | 0 | 0 | 0
877 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage in Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ II Block under Burdwan Division, PHE. Dte. | 385/BWD | 20/01/2022 | 30 | BISWAS ENTERPRISE | 11.97 | 1.5 | 100 | 100
878 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for SUHARI its Adjoining Mouza W/S Scheme, Block -Bardhaman-II within Burdwan Sub-Division, PHE Dte. (Mouza- PURBA KRISHNAPUR) | 502/BSD | 21/03/2023 | 45 | M/S PALASH BISWAS | 3.45 | 2.83 | 100 | 100
879 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Providing FHTC for 100% coverage in different village (SUHARI, JARUL, ATTAGAR & GHATSHILA) from existing distribution system within SUHARI PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte._2ND CALL | 3722/BWD | 25/08/2023 | 30 | BIPLAB SAMANTA | 18.91 | 16.58 | 87.68 | 100
880 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Suhari piped water supply scheme at Putunda, Atagarh (08 Nos. Habitation), Ghatshila (04 Nos. Habitation), Jarur (02 Nos. Habitation), Saiadpur Chak, Tajpur (04 Nos. Habitation) village, Bardhaman-II Block under Burdwan Division, PHE Dte. | 5004/BWD | 10/12/2020 | 90 | NATIONAL CONSTRUCTION | 80.78 | 15.48 | 100 | 0
881 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Tajpur Village, Burdwan - II Block within Suhari PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 853/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 100 | 100
882 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Providing laying distribution pipe line due to shal balla pileing at Sontoshpur village by P.Samiti for SUHARI PWSS at Bardhhaman-II Development Block under Burdwan Division,PHE Dte | 537/BSD | 14/03/2024 | 30 | M/S PALASH BISWAS | 0.89 | 0.89 | 100 | 100
883 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Providing left out FHTC for Putunda village within SUHARI PWSS , Bardhhaman-II Development Block under Burdwan Division, PHE Dte | 1032/BSD | 10/06/2024 | 30 | ISHAN CONSTRUCTION | 0.96 | 0.95 | 100 | 100
884 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Allied work for inter connection between 3rd tube well site and laying distribution system for Suhari PWSS within Bardhaman-II Block , under Burdwan Division, PHE Dte | 1274/BSD | 12/07/2024 | 7 | ISHAN CONSTRUCTION | 2.34 | 2.34 | 100 | 100
885 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Suhari Piped Water Supply Scheme , SM/07823 | Retrofitting | Allied work for providing left out FHTC for Putunda village within SUHARI PWSS,Bardhha under Burdwan Division, PHE Dte. | 508/BSD | 06/03/2025 | 23 | ISHAN CONSTRUCTION | 0.96 | 0 | 0 | 100
886 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme , SM/07825 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dhanya Kherur village and Deleypara, Malpara, Mandalpara, Paschimpara & Purba Daspara habitation of Majhergram piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-385/BWD/2020-21) | 4124/BWD | 16/10/2020 | 30 | SUBRATA GUPTA | 4.86 | 9.73 | 200 | 1
887 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme , SM/07825 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sihigram village and Adibashipara, Hindupara (Sihigram), Kamarpara & Makarpara habitation of Majhergram piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-605/BWD/2020-21) | 4125/BWD | 16/10/2020 | 30 | N.S. ENTERPRISE | 4.86 | 6.21 | 127.86 | 1
888 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme , SM/07825 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dhanya Kherur village and Duleypara, Malpara, Mandalpara, Paschimpara & Purba Daspara Habitation of Majhergram piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | 260/BWD | 13/01/2021 | 30 | SUBRATA GUPTA | 4.86 | 9.73 | 200 | 1
889 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme , SM/07825 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Majhergram Piped Water Supply Scheme at Sihigram (P) (Paschimpara habs.), Sonagachi (3 Nos. habs.), Majhergram (8 Nos. habs.) & Ganguria (3 Nos. habs), Monteswar Block under Burdwan Division, PHE Dte. | 1497/BWD | 18/02/2021 | 60 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 57.97 | 74.34 | 86.02 | 1
890 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme , SM/07825 | Retrofitting | Extension of 63 mm dia UPVC pipeline to provide house connection to the beneficiaries of Sihigram village of Majhergram water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Sl No.-D] | 141/KSD | 12/02/2021 | 30 | GOUTAM DEY | 3.14 | 2.96 | 100 | 1
891 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme , SM/07825 | Retrofitting | Continuation work for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sihigram village and Adibasipara, Hindupara (Sihigram), Kamarpara & Makarpara habitation of Majhergram Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿11B¿] | 1667/BWD | 23/03/2022 | 30 | N.S. ENTERPRISE | 4.16 | 3.66 | 100 | 1
892 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme , SM/07825 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
893 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme , SM/07825 | Retrofitting | Construction of sanitary Latrine and water supply arrangement at Head Work Site of Majhigram Singot piped water supply schemes under Mongalkote Block under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No-01] | 159/KTS | 24/02/2022 | 21 | BABUL SK | 1.76 | 0 | 0 | 1
894 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme , SM/07825 | Retrofitting | Material Requisition To Resource Division | 1106/BWD | 26/02/2022 | 0 | Resource Division | 44.82 | 0 | 0 | 0
895 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme , SM/07825 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41J-6795) for the office of the Deputy Superintending Engineer, Central Circle, PHE Dte. for the month of November & December'22. | 1131/JJM | 28/02/2023 | 0 | MD HASIN | 0.72 | 0 | 0 | 0
896 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Majhergram Piped Water Supply Scheme , SM/07825 | Retrofitting | Restoration of Nepakuli -Baghnapara road from 1.50 km to 2.50 km damaged due to laying of underground water pipe line by PHE with box cutting and Jhama moorum consolidation under Kalna Highway Sub-Division of Burdwan South Highway Division , P.W (Roads) Dte. during the year 2023-2024 | 1025/JJM | 05/10/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 1.74 | 0 | 0 | 0
897 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block , SM/07828 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Basuda village and Basuda Habitation of Serua piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I][Gr.-9A] | 4086/BWD | 16/10/2020 | 30 | DHIRENDRANATH SOM | 4.87 | 0 | 0 | 1
898 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block , SM/07828 | Retrofitting | Extension of pipeline at "Bamunara & Kumarun & Sakraw" villages of Serua and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-F] | 05/DSD | 03/01/2022 | 30 | DHIRENDRANATH SOM | 2.98 | 0 | 0 | 0
899 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block , SM/07828 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Serua Piped Water Supply Scheme at Rajipur, Ratanpur, Serua & Basuda (P) village, Bhatar Block under Burdwan Division, PHE Dte.[Agreement No. 708/BWD OF 2020-2021] | 1580/BWD | 22/02/2021 | 60 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 74.3 | 78.25 | 145.29 | 1
900 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block , SM/07828 | Retrofitting | Extension of 180 mm dia pipeline at "Serua" villages of Serua and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-A] | 01/DSD | 03/01/2022 | 30 | DHIRENDRANATH SOM | 4.82 | 4.8 | 100 | 1
901 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block , SM/07828 | Retrofitting | Extension of 50 mm dia. pipeline at "Serua-Basuda-Jhujkadanga" villages of Serua and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte.[Gr.-C] | 02/DSD | 03/01/2022 | 30 | DHIRENDRANATH SOM | 1.84 | 0.86 | 100 | 1
902 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block , SM/07828 | Retrofitting | Extension of pipeline at "Panua, Ratanpur & Rajipur" villages of Serua and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-E] | 04/DSD | 03/01/2022 | 30 | DHIRENDRANATH SOM | 4.68 | 2.09 | 100 | 1
903 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block , SM/07828 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Bhatar Block under Burdwan Division, PHE. Dte. | 268/BWD | 14/01/2022 | 30 | BHARAT CONSTRUCTION | 14.17 | 0 | 0 | 1
904 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block , SM/07828 | Retrofitting | Relaying of distribution main in alternate route for improvement of water supply at Basudha (South Panoa) village within Serua water supply scheme in Bhatar Block under Burdwan Division, PHE Dte. | 6119/BWD | 25/10/2021 | 30 | KOUSIK MALLICK | 26.54 | 25.91 | 100 | 1
905 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block , SM/07828 | Retrofitting | Trial boring at Kumarun for Serua and its Adjoining Mouza Water Supply Scheme within Bhatar Block under Burdwan Division PHE Dte. [Gr.-C] | 526/DSD | 22/08/2022 | 7 | BABA ADHIRA CONSTRUCTION | 0.6 | 0.6 | 100 | 1
906 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block , SM/07828 | Retrofitting | Trial boring at Serua for Serua and its Adjoining Mouza Water Supply Scheme within Bhatar Block under Burdwan Division PHE Dte. [Gr.-D] | 527/DSD | 22/08/2022 | 7 | BABA ADHIRA CONSTRUCTION | 0.6 | 0.6 | 100 | 1
907 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block , SM/07828 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Serua Piped Water Supply Scheme at Bamunara village (Bamunara habs), Jhujkadanga village, Kumarun village & Panua (P) village (Panua (P) & Sakra habs), Bhatar Block under Burdwan Division, PHE Dte.[ | 1579/BWD | 22/02/2021 | 60 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 54.03 | 66.71 | 149.74 | 1
908 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block , SM/07828 | Retrofitting | Restoration and shifting of pipeline, providing sluice valve, Painting and minor repairing of Switch room, Clearing compound premises, making temporary earthen road and repairing of old Valve chamber, Septic tank etc of Serua Piped water supply Scheme , P.H.E Dte. Block:-Bhatar Dist: Purba Bardhaman. | 236/DSD | 07/02/2025 | 45 | DHIRENDRANATH SOM | 10.43 | 0 | 0 | 100
909 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Serua Piped Water Supply Scheme at Bhatar Block , SM/07828 | Retrofitting | Construction of Boundary wall, Land Development work at Head work site, Construction of approach road from main road to OHR of SERUA Piped water supply Scheme, P.H.E Dte. Block:-Bhatar Dist: Purba Bardhaman. | 1024/BWD | 21/03/2025 | 90 | KALYAN CHOWDHURY | 18.74 | 0 | 0 | 50
910 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block , SM/07807 | Retrofitting | Extension of pipeline including water tap connection (FHTC) at Pubar Vill [Kamalpur & Pubar (Part) Hab.] of PUBAR and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte._2ND CALL. | 6105/BWD | 08/10/2021 | 30 | ANWESHA CONSTRUCTION | 29.76 | 0 | 0 | 1
911 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block , SM/07807 | Retrofitting | Extension of pipeline including water tap connection (FHTC) at Pubar Vill [Kamalpur & Pubar (Part) Hab.] of PUBAR and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte._2ND CALL | 6104/BWD | 08/10/2021 | 30 | ANWESHA CONSTRUCTION | 29.76 | 29.22 | 100 | 1
912 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block , SM/07807 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Ausgram-II Block under Burdwan Division, PHE. Dte. | 940/BWD | 17/02/2022 | 30 | NANDY UDYOG | 11.82 | 0 | 0 | 0
913 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block , SM/07807 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Pubar (Part) village (Pubar (Part) habitation) of Pubar Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [Sl. No. : ¿16¿] | 66/BWD | 05/01/2021 | 15 | SUBRATA GUPTA | 4.86 | 4.86 | 100 | 1
914 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block , SM/07807 | Retrofitting | Extension of Pipeline with Providing Functional Household Tap Connection (FHTC) within the command area of PUBER Piped Water Supply Scheme , Block- Ausgram-II within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-E] | 77/DSD | 11/02/2022 | 30 | ANWESHA CONSTRUCTION | 4.75 | 2.94 | 100 | 1
915 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block , SM/07807 | Retrofitting | Relaying of pipeline damaged by construction of Road/Drain etc. at different location of Pubar and its adjoining mouzas water supply scheme at Ausgram-II Block within Durgapur Sub-Division, under Burdwan Division, PHE Dte. [SL-20] | 719/DSD | 30/12/2022 | 30 | ASRUL HAQUE MONDAL | 0.88 | 0.88 | 100 | 100
916 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pubar Piped Water Supply Scheme at Ausgram-II Block , SM/07807 | Retrofitting | Laying parallel pipeline to increase the water supply towards Kaldanda of PUBER and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-C] | 344/DSD | 30/06/2022 | 30 | ANWESHA CONSTRUCTION | 4.81 | 4.81 | 100 | 1
917 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block , SM/07809 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Takipur Piped Water Supply Scheme at Asinda, Chonari & Takipur Village (Mouza), Ausgram-I Block under Burdwan Division, PHE Dte. (Agreement No. 575/BWD of 2020-2021) | 440/BWD | 19/01/2021 | 45 | KOUSIK MALLICK | 36.91 | 66.2 | 200 | 1
918 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block , SM/07809 | Retrofitting | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of TAKIPUR Piped Water Supply Scheme at Takipur (Part), Asinda (part) & Chanwari (Part) habitation, Ausgram-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. | 6693/BWD | 01/12/2021 | 30 | HAMID SK | 20.08 | 19.98 | 100 | 1
919 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block , SM/07809 | Retrofitting | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of TAKIPUR Piped Water Supply Scheme at Takipur (Part), Asinda (part) & Chanwari (Part) habitation, Ausgram-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Sl-A] | 135/DSD | 02/03/2022 | 30 | HAMID SK | 4.78 | 4.78 | 100 | 1
920 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block , SM/07809 | Retrofitting | Installation of Sluice Valve, Air Valve and inter connection of Pipeline and allied works to regulate the water supply towards Ashinda & Takipur Village of TAKIPUR and its adjoining mouza's Piped W/S Scheme at Ausgram-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [SL-09] | 709/DSD | 30/12/2022 | 30 | HAMID SK | 4.71 | 4.67 | 99.32 | 0
921 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block , SM/07809 | Retrofitting | Construction of Path way, Drain, Vertical Extension of valve chamber & repairing of OHR connection etc. including shifting of damage pipeline at Head work site of TAKIPUR water supply scheme, Block-Ausgram-II within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Gr.-H] | 662/DSD | 22/11/2021 | 30 | PAL CONSTRUCTION | 4.02 | 3.95 | 100 | 1
922 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block , SM/07809 | Retrofitting | Relaying of pipe line damaged by Construction of Health Centre & construction of road / drain etc. at different location of TAKIPUR and its adjoining mouza's Piped W/S Scheme at Ausgram-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte.[SL-9] | 175/DSD | 18/04/2023 | 21 | TARAMA AGENCY | 0.77 | 0.77 | 100 | 100
923 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Takipur Piped Water Supply Scheme at Ausgram-I Block , SM/07809 | Retrofitting | Relaying of pipe line damaged by Construction of Community Centre & construction of road / drain etc. at different location of TAKIPUR and its adjoining mouza's Piped W/S Scheme at Ausgram-I Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte.[SL-08] | 174/DSD | 18/04/2023 | 21 | TARAMA AGENCY | 0.91 | 0.91 | 100 | 100
924 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Tehata (Part) village Tehata (Part) habitation of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-05] | 1223/BWD | 11/02/2021 | 15 | ROY & ROY CONSTRUCTION | 3.16 | 6.32 | 200 | 1
925 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bajitpur village, Bajit habitation & Jhikra village (Jhikra habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-02] | 52/BWD | 05/01/2021 | 15 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.86 | 9.73 | 200 | 1
926 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Baitipara village (Baitipara Habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Sl No.-01] | 51/BWD | 05/01/2021 | 15 | SUKANTA DEY | 4.87 | 0 | 0 | 1
927 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Baitipara village (Baitipara habitation) of Tehata Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Sl. No. : ¿01¿] | 4020/BWD | 05/08/2021 | 15 | SUKANTA DEY | 3.23 | 3.23 | 100 | 1
928 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Tehata (Part) village, Tehata (Part) habitation of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-05] | 55/BWD | 05/01/2021 | 15 | ROY & ROY CONSTRUCTION | 4.86 | 9.72 | 200 | 1
929 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kutubpur (Part) village (Kutub Habitation) & Suipara village (Suipara Habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Sl No.-04] | 54/BWD | 05/01/2021 | 15 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.84 | 9.68 | 200 | 1
930 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Tehata (Part) village (Bajitpur & Sarpukur habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-06] | 56/BWD | 05/01/2021 | 15 | M/S UNIQUE | 4.86 | 9.72 | 200 | 1
931 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Tehata Piped Water Supply Scheme at Bajitpur (P), Jhiekra (P), Habibpur (P), Narenga Kutubpur (P) & Saipara (P) Village (Mouza), Kalna-II Block under Burdwan Division, PHE Dte. | 6640/BWD | 29/11/2021 | 30 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 26.96 | 24.45 | 100 | 1
932 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Providing FHTC work at Agradaha village (25 Nos), Jhikra village (20 Nos), Kutubpur village (122 Nos) Habibpur village (232 Nos) & Bajitpur village (16 Nos) under Tehata Zone-II Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 5515/BWD | 14/12/2023 | 30 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 23.96 | 0 | 0 | 0
933 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Providing FHTC work at Suipara village (13 Nos), Tehata village (52 Nos), Bajitpur village (18 Nos) Narenga village (282 nos) & Baitipara village (52 Nos) under TEHATA Zone-I Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 5516/BWD | 14/12/2023 | 30 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 19.32 | 0 | 0 | 0
934 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Work order for " Providing Functional house hold tap connections for Sajal Gram Village within Kalna-II Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Tehata Water Supply Scheme)" | 345/KSD | 17/04/2023 | 30 | ARINDAM BHATTACHARYA | 0.88 | 0.88 | 100 | 100
935 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Hire & fuel charges of vehicle Car No.-WB-04G-7127 for the month of July & August'2023. | 767/JJM | 12/10/2023 | 0 | PARTHA PRATIM ACHARYA | 0.78 | 0 | 0 | 0
936 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kutubpur (Part) village (Habibpur Habitation) of Tehata piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [SL NO.-03] | 53/BWD | 05/01/2021 | 15 | TAPAS KUMAR ROY | 4.86 | 9.73 | 200 | 0
937 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Vehicle bill [car No.-WB-04G-7127] for the month of October & November'2023. | 1321/JJM | 01/02/2024 | 0 | PARTHA PRATIM ACHARYA | 0.73 | 0 | 0 | 0
938 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Vehicle bill for the month of August & September'2023. | 1139/JJM | 29/12/2023 | 0 | MD HASIN | 0.77 | 0 | 0 | 0
939 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Tehata Piped Water Supply Scheme at Kalna-II Block , SM/07812 | Retrofitting | Different types of works involve in connection with Augmentation of TEHATA Zone-I & II (SM/16301) Water Supply Scheme, CHAKSIMLA (SM/15586) Water Supply Scheme & DWARIATON (SM/16285) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2201/BWD | 13/06/2024 | 752 | M/S ASHA CONSTRUCTION | 449.98 | 8.47 | 84.9 | 25
940 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amrargar Piped Water Supply Scheme at Ausgram-II Block , SM/07817 | Retrofitting | Restoration of village Road dismantled by laying pipeline for providing FHTC at Amarargarh Mandalpara of AMARARGARH Piped Water Supply Scheme [Retrofitting] under Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-08] | 156/DSD | 13/04/2023 | 21 | PARTHA RAY | 0.96 | 0.95 | 100 | 100
941 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amrargar Piped Water Supply Scheme at Ausgram-II Block , SM/07817 | Retrofitting | Restoration of village Road dismantled by laying pipeline for providing FHTC at Amarargarh Dakshinpara of AMARARGARH Piped Water Supply Scheme [Retrofitting] under Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte.[SL-07] | 155/DSD | 13/04/2023 | 21 | RAM MOHAN MUKHERJEE | 0.97 | 0.96 | 100 | 100
942 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amrargar Piped Water Supply Scheme at Ausgram-II Block , SM/07817 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amrargarh Piped Water Supply Scheme at Amrargarh (10 Nos Habitation), Dombandi (2 Nos Habitation), Jamtara (2 Nos Habitation) & Panch Mahali Village (Mouza), Ausgram-II Block under Burdwan Division, PHE Dte. | 3875/BWD | 27/07/2021 | 60 | B.B.C. ENTERPRISE | 91.55 | 73.62 | 80.42 | 100
943 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amrargar Piped Water Supply Scheme at Ausgram-II Block , SM/07817 | Retrofitting | Restoration of village Road dismantled by laying pipeline for providing FHTC at Amarargarh Ankurepara, Bonpara & Sahapara of AMARARGARH Piped Water Supply Scheme [Rectrofitting] under Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-06] | 154/DSD | 13/04/2023 | 637 | SAIKAT RAY | 0.97 | 0 | 0 | 100
944 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Amrargar Piped Water Supply Scheme at Ausgram-II Block , SM/07817 | Retrofitting | Acceptance cum Formal work order for the work of " Supplying and Laying of different dia UPVC pipe (LDS) including providing FHTC and Repairing and renovation of existing RCC OHR at Amrargarh under Amarargarh PWSS, Block- Aushgram-II, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 751/DWSD | 05/06/2024 | 300 | SAIKAT RAY | 36.37 | 0 | 0 | 100
945 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Preparation of DPR for augmentation of Naopara W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-I) | 211/KSD | 23/02/2022 | 21 | ROY CHOWDHURY ASSOCIATES | 2.43 | 2.43 | 100 | 1
946 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Laying Rising main and distribution pipeline including Providing Functional Household Tap Connection (FHTC) within the command are of Augmentation of NAOPARA Piped W/S. Scheme under Burdwan Division, PHE. Dte. | 1870/BWD | 05/04/2022 | 45 | KOUSIK MALLICK | 66.6 | 66.49 | 100 | 1
947 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
948 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Work order for Repairing and laying of UPVC pipeline & providing FHTC work from Mallick oil mil to the house of Khalil Sk at Naopara Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 397/KSD | 02/05/2023 | 30 | ARINDAM BHATTACHARYA | 0.99 | 0 | 0 | 0
949 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Jahannagar, Ganganandapur, Nowapara & Monteswar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, P.H.E. Dte.[Part ¿ A] | 3632/BWD | 22/08/2022 | 20 | RAMASISH ENTERPRISE | 12.8 | 3.2 | 100 | 1
950 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Material Requisition To Resource Division | 542/BWD | 27/01/2022 | 0 | Resource Division | 9.97 | 0 | 0 | 0
951 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Material Requisition To Resource Division | 1240/BWD | 07/03/2022 | 0 | Resource Division | 4.19 | 0 | 0 | 0
952 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Material Requisition To Resource Division | 1526/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
953 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Work order for Repairing and laying of UPVC pipeline & providing FHTC work from wood shop to the house of Patal Das at Naopara Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 396/KSD | 02/05/2023 | 30 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.99 | 0.69 | 100 | 100
954 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Work Order for Repairing and laying of UPVC pipeline & providing FHTC work from the house of Habu Sk to the house of Asadul Kha at Naopara Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 421/KSD | 11/05/2023 | 30 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.97 | 0.97 | 100 | 100
955 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Work Order for "Repairing and laying of UPVC pipeline & providing FHTC work from the shop of Bhoton Sk to the petrol pump at Naopara Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | 1308/KSD | 23/08/2023 | 30 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 3.59 | 3.58 | 100 | 100
956 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Work Order for "Restoration of Pipeline of Naopara Piped Water Supply Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl-1) | 2060/KSD | 23/02/2024 | 30 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 2.98 | 2.95 | 100 | 50
957 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Work Order for "Road Restoration and other ancilliary works under NAOPARA(SM/09407) water supply scheme under Kalna Sub-Division under Burdwan Division, PHE Dte." | 2198/KSD | 15/03/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 1.34 | 1.12 | 100 | 50
958 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Work Order for "Ancillary work of Rising Main including Construction of Sluice Valve Chamber & other allied work of Naopara Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-2) | 2061/KSD | 23/02/2024 | 20 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 1.69 | 1.67 | 100 | 5
959 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Quotation from WBSEDCL for load enhancement charges of Aug Naopara w/s scheme under Burdwan Division, PHE Dte. (Application No.-5004355150)(Ref. ID-500374861) | 1047/JJM | 30/10/2024 | 0 | WBSEDCL | 1.34 | 0 | 0 | 0
960 | PURBA BARDHAMAN | Burdwan Division | Augmentation of NAOPARA PWSS for providing Functional Household Tap Connection (FHTC) , SM/09407 | Augmentation | Different Types of work involved in connection with Augmentation of NAOPARA (SM/09407) & HARIPUR (SM/13315) water supply scheme Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2203/BWD | 13/06/2024 | 344 | MONDAL & CO. | 223.65 | 32.69 | 93.37 | 50
961 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SINGI PWSS to accommodate FHTC in Katwa-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09412 | Augmentation | Route Survey and preparation of DPR for SINGHI PWSS under Katwa -II Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-03] | 54/KTS | 25/01/2022 | 21 | RADIANT | 2.81 | 2.81 | 100 | 1
962 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SINGI PWSS to accommodate FHTC in Katwa-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09412 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
963 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SINGI PWSS to accommodate FHTC in Katwa-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09412 | Augmentation | Material Requisition To Resource Division | 1239/BWD | 07/03/2022 | 0 | Resource Division | 4.33 | 0 | 0 | 0
964 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SINGI PWSS to accommodate FHTC in Katwa-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09412 | Augmentation | Material Requisition To Resource Division | 566/BWD | 27/01/2022 | 0 | Resource Division | 22.48 | 0 | 0 | 0
965 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SINGI PWSS to accommodate FHTC in Katwa-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09412 | Augmentation | Material Requisition To Resource Division | 1318/BWD | 08/03/2022 | 0 | Resource Division | 23.18 | 0 | 0 | 0
966 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SINGI PWSS to accommodate FHTC in Katwa-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09412 | Augmentation | Material Requisition To Resource Division | 1523/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
967 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SINGI PWSS to accommodate FHTC in Katwa-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09412 | Augmentation | Augmentation of Laying Distribution and Rising main Network and Construction of 250 Cum capacity 20 Mtr. staging height RCC Over Head Reservoir including Soil Investigation and pipe connection with cost of pipes, specials and Providing Functional Household Tap Connection (FHTC) from distribution system within the command area of SINGHI Piped Water Supply Scheme under JAL SWAPNA MISSION under Katwa II Block in Purba Bardhaman District under Burdwan Division, PHE. Dte. | 2014/BWD | 18/04/2022 | 683 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 465.17 | 324.41 | 71.1 | 95
968 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08701 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AJHAPUR Piped Water Supply Scheme and its adjoining mouzas (Vill- Ajhapur, Habitation- Purba Sadipur, Musunda) at Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1352/BWD | 09/03/2022 | 45 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 41.37 | 38.97 | 100 | 1
969 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08701 | Retrofitting | Providing Functional House Hold Tap Connection (FHTC) at Ajhapur village (Habitation,near Head Work Site)under AJHAPUR PWSS at Jamalpur Dev. Block of Burdwan Sub-Division under Burdwan Division,PHE Dte. Gr.D. | 1480/BSD | 25/08/2022 | 30 | T.K. BANERJEE & CO. | 3.33 | 3.33 | 100 | 1
970 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08701 | Retrofitting | Providing Functional Household Tap Connection(FHTC)from existing distribution pipe line system within command area of AJHAPUR Piped W/S Scheme at Ajhapur Habitation (Near Head Works Site), Jamalpur Development Block under Burdwan Division,PHE Dte. Gr.E. | 1602/BSD | 14/09/2022 | 30 | DEY NIRMAN | 4.03 | 3.92 | 100 | 1
971 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08701 | Retrofitting | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. | 1194/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0 | 0
972 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08701 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) of AJHAPUR & its adjoining mouzas Piped Water Supply Scheme, Block - Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 5124/BWD | 21/11/2022 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 11.24 | 9.77 | 86.98 | 1
973 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08701 | Retrofitting | Extension of pipeline of AJHAPUR Piped Water Supply scheme of Jamalpur Block under Burdwan Sub-Division,under Burdwan Division,PHE Dte. | 1978/BSD | 17/11/2022 | 15 | DEY NIRMAN | 0.51 | 0.51 | 100 | 1
974 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08701 | Retrofitting | Material Requisition To Resource Division | 422/BWD | 20/01/2022 | 0 | Resource Division | 5.49 | 0 | 0 | 0
975 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08701 | Retrofitting | Beautification of PWSS with Arboriculture, Recharge Pit including shaft and anciliary works at AJHAPUR (Jamalpur Block) P.W.S.S under Burdwan Division, PHE Dte. | 276/RWS | 03/09/2024 | 10 | DEY NIRMAN | 0.91 | 0 | 0 | 0
976 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08701 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for AJHAPUR its Adjoining Mouza W/S Scheme, Block -Jamalpur within Burdwan Sub-Division, PHE Dte. (Mouza- SALMULA) | 507/BSD | 21/03/2023 | 45 | M/S MA TARA ENTERPRISE | 3.29 | 2.78 | 100 | 100
977 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08701 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 46/2020-2021 OF SE/CC/PHE. DTE.) | 4753/BWD | 01/12/2020 | 90 | SK ALIM | 93.16 | 45.49 | 200 | 0
978 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08701 | Retrofitting | Construction of Boundary wall at 4th Tubewell site with Inter Connection and providing FHTC at Mirepara, Adampur, Shalmula Village (Habitation) of AJHAPUR Water Supply Scheme under JAMALPUR Block of Burdwan Division, PHE Dte. | 783/BWD | 27/02/2024 | 30 | MUNSHI JAVEDUR JAMAN | 14.96 | 12.75 | 100 | 100
979 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08701 | Retrofitting | Laying of pipeline for providing FHTC 100% coverage and also construction & installation of Sluice Valve & Valve Chamber to control the flow of water, road restoration work etc. of different Piped W/S Schemes, Block Jamalpur under Burdwan Division, PHE Dte. | 2488/BWD | 01/07/2024 | 550 | M/S NATIONAL CONSTRUCTION | 480.97 | 0 | 0 | 80
980 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08701 | Retrofitting | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 0 | 40
981 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of AJHAPUR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08701 | Retrofitting | Construction of overhead structure for placing 2 Nos 5000 lit PVC tank including interconnection, Installation of Solar pump, FHTC, LDS & Sinking of 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe at Mohanpur village for AJHAPUR Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman under Burdwan Division PHE Dte. | 817/BWD | 04/03/2025 | 90 | UJJWAL MUKHERJEE | 23.02 | 0 | 0 | 0
982 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Functional Household Tap Connection (FHTC) at Baratikra village within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. (Part-A). | 1858/AE/HQ | 05/10/2021 | 30 | J. K. CORPORATION | 4.83 | 4.83 | 100 | 1
983 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Baratikra village within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. (Part-B). | 1859/AE/HQ | 05/10/2021 | 30 | INDRAJIT MONDAL | 4.83 | 4.83 | 100 | 1
984 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Laying of HDPE pipeline at Antpara village for dedicated water supply at Dakshinmohonpur village within Antpara PWSS, Block-Jamalpur under Burdwan Division, PHE Dte. [Group : A] | 65/AE/HQ | 11/02/2022 | 30 | SUPER SKILL | 4.68 | 4.68 | 100 | 1
985 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Continuation work order for functional household tap connection (FHTC) at Baratikra village within the command area of Antpara piped water supply scheme at Jamalpur Block under Burdwan Division, PHE Dte.[Part-A][Gr.-D] | 1950/AE/HQ | 22/12/2021 | 30 | J. K. CORPORATION | 4.73 | 4.73 | 100 | 1
986 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H-3668) for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. for the month of May & June'22. | 462/VEH/22-23 | 29/08/2022 | 0 | MD HASIN | 0.51 | 0 | 0 | 0
987 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) of ANTPARA & its adjoining mouzas Piped Water Supply Scheme, [Nandanpur Vill.] Block ? Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. _2ND CALL. | 5275/BWD | 30/11/2022 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 9.45 | 9.44 | 99.92 | 0
988 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Extension of pipeline for providing functional house hold tap connection at Dakshin Mohonpur & Uttar Mohanpur habitation under Antpara water supply scheme under Burdwan Division, PHE Dte. | 1244/AE/HQ | 12/02/2021 | 30 | DIBAKAR SHAW | 4.81 | 1.49 | 100 | 1
989 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Extension of pipeline for providing functional house hold tap connection at Antpara habitation within the command area of Antpara water supply scheme under Burdwan Division, PHE Dte. | 1258/AE/HQ | 15/02/2021 | 30 | WESTERN WATER SUPPLY AGENCY | 4.8 | 1.46 | 100 | 1
990 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Construction of sluice valve chamber and extension of pipeline for making functional of Household Tap at Daspur village within Antpara piped water supply scheme under Burdwan Division, PHE Dte.[Gr.-A] | 1728/AE/HQ | 25/08/2021 | 30 | J. K. CORPORATION | 1.64 | 0 | 0 | 1
991 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). | 40/BWD | 05/01/2022 | 30 | PREMANANDA ROY BISWAS | 22.68 | 0 | 0 | 1
992 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Construction of different dia. Sluice Valve chamber to operate water flow for supplying water in zonal demand basis within command area of Antpara PWSS under Burdwan Division, PHE Dte._Gr-C | 125/AE/HQ | 04/03/2022 | 15 | SUPER SKILL | 4.81 | 4.81 | 100 | 1
993 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Laying of uPVC pipe for providing FHTC at Baratikra Village within ANTPARA Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte. [Group : C] | 242/AE/HQ | 20/04/2022 | 30 | J. K. CORPORATION | 4.58 | 4.39 | 100 | 1
994 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Repairing and restoration of pipeline besides river bank of Damodar damaged due to construction of retaining wall at Antpara to Dakshinmohanpur within command area of ANTPARA PWSS under Burdwan Division, PHE Dte._Gr-B | 134/AE/HQ | 11/03/2022 | 20 | SUPER SKILL | 4.18 | 0 | 0 | 1
995 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. | 1454/BWD | 11/03/2022 | 30 | PREMANANDA ROY BISWAS | 18.83 | 0 | 0 | 1
996 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ramkrishnapur village (Ramkrishnapur Habitation) of Antpara piped water supply scheme within Head Quarters under Burdwan Division, PHE Dte.[Part-A] | 1083/BWD | 08/02/2021 | 15 | DIBAKAR SHAW | 4.78 | 4.77 | 100 | 1
997 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Laying of uPVC pipe for providing FHTC at Dakshinmohanpur habitation within ANTPARA Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-C | 145/AE/HQ | 16/03/2022 | 20 | MUKHERJEE ENTERPRISE | 4.75 | 4.68 | 100 | 1
998 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Antpara village within the command area of ANTPARA Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : A] | 240/AE/HQ | 20/04/2022 | 30 | N.S. ENTERPRISE | 4.77 | 3.69 | 100 | 1
999 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Laying of distribution system of different damaged section at Chakundi & Saligram village regarding smooth running FHTC work within Nabastha PWSS, Bardhhaman II Development Block under Burdwan Division, PHE Dte. | 787/BSD | 28/04/2023 | 30 | D.M. ENTERPRISE | 0.97 | 0.95 | 100 | 100
1000 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Laying of UPVC Pipeline at Daspur Habitation under ANTPARA Piped Water Supply Scheme, Jamalpur Development Block under Burdwan Division, PHE Dte. | 416/AE/HQ | 01/08/2023 | 30 | J K CORPORATION | 0.96 | 0.94 | 100 | 100
1001 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Re-Laying of UPVC Pipeline (Damaged by Irrigation Department) at Dakshin Mohanpur Habitation under ANTPARA Piped Water Supply Scheme, Jamalpur Development Block under Burdwan Division, PHE Dte. | 400/AE/HQ | 28/07/2023 | 30 | J K CORPORATION | 0.96 | 0.94 | 100 | 100
1002 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Laying UPVC (Damaged By Irrigation Department) pipeline at Uttar Mohanpur habitation, ANTPARA Piped W/S. Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 168/AE/HQ | 07/03/2024 | 30 | J.K. CORPORATION | 0.92 | 0.92 | 100 | 100
1003 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near RAMKRISHNAPUR MONDAL PARA under ANTPARA PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 740/AE/HQ | 13/09/2024 | 30 | J.K. CORPORATION | 0.96 | 0.96 | 100 | 100
1004 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Laying of UPVC (Damaged By Irrigation Department) pipeline at Daspur & Uttar Mohanpur habitation, ANTPARA Piped W/S. Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 167/AE/HQ | 07/03/2024 | 30 | J.K. CORPORATION | 0.82 | 0.82 | 100 | 100
1005 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Laying of UPVC (Damaged By Irrigation Department) pipeline near Baratikra Bridge including construction of new valve chamber under ANTPARA Piped W/S. Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 169/AE/HQ | 07/03/2024 | 30 | J.K. CORPORATION | 0.84 | 0.84 | 100 | 100
1006 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near RAMKRISHNAPUR MUSLIM PARA under ANTPARA PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 741/AE/HQ | 13/09/2024 | 30 | J.K. CORPORATION | 0.95 | 0.95 | 100 | 100
1007 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 0 | 40
1008 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Laying of uPVC pipe for providing FHTC at Nandanpur Village within ANTPARA Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-D | 146/AE/HQ | 16/03/2022 | 1111 | MUNSHI JAVEDUR JAMAN | 4.75 | 0 | 0 | 100
1009 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dakshin Mohanpur village (Dakshin Mohanpur Habitation) of Antpara piped water supply scheme within Head Quarters under Burdwan Division, PHE Dte. | 4691/BWD | 20/01/2021 | 809 | DIBAKAR SHAW | 4.86 | 4.08 | 94.75 | 100
1010 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Arrangement of drinking water supply by installation of solar submersible pump including sinking of 200 mm. dia. Tube well 150 Mtr. Deep by direct rotary rig method, Laying dist. System, FHTC and 2 Nos. 5000 Ltr. PVC tank installation with construction of RCC structure for ANTPARA Piped W/S. Scheme, Block Jamalpur under Burdwan Division, PHE Dte. | 1085/BWD | 12/03/2024 | 259 | HI-LIGHT ELECTRONICS | 16.31 | 12.84 | 66.05 | 40
1011 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Extension of Pipeline with Providing Functional Household Tap Connection (FHTC) within Daspur (Mouza) of the command area of ANTPARA Piped Water Supply Scheme Near Daspur Football Play Ground, Jamalpur Block within the Jurisdiction of the Assistant Engineer, HQ, Burdwan Division under Burdwan Division, P.H.E. Dte. | 752/AE/HQ | 18/09/2024 | 30 | GHOSH ENTERPRISE | 0.96 | 0.96 | 100 | 100
1012 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Construction of temporary kiosk for the necessary arrangement of electrification of 4th tube well at Nandanpur (mouza) under Antpata P.W.S.S within the jurisdiction of the Assistant Engineer, HQ, Burdwan Division under Burdwan Division, P.H.E. Dte. | 757/AE/HQ | 18/09/2024 | 30 | GHOSH ENTERPRISE | 0.33 | 0.33 | 100 | 100
1013 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Antpara Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08703 | Retrofitting | Extension of Pipeline with Providing Functional Household Tap Connection (FHTC) within Antpara (Mouza) & Daspur (Mouza) of the command area of ANTPARA Piped Water Supply Scheme, Jamalpur Block within the Jurisdiction of the Assistant Engineer, HQ, Burdwan Division under Burdwan Division, P.H.E. Dte. | 753/AE/HQ | 18/09/2024 | 30 | GHOSH ENTERPRISE | 0.96 | 0.95 | 100 | 100
1014 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Gobindapur piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08706 | Retrofitting | Providing FHTC from dist. System within the command area of GOBINDAPUR Piped Water Supply Scheme at Gobindapur (Part), Ichabacha, Taherpur, Dangapara, Purba Kashiara (Part), Matdanga, Chilinda, Sitarampur Village at Memari-I Development Block under Burdwan Division, PHE Dte. | 210/BWD | 11/01/2022 | 30 | A R TRADERS | 28.37 | 28.37 | 100 | 1
1015 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Gobindapur piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08706 | Retrofitting | Emergent 56 Nos. Street Stand Post closed for FHTC Work under Gobindapur Piped Water Supply Scheme (Retro Fittings) under Burdwan Sub-Divn.within Burdwan Division, PHE Dte. | 1974/BSD | 16/11/2022 | 15 | A R TRADERS | 0.24 | 0.24 | 100 | 1
1016 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Gobindapur piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08706 | Retrofitting | Beautification of PWSS with Land filling and arboriculture of Head Works site & 2nd pump house Gobindapur Pwss under memari-i Development Block under Burdwan Division, PHE Dte. | 278/RWS | 03/09/2024 | 10 | MUNSHI JAVEDUR JAMAN | 0.97 | 0 | 0 | 0
1017 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Water tap connection in each house hold from existing dist. System within Scheme jurisdiction in Katshimul village (Part) of Kamarhati (Zone-II) piped water supply scheme within Burdwan Sub-Division PHE Dte Part-A.Gr. D. | 1476/BSD | 09/11/2021 | 30 | MUNSHI JAVEDUR JAMAN | 4.83 | 4.83 | 100 | 1
1018 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Water tap connection in each house hold from existing dist. System within Scheme jurisdiction in Katshimul village (Part) of Kamarhati (Zone-II) piped water supply scheme within Burdwan Sub-Division PHE Dte Part-B..Gr. E. | 1477/BSD | 09/11/2021 | 30 | DUBE ENTERPRISE | 4.83 | 4.8 | 100 | 1
1019 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamarhati Z-II Piped Water Supply Scheme at Gotan, Kamarhati & Jashapur Village (Mouza), Raina-II Block under Burdwan Division, PHE Dte. | 6535/BWD | 24/11/2021 | 60 | KOUSIK MALLICK | 71.1 | 66.22 | 100 | 1
1020 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing dist. System within Scheme jurisdiction in Katshimul village (Part) of Kamarhati (Zone-II) piped water supply scheme within Burdwan Sub-Division PHE Dte Part-A.Gr. D. | 1686/BSD | 17/12/2021 | 30 | MUNSHI JAVEDUR JAMAN | 4.83 | 4.83 | 100 | 1
1021 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing dist. System within Scheme jurisdiction in Katshimul village (Part) of Kamarhati (Zone-II) piped water supply scheme within Burdwan Sub-Division PHE Dte Part-B..Gr. E. | 1685/BSD | 17/12/2021 | 30 | DUBE ENTERPRISE | 4.83 | 4.83 | 100 | 1
1022 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at Kamarhati village within Raina-II Block , under Burdwan Division, PHE Dte. (Zone-II). Gr.A. | 369/BSD | 02/03/2022 | 30 | DUBE ENTERPRISE | 4.98 | 4.97 | 100 | 1
1023 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at Jashapur village within Raina-II Block , under Burdwan Division, PHE Dte.Gr.C. | 276/BSD | 15/02/2022 | 30 | KOUSIK MALLICK | 4.99 | 4.98 | 100 | 1
1024 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Laying pipeline with FHTC for KAMARHATI Zone -II Water Supply Scheme at Kamarhati village (95 Nos.), Barati village (155 Nos.), Baidyapur village (110 Nos.), Jashapur village (125 Nos.) of Raina-II Block under Burdwan Division, PHE Dte. | 3166/BWD | 21/07/2022 | 45 | ANWESHA CONSTRUCTION | 31.48 | 31.37 | 100 | 1
1025 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | FHTC for Kamarhati (Zone-II) Water Supply Scheme at Kamarhati Village (36 Nos) of Raina II Block under Burdwan Division, PHE Dte [For 100% FHTC at Kamarhati Village (Harghar Jal). Gr.J | 1367/BSD | 04/08/2022 | 5 | ANWESHA CONSTRUCTION | 0.98 | 0 | 0 | 1
1026 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at Barati and Badyapur village within Raina-II Block , under Burdwan Division, PHE Dte(Zone-II). Gr.D. | 200/BSD | 01/02/2022 | 30 | ARISTOCON ENGINEERS CO-OP SOCIETY LTD | 4.8 | 4.74 | 100 | 1
1027 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | 225mm.Dia UPVC Pipeline at Node 11A to 11B of KAMARHATI(Zone-I)Water Supply Scheme within Raina-II Block , under Burdwan Division, PHE Dte. Gr.B. | 58/BSD | 13/01/2022 | 30 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 2.99 | 0 | 0 | 1
1028 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | 225mm.Dia UPVC Pipeline at Node 86C-92,86-B-86C,86-A-86B,10-11-53-53A of KAMARHATI(Zone-I)Water Supply Scheme within Raina-II Block , under Burdwan Division, PHE Dte. Gr.C. | 59/BSD | 13/01/2022 | 30 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 3.96 | 3.92 | 100 | 1
1029 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Formal Work Order for Laying distribution system including providing house connection at Nizampur, Daminya village (Mouza) of KAMARHATI Piped W/S. Scheme (Zone-I) at Raina - II Block under Burdwan Division, PHE. Dte.(Part-B) _2ND CALL. | 1601/BWD | 22/02/2021 | 90 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 184.73 | 168.79 | 100 | 100
1030 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at Kamarhati village (Purba para,Pal para,Kana para,Pandit para, pashim para)within Raina-II Block, under Burdwan Division, PHE Dte. Gr.B. | 678/BSD | 22/04/2022 | 30 | BAMDEB CONSTRUCTION & CO | 2.84 | 2.83 | 100 | 1
1031 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Extension of pipeline for KAMARHATI Water Supply Scheme FOR FHTC work at GOTAN village within Raina II Block, under Burdwan Division, PHE Dte. Gr.A. | 534/BSD | 28/03/2022 | 30 | KOUSIK MALLICK | 4.96 | 4.96 | 100 | 1
1032 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Bullah pilling (92.0 mtr) at HD Works Site(North,East & South) for protection of Boundary wall beside irrigation canel of KAMARHATI ZONE-II W/S Scheme of RAINA-II Block at Burdwan Sub -Division within Burdwan Division, PHE Dte. Dist.-Purba Bardhaman.Gr.B. | 468/BSD | 21/03/2022 | 15 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 4.61 | 0 | 0 | 1
1033 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Laying of interconnection of the Pump No.-1 & 2 with OHR and distribution main of 300 mm dia for Kamarhati (Zone-II) piped water supply scheme within Raina-II Block under Burdwan Division, PHE Dte.[Gr.-H] | 959/BSD | 23/07/2021 | 30 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 4.8 | 0 | 0 | 1
1034 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Pipeline with FHTC for KAMARHATI ZONE -II Water Supply Scheme at Kamarhati village(80 NOS) of Raina-II Block,under Burdwan Division, PHE Dte. Group : C. | 1016/BSD | 20/06/2022 | 30 | D.M. ENTERPRISE | 4.94 | 4.91 | 100 | 1
1035 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Pipeline with FHTC for KAMARHATI ZONE -II Water Supply Scheme at Kamarhati village (52 Nos.) of Raina-II Block,under Burdwan Division, PHE Dte. Group : A. | 1035/BSD | 20/06/2022 | 30 | KOUSIK MALLICK | 4.96 | 4.8 | 100 | 1
1036 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Pipeline with FHTC for KAMARHATI ZONE -II Water Supply Scheme at Kamarhati village(70 NOS) of Raina-II Block,under Burdwan Division, PHE Dte. Group : B. | 1015/BSD | 20/06/2022 | 30 | KONAR ENTERPRISE | 4.95 | 4.85 | 100 | 1
1037 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | Land Development(at entrance)of Head Works Site of of KAMARHATI ZONE-II PIPED Water Supply Scheme at RAINA-II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. Group : F. | 988/BSD | 16/06/2022 | 15 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 1.85 | 0 | 0 | 1
1038 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAMARHATI Piped Water Supply Scheme at RAINA-II Block under Burdwan Division, P.H.E. DTE. , SM/08709 | Retrofitting | FHTC for KAMARHATI (Zone-II] Water Supply Scheme at Kamarhati village (36 Nos) of Raina-II Block under Burdwan Division, PHE Dte. [for 100% FHTC at Kamarhati village (Harghar Jal)] | 1367-A/BSD | 04/08/2022 | 5 | ANWESHA CONSTRUCTION | 0.98 | 0.98 | 100 | 1
1039 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Krishnabati Piped Water Supply Scheme at Purbasthali-II Block , SM/07827 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Krishnabati Piped Water Supply Scheme at Bahara (3 Nos Habitation), Chak Bahara (Natungram Habitation), Chandanpur Simuldanga & Krishnabati (2 Nos Habitation) Village (Mouza), Mangalkot Block under Burdwan Division, PHE Dte. | 3592/BWD | 13/07/2021 | 60 | H SAMANTA | 84.33 | 73.7 | 100 | 100
1040 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Krishnabati Piped Water Supply Scheme at Purbasthali-II Block , SM/07827 | Retrofitting | NAME OF THE WORK -RESTORATION WORK OF BIDYANAGAR TO VIA DAMODAR PARA TO BOGPUR ROAD,PACKAGE NO-WB-22-27,BLOCK-PURBASTHALI-1,GP-SRIRAMPUR & JAHANNAGAR. | 893/JJM | 25/09/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 5.21 | 0 | 0 | 0
1041 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Krishnabati Piped Water Supply Scheme at Purbasthali-II Block , SM/07827 | Retrofitting | Quotation from WBSEDCL for new service connection charges of Krishnabati w/s scheme under Burdwan Division, PHE Dte. (Application No.-5004422952)(Ref. ID-503758136) | 1048/JJM | 30/10/2024 | 0 | WBSEDCL | 7.08 | 0 | 0 | 0
1042 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Krishnabati Piped Water Supply Scheme at Purbasthali-II Block , SM/07827 | Retrofitting | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 618/BWD | 11/02/2025 | 180 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0 | 0
1043 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Krishnabati Piped Water Supply Scheme at Purbasthali-II Block , SM/07827 | Retrofitting | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | 2296/BWD | 20/06/2024 | 616 | M/S DATTA ENTERPRISE | 579.85 | 34.32 | 85.79 | 2
1044 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09714 | Augmentation | Route Survey & Preparation of DPR for BANNABAGRAM PWSS under Durgapur(Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-C] | 101/DSD | 18/02/2022 | 15 | SIRCON ENGINEERING SERVICES | 3.09 | 3.09 | 100 | 1
1045 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09714 | Augmentation | Sinking of additional 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Augmentation of BANANABAGRAM Piped Water Supply Scheme, Block - Ausgram - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]_3RD CALL | 3297/BWD | 29/07/2022 | 45 | ANIRUDDHA FARUQUE | 27.54 | 3.64 | 100 | 1
1046 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09714 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
1047 | PURBA BARDHAMAN | Central Mechanical | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09714 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Bononabagram Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2561/CMD | 06/06/2023 | 30 | SOUVIK HALDER | 10.98 | 0 | 0 | 0
1048 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09714 | Augmentation | Shifting of UPVC Pipeline due to construction of culvert along PWD Road near Bannabagram Hospital of Bannabagram Piped Water Supply Scheme under Ausgram-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-G] | 79/DSD | 11/02/2022 | 30 | M/S UNIQUE | 2.13 | 0 | 0 | 1
1049 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09714 | Augmentation | Laying of pipeline for road crossing due to construction of culvert along PWD Road near Bannabagram Hospital of Bannabagram Piped Water Supply Scheme under Ausgram-I Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr,-D] | 345/DSD | 30/06/2022 | 30 | DUBE ENTERPRISE | 1.07 | 1.07 | 100 | 1
1050 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09714 | Augmentation | Material Requisition To Resource Division | 550/BWD | 27/01/2022 | 0 | Resource Division | 13.66 | 0 | 0 | 0
1051 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09714 | Augmentation | Material Requisition To Resource Division | 1373/BWD | 09/03/2022 | 0 | Resource Division | 3.83 | 0 | 0 | 0
1052 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09714 | Augmentation | Material Requisition To Resource Division | 1562/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
1053 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09714 | Augmentation | Material Requisition To Resource Division | 1203/BWD | 04/03/2022 | 0 | Resource Division | 22.68 | 0 | 0 | 0
1054 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09714 | Augmentation | Material Requisition To Resource Division | 1330/BWD | 08/03/2022 | 0 | Resource Division | 39.95 | 0 | 0 | 0
1055 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09714 | Augmentation | Material Requisition To Resource Division | 4628/BWD | 17/10/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
1056 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09714 | Augmentation | Augmentation of BANNABAGRAM Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 400 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation including construction of switch room without sanitary arrangements Block-Ausgram-I, District:- Purba-Burdwan. | 2497/BWD | 13/05/2022 | 1051 | GHOSH CONCERN | 454.28 | 326.19 | 77.58 | 70
1057 | PURBA BARDHAMAN | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for BONNABAGRAM to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09714 | Augmentation | Additional work for sinking of tube well construction of boundary wall pump house ,inter connection of tube well with allied work for augmentaiton of Bannabagram PWSS of Ausgram Block-I of Purba Bardhaman under DURGAPUR W/S DIVISION,PHE Dte (SM -09714) | 687/DWSD | 28/04/2025 | 180 | SIRAJUL MANDAL | 23.34 | 0 | 0 | 40
1058 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10060 | Augmentation | Route Survey & Preparation of DPR for Satgachia (Zone-I) & (Zone-II) W/S Scheme under Memari-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.4. | 179/BSD | 31/01/2022 | 30 | RADIANT | 4.21 | 2.1 | 100 | 1
1059 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10060 | Augmentation | Restoration work due to laying of 160 mm, 140 mm dia HDPE pipe along with Bardhaman Kalna Road from 31.00kmp to 32.00 kmp with sand filling, GSB, WBM & BM and shoulder portion jhama with moorum consolidation of Augmentation of Satgachia Zone-II water supply scheme "JAL JEEVAN MISSION" under Burdwan Division, PHE Dte. | 195/JJM | 31/05/2023 | 0 | EXECUTIVE ENGINEER PWD BURDWAN DIVISION | 27.42 | 0 | 0 | 0
1060 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10060 | Augmentation | Relaying of damaged pipeline of 90mm HDPE pipeline for FHTC work & shifiting of sluice valve chamber for Road culvert work from Zilla parisad at Satgachia zone-II Piped Water Supply Scheme within Memari-II block under Burdwan Division, PHE Dte. | 1857/BSD | 22/08/2024 | 30 | D.M. ENTERPRISE | 0.93 | 0.92 | 100 | 100
1061 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10060 | Augmentation | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 848/BWD | 05/03/2025 | 120 | PROJECT INDIA | 394.29 | 0 | 0 | 0
1062 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10060 | Augmentation | Extension of pipeline & providing Functional Household Tap Connection (350 Nos. FHTC) from existing distribution system within the command are of SATGACHIA Zone - II Piped W/S. Scheme at (Bohar, Jakra, Raibati) Mouza (14 Nos. Habitation) under Memari - II Block under Burdwan Division, PHE Dte. | 1681/BWD | 10/04/2023 | 45 | G.B. CONSTRUCTION & CO. | 39.5 | 39.47 | 100 | 100
1063 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10060 | Augmentation | Augmentation of SATGACHIA (Zone-II) Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 400 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation under Memari ¿ II Block, District - Purba Bardhaman. | 1900/BWD | 07/04/2022 | 1031 | G.B. CONSTRUCTION & CO. | 391.54 | 349.74 | 92.32 | 100
1064 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10060 | Augmentation | Replacement of Tube-well & Rising main at HEAD TW site for Aug. of PARHATI, SRIDHARPUR, SATGACHIA ZONE-I, SATGACHIA ZONE-II, Piped Water Supply Scheme within MEMARI-II Block under Burdwan Divn., PHE. Dte. District:- Purba-Bardhaman. | 24/BWD | 03/01/2024 | 637 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 54.2 | 10.66 | 100 | 90
1065 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10060 | Augmentation | Repairing damaged Pipeline & concrete road by Cement concrete (mix 1:1.5:3) and drainage system, Sluice valve chamber for FHTC work for SATGACHIA ZONE-I, SATGACHIA ZONE-II, SRIDHARPUR, PARHATI, KUCHUT, NOAHATI, MONDALGRAM PWSS and its adjoining mouzas within MEMARI-II BLOCK under Burdwan Division, PHE Dte. | 2715/BWD | 11/07/2024 | 205 | A.R. TRADERS | 74.28 | 4.99 | 100 | 100
1066 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Repairing and painting of 2 Nos existing Pump House for Kota Chnadipur Pipe Water Supply Scheme, Block- Ausgram-II, under Durgapur Sub-Division, P.H.E Dte. within Burdwan Division P.H.E. Dte. Dist:Purba Bardhaman. [Gr.-E] | 346/DSD | 30/06/2022 | 45 | SUNNY CONSTRUCTION | 2.13 | 0 | 0 | 0
1067 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Route Survey & Preparation of DPR for KOTA-CHANDIPUR PWSS under Ausgram-II under Durgapur (Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-A] | 99/DSD | 18/02/2022 | 15 | SIRCON ENGINEERING SERVICES | 2.74 | 2.74 | 100 | 1
1068 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Sinking of additional 250 X 150mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for KOTACHANDIPUR Piped Water Supply Scheme, Block - Ausgram - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 2202/BWD | 28/04/2022 | 30 | ANIRUDDHA FARUQUE | 10.15 | 9.57 | 100 | 1
1069 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. | 1194/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0 | 0
1070 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
1071 | PURBA BARDHAMAN | Central Mechanical | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation-1 of Kotachandipur Water Supply Scheme [ Block- Ausgram-I ] at Tube well No.-3 under CMD, PHE Dte., Dist.- Purba-Bardhaman | 2100/CMD | 08/09/2022 | 30 | DELTA ENGINEERING ENTERPRISE | 11.65 | 11.4 | 97.8 | 0
1072 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Work Order for Augmentation of Kota-Chandipur Water Supply Scheme with LDS, Rising Main, FHTC work, Pump House & Boundary Wall of Ausgram ¿ II Block in Burdwan (North) Sub-Division, District ¿ Purba Bardhaman under Burdwan Division, PHE. Dte. | 7088/BWD | 22/12/2021 | 150 | TIRUPATI ENTERPRISES | 218.89 | 218.04 | 100 | 1
1073 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Dignagar, Galsi, Barabelun & Kotachandipur Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. Dte. _2ND CALL | 3624/BWD | 22/08/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.76 | 3.69 | 100 | 1
1074 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Construction of drain at new 3rd Tube well site of Augmentation of Kota Chandipur water supply scheme, Block-Ausgram-II within Durgapur (Bardhaman North) Sub-Division, under Burdwan Division, Phe Dte.[SL-03] | 169/DSD | 18/04/2023 | 21 | PARTHA RAY | 0.96 | 0.93 | 100 | 100
1075 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Construction of pathway at new 3rd Tube well site of Augmentation of Kota Chandipur water supply scheme, Block-Ausgram-II within Durgapur (Bardhaman North) Sub-Division, under Burdwan Division, Phe. Dte.[SL-05] | 171/DSD | 18/04/2023 | 21 | M/S MUKHERJEE CONSTRUCTION | 0.96 | 0.95 | 100 | 100
1076 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Ground development at new 3rd Tube well site of Augmentation of Kota Chandipur water supply scheme, Block-Ausgram-II within Durgapur (Bardhaman North) Sub-Division, under Burdwan Division, Phe. Dte.[SL-04] | 170/DSD | 18/04/2023 | 21 | M/S MUKHERJEE CONSTRUCTION | 0.91 | 0.91 | 100 | 100
1077 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Restoration of village Road dismantled by laying pipeline for providing FHTC at Kota Ankure para, Bauripara & Loharpara under Augmentation of KOTA-CHANDIPUR Piped Water Supply Scheme under Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [SL-07] | 181/DSD | 18/04/2023 | 21 | PARTHA RAY | 0.96 | 0.95 | 100 | 100
1078 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Colour washing, lettering, earthling and other allied works of RCC elevated reservoir (Capacity-200 cum) in connection with Augmentation of Kota-Chandipur water supply scheme within Durgapur (Bardhaman North) Sub-Division, PHE Dte, Block-Ausgram-II under Burdwan Division, PHE Dte. [SL-21] | 720/DSD | 30/12/2022 | 30 | TIRUPATI ENTERPRISES | 1.85 | 1.83 | 100 | 100
1079 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Retrofitting of RCC elevated reservoir (Capacity-200 cum) by shotcreting, guinting etc. connection with Augmentation of Kota-Chandipur water supply scheme within Durgapur (Bardhaman North) Sub-Division, PHE Dte, Block-Ausgram-II under Burdwan Division, PHE Dte. [SL-22] | 721/DSD | 30/12/2022 | 30 | P. ENTERPRISE | 2.98 | 2.95 | 100 | 100
1080 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Material Requisition To Resource Division | 7347/BWD | 30/12/2021 | 0 | Resource Division | 6.59 | 0 | 0 | 0
1081 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Material Requisition To Resource Division | 558/BWD | 27/01/2022 | 0 | Resource Division | 6.51 | 0 | 0 | 0
1082 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Material Requisition To Resource Division | 771/BWD | 07/02/2022 | 0 | Resource Division | 18.27 | 0 | 0 | 0
1083 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Material Requisition To Resource Division | 1384/BWD | 09/03/2022 | 0 | Resource Division | 3.83 | 0 | 0 | 0
1084 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Material Requisition To Resource Division | 1561/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
1085 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Material Requisition To Resource Division | 1329/BWD | 08/03/2022 | 0 | Resource Division | 18.37 | 0 | 0 | 0
1086 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Quotation for new connection charges for Augmentation of Kotachandipur w/s scheme under Burdwan Division, PHE Dte. T.W. No.-3 [Application No.-5003543454, dt.-05/12/2022, Ref. ID-503235377] | 916/DW | 30/12/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.02 | 0 | 0 | 0
1087 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for KOTACHANDIPUR to accommodate FHTC under Jal Sapno Mission under Ausgram-II Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09699 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of Augmentation of KOTA-CHANDIPUR Piped Water Supply Scheme [Retrofitting] at Kota (Part), village, habitation, Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. | 5358/BWD | 06/12/2023 | 30 | DEBJYOTI GOSWAMI | 9.29 | 8.52 | 100 | 100
1088 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block , SM/08101 | Retrofitting | Construction of boundary wall (Back side of OHR) including land development & Pumping out of water at Pump house no - 1 Site of Nabagram Water Supply Scheme under Jamalpur Dev. Block of Burdwan Division, PHE Dte. (Length -50.00 Mtr, Col-20 Nos). Gr.G. | 472/BSD | 21/03/2022 | 45 | MOHAMMAD ISSA | 3.77 | 0 | 0 | 1
1089 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block , SM/08101 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nabagram Piped Water Supply Scheme at Ajhapur (Part) (Masagram Habitation), Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 115/2020-2021 OF SE/CC/PHE. DTE.) | 1402/BWD | 15/02/2021 | 60 | M/S ASHA CONSTRUCTION | 67.11 | 94.19 | 164.53 | 1
1090 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block , SM/08101 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nabagram Piped Water Supply Scheme at Ajhapur (Part) (Ajhapur Habitation), Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement no. 116/SE/CC/PHE/Dte of 2020-2021) | 1515/BWD | 19/02/2021 | 60 | S.S. CONSTRUCTION | 75.65 | 150.48 | 200 | 0
1091 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block , SM/08101 | Retrofitting | Providing FHTC for 100% coverage at Nabagram, Basishta Pur, Keliri, Ajhapur & Dattapur Mouza (Village) for NABAGRAM Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 3716/BWD | 24/08/2023 | 30 | M/S UNIQUE | 23.77 | 23.65 | 100 | 50
1092 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block , SM/08101 | Retrofitting | Laying of pipeline for providing FHTC 100% coverage and also construction & installation of Sluice Valve & Valve Chamber to control the flow of water, road restoration work etc. of different Piped W/S Schemes, Block Jamalpur under Burdwan Division, PHE Dte. | 2488/BWD | 01/07/2024 | 550 | M/S NATIONAL CONSTRUCTION | 480.97 | 0 | 0 | 80
1093 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Nabagram Piped Water Supply Scheme at Jamalpur Block , SM/08101 | Retrofitting | Sinking of 300 mm X 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) with construction of Pump House, Boundary wall, Land Development and Rising main connection of NABAGRAM Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman under Burdwan Division PHE Dte. [FOR 3rd. TUBE WELL SITE]. | 784/BWD | 27/02/2024 | 490 | ANIRUDDHA FARUQUE | 29.04 | 10.84 | 37.7 | 35
1094 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/10130 | Augmentation | Route Survey & Preparation of DPR for Kaity W/S Scheme under Raina-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.16. | 191/BSD | 31/01/2022 | 30 | RADIANT | 3.43 | 3.42 | 100 | 1
1095 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/10130 | Augmentation | Quotation for shifting of 25 KVA DTR along with 11 KV HTOH Kaity Feeder at Kaity PHE campus under Madhabdihi-CCC. [Ref Id-860252403] | 726/DW/22-23 | 03/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.71 | 0 | 0 | 0
1096 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/10130 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
1097 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/10130 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 3rd TW Site of Aug. KAITY & its adjoining mouzas Piped Water Supply Scheme, Block ¿ Raina ¿ II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 5281/BWD | 01/12/2022 | 30 | MUNSHI ENTERPRISE | 11.34 | 0 | 0 | 0
1098 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/10130 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of KAITY & its adjoining mouzas Piped Water Supply Scheme, Block - Raina - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 5026/BWD | 10/11/2022 | 30 | M/S D. PALIT & CO. | 10.06 | 8.33 | 100 | 1
1099 | PURBA BARDHAMAN | Central Mechanical | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/10130 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring of Tube Well No- 01 & 02 at Augmentation Kaity [Block ¿Raina-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1082/CMD | 03/03/2023 | 30 | JOYGURU ENTERPRISE | 12.31 | 11.96 | 100 | 100
1100 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/10130 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for KAITY its Adjoining Mouza W/S Scheme, Block -Raina-II within Burdwan Sub-Division, PHE Dte. (Mouza- DURGABATI) | 503/BSD | 21/03/2023 | 45 | DEBJYOTI GOSWAMI | 3.61 | 2.85 | 100 | 100
1101 | PURBA BARDHAMAN | Central Mechanical | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/10130 | Augmentation | Installation of Electro-mechanical accessories at Kaity PH-1 (replacement T.W) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman | 4352/CMD | 20/09/2023 | 30 | MITRA ENTERPRISE | 3.28 | 3.28 | 100 | 100
1102 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/10130 | Augmentation | Material Requisition To Resource Division | 1385/BWD | 09/03/2022 | 0 | Resource Division | 4.26 | 0 | 0 | 0
1103 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/10130 | Augmentation | Material Requisition To Resource Division | 1550/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
1104 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/10130 | Augmentation | 02 Nos. Quotation for new connection of WBSEDCL of Augmentation of Kaity water supply scheme. | 302/JJM/23-24 | 28/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 12.21 | 0 | 0 | 0
1105 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/10130 | Augmentation | Augmentation of KAITY Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 700 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under RAINA- II Block, District:- Purba-Burdwan. | 2930/BWD | 28/06/2022 | 365 | SK ALIM | 689.36 | 688.91 | 100 | 100
1106 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KAITY PWSS to accommodate FHTC in Raina-II block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/10130 | Augmentation | Allied works for Augmentation of KAITY W/S Scheme under Burdwan Division, PHE. Dte. | 3034/BWD | 14/07/2023 | 90 | SK ALIM | 122.65 | 114.07 | 100 | 100
1107 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08707 | Retrofitting | Providing Functional Household Tap Connection from existing distribution system within the command area of JAGGESWARDIHI PWSS under Sitalgram village under Mongalkote Block within Katwa Sub-Division under Burdwan Division PHE Dte. | 3150/BWD | 20/07/2022 | 30 | BAMDEB CONSTRUCTION & CO | 15.4 | 13.71 | 100 | 1
1108 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08707 | Retrofitting | Extension of pipeline from the existing distribution system within scheme jurisdiction at Kanaidanga under Jaggeswardihi piped water supply scheme under Mongalkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-2] | 82/KTS | 09/02/2021 | 15 | HAMID SK | 1.25 | 0 | 0 | 1
1109 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08707 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Mongalkote Block under Burdwan Division, PHE. Dte. | 284/BWD | 17/01/2022 | 30 | BABUL SK | 6.81 | 4 | 100 | 1
1110 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08707 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jageswardihi Piped Water Supply Scheme at Kaichar & Sitalgram Village (Mouza), Mongolkot Block under Burdwan Division, PHE Dte. | 6694/BWD | 01/12/2021 | 60 | HAMID SK | 58.77 | 17.29 | 100 | 1
1111 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08707 | Retrofitting | Surging of existing tube well at 1st , 2nd and 3rd Tube Well Site at Jaggeswardihi under Jaggeswardihi Piped Water Supply Scheme under Mongalkote Block under Katwa Sub-Division within Burdwan Division, P.H.E.Dte [Sl No-02] | 149/KTS | 23/02/2022 | 15 | PARTHA PRATIM ACHARYA | 1.03 | 1.03 | 100 | 1
1112 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08707 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Jaggeswardihi village under Jaggeswardihi PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.. [Sl No-03] | 170/KTS | 25/02/2022 | 7 | BABUL SK | 2.05 | 2.02 | 100 | 1
1113 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08707 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of JAGGESWARDIHI and its adjoining mouzas Piped Water Supply Scheme, Block Mongalkote, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 4959/BWD | 09/11/2022 | 30 | ANIRUDDHA FARUQUE | 13.08 | 9.22 | 100 | 1
1114 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08707 | Retrofitting | Extension of pipe line at Kaichar Paschim Para from the existing Distribution System within scheme jurisdiction under Jaggeswardihi PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-06] | 173/KTS | 25/02/2022 | 15 | BABUL SK | 4.67 | 4.67 | 100 | 1
1115 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08707 | Retrofitting | Extension of pipe line at Kaichar Khane Para from the existing Distribution System within scheme jurisdiction under Jaggeswardihi PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-04] | 171/KTS | 25/02/2022 | 15 | BABUL SK | 4.64 | 4.64 | 100 | 1
1116 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08707 | Retrofitting | Quotation from WBSEDCL for additional T/W at Jaggeswardihi w/s scheme under Burdwan Division, PHE Dte. | 1035/JJM | 25/10/2024 | 0 | WBSEDCL | 3.22 | 0 | 0 | 0
1117 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08707 | Retrofitting | Construction of Pump House, Boundary walls and Raising Main for Aug. of JAGGESWARDIHI Piped Water Supply Scheme under Mongalkote Block, District:- Purba-Bardhaman. | 5494/BWD | 13/12/2023 | 385 | PAPRI HAZRA | 10.13 | 7.39 | 72.93 | 75
1118 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08707 | Retrofitting | Providing FHTC (151 Nos.) of the left out house hold at Ichak habitation including Laying of pipe line from the existing Distribution System within the command area of JAGGESWARDIHI Piped Water Supply Scheme at Mangalkote Block under Katwa Sub-Division under Burdwan Division, PHE Dte. | 495/BWD | 28/01/2025 | 30 | ABDUL HAI | 8.3 | 0 | 0 | 0
1119 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kaichar, Sitalgram, Haripur and Mathrun mouzas within the command area of Jageswardihi piped Water Supply Scheme at Mangolkote Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08707 | Retrofitting | Clearing the compound premises of Head Work Site of Jaggeswardihi PWSS under Block- Mongalkote under Katwa Sub-Division within Burdwan Division PHE Dte. (Sl No-01) | 268/KTS | 21/02/2025 | 15 | PURBA KANDRA CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 0.96 | 0 | 0 | 100
1120 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. , SM/12080 | Retrofitting | Connection of CGWB Tube well Raising Main Line of Head Work Site of Kashiyara Piped Water Supply Scheme within Katwa Sub-Division under Burdwan Division, P.H.E. Dte. (Sl No-1) | 635/KTS | 20/09/2021 | 15 | ASMA ENTERPRISE | 0.92 | 0.94 | 100 | 1
1121 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. , SM/12080 | Retrofitting | Extention of pipe line for providing FHTC from existing Distribuation System within scheme jurisdiction in Kashiara Piped Water Supply Scheme at Gotishta Village within Katwa Sub-Division under Burdwan Division PHE Dte. (Sl -3) | 663/KTS | 28/09/2021 | 15 | MAJUMDER ENTERPRISE | 4.84 | 4.81 | 100 | 1
1122 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. , SM/12080 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Gopalbera village under KASIYARA PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl - 1] | 661/KTS | 28/09/2021 | 15 | MAJUMDER ENTERPRISE | 1.26 | 1.23 | 100 | 1
1123 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. , SM/12080 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Kasiyara and Dirghyasoya village under KASIYARA PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl - 2] | 662/KTS | 28/09/2021 | 15 | MAJUMDER ENTERPRISE | 4.56 | 4.56 | 100 | 1
1124 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. , SM/12080 | Retrofitting | Providing Functional Household Tap Connection at Gopalbera , Gotistha, dirghesoa habitation of Gopalbera , Gotistha, Kashiara village of Chanak and Gotistha G.P. from existing distribution system within the command area of Kashiara PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-01) | 127/KTS | 21/02/2022 | 30 | TAPAS KUMAR ROY | 4.83 | 4.73 | 100 | 1
1125 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. , SM/12080 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Chanak village under Kashiara PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. _2nd Call [Sl No-01] | 319/KTS | 25/04/2022 | 21 | ASMA ENTERPRISE | 0.95 | 0.92 | 100 | 1
1126 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PHASE-II BY AREA OF KASIARA PIPED WATER SUPPLY SCHEME AT MONGALKOTE BLOCK UNDER BURDWAN DIVISION PHE DTE. , SM/12080 | Retrofitting | Road crossing through bituminus PWD road by Jack Pushing method of different location under the command area of KASHIARA (SM/12080, SM/15562) & SIMULIA (SM/18459) PWSS under Mongalkote Block under Katwa Sub Division under Burdwan Division, PHE. Dte. | 976/BWD | 13/03/2025 | 45 | MANASH GHOSH | 48.92 | 0 | 0 | 100
1127 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. , SM/11283 | School | Material Requisition To Resource Division | 5398/BWD | 12/12/2022 | 0 | Resource Division | 85 | 0 | 0 | 0
1128 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. , SM/11283 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Purbasthali II Block (16 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | 3595/BWD | 17/08/2022 | 30 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 17.9 | 16.44 | 91.81 | 0
1129 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. , SM/11283 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Monteswar Block (47 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-C). | 3661/BWD | 29/08/2022 | 45 | MITHU BUILDERS | 52.73 | 45.16 | 100 | 0
1130 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. , SM/11283 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Kalna-I Block (43 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte._2ND CALL. | 3806/BWD | 02/09/2022 | 45 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 48.36 | 42.83 | 100 | 100
1131 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. , SM/11283 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Purbasthali ¿ I Block (36 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | 3418/BWD | 05/08/2022 | 30 | HAMID SK | 40.56 | 36.13 | 100 | 0
1132 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. , SM/11283 | School | Material Requisition To Resource Division | 3300/BWD | 29/07/2022 | 0 | Resource Division | 104.7 | 0 | 0 | 0
1133 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. , SM/11283 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Monteswar Block (50 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-B). | 3665/BWD | 29/08/2022 | 45 | SUKALPA NIRMAN | 56.36 | 51.46 | 100 | 50
1134 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(290 nos) for 100% School Coverage in Purba Bardhaman within Kalna Sub Division under Burdwan Division P.H.E. DTE. , SM/11283 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Monteswar Block (50 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-A). | 3662/BWD | 29/08/2022 | 45 | SUPRIYA RAY | 56.36 | 51.31 | 100 | 100
1135 | PURBA BARDHAMAN | Burdwan Division | Karatia Piped Water Supply Scheme , SM/13397 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 4.22 | 0 | 0 | 0
1136 | PURBA BARDHAMAN | Burdwan Division | Karatia Piped Water Supply Scheme , SM/13397 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.44 | 0 | 0 | 0
1137 | PURBA BARDHAMAN | Burdwan Division | Karatia Piped Water Supply Scheme , SM/13397 | New | Material Requisition To Resource Division | 4875/BWD | 10/11/2023 | 0 | Resource Division | 25.7 | 0 | 0 | 0
1138 | PURBA BARDHAMAN | Central Mechanical | Karatia Piped Water Supply Scheme , SM/13397 | New | New service connection charges for Karatia PWSS TW-2 | BP-2023-24-161 | 18/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.19 | 0 | 0 | 0
1139 | PURBA BARDHAMAN | Central Mechanical | Karatia Piped Water Supply Scheme , SM/13397 | New | New service connection charges for Karatia PWSS TW-1 | BP-2023-24-117 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.9 | 0 | 0 | 0
1140 | PURBA BARDHAMAN | Burdwan Division | Karatia Piped Water Supply Scheme , SM/13397 | New | Continuation work for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-II) on hire basis for the office of the assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE.Govt. of West Bengal (for the period of December'2023 to May'2024) | 877/DSD | 30/11/2023 | 183 | SUJAUDDIN SEKH | 0.87 | 0.36 | 41.56 | 50
1141 | PURBA BARDHAMAN | Burdwan Division | Karatia Piped Water Supply Scheme , SM/13397 | New | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/06/2024 to 31/07/2024) | 411/DSD | 28/05/2024 | 61 | SUJAUDDIN SEKH | 0.8 | 0 | 0 | 0
1142 | PURBA BARDHAMAN | Central Mechanical | Karatia Piped Water Supply Scheme , SM/13397 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
1143 | PURBA BARDHAMAN | Burdwan Division | Karatia Piped Water Supply Scheme , SM/13397 | New | KARATIA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3082/BWD | 18/07/2023 | 898 | BANSBERIA CONSTRUCTION CO. | 578.76 | 442.43 | 76.44 | 95
1144 | PURBA BARDHAMAN | Durgapur W/S Division | Karatia Piped Water Supply Scheme , SM/13397 | New | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 0 | 1
1145 | PURBA BARDHAMAN | Central Mechanical | Karatia Piped Water Supply Scheme , SM/13397 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Karatia Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3172/CMD | 26/07/2023 | 30 | C.M. ENTERPRISE | 27.12 | 21.33 | 95.16 | 96
1146 | PURBA BARDHAMAN | Burdwan Division | UKHRID PIPED WATER SUPPLY SCHEME , SM/13505 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 31.25 | 0 | 0 | 0
1147 | PURBA BARDHAMAN | Burdwan Division | UKHRID PIPED WATER SUPPLY SCHEME , SM/13505 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 12.6 | 0 | 0 | 0
1148 | PURBA BARDHAMAN | Burdwan Division | UKHRID PIPED WATER SUPPLY SCHEME , SM/13505 | New | Material Requisition To Resource Division | 5234/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
1149 | PURBA BARDHAMAN | Central Mechanical | UKHRID PIPED WATER SUPPLY SCHEME , SM/13505 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
1150 | PURBA BARDHAMAN | Central Mechanical | UKHRID PIPED WATER SUPPLY SCHEME , SM/13505 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Ukhrid Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4019/CMD | 29/08/2023 | 30 | C.M. ENTERPRISE | 28.88 | 23.89 | 100 | 100
1151 | PURBA BARDHAMAN | Central Mechanical | UKHRID PIPED WATER SUPPLY SCHEME , SM/13505 | New | Quotation for new service connection at Ukhrid W/S Scheme PH-II. | BP-2023-24-304 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.29 | 0 | 0 | 0
1152 | PURBA BARDHAMAN | Central Mechanical | UKHRID PIPED WATER SUPPLY SCHEME , SM/13505 | New | Quotation for new service connection at UKHRID W/S Scheme PH-I. | BP-2023-24-303 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.54 | 0 | 0 | 0
1153 | PURBA BARDHAMAN | Burdwan Division | UKHRID PIPED WATER SUPPLY SCHEME , SM/13505 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA, BALABATI, UKHRID & RUPSA Piped Water Supply Scheme under KHANDAGHOSH Block, District:- Purba Bardhaman [NEW SCHEME] | 1726/BWD | 13/04/2023 | 902 | S.P. CONSTRUCTION | 1710.27 | 276.07 | 64.01 | 45
1154 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 5.72 | 0 | 0 | 0
1155 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | Material Requisition To Resource Division | 4307/BWD | 29/09/2023 | 0 | Resource Division | 78.8 | 0 | 0 | 0
1156 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/08/2024 to 30/09/2024) | 602/DSD | 30/07/2024 | 61 | SUJAUDDIN SEKH | 0.8 | 0.19 | 47.94 | 100
1157 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/10/2024 to 30/11/2024) | 772/DSD | 18/09/2024 | 61 | SUJAUDDIN SEKH | 0.8 | 0.26 | 64.54 | 0
1158 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | Material Requisition To Resource Division | 329/BWD | 24/01/2024 | 0 | Resource Division | 36.64 | 0 | 0 | 0
1159 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | NEW SERVICE CONNECTION FOR JAMNA PWSS TW -2. | BP-2023-24-646 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.48 | 0 | 0 | 0
1160 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | Alt&ment of Fund due to damaged causes by PHED pipe tine work in connection with the work namely Construction of road from Jamna Samabay Samiti on PWD (Roads) to Moynampur more on Memari- Monteswar PWD Road via Dheuchanda, Katsihi Village under Monteswar Block in the District Purba Bardhaman under RIDF-XXVI¦I | 1051/JJM | 05/11/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 10.97 | 0 | 0 | 0
1161 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | NEW SERVICE CONNECTION FOR JAMNA PWSS. | BP-2023-24-572 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.32 | 0 | 0 | 0
1162 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BELENDA, JAMNA, PIPLON & PARGUNA Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | 4388/BWD | 05/10/2023 | 667 | AKASH CONSTRUCTION | 2296.4 | 190.98 | 31.8 | 50
1163 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | Balance work for laying of pipeline, providing FHTC & other allied works in connection with Augmentation of MONTESWAR PWSS & SUTRA PWSS (SM/13280) under Kalna Sub-Division under Burdwan Division, PHE Dte. | 3572/BWD | 27/09/2024 | 181 | BAKSHI ENTERPRISE | 51.14 | 0 | 0 | 30
1164 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
1165 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/12/2024 to 31/12/2024) | 992/DSD | 25/11/2024 | 61 | SUJAUDDIN SEKH | 0.4 | 0.17 | 86.45 | 0
1166 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | Continuation for Supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/04/2025 to 31/05/2025) | 483/DSD | 21/03/2025 | 61 | SK ALACK JANDER | 0.8 | 0.25 | 63.04 | 0
1167 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | Supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/02/2025 to 31/03/2025) | 142/DSD | 24/01/2025 | 59 | SK ALACK JANDER | 0.8 | 0.27 | 67.45 | 0
1168 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR JAMNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13291 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Jamna Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4048/CMD | 29/08/2023 | 703 | MS DAS ELECTRIC CO | 29.95 | 0 | 0 | 50
1169 | PURBA BARDHAMAN | Central Mechanical | SATINANDI PIPED WATER SUPPLY SCHEME , SM/13494 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Satinandi Water Supply Scheme [ Block- Galsi-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2496/CMD | 01/06/2023 | 30 | DEY ENTERPRISE | 27.74 | 20.12 | 72.52 | 50
1170 | PURBA BARDHAMAN | Burdwan Division | SATINANDI PIPED WATER SUPPLY SCHEME , SM/13494 | New | Material Requisition To Resource Division | 1264/BWD | 17/03/2023 | 0 | Resource Division | 8.15 | 0 | 0 | 0
1171 | PURBA BARDHAMAN | Burdwan Division | SATINANDI PIPED WATER SUPPLY SCHEME , SM/13494 | New | Material Requisition To Resource Division | 4021/BWD | 08/09/2023 | 0 | Resource Division | 1.24 | 0 | 0 | 0
1172 | PURBA BARDHAMAN | Burdwan Division | SATINANDI PIPED WATER SUPPLY SCHEME , SM/13494 | New | Material Requisition To Resource Division | 4906/BWD | 10/11/2023 | 0 | Resource Division | 33.07 | 0 | 0 | 0
1173 | PURBA BARDHAMAN | Central Mechanical | SATINANDI PIPED WATER SUPPLY SCHEME , SM/13494 | New | New service connection charges of Satinandi Water Supply Scheme TW-2 | BP-2023-24-26 | 21/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.05 | 0 | 0 | 0
1174 | PURBA BARDHAMAN | Central Mechanical | SATINANDI PIPED WATER SUPPLY SCHEME , SM/13494 | New | New service connection charges of Satinandi Water Supply Scheme TW-1 | BP-2023-24-25 | 21/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.08 | 0 | 0 | 0
1175 | PURBA BARDHAMAN | Central Mechanical | SATINANDI PIPED WATER SUPPLY SCHEME , SM/13494 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
1176 | PURBA BARDHAMAN | Burdwan Division | SATINANDI PIPED WATER SUPPLY SCHEME , SM/13494 | New | SATINANDI Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Burdwan-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | 5520/BWD | 23/12/2022 | 365 | MD HASIN | 389.47 | 389.47 | 100 | 40
1177 | PURBA BARDHAMAN | Durgapur W/S Division | SATINANDI PIPED WATER SUPPLY SCHEME , SM/13494 | New | Material Requisition To Resource Division | 1724/A/DWSD | 10/12/2024 | 0 | Resource Division | 0.31 | 0 | 0 | 0
1178 | PURBA BARDHAMAN | Durgapur W/S Division | SATINANDI PIPED WATER SUPPLY SCHEME , SM/13494 | New | Acceptance cum Formal Work Order for SATINANDI Piped Water Supply Scheme with INSTALLATION OF BARBED WIRE, FHTC ,Road restoration ,DEMOLITION WORK & land development with road at TW site under Galsi-II Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte. | 1620/DWSD | 26/11/2024 | 326 | A K SIKDAR | 79.05 | 0 | 0 | 70
1179 | PURBA BARDHAMAN | Durgapur W/S Division | SATINANDI PIPED WATER SUPPLY SCHEME , SM/13494 | New | Acceptance cum Formal Work Order for Sinking of 300 x 200 mm dia tube well 150 mtr depth by DR Rig method for trial bore at Tetulmari & Golgram under Satinandi PWSS (JJM), Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 1596/DWSD | 25/11/2024 | 20 | S & P ENTERPRISE | 7.5 | 0 | 0 | 60
1180 | PURBA BARDHAMAN | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME , SM/13506 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.9 | 0 | 0 | 0
1181 | PURBA BARDHAMAN | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME , SM/13506 | New | Material Requisition To Resource Division | 3987/BWD | 08/09/2023 | 0 | Resource Division | 4.94 | 0 | 0 | 0
1182 | PURBA BARDHAMAN | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME , SM/13506 | New | Material Requisition To Resource Division | 5103/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
1183 | PURBA BARDHAMAN | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME , SM/13506 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | 2751/BSD | 28/11/2023 | 183 | SK.ASFIA | 2.4 | 0.4 | 99.88 | 70
1184 | PURBA BARDHAMAN | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME , SM/13506 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-09-2024 to 30-11-2024 | 1957/BSD | 30/08/2024 | 91 | SK. ASFIA | 1.2 | 0.4 | 99.88 | 60
1185 | PURBA BARDHAMAN | Central Mechanical | DEHA PIPED WATER SUPPLY SCHEME , SM/13506 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at DEHA Water Supply Scheme [ Block- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4092/CMD | 29/08/2023 | 491 | ORIENTAL ENGINEERING CO. | 29.39 | 20.12 | 82.69 | 100
1186 | PURBA BARDHAMAN | Central Mechanical | DEHA PIPED WATER SUPPLY SCHEME , SM/13506 | New | Quotation for new electric service connection at Deha PH NO.-2 | BP-2023-24-241 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.48 | 0 | 0 | 0
1187 | PURBA BARDHAMAN | Central Mechanical | DEHA PIPED WATER SUPPLY SCHEME , SM/13506 | New | Quotation for new electric service connection at Deha PH NO.-1 | BP-2023-24-242 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0 | 0
1188 | PURBA BARDHAMAN | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME , SM/13506 | New | Restoration of concrete road by Cement concrete (mix 1:1.5:3),Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for DURGADANGA SVS & DEHA PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | 141/BWD | 08/01/2025 | 90 | MUKHERJEE ENTERPRISE | 64.37 | 0 | 0 | 0
1189 | PURBA BARDHAMAN | Burdwan Division | DEHA PIPED WATER SUPPLY SCHEME , SM/13506 | New | Continuation Work Order for Supply of one No.Diesel Driven Ambassador Car No. WB:41H-4009 on hire basis for the office of the Assistant Engineer,Burdwan Sub-Division,PHE Dte(Period from 01-03-2025 to 31.05.2025) | 457/BSD | 28/02/2025 | 90 | SK. ASFIA | 1.2 | 0.4 | 99.81 | 100
1190 | PURBA BARDHAMAN | Central Mechanical | HARIPUR PIPED WATER SUPPLY SCHEME , SM/13315 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at HARIPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2931/CMD | 12/07/2023 | 30 | ASHIM UDYOG | 20.77 | 9.37 | 45.12 | 30
1191 | PURBA BARDHAMAN | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME , SM/13315 | New | Material Requisition To Resource Division | 4284/BWD | 29/09/2023 | 0 | Resource Division | 0.55 | 0 | 0 | 0
1192 | PURBA BARDHAMAN | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME , SM/13315 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 10.75 | 0 | 0 | 0
1193 | PURBA BARDHAMAN | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME , SM/13315 | New | Material Requisition To Resource Division | 4905/BWD | 10/11/2023 | 0 | Resource Division | 4.86 | 0 | 0 | 0
1194 | PURBA BARDHAMAN | Central Mechanical | HARIPUR PIPED WATER SUPPLY SCHEME , SM/13315 | New | New service connection charges for Haripur PWSS TW-1 | BP-2023-24-97 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.02 | 0 | 0 | 0
1195 | PURBA BARDHAMAN | Central Mechanical | HARIPUR PIPED WATER SUPPLY SCHEME , SM/13315 | New | Supply and Delivery of standby pump motor set for Sipta, Uchitpur, Haripur & others Water Supply Scheme under CMD, PHE Dte. | 2596/CMD | 27/08/2024 | 30 | JOYGURU ENTERPRISE | 4.72 | 1.65 | 100 | 100
1196 | PURBA BARDHAMAN | Central Mechanical | HARIPUR PIPED WATER SUPPLY SCHEME , SM/13315 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 30
1197 | PURBA BARDHAMAN | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME , SM/13315 | New | HARIPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali I Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1340/BWD | 22/03/2023 | 373 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 94.46 | 67.41 | 92.19 | 100
1198 | PURBA BARDHAMAN | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME , SM/13315 | New | Refitting & Re-fixing of Existing FHTC along with laying of damaged portion Pipeline Due to construction of Concrete Drain by PRI body at Haripur (SM/13315) Piped Water Supply Scheme water supply scheme under Kalna Sub-Division under Burdwan Division, PHE Dte. | 4619/BWD | 31/12/2024 | 30 | MONDAL & CO. | 9.67 | 0 | 0 | 100
1199 | PURBA BARDHAMAN | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME , SM/13315 | New | Different Types of work involved in connection with Augmentation of NAOPARA (SM/09407) & HARIPUR (SM/13315) water supply scheme Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2203/BWD | 13/06/2024 | 344 | MONDAL & CO. | 223.65 | 128.63 | 77.79 | 50
1200 | PURBA BARDHAMAN | Burdwan Division | HARIPUR PIPED WATER SUPPLY SCHEME , SM/13315 | New | Work order for " Provided leftout FHTC at different location of " Haripur& Dastipara Mouzas" under the command area of HARIPUR PWSS(SM/13315) in order to Declare Haripur as "SAJALGRAM" under Kalna Sub-Division under Burdwan Division, PHE Dte." | 304/KSD | 25/02/2025 | 15 | SAYAK DEY | 1.79 | 0 | 0 | 100
1201 | PURBA BARDHAMAN | Burdwan Division | NIRALGACHHI PIPED WATER SUPPLY SCHEME , SM/14436 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 37.35 | 0 | 0 | 0
1202 | PURBA BARDHAMAN | Burdwan Division | NIRALGACHHI PIPED WATER SUPPLY SCHEME , SM/14436 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 20.14 | 0 | 0 | 0
1203 | PURBA BARDHAMAN | Central Mechanical | NIRALGACHHI PIPED WATER SUPPLY SCHEME , SM/14436 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
1204 | PURBA BARDHAMAN | Central Mechanical | NIRALGACHHI PIPED WATER SUPPLY SCHEME , SM/14436 | New | NEW SERVICE CONNECTION FOR NIRALGACHI PWSS TW-I | BP-2024-25-42 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.14 | 0 | 0 | 0
1205 | PURBA BARDHAMAN | Central Mechanical | NIRALGACHHI PIPED WATER SUPPLY SCHEME , SM/14436 | New | Quotation for new service connection at Niralgachi PWSS TW-2. | BP-2024-25-265 | 20/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.28 | 0 | 0 | 0
1206 | PURBA BARDHAMAN | Central Mechanical | NIRALGACHHI PIPED WATER SUPPLY SCHEME , SM/14436 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Niralgachhi Water Supply Scheme [ Block- KALNA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4061/CMD | 29/08/2023 | 644 | M/S, S.S. ENTERPRISE. | 27.79 | 0 | 0 | 90
1207 | PURBA BARDHAMAN | Burdwan Division | NIRALGACHHI PIPED WATER SUPPLY SCHEME , SM/14436 | New | Work Order for "DESIGNING,MAKING AND ERECTION OF SIGN BOARD FOR SAJAL GRAM IN ¿¿4 No... VILLAGE, ¿KALNA-I.. BLOCK UNDER KALNA SUB DIVISION WITHIN BURDWAN DIVISION PHE DTE.(12nos board)". | 1975/KSD | 05/12/2024 | 10 | OMKAR ENTERPRISE | 1.68 | 0 | 0 | 100
1208 | PURBA BARDHAMAN | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME , SM/14438 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.94 | 0 | 0 | 0
1209 | PURBA BARDHAMAN | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME , SM/14438 | New | Material Requisition To Resource Division | 3979/BWD | 08/09/2023 | 0 | Resource Division | 32.04 | 0 | 0 | 0
1210 | PURBA BARDHAMAN | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME , SM/14438 | New | Providing FHTC with laying of 90 mm dia HDPE Pipe of Susunia PWSS of Kuli village under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | 269/DSD | 15/03/2024 | 30 | SOUMYAVASH DAS | 0.94 | 0 | 0 | 0
1211 | PURBA BARDHAMAN | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME , SM/14438 | New | Construction of valve chamber HD works site and installation of sluice valve at Budpur village of Susunia PWSS under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | 268./DSD | 15/03/2024 | 30 | PRONAB KUMAR DEY | 0.94 | 0 | 0 | 0
1212 | PURBA BARDHAMAN | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME , SM/14438 | New | Providing FHTC with laying of 90 mm dia HDPE Pipe of Susunia PWSS under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | 266/DSD | 15/03/2024 | 30 | PRONAB KUMAR DEY | 0.95 | 0 | 0 | 0
1213 | PURBA BARDHAMAN | Central Mechanical | SHUSHNA PIPED WATER SUPPLY SCHEME , SM/14438 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Shushna Water Supply Scheme [ Block- MONTESWAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4062/CMD | 29/08/2023 | 30 | ORIENTAL ENGINEERING CO. | 28.97 | 23.46 | 100 | 80
1214 | PURBA BARDHAMAN | Central Mechanical | SHUSHNA PIPED WATER SUPPLY SCHEME , SM/14438 | New | New service at Shushna PWSS TW-2. | BP-2023-24-440 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.03 | 0 | 0 | 0
1215 | PURBA BARDHAMAN | Central Mechanical | SHUSHNA PIPED WATER SUPPLY SCHEME , SM/14438 | New | New Service connection at SHUSHNA PWSS TW-1. | BP-2023-24-481 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.48 | 0 | 0 | 0
1216 | PURBA BARDHAMAN | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME , SM/14438 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PASCHIM KHARAMPUR, SHUSHNA & SIGHNALI Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | 3494/BWD | 09/08/2023 | 783 | S.P. CONSTRUCTION | 1925.07 | 305.44 | 53.51 | 80
1217 | PURBA BARDHAMAN | Burdwan Division | SHUSHNA PIPED WATER SUPPLY SCHEME , SM/14438 | New | Providing FHTC with laying of 90 mm dia HDPE Pipe of Susunia PWSS of kalsar village under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | 267./DSD | 15/03/2024 | 382 | PRONAB KUMAR DEY | 0.97 | 0 | 0 | 100
1218 | PURBA BARDHAMAN | Central Mechanical | SHUSHNA PIPED WATER SUPPLY SCHEME , SM/14438 | New | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3105/CMD | 11/12/2024 | 60 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0 | 0
1219 | PURBA BARDHAMAN | Central Mechanical | SHUSHNA PIPED WATER SUPPLY SCHEME , SM/14438 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
1220 | PURBA BARDHAMAN | Burdwan Division | BAHIR SARBAMANGALA-B PIPED WATER SUPPLY SCHEME , SM/14979 | New | BAHIRSARBAMANGALA-B Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 2298/BWD | 19/05/2023 | 365 | MLG CONSTRUCTION | 308.66 | 0 | 0 | 0
1221 | PURBA BARDHAMAN | Central Mechanical | BAHIR SARBAMANGALA-B PIPED WATER SUPPLY SCHEME , SM/14979 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bahir Sarbamangala-B Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4046/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 29.34 | 0 | 0 | 0
1222 | PURBA BARDHAMAN | Burdwan Division | BAHIR SARBAMANGALA-B PIPED WATER SUPPLY SCHEME , SM/14979 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.95 | 0 | 0 | 0
1223 | PURBA BARDHAMAN | Burdwan Division | BAHIR SARBAMANGALA-B PIPED WATER SUPPLY SCHEME , SM/14979 | New | Material Requisition To Resource Division | 4032/BWD | 08/09/2023 | 0 | Resource Division | 6.34 | 0 | 0 | 0
1224 | PURBA BARDHAMAN | Burdwan Division | BAHIR SARBAMANGALA-B PIPED WATER SUPPLY SCHEME , SM/14979 | New | Material Requisition To Resource Division | 5095/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
1225 | PURBA BARDHAMAN | Burdwan Division | IBRAMBAD PIPED WATER SUPPLY SCHEME , SM/14444 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 3.02 | 0 | 0 | 0
1226 | PURBA BARDHAMAN | Burdwan Division | IBRAMBAD PIPED WATER SUPPLY SCHEME , SM/14444 | New | Material Requisition To Resource Division | 4052/BWD | 11/09/2023 | 0 | Resource Division | 3.03 | 0 | 0 | 0
1227 | PURBA BARDHAMAN | Burdwan Division | IBRAMBAD PIPED WATER SUPPLY SCHEME , SM/14444 | New | Material Requisition To Resource Division | 3978/BWD | 08/09/2023 | 0 | Resource Division | 32.08 | 0 | 0 | 0
1228 | PURBA BARDHAMAN | Burdwan Division | IBRAMBAD PIPED WATER SUPPLY SCHEME , SM/14444 | New | Material Requisition To Resource Division | 323/BWD | 24/01/2024 | 0 | Resource Division | 34.15 | 0 | 0 | 0
1229 | PURBA BARDHAMAN | Central Mechanical | IBRAMBAD PIPED WATER SUPPLY SCHEME , SM/14444 | New | Quotation for new electric service connection at Ibrambad PH NO.-2 | BP-2023-24-249 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.13 | 0 | 0 | 0
1230 | PURBA BARDHAMAN | Central Mechanical | IBRAMBAD PIPED WATER SUPPLY SCHEME , SM/14444 | New | NEW SERVICE CONNECTION FOR IBRAMBAD PWSS. | BP-2023-24-573 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.51 | 0 | 0 | 0
1231 | PURBA BARDHAMAN | Central Mechanical | IBRAMBAD PIPED WATER SUPPLY SCHEME , SM/14444 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
1232 | PURBA BARDHAMAN | Central Mechanical | IBRAMBAD PIPED WATER SUPPLY SCHEME , SM/14444 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Ibrambad Water Supply Scheme [ Block- Monteswar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4064/CMD | 29/08/2023 | 30 | M/S. S.R. ENTERPRISE | 28.96 | 22.76 | 95.45 | 90
1233 | PURBA BARDHAMAN | Burdwan Division | NRISINHAPUR PIPED WATER SUPPLY SCHEME , SM/14071 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.86 | 0 | 0 | 0
1234 | PURBA BARDHAMAN | Burdwan Division | NRISINHAPUR PIPED WATER SUPPLY SCHEME , SM/14071 | New | Material Requisition To Resource Division | 3974/BWD | 08/09/2023 | 0 | Resource Division | 1.93 | 0 | 0 | 0
1235 | PURBA BARDHAMAN | Burdwan Division | NRISINHAPUR PIPED WATER SUPPLY SCHEME , SM/14071 | New | Material Requisition To Resource Division | 4904/BWD | 10/11/2023 | 0 | Resource Division | 33.07 | 0 | 0 | 0
1236 | PURBA BARDHAMAN | Central Mechanical | NRISINHAPUR PIPED WATER SUPPLY SCHEME , SM/14071 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at NRISINHAPUR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4097/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 28.96 | 11.36 | 39.23 | 48
1237 | PURBA BARDHAMAN | Durgapur W/S Division | NRISINHAPUR PIPED WATER SUPPLY SCHEME , SM/14071 | New | Material Requisition To Resource Division | 1724/D/DWSD | 10/12/2024 | 0 | Resource Division | 2 | 0 | 0 | 0
1238 | PURBA BARDHAMAN | Central Mechanical | NRISINHAPUR PIPED WATER SUPPLY SCHEME , SM/14071 | New | New service connection charges for Nrisinhapur PWSS TW-2 | BP-2024-25-318 | 30/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.63 | 0 | 0 | 0
1239 | PURBA BARDHAMAN | Central Mechanical | NRISINHAPUR PIPED WATER SUPPLY SCHEME , SM/14071 | New | New service connection charges for Nrisinhapur PWSS TW-1 | BP-2023-24-328 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.56 | 0 | 0 | 0
1240 | PURBA BARDHAMAN | Durgapur W/S Division | NRISINHAPUR PIPED WATER SUPPLY SCHEME , SM/14071 | New | Acceptance cum Formal Work Order for Balance work for NIRSINHAPUR Piped Water Supply Scheme i.e , Construction work LDS, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway etc. at 3rd Pump house site under AUSGRAM-II Block, District:- Purba-Bardhaman, under Durgapur W/S Division, PHE Dte. | 1594/DWSD | 25/11/2024 | 367 | KIRON ENTERPRISE | 59.79 | 0 | 0 | 65
1241 | PURBA BARDHAMAN | Burdwan Division | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/14073 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 39.22 | 0 | 0 | 0
1242 | PURBA BARDHAMAN | Burdwan Division | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/14073 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 6.23 | 0 | 0 | 0
1243 | PURBA BARDHAMAN | Central Mechanical | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/14073 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
1244 | PURBA BARDHAMAN | Central Mechanical | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/14073 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
1245 | PURBA BARDHAMAN | Burdwan Division | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/14073 | New | Material Requisition To Resource Division | 200/BWD | 10/01/2024 | 0 | Resource Division | 7.26 | 0 | 0 | 0
1246 | PURBA BARDHAMAN | Burdwan Division | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/14073 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ALIGRAM, JAYKRISHNAPUR, JADABGANJ & KALYANPUR Piped Water Supply Scheme under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 4581/BWD | 16/10/2023 | 965 | SAFECO ENTERPRISES | 1551.98 | 150.45 | 33 | 60
1247 | PURBA BARDHAMAN | Central Mechanical | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/14073 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JAYKRISHNAPUR Water Supply Scheme [ Block- AUSGRAM-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4094/CMD | 29/08/2023 | 588 | MS S G ENTERPRISE | 27.68 | 0 | 0 | 96
1248 | PURBA BARDHAMAN | Durgapur W/S Division | JAYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/14073 | New | ACCEPTANCE CUM FORMAL WORK ORDER FOR Supplying, delivery, Installation of 13 (Thirteen) Nos new PC and upgradation 6 (Six) Nos existing PC including providing other asseries as per office requirement for JJM works under Durgapur W/s Division, PHE Dte under Jaykrishnapur PWSS,Aligram PWSS,Jadabganj PWSS and Kalyanpur PWSS. | 59/DWSD | 10/01/2025 | 45 | DIGITEK SOLUTIONS | 17.56 | 4.65 | 20.94 | 85
1249 | PURBA BARDHAMAN | Burdwan Division | Serpur Piped Water Supply Scheme , SM/13384 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.9 | 0 | 0 | 0
1250 | PURBA BARDHAMAN | Burdwan Division | Serpur Piped Water Supply Scheme , SM/13384 | New | Material Requisition To Resource Division | 4007/BWD | 08/09/2023 | 0 | Resource Division | 2.05 | 0 | 0 | 0
1251 | PURBA BARDHAMAN | Burdwan Division | Serpur Piped Water Supply Scheme , SM/13384 | New | Material Requisition To Resource Division | 5073/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
1252 | PURBA BARDHAMAN | Central Mechanical | Serpur Piped Water Supply Scheme , SM/13384 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
1253 | PURBA BARDHAMAN | Central Mechanical | Serpur Piped Water Supply Scheme , SM/13384 | New | NEW SERVICE CONNECTION FOR SERPUR PWSS PH-2 | BP-2024-25-43 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.23 | 0 | 0 | 0
1254 | PURBA BARDHAMAN | Central Mechanical | Serpur Piped Water Supply Scheme , SM/13384 | New | New Service connection for Serpur W/S Scheme PH No.-I | BP-2023-24-301 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0 | 0
1255 | PURBA BARDHAMAN | Burdwan Division | Serpur Piped Water Supply Scheme , SM/13384 | New | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related(schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-02-2025 to 30-04-2025) | 240/BSD | 31/01/2025 | 66 | PARVIN BEGAM | 0.85 | 0 | 0.46 | 100
1256 | PURBA BARDHAMAN | Central Mechanical | Serpur Piped Water Supply Scheme , SM/13384 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Serpur Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3994/CMD | 29/08/2023 | 549 | S.P. CONSTRUCTION | 28.92 | 23.04 | 95.5 | 80
1257 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block , SM/07814 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ORGRAM Piped Water Supply Scheme & Sibda Colony habitation, Bhatar Block under Burdwan Division, PHE Dte.(Agreement No. 59/2020-2021 OF SE/CC/PHE. DTE.) | 4886/BWD | 07/12/2020 | 90 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 97.01 | 28.41 | 100 | 1
1258 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block , SM/07814 | Retrofitting | Construction of 300 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pipe connection and cost of pipes, specials for Orgram (Zone-I) & it's adjoining mouzas W/S. scheme under Burdwan Division, P.H.E. Dte.Ref. Drawing No.PC-I/OHR/7/2012 Dated 07.06.2012. | 764/BWD | 07/02/2022 | 180 | S.N. ENTERPRISE | 67.98 | 0 | 0 | 0
1259 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block , SM/07814 | Retrofitting | Shifting and relaying of Distribution system and Rising main at OHR site of Orgram Piped W/S Scheme (Zone-II) at Bhatar Block under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. | 655/DSD | 24/08/2023 | 30 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 0.75 | 0 | 0 | 0
1260 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block , SM/07814 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ORGRAM Piped Water Supply Scheme at Salkuni, Orgram (10 Nos Habitation), & Silakote Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte._2ND CALL.(Agreement no. 102/SE/CC/PHE/Dte of 2020-2021) | 1086/BWD | 08/02/2021 | 90 | SUPER CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 81.92 | 44.04 | 100 | 1
1261 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block , SM/07814 | Retrofitting | Extension of distribution main for providing FHTC at Shikarpur village within Orgram W/S Scheme (Zone-II) in Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-E] | 719/DSD | 17/12/2021 | 30 | DHIRENDRANATH SOM | 3.28 | 3.28 | 100 | 1
1262 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block , SM/07814 | Retrofitting | Extension of distribution main for providing FHTC at Shilakot village within Orgram W/S Scheme (Zone-II) in Bhatar Block under Burdwan Division, P.H.E. Dte.[Gr.-D] | 718/DSD | 17/12/2021 | 30 | DHIRENDRANATH SOM | 3.15 | 3.1 | 100 | 1
1263 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block , SM/07814 | Retrofitting | Extension of distribution main for providing FHTC at Shalkuni village within Orgram W/S Scheme (Zone-II) in Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-C] | 717/DSD | 17/12/2021 | 30 | DHIRENDRANATH SOM | 3.62 | 3.62 | 100 | 1
1264 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block , SM/07814 | Retrofitting | Extension of pipeline at Bagmara village of Orgram (Z-II) and its adjoining mouzas piped water supply scheme at Bhatar Block within Burdwan Sadar Sub-Division, under Burdwan Division, PHE Dte.[Gr.-G] | 952/BSD | 23/07/2021 | 30 | M/S S. CHOUDHURY | 2.01 | 0 | 0 | 1
1265 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block , SM/07814 | Retrofitting | Vehicle bill (Car No.-WB-41H-3668) for the month of July to September'2023. | 1142/JJM | 29/12/2023 | 0 | MD HASIN | 0.86 | 0 | 0 | 0
1266 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Orgram Piped Water Supply Scheme at Bhatar Block , SM/07814 | Retrofitting | Restoration of damaged flanks due to laying of HDPE pipe line along the flank of Burdwan Katwa Road from 14.70 kmp to 16.20 kmp in the district of Purba Bardhaman under Bardhaman Division,P.W.D. | 867/JJM | 23/09/2024 | 0 | EXECUTIVE ENGINEER PWD BURDWAN DIVISION | 7.9 | 0 | 0 | 0
1267 | PURBA BARDHAMAN | Burdwan Division | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For Paschim Kharampur PWSS in Manteshwar Block of Burdwan District under Burdwan Division, PHE Dte. , SM/13332 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 14.14 | 0 | 0 | 0
1268 | PURBA BARDHAMAN | Burdwan Division | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For Paschim Kharampur PWSS in Manteshwar Block of Burdwan District under Burdwan Division, PHE Dte. , SM/13332 | New | Material Requisition To Resource Division | 3976/BWD | 08/09/2023 | 0 | Resource Division | 103.5 | 0 | 0 | 0
1269 | PURBA BARDHAMAN | Burdwan Division | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For Paschim Kharampur PWSS in Manteshwar Block of Burdwan District under Burdwan Division, PHE Dte. , SM/13332 | New | Material Requisition To Resource Division | 324/BWD | 24/01/2024 | 0 | Resource Division | 92.56 | 0 | 0 | 0
1270 | PURBA BARDHAMAN | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For Paschim Kharampur PWSS in Manteshwar Block of Burdwan District under Burdwan Division, PHE Dte. , SM/13332 | New | New Service connection at PASCHIM KHARAMPUR PWSS TW-1. | BP-2023-24-479 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.89 | 0 | 0 | 0
1271 | PURBA BARDHAMAN | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For Paschim Kharampur PWSS in Manteshwar Block of Burdwan District under Burdwan Division, PHE Dte. , SM/13332 | New | New service Paschim Kharapur PWSS TW-2. | BP-2023-24-441 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.93 | 0 | 0 | 0
1272 | PURBA BARDHAMAN | Burdwan Division | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For Paschim Kharampur PWSS in Manteshwar Block of Burdwan District under Burdwan Division, PHE Dte. , SM/13332 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PASCHIM KHARAMPUR, SHUSHNA & SIGHNALI Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | 3494/BWD | 09/08/2023 | 783 | S.P. CONSTRUCTION | 1925.07 | 590.23 | 77.51 | 80
1273 | PURBA BARDHAMAN | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For Paschim Kharampur PWSS in Manteshwar Block of Burdwan District under Burdwan Division, PHE Dte. , SM/13332 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
1274 | PURBA BARDHAMAN | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For Paschim Kharampur PWSS in Manteshwar Block of Burdwan District under Burdwan Division, PHE Dte. , SM/13332 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Paschim Kharampur Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4049/CMD | 29/08/2023 | 609 | MITRA ENTERPRISE | 29.57 | 23.57 | 95.6 | 85
1275 | PURBA BARDHAMAN | Burdwan Division | MOUDANGA PIPED WATER SUPPLY SCHEME , SM/14020 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 14.15 | 0 | 0 | 0
1276 | PURBA BARDHAMAN | Burdwan Division | MOUDANGA PIPED WATER SUPPLY SCHEME , SM/14020 | New | Material Requisition To Resource Division | 4035/BWD | 08/09/2023 | 0 | Resource Division | 1.38 | 0 | 0 | 0
1277 | PURBA BARDHAMAN | Burdwan Division | MOUDANGA PIPED WATER SUPPLY SCHEME , SM/14020 | New | Material Requisition To Resource Division | 305/BWD | 24/01/2024 | 0 | Resource Division | 17.52 | 0 | 0 | 0
1278 | PURBA BARDHAMAN | Central Mechanical | MOUDANGA PIPED WATER SUPPLY SCHEME , SM/14020 | New | New service connection for MOUDANGA PWSS | BP-2023-24-546 | 19/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.78 | 0 | 0 | 0
1279 | PURBA BARDHAMAN | Central Mechanical | MOUDANGA PIPED WATER SUPPLY SCHEME , SM/14020 | New | New service connection for Moudanga PH-1 PWSS. | BP-2024-25-28 | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.45 | 0 | 0 | 0
1280 | PURBA BARDHAMAN | Burdwan Division | MOUDANGA PIPED WATER SUPPLY SCHEME , SM/14020 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NAMA BHANDARITURI, SAHAPUR & MOUDANGA Piped Water Supply Scheme under PURBASTHALI-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3689/BWD | 23/08/2023 | 770 | THE MAHADEV CONSTRUCTION | 734.18 | 85.26 | 23.15 | 50
1281 | PURBA BARDHAMAN | Central Mechanical | MOUDANGA PIPED WATER SUPPLY SCHEME , SM/14020 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MOUDANGA Water Supply Scheme [ Block- PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4106/CMD | 29/08/2023 | 581 | WEST BENGAL ENGINEERING CO. | 26.95 | 0 | 0 | 50
1282 | PURBA BARDHAMAN | Burdwan Division | MOUDANGA PIPED WATER SUPPLY SCHEME , SM/14020 | New | Different types of works involve in connection with Augmentation of DIRGHAPARA (SM/07804) Water Supply Scheme, MOUDANGA (SM/ 14020) Water supply Scheme & BHANDARTIKURI (SM/14925) Water Supply Scheme under Burdwan Division, PHE Dte. | 2912/BWD | 25/07/2024 | 431 | BANSBERIA CONSTRUCTION CO. | 293.38 | 0 | 0 | 22
1283 | PURBA BARDHAMAN | Central Mechanical | MOUDANGA PIPED WATER SUPPLY SCHEME , SM/14020 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 30
1284 | PURBA BARDHAMAN | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/13417 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 10.35 | 0 | 0 | 0
1285 | PURBA BARDHAMAN | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/13417 | New | Material Requisition To Resource Division | 3869/BWD | 01/09/2023 | 0 | Resource Division | 8.83 | 0 | 0 | 0
1286 | PURBA BARDHAMAN | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/13417 | New | Material Requisition To Resource Division | 5250/BWD | 30/11/2023 | 0 | Resource Division | 20.21 | 0 | 0 | 0
1287 | PURBA BARDHAMAN | Central Mechanical | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/13417 | New | New service connection charges for Durgadanga PWSS TW-1 | BP-2023-24-122 | 17/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.07 | 0 | 0 | 0
1288 | PURBA BARDHAMAN | Central Mechanical | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/13417 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
1289 | PURBA BARDHAMAN | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/13417 | New | DURGADANGA Single Village Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1714/BWD | 12/04/2023 | 90 | A R TRADERS | 57.63 | 57.42 | 100 | 100
1290 | PURBA BARDHAMAN | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/13417 | New | Sinking of Tube-well, construction of switch rooms & Rising main at 2ND TW site for DURGADANGA Piped Water Supply Scheme under MEMARI-I Block, District:- Purba-Bardhaman. | 5307/BWD | 01/12/2023 | 60 | A R TRADERS | 21.69 | 20.71 | 100 | 100
1291 | PURBA BARDHAMAN | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/13417 | New | Allied work of Laying distribution system for FHTC work for DURGADANGA Piped Water Supply Scheme at Durgadanga mouza within MEMARI - I Block under Burdwan Division, PHE Dte. | 521/BWD | 06/02/2024 | 30 | A R TRADERS | 13.36 | 13.34 | 100 | 100
1292 | PURBA BARDHAMAN | Central Mechanical | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/13417 | New | NEW SERVICE CONNECTION FOR DURGADANGA PWSS | BP-2023-24-587 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.12 | 0 | 0 | 0
1293 | PURBA BARDHAMAN | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/13417 | New | Restoration of concrete road by Cement concrete (mix 1:1.5:3),Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for DURGADANGA SVS & DEHA PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | 141/BWD | 08/01/2025 | 90 | MUKHERJEE ENTERPRISE | 64.37 | 0 | 0 | 0
1294 | PURBA BARDHAMAN | Burdwan Division | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/13417 | New | Construction of Boundary wall at HEAD WORK Site & 2nd TW site & Culvert at Head work site & Interconnection between Head work site distribution line 2nd Tw site of DURGADANGA Piped Water Supply Scheme under MEMARI-I Block of Burdwan Division, PHE Dte. (Length -164.00 Mtr, Col-66 Nos). | 2857/BWD | 22/07/2024 | 468 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 29.26 | 0 | 0 | 50
1295 | PURBA BARDHAMAN | Central Mechanical | DURGADANGA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/13417 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Durgadanga Water Supply Scheme [ Block- Memari-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2820/CMD | 04/07/2023 | 30 | C.M. ENTERPRISE | 29.33 | 23.71 | 97.52 | 95
1296 | PURBA BARDHAMAN | Burdwan Division | MARO PIPED WATER SUPPLY SCHEME , SM/15579 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 3.65 | 0 | 0 | 0
1297 | PURBA BARDHAMAN | Burdwan Division | MARO PIPED WATER SUPPLY SCHEME , SM/15579 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7 | 0 | 0 | 0
1298 | PURBA BARDHAMAN | Burdwan Division | MARO PIPED WATER SUPPLY SCHEME , SM/15579 | New | Material Requisition To Resource Division | 4910/BWD | 10/11/2023 | 0 | Resource Division | 12.78 | 0 | 0 | 0
1299 | PURBA BARDHAMAN | Burdwan Division | MARO PIPED WATER SUPPLY SCHEME , SM/15579 | New | MARO Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Galsi-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 2569/BWD | 01/06/2023 | 120 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 113.32 | 90.81 | 80.14 | 90
1300 | PURBA BARDHAMAN | Central Mechanical | MARO PIPED WATER SUPPLY SCHEME , SM/15579 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MARO Water Supply Scheme [ Block- GALSI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4167/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 28.54 | 11.6 | 40.66 | 48
1301 | PURBA BARDHAMAN | Central Mechanical | MARO PIPED WATER SUPPLY SCHEME , SM/15579 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
1302 | PURBA BARDHAMAN | Central Mechanical | MARO PIPED WATER SUPPLY SCHEME , SM/15579 | New | New service connection for MARO PWSS, PG-1. | BP-2023-24-537 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.06 | 0 | 0 | 0
1303 | PURBA BARDHAMAN | Burdwan Division | MARO PIPED WATER SUPPLY SCHEME , SM/15579 | New | Different works related (sinking of Tube-wells at Maro Dakshin Para, LDSs, Interconnections, FHTCs, Construction of MARO Piped Water Supply Scheme for obstruction of Railway under Galsi-I Block, of Durgapur Sub Division, under Burdwan Division, PHE. Dte. | 2895/BWD | 23/07/2024 | 371 | PREMANANDA ROY BISWAS | 42.93 | 0 | 0 | 90
1304 | PURBA BARDHAMAN | Burdwan Division | CHARKHI PIPED WATER SUPPLY SCHEME , SM/14966 | New | Material Requisition To Resource Division | 4012/BWD | 08/09/2023 | 0 | Resource Division | 0.69 | 0 | 0 | 0
1305 | PURBA BARDHAMAN | Burdwan Division | CHARKHI PIPED WATER SUPPLY SCHEME , SM/14966 | New | Material Requisition To Resource Division | 4880/BWD | 10/11/2023 | 0 | Resource Division | 29.6 | 0 | 0 | 0
1306 | PURBA BARDHAMAN | Central Mechanical | CHARKHI PIPED WATER SUPPLY SCHEME , SM/14966 | New | New service connection charges for Charkhi PWSS TW-2 | BP-2023-24-110 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.25 | 0 | 0 | 0
1307 | PURBA BARDHAMAN | Central Mechanical | CHARKHI PIPED WATER SUPPLY SCHEME , SM/14966 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
1308 | PURBA BARDHAMAN | Burdwan Division | CHARKHI PIPED WATER SUPPLY SCHEME , SM/14966 | New | Material Requisition To Resource Division | 194/BWD | 10/01/2024 | 0 | Resource Division | 9.75 | 0 | 0 | 0
1309 | PURBA BARDHAMAN | Central Mechanical | CHARKHI PIPED WATER SUPPLY SCHEME , SM/14966 | New | Quotation for new electric service connection at Charki PWSS TW No-1 | BP-2023-24-251 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0 | 0
1310 | PURBA BARDHAMAN | Burdwan Division | CHARKHI PIPED WATER SUPPLY SCHEME , SM/14966 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHARKHI & SHIBNUL Piped Water Supply Scheme under KETUGRAM-II Block, District:- Purba Bardhaman [NEW SCHEME] | 1823/BWD | 18/04/2023 | 1293 | PASCON | 723.75 | 206.17 | 52.6 | 35
1311 | PURBA BARDHAMAN | Burdwan Division | CHARKHI PIPED WATER SUPPLY SCHEME , SM/14966 | New | Balance work for OHR, extension of pipeline to provide FHTC with land development, plinth protection for pump house & OHR under Charkhi PWSS, Block-Ketugram-II under Katwa Sub Division within Burdwan Division PHE Dte. | 2836/BWD | 19/07/2024 | 835 | PASCON | 74.08 | 0 | 0 | 90
1312 | PURBA BARDHAMAN | Central Mechanical | CHARKHI PIPED WATER SUPPLY SCHEME , SM/14966 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHARKHI Water Supply Scheme [ Block- KETUGRAM-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3663/CMD | 01/08/2023 | 670 | AHALYA ENGINEERING WORKS | 27.78 | 21.5 | 94.94 | 48
1313 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-C) [SL. No. : 11] | 3408/BWD | 25/06/2021 | 15 | N.S. ENTERPRISE | 4.86 | 0.59 | 100 | 1
1314 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Extension of pipeline for providing functional house hold tap connection at Jougram village of Jougram piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte..Gr.A. | 1033/BSD | 05/08/2021 | 30 | N.S. ENTERPRISE | 0.69 | 0.67 | 100 | 1
1315 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jaugram Piped Water Supply Scheme at Jaugram Village (P) (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. | 6952/BWD | 14/12/2021 | 30 | SAIKAT RAY | 33.69 | 29.78 | 100 | 1
1316 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Land Development at Jougram 4th T/W Site at Jamalpur Block under Burdwan Sub Division in Burdwan Division,PHE Dte. Gr.G. | 1487/BSD | 26/08/2022 | 30 | PANCHANAN CHAKROBORTY | 1.17 | 1.1 | 100 | 1
1317 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Replace damaged and chokaged various dia. A.C. Pipeline with UPVC pipes, construction of valve chambers and providing FHTC at mouza (Habitation) under JOUGRAM PWSS, Jamalpur Development Block of Burdwan Sub-Division under Burdwan Division, PHE Dte". Gr.B. | 1599/BSD | 14/09/2022 | 30 | MUKHERJEE ENTERPRISE | 3.38 | 3.19 | 100 | 1
1318 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Laying of 100 mm dia D.I Pipe for Road widening from 4 lane to 6 lane of NH2 at chainage 599+654 & 599+154 at Jougram Water supply within Jamalpur Block,under Burdwan Division,PHE Dte". Group : B. | 981/BSD | 16/06/2022 | 30 | PRATIVA CONSTRUCTION | 2.97 | 0 | 0 | 0
1319 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Concrete road at Head Work site Tubewell site of Jaugram Water Supply Scheme under JAMALPUR Block of Burdwan Division, PHE Dte. Gr.L | 1608/BSD | 14/09/2022 | 15 | DUBE ENTERPRISE | 1.7 | 0 | 0 | 1
1320 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ilsora village and Ilsora habitation of JAUGRAM Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿6A¿] | 3330/BWD | 18/09/2020 | 30 | MUKHERJEE ENTERPRISE | 4.86 | 4.86 | 100 | 1
1321 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Replacement of 775 meter AC pipeline by using UPVC pipeline in Jaugram piped water supply scheme at Jamalpur Block under Burdwan Division PHE Dte.Gr.A. | 69/BSD | 14/01/2022 | 30 | MUKHERJEE ENTERPRISE | 4.83 | 4.71 | 100 | 1
1322 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). | 40/BWD | 05/01/2022 | 30 | PREMANANDA ROY BISWAS | 22.68 | 3.33 | 100 | 1
1323 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Construction of Boundary wall at 4th Tubewell site Of Jaugram Water Supply scheme under JAMALPUR Block of Burdwan Division, PHE Dte. (LENGTH- 71.0M, COL.- 28 NOS )Gr.F. | 471/BSD | 21/03/2022 | 45 | PANCHANAN CHAKROBORTY | 3.77 | 3.72 | 100 | 1
1324 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. | 1454/BWD | 11/03/2022 | 30 | PREMANANDA ROY BISWAS | 18.83 | 0 | 0 | 1
1325 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Construction of Boundary wall at 3RD Tubewell site Of Jaugram Water Supply scheme under JAMALPUR Block of Burdwan Division, PHE Dte. (LENGTH- 70.0M , COL- 28 NOS ) Gr.E | 470/BSD | 21/03/2022 | 45 | MUKHERJEE ENTERPRISE | 3.83 | 3.81 | 100 | 1
1326 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | BALANCE PORTION Boundary wall at 3RD Tubewell site Of Jaugram Water Supply scheme under JAMALPUR Block of Burdwan Division, PHE Dte. (LENGTH- 34.0M , COL- 14 NOS) GROUP : G | 820/BSD | 20/05/2022 | 45 | MUKHERJEE ENTERPRISE | 3.3 | 3.29 | 100 | 1
1327 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Repairing and Restoration of damaged and chokaged various Dia UPVC Pipeline and Construction of Valve Chambers to conrrol flow of waer for providing FHTC in JOUGRAM PWSS at Jamalpur Dev.block under Burdwan Division,PHE Dte.Group : D. | 1017/BSD | 20/06/2022 | 30 | MUKHERJEE ENTERPRISE | 1.43 | 1.39 | 100 | 1
1328 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Providing FHTC for Dogachia Mouza [(Habitation (Village)] for AMRA piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 2019/BWD | 28/04/2023 | 30 | DEY NIRMAN | 20.61 | 2.37 | 100 | 100
1329 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ilsora village and Ilsora habitation of JAUGRAM Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿6A¿] | 4513/BWD | 12/11/2020 | 30 | MUKHERJEE ENTERPRISE | 4.86 | 1.98 | 100 | 100
1330 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Moyna Habitation of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [GROUP - 'B'] | 2401/BWD | 20/07/2020 | 30 | DEY NIRMAN | 4.92 | 4.05 | 100 | 100
1331 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jougram village (Jougram habitation) of Jougram Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part-B) [SL. No. : 13] | 1398/BWD | 15/02/2021 | 15 | DEY NIRMAN | 4.84 | 4.84 | 100 | 0
1332 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jaugram piped Water Supply Scheme at Jamalpur Block under Burdwan Division PHE. DTE. , SM/09104 | Retrofitting | Laying of pipeline for providing FHTC 100% coverage and also construction & installation of Sluice Valve & Valve Chamber to control the flow of water, road restoration work etc. of different Piped W/S Schemes, Block Jamalpur under Burdwan Division, PHE Dte. | 2488/BWD | 01/07/2024 | 550 | M/S NATIONAL CONSTRUCTION | 480.97 | 0 | 0 | 80
1333 | PURBA BARDHAMAN | Central Mechanical | ANKHONA PIPED WATER SUPPLY SCHEME , SM/15157 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at ANKHONA Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4127/CMD | 29/08/2023 | 30 | M/S, N.G. ENTERPRISES. | 27.75 | 0 | 0 | 0
1334 | PURBA BARDHAMAN | Central Drilling | ANKHONA PIPED WATER SUPPLY SCHEME , SM/15157 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Ankhona W/S Scheme (T/W-I & II) ,Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | 1350/CDD | 13/09/2023 | 30 | ASHUTOSH DAS & CO | 16.59 | 0 | 0 | 0
1335 | PURBA BARDHAMAN | Burdwan Division | ANKHONA PIPED WATER SUPPLY SCHEME , SM/15157 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.29 | 0 | 0 | 0
1336 | PURBA BARDHAMAN | Burdwan Division | ANKHONA PIPED WATER SUPPLY SCHEME , SM/15157 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 21.5 | 0 | 0 | 0
1337 | PURBA BARDHAMAN | Burdwan Division | ANKHONA PIPED WATER SUPPLY SCHEME , SM/15157 | New | Material Requisition To Resource Division | 5109/BWD | 23/11/2023 | 0 | Resource Division | 20.84 | 0 | 0 | 0
1338 | PURBA BARDHAMAN | Central Mechanical | ANKHONA PIPED WATER SUPPLY SCHEME , SM/15157 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
1339 | PURBA BARDHAMAN | Burdwan Division | ANKHONA PIPED WATER SUPPLY SCHEME , SM/15157 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Ankhona, Pandugram, Sripur PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2738/BWD | 12/07/2024 | 173 | PUSPA ENTERPRISE | 128.29 | 0 | 0 | 75
1340 | PURBA BARDHAMAN | Central Mechanical | ANKHONA PIPED WATER SUPPLY SCHEME , SM/15157 | New | Quotation for new service connection Ankhona PWSS TW No.1. | BP-2024-25-293 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.99 | 0 | 0 | 0
1341 | PURBA BARDHAMAN | Central Mechanical | ANKHONA PIPED WATER SUPPLY SCHEME , SM/15157 | New | Quotation for new service connection Ankhona PWSS TW No. 2. | BP-2024-25-294 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.38 | 0 | 0 | 0
1342 | PURBA BARDHAMAN | Burdwan Division | ANKHONA PIPED WATER SUPPLY SCHEME , SM/15157 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ANKHONA, PANDUGRAM & SRIPUR Piped Water Supply Scheme under KETUGRAM¿I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3388/BWD | 03/08/2023 | 882 | PUSPA ENTERPRISE | 989.13 | 247.36 | 62.68 | 50
1343 | PURBA BARDHAMAN | Burdwan Division | ANKHONA PIPED WATER SUPPLY SCHEME , SM/15157 | New | Road crossing through metal/Concrete road by Jack Push Method for ANKHONA PWSS (SM/15157) under Ketugram-I Development Block under Katwa Sub-Divn within Burdwan Division PHE Dte. | 1321/BWD | 29/04/2025 | 30 | PUSPA ENTERPRISE | 23.14 | 0 | 0 | 100
1344 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SEHERA PWSS IN RAINA-I BLOCK , SM/15173 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of SEHERA( Part-B)[RAINA-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4200/CMD | 29/08/2023 | 30 | AMUSAR IMPEX PVT. LTD. | 24.39 | 0 | 0 | 0
1345 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SEHERA PWSS IN RAINA-I BLOCK , SM/15173 | Augmentation | Functional Household Tap Connection (FHTC) for Sehera, Mogolmari, Kona Krishnapur village for Augmentation of SEHERA Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1112/BWD | 13/03/2024 | 60 | PAL CONSTRUCTION | 35.49 | 0 | 0 | 0
1346 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SEHERA PWSS IN RAINA-I BLOCK , SM/15173 | Augmentation | Making illumination arrangement and mise works at Aug. of Sheherabazar water supply scheme RAINA-I BLOCK under Central Mechanical Division P.H.E. Dte. Purba-Bardhaman. | 2952/CMD | 20/11/2024 | 233 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 17.51 | 0 | 0 | 30
1347 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SEHERA PWSS IN RAINA-I BLOCK , SM/15173 | Augmentation | Providing leftout FHTC, Const. of Boundary Wall (HW Site & 2nd TW Site), Drain, Pathway and land development at Head Work site & 2nd TW Site (Replacement), Rising main connection of 2nd TW (Replacement) with necessary repairing work for SEHERA Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | 63/BWD | 06/01/2025 | 90 | H SAMANTA | 41.78 | 0 | 0 | 0
1348 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SEHERA PWSS IN RAINA-I BLOCK , SM/15173 | Augmentation | Laying of Interconnection of Head work site New Tube well of Sehera Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 738/BSD | 20/04/2023 | 15 | M/S UNIT CONSTRUCTION | 0.95 | 0 | 0 | 100
1349 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE II , SM/16014 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 09 Nos. Piped W/S. Schemes under Purbasthali II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3018/BWD | 05/08/2024 | 50 | HORIZEN | 23.7 | 0.18 | 100 | 10
1350 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE II , SM/16014 | Augmentation | Material Requisition To Resource Division | 196/BWD | 10/01/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
1351 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE II , SM/16014 | Augmentation | Augmentation of PURBASTHALI Surface Water Supply Scheme (ZONE-4B) with LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-II Block, District:- Purba-Bardhaman._2ND CALL | 5371/BWD | 07/12/2023 | 570 | TAPAS KUMAR CHAKRABORTY & CO. | 819.09 | 21.82 | 2.66 | 5
1352 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE II , SM/16014 | Augmentation | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
1353 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF EKAIHAT PIPED WATER SUPPLY SCHEME , SM/16017 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Ekaihat Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2583/CMD | 07/06/2023 | 30 | M/S. S.R. ENTERPRISE | 22.38 | 0 | 0 | 0
1354 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF EKAIHAT PIPED WATER SUPPLY SCHEME , SM/16017 | Augmentation | QUOTATION FOR AUGMENTATION OF EKAIHAT PWSS TW-4 | BP-2024-25-266 | 20/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.65 | 0 | 0 | 0
1355 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF EKAIHAT PIPED WATER SUPPLY SCHEME , SM/16017 | Augmentation | Augmentation of EKAIHAT Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & Construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-I Block, District:- Purba-Bardhaman. | 3031/BWD | 14/07/2023 | 627 | HAMID SK | 130.08 | 85.39 | 68.39 | 100
1356 | PURBA BARDHAMAN | Burdwan Division | AMEGERIA PIPED WATER SUPPLY SCHEME , SM/16023 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.01 | 0 | 0 | 0
1357 | PURBA BARDHAMAN | Burdwan Division | AMEGERIA PIPED WATER SUPPLY SCHEME , SM/16023 | New | Material Requisition To Resource Division | 5252/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0 | 0
1358 | PURBA BARDHAMAN | Central Mechanical | AMEGERIA PIPED WATER SUPPLY SCHEME , SM/16023 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
1359 | PURBA BARDHAMAN | Burdwan Division | AMEGERIA PIPED WATER SUPPLY SCHEME , SM/16023 | New | Material Requisition To Resource Division | 199/BWD | 10/01/2024 | 0 | Resource Division | 11.48 | 0 | 0 | 0
1360 | PURBA BARDHAMAN | Central Mechanical | AMEGERIA PIPED WATER SUPPLY SCHEME , SM/16023 | New | Quotation for new service connection at Amgoria PWSS TW 2. | BP-2024-25-232 | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.65 | 0 | 0 | 0
1361 | PURBA BARDHAMAN | Central Mechanical | AMEGERIA PIPED WATER SUPPLY SCHEME , SM/16023 | New | Quotation for new service connection at Amegeria PWSS PH-I. | BP-2024-25-167 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.43 | 0 | 0 | 0
1362 | PURBA BARDHAMAN | Burdwan Division | AMEGERIA PIPED WATER SUPPLY SCHEME , SM/16023 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMEGERIA, ARGUN, CHINISPUR & KULUTIA Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3630/BWD | 21/08/2023 | 1107 | M/S GOUTAM DAS | 1421.7 | 161.16 | 42.54 | 75
1363 | PURBA BARDHAMAN | Central Mechanical | AMEGERIA PIPED WATER SUPPLY SCHEME , SM/16023 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at AMEGERIA Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4166/CMD | 29/08/2023 | 640 | M/S, S.DAS AND ENTERPRISE. | 28.48 | 0 | 0 | 88
1364 | PURBA BARDHAMAN | Burdwan Division | AMEGERIA PIPED WATER SUPPLY SCHEME , SM/16023 | New | Road crossing through metal / concrete road by Jack Push Method for AMEGERIA (SM/16023), ARGUN (SM/16482), CHINISPUR (SM/15170) and KULITIA (SM/15167) PWSS under Ketugram I Development Block under Katwa Sub Division within Burdwan Division, PHE. Dte. | 977/BWD | 13/03/2025 | 60 | M/S GOUTAM DAS | 39.22 | 0 | 0 | 100
1365 | PURBA BARDHAMAN | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME , SM/16028 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 28.1 | 0 | 0 | 0
1366 | PURBA BARDHAMAN | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME , SM/16028 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.02 | 0 | 0 | 0
1367 | PURBA BARDHAMAN | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME , SM/16028 | New | Work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.12.2023 to 31.05.2024]" (Vehicle No-WB 04G 7127) | 1681/KSD | 22/11/2023 | 183 | PARTHA PRATIM ACHARYA | 2.4 | 0.31 | 12.79 | 0
1368 | PURBA BARDHAMAN | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME , SM/16028 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR DAFARPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 2104/KSD | 04/03/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.66 | 100 | 2
1369 | PURBA BARDHAMAN | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME , SM/16028 | New | Work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.12.2023 to 31.05.2024]" (Vehicle No-WB 04G 7127) | 1681/KSD | 22/11/2023 | 183 | PARTHA PRATIM ACHARYA | 0.87 | 1.57 | 100 | 51
1370 | PURBA BARDHAMAN | Central Mechanical | DAFARPUR PIPED WATER SUPPLY SCHEME , SM/16028 | New | NEW SERVICE CONNECTION FOR DAFARPUR PWSS TW -1. | BP-2023-24-643 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 20.65 | 0 | 0 | 0
1371 | PURBA BARDHAMAN | Central Mechanical | DAFARPUR PIPED WATER SUPPLY SCHEME , SM/16028 | New | New service at Dafarpur PWSS TW-2. | BP-2023-24-438 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.7 | 0 | 0 | 0
1372 | PURBA BARDHAMAN | Central Mechanical | DAFARPUR PIPED WATER SUPPLY SCHEME , SM/16028 | New | Additional quotation for Dafarpur PWSS PH-2 | BP-2024-25-224 | 26/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.51 | 0 | 0 | 0
1373 | PURBA BARDHAMAN | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME , SM/16028 | New | Continuation work order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection Vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.06.2024 to 30.11.2024]" (Vehicle No-WB 04G 7127) | 272/KSD | 30/05/2024 | 183 | PARTHA PRATIM ACHARYA | 2.4 | 1.22 | 50.91 | 0
1374 | PURBA BARDHAMAN | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME , SM/16028 | New | Continuation work order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.12.2024 to 28.02.2025] [Vehicle No-WB 04G 7127]". | 1877/KSD | 28/11/2024 | 90 | PARTHA PRATIM ACHARYA | 1.2 | 0 | 0 | 0
1375 | PURBA BARDHAMAN | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME , SM/16028 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
1376 | PURBA BARDHAMAN | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME , SM/16028 | New | Continual work order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.03.2025 to 31.05.2025] [Vehicle No-WB 04G 7127]". | 335/KSD | 28/02/2025 | 92 | PARTHA PRATIM ACHARYA | 1.2 | 0 | 0 | 0
1377 | PURBA BARDHAMAN | Burdwan Division | DAFARPUR PIPED WATER SUPPLY SCHEME , SM/16028 | New | Continual work order for " Hiring of one no. DIESEL MOTOR CAB (BS-VI) (Inspection vehicle) for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01/06/2025 to 31/08/2025] [Vehicle No-WB 04G 7127]". | 734/KSD | 30/05/2025 | 92 | PARTHA PRATIM ACHARYA | 1.2 | 0 | 0 | 0
1378 | PURBA BARDHAMAN | Central Mechanical | DAFARPUR PIPED WATER SUPPLY SCHEME , SM/16028 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at DAFARPUR Water Supply Scheme [Block - KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4158/CMD | 29/08/2023 | 733 | GOENKA ENTERPRISE | 20.81 | 0 | 0 | 90
1379 | PURBA BARDHAMAN | Central Drilling | KHANJI PIPED WATER SUPPLY SCHEME , SM/16476 | New | Providing drilling crew and other allied works or construction of Tube Well (250mm x 200mm x 114 Mtrs. Depth) by utilising Departmental machineries for Khanji Scheme (T/W-i & II) ketugram-I Block under Purba Bardhaman District, CDD PHE Dte. | 861/CDD | 10/07/2023 | 30 | OSMAN SEKH | 16.66 | 13.26 | 100 | 100
1380 | PURBA BARDHAMAN | Burdwan Division | KHANJI PIPED WATER SUPPLY SCHEME , SM/16476 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 5.23 | 0 | 0 | 0
1381 | PURBA BARDHAMAN | Burdwan Division | KHANJI PIPED WATER SUPPLY SCHEME , SM/16476 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.94 | 0 | 0 | 0
1382 | PURBA BARDHAMAN | Burdwan Division | KHANJI PIPED WATER SUPPLY SCHEME , SM/16476 | New | Material Requisition To Resource Division | 5261/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0 | 0
1383 | PURBA BARDHAMAN | Central Mechanical | KHANJI PIPED WATER SUPPLY SCHEME , SM/16476 | New | New service connection charges for Khanji PWSS TW-2 | BP-2023-24-223 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.96 | 0 | 0 | 0
1384 | PURBA BARDHAMAN | Central Mechanical | KHANJI PIPED WATER SUPPLY SCHEME , SM/16476 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
1385 | PURBA BARDHAMAN | Central Mechanical | KHANJI PIPED WATER SUPPLY SCHEME , SM/16476 | New | Quotation for new electric service connection at Khanji PWSS TW No-1 | BP-2023-24-270 | 11/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.48 | 0 | 0 | 0
1386 | PURBA BARDHAMAN | Burdwan Division | KHANJI PIPED WATER SUPPLY SCHEME , SM/16476 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MALGRAM, MURGRAM, MORGRAM & KHANJI Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3387/BWD | 03/08/2023 | 882 | PUSPA ENTERPRISE | 1333.98 | 242.7 | 61.41 | 40
1387 | PURBA BARDHAMAN | Burdwan Division | KHANJI PIPED WATER SUPPLY SCHEME , SM/16476 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Murgram, Moregram, Malgram, Khanji, PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2739/BWD | 12/07/2024 | 173 | PUSPA ENTERPRISE | 185.75 | 21.14 | 45.52 | 72
1388 | PURBA BARDHAMAN | Central Mechanical | KHANJI PIPED WATER SUPPLY SCHEME , SM/16476 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Khanji Water Supply Scheme [ BLOCK- Ketugram-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 882/CMD | 26/03/2025 | 60 | KAMAKHYA ENTERPRISE | 11.62 | 0 | 0 | 0
1389 | PURBA BARDHAMAN | Central Mechanical | KHANJI PIPED WATER SUPPLY SCHEME , SM/16476 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KHANJI Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4114/CMD | 29/08/2023 | 30 | M/S. S.R. ENTERPRISE | 29.41 | 23.13 | 95.21 | 97
1390 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF BAMANGARIA PIPED WATER SUPPLY SCHEME , SM/16304 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of BAMUNGARIA[PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4201/CMD | 29/08/2023 | 30 | DAS TRADING CO. | 24.41 | 0 | 0 | 0
1391 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF BAMANGARIA PIPED WATER SUPPLY SCHEME , SM/16304 | Augmentation | Augmentation of BAMANGARIA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Purbasthali - I Block, Purba Burdwan District under Burdwan Division, PHE.Dte. | 2044/BWD | 03/05/2023 | 60 | TAPAS KUMAR ROY | 38.28 | 35.67 | 100 | 100
1392 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF BAMANGARIA PIPED WATER SUPPLY SCHEME , SM/16304 | Augmentation | Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire at Pump House- 1 in connection with Augmentation of BAMUNGARIA Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 3722/BWD | 29/10/2024 | 30 | GOUTAM DEY | 9.6 | 0 | 0 | 1
1393 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF BAMANGARIA PIPED WATER SUPPLY SCHEME , SM/16304 | Augmentation | Work Order for "Restoration of HDPE Pipeline at 2nd Pump House adjacent to Bamungaria village in connection with Augmentation of Bamungaria PWSS under Kalna Sub-Division under Burdwan Division, PHE Dte.". | 776/KSD | 12/07/2024 | 15 | SETH ENTERPRISE | 0.81 | 0 | 0 | 100
1394 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF BAMANGARIA PIPED WATER SUPPLY SCHEME , SM/16304 | Augmentation | Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire in connection with Augmentation of BAMUNGARIA Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.(P.H: 2) | 3726/BWD | 29/10/2024 | 30 | JAMALUDDIN SK | 8.28 | 7.84 | 100 | 1
1395 | PURBA BARDHAMAN | Central Mechanical | KHARGAKUR PIPED WATER SUPPLY SCHEME , SM/16035 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KHARGAKUR Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4156/CMD | 29/08/2023 | 30 | S.K. ELECTRICALS | 26.96 | 0 | 0 | 0
1396 | PURBA BARDHAMAN | Burdwan Division | KHARGAKUR PIPED WATER SUPPLY SCHEME , SM/16035 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 14.2 | 0 | 0 | 0
1397 | PURBA BARDHAMAN | Burdwan Division | KHARGAKUR PIPED WATER SUPPLY SCHEME , SM/16035 | New | Material Requisition To Resource Division | 3842/BWD | 01/09/2023 | 0 | Resource Division | 6.91 | 0 | 0 | 0
1398 | PURBA BARDHAMAN | Burdwan Division | KHARGAKUR PIPED WATER SUPPLY SCHEME , SM/16035 | New | Material Requisition To Resource Division | 4305/BWD | 29/09/2023 | 0 | Resource Division | 25.37 | 0 | 0 | 0
1399 | PURBA BARDHAMAN | Burdwan Division | KHARGAKUR PIPED WATER SUPPLY SCHEME , SM/16035 | New | KHARGAKUR PWSS Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna-II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | 3751/BWD | 28/08/2023 | 365 | MITRA CONSTRUCTION | 310.02 | 161.2 | 52 | 15
1400 | PURBA BARDHAMAN | Burdwan Division | KHARGAKUR PIPED WATER SUPPLY SCHEME , SM/16035 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR KHAGRAKUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 2171/KSD | 11/03/2024 | 10 | MITRA CONSTRUCTION | 0.66 | 0.66 | 100 | 100
1401 | PURBA BARDHAMAN | Central Mechanical | KHARGAKUR PIPED WATER SUPPLY SCHEME , SM/16035 | New | Quotation for new electric service connection at Khargakur PH NO.-2 | BP-2023-24-256 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.28 | 0 | 0 | 0
1402 | PURBA BARDHAMAN | Central Mechanical | KHARGAKUR PIPED WATER SUPPLY SCHEME , SM/16035 | New | Quotation for new electric service connection at Khargakur PH NO.-1 | BP-2023-24-257 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.35 | 0 | 0 | 0
1403 | PURBA BARDHAMAN | Central Mechanical | KHARGAKUR PIPED WATER SUPPLY SCHEME , SM/16035 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
1404 | PURBA BARDHAMAN | Burdwan Division | KHARGAKUR PIPED WATER SUPPLY SCHEME , SM/16035 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
1405 | PURBA BARDHAMAN | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME , SM/16036 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 22.36 | 0 | 0 | 0
1406 | PURBA BARDHAMAN | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME , SM/16036 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.79 | 0 | 0 | 0
1407 | PURBA BARDHAMAN | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME , SM/16036 | New | Material Requisition To Resource Division | 4874/BWD | 10/11/2023 | 0 | Resource Division | 28.85 | 0 | 0 | 0
1408 | PURBA BARDHAMAN | Central Mechanical | KUSDANGA PIPED WATER SUPPLY SCHEME , SM/16036 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System, Internal House Wiring and Compound lighting arrangement for Tube well No.- 1 & 2 at KUSDANGA Water Supply Scheme [BLOCK- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1536/CMD | 05/03/2024 | 60 | MITRA ENTERPRISE | 28.81 | 11.49 | 39.86 | 50
1409 | PURBA BARDHAMAN | Central Mechanical | KUSDANGA PIPED WATER SUPPLY SCHEME , SM/16036 | New | New Service connection for Kushodanga W/S Scheme. | BP-2023-24-437 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.25 | 0 | 0 | 0
1410 | PURBA BARDHAMAN | Central Mechanical | KUSDANGA PIPED WATER SUPPLY SCHEME , SM/16036 | New | NEW SERVICE CONNECTION FOR KUSDANGA PWSS TW -2. | BP-2023-24-647 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.03 | 0 | 0 | 0
1411 | PURBA BARDHAMAN | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME , SM/16036 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
1412 | PURBA BARDHAMAN | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME , SM/16036 | New | Restoration of Masonary drain due laying of 90 mm. dia. HDPE pipe along with increasing height of boundary wall and other ancillary work under the command area of Kusdanga PWSS (SM/16036) under Kalna Sub Division under Burdwan Divn., PHE. Dte. | 4240/BWD | 03/12/2024 | 21 | RUBAL CONSTRUCTION | 13.62 | 0 | 0 | 100
1413 | PURBA BARDHAMAN | Burdwan Division | KUSDANGA PIPED WATER SUPPLY SCHEME , SM/16036 | New | Road Restoration work under the command area of Kusdanga PWSS (SM/16036) under Kalna Sub Division under Burdwan Division, PHE. Dte. | 4170/BWD | 29/11/2024 | 21 | RUBAL CONSTRUCTION | 15.12 | 0 | 0 | 100
1414 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR , SM/15701 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-II W/S Scheme at Kalsi Mouza, RASULPUR W/S Scheme at 4th TW site & ALIPUR W/S Scheme at 4th TW site under Memari-I Block under within Burdwan Sub-Division, PHE Dte. [For 3 Nos. Tube well]. | 2455/BWD | 31/05/2023 | 60 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 39.76 | 13.1 | 100 | 100
1415 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR , SM/15701 | Augmentation | Preparation and Submission of DPR for Augmentation of Rasulpur PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1583/BSD | 24/07/2023 | 15 | GEO-SOLUTION | 0.78 | 0.77 | 100 | 100
1416 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR , SM/15701 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Rasulpur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2594/CMD | 07/06/2023 | 30 | CHOUDHURY ENTERPRISE | 22.76 | 11.08 | 48.69 | 50
1417 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR , SM/15701 | Augmentation | Construction of switch rooms & Rising main at different TW site for RASULPUR Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | 5356/BWD | 06/12/2023 | 60 | SANDIP SARKAR | 7.43 | 5.45 | 100 | 95
1418 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR , SM/15701 | Augmentation | Supply & installation of Automatic Chlorinator at Rasulpur water supply scheme, P.H. No.- II under CMD, P.H.E. Dte., Dist.- Purba Bardhaman. | 18/CMSD | 04/01/2024 | 12 | MS S M ELECTRICAL | 0.96 | 0.96 | 100 | 100
1419 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR , SM/15701 | Augmentation | Extension of height of Boundary Wall by Angle Rolled Section and Barbed Wire and Roof treatment of Pump house for Rasulpur and its Adjoining Mouza W/S Scheme, block -Memari-I within Burdwan Sub-Division ,PHE Dte | 1282/BSD | 12/07/2024 | 60 | GHOSH CONSTRUCTION | 1.27 | 1.23 | 100 | 98
1420 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR , SM/15701 | Augmentation | Quotation for New Electric Connection for Rasulpur Augmentation W/S Scheme TW No. - 4 | BP-2023-24-254 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.09 | 0 | 0 | 0
1421 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RASULPUR , SM/15701 | Augmentation | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for RASULPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | 4474/BWD | 19/12/2024 | 90 | SARKAR AGENCY | 91.74 | 0 | 0 | 51
1422 | PURBA BARDHAMAN | Central Mechanical | JIUDHARA PWSS , SM/18314 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at JIUDHARA Water Supply Scheme [ Block- KALNA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4164/CMD | 29/08/2023 | 30 | DUTTA ENTERPRISE | 44.4 | 0 | 0 | 0
1423 | PURBA BARDHAMAN | Burdwan Division | JIUDHARA PWSS , SM/18314 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 18.12 | 0 | 0 | 0
1424 | PURBA BARDHAMAN | Burdwan Division | JIUDHARA PWSS , SM/18314 | New | Material Requisition To Resource Division | 4877/BWD | 10/11/2023 | 0 | Resource Division | 26.94 | 0 | 0 | 0
1425 | PURBA BARDHAMAN | Burdwan Division | JIUDHARA PWSS , SM/18314 | New | Material Requisition To Resource Division | 4291/BWD | 29/09/2023 | 0 | Resource Division | 50.47 | 0 | 0 | 0
1426 | PURBA BARDHAMAN | Central Mechanical | JIUDHARA PWSS , SM/18314 | New | New service connection for Jewdhara PWSS PH-1 | BP-2023-24-458 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.55 | 0 | 0 | 0
1427 | PURBA BARDHAMAN | Burdwan Division | JIUDHARA PWSS , SM/18314 | New | JIUDHARA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna II Block, District:- Purba-Bardhaman [NEW SCHEME] | 4534/BWD | 13/10/2023 | 780 | SOMNATH ROY CHOWDHURY | 625.16 | 108.02 | 17.28 | 45
1428 | PURBA BARDHAMAN | Burdwan Division | JIUDHARA PWSS , SM/18314 | New | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 618/BWD | 11/02/2025 | 180 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0 | 0
1429 | PURBA BARDHAMAN | Central Mechanical | JIUDHARA PWSS , SM/18314 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
1430 | PURBA BARDHAMAN | Burdwan Division | JIUDHARA PWSS , SM/18314 | New | Work order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR JIUDHARA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 1231/KSD | 27/09/2024 | 15 | DEL DELTA CONSTRUCTION | 0.66 | 0 | 0 | 100
1431 | PURBA BARDHAMAN | Central Mechanical | BERUGRAM PIPED WATER SUPPLY SCHEME , SM/18606 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Berugram Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | 4195/CMD | 29/08/2023 | 30 | M/S, S.DAS AND ENTERPRISE. | 29.71 | 0 | 0 | 0
1432 | PURBA BARDHAMAN | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME , SM/18606 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.09 | 0 | 0 | 0
1433 | PURBA BARDHAMAN | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME , SM/18606 | New | Material Requisition To Resource Division | 4289/BWD | 29/09/2023 | 0 | Resource Division | 16.32 | 0 | 0 | 0
1434 | PURBA BARDHAMAN | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME , SM/18606 | New | Material Requisition To Resource Division | 5114/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
1435 | PURBA BARDHAMAN | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME , SM/18606 | New | Land demarcation and preparation of sketch map for Haldi, Sultanpur, Berugram & Karail Piped W/S. Scheme (New Scheme) at different Blocks under JJM under Burdwan Division, PHE Dte. | 842/AE/HQ | 01/11/2023 | 15 | M/S S. CHOUDHURY | 0.33 | 0 | 0 | 100
1436 | PURBA BARDHAMAN | Central Mechanical | BERUGRAM PIPED WATER SUPPLY SCHEME , SM/18606 | New | New Service connection for Berugram PWSS TW-2. | BP-2023-24-475 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.69 | 0 | 0 | 0
1437 | PURBA BARDHAMAN | Central Mechanical | BERUGRAM PIPED WATER SUPPLY SCHEME , SM/18606 | New | Quotation for new service connection at Berugram W/S Scheme PH-I. | BP-2023-24-323 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.94 | 0 | 0 | 0
1438 | PURBA BARDHAMAN | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME , SM/18606 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BERUGRAM & SULTANPUR Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | 092/BWD | 05/01/2024 | 604 | SK ALIM | 1368.51 | 287.39 | 42.24 | 55
1439 | PURBA BARDHAMAN | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME , SM/18606 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day. [PeriodFebruary.'2025 to April'2025] | 129/DSD | 29/01/2025 | 78 | MD HASIN | 1 | 0 | 0 | 0
1440 | PURBA BARDHAMAN | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME , SM/18606 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period NOV.'2024 to JAN.'2025] | 886/DSD | 21/10/2024 | 78 | MD HASIN | 1 | 0.33 | 100 | 0
1441 | PURBA BARDHAMAN | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME , SM/18606 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period AUG.'2024 to OCT.'2024] | 575/DSD | 19/07/2024 | 78 | MD HASIN | 1 | 0.18 | 53.85 | 0
1442 | PURBA BARDHAMAN | Central Mechanical | BERUGRAM PIPED WATER SUPPLY SCHEME , SM/18606 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
1443 | PURBA BARDHAMAN | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME , SM/18606 | New | Balance work of BERUGRAM & SULTANPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman. | 723/BWD | 24/02/2025 | 180 | MD HASIN | 438.83 | 0 | 0 | 0
1444 | PURBA BARDHAMAN | Burdwan Division | BERUGRAM PIPED WATER SUPPLY SCHEME , SM/18606 | New | Continuation for Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day for the month of May'2025 | 660/DSD | 30/04/2025 | 31 | MD HASIN | 0.4 | 0 | 0 | 0
1445 | PURBA BARDHAMAN | Central Drilling | EHIAPUR PIPED WATER SUPPLY SCHEME , SM/18342 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Ehiapur W/S Scheme (T/W-I & II) ,Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | 1348/CDD | 13/09/2023 | 30 | CHANDA ENTERPRISE | 16.67 | 0 | 0 | 0
1446 | PURBA BARDHAMAN | Burdwan Division | EHIAPUR PIPED WATER SUPPLY SCHEME , SM/18342 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.15 | 0 | 0 | 0
1447 | PURBA BARDHAMAN | Burdwan Division | EHIAPUR PIPED WATER SUPPLY SCHEME , SM/18342 | New | Material Requisition To Resource Division | 3874/BWD | 01/09/2023 | 0 | Resource Division | 64.94 | 0 | 0 | 0
1448 | PURBA BARDHAMAN | Burdwan Division | EHIAPUR PIPED WATER SUPPLY SCHEME , SM/18342 | New | Material Requisition To Resource Division | 4924/BWD | 10/11/2023 | 0 | Resource Division | 40.35 | 0 | 0 | 0
1449 | PURBA BARDHAMAN | Central Mechanical | EHIAPUR PIPED WATER SUPPLY SCHEME , SM/18342 | New | New service connection charges for Ehiapur PWSS TW-1 | BP-2023-24-168 | 27/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.42 | 0 | 0 | 0
1450 | PURBA BARDHAMAN | Burdwan Division | EHIAPUR PIPED WATER SUPPLY SCHEME , SM/18342 | New | EHIAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3438/BWD | 08/08/2023 | 365 | M/S S.S. ENTERPRISE | 732.05 | 606.31 | 82.82 | 75
1451 | PURBA BARDHAMAN | Central Mechanical | EHIAPUR PIPED WATER SUPPLY SCHEME , SM/18342 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
1452 | PURBA BARDHAMAN | Burdwan Division | EHIAPUR PIPED WATER SUPPLY SCHEME , SM/18342 | New | Material Requisition To Resource Division | 4111/BWD | 25/11/2024 | 0 | Resource Division | 9.24 | 0 | 0 | 0
1453 | PURBA BARDHAMAN | Central Mechanical | EHIAPUR PIPED WATER SUPPLY SCHEME , SM/18342 | New | New service connection charges for Ehiapur PWSS TW-3 | BP-2023-24-258 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.52 | 0 | 0 | 0
1454 | PURBA BARDHAMAN | Central Mechanical | EHIAPUR PIPED WATER SUPPLY SCHEME , SM/18342 | New | New service connection charges for Ehiapur PWSS TW-2 | BP-2023-24-259 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.82 | 0 | 0 | 0
1455 | PURBA BARDHAMAN | Central Mechanical | EHIAPUR PIPED WATER SUPPLY SCHEME , SM/18342 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at EHIAPUR Water Supply Scheme [ Block- KETUGRAM-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4115/CMD | 29/08/2023 | 615 | ASHIM UDYOG | 44.39 | 35.13 | 79.14 | 61
1456 | PURBA BARDHAMAN | Burdwan Division | EHIAPUR PIPED WATER SUPPLY SCHEME , SM/18342 | New | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2741/BWD | 12/07/2024 | 538 | M/S M.M. ENTERPRISE | 205.15 | 7.34 | 25.66 | 65
1457 | PURBA BARDHAMAN | Central Mechanical | HALIMPUR PIPE WATER SUPPLY SCHEME , SM/18343 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at HALIMPUR Water Supply Scheme [ Block- MANGOLKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4134/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 45.29 | 0 | 0 | 0
1458 | PURBA BARDHAMAN | Burdwan Division | HALIMPUR PIPE WATER SUPPLY SCHEME , SM/18343 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.69 | 0 | 0 | 0
1459 | PURBA BARDHAMAN | Burdwan Division | HALIMPUR PIPE WATER SUPPLY SCHEME , SM/18343 | New | Material Requisition To Resource Division | 3872/BWD | 01/09/2023 | 0 | Resource Division | 1.27 | 0 | 0 | 0
1460 | PURBA BARDHAMAN | Burdwan Division | HALIMPUR PIPE WATER SUPPLY SCHEME , SM/18343 | New | Material Requisition To Resource Division | 4921/BWD | 10/11/2023 | 0 | Resource Division | 27.49 | 0 | 0 | 0
1461 | PURBA BARDHAMAN | Central Mechanical | HALIMPUR PIPE WATER SUPPLY SCHEME , SM/18343 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
1462 | PURBA BARDHAMAN | Burdwan Division | HALIMPUR PIPE WATER SUPPLY SCHEME , SM/18343 | New | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | 485/KTS | 16/04/2024 | 72 | AJIT SAMANTA | 0.92 | 0.23 | 100 | 10
1463 | PURBA BARDHAMAN | Burdwan Division | HALIMPUR PIPE WATER SUPPLY SCHEME , SM/18343 | New | Material Requisition To Resource Division | 4109/BWD | 25/11/2024 | 0 | Resource Division | 6.9 | 0 | 0 | 0
1464 | PURBA BARDHAMAN | Central Mechanical | HALIMPUR PIPE WATER SUPPLY SCHEME , SM/18343 | New | Quotation for new service connection at Halimpur PWSS TW-1 | BP-2024-25-396 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.11 | 0 | 0 | 0
1465 | PURBA BARDHAMAN | Burdwan Division | HALIMPUR PIPE WATER SUPPLY SCHEME , SM/18343 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHAKULIA, KULSANA & HALIMPUR Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] | 3443/BWD | 08/08/2023 | 836 | ASHOK KUMAR GHOSH | 1588.1 | 45.62 | 7.04 | 15
1466 | PURBA BARDHAMAN | Burdwan Division | HALIMPUR PIPE WATER SUPPLY SCHEME , SM/18343 | New | Balance work of HALIMPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman | 845/BWD | 05/03/2025 | 120 | M/S H.R. CONSTRUCTION | 248.04 | 0 | 0 | 0
1467 | PURBA BARDHAMAN | Central Drilling | HALIMPUR PIPE WATER SUPPLY SCHEME , SM/18343 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for Halimpur W/S Scheme (T/W-I & II), Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | 1340/CDD | 13/09/2023 | 583 | M/S SAIKAT ENTERPRISE | 23.35 | 10.8 | 46.63 | 100
1468 | PURBA BARDHAMAN | Burdwan Division | KULSANA PIPE WATER SUPPLY SCHEME , SM/18440 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 1.75 | 0 | 0 | 0
1469 | PURBA BARDHAMAN | Burdwan Division | KULSANA PIPE WATER SUPPLY SCHEME , SM/18440 | New | Material Requisition To Resource Division | 3826/BWD | 01/09/2023 | 0 | Resource Division | 4.47 | 0 | 0 | 0
1470 | PURBA BARDHAMAN | Central Mechanical | KULSANA PIPE WATER SUPPLY SCHEME , SM/18440 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
1471 | PURBA BARDHAMAN | Burdwan Division | KULSANA PIPE WATER SUPPLY SCHEME , SM/18440 | New | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | 485/KTS | 16/04/2024 | 72 | AJIT SAMANTA | 0.92 | 0.23 | 100 | 10
1472 | PURBA BARDHAMAN | Central Drilling | KULSANA PIPE WATER SUPPLY SCHEME , SM/18440 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for Kulsana W/S Scheme (T/W-I & II), Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | 1341/CDD | 13/09/2023 | 322 | SUNRISE ENGINEERING CORPORATION | 23.34 | 19.11 | 100 | 100
1473 | PURBA BARDHAMAN | Burdwan Division | KULSANA PIPE WATER SUPPLY SCHEME , SM/18440 | New | Material Requisition To Resource Division | 308/BWD | 24/01/2024 | 0 | Resource Division | 32.08 | 0 | 0 | 0
1474 | PURBA BARDHAMAN | Burdwan Division | KULSANA PIPE WATER SUPPLY SCHEME , SM/18440 | New | Material Requisition To Resource Division | 4099/BWD | 25/11/2024 | 0 | Resource Division | 20.51 | 0 | 0 | 0
1475 | PURBA BARDHAMAN | Central Mechanical | KULSANA PIPE WATER SUPPLY SCHEME , SM/18440 | New | QUOTATION FOR NEW SERVICE CONNECTION AT KULSANA PWSS TW-1 | BP-2024-25-187 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.91 | 0 | 0 | 0
1476 | PURBA BARDHAMAN | Central Mechanical | KULSANA PIPE WATER SUPPLY SCHEME , SM/18440 | New | Quotation for new service connection at Kulsana PWSS TW-2 | BP-2024-25-186 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.43 | 0 | 0 | 0
1477 | PURBA BARDHAMAN | Burdwan Division | KULSANA PIPE WATER SUPPLY SCHEME , SM/18440 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHAKULIA, KULSANA & HALIMPUR Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] | 3443/BWD | 08/08/2023 | 836 | ASHOK KUMAR GHOSH | 1588.1 | 252.57 | 39.61 | 15
1478 | PURBA BARDHAMAN | Central Mechanical | KULSANA PIPE WATER SUPPLY SCHEME , SM/18440 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KULSANA Water Supply Scheme [ Block-MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4139/CMD | 29/08/2023 | 640 | M/S, S.S. ENTERPRISE. | 44.56 | 3.11 | 6.99 | 43
1479 | PURBA BARDHAMAN | Burdwan Division | KULSANA PIPE WATER SUPPLY SCHEME , SM/18440 | New | Balance work of KULSANA Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman. | 935/BWD | 11/03/2025 | 120 | M/S GHOSH CONSTRUCTION | 249.53 | 0 | 0 | 0
1480 | PURBA BARDHAMAN | Burdwan Division | PANDUK PIPED WATER SUPPLY SCHEME , SM/18445 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.25 | 0 | 0 | 0
1481 | PURBA BARDHAMAN | Burdwan Division | PANDUK PIPED WATER SUPPLY SCHEME , SM/18445 | New | Material Requisition To Resource Division | 3840/BWD | 01/09/2023 | 0 | Resource Division | 55.98 | 0 | 0 | 0
1482 | PURBA BARDHAMAN | Burdwan Division | PANDUK PIPED WATER SUPPLY SCHEME , SM/18445 | New | Material Requisition To Resource Division | 4919/BWD | 10/11/2023 | 0 | Resource Division | 53.67 | 0 | 0 | 0
1483 | PURBA BARDHAMAN | Durgapur W/S Division | PANDUK PIPED WATER SUPPLY SCHEME , SM/18445 | New | Acceptance cum Formal Work Order for Sinking of 300X200 mm dia TW,Pump House,Boundary wall concrete road & bituminous road restoration ,Jack pushing with laying of MS Pipe FHTC and land development of H/W Site drain & Internal pathway laying of MS pipe under Bhedia PWSS (JJM),Block-Aushgram-II,Dist-Purba Bardhaman under Durgapur W/S Division,PHE Dte. | 1611/DWSD | 26/11/2024 | 90 | SUPRIYA RAY | 87.54 | 0 | 0 | 0
1484 | PURBA BARDHAMAN | Burdwan Division | PANDUK PIPED WATER SUPPLY SCHEME , SM/18445 | New | Material Requisition To Resource Division | 204/BWD | 10/01/2024 | 0 | Resource Division | 12.89 | 0 | 0 | 0
1485 | PURBA BARDHAMAN | Central Mechanical | PANDUK PIPED WATER SUPPLY SCHEME , SM/18445 | New | Quotation for new service connection for Panduk PWSS PH 1. | BP-2024-25-112 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.47 | 0 | 0 | 0
1486 | PURBA BARDHAMAN | Central Mechanical | PANDUK PIPED WATER SUPPLY SCHEME , SM/18445 | New | Quotation for new service connection for Panduk PWSS PH 2. | BP-2024-25-113 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.92 | 0 | 0 | 0
1487 | PURBA BARDHAMAN | Central Mechanical | PANDUK PIPED WATER SUPPLY SCHEME , SM/18445 | New | Quotation for new service connection for Panduk PWSS PH 3. | BP-2024-25-114 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.39 | 0 | 0 | 0
1488 | PURBA BARDHAMAN | Burdwan Division | PANDUK PIPED WATER SUPPLY SCHEME , SM/18445 | New | PANDUK Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | 3505/BWD | 10/08/2023 | 875 | M/S PIONEER CONSTRUCTION | 722.29 | 397.52 | 55.04 | 80
1489 | PURBA BARDHAMAN | Central Mechanical | PANDUK PIPED WATER SUPPLY SCHEME , SM/18445 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at PANDUK Water Supply Scheme [ Block- AUSGRAM-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4082/CMD | 29/08/2023 | 611 | PADMA ENGINEERING CO. | 41.68 | 0 | 0 | 67
1490 | PURBA BARDHAMAN | Durgapur W/S Division | PANDUK PIPED WATER SUPPLY SCHEME , SM/18445 | New | FORMAL WORK ORDER FOR Balance work for Construction of Boundary wall, dismantling concrete road including mending work, construction of approach road by fill-up stone dust, bolders on lowland at OHR site and etc. allied work under PANDUK PWSS, Block-Ausgram-II under DURGAPUR W/S DIVISION, PHE DTE. | 257/DWSD | 11/02/2025 | 90 | M/S PIONEER CONSTRUCTION | 124.43 | 32.46 | 20.71 | 100
1491 | PURBA BARDHAMAN | Burdwan Division | AURIA PIPED WATER SUPPLY SCHEME , SM/18455 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 17.33 | 0 | 0 | 0
1492 | PURBA BARDHAMAN | Burdwan Division | AURIA PIPED WATER SUPPLY SCHEME , SM/18455 | New | Material Requisition To Resource Division | 3853/BWD | 01/09/2023 | 0 | Resource Division | 64.75 | 0 | 0 | 0
1493 | PURBA BARDHAMAN | Central Mechanical | AURIA PIPED WATER SUPPLY SCHEME , SM/18455 | New | New service connection charges for Auria PWSS TW-1 | BP-2023-24-188 | 09/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.89 | 0 | 0 | 0
1494 | PURBA BARDHAMAN | Central Mechanical | AURIA PIPED WATER SUPPLY SCHEME , SM/18455 | New | New service connection charges for Auria PWSS TW-2 | BP-2023-24-189 | 09/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.77 | 0 | 0 | 0
1495 | PURBA BARDHAMAN | Central Mechanical | AURIA PIPED WATER SUPPLY SCHEME , SM/18455 | New | New service connection charges for Auria PWSS TW-3 | BP-2023-24-190 | 09/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7 | 0 | 0 | 0
1496 | PURBA BARDHAMAN | Central Mechanical | AURIA PIPED WATER SUPPLY SCHEME , SM/18455 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
1497 | PURBA BARDHAMAN | Central Mechanical | AURIA PIPED WATER SUPPLY SCHEME , SM/18455 | New | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3106/CMD | 11/12/2024 | 60 | S.K. ELECTRICALS | 13.6 | 0 | 0 | 0
1498 | PURBA BARDHAMAN | Burdwan Division | AURIA PIPED WATER SUPPLY SCHEME , SM/18455 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMUL & AURIA Piped Water Supply Scheme under Katwa ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3198/BWD | 24/07/2023 | 1257 | MANASH GHOSH | 1418.89 | 658.51 | 91.73 | 48
1499 | PURBA BARDHAMAN | Central Mechanical | AURIA PIPED WATER SUPPLY SCHEME , SM/18455 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at AURIA Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4088/CMD | 29/08/2023 | 30 | ORIENTAL ENGINEERING CO. | 44.4 | 23.46 | 63.54 | 64
1500 | PURBA BARDHAMAN | Central Mechanical | AURIA PIPED WATER SUPPLY SCHEME , SM/18455 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 2 at Augumentation of Agradip Kashipur (Babladanga) Water Supply Scheme [BLOCK- Katwa-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2445/CMD | 07/08/2024 | 300 | SUBRATA BHADRA | 11.63 | 0 | 0 | 91
1501 | PURBA BARDHAMAN | Burdwan Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME , SM/18408 | New | Material Requisition To Resource Division | 3864/BWD | 01/09/2023 | 0 | Resource Division | 128.72 | 0 | 0 | 0
1502 | PURBA BARDHAMAN | Burdwan Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME , SM/18408 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 20.29 | 0 | 0 | 0
1503 | PURBA BARDHAMAN | Burdwan Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME , SM/18408 | New | Material Requisition To Resource Division | 5110/BWD | 23/11/2023 | 0 | Resource Division | 22.15 | 0 | 0 | 0
1504 | PURBA BARDHAMAN | Central Mechanical | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME , SM/18408 | New | Quotation for new service connection at Baksibad PWSS TW-2. | BP-2024-25-412 | 11/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.75 | 0 | 0 | 0
1505 | PURBA BARDHAMAN | Central Mechanical | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME , SM/18408 | New | NEW SERVICE CONNECTION FOR BAKSIBAD PWSS PH-1. | BP-2023-24-652 | 20/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.55 | 0 | 0 | 0
1506 | PURBA BARDHAMAN | Burdwan Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME , SM/18408 | New | BAKSIBAD POGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | 3504/BWD | 10/08/2023 | 813 | M/S PIONEER CONSTRUCTION | 691.24 | 162.06 | 23.45 | 40
1507 | PURBA BARDHAMAN | Durgapur W/S Division | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME , SM/18408 | New | FORMAL WORK ORDER FOR Balance work for construction of boundary wall, dismantling concrete road including mending work, construction of approach road by fillup stone dust, bolders on low load at OHR site and etc allied works under Bakshibad PWSS, Ausgram-II Block under DURGAPUR W/S DIVISION,PHE DTE. | 256/DWSD | 11/02/2025 | 406 | M/S. UNIT CONSTRUCTION | 122.59 | 29.85 | 24.35 | 95
1508 | PURBA BARDHAMAN | Central Mechanical | BAKSIBAD POGRAM PIPED WATER SUPPLY SCHEME , SM/18408 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Baksibad Pogram Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4052/CMD | 29/08/2023 | 553 | JAGANNATH ENTERPRISE | 29.61 | 12.33 | 32.44 | 80
1509 | PURBA BARDHAMAN | Burdwan Division | HATSIMUL PIPED WATER SUPPLY SCHEME , SM/18409 | New | Material Requisition To Resource Division | 3846/BWD | 01/09/2023 | 0 | Resource Division | 17.48 | 0 | 0 | 0
1510 | PURBA BARDHAMAN | Burdwan Division | HATSIMUL PIPED WATER SUPPLY SCHEME , SM/18409 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 2.25 | 0 | 0 | 0
1511 | PURBA BARDHAMAN | Burdwan Division | HATSIMUL PIPED WATER SUPPLY SCHEME , SM/18409 | New | Material Requisition To Resource Division | 5076/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
1512 | PURBA BARDHAMAN | Central Mechanical | HATSIMUL PIPED WATER SUPPLY SCHEME , SM/18409 | New | Electric quotation for New Service Connection at Hatsimul W/S Scehem PH-I. | BP-2023-24-29 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.13 | 0 | 0 | 0
1513 | PURBA BARDHAMAN | Central Mechanical | HATSIMUL PIPED WATER SUPPLY SCHEME , SM/18409 | New | Electric quotation for New Service Connection at Hatsimul W/S Scehem PH-II. | BP-2023-24-293 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.12 | 0 | 0 | 0
1514 | PURBA BARDHAMAN | Central Mechanical | HATSIMUL PIPED WATER SUPPLY SCHEME , SM/18409 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 0 | 12
1515 | PURBA BARDHAMAN | Central Mechanical | HATSIMUL PIPED WATER SUPPLY SCHEME , SM/18409 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Hatsimul Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4009?CMD | 29/08/2023 | 30 | WEST BENGAL ENGINEERING CO. | 28.96 | 23.34 | 97.73 | 100
1516 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme , SM/06965 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Barwa Piped Water Supply Scheme at Berwa (2 Nos Habitation Part), Mutra (2 Nos Habitation Part), Baneswarpur & Senpur (4 Nos Habitation) Village (Mouza), Memari-II Block under Burdwan Division, PHE Dte. | 916/BWD | 02/02/2021 | 90 | KALYAN CHOWDHURY | 45.14 | 0 | 0 | 1
1517 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme , SM/06965 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Barwa village of Barwa piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-573/BWD/2020-21) | 4627/BWD | 25/11/2020 | 30 | M/S SAYAN CHAKRABORTY | 4.92 | 9.84 | 200 | 1
1518 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme , SM/06965 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Barwa Piped Water Supply Scheme at Berwa (2 Nos Habitation Part), Mutra (2 Nos Habitation Part), Baneswarpur & Senpur (4 Nos Habitation) Village (Mouza), Memari-II Block under Burdwan Division, PHE Dte. | 3442/BWD | 28/06/2021 | 90 | KALYAN CHOWDHURY | 45.14 | 41.9 | 171.45 | 100
1519 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme , SM/06965 | Retrofitting | Extension of 75 mm dia pipeline at Miya Para, Modhya Bohar & Bhagar Para Purba Bohar regarding FHTC under Satgachia (Zone-I) water supply scheme under Burdwan Division, PHE Dte.[Gr.-A] | 703/BSD | 11/06/2021 | 5 | M/S SAYAN CHAKRABORTY | 0.88 | 0 | 0 | 1
1520 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme , SM/06965 | Retrofitting | Emergency repaired cleaning of chokage AC Pipeline for BARWA Piped Water Supply Scheme (Retrrofittings)at Mutra, senpur, Mohanpur & Barwa village distribution line smooth drinking (FHTC) water supply within Memari-II Block under Burdwan Division, PHE Dte. Gr.C | 1919/BSD | 11/11/2022 | 15 | A R TRADERS | 0.79 | 0.79 | 100 | 1
1521 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme , SM/06965 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bohar (Part) village (Bohar (Part) habitation) of Satgachia Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Sl. No. : ¿20¿] | 70/BWD | 05/01/2021 | 15 | M/S SAYAN CHAKRABORTY | 4.86 | 4.79 | 100 | 0
1522 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme , SM/06965 | Retrofitting | Restoration of Pump House at Head Work site of BARWA Piped water supply scheme at Memari-II Block under Burdwan Division, Dist.-Purba Bardhaman | 1007/BSD | 06/06/2024 | 30 | I.S. ENTERPRISE | 0.97 | 0.96 | 100 | 100
1523 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Berwa Piped Water Supply Scheme , SM/06965 | Retrofitting | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 848/BWD | 05/03/2025 | 120 | PROJECT INDIA | 394.29 | 0 | 0 | 0
1524 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme , SM/07204 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Saktigarh (Pt-B) village of Shaktigarh Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿8B¿] (T.R. No.-380/BWD/2020-21) | 2742/BWD | 10/08/2020 | 30 | T.K. BANERJEE & CO. | 4.91 | 9.83 | 200 | 1
1525 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme , SM/07204 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Saktigarh (Pt-A) village of Shaktigarh Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿8A¿] (T.R. No. 428/BWD/2020-21) | 3801/BWD | 08/10/2020 | 30 | SARKAR AGENCY | 4.92 | 9.84 | 200 | 1
1526 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme , SM/07204 | Retrofitting | Providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Saktigarh Piped water supply scheme at Shaktigarh village, Burdwan-II Block under Burdwan Division, PHE Dte. [Tr No.-101/SE/CC/2020-21] | 715/BWD | 28/01/2021 | 60 | SARKAR AGENCY | 62.17 | 58.02 | 142.66 | 1
1527 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme , SM/07204 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Shaktigarh (Part-B) village of Shaktigarh piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-649/BWD/2020-21) | 4271/BWD | 03/11/2020 | 30 | T.K. BANERJEE & CO. | 4.91 | 9.83 | 200 | 1
1528 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme , SM/07204 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 2nd tube well site for Shaktigarh & its adjoining mouzas water supply scheme , Block-Bardhaman-II under Burdwan Division, PHE Dte.[Gr.-G] | 1391/BSD | 07/10/2021 | 60 | DEBJYOTI GOSWAMI | 2.77 | 2.53 | 100 | 1
1529 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Shaktigarh Piped Water Supply Scheme , SM/07204 | Retrofitting | Providing bib cock,stop cock & PVC Pipe for existing FHTC of Shaktigar PWSS under Burdwan Sub Division ,Block:BWN-II under Burdwan Divn,PHE Dte. | 504/BSD | 06/03/2025 | 30 | SARKAR AGENCY | 0.94 | 0 | 0 | 100
1530 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Gangatikuri PWSS , SM/06750 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of GANGATIKURI Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, PHE Dte. | 1007/BWD | 05/02/2021 | 90 | M/S ASOKE GHOSH & BROTHERS | 47.52 | 29.44 | 61.96 | 1
1531 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Gangatikuri PWSS , SM/06750 | Retrofitting | Supply of 10 mm NB Gun-Metal Ferrule conforming to IS:2692-1989 for water tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-4] | 3186/BWD | 08/06/2021 | 30 | R.K. INDUSTRIES | 76.05 | 40.71 | 200 | 0
1532 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme , SM/07546 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Uddharanpur Piped Water Supply Scheme at Enayetpur, Naihati, Sankhai, Sitahati & Uddharanpur (1 No Habitation) Village (Mouza), Ketugram-II Block under Burdwan Division, PHE Dte. (Agreement No. 97/SE/CC/PHE/Dte of 2020-2021) | 913/BWD | 02/02/2021 | 60 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 86.77 | 52.73 | 50 | 1
1533 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme , SM/07546 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Uddharanpur village under UDDHARANPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.(Sl No-2) | 590/KTS | 06/09/2021 | 30 | M/S S. CHOUDHURY | 4.83 | 4.82 | 100 | 1
1534 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme , SM/07546 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Naihati village under UDDHARANPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-3) | 591/KTS | 06/09/2021 | 30 | M/S S. CHOUDHURY | 4.83 | 4.81 | 100 | 1
1535 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme , SM/07546 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Enayatpur and Sankhai village under UDDHARANPUR PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-1) | 589/KTS | 06/09/2021 | 30 | M/S S. CHOUDHURY | 4.85 | 4.85 | 100 | 1
1536 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme , SM/07546 | Retrofitting | Drinking water supply to 10 Nos ICDS for Uddharanpur water supply scheme Ketugram-II Block under Katwa Sub-Division under Burdwan Division, PHE Dte. | 36/KTS | 18/01/2021 | 30 | MAA KHEPIMAYER CHARANE | 4.79 | 0.02 | 100 | 1
1537 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Uddharanpur Piped Water Supply Scheme , SM/07546 | Retrofitting | Special maintenance and construction of sluice Valve chamber at Uddharanpur Piped water Supply Scheme at Ketugram-II Block, under Katwa Sub-Division within Burdwan Division PHE Dte.[Sl No-2] | 611/KTS | 19/06/2023 | 30 | BABUL SK | 0.97 | 0 | 0 | 100
1538 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme , SM/07550 | Retrofitting | Material Requisition To Resource Division | 5523/BWD | 23/12/2022 | 0 | Resource Division | 0.62 | 0 | 0 | 0
1539 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme , SM/07550 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mahindar Piped Water Supply Scheme at Mahindar Village (2 Nos habitations), Faimpur Village, Shitalpur Village, Sahapur Village (2 Nos. habitations & Parbatpur Village (2 Nos. habitations), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 684/BWD OF 2020-2021.] | 1456/BWD | 18/02/2021 | 60 | S.S. CONSTRUCTION | 73.07 | 71.59 | 100 | 1
1540 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme , SM/07550 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Madhabpur village and Madhabpur habitation of MADHABPUR Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿7C¿] | 7050/BWD | 22/12/2020 | 30 | KAJAL MUKHERJEE | 4.86 | 0.38 | 100 | 1
1541 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme , SM/07550 | Retrofitting | Laying of uPVC pipe for providing FHTC at Faimpur, Parbatpur, Sahapur, Silatpur and Mahindar Village within Mahindar Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr. F | 128/AE/HQ | 04/03/2022 | 15 | M/S S. CHOUDHURY | 4.82 | 4.81 | 100 | 1
1542 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme , SM/07550 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Sahapur and Faimpur village within the command area of MAHINDAR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : D] | 202/AE/HQ | 06/04/2022 | 30 | DEBJYOTI GOSWAMI | 4.84 | 4.81 | 100 | 1
1543 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme , SM/07550 | Retrofitting | Laying of rising main for interconnection of Pump House No 1 & 2 and distribution main alongwith bypass arrangement for Over Head Reservoir for Mahindar Piped water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte. [Gr.-D] | 1229/AE/HQ | 10/02/2021 | 30 | APORUPA CONSTRUCTION | 4.97 | 0 | 0 | 1
1544 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme , SM/07550 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Parbatpur village within the command area of MAHINDAR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : A] | 227/AE/HQ | 19/04/2022 | 30 | M/S S. CHOUDHURY | 4.78 | 4.78 | 100 | 1
1545 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme , SM/07550 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Mahindar village within the command area of MAHINDAR Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : E] | 203/AE/HQ | 06/04/2022 | 30 | M/S ASHA CONSTRUCTION | 4.85 | 4.84 | 100 | 1
1546 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme , SM/07550 | Retrofitting | Repairing of concrete road damaged due to laying of pipeline within command area of MAHINDER PWSS under Burdwan Division PHE Dte. | 760/AE/HQ | 23/08/2023 | 30 | GHOSH CONSTRUCTION | 2.68 | 2.12 | 100 | 100
1547 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Mahindar Piped Water Supply Scheme , SM/07550 | Retrofitting | Construction of approach road to get to the Head works site of MAHINDAR Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._2ND CALL [Group : G] | 205/AE/HQ | 06/04/2022 | 30 | APORUPA CONSTRUCTION | 4.84 | 0 | 0 | 100
1548 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme , SM/07551 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Siptai Piped Water Supply Scheme at Shrimanpur Village, Siptai Village, Ilampur Village, Prijpur Village & Gohaldaha Village, Jamalpur Block under Burdwan Division, PHE Dte. | 3342/BWD | 21/06/2021 | 45 | ASHOK KUMAR GHOSH | 41.9 | 80.84 | 100 | 1
1549 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme , SM/07551 | Retrofitting | Extension of pipeline including FHTC for Siptai Piped Water Supply Scheme at Ilampur (30 Nos) habitation for Sajal Gram (As per FIELD VERIFICATION REPORT DULY SIGNED BY PRADHAN FOR HAR GHAR JAL CERTIFICATION) within Jamalpur Block under Burdwan Division, PHE Dte. Gr.S. | 1394/BSD | 08/08/2022 | 5 | ROY CONSTRUCTION | 0.96 | 0 | 0 | 1
1550 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme , SM/07551 | Retrofitting | Extension of pipeline including providing FHTC for SIPTAI Piped Water Supply Scheme at Pirijpur 40 No¿s Habitation for Sajal Gram (As per FIELD VERIFICATION REPORT FOR HAR GHAR JAL CERTIFICATION within Jamalpur under Burdwan Division, PHE Dte. Gr.Q. | 1392/BSD | 08/08/2022 | 5 | ROY CONSTRUCTION | 0.95 | 0.95 | 100 | 1
1551 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme , SM/07551 | Retrofitting | Extension of pipeline including providing FHTC for SIPTAI Piped Water Supply Scheme at Siptai (42 Nos) Habitation for Sajal Gram (As per FIELD VERIFICATION REPORT DULY SIGNED BY PRADHAN FOR HAR GHAR JAL CERTIFICATION) within Jamalpur Block under Burdwan Division, PHE Dte. Gr.R | 1393/BSD | 08/08/2022 | 5 | ROY CONSTRUCTION | 0.97 | 0 | 0 | 100
1552 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme , SM/07551 | Retrofitting | Extension of pipeline including FHTC for SIPTAI Piped Water Supply Scheme at Pirijpur (40 Nos) Habitation for Sajal Gram (As per field verification report duly signed by Pradhan for Har Ghar Jal Certification) within Jamalpur Block under Burdwan Division, PHE Dte. | 1392-A/BSD | 08/08/2022 | 5 | ROY CONSTRUCTION | 0.95 | 0 | 0 | 0
1553 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme , SM/07551 | Retrofitting | Extension of pipeline including FHTC for SIPTAI Piped Water Supply Scheme at Siptai (42 Nos) Habitation for Sajal Gram (As per field verification report duly signed by Pradhan for Har Ghar Jal Certification) within Jamalpur Block under Burdwan Division, PHE Dte. | 1393-A/BSD | 08/08/2022 | 5 | ROY CONSTRUCTION | 0.97 | 0.97 | 100 | 100
1554 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme , SM/07551 | Retrofitting | Extension of pipeline including providing FHTC for Siptai Piped Water Supply Scheme at Ilampur[30 No's],Habitation for Sajal Gram (As per Sajal Gram(As per Field Verification Report duly signed by Pradhan for Har Ghar Jal Certification)within Jamalpur Block under Burdwan Division, PHE Dte. | 1394-A/BSD | 08/08/2022 | 5 | ROY CONSTRUCTION | 0.96 | 0.96 | 100 | 100
1555 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme , SM/07551 | Retrofitting | Providing FHTC for 100% coverage at Srimanpur (Village) (Habitation) for SIPTAI Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 5487/BWD | 13/12/2023 | 30 | GOUTAM KUMAR MITRA | 4.34 | 4.3 | 100 | 100
1556 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Siptai Piped Water Supply Scheme , SM/07551 | Retrofitting | Additional work for laying of UPVC pipeline for providing FHTC at Srimanpur (Village) (Habitation) under SIPTAI Piped W/S. Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 99/AE/HQ | 15/02/2024 | 30 | GOUTAM KUMAR MITRA | 0.72 | 0.72 | 100 | 100
1557 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme , SM/07557 | Retrofitting | Continuation work order for water tap connection in each household from existing distribution system within scheme jurisdiction in Kuli habitation of Shushunia piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Gr.-H] | 4787./BWD | 02/12/2020 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 2.92 | 1.91 | 65.35 | 1
1558 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme , SM/07557 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Shushuni Piped Water Supply Scheme at Shushuni (Part) (Ghoshpara & Sethpur habitation) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte. [Agreement No.661/BWD OF 2020-2021] | 1152/BWD | 09/02/2021 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 19.79 | 5.4 | 100 | 1
1559 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme , SM/07557 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Shushuni Piped Water Supply Scheme at Shushuni (Part) (Tentulia Bogpara habitation), Budhpur & Kalswar Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte.[Agreement No. 660/BWD OF 2020-2021] | 1151/BWD | 09/02/2021 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 22.8 | 9.63 | 100 | 1
1560 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme , SM/07557 | Retrofitting | Work order for Restoration of road and base concreting in FHTC for retrofitting of Shushunia water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 427/KSD | 11/05/2023 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 0.6 | 0.57 | 100 | 100
1561 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme , SM/07557 | Retrofitting | Laying of UPVC pipeline for smooth running of FHTC work of SHUSHUNIA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2342/BWD | 22/05/2023 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 22.26 | 21.07 | 100 | 100
1562 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme , SM/07557 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Kuli Village, Monteswar Block within Susunia PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 827/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0.72 | 100 | 100
1563 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Shushuni Piped Water Supply Scheme , SM/07557 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Budhpur Village, Monteswar Block within Susunia PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 828/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0.72 | 100 | 100
1564 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Gopikantapur Piped Water Supply Scheme at Bishnubati, Chakdighi & Dhapdhara Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 96/SE/CC/PHE/Dte of 2020-2021.] | 716/BWD | 28/01/2021 | 45 | BHARAT CONSTRUCTION | 47 | 16.87 | 100 | 1
1565 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H-3668) for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. for the month of May & June'22. | 462/VEH/22-23 | 29/08/2022 | 0 | MD HASIN | 0.51 | 0 | 0 | 0
1566 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
1567 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Gopikantapur Piped Water Supply Scheme at Kubajpur, Pranballabhpur (2 Nos Habitation) & Ramchandrapur Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 98/SE/CC/PHE/Dte of 2020-2021.] | 914/BWD | 02/02/2021 | 60 | S.S. CONSTRUCTION | 62.95 | 37.03 | 100 | 1
1568 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pipe connection and cost of pipes, specials for Gopikantapur & it's adjoining mouzas W/S. scheme under Burdwan Division, P.H.E. Dte.Ref. Drawing No.PC-I/OHR/11/2012 (Sheet No.1&2)(R-I) Dated 20.06.2012. [Revision - 1 dt. 20.12.2012] | 696/BWD | 02/02/2022 | 180 | M/S JAN MAHAMMAD | 76.26 | 0 | 0 | 0
1569 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Laying of uPVC pipeline due to obstruction arise for PWD roads within Gopikantapur W/S Scheme under Burdwan Division, PHE Dte. [Group: ¿F¿] | 1817/AE/HQ | 21/09/2021 | 30 | M/S S. CHOUDHURY | 3.55 | 0 | 0 | 1
1570 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Extension of pipeline (Branch & Sub Branch) for Functional House Hold Tap Connection from existing distribution system within the command area of GOPIKANTAPUR Piped Water Supply Scheme, at Bhairabpur village, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-H | 130/AE/HQ | 04/03/2022 | 15 | D.M. ENTERPRISE | 2.37 | 0 | 0 | 1
1571 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Laying of HDPE and UPVC pipe for providing FHTC at Pranballabhpur Village within GOPIKANTAPUR Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-G | 148/AE/HQ | 16/03/2022 | 20 | OM ENTERPRISE | 4.8 | 0 | 0 | 1
1572 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhairabpur Habitation of Gopikantapur piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. | 4818/BWD | 22/09/2021 | 30 | D.M. ENTERPRISE | 3.76 | 3.76 | 100 | 1
1573 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Laying of UPVC pipe for providing FHTC in different habitaion of Ramchandrapur, Pranballabpur Mouza within Gopikantapur piped water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte. [Gr.-B] | 1856/AE/HQ | 05/10/2021 | 30 | M/S S. CHOUDHURY | 4.82 | 4.82 | 100 | 1
1574 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Laying of uPVC pipe for providing FHTC at Gopikantapur, Ramchandrapur and Bishnubati Village within Gopikantapur Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-G | 129/AE/HQ | 04/03/2022 | 15 | S.S. CONSTRUCTION | 3.71 | 0 | 0 | 1
1575 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Material Requisition To Resource Division | 1102/BWD | 26/02/2022 | 0 | Resource Division | 8.61 | 0 | 0 | 0
1576 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Preparation and Submission of DPR for Augmentation of Ground Water Based Piped Water Supply Scheme for GOPIKANTAPUR, Block:Jamalpur under Burdwan Division, P.H.E Dte. | 1911/BSD | 28/08/2024 | 15 | MEASURE LAND | 0.78 | 0 | 0 | 0
1577 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Sinking of 300 mm X 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) with construction of Pump House & Boundary wall of GOPIKANTAPUR Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman under Burdwan Division PHE Dte. [FOR 3rd. TUBE WELL SITE]. | 786/BWD | 27/02/2024 | 440 | BIBHUTI SHAW | 23.9 | 0 | 0 | 40
1578 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting withinthe command area of Gopikantapur Piped Water Supply Scheme at Jamalpur Block , SM/07775 | Retrofitting | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 0 | 40
1579 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block , SM/07781 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Joykrishnapur Piped Water Supply Scheme at Joykrishnapur (4 Nos Habitation), Pilgram & Taranagar (2 Nos Habitation) Village (Mouza), Galsi-II Block under Burdwan Divn., PHE Dte.[Agreement No. 609/BWD OF 2020-2021] | 752/BWD | 29/01/2021 | 45 | SUDHAMAY MAJUMDAR | 43.97 | 73.64 | 170.11 | 1
1580 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block , SM/07781 | Retrofitting | Restoration of damaged pipeline of distribution main for construction of drain, concrete road etc. at various point at Jaykrishnapur, Taranagar and Pilgram village for providing FHTC within Jaykrishnapur W/S Scheme in Galsi-II Block under Burdwan Division, P.H.E. Dte.[SL-A] | 162/DSD | 16/03/2022 | 30 | SUDHAMAY MAJUMDAR | 4.81 | 4.78 | 100 | 1
1581 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block , SM/07781 | Retrofitting | Sinking of 200mm dia River bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Taranagar village under Joykrishnapur water supply scheme,Block -Galsi-II, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-A] | 533/DSD | 22/08/2022 | 21 | ANIRUDDHA FARUQUE | 4.35 | 0 | 0 | 1
1582 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block , SM/07781 | Retrofitting | Sinking of 200mm dia River bank Tube Well 60 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) at Simuliya village under Joykrishnapur water supply scheme,Block -Galsi-II, Dist - Purba Bardhaman under Durgapur Sub Division, PHE Dte. [Gr.-B] | 534/DSD | 22/08/2022 | 21 | SANDIPAN SENGUPTA | 4.35 | 4.36 | 100 | 1
1583 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block , SM/07781 | Retrofitting | Making Connection with 90 mm dia uPVC pipe within Node 162-168 for improvement of water supply to FHTC at Taranagar village within Jaykrishnapur and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-24] | 722/DSD | 30/12/2022 | 30 | TARAMA AGENCY | 2.07 | 1.98 | 100 | 100
1584 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block , SM/07781 | Retrofitting | Laying of parallel line with 90 mm dia uPVC pipe within Node 86-88 and providing air valve for improvement of water supply to FHTC at Pilgram village within Jaykrishnapur and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-I) | 81/DSD | 11/02/2022 | 30 | TARAMA AGENCY | 3.12 | 3.02 | 100 | 1
1585 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block , SM/07781 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of April'23. | 203/JJM | 01/06/2023 | 0 | SUJAUDDIN SEKH | 0.4 | 0 | 0 | 0
1586 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jay Krishnapur Piped Water Supply Scheme at Galsi-II Block , SM/07781 | Retrofitting | Vehicle bill for the month of September & October'2023. | 961/JJM | 01/12/2023 | 0 | SUJAUDDIN SEKH | 0.65 | 0 | 0 | 0
1587 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village and Bandh-O-Tawra & Nunari habitation of MAHACHANDA piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-529/BWD/2020-21) | 3344/BWD | 18/09/2020 | 30 | PAPRI HAZRA | 4.86 | 9.71 | 200 | 1
1588 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village and Bandh-O-Tawra & Nunari habitation of MAHACHANDA piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-530/BWD/2020-21) | 4006/BWD | 14/10/2020 | 30 | PAPRI HAZRA | 4.79 | 9.57 | 200 | 1
1589 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda village (Iymapara & Mahachanda (Part) habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 01] | 577/BWD | 25/01/2021 | 15 | S. MONDAL | 4.86 | 4.86 | 100 | 1
1590 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda (Part) village (Aymapara & Mahachanda (P) habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte [SL. No. : 15] | 1466/BWD | 18/02/2021 | 15 | BARABELUN NO.-II G.P. UNEMPLOYED CO-OP LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.86 | 4.78 | 100 | 1
1591 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village (Patuna habitation) & Parhat village (Parhat habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [SL. No. : 04] | 6266/BWD | 02/11/2021 | 15 | PAPRI HAZRA | 4.86 | 4.78 | 100 | 1
1592 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Restoration of damaged flanks during laying of distribution pipe with jhama metal and moorum of Bardhaman Katwa road from Shibpur towards 6th Mile ( From Node 89 -64) of Mahachanda Water Supply Scheme within Durgapur Sub Division Under Burdwan Division, PHE Dte.[SL-D] | 165/DSD | 16/03/2022 | 30 | PREMANANDA ROY BISWAS | 3.89 | 0 | 0 | 1
1593 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda village and Mahachanda habitation of MAHACHANDA piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-527/BWD/2020-21) | 3343/BWD | 18/09/2020 | 30 | BIPLAB SAMANTA | 4.86 | 9.71 | 200 | 1
1594 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda village and Mahachanda habitation of MAHACHANDA piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. (Tr No.-528/BWD/20-21) | 4270/BWD | 03/11/2020 | 30 | BIPLAB SAMANTA | 4.86 | 9.71 | 200 | 1
1595 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village (Patuna habitation) & Parhat village (Parhat habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 03] | 6265/BWD | 02/11/2021 | 15 | BIPLAB SAMANTA | 4.86 | 4.86 | 100 | 1
1596 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Restoration of pipeline at 6-Mile_Shibpur-Dharampur along & across Bardhaman-Katwa Road (SH-7) & providing FHTC at Aimapara (Part), Mahachanda (Part), Shibpur, Dharampur, Nunari (Part) Village (Mouza) under MAHACHANDA Piped W/S. Scheme under Burdwan Division, PHE. Dte. | 6934/BWD | 13/12/2021 | 45 | PREMANANDA ROY BISWAS | 43.33 | 41.32 | 100 | 1
1597 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Extension of Pipeline for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mahachanda Piped Water Supply Scheme , Block- Bhatar within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-D] | 97/DSD | 18/02/2022 | 30 | BIPLAB SAMANTA | 3.54 | 3.54 | 100 | 1
1598 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Restoration of damaged flanks during laying of distribution pipe with jhama metal and moorum of Bardhaman Katwa road from Shibpur towards 6th Mile ( From Node 89 -64) of Mahachanda Water Supply Scheme within Durgapur Sub Division Under Burdwan Division, PHE Dte.[SL-D] | 165/DSD | 16/03/2022 | 30 | OM ENTERPRISE | 3.88 | 3.86 | 100 | 1
1599 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Laying of parallel line with 90 mm dia uPVC pipe within Node J8-J-48 and providing air valve for improvement of water supply to FHTC at Twara village within MAHACHANDA and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. | 3967/BWD | 13/09/2022 | 30 | PAPRI HAZRA | 5.26 | 4.99 | 94.87 | 1
1600 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Mahachanda village (Shibpur-Dharampur habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 02] | 578/BWD | 25/01/2021 | 15 | PRONAB KUMAR DEY | 4.86 | 4.86 | 100 | 1
1601 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Bhatar Block under Burdwan Division, PHE. Dte. | 268/BWD | 14/01/2022 | 30 | BHARAT CONSTRUCTION | 14.17 | 0 | 0 | 1
1602 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village (Patuna habitation) & Parhat village (Parhat habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 03] | 582/BWD | 25/01/2021 | 15 | BIPLAB SAMANTA | 4.86 | 9.73 | 200 | 0
1603 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nunari village (Patuna habitation) & Parhat village (Parhat habitation) of Mahachanda Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [SL. No. : 04] | 583/BWD | 25/01/2021 | 15 | PAPRI HAZRA | 4.86 | 9.68 | 200 | 0
1604 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Extension of pipeline at Parhat & Patuna village of Mahachanda and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur (Bardhaman North) Sub Division under Burdwan Division, P.H.E. Dte. (Gr.-C) | 418/DSD | 02/07/2021 | 30 | PAPRI HAZRA | 4.18 | 4 | 100 | 0
1605 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Laying of UPVC pipeline in TAWRA Habitation within Mahachanda PWSS WITHIN Durgapur(Burdwan North ) Sub Division ,PHE Dte, Under Burdwan Division PHE Dte. | 622/DSD | 05/08/2024 | 30 | MAA MAHAMAYA CONSTRUCTION | 4.54 | 4.54 | 100 | 100
1606 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Arrangement of drinking water supply by installation of solar submersible pump including sinking of 200 mm. dia. Tube well 150 Mtr. Deep by direct rotary rig method, Laying dist. System, FHTC for Nunari Village under MAHACHANDA Piped W/S. Scheme, Block Bhatar under Burdwan Division, PHE Dte. | 2525/BWD | 03/07/2024 | 120 | THE BUSINESS ENGINEERS INDIA | 28 | 0 | 0 | 25
1607 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in Parhat (Part-B) village of MAHACHANDA piped W/S Scheme within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | 910/DSD | 15/12/2023 | 434 | OM ENTERPRISE | 0.96 | 0.45 | 35.41 | 100
1608 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in Parhat (Part-A) village of MAHACHANDA piped W/S Scheme within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | 911/DSD | 15/12/2023 | 434 | OM ENTERPRISE | 0.95 | 0 | 0 | 100
1609 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahachanda Piped Water Supply Scheme at Bhatar Block , SM/07867 | Retrofitting | Laying of UPVC and HDPE Pipe Line at Bostom Para of MAHACHANDA W/S Scheme within BHATAR Block Under Durgapur Sub Division , Under Burdwan Division PHE Dte | 297/DSD | 20/02/2025 | 131 | BAMDEB CONSTRUCTION & CO | 1.93 | 0 | 0 | 100
1610 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAMKRISHNAPUR Piped Water Supply Scheme at Raina-I Block , SM/07873 | Retrofitting | Providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Ramkrishnapur piped water supply scheme at Jamui, Fakirpur, Khemta, Ramkrishnapur & Chandipur village (Mouza), Raina-I Block under Burdwan Division, PHE Dte. | 4217/BWD | 16/08/2021 | 45 | GHOSH CONCERN | 36.49 | 35.45 | 50 | 1
1611 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAMKRISHNAPUR Piped Water Supply Scheme at Raina-I Block , SM/07873 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ I Block under Burdwan Division, PHE. Dte. | 39/BWD | 05/01/2022 | 30 | HAFIJUR RAHAMAN MIDYA | 15.62 | 0 | 0 | 1
1612 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAMKRISHNAPUR Piped Water Supply Scheme at Raina-I Block , SM/07873 | Retrofitting | Extension of pipeline for Ramkrishnapur Water Supply Scheme at Ramkrishnapur and chandipur village within Raina-I Block , under Burdwan Division, PHE Dte. Gr.B. | 43/BSD | 10/01/2022 | 30 | SUPRIYA RAY | 4.79 | 0 | 0 | 1
1613 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS , SM/06771 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SONARUDRA Piped Water Supply Scheme at Purbasthali-I Block under Burdwan Division, PHE Dte.(Agreement No. 51/2020-2021 OF SE/CC/PHE. DTE.) | 4900/BWD | 07/12/2020 | 90 | J.D.J. ENTERPRISE | 88.29 | 44.19 | 50.05 | 0
1614 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS , SM/06771 | Retrofitting | Interconnection of tube well no.-1 & Tube well No.-2 along with connection of existing OHR by 100 mm dia DI (K9) pipe and construction of sluice valve chamber of Sonarudra water supply scheme within Kalna Sub-Division, under Burdwan Division, PHE Dte. | 8/KSD | 05/01/2021 | 30 | BISWAS ENTERPRISE | 2.54 | 4.57 | 200 | 1
1615 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS , SM/06771 | Retrofitting | Providing FHTC from the existing distribution line and special repair of existing different dia UPVC pipeline including supply of Sluice Valve for proper functioning the existing line of Sonarudra W/S Scheme of Purbasthali-I block within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | 1260/KSD Dt-22.12.2021 | 22/12/2021 | 31 | BABUL SK | 4.14 | 2.42 | 100 | 1
1616 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS , SM/06771 | Retrofitting | Providing FHTC from the existing distribution line and special repair of existing different dia UPVC pipeline including supply of Sluice Valve for proper functioning the existing line of Sonarudra W/S Scheme of Purbasthali-I block within Kalna Sub-Division under Burdwan Division, PHE Dte. | 29/KSD | 07/01/2022 | 30 | BABUL SK | 4.14 | 0.92 | 100 | 1
1617 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS , SM/06771 | Retrofitting | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-5]. | 3590/BWD | 13/07/2021 | 30 | PREMANANDA ROY BISWAS | 127.5 | 84.65 | 200 | 1
1618 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS , SM/06771 | Retrofitting | Construction of pathway & plinth protection of Pump House and Surface Drain at the Head Work Site of Sonarudra water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | 1218/KSD Dt-10.12.2021 | 10/12/2021 | 31 | BABUL SK | 1.77 | 1.72 | 100 | 1
1619 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS , SM/06771 | Retrofitting | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] | 4318/BWD | 04/11/2020 | 10 | MD HASIN | 4.93 | 1.02 | 100 | 1
1620 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS , SM/06771 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kashira Piped Water Supply Scheme at Chanak (Part), Gopalbera, Krishnapur, Gatistha & Kashira (Part) Village (Mouza), Mongolkot Block under Burdwan Division, PHE Dte. (Agreement No. 99/SE/CC/PHE/Dte of 2020-2021) | 915/BWD | 02/02/2021 | 60 | MAJUMDER ENTERPRISE | 53.52 | 14.36 | 200 | 0
1621 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Sonarudra PWSS , SM/06771 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Paranpur village and Paranpur habitation of Jahannagar piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-814/BWD/2020-21) | 4110/BWD | 16/10/2020 | 30 | J. K. CORPORATION | 4.86 | 5.49 | 200 | 0
1622 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09413 | Augmentation | Route Survey and preparation of DPR for PALITA PWSS under Ketugram-I Block under Katwa Sub-Division under Burdwan Division PHE Dte.[Sl No-04] | 55/KTS | 25/01/2022 | 21 | RADIANT | 2.78 | 2.78 | 100 | 1
1623 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09413 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
1624 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09413 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of PALITA Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte._Sl. No. 09 | 143/AE/HQ | 16/03/2022 | 10 | MAKALI ENGINEERING CORPORATION | 4.52 | 0 | 0 | 0
1625 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09413 | Augmentation | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day.(Sl No-1) | 499/KTS | 22/05/2023 | 70 | M/S MUNMUN DEY | 0.9 | 0.3 | 100 | 100
1626 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09413 | Augmentation | Material Requisition To Resource Division | 543/BWD | 27/01/2022 | 0 | Resource Division | 15.49 | 0 | 0 | 0
1627 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09413 | Augmentation | Material Requisition To Resource Division | 1530/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
1628 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09413 | Augmentation | Material Requisition To Resource Division | 929/BWD | 16/02/2022 | 0 | Resource Division | 26.89 | 0 | 0 | 0
1629 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09413 | Augmentation | Augmentation of PALITA Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 350 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation, Construction of boundarywall at HW and 2nd TW site with repairing of Pump house -I & II under Ketugram-I Block, District:- Purba-Burdwan. | 2139/BWD | 25/04/2022 | 1347 | M/S GUPTA ENTERPRISE | 472.81 | 448.02 | 94.76 | 98
1630 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PALITA PWSS TO ACCOMMODATE FHTC IN KETUGRAM-I BLOCK UNDER KATWA SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09413 | Augmentation | Continuation order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. (Sl No-1) | 1016/KTS | 20/09/2023 | 23 | M/S MUNMUN DEY | 0.3 | 0.09 | 100 | 0
1631 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. , SM/08711 | Retrofitting | Providing Functional Household Tap Connection (FHTC) for the balance household in (Kolsara, Kulingram Uttar, Kulingram Dakshin, Ranapara Uttar, Ranapara Dakshin, Dutta Para, Kantagoria, Gokul, Gopalpur, Reora & Chack) Part Habitations from existing distribution system within the command area of KULINGRAM Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. | 4536/BWD | 06/09/2021 | 30 | SK ALIM | 31.2 | 30 | 100 | 1
1632 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. , SM/08711 | Retrofitting | Extension of pipeline for KULINGRAM Water Supply Scheme FOR FHTC work within Jamalpur Block , under Burdwan Division, PHE Dte. Gr.B | 198/BSD | 01/02/2022 | 30 | SK ALIM | 4.34 | 3.37 | 100 | 1
1633 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. , SM/08711 | Retrofitting | HDPE pipeline of 75 mm dia of Kulingram water supply scheme for FHTC (Gopalpur, Ranapara, Koisara, Gokul Katagoria)of Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-A] | 1424/BSD | 25/10/2021 | 30 | SK ALIM | 4.52 | 4.48 | 100 | 1
1634 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. , SM/08711 | Retrofitting | Relaying of damage of pipeline due to irrigation cannel and 75 mm dia HDPE pipeline with FHTC for KULINGRAM Water Supply Scheme within Jamalpur Block,under Burdwan Division, PHE Dte. Group : A | 828/BSD | 23/05/2022 | 30 | BISWAKARMA CONSTRUCTION | 4.96 | 4.66 | 100 | 1
1635 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. , SM/08711 | Retrofitting | Sinking of additional 250 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for KULINGRAM Piped Water Supply Scheme, Block - Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 2473/BWD | 12/05/2022 | 30 | NADIA TUBEWELLS | 10.32 | 0 | 0 | 1
1636 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. , SM/08711 | Retrofitting | Extension of pipeline for Kulingram Water Supply Scheme (Rewra village, Gokul Village, Kulingram uttar Village, Chak Village, Ranapara Village, Kantagaria Village, Mirjapur Village, Duttapara Village, Kolsara Village, Gopalpur Village) within Jamalpur Block including water tap connection (FHTC) under Burdwan Division, PHE Dte. | 3116/BWD | 02/06/2021 | 60 | SK ALIM | 151.26 | 291.46 | 200 | 0
1637 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. , SM/08711 | Retrofitting | Laying of Interconnection of 4th Tube well site and Laying of 90 mm dia HDPE pipeline for KULINGRAM Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 3917/BWD | 05/09/2023 | 30 | BARABELUN NO.-II G.P. UNEMPLOYED CO-OP LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 8.28 | 6.08 | 100 | 100
1638 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. , SM/08711 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Gopalpur Village, Jamalpur Block within Kulingram PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 875/AE/HQ | 07/11/2023 | 30 | PAPRI HAZRA | 0.76 | 0.72 | 100 | 100
1639 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. , SM/08711 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Gangarambati Village, Jamalpur Block within Kulingram PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 876/AE/HQ | 07/11/2023 | 30 | PAPRI HAZRA | 0.76 | 0.72 | 100 | 100
1640 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. , SM/08711 | Retrofitting | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 0 | 40
1641 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KULINGRAM Piped Water Supply Scheme at JAMALPUR Block under Burdwan Division, P.H.E. DTE. , SM/08711 | Retrofitting | Providing FHTC for Declaration of Sajal Gram at Duttapara (25 Nos), Kamalpur (04 Nos) and Chak Mujaffarpur (07) Mouzas (Habitation) for KULINGRAM Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte._2ND CALL | 967/AE/HQ | 22/11/2024 | 30 | SOUMYAVASH DAS | 2.47 | 0 | 0 | 100
1642 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, P.H.E. DTE. , SM/08713 | Retrofitting | Connection of CWR & IEP with the existing distribution system under Natungram Piped Water Supply Scheme under Katwa Sub-Division under Burdwan Division, P.H.E. Dte. [Sl No-01] | 160/KTS | 24/02/2022 | 30 | JAHAR GHOSH | 1.5 | 1.36 | 100 | 1
1643 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, P.H.E. DTE. , SM/08713 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Natungram Piped Water Supply Scheme at Natungram (Part) & Charnarayanpur Village (Mouza), Ketugram-II Block under Burdwan Division, PHE Dte. (Agreement no. 567/BWD of 2020-2021) | 357/BWD | 15/01/2021 | 30 | JAHAR GHOSH | 22.73 | 6.83 | 100 | 1
1644 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, P.H.E. DTE. , SM/08713 | Retrofitting | Construction of sanitary system and drinking water supply arrangement for Head Work Site of Natungram Water Supply Scheme under Katwa Sub-Division within Burdwan Division P.H.E Dte. (Sl No-3) | 800/KTS | 10/12/2021 | 45 | JAHAR GHOSH | 1 | 0.23 | 100 | 1
1645 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, P.H.E. DTE. , SM/08713 | Retrofitting | Construction of Boundary wall including land development, Pathway and plantation at Head works site of Natungram water supply scheme, Block-Ketugram-II under Katwa Sub-Division under Burdwan Division, PHE Dte. [Tr No.-347/BWD/20-21] | 4282/BWD | 03/11/2020 | 60 | MOJAI SK | 31.33 | 8.94 | 100 | 1
1646 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme at Ketugram-II Block under Burdwan Division, P.H.E. DTE. , SM/08713 | Retrofitting | Regarding release of fund for restoration of road under PMGSY scheme under Ketugram-II Block Katwa Sub-Division PHE Dte. Khatundi to Chitahati (Package No-WB-22-47) | 896/JJM | 26/09/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 2.45 | 0 | 0 | 0
1647 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Srikhanda mouza within the command area of Srikhanda piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08716 | Retrofitting | Supplying, laying and commissioning of Rising main at pump no. - 2 of Srikhanda PWSS under Katwa Sub-Division under Burdwan Division, PHE Dte. [Sl No-07] | 444/KTS | 27/06/2022 | 30 | ASHOK KUMAR GHOSH | 1.84 | 1.84 | 100 | 1
1648 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Srikhanda mouza within the command area of Srikhanda piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08716 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of SRIKHANDA and its adjoining mouzas Piped Water Supply Scheme, Block Katwa I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 388/BWD | 31/01/2023 | 30 | SUBODH KUMAR MONDAL | 11.81 | 8.54 | 100 | 100
1649 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Srikhanda mouza within the command area of Srikhanda piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08716 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SRIKHANDA Piped Water Supply Scheme at Katwa - I Block under Burdwan Division, PHE Dte.(Agreement No. 53/2020-2021 OF SE/CC/PHE. DTE.) | 4880/BWD | 07/12/2020 | 90 | ASHOK KUMAR GHOSH | 96.84 | 58.5 | 100 | 1
1650 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Srikhanda mouza within the command area of Srikhanda piped Water Supply Scheme at Katwa-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08716 | Retrofitting | Construction of Pump House cum switch room (5.40 m x 3.60 m) with sanitary arrangement [As per Drawing No. : PHE/SE/CC/PH/DWG-01/2022-23] for additional TW. No - I(Beside BPHC) under Srikhanda PWSS (SM/08716) of Katwa-I Block under Katwa Sub-Division PHE Dte. | 1230/BWD | 22/04/2025 | 60 | BABUL SK | 6.75 | 0 | 0 | 100
1651 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Route Survey & Preparation of DPR for Shyamsundar W/S Scheme under Raina-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.7. | 182/BSD | 31/01/2022 | 30 | RADIANT | 2.9 | 2.89 | 100 | 1
1652 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Supply of 100 mm dia C.I. Sluice valve(P.N.-I) of Augmentation of Shyamsundar Water Supply Scheme of Raina-I under Burdwan Sub Division, PHE Dte. Gr.F. | 1603/BSD | 14/09/2022 | 15 | SK ALIM | 1.73 | 1.73 | 100 | 1
1653 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Extension of Pipeline for Shyamsundar village Uttar para of Augmentation of Shyamsundar Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.G. | 1604/BSD | 14/09/2022 | 30 | M/S PROCHESTA ENTERPRISE | 4.78 | 4.77 | 100 | 1
1654 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Extension of Pipeline for Shyamsundar village Dakshin para of Augmentation of Shyamsundar Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.I. | 1606/BSD | 14/09/2022 | 30 | SK ABDUL HALIM | 4.77 | 4.77 | 100 | 1
1655 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Concrete cutting of khalina, shibrampur, shyamsundar uttar para,shyamsundar dakshin para ,natungram village for Augmentation of Shyamsundar Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.D. | 1406/BSD | 10/08/2022 | 30 | SK ALIM | 4.68 | 4.68 | 100 | 1
1656 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Extension of Pipeline for Natungram and Shyamsundar village of Augmentation of Shyamsundar Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.C | 1479/BSD | 25/08/2022 | 45 | SK ABDUL HALIM | 4.84 | 4.83 | 100 | 1
1657 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
1658 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Conversion of ACSR Cond to AB CABL of 11KV Shyamsundar Feeder Emanating from Raina S/STN at Shyamsundar PWSS under Burdwan Division, PHE Dte. [Ref ID-860250397, Application ID-100000060727, dt.-16/09/2022] | 653/DW/22-23 | 28/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.08 | 0 | 0 | 0
1659 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Paharhati, Nababhat, Shyamsundar & Dewandighi-Mirzapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. | 4703/BWD | 19/10/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 3.61 | 100 | 1
1660 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Sand filling at PWD road side near bazar to thana more(Drawing NOD 15 to 16,16 to 17,6 to 89,11 to 12,12 to 13,12 to 156,10 to 11,13 to 14,14 to 15,1 to 2 to 267,2 to 3 ,7 to 8,7 to 82,4 to 5 ,5 to 6,6 to 82,3 to 4. at Shyamsundar Water supply scheme of Raina Block within Burdwan Division, PHE Dte. Gr.A. | 1224/BSD | 08/07/2022 | 7 | SK ALIM | 4.16 | 4.09 | 100 | 1
1661 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of SHYAMSUNDAR & its adjoining mouzas Piped Water Supply Scheme [Shyamsundar Mouza], Block ¿ Raina ¿ I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 4446/BWD | 27/09/2022 | 30 | SK ALIM | 9.87 | 8.55 | 100 | 1
1662 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Material Requisition To Resource Division | 532/BWD | 27/01/2022 | 0 | Resource Division | 15.09 | 0 | 0 | 0
1663 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Material Requisition To Resource Division | 901/BWD | 15/02/2022 | 0 | Resource Division | 23.47 | 0 | 0 | 0
1664 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Material Requisition To Resource Division | 1539/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
1665 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based SHYAMSUNDAR PWSS to accommodate FHTC in RAINA-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09495 | Augmentation | Augmentation of SHYAMSUNDAR Piped Water Supply Scheme with LDS, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test, Construction of boundary wall at Head works & 2nd TW site & FHTC under Raina ¿ I Block, District - Purba Bardhaman. | 1474/BWD | 14/03/2022 | 365 | SK ALIM | 474.78 | 412.65 | 100 | 100
1666 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Preparation of DPR for augmentation of Kaigram W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No- E) | 185/KSD | 21/02/2022 | 21 | LEMNISCATE | 2.66 | 2.66 | 100 | 1
1667 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
1668 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Material Requisition To Resource Division | 605/BWD | 28/01/2022 | 0 | Resource Division | 24.12 | 0 | 0 | 0
1669 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Material Requisition To Resource Division | 533/BWD | 27/01/2022 | 0 | Resource Division | 16.17 | 0 | 0 | 0
1670 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Material Requisition To Resource Division | 905/BWD | 15/02/2022 | 0 | Resource Division | 12.41 | 0 | 0 | 0
1671 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Material Requisition To Resource Division | 1563/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
1672 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Augmentation of KAIGRAM Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction 250 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Construction of Boundary wall under Kalna Sub-Division, Block - Monteswar, Dist. - Purba Bardhaman under Burdwan Division, PHE. Dte. | 697/BWD | 02/02/2022 | 365 | B.B.C. ENTERPRISE | 291.4 | 234.3 | 80.41 | 80
1673 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell site for KAIGRAM Piped Water Supply Scheme, Block - Monteswar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | 1959/BWD | 12/04/2022 | 45 | ACME CONSTRUCTION | 14.81 | 13.92 | 100 | 100
1674 | PURBA BARDHAMAN | Central Mechanical | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of Kaigram Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2564/CMD | 06/06/2023 | 30 | CHOUDHURY ENTERPRISE | 20.45 | 19.89 | 100 | 98
1675 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Work Order for "Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site for Augmentation of Kaigram Piped Water Supply Scheme (SM/09717) within Kalna Sub-Division under Burdwan Division, PHE Dte." | 2190/KSD | 15/03/2024 | 10 | PARTHA PRATIM ACHARYA | 4.56 | 4.56 | 100 | 100
1676 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Work Order for " Renovation of Pump House for Augmentation of Kaigram Piped Water Supply Scheme (SM/09717) under Kalna Sub-Division under Burdwan Division, PHE Dte. (1 no Pump House Repairing)" | 2203/KSD | 18/03/2024 | 10 | PARTHA PRATIM ACHARYA | 1.28 | 1.27 | 100 | 100
1677 | PURBA BARDHAMAN | Central Mechanical | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Quotation for new service connection (Load enhancement) at Kaigram PWSS PH-2. |  | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.48 | 0 | 0 | 0
1678 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Quotation from WBSEDCL for load enhancement of Kaigram water supply scheme for P.H.-1 & 2 under Burdwan Division, PHE Dte. | 732/JJM | 27/08/2024 | 0 | WBSEDCL | 5.01 | 0 | 0 | 0
1679 | PURBA BARDHAMAN | Central Mechanical | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Quotation for new service connection (Load enhancement) at Kaigram PWSS PH-1. |  | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.53 | 0 | 0 | 0
1680 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | WSork Order for "-Construction of Toilet (1.8 m x 1.8 m) with saitary arrangement in connection with Augmentation of Kaigram pwss (09717) pwss under Kalna sub division under Burdwan Division. [2 units]." | 1596/KSD | 28/10/2024 | 30 | SUPRIYA RAY | 4.91 | 0 | 0 | 100
1681 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Work order for "Protection works for 150 mm dia DI Rising main and to protect Boundary wall at Head works site by UC bullah in connection with Augmentation Kaigram pwss(SM/09717) under Kalna Sub-Division under Burdwan Division P.H.E. Dte." | 1922/KSD | 02/12/2024 | 21 | UNIQUE CONSTRUCTION | 4.42 | 0 | 0 | 100
1682 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Kaigram PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09717 | Augmentation | Providing of balance FHTC and other allied works at Brahmapur Mouza under the command area of Kaigram Piped Water Supply Scheme (SM/09717) in order to declare Sajalgram under Mamudpur GP-II under Manteshwar Block under Kalna Sub-Division under Burdwan Division, PHE Dte. | 1251/BWD | 23/04/2025 | 30 | MONDAL & CO. | 19.21 | 0 | 0 | 100
1683 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Route Survey and Preparation of DPR for KETUGRAM (ZONE-I & II ) PWSS under Ketugram-I & II Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-06] | 66/KTS | 27/01/2022 | 21 | RADIANT | 4.81 | 4.91 | 100 | 1
1684 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
1685 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Ketugram (Zone - I) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2569/CMD | 06/06/2023 | 30 | M/S, MONDAL ASSOCIATES. | 10.98 | 0 | 0 | 0
1686 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Supply , delivery & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 3 of Kandra [ Ketugram ] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. [ Block - Ketugram-I ] | 1170/CMD | 27/06/2022 | 365 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 10.38 | 9.64 | 100 | 1
1687 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Augmentation of Ketugram Water Supply Scheme [Zone-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | 2098/CMD | 08/09/2022 | 30 | STANDARD ELECTRICALS | 11.51 | 10.86 | 100 | 1
1688 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Baharan-Birampur, Kaithan, Majhigram-Sigot & Ketugram (Zone-I & II) Piped Water Supply Scheme within Katwa Sub-Division under Burdwan Division, P.H.E. Dte. | 4702/BWD | 19/10/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 7.22 | 100 | 1
1689 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Material Requisition To Resource Division | 1248/BWD | 07/03/2022 | 0 | Resource Division | 4.32 | 0 | 0 | 0
1690 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Material Requisition To Resource Division | 1549/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
1691 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Material Requisition To Resource Division | 1334/BWD | 08/03/2022 | 0 | Resource Division | 114.05 | 0 | 0 | 0
1692 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Material Requisition To Resource Division | 4631/BWD | 17/10/2022 | 0 | Resource Division | 0.06 | 0 | 0 | 0
1693 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Material Requisition To Resource Division | 3271/BWD | 29/07/2022 | 0 | Resource Division | 50.19 | 0 | 0 | 0
1694 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Inter connection work with MS pipe from OHR to Distribution system and restoration of village road and drains for Augmentation of KETUGRAM Z-II Piped Water Supply Scheme under Ketugram-II Block, Dist-Purba Bardhaman. | 5481/BWD | 13/12/2023 | 354 | S & P ENTERPRISE | 181.31 | 77.21 | 42.58 | 40
1695 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Sinking of additional 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Augmentation of KETUGRAM (ZONE-I) Piped Water Supply Scheme, Block - Ketugram - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | 2420/BWD | 11/05/2022 | 45 | AUXILIARY TUBE WELL DRILLERS | 23.9 | 20.87 | 100 | 100
1696 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Quotation from WBSEDCL for new service connection of Augmentation of ground water based Ketugram Zone-I PWSS. | 688/JJM | 14/08/2024 | 0 | WBSEDCL | 9.28 | 0 | 0 | 0
1697 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Augmentation of KETUGRAM ZONE-I (PART-A & PART-B) Piped Water Supply Scheme with LDS, FHTC, & Construction of 700 cum & 200 Cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation respectively under Ketugram-I Block, District:- Purba-Burdwan. | 3075/BWD | 11/07/2022 | 1135 | M/S S.S. ENTERPRISE | 930.6 | 737 | 79.2 | 70
1698 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 3 at Augumentation of Ketugram (Zone - II) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2573/CMD | 06/06/2023 | 30 | SOUNAK ENTERPRISE | 21.96 | 0 | 0 | 40
1699 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Augmentation of KETUGRAM ZONE-II Piped Water Supply Scheme with LDS, FHTC, & Construction of 1250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under Ketugram-II Block, District:- Purba-Burdwan. | 2996/BWD | 05/07/2022 | 880 | S & P ENTERPRISE | 1064.91 | 965.35 | 90.65 | 90
1700 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Continuation work order for Supply of 1 (one) No. Diesel driven Ambassador Car (Luxury Taxi) / Motor Cab on hire basis for the Office of the Assistant Engineer, under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.01.2025 to 30.06.2025]. | 1810/KTS | 31/12/2024 | 181 | KRISHNA MONDAL | 2.4 | 1.17 | 48.84 | 20
1701 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2741/BWD | 12/07/2024 | 538 | M/S M.M. ENTERPRISE | 205.15 | 0 | 0 | 65
1702 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Sinking of additional 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Augmentation of KETUGRAM (ZONE-II) Piped Water Supply Scheme, Block - Ketugram - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [3 Nos. GTW]. | 2421/BWD | 11/05/2022 | 965 | AUXILIARY TUBE WELL DRILLERS | 35.85 | 18.19 | 65.75 | 80
1703 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of KETUGRAM (Zone-I & II) Piped W/S. Scheme within Katwa Sub-Division under Burdwan Division, PHE. Dte. [Part-A]. | 2838/BWD | 19/07/2024 | 215 | ELECTROSTEEL CASTING LIMITED | 4.95 | 0 | 0 | 100
1704 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of KETUGRAM (Zone-I & II) Piped W/S. Scheme within Katwa Sub-Division under Burdwan Division, PHE. Dte. [Part-C]. | 2830/BWD | 19/07/2024 | 224 | JINDAL SAW LTD. | 4.63 | 0 | 0 | 100
1705 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KETUGRAM (ZONE I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM I & II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10085 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of KETUGRAM (Zone-I & II) Piped W/S. Scheme within Katwa Sub-Division under Burdwan Division, PHE. Dte. [Part-B]. | 2826/BWD | 19/07/2024 | 216 | KEJRIWAL CASTINGS LIMITED | 4.82 | 0 | 0 | 100
1706 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | Route Survey & Preparation of DPR for Borsul (Zone-I) & (Zone-II) W/S Scheme under Burdwan-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.1. | 176/BSD | 31/01/2022 | 30 | APEX ENGINEERING | 4.18 | 4.18 | 100 | 1
1707 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at BELNA Mouza & Head Works Site for BORSHUL (Zone-II) Piped Water Supply Scheme, Block - Burdwan - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. | 2709/BWD | 08/06/2023 | 45 | M/S D. PALIT & CO. | 19.82 | 17.8 | 100 | 100
1708 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | Material Requisition To Resource Division | 4852/BWD | 20/10/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
1709 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | New service connection charges for Borshul PWSS Z-II TW-1 | BP-2023-24-140 | 28/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.99 | 0 | 0 | 0
1710 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | Improvement works of Borshul Godown & other allied works under Augmentation of BORSHUL (Zone-II) PWSS in Bardhaman-II Block. (SM/10481) within Burdwan Division PHE Dte. | 2418/BWD | 27/06/2024 | 90 | ANWESHA CONSTRUCTION | 20.86 | 0 | 0 | 0
1711 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for BARSUL ZONE-II its Adjoining Mouza W/S Scheme, Block -BURDWAN-II within Burdwan Sub-Division, PHE Dte. (Mouza- Belna) | 509/BSD | 21/03/2023 | 45 | MOHAMMAD ISSA | 3.49 | 2.89 | 100 | 100
1712 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | Construction of 3.6mtr.x3.0mtr.Size pump house including plinth protection with surface drain at Head Work TW site for Borshul (Zone-II) Water Supply Scheme, Block: Burdwan-II within Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | 2042/BSD | 24/08/2023 | 45 | RAHAMAN ENTERPRISE | 4.84 | 4.84 | 100 | 100
1713 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | New service connection charges for Borshul PWSS ZONE-II, TW-2 | BP-2023-24-335 | 06/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.11 | 0 | 0 | 0
1714 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | Quotation for new service connection at Borsul W/S Scheme Zone-II, PH-III. | BP-2024-25-334 | 04/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.86 | 0 | 0 | 0
1715 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | Augmentation of Borshul (Zone-II) (Mouzas :- Belna, Manikhati, Jafrabad, Kalinagar, Baje Salepur, Totopara) Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under BARDHAMAN- II Block, District:- Purba-Burdwan. | 3101/BWD | 14/07/2022 | 898 | ASHOK KUMAR GHOSH | 342.55 | 311.53 | 95.43 | 80
1716 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring of Tube Well No- 01, 02 & 03 at Augmentation Borsul (Zone-II) [Block ¿Burdwan -2] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4178/CMD | 29/08/2023 | 491 | M/S, S.S. ENTERPRISE. | 35.95 | 23.47 | 67.86 | 100
1717 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | Construction of boundary wall at 2nd T/W Site (Belna-Mouza) of BARSUL Zone II Piped W/S. Scheme under Burdwan-II Block of Burdwan Division, PHE Dte. (Length =100.00 Mtr, Col-36 Nos). | 3142/BWD | 20/08/2024 | 134 | PANCHANAN CHAKROBORTY | 6.77 | 0 | 0 | 100
1718 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | Improvement works including repairing & remodelling of Borshul Inspection Banglow under Augmentation of BORSHUL (Zone-II) PWSS in Bardhaman-II Block. (SM/10481) within Burdwan Division PHE Dte. | 2971/BWD | 31/07/2024 | 90 | ESCON INDIA | 15.27 | 0 | 0 | 100
1719 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | Construction of switch room, rising main & Sinking of Tube-well at 3rd TW SITE for BARSHUL Zone-II Piped Water Supply Scheme under BARDHAMAN-II Block, District:- Purba-Bardhaman. | 1128/BWD | 14/03/2024 | 292 | M/S R.K. SAMANTA & CO. | 19.02 | 0 | 0 | 100
1720 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF BORSHUL (ZONE-II) PWSS BURDWAN-II PURBA BARDHAMAN , SM/10481 | Augmentation | Construction of boundary wall at 1ST TUBE WALL (HEAD WORK) Site of BARSUL Zone-II Piped W/S. Scheme under Burdwan-II Block of Burdwan Division, PHE Dte. (Length =174.00 Mtr, Col-65 Nos). | 2521/BWD | 03/07/2024 | 181 | RAHAMAN ENTERPRISE | 13.25 | 0 | 0 | 100
1721 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Purbasthali-I Block under Burdwan Division, PHE Dte.[Part-A] | 6738/BWD | 03/12/2021 | 15 | TAPAS KUMAR ROY | 3.78 | 2.21 | 58.48 | 0
1722 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Kalna-I Block under Burdwan Division, PHE Dte.[SL-13] | 6752/BWD | 03/12/2021 | 15 | BISWAS ENTERPRISE | 4.73 | 1.85 | 39.17 | 0
1723 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Purbasthali-II Block under Burdwan Division, PHE Dte.[Part-B][SL-27] | 6759/.BWD | 03/12/2021 | 15 | PARTHA PRATIM ACHARYA | 4.71 | 2.79 | 59.19 | 0
1724 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Memari-I Block under Burdwan Division, PHE Dte.[SL-21] | 6735/BWD | 03/12/2021 | 15 | N.S. ENTERPRISE | 3.89 | 1.31 | 33.62 | 0
1725 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Memari-I Block under Burdwan Division, PHE Dte.[SL-22] | 6736/BWD | 03/12/2021 | 15 | A R TRADERS | 4.01 | 1.74 | 43.37 | 0
1726 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Burdwan-I Block under Burdwan Division, PHE Dte. | 6748/BWD | 03/12/2021 | 15 | DEBJYOTI GOSWAMI | 4.84 | 1.04 | 100 | 0
1727 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Raina-I Block under Burdwan Division, PHE Dte. | 6760/BWD | 03/12/2021 | 15 | POMPA CONSTRUCTION CO. | 2.97 | 0.71 | 100 | 0
1728 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Memari-II Block under Burdwan Division, PHE Dte.[SL-23] | 6737/BWD | 03/12/2021 | 15 | M/S LOKE NIRMAN | 1.39 | 1.04 | 100 | 0
1729 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Kalna-II Block under Burdwan Division, PHE Dte.[sl-14] | 6753/BWD | 03/12/2021 | 15 | M/S UNIQUE | 3.9 | 3.81 | 100 | 0
1730 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Katwa-I Block under Burdwan Division, PHE Dte.[sl-15] | 6754/BWD | 03/12/2021 | 15 | CHANCHAL PAL | 2.06 | 1 | 100 | 0
1731 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Jamalpur Block under Burdwan Division, PHE Dte.[sl-03] | 6742/BWD | 03/12/2021 | 15 | ROY CONSTRUCTION | 4.78 | 3.51 | 100 | 0
1732 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Katwa-II Block under Burdwan Division, PHE Dte.[sl-16] | 6755/BWD | 03/12/2021 | 15 | OM CONSTRUCTION | 1.84 | 1.17 | 100 | 0
1733 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Monteswar Block under Burdwan Division, PHE Dte.[SL-22] | 6733/BWD | 03/12/2021 | 15 | PRONAB KUMAR DEY | 4.01 | 2.29 | 100 | 0
1734 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Burdwan-II Block under Burdwan Division, PHE Dte. [SL NO.-10] | 6749/BWD | 03/12/2021 | 15 | GOUTAM KUMAR MITRA | 2.42 | 2.04 | 100 | 0
1735 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Khandaghosh Block under Burdwan Division, PHE Dte.[SL-20] | 6734/BWD | 03/12/2021 | 15 | SOUMYAVASH DAS | 3.33 | 2.47 | 100 | 0
1736 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Jamalpur Block under Burdwan Division, PHE Dte.[SL-04] | 6743/BWD | 03/12/2021 | 15 | ROY BISWAS CONSTRUCTION | 4.72 | 2.67 | 100 | 0
1737 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Bhatar Block under Burdwan Division, PHE Dte.[SL-08] | 6747/BWD | 03/12/2021 | 15 | DEEPAK ENTERPRISE | 4.47 | 0.59 | 100 | 0
1738 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Ausgram-II Block under Burdwan Division, PHE Dte.[SL-06] | 6745/BWD | 03/12/2021 | 15 | TARAMA AGENCY | 2.42 | 0.42 | 100 | 0
1739 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Galsi-I Block under Burdwan Division, PHE Dte.[SL-11] | 6750/BWD | 03/12/2021 | 15 | PAPRI HAZRA | 4.67 | 2.33 | 100 | 0
1740 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Jamalpur Block under Burdwan Division, PHE Dte. [Part-A][Sl-01] | 6740/BWD | 03/12/2021 | 15 | MUKHERJEE ENTERPRISE | 4.77 | 2.85 | 100 | 0
1741 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte. [Part-B] | 674/BWD | 03/12/2021 | 15 | KAJAL MUKHERJEE | 4.77 | 1.84 | 100 | 0
1742 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Purbasthali-II Block under Burdwan Division, PHE Dte. [Part-A][SL-26] | 6758/BWD | 03/12/2021 | 15 | MOYAZZEM CONSTRUCTION | 4.67 | 2.07 | 100 | 0
1743 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Mongalkote Block under Burdwan Division, PHE Dte.[SL-30] | 6762/BWD | 03/12/2021 | 15 | ASMA ENTERPRISE | 3.45 | 2.71 | 100 | 0
1744 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Purbasthali-I Block under Burdwan Division, PHE Dte.[Part-B][SL-25] | 6759/BWD | 03/12/2021 | 15 | M/S SAYAN CHAKRABORTY | 3.79 | 2.29 | 78.81 | 0
1745 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within scheme jurisdiction of different piped water supply schemes within Ketugram-II Block under Burdwan Division, PHE Dte.[SL-18] | 6757/BWD | 03/12/2021 | 15 | ABDUL HAI | 2.97 | 2.67 | 100 | 0
1746 | PURBA BARDHAMAN | Burdwan Division | Details Project Report on Providing Water Tap Connection in each School (1021 Nos) for 100% School Coverage from existing Distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purba Bardhaman District under Burdwan , SM/10378 | School | Providing leftout water tap connection in each school for 100 % school coverage from existing distribution system within the scheme jurisdiction of different piped water supply schemes within Ketugram-I Block under Burdwan Division, PHE Dte. [SL-17] | 6756/BWD | 03/12/2021 | 15 | DULU MIDDA | 4.71 | 4.07 | 100 | 100
1747 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme , SM/07822 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mondalgram Piped Water Supply Scheme at Mondalgram (10 Nos Habitation) Village (Mouza), Memari-II Block under Burdwan Division, PHE Dte. | 3879/BWD | 27/07/2021 | 60 | SUPRIYA RAY | 102.04 | 83.81 | 82.14 | 1
1748 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme , SM/07822 | Retrofitting | Extension of UPVC water supply line for Mondalgram and its adjoining mouzas W/S. Scheme within Memari- II Block, under Burdwan Division, PHE Dte. | 1576/BWD | 16/03/2022 | 30 | PAPRI HAZRA | 10.41 | 8.28 | 100 | 1
1749 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme , SM/07822 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) of MONDALGRAM & its adjoining mouzas Piped Water Supply Scheme, Block ? Memari ? II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 5196/BWD | 24/11/2022 | 30 | ANIRUDDHA FARUQUE | 11.24 | 9.82 | 100 | 1
1750 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme , SM/07822 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for MONDALGRAM its Adjoining Mouza W/S Scheme, Block -Memari-II within Burdwan Sub-Division, PHE Dte. (Mouza- Untia) | 508/BSD | 21/03/2023 | 45 | NARSAD SAIKH | 3.12 | 2.55 | 100 | 100
1751 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme , SM/07822 | Retrofitting | Additional quotation for Untia PHE of Augmentation of Mondalgram water supply scheme.[Memo No.-SGA/ADDL/QUOTI, Dated-21/06/23] | 358/JJM | 14/07/2023 | 0 | WEST BENGAL BUILDING AND OTHER CONSTRUCTION WORKERS WELFARE FUND | 2.16 | 0 | 0 | 0
1752 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme , SM/07822 | Retrofitting | Quotation of New connection charges at Augmentation of Mondalgram water supply scheme. [Application No.-5003701437] | 152/JJM | 26/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.64 | 0 | 0 | 0
1753 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme , SM/07822 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of MONDALGRAM Piped Water Supply Scheme at Bamunia (Part) (4 Nos. Habs.), Bhigobanpur, Halaodharpur (Part) (2 Nos. Habs.), Mondalgram (Part) (10 Nos. Habs.), Saragachi & Malamba Village (Mouza), Memari - II Block under Burdwan Division, PHE Dte. | 994/BWD | 21/02/2022 | 60 | SUPRIYA RAY | 61.24 | 53.61 | 87.55 | 70
1754 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mondalgram Piped Water Supply Scheme , SM/07822 | Retrofitting | Left out Functional House hold Tap Connection (FHTC) for MONDALGRAM and its adjoining Mouza W/S Scheme, block ¿Memari II within Burdwan Sub-Division, PHE Dte. | 1326/BWD | 22/03/2023 | 60 | DEBASHISH ENTERPRISE | 30.33 | 11.06 | 36.46 | 35
1755 | PURBA BARDHAMAN | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13453 | New | Material Requisition To Resource Division | 4026/BWD | 08/09/2023 | 0 | Resource Division | 0.98 | 0 | 0 | 0
1756 | PURBA BARDHAMAN | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13453 | New | New service connection charges for Kamalpur PWSS TW-1 | BP-2023-24-388 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.38 | 0 | 0 | 0
1757 | PURBA BARDHAMAN | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13453 | New | New service connection for KAMALPUR PWSS TW-2. | BP-2023-24-501 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.24 | 0 | 0 | 0
1758 | PURBA BARDHAMAN | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13453 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KACHUA & KAMALPUR Piped Water Supply Scheme under Purbasthali ¿ I Block, District:- Purba Bardhaman [NEW SCHEME] | 2344/BWD | 22/05/2023 | 863 | CONCORD ENGINEERING | 470.92 | 80.93 | 41.08 | 40
1759 | PURBA BARDHAMAN | Burdwan Division | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13453 | New | Different types of works involve in connection with Augmentation of SRIRAMPUR (Zone I & II) (SM/08103), MANGANPUR (SM/13327), KAMALPUR (SM/13453) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2429/BWD | 27/06/2024 | 480 | S.P. CONSTRUCTION | 500.89 | 0 | 0 | 2
1760 | PURBA BARDHAMAN | Central Mechanical | KAMALPUR PIPED WATER SUPPLY SCHEME , SM/13453 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at KAMALPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4095/CMD | 29/08/2023 | 519 | MUKHERJEE ART CENTRE | 21.4 | 20.46 | 94.96 | 100
1761 | PURBA BARDHAMAN | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/13425 | New | Material Requisition To Resource Division | 1262/BWD | 17/03/2023 | 0 | Resource Division | 7.32 | 0 | 0 | 0
1762 | PURBA BARDHAMAN | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/13425 | New | Material Requisition To Resource Division | 4024/BWD | 08/09/2023 | 0 | Resource Division | 2.93 | 0 | 0 | 0
1763 | PURBA BARDHAMAN | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/13425 | New | Material Requisition To Resource Division | 5074/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
1764 | PURBA BARDHAMAN | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/13425 | New | New Service Connection charges for Sahapur W/S Scheme TW-1 | BP-2023-24-13 | 17/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.9 | 0 | 0 | 0
1765 | PURBA BARDHAMAN | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/13425 | New | New Service Connection charges for Sahapur W/S Scheme TW-2 | BP-2023-24-14 | 17/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.08 | 0 | 0 | 0
1766 | PURBA BARDHAMAN | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/13425 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
1767 | PURBA BARDHAMAN | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/13425 | New | SAHAPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Memari-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 82/BWD | 09/01/2023 | 365 | S.K. CONSTRUCTION | 256.31 | 256.03 | 100 | 100
1768 | PURBA BARDHAMAN | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/13425 | New | Rest portion of OHR (Plaster, Painting and interconnection of Rising Main with Specials) at SAHAPUR Piped Water Supply Scheme under Memari-I Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 2419/BWD | 27/06/2024 | 90 | S.K. CONSTRUCTION | 20.6 | 13.33 | 100 | 100
1769 | PURBA BARDHAMAN | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/13425 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sahapur Water Supply Scheme [Block- Memari-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2480/CMD | 31/05/2023 | 30 | P.K. ENGINEERING | 29.29 | 24 | 100 | 98
1770 | PURBA BARDHAMAN | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/13425 | New | Designing, making and erection of Sign Board for SWAJAL GRAM in Sekhpur village of Memari-I Block under Sahapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte (5 nos Board) | 2370/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
1771 | PURBA BARDHAMAN | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/13425 | New | Designing,making and erection of Sign Board for SWAJAL GRAM in Nagarkona village of Memari-I Block under Sahapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte (5 Nos. Board) | 2306/BSD | 19/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
1772 | PURBA BARDHAMAN | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/13425 | New | Designing, making and erection of Sign Board for SWAJAL GRAM in Sahapur village of Memari-I Block under Sahapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos Board) | 2337/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
1773 | PURBA BARDHAMAN | Burdwan Division | Baikunthapur Piped Water Supply Scheme , SM/13294 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 4.39 | 0 | 0 | 0
1774 | PURBA BARDHAMAN | Burdwan Division | Baikunthapur Piped Water Supply Scheme , SM/13294 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 1.97 | 0 | 0 | 0
1775 | PURBA BARDHAMAN | Burdwan Division | Baikunthapur Piped Water Supply Scheme , SM/13294 | New | Material Requisition To Resource Division | 5044/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
1776 | PURBA BARDHAMAN | Central Mechanical | Baikunthapur Piped Water Supply Scheme , SM/13294 | New | Hiring of inspection vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of the Assistant Engineer,under CMD PHE Dte. w.e.f -01/08/2024 to 30/09/2024 .[Under JJM Works] | 834/CMSD | 07/06/2024 | 61 | PRODYUT GHOSH | 0.8 | 0.79 | 99.77 | 0
1777 | PURBA BARDHAMAN | Central Mechanical | Baikunthapur Piped Water Supply Scheme , SM/13294 | New | New service connection at BAIAKUNTHAPUR PWSS Ph-2 | BP-2023-24-443 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.73 | 0 | 0 | 0
1778 | PURBA BARDHAMAN | Central Mechanical | Baikunthapur Piped Water Supply Scheme , SM/13294 | New | New service connection at BAIAKUNTHAPUR PWSS Ph-1 | BP-2023-24-442 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.45 | 0 | 0 | 0
1779 | PURBA BARDHAMAN | Burdwan Division | Baikunthapur Piped Water Supply Scheme , SM/13294 | New | Shifting of pole for laying of water supply pipeline of Baikunthapur pwss under Burdwan Division, PHE Dte. [Ref ID-860315315, Application ID-100000120685, dt.-01/10/2024] | 1173/JJM | 17/12/2024 | 0 | WBSEDCL | 0.89 | 0 | 0 | 0
1780 | PURBA BARDHAMAN | Central Mechanical | Baikunthapur Piped Water Supply Scheme , SM/13294 | New | New service connection charges for Baikunthapur PWSS TW-2 | BP-2023-24-517 | 08/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.48 | 0 | 0 | 0
1781 | PURBA BARDHAMAN | Central Mechanical | Baikunthapur Piped Water Supply Scheme , SM/13294 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 0 | 12
1782 | PURBA BARDHAMAN | Central Mechanical | Baikunthapur Piped Water Supply Scheme , SM/13294 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Baikunthapur Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4006/CMD | 29/08/2023 | 30 | A.S. ENTERPRISE | 28.95 | 5.2 | 17.87 | 100
1783 | PURBA BARDHAMAN | Burdwan Division | Amra Piped Water Supply Scheme , SM/13296 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.95 | 0 | 0 | 0
1784 | PURBA BARDHAMAN | Burdwan Division | Amra Piped Water Supply Scheme , SM/13296 | New | Material Requisition To Resource Division | 5060/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
1785 | PURBA BARDHAMAN | Burdwan Division | Amra Piped Water Supply Scheme , SM/13296 | New | Continuation Work for the supply of one no. Diesel driven Motor Cab/Maxi Cab (Air Conditioner) on hire basis for the office of the Assistant Engineer, to be used by the Assistant Engineer, RWS Burdwan Sub-Divn., PHE. Dte. (Period from 01/05/2024 to 30/06/2024) | 154/RWS | 29/04/2024 | 61 | MD HASIN | 0.8 | 0.55 | 68.59 | 0
1786 | PURBA BARDHAMAN | Burdwan Division | Amra Piped Water Supply Scheme , SM/13296 | New | Material Requisition To Resource Division | 195/BWD | 10/01/2024 | 0 | Resource Division | 5.52 | 0 | 0 | 0
1787 | PURBA BARDHAMAN | Central Mechanical | Amra Piped Water Supply Scheme , SM/13296 | New | New Service connection forAmra PWSS TW-2. | BP-2023-24-473 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 16.94 | 0 | 0 | 0
1788 | PURBA BARDHAMAN | Central Mechanical | Amra Piped Water Supply Scheme , SM/13296 | New | New Service connection for Amra PWSS TW-1. | BP-2023-24-472 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.51 | 0 | 0 | 0
1789 | PURBA BARDHAMAN | Central Mechanical | Amra Piped Water Supply Scheme , SM/13296 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 0 | 12
1790 | PURBA BARDHAMAN | Central Mechanical | Amra Piped Water Supply Scheme , SM/13296 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Amra Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4005/CMD | 29/08/2023 | 642 | S.K. ENTERPRISE | 28.98 | 22.82 | 95.46 | 85
1791 | PURBA BARDHAMAN | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME , SM/13298 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 8.1 | 0 | 0 | 0
1792 | PURBA BARDHAMAN | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME , SM/13298 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 20.06 | 0 | 0 | 0
1793 | PURBA BARDHAMAN | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME , SM/13298 | New | Material Requisition To Resource Division | 5238/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
1794 | PURBA BARDHAMAN | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME , SM/13298 | New | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | 995/DSD | 29/12/2023 | 183 | SUJAUDDIN SEKH | 2 | 0.4 | 100 | 60
1795 | PURBA BARDHAMAN | Central Mechanical | RUPSA PIPED WATER SUPPLY SCHEME , SM/13298 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
1796 | PURBA BARDHAMAN | Central Mechanical | RUPSA PIPED WATER SUPPLY SCHEME , SM/13298 | New | New service connection for Rupsa W/S scheme TW No-1 | BP-2023-24-410 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0 | 0
1797 | PURBA BARDHAMAN | Central Mechanical | RUPSA PIPED WATER SUPPLY SCHEME , SM/13298 | New | Quotation for new service connection at RUPSA PWSS PH-2 | BP-2024-25-201 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0 | 0
1798 | PURBA BARDHAMAN | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME , SM/13298 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA, BALABATI, UKHRID & RUPSA Piped Water Supply Scheme under KHANDAGHOSH Block, District:- Purba Bardhaman [NEW SCHEME] | 1726/BWD | 13/04/2023 | 902 | S.P. CONSTRUCTION | 1710.27 | 230.92 | 50.42 | 45
1799 | PURBA BARDHAMAN | Central Mechanical | RUPSA PIPED WATER SUPPLY SCHEME , SM/13298 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Rupsa Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4013/CMD | 29/08/2023 | 30 | SAIKAT ENTERPRISE | 28.98 | 11.24 | 38.77 | 85
1800 | PURBA BARDHAMAN | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME , SM/13298 | New | Balance work for providing Functional Household Tap Connection (FHTC) within the command area BALABATI, AMRA & RUPSA W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | 609/BWD | 11/02/2025 | 120 | M/S S.S. ENTERPRISE | 194.58 | 0 | 0 | 0
1801 | PURBA BARDHAMAN | Burdwan Division | RUPSA PIPED WATER SUPPLY SCHEME , SM/13298 | New | FIXING OF DISPLAY BOARD WITH M.S STRUCTURE CONTAINING LAND DESCRIPTION AT RUPSA PWSS AND OTHER SCHEMES (49 Nos.) WITHIN KHANDOGHOSH BLOCK UNDER BURDWAN DIVISION , PHE Dte. | 1086/DSD | 11/12/2024 | 15 | SOUMYAVASH DAS | 3.18 | 0 | 0 | 100
1802 | PURBA BARDHAMAN | Burdwan Division | JADABGANJ PIPED WATER SUPPLY SCHEME , SM/13966 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.54 | 0 | 0 | 0
1803 | PURBA BARDHAMAN | Burdwan Division | JADABGANJ PIPED WATER SUPPLY SCHEME , SM/13966 | New | Material Requisition To Resource Division | 4927/BWD | 10/11/2023 | 0 | Resource Division | 36.98 | 0 | 0 | 0
1804 | PURBA BARDHAMAN | Burdwan Division | JADABGANJ PIPED WATER SUPPLY SCHEME , SM/13966 | New | Material Requisition To Resource Division | 4285/BWD | 29/09/2023 | 0 | Resource Division | 47.1 | 0 | 0 | 0
1805 | PURBA BARDHAMAN | Central Mechanical | JADABGANJ PIPED WATER SUPPLY SCHEME , SM/13966 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
1806 | PURBA BARDHAMAN | Durgapur W/S Division | JADABGANJ PIPED WATER SUPPLY SCHEME , SM/13966 | New | Continution Work Order for Demarcation of new land of PHE site under various places (Jadabganj PWSS) under Durgapur W/S Division, PHE Dte. | 1312/DWSD | 12/09/2024 | 15 | SAIKAT RAY | 28.57 | 0 | 0 | 70
1807 | PURBA BARDHAMAN | Durgapur W/S Division | JADABGANJ PIPED WATER SUPPLY SCHEME , SM/13966 | New | Acceptance cum Formal Work Order for Demarcation of new land of PHE site under various places (Jadabganj PWSS) under Durgapur W/S Division, PHE Dte. | 1243/DWSD | 29/08/2024 | 30 | SAIKAT RAY | 28.57 | 28.57 | 100 | 80
1808 | PURBA BARDHAMAN | Central Mechanical | JADABGANJ PIPED WATER SUPPLY SCHEME , SM/13966 | New | New service connection at Jadabganj PWSS PH-1 | BP-2023-24-432 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.24 | 0 | 0 | 0
1809 | PURBA BARDHAMAN | Central Mechanical | JADABGANJ PIPED WATER SUPPLY SCHEME , SM/13966 | New | QUOTATION FOR NEW SERVICE CONNECTION AT JADABGANJ PWSS TW-2 | BP-2024-25-191 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.7 | 0 | 0 | 0
1810 | PURBA BARDHAMAN | Burdwan Division | JADABGANJ PIPED WATER SUPPLY SCHEME , SM/13966 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ALIGRAM, JAYKRISHNAPUR, JADABGANJ & KALYANPUR Piped Water Supply Scheme under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 4581/BWD | 16/10/2023 | 965 | SAFECO ENTERPRISES | 1551.98 | 107.87 | 23.9 | 60
1811 | PURBA BARDHAMAN | Central Mechanical | JADABGANJ PIPED WATER SUPPLY SCHEME , SM/13966 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Jadabganj Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4065/CMD | 29/08/2023 | 620 | M/S. SWAPAN BANERJEE | 27.78 | 0 | 0 | 96
1812 | PURBA BARDHAMAN | Durgapur W/S Division | JADABGANJ PIPED WATER SUPPLY SCHEME , SM/13966 | New | Continution Work Order for Repairing and Renovation of Existing Room for prepair of Laboratory Room and Store Room , Boundary Wall with Gate, side drain with necessary allied works at Galsi-II Head Works site under Jadabganj Pipe Water Supply Scheme (JJM) under Durgapur W/S Division, PHE Dte. | 1348/DWSD | 20/09/2024 | 485 | SAIKAT RAY | 25.7 | 0 | 0 | 95
1813 | PURBA BARDHAMAN | Durgapur W/S Division | JADABGANJ PIPED WATER SUPPLY SCHEME , SM/13966 | New | Continution Work Order for Demarcation of new land of PHE site under various places (Jadabganj PWSS) under Durgapur W/S Division, PHE Dte. | 1658/DWSD | 29/11/2024 | 30 | SAIKAT RAY | 28.57 | 7.5 | 20.94 | 90
1814 | PURBA BARDHAMAN | Durgapur W/S Division | JADABGANJ PIPED WATER SUPPLY SCHEME , SM/13966 | New | Acceptance cum Formal Work Order for Repairing and Renovation of Existing Room for prepair of Laboratory Room and Store Room , Boundary Wall with Gate, side drain with necessary allied works at Galsi-II Head Works site under Jadabganj Pipe Water Supply Scheme (JJM) under Durgapur W/S Division, PHE Dte. | 1113/DWSD | 02/08/2024 | 120 | SAIKAT RAY | 25.7 | 0 | 0 | 80
1815 | PURBA BARDHAMAN | Burdwan Division | EORA PIPED WATER SUPPLY SCHEME , SM/13968 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 23.59 | 0 | 0 | 0
1816 | PURBA BARDHAMAN | Burdwan Division | EORA PIPED WATER SUPPLY SCHEME , SM/13968 | New | Material Requisition To Resource Division | 5249/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0 | 0
1817 | PURBA BARDHAMAN | Burdwan Division | EORA PIPED WATER SUPPLY SCHEME , SM/13968 | New | Material Requisition To Resource Division | 3833/BWD | 01/09/2023 | 0 | Resource Division | 3.71 | 0 | 0 | 0
1818 | PURBA BARDHAMAN | Central Mechanical | EORA PIPED WATER SUPPLY SCHEME , SM/13968 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
1819 | PURBA BARDHAMAN | Central Mechanical | EORA PIPED WATER SUPPLY SCHEME , SM/13968 | New | NEW SERVICE CONNECTION FOR EORA PWSS | BP-2023-24-548 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.64 | 0 | 0 | 0
1820 | PURBA BARDHAMAN | Central Mechanical | EORA PIPED WATER SUPPLY SCHEME , SM/13968 | New | NEW SERVICE CONNECTION FOR EORA PWSS TW -1. | BP-2023-24-642 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.54 | 0 | 0 | 0
1821 | PURBA BARDHAMAN | Central Mechanical | EORA PIPED WATER SUPPLY SCHEME , SM/13968 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Eora Water Supply Scheme [ Block- Bhatar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4056/CMD | 29/08/2023 | 990 | SUNRISE ENGINEERING CORPORATION | 26.98 | 20.94 | 77.62 | 90
1822 | PURBA BARDHAMAN | Burdwan Division | EORA PIPED WATER SUPPLY SCHEME , SM/13968 | New | Road Restoration for Eora PWSS in Bhatar Block under Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. | 624/DSD | 05/08/2024 | 30 | KOHINOOR CONSTRUCTION CO. | 5.38 | 0 | 0 | 0
1823 | PURBA BARDHAMAN | Burdwan Division | EORA PIPED WATER SUPPLY SCHEME , SM/13968 | New | EORA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1936/BWD | 24/04/2023 | 865 | TUSHAR KANTI GHOSH | 79.02 | 49.97 | 71.26 | 100
1824 | PURBA BARDHAMAN | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME , SM/14053 | New | Material Requisition To Resource Division | 1645/BWD | 06/04/2023 | 0 | Resource Division | 14.26 | 0 | 0 | 0
1825 | PURBA BARDHAMAN | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME , SM/14053 | New | Material Requisition To Resource Division | 1259/BWD | 17/03/2023 | 0 | Resource Division | 17.21 | 0 | 0 | 0
1826 | PURBA BARDHAMAN | Central Mechanical | KALIKAPUR PIPED WATER SUPPLY SCHEME , SM/14053 | New | New service connection charges for Kalikapur PWSS TW-1 | BP-2023-24-155 | 07/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.07 | 0 | 0 | 0
1827 | PURBA BARDHAMAN | Central Mechanical | KALIKAPUR PIPED WATER SUPPLY SCHEME , SM/14053 | New | New service connection charges for Kalikapur PWSS TW-2 | BP-2023-24-170 | 27/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.43 | 0 | 0 | 0
1828 | PURBA BARDHAMAN | Central Mechanical | KALIKAPUR PIPED WATER SUPPLY SCHEME , SM/14053 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kalikapur Water Supply Scheme [ Block- Katwa-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3953/CMD | 24/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 29.61 | 23.4 | 79.02 | 90
1829 | PURBA BARDHAMAN | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME , SM/14053 | New | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | 1009/KTS | 19/07/2024 | 60 | AJIT SAMANTA | 0.77 | 0.23 | 76.98 | 100
1830 | PURBA BARDHAMAN | Central Mechanical | KALIKAPUR PIPED WATER SUPPLY SCHEME , SM/14053 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
1831 | PURBA BARDHAMAN | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME , SM/14053 | New | KALIKAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -II Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1047/BWD | 09/03/2023 | 968 | PASCON | 629.59 | 351.46 | 55.82 | 67
1832 | PURBA BARDHAMAN | Burdwan Division | KALIKAPUR PIPED WATER SUPPLY SCHEME , SM/14053 | New | Balance work of OHR, Functional Household Tap Connection, Road restoration etc. for Kalikapur PWSS under KATWA -II Block under Katwa Sub-Division under Burdwan Division, PHED, District:- Purba-Bardhaman. | 192/BWD | 08/01/2025 | 662 | PASCON | 57.78 | 0 | 0 | 90
1833 | PURBA BARDHAMAN | Burdwan Division | SRIBATI PIPED WATER SUPPLY SCHEME , SM/14055 | New | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day.(Sl No-1) | 499/KTS | 22/05/2023 | 70 | M/S MUNMUN DEY | 0.9 | 0.3 | 100 | 100
1834 | PURBA BARDHAMAN | Burdwan Division | SRIBATI PIPED WATER SUPPLY SCHEME , SM/14055 | New | Material Requisition To Resource Division | 1633/BWD | 06/04/2023 | 0 | Resource Division | 9.14 | 0 | 0 | 0
1835 | PURBA BARDHAMAN | Burdwan Division | SRIBATI PIPED WATER SUPPLY SCHEME , SM/14055 | New | Material Requisition To Resource Division | 1258/BWD | 17/03/2023 | 0 | Resource Division | 17.24 | 0 | 0 | 0
1836 | PURBA BARDHAMAN | Central Mechanical | SRIBATI PIPED WATER SUPPLY SCHEME , SM/14055 | New | New service connection charges for Sribati PWSS TW-2 | BP-2023-24-61 | 17/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.58 | 0 | 0 | 0
1837 | PURBA BARDHAMAN | Central Mechanical | SRIBATI PIPED WATER SUPPLY SCHEME , SM/14055 | New | New service connection charges for SribatiPWSS TW-1 | BP-2023-24-111 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.83 | 0 | 0 | 0
1838 | PURBA BARDHAMAN | Burdwan Division | SRIBATI PIPED WATER SUPPLY SCHEME , SM/14055 | New | SRIBATI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -II Block, District:- Purba-Bardhaman [NEW SCHEME] | 776/BWD | 24/02/2023 | 1253 | MANASH GHOSH | 629.32 | 531.6 | 84.47 | 80
1839 | PURBA BARDHAMAN | Central Mechanical | SRIBATI PIPED WATER SUPPLY SCHEME , SM/14055 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sribati Water Supply Scheme [ Block- Katwa-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2520/CMD | 02/06/2023 | 30 | S.K. ELECTRICALS | 29.6 | 0 | 0 | 48
1840 | PURBA BARDHAMAN | Central Mechanical | SRIBATI PIPED WATER SUPPLY SCHEME , SM/14055 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
1841 | PURBA BARDHAMAN | Burdwan Division | SRIBATI PIPED WATER SUPPLY SCHEME , SM/14055 | New | Material Requisition To Resource Division | 321/BWD | 24/01/2024 | 0 | Resource Division | 26.68 | 0 | 0 | 0
1842 | PURBA BARDHAMAN | Central Mechanical | SRIBATI PIPED WATER SUPPLY SCHEME , SM/14055 | New | SUPPLY AND INSTALLATION WORKS FOR SRIBATI PWSS | BP-2023-24-559 | 21/02/2024 | 0 | S.K. ELECTRICALS | 23.73 | 0 | 0 | 0
1843 | PURBA BARDHAMAN | Burdwan Division | JABAGRAM PIPED WATER SUPPLY SCHEME , SM/14980 | New | Material Requisition To Resource Division | 1646/BWD | 06/04/2023 | 0 | Resource Division | 1.65 | 0 | 0 | 0
1844 | PURBA BARDHAMAN | Burdwan Division | JABAGRAM PIPED WATER SUPPLY SCHEME , SM/14980 | New | Material Requisition To Resource Division | 1257/BWD | 17/03/2023 | 0 | Resource Division | 13.53 | 0 | 0 | 0
1845 | PURBA BARDHAMAN | Burdwan Division | JABAGRAM PIPED WATER SUPPLY SCHEME , SM/14980 | New | Material Requisition To Resource Division | 5061/BWD | 23/11/2023 | 0 | Resource Division | 19.78 | 0 | 0 | 0
1846 | PURBA BARDHAMAN | Central Mechanical | JABAGRAM PIPED WATER SUPPLY SCHEME , SM/14980 | New | New Service connection charges for Jabagram W/S Scheme TW-I | BP-2023-24-8 | 12/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.81 | 0 | 0 | 0
1847 | PURBA BARDHAMAN | Burdwan Division | JABAGRAM PIPED WATER SUPPLY SCHEME , SM/14980 | New | Continuation order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. (Sl No-1) | 1016/KTS | 20/09/2023 | 23 | M/S MUNMUN DEY | 0.3 | 0.09 | 100 | 0
1848 | PURBA BARDHAMAN | Central Mechanical | JABAGRAM PIPED WATER SUPPLY SCHEME , SM/14980 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
1849 | PURBA BARDHAMAN | Central Mechanical | JABAGRAM PIPED WATER SUPPLY SCHEME , SM/14980 | New | NEW SERVICE CONNECTION FOR JABAGRAM PWSS TW-2. | BP-2024-25-1 | 04/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.75 | 0 | 0 | 0
1850 | PURBA BARDHAMAN | Burdwan Division | JABAGRAM PIPED WATER SUPPLY SCHEME , SM/14980 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOHAGRAM, KHERUA & JABAGRAM Piped Water Supply Scheme under Mangalkote Block, District:- Purba Bardhaman [NEW SCHEME] | 582/BWD | 17/02/2023 | 1049 | PUSPA ENTERPRISE | 1185.88 | 380.48 | 82.09 | 75
1851 | PURBA BARDHAMAN | Burdwan Division | JABAGRAM PIPED WATER SUPPLY SCHEME , SM/14980 | New | Different types of works involve in connection with implementation of Gohgram, Jabagram, Kherua, Lakshmipur & Simulia Piped Water Supply Scheme under Mongolkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. | 936/BWD | 11/03/2025 | 180 | M/S GHOSH CONSTRUCTION | 360.68 | 0 | 0 | 0
1852 | PURBA BARDHAMAN | Central Mechanical | JABAGRAM PIPED WATER SUPPLY SCHEME , SM/14980 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JABAGRAM Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2472/CMD | 30/05/2023 | 570 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 28.96 | 23.24 | 97.72 | 88
1853 | PURBA BARDHAMAN | Burdwan Division | KASHIARA PIPED WATER SUPPLY SCHEME , SM/14075 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.83 | 0 | 0 | 0
1854 | PURBA BARDHAMAN | Burdwan Division | KASHIARA PIPED WATER SUPPLY SCHEME , SM/14075 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.97 | 0 | 0 | 0
1855 | PURBA BARDHAMAN | Burdwan Division | KASHIARA PIPED WATER SUPPLY SCHEME , SM/14075 | New | Material Requisition To Resource Division | 5265/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
1856 | PURBA BARDHAMAN | Central Mechanical | KASHIARA PIPED WATER SUPPLY SCHEME , SM/14075 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kashiara Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3999/CMD | 29/08/2023 | 30 | MENAKA ENTERPRISE. | 28.98 | 22.53 | 77.73 | 90
1857 | PURBA BARDHAMAN | Central Mechanical | KASHIARA PIPED WATER SUPPLY SCHEME , SM/14075 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
1858 | PURBA BARDHAMAN | Central Mechanical | KASHIARA PIPED WATER SUPPLY SCHEME , SM/14075 | New | New service connection for Kashiara W/S Scheme. | BP-2023-24-384 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.91 | 0 | 0 | 0
1859 | PURBA BARDHAMAN | Central Mechanical | KASHIARA PIPED WATER SUPPLY SCHEME , SM/14075 | New | New service connection charges for Kashiara PWSS TW-2 | BP-2023-24-398 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.22 | 0 | 0 | 0
1860 | PURBA BARDHAMAN | Burdwan Division | KASHIARA PIPED WATER SUPPLY SCHEME , SM/14075 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch room, boundary walls with gates, land development, surface drains and internal pathways at different TW site for KASHIARA Piped Water Supply Scheme under BURDWAN I Block, District:- Purba-Bardhaman [NEW SCHEME] | 256/BWD | 09/08/2023 | 836 | PUSPA ENTERPRISE | 597.52 | 240.68 | 40.28 | 70
1861 | PURBA BARDHAMAN | Central Mechanical | JAGADABAD PIPED WATER SUPPLY SCHEME , SM/13945 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Jagadbad Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3997/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 28.93 | 0 | 0 | 0
1862 | PURBA BARDHAMAN | Burdwan Division | JAGADABAD PIPED WATER SUPPLY SCHEME , SM/13945 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 8.29 | 0 | 0 | 0
1863 | PURBA BARDHAMAN | Burdwan Division | JAGADABAD PIPED WATER SUPPLY SCHEME , SM/13945 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.21 | 0 | 0 | 0
1864 | PURBA BARDHAMAN | Burdwan Division | JAGADABAD PIPED WATER SUPPLY SCHEME , SM/13945 | New | Material Requisition To Resource Division | 5274/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
1865 | PURBA BARDHAMAN | Central Mechanical | JAGADABAD PIPED WATER SUPPLY SCHEME , SM/13945 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
1866 | PURBA BARDHAMAN | Central Mechanical | JAGADABAD PIPED WATER SUPPLY SCHEME , SM/13945 | New | NEW SERVICE CONNECTION FOR JAGDABAD PWSS PH-1. | BP-2023-24-609 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.65 | 0 | 0 | 0
1867 | PURBA BARDHAMAN | Central Mechanical | JAGADABAD PIPED WATER SUPPLY SCHEME , SM/13945 | New | NEW SERVICE CONNECTION FOR JAGDABAD PWSS PH-2. | BP-2023-24-608 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.21 | 0 | 0 | 0
1868 | PURBA BARDHAMAN | Burdwan Division | JAGADABAD PIPED WATER SUPPLY SCHEME , SM/13945 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARASAT, JAGADABAD & KHAIDYA Piped Water Supply Scheme under BURDWAN-I Block, District:- Purba Bardhaman [NEW SCHEME] | 3460/BWD | 08/08/2023 | 783 | CONCORD EMC ENCLAVE LLP | 1526.24 | 229 | 45.53 | 5
1869 | PURBA BARDHAMAN | Burdwan Division | KHANDARI PIPED WATER SUPPLY SCHEME , SM/13396 | New | Material Requisition To Resource Division | 1267/BWD | 17/03/2023 | 0 | Resource Division | 13.39 | 0 | 0 | 0
1870 | PURBA BARDHAMAN | Burdwan Division | KHANDARI PIPED WATER SUPPLY SCHEME , SM/13396 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 65.98 | 0 | 0 | 0
1871 | PURBA BARDHAMAN | Burdwan Division | KHANDARI PIPED WATER SUPPLY SCHEME , SM/13396 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.58 | 0 | 0 | 0
1872 | PURBA BARDHAMAN | Burdwan Division | KHANDARI PIPED WATER SUPPLY SCHEME , SM/13396 | New | Material Requisition To Resource Division | 5104/BWD | 23/11/2023 | 0 | Resource Division | 21.42 | 0 | 0 | 0
1873 | PURBA BARDHAMAN | Central Mechanical | KHANDARI PIPED WATER SUPPLY SCHEME , SM/13396 | New | New service connection charges for Khandari PWSS TW 2 | BP-2023-24-98 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.97 | 0 | 0 | 0
1874 | PURBA BARDHAMAN | Central Mechanical | KHANDARI PIPED WATER SUPPLY SCHEME , SM/13396 | New | New service connection charges for Khandari PWSS TW-1 | BP-2023-24-49 | 13/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.71 | 0 | 0 | 0
1875 | PURBA BARDHAMAN | Central Mechanical | KHANDARI PIPED WATER SUPPLY SCHEME , SM/13396 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khandari Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2508/CMD | 02/06/2023 | 30 | CHOUDHURY ENTERPRISE | 27.79 | 22.62 | 100 | 98
1876 | PURBA BARDHAMAN | Durgapur W/S Division | KHANDARI PIPED WATER SUPPLY SCHEME , SM/13396 | New | Material Requisition To Resource Division | 1724/J/DWSD | 10/12/2024 | 0 | Resource Division | 11.03 | 0 | 0 | 0
1877 | PURBA BARDHAMAN | Durgapur W/S Division | KHANDARI PIPED WATER SUPPLY SCHEME , SM/13396 | New | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 0 | 1
1878 | PURBA BARDHAMAN | Burdwan Division | KHANDARI PIPED WATER SUPPLY SCHEME , SM/13396 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KHANDARI & CHHORA Piped Water Supply Scheme under Ausgram II Block, District:- Purba Bardhaman [NEW SCHEME] | 1005/BWD | 06/03/2023 | 696 | M/S NATIONAL CONSTRUCTION | 1331.54 | 642.9 | 95.21 | 100
1879 | PURBA BARDHAMAN | Burdwan Division | PALITPUR PIPED WATER SUPPLY SCHEME , SM/14076 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 5.23 | 0 | 0 | 0
1880 | PURBA BARDHAMAN | Burdwan Division | PALITPUR PIPED WATER SUPPLY SCHEME , SM/14076 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.42 | 0 | 0 | 0
1881 | PURBA BARDHAMAN | Burdwan Division | PALITPUR PIPED WATER SUPPLY SCHEME , SM/14076 | New | Material Requisition To Resource Division | 5275/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
1882 | PURBA BARDHAMAN | Central Mechanical | PALITPUR PIPED WATER SUPPLY SCHEME , SM/14076 | New | New service connection charges for Palitpur PWSS TW-1 | BP-2023-24-228 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.84 | 0 | 0 | 0
1883 | PURBA BARDHAMAN | Central Mechanical | PALITPUR PIPED WATER SUPPLY SCHEME , SM/14076 | New | New service connection charges for Palitpur PWSS TW-2 | BP-2023-24-229 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.84 | 0 | 0 | 0
1884 | PURBA BARDHAMAN | Central Mechanical | PALITPUR PIPED WATER SUPPLY SCHEME , SM/14076 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
1885 | PURBA BARDHAMAN | Burdwan Division | PALITPUR PIPED WATER SUPPLY SCHEME , SM/14076 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KALIGRAM & PALITPUR Piped Water Supply Scheme under Burdwan I Block, District:- Purba Bardhaman [NEW SCHEME] | 3532/BWD | 10/08/2023 | 722 | SUPRITI ENTERPRISE | 704.5 | 17.68 | 6 | 50
1886 | PURBA BARDHAMAN | Central Mechanical | PALITPUR PIPED WATER SUPPLY SCHEME , SM/14076 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Palitpur Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4004/CMD | 29/08/2023 | 703 | SUBRATA BHADRA | 28.96 | 0 | 0 | 90
1887 | PURBA BARDHAMAN | Burdwan Division | AMRA PIPED WATER SUPPLY SCHEME , SM/13454 | New | Material Requisition To Resource Division | 5049/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
1888 | PURBA BARDHAMAN | Burdwan Division | AMRA PIPED WATER SUPPLY SCHEME , SM/13454 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 15.41 | 0 | 0 | 0
1889 | PURBA BARDHAMAN | Central Mechanical | AMRA PIPED WATER SUPPLY SCHEME , SM/13454 | New | New service connection charges for Amra PWSS TW-1 | BP-2023-24-172 | 29/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.84 | 0 | 0 | 0
1890 | PURBA BARDHAMAN | Central Mechanical | AMRA PIPED WATER SUPPLY SCHEME , SM/13454 | New | New service connection charges for Amra PWSS TW-2 | BP-2023-24-173 | 29/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.42 | 0 | 0 | 0
1891 | PURBA BARDHAMAN | Central Mechanical | AMRA PIPED WATER SUPPLY SCHEME , SM/13454 | New | Supply & fitting fixing of FASD motor starter (for urgent FHTC) for Tube well no.-I & II at Amra water supply scheme, (Block- Khandaghosh) under CMD, PHE Dte., Dist.- Purba-Bardhaman | 743/CMSD | 13/05/2024 | 10 | M/S. SWAPAN BANERJEE | 0.6 | 0.6 | 100 | 100
1892 | PURBA BARDHAMAN | Burdwan Division | AMRA PIPED WATER SUPPLY SCHEME , SM/13454 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA, BALABATI, UKHRID & RUPSA Piped Water Supply Scheme under KHANDAGHOSH Block, District:- Purba Bardhaman [NEW SCHEME] | 1726/BWD | 13/04/2023 | 902 | S.P. CONSTRUCTION | 1710.27 | 305.15 | 66.2 | 45
1893 | PURBA BARDHAMAN | Burdwan Division | AMRA PIPED WATER SUPPLY SCHEME , SM/13454 | New | Surveying, planning, design, drawing and construction of pipe carrying structural bridge for carrying 200 mm. dia. D.I. Pipe line at AMRA Piped W/S. Scheme, Khandaghosh Dev. Block under Durgapur (Burdwan North) Sub-Division, PHE. Dte. within Burdwan Division, PHE. Dte. | 4085/BWD | 22/11/2024 | 361 | S.P. CONSTRUCTION | 149.75 | 0 | 0 | 25
1894 | PURBA BARDHAMAN | Central Mechanical | AMRA PIPED WATER SUPPLY SCHEME , SM/13454 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
1895 | PURBA BARDHAMAN | Burdwan Division | AMRA PIPED WATER SUPPLY SCHEME , SM/13454 | New | Balance work for providing Functional Household Tap Connection (FHTC) within the command area BALABATI, AMRA & RUPSA W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | 609/BWD | 11/02/2025 | 120 | M/S S.S. ENTERPRISE | 194.58 | 0 | 0 | 0
1896 | PURBA BARDHAMAN | Central Mechanical | AMRA PIPED WATER SUPPLY SCHEME , SM/13454 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Amra Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4010/CMD | 29/08/2023 | 30 | M/S. SWAPAN BANERJEE | 28.98 | 2.34 | 10.65 | 100
1897 | PURBA BARDHAMAN | Burdwan Division | PURULIA PIPED WATER SUPPLY SCHEME , SM/15239 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 15.02 | 0 | 0 | 0
1898 | PURBA BARDHAMAN | Burdwan Division | PURULIA PIPED WATER SUPPLY SCHEME , SM/15239 | New | Material Requisition To Resource Division | 4014/BWD | 08/09/2023 | 0 | Resource Division | 8.73 | 0 | 0 | 0
1899 | PURBA BARDHAMAN | Burdwan Division | PURULIA PIPED WATER SUPPLY SCHEME , SM/15239 | New | Material Requisition To Resource Division | 4891/BWD | 10/11/2023 | 0 | Resource Division | 10 | 0 | 0 | 0
1900 | PURBA BARDHAMAN | Central Mechanical | PURULIA PIPED WATER SUPPLY SCHEME , SM/15239 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
1901 | PURBA BARDHAMAN | Central Mechanical | PURULIA PIPED WATER SUPPLY SCHEME , SM/15239 | New | New service connection at Purulia PWSS TW No.1 | BP-2023-24-492 | 01/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.09 | 0 | 0 | 0
1902 | PURBA BARDHAMAN | Central Mechanical | PURULIA PIPED WATER SUPPLY SCHEME , SM/15239 | New | NEW SERVICE CONNECTION FOR PURULIA PWSS TW 2. | BP-2023-24-650 | 20/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.36 | 0 | 0 | 0
1903 | PURBA BARDHAMAN | Burdwan Division | PURULIA PIPED WATER SUPPLY SCHEME , SM/15239 | New | Balance work of OHR, construction Concrete Road, Drum Sheet Pilling, Functional Household Tap Connection, construction of HUME Pipe culvert, land development, Road restoration etc. under Billeswar PWSS, Purulia PWSS & Gurpara PWSS under KATWA -II Block under Katwa Sub-Divn. under Burdwan Division, PHED. District:- Purba-Bardhaman | 2834/BWD | 19/07/2024 | 835 | PASCON | 190.06 | 0 | 0 | 90
1904 | PURBA BARDHAMAN | Central Mechanical | PURULIA PIPED WATER SUPPLY SCHEME , SM/15239 | New | Supply and delivery of 7.5 HP pump motor set at T.W. No - 2 of PURULIA (Block- Ketugram-II) water supply scheme under CMD, PHE Dte. | 821/DIC/BMSD(D) | 05/12/2024 | 33 | BARMAN ROY TRADERS | 0.67 | 0 | 0 | 100
1905 | PURBA BARDHAMAN | Central Mechanical | PURULIA PIPED WATER SUPPLY SCHEME , SM/15239 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at PURULIA Water Supply Scheme [Block - KETUGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4100/CMD | 29/08/2023 | 665 | BARMAN ROY TRADERS | 21.01 | 7.97 | 29.57 | 43
1906 | PURBA BARDHAMAN | Central Mechanical | PURULIA PIPED WATER SUPPLY SCHEME , SM/15239 | New | Increasing of tube well casing and other works at PURULIA PWSS under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 151/DIC/BMSD(D) | 04/03/2025 | 7 | BARMAN ROY TRADERS | 0.29 | 0 | 0 | 100
1907 | PURBA BARDHAMAN | Burdwan Division | BILLESWAR PIPED WATER SUPPLY SCHEME , SM/15241 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 0.83 | 0 | 0 | 0
1908 | PURBA BARDHAMAN | Burdwan Division | BILLESWAR PIPED WATER SUPPLY SCHEME , SM/15241 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.05 | 0 | 0 | 0
1909 | PURBA BARDHAMAN | Burdwan Division | BILLESWAR PIPED WATER SUPPLY SCHEME , SM/15241 | New | Material Requisition To Resource Division | 4870/BWD | 10/11/2023 | 0 | Resource Division | 29.6 | 0 | 0 | 0
1910 | PURBA BARDHAMAN | Central Mechanical | BILLESWAR PIPED WATER SUPPLY SCHEME , SM/15241 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BILLESWAR Water Supply Scheme [ Block- KETUGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4073/CMD | 29/08/2023 | 30 | KAMAKHYA ENTERPRISE | 26.97 | 21.21 | 78.64 | 88
1911 | PURBA BARDHAMAN | Central Mechanical | BILLESWAR PIPED WATER SUPPLY SCHEME , SM/15241 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
1912 | PURBA BARDHAMAN | Central Mechanical | BILLESWAR PIPED WATER SUPPLY SCHEME , SM/15241 | New | New service connection at Billeswar PWSS TW No.1 | BP-2023-24-493 | 01/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.28 | 0 | 0 | 0
1913 | PURBA BARDHAMAN | Central Mechanical | BILLESWAR PIPED WATER SUPPLY SCHEME , SM/15241 | New | New Service connection for Billwswar PWSS TW-2 | BP-2023-24-466 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.04 | 0 | 0 | 0
1914 | PURBA BARDHAMAN | Burdwan Division | BILLESWAR PIPED WATER SUPPLY SCHEME , SM/15241 | New | Balance work of OHR, construction Concrete Road, Drum Sheet Pilling, Functional Household Tap Connection, construction of HUME Pipe culvert, land development, Road restoration etc. under Billeswar PWSS, Purulia PWSS & Gurpara PWSS under KATWA -II Block under Katwa Sub-Divn. under Burdwan Division, PHED. District:- Purba-Bardhaman | 2834/BWD | 19/07/2024 | 835 | PASCON | 190.06 | 0 | 0 | 90
1915 | PURBA BARDHAMAN | Central Mechanical | UDGARA PIPED WATER SUPPLY SCHEME , SM/14961 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Udgara Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4023/CMD | 29/08/2023 | 30 | CHATTERJEE ENTERPRISE | 28.95 | 0 | 0 | 0
1916 | PURBA BARDHAMAN | Burdwan Division | UDGARA PIPED WATER SUPPLY SCHEME , SM/14961 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 9.24 | 0 | 0 | 0
1917 | PURBA BARDHAMAN | Burdwan Division | UDGARA PIPED WATER SUPPLY SCHEME , SM/14961 | New | Material Requisition To Resource Division | 4287/BWD | 29/09/2023 | 0 | Resource Division | 4.57 | 0 | 0 | 0
1918 | PURBA BARDHAMAN | Burdwan Division | UDGARA PIPED WATER SUPPLY SCHEME , SM/14961 | New | Material Requisition To Resource Division | 5069/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
1919 | PURBA BARDHAMAN | Burdwan Division | UDGARA PIPED WATER SUPPLY SCHEME , SM/14961 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BHAGABATIPUR, MACHKHARA & UDGARA Piped Water Supply Scheme under Raina ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] | 4386/BWD | 05/10/2023 | 365 | SK ALIM | 1378.97 | 77.61 | 21.75 | 55
1920 | PURBA BARDHAMAN | Central Mechanical | UDGARA PIPED WATER SUPPLY SCHEME , SM/14961 | New | New Service connection for Udgra W/S Scheme PH No.-I | BP-2023-24-310 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.13 | 0 | 0 | 0
1921 | PURBA BARDHAMAN | Central Mechanical | UDGARA PIPED WATER SUPPLY SCHEME , SM/14961 | New | New Service connection for Udgram W/S Scheme PH No.-II | BP-2023-24-311 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.73 | 0 | 0 | 0
1922 | PURBA BARDHAMAN | Central Mechanical | UDGARA PIPED WATER SUPPLY SCHEME , SM/14961 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
1923 | PURBA BARDHAMAN | Burdwan Division | UDGARA PIPED WATER SUPPLY SCHEME , SM/14961 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2024 to 31-01-2025) | 2438/BSD | 29/10/2024 | 66 | PARVIN BEGAM | 0.85 | 0.28 | 99.82 | 100
1924 | PURBA BARDHAMAN | Burdwan Division | UDGARA PIPED WATER SUPPLY SCHEME , SM/14961 | New | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related (schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-05-2025 to 31-07-2025) | 960/BSD | 30/04/2025 | 66 | PARVIN BEGAM | 0.85 | 0 | 0 | 100
1925 | PURBA BARDHAMAN | Burdwan Division | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME , SM/14962 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 32.63 | 0 | 0 | 0
1926 | PURBA BARDHAMAN | Burdwan Division | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME , SM/14962 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 4.84 | 0 | 0 | 0
1927 | PURBA BARDHAMAN | Burdwan Division | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME , SM/14962 | New | Material Requisition To Resource Division | 4907/BWD | 10/11/2023 | 0 | Resource Division | 33.07 | 0 | 0 | 0
1928 | PURBA BARDHAMAN | Central Mechanical | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME , SM/14962 | New | New service connection charges for Bazar Mahammadpur PWSS TW-1 | BP-2023-24-109 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.85 | 0 | 0 | 0
1929 | PURBA BARDHAMAN | Central Mechanical | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME , SM/14962 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BAZAR MAHAMMADPUR Water Supply Scheme [ Block- BHATAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3171/CMD | 26/07/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 27.78 | 5.62 | 20.23 | 95
1930 | PURBA BARDHAMAN | Central Mechanical | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME , SM/14962 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
1931 | PURBA BARDHAMAN | Central Mechanical | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME , SM/14962 | New | New service connection charges for Bazar Mohammadpur PWSS TW-2 | BP-2023-24-250 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.98 | 0 | 0 | 0
1932 | PURBA BARDHAMAN | Central Mechanical | BAZAR MAHAMMADPUR PIPED WATER SUPPLY SCHEME , SM/14962 | New | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3105/CMD | 11/12/2024 | 60 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0 | 0
1933 | PURBA BARDHAMAN | Burdwan Division | BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14925 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 15.82 | 0 | 0 | 0
1934 | PURBA BARDHAMAN | Burdwan Division | BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14925 | New | Material Requisition To Resource Division | 3866/BWD | 01/09/2023 | 0 | Resource Division | 0.23 | 0 | 0 | 0
1935 | PURBA BARDHAMAN | Central Mechanical | BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14925 | New | New service connection charges for Bhandarituri PWSS TW-1 | BP-2023-24-202 | 18/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.82 | 0 | 0 | 0
1936 | PURBA BARDHAMAN | Central Mechanical | BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14925 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at BHANDARITURI Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4096/CMD | 29/08/2023 | 30 | KAMAKHYA ENTERPRISE | 20.75 | 9.49 | 45.73 | 60
1937 | PURBA BARDHAMAN | Burdwan Division | BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14925 | New | BHANDARTIKURI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1280/BWD | 20/03/2023 | 90 | NANDANIK ENGINEERS CO-OPERATIVE SOCIETY LTD. | 65.35 | 60.38 | 100 | 100
1938 | PURBA BARDHAMAN | Burdwan Division | BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14925 | New | Material Requisition To Resource Division | 312/BWD | 24/01/2024 | 0 | Resource Division | 7.05 | 0 | 0 | 0
1939 | PURBA BARDHAMAN | Burdwan Division | BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14925 | New | Different types of works involve in connection with Augmentation of DIRGHAPARA (SM/07804) Water Supply Scheme, MOUDANGA (SM/ 14020) Water supply Scheme & BHANDARTIKURI (SM/14925) Water Supply Scheme under Burdwan Division, PHE Dte. | 2912/BWD | 25/07/2024 | 431 | BANSBERIA CONSTRUCTION CO. | 293.38 | 0 | 0 | 22
1940 | PURBA BARDHAMAN | Central Mechanical | BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14925 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 30
1941 | PURBA BARDHAMAN | Burdwan Division | BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14925 | New | Work order for "Restoration of Concrete Roads & other allied works , at Barishalpara,Habitation-Bhandartikuri,G.P-Jahannagar, in the command area of BHANDARTIKURI PWSS (SM/14925) ,BLOCK-Purbasthali -1 , under Kalna Sub-Division under Burdwan Division, PHE Dte.". | 389/KSD | 10/03/2025 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.96 | 0 | 0 | 100
1942 | PURBA BARDHAMAN | Burdwan Division | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14965 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 4.92 | 0 | 0 | 0
1943 | PURBA BARDHAMAN | Burdwan Division | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14965 | New | Material Requisition To Resource Division | 4020/BWD | 08/09/2023 | 0 | Resource Division | 0.41 | 0 | 0 | 0
1944 | PURBA BARDHAMAN | Burdwan Division | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14965 | New | Material Requisition To Resource Division | 5113/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
1945 | PURBA BARDHAMAN | Central Mechanical | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14965 | New | New Service connection for Bamchandrapur PWSS TW-2. | BP-2023-24-626 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.71 | 0 | 0 | 0
1946 | PURBA BARDHAMAN | Central Mechanical | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14965 | New | New Service connection for Bamchandrapur PWSS TW-1. | BP-2023-24-627 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.75 | 0 | 0 | 0
1947 | PURBA BARDHAMAN | Central Mechanical | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14965 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bamchandrapur Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4044/CMD | 29/08/2023 | 30 | S.K. ENTERPRISE | 30.08 | 0 | 0 | 90
1948 | PURBA BARDHAMAN | Central Mechanical | BAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14965 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 0 | 12
1949 | PURBA BARDHAMAN | Burdwan Division | MACHKHARA PIPED WATER SUPPLY SCHEME , SM/14967 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.92 | 0 | 0 | 0
1950 | PURBA BARDHAMAN | Burdwan Division | MACHKHARA PIPED WATER SUPPLY SCHEME , SM/14967 | New | Material Requisition To Resource Division | 4296/BWD | 29/09/2023 | 0 | Resource Division | 5.11 | 0 | 0 | 0
1951 | PURBA BARDHAMAN | Burdwan Division | MACHKHARA PIPED WATER SUPPLY SCHEME , SM/14967 | New | Material Requisition To Resource Division | 5063/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
1952 | PURBA BARDHAMAN | Burdwan Division | MACHKHARA PIPED WATER SUPPLY SCHEME , SM/14967 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BHAGABATIPUR, MACHKHARA & UDGARA Piped Water Supply Scheme under Raina ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] | 4386/BWD | 05/10/2023 | 365 | SK ALIM | 1378.97 | 267.86 | 52.64 | 55
1953 | PURBA BARDHAMAN | Central Mechanical | MACHKHARA PIPED WATER SUPPLY SCHEME , SM/14967 | New | New service connection for Machkhanda PWSS. | BP-2023-24-399 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.37 | 0 | 0 | 0
1954 | PURBA BARDHAMAN | Central Mechanical | MACHKHARA PIPED WATER SUPPLY SCHEME , SM/14967 | New | New service connection for Mackhara PWSS TW-2. | BP-2023-24-434 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.5 | 0 | 0 | 0
1955 | PURBA BARDHAMAN | Central Mechanical | MACHKHARA PIPED WATER SUPPLY SCHEME , SM/14967 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
1956 | PURBA BARDHAMAN | Central Mechanical | MACHKHARA PIPED WATER SUPPLY SCHEME , SM/14967 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Machkhara Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4020/CMD | 29/08/2023 | 598 | CHOUDHURY ENTERPRISE | 28.98 | 11.6 | 48.01 | 85
1957 | PURBA BARDHAMAN | Burdwan Division | KHARIJA KASHIGRAM PIPED WATER SUPPLY SCHEME , SM/14916 | New | Material Requisition To Resource Division | 1965/BWD | 26/04/2023 | 0 | Resource Division | 2.74 | 0 | 0 | 0
1958 | PURBA BARDHAMAN | Burdwan Division | KHARIJA KASHIGRAM PIPED WATER SUPPLY SCHEME , SM/14916 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 22.26 | 0 | 0 | 0
1959 | PURBA BARDHAMAN | Central Mechanical | KHARIJA KASHIGRAM PIPED WATER SUPPLY SCHEME , SM/14916 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
1960 | PURBA BARDHAMAN | Burdwan Division | KHARIJA KASHIGRAM PIPED WATER SUPPLY SCHEME , SM/14916 | New | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. | 22/KTS | 05/01/2024 | 70 | AJIT SAMANTA | 0.9 | 0.3 | 100 | 100
1961 | PURBA BARDHAMAN | Burdwan Division | KHARIJA KASHIGRAM PIPED WATER SUPPLY SCHEME , SM/14916 | New | Material Requisition To Resource Division | 301/BWD | 24/01/2024 | 0 | Resource Division | 20.47 | 0 | 0 | 0
1962 | PURBA BARDHAMAN | Central Mechanical | KHARIJA KASHIGRAM PIPED WATER SUPPLY SCHEME , SM/14916 | New | New service connection charges for Kharija Kashigram PWSS TW-1 | BP-2023-24-275 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.81 | 0 | 0 | 0
1963 | PURBA BARDHAMAN | Central Mechanical | KHARIJA KASHIGRAM PIPED WATER SUPPLY SCHEME , SM/14916 | New | NEW SERVICE CONNECTION FOR KHARIJA KASHIGRAM PWSS PH-2 | BP-2024-25-91 | 17/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.45 | 0 | 0 | 0
1964 | PURBA BARDHAMAN | Burdwan Division | KHARIJA KASHIGRAM PIPED WATER SUPPLY SCHEME , SM/14916 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEULIA, GOBARDHANPUR, KHARIJA-KASHIGRAM & UNIATATARPUR Piped Water Supply Scheme under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | 3491/BWD | 09/08/2023 | 1058 | POWER TOOLS & ENGINEERING | 1741.05 | 62.69 | 13.61 | 10
1965 | PURBA BARDHAMAN | Central Mechanical | KHARIJA KASHIGRAM PIPED WATER SUPPLY SCHEME , SM/14916 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KHARIJA KASHIGRAM Water Supply Scheme [ Block-MONGOLKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4072/CMD | 29/08/2023 | 640 | SOUNAK ENTERPRISE | 27.79 | 10.81 | 47.65 | 48
1966 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Interconnection of rising main from 2nd Tube Well site and renovation of boundary wall and pump house at 2nd Tube Well Site of Ganganandapur W/S Scheme within Kalna Sub-Division under Burdwan Division , PHE Dte. (Sl No-C) | 88/KSD | 21/01/2022 | 30 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 1.2 | 0.86 | 100 | 1
1967 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Preparation of DPR for augmentation of Ganganandapur W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-E) | 207/KSD | 23/02/2022 | 21 | ROY CHOWDHURY ASSOCIATES | 2.84 | 2.82 | 100 | 1
1968 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
1969 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Sinking of additional 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for GANGANANDAPUR Piped Water Supply Scheme, Block - Purbasthali - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 2424/BWD | 11/05/2022 | 30 | M/S SYCHROTECH INDUSTRY | 9.01 | 8.47 | 94.03 | 0
1970 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Construction of Pump House cum switch room (5.40 mtr x 3.60 mtr) with sanitary arrangement (as per drawing no. PHE/SE/CC/PH/DWG-01/2022-2023) at GANGANANDAPUR Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | 4481/BWD | 11/10/2023 | 60 | LOKNATH ENTERPRISE | 6.31 | 0 | 0 | 0
1971 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Jahannagar, Ganganandapur, Nowapara & Monteswar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, P.H.E. Dte.[Part ¿ A] | 3632/BWD | 22/08/2022 | 20 | RAMASISH ENTERPRISE | 12.8 | 3.2 | 100 | 1
1972 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Material Requisition To Resource Division | 603/BWD | 28/01/2022 | 0 | Resource Division | 24.12 | 0 | 0 | 0
1973 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Material Requisition To Resource Division | 553/BWD | 27/01/2022 | 0 | Resource Division | 18.08 | 0 | 0 | 0
1974 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Material Requisition To Resource Division | 1524/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
1975 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Material Requisition To Resource Division | 952/BWD | 17/02/2022 | 0 | Resource Division | 74.99 | 0 | 0 | 0
1976 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Material Requisition To Resource Division | 4626/BWD | 17/10/2022 | 0 | Resource Division | 18.48 | 0 | 0 | 0
1977 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Quotation from WBSEDCL for new service connection of Ganganandapur w/s scheme. T.W.-3 | 537/JJM | 21/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.6 | 0 | 0 | 0
1978 | PURBA BARDHAMAN | Central Mechanical | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Ganganandapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2562/CMD | 06/06/2023 | 30 | SUDIPTA GHOSH | 10.98 | 10.45 | 95.11 | 95
1979 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Additional works to implement the GANGANANDAPUR Piped Water Supply Scheme under Purbasthali-I Block, Dist :- Purba Bardhaman under Burdwan Division, PHE. Dte. | 754/BWD | 23/02/2023 | 60 | MANASH GHOSH | 76.57 | 76.42 | 100 | 85
1980 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 14 Nos. Piped W/S. Schemes under Purbasthali I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3017/BWD | 05/08/2024 | 75 | HORIZEN | 38 | 16.76 | 100 | 100
1981 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Work Order for " Renovation of Pump house along with laboratory building of Ganganandapur piped water supply scheme in connection with Augmentation of Ganganandapur Piped Water Supply Scheme under Burdwan Division, PHE Dte." | 318/KSD | 07/06/2024 | 30 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 4.31 | 4.24 | 100 | 100
1982 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Work Order for "Supervision and extend support to NABL recognised Water Quality Testing Block level Laboratory under The Assistant Engineer, Kalna Sub- Division, Public Health Engineering Directorate, Government of West Bengal by assigining team of competent resource personnel who will be engeged for complete supervision for retaining NABL recognition and compilation of preparatory up-to-date documentation,Calibration for on-site survelliance by NABL (as per NABL 139) for a period of one month from the date of commencement. (Name of SDL : Ganganandapur Sub District Water Testing Laboratory under Kalna Sub Division)". | 1334/KSD | 28/08/2023 | 30 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 0.51 | 0 | 0 | 1
1983 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Work Order for " Renovation of boundary wall in connection with Augmentation of Ganganandapur Water Supply Scheme (SM/09411) within Kalna Sub-Division under Burdwan Division, PHE Dte. (Length - 170 Mtr). - 2 Nos". | 1778/KSD | 20/11/2024 | 30 | UNIQUE CONSTRUCTION | 4.55 | 0 | 0 | 100
1984 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Renovation of Pump House in connection with Augmentation of Ganganandapur piped Water supply (SM/09411) Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte. (2 Nos Pump House Repairing) | 3748/BWD | 29/10/2024 | 30 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 9.7 | 0.25 | 2.6 | 100
1985 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ganganandapur PWSS for providing FHTC. , SM/09411 | Augmentation | Work order for "Construction of Toilet (1.8 m x 1.8 m) with saitary arrangement along with other allied works at PH No-3 of Ganganandapur pwss (SM/09411) under Kalna sub division under Burdwan Division.". | 303/KSD | 25/02/2025 | 30 | DUTTA CONSTRUCTION & CONSULTANCY | 2.45 | 0 | 0 | 100
1986 | PURBA BARDHAMAN | Burdwan Division | Narottambati Piped Water Supply Scheme , SM/15486 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] | 1759/BSD | 28/07/2023 | 66 | MD HASIN | 0.85 | 0 | 0 | 0
1987 | PURBA BARDHAMAN | Burdwan Division | Narottambati Piped Water Supply Scheme , SM/15486 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.94 | 0 | 0 | 0
1988 | PURBA BARDHAMAN | Burdwan Division | Narottambati Piped Water Supply Scheme , SM/15486 | New | Material Requisition To Resource Division | 5081/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
1989 | PURBA BARDHAMAN | Burdwan Division | Narottambati Piped Water Supply Scheme , SM/15486 | New | Material Requisition To Resource Division | 3837/BWD | 01/09/2023 | 0 | Resource Division | 6.91 | 0 | 0 | 0
1990 | PURBA BARDHAMAN | Central Mechanical | Narottambati Piped Water Supply Scheme , SM/15486 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
1991 | PURBA BARDHAMAN | Central Mechanical | Narottambati Piped Water Supply Scheme , SM/15486 | New | New service connection for Narottambati PWSS. | BP-2023-24-496 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.09 | 0 | 0 | 0
1992 | PURBA BARDHAMAN | Central Mechanical | Narottambati Piped Water Supply Scheme , SM/15486 | New | NEW SERVICE CONNECTION FOR NAROTTAMBATI PWSS TW 2. | BP-2023-24-664 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.31 | 0 | 0 | 0
1993 | PURBA BARDHAMAN | Burdwan Division | Narottambati Piped Water Supply Scheme , SM/15486 | New | NAROTTAMBATI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3501/BWD | 10/08/2023 | 875 | S.S.S. ENTERPRISES | 585.33 | 149.09 | 25.47 | 75
1994 | PURBA BARDHAMAN | Burdwan Division | Narottambati Piped Water Supply Scheme , SM/15486 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-12-2024 to 28-02-2025 | 2636/BSD | 29/11/2024 | 90 | SK. ASFIA | 1.2 | 0.36 | 90.86 | 60
1995 | PURBA BARDHAMAN | Central Mechanical | Narottambati Piped Water Supply Scheme , SM/15486 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Narottombati Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4173/CMD | 29/08/2023 | 30 | J.S. CONSTRUCTION. | 29.71 | 0 | 0 | 90
1996 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME , SM/16487 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augmentation of Mongolkot Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2631/CMD | 13/06/2023 | 30 | S.K. ELECTRICALS | 22.05 | 0 | 0 | 0
1997 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME , SM/16487 | Augmentation | Extension and replacement of pipe line from the existing Distribution System within scheme jurisdiction at Mongalkote village under Mongalkote PWSS under Mongalkote Block within Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-01] | 437/KTS | 27/06/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.84 | 4.81 | 100 | 0
1998 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME , SM/16487 | Augmentation | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of Mongalkote & Natunhat and its adjoining mouzas Piped Water Supply Scheme, Block - Mongalkote, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 4658/BWD | 18/10/2022 | 30 | ANIRUDDHA FARUQUE | 13.24 | 8.79 | 100 | 1
1999 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME , SM/16487 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme MONGALKOTE PWSS (Sl No-06) | 399/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 2.93 | 2.93 | 100 | 100
2000 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF MANGALKOT PIPED WATER SUPPLY SCHEME , SM/16487 | Augmentation | Yard lighting arrangement & allied works at Mangalkote water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2790/CMD | 01/10/2024 | 60 | JAGANNATH ENTERPRISE | 13.47 | 0 | 0 | 0
2001 | PURBA BARDHAMAN | Burdwan Division | MALGRAM PIPED WATER SUPPLY SCHEME , SM/15150 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.83 | 0 | 0 | 0
2002 | PURBA BARDHAMAN | Burdwan Division | MALGRAM PIPED WATER SUPPLY SCHEME , SM/15150 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.73 | 0 | 0 | 0
2003 | PURBA BARDHAMAN | Burdwan Division | MALGRAM PIPED WATER SUPPLY SCHEME , SM/15150 | New | Material Requisition To Resource Division | 5259/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0 | 0
2004 | PURBA BARDHAMAN | Central Mechanical | MALGRAM PIPED WATER SUPPLY SCHEME , SM/15150 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
2005 | PURBA BARDHAMAN | Burdwan Division | MALGRAM PIPED WATER SUPPLY SCHEME , SM/15150 | New | Material Requisition To Resource Division | 4108/BWD | 25/11/2024 | 0 | Resource Division | 4.93 | 0 | 0 | 0
2006 | PURBA BARDHAMAN | Central Mechanical | MALGRAM PIPED WATER SUPPLY SCHEME , SM/15150 | New | Quotation for new service connection at Malgram PWSS PH-2. | BP-2024-25-225 | 26/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.27 | 0 | 0 | 0
2007 | PURBA BARDHAMAN | Central Mechanical | MALGRAM PIPED WATER SUPPLY SCHEME , SM/15150 | New | Quotation for new service connection at Malgram PWSS PH-I. | BP-2024-25-168 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.14 | 0 | 0 | 0
2008 | PURBA BARDHAMAN | Burdwan Division | MALGRAM PIPED WATER SUPPLY SCHEME , SM/15150 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MALGRAM, MURGRAM, MORGRAM & KHANJI Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3387/BWD | 03/08/2023 | 882 | PUSPA ENTERPRISE | 1333.98 | 201.38 | 61.66 | 40
2009 | PURBA BARDHAMAN | Central Mechanical | MALGRAM PIPED WATER SUPPLY SCHEME , SM/15150 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MALGRAM Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4120/CMD | 29/08/2023 | 550 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 27.75 | 6.1 | 21.97 | 82
2010 | PURBA BARDHAMAN | Burdwan Division | MALGRAM PIPED WATER SUPPLY SCHEME , SM/15150 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Murgram, Moregram, Malgram, Khanji, PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2739/BWD | 12/07/2024 | 173 | PUSPA ENTERPRISE | 185.75 | 21.72 | 46.76 | 72
2011 | PURBA BARDHAMAN | Central Drilling | KHATUNDI PIPED WATER SUPPLY SCHEME , SM/15154 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Khatundi W/S Scheme (T/W-I & II) , Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | 1055/CDD | 16/08/2023 | 30 | OSMAN SEKH | 16.61 | 0 | 0 | 0
2012 | PURBA BARDHAMAN | Burdwan Division | KHATUNDI PIPED WATER SUPPLY SCHEME , SM/15154 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.05 | 0 | 0 | 0
2013 | PURBA BARDHAMAN | Burdwan Division | KHATUNDI PIPED WATER SUPPLY SCHEME , SM/15154 | New | Material Requisition To Resource Division | 3980/BWD | 08/09/2023 | 0 | Resource Division | 0.66 | 0 | 0 | 0
2014 | PURBA BARDHAMAN | Burdwan Division | KHATUNDI PIPED WATER SUPPLY SCHEME , SM/15154 | New | Material Requisition To Resource Division | 5251/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0 | 0
2015 | PURBA BARDHAMAN | Central Mechanical | KHATUNDI PIPED WATER SUPPLY SCHEME , SM/15154 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
2016 | PURBA BARDHAMAN | Central Mechanical | KHATUNDI PIPED WATER SUPPLY SCHEME , SM/15154 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at KHATUNDI Water Supply Scheme [Block - KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4121/CMD | 29/08/2023 | 30 | A.K SIKDAR | 20.81 | 19.62 | 100 | 91
2017 | PURBA BARDHAMAN | Central Mechanical | KHATUNDI PIPED WATER SUPPLY SCHEME , SM/15154 | New | New service connection charges for Khatundi PWSS TW-1 | BP-2023-24-252 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.23 | 0 | 0 | 0
2018 | PURBA BARDHAMAN | Central Mechanical | KHATUNDI PIPED WATER SUPPLY SCHEME , SM/15154 | New | New Service connection for Khatundi PWSS TW-2 | BP-2023-24-463 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.33 | 0 | 0 | 0
2019 | PURBA BARDHAMAN | Burdwan Division | KHATUNDI PIPED WATER SUPPLY SCHEME , SM/15154 | New | KHATUNDI Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 150 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ketugram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3258/BWD | 27/07/2023 | 767 | SUJAN KUMAR MISTRY | 260.06 | 198.62 | 76.38 | 60
2020 | PURBA BARDHAMAN | Burdwan Division | KHATUNDI PIPED WATER SUPPLY SCHEME , SM/15154 | New | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2741/BWD | 12/07/2024 | 538 | M/S M.M. ENTERPRISE | 205.15 | 19.03 | 39.97 | 65
2021 | PURBA BARDHAMAN | Burdwan Division | Chaudanga Piped Water Supply Scheme , SM/15489 | New | Material Requisition To Resource Division | 3863/BWD | 01/09/2023 | 0 | Resource Division | 3.95 | 0 | 0 | 0
2022 | PURBA BARDHAMAN | Burdwan Division | Chaudanga Piped Water Supply Scheme , SM/15489 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.3 | 0 | 0 | 0
2023 | PURBA BARDHAMAN | Burdwan Division | Chaudanga Piped Water Supply Scheme , SM/15489 | New | Material Requisition To Resource Division | 5082/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
2024 | PURBA BARDHAMAN | Burdwan Division | Chaudanga Piped Water Supply Scheme , SM/15489 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-09-2024 to 30-11-2024 | 1957/BSD | 30/08/2024 | 91 | SK. ASFIA | 1.2 | 0.4 | 99.35 | 60
2025 | PURBA BARDHAMAN | Central Mechanical | Chaudanga Piped Water Supply Scheme , SM/15489 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
2026 | PURBA BARDHAMAN | Central Mechanical | Chaudanga Piped Water Supply Scheme , SM/15489 | New | New electric connection for Chaudanga PWSS, PH-1. | BP-2023-24-347 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.67 | 0 | 0 | 0
2027 | PURBA BARDHAMAN | Central Mechanical | Chaudanga Piped Water Supply Scheme , SM/15489 | New | New electric connection for Chuadanga PWSS, PH-2. | BP-2023-24-348 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.13 | 0 | 0 | 0
2028 | PURBA BARDHAMAN | Burdwan Division | Chaudanga Piped Water Supply Scheme , SM/15489 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARABAINAN & CHAUDANGA Piped Water Supply Scheme under Raina ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3257/BWD | 27/07/2023 | 989 | SK ALIM | 1144.16 | 288.08 | 47.89 | 90
2029 | PURBA BARDHAMAN | Central Mechanical | Chaudanga Piped Water Supply Scheme , SM/15489 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHAUDANGA Water Supply Scheme [ Block-RAINA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4090/CMD | 29/08/2023 | 610 | MS DAS ELECTRIC CO | 28.98 | 15.76 | 55.44 | 50
2030 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION RAYAN PART IV (DURGADANGA) PIPED WATER SUPPLY SCHEME , SM/15556 | Augmentation | Route Survey & Preparation of DPR for RAYAN PART-(IV) DURGA DANGA W/S Scheme under Burdwan-I Block under Burdwan Sub- Division under Burdwan Division PHE Dte | 2587/BSD | 26/11/2024 | 45 | APEX ENGINEERING | 2.43 | 0 | 0 | 0
2031 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION RAYAN PART IV (DURGADANGA) PIPED WATER SUPPLY SCHEME , SM/15556 | Augmentation | Material Requisition To Resource Division | 4102/BWD | 25/11/2024 | 0 | Resource Division | 10.19 | 0 | 0 | 0
2032 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION RAYAN PART IV (DURGADANGA) PIPED WATER SUPPLY SCHEME , SM/15556 | Augmentation | Quotation for new service connection of Rayan (Aug) Part-4 (Durgadanga) PWSS TW 1 | BP-2024-25-236 | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.91 | 0 | 0 | 0
2033 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION RAYAN PART IV (DURGADANGA) PIPED WATER SUPPLY SCHEME , SM/15556 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Rayan. Part -4 Durgadanga Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2597/CMD | 07/06/2023 | 693 | M/S, S.S. ENTERPRISE. | 24.11 | 9.01 | 37.37 | 50
2034 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION RAYAN PART IV (DURGADANGA) PIPED WATER SUPPLY SCHEME , SM/15556 | Augmentation | Augmentation RAYAN (Part-IV) (Durgadanga) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of switch rooms & boundary walls with gates at different TW site under Burdwan - I Block, District:- Purba-Bardhaman. | 245/BWD | 15/01/2024 | 442 | DHIRENDRANATH SOM | 93.34 | 34.69 | 45.87 | 100
2035 | PURBA BARDHAMAN | Central Drilling | MORGRAM PIPED WATER SUPPLY SCHEME , SM/15163 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Morgram W/S Scheme (T/W-I & II) , Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | 1346/CDD | 13/09/2023 | 30 | S B S ENTERPRISE | 16.67 | 0 | 0 | 0
2036 | PURBA BARDHAMAN | Burdwan Division | MORGRAM PIPED WATER SUPPLY SCHEME , SM/15163 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 3.97 | 0 | 0 | 0
2037 | PURBA BARDHAMAN | Burdwan Division | MORGRAM PIPED WATER SUPPLY SCHEME , SM/15163 | New | Material Requisition To Resource Division | 5257/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0 | 0
2038 | PURBA BARDHAMAN | Burdwan Division | MORGRAM PIPED WATER SUPPLY SCHEME , SM/15163 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.45 | 0 | 0 | 0
2039 | PURBA BARDHAMAN | Central Mechanical | MORGRAM PIPED WATER SUPPLY SCHEME , SM/15163 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MORGRAM Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4125/CMD | 29/08/2023 | 30 | JAGANNATH ENTERPRISE | 27.79 | 21.65 | 77.9 | 88
2040 | PURBA BARDHAMAN | Central Mechanical | MORGRAM PIPED WATER SUPPLY SCHEME , SM/15163 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
2041 | PURBA BARDHAMAN | Central Mechanical | MORGRAM PIPED WATER SUPPLY SCHEME , SM/15163 | New | Quotation for new service connection at Morgram W/S Scheme PH-II. | BP-2023-24-316 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.7 | 0 | 0 | 0
2042 | PURBA BARDHAMAN | Central Mechanical | MORGRAM PIPED WATER SUPPLY SCHEME , SM/15163 | New | Quotation for new service connection at Morgram W/S Scheme PH-I. | BP-2023-24-315 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.76 | 0 | 0 | 0
2043 | PURBA BARDHAMAN | Burdwan Division | MORGRAM PIPED WATER SUPPLY SCHEME , SM/15163 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MALGRAM, MURGRAM, MORGRAM & KHANJI Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3387/BWD | 03/08/2023 | 882 | PUSPA ENTERPRISE | 1333.98 | 142.34 | 42.83 | 40
2044 | PURBA BARDHAMAN | Burdwan Division | MORGRAM PIPED WATER SUPPLY SCHEME , SM/15163 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Murgram, Moregram, Malgram, Khanji, PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2739/BWD | 12/07/2024 | 173 | PUSPA ENTERPRISE | 185.75 | 19.02 | 40.96 | 72
2045 | PURBA BARDHAMAN | Burdwan Division | MORGRAM PIPED WATER SUPPLY SCHEME , SM/15163 | New | Extension work of pipe line MORGRAM Piped W/S. Scheme under Ketugram-I Block under Katwa Sub-Division within Burdwan Division PHE Dte. | 990/BWD | 06/03/2024 | 482 | PUSPA ENTERPRISE | 133.47 | 128.97 | 96.63 | 82
2046 | PURBA BARDHAMAN | Burdwan Division | MORGRAM PIPED WATER SUPPLY SCHEME , SM/15163 | New | Road crossing through metal/Concrete road by Jack Push Method for MORGRAM PWSS (SM/15163) under Ketugram-I Development Block under Katwa Sub-Divn within Burdwan Division PHE Dte. | 1320/BWD | 29/04/2025 | 21 | PUSPA ENTERPRISE | 9.6 | 0 | 0 | 100
2047 | PURBA BARDHAMAN | Central Drilling | CHATKA PIPED WATER SUPPLY SCHEME , SM/15168 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Chatka W/S Scheme (T/W-I & II), Ketugram-I Block under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | 1344/CDD | 13/09/2023 | 30 | OSMAN SEKH | 16.61 | 0 | 0 | 0
2048 | PURBA BARDHAMAN | Burdwan Division | CHATKA PIPED WATER SUPPLY SCHEME , SM/15168 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 2.18 | 0 | 0 | 0
2049 | PURBA BARDHAMAN | Burdwan Division | CHATKA PIPED WATER SUPPLY SCHEME , SM/15168 | New | Material Requisition To Resource Division | 3856/BWD | 01/09/2023 | 0 | Resource Division | 0.69 | 0 | 0 | 0
2050 | PURBA BARDHAMAN | Burdwan Division | CHATKA PIPED WATER SUPPLY SCHEME , SM/15168 | New | Material Requisition To Resource Division | 5232/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0 | 0
2051 | PURBA BARDHAMAN | Central Mechanical | CHATKA PIPED WATER SUPPLY SCHEME , SM/15168 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
2052 | PURBA BARDHAMAN | Central Mechanical | CHATKA PIPED WATER SUPPLY SCHEME , SM/15168 | New | New service connection charges for Chatka PWSS TW-2 | BP-2023-24-277 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.06 | 0 | 0 | 0
2053 | PURBA BARDHAMAN | Central Mechanical | CHATKA PIPED WATER SUPPLY SCHEME , SM/15168 | New | New service connection charges for Chatka PWSS TW-1 | BP-2023-24-276 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.85 | 0 | 0 | 0
2054 | PURBA BARDHAMAN | Burdwan Division | CHATKA PIPED WATER SUPPLY SCHEME , SM/15168 | New | CHATKA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | 3065/BWD | 17/07/2023 | 534 | M/S H.R. CONSTRUCTION | 402.79 | 365.97 | 90.9 | 86
2055 | PURBA BARDHAMAN | Central Mechanical | CHATKA PIPED WATER SUPPLY SCHEME , SM/15168 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHATKA Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4117/CMD | 29/08/2023 | 740 | SOUNAK ENTERPRISE | 28.48 | 22.2 | 95.23 | 90
2056 | PURBA BARDHAMAN | Burdwan Division | CHATKA PIPED WATER SUPPLY SCHEME , SM/15168 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Chakta, Mahula, Rajoor and Srigram PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2721/BWD | 11/07/2024 | 447 | ESCON INDIA | 139.35 | 21.22 | 78.05 | 70
2057 | PURBA BARDHAMAN | Central Mechanical | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15172 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 3 at Joykrishnapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 838/CMD | 20/02/2023 | 30 | C.M. ENTERPRISE | 10.43 | 9.62 | 100 | 100
2058 | PURBA BARDHAMAN | Central Mechanical | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15172 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 4 at Joykrishnapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 839/CMD | 20/02/2023 | 30 | MS MANABESH ROY | 10.14 | 9.61 | 100 | 100
2059 | PURBA BARDHAMAN | Burdwan Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15172 | New | Material Requisition To Resource Division | 4288/BWD | 29/09/2023 | 0 | Resource Division | 0.55 | 0 | 0 | 0
2060 | PURBA BARDHAMAN | Burdwan Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15172 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.33 | 0 | 0 | 0
2061 | PURBA BARDHAMAN | Burdwan Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15172 | New | Material Requisition To Resource Division | 4037/BWD | 08/09/2023 | 0 | Resource Division | 37.2 | 0 | 0 | 0
2062 | PURBA BARDHAMAN | Burdwan Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15172 | New | Laying of Rising main in between Tube Well and Distribution Line for Shimulia Village in Galsi -II Block under Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.. | 621/DSD | 05/08/2024 | 30 | MAA MAHAMAYA CONSTRUCTION | 2.15 | 2.13 | 100 | 100
2063 | PURBA BARDHAMAN | Burdwan Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15172 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR JOYKRISHNAPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE.". | 1015/KSD | 07/08/2024 | 15 | DEL DELTA CONSTRUCTION | 0.66 | 0.66 | 100 | 100
2064 | PURBA BARDHAMAN | Durgapur W/S Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15172 | New | Acceptance cum Formal Work order for Laying of interconnection for PH NO-3 (At Taranagar) Pipe Line for under JOYKRISHNAPUR PWSS, Galsi-II Block, under Durgapur W/S Division, PHE Dte. | 1410/DWSD | 01/10/2024 | 60 | MUNSHI JAVEDUR JAMAN | 0.63 | 0.58 | 100 | 100
2065 | PURBA BARDHAMAN | Central Mechanical | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15172 | New | Quotation for new service connection at Joykrishnapur PWSS PH-2 | BP-2023-24-333 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.33 | 0 | 0 | 0
2066 | PURBA BARDHAMAN | Central Mechanical | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15172 | New | New service connection charges for Joykrishnapur PWSS TW-1 | BP-2023-24-390 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.39 | 0 | 0 | 0
2067 | PURBA BARDHAMAN | Central Mechanical | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15172 | New | NEW SERVICE CONNECTION FOR JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME. | BP-2023-24-592 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.43 | 0 | 0 | 0
2068 | PURBA BARDHAMAN | Central Mechanical | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15172 | New | Quotation for new service connection at Joykrishnapur W/S Scheme for PH No-1 | BP-2023-24-332 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.57 | 0 | 0 | 0
2069 | PURBA BARDHAMAN | Burdwan Division | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15172 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GHUNI & JOYKRISHNAPUR Piped Water Supply Scheme under Purbasthali II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3510/BWD | 10/08/2023 | 808 | BKB INFRA PROJECTS PRIVATE LIMITED | 551.42 | 202.23 | 63.95 | 20
2070 | PURBA BARDHAMAN | Central Mechanical | JOYKRISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15172 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JOYKRISHNAPUR Water Supply Scheme [ Block- PURBASTHALI-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4143/CMD | 29/08/2023 | 646 | JYOTY SOLAR POWER. | 26.98 | 0 | 0 | 45
2071 | PURBA BARDHAMAN | Burdwan Division | UNIATATARPUR PIPED WATER SUPPLY SCHEME , SM/15133 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.34 | 0 | 0 | 0
2072 | PURBA BARDHAMAN | Burdwan Division | UNIATATARPUR PIPED WATER SUPPLY SCHEME , SM/15133 | New | Material Requisition To Resource Division | 3982/BWD | 08/09/2023 | 0 | Resource Division | 2.76 | 0 | 0 | 0
2073 | PURBA BARDHAMAN | Burdwan Division | UNIATATARPUR PIPED WATER SUPPLY SCHEME , SM/15133 | New | Material Requisition To Resource Division | 5070/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
2074 | PURBA BARDHAMAN | Central Mechanical | UNIATATARPUR PIPED WATER SUPPLY SCHEME , SM/15133 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at UNIATATARPUR Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4101/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 26.93 | 20.81 | 77.29 | 48
2075 | PURBA BARDHAMAN | Burdwan Division | UNIATATARPUR PIPED WATER SUPPLY SCHEME , SM/15133 | New | Balance work for OHR, extension of pipeline to provide FHTC in Barulia & Narayanpur mouza with Sinking of Tube well, Construction of Pump house, Boundary Wall, Land Development, Plinth Protection for pump house & OHR under, approach road to 2nd pump house UNIATATARPUR PWSS, Katwa Sub Division, Block- Mongolkote, Burdwan Division PHE Dte. | 3162/BWD | 22/08/2024 | 120 | POWER TOOLS & ENGINEERING | 152.52 | 0 | 0 | 0
2076 | PURBA BARDHAMAN | Central Mechanical | UNIATATARPUR PIPED WATER SUPPLY SCHEME , SM/15133 | New | Quotation for new service connection for Unitatarpur PWSS PH-1 | BP-2024-25-127 | 31/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.22 | 0 | 0 | 0
2077 | PURBA BARDHAMAN | Central Mechanical | UNIATATARPUR PIPED WATER SUPPLY SCHEME , SM/15133 | New | Quotation for New service connection for Unitatarpur PWSS PH 2 | BP-2024-25-126 | 31/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.78 | 0 | 0 | 0
2078 | PURBA BARDHAMAN | Burdwan Division | UNIATATARPUR PIPED WATER SUPPLY SCHEME , SM/15133 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEULIA, GOBARDHANPUR, KHARIJA-KASHIGRAM & UNIATATARPUR Piped Water Supply Scheme under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | 3491/BWD | 09/08/2023 | 1058 | POWER TOOLS & ENGINEERING | 1741.05 | 137.46 | 34.25 | 10
2079 | PURBA BARDHAMAN | Central Mechanical | UNIATATARPUR PIPED WATER SUPPLY SCHEME , SM/15133 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
2080 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI , SM/15184 | Augmentation | Preparation and Submission of DPR for Augmentation of ABUJHATI PWSS under Jamalpur Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1526/BSD | 17/07/2023 | 15 | MEASURE LAND | 0.78 | 0.77 | 100 | 100
2081 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI , SM/15184 | Augmentation | Laying of HDPE Pipeline from 4th Number Pump House to main distribution system for ABUJHATI Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 3925/BWD | 05/09/2023 | 30 | MAA BHABANI CONSTRUCTION | 21.04 | 20.26 | 100 | 100
2082 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI , SM/15184 | Augmentation | New service connection charges for Abujhati PWSS TW-4 | BP-2023-24-66 | 20/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.26 | 0 | 0 | 0
2083 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI , SM/15184 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augmentation of ABUJHATI[JAMALPUR] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3902/CMD | 18/08/2023 | 30 | KUNDU CONSTRUCTION. | 12.25 | 10.78 | 88.06 | 95
2084 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI , SM/15184 | Augmentation | Extension of CIDF/D.I Pipes with specials for providing FHTC at Siromoni mouza within command area of Abujhati Piped W/S Scheme Jamalpur Development Block under Burdwan Division,PHE Dte. | 1005/BSD | 06/06/2023 | 15 | DEBASHISH ENTERPRISE | 0.94 | 0.79 | 100 | 100
2085 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI , SM/15184 | Augmentation | Laying different dia UPVC Pipeline for inter connection of existing FHTC near Raypara of Abujhati Flyover i.c.w. Road widening from 4 lane to 6 lane of NH-2 at chane 601+9521+960 under ABUIHATI PWSS in jamalpur Block within Burdwan Sub Divn. under Burdwan Division, P.H.E. Dte. | 532/BSD | 14/03/2024 | 30 | SOUMYAVASH DAS | 0.89 | 0.88 | 100 | 100
2086 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI , SM/15184 | Augmentation | Illumination arrangement and miscelleneous works at Abujhati water supply scheme under Jamalpur Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2783/CMD | 01/10/2024 | 60 | M/S. S.R. ENTERPRISE | 19.25 | 0 | 0 | 20
2087 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI , SM/15184 | Augmentation | Providing FHTC for 100% coverage at Napara, Astai, Panch Shimul, Dastanpur, Keotara, Siromani, Abujhati & Ajhapur Habitation (Village) for ABUJHATI Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 2236/BWD | 16/05/2023 | 688 | PAL CONSTRUCTION | 36.63 | 26.66 | 72.96 | 50
2088 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI , SM/15184 | Augmentation | Construction of overflow chamber with u-PVC pipe line for removal of excess water at Head work Site Under ABUJHATI PWSS Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 88/AE/HQ | 08/01/2025 | 30 | SOUMYAVASH DAS | 0.97 | 0 | 0 | 100
2089 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI , SM/15184 | Augmentation | Improvement of 300 CuM OHR (Concreting, Plastering, Primer and Painting) for Abujhati PWSS under Jamalpur Block under Burdwan Divn., PHE. Dte. | 450/AE/HQ | 24/07/2024 | 45 | DEBASHISH ENTERPRISE | 2.01 | 2.01 | 100 | 100
2090 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR ABUJHATI , SM/15184 | Augmentation | Construction of Boundary wall, Land Development and Interconnection of ABUJHATI Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. [FOR 4TH. TUBE WELL SITE]. | 71/BWD | 06/01/2025 | 30 | ABDUL HAI | 10.34 | 0 | 0 | 100
2091 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF RAYAN PART III (KOPIBAGAN) PIPED WATER SUPPLY SCHEME , SM/16548 | Augmentation | Route Survey & Preparation of DPR for RAYAN PART-III KOPIBAGAN W/S Scheme under Burdwan-I Block under Burdwan Sub- Division under Burdwan Division PHE Dte. | 2586/BSD | 26/11/2024 | 45 | APEX ENGINEERING | 2.57 | 0 | 0 | 0
2092 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF RAYAN PART III (KOPIBAGAN) PIPED WATER SUPPLY SCHEME , SM/16548 | Augmentation | Re-Connection of existing FHTC from newly laid distribution pipe At SUKANTA PALLY for Augmentation of RAYAN (PART-III) [ KOPIBAGAN] PIPED WATER SUPPLY SCHEME , Block- Burdwan-I , within Burdwan Sub Division under Burdwan Division PHE Dte | 1009/BSD | 06/06/2024 | 30 | SK RAJU | 0.96 | 0 | 0 | 0
2093 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF RAYAN PART III (KOPIBAGAN) PIPED WATER SUPPLY SCHEME , SM/16548 | Augmentation | Re-Connection of existing FHTC from newly laid distribution pipe At KHA PUKUR ADIBASIPARA for Augmentation of RAYAN (PART-III) [ KOPIBAGAN] PIPED WATER SUPPLY SCHEME , Block- Burdwan-I , within Burdwan Sub Division under Burdwan Division PHE Dte. | 1030/BSD | 10/06/2024 | 30 | SK RAJU | 0.96 | 0 | 0 | 0
2094 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF RAYAN PART III (KOPIBAGAN) PIPED WATER SUPPLY SCHEME , SM/16548 | Augmentation | Material Requisition To Resource Division | 4100/BWD | 25/11/2024 | 0 | Resource Division | 11.09 | 0 | 0 | 0
2095 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF RAYAN PART III (KOPIBAGAN) PIPED WATER SUPPLY SCHEME , SM/16548 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Rayan. Part -3 Kopibagan Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2596/CMD | 07/06/2023 | 694 | CHOUDHURY ENTERPRISE | 24.13 | 6.45 | 26.74 | 50
2096 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF RAYAN PART III (KOPIBAGAN) PIPED WATER SUPPLY SCHEME , SM/16548 | Augmentation | Augmentation of RAYAN (Part-III) (KOPIBAGAN) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan -I Block, District:- Purba-Bardhaman. | 2304/BWD | 19/05/2023 | 927 | IJABUL SEKH | 166.98 | 79.31 | 47.5 | 100
2097 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF RAYAN PART III (KOPIBAGAN) PIPED WATER SUPPLY SCHEME , SM/16548 | Augmentation | Illumination arrangement & different electro-mechanical works at RAYAN water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2799/CMD | 01/10/2024 | 60 | JOYGURU ENTERPRISE | 6.04 | 0 | 0 | 40
2098 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF RAYAN PART III (KOPIBAGAN) PIPED WATER SUPPLY SCHEME , SM/16548 | Augmentation | Allied work for Road restoration work due to FHTC & Extension pipe line for different village and inside road of OHR side for Rayan pwss at Bardhhaman-I Development Block under Burdwan Division, PHE Dte. | 1273/BSD | 12/07/2024 | 217 | MAA KALI CONSTRUCTION | 3.89 | 0 | 0 | 100
2099 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF RAYAN PART III (KOPIBAGAN) PIPED WATER SUPPLY SCHEME , SM/16548 | Augmentation | Laying distribution system different damaged section regrading smooth running FHTC work for RAYAN Water Supply Scheme at Bardhaman-I Development Block under Burdwan Division,PHE Dte. | 121/BSD | 18/01/2024 | 30 | DHIRENDRANATH SOM | 0.96 | 0 | 0 | 100
2100 | PURBA BARDHAMAN | Central Drilling | ARGUN PIPED WATER SUPPLY SCHEME , SM/16482 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Argun W/S Scheme (T/W-I & II) , Ketugram-I Block under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | 1056/CDD | 16/08/2023 | 30 | C.M. ENTERPRISE | 16.2 | 0 | 0 | 0
2101 | PURBA BARDHAMAN | Burdwan Division | ARGUN PIPED WATER SUPPLY SCHEME , SM/16482 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.38 | 0 | 0 | 0
2102 | PURBA BARDHAMAN | Burdwan Division | ARGUN PIPED WATER SUPPLY SCHEME , SM/16482 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 16.15 | 0 | 0 | 0
2103 | PURBA BARDHAMAN | Burdwan Division | ARGUN PIPED WATER SUPPLY SCHEME , SM/16482 | New | Material Requisition To Resource Division | 5253/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0 | 0
2104 | PURBA BARDHAMAN | Central Mechanical | ARGUN PIPED WATER SUPPLY SCHEME , SM/16482 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
2105 | PURBA BARDHAMAN | Central Mechanical | ARGUN PIPED WATER SUPPLY SCHEME , SM/16482 | New | New Service connection for Argun PWSS TW-1 | BP-2023-24-460 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.91 | 0 | 0 | 0
2106 | PURBA BARDHAMAN | Central Mechanical | ARGUN PIPED WATER SUPPLY SCHEME , SM/16482 | New | New Service connection at Argun PWSS PH-2 | BP-2023-24-461 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.63 | 0 | 0 | 0
2107 | PURBA BARDHAMAN | Burdwan Division | ARGUN PIPED WATER SUPPLY SCHEME , SM/16482 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMEGERIA, ARGUN, CHINISPUR & KULUTIA Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3630/BWD | 21/08/2023 | 1107 | M/S GOUTAM DAS | 1421.7 | 240.73 | 73.35 | 75
2108 | PURBA BARDHAMAN | Burdwan Division | ARGUN PIPED WATER SUPPLY SCHEME , SM/16482 | New | Hiring of one no Diesel Motor Cab (BS-VI) including the cost of fuel . mobile & other charges for the inspection of the different projects of JJM for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. (Period:- 01/03/2025 to 31/08/2025) [Sl No-02] | 321/KTS | 28/02/2025 | 184 | HAMID SK | 1.84 | 0 | 0 | 0
2109 | PURBA BARDHAMAN | Central Mechanical | ARGUN PIPED WATER SUPPLY SCHEME , SM/16482 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at ARGUN Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4119/CMD | 29/08/2023 | 30 | DUTTA ENTERPRISE | 26.95 | 20.79 | 94.78 | 88
2110 | PURBA BARDHAMAN | Burdwan Division | ARGUN PIPED WATER SUPPLY SCHEME , SM/16482 | New | Road crossing through metal / concrete road by Jack Push Method for AMEGERIA (SM/16023), ARGUN (SM/16482), CHINISPUR (SM/15170) and KULITIA (SM/15167) PWSS under Ketugram I Development Block under Katwa Sub Division within Burdwan Division, PHE. Dte. | 977/BWD | 13/03/2025 | 60 | M/S GOUTAM DAS | 39.22 | 0 | 0 | 100
2111 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Belari village of Kayrapur Piped W/S Scheme (Part-A) within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte.[Gr.-A] | 715/DSD | 17/12/2021 | 15 | M/S S. CHOUDHURY | 4.83 | 4.83 | 100 | 1
2112 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kayrapur vilage of Kayrapur Piped W/S Scheme (Part-A) within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-B] | 716/DSD | 17/12/2021 | 15 | M/S S. CHOUDHURY | 4.83 | 4.83 | 100 | 1
2113 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from distribution system within the command area of KAYRAPUR Water Supply Scheme (Part-A) at Belari, Bara, Bhada & Kayrapur (Part) village under JAL SAPNO MISSION under Ausgram-I Block in Purba Bardhanan District under Burdwan Division, P.H.E. Dte. | 26/BWD | 04/01/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 42.23 | 42.94 | 100 | 1
2114 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Belari village of Kayrapur Piped W/S Scheme (Part-A) within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-A] | 736/DSD | 28/12/2021 | 15 | M/S S. CHOUDHURY | 4.83 | 4.83 | 100 | 1
2115 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kayrapur vilage of Kayrapur Piped W/S Scheme (Part-A) within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, P.H.E. Dte. [Gr.-B] | 737/DSD | 28/12/2021 | 15 | M/S S. CHOUDHURY | 4.83 | 4.83 | 100 | 1
2116 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
2117 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from distribution system within the command area of KAYRAPUR Water Supply Scheme (Part-B) at Billogram, Brajapur, Asinda and Noada village under JAL SAPNO MISSION under Ausgram-I Block in Purba Bardhanan District under Burdwan Division, P.H.E. Dte. | 860/BWD | 11/02/2022 | 60 | ASHOK KUMAR GHOSH | 95.9 | 51.4 | 53.6 | 1
2118 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Land development and Construction of connecting road from PH to OHR at 1st tube well site of KAYRAPUR Water Supply Scheme (Part-B) within Durgapur Sub Division Under Burdwan Division, PHE Dte. | 558/DSD | 20/07/2023 | 30 | SAMANTA CONSTRUCTION | 4.84 | 0 | 0 | 0
2119 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Kayrapur Village, Ausgram-I Block within Kayrapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 823/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0 | 0 | 0
2120 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhada village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte.. [SL. No. : 20] | 3399/BWD | 24/06/2021 | 15 | M/S S. CHOUDHURY | 4.86 | 4.86 | 100 | 1
2121 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kayrapur village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 19] | 3398/BWD | 24/06/2021 | 15 | M/S S. CHOUDHURY | 4.86 | 4.86 | 100 | 1
2122 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Laying of rising main in between two number of Tube wells to Over Head Reservoir for Kayrapur water supply scheme (Part-A) within Durgapur Sub-Division in Ausgram-I Block under Burdwan Division, PHE Dte. | 991/BWD | 04/02/2021 | 30 | M/S S. CHOUDHURY | 7.12 | 0 | 0 | 1
2123 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Additional cutting of existing concrete pavement between Node J4 to J51 for laying of 300 mm dia D.I distribution in connection with Laying distribution system of Kayrapur Piped Water Supply Scheme at Ausgram-I Block within Durgapur Sub-Division under Burdwan Division, PHE Dte. (Gr.-C) | 109/DSD | 29/01/2021 | 15 | M/S S. CHOUDHURY | 4.05 | 0 | 0 | 1
2124 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Koranji village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 21] | 3397/BWD | 24/06/2021 | 15 | M/S S. CHOUDHURY | 3.44 | 3.44 | 100 | 1
2125 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Restoration of damaged pipeline of distribution main for construction of drain at Billwagram village within Kayrapur W/S Scheme (Part-B) in Ausgram-I Block under Burdwan Division, P.H.E. Dte.[SL-11] | 159/DSD | 13/04/2023 | 21 | SANDIPAN SENGUPTA | 0.52 | 0.52 | 100 | 100
2126 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Relaying and restoration of damaged pipeline of distribution main for construction of drain at Brajapur, Chonary and Asinda village to keep on FHTC within Kayrapur W/S Scheme (Part-B) in Ausgram-I Block under Burdwan Division, P.H.E. Dte. | 651/DSD | 24/08/2023 | 30 | TARAMA AGENCY | 0.95 | 0.95 | 100 | 100
2127 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Material Requisition To Resource Division | 1110/BWD | 26/02/2022 | 0 | Resource Division | 25.78 | 0 | 0 | 0
2128 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of November'2022. | 954/JJM/22-23 | 13/01/2023 | 0 | SUJAUDDIN SEKH | 0.38 | 0 | 0 | 0
2129 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kayrapur village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 19] | 1459/BWD | 18/02/2021 | 15 | M/S S. CHOUDHURY | 4.86 | 9.73 | 200 | 0
2130 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Koranji village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 21] | 1457/BWD | 18/02/2021 | 15 | M/S S. CHOUDHURY | 4.86 | 9.73 | 200 | 0
2131 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhada village of Kayrapur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte.. [SL. No. : 20] | 1458/BWD | 18/02/2021 | 15 | M/S S. CHOUDHURY | 4.86 | 9.73 | 200 | 0
2132 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Construction of boundary wall at 2nd Tube well site of KAYRAPUR Water Supply Scheme (Part-B) and its adjoining mouzas, Block-Ausgram-I, under Burdwan Division P.H.E. Dte. | 44/DSD | 17/01/2024 | 30 | SK BADIUZZAMAL | 3.83 | 0 | 0 | 100
2133 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of KAYRAPUR Piped Water Supply Scheme at AUSGRAM-I Block under Burdwan Division, P.H.E. DTE. , SM/08710 | Retrofitting | Acceptance cum Formal Work Order for Balance work for distribution system HDPE earth work & concrete work for Kayrapur PWSS, Block- Ausgram-I under Durgapur W/S Division, PHE Dte. | 1240/DWSD | 29/08/2024 | 15 | TARA MA AGENCY | 1 | 0.47 | 100 | 100
2134 | PURBA BARDHAMAN | Burdwan Division | KHANPUR PIPED WATER SUPPLY SCHEME , SM/16540 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.22 | 0 | 0 | 0
2135 | PURBA BARDHAMAN | Burdwan Division | KHANPUR PIPED WATER SUPPLY SCHEME , SM/16540 | New | Material Requisition To Resource Division | 4293/BWD | 29/09/2023 | 0 | Resource Division | 2.89 | 0 | 0 | 0
2136 | PURBA BARDHAMAN | Burdwan Division | KHANPUR PIPED WATER SUPPLY SCHEME , SM/16540 | New | Material Requisition To Resource Division | 4934/BWD | 10/11/2023 | 0 | Resource Division | 67.03 | 0 | 0 | 0
2137 | PURBA BARDHAMAN | Central Mechanical | KHANPUR PIPED WATER SUPPLY SCHEME , SM/16540 | New | NEW SERVICE CONNECTION FOR KHANPUR PWSS. | BP-2023-24-562 | 23/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.01 | 0 | 0 | 0
2138 | PURBA BARDHAMAN | Central Mechanical | KHANPUR PIPED WATER SUPPLY SCHEME , SM/16540 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KHANPUR Water Supply Scheme [ Block-MONTESWAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4086/CMD | 29/08/2023 | 30 | S DUTTA | 43.47 | 0 | 0 | 65
2139 | PURBA BARDHAMAN | Burdwan Division | KHANPUR PIPED WATER SUPPLY SCHEME , SM/16540 | New | KHANPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Monteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | 4808/BWD | 08/11/2023 | 723 | NATIONAL CONSTRUCTION | 707.7 | 0 | 0 | 60
2140 | PURBA BARDHAMAN | Central Mechanical | KHANPUR PIPED WATER SUPPLY SCHEME , SM/16540 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
2141 | PURBA BARDHAMAN | Central Mechanical | KHANPUR PIPED WATER SUPPLY SCHEME , SM/16540 | New | CONTINUATION OREDER- Hiring of inspection vehicle no. [ WB41H5741] (Diesel/CNG/LPG Driven) for supervision of the site for the office of the Assistant Engineer ,CMD PHE Dte. [W.E.F- 01.08.2025 to 30.09.2025] | 1035/CMSD | 30/07/2025 | 61 | PRODYUT GHOSH | 0.8 | 0 | 0 | 0
2142 | PURBA BARDHAMAN | Burdwan Division | KHANPUR PIPED WATER SUPPLY SCHEME , SM/16540 | New | Land demarcation and preparation of sketch map including legal charges for different PWSS under JJM of Manteswar Block under Duragapur (Burdwan North) Sub-Division, P.H.E. DTE. [Part-A] | 159/DSD | 27/01/2025 | 180 | SHUBHRA KANTI GHOSH | 0.81 | 0 | 0 | 100
2143 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF KALYANPUR PIPED WATER SUPPLY SCHEME , SM/16299 | Augmentation | NEW SERVICE CONNECTION FOR AUGMENTATION FOR KALYANPUR PWSS PH-2 | BP-2024-25-87 | 15/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.96 | 0 | 0 | 0
2144 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF KALYANPUR PIPED WATER SUPPLY SCHEME , SM/16299 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of KALYANPUR[KALNA-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4438/CMD | 01/11/2023 | 760 | SOUNAK ENTERPRISE | 24.41 | 9.51 | 38.95 | 50
2145 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF KALYANPUR PIPED WATER SUPPLY SCHEME , SM/16299 | Augmentation | Different types of works involve in connection with Augmentation of KALYANPUR (SM/16299) Water Supply Scheme & BHABANANDAPUR (SM/16024) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2433/BWD | 27/06/2024 | 247 | BALAJEE ENTERPRISES | 225.16 | 109.26 | 72.36 | 2
2146 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF KALYANPUR PIPED WATER SUPPLY SCHEME , SM/16299 | Augmentation | Providing FHTC work at Kalyanpur village under KALYANPUR Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 5514/BWD | 14/12/2023 | 151 | SETH ENTERPRISE | 13.89 | 0 | 0 | 100
2147 | PURBA BARDHAMAN | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME , SM/16303 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.5 | 0 | 0 | 0
2148 | PURBA BARDHAMAN | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME , SM/16303 | New | Material Requisition To Resource Division | 4899/BWD | 10/11/2023 | 0 | Resource Division | 15.99 | 0 | 0 | 0
2149 | PURBA BARDHAMAN | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME , SM/16303 | New | Material Requisition To Resource Division | 4308/BWD | 29/09/2023 | 0 | Resource Division | 0.81 | 0 | 0 | 0
2150 | PURBA BARDHAMAN | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME , SM/16303 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR GAHAK PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 1017/KSD | 07/08/2024 | 15 | DEL DELTA CONSTRUCTION | 0.66 | 0.66 | 100 | 100
2151 | PURBA BARDHAMAN | Central Mechanical | GAHAK PIPE WATER SUPPLY SCHEME , SM/16303 | New | New service connection for Gahak PWSS TW-2. | BP-2023-24-498 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.7 | 0 | 0 | 0
2152 | PURBA BARDHAMAN | Central Mechanical | GAHAK PIPE WATER SUPPLY SCHEME , SM/16303 | New | New service connection for Gahak PWSS TW-1. | BP-2023-24-497 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.7 | 0 | 0 | 0
2153 | PURBA BARDHAMAN | Central Mechanical | GAHAK PIPE WATER SUPPLY SCHEME , SM/16303 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at GAHAK Water Supply Scheme [ Block- PURBASTHALI -1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | 4192/CMD | 29/08/2023 | 30 | SOUNAK ENTERPRISE | 21.33 | 0 | 0 | 50
2154 | PURBA BARDHAMAN | Burdwan Division | GAHAK PIPE WATER SUPPLY SCHEME , SM/16303 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMPUR, GAHAK & SHANKRA Piped Water Supply Scheme under Purbasthali I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3957/BWD | 07/09/2023 | 1051 | M/S B. NANDI | 758.52 | 92.6 | 38.14 | 20
2155 | PURBA BARDHAMAN | Central Mechanical | GAHAK PIPE WATER SUPPLY SCHEME , SM/16303 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
2156 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME , SM/16301 | Augmentation | Augmentation of KULTI PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Kalna - II Block, Purba Burdwan District under Burdwan Division, PHE.Dte. | 3747/BWD | 28/08/2023 | 60 | MAHALAXMI CONSTRUCTION | 21.92 | 0 | 0 | 0
2157 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME , SM/16301 | Augmentation | Additional Quotation for augmentation of Kulti PWSS PH 3 | BP-2024-25-407 | 11/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.79 | 0 | 0 | 0
2158 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME , SM/16301 | Augmentation | New service connection for augmentation of Kulti PH-3 PWSS. | BP-2024-25-29 | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.7 | 0 | 0 | 0
2159 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME , SM/16301 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1, 2 & 3 at Augmentation of KULTI[KALNA-II]] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4439/CMD | 04/10/2023 | 698 | CHOUDHURY ENTERPRISE | 36.64 | 0 | 0 | 33
2160 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME , SM/16301 | Augmentation | Different types of works involve in connection with Augmentation of KULTI (SM/16301) Water Supply Scheme, Block Kalna II under Burdwan Division, PHE Dte. | 2553/BWD | 04/07/2024 | 240 | HAMID SK | 222.11 | 83.72 | 41.1 | 80
2161 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF KULTI PIPED WATER SUPPLY SCHEME , SM/16301 | Augmentation | Illumination arrangement at Kulti water supply scheme under Kalna 2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2787/CMD | 01/10/2024 | 334 | DELTA ENGINEERING ENTERPRISE | 10.7 | 0 | 0 | 30
2162 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA , SM/16192 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of PALLA W/S Scheme under Memari - I Block within Burdwan Sub-Division, PHE Dte. | 2706/BWD | 08/06/2023 | 30 | DAS CONSTRUCTION | 13.26 | 11.91 | 100 | 100
2163 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA , SM/16192 | Augmentation | Preparation and Submission of DPR for Augmentation of Palla PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1585/BSD | 24/07/2023 | 15 | MEASURE LAND | 0.78 | 0.77 | 100 | 100
2164 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA , SM/16192 | Augmentation | Illumination arrangement & different electro-mechanical works at PALLA and others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2798/CMD | 01/10/2024 | 60 | SUBRATA BHADRA | 15.45 | 0 | 0 | 0
2165 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA , SM/16192 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augmentation of PALLA[MEMARI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3903/CMD | 18/08/2023 | 30 | SIMARR | 11.88 | 11.53 | 100 | 100
2166 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA , SM/16192 | Augmentation | Construction of switch rooms & Rising main at different TW site for PALLA Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | 3765/BWD | 29/08/2023 | 60 | SANDIP SARKAR | 7.52 | 5.87 | 100 | 98
2167 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA , SM/16192 | Augmentation | Supply & installation of Automatic Chlorinator at Palla water supply scheme, P.H. No.- II under CMD, P.H.E. Dte., Dist.- Purba Bardhaman. | 726/CMSD | 10/05/2024 | 10 | MITRA ENTERPRISE | 0.96 | 0 | 0 | 100
2168 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA , SM/16192 | Augmentation | NEW SERVICE CONNECTION FOR PALLA PWSS | BP-2023-24-553 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.35 | 0 | 0 | 0
2169 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA , SM/16192 | Augmentation | Additional quotation for installation of DTR 25KVA at Palla PWSS PH-2 | BP-2024-25-235 | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.51 | 0 | 0 | 0
2170 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA , SM/16192 | Augmentation | Augmentation of PALLA PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Memari - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | 2415/BWD | 29/05/2023 | 701 | LAKSHMIKANTA DAS | 11.03 | 0 | 0 | 100
2171 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALLA , SM/16192 | Augmentation | Laying distribution pipe line, FHTC, 3rd tube well installation, Construction of switch room and boundary wall for PALLA village under Augmentation of PALLA Piped Water Supply Scheme, Block - Memari - I, under Burdwan Division, P.H.E. Dte. | 5329/BWD | 04/12/2023 | 502 | SARKAR AGENCY | 136.31 | 67.39 | 49.49 | 95
2172 | PURBA BARDHAMAN | Burdwan Division | NETRAKHANDA PIPED WATER SUPPLY SCHEME , SM/16616 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.53 | 0 | 0 | 0
2173 | PURBA BARDHAMAN | Burdwan Division | NETRAKHANDA PIPED WATER SUPPLY SCHEME , SM/16616 | New | Material Requisition To Resource Division | 5055/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
2174 | PURBA BARDHAMAN | Burdwan Division | NETRAKHANDA PIPED WATER SUPPLY SCHEME , SM/16616 | New | Material Requisition To Resource Division | 4290/BWD | 29/09/2023 | 0 | Resource Division | 2.08 | 0 | 0 | 0
2175 | PURBA BARDHAMAN | Burdwan Division | NETRAKHANDA PIPED WATER SUPPLY SCHEME , SM/16616 | New | NETRAKHANDA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | 4121/BWD | 14/09/2023 | 365 | SUJAY KUMAR RAY | 345.67 | 23.33 | 6.75 | 50
2176 | PURBA BARDHAMAN | Central Mechanical | NETRAKHANDA PIPED WATER SUPPLY SCHEME , SM/16616 | New | New Service connection for Netrakahanda W/S Scheme PH No.-I | BP-2023-24-319 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.7 | 0 | 0 | 0
2177 | PURBA BARDHAMAN | Central Mechanical | NETRAKHANDA PIPED WATER SUPPLY SCHEME , SM/16616 | New | New Service connection for Netrakhanda W/S Scheme PH No.-II | BP-2023-24-320 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.85 | 0 | 0 | 0
2178 | PURBA BARDHAMAN | Central Mechanical | NETRAKHANDA PIPED WATER SUPPLY SCHEME , SM/16616 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Netrakhanda Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4033/CMD | 29/08/2023 | 30 | GLACIER ENGINEERING CO | 28.97 | 0 | 0 | 96
2179 | PURBA BARDHAMAN | Central Mechanical | NETRAKHANDA PIPED WATER SUPPLY SCHEME , SM/16616 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
2180 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN , SM/15723 | Augmentation | Installation of a voltage Correcting device along with allied accessories at PALASAN Water Supply Scheme, Pump House-1, under CMD, PHE Dte., Dist.- Paschim-Bardhaman. | 1160/CMD | 13/03/2023 | 30 | P.K. ENGINEERING | 2.98 | 2.98 | 100 | 0
2181 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN , SM/15723 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Palasan Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | 3047/CMD | 20/07/2023 | 30 | S.K. ELECTRICALS | 11.09 | 10.23 | 92.22 | 80
2182 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN , SM/15723 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of PALASON & its adjoining mouzas Piped Water Supply Scheme, Block - Raina - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 4612/BWD | 17/10/2022 | 30 | M/S SYCHROTECH INDUSTRY | 10.12 | 8.33 | 100 | 0
2183 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN , SM/15723 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for PALASON its Adjoining Mouza W/S Scheme, Block - Raina-I within Burdwan Sub-Division, PHE Dte. (Mouza- PASCHIM PARA) | 497/BSD | 21/03/2023 | 45 | MAA MAHAMAYA CONSTRUCTION | 3.63 | 3.32 | 100 | 100
2184 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN , SM/15723 | Augmentation | New Service Connection Charges Bill for TW-3 of Aug. Palasan W/S Scheme | BP-2023-24-7 | 08/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.39 | 0 | 0 | 0
2185 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN , SM/15723 | Augmentation | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PALASHAN Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1601/BWD | 04/04/2023 | 60 | BHOWMICK ENTERPRISE | 50.14 | 47.9 | 100 | 100
2186 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN , SM/15723 | Augmentation | Improvement work of PALASON Piped Water Supply Scheme for smooth running of FHTC within Raina-I block under Burdwan Division, PHE Dte. | 2739/BSD | 28/11/2023 | 30 | ANWESHA CONSTRUCTION | 0.95 | 0.94 | 100 | 100
2187 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN , SM/15723 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Paschimpara village of Raina-I Block under Palashan Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte(5 nos Board) | 2355/BSD | 21/08/2025 | 10 | S.M. ENGOCON | 0.72 | 0 | 0 | 0
2188 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR PALASAN , SM/15723 | Augmentation | Left out FHTC & distribution Networks at Palasan Paschim para under PALASAN Piped Water Supply Scheme, Block- RAINA-I within Burdwan Sub-Division under Burdwan Division PHE Dte. | 1471/BSD | 25/06/2025 | 30 | SK ABDUL HALIM | 1.97 | 0 | 0 | 0
2189 | PURBA BARDHAMAN | Burdwan Division | BAKALSA PIPE WATER SUPPLY SCHEME , SM/16030 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 12.89 | 0 | 0 | 0
2190 | PURBA BARDHAMAN | Central Mechanical | BAKALSA PIPE WATER SUPPLY SCHEME , SM/16030 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BAKALSA Water Supply Scheme [ Block- KETUGRAM-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | 4191/CMD | 29/08/2023 | 485 | MITRA ASSOCIATE | 20.63 | 9.43 | 45.72 | 44
2191 | PURBA BARDHAMAN | Central Mechanical | BAKALSA PIPE WATER SUPPLY SCHEME , SM/16030 | New | New service connection charges for Bakalsa PWSS TW-1 | BP-2024-25-322 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.62 | 0 | 0 | 0
2192 | PURBA BARDHAMAN | Central Mechanical | BAKALSA PIPE WATER SUPPLY SCHEME , SM/16030 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bakalsa Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4169/CMD | 29/08/2023 | 580 | M/S, S.DAS AND ENTERPRISE. | 29.71 | 14.94 | 50.3 | 50
2193 | PURBA BARDHAMAN | Burdwan Division | BAKALSA PIPE WATER SUPPLY SCHEME , SM/16030 | New | Balance Work For OHR, Extension Of Pipeline To Provide FHTC With Sinking Of Tube Well, Construction Of Pump House, Boundary Wall, Land Development, Plinth Protection For Pump House, Approach Road & Other Related Work Under Bakalsa, Chakdaha, Ehaipur, Khatundi And Ketugram (Zone-I) Part-A & B PWSS Under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2741/BWD | 12/07/2024 | 538 | M/S M.M. ENTERPRISE | 205.15 | 6.49 | 22.73 | 65
2194 | PURBA BARDHAMAN | Central Mechanical | KANKURHATI PIPED WATER SUPPLY SCHEME , SM/16031 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at KANKURHATI [KETUGRAM-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2519/CMD | 02/06/2023 | 30 | P.K. ENGINEERING | 21.26 | 9.52 | 44.76 | 40
2195 | PURBA BARDHAMAN | Burdwan Division | KANKURHATI PIPED WATER SUPPLY SCHEME , SM/16031 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 0.87 | 0 | 0 | 0
2196 | PURBA BARDHAMAN | Burdwan Division | KANKURHATI PIPED WATER SUPPLY SCHEME , SM/16031 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 21.7 | 0 | 0 | 0
2197 | PURBA BARDHAMAN | Burdwan Division | KANKURHATI PIPED WATER SUPPLY SCHEME , SM/16031 | New | Material Requisition To Resource Division | 4938/BWD | 10/11/2023 | 0 | Resource Division | 0.73 | 0 | 0 | 0
2198 | PURBA BARDHAMAN | Central Mechanical | KANKURHATI PIPED WATER SUPPLY SCHEME , SM/16031 | New | New service connection charges for Kankurhati W/S Scheme TW-1 | BP-2023-24-28 | 22/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.49 | 0 | 0 | 0
2199 | PURBA BARDHAMAN | Central Mechanical | KANKURHATI PIPED WATER SUPPLY SCHEME , SM/16031 | New | New service connection charges for Kankurhati PWSS TW-2 | BP-2023-24-406 | 04/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.45 | 0 | 0 | 0
2200 | PURBA BARDHAMAN | Burdwan Division | KANKURHATI PIPED WATER SUPPLY SCHEME , SM/16031 | New | KANKURHATI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at KANKURHATI Mouza (J.L. - 120) under KETUGRAM -II Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1428/BWD | 24/03/2023 | 648 | HAMID SK | 77.54 | 54.7 | 79.8 | 100
2201 | PURBA BARDHAMAN | Burdwan Division | KANKURHATI PIPED WATER SUPPLY SCHEME , SM/16031 | New | KANKURHATI Piped Water Supply Scheme (Balance Portion) with sinking of Tube-well, LDS, Rising Main, FHTC, & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at BEGUNKHOLA Mouza (J.L. - 121) under KETUGRAM -II Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL. | 517/BWD | 06/02/2024 | 604 | OM ENTERPRISE | 60.2 | 34.25 | 52.08 | 80
2202 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for SAGRAI its Adjoining Mouza W/S Scheme, Block -Khandaghosh within Burdwan Sub-Division, PHE Dte. (Mouza- Jubila) | 504/BSD | 21/03/2023 | 45 | JYOTI ENTERPRISE | 3.5 | 2.76 | 100 | 100
2203 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | New service connection charges for Sagrai W/S Scheme TW-3 | BP-2023-24-27 | 22/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.31 | 0 | 0 | 0
2204 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of SAGRAI(Part-B)[KHANDAGHOSH] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3898/CMD | 18/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 24.41 | 11.98 | 49.08 | 40
2205 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | Illumination arrangement & different electro-mechanical works at SAGRAI water supply scheme under KHANDAGHOSH Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2800/CMD | 01/10/2024 | 60 | CHOUDHURY ENTERPRISE | 14.29 | 0 | 0 | 0
2206 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of SAGRAI W/S Scheme (2ND TW SITE) under Khandaghosh Block within Burdwan Sub-Division, PHE Dte. [For 01 No. Tube well]. | 2688/BWD | 08/06/2023 | 30 | NATIONAL CONSTRUCTION | 13.23 | 10.23 | 100 | 100
2207 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | Designing, Making and Erection of Sign Board for SAJAL GRAM in Sagrai Village, Khandaghosh Block within Sagrai PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 830/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0.72 | 100 | 100
2208 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | Repairing damaged concrete road by cement concrete (mix 1:1.5:3) for FHTC work for SAGRAI Piped W/S. Scheme and its adj. mouzas within Khandaghosh Block under Burdwan Division PHE Dte. | 895/BWD | 01/03/2024 | 30 | SK KHAIRUL ISLAM | 8.78 | 8.71 | 100 | 100
2209 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | Laying of Rising main in between 3rd Tube Wells to 125 mm dia distribution pipe line at Chatimpur village for SAGRAI Pipe Water Supply scheme in Khandaghosh Block under Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. | 516/BSD | 13/03/2024 | 30 | SHANKHA GHOSH | 0.97 | 0.91 | 100 | 100
2210 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | Restore of Pipeline damaded by construction of drain by Zilla Parishad near Jobila Muslimpara under SAGRAI Piped Water Supply Scheme, Block- Khandaghosh within Burdwan Sub Division under Burdwan Division PHE Dte | 278/BSD | 09/02/2024 | 30 | SHUBHRA KANTI GHOSH | 0.96 | 0.4 | 34.5 | 100
2211 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | Restore of Pipeline damaged by construction of drain by Zilla Parishad near Jobila Sarkarpara under SAGRAI Piped Water Supply Scheme, Block- Khandaghosh within Burdwan Sub Division under Burdwan Division PHE Dte | 531/BSD | 14/03/2024 | 30 | SHUBHRA KANTI GHOSH | 0.96 | 0.58 | 100 | 100
2212 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | Restore of Pipeline damaded by construction of drain by Zilla Parishad near Jobila F.P.School & Peer Tala & Chatimpur under SAGRAI Piped Water Supply Scheme, Block- Khandaghosh within Burdwan Sub Division under Burdwan Division PHE Dte. | 534/BSD | 14/03/2024 | 30 | SHUBHRA KANTI GHOSH | 0.94 | 0 | 0 | 100
2213 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | Shifting of pipeline of 160mm & 90mm HDPE pipeline for Irrigation canel crossing and special maintenance for FHTC work for Sagrai & Khandaghosh Piped Water Supply Scheme within Khandaghosh block under Burdwan Division, PHE Dte. | 1008/BSD | 06/06/2024 | 30 | SHUBHRA KANTI GHOSH | 0.86 | 0.86 | 100 | 100
2214 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | Quotation for new service connection for Sagrai PWSS TW-4. | BP-2024-25-135 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.68 | 0 | 0 | 0
2215 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | Beautification of PWSS with Arboriculture, Recharge Pit including shaft and anciliary works at SAGRAI (Khandaghosh Block) P.W.S.S under Burdwan Division, PHE Dte. | 282/RWS | 03/09/2024 | 120 | ALOKA CONSTRUCTION | 0.97 | 0 | 0 | 100
2216 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRAI PWSS (PART B) , SM/16774 | Augmentation | Replacement of Tube-well & Rising main at HEAD TW SITE, 2ND TW site, 3rd TW site for Khandaghosh PWSS, HEAD TW SITE for Sagrai PWSS, HEAD TW SITE for SANKARI Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman. | 3077/BWD | 09/08/2024 | 311 | ANIRUDDHA FARUQUE | 80.21 | 53.83 | 88.87 | 100
2217 | PURBA BARDHAMAN | Central Mechanical | AMADPUR PIPED WATER SUPPLY SCHEME , SM/18146 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for new Tube well no.- 1 & 2 of AMADPUR[MEMARI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4511/CMD | 06/10/2023 | 30 | AMUSAR IMPEX PVT. LTD. | 25.2 | 0 | 0 | 0
2218 | PURBA BARDHAMAN | Central Mechanical | AMADPUR PIPED WATER SUPPLY SCHEME , SM/18146 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
2219 | PURBA BARDHAMAN | Central Mechanical | AMADPUR PIPED WATER SUPPLY SCHEME , SM/18146 | New | New service connection for Amadpur W/S Scheme. | BP-2023-24-383 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.47 | 0 | 0 | 0
2220 | PURBA BARDHAMAN | Central Mechanical | AMADPUR PIPED WATER SUPPLY SCHEME , SM/18146 | New | New service connection for Amadpur W/S Scheme. | BP-2023-24-382 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.69 | 0 | 0 | 0
2221 | PURBA BARDHAMAN | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME , SM/18313 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.77 | 0 | 0 | 0
2222 | PURBA BARDHAMAN | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME , SM/18313 | New | Material Requisition To Resource Division | 4297/BWD | 29/09/2023 | 0 | Resource Division | 1.83 | 0 | 0 | 0
2223 | PURBA BARDHAMAN | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME , SM/18313 | New | Material Requisition To Resource Division | 4445/BWD | 09/10/2023 | 0 | Resource Division | 14.51 | 0 | 0 | 0
2224 | PURBA BARDHAMAN | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME , SM/18313 | New | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. | 5324/BWD | 01/12/2023 | 120 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 21.53 | 100 | 100
2225 | PURBA BARDHAMAN | Burdwan Division | KHANO PIPED WATER SUPPLY SCHEME , SM/18313 | New | Material Requisition To Resource Division | 198/BWD | 10/01/2024 | 0 | Resource Division | 16.34 | 0 | 0 | 0
2226 | PURBA BARDHAMAN | Central Mechanical | KHANO PIPED WATER SUPPLY SCHEME , SM/18313 | New | New service connection charges for Khano PWSS Z-I TW-2 | BP-2024-25-323 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.9 | 0 | 0 | 0
2227 | PURBA BARDHAMAN | Central Mechanical | KHANO PIPED WATER SUPPLY SCHEME , SM/18313 | New | Quotation for new service connection for Khano PWSS PH 3. | BP-2024-25-110 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.74 | 0 | 0 | 0
2228 | PURBA BARDHAMAN | Durgapur W/S Division | KHANO PIPED WATER SUPPLY SCHEME , SM/18313 | New | Formal Work Order for Laying of Rising Main including Jack Pushing and construction of Pipe Carring Bridge with Pipe supporting structure under TAHERPUR and KHANO Piped Water Supply Scheme under Durgapur W/S Division, PHE Dte. | 1506/DWSD | 05/11/2024 | 236 | MANASH GHOSH | 1114.23 | 342.4 | 61.46 | 60
2229 | PURBA BARDHAMAN | Central Mechanical | KHANO PIPED WATER SUPPLY SCHEME , SM/18313 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Zone-1 & 2, T.W. No.- 1 & 2 at KHANO Water Supply Scheme [ BLOCK- Galsi-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3089/CMD | 10/12/2024 | 236 | M.S. ENTERPRISE | 50.29 | 0 | 0 | 24
2230 | PURBA BARDHAMAN | Durgapur W/S Division | KHANO PIPED WATER SUPPLY SCHEME , SM/18313 | New | Execution and payment of wayleave permission with railway services for crossing of portable water supply PWSSat Khano under Khano PWSS under DWSD,PHE Dte | 657/DWSD | 21/04/2025 | 195 | MANASH GHOSH | 7.09 | 5.26 | 74.21 | 71
2231 | PURBA BARDHAMAN | Central Mechanical | KHANO PIPED WATER SUPPLY SCHEME , SM/18313 | New | Supply, installation, commissioning of Electro-Mechanical and instrumentation components at newly constructed Boosting Station under Taherpur-khano sub surface water supply scheme under Central Mechanical Division PHE Dte. | 480/CMD | 06/02/2025 | 75 | GLACIER ENGINEERING CO | 105.71 | 0 | 0 | 0
2232 | PURBA BARDHAMAN | Durgapur W/S Division | KHANO PIPED WATER SUPPLY SCHEME , SM/18313 | New | Acceptance cum Formal Work Order for Design Engineering Services of Survey, General arrangement drawing, Pile foundation design and drawings, Pipe Pedestal and BOM, Structural design design and drawing, Fabrication drawings for 26 Numbers different dia meter pipe crossing Pipe Bridge at "PURANGAN (Zone-I, II, III), 11 Nos. Mouzas under PURSHA and UCHCHGRAM, SHILLA (Zone-I, II, III, IV), TAHER PUR (Zone-I, II, III) and KHANO (Zone-I and II) sites under Durgapur W/S Division,PHE Dte. | 1058/DWSD | 25/07/2024 | 270 | ASTER CONSULTANCY | 47.43 | 8.76 | 40.95 | 70
2233 | PURBA BARDHAMAN | Durgapur W/S Division | KHANO PIPED WATER SUPPLY SCHEME , SM/18313 | New | Acceptance cum Formal Work Order for Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method for Trial Bore at Khano under Sanko PWSS (JJM) District:- Purba-Bardhaman, under Durgapur W/S Division, PHE Dte , PHE Dte. | 1600/DWSD | 25/11/2024 | 20 | MEGHDOOT GHOSH | 5.6 | 0 | 0 | 80
2234 | PURBA BARDHAMAN | Central Mechanical | PASHALA PIPED WATER SUPPLY SCHEME , SM/15245 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PASHALA Water Supply Scheme [ Block-BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4071/CMD | 29/08/2023 | 30 | SOUNAK ENTERPRISE | 27.79 | 0 | 0 | 0
2235 | PURBA BARDHAMAN | Burdwan Division | PASHALA PIPED WATER SUPPLY SCHEME , SM/15245 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 0.33 | 0 | 0 | 0
2236 | PURBA BARDHAMAN | Burdwan Division | PASHALA PIPED WATER SUPPLY SCHEME , SM/15245 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.8 | 0 | 0 | 0
2237 | PURBA BARDHAMAN | Burdwan Division | PASHALA PIPED WATER SUPPLY SCHEME , SM/15245 | New | Material Requisition To Resource Division | 5242/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0 | 0
2238 | PURBA BARDHAMAN | Central Mechanical | PASHALA PIPED WATER SUPPLY SCHEME , SM/15245 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
2239 | PURBA BARDHAMAN | Central Mechanical | PASHALA PIPED WATER SUPPLY SCHEME , SM/15245 | New | NEW SERVICE CONNECTION FOR PASHALA PWSS | BP-2023-24-550 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.16 | 0 | 0 | 0
2240 | PURBA BARDHAMAN | Central Mechanical | PASHALA PIPED WATER SUPPLY SCHEME , SM/15245 | New | NEW SERVICE CONNECTION FOR PASHALA PWSS | BP-2023-24-549 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 14.97 | 0 | 0 | 0
2241 | PURBA BARDHAMAN | Burdwan Division | PASHALA PIPED WATER SUPPLY SCHEME , SM/15245 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NABASTA, PASHALA & POALKURA Piped Water Supply Scheme under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | 4652/BWD | 31/10/2023 | 898 | STARCO CONSTRUCTIONS | 900.17 | 9.61 | 6.19 | 2
2242 | PURBA BARDHAMAN | Burdwan Division | GUSUMBA PIPED WATER SUPPLY SCHEME , SM/18441 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.48 | 0 | 0 | 0
2243 | PURBA BARDHAMAN | Burdwan Division | GUSUMBA PIPED WATER SUPPLY SCHEME , SM/18441 | New | Material Requisition To Resource Division | 4306/BWD | 29/09/2023 | 0 | Resource Division | 72.67 | 0 | 0 | 0
2244 | PURBA BARDHAMAN | Central Mechanical | GUSUMBA PIPED WATER SUPPLY SCHEME , SM/18441 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at GUSUMBA Water Supply Scheme [ Block- KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4130/CMD | 29/08/2023 | 30 | S.P. CONSTRUCTION | 44.39 | 19.57 | 44.08 | 31
2245 | PURBA BARDHAMAN | Central Mechanical | GUSUMBA PIPED WATER SUPPLY SCHEME , SM/18441 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
2246 | PURBA BARDHAMAN | Burdwan Division | GUSUMBA PIPED WATER SUPPLY SCHEME , SM/18441 | New | Balance work of OHR, construction concrete Road, Functional Household Tap Connection, Construction of drain, Road restoration etc. for GOSUMBA PWSS, under KATWA-I Block under Katwa Sub-Division under Burdwan Division, PHE Dte. | 3622/BWD | 03/10/2024 | 90 | MA KANKALI ENTERPRISE | 67.86 | 0 | 0 | 0
2247 | PURBA BARDHAMAN | Central Mechanical | GUSUMBA PIPED WATER SUPPLY SCHEME , SM/18441 | New | Quotation for new service connection at Gusumba PWSS, PH-2. | BP-2024-25-251 | 01/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.55 | 0 | 0 | 0
2248 | PURBA BARDHAMAN | Central Mechanical | GUSUMBA PIPED WATER SUPPLY SCHEME , SM/18441 | New | NEW SERVICE CONNECTION FOR GUSUMBA PWSS TW -1. | BP-2023-24-638 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.88 | 0 | 0 | 0
2249 | PURBA BARDHAMAN | Central Mechanical | GUSUMBA PIPED WATER SUPPLY SCHEME , SM/18441 | New | NEW SERVICE CONNECTION FOR GUSUMBA PWSS TW-3 | BP-2024-25-60 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.93 | 0 | 0 | 0
2250 | PURBA BARDHAMAN | Burdwan Division | GUSUMBA PIPED WATER SUPPLY SCHEME , SM/18441 | New | GUSUMBA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3325/BWD | 02/08/2023 | 791 | NATIONAL CONSTRUCTION | 766.99 | 333.72 | 43.51 | 48
2251 | PURBA BARDHAMAN | Burdwan Division | BAGHTONA PIPED WATER SUPPLY SCHEME , SM/18334 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 1.33 | 0 | 0 | 0
2252 | PURBA BARDHAMAN | Burdwan Division | BAGHTONA PIPED WATER SUPPLY SCHEME , SM/18334 | New | Material Requisition To Resource Division | 3854/BWD | 01/09/2023 | 0 | Resource Division | 39.78 | 0 | 0 | 0
2253 | PURBA BARDHAMAN | Central Mechanical | BAGHTONA PIPED WATER SUPPLY SCHEME , SM/18334 | New | Additional Quotation for new service connection charges for Baghtona PWSS TW-1 | BP-2023-24-145 | 31/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.9 | 0 | 0 | 0
2254 | PURBA BARDHAMAN | Central Mechanical | BAGHTONA PIPED WATER SUPPLY SCHEME , SM/18334 | New | New service connection charges for Baghtona PWSS TW-1 | BP-2023-24-149 | 01/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.36 | 0 | 0 | 0
2255 | PURBA BARDHAMAN | Central Mechanical | BAGHTONA PIPED WATER SUPPLY SCHEME , SM/18334 | New | Additional quotation for Baghtona PWSS TW-1 | BP-2023-24-210 | 01/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0 | 0 | 0 | 0
2256 | PURBA BARDHAMAN | Burdwan Division | BAGHTONA PIPED WATER SUPPLY SCHEME , SM/18334 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAGHTONA, & KASIGRAM Piped Water Supply Scheme under Katwa ¿ I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3199/BWD | 24/07/2023 | 1257 | MANASH GHOSH | 1161.82 | 445.78 | 90.05 | 95
2257 | PURBA BARDHAMAN | Central Mechanical | BAGHTONA PIPED WATER SUPPLY SCHEME , SM/18334 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
2258 | PURBA BARDHAMAN | Burdwan Division | BAGHTONA PIPED WATER SUPPLY SCHEME , SM/18334 | New | Material Requisition To Resource Division | 4105/BWD | 25/11/2024 | 0 | Resource Division | 11.5 | 0 | 0 | 0
2259 | PURBA BARDHAMAN | Central Mechanical | BAGHTONA PIPED WATER SUPPLY SCHEME , SM/18334 | New | NEW SERVICE CONNECTION FOR BAGHTONA PWSS TW-2 | BP-2024-25-61 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.01 | 0 | 0 | 0
2260 | PURBA BARDHAMAN | Central Mechanical | BAGHTONA PIPED WATER SUPPLY SCHEME , SM/18334 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BAGHTONA Water Supply Scheme [ Block- KATWA-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3954/CMD | 24/08/2023 | 615 | SOUNAK ENTERPRISE | 28.48 | 2.12 | 8.33 | 44
2261 | PURBA BARDHAMAN | Burdwan Division | BAINCHI PIPED WATER SUPPLY SCHEME , SM/18335 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.1 | 0 | 0 | 0
2262 | PURBA BARDHAMAN | Burdwan Division | BAINCHI PIPED WATER SUPPLY SCHEME , SM/18335 | New | Material Requisition To Resource Division | 4030/BWD | 08/09/2023 | 0 | Resource Division | 46.22 | 0 | 0 | 0
2263 | PURBA BARDHAMAN | Central Mechanical | BAINCHI PIPED WATER SUPPLY SCHEME , SM/18335 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
2264 | PURBA BARDHAMAN | Central Mechanical | BAINCHI PIPED WATER SUPPLY SCHEME , SM/18335 | New | New service connection charges for Bainchi PWSS TW-2 | BP-2024-25-324 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.75 | 0 | 0 | 0
2265 | PURBA BARDHAMAN | Central Mechanical | BAINCHI PIPED WATER SUPPLY SCHEME , SM/18335 | New | New service connection charges for Bainchi PWSS TW-1 | BP-2024-25-325 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.89 | 0 | 0 | 0
2266 | PURBA BARDHAMAN | Burdwan Division | BAINCHI PIPED WATER SUPPLY SCHEME , SM/18335 | New | BAINCHI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3503/BWD | 10/08/2023 | 783 | MAA ENGINEERS CO. OPERATIVE & CONSTRUCTION SOCIETY LTD. | 521.7 | 110.59 | 21.2 | 75
2267 | PURBA BARDHAMAN | Central Mechanical | BAINCHI PIPED WATER SUPPLY SCHEME , SM/18335 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BAINCHI Water Supply Scheme [ Block- KATWA-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4148/CMD | 29/08/2023 | 740 | M/S, S.S. ENTERPRISE. | 30.35 | 0 | 0 | 88
2268 | PURBA BARDHAMAN | Central Mechanical | BAINCHI PIPED WATER SUPPLY SCHEME , SM/18335 | New | CONTINUATION ORDER-Hiring of inspection vehicle bearing no. WB41H5698 (Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Assistant Engineer, CMSD,P.H.E. Dte. [W.E.F-01/09/2025 TO 31/10/2025 ] | 1166/CMSD | 25/08/2025 | 61 | SUBRATA BHADRA | 0.81 | 0 | 0 | 0
2269 | PURBA BARDHAMAN | Burdwan Division | BAHADURPUR PIPED WATER SUPPLY SCHEME , SM/13504 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 0.44 | 0 | 0 | 0
2270 | PURBA BARDHAMAN | Burdwan Division | BAHADURPUR PIPED WATER SUPPLY SCHEME , SM/13504 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.54 | 0 | 0 | 0
2271 | PURBA BARDHAMAN | Burdwan Division | BAHADURPUR PIPED WATER SUPPLY SCHEME , SM/13504 | New | Material Requisition To Resource Division | 4916/BWD | 10/11/2023 | 0 | Resource Division | 30.36 | 0 | 0 | 0
2272 | PURBA BARDHAMAN | Central Mechanical | BAHADURPUR PIPED WATER SUPPLY SCHEME , SM/13504 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bahadurpur Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4176/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 28.59 | 22.35 | 78.16 | 96
2273 | PURBA BARDHAMAN | Burdwan Division | BAHADURPUR PIPED WATER SUPPLY SCHEME , SM/13504 | New | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | 995/DSD | 29/12/2023 | 183 | SUJAUDDIN SEKH | 2 | 0.19 | 48.44 | 60
2274 | PURBA BARDHAMAN | Burdwan Division | BAHADURPUR PIPED WATER SUPPLY SCHEME , SM/13504 | New | BAHADURPUR Piped Water Supply Scheme with sinking of Tube-well, LDS,Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3455/BWD | 08/08/2023 | 180 | KOUSIK MALLICK | 190.29 | 190.08 | 100 | 95
2275 | PURBA BARDHAMAN | Central Mechanical | BAHADURPUR PIPED WATER SUPPLY SCHEME , SM/13504 | New | NEW SERVICE CONNECTION FOR BAHADURPUR PWSS | BP-2023-24-533 | 13/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.83 | 0 | 0 | 0
2276 | PURBA BARDHAMAN | Central Mechanical | BAHADURPUR PIPED WATER SUPPLY SCHEME , SM/13504 | New | New service connection for Bahadurpur PWSS | BP-2023-24-529 | 13/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.96 | 0 | 0 | 0
2277 | PURBA BARDHAMAN | Durgapur W/S Division | BAHADURPUR PIPED WATER SUPPLY SCHEME , SM/13504 | New | ACCEPTANCE CUM FORMAL WORK ORDER FOR Additional work for laying of Extension or Laying of parallel pipeline, Providing FHTC, Road Restoration work, Land development under Bahadurpur PWSS in Ausgram -II Block under Durgapur Water Supply Division, PHE Dte. | 08/DWSD | 02/01/2025 | 60 | KOUSIK MALLICK | 31.92 | 0 | 0 | 100
2278 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RAINA (PART-B) PWSS TO ACCOMODATE FHTC IN RAINA-I BLOCK WITH IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE. , SM/19113 | Augmentation | Repairing and restore pipe line dammaged by laying of pipeline at different location of Augmentation of RAINA and its adjoining mouza's Piped W/S Scheme at Raina-I Block within Burdwan Sub Division under Burdwan Division, P.H.E. Dte | 118/BSD | 18/01/2024 | 30 | POMPA CONSTRUCTION CO. | 0.94 | 0.94 | 100 | 100
2279 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RAINA (PART-B) PWSS TO ACCOMODATE FHTC IN RAINA-I BLOCK WITH IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE. , SM/19113 | Augmentation | Restoration of village road damaged by laying pipeline at Nandipara Kalitala,Ranapara and Raina Co-Operative Society of Augmentation of Raina Water Supply Scheme at Raina-I Block within under Burdwan Division,PHE Dte | 117/BSD | 18/01/2024 | 15 | SOUMYAVASH DAS | 0.92 | 0.91 | 100 | 100
2280 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RAINA (PART-B) PWSS TO ACCOMODATE FHTC IN RAINA-I BLOCK WITH IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE. , SM/19113 | Augmentation | Construction of boundary wall (128.40 Mtr.) including switch room at 3rd tube well site (New) of Aug. of RAINA and its adj. mouzas Piped W/S. Scheme under Budwan Division, PHE. Dte. | 2398/BWD | 26/06/2024 | 370 | RANADHIR SINHA | 19.41 | 0 | 0 | 82
2281 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED RAINA (PART-B) PWSS TO ACCOMODATE FHTC IN RAINA-I BLOCK WITH IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE. , SM/19113 | Augmentation | Balance work OHR Connection, Platform, Laying Parallel Pipeline, providing FHTC, Construction of Boundary Wall, Drain & Pathway at Head Work site & Repairing of Pump House at Head Work site & 2nd Tube Well Site for AUGMENTATION OF RAINA PIPED WATER SUPPLY SCHEME, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | 2268/BWD | 18/06/2024 | 378 | RANADHIR SINHA | 96.75 | 0 | 0 | 65
2282 | PURBA BARDHAMAN | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block , SM/18679 | New | Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-I under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.03.2024 to 31.08.2024 (6 Months)(Sl-03) | 269/DWSD | 29/02/2024 | 184 | BIPLAB BANERJEE | 0.82 | 2.4 | 291.06 | 0
2283 | PURBA BARDHAMAN | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block , SM/18679 | New | Acceptance cum Formal Work Order for the work of Sinking of 3 nos 300 x 200 mm dia T/W 150 mtr and 20Nos 200 x 200 mm dia Riverbank T/W 51 mtr with Construction of P/H cum switch room chlorine room at Uchagram under 11 nos mouzas PWSS (JJM), Block:- Galsi-I, Dist- Purba Bardhaman. | 373/DWSD | 15/03/2024 | 785 | S & P ENTERPRISE | 72.51 | 34.25 | 47.23 | 50
2284 | PURBA BARDHAMAN | Burdwan Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block , SM/18679 | New | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. | 5324/BWD | 01/12/2023 | 120 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 15.87 | 100 | 100
2285 | PURBA BARDHAMAN | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block , SM/18679 | New | Formal Work Order for Laying of Rising Main including Jack Pushing and construction of Pipe carring Bridge with Pipe supporting structure under PURANGRAM and 11 nos Mouzas Piped Water Supply Scheme under Durgapur W/S Division, PHE Dte. | 1503/DWSD | 05/11/2024 | 120 | MANASH GHOSH | 1075.24 | 58.36 | 5.43 | 50
2286 | PURBA BARDHAMAN | Central Mechanical | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block , SM/18679 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Zone- Pursa, Uchchagram &, Rampur at 11 nos. Mouja Water Supply Scheme [ BLOCK- Galsi-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3100/CMD | 11/12/2024 | 60 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 37.78 | 0 | 0 | 0
2287 | PURBA BARDHAMAN | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block , SM/18679 | New | Continuation order for Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-I under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.09.2024 to 28.02.2025 (6 Months)(Sl-03) | 1250/DWSD | 30/08/2024 | 182 | BIPLAB BANERJEE | 0.82 | 2.39 | 290.47 | 0
2288 | PURBA BARDHAMAN | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block , SM/18679 | New | Formal Work Order for Additional work of Soil investigation & construction of CWR/Pump House etc, Land development of H/W Site,drain & internal Path Way, Concrete Road Restoration,FHTC with Platform with necessary allied Works of Sub Surface Based PURANGAN Pipe W/S Scheme (JJM) under Galsi - I Block, Dist - Purba- Bardhaman ,under Durgapur Water Supply Division, PHE Dte. | 1521/DWSD | 11/11/2024 | 360 | MANASH GHOSH | 789.87 | 0 | 0 | 75
2289 | PURBA BARDHAMAN | Central Mechanical | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block , SM/18679 | New | Supply, installation, commissioning of Electro-Mechanical and instrumentation components at newly constructed Boosting Station under Purangan & 11 nos. Mouza water supply scheme under Central Mechanical Division PHE Dte. | 479/CMD | 06/02/2025 | 75 | S.P. CONSTRUCTION | 135.24 | 0 | 0 | 0
2290 | PURBA BARDHAMAN | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block , SM/18679 | New | Continuation order for Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-I under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.06.2025 to 31.08.2025. | 852/DWSD | 29/05/2025 | 90 | BIPLAB BANERJEE | 0.41 | 0.4 | 96.75 | 35
2291 | PURBA BARDHAMAN | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block , SM/18679 | New | Continuation order for Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-I under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.03.2025 to 31.05.2025. | 334/DWSD | 27/02/2025 | 89 | BIPLAB BANERJEE | 0.41 | 1.2 | 290.92 | 35
2292 | PURBA BARDHAMAN | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block , SM/18679 | New | Laying HDPE pipe with Auger boring Construction of Valve Chamber and Remaining Road Restoration of CHHORA PWSS, Ausgram-II Block of under Durgapur Water Supply Division, PHE Dte. (Sl-03) | 1385/DWSD | 26/08/2025 | 10 | SIDDHARTH ENTERPRISE | 0.97 | 0 | 0 | 100
2293 | PURBA BARDHAMAN | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block , SM/18679 | New | Hiring of Diesel Ambassador car BS_IV /Luxury taxi catalytic converter attachment (Euro-4)/Bolero/Scorpio having contract carriage permit from Regional Transport Authority for the use of the JJM under the office of the Executive Engineer,Durgapur water supply division PHE. Dte. at Fagupur , Nababhat,Purba Bardhhaman on daily basis (as and when required including Govt. holidays) period of 01.09.2025 to 28.02.2026 (181 days) (Sl-02) | 1380/DWSD | 26/08/2025 | 181 | PRAMIT CHATTERJEE | 0.86 | 0 | 0 | 0
2294 | PURBA BARDHAMAN | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block , SM/18679 | New | Acceptance cum Formal Work Order for Design Engineering Services of Survey, General arrangement drawing, Pile foundation design and drawings, Pipe Pedestal and BOM, Structural design design and drawing, Fabrication drawings for 26 Numbers different dia meter pipe crossing Pipe Bridge at "PURANGAN (Zone-I, II, III), 11 Nos. Mouzas under PURSHA and UCHCHGRAM, SHILLA (Zone-I, II, III, IV), TAHER PUR (Zone-I, II, III) and KHANO (Zone-I and II) sites under Durgapur W/S Division,PHE Dte. | 1058/DWSD | 25/07/2024 | 270 | ASTER CONSULTANCY | 47.43 | 17.52 | 50 | 70
2295 | PURBA BARDHAMAN | Durgapur W/S Division | Sub-Surface Water based Piped Water Supply Scheme for 11 nos. Mouzas under Galsi-I Block , SM/18679 | New | Continuation order for the work of Computer routine maintenance and software's installation including supply of computer peripherals and Stationeries etc. for use office under DWSD, PHE Dte (w.e.f 01.06.2024 to 30.05.2025) | 575/DWSD | 22/04/2024 | 365 | JOY GURU ENTERPRISE | 3.79 | 0 | 0 | 100
2296 | PURBA BARDHAMAN | Burdwan Division | KHANDRA PIPED WATER SUPPLY SCHEME , SM/18505 | New | Material Requisition To Resource Division | 4894/BWD | 10/11/2023 | 0 | Resource Division | 36.98 | 0 | 0 | 0
2297 | PURBA BARDHAMAN | Burdwan Division | KHANDRA PIPED WATER SUPPLY SCHEME , SM/18505 | New | Material Requisition To Resource Division | 4292/BWD | 29/09/2023 | 0 | Resource Division | 68.65 | 0 | 0 | 0
2298 | PURBA BARDHAMAN | Burdwan Division | KHANDRA PIPED WATER SUPPLY SCHEME , SM/18505 | New | Material Requisition To Resource Division | 322/BWD | 24/01/2024 | 0 | Resource Division | 42.03 | 0 | 0 | 0
2299 | PURBA BARDHAMAN | Burdwan Division | KHANDRA PIPED WATER SUPPLY SCHEME , SM/18505 | New | Material Requisition To Resource Division | 205/BWD | 10/01/2024 | 0 | Resource Division | 19.71 | 0 | 0 | 0
2300 | PURBA BARDHAMAN | Central Mechanical | KHANDRA PIPED WATER SUPPLY SCHEME , SM/18505 | New | New Service connection at KHANDRA PWSS TW-1. | BP-2023-24-486 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0 | 0
2301 | PURBA BARDHAMAN | Central Mechanical | KHANDRA PIPED WATER SUPPLY SCHEME , SM/18505 | New | New Service connection at KHANDRA PWSS TW-2. | BP-2023-24-487 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.6 | 0 | 0 | 0
2302 | PURBA BARDHAMAN | Central Mechanical | KHANDRA PIPED WATER SUPPLY SCHEME , SM/18505 | New | New service connection for Khandra PH-3 PWSS. | BP-2024-25-26 | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.24 | 0 | 0 | 0
2303 | PURBA BARDHAMAN | Central Mechanical | KHANDRA PIPED WATER SUPPLY SCHEME , SM/18505 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KHANDRA Water Supply Scheme [ Block-MONTESWAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4184/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 44.74 | 0 | 0 | 33
2304 | PURBA BARDHAMAN | Central Mechanical | KHANDRA PIPED WATER SUPPLY SCHEME , SM/18505 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
2305 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme , SM/07202 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur (Pt-B) village of Khetpur Palasi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-165/BWD/2020-21) | 2605/BWD | 04/08/2020 | 30 | SANTANU BHATTACHARYAY | 4.92 | 9.84 | 200 | 1
2306 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme , SM/07202 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur (Pt.-A) village of Khetpur Palasi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-183/BWD/2020-21) | 2601/BWD | 04/08/2020 | 30 | CHANCHAL PAL | 4.92 | 9.84 | 200 | 1
2307 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme , SM/07202 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur Palashi (Pt-B) village of Khetpur Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-463/BWD/2020-21) | 242/KTS | 01/10/2020 | 4 | SANTANU BHATTACHARYAY | 1.21 | 2.4 | 200 | 1
2308 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme , SM/07202 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur (Pt-A) village of Khetpur-Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-257/BWD/2020-21) | 3528-A/BWD | 25/09/2020 | 30 | CHANCHAL PAL | 2.81 | 5.61 | 200 | 1
2309 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme , SM/07202 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur village of Khetpur Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. | 366/KTS | 15/12/2020 | 7 | TAPAS KUMAR ROY | 2.82 | 5.61 | 200 | 1
2310 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme , SM/07202 | Retrofitting | Construction of sluice valve chamber (80 mm dia S/V) of Khetpur Palashi piped water supply scheme under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No.-01] | 14/KTS | 08/01/2021 | 3 | CHANCHAL PAL | 0.41 | 0.82 | 200 | 1
2311 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme , SM/07202 | Retrofitting | Providing Functional Household Tap Connection from existing distribution system within the command area of Kshetpur Palashi PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-1] | 126/KTS | 21/02/2022 | 30 | SANTANU BHATTACHARYAY | 3.19 | 3.16 | 100 | 1
2312 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme , SM/07202 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H/3668) for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. for the month of July & August'2022. | 612/VEH/22-23 | 23/09/2022 | 0 | MD HASIN | 0.56 | 0 | 0 | 0
2313 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme , SM/07202 | Retrofitting | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] | 4318/BWD | 04/11/2020 | 10 | MD HASIN | 4.93 | 0.42 | 100 | 1
2314 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme , SM/07202 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of January'23. | 1118/JJM | 27/02/2023 | 0 | M/S MUNMUN DEY | 0.26 | 0 | 0 | 0
2315 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme , SM/07202 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur Palashi (Part-A) village of Khetpur Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. (Tr No.-471/BWD/2020-21) | 241/KTS | 01/10/2020 | 4 | CHANCHAL PAL | 1.19 | 2.33 | 200 | 1
2316 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme , SM/07202 | Retrofitting | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme AGRADWIP, KHETPUR PALASHI, SAHAPUR PWSS (Sl No-1) | 393/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 3.71 | 1.24 | 100 | 100
2317 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Kshetpur Palashi Piped Water Supply Scheme , SM/07202 | Retrofitting | Providing of balance FHTC and other allied works at different location under the command area of Kshetpur Palasi PWSS (SM/07202) in order to declare Sajal Gram, Block - Katwa-II Block under Katwa Sub-Division, PHE Dte. (Sl No-3) | 459/KTS | 17/03/2025 | 21 | DULU MIDDA | 4.81 | 0 | 0 | 100
2318 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Amarpur (Amarpur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 572/BWD of 2020-2021) | 439/BWD | 19/01/2021 | 60 | M/S ANAND CONSTRUCTION | 16.46 | 0 | 0 | 1
2319 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Reshalatpur village and Reshalatpur habitation of SIALI piped water supply scheme within Burdwan Sub-Division, under Burdwan Division, PHE Dte.[Phase-I] | 3321/BWD | 18/09/2020 | 30 | MUKHERJEE ENTERPRISE | 4.84 | 0.17 | 100 | 1
2320 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Mudipur (Part), Rasalatpur (Part) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. | 58/BWD | 05/01/2022 | 30 | BOSE ENTERPRISE | 18.34 | 16.99 | 100 | 1
2321 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Siali (Math Siali & Siali Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte._2ND CALL. | 1709/BWD | 25/02/2021 | 30 | SKILLS AND FACILITY TRAINING INSTITUTE | 18.33 | 17.48 | 100 | 1
2322 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Ujirpur (Par Ujirpur & Ujirpur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte._2ND CALL. | 1546/BWD | 22/02/2021 | 30 | SKILLS AND FACILITY TRAINING INSTITUTE | 18.87 | 18.01 | 100 | 1
2323 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Reshalatpur village and Reslatpur habitation of Siali piped water supply scheme under Burdwan Division, PHE Dte.[Phase-I] | 7089/BWD | 22/12/2021 | 30 | MUKHERJEE ENTERPRISE | 3.45 | 3.11 | 100 | 1
2324 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SIALI Piped Water Supply Scheme at Kora (Kora Habitation), Mudipur (Part) (Mudipur (Part) Habitation) & Reshalatpur (Part) (Reshalatpur (Part) Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. | 649/BWD | 27/01/2021 | 60 | DHIRENDRANATH SOM | 19.53 | 0 | 0 | 1
2325 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Re-alignment of damaged distribution pipeline at different section due to road widening (PWD Deptt.) of SIALI piped water supply scheme at Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-G] | 667/BSD | 08/06/2021 | 30 | RAINBOW CONSTRUCTION | 4.7 | 0 | 0 | 1
2326 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Extension of uPVC distribution pipe line (Node-128 & 136) in regarding FHTC at Par-Ujirpur village from Sura (Zone-II) water supply scheme within Siali W/S scheme at Jamalpur Development Block. under Burdwan Division, PHE Dte. Gr.B. | 370/BSD | 02/03/2022 | 30 | BHARAT CONSTRUCTION | 3.36 | 2.78 | 100 | 1
2327 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Extension of pipeline from existing distribution system within the command area of Siali piped water supply scheme at Siali (Math Siali & Siali Habitation) village mouza under Jamalpur Block under Burdwan Division, PHE Dte. [Gr.-E] | 957/BSD | 23/07/2021 | 30 | ELECTRONIC SURVILLANCE | 3.22 | 2.81 | 100 | 1
2328 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Extension of pipeline for providing functional household tap connection at Reshalatpur (Part) of Siali piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Gr.-C] | 1142/BSD | 26/08/2021 | 30 | DHIRENDRANATH SOM | 2.49 | 0 | 0 | 1
2329 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Extension of pipeline for Providing Functional Household tap connection at Siali Habitation of SIALI Piped Water Supply Scheme under Burdwan Division, P.H.E.Dte. [Group : D] | 243/AE/HQ | 20/04/2022 | 30 | BOSE ENTERPRISE | 3.1 | 2.92 | 100 | 1
2330 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Extension of pipeline from existing distribution system within the command area of Siali piped water supply scheme for FHTC at Ujirpur (Par Ujirpur & Ujirpur Habitation) village mouza under Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-F] | 958/BSD | 23/07/2021 | 30 | ELECTRONIC SURVILLANCE | 4.3 | 3.88 | 100 | 1
2331 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Extension of pipeline (Branch & Sub Branch) from existing distribution system within the command area of Siali piped water supply scheme for FHTC at Mudipur village and Mudipur habitation within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-I] | 1030/BSD | 05/08/2021 | 30 | ELECTRONIC SURVILLANCE | 2.16 | 2.14 | 100 | 1
2332 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Extension of HDPE pipeline for Providing Functional Household Tap Connection at Amarpur Habitation of SIALI Piped Water Supply Scheme under Burdwan Division,P.H.E.Dte. [Group : E] | 244/AE/HQ | 20/04/2022 | 30 | BOSE ENTERPRISE | 4.11 | 4.1 | 100 | 1
2333 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Extension of pipeline for providing functional house hold tap connection at Kora (Part) village of Siali piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Gr.-A] | 1643/BSD | 14/12/2021 | 30 | MUKHERJEE ENTERPRISE | 1.73 | 1.58 | 100 | 1
2334 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SIALI Piped Water Supply Scheme at Jamalpur Block , SM/07856 | Retrofitting | Providing FHTC for 100% coverage at Muidipur, Ujirpur, Reshalatpur, Kora, Siali & Amarpur Habitation (Village) for SIALI piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 3033/BWD | 14/07/2023 | 264 | ANWESHA CONSTRUCTION | 31.38 | 20.71 | 84.75 | 100
2335 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Rahatpur Piped Water Supply Scheme , SM/07555 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Rahatpur village and Rahatpur Habitation of Rahatpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-491/BWD/2020-21) | 4116/BWD | 16/10/2020 | 30 | DUBE ENTERPRISE | 4.87 | 9.73 | 200 | 1
2336 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Rahatpur Piped Water Supply Scheme , SM/07555 | Retrofitting | Extension of 63 mm dia UPVC pipeline to provide house connection to the beneficiaries of Rahatpur water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Sl No.-B] | 139/KSD | 12/02/2021 | 30 | DUBE ENTERPRISE | 4.49 | 4.57 | 100 | 1
2337 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Rahatpur Piped Water Supply Scheme , SM/07555 | Retrofitting | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Rahatpur village and Rahatpur habitation of Rahatpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Gr.-7A] | 4913./BWD | 08/12/2020 | 30 | DUBE ENTERPRISE | 4.31 | 4.31 | 50 | 1
2338 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme , SM/07556 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Banki village and Banki Habitation of Bamangaria piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | 4123/BWD | 16/10/2020 | 30 | GOUTAM KUMAR MITRA | 4.86 | 9.38 | 192.86 | 1
2339 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme , SM/07556 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Banki village and Banki habitation of Bamungoria Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿10B¿] | 4543/BWD | 06/09/2021 | 30 | GOUTAM KUMAR MITRA | 0.97 | 0.97 | 100 | 1
2340 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme , SM/07556 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bamangaria village and Bamangaria habitation of Bamangaria piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-536/BWD/2020-21) | 4122/BWD | 16/10/2020 | 30 | PAL CONSTRUCTION | 4.86 | 9.71 | 200 | 1
2341 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme , SM/07556 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bamangaria village and Bamungoria habitation of Bamungoria Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿10A¿] | 151/BWD | 08/01/2021 | 30 | PAL CONSTRUCTION | 1.73 | 1.73 | 100 | 1
2342 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme , SM/07556 | Retrofitting | Extension of different dia UPVC pipeline to provide house connections to the different leftout areas in the command area of Bamungaria W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | 07/KSD Dt-04.01.2022 | 04/01/2022 | 31 | PAL CONSTRUCTION | 2.52 | 1.61 | 100 | 1
2343 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme , SM/07556 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of March to September'2022. | 866/VEH | 09/12/2022 | 0 | PARTHA PRATIM ACHARYA | 2.79 | 0 | 0 | 0
2344 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme , SM/07556 | Retrofitting | Hire & fuel charges of vehicle (Car No.-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of October & November'2022. | 956/JJM/22-23 | 13/01/2023 | 0 | PARTHA PRATIM ACHARYA | 0.77 | 0 | 0 | 0
2345 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme , SM/07556 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhaturia village (Bhaturia habitation) of Bamungoria Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part-A). [SL. No. : 22] | 1461/BWD | 18/02/2021 | 15 | ABDUL HAI | 4.86 | 9.73 | 200 | 0
2346 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme , SM/07556 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bhaturia village (Bhaturia habitation) of Bamungoria Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part-B). [SL. No. : 23] | 1460/BWD | 18/02/2021 | 15 | SANTANU BHATTACHARYAY | 4.86 | 9.73 | 200 | 0
2347 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme , SM/07556 | Retrofitting | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 14 Nos. Piped W/S. Schemes under Purbasthali I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3017/BWD | 05/08/2024 | 75 | HORIZEN | 38 | 13.52 | 100 | 100
2348 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bamangaria Piped Water Supply Scheme , SM/07556 | Retrofitting | Different Types of work involved in connection with Augmentation of SONARUDRA (SM/16349) & KACHUA (SM/13497) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2430/BWD | 27/06/2024 | 480 | R.G. INFRASTRUCTURE | 240.7 | 0 | 0 | 2
2349 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahishgaria Piped Water Supply Scheme at Jamalpur Block , SM/07799 | Retrofitting | Extension of pipeline including leftout Functional Household Tap Connection (FHTC) for Mahishgoria Piped Water Supply Scheme at Mahishgoria, Bidyabatipur, Narayanpur village in Jamalpur Block under Burdwan Division, PHE Dte. GROUP : D | 427/AE/HQ | 03/08/2022 | 30 | A R TRADERS | 4.91 | 4.91 | 100 | 1
2350 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Mahishgaria Piped Water Supply Scheme at Jamalpur Block , SM/07799 | Retrofitting | Providing FHTC for 100% coverage at Baidyabatipur, Tilkuria, Mahishgaria, Narayanpur & Mathurapur village (Mouza) for MAHISHGARIA Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 2259/BWD | 18/05/2023 | 30 | MUKHERJEE ENTERPRISE | 11.92 | 11.75 | 100 | 100
2351 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jhaudanga Piped Water Supply Scheme at Purbasthali-II Block , SM/07805 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jhaudanga & Sarisha village and North Jhaudwnga (Part) & Sarisha habitation of Jhaudanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-554/BWD/2020-21) | 4114/BWD | 16/10/2020 | 30 | BARABELUN NO.-II G.P. UNEMPLOYED CO-OP LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.86 | 9.72 | 200 | 1
2352 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jhaudanga Piped Water Supply Scheme at Purbasthali-II Block , SM/07805 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jhaudanga village and North Jhaudanga (Part) habitation of Jhaudanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-761/BWD/2020-21) | 4113/BWD | 16/10/2020 | 30 | BARDHAMAN AQUA ENGINEERING | 4.86 | 9.72 | 200 | 1
2353 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jhaudanga Piped Water Supply Scheme at Purbasthali-II Block , SM/07805 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jhaudanga village and North Jhaudanga (Part) habitation of Jhaudanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-762/BWD/2020-21) | 4795/BWD | 03/12/2020 | 30 | BARDHAMAN AQUA ENGINEERING | 3.51 | 7.01 | 200 | 1
2354 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jhaudanga Piped Water Supply Scheme at Purbasthali-II Block , SM/07805 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jhaudanga village (Jhaudanga south habitation) of Jhaudanga piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-868/BWD/2020-21) | 597/BWD | 25/01/2021 | 15 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.86 | 9.72 | 200 | 1
2355 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jhaudanga Piped Water Supply Scheme at Purbasthali-II Block , SM/07805 | Retrofitting | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 09 Nos. Piped W/S. Schemes under Purbasthali II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3018/BWD | 05/08/2024 | 50 | HORIZEN | 23.7 | 7.42 | 100 | 10
2356 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jhaudanga Piped Water Supply Scheme at Purbasthali-II Block , SM/07805 | Retrofitting | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
2357 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block , SM/07830 | Retrofitting | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Radhakantapur High School Kantagorer Par [23 Nos],Total 23 Nos FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification) within Memari-I Block including leftout household water tap connection(FHTC)under Burdwan Division,PHE Dte. Gr.U | 1365/BSD | 04/08/2022 | 5 | D.M. ENTERPRISE | 0.97 | 0 | 0 | 1
2358 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block , SM/07830 | Retrofitting | Extension of pipeline for UTTAR RADHAKANTAPUR Piped water Supply Scheme at Harirambati[7 Nos],Kamalpur[4 Nos],Kole[5 Nos],Mallikapur[2 Nos],Sahanagar[5 Nos]Total 23 Nos FHTC Work for Sajal Gram(As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout household water tap connection(FHTC)under Burdwan Division,PHE Dte.Gr.D. | 1359/BSD | 03/08/2022 | 5 | D.M. ENTERPRISE | 0.96 | 0 | 0 | 1
2359 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block , SM/07830 | Retrofitting | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Radhakantapur Purbo Sansad Dule Para(23 Nos)Total 23 Nos FHTC Work for Sajal Gram(As per Field Verification Report for Har Ghar Jal Certification and praved for Prodhan of Gop Ganter-II G.P. within Memari-I Block including leftout household water tap connection(FHTC)under Burdwan Division,PHE Dte. Gr.V | 1366/BSD | 04/08/2022 | 5 | D.M. ENTERPRISE | 0.97 | 0 | 0 | 1
2360 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block , SM/07830 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Memari-I Block (Daluibazar-II, Gopegantar-I & II G.P.) under Burdwan Division, PHE. Dte. Dte._Part-A. | 209/BWD | 11/01/2022 | 30 | M/S ANAND CONSTRUCTION | 21.11 | 13.18 | 100 | 1
2361 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block , SM/07830 | Retrofitting | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Harirambati [7 No's], Kamalpur [4 No's], Kole [5 No's] Mallikapur [2 No's], Sahanagar [5 No's]Total 23 No's FHTC Work for Sajal Gram (As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | 1359-A/BSD | 03/08/2022 | 5 | D.M. ENTERPRISE | 0.96 | 0.96 | 100 | 1
2362 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block , SM/07830 | Retrofitting | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Radhakantapur High School Kantagorer Par [23 Nos] Total 23 No's FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | 1365-A/BSD | 04/08/2022 | 5 | D.M. ENTERPRISE | 0.97 | 0.97 | 100 | 1
2363 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block , SM/07830 | Retrofitting | Extension of pipeline for UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Radhakantapur Purbo Sansad Dule Para[23 No's] Total 23 No's FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | 1366-A/BSD | 04/08/2022 | 5 | D.M. ENTERPRISE | 0.97 | 0.97 | 100 | 1
2364 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block , SM/07830 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Kamalpur Village, Memari - I Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 862/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 100 | 100
2365 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block , SM/07830 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Balidanga Village, Memari - I Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 863/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 100 | 100
2366 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block , SM/07830 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Mallikpur Village, Memari - I Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 859/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 100 | 100
2367 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block , SM/07830 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Sahanagar Village, Memari - I Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 860/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 100 | 100
2368 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block , SM/07830 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Purba Shrirampur Village, Memari - II Block within Uttar Radhakantapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 837/AE/HQ | 31/10/2023 | 30 | MUNSHI JAVEDUR JAMAN | 0.76 | 0.72 | 100 | 100
2369 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block , SM/07830 | Retrofitting | Extension of PVC Water supply line at Koley village for UTTAR RADHAKANTAPUR and its adjoining mouza W/S Scheme Block:Memari-I within Burdwan Sub-Division,PHE Dte. | 120/BSD | 18/01/2024 | 30 | A R TRADERS | 0.92 | 0.8 | 100 | 98
2370 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Uttar Radhakantapur Piped Water Supply Scheme at Memari-II Block , SM/07830 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of UTTAR RADHAKANTAPUR Piped Water Supply Scheme at Uttar Radhakantapur, Patra, Katna etc village mouza, Memari-I Block under BURDWAN Division, P.H.E Dte. | 3763/BWD | 29/08/2023 | 760 | DEY NIRMAN | 13.95 | 10.83 | 91.21 | 100
2371 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block , SM/07815 | Retrofitting | Extension of UPVC distribution pipeline in connection with FHTC for Masagram (Zone-I) & adjoining mouzas water supply scheme at Jamalpur Development Block under Burdwan Division, PHE Dte.[Gr.-B] | 1112/BSD | 23/08/2021 | 45 | M/S ASHA CONSTRUCTION | 4.71 | 4.71 | 100 | 1
2372 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block , SM/07815 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Masagram Piped Water Supply Scheme at Habaspur Village, Chouberia Village, Ballabhbati Village & Masagram (4 Nos. habitations), Jamalpur Block under Burdwan Division, PHE Dte. (Agr. No. 710/BWD of 2020-2021) | 1578/BWD | 22/02/2021 | 60 | MD HASIN | 60.21 | 65.84 | 128.73 | 1
2373 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block , SM/07815 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Masagram Piped Water Supply Scheme at Dadpur Village, Sarangpur Village (2Nos. habitations) & Sanchra Village, Jamalpur Block under Burdwan Division, PHE Dte.(Agreement No. 753/BWD of 2020-2021) | 1599/BWD | 22/02/2021 | 60 | M/S ASHA CONSTRUCTION | 65 | 98.84 | 154.72 | 1
2374 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block , SM/07815 | Retrofitting | Construction of Boundary Wall at 2nd T/W Site of Masagram Zone-I Water Supply Scheme under Jamalpur Block of Burdwan Division, PHE Dte (Length-50.0 Mtr,Col-17 Nos). Gr.E. | 201/BSD | 01/02/2022 | 45 | SANDIPAN SENGUPTA | 3.12 | 0 | 0 | 1
2375 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block , SM/07815 | Retrofitting | Extension of UPVC distribution pipeline in connection with FHTC for Masagram (Zone-II) and its adjoining mouzas water supply scheme at Jamalpur Development Block under Burdwan Division, PHE Dte. (Habaspur Habitation) [Gr.-A] | 1206/BSD | 09/09/2021 | 30 | MD HASIN | 4.85 | 4.84 | 100 | 1
2376 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block , SM/07815 | Retrofitting | Laying of 200mm.dia. HDPE Distribution pipe line (Node No.118 to 119) for Masagram (Zone-I) & adjoining mouzas Water Supply Scheme at Jamalpur Development block under Burdwan Division,PHE Dte. Group : C. | 830/BSD | 23/05/2022 | 30 | M/S ASHA CONSTRUCTION | 4.6 | 0 | 0 | 1
2377 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block , SM/07815 | Retrofitting | Extension of pipe linefor providing functional house hold tap connection at Sanchra habitation(Part)of MOSAGRAM ZONE-II Piped Water Supply Schemewithin Burdwan Sub-Divn under Burdwan Division,PHE Dte". Group : E. | 987/BSD | 16/06/2022 | 30 | MD HASIN | 2.51 | 2.51 | 100 | 1
2378 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block , SM/07815 | Retrofitting | Construction of Approach P.C.C Road & Circular Soak Well At Head works site of MASAGRAM Zone-II Piped W/S. Scheme at Jamalpur Dev. Block under Burdwan Division, PHE Dte._2ND CALL | 966/AE/HQ | 22/11/2024 | 30 | SOUMYAVASH DAS | 0.93 | 0 | 0 | 0
2379 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block , SM/07815 | Retrofitting | Re-laying of u-PVC Pipeline damaged by Irrigation department at Sanchra village of Masagram Zone-II Piped W/S Scheme at Jamalpur Development Block under Burdwan Division,PHE Dte | 127/BSD | 18/01/2024 | 30 | DHIRENDRANATH SOM | 0.85 | 0 | 0 | 0
2380 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block , SM/07815 | Retrofitting | Re-laying of UPVC Pipeline(Damaged by Irrigation Department)and repairing damaged FHTC at Masagram Mouza (Habitation) under Masagram Zone-I Piped Water Supply Scheme Jamalpur Development under Burdwan Division,PHE Dte. | 1007/BSD | 06/06/2023 | 15 | DEBASHISH ENTERPRISE | 0.85 | 0.83 | 100 | 100
2381 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Masagram Piped Water Supply Scheme at Jamalpur Block , SM/07815 | Retrofitting | Sinking of 300 mm X 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) with construction of Pump House, Boundary wall, Land Development and Rising main connection of MASAGRAM (Zone-II) Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman under Burdwan Division PHE Dte. [FOR 3rd. TUBE WELL SITE]. | 785/BWD | 27/02/2024 | 187 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 25.8 | 12.8 | 51.02 | 40
2382 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL , SM/09409 | Augmentation | Preparation of DPR for augmentation of Samudragarh W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-E) | 217/KSD | 24/02/2022 | 21 | M/S R. DUTTA & CO. | 2.8 | 2.78 | 100 | 1
2383 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL , SM/09409 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of SAMUDRAGARH Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte.SL. No. 10 | 144/AE/HQ | 16/03/2022 | 10 | MA SARADA ENTERPRISE | 4.52 | 4.52 | 100 | 1
2384 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL , SM/09409 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
2385 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL , SM/09409 | Augmentation | Additional works to implement the augmentation of SAMUDRAGARH Piped Water Supply Scheme under Purbasthali-I Block, Dist :- Purba Burdwan under Burdwan Division, PHE. Dte. | 1731/BWD | 13/04/2023 | 30 | AZAD CONSTRUCTION | 18.67 | 15.24 | 100 | 100
2386 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL , SM/09409 | Augmentation | Material Requisition To Resource Division | 930/BWD | 16/02/2022 | 0 | Resource Division | 22 | 0 | 0 | 0
2387 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL , SM/09409 | Augmentation | Material Requisition To Resource Division | 1531/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
2388 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL , SM/09409 | Augmentation | Material Requisition To Resource Division | 540/BWD | 27/01/2022 | 0 | Resource Division | 20.81 | 0 | 0 | 0
2389 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL , SM/09409 | Augmentation | Quotation charges of WBSEDCL of Aug. of Samudragarh PWSS. [Ref. ID-503495985] | 1087/JJM | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.42 | 0 | 0 | 0
2390 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL , SM/09409 | Augmentation | Augmentation of SAMUDRAGARH Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 450 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation including with construction of boundary wall at Head works site under Purbasthali I Block, District - Purba Bardhaman. | 1963/BWD | 12/04/2022 | 365 | AZAD ENTERPRISE | 426.18 | 262.64 | 61.63 | 80
2391 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL , SM/09409 | Augmentation | Quotation charges of WBSEDCL of Aug. of Samudragarh PWSS. [Ref. ID-503564676][TW-4] | 1366/JJM | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 7.35 | 0 | 0 | 0
2392 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION SAMUDRAGARH PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BLOCK PURBASTHALI-I PURBA BARDHAMAN WEST BENGAL , SM/09409 | Augmentation | Quotation from WBSEDCL for load enhancement of Augmentation of Samudragarh w/s scheme for P.H.-3 under Burdwan Division, PHE Dte. | 1825/JJM | 27/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.39 | 0 | 0 | 0
2393 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. , SM/08714 | Retrofitting | Additional extension UPVC distribution Pipeline in connection with FHTC work for Palsit Piped Water Supply Scheme at Khargram, Karanda, Palsit & Bhaita under Bardhaman- II Block under Burdwan Division, PHE Dte. | 6065/BWD | 07/10/2021 | 30 | BRINDABAN KONAR | 14.22 | 13.89 | 100 | 1
2394 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. , SM/08714 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H/3668) for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. for the month of July & August'2022. | 612/VEH/22-23 | 23/09/2022 | 0 | MD HASIN | 0.56 | 0 | 0 | 0
2395 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. , SM/08714 | Retrofitting | Construction of boundary wall including land development at 2nd Pump house of PALSIT within command area of PALSIT Piped W/S. Scheme under Burdwan Division, PHE. Dte. [Group : F] | 238/AE/HQ | 19/04/2022 | 30 | M/S F.S. ENTERPRISE | 0.96 | 0 | 0 | 1
2396 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. , SM/08714 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of PALSIT & its adjoining mouzas Piped Water Supply Scheme, Block - Burdwan - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 4886/BWD | 02/11/2022 | 30 | WESTERN WATER SUPPLY AGENCY | 10.04 | 10.04 | 100 | 100
2397 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. , SM/08714 | Retrofitting | Providing FHTC for 100% coverage in different village from existing distribution system within PALSIT PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | 1423/BWD | 24/03/2023 | 30 | BABUL SK | 28.53 | 27.27 | 100 | 100
2398 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. , SM/08714 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Palsit piped water supply scheme at Bhaita (11 Nos Habitation), Khargram (17 Nos. Habitation), Palsit (19 Nos. Habitation), Karanda (17 Nos. Habitation) & Paschim Chandipur village, Bardhaman-II Block under Burdwan Division, PHE Dte. | 5000/BWD | 10/12/2020 | 90 | BRINDABAN KONAR | 96.95 | 55.82 | 200 | 0
2399 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. , SM/08714 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for PALSIT its Adjoining Mouza W/S Scheme, Block -Bardhaman-II within Burdwan Sub-Division, PHE Dte. (Mouza- KARANA) | 498/BSD | 21/03/2023 | 45 | M/S PALASH BISWAS | 3.32 | 3.17 | 100 | 100
2400 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. , SM/08714 | Retrofitting | Providing parallel distribution system from Khargram more to Bhaita High School within PALSIT PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | 005/BWD | 02/01/2024 | 30 | TARAMA AGENCY | 20.68 | 18.8 | 100 | 100
2401 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. , SM/08714 | Retrofitting | Providing left out FHTC for 100% coverage in different village within PALSIT PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte | 1038/BSD | 10/06/2024 | 30 | M/S PALASH BISWAS | 0.95 | 0.94 | 100 | 100
2402 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. , SM/08714 | Retrofitting | Providing left out FHTC for 100% covarage in different village within PALSIT PWSS , Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | 995/BSD | 06/06/2024 | 30 | M/S PALASH BISWAS | 0.96 | 0.95 | 100 | 100
2403 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of PALSIT Piped Water Supply Scheme at BURDWAN-II Block under Burdwan Division, P.H.E. DTE. , SM/08714 | Retrofitting | Construction of boundary wall at HEAD WORK Site of PALSIT Piped W/S. Scheme under Burdwan-II Block of Burdwan Division, PHE Dte. (Length =186.00 Mtr, Col-75 Nos). | 3134/BWD | 16/08/2024 | 212 | SK BADIUZZAMAL | 14.51 | 0 | 0 | 100
2404 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09492 | Augmentation | Route Survey & Preparation of DPR for Sagrai W/S Scheme under Khandaghosh Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.11. | 186/BSD | 31/01/2022 | 30 | RADIANT | 2.92 | 2.91 | 100 | 1
2405 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09492 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
2406 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09492 | Augmentation | Repairing of dismantling concrete road by Cement Concrete (1:3:6) for Augmentation of KHANDAGHOSH Pipe Water Supply Scheme (Mouza Khandaghosh, Iodna, Barisiali, Kapshit, Nabagram, Metedanga) at Khandaghosh Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.A. | 1403/BSD | 10/08/2022 | 60 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 4.81 | 0 | 0 | 100
2407 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09492 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of SAGRAI & its adjoining mouzas Piped Water Supply Scheme, Block - Khandaghosh, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 4613/BWD | 17/10/2022 | 30 | M/S SYCHROTECH INDUSTRY | 10.22 | 8.15 | 79.72 | 0
2408 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09492 | Augmentation | Augmentation of SAGRAI Piped Water Supply Scheme with LDS, FHTC, Rising Main with necessary interconnections & Construction of 400 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test under Khandaghosh Block, District - Purba Bardhaman. | 1624/BWD | 21/03/2022 | 12 | NATIONAL CONSTRUCTION | 472.26 | 472.14 | 99.97 | 1
2409 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09492 | Augmentation | Material Requisition To Resource Division | 561/BWD | 27/01/2022 | 0 | Resource Division | 16.61 | 0 | 0 | 0
2410 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09492 | Augmentation | Material Requisition To Resource Division | 1541/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
2411 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SAGRIA PWSS TO ACCOMMODATE FHTC IN KHANDOGHOSH BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09492 | Augmentation | Material Requisition To Resource Division | 931/BWD | 16/02/2022 | 0 | Resource Division | 25.87 | 0 | 0 | 0
2412 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10059 | Augmentation | Laying distribution and rising main pipeline including Providing Functional Household Tap Connection (FHTC) for augmentation of SASINARA ZONE III Piped Water Supply Scheme under MEMARI I Block, District: Purba Bardhaman under Burdwan Division, PHE. Dte. | 1839/BWD | 04/04/2022 | 30 | THREE MAA ENTERPRISE | 49.71 | 49.6 | 50 | 1
2413 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10059 | Augmentation | Laying of 90mm dia pipeline for SASINARA ZONE-III Piped Water Supply Scheme from Pump house to Nishraghar dharmatala via Annapurnatala under MEMARI- I Block under Burdwan Sub-Division under Burdwan Division, PHE Dte. Group.A. | 965/BSD | 14/06/2022 | 30 | THREE MAA ENTERPRISE | 4.78 | 4.78 | 100 | 1
2414 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10059 | Augmentation | Providing Balance Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SASINARA ZONE-III Piped Water Supply Scheme and under NISHRAGHAR Mouza under MEMARI-I Block of Burdwan Sub-Division under Burdwan Division, PHE. Dte. | 510/BSD | 21/03/2023 | 45 | A R TRADERS | 3.51 | 3.49 | 99.63 | 100
2415 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10059 | Augmentation | Route Survey & Preparation of DPR for Sasinara (Zone-II) & (Zone-III) W/S Scheme under Burdwan-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.2. | 177/BSD | 31/01/2022 | 30 | RADIANT | 3.76 | 1.88 | 100 | 1
2416 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10059 | Augmentation | Material Requisition To Resource Division | 1245/BWD | 07/03/2022 | 0 | Resource Division | 3.92 | 0 | 0 | 0
2417 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10059 | Augmentation | Material Requisition To Resource Division | 1337/BWD | 08/03/2022 | 0 | Resource Division | 2.81 | 0 | 0 | 0
2418 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE III PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10059 | Augmentation | Material Requisition To Resource Division | 1548/BWD | 15/03/2022 | 0 | Resource Division | 1.32 | 0 | 0 | 0
2419 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Route Survey & Preparation of DPR for Sasinara (Zone-I) W/S Scheme under Memari-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.3 | 178/BSD | 31/01/2022 | 30 | APEX ENGINEERING | 3.01 | 3 | 100 | 1
2420 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
2421 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Material Requisition To Resource Division | 1246/BWD | 07/03/2022 | 0 | Resource Division | 4.36 | 0 | 0 | 0
2422 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Material Requisition To Resource Division | 1554/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
2423 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Material Requisition To Resource Division | 1333/BWD | 08/03/2022 | 0 | Resource Division | 51.36 | 0 | 0 | 0
2424 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Material Requisition To Resource Division | 4853/BWD | 20/10/2022 | 0 | Resource Division | 13.55 | 0 | 0 | 0
2425 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Restoration of Pump House at Head Work site of SASINARA ZONE-I Piped water supply scheme at Memari-I Block under Burdwan Division, Dist.-Purba Bardhaman. | 1004/BSD | 06/06/2024 | 30 | MS MOLLA CONSTRUCTION | 0.96 | 0 | 0 | 0
2426 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Quotation for new service connection at Sasinara W/S (Aug) Z-1, TW-3. | BP-2024-25-350 | 05/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.88 | 0 | 0 | 0
2427 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Construction of switch rooms & Rising main at different TW site for SASINARA (Zone-I) Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | 3725/BWD | 25/08/2023 | 615 | MOTIONMASS TECHNO (OPC) PRIVATE LIMITED | 9.03 | 0 | 0 | 90
2428 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Zone- 1 & 2, Tube well No.-3 at Augumentation of SASINARA Water Supply Scheme [BLOCK- MEMARI-I] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2138/CMD | 05/07/2024 | 60 | C.M. ENTERPRISE | 24.63 | 11.53 | 46.82 | 100
2429 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Designing,making and erection of Sign Board for SWAJAL GRAM in Dharmma Simla village of Memari-I Block under Sasinara(Zone-I) Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte (5 Nos. Board) | 2307/BSD | 19/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
2430 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Chaupira village of Memari-I Block under Sasinara (Zone-I) Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. (5 nos Board) | 2364/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
2431 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Jot Chaitanya village of Memari-I Block under Sasinara(Z-I) Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte (5 nos Board) | 2368/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
2432 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-I W/S Scheme at DEBIPUR Mouza under Memari-I Block and SATGACHIA Z-I W/S Scheme at BEGUNIA Mouza under Memari-II Block within Burdwan Sub-Division, PHE Dte. [For 02 Nos. Tube well]. | 2687/BWD | 08/06/2023 | 60 | ANIRUDDHA FARUQUE | 26.48 | 12.12 | 100 | 50
2433 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Replacement of Tube-well & Rising main at HEAD TW SITE for Aug. of BAGILA, SASINARA ZONE-I, SASINARA ZONE-II, Piped Water Supply Scheme within MEMARI-I Block under Burdwan Division, PHE. Dte. District:- Purba-Bardhaman. | 027/BWD | 03/01/2024 | 60 | KOUSIK MALLICK | 38.87 | 0 | 0 | 90
2434 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Construction of boundary wall at 1st Tube well site for SASINARA ZONE- III PWSS under MEMARI - I Block, District:- Purba-Bardhaman. | 3706/BWD | 28/10/2024 | 90 | S.M. ENTERPRISE | 10.59 | 0 | 0 | 100
2435 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10057 | Augmentation | Providing Balance Functional Household Tap Connection (1057 Nos FHTC) from existing distribution system within the command area of SASINARA ZONE-I Piped Water Supply Scheme at (Chhotodhama, Debipur, Dharmasimla, Purnagram, Jotchaitanya, Chaupira, Gouripur, Poltara) Mouza, Construction of boundary wall at head work site, 2nd T/W & 3rd T/W site under MEMARI-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 2176/BWD | 12/06/2024 | 262 | AMIT KUMAR ROY | 71.85 | 15.17 | 42.91 | 30
2436 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block , SM/07818 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Hiranyagram village within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : B] | 67/AE/HQ | 11/02/2022 | 30 | APORUPA CONSTRUCTION | 4.83 | 4.62 | 100 | 1
2437 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block , SM/07818 | Retrofitting | Material Requisition To Resource Division | 5525/BWD | 23/12/2022 | 0 | Resource Division | 0.62 | 0 | 0 | 0
2438 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block , SM/07818 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Head Quarters, Burdwan Division, PHE Dte. for the month of June & July'22. | 460/VEH/22-23 | 29/08/2022 | 0 | SK. ASRAFUDDIN | 0.76 | 0 | 0 | 0
2439 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block , SM/07818 | Retrofitting | Laying of 75mm and 50mm dia. uPVC pipe for providing FHTC at different habitation of Paratal and Ruda Mouza within Hiranyagram Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E DTE. [Group: ¿B¿] | 1818/AE/HQ | 21/09/2021 | 30 | APORUPA CONSTRUCTION | 4.74 | 4.44 | 100 | 1
2440 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block , SM/07818 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Hiranyagram Piped Water Supply Scheme at Ruda Village (2 Nos. habitations), Hiranyagram Village (2 Nos. habitations), Sajipur Village, Basantapur Village (2 Nos. habitations), Parutal Village (2 Nos. habitations), Betragarh Village, Jamalpur Block under Burdwan Division, PHE Dte.[Agreement No. 711/BWD OF 2020-2021.] | 1597/BWD | 22/02/2021 | 60 | MANASH GHOSH | 93.36 | 137.75 | 148.6 | 1
2441 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block , SM/07818 | Retrofitting | Continuation order for supply & delivery of different dia CIDF pipes, sluice valve & fittings for construction of RCC OHR (450 cum capacity) for Hiranyagram w/s scheme under Burdwan Division, PHE Dte. | 388/BWD | 20/01/2022 | 20 | ASHOKE ENGINEERING WORKS | 15.17 | 0 | 0 | 1
2442 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block , SM/07818 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Paratal village within the command area of HIRANYAGRAM Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : C] | 201/AE/HQ | 06/04/2022 | 30 | M/S SAYAN CHAKRABORTY | 4.85 | 4.84 | 100 | 1
2443 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block , SM/07818 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Basantaput and Paratal village within the command area of HIRANYAGRAM Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : B] | 228/AE/HQ | 19/04/2022 | 30 | M/S UNIQUE | 4.77 | 4.66 | 100 | 1
2444 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block , SM/07818 | Retrofitting | Construction of boundary wall (North-East Side) at Headworks site of HIRANYAGRAM W/S Scheme under Jamalpur Block of Burdwan Division, PHE Dte. (Length-63Mtr., Column-26Nos.) [Group : E] | 237/AE/HQ | 19/04/2022 | 30 | APORUPA CONSTRUCTION | 4.83 | 0 | 0 | 1
2445 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block , SM/07818 | Retrofitting | Construction of balance portion of boundary wall at H/W SITE of HIRANYAGRAM Piped W/S. Scheme under Burdwan Division PHE Dte. [Group : C] | 447/AE/HQ | 16/08/2022 | 30 | APORUPA CONSTRUCTION | 2.98 | 0 | 0 | 1
2446 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block , SM/07818 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Basantapur and Ruda village within the command area of HIRANYAGRAM Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : B] | 200/AE/HQ | 06/04/2022 | 30 | DEY NIRMAN | 4.85 | 4.35 | 100 | 1
2447 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block , SM/07818 | Retrofitting | Construction of valve chamber and necessary repairing work of pipeline for smooth running of HIRANYAGRAM Piped Water Supply Scheme, Jamalpur Dev. Block under Burdwan Division, P.H.E Dte. | 387/AE/HQ | 26/07/2023 | 30 | SANDIPAN SENGUPTA | 0.74 | 0.74 | 100 | 100
2448 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Hiranyagram Piped Water Supply Scheme at Jamalpur Block , SM/07818 | Retrofitting | Laying of uPVC pipe for providing FHTC at Ruda, Sajipur, Paratal, Betragar Village within Hiranyagram Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte._Gr-D | 126/AE/HQ | 04/03/2022 | 15 | APORUPA CONSTRUCTION | 4.64 | 3.41 | 100 | 100
2449 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bhatkunda Piped Water Supply Scheme , SM/07547 | Retrofitting | Extension of UPVC pipeline of laying distribution system at Moukata village at Bhatkunda and its adjoining mouzas water supply scheme within Ausgram-II Block under Durgapur Sub-Division under Burdwan Division, PHE Dte. [Gr.-D] | 171/DSD | 19/02/2021 | 21 | SHUBHRA KANTI GHOSH | 4.62 | 0 | 0 | 1
2450 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bhatkunda Piped Water Supply Scheme , SM/07547 | Retrofitting | Land development and Construction of culvert and approach road at 2nd tubewell site of Bhatkunda Water Supply Scheme within Durgapur Sub Division Under Burdwan Division, PHE Dte.[SL-F] | 337/DSD | 27/06/2022 | 30 | RAM MOHAN MUKHERJEE | 3.33 | 0 | 0 | 1
2451 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Bhatkunda Piped Water Supply Scheme , SM/07547 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bhatkunda Piped Water Supply Scheme at Bhatkunda (Part) Village (Adibasi Para, Bhatkunda (P), Boldanga Adibashipara habitation), Moukota (Part) Village (Adibashipara, Moukota (P) habitation), Parisha Village, Chaktilong Village, Ranngakhila Village (4Nos. habitations), Balarambati Village & Jijira Village (2 Nos. habitations) Ausgram - II Block under Burdwan Division, PHE Dte. | 3205/BWD | 09/06/2021 | 618 | ASHOK KUMAR GHOSH | 55.74 | 41.6 | 93.63 | 100
2452 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BY RETROFITTING (PHASE III) AT KALYANBATI, NARAYANPUR,RADHKRISHNAPUR & SUDPUR MOUZAS WITHIN THE COMMAND AREA OF SUDPUR PIPED WATER SUPPLY SCHEME AND AT KATWA-I BLOCK UNDER KATWA SUB DIVISION WITHIN BUR , SM/12081 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SUDPUR Piped Water Supply Scheme (PART-A) at Katwa-I Block under Burdwan Division, PHE Dte. [Agreement No. 44/2020-2021 OF SE/CC/PHE. DTE.] | 4290/BWD | 03/11/2020 | 90 | MD HASIN | 86.85 | 15.21 | 100 | 1
2453 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BY RETROFITTING (PHASE III) AT KALYANBATI, NARAYANPUR,RADHKRISHNAPUR & SUDPUR MOUZAS WITHIN THE COMMAND AREA OF SUDPUR PIPED WATER SUPPLY SCHEME AND AT KATWA-I BLOCK UNDER KATWA SUB DIVISION WITHIN BUR , SM/12081 | Retrofitting | Supply, delivery & installation of submersible pumping machinery, voltage stabiliser, chlorinator and internal house wiring for Tube well No.-3 of Sudpur water supply scheme under CMD PHE Dte. | 788/DW/22-23 | 23/11/2022 | 0 | M.S. ENTERPRISE | 9.43 | 0 | 0 | 0
2454 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BY RETROFITTING (PHASE III) AT KALYANBATI, NARAYANPUR,RADHKRISHNAPUR & SUDPUR MOUZAS WITHIN THE COMMAND AREA OF SUDPUR PIPED WATER SUPPLY SCHEME AND AT KATWA-I BLOCK UNDER KATWA SUB DIVISION WITHIN BUR , SM/12081 | Retrofitting | Laying of pipe line parallel to the main line of the existing Distribution System including providing FHTC at Kalyanbati, Narayanpur, Bijoynagar, Purba Bijnagar & Ramkrishnapur village (Mouza) within scheme jurisdiction of SUDPUR Piped W/S. Scheme under Burdwan Division PHE Dte. | 6972/BWD | 15/12/2021 | 60 | MD HASIN | 63.4 | 13.33 | 86.13 | 1
2455 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BY RETROFITTING (PHASE III) AT KALYANBATI, NARAYANPUR,RADHKRISHNAPUR & SUDPUR MOUZAS WITHIN THE COMMAND AREA OF SUDPUR PIPED WATER SUPPLY SCHEME AND AT KATWA-I BLOCK UNDER KATWA SUB DIVISION WITHIN BUR , SM/12081 | Retrofitting | Balance work of OHR at Head Work site, construction of HUME Pipe culvert , Road restoration work and boundary wall at 2nd TW site with Gate, land development at Head work site and 2nd TW site under KAITHAN, SUDPUR & PANUHAT Piped Water Supply Scheme under KATWA -I Block, under Katwa Sub-Division within Burdwan Division, PHE Dte. | 3141/BWD | 20/08/2024 | 120 | VISHAL CONSTRUCTION CO. | 126.29 | 0 | 0 | 50
2456 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) BY RETROFITTING (PHASE III) AT KALYANBATI, NARAYANPUR,RADHKRISHNAPUR & SUDPUR MOUZAS WITHIN THE COMMAND AREA OF SUDPUR PIPED WATER SUPPLY SCHEME AND AT KATWA-I BLOCK UNDER KATWA SUB DIVISION WITHIN BUR , SM/12081 | Retrofitting | Construction of valve Chamber and supply of sluice valve at Sudpur PWSS under Katwa-I Block under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No-4] | 671/KTS | 22/06/2023 | 30 | HAMID SK | 0.93 | 0.93 | 100 | 100
2457 | PURBA BARDHAMAN | Burdwan Division | DEBPUR PIPED WATER SUPPLY SCHEME , SM/13398 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 21.04 | 0 | 0 | 0
2458 | PURBA BARDHAMAN | Burdwan Division | DEBPUR PIPED WATER SUPPLY SCHEME , SM/13398 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 20.38 | 0 | 0 | 0
2459 | PURBA BARDHAMAN | Burdwan Division | DEBPUR PIPED WATER SUPPLY SCHEME , SM/13398 | New | Material Requisition To Resource Division | 5106/BWD | 23/11/2023 | 0 | Resource Division | 20.32 | 0 | 0 | 0
2460 | PURBA BARDHAMAN | Central Mechanical | DEBPUR PIPED WATER SUPPLY SCHEME , SM/13398 | New | New service connection charges for Debpur PWSS TW-1 | BP-2023-24-146 | 31/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.73 | 0 | 0 | 0
2461 | PURBA BARDHAMAN | Central Mechanical | DEBPUR PIPED WATER SUPPLY SCHEME , SM/13398 | New | New service connection charges for Debpur PWSS TW-2 | BP-2023-24-224 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.53 | 0 | 0 | 0
2462 | PURBA BARDHAMAN | Burdwan Division | DEBPUR PIPED WATER SUPPLY SCHEME , SM/13398 | New | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | 995/DSD | 29/12/2023 | 183 | SUJAUDDIN SEKH | 2 | 0.3 | 73.86 | 60
2463 | PURBA BARDHAMAN | Central Mechanical | DEBPUR PIPED WATER SUPPLY SCHEME , SM/13398 | New | Continuation order-Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven ) for supervision of site for the office of the Assistant Engineer,under CMD,PHE,Dte. [W.e.f-29/06/2024 to 31/07/2024] | 897/CMSD | 28/06/2024 | 33 | SUBRATA BHADRA | 0.4 | 0 | 0 | 0
2464 | PURBA BARDHAMAN | Central Mechanical | DEBPUR PIPED WATER SUPPLY SCHEME , SM/13398 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
2465 | PURBA BARDHAMAN | Central Mechanical | DEBPUR PIPED WATER SUPPLY SCHEME , SM/13398 | New | SUPPLY AND INSTALLATION WORKS FOR DEBPUR PWSS | BP-2023-24-557 | 21/02/2024 | 0 | P.K. ENGINEERING | 11.09 | 0 | 0 | 0
2466 | PURBA BARDHAMAN | Burdwan Division | DEBPUR PIPED WATER SUPPLY SCHEME , SM/13398 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DHENRIA, MAHATA, DEBPUR Piped Water Supply Scheme under BHATAR Block, District:- Purba-Bardhaman [NEW SCHEME] | 1737/BWD | 13/04/2023 | 993 | M/S B. RAI CONSTRUCTION COMPANY | 1643.39 | 317.66 | 54.37 | 81
2467 | PURBA BARDHAMAN | Central Mechanical | DEBPUR PIPED WATER SUPPLY SCHEME , SM/13398 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Debpur Water Supply Scheme [ Block- Bhatar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3174/CMD | 26/07/2023 | 30 | P.K. ENGINEERING | 27.69 | 10.99 | 47.45 | 95
2468 | PURBA BARDHAMAN | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME , SM/13904 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 14.19 | 0 | 0 | 0
2469 | PURBA BARDHAMAN | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME , SM/13904 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 9.5 | 0 | 0 | 0
2470 | PURBA BARDHAMAN | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME , SM/13904 | New | Material Requisition To Resource Division | 5256/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0 | 0
2471 | PURBA BARDHAMAN | Central Mechanical | BALSIDANGA PIPED WATER SUPPLY SCHEME , SM/13904 | New | New service connection charges for Balsidanga PWSS TW-1 | BP-2023-24-71 | 21/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.28 | 0 | 0 | 0
2472 | PURBA BARDHAMAN | Central Mechanical | BALSIDANGA PIPED WATER SUPPLY SCHEME , SM/13904 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
2473 | PURBA BARDHAMAN | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME , SM/13904 | New | BALSIDANGA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under BHATAR Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1443/BWD | 24/03/2023 | 90 | G.S. CONSTRUCTION & CO. | 60.82 | 29.27 | 56.77 | 100
2474 | PURBA BARDHAMAN | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME , SM/13904 | New | Sinking of 250 X 150 mm dia Tubewell, Construction of pump House, Connection with pump house and Modification to distribution network by making a loop and extension with uPVC pipe to augment the water supply to FHTC at Beldanga and Kanchgoria village of BALSHIDANGA W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. | 1017/BWD | 07/03/2024 | 60 | BAMDEB CONSTRUCTION & CO | 40.65 | 40.65 | 100 | 100
2475 | PURBA BARDHAMAN | Central Mechanical | BALSIDANGA PIPED WATER SUPPLY SCHEME , SM/13904 | New | ADDITIONAL QUOTATION NEW SERVICE CONNECTION FOR BALSIDNAGA PWSS TW -1. | BP-2023-24-645 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.04 | 0 | 0 | 0
2476 | PURBA BARDHAMAN | Central Mechanical | BALSIDANGA PIPED WATER SUPPLY SCHEME , SM/13904 | New | Quotation for new service connection at Balsidanga PWSS PH-2. | BP-2024-25-203 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.09 | 0 | 0 | 0
2477 | PURBA BARDHAMAN | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME , SM/13904 | New | Land Development work , Remaining FHTC at Balsidanga Piped Water Supply Scheme , P.H.E Dte. Block:-Bhatar Dist: Purba Bardhaman. | 1064/DSD | 24/07/2025 | 116 | KALYAN CHOWDHURY | 1.93 | 0 | 0 | 100
2478 | PURBA BARDHAMAN | Central Mechanical | BALSIDANGA PIPED WATER SUPPLY SCHEME , SM/13904 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Balsidanga Water Supply Scheme [ Block- Bhatar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2818/CMD | 04/07/2023 | 640 | M/S. SWAPAN BANERJEE | 26.97 | 11.6 | 51.55 | 60
2479 | PURBA BARDHAMAN | Burdwan Division | BALSIDANGA PIPED WATER SUPPLY SCHEME , SM/13904 | New | Additional work for BALSIDANGA Piped Water Supply Scheme with FHTC & approach road with bullah pilling under Bhatar Block, District:- Purba Bardhaman [New SCHEME]. | 3314/BWD | 06/09/2024 | 90 | KALYAN CHOWDHURY | 14.81 | 0 | 0 | 100
2480 | PURBA BARDHAMAN | Burdwan Division | GOPALBERA PIPED WATER SUPPLY SCHEME , SM/13905 | New | Material Requisition To Resource Division | 1965/BWD | 26/04/2023 | 0 | Resource Division | 9.42 | 0 | 0 | 0
2481 | PURBA BARDHAMAN | Burdwan Division | GOPALBERA PIPED WATER SUPPLY SCHEME , SM/13905 | New | Material Requisition To Resource Division | 5269/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
2482 | PURBA BARDHAMAN | Burdwan Division | GOPALBERA PIPED WATER SUPPLY SCHEME , SM/13905 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.22 | 0 | 0 | 0
2483 | PURBA BARDHAMAN | Central Mechanical | GOPALBERA PIPED WATER SUPPLY SCHEME , SM/13905 | New | New service connection for Gopalbera PWSS TW -1. | BP-2023-24-513 | 08/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.42 | 0 | 0 | 0
2484 | PURBA BARDHAMAN | Central Mechanical | GOPALBERA PIPED WATER SUPPLY SCHEME , SM/13905 | New | New service connection for Gopalbera PWSS TW -2. | BP-2023-24-514 | 08/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.28 | 0 | 0 | 0
2485 | PURBA BARDHAMAN | Burdwan Division | GOPALBERA PIPED WATER SUPPLY SCHEME , SM/13905 | New | GOPALBERA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | 2079/BWD | 04/05/2023 | 698 | KHAN ENTERPRISE | 588.35 | 436.82 | 74.24 | 50
2486 | PURBA BARDHAMAN | Burdwan Division | GOPALBERA PIPED WATER SUPPLY SCHEME , SM/13905 | New | Balance work for providing Functional Household Tap Connection (FHTC) within command area GOPALBERA & CHAGRAM W/S. Scheme of Khandaghosh Block under Burdwan Divn., PHE. Dte. | 4438/BWD | 18/12/2024 | 253 | DUBE ENTERPRISE | 143.33 | 0 | 0 | 70
2487 | PURBA BARDHAMAN | Central Mechanical | GOPALBERA PIPED WATER SUPPLY SCHEME , SM/13905 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
2488 | PURBA BARDHAMAN | Central Mechanical | GOPALBERA PIPED WATER SUPPLY SCHEME , SM/13905 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Gopalbera Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4042/CMD | 29/08/2023 | 30 | ASHIM UDYOG | 28.95 | 22.76 | 95.21 | 100
2489 | PURBA BARDHAMAN | Burdwan Division | CHOTKHANDA PIPED WATER SUPPLY SCHEME , SM/13907 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.93 | 0 | 0 | 0
2490 | PURBA BARDHAMAN | Burdwan Division | CHOTKHANDA PIPED WATER SUPPLY SCHEME , SM/13907 | New | Material Requisition To Resource Division | 3991/BWD | 08/09/2023 | 0 | Resource Division | 9.08 | 0 | 0 | 0
2491 | PURBA BARDHAMAN | Burdwan Division | CHOTKHANDA PIPED WATER SUPPLY SCHEME , SM/13907 | New | Material Requisition To Resource Division | 5085/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
2492 | PURBA BARDHAMAN | Burdwan Division | CHOTKHANDA PIPED WATER SUPPLY SCHEME , SM/13907 | New | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, land development, Sluice valve chamber for smooth water supply of FHTC work for CHOTKHANDA PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | 4280/BWD | 09/12/2024 | 90 | TARAMA AGENCY | 21.09 | 0 | 0 | 0
2493 | PURBA BARDHAMAN | Central Mechanical | CHOTKHANDA PIPED WATER SUPPLY SCHEME , SM/13907 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
2494 | PURBA BARDHAMAN | Central Mechanical | CHOTKHANDA PIPED WATER SUPPLY SCHEME , SM/13907 | New | Supply & delivery of different electro-mechanical accessories (for urgent FHTC) for Tube well no.-I & II at Chotkhanda w/s scheme, (Block- Memari-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | 540/CMSD | 28/03/2024 | 7 | S.K. ENTERPRISE | 0.53 | 0.53 | 100 | 100
2495 | PURBA BARDHAMAN | Central Mechanical | CHOTKHANDA PIPED WATER SUPPLY SCHEME , SM/13907 | New | New service connection charges for Chotkhanda PWSS TW-1 | BP-2023-24-244 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.02 | 0 | 0 | 0
2496 | PURBA BARDHAMAN | Central Mechanical | CHOTKHANDA PIPED WATER SUPPLY SCHEME , SM/13907 | New | Quotation for new electric service connection at Chotkhanda TW NO.-2 | BP-2023-24-243 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.61 | 0 | 0 | 0
2497 | PURBA BARDHAMAN | Burdwan Division | CHOTKHANDA PIPED WATER SUPPLY SCHEME , SM/13907 | New | CHOTKHANDA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari I Block, District:- Purba-Bardhaman [NEW SCHEME] | 2306/BWD | 19/05/2023 | 683 | ASHOK KUMAR GHOSH | 513.64 | 371.17 | 72.26 | 85
2498 | PURBA BARDHAMAN | Central Mechanical | CHOTKHANDA PIPED WATER SUPPLY SCHEME , SM/13907 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chotkhanda Water Supply Scheme [ Block- Memari-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4041/CMD | 29/08/2023 | 369 | S.K. ENTERPRISE | 29.59 | 23.57 | 79.64 | 100
2499 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B , SM/13043 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AGRADWIP Piped Water Supply Scheme at Agradwip, Babla danga, Gonsaidhowra, Saheb Nagar & Sarawaridhowra (Mouza), Katwa - II Block under Burdwan Division, PHE Dte. | 6253/BWD | 01/11/2021 | 60 | SHUBHRA KANTI GHOSH | 53.67 | 34.17 | 100 | 1
2500 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B , SM/13043 | Retrofitting | Providing Functional Household Tap Connection from existing distribution system within the command area of AGRADWIP PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-1) | 688/KTS | 08/10/2021 | 7 | CHANCHAL PAL | 1.21 | 1.2 | 100 | 1
2501 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B , SM/13043 | Retrofitting | Extension of pipe line of Providing Functional Household Tap Connection (FHTC) from existing distribution system within command area of Agradwip Water Supply Schame under Agradwip PWSS at Gonsaishowra, & Sarawaridhowar Habitation Katwa-II Block Katwa Sub-Division under Burdwan Division PHE Dte.. [Sl No-05] | 172/KTS | 25/02/2022 | 7 | SHUBHRA KANTI GHOSH | 1.32 | 1.3 | 100 | 1
2502 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B , SM/13043 | Retrofitting | Extension of pipe line of Providing Functional Household Tap Connection (FHTC) from existing distribution system within command area of Agradwip Water Supply Schame under Agradwip PWSS at Babla danga and Saheb Nagar Habitation Katwa-II Block Katwa Sub-Division under Burdwan Division PHE Dte.. [Sl No-02] | 161/KTS | 24/02/2022 | 7 | SHUBHRA KANTI GHOSH | 2.1 | 2.08 | 100 | 1
2503 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B , SM/13043 | Retrofitting | Supplying and laying of valves along with construction of valve chamber at the existing distribution pipe line of Agradwip PWSS under Katwa Sub-Division under Burdwan Division, PHE Dte [Sl No-04] | 440/KTS | 27/06/2022 | 30 | TAPAS KUMAR ROY | 0.78 | 0.78 | 100 | 1
2504 | PURBA BARDHAMAN | Burdwan Division | PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC BY RETROFITTING AT AGRADWIP MOUZA WITHIN THE COMMAND AREA AGRADWIP PIPED WATER SUPPLY SCHEME AT KATWA II BLOCK UNDER BURDWAN DIVISION PHE DTE PART B , SM/13043 | Retrofitting | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme AGRADWIP, KHETPUR PALASHI, SAHAPUR PWSS (Sl No-1) | 393/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 3.71 | 1.24 | 100 | 100
2505 | PURBA BARDHAMAN | Burdwan Division | AMARPUR PIPED WATER SUPPLY SCHEME , SM/13967 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 9.35 | 0 | 0 | 0
2506 | PURBA BARDHAMAN | Burdwan Division | AMARPUR PIPED WATER SUPPLY SCHEME , SM/13967 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 20.19 | 0 | 0 | 0
2507 | PURBA BARDHAMAN | Burdwan Division | AMARPUR PIPED WATER SUPPLY SCHEME , SM/13967 | New | Material Requisition To Resource Division | 4932/BWD | 10/11/2023 | 0 | Resource Division | 30.36 | 0 | 0 | 0
2508 | PURBA BARDHAMAN | Burdwan Division | AMARPUR PIPED WATER SUPPLY SCHEME , SM/13967 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways for AMARPUR Piped Water Supply Scheme under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 4952/BWD | 17/11/2023 | 365 | SUJAY KUMAR RAY | 344.32 | 145.1 | 42.14 | 50
2509 | PURBA BARDHAMAN | Central Mechanical | AMARPUR PIPED WATER SUPPLY SCHEME , SM/13967 | New | NEW SERVICE CONNECTION FOR AMARPUR PWSS PH 2. | BP-2023-24-605 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.88 | 0 | 0 | 0
2510 | PURBA BARDHAMAN | Central Mechanical | AMARPUR PIPED WATER SUPPLY SCHEME , SM/13967 | New | NEW SERVICE CONNECTION FOR AMARPUR PWSS PH 1. | BP-2023-24-604 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0 | 0
2511 | PURBA BARDHAMAN | Durgapur W/S Division | AMARPUR PIPED WATER SUPPLY SCHEME , SM/13967 | New | Formal Work Order for Additional work for laying 200 mm dia HDPE pipe line and other necessary allied works Amarpur & Bhedia Piped W/S Scheme, Block- Aushgram-2, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 1291/DWSD | 06/09/2024 | 210 | SAIKAT RAY | 196.61 | 9.11 | 9.27 | 60
2512 | PURBA BARDHAMAN | Central Mechanical | AMARPUR PIPED WATER SUPPLY SCHEME , SM/13967 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Amarpur Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4177/CMD | 29/08/2023 | 611 | AMUSAR IMPEX PVT. LTD. | 28.55 | 22.63 | 95.42 | 96
2513 | PURBA BARDHAMAN | Burdwan Division | MANGANPUR PIPED WATER SUPPLY SCHEME , SM/13327 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.02 | 0 | 0 | 0
2514 | PURBA BARDHAMAN | Burdwan Division | MANGANPUR PIPED WATER SUPPLY SCHEME , SM/13327 | New | Material Requisition To Resource Division | 3999/BWD | 08/09/2023 | 0 | Resource Division | 3.31 | 0 | 0 | 0
2515 | PURBA BARDHAMAN | Central Mechanical | MANGANPUR PIPED WATER SUPPLY SCHEME , SM/13327 | New | New service connection charges for Manganpur PWSS TW-1 | BP-2023-24-227 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.63 | 0 | 0 | 0
2516 | PURBA BARDHAMAN | Central Mechanical | MANGANPUR PIPED WATER SUPPLY SCHEME , SM/13327 | New | Supply and delivery of portable generator set for emergency internal installation work at Manganpur and other Water Supply Scheme under CMD., PHE Dte. | 153/CMSD | 22/01/2024 | 15 | M/S, MONDAL ASSOCIATES. | 2.11 | 2.11 | 100 | 100
2517 | PURBA BARDHAMAN | Burdwan Division | MANGANPUR PIPED WATER SUPPLY SCHEME , SM/13327 | New | Material Requisition To Resource Division | 315/BWD | 24/01/2024 | 0 | Resource Division | 17.52 | 0 | 0 | 0
2518 | PURBA BARDHAMAN | Burdwan Division | MANGANPUR PIPED WATER SUPPLY SCHEME , SM/13327 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MANGANPUR & BAGPUR Piped Water Supply Scheme under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3200/BWD | 24/07/2023 | 1100 | M/S GHOSH & CO. | 711.81 | 180.13 | 42.99 | 10
2519 | PURBA BARDHAMAN | Central Mechanical | MANGANPUR PIPED WATER SUPPLY SCHEME , SM/13327 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at MANGANPUR Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4040/CMD | 29/08/2023 | 30 | SOUNAK ENTERPRISE | 22.1 | 10 | 45.24 | 50
2520 | PURBA BARDHAMAN | Burdwan Division | MANGANPUR PIPED WATER SUPPLY SCHEME , SM/13327 | New | Different types of works involve in connection with Augmentation of SRIRAMPUR (Zone I & II) (SM/08103), MANGANPUR (SM/13327), KAMALPUR (SM/13453) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2429/BWD | 27/06/2024 | 480 | S.P. CONSTRUCTION | 500.89 | 158.83 | 56.73 | 2
2521 | PURBA BARDHAMAN | Central Mechanical | MANGANPUR PIPED WATER SUPPLY SCHEME , SM/13327 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 30
2522 | PURBA BARDHAMAN | Central Mechanical | MANGANPUR PIPED WATER SUPPLY SCHEME , SM/13327 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
2523 | PURBA BARDHAMAN | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/13331 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.24 | 0 | 0 | 0
2524 | PURBA BARDHAMAN | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/13331 | New | Material Requisition To Resource Division | 3972/BWD | 08/09/2023 | 0 | Resource Division | 108.75 | 0 | 0 | 0
2525 | PURBA BARDHAMAN | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/13331 | New | NEW SERVICE CONNECTION FOR DHENUA PWSS. | BP-2023-24-564 | 23/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.21 | 0 | 0 | 0
2526 | PURBA BARDHAMAN | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/13331 | New | NEW SERVICE CONNECTION FOR DHENUA PWSS TW -1. | BP-2023-24-641 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.52 | 0 | 0 | 0
2527 | PURBA BARDHAMAN | Burdwan Division | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/13331 | New | Arrangement of drinking water supply by installation of solar submersible pump including sinking of 200 mm. dia. Tube well 150 Mtr. Deep by direct rotary rig method, Laying dist. System, FHTC and 2 Nos. 5000 Ltr. PVC tank installation with construction of RCC structure for RUIGORIA Habitation which is uncovered of DHENUA Piped W/S. Scheme, Block Manteswar under Burdwan Division, PHE Dte. | 3667/BWD | 22/10/2024 | 90 | UJJWAL MUKHERJEE | 31.83 | 0 | 0 | 0
2528 | PURBA BARDHAMAN | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/13331 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
2529 | PURBA BARDHAMAN | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/13331 | New | CONTINUATION ORDER-Hiring of inspection vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of the Assistant Engineer ,under CMD,PHE,Dte.[W.E.F-31/01/2025 TO 31/03/2025][UNDER JJM WORKS] | 110/CMSD | 30/01/2025 | 60 | PRODYUT GHOSH | 0.79 | 0.79 | 100 | 0
2530 | PURBA BARDHAMAN | Central Mechanical | Ground Water Supply Based Piped Water Supply Scheme For DHENUA PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/13331 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Dhenua Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4050/CMD | 29/08/2023 | 640 | SUBRATA BHADRA | 29.91 | 0 | 0 | 100
2531 | PURBA BARDHAMAN | Burdwan Division | MANDARDIHI PIPED WATER SUPPLY SCHEME , SM/14052 | New | Material Requisition To Resource Division | 1238/BWD | 17/03/2023 | 0 | Resource Division | 2.16 | 0 | 0 | 0
2532 | PURBA BARDHAMAN | Burdwan Division | MANDARDIHI PIPED WATER SUPPLY SCHEME , SM/14052 | New | Material Requisition To Resource Division | 5247/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0 | 0
2533 | PURBA BARDHAMAN | Central Mechanical | MANDARDIHI PIPED WATER SUPPLY SCHEME , SM/14052 | New | New service connection charges for Mandardihi PWSS TW-2 | BP-2023-24-148 | 31/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.15 | 0 | 0 | 0
2534 | PURBA BARDHAMAN | Central Mechanical | MANDARDIHI PIPED WATER SUPPLY SCHEME , SM/14052 | New | New service connection charges for Mandardihi PWSS TW-1 | BP-2023-24-119 | 17/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.61 | 0 | 0 | 0
2535 | PURBA BARDHAMAN | Central Mechanical | MANDARDIHI PIPED WATER SUPPLY SCHEME , SM/14052 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MANDARDIHI Water Supply Scheme [ Block- BHATAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3504/CMD | 31/07/2023 | 668 | S.K. ELECTRICALS | 26.96 | 18.81 | 69.78 | 90
2536 | PURBA BARDHAMAN | Central Mechanical | MANDARDIHI PIPED WATER SUPPLY SCHEME , SM/14052 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
2537 | PURBA BARDHAMAN | Burdwan Division | MANDARDIHI PIPED WATER SUPPLY SCHEME , SM/14052 | New | MANDARDIHI (PART:-B) Piped Water Supply Scheme with LDS & FHTC [NODE POINT 49 TO 77] under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | 919/BWD | 02/03/2023 | 30 | PAPRI HAZRA | 18.89 | 17.17 | 100 | 100
2538 | PURBA BARDHAMAN | Burdwan Division | MANDARDIHI PIPED WATER SUPPLY SCHEME , SM/14052 | New | MANDARDIHI (PART:-A) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | 928/BWD | 02/03/2023 | 60 | DUBE ENTERPRISE | 63.01 | 63 | 100 | 30
2539 | PURBA BARDHAMAN | Central Mechanical | MANDARDIHI PIPED WATER SUPPLY SCHEME , SM/14052 | New | Emergency installation (for urgent FHTC) at Mandardihi Water Supply Scheme PH 2 (part-3) under CMD, PHE Dte., Dist.- Purba-Bardhaman | 83/CMSD | 15/01/2024 | 12 | CHOUDHURY ENTERPRISE | 0.92 | 0.92 | 100 | 100
2540 | PURBA BARDHAMAN | Central Mechanical | MANDARDIHI PIPED WATER SUPPLY SCHEME , SM/14052 | New | Supply and delivery of different Electro-mechanical items (for urgent FHTC) for Mandardihi Water Supply Scheme PH 2 (part-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | 19/CMSD | 04/01/2024 | 10 | CHOUDHURY ENTERPRISE | 0.91 | 0.91 | 100 | 100
2541 | PURBA BARDHAMAN | Central Mechanical | MANDARDIHI PIPED WATER SUPPLY SCHEME , SM/14052 | New | Supply and delivery of submersible pumping machinery (for urgent FHTC) for mandardihi Water Supply Scheme PH 2 (part-2) under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 66/CMSD | 11/01/2024 | 12 | CHOUDHURY ENTERPRISE | 0.81 | 0.81 | 100 | 100
2542 | PURBA BARDHAMAN | Burdwan Division | MANDARDIHI PIPED WATER SUPPLY SCHEME , SM/14052 | New | Restoration of Concrete Road , Providing Sluice Valve , Land development and Construction of Approach road at Pump House site of Mandardihi piped water supply scheme of JJM in Bhatar Block , District Purba Bardhaman, Durgapur Sub Division under Burdwan Division, P.H.E. Dte. | 382/DSD | 10/03/2025 | 45 | TARAMA AGENCY | 4.79 | 0 | 0 | 100
2543 | PURBA BARDHAMAN | Burdwan Division | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME , SM/14054 | New | Material Requisition To Resource Division | 1246/BWD | 17/03/2023 | 0 | Resource Division | 17.02 | 0 | 0 | 0
2544 | PURBA BARDHAMAN | Burdwan Division | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME , SM/14054 | New | Material Requisition To Resource Division | 1638/BWD | 06/04/2023 | 0 | Resource Division | 1.1 | 0 | 0 | 0
2545 | PURBA BARDHAMAN | Central Mechanical | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME , SM/14054 | New | New service connection charges for Jagadanandapur PWSS TW-2 | BP-2023-24-85 | 26/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.95 | 0 | 0 | 0
2546 | PURBA BARDHAMAN | Central Mechanical | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME , SM/14054 | New | New service connection charges for Jagadanandapur W/S Scheme TW-1 | BP-2023-24-36 | 27/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.38 | 0 | 0 | 0
2547 | PURBA BARDHAMAN | Burdwan Division | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME , SM/14054 | New | JAGADANANDAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -II Block, District:- Purba-Bardhaman [NEW SCHEME] | 777/BWD | 24/02/2023 | 1253 | MANASH GHOSH | 562.08 | 469 | 83.44 | 78
2548 | PURBA BARDHAMAN | Burdwan Division | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME , SM/14054 | New | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | 1009/KTS | 19/07/2024 | 60 | AJIT SAMANTA | 0.77 | 0.17 | 55.6 | 100
2549 | PURBA BARDHAMAN | Central Mechanical | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME , SM/14054 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
2550 | PURBA BARDHAMAN | Central Mechanical | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME , SM/14054 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Jagadanandapur Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2659/CMD | 16/06/2023 | 30 | PADMA ENGINEERING CO. | 28.97 | 21.56 | 91.54 | 60
2551 | PURBA BARDHAMAN | Burdwan Division | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME , SM/14054 | New | Material Requisition To Resource Division | 327/BWD | 24/01/2024 | 0 | Resource Division | 22.74 | 0 | 0 | 0
2552 | PURBA BARDHAMAN | Burdwan Division | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME , SM/14054 | New | Providing of left out FHTC in different location of JAGADANANDAPUR PWSS (SM/14054) at Musthuli Mouza in order to declare Sajal Gram, under Katwa-II Block under Katwa Sub-Division, PHE Dte. | 980/BWD | 13/03/2025 | 172 | MANASH GHOSH | 9.53 | 0 | 0 | 100
2553 | PURBA BARDHAMAN | Burdwan Division | JAGADANANDAPUR PIPED WATER SUPPLY SCHEME , SM/14054 | New | Providing of left out FHTC in different location of JAGADANANDAPUR PWSS (SM/14054) at Jagadanandapur, and Amdanga Mouza in order to declare Sajal Gram, under Katwa-II Block under Katwa Sub-Division, PHE Dte. | 981/BWD | 13/03/2025 | 172 | MANASH GHOSH | 9.55 | 0 | 0 | 100
2554 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Material Requisition To Resource Division | 1640/BWD | 06/04/2023 | 0 | Resource Division | 4.7 | 0 | 0 | 0
2555 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Material Requisition To Resource Division | 1237/BWD | 17/03/2023 | 0 | Resource Division | 10.42 | 0 | 0 | 0
2556 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Material Requisition To Resource Division | 3967/BWD | 08/09/2023 | 0 | Resource Division | 19.84 | 0 | 0 | 0
2557 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Material Requisition To Resource Division | 5093/BWD | 23/11/2023 | 0 | Resource Division | 21.42 | 0 | 0 | 0
2558 | PURBA BARDHAMAN | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | New service connection charges for Deara PWSS TW-1 | BP-2023-24-222 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.46 | 0 | 0 | 0
2559 | PURBA BARDHAMAN | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
2560 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Work Order for "Supply of 1 (one) No. Diesel driven Motor cab (Inspection vehicle) on hire basis for JJM projects for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period for 3 (Three) Months]". | 1333/KSD | 28/08/2023 | 72 | PARTHA PRATIM ACHARYA | 0.92 | 0.81 | 100 | 100
2561 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Work order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR DEARA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 1979/KSD | 09/02/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.66 | 100 | 100
2562 | PURBA BARDHAMAN | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | New service connection for DEARA PWSS | BP-2023-24-544 | 19/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.53 | 0 | 0 | 0
2563 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEARA, PATHARDANGA & SHIKARPUR Piped Water Supply Scheme under KALNA-I Block, District:- Purba Bardhaman [NEW SCHEME] | 1004/BWD | 06/03/2023 | 641 | M/S TAPAS KUMAR CHAKRABORTY | 1584.09 | 296.81 | 73.67 | 75
2564 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
2565 | PURBA BARDHAMAN | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Deara Water Supply Scheme [ Block- KALNA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4060/CMD | 29/08/2023 | 485 | S.K. ENTERPRISE | 28.6 | 22.57 | 95.41 | 100
2566 | PURBA BARDHAMAN | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Installation of Electrical items & allied works for Urgent FHTC for Deara PH 1 water supply scheme under CMD P.H.E. Dte. | 822/CMSD | 31/05/2024 | 30 | S.K. ENTERPRISE | 0.64 | 0 | 0 | 100
2567 | PURBA BARDHAMAN | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Continuation Order-Providing Diesel generator set at DEARA Water supply scheme for Urgent FHTC connection under CMD PHE Dte. [W.E.F- 05.06.2024 TO 08.06.2024] | 827/CMSD | 04/06/2024 | 7 | S.K. ENTERPRISE | 0.85 | 0 | 0 | 100
2568 | PURBA BARDHAMAN | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Providing Diesel generator set at Deara water supply scheme for Urgent FHTC connection under CMD P.H.E. Dte. | 821/CMSD | 31/05/2024 | 7 | S.K. ENTERPRISE | 0.85 | 0 | 0 | 100
2569 | PURBA BARDHAMAN | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Installation of Electrical items & allied works for Urgent FHTC for Deara PH 2 water supply scheme under CMD P.H.E. Dte. | 823/CMSD | 31/05/2024 | 30 | S.K. ENTERPRISE | 0.64 | 0 | 0 | 100
2570 | PURBA BARDHAMAN | Burdwan Division | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Work order for "Restoration of pipeline with other allied works at different places of Deara mouja under Deara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | 968/KSD | 31/07/2024 | 10 | M/S TAPAS KUMAR CHAKRABORTY | 2.35 | 0 | 0 | 100
2571 | PURBA BARDHAMAN | Central Mechanical | DEARA PIPED WATER SUPPLY SCHEME , SM/14435 | New | Continuation Order-Providing Diesel generator set at DEARA Water Supply Scheme for Urgent FHTC connection under CMD PHE Dte [09/06/2024 to 12/06/2024] | 836/CMSD | 07/06/2024 | 7 | S.K. ENTERPRISE | 0.85 | 0 | 0 | 100
2572 | PURBA BARDHAMAN | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME , SM/14443 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] | 593/DSD | 31/07/2023 | 66 | AFIBS ENTERPRISE | 0.85 | 0.83 | 100 | 100
2573 | PURBA BARDHAMAN | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME , SM/14443 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 27.18 | 0 | 0 | 0
2574 | PURBA BARDHAMAN | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME , SM/14443 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 17.06 | 0 | 0 | 0
2575 | PURBA BARDHAMAN | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME , SM/14443 | New | Material Requisition To Resource Division | 4897/BWD | 10/11/2023 | 0 | Resource Division | 38.94 | 0 | 0 | 0
2576 | PURBA BARDHAMAN | Central Mechanical | NASIGRAM PIPED WATER SUPPLY SCHEME , SM/14443 | New | New service connection charges for Nasigram PWSS TW-1 | BP-2023-24-72 | 21/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.83 | 0 | 0 | 0
2577 | PURBA BARDHAMAN | Central Mechanical | NASIGRAM PIPED WATER SUPPLY SCHEME , SM/14443 | New | New service connection charges for Nasigram PWSS TW-2 | BP-2023-24-73 | 21/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.19 | 0 | 0 | 0
2578 | PURBA BARDHAMAN | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME , SM/14443 | New | Continuation Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/11/2023 to 31/01/2024] | 825/DSD | 31/10/2023 | 66 | AFIBS ENTERPRISE | 0.85 | 0.28 | 33.33 | 100
2579 | PURBA BARDHAMAN | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME , SM/14443 | New | Making connection with 4th tube well, Construction of Plinth protection of OHR, Restoration of road and FHTC (The rest portion) of Bara Belun Water Supply Scheme at Bara Belun village & Providing Functional Household Tap Connection (FHTC) within the command area of NASIGRAM Piped W/S. Scheme within Bhatar Block under Burdwan Division, PHE. Dte. | 3685/BWD | 23/10/2024 | 120 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 91.48 | 0 | 0 | 0
2580 | PURBA BARDHAMAN | Central Mechanical | NASIGRAM PIPED WATER SUPPLY SCHEME , SM/14443 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
2581 | PURBA BARDHAMAN | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME , SM/14443 | New | Continuation Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/11/2023 to 31/01/2024] | 825/DSD | 31/10/2023 | 66 | AFIBS ENTERPRISE | 0.85 | 1.13 | 100 | 100
2582 | PURBA BARDHAMAN | Central Mechanical | NASIGRAM PIPED WATER SUPPLY SCHEME , SM/14443 | New | NEW SERVICE CONNECTION FOR NASIGRAM PWSS | BP-2023-24-574 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.54 | 0 | 0 | 0
2583 | PURBA BARDHAMAN | Burdwan Division | NASIGRAM PIPED WATER SUPPLY SCHEME , SM/14443 | New | NASIGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | 1826/BWD | 19/04/2023 | 742 | MD HASIN | 742.95 | 499.95 | 67.29 | 50
2584 | PURBA BARDHAMAN | Central Mechanical | NASIGRAM PIPED WATER SUPPLY SCHEME , SM/14443 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at NASIGRAM Water Supply Scheme [ Block- BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2856/CMD | 05/07/2023 | 30 | M/S. S.R. ENTERPRISE | 41.65 | 32.63 | 95.25 | 90
2585 | PURBA BARDHAMAN | Burdwan Division | GURPARA PIPED WATER SUPPLY SCHEME , SM/14447 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 9.42 | 0 | 0 | 0
2586 | PURBA BARDHAMAN | Burdwan Division | GURPARA PIPED WATER SUPPLY SCHEME , SM/14447 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 17.31 | 0 | 0 | 0
2587 | PURBA BARDHAMAN | Burdwan Division | GURPARA PIPED WATER SUPPLY SCHEME , SM/14447 | New | Material Requisition To Resource Division | 4871/BWD | 10/11/2023 | 0 | Resource Division | 29.6 | 0 | 0 | 0
2588 | PURBA BARDHAMAN | Central Mechanical | GURPARA PIPED WATER SUPPLY SCHEME , SM/14447 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
2589 | PURBA BARDHAMAN | Central Mechanical | GURPARA PIPED WATER SUPPLY SCHEME , SM/14447 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Gurpara Water Supply Scheme [ Block- Ketugram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4059/CMD | 29/08/2023 | 30 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 26.93 | 21.07 | 95.1 | 91
2590 | PURBA BARDHAMAN | Central Mechanical | GURPARA PIPED WATER SUPPLY SCHEME , SM/14447 | New | Quotation for new service connection at Gurpara W/S Scheme PH-I. | BP-2023-24-308 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.28 | 0 | 0 | 0
2591 | PURBA BARDHAMAN | Central Mechanical | GURPARA PIPED WATER SUPPLY SCHEME , SM/14447 | New | New service connection at Guyrpara PWSS TW No.2 | BP-2023-24-488 | 01/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.9 | 0 | 0 | 0
2592 | PURBA BARDHAMAN | Burdwan Division | GURPARA PIPED WATER SUPPLY SCHEME , SM/14447 | New | Balance work of OHR, construction Concrete Road, Drum Sheet Pilling, Functional Household Tap Connection, construction of HUME Pipe culvert, land development, Road restoration etc. under Billeswar PWSS, Purulia PWSS & Gurpara PWSS under KATWA -II Block under Katwa Sub-Divn. under Burdwan Division, PHED. District:- Purba-Bardhaman | 2834/BWD | 19/07/2024 | 835 | PASCON | 190.06 | 0 | 0 | 90
2593 | PURBA BARDHAMAN | Burdwan Division | NABASTA PIPED WATER SUPPLY SCHEME , SM/14059 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 80.57 | 0 | 0 | 0
2594 | PURBA BARDHAMAN | Burdwan Division | NABASTA PIPED WATER SUPPLY SCHEME , SM/14059 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 3.49 | 0 | 0 | 0
2595 | PURBA BARDHAMAN | Burdwan Division | NABASTA PIPED WATER SUPPLY SCHEME , SM/14059 | New | Material Requisition To Resource Division | 4931/BWD | 10/11/2023 | 0 | Resource Division | 33.07 | 0 | 0 | 0
2596 | PURBA BARDHAMAN | Central Mechanical | NABASTA PIPED WATER SUPPLY SCHEME , SM/14059 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
2597 | PURBA BARDHAMAN | Central Mechanical | NABASTA PIPED WATER SUPPLY SCHEME , SM/14059 | New | New Service connection at Nabastha PWSS PH-1 | BP-2023-24-456 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.04 | 0 | 0 | 0
2598 | PURBA BARDHAMAN | Central Mechanical | NABASTA PIPED WATER SUPPLY SCHEME , SM/14059 | New | New Service connection at Nabastha PWSS PH-2 | BP-2023-24-457 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.95 | 0 | 0 | 0
2599 | PURBA BARDHAMAN | Central Mechanical | NABASTA PIPED WATER SUPPLY SCHEME , SM/14059 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at NABASTA Water Supply Scheme [ Block-BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4070/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 27.79 | 14.92 | 53.68 | 40
2600 | PURBA BARDHAMAN | Burdwan Division | NABASTA PIPED WATER SUPPLY SCHEME , SM/14059 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NABASTA, PASHALA & POALKURA Piped Water Supply Scheme under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | 4652/BWD | 31/10/2023 | 898 | STARCO CONSTRUCTIONS | 900.17 | 100.31 | 20.67 | 2
2601 | PURBA BARDHAMAN | Burdwan Division | NABASTA PIPED WATER SUPPLY SCHEME , SM/14059 | New | Providing Parallal LDS (Node- 30-43-42-41-49 to 36) & 4nos ICDS connection for at Palsa-Chandrasekharpara within Nabastha PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | 358/BWD | 16/01/2025 | 60 | PRATIVA CONSTRUCTION | 7.61 | 0 | 0 | 0
2602 | PURBA BARDHAMAN | Burdwan Division | PHANRIJANGALPIPED WATER SUPPLY SCHEME , SM/14060 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.24 | 0 | 0 | 0
2603 | PURBA BARDHAMAN | Burdwan Division | PHANRIJANGALPIPED WATER SUPPLY SCHEME , SM/14060 | New | Material Requisition To Resource Division | 5090/BWD | 23/11/2023 | 0 | Resource Division | 21.84 | 0 | 0 | 0
2604 | PURBA BARDHAMAN | Burdwan Division | PHANRIJANGALPIPED WATER SUPPLY SCHEME , SM/14060 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 32.65 | 0 | 0 | 0
2605 | PURBA BARDHAMAN | Central Mechanical | PHANRIJANGALPIPED WATER SUPPLY SCHEME , SM/14060 | New | New service connection charges for Phanrijangal PWSS TW 1 | BP-2023-24-184 | 04/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.21 | 0 | 0 | 0
2606 | PURBA BARDHAMAN | Central Mechanical | PHANRIJANGALPIPED WATER SUPPLY SCHEME , SM/14060 | New | New service connection charges for Phanrijangal PWSS TW-2 | BP-2023-24-213 | 03/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.42 | 0 | 0 | 0
2607 | PURBA BARDHAMAN | Burdwan Division | PHANRIJANGALPIPED WATER SUPPLY SCHEME , SM/14060 | New | PHANRIJANGAL Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3030/BWD | 14/07/2023 | 180 | SUPRIYA RAY | 271.24 | 228.47 | 84.23 | 35
2608 | PURBA BARDHAMAN | Durgapur W/S Division | PHANRIJANGALPIPED WATER SUPPLY SCHEME , SM/14060 | New | FORMAL WORK ORDER FOR Balance work for PHANRIJANGAL PWSS with sining of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-II Block under DURGAPUR W/S DIVISION, PHE DTE. | 281/DWSD | 17/02/2025 | 120 | SUJAY KUMAR RAY | 101.85 | 0 | 0 | 0
2609 | PURBA BARDHAMAN | Central Mechanical | PHANRIJANGALPIPED WATER SUPPLY SCHEME , SM/14060 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PHANRIJANGAL Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4017/CMD | 29/08/2023 | 30 | SOUNAK ENTERPRISE | 28.48 | 21.95 | 95.17 | 98
2610 | PURBA BARDHAMAN | Burdwan Division | POALKURA PIPED WATER SUPPLY SCHEME , SM/14061 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 15.26 | 0 | 0 | 0
2611 | PURBA BARDHAMAN | Burdwan Division | POALKURA PIPED WATER SUPPLY SCHEME , SM/14061 | New | Material Requisition To Resource Division | 5239/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0 | 0
2612 | PURBA BARDHAMAN | Burdwan Division | POALKURA PIPED WATER SUPPLY SCHEME , SM/14061 | New | Material Requisition To Resource Division | 4948/BWD | 10/11/2023 | 0 | Resource Division | 1.3 | 0 | 0 | 0
2613 | PURBA BARDHAMAN | Central Mechanical | POALKURA PIPED WATER SUPPLY SCHEME , SM/14061 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
2614 | PURBA BARDHAMAN | Central Mechanical | POALKURA PIPED WATER SUPPLY SCHEME , SM/14061 | New | New service connection for Poalkora PWSS | BP-2023-24-545 | 19/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.14 | 0 | 0 | 0
2615 | PURBA BARDHAMAN | Central Mechanical | POALKURA PIPED WATER SUPPLY SCHEME , SM/14061 | New | Additional quotation for new service connection for POALKURA PWSS PH1 | BP-2024-25-418 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.5 | 0 | 0 | 0
2616 | PURBA BARDHAMAN | Central Mechanical | POALKURA PIPED WATER SUPPLY SCHEME , SM/14061 | New | New service connection for Poalkura PWSS | BP-2023-24-590 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.85 | 0 | 0 | 0
2617 | PURBA BARDHAMAN | Central Mechanical | POALKURA PIPED WATER SUPPLY SCHEME , SM/14061 | New | New Service connection at Poalkura PWSS PH-1 | BP-2023-24-455 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.32 | 0 | 0 | 0
2618 | PURBA BARDHAMAN | Central Mechanical | POALKURA PIPED WATER SUPPLY SCHEME , SM/14061 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at POALKURA Water Supply Scheme [ Block- BHATAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4181/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 27.65 | 14.46 | 52.29 | 40
2619 | PURBA BARDHAMAN | Burdwan Division | POALKURA PIPED WATER SUPPLY SCHEME , SM/14061 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NABASTA, PASHALA & POALKURA Piped Water Supply Scheme under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | 4652/BWD | 31/10/2023 | 898 | STARCO CONSTRUCTIONS | 900.17 | 82.83 | 31.89 | 2
2620 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES AT UNCOVERED VILLAGES IN ALL BLOCKS WITHIN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/14132 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 6 at Augmentation of Bhatar (Zone - II) (Bhumsor) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1310/CMD | 22/03/2023 | 30 | SUDIPTA GHOSH | 12.05 | 11.62 | 100 | 95
2621 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES AT UNCOVERED VILLAGES IN ALL BLOCKS WITHIN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/14132 | New | Quotation for new service connection at Nabagram PWSS TW-3 | BP-2024-25-381 | 14/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 19.77 | 0 | 0 | 0
2622 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES AT UNCOVERED VILLAGES IN ALL BLOCKS WITHIN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/14132 | New | Quotation for new service connection at Jahannagar Augmentation PWSS TW-3 | BP-2024-25-382 | 14/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.54 | 0 | 0 | 0
2623 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES AT UNCOVERED VILLAGES IN ALL BLOCKS WITHIN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/14132 | New | Implementation of Ground Water Based Mini Piped Water supply Scheme in 129 Nos. villages in Aushgram I & II, Burdwan I & II, Galsi I & II, Katwa I & II, Ketugream I & II, Raina I & II, Bhatar, Khandaghosh, Mongalkote and Memari II Block maximum 100 households in Purba Bardhaman district under Burdwan Division, PHE. Dte. | 641/BWD | 20/02/2023 | 1042 | BIRBHUM INFRAPARK PRIVATE LIMITED | 4231.72 | 1214.93 | 28.71 | 42
2624 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED MINI PIPED WATER SUPPLY SCHEMES AT UNCOVERED VILLAGES IN ALL BLOCKS WITHIN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/14132 | New | Designing, making and erection of Sign Board for SWAJAL GRAM in Jamaipota village of Raina-I Block under Mini Piped Water Supply Scheme (100 Household) within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos. Board) | 2341/BSD | 21/08/2025 | 10 | S.M. ENGOCON | 0.72 | 0 | 0 | 0
2625 | PURBA BARDHAMAN | Burdwan Division | ARJUNPUKUR PIPED WATER SUPPLY SCHEME , SM/13413 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 17.1 | 0 | 0 | 0
2626 | PURBA BARDHAMAN | Burdwan Division | ARJUNPUKUR PIPED WATER SUPPLY SCHEME , SM/13413 | New | Material Requisition To Resource Division | 4000/BWD | 08/09/2023 | 0 | Resource Division | 1.54 | 0 | 0 | 0
2627 | PURBA BARDHAMAN | Central Mechanical | ARJUNPUKUR PIPED WATER SUPPLY SCHEME , SM/13413 | New | New service connection charges for Arjunpukur PWSS Tw-1 | BP-2023-24-50 | 13/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0 | 0
2628 | PURBA BARDHAMAN | Central Mechanical | ARJUNPUKUR PIPED WATER SUPPLY SCHEME , SM/13413 | New | New service connection charges for Arjunpukur PWSS Tw-2 | BP-2023-24-51 | 13/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.05 | 0 | 0 | 0
2629 | PURBA BARDHAMAN | Central Mechanical | ARJUNPUKUR PIPED WATER SUPPLY SCHEME , SM/13413 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at ARJUNPUKUR Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2638/CMD | 14/06/2023 | 444 | ANJAN ENTERPRISE | 21.51 | 19.5 | 90.68 | 90
2630 | PURBA BARDHAMAN | Burdwan Division | ARJUNPUKUR PIPED WATER SUPPLY SCHEME , SM/13413 | New | Laying of additional pipeline and providing FHTC at ARJUNPUKUR Water Supply Scheme under Kalna Sub-Division, Burdwan Division, PHE Dte. | 2252/BWD | 18/06/2024 | 90 | IYASIN DAFADAR | 16.6 | 16.6 | 100 | 2
2631 | PURBA BARDHAMAN | Burdwan Division | ARJUNPUKUR PIPED WATER SUPPLY SCHEME , SM/13413 | New | Material Requisition To Resource Division | 314/BWD | 24/01/2024 | 0 | Resource Division | 14.63 | 0 | 0 | 0
2632 | PURBA BARDHAMAN | Central Mechanical | ARJUNPUKUR PIPED WATER SUPPLY SCHEME , SM/13413 | New | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3105/CMD | 11/12/2024 | 60 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0 | 0
2633 | PURBA BARDHAMAN | Burdwan Division | ARJUNPUKUR PIPED WATER SUPPLY SCHEME , SM/13413 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
2634 | PURBA BARDHAMAN | Central Mechanical | ARJUNPUKUR PIPED WATER SUPPLY SCHEME , SM/13413 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
2635 | PURBA BARDHAMAN | Burdwan Division | ARJUNPUKUR PIPED WATER SUPPLY SCHEME , SM/13413 | New | Work Order for " Laying distribution system including restorationof FHTC under the command area of Arjunpukur Piped water supply scheme (SM/13413) under Kalna Sub-Division under Burdwan Division, PHE Dte." | 1842/KSD | 27/11/2024 | 20 | IYASIN DAFADAR | 2.82 | 0 | 0 | 100
2636 | PURBA BARDHAMAN | Central Mechanical | TELUN PIPED WATER SUPPLY SCHEME , SM/13455 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Telun Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4171/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 29.82 | 0 | 0 | 0
2637 | PURBA BARDHAMAN | Burdwan Division | TELUN PIPED WATER SUPPLY SCHEME , SM/13455 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 7.19 | 0 | 0 | 0
2638 | PURBA BARDHAMAN | Burdwan Division | TELUN PIPED WATER SUPPLY SCHEME , SM/13455 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.11 | 0 | 0 | 0
2639 | PURBA BARDHAMAN | Burdwan Division | TELUN PIPED WATER SUPPLY SCHEME , SM/13455 | New | Material Requisition To Resource Division | 5258/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
2640 | PURBA BARDHAMAN | Central Mechanical | TELUN PIPED WATER SUPPLY SCHEME , SM/13455 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
2641 | PURBA BARDHAMAN | Central Mechanical | TELUN PIPED WATER SUPPLY SCHEME , SM/13455 | New | New service connection charges for Telun PWSS TW-1 | BP-2023-24-392 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.9 | 0 | 0 | 0
2642 | PURBA BARDHAMAN | Central Mechanical | TELUN PIPED WATER SUPPLY SCHEME , SM/13455 | New | Quotation for new service connection at TELUN W/S Scheme PH-II. | BP-2023-24-302 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.25 | 0 | 0 | 0
2643 | PURBA BARDHAMAN | Burdwan Division | TELUN PIPED WATER SUPPLY SCHEME , SM/13455 | New | TELUN Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KHANDAGHOSH Block, District:- Purba-Bardhaman [NEW SCHEME] | 1535/BWD | 29/03/2023 | 952 | G.B. CONSTRUCTION & CO. | 449.21 | 96.91 | 21.57 | 30
2644 | PURBA BARDHAMAN | Burdwan Division | TELUN PIPED WATER SUPPLY SCHEME , SM/13455 | New | Balance work for providing Functional Household Tap Connection (FHTC) within the command area BICHKHARA & TELUN W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | 434/BWD | 20/01/2025 | 182 | KOUSIK MALLICK | 108.55 | 0 | 0 | 50
2645 | PURBA BARDHAMAN | Burdwan Division | TELUN PIPED WATER SUPPLY SCHEME , SM/13455 | New | Land demarcation and preparation of sketch map including legal charges for different PWSS under JJM of Khandaghosh Block under Duragapur (Burdwan North) Sub-Division, P.H.E. DTE. [Part-A] | 158/DSD | 27/01/2025 | 180 | SHUBHRA KANTI GHOSH | 0.81 | 0 | 0 | 90
2646 | PURBA BARDHAMAN | Burdwan Division | BALABATI PIPED WATER SUPPLY SCHEME , SM/13457 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.2 | 0 | 0 | 0
2647 | PURBA BARDHAMAN | Burdwan Division | BALABATI PIPED WATER SUPPLY SCHEME , SM/13457 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 9.06 | 0 | 0 | 0
2648 | PURBA BARDHAMAN | Burdwan Division | BALABATI PIPED WATER SUPPLY SCHEME , SM/13457 | New | Material Requisition To Resource Division | 5048/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
2649 | PURBA BARDHAMAN | Central Mechanical | BALABATI PIPED WATER SUPPLY SCHEME , SM/13457 | New | New service connection charges for Balabati PWSS TW-1 | BP-2023-24-283 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.89 | 0 | 0 | 0
2650 | PURBA BARDHAMAN | Central Mechanical | BALABATI PIPED WATER SUPPLY SCHEME , SM/13457 | New | Electric quotation for New Service Connection at Balabati W/S Scehem PH-2. | BP-2023-24-284 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.71 | 0 | 0 | 0
2651 | PURBA BARDHAMAN | Burdwan Division | BALABATI PIPED WATER SUPPLY SCHEME , SM/13457 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMRA, BALABATI, UKHRID & RUPSA Piped Water Supply Scheme under KHANDAGHOSH Block, District:- Purba Bardhaman [NEW SCHEME] | 1726/BWD | 13/04/2023 | 902 | S.P. CONSTRUCTION | 1710.27 | 271.5 | 75.42 | 45
2652 | PURBA BARDHAMAN | Central Mechanical | BALABATI PIPED WATER SUPPLY SCHEME , SM/13457 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
2653 | PURBA BARDHAMAN | Burdwan Division | BALABATI PIPED WATER SUPPLY SCHEME , SM/13457 | New | Balance work for providing Functional Household Tap Connection (FHTC) within the command area BALABATI, AMRA & RUPSA W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | 609/BWD | 11/02/2025 | 120 | M/S S.S. ENTERPRISE | 194.58 | 0 | 0 | 0
2654 | PURBA BARDHAMAN | Central Mechanical | BALABATI PIPED WATER SUPPLY SCHEME , SM/13457 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Balabati Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4011/CMD | 29/08/2023 | 369 | UNIVERSAL ENTERPRISES | 28.95 | 22.78 | 95.21 | 100
2655 | PURBA BARDHAMAN | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | Material Requisition To Resource Division | 1642/BWD | 06/04/2023 | 0 | Resource Division | 1.83 | 0 | 0 | 0
2656 | PURBA BARDHAMAN | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | Material Requisition To Resource Division | 1261/BWD | 17/03/2023 | 0 | Resource Division | 7.73 | 0 | 0 | 0
2657 | PURBA BARDHAMAN | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | Material Requisition To Resource Division | 4879/BWD | 10/11/2023 | 0 | Resource Division | 31.56 | 0 | 0 | 0
2658 | PURBA BARDHAMAN | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.06.2024 to 31.07.2024] | 306/AE/HQ | 31/05/2024 | 61 | MD HASIN | 0.8 | 0.77 | 96.63 | 0
2659 | PURBA BARDHAMAN | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.10.2024 to 30.11.2024] | 802/AE/HQ | 30/09/2024 | 61 | MD HASIN | 0.8 | 0.63 | 78.89 | 0
2660 | PURBA BARDHAMAN | Central Mechanical | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
2661 | PURBA BARDHAMAN | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.08.2024 to 30.09.2024] | 547/AE/HQ | 01/08/2024 | 61 | MD HASIN | 0.8 | 0.74 | 92.9 | 0
2662 | PURBA BARDHAMAN | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.02.2024 to 31.03.2024] | 43/AE/HQ | 29/01/2024 | 60 | MD HASIN | 0.8 | 0.76 | 95.59 | 0
2663 | PURBA BARDHAMAN | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | Different work for MERA PWSS (Mustafapur, Arangabad and Mera mouza) plinth protection for pump house & OHR under MERA PWSS, at Katwa -I Block under Katwa Sub-Division under Burdwan Division PHE Dte. | 4374/BWD | 13/12/2024 | 90 | J.K. CORPORATION | 51.3 | 0 | 0 | 0
2664 | PURBA BARDHAMAN | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.04.2024 to 31.05.2024] | 236/AE/HQ | 28/03/2024 | 61 | MD HASIN | 0.8 | 0.76 | 94.41 | 0
2665 | PURBA BARDHAMAN | Central Mechanical | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MERA Water Supply Scheme [ Block- KATWA-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4149/CMD | 29/08/2023 | 30 | GOENKA ENTERPRISE | 26.98 | 21.2 | 95.13 | 91
2666 | PURBA BARDHAMAN | Central Mechanical | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | New service connection for MERA PWSS TW 2. | BP-2023-24-525 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.08 | 0 | 0 | 0
2667 | PURBA BARDHAMAN | Central Mechanical | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | New Service connection for Mera PWSS TW-1 | BP-2023-24-462 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.98 | 0 | 0 | 0
2668 | PURBA BARDHAMAN | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.12.2024 to 31.01.2025] | 1010/AE/HQ | 29/11/2024 | 61 | MD HASIN | 0.8 | 0.72 | 90.39 | 0
2669 | PURBA BARDHAMAN | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.02.2025 to 31.03.2025] | 186/AE/HQ | 31/01/2025 | 59 | MD HASIN | 0.8 | 0.62 | 77.07 | 0
2670 | PURBA BARDHAMAN | Burdwan Division | MERA PIPE WATER SUPPLY SCHEME , SM/15575 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. [Period from 01.10.2025 to 30.11.2025] | 1195/AE/HQ | 24/09/2025 | 61 | MD HASIN | 0.8 | 0 | 0 | 0
2671 | PURBA BARDHAMAN | Burdwan Division | DHENRIA PIPED WATER SUPPLY SCHEME , SM/15246 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 8.61 | 0 | 0 | 0
2672 | PURBA BARDHAMAN | Burdwan Division | DHENRIA PIPED WATER SUPPLY SCHEME , SM/15246 | New | Material Requisition To Resource Division | 4930/BWD | 10/11/2023 | 0 | Resource Division | 34.57 | 0 | 0 | 0
2673 | PURBA BARDHAMAN | Burdwan Division | DHENRIA PIPED WATER SUPPLY SCHEME , SM/15246 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 31.52 | 0 | 0 | 0
2674 | PURBA BARDHAMAN | Central Mechanical | DHENRIA PIPED WATER SUPPLY SCHEME , SM/15246 | New | New service connection charges for Dhenria PWSS TW-1 | BP-2023-24-147 | 31/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0 | 0
2675 | PURBA BARDHAMAN | Central Mechanical | DHENRIA PIPED WATER SUPPLY SCHEME , SM/15246 | New | New service connection charges for Dhenria PWSS TW-2 | BP-2023-24-167 | 27/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.71 | 0 | 0 | 0
2676 | PURBA BARDHAMAN | Central Mechanical | DHENRIA PIPED WATER SUPPLY SCHEME , SM/15246 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at DHENRIA Water Supply Scheme [ Block-BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3872/CMD | 17/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 27.79 | 21.41 | 77.06 | 90
2677 | PURBA BARDHAMAN | Central Mechanical | DHENRIA PIPED WATER SUPPLY SCHEME , SM/15246 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
2678 | PURBA BARDHAMAN | Burdwan Division | DHENRIA PIPED WATER SUPPLY SCHEME , SM/15246 | New | Material Requisition To Resource Division | 325/BWD | 24/01/2024 | 0 | Resource Division | 6.44 | 0 | 0 | 0
2679 | PURBA BARDHAMAN | Burdwan Division | DHENRIA PIPED WATER SUPPLY SCHEME , SM/15246 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DHENRIA, MAHATA, DEBPUR Piped Water Supply Scheme under BHATAR Block, District:- Purba-Bardhaman [NEW SCHEME] | 1737/BWD | 13/04/2023 | 993 | M/S B. RAI CONSTRUCTION COMPANY | 1643.39 | 251.96 | 47.97 | 81
2680 | PURBA BARDHAMAN | Burdwan Division | DHENRIA PIPED WATER SUPPLY SCHEME , SM/15246 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day. [PeriodFebruary.'2025 to April'2025] | 129/DSD | 29/01/2025 | 78 | MD HASIN | 1 | 0 | 0 | 0
2681 | PURBA BARDHAMAN | Burdwan Division | DHENRIA PIPED WATER SUPPLY SCHEME , SM/15246 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period NOV.'2024 to JAN.'2025] | 886/DSD | 21/10/2024 | 78 | MD HASIN | 1 | 0.33 | 100 | 0
2682 | PURBA BARDHAMAN | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14969 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 18.45 | 0 | 0 | 0
2683 | PURBA BARDHAMAN | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14969 | New | Material Requisition To Resource Division | 4034/BWD | 08/09/2023 | 0 | Resource Division | 3.06 | 0 | 0 | 0
2684 | PURBA BARDHAMAN | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14969 | New | Material Requisition To Resource Division | 299/BWD | 24/01/2024 | 0 | Resource Division | 14.63 | 0 | 0 | 0
2685 | PURBA BARDHAMAN | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14969 | New | Additional Quotation for new service connection for Sahapur PWSS, PH-1. | BP-2024-25-152 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.86 | 0 | 0 | 0
2686 | PURBA BARDHAMAN | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14969 | New | New service connection charges for Sahapur PWSS TW-2 | BP-2023-24-337 | 06/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.21 | 0 | 0 | 0
2687 | PURBA BARDHAMAN | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14969 | New | New service connection for Sahapur PWSS. | BP-2023-24-389 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.86 | 0 | 0 | 0
2688 | PURBA BARDHAMAN | Burdwan Division | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14969 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NAMA BHANDARITURI, SAHAPUR & MOUDANGA Piped Water Supply Scheme under PURBASTHALI-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3689/BWD | 23/08/2023 | 770 | THE MAHADEV CONSTRUCTION | 734.18 | 147.39 | 60.11 | 50
2689 | PURBA BARDHAMAN | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14969 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 30
2690 | PURBA BARDHAMAN | Central Mechanical | SAHAPUR PIPED WATER SUPPLY SCHEME , SM/14969 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at SAHAPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2473/CMD | 30/05/2023 | 30 | MAA KALI ENTERPRISE | 20.8 | 18.94 | 94.58 | 90
2691 | PURBA BARDHAMAN | Burdwan Division | SHIBLUN PIPE WATER SUPPLY SCHEME , SM/14972 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.1 | 0 | 0 | 0
2692 | PURBA BARDHAMAN | Burdwan Division | SHIBLUN PIPE WATER SUPPLY SCHEME , SM/14972 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 75.98 | 0 | 0 | 0
2693 | PURBA BARDHAMAN | Burdwan Division | SHIBLUN PIPE WATER SUPPLY SCHEME , SM/14972 | New | Material Requisition To Resource Division | 5246/BWD | 30/11/2023 | 0 | Resource Division | 18.9 | 0 | 0 | 0
2694 | PURBA BARDHAMAN | Burdwan Division | SHIBLUN PIPE WATER SUPPLY SCHEME , SM/14972 | New | Material Requisition To Resource Division | 4011/BWD | 08/09/2023 | 0 | Resource Division | 1.1 | 0 | 0 | 0
2695 | PURBA BARDHAMAN | Central Mechanical | SHIBLUN PIPE WATER SUPPLY SCHEME , SM/14972 | New | New service connection charges for Shiblun PWSS TW-2 | BP-2023-24-133 | 22/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.04 | 0 | 0 | 0
2696 | PURBA BARDHAMAN | Central Mechanical | SHIBLUN PIPE WATER SUPPLY SCHEME , SM/14972 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
2697 | PURBA BARDHAMAN | Central Mechanical | SHIBLUN PIPE WATER SUPPLY SCHEME , SM/14972 | New | REVISED QUOTATION FOR NEW SERVICE CONNECTION AT SHIBLUN PWSS TW-1 | BP-2024-25-190 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.19 | 0 | 0 | 0
2698 | PURBA BARDHAMAN | Central Mechanical | SHIBLUN PIPE WATER SUPPLY SCHEME , SM/14972 | New | New service connection charges for Shiblun PWSS TW-1 | BP-2023-24-368 | 15/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.19 | 0 | 0 | 0
2699 | PURBA BARDHAMAN | Burdwan Division | SHIBLUN PIPE WATER SUPPLY SCHEME , SM/14972 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHARKHI & SHIBNUL Piped Water Supply Scheme under KETUGRAM-II Block, District:- Purba Bardhaman [NEW SCHEME] | 1823/BWD | 18/04/2023 | 1293 | PASCON | 723.75 | 174.88 | 52.7 | 35
2700 | PURBA BARDHAMAN | Burdwan Division | SHIBLUN PIPE WATER SUPPLY SCHEME , SM/14972 | New | Balance work for OHR, extension of pipeline to provide FHTC with land development, plinth protection for pump house & OHR under SIBLUN PWSS, Block-Ketugram-II under Katwa Sub Division within Burdwan Division PHE Dte. | 2835/BWD | 19/07/2024 | 835 | PASCON | 84.02 | 0 | 0 | 80
2701 | PURBA BARDHAMAN | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15583 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.02 | 0 | 0 | 0
2702 | PURBA BARDHAMAN | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15583 | New | Route Survey & Preparation of DPR for GOPALPUR W/S Scheme under Burdwan-I Block under Burdwan Sub- Division under Burdwan Division PHE Dte. | 2584/BSD | 26/11/2024 | 45 | APEX ENGINEERING | 2.71 | 0 | 0 | 0
2703 | PURBA BARDHAMAN | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15583 | New | New Service connection at GOPALPUR PWSS TW-2. | BP-2023-24-483 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.65 | 0 | 0 | 0
2704 | PURBA BARDHAMAN | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15583 | New | New service connection for Gopalpur PWSS TW-1. | BP-2023-24-433 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4 | 0 | 0 | 0
2705 | PURBA BARDHAMAN | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15583 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at GOPALPUR Water Supply Scheme [Block-JAMALPUR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4168/CMD | 29/08/2023 | 546 | SOUNAK ENTERPRISE | 22.1 | 0 | 0 | 100
2706 | PURBA BARDHAMAN | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15583 | New | GOPALPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Jamalpur Block, District:- Purba-Bardhaman [NEW SCHEME] | 2305/BWD | 19/05/2023 | 757 | IJABUL SEKH | 266.75 | 83.04 | 52.32 | 100
2707 | PURBA BARDHAMAN | Burdwan Division | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. , SM/15586 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 8.53 | 0 | 0 | 0
2708 | PURBA BARDHAMAN | Burdwan Division | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. , SM/15586 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.27 | 0 | 0 | 0
2709 | PURBA BARDHAMAN | Burdwan Division | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. , SM/15586 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR CHAKSIMLA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 2020/KSD | 06/03/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.66 | 100 | 2
2710 | PURBA BARDHAMAN | Burdwan Division | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. , SM/15586 | New | Material Requisition To Resource Division | 318/BWD | 24/01/2024 | 0 | Resource Division | 30.81 | 0 | 0 | 0
2711 | PURBA BARDHAMAN | Central Mechanical | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. , SM/15586 | New | New service connection at Chak Shimla PWSS Ph-1 | BP-2023-24-449 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.74 | 0 | 0 | 0
2712 | PURBA BARDHAMAN | Central Mechanical | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. , SM/15586 | New | New service connection at Chak Shimla PWSS Ph-2 | BP-2023-24-450 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.35 | 0 | 0 | 0
2713 | PURBA BARDHAMAN | Burdwan Division | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. , SM/15586 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALINDAR, CHAK SHIMLA & DWARIATAN Piped Water Supply Scheme under Kalna II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3700/BWD | 24/08/2023 | 770 | SUPRITI ENTERPRISE | 1424.22 | 65.09 | 17.91 | 30
2714 | PURBA BARDHAMAN | Burdwan Division | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. , SM/15586 | New | Different types of works involve in connection with Augmentation of TEHATA Zone-I & II (SM/16301) Water Supply Scheme, CHAKSIMLA (SM/15586) Water Supply Scheme & DWARIATON (SM/16285) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2201/BWD | 13/06/2024 | 752 | M/S ASHA CONSTRUCTION | 449.98 | 196.66 | 89.39 | 25
2715 | PURBA BARDHAMAN | Central Mechanical | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. , SM/15586 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
2716 | PURBA BARDHAMAN | Central Mechanical | CHAK SHIMLA PIPE WATER SUPPLY SCHEME. , SM/15586 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHAK SIMLA Water Supply Scheme [ Block-KALNA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | 4194/CMD | 29/08/2023 | 735 | J.S. CONSTRUCTION. | 28.48 | 0 | 0 | 40
2717 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MUGURA , SM/16488 | Retrofitting | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of MUGURA Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1429/BWD | 24/03/2023 | 30 | J K CORPORATION | 18.57 | 18.56 | 100 | 100
2718 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MUGURA , SM/16488 | Retrofitting | Preparation and Submission of DPR for Retrofitting of Mugura PWSS under Raina-I Development Block under Burdwan Division, P.H.E Dte(2nd Call) | 2831/BSD | 07/12/2023 | 15 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
2719 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR MUGURA , SM/16488 | Retrofitting | Laying Parallel Pipeline to improve drinking water supply, Construction of Boundary wall, Path Way, Drain at Head Work Site & 2nd TW Site and providing leftout FHTC, Road Restoration with allied work for MUGRA Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | 2711/BWD | 11/07/2024 | 2720 | M/S PURBASHA | 40.24 | 0 | 0 | 90
2720 | PURBA BARDHAMAN | Burdwan Division | JAJIGRAM PIPE WATER SUPPLY SCHEME , SM/15151 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.59 | 0 | 0 | 0
2721 | PURBA BARDHAMAN | Burdwan Division | JAJIGRAM PIPE WATER SUPPLY SCHEME , SM/15151 | New | Material Requisition To Resource Division | 4016/BWD | 08/09/2023 | 0 | Resource Division | 0.97 | 0 | 0 | 0
2722 | PURBA BARDHAMAN | Burdwan Division | JAJIGRAM PIPE WATER SUPPLY SCHEME , SM/15151 | New | Material Requisition To Resource Division | 4883/BWD | 10/11/2023 | 0 | Resource Division | 28.85 | 0 | 0 | 0
2723 | PURBA BARDHAMAN | Central Mechanical | JAJIGRAM PIPE WATER SUPPLY SCHEME , SM/15151 | New | New service connection charges for Jajigram PWSS TW-2 | BP-2023-24-206 | 30/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.31 | 0 | 0 | 0
2724 | PURBA BARDHAMAN | Central Mechanical | JAJIGRAM PIPE WATER SUPPLY SCHEME , SM/15151 | New | New service connection charges for Jajigram PWSS TW-1 | BP-2023-24-174 | 29/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.42 | 0 | 0 | 0
2725 | PURBA BARDHAMAN | Central Mechanical | JAJIGRAM PIPE WATER SUPPLY SCHEME , SM/15151 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
2726 | PURBA BARDHAMAN | Central Mechanical | JAJIGRAM PIPE WATER SUPPLY SCHEME , SM/15151 | New | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3106/CMD | 11/12/2024 | 60 | S.K. ELECTRICALS | 13.6 | 0 | 0 | 0
2727 | PURBA BARDHAMAN | Burdwan Division | JAJIGRAM PIPE WATER SUPPLY SCHEME , SM/15151 | New | JAJIGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -I Block, District:- Purba-Bardhaman [NEW SCHEME] | 1135/BWD | 13/03/2023 | 1115 | POWER TOOLS & ENGINEERING | 368.83 | 284.13 | 77.04 | 75
2728 | PURBA BARDHAMAN | Burdwan Division | JAJIGRAM PIPE WATER SUPPLY SCHEME , SM/15151 | New | Construction of Office Cum Godown at Head work site of JAJIGRAM PWSS under Katwa Sub Division, within Burdwan Division PHE Dte. | 5201/BWD | 29/11/2023 | 180 | SUBODH KUMAR MONDAL | 37.69 | 32.7 | 86.77 | 10
2729 | PURBA BARDHAMAN | Burdwan Division | JAJIGRAM PIPE WATER SUPPLY SCHEME , SM/15151 | New | Balance work for the construction of office cum Go-Down at ground floor at the head work site of JAJIGRAM PWSS under Katwa I Block under Katwa Sub-Division under Burdwan Division, PHE. Dte. | 106/BWD | 07/01/2025 | 60 | SUBODH KUMAR MONDAL | 9.11 | 0 | 0 | 0
2730 | PURBA BARDHAMAN | Central Mechanical | JAJIGRAM PIPE WATER SUPPLY SCHEME , SM/15151 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JAJIGRAM Water Supply Scheme [ Block- KATWA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4123/CMD | 29/08/2023 | 415 | M/S, N.G. ENTERPRISES. | 26.94 | 0 | 0 | 100
2731 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN , SM/15194 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Augmentation of Chhotoboinan Water Supply Scheme [ Block- Raina-II ] ( Tube Well no 4 ) under CMD, PHE Dte., Dist.- Purba-Bardhaman | 3142/CMD | 29/11/2022 | 30 | CHATTERJEE ENTERPRISE | 10.99 | 10.6 | 96.53 | 0
2732 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN , SM/15194 | Augmentation | Laying of Interconnection of 3rd Tube well Site of Chotobainan Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 737/BSD | 20/04/2023 | 15 | BRINDABAN KONAR | 0.93 | 0.9 | 100 | 100
2733 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN , SM/15194 | Augmentation | Providing Electrical accessories for Tube well No. 2 of Chotobainan & others Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4347/CMD | 19/09/2023 | 30 | DUTTA ENTERPRISE | 3.09 | 3.09 | 100 | 100
2734 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN , SM/15194 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Chotoboinan Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2590/CMD | 07/06/2023 | 30 | CHOUDHURY ENTERPRISE | 22.51 | 10.52 | 46.73 | 48
2735 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN , SM/15194 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of CHHOTOBAINAN (NILEDIGHIR PAR) W/S Scheme under Raina-II Block within Burdwan Sub-Division, PHE Dte. [For 01 No. Tube well]. | 3768/BWD | 29/08/2023 | 30 | B.S. ENTERPRISE | 13.13 | 10.52 | 100 | 100
2736 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN , SM/15194 | Augmentation | Procurement of electro-mechanical accessories for Chotoboinan Water Supply Scheme under JJM under CMD, PHE Dte. | 529/CMSD | 07/07/2023 | 30 | JOYGURU ENTERPRISE | 0.84 | 0.84 | 100 | 99
2737 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN , SM/15194 | Augmentation | Construction of Switch room cum chlorine room with sanitary and water supply arrangement (P.H-4) at New Tube Well Site of CHOTOBAINAN and its adjoining Mouzas Pipe Water Supply Scheme of cracky nature of soil according to departmental drawing no.-PHE/BD/P.H/DRG-01/DCE-2017, Block:- Raina-II, under Burdwan Sub-Division, P.H.E Dte. within Burdwan Division P.H.E. Dte. Dist:Purba Bardhaman. | 001/BWD | 02/01/2024 | 60 | CHOWDHURY CONSTRUCTION | 5.83 | 5.16 | 100 | 99
2738 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN , SM/15194 | Augmentation | Preparation and Submission of DPR for Augmentation of Chhotobainan PWSS under Raina-II Development Block under Burdwan Division, P.H.E Dte (2nd Call) | 2974/BSD | 20/12/2023 | 15 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
2739 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN , SM/15194 | Augmentation | Improvement/ Strenthenning of RCC Elevated Reservoir (Capacity 700 Cum) & pipe line of CHOTOBAINAN PWSS for smooth running of FHTC work under RAINA-II Block, District:- Purba- Bardhaman. | 1277/BSD | 12/07/2024 | 60 | ANWESHA CONSTRUCTION | 3.34 | 0 | 0 | 100
2740 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN , SM/15194 | Augmentation | New service connection for Augmentation of Chotoboinan PWSS TW-4. | BP-2023-24-435 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.66 | 0 | 0 | 0
2741 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN , SM/15194 | Augmentation | Balance Work for extension of pipe lines to provide FHTC With Sinking of Tubwell (Replacement TW), Repairing of pump house with Boundary wall at head worksite & other related works for CHOTOBAINAN PWSS under Burdwan Sub-Div., Block -Raina-II, under Burdwan Division PHE Dte. | 435/BWD | 20/01/2025 | 120 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 106.18 | 0 | 0 | 0
2742 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR CHHOTOBAINAN , SM/15194 | Augmentation | Pipeline with FHTC for CHOTOBAINAN Water Supply Scheme at Gopalpur village (400 Nos), Akhina village (250 Nos) within Raina-II Block, under Burdwan Division, PHE Dte. | 1498/BWD | 28/03/2023 | 614 | BRINDABAN KONAR | 59.24 | 42.2 | 65.94 | 100
2743 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF PANUHAT PIPED WATER SUPPLY SCHEME , SM/15555 | Augmentation | Yard lighting arrangement & allied works at Panuhat water supply scheme under Katwa-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2791/CMD | 01/10/2024 | 60 | BEHERA ENTERPRISE | 7.11 | 0 | 0 | 0
2744 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF PANUHAT PIPED WATER SUPPLY SCHEME , SM/15555 | Augmentation | NEW SERVICE CONNECTION FOR ADDITIONAL TUBE WELL AT PANUHAT | BP-2024-25-62 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.52 | 0 | 0 | 0
2745 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF PANUHAT PIPED WATER SUPPLY SCHEME , SM/15555 | Augmentation | Quotation for new service connection at Augmentation of Panuhat PWSS TW - 01. | BP-2024-25-283 | 10/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.98 | 0 | 0 | 0
2746 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PANUHAT PIPED WATER SUPPLY SCHEME , SM/15555 | Augmentation | Construction of Pump House, Boundary walls and Raising Main for Aug. of PANUHAT Piped W/S. Scheme under Katwa-I Block, District:- Purba-Bardhaman. | 5484/BWD | 13/12/2023 | 60 | SUBODH KUMAR MONDAL | 9.73 | 2.16 | 22.2 | 26
2747 | PURBA BARDHAMAN | Central Drilling | KULUTIA PIPED WATER SUPPLY SCHEME , SM/15167 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Kulutia W/S Scheme (T/W-I & II) ,Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | 1349/CDD | 13/09/2023 | 30 | UNIVERSAL ENTERPRISES | 16.66 | 0 | 0 | 0
2748 | PURBA BARDHAMAN | Burdwan Division | KULUTIA PIPED WATER SUPPLY SCHEME , SM/15167 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.23 | 0 | 0 | 0
2749 | PURBA BARDHAMAN | Burdwan Division | KULUTIA PIPED WATER SUPPLY SCHEME , SM/15167 | New | Material Requisition To Resource Division | 3825/BWD | 01/09/2023 | 0 | Resource Division | 2.16 | 0 | 0 | 0
2750 | PURBA BARDHAMAN | Burdwan Division | KULUTIA PIPED WATER SUPPLY SCHEME , SM/15167 | New | Material Requisition To Resource Division | 5240/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0 | 0
2751 | PURBA BARDHAMAN | Central Mechanical | KULUTIA PIPED WATER SUPPLY SCHEME , SM/15167 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
2752 | PURBA BARDHAMAN | Central Mechanical | KULUTIA PIPED WATER SUPPLY SCHEME , SM/15167 | New | New Service connection at Kulutia PWSS TW NO. 1 | BP-2023-24-491 | 01/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.01 | 0 | 0 | 0
2753 | PURBA BARDHAMAN | Central Mechanical | KULUTIA PIPED WATER SUPPLY SCHEME , SM/15167 | New | New service connection for Kulitia PWSS PH-2. | BP-2023-24-623 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.19 | 0 | 0 | 0
2754 | PURBA BARDHAMAN | Burdwan Division | KULUTIA PIPED WATER SUPPLY SCHEME , SM/15167 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMEGERIA, ARGUN, CHINISPUR & KULUTIA Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3630/BWD | 21/08/2023 | 1107 | M/S GOUTAM DAS | 1421.7 | 139.29 | 33.82 | 75
2755 | PURBA BARDHAMAN | Central Mechanical | KULUTIA PIPED WATER SUPPLY SCHEME , SM/15167 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KULUTIA Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4124/CMD | 29/08/2023 | 610 | KAMAKHYA ENTERPRISE | 26.93 | 0 | 0 | 46
2756 | PURBA BARDHAMAN | Burdwan Division | KULUTIA PIPED WATER SUPPLY SCHEME , SM/15167 | New | Road crossing through metal / concrete road by Jack Push Method for AMEGERIA (SM/16023), ARGUN (SM/16482), CHINISPUR (SM/15170) and KULITIA (SM/15167) PWSS under Ketugram I Development Block under Katwa Sub Division within Burdwan Division, PHE. Dte. | 977/BWD | 13/03/2025 | 60 | M/S GOUTAM DAS | 39.22 | 0 | 0 | 100
2757 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR , SM/15181 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of BALARAMPUR W/S Scheme under Jamalpur Block within Burdwan Sub-Division, PHE Dte. | 2705/BWD | 08/06/2023 | 30 | TULIP ENGINEERS CO-OPERATIVE SOCIETY LTD. | 13.26 | 12.64 | 100 | 100
2758 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR , SM/15181 | Augmentation | Preparation and Submission of DPR for Augmentation of Balarampur PWSS under Jamalpur Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1528/BSD | 17/07/2023 | 15 | GEO-SOLUTION | 0.78 | 0.77 | 100 | 100
2759 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR , SM/15181 | Augmentation | Extension of CIDF/DI Pipes with specials within command area of Balarampur piped W/S Scheme at Shalim Danga Sabgi Bazar,,Jamalpur Development Block under Burdwan Division,PHE Dte. [2nd Call]. | 789/BSD | 28/04/2023 | 15 | GHOSH ENTERPRISE | 0.32 | 0.32 | 100 | 100
2760 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR , SM/15181 | Augmentation | Construction of switch rooms & Rising main at different TW site for BALARAMPUR Piped Water Supply Scheme under Jamalpur Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | 3769/BWD | 29/08/2023 | 60 | SOUMYAVASH DAS | 8.94 | 8.91 | 100 | 100
2761 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR , SM/15181 | Augmentation | Procurement of electro-mechanical accessories for Balarampur Water Supply Scheme under JJM under CMD, PHE Dte. | 531/CMSD | 07/07/2023 | 30 | M/S. S.D. CONSTRUCTION | 0.58 | 0.58 | 100 | 100
2762 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR , SM/15181 | Augmentation | New Service connection at BALARAMPUR PWSS TW-5. | BP-2023-24-482 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 16.19 | 0 | 0 | 0
2763 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR , SM/15181 | Augmentation | New service connection charges for Balarampur PWSS TW-4 | BP-2023-24-386 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.6 | 0 | 0 | 0
2764 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR , SM/15181 | Augmentation | Illumination arrangement and miscellaneous works at Balarampur water supply scheme under Jamalpur Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2786/CMD | 01/10/2024 | 60 | A.K. ENTERPRISE | 15.91 | 0 | 0 | 30
2765 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR , SM/15181 | Augmentation | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 0 | 40
2766 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR , SM/15181 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Balarampur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2589/CMD | 07/06/2023 | 697 | P.K. ENGINEERING | 22.61 | 20.69 | 94.88 | 90
2767 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR , SM/15181 | Augmentation | Construction of (i) Pump House cum chlorine room without sanitary and water supply arrangement at 5th Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/ DEC-17 (Size 3.60 mtr x 3.00 mtr room), (CD) and UPVC Deep Well Screen (RDS), (ii) Interconnection between pump house & delivery line for BALARAMPUR W/S Scheme under Jamalpur Block under Burdwan Division, PHE Dte. | 832/BWD | 29/02/2024 | 30 | SK KHAIRUL ISLAM | 4.79 | 0 | 0 | 100
2768 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR , SM/15181 | Augmentation | Construction of boundary wall at 4Th Tubewell of BALARAMPUR PWSS at Jamalpur Block under Burdwan Division, PHE Dte. (Length -110 Mtr, Col-42 Nos). | 4300/BWD | 10/12/2024 | 30 | MOFIZ UDDIN MOLLICK | 9.09 | 0 | 0 | 100
2769 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR , SM/15181 | Augmentation | Re-Laying of HDPE Pipeline (Damaged during flood) at Shalimdanga Bazar,Balarampur PWSS under Jamalpur Dev. Block, Burdwan Division, PHE Dte. | 263/AE/HQ | 18/02/2025 | 30 | SOUMYAVASH DAS | 1.63 | 0 | 0 | 100
2770 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BALARAMPUR , SM/15181 | Augmentation | Land Possession Display Board at BALARAMPUR PWSS & Other schemes (Total=82 Nos) under JAMALPUR Block. Under Burdwan Div. PHE Dte. | 352/AE/HQ | 10/03/2025 | 30 | M/S ANAND CONSTRUCTION | 3.36 | 0 | 0 | 100
2771 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for SHYAMSUNDAR its Adjoining Mouza W/S Scheme, Block -Raina-I within Burdwan Sub-Division, PHE Dte. (Mouza- Gopinathpur) | 505/BSD | 21/03/2023 | 45 | JYOTI ENTERPRISE | 3.5 | 2.76 | 100 | 100
2772 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | New service connection charges for Aug. Shyamsundar PWSS TW-4 | BP-2023-24-150 | 05/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.25 | 0 | 0 | 0
2773 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | New service connection charges for Aug. of Shyamsundar PWSS TW-1 | BP-2023-24-104 | 07/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.18 | 0 | 0 | 0
2774 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | Construction of Pathway at Head Work site for SHYAMSUNDAR PIPED WATER SUPPLY SCHEME , Block- Raina-I , within Burdwan Sub Division under Burdwan Division PHE Dte. | 1040/BSD | 10/06/2024 | 30 | POMPA CONSTRUCTION CO. | 0.93 | 0 | 0 | 0
2775 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | Laying Parallel Pipeline, providing FHTC and Repairing of Pump House at 2nd Tube Well Site for Aug. of SHYAMSUNDAR Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | 2524/BWD | 03/07/2024 | 90 | DEBASHISH ENTERPRISE | 22.66 | 0 | 0 | 0
2776 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | Augmentation of SHYAMSUNDAR Piped Water Supply Scheme with LDS, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test, Construction of boundary wall at Head works & 2nd TW site & FHTC under Raina ¿ I Block, District - Purba Bardhaman. | 1474/BWD | 14/03/2022 | 365 | SK ALIM | 474.78 | 61.66 | 100 | 100
2777 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | Allied works for Augmentation of SHYAMSUNDAR W/S Scheme under Burdwan Division, PHE. Dte. | 3035/BWD | 14/07/2023 | 90 | SK ALIM | 113.11 | 94.14 | 100 | 100
2778 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | Making illumination arrangement and mise works at SHYAMSUNDAR water supply scheme RAINA-I BLOCK under Central Mechanical Division P.H.E. Dte. Purba-Bardhaman. | 2954/CMD | 20/11/2024 | 60 | CHATTERJEE ENTERPRISE | 14.87 | 0 | 0 | 30
2779 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Muktipur village of Raina-I Block under Shyamsundar Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte (5 nos Board) | 2369/BSD | 21/08/2025 | 10 | S.M. ENGOCON | 0.72 | 0 | 0 | 0
2780 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of SHYAMSUNDAR(Part-B)[RAINA-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3901/CMD | 18/08/2023 | 286 | SOUNAK ENTERPRISE | 24.41 | 23.77 | 100 | 90
2781 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | Construction of Drain at Head Work site for SHYAMSUNDAR PIPED WATER SUPPLY SCHEME , Block- Raina-I , within Burdwan Sub Division under Burdwan Division PHE Dte | 1041/BSD | 10/06/2024 | 30 | LAKSHMIKANTA DAS | 0.93 | 0 | 0 | 100
2782 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | Restore of pipeline damaged by construction of Pathashree Road near Muktipur Village for SHYAMSUNDAR PIPED WATER SUPPLY SCHEME , Block- Raina-I , within Burdwan Sub Division under Burdwan Division PHE Dte. | 1865/BSD | 22/08/2024 | 30 | MAA MAHAMAYA CONSTRUCTION | 0.97 | 0 | 0 | 100
2783 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | Restore of pipeline damaged by construction of pathashree road near Surya Pally for SHYAMSUNDAR Piped Water Supply Scheme,Block:Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | 10/BSD | 02/01/2025 | 15 | MAA MAHAMAYA CONSTRUCTION | 0.97 | 0 | 0 | 100
2784 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | Re- Connection of existing FHTC [54Nos.] damaged by construction of PATHASHREE ROAD for SHYAMSUNDA RPIPED WATER SUPPLY SCHEME,Block-Raina-I,within Burdwan Sub Division under Burdwan Division PHE Dte. | 1862/BSD | 22/08/2024 | 30 | MAA MAHAMAYA CONSTRUCTION | 0.95 | 0.25 | 20.94 | 100
2785 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | Restore of pipeline damaged by construction of pathashree road near Shyamsundar Grils School for SHYAMSUNDAR Piped Water Supply Scheme,Block:Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte | 506/BSD | 06/03/2025 | 30 | MAA MAHAMAYA CONSTRUCTION | 0.95 | 0 | 0 | 100
2786 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SHYAMSUNDAR (PART B) PWSS , SM/15183 | Augmentation | Laying Parallel Pipeline along Pathashree Road from Girls School to Muktipur Village for SHYAMSUNDAR PIPED WATER SUPPLY SCHEME, Block- Raina-I , within Burdwan Sub Division under Burdwan Division PHE Dte. | 102/BSD | 16/01/2025 | 30 | MAA MAHAMAYA CONSTRUCTION | 4.08 | 0 | 0 | 100
2787 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR , SM/15185 | Augmentation | Preparation and Submission of DPR for Augmentation of Ruppur PWSS under Jamalpur Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1478/BSD | 12/07/2023 | 15 | CARTO | 0.78 | 0.77 | 100 | 100
2788 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR , SM/15185 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 3 at Augumentation of RUPPUR Water Supply Scheme [BLOCK- JAMALPUR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1540/CMD | 05/03/2024 | 60 | KAMAKHYA ENTERPRISE | 12.33 | 0 | 0 | 0
2789 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR , SM/15185 | Augmentation | Providing FHTC for 100% coverage at RUPPUR & Dhuluk Habitation (Village) for RUPPUR Piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 2315/BWD | 19/05/2023 | 60 | MAJILA ENTERPRISE | 62.34 | 59.96 | 100 | 100
2790 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR , SM/15185 | Augmentation | Relaying and replace of damaged HDPE pipeline with repairing of valve for control of water flow within command area of RUPPUR Piped W/S Scheme at Ruppur Habitation,Jamalpur Development Block under Burdwan Division PHE Dte. | 1044/BSD | 10/06/2024 | 30 | SANDIPAN SENGUPTA | 0.65 | 0.65 | 100 | 100
2791 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR , SM/15185 | Augmentation | Sinking of 300 mm X 200 mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) with construction of Pump House, Boundary wall, Land Development and Rising main connection of RUPPUR Piped Water Supply Scheme, Block- Jamalpur, District:- Purba-Bardhaman under Burdwan Division PHE Dte. [FOR 3rd. TUBE WELL SITE] | 4593/BWD | 31/12/2024 | 120 | HI-LIGHT ELECTRONICS | 26.2 | 5.39 | 20.57 | 30
2792 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RUPPUR , SM/15185 | Augmentation | Illumination arrangement and miscellaneous works at Ruppur water supply scheme under Jamalpur Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2947/CMD | 20/11/2024 | 60 | M/S. SWAPAN BANERJEE | 19.64 | 0 | 0 | 30
2793 | PURBA BARDHAMAN | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME , SM/16253 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 7.15 | 0 | 0 | 0
2794 | PURBA BARDHAMAN | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME , SM/16253 | New | Material Requisition To Resource Division | 4008/BWD | 08/09/2023 | 0 | Resource Division | 2.23 | 0 | 0 | 0
2795 | PURBA BARDHAMAN | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME , SM/16253 | New | Material Requisition To Resource Division | 5065/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
2796 | PURBA BARDHAMAN | Central Mechanical | RASUIKHANDA PIPED WATER SUPPLY SCHEME , SM/16253 | New | New service connection charges for Rasuikhanda PWSS TW-2 | BP-2023-24-153 | 05/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.7 | 0 | 0 | 0
2797 | PURBA BARDHAMAN | Central Mechanical | RASUIKHANDA PIPED WATER SUPPLY SCHEME , SM/16253 | New | New service connection charges for Rasuikhanda PWSS TW 1 | BP-2023-24-139 | 25/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.04 | 0 | 0 | 0
2798 | PURBA BARDHAMAN | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME , SM/16253 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | 2751/BSD | 28/11/2023 | 183 | SK.ASFIA | 2.4 | 0.4 | 99.9 | 70
2799 | PURBA BARDHAMAN | Central Mechanical | RASUIKHANDA PIPED WATER SUPPLY SCHEME , SM/16253 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
2800 | PURBA BARDHAMAN | Burdwan Division | RASUIKHANDA PIPED WATER SUPPLY SCHEME , SM/16253 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOPALPUR & RASUIKHANDA Piped Water Supply Scheme under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 1691/BWD | 12/04/2023 | 719 | SK ALIM | 1081.52 | 606.84 | 95.71 | 92
2801 | PURBA BARDHAMAN | Central Mechanical | RASUIKHANDA PIPED WATER SUPPLY SCHEME , SM/16253 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Rasuikhanda Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2968/CMD | 17/07/2023 | 351 | ORIENTAL ENGINEERING CO. | 28.96 | 23.34 | 95.56 | 90
2802 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF KSHETPUR PALASHI PIPED WATER SUPPLY SCHEME , SM/16016 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Kshetpur Plasi Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2585/CMD | 07/06/2023 | 820 | SOUNAK ENTERPRISE | 22.6 | 10.29 | 45.52 | 48
2803 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF KSHETPUR PALASHI PIPED WATER SUPPLY SCHEME , SM/16016 | Augmentation | Augmentation of KSHETPUR PALASHI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & Renovation of switch-rooms & boundary walls at different TW site under Katwa-II Block, District:- Purba-Bardhaman. | 2303/BWD | 19/05/2023 | 448 | SHUBHRA KANTI GHOSH | 121.71 | 46.04 | 39.02 | 95
2804 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF KSHETPUR PALASHI PIPED WATER SUPPLY SCHEME , SM/16016 | Augmentation | New service connection charges for Kshetpur Palashi PWSS TW-1 | BP-2023-24-280 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4 | 0 | 0 | 0
2805 | PURBA BARDHAMAN | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME , SM/16618 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 8.72 | 0 | 0 | 0
2806 | PURBA BARDHAMAN | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME , SM/16618 | New | Material Requisition To Resource Division | 5058/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
2807 | PURBA BARDHAMAN | Central Mechanical | SIPTA PIPED WATER SUPPLY SCHEME , SM/16618 | New | New service connection charges for Sipta PWSS TW-1 | BP-2023-24-88 | 26/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.76 | 0 | 0 | 0
2808 | PURBA BARDHAMAN | Central Mechanical | SIPTA PIPED WATER SUPPLY SCHEME , SM/16618 | New | New service connection charges for Sipta PWSS TW-2 | BP-2023-24-89 | 26/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.07 | 0 | 0 | 0
2809 | PURBA BARDHAMAN | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME , SM/16618 | New | Providing 20 Nos.FHTC at SIPTA village for declearation of SWAJALGRAM under SIPTA Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte | 1861/BSD | 22/08/2024 | 30 | ROY CONSTRUCTION | 0.96 | 0 | 0 | 0
2810 | PURBA BARDHAMAN | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME , SM/16618 | New | SIPTA Single Village Scheme with sinking of Tube-well & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1444/BWD | 24/03/2023 | 90 | S.B. ASSOCIATES | 49.61 | 49.53 | 100 | 100
2811 | PURBA BARDHAMAN | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME , SM/16618 | New | SIPTA Single Village Scheme with sinking of LDS, Rising Main and FHTC under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 2258/BWD | 18/05/2023 | 90 | ROY CONSTRUCTION | 115.09 | 115.04 | 100 | 100
2812 | PURBA BARDHAMAN | Central Mechanical | SIPTA PIPED WATER SUPPLY SCHEME , SM/16618 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sipta Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2880/CMD | 07/07/2023 | 30 | S.G. ENTERPRISE | 28.95 | 24.34 | 100 | 95
2813 | PURBA BARDHAMAN | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME , SM/16618 | New | Construction of approach road near 2nd. Tube well site of SIPTA Water Supply Scheme [New Scheme], Raina-I, under Burdwan Sub Division PHE Dte. under Burdwan Division PHE. Dte. | 211/BWD | 09/01/2025 | 30 | SAIKAT RAY | 7.2 | 0 | 0 | 0
2814 | PURBA BARDHAMAN | Central Mechanical | SIPTA PIPED WATER SUPPLY SCHEME , SM/16618 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
2815 | PURBA BARDHAMAN | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME , SM/16618 | New | Restore of village Road dismalted by laying pipe line at for providing FHTC at Kukre village under SIPTA PIPED WATER SUPPLY SCHEME [new scheme],Block-Raina-I,within Burdwan Sub Division under Burdwan Division PHE Dte. | 261/BSD | 05/02/2025 | 15 | ROY CONSTRUCTION | 0.96 | 0 | 0 | 100
2816 | PURBA BARDHAMAN | Burdwan Division | SIPTA PIPED WATER SUPPLY SCHEME , SM/16618 | New | Restore of village Road dismalted by laying pipeline at for providing FHTC at Sipta village under SIPTA PIPED WATER SUPPLY SCHEME[news cheme],Block-Raina-I,within Burdwan Sub Division under Burdwan Division PHE Dte. | 505/BSD | 06/03/2025 | 30 | STRATEGIC BUILDCON | 0.96 | 0 | 0 | 100
2817 | PURBA BARDHAMAN | Burdwan Division | ONARI PIPED WATER SUPPLY SCHEME , SM/18246 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 14.41 | 0 | 0 | 0
2818 | PURBA BARDHAMAN | Burdwan Division | ONARI PIPED WATER SUPPLY SCHEME , SM/18246 | New | Material Requisition To Resource Division | 5075/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
2819 | PURBA BARDHAMAN | Burdwan Division | ONARI PIPED WATER SUPPLY SCHEME , SM/18246 | New | Material Requisition To Resource Division | 3829/BWD | 01/09/2023 | 0 | Resource Division | 24.57 | 0 | 0 | 0
2820 | PURBA BARDHAMAN | Central Mechanical | ONARI PIPED WATER SUPPLY SCHEME , SM/18246 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
2821 | PURBA BARDHAMAN | Central Mechanical | ONARI PIPED WATER SUPPLY SCHEME , SM/18246 | New | New Service connection for Onari PWSS TW-2. | BP-2023-24-620 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.68 | 0 | 0 | 0
2822 | PURBA BARDHAMAN | Central Mechanical | ONARI PIPED WATER SUPPLY SCHEME , SM/18246 | New | New service connection for Onari PWSS TW-1. | BP-2023-24-619 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.68 | 0 | 0 | 0
2823 | PURBA BARDHAMAN | Burdwan Division | ONARI PIPED WATER SUPPLY SCHEME , SM/18246 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ONARI & SASANGA Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | 3430/BWD | 07/08/2023 | 786 | M/S JAN MAHAMMAD | 1398.82 | 323.66 | 57.24 | 50
2824 | PURBA BARDHAMAN | Central Mechanical | ONARI PIPED WATER SUPPLY SCHEME , SM/18246 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Onari Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4012/CMD | 29/08/2023 | 30 | M/S. S.R. ENTERPRISE | 28.09 | 0 | 0 | 95
2825 | PURBA BARDHAMAN | Burdwan Division | ONARI PIPED WATER SUPPLY SCHEME , SM/18246 | New | Supply of flow control devices and CIDF Pipes for ONARI PWSS (SM/18246) under Burdwan Division, PHE Dte._2ND CALL | 81/AE/HQ | 07/01/2025 | 127 | MAKALI ENGINEERING CORPORATION | 9.95 | 0 | 0 | 100
2826 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kulti Piped Water Supply Scheme at Kalna-II Block , SM/07826 | Retrofitting | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of Kulti piped water supply scheme at Chagram village (Chagram habitation), Dakshin Krishnapur village (Krishnapur habitation), Kala village (Anandanagar, Baganpara, Kala & Saklompur habitation), Kulti village (Dhapaspara & Kulti habitation), Dampara village (Dampara habitation) & Kashipur village (Kashipur habitation), Kalna-II Block under Burdwan Division, PHE Dte.[Tr No.-108/SE/CC/20-21] | 1130/BWD | 09/02/2021 | 60 | UMWELT ENGINEER PVT LTD | 103.15 | 62.13 | 200 | 1
2827 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kulti Piped Water Supply Scheme at Kalna-II Block , SM/07826 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Kalna ¿ II Block under Burdwan Division, PHE. Dte. | 943/BWD | 17/02/2022 | 30 | UDYOG CONSTRUCTION | 5.27 | 4.65 | 100 | 100
2828 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kulti Piped Water Supply Scheme at Kalna-II Block , SM/07826 | Retrofitting | Restoration work of Singerkone to Pandua Kulti road via badla from 0.00 km to 2.90 km, (in stretches) damaged due to laying of underground water pipe line by PHE with box cutting and Jhama with moorum consolidation under-Kalna Highvway Sub Division of Burdwan South Highway Division, P.W(Roads)Dte. during the year 2023-24. | 825/JJM | 13/09/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 5.36 | 0 | 0 | 0
2829 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kulti Piped Water Supply Scheme at Kalna-II Block , SM/07826 | Retrofitting | Different types of works involve in connection with Augmentation of KULTI (SM/16301) Water Supply Scheme, Block Kalna II under Burdwan Division, PHE Dte. | 2553/BWD | 04/07/2024 | 240 | HAMID SK | 222.11 | 0 | 0 | 80
2830 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kulti Piped Water Supply Scheme at Kalna-II Block , SM/07826 | Retrofitting | Construction of approach road along with Land Development work in connection with retrofitting of KULTI PWSS (SM/07826) under Kalna Sub-Division under Burdwan Division, PHE Dte. | 1252/BWD | 23/04/2025 | 21 | GOPINATH ENTERPRISE | 10.18 | 0 | 0 | 100
2831 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kulti Piped Water Supply Scheme at Kalna-II Block , SM/07826 | Retrofitting | Construction of 1.5 Mtrs. height boundary wall along with 750 mm height 3 layer barbed wire in connection with KULTI Piped W/S. Scheme under Kalna Sub Division under Burdwan Division, PHE. Dte. | 768/BWD | 27/02/2025 | 30 | GOPINATH ENTERPRISES | 15.13 | 0 | 0 | 100
2832 | PURBA BARDHAMAN | Burdwan Division | MOHANPUR PIPED WATER SUPPLY SCHEME , SM/18242 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 2.41 | 0 | 0 | 0
2833 | PURBA BARDHAMAN | Burdwan Division | MOHANPUR PIPED WATER SUPPLY SCHEME , SM/18242 | New | Material Requisition To Resource Division | 4937/BWD | 10/11/2023 | 0 | Resource Division | 54.72 | 0 | 0 | 0
2834 | PURBA BARDHAMAN | Burdwan Division | MOHANPUR PIPED WATER SUPPLY SCHEME , SM/18242 | New | Material Requisition To Resource Division | 3844/BWD | 01/09/2023 | 0 | Resource Division | 251.04 | 0 | 0 | 0
2835 | PURBA BARDHAMAN | Burdwan Division | MOHANPUR PIPED WATER SUPPLY SCHEME , SM/18242 | New | Shifting of 11KV Line of Mohanpur PWSS under Burdwan Division, PHE Dte. | 1055/JJM | 13/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.33 | 0 | 0 | 0
2836 | PURBA BARDHAMAN | Central Mechanical | MOHANPUR PIPED WATER SUPPLY SCHEME , SM/18242 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
2837 | PURBA BARDHAMAN | Durgapur W/S Division | MOHANPUR PIPED WATER SUPPLY SCHEME , SM/18242 | New | Material Requisition To Resource Division | 1724/N/DWSD | 10/12/2024 | 0 | Resource Division | 11.33 | 0 | 0 | 0
2838 | PURBA BARDHAMAN | Central Mechanical | MOHANPUR PIPED WATER SUPPLY SCHEME , SM/18242 | New | New service connection for Mohanpur PWSS . | BP-2023-24-507 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.83 | 0 | 0 | 0
2839 | PURBA BARDHAMAN | Central Mechanical | MOHANPUR PIPED WATER SUPPLY SCHEME , SM/18242 | New | New service connection for Mohanpur PWSS . | BP-2023-24-506 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.86 | 0 | 0 | 0
2840 | PURBA BARDHAMAN | Burdwan Division | MOHANPUR PIPED WATER SUPPLY SCHEME , SM/18242 | New | MOHANPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Galsi-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3149/BWD | 20/07/2023 | 774 | MD HASIN | 963.53 | 540.57 | 56.1 | 80
2841 | PURBA BARDHAMAN | Durgapur W/S Division | MOHANPUR PIPED WATER SUPPLY SCHEME , SM/18242 | New | FORMAL WORK ORDER FOR MOHANPUR Piped Water Supply Scheme with Inter-connection, LDS, FHTC ,Road restoration & construction of switch rooms & boundary walls with gates, land development with road at TW site under Galsi-II Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte | 41/DWSD | 08/01/2025 | 334 | MD.HASIN | 148.94 | 0 | 0 | 70
2842 | PURBA BARDHAMAN | Central Mechanical | MOHANPUR PIPED WATER SUPPLY SCHEME , SM/18242 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-4 at MOHANPUR Water Supply Scheme [ BLOCK- GALSI-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 881/CMD | 26/03/2025 | 60 | CHOUDHURY ENTERPRISE | 12.88 | 0 | 0 | 0
2843 | PURBA BARDHAMAN | Burdwan Division | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | Material Requisition To Resource Division | 4312/BWD | 29/09/2023 | 0 | Resource Division | 73.01 | 0 | 0 | 0
2844 | PURBA BARDHAMAN | Burdwan Division | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | BANDMURA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 5007/BWD | 22/11/2023 | 1136 | MANASH GHOSH | 883.19 | 181.59 | 20.56 | 35
2845 | PURBA BARDHAMAN | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
2846 | PURBA BARDHAMAN | Burdwan Division | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | Material Requisition To Resource Division | 208/BWD | 10/01/2024 | 0 | Resource Division | 21.5 | 0 | 0 | 0
2847 | PURBA BARDHAMAN | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | New service connection for Bandhmura PWSS PH-3. | BP-2023-24-615 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.32 | 0 | 0 | 0
2848 | PURBA BARDHAMAN | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | NEW SERVICE CONNECTION FOR BANDMURA PWSS TW 1. | BP-2023-24-536 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12.36 | 0 | 0 | 0
2849 | PURBA BARDHAMAN | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | Quotation for new service connection for Bandmura PWSS TW-2. | BP-2024-25-292 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.03 | 0 | 0 | 0
2850 | PURBA BARDHAMAN | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at BANDMURA Water Supply Scheme [ Block- KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4132/CMD | 29/08/2023 | 590 | GLACIER ENGINEERING CO | 44.42 | 23.74 | 53.45 | 31
2851 | PURBA BARDHAMAN | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | Hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte , w.e.f : 01/ 01/ 2025 to 28/02/2025 | 922/DIC/BMSD(D) | 26/12/2024 | 59 | SUBRATA BHADRA | 0.8 | 0.74 | 92.26 | 0
2852 | PURBA BARDHAMAN | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | continuation order for Hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte ,wef : 01/ 11/ 20 24 to 31/12/2024. | 739/DIC/BMSD(D) | 25/10/2024 | 61 | SUBRATA BHADRA | 0.81 | 0.78 | 96.46 | 0
2853 | PURBA BARDHAMAN | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte , w.e.f : 01/05/2025 to 30/06/2025. | 248/DIC/BMSD(D) | 23/04/2025 | 61 | SUBRATA BHADRA | 0.81 | 0.67 | 82.96 | 0
2854 | PURBA BARDHAMAN | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte , w.e.f : 01/03/2025 to 30/04/2025. | 134/DIC/BMSD(D) | 24/02/2025 | 61 | SUBRATA BHADRA | 0.81 | 0.75 | 92.09 | 0
2855 | PURBA BARDHAMAN | Central Mechanical | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of JJM works under the jurisdiction of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte , w.e.f : 01/07/2025 to 30/08/2025. | 476/DIC/BMSD(D) | 26/06/2025 | 61 | SUBRATA BHADRA | 0.81 | 0 | 0 | 0
2856 | PURBA BARDHAMAN | Burdwan Division | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | Crossing of road following Jack Push method under the command area of Bandhmura PWSS (SM/18480) of Katwa-I Block under Katwa Sub-Division PHE Dte. | 1288/BWD | 24/04/2025 | 30 | MANASH GHOSH | 32.76 | 0 | 0 | 100
2857 | PURBA BARDHAMAN | Burdwan Division | BANDMURA PIPED WATER SUPPLY SCHEME , SM/18480 | New | Providing of left out FHTC in different location of BANDHMURA PWSS (SM/18480) at Ganfulia Mouza in order to declare Sajal Gram, under Katwa-II Block under Katwa Sub-Division, PHE Dte. | 983/BWD | 13/03/2025 | 172 | MANASH GHOSH | 9.43 | 0 | 0 | 100
2858 | PURBA BARDHAMAN | Burdwan Division | BELSHAR PIPED WATER SUPPLY SCHEME , SM/18338 | New | Material Requisition To Resource Division | 3860/BWD | 01/09/2023 | 0 | Resource Division | 3.41 | 0 | 0 | 0
2859 | PURBA BARDHAMAN | Burdwan Division | BELSHAR PIPED WATER SUPPLY SCHEME , SM/18338 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 1.8 | 0 | 0 | 0
2860 | PURBA BARDHAMAN | Burdwan Division | BELSHAR PIPED WATER SUPPLY SCHEME , SM/18338 | New | Material Requisition To Resource Division | 5100/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
2861 | PURBA BARDHAMAN | Central Mechanical | BELSHAR PIPED WATER SUPPLY SCHEME , SM/18338 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Belshar Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4030/CMD | 29/08/2023 | 474 | SINHA ELECTRICALS | 28.97 | 25.18 | 100 | 96
2862 | PURBA BARDHAMAN | Burdwan Division | BELSHAR PIPED WATER SUPPLY SCHEME , SM/18338 | New | Material Requisition To Resource Division | 4115/BWD | 25/11/2024 | 0 | Resource Division | 21.15 | 0 | 0 | 0
2863 | PURBA BARDHAMAN | Central Mechanical | BELSHAR PIPED WATER SUPPLY SCHEME , SM/18338 | New | New electric connection for Belswar PWSS, PH-1. | BP-2023-24-360 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.01 | 0 | 0 | 0
2864 | PURBA BARDHAMAN | Central Mechanical | BELSHAR PIPED WATER SUPPLY SCHEME , SM/18338 | New | NEW SERVICE CONNECTION FOR BELSHAR PWSS TW 2. | BP-2023-24-666 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.39 | 0 | 0 | 0
2865 | PURBA BARDHAMAN | Central Mechanical | BELSHAR PIPED WATER SUPPLY SCHEME , SM/18338 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
2866 | PURBA BARDHAMAN | Burdwan Division | NALA PIPED WATER SUPPLY SCHEME , SM/18256 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.83 | 0 | 0 | 0
2867 | PURBA BARDHAMAN | Burdwan Division | NALA PIPED WATER SUPPLY SCHEME , SM/18256 | New | Material Requisition To Resource Division | 3868/BWD | 01/09/2023 | 0 | Resource Division | 3.83 | 0 | 0 | 0
2868 | PURBA BARDHAMAN | Burdwan Division | NALA PIPED WATER SUPPLY SCHEME , SM/18256 | New | Material Requisition To Resource Division | 5054/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
2869 | PURBA BARDHAMAN | Central Mechanical | NALA PIPED WATER SUPPLY SCHEME , SM/18256 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Nala Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4002/CMD | 29/08/2023 | 528 | P.K. ENGINEERING | 28.89 | 11.4 | 39.47 | 95
2870 | PURBA BARDHAMAN | Central Mechanical | NALA PIPED WATER SUPPLY SCHEME , SM/18256 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
2871 | PURBA BARDHAMAN | Central Mechanical | NALA PIPED WATER SUPPLY SCHEME , SM/18256 | New | New service connection at NALA PWSS Ph-2 | BP-2023-24-445 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0 | 0
2872 | PURBA BARDHAMAN | Central Mechanical | NALA PIPED WATER SUPPLY SCHEME , SM/18256 | New | New service connection at NALA PWSS Ph-1 | BP-2023-24-444 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.2 | 0 | 0 | 0
2873 | PURBA BARDHAMAN | Burdwan Division | NALA PIPED WATER SUPPLY SCHEME , SM/18256 | New | Balance work i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, Solar System with structure, inter Connection of Additional Tube Well, & allied work for NALA Piped Water Supply Scheme under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | 847/BWD | 05/03/2025 | 120 | DIAMOND ENGINEERS CO-OP SOCIETY LTD. | 184.95 | 0 | 0 | 0
2874 | PURBA BARDHAMAN | Burdwan Division | LAKSHIMPUR PWSS , SM/18457 | New | Material Requisition To Resource Division | 4941/BWD | 10/11/2023 | 0 | Resource Division | 27.49 | 0 | 0 | 0
2875 | PURBA BARDHAMAN | Burdwan Division | LAKSHIMPUR PWSS , SM/18457 | New | Material Requisition To Resource Division | 4302/BWD | 29/09/2023 | 0 | Resource Division | 10.51 | 0 | 0 | 0
2876 | PURBA BARDHAMAN | Burdwan Division | LAKSHIMPUR PWSS , SM/18457 | New | Material Requisition To Resource Division | 206/BWD | 10/01/2024 | 0 | Resource Division | 17.75 | 0 | 0 | 0
2877 | PURBA BARDHAMAN | Central Mechanical | LAKSHIMPUR PWSS , SM/18457 | New | NEW SERVICE CONNECTION FOR LAKSHIMPUR PWSS TW-1 | BP-2024-25-89 | 15/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.14 | 0 | 0 | 0
2878 | PURBA BARDHAMAN | Central Mechanical | LAKSHIMPUR PWSS , SM/18457 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at LAKSHIMPUR Water Supply Scheme [ Block- MONGALKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4087/CMD | 29/08/2023 | 640 | ORIENTAL ENGINEERING CO. | 44.4 | 0 | 0 | 31
2879 | PURBA BARDHAMAN | Burdwan Division | LAKSHIMPUR PWSS , SM/18457 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SIMULIA & LAKSHIMPUR Piped Water Supply Scheme under Mongalkote Block, District:- Purba-Bardhaman [NEW SCHEME] | 4363/BWD | 04/10/2023 | 727 | PUSPA ENTERPRISE | 1090.95 | 199.9 | 36.47 | 37
2880 | PURBA BARDHAMAN | Central Mechanical | LAKSHIMPUR PWSS , SM/18457 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
2881 | PURBA BARDHAMAN | Burdwan Division | LAKSHIMPUR PWSS , SM/18457 | New | Different types of works involve in connection with implementation of Gohgram, Jabagram, Kherua, Lakshmipur & Simulia Piped Water Supply Scheme under Mongolkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. | 936/BWD | 11/03/2025 | 180 | M/S GHOSH CONSTRUCTION | 360.68 | 0 | 0 | 0
2882 | PURBA BARDHAMAN | Burdwan Division | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
2883 | PURBA BARDHAMAN | Burdwan Division | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Material Requisition To Resource Division | 4889/BWD | 10/11/2023 | 0 | Resource Division | 75.91 | 0 | 0 | 0
2884 | PURBA BARDHAMAN | Burdwan Division | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Material Requisition To Resource Division | 3850/BWD | 01/09/2023 | 0 | Resource Division | 63.64 | 0 | 0 | 0
2885 | PURBA BARDHAMAN | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | New service connection charges for Karui PWSS TW-2 | BP-2023-24-86 | 26/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.67 | 0 | 0 | 0
2886 | PURBA BARDHAMAN | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | New service connection charges for Karui PWSS TW-3 | BP-2023-24-132 | 22/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.65 | 0 | 0 | 0
2887 | PURBA BARDHAMAN | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | New service connection charges for Karui PWSS TW-1 | BP-2023-24-101 | 03/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.19 | 0 | 0 | 0
2888 | PURBA BARDHAMAN | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Continuation order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of The Driller In Charge, Bardhaman Mech, Sub Division ( Drilling) under C.M.D. P.H.E. Dte. w.e.f.-01/11/2023 to 31/12/2023. | 159/DIC/BMSD(D) | 31/10/2023 | 61 | SUBRATA BHADRA | 0.79 | 0.64 | 80.75 | 100
2889 | PURBA BARDHAMAN | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of The Driller In Charge, Bardhaman Mech, Sub Division ( Drilling) under C.M.D. P.H.E. Dte. w.e.f.-01/09/2023 to 31/10/2023. | 70/DIC/BMSD(D) | 28/08/2023 | 61 | SUBRATA BHADRA | 0.79 | 0.54 | 68.34 | 100
2890 | PURBA BARDHAMAN | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of site for the office of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte, [w.e.f: 01.07.2024 to 31.08.2024] | 350/DIC/BMSD(D) | 27/06/2024 | 62 | SUBRATA BHADRA | 0.79 | 0.75 | 94.46 | 0
2891 | PURBA BARDHAMAN | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of site for the office of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte, [w.e.f.-01/05/2024 to 30/06/2024] | 259/DIC/BMSD(D) | 26/04/2024 | 61 | SUBRATA BHADRA | 0.79 | 0.72 | 91.51 | 0
2892 | PURBA BARDHAMAN | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of site for the office of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte, Dte. [w.e.f: 01.01.2024 to 29.02.2024] | 365/DIC/BMSD(D) | 29/12/2023 | 60 | SUBRATA BHADRA | 0.78 | 0.64 | 81.83 | 100
2893 | PURBA BARDHAMAN | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Continuation order for hiring of Inspection Vehicle ( Diesel/CNG/LPG Driven) for supervision of site for the office of the Driller In charge, Bardhaman Mechanical Sub Division(Drilling) under CMD, PHE, Dte, [w.e.f: 01.03.2024 to 30.04.2024] | 141/DIC/BMSD(D) | 29/02/2024 | 61 | SUBRATA BHADRA | 0.79 | 0.69 | 87.52 | 100
2894 | PURBA BARDHAMAN | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
2895 | PURBA BARDHAMAN | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3106/CMD | 11/12/2024 | 60 | S.K. ELECTRICALS | 13.6 | 0 | 0 | 0
2896 | PURBA BARDHAMAN | Burdwan Division | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Material Requisition To Resource Division | 326/BWD | 24/01/2024 | 0 | Resource Division | 8.78 | 0 | 0 | 0
2897 | PURBA BARDHAMAN | Burdwan Division | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Construction of Toilet (1.8 m x 1.8 m) with sanitary arrangement under KARUI PWSS (SM/18460) 3rd Tube Well Site under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-04) | 345/KTS | 05/03/2025 | 30 | JAMALUDDIN SK | 2.46 | 0 | 0 | 0
2898 | PURBA BARDHAMAN | Burdwan Division | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Construction of Toilet (1.8 m x 1.8 m) with sanitary arrangement under KARUI PWSS (SM/18460) 2nd Tube Well Site under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-3) | 344/KTS | 05/03/2025 | 30 | JAMALUDDIN SK | 2.46 | 0 | 0 | 0
2899 | PURBA BARDHAMAN | Central Mechanical | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KARUI Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3099/CMD | 24/07/2023 | 550 | JAL PRAVAHIKA PVT LTD | 44.4 | 37.01 | 100 | 91
2900 | PURBA BARDHAMAN | Burdwan Division | KARUI PIPED WATER SUPPLY SCHEME , SM/18460 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MEJHIARY & KARUI Piped Water Supply Scheme under Katwa ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3291/BWD | 31/07/2023 | 701 | M/S S. CHOUDHURY | 1294.79 | 715.59 | 99.33 | 100
2901 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Extension of distribution main for providing FHTC at Kashipur Ramgere Adibasipara within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-A] | 602/DSD | 07/10/2021 | 30 | THREE MAA ENTERPRISE | 4.82 | 0 | 0 | 1
2902 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sripur village (Sripur Habitation) of Kashipur piped water supply scheme within Durgapur Sub-Division under Burdwan Division, PHE Dte.(Tr No.-718/BWD/2020-21) | 1439/BWD | 18/02/2021 | 15 | ROY BISWAS CONSTRUCTION | 4.5 | 9 | 200 | 1
2903 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nurpur village and Nurpur Habitation of KASHIPUR piped water supply scheme within Durgapur Sub-Division (Bardhaman North) under Burdwan Division, PHE Dte. [Phase-I] | 3971/BWD | 14/10/2020 | 30 | THREE MAA ENTERPRISE | 1.21 | 0 | 0 | 1
2904 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kashipur Piped Water Supply Scheme at Sripur, (Sripur Habitation), Kashipur (Part) (Kashipur & Sahabganj Part Habitation) Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. | 3118/BWD | 02/06/2021 | 30 | PREMANANDA ROY BISWAS | 35.02 | 59.31 | 200 | 1
2905 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Extension of distribution main for providing FHTC at Kashipur Ramgere Adibasipara within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-A] | 619/DSD | 25/10/2021 | 30 | THREE MAA ENTERPRISE | 4.82 | 4.82 | 100 | 1
2906 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur (Part) village (Kashipur habitation) of Kashipur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 18] [Agr. No. 720/BWD of 2020-2021] | 1441/BWD | 18/02/2021 | 15 | PREMANANDA ROY BISWAS | 4.48 | 0.44 | 100 | 1
2907 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur (Part) village (Sahebganj (P) habitation) of Kashipur Piped Water Supply Scheme within Durgapur Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 16] [Agree Ment No.719/BWD of 2020-21] | 1440/BWD | 18/02/2021 | 15 | THREE MAA ENTERPRISE | 4.52 | 0.45 | 100 | 1
2908 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Bhatar Block under Burdwan Division, PHE. Dte. | 268/BWD | 14/01/2022 | 30 | BHARAT CONSTRUCTION | 14.17 | 4.11 | 100 | 1
2909 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Restoration of damaged pipeline during construction of drain, concrete road etc and making valve chamber at various point at Kashipur village within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. [SL-14] | 739/DSD | 30/12/2022 | 21 | PAPRI HAZRA | 0.87 | 0.86 | 100 | 100
2910 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Providing Functional Household Tap Connection (FHTC)from distribution system within the command area of Kashipur water supply scheme at Kashipur Nurpur and Sahebganj village to make its Swajalgram under JAL JIBAN MISSION within Bhatar Block in Purba Bardhanan District undrer Burdwan Division, P.H.E. Dte. | 623/DSD | 05/08/2024 | 90 | RAM MOHAN MUKHERJEE | 3.15 | 0 | 0 | 0
2911 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur village in Sahebganj habitation of Kashipur piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-361/BWD/2020-21) | 3973/BWD | 14/10/2020 | 30 | PREMANANDA ROY BISWAS | 4.84 | 1.2 | 100 | 0
2912 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nurpur village and Nurpur habitation of Kashipur piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-359/BWD/2020-21) | 3340/BWD | 18/09/2020 | 30 | THREE MAA ENTERPRISE | 4.84 | 1.2 | 100 | 0
2913 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashipur village and Sahebganj habitation of Kashipur piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-360/BWD/2020-21) | 3339/BWD | 18/09/2020 | 30 | PREMANANDA ROY BISWAS | 4.84 | 1.2 | 100 | 0
2914 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Relaying and restoration of damaged pipeline of distribution main for widening of PWD road and Bridge at Sahebganj Bazar for providing FHTC within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. | 653/DSD | 24/08/2023 | 30 | ANWESHA CONSTRUCTION | 0.95 | 0.95 | 100 | 100
2915 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kashipur Piped Water Supply Scheme at Bhatar Block , SM/07868 | Retrofitting | Restoration of damaged pipeline of distribution main for construction of drain, concrete road etc at various point at Majhipara village for providing FHTC within Kashipur W/S Scheme in Bhatar Block under Burdwan Division, P.H.E. Dte. | 652/DSD | 24/08/2023 | 30 | ANWESHA CONSTRUCTION | 0.96 | 0.96 | 100 | 100
2916 | PURBA BARDHAMAN | Burdwan Division | Ichalabad Piped Water Supply Scheme , SM/18404 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.88 | 0 | 0 | 0
2917 | PURBA BARDHAMAN | Burdwan Division | Ichalabad Piped Water Supply Scheme , SM/18404 | New | Material Requisition To Resource Division | 3848/BWD | 01/09/2023 | 0 | Resource Division | 15.12 | 0 | 0 | 0
2918 | PURBA BARDHAMAN | Burdwan Division | Ichalabad Piped Water Supply Scheme , SM/18404 | New | Material Requisition To Resource Division | 5062/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
2919 | PURBA BARDHAMAN | Central Mechanical | Ichalabad Piped Water Supply Scheme , SM/18404 | New | Quotation for new service connection for Ichalabad PWSS PH 1. | BP-2024-25-121 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 36.6 | 0 | 0 | 0
2920 | PURBA BARDHAMAN | Central Mechanical | Ichalabad Piped Water Supply Scheme , SM/18404 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 0 | 12
2921 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of RASULPUR Piped Water Supply Scheme , SM/08031 | Retrofitting | Providing FHTC from dist. System within the command area of RASULPUR Piped Water Supply Scheme at Genraghata, Paschim Tazpur, Ulara, Daluibazar of Daluibazar - I G.P. and different samsad such as Samsad No. 05, 13, 08, 12, 09, 10, 11, 15 & 14 within Nimo-I G.P. at Memari-I Development Block under Burdwan Division, PHE Dte. | 1572/BWD | 16/03/2022 | 60 | SUJAY KUMAR RAY | 55.17 | 41.89 | 100 | 1
2922 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of RASULPUR Piped Water Supply Scheme , SM/08031 | Retrofitting | Emergency repair and provide 5 (5 nos 100 dia. S.V) No's Sluice Valve at Chaknara & Ullara village under Rasulpur piped water supply scheme (Retro Fittings) for smooth drinking water supply within Memari-I Block under Burdwan Division, PHE Dte (Part-B). | 1972/BSD | 16/11/2022 | 15 | SUPRIYA RAY | 0.9 | 0 | 0 | 0
2923 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of RASULPUR Piped Water Supply Scheme , SM/08031 | Retrofitting | Construction of Balance portion of Boundary wall at Head Works Site of RASULPUR Water Supply scheme under MEMARI-I Block of Burdwan Division, PHE Dte. (Length -15.00 Mtr, Col-7 Nos). Gr.E. | 1481/BSD | 25/08/2022 | 30 | DEBASHISH ENTERPRISE | 1.95 | 1.51 | 100 | 100
2924 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of RASULPUR Piped Water Supply Scheme , SM/08031 | Retrofitting | Material Requisition To Resource Division | 425/BWD | 20/01/2022 | 0 | Resource Division | 5.5 | 0 | 0 | 0
2925 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of RASULPUR Piped Water Supply Scheme , SM/08031 | Retrofitting | Emergency repair and provided (4 nos.100 dia S.V) No's Sluice Valve at Rasulpur Natun Rasta,Nichu Bazar of RASULPUR Piped Water Supply Scheme (Retrofittings) for smooth drinking water supply within within Memari-I Block under Burdwan Division, PHE Dte. Gr.D | 1920/BSD | 11/11/2022 | 15 | SUPRIYA RAY | 0.73 | 0 | 0 | 100
2926 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of RASULPUR Piped Water Supply Scheme , SM/08031 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rasulpur Piped Water Supply Scheme at Chaknara, Rasulpur (4 Nos Habitation Part) Daluibazar (Part) Village (Mouza), Memari-I Block under Burdwan Division, PHE Dte..[Agreement No. 103/SE/CC/PHE/Dte of 2020-2021.] | 997/BWD | 04/02/2021 | 60 | MITRA CONSTRUCTION | 95.96 | 189.33 | 200 | 0
2927 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of RASULPUR Piped Water Supply Scheme , SM/08031 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rasulpur Piped Water Supply Scheme at Jitkanu, Genraghata, Paschim Tazpur, Ulara (2 Nos Habitation) & Baidyadanga Village (Mouza), Memari-I Block under Burdwan Division, PHE Dte.(Agreement No. 104/SE/CC/PHE/DTE of 2020-2021) | 996/BWD | 04/02/2021 | 60 | MITRA CONSTRUCTION | 93.49 | 188.21 | 200 | 0
2928 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of RASULPUR Piped Water Supply Scheme , SM/08031 | Retrofitting | Restoration of damaged portion of 75 mm dia & 125 mm dia UPVC pipeline due to widening of GT Road by from Palla Road more to Mahamaya Store at RASULPUR water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Gr.-C] | 19/BSD | 06/01/2021 | 30 | PAL CONSTRUCTION | 4.79 | 4.25 | 100 | 0
2929 | PURBA BARDHAMAN | Burdwan Division | Rretrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the commend area of RASULPUR Piped Water Supply Scheme , SM/08031 | Retrofitting | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for RASULPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | 4474/BWD | 19/12/2024 | 90 | SARKAR AGENCY | 91.74 | 0 | 0 | 51
2930 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme , SM/08102 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rayan Piped Water Supply Scheme at Rayan (Part) (Baisnabpara, Bayanpara, Bhotargra, Bhtarpur, DVC Canal, Dakhinpara, Dangapara, Daspara, Dulapara, Durgamandir, Ghatimgore, Gopaldighi & Hatu Dewan (N)) Village (Mouza), Bardhaman-I Block under Burdwan Division, PHE Dte.._2ND CALL. | 3202/BWD | 09/06/2021 | 60 | SUNNY ELECTRIC CO. | 53.1 | 51.27 | 100 | 1
2931 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme , SM/08102 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Rayan Piped Water Supply Scheme at Rayan (Part) (Hatu Dewan(S), Kantai Krishnapur, Katwa Road, KhanPukur, Krishnapur, MadanSayar, Makumpara, Malikpara, Malir Bagan, Muchipara, Muslimpara & Narupara) Village (Mouza), Bardhaman-I Block under Burdwan Division, PHE Dte. | 3143/BWD | 04/06/2021 | 45 | S.R. ENTERPRISE | 49.27 | 47.96 | 100 | 1
2932 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme , SM/08102 | Retrofitting | Extension of upvc distribution pipe line, s/valve chamber & conc. Work (Habitation-Belbagan,sutradharpara, Khanpukur & Adibasipara under Nari village) in regarding FHTC for Rayan water supply scheme at Bardhhaman-I Development Block under Burdwan Division, PHE Dte.Gr.B. | 70/BSD | 14/01/2022 | 30 | BRINDABAN KONAR | 4.64 | 4.32 | 100 | 1
2933 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme , SM/08102 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of RAYAN Piped Water Supply Scheme at Narayandighi & Sadhanpur (Part) Village (Mouza), Burdwan - I Block under Burdwan Division, PHE Dte. | 27/BWD | 04/01/2022 | 30 | DUBE ENTERPRISE | 30.24 | 30.23 | 100 | 1
2934 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme , SM/08102 | Retrofitting | Laying of interconnection between tube well No 1 to 6 & OHR and OHR to distribution system for RAYAN & Its Adjoing Mouzas Water Supply Scheme within Bardhaman I Dev. Block , under Burdwan Division, PHE Dte.Gr.C. | 71/BSD | 14/01/2022 | 30 | BRINDABAN KONAR | 4.81 | 0 | 0 | 1
2935 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme , SM/08102 | Retrofitting | Providing FHTC of distribution pipe line at Nari village(Habitation-Sutradharpara,Adibasipara & Suriyapally)for RAYAN Water Supply Scheme at Bardhhaman-I Development Block under Burdwan Division,PHE Dte.Gr.A | 677/BSD | 22/04/2022 | 30 | BRINDABAN KONAR | 2.68 | 2.68 | 100 | 1
2936 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme , SM/08102 | Retrofitting | Extension of UPVC distribution pipeline sluice valve chamber & concrete work in regarding FHTC for Rayan water supply scheme of Bardhaman-I Development Block under Burdwan Division, PHE Dte.[Gr.-E] | 1428/BSD | 28/10/2021 | 30 | S.R. ENTERPRISE | 4.01 | 4 | 100 | 1
2937 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme , SM/08102 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of RAYAN Piped Water Supply Scheme at Naridaspara and balance portion of Sukantapally, Suryapally, Nari Purbapara & Nasakali (Nari Mouza), Burdwan - I Block under Burdwan Division, PHE. Dte. | 2558/BWD | 19/05/2022 | 30 | SARKAR AGENCY | 41.42 | 41.57 | 100 | 1
2938 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme , SM/08102 | Retrofitting | Road restoration work due to FHTC & extension pipeline for different village (Rayan, Naryandighi, Nari Das Para, Krishnapur, Nari & Sukantapally) under RAYAN Piped W/S. Scheme at Burdwan - I Dev. Block under Burdwan Division, PHE. Dte. | 3771/BWD | 29/08/2023 | 30 | DURGAPADA MONDAL | 5.97 | 5.92 | 100 | 100
2939 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) retrofitting in the command area of of Rayan Piped Water Supply Scheme , SM/08102 | Retrofitting | Material Requisition To Resource Division | 4103/BWD | 25/11/2024 | 0 | Resource Division | 54.42 | 0 | 0 | 0
2940 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme , SM/07203 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Akaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-196/BWD/2020-21) | 2597/BWD | 04/08/2020 | 30 | JAI MAA DURGA & CO. | 4.92 | 9.84 | 200 | 1
2941 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme , SM/07203 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bikaihat & Akaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-169/BWD/2020-21) | 2598/BWD | 04/08/2020 | 30 | JAGADANANDAPUR CO. OP. LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 4.92 | 9.84 | 200 | 1
2942 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme , SM/07203 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ekaihat & Bikaihat (Pt-A) village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-486/BWD/2020-21) | 236/KTS | 30/09/2020 | 4 | JAI MAA DURGA & CO. | 1.29 | 2.55 | 200 | 1
2943 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme , SM/07203 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ekaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-329/BWD/2020-21) | 3739/BWD | 07/10/2020 | 30 | JAI MAA DURGA & CO. | 1.74 | 3.47 | 200 | 1
2944 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme , SM/07203 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ekaihat & Bikaihat (Part-B) village of Ekaihat & Bikaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. (Tr No.-539/BWD/2020-21) | 237/KTS | 30/09/2020 | 4 | JAGADANANDAPUR CO. OP. LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 1.32 | 2.65 | 200 | 1
2945 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme , SM/07203 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bikaihat & Ekaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-538/BWD/2020-21) | 3697/BWD | 05/10/2020 | 30 | JAGADANANDAPUR CO. OP. LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 1.79 | 3.59 | 200 | 1
2946 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme , SM/07203 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Ekaihat & Bikaihat village of Ekaihat piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. | 364/KTS | 15/12/2020 | 7 | BISHWAJIT DAS | 1.18 | 2.35 | 200 | 1
2947 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme , SM/07203 | Retrofitting | Providing Functional Household Tap Connection from existing distribution system within the command area of Akaihat and Bikihat PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-1) | 750/KTS | 24/11/2021 | 15 | JAI MAA DURGA & CO. | 2.54 | 2.52 | 100 | 1
2948 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme , SM/07203 | Retrofitting | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] | 4318/BWD | 04/11/2020 | 10 | MD HASIN | 4.93 | 0.61 | 100 | 1
2949 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme , SM/07203 | Retrofitting | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme EKAIHAT, PANUHAT PWSS (Sl No-2) | 394/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 2.48 | 1.24 | 100 | 100
2950 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme , SM/07203 | Retrofitting | Vehicle bill [Car No.-WB-04G-6018] for the month of September & October'2023. | 1269/JJM | 16/01/2024 | 0 | M/S MUNMUN DEY | 0.49 | 0 | 0 | 0
2951 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Ekaihat Piped Water Supply Scheme , SM/07203 | Retrofitting | Vehicle bill [Car No.-WB-04G-6018] for the month of November & December'2023. | 1894/JJM | 28/03/2024 | 0 | M/S MUNMUN DEY | 0.45 | 0 | 0 | 0
2952 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme , SM/06968 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Momrejpur village of Chhotobainan piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-174/BWD/2020-21) | 2741/BWD | 10/08/2020 | 30 | TIRUPATI ENTERPRISES | 4.92 | 9.84 | 200 | 1
2953 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme , SM/06968 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chhotobainan Piped Water Supply Scheme at Chhotobainan (3 Nos Part Habitation), Akhina, Dakhin Mohanour, Pahalanpur & Rupsara Village (Mouza), Raina-II Block under Burdwan Division, PHE Dte.(Agreement No. 62/2020-2021 OF SE/CC/PHE. DTE.) | 4852/BWD | 04/12/2020 | 90 | TIRUPATI ENTERPRISES | 100.4 | 164.88 | 200 | 1
2954 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme , SM/06968 | Retrofitting | Extension of pipeline for CHHOTOBAINAN water supply scheme at Pahalanpur and Rupsara and Dakshin Mohonpur village within Raina-II Block under Burdwan Division, PHE Dte. [Gr.-E] | 988/BSD | 30/07/2021 | 30 | TIRUPATI ENTERPRISES | 4.82 | 6.7 | 200 | 1
2955 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme , SM/06968 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 900/DW | 03/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 34.54 | 0 | 0 | 0
2956 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme , SM/06968 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Chhotobainan village of Chhotobainan piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-173/BWD/2020-21) | 2740/BWD | 10/08/2020 | 30 | BOSE ENTERPRISE | 4.9 | 9.8 | 200 | 1
2957 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chhotobainan Piped Water Supply Scheme , SM/06968 | Retrofitting | Extension of pipeline for CHHOTOBAINAN water supply scheme at Chhotobainan village within Raina-II Block under Burdwan Division, PHE Dte. (Gr.-D) | 956/BSD | 23/07/2021 | 30 | BOSE ENTERPRISE | 4.92 | 8.55 | 200 | 0
2958 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Bundebaj PWSS , SM/06753 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bundebaj (Pt-B) village of Bundebaj Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 8B] (T.R. no. 377/BWD/2020-21) | 2591/BWD | 04/08/2020 | 30 | MAA LAXMI ENTERPRISE | 4.92 | 9.84 | 200 | 1
2959 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Bundebaj PWSS , SM/06753 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bundebaj (Pt-A) village of Bundebaj Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 8A] (T.R. No. 320/BWD/2020-21) | 2586/BWD | 04/08/2020 | 30 | MOMINUL ISLAM MONDAL | 4.92 | 9.84 | 200 | 1
2960 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Bundebaj PWSS , SM/06753 | Retrofitting | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-6] | 4318/BWD | 04/11/2020 | 10 | MD HASIN | 4.93 | 0.32 | 100 | 1
2961 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Bundebaj PWSS , SM/06753 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bohar village and Minapur & Khortikpara habitation of SATGACHIA piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Gr.-4A] | 3326/BWD | 18/09/2020 | 30 | SUBRATA GUPTA | 4.87 | 9.67 | 200 | 0
2962 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme , SM/07820 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Nandanpur and Rampur village within the command area of Keunta Piped Water Supply Scheme at Raina-II Block under Burdwan Division, PHE Dte. [Group : D] | 69/AE/HQ | 11/02/2022 | 30 | SUPER SKILL | 4.16 | 3.85 | 92.5 | 1
2963 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme , SM/07820 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  | 21/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
2964 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme , SM/07820 | Retrofitting | Payment for supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 934/DW | 31/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
2965 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme , SM/07820 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KEUNTA Piped Water Supply Scheme at Kalui, Keunta, Kulpukur, Rathtala, Mandarpur, Rampur & Nandanpur habitation, Raina - I Block under Burdwan Division, PHE Dte. (Agreement No. 57/2020-2021 OF SE/CC/PHE. DTE.) | 4853/BWD | 04/12/2020 | 90 | SUPER SKILL | 95.71 | 49.1 | 51.31 | 1
2966 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme , SM/07820 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ II Block under Burdwan Division, PHE. Dte. | 269/BWD | 14/01/2022 | 30 | PRONAB KUMAR DEY | 6.99 | 3.32 | 100 | 1
2967 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme , SM/07820 | Retrofitting | Repairing of damage concrete work due to laying of pipeline at Keunta within Keunta water supply scheme under Burdwan Division, PHE Dte. [Gr.-G] | 1895/AE/HQ | 16/11/2021 | 30 | DUBE ENTERPRISE | 2.39 | 2.27 | 100 | 1
2968 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme , SM/07820 | Retrofitting | Realignment and culvert crossing of D.I. pipeline at damaged section and repairing of uPVC pipeline at Nandanpur, Keunta and Rampur village within Keunta Piped Water Supply Scheme, Raina ¿ II Block under Burdwan Division, PHE. Dte. [Group : D] | 236/AE/HQ | 19/04/2022 | 30 | SUPER SKILL | 4.61 | 3.15 | 100 | 1
2969 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme , SM/07820 | Retrofitting | Extension of pipe line for providing Functional Household Tap Connection (FHTC) and construction of sluice valve chamber within the command area of KEUNTA Piped Water Supply scheme, Raina-II Block under Burdwan Division, PHE Dte._Gr-H | 138/AE/HQ | 15/03/2022 | 20 | SUPER SKILL | 4.81 | 3.63 | 100 | 1
2970 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme , SM/07820 | Retrofitting | Pipeline with FHTC for KEUNTA Water Supply Scheme at Kalui village (30 Nos.), Keunta village (30 Nos.), Mandarpur village (30 Nos.), Rampur village (30 Nos.), Nandanpur village (60 Nos.), within Raina-II Block, under Burdwan Division, PHE Dte. | 855/BWD | 28/02/2023 | 45 | DUBE ENTERPRISE | 60.1 | 49.88 | 100 | 100
2971 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme , SM/07820 | Retrofitting | Material Requisition To Resource Division | 3692/BWD | 16/07/2021 | 0 | Resource Division | 12.43 | 0 | 0 | 0
2972 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme , SM/07820 | Retrofitting | Hire & fuel charges of vehicle Car No.-WB-41J-6795 for the month of June & July2023. | 745/JJM | 11/10/2023 | 0 | MD HASIN | 0.79 | 0 | 0 | 0
2973 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Keunta Piped Water Supply Scheme , SM/07820 | Retrofitting | Vehicle bill for the office of the Assistant Engineer, Burdwan Division, PHE Dte. for the month of July'23. | 560/JJM | 24/08/2023 | 0 | SK.ASFIA | 0.4 | 0 | 0 | 0
2974 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maheshdanga Piped Water Supply Scheme at Maheshdanga Village (5 Nos. habitations) & Kathalgachhi Village (3 Nos. habitations), Memari ¿ I Block under Burdwan Division, PHE Dte.(Agreement No. 722/BWD of 2020-2021) | 1687/BWD | 24/02/2021 | 60 | PABITRA KUMAR SAMANTA | 54.78 | 108.93 | 193.1 | 1
2975 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maheshdanga Piped Water Supply Scheme at Salda Village (2 Nos. habitations) & Bahara Village (5 Nos. habitations), Jamalpur Block under Burdwan Division, PHE Dte. | 4634/BWD | 09/09/2021 | 60 | CREATION CONSTRUCTION | 52.73 | 52.53 | 100 | 1
2976 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. | 1194/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0 | 0
2977 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Providing FHTC from dist. System within the command area of MAHESDANGA Piped Water Supply Scheme at Deule Village, Salda Village, Bhara Village, Kathalgachi Village & Koleypara Village at Memari-I Development Block under Burdwan Division, PHE Dte. | 1573/BWD | 16/03/2022 | 60 | SUPRIYA RAY | 70.5 | 14.96 | 72.99 | 0
2978 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Canal crossing of Mahesdanga water supply scheme(Node point 192 to 193) under Memari-I Block under Burdwan Division, PHE Dte.[Gr.-D] | 1158/BSD | 31/08/2021 | 30 | RANADHIR SINHA | 4.85 | 0 | 0 | 1
2979 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Construction of boundary wall (North side) including Front Gate at Pump house no - I Site of Maheshdanga Water Supply Scheme under Memari-I Dev. Block of Burdwan Division, PHE Dte. (Length -55.00 Mtr, Col-20 Nos). Gr.D. | 469/BSD | 21/03/2022 | 45 | SK ABDUL HALIM | 4.37 | 0 | 0 | 1
2980 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Providing FHTC from dist. System within the command area of MAHESDANGA Piped Water Supply Scheme at Bahera (Part) and Mahesdanga (Part) Village (Mahesdanga, Aymadeulepara, Kamarpara & Jangalpara Habs.) at Memari-I Development Block under Burdwan Division, PHE Dte. | 1571/BWD | 16/03/2022 | 30 | SUPRIYA RAY | 22.42 | 22.4 | 100 | 1
2981 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Laying of 200 mm dia HDPE distribution pipe line (Node No-402 To 401B) for Mahesdanga & ADJOINING MOUZAS WATER SUPPLY SCHEME at Memari-I Development Block under Burdwan Division, PHE Dte. Group : C | 816/BSD | 20/05/2022 | 30 | M/S ASHA CONSTRUCTION | 4.79 | 0 | 0 | 1
2982 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Sinking of additional 250 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for MAHESHDANGA Piped Water Supply Scheme, Block - Memari - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 2472/BWD | 12/05/2022 | 30 | NADIA TUBEWELLS | 10.32 | 0 | 0 | 1
2983 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Earth work in excavation including shoring work of 700 cum capacity 20 Mtr staging height RCC Over Head Reservoir of Mahesdanga water supply scheme of Memari-I Block under Burdwan Division, PHE Dte.[Gr.-A] | 1365/BSD | 05/10/2021 | 5 | SK ALIM | 4.73 | 0 | 0 | 1
2984 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Laying of 200mm.dia. HDPE Distribution pipe line(Node No.401B to 401)for MAHESHDANGA & adjoining mouzas Water Supply Scheme at Memari-I Development block under Burdwan Division,PHE Dte. Group - D. | 831/BSD | 23/05/2022 | 30 | M/S ASHA CONSTRUCTION | 4.49 | 0 | 0 | 1
2985 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Earth filling and sand filling in excavated portion and land development at Head work site of 700 cum capacity 20 Mtr staging height RCC Over Head Reservoir of Mahesdanga water supply scheme of Memari-I Block under Burdwan Division, PHE Dte.[Gr.-A] | 1408/BSD | 08/10/2021 | 5 | M/S PROCHESTA ENTERPRISE | 4.14 | 0 | 0 | 1
2986 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Construction of boundary wall including land development at 2nd Tube Well site of MAHESHDANGA water supply scheme under Memari-I Block of Burdwan Division, PHE Dte. (Length -52.00 Mtr, Col-20 Nos). " Group : C. | 985/BSD | 16/06/2022 | 45 | MAA MAHAMAYA CONSTRUCTION | 3.46 | 0 | 0 | 1
2987 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Construction of boundary wall (SOUTH side) at Pump house no - I Site of Maheshdanga Water Supply Scheme under Memari-I Dev. Block of Burdwan Division, PHE Dte. (Length -58.00 Mtr, Col-21 Nos). Gr. G | 280/BSD | 15/02/2022 | 45 | SK ABDUL HALIM | 4.19 | 0 | 0 | 1
2988 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Construction of 168 Mtr long P.C.C Approach road from Main Road to OHR site and inside boundary of OHR Site of MAHESHDANGA PWSS under Memari-I Development Block under Burdwan Division PHE Dte. | 3627/BWD | 21/08/2023 | 30 | MANAS BHATTACHARYA | 5.95 | 5.3 | 100 | 100
2989 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Material Requisition To Resource Division | 421/BWD | 20/01/2022 | 0 | Resource Division | 5.49 | 0 | 0 | 0
2990 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Replacement of fully damaged PVC water supply line at Dulepara along National Highway for MAHESDANGA and its adj.mouza W/S Scheme,Block:Memari-I within Burdwan Sub-Division,PHE Dte | 2746/BSD | 28/11/2023 | 30 | SUPRIYA RAY | 0.96 | 0 | 0 | 100
2991 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MAHESHDANGA Piped Water Supply Scheme at Memari-I Block , SM/07855 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Maheshdanga Piped Water Supply Scheme at Deule Village (4 Nos. habitations), Memari ¿ I Block under Burdwan Division, PHE Dte. | 1796/A/BWD | 26/02/2021 | 45 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 27.66 | 55.3 | 200 | 0
2992 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Shura (Zone-I) Piped Water Supply Scheme at Shura Village (3 Nos. habitations), Chakdihi Village & Shukpur Village, Jamalpur Block under Burdwan Division, PHE Dte. | 1763/BWD | 26/02/2021 | 60 | SUKALPA NIRMAN | 83.4 | 108.82 | 132.44 | 1
2993 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Shura (Zone-II) Piped Water Supply Scheme at Haragobindapur Village, Kubajpur Village, Dhapdhara Village, Sonargoria Village, Sahahosenpur Village & Paikpara Village Jamalpur Block under Burdwan Division, PHE Dte. (Agreement No. 687/BWD of 2020-2021) | 1324/BWD | 12/02/2021 | 60 | M/S PIONEER CONSTRUCTION | 73.63 | 71.52 | 100 | 1
2994 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Engineer, Headquarters, Burdwan Division, PHE Dte. for the month of September & October'2022. | 766/VEH/22-23 | 22/11/2022 | 0 | SK. ASRAFUDDIN | 0.7 | 0 | 0 | 0
2995 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Laying of HDPE pipe for providing FHTC in different habitation of Shura Mouza within Shura Piped Water Supply Scheme (Zone-I), Jamalpur Block under Burdwan Division, P.H.E DTE. [Group: ¿A¿] | 1815/AE/HQ | 21/09/2021 | 30 | SUKALPA NIRMAN | 4.79 | 4.22 | 100 | 1
2996 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Laying of HDPE pipe for underground crossing of river embankment at different section of Shura piped water supply scheme (Zone-II) under Burdwan Division, PHE Dte. [Gr.-A] | 1855/AE/HQ | 05/10/2021 | 30 | M/S PIONEER CONSTRUCTION | 4.67 | 0 | 0 | 1
2997 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Laying of rising main for interconnection of Pump House 1 & 2 and distribution main along with bye pass arrangement for Over Head Reservoir for Shura piped water supply scheme (Zone-II) within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-B] | 1226/AE/HQ | 10/02/2021 | 30 | M/S UNIT CONSTRUCTION | 4.29 | 0 | 0 | 1
2998 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Laying of HDPE pipeline at Shura, Chakdighi and Shukpur village for providing FHTC within Shura PWSS (Zone-I), Block-Jamalpur under Burdwan Division, PHE Dte._Gr-A | 124/AE/HQ | 04/03/2022 | 15 | BANGA NIRMAN | 4.71 | 4.56 | 100 | 1
2999 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Laying of HDPE pipeline at Dhapdhara village for providing FHTC within SHURA PWSS (Zone-II), Block-Jamalpur under Burdwan Division, PHE Dte._Gr-A | 133/AE/HQ | 11/03/2022 | 20 | M/S UNIT CONSTRUCTION | 2.79 | 2.79 | 100 | 1
3000 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Supply & delivery of different dia. CIDF Pipes, Sluice valve & fittings for construction of RCC OHR (350 cum capacity) for SHURA (ZONE-I) W/S. Scheme under Burdwan Division, P.H.E. Dte. [Group: B] | 165/AE/HQ | 24/03/2022 | 10 | BENGAL BUILDERS | 3.08 | 0 | 0 | 1
3001 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Laying of rising main for interconnection of Pump House -1 &2 and distribution main alongwith bye-pass arrangement for Over Head Reservoir for Shura piped water supply scheme (Zone-I) within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-A] | 1228/AE/HQ | 10/02/2021 | 30 | BENGAL BUILDERS | 4.71 | 0 | 0 | 1
3002 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Laying of HDPE pipeline at Sonargoria and Kubajur village for providing FHTC within Shura PWSS (Zone-II), Block-Jamalpur under Burdwan Division, PHE Dte._2ND CALL [Group : F] | 204/AE/HQ | 06/04/2022 | 30 | M/S UNIT CONSTRUCTION | 4.81 | 4.71 | 100 | 1
3003 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at leftout area of Chakdighi Gram Panchayat within the command area of SHURA ZONE-I Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. GROUP : C | 426/AE/HQ | 03/08/2022 | 30 | D.M. ENTERPRISE | 3.25 | 3.24 | 100 | 1
3004 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Supplying, laying, fitting, fixing of Sluice valve including construction of valve chamber within command area of SURAH ZONE I PWSS Block Jamalpur under Burdwan Division P.H.E Dte. | 524/AE/HQ | 29/09/2022 | 30 | D.M. ENTERPRISE | 0.41 | 0.37 | 100 | 100
3005 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Extension of pipeline for SHURA (Zone-I) Piped W/S. Scheme Total 115 Nos. FHTC work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Jamalpur Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | 1185/BWD | 15/03/2023 | 30 | SK NUR ALAM | 3.52 | 3.3 | 100 | 100
3006 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Extension of pipeline for SHURA (Zone-II) Piped W/S. Scheme Total 129 Nos. FHTC work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Jamalpur Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | 970/BWD | 03/03/2023 | 30 | SANDIPAN SENGUPTA | 4.08 | 4.08 | 100 | 1
3007 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Beautification work at Head work, 2nd Pump house site of Surah Zone-I PWSS with Arboriculture, Recharge Pit including shaft and anciliary works at (Jamalpur Block) P.W.S.S under Burdwan Division, PHE Dte. | 280/RWS | 03/09/2024 | 10 | D.M. ENTERPRISE | 0.97 | 0 | 0 | 0
3008 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Beautification work at Head work, 2nd Pump house site of Surah Zone-II PWSS with Arboriculture, Recharge Pit including shaft and anciliary works at (Jamalpur Block) P.W.S.S under Burdwan Division, PHE Dte. | 281/RWS | 27/08/2024 | 10 | J.K. CORPORATION | 0.97 | 0 | 0 | 0
3009 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Extension of pipeline & providing Functional House Tap Connection at leftout portion of SHURA Zone-II W/S Scheme within Jamalpur Block under Burdwan Division, P.H.E Dte. | 764/AE/HQ | 25/08/2023 | 30 | SANDIPAN SENGUPTA | 3.93 | 3.93 | 100 | 100
3010 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near Dhapdhara Uttor Pal Para under SHURA Z-II PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 742/AE/HQ | 13/09/2024 | 30 | J.K. CORPORATION | 0.96 | 0.96 | 100 | 100
3011 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Shifting & Relaying of Damaged UPVC Pipeline at Chakdighi for Construction of Road under "PATHASHREE", SHURA ZONE-I PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 745/AE/HQ | 13/09/2024 | 30 | D.M. ENTERPRISE | 0.95 | 0.95 | 100 | 100
3012 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near Dhapdhara Bostom Para under SHURA Z-II PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 743/AE/HQ | 13/09/2024 | 30 | J.K. CORPORATION | 0.94 | 0.94 | 100 | 100
3013 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Re-laying of UPVC (Damaged By WBSRDA Department) pipeline near Dhapdhara Purba Pal Para under SHURA Z-II PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 744/AE/HQ | 13/09/2024 | 30 | J.K. CORPORATION | 0.96 | 0.96 | 100 | 100
3014 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Laying of different dia UPVC pipeline for providing FHTC work at various places under SHURA ZONE- I PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 97/AE/HQ | 15/02/2024 | 30 | D.M. ENTERPRISE | 0.93 | 0.93 | 100 | 100
3015 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Construction & Installation of Sluice valve & valve Chamber to control the flow of water under SHURA ZONE-I PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 98/AE/HQ | 15/02/2024 | 30 | D.M. ENTERPRISE | 0.76 | 0.76 | 100 | 100
3016 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of SHURA Piped Water Supply Scheme at Jamalpur Block , SM/07858 | Retrofitting | Shifting & Relaying of Damaged UPVC Pipeline at Chakdighi Baganbari for Construction of Road under "PATHASHREE", SHURA ZONE-I PWSS, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 746/AE/HQ | 13/09/2024 | 30 | D.M. ENTERPRISE | 0.72 | 0.72 | 100 | 100
3017 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme , SM/07860 | Retrofitting | Pipeline with FHTC for Isufabad Water Supply Scheme at Fagupur village (15 Nos) of Burdwan-I Block, under Burdwan Division, PHE Dte. Gr.C. | 1600/BSD | 14/09/2022 | 30 | DUBE ENTERPRISE | 3.08 | 2.78 | 100 | 1
3018 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme , SM/07860 | Retrofitting | Pipeline with FHTC for Isufabad Water Supply Scheme at ISUFABAD village (15 Nos) of Burdwan-I Block, under Burdwan Division, PHE Dte. Gr.J. | 1607/BSD | 14/09/2022 | 30 | DUBE ENTERPRISE | 1.89 | 1.63 | 100 | 1
3019 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme , SM/07860 | Retrofitting | Extension of pipeline for ISUFABAD Water Supply Scheme at KASIMPUR village within BURDWAN-I Block , under Burdwan Division, PHE Dte.Gr.A | 274/BSD | 15/02/2022 | 30 | SUPRIYA RAY | 4.98 | 0 | 0 | 1
3020 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme , SM/07860 | Retrofitting | Providing 19 Nos. FHTC at ISHUFABAD & GRAMGORIA village for declaration of SWAJALGRAM under ISHUFABAD Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte | 1037/BSD | 10/06/2024 | 30 | DEBASHISH ENTERPRISE | 0.91 | 0 | 0 | 0
3021 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme , SM/07860 | Retrofitting | Providing 35 Nos.FHTC at KASHIMPUR village for declearation of SWAJALGRAM under ISHUFABAD Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. | 1278/BSD | 12/07/2024 | 45 | DUBE ENTERPRISE | 1.64 | 0 | 0 | 0
3022 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of ISUFABAD Piped Water Supply Scheme , SM/07860 | Retrofitting | Providing 19 Nos. FHTC at DHOLAN & FAGUPUR village for declaration of SWAJALGRAM under ISHUFABAD Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. | 1036/BSD | 10/06/2024 | 30 | MUKHERJEE ENTERPRISES | 0.91 | 0 | 0 | 100
3023 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nadangahat Piped Water Supply Scheme , SM/07801 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dhamai village and Dhamai habitation of Nadanghat piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-558/BWD/2020-21) | 4120/BWD | 16/10/2020 | 30 | NANDY UDYOG | 4.85 | 9.69 | 200 | 1
3024 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nadangahat Piped Water Supply Scheme , SM/07801 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Dhamai village and Nimar habitation of Nadanghat piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-389/BWD/2020-21) | 4121/BWD | 16/10/2020 | 30 | RUPALI ENTERPRISE | 4.86 | 9.73 | 200 | 1
3025 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nadangahat Piped Water Supply Scheme , SM/07801 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nadanghat Piped Water Supply Scheme at Kundapara village & Nadanghat village, Purbasthali - I Block under Burdwan Division, PHE Dte. (Agreement No. 700/BWD of 2020-2021) | 1543/BWD | 22/02/2021 | 60 | MAA LAXMI ENTERPRISE | 51.66 | 50.07 | 100 | 1
3026 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nadangahat Piped Water Supply Scheme , SM/07801 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Nadanghat piped water supply scheme at Kundapara village (37 nos FHTC) & Nadanghat village (75 nos FHTC), Purbasthali-I Block within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | 153/KSD | 15/02/2022 | 15 | MAA LAXMI ENTERPRISE | 4.51 | 4.49 | 100 | 1
3027 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nadangahat Piped Water Supply Scheme , SM/07801 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of December22 to February'23. | 30/JJM | 19/04/2023 | 0 | PARTHA PRATIM ACHARYA | 1.19 | 0 | 0 | 0
3028 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme , SM/07865 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Basatpur village of Raipur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿1A¿] | 2726/BWD | 10/08/2020 | 30 | ASHOK KUMAR GHOSH | 4.92 | 4.92 | 100 | 1
3029 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme , SM/07865 | Retrofitting | Providing FHTC in Purba Kashiara village for 100% coverage in Sajal Gram from existing distribution system within RAIPUR PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. Gr.E. | 1368/BSD | 04/08/2022 | 5 | ASHOK KUMAR GHOSH | 0.68 | 0 | 0 | 0
3030 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme , SM/07865 | Retrofitting | Providing FHTC and extension of UPVC distribution pipeline at Raipur, Gumri, Namalpur & Mahipal habitation for RAIPUR Piped Water Supply Scheme at Burdwan - II Development Block under Burdwan Division, PHE Dte. | 104/BWD | 06/01/2022 | 30 | ROY CONSTRUCTION | 23.65 | 23.65 | 100 | 1
3031 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme , SM/07865 | Retrofitting | Shifting & Relaying of 2nd T.Well Raising main and providing 5 nos (100mm dia) S/Valve at existing dist. Line for Raipur water supply scheme at Bardhhaman-II Development Block under Burdwan Division, PHE Dte. Group: H | 1605/BSD | 14/09/2022 | 30 | ASHOK KUMAR GHOSH | 1.72 | 0 | 0 | 0
3032 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme , SM/07865 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Raipur piped water supply scheme at Mahipal (05 Nos Habitation), Purba Kashiara (08 Nos. Habitation), Sahara (04 Nos. Habitation), Sonakur (07 Nos. Habitation), Baratpur (16 Nos, Habitation) & Raipur (10 Nos. Habitation) village, Bardhaman-II Block under Burdwan Division, PHE Dte. | 5007/BWD | 10/12/2020 | 90 | ASHOK KUMAR GHOSH | 43.99 | 3.76 | 100 | 1
3033 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme , SM/07865 | Retrofitting | Providing FHTC (12 Nos.) and extension of UPVC distribution pipeline at Basatpur Habitation for Raipur water supply scheme at Burdwan-II Development Block under Burdwan Division, PHE Dte.[Gr.-A] | 1461/BSD | 01/11/2021 | 30 | ASHOK KUMAR GHOSH | 2.14 | 2.14 | 100 | 1
3034 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme , SM/07865 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) of RAIPUR & its adjoining mouzas Piped Water Supply Scheme, Block - Burdwan - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. _2ND CALL. | 5273/BWD | 30/11/2022 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 9.45 | 7.8 | 100 | 1
3035 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme , SM/07865 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for RAIPUR its Adjoining Mouza W/S Scheme, Block -Bardhaman-II within Burdwan Sub-Division, PHE Dte. (Mouza- PURBA KASHIARA) | 501/BSD | 21/03/2023 | 45 | IRIN CONSTRUCTION CO. | 3.3 | 2.72 | 100 | 100
3036 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme , SM/07865 | Retrofitting | Laying of inter connection between 3rd tube well site and distribution system for Raipur PWSS within Bardhaman-II Block, under Burdwan Division, PHE Dte. | 2039/BSD | 24/08/2023 | 45 | ISHAN CONSTRUCTION | 1.57 | 1.56 | 100 | 100
3037 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme , SM/07865 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Basatpur Village, Burdwan - II Block within Raipur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 856/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 100 | 100
3038 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme , SM/07865 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Mahipal Village, Burdwan - II Block within Raipur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 854/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 100 | 100
3039 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme , SM/07865 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Purba Kashiara Village, Burdwan - II Block within Raipur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 857/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 100 | 100
3040 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme , SM/07865 | Retrofitting | Different type of works related (Internal pathways and approach road 2nd pump, Land-Development, FHTC, repair of boundary wall & pump houses and road restoration) under RAIPUR PWSS under Burdwan-II Block under Burdwan Division, PHE Dte. | 2995/BWD | 01/08/2024 | 184 | PRATIVA CONSTRUCTION | 11.79 | 0 | 0 | 80
3041 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of RAIPUR Piped Water Supply Scheme , SM/07865 | Retrofitting | Providing Parall LDS (Node- 20 to 24) for smoothly getting water at Baral village within Raipur PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | 1026/BWD | 21/03/2025 | 72 | ROY CONSTRUCTION | 8.82 | 0 | 0 | 100
3042 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block , SM/07779 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Natungram village and Natungram, Daspara, Palpara habitation of Lohana piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-475/BWD/2020-21) | 4781/BWD | 02/12/2020 | 30 | PARTHA PRATIM ACHARYA | 2.95 | 0 | 0 | 1
3043 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block , SM/07779 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of LOHAI Piped Water Supply Scheme at Madhabdihi, Bhanjanpur, Akhina & Dakhin Gopalpur Village (Mouza), Raina-II Block under Burdwan Division, PHE Dte. | 4635/BWD | 09/09/2021 | 60 | CREATION CONSTRUCTION | 61.85 | 25.75 | 41.64 | 1
3044 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block , SM/07779 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Lohai Piped Water Supply Scheme at Arui, Dighra, Jotragob, Konerpur & Lohai Village (Mouza), Raina-II Block under Burdwan Division, PHE Dte. [Agreement No. 54/2020-2021 OF SE/CC/PHE. DTE.] | 4888/BWD | 07/12/2020 | 90 | M/S S. CHOUDHURY | 75.66 | 31.29 | 100 | 1
3045 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block , SM/07779 | Retrofitting | Plinth protection and uplift of inner side of base floor of OHR and construction of sluice valve chamber at LOHAI PWSS at Raina-II Block under Burdwan Division PHE Dte. [Group : B] | 446/AE/HQ | 16/08/2022 | 30 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 1.91 | 1.82 | 100 | 1
3046 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block , SM/07779 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Barakalmi & Sirajpur village of Lohana Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 22] | 6188/BWD | 28/10/2021 | 15 | PARTHA PRATIM ACHARYA | 4.86 | 0 | 0 | 1
3047 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block , SM/07779 | Retrofitting | Laying of uPVC pipe for providing FHTC in different habitation of Lohai, Akhina and Dakshin Gopalpur Mouza within Lohai Piped Water Supply Scheme, Raina-II Block under Burdwan Division P.H.E DTE. [Group: ¿E¿] | 1816/AE/HQ | 21/09/2021 | 30 | M/S S. CHOUDHURY | 4.76 | 4.68 | 100 | 1
3048 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block , SM/07779 | Retrofitting | Laying of uPVC pipe for providing FHTC at Madhabdihi, Lohai and Akhina Village within LOHAI Piped Water Supply Scheme, Raina-II Block under Burdwan Division P.H.E Dte._Gr-E | 137/AE/HQ | 15/03/2022 | 20 | M/S S. CHOUDHURY | 4.8 | 4.8 | 100 | 1
3049 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block , SM/07779 | Retrofitting | Laying of uPVC pipe for providing FHTC at Bhanjapur, Alampur and Akhina Village within Lohai Piped Water Supply Scheme, Raina-II Block under Burdwan Division P.H.E Dte.Gr. E | 127/AE/HQ | 04/03/2022 | 15 | M/S S. CHOUDHURY | 4.79 | 4.48 | 100 | 1
3050 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block , SM/07779 | Retrofitting | Laying of dedicated HDPE pipeline for supply of sufficient water at Bhanjapur village of Lohai piped water supply scheme, Raina-II Block under Burdwan Division, PHE Dte. | 6741/BWD | 03/12/2021 | 30 | THREE MAA ENTERPRISE | 20.11 | 0 | 0 | 1
3051 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block , SM/07779 | Retrofitting | Extension of pipeline for providing functional house hold tap connection at Bhanjapur Mouza within Lohai water supply scheme under Burdwan Division, PHE Dte.[Gr.-D] | 1259/AE/HQ | 15/02/2021 | 30 | M/S S. CHOUDHURY | 4.14 | 3.26 | 100 | 1
3052 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block , SM/07779 | Retrofitting | MAINTENANCE OF ROAD (WHISH IS DAMAGED FOR LAYING PIPELINE BY PHE DEPTT) NAMELY NARUGRAM H.C TO BADSHI ROAD VIDE- PACKAGE NO- WB 22 12 UNDER PMGSY-III UNDER NARUGRAM GP. & RAINA-I BLOCK, IN PURBA BARDHAMAN DISTRICT | 894/JJM | 25/09/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 3.86 | 0 | 0 | 0
3053 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Lohai Piped Water Supply Scheme at Raina-II Block , SM/07779 | Retrofitting | Balance Work for extension of pipe lines to provide FHTC with Sinking of Tubwell, Construction of pump house with Boundary wall & other related work for LOHAI PWSS under Burdwan Sub-Div., Block -Raina-II, under Burdwan Division PHE Dte. | 61/BWD | 06/01/2025 | 120 | B.S. ENTERPRISE | 62.48 | 0 | 0 | 0
3054 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme , SM/07821 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of GHOSH Piped Water Supply Scheme at Andur & Bahapur village (Mouza), Memari ¿ I Block under Burdwan Division, PHE Dte.(Agreement No. 577/BWD of 2020-2021) | 437/BWD | 24/02/2021 | 30 | MAJILA ENTERPRISE | 22.76 | 0 | 0 | 1
3055 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme , SM/07821 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Ghosh Piped Water Supply Scheme at Mondaljana Part (Bajamondaljana, Kashirampur & Mondaljana Habitation), Horirampur & Ghosh Part Village (Mouza) Memari-I Block under Burdwan Division, PHE Dte. | 3781/BWD | 22/07/2021 | 30 | KAUSHIK RAY | 20.09 | 40.18 | 200 | 1
3056 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme , SM/07821 | Retrofitting | Providing FHTC from dist. System within the command area of GHOSH Piped Water Supply Scheme at Kashirampur, Joyampur, Sajina, Ichapur, Purba-Gantar, Andur, Bahabpur & Ghosh (Part) village (Mouza) at Memari-I Development Block under Burdwan Division, PHE Dte. | 25/BWD | 04/01/2022 | 30 | MAJILA ENTERPRISE | 36.17 | 36.79 | 100 | 1
3057 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme , SM/07821 | Retrofitting | Extension of pipeline for GHOSH Piped Water Supply Scheme at Mondaljone (6 Nos), Kashirampur (8 Nos),Total 14 Nos FHTC Work for Sajal Gram(As per Field verification report for Har Ghar Jal Certification within Memari-I Block including leftout household water connection (FHTC) under Burdwan Division,PHE Dte. Gr.A. | 1350/BSD | 02/08/2022 | 5 | MAJILA ENTERPRISE | 0.97 | 0.97 | 100 | 1
3058 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme , SM/07821 | Retrofitting | Extension of pipeline for GHOSH Piped Water Supply Scheme at Mondaljona [6 No's], Kashirampur [8 No's],Total 14 No's FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Memari-I Block including leftout husehold water tap connection(FHTC) under Burdwan Division, PHE Dte. | 1350-A/BSD | 02/08/2022 | 5 | MAJILA ENTERPRISE | 0.97 | 0 | 0 | 0
3059 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme , SM/07821 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Memari-I Block (Daluibazar-II, Gopegantar-I & II G.P.) under Burdwan Division, PHE. Dte. Dte._Part-A. | 209/BWD | 11/01/2022 | 30 | M/S ANAND CONSTRUCTION | 21.11 | 0 | 0 | 1
3060 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ghosh Piped Water Supply Scheme , SM/07821 | Retrofitting | Re-Laying of damaged pipeline on distribution system for FHTC work for GHOSH Piped Water Supply Scheme at JOY RAMPUR mouza within MEMARI - I BLOCK under Burdwan Division, PHE Dte. | 104/BSD | 16/01/2025 | 30 | N.S. ENTERPRISE | 4.81 | 0 | 0 | 0
3061 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kasiara Piped Water Supply Scheme atMangolkote Block , SM/07811 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Chanak village of Kashiara piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-259/BWD/2020-21) | 3412/BWD | 22/09/2020 | 30 | BABUL SK | 4.92 | 9.84 | 200 | 1
3062 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kasiara Piped Water Supply Scheme atMangolkote Block , SM/07811 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kashiara village of Kasiara piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-260/BWD/2020-21) | 341/BWD | 22/09/2020 | 30 | HAMID SK | 4.92 | 9.84 | 200 | 1
3063 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kasiara Piped Water Supply Scheme atMangolkote Block , SM/07811 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kashira Piped Water Supply Scheme at Chanak (Part), Gopalbera, Krishnapur, Gatistha & Kashira (Part) Village (Mouza), Mongolkot Block under Burdwan Division, PHE Dte. (Agreement No. 99/SE/CC/PHE/Dte of 2020-2021) | 915/BWD | 02/02/2021 | 60 | MAJUMDER ENTERPRISE | 53.52 | 91.12 | 100 | 0
3064 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL , SM/09415 | Augmentation | Preparation of DPR for augmentation of Dogachia W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-H) | 210/KSD | 23/02/2022 | 21 | ROY CHOWDHURY ASSOCIATES | 2.62 | 2.65 | 100 | 1
3065 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL , SM/09415 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3066 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL , SM/09415 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of DOGACHIA Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte._SL.No-08 | 142/AE/HQ | 16/03/2022 | 10 | MAKALI ENGINEERING CORPORATION | 4.52 | 0 | 0 | 0
3067 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL , SM/09415 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 2nd TW Site of Aug. of DOGACHHIA & its adjoining mouzas Piped Water Supply Scheme, Block ? Purbasthali ? I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 5129/BWD | 21/11/2022 | 30 | MUNSHI ENTERPRISE | 8.72 | 7.89 | 90.47 | 0
3068 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL , SM/09415 | Augmentation | Material Requisition To Resource Division | 1247/BWD | 07/03/2022 | 0 | Resource Division | 4.19 | 0 | 0 | 0
3069 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL , SM/09415 | Augmentation | Material Requisition To Resource Division | 541/BWD | 27/01/2022 | 0 | Resource Division | 9.17 | 0 | 0 | 0
3070 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL , SM/09415 | Augmentation | Material Requisition To Resource Division | 1529/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
3071 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL , SM/09415 | Augmentation | Material Requisition To Resource Division | 949/BWD | 17/02/2022 | 0 | Resource Division | 14.44 | 0 | 0 | 0
3072 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL , SM/09415 | Augmentation | Sinking of tube well, laying dist. system, construction of pump house and laying rising main of DOGACHIA Piped Water Supply Scheme with Kalna Sub-Division under Burdwan Division, PHE. Dte. | 5337/BWD | 04/12/2023 | 120 | MITRA CONSTRUCTION | 78.72 | 15.34 | 19.48 | 20
3073 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL , SM/09415 | Augmentation | Additional work to implement augmentation of DOGACHHIA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 5512/BWD | 14/12/2023 | 30 | PARTHA PRATIM ACHARYA | 9.39 | 6.22 | 66.21 | 100
3074 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL , SM/09415 | Augmentation | Quotation from WBSEDCL for Augmentation of Dogachia water supply scheme for Pump House No.-4 under Burdwan Division, PHE Dte. | 566/JJM | 23/07/2024 | 0 | WBSEDCL | 8.89 | 0 | 0 | 0
3075 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION OF DOGACHIA PWSS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) PURBASTHALI-I BLOCK PURBA BARDHAMAN WEST BENGAL , SM/09415 | Augmentation | Quotation from WBSEDCL for Augmentation of Dogachia water supply scheme for Pump House No.-3 under Burdwan Division, PHE Dte. | 567/JJM | 23/07/2024 | 0 | WBSEDCL | 7.63 | 0 | 0 | 0
3076 | PURBA BARDHAMAN | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District , SM/09416 | Augmentation | Relaying of HDPE pipeline at damaged portion at Kutirpara village within Champahati W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | 152/KSD | 15/02/2022 | 30 | P.C. CONSTRUCTION | 4.84 | 4.85 | 100 | 1
3077 | PURBA BARDHAMAN | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District , SM/09416 | Augmentation | Preparation of DPR for augmentation of Champahati W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-G) | 209/KSD | 23/02/2022 | 21 | INDRANIL DUTTA & ASSOCIATES | 2.7 | 2.71 | 100 | 1
3078 | PURBA BARDHAMAN | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District , SM/09416 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3079 | PURBA BARDHAMAN | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District , SM/09416 | Augmentation | Material Requisition To Resource Division | 564/BWD | 27/01/2022 | 0 | Resource Division | 10.64 | 0 | 0 | 0
3080 | PURBA BARDHAMAN | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District , SM/09416 | Augmentation | Material Requisition To Resource Division | 1534/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
3081 | PURBA BARDHAMAN | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District , SM/09416 | Augmentation | Material Requisition To Resource Division | 950/BWD | 17/02/2022 | 0 | Resource Division | 35.32 | 0 | 0 | 0
3082 | PURBA BARDHAMAN | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District , SM/09416 | Augmentation | Material Requisition To Resource Division | 606/BWD | 28/01/2022 | 0 | Resource Division | 24.12 | 0 | 0 | 0
3083 | PURBA BARDHAMAN | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District , SM/09416 | Augmentation | Material Requisition To Resource Division | 4633/BWD | 17/10/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
3084 | PURBA BARDHAMAN | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District , SM/09416 | Augmentation | Work Order for "Laying of Rising Main for CHAMPAHATI(SM/09416) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | 2187/KSD | 15/03/2024 | 10 | DEL DELTA CONSTRUCTION | 4.82 | 0 | 0 | 2
3085 | PURBA BARDHAMAN | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District , SM/09416 | Augmentation | Augmentation of CHAMPAHATI Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 250 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test with construction of boundary wall at Head works site under Kalna ¿ II Block, District - Purba Bardhaman. | 1655/BWD | 22/03/2022 | 365 | MONDAL ENTERPRISE | 265.13 | 263.45 | 100 | 80
3086 | PURBA BARDHAMAN | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District , SM/09416 | Augmentation | Additional works to implement the CHAMPAHATI Piped Water Supply Scheme under Purbasthali-I Block, Dist :- Purba Burdwan under Burdwan Divn., PHE. Dte. | 1270/BWD | 17/03/2023 | 30 | MONDAL ENTERPRISE | 24.02 | 23.59 | 100 | 50
3087 | PURBA BARDHAMAN | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District , SM/09416 | Augmentation | Additional Work of CHAMPAHATI Piped Water Supply Scheme with sinking of Tube-wells, LDSs, FHTCs, construction of switch rooms & boundary wall with gate under PURBASTHALI-I Block, District:- Purba Bardhaman._2ND CALL. | 370/BWD | 29/01/2024 | 245 | ANWESHA CONSTRUCTION | 59.07 | 50.44 | 75.19 | 20
3088 | PURBA BARDHAMAN | Burdwan Division | Augmentation of CHAMPAHATI PWSS for providing functional household tap connection FHTC in Purbasthali-I block under Burdwan Division in Purba Bardhaman District , SM/09416 | Augmentation | Additional works for construction of OHR having capacity 250 cum in connection with Augmentation of CHAMPAHATI PWSS (SM/09416) under Purbasthali-I Block under Kalna Sub-Division, PHE Dte. | 2924/BWD | 26/07/2024 | 90 | MONDAL ENTERPRISE | 27.44 | 0 | 0 | 2
3089 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Jotshyam, Jurepar, Kadipur, Medgachi, Muragachha, Naopara, Ramanandapur mouzas within the command area of Manikhar piped Water Supply Scheme at Mangolkote Block under Burdwan Divisio , SM/08712 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
3090 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Jotshyam, Jurepar, Kadipur, Medgachi, Muragachha, Naopara, Ramanandapur mouzas within the command area of Manikhar piped Water Supply Scheme at Mangolkote Block under Burdwan Divisio , SM/08712 | Retrofitting | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 2nd TW Site of MANIKHAR & its adjoining mouzas Piped Water Supply Scheme, Block Kalna I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 658/BWD | 21/02/2023 | 30 | DAS CONSTRUCTION | 8.72 | 8.14 | 93.36 | 1
3091 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Jotshyam, Jurepar, Kadipur, Medgachi, Muragachha, Naopara, Ramanandapur mouzas within the command area of Manikhar piped Water Supply Scheme at Mangolkote Block under Burdwan Divisio , SM/08712 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of MANIKHAR Piped Water Supply Scheme at Kalna-I Block under Burdwan Division, PHE Dte. (Agreement No. 47/2020-2021 OF SE/CC/PHE. DTE.) | 4787/BWD | 02/12/2020 | 90 | H SAMANTA | 96.04 | 74.56 | 100 | 1
3092 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Jotshyam, Jurepar, Kadipur, Medgachi, Muragachha, Naopara, Ramanandapur mouzas within the command area of Manikhar piped Water Supply Scheme at Mangolkote Block under Burdwan Divisio , SM/08712 | Retrofitting | Material Requisition To Resource Division | 1112/BWD | 26/02/2022 | 0 | Resource Division | 28.05 | 0 | 0 | 0
3093 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Jotshyam, Jurepar, Kadipur, Medgachi, Muragachha, Naopara, Ramanandapur mouzas within the command area of Manikhar piped Water Supply Scheme at Mangolkote Block under Burdwan Divisio , SM/08712 | Retrofitting | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 11 Nos. Piped W/S. Schemes under Kalna I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3015/BWD | 05/08/2024 | 60 | HORIZEN | 29.6 | 7.4 | 100 | 10
3094 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09489 | Augmentation | Route Survey & Preparation of DPR for Nababhat W/S Scheme under Burdwan-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl. No.14. | 189/BSD | 31/01/2022 | 30 | RADIANT | 2.87 | 2.86 | 100 | 1
3095 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09489 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3096 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09489 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of NABABHAT & its adjoining mouzas Piped Water Supply Scheme, Block - Burdwan - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 5194/BWD | 24/11/2022 | 30 | ANIRUDDHA FARUQUE | 11.24 | 9.61 | 85.49 | 1
3097 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09489 | Augmentation | Construction of boundary wall at East side of Nababhat PHE Complex Burdwan Division, PHE Dte. (Length-106.0Mtr, Col-37 Nos.) | 4664/BWD | 10/09/2021 | 30 | MANAS KUMAR CHATTERJEE | 7.89 | 8.03 | 100 | 1
3098 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09489 | Augmentation | Land Development at East Side of Office Building under Nababhat PHE Complex under Burdwan Sub-Division in Burdwan Division,PHE Dte. Gr.D. | 277/BSD | 15/02/2022 | 30 | MANAS KUMAR CHATTERJEE | 3.17 | 3.17 | 100 | 1
3099 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09489 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Paharhati, Nababhat, Shyamsundar & Dewandighi-Mirzapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. | 4703/BWD | 19/10/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 3.61 | 100 | 1
3100 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09489 | Augmentation | Wall Painting at East Side Boundary Wall of Nababhat PHE Complex for IEC Programme for FHTC WORK under Burdwan Sub-Division, PHE Dte. Gr. A. | 1067/BSD | 27/06/2022 | 7 | FIVE HURDS ENGINEERING FARM | 0.4 | 0.39 | 100 | 1
3101 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09489 | Augmentation | Construction of boundary wall (with main gate) at west side of Nababhat PHE complex of Augmentation of Nababhat under Burdwan Division, PHE Dte. (Length-110 Mtr, Col-45 Nos.) | 6254/BWD | 01/11/2021 | 30 | SUROVI CONSTRUCTION AND GENERAL ORDER SUPPLIERS | 7.05 | 6.59 | 100 | 0
3102 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09489 | Augmentation | Material Requisition To Resource Division | 1322/BWD | 08/03/2022 | 0 | Resource Division | 12.13 | 0 | 0 | 0
3103 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09489 | Augmentation | Material Requisition To Resource Division | 1238/BWD | 07/03/2022 | 0 | Resource Division | 4.19 | 0 | 0 | 0
3104 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09489 | Augmentation | Material Requisition To Resource Division | 544/BWD | 27/01/2022 | 0 | Resource Division | 25.82 | 0 | 0 | 0
3105 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09489 | Augmentation | Material Requisition To Resource Division | 1537/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
3106 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based NABABHAT PWSS to accommodate FHTC in BURDWAN-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09489 | Augmentation | Augmentation of NABABHAT Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 450 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation & repairing of Pump House at Head works & 2nd TW site under Burdwan I Block, District - Purba Bardhaman. | 1964/BWD | 12/04/2022 | 1085 | S.P. CONSTRUCTION | 514.15 | 442.02 | 91.71 | 100
3107 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KAITHAN PWSS TO ACCOMMODATE FHTC IN KATWA-I BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09568 | Augmentation | Route Survey and preparation of DPR for KAITHAN PWSS under Katwa-I & II Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-02] | 45/KTS | 24/01/2022 | 21 | RADIANT | 2.59 | 2.59 | 100 | 1
3108 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KAITHAN PWSS TO ACCOMMODATE FHTC IN KATWA-I BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09568 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3109 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KAITHAN PWSS TO ACCOMMODATE FHTC IN KATWA-I BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09568 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Baharan-Birampur, Kaithan, Majhigram-Sigot & Ketugram (Zone-I & II) Piped Water Supply Scheme within Katwa Sub-Division under Burdwan Division, P.H.E. Dte. | 4702/BWD | 19/10/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 7.22 | 100 | 1
3110 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KAITHAN PWSS TO ACCOMMODATE FHTC IN KATWA-I BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09568 | Augmentation | Material Requisition To Resource Division | 1324/BWD | 08/03/2022 | 0 | Resource Division | 17.01 | 0 | 0 | 0
3111 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KAITHAN PWSS TO ACCOMMODATE FHTC IN KATWA-I BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09568 | Augmentation | Material Requisition To Resource Division | 1377/BWD | 09/03/2022 | 0 | Resource Division | 4.13 | 0 | 0 | 0
3112 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KAITHAN PWSS TO ACCOMMODATE FHTC IN KATWA-I BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09568 | Augmentation | Material Requisition To Resource Division | 547/BWD | 27/01/2022 | 0 | Resource Division | 17.27 | 0 | 0 | 0
3113 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KAITHAN PWSS TO ACCOMMODATE FHTC IN KATWA-I BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09568 | Augmentation | Material Requisition To Resource Division | 1542/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
3114 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KAITHAN PWSS TO ACCOMMODATE FHTC IN KATWA-I BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09568 | Augmentation | Material Requisition To Resource Division | 1089/BWD | 25/02/2022 | 0 | Resource Division | 32.22 | 0 | 0 | 0
3115 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KAITHAN PWSS TO ACCOMMODATE FHTC IN KATWA-I BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09568 | Augmentation | Augmentation of KAITHAN Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation including repairing of pump house at Head Works & 2nd TW site under Katwa ¿ I Block, District - Purba Bardhaman. | 2007/BWD | 13/04/2022 | 365 | VISHAL CONSTRUCTION CO. | 365.96 | 348.32 | 95.18 | 95
3116 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED KAITHAN PWSS TO ACCOMMODATE FHTC IN KATWA-I BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09568 | Augmentation | Construction of Boundary Wall at Head Work site of KAITHAN PWSS under Katwa-I Block under Katwa Sub-Division within Burdwan Sub-Division PHE Dte. | 5200/BWD | 29/11/2023 | 30 | SUBODH KUMAR MONDAL | 22.82 | 0 | 0 | 75
3117 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09713 | Augmentation | Route Survey & Preparation of DPR for DIGNAGAR PWSS under Durgapur (Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-B] | 100/DSD | 18/02/2022 | 15 | SIRCON ENGINEERING SERVICES | 2.81 | 2.81 | 100 | 1
3118 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09713 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3119 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09713 | Augmentation | Augmentation of DIGNAGAR Piped Water Supply Scheme with LDS, FHTC Work, Rising Main, Switch room (with water supply & sanitary arrangements), 400 cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Boundary wall construction (New TW Site) with repairing of existing switch room cum chlorine room, Block ¿ Ausgram ¿ I, District - Purba Bardhaman. | 289/BWD | 17/01/2022 | 365 | S.S. ENTERPRISE | 390.11 | 388.86 | 100 | 1
3120 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09713 | Augmentation | Sinking of additional 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Augmentation of DIGNAGAR Piped Water Supply Scheme, Block - Ausgram I, Dist Purba Bardhaman under Burdwan Division, PHE Dte. | 2234/BWD | 29/04/2022 | 30 | J. K. CORPORATION | 14.12 | 12.03 | 100 | 1
3121 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09713 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Dignagar, Galsi, Barabelun & Kotachandipur Piped Water Supply Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, P.H.E. Dte. _2ND CALL | 3624/BWD | 22/08/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.76 | 3.69 | 100 | 1
3122 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09713 | Augmentation | Laying of UPVC pipe line by replacement of AC pipe, installation new SSP and Sluice valve, restoration of existing Street Stand Posts, Valve chamber, and allied work of DIGNAGAR W/S Scheme under Durgapur (Burdwan North)Sub Division under Burdwan Division, P.H.E. Dte.[Gr.-F] | 624/DSD | 25/10/2021 | 45 | ANWESHA CONSTRUCTION | 2.08 | 2.04 | 100 | 1
3123 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09713 | Augmentation | Material Requisition To Resource Division | 552/BWD | 27/01/2022 | 0 | Resource Division | 12.66 | 0 | 0 | 0
3124 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09713 | Augmentation | Material Requisition To Resource Division | 1326/BWD | 08/03/2022 | 0 | Resource Division | 36.24 | 0 | 0 | 0
3125 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09713 | Augmentation | Material Requisition To Resource Division | 1379/BWD | 09/03/2022 | 0 | Resource Division | 4.45 | 0 | 0 | 0
3126 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09713 | Augmentation | Material Requisition To Resource Division | 618/BWD | 28/01/2022 | 0 | Resource Division | 22.71 | 0 | 0 | 0
3127 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09713 | Augmentation | Material Requisition To Resource Division | 1558/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
3128 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09713 | Augmentation | Quotation for Dignagar water supply scheme. P.H. No.-03 [Quotation Memo No.-5003612925/Quot/03, dt.-17/02/2023] | 1169/JJM | 10/03/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.06 | 0 | 0 | 0
3129 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09713 | Augmentation | Installation of AIR valve with MS pipe Connection near both side of Dignagar irrigation Canal under Augmentation of DIGNAGAR and its adjoining mouza¿s piped W/S Scheme at Ausgram-I Block within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | 912/DSD | 15/12/2023 | 30 | S.S. ENTERPRISE | 0.96 | 0.91 | 100 | 100
3130 | PURBA BARDHAMAN | Durgapur W/S Division | Augmentation of Ground Water based Piped Water Supply Scheme for DIGNAGAR to accommodate FHTC under Jal Sapno Mission under Ausgram-I Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09713 | Augmentation | Acceptance cum formal work order for the work of " Supplying & Laying of different dia UPVC pipe at Dignagar under Dignagar PWSS, Block- Aushgram-I, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 761/DWSD | 06/06/2024 | 260 | SAFTI PRIVATE LIMITED | 53.8 | 0 | 0 | 35
3131 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Route Survey & Preparation of DPR for BHATAKUL PWSS under Durgapur(Bardhaman North) Sub-Division under Burdwan Division PHE Dte.[SL-F] | 106/DSD | 18/02/2022 | 15 | SIRCON ENGINEERING SERVICES | 2.63 | 2.63 | 100 | 1
3132 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. | 1194/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0 | 0
3133 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Shifting of 25 KVA S/STN with Selenda 11KV HTOH Line from the premises of Bhatakul PWSS under Burdwan Division, PHE Dte. | 550/DW/22-23 | 13/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 2.43 | 0 | 0 | 0
3134 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3135 | PURBA BARDHAMAN | Central Mechanical | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augmentation of Bhatakul (Zone-I) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2093/CMD | 08/09/2022 | 30 | CHOUDHURY ENTERPRISE | 10.82 | 10.73 | 100 | 1
3136 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Construction of Drum Sheet Walling and Approach road to HW site for Augmentation of Bhatakul (Zone-I ) Piped water supply Scheme , P.H.E Dte. Block:-Bhatar, Dist: Purba Bardhaman. SL-13 | 653/DSD | 03/11/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 2.99 | 2.99 | 100 | 100
3137 | PURBA BARDHAMAN | Central Mechanical | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Restoration of power line for New Well No. 1 at Bhatakul (Zone - I) Water Supply Scheme, under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1370/CMSD - I | 30/12/2022 | 15 | CHOUDHURY ENTERPRISE | 1.66 | 1.66 | 100 | 1
3138 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Material Requisition To Resource Division | 548/BWD | 27/01/2022 | 0 | Resource Division | 9.39 | 0 | 0 | 0
3139 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Material Requisition To Resource Division | 1543/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
3140 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Material Requisition To Resource Division | 1374/BWD | 09/03/2022 | 0 | Resource Division | 3.83 | 0 | 0 | 0
3141 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Material Requisition To Resource Division | 1338/BWD | 08/03/2022 | 0 | Resource Division | 56.67 | 0 | 0 | 0
3142 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Material Requisition To Resource Division | 768/BWD | 07/02/2022 | 0 | Resource Division | 38.41 | 0 | 0 | 0
3143 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Material Requisition To Resource Division | 3276/BWD | 29/07/2022 | 0 | Resource Division | 69.15 | 0 | 0 | 0
3144 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell site for Augmentation of BHATAKUL (Zone-I & II) Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | 1962/BWD | 12/04/2022 | 45 | ACME CONSTRUCTION | 22.05 | 16.19 | 100 | 100
3145 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Augmentation of BHATAKUL Piped Water Supply Scheme (Zone - I & II) including Laying Distribution System, Functional Household Tap Connection, Pumping Main, 350 Cum capacity Over Head Reservoir with 20 Mtr. staging height (including Soil Testing), Switch Room with sanitary arrangement, construction of Boundary wall in Head work site and repairing of pump house at Bhatar Block in under Burdwan Division, PHE. Dte. | 277/BWD | 14/01/2022 | 657 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 351.08 | 206.56 | 59.6 | 100
3146 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Quotation from WBSEDCL for Augmentation of Bhatakul Zone-2 water supply scheme for P.H.-2 under Burdwan Division, PHE Dte. | 536/JJM | 18/07/2024 | 0 | WBSEDCL | 11.79 | 0 | 0 | 0
3147 | PURBA BARDHAMAN | Central Mechanical | Augmentation of Ground Water based Piped Water Supply Scheme for BHATAKUL (Zone-I & II) to accommodate FHTC under Jal Sapno Mission under Bhatar Block in Purba Bardhaman District under Burdwan Division, P.H.E. DTE. , SM/09715 | Augmentation | Quotation for new service connection for Bhatakul PWSS Zone-2, PH-2. |  | 19/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 11.79 | 0 | 0 | 0
3148 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC WITHIN THE COMMAND AREA OF BHALKI WATER SUPPLY SCHEME AUSGRAM II BLOCK PURBA BARDHAMAN , SM/10055 | Retrofitting | Construction of Drain and restoration of connection for Augmentation of BHALKI W/S Scheme , Block- Ausgram-II, under Durgapur (Burdwan North)Sub Division Burdwan Division, P.H.E. Dte. [SL-B] | 334/DSD | 27/06/2022 | 30 | TAUSIF HOSSAIN MONDAL | 1.88 | 0 | 0 | 1
3149 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC WITHIN THE COMMAND AREA OF BHALKI WATER SUPPLY SCHEME AUSGRAM II BLOCK PURBA BARDHAMAN , SM/10055 | Retrofitting | Making structure with GI pipe for provision of joining and laying of pipeline near Abhirampur branch Canal for Bhalki and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-H] | 349/DSD | 30/06/2022 | 45 | PARTHA RAY | 1.9 | 0 | 0 | 1
3150 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC WITHIN THE COMMAND AREA OF BHALKI WATER SUPPLY SCHEME AUSGRAM II BLOCK PURBA BARDHAMAN , SM/10055 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of augmentation BHALKI Piped Water Supply Scheme at Bhalki (Part), Chandipur (Part), Samantapara (Part), Telota (Part) & Abhirampuri (Part) village, habitation, Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. | 1907/BWD | 07/04/2022 | 30 | ROY CONSTRUCTION | 49.52 | 49.18 | 100 | 1
3151 | PURBA BARDHAMAN | Durgapur W/S Division | RETROFITTING WORKS FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION FHTC WITHIN THE COMMAND AREA OF BHALKI WATER SUPPLY SCHEME AUSGRAM II BLOCK PURBA BARDHAMAN , SM/10055 | Retrofitting | Acceptance cum Formal Work Order for the work of Sinking of 250 x 150 mtr deapth by DR Rig and supplying and laying of UPVC pipe line (LDS) and construction of temporary KIOSK for arrangement of electrification of Tube well at BHALKI under BHALKI PWSS , Block- Ausgram-II, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 772/DWSD | 06/06/2024 | 360 | EVEREST INFRATECH INC | 64.56 | 0 | 0 | 5
3152 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Palasan PWSS , SM/06772 | Retrofitting | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of PALASON piped water supply scheme at Raina-I Block under Burdwan Division, PHE Dte._2nd call. | 1409/BWD | 18/02/2021 | 60 | S.S. ENTERPRISE | 72.41 | 71.05 | 137.3 | 1
3153 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Palasan PWSS , SM/06772 | Retrofitting | Interconnection between Raising Main to OHR & OHR to distribution System with bypass arrangement for Palason Water Supply Scheme within Raina-I Block under Burdwan Division, PHE Dte._2ND CALL Gr.E. | 278/BSD | 15/02/2022 | 30 | S.S. ENTERPRISE | 3.23 | 0 | 0 | 1
3154 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Palasan PWSS , SM/06772 | Retrofitting | Construction of concrete road and rest portion of Boundary Wall at Head Works Site of PALASON Water Supply Scheme under Raina-I Block of Burdwan Division,PHE Dte(Length-48.00 Mtr,Col-16 Nos)[Front Side]Gr.F. | 279/BSD | 15/02/2022 | 45 | NEW MANGES INDUSTRIAL CORPORATION | 4.12 | 4.17 | 100 | 1
3155 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | Providing Functional Household tap connection (FHTC) from existing distribution system within the command area of NABASTHA piped water supply scheme at Begut, Bodhpur, Chakundi, Nabastha & Palsha village, Burdwan-II Block under Burdwan Division, PHE Dte.[Tr No.-65/BWD/20-21] | 5003/BWD | 10/12/2020 | 90 | M/S ASHA CONSTRUCTION | 88.6 | 70.86 | 134.68 | 1
3156 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nabastha Piped Water Supply Scheme at Saligram (9 Nos Habitation) Village (Mouza), Burdwan-II Block under Burdwan Division, PHE Dte. | 3447/BWD | 29/06/2021 | 30 | PAL CONSTRUCTION | 19.73 | 19.19 | 100 | 1
3157 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | Providing FHTC from existing distribution pipe line system within command area of Nabastha Piped W/S. Scheme at Chakundi- Mouza, Bardhaman-II Development Block under Burdwan Division, PHE Dte. | 3138/BWD | 19/07/2022 | 30 | BABUL SK | 11.86 | 12.12 | 100 | 1
3158 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | Construction of boundary wall at Head works site of NABASTHA Piped Water Supply Scheme in Burdwan-II Block under Burdwan Division, PHE Dte. (Length - 154 Mtr., 69 Nos Column). | 2742/BWD | 08/06/2022 | 30 | MOYAZZEM CONSTRUCTION | 10.54 | 10.01 | 94.95 | 1
3159 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage in Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ II Block under Burdwan Division, PHE. Dte. | 385/BWD | 20/01/2022 | 30 | BISWAS ENTERPRISE | 11.97 | 0 | 0 | 100
3160 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | Speacial repairing and replace damaged pipe line from Nabastha bus stand to saligram & chakundi village of Nabastha piped water supply scheme at Bardhhaman-II Block under Burdwan Div., PHE Dte.Gr.A. | 467/BSD | 21/03/2022 | 30 | SETH ENTERPRISE | 4.82 | 4.77 | 100 | 1
3161 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | Providing FHTC in Chakundi, Nabastha & Saligram village for 100% coverage in Sajal Gram from existing distribution system within NABASTHA PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | 1728/BWD | 13/04/2023 | 30 | KAUSHIK RAY | 23.96 | 23.87 | 100 | 100
3162 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | Laying of distribution system of different damaged section at Begut, Nabastha & Palsha village regarding smooth running FHTC work within Nabastha PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | 784/BSD | 28/04/2023 | 30 | D.M. ENTERPRISE | 0.95 | 0.94 | 100 | 100
3163 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04H-9111) for the office of the Superintending Engineer, Central Circle, PHE Dte. for the month of December'22 & January'23. | 1116/JJM | 27/02/2023 | 0 | SOURAV JANA | 0.8 | 0 | 0 | 0
3164 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41J-6795) for the office of the Deputy Superintending Engineer, Central Circle, PHE Dte. for the month of March to May'23. | 430/JJM | 25/07/2023 | 0 | MD HASIN | 1.04 | 0 | 0 | 0
3165 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | Preparation and Submission of DPR for Augmentation of Ground Water Based Piped Water Supply Scheme for NABASTHA, Block:Burdwan-II under Burdwan Division, P.H.E Dte. | 1908/BSD | 28/08/2024 | 15 | MEASURE LAND | 0.78 | 0 | 0 | 0
3166 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | Laying of interconnection between 4th tube well to OHR for Nabastha Water Supply Scheme within Burdhaman-II Block , under Burdwan Division, PHE Dte. | 430/BSD | 15/03/2023 | 30 | D.M. ENTERPRISE | 0.91 | 0.67 | 100 | 100
3167 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | Providing FHTC for 100% coverage at Palsha (30 nos) & Begut (13nos) and special repairing of Nabastha, Begut & Palsha village for Nabastha Piped W/S scheme , Bardhhaman-II Dev. Block under Burdwan Division, PHE Dte" Gr.C. | 1405/BSD | 10/08/2022 | 212 | M/S ASHA CONSTRUCTION | 4.71 | 0 | 0 | 100
3168 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | Different type of works releted at head work side (Internal pathways , Land-Development, repair of pump house and drain) under Nabastha PWSS under Burdwan-II Block under Burdwan Division, PHE Dte. | 1272/BSD | 12/07/2024 | 173 | M/S PALASH BISWAS | 4.77 | 4.75 | 100 | 100
3169 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of NABASTHA Piped Water Supply Scheme , SM/07864 | Retrofitting | FIXING OF DISPLAY BOARD WITH M.S STRUCTURE CONTAINING LAND DESCRIPTION AT NABASTA PWSS AND OTHER SCHEMES (57Nos) WITHIN BHATAR BLOCK UNDER BURDWAN DIVISION, PHE Dte. | 1087/DSD | 11/12/2024 | 15 | SHANKHA GHOSH | 3.7 | 0 | 0 | 100
3170 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11491 | New | Material Requisition To Resource Division | 5522/BWDQ | 23/12/2022 | 0 | Resource Division | 8.88 | 0 | 0 | 0
3171 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11491 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Kalera Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | 3115/CMD | 23/11/2022 | 30 | P.K. ENGINEERING | 11.07 | 10.73 | 100 | 80
3172 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11491 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Kalera Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | 3116/CMD | 23/11/2022 | 30 | DUTTA ENTERPRISE | 11.08 | 7.74 | 100 | 80
3173 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11491 | New | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR KALERA W/S (TW-I) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. | 319/CMSD-I | 21/07/2022 | 15 | C.M. ENTERPRISE | 1.74 | 1.74 | 100 | 1
3174 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11491 | New | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KALERA W/S (TW-I) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. | 316/CMSD-I | 22/07/2022 | 15 | C.M. ENTERPRISE | 3.28 | 3.22 | 100 | 1
3175 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11491 | New | PROVIDING TUBE WELL MATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KALERA W/S SCH (TW-II) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. | 317/CMSD-I | 22/07/2022 | 15 | C.M. ENTERPRISE | 3.28 | 3.12 | 100 | 1
3176 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11491 | New | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT KELERA W/S (TW-I) SCHEME, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. | 320/CMSD-I | 21/07/2022 | 15 | C.M. ENTERPRISE | 1.88 | 1.19 | 100 | 1
3177 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11491 | New | Additional Transportation of Departmental rig unit no. Super RR with compressor and pump unit from Kalera PWSS under CDD, PHE dte. | 532/CMSD-II(D) | 01/12/2022 | 7 | PADMA ENGINEERING & CO. | 0.75 | 0.75 | 100 | 1
3178 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11491 | New | Providing drilling crews for construction of TW (250mm x 150mm) by Departmental rig machine for kalera WS (TW-II), Jamalpur block purba Burdwan, CDD, PHE Dte. | 330/CMSD-I(D) | 15/07/2022 | 15 | C.M. ENTERPRISE | 1.74 | 1.38 | 100 | 1
3179 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11491 | New | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT KALERA W/S SCH (TW-II) SCH, JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. | 331/CMSD-I | 15/07/2022 | 15 | C.M. ENTERPRISE | 1.88 | 1.16 | 100 | 1
3180 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11491 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 12.9 | 0 | 0 | 0
3181 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11491 | New | New Service Connection Charges for Kalera W/S Scheme PH-1 | 25 | 02/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.51 | 0 | 0 | 0
3182 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11491 | New | New Service Connection Charges for Kalera W/S Scheme PH-2 | 26 | 02/01/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.9 | 0 | 0 | 0
3183 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED KALERA PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11491 | New | Hiring of Diesel driven motor cab (BS-III & above) having contract carriage permit along with driver for the office of the Executive Engineer, CDD, PHE Dte. | 45/S&WSD | 26/04/2023 | 7 | ASHUTOSH DAS & CO | 0.87 | 1.69 | 100 | 83
3184 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/10391 | Augmentation | Construction of 600 cum capacity 20 mtr staging height RCC Over Head Reservoir including pipe connection and cost of pipes, specials for Bonpass-Kamarpara & its adjoining mouzas water supply scheme under Burdwan Division, PHE Dte. | 3655/BWD | 14/07/2021 | 180 | ASHOK MITRA | 107 | 0 | 0 | 1
3185 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/10391 | Augmentation | Sinking of additional 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 4th & 5th Tube well Site for Augmentation of BONPAS-KAMARPARA Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | 3031/BWD | 07/07/2022 | 45 | B.K. ENTERPRISE | 28.13 | 0 | 0 | 1
3186 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/10391 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 5 at BonpassKamarpara Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3329/CMD | 12/12/2022 | 30 | CHOUDHURY ENTERPRISE | 10.09 | 9.82 | 100 | 100
3187 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/10391 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 4 at BonpassKamarpara Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3328/CMD | 12/12/2022 | 30 | P.K. ENGINEERING | 10.06 | 9.65 | 100 | 80
3188 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/10391 | Augmentation | Augmentation of BANPAS Piped Water Supply Scheme (Dhandalsa Mouza) with LDS & FHTC and construction of Pump House at 4th TW site under Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-F]. | 891/BWD | 01/03/2023 | 60 | DEY NIRMAN | 71.08 | 71.08 | 100 | 100
3189 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/10391 | Augmentation | Repairing of Switch room cum chlorine room with sanitary and water supply arrangement (P.H-2) at 2nd Tubewell Site for Bonpas-Kamarpara and its adjoining mouza's water supply scheme under Durgapur Sub-Division, P.H.E Dte. Block:-Bhatar, Dist:Purba Bardhaman. [Gr.-F] | 499/DSD | 12/08/2022 | 30 | SUPRIYA RAY | 2.03 | 0 | 0 | 100
3190 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/10391 | Augmentation | Augmentation of BANPAS KAMARPARA Piped Water Supply Scheme (Haribati & Chandai Mouza) with LDS & FHTC within Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-E]. | 2262/BWD | 18/05/2023 | 60 | M/S K.P. CONSTRUCTION | 80.02 | 57.31 | 71.62 | 80
3191 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/10391 | Augmentation | Augmentation of BANPAS Piped Water Supply Scheme (Narayanpur Mouza) with LDS, FHTC and Construction of Pump House at 4th TW site under Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-D]. | 1029/BWD | 09/03/2023 | 60 | SARKAR AGENCY | 111.93 | 111.2 | 100 | 100
3192 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/10391 | Augmentation | Augmentation of BANPAS KAMARPARA Piped Water Supply Scheme (Ambana Mouza) with LDS, FHTC and Construction of Pump House at 4th TW site under Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-B]. | 2261/BWD | 18/05/2023 | 60 | M/S K.P. CONSTRUCTION | 91.92 | 88.24 | 100 | 100
3193 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/10391 | Augmentation | Augmentation of BONPAS KAMARPARA Piped Water Supply Scheme (Banpas Mouza) with LDS, Rising main, FHTC and construction of Boundary wall for existing TW site under Bhatar Block, District:- Purba-Burdwan. (PART - A) | 3110/BWD | 19/07/2023 | 120 | R.G. INFRASTRUCTURE | 389.91 | 312.73 | 75.35 | 80
3194 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/10391 | Augmentation | Augmentation of BANPAS Piped Water Supply Scheme (Mohanpur Mouza) with LDS & FHTC under Bhatar Block, District:- Purba-Burdwan under Burdwan Division, PHE. Dte. [PART-C]. | 888/BWD | 01/03/2023 | 60 | KOUSIK MALLICK | 104.59 | 106.42 | 100 | 100
3195 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR BONPAS KAMARPARA TO ACCOMMODATE FHTC UNDER BHATAR BLOCK IN PURBA BARDHAMAN DISTRICT UNDER BURDWAN DIVISION PHE DTE , SM/10391 | Augmentation | Illumination arrangement and miscelleneous works at Bonpas Kamarpara water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2785/CMD | 01/10/2024 | 60 | CINZANO | 14.08 | 0 | 0 | 50
3196 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] | 1759/BSD | 28/07/2023 | 66 | MD HASIN | 0.85 | 0 | 0 | 0
3197 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Supply & delivery of different dia. MJ Coller for FHTC as well as smooth running of different W/S. Schemes under Burdwan Division, P.H.E. Dte. [i.e. (1) Magra PWSS, Memari-I Block, (2) Kuchut PWSS, Memari - II Block, (3) Khundkuri PWSS, Khandaghosh Block & (4) Samanti PWSS, Burdwan - II Block)] | 4076/BWD | 13/09/2023 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 20.63 | 5 | 100 | 100
3198 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Material Requisition To Resource Division | 1269/BWD | 17/03/2023 | 0 | Resource Division | 14.2 | 0 | 0 | 0
3199 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Material Requisition To Resource Division | 3990/BWD | 08/09/2023 | 0 | Resource Division | 1.7 | 0 | 0 | 0
3200 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Material Requisition To Resource Division | 5051/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
3201 | PURBA BARDHAMAN | Central Mechanical | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | New service connection charges for Kuchut PWSS TW-1 | BP-2023-24-77 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.87 | 0 | 0 | 0
3202 | PURBA BARDHAMAN | Central Mechanical | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | New service connection charges for Kuchut PWSS TW-2 | BP-2023-24-78 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.83 | 0 | 0 | 0
3203 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.06.2024 to 31.07.2024] | 305/AE/HQ | 31/05/2024 | 61 | SOURAV JANA | 0.8 | 0.8 | 99.91 | 0
3204 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.10.2024 to 30.11.2024] | 822/AE/HQ | 01/10/2024 | 61 | SOURAV JANA | 0.8 | 0.76 | 94.95 | 0
3205 | PURBA BARDHAMAN | Central Mechanical | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
3206 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.02.2024 to 31.03.2024] | 41/AE/HQ | 29/01/2024 | 60 | SOURAV JANA | 0.8 | 0.8 | 99.69 | 50
3207 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.04.2024 to 31.05.2024] | 232/AE/HQ | 28/03/2024 | 61 | SOURAV JANA | 0.8 | 0.8 | 99.87 | 0
3208 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.08.2024 to 30.09.2024] | 546/AE/HQ | 01/08/2024 | 61 | SOURAV JANA | 0.8 | 0.8 | 99.97 | 0
3209 | PURBA BARDHAMAN | Central Mechanical | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kuchut Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2512/CMD | 02/06/2023 | 30 | CHOUDHURY ENTERPRISE | 29.4 | 24.17 | 100 | 50
3210 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.12.2024 to 31.01.2025] | 1011/AE/HQ | 29/11/2024 | 61 | SOURAV JANA | 0.8 | 0.8 | 99.62 | 0
3211 | PURBA BARDHAMAN | Central Mechanical | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3103/CMD | 11/12/2024 | 60 | S DUTTA | 15.06 | 0 | 0 | 0
3212 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.02.2025 to 31.03.2025] | 184/AE/HQ | 31/01/2025 | 59 | SOURAV JANA | 0.8 | 0.8 | 99.8 | 0
3213 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1116/BWD | 03/04/2025 | 120 | SOFIQUL ISLAM | 176.89 | 0 | 0 | 0
3214 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.04.2025 to 31.05.2025] | 454/AE/HQ | 28/03/2025 | 61 | SOURAV JANA | 0.8 | 0.4 | 49.93 | 0
3215 | PURBA BARDHAMAN | Burdwan Division | KUCHUT PIPED WATER SUPPLY SCHEME , SM/13464 | New | Repairing damaged Pipeline & concrete road by Cement concrete (mix 1:1.5:3) and drainage system, Sluice valve chamber for FHTC work for SATGACHIA ZONE-I, SATGACHIA ZONE-II, SRIDHARPUR, PARHATI, KUCHUT, NOAHATI, MONDALGRAM PWSS and its adjoining mouzas within MEMARI-II BLOCK under Burdwan Division, PHE Dte. | 2715/BWD | 11/07/2024 | 205 | A.R. TRADERS | 74.28 | 15.36 | 52.09 | 100
3216 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. , SM/11284 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Galsi I Block (42 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-A). | 3663/BWD | 29/08/2022 | 45 | SAIKAT RAY | 47.35 | 0 | 0 | 0
3217 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. , SM/11284 | School | Material Requisition To Resource Division | 5397/BWD | 12/12/2022 | 0 | Resource Division | 85 | 0 | 0 | 0
3218 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. , SM/11284 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Galsi ? II Block (40 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-B). | 3608/BWD | 18/08/2022 | 45 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 45.08 | 36.13 | 80.15 | 0
3219 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. , SM/11284 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Ausgram ? I Block (27 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | 3596/BWD | 17/08/2022 | 45 | SIRAJUL MANDAL | 29.87 | 28.74 | 100 | 100
3220 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. , SM/11284 | School | Material Requisition To Resource Division | 3299/BWD | 29/07/2022 | 0 | Resource Division | 80.44 | 0 | 0 | 0
3221 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. , SM/11284 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Bhatar Block (40 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | 3417/BWD | 05/08/2022 | 45 | DHIRENDRANATH SOM | 45.05 | 33.39 | 100 | 100
3222 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. , SM/11284 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Galsi ¿ I Block (41 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-B). | 3664/BWD | 29/08/2022 | 45 | ASHOK KUMAR GHOSH | 46.23 | 34.22 | 100 | 100
3223 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. , SM/11284 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Ausgram ? II Block (31 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-A). | 3691/BWD | 29/08/2022 | 45 | BASUNDHARA SOLUTION | 34.6 | 33.31 | 100 | 100
3224 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. , SM/11284 | School | Sinking of 90mtr. deep 100 × 40mm tubewell for providing water supply arrangement in scoreless School under Bhatar Block (2 Nos School [i) Dangsara F.P.School ii) Bhumshore S.S.K.]) within Purba Bardhaman District under Burdwan Division, PHE Dte. | 347(b)/DSD | 19/04/2024 | 6 | BIPLAB SAMANTA | 2.47 | 0 | 0 | 100
3225 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(292 nos) for 100% School Coverage in Purba Bardhaman within Burdwan North Sub Division under Burdwan Division P.H.E. DTE. , SM/11284 | School | Sinking of 90mtr. deep 100 × 50 mm tubewell for providing water supply arrangement in Scoreless School under Bhatar Block (2 Nos School) [i) Chamardighi F.P.School , ii)Gardanmari S.S.K.]) within Purba Bardhaman District under Burdwan Division, PHE Dte. | 347(a)/DSD | 19/04/2024 | 6 | PAPRI HAZRA | 2.47 | 0 | 0 | 100
3226 | PURBA BARDHAMAN | Burdwan Division | BICHKHARA PIPED WATER SUPPLY SCHEME , SM/13422 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.14 | 0 | 0 | 0
3227 | PURBA BARDHAMAN | Burdwan Division | BICHKHARA PIPED WATER SUPPLY SCHEME , SM/13422 | New | Material Requisition To Resource Division | 1265/BWD | 17/03/2023 | 0 | Resource Division | 2.71 | 0 | 0 | 0
3228 | PURBA BARDHAMAN | Burdwan Division | BICHKHARA PIPED WATER SUPPLY SCHEME , SM/13422 | New | Material Requisition To Resource Division | 5042/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
3229 | PURBA BARDHAMAN | Central Mechanical | BICHKHARA PIPED WATER SUPPLY SCHEME , SM/13422 | New | New service connection charges for Bichkhara W/S Scheme TW-2 | BP-2023-24-30 | 22/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.64 | 0 | 0 | 0
3230 | PURBA BARDHAMAN | Central Mechanical | BICHKHARA PIPED WATER SUPPLY SCHEME , SM/13422 | New | New service connection charges for Bichkhara W/S Scheme TW-1 | BP-2023-24-29 | 22/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.61 | 0 | 0 | 0
3231 | PURBA BARDHAMAN | Central Mechanical | BICHKHARA PIPED WATER SUPPLY SCHEME , SM/13422 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
3232 | PURBA BARDHAMAN | Burdwan Division | BICHKHARA PIPED WATER SUPPLY SCHEME , SM/13422 | New | BICHKHARA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch-rooms & boundary walls at different TW site under KHANDOGHOSH Block, District:- Purba-Bardhaman [NEW SCHEME] | 253/BWD | 16/01/2023 | 180 | KOUSIK MALLICK | 121.67 | 112.18 | 100 | 90
3233 | PURBA BARDHAMAN | Central Mechanical | BICHKHARA PIPED WATER SUPPLY SCHEME , SM/13422 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bichkhara Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2494/CMD | 01/06/2023 | 30 | CONCORD ENGINEERING | 28.89 | 23.91 | 100 | 98
3234 | PURBA BARDHAMAN | Central Mechanical | BICHKHARA PIPED WATER SUPPLY SCHEME , SM/13422 | New | Supply & delivery of standby Submersible pumping machinery & automatic Chlorinator for Bichkhara & others water supply scheme, under CMD, P.H.E. Dte., Dist.- Purba Bardhaman | 149/CMSD | 22/01/2024 | 15 | CHOUDHURY ENTERPRISE | 1.76 | 1.76 | 100 | 100
3235 | PURBA BARDHAMAN | Burdwan Division | BICHKHARA PIPED WATER SUPPLY SCHEME , SM/13422 | New | Balance work for providing Functional Household Tap Connection (FHTC) within the command area BICHKHARA & TELUN W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | 434/BWD | 20/01/2025 | 182 | KOUSIK MALLICK | 108.55 | 0 | 0 | 50
3236 | PURBA BARDHAMAN | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13450 | New | Material Requisition To Resource Division | 1254/BWD | 17/03/2023 | 0 | Resource Division | 4.93 | 0 | 0 | 0
3237 | PURBA BARDHAMAN | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13450 | New | Material Requisition To Resource Division | 1634/BWD | 06/04/2023 | 0 | Resource Division | 0.76 | 0 | 0 | 0
3238 | PURBA BARDHAMAN | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13450 | New | Material Requisition To Resource Division | 5039/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
3239 | PURBA BARDHAMAN | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13450 | New | Shifting of 25KVA DTR at Punshur Water Supply Scheme | BP-2023-24-17 | 02/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.88 | 0 | 0 | 0
3240 | PURBA BARDHAMAN | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13450 | New | New service connection charges of Punshur W/S Scheme TW-2 | BP-2023-24-22 | 21/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.8 | 0 | 0 | 0
3241 | PURBA BARDHAMAN | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13450 | New | New service connection charges of Punshur W/S Scheme TW-1 | BP-2023-24-21 | 21/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.29 | 0 | 0 | 0
3242 | PURBA BARDHAMAN | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13450 | New | PUNSUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under KHANDOGOSH Block, District:- Purba-Bardhaman [NEW SCHEME] | 162/BWD | 11/01/2023 | 365 | TIRUPATI ENTERPRISES | 278.54 | 157.59 | 56.58 | 75
3243 | PURBA BARDHAMAN | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13450 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
3244 | PURBA BARDHAMAN | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13450 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Punsur Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2495/CMD | 01/06/2023 | 30 | M/S. SWAPAN BANERJEE | 28.94 | 11.94 | 50.14 | 100
3245 | PURBA BARDHAMAN | Central Mechanical | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13450 | New | Supply & installation works for Punsur PWSS. | BP-2023-24-547 | 20/02/2024 | 0 | M/S. SWAPAN BANERJEE | 11.87 | 0 | 0 | 0
3246 | PURBA BARDHAMAN | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13450 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day [Period February'2024 to April'2024] | 91/DSD | 31/01/2024 | 78 | MD HASIN | 1 | 0.29 | 88.46 | 0
3247 | PURBA BARDHAMAN | Burdwan Division | PUNSHUR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13450 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period May'2024 to July'2024] | 369/DSD | 30/04/2024 | 78 | MD HASIN | 1 | 0.33 | 100 | 0
3248 | PURBA BARDHAMAN | Burdwan Division | BHUYERA PIPED WATER SUPPLY SCHEME , SM/13948 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.34 | 0 | 0 | 0
3249 | PURBA BARDHAMAN | Burdwan Division | BHUYERA PIPED WATER SUPPLY SCHEME , SM/13948 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.16 | 0 | 0 | 0
3250 | PURBA BARDHAMAN | Burdwan Division | BHUYERA PIPED WATER SUPPLY SCHEME , SM/13948 | New | Material Requisition To Resource Division | 4886/BWD | 10/11/2023 | 0 | Resource Division | 30.36 | 0 | 0 | 0
3251 | PURBA BARDHAMAN | Central Mechanical | BHUYERA PIPED WATER SUPPLY SCHEME , SM/13948 | New | New service connection for Bhuyera W/S scheme TW No-1 | BP-2023-24-312 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.52 | 0 | 0 | 0
3252 | PURBA BARDHAMAN | Central Mechanical | BHUYERA PIPED WATER SUPPLY SCHEME , SM/13948 | New | New service connection charges for Bhuyera PWSS TW-1 | BP-2023-24-285 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.3 | 0 | 0 | 0
3253 | PURBA BARDHAMAN | Durgapur W/S Division | BHUYERA PIPED WATER SUPPLY SCHEME , SM/13948 | New | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 0 | 1
3254 | PURBA BARDHAMAN | Central Mechanical | BHUYERA PIPED WATER SUPPLY SCHEME , SM/13948 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BHUYERA Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4111/CMD | 29/08/2023 | 30 | SOUNAK ENTERPRISE | 29.61 | 23.25 | 95.54 | 48
3255 | PURBA BARDHAMAN | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] | 1759/BSD | 28/07/2023 | 66 | MD HASIN | 0.85 | 0 | 0 | 0
3256 | PURBA BARDHAMAN | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Supply & delivery of different dia. MJ Coller for FHTC as well as smooth running of different W/S. Schemes under Burdwan Division, P.H.E. Dte. [i.e. (1) Magra PWSS, Memari-I Block, (2) Kuchut PWSS, Memari - II Block, (3) Khundkuri PWSS, Khandaghosh Block & (4) Samanti PWSS, Burdwan - II Block)] | 4076/BWD | 13/09/2023 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 20.63 | 5.63 | 100 | 100
3257 | PURBA BARDHAMAN | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Material Requisition To Resource Division | 1251/BWD | 17/03/2023 | 0 | Resource Division | 12.34 | 0 | 0 | 0
3258 | PURBA BARDHAMAN | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Material Requisition To Resource Division | 3986/BWD | 08/09/2023 | 0 | Resource Division | 8.96 | 0 | 0 | 0
3259 | PURBA BARDHAMAN | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Material Requisition To Resource Division | 5080/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
3260 | PURBA BARDHAMAN | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.06.2024 to 31.07.2024] | 307/AE/HQ | 31/05/2024 | 61 | MD HASIN | 0.8 | 0.76 | 94.6 | 0
3261 | PURBA BARDHAMAN | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.02.2024 to 31.03.2024] | 42/AE/HQ | 29/01/2024 | 60 | MD HASIN | 0.8 | 0.76 | 94.53 | 50
3262 | PURBA BARDHAMAN | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.08.2024 to 30.09.2024] | 548/AE/HQ | 01/08/2024 | 61 | MD HASIN | 0.8 | 0.75 | 94.02 | 0
3263 | PURBA BARDHAMAN | Central Mechanical | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
3264 | PURBA BARDHAMAN | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.04.2024 to 31.05.2024] | 233/AE/HQ | 28/03/2024 | 61 | MD HASIN | 0.8 | 0.74 | 92.73 | 0
3265 | PURBA BARDHAMAN | Central Mechanical | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | New Service connection for Magra PWSS TW-2. | BP-2023-24-474 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.7 | 0 | 0 | 0
3266 | PURBA BARDHAMAN | Central Mechanical | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | New service connection for Magra W/S Sechem. | BP-2023-24-379 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.1 | 0 | 0 | 0
3267 | PURBA BARDHAMAN | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.02.2025 to 31.03.2025] | 185/AE/HQ | 31/01/2025 | 59 | MD HASIN | 0.8 | 0.34 | 42.92 | 0
3268 | PURBA BARDHAMAN | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.12.2024 to 31.01.2025] | 1009/AE/HQ | 29/11/2024 | 61 | MD HASIN | 0.8 | 0.78 | 97.86 | 0
3269 | PURBA BARDHAMAN | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.10.2024 to 30.11.2024] | 803/AE/HQ | 30/09/2024 | 61 | MD HASIN | 0.8 | 0.67 | 83.36 | 0
3270 | PURBA BARDHAMAN | Central Mechanical | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3103/CMD | 11/12/2024 | 60 | S DUTTA | 15.06 | 0 | 0 | 0
3271 | PURBA BARDHAMAN | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Superintending Engineer, Central Circle, P.H.E. Dte. to be used by the Deputy Superintending Engineer, Central Circle, P.H.E. Dte. [Period from 01.04.2025 to 31.05.2025] | 455/AE/HQ | 28/03/2025 | 61 | MD HASIN | 0.8 | 0.37 | 46.62 | 0
3272 | PURBA BARDHAMAN | Burdwan Division | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Restoration of Conc. road, Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for MAGRA, SANUI, SATGACHIA Zone-I & NARAGOHALIA PIPED WATER SUPPLY SCHEME, Block-Memari-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | 611/BWD | 11/02/2025 | 180 | M/S ASHA CONSTRUCTION | 354.13 | 0 | 0 | 25
3273 | PURBA BARDHAMAN | Central Mechanical | MAGRA PIPED WATER SUPPLY SCHEME IN MEMARI-1 BLOCK , SM/13491 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Magra Water Supply Scheme [ Block- Memari-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3993/CMD | 29/08/2023 | 611 | ORIENTAL ENGINEERING CO. | 29.35 | 8.47 | 34.82 | 100
3274 | PURBA BARDHAMAN | Burdwan Division | LAKSHAMPUR PIPED WATER SUPPLY SCHEME , SM/13493 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 6.59 | 0 | 0 | 0
3275 | PURBA BARDHAMAN | Burdwan Division | LAKSHAMPUR PIPED WATER SUPPLY SCHEME , SM/13493 | New | Material Requisition To Resource Division | 3867/BWD | 01/09/2023 | 0 | Resource Division | 0.14 | 0 | 0 | 0
3276 | PURBA BARDHAMAN | Burdwan Division | LAKSHAMPUR PIPED WATER SUPPLY SCHEME , SM/13493 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.66 | 0 | 0 | 0
3277 | PURBA BARDHAMAN | Central Mechanical | LAKSHAMPUR PIPED WATER SUPPLY SCHEME , SM/13493 | New | Addl. quotation for new service connection charges for Laxmanpur PWSS | BP-2023-24-157 | 11/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.54 | 0 | 0 | 0
3278 | PURBA BARDHAMAN | Central Mechanical | LAKSHAMPUR PIPED WATER SUPPLY SCHEME , SM/13493 | New | New service connection charges for Lakshampur PWSS TW-1 | BP-2023-24-55 | 14/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.74 | 0 | 0 | 0
3279 | PURBA BARDHAMAN | Burdwan Division | LAKSHAMPUR PIPED WATER SUPPLY SCHEME , SM/13493 | New | LAKSHAMPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1518/BWD | 28/03/2023 | 90 | JAHAR GHOSH | 42.34 | 37.88 | 89.46 | 40
3280 | PURBA BARDHAMAN | Burdwan Division | LAKSHAMPUR PIPED WATER SUPPLY SCHEME , SM/13493 | New | Different Types of work involved in connection with Augmentation of RAHATPUR (SM/16306) & LAKSHMANPUR (SM/13493) Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2069/BWD | 07/06/2024 | 240 | SAIKAT RAY | 213.73 | 0 | 0 | 2
3281 | PURBA BARDHAMAN | Central Mechanical | LAKSHAMPUR PIPED WATER SUPPLY SCHEME , SM/13493 | New | Withdrawing of pump motor set due to low discharge and installation of new pump motor set at Lakshampur PH 1 water supply scheme under CMD P.H.E. Dte. | 363/CMSD | 28/02/2024 | 15 | C.M. ENTERPRISE | 0.67 | 0 | 0 | 0
3282 | PURBA BARDHAMAN | Central Mechanical | LAKSHAMPUR PIPED WATER SUPPLY SCHEME , SM/13493 | New | New service connection for Laxmanpur PWSS PH-1 | BP-2023-24-454 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.01 | 0 | 0 | 0
3283 | PURBA BARDHAMAN | Central Mechanical | LAKSHAMPUR PIPED WATER SUPPLY SCHEME , SM/13493 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at LAKSHAMPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2639/CMD | 14/06/2023 | 30 | C.M. ENTERPRISE | 20.81 | 9.35 | 44.93 | 60
3284 | PURBA BARDHAMAN | Central Mechanical | LAKSHAMPUR PIPED WATER SUPPLY SCHEME , SM/13493 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
3285 | PURBA BARDHAMAN | Burdwan Division | SONAIAIMA Purba Piped Water Supply Scheme , SM/13326 | New | Material Requisition To Resource Division | 1255/BWD | 17/03/2023 | 0 | Resource Division | 8.72 | 0 | 0 | 0
3286 | PURBA BARDHAMAN | Burdwan Division | SONAIAIMA Purba Piped Water Supply Scheme , SM/13326 | New | Material Requisition To Resource Division | 1629/BWD | 06/04/2023 | 0 | Resource Division | 0.41 | 0 | 0 | 0
3287 | PURBA BARDHAMAN | Burdwan Division | SONAIAIMA Purba Piped Water Supply Scheme , SM/13326 | New | Material Requisition To Resource Division | 5091/BWD | 23/11/2023 | 0 | Resource Division | 21.7 | 0 | 0 | 0
3288 | PURBA BARDHAMAN | Central Mechanical | SONAIAIMA Purba Piped Water Supply Scheme , SM/13326 | New | New service connection charges for Sonaiaima PWSS TW-2 | BP-2023-24-99 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.06 | 0 | 0 | 0
3289 | PURBA BARDHAMAN | Central Mechanical | SONAIAIMA Purba Piped Water Supply Scheme , SM/13326 | New | New service connection charges for Sonaiaima PWSS TW-1 | BP-2023-24-46 | 13/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.13 | 0 | 0 | 0
3290 | PURBA BARDHAMAN | Central Mechanical | SONAIAIMA Purba Piped Water Supply Scheme , SM/13326 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sonaiaima Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2493/CMD | 01/06/2023 | 30 | CHATTERJEE ENTERPRISE | 27.71 | 21.7 | 97.56 | 40
3291 | PURBA BARDHAMAN | Durgapur W/S Division | SONAIAIMA Purba Piped Water Supply Scheme , SM/13326 | New | Material Requisition To Resource Division | 1724/B/DWSD | 10/12/2024 | 0 | Resource Division | 7.42 | 0 | 0 | 0
3292 | PURBA BARDHAMAN | Durgapur W/S Division | SONAIAIMA Purba Piped Water Supply Scheme , SM/13326 | New | FOMAL WORK ORDER FOR Balance works related (Sinking of Tube Wells at Bilaspur Village, LDS, Rising Mains, FHTCs, Road restoration of Sonaiaima PWSS under Ausgram-II Block under Durgapur W/S Division, PHE Dte. | 128/DWSD | 22/01/2025 | 120 | RANADHIR SINHA | 131.08 | 0 | 0 | 30
3293 | PURBA BARDHAMAN | Burdwan Division | SONAIAIMA Purba Piped Water Supply Scheme , SM/13326 | New | SONAIAIMA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under AUSGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 254/BWD | 16/01/2023 | 806 | RANADHIR SINHA | 360.13 | 324.57 | 88.04 | 100
3294 | PURBA BARDHAMAN | Burdwan Division | SONAIAIMA Purba Piped Water Supply Scheme , SM/13326 | New | Ground development at Head Work site of SONAIAIMA Piped water supply Scheme, block ¿ Ausgram - I within Durgapur Sub Division under Burdwan Division P.H.E. Dte. | 723/DSD | 21/09/2023 | 30 | SINHA BROTHERS | 0.94 | 0.91 | 100 | 100
3295 | PURBA BARDHAMAN | Burdwan Division | SONAIAIMA Purba Piped Water Supply Scheme , SM/13326 | New | Repairing and restore pipe line damaged by newly laying of pipeline at different location of Somai village (West Part) SONAIAIMA and its adjoining mouza's Piped W/S Scheme (NEW) at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. | 722/DSD | 21/09/2023 | 15 | RANADHIR SINHA | 0.87 | 0 | 0 | 100
3296 | PURBA BARDHAMAN | Burdwan Division | SONAIAIMA Purba Piped Water Supply Scheme , SM/13326 | New | Repairing and restore pipe line damaged by newly laying of pipeline at different location of Somai village ( East Part) SONAIAIMA and its adjoining mouza's Piped W/S Scheme (NEW) at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. | 721/DSD | 21/09/2023 | 15 | RANADHIR SINHA | 0.86 | 0.44 | 34.57 | 100
3297 | PURBA BARDHAMAN | Burdwan Division | AKHRA PIPED WATER SUPPLY SCHEME , SM/14057 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 14.84 | 0 | 0 | 0
3298 | PURBA BARDHAMAN | Burdwan Division | AKHRA PIPED WATER SUPPLY SCHEME , SM/14057 | New | Material Requisition To Resource Division | 4882/BWD | 10/11/2023 | 0 | Resource Division | 26 | 0 | 0 | 0
3299 | PURBA BARDHAMAN | Burdwan Division | AKHRA PIPED WATER SUPPLY SCHEME , SM/14057 | New | Material Requisition To Resource Division | 4017/BWD | 08/09/2023 | 0 | Resource Division | 23.3 | 0 | 0 | 0
3300 | PURBA BARDHAMAN | Central Mechanical | AKHRA PIPED WATER SUPPLY SCHEME , SM/14057 | New | New service connection charges for Akhra PWSS TW-1 | BP-2023-24-56 | 17/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.96 | 0 | 0 | 0
3301 | PURBA BARDHAMAN | Central Mechanical | AKHRA PIPED WATER SUPPLY SCHEME , SM/14057 | New | New service connection charges for Akhra PWSS TW-2 | BP-2023-24-57 | 17/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.39 | 0 | 0 | 0
3302 | PURBA BARDHAMAN | Burdwan Division | AKHRA PIPED WATER SUPPLY SCHEME , SM/14057 | New | AKHARA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 1725/BWD | 13/04/2023 | 1205 | MANASH GHOSH | 455.23 | 405.69 | 89.12 | 78
3303 | PURBA BARDHAMAN | Central Mechanical | AKHRA PIPED WATER SUPPLY SCHEME , SM/14057 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
3304 | PURBA BARDHAMAN | Central Mechanical | AKHRA PIPED WATER SUPPLY SCHEME , SM/14057 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of Assistant Engineer, under C.M.D. P.H.E. Dte. w.e.f.- 01/11/2023 to 31/12/2023. [Under JJM Works]. | 859/CMSD | 30/10/2023 | 61 | SUBRATA BHADRA | 0.8 | 0.79 | 100 | 100
3305 | PURBA BARDHAMAN | Central Mechanical | AKHRA PIPED WATER SUPPLY SCHEME , SM/14057 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Akhra Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2760/CMD | 28/06/2023 | 275 | CHOUDHURY ENTERPRISE | 27.73 | 21.37 | 95.17 | 40
3306 | PURBA BARDHAMAN | Burdwan Division | AKHRA PIPED WATER SUPPLY SCHEME , SM/14057 | New | Providing of balance FHTC and other allied works at Benga, Nowapara under the command area of AKHARA PWSS (SM/14057) in order to declare Sajal Gram, under Katwa-II Block under Katwa Sub-Division, PHE Dte. | 979/BWD | 13/03/2025 | 172 | MANASH GHOSH | 8.52 | 0 | 0 | 100
3307 | PURBA BARDHAMAN | Burdwan Division | AKHRA PIPED WATER SUPPLY SCHEME , SM/14057 | New | Road crossing through metal/Concrete road by Jack Push Method for Akhara PWSS (SM/14057) of Katwa-II Block Development Block under Katwa Sub-Division within Burdwan Division PHE Dte. | 1296/BWD | 25/04/2025 | 30 | MONDAL & CO. | 43.64 | 0 | 0 | 100
3308 | PURBA BARDHAMAN | Burdwan Division | AKHRA PIPED WATER SUPPLY SCHEME , SM/14057 | New | Providing of balance FHTC and other allied works at Akhra, Bishnupur under the command area of AKHARA PWSS (SM/14057) in order to declare Sajal Gram, under Katwa-II Block under Katwa Sub-Division, PHE Dte. | 978/BWD | 13/03/2025 | 172 | MANASH GHOSH | 8.28 | 0 | 0 | 100
3309 | PURBA BARDHAMAN | Burdwan Division | KHEJURHATI PIPED WATER SUPPLY SCHEME , SM/14952 | New | Material Requisition To Resource Division | 1965/BWD | 26/04/2023 | 0 | Resource Division | 2.84 | 0 | 0 | 0
3310 | PURBA BARDHAMAN | Burdwan Division | KHEJURHATI PIPED WATER SUPPLY SCHEME , SM/14952 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 2.96 | 0 | 0 | 0
3311 | PURBA BARDHAMAN | Burdwan Division | KHEJURHATI PIPED WATER SUPPLY SCHEME , SM/14952 | New | Material Requisition To Resource Division | 5276/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
3312 | PURBA BARDHAMAN | Central Mechanical | KHEJURHATI PIPED WATER SUPPLY SCHEME , SM/14952 | New | New service connection charges for Khejurhati PWSS TW 2 | BP-2023-24-200 | 17/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.02 | 0 | 0 | 0
3313 | PURBA BARDHAMAN | Central Mechanical | KHEJURHATI PIPED WATER SUPPLY SCHEME , SM/14952 | New | New service connection charges for Khejurhati PWSS TW-1 | BP-2023-24-207 | 30/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.78 | 0 | 0 | 0
3314 | PURBA BARDHAMAN | Central Mechanical | KHEJURHATI PIPED WATER SUPPLY SCHEME , SM/14952 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khejurhati Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3662/CMD | 01/08/2023 | 30 | SINHA ELECTRICALS | 28.98 | 23.76 | 100 | 98
3315 | PURBA BARDHAMAN | Burdwan Division | KHEJURHATI PIPED WATER SUPPLY SCHEME , SM/14952 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHAGRAM & KHEJURHATI Piped Water Supply Scheme under Khandaghosh Block, District:- Purba Bardhaman [NEW SCHEME] | 2080/BWD | 04/05/2023 | 698 | KHAN ENTERPRISE | 688.15 | 198.49 | 81.28 | 58
3316 | PURBA BARDHAMAN | Central Mechanical | KHEJURHATI PIPED WATER SUPPLY SCHEME , SM/14952 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
3317 | PURBA BARDHAMAN | Burdwan Division | KHEJURHATI PIPED WATER SUPPLY SCHEME , SM/14952 | New | Balance work for providing Functional Household Tap Connection (FHTC) within the command area KHEJURHATI & GUIR W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | 724/BWD | 24/02/2025 | 120 | ROY CONSTRUCTION | 153.99 | 0 | 0 | 0
3318 | PURBA BARDHAMAN | Burdwan Division | JALKANDAR PIPED WATER SUPPLY SCHEME , SM/14953 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 73.04 | 0 | 0 | 0
3319 | PURBA BARDHAMAN | Burdwan Division | JALKANDAR PIPED WATER SUPPLY SCHEME , SM/14953 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.34 | 0 | 0 | 0
3320 | PURBA BARDHAMAN | Burdwan Division | JALKANDAR PIPED WATER SUPPLY SCHEME , SM/14953 | New | Material Requisition To Resource Division | 4878/BWD | 10/11/2023 | 0 | Resource Division | 30.36 | 0 | 0 | 0
3321 | PURBA BARDHAMAN | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME , SM/14953 | New | New service connection charges for Jalkandar PWSS TW-1 | BP-2023-24-290 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.59 | 0 | 0 | 0
3322 | PURBA BARDHAMAN | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME , SM/14953 | New | Supply & Installation of Submersible Pumping Machinery, and piping works for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | 40/DIC/BMSD(D) | 15/01/2024 | 15 | H.K. DAS & CO. | 0.38 | 0 | 0 | 0
3323 | PURBA BARDHAMAN | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME , SM/14953 | New | Supply & Delivery of actuator valve for Tube Well No: 02 at JALKHANDAR Water Supply Scheme [Block- AUSGRAM -2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 100/DIC/BMSD(D) | 12/02/2024 | 7 | H.K. DAS & CO. | 0.97 | 0 | 0 | 0
3324 | PURBA BARDHAMAN | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME , SM/14953 | New | Supply & delivery of the following Electrical & Mechanical accessories for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [ Block- AUSGRAM-2) under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | 23/DIC/BMSD(D) | 05/01/2024 | 7 | H.K. DAS & CO. | 0.93 | 0 | 0 | 0
3325 | PURBA BARDHAMAN | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME , SM/14953 | New | Supply & Delivery of Submersible Pumping Machinery for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [Block- AUSGRAM -2] under CMD, PHE Dte.,Dist.- Purba-Bardhaman. | 349/DIC/BMSD(D) | 22/12/2023 | 7 | H.K. DAS & CO. | 0.8 | 0 | 0 | 0
3326 | PURBA BARDHAMAN | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME , SM/14953 | New | Supply & delivery of Electrical & Mechanical accessories for Tube well No.- 2 at JALKHANDAR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.· Purba Bardhaman. | 45/DIC/BMSD(D) | 19/01/2024 | 7 | H.K. DAS & CO. | 0.63 | 0 | 0 | 0
3327 | PURBA BARDHAMAN | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME , SM/14953 | New | Quotation for new service connection at Jalikandar W/S Scheme for PH No-2 | BP-2023-24-330 | 03/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.52 | 0 | 0 | 0
3328 | PURBA BARDHAMAN | Durgapur W/S Division | JALKANDAR PIPED WATER SUPPLY SCHEME , SM/14953 | New | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 0 | 1
3329 | PURBA BARDHAMAN | Central Mechanical | JALKANDAR PIPED WATER SUPPLY SCHEME , SM/14953 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at JALKANDAR Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4180/CMD | 29/08/2023 | 30 | SOUNAK ENTERPRISE | 28.48 | 21.92 | 95.17 | 96
3330 | PURBA BARDHAMAN | Burdwan Division | BARAPALASHAN PIPED WATER SUPPLY SCHEME , SM/13423 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 23.4 | 0 | 0 | 0
3331 | PURBA BARDHAMAN | Burdwan Division | BARAPALASHAN PIPED WATER SUPPLY SCHEME , SM/13423 | New | Material Requisition To Resource Division | 4025/BWD | 08/09/2023 | 0 | Resource Division | 6.08 | 0 | 0 | 0
3332 | PURBA BARDHAMAN | Burdwan Division | BARAPALASHAN PIPED WATER SUPPLY SCHEME , SM/13423 | New | Material Requisition To Resource Division | 5099/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
3333 | PURBA BARDHAMAN | Central Mechanical | BARAPALASHAN PIPED WATER SUPPLY SCHEME , SM/13423 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
3334 | PURBA BARDHAMAN | Burdwan Division | BARAPALASHAN PIPED WATER SUPPLY SCHEME , SM/13423 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-06-2024 to 31-08-2024" | 918/BSD | 28/05/2024 | 92 | SK. ASFIA | 1.2 | 0 | 0 | 60
3335 | PURBA BARDHAMAN | Central Mechanical | BARAPALASHAN PIPED WATER SUPPLY SCHEME , SM/13423 | New | New service connection at Barapalasan PWSS TW -2 | BP-2023-24-448 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.18 | 0 | 0 | 0
3336 | PURBA BARDHAMAN | Central Mechanical | BARAPALASHAN PIPED WATER SUPPLY SCHEME , SM/13423 | New | New service connection at Barapalasan PWSS TW -1. | BP-2023-24-447 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.9 | 0 | 0 | 0
3337 | PURBA BARDHAMAN | Burdwan Division | BARAPALASHAN PIPED WATER SUPPLY SCHEME , SM/13423 | New | BARA PALASHAN Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 2300/BWD | 19/05/2023 | 867 | MLG CONSTRUCTION | 358.59 | 159.02 | 44.34 | 65
3338 | PURBA BARDHAMAN | Burdwan Division | BARAPALASHAN PIPED WATER SUPPLY SCHEME , SM/13423 | New | Continuation Work Order for Supply of one No.Diesel Driven Ambassador Car No. WB:41H-4009 on hire basis for the office of the Assistant Engineer,Burdwan Sub-Division,PHE Dte(Period from 01-03-2025 to 31.05.2025) | 457/BSD | 28/02/2025 | 90 | SK. ASFIA | 1.2 | 0 | 0 | 100
3339 | PURBA BARDHAMAN | Central Mechanical | BARAPALASHAN PIPED WATER SUPPLY SCHEME , SM/13423 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Barapalashan Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4022/CMD | 29/08/2023 | 30 | MITRA ENTERPRISE | 29.26 | 11.55 | 47.62 | 100
3340 | PURBA BARDHAMAN | Burdwan Division | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME , SM/14074 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 53 | 0 | 0 | 0
3341 | PURBA BARDHAMAN | Burdwan Division | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME , SM/14074 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.76 | 0 | 0 | 0
3342 | PURBA BARDHAMAN | Central Mechanical | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME , SM/14074 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
3343 | PURBA BARDHAMAN | Central Mechanical | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME , SM/14074 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SHYAMSUNDARPUR Water Supply Scheme [ Block- GALSI-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4112/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 27.73 | 22.68 | 100 | 48
3344 | PURBA BARDHAMAN | Central Mechanical | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME , SM/14074 | New | Quotation for new electric service connection at Shyamsundarpur PH NO.-1 | BP-2023-24-246 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.34 | 0 | 0 | 0
3345 | PURBA BARDHAMAN | Central Mechanical | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME , SM/14074 | New | New service connection for SHYAMSUNDARPUR PWSS TW 2. | BP-2023-24-522 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4 | 0 | 0 | 0
3346 | PURBA BARDHAMAN | Burdwan Division | SHYAMSUNDARPUR PIPED WATER SUPPLY SCHEME , SM/14074 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMSUNDARPUR & BELGRAM Piped Water Supply Scheme under Galsi-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 2147/BWD | 10/05/2023 | 730 | MAHMOOD ASSOCIATES PVT. LTD. | 1172.24 | 378.31 | 64.78 | 78
3347 | PURBA BARDHAMAN | Central Mechanical | Kusha Piped Water Supply Scheme , SM/13279 | New | Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of Assistant Engineer, under C.M.D. P.H.E. Dte. w.e.f.-01/07/2023 to 31/08/2023. [Under JJM Works]. | 523/A/CMSD-I | 28/06/2023 | 62 | SUBRATA BHADRA | 0.79 | 0.76 | 95.9 | 50
3348 | PURBA BARDHAMAN | Burdwan Division | Kusha Piped Water Supply Scheme , SM/13279 | New | Additional laying distribution system work for KUSHA W/S. Scheme under Burdwan - II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 3386/BWD | 03/08/2023 | 60 | RICK CONSTRUCTION | 39.84 | 39.84 | 100 | 100
3349 | PURBA BARDHAMAN | Burdwan Division | Kusha Piped Water Supply Scheme , SM/13279 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.48 | 0 | 0 | 0
3350 | PURBA BARDHAMAN | Burdwan Division | Kusha Piped Water Supply Scheme , SM/13279 | New | Material Requisition To Resource Division | 1250/BWD | 17/03/2023 | 0 | Resource Division | 6.52 | 0 | 0 | 0
3351 | PURBA BARDHAMAN | Burdwan Division | Kusha Piped Water Supply Scheme , SM/13279 | New | Material Requisition To Resource Division | 5270/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
3352 | PURBA BARDHAMAN | Central Mechanical | Kusha Piped Water Supply Scheme , SM/13279 | New | New Service connection charges for Kusha W/S Scheme TW-I | BP-2023-24-9 | 12/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.07 | 0 | 0 | 0
3353 | PURBA BARDHAMAN | Central Mechanical | Kusha Piped Water Supply Scheme , SM/13279 | New | New Service connection charges for Kusha W/S Scheme TW-II | BP-2023-24-10 | 12/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.41 | 0 | 0 | 0
3354 | PURBA BARDHAMAN | Central Mechanical | Kusha Piped Water Supply Scheme , SM/13279 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kusha Water Supply Scheme [Block- Burdwan-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2470/CMD | 30/05/2023 | 30 | SUBRATA BHADRA | 28.71 | 23.98 | 100 | 60
3355 | PURBA BARDHAMAN | Central Mechanical | Kusha Piped Water Supply Scheme , SM/13279 | New | Supply & delivery of standby Submersible pumping machinery & automatic Chlorinator for Kusha & others water supply scheme, under CMD, P.H.E. Dte., Dist.- Purba Bardhaman | 150/CMSD | 22/01/2024 | 15 | SUBRATA BHADRA | 1.76 | 1.76 | 100 | 100
3356 | PURBA BARDHAMAN | Central Mechanical | Kusha Piped Water Supply Scheme , SM/13279 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 0 | 12
3357 | PURBA BARDHAMAN | Burdwan Division | Kusha Piped Water Supply Scheme , SM/13279 | New | KUSHA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Bardhaman-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 389/BWD. | 31/01/2023 | 791 | SYED KHORSED ALAM | 250.51 | 234.57 | 93.64 | 75
3358 | PURBA BARDHAMAN | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14080 | New | Material Requisition To Resource Division | 3834/BWD | 01/09/2023 | 0 | Resource Division | 5.48 | 0 | 0 | 0
3359 | PURBA BARDHAMAN | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14080 | New | Material Requisition To Resource Division | 5052/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
3360 | PURBA BARDHAMAN | Central Mechanical | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14080 | New | New service connection charges for Malkita PWSS TW-1 | BP-2023-24-102 | 04/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.26 | 0 | 0 | 0
3361 | PURBA BARDHAMAN | Central Mechanical | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14080 | New | New service connection charges for Malkita PWSS TW-2 | BP-2023-24-103 | 04/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.25 | 0 | 0 | 0
3362 | PURBA BARDHAMAN | Central Mechanical | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14080 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
3363 | PURBA BARDHAMAN | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14080 | New | MALKITA Single Village Scheme with sinking of Tube-well & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 1933/BWD | 24/04/2023 | 90 | GHOSH CONSTRUCTION | 49.99 | 49.95 | 100 | 100
3364 | PURBA BARDHAMAN | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14080 | New | MALKITA Single Village Scheme with LDS, Rising Main and FHTC under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | 2454/BWD | 31/05/2023 | 90 | M/S PURBASHA | 71.78 | 71.76 | 100 | 72
3365 | PURBA BARDHAMAN | Burdwan Division | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14080 | New | Installation of Sluice Valve, Washout Valve to regulate water supply with Road Restoration work, Extension pipeline and providing FHTC for MALKITA Piped Water Supply Scheme, Block- Burdwan-I, under Burdwan sub Division within Burdwan Division PHE Dte. | 552/BWD | 04/02/2025 | 90 | M/S PURBASHA | 9.62 | 0 | 0 | 0
3366 | PURBA BARDHAMAN | Central Mechanical | MALKITA PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14080 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Malkita Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3067/CMD | 21/07/2023 | 30 | S.P. CONSTRUCTION | 28.96 | 21.66 | 91.58 | 100
3367 | PURBA BARDHAMAN | Burdwan Division | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | Material Requisition To Resource Division | 1644/BWD | 06/04/2023 | 0 | Resource Division | 43.68 | 0 | 0 | 0
3368 | PURBA BARDHAMAN | Burdwan Division | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | Material Requisition To Resource Division | 1268/BWD | 17/03/2023 | 0 | Resource Division | 16.43 | 0 | 0 | 0
3369 | PURBA BARDHAMAN | Burdwan Division | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | Material Requisition To Resource Division | 5105/BWD | 23/11/2023 | 0 | Resource Division | 24.22 | 0 | 0 | 0
3370 | PURBA BARDHAMAN | Central Mechanical | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | New service connection charges of Chhora PWSS TW-2 | BP-2023-24-47 | 13/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.44 | 0 | 0 | 0
3371 | PURBA BARDHAMAN | Central Mechanical | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | New service connection charges of Chhora PWSS TW-1 | BP-2023-24-48 | 13/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.21 | 0 | 0 | 0
3372 | PURBA BARDHAMAN | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | Acceptance cum Formal Work Order for Sinking of 300 X 200mm dia Tube Well- 300 mtr.& 2 nos Trial Bore of 200 X 200mm dia Tube Well- 300 mtr at Pubar village under Chhora PWSS (JJM) Block - Ausgram -II, District:- Purba-Bardhaman, under Durgapur W/S Division , PHE Dte. | 1612/DWSD | 26/11/2024 | 60 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 34.01 | 0 | 0 | 0
3373 | PURBA BARDHAMAN | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-II under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.03.2024 to 31.08.2024 (6 Months)(Sl-02) | 268/DWSD | 29/02/2024 | 6 | PRAMIT CHATTERJEE | 0.82 | 2.38 | 288.99 | 0
3374 | PURBA BARDHAMAN | Central Mechanical | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHHORA Water Supply Scheme [ Block- AUSGRAM-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2514/CMD | 02/06/2023 | 30 | MITRA ENTERPRISE | 29.43 | 24.31 | 100 | 45
3375 | PURBA BARDHAMAN | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | Acceptance cum Formal Work Order work of Balance work for renovation and modification of administrative office building at PHE Complex 2nd Floor, Nababhat, P.O- Fagupur, Dist- Purba Bardhaman inconnection with Augmentation of Chhora PWSS under Aushgram-II Block. | 364/DWSD | 15/03/2024 | 30 | SANDIPAN SENGUPTA | 9.6 | 7.88 | 100 | 100
3376 | PURBA BARDHAMAN | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | Material Requisition To Resource Division | 1724/H/DWSD | 10/12/2024 | 0 | Resource Division | 7.83 | 0 | 0 | 0
3377 | PURBA BARDHAMAN | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | Continuation order for Hiring of LUXURY Diesel Ambassador Car (Inspection Vehicle) for using of the Assistant Engineer-II under office of the Executive Engineer, Durgapur Water Supply Division, Public Health Engineering Dte at Fagupur, Nababhat, Purba Bardhaman for the period of 01.09.2024 to 28.02.2025 (6 Months)(Sl-02) | 1249/DWSD | 30/08/2024 | 182 | PRAMIT CHATTERJEE | 0.82 | 2.39 | 290.36 | 20
3378 | PURBA BARDHAMAN | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.03.2025 to 31.05.2025 (3 Months). | 341/DWSD | 27/02/2025 | 89 | PRAMIT CHATTERJEE | 0.41 | 0 | 0 | 0
3379 | PURBA BARDHAMAN | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 0 | 1
3380 | PURBA BARDHAMAN | Durgapur W/S Division | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | Continuation order for Hiring of Luxury Diesel Ambassador Car use for Inspection Vehicle of JJM under Office of the Executive Engineer, Durgapur W/S Division, Public Health Engineering Dte at Fagurpur, Nababhat, Purba Bardhaman for the period from 01.06.2025 to 31.08.2025 (3 Months). | 854/DWSD | 29/05/2025 | 90 | PRAMIT CHATTERJEE | 0.41 | 0.4 | 96.3 | 0
3381 | PURBA BARDHAMAN | Burdwan Division | CHHORA PIPED WATER SUPPLY SCHEME , SM/13328 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KHANDARI & CHHORA Piped Water Supply Scheme under Ausgram II Block, District:- Purba Bardhaman [NEW SCHEME] | 1005/BWD | 06/03/2023 | 696 | M/S NATIONAL CONSTRUCTION | 1331.54 | 624.16 | 95.11 | 100
3382 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of kalyanpur Piped Water Supply Scheme at Kalna-II Block , SM/07806 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kalyanpur (Part) village, Kalyan (Part) habitation of Kalyanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Part-A)[SL NO.-07] | 57/BWD | 05/01/2021 | 15 | SETH ENTERPRISE | 4.86 | 9.73 | 200 | 1
3383 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of kalyanpur Piped Water Supply Scheme at Kalna-II Block , SM/07806 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kalyanpur (Part) village (Kalyanpur Part habitation) of Kalyanpur piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.(Part-B)[SL NO.-08] | 58/BWD | 05/01/2021 | 15 | BISHWAJIT DAS | 4.86 | 9.72 | 200 | 1
3384 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of kalyanpur Piped Water Supply Scheme at Kalna-II Block , SM/07806 | Retrofitting | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 2nd TW Site of KALYANPUR & its adjoining mouzas Piped Water Supply Scheme, Block ? Kalna ? II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 5128/BWD | 21/11/2022 | 30 | MUNSHI ENTERPRISE | 8.72 | 8.16 | 100 | 100
3385 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of kalyanpur Piped Water Supply Scheme at Kalna-II Block , SM/07806 | Retrofitting | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 03 Nos. Piped W/S. Schemes under Kalna II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3016/BWD | 05/08/2024 | 20 | HORIZEN | 7.55 | 2.52 | 100 | 100
3386 | PURBA BARDHAMAN | Burdwan Division | KARJJANA PIPED WATER SUPPLY SCHEME , SM/15244 | New | Material Requisition To Resource Division | 1248/BWD | 17/03/2023 | 0 | Resource Division | 1.91 | 0 | 0 | 0
3387 | PURBA BARDHAMAN | Burdwan Division | KARJJANA PIPED WATER SUPPLY SCHEME , SM/15244 | New | Material Requisition To Resource Division | 5248/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0 | 0
3388 | PURBA BARDHAMAN | Central Mechanical | KARJJANA PIPED WATER SUPPLY SCHEME , SM/15244 | New | New service connection charges for Karjjana PWSS TW-1 | BP-2023-24-53 | 18/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.66 | 0 | 0 | 0
3389 | PURBA BARDHAMAN | Central Mechanical | KARJJANA PIPED WATER SUPPLY SCHEME , SM/15244 | New | New service connection charges for Karjjana PWSS TW-2 | BP-2023-24-54 | 14/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.43 | 0 | 0 | 0
3390 | PURBA BARDHAMAN | Central Mechanical | KARJJANA PIPED WATER SUPPLY SCHEME , SM/15244 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
3391 | PURBA BARDHAMAN | Burdwan Division | KARJJANA PIPED WATER SUPPLY SCHEME , SM/15244 | New | KARJJANA [PART :-A] Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME]. | 955/BWD | 03/03/2023 | 60 | DHIRENDRANATH SOM | 44.51 | 35.31 | 100 | 100
3392 | PURBA BARDHAMAN | Burdwan Division | KARJJANA PIPED WATER SUPPLY SCHEME , SM/15244 | New | KARJJANA [PART :-B] Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME]. | 956/BWD | 03/03/2023 | 60 | DHIRENDRANATH SOM | 45.79 | 30.55 | 100 | 95
3393 | PURBA BARDHAMAN | Central Mechanical | KARJJANA PIPED WATER SUPPLY SCHEME , SM/15244 | New | New service connection for KARJANA PWSS, PH-2. | BP-2023-24-535 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.06 | 0 | 0 | 0
3394 | PURBA BARDHAMAN | Central Mechanical | KARJJANA PIPED WATER SUPPLY SCHEME , SM/15244 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KARJJANA Water Supply Scheme [ Block-BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2521/CMD | 02/06/2023 | 1031 | MITRA ASSOCIATES | 27.66 | 21.37 | 95.17 | 95
3395 | PURBA BARDHAMAN | Burdwan Division | KARJJANA PIPED WATER SUPPLY SCHEME , SM/15244 | New | Additional Distribution Pipeline work at KARJJANA Piped Water Supply Scheme with Rising Main, LDS & FHTC work under Bhatar Block, District:- Purba-Bardhaman. | 789/BWD | 27/02/2024 | 30 | DHIRENDRANATH SOM | 6.2 | 6.2 | 100 | 100
3396 | PURBA BARDHAMAN | Burdwan Division | KARJJANA PIPED WATER SUPPLY SCHEME , SM/15244 | New | FIXING OF DISPLAY BOARD WITH M.S STRUCTURE CONTAINING LAND DESCRIPTION AT KARJJANA PWSS AND OTHER SCHEMES (30 Nos.) WITHIN BHATAR BLOCK UNDER BURDWAN DIVISION , PHE Dte. | 1085/DSD | 11/12/2024 | 15 | SHUBHRA KANTI GHOSH | 1.95 | 0.45 | 20.94 | 100
3397 | PURBA BARDHAMAN | Burdwan Division | BAMUNPUKUR PIPED WATER SUPPLY SCHEME , SM/14930 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 8.19 | 0 | 0 | 0
3398 | PURBA BARDHAMAN | Burdwan Division | BAMUNPUKUR PIPED WATER SUPPLY SCHEME , SM/14930 | New | Material Requisition To Resource Division | 4299/BWD | 29/09/2023 | 0 | Resource Division | 9.65 | 0 | 0 | 0
3399 | PURBA BARDHAMAN | Burdwan Division | BAMUNPUKUR PIPED WATER SUPPLY SCHEME , SM/14930 | New | Material Requisition To Resource Division | 5112/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
3400 | PURBA BARDHAMAN | Burdwan Division | BAMUNPUKUR PIPED WATER SUPPLY SCHEME , SM/14930 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | 2751/BSD | 28/11/2023 | 183 | SK.ASFIA | 2.4 | 0.4 | 99.93 | 70
3401 | PURBA BARDHAMAN | Central Mechanical | BAMUNPUKUR PIPED WATER SUPPLY SCHEME , SM/14930 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
3402 | PURBA BARDHAMAN | Burdwan Division | BAMUNPUKUR PIPED WATER SUPPLY SCHEME , SM/14930 | New | Restoration Work of damage portion of the RIDF road from Bilbari to Farakpur for PHE pipe laying work within MEMARI-II BLOCK IN THE DISTRICT OF PURBABARDHAMAN | 1052/JJM | 13/11/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 23.03 | 0 | 0 | 0
3403 | PURBA BARDHAMAN | Central Mechanical | BAMUNPUKUR PIPED WATER SUPPLY SCHEME , SM/14930 | New | New service connection for Bamunpukur PWSS TW 1. | BP-2023-24-524 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.99 | 0 | 0 | 0
3404 | PURBA BARDHAMAN | Central Mechanical | BAMUNPUKUR PIPED WATER SUPPLY SCHEME , SM/14930 | New | New service connection for Bamunpukur PWSS of PH-1 | BP-2023-24-471 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.81 | 0 | 0 | 0
3405 | PURBA BARDHAMAN | Central Mechanical | BAMUNPUKUR PIPED WATER SUPPLY SCHEME , SM/14930 | New | Quotation for new service connection at Bamunpukur PWSS TW-2. | BP-2024-25-349 | 05/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.45 | 0 | 0 | 0
3406 | PURBA BARDHAMAN | Burdwan Division | BAMUNPUKUR PIPED WATER SUPPLY SCHEME , SM/14930 | New | BAMUNPUKUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 2301/BWD | 19/05/2023 | 1109 | MLG CONSTRUCTION | 447.89 | 161.47 | 36.05 | 62
3407 | PURBA BARDHAMAN | Central Mechanical | BAMUNPUKUR PIPED WATER SUPPLY SCHEME , SM/14930 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bamunpukur Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4021/CMD | 29/08/2023 | 703 | DUTTA ENTERPRISE | 29.38 | 0 | 0 | 50
3408 | PURBA BARDHAMAN | Burdwan Division | BAMUNPUKUR PIPED WATER SUPPLY SCHEME , SM/14930 | New | Continuation Work Order for supply of inspection Vehicle No. WB42Y- 7403 for inspection of different JJM related(schemes) works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub Division under Burdwan Division, PHE Dte consider 96.00 Km. run per day (Period from 01-02-2025 to 30-04-2025) | 240/BSD | 31/01/2025 | 66 | PARVIN BEGAM | 0.85 | 0.28 | 100 | 100
3409 | PURBA BARDHAMAN | Burdwan Division | CHAKPUROHIT PIPED WATER SUPPLY SCHEME , SM/14978 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.34 | 0 | 0 | 0
3410 | PURBA BARDHAMAN | Burdwan Division | CHAKPUROHIT PIPED WATER SUPPLY SCHEME , SM/14978 | New | Material Requisition To Resource Division | 4009/BWD | 08/09/2023 | 0 | Resource Division | 1.37 | 0 | 0 | 0
3411 | PURBA BARDHAMAN | Burdwan Division | CHAKPUROHIT PIPED WATER SUPPLY SCHEME , SM/14978 | New | Material Requisition To Resource Division | 5102/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
3412 | PURBA BARDHAMAN | Central Mechanical | CHAKPUROHIT PIPED WATER SUPPLY SCHEME , SM/14978 | New | New service connection charges for Chakpurohit PWSS TW-2 | BP-2023-24-221 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.93 | 0 | 0 | 0
3413 | PURBA BARDHAMAN | Central Mechanical | CHAKPUROHIT PIPED WATER SUPPLY SCHEME , SM/14978 | New | New service connection charges for Chakpurohit PWSS TW-1 | BP-2023-24-192 | 11/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.9 | 0 | 0 | 0
3414 | PURBA BARDHAMAN | Burdwan Division | CHAKPUROHIT PIPED WATER SUPPLY SCHEME , SM/14978 | New | CHAK PUROHIT Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 150 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 2702/BWD | 08/06/2023 | 300 | M/S PROCHESTA ENTERPRISE | 263.18 | 222.45 | 84.52 | 80
3415 | PURBA BARDHAMAN | Burdwan Division | CHAKPUROHIT PIPED WATER SUPPLY SCHEME , SM/14978 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-05-2024 to 31-07-2024) | 807/BSD | 29/04/2024 | 66 | PARVIN BEGAM | 0.85 | 0.28 | 99.58 | 100
3416 | PURBA BARDHAMAN | Central Mechanical | CHAKPUROHIT PIPED WATER SUPPLY SCHEME , SM/14978 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
3417 | PURBA BARDHAMAN | Central Mechanical | CHAKPUROHIT PIPED WATER SUPPLY SCHEME , SM/14978 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chak Purohit Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3916/CMD | 21/08/2023 | 345 | P.K. ENGINEERING | 28.9 | 22.79 | 95.45 | 96
3418 | PURBA BARDHAMAN | Burdwan Division | SHRIGRAM PIPED WATER SUPPLY SCHEME , SM/14915 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.32 | 0 | 0 | 0
3419 | PURBA BARDHAMAN | Burdwan Division | SHRIGRAM PIPED WATER SUPPLY SCHEME , SM/14915 | New | Material Requisition To Resource Division | 4010/BWD | 08/09/2023 | 0 | Resource Division | 0.28 | 0 | 0 | 0
3420 | PURBA BARDHAMAN | Burdwan Division | SHRIGRAM PIPED WATER SUPPLY SCHEME , SM/14915 | New | Material Requisition To Resource Division | 5245/BWD | 30/11/2023 | 0 | Resource Division | 18.9 | 0 | 0 | 0
3421 | PURBA BARDHAMAN | Burdwan Division | SHRIGRAM PIPED WATER SUPPLY SCHEME , SM/14915 | New | SHRIGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM -I Block, District:- Purba- Bardhaman [NEW SCHEME] | 2385/BWD | 23/05/2023 | 365 | S.D. CONSTRUCTION | 351.47 | 129.4 | 36.82 | 43
3422 | PURBA BARDHAMAN | Central Mechanical | SHRIGRAM PIPED WATER SUPPLY SCHEME , SM/14915 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
3423 | PURBA BARDHAMAN | Central Mechanical | SHRIGRAM PIPED WATER SUPPLY SCHEME , SM/14915 | New | Quotation for new service connection at Shrigram PWSS PH-2. | BP-2024-25-222 | 26/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.77 | 0 | 0 | 0
3424 | PURBA BARDHAMAN | Central Mechanical | SHRIGRAM PIPED WATER SUPPLY SCHEME , SM/14915 | New | Quotation for new service connection at Shrigram PWSS PH-1. | BP-2024-25-221 | 26/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.4 | 0 | 0 | 0
3425 | PURBA BARDHAMAN | Central Mechanical | SHRIGRAM PIPED WATER SUPPLY SCHEME , SM/14915 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SHRIGRAM Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4109/CMD | 29/08/2023 | 30 | DUTTA ENTERPRISE | 26.96 | 0 | 0 | 100
3426 | PURBA BARDHAMAN | Burdwan Division | SHRIGRAM PIPED WATER SUPPLY SCHEME , SM/14915 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Chakta, Mahula, Rajoor and Srigram PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2721/BWD | 11/07/2024 | 447 | ESCON INDIA | 139.35 | 23.14 | 63.59 | 70
3427 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III , SM/15588 | Augmentation | Material Requisition To Resource Division | 3969/BWD | 08/09/2023 | 0 | Resource Division | 28.36 | 0 | 0 | 0
3428 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III , SM/15588 | Augmentation | Work Order for "Route Survey & Prepatration of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-III (Zone-III A) (SM/15588) under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-4) | 2079/KSD | 29/02/2024 | 45 | APEX ENGINEERING | 2.27 | 0 | 0 | 100
3429 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III , SM/15588 | Augmentation | Material Requisition To Resource Division | 197/BWD | 10/01/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
3430 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III , SM/15588 | Augmentation | Augmentation of PURBASTHALI Surface Water Supply Scheme (ZONE-3A) with LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-II Block, District:- Purba-Bardhaman. | 3701/BWD | 24/08/2023 | 860 | SUPRITI ENTERPRISE | 560.35 | 0 | 0 | 1
3431 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III , SM/15588 | Augmentation | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
3432 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE III , SM/15588 | Augmentation | Construction of protection wall along with reconstruction of boundary wall (Damaged portion due to land slide along the pond side) and other allied work at Surface Water Based Water Supply Scheme (Zone - 3) | 913/BWD | 10/03/2025 | 30 | MONDAL & CO. | 17.92 | 0 | 0 | 100
3433 | PURBA BARDHAMAN | Central Drilling | PANDUGRAM PIPED WATER SUPPLY SCHEME , SM/15160 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Pandugram W/S Scheme (T/W-I & II) , Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | 1347/CDD | 13/09/2023 | 30 | M/S S.K.GHOSH & CO. | 16.67 | 0 | 0 | 0
3434 | PURBA BARDHAMAN | Burdwan Division | PANDUGRAM PIPED WATER SUPPLY SCHEME , SM/15160 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 0.69 | 0 | 0 | 0
3435 | PURBA BARDHAMAN | Burdwan Division | PANDUGRAM PIPED WATER SUPPLY SCHEME , SM/15160 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.57 | 0 | 0 | 0
3436 | PURBA BARDHAMAN | Burdwan Division | PANDUGRAM PIPED WATER SUPPLY SCHEME , SM/15160 | New | Material Requisition To Resource Division | 4873/BWD | 10/11/2023 | 0 | Resource Division | 29.6 | 0 | 0 | 0
3437 | PURBA BARDHAMAN | Central Mechanical | PANDUGRAM PIPED WATER SUPPLY SCHEME , SM/15160 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
3438 | PURBA BARDHAMAN | Burdwan Division | PANDUGRAM PIPED WATER SUPPLY SCHEME , SM/15160 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Ankhona, Pandugram, Sripur PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2738/BWD | 12/07/2024 | 173 | PUSPA ENTERPRISE | 128.29 | 0 | 0 | 75
3439 | PURBA BARDHAMAN | Central Mechanical | PANDUGRAM PIPED WATER SUPPLY SCHEME , SM/15160 | New | New electric connection for Pandugram PWSS, PH-1. | BP-2023-24-378 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.98 | 0 | 0 | 0
3440 | PURBA BARDHAMAN | Central Mechanical | PANDUGRAM PIPED WATER SUPPLY SCHEME , SM/15160 | New | New service connection charges for Pandugram PWSS TW-2 | BP-2023-24-253 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.61 | 0 | 0 | 0
3441 | PURBA BARDHAMAN | Central Mechanical | PANDUGRAM PIPED WATER SUPPLY SCHEME , SM/15160 | New | Quotation for burnt meter problem at Pandugram PWSS TW-2 | BP-2024-25-408 | 11/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.07 | 0 | 0 | 0
3442 | PURBA BARDHAMAN | Burdwan Division | PANDUGRAM PIPED WATER SUPPLY SCHEME , SM/15160 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ANKHONA, PANDUGRAM & SRIPUR Piped Water Supply Scheme under KETUGRAM¿I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3388/BWD | 03/08/2023 | 882 | PUSPA ENTERPRISE | 989.13 | 172.08 | 55.31 | 50
3443 | PURBA BARDHAMAN | Central Mechanical | PANDUGRAM PIPED WATER SUPPLY SCHEME , SM/15160 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PANDUGRAM Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4128/CMD | 29/08/2023 | 30 | MENAKA ENTERPRISE. | 26.95 | 10.4 | 47.52 | 48
3444 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME , SM/15176 | Augmentation | Quotation for new service connection at Amragarah PWSS TW-2 (Aug). | BP-2024-25-338 | 04/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.59 | 0 | 0 | 0
3445 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME , SM/15176 | Augmentation | Quotation for new service connection at Amragarh PWSS TW-3 | BP-2024-25-401 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.49 | 0 | 0 | 0
3446 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME , SM/15176 | Augmentation | Making illumination arrangement and mise works at AMRARGARH and adjacent water supply scheme ausgram-II BLOCK under Central Mechanical Division P.H.E. Dte. Purba-Bardhaman. | 2955/CMD | 20/11/2024 | 60 | A.S. ENTERPRISE | 22.81 | 0 | 0 | 50
3447 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME , SM/15176 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of AMRARGARH[AUSGRAM-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4509/CMD | 06/10/2023 | 605 | S.K. ENTERPRISE | 24.39 | 6.11 | 20.14 | 80
3448 | PURBA BARDHAMAN | Durgapur W/S Division | AUGUMENTATION OF AMRARGAR PIPED WATER SUPPLY SCHEME , SM/15176 | Augmentation | Formal Work Order for Source Augmentation of Amarargarh Piped Water Supply Scheme [Tube Well, Pump House, Bounday Wall, Rising Main, FHTC etc], Block- Ausgram-II, Dist- purba Bardhaman under Durgapur W/S Division, PHE Dte | 1014/DWSD | 16/07/2024 | 444 | BIPLAB GUHA | 109.16 | 34.32 | 31.45 | 100
3449 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) , SM/15182 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of SATGACHIA(Z-II, Part-B)[MEMARI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4199/CMD | 29/08/2023 | 30 | DAS TRADING CO. | 24.41 | 0 | 0 | 0
3450 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) , SM/15182 | Augmentation | Sinking of Tube-well, construction of switch rooms & Rising main at 3RD TW site for SATGACHIA ZONE-II Piped Water Supply Scheme under MEMARI-II Block, District:- Purba-Bardhaman. | 5357/BWD | 06/12/2023 | 60 | J K CORPORATION | 20.1 | 0 | 0 | 0
3451 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) , SM/15182 | Augmentation | Construction of boundary wall and Land development with approach road including internal drain at 2ND TW site for SATGACHIA ZONE-II PWSS under Memari-II Block, District:- Purba-Bardhaman. | 5595/BWD | 20/12/2023 | 30 | GOUTAM KUMAR MITRA | 5.09 | 5.08 | 100 | 100
3452 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) , SM/15182 | Augmentation | Restoration of Pump House at Head Work site of SATGACHIA ZONE-II Piped water supply scheme at Memari-II Block under Burdwan Division, Dist.-Purba Bardhaman. | 1002/BSD | 06/06/2024 | 30 | SAANVI ENTERPRISE | 0.96 | 0.95 | 100 | 10
3453 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) , SM/15182 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Zone- I & II, Tube well No.- I (Replacement tube well) at Satgachia Water Supply Scheme [ BLOCK- Memari-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3071/CMD | 03/12/2024 | 60 | NABAUDYOG ELECTRICAL ENGINEERING CO-OPERATIVE SOCIETY LTD | 25.34 | 0 | 0 | 95
3454 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SATGACHIA ZONE-II (PART-B) , SM/15182 | Augmentation | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 848/BWD | 05/03/2025 | 120 | PROJECT INDIA | 394.29 | 0 | 0 | 0
3455 | PURBA BARDHAMAN | Central Mechanical | KASIPUR PIPED WATER SUPPLY SCHEME , SM/16019 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KASIPUR Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4163/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 28.59 | 0 | 0 | 0
3456 | PURBA BARDHAMAN | Burdwan Division | KASIPUR PIPED WATER SUPPLY SCHEME , SM/16019 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 31.64 | 0 | 0 | 0
3457 | PURBA BARDHAMAN | Burdwan Division | KASIPUR PIPED WATER SUPPLY SCHEME , SM/16019 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 6.85 | 0 | 0 | 0
3458 | PURBA BARDHAMAN | Central Mechanical | KASIPUR PIPED WATER SUPPLY SCHEME , SM/16019 | New | New service at Kasipur PWSS TW-2. | BP-2023-24-439 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.72 | 0 | 0 | 0
3459 | PURBA BARDHAMAN | Burdwan Division | KASIPUR PIPED WATER SUPPLY SCHEME , SM/16019 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KASIPUR, PATHAR GHATA & SABIDPUR Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3697/BWD | 24/08/2023 | 770 | SUPRITI ENTERPRISE | 1185.67 | 164.63 | 41.54 | 42
3460 | PURBA BARDHAMAN | Burdwan Division | KASIPUR PIPED WATER SUPPLY SCHEME , SM/16019 | New | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 618/BWD | 11/02/2025 | 180 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0 | 0
3461 | PURBA BARDHAMAN | Central Mechanical | KASIPUR PIPED WATER SUPPLY SCHEME , SM/16019 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
3462 | PURBA BARDHAMAN | Burdwan Division | KASIPUR PIPED WATER SUPPLY SCHEME , SM/16019 | New | Road restoration work for implementation of KASIPUR PWSS (SM/16019) within Kalna Sub-Division under Burdwan Division, PHE Dte. | 559/BWD | 06/02/2025 | 90 | SUPRITI ENTERPRISE | 9.43 | 0 | 0 | 100
3463 | PURBA BARDHAMAN | Burdwan Division | SABIDPUR PIPED WATER SUPPLY SCHEME , SM/16021 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 36.67 | 0 | 0 | 0
3464 | PURBA BARDHAMAN | Burdwan Division | SABIDPUR PIPED WATER SUPPLY SCHEME , SM/16021 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 22.3 | 0 | 0 | 0
3465 | PURBA BARDHAMAN | Burdwan Division | SABIDPUR PIPED WATER SUPPLY SCHEME , SM/16021 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR SABIDPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 2150/KSD | 07/03/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.66 | 100 | 2
3466 | PURBA BARDHAMAN | Central Mechanical | SABIDPUR PIPED WATER SUPPLY SCHEME , SM/16021 | New | Quotation for new electric service connection at Sabidpur PH NO.-1 | BP-2023-24-255 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.37 | 0 | 0 | 0
3467 | PURBA BARDHAMAN | Central Mechanical | SABIDPUR PIPED WATER SUPPLY SCHEME , SM/16021 | New | New service connection for SABIDPUR PWSS TW-2. | BP-2023-24-502 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.96 | 0 | 0 | 0
3468 | PURBA BARDHAMAN | Burdwan Division | SABIDPUR PIPED WATER SUPPLY SCHEME , SM/16021 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KASIPUR, PATHAR GHATA & SABIDPUR Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3697/BWD | 24/08/2023 | 770 | SUPRITI ENTERPRISE | 1185.67 | 172.3 | 41.01 | 42
3469 | PURBA BARDHAMAN | Burdwan Division | SABIDPUR PIPED WATER SUPPLY SCHEME , SM/16021 | New | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 618/BWD | 11/02/2025 | 180 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0 | 0
3470 | PURBA BARDHAMAN | Central Mechanical | SABIDPUR PIPED WATER SUPPLY SCHEME , SM/16021 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
3471 | PURBA BARDHAMAN | Central Mechanical | SABIDPUR PIPED WATER SUPPLY SCHEME , SM/16021 | New | CONTINUATION ORDER-Hiring of inspection vehicle (Diesel/CNG/LPG Driven) [bearing no. WB41H5741] for supervision of the site for the office of the Assistant Engineer,CMD,PHE,Dte.[w.e.f-01.06.2025 to 31.07.2025][JJM WORKS] | 646/CMSD | 26/05/2025 | 61 | PRODYUT GHOSH | 0.8 | 0.39 | 49.11 | 0
3472 | PURBA BARDHAMAN | Burdwan Division | AKALPAUSH PIPE WATER SUPPLY SCHEME , SM/16485 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 20.78 | 0 | 0 | 0
3473 | PURBA BARDHAMAN | Burdwan Division | AKALPAUSH PIPE WATER SUPPLY SCHEME , SM/16485 | New | Material Requisition To Resource Division | 4914/BWD | 10/11/2023 | 0 | Resource Division | 31.31 | 0 | 0 | 0
3474 | PURBA BARDHAMAN | Burdwan Division | AKALPAUSH PIPE WATER SUPPLY SCHEME , SM/16485 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 34.71 | 0 | 0 | 0
3475 | PURBA BARDHAMAN | Burdwan Division | AKALPAUSH PIPE WATER SUPPLY SCHEME , SM/16485 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AKALPAUSH & BIRUHA Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3698/BWD | 24/08/2023 | 365 | SUPRITI ENTERPRISE | 1010.87 | 274.49 | 52.25 | 37
3476 | PURBA BARDHAMAN | Burdwan Division | AKALPAUSH PIPE WATER SUPPLY SCHEME , SM/16485 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR AKALPOUSH PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 2095/KSD | 04/03/2024 | 10 | BISWAS ENTERPRISE | 0.66 | 0.66 | 100 | 2
3477 | PURBA BARDHAMAN | Burdwan Division | AKALPAUSH PIPE WATER SUPPLY SCHEME , SM/16485 | New | Material Requisition To Resource Division | 330/BWD | 24/01/2024 | 0 | Resource Division | 13.92 | 0 | 0 | 0
3478 | PURBA BARDHAMAN | Burdwan Division | AKALPAUSH PIPE WATER SUPPLY SCHEME , SM/16485 | New | RESTORATION WORK OF KALNA BAIDYAPUR ROAD TO AKALPOUSH HC ROAD FROM 0.00 KM TO 1.50 KM (IN STRETCHES )DAMAGED DUE TO LAYING OF UNDERGROUND WATER PIPELINEBY PHE WITH BOX CUTTING AND JHAMA WITH MOORUM CONSOLIDATION UNDR KALNA HIGHWAY SUB DIVISION OF BURDWAN SOUTH HIGHWAY DIVISION P.W.(ROADS) DTE.. DURING YEAR 2023-2024. | 825/JJM | 13/09/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 1.85 | 0 | 0 | 0
3479 | PURBA BARDHAMAN | Central Mechanical | AKALPAUSH PIPE WATER SUPPLY SCHEME , SM/16485 | New | New Service connection at Akalpoush PWSS PH-2 | BP-2023-24-452 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.25 | 0 | 0 | 0
3480 | PURBA BARDHAMAN | Central Mechanical | AKALPAUSH PIPE WATER SUPPLY SCHEME , SM/16485 | New | New Service connection at Akalpoush PWSS PH-1 | BP-2023-24-451 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.42 | 0 | 0 | 0
3481 | PURBA BARDHAMAN | Central Mechanical | AKALPAUSH PIPE WATER SUPPLY SCHEME , SM/16485 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
3482 | PURBA BARDHAMAN | Central Mechanical | AKALPAUSH PIPE WATER SUPPLY SCHEME , SM/16485 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at AKALPAUSH Water Supply Scheme [ Block-KALNA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | 4190/CMD | 29/08/2023 | 30 | AMUSAR IMPEX PVT. LTD. | 28.57 | 0 | 0 | 100
3483 | PURBA BARDHAMAN | Central Mechanical | AKALPAUSH PIPE WATER SUPPLY SCHEME , SM/16485 | New | Installation of starter in the temporary kiosk & Allied works for urgent FHTC at Akalpaush w/s scheme, T.W. No.-2 under CMD, PHE Dte., Dist.- Purba-Bardhaman. [JJM WORKS] | 826/CMSD | 03/06/2024 | 7 | S.K. ENTERPRISE | 0.55 | 0 | 0 | 100
3484 | PURBA BARDHAMAN | Central Mechanical | AKALPAUSH PIPE WATER SUPPLY SCHEME , SM/16485 | New | Installation of starter in the temporary kiosk & Allied works for urgent FHTC at Akalpaush w/s scheme, T.W. No.-1 under CMD, PHE Dte., Dist.- Purba-Bardhaman. [JJM WORKS] | 825/CMSD | 03/06/2024 | 7 | S.K. ENTERPRISE | 0.55 | 0 | 0 | 100
3485 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JAUGRAM , SM/15602 | Augmentation | Laying of HDPE pipes with installation & construction of new valve chambers to control the flow of water within command area of JOUGRAM Piped W/S. Scheme at Jougram habitation, Jamalpur Block under Burdwan Division, PHE Dte. | 1292/BWD | 20/03/2023 | 30 | DIPAK SARKAR | 18.24 | 18.23 | 99.94 | 1
3486 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JAUGRAM , SM/15602 | Augmentation | Construction of 400 cum capacity 20 Mtr. staging height RCC Over Head Reservoir including pile foundation, pipe connection and cost of pipes, specials for JOUGRAM & It's Adjoining Mouzas W/S. scheme under Burdwan Sub-Division, Burdwan Division, P.H.E. Dte. Ref. Drawing No.PC-I/OHR/11/2012 (Sheet No.1&2)(R-I) Dated 20.06.2012. | 3114/BWD | 02/06/2021 | 180 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 90.26 | 90.26 | 100 | 100
3487 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JAUGRAM , SM/15602 | Augmentation | Laying of Rising Main with interconnection of OHR and distribution line for JAUGRAM Piped Water Supply Scheme and its adjoining mouzas within Jamalpur Block under Burdwan Division, PHE Dte. | 1297/BWD | 21/03/2023 | 30 | GOUTAM DEY | 5.55 | 5.54 | 100 | 100
3488 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR JAUGRAM , SM/15602 | Augmentation | Augmentation of JAUGRAM Piped Water Supply Scheme LDS, FHTC, land development, drain at different TW site under JAMALPUR Block, District:- Purba-Bardhaman. | 3059/BWD | 17/07/2023 | 682 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 406.76 | 121.76 | 30.2 | 50
3489 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME , SM/16298 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of NADANGHAT[PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4440/CMD | 04/10/2023 | 30 | S.K. ENTERPRISE | 24.39 | 0 | 0 | 0
3490 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME , SM/16298 | Augmentation | Augmentation of NADANGHAT PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Purbasthali - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | 2043/BWD | 03/05/2023 | 60 | HAFIJUR RAHAMAN MIDYA | 26.28 | 20.8 | 100 | 100
3491 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME , SM/16298 | Augmentation | Laying of Rising Main and distribution system with FHTC work, sinking of tube wells with other allied works in connection with Augmentation of NADANGHAT Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2066/BWD | 07/06/2024 | 120 | TIRUPATI ENTERPRISES | 272.43 | 0 | 0 | 0
3492 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME , SM/16298 | Augmentation | Illumination arrangement at Nadanghat water supply scheme under Purbasthali-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2782/CMD | 01/10/2024 | 60 | SUBRATA BHADRA | 16.18 | 0 | 0 | 0
3493 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME , SM/16298 | Augmentation | Work Order for "Restoration and laying of HDPE Pipeline at 2nd Pump House adjacent to Dogachhia village of DOGACHHIA PWSS & Nadanghat PWSS (SM/16298) under Kalna Sub-Division under Burdwan Division, PHE Dte.". | 774/KSD | 12/07/2024 | 15 | HAMID SK | 0.96 | 0.92 | 100 | 100
3494 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME , SM/16298 | Augmentation | Work Order for "Restoration and laying of HDPE Pipeline at 2nd Pump House adjacent to Parulia village of PARULIA PWSS & Nadanghat PWSS (SM/16298) under Kalna Sub-Division under Burdwan Division, PHE Dte." | 773/KSD | 12/07/2024 | 15 | HAMID SK | 0.96 | 0.96 | 100 | 100
3495 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME , SM/16298 | Augmentation | Quotation for load enhancement at Nadanghat PWSS PH 2. | BP-2024-25-116 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.89 | 0 | 0 | 0
3496 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF NADANGHAT PIPED WATER SUPPLY SCHEME , SM/16298 | Augmentation | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
3497 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NANDRA PIPE WATER SUPPLY SCHEME , SM/15725 | Augmentation | Preparation and Submission of DPR for Augmentation of Nandra PWSS under Burdwan-II Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1476/BSD | 12/07/2023 | 15 | CARTO | 0.78 | 0.77 | 100 | 100
3498 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NANDRA PIPE WATER SUPPLY SCHEME , SM/15725 | Augmentation | Augmentation of NADRA Piped Water Supply Scheme Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & Rising Main under BARDHAMAN-II Block, District:- Purba-Bardhaman. _2ND CALL | 002/BWD | 02/01/2024 | 180 | R.G. INFRASTRUCTURE | 72.79 | 0 | 0 | 0
3499 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NANDRA PIPE WATER SUPPLY SCHEME , SM/15725 | Augmentation | Continuation Work for the supply of one no. Diesel driven Motor Cab/Maxi Cab (Air Conditioner) on hire basis for the office of the Assistant Engineer, to be used by the Assistant Engineer, RWS Burdwan Sub-Divn., PHE. Dte. (Period from 01/03/2024 to 30/04/2024) | 62/RWS | 27/02/2024 | 60 | MD HASIN | 0.8 | 0.55 | 68.93 | 0
3500 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED NANDRA PIPE WATER SUPPLY SCHEME , SM/15725 | Augmentation | Different type of works related internal pathways and approach road, land development, repair of boundary wall & pump houses and road restoration under NANDRA PWSS under Burdwan II Block under Burdwan Divn., PHE. Dte. | 1404/BWD | 16/05/2025 | 45 | POMPA CONSTRUCTION CO. | 5.89 | 0 | 0 | 0
3501 | PURBA BARDHAMAN | Burdwan Division | LOHARUNDI PIPED WATER SUPPLY SCHEME , SM/16033 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.47 | 0 | 0 | 0
3502 | PURBA BARDHAMAN | Burdwan Division | LOHARUNDI PIPED WATER SUPPLY SCHEME , SM/16033 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 1.95 | 0 | 0 | 0
3503 | PURBA BARDHAMAN | Burdwan Division | LOHARUNDI PIPED WATER SUPPLY SCHEME , SM/16033 | New | Material Requisition To Resource Division | 4936/BWD | 10/11/2023 | 0 | Resource Division | 0.46 | 0 | 0 | 0
3504 | PURBA BARDHAMAN | Burdwan Division | LOHARUNDI PIPED WATER SUPPLY SCHEME , SM/16033 | New | Balance work for extension of pipeline to provide FHTC with land development, plinth protection for pump house under LOHARUNDI PWSS, Block-Ketugram-II under Katwa Sub Division within Burdwan Division PHE Dte. | 3313/BWD | 06/09/2024 | 60 | LAKSHMIKANTA DAS | 9.88 | 0 | 0 | 0
3505 | PURBA BARDHAMAN | Central Mechanical | LOHARUNDI PIPED WATER SUPPLY SCHEME , SM/16033 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
3506 | PURBA BARDHAMAN | Central Mechanical | LOHARUNDI PIPED WATER SUPPLY SCHEME , SM/16033 | New | Quotation for new service connection at Loharudni PWSS PH-2. | BP-2024-25-169 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0 | 0
3507 | PURBA BARDHAMAN | Central Mechanical | LOHARUNDI PIPED WATER SUPPLY SCHEME , SM/16033 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at LOHARUNDI [KETUGRAM-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4154/CMD | 29/08/2023 | 640 | AMUSAR IMPEX PVT. LTD. | 21.26 | 0 | 0 | 46
3508 | PURBA BARDHAMAN | Burdwan Division | LOHARUNDI PIPED WATER SUPPLY SCHEME , SM/16033 | New | LOHARUNDI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM -II Block, District:- Purba-Bardhaman [NEW SCHEME] | 5328/BWD | 04/12/2023 | 484 | OM ENTERPRISE | 96.34 | 93.83 | 97.55 | 90
3509 | PURBA BARDHAMAN | Central Mechanical | LOHARUNDI PIPED WATER SUPPLY SCHEME , SM/16033 | New | Supply and delivery of 6 HP pump motor set at T.W. No -1 of Loharundi (Block- Ketugram-II) water supply scheme under CMD, PHE Dte . | 839/DIC/BMSD(D) | 13/12/2024 | 7 | S.K. ENTERPRISE | 0.58 | 0 | 0 | 100
3510 | PURBA BARDHAMAN | Burdwan Division | GHUNI PIPE WATER SUPPLY SCHEME , SM/16034 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.84 | 0 | 0 | 0
3511 | PURBA BARDHAMAN | Burdwan Division | GHUNI PIPE WATER SUPPLY SCHEME , SM/16034 | New | Material Requisition To Resource Division | 4027/BWD | 08/09/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
3512 | PURBA BARDHAMAN | Burdwan Division | GHUNI PIPE WATER SUPPLY SCHEME , SM/16034 | New | Material Requisition To Resource Division | 4929/BWD | 10/11/2023 | 0 | Resource Division | 39.66 | 0 | 0 | 0
3513 | PURBA BARDHAMAN | Central Mechanical | GHUNI PIPE WATER SUPPLY SCHEME , SM/16034 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at GHUNI [PURBASTHALI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4152/CMD | 29/08/2023 | 30 | S.K. ELECTRICALS | 20.78 | 18.77 | 90.31 | 90
3514 | PURBA BARDHAMAN | Central Mechanical | GHUNI PIPE WATER SUPPLY SCHEME , SM/16034 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
3515 | PURBA BARDHAMAN | Burdwan Division | GHUNI PIPE WATER SUPPLY SCHEME , SM/16034 | New | work Order "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR GHUNI PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE.". | 1014/KSD | 07/08/2024 | 15 | DEL DELTA CONSTRUCTION | 0.66 | 0.66 | 100 | 100
3516 | PURBA BARDHAMAN | Central Mechanical | GHUNI PIPE WATER SUPPLY SCHEME , SM/16034 | New | NEW SERVICE CONNECTION FOR GHUNI PIPED WATER SUPPLY SCHEME. | BP-2023-24-596 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.04 | 0 | 0 | 0
3517 | PURBA BARDHAMAN | Central Mechanical | GHUNI PIPE WATER SUPPLY SCHEME , SM/16034 | New | NEW SERVICE CONNECTION FOR | BP-2023-24-595 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.93 | 0 | 0 | 0
3518 | PURBA BARDHAMAN | Burdwan Division | GHUNI PIPE WATER SUPPLY SCHEME , SM/16034 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GHUNI & JOYKRISHNAPUR Piped Water Supply Scheme under Purbasthali II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3510/BWD | 10/08/2023 | 808 | BKB INFRA PROJECTS PRIVATE LIMITED | 551.42 | 187.09 | 79.55 | 20
3519 | PURBA BARDHAMAN | Central Mechanical | GHUNI PIPE WATER SUPPLY SCHEME , SM/16034 | New | CONTINUATION ORDER -Hiring of inspection vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of the Assistant engineer ,under CMD,PHE,Dte. [W.E.F-01/12/2024 to 30/01/2025] [Under JJM Works] | 1377/CMSD | 28/11/2024 | 61 | PRODYUT GHOSH | 0.8 | 0.79 | 99.58 | 0
3520 | PURBA BARDHAMAN | Burdwan Division | GHUNI PIPE WATER SUPPLY SCHEME , SM/16034 | New | Work order for " DESIGNING,MAKING AND ERECTION OF SIGN BOARD FOR SAJAL GRAM IN ¿¿4 No... VILLAGE, ¿PURBASTHALI-II BLOCK UNDER KALNA SUB DIVISION WITHIN BURDWAN DIVISION PHE DTE.(12nos board)". | 1985/KSD | 09/12/2024 | 10 | OMKAR ENTERPRISE | 1.68 | 0 | 0 | 100
3521 | PURBA BARDHAMAN | Burdwan Division | Balgana Piped Water Supply Scheme , SM/18326 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 3.74 | 0 | 0 | 0
3522 | PURBA BARDHAMAN | Burdwan Division | Balgana Piped Water Supply Scheme , SM/18326 | New | Material Requisition To Resource Division | 3830/BWD | 01/09/2023 | 0 | Resource Division | 19.8 | 0 | 0 | 0
3523 | PURBA BARDHAMAN | Burdwan Division | Balgana Piped Water Supply Scheme , SM/18326 | New | Material Requisition To Resource Division | 5111/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
3524 | PURBA BARDHAMAN | Central Mechanical | Balgana Piped Water Supply Scheme , SM/18326 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Replacement T.W of Bolgona Water Supply Scheme(H.W site) [ BLOCK- Bhatar] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3069/CMD | 03/12/2024 | 60 | CHOUDHURY ENTERPRISE | 18.41 | 0 | 0 | 0
3525 | PURBA BARDHAMAN | Central Mechanical | Balgana Piped Water Supply Scheme , SM/18326 | New | New service connection charges for Balgana PWSS TW-2 | BP-2023-24-403 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.86 | 0 | 0 | 0
3526 | PURBA BARDHAMAN | Central Mechanical | Balgana Piped Water Supply Scheme , SM/18326 | New | Quotation for new service connection at Augmentation of Balgona PWSS PH-4 | BP-2024-25-208 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.22 | 0 | 0 | 0
3527 | PURBA BARDHAMAN | Central Mechanical | Balgana Piped Water Supply Scheme , SM/18326 | New | New service connection charges for Balgona PWSS TW-1 | BP-2023-24-339 | 06/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.44 | 0 | 0 | 0
3528 | PURBA BARDHAMAN | Burdwan Division | Balgana Piped Water Supply Scheme , SM/18326 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALGANA & GANGPUR Piped Water Supply Scheme under Burdwan ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3699/BWD | 24/08/2023 | 769 | SUPRITI ENTERPRISE | 1345.79 | 98.22 | 14.74 | 20
3529 | PURBA BARDHAMAN | Central Mechanical | Balgana Piped Water Supply Scheme , SM/18326 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Balgana Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4007/CMD | 29/08/2023 | 581 | GLACIER ENGINEERING CO | 28.96 | 2.55 | 8.8 | 95
3530 | PURBA BARDHAMAN | Central Mechanical | Balgana Piped Water Supply Scheme , SM/18326 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 0 | 12
3531 | PURBA BARDHAMAN | Burdwan Division | BANTIR PIPED WATER SUPPLY SCHEME , SM/18300 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 16.06 | 0 | 0 | 0
3532 | PURBA BARDHAMAN | Burdwan Division | BANTIR PIPED WATER SUPPLY SCHEME , SM/18300 | New | Material Requisition To Resource Division | 3862/BWD | 01/09/2023 | 0 | Resource Division | 3.19 | 0 | 0 | 0
3533 | PURBA BARDHAMAN | Burdwan Division | BANTIR PIPED WATER SUPPLY SCHEME , SM/18300 | New | Material Requisition To Resource Division | 5098/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
3534 | PURBA BARDHAMAN | Central Mechanical | BANTIR PIPED WATER SUPPLY SCHEME , SM/18300 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bantir Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4029/CMD | 29/08/2023 | 520 | M.S. ENTERPRISE | 28.98 | 22.81 | 95.46 | 96
3535 | PURBA BARDHAMAN | Central Mechanical | BANTIR PIPED WATER SUPPLY SCHEME , SM/18300 | New | New service connection charges for Bantir PWSS TW-2 | BP-2023-24-402 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.33 | 0 | 0 | 0
3536 | PURBA BARDHAMAN | Central Mechanical | BANTIR PIPED WATER SUPPLY SCHEME , SM/18300 | New | New electric connection for Bantir PWSS, PH-1. | BP-2023-24-359 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.18 | 0 | 0 | 0
3537 | PURBA BARDHAMAN | Burdwan Division | BANTIR PIPED WATER SUPPLY SCHEME , SM/18300 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-08-2024 to 31-10-2024) | 1500/BSD | 30/07/2024 | 66 | PARVIN BEGAM | 0.85 | 0.28 | 100 | 100
3538 | PURBA BARDHAMAN | Central Mechanical | BANTIR PIPED WATER SUPPLY SCHEME , SM/18300 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
3539 | PURBA BARDHAMAN | Burdwan Division | BANTIR PIPED WATER SUPPLY SCHEME , SM/18300 | New | Supply of various D.I. Mechanical joints & specials for KATNABIL & BANTIR Piped W/S. Scheme within Burdwan Sub-Division under Burdwan Division, PHE. Dte. [Part-B]. | 2825/BWD | 19/07/2024 | 216 | KEJRIWAL CASTINGS LIMITED | 4.82 | 0 | 0 | 100
3540 | PURBA BARDHAMAN | Burdwan Division | BANTIR PIPED WATER SUPPLY SCHEME , SM/18300 | New | Supply of various D.I. Mechanical joints & specials for KATNABIL & BANTIR Piped W/S. Scheme within Burdwan Sub-Division under Burdwan Division, PHE. Dte. [Part-A]. | 2837/BWD | 19/07/2024 | 215 | ELECTROSTEEL CASTING LIMITED | 4.95 | 0 | 0 | 100
3541 | PURBA BARDHAMAN | Burdwan Division | BANTIR PIPED WATER SUPPLY SCHEME , SM/18300 | New | Supply of various D.I. Mechanical joints & specials for KATNABIL & BANTIR Piped W/S. Scheme within Burdwan Sub-Division under Burdwan Division, PHE. Dte. [Part-C]. | 2829/BWD | 19/07/2024 | 225 | JINDAL SAW LTD. | 4.63 | 0 | 0 | 100
3542 | PURBA BARDHAMAN | Central Mechanical | BANTIR PIPED WATER SUPPLY SCHEME , SM/18300 | New | Supply & delivery of starter, cable & other electro-mechanical equipment for the installation of pumping machinery in kiosk to facilitate urgent FHTC work at Bantir w/s scheme, T/W no.-I [Raina-I block] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [JJM WORKS]. | 580/CMSD | 05/04/2024 | 7 | M.S. ENTERPRISE | 0.38 | 0 | 0 | 100
3543 | PURBA BARDHAMAN | Central Mechanical | BARASAT PIPED WATER SUPPLY SCHEME , SM/13906 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Barasat Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3995/CMD | 29/08/2023 | 30 | JAGANNATH ENTERPRISE | 28.95 | 0 | 0 | 0
3544 | PURBA BARDHAMAN | Burdwan Division | BARASAT PIPED WATER SUPPLY SCHEME , SM/13906 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 7.63 | 0 | 0 | 0
3545 | PURBA BARDHAMAN | Burdwan Division | BARASAT PIPED WATER SUPPLY SCHEME , SM/13906 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.22 | 0 | 0 | 0
3546 | PURBA BARDHAMAN | Burdwan Division | BARASAT PIPED WATER SUPPLY SCHEME , SM/13906 | New | Material Requisition To Resource Division | 5040/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
3547 | PURBA BARDHAMAN | Central Mechanical | BARASAT PIPED WATER SUPPLY SCHEME , SM/13906 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
3548 | PURBA BARDHAMAN | Central Mechanical | BARASAT PIPED WATER SUPPLY SCHEME , SM/13906 | New | New service connection charges for Barasat PWSS TW-2 | BP-2023-24-394 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.63 | 0 | 0 | 0
3549 | PURBA BARDHAMAN | Central Mechanical | BARASAT PIPED WATER SUPPLY SCHEME , SM/13906 | New | New service connection charges for Barasat PWSS TW-1 | BP-2023-24-393 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.59 | 0 | 0 | 0
3550 | PURBA BARDHAMAN | Burdwan Division | BARASAT PIPED WATER SUPPLY SCHEME , SM/13906 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARASAT, JAGADABAD & KHAIDYA Piped Water Supply Scheme under BURDWAN-I Block, District:- Purba Bardhaman [NEW SCHEME] | 3460/BWD | 08/08/2023 | 783 | CONCORD EMC ENCLAVE LLP | 1526.24 | 199.42 | 43.62 | 5
3551 | PURBA BARDHAMAN | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME , SM/18608 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.44 | 0 | 0 | 0
3552 | PURBA BARDHAMAN | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME , SM/18608 | New | Material Requisition To Resource Division | 3857/BWD | 01/09/2023 | 0 | Resource Division | 4.47 | 0 | 0 | 0
3553 | PURBA BARDHAMAN | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME , SM/18608 | New | Material Requisition To Resource Division | 4942/BWD | 10/11/2023 | 0 | Resource Division | 41.11 | 0 | 0 | 0
3554 | PURBA BARDHAMAN | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME , SM/18608 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
3555 | PURBA BARDHAMAN | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME , SM/18608 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-05-2024 to 31-07-2024) | 807/BSD | 29/04/2024 | 66 | PARVIN BEGAM | 0.85 | 0.28 | 99.58 | 100
3556 | PURBA BARDHAMAN | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME , SM/18608 | New | Material Requisition To Resource Division | 4117/BWD | 25/11/2024 | 0 | Resource Division | 18.97 | 0 | 0 | 0
3557 | PURBA BARDHAMAN | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME , SM/18608 | New | New electric connection for Bishnupur PWSS, PH-3. | BP-2023-24-362 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.87 | 0 | 0 | 0
3558 | PURBA BARDHAMAN | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME , SM/18608 | New | New service connection charges for Bishnupur PWSS TW-2 | BP-2023-24-404 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.36 | 0 | 0 | 0
3559 | PURBA BARDHAMAN | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME , SM/18608 | New | New electric connection for Bishnupur PWSS, PH-1. | BP-2023-24-361 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 15.08 | 0 | 0 | 0
3560 | PURBA BARDHAMAN | Burdwan Division | BISHNUPUR PIPED WATER SUPPLY SCHEME , SM/18608 | New | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1116/BWD | 03/04/2025 | 120 | SOFIQUL ISLAM | 176.89 | 0 | 0 | 0
3561 | PURBA BARDHAMAN | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME , SM/18608 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at BISHNUPUR Water Supply Scheme [ Block- MEMARI-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4079/CMD | 29/08/2023 | 30 | C.M. ENTERPRISE | 44.08 | 0 | 0 | 95
3562 | PURBA BARDHAMAN | Central Mechanical | BISHNUPUR PIPED WATER SUPPLY SCHEME , SM/18608 | New | Supply & fitting fixing of pressure gauge & additional submersible cable at Bishnupur, Ukhrid& others water supply scheme under CMD, P.H.E. Dte., Dist.- PurbaBardhaman | 1252/CMSD | 30/09/2024 | 15 | C.M. ENTERPRISE | 0.7 | 0 | 0 | 100
3563 | PURBA BARDHAMAN | Burdwan Division | KARAJGRAM PIPED WATER SUPPLY SCHEME , SM/18483 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.39 | 0 | 0 | 0
3564 | PURBA BARDHAMAN | Burdwan Division | KARAJGRAM PIPED WATER SUPPLY SCHEME , SM/18483 | New | Material Requisition To Resource Division | 4029/BWD | 08/09/2023 | 0 | Resource Division | 72.54 | 0 | 0 | 0
3565 | PURBA BARDHAMAN | Central Mechanical | KARAJGRAM PIPED WATER SUPPLY SCHEME , SM/18483 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
3566 | PURBA BARDHAMAN | Central Mechanical | KARAJGRAM PIPED WATER SUPPLY SCHEME , SM/18483 | New | New service connection for Karajgram PWSS PH-1. | BP-2023-24-417 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 11.35 | 0 | 0 | 0
3567 | PURBA BARDHAMAN | Central Mechanical | KARAJGRAM PIPED WATER SUPPLY SCHEME , SM/18483 | New | Quotation for new service connection for Kharajgram PWSS TW-3 | BP-2024-25-164 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.61 | 0 | 0 | 0
3568 | PURBA BARDHAMAN | Central Mechanical | KARAJGRAM PIPED WATER SUPPLY SCHEME , SM/18483 | New | New service connection charges for Karajgram PWSS TW-2 | BP-2024-25-405 | 25/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.19 | 0 | 0 | 0
3569 | PURBA BARDHAMAN | Burdwan Division | KARAJGRAM PIPED WATER SUPPLY SCHEME , SM/18483 | New | KARAJGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS,Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3326/BWD | 02/08/2023 | 1247 | MANASH GHOSH | 533.47 | 169.36 | 31.75 | 60
3570 | PURBA BARDHAMAN | Central Mechanical | KARAJGRAM PIPED WATER SUPPLY SCHEME , SM/18483 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KARAJGRAM Water Supply Scheme [ Block-KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4135/CMD | 29/08/2023 | 610 | SOUNAK ENTERPRISE | 45.53 | 0 | 0 | 66
3571 | PURBA BARDHAMAN | Burdwan Division | KARAJGRAM PIPED WATER SUPPLY SCHEME , SM/18483 | New | Crossing of road following Jack Push method under the command area of Karajgram PWSS (SM/18483) of Katwa-1 Block under Katwa Sub-Division PHE Dte. | 1289/BWD | 24/04/2025 | 30 | MANASH GHOSH | 26.21 | 0 | 0 | 100
3572 | PURBA BARDHAMAN | Burdwan Division | KHAJURDIHI PIPE WATER SUPPLY SCHEME , SM/18484 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.74 | 0 | 0 | 0
3573 | PURBA BARDHAMAN | Burdwan Division | KHAJURDIHI PIPE WATER SUPPLY SCHEME , SM/18484 | New | Material Requisition To Resource Division | 3828/BWD | 01/09/2023 | 0 | Resource Division | 96.08 | 0 | 0 | 0
3574 | PURBA BARDHAMAN | Central Mechanical | KHAJURDIHI PIPE WATER SUPPLY SCHEME , SM/18484 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
3575 | PURBA BARDHAMAN | Central Mechanical | KHAJURDIHI PIPE WATER SUPPLY SCHEME , SM/18484 | New | New Service Connection for KHAJURDIHI PWSS PH-1. | BP-2023-24-418 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.8 | 0 | 0 | 0
3576 | PURBA BARDHAMAN | Central Mechanical | KHAJURDIHI PIPE WATER SUPPLY SCHEME , SM/18484 | New | New service connection for Khajurdhi, PWSS PH-2. | BP-2023-24-419 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.81 | 0 | 0 | 0
3577 | PURBA BARDHAMAN | Central Mechanical | KHAJURDIHI PIPE WATER SUPPLY SCHEME , SM/18484 | New | Addl. quotation for Khajurdihi PWSS TW-2 | BP-2024-25-326 | 03/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.99 | 0 | 0 | 0
3578 | PURBA BARDHAMAN | Burdwan Division | KHAJURDIHI PIPE WATER SUPPLY SCHEME , SM/18484 | New | KHAJURDIHI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | 3527/BWD | 10/08/2023 | 965 | MONDAL ENTERPRISE | 570.77 | 237.19 | 41.56 | 75
3579 | PURBA BARDHAMAN | Burdwan Division | KHAJURDIHI PIPE WATER SUPPLY SCHEME , SM/18484 | New | Different work for Khajurdihi PWSS Khajurdihi and Bera mouza with boundary wall, land development, plinth protection for pump house & OHR under KHAJURDIHI PWSS, at Katwa -I Block under Katwa Sub Division under Burdwan Division PHE Dte. | 610/BWD | 11/02/2025 | 120 | MONDAL ENTERPRISE | 196.33 | 0 | 0 | 0
3580 | PURBA BARDHAMAN | Burdwan Division | KHAJURDIHI PIPE WATER SUPPLY SCHEME , SM/18484 | New | Necessary restoration work of Khajurdihi PWSS under Katwa-I Block under Katwa Sub-Division Burdwan Division PHE Dte. (Sl no -06) | 1609-A/KTS | 14/11/2024 | 45 | D.M. ENTERPRISE | 0.97 | 0 | 0 | 100
3581 | PURBA BARDHAMAN | Burdwan Division | KHAJURDIHI PIPE WATER SUPPLY SCHEME , SM/18484 | New | Emergent road restoration work due to laying of 225 mm dia. & 90 mm dia. HDPE Pipe line from Khajurdihi Bazar to Khajurdihi football play ground in connection with Khajurdihi PWSS (SM/18484) under Katwa-I Block under Katwa Sub-Division within Burdwan Division PHE Dte. | 219/BWD | 10/01/2025 | 21 | D.M. ENTERPRISE | 9 | 0 | 0 | 100
3582 | PURBA BARDHAMAN | Burdwan Division | KHAJURDIHI PIPE WATER SUPPLY SCHEME , SM/18484 | New | Connection pipeline KHAJURDIHI Piped W/S. Scheme under Katwa-I Block under Katwa Sub-Division within Burdwan Division PHE Dte. | 2856/BWD | 22/07/2024 | 120 | D.M. ENTERPRISE | 83.94 | 22.06 | 20.94 | 97
3583 | PURBA BARDHAMAN | Burdwan Division | LOAPUR PIPED WATER SUPPLY SCHEME , SM/18323 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 3.72 | 0 | 0 | 0
3584 | PURBA BARDHAMAN | Burdwan Division | LOAPUR PIPED WATER SUPPLY SCHEME , SM/18323 | New | Material Requisition To Resource Division | 3845/BWD | 01/09/2023 | 0 | Resource Division | 164.37 | 0 | 0 | 0
3585 | PURBA BARDHAMAN | Burdwan Division | LOAPUR PIPED WATER SUPPLY SCHEME , SM/18323 | New | Material Requisition To Resource Division | 4918/BWD | 10/11/2023 | 0 | Resource Division | 60.13 | 0 | 0 | 0
3586 | PURBA BARDHAMAN | Burdwan Division | LOAPUR PIPED WATER SUPPLY SCHEME , SM/18323 | New | LOAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 600 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Galsi-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3290/BWD | 31/07/2023 | 365 | M/S ASHA CONSTRUCTION | 824.72 | 255.05 | 30.93 | 15
3587 | PURBA BARDHAMAN | Durgapur W/S Division | LOAPUR PIPED WATER SUPPLY SCHEME , SM/18323 | New | Acceptance cum Formal Work Order for Balance work of dismantling concrete road including mending work, construction of approach road by fill up stone dust , bolders etc. and allied works under LOAPUR Water Supply Scheme, Galsi-I Block, District:- Purba-Bardhaman. | 1595/DWSD | 25/11/2024 | 120 | M/S ASHA CONSTRUCTION | 95.37 | 0 | 0 | 0
3588 | PURBA BARDHAMAN | Central Mechanical | LOAPUR PIPED WATER SUPPLY SCHEME , SM/18323 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
3589 | PURBA BARDHAMAN | Durgapur W/S Division | LOAPUR PIPED WATER SUPPLY SCHEME , SM/18323 | New | Material Requisition To Resource Division | 1724/S/DWSD | 10/12/2024 | 0 | Resource Division | 17.89 | 0 | 0 | 0
3590 | PURBA BARDHAMAN | Central Mechanical | LOAPUR PIPED WATER SUPPLY SCHEME , SM/18323 | New | NEW SERVICE CONNECTION FOR LOHAPUR PWSS PH-1. | BP-2023-24-651 | 20/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.92 | 0 | 0 | 0
3591 | PURBA BARDHAMAN | Burdwan Division | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.86 | 0 | 0 | 0
3592 | PURBA BARDHAMAN | Burdwan Division | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | Material Requisition To Resource Division | 3870/BWD | 01/09/2023 | 0 | Resource Division | 6.49 | 0 | 0 | 0
3593 | PURBA BARDHAMAN | Burdwan Division | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | Material Requisition To Resource Division | 5107/BWD | 23/11/2023 | 0 | Resource Division | 20.32 | 0 | 0 | 0
3594 | PURBA BARDHAMAN | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | New service connection charges for Mejhiari PWSS TW-1 | BP-2023-24-211 | 01/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.05 | 0 | 0 | 0
3595 | PURBA BARDHAMAN | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | New service connection charges for Mejhiari PWSS TW-2 | BP-2023-24-208 | 30/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.87 | 0 | 0 | 0
3596 | PURBA BARDHAMAN | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | Supply & Delivery of Submersible Pumping Machinery, suspension clamp and tube well cover etc. for Tube well No.-2 at MEJHIARI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte.,Dist.- Purba-Bardhaman. | 352/DIC/BMSD(D) | 22/12/2023 | 7 | SUBRATA BHADRA | 0.89 | 0 | 0 | 0
3597 | PURBA BARDHAMAN | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
3598 | PURBA BARDHAMAN | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3106/CMD | 11/12/2024 | 60 | S.K. ELECTRICALS | 13.6 | 0 | 0 | 0
3599 | PURBA BARDHAMAN | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | Supply & Delivery of Submersible cable and column pipes for Tube Well No No:-2 at MEJHIARI water supply scheme[ Block - KATWA -2] under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | 42/DIC/BMSD(D) | 15/01/2024 | 7 | SUBRATA BHADRA | 0.82 | 0.82 | 100 | 100
3600 | PURBA BARDHAMAN | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | Supply & delivery of valves, starter and Installation of Submersible Pumping Machinery for Tube well No. - 2 at MEJHIARI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte., Dist.· Purba Bardhaman. | 46/DIC/BMSD(D) | 19/01/2024 | 15 | SUBRATA BHADRA | 0.68 | 0.59 | 100 | 100
3601 | PURBA BARDHAMAN | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | Supply & Delivery of 3 Phase actuator operated wafer type butterfly valve for Tube well No.- 2 at MEJHIARI Water Supply Scheme [Block- KATWA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 24/DIC/BMSD(D) | 05/01/2024 | 7 | SUBRATA BHADRA | 0.98 | 0.98 | 100 | 99
3602 | PURBA BARDHAMAN | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | Supply & Delivery of Submersible Pumping Machinery, suspension clamp and tube well cover etc. for Tube well No.-2 at MEJHIARI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte.,Dist.- Purba-Bardhaman. | 351/DIC/BMSD(D) | 22/12/2023 | 7 | SUBRATA BHADRA | 0.89 | 0.89 | 100 | 100
3603 | PURBA BARDHAMAN | Burdwan Division | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | Construction of Toilet (1.8 m x 1.8 m) with sanitary arrangement under MAJHIARI PWSS(SM/18456) 2nd Tube Well Site under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-05) | 346/KTS | 05/03/2025 | 30 | GHOSH CONSTRUCTION | 2.45 | 0 | 0 | 100
3604 | PURBA BARDHAMAN | Central Mechanical | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MEJHIARI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3854/CMD | 14/08/2023 | 30 | S.K. ELECTRICALS | 28.96 | 19.54 | 94.46 | 90
3605 | PURBA BARDHAMAN | Burdwan Division | MEJHIARI PIPED WATER SUPPLY SCHEME , SM/18456 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MEJHIARY & KARUI Piped Water Supply Scheme under Katwa ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3291/BWD | 31/07/2023 | 701 | M/S S. CHOUDHURY | 1294.79 | 559.78 | 98.01 | 100
3606 | PURBA BARDHAMAN | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME , SM/18834 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 19.77 | 0 | 0 | 0
3607 | PURBA BARDHAMAN | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME , SM/18834 | New | Material Requisition To Resource Division | 4295/BWD | 29/09/2023 | 0 | Resource Division | 3.92 | 0 | 0 | 0
3608 | PURBA BARDHAMAN | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME , SM/18834 | New | Material Requisition To Resource Division | 5057/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
3609 | PURBA BARDHAMAN | Central Mechanical | NUDIPUR PIPED WATER SUPPLY SCHEME , SM/18834 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
3610 | PURBA BARDHAMAN | Central Mechanical | NUDIPUR PIPED WATER SUPPLY SCHEME , SM/18834 | New | New service connection at Nudipur PWSS PH-2 | BP-2023-24-468 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.43 | 0 | 0 | 0
3611 | PURBA BARDHAMAN | Central Mechanical | NUDIPUR PIPED WATER SUPPLY SCHEME , SM/18834 | New | New service connection at Nudipur PWSS PH-1 | BP-2023-24-467 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 13.67 | 0 | 0 | 0
3612 | PURBA BARDHAMAN | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME , SM/18834 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-08-2024 to 31-10-2024) | 1500/BSD | 30/07/2024 | 66 | PARVIN BEGAM | 0.85 | 0.28 | 100 | 100
3613 | PURBA BARDHAMAN | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME , SM/18834 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-12-2024 to 28-02-2025 | 2636/BSD | 29/11/2024 | 90 | SK. ASFIA | 1.2 | 0 | 0 | 60
3614 | PURBA BARDHAMAN | Burdwan Division | NUDIPUR PIPED WATER SUPPLY SCHEME , SM/18834 | New | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for NUDIPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | 477/BWD | 24/01/2025 | 250 | SHIVAM UN-EMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 64.73 | 0 | 0 | 25
3615 | PURBA BARDHAMAN | Central Mechanical | NUDIPUR PIPED WATER SUPPLY SCHEME , SM/18834 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Nudipur Water Supply Scheme [ Block- Memari-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4512/CMD | 06/10/2023 | 30 | JAL PRAVAHIKA PVT LTD | 28.96 | 22.89 | 95.47 | 100
3616 | PURBA BARDHAMAN | Burdwan Division | Bara Bainan Piped Water Supply Scheme , SM/18406 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 10.15 | 0 | 0 | 0
3617 | PURBA BARDHAMAN | Burdwan Division | Bara Bainan Piped Water Supply Scheme , SM/18406 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.15 | 0 | 0 | 0
3618 | PURBA BARDHAMAN | Burdwan Division | Bara Bainan Piped Water Supply Scheme , SM/18406 | New | Material Requisition To Resource Division | 3838/BWD | 01/09/2023 | 0 | Resource Division | 8.01 | 0 | 0 | 0
3619 | PURBA BARDHAMAN | Burdwan Division | Bara Bainan Piped Water Supply Scheme , SM/18406 | New | Continuation Work Order supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2023 to 31-01-2024) | 2561/BSD | 30/10/2023 | 66 | MD HASIN | 0.85 | 0 | 0 | 0
3620 | PURBA BARDHAMAN | Burdwan Division | Bara Bainan Piped Water Supply Scheme , SM/18406 | New | Supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-02-2024 to 30-04-2024) | 188/BSD | 31/01/2024 | 66 | PARVIN BEGAM | 0.85 | 0.28 | 99.55 | 97
3621 | PURBA BARDHAMAN | Central Mechanical | Bara Bainan Piped Water Supply Scheme , SM/18406 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
3622 | PURBA BARDHAMAN | Central Mechanical | Bara Bainan Piped Water Supply Scheme , SM/18406 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Barabainan Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4036/CMD | 29/08/2023 | 30 | S.K. ENTERPRISE | 28.98 | 23.16 | 95.52 | 96
3623 | PURBA BARDHAMAN | Burdwan Division | Bara Bainan Piped Water Supply Scheme , SM/18406 | New | Material Requisition To Resource Division | 320/BWD | 24/01/2024 | 0 | Resource Division | 21.17 | 0 | 0 | 0
3624 | PURBA BARDHAMAN | Central Mechanical | Bara Bainan Piped Water Supply Scheme , SM/18406 | New | Quotation for new electric service connection at Bara Bainan PH NO.-1 | BP-2023-24-262 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.49 | 0 | 0 | 0
3625 | PURBA BARDHAMAN | Central Mechanical | Bara Bainan Piped Water Supply Scheme , SM/18406 | New | New Service connection at BARA BAINAN PWSS TW-1. | BP-2023-24-485 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.68 | 0 | 0 | 0
3626 | PURBA BARDHAMAN | Central Mechanical | Bara Bainan Piped Water Supply Scheme , SM/18406 | New | New service connection charges for Bara Bainan PWSS TW-2 | BP-2023-24-387 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.11 | 0 | 0 | 0
3627 | PURBA BARDHAMAN | Burdwan Division | Bara Bainan Piped Water Supply Scheme , SM/18406 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARABAINAN & CHAUDANGA Piped Water Supply Scheme under Raina ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3257/BWD | 27/07/2023 | 989 | SK ALIM | 1144.16 | 406.43 | 74.9 | 90
3628 | PURBA BARDHAMAN | Central Mechanical | Bara Bainan Piped Water Supply Scheme , SM/18406 | New | Installation of starter in the temporary Kisok and allied works for urgent FHTC at BOROBOINAN PUMP HOUSE NO. 2 (RAINA-02 BLOCK) W/s scheme under CMD PHE Dte. | 770/CMSD | 21/05/2024 | 10 | S.K. ENTERPRISE | 1 | 0 | 0 | 100
3629 | PURBA BARDHAMAN | Central Mechanical | Bara Bainan Piped Water Supply Scheme , SM/18406 | New | Installation of starter in the temporary Kisok and allied works for urgent FHTC at BOROBOINAN PUMP HOUSE NO 1 (RAINA 02 BLOCK) w/s scheme under CMD,PHE ,Dte. | 769/CMSD | 21/05/2024 | 10 | S.K. ENTERPRISE | 1 | 0 | 0 | 100
3630 | PURBA BARDHAMAN | Burdwan Division | Sanko Piped Water Supply Scheme , SM/18407 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.07 | 0 | 0 | 0
3631 | PURBA BARDHAMAN | Burdwan Division | Sanko Piped Water Supply Scheme , SM/18407 | New | Material Requisition To Resource Division | 3832/BWD | 01/09/2023 | 0 | Resource Division | 191.84 | 0 | 0 | 0
3632 | PURBA BARDHAMAN | Central Mechanical | Sanko Piped Water Supply Scheme , SM/18407 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
3633 | PURBA BARDHAMAN | Durgapur W/S Division | Sanko Piped Water Supply Scheme , SM/18407 | New | Material Requisition To Resource Division | 1724/M/DWSD | 10/12/2024 | 0 | Resource Division | 16.63 | 0 | 0 | 0
3634 | PURBA BARDHAMAN | Central Mechanical | Sanko Piped Water Supply Scheme , SM/18407 | New | New service connection charges for Sanko PWSS TW-1 | BP-2023-24-373 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.63 | 0 | 0 | 0
3635 | PURBA BARDHAMAN | Central Mechanical | Sanko Piped Water Supply Scheme , SM/18407 | New | New service connection for Sanko PWSS . | BP-2023-24-508 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.1 | 0 | 0 | 0
3636 | PURBA BARDHAMAN | Central Mechanical | Sanko Piped Water Supply Scheme , SM/18407 | New | Quotation for new service connection at Sanko PWSS TW 3 | BP-2024-25-417 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.83 | 0 | 0 | 0
3637 | PURBA BARDHAMAN | Central Mechanical | Sanko Piped Water Supply Scheme , SM/18407 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SANKO Water Supply Scheme [ Block- GALSI-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4075/CMD | 29/08/2023 | 615 | BENGAL CONSTRUCTION. | 41.68 | 0 | 0 | 96
3638 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Arrah village and arrah habitation of AMARUN piped water supply scheme within Durgapur (bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-542/BWD/2020-21) | 3346/BWD | 18/09/2020 | 30 | M.R. CONSTRUCTION CO. | 4.86 | 9.72 | 200 | 1
3639 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amarun village and Amarun habitation of Amarun piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I][Tr No.-508/BWD/20-21] | 4793/BWD | 03/12/2020 | 30 | BHARAT CONSTRUCTION | 4.87 | 9.6 | 200 | 1
3640 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Arra village and Arrah habitation of Amarun piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | 4989/BWD | 10/12/2020 | 30 | M.R. CONSTRUCTION CO. | 4.86 | 9.72 | 200 | 1
3641 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amarun village and Amarun habitation of Amarun piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-805/BWD/2020-21) | 3345/BWD | 18/09/2020 | 30 | BHARAT CONSTRUCTION | 4.87 | 9.73 | 200 | 1
3642 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AMARUN (Z-II) Piped Water Supply Scheme at Hanrgram (4 Nos. Habs.), Erachya (6 Nos. Habs.) Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. | 7157/BWD | 24/12/2021 | 60 | S.S. CONSTRUCTION | 76.46 | 38.46 | 50.3 | 1
3643 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AMARUN (Z-I & II) Piped Water Supply Scheme at Arra, Amarun, Nawada, Sunur (Part), Eora, Palsona & Bijyapur Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. | 7086/BWD | 22/12/2021 | 60 | NATIONAL CONSTRUCTION | 85.05 | 80.1 | 100 | 1
3644 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Relaying for shifting of distribution line at Eora village for construction of Box culvert by PWD Department within Amarun and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [Gr.-B] | 525/DSD | 22/08/2022 | 15 | BHARAT CONSTRUCTION | 0.73 | 0 | 0 | 0
3645 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Construction of Temporary Approach road to HW site for Augmentation of Amarun (Zone-II ) Piped water supply Scheme , P.H.E Dte. Block:-Bhatar, Dist: Purba Bardhaman. [Gr.-F] | 347/DSD | 30/06/2022 | 21 | M/S S. CHOUDHURY | 1.04 | 1.04 | 100 | 100
3646 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Restoration of damaged pipeline of distribution main for construction of drain, concrete road etc at various point at Sunur, and Amarun village for providing FHTC within Amarun W/S Scheme (Zone-I &II) in Bhatar Block under Burdwan Division, P.H.E. Dte. [SL-17] | 716/DSD | 30/12/2022 | 30 | SAMANTA CONSTRUCTION | 1.93 | 1.91 | 100 | 100
3647 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Extension of UPVC pipe line of LDS at Palsona Mouza for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Phase-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-15] | 714/DSD | 30/12/2022 | 30 | SANDIPAN SENGUPTA | 4.81 | 4.81 | 100 | 100
3648 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Extension of UPVC pipe line of LDS at Bijyapur Mouza for providing FHTC of Amarun and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-16] | 715/DSD | 30/12/2022 | 30 | SAMANTA CONSTRUCTION | 4.83 | 4.83 | 100 | 100
3649 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Extension of UPVC pipe line of LDS at Hanrgram Khaspara, Chhatipara and Daspara for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte.[SL-29] | 708/DSD | 31/12/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.61 | 0 | 0 | 100
3650 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Extension of UPVC pipe line of LDS at Nandanarayanpur and Paschimpara for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-27] | 725/DSD | 30/12/2022 | 30 | BABA ADHIRA CONSTRUCTION | 4.83 | 4.83 | 100 | 100
3651 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Sinking of 250 X 150 mm dia Tubewell and Modification to distribution network by making a loop and extension with uPVC pipe to augment the water supply to FHTC at Sunur and Arra village of AMARUN and its adjoining mouzas W/S Scheme (Zone-I) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. | 1016/BWD | 07/03/2024 | 60 | BAMDEB CONSTRUCTION & CO | 34.03 | 34.01 | 100 | 80
3652 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Extension of UPVC pipe line of LDS at Kubajpur Adibasipara and Erachya for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-26] | 724/DSD | 30/12/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.58 | 4.58 | 100 | 100
3653 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Extension of UPVC pipe line of LDS at Ramnagar Mouza for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte. [SL-28] | 726/DSD | 30/12/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.16 | 0 | 0 | 100
3654 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Amarun Piped Water Supply Scheme, Block Bhatar, District Purba Bardhaman , SM/08105 | Retrofitting | Extension of UPVC pipe line of LDS at Hanrgram Uttarpara, Majhipukur par and Dulepara for providing FHTC of Amarun and its adjoining mouzas W/S Scheme (Zone-II) under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte.[SL-30] | 727/DSD | 30/12/2022 | 30 | RAM MOHAN MUKHERJEE | 4.78 | 0 | 0 | 100
3655 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block , SM/07857 | Retrofitting | Construction of Boundary wall at 2nd TW site for Chakshanjadi W/S Scheme with in Jamalpur block under Burdwan Div. PHED.(Lenth-78.0mtr & Col.-28nos.) GROUP : F | 819/BSD | 20/05/2022 | 45 | SOUMYAVASH DAS | 4.06 | 0 | 0 | 1
3656 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block , SM/07857 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
3657 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block , SM/07857 | Retrofitting | Extension of pipeline including providing FHTC for CHAKSHANJADI Piped Water Supply Scheme at Chalbalpur Habitation for Sajal Gram (As per Field Verification Report duly signed by Pradhan for Har Ghar Jal Certification) within Jamalpur Block under Burdwan Divn.PHE Dte.Gr.G. | 1361/BSD | 03/08/2022 | 5 | M/S ANAND CONSTRUCTION | 0.95 | 0 | 0 | 1
3658 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block , SM/07857 | Retrofitting | Extension of pipeline providing FHTC for CHAKSHANJADI Piped Water Supply Scheme at Chalbalpur Habitation for Sajal Gram(As per Field Verification Report duly signed by Pradhan for Har Ghar Jal Certification)within Jamalpur Block under Burdwan Divn.PHE Dte.Gr.H. | 1364/BSD | 04/08/2022 | 5 | M/S ANAND CONSTRUCTION | 0.96 | 0 | 0 | 1
3659 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block , SM/07857 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chaksanjadi Piped Water Supply Scheme at Jamdaha, Haibatpur, Chalbalpur & Kanakpur Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement no. 791/BWD of 2020-2021) | 1795/BWD | 26/02/2021 | 45 | M/S GUPTA ENTERPRISE | 40.21 | 39.33 | 100 | 1
3660 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block , SM/07857 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). | 40/BWD | 05/01/2022 | 30 | PREMANANDA ROY BISWAS | 22.68 | 0 | 0 | 1
3661 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block , SM/07857 | Retrofitting | Laying of interconnection of both the Pump No.1,2 & 3 and distribution main of 250 mm dia along with Byw-Pass arrangement from Over Head Reservoir for Chak Shanjadi piped water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte. | 4970/BWD | 10/12/2020 | 30 | TIRUPATI ENTERPRISES | 8.98 | 0 | 0 | 1
3662 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block , SM/07857 | Retrofitting | Continuation order for supply & delivery of different dia CIDF pipes, sluice valve & fittings for construction of RCC OHR (400 cum capacity) for Chakshanjadi w/s scheme under Burdwan Division, PHE Dte. | 387/BWD | 20/01/2022 | 20 | B.B.C. ENTERPRISE | 15.17 | 0 | 0 | 1
3663 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block , SM/07857 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. | 1454/BWD | 11/03/2022 | 30 | PREMANANDA ROY BISWAS | 18.83 | 0 | 0 | 1
3664 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block , SM/07857 | Retrofitting | Construction of boundary wall at Head works site of CHAKSHANJADI Piped Water Supply Scheme in Jamalpur Block under Burdwan Division, PHE Dte. (Length - 123 Mtr., 46 Nos Column). | 2743/BWD | 08/06/2022 | 30 | MOYAZZEM CONSTRUCTION | 8.12 | 0 | 0 | 1
3665 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block , SM/07857 | Retrofitting | Construction of Boundary wall at 3rd TW site for Chakshanjadi W/S Scheme with in Jamalpur block under Burdwan Div. PHED.(Lenth-48.0mtr & Col.-19nos.) GROUP : E | 818/BSD | 20/05/2022 | 45 | M/S PURBASHA | 4.06 | 0 | 0 | 1
3666 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block , SM/07857 | Retrofitting | Material Requisition To Resource Division | 1107/BWD | 26/02/2022 | 0 | Resource Division | 44.82 | 0 | 0 | 0
3667 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of CHAK SANJADI Piped Water Supply Scheme at Jamalpur Block , SM/07857 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Chaksanjadi Piped Water Supply Scheme at Chaksanjadi & Shambhupur Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 680/BWD OF 2020-2021] | 1399/BWD | 15/02/2021 | 45 | B.B.C. ENTERPRISE | 43.5 | 84.6 | 200 | 0
3668 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme , SM/07552 | Retrofitting | Extension of pipe line for FHTC work from the existing Distribution System within scheme jurisdiction at Panuhat village under Panuhat PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Phase-2] (Sl No-2) | 729/KTS | 16/11/2021 | 7 | HAMID SK | 1.93 | 1.93 | 100 | 1
3669 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme , SM/07552 | Retrofitting | Extension of pipe line for FHTC work from the existing Distribution System within scheme jurisdiction at Panuhat village under Panuhat PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. [Phase-1] (Sl No-1) | 728/KTS | 16/11/2021 | 7 | HAMID SK | 1.96 | 1.96 | 100 | 1
3670 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme , SM/07552 | Retrofitting | Supplying, laying and commissioning of Rising main at pump no. - 1 of Panuhat Piped Water Supply Scheme under Katwa Sub-Division under Burdwan Division, PHE Dte. [Sl No-06] | 443/KTS | 27/06/2022 | 30 | HAMID SK | 2.27 | 2.27 | 100 | 1
3671 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme , SM/07552 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of PANUHAT and its adjoining mouzas Piped Water Supply Scheme, Block Katwa I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 387/BWD | 31/01/2023 | 30 | SUBODH KUMAR MONDAL | 11.7 | 8.35 | 100 | 100
3672 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme , SM/07552 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of January'23. | 1118/JJM | 27/02/2023 | 0 | M/S MUNMUN DEY | 0.26 | 0 | 0 | 0
3673 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme , SM/07552 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of November & December'22. | 1048/JJM | 07/02/2023 | 0 | M/S MUNMUN DEY | 0.59 | 0 | 0 | 0
3674 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme , SM/07552 | Retrofitting | Balance work of OHR at Head Work site, construction of HUME Pipe culvert , Road restoration work and boundary wall at 2nd TW site with Gate, land development at Head work site and 2nd TW site under KAITHAN, SUDPUR & PANUHAT Piped Water Supply Scheme under KATWA -I Block, under Katwa Sub-Division within Burdwan Division, PHE Dte. | 3141/BWD | 20/08/2024 | 120 | VISHAL CONSTRUCTION CO. | 126.29 | 0 | 0 | 50
3675 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme , SM/07552 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PANUHAT Piped Water Supply Scheme at different villages, Katwa-I Block under Burdwan Division, PHE Dte. (Part-B).[Agreement No. 728/BWD OF 2020-2021.] | 1689/BWD | 24/02/2021 | 45 | HAMID SK | 35.28 | 35.04 | 100 | 0
3676 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme , SM/07552 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PANUHAT Piped Water Supply Scheme at different villages, Katwa-I Block under Burdwan Division, PHE Dte. (Part-A).[Agreement No. 727/BWD OF 2020-2021.] | 1688/BWD | 24/02/2021 | 45 | HAMID SK | 35.66 | 37.99 | 200 | 0
3677 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Panuhat Piped Water Supply Scheme , SM/07552 | Retrofitting | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme EKAIHAT, PANUHAT PWSS (Sl No-2) | 394/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 2.48 | 1.24 | 100 | 100
3678 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block , SM/07859 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Mongalkot Piped Water Supply Scheme at Mongalkot (3 Nos Habitation) Village (Mouza), Mongalkot Block under Burdwan Division, PHE Dte. | 3598/BWD | 13/07/2021 | 60 | S.S. CONSTRUCTION | 115.84 | 115.03 | 100 | 1
3679 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block , SM/07859 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G/6018) for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. for the month of May & June'2022. | 546/VEH/22-23 | 13/09/2022 | 0 | M/S MUNMUN DEY | 0.56 | 0 | 0 | 0
3680 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block , SM/07859 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
3681 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block , SM/07859 | Retrofitting | Extension and replacement of pipe line from the existing Distribution System within scheme jurisdiction at Mongalkote village under Mongalkote PWSS under Mongalkote Block within Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-02] | 438/KTS | 27/06/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.75 | 4.7 | 100 | 1
3682 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block , SM/07859 | Retrofitting | Extension and replacement of pipe line from the existing Distribution System within scheme jurisdiction at Mongalkote village under Mongalkote PWSS under Mongalkote Block within Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-03] | 439/KTS | 27/06/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 1.38 | 1.38 | 100 | 1
3683 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block , SM/07859 | Retrofitting | Material Requisition To Resource Division | 1101/BWD | 26/02/2022 | 0 | Resource Division | 9.23 | 0 | 0 | 0
3684 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block , SM/07859 | Retrofitting | Vehicle bill (Car No.-WB-04G-7127) for the month of September'2023. | 1041/JJM | 11/12/2023 | 0 | PARTHA PRATIM ACHARYA | 0.39 | 0 | 0 | 0
3685 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of MANGOLKOTE and NATUNHAT Piped Water Supply Scheme at Mangolkote Block , SM/07859 | Retrofitting | Laying of 150 mm dia. D.I distribution pipe line and restoration of drainage system at Mojlish Dighir Par at Mongalkote under MONGALKOTE Piped Water Supply Scheme under Mongalkote Block under Katwa Sub-Division under Burdwan Division, P.H.E. Dte. | 1577/BWD | 16/03/2022 | 30 | ASMA ENTERPRISE | 7.93 | 0 | 0 | 1
3686 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme , SM/07800 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Paschim Gopalpur (Part) village (Jadabbati, Mirapur & Paschim Gopalpur (Part) habitation) & Radhanagar village (Radhanagar habitation) of Paschim Gopalpur Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Sl. No. : ¿14¿] | 64/BWD | 05/01/2021 | 15 | ASMA ENTERPRISE | 4.86 | 4.86 | 100 | 1
3687 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme , SM/07800 | Retrofitting | Extension of pipe line from the existing Distribution System within scheme jurisdiction at Paschim Gopalpur & Mirapur village under Paschim Gopalpur PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-1) | 698/KTS | 27/10/2021 | 15 | ASMA ENTERPRISE | 1.06 | 1.06 | 100 | 1
3688 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme , SM/07800 | Retrofitting | Providing Functional Household Tap Connection from existing distribution system at Sukhpukuria village under Gotistha Gram Panchayet under Mongalkote Block under Paschim Gopalpur PWSS under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-2) | 799/KTS | 10/12/2021 | 15 | JAMALUDDIN SK | 3.69 | 3.67 | 100 | 1
3689 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme , SM/07800 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Mongalkote Block under Burdwan Division, PHE. Dte. | 284/BWD | 17/01/2022 | 30 | BABUL SK | 6.81 | 0.41 | 100 | 1
3690 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme , SM/07800 | Retrofitting | Providing Functional Household Tap Connection at Jadabbati,Sukhpukuria and Pilsona habitation of Paschim Gopalpur, Sukhpukuria and Pilsona village of Gotistha G.P. from existing distribution system within the command area of Paschim Gopalpur PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. | 1439/BWD | 11/03/2022 | 30 | PARTHA PRATIM ACHARYA | 10.47 | 10.41 | 100 | 1
3691 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme , SM/07800 | Retrofitting | Restoration of pipe line at Mera Para to Babunara, Gopalpur to Nayapaya and Pilsoya to Darshini due to construction of drain by PRI bodies along with crossing culvert under the command area Paschim Gopalpur PWSS (SM/07800) under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. (Sl No-02) | 343/KTS | 05/03/2025 | 30 | M/S S. CHOUDHURY | 3.63 | 0 | 0 | 100
3692 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gopalpur Piped Water Supply Scheme , SM/07800 | Retrofitting | Construction of approach Road and Land Development at Head Work Site of Paschim Gopalpur PWSS (SM/07800) under Katwa Sub-Division under Mongolkote Block within Burdwan Division PHE Dte. (Sl No -01) | 342/KTS | 05/03/2025 | 30 | OM CONSTRUCTION | 4.83 | 0 | 0 | 100
3693 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jalahati Piped Water Supply Scheme at Purbasthali-I Block , SM/07803 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jalahati (P) village (Jalahati (P) habitation) of Jalahati Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [SL. No. : 26] | 1462/BWD | 18/02/2021 | 15 | BARDHAMAN AQUA ENGINEERING | 4.86 | 9.73 | 200 | 1
3694 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jalahati Piped Water Supply Scheme at Purbasthali-I Block , SM/07803 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jalahati (P)village (Beltalapara habitation) of Jalahati Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part-A). [SL. No. : 24] | 1465/BWD | 18/02/2021 | 15 | SETH ENTERPRISE | 4.82 | 9.73 | 200 | 1
3695 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jalahati Piped Water Supply Scheme at Purbasthali-I Block , SM/07803 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jalahati village of Jalahati piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-768/BWD/2020-21) | 4793/1/BWD | 03/12/2020 | 30 | SETH ENTERPRISE | 4.92 | 9.84 | 200 | 1
3696 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jalahati Piped Water Supply Scheme at Purbasthali-I Block , SM/07803 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jalahati (P) village (Beltalapara habitation) of Jalahati Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. (Part-B). [SL. No. : 25] | 1464/BWD | 18/02/2021 | 15 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.86 | 9.73 | 200 | 1
3697 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jalahati Piped Water Supply Scheme at Purbasthali-I Block , SM/07803 | Retrofitting | Providing 350 Nos. FHTC work at JALAHATI W/S scheme for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification) within Purbasthali-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | 1520/BWD | 28/03/2023 | 30 | IYASIN DAFADAR | 14.47 | 13.57 | 93.78 | 0
3698 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Providing Functional Household tap connection from existing distribution system within the command area of Augmentation of Purbasthali piped water supply scheme at Palaspuli village (Mouza), Purbasthali-II Block under Burdwan Division, PHE Dte. | 993./BWD | 04/02/2021 | 45 | IJABUL SEKH | 51.07 | 0 | 0 | 1
3699 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Augmentation of Purbasthali Piped Water Supply Scheme at Chupi Village (Mouza), Purbasthali-II Block under Burdwan Division, PHE Dte._2ND CALL | 1589/BWD | 22/02/2021 | 45 | DHIRENDRA ENGINEERING & CONSTRUCTION | 70.28 | 55.84 | 146.87 | 1
3700 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
3701 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Extension of different dia UPVC Pipeline (suggested) as per survey of Horizon of Zone-III portion of Surface Based W/S Scheme in Arsenic Affected Areas of Purbasthali - II Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | 3136/BWD | 03/06/2021 | 60 | ASHOK KUMAR GHOSH | 34.74 | 34.29 | 100 | 1
3702 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Extension of different dia UPVC pipeline (suggested) as per survey of Horizon of Zone-I portion of surface based water supply scheme in Arsenic affected areas of Purbasthali-II Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | 826/BWD | 01/02/2021 | 60 | DEY NIRMAN | 24.83 | 2.77 | 100 | 1
3703 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Extension of different dia UPVC pipeline (suggested) as per survey of Horizon of Zone-IV portion of surface Based Water supply scheme in Arsenic affected areas of Purbasthali-II Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | 754/BWD | 29/01/2021 | 60 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 20.95 | 6.92 | 100 | 1
3704 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Construction of Pump House cum chlorine room (3.6 mtr x 3.0 mtr room) without sanitary and water supply arrangement at old Head Work Site of Purbasthali & it's adj. mouzas water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.^ (Sl No-C) | 986/KSD Dt- 24.09.2021 | 24/09/2021 | 60 | SURATH DEY | 2.84 | 2.74 | 100 | 1
3705 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Laying of different dia UPVC pipe at the balance portion of different section for Augmentation of Purbasthali & its adjoining mouzas water supply scheme within Kalna Sub-Division, under Burdwan Division, PHE Dte.[Part-C][Gr.-C] | 31/KSD | 11/01/2021 | 45 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 4.68 | 0 | 0 | 1
3706 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Relaying of different dia UPVC pipeline at damaged portion as shown by Horizon of Zone-III of surface based water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL-B] | 148/KSD | 12/02/2021 | 30 | CHANCHAL PAL | 4.82 | 0 | 0 | 1
3707 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Work Order for "Providing Functional house hold tap connections for Sajal Gram Village within Purbasthali-II Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Purbasthali Aug & Kamalnagar water supply scheme)" | 346/KSD | 17/04/2023 | 30 | RAJESH DAFADAR | 0.88 | 0.84 | 100 | 100
3708 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Work Order for "Repairing and laying of UPVC pipeline of Majida, Nimdaha, Lakshmipur and Ukhura village for smooth running of FHTC work of Surface Based Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | 1303/KSD | 23/08/2023 | 15 | PARTHA PRATIM ACHARYA | 1 | 1 | 100 | 100
3709 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Hire and labour charges for staging and scaffolding bamboo barricading and removal of rubbish for dismantling capacity 136 Cum of RCC Over Head Reservoir at Purbasthali & it's adj. mouzas water Supply Scheme within Kalna Sub Divison under Burdwan Division , PHE Dte. (Sl No-A) | 967/KSD Dt-20.09.2021 | 20/09/2021 | 30 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 4.47 | 2.56 | 100 | 1
3710 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Material Requisition To Resource Division | 1111/BWD | 26/02/2022 | 0 | Resource Division | 37.62 | 0 | 0 | 0
3711 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Hire & fuel charges of vehicle Car No.-WB-41J-6795 for the month of June & July2023. | 745/JJM | 11/10/2023 | 0 | MD HASIN | 0.79 | 0 | 0 | 0
3712 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at balance portion from existing distribution system within the command area of Aug. of PURBASTHALI Piped Water Supply Scheme at Chupi village (Mouza), Purbasthali - II Block under Burdwan Division, PHE Dte. | 2079/BWD | 20/04/2022 | 30 | M/S K.P. CONSTRUCTION | 39.64 | 22.64 | 100 | 100
3713 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Augmentation of Purbasthali piped water supply scheme at Palaspuli village (Mouza), Purbasthali-II Block under burdwan Division, PHE Dte. | 993/BWD | 04/02/2021 | 45 | IJABUL SEKH | 51.07 | 63 | 200 | 0
3714 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of AUGMENTATION OF PURBASTHALI Piped Water Supply Scheme at Purbasthali-II Block , SM/07866 | Retrofitting | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 618/BWD | 11/02/2025 | 180 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0 | 0
3715 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme , SM/07544 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kailaspur Habitation of Kenna Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [GROUP : ¿L¿] (T.R. No. 201/BWD of 2020-2021) | 2399/BWD | 20/07/2020 | 30 | BRINDABAN KONAR | 4.92 | 0 | 0 | 1
3716 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme , SM/07544 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kailaspur Habitation of Kenna Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [GROUP : ¿L¿] (T.R. No. 248/BWD of 2020-2021) | 3517/BWD | 25/09/2020 | 30 | BRINDABAN KONAR | 4.92 | 0 | 0 | 1
3717 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme , SM/07544 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kenna village of Kenna piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1225/BWD | 11/02/2021 | 30 | BRINDABAN KONAR | 4.92 | 9.84 | 200 | 1
3718 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme , SM/07544 | Retrofitting | Extension of pipeline for Kenna Water Supply Scheme (Kenna, Dahura, Kailashpur, Dadur, Baral Village) within Memari - I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | 6307/BWD | 09/11/2021 | 60 | T.K. BANERJEE & CO. | 41.46 | 41.02 | 100 | 1
3719 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme , SM/07544 | Retrofitting | Extension of pipeline for KENNA Piped Water Supply Scheme at Kaliashpur 25 Nos FHTC Work for Sajal Gram (As per Field Verification Report for Har Ghar Jal Certification within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte. | 1391-A/BSD | 08/08/2022 | 5 | BRINDABAN KONAR | 0.97 | 0 | 0 | 0
3720 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme , SM/07544 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Memari-I Block (Daluibazar-II, Gopegantar-I & II G.P.) under Burdwan Division, PHE. Dte. Dte._Part-A. | 209/BWD | 11/01/2022 | 30 | M/S ANAND CONSTRUCTION | 21.11 | 5 | 100 | 1
3721 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme , SM/07544 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41G-2149) for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. for the month of February'23. | 1226/JJM | 20/03/2023 | 0 | SK.ASFIA | 0.4 | 0 | 0 | 0
3722 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Kenna Piped Water Supply Scheme , SM/07544 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KENNA Piped Water Supply Scheme at Dandur, Kailashpur (2 Nos. Habitation) village (Mouza), Memari - I Block under Burdwan Division, PHE Dte.[Agreement No. 570/BWD OF 2020-2021.] | 438/BWD | 19/01/2021 | 30 | BRINDABAN KONAR | 22.09 | 43.57 | 200 | 0
3723 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS , SM/06773 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of SRIKHANDA Piped Water Supply Scheme at Katwa - I Block under Burdwan Division, PHE Dte.(Agreement No. 53/2020-2021 OF SE/CC/PHE. DTE.) | 4880/BWD | 07/12/2020 | 90 | ASHOK KUMAR GHOSH | 96.84 | 75.09 | 200 | 1
3724 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS , SM/06773 | Retrofitting | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-7] | 2942/BWD | 04/05/2021 | 10 | KISHORE GHOSH | 3.94 | 3.44 | 100 | 1
3725 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS , SM/06773 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bohar village and Bohar habitation of Satgachia piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-435/BWD/2020-21) | 3327/BWD | 18/09/2020 | 30 | TARAMA AGENCY | 4.86 | 9.66 | 200 | 0
3726 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS , SM/06773 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jakra village and Jakra Paschimpara habitation of Satgachhia piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-383/BWD/2020-21) | 3328/BWD | 18/09/2020 | 30 | A R TRADERS | 4.86 | 9.72 | 200 | 0
3727 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS , SM/06773 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jakra (Part) village (Innathgore Habitation) & Bohat (Part) village (Hamunpur Habitation) of Satgachia piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Sl No.-21] | 71/BWD | 05/01/2021 | 15 | A R TRADERS | 4.86 | 9.71 | 200 | 0
3728 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Srikhanda PWSS , SM/06773 | Retrofitting | Continuation work order for water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bohar village and Bohar habitation of Satgachia piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.[Phase-I][Gr.-4B] | 4990/BWD | 10/12/2020 | 30 | TARAMA AGENCY | 4.86 | 9.37 | 200 | 0
3729 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08704 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila Habitation) of Bagila piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Part-A)[SL NO.-08] | 587./BWD | 25/01/2021 | 15 | PAL CONSTRUCTION | 4.86 | 9.71 | 200 | 1
3730 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08704 | Retrofitting | Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of BAGILA Piped Water Supply Scheme at Kiskinda (2 nos Hab), Krishnapur, Talchini & Bagila (Part) Village (Mouza), Memari-I Block under Burdwan Division, PHE Dte. | 4659/BWD | 10/09/2021 | 60 | HAMID SK | 60.69 | 53.57 | 100 | 1
3731 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08704 | Retrofitting | Extension of pipe line for BAGILA Piped Water Supply Scheme at Krishnapur,Baharampur,Kiskindha,Taktipur in Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte.Group : A | 983/BSD | 16/06/2022 | 30 | A R TRADERS | 4.83 | 4.83 | 100 | 1
3732 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08704 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila Habitation) of Bagila piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte.(Part-B)[SL NO.-09] | 585./BWD | 25/01/2021 | 15 | HAMID SK | 4.87 | 9.73 | 200 | 1
3733 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08704 | Retrofitting | Extension of pipeline for BAGILA Water Supply Scheme at (Baharampur, Taktipur, Krishnapur & Kiskinda North East) village within Memari I Block, under Burdwan Division, PHE Dte. | 1708/BWD | 25/03/2022 | 30 | A R TRADERS | 27.27 | 27.27 | 100 | 1
3734 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08704 | Retrofitting | Sinking of additional 250 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for BAGILA Piped Water Supply Scheme, Block - Memari - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte._ 2ND CALL | 3503/BWD | 10/08/2022 | 30 | MUNSHI ENTERPRISE | 10.18 | 0 | 0 | 1
3735 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08704 | Retrofitting | Emergency repaired cleaning of chokage AC Pipeline for (Retrofittins) for BAGILA Piped water supply scheme at Baharampur, Takipur & Kiskinda village for smooth drinking water supply (FHTC) within Memari-I Block under Burdwan Division, PHE Dte. Gr.A | 1918/BSD | 11/11/2022 | 15 | A R TRADERS | 0.93 | 0.93 | 100 | 1
3736 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08704 | Retrofitting | Sinking of additional tube well 250 x 200 mm dia Tube well 150 mtr depth by D.R. Rig method using upvc pipe (CD) and fibre glass strainer for Bagila piped water supply scheme (2nd tube well site), Block-Memari-I under Burdwan Division, PHE Dte. | 1494/BWD | 18/02/2021 | 30 | C.M. ENTERPRISE | 8.68 | 8.21 | 100 | 0
3737 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08704 | Retrofitting | Preparation and Submission of DPR for Augmentation of Ground Water Based Piped Water Supply Scheme for MAHESHDANGA, Block:Memari-I under Burdwan Division, P.H.E Dte. | 1909/BSD | 28/08/2024 | 15 | CARTO | 0 | 0 | 0 | 0
3738 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08704 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila habitation) of Bagila Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - B) [SL. No. : 09] | 3465/BWD | 29/06/2021 | 15 | HAMID SK | 4.87 | 9.73 | 200 | 0
3739 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08704 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Bagila village (Bagila habitation) of Bagila Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [SL. No. : 08] | 3406/BWD | 25/06/2021 | 15 | PAL CONSTRUCTION | 4.86 | 9.71 | 200 | 0
3740 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08704 | Retrofitting | Restoration of Pump House at Head Work site of BAGILA Piped water supply scheme at Memari-I Block under Burdwan Division, Dist.-Purba Bardhaman | 1006/BSD | 06/06/2024 | 30 | A.R. TRADERS | 0.96 | 0.95 | 100 | 100
3741 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08704 | Retrofitting | MAINTENANCE OF ROAD (WHISH IS DAMAGED FOR LAYING PIPELINE BY PHE DEPTT) NAMELY NARUGRAM H.C TO BADSHI ROAD VIDE- PACKAGE NO- WB 22 12 UNDER PMGSY-III UNDER NARUGRAM GP. & RAINA-I BLOCK, IN PURBA BARDHAMAN DISTRICT | 894/JJM | 25/09/2024 | 0 | EXECUTIVE ENGINEER (WBSRDA) PURBA BARDHAMAN DIVISION | 3.86 | 0 | 0 | 0
3742 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting within the command area of Bagila piped Water Supply Scheme at Memari-I Block under Burdwan Division, P.H.E. DTE. , SM/08704 | Retrofitting | Laying of 150mm DI pipeline for interconnection of 4no tw to distribution line & Kalsi mouza 3rd tw to distribution line for Bagila Piped Water Supply Scheme under memari-I Block, District:- Purba-Bardhaman. | 105/BSD | 16/01/2025 | 30 | A.R. TRADERS | 1.88 | 0 | 0 | 0
3743 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09488 | Augmentation | Route Survey & Preparation of DPR for Sridharpur W/S Scheme under Memari-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.6. | 181/BSD | 31/01/2022 | 30 | RADIANT | 2.59 | 2.59 | 100 | 1
3744 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09488 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3745 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09488 | Augmentation | Augmentation of SRIDHARPUR Piped Water Supply Scheme with LDS, FHTC, Rising Main with necessary interconnection, Construction of 200 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation under Memari II Block, District Purba Bardhaman. | 1937/BWD | 11/04/2022 | 365 | SUJAY KUMAR RAY | 251.3 | 178.78 | 71.14 | 60
3746 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09488 | Augmentation | Material Requisition To Resource Division | 562/BWD | 27/01/2022 | 0 | Resource Division | 11 | 0 | 0 | 0
3747 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09488 | Augmentation | Material Requisition To Resource Division | 1069/BWD | 24/02/2022 | 0 | Resource Division | 37.52 | 0 | 0 | 0
3748 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09488 | Augmentation | Material Requisition To Resource Division | 1520/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
3749 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SRIDHARPUR PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09488 | Augmentation | Replacement of Tube-well & Rising main at HEAD TW site for Aug. of PARHATI, SRIDHARPUR, SATGACHIA ZONE-I, SATGACHIA ZONE-II, Piped Water Supply Scheme within MEMARI-II Block under Burdwan Divn., PHE. Dte. District:- Purba-Bardhaman. | 24/BWD | 03/01/2024 | 637 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 54.2 | 17.35 | 100 | 90
3750 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Material Requisition To Resource Division | 5524/BWD | 23/12/2022 | 0 | Resource Division | 12.41 | 0 | 0 | 0
3751 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 at Selimabad Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | 3117/CMD | 23/11/2022 | 30 | M/S. DAS ELECTRIC CO. | 11.08 | 10.67 | 100 | 80
3752 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | PROVIDING TUBE WELLMATERIALS CONFORMING TO IS: 12818:2010 WITH OTHER WORKS AT SITE FOR CONSTRUCTION OF TUBE WELL AT SELIMABAD PWSS (TW-I), JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. | 313/CMSD-I | 22/07/2022 | 15 | UTTAM KUMAR CHATTERJEE | 3.29 | 3.16 | 100 | 1
3753 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | PROVIDING DRILLING CREWS FOR CONSTRUCTION OF TUBE WELL (250MM X 150MM) BY DEPARTMENTAL RIG MACHINE FOR SELIMABAD PWSS (TW-I), JAMALPUR BLOCK UNDER PURBA BARDAMAN, CDD, PHE DTE. | 312/CMSD-I | 22/07/2022 | 15 | UTTAM KUMAR CHATTERJEE | 1.74 | 1.38 | 100 | 1
3754 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | PROVIDING PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED AT SITE WITH OTHER WORKS FOR CONSTRUCTION OF TUBE WELL AT SELIMABAD PWSS (TW-I), JAMALPUR BLOCK UNDER PURBA BARDHAMAN, CDD, PHE DTE. | 315/CMSD-I | 12/07/2022 | 15 | UTTAM KUMAR CHATTERJEE | 1.88 | 1.19 | 100 | 1
3755 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Providing Drilling crew and other allied works for construction of Tube well (250mm x 150mm) by utilising Departmental machineries for Selimabad PWSS(TW-I), Jamalpur block under Purba Bardhaman District, CDD PHE Dte. | 322/CMSD-I(D) | 12/07/2022 | 15 | M/S SREEJIT ENTERPRISE | 1.73 | 1.55 | 100 | 100
3756 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Providing pea size Gravels and Bentonite Powder sodium based at site with other works for construction of Tube well at Selimabad PWSS(TW-II), Jamalpur block under Purba Bardhaman District, CDD PHE Dte. | 324/CMSD-I(D) | 12/07/2022 | 15 | M/S SREEJIT ENTERPRISE | 1.88 | 1.16 | 100 | 100
3757 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Providing Tube well materials conforming to IS: 12818:2010 with other works at site for construction of Tube well at Selimabad PWSS(TW-II), Jamalpur block under Purba Bardhaman District, CDD PHE Dte. | 321/CMSD-I(D) | 12/07/2022 | 15 | M/S SREEJIT ENTERPRISE | 3.28 | 3.24 | 100 | 100
3758 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 5.49 | 0 | 0 | 0
3759 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | New service connection charges for Selimabad PWSS TW-2 | BP-2023-24-191 | 09/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.82 | 0 | 0 | 0
3760 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | New service connection charges for Selimabad W/S Scheme TW-1 | BP-2023-24-16 | 22/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.37 | 0 | 0 | 0
3761 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.02.2024 to 31.03.2024] | 44/AE/HQ | 29/01/2024 | 60 | SK. ASRAFUDDIN | 0.8 | 0.8 | 99.9 | 50
3762 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.04.2024 to 31.05.2024] | 226/AE/HQ | 27/03/2024 | 61 | SK. ASRAFUDDIN | 0.8 | 0.8 | 99.66 | 0
3763 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.08.2024 to 30.09.2024] | 545/AE/HQ | 01/08/2024 | 61 | SK. ASRAFUDDIN | 0.8 | 0.8 | 99.86 | 0
3764 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.06.2024 to 31.07.2024] | 304/AE/HQ | 31/05/2024 | 61 | SK. ASRAFUDDIN | 0.8 | 0.8 | 99.71 | 0
3765 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Providing pea size Gravels and Bentonite Powder sodium based at site with other works for construction of tube well at Selimabad PWSS( TW-III),Jamalpur Block under Purba Bardhaman ,Central Drilling Division, P.H.E Dte | 269/CMSD-I(D) | 04/12/2023 | 15 | C.M. ENTERPRISE | 1.88 | 0.78 | 100 | 100
3766 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Providing Tube well materials Conforming to IS: 12818:2010 with other Works at site for construction of Tube Well at Selimabad PWSS (TW-III),Jamalpur Block under Purba Bardhaman , Central Drilling Division, P.H.E Dte. | 271/CMSD-I(D) | 04/12/2023 | 15 | C.M. ENTERPRISE | 3.28 | 2.39 | 100 | 100
3767 | PURBA BARDHAMAN | Central Drilling | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Providing drilling crews for construction of TW (250mm x 150mm) by Departmental Rig machine for Selimabad PWSS (TW-III), Jamalpur block under Purba Midnapur, CDD, PHE Dte. | 270/CMSD-I(D) | 04/12/2023 | 15 | C.M. ENTERPRISE | 1.73 | 1.55 | 100 | 100
3768 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-2 at Selimabad Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | 3118/CMD | 23/11/2022 | 30 | SUBRATA BHADRA | 11.07 | 10.72 | 100 | 95
3769 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Quotation from WBSEDCL for new connection charges of Selimabad w/s scheme of T.W.-3 under Burdwan Division, PHE Dte. | 1824/JJM | 27/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 10.47 | 0 | 0 | 0
3770 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | NEW SERVICE CONNECTION FOR SELIMABAD PWSS. | BP-2023-24-565 | 23/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.66 | 0 | 0 | 0
3771 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Additional Quotation for new service connection at Selimabad PWSS PH-3. | BP-2024-25-248 | 01/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.95 | 0 | 0 | 0
3772 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.02.2025 to 31.03.2025] | 187/AE/HQ | 31/01/2025 | 59 | SK. ASRAFUDDIN | 0.8 | 0.76 | 94.73 | 0
3773 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.12.2024 to 31.01.2025] | 1012/AE/HQ | 29/11/2024 | 61 | SK. ASRAFUDDIN | 0.8 | 0.8 | 99.87 | 0
3774 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.10.2024 to 30.11.2024] | 821/AE/HQ | 01/10/2024 | 61 | SK. ASRAFUDDIN | 0.8 | 0.7 | 87.03 | 0
3775 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.06.2025 to 31.07.2025] | 685/AE/HQ | 30/05/2025 | 61 | SK. ASRAFUDDIN | 0.8 | 0 | 0 | 0
3776 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Continuation work for Supply of one no. Diesel / LPG / CNG driven Motor Cab / Maxi Cab (Air Condition) on hire basis for the office of the Executive Engineer, Burdwan Division, P.H.E. Dte. to be used by the Assistant Engineer, Headquarters, P.H.E. Dte. [Period from 01.04.2025 to 31.05.2025] | 453/AE/HQ | 28/03/2025 | 61 | SK. ASRAFUDDIN | 0.8 | 0.77 | 95.73 | 0
3777 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Laying of additional pipeline (HDPE) with interconnection from Selimabad 3rd Pump House to BDO Office under Selimabad PWSS, Jamalpur Dev. Block under PHE. Dte. | 1037/AE/HQ | 01/08/2025 | 30 | A.R. TRADERS | 0.97 | 0 | 0 | 0
3778 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED SELIMABAD PIPED WATER SUPPLY SCHEME JAMALPUR BLOCK PURBA BARDHAMAN , SM/11492 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Selimabad Water Supply Scheme [ Block- Jamalpur ] under CMD, PHE Dte., Dist.- Purba-Bardhaman | 3119/CMD | 23/11/2022 | 740 | MITRA ENTERPRISE | 10.73 | 7.58 | 100 | 98
3779 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. , SM/11514 | School | Material Requisition To Resource Division | 5400/BWD | 12/12/2022 | 0 | Resource Division | 105.18 | 0 | 0 | 0
3780 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. , SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Ketugram - II Block (09 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | 3807/BWD | 02/09/2022 | 30 | M/S STANDARD CONSTRUCTION | 9.76 | 7.37 | 75.43 | 0
3781 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. , SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Katwa I Block (35 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte.(Part-A). | 3587/BWD | 17/08/2022 | 45 | HAMID SK | 38.97 | 33.15 | 100 | 0
3782 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. , SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Katwa I Block (35 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte.(Part B). | 3635/BWD | 23/08/2022 | 45 | JAI MAA DURGA & CO. | 39.46 | 36.01 | 100 | 0
3783 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. , SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Ketugram - I Block (33 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-A). | 3514/BWD | 12/08/2022 | 45 | JAHAR GHOSH | 36.83 | 33.55 | 100 | 100
3784 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. , SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Mongalkote Block (39 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte.(Part-A). | 3515/BWD | 12/08/2022 | 45 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 43.97 | 39.72 | 100 | 100
3785 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. , SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Mongalkote Block (39 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte.(Part-B). | 3516/BWD | 12/08/2022 | 45 | S.S. CONSTRUCTION | 43.97 | 39.18 | 100 | 100
3786 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. , SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Ketugram - I Block (33 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-B)._2ND CALL. | 3586/BWD | 17/08/2022 | 45 | ANIRUDDHA FARUQUE | 35.94 | 34.06 | 100 | 0
3787 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. , SM/11514 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Katwa ? II Block (27 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | 3526/BWD | 12/08/2022 | 45 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 30.2 | 24.5 | 100 | 0
3788 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at left out Primary Schools(250 nos) for 100% School Coverage in Purba Bardhaman within Katwa Sub Division under Burdwan Division P.H.E. DTE. , SM/11514 | School | Material Requisition To Resource Division | 3301/BWD | 29/07/2022 | 0 | Resource Division | 32.5 | 0 | 0 | 0
3789 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. , SM/11285 | School | Material Requisition To Resource Division | 5399/BWD | 12/12/2022 | 0 | Resource Division | 85 | 0 | 0 | 0
3790 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. , SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Raina II Block (39 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-B). | 3634/BWD | 23/08/2022 | 45 | PREMANANDA ROY BISWAS | 43.83 | 41.05 | 93.67 | 0
3791 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. , SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Memari ¿ I Block (17 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | 3415/BWD | 05/08/2022 | 30 | DIPAYAN DEY | 17.85 | 14.9 | 83.47 | 100
3792 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. , SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Raina I Block (34 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-A)_2ND CALL. | 3673/BWD | 29/08/2022 | 45 | MOTI RAHAMAN | 37.97 | 27.67 | 72.87 | 0
3793 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. , SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Burdwan-I Block (37 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | 3419/BWD | 05/08/2022 | 45 | P.C. CONSTRUCTION | 41.51 | 35.48 | 100 | 0
3794 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. , SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Khandaghosh Block (43 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-A). | 3690/BWD | 29/08/2022 | 45 | SHUBHRA KANTI GHOSH | 48.43 | 42.33 | 100 | 0
3795 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. , SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Khandaghosh Block (43 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-B). | 3666/BWD | 29/08/2022 | 45 | M/S LOKE NIRMAN | 48.38 | 29.13 | 100 | 100
3796 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. , SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Raina ¿ II Block (34 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-A). | 3612/BWD | 18/08/2022 | 45 | HAFIJUR RAHAMAN MIDYA | 43.97 | 26.45 | 100 | 0
3797 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. , SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Jamalpur Block (05 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | 3588/BWD | 17/08/2022 | 15 | UDYOG CONSTRUCTION | 4.72 | 4.41 | 100 | 0
3798 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. , SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Raina I Block (33 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. (Part-B). | 3416/BWD | 05/08/2022 | 45 | THREE MAA ENTERPRISE | 36.46 | 30.34 | 100 | 0
3799 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. , SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Burdwan-II Block (28 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | 3414/BWD | 05/08/2022 | 45 | G.S. CONSTRUCTION & CO. | 31.49 | 27.19 | 100 | 0
3800 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. , SM/11285 | School | Sinking of 100mtr. deep 100 × 40mm tubewell for providing water supply arrangement in Schools under Memari II Block (41 Nos School) within Purba Bardhaman District under Burdwan Division, PHE Dte. | 3636/BWD | 23/08/2022 | 45 | BRINDABAN KONAR | 46.23 | 34.63 | 100 | 100
3801 | PURBA BARDHAMAN | Burdwan Division | Providing Water Supply Arrangement by Sinking of Tube Well at leftout Primary Schools(359 nos) for 100% School Coverage in Purba Bardhaman within Burdwan South Sub Division under Burdwan Division P.H.E. DTE. , SM/11285 | School | Material Requisition To Resource Division | 3298/BWD | 29/07/2022 | 0 | Resource Division | 90.49 | 0 | 0 | 0
3802 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED DEWANDIGHI MIRJAPUR PWSS TO ACCOMMODATE FHTC IN BURDWAN-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09494 | Augmentation | Route Survey & Preparation of DPR for Dewandighi-Mirzapur W/S Scheme under Burdwan-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.5. | 180/BSD | 31/01/2022 | 30 | RADIANT | 2.51 | 2.5 | 100 | 1
3803 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED DEWANDIGHI MIRJAPUR PWSS TO ACCOMMODATE FHTC IN BURDWAN-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09494 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
3804 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED DEWANDIGHI MIRJAPUR PWSS TO ACCOMMODATE FHTC IN BURDWAN-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09494 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Paharhati, Nababhat, Shyamsundar & Dewandighi-Mirzapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. | 4703/BWD | 19/10/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 3.61 | 100 | 1
3805 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED DEWANDIGHI MIRJAPUR PWSS TO ACCOMMODATE FHTC IN BURDWAN-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09494 | Augmentation | Allied work for Augmentation of DEWANDIGHI PWSS under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1168/BWD | 14/03/2023 | 45 | BOSE ENTERPRISE | 50.01 | 46.23 | 100 | 100
3806 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED DEWANDIGHI MIRJAPUR PWSS TO ACCOMMODATE FHTC IN BURDWAN-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09494 | Augmentation | Material Requisition To Resource Division | 560/BWD | 27/01/2022 | 0 | Resource Division | 11.04 | 0 | 0 | 0
3807 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED DEWANDIGHI MIRJAPUR PWSS TO ACCOMMODATE FHTC IN BURDWAN-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09494 | Augmentation | Material Requisition To Resource Division | 1538/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
3808 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED DEWANDIGHI MIRJAPUR PWSS TO ACCOMMODATE FHTC IN BURDWAN-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09494 | Augmentation | Material Requisition To Resource Division | 881/BWD | 11/02/2022 | 0 | Resource Division | 13.26 | 0 | 0 | 0
3809 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED DEWANDIGHI MIRJAPUR PWSS TO ACCOMMODATE FHTC IN BURDWAN-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09494 | Augmentation | Augmentation of DEWANDIGHI Piped Water Supply Scheme with LDS, FHTC, Rising main with necessary interconnection, Construction of 200 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under Burdwan-I Block, District:- Purba-Burdwan. | 2055/BWD | 19/04/2022 | 365 | SHREE J.M. CONSTRUCTION | 213.62 | 190.06 | 100 | 100
3810 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED DEWANDIGHI MIRJAPUR PWSS TO ACCOMMODATE FHTC IN BURDWAN-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09494 | Augmentation | Balance Work for extension of pipe lines to provide FHTC With Sinking of Tub well , Construction of pump house with Boundary wall & other related work for TALIT-SIMDAL (SM/18112), NABABHAT (SM-15166) and DEWANDIGHI-MIRJAPUR (SM/09494) PWSS under Burdwan Sub-Div., Block -Bwn-1, under Burdwan Division PHE Dte. | 793/BWD | 03/03/2025 | 120 | M/S S.S. ENTERPRISE | 227.66 | 0 | 0 | 0
3811 | PURBA BARDHAMAN | Burdwan Division | KHURUL PIPED WATER SUPPLY SCHEME , SM/13549 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 6.52 | 0 | 0 | 0
3812 | PURBA BARDHAMAN | Burdwan Division | KHURUL PIPED WATER SUPPLY SCHEME , SM/13549 | New | Material Requisition To Resource Division | 4911/BWD | 10/11/2023 | 0 | Resource Division | 32.92 | 0 | 0 | 0
3813 | PURBA BARDHAMAN | Burdwan Division | KHURUL PIPED WATER SUPPLY SCHEME , SM/13549 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 23.91 | 0 | 0 | 0
3814 | PURBA BARDHAMAN | Central Mechanical | KHURUL PIPED WATER SUPPLY SCHEME , SM/13549 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
3815 | PURBA BARDHAMAN | Central Mechanical | KHURUL PIPED WATER SUPPLY SCHEME , SM/13549 | New | NEW SERVICE CONNECTION FOR KHURUL PIPED WATER SUPPLY SCHEME. | BP-2023-24-589 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.45 | 0 | 0 | 0
3816 | PURBA BARDHAMAN | Central Mechanical | KHURUL PIPED WATER SUPPLY SCHEME , SM/13549 | New | NEW SERVICE CONNECTION FOR KHURUL PIPED WATER SUPPLY SCHEME. | BP-2023-24-588 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.72 | 0 | 0 | 0
3817 | PURBA BARDHAMAN | Central Mechanical | KHURUL PIPED WATER SUPPLY SCHEME , SM/13549 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KHURUL Water Supply Scheme [ Block- BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4089/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 27.79 | 10.74 | 38.66 | 60
3818 | PURBA BARDHAMAN | Burdwan Division | KHURUL PIPED WATER SUPPLY SCHEME , SM/13549 | New | KHURUL Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | 5480/BWD | 13/12/2023 | 476 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 182.02 | 79.47 | 51.31 | 65
3819 | PURBA BARDHAMAN | Burdwan Division | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13424 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 3.93 | 0 | 0 | 0
3820 | PURBA BARDHAMAN | Burdwan Division | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13424 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.07 | 0 | 0 | 0
3821 | PURBA BARDHAMAN | Burdwan Division | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13424 | New | Material Requisition To Resource Division | 5268/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
3822 | PURBA BARDHAMAN | Central Mechanical | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13424 | New | New service connection charges for Guir PWSS TW 1 | BP-2023-24-96 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.97 | 0 | 0 | 0
3823 | PURBA BARDHAMAN | Central Mechanical | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13424 | New | New service connection charges for Guir PWSS TW-2 | BP-2023-24-84 | 26/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.96 | 0 | 0 | 0
3824 | PURBA BARDHAMAN | Central Mechanical | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13424 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
3825 | PURBA BARDHAMAN | Burdwan Division | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13424 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day [Period February'2024 to April'2024] | 91/DSD | 31/01/2024 | 78 | MD HASIN | 1 | 0.29 | 88.46 | 0
3826 | PURBA BARDHAMAN | Burdwan Division | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13424 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period May'2024 to July'2024] | 369/DSD | 30/04/2024 | 78 | MD HASIN | 1 | 0.31 | 92.31 | 0
3827 | PURBA BARDHAMAN | Burdwan Division | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13424 | New | Balance work for providing Functional Household Tap Connection (FHTC) within the command area KHEJURHATI & GUIR W/S. Scheme of Khandaghosh Block under Burdwan Division, PHE. Dte. | 724/BWD | 24/02/2025 | 120 | ROY CONSTRUCTION | 153.99 | 0 | 0 | 0
3828 | PURBA BARDHAMAN | Central Mechanical | GUIR PIPED WATER SUPPLY SCHEME IN KHANDOGHOSH BLOCK , SM/13424 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Guir Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2855/CMD | 05/07/2023 | 30 | M/S GHOSH ENTERPRISE | 28.95 | 22.59 | 95.17 | 90
3829 | PURBA BARDHAMAN | Burdwan Division | NOAHATI PIPED WATER SUPPLY SCHEME , SM/13452 | New | Material Requisition To Resource Division | 1247/BWD | 17/03/2023 | 0 | Resource Division | 11.94 | 0 | 0 | 0
3830 | PURBA BARDHAMAN | Burdwan Division | NOAHATI PIPED WATER SUPPLY SCHEME , SM/13452 | New | Material Requisition To Resource Division | 3989/BWD | 08/09/2023 | 0 | Resource Division | 2.9 | 0 | 0 | 0
3831 | PURBA BARDHAMAN | Burdwan Division | NOAHATI PIPED WATER SUPPLY SCHEME , SM/13452 | New | Material Requisition To Resource Division | 5056/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
3832 | PURBA BARDHAMAN | Central Mechanical | NOAHATI PIPED WATER SUPPLY SCHEME , SM/13452 | New | New service connection charges for Noahati PWSS TW-1 | BP-2023-24-74 | 21/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.87 | 0 | 0 | 0
3833 | PURBA BARDHAMAN | Central Mechanical | NOAHATI PIPED WATER SUPPLY SCHEME , SM/13452 | New | New service connection charges for Noahati PWSS TW-2 | BP-2023-24-75 | 21/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.17 | 0 | 0 | 0
3834 | PURBA BARDHAMAN | Central Mechanical | NOAHATI PIPED WATER SUPPLY SCHEME , SM/13452 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
3835 | PURBA BARDHAMAN | Central Mechanical | NOAHATI PIPED WATER SUPPLY SCHEME , SM/13452 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Noahati Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2819/CMD | 04/07/2023 | 30 | M/S. S.R. ENTERPRISE | 29.4 | 24.17 | 100 | 100
3836 | PURBA BARDHAMAN | Burdwan Division | NOAHATI PIPED WATER SUPPLY SCHEME , SM/13452 | New | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1116/BWD | 03/04/2025 | 120 | SOFIQUL ISLAM | 176.89 | 0 | 0 | 0
3837 | PURBA BARDHAMAN | Burdwan Division | NOAHATI PIPED WATER SUPPLY SCHEME , SM/13452 | New | Repairing damaged Pipeline & concrete road by Cement concrete (mix 1:1.5:3) and drainage system, Sluice valve chamber for FHTC work for SATGACHIA ZONE-I, SATGACHIA ZONE-II, SRIDHARPUR, PARHATI, KUCHUT, NOAHATI, MONDALGRAM PWSS and its adjoining mouzas within MEMARI-II BLOCK under Burdwan Division, PHE Dte. | 2715/BWD | 11/07/2024 | 205 | A.R. TRADERS | 74.28 | 3.56 | 8.75 | 100
3838 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PIPLON PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13283 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 6.18 | 0 | 0 | 0
3839 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PIPLON PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13283 | New | Material Requisition To Resource Division | 4310/BWD | 29/09/2023 | 0 | Resource Division | 85.2 | 0 | 0 | 0
3840 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PIPLON PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13283 | New | NEW SERVICE CONNECTION FOR PIPLON PWSS TW -3. | BP-2023-24-640 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.25 | 0 | 0 | 0
3841 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PIPLON PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13283 | New | Quotation for new service connection for Piplon PWSS PH-2. | BP-2024-25-143 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.73 | 0 | 0 | 0
3842 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PIPLON PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13283 | New | NEW SERVICE CONNECTION FOR PIPLON PWSS. | BP-2023-24-563 | 23/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.15 | 0 | 0 | 0
3843 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PIPLON PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13283 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at PIPLON Water Supply Scheme [ Block- MONTESWAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4081/CMD | 29/08/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 44.42 | 0 | 0 | 94
3844 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PIPLON PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13283 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BELENDA, JAMNA, PIPLON & PARGUNA Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | 4388/BWD | 05/10/2023 | 667 | AKASH CONSTRUCTION | 2296.4 | 228.41 | 35.41 | 50
3845 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PIPLON PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13283 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
3846 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME , SM/13495 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7 | 0 | 0 | 0
3847 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME , SM/13495 | New | Material Requisition To Resource Division | 4315/BWD | 29/09/2023 | 0 | Resource Division | 0.83 | 0 | 0 | 0
3848 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME , SM/13495 | New | Material Requisition To Resource Division | 5117/BWD | 23/11/2023 | 0 | Resource Division | 18.94 | 0 | 0 | 0
3849 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME , SM/13495 | New | New service connection charges for Chak Baraspur PWSS TW-1 | BP-2023-24-107 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.19 | 0 | 0 | 0
3850 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME , SM/13495 | New | Beautification of PWSS with Arboriculture, Recharge Pit including shaft and approach footway to Pump-House. Facelifting of masonary works at ANGUNA-BATASPUR (Raina-I Block) P.W.S.S under Burdwan Division, PHE Dte. | 230/RWS | 25/07/2024 | 10 | DAS ENTERPRISE | 0.97 | 0 | 0 | 0
3851 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME , SM/13495 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
3852 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME , SM/13495 | New | Beautification of PWSS with Arboriculture at Chak Bataspur and Recharge Pit including shaft & anciliary works at Head Works site and Repair and colour at 2nd Tubewell site of Kaity (Raina-II Block) P.W.S.S under Burdwan Division, PHE Dte. | 236/RWS | 30/07/2024 | 10 | ANWESHA CONSTRUCTION | 0.97 | 0 | 0 | 0
3853 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME , SM/13495 | New | CHAK BATASPUR Single Village Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | 2115/BWD | 10/05/2023 | 90 | ANWESHA CONSTRUCTION | 63.63 | 63.63 | 100 | 100
3854 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED CHAK BATASPURR SINGLE VILLAGE PIPED WATER SUPPPLY SCHEME , SM/13495 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHAK BATASPUR Water Supply Scheme [ Block-RAINA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2930/CMD | 12/07/2023 | 232 | CONCORD ENGINEERING | 28.98 | 11.46 | 39.54 | 40
3855 | PURBA BARDHAMAN | Burdwan Division | SIGHNALI PIPED WATER SUPPLY SCHEME. , SM/13496 | New | Material Requisition To Resource Division | 3977/BWD | 08/09/2023 | 0 | Resource Division | 38.31 | 0 | 0 | 0
3856 | PURBA BARDHAMAN | Burdwan Division | SIGHNALI PIPED WATER SUPPLY SCHEME. , SM/13496 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 15.55 | 0 | 0 | 0
3857 | PURBA BARDHAMAN | Central Mechanical | SIGHNALI PIPED WATER SUPPLY SCHEME. , SM/13496 | New | New service connection for SIGHNALI PWSS TW 1. | BP-2023-24-519 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.24 | 0 | 0 | 0
3858 | PURBA BARDHAMAN | Central Mechanical | SIGHNALI PIPED WATER SUPPLY SCHEME. , SM/13496 | New | NEW SERVICE CONNECTION FOR SIGHNALI PWSS. | BP-2023-24-571 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.01 | 0 | 0 | 0
3859 | PURBA BARDHAMAN | Burdwan Division | SIGHNALI PIPED WATER SUPPLY SCHEME. , SM/13496 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PASCHIM KHARAMPUR, SHUSHNA & SIGHNALI Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | 3494/BWD | 09/08/2023 | 783 | S.P. CONSTRUCTION | 1925.07 | 362.27 | 61.11 | 80
3860 | PURBA BARDHAMAN | Central Mechanical | SIGHNALI PIPED WATER SUPPLY SCHEME. , SM/13496 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
3861 | PURBA BARDHAMAN | Central Mechanical | SIGHNALI PIPED WATER SUPPLY SCHEME. , SM/13496 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sighnali Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4053/CMD | 29/08/2023 | 611 | ASHIM UDYOG | 27.76 | 0 | 0 | 100
3862 | PURBA BARDHAMAN | Burdwan Division | KARAIL PIPED WATER SUPPLY SCHEME , SM/13498 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 19.71 | 0 | 0 | 0
3863 | PURBA BARDHAMAN | Burdwan Division | KARAIL PIPED WATER SUPPLY SCHEME , SM/13498 | New | Land demarcation and preparation of sketch map for Haldi, Sultanpur, Berugram & Karail Piped W/S. Scheme (New Scheme) at different Blocks under JJM under Burdwan Division, PHE Dte. | 842/AE/HQ | 01/11/2023 | 15 | M/S S. CHOUDHURY | 0.33 | 0 | 0 | 100
3864 | PURBA BARDHAMAN | Burdwan Division | KARAIL PIPED WATER SUPPLY SCHEME , SM/13498 | New | KARAIL Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | 345/BWD | 25/01/2024 | 120 | T.K. BANERJEE & CO. | 59.45 | 5.72 | 9.63 | 30
3865 | PURBA BARDHAMAN | Central Mechanical | KARAIL PIPED WATER SUPPLY SCHEME , SM/13498 | New | Quotation for new service connection at Karail PH-1 PWSS | BP-2024-25-307 | 24/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.51 | 0 | 0 | 0
3866 | PURBA BARDHAMAN | Central Mechanical | KARAIL PIPED WATER SUPPLY SCHEME , SM/13498 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at KARAIL Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4104/CMD | 29/08/2023 | 30 | PADMA ENGINEERING CO. | 20.8 | 0 | 0 | 60
3867 | PURBA BARDHAMAN | Central Mechanical | KARAIL PIPED WATER SUPPLY SCHEME , SM/13498 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 30
3868 | PURBA BARDHAMAN | Burdwan Division | BAGPUR PIPED WATER SUPPLY SCHEME , SM/13323 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.24 | 0 | 0 | 0
3869 | PURBA BARDHAMAN | Burdwan Division | BAGPUR PIPED WATER SUPPLY SCHEME , SM/13323 | New | Material Requisition To Resource Division | 3998/BWD | 08/09/2023 | 0 | Resource Division | 0.83 | 0 | 0 | 0
3870 | PURBA BARDHAMAN | Burdwan Division | BAGPUR PIPED WATER SUPPLY SCHEME , SM/13323 | New | Different types of works in connection with implementation of MIRGAHAR Piped Water Supply Scheme (SM/18365) & BAGPUR PWSS (SM/13323) under Kalna Sub-Division under Burdwan Division, PHE Dte. | 2400/BWD | 26/06/2024 | 120 | M/S S. CHOUDHURY | 301.24 | 0 | 0 | 60
3871 | PURBA BARDHAMAN | Burdwan Division | BAGPUR PIPED WATER SUPPLY SCHEME , SM/13323 | New | Material Requisition To Resource Division | 313/BWD | 24/01/2024 | 0 | Resource Division | 17.19 | 0 | 0 | 0
3872 | PURBA BARDHAMAN | Central Mechanical | BAGPUR PIPED WATER SUPPLY SCHEME , SM/13323 | New | New service connection for BAGPUR PWSS TW-2. | BP-2023-24-499 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.09 | 0 | 0 | 0
3873 | PURBA BARDHAMAN | Central Mechanical | BAGPUR PIPED WATER SUPPLY SCHEME , SM/13323 | New | Quotation for new service connection at Bogpur PWSS PH-1 | BP-2024-25-202 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.2 | 0 | 0 | 0
3874 | PURBA BARDHAMAN | Burdwan Division | BAGPUR PIPED WATER SUPPLY SCHEME , SM/13323 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MANGANPUR & BAGPUR Piped Water Supply Scheme under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3200/BWD | 24/07/2023 | 1100 | M/S GHOSH & CO. | 711.81 | 30.11 | 10.28 | 10
3875 | PURBA BARDHAMAN | Central Mechanical | BAGPUR PIPED WATER SUPPLY SCHEME , SM/13323 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at BAGPUR Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 16/CMD | 03/01/2024 | 30 | BARMAN ROY TRADERS | 21.77 | 0 | 0 | 45
3876 | PURBA BARDHAMAN | Central Mechanical | BAGPUR PIPED WATER SUPPLY SCHEME , SM/13323 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 30
3877 | PURBA BARDHAMAN | Burdwan Division | UCHALAN PIPED WATER SUPPLY SCHEME , SM/13329 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.85 | 0 | 0 | 0
3878 | PURBA BARDHAMAN | Burdwan Division | UCHALAN PIPED WATER SUPPLY SCHEME , SM/13329 | New | Material Requisition To Resource Division | 4002/BWD | 08/09/2023 | 0 | Resource Division | 11.88 | 0 | 0 | 0
3879 | PURBA BARDHAMAN | Burdwan Division | UCHALAN PIPED WATER SUPPLY SCHEME , SM/13329 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 2.75 | 0 | 0 | 0
3880 | PURBA BARDHAMAN | Burdwan Division | UCHALAN PIPED WATER SUPPLY SCHEME , SM/13329 | New | Material Requisition To Resource Division | 5067/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
3881 | PURBA BARDHAMAN | Central Mechanical | UCHALAN PIPED WATER SUPPLY SCHEME , SM/13329 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Uchalan Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4174/CMD | 29/08/2023 | 30 | M/S, S.DAS AND ENTERPRISE. | 29.71 | 12.37 | 41.64 | 50
3882 | PURBA BARDHAMAN | Burdwan Division | UCHALAN PIPED WATER SUPPLY SCHEME , SM/13329 | New | Continuation Work Order supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2023 to 31-01-2024) | 2561/BSD | 30/10/2023 | 66 | MD HASIN | 0.85 | 0 | 0 | 0
3883 | PURBA BARDHAMAN | Central Mechanical | UCHALAN PIPED WATER SUPPLY SCHEME , SM/13329 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
3884 | PURBA BARDHAMAN | Central Mechanical | UCHALAN PIPED WATER SUPPLY SCHEME , SM/13329 | New | New Service connection for Uchalan W/S Scheme PH No.-1 | BP-2023-24-299 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.13 | 0 | 0 | 0
3885 | PURBA BARDHAMAN | Central Mechanical | UCHALAN PIPED WATER SUPPLY SCHEME , SM/13329 | New | New electric connection for Uchalan PWSS, PH-2. | BP-2023-24-341 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.5 | 0 | 0 | 0
3886 | PURBA BARDHAMAN | Burdwan Division | UCHALAN PIPED WATER SUPPLY SCHEME , SM/13329 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-08-2024 to 31-10-2024) | 1500/BSD | 30/07/2024 | 66 | PARVIN BEGAM | 0.85 | 0.21 | 74.23 | 100
3887 | PURBA BARDHAMAN | Burdwan Division | DIGHA PIPED WATER SUPPLY SCHEME , SM/13938 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 55.76 | 0 | 0 | 0
3888 | PURBA BARDHAMAN | Burdwan Division | DIGHA PIPED WATER SUPPLY SCHEME , SM/13938 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.65 | 0 | 0 | 0
3889 | PURBA BARDHAMAN | Burdwan Division | DIGHA PIPED WATER SUPPLY SCHEME , SM/13938 | New | Material Requisition To Resource Division | 4944/BWD | 10/11/2023 | 0 | Resource Division | 34.27 | 0 | 0 | 0
3890 | PURBA BARDHAMAN | Burdwan Division | DIGHA PIPED WATER SUPPLY SCHEME , SM/13938 | New | Material Requisition To Resource Division | 3973/BWD | 08/09/2023 | 0 | Resource Division | 29.28 | 0 | 0 | 0
3891 | PURBA BARDHAMAN | Central Mechanical | DIGHA PIPED WATER SUPPLY SCHEME , SM/13938 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
3892 | PURBA BARDHAMAN | Durgapur W/S Division | DIGHA PIPED WATER SUPPLY SCHEME , SM/13938 | New | Material Requisition To Resource Division | 1724/O/DWSD | 10/12/2024 | 0 | Resource Division | 4.05 | 0 | 0 | 0
3893 | PURBA BARDHAMAN | Central Mechanical | DIGHA PIPED WATER SUPPLY SCHEME , SM/13938 | New | NEW SERVICE CONNECTION FOR DIGHA PWSS PH-1. | BP-2023-24-648 | 20/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.12 | 0 | 0 | 0
3894 | PURBA BARDHAMAN | Central Mechanical | DIGHA PIPED WATER SUPPLY SCHEME , SM/13938 | New | NEW SERVICE CONNECTION FOR DIGHA PWSS | BP-2023-24-554 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.08 | 0 | 0 | 0
3895 | PURBA BARDHAMAN | Burdwan Division | DIGHA PIPED WATER SUPPLY SCHEME , SM/13938 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways at different TW sites for DIGHA Piped Water Supply Scheme under Ausgram-I Block, District:- Purba Bardhaman [NEW SCHEME] | 3454/BWD | 08/08/2023 | 730 | APORUPA CONSTRUCTION | 423.95 | 340.07 | 80.21 | 75
3896 | PURBA BARDHAMAN | Durgapur W/S Division | DIGHA PIPED WATER SUPPLY SCHEME , SM/13938 | New | Formal Work Order for Balance works related sinking of tubewells at GANGARAMPUR village, LDS with Jack Pushing, Rising Main Construction Switchroom and FHTC of DIGHA PWSS of Ausgram-I Block, under Durgapur W/S Division, PHE Dte. | 1573/DWSD | 21/11/2024 | 120 | MANASH GHOSH | 189.93 | 0 | 0 | 95
3897 | PURBA BARDHAMAN | Central Mechanical | GOBARDHANPUR PIPED WATER SUPPLY SCHEME , SM/14445 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at GOBARDHANPUR Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | 4196/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 29.71 | 0 | 0 | 0
3898 | PURBA BARDHAMAN | Burdwan Division | GOBARDHANPUR PIPED WATER SUPPLY SCHEME , SM/14445 | New | Material Requisition To Resource Division | 1965/BWD | 26/04/2023 | 0 | Resource Division | 17.79 | 0 | 0 | 0
3899 | PURBA BARDHAMAN | Burdwan Division | GOBARDHANPUR PIPED WATER SUPPLY SCHEME , SM/14445 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.53 | 0 | 0 | 0
3900 | PURBA BARDHAMAN | Burdwan Division | GOBARDHANPUR PIPED WATER SUPPLY SCHEME , SM/14445 | New | Material Requisition To Resource Division | 5277/BWD | 30/11/2023 | 0 | Resource Division | 20.37 | 0 | 0 | 0
3901 | PURBA BARDHAMAN | Central Mechanical | GOBARDHANPUR PIPED WATER SUPPLY SCHEME , SM/14445 | New | Quotation for new service connection at Gobardhanpur PWSS TW-1 | BP-2024-25-397 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.93 | 0 | 0 | 0
3902 | PURBA BARDHAMAN | Central Mechanical | GOBARDHANPUR PIPED WATER SUPPLY SCHEME , SM/14445 | New | Quotation for new service connection for Gobardhanpur PWSS TW-2. | BP-2024-25-131 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.11 | 0 | 0 | 0
3903 | PURBA BARDHAMAN | Burdwan Division | GOBARDHANPUR PIPED WATER SUPPLY SCHEME , SM/14445 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEULIA, GOBARDHANPUR, KHARIJA-KASHIGRAM & UNIATATARPUR Piped Water Supply Scheme under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | 3491/BWD | 09/08/2023 | 1058 | POWER TOOLS & ENGINEERING | 1741.05 | 0 | 0 | 10
3904 | PURBA BARDHAMAN | Central Mechanical | GOBARDHANPUR PIPED WATER SUPPLY SCHEME , SM/14445 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
3905 | PURBA BARDHAMAN | Burdwan Division | GOBARDHANPUR PIPED WATER SUPPLY SCHEME , SM/14445 | New | Designing, making and erection of Sign Board for SWAJAL GRAM in Taharpur village of Memari-I Block under Gobindapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte(5 nos Board) | 2352/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
3906 | PURBA BARDHAMAN | Burdwan Division | CHHATINI PIPED WATER SUPPLY SCHEME , SM/14017 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 56.53 | 0 | 0 | 0
3907 | PURBA BARDHAMAN | Burdwan Division | CHHATINI PIPED WATER SUPPLY SCHEME , SM/14017 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 19.47 | 0 | 0 | 0
3908 | PURBA BARDHAMAN | Burdwan Division | CHHATINI PIPED WATER SUPPLY SCHEME , SM/14017 | New | Material Requisition To Resource Division | 4928/BWD | 10/11/2023 | 0 | Resource Division | 34.57 | 0 | 0 | 0
3909 | PURBA BARDHAMAN | Central Mechanical | CHHATINI PIPED WATER SUPPLY SCHEME , SM/14017 | New | New service connection charges for Chhatini PWSS TW-1 | BP-2023-24-118 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.96 | 0 | 0 | 0
3910 | PURBA BARDHAMAN | Central Mechanical | CHHATINI PIPED WATER SUPPLY SCHEME , SM/14017 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
3911 | PURBA BARDHAMAN | Central Mechanical | CHHATINI PIPED WATER SUPPLY SCHEME , SM/14017 | New | New Service connection at CHHATINI PWSS TW-2. | BP-2023-24-480 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.24 | 0 | 0 | 0
3912 | PURBA BARDHAMAN | Burdwan Division | CHHATINI PIPED WATER SUPPLY SCHEME , SM/14017 | New | CHHATINI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | 2216/BWD | 15/05/2023 | 687 | SHWET BARANI | 539.35 | 124.11 | 23.01 | 55
3913 | PURBA BARDHAMAN | Central Mechanical | CHHATINI PIPED WATER SUPPLY SCHEME , SM/14017 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chhatini Water Supply Scheme [ Block- Bhatar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3069/CMD | 21/07/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 27.79 | 0 | 0 | 60
3914 | PURBA BARDHAMAN | Burdwan Division | CHHATINI PIPED WATER SUPPLY SCHEME , SM/14017 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day [Period February'2024 to April'2024] | 91/DSD | 31/01/2024 | 78 | MD HASIN | 1 | 0.29 | 88.46 | 0
3915 | PURBA BARDHAMAN | Burdwan Division | CHHATINI PIPED WATER SUPPLY SCHEME , SM/14017 | New | Providing Functional Household Tap Connection (FHTC) by sinking of tube well 250 x 150 mm. dia., Constn. of Pump House & Boundary Wall within command area of CHHATINI W/S. Scheme, Bhatar Block under Burdwan Division, PHE. Dte. | 3033/BWD | 06/08/2024 | 120 | SAHA CONSTRUCTION & CO. | 129.06 | 0 | 0 | 50
3916 | PURBA BARDHAMAN | Burdwan Division | CHHATINI PIPED WATER SUPPLY SCHEME , SM/14017 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period May'2024 to July'2024] | 369/DSD | 30/04/2024 | 78 | MD HASIN | 1 | 0.33 | 100 | 0
3917 | PURBA BARDHAMAN | Burdwan Division | MULGRAM PIPED WATER SUPPLY SCHEME , SM/14058 | New | Material Requisition To Resource Division | 1630/BWD | 06/04/2023 | 0 | Resource Division | 1.65 | 0 | 0 | 0
3918 | PURBA BARDHAMAN | Burdwan Division | MULGRAM PIPED WATER SUPPLY SCHEME , SM/14058 | New | Material Requisition To Resource Division | 1236/BWD | 17/03/2023 | 0 | Resource Division | 13.55 | 0 | 0 | 0
3919 | PURBA BARDHAMAN | Burdwan Division | MULGRAM PIPED WATER SUPPLY SCHEME , SM/14058 | New | Material Requisition To Resource Division | 5092/BWD | 23/11/2023 | 0 | Resource Division | 24.47 | 0 | 0 | 0
3920 | PURBA BARDHAMAN | Central Mechanical | MULGRAM PIPED WATER SUPPLY SCHEME , SM/14058 | New | New service connection charges for Mulgram W/S Scheme TW-1 | BP-2023-24-37 | 27/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.76 | 0 | 0 | 0
3921 | PURBA BARDHAMAN | Central Mechanical | MULGRAM PIPED WATER SUPPLY SCHEME , SM/14058 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
3922 | PURBA BARDHAMAN | Central Mechanical | MULGRAM PIPED WATER SUPPLY SCHEME , SM/14058 | New | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3106/CMD | 11/12/2024 | 60 | S.K. ELECTRICALS | 13.6 | 0 | 0 | 0
3923 | PURBA BARDHAMAN | Central Mechanical | MULGRAM PIPED WATER SUPPLY SCHEME , SM/14058 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Mulgram Water Supply Scheme [ Block- KATWA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2511/CMD | 02/06/2023 | 30 | M/S. S.R. ENTERPRISE | 28.96 | 22.84 | 95.46 | 40
3924 | PURBA BARDHAMAN | Central Mechanical | MULGRAM PIPED WATER SUPPLY SCHEME , SM/14058 | New | New service connection charges for Mulgram PWSS TW-2 | BP-2023-24-273 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.26 | 0 | 0 | 0
3925 | PURBA BARDHAMAN | Burdwan Division | SARANGA PIPED WATER SUPPLY SCHEME , SM/14078 | New | Material Requisition To Resource Division | 1965/BWD | 26/04/2023 | 0 | Resource Division | 7.15 | 0 | 0 | 0
3926 | PURBA BARDHAMAN | Burdwan Division | SARANGA PIPED WATER SUPPLY SCHEME , SM/14078 | New | Material Requisition To Resource Division | 5235/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
3927 | PURBA BARDHAMAN | Burdwan Division | SARANGA PIPED WATER SUPPLY SCHEME , SM/14078 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 5.01 | 0 | 0 | 0
3928 | PURBA BARDHAMAN | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME , SM/14078 | New | New service connection charges for Saranga PWSS TW-2 | BP-2023-24-87 | 26/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.97 | 0 | 0 | 0
3929 | PURBA BARDHAMAN | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME , SM/14078 | New | New service connection charges for Saranga PWSS TW-1 | BP-2023-24-94 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.5 | 0 | 0 | 0
3930 | PURBA BARDHAMAN | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME , SM/14078 | New | Continuation order-Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven ) for supervision of site for the office of the Assistant Engineer,under CMD,PHE,Dte. [W.e.f-01/03/2024 to 29/04/2024) | 359/CMSD | 27/02/2024 | 60 | SUBRATA BHADRA | 0.79 | 0.79 | 99.81 | 100
3931 | PURBA BARDHAMAN | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME , SM/14078 | New | Supply & delivery of submersible pumping machinery (for urgent FHTC) for Tube well no.-1 at Saranga w/s scheme, (Block -Khandaghosh) under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1075/CMSD | 15/12/2023 | 12 | SUBHRA ENTERPRISE | 0.67 | 0.67 | 100 | 100
3932 | PURBA BARDHAMAN | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME , SM/14078 | New | Supply & delivery of different electro-mechanical accessories (for urgent FHTC) for Tube well no.-1 at Saranga w/s scheme, ( Block -Khandaghosh) under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1073/CMSD | 15/12/2023 | 10 | SUBHRA ENTERPRISE | 0.8 | 0.77 | 100 | 100
3933 | PURBA BARDHAMAN | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME , SM/14078 | New | Emergency Installation (for urgent FHTC) of departmental supply submersible pumping machinery with supply main switch, cable, starter etc. for Tube well no.-1 at Saranga w/s scheme, ( Block -Khandaghosh) under CMD, PHE Dte., Dist.- Purba-Bardhaman | 06/CMSD | 02/01/2024 | 10 | SUBHRA ENTERPRISE | 0.72 | 0.68 | 100 | 100
3934 | PURBA BARDHAMAN | Burdwan Division | SARANGA PIPED WATER SUPPLY SCHEME , SM/14078 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SARANGA & KAMALPUR Piped Water Supply Scheme under Khandaghosh Block, District:- Purba Bardhaman [NEW SCHEME] | 2078/BWD | 04/05/2023 | 698 | KHAN ENTERPRISE | 820.73 | 249.61 | 78.67 | 42
3935 | PURBA BARDHAMAN | Burdwan Division | SARANGA PIPED WATER SUPPLY SCHEME , SM/14078 | New | Balance work for providing Functional Household Tap Connection (FHTC) within command area SARANGA W/S. Scheme of Khandaghosh Block under Burdwan Divn., PHE. Dte. | 431/BWD | 20/01/2025 | 120 | ANWESHA CONSTRUCTION | 98.39 | 0 | 0 | 0
3936 | PURBA BARDHAMAN | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME , SM/14078 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
3937 | PURBA BARDHAMAN | Central Mechanical | SARANGA PIPED WATER SUPPLY SCHEME , SM/14078 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Saranga Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2854/CMD | 05/07/2023 | 30 | ORIENTAL ENGINEERING CO. | 28.97 | 22.55 | 95.41 | 100
3938 | PURBA BARDHAMAN | Burdwan Division | BARA KULGACHHI PIPED WATER SUPPLY SCHEME , SM/14079 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 20.38 | 0 | 0 | 0
3939 | PURBA BARDHAMAN | Burdwan Division | BARA KULGACHHI PIPED WATER SUPPLY SCHEME , SM/14079 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 9.61 | 0 | 0 | 0
3940 | PURBA BARDHAMAN | Central Mechanical | BARA KULGACHHI PIPED WATER SUPPLY SCHEME , SM/14079 | New | New service connection charges for Barakulgachi PWSS TW-2 | BP-2023-24-108 | 09/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.73 | 0 | 0 | 0
3941 | PURBA BARDHAMAN | Central Mechanical | BARA KULGACHHI PIPED WATER SUPPLY SCHEME , SM/14079 | New | New service connection charges for Bara Kulgachi PWSS TW-1 | BP-2023-24-131 | 22/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.92 | 0 | 0 | 0
3942 | PURBA BARDHAMAN | Burdwan Division | BARA KULGACHHI PIPED WATER SUPPLY SCHEME , SM/14079 | New | BARA KULGACHHI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -II Block, District:- Purba-Bardhaman [NEW SCHEME] | 775/BWD | 24/02/2023 | 1253 | MANASH GHOSH | 557.58 | 468.82 | 84.08 | 73
3943 | PURBA BARDHAMAN | Central Mechanical | BARA KULGACHHI PIPED WATER SUPPLY SCHEME , SM/14079 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
3944 | PURBA BARDHAMAN | Central Mechanical | BARA KULGACHHI PIPED WATER SUPPLY SCHEME , SM/14079 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BARAKULGACHHI Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3173/CMD | 26/07/2023 | 30 | GOENKA ENTERPRISE | 28.98 | 22.7 | 95.44 | 90
3945 | PURBA BARDHAMAN | Burdwan Division | BARA KULGACHHI PIPED WATER SUPPLY SCHEME , SM/14079 | New | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | 907/BWD | 04/03/2024 | 30 | MANASH GHOSH | 23.87 | 3.83 | 100 | 100
3946 | PURBA BARDHAMAN | Burdwan Division | BARA KULGACHHI PIPED WATER SUPPLY SCHEME , SM/14079 | New | Material Requisition To Resource Division | 331/BWD | 24/01/2024 | 0 | Resource Division | 16.79 | 0 | 0 | 0
3947 | PURBA BARDHAMAN | Burdwan Division | BARA KULGACHHI PIPED WATER SUPPLY SCHEME , SM/14079 | New | Road crossing through metal/Concrete road by Jack Push Method for Barakulgachhi PWSS(SM/14079) of Katwa-II Block Development Block under Katwa Sub-Division within Burdwan Division PHE Dte. | 1297/BWD | 25/04/2025 | 30 | MONDAL & CO. | 43.65 | 0 | 0 | 100
3948 | PURBA BARDHAMAN | Burdwan Division | BARA KULGACHHI PIPED WATER SUPPLY SCHEME , SM/14079 | New | Providing of balance FHTC and other allied works at Barakulgachhi, Chhoto Kulgachhi and Garagachha under the command area of BARAKULGACHI PWSS (SM/14079) in order to declare Sajal Gram, under Katwa-II Block under Katwa Sub-Division, PHE Dte. | 982/BWD | 13/03/2025 | 172 | MANASH GHOSH | 9.51 | 0 | 0 | 100
3949 | PURBA BARDHAMAN | Burdwan Division | PICHKURI PIPED WATER SUPPLY SCHEME , SM/13330 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 25.71 | 0 | 0 | 0
3950 | PURBA BARDHAMAN | Burdwan Division | PICHKURI PIPED WATER SUPPLY SCHEME , SM/13330 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.16 | 0 | 0 | 0
3951 | PURBA BARDHAMAN | Burdwan Division | PICHKURI PIPED WATER SUPPLY SCHEME , SM/13330 | New | Material Requisition To Resource Division | 4908/BWD | 10/11/2023 | 0 | Resource Division | 12.03 | 0 | 0 | 0
3952 | PURBA BARDHAMAN | Central Mechanical | PICHKURI PIPED WATER SUPPLY SCHEME , SM/13330 | New | New service connection charges for Pichkuri PWSS TW-1 | BP-2023-24-64 | 18/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.96 | 0 | 0 | 0
3953 | PURBA BARDHAMAN | Central Mechanical | PICHKURI PIPED WATER SUPPLY SCHEME , SM/13330 | New | New service connection charges for Pichkuri PWSS TW-2 | BP-2023-24-65 | 18/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.26 | 0 | 0 | 0
3954 | PURBA BARDHAMAN | Burdwan Division | PICHKURI PIPED WATER SUPPLY SCHEME , SM/13330 | New | Continuation order for Supply of 01(one) No. Diesel Driven Motor Cab (Bharat Stage-II) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Division (Burdwan North) P.H.E. Dte. Govt. of West Bengal (for the period of 01/01/2024 to 31/05/2024) | 995/DSD | 29/12/2023 | 183 | SUJAUDDIN SEKH | 2 | 0.23 | 58.35 | 60
3955 | PURBA BARDHAMAN | Burdwan Division | PICHKURI PIPED WATER SUPPLY SCHEME , SM/13330 | New | Continuation work order for supply of 01 (one) No. Diesel driven Motor Cab (Bharat Stage-III) on hire basis for the office of the Assistant Engineer, Durgapur Sub-Divison(Burdwan North), P.H.E. DTE. Govt. of West Bengal (for the period of 01/06/2024 to 31/07/2024) | 411/DSD | 28/05/2024 | 61 | SUJAUDDIN SEKH | 0.8 | 0.76 | 189.09 | 0
3956 | PURBA BARDHAMAN | Central Mechanical | PICHKURI PIPED WATER SUPPLY SCHEME , SM/13330 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
3957 | PURBA BARDHAMAN | Central Mechanical | PICHKURI PIPED WATER SUPPLY SCHEME , SM/13330 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Pichkuri Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2886/CMD | 10/07/2023 | 30 | CHATTERJEE ENTERPRISE | 27.75 | 22.16 | 100 | 98
3958 | PURBA BARDHAMAN | Burdwan Division | PICHKURI PIPED WATER SUPPLY SCHEME , SM/13330 | New | PICHKURI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ausgram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 1985/BWD | 27/04/2023 | 980 | BANSBERIA CONSTRUCTION CO. | 445.01 | 307.65 | 69.13 | 95
3959 | PURBA BARDHAMAN | Durgapur W/S Division | PICHKURI PIPED WATER SUPPLY SCHEME , SM/13330 | New | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 0 | 1
3960 | PURBA BARDHAMAN | Burdwan Division | Samanti Piped Water Supply Scheme , SM/13319 | New | Supply & delivery of different dia. MJ Coller for FHTC as well as smooth running of different W/S. Schemes under Burdwan Division, P.H.E. Dte. [i.e. (1) Magra PWSS, Memari-I Block, (2) Kuchut PWSS, Memari - II Block, (3) Khundkuri PWSS, Khandaghosh Block & (4) Samanti PWSS, Burdwan - II Block)] | 4076/BWD | 13/09/2023 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 20.63 | 5 | 100 | 100
3961 | PURBA BARDHAMAN | Burdwan Division | Samanti Piped Water Supply Scheme , SM/13319 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 10.45 | 0 | 0 | 0
3962 | PURBA BARDHAMAN | Burdwan Division | Samanti Piped Water Supply Scheme , SM/13319 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 23.19 | 0 | 0 | 0
3963 | PURBA BARDHAMAN | Burdwan Division | Samanti Piped Water Supply Scheme , SM/13319 | New | Material Requisition To Resource Division | 5237/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
3964 | PURBA BARDHAMAN | Central Mechanical | Samanti Piped Water Supply Scheme , SM/13319 | New | New service connection charges for Samanti PWSS TW-1 | BP-2023-24-112 | 10/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.1 | 0 | 0 | 0
3965 | PURBA BARDHAMAN | Central Mechanical | Samanti Piped Water Supply Scheme , SM/13319 | New | New service connection for Samanti W/S scheme TW No-2 | BP-2023-24-411 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.6 | 0 | 0 | 0
3966 | PURBA BARDHAMAN | Burdwan Division | Samanti Piped Water Supply Scheme , SM/13319 | New | Restoration of hard shouldering and flank damaged during laying of PHE pipeline at Samanti village road from 0.00 Kmp to 3.00 Kmp within Samanti PWSS. | 226/JJM | 14/05/2024 | 0 | EXECUTIVE ENGINEER-I, BURDWAN DIVISION, P.W.D. | 5.08 | 0 | 0 | 0
3967 | PURBA BARDHAMAN | Burdwan Division | Samanti Piped Water Supply Scheme , SM/13319 | New | SAMANTI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under BARDHAMAN-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 1536/BWD | 29/03/2023 | 1008 | G.B. CONSTRUCTION & CO. | 504.69 | 304.41 | 60.32 | 36
3968 | PURBA BARDHAMAN | Central Mechanical | Samanti Piped Water Supply Scheme , SM/13319 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 0 | 12
3969 | PURBA BARDHAMAN | Central Mechanical | Samanti Piped Water Supply Scheme , SM/13319 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Samanti Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2979/CMD | 18/07/2023 | 30 | MS DAS ELECTRIC CO | 28.98 | 22.86 | 95.35 | 95
3970 | PURBA BARDHAMAN | Burdwan Division | SAR PIPED WATER SUPPLY SCHEME , SM/14929 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 11.55 | 0 | 0 | 0
3971 | PURBA BARDHAMAN | Burdwan Division | SAR PIPED WATER SUPPLY SCHEME , SM/14929 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.41 | 0 | 0 | 0
3972 | PURBA BARDHAMAN | Burdwan Division | SAR PIPED WATER SUPPLY SCHEME , SM/14929 | New | Material Requisition To Resource Division | 5241/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0 | 0
3973 | PURBA BARDHAMAN | Central Mechanical | SAR PIPED WATER SUPPLY SCHEME , SM/14929 | New | New service connection charges for Sar PWSS TW-2 | BP-2023-24-162 | 18/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.45 | 0 | 0 | 0
3974 | PURBA BARDHAMAN | Central Mechanical | SAR PIPED WATER SUPPLY SCHEME , SM/14929 | New | New service connection charges for Sar PWSS TW-1 | BP-2023-24-163 | 18/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.8 | 0 | 0 | 0
3975 | PURBA BARDHAMAN | Durgapur W/S Division | SAR PIPED WATER SUPPLY SCHEME , SM/14929 | New | Acceptance cum Formal Work Order for Road Restoration ,Land development with access road & allied works for Augmentation of SAR PWSS , Ausgram-II Block under Durgapur Water Supply Division, PHE Dte. | 1616/DWSD | 26/11/2024 | 90 | SAIKAT RAY | 10.77 | 0 | 0 | 0
3976 | PURBA BARDHAMAN | Burdwan Division | SAR PIPED WATER SUPPLY SCHEME , SM/14929 | New | SAR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 2231/BWD | 16/05/2023 | 365 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 193.73 | 196.53 | 100 | 100
3977 | PURBA BARDHAMAN | Durgapur W/S Division | SAR PIPED WATER SUPPLY SCHEME , SM/14929 | New | Material Requisition To Resource Division | 1724/K/DWSD | 10/12/2024 | 0 | Resource Division | 0.55 | 0 | 0 | 0
3978 | PURBA BARDHAMAN | Durgapur W/S Division | SAR PIPED WATER SUPPLY SCHEME , SM/14929 | New | Acceptance cum Formal Work Order for SATINANDI Piped Water Supply Scheme with INSTALLATION OF BARBED WIRE, FHTC ,Road restoration ,DEMOLITION WORK & land development with road at TW site under Galsi-II Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte. | 1620/DWSD | 26/11/2024 | 326 | A K SIKDAR | 79.05 | 0 | 0 | 70
3979 | PURBA BARDHAMAN | Central Mechanical | SAR PIPED WATER SUPPLY SCHEME , SM/14929 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sar Water Supply Scheme [ Block-Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3924/CMD | 22/08/2023 | 30 | D.K. ELECTRIC | 27.75 | 21.57 | 95.21 | 98
3980 | PURBA BARDHAMAN | Durgapur W/S Division | SAR PIPED WATER SUPPLY SCHEME , SM/14929 | New | Acceptance cum Formal Work for Additional work for SAR (SAR Canalpar, Adibasipara) Piped Water Supply Scheme with LDS & FHTC under ausgram-II Block, Dist- Purba Bardhaman (New Scheme) under Durgapur W/S Division, PHE Dte. | 1384/DWSD | 26/09/2024 | 45 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 16.59 | 3.68 | 20.94 | 100
3981 | PURBA BARDHAMAN | Burdwan Division | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14909 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 6.74 | 0 | 0 | 0
3982 | PURBA BARDHAMAN | Burdwan Division | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14909 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.32 | 0 | 0 | 0
3983 | PURBA BARDHAMAN | Burdwan Division | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14909 | New | Material Requisition To Resource Division | 4890/BWD | 10/11/2023 | 0 | Resource Division | 10.17 | 0 | 0 | 0
3984 | PURBA BARDHAMAN | Central Mechanical | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14909 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
3985 | PURBA BARDHAMAN | Central Mechanical | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14909 | New | Quotation for new service connection for Ramchandrapur Zone-2 PWSS PH 1. | BP-2024-25-117 | 28/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.39 | 0 | 0 | 0
3986 | PURBA BARDHAMAN | Central Mechanical | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14909 | New | NEW SERVICE CONNECTION FOR RAMCHANDRAPUR ZONE - I PWSS | BP-2023-24-551 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.15 | 0 | 0 | 0
3987 | PURBA BARDHAMAN | Central Mechanical | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14909 | New | Quotation for new service connection for Ramchandarapur Zone-2 PWSS PH 2. | BP-2024-25-118 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.35 | 0 | 0 | 0
3988 | PURBA BARDHAMAN | Central Mechanical | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14909 | New | Quotation for new service connection at Ramchandrapur Zone-1 PWSS PH-2 | BP-2024-25-205 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.44 | 0 | 0 | 0
3989 | PURBA BARDHAMAN | Burdwan Division | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14909 | New | RAMCHANDRAPUR (ZONE-I & II ) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Bhatar Block, District:- Purba-Bardhaman [NEW SCHEME] | 3703/BWD | 24/08/2023 | 677 | SUPRITI ENTERPRISE | 582.13 | 0 | 0 | 60
3990 | PURBA BARDHAMAN | Central Mechanical | RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14909 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2, 3 & 4 at RAMCHANDRAPUR Water Supply Scheme [ Block- BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4183/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 56.97 | 30.58 | 53.68 | 40
3991 | PURBA BARDHAMAN | Burdwan Division | SHYAMPUR PIPE WATER SUPPLY SCHEME , SM/15585 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 14.98 | 0 | 0 | 0
3992 | PURBA BARDHAMAN | Burdwan Division | SHYAMPUR PIPE WATER SUPPLY SCHEME , SM/15585 | New | Material Requisition To Resource Division | 4300/BWD | 29/09/2023 | 0 | Resource Division | 0.58 | 0 | 0 | 0
3993 | PURBA BARDHAMAN | Burdwan Division | SHYAMPUR PIPE WATER SUPPLY SCHEME , SM/15585 | New | Material Requisition To Resource Division | 4946/BWD | 10/11/2023 | 0 | Resource Division | 9.76 | 0 | 0 | 0
3994 | PURBA BARDHAMAN | Burdwan Division | SHYAMPUR PIPE WATER SUPPLY SCHEME , SM/15585 | New | CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR SHYAMPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE. | 1016/KSD | 07/08/2024 | 15 | DEL DELTA CONSTRUCTION | 0.66 | 0.66 | 100 | 100
3995 | PURBA BARDHAMAN | Central Mechanical | SHYAMPUR PIPE WATER SUPPLY SCHEME , SM/15585 | New | Quotation for new service connection at Shyampur PWSS PH-2. | BP-2024-25-250 | 01/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.61 | 0 | 0 | 0
3996 | PURBA BARDHAMAN | Central Mechanical | SHYAMPUR PIPE WATER SUPPLY SCHEME , SM/15585 | New | Quotation for new service connection at Shyampur PWSS PH 1. | BP-2024-25-352 | 05/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.57 | 0 | 0 | 0
3997 | PURBA BARDHAMAN | Burdwan Division | SHYAMPUR PIPE WATER SUPPLY SCHEME , SM/15585 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMPUR, GAHAK & SHANKRA Piped Water Supply Scheme under Purbasthali I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3957/BWD | 07/09/2023 | 1051 | M/S B. NANDI | 758.52 | 146.35 | 53.43 | 20
3998 | PURBA BARDHAMAN | Central Mechanical | SHYAMPUR PIPE WATER SUPPLY SCHEME , SM/15585 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
3999 | PURBA BARDHAMAN | Central Mechanical | SHYAMPUR PIPE WATER SUPPLY SCHEME , SM/15585 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at SHYAMPUR [PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4151/CMD | 29/08/2023 | 581 | DUTTA ENTERPRISE | 20.8 | 0 | 0 | 100
4000 | PURBA BARDHAMAN | Burdwan Division | ANGARSON PIPED WATER SUPPLY SCHEME , SM/15587 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 42.44 | 0 | 0 | 0
4001 | PURBA BARDHAMAN | Burdwan Division | ANGARSON PIPED WATER SUPPLY SCHEME , SM/15587 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.32 | 0 | 0 | 0
4002 | PURBA BARDHAMAN | Burdwan Division | ANGARSON PIPED WATER SUPPLY SCHEME , SM/15587 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR ANGERSON PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 2105/KSD | 04/03/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.66 | 100 | 2
4003 | PURBA BARDHAMAN | Central Mechanical | ANGARSON PIPED WATER SUPPLY SCHEME , SM/15587 | New | New electric connection for Angarson PWSS, PH-1. | BP-2023-24-349 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.47 | 0 | 0 | 0
4004 | PURBA BARDHAMAN | Central Mechanical | ANGARSON PIPED WATER SUPPLY SCHEME , SM/15587 | New | New service connection charges for Angarson PWSS TW-2 | BP-2023-24-350 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.07 | 0 | 0 | 0
4005 | PURBA BARDHAMAN | Central Mechanical | ANGARSON PIPED WATER SUPPLY SCHEME , SM/15587 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
4006 | PURBA BARDHAMAN | Burdwan Division | ANGARSON PIPED WATER SUPPLY SCHEME , SM/15587 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
4007 | PURBA BARDHAMAN | Central Mechanical | ANGARSON PIPED WATER SUPPLY SCHEME , SM/15587 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at ANGARSON Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4157/CMD | 29/08/2023 | 640 | S.K. ELECTRICALS | 27.77 | 5.69 | 20.13 | 95
4008 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR TEANDUL , SM/16489 | Retrofitting | Construction of Path Way, Drain, Repairing of Pump House at 2nd TW Site and Providing leftout FHTC, Road Restoration with allied work for TENDUL Piped Water Supply Scheme, Block- Raina-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | 4375/BWD | 13/12/2024 | 90 | DEY NIRMAN | 12.69 | 0 | 0 | 0
4009 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR TEANDUL , SM/16489 | Retrofitting | Construction of Boundary wall at Head Works Site of TEANDUL Water Supply Scheme under RAINA I Block of Burdwan Division, PHE Dte. (Length -151.00 Mtr, Col - 48 Nos). | 1727/BWD | 13/04/2023 | 60 | HI-LIGHT ELECTRONICS | 21.94 | 21.93 | 100 | 100
4010 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR TEANDUL , SM/16489 | Retrofitting | Laying of Parallel Pipeline from Distribution line near Head Work site to Sonadanga to improve water demand at Madubon, Sultanbad & Dhomas village by direct water supply of TENDUL Piped Water Supply Scheme, Raina-I Block under Burdwan Sub Division under Burdwan Division PHE Dte. | 1117/BWD | 14/03/2024 | 124 | ANWESHA CONSTRUCTION | 11.7 | 6.02 | 79.13 | 100
4011 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME , SM/15152 | Augmentation | Sinking of 300 X 200mm dia Tube Well 200 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of AGRADWIP and its adjoining mouzas Piped Water Supply Scheme, Block Katwa II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 604/BWD | 17/02/2023 | 30 | AUXILIARY TUBE WELL DRILLERS | 12.77 | 9.45 | 100 | 100
4012 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME , SM/15152 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Agradip Kashipur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2579/CMD | 07/06/2023 | 486 | MITRA ENTERPRISE | 10.99 | 0 | 0 | 100
4013 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME , SM/15152 | Augmentation | Installation of deptt.supplied Pump·motor set and other allied works at PH-1 of Aug. of Agradip Kashipur water supply scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 513/DIC/BMSD(D) | 20/08/2024 | 7 | MITRA ENTERPRISE | 0.33 | 0 | 0 | 100
4014 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME , SM/15152 | Augmentation | NEW SERVICE CONNECTION FOR AGRADIP KASHIPUR PWSS PH 1 | BP-2023-24-637 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.92 | 0 | 0 | 0
4015 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME , SM/15152 | Augmentation | Augmentation of AGRADWIP Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA-II Block, District:- Purba-Bardhaman._2ND CALL | 3778/BWD | 29/08/2023 | 1221 | MOTHER INFRASTRUCTURE | 420.6 | 327.93 | 77.97 | 86
4016 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME , SM/15152 | Augmentation | Construction of Pump House, Boundary walls and Raising Main for Aug. of AGRADWIP Piped W/S. Scheme under Katwa-II Block, District:- Purba-Bardhaman. | 5485/BWD | 13/12/2023 | 391 | JAMALUDDIN SK | 9.75 | 0 | 0 | 80
4017 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME , SM/15152 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 2 at Augumentation of Agradip Kashipur (Babladanga) Water Supply Scheme [BLOCK- Katwa-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2445/CMD | 07/08/2024 | 300 | SUBRATA BHADRA | 11.63 | 0 | 0 | 91
4018 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF AGRADWIP KASHIPUR PIPED WATER SUPPLY SCHEME , SM/15152 | Augmentation | Construction of Pump House cum switch room (5.40 m x 3.60 m) with sanitary arrangement [As per Drawing No. : PHE/SE/CC/PH/DWG-01/2022-23] for additional TW. No - I (Babladanga) under AGRADWIP PWSS (SM/15152) of Katwa-II Block under Katwa Sub-Division PHE Dte. | 1229/BWD | 22/04/2025 | 60 | JAMALUDDIN SK | 6.79 | 0 | 0 | 100
4019 | PURBA BARDHAMAN | Central Drilling | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Murgram W/S Scheme (T/W-I & II) , Ketugram-I Block under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | 1345/CDD | 13/09/2023 | 30 | OSMAN SEKH | 16.61 | 0 | 0 | 0
4020 | PURBA BARDHAMAN | Burdwan Division | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.38 | 0 | 0 | 0
4021 | PURBA BARDHAMAN | Burdwan Division | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 18.01 | 0 | 0 | 0
4022 | PURBA BARDHAMAN | Burdwan Division | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | Material Requisition To Resource Division | 5260/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0 | 0
4023 | PURBA BARDHAMAN | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MURGRAM Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4122/CMD | 29/08/2023 | 30 | S.K. ELECTRICALS | 27.77 | 19.55 | 70.38 | 46
4024 | PURBA BARDHAMAN | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
4025 | PURBA BARDHAMAN | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | Supply & Delivery of 3 Phase actuator operated wafer type butterfly valve for Tube well No.- 1 at MURGRAM Water Supply Scheme [Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 348/DIC/BMSD(D) | 22/12/2023 | 7 | SUBRATA BHADRA | 0.98 | 0 | 0 | 0
4026 | PURBA BARDHAMAN | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | Supply & delivery of Submersible Pumping Machinery, Suspension clamp and tube well cover etc. Tube well No.- 1 at MURGRAM Water Supply Scheme [ Block· KETUGRAM -1] under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | 25/DIC/BMSD(D) | 05/01/2024 | 7 | SUBRATA BHADRA | 0.86 | 0.86 | 100 | 100
4027 | PURBA BARDHAMAN | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | Supply & delivery of valves, starter and Installation of Submersible Pumping Machinery for Tube well No. - 1 at MURGRAM Water Supply Scheme [ Block- KETUGRAM -1] under CMD, PHE Dte., Dist.· Purba Bardhaman. | 48/DIC/BMSD(D) | 19/01/2024 | 15 | SUBRATA BHADRA | 0.69 | 0.59 | 100 | 100
4028 | PURBA BARDHAMAN | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | Supply & Delivery of Submersible cable and column pipes for Tube Well No No:-1 at MURGRAM water supply scheme[ Block - KETUGRAM -1] under CMD, PHE Dte,. Dist.- Purba-Bardhaman. | 41/DIC/BMSD(D) | 15/01/2024 | 7 | SUBRATA BHADRA | 0.87 | 0.87 | 100 | 100
4029 | PURBA BARDHAMAN | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | Quotation for new service connection at Murgram W/S Scheme PH-II. | BP-2023-24-314 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.25 | 0 | 0 | 0
4030 | PURBA BARDHAMAN | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | Quotation for new service connection at Murgram W/S Scheme PH-I. | BP-2023-24-313 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.21 | 0 | 0 | 0
4031 | PURBA BARDHAMAN | Central Mechanical | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | NEW SERVICE CONNECTION FOR MURGRAM PWSS PH-I. | BP-2024-25-44 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.64 | 0 | 0 | 0
4032 | PURBA BARDHAMAN | Burdwan Division | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to MALGRAM, MURGRAM, MORGRAM & KHANJI Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3387/BWD | 03/08/2023 | 882 | PUSPA ENTERPRISE | 1333.98 | 221.92 | 79.3 | 40
4033 | PURBA BARDHAMAN | Burdwan Division | MURGRAM PIPED WATER SUPPLY SCHEME , SM/15156 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Murgram, Moregram, Malgram, Khanji, PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2739/BWD | 12/07/2024 | 173 | PUSPA ENTERPRISE | 185.75 | 24.12 | 51.93 | 72
4034 | PURBA BARDHAMAN | Burdwan Division | Pipuldaha Piped Water Supply Scheme , SM/15488 | New | Material Requisition To Resource Division | 3865/BWD | 01/09/2023 | 0 | Resource Division | 20.78 | 0 | 0 | 0
4035 | PURBA BARDHAMAN | Burdwan Division | Pipuldaha Piped Water Supply Scheme , SM/15488 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 3.55 | 0 | 0 | 0
4036 | PURBA BARDHAMAN | Burdwan Division | Pipuldaha Piped Water Supply Scheme , SM/15488 | New | Material Requisition To Resource Division | 5078/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
4037 | PURBA BARDHAMAN | Central Mechanical | Pipuldaha Piped Water Supply Scheme , SM/15488 | New | Continuation Order- Hiring of inspection vehicle (Diesel /CNG/LPG Driven) for supervision of site for the office of Assistant Engineer under CMD,PHE,Dte. [W.E.F-30.04.2024 to 28.06.2024 ] | 703/CMSD | 29/04/2024 | 60 | SUBRATA BHADRA | 0.79 | 0 | 0 | 0
4038 | PURBA BARDHAMAN | Burdwan Division | Pipuldaha Piped Water Supply Scheme , SM/15488 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-06-2024 to 31-08-2024" | 918/BSD | 28/05/2024 | 92 | SK. ASFIA | 1.2 | 0.4 | 99.59 | 60
4039 | PURBA BARDHAMAN | Central Mechanical | Pipuldaha Piped Water Supply Scheme , SM/15488 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
4040 | PURBA BARDHAMAN | Central Mechanical | Pipuldaha Piped Water Supply Scheme , SM/15488 | New | New electric connection for Pipuldaha PWSS. | BP-2023-24-346 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.54 | 0 | 0 | 0
4041 | PURBA BARDHAMAN | Central Mechanical | Pipuldaha Piped Water Supply Scheme , SM/15488 | New | New electric connection for Pipuldaha PWSS, PH-1. | BP-2023-24-345 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.76 | 0 | 0 | 0
4042 | PURBA BARDHAMAN | Burdwan Division | Pipuldaha Piped Water Supply Scheme , SM/15488 | New | PIPULDAHA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3440/BWD | 08/08/2023 | 1058 | SK ABDUL HALIM | 644.77 | 289.73 | 44.94 | 97
4043 | PURBA BARDHAMAN | Burdwan Division | Pipuldaha Piped Water Supply Scheme , SM/15488 | New | Continuation Work Order for supply of inspection Vehicle for inspection of different JJM related (schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-11-2024 to 31-01-2025) | 2438/BSD | 29/10/2024 | 66 | PARVIN BEGAM | 0.85 | 0.56 | 200 | 100
4044 | PURBA BARDHAMAN | Central Mechanical | Pipuldaha Piped Water Supply Scheme , SM/15488 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Pipuldaha Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4039/CMD | 29/08/2023 | 30 | ANANTA ELECTRICAL ENGINEERING CONSTRUCTION | 28.94 | 11.65 | 47.87 | 50
4045 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR , SM/15191 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-II W/S Scheme at Kalsi Mouza, RASULPUR W/S Scheme at 4th TW site & ALIPUR W/S Scheme at 4th TW site under Memari-I Block under within Burdwan Sub-Division, PHE Dte. [For 3 Nos. Tube well]. | 2455/BWD | 31/05/2023 | 60 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 39.76 | 13.23 | 100 | 100
4046 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR , SM/15191 | Augmentation | Preparation and Submission of DPR for Augmentation of Alipore PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1582/BSD | 24/07/2023 | 15 | MEASURE LAND | 0.78 | 0.77 | 100 | 100
4047 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR , SM/15191 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Alipur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2593/CMD | 07/06/2023 | 30 | SOUNAK ENTERPRISE | 22.73 | 10.85 | 47.72 | 50
4048 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR , SM/15191 | Augmentation | Construction of boundary wall and Soak Well at Head Works Site, Extension of Pipe Line at Alipur Adibasipara and Installation of water level indicator of ALIPUR Water Supply Scheme under MEMARI-I Block of Burdwan Division, PHE Dte. (Length -230.00 Mtr, Col-85 Nos). | 2300/BWD | 20/06/2024 | 120 | ROHAN MONDAL | 31.47 | 4.29 | 13.64 | 17
4049 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR , SM/15191 | Augmentation | Construction of switch rooms & Rising main at different TW site for ALIPUR Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | 4162/BWD | 20/09/2023 | 60 | M/S PALASH BISWAS | 8.12 | 7.19 | 100 | 100
4050 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR , SM/15191 | Augmentation | Quotation for new electric service connection at Alipur PH NO.-3 | BP-2023-24-266 | 11/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.78 | 0 | 0 | 0
4051 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR , SM/15191 | Augmentation | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for ALIPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | 430/BWD | 20/01/2025 | 287 | DULAL MAJUMDER | 117.26 | 0 | 0 | 30
4052 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR , SM/15191 | Augmentation | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3103/CMD | 11/12/2024 | 60 | S DUTTA | 15.06 | 0 | 0 | 0
4053 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR , SM/15191 | Augmentation | Laying parallel 200 mm dia pipeline at Shyamnagar of Alipur pwss under Memari-I Development Block under Burdwan Division PHE Dte. | 1026/BSD | 08/05/2025 | 30 | ROHAN MONDAL | 4.92 | 0 | 0 | 0
4054 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR , SM/15191 | Augmentation | Replacing damaged PVC water supply line and re installation of FHTC at Shyamnagar for Alipur and its Adjoining Mouza W/S Scheme, block -Memari-I within Burdwan Sub-Division ,PHE Dte | 114/BSD | 16/01/2025 | 30 | MUKHERJEE ENTERPRISE | 2.44 | 0 | 0 | 80
4055 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR , SM/15191 | Augmentation | Illumination arrangement & different electro-mechanical works at ALIPUR water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2794/CMD | 01/10/2024 | 92 | S DUTTA | 12.53 | 12.2 | 100 | 100
4056 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR ALIPUR , SM/15191 | Augmentation | Providing Balance Functional Household Tap Connection (800 Nos. FHTC) from existing distribution system within the command area of ALIPUR Piped Water Supply scheme at ALIPUR, AMADPUR (PART) mouza, Construction of boundary wall at 4th T/W site MEMARI-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 2855/BWD | 22/07/2024 | 244 | MUKHERJEE ENTERPRISE | 84.14 | 30.02 | 35.73 | 30
4057 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF KASHIARA PIPED WATER SUPPLY SCHEME , SM/15562 | Augmentation | Detail route survey, design of distribution network and preparation of estimate, drawing & DPR for providing FHTC in the scheme KASHIARA PWSS (Sl No-5) | 397/KTS | 13/04/2023 | 30 | SIRCON ENGINEERING SERVICES | 2.62 | 2.62 | 100 | 100
4058 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF KASHIARA PIPED WATER SUPPLY SCHEME , SM/15562 | Augmentation | Augmentation of KASHIARA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 450 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under MONGALKOTE Block, District:- Purba-Bardhaman. | 4666/BWD | 01/11/2023 | 427 | M/S B. RAI CONSTRUCTION COMPANY | 372.35 | 103.98 | 27.92 | 30
4059 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF KASHIARA PIPED WATER SUPPLY SCHEME , SM/15562 | Augmentation | Yard lighting arrangement & allied works at Kasiara water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2789/CMD | 01/10/2024 | 60 | BABA MALLESHWAR ENTERPRISE. | 5.55 | 0 | 0 | 0
4060 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF KASHIARA PIPED WATER SUPPLY SCHEME , SM/15562 | Augmentation | Quotation for new service connection at Augmentation of Kashiara PWSS TW-1 | BP-2024-25-398 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.75 | 0 | 0 | 0
4061 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF KASHIARA PIPED WATER SUPPLY SCHEME , SM/15562 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Kashiara Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2580/CMD | 07/06/2023 | 710 | GLACIER ENGINEERING CO | 11.03 | 0 | 0 | 100
4062 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF KASHIARA PIPED WATER SUPPLY SCHEME , SM/15562 | Augmentation | Road crossing through bituminus PWD road by Jack Pushing method of different location under the command area of KASHIARA (SM/12080, SM/15562) & SIMULIA (SM/18459) PWSS under Mongalkote Block under Katwa Sub Division under Burdwan Division, PHE. Dte. | 976/BWD | 13/03/2025 | 45 | MANASH GHOSH | 48.92 | 0 | 0 | 100
4063 | PURBA BARDHAMAN | Burdwan Division | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15165 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.28 | 0 | 0 | 0
4064 | PURBA BARDHAMAN | Burdwan Division | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15165 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.58 | 0 | 0 | 0
4065 | PURBA BARDHAMAN | Burdwan Division | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15165 | New | Material Requisition To Resource Division | 5254/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0 | 0
4066 | PURBA BARDHAMAN | Burdwan Division | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15165 | New | CHAR SUJAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM -II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3032/BWD | 14/07/2023 | 365 | M/S H.R. CONSTRUCTION | 471.47 | 385.07 | 81.68 | 91
4067 | PURBA BARDHAMAN | Central Mechanical | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15165 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
4068 | PURBA BARDHAMAN | Central Mechanical | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15165 | New | New service connection for Char Sujapur PWSS PH-1. | BP-2023-24-414 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.99 | 0 | 0 | 0
4069 | PURBA BARDHAMAN | Central Mechanical | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15165 | New | New service connection for Char Sujapur PWSS PH-2. | BP-2023-24-415 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.27 | 0 | 0 | 0
4070 | PURBA BARDHAMAN | Burdwan Division | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15165 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house & OHR under Charsujapur PWSS, Block-Ketugram-II under Katwa Sub Division within Burdwan division PHE Dte. | 2923/BWD | 26/07/2024 | 90 | M/S H.R. CONSTRUCTION | 81.31 | 0 | 0 | 2
4071 | PURBA BARDHAMAN | Central Mechanical | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15165 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-3 at Char Sujapur Water Supply Scheme [ BLOCK- Ketugram-II] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 883/CMD | 26/03/2025 | 60 | CHATTERJEE ENTERPRISE | 12.31 | 0 | 0 | 0
4072 | PURBA BARDHAMAN | Central Mechanical | CHAR SUJAPUR PIPED WATER SUPPLY SCHEME , SM/15165 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHAR SUJAPUR Water Supply Scheme [ Block- KETUGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4118/CMD | 29/08/2023 | 550 | M/S. S.R. ENTERPRISE | 29.41 | 11.63 | 47.8 | 46
4073 | PURBA BARDHAMAN | Central Drilling | CHINISPUR PIPED WATER SUPPLY SCHEME , SM/15170 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Chinispur W/S Scheme (T/W-I & II) , Ketugram-I Block under PurbaBardhman District, Central Drilling Division, P.H.E. Dte. | 1054 | 16/08/2023 | 30 | OSMAN SEKH | 16.61 | 0 | 0 | 0
4074 | PURBA BARDHAMAN | Burdwan Division | CHINISPUR PIPED WATER SUPPLY SCHEME , SM/15170 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.34 | 0 | 0 | 0
4075 | PURBA BARDHAMAN | Burdwan Division | CHINISPUR PIPED WATER SUPPLY SCHEME , SM/15170 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 20.24 | 0 | 0 | 0
4076 | PURBA BARDHAMAN | Burdwan Division | CHINISPUR PIPED WATER SUPPLY SCHEME , SM/15170 | New | Material Requisition To Resource Division | 5255/BWD | 30/11/2023 | 0 | Resource Division | 20.18 | 0 | 0 | 0
4077 | PURBA BARDHAMAN | Central Mechanical | CHINISPUR PIPED WATER SUPPLY SCHEME , SM/15170 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
4078 | PURBA BARDHAMAN | Central Mechanical | CHINISPUR PIPED WATER SUPPLY SCHEME , SM/15170 | New | Quotation for new service connection CHINISPUR PWSS TW No. 2. | BP-2024-25-296 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.51 | 0 | 0 | 0
4079 | PURBA BARDHAMAN | Central Mechanical | CHINISPUR PIPED WATER SUPPLY SCHEME , SM/15170 | New | Quotation for new service connection Chinispur PWSS TW No. 1. | BP-2024-25-295 | 13/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.07 | 0 | 0 | 0
4080 | PURBA BARDHAMAN | Burdwan Division | CHINISPUR PIPED WATER SUPPLY SCHEME , SM/15170 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AMEGERIA, ARGUN, CHINISPUR & KULUTIA Piped Water Supply Scheme under KETUGRAM -I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3630/BWD | 21/08/2023 | 1107 | M/S GOUTAM DAS | 1421.7 | 114.81 | 37.91 | 75
4081 | PURBA BARDHAMAN | Central Mechanical | CHINISPUR PIPED WATER SUPPLY SCHEME , SM/15170 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at CHINISPUR Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4116/CMD | 29/08/2023 | 640 | M/S, S.S. ENTERPRISE. | 28.48 | 5.9 | 20.71 | 88
4082 | PURBA BARDHAMAN | Burdwan Division | CHINISPUR PIPED WATER SUPPLY SCHEME , SM/15170 | New | Hiring of one no Diesel Motor Cab (BS-VI) including the cost of fuel . mobile & other charges for the inspection of the different projects of JJM for the office of the Assistant Engineer, Katwa Sub-Division, PHE Dte. (Period:- 01/03/2025 to 31/08/2025) [Sl No-02] | 321/KTS | 28/02/2025 | 184 | HAMID SK | 1.84 | 0 | 0 | 0
4083 | PURBA BARDHAMAN | Burdwan Division | CHINISPUR PIPED WATER SUPPLY SCHEME , SM/15170 | New | Road crossing through metal / concrete road by Jack Push Method for AMEGERIA (SM/16023), ARGUN (SM/16482), CHINISPUR (SM/15170) and KULITIA (SM/15167) PWSS under Ketugram I Development Block under Katwa Sub Division within Burdwan Division, PHE. Dte. | 977/BWD | 13/03/2025 | 60 | M/S GOUTAM DAS | 39.22 | 0 | 0 | 100
4084 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME , SM/15568 | Augmentation | NEW SERVICE CONNECTION FOR AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME. | BP-2023-24-594 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.25 | 0 | 0 | 0
4085 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME , SM/15568 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Berawa Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2600/CMD | 07/06/2023 | 755 | SOUNAK ENTERPRISE | 22.6 | 0 | 0 | 50
4086 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME , SM/15568 | Augmentation | Augmentation of BERWA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-II Block, District:- Purba-Bardhaman. | 3743/BWD | 28/08/2023 | 942 | ROY ENTERPRISE | 334.82 | 132.35 | 39.53 | 65
4087 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME , SM/15568 | Augmentation | Illumination arrangement & different electro-mechanical works at BARWA water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2796/CMD | 01/10/2024 | 60 | A.K. ENTERPRISE | 11.65 | 0 | 0 | 60
4088 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME , SM/15568 | Augmentation | Replacement of Tube-well & Rising main at Head work TW site for BARWA Piped Water Supply Scheme under MEMARI-II Block, District:- Purba-Bardhaman. | 2523/BWD | 03/07/2024 | 90 | ROY ENTERPRISE | 15.27 | 12.14 | 79.47 | 80
4089 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME , SM/15568 | Augmentation | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 848/BWD | 05/03/2025 | 120 | PROJECT INDIA | 394.29 | 0 | 0 | 0
4090 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF BERWA PIPED WATER SUPPLY SCHEME , SM/15568 | Augmentation | Withdrawing damaged p/m set from defunct tube well and Supply & Installation of submersible pumping machinery for T.W. No.-I (Replacement tube well) and different electro-mechanical works for P.H No.-I & II at BARWA w/s scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1147/CMSD | 02/09/2024 | 30 | MITRA ENTERPRISE | 4.16 | 0 | 0 | 100
4091 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH , SM/15179 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Ghosh Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2588/CMD | 07/06/2023 | 30 | SUDIPTA GHOSH | 11.26 | 0 | 0 | 0
4092 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH , SM/15179 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of GHOSH W/S Scheme under Memari-I Block within Burdwan Sub-Division, PHE Dte. [For Bahabpur village]. | 2703/BWD | 08/06/2023 | 30 | DAS CONSTRUCTION | 13.25 | 0 | 0 | 0
4093 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH , SM/15179 | Augmentation | Construction of switch rooms & Rising main at different TW site for GHOSH Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | 5296/BWD | 01/12/2023 | 60 | TRIYA CONSTRUCTION | 8.94 | 0 | 0 | 0
4094 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH , SM/15179 | Augmentation | Preparation and Submission of DPR for Augmentation of GHOSH PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1527/BSD | 17/07/2023 | 15 | MEASURE LAND | 0.78 | 0 | 0 | 0
4095 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH , SM/15179 | Augmentation | Supply & Installation of voltage correcting device. LED fixture set & allied works at GHOSH Water Supply Scheme PH-II under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1037/CMSD | 26/07/2024 | 30 | BENGAL ELECTRICAL CONSTRUCTION | 3.28 | 3.25 | 100 | 100
4096 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH , SM/15179 | Augmentation | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for GHOSH PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | 612/BWD | 11/02/2025 | 90 | PAL CONSTRUCTION | 29.22 | 0 | 0 | 0
4097 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH , SM/15179 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Mandaljana village of Memari-I Block under Ghosh Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. (5 nos Board) | 2365/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
4098 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH , SM/15179 | Augmentation | Allied work of Laying distribution system for FHTC work for GHOSH Piped Water Supply Scheme at Bahabpur mouza within MEMARI - I BLOCK under Burdwan Division, PHE Dte. | 113/BSD | 16/01/2025 | 45 | A.R. TRADERS | 4.7 | 0 | 0 | 100
4099 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH , SM/15179 | Augmentation | Extension of pipeline & Left out FHTC Connection work for GHOSH Piped Water Supply Scheme at Bahabpur village [200 Nos], Andur [40 Nos], Tanti Gantar [80 Nos], Kabirpur [48 Nos], Total 368 Nos FHTC Work for Sajal Gram within Memari-I Block including leftout household water tap connection (FHTC) under BURDWAN Division, P.H.E Dte. | 1021/BWD | 07/03/2024 | 336 | SKILLS AND FACILITY TRAINING INSTITUTE | 21.53 | 0 | 0 | 99
4100 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GHOSH , SM/15179 | Augmentation | Illumination arrangement & different electro-mechanical works at GHOSH water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2797/CMD | 01/10/2024 | 183 | PADMA ENGINEERING CO. | 15.79 | 0 | 0 | 100
4101 | PURBA BARDHAMAN | Burdwan Division | BHABANANDAPUR PIPED WATER SUPPLY SCHEME , SM/16024 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 44.37 | 0 | 0 | 0
4102 | PURBA BARDHAMAN | Burdwan Division | BHABANANDAPUR PIPED WATER SUPPLY SCHEME , SM/16024 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 18.56 | 0 | 0 | 0
4103 | PURBA BARDHAMAN | Central Mechanical | BHABANANDAPUR PIPED WATER SUPPLY SCHEME , SM/16024 | New | New service connection for BHABANANDAPUR PWSS TW-1. | BP-2023-24-500 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.85 | 0 | 0 | 0
4104 | PURBA BARDHAMAN | Central Mechanical | BHABANANDAPUR PIPED WATER SUPPLY SCHEME , SM/16024 | New | Additional quotation for Bhavanandapur PWSS PH-1 | BP-2024-25-223 | 26/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.67 | 0 | 0 | 0
4105 | PURBA BARDHAMAN | Central Mechanical | BHABANANDAPUR PIPED WATER SUPPLY SCHEME , SM/16024 | New | Quotation for new service connection for Bhabanandapur PWSS PH-2. | BP-2024-25-144 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.78 | 0 | 0 | 0
4106 | PURBA BARDHAMAN | Burdwan Division | BHABANANDAPUR PIPED WATER SUPPLY SCHEME , SM/16024 | New | Different types of works involve in connection with Augmentation of KALYANPUR (SM/16299) Water Supply Scheme & BHABANANDAPUR (SM/16024) Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2433/BWD | 27/06/2024 | 247 | BALAJEE ENTERPRISES | 225.16 | 45.18 | 60.91 | 2
4107 | PURBA BARDHAMAN | Central Mechanical | BHABANANDAPUR PIPED WATER SUPPLY SCHEME , SM/16024 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
4108 | PURBA BARDHAMAN | Central Mechanical | BHABANANDAPUR PIPED WATER SUPPLY SCHEME , SM/16024 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BHABANANDAPUR Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4161/CMD | 29/08/2023 | 521 | SOUNAK ENTERPRISE | 28.48 | 0 | 0 | 95
4109 | PURBA BARDHAMAN | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME , SM/16478 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 45.18 | 0 | 0 | 0
4110 | PURBA BARDHAMAN | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME , SM/16478 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.21 | 0 | 0 | 0
4111 | PURBA BARDHAMAN | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME , SM/16478 | New | Work order for "Restoration of pipeline with other allied works at different places of Bharkunda,potna,Bara dhamash,Balindar,Tola mouja under Balindar Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-II panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | 1844/KSD | 27/11/2024 | 15 | SUPRITI ENTERPRISE | 2.86 | 0 | 0 | 0
4112 | PURBA BARDHAMAN | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME , SM/16478 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR BALINDAR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 2106/KSD | 04/03/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.66 | 100 | 2
4113 | PURBA BARDHAMAN | Central Mechanical | BALINDAR PIPED WATER SUPPLY SCHEME , SM/16478 | New | New service connection for BALINDAR PWSS TW-2. | BP-2023-24-503 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.97 | 0 | 0 | 0
4114 | PURBA BARDHAMAN | Central Mechanical | BALINDAR PIPED WATER SUPPLY SCHEME , SM/16478 | New | New service connection charges for Balindar PWSS TW-1 | BP-2023-24-357 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.2 | 0 | 0 | 0
4115 | PURBA BARDHAMAN | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME , SM/16478 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALINDAR, CHAK SHIMLA & DWARIATAN Piped Water Supply Scheme under Kalna II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3700/BWD | 24/08/2023 | 770 | SUPRITI ENTERPRISE | 1424.22 | 83.43 | 15.8 | 30
4116 | PURBA BARDHAMAN | Central Mechanical | BALINDAR PIPED WATER SUPPLY SCHEME , SM/16478 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
4117 | PURBA BARDHAMAN | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME , SM/16478 | New | Construction of Pipe carrying Truss Bridge for carrying 200 mm dia MS Pipe at PWD Bridge under Hatgachha Mouza under the command area of Balindar PWSS (SM/16478) within Kalna -II block of Kalna Sub-Division, PHE Dte under Burdwan Division, PHE Dte. | 1244/BWD | 23/04/2025 | 60 | M/S DATTA ENTERPRISE | 29.3 | 0 | 0 | 1
4118 | PURBA BARDHAMAN | Central Mechanical | BALINDAR PIPED WATER SUPPLY SCHEME , SM/16478 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BALINDAR Water Supply Scheme [ Block- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4126/CMD | 29/08/2023 | 756 | ASIA CONSTRUCTION. | 28.98 | 0 | 0 | 90
4119 | PURBA BARDHAMAN | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME , SM/16478 | New | Providing of Balance FHTC and other allied works at Tola Mouza under the command area of Balindar Piped Water Supply Scheme (SM/16478) in order to declare Sajalgram under Kalna-II Block under Kalna Sub-Division under Burdwan Division, PHE Dte. | 1246/BWD | 23/04/2025 | 69 | GOPINATH ENTERPRISE | 15.44 | 0 | 0 | 100
4120 | PURBA BARDHAMAN | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME , SM/16478 | New | Providing of Balance FHTC and other allied works at Baradhamas Mouza under the command area of Balindar Piped Water Supply Scheme (SM/16478) in order to declare Sajalgram under Kalna-II Block under Kalna Sub-Division under Burdwan Division, PHE Dte. | 1248/BWD | 23/04/2025 | 69 | GOPINATH ENTERPRISE | 13.68 | 0 | 0 | 100
4121 | PURBA BARDHAMAN | Burdwan Division | BALINDAR PIPED WATER SUPPLY SCHEME , SM/16478 | New | Providing of Balance FHTC and other allied works at Bhurkunda & Balindar Mouza under the command area of Balindar Piped Water Supply Scheme (SM/16478) in order to declare Sajalgram under Kalna-II Block under Kalna Sub-Division under Burdwan Division, PHE Dte. | 1250/BWD | 23/04/2025 | 69 | GOPINATH ENTERPRISE | 12.19 | 0 | 0 | 100
4122 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH , SM/16479 | Augmentation | Illumination arrangement & different electro-mechanical works at SAKTIGARH water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2956/CMD | 20/11/2024 | 60 | CHOUDHURY ENTERPRISE | 14.34 | 0 | 0 | 0
4123 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH , SM/16479 | Augmentation | Supply of one No. Diesel Driven Car ( other than Ambasader) on hire basis for the office of the Assistant Engineer, RWS Burdwan Sub-Division, PHE Dte. (Period from 01-07-2024 to 31-08-2024). | 207/RWS | 28/06/2024 | 61 | MD HASIN | 0.8 | 0.57 | 70.67 | 0
4124 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH , SM/16479 | Augmentation | Continuation Work for the supply of one no. Diesel driven Motor Cab/Maxi Cab (Air Conditioner) on hire basis for the office of the Assistant Engineer, to be used by the Assistant Engineer, RWS Burdwan Sub-Divn., PHE. Dte. (Period from 01/01/2024 to 29/02/2024) | 403/RWS | 29/12/2023 | 62 | MD HASIN | 0.8 | 0.5 | 62.87 | 0
4125 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH , SM/16479 | Augmentation | Protection work of LDS and approach road to 2nd Pump-House of Saktigarh PWSS Augmentation at the node point of 161-166 under Burdwan Division, PHE Dte. [SM-16479] | 94/RWS | 13/03/2024 | 20 | JAYANTA CHAKRABORTY | 0.95 | 0.95 | 100 | 100
4126 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH , SM/16479 | Augmentation | Crossing of Old G.T Road near Head Works with 250 mm dia pipeline through pushing of 750mm.dia RCC casing pipe by hydraulic jacking method for Saktigarh W/S Scheme (Augmentation) under Burdwan Division, PHE Dte. | 153/RWS | 29/04/2024 | 25 | IJABUL SEKH | 6.55 | 6.55 | 100 | 100
4127 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH , SM/16479 | Augmentation | Protection of LDS of Saktigarh PWSS Augmentation at the node point of 36-44-64 under Burdwan Division, PHE Dte. [SM-16479] | 92/RWS | 13/03/2024 | 20 | KHUSI BHAKAT | 0.78 | 0.76 | 100 | 100
4128 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH , SM/16479 | Augmentation | Protection of LDS of Saktigarh PWSS Augmentation at the node point of 75-123 under Burdwan Division, PHE Dte. [SM-16479] | 93/RWS | 13/03/2024 | 20 | GHOSH ENTERPRISE | 0.79 | 0.79 | 100 | 100
4129 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH , SM/16479 | Augmentation | Quotation for new service connection at Augmentation of Shaktigarh W/S Scheme TW-3. | BP-2024-25-184 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.01 | 0 | 0 | 0
4130 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH , SM/16479 | Augmentation | Additional quotation for conversion of HTOH line from HT at Saktigarh (Aug) PWSS. | BP-2024-25-231 | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.08 | 0 | 0 | 0
4131 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH , SM/16479 | Augmentation | Quotation for new service connection for Shaktigarh PWSS PH-2 | BP-2024-25-183 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.48 | 0 | 0 | 0
4132 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH , SM/16479 | Augmentation | Upgradation of Boundary wall, Drain & land development at Head work site for SHAKTIGAR PWSS under Burdwan-Sub Div, Block-Burdwan II under Burdwan Div. PHE Dte. | 1425/BWD | 20/05/2025 | 30 | SARKAR AGENCY | 5.39 | 0 | 0 | 0
4133 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH , SM/16479 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Saktigrah Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2587/CMD | 07/06/2023 | 755 | P.K. ENGINEERING | 22.69 | 0 | 0 | 100
4134 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR SHAKTIGARH , SM/16479 | Augmentation | Augmentation of SAKTIGARH Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & Construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under BARDHAMAN-II Block, District:- Purba-Bardhaman. | 5376/BWD | 07/12/2023 | 390 | IJABUL SEKH | 203.46 | 81.31 | 55.79 | 50
4135 | PURBA BARDHAMAN | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME , SM/16308 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.38 | 0 | 0 | 0
4136 | PURBA BARDHAMAN | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME , SM/16308 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 15.09 | 0 | 0 | 0
4137 | PURBA BARDHAMAN | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME , SM/16308 | New | Material Requisition To Resource Division | 4884/BWD | 10/11/2023 | 0 | Resource Division | 33.21 | 0 | 0 | 0
4138 | PURBA BARDHAMAN | Central Mechanical | SADHPUKHARIA PIPED WATER SUPPLY SCHEME , SM/16308 | New | New service connection charges for Sadhpukuria PWSS TW-1 | BP-2023-24-185 | 04/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0 | 0
4139 | PURBA BARDHAMAN | Central Mechanical | SADHPUKHARIA PIPED WATER SUPPLY SCHEME , SM/16308 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SADHPUKHRIA Water Supply Scheme [ Block- KALNA-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | 4131/CMD | 29/08/2023 | 30 | SIMARR | 20.64 | 9.28 | 44.96 | 71
4140 | PURBA BARDHAMAN | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME , SM/16308 | New | Work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) for the Office of the Assistant Engineer, Kalna Sub-Division, Burdwan Division, P.H.E. Dte. [Period from 01.12.2023 to 31.05.2024] (Vehicle No-WB 25K 4575). | 1680/KSD | 22/11/2023 | 183 | SUSMITA MANDAL | 0.87 | 2.33 | 267.77 | 23
4141 | PURBA BARDHAMAN | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME , SM/16308 | New | Continuation work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) for the Office of the Assistant Engineer, Kalna Sub-Division, Burdwan Division, P.H.E. Dte. [Period - 01.06.2024 to 30.11.2024]" (Vehicle No-WB 25K 4575) | 273/KSD | 30/05/2024 | 183 | SUSMITA MANDAL | 2.4 | 2.25 | 93.84 | 0
4142 | PURBA BARDHAMAN | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME , SM/16308 | New | Continuation work order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) for the Office of the Assistant Engineer, Kalna Sub-Division, Burdwan Division, P.H.E. Dte. [Period from 01.12.2024 to 28.02.2025]". [Vehicle No- WB 25K 4575]. | 1896/KSD | 29/11/2024 | 91 | SUSMITA MANDAL | 1.2 | 1.14 | 95.27 | 0
4143 | PURBA BARDHAMAN | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME , SM/16308 | New | Work Order for "Hiring of one no. DIESEL MOTOR CAB (BS-VI) for the Office of the Assistant Engineer, Kalna Sub-Division, Burdwan Division, P.H.E. Dte. [Period from 01.03.2025 to 31.05.2025]". [Vehicle No- 25 K 4575]. | 316/KSD | 28/02/2025 | 92 | SUSMITA MANDAL | 1.2 | 0.39 | 32.26 | 1
4144 | PURBA BARDHAMAN | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME , SM/16308 | New | SADHPUKHARIA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Kalna-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1934/BWD | 24/04/2023 | 313 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 72 | 66.88 | 91.84 | 30
4145 | PURBA BARDHAMAN | Burdwan Division | SADHPUKHARIA PIPED WATER SUPPLY SCHEME , SM/16308 | New | Work order for "DESIGNING,MAKING AND ERECTION OF SIGN BOARD FOR SAJAL GRAM IN ¿¿6 No... VILLAGE, ¿KALNA-II... BLOCK UNDER KALNA SUB DIVISION WITHIN BURDWAN DIVISION PHE DTE.(18nos board)". | 1983/KSD | 06/12/2024 | 10 | OMKAR ENTERPRISE | 2.52 | 0 | 0 | 100
4146 | PURBA BARDHAMAN | Central Mechanical | BAJITPUR PIPED WATER SUPPLY SCHEME , SM/16619 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bajitpur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4028/CMD | 29/08/2023 | 30 | SAIKAT ENTERPRISE | 28.98 | 0 | 0 | 0
4147 | PURBA BARDHAMAN | Burdwan Division | BAJITPUR PIPED WATER SUPPLY SCHEME , SM/16619 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.46 | 0 | 0 | 0
4148 | PURBA BARDHAMAN | Burdwan Division | BAJITPUR PIPED WATER SUPPLY SCHEME , SM/16619 | New | Material Requisition To Resource Division | 4003/BWD | 08/09/2023 | 0 | Resource Division | 9.08 | 0 | 0 | 0
4149 | PURBA BARDHAMAN | Burdwan Division | BAJITPUR PIPED WATER SUPPLY SCHEME , SM/16619 | New | Material Requisition To Resource Division | 5096/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
4150 | PURBA BARDHAMAN | Burdwan Division | BAJITPUR PIPED WATER SUPPLY SCHEME , SM/16619 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-09-2024 to 30-11-2024 | 1957/BSD | 30/08/2024 | 91 | SK. ASFIA | 1.2 | 0.34 | 85.9 | 60
4151 | PURBA BARDHAMAN | Central Mechanical | BAJITPUR PIPED WATER SUPPLY SCHEME , SM/16619 | New | New electric connection for Bajitpur PWSS, PH-1. | BP-2023-24-358 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.31 | 0 | 0 | 0
4152 | PURBA BARDHAMAN | Burdwan Division | BAJITPUR PIPED WATER SUPPLY SCHEME , SM/16619 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAJITPUR, SHUKUR & HARISHNAPUR Piped Water Supply Scheme under RAINA-I Block, District:- Purba Bardhaman [NEW SCHEME] | 3197/BWD | 24/07/2023 | 907 | MRITYUNJOY MUKHERJEE & CO. | 1242.03 | 54.78 | 15.18 | 55
4153 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATUNGRAM , SM/15753 | Augmentation | Preparation and Submission of DPR for Augmentation of Natungram PWSS under Burdwan-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1474/BSD | 12/07/2023 | 15 | MEASURE LAND | 0.78 | 0.77 | 100 | 100
4154 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATUNGRAM , SM/15753 | Augmentation | Augmentation of NATUNGRAM Piped Water Supply Scheme Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & Rising Main under BARDHAMAN-I Block, District:- Purba-Bardhaman. | 3726/BWD | 25/08/2023 | 915 | BASU ENTERPRISE | 72.82 | 37.76 | 51.86 | 90
4155 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATUNGRAM , SM/15753 | Augmentation | Providing 20 Nos.FHTC at AMAR & KAMODPUR village for declearation of SWAJALGRAM under NATUNGRAM Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. | 1034/BSD | 10/06/2024 | 108 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.94 | 0 | 0 | 100
4156 | PURBA BARDHAMAN | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME , SM/18245 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 6.45 | 0 | 0 | 0
4157 | PURBA BARDHAMAN | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME , SM/18245 | New | Material Requisition To Resource Division | 3827/BWD | 01/09/2023 | 0 | Resource Division | 17.67 | 0 | 0 | 0
4158 | PURBA BARDHAMAN | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME , SM/18245 | New | Material Requisition To Resource Division | 4923/BWD | 10/11/2023 | 0 | Resource Division | 41.11 | 0 | 0 | 0
4159 | PURBA BARDHAMAN | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME , SM/18245 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SASANGA Water Supply Scheme [ Block-KHONDOGHOSH ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4185/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 45.37 | 24.01 | 52.92 | 90
4160 | PURBA BARDHAMAN | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME , SM/18245 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
4161 | PURBA BARDHAMAN | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME , SM/18245 | New | Material Requisition To Resource Division | 4116/BWD | 25/11/2024 | 0 | Resource Division | 22.79 | 0 | 0 | 0
4162 | PURBA BARDHAMAN | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME , SM/18245 | New | Quotation for new service connection for Sasanga PWSS PH 2. | BP-2024-25-120 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.09 | 0 | 0 | 0
4163 | PURBA BARDHAMAN | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME , SM/18245 | New | New service connection charges for Sasanga PWSS TW-2 | BP-2023-24-401 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.5 | 0 | 0 | 0
4164 | PURBA BARDHAMAN | Central Mechanical | SASANGA PIPED WATER SUPPLY SCHEME , SM/18245 | New | New service connection charges for Sasanga PWSS TW-1 | BP-2023-24-400 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.46 | 0 | 0 | 0
4165 | PURBA BARDHAMAN | Burdwan Division | SASANGA PIPED WATER SUPPLY SCHEME , SM/18245 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ONARI & SASANGA Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | 3430/BWD | 07/08/2023 | 786 | M/S JAN MAHAMMAD | 1398.82 | 486.11 | 58.33 | 50
4166 | PURBA BARDHAMAN | Central Mechanical | SULTANPUR PIPED WATER SUPPLY SCHEME , SM/18607 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sultanpur Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4018/CMD | 29/08/2023 | 30 | SUBRATA BHADRA | 28.96 | 0 | 0 | 0
4167 | PURBA BARDHAMAN | Burdwan Division | SULTANPUR PIPED WATER SUPPLY SCHEME , SM/18607 | New | Material Requisition To Resource Division | 5071/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
4168 | PURBA BARDHAMAN | Burdwan Division | SULTANPUR PIPED WATER SUPPLY SCHEME , SM/18607 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.55 | 0 | 0 | 0
4169 | PURBA BARDHAMAN | Burdwan Division | SULTANPUR PIPED WATER SUPPLY SCHEME , SM/18607 | New | Material Requisition To Resource Division | 4301/BWD | 29/09/2023 | 0 | Resource Division | 6.53 | 0 | 0 | 0
4170 | PURBA BARDHAMAN | Burdwan Division | SULTANPUR PIPED WATER SUPPLY SCHEME , SM/18607 | New | Land demarcation and preparation of sketch map for Haldi, Sultanpur, Berugram & Karail Piped W/S. Scheme (New Scheme) at different Blocks under JJM under Burdwan Division, PHE Dte. | 842/AE/HQ | 01/11/2023 | 15 | M/S S. CHOUDHURY | 0.33 | 0 | 0 | 100
4171 | PURBA BARDHAMAN | Central Mechanical | SULTANPUR PIPED WATER SUPPLY SCHEME , SM/18607 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
4172 | PURBA BARDHAMAN | Central Mechanical | SULTANPUR PIPED WATER SUPPLY SCHEME , SM/18607 | New | Quotation for new service connection at SULTANPUR W/S Scheme PH-I. | BP-2023-24-324 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.49 | 0 | 0 | 0
4173 | PURBA BARDHAMAN | Burdwan Division | SULTANPUR PIPED WATER SUPPLY SCHEME , SM/18607 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BERUGRAM & SULTANPUR Piped Water Supply Scheme under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | 092/BWD | 05/01/2024 | 604 | SK ALIM | 1368.51 | 317.88 | 46.2 | 55
4174 | PURBA BARDHAMAN | Burdwan Division | SULTANPUR PIPED WATER SUPPLY SCHEME , SM/18607 | New | Balance work of BERUGRAM & SULTANPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman. | 723/BWD | 24/02/2025 | 180 | MD HASIN | 438.83 | 0 | 0 | 0
4175 | PURBA BARDHAMAN | Burdwan Division | SANUI PIPED WATER SUPPLY SCHEME , SM/18610 | New | Material Requisition To Resource Division | 3852/BWD | 01/09/2023 | 0 | Resource Division | 13.05 | 0 | 0 | 0
4176 | PURBA BARDHAMAN | Burdwan Division | SANUI PIPED WATER SUPPLY SCHEME , SM/18610 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.15 | 0 | 0 | 0
4177 | PURBA BARDHAMAN | Burdwan Division | SANUI PIPED WATER SUPPLY SCHEME , SM/18610 | New | Material Requisition To Resource Division | 4943/BWD | 10/11/2023 | 0 | Resource Division | 41.11 | 0 | 0 | 0
4178 | PURBA BARDHAMAN | Burdwan Division | SANUI PIPED WATER SUPPLY SCHEME , SM/18610 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-06-2024 to 31-08-2024" | 918/BSD | 28/05/2024 | 92 | SK. ASFIA | 1.2 | 0.8 | 199.74 | 60
4179 | PURBA BARDHAMAN | Central Mechanical | SANUI PIPED WATER SUPPLY SCHEME , SM/18610 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
4180 | PURBA BARDHAMAN | Burdwan Division | SANUI PIPED WATER SUPPLY SCHEME , SM/18610 | New | Material Requisition To Resource Division | 4107/BWD | 25/11/2024 | 0 | Resource Division | 15.04 | 0 | 0 | 0
4181 | PURBA BARDHAMAN | Central Mechanical | SANUI PIPED WATER SUPPLY SCHEME , SM/18610 | New | New service connection for Sanui W/S Scheme. | BP-2023-24-380 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 15.93 | 0 | 0 | 0
4182 | PURBA BARDHAMAN | Central Mechanical | SANUI PIPED WATER SUPPLY SCHEME , SM/18610 | New | New service connection for Sanui W/S Scheme. | BP-2023-24-381 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.95 | 0 | 0 | 0
4183 | PURBA BARDHAMAN | Burdwan Division | SANUI PIPED WATER SUPPLY SCHEME , SM/18610 | New | SANUI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Memari-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3536/BWD | 10/08/2023 | 783 | M/S ASHA CONSTRUCTION | 825.12 | 238.99 | 28.96 | 35
4184 | PURBA BARDHAMAN | Burdwan Division | SANUI PIPED WATER SUPPLY SCHEME , SM/18610 | New | Restoration of Conc. road, Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for MAGRA, SANUI, SATGACHIA Zone-I & NARAGOHALIA PIPED WATER SUPPLY SCHEME, Block-Memari-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | 611/BWD | 11/02/2025 | 180 | M/S ASHA CONSTRUCTION | 354.13 | 0 | 0 | 25
4185 | PURBA BARDHAMAN | Central Mechanical | SANUI PIPED WATER SUPPLY SCHEME , SM/18610 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SANUI Water Supply Scheme [ Block- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4077/CMD | 29/08/2023 | 672 | JAL PRAVAHIKA PVT LTD | 44.08 | 0 | 0 | 70
4186 | PURBA BARDHAMAN | Burdwan Division | PALISGRAM PIPE WATER SUPPLY SCHEME , SM/18481 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 2.93 | 0 | 0 | 0
4187 | PURBA BARDHAMAN | Burdwan Division | PALISGRAM PIPE WATER SUPPLY SCHEME , SM/18481 | New | Material Requisition To Resource Division | 4939/BWD | 10/11/2023 | 0 | Resource Division | 27.8 | 0 | 0 | 0
4188 | PURBA BARDHAMAN | Burdwan Division | PALISGRAM PIPE WATER SUPPLY SCHEME , SM/18481 | New | Material Requisition To Resource Division | 4304/BWD | 29/09/2023 | 0 | Resource Division | 1.53 | 0 | 0 | 0
4189 | PURBA BARDHAMAN | Central Mechanical | PALISGRAM PIPE WATER SUPPLY SCHEME , SM/18481 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at PALISGRAM Water Supply Scheme [ Block-MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4133/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 44.62 | 24.76 | 55.5 | 63
4190 | PURBA BARDHAMAN | Burdwan Division | PALISGRAM PIPE WATER SUPPLY SCHEME , SM/18481 | New | Material Requisition To Resource Division | 4114/BWD | 25/11/2024 | 0 | Resource Division | 17.51 | 0 | 0 | 0
4191 | PURBA BARDHAMAN | Central Mechanical | PALISGRAM PIPE WATER SUPPLY SCHEME , SM/18481 | New | NEW SERVICE CONNECTION FOR PALISHGRAM PH -2 PWSS. | BP-2024-25-3 | 04/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.87 | 0 | 0 | 0
4192 | PURBA BARDHAMAN | Central Mechanical | PALISGRAM PIPE WATER SUPPLY SCHEME , SM/18481 | New | NEW SERVICE CONNECTION FOR PALISHGRAM PWSS. | BP-2024-25-2 | 04/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.96 | 0 | 0 | 0
4193 | PURBA BARDHAMAN | Central Mechanical | PALISGRAM PIPE WATER SUPPLY SCHEME , SM/18481 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
4194 | PURBA BARDHAMAN | Burdwan Division | PALISGRAM PIPE WATER SUPPLY SCHEME , SM/18481 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PALISGRAM, PURBA NAYAPARA & SITAHATI Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] | 4364/BWD | 04/10/2023 | 910 | M/S S. CHOUDHURY | 1505.07 | 68.35 | 9.97 | 77
4195 | PURBA BARDHAMAN | Burdwan Division | GIDHGRAM PIPED WATER SUPPLY SCHEME , SM/18485 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.31 | 0 | 0 | 0
4196 | PURBA BARDHAMAN | Burdwan Division | GIDHGRAM PIPED WATER SUPPLY SCHEME , SM/18485 | New | Material Requisition To Resource Division | 4015/BWD | 08/09/2023 | 0 | Resource Division | 74.64 | 0 | 0 | 0
4197 | PURBA BARDHAMAN | Central Mechanical | GIDHGRAM PIPED WATER SUPPLY SCHEME , SM/18485 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
4198 | PURBA BARDHAMAN | Central Mechanical | GIDHGRAM PIPED WATER SUPPLY SCHEME , SM/18485 | New | New service connection for Gidhagram PWSS PH-3 | BP-2023-24-420 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.9 | 0 | 0 | 0
4199 | PURBA BARDHAMAN | Central Mechanical | GIDHGRAM PIPED WATER SUPPLY SCHEME , SM/18485 | New | NEW SERVICE CONNECTION FOR GIDHGRAM PWSS TW 1 | BP-2023-24-635 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.48 | 0 | 0 | 0
4200 | PURBA BARDHAMAN | Central Mechanical | GIDHGRAM PIPED WATER SUPPLY SCHEME , SM/18485 | New | Quotation for new service connection at Gidhgram PWSS TW 3. | BP-2024-25-413 | 16/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.54 | 0 | 0 | 0
4201 | PURBA BARDHAMAN | Central Mechanical | GIDHGRAM PIPED WATER SUPPLY SCHEME , SM/18485 | New | NEW SERVICE CONNECTION FOR GIDHGRAM PWSS TW 2. | BP-2023-24-534 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.91 | 0 | 0 | 0
4202 | PURBA BARDHAMAN | Burdwan Division | GIDHGRAM PIPED WATER SUPPLY SCHEME , SM/18485 | New | GIDHGRAM Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3431/BWD | 07/08/2023 | 1059 | POWER TOOLS & ENGINEERING | 671.42 | 310.97 | 46.32 | 31
4203 | PURBA BARDHAMAN | Central Mechanical | GIDHGRAM PIPED WATER SUPPLY SCHEME , SM/18485 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at GIDHGRAM Water Supply Scheme [ Block-KATWA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4136/CMD | 29/08/2023 | 605 | M/S, S.S. ENTERPRISE. | 45.53 | 23.87 | 52.44 | 64
4204 | PURBA BARDHAMAN | Central Mechanical | GIDHGRAM PIPED WATER SUPPLY SCHEME , SM/18485 | New | CONTINUATION ORDER-Hiring of inspection vehicle bearing no WB41H5698 (Disel/CNG/LPG driven) for supervision of JJM works under jurisdiction of the Assistant Engineer CMSD PHE Dte .[W.E.F- 01/11/2025 TO 31/12/2025] | 1436/CMSD | 29/10/2025 | 61 | SUBRATA BHADRA | 0.81 | 0 | 0 | 0
4205 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Dhoba and Goalpara Mouzas of Nasratpur PWSS , SM/06745 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of NASARATPUR Piped Water Supply Scheme at Purbasthali-I Block under Burdwan Division, PHE Dte._2ND CALL. | 6079/BWD | 08/10/2021 | 60 | BRINDABAN KONAR | 54.89 | 48.84 | 100 | 1
4206 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Dhoba and Goalpara Mouzas of Nasratpur PWSS , SM/06745 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of NASARATPUR Piped Water Supply Scheme at Gopinathpur (Part), Nasaratput (Part) & Paruldanga (Part) Village (Mouza), Purbasthali - I Block under Burdwan Division, PHE Dte | 211/BWD | 11/01/2022 | 60 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 76.77 | 15.16 | 100 | 1
4207 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Dhoba and Goalpara Mouzas of Nasratpur PWSS , SM/06745 | Retrofitting | Work order for Repairing of leakage of existing pipe line of Nasaratpur habitation of Purbasthali-I Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | 419/KSD | 11/05/2023 | 30 | PARTHA PRATIM ACHARYA | 0.97 | 0.72 | 100 | 50
4208 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Dhoba and Goalpara Mouzas of Nasratpur PWSS , SM/06745 | Retrofitting | Restoration work of Kalna baidyapur road from 7.90 km to 13.75 km (in stretches) damaged due to laying of underground water pipe line by PHE with box cutting and Jhama with moorum consolidation under Kalna Highway Sub-Division of Burdwan South Highway Division, P.W (Roads) Dte. during the year 2023-2024. | 1025/JJM | 05/10/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 8.1 | 0 | 0 | 0
4209 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Dhoba and Goalpara Mouzas of Nasratpur PWSS , SM/06745 | Retrofitting | Restoration work of Kulti Haritala to Jamna Bus stand via Krishnapur, Baharkuli,Sargoria road from 3.15 km to 5.70 km, damaged due to laying of underground water pipe line by PHE with box cutting and Jhama with moorum consolidation under Kalna Highway Sub Division of Burdwan South Highway Division, P.W(Roads) Dte. during the year 2023-24. | 1025/JJM | 05/10/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 5.36 | 0 | 0 | 0
4210 | PURBA BARDHAMAN | Burdwan Division | SIMULIA PIPE WATER SUPPLY SCHEME , SM/18459 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 18.62 | 0 | 0 | 0
4211 | PURBA BARDHAMAN | Burdwan Division | SIMULIA PIPE WATER SUPPLY SCHEME , SM/18459 | New | Material Requisition To Resource Division | 4303/BWD | 29/09/2023 | 0 | Resource Division | 4.13 | 0 | 0 | 0
4212 | PURBA BARDHAMAN | Burdwan Division | SIMULIA PIPE WATER SUPPLY SCHEME , SM/18459 | New | Material Requisition To Resource Division | 307/BWD | 24/01/2024 | 0 | Resource Division | 32.21 | 0 | 0 | 0
4213 | PURBA BARDHAMAN | Central Mechanical | SIMULIA PIPE WATER SUPPLY SCHEME , SM/18459 | New | New service connection charges for Shimulia PWSS TW-1 | BP-2023-24-376 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.42 | 0 | 0 | 0
4214 | PURBA BARDHAMAN | Central Mechanical | SIMULIA PIPE WATER SUPPLY SCHEME , SM/18459 | New | New service connection charges for Simulia PWSS TW-2 | BP-2023-24-377 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.22 | 0 | 0 | 0
4215 | PURBA BARDHAMAN | Central Mechanical | SIMULIA PIPE WATER SUPPLY SCHEME , SM/18459 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SIMULIA Water Supply Scheme [ Block- MONGOLKOTE ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4084/CMD | 29/08/2023 | 610 | P.K. ENGINEERING | 41.62 | 0 | 0 | 31
4216 | PURBA BARDHAMAN | Burdwan Division | SIMULIA PIPE WATER SUPPLY SCHEME , SM/18459 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SIMULIA & LAKSHIMPUR Piped Water Supply Scheme under Mongalkote Block, District:- Purba-Bardhaman [NEW SCHEME] | 4363/BWD | 04/10/2023 | 727 | PUSPA ENTERPRISE | 1090.95 | 278.65 | 51.34 | 37
4217 | PURBA BARDHAMAN | Central Mechanical | SIMULIA PIPE WATER SUPPLY SCHEME , SM/18459 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
4218 | PURBA BARDHAMAN | Burdwan Division | SIMULIA PIPE WATER SUPPLY SCHEME , SM/18459 | New | Different types of works involve in connection with implementation of Gohgram, Jabagram, Kherua, Lakshmipur & Simulia Piped Water Supply Scheme under Mongolkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. | 936/BWD | 11/03/2025 | 180 | M/S GHOSH CONSTRUCTION | 360.68 | 0 | 0 | 0
4219 | PURBA BARDHAMAN | Burdwan Division | SIMULIA PIPE WATER SUPPLY SCHEME , SM/18459 | New | Road crossing through bituminus PWD road by Jack Pushing method of different location under the command area of KASHIARA (SM/12080, SM/15562) & SIMULIA (SM/18459) PWSS under Mongalkote Block under Katwa Sub Division under Burdwan Division, PHE. Dte. | 976/BWD | 13/03/2025 | 45 | MANASH GHOSH | 48.92 | 0 | 0 | 100
4220 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme , SM/06970 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amar village of Natungram piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-579/BWD/2020-21) | 4465/BWD | 11/11/2020 | 30 | BAMDEB CONSTRUCTION & CO | 4.92 | 9.84 | 200 | 1
4221 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme , SM/06970 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Natungram Piped Water Supply Scheme at Amar (6 Nos Habitation Part), Natungram (4 Nos Habitation Part) & Bohar Village (Mouza), Bardhaman-I Block under Burdwan Division, PHE Dte.(Agreement No. 73/2020-2021 OF SE/CC/PHE. DTE.) | 7052/BWD | 22/12/2020 | 90 | HAMID SK | 48.2 | 82.8 | 200 | 1
4222 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme , SM/06970 | Retrofitting | Providing Functional House hold Tap connection (FHTC) from existing distribution system within the command area of NATUNGRAM piped water supply scheme at Natungram village under Bardhaman-I Block under Burdwan Division, PHE Dte.[Gr.-C] | 687/BSD | 09/06/2021 | 30 | HAMID SK | 2.95 | 5.81 | 200 | 1
4223 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme , SM/06970 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Amra village of Natungram piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-332/BWD/2020-21) | 2732/BWD | 10/08/2020 | 30 | BAMDEB CONSTRUCTION & CO | 4.92 | 9.84 | 200 | 1
4224 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme , SM/06970 | Retrofitting | Publication charges bill for the office of the Executive Engineer, Burdwan Division, PHE Dte.[Invoice No.-BCWB20RV-0001293, dt.-19/05/20, BCWB20RV-0001770, dt.-31/05/20, BCWB20RV-0001920, dt.-05/06/20, BCWB20RV-0001860, dt.-03/06/20, BCWB20RV-0001861, dt.-03/06/20, BCWB20RV-0001928, dt.-05/06/20, BCWB20RV-0001820, dt.-03/06/20, BCWB19RV-0059455, dt.-20/03/20, BCWB19RV-0059454. dt.-20/03/20, BCWB19RV-0057682, dt.-12/03/20, BCWB20RV-0003210, dt.-26/06/20, BCWB20RV-0000918, dt.-07/05/20, BCWB20RV-0001352, dt.-22/05/20, BCWB19RV-0050592, dt.-30/01/20] | 240/DW/22-23 | 04/07/2022 | 0 | BENNETT COLEMAN & COMPANY LIMITED | 1.89 | 0 | 0 | 0
4225 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme , SM/06970 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ I Block under Burdwan Division, PHE. Dte. | 32/BWD | 04/01/2022 | 30 | ROY BISWAS CONSTRUCTION | 9.89 | 4.9 | 100 | 1
4226 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme , SM/06970 | Retrofitting | Providing 45 Nos.FHTC at SIJEPARA village for declearation of SWAJALGRAM under NATUNGRAM Piped Water Supply Scheme , Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte | 1280/BSD | 12/07/2024 | 45 | SHANKHA GHOSH | 1.76 | 0 | 0 | 0
4227 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natungram Piped Water Supply Scheme , SM/06970 | Retrofitting | Providing 50 Nos.FHTC at BIRPUR village for declearation of SWAJALGRAM under NATUNGRAM Piped Water Supply Scheme , Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. | 1281/BSD | 12/07/2024 | 45 | I.S. ENTERPRISE | 2.28 | 2.28 | 100 | 100
4228 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Deriapur PWSS , SM/06749 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Deriapur village of Deriapur piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-158/BWD/2020-21) | 2691/BWD | 07/08/2020 | 30 | ASHOK KUMAR GHOSH | 4.92 | 9.84 | 200 | 1
4229 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Deriapur PWSS , SM/06749 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Deriapur village of Deriapur piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-351/BWD/2020-21) | 3898/BWD | 12/10/2020 | 30 | ASHOK KUMAR GHOSH | 3.59 | 7.18 | 100 | 1
4230 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Deriapur PWSS , SM/06749 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of DERIAPUR Piped Water Supply Scheme at Astikur, Balagar & Bora Village (Mouza), Raina-I Block under Burdwan Division, PHE Dte.(Agreement No. 474/BWD OF 2020-2021) | 4916/BWD | 08/12/2020 | 90 | ASHOK KUMAR GHOSH | 39.84 | 61.89 | 193 | 1
4231 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Deriapur PWSS , SM/06749 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ I Block under Burdwan Division, PHE. Dte. | 39/BWD | 05/01/2022 | 30 | HAFIJUR RAHAMAN MIDYA | 15.62 | 9.1 | 100 | 1
4232 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Deriapur PWSS , SM/06749 | Retrofitting | Sinking of Tube Well, Construction of Pump House, Boundary Wall at 3rd TW Site with Extension of Pipeline & Laying Parallel line and Providing FHTC (Leftout] with allied works for DERIAPUR Piped Water Supply Scheme under Raina-I Block within Burdwan Sub Division under Burdwan Division P.H.E Dte. | 2270/BWD | 18/06/2024 | 388 | ROY CONSTRUCTION | 68.15 | 0 | 0 | 100
4233 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme , SM/07205 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nandra village of Nandra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-176/BWD/2020-21) | 2735/BWD | 10/08/2020 | 30 | BHARAT CONSTRUCTION | 4.92 | 9.84 | 200 | 1
4234 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme , SM/07205 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kalyanpur & Dangachha village of Nandra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-177/BWD/2020-21) | 2736/BWD | 10/08/2020 | 30 | BHARAT CONSTRUCTION | 4.92 | 9.84 | 200 | 1
4235 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme , SM/07205 | Retrofitting | Additional Extension of UPVC distribution pipeline in connection with FHTC for NANDRA & adjoining mouzas water supply scheme at Bardhaman-I Block under Burdwan division, PHE Dte.[Gr.-C] | 73/BSD | 19/01/2021 | 30 | BHARAT CONSTRUCTION | 4.22 | 8.37 | 200 | 1
4236 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme , SM/07205 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Nandra village of Nandra piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | 4087/BWD | 16/10/2020 | 30 | BHARAT CONSTRUCTION | 2 | 4 | 200 | 1
4237 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme , SM/07205 | Retrofitting | Providing FHTC (130 nos.) and Extension of UPVC dist. Pipeline at Noapara, Pirtala ,Nandra village of NANDRA water supply scheme at Burdwan-II Block under Burdwan Division PHE Dte..Gr. I | 1479/BSD | 09/11/2021 | 30 | BHARAT CONSTRUCTION | 4.81 | 4.81 | 100 | 1
4238 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme , SM/07205 | Retrofitting | Providing FHTC in Nandra & Naopara village for 100% coverage in Sajal Gram from existing distribution system within NANDRA PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. Gr.F. | 1360/BSD | 03/08/2022 | 5 | BHARAT CONSTRUCTION | 0.97 | 0 | 0 | 1
4239 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme , SM/07205 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage in Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ II Block under Burdwan Division, PHE. Dte. | 385/BWD | 20/01/2022 | 30 | BISWAS ENTERPRISE | 11.97 | 0 | 0 | 100
4240 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme , SM/07205 | Retrofitting | Providing FHTC in Nandra & Naopara village for 100% coverage in Sajal Gram from existing distribution system within Nandra PWSS, Bardhhaman-II Development Block under Burdwan Division, PHE Dte. | 1360-A/BSD | 03/08/2022 | 5 | BHARAT CONSTRUCTION | 0.97 | 0.96 | 100 | 1
4241 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House Hold Tap Connection (FHTC) by retrofitting within the command area of Nandra Piped Water Supply Scheme , SM/07205 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Kalyanpur & Dangachha village of Nandra Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿10B¿] | 4085/BWD | 16/10/2020 | 30 | BHARAT CONSTRUCTION | 1.65 | 3.3 | 200 | 0
4242 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme , SM/07553 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Engineer, Headquarters, Burdwan Division, PHE Dte. for the month of September & October'2022. | 766/VEH/22-23 | 22/11/2022 | 0 | SK. ASRAFUDDIN | 0.7 | 0 | 0 | 0
4243 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme , SM/07553 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41H-9788) for the office of the Assistant Head Quarters, Burdwan Division, PHE Dte. for the month of June & July'22. | 460/VEH/22-23 | 29/08/2022 | 0 | SK. ASRAFUDDIN | 0.76 | 0 | 0 | 0
4244 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme , SM/07553 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within the command area of Taraposh piped water supply scheme at Alladipur, Chintamonipur, Jarul, Kamdebpur, Punia, Sunia & Taraposh, Khandaghosh Block under Burdwan Division, PHE Dte. | 4766/BWD | 01/12/2020 | 90 | SINGHA ROY AND CO. | 70.55 | 27.59 | 100 | 1
4245 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme , SM/07553 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Khandaghosh Block under Burdwan Division, PHE. Dte. | 283/BWD | 17/01/2022 | 30 | J. K. CORPORATION | 11.88 | 11.87 | 100 | 1
4246 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme , SM/07553 | Retrofitting | Repairing of Pipeline of DVC 11 No. Canal towards Amila Bazar and DVC 11B No. Conal Towards Sehara Bazar at TARAPOSH Pipes Water Supply Scheme at Khandaghosh Block under Burdwan Division,PHE Dte. Group : F | 833/BSD | 23/05/2022 | 30 | HAFIJUR RAHAMAN MIDYA | 1.56 | 1.57 | 100 | 1
4247 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme , SM/07553 | Retrofitting | Construction of 250 cum capacity 20 Mtr staging height RCC Over Head Reservoir including pipe connection and cost of pipes specials including soil investigation for TARAPOSH & its adjoining mouzas water supply scheme under Burdwan Sub-Division, under Burdwan Division, PHE Dte. | 4594/BWD | 24/11/2020 | 180 | MITRA CONSTRUCTION | 57 | 56 | 100 | 100
4248 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Taraposh Piped Water Supply Scheme , SM/07553 | Retrofitting | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of TARAPOSE Piped Water Supply Scheme within KHANDAGHOSH Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1289/BWD | 20/03/2023 | 30 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 21.86 | 0 | 0 | 100
4249 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Chandutia Piped Water Supply Scheme , SM/07554 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Burdwan ¿ I Block under Burdwan Division, PHE. Dte. | 32/BWD | 04/01/2022 | 30 | ROY BISWAS CONSTRUCTION | 9.89 | 5 | 100 | 1
4250 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block , SM/07797 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of FAKIRPUR Piped Water Supply Scheme at Fakirpur & Bongpur village (Mouza), Burdwan - I Block under Burdwan Division, PHE Dte._2ND CALL. | 355/BWD | 15/01/2021 | 45 | AYSAN KHAN | 36.69 | 18.91 | 184.24 | 1
4251 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block , SM/07797 | Retrofitting | Providing Balance Functional Household Tap Connection (FHTC)for Swajal Gram from existing distribution system within the command area of Idilpur & Fakirpur village under Fakirpur Piped W/S.Scheme under Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr. I | 1380/BSD | 05/08/2022 | 5 | BAMDEB CONSTRUCTION & CO | 0.96 | 0.96 | 100 | 100
4252 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block , SM/07797 | Retrofitting | Providing Balance Functional Household Tap Connection(FHTC)for Swajal Gram from existing distribution system within the command area of Idilpur & Fakirpur Village under of FAKIRPUR W.S.Scheme of Burdwan-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1380-A/BSD | 05/08/2022 | 5 | BAMDEB CONSTRUCTION & CO | 0.96 | 0 | 0 | 0
4253 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block , SM/07797 | Retrofitting | Construction of boundary wall at Head works site of Fakirpur water supply scheme under Bardhaman-I Block under Burdwan Division, PHE Dte.[Length-50.20 Mtr][Part-B][South & West Side][Gr.-C] | 1026/BSD | 05/08/2021 | 45 | AYSAN KHAN | 3.77 | 0 | 0 | 1
4254 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block , SM/07797 | Retrofitting | Providing 22 Nos.FHTC at IDILPUR & FAKIRPUR village for declearation of SWAJALGRAM under FAKIRPUR Piped Water Supply Scheme, Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE Dte. | 1035/BSD | 10/06/2024 | 30 | IMPULSE INTERNATIONAL | 0.75 | 0 | 0 | 0
4255 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block , SM/07797 | Retrofitting | Providing 50 Nos. FHTC at Bongapur Casimama village for deceleration of SWAJALGRAM under FAKIRPUR Piped Water Supply Scheme , Block- Burdwan-I within Burdwan Sub Division under Burdwan Division PHE | 1279/BSD | 12/07/2024 | 61 | S.M. ENTERPRISE | 2.32 | 0 | 0 | 100
4256 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Fakirpur Piped Water Supply Scheme at Burdwan-I Block , SM/07797 | Retrofitting | Laying Parallel Pipeline, providing FHTC, Construction of Pathway and land development at Head Work site & Road restoration work for FAKIRPUR Piped Water Supply Scheme, Block- Burdwan-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | 62/BWD | 06/01/2025 | 90 | GENUINE ENGINEERS CO-OP. SOCIETY LTD. | 20.75 | 0 | 0 | 95
4257 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block , SM/07776 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Paratal-II, Berugram, Abujhati & Chakdighi G.P.) under Burdwan Division, PHE. Dte. (Part-B). | 40/BWD | 05/01/2022 | 30 | PREMANANDA ROY BISWAS | 22.68 | 5 | 100 | 1
4258 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block , SM/07776 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Jamalpur Block (Jarogram, Ajhapur, Panchra & Jougram G.P.) under Burdwan Division, PHE. Dte. (Part-A)_2ND CALL. | 1454/BWD | 11/03/2022 | 30 | PREMANANDA ROY BISWAS | 18.83 | 6.19 | 100 | 1
4259 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block , SM/07776 | Retrofitting | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for Augmentation of BALARAMPUR & its adjoining mouzas Piped Water Supply Scheme, Block - Jamalpur, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 4887/BWD | 02/11/2022 | 30 | BIBHUTI SHAW | 10.07 | 9.83 | 100 | 100
4260 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block , SM/07776 | Retrofitting | Material Requisition To Resource Division | 423/BWD | 20/01/2022 | 0 | Resource Division | 5.5 | 0 | 0 | 0
4261 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block , SM/07776 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Balarampur Piped Water Supply Scheme at Balarampur (3 Nos Habitation), Berugram (3 Nos Habitation), Krishnapur (2 Nos Habitation) & Sadipur (3 Nos Habitation Part) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 66/2020-2021 OF SE/CC/PHE. DTE.] | 5009/BWD | 10/12/2020 | 90 | M/S ASHA CONSTRUCTION | 100.79 | 51.35 | 200 | 0
4262 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block , SM/07776 | Retrofitting | Construction of temporary approach road for Boring machine and its accessories at 4th Tube Well site (due to low land) of Balarampur PWSS, Jamalpur Dev. Block Burdwan Sub-Division under Burdwan Division,PHE Dte | 519/BSD | 13/03/2024 | 15 | BIBHUTI SHAW | 0.92 | 0.9 | 100 | 100
4263 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Balarampur Piped Water Supply Scheme at Jamalpur Block , SM/07776 | Retrofitting | Laying pipeline with FHTC for BALARAMPUR Water Supply Scheme at Matnasipur village (600 Nos) (from near rail gate to matnasipur) and rest portion FHTC work of Berugram village (46 Nos), Balarampur village (40 Nos), Nasipur village (45 Nos), Salimdanga village (15 Nos) within Jamalpur Block, under Burdwan Division, PHE Dte. | 1620/BWD | 21/03/2022 | 1217 | M/S ASHA CONSTRUCTION | 47.32 | 0 | 0 | 100
4264 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block , SM/07782 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AGRADWIP Piped Water Supply Scheme at Agradwip, Babla danga, Gonsaidhowra, Saheb Nagar & Sarawaridhowra (Mouza), Katwa - II Block under Burdwan Division, PHE Dte. | 6253/BWD | 01/11/2021 | 60 | SHUBHRA KANTI GHOSH | 53.67 | 19.01 | 100 | 1
4265 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block , SM/07782 | Retrofitting | Replacement and extension of pipe line from the existing Distribution System within scheme jurisdiction at Agradwip Ghosh para village under AGRADWIP PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.(Sl No-6) | 594/KTS | 06/09/2021 | 30 | SHUBHRA KANTI GHOSH | 3.56 | 3.56 | 100 | 1
4266 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block , SM/07782 | Retrofitting | Replacement and extension of pipe line from the existing Distribution System within scheme jurisdiction at Agradwip Gopinath para and Majherpara village under AGRADWIP PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.(Sl No-5) | 593/KTS | 06/09/2021 | 30 | CHANCHAL PAL | 3.47 | 3.47 | 100 | 1
4267 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block , SM/07782 | Retrofitting | Replacement and extension of pipe line from the existing Distribution System within scheme jurisdiction at Sahebnagar village under AGRADWIP PWSS under Katwa Sub-Division under Burdwan Division PHE Dte.(Sl No-4) | 592/KTS | 06/09/2021 | 30 | TAPAS KUMAR ROY | 4.84 | 4.82 | 100 | 1
4268 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block , SM/07782 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Agradwip Piped Water Supply Scheme at Agradwip (P) village & Kharpur (P) village, Katwa - II Block under Burdwan Division, PHE Dte._Part-B.[Agreement No. 685/BWD OF 2020-2021.] | 1511/BWD | 19/02/2021 | 45 | SHUBHRA KANTI GHOSH | 44.47 | 87.03 | 112.12 | 0
4269 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Agradwip Piped Water Supply Scheme at Katwa-II Block , SM/07782 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Agradwip Piped Water Supply Scheme at Agradwip (P) village & Kharpur (P) village, Katwa - II Block under Burdwan Division, PHE Dte._Part-A. [Agreement No. 704/BWD OF 2020-2021] | 1567/BWD | 22/02/2021 | 45 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 44.39 | 86.97 | 200 | 0
4270 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block , SM/07869 | Retrofitting | Formal Work Order for providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Golgram Piped Water Supply Scheme at Golgram Village (Mouza), Galsi-I Block under Burdwan Division, PHE Dte. [Agreement No. 100/SE/CC/PHE/Dte of 2020-2021.] | 638/BWD | 25/01/2021 | 60 | SHUBHRA KANTI GHOSH | 63.87 | 19.17 | 100 | 1
4271 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block , SM/07869 | Retrofitting | Making Connection with Rising Main And Over Head Reservoir of Golgram W/S Scheme within Durgapur Sub-Division in Galsi-I Block under Burdwan Division, P.H.E. Dte. [Gr.-G] | 348/DSD | 30/06/2022 | 15 | RANADHIR SINHA | 0.33 | 0.32 | 100 | 1
4272 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block , SM/07869 | Retrofitting | Construction of approach road from entrance to OHR, Pump House and filling of low land around Over Head Reservoir with carried earth at 1st Tube well site of Golgram & its adjoining mouzas water supply scheme, Block-Galsi-I, under Burdwan Division, PHE Dte. [SL-D] | 335/DSD | 27/06/2022 | 30 | CHOUDHURY INFRA | 1.86 | 0 | 0 | 1
4273 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block , SM/07869 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of February'23. | 13/JJM | 17/04/2023 | 0 | SUJAUDDIN SEKH | 0.36 | 0 | 0 | 0
4274 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block , SM/07869 | Retrofitting | Acceptance cum Formal Work Order for the work of Balance work for Distribution System (CI/DI/UPVC), Earth Work & Concrete Work for GOLGRAM PWSS Schemes of GALSI-I Block under Durgapur Water Supply Division, PHE Dte. | 767/DWSD | 06/06/2024 | 25 | SHUBHRA KANTI GHOSH | 1.12 | 1.01 | 100 | 100
4275 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block , SM/07869 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Galsi ¿ I Block under Burdwan Division, PHE. Dte._2ND CALL. | 1738/BWD | 28/03/2022 | 1101 | JYOTI ENTERPRISE | 5.72 | 0 | 0 | 100
4276 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Golgram Piped Water Supply Scheme at Galsi-I Block , SM/07869 | Retrofitting | Acceptance cum Formal Work Order for the work of " Sinking of 300 x 200mm x 150 mtr depth by DR Rig, Repairing & Renovation of existing OHR, Construction of 01 (One) 5.25 x 3.25m No Pump House cum Chlorine Room including laying UPVC distribution system (LDS) and interconnection of PWSS & construction of Boundary wall & other allied works at Golgram under GOLGRAM PWSS, Block- Galsi-I, Dist- Purba Bardhman under Durgapur W/S Division, PHE Dte. | 771/DWSD | 06/06/2024 | 476 | ARISH CONSTRUCTION | 83.56 | 10.34 | 14.38 | 90
4277 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block , SM/07808 | Retrofitting | Extension of pipeline at Pratappur DANDA PARA, BATHAN PARA, BANGAL PARA, HINDU PARA & ADIBASI PARA of PRATAPPUR (ZONE-I) and its adjoining mouza's Piped W/S Scheme including water tap connection (FHTC) at Babuisol Vill (Goswamibandh Adibashipara Hab.), Kuldiha Vill (Adibashipara Hab.) Lachminnarayanpur Vill (2 Nos. Hab.), Pratappur Vill (2 Nos. Habs.), Radhaballabhpur Vill (1 No. Hab), Ramharipur Vill (2 Nos. Hab.) Radhamohanpur Vill. (1 No. Hab.) at Ausgram-II Block under Burdwan Division, PHE Dte._2ND CALL | 6393/BWD | 16/11/2021 | 60 | SAIKAT RAY | 44.09 | 43.5 | 100 | 1
4278 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block , SM/07808 | Retrofitting | Extension of pipeline for providing FHTC at Pratappur CHITIM DANGA, RAMHARIPUR , MUSLIMPARA & DHANDAGHA of PRATAPPUR (ZONE-I) and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur (Burdwan North)Sub Division under Burdwan Division, P.H.E. Dte. [Sl-E] | 134/DSD | 02/03/2022 | 30 | SAIKAT RAY | 4.64 | 4.41 | 100 | 1
4279 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block , SM/07808 | Retrofitting | Connection from newly constructed Over Head Reservoir to Distribution System & Rising main Pipe Line of PRATAPPUR ( ZONE - I & II ) and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block, within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte._2nd Call [Gr.-A] | 689/DSD | 08/12/2021 | 21 | S.S. ENTERPRISE | 1.66 | 0 | 0 | 1
4280 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block , SM/07808 | Retrofitting | Extension of pipeline at Babuisole & Gosaibandh village of PRATAPPUR (ZONE-II) and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-F] | 173/DSD | 19/02/2021 | 21 | RALLY CO-OP LABOUR CONTRACT & CONSTRUCTION SOCIETY LTD. | 4.67 | 0 | 0 | 1
4281 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block , SM/07808 | Retrofitting | Extension of pipeline at Kuldiha & Raniganj village of PRATAPPUR (ZONE-II) and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-E] | 172/DSD | 19/02/2021 | 21 | RELIABLE ENGINEERS CO.-OPERATIVE CONSTRUCTION SOCIETY LTD. | 4.73 | 0 | 0 | 1
4282 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block , SM/07808 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PRATAPPUR Piped Water Supply Scheme at Raniganj (Part), Babuisol (Part), Pratappur (Part), village, habitation, Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. | 5482/BWD | 13/12/2023 | 30 | N.S. ENTERPRISE | 10.92 | 9.66 | 100 | 100
4283 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Pratappur Piped Water Supply Scheme at Ausgram-II Block , SM/07808 | Retrofitting | Acceptance cum Formal Work Order for the work of Supplying and Laying of different dia UPVC pipe (LDS) including providing FHTC at Pratappur under PRATAPPUR PWSS, Block- Aushgram-II, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte | 770/DWSD | 06/06/2024 | 422 | KIRON ENTERPRISE | 27.17 | 11.14 | 41.46 | 100
4284 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ura Piped Water Supply Scheme at Galsi-II Block , SM/07810 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of URA Piped Water Supply Scheme at Ura (1 No Part & 1 No Habitation), Sarul (2 Nos Habitation) & Adrahati Village (Mouza), Gaisi-II Block under Burdwan Division, PHE Dte..(Agreement No. 95/SE/CC/PHE/Dte of 2020-2021) | 1087/BWD | 08/02/2021 | 60 | M/S PURBASHA | 66.7 | 51.62 | 116.07 | 1
4285 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ura Piped Water Supply Scheme at Galsi-II Block , SM/07810 | Retrofitting | Construction of drain and pathway at Head work site of URA piped water supply scheme, Block-Galsi-II within Durgapur (Bardhaman North) Sub-Division, under Burdwan Division, PHE Dte. SL-03 | 648/DSD | 03/11/2022 | 30 | M/S PURBASHA | 3.66 | 3.62 | 100 | 1
4286 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ura Piped Water Supply Scheme at Galsi-II Block , SM/07810 | Retrofitting | Quotation for new service connection at URA PWSS TW-I under CMD/PHED | BP-2024-25-104 | 03/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 6.65 | 0 | 0 | 0
4287 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09406 | Augmentation | Route Survey and preparation of DPR for BAHARAN BIRHIMPUR PWSS under Ketugram-II Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-01] | 43/KTS | 24/01/2022 | 21 | RADIANT | 2.6 | 2.6 | 100 | 1
4288 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09406 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4289 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09406 | Augmentation | Material Requisition To Resource Division | 882/BWD | 11/02/2022 | 0 | Resource Division | 7.08 | 0 | 0 | 0
4290 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09406 | Augmentation | Material Requisition To Resource Division | 534/BWD | 27/01/2022 | 0 | Resource Division | 11.25 | 0 | 0 | 0
4291 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09406 | Augmentation | Material Requisition To Resource Division | 1525/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
4292 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based BAHARAN-BIRHIMPUR PWSS to accommodate FHTC in Ketugram-II block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09406 | Augmentation | Augmentation of BAHRAN BIRAHIMPUR Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation with repairing of Pump house -I & II under Ketugram-II Block, District:- Purba-Burdwan. | 2252/BWD | 02/05/2022 | 365 | ASHOK MITRA | 290.62 | 223.89 | 77.04 | 100
4293 | PURBA BARDHAMAN | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District , SM/09414 | Augmentation | Preparation of DPR for augmentation of Monteswar W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-F) | 208/KSD | 23/02/2022 | 21 | INDRANIL DUTTA & ASSOCIATES | 2.75 | 2.73 | 100 | 1
4294 | PURBA BARDHAMAN | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District , SM/09414 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Jahannagar, Ganganandapur, Nowapara & Monteswar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, P.H.E. Dte.[Part B] | 3728/BWD | 30/08/2022 | 20 | NANDY UDYOG | 2.88 | 2.88 | 100 | 1
4295 | PURBA BARDHAMAN | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District , SM/09414 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4296 | PURBA BARDHAMAN | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District , SM/09414 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Jahannagar, Ganganandapur, Nowapara & Monteswar Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, P.H.E. Dte.[Part ¿ A] | 3632/BWD | 22/08/2022 | 20 | RAMASISH ENTERPRISE | 12.8 | 3.2 | 100 | 1
4297 | PURBA BARDHAMAN | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District , SM/09414 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 1ST TW Site of Aug. of MONTESWAR & its adjoining mouzas Piped Water Supply Scheme, Block ? Monteswar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 5178/BWD | 23/11/2022 | 30 | ANIRUDDHA FARUQUE | 8.73 | 7.9 | 100 | 100
4298 | PURBA BARDHAMAN | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District , SM/09414 | Augmentation | Work Order for "Surging of existing 300 x 200 mm dia Tube Well depth 123 mtr & lowering of part tube well 200 x 150 mm dia depth , existing 300 x 200 mm dia tube well at Manteswar zone-I under Kalna Sub-Division , PHE Dte." | 1306/KSD | 23/08/2023 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 4.2 | 4.16 | 100 | 100
4299 | PURBA BARDHAMAN | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District , SM/09414 | Augmentation | Material Requisition To Resource Division | 563/BWD | 27/01/2022 | 0 | Resource Division | 14.37 | 0 | 0 | 0
4300 | PURBA BARDHAMAN | Burdwan Division | Augmentation of MANTESWAR PWSS for providing functional household tap connection FHTC in Manteswar block under Burdwan Division in Purba Bardhaman District , SM/09414 | Augmentation | Quotation for new service connection charges of Monteswar PWSS.[PH No.-3] | 1085/JJM | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.99 | 0 | 0 | 0
4301 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08705 | Retrofitting | Material Requisition To Resource Division | 1103/BWD | 26/02/2022 | 0 | Resource Division | 12.3 | 0 | 0 | 0
4302 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08705 | Retrofitting | Acceptance cum Formal Work Order for the work of "Sinking of 300 x 200 mm x 150 mtr deapth by DR, Repairing & Renovation of existing OHR, Construction of 01 (One) no 5.25 x 3.25 m Pump House cum Chlorine Room including laying UPVC distribution system (LDS) and interconnection & other allied works at CHAKTETUL PWSS, Block- Galsi-I, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 759/DWSD | 06/06/2024 | 270 | M/S JAYDEEP DASGUPTA | 77.42 | 23.36 | 30.17 | 90
4303 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08705 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of CHAKTENTUL Piped Water Supply Scheme at Chaktentul (1 No Part, 2 Nos Habitation), Bharatpur (2 Nos Habitation) Village (Mouza), Galsi-I Block under Burdwan Division, PHE Dte.(Agreement No. 71/2020-2021 OF SE/CC/PHE. DTE.) | 5005/BWD | 10/12/2020 | 90 | SUPRIYA RAY | 75.14 | 25 | 100 | 1
4304 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08705 | Retrofitting | Quotation for new service connection at Chaktetul Ausgram -I PWSS under CMD/PHED | BP-2024-25-99 | 27/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LIMITED | 9.38 | 0 | 0 | 0
4305 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Bharatpur, Nskarbandh and Shaldanga mouzas within the command area of Chaktentul piped Water Supply Scheme at Galsi-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08705 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Galsi ¿ I Block under Burdwan Division, PHE. Dte._2ND CALL. | 1738/BWD | 28/03/2022 | 1101 | JYOTI ENTERPRISE | 5.72 | 0 | 0 | 100
4306 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08715 | Retrofitting | Construction of concrete path way at Head Work Site & 2nd & 3rd Tube Well site along with plinth protection of Pump House No-I & laying of 200 mm dia DI Pipe for wash out and over flow drain of existing OHR of Putsuri W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2218/BWD | 28/04/2022 | 30 | BISHWAJIT DAS | 4.07 | 0 | 0 | 0
4307 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08715 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PUTSURI Piped Water Supply Scheme at Kasa (6 Nos. Habs.), Purba Balarampur, Bhurkunda (7 Nos. Habs.), Patun (5 Nos. Habs.) & Bigha (3 Nos. Habs.) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte. | 7020/BWD | 17/12/2021 | 60 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 53.94 | 45.21 | 100 | 1
4308 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08715 | Retrofitting | Laying of different dia.UPVC pipeline at the damaged portion from Denur to Mousa Daukadanga under Putsuri & its adjoining mouzas water supply scheme within Kalna Sub-Division, under Burdwan Division, PHE Dte. | 6013/BWD | 05/10/2021 | 30 | D.M. ENTERPRISE | 23.17 | 0 | 0 | 1
4309 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08715 | Retrofitting | Sinking of Tube Well, Construction of Pump House, Boundary wall & interconnection work of Kasa village of PUTSURI Water Supply Scheme within Kalna Sub-Division under Burdwan division, PHE Dte. | 4532/BWD | 13/10/2023 | 60 | B.S. ENTERPRISE | 27.32 | 14.54 | 53.23 | 40
4310 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08715 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Putsuri Piped Water Supply Scheme at Denur (6 Nos Habitation Part) & Putsuri (11 Nos Habitation Part) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte.(Agreement No. 55/2020-2021 OF SE/CC/PHE. DTE.) | 4887/BWD | 07/12/2020 | 90 | M/S S. CHOUDHURY | 77.12 | 16 | 100 | 1
4311 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08715 | Retrofitting | Construction of Pump House cum switch room (5.40m x 3.60m) with sanitary arrangement (As per drawing no-PHE/SE/CC/PH/ DWG-01/2022-2023) at Aug. of MANTESWAR Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. 1 No Pump House. | 467/BWD | 05/02/2024 | 60 | BISHWAJIT DAS | 5.86 | 0 | 0 | 100
4312 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Kasa, Denur, Patun and Bigha mouzas within the command area of Putsuri piped Water Supply Scheme at Manteswar Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08715 | Retrofitting | Providing FHTC with laying of 75 mm dia HDPE Pipe of Putsuri PWSS of Hazra para Paschim village under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | 265/DSD | 15/03/2024 | 113 | PRONAB KUMAR DEY | 0.95 | 0.95 | 100 | 100
4313 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09493 | Augmentation | Route Survey & Preparation of DPR for Raina W/S Scheme under Raina-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.12. | 187/BSD | 31/01/2022 | 30 | RADIANT | 2.72 | 2.71 | 100 | 1
4314 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09493 | Augmentation | Quotation for shifting of 11 KV Raina Local Feeder at Raina PHE under Burdwan South Division, WBSEDCL.[Ref ID-860249099, App ID-100000061079, dt.-22/09/2022] | 675/DW/22-23 | 29/09/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.94 | 0 | 0 | 0
4315 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09493 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4316 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09493 | Augmentation | Laying Distribution of 160 mm dia HDPE pipeline for Augmentation of RAINA Piped Water Supply Scheme AT NODE 138 to 135, 135 to 119, 119 to 114, 114 to 110 to 105, 105 to 93 within Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.B. | 1404/BSD | 10/08/2022 | 45 | RANADHIR SINHA | 4.77 | 3.53 | 100 | 0
4317 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09493 | Augmentation | Supply of 100 mm dia C.I. Sluice valve (P.N.-I) of Augmentation of Raina water supply scheme of Raina-I under Burdwan sub division, PHE Dte. Gr.C. | 1851/BSD | 21/10/2022 | 15 | SINHA BROTHERS | 0.47 | 0.47 | 100 | 1
4318 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09493 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of RAINA W/S Scheme (H.W SITE) under Raina-I Block within Burdwan Sub-Division, PHE Dte. [For 01 No. Tube well]. | 2697/BWD | 08/06/2023 | 30 | RANADHIR SINHA | 13.2 | 11.37 | 100 | 100
4319 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09493 | Augmentation | Restoration work at various location at Thanar Danga to Nandipara Kalitala via.Ranapara and Raina Co-Operative Society of Augmentation of Raina Water Supply Scheme at Raina-I Block within under Burdwan Division,PHE Dte. | 1004/BSD | 06/06/2023 | 15 | SOUMYAVASH DAS | 0.95 | 0.94 | 100 | 100
4320 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09493 | Augmentation | Material Requisition To Resource Division | 559/BWD | 27/01/2022 | 0 | Resource Division | 12.84 | 0 | 0 | 0
4321 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09493 | Augmentation | Material Requisition To Resource Division | 932/BWD | 16/02/2022 | 0 | Resource Division | 23.01 | 0 | 0 | 0
4322 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09493 | Augmentation | Material Requisition To Resource Division | 1540/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
4323 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09493 | Augmentation | Augmentation of RAINA Piped Water Supply Scheme with LDS, FHTC, Rising Main & Construction of 300 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test under Raina ¿ I Block, District - Purba Bardhaman. | 1475/BWD | 14/03/2022 | 365 | RANADHIR SINHA | 319.21 | 251.96 | 82.03 | 100
4324 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based RAINA PWSS to accommodate FHTC in Raina-I block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09493 | Augmentation | Quotation for new service connection of Augmentation of Raina water supply scheme.[REF ID-503550762][TW-3] | 1367/JJM | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.08 | 0 | 0 | 0
4325 | PURBA BARDHAMAN | Burdwan Division | Rejuvenation of Bhalki Water Supply Scheme. , SM/09103 | Augmentation | Restoration of Pipeline by Re-Laying of Pipe Line for Rejuvenation of BHALKI and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block under Burdwan Division, P.H.E. Dte. | 3877/BWD | 27/07/2021 | 60 | ASHOK KUMAR GHOSH | 279.81 | 276.39 | 80.02 | 1
4326 | PURBA BARDHAMAN | Burdwan Division | Rejuvenation of Bhalki Water Supply Scheme. , SM/09103 | Augmentation | Construction of Drain and restoration of connection for Augmentation of BHALKI W/S Scheme , Block- Ausgram-II, under Durgapur (Burdwan North)Sub Division Burdwan Division, P.H.E. Dte. [SL-B] | 334/DSD | 27/06/2022 | 30 | TAUSIF HOSSAIN MONDAL | 1.88 | 1.87 | 100 | 1
4327 | PURBA BARDHAMAN | Burdwan Division | Rejuvenation of Bhalki Water Supply Scheme. , SM/09103 | Augmentation | Making structure with GI pipe for provision of joining and laying of pipeline near Abhirampur branch Canal for Bhalki and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-H] | 349/DSD | 30/06/2022 | 45 | PARTHA RAY | 1.9 | 1.82 | 100 | 1
4328 | PURBA BARDHAMAN | Burdwan Division | Rejuvenation of Bhalki Water Supply Scheme. , SM/09103 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system with within the command area of augmentation BHALKI Piped Water Supply Scheme at Bhalki (Part), Chandipur (Part), Samantapara (Part), Telota (Part) & Abhirampuri (Part) village, habitation, Ausgram-II Block within Durgapur (Burdwan North) Sub Division under Burdwan Division, P.H.E. Dte. | 1907/BWD | 07/04/2022 | 30 | ROY CONSTRUCTION | 49.52 | 0 | 0 | 1
4329 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Preparation of DPR for augmentation of Patuli W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | 181/KSD | 21/02/2022 | 21 | M/S R. DUTTA & CO. | 3.75 | 3.81 | 100 | 1
4330 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4331 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Supply of materials for different water supply schemes under Burdwan Division, PHE Dte. | 1194/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 62.76 | 0 | 0 | 0
4332 | PURBA BARDHAMAN | Central Mechanical | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of Patuli (Zone - II) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2566/CMD | 06/06/2023 | 30 | M/S. S.R. ENTERPRISE | 21.77 | 0 | 0 | 0
4333 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Work Order for "Replacement of Valve and Restoration of Concrete Roads at Patuli Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | 1304/KSD | 23/08/2023 | 30 | IYASIN DAFADAR | 4.09 | 4.04 | 100 | 100
4334 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Material Requisition To Resource Division | 7348/BWD | 30/12/2021 | 0 | Resource Division | 13.73 | 0 | 0 | 0
4335 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Material Requisition To Resource Division | 1378/BWD | 09/03/2022 | 0 | Resource Division | 4.45 | 0 | 0 | 0
4336 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Material Requisition To Resource Division | 1325/BWD | 08/03/2022 | 0 | Resource Division | 74.18 | 0 | 0 | 0
4337 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Material Requisition To Resource Division | 557/BWD | 27/01/2022 | 0 | Resource Division | 22.05 | 0 | 0 | 0
4338 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Material Requisition To Resource Division | 1557/BWD | 15/03/2022 | 0 | Resource Division | 0 | 0 | 0 | 0
4339 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Material Requisition To Resource Division | 769/BWD | 07/02/2022 | 0 | Resource Division | 51.93 | 0 | 0 | 0
4340 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Load enhancement charges of Aug of Patuli water supply scheme under Burdwan Division, PHE Dte. | 665/JJM | 21/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.03 | 0 | 0 | 0
4341 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at H.W & 2nd Tubewell site for PATULI (Zone-I & II) Piped Water Supply Scheme, Block - Purbasthali - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 + 2 = 4 Nos. GTW]. | 1621/BWD | 21/03/2022 | 1025 | AUXILIARY TUBE WELL DRILLERS | 31.66 | 7.65 | 24.17 | 50
4342 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Augmentation of PATULI Water Supply Scheme (Zone-I & II) with LDS, Rising Main, FHTC work, Pump House & Boundary Wall of Purbasthali - II Block in Kalna Sub-Division, District - Purba Bardhaman under Burdwan Division, PHE. Dte. | 256/BWD | 13/01/2022 | 180 | IJABUL SEKH | 407.57 | 365.05 | 100 | 80
4343 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Work Order for " Restoration of Pipeline and Other Allied Works i.c.w. Augmentation of PATULI(SM/09718) Piped Water Supply Scheme under PURBASTHALI-II Block,Kalna Sub-Division, District:- Purba Bardhaman." | 2191/KSD | 15/03/2024 | 10 | IYASIN DAFADAR | 4.52 | 4.51 | 100 | 2
4344 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Quotation from WBSEDCL for new service connection of Augmentation of Patuli TW-3 Water supply scheme under Burdwan Division, PHE Dte. | 826/JJM | 18/09/2024 | 0 | WBSEDCL | 7.53 | 0 | 0 | 0
4345 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Patuli PWSS for providing FHTC under Burdwan Divison. , SM/09718 | Augmentation | Different types of works involve in connection with Augmentation of JHAUDANGA (SM/16293), KASHIPUR (SM/16297), PATULI (SM/09718) & PARULIA (SM/09719) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | 2202/BWD | 13/06/2024 | 631 | MONDAL PRECISION PVT LTD | 570 | 55.42 | 92.37 | 2
4346 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09719 | Augmentation | Preparation of DPR for augmentation of Parulia W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-D) | 216/KSD | 24/02/2022 | 21 | M/S R. DUTTA & CO. | 2.84 | 2.79 | 100 | 1
4347 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09719 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4348 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09719 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Deep Well Screen (RMS) for 2nd TW Site of Aug. of PARULIA & its adjoining mouzas Piped Water Supply Scheme, Block ? Purbasthali ? II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 5126/BWD | 21/11/2022 | 30 | M/S SYCHROTECH INDUSTRY | 8.72 | 8.18 | 93.81 | 0
4349 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09719 | Augmentation | Material Requisition To Resource Division | 535/BWD | 27/01/2022 | 0 | Resource Division | 14.55 | 0 | 0 | 0
4350 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09719 | Augmentation | Material Requisition To Resource Division | 604/BWD | 28/01/2022 | 0 | Resource Division | 24.12 | 0 | 0 | 0
4351 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09719 | Augmentation | Material Requisition To Resource Division | 906/BWD | 15/02/2022 | 0 | Resource Division | 6.93 | 0 | 0 | 0
4352 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09719 | Augmentation | Material Requisition To Resource Division | 1564/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
4353 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09719 | Augmentation | Material Requisition To Resource Division | 4632/BWD | 17/10/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
4354 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09719 | Augmentation | Augmentation of PARULIA Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction 300 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Construction of Boundary wall under Kalna Sub-Division, Block ¿ Purbasthali ¿ II, Dist. - Purba Bardhaman under Burdwan Division, PHE. Dte. | 699/BWD | 02/02/2022 | 365 | M/S ASHA CONSTRUCTION | 407.54 | 379.29 | 93.07 | 100
4355 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Parulia PWSS for providing Functional House Hold Tap Connection (FHTC) , SM/09719 | Augmentation | Different types of works involve in connection with Augmentation of JHAUDANGA (SM/16293), KASHIPUR (SM/16297), PATULI (SM/09718) & PARULIA (SM/09719) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | 2202/BWD | 13/06/2024 | 631 | MONDAL PRECISION PVT LTD | 570 | 0 | 0 | 2
4356 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT , SM/08998 | Augmentation | Route Survey & Preparation of DPR for Parhati W/S Scheme under Memari-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.13. | 188/BSD | 31/01/2022 | 30 | RADIANT | 2.72 | 2.72 | 100 | 1
4357 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT , SM/08998 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4358 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT , SM/08998 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of Paharhati, Nababhat, Shyamsundar & Dewandighi-Mirzapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. | 4703/BWD | 19/10/2022 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 14.45 | 3.61 | 100 | 1
4359 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT , SM/08998 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PARHATI Piped Water Supply Scheme (Mouza- Akalia, Chandipur, Ganti, Kabastigiri, Kanpur, Kasipur, Madhupur, Parhati, Tajpur) of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 5193/BWD | 24/11/2022 | 45 | ANWESHA CONSTRUCTION | 39.72 | 39.67 | 100 | 1
4360 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT , SM/08998 | Augmentation | Material Requisition To Resource Division | 904/BWD | 15/02/2022 | 0 | Resource Division | 11.38 | 0 | 0 | 0
4361 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT , SM/08998 | Augmentation | Material Requisition To Resource Division | 549/BWD | 27/01/2022 | 0 | Resource Division | 16.9 | 0 | 0 | 0
4362 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT , SM/08998 | Augmentation | Material Requisition To Resource Division | 1521/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
4363 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT , SM/08998 | Augmentation | Providing Balance Functional Household Tap Connection (848 nos FHTC) from existing distribution system within the command area of PARHATI Piped Water Supply Scheme at (Akalia, Chandipur, Ganti, Kabastigiri, Kanpur, Kasipur, Madhupur, Parhati, Tajpur) Mouza, Construction of boundary wall at head work site & 2nd T/W site under MEMARI-II Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1363/BWD | 22/03/2023 | 60 | ASHOK KUMAR GHOSH | 53.71 | 26.86 | 50.08 | 100
4364 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PARHATI PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BURDWAN DISTRICT , SM/08998 | Augmentation | Augmentation of PARHATI Piped Water Supply Scheme with LDS, Construction of 350 Cum capacity OHR with 20.0 Mtgr. Staging height inclusive of soil test & FHTC under Memari - II Block, District - Purba Bardhaman. | 1472/BWD | 14/03/2022 | 365 | ASHOK KUMAR GHOSH | 361.27 | 334.18 | 100 | 100
4365 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4366 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Installation of a Voltage correcting device along with allied accessories at DHATRIGRAM Water Supply Scheme, Pump house-2 under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 497/CMSD-I | 13/06/2023 | 21 | SUDIKSHA CONSTRUCTION | 3.48 | 3.48 | 100 | 0
4367 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Supply and Installation of Submersible Pumping Machinery for breakdown maintenance along with allied accessories for Tube Well no- 3A & Lowering of pumping machinery at T.W-3B at DHATRIGRAM and some other works at jot raghab & Deriapur Water Supply Scheme, under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 387/CMSD-I | 19/04/2023 | 21 | CHOUDHURY ENTERPRISE | 0.69 | 0.69 | 100 | 0
4368 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Preparation of DPR for augmentation of Dhatrigram W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-C) | 183/KSD | 21/02/2022 | 21 | LEMNISCATE | 3.17 | 3.17 | 100 | 1
4369 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Restoration of existing concrete road and HDD Boring for laying distribution system of augmentation of Dhatrigram Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2055/BWD | 04/05/2023 | 60 | PUSPA ENTERPRISE | 38.67 | 38.67 | 100 | 100
4370 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of DHATRIGRAM Piped Water Supply Scheme, Block - Kalna - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. | 2710/BWD | 08/06/2023 | 45 | AUXILIARY TUBE WELL DRILLERS | 19.76 | 18.22 | 100 | 100
4371 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Material Requisition To Resource Division | 1336/BWD | 08/03/2022 | 0 | Resource Division | 70.03 | 0 | 0 | 0
4372 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Material Requisition To Resource Division | 1552/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
4373 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Material Requisition To Resource Division | 1382/BWD | 09/03/2022 | 0 | Resource Division | 3.88 | 0 | 0 | 0
4374 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Material Requisition To Resource Division | 4850/BWD | 20/10/2022 | 0 | Resource Division | 15.4 | 0 | 0 | 0
4375 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | New service connection charges for Dhatrigram PWSS TW 4 | BP-2023-24-181 | 04/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.35 | 0 | 0 | 0
4376 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | New service connection charges for Dhatrigram PWSS TW-7 | BP-2023-24-182 | 04/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.36 | 0 | 0 | 0
4377 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Shifting of pipe line of DHATRIGRAM Piped Water Supply Scheme for widening of road from Nabadwip more to Dhatrigram rail gate along the Dhatrigram-Burdwan road within Kalna Sub-Division under Burdwan Division, PHE Dte. | 4281/BWD | 29/09/2023 | 60 | IYASIN DAFADAR | 11.99 | 9.52 | 100 | 100
4378 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Additional Quotation for new service connection for Dhatrigram Daspara PWSS . | BP-2024-25-151 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.45 | 0 | 0 | 0
4379 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3105/CMD | 11/12/2024 | 60 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0 | 0
4380 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Augmentation of Dhatrigram Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of new 500 cum capacity OHR with 20.0 mtr. Staging height with soil investigation including construction of 5(five) nos. switch-room(5.40mx3.6m), construction of five nos. new boundary wall for new TW sites & repairing of existing OHR, switch room & boundary wall under Kalna-I Block, District:- Purba-Burdwan. | 3046/BWD | 08/07/2022 | 1029 | PUSPA ENTERPRISE | 697.5 | 574.11 | 90.16 | 70
4381 | PURBA BARDHAMAN | Burdwan Division | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Additional pipe laying and other allied works of distribution system for construction of New OHR Site within the command area of Aug. of DHATRIGRAM Piped Water Supply Scheme of KALNA Sub-Division under Burdwan Division, PHE Dte. | 004/BWD | 02/01/2024 | 243 | PUSPA ENTERPRISE | 55.13 | 17.99 | 87.78 | 33
4382 | PURBA BARDHAMAN | Central Mechanical | DETAILED PROJECT REPORT FOR AUGMENTATION F GROUND WATER BASED DHATRIGRAM PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10270 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 4 & 5 at Augumentation of DHATRIGRAM Water Supply Scheme [BLOCK- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1543/CMD | 05/03/2024 | 60 | M/S. SWAPAN BANERJEE | 24.62 | 23.42 | 95.59 | 90
4383 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09404 | Augmentation | Route Survey & Preparation of DPR for Khandaghosh W/S Scheme under Khandaghosh Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.15. | 190/BSD | 31/01/2022 | 30 | RADIANT | 3.01 | 3.01 | 100 | 1
4384 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09404 | Augmentation | Dismantling of concrete road for Augmentation of KHANDAGHOSH Pipe water supply scheme (Mouza: Khandaghosh, Lodna, Barisiali, Kapshit, Nabagram, Metedanga) at Khandaghosh Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. Gr.B. | 1466/BSD | 25/08/2022 | 45 | JMD ENGINEERING INFRASTRUCTURE COMPANY | 4.84 | 4.69 | 100 | 1
4385 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09404 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4386 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09404 | Augmentation | Supply and delivery of different dia. CIDF sluice valve for Augmentation of KHANDAGHOSH Piped Water Supply Scheme under Burdwan Division, P.H.E. Dte._SL. No. 07 | 141/AE/HQ | 16/03/2022 | 10 | MAKALI ENGINEERING CORPORATION | 4.52 | 0 | 0 | 0
4387 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09404 | Augmentation | Augmentation of KHANDAGHOSH Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 600 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation & construction of boundary wall at Head works, 2nd TW & 3rd TW site under Khandaghosh Block, District - Purba Bardhaman. | 1967/BWD | 12/04/2022 | 365 | M/S JAN MAHAMMAD | 666.04 | 665.97 | 100 | 100
4388 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09404 | Augmentation | Material Requisition To Resource Division | 565/BWD | 27/01/2022 | 0 | Resource Division | 25.72 | 0 | 0 | 0
4389 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09404 | Augmentation | Material Requisition To Resource Division | 1528/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
4390 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09404 | Augmentation | Material Requisition To Resource Division | 951/BWD | 17/02/2022 | 0 | Resource Division | 59.29 | 0 | 0 | 0
4391 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09404 | Augmentation | Material Requisition To Resource Division | 3278/BWD | 29/07/2022 | 0 | Resource Division | 34.57 | 0 | 0 | 0
4392 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09404 | Augmentation | Construction of Boundary wall at Head Works Site of Aug. of KHANDAGHOSH Water Supply Scheme under KHANDAGHOSH Block of Burdwan Division, PHE Dte. (Length -210.00 Mtr, Col-80 Nos). | 3631/BWD | 21/08/2023 | 60 | ROY ASSOCIATE | 28.73 | 28.7 | 100 | 100
4393 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09404 | Augmentation | Restoration work of hard shoulder at Badulia Khandaghosh Road from 12.00 to 13.00 km (L/S) due to laying of water supply pipeline by PHE Dte. under Sadarghat Highway Sub-Division No.-I of Burdwan South Highway Division, P.W. Roads Dte. in the district of Purba Bardhaman. | 565/JJM | 23/07/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 8.12 | 0 | 0 | 0
4394 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based KHANDOGHOSH PWSS to accommodate FHTC in Khandoghosh block under Burdwan Sub Division of Burdwan Division in Purba Bardhaman District , SM/09404 | Augmentation | Providing Balance Functional Household Tap Connection (372 nos FHTC) from existing distribution system within the command area of KHANDAGHOSH Piped Water Supply Scheme at (Khandaghosh, Lodna, Metedanga, Nabagram, Kapsit, Barsiali) Mouza under KHANDAGHOSH Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 2689/BWD | 08/06/2023 | 30 | KAUSHIK RAY | 16.73 | 0 | 0 | 100
4395 | PURBA BARDHAMAN | Burdwan Division | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/14021 | New | Material Requisition To Resource Division | 1241/BWD | 17/03/2023 | 0 | Resource Division | 3.55 | 0 | 0 | 0
4396 | PURBA BARDHAMAN | Burdwan Division | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/14021 | New | Material Requisition To Resource Division | 4001/BWD | 08/09/2023 | 0 | Resource Division | 1.09 | 0 | 0 | 0
4397 | PURBA BARDHAMAN | Central Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/14021 | New | Damage restoration charges in connection with WBSEDCL electrification under Rajapur PWSS | BP-2023-24-176 | 29/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.1 | 0 | 0 | 0
4398 | PURBA BARDHAMAN | Central Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/14021 | New | New service connection charges for Rajapur PWSS TW-1 | BP-2023-24-120 | 17/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.97 | 0 | 0 | 0
4399 | PURBA BARDHAMAN | Central Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/14021 | New | New service connection charges for Rajapur PWSS TW-2 | BP-2023-24-121 | 17/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.51 | 0 | 0 | 0
4400 | PURBA BARDHAMAN | Burdwan Division | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/14021 | New | Material Requisition To Resource Division | 298/BWD | 24/01/2024 | 0 | Resource Division | 8.86 | 0 | 0 | 0
4401 | PURBA BARDHAMAN | Central Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/14021 | New | Addl. New service connection charges for Rajapur PWSS TW-1 | BP-2023-24-245 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.76 | 0 | 0 | 0
4402 | PURBA BARDHAMAN | Burdwan Division | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/14021 | New | RAJAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under PURBASTHALI-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 359/BWD | 30/01/2023 | 519 | PABITRA KUMAR SAMANTA | 116.35 | 92.7 | 92.32 | 90
4403 | PURBA BARDHAMAN | Central Mechanical | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/14021 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at RAJAPUR Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2516/CMD | 02/06/2023 | 30 | M/S GHOSH ENTERPRISE | 20.8 | 12.62 | 92.08 | 90
4404 | PURBA BARDHAMAN | Burdwan Division | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/14021 | New | Work order for ' Laying of Pipeline and providing FHTC under Rajapur(SM/16308) and Sadhpukharia PWSS (SM/14021) under Kalna Sub-Division under Burdwan Division, PHE Dte. '. | 1775/KSD | 20/11/2024 | 39 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 3.33 | 3.08 | 100 | 100
4405 | PURBA BARDHAMAN | Burdwan Division | RAJAPUR PIPED WATER SUPPLY SCHEME , SM/14021 | New | Additional work for Increasing height of boundary wall & land development work and construction of retaining wall at 2nd TW site and construction of approach road at 1st TW Site of RAJAPUR Water Supply Scheme at Purbasthali-I Block within Kalna Sub- Division under Burdwan Division, PHE Dte. | 782/BWD | 27/02/2024 | 30 | THE BENGAL HARDWARE | 11.55 | 8.03 | 100 | 100
4406 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13280 | New | Material Requisition To Resource Division | 1243/BWD | 17/03/2023 | 0 | Resource Division | 10.3 | 0 | 0 | 0
4407 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13280 | New | Material Requisition To Resource Division | 1632/BWD | 06/04/2023 | 0 | Resource Division | 11.55 | 0 | 0 | 0
4408 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13280 | New | Material Requisition To Resource Division | 4885/BWD | 10/11/2023 | 0 | Resource Division | 33.21 | 0 | 0 | 0
4409 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13280 | New | New service connection charges for Sutra PWSS TW-1 | BP-2023-24-80 | 25/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.89 | 0 | 0 | 0
4410 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13280 | New | New service connection charges for Sutra PWSS TW-2 | BP-2023-24-81 | 25/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.84 | 0 | 0 | 0
4411 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13280 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sutra Water Supply Scheme [ Block- Monteswar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2967/CMD | 17/07/2023 | 30 | M.S. ENTERPRISE | 27.67 | 1.09 | 4.7 | 100
4412 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13280 | New | Laying of additional pipeline and providing FHTC at SUTRA water supply scheme under Kalna Sub-Division, Burdwan Division, PHE Dte. | 2175/BWD | 12/06/2024 | 120 | DUBE ENTERPRISE | 42.09 | 22.92 | 50.84 | 40
4413 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13280 | New | SUPPLY & INSTALLATION WORKS FOR SUTRA PWSS | BP-2023-24-558 | 21/02/2024 | 0 | M.S. ENTERPRISE | 21.99 | 0 | 0 | 0
4414 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13280 | New | Balance work for laying of pipeline, providing FHTC & other allied works in connection with Augmentation of MONTESWAR PWSS & SUTRA PWSS (SM/13280) under Kalna Sub-Division under Burdwan Division, PHE Dte. | 3572/BWD | 27/09/2024 | 181 | BAKSHI ENTERPRISE | 51.14 | 0 | 0 | 30
4415 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR SUTRA PWSS IN MANTESHWAR BLOCK OF PURBA BURDWAN DISTRICT UNDER BURDWAN DIVISION, P.H.E. DTE. , SM/13280 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
4416 | PURBA BARDHAMAN | Burdwan Division | CHAK CHANDAN PIPED WATER SUPPLY SCHEME , SM/13281 | New | Material Requisition To Resource Division | 1898/BWD | 12/05/2023 | 0 | Resource Division | 11.69 | 0 | 0 | 0
4417 | PURBA BARDHAMAN | Burdwan Division | CHAK CHANDAN PIPED WATER SUPPLY SCHEME , SM/13281 | New | Material Requisition To Resource Division | 4028/BWD | 08/09/2023 | 0 | Resource Division | 8.29 | 0 | 0 | 0
4418 | PURBA BARDHAMAN | Burdwan Division | CHAK CHANDAN PIPED WATER SUPPLY SCHEME , SM/13281 | New | Material Requisition To Resource Division | 5118/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
4419 | PURBA BARDHAMAN | Central Mechanical | CHAK CHANDAN PIPED WATER SUPPLY SCHEME , SM/13281 | New | New service connection charges for Chak Chandan PWSS TW-1 | BP-2023-24-220 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.07 | 0 | 0 | 0
4420 | PURBA BARDHAMAN | Central Mechanical | CHAK CHANDAN PIPED WATER SUPPLY SCHEME , SM/13281 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
4421 | PURBA BARDHAMAN | Central Mechanical | CHAK CHANDAN PIPED WATER SUPPLY SCHEME , SM/13281 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chak Chandan Water Supply Scheme [ Block- Raina-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4037/CMD | 29/08/2023 | 30 | M/S. S.R. ENTERPRISE | 28.98 | 22.75 | 95.45 | 96
4422 | PURBA BARDHAMAN | Central Mechanical | CHAK CHANDAN PIPED WATER SUPPLY SCHEME , SM/13281 | New | Emergency installation (for urgent FHTC) at Chak Chandan Water Supply Scheme PH 1 (part-3) under CMD, PHE Dte., Dist.- Purba-Bardhaman | 82/CMSD | 15/01/2024 | 12 | CHOUDHURY ENTERPRISE | 0.88 | 0.88 | 100 | 100
4423 | PURBA BARDHAMAN | Central Mechanical | CHAK CHANDAN PIPED WATER SUPPLY SCHEME , SM/13281 | New | New electric connection for Chakchandan PWSS, PH-2. | BP-2023-24-340 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.49 | 0 | 0 | 0
4424 | PURBA BARDHAMAN | Burdwan Division | CHAK CHANDAN PIPED WATER SUPPLY SCHEME , SM/13281 | New | Continuation Work Order for Supply of one No.Diesel Driven Ambassador Car No. WB:41H-4009 on hire basis for the office of the Assistant Engineer,Burdwan Sub-Division,PHE Dte(Period from 01-03-2025 to 31.05.2025) | 457/BSD | 28/02/2025 | 90 | SK. ASFIA | 1.2 | 0 | 0 | 100
4425 | PURBA BARDHAMAN | Central Mechanical | CHAK CHANDAN PIPED WATER SUPPLY SCHEME , SM/13281 | New | Supply and delivery of submersible pumping machinery (for urgent FHTC) for Chak Chandan Water Supply Scheme PH 1 (part-2) under CMD, PHE Dte., Dist.- Purba-Bardhaman | 65/CMSD | 11/01/2024 | 12 | CHOUDHURY ENTERPRISE | 0.86 | 0.86 | 100 | 100
4426 | PURBA BARDHAMAN | Central Mechanical | CHAK CHANDAN PIPED WATER SUPPLY SCHEME , SM/13281 | New | Delivery of different Electro-mechanical items (for urgent FHTC) for Chak Chandan Water Supply Scheme PH 1 (part-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | 08/CMSD | 02/01/2024 | 40 | CHOUDHURY ENTERPRISE | 0.92 | 0.92 | 100 | 100
4427 | PURBA BARDHAMAN | Central Mechanical | KALIGRAM PIPED WATER SUPPLY SCHEME , SM/13940 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kaligram Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3998/CMD | 29/08/2023 | 30 | MITRA ENTERPRISE | 28.83 | 0 | 0 | 0
4428 | PURBA BARDHAMAN | Burdwan Division | KALIGRAM PIPED WATER SUPPLY SCHEME , SM/13940 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.64 | 0 | 0 | 0
4429 | PURBA BARDHAMAN | Burdwan Division | KALIGRAM PIPED WATER SUPPLY SCHEME , SM/13940 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 18.63 | 0 | 0 | 0
4430 | PURBA BARDHAMAN | Burdwan Division | KALIGRAM PIPED WATER SUPPLY SCHEME , SM/13940 | New | Material Requisition To Resource Division | 5272/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
4431 | PURBA BARDHAMAN | Central Mechanical | KALIGRAM PIPED WATER SUPPLY SCHEME , SM/13940 | New | New service connection charges for Kaligram PWSS TW-1 | BP-2023-24-225 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.91 | 0 | 0 | 0
4432 | PURBA BARDHAMAN | Central Mechanical | KALIGRAM PIPED WATER SUPPLY SCHEME , SM/13940 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
4433 | PURBA BARDHAMAN | Central Mechanical | KALIGRAM PIPED WATER SUPPLY SCHEME , SM/13940 | New | Quotation for new service connection at KALIGRAM W/S Scheme PH-II. | BP-2023-24-305 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.57 | 0 | 0 | 0
4434 | PURBA BARDHAMAN | Burdwan Division | KALIGRAM PIPED WATER SUPPLY SCHEME , SM/13940 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KALIGRAM & PALITPUR Piped Water Supply Scheme under Burdwan I Block, District:- Purba Bardhaman [NEW SCHEME] | 3532/BWD | 10/08/2023 | 722 | SUPRITI ENTERPRISE | 704.5 | 127.6 | 31.12 | 50
4435 | PURBA BARDHAMAN | Burdwan Division | CHAGRAM PIPED WATER SUPPLY SCHEME , SM/13941 | New | Material Requisition To Resource Division | 1965/BWD | 26/04/2023 | 0 | Resource Division | 18.8 | 0 | 0 | 0
4436 | PURBA BARDHAMAN | Burdwan Division | CHAGRAM PIPED WATER SUPPLY SCHEME , SM/13941 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 10.42 | 0 | 0 | 0
4437 | PURBA BARDHAMAN | Burdwan Division | CHAGRAM PIPED WATER SUPPLY SCHEME , SM/13941 | New | Material Requisition To Resource Division | 5043/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
4438 | PURBA BARDHAMAN | Central Mechanical | CHAGRAM PIPED WATER SUPPLY SCHEME , SM/13941 | New | New service connection charges for Chagram PWSS TW-1 | BP-2023-24-95 | 02/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.24 | 0 | 0 | 0
4439 | PURBA BARDHAMAN | Central Mechanical | CHAGRAM PIPED WATER SUPPLY SCHEME , SM/13941 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chagram Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3068/CMD | 21/07/2023 | 30 | PADMA ENGINEERING CO. | 28.96 | 23.67 | 100 | 100
4440 | PURBA BARDHAMAN | Central Mechanical | CHAGRAM PIPED WATER SUPPLY SCHEME , SM/13941 | New | New Electric connection Chagram W/S PH-II | BP-2023-24-306 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.27 | 0 | 0 | 0
4441 | PURBA BARDHAMAN | Burdwan Division | CHAGRAM PIPED WATER SUPPLY SCHEME , SM/13941 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHAGRAM & KHEJURHATI Piped Water Supply Scheme under Khandaghosh Block, District:- Purba Bardhaman [NEW SCHEME] | 2080/BWD | 04/05/2023 | 698 | KHAN ENTERPRISE | 688.15 | 332.98 | 75 | 58
4442 | PURBA BARDHAMAN | Burdwan Division | CHAGRAM PIPED WATER SUPPLY SCHEME , SM/13941 | New | Balance work for providing Functional Household Tap Connection (FHTC) within command area GOPALBERA & CHAGRAM W/S. Scheme of Khandaghosh Block under Burdwan Divn., PHE. Dte. | 4438/BWD | 18/12/2024 | 253 | DUBE ENTERPRISE | 143.33 | 0 | 0 | 70
4443 | PURBA BARDHAMAN | Central Mechanical | CHAGRAM PIPED WATER SUPPLY SCHEME , SM/13941 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
4444 | PURBA BARDHAMAN | Burdwan Division | KOTALGHOSH PIPED WATER SUPPLY SCHEME , SM/14062 | New | Material Requisition To Resource Division | 1965/BWD | 26/04/2023 | 0 | Resource Division | 1.92 | 0 | 0 | 0
4445 | PURBA BARDHAMAN | Burdwan Division | KOTALGHOSH PIPED WATER SUPPLY SCHEME , SM/14062 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 1.48 | 0 | 0 | 0
4446 | PURBA BARDHAMAN | Central Mechanical | KOTALGHOSH PIPED WATER SUPPLY SCHEME , SM/14062 | New | New service connection charges for Kotalghosh PWSS TW-1 | BP-2023-24-183 | 04/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.28 | 0 | 0 | 0
4447 | PURBA BARDHAMAN | Central Mechanical | KOTALGHOSH PIPED WATER SUPPLY SCHEME , SM/14062 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
4448 | PURBA BARDHAMAN | Burdwan Division | KOTALGHOSH PIPED WATER SUPPLY SCHEME , SM/14062 | New | Material Requisition To Resource Division | 306/BWD | 24/01/2024 | 0 | Resource Division | 20.47 | 0 | 0 | 0
4449 | PURBA BARDHAMAN | Central Mechanical | KOTALGHOSH PIPED WATER SUPPLY SCHEME , SM/14062 | New | NEW SERVICE CONNECTION FOR KOTALGHOSH PWSS TW 2. | BP-2023-24-540 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.46 | 0 | 0 | 0
4450 | PURBA BARDHAMAN | Central Mechanical | KOTALGHOSH PIPED WATER SUPPLY SCHEME , SM/14062 | New | Additional quotation in second time against additional works at Kotalghosh PWSS TW-2. | BP-2024-25-269 | 23/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.87 | 0 | 0 | 0
4451 | PURBA BARDHAMAN | Burdwan Division | KOTALGHOSH PIPED WATER SUPPLY SCHEME , SM/14062 | New | KOTALGHOSH Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman [NEW SCHEME] | 3528/BWD | 10/08/2023 | 965 | BRINDABAN KONAR | 325.17 | 271.02 | 83.35 | 5
4452 | PURBA BARDHAMAN | Central Mechanical | KOTALGHOSH PIPED WATER SUPPLY SCHEME , SM/14062 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KOTALGHOSH Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4188/CMD | 29/08/2023 | 610 | MITRA ASSOCIATE | 26.74 | 10.27 | 48.62 | 48
4453 | PURBA BARDHAMAN | Central Mechanical | KOTALGHOSH PIPED WATER SUPPLY SCHEME , SM/14062 | New | Supply and delivery of 10 HP pump motor set at T.W. No - 2 of Kotalghosh water supply scheme under CMD, PHE Dte | 926/DIC/BMSD(D) | 26/12/2024 | 7 | MITRA ASSOCIATE | 0.75 | 0 | 0 | 100
4454 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bahirghanya Piped Water Supply Scheme at Galsi-II Block , SM/07870 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bahirgannya piped water supply scheme at Bahirgannya (04 Nos. habitation Part), Askaran (02 Nos. habitation), Brindabanpur (02 Nos. Habitation), Kurkuba (03 Nos Habitation) & Srirampur (02 Nos. Habitation) village, Galsi-II Block under Burdwan Division, PHE Dte. | 5006/BWD | 10/12/2020 | 90 | SUPRIYA RAY | 99.82 | 43.43 | 43.51 | 1
4455 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bahirghanya Piped Water Supply Scheme at Galsi-II Block , SM/07870 | Retrofitting | Laying parallel pipeline to increase the water supply towards Kalyanpur [ Node No-146 t0 100 ] of BAHIRGHANNYA and its adjoining mouza's Piped W/S Scheme at Galsi-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-B] | 343/DSD | 30/06/2022 | 30 | SUPRIYA RAY | 4.89 | 0 | 0 | 1
4456 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bahirghanya Piped Water Supply Scheme at Galsi-II Block , SM/07870 | Retrofitting | Shifting of pipeline for Strengthening work of Anandabazar-Galsi via Sar Road under Asansol Highway Division P.W. (Roads) [Node No- 6-7-8-9-10] and restore damage pipeline at Askaran village due to construction of drain by the Kurkuba GP of BAHIRGHANNYA and its adjoining mouza's Piped W/S Scheme at Galsi-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. | 1604/BWD | 05/04/2023 | 84 | SUPRIYA RAY | 16.6 | 0 | 0 | 100
4457 | PURBA BARDHAMAN | Burdwan Division | HARIGRAM PIPED WATER SUPPLY SCHEME , SM/13292 | New | Material Requisition To Resource Division | 1252/BWD | 17/03/2023 | 0 | Resource Division | 7.5 | 0 | 0 | 0
4458 | PURBA BARDHAMAN | Burdwan Division | HARIGRAM PIPED WATER SUPPLY SCHEME , SM/13292 | New | Material Requisition To Resource Division | 1643/BWD | 06/04/2023 | 0 | Resource Division | 1.79 | 0 | 0 | 0
4459 | PURBA BARDHAMAN | Burdwan Division | HARIGRAM PIPED WATER SUPPLY SCHEME , SM/13292 | New | Material Requisition To Resource Division | 5267/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
4460 | PURBA BARDHAMAN | Central Mechanical | HARIGRAM PIPED WATER SUPPLY SCHEME , SM/13292 | New | New service connection charges for Harigram PWSS TW-2 | BP-2023-24-236 | 06/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.69 | 0 | 0 | 0
4461 | PURBA BARDHAMAN | Central Mechanical | HARIGRAM PIPED WATER SUPPLY SCHEME , SM/13292 | New | New service connection charges for Harigram PWSS TW-1 | BP-2023-24-169 | 27/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.5 | 0 | 0 | 0
4462 | PURBA BARDHAMAN | Burdwan Division | HARIGRAM PIPED WATER SUPPLY SCHEME , SM/13292 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | 2751/BSD | 28/11/2023 | 183 | SK.ASFIA | 2.4 | 0.4 | 99.91 | 70
4463 | PURBA BARDHAMAN | Central Mechanical | HARIGRAM PIPED WATER SUPPLY SCHEME , SM/13292 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Harigram Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3940/CMD | 23/08/2023 | 30 | CHOUDHURY ENTERPRISE | 28.9 | 23.82 | 100 | 100
4464 | PURBA BARDHAMAN | Central Mechanical | HARIGRAM PIPED WATER SUPPLY SCHEME , SM/13292 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 0 | 12
4465 | PURBA BARDHAMAN | Central Mechanical | HARIGRAM PIPED WATER SUPPLY SCHEME , SM/13292 | New | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3103/CMD | 11/12/2024 | 60 | S DUTTA | 15.06 | 0 | 0 | 0
4466 | PURBA BARDHAMAN | Burdwan Division | HARIGRAM PIPED WATER SUPPLY SCHEME , SM/13292 | New | Allied works (OHR, FHTC, internal pathway, approach road and road restoration) for HARIGRAM PWSS under Bardhaman II Block within Burdwan Division, PHE. Dte. | 1405/BWD | 16/05/2025 | 90 | S.R. ENTERPRISE | 14.32 | 0 | 0 | 0
4467 | PURBA BARDHAMAN | Burdwan Division | HARIGRAM PIPED WATER SUPPLY SCHEME , SM/13292 | New | HARIGRAM Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Burdwan-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 481/BWD | 08/02/2023 | 693 | SAKTI ENTERPRISE | 262.46 | 236.52 | 90.64 | 81
4468 | PURBA BARDHAMAN | Burdwan Division | Gangua Piped Water Supply Scheme , SM/13295 | New | Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division, P.H.E. Dte. consider 96.00 Km. run per day.[Period from 01/08/2023 to 31/10/2023] | 1759/BSD | 28/07/2023 | 66 | MD HASIN | 0.85 | 0 | 0 | 0
4469 | PURBA BARDHAMAN | Burdwan Division | Gangua Piped Water Supply Scheme , SM/13295 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.5 | 0 | 0 | 0
4470 | PURBA BARDHAMAN | Burdwan Division | Gangua Piped Water Supply Scheme , SM/13295 | New | Material Requisition To Resource Division | 4038/BWD | 08/09/2023 | 0 | Resource Division | 0.41 | 0 | 0 | 0
4471 | PURBA BARDHAMAN | Burdwan Division | Gangua Piped Water Supply Scheme , SM/13295 | New | Material Requisition To Resource Division | 5088/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
4472 | PURBA BARDHAMAN | Central Mechanical | Gangua Piped Water Supply Scheme , SM/13295 | New | New service connection for Gangua PWSS TW 2 | BP-2023-24-512 | 08/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.61 | 0 | 0 | 0
4473 | PURBA BARDHAMAN | Central Mechanical | Gangua Piped Water Supply Scheme , SM/13295 | New | New service connection for Gangua W/S scheme TW No-1 | BP-2023-24-409 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.34 | 0 | 0 | 0
4474 | PURBA BARDHAMAN | Central Mechanical | Gangua Piped Water Supply Scheme , SM/13295 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 0 | 12
4475 | PURBA BARDHAMAN | Central Mechanical | Gangua Piped Water Supply Scheme , SM/13295 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Gangua Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3992/CMD | 29/08/2023 | 30 | C.M. ENTERPRISE | 28.85 | 0 | 0 | 90
4476 | PURBA BARDHAMAN | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME , SM/14437 | New | Material Requisition To Resource Division | 1249/BWD | 17/03/2023 | 0 | Resource Division | 15.17 | 0 | 0 | 0
4477 | PURBA BARDHAMAN | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME , SM/14437 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 41.55 | 0 | 0 | 0
4478 | PURBA BARDHAMAN | Central Mechanical | SHIKARPUR PIPED WATER SUPPLY SCHEME , SM/14437 | New | Quotation for new electric service connection at Shikarpur PH NO.-2 | BP-2023-24-247 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.73 | 0 | 0 | 0
4479 | PURBA BARDHAMAN | Central Mechanical | SHIKARPUR PIPED WATER SUPPLY SCHEME , SM/14437 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
4480 | PURBA BARDHAMAN | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME , SM/14437 | New | Work Order For "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR NANDAI PWSS & SHIKARPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 1980/KSD | 09/02/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.33 | 100 | 100
4481 | PURBA BARDHAMAN | Central Mechanical | SHIKARPUR PIPED WATER SUPPLY SCHEME , SM/14437 | New | Electric quotation for New Service Connection at Shikarpur W/S Scehem PH-I. | BP-2023-24-287 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.57 | 0 | 0 | 0
4482 | PURBA BARDHAMAN | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME , SM/14437 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEARA, PATHARDANGA & SHIKARPUR Piped Water Supply Scheme under KALNA-I Block, District:- Purba Bardhaman [NEW SCHEME] | 1004/BWD | 06/03/2023 | 641 | M/S TAPAS KUMAR CHAKRABORTY | 1584.09 | 319.18 | 58.78 | 75
4483 | PURBA BARDHAMAN | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME , SM/14437 | New | Temporary approach road from Shikarpur Graveyard to OHr site and Shikarpur Bus stand to 2nd tube well site in order to carry building materials for Shikarpur Piped W/S. Scheme (SM/14437) within Kalna Sub-Division under Burdwan Division, PHE. Dte. | 767/BWD | 27/02/2025 | 15 | M/S TAPAS KUMAR CHAKRABORTY | 5.75 | 0 | 0 | 0
4484 | PURBA BARDHAMAN | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME , SM/14437 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
4485 | PURBA BARDHAMAN | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME , SM/14437 | New | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
4486 | PURBA BARDHAMAN | Central Mechanical | SHIKARPUR PIPED WATER SUPPLY SCHEME , SM/14437 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SHIKARPUR Water Supply Scheme [ Block- KALNA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4110/CMD | 29/08/2023 | 30 | CHOUDHURY ENTERPRISE | 30.14 | 12.16 | 48.08 | 50
4487 | PURBA BARDHAMAN | Burdwan Division | SHIKARPUR PIPED WATER SUPPLY SCHEME , SM/14437 | New | Work Order for " Restoration of pipeline with other allied works at different places of Shikarpur mouja under Shikarpur Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | 969/KSD | 31/07/2024 | 10 | M/S TAPAS KUMAR CHAKRABORTY | 3.58 | 0 | 0 | 100
4488 | PURBA BARDHAMAN | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Work Order for Supply of 1 (one) No. Diesel driven Motor cab on hire basis for the Office of the Assistant Engineer, under Kalna Sub-Division within Burdwan Division, P.H.E. Dte. [Period from 01.07.2023 to 31.12.2023] | 825/KSD | 28/06/2023 | 184 | PARTHA PRATIM ACHARYA | 0 | 0 | 0 | 0
4489 | PURBA BARDHAMAN | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Material Requisition To Resource Division | 1636/BWD | 06/04/2023 | 0 | Resource Division | 4.2 | 0 | 0 | 0
4490 | PURBA BARDHAMAN | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Material Requisition To Resource Division | 1242/BWD | 17/03/2023 | 0 | Resource Division | 17.57 | 0 | 0 | 0
4491 | PURBA BARDHAMAN | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Material Requisition To Resource Division | 4022/BWD | 08/09/2023 | 0 | Resource Division | 34.67 | 0 | 0 | 0
4492 | PURBA BARDHAMAN | Central Mechanical | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | New service connection charges for Pathardanga PWSS TW-2 | BP-2023-24-198 | 13/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.06 | 0 | 0 | 0
4493 | PURBA BARDHAMAN | Central Mechanical | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PATHARDANGA Water Supply Scheme [ Block- KALNA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4016/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 29.61 | 11.65 | 39.33 | 60
4494 | PURBA BARDHAMAN | Central Mechanical | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
4495 | PURBA BARDHAMAN | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL UNDER PATHARDANGA PWSS AND TAIPARA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE. (2 UNITS:- 1 NO FOR PATHARDANGA PWSS & 1 NO FOR TAIPARA PWSS)" | 1977/KSD | 09/02/2024 | 10 | BISWAS ENTERPRISE | 0.66 | 0.33 | 100 | 100
4496 | PURBA BARDHAMAN | Central Mechanical | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | New Service connection for Pathardanga W/S Scheme PH No.-1 | BP-2023-24-307 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.44 | 0 | 0 | 0
4497 | PURBA BARDHAMAN | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEARA, PATHARDANGA & SHIKARPUR Piped Water Supply Scheme under KALNA-I Block, District:- Purba Bardhaman [NEW SCHEME] | 1004/BWD | 06/03/2023 | 641 | M/S TAPAS KUMAR CHAKRABORTY | 1584.09 | 483.06 | 75.69 | 75
4498 | PURBA BARDHAMAN | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Work order for "Restoration of pipeline with other allied works at different places of Ghanashyampur mouja under Pathardanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | 1846/KSD | 27/11/2024 | 15 | M/S TAPAS KUMAR CHAKRABORTY | 4.22 | 0 | 0 | 100
4499 | PURBA BARDHAMAN | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Work order for " Restoration of pipeline with other allied works at different places of Pathardanga mouja under Pathardanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | 1847/KSD | 27/11/2024 | 15 | M/S TAPAS KUMAR CHAKRABORTY | 4.14 | 0 | 0 | 100
4500 | PURBA BARDHAMAN | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Work order for "Restoration of pipeline with other allied works at different places of Beshbati mouja of Pathardanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | 1852/KSD | 27/11/2024 | 15 | M/S TAPAS KUMAR CHAKRABORTY | 3.58 | 0 | 0 | 100
4501 | PURBA BARDHAMAN | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Work order for "Restoration of pipeline with other allied works at different places of Rampur mouja under Pathardanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | 1849/KSD | 27/11/2024 | 15 | M/S TAPAS KUMAR CHAKRABORTY | 3.66 | 0 | 0 | 100
4502 | PURBA BARDHAMAN | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
4503 | PURBA BARDHAMAN | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Work Order for "Restoration of pipeline with other allied works at different places of Indrapur mouja under Patahrdanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | 966/KSD | 31/07/2024 | 10 | M/S TAPAS KUMAR CHAKRABORTY | 3.12 | 0 | 0 | 100
4504 | PURBA BARDHAMAN | Burdwan Division | PATHARDANGA PIPED WATER SUPPLY SCHEME , SM/14440 | New | Work Order for "Restoration of pipeline with other allied works at different places of parshapur mouja under Patahrdanga Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | 967/KSD | 31/07/2024 | 10 | M/S TAPAS KUMAR CHAKRABORTY | 2.21 | 1.35 | 40.21 | 100
4505 | PURBA BARDHAMAN | Burdwan Division | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME , SM/14448 | New | Material Requisition To Resource Division | 1965/BWD | 26/04/2023 | 0 | Resource Division | 35.89 | 0 | 0 | 0
4506 | PURBA BARDHAMAN | Burdwan Division | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME , SM/14448 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 17.8 | 0 | 0 | 0
4507 | PURBA BARDHAMAN | Burdwan Division | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME , SM/14448 | New | Material Requisition To Resource Division | 5263/BWD | 30/11/2023 | 0 | Resource Division | 20.78 | 0 | 0 | 0
4508 | PURBA BARDHAMAN | Central Mechanical | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME , SM/14448 | New | New service connection charges for Purba Gopalpur PWSS TW-1 | BP-2023-24-144 | 31/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.2 | 0 | 0 | 0
4509 | PURBA BARDHAMAN | Central Mechanical | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME , SM/14448 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
4510 | PURBA BARDHAMAN | Central Mechanical | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME , SM/14448 | New | New service connection charges for Purba Gopalpur PWSS TW-2 | BP-2023-24-274 | 21/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.51 | 0 | 0 | 0
4511 | PURBA BARDHAMAN | Central Mechanical | PURBA GOPALPUR PIPED WATER SUPPLY SCHEME , SM/14448 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PURBA GOPALPUR Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3873/CMD | 17/08/2023 | 363 | UNIVERSAL ENTERPRISES | 29.94 | 24.24 | 95.71 | 90
4512 | PURBA BARDHAMAN | Burdwan Division | KURMUN PIPED WATER SUPPLY SCHEME , SM/13943 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 9.02 | 0 | 0 | 0
4513 | PURBA BARDHAMAN | Burdwan Division | KURMUN PIPED WATER SUPPLY SCHEME , SM/13943 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.67 | 0 | 0 | 0
4514 | PURBA BARDHAMAN | Burdwan Division | KURMUN PIPED WATER SUPPLY SCHEME , SM/13943 | New | Material Requisition To Resource Division | 5271/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
4515 | PURBA BARDHAMAN | Central Mechanical | KURMUN PIPED WATER SUPPLY SCHEME , SM/13943 | New | New service connection charges for Kurmun PWSS TW-1 | BP-2023-24-226 | 10/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0 | 0
4516 | PURBA BARDHAMAN | Central Mechanical | KURMUN PIPED WATER SUPPLY SCHEME , SM/13943 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
4517 | PURBA BARDHAMAN | Burdwan Division | KURMUN PIPED WATER SUPPLY SCHEME , SM/13943 | New | Supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-02-2024 to 30-04-2024) | 188/BSD | 31/01/2024 | 66 | PARVIN BEGAM | 0.85 | 0.28 | 99.64 | 97
4518 | PURBA BARDHAMAN | Burdwan Division | KURMUN PIPED WATER SUPPLY SCHEME , SM/13943 | New | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | 907/BWD | 04/03/2024 | 30 | MANASH GHOSH | 23.87 | 4.93 | 100 | 100
4519 | PURBA BARDHAMAN | Central Mechanical | KURMUN PIPED WATER SUPPLY SCHEME , SM/13943 | New | New service connection for Kurmun PWSS | BP-2023-24-603 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.63 | 0 | 0 | 0
4520 | PURBA BARDHAMAN | Burdwan Division | KURMUN PIPED WATER SUPPLY SCHEME , SM/13943 | New | KURMUN Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 4124/BWD | 14/09/2023 | 818 | GHOSH CONCERN | 550.63 | 131.72 | 23.92 | 65
4521 | PURBA BARDHAMAN | Burdwan Division | KURMUN PIPED WATER SUPPLY SCHEME , SM/13943 | New | Balance work [ i.e. Extension or parallel Pipeline, Leftout FHTC, Road Restoration work, Sinking of Additional Tube Well with Pump House & Boundary wall, inter Connection of Additional Tube Well, with allied work of KURMUN Piped Water Supply Scheme, Block-Burdwan- I under Burdwan Sub Division, PHE Dte. within Burdwan Division PHE Dte. | 727/BWD | 24/02/2025 | 120 | SHIVAM UN-EMPLOYED ENGINEERS CO-OPERATIVE SOCIETY LTD. | 95.65 | 0 | 0 | 0
4522 | PURBA BARDHAMAN | Central Mechanical | KURMUN PIPED WATER SUPPLY SCHEME , SM/13943 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kurmun Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4001/CMD | 29/08/2023 | 30 | S.P. CONSTRUCTION | 28.96 | 22.95 | 95.24 | 100
4523 | PURBA BARDHAMAN | Burdwan Division | BAKALSA PIPED WATER SUPPLY SCHEME , SM/13944 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 3.25 | 0 | 0 | 0
4524 | PURBA BARDHAMAN | Burdwan Division | BAKALSA PIPED WATER SUPPLY SCHEME , SM/13944 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 21.15 | 0 | 0 | 0
4525 | PURBA BARDHAMAN | Burdwan Division | BAKALSA PIPED WATER SUPPLY SCHEME , SM/13944 | New | Material Requisition To Resource Division | 5041/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
4526 | PURBA BARDHAMAN | Burdwan Division | BAKALSA PIPED WATER SUPPLY SCHEME , SM/13944 | New | Material Requisition To Resource Division | 4893/BWD | 10/11/2023 | 0 | Resource Division | 6.5 | 0 | 0 | 0
4527 | PURBA BARDHAMAN | Central Mechanical | BAKALSA PIPED WATER SUPPLY SCHEME , SM/13944 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
4528 | PURBA BARDHAMAN | Central Mechanical | BAKALSA PIPED WATER SUPPLY SCHEME , SM/13944 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
4529 | PURBA BARDHAMAN | Burdwan Division | BAKALSA PIPED WATER SUPPLY SCHEME , SM/13944 | New | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | 907/BWD | 04/03/2024 | 30 | MANASH GHOSH | 23.87 | 4.99 | 100 | 100
4530 | PURBA BARDHAMAN | Central Mechanical | BAKALSA PIPED WATER SUPPLY SCHEME , SM/13944 | New | New service connection charges for Bakalsa PWSS TW-1 | BP-2023-24-336 | 06/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.04 | 0 | 0 | 0
4531 | PURBA BARDHAMAN | Central Mechanical | BAKALSA PIPED WATER SUPPLY SCHEME , SM/13944 | New | New service connection for Bakalsa PWSS. | BP-2023-24-395 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.99 | 0 | 0 | 0
4532 | PURBA BARDHAMAN | Burdwan Division | BAKALSA PIPED WATER SUPPLY SCHEME , SM/13944 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch room, boundary walls with gates, land development, surface drains and internal pathways at different TW site for BAKALSA Piped Water Supply Scheme under BURDWAN-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3723/BWD | 25/08/2023 | 727 | M/S GHOSH & CO. | 534.23 | 166.72 | 31.21 | 25
4533 | PURBA BARDHAMAN | Burdwan Division | NANDIARA PIPED WATER SUPPLY SCHEME , SM/14019 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.72 | 0 | 0 | 0
4534 | PURBA BARDHAMAN | Burdwan Division | NANDIARA PIPED WATER SUPPLY SCHEME , SM/14019 | New | Material Requisition To Resource Division | 3836/BWD | 01/09/2023 | 0 | Resource Division | 2.35 | 0 | 0 | 0
4535 | PURBA BARDHAMAN | Burdwan Division | NANDIARA PIPED WATER SUPPLY SCHEME , SM/14019 | New | Material Requisition To Resource Division | 5064/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
4536 | PURBA BARDHAMAN | Burdwan Division | NANDIARA PIPED WATER SUPPLY SCHEME , SM/14019 | New | NANDIARA Piped Water Supply Scheme with sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of 200 cum capacity RCC OHRs with 20.0 mtr. Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site under Memari-II Block, District:- Purba Bardhaman [NEW SCHEME] | 3502/BWD | 10/08/2023 | 690 | S.S.S. ENTERPRISES | 451.06 | 180.28 | 39.97 | 45
4537 | PURBA BARDHAMAN | Central Mechanical | NANDIARA PIPED WATER SUPPLY SCHEME , SM/14019 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at NOAHATI & others water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2395/CMD | 02/08/2024 | 90 | S.G. TECHNICAL SERVICES | 36.99 | 0 | 0 | 0
4538 | PURBA BARDHAMAN | Burdwan Division | NANDIARA PIPED WATER SUPPLY SCHEME , SM/14019 | New | Supply of inspection Vehicle for inspection of different JJM related(schemes)works as and when required including supply of driver & fuel(minimum 8 hours duty per day) and all taxes etc. for Burdwan Sub-Division under Burdwan Division,PHE Dte consider 96.00 Km. run per day (Period from 01-02-2024 to 30-04-2024) | 188/BSD | 31/01/2024 | 66 | PARVIN BEGAM | 0.85 | 0.28 | 99.55 | 97
4539 | PURBA BARDHAMAN | Central Mechanical | NANDIARA PIPED WATER SUPPLY SCHEME , SM/14019 | New | New service connection for NANDIARA PWSS TW 2. | BP-2023-24-520 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.33 | 0 | 0 | 0
4540 | PURBA BARDHAMAN | Central Mechanical | NANDIARA PIPED WATER SUPPLY SCHEME , SM/14019 | New | New service connection for NANDIARA PWSS TW 1. | BP-2023-24-521 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.76 | 0 | 0 | 0
4541 | PURBA BARDHAMAN | Central Mechanical | NANDIARA PIPED WATER SUPPLY SCHEME , SM/14019 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Nandiara Water Supply Scheme [ Block- Memari-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4026/CMD | 29/08/2023 | 642 | JAGANNATH ENTERPRISE | 29.39 | 0 | 0 | 50
4542 | PURBA BARDHAMAN | Burdwan Division | NANDIARA PIPED WATER SUPPLY SCHEME , SM/14019 | New | Continuation work order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte. (Period from 01-12-2024 to 28-02-2025 | 2636/BSD | 29/11/2024 | 90 | SK. ASFIA | 1.2 | 0.78 | 194.76 | 60
4543 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS , SM/13339 | New | Material Requisition To Resource Division | 1256/BWD | 17/03/2023 | 0 | Resource Division | 6.23 | 0 | 0 | 0
4544 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS , SM/13339 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 3.3 | 0 | 0 | 0
4545 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS , SM/13339 | New | Material Requisition To Resource Division | 5262/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
4546 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS , SM/13339 | New | New Service Connection charges for Kandarsona W/S Scheme TW-2 | BP-2023-24-12 | 17/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.4 | 0 | 0 | 0
4547 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS , SM/13339 | New | New Service Connection charges for Kandarsona W/S Scheme TW-1 | BP-2023-24-11 | 17/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0 | 0
4548 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS , SM/13339 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kandarsona Water Supply Scheme [Block- Burdwan-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2471/CMD | 30/05/2023 | 30 | DUTTA ENTERPRISE | 28.92 | 23.54 | 100 | 80
4549 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS , SM/13339 | New | Supply & delivery of standby Submersible pumping machinery for Kandarsona & others water supply scheme, under CMD, P.H.E. Dte., Dist.- Purba Bardhaman | 823/CMSD | 05/10/2023 | 21 | DUTTA ENTERPRISE | 0.84 | 0.84 | 100 | 98
4550 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS , SM/13339 | New | Re-orientation of delivery pipe line by supply & fitting fixing different CIDF materials, pressure gauge etc. at Kandarsona water supply scheme, T.W. No.- I & II under CMD, P.H.E. Dte., Dist.- Purba Bardhaman. | 843/CMSD | 18/10/2023 | 10 | DUTTA ENTERPRISE | 0.79 | 0.79 | 100 | 99
4551 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS , SM/13339 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 0 | 12
4552 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED KANDARSONA PWSS , SM/13339 | New | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3103/CMD | 11/12/2024 | 60 | S DUTTA | 15.06 | 0 | 0 | 0
4553 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS , SM/13339 | New | KANDARSONA Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC, Construction of 150 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site under Burdwan-II Block, District:- Purba-Bardhaman. [NEW SCHEME] | 358/BWD | 30/01/2023 | 701 | M/S S.S. ENTERPRISE | 284.66 | 240.27 | 93.59 | 90
4554 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS , SM/13339 | New | Beautification of PWSS with Arboriculture, Recharge Pit including shaft and anciliary works) Kandarsona P.W.S.S under Burdwan Division, PHE Dte. | 279/RWS | 03/09/2024 | 110 | M/S PALASH BISWAS | 0.97 | 0 | 0 | 100
4555 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED KANDARSONA PWSS , SM/13339 | New | Providing FHTC (due to const. of road by BDA Dept)for Kandarsona PWSS under Bardhaman-II block within Burdwan Div.PHE Dte | 1549/BSD | 02/07/2025 | 30 | M/S PALASH BISWAS | 0.63 | 0 | 0 | 100
4556 | PURBA BARDHAMAN | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15235 | New | Material Requisition To Resource Division | 4006/BWD | 08/09/2023 | 0 | Resource Division | 5.14 | 0 | 0 | 0
4557 | PURBA BARDHAMAN | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15235 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 12.69 | 0 | 0 | 0
4558 | PURBA BARDHAMAN | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15235 | New | Material Requisition To Resource Division | 5083/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
4559 | PURBA BARDHAMAN | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15235 | New | New service connection charges for Gopalpur PWSS TW-2 | BP-2023-24-193 | 11/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.82 | 0 | 0 | 0
4560 | PURBA BARDHAMAN | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15235 | New | Restoration of hard shoulder from 0.00 km to 2.918 km of Sagrai Raina Road (MDR) for laying of water supply pipeline of Gopalpur PWSS under Burdwan Division, PHE Dte. | 1084/JJM | 20/12/2023 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 4.72 | 0 | 0 | 0
4561 | PURBA BARDHAMAN | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15235 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Gopalpur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4031/CMD | 29/08/2023 | 30 | M/S. SWAPAN BANERJEE | 28.98 | 23.86 | 100 | 100
4562 | PURBA BARDHAMAN | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15235 | New | New electric connection for Gopalpur PWSS. | BP-2023-24-344 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.66 | 0 | 0 | 0
4563 | PURBA BARDHAMAN | Central Mechanical | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15235 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
4564 | PURBA BARDHAMAN | Burdwan Division | GOPALPUR PIPED WATER SUPPLY SCHEME , SM/15235 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOPALPUR & RASUIKHANDA Piped Water Supply Scheme under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 1691/BWD | 12/04/2023 | 719 | SK ALIM | 1081.52 | 374.36 | 83.93 | 92
4565 | PURBA BARDHAMAN | Burdwan Division | MAHATA PIPED WATER SUPPLY SCHEME , SM/15242 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 45.74 | 0 | 0 | 0
4566 | PURBA BARDHAMAN | Burdwan Division | MAHATA PIPED WATER SUPPLY SCHEME , SM/15242 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 5.19 | 0 | 0 | 0
4567 | PURBA BARDHAMAN | Burdwan Division | MAHATA PIPED WATER SUPPLY SCHEME , SM/15242 | New | Material Requisition To Resource Division | 4926/BWD | 10/11/2023 | 0 | Resource Division | 37.58 | 0 | 0 | 0
4568 | PURBA BARDHAMAN | Central Mechanical | MAHATA PIPED WATER SUPPLY SCHEME , SM/15242 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MAHATA Water Supply Scheme [ Block- BHATAR] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4099/CMD | 29/08/2023 | 30 | BENGAL CONSTRUCTION. | 27.79 | 21.39 | 76.98 | 90
4569 | PURBA BARDHAMAN | Central Mechanical | MAHATA PIPED WATER SUPPLY SCHEME , SM/15242 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
4570 | PURBA BARDHAMAN | Central Mechanical | MAHATA PIPED WATER SUPPLY SCHEME , SM/15242 | New | New service connection charges for Mahata PWSS TW-1 | BP-2023-24-338 | 06/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.54 | 0 | 0 | 0
4571 | PURBA BARDHAMAN | Central Mechanical | MAHATA PIPED WATER SUPPLY SCHEME , SM/15242 | New | New Service connection at Mahata PWSS PH-1 | BP-2023-24-538 | 15/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.24 | 0 | 0 | 0
4572 | PURBA BARDHAMAN | Central Mechanical | MAHATA PIPED WATER SUPPLY SCHEME , SM/15242 | New | ADDITIONAL CONNECTION FOR MAHATA PWSS PH-1. | BP-2023-24-599 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.1 | 0 | 0 | 0
4573 | PURBA BARDHAMAN | Burdwan Division | MAHATA PIPED WATER SUPPLY SCHEME , SM/15242 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DHENRIA, MAHATA, DEBPUR Piped Water Supply Scheme under BHATAR Block, District:- Purba-Bardhaman [NEW SCHEME] | 1737/BWD | 13/04/2023 | 993 | M/S B. RAI CONSTRUCTION COMPANY | 1643.39 | 289.77 | 54.28 | 81
4574 | PURBA BARDHAMAN | Burdwan Division | MAHATA PIPED WATER SUPPLY SCHEME , SM/15242 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period AUG.'2024 to OCT.'2024] | 575/DSD | 19/07/2024 | 78 | MD HASIN | 1 | 0.33 | 100 | 0
4575 | PURBA BARDHAMAN | Burdwan Division | MAHATA PIPED WATER SUPPLY SCHEME , SM/15242 | New | FOR FIXING OF DISPLAY BOARD WITH M.S STRUCTURE CONTAINING SCHEME DESCRIPTION AT KHEJURHATI PWSS AND OTHER SCHEMES ( 16 Nos) WITHIN BHATAR BLOCK UNDER BURDWAN DIVISION , PHE Dte. | 298/DSD | 20/02/2025 | 21 | SHUBHRA KANTI GHOSH | 1.39 | 0 | 0 | 0
4576 | PURBA BARDHAMAN | Burdwan Division | AMILIA PIPED WATER SUPPLY SCHEME , SM/14963 | New | Material Requisition To Resource Division | 1637/BWD | 06/04/2023 | 0 | Resource Division | 1.93 | 0 | 0 | 0
4577 | PURBA BARDHAMAN | Burdwan Division | AMILIA PIPED WATER SUPPLY SCHEME , SM/14963 | New | Material Requisition To Resource Division | 1239/BWD | 17/03/2023 | 0 | Resource Division | 5.51 | 0 | 0 | 0
4578 | PURBA BARDHAMAN | Central Mechanical | AMILIA PIPED WATER SUPPLY SCHEME , SM/14963 | New | New service connection charges of Amilia W/S Scheme TW-2 | BP-2023-24-24 | 21/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.81 | 0 | 0 | 0
4579 | PURBA BARDHAMAN | Central Mechanical | AMILIA PIPED WATER SUPPLY SCHEME , SM/14963 | New | New service connection charges of Amilia W/S Scheme TW-1 | BP-2023-24-23 | 21/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.9 | 0 | 0 | 0
4580 | PURBA BARDHAMAN | Burdwan Division | AMILIA PIPED WATER SUPPLY SCHEME , SM/14963 | New | AMILIA Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 150 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | 1067/BWD | 13/03/2023 | 300 | SHUBHRA KANTI GHOSH | 247.76 | 225.51 | 91.02 | 40
4581 | PURBA BARDHAMAN | Central Mechanical | AMILIA PIPED WATER SUPPLY SCHEME , SM/14963 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Amilia Water Supply Scheme [ Block- Khandoghosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2515/CMD | 02/06/2023 | 30 | MS MANABESH ROY | 28.91 | 23.6 | 100 | 90
4582 | PURBA BARDHAMAN | Burdwan Division | AMILIA PIPED WATER SUPPLY SCHEME , SM/14963 | New | Material Requisition To Resource Division | 319/BWD | 24/01/2024 | 0 | Resource Division | 21.17 | 0 | 0 | 0
4583 | PURBA BARDHAMAN | Burdwan Division | AMILIA PIPED WATER SUPPLY SCHEME , SM/14963 | New | Way leave / Track crossing proposal with Application ID: SER-ADRA-2024-WL-114 in IR-RBCS laying of 200 mm dia Carrier pipe with 600 mm dia Casing pipe for water supply on (Jal Jeevan Mission) at KM 317/03 to 317/04 in between Seharabazar (SRBZ) to Kaiyar (KYB) by PHE Dte.,Burdwan Division. | 1184/JJM | 20/12/2024 | 0 | INDIAN RAILWAY | 5.32 | 0 | 0 | 0
4584 | PURBA BARDHAMAN | Burdwan Division | AMILIA PIPED WATER SUPPLY SCHEME , SM/14963 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period AUG.'2024 to OCT.'2024] | 575/DSD | 19/07/2024 | 78 | MD HASIN | 1 | 0.33 | 100 | 0
4585 | PURBA BARDHAMAN | Central Mechanical | AMILIA PIPED WATER SUPPLY SCHEME , SM/14963 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KHEJURHATI & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2391/CMD | 02/08/2024 | 90 | C.M. ENTERPRISE | 45.81 | 0 | 0 | 10
4586 | PURBA BARDHAMAN | Burdwan Division | AMILIA PIPED WATER SUPPLY SCHEME , SM/14963 | New | Survey, planning, design of pipe crossing system by adopting trenchless technologies (e.g. Jack Pushing Method etc.) for crossing Railway, as per relevant I.S. Code with latest amendment, guidelines, specification and requirement of the authorities owning the railway track, submission of design report and drawing obtaining permission on behalf of the PHE Dte. across the railway track between Seharabazar (SRBZ) and Kaiyar (KYB) Station & connecting with existing 160mm dia HDPE distribution main line of AMILIA Water Supply Scheme of Khandaghosh Block under Burdwan Division, P.H.E. Dte. | 938/BWD | 11/03/2025 | 30 | MANASH GHOSH | 30.33 | 0 | 0 | 0
4587 | PURBA BARDHAMAN | Burdwan Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14926 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 0.33 | 0 | 0 | 0
4588 | PURBA BARDHAMAN | Burdwan Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14926 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 5.69 | 0 | 0 | 0
4589 | PURBA BARDHAMAN | Burdwan Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14926 | New | Material Requisition To Resource Division | 5244/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0 | 0
4590 | PURBA BARDHAMAN | Central Mechanical | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14926 | New | New service connection charges for Chhoto Ramchandrapur PWSS TW-1 | BP-2023-24-180 | 04/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.92 | 0 | 0 | 0
4591 | PURBA BARDHAMAN | Durgapur W/S Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14926 | New | Material Requisition To Resource Division | 1724/G/DWSD | 10/12/2024 | 0 | Resource Division | 3.99 | 0 | 0 | 0
4592 | PURBA BARDHAMAN | Central Mechanical | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14926 | New | New service connection for Choto Ramchandrapur W/S scheme TW No-2 | BP-2023-24-413 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.94 | 0 | 0 | 0
4593 | PURBA BARDHAMAN | Durgapur W/S Division | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14926 | New | Acceptance cum Formal Work Order for Balance works related sinking of Tube-wells at ARJURI village,PH,BW, LDS , Rising Mains, FHTCs,Road Restoration ,Land Development Etc. Construction of CHOTORAMCHANDRAPUR Piped Water Supply Scheme under Aushgram-II Block, of Durgapur Water supply Division, PHE Dte. | 1610/DWSD | 26/11/2024 | 270 | KALPANA BUILDERS | 78.66 | 0 | 0 | 0
4594 | PURBA BARDHAMAN | Central Mechanical | CHHOTO RAMCHANDRAPUR PIPED WATER SUPPLY SCHEME , SM/14926 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chhoto Ramchandrapur Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4015/CMD | 29/08/2023 | 580 | JAL PRAVAHIKA PVT LTD | 27.77 | 21.67 | 95.23 | 48
4595 | PURBA BARDHAMAN | Burdwan Division | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME , SM/14964 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.26 | 0 | 0 | 0
4596 | PURBA BARDHAMAN | Burdwan Division | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME , SM/14964 | New | Material Requisition To Resource Division | 5079/BWD | 23/11/2023 | 0 | Resource Division | 19.78 | 0 | 0 | 0
4597 | PURBA BARDHAMAN | Burdwan Division | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME , SM/14964 | New | Material Requisition To Resource Division | 4023/BWD | 08/09/2023 | 0 | Resource Division | 5.83 | 0 | 0 | 0
4598 | PURBA BARDHAMAN | Central Mechanical | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME , SM/14964 | New | NEW SERVICE CONNECTION FOR PASCHIM NABAGRAM PWSS PH-2 | BP-2024-25-86 | 15/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.13 | 0 | 0 | 0
4599 | PURBA BARDHAMAN | Central Mechanical | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME , SM/14964 | New | NEW SERVICE CONNECTION FOR PASCHIM NABAGRAM PWSS PH-1 | BP-2024-25-85 | 15/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.06 | 0 | 0 | 0
4600 | PURBA BARDHAMAN | Central Mechanical | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME , SM/14964 | New | Additional Quotation for service connection at Paschim Nabagram PWSS PH-2. | BP-2024-25-220 | 26/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 12 | 0 | 0 | 0
4601 | PURBA BARDHAMAN | Central Mechanical | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME , SM/14964 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
4602 | PURBA BARDHAMAN | Central Mechanical | PASCHIM NABAGRAM PIPED WATER SUPPLY SCHEME , SM/14964 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PASCHIM NABAGRAM Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4189/CMD | 29/08/2023 | 30 | M/S. S.R. ENTERPRISE | 29.91 | 24 | 95.67 | 43
4603 | PURBA BARDHAMAN | Burdwan Division | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME , SM/14976 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.5 | 0 | 0 | 0
4604 | PURBA BARDHAMAN | Burdwan Division | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME , SM/14976 | New | Material Requisition To Resource Division | 4031/BWD | 08/09/2023 | 0 | Resource Division | 3.08 | 0 | 0 | 0
4605 | PURBA BARDHAMAN | Burdwan Division | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME , SM/14976 | New | Material Requisition To Resource Division | 5094/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
4606 | PURBA BARDHAMAN | Burdwan Division | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME , SM/14976 | New | BAHIRSARBAMANGALA-A Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 2297/BWD | 19/05/2023 | 365 | MLG CONSTRUCTION | 371.05 | 0 | 0 | 30
4607 | PURBA BARDHAMAN | Central Mechanical | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME , SM/14976 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
4608 | PURBA BARDHAMAN | Central Mechanical | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME , SM/14976 | New | New Service connection for Bahir Sarbamangala (Part-A) PWSS TW-1. | BP-2023-24-624 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.85 | 0 | 0 | 0
4609 | PURBA BARDHAMAN | Central Mechanical | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME , SM/14976 | New | New Service connection for Bahir Sarbamangala (Part-A) PWSS TW-2. | BP-2023-24-625 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.52 | 0 | 0 | 0
4610 | PURBA BARDHAMAN | Central Mechanical | BAHIR SARBAMANGALA-A PIPE WATER SUPPLY SCHEME , SM/14976 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Bahir Sarbamangala-A Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4045/CMD | 29/08/2023 | 672 | P.K. ENGINEERING | 29.35 | 0 | 0 | 45
4611 | PURBA BARDHAMAN | Burdwan Division | BHEDIA PIPED WATER SUPPLY SCHEME , SM/14748 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 3.03 | 0 | 0 | 0
4612 | PURBA BARDHAMAN | Burdwan Division | BHEDIA PIPED WATER SUPPLY SCHEME , SM/14748 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 14.27 | 0 | 0 | 0
4613 | PURBA BARDHAMAN | Burdwan Division | BHEDIA PIPED WATER SUPPLY SCHEME , SM/14748 | New | Material Requisition To Resource Division | 4909/BWD | 10/11/2023 | 0 | Resource Division | 33.07 | 0 | 0 | 0
4614 | PURBA BARDHAMAN | Durgapur W/S Division | BHEDIA PIPED WATER SUPPLY SCHEME , SM/14748 | New | Acceptance cum Formal Work Order for Sinking of 300X200 mm dia TW,Pump House,Boundary wall concrete road & bituminous road restoration ,Jack pushing with laying of MS Pipe FHTC and land development of H/W Site drain & Internal pathway laying of MS pipe under Bhedia PWSS (JJM),Block-Aushgram-II,Dist-Purba Bardhaman under Durgapur W/S Division,PHE Dte. | 1611/DWSD | 26/11/2024 | 90 | SUPRIYA RAY | 87.54 | 0 | 0 | 0
4615 | PURBA BARDHAMAN | Central Mechanical | BHEDIA PIPED WATER SUPPLY SCHEME , SM/14748 | New | NEW SERVICE CONNECTION FOR BHEDIA PWSS PH-1. | BP-2023-24-649 | 20/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.26 | 0 | 0 | 0
4616 | PURBA BARDHAMAN | Central Mechanical | BHEDIA PIPED WATER SUPPLY SCHEME , SM/14748 | New | New service connection charges for Bhedia PWSS TW-2 | BP-2024-25-319 | 30/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.48 | 0 | 0 | 0
4617 | PURBA BARDHAMAN | Burdwan Division | BHEDIA PIPED WATER SUPPLY SCHEME , SM/14748 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways for BHEDIA Piped Water Supply Scheme under Ausgram-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 4847/BWD | 09/11/2023 | 730 | SUPRIYA RAY | 397.54 | 111.99 | 28.17 | 50
4618 | PURBA BARDHAMAN | Durgapur W/S Division | BHEDIA PIPED WATER SUPPLY SCHEME , SM/14748 | New | Formal Work Order for Additional work for laying 200 mm dia HDPE pipe line and other necessary allied works Amarpur & Bhedia Piped W/S Scheme, Block- Aushgram-2, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 1291/DWSD | 06/09/2024 | 210 | SAIKAT RAY | 196.61 | 70.81 | 72.03 | 60
4619 | PURBA BARDHAMAN | Central Mechanical | BHEDIA PIPED WATER SUPPLY SCHEME , SM/14748 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BHEDIA Water Supply Scheme [ Block- AUSGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4103/CMD | 29/08/2023 | 611 | WEST BENGAL ENGINEERING CO. | 27.76 | 15.77 | 41.51 | 80
4620 | PURBA BARDHAMAN | Burdwan Division | LAKHURIA PIPE WATER SUPPLY SCHEME , SM/14918 | New | Material Requisition To Resource Division | 1965/BWD | 26/04/2023 | 0 | Resource Division | 1.64 | 0 | 0 | 0
4621 | PURBA BARDHAMAN | Burdwan Division | LAKHURIA PIPE WATER SUPPLY SCHEME , SM/14918 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 5.83 | 0 | 0 | 0
4622 | PURBA BARDHAMAN | Central Mechanical | LAKHURIA PIPE WATER SUPPLY SCHEME , SM/14918 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
4623 | PURBA BARDHAMAN | Burdwan Division | LAKHURIA PIPE WATER SUPPLY SCHEME , SM/14918 | New | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | 485/KTS | 16/04/2024 | 72 | AJIT SAMANTA | 0.92 | 0.23 | 100 | 10
4624 | PURBA BARDHAMAN | Burdwan Division | LAKHURIA PIPE WATER SUPPLY SCHEME , SM/14918 | New | Material Requisition To Resource Division | 295/BWD | 24/01/2024 | 0 | Resource Division | 20.47 | 0 | 0 | 0
4625 | PURBA BARDHAMAN | Central Mechanical | LAKHURIA PIPE WATER SUPPLY SCHEME , SM/14918 | New | Quotation for new service connection at Lakhuria PWSS PH-I. | BP-2024-25-165 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.7 | 0 | 0 | 0
4626 | PURBA BARDHAMAN | Central Mechanical | LAKHURIA PIPE WATER SUPPLY SCHEME , SM/14918 | New | Quotation for new service connection at Lakhuria PWSS PH-2. | BP-2024-25-166 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.69 | 0 | 0 | 0
4627 | PURBA BARDHAMAN | Central Mechanical | LAKHURIA PIPE WATER SUPPLY SCHEME , SM/14918 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Lakhuria Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4067/CMD | 29/08/2023 | 640 | GLACIER ENGINEERING CO | 26.98 | 10.58 | 49.05 | 43
4628 | PURBA BARDHAMAN | Central Mechanical | LAKHURIA PIPE WATER SUPPLY SCHEME , SM/14918 | New | Supply and delivery of 10 HP pump motor set at T.W. No - 2 of Lakhuria (Block-Mongolkote) water supply scheme under CMD, PHE Dte. | 128/DIC/BMSD(D) | 20/02/2025 | 7 | GLACIER ENGINEERING CO | 0.81 | 0 | 0 | 100
4629 | PURBA BARDHAMAN | Central Mechanical | HARISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15319 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Harishnapur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4032/CMD | 29/08/2023 | 30 | SUBRATA BHADRA | 28.96 | 0 | 0 | 0
4630 | PURBA BARDHAMAN | Burdwan Division | HARISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15319 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.85 | 0 | 0 | 0
4631 | PURBA BARDHAMAN | Burdwan Division | HARISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15319 | New | Material Requisition To Resource Division | 4005/BWD | 08/09/2023 | 0 | Resource Division | 10.43 | 0 | 0 | 0
4632 | PURBA BARDHAMAN | Burdwan Division | HARISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15319 | New | Material Requisition To Resource Division | 5084/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
4633 | PURBA BARDHAMAN | Central Mechanical | HARISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15319 | New | New service connection charges for Harishnapur PWSS TW-01 | BP-2023-24-495 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.92 | 0 | 0 | 0
4634 | PURBA BARDHAMAN | Central Mechanical | HARISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15319 | New | New Service connection at HARISHNAPUR, PWSS. | BP-2023-24-483 | 31/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.37 | 0 | 0 | 0
4635 | PURBA BARDHAMAN | Burdwan Division | HARISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15319 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BAJITPUR, SHUKUR & HARISHNAPUR Piped Water Supply Scheme under RAINA-I Block, District:- Purba Bardhaman [NEW SCHEME] | 3197/BWD | 24/07/2023 | 907 | MRITYUNJOY MUKHERJEE & CO. | 1242.03 | 51.36 | 13.42 | 55
4636 | PURBA BARDHAMAN | Central Mechanical | HARISHNAPUR PIPED WATER SUPPLY SCHEME , SM/15319 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
4637 | PURBA BARDHAMAN | Burdwan Division | MAKHALTOR PIPED WATER SUPPLY SCHEME , SM/15153 | New | Material Requisition To Resource Division | 1260/BWD | 17/03/2023 | 0 | Resource Division | 6.59 | 0 | 0 | 0
4638 | PURBA BARDHAMAN | Central Mechanical | MAKHALTOR PIPED WATER SUPPLY SCHEME , SM/15153 | New | New service connection charges for Makhaltor W/S Scheme TW-2 | BP-2023-24-38 | 27/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.11 | 0 | 0 | 0
4639 | PURBA BARDHAMAN | Central Mechanical | MAKHALTOR PIPED WATER SUPPLY SCHEME , SM/15153 | New | New service connection charges of Makhaltor W/S Scheme TW-1 | BP-2023-24-35 | 26/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.3 | 0 | 0 | 0
4640 | PURBA BARDHAMAN | Central Mechanical | MAKHALTOR PIPED WATER SUPPLY SCHEME , SM/15153 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Mulgram & others water supply scheme under Katwa-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2409/CMD | 02/08/2024 | 90 | DUTTA ENTERPRISE | 50.18 | 0 | 0 | 0
4641 | PURBA BARDHAMAN | Burdwan Division | MAKHALTOR PIPED WATER SUPPLY SCHEME , SM/15153 | New | MAKHALTOR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Katwa-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 1050/BWD | 10/03/2023 | 663 | HAMID SK | 195.79 | 198.13 | 100 | 99
4642 | PURBA BARDHAMAN | Central Mechanical | MAKHALTOR PIPED WATER SUPPLY SCHEME , SM/15153 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at MAKHALTOR Water Supply Scheme [ Block- KATWA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2612/CMD | 08/06/2023 | 280 | SOUNAK ENTERPRISE | 27.65 | 21.16 | 94.74 | 30
4643 | PURBA BARDHAMAN | Burdwan Division | MAKHALTOR PIPED WATER SUPPLY SCHEME , SM/15153 | New | Providing left out FHTC at different area under the command area of Makhaltore PWSS (SM/15153) in order to declare Sajal Gram and other anciallary works, Katwa II Block under Katwa Sub Division, PHE. Dte. | 1085/BWD | 28/03/2025 | 30 | HAMID SK | 7.42 | 0 | 0 | 70
4644 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME , SM/15487 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Gangpur Water Supply Scheme [ Block- Burdwan-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4008/CMD | 29/08/2023 | 30 | CHATTERJEE ENTERPRISE | 28.95 | 0 | 0 | 0
4645 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME , SM/15487 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 6.43 | 0 | 0 | 0
4646 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME , SM/15487 | New | Material Requisition To Resource Division | 3873/BWD | 01/09/2023 | 0 | Resource Division | 5.75 | 0 | 0 | 0
4647 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME , SM/15487 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.55 | 0 | 0 | 0
4648 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME , SM/15487 | New | Material Requisition To Resource Division | 4920/BWD | 10/11/2023 | 0 | Resource Division | 42.46 | 0 | 0 | 0
4649 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME , SM/15487 | New | Material Requisition To Resource Division | 4112/BWD | 25/11/2024 | 0 | Resource Division | 15.69 | 0 | 0 | 0
4650 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME , SM/15487 | New | NEW SERVICE CONNECTION FOR GANGPUR TW 1. | BP-2023-24-636 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.74 | 0 | 0 | 0
4651 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME , SM/15487 | New | Quotation for new service connection Gangpur PWSS TW-2. | BP-2024-25-163 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.72 | 0 | 0 | 0
4652 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME , SM/15487 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BALGANA & GANGPUR Piped Water Supply Scheme under Burdwan ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3699/BWD | 24/08/2023 | 769 | SUPRITI ENTERPRISE | 1345.79 | 9.03 | 1.33 | 20
4653 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER BASED GANGPUR PIPED WATER SUPPLY SCHEME , SM/15487 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at KUSHA & others water supply scheme under Bardhaman-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2389/CMD | 02/08/2024 | 90 | DILIP MAHATO | 53.14 | 0 | 0 | 12
4654 | PURBA BARDHAMAN | Central Drilling | SRIPUR PIPE WATER SUPPLY SCHEME , SM/15158 | New | Providing drilling crew and other allied works for construction of Tube Well ( 250mm X200mm X 114 Mtrs. Depth) by utilising Departmental Machineries for Sripur Scheme (T/W-I & II) , Ketugram-I Block under Purba Bardhaman District, Central Drilling Division, P.H.E. Dte. | 860/CDD | 10/07/2023 | 30 | OSMAN SEKH | 16.62 | 0 | 0 | 0
4655 | PURBA BARDHAMAN | Burdwan Division | SRIPUR PIPE WATER SUPPLY SCHEME , SM/15158 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.55 | 0 | 0 | 0
4656 | PURBA BARDHAMAN | Burdwan Division | SRIPUR PIPE WATER SUPPLY SCHEME , SM/15158 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.91 | 0 | 0 | 0
4657 | PURBA BARDHAMAN | Burdwan Division | SRIPUR PIPE WATER SUPPLY SCHEME , SM/15158 | New | Material Requisition To Resource Division | 4916/BWD | 10/11/2023 | 0 | Resource Division | 19.75 | 0 | 0 | 0
4658 | PURBA BARDHAMAN | Central Mechanical | SRIPUR PIPE WATER SUPPLY SCHEME , SM/15158 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
4659 | PURBA BARDHAMAN | Burdwan Division | SRIPUR PIPE WATER SUPPLY SCHEME , SM/15158 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Ankhona, Pandugram, Sripur PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2738/BWD | 12/07/2024 | 173 | PUSPA ENTERPRISE | 128.29 | 0 | 0 | 75
4660 | PURBA BARDHAMAN | Central Mechanical | SRIPUR PIPE WATER SUPPLY SCHEME , SM/15158 | New | New Service connection at Sripur PWSS TW-1 | BP-2023-24-489 | 01/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.49 | 0 | 0 | 0
4661 | PURBA BARDHAMAN | Central Mechanical | SRIPUR PIPE WATER SUPPLY SCHEME , SM/15158 | New | New service connection at Sripur PWSS TW No.2 | BP-2023-24-490 | 01/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.54 | 0 | 0 | 0
4662 | PURBA BARDHAMAN | Central Mechanical | SRIPUR PIPE WATER SUPPLY SCHEME , SM/15158 | New | NEW SERVICE CONNECTION FOR SRIPUR PWSS PH-2. | BP-2024-25-45 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.76 | 0 | 0 | 0
4663 | PURBA BARDHAMAN | Burdwan Division | SRIPUR PIPE WATER SUPPLY SCHEME , SM/15158 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ANKHONA, PANDUGRAM & SRIPUR Piped Water Supply Scheme under KETUGRAM¿I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3388/BWD | 03/08/2023 | 882 | PUSPA ENTERPRISE | 989.13 | 143.77 | 50.74 | 50
4664 | PURBA BARDHAMAN | Central Mechanical | SRIPUR PIPE WATER SUPPLY SCHEME , SM/15158 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at SRIPUR Water Supply Scheme [ Block- KETUGRAM-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4129/CMD | 29/08/2023 | 30 | M/S, S.S. ENTERPRISE. | 27.65 | 21.33 | 94.78 | 88
4665 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 3rd Tube well site at Bagila village to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for BAGILA its Adjoining Mouza W/S scheme, block -MEMARI-I within Burdwan Sub-Division ,PHE Dte._2ND CALL | 809/BSD | 03/05/2023 | 45 | A R TRADERS | 3.6 | 3.55 | 100 | 100
4666 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Laying of 150mm DI pipeline between Bagila health centre to Bagila Baroaritala for BAGILA Piped Water Supply Scheme to provide house connection under memari-I block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1473/BSD | 12/07/2023 | 15 | A R TRADERS | 0.97 | 0.94 | 100 | 100
4667 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Preparation and Submission of DPR for Augmentation of Bagila PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1584/BSD | 24/07/2023 | 15 | MEASURE LAND | 0.78 | 0.77 | 100 | 100
4668 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | New service connection charges for Aug. Bagila PWSS TW-3 | BP-2023-24-67 | 20/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.18 | 0 | 0 | 0
4669 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Illumination arrangement & different electro-mechanical works at BAGILA water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2795/CMD | 01/10/2024 | 60 | GOENKA ENTERPRISE | 14.16 | 0 | 0 | 0
4670 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Bagila Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2591/CMD | 07/06/2023 | 30 | SUBRATA BHADRA | 11.09 | 10.6 | 100 | 50
4671 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Interconnection between Head Work site T/W to 2nd T/W site for BAGILA Piped Water Supply Scheme to provide house connection within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1006/BSD | 06/06/2023 | 30 | A R TRADERS | 0.96 | 0.95 | 100 | 100
4672 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Restoration Rising main line for FHTC work and Construction of boundary wall at Head work site with gate and land development, drain and internal pathway and for BAGILA PWSS under Memari-I Block, District:- Purba-Bardhaman. | 5381/BWD | 08/12/2023 | 60 | SK RAJU | 35.42 | 34.69 | 100 | 100
4673 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Supply & delivery of standby Submersible pumping machinery & automatic Chlorinator for Bagila & others water supply scheme, under CMD, P.H.E. Dte., Dist.- Purba Bardhaman | 152/CMSD | 22/01/2024 | 15 | BEHERA ENTERPRISE | 1.74 | 1.74 | 100 | 100
4674 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Electric quotation for New Service Connection at Bagila W/S (Aug.) Scehem PH-IV. | BP-2023-24-291 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.43 | 0 | 0 | 0
4675 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Augmentation of BAGILA Piped Water Supply Scheme with sinking of Tube-well, LDS & FHTC For Songoti Pally, LDS & FHTC For Station Para & LDS & FHTC For Taktipur, Baharampur, Krishnapur, Talchina & Kiskinda Habitation under Memari-I Block, District:- Purba-Bardhaman. | 3036/BWD | 14/07/2023 | 537 | H SAMANTA | 149.26 | 142.33 | 95.36 | 85
4676 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Providing FHTC work on distribution system for FHTC work for BAGILA Piped W/S. Scheme at berhampur, Krishnapur, Kiskinda, Taktipur mouza within Memari I Block under Burdwan Divn., PHE. Dte. | 2289/BWD | 06/08/2025 | 45 | H SAMANTA | 9.73 | 0 | 0 | 0
4677 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Designing,making and erection of Sign Board for SWAJAL GRAM in Krishnapur village of Memari-I Block under Bagila Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos Board) | 2350/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
4678 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Providing balance FHTC work on distribution system for FHTC work for BAGILA Piped Water Supply Scheme at various mouza within Memari I Block under Burdwan Divn., PHE. Dte. | 1407/BWD | 16/05/2025 | 45 | H SAMANTA | 10.2 | 0 | 0 | 0
4679 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Replacement of Tube-well & Rising main at HEAD TW SITE for Aug. of BAGILA, SASINARA ZONE-I, SASINARA ZONE-II, Piped Water Supply Scheme within MEMARI-I Block under Burdwan Division, PHE. Dte. District:- Purba-Bardhaman. | 027/BWD | 03/01/2024 | 60 | KOUSIK MALLICK | 38.87 | 30.63 | 99.12 | 90
4680 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR BAGILA , SM/15192 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 4 at Augmentation of BAGILA Water Supply Scheme [ BLOCK- MEMARI-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1537/CMD | 05/03/2024 | 240 | SUDIKSHA CONSTRUCTION | 12.32 | 11.57 | 95.64 | 100
4681 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DERIAPUR , SM/15195 | Retrofitting | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Astikpur, Dakhinkul & Balagar of DERIAPUR Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1296/BWD | 21/03/2023 | 651 | T.K. BANERJEE & CO. | 68.81 | 56.29 | 88.86 | 100
4682 | PURBA BARDHAMAN | Burdwan Division | RETROFITTING OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR DERIAPUR , SM/15195 | Retrofitting | Sinking of Tube Well, Construction of Pump House, Boundary Wall at 3rd TW Site with Extension of Pipeline & Laying Parallel line and Providing FHTC (Leftout] with allied works for DERIAPUR Piped Water Supply Scheme under Raina-I Block within Burdwan Sub Division under Burdwan Division P.H.E Dte. | 2270/BWD | 18/06/2024 | 388 | ROY CONSTRUCTION | 68.15 | 0 | 0 | 100
4683 | PURBA BARDHAMAN | Burdwan Division | CHAKULIA PIPE WATER SUPPLY SCHEME , SM/15162 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.38 | 0 | 0 | 0
4684 | PURBA BARDHAMAN | Burdwan Division | CHAKULIA PIPE WATER SUPPLY SCHEME , SM/15162 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.8 | 0 | 0 | 0
4685 | PURBA BARDHAMAN | Burdwan Division | CHAKULIA PIPE WATER SUPPLY SCHEME , SM/15162 | New | Material Requisition To Resource Division | 5047/BWD | 23/11/2023 | 0 | Resource Division | 19.78 | 0 | 0 | 0
4686 | PURBA BARDHAMAN | Central Mechanical | CHAKULIA PIPE WATER SUPPLY SCHEME , SM/15162 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
4687 | PURBA BARDHAMAN | Central Drilling | CHAKULIA PIPE WATER SUPPLY SCHEME , SM/15162 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X150mm X 240 Mtrs. Depth) by utilizing Departmental Machineries for Chakulia W/S Scheme (T/W-I & II), Block- Mangolkote under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | 1339/CDD | 13/09/2023 | 210 | M/S SAIKAT ENTERPRISE | 23.35 | 16.79 | 100 | 100
4688 | PURBA BARDHAMAN | Burdwan Division | CHAKULIA PIPE WATER SUPPLY SCHEME , SM/15162 | New | Supply, delivery, installation & hand hold demonstration of different equipments / machineries to test HDPE pipes as per IS: 4984-2016 at the pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte._2ND CALL | 907/BWD | 04/03/2024 | 30 | MANASH GHOSH | 23.87 | 5.35 | 100 | 100
4689 | PURBA BARDHAMAN | Burdwan Division | CHAKULIA PIPE WATER SUPPLY SCHEME , SM/15162 | New | Material Requisition To Resource Division | 4110/BWD | 25/11/2024 | 0 | Resource Division | 9.28 | 0 | 0 | 0
4690 | PURBA BARDHAMAN | Central Mechanical | CHAKULIA PIPE WATER SUPPLY SCHEME , SM/15162 | New | Quotation for new service connection for Chakulia PWSS TW-1. | BP-2024-25-134 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.57 | 0 | 0 | 0
4691 | PURBA BARDHAMAN | Central Mechanical | CHAKULIA PIPE WATER SUPPLY SCHEME , SM/15162 | New | Quotation for new service connection for Chakulia PWSS TW-2. | BP-2024-25-133 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.1 | 0 | 0 | 0
4692 | PURBA BARDHAMAN | Central Mechanical | CHAKULIA PIPE WATER SUPPLY SCHEME , SM/15162 | New | Additional quotation in second time against additional work at Chakulia PWSS TW-2 | BP-2024-25-268 | 21/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.31 | 0 | 0 | 0
4693 | PURBA BARDHAMAN | Burdwan Division | CHAKULIA PIPE WATER SUPPLY SCHEME , SM/15162 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to CHAKULIA, KULSANA & HALIMPUR Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] | 3443/BWD | 08/08/2023 | 836 | ASHOK KUMAR GHOSH | 1588.1 | 86.62 | 28.64 | 15
4694 | PURBA BARDHAMAN | Central Mechanical | CHAKULIA PIPE WATER SUPPLY SCHEME , SM/15162 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System, Internal House Wiring and Compound lighting arrangement for Tube well No.- 1 & 2 at CHAKULIA Water Supply Scheme [BLOCK- MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman | 1534/CMD | 05/03/2024 | 626 | CHATTERJEE ENTERPRISE | 28.81 | 6.9 | 23.94 | 70
4695 | PURBA BARDHAMAN | Burdwan Division | CHAKULIA PIPE WATER SUPPLY SCHEME , SM/15162 | New | Balance work of CHAKULIA Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongalkote Block, District:- Purba-Bardhaman | 846/BWD | 05/03/2025 | 120 | M/S M.M. ENTERPRISE | 214.08 | 0 | 0 | 0
4696 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU , SM/15203 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW site of NATU W/S Scheme under Raina - I Block within Burdwan Sub-Division, PHE Dte. | 2707/BWD | 08/06/2023 | 30 | M/S D. PALIT & CO. | 13.25 | 11.23 | 100 | 100
4697 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU , SM/15203 | Augmentation | Preparation and Submission of DPR for Augmentation of Natu PWSS under Raina-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1586/BSD | 24/07/2023 | 15 | GEO-SOLUTION | 0.78 | 0.77 | 100 | 100
4698 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU , SM/15203 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Natu Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2598/CMD | 07/06/2023 | 30 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 11.15 | 10.02 | 94.76 | 96
4699 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU , SM/15203 | Augmentation | NEW SERVICE CONNECTION FOR NATU (AUGMENTATION) PWSS TW 03 | BP-2024-25-58 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.49 | 0 | 0 | 0
4700 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU , SM/15203 | Augmentation | Extension of Pipeline for providing Functional Household Tap Connection (FHTC) at Birupur & Sudarshanpur village under NATU Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | 675/BWD | 19/02/2024 | 424 | KALYAN CHOWDHURY | 7.49 | 0 | 0 | 100
4701 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU , SM/15203 | Augmentation | Laying Parallel Pipeline to improve drinking water supply, Construction of Boundary wall, Path Way, Drain at Head Work Site and providing leftout FHTC, Road Restoration with allied work for NATU Piped Water Supply Scheme, Block-Raina-I within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 2994/BWD | 01/08/2024 | 487 | ANWESHA CONSTRUCTION | 55.19 | 0 | 0 | 75
4702 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU , SM/15203 | Augmentation | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Birupur & Siyali of NATU Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1576/BWD | 31/03/2023 | 761 | KALYAN CHOWDHURY | 30.88 | 22.8 | 74.02 | 100
4703 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR NATU , SM/15203 | Augmentation | Construction of switch rooms & Rising main at different TW site for NATU Piped Water Supply Scheme under Raina - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte | 4164/BWD | 20/09/2023 | 300 | M/S MA TARA ENTERPRISE | 8.01 | 7.92 | 100 | 100
4704 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR , SM/15175 | Augmentation | Preparation and Submission of DPR for Augmentation of Hatgobindapur PWSS under Burdwan-II Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1477/BSD | 12/07/2023 | 15 | MEASURE LAND | 0.78 | 0.77 | 100 | 100
4705 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR , SM/15175 | Augmentation | Construction of 300 cu.m. capacity 20 mtr staging height RCC Over Head Reservoir including Pipe connection & soil investigation under HATGOBINDAPUR Piped W/S. Scheme within Burdwan - II Block under Burdwan Division, P.H.E Dte. | 1729/BWD | 13/04/2023 | 537 | GUPTA ENTERPRISE | 89.36 | 70.5 | 79.8 | 100
4706 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR , SM/15175 | Augmentation | Laying of interconnection between 1st & 2nd tube well to OHR for Hatgobindapur PWSS within Burdhaman-II Block under Burdwan Division, PHE Dte. | 103/BSD | 16/01/2025 | 46 | I.S. ENTERPRISE | 3.6 | 0 | 0 | 100
4707 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR , SM/15175 | Augmentation | Different works related (Sinking of Tube well-4th, Rising Main, construction of Pump House cum switch room and Boundary wall for HATGOBINDAPUR Piped Water Supply Scheme under BURDWAN -II Block, District:- Purba-Bardhaman. | 2712/BWD | 11/07/2024 | 264 | DEY NIRMAN | 41.51 | 27.33 | 70.11 | 100
4708 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR HATGOBINDAPUR , SM/15175 | Augmentation | Providing LDS in place of AC pipe line for HATGOBINDAPUR PWSS under Bardhaman-II Block within Burdwan Div. PHE Dte. | 874/BWD | 06/03/2025 | 177 | DEY NIRMAN | 35.37 | 0 | 0 | 100
4709 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) , SM/15178 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of SATGACHIA(Z-I, Part-B)[MEMARI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman | 4197/CMD | 29/08/2023 | 30 | DAS TRADING CO. | 24.41 | 0 | 0 | 0
4710 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) , SM/15178 | Augmentation | Illumination arrangement & different electro-mechanical works at SATGACHIA (Zone-I, Part-B) water supply scheme under Memari-II Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2801/CMD | 01/10/2024 | 60 | S.K. ELECTRICALS | 12.53 | 0 | 0 | 0
4711 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) , SM/15178 | Augmentation | Restoration of Pump House at Head Work site of Satgachia Zone-I Piped water supply scheme at Memari-II BlockUnder Burdwan Division, Dist.-Purba Bardhaman. | 998/BSD | 06/06/2024 | 30 | INDRAJIT MONDAL | 0.96 | 0.43 | 100 | 90
4712 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) , SM/15178 | Augmentation | NEW SERVICE CONNECTION FOR AUGMENTATION OF SATGACHIA PWSS | BP-2023-24-593 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.58 | 0 | 0 | 0
4713 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) , SM/15178 | Augmentation | 150MM DI bypass pipeline at DVC Canel side for smooth water supply for FHTC from Patra mouza to Katna, Shrirampur & Begunia mouza under satgachia zone- I pwss within Memari- II block under Burdwan Division PHE DTE. | 633/BSD | 19/03/2025 | 30 | M/S ANAND CONSTRUCTION | 4.94 | 0 | 0 | 0
4714 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) , SM/15178 | Augmentation | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 848/BWD | 05/03/2025 | 120 | PROJECT INDIA | 394.29 | 0 | 0 | 0
4715 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) , SM/15178 | Augmentation | Restoration of Conc. road, Providing leftout FHTC with extension of Pipeline, construction of Pathway, drain, repairing of Pump House at Head Work site with allied works for MAGRA, SANUI, SATGACHIA Zone-I & NARAGOHALIA PIPED WATER SUPPLY SCHEME, Block-Memari-I, within Burdwan Sub Division under Burdwan Division PHE Dte. | 611/BWD | 11/02/2025 | 180 | M/S ASHA CONSTRUCTION | 354.13 | 0 | 0 | 25
4716 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) , SM/15178 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-I W/S Scheme at DEBIPUR Mouza under Memari-I Block and SATGACHIA Z-I W/S Scheme at BEGUNIA Mouza under Memari-II Block within Burdwan Sub-Division, PHE Dte. [For 02 Nos. Tube well]. | 2687/BWD | 08/06/2023 | 60 | ANIRUDDHA FARUQUE | 26.48 | 12.24 | 100 | 50
4717 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SATGACHIA PWSS (ZONE-I)(PART-B) , SM/15178 | Augmentation | Laying of damaged pipeline for parhati & Satgachia zone -I pwss under MEMARI-II Block of Burdwan Sub-Division under Burdwan Division, PHE Dte | 632/BSD | 19/03/2025 | 30 | SAMANTA CONSTRUCTION | 4.85 | 0 | 0 | 100
4718 | PURBA BARDHAMAN | Burdwan Division | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/16254 | New | UCHITPUR Single Village Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Raina-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 1422/BWD | 24/03/2023 | 90 | ANWESHA CONSTRUCTION | 77.19 | 76.95 | 100 | 100
4719 | PURBA BARDHAMAN | Burdwan Division | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/16254 | New | Material Requisition To Resource Division | 3839/BWD | 01/09/2023 | 0 | Resource Division | 1.31 | 0 | 0 | 0
4720 | PURBA BARDHAMAN | Burdwan Division | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/16254 | New | Material Requisition To Resource Division | 5068/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
4721 | PURBA BARDHAMAN | Central Mechanical | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/16254 | New | New service connection charges for Uchitpur PWSS TW-1 | BP-2023-24-79 | 24/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.26 | 0 | 0 | 0
4722 | PURBA BARDHAMAN | Burdwan Division | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/16254 | New | Extension of pipeline & installation of Air Valve for providing FHTC at Dharapara & Malick para of Uchitpur village for UCHITPUR Piped Water Supply Scheme[New Scheme], Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | 530/BSD | 14/03/2024 | 30 | ANWESHA CONSTRUCTION | 0.96 | 0 | 0 | 0
4723 | PURBA BARDHAMAN | Burdwan Division | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/16254 | New | Providing FHTC at leftour part of Malik Para of Uchitpur Village under UCHITPUR Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | 281/BSD | 09/02/2024 | 30 | ANWESHA CONSTRUCTION | 0.95 | 0.95 | 100 | 100
4724 | PURBA BARDHAMAN | Burdwan Division | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/16254 | New | Providing FHTC at leftour part of Dhara Para of Uchitpur Village under UCHITPUR Piped Water Supply Scheme, Block- Raina-I within Burdwan Sub Division under Burdwan Division PHE Dte. | 518/BSD | 13/03/2024 | 30 | ANWESHA CONSTRUCTION | 0.95 | 0.81 | 100 | 100
4725 | PURBA BARDHAMAN | Central Mechanical | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/16254 | New | Supply and Delivery of standby pump motor set for Sipta, Uchitpur, Haripur & others Water Supply Scheme under CMD, PHE Dte. | 2596/CMD | 27/08/2024 | 30 | JOYGURU ENTERPRISE | 4.72 | 1.4 | 100 | 100
4726 | PURBA BARDHAMAN | Central Mechanical | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/16254 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Uchitpur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2881/CMD | 07/07/2023 | 331 | WEST BENGAL ENGINEERING CO. | 28.96 | 11.44 | 39.52 | 100
4727 | PURBA BARDHAMAN | Central Mechanical | UCHITPUR PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/16254 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
4728 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SAHAPUR PIPED WATER SUPPLY SCHEME , SM/16022 | Augmentation | New service connection charges for Sahapur PWSS TW-1 | BP-2023-24-187 | 09/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.16 | 0 | 0 | 0
4729 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF SAHAPUR PIPED WATER SUPPLY SCHEME , SM/16022 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Sahapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2586/CMD | 07/06/2023 | 30 | M/S, S.S. ENTERPRISE. | 22.6 | 0 | 0 | 46
4730 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF SAHAPUR PIPED WATER SUPPLY SCHEME , SM/16022 | Augmentation | Augmentation of SAHAPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & renovation of switch-rooms & boundary walls at different TW site under Katwa-II Block, District:- Purba-Bardhaman. | 2343/BWD | 22/05/2023 | 120 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 137.76 | 128.04 | 100 | 95
4731 | PURBA BARDHAMAN | Central Drilling | MAHULA PIPED WATER SUPPLY SCHEME , SM/16025 | New | Providing drilling crew and other allied works for construction of Tube Well (250mm X200mm X 114 Mtrs. Depth) by utilizing Departmental Machineries for Mahula W/S Scheme (T/W-I & II) , Ketugram-I Block under Purba Bardhman District, Central Drilling Division, P.H.E. Dte. | 1057/CDD | 16/08/2023 | 30 | C.M. ENTERPRISE | 16.2 | 0 | 0 | 0
4732 | PURBA BARDHAMAN | Burdwan Division | MAHULA PIPED WATER SUPPLY SCHEME , SM/16025 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.27 | 0 | 0 | 0
4733 | PURBA BARDHAMAN | Burdwan Division | MAHULA PIPED WATER SUPPLY SCHEME , SM/16025 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.89 | 0 | 0 | 0
4734 | PURBA BARDHAMAN | Burdwan Division | MAHULA PIPED WATER SUPPLY SCHEME , SM/16025 | New | Material Requisition To Resource Division | 4872/BWD | 10/11/2023 | 0 | Resource Division | 29.6 | 0 | 0 | 0
4735 | PURBA BARDHAMAN | Burdwan Division | MAHULA PIPED WATER SUPPLY SCHEME , SM/16025 | New | MAHULA Piped Water Supply Scheme with sinking of Tube-well, LDS, Construction of 150 cum RCC OHR with 20 mtr. staging height including soil testing, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Ketugram-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3665/BWD | 22/08/2023 | 300 | SUJATA CONSTRUCTION | 262.37 | 140.79 | 53.66 | 3
4736 | PURBA BARDHAMAN | Central Mechanical | MAHULA PIPED WATER SUPPLY SCHEME , SM/16025 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Rajur & others water supply scheme under Ketugram-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2407/CMD | 02/08/2024 | 90 | M.S. ENTERPRISE | 82.29 | 0 | 0 | 0
4737 | PURBA BARDHAMAN | Central Mechanical | MAHULA PIPED WATER SUPPLY SCHEME , SM/16025 | New | Quotation for new service connection at Mahula PWSS PH-I. | BP-2024-25-173 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.02 | 0 | 0 | 0
4738 | PURBA BARDHAMAN | Central Mechanical | MAHULA PIPED WATER SUPPLY SCHEME , SM/16025 | New | Quotation for new service connection at Mahula PWSS PH-2. | BP-2024-25-172 | 01/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.31 | 0 | 0 | 0
4739 | PURBA BARDHAMAN | Central Mechanical | MAHULA PIPED WATER SUPPLY SCHEME , SM/16025 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at MAHULA [KETUGRAM-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4145/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 21.4 | 0 | 0 | 70
4740 | PURBA BARDHAMAN | Burdwan Division | MAHULA PIPED WATER SUPPLY SCHEME , SM/16025 | New | Balance work for OHR, extension of pipeline to provide FHTC with sinking of tube well, construction of pump house, boundary wall, land development, plinth protection for pump house, approach road & other related work under Chakta, Mahula, Rajoor and Srigram PWSS under Katwa Sub Division, Block- Ketugram-I, Burdwan Division PHE Dte. | 2721/BWD | 11/07/2024 | 447 | ESCON INDIA | 139.35 | 12.3 | 35.34 | 70
4741 | PURBA BARDHAMAN | Central Mechanical | MAHULA PIPED WATER SUPPLY SCHEME , SM/16025 | New | Supply, delivery of Submersible Pumping Motor and other materials for Tube Well no 1 of Mahula Water Supply Scheme [BLOCK- Ketugram-I] under CMD, PHE Dte., Dist.-Purba-Bardhaman. | 157/DIC/BMSD(D) | 05/03/2025 | 7 | P.K. ENGINEERING | 0.97 | 0 | 0 | 100
4742 | PURBA BARDHAMAN | Central Mechanical | MAHULA PIPED WATER SUPPLY SCHEME , SM/16025 | New | Supply, delivery of submersible cable and other materials for Tube Well no 1 of Mahula Water Supply Scheme [ BLOCK- Ketugram-1] under CMD, PH E Dte., Dist.- Purba-Bardhaman. | 168/DIC/BMSD(D) | 07/03/2025 | 7 | P.K. ENGINEERING | 0.95 | 0 | 0 | 100
4743 | PURBA BARDHAMAN | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME , SM/16026 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 0.66 | 0 | 0 | 0
4744 | PURBA BARDHAMAN | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME , SM/16026 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 16.93 | 0 | 0 | 0
4745 | PURBA BARDHAMAN | Central Mechanical | NAYAPARA PIPED WATER SUPPLY SCHEME , SM/16026 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at NAYAPARA [MANGOLKOTE] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4155/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 21.36 | 9.69 | 45.36 | 46
4746 | PURBA BARDHAMAN | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME , SM/16026 | New | Material Requisition To Resource Division | 297/BWD | 24/01/2024 | 0 | Resource Division | 14.5 | 0 | 0 | 0
4747 | PURBA BARDHAMAN | Central Mechanical | NAYAPARA PIPED WATER SUPPLY SCHEME , SM/16026 | New | NEW SERVICE CONNECTION FOR NAYAPARA PWSS. | BP-2023-24-532 | 13/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.03 | 0 | 0 | 0
4748 | PURBA BARDHAMAN | Central Mechanical | NAYAPARA PIPED WATER SUPPLY SCHEME , SM/16026 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
4749 | PURBA BARDHAMAN | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME , SM/16026 | New | Sinking of additional tube well, Construction of pump house, Boundary wall, Land development under NAYAPARA PWSS, Katwa Sub-Division, Block- Mongolkote, Burdwan Division PHE Dte. | 456/BWD | 21/01/2025 | 224 | HI-LIGHT ELECTRONICS | 34.04 | 0 | 0 | 20
4750 | PURBA BARDHAMAN | Burdwan Division | NAYAPARA PIPED WATER SUPPLY SCHEME , SM/16026 | New | NAYAPARA Piped Water Supply Scheme (Mini Scheme) with sinking of Tube-well, LDS, Rising Main, drain and internal pathway at different TW site under Mongolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | 5121/BWD | 23/11/2023 | 464 | HAMID SK | 104.6 | 80.8 | 84.54 | 100
4751 | PURBA BARDHAMAN | Burdwan Division | PURBA NAYAPARA PIPE WATER SUPPLY SCHEME , SM/16477 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.93 | 0 | 0 | 0
4752 | PURBA BARDHAMAN | Burdwan Division | PURBA NAYAPARA PIPE WATER SUPPLY SCHEME , SM/16477 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 15.26 | 0 | 0 | 0
4753 | PURBA BARDHAMAN | Burdwan Division | PURBA NAYAPARA PIPE WATER SUPPLY SCHEME , SM/16477 | New | Material Requisition To Resource Division | 5231/BWD | 30/11/2023 | 0 | Resource Division | 20.37 | 0 | 0 | 0
4754 | PURBA BARDHAMAN | Central Mechanical | PURBA NAYAPARA PIPE WATER SUPPLY SCHEME , SM/16477 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at PURBA NAYAPARA Water Supply Scheme [ Block- MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4137/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 29.6 | 23.31 | 78.75 | 88
4755 | PURBA BARDHAMAN | Central Mechanical | PURBA NAYAPARA PIPE WATER SUPPLY SCHEME , SM/16477 | New | New service connection for Purba Nayapara PWSS TW 1. | BP-2023-24-621 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.46 | 0 | 0 | 0
4756 | PURBA BARDHAMAN | Central Mechanical | PURBA NAYAPARA PIPE WATER SUPPLY SCHEME , SM/16477 | New | New service connection for Purba Nayapara PWSS TW 2. | BP-2023-24-622 | 07/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.56 | 0 | 0 | 0
4757 | PURBA BARDHAMAN | Central Mechanical | PURBA NAYAPARA PIPE WATER SUPPLY SCHEME , SM/16477 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
4758 | PURBA BARDHAMAN | Burdwan Division | PURBA NAYAPARA PIPE WATER SUPPLY SCHEME , SM/16477 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to PALISGRAM, PURBA NAYAPARA & SITAHATI Piped Water Supply Scheme under MONGALKOTE Block, District:- Purba-Bardhaman [NEW SCHEME] | 4364/BWD | 04/10/2023 | 910 | M/S S. CHOUDHURY | 1505.07 | 100.68 | 23.44 | 77
4759 | PURBA BARDHAMAN | Burdwan Division | BANKAPASI PIPE WATER SUPPLY SCHEME , SM/16484 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 4.03 | 0 | 0 | 0
4760 | PURBA BARDHAMAN | Burdwan Division | BANKAPASI PIPE WATER SUPPLY SCHEME , SM/16484 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 11.91 | 0 | 0 | 0
4761 | PURBA BARDHAMAN | Burdwan Division | BANKAPASI PIPE WATER SUPPLY SCHEME , SM/16484 | New | Material Requisition To Resource Division | 4892/BWD | 10/11/2023 | 0 | Resource Division | 27.17 | 0 | 0 | 0
4762 | PURBA BARDHAMAN | Central Mechanical | BANKAPASI PIPE WATER SUPPLY SCHEME , SM/16484 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
4763 | PURBA BARDHAMAN | Burdwan Division | BANKAPASI PIPE WATER SUPPLY SCHEME , SM/16484 | New | Continuation Work Order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day | 485/KTS | 16/04/2024 | 72 | AJIT SAMANTA | 0.92 | 0.23 | 100 | 10
4764 | PURBA BARDHAMAN | Central Mechanical | BANKAPASI PIPE WATER SUPPLY SCHEME , SM/16484 | New | NEW SERVICE CONNECTION FOR BANKAPASI PWSS. | BP-2023-24-613 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.89 | 0 | 0 | 0
4765 | PURBA BARDHAMAN | Central Mechanical | BANKAPASI PIPE WATER SUPPLY SCHEME , SM/16484 | New | NEW SERVICE CONNECTION FOR BANKAPASI PWSS TW- 2. | BP-2023-24-614 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.23 | 0 | 0 | 0
4766 | PURBA BARDHAMAN | Burdwan Division | BANKAPASI PIPE WATER SUPPLY SCHEME , SM/16484 | New | BANKAPASI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Mongolkote Block, District:- Purba-Bardhaman [NEW SCHEME]_2ND CALL | 3534/BWD | 10/08/2023 | 783 | DESTINATION SOLUTIONS & SERVICES PRIVATE LIMITED | 490.18 | 99.57 | 20.31 | 20
4767 | PURBA BARDHAMAN | Central Mechanical | BANKAPASI PIPE WATER SUPPLY SCHEME , SM/16484 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at BANKAPASI Water Supply Scheme [ Block- MANGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4140/CMD | 29/08/2023 | 640 | CHOUDHURY ENTERPRISE | 28.62 | 0 | 0 | 43
4768 | PURBA BARDHAMAN | Burdwan Division | JHAMATPUR PIPED WATER SUPPLY SCHEME , SM/16256 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 1.42 | 0 | 0 | 0
4769 | PURBA BARDHAMAN | Burdwan Division | JHAMATPUR PIPED WATER SUPPLY SCHEME , SM/16256 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 2.35 | 0 | 0 | 0
4770 | PURBA BARDHAMAN | Burdwan Division | JHAMATPUR PIPED WATER SUPPLY SCHEME , SM/16256 | New | Material Requisition To Resource Division | 4902/BWD | 10/11/2023 | 0 | Resource Division | 10 | 0 | 0 | 0
4771 | PURBA BARDHAMAN | Central Mechanical | JHAMATPUR PIPED WATER SUPPLY SCHEME , SM/16256 | New | New service connection charges for Jhamatpur PWSS Tw-1 | BP-2023-24-63 | 18/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.3 | 0 | 0 | 0
4772 | PURBA BARDHAMAN | Burdwan Division | JHAMATPUR PIPED WATER SUPPLY SCHEME , SM/16256 | New | JHAMATPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 100 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KETUGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 2384/BWD | 23/05/2023 | 300 | M/S M.M. ENTERPRISE | 228.72 | 144.88 | 63.34 | 80
4773 | PURBA BARDHAMAN | Central Mechanical | JHAMATPUR PIPED WATER SUPPLY SCHEME , SM/16256 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Kankurhati & others water supply scheme under Ketugram-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2408/CMD | 02/08/2024 | 90 | DIPALI CONSTRUCTION | 41.95 | 0 | 0 | 0
4774 | PURBA BARDHAMAN | Central Mechanical | JHAMATPUR PIPED WATER SUPPLY SCHEME , SM/16256 | New | New service connection charges for Jhamatpur PWSS TW-2 | BP-2023-24-369 | 15/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.3 | 0 | 0 | 0
4775 | PURBA BARDHAMAN | Central Mechanical | JHAMATPUR PIPED WATER SUPPLY SCHEME , SM/16256 | New | Supplimentary Quotation for ROW at Jhamatpur PWSS TW-2. | BP-2024-25-132 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.71 | 0 | 0 | 0
4776 | PURBA BARDHAMAN | Central Mechanical | JHAMATPUR PIPED WATER SUPPLY SCHEME , SM/16256 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at JHAMATPUR Water Supply Scheme [Block - KETUGRAM-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2887/CMD | 10/07/2023 | 730 | A.S. ENTERPRISE | 20.76 | 19.04 | 97.23 | 40
4777 | PURBA BARDHAMAN | Burdwan Division | BIRUHA PIPED WATER SUPPLY SCHEME , SM/16287 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 12.79 | 0 | 0 | 0
4778 | PURBA BARDHAMAN | Burdwan Division | BIRUHA PIPED WATER SUPPLY SCHEME , SM/16287 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.53 | 0 | 0 | 0
4779 | PURBA BARDHAMAN | Burdwan Division | BIRUHA PIPED WATER SUPPLY SCHEME , SM/16287 | New | Material Requisition To Resource Division | 4913/BWD | 10/11/2023 | 0 | Resource Division | 35.77 | 0 | 0 | 0
4780 | PURBA BARDHAMAN | Burdwan Division | BIRUHA PIPED WATER SUPPLY SCHEME , SM/16287 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to AKALPAUSH & BIRUHA Piped Water Supply Scheme under Kalna ¿ II Block, District:- Purba-Bardhaman [NEW SCHEME] | 3698/BWD | 24/08/2023 | 365 | SUPRITI ENTERPRISE | 1010.87 | 193.93 | 39.94 | 37
4781 | PURBA BARDHAMAN | Burdwan Division | BIRUHA PIPED WATER SUPPLY SCHEME , SM/16287 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR BIRUHA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 2096/KSD | 04/03/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.66 | 100 | 2
4782 | PURBA BARDHAMAN | Central Mechanical | BIRUHA PIPED WATER SUPPLY SCHEME , SM/16287 | New | New electric connection for Biruha PWSS, PH-1. | BP-2023-24-354 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0 | 0
4783 | PURBA BARDHAMAN | Central Mechanical | BIRUHA PIPED WATER SUPPLY SCHEME , SM/16287 | New | New electric connection for Biruha PWSS, PH-2. | BP-2023-24-355 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.94 | 0 | 0 | 0
4784 | PURBA BARDHAMAN | Central Mechanical | BIRUHA PIPED WATER SUPPLY SCHEME , SM/16287 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Khargakur & others water supply scheme under Kalna-2 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2393/CMD | 02/08/2024 | 280 | HANNAN BUILDERS PVT LTD | 76.8 | 0 | 0 | 20
4785 | PURBA BARDHAMAN | Burdwan Division | BIRUHA PIPED WATER SUPPLY SCHEME , SM/16287 | New | Work order for "Restoration of pipeline with other allied works at different places of Bardalia,Masidpur,Biruha,Mainagari mouja under Birhua Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-II panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | 1845/KSD | 27/11/2024 | 15 | SUPRITI ENTERPRISE | 2.89 | 0 | 0 | 100
4786 | PURBA BARDHAMAN | Burdwan Division | BIRUHA PIPED WATER SUPPLY SCHEME , SM/16287 | New | Pipeline laying by HDD method and different types of balance works in connection with different Augmentation & New Scheme [(SM/ 08103), (SM/13413), (SM/15587), (SM/16035), (SM/16287), (SM/16029), (SM/15581), (SM/14437), (SM/16028), (SM/16036) & (SM/14425)] within Kalna Sub-Division under Burdwan Division, PHE Dte. | 849/BWD | 05/03/2025 | 180 | S.P. CONSTRUCTION | 683.3 | 0 | 0 | 0
4787 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME , SM/16297 | Augmentation | Augmentation of KASHIPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Purbasthali - II Block, Purba Burdwan District under Burdwan Division, PHE.Dte. | 2588/BWD | 01/06/2023 | 60 | BAKSHI ENTERPRISE | 19.74 | 13.85 | 100 | 100
4788 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME , SM/16297 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 09 Nos. Piped W/S. Schemes under Purbasthali II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3018/BWD | 05/08/2024 | 50 | HORIZEN | 23.7 | 9.91 | 100 | 10
4789 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME , SM/16297 | Augmentation | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR KASHIPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 2022/KSD | 06/03/2024 | 10 | DEL DELTA CONSTRUCTION | 0.66 | 0.66 | 100 | 100
4790 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME , SM/16297 | Augmentation | New service connection charges for Kashipur PWSS TW-1 | BP-2023-24-356 | 11/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.77 | 0 | 0 | 0
4791 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME , SM/16297 | Augmentation | Different types of works involve in connection with Augmentation of JHAUDANGA (SM/16293), KASHIPUR (SM/16297), PATULI (SM/09718) & PARULIA (SM/09719) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | 2202/BWD | 13/06/2024 | 631 | MONDAL PRECISION PVT LTD | 570 | 99.42 | 52.33 | 2
4792 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF KASHIPUR PIPED WATER SUPPLY SCHEME , SM/16297 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of KASHIPUR[PURBASTHALI-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4437/CMD | 01/11/2023 | 30 | DUTTA ENTERPRISE | 24.4 | 0 | 0 | 100
4793 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF BUNDEBAJ PIPED WATER SUPPLY SCHEME , SM/16196 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of BUNDEBAJ[KALNA-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4202/CMD | 29/08/2023 | 30 | C.M. ENTERPRISE | 24.42 | 0 | 0 | 0
4794 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF BUNDEBAJ PIPED WATER SUPPLY SCHEME , SM/16196 | Augmentation | Augmentation of BUNDEBAJ PWSS to accommodate FHTC Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Kalna - II Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | 4615/BWD | 17/10/2023 | 60 | M/S CHANDRANATH MUKHERJEE | 39.76 | 39.59 | 100 | 100
4795 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF BUNDEBAJ PIPED WATER SUPPLY SCHEME , SM/16196 | Augmentation | Quotation for load enhancement of Bundebaj PWSS TW-2 | BP-2024-25-303 | 24/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.51 | 0 | 0 | 0
4796 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF BUNDEBAJ PIPED WATER SUPPLY SCHEME , SM/16196 | Augmentation | Quotation for load enhancement of Bundebaj PH-2 | BP-2024-25-304 | 24/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.51 | 0 | 0 | 0
4797 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF BUNDEBAJ PIPED WATER SUPPLY SCHEME , SM/16196 | Augmentation | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 618/BWD | 11/02/2025 | 180 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0 | 0
4798 | PURBA BARDHAMAN | Burdwan Division | MASARU PIPE WATER SUPPLY SCHEME , SM/16020 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 13.25 | 0 | 0 | 0
4799 | PURBA BARDHAMAN | Burdwan Division | MASARU PIPE WATER SUPPLY SCHEME , SM/16020 | New | Material Requisition To Resource Division | 3975/BWD | 08/09/2023 | 0 | Resource Division | 0.98 | 0 | 0 | 0
4800 | PURBA BARDHAMAN | Burdwan Division | MASARU PIPE WATER SUPPLY SCHEME , SM/16020 | New | Material Requisition To Resource Division | 4896/BWD | 10/11/2023 | 0 | Resource Division | 13.36 | 0 | 0 | 0
4801 | PURBA BARDHAMAN | Central Mechanical | MASARU PIPE WATER SUPPLY SCHEME , SM/16020 | New | New service connection charges for Mosharu PWSS TW-2 | BP-2023-24-375 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.85 | 0 | 0 | 0
4802 | PURBA BARDHAMAN | Central Mechanical | MASARU PIPE WATER SUPPLY SCHEME , SM/16020 | New | New service connection charges for Mosharu PWSS TW-1 | BP-2023-24-374 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.41 | 0 | 0 | 0
4803 | PURBA BARDHAMAN | Central Mechanical | MASARU PIPE WATER SUPPLY SCHEME , SM/16020 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Lakshimpur & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2406/CMD | 02/08/2024 | 290 | CHOUDHURY ENTERPRISE | 57.65 | 0 | 0 | 10
4804 | PURBA BARDHAMAN | Central Mechanical | MASARU PIPE WATER SUPPLY SCHEME , SM/16020 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at MASARU [MONGOLKOTE] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4147/CMD | 29/08/2023 | 640 | CHOUDHURY ENTERPRISE | 21.27 | 19.17 | 94.64 | 46
4805 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KUENTA , SM/15718 | Augmentation | Pipeline with FHTC for KEUNTA Water Supply Scheme at Kalui village (30 Nos.), Keunta village (30 Nos.), Mandarpur village (30 Nos.), Rampur village (30 Nos.), Nandanpur village (60 Nos.), within Raina-II Block, under Burdwan Division, PHE Dte. | 855/BWD | 28/02/2023 | 45 | DUBE ENTERPRISE | 60.1 | 10.1 | 100 | 100
4806 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR KUENTA , SM/15718 | Augmentation | Laying of pipeline due to damage for drainage work at Keunta Piped Water Supply Scheme within Raina-II block under Burdwan Division, PHE Dte. | 112/BSD | 16/01/2025 | 59 | DEBJYOTI GOSWAMI | 3.87 | 0 | 0 | 100
4807 | PURBA BARDHAMAN | Burdwan Division | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14917 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.77 | 0 | 0 | 0
4808 | PURBA BARDHAMAN | Burdwan Division | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14917 | New | Material Requisition To Resource Division | 4033/BWD | 08/09/2023 | 0 | Resource Division | 0.33 | 0 | 0 | 0
4809 | PURBA BARDHAMAN | Central Mechanical | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14917 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at NAMA BHANDARITURI Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4107/CMD | 29/08/2023 | 30 | B.P. TRADING CORPORATION | 20.79 | 13.43 | 64.59 | 60
4810 | PURBA BARDHAMAN | Burdwan Division | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14917 | New | Material Requisition To Resource Division | 304/BWD | 24/01/2024 | 0 | Resource Division | 3.84 | 0 | 0 | 0
4811 | PURBA BARDHAMAN | Central Mechanical | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14917 | New | New service connection for Nama Bhandartikuri W/S Scheme. | BP-2023-24-385 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.19 | 0 | 0 | 0
4812 | PURBA BARDHAMAN | Burdwan Division | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14917 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to NAMA BHANDARITURI, SAHAPUR & MOUDANGA Piped Water Supply Scheme under PURBASTHALI-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3689/BWD | 23/08/2023 | 770 | THE MAHADEV CONSTRUCTION | 734.18 | 75.99 | 62.93 | 50
4813 | PURBA BARDHAMAN | Burdwan Division | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14917 | New | Different types of works involve in connection with Augmentation of SAJIARA (SM/09716), NAMA BHANDARTIKURI (SM/14917) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | 3010/BWD | 02/08/2024 | 240 | PRATIMA CONSTRUCTION | 79.16 | 0 | 0 | 2
4814 | PURBA BARDHAMAN | Central Mechanical | NAMA BHANDARITURI PIPED WATER SUPPLY SCHEME , SM/14917 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
4815 | PURBA BARDHAMAN | Burdwan Division | TAHERPUR PIPED WATER SUPPLY SCHEME , SM/18478 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 55.9 | 0 | 0 | 0
4816 | PURBA BARDHAMAN | Burdwan Division | TAHERPUR PIPED WATER SUPPLY SCHEME , SM/18478 | New | Material Requisition To Resource Division | 3831/BWD | 01/09/2023 | 0 | Resource Division | 269.94 | 0 | 0 | 0
4817 | PURBA BARDHAMAN | Durgapur W/S Division | TAHERPUR PIPED WATER SUPPLY SCHEME , SM/18478 | New | Formal Work Order for the work of " Sinking of 3 nos. 300 x 200 mm dia T/W- 150 mtr and 7 nos 200 x 200 mm dia River Bank T/W- 51 mtr with Construction of P/H cum switch room under Taherpur PWSS (JJM) Block- Galsi-II, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 377/DWSD | 15/03/2024 | 90 | S & P ENTERPRISE | 0 | 0 | 0 | 0
4818 | PURBA BARDHAMAN | Durgapur W/S Division | TAHERPUR PIPED WATER SUPPLY SCHEME , SM/18478 | New | Acceptance cum Formal Work Order for the work of " Construction of Additional Store Room at Nababhat Office Building under Galsi-II Pipe Water Supply Scheme (JJM) under Durgapur W/S Division, PHE Dte | 764/DWSD | 06/06/2024 | 90 | KIRON ENTERPRISE | 17.08 | 0 | 0 | 30
4819 | PURBA BARDHAMAN | Burdwan Division | TAHERPUR PIPED WATER SUPPLY SCHEME , SM/18478 | New | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. | 5324/BWD | 01/12/2023 | 120 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 32.86 | 100 | 100
4820 | PURBA BARDHAMAN | Durgapur W/S Division | TAHERPUR PIPED WATER SUPPLY SCHEME , SM/18478 | New | Acceptance cum Formal Work Order for the work of Trial bore with necessary allied work and supply and delivery of office furnitures for the new office setup of the EE/DWSD/PHE Dte. at Nababhat,Purba bardhaman.in connection with Taherpur W/S Scheme under Durgapur Water Supply Division, PHE Dte. | 750/DWSD | 05/06/2024 | 90 | K.M. ENTERPRISE | 3.83 | 3.82 | 100 | 100
4821 | PURBA BARDHAMAN | Central Mechanical | TAHERPUR PIPED WATER SUPPLY SCHEME , SM/18478 | New | Quotation for new service connection for Taherpur PWSS TW - 2 (Z-I) | BP-2024-25-146 | 19/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.26 | 0 | 0 | 0
4822 | PURBA BARDHAMAN | Central Mechanical | TAHERPUR PIPED WATER SUPPLY SCHEME , SM/18478 | New | Quotation for new service connection at Taherpur PWSS TW-3 | BP-2024-25-404 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.08 | 0 | 0 | 0
4823 | PURBA BARDHAMAN | Durgapur W/S Division | TAHERPUR PIPED WATER SUPPLY SCHEME , SM/18478 | New | Formal Work Order for the work of Sinking of 3 nos 300 x 200mm dia Tube Well-150 mtr and 7 Nos 200 x 200 mm dia River Bank Tube Well- 51 mtr with Construction of Pump House Cum Switch Room Chlorine Room under TAHERPUR PWSS (JJM) Block- Galsi-II, Distric- Purba Bardhaman under Durgapur W/S Division, PHE Dte | 1000/DWSD | 11/07/2024 | 520 | S & P ENTERPRISE | 102.54 | 0 | 0 | 60
4824 | PURBA BARDHAMAN | Durgapur W/S Division | TAHERPUR PIPED WATER SUPPLY SCHEME , SM/18478 | New | Formal Work Order for Laying of Rising Main including Jack Pushing and construction of Pipe Carring Bridge with Pipe supporting structure under TAHERPUR and KHANO Piped Water Supply Scheme under Durgapur W/S Division, PHE Dte. | 1506/DWSD | 05/11/2024 | 236 | MANASH GHOSH | 1114.23 | 0 | 0 | 60
4825 | PURBA BARDHAMAN | Central Mechanical | TAHERPUR PIPED WATER SUPPLY SCHEME , SM/18478 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for OHR SITE of Zone-1, 2, & 3 at TAHERPUR Water Supply Scheme [ BLOCK- Galsi-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3102/CMD | 11/12/2024 | 60 | M/S, S.S. ENTERPRISE. | 38.16 | 0 | 0 | 28
4826 | PURBA BARDHAMAN | Central Mechanical | TAHERPUR PIPED WATER SUPPLY SCHEME , SM/18478 | New | Supply, installation, commissioning of Electro-Mechanical and instrumentation components at newly constructed Boosting Station under Taherpur-khano sub surface water supply scheme under Central Mechanical Division PHE Dte. | 480/CMD | 06/02/2025 | 75 | GLACIER ENGINEERING CO | 105.71 | 0 | 0 | 0
4827 | PURBA BARDHAMAN | Durgapur W/S Division | TAHERPUR PIPED WATER SUPPLY SCHEME , SM/18478 | New | Acceptance cum Formal Work Order for Preparation and Submission of Structural Design Calculation (Civil) & Structural drawing of Proposed CWR with M.S Structural Pump House over cwr, WBSEDCL Mettering Room and - PDB Room -2 Nos, Transformer yeard -2 nos, Chlorin Room -1 No with General Arrangement Drawing of Internal Road - Drain & necessary Soil investigation at Intake Site of "THERPUR (Zone-I, II, III) and KHANO (Zone I & II) PWSS (6 Copy) under Durgapur W/s Division, PHE Dte. | 1608/DWSD | 26/11/2024 | 45 | DAFFODIL | 9.48 | 9.48 | 100 | 90
4828 | PURBA BARDHAMAN | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/18365 | New | Supply and delivery of Stationary items for the official works related with Mirghar and differents water supply scheme under JJM Programme for Central Mechanical Division and its subordinate offices of P.H.E. Dte. | 702/CMSD | 17/08/2023 | 10 | BURDWAN DISTRICT CENTRAL SERVICE CUM MARKETING INDUSTRIAL CO-OPARETIVE UNION LTD | 0.74 | 0.74 | 100 | 100
4829 | PURBA BARDHAMAN | Burdwan Division | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/18365 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 19.8 | 0 | 0 | 0
4830 | PURBA BARDHAMAN | Burdwan Division | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/18365 | New | Material Requisition To Resource Division | 3985/BWD | 08/09/2023 | 0 | Resource Division | 262.83 | 0 | 0 | 0
4831 | PURBA BARDHAMAN | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/18365 | New | New service connection charges for Mirghar PWSS TW-2 | BP-2023-24-134 | 24/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.42 | 0 | 0 | 0
4832 | PURBA BARDHAMAN | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/18365 | New | New service connection charges for Mirghar PWSS TW-3 | BP-2023-24-135 | 24/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.29 | 0 | 0 | 0
4833 | PURBA BARDHAMAN | Burdwan Division | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/18365 | New | MIRGAHAR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 700 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls and land development, drain and internal pathway at different TW site under Monteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | 3104/BWD | 19/07/2023 | 365 | M/S S. CHOUDHURY | 929.46 | 482.99 | 51.96 | 60
4834 | PURBA BARDHAMAN | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/18365 | New | continuation order Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of Assistant Engineer, under C.M.D. P.H.E. Dte. w.e.f.- 01/01/2024 to 29/02/2024. [Under JJM Works] | 1240/CMSD | 31/12/2023 | 60 | SUBRATA BHADRA | 0.79 | 0.79 | 99.86 | 100
4835 | PURBA BARDHAMAN | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/18365 | New | Supply and installation of Electro-Magnetic flow meter at AURIA, KARUI & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3106/CMD | 11/12/2024 | 60 | S.K. ELECTRICALS | 13.6 | 0 | 0 | 0
4836 | PURBA BARDHAMAN | Burdwan Division | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/18365 | New | Different types of works in connection with implementation of MIRGAHAR Piped Water Supply Scheme (SM/18365) & BAGPUR PWSS (SM/13323) under Kalna Sub-Division under Burdwan Division, PHE Dte. | 2400/BWD | 26/06/2024 | 120 | M/S S. CHOUDHURY | 301.24 | 85.64 | 91.58 | 60
4837 | PURBA BARDHAMAN | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/18365 | New | NEW SERVICE CONNECTION FOR MIRGHAR PWSS | BP-2023-24-552 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.8 | 0 | 0 | 0
4838 | PURBA BARDHAMAN | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/18365 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1,2, 3 & 4 at MIRGHAR Water Supply Scheme [ Block- MONTESWAER] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3724/CMD | 08/08/2023 | 30 | P.K. ENGINEERING | 59.87 | 36.16 | 60.39 | 75
4839 | PURBA BARDHAMAN | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/18365 | New | Supply and installation of Electro-Magnetic flow meter at Bazar Mahammadpur, Dhatrigram, Arjunpukur & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3105/CMD | 11/12/2024 | 60 | SHREE BISHNU CONSTRUCTION | 19.77 | 0 | 0 | 0
4840 | PURBA BARDHAMAN | Central Mechanical | Detailed Project Report of Ground Water Supply Based Piped Water Supply Scheme For MIRGHAR PWSS in Manteshwar Block of Purab Burdwan District under Burdwan Division, PHE Dte. , SM/18365 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
4841 | PURBA BARDHAMAN | Burdwan Division | SANKARPUR PIPED WATER SUPPLY SCHEME , SM/18337 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 6.97 | 0 | 0 | 0
4842 | PURBA BARDHAMAN | Burdwan Division | SANKARPUR PIPED WATER SUPPLY SCHEME , SM/18337 | New | Material Requisition To Resource Division | 3858/BWD | 01/09/2023 | 0 | Resource Division | 2.13 | 0 | 0 | 0
4843 | PURBA BARDHAMAN | Burdwan Division | SANKARPUR PIPED WATER SUPPLY SCHEME , SM/18337 | New | Material Requisition To Resource Division | 5066/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
4844 | PURBA BARDHAMAN | Central Mechanical | SANKARPUR PIPED WATER SUPPLY SCHEME , SM/18337 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Sankarpur Water Supply Scheme [ Block- Raina-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4034/CMD | 29/08/2023 | 30 | GOENKA ENTERPRISE | 29.4 | 23.37 | 95.56 | 95
4845 | PURBA BARDHAMAN | Central Mechanical | SANKARPUR PIPED WATER SUPPLY SCHEME , SM/18337 | New | New service connection for Shankarpur PWSS TW-1. | BP-2023-24-436 | 29/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.32 | 0 | 0 | 0
4846 | PURBA BARDHAMAN | Burdwan Division | SANKARPUR PIPED WATER SUPPLY SCHEME , SM/18337 | New | Restoration work of Sankarpur - Nibhuji bazar Road from 13.80 km to 15.75km. damaged due to laying of underground water pipe line by PHE with box cutting and Jhama with moorum consolidation under Kalna Highway sub Division of Burdwan south Highway Division P.W(Roads) Dte . During the year 2023-24 | 825/JJM | 13/09/2024 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 3.34 | 0 | 0 | 0
4847 | PURBA BARDHAMAN | Central Mechanical | SANKARPUR PIPED WATER SUPPLY SCHEME , SM/18337 | New | NEW SERVICE CONNECTION FOR SANKARPUR PWSS TW 2. | BP-2023-24-665 | 22/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.26 | 0 | 0 | 0
4848 | PURBA BARDHAMAN | Central Mechanical | SANKARPUR PIPED WATER SUPPLY SCHEME , SM/18337 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Bajitpur, Belsar & other water supply scheme under Raina-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2589/CMD | 27/08/2024 | 90 | DEY ENTERPRISE | 74.58 | 0 | 0 | 10
4849 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED TALIT-SIMDAL PWSS TO ACCOMMODATE FHTC IN BURDWAN -I BLOCK UNDER BURDWAN SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09566 | Augmentation | Route Survey & Preparation of DPR for Talit-Simdal W/S Scheme under Burdwan-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.8. | 183/BSD | 31/01/2022 | 30 | RADIANT | 2.96 | 2.94 | 100 | 1
4850 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED TALIT-SIMDAL PWSS TO ACCOMMODATE FHTC IN BURDWAN -I BLOCK UNDER BURDWAN SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09566 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
4851 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED TALIT-SIMDAL PWSS TO ACCOMMODATE FHTC IN BURDWAN -I BLOCK UNDER BURDWAN SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09566 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for Augmentation of TALIT-SIMDAL & its adjoining mouzas Piped Water Supply Scheme, Block - Burdwan - I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 5195/BWD | 24/11/2022 | 30 | ANIRUDDHA FARUQUE | 11.35 | 8.83 | 77.8 | 0
4852 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED TALIT-SIMDAL PWSS TO ACCOMMODATE FHTC IN BURDWAN -I BLOCK UNDER BURDWAN SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09566 | Augmentation | Material Requisition To Resource Division | 1556/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
4853 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED TALIT-SIMDAL PWSS TO ACCOMMODATE FHTC IN BURDWAN -I BLOCK UNDER BURDWAN SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09566 | Augmentation | Material Requisition To Resource Division | 538/BWD | 27/01/2022 | 0 | Resource Division | 20.19 | 0 | 0 | 0
4854 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED TALIT-SIMDAL PWSS TO ACCOMMODATE FHTC IN BURDWAN -I BLOCK UNDER BURDWAN SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09566 | Augmentation | Material Requisition To Resource Division | 880/BWD | 11/02/2022 | 0 | Resource Division | 9.9 | 0 | 0 | 0
4855 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED TALIT-SIMDAL PWSS TO ACCOMMODATE FHTC IN BURDWAN -I BLOCK UNDER BURDWAN SUB-DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/09566 | Augmentation | Augmentation of TALIT-SIMDAL Piped Water Supply Scheme with LDS, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test, Construction of boundary wall construction at Head work site & FHTC under Burdwan ¿ I Block, District - Purba Bardhaman. | 1876/BWD | 05/04/2022 | 1122 | M/S S.S. ENTERPRISE | 576.42 | 434.23 | 75.33 | 85
4856 | PURBA BARDHAMAN | Burdwan Division | PURANGAN PIPED WATER SUPPLY SCHEME , SM/18446 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.26 | 0 | 0 | 0
4857 | PURBA BARDHAMAN | Burdwan Division | PURANGAN PIPED WATER SUPPLY SCHEME , SM/18446 | New | Material Requisition To Resource Division | 3835/BWD | 01/09/2023 | 0 | Resource Division | 24.5 | 0 | 0 | 0
4858 | PURBA BARDHAMAN | Durgapur W/S Division | PURANGAN PIPED WATER SUPPLY SCHEME , SM/18446 | New | Acceptance cum Formal Work Order for Additional work of Construction of CWR cum Pump House with MS Structural work, Substation, Chlorine Room etc, Laying of MS pipe and necessary allied works of Surface Based Purangan and 11 Nos Mouzas Sub Surface based Pipe W/S Scheme (JJM) under Galsi-I Block, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 1112/DWSD | 02/08/2024 | 120 | MANASH GHOSH | 98.87 | 0 | 0 | 0
4859 | PURBA BARDHAMAN | Burdwan Division | PURANGAN PIPED WATER SUPPLY SCHEME , SM/18446 | New | Hydro-geological study of Sub Surface Water Flow/Storage Characteristics for Creation of Sustainable Source and Estimation of Sustainable Yield (5 Nos of Schemes) in Purba Bardhaman District, West Bengal towards implementation of water supply project. | 5324/BWD | 01/12/2023 | 120 | THE REGISTRAR JADAVPUR UNIVERSITY | 113.34 | 21.53 | 100 | 100
4860 | PURBA BARDHAMAN | Burdwan Division | PURANGAN PIPED WATER SUPPLY SCHEME , SM/18446 | New | Material Requisition To Resource Division | 192/BWD | 10/01/2024 | 0 | Resource Division | 24.5 | 0 | 0 | 0
4861 | PURBA BARDHAMAN | Central Mechanical | PURANGAN PIPED WATER SUPPLY SCHEME , SM/18446 | New | Quotation for new service connection at Purangan. | BP-2024-25-403 | 22/11/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.32 | 0 | 0 | 0
4862 | PURBA BARDHAMAN | Burdwan Division | PURANGAN PIPED WATER SUPPLY SCHEME , SM/18446 | New | Sub Surface Based Piped Water Supply Scheme with LDS, FHTC, Construction of different capacity RCC OHRs with 20.0 mtr. with Staging height including soil investigation, Construction of CWR, Chlorine Room, Guard Room, Sub Station Building, High Lift Pump House Boundary walls with gates, land development, drain and internal pathway of PURANGAN Piped Water Supply Scheme under Galsi-II Block, District:- Purba-Bardhaman [NEW SCHEME]_ 2ND CALL | 3441/BWD | 08/08/2023 | 730 | MANASH GHOSH | 1312.95 | 401.09 | 30.55 | 65
4863 | PURBA BARDHAMAN | Central Mechanical | PURANGAN PIPED WATER SUPPLY SCHEME , SM/18446 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for OHR SITE of Zone-1, 2, & 3 at PURANGAN Water Supply Scheme [ BLOCK- Galsi-I ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3099/CMD | 11/12/2024 | 373 | CHOUDHURY ENTERPRISE | 38.16 | 0 | 0 | 32
4864 | PURBA BARDHAMAN | Durgapur W/S Division | PURANGAN PIPED WATER SUPPLY SCHEME , SM/18446 | New | Formal Work Order for Additional work of Soil investigation & construction of CWR/Pump House etc, Land development of H/W Site,drain & internal Path Way, Concrete Road Restoration,FHTC with Platform with necessary allied Works of Sub Surface Based PURANGAN Pipe W/S Scheme (JJM) under Galsi - I Block, Dist - Purba- Bardhaman ,under Durgapur Water Supply Division, PHE Dte. | 1521/DWSD | 11/11/2024 | 360 | MANASH GHOSH | 789.87 | 0 | 0 | 75
4865 | PURBA BARDHAMAN | Durgapur W/S Division | PURANGAN PIPED WATER SUPPLY SCHEME , SM/18446 | New | Acceptance cum Formal Work Order for the work of Sinking of 3 Nos 300 x 200 mm dia T/W 150 mtr and 5 nos 200 x 200 mm dia River Bank T/W 51 mtr with Construction of 3 nos P/H cum switch room under chlorine room under PURANGAN PWSS (JJM), Block:- Galsi-I , Dist- Purba Bardhaman. | 372/DWSD | 15/03/2024 | 90 | MANASH GHOSH | 90.55 | 65.91 | 72.79 | 53
4866 | PURBA BARDHAMAN | Central Mechanical | PURANGAN PIPED WATER SUPPLY SCHEME , SM/18446 | New | Supply, installation, commissioning of Electro-Mechanical and instrumentation components at newly constructed Boosting Station under Purangan & 11 nos. Mouza water supply scheme under Central Mechanical Division PHE Dte. | 479/CMD | 06/02/2025 | 75 | S.P. CONSTRUCTION | 135.24 | 0 | 0 | 0
4867 | PURBA BARDHAMAN | Durgapur W/S Division | PURANGAN PIPED WATER SUPPLY SCHEME , SM/18446 | New | Acceptance cum Formal Work Order for Preparation and Submission of Structural Design Calculation (Civil) & Structural drawing of Proposed CWR with M.S Structural Pump House over cwr, WBSEDCL Mettering Room and - PDB Room -2 Nos, Transformer yeard -2 nos, Chlorin Room -1 No with General Arrangement Drawing of Internal Road - Drain & necessary Soil investigation at Intake Site of "PURANGAN (Zone-I, II, III) and 11 Nos. Mouzas PWSS under Durgapur W/s Division, PHE Dte. | 1607/DWSD | 26/11/2024 | 45 | MANASH GHOSH | 9.46 | 9.46 | 100 | 100
4868 | PURBA BARDHAMAN | Durgapur W/S Division | PURANGAN PIPED WATER SUPPLY SCHEME , SM/18446 | New | Formal Work Order for Road Restoration work of PWD Road for laying of Rising Main of 11 Nos Mouzas and Purangan PWSS under Sub Surface Based 11 Nos Mouzas Pipe W/S Scheme (JJM), Galsi-I Block, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 1290/DWSD | 06/09/2024 | 275 | MANASH GHOSH | 216.51 | 0 | 0 | 80
4869 | PURBA BARDHAMAN | Burdwan Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/18405 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 22.79 | 0 | 0 | 0
4870 | PURBA BARDHAMAN | Burdwan Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/18405 | New | Material Requisition To Resource Division | 4949/BWD | 10/11/2023 | 0 | Resource Division | 123.19 | 0 | 0 | 0
4871 | PURBA BARDHAMAN | Central Mechanical | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/18405 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Karjana & others water supply scheme under Bhatar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2394/CMD | 02/08/2024 | 90 | AHALYA ENGINEERING WORKS | 82 | 0 | 0 | 0
4872 | PURBA BARDHAMAN | Central Mechanical | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/18405 | New | Quotation for new electric service connection at Santoshpur PH NO.-2 | BP-2023-24-260 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.91 | 0 | 0 | 0
4873 | PURBA BARDHAMAN | Central Mechanical | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/18405 | New | New service connection charges for Santoshpur PWSS TW-1 | BP-2023-24-261 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.42 | 0 | 0 | 0
4874 | PURBA BARDHAMAN | Central Mechanical | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/18405 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at SANTOSHPUR Water Supply Scheme [ Block- BHATAR ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4076/CMD | 29/08/2023 | 30 | SUNRISE ENGINEERING CORPORATION | 41.68 | 0 | 0 | 60
4875 | PURBA BARDHAMAN | Burdwan Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/18405 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under Burdwan Division, P.H.E. Dte.consider 96.00 Km. run per day. [PeriodFebruary.'2025 to April'2025] | 129/DSD | 29/01/2025 | 78 | MD HASIN | 1 | 0 | 0 | 0
4876 | PURBA BARDHAMAN | Burdwan Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/18405 | New | Continuation for the work of Supply of Inspection Vehicle for inspection of different JJM related (Schemes) works as and when required including supply of driver & fuel (minimum 8 Hours duty per day) and all taxes etc. for Durgapur Sub-Division under BurdwanDivision, P.H.E. Dte.consider 96.00 Km. run per day [Period NOV.'2024 to JAN.'2025] | 886/DSD | 21/10/2024 | 78 | MD HASIN | 1 | 0.33 | 100 | 0
4877 | PURBA BARDHAMAN | Burdwan Division | SANTOSHPUR PIPED WATER SUPPLY SCHEME , SM/18405 | New | FIXING OF DISPLAY BOARD WITH M.S STRUCTURE CONTAINING SCHEME DESCRIPTION AT NASIGRAM PWSS AND OTHER SCHEMES (16 Nos) WITHIN BHATAR BLOCK UNDER BURDWAN DIVISION , PHE Dte. | 311/DSD | 21/02/2025 | 21 | SHUBHRA KANTI GHOSH | 1.39 | 0 | 0 | 0
4878 | PURBA BARDHAMAN | Burdwan Division | REAN PIPED WATER SUPPLY SCHEME , SM/18504 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 12.98 | 0 | 0 | 0
4879 | PURBA BARDHAMAN | Burdwan Division | REAN PIPED WATER SUPPLY SCHEME , SM/18504 | New | Material Requisition To Resource Division | 5077/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
4880 | PURBA BARDHAMAN | Burdwan Division | REAN PIPED WATER SUPPLY SCHEME , SM/18504 | New | Material Requisition To Resource Division | 3859/BWD | 01/09/2023 | 0 | Resource Division | 13.03 | 0 | 0 | 0
4881 | PURBA BARDHAMAN | Central Mechanical | REAN PIPED WATER SUPPLY SCHEME , SM/18504 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System, Internal House Wiring and compound lighting arrangement for Tube well No.- 1 & 2 at REAN Water Supply Scheme [ BLOCK- MEMARI- II] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1532/CMD | 05/03/2024 | 60 | SUBRATA BHADRA | 28.81 | 22.88 | 79.41 | 70
4882 | PURBA BARDHAMAN | Central Mechanical | REAN PIPED WATER SUPPLY SCHEME , SM/18504 | New | New service connection for Rean W/S scheme TW No-1 | BP-2023-24-421 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4 | 0 | 0 | 0
4883 | PURBA BARDHAMAN | Central Mechanical | REAN PIPED WATER SUPPLY SCHEME , SM/18504 | New | New service connection at Rean PWSS TW -2 | BP-2023-24-453 | 30/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.7 | 0 | 0 | 0
4884 | PURBA BARDHAMAN | Burdwan Division | REAN PIPED WATER SUPPLY SCHEME , SM/18504 | New | Different Types of work involved in connection with different New Schemes (05 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1116/BWD | 03/04/2025 | 120 | SOFIQUL ISLAM | 176.89 | 0 | 0 | 0
4885 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sahahosenpur Piped Water Supply Scheme at Srikrishnapur Village, Rajarampur Village (2 Nos. habitations), Paikpara Village, Jotdakshin Village & Jotsriram Village, Jamalpur Block under Burdwan Division, PHE Dte. | 1690/BWD | 24/02/2021 | 60 | DIPAK ROY | 70.56 | 63.87 | 117.59 | 1
4886 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Construction of boundary wall including land development at 3rd Tube Well site of Sahhosenpur water supply scheme under Jamalpur Block of Burdwan Division, PHE Dte. (Length -58.00 Mtr, Col-21 Nos). GROUP : D | 817/BSD | 20/05/2022 | 45 | SARKAR CONSTRUCTION | 3.47 | 0 | 0 | 1
4887 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Extension of pipeline including providing FHTC for SAHHOSENPUR Piped Water Supply Scheme at Jotdakshin (6 Nos), Jotshiram (20 Nos) Habitation for Sajal Gram (As per field verification report duly signed by Pradhan for Har Ghar Jal Certification) within Jamalpur Block under Burdwan Division, PHE Dte. Gr.T. | 1341/BSD | 02/08/2022 | 5 | ROY BISWAS CONSTRUCTION | 0.95 | 0 | 0 | 1
4888 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Sahahosenpur (Part) village (Sahahosenpur (Part) habitation) of Sahahosenpur Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. (Part - A) [Sl. No. : ¿17¿] | 816/BWD | 01/02/2021 | 15 | ROY BISWAS CONSTRUCTION | 4.86 | 4.86 | 100 | 1
4889 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Extension of pipeline for Sahhosenpur water supply scheme at Sahhosenpur village (Near Masjid) within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-B] | 1212/BSD | 09/09/2021 | 30 | ROY BISWAS CONSTRUCTION | 4.96 | 0 | 0 | 1
4890 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Extension of pipeline for Sahhosenpur water supply scheme at Jotsrirram village within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-C] | 1333/BSD | 30/09/2021 | 30 | PREMANANDA ROY BISWAS | 4.52 | 0 | 0 | 1
4891 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Pipeline laying at different culvert crossing for damage of PMGSY Road of Sahhosenpur water supply scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Gr.-F] | 1481/BSD | 09/11/2021 | 30 | ROY BISWAS CONSTRUCTION | 3.53 | 0 | 0 | 1
4892 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Extension of pipeline for Sahhosenpur water supply scheme at Srikrishnapur and Rajarampur village within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-H] | 1483/BSD | 09/11/2021 | 30 | DIPAK ROY | 4.7 | 2.7 | 100 | 1
4893 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Extension of pipeline for Sahhosenpur water supply scheme at Jotdakshin village within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-D] | 1524/BSD | 18/11/2021 | 30 | THREE MAA ENTERPRISE | 4.81 | 0 | 0 | 1
4894 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Extension of pipeline for Providing FHTC at Srikrishnapur village under SAHAHOSENPUR Piped Water Supply Scheme at Srikrishnapur village within Jamalpur Block , under Burdwan Division, PHE Dte. Group : B | 829/BSD | 23/05/2022 | 30 | MMS CONSTRUCTIONS PVT LTD | 4.62 | 4.54 | 100 | 1
4895 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Construction of different slab of damage valve chamber due to widening of PMGSY ROAD and sand filling of PMGSY ROAD of Sahahossenpur water supply scheme under Jamalpur Block of Burdwan Division, PHE Dte. Gr.E. | 832/BSD | 23/05/2022 | 30 | ROY BISWAS CONSTRUCTION | 2.68 | 0 | 0 | 1
4896 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Laying of interconnection of the Pump No.-1, 2 & 3 with OHR and distribution main of 350 mm dia for Sahhosenpur water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-C] | 1482/BSD | 09/11/2021 | 30 | THREE MAA ENTERPRISE | 4.83 | 4.83 | 100 | 1
4897 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Hire & fuel charges of vehicle Car No.-WB-41G-8280 for the month of January to July'2023. | 852/JJM | 30/10/2023 | 0 | MD HASIN | 2.5 | 0 | 0 | 0
4898 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Hire & fuel charges of vehicle Car No.-wb-41H-9788 for the month of August'2023 | 747/JJM | 11/10/2023 | 0 | SK. ASRAFUDDIN | 0.4 | 0 | 0 | 0
4899 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Replace Damaged & deface FHTC(By WBSRDA)with all with accessories within the command area of SAHHOSENPUR Piped W/S Scheme at SahhosenpurSaikh Para and Rajarampur village,Jamalpur Development Block under Burdwan Division,PHE Dte. | 1045/BSD | 10/06/2024 | 30 | SARKAR CONSTRUCTION | 0.83 | 0.81 | 100 | 100
4900 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Vehicle bill for the month of October'2023. | 1040/JJM | 11/12/2023 | 0 | SK.ASFIA | 0.38 | 0 | 0 | 0
4901 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Vehicle Bill (Car No.-WB-41H-9788) for the month of October'2023. | 1033/JJM | 11/12/2023 | 0 | SK. ASRAFUDDIN | 0.37 | 0 | 0 | 0
4902 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Vehicle Bill [Car No.-WB-41H-9788] for the month of December'23. | 1322/JJM | 01/02/2024 | 0 | SK. ASRAFUDDIN | 0.4 | 0 | 0 | 0
4903 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Sahhosenpur Piped Water Supply Scheme at Jamalpur Block , SM/07813 | Retrofitting | Construction of Boundary wall, Land Development for various PWSS, Block- Jamalpur, District:- Purba-Bardhaman within Burdwan Sub Division under Burdwan Division PHE Dte. | 433/BWD | 20/01/2025 | 120 | RABINDRA NATH GORANG | 132.64 | 0 | 0 | 40
4904 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Sajiara, Simla, Barapara, Bodhsah, Dubrajpur, Gobindapur, Isabpur, Kaibati, Khord Kaibati, Kubajpur, Kuksimla, Muksimpara, Sanghoshpara, Sumuria & Chhatni (15nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | 3230/BWD | 10/06/2021 | 60 | UNICON INDIA | 223.63 | 174.41 | 77.99 | 1
4905 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Work Order for Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Muragachha, Sardanga, Sihipara, Bagachra, Baragachhi, Belgachhi, Kumirpara, Lohachur, Atpara, Barea, Dhamas, Kamalapur & Kamalnagar (13nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | 3418/BWD | 25/06/2021 | 60 | MRITYUNJOY MUKHERJEE & CO. | 232.13 | 289.27 | 138.62 | 1
4906 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Majida, Rukuspur, Uttar Lakshmipur, Candipur, Gopipur, Kuturia & Mertala (7nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | 3393/BWD | 24/06/2021 | 60 | SATYANARAYAN ENGINEERS CO. OP. SOCIETY LTD. | 219.81 | 305.67 | 140.64 | 1
4907 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Supply of SS316 grade flow control valve for FHTC at Surface Water Based w/s scheme for Arsenic affected areas of Purbasthali-II block within Kalna Sub-Division under Burdwan Division, PHE Dte. (Part-A) and delivered to Barsul Divisional Store .[Part-3] | 3836/BWD | 23/07/2021 | 15 | A.K. SIKDAR | 17.62 | 35.25 | 200 | 1
4908 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Hapania, Kankhal, Khar Dattapara, Pathangram, Sontoshpur Pila & Uttar Srirampur (6nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | 3416/BWD | 25/06/2021 | 60 | M/S ASHA CONSTRUCTION | 146.22 | 124.49 | 100 | 1
4909 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Purbasthali ¿ II Block under Burdwan Division, PHE. Dte. | 149/BWD | 07/01/2022 | 30 | G.S. CONSTRUCTION & CO. | 22.15 | 21.59 | 100 | 1
4910 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Construction of wash out & over flow & drain for drain out of over flow water by 250 mm dia UPVC pipeline & soak well along with land development at Zone-I Head work site of surface based water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL-C] | 160/KSD | 19/02/2021 | 30 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 2.1 | 1.87 | 100 | 1
4911 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Supply of SS316 grade flow control valve for FHTC at surface water based water supply scheme for Arsenic affected areas of Purbasthali-II Block within Kalna Sub-Division under Burdwan Division, PHE Dte.[Part-B] and delivered at Barsul Divisional store. | 4476/BWD | 03/09/2021 | 15 | INDIA PIPE FITTING CO | 17.62 | 17.62 | 100 | 1
4912 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Augmentation of Purbasthali Piped Water Supply Scheme at Kasthashali Village (Kasthashali habitation) (Mouza) & Purbasthali village (Purbasthali habitation), Purbasthali-II Block under Burdwan Division, PHE Dte. | 1328/BWD | 12/02/2021 | 60 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 91.41 | 3.02 | 33.82 | 1
4913 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Ukhra, Dafarpota, Dampal, Mmudpur, Narayanpur, Nowapara, Patuli, Tegachhi & Gachha (9nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | 3122/BWD | 02/06/2021 | 60 | SK ALIM | 212.45 | 200.97 | 136.62 | 1
4914 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Harispur, Hatsiuri, Jajneswarpur, Jamalpur, Madhupur, Nakadaha, Nimdaha, Palasberia & Sarangpur (9nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | 3417/BWD | 25/06/2021 | 60 | ASHOK KUMAR GHOSH | 230.37 | 288.1 | 139.79 | 1
4915 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Laying of 140 mm dia HDPE Pipe from Bardangamore to Khardattapara more (Node No- 289A -289- 286) of Zone-III under Surface Based W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | 84/KSD | 20/01/2022 | 30 | UNICON INDIA | 4.84 | 4.74 | 100 | 1
4916 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Withdrawing of 110 mm dia HDPE Pipeline and relaying of 140 mm dia HDPE Pipe from Naomatha more to Bordanga more (Node No- 291 to 289-289A) under Surface Based W/S Scheme (Zone-III) within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | 87/KSD | 21/01/2022 | 30 | UNICON INDIA | 4.84 | 4.84 | 100 | 1
4917 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Sheet piling and others ancillary works to protect errosion of river bank protection area at raw water intake point of Kamalnagar WTP under Burdwan Division PHE Dte. | 2015/BWD | 18/04/2022 | 45 | CONCORD ENGINEERING | 122.2 | 122.2 | 100 | 1
4918 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Relaying of different dia UPVC pipeline at damaged portion as shown by Horizon of Zone-III of surface based water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL-B] | 148/KSD | 12/02/2021 | 30 | CHANCHAL PAL | 4.82 | 3.98 | 100 | 1
4919 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Repairing and Renovation of Filter Bed, Main Boundary Gate, resetting of Paver Block Pathway, replacement of different damaged portion of doors/windows or any other structures & other related works for Kamalnagar WTP within Kalna Sub Division under Burdwan Division, P.H.E. Dte. | 5510/BWD | 14/12/2023 | 120 | GHOSH BROTHERS | 47.97 | 26.68 | 55.61 | 5
4920 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Kamalnagar Surface Based Piped Water Supply Scheme at Biswarambha, Dhitpur, Doghori, Falea, Harishi & Moail, (6nos) Village (Mouza) under Kalna Sub Division, PHE Dte. | 3121/BWD | 02/06/2021 | 60 | IJABUL SEKH | 225.09 | 296.67 | 144.68 | 0
4921 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Painting and renovation work of WTP Building, Boundary Wall, Truss Bridge etc. at Kamalnagar of Surface Water Based Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. | 5517/BWD | 14/12/2023 | 30 | SETH ENTERPRISE | 12.63 | 12 | 100 | 100
4922 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Painting & renovation work at Purbasthali raw water pumping station within Kalna Sub-Division under Burdwan Division, PHE Dte. | 4560/BWD | 16/10/2023 | 30 | CONCORD ENGINEERING | 6.53 | 4.02 | 100 | 100
4923 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | 2296/BWD | 20/06/2024 | 616 | M/S DATTA ENTERPRISE | 579.85 | 234.86 | 86.23 | 2
4924 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting along with intake jetty protection and minor repair of WTP at Surface Water Based Piped Water Supply Scheme for Arsenic affected areas of Purbasthali-II Block , SM/08030 | Retrofitting | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
4925 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme , SM/06972 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Natu village of Natu piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-162/BWD/2020-21) | 2687/BWD | 07/08/2020 | 30 | SINGHA ROY AND CO. | 4.92 | 9.84 | 200 | 1
4926 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme , SM/06972 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Haripur village of Natu piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-161/BWD/2020-21) | 2688/BWD | 07/08/2020 | 30 | MITRA CONSTRUCTION | 4.92 | 9.84 | 200 | 1
4927 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme , SM/06972 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Haripur village of Natu piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-278/BWD/2020-21) | 3365/BWD | 21/09/2020 | 30 | MITRA CONSTRUCTION | 4.92 | 9.84 | 200 | 1
4928 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme , SM/06972 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Natu Piped Water Supply Scheme at Notu (2 Nos Habitation Part), Horipur (4 Nos Habitation Part), Uttar Mohanpur Village (Mouza), Raina-I Block under Burdwan Division, PHE Dte.(Agreement No. 49/2020-2021 OF SE/CC/PHE. DTE.) | 4767/BWD | 01/12/2020 | 90 | SINGHA ROY AND CO. | 57.87 | 82.52 | 142.9 | 1
4929 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme , SM/06972 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Natu village of Natu piped water supply scheme within Headquarters under Burdwan Division, PHE Dte. [Phase-I](Tr No.-276/BWD/2020-21) | 3363/BWD | 21/09/2020 | 30 | SINGHA ROY AND CO. | 4.46 | 8.92 | 200 | 1
4930 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme , SM/06972 | Retrofitting | Supply of SS316 grade flow control valve for FHTC at different water supply schemes within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional store.[Part-2] | 1792 /BWD | 26/02/2021 | 10 | INDIA PIPE FITTING CO | 9.7 | 3.13 | 100 | 1
4931 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme , SM/06972 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ I Block under Burdwan Division, PHE. Dte. | 39/BWD | 05/01/2022 | 30 | HAFIJUR RAHAMAN MIDYA | 15.62 | 0.62 | 100 | 1
4932 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme , SM/06972 | Retrofitting | Extension of 75 mm dia pipeline at Miya Para, Modhya Bohar & Bhagar Para Purba Bohar regarding FHTC under Satgachia (Zone-I) water supply scheme under Burdwan Division, PHE Dte.[Gr.-A] | 703/BSD | 11/06/2021 | 5 | M/S SAYAN CHAKRABORTY | 0.88 | 0.81 | 100 | 1
4933 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Natu Piped Water Supply Scheme , SM/06972 | Retrofitting | Laying Parallel Pipeline to improve drinking water supply, Construction of Boundary wall, Path Way, Drain at Head Work Site and providing leftout FHTC, Road Restoration with allied work for NATU Piped Water Supply Scheme, Block-Raina-I within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 2994/BWD | 01/08/2024 | 487 | ANWESHA CONSTRUCTION | 55.19 | 0 | 0 | 75
4934 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bamunpara Piped Water Supply Scheme , SM/06962 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Bamunpara Piped Water Supply Scheme at Bamunpara (7 Nos Habitation Part), Sahajadpur (5 Nos Habitation Part), Gulita Daspara & Purba Khanpur (4 Nos Habitation) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte.(Agreement No. 69/2020-2021 OF SE/CC/PHE. DTE.) | 5002/BWD | 07/12/2020 | 90 | M/S S. CHOUDHURY | 50.71 | 84.67 | 185.31 | 1
4935 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bamunpara Piped Water Supply Scheme , SM/06962 | Retrofitting | Supply of SS316 grade flow control valve for FHTC at different water supply schemes within Kalna Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional store.[Part-2] | 1792 /BWD | 26/02/2021 | 10 | INDIA PIPE FITTING CO | 9.7 | 5.47 | 100 | 1
4936 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bamunpara Piped Water Supply Scheme , SM/06962 | Retrofitting | Providing FHTC - Sahajadpur (5 nos habitations)-170 nos & Bamunpara (7 nos habitation)-170 nos & Extension of pipeline to provide house connection at Tentulia village & Sahajadpur village for Drain out water of wash out & over flow line from existing OHR at Head Works Site of BAMUNPARA W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 1417/BWD | 10/03/2022 | 30 | M/S UNIQUE | 16.5 | 16.33 | 100 | 1
4937 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Bamunpara Piped Water Supply Scheme , SM/06962 | Retrofitting | Laying of UPVC pipeline & providing FHTC work at Bamunpara, Sahajadpur, Tentulia & Gulita village of BAMUNPARA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2423/BWD | 30/05/2023 | 30 | GOUTAM KUMAR MITRA | 9.65 | 9.4 | 100 | 100
4938 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Putsuri village of Putsuri piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-546/BWD/2020-21) | 3532/BWD | 25/09/2020 | 30 | PRONAB KUMAR DEY | 4.92 | 9.84 | 200 | 1
4939 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Putsuri Piped Water Supply Scheme at Denur (6 Nos Habitation Part) & Putsuri (11 Nos Habitation Part) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte.(Agreement No. 55/2020-2021 OF SE/CC/PHE. DTE.) | 4887/BWD | 07/12/2020 | 90 | M/S S. CHOUDHURY | 77.12 | 100.09 | 182.68 | 1
4940 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Denur village of Putsuri piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-562/BWD/2020-21) | 3804/BWD | 08/10/2020 | 30 | IJABUL SEKH | 4.92 | 9.84 | 200 | 1
4941 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Load Enhancement charges bill for Putsuri water supply scheme under Burdwan Division, PHE Dte.[Application No.-5003378053, Consumer Id-500684865] | 300/DW/22-23 | 05/07/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.56 | 0 | 0 | 0
4942 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Work Order for "Providing Functional house hold tap connections for Sajal Gram villages within Monteswar Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Putsuri water supply Scheme) (Sl No-9) | 344/KSD | 17/04/2023 | 30 | HASAN CONSTRUCTION | 0.88 | 0 | 0 | 0
4943 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Work Order for "Providing Functional house hold tap connections for Sajal Gram Village within Monteswar Block under Kalna Sub-Division under Burdwan Division, PHE Dte. (Putsuri water supply scheme)" | 344/KSD | 17/04/2023 | 30 | HASAN CONSTRUCTION | 0.88 | 0 | 0 | 0
4944 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Supply of 10 mm NB Gun-metal Ferrule conforming to IS: 2692-1989 for Water tap connection in each house hold from existing distribution system within Scheme jurisdiction in different Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. and delivered at Borsul Divl. Store. [Part-5]. | 3590/BWD | 13/07/2021 | 30 | PREMANANDA ROY BISWAS | 127.5 | 14.26 | 200 | 1
4945 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Extension of 75 mm dia UPVC pipeline at different places of Denur village under Putsuri & its adjoining mouzas water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.[SL NO.-C] | 169/KSD | 19/02/2021 | 30 | M/S S. CHOUDHURY | 2.37 | 0 | 0 | 1
4946 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PUTSURI Piped Water Supply Scheme at Kasa (6 Nos. Habs.), Purba Balarampur, Bhurkunda (7 Nos. Habs.), Patun (5 Nos. Habs.) & Bigha (3 Nos. Habs.) Village (Mouza), Monteswar Block under Burdwan Division, PHE Dte. | 7020/BWD | 17/12/2021 | 60 | INVENT ENGINEERS CO. OPERATIVE SOCIETY LTD. | 53.94 | 8.54 | 100 | 1
4947 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Laying of different dia.UPVC pipeline at the damaged portion from Denur to Mousa Daukadanga under Putsuri & its adjoining mouzas water supply scheme within Kalna Sub-Division, under Burdwan Division, PHE Dte. | 6013/BWD | 05/10/2021 | 30 | D.M. ENTERPRISE | 23.17 | 0 | 0 | 1
4948 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of March & April'23. | 367/JJM | 18/07/2023 | 0 | PARTHA PRATIM ACHARYA | 0.77 | 0 | 0 | 0
4949 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Hire & fuel charges of vehicle Car No.-WB-41H-3668 for the month of May & June'2023. | 744/JJM | 11/10/2023 | 0 | MD HASIN | 0.53 | 0 | 0 | 0
4950 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Providing FHTC with laying of 75 mm dia HDPE Pipe of Putsuri PWSS of near Health Centre under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | 272/DSD | 15/03/2024 | 30 | SAYAK DEY | 0.97 | 0 | 0 | 0
4951 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Relaying of different dia UPVC Pipeline at the different damage portion towards Mojaharnagar, Gulita, Denur & Putsuri of Putsuri PWSS within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | 985/KSD Dt- 24.09.2021 | 24/09/2021 | 30 | M/S S. CHOUDHURY | 3.66 | 3.65 | 100 | 100
4952 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Work order for "Interconnection of rising main from 4th Tube Well site to Over Head Reservoir for FHTC related water supply under Putsuri W/S Scheme within Kalna Sub-Division under Burdwan Division , PHE Dte." | 1309/KSD | 23/08/2023 | 15 | PRONAB KUMAR DEY | 2.1 | 1.78 | 100 | 100
4953 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Putsuri Piped Water Supply Scheme , SM/06963 | Retrofitting | Providing FHTC with laying of 75 mm dia HDPE Pipe of Putsuri PWSS of Ghosh para village under Manteswar Block under Durgapur Sub Division of Burdwan Division ,P.H.E.Dte | 271/DSD | 15/03/2024 | 30 | SAYAK DEY | 0.97 | 0.96 | 100 | 100
4954 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme , SM/06964 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of CHAKTENTUL Piped Water Supply Scheme at Chaktentul (1 No Part, 2 Nos Habitation), Bharatpur (2 Nos Habitation) Village (Mouza), Galsi-I Block under Burdwan Division, PHE Dte.(Agreement No. 71/2020-2021 OF SE/CC/PHE. DTE.) | 5005/BWD | 10/12/2020 | 90 | SUPRIYA RAY | 75.14 | 75.59 | 180.5 | 1
4955 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme , SM/06964 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Chaktentul village and Chaktentul habitation of Chaktentul piped water supply scheme within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | 4455/BWD | 10/11/2020 | 30 | SAIKAT RAY | 4.92 | 9.84 | 200 | 1
4956 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme , SM/06964 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
4957 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme , SM/06964 | Retrofitting | Repairing of valve chamber & Construction of new valve chamber and supply of sluice valve at Head Works Site for CHAKTATUL PWSS within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | 905/DSD | 15/12/2023 | 30 | SAIKAT RAY | 0.97 | 0 | 0 | 0
4958 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme , SM/06964 | Retrofitting | Supply of 10 mm NB Gun-metal Ferrul conforming to IS:2692-1989 for water tap connection in each house hold from existing distribution system within scheme jurisdiction in different piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division PHE Dte. and delivered at Barsul Divisional Store. [Part-6] | 3402/BWD | 24/06/2021 | 30 | A.K. SIKDAR | 91.8 | 50.49 | 165.6 | 1
4959 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme , SM/06964 | Retrofitting | Continuation work order for supply of 10 mm NB Gun-Metal /Brass Ferrul conforming to IS:2692-1989 for water tap connection in each household from existing distribution system within scheme jurisdiction in different piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. and delivered at Barsul Divisional Store.[Part-7] | 2942/BWD | 04/05/2021 | 10 | KISHORE GHOSH | 3.94 | 0 | 0 | 1
4960 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme , SM/06964 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-37C-8293) for the month of June & July'23. | 633/JJM | 13/09/2023 | 0 | SUJAUDDIN SEKH | 0.78 | 0 | 0 | 0
4961 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme , SM/06964 | Retrofitting | Hire & fuel charges of vehicle Car No.-WB-37C-8293 for the month of August'2023. | 746/JJM | 11/10/2023 | 0 | SUJAUDDIN SEKH | 0.39 | 0 | 0 | 0
4962 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme , SM/06964 | Retrofitting | Vehicle bill for the office of the Assistant Engineer, Durgapur Sub-Division, PHE Dte. for the month of May'23. | 562/JJM | 24/08/2023 | 0 | SUJAUDDIN SEKH | 0.4 | 0 | 0 | 0
4963 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme , SM/06964 | Retrofitting | Laying of interconnection of Head Works Site to distribution main line for CHAKTATUL PWSS within Durgapur Sub- Division (Burdwan North) under Burdwan Division PHE Dte. | 906/DSD | 15/12/2023 | 45 | SAIKAT RAY | 0.95 | 0 | 0 | 100
4964 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Chaktentul Piped Water Supply Scheme , SM/06964 | Retrofitting | Vehicle bill for the month of November'23. | 1138/JJM | 29/12/2023 | 0 | SUJAUDDIN SEKH | 0.38 | 0 | 0 | 0
4965 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Uttar Rameswarpur village of Nandai Piped Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [Sl.No : 4B] | 3409/BWD | 25/06/2021 | 30 | AURGHA BHATTACHARYA | 4.92 | 0 | 0 | 1
4966 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1132/DW | 26/02/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 221 | 0 | 0 | 0
4967 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nandai Piped Water Supply Scheme at Nandai (Part) (7 Nos Habitation Part), Nagargachhi, Pardupra & Uttar Rameswarpur (Part) Village (Mouza), Kalna-I Block under Burdwan Division, PHE Dte. | 3599/BWD | 13/07/2021 | 60 | INDIAN ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 110.43 | 107.33 | 100 | 1
4968 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of NANDAI Piped Water Supply Scheme at opposite site of railway track at Malatipur, Nagargachhi, Mirjapur, Durgapur habitations, Kalna - I Block under Burdwan Division, PHE Dte. | 1869/BWD | 05/04/2022 | 30 | KOUSIK MALLICK | 51.64 | 49.63 | 100 | 1
4969 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of BAIDYAPUR (Z-I) PWSS, Block - Kalna - II and NANDAI PWSS, Block - Kalna - I Piped Water Supply Scheme, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. | 2424/BWD | 30/05/2023 | 45 | KOUSIK MALLICK | 19.84 | 9.14 | 100 | 100
4970 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Material Requisition To Resource Division | 1109/BWD | 26/02/2022 | 0 | Resource Division | 67.99 | 0 | 0 | 0
4971 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Quotation for new service connection charges at Nandai PWSS [PH No.-V][Ref ID-503434397] | 1086/JJM | 20/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 9.28 | 0 | 0 | 0
4972 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-41J-6795) for the office of the Superintending Engineer, Central Circle, PHE Dte. for the month of January & February'23. | 218/JJM | 06/06/2023 | 0 | MD HASIN | 0.79 | 0 | 0 | 0
4973 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Construction of Pump House cum switch room (5.40 mtr x 3.60 mtr) with sanitary arrangement (as per drawing no. PHE/SE/CC/PH/DWG-01/2022-2023) at NANDAI Water Supply Scheme within Kalna Sub-Divn. under Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | 4820/BWD | 08/11/2023 | 352 | SK BADIUZZAMAL | 5.69 | 5.69 | 100 | 100
4974 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Work Order for "Laying of pipeline at gap portion of old and new pipeline of Nandai Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division , PHE Dte. " | 1714/KSD | 04/12/2023 | 7 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.64 | 0.64 | 100 | 100
4975 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Work Order For "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR NANDAI PWSS & SHIKARPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 1980/KSD | 09/02/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.66 | 0.33 | 100 | 100
4976 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Work Order for "Restoration of 350 mm dia DI Rising Main with other allied works in connection with Augmentation of Nandai (SM/08104) Piped Water Supply Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte." | 2192/KSD | 15/03/2024 | 15 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 3.3 | 3.14 | 100 | 100
4977 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Vehicle bill (Car No.-WB-04G-7127) for the month of September'2023. | 1041/JJM | 11/12/2023 | 0 | PARTHA PRATIM ACHARYA | 0.39 | 0 | 0 | 0
4978 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Providing FHTC in the left out portion of Natungram, Kutirdanga, Kharinan village along with other ancillary work in order to declare Sajal Gram under the command area of NANDAI PWSS (SM/08104) within Kalna Sub Division under Burdwan Division, PHE. Dte. | 1447/BWD | 22/05/2025 | 120 | MUKHERJEE ENTERPRISE | 42.77 | 0 | 0 | 0
4979 | PURBA BARDHAMAN | Burdwan Division | Retrofitting wroks for Providing Functional Household Tap Connection (FHTC) within the command area of of Nandai and adj.Mouzas Piped Water Supply Scheme, Block Kalna-I, District Purba Bardhaman , SM/08104 | Retrofitting | Providing left out FHTC at Different places under the Command area of Nandai PWSS under Kalna Sub-Division under Burdwan Division, PHE Dte. | 3720/BWD | 29/10/2024 | 56 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 9.32 | 2.45 | 20.94 | 100
4980 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jageswardihi Piped Water Supply Scheme , SM/06966 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jaggeswardihi village of Jaggeswardihi Piped Water Supply Scheme within Katwa Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [SL. No : 9A] (T.R. No.-219/BWD/2020-21) | 2630/BWD | 04/08/2020 | 30 | ABDUL HAI | 4.92 | 0 | 0 | 1
4981 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jageswardihi Piped Water Supply Scheme , SM/06966 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Chaitynapur village of Jaggeswardihi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-204/BWD/2020-21) | 2604/BWD | 04/08/2020 | 30 | SUBRATA GUPTA | 4.92 | 9.84 | 200 | 1
4982 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jageswardihi Piped Water Supply Scheme , SM/06966 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jaggeswardihi (Part) village of Jaggeswardihi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-251/BWD/2020-21) | 3383/BWD | 22/09/2020 | 30 | SUBRATA GUPTA | 4.92 | 9.84 | 200 | 1
4983 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jageswardihi Piped Water Supply Scheme , SM/06966 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Jaggeswardihi (Part) village of Jaggeswardihi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-250/BWD/2020-21) | 3413/BWD | 22/09/2020 | 30 | ABDUL HAI | 4.92 | 9.84 | 200 | 1
4984 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jageswardihi Piped Water Supply Scheme , SM/06966 | Retrofitting | Extension of pipeline from the existing distribution system within scheme jurisdiction at Kanaidanga under Jaggeswardihi piped water supply scheme under Mongalkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. [Phase-2] | 82/KTS | 09/02/2021 | 15 | HAMID SK | 1.25 | 0 | 0 | 1
4985 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jageswardihi Piped Water Supply Scheme , SM/06966 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jageswardihi Piped Water Supply Scheme at Kaichar & Sitalgram Village (Mouza), Mongolkot Block under Burdwan Division, PHE Dte. | 6694/BWD | 01/12/2021 | 60 | HAMID SK | 58.77 | 40.93 | 100 | 1
4986 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Jageswardihi Piped Water Supply Scheme , SM/06966 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Jaggeswardihi Piped Water Supply Scheme at Kanaidanga & Jageswardihi (1 Part & 1 Habitation) Village (Mouza), Mangolkote Block under Burdwan Division, PHE Dte.[Agreement No. 578/BWD OF 2020-2021] | 436/BWD | 19/01/2021 | 45 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 38.09 | 75.5 | 200 | 0
4987 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme , SM/06967 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Palla(Pt-B) village of Palla piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-246/BWD/2020-21) | 2738/BWD | 10/08/2020 | 30 | S.C. ENTERPRISE | 4.92 | 9.84 | 200 | 1
4988 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme , SM/06967 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Palla(Pt-A) village of Palla piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-487/BWD/2020-21) | 3972/BWD | 14/10/2020 | 30 | JAYANTA CHAKRABORTY | 4.92 | 9.84 | 200 | 1
4989 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme , SM/06967 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Palla (Pt-B) village of Palla Piped Water Supply Scheme within Burdwan Sub-Divn. under Burdwan Division, PHE. Dte. [Phase - I] [GROUP : ¿11B¿] | 4912/BWD | 08/12/2020 | 30 | S.C. ENTERPRISE | 4.92 | 9.76 | 200 | 1
4990 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme , SM/06967 | Retrofitting | Additional work providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Palla piped water supply scheme at Palla village (Mouza) Memari-I Block under Burdwan Division, PHE Dte. [Gr.-F] | 685/BSD | 09/06/2021 | 30 | S.C. ENTERPRISE | 0.77 | 1.52 | 200 | 1
4991 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme , SM/06967 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of PALLA Piped Water Supply Scheme at Palla(Paschim Palla Habitation Part)village(Mouza)Memari-I Block under Burdwan Division, PHE Dte.Gr.C | 199/BSD | 01/02/2022 | 30 | MUKHERJEE ENTERPRISE | 4.58 | 4.51 | 100 | 1
4992 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme , SM/06967 | Retrofitting | Providing Functional Household Tap Connection(FHTC)from existing distribution system within the command area of PALLA Water supply scheme at Palla(Paschim palla Habitation part) village (Mouza) opposite side of navigation cannel, in Memari-I Block including leftout household water tap connection(FHTC) under Burdwan Division, PHE Dte. Group : B | 984/BSD | 16/06/2022 | 30 | DUBE ENTERPRISE | 4.22 | 4.21 | 100 | 1
4993 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme , SM/06967 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Palla Piped Water Supply Scheme at Palla (Part) (7 Nos Habitation Part) Village (Mouza), Memari-I Block under Burdwan Division, PHE Dte. | 3345/BWD | 21/06/2021 | 30 | M/S ASHA CONSTRUCTION | 27.79 | 26.27 | 200 | 0
4994 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Palla Piped Water Supply Scheme , SM/06967 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Palla(Pt-A) village of Palla piped water supply scheme within Burdwan Sub-Division under Burdwan Division, PHE Dte. [Phase-I](Tr No.-245/BWD/2020-21) | 2746/BWD | 10/08/2020 | 30 | JAYANTA CHAKRABORTY | 4.92 | 9.84 | 200 | 1
4995 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Teandul PWSS , SM/06746 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of TEANDUL Piped Water Supply Scheme at Raina-I Block under Burdwan Division, PHE Dte.(Agreement No. 61/2020-2021 OF SE/CC/PHE. DTE.) | 4881/BWD | 07/12/2020 | 90 | ASHOK KUMAR GHOSH | 70.51 | 72.26 | 159.54 | 1
4996 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Teandul PWSS , SM/06746 | Retrofitting | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Madhuban, Sultanbad, Dhamas & Teyandul of TEANDUL Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1228/BWD | 17/03/2023 | 60 | M/S UNIQUE | 31.31 | 25 | 100 | 0
4997 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Teandul PWSS , SM/06746 | Retrofitting | Construction of Retaining wall for protection of soil erosion at Headwork site (Western Side) at TEANDUL Piped Water Supply Scheme under Burdwan Division, PHE Dte. [Group : B] | 241/AE/HQ | 20/04/2022 | 30 | ROY CONSTRUCTION | 4.82 | 0 | 0 | 1
4998 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting at Teandul PWSS , SM/06746 | Retrofitting | Construction of Retaining wall for protection of soil erosion at Headwork site (southern side) at Teandul PWSS under Burdwan Division, PHE Dte. [Group: ¿H¿] | 1902/AE/HQ | 16/11/2021 | 30 | ASHOK KUMAR GHOSH | 4.5 | 0 | 0 | 1
4999 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Alipur Piped Water Supply Scheme , SM/07819 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of ALIPUR Piped Water Supply Scheme at Debipur, Alipur & Benapur (2 Nos Habitation) Village (Mouza), Memari-I Block under Burdwan Division, PHE Dte. [Agreement No. 92/2020-2021 OF SE/CC/PHE. DTE.] | 812/BWD | 01/02/2021 | 90 | MD HASIN | 90.85 | 37.63 | 200 | 0
5000 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Alipur Piped Water Supply Scheme , SM/07819 | Retrofitting | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for ALIPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | 430/BWD | 20/01/2025 | 287 | DULAL MAJUMDER | 117.26 | 0 | 0 | 30
5001 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Alipur Piped Water Supply Scheme , SM/07819 | Retrofitting | Interconnection of 150MM DI pipeline from 2no TW to delivery line for smooth water supply for FHTC under ALIPUR pwss within Memari- I block under Burdwan Division PHE Dte. | 09/BSD | 02/01/2025 | 243 | MUKHERJEE ENTERPRISE | 0.97 | 0 | 0 | 100
5002 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Alipur Piped Water Supply Scheme , SM/07819 | Retrofitting | Construction of sluice valve chamber with supply of sluice valve for smooth water supply for FHTC under ALIPUR pwss within Memari- I block under Burdwan Division PHE DTE | 1863/BSD | 22/08/2024 | 30 | ROY CONSTRUCTION | 0.95 | 0 | 0 | 100
5003 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme , SM/07548 | Retrofitting | Formal Work Order for Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Dwariapur Piped Water Supply Scheme at Gonna (1 No. Habitation), Alutia (Part), Dwariapur (7Nos Habitation) & Lakshmiganj (5 Nos Habitation) Village (Mouza), Ausgram-I Block under Burdwan Division, PHE Dte.[Agreement No. 109/2020-2021 OF SE/CC/PHE. DTE.] | 1600/BWD | 22/02/2021 | 60 | RANADHIR SINHA | 81.21 | 45.58 | 100 | 1
5004 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme , SM/07548 | Retrofitting | Restoration of damaged pipeline of distribution main at Laxmiganj village and laying of parallel line at Gonna village for providing FHTC within Dwariapur W/S Scheme in Ausgram-II Block under Burdwan Division, P.H.E. Dte. [Gr.-G] | 06/DSD | 03/01/2022 | 30 | RANADHIR SINHA | 2.11 | 2.11 | 100 | 1
5005 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme , SM/07548 | Retrofitting | Restoration of damaged concrete road in connection with laying distribution system at Laxmiganj, Gonna and Gopinathbati village within Dwariapur Piped Water Supply Scheme at Ausgram-I Block within Durgapur Sub-Division under Burdwan Division, PHE Dte. [Gr.-H] | 80/DSD | 11/02/2022 | 15 | RANADHIR SINHA | 4.73 | 4.73 | 100 | 1
5006 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme , SM/07548 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Ausgram-I Block under Burdwan Division, PHE. Dte. | 120/BWD | 07/01/2022 | 30 | ANIRUDDHA FARUQUE | 12.33 | 12.56 | 100 | 1
5007 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme , SM/07548 | Retrofitting | Making Connection with Rising Main And Over Head Reservoir of Dwariapur W/S Scheme within Durgapur Sub-Division in Ausgram-I Block under Burdwan Division, P.H.E. Dte.[Gr.-C] | 133/DSD | 02/03/2022 | 15 | RANADHIR SINHA | 0.34 | 0 | 0 | 1
5008 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme , SM/07548 | Retrofitting | Restoration of damaged concrete road in connection with providing FHTC work at Laxmiganj, Gonna and Gopinathbati and Dwariapur village within Dwariapur Piped Water Supply Scheme at Ausgram-I Block within Durgapur Sub-Division under Burdwan Division, PHE Dte.[SL-B] | 163/DSD | 16/03/2022 | 15 | RANADHIR SINHA | 4.12 | 4.12 | 100 | 1
5009 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) under the command area of Dwariapur Piped Water Supply Scheme , SM/07548 | Retrofitting | Modification to the distribution network by making a loop to augment the water supply to FHTC at Gopinathbati village of Dwariyapur and its adjoining mouzas W/S Scheme under Durgapur Sub-Division, Burdwan Division, P.H.E. Dte._2nd call[SL-05] | 180/DSD | 18/04/2023 | 21 | ANIRUDDHA FARUQUE | 0.92 | 0.92 | 100 | 100
5010 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block , SM/07798 | Retrofitting | Extension of pipeline for NABAGRAM Piped Water Supply Scheme at Konarpara [24 No's]Total 24 No's FHTC Work for Sajal Gram (As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout husehold water tap connection (FHTC) under Burdwan Division, PHE Dte".Gr. B | 1351/BSD | 02/08/2022 | 5 | BHARAT CONSTRUCTION | 0.97 | 0 | 0 | 1
5011 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block , SM/07798 | Retrofitting | Extension of pipeline for NABAGRAM Piped water Supply Scheme at Kalupukur[2 Nos]Kalanabagram[5 Nos]Dadpur[8 Nos],Paschim Memari[6 Nos]Pingur[3 Nos]Chuadanga:3 Nos Total 27 Nos FHTC Work for Sajal Gram(As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout household water tap connection(FHTC)under Burdwan Division,PHE Dte.Gr.C. | 1352/BSD | 02/08/2022 | 5 | BHARAT CONSTRUCTION | 0.97 | 0 | 0 | 1
5012 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block , SM/07798 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Nabagram Piped Water Supply Scheme at Konar Village (2 Nos. habitations), Dadpur Village (4 Nos. habitations), Paschim Memari Village (2 Nos. habitations), Pingur Village & Nabagram Village (4 Nos. habitations), Memari - I Block under Burdwan Division, PHE Dte.[Agreement No. 681/BWD OF 2020-2021] | 1400/BWD | 15/02/2021 | 60 | UNIQUE AGENCY | 68.1 | 133.59 | 190.82 | 1
5013 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block , SM/07798 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Memari-I Block (Daluibazar-II, Gopegantar-I & II G.P.) under Burdwan Division, PHE. Dte. Dte._Part-A. | 209/BWD | 11/01/2022 | 30 | M/S ANAND CONSTRUCTION | 21.11 | 0 | 0 | 1
5014 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block , SM/07798 | Retrofitting | Sinking of 150mm. dia. 100 Mtr. Deep tube well & Laying Distribution pipeline including FHTC under Jal Swapna Scheme for SWASTI PALLY Mini Piped W/S. Scheme within NABAGRAM Piped W/S. Scheme under Burdwan Division, PHE. Dte. | 890/BWD | 01/03/2023 | 45 | BAMDEB CONSTRUCTION & CO | 30.68 | 16.9 | 100 | 100
5015 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block , SM/07798 | Retrofitting | Extension of pipeline for NABAGRAM Piped Water Supply Scheme at Konarpara [24 No's]Total 24 No's FHTC Work for Sajal Gram (As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout husehold water tap connection(FHTC) under Burdwan Division, PHE Dte. | 1351-A/BSD | 02/08/2022 | 5 | BHARAT CONSTRUCTION | 0.97 | 0.97 | 100 | 1
5016 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Nabagram Piped Water Supply Scheme at Memari-I Block , SM/07798 | Retrofitting | Extension of pipeline for NABAGRAM Piped Water Supply Scheme at Kalupukur [2 No's], Kalanabagram[5 No's] Dadpur [8 No's], Paschim Memari [6 No's], Pingur [3 No's] Chuadanga [3 No's] Total 27 No's FHTC Work for Sajal Gram (As per Resulation taken in Special Gram Sava on 01-08-2022 within Memari-I Block including leftout household water tap connection (FHTC) under Burdwan Division, PHE Dte | 1352-A/BSD | 02/08/2022 | 5 | BHARAT CONSTRUCTION | 0.97 | 0.97 | 100 | 1
5017 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme , SM/07863 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Khetpur Palashi (Part-A) village of Khetpur Palashi piped water supply scheme within Katwa Sub-Division under Burdwan Division, PHE Dte. (Tr No.-471/BWD/2020-21) | 241/KTS | 01/10/2020 | 4 | CHANCHAL PAL | 1.19 | 0 | 0 | 1
5018 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme , SM/07863 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system at KHETIA Pipe Water Supply Scheme of Burdwan -I Block under Burdwan Sub-Division under Burdwan Division, PHE Dte. | 3963/BWD | 13/09/2022 | 30 | M/S UNIQUE | 6.23 | 5.2 | 100 | 1
5019 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme , SM/07863 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Khetia Piped Water Supply Scheme at Simdali (P) village (09 Nos. (P) habs), Burdwan-I Block under Burdwan Division, PHE Dte. [Agreement No. 749/BWD OF 2020-2021] | 1496/BWD | 18/02/2021 | 60 | H SAMANTA | 52.6 | 18.56 | 100 | 1
5020 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme , SM/07863 | Retrofitting | Providing Functional Household Tap Connection(FHTC)from existing distribution system at Khetia Water Supply Scheme(Habitation-Khetia,Gopalbati,Tentral)of Burdwan-I Block under Burdwan Sub-Division under Burdwan Division,PHE Dte. | 11/BSD | 06/01/2023 | 15 | M/S UNIQUE | 0.92 | 0.92 | 100 | 0
5021 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme , SM/07863 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Khetia Piped Water Supply Scheme at Gopalbati village, Khetia village (04 Nos. habs) & Tentral village Burdwan-I Block under Burdwan Division, PHE Dte. [Agreement No. 748/BWD OF 2020-2021.] | 1495/BWD | 18/02/2021 | 45 | H SAMANTA | 29.16 | 40.09 | 166.15 | 1
5022 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme , SM/07863 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Tentral Village, Burdwan - I Block within Khetia PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 826/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0.72 | 100 | 100
5023 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme , SM/07863 | Retrofitting | Designing, Making and Erection of Sign Board for SAJAL GRAM in Gopalbati Village, Burdwan - I Block within Khetia PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 825/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0.72 | 100 | 100
5024 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme , SM/07863 | Retrofitting | Allied work of interconnection between 2nd TW to distribution line for FHTC work for KHETIA Piped Water Supply Scheme and its adjoining mouzas within BURDWAN-I BLOCK under Burdwan Division, PHE Dte. | 1016/BSD | 07/06/2024 | 45 | ROY CONSTRUCTION | 4.79 | 4.78 | 100 | 100
5025 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme , SM/07863 | Retrofitting | KHETIA Piped Water Supply Scheme with Rising Main & Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation at different TW site under BARDHAMAN-I Block, District:- Purba-Bardhaman. | 5330/BWD | 04/12/2023 | 542 | THE DEVELOPER | 68.62 | 23.12 | 33.7 | 56
5026 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of KHETIA Piped Water Supply Scheme , SM/07863 | Retrofitting | Restoration of Pump House at Head Work site of KHETIA Piped water supply scheme at Burdwan-I Block under Burdwan Division, Dist.-Purba Bardhaman. | 1000/BSD | 06/06/2024 | 30 | DEBJYOTI GOSWAMI | 0.96 | 0 | 0 | 80
5027 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Balgona village and Balgona Habitation of Balgona piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | 4333/BWD | 05/11/2020 | 30 | S.S. CONSTRUCTION | 4.86 | 0 | 0 | 1
5028 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Continuation work order for Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Haripur village and Haripur habitation of Balgona piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | 4334/BWD | 05/11/2020 | 30 | S.S. CONSTRUCTION | 4.03 | 0 | 0 | 1
5029 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Water tap connection in each house hold from existing distribution system within scheme jurisdiction in Balgona village and Balgona habitation of Balgona piped water supply scheme within Durgapur (Bardhaman North) Sub-Division under Burdwan Division, PHE Dte. [Phase-I] | 3347/BWD | 18/09/2020 | 30 | S.S. CONSTRUCTION | 4.86 | 0 | 0 | 1
5030 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Sinking of additional 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for BALGONA Piped Water Supply Scheme, Block - Bhatar, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 2389/BWD | 10/05/2022 | 30 | ANIRUDDHA FARUQUE | 9.03 | 8.05 | 100 | 1
5031 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Balgona Piped Water Supply Scheme at Balgona village (Balgona (P), Patna habs), Bhatar Block under Burdwan Division, PHE Dte. | 1574/BWD | 22/02/2021 | 60 | M/S S. CHOUDHURY | 63.94 | 32.4 | 100 | 1
5032 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Laying of additional pipeline to facilitate FHTC at Patna village of Bolgona and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [SL-11] | 711/DSD | 30/12/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.09 | 0 | 0 | 0
5033 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Extension of pipeline at Patna village of Bolgona and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [SL-10] | 710/DSD | 30/12/2022 | 30 | NANGTASWAR CO. OP. LABOUR CONT. AND CONSTRUCTION SOCIETY LTD. | 4.65 | 0 | 0 | 0
5034 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Surging of existing Tube Well at Headwork site for Bolgona Water Supply Scheme , Block - Bhatar, Dist - Purba Barddhaman under Durgapur Sub Division, PHE Dte.[SL-C] | 164/DSD | 16/03/2022 | 5 | J. K. CORPORATION | 0.54 | 0 | 0 | 1
5035 | PURBA BARDHAMAN | Central Drilling | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 120 mtrs. Depth) by utilising Departmental machineries for Balgana W/S Scheme, Bhatar block under Purba Burdwan District, CDD PHE Dte. | 63/CDD | 06/04/2023 | 30 | C.M. ENTERPRISE | 9.91 | 7.52 | 100 | 100
5036 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | WBSEDCL quotation of Balgona piped water supply scheme under Burdwan Division, PHE Dte. [Ref. ID-503447092] | 713/JJM | 05/10/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.68 | 0 | 0 | 0
5037 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Placing of pipeline at "Patna and adj" villages of Balgona and its adjoining mouza's Piped W/S Scheme at Bhatar Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [SL-A] | 333/DSD | 27/06/2022 | 15 | R.K. ENTERPRISE | 1.11 | 0 | 0 | 0
5038 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Providing Functional Household Tap Connection (FHTC) by sinking of tube well 250 x 150 mm. dia. (2 Nos.) Constn. of Pump House, Boundary Wall and Land Development within command area of BALGANA & BHATAKUL W/S. Scheme, Bhatar Block under Burdwan Division, PHE. Dte. | 596/BWD | 07/02/2025 | 120 | M/S S.S. ENTERPRISE | 114.01 | 0 | 0 | 0
5039 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Sinking of additional 300 X 200 mm dia. Tube Well, 420 Mtrs. Depth by D.R. Rig method using UPVC Pipe (CD) and UPVC Deep Well Screen (RDS) for AUGMANTATION of BHATAR & BALGONA Water Supply Scheme within Bhatar Block, Dist.- Purba Bardhaman within Durgapur Sub Division under Burdwan Division PHE Dte. [For 02 Nos. Tube well]. | 1125/BWD | 14/03/2024 | 122 | KAR CONSTRUCTION AND ORDER SUPPLIERS | 58.25 | 7.54 | 20.94 | 100
5040 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Supply of various D.I. Mechanical joints & specials for Aug. of BHATAR & Aug. of BALGONA Piped W/S. Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, PHE. Dte. [Part-B]. | 2828/BWD | 19/07/2024 | 216 | KEJRIWAL CASTINGS LIMITED | 4.82 | 0 | 0 | 100
5041 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Supply of various D.I. Mechanical joints & specials for Aug. of BHATAR & Aug. of BALGONA Piped W/S. Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, PHE. Dte. [Part-C]. | 2832/BWD | 19/07/2024 | 225 | JINDAL SAW LTD. | 4.63 | 0 | 0 | 100
5042 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of BALGANA Piped Water Supply Scheme at Bhatar Block , SM/07871 | Retrofitting | Supply of various D.I. Mechanical joints & specials for Aug. of BHATAR & Aug. of BALGONA Piped W/S. Scheme within Durgapur (Burdwan North) Sub-Division under Burdwan Division, PHE. Dte. [Part-A]. | 2840/BWD | 19/07/2024 | 215 | ELECTROSTEEL CASTING LIMITED | 4.95 | 0 | 0 | 100
5043 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block , SM/07824 | Retrofitting | Extension of Pipeline with providing Functional Household Tap Connection (FHTC) at Raibandh, Raykona & Kankora adibasipara of DEBSALA and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-C] | 75/DSD | 11/02/2022 | 30 | BHARAT CONSTRUCTION | 4.33 | 4.3 | 100 | 1
5044 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block , SM/07824 | Retrofitting | Extension of Pipeline with providing Functional Household Tap Connection (FHTC) at Debsala Village,Kankora & Pathuria Adibasipara of DEBSALA and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte. [Gr.-D] | 76/DSD | 11/02/2022 | 30 | D.M. ENTERPRISE | 4.45 | 4.29 | 100 | 1
5045 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block , SM/07824 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Ausgram-II Block under Burdwan Division, PHE. Dte. | 940/BWD | 17/02/2022 | 30 | NANDY UDYOG | 11.82 | 0 | 0 | 0
5046 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block , SM/07824 | Retrofitting | Providing functional household tap connection (FHTC) from existing distribution system within command area of DEBSHALA piped water supply scheme at Bagbati (02 Nos. habitation), Kakra, Satla (02 Nos. habitation), Gobindapur (03 Nos Habitation), Debshala (02 Nos. Habitation Part), Kankra (Part) & Paduma (02 Nos. habitation Part) village, Ausgram-II Block under Burdwan Division, PHE Dte. | 4998/BWD | 10/12/2020 | 90 | SAI TUBE CO. | 59.61 | 40.73 | 100 | 1
5047 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block , SM/07824 | Retrofitting | Restoration of village and drains at Kakra village for DEBSHALA piped water supply scheme, Block-Ausgram-II under Burdwan Division, PHE Dte. [Gr.-L] | 669/DSD | 25/11/2021 | 15 | SAI TUBE CO. | 3.97 | 0 | 0 | 1
5048 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block , SM/07824 | Retrofitting | Restoration of village road and drains at part of RAYKONA & KAKRA for Debshala piped water supply scheme, Block-Ausgram-II under Burdwan Division, PHE Dte. [Gr.-M] | 668/DSD | 25/11/2021 | 15 | SAI TUBE CO. | 3.91 | 0 | 0 | 1
5049 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block , SM/07824 | Retrofitting | Relaying of pipe line damaged by construction of road with drain at Kankora and installation of Valves to regulate water supply at Bilashpur & Gobindapur of DEBSALA and its adjoining mouza's Piped W/S Scheme at Ausgram-II Block within Durgapur Sub Division under Burdwan Division, P.H.E. Dte.[SL-E] | 166/DSD | 16/03/2022 | 30 | BHARAT CONSTRUCTION | 2.53 | 2.52 | 100 | 1
5050 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block , SM/07824 | Retrofitting | Extension of pipeline of DEBSHALA and its adjoining mouzas piped water supply scheme at Ausgram-II Block within Durgapur Sub-Division under Burdwan Division, PHE Dte. | 1568/BWD | 22/02/2021 | 45 | BHARAT CONSTRUCTION | 41.01 | 81.32 | 200 | 0
5051 | PURBA BARDHAMAN | Durgapur W/S Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Debshala Piped Water Supply Scheme at Ausgram-II Block , SM/07824 | Retrofitting | Acceptance cum Formal Work Order for Big Dia Tubewell Surging by using suitable air compressor at PH-1 & PH-2 of Debshala PWSS Scheme under Durgapur W/S Division, PHE Dte. | 1212/DWSD | 23/08/2024 | 10 | GHOSH & ROY ENTERPRISE | 0.66 | 0.66 | 100 | 100
5052 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KANSHRA Piped Water Supply Scheme at Bishnubati (Harekrishnapur Habitation), Jotsubal (Jotsubalpaharpur & Sagar Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. (Agreement no. 594/BWD of 2020-2021) | 619/BWD | 25/01/2021 | 60 | ROY CONSTRUCTION | 20.42 | 0 | 0 | 1
5053 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KANSHRA Piped Water Supply Scheme at Jotkrishtai (Jotkestai Habitation), Kalna (Jotkalna Habitation) & Kanshra (Bhabanipur Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte.(Agreement no. 571/BWD of 2020-2021) | 441/BWD | 19/01/2021 | 60 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 19.48 | 0 | 0 | 1
5054 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Laying of UPVC Pipeline for providing FHTC at Kanshra Mouza (Habitation) under KANSHRA Piped Water Supply Scheme, Jamalpur Development Block under Burdwan Division, PHE Dte. | 2018/BWD | 28/04/2023 | 30 | TARAMA AGENCY | 12.58 | 12.56 | 99.82 | 0
5055 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KANSHRA Piped Water Supply Scheme at Kalna (Kalnagram & Surakalna Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte. [Agreement No. 639/BWD OF 2020-2021] | 989/BWD | 04/02/2021 | 60 | IJABUL SEKH | 22.09 | 21.45 | 100 | 1
5056 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of KANSHRA Piped Water Supply Scheme at Kanshra (Jorbandh & Kanshra Habitation) Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte.[Agreement No. 625/BWD OF 2020-2021] | 957/BWD | 03/02/2021 | 60 | DEBASHISH ENTERPRISE | 21.87 | 21.76 | 100 | 1
5057 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Laying of uPVC pipe for providing FHTC at Jorbandh habitation of Kanshra Mouza within Kanshra Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E DTE. [Group: ¿C¿] | 1898/AE/HQ | 16/11/2021 | 30 | M/S ANAND CONSTRUCTION | 4.62 | 4.62 | 100 | 1
5058 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Kalna village within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. [Group : C] | 68/AE/HQ | 11/02/2022 | 30 | MAA BHABANI CONSTRUCTION | 4.81 | 4.81 | 100 | 1
5059 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Extension of pipeline for providing functional house hold tap connection at Jotsubal village within Kanshra water supply scheme under Burdwan Division, PHE Dte. [Gr.-A] | 1256/AE/HQ | 15/02/2021 | 30 | ROY CONSTRUCTION | 4.84 | 0 | 0 | 1
5060 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Laying of uPVC pipe for providing FHTC at Kanshra Village within KANSHRA Piped Water Supply Scheme, Jamalpur Block under Burdwan Division P.H.E Dte. [Group : A] | 199/AE/HQ | 06/04/2022 | 30 | DEBASHISH ENTERPRISE | 4.84 | 4.84 | 100 | 1
5061 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Laying of 90 mm dia UPVC pipe for providing FHTC at Surekalna habitation of Kalna Mouza within Kanshra piped water supply scheme, at Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-D] | 1899/AE/HQ | 16/11/2021 | 30 | SWASTIK ENTERPRISE | 4.75 | 4.58 | 100 | 1
5062 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Laying of 75 mm and 50 mm dia UPVC pipe for providing FHTC at Kalnagram habitation of Kalna Mouza within Kanshra piped water supply scheme within Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-C] | 1857/AE/HQ | 05/10/2021 | 30 | SANJAY SK | 3.5 | 2.73 | 100 | 1
5063 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Paharpur & Chikonhati village within the command area of KANSHRA Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, PHE Dte. GROUP : B | 425/AE/HQ | 03/08/2022 | 30 | OM ENTERPRISE | 4.1 | 4.1 | 100 | 1
5064 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Interconnection between inlet & delivery pipe with main distribution pipeline within command area of KANSHRA Piped W/S. Scheme, Jamalpur Block under Burdwan Division, PHE. Dte. | 214/AE/HQ | 31/03/2023 | 30 | OM ENTERPRISE | 0.87 | 0.83 | 100 | 100
5065 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Extension of pipeline for KANSHRA Piped Water Supply Scheme at Badalpur Habitation in Jamalpur Block under Burdwan Division, PHE Dte. | 216/AE/HQ | 31/03/2023 | 30 | DEBASHISH ENTERPRISE | 0.95 | 0.95 | 100 | 100
5066 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Construction of sluice valve chamber & supply of sluice valve for extension of pipeline for KANSHRA Piped W/S. Scheme, Jamalpur Block under Burdwan Division, PHE. Dte. | 217/AE/HQ | 31/03/2023 | 30 | DEBASHISH ENTERPRISE | 0.92 | 0.92 | 100 | 100
5067 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Extension of pipeline for KANSHRA Piped Water Supply Scheme at Natungram Habitation in Jamalpur Block under Burdwan Division, PHE Dte. | 215/AE/HQ | 31/03/2023 | 30 | DEBASHISH ENTERPRISE | 0.95 | 0.95 | 100 | 100
5068 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Kanshra Piped Water Supply Scheme at Jamalpur Block , SM/07816 | Retrofitting | Extension of pipeline for KANSHRA Piped Water Supply Scheme at Badalpur & Natungram (Habitation) in Jamalpur Development Block for providing water tap connection (FHTC) under Burdwan Division, PHE Dte. | 421/AE/HQ | 02/08/2023 | 30 | DEBASHISH ENTERPRISE | 0.95 | 0.95 | 100 | 100
5069 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District , SM/09410 | Augmentation | Sinking of additional 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SINHARI Piped Water Supply Scheme, Block - Purbasthali - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 2425/BWD | 11/05/2022 | 30 | M/S SYCHROTECH INDUSTRY | 9.01 | 0 | 0 | 0
5070 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District , SM/09410 | Augmentation | Preparation of DPR for augmentation of Sinhari W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-C) | 215/KSD | 24/02/2022 | 21 | LEMNISCATE | 2.92 | 2.86 | 100 | 1
5071 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District , SM/09410 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
5072 | PURBA BARDHAMAN | Central Mechanical | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District , SM/09410 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1,2 &3 at Augumentation of Sinhari Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2574/CMD | 06/06/2023 | 30 | P.K. ENGINEERING | 33.08 | 0 | 0 | 0
5073 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District , SM/09410 | Augmentation | Material Requisition To Resource Division | 539/BWD | 27/01/2022 | 0 | Resource Division | 16.89 | 0 | 0 | 0
5074 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District , SM/09410 | Augmentation | Material Requisition To Resource Division | 1321/BWD | 08/03/2022 | 0 | Resource Division | 44.3 | 0 | 0 | 0
5075 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District , SM/09410 | Augmentation | Material Requisition To Resource Division | 1536/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
5076 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District , SM/09410 | Augmentation | Material Requisition To Resource Division | 1241/BWD | 07/03/2022 | 0 | Resource Division | 4.19 | 0 | 0 | 0
5077 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District , SM/09410 | Augmentation | Augmentation of SINHARI Piped Water Supply Scheme with LDS, FHTC, Rising Main, Construction of 350 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil investigation including construction of switch room (3.60mx3.0m) for new TW site under Purbasthali II Block, District - Purba Bardhaman. | 1940/BWD | 11/04/2022 | 365 | CONCORD ENGINEERING | 441.1 | 292.72 | 99.03 | 60
5078 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SINHARI PWSS for providing functional household tap conncetion FHTC in Purbasthali-II block under Burdwan Division in Purba Bardhaman District , SM/09410 | Augmentation | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | 2296/BWD | 20/06/2024 | 616 | M/S DATTA ENTERPRISE | 579.85 | 40.37 | 95.82 | 2
5079 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08702 | Retrofitting | Laying of 100 mm dia D.I Pipe for Road widening from 4 lane to 6 lane of NH2 at chainage 596+286 & 596+086 & 596+ 486 at Amra Water supply within Jamalpur Block,under Burdwan Division,PHE Dte". Group : A. | 982/BSD | 16/06/2022 | 30 | DEY NIRMAN | 2.89 | 0 | 0 | 0
5080 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08702 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Amra Piped Water Supply Scheme at Amra (2 Nos Habitation Part) & Dogachia Village (Mouza), Jamalpur Block under Burdwan Division, PHE Dte._3rd CALL. | 3138/BWD | 03/06/2021 | 45 | D.M. ENTERPRISE | 57.42 | 28.82 | 100 | 1
5081 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08702 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of AMRA Piped Water Supply Scheme (Vill-Dogechia, Habitation- Dogechia ) at Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte.Gr.A. | 57/BSD | 13/01/2022 | 30 | DEY NIRMAN | 4.81 | 0 | 0 | 1
5082 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08702 | Retrofitting | Extension of pipeline at AMRA water supply scheme at different villages (Tengaberia, Badpur & Kolupukur) FHTC of Jamalpur Block under Burdwan Division, PHE Dte.[Gr.-F] | 1374/BSD | 05/10/2021 | 30 | D.M. ENTERPRISE | 4.74 | 3.81 | 100 | 1
5083 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08702 | Retrofitting | Construction of Boundary wall at 3rd Tube well site of Dogachia Mouza of Amra water supply scheme under Jamalpur block under Burdwan Division, PHE Dte. [Length-59 Mtr][Gr.-F] | 1028/BSD | 05/08/2021 | 45 | MUKHERJEE ENTERPRISE | 4.45 | 0 | 0 | 1
5084 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08702 | Retrofitting | Construction of concrete road and rest portion of boundary wall at Head works site of AMRA Piped Water Supply Scheme in Jamalpur Block under Burdwan Division, PHE Dte. (Length - 122 Mtr., 45 Nos Column). | 3100/BWD | 14/07/2022 | 30 | CHAUDHURI ENTERPRISE | 7.68 | 7.74 | 100 | 0
5085 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08702 | Retrofitting | Repairing and replace of damaged UPVC Pipeline with installation and construction of valve chamber for control of water flow within command area of AMRA Piped W/S Scheme at Dogachia habitation,Jamalpur Development Block under Burdwan Division,PHE Dte. | 429/BSD | 15/03/2023 | 30 | DEY NIRMAN | 0.89 | 0.87 | 100 | 100
5086 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Dogachia mouza within the command area of Amra piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08702 | Retrofitting | Providing FHTC for Dogachia Mouza [(Habitation (Village)] for AMRA piped W/S Scheme, Jamalpur Dev. Block under Burdwan Division, PHE Dte. | 2019/BWD | 28/04/2023 | 30 | DEY NIRMAN | 20.61 | 18 | 100 | 100
5087 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09569 | Augmentation | Route Survey and preparation of DPR for MAJHIGRAM-SINGHOT PWSS under Mongalkote Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-05] | 56/KTS | 25/01/2022 | 21 | RADIANT | 2.63 | 2.63 | 100 | 1
5088 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09569 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
5089 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09569 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Head Work Site to departmental drawing (Size 3.60 mtr x 3.00 mtr room) for MAJHIGRAM SINGOT water supply schemes under Katwa Sub-Division within Burdwan Division, PHE Dte. [ G.L to P.L Height= 1.20 Mtr] (Sl No-1) | 798/KTS | 10/12/2021 | 60 | BABUL SK | 3.24 | 2.91 | 100 | 1
5090 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09569 | Augmentation | Construction of sanitary Latrine and water supply arrangement at Head Work Site of Majhigram Singot piped water supply schemes under Mongalkote Block under Katwa Sub-Division under Burdwan Division, PHE Dte.[Sl No-01] | 159/KTS | 24/02/2022 | 21 | BABUL SK | 1.76 | 1.72 | 100 | 1
5091 | PURBA BARDHAMAN | Central Mechanical | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09569 | Augmentation | Supply , delivery & Installation of Submersible Pumping Machinery , Voltage stabiliser , Chlorinator and Internal House wiring for Tube well No. 3 of Majhigram Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. [ Block- Mongalkoat ] | 1173/CMD | 27/06/2022 | 30 | MITRA ENTERPRISE | 9.22 | 9.03 | 100 | 1
5092 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09569 | Augmentation | Material Requisition To Resource Division | 1323/BWD | 08/03/2022 | 0 | Resource Division | 16 | 0 | 0 | 0
5093 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09569 | Augmentation | Material Requisition To Resource Division | 545/BWD | 27/01/2022 | 0 | Resource Division | 16.58 | 0 | 0 | 0
5094 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09569 | Augmentation | Material Requisition To Resource Division | 1553/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
5095 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09569 | Augmentation | Material Requisition To Resource Division | 1376/BWD | 09/03/2022 | 0 | Resource Division | 3.83 | 0 | 0 | 0
5096 | PURBA BARDHAMAN | Burdwan Division | Augmentation of ground water based MAJHIGRAM SINGOT PWSS to accommodate FHTC in Mangolkote block under Katwa Sub Division of Burdwan Division in Purba Bardhaman District , SM/09569 | Augmentation | Material Requisition To Resource Division | 3275/BWD | 29/07/2022 | 0 | Resource Division | 34.57 | 0 | 0 | 0
5097 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08700 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Sultanpur Piped Water Supply Scheme at Halbele, Hridaypur, Isabpur, Nowapara & Uplati Village (Mouza), Kalna ¿ I Block under Burdwan Division, PHE Dte.(Agreement No. 56/2020-2021 OF SE/CC/PHE. DTE.) | 4901/BWD | 07/12/2020 | 90 | MAJILA ENTERPRISE | 94.67 | 6.47 | 100 | 1
5098 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08700 | Retrofitting | Protection work of distribution system (200 mm dia) of 35 Mtr length near the head work site (Right Side) of Sultanpur & its adjoining mouzas water supply scheme by UC Bullah including Drum Sheet within Kalna Sub-Division under Burdwan Division, PHE Dte.[Gr.-E] | 20/KSD | 07/01/2021 | 30 | DEBASHISH ENTERPRISE | 0.75 | 0 | 0 | 1
5099 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08700 | Retrofitting | Extension of different dia UPVC pipeline at different section of village Upalati, Hridaypur, Gopalpur, Sultanpur & Hatbele to cover up the uncovered habitation of Sultanpur PWSS within Kalna Sub-Division under Burdwan Division, PHE Dte. | 6122/BWD | 26/10/2021 | 30 | MAJILA ENTERPRISE | 14.34 | 14.29 | 100 | 1
5100 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08700 | Retrofitting | Providing FHTC in each household from dist. System within Scheme jurisdiction in Hridaypur, Upalati, Belerhat, Gopalpur, Sultanpur, Isabpur & Naopara Village of SULTANPUR W/S. Scheme under Burdwan Division, PHE Dte. | 1357/BWD | 09/03/2022 | 30 | TAPAS KUMAR ROY | 16.69 | 16.45 | 100 | 1
5101 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08700 | Retrofitting | Hire & fuel charges of vehicle (Car No.-WB-04G-7127) for the office of the Assistant Engineer, Kalna Sub-Division, PHE Dte. for the month of December22 to February'23. | 30/JJM | 19/04/2023 | 0 | PARTHA PRATIM ACHARYA | 1.19 | 0 | 0 | 0
5102 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Hatbela and Hridaypur mouza within the command area of Sultanpur piped Water Supply Scheme at Kalna-I Block under Burdwan Division, P.H.E. DTE. (Pt.-B) , SM/08700 | Retrofitting | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 11 Nos. Piped W/S. Schemes under Kalna I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3015/BWD | 05/08/2024 | 60 | HORIZEN | 29.6 | 11.1 | 100 | 10
5103 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Augmentation of SAJIARA Piped Water Supply Scheme with LDS, Rising Main, Switch Room (with & without water supply & sanitary arrangements), Construction 300 Cum capacity OHR with 20.0 Mtr. Staging height inclusive of soil test & Construction of Boundary wall under Kalna Sub-Division, Block - Purbasthali - II, Dist. - Purba Bardhaman under Burdwan Division, PHE. Dte. | 645/BWD | 01/02/2022 | 365 | UNICON INDIA | 318.07 | 39.69 | 12.48 | 0
5104 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Preparation of DPR for augmentation of Sajiara W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-D) | 184/KSD | 21/02/2022 | 21 | M/S R. DUTTA & CO. | 2.88 | 2.88 | 100 | 1
5105 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
5106 | PURBA BARDHAMAN | Central Mechanical | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of Sajiara Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2567/CMD | 06/06/2023 | 30 | AMUSAR IMPEX PVT. LTD. | 21.95 | 0 | 0 | 0
5107 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Work Order for "Construction of Pump house cum chlorine room without sanitary (Size 3.60 mtr x 3.00 mtr room) at 2nd Tube well site for augmentation of Sajiara Water Supply Scheme for providing Functional Household Tap Connection (FHTC) within Kalna Sub-Division under Burdwan Division, PHE Dte.^". | 1307/KSD | 23/08/2023 | 60 | BUILD-TECH | 3.02 | 0 | 0 | 0
5108 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Construction of Pump House cum chlorine room with sanitary and water supply arrangement at Head Work Site for augmentation of SAJIARA according to departmental drawing No-PHE/BD/P.H/DRG-01/DEC-2017 (Size 3.30 mtr x 3.60 mtr room with 1.2 Mtr. wide verandah) to provide house connection within Kalna Sub-Division under Burdwan Division, PHE Dte._2ND CALL | 5713/BWD | 29/12/2023 | 60 | DEL DELTA CONSTRUCTION | 5.2 | 0 | 0 | 0
5109 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Material Requisition To Resource Division | 546/BWD | 27/01/2022 | 0 | Resource Division | 15.25 | 0 | 0 | 0
5110 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Material Requisition To Resource Division | 1244/BWD | 07/03/2022 | 0 | Resource Division | 2.64 | 0 | 0 | 0
5111 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Material Requisition To Resource Division | 1339/BWD | 08/03/2022 | 0 | Resource Division | 53.75 | 0 | 0 | 0
5112 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Material Requisition To Resource Division | 1565/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
5113 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Material Requisition To Resource Division | 3274/BWD | 29/07/2022 | 0 | Resource Division | 34.57 | 0 | 0 | 0
5114 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Laying of Rising Main for Augmentation of SAJIARA Piped Water Supply Scheme to provide house connection within Kalna Sub-Division under Burdwan Division, PHE Dte. | 3766/BWD | 29/08/2023 | 30 | CHOWDHURY CONSTRUCTION | 8.19 | 0 | 0 | 2
5115 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Work Order for "Construction of Pump house cum chlorine room without sanitary (Size 3.60 mtr x 3.00 mtr room) at 2nd Tube well site for augmentation of Sajiara Water Supply Scheme for providing Functional Household Tap Connection (FHTC) within Kalna Sub-Division under Burdwan Division, PHE Dte.^". | 1307/KSD | 23/08/2023 | 60 | BUILD-TECH | 3.02 | 0 | 0 | 0
5116 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) at 1st & 2nd Tubewell site for SAJIARA Piped Water Supply Scheme, Block - Purbasthali - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [2 Nos. GTW]. | 1960/BWD | 12/04/2022 | 45 | ACME CONSTRUCTION | 14.81 | 13.62 | 100 | 100
5117 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Laying distribution system for augmentation of SAJIARA W/S Scheme to provide house connection within Kalna Sub-Division under Burdwan Division, PHE Dte. | 3554/BWD | 11/08/2023 | 45 | SK RAJU | 42.39 | 32.46 | 100 | 40
5118 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Construction of boundary wall of SAJIARA Piped water supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Length -150 Mtr, No of Columns-43 Nos. Centre to Centre- 3.5 Mtr.) With Double Tie Beam. | 4172/BWD | 21/09/2023 | 30 | HAIDER ALI MONDAL | 14.53 | 3.84 | 20.94 | 80
5119 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Quotation from WBSEDCL for Load Enhancement charges of Sajiara water supply scheme of PH-1. under Burdwan Division, PHE Dte. | 1402/JJM | 29/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.32 | 0 | 0 | 0
5120 | PURBA BARDHAMAN | Burdwan Division | Augmentation of Sajiara PWSS for providing FHTC under Baurdwan Division. , SM/09716 | Augmentation | Different types of works involve in connection with Augmentation of SAJIARA (SM/09716), NAMA BHANDARTIKURI (SM/14917) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | 3010/BWD | 02/08/2024 | 240 | PRATIMA CONSTRUCTION | 79.16 | 0 | 0 | 2
5121 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10056 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
5122 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10056 | Augmentation | Route Survey & Preparation of DPR for Sasinara (Zone-II) & (Zone-III) W/S Scheme under Burdwan-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.2. | 177/BSD | 31/01/2022 | 30 | RADIANT | 3.76 | 1.88 | 100 | 1
5123 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10056 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SASINARA Z-II W/S Scheme at Kalsi Mouza, RASULPUR W/S Scheme at 4th TW site & ALIPUR W/S Scheme at 4th TW site under Memari-I Block under within Burdwan Sub-Division, PHE Dte. [For 3 Nos. Tube well]. | 2455/BWD | 31/05/2023 | 60 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 39.76 | 13.4 | 100 | 100
5124 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10056 | Augmentation | Material Requisition To Resource Division | 1332/BWD | 08/03/2022 | 0 | Resource Division | 108.97 | 0 | 0 | 0
5125 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10056 | Augmentation | Material Requisition To Resource Division | 1546/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
5126 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10056 | Augmentation | Material Requisition To Resource Division | 1387/BWD | 09/03/2022 | 0 | Resource Division | 4.83 | 0 | 0 | 0
5127 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10056 | Augmentation | Material Requisition To Resource Division | 4851/BWD | 20/10/2022 | 0 | Resource Division | 10.47 | 0 | 0 | 0
5128 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10056 | Augmentation | Quotation for WBSEDCL for New Service connection of Sasinara Z-II TW-3 water supply scheme. | 1149/JJM | 29/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 6.03 | 0 | 0 | 0
5129 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10056 | Augmentation | Providing Balance Functional Household Tap Connection (850nos FHTC) from existing distribution system within the command area of SASINARA ZONE-II Piped Water Supply Scheme at (Sasinara, Kalsi, Debipur, Amadpur, Maheshpur, Mobarakpur) Mouza, Construction of boundary wall at head work site, 2nd T/W & 3rd T/W site under MEMARI-I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 3628/BWD | 21/08/2023 | 60 | A R TRADERS | 69.4 | 69.37 | 100 | 99
5130 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10056 | Augmentation | Construction of switch rooms & Rising main at different TW site for SASINARA (Zone-II) Piped Water Supply Scheme under Memari - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | 4165/BWD | 20/09/2023 | 60 | PAL CONSTRUCTION | 9.12 | 9.11 | 100 | 100
5131 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED SASINARA ZONE II PWSS TO ACCOMMODATE FHTC IN MEMARI-I BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10056 | Augmentation | Augmentation of SASINARA ZONE-II Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 350 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under MEMARI- I Block, District:- Purba-Burdwan. | 2929/BWD | 28/06/2022 | 885 | ASHOK KUMAR GHOSH | 481.08 | 479.17 | 99.57 | 100
5132 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10061 | Augmentation | Route Survey & Preparation of DPR for Satgachia (Zone-I) & (Zone-II) W/S Scheme under Memari-II Block under Burdwan Sub-Division under Burdwan Division PHE Dte. Sl No.4. | 179/BSD | 31/01/2022 | 30 | RADIANT | 4.21 | 2.1 | 100 | 1
5133 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10061 | Augmentation | Restoration work of Debipur-Bulbulitala Road from 15.00 km to 17.10 km (in stretches) damage due to laying of underground water pipeline by PHE with box cutting and jhama with moorum consolidation under Kalna Highway Sub-Division of Burdwan South Highway Division, P.W. Roads Dte. during the Year 2023-2024. | 1079/JJM | 20/12/2023 | 0 | EXECUTIVE ENGINEER BURDWAN SOUTH HIGHWAY DIVISION P.W. (ROADS) DTE. | 5.51 | 0 | 0 | 0
5134 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10061 | Augmentation | Construction of switch rooms & Rising main at different TW site for SATGACHIA (Zone-I) Piped Water Supply Scheme under Memari - II Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | 3632/BWD | 21/08/2023 | 60 | ROY ASSOCIATE | 9.08 | 7.65 | 100 | 100
5135 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10061 | Augmentation | Different Types of work involved in connection with different Augmentation & Retrofitting Schemes (06 Nos.) Piped Water Supply Scheme under Memari II Block within Burdwan Sub-Division under Burdwan Division, PHE Dte. | 848/BWD | 05/03/2025 | 120 | PROJECT INDIA | 394.29 | 0 | 0 | 0
5136 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10061 | Augmentation | Replacement of Tube-well & Rising main at HEAD TW site for Aug. of PARHATI, SRIDHARPUR, SATGACHIA ZONE-I, SATGACHIA ZONE-II, Piped Water Supply Scheme within MEMARI-II Block under Burdwan Divn., PHE. Dte. District:- Purba-Bardhaman. | 24/BWD | 03/01/2024 | 637 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 54.2 | 14.26 | 89.65 | 90
5137 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED SATGACHIA ZONE I PWSS TO ACCOMMODATE FHTC IN MEMARI-II BLOCK UNDER BURDWAN SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10061 | Augmentation | Repairing damaged Pipeline & concrete road by Cement concrete (mix 1:1.5:3) and drainage system, Sluice valve chamber for FHTC work for SATGACHIA ZONE-I, SATGACHIA ZONE-II, SRIDHARPUR, PARHATI, KUCHUT, NOAHATI, MONDALGRAM PWSS and its adjoining mouzas within MEMARI-II BLOCK under Burdwan Division, PHE Dte. | 2715/BWD | 11/07/2024 | 205 | A.R. TRADERS | 74.28 | 4.83 | 97.03 | 100
5138 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Preparation of DPR for augmentation of Hatkalna W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-C) | 269/KSD | 15/03/2022 | 21 | ROY CHOWDHURY ASSOCIATES | 3.23 | 3.22 | 100 | 1
5139 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Sinking of Tube well 250 x 200 mm dia Tube well 150 mtr depth by D.R. Rig method using UPVC pipe (CD) and fibre glass strainer for HATKALNA piped water supply scheme (2nd tube well site), Block-Kalna-I, Dist.-Purba Bardhaman, under Burdwan Division, PHE Dte. | 1492/BWD | 18/02/2021 | 30 | C.M. ENTERPRISE | 8.68 | 8.06 | 100 | 1
5140 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 2nd TW Site of Aug. HATKALNA & its adjoining mouzas Piped Water Supply Scheme, Block ¿ Kalna ¿ I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 605/BWD | 17/02/2023 | 30 | AUXILIARY TUBE WELL DRILLERS | 8.64 | 8.44 | 97.69 | 1
5141 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Material Requisition To Resource Division | 3279/BWD | 29/07/2022 | 0 | Resource Division | 52.8 | 0 | 0 | 0
5142 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 3RD TW Site of Aug. HATKALNA & its adjoining mouzas Piped Water Supply Scheme, Block ¿ Kalna ¿ I, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 01 No. Tube well]. | 2711/BWD | 08/06/2023 | 30 | AUXILIARY TUBE WELL DRILLERS | 9.89 | 9.34 | 100 | 90
5143 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Additional work viz. Carriage of different type of departmental pipes and Interconnection of Tube well and existing pipe line and Restoration of existing concrete road and laying of pipeline of HATKALNA Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 003/BWD | 02/01/2024 | 120 | S.P. CONSTRUCTION | 162.05 | 161.21 | 100 | 100
5144 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Supply & Installation of Chlorination System for Tube well No.-1 at Hat Kalna Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 464/CMSD | 21/03/2024 | 12 | JOYGURU ENTERPRISE | 0.96 | 0.96 | 100 | 100
5145 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 11 Nos. Piped W/S. Schemes under Kalna I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3015/BWD | 05/08/2024 | 60 | HORIZEN | 29.6 | 11.1 | 100 | 10
5146 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Supply & Installation of Chlorination System for Tube well No.-2 at Hat Kalna Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 377/CMSD | 29/02/2024 | 15 | SUDIKSHA CONSTRUCTION | 0.96 | 0.96 | 100 | 100
5147 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | QUOTATION FOR NEW SERVICE CONNECTION AT AUGMENTATION OF HAT KALNA PWSS TW 3, BLOCK KALNA-1 | BP-2024-25-285 | 10/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.36 | 0 | 0 | 0
5148 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Augmentation of Hatkalna Piped Water Supply Scheme with LDS, FHTC, Construction of 1000 cum capacity OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch-rooms & boundary walls at different TW site & repairing of switch rooms under Kalna-I Block, District:- Purba-Bardhaman. | 5019/BWD | 10/11/2022 | 1057 | S.P. CONSTRUCTION | 976.48 | 858.64 | 87.93 | 50
5149 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring of Tube Well No- 01,02 03 & 04 at Augmentation Hatkalna [Block -Kalna-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1080/CMD | 03/03/2023 | 820 | P.K. ENGINEERING | 41.64 | 0 | 0 | 35
5150 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Construction of switch rooms & Rising main at different TW site for Hatkalna Piped Water Supply Scheme under Kalna - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | 4736/BWD | 03/11/2023 | 422 | BISWAS ENTERPRISE | 8.38 | 0 | 0 | 100
5151 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Construction of 1.5 Mtr. height boundary wall along with 750 mm. height 3 layer barbed wire and other ancillary works at Head Work Site in connection with Augmentation of Hatkalna PWSS (SM/10337) Piped Water Supply Scheme within Kalna Sub Division under Burdwan Divn., PHE. Dte. | 4067/BWD | 21/11/2024 | 30 | UJJWAL MUKHERJEE | 20.99 | 0 | 0 | 100
5152 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Work Order for "Construction of Toilet (1.8 m x 1.8 m) with saitary arrangement in connection with Augmentation of Hatkalna pwss (SM/10337) under Kalna sub division under Burdwan Division." | 1766/KSD | 20/11/2024 | 30 | S.B.S. ENTERPRISE | 4.91 | 0 | 0 | 100
5153 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Work Order for "Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire in connection with Augmentation of Hatkalna PWSS ( SM/10337) Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | 1767/KSD | 20/11/2024 | 30 | S.B.S. ENTERPRISE | 3.35 | 2.89 | 100 | 2
5154 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Renovation of Pump House in connection with Augmentation of Hatkalna piped Water supply (SM/10337) Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte. (2 units) | 3747/BWD | 29/10/2024 | 30 | S.B.S. ENTERPRISE | 9.7 | 8.76 | 100 | 100
5155 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED HATKALNA PWSS TO ACCOMMODATE FHTC IN KALNA I BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10337 | Augmentation | Work Order for "Constrcution of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire around Other than head work site for Hatkalna Piped Water Supply Scheme (SM/10337) within Kalna Sub-Division under Burdwan Division, PHE Dte." | 2188/KSD | 15/03/2024 | 130 | BISWAS ENTERPRISE | 4.59 | 0 | 0 | 100
5156 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Preparation of DPR for augmentation of Baidyapur W/S Scheme (Zone-I & II) within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-A) | 203/KSD | 23/02/2022 | 21 | INDRANIL DUTTA & ASSOCIATES | 4.19 | 4.17 | 100 | 1
5157 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CM) and UPVC Medium Well Screen (RMS) for 2nd TW Site of Aug. of BAIDYAPUR (Z-II) & its adjoining mouzas Piped Water Supply Scheme, Block ? Kalna ? II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte._2ND CALL. | 5274/BWD | 30/11/2022 | 30 | SUSUNIA GP CO. OPERATIVE LABOUR CONTRACT AND CONSTRUCTION SOCIETY LTD. | 7.33 | 6.97 | 100 | 0
5158 | PURBA BARDHAMAN | Central Mechanical | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Augmentation of BAIDYAPUR PWSS under CMD, PHE Dte., Dist.- Purba-Bardhaman | 1036/CMD | 02/03/2023 | 30 | BEHERA ENTERPRISE | 11.46 | 11.13 | 100 | 80
5159 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Sinking of 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for Aug. of BAIDYAPUR (Z-I) PWSS, Block - Kalna - II and NANDAI PWSS, Block - Kalna - I Piped Water Supply Scheme, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. [For 02 Nos. Tube well]. | 2424/BWD | 30/05/2023 | 45 | KOUSIK MALLICK | 19.84 | 9.14 | 100 | 100
5160 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Material Requisition To Resource Division | 3272/BWD | 29/07/2022 | 0 | Resource Division | 31.47 | 0 | 0 | 0
5161 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | New service connection quotation from WBSEDCL of Augmentation of Baidyapur Z-II (T.W.-3) under Burdwan Division, PHE Dte. | 194/JJM | 31/05/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.56 | 0 | 0 | 0
5162 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Work Order for "Restoration in pipe connection of Augmentation scheme of Baidyapur Zone-II Piped Water Supply Scheme under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-3) | 2062/KSD | 23/02/2024 | 20 | YOUNG ENGINEERS CO.-OPERATIVE SOCIETY LTD. | 1.37 | 0 | 0 | 0
5163 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Construction of switch rooms & Rising main at different TW site for Baidyapur (Zone-I) Piped Water Supply Scheme under Kalna - II Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | 3626/BWD | 21/08/2023 | 60 | M/S UNIQUE | 9.11 | 6.67 | 100 | 65
5164 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Work Order for "Renovation of Pump House for Augmentation 1 of Baidyapur (Zone-II) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte." | 1953/KSD | 05/02/2024 | 25 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.59 | 0.54 | 100 | 100
5165 | PURBA BARDHAMAN | Central Mechanical | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Supply & Installation of Chlorination System for Tube well No.-1 at Baidyapur (zone-1) Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 461/CMSD | 21/03/2024 | 12 | SUDIKSHA CONSTRUCTION | 0.96 | 0.96 | 100 | 100
5166 | PURBA BARDHAMAN | Central Mechanical | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Supply and delivery of different Electro-mechanical items for Baidyapur zone-1 Water Supply Scheme PH 1 replacement T.W (part-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | 64/CMSD | 11/01/2024 | 12 | SUBRATA BHADRA | 0.96 | 0.94 | 100 | 100
5167 | PURBA BARDHAMAN | Central Mechanical | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | House wiring, double earthing and allied works for Baidyapur zone-1 Water Supply Scheme PH 1 replacement T.W (part-2) under CMD, PHE Dte., Dist.- Purba-Bardhaman | 80/CMSD | 15/01/2024 | 12 | SUBRATA BHADRA | 0.97 | 0.97 | 100 | 100
5168 | PURBA BARDHAMAN | Central Mechanical | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Quotation for new service connection at Baidyapur Zone-2 PWSS PH-3 | BP-2024-25-200 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.14 | 0 | 0 | 0
5169 | PURBA BARDHAMAN | Central Mechanical | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Quotation for load enhancement at Baidyapur PH2 | BP-2024-25-302 | 24/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.35 | 0 | 0 | 0
5170 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Augmentation of Baidyapur (Zone-I & II) Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 200 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation including repairing of OHR, boundary walls & switch rooms under Kalna-II Block, District:- Purba-Burdwan. | 2859/BWD | 22/06/2022 | 1229 | SUPRITI ENTERPRISE | 734.07 | 712.21 | 97.02 | 60
5171 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Additional pipe laying of HDPE pipeline & providing FHTC work at Sanpukur, Mirhat village under BAIDYAPUR Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 5308/BWD | 01/12/2023 | 166 | GENUINE ENGINEERING CO-OP. SOCIETY LTD. | 35.01 | 26.03 | 74.37 | 1
5172 | PURBA BARDHAMAN | Central Mechanical | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 5 & 6 at Augumentation of BAIDYAPUR Water Supply Scheme [BLOCK- KALNA-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1542/CMD | 05/03/2024 | 425 | PROGRESSIVE ENGINEERS CO-OPERATIVE SOCIETY LIMITED | 24.62 | 0 | 0 | 50
5173 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Different Types of work involved in connection with Augmentation of 6 Nos. [(SM/07827), (SM/07866), (SM/16196), (SM/18314), (SM/16021), (SM/16019)] Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 618/BWD | 11/02/2025 | 180 | M/S DATTA ENTERPRISE | 578.09 | 0 | 0 | 0
5174 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of SATGACHI & Aug. of BAIDYAPUR Piped W/S. Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. [Part-B]. | 2827/BWD | 19/07/2024 | 216 | KEJRIWAL CASTINGS LIMITED | 4.82 | 0 | 0 | 100
5175 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of SATGACHI & Aug. of BAIDYAPUR Piped W/S. Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. [Part-A]. | 2839/BWD | 19/07/2024 | 215 | ELECTROSTEEL CASTING LIMITED | 4.95 | 0 | 0 | 100
5176 | PURBA BARDHAMAN | Burdwan Division | AGUMENTATION OF GROUND WATER BASED BAIDYAPUR PWSS TO ACCOMMODATE FHTC IN KALNA-II BLOCK UNDER KALNA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT (ZONE-I & ZONE-II) , SM/10032 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of SATGACHI & Aug. of BAIDYAPUR Piped W/S. Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. [Part-C]. | 2831/BWD | 19/07/2024 | 225 | JINDAL SAW LTD. | 4.63 | 0 | 0 | 100
5177 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10123 | Augmentation | Route Survey and Preparation of DPR for MOUGRAM (ZONE-I & II) PWSS under Ketugram-II Block under Katwa Sub-Division under Burdwan Division PHE Dte. [Sl No-07] | 67/KTS | 27/01/2022 | 21 | RADIANT | 4.11 | 4.11 | 100 | 1
5178 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10123 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
5179 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10123 | Augmentation | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day.(Sl No-1) | 499/KTS | 22/05/2023 | 70 | M/S MUNMUN DEY | 0.9 | 0.3 | 100 | 100
5180 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10123 | Augmentation | Material Requisition To Resource Division | 1383/BWD | 09/03/2022 | 0 | Resource Division | 4.47 | 0 | 0 | 0
5181 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10123 | Augmentation | Material Requisition To Resource Division | 1335/BWD | 08/03/2022 | 0 | Resource Division | 25.88 | 0 | 0 | 0
5182 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10123 | Augmentation | Material Requisition To Resource Division | 1551/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
5183 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10123 | Augmentation | Material Requisition To Resource Division | 3280/BWD | 29/07/2022 | 0 | Resource Division | 34.57 | 0 | 0 | 0
5184 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10123 | Augmentation | Shifting of 63 KVA DTR at Naliapur village of Augmentation of Mougram Z-II water supply scheme under Burdwan Division, PHE Dte. (Ref ID-860268576, Application ID-100000077306, dt.-02/05/2023) | 231/JJM/23-24 | 13/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 4.21 | 0 | 0 | 0
5185 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10123 | Augmentation | Continuation order for Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. (Sl No-1) | 1016/KTS | 20/09/2023 | 23 | M/S MUNMUN DEY | 0.3 | 0.12 | 100 | 0
5186 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED MOUGRAM (ZONE-I & II) PWSS TO ACCOMMODATE FHTC IN KETUGRAM-II BLOCK UNDER KATWA SUB DIVISION OF BURDWAN DIVISION IN PURBA BARDHAMAN DISTRICT , SM/10123 | Augmentation | Augmentation of MOUGRAM (ZONE-I) Piped Water Supply Scheme with LDS, FHTC, & Construction of 250 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation under Ketugram-II Block, District:- Purba-Burdwan. | 2611/BWD | 23/05/2022 | 365 | UMWELT ENGINEER PVT LTD | 499.84 | 314.31 | 100 | 97
5187 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block , SM/07777 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Gramdihi Piped Water Supply Scheme at Mandarbati, Gholada & Bigra Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. (Agreement no. 792/BWD of 2020-2021) | 1794/BWD | 26/02/2021 | 45 | M/S GUPTA ENTERPRISE | 41.94 | 33.9 | 100 | 1
5188 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block , SM/07777 | Retrofitting | Extension of UPVC pipe line of LDS at Gholada village for providing FHTC of Gramdihi and its adjoining mouzas W/S Scheme within Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-C] | 691/DSD | 08/12/2021 | 30 | M/S GUPTA ENTERPRISE | 4.84 | 0 | 0 | 1
5189 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block , SM/07777 | Retrofitting | Extension of pipeline in Connection to FHTC work at Gramdihi village of Gramdihi and its adjoining Mouza's Piped W/S Scheme at Bhatar Block within Durgapur (Bardhaman North)Sub-Division under Burdwan Division, P.H.E. Dte. (Gr.-A) | 416/DSD | 02/07/2021 | 30 | DEY NIRMAN | 4.71 | 0.23 | 100 | 1
5190 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block , SM/07777 | Retrofitting | Extension of UPVC pipe line of LDS at Bighra village for providing FHTC of Gramdihi and its adjoining mouzas W/S Scheme within Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-D] | 692/DSD | 08/12/2021 | 30 | SHUBHRA KANTI GHOSH | 4.3 | 4.1 | 100 | 1
5191 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block , SM/07777 | Retrofitting | Extension of UPVC pipe line of LDS at Manderbati village and Majhipara for providing FHTC of Gramdihi and its adjoining mouzas W/S Scheme within Bhatar Block under Burdwan Division, P.H.E. Dte. [Gr.-B] | 690/DSD | 08/12/2021 | 30 | BIPLAB SAMANTA | 2.26 | 2.22 | 100 | 1
5192 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block , SM/07777 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Bhatar Block under Burdwan Division, PHE. Dte. | 268/BWD | 14/01/2022 | 30 | BHARAT CONSTRUCTION | 14.17 | 7.45 | 100 | 1
5193 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block , SM/07777 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Gramdihi Piped Water Supply Scheme at Gramdihi & Sanchalida Village (Mouza), Bhatar Block under Burdwan Division, PHE Dte. [Agreement No. 631/BWD OF 2020-2021.] | 956/BWD | 03/02/2021 | 45 | DEY NIRMAN | 35.08 | 41.01 | 200 | 0
5194 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block , SM/07777 | Retrofitting | Restoration of work due to laying of Water Supply Pipelines along Bonpass Village(Kamarpara) to Banpass Railway Station Road by Public Health Engineering Directorate under " Jal Jeevan Mission from 0.00 km to 1.54 km in the district of Purba Bardhaman under Burdwan Division,P.W.D." | 866/JJM | 23/09/2024 | 0 | EXECUTIVE ENGINEER PWD BURDWAN DIVISION | 2.94 | 0 | 0 | 0
5195 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block , SM/07777 | Retrofitting | Payment of vehicle bill (Car No.-WB-41H-9788) for the month of September'23. | 899/JJM | 22/11/2023 | 0 | SK. ASRAFUDDIN | 0.4 | 0 | 0 | 0
5196 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Gramdihi Piped Water Supply Scheme at Bhatar Block , SM/07777 | Retrofitting | Restoration of damaged flanks due to laying of HDPE pipe line along the flank of Burdwan Katwa Road from 14.70 kmp to 16.20 kmp in the district of Purba Bardhaman under Bardhaman Division,P.W.D. | 867/JJM | 23/09/2024 | 0 | EXECUTIVE ENGINEER PWD BURDWAN DIVISION | 7.9 | 0 | 0 | 0
5197 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Preparation of DPR for augmentation of Satgachhi W/S Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (Sl No-B) | 182/KSD | 21/02/2022 | 21 | M/S R. DUTTA & CO. | 3.27 | 3.22 | 100 | 1
5198 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 1207/DW | 10/03/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 3005 | 0 | 0 | 0
5199 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Extension of 75 mm dia pipeline at Miya Para, Modhya Bohar & Bhagar Para Purba Bohar regarding FHTC under Satgachia (Zone-I) water supply scheme under Burdwan Division, PHE Dte.[Gr.-A] | 703/BSD | 11/06/2021 | 5 | M/S SAYAN CHAKRABORTY | 0.88 | 0 | 0 | 1
5200 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Material Requisition To Resource Division | 1331/BWD | 08/03/2022 | 0 | Resource Division | 160.86 | 0 | 0 | 0
5201 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Material Requisition To Resource Division | 551/BWD | 27/01/2022 | 0 | Resource Division | 39.34 | 0 | 0 | 0
5202 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Material Requisition To Resource Division | 1545/BWD | 15/03/2022 | 0 | Resource Division | 0.37 | 0 | 0 | 0
5203 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Material Requisition To Resource Division | 1388/BWD | 09/03/2022 | 0 | Resource Division | 4.6 | 0 | 0 | 0
5204 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Material Requisition To Resource Division | 3273/BWD | 29/07/2022 | 0 | Resource Division | 33.26 | 0 | 0 | 0
5205 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Material Requisition To Resource Division | 4630/BWD | 17/10/2022 | 0 | Resource Division | 12.32 | 0 | 0 | 0
5206 | PURBA BARDHAMAN | Central Mechanical | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | New service connection charges for Aug. of Satgachi PWSS TW-4 | BP-2023-24-137 | 25/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.67 | 0 | 0 | 0
5207 | PURBA BARDHAMAN | Central Mechanical | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | New service connection charges for Aug. of Satgachi PWSS TW-3 | BP-2023-24-136 | 25/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.05 | 0 | 0 | 0
5208 | PURBA BARDHAMAN | Central Mechanical | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augumentation of Satgachi Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. [2nd CALL] | 3046/CMD | 20/07/2023 | 30 | AMUSAR IMPEX PVT. LTD. | 21.98 | 21.21 | 96.52 | 95
5209 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Sinking of additional 250 X 150mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for SATGACHHI Piped Water Supply Scheme, Block - Kalna - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 2423/BWD | 11/05/2022 | 30 | M/S SYCHROTECH INDUSTRY | 9.01 | 8.56 | 100 | 100
5210 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 03 Nos. Piped W/S. Schemes under Kalna II Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3016/BWD | 05/08/2024 | 20 | HORIZEN | 7.55 | 2.5 | 100 | 100
5211 | PURBA BARDHAMAN | Central Mechanical | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Quotation for new service connection at Satgachi PWSS PH 5 | BP-2024-25-351 | 05/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.59 | 0 | 0 | 0
5212 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Augmentation of SATGACHI Piped Water Supply Scheme with LDS, FHTC, Rising main, Construction of 700 cum capacity OHR with 20.0 mtr. Staging height inclusive of soil investigation including construction of switch-room (3.60mx3.0m) & boundary wall under Kalna-II Block, District:- Purba-Burdwan. | 2339/BWD | 10/05/2022 | 1056 | P.B. ENTERPRISE | 727.47 | 593.81 | 78.81 | 100
5213 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of SATGACHI & Aug. of BAIDYAPUR Piped W/S. Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. [Part-B]. | 2827/BWD | 19/07/2024 | 216 | KEJRIWAL CASTINGS LIMITED | 4.82 | 0 | 0 | 100
5214 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of SATGACHI & Aug. of BAIDYAPUR Piped W/S. Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. [Part-A]. | 2839/BWD | 19/07/2024 | 215 | ELECTROSTEEL CASTING LIMITED | 4.95 | 0 | 0 | 100
5215 | PURBA BARDHAMAN | Burdwan Division | Augmentation of SATGACHI PWSS for providing Functional Household Tap Connection (FHTC) Block- Kalna-II Purba Burdwan West Bengal , SM/09921 | Augmentation | Supply of various D.I. Mechanical joints & specials for Aug. of SATGACHI & Aug. of BAIDYAPUR Piped W/S. Scheme within Kalna Sub-Division under Burdwan Division, PHE. Dte. [Part-C]. | 2831/BWD | 19/07/2024 | 225 | JINDAL SAW LTD. | 4.63 | 0 | 0 | 100
5216 | PURBA BARDHAMAN | Burdwan Division | Laying of pipe line (parallel to the main line) of the existing Distribution System and providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Srikhanda PWSS at Katwa-I block under Burdwan divisio , SM/12116 | Augmentation | Laying of pipe line (Parallel to the main line) of the existing Distribution System and Providing Functional Household Tap Connection(FHTC) from existing distribution system within the command area of SRIKHANDA Piped Water Supply Scheme at Katwa-I Block under Burdwan Division, PHE Dte. | 2027/BWD | 18/04/2022 | 30 | M/S JOY | 53.12 | 53.15 | 100 | 1
5217 | PURBA BARDHAMAN | Burdwan Division | Laying of pipe line (parallel to the main line) of the existing Distribution System and providing Functional Household Tap connection (FHTC) from existing distribution system within the command area of Srikhanda PWSS at Katwa-I block under Burdwan divisio , SM/12116 | Augmentation | Balance work of OHR, construction Concrete Road, Functional Household Tap Connection, Road restoration etc. for Nanagar PWSS, Srikhanda PWSS, under KATWA -I Block under Katwa Sub-Divn under Burdwan Division, PHE Dte. District:- Purba-Bardhaman. | 3655/BWD | 21/10/2024 | 120 | HAMID SK | 121.69 | 0 | 0 | 0
5218 | PURBA BARDHAMAN | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME , SM/13465 | New | Supply & delivery of different dia. MJ Coller for FHTC as well as smooth running of different W/S. Schemes under Burdwan Division, P.H.E. Dte. [i.e. (1) Magra PWSS, Memari-I Block, (2) Kuchut PWSS, Memari - II Block, (3) Khundkuri PWSS, Khandaghosh Block & (4) Samanti PWSS, Burdwan - II Block)] | 4076/BWD | 13/09/2023 | 20 | SSPR VALVE MANUFACTURING PVT LTD. | 20.63 | 5 | 100 | 100
5219 | PURBA BARDHAMAN | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME , SM/13465 | New | Material Requisition To Resource Division | 1253/BWD | 17/03/2023 | 0 | Resource Division | 16.58 | 0 | 0 | 0
5220 | PURBA BARDHAMAN | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME , SM/13465 | New | Material Requisition To Resource Division | 1631/BWD | 06/04/2023 | 0 | Resource Division | 12.19 | 0 | 0 | 0
5221 | PURBA BARDHAMAN | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME , SM/13465 | New | Material Requisition To Resource Division | 5046/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
5222 | PURBA BARDHAMAN | Central Mechanical | KHUNDKURI PIPED WATER SUPPLY SCHEME , SM/13465 | New | New service connection charges for Khundkuri PWSS TW-1 | BP-2023-24-115 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.93 | 0 | 0 | 0
5223 | PURBA BARDHAMAN | Central Mechanical | KHUNDKURI PIPED WATER SUPPLY SCHEME , SM/13465 | New | New service connection charges for Khundkuri PWSS TW-2 | BP-2023-24-116 | 16/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.65 | 0 | 0 | 0
5224 | PURBA BARDHAMAN | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME , SM/13465 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | 2751/BSD | 28/11/2023 | 183 | SK.ASFIA | 2.4 | 0.4 | 99.92 | 70
5225 | PURBA BARDHAMAN | Central Mechanical | KHUNDKURI PIPED WATER SUPPLY SCHEME , SM/13465 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at BICHKHARA & others water supply scheme under Khandoghosh Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2390/CMD | 02/08/2024 | 90 | MS DAS ELECTRIC CO | 46.54 | 0 | 0 | 0
5226 | PURBA BARDHAMAN | Central Mechanical | KHUNDKURI PIPED WATER SUPPLY SCHEME , SM/13465 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khundkuri Water Supply Scheme [ Block- Khandogosh ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2513/CMD | 02/06/2023 | 30 | RAJIB COMPANY | 28.95 | 23.86 | 100 | 98
5227 | PURBA BARDHAMAN | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME , SM/13465 | New | Interconnection between pump house and delivery line and Construction of boundary wall at 2nd TW site for KHUDKURI PWSS under Khandaghosh Block, District:- Purba-Bardhaman. | 5309/BWD | 01/12/2023 | 60 | JYOTI ENTERPRISE | 12.63 | 12.6 | 100 | 100
5228 | PURBA BARDHAMAN | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME , SM/13465 | New | KHUNDKURI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 350 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Khandaghosh Block, District:- Purba-Bardhaman [NEW SCHEME] | 1217/BWD | 16/03/2023 | 747 | M/S JAN MAHAMMAD | 510.97 | 401.24 | 78.55 | 100
5229 | PURBA BARDHAMAN | Burdwan Division | KHUNDKURI PIPED WATER SUPPLY SCHEME , SM/13465 | New | Supply of flow control devices for KHUNDKURI PWSS (SM/13465) under Burdwan Division, PHE Dte. | 986/AE/HQ | 26/11/2024 | 70 | MAKALI ENGINEERING CORPORATION | 8.33 | 0 | 0 | 100
5230 | PURBA BARDHAMAN | Central Mechanical | KALYANPUR PIPED WATER SUPPLY SCHEME , SM/13939 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Kalyanpur Water Supply Scheme [ Block-Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4055/CMD | 29/08/2023 | 30 | T.N. BANERJEE | 27.71 | 0 | 0 | 0
5231 | PURBA BARDHAMAN | Burdwan Division | KALYANPUR PIPED WATER SUPPLY SCHEME , SM/13939 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 25.59 | 0 | 0 | 0
5232 | PURBA BARDHAMAN | Burdwan Division | KALYANPUR PIPED WATER SUPPLY SCHEME , SM/13939 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 8.13 | 0 | 0 | 0
5233 | PURBA BARDHAMAN | Burdwan Division | KALYANPUR PIPED WATER SUPPLY SCHEME , SM/13939 | New | Material Requisition To Resource Division | 4945/BWD | 10/11/2023 | 0 | Resource Division | 34.27 | 0 | 0 | 0
5234 | PURBA BARDHAMAN | Burdwan Division | KALYANPUR PIPED WATER SUPPLY SCHEME , SM/13939 | New | Material Requisition To Resource Division | 4313/BWD | 29/09/2023 | 0 | Resource Division | 24.08 | 0 | 0 | 0
5235 | PURBA BARDHAMAN | Burdwan Division | KALYANPUR PIPED WATER SUPPLY SCHEME , SM/13939 | New | Material Requisition To Resource Division | 201/BWD | 10/01/2024 | 0 | Resource Division | 5.46 | 0 | 0 | 0
5236 | PURBA BARDHAMAN | Central Mechanical | KALYANPUR PIPED WATER SUPPLY SCHEME , SM/13939 | New | NEW SERVICE CONNECTION FOR KALYANPUR PWSS. | BP-2023-24-555 | 20/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.16 | 0 | 0 | 0
5237 | PURBA BARDHAMAN | Central Mechanical | KALYANPUR PIPED WATER SUPPLY SCHEME , SM/13939 | New | QUOTATION FOR NEW SERVICE CONNECTION FOR KALYANPUR PWSS PH-2. | BP-2024-25-90 | 17/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.89 | 0 | 0 | 0
5238 | PURBA BARDHAMAN | Central Mechanical | KALYANPUR PIPED WATER SUPPLY SCHEME , SM/13939 | New | Quotation for New service connection for Kalyanpur PWSS PH 1 | BP-2024-25-130 | 05/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.51 | 0 | 0 | 0
5239 | PURBA BARDHAMAN | Burdwan Division | KALYANPUR PIPED WATER SUPPLY SCHEME , SM/13939 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to ALIGRAM, JAYKRISHNAPUR, JADABGANJ & KALYANPUR Piped Water Supply Scheme under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 4581/BWD | 16/10/2023 | 965 | SAFECO ENTERPRISES | 1551.98 | 19.44 | 4.43 | 60
5240 | PURBA BARDHAMAN | Burdwan Division | KHAIDYA PIPED WATER SUPPLY SCHEME , SM/13946 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 2.56 | 0 | 0 | 0
5241 | PURBA BARDHAMAN | Burdwan Division | KHAIDYA PIPED WATER SUPPLY SCHEME , SM/13946 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.37 | 0 | 0 | 0
5242 | PURBA BARDHAMAN | Burdwan Division | KHAIDYA PIPED WATER SUPPLY SCHEME , SM/13946 | New | Material Requisition To Resource Division | 5264/BWD | 30/11/2023 | 0 | Resource Division | 21.07 | 0 | 0 | 0
5243 | PURBA BARDHAMAN | Central Mechanical | KHAIDYA PIPED WATER SUPPLY SCHEME , SM/13946 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
5244 | PURBA BARDHAMAN | Central Mechanical | KHAIDYA PIPED WATER SUPPLY SCHEME , SM/13946 | New | New service connection charges for Khaidya PWSS TW-1 | BP-2023-24-396 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.66 | 0 | 0 | 0
5245 | PURBA BARDHAMAN | Central Mechanical | KHAIDYA PIPED WATER SUPPLY SCHEME , SM/13946 | New | New service connection charges for Khaidya PWSS TW-2 | BP-2023-24-397 | 17/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.36 | 0 | 0 | 0
5246 | PURBA BARDHAMAN | Burdwan Division | KHAIDYA PIPED WATER SUPPLY SCHEME , SM/13946 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BARASAT, JAGADABAD & KHAIDYA Piped Water Supply Scheme under BURDWAN-I Block, District:- Purba Bardhaman [NEW SCHEME] | 3460/BWD | 08/08/2023 | 783 | CONCORD EMC ENCLAVE LLP | 1526.24 | 183.82 | 32.47 | 5
5247 | PURBA BARDHAMAN | Central Mechanical | KHAIDYA PIPED WATER SUPPLY SCHEME , SM/13946 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Khaidya Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4000/CMD | 29/08/2023 | 642 | AHALYA ENGINEERING WORKS | 28.95 | 0 | 0 | 90
5248 | PURBA BARDHAMAN | Burdwan Division | KACHUA PIPED WATER SUPPLY SCHEME , SM/13497 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 1.9 | 0 | 0 | 0
5249 | PURBA BARDHAMAN | Burdwan Division | KACHUA PIPED WATER SUPPLY SCHEME , SM/13497 | New | Material Requisition To Resource Division | 3997/BWD | 08/09/2023 | 0 | Resource Division | 0.55 | 0 | 0 | 0
5250 | PURBA BARDHAMAN | Burdwan Division | KACHUA PIPED WATER SUPPLY SCHEME , SM/13497 | New | Material Requisition To Resource Division | 310/BWD | 24/01/2024 | 0 | Resource Division | 17.19 | 0 | 0 | 0
5251 | PURBA BARDHAMAN | Central Mechanical | KACHUA PIPED WATER SUPPLY SCHEME , SM/13497 | New | New service connection for KACHUA PWSS TW-2. | BP-2023-24-505 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.03 | 0 | 0 | 0
5252 | PURBA BARDHAMAN | Central Mechanical | KACHUA PIPED WATER SUPPLY SCHEME , SM/13497 | New | New service connection for KACHUA PWSS TW-1. | BP-2023-24-504 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.27 | 0 | 0 | 0
5253 | PURBA BARDHAMAN | Burdwan Division | KACHUA PIPED WATER SUPPLY SCHEME , SM/13497 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KACHUA & KAMALPUR Piped Water Supply Scheme under Purbasthali ¿ I Block, District:- Purba Bardhaman [NEW SCHEME] | 2344/BWD | 22/05/2023 | 863 | CONCORD ENGINEERING | 470.92 | 169.93 | 62.04 | 40
5254 | PURBA BARDHAMAN | Burdwan Division | KACHUA PIPED WATER SUPPLY SCHEME , SM/13497 | New | Different Types of work involved in connection with Augmentation of SONARUDRA (SM/16349) & KACHUA (SM/13497) Piped Water Supply Scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2430/BWD | 27/06/2024 | 480 | R.G. INFRASTRUCTURE | 240.7 | 103.84 | 58.11 | 2
5255 | PURBA BARDHAMAN | Central Mechanical | KACHUA PIPED WATER SUPPLY SCHEME , SM/13497 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Haripur & others water supply scheme under purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2397/CMD | 02/08/2024 | 90 | CHATTERJEE ENTERPRISE | 48.6 | 0 | 0 | 30
5256 | PURBA BARDHAMAN | Central Mechanical | KACHUA PIPED WATER SUPPLY SCHEME , SM/13497 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at KACHUA Water Supply Scheme [Block - PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4105/CMD | 29/08/2023 | 30 | MENAKA ENTERPRISE. | 20.8 | 17.67 | 94.21 | 95
5257 | PURBA BARDHAMAN | Burdwan Division | KACHUA PIPED WATER SUPPLY SCHEME , SM/13497 | New | Work order for "DESIGNING,MAKING AND ERECTION OF SIGN BOARD FOR SAJAL GRAM IN ¿¿9 No... VILLAGE, ¿PURBASTHALI-1 BLOCK UNDER KALNA SUB DIVISION WITHIN BURDWAN DIVISION PHE DTE.(27nos board)" | 1976/KSD | 05/12/2024 | 10 | OMKAR ENTERPRISE | 3.79 | 0 | 0 | 100
5258 | PURBA BARDHAMAN | Burdwan Division | SHIBADA PIPED WATER SUPPLY SCHEME , SM/13492 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 4.95 | 0 | 0 | 0
5259 | PURBA BARDHAMAN | Burdwan Division | SHIBADA PIPED WATER SUPPLY SCHEME , SM/13492 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 15.17 | 0 | 0 | 0
5260 | PURBA BARDHAMAN | Burdwan Division | SHIBADA PIPED WATER SUPPLY SCHEME , SM/13492 | New | Material Requisition To Resource Division | 4915/BWD | 10/11/2023 | 0 | Resource Division | 16.68 | 0 | 0 | 0
5261 | PURBA BARDHAMAN | Central Mechanical | SHIBADA PIPED WATER SUPPLY SCHEME , SM/13492 | New | New service connection charges for Shibada PWSS TW-1 | BP-2023-24-232 | 20/11/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.08 | 0 | 0 | 0
5262 | PURBA BARDHAMAN | Central Mechanical | SHIBADA PIPED WATER SUPPLY SCHEME , SM/13492 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Shibada Water Supply Scheme [ Block- Ausgram-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4014/CMD | 29/08/2023 | 30 | S.P. CONSTRUCTION | 29.59 | 18.35 | 62 | 48
5263 | PURBA BARDHAMAN | Burdwan Division | SHIBADA PIPED WATER SUPPLY SCHEME , SM/13492 | New | Repairing of Sajaldhara pipeline(Colony para Uttar) for SIBDA Water Supply Scheme of Aushgram-I Block,under Burdwan Division, PHE Dte. | 236/DSD | 12/03/2024 | 15 | ONKAR ENTERPRISE | 0.97 | 0 | 0 | 100
5264 | PURBA BARDHAMAN | Central Mechanical | SHIBADA PIPED WATER SUPPLY SCHEME , SM/13492 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at SAHAPUR & others water supply scheme under Memari-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2392/CMD | 02/08/2024 | 90 | MITRA ENTERPRISE | 47.62 | 0 | 0 | 0
5265 | PURBA BARDHAMAN | Central Mechanical | SHIBADA PIPED WATER SUPPLY SCHEME , SM/13492 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Pichkuri, karatia & others water supply scheme under Ausgram-1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2764/CMD | 26/09/2024 | 90 | JAL PRAVAHIKA PVT LTD | 52.55 | 0 | 0 | 0
5266 | PURBA BARDHAMAN | Durgapur W/S Division | SHIBADA PIPED WATER SUPPLY SCHEME , SM/13492 | New | Material Requisition To Resource Division | 1724/E/DWSD | 10/12/2024 | 0 | Resource Division | 3.95 | 0 | 0 | 0
5267 | PURBA BARDHAMAN | Central Mechanical | SHIBADA PIPED WATER SUPPLY SCHEME , SM/13492 | New | NEW SERVICE CONNECTION FOR SHIBDA PWSS | BP-2023-24-528 | 13/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 16.79 | 0 | 0 | 0
5268 | PURBA BARDHAMAN | Central Mechanical | SHIBADA PIPED WATER SUPPLY SCHEME , SM/13492 | New | Additional quotation for new service connection at Shibda PWSS PH-2 | BP-2024-25-136 | 11/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.35 | 0 | 0 | 0
5269 | PURBA BARDHAMAN | Burdwan Division | SHIBADA PIPED WATER SUPPLY SCHEME , SM/13492 | New | Sinking of Tube-wells, LDS, Rising Main, FHTC, Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation, construction of switch rooms, boundary walls with gates, land development, internal drains and internal pathways at different TW sites for SHIBADA Piped Water Supply Scheme under Ausgram-I Block, District:- Purba Bardhaman [NEW SCHEME] | 3218/BWD | 25/07/2023 | 365 | ONKAR ENTERPRISE | 319.96 | 195.9 | 61.23 | 71
5270 | PURBA BARDHAMAN | Burdwan Division | SHIBADA PIPED WATER SUPPLY SCHEME , SM/13492 | New | Sajaldhara pipeline(Colony para Dakshin) for SIBDA Water Supply Scheme of Aushgram-I Block,under Burdwan Division, PHE Dte. | 242/DSD | 12/03/2024 | 15 | ONKAR ENTERPRISE | 0.98 | 0 | 0 | 100
5271 | PURBA BARDHAMAN | Durgapur W/S Division | SHIBADA PIPED WATER SUPPLY SCHEME , SM/13492 | New | FORMAL WORK ORDER FOR Balance and additional works for sinking of 300X200 mm dia X 210 mtr deapth RRM Tube well and laying pipe line (LDS),FHTC, Construction of Switch Room,Pump House,Inter Connection along with road restoration and construction of Boundary wall for head worksites and other allieds work related to JJM (7 Nos PWSS) i.e. Aushgram PWSS, Jalkandar and Bhuyera PWSS, Karatia PWSS, Khandari PWSS, Pichkuri PWSS, Shibda PWSS under Aushgram-I and II,Galsi-I and II Block under DURGAPUR W/S DIVISION,PHE Dte. | 493/DWSD | 19/03/2025 | 185 | MANASH GHOSH | 745.87 | 0 | 0 | 1
5272 | PURBA BARDHAMAN | Burdwan Division | DHARALA PIPED WATER SUPPLY SCHEME , SM/14056 | New | Material Requisition To Resource Division | 1641/BWD | 06/04/2023 | 0 | Resource Division | 0.78 | 0 | 0 | 0
5273 | PURBA BARDHAMAN | Burdwan Division | DHARALA PIPED WATER SUPPLY SCHEME , SM/14056 | New | Material Requisition To Resource Division | 1240/BWD | 17/03/2023 | 0 | Resource Division | 2.49 | 0 | 0 | 0
5274 | PURBA BARDHAMAN | Burdwan Division | DHARALA PIPED WATER SUPPLY SCHEME , SM/14056 | New | Material Requisition To Resource Division | 5243/BWD | 30/11/2023 | 0 | Resource Division | 18.5 | 0 | 0 | 0
5275 | PURBA BARDHAMAN | Central Mechanical | DHARALA PIPED WATER SUPPLY SCHEME , SM/14056 | New | New service connection charges for Dharala PWSS TW-1 | BP-2023-24-68 | 20/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.76 | 0 | 0 | 0
5276 | PURBA BARDHAMAN | Burdwan Division | DHARALA PIPED WATER SUPPLY SCHEME , SM/14056 | New | DHARALA [DHARALA VILLAGE] Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under AUSGRAM-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1208/BWD | 15/03/2023 | 90 | THREE MAA ENTERPRISE | 68.82 | 68.41 | 100 | 100
5277 | PURBA BARDHAMAN | Burdwan Division | DHARALA PIPED WATER SUPPLY SCHEME , SM/14056 | New | DHARALA [RAGHUNATHPUR VILLAGE] Piped Water Supply Scheme with sinking of Tube-well, LDS, FHTC & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under AUSGRAM-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | 2054/BWD | 04/05/2023 | 90 | BIPLAB GUHA | 65.39 | 65.19 | 100 | 100
5278 | PURBA BARDHAMAN | Durgapur W/S Division | DHARALA PIPED WATER SUPPLY SCHEME , SM/14056 | New | Material Requisition To Resource Division | 1724/F/DWSD | 10/12/2024 | 0 | Resource Division | 5.24 | 0 | 0 | 0
5279 | PURBA BARDHAMAN | Central Mechanical | DHARALA PIPED WATER SUPPLY SCHEME , SM/14056 | New | New service connection charges for Dharala PWSS TW-2 | BP-2023-24-286 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.29 | 0 | 0 | 0
5280 | PURBA BARDHAMAN | Central Mechanical | DHARALA PIPED WATER SUPPLY SCHEME , SM/14056 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Dharala Water Supply Scheme [ Block- Ausgram-II ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. [3rd CALL] | 3048/CMD | 20/07/2023 | 651 | J.S. CONSTRUCTION. | 29.71 | 0 | 0 | 70
5281 | PURBA BARDHAMAN | Durgapur W/S Division | DHARALA PIPED WATER SUPPLY SCHEME , SM/14056 | New | Acceptance cum Formal Work Order for Balance works related ( LDS , FHTCs, Road Restoration of Dharala Piped Water Supply Scheme under Aushgram-II Block, of Durgapur Water supply Division, PHE Dte. | 1609/DWSD | 26/11/2024 | 180 | SARKAR AGENCY | 51.36 | 0 | 0 | 70
5282 | PURBA BARDHAMAN | Burdwan Division | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 14.82 | 0 | 0 | 0
5283 | PURBA BARDHAMAN | Burdwan Division | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Material Requisition To Resource Division | 4888/BWD | 10/11/2023 | 0 | Resource Division | 29.45 | 0 | 0 | 0
5284 | PURBA BARDHAMAN | Burdwan Division | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 22.25 | 0 | 0 | 0
5285 | PURBA BARDHAMAN | Central Mechanical | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Quotation for New Electric Connection for Taipara W/S Scheme PH NO.-1 | BP-2023-24-248 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.1 | 0 | 0 | 0
5286 | PURBA BARDHAMAN | Central Mechanical | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Electric quotation for New Service Connection at Taipara W/S Scehem PH-2. | BP-2023-24-288 | 26/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.67 | 0 | 0 | 0
5287 | PURBA BARDHAMAN | Central Mechanical | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
5288 | PURBA BARDHAMAN | Burdwan Division | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Work Order for "Restoration of pipeline with other allied works at different places of Dhaleswar mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | 973/KSD | 31/07/2024 | 10 | S.GHOSH & ASSOCIATES PVT LTD. | 2.29 | 2.15 | 100 | 100
5289 | PURBA BARDHAMAN | Burdwan Division | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL UNDER PATHARDANGA PWSS AND TAIPARA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE. (2 UNITS:- 1 NO FOR PATHARDANGA PWSS & 1 NO FOR TAIPARA PWSS)" | 1977/KSD | 09/02/2024 | 10 | BISWAS ENTERPRISE | 0.66 | 0.33 | 100 | 100
5290 | PURBA BARDHAMAN | Burdwan Division | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Work order for "Restoration of pipeline with other allied works at different places of Bagpur mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | 971/KSD | 31/07/2024 | 10 | S.GHOSH & ASSOCIATES PVT LTD. | 2.84 | 2.62 | 100 | 100
5291 | PURBA BARDHAMAN | Burdwan Division | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Work order for "Restoration of pipeline with other allied works at different places of Rajkhara mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | 970/KSD | 31/07/2024 | 10 | S.GHOSH & ASSOCIATES PVT LTD. | 2.75 | 2.69 | 100 | 100
5292 | PURBA BARDHAMAN | Burdwan Division | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Work Order for "Restoration of pipeline with other allied works at different places of Bherua mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | 972/KSD | 31/07/2024 | 10 | S.GHOSH & ASSOCIATES PVT LTD. | 3.39 | 3.28 | 100 | 100
5293 | PURBA BARDHAMAN | Central Mechanical | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Taipara Water Supply Scheme [ Block- KALNA-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4063/CMD | 29/08/2023 | 30 | P.K. ENGINEERING | 28.89 | 23.32 | 95.56 | 90
5294 | PURBA BARDHAMAN | Burdwan Division | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Work order for "Restoration of pipeline with other allied works at different places of Chaugharia mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | 1848/KSD | 27/11/2024 | 15 | S.GHOSH & ASSOCIATES PVT LTD. | 3.17 | 0 | 0 | 100
5295 | PURBA BARDHAMAN | Burdwan Division | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Work order for "Restoration of pipeline with other allied works at different places of Narayanpur mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte.". | 1850/KSD | 27/11/2024 | 15 | S.GHOSH & ASSOCIATES PVT LTD. | 3.58 | 0 | 0 | 100
5296 | PURBA BARDHAMAN | Burdwan Division | TAIPARA Piped Water Supply Scheme. , SM/14442 | New | Work order for "Restoration of pipeline with other allied works at different places of Kulera mouja under Taipara Pwss due to construction of rcc cover drain & widening of rcc concrete road constructed by PRI body under Kalna-I panchayat samiti under Kalna Sub-Division under Burdwan Division, PHE Dte." | 1851/KSD | 27/11/2024 | 15 | S.GHOSH & ASSOCIATES PVT LTD. | 3.64 | 0 | 0 | 100
5297 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN , SM/14014 | Augmentation | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of NASARATPUR Piped Water Supply Scheme at Gopinathpur (Part), Nasaratput (Part) & Paruldanga (Part) Village (Mouza), Purbasthali - I Block under Burdwan Division, PHE Dte | 211/BWD | 11/01/2022 | 60 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 76.77 | 59.72 | 100 | 1
5298 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN , SM/14014 | Augmentation | Digital structurization of pipeline alignment and asset evaluation including holistic design, preparation of design drawings of overall LDS & preparation of estimate for 14 Nos. Piped W/S. Schemes under Purbasthali I Block under Kalna Sub-Division under Burdwan Division, PHE. Dte. | 3017/BWD | 05/08/2024 | 75 | HORIZEN | 38 | 13.64 | 100 | 100
5299 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN , SM/14014 | Augmentation | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL UNDER NASARATPUR PWSS UNDER KALNA SUB-DIVISION UNDER BURDWAN DIVISION, PHE DTE." | 1978/KSD | 09/02/2024 | 10 | BISWAS ENTERPRISE | 0.66 | 0.66 | 100 | 100
5300 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN , SM/14014 | Augmentation | New service connection for Augmentation of Nasratpur PWSS TW-2. | BP-2023-24-509 | 06/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.21 | 0 | 0 | 0
5301 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN , SM/14014 | Augmentation | New service connection for augmentation of Nasratpur PH-I PWSS. | BP-2024-25-30 | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 10.19 | 0 | 0 | 0
5302 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN , SM/14014 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 3 & 4 at Augumentation of NASRATPUR Water Supply Scheme [BLOCK- PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1544/CMD | 05/03/2024 | 453 | MS DAS ELECTRIC CO | 24.63 | 11.7 | 47.52 | 95
5303 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN , SM/14014 | Augmentation | Different types of works involve in connection with Augmentation of NASRATPUR PWSS (SM/14014), Purbasthali-I Block, under Kalna Sub-Division under Burdwan Division, PHE Dte. | 432/BWD | 20/01/2025 | 120 | SANDIP BISWAS | 199.5 | 0 | 0 | 0
5304 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN , SM/14014 | Augmentation | Augmentation of NASARATPUR (Part-B) Piped Water Supply Scheme with Sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of switch rooms & Boundary walls with gates at different TW site under Purbasthali-I Block, District:- Purba Bardhaman. | 3535/BWD | 10/08/2023 | 541 | IJABUL SEKH | 512.69 | 357.15 | 70.45 | 60
5305 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN , SM/14014 | Augmentation | Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire in connection with Augmentation of .NASARATPUR Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte.(P.H: 1) | 3732/BWD | 29/10/2024 | 30 | DEBJYOTI GOSWAMI | 9.71 | 0 | 0 | 1
5306 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED WATER SUPPLY SCHEME FOR NASRATPUR PWSS (PART-B) UNDER BURDWAN DIVISION BLOCK PURBASTHALI I DISTRICT PURBA BARDDHAMAN , SM/14014 | Augmentation | Construction of 1.5 mtrs. Height Boundary Wall along with 750 mm Height 3 layer barbed wire in connection with Augmentation of NASARATPUR Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. (P.H: 2) | 3731/BWD | 29/10/2024 | 30 | CHOWDHURY CONSTRUCTION | 9.68 | 0 | 0 | 100
5307 | PURBA BARDHAMAN | Burdwan Division | BELGRAM PIPED WATER SUPPLY SCHEME , SM/14018 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 141.29 | 0 | 0 | 0
5308 | PURBA BARDHAMAN | Burdwan Division | BELGRAM PIPED WATER SUPPLY SCHEME , SM/14018 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 9.94 | 0 | 0 | 0
5309 | PURBA BARDHAMAN | Burdwan Division | BELGRAM PIPED WATER SUPPLY SCHEME , SM/14018 | New | Material Requisition To Resource Division | 4925/BWD | 10/11/2023 | 0 | Resource Division | 39.08 | 0 | 0 | 0
5310 | PURBA BARDHAMAN | Central Mechanical | BELGRAM PIPED WATER SUPPLY SCHEME , SM/14018 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
5311 | PURBA BARDHAMAN | Burdwan Division | BELGRAM PIPED WATER SUPPLY SCHEME , SM/14018 | New | Quotation from WBSEDCL for load enhancement of Belgram water supply scheme for PH-2 under Burdwan Division, PHE Dte. | 267/JJM | 21/05/2024 | 0 | WBSEDCL | 4.33 | 0 | 0 | 0
5312 | PURBA BARDHAMAN | Central Mechanical | BELGRAM PIPED WATER SUPPLY SCHEME , SM/14018 | New | New service connection charges for Belgram PWSS TW-1 | BP-2023-24-372 | 16/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.27 | 0 | 0 | 0
5313 | PURBA BARDHAMAN | Burdwan Division | BELGRAM PIPED WATER SUPPLY SCHEME , SM/14018 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to SHYAMSUNDARPUR & BELGRAM Piped Water Supply Scheme under Galsi-II Block, District:- Purba-Bardhaman [NEW SCHEME] | 2147/BWD | 10/05/2023 | 730 | MAHMOOD ASSOCIATES PVT. LTD. | 1172.24 | 420.36 | 71.46 | 78
5314 | PURBA BARDHAMAN | Central Mechanical | BELGRAM PIPED WATER SUPPLY SCHEME , SM/14018 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Belgrem Water Supply Scheme [ Block- Galsi-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4066/CMD | 29/08/2023 | 580 | PADMA ENGINEERING CO. | 27.78 | 22.31 | 97.63 | 48
5315 | PURBA BARDHAMAN | Burdwan Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME , SM/14072 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 17.75 | 0 | 0 | 0
5316 | PURBA BARDHAMAN | Burdwan Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME , SM/14072 | New | Material Requisition To Resource Division | 5236/BWD | 30/11/2023 | 0 | Resource Division | 18.78 | 0 | 0 | 0
5317 | PURBA BARDHAMAN | Burdwan Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME , SM/14072 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 79.1 | 0 | 0 | 0
5318 | PURBA BARDHAMAN | Central Mechanical | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME , SM/14072 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Satinandi,Sanko & others water supply scheme under Galsi-1 Block ; Serpur, Uchalan & others water supply scheme under Raina-2 Block and maro, loapur & others water supply scheme under Galsi-2 block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2751/CMD | 24/09/2024 | 90 | ORIENTAL ENGINEERING CO. | 88.42 | 0 | 0 | 0
5319 | PURBA BARDHAMAN | Durgapur W/S Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME , SM/14072 | New | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method for Trial Bore at Uchchagram under Krishnarampur PWSS (JJM) District:- Purba-Bardhaman, Under Durgapur W/S Division , PHE Dte. | 1418/DWSD | 03/10/2024 | 20 | D.M.ENTERPRISE | 6.61 | 6.61 | 100 | 80
5320 | PURBA BARDHAMAN | Burdwan Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME , SM/14072 | New | Material Requisition To Resource Division | 317/BWD | 24/01/2024 | 0 | Resource Division | 43.39 | 0 | 0 | 0
5321 | PURBA BARDHAMAN | Durgapur W/S Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME , SM/14072 | New | Material Requisition To Resource Division | 1724/Q/DWSD | 10/12/2024 | 0 | Resource Division | 4 | 0 | 0 | 0
5322 | PURBA BARDHAMAN | Central Mechanical | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME , SM/14072 | New | NEW SERVICE CONNECTION FOR KRISHNARAMPUR PWSS PH-1. | BP-2023-24-606 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.75 | 0 | 0 | 0
5323 | PURBA BARDHAMAN | Central Mechanical | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME , SM/14072 | New | NEW SERVICE CONNECTION FOR KRISHNARAMPUR PWSS PH-2. | BP-2023-24-607 | 06/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.94 | 0 | 0 | 0
5324 | PURBA BARDHAMAN | Burdwan Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME , SM/14072 | New | KRISHNARAMPUR Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Galsi-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 3234/BWD | 26/07/2023 | 791 | DUTTA ENTERPRISE | 661.41 | 249.5 | 37.72 | 80
5325 | PURBA BARDHAMAN | Central Mechanical | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME , SM/14072 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1, 2 & 3 at KRISHNARAMPUR Water Supply Scheme [ Block- GALSI-2] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4085/CMD | 29/08/2023 | 30 | BENGAL CONSTRUCTION. | 40.47 | 0 | 0 | 96
5326 | PURBA BARDHAMAN | Durgapur W/S Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME , SM/14072 | New | Acceptance cum Formal Work Order for Balance work for KRISHNARAMPUR Piped Water Supply Scheme i.e , Contruction of boundary walls with gates and land development, drain and internal pathway etc. at 3rd Pump house site & FHTC work under GALSI-I Block, District:- Purba-Bardhaman under Durgapur W/S Division, PHE Dte. | 1549/DWSD | 14/11/2024 | 270 | JOY GURU ENTERPRISE | 43.27 | 0 | 0 | 100
5327 | PURBA BARDHAMAN | Durgapur W/S Division | KRISHNARAMPUR PIPED WATER SUPPLY SCHEME , SM/14072 | New | Acceptance cum Formal Work Order for Sinking of 300 x 200 mm dia tube well 150 mtr depth by DR Rig method for trial bore at Sirorai and Bikrampur under Krishnarampur PWSS (JJM), Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 1597/DWSD | 25/11/2024 | 20 | MANASH GHOSH | 10.17 | 10.17 | 100 | 100
5328 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PARGUNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13282 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.04 | 0 | 0 | 0
5329 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PARGUNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13282 | New | Material Requisition To Resource Division | 4298/BWD | 29/09/2023 | 0 | Resource Division | 136.65 | 0 | 0 | 0
5330 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PARGUNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13282 | New | NEW SERVICE CONNECTION FOR PURGUNA PIPED WATER SUPPLY SCHEME. | BP-2023-24-586 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.73 | 0 | 0 | 0
5331 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PARGUNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13282 | New | New service connection for Parguna PH-2 PWSS. | BP-2024-25-27 | 19/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 7.38 | 0 | 0 | 0
5332 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PARGUNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13282 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Parguna Water Supply Scheme [ Block- Monteshwar ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4047/CMD | 29/08/2023 | 30 | SINHA ELECTRICALS | 27.78 | 0 | 0 | 90
5333 | PURBA BARDHAMAN | Burdwan Division | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PARGUNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13282 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to BELENDA, JAMNA, PIPLON & PARGUNA Piped Water Supply Scheme under Manteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | 4388/BWD | 05/10/2023 | 667 | AKASH CONSTRUCTION | 2296.4 | 164.51 | 27.48 | 50
5334 | PURBA BARDHAMAN | Central Mechanical | GROUND WATER SUPPLY BASED PIPED WATER SUPPLY SCHEME FOR PARGUNA PWSS IN MANTESHWAR BLOCK OF PURBA BARDHAMAN UNDER BURDWAN DIVISION PHE DTE , SM/13282 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Sutra & others water supply scheme under Monteswar Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2396/CMD | 02/08/2024 | 455 | SINHA ELECTRICALS | 78.06 | 0 | 0 | 20
5335 | PURBA BARDHAMAN | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME , SM/14077 | New | Continuation order for Hiring of Inspection Vehicle (Diesel/CNG/LPG Driven) for supervision of site for the office of the Assistant Engineer, under C.M.D. P.H.E. Dte. w.e.f.-01/09/2023 to 31/10/2023 [JJM Works]. | 734/CMSD-I | 29/08/2023 | 61 | SUBRATA BHADRA | 0.79 | 0.79 | 100 | 50
5336 | PURBA BARDHAMAN | Burdwan Division | UTRA PIPED WATER SUPPLY SCHEME , SM/14077 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 49.01 | 0 | 0 | 0
5337 | PURBA BARDHAMAN | Burdwan Division | UTRA PIPED WATER SUPPLY SCHEME , SM/14077 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 12.47 | 0 | 0 | 0
5338 | PURBA BARDHAMAN | Burdwan Division | UTRA PIPED WATER SUPPLY SCHEME , SM/14077 | New | Material Requisition To Resource Division | 4940/BWD | 10/11/2023 | 0 | Resource Division | 39.83 | 0 | 0 | 0
5339 | PURBA BARDHAMAN | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME , SM/14077 | New | New service connection charges for Utra PWSS TW 1 | BP-2023-24-91 | 31/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.03 | 0 | 0 | 0
5340 | PURBA BARDHAMAN | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME , SM/14077 | New | New service connection charges for Utra PWSS TW 2 | BP-2023-24-90 | 28/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.59 | 0 | 0 | 0
5341 | PURBA BARDHAMAN | Burdwan Division | UTRA PIPED WATER SUPPLY SCHEME , SM/14077 | New | UTRA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 300 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Monteswar Block, District:- Purba-Bardhaman [NEW SCHEME] | 1698/BWD | 12/04/2023 | 365 | M/S S.S. ENTERPRISE | 487.32 | 426.97 | 87.62 | 87
5342 | PURBA BARDHAMAN | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME , SM/14077 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Joykrishnapur & others water supply scheme under Purbasthali-2,jamalpur,kalna 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2398/CMD | 02/08/2024 | 90 | MS S G ENTERPRISE | 53.43 | 0 | 0 | 0
5343 | PURBA BARDHAMAN | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME , SM/14077 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at UTRA Water Supply Scheme [ Block- KALNA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2857/CMD | 05/07/2023 | 30 | SOUNAK ENTERPRISE | 28.48 | 23.15 | 100 | 90
5344 | PURBA BARDHAMAN | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME , SM/14077 | New | Supply and Delivery of standby Chlorination System for Utra PH 1 & others Water Supply Scheme under CMD, PHE Dte. | 812/CMSD | 04/10/2023 | 30 | SUBRATA BHADRA | 0.9 | 0.9 | 100 | 100
5345 | PURBA BARDHAMAN | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME , SM/14077 | New | Supply and Delivery of standby Chlorination System for Utra PH 2 & others Water Supply Scheme under CMD, PHE Dte. | 813/CMSD | 04/10/2023 | 30 | SUBRATA BHADRA | 0.9 | 0.9 | 100 | 100
5346 | PURBA BARDHAMAN | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME , SM/14077 | New | Standby Pump Motor set for Utra PH 2 Water Supply Scheme under CMD, PHE Dte. | 1074/CMSD | 15/12/2023 | 12 | M/S. S.D. CONSTRUCTION | 0.84 | 0.84 | 100 | 100
5347 | PURBA BARDHAMAN | Central Mechanical | UTRA PIPED WATER SUPPLY SCHEME , SM/14077 | New | Standby Pump Motor set for UTRA PH 1 water supply scheme under CMD,PHE,Dte. | 1076/CMSD | 15/12/2023 | 15 | SUDIKSHA CONSTRUCTION | 0.84 | 0.84 | 100 | 100
5348 | PURBA BARDHAMAN | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME , SM/13318 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 13.55 | 0 | 0 | 0
5349 | PURBA BARDHAMAN | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME , SM/13318 | New | Material Requisition To Resource Division | 3996/BWD | 08/09/2023 | 0 | Resource Division | 1.64 | 0 | 0 | 0
5350 | PURBA BARDHAMAN | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME , SM/13318 | New | New service connection charges for Masgaria PWSS TW-1 | BP-2023-24-132 | 05/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.75 | 0 | 0 | 0
5351 | PURBA BARDHAMAN | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME , SM/13318 | New | New service connection charges for Masgaria PWSS TW-2 | BP-2023-24-165 | 26/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.2 | 0 | 0 | 0
5352 | PURBA BARDHAMAN | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME , SM/13318 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to KONRAPUR & MASGARIA Piped Water Supply Scheme under Purbasthali-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 1765/BWD | 17/04/2023 | 365 | M/S ASHA CONSTRUCTION | 710.72 | 202.16 | 66.21 | 43
5353 | PURBA BARDHAMAN | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME , SM/13318 | New | Supply and delivery of different Electro-mechanical items (for urgent FHTC) for masgaria Water Supply Scheme PH 2 (part-1) under CMD, PHE Dte., Dist.- Purba-Bardhaman | 07/CMSD | 02/01/2024 | 10 | DIPALI CONSTRUCTION | 0.92 | 0.92 | 100 | 100
5354 | PURBA BARDHAMAN | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME , SM/13318 | New | Emergency installation (for urgent FHTC) at Masgaria Water Supply Scheme PH 2 (part-3) under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 84/CMSD | 15/01/2024 | 12 | DIPALI CONSTRUCTION | 0.8 | 0.8 | 100 | 100
5355 | PURBA BARDHAMAN | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME , SM/13318 | New | Work Order for "CONSTRUCTION OF TEMPORARY KIOSK FOR THE NECESSARY ARRANGEMENT OF ELECTRIFICATION OF TUBEWELL FOR MASGARIA PWSS UNDER KALNA SUB-DIVISION UNDER BURDWN DIVISION, PHE DTE." | 1981/KSD | 09/02/2024 | 10 | ER CONSTRUCTION & GENERAL ORDER SUPPLIER | 0.33 | 0.33 | 100 | 2
5356 | PURBA BARDHAMAN | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME , SM/13318 | New | Supply and delivery of submersible pumping machinery (for urgent FHTC) for masgaria Water Supply Scheme PH 2 (part-2) under CMD, PHE Dte., Dist.- Purba-Bardhaman | 67/CMSD | 11/01/2024 | 12 | DIPALI CONSTRUCTION | 0.85 | 0.85 | 100 | 100
5357 | PURBA BARDHAMAN | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME , SM/13318 | New | Material Requisition To Resource Division | 294/BWD | 24/01/2024 | 0 | Resource Division | 14.63 | 0 | 0 | 0
5358 | PURBA BARDHAMAN | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME , SM/13318 | New | Addl quotation for New service connection charges for Masgaria PWSS TW-1 | BP-2023-24-240 | 07/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.44 | 0 | 0 | 0
5359 | PURBA BARDHAMAN | Burdwan Division | MASGARIA PIPED WATER SUPPLY SCHEME , SM/13318 | New | Different types of balance works involve in connection with KONRAPUR (SM/13419) & MASGORIA (SM/13318) Piped water supply scheme under Purbasthali-I Block within Kalna Sub-Division under Burdwan Division, PHE Dte. | 142/BWD | 08/01/2025 | 120 | M/S ASHA CONSTRUCTION | 65.74 | 0 | 0 | 0
5360 | PURBA BARDHAMAN | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME , SM/13318 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Manganpur & others water supply scheme under Purbasthali 1 Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2979/CMD | 25/11/2024 | 90 | H.K. DAS & CO. | 53.27 | 0 | 0 | 0
5361 | PURBA BARDHAMAN | Central Mechanical | MASGARIA PIPED WATER SUPPLY SCHEME , SM/13318 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination System and Internal House wiring for Tube well no.- 1 & 2 at MASGARIA Water Supply Scheme [Block-PURBASTHALI-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3505/CMD | 31/07/2023 | 30 | M/S. SWAPAN BANERJEE | 21.55 | 19.38 | 94.7 | 95
5362 | PURBA BARDHAMAN | Burdwan Division | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME , SM/13466 | New | Material Requisition To Resource Division | 1266/BWD | 17/03/2023 | 0 | Resource Division | 3.1 | 0 | 0 | 0
5363 | PURBA BARDHAMAN | Burdwan Division | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME , SM/13466 | New | Material Requisition To Resource Division | 1635/BWD | 06/04/2023 | 0 | Resource Division | 16.63 | 0 | 0 | 0
5364 | PURBA BARDHAMAN | Burdwan Division | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME , SM/13466 | New | Material Requisition To Resource Division | 4901/BWD | 10/11/2023 | 0 | Resource Division | 34.12 | 0 | 0 | 0
5365 | PURBA BARDHAMAN | Central Mechanical | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME , SM/13466 | New | New service connection charges for Chak Radhamohanpur PWSS TW-1 | BP-2023-24-59 | 17/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.13 | 0 | 0 | 0
5366 | PURBA BARDHAMAN | Central Mechanical | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME , SM/13466 | New | New service connection charges for Chak Radhamohanpur PWSS TW-2 | BP-2023-24-62 | 18/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 6.09 | 0 | 0 | 0
5367 | PURBA BARDHAMAN | Central Mechanical | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME , SM/13466 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Chak Radhamohanpur Water Supply Scheme [ Block- Ausgram-2 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2492/CMD | 01/06/2023 | 30 | MS DAS ELECTRIC CO | 27.73 | 22.32 | 100 | 40
5368 | PURBA BARDHAMAN | Central Mechanical | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME , SM/13466 | New | Addl. Quotation for new electric service connection at Chak Radhamohanpur PH NO.-2 | BP-2023-24-265 | 11/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.76 | 0 | 0 | 0
5369 | PURBA BARDHAMAN | Burdwan Division | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME , SM/13466 | New | CHAK RADHAMOHANPUR Piped Water Supply Scheme with Sinking of tube-well, LDS, Rising Main, FHTC & construction of switch-rooms & boundary walls at different TW site under Aushgram-II Block, District:- Purba-Bardhaman [NEW SCHEME]. | 453/BWD | 06/02/2023 | 240 | HAMID SK | 122.63 | 122.56 | 99.16 | 100
5370 | PURBA BARDHAMAN | Durgapur W/S Division | CHAK RADHAMOHANPUR PIPED WATER SUPPLY SCHEME , SM/13466 | New | Acceptance cum Formal Work Order for Additional Distribution Pipeline work at CHAK RADHAMOHANPUR Piped Water Supply Scheme (Chak Radhamohanpur Muslimpara and Chak Radhamohanpur Hatchery Para) with LDS & FHTC work under Ausgram-II Block, Dist- Purba Bardhaman under Durgapur W/S Division, PHE Dte. | 1381/DWSD | 26/09/2024 | 101 | HAMID SK | 18.67 | 0 | 0 | 100
5371 | PURBA BARDHAMAN | Burdwan Division | KHERUA PIPED WATER SUPPLY SCHEME , SM/15240 | New | Material Requisition To Resource Division | 1639/BWD | 06/04/2023 | 0 | Resource Division | 1.38 | 0 | 0 | 0
5372 | PURBA BARDHAMAN | Burdwan Division | KHERUA PIPED WATER SUPPLY SCHEME , SM/15240 | New | Material Requisition To Resource Division | 1245/BWD | 17/03/2023 | 0 | Resource Division | 9.37 | 0 | 0 | 0
5373 | PURBA BARDHAMAN | Burdwan Division | KHERUA PIPED WATER SUPPLY SCHEME , SM/15240 | New | Material Requisition To Resource Division | 5045/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
5374 | PURBA BARDHAMAN | Central Mechanical | KHERUA PIPED WATER SUPPLY SCHEME , SM/15240 | New | Additional quotation for New service connection charges for Kherua PWSS TW-2 | BP-2023-24-128 | 21/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.03 | 0 | 0 | 0
5375 | PURBA BARDHAMAN | Central Mechanical | KHERUA PIPED WATER SUPPLY SCHEME , SM/15240 | New | New service connection charges of Kherua W/S Scheme TW-1 | BP-2023-24-33 | 26/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.59 | 0 | 0 | 0
5376 | PURBA BARDHAMAN | Central Mechanical | KHERUA PIPED WATER SUPPLY SCHEME , SM/15240 | New | New service connection charges for Kherua PWSS TW-2 | BP-2023-24-124 | 18/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.67 | 0 | 0 | 0
5377 | PURBA BARDHAMAN | Central Mechanical | KHERUA PIPED WATER SUPPLY SCHEME , SM/15240 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
5378 | PURBA BARDHAMAN | Central Mechanical | KHERUA PIPED WATER SUPPLY SCHEME , SM/15240 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at KHERUA Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2510/CMD | 02/06/2023 | 30 | GOENKA ENTERPRISE | 26.97 | 21.45 | 97.53 | 100
5379 | PURBA BARDHAMAN | Burdwan Division | KHERUA PIPED WATER SUPPLY SCHEME , SM/15240 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to GOHAGRAM, KHERUA & JABAGRAM Piped Water Supply Scheme under Mangalkote Block, District:- Purba Bardhaman [NEW SCHEME] | 582/BWD | 17/02/2023 | 1049 | PUSPA ENTERPRISE | 1185.88 | 346.54 | 95.47 | 75
5380 | PURBA BARDHAMAN | Burdwan Division | KHERUA PIPED WATER SUPPLY SCHEME , SM/15240 | New | Different types of works involve in connection with implementation of Gohgram, Jabagram, Kherua, Lakshmipur & Simulia Piped Water Supply Scheme under Mongolkote Block within Katwa Sub-Division under Burdwan Division, PHE Dte. | 936/BWD | 11/03/2025 | 180 | M/S GHOSH CONSTRUCTION | 360.68 | 0 | 0 | 0
5381 | PURBA BARDHAMAN | Burdwan Division | KHERUA PIPED WATER SUPPLY SCHEME , SM/15240 | New | Providing left out FHTC at different places of Kherua village in order to declare swajal gram under the command area of Kherua Piped water supply scheme within (SM/ 15240) Katwa Sub-Division under Burdwan Division, PHE Dte.(Sl No-1) | 336/KTS | 05/03/2025 | 37 | CHANCHAL PAL | 4.25 | 0 | 0 | 100
5382 | PURBA BARDHAMAN | Burdwan Division | KHERUA PIPED WATER SUPPLY SCHEME , SM/15240 | New | Providing left out FHTC at different places of Kowarpur village in order to declare swajal gram under the command area of Kherua Piped water supply scheme (SM/15240) within Katwa Sub-Division under Burdwan Division, PHE Dte.(Sl No-3) | 338/KTS | 05/03/2025 | 48 | CHANCHAL PAL | 3.4 | 0 | 0 | 100
5383 | PURBA BARDHAMAN | Burdwan Division | KHERUA PIPED WATER SUPPLY SCHEME , SM/15240 | New | Providing left out FHTC at different places of Sanri village in order to declare swajal gram under the command area of Kherua Piped water supply scheme (SM/15240) within Katwa Sub-Division under Burdwan Division, PHE Dte.(Sl No-2) | 337/KTS | 05/03/2025 | 39 | BABUL SK | 3.66 | 0 | 0 | 100
5384 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08708 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of JOTRAGHAB Piped Water Supply Scheme at (JOTKRISHTAI) Mouza under Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 4007/BWD | 15/09/2022 | 30 | PAL CONSTRUCTION | 13.87 | 13.63 | 100 | 1
5385 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08708 | Retrofitting | Quotation for payment of service connection charge on full deposit scheme of Jotraghab w/s scheme. | 724/DW/22-23 | 03/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 1.76 | 0 | 0 | 0
5386 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08708 | Retrofitting | Quotation for payment of service connection charges for Augmentation of Jotraghab w/s scheme. | 725/DW/22-23 | 03/11/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 0.33 | 0 | 0 | 0
5387 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08708 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of JOTRAGHAB Piped Water Supply Scheme at (JOTRAGHAB, RADHABALLAB BATI, KHANPUR, JOTKRISHTAI) Mouza under Jamalpur Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 382/BWD | 31/01/2023 | 30 | KAUSHIK RAY | 21.55 | 21.31 | 98.87 | 100
5388 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08708 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of JOTRAGHAB Piped Water Supply Scheme at Jotraghab & Radhaballabbati Mouza), Jamalpur Block under Burdwan Division, PHE. Dte. | 2239/BWD | 02/05/2022 | 45 | MAJUMDER ENTERPRISE | 54.07 | 48.26 | 100 | 1
5389 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap connection (FHTC) by retrofitting within the command area of Jot Raghab Piped Water Supply Scheme at Jamalpur Block under Burdwan Division, P.H.E. DTE. , SM/08708 | Retrofitting | Restoration of concrete road ,construction of valve chamber of JOTRAGHAB Piped Water Supply Scheme and its adjoining mouzas within JAMALPUR block under Burdwan Division, PHE Dte. | 2738/BSD | 28/11/2023 | 30 | A R TRADERS | 0.96 | 0.92 | 100 | 100
5390 | PURBA BARDHAMAN | Burdwan Division | DEULIA PIPED WATER SUPPLY SCHEME , SM/14973 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 7.44 | 0 | 0 | 0
5391 | PURBA BARDHAMAN | Burdwan Division | DEULIA PIPED WATER SUPPLY SCHEME , SM/14973 | New | Material Requisition To Resource Division | 3981/BWD | 08/09/2023 | 0 | Resource Division | 44.04 | 0 | 0 | 0
5392 | PURBA BARDHAMAN | Burdwan Division | DEULIA PIPED WATER SUPPLY SCHEME , SM/14973 | New | Material Requisition To Resource Division | 5086/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
5393 | PURBA BARDHAMAN | Central Mechanical | DEULIA PIPED WATER SUPPLY SCHEME , SM/14973 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
5394 | PURBA BARDHAMAN | Burdwan Division | DEULIA PIPED WATER SUPPLY SCHEME , SM/14973 | New | Supply of 1 (one) No. Inspection Vehicle for different JJM Related Works as and when required including supply of driver and fuels (Minimum 8 Hours of duty) under Katwa Sub-Division within Burdwan Division, P.H.E. Dte. Consider 96.00 Km run per Day. | 22/KTS | 05/01/2024 | 70 | AJIT SAMANTA | 0.9 | 0.3 | 100 | 100
5395 | PURBA BARDHAMAN | Central Mechanical | DEULIA PIPED WATER SUPPLY SCHEME , SM/14973 | New | QUOTATION FOR NEW SERVICE CONNECTION AT DEULIA PWSS TW-1 | BP-2024-25-189 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.69 | 0 | 0 | 0
5396 | PURBA BARDHAMAN | Central Mechanical | DEULIA PIPED WATER SUPPLY SCHEME , SM/14973 | New | Quotation for new service connection at Deulia PWSS TW-2. | BP-2024-25-410 | 11/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.52 | 0 | 0 | 0
5397 | PURBA BARDHAMAN | Burdwan Division | DEULIA PIPED WATER SUPPLY SCHEME , SM/14973 | New | Different works related (sinking of Tube-wells, LDSs, Rising Mains, FHTCs, Construction of different capacity RCC OHRs each with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drains and internal pathways at different TW site) to DEULIA, GOBARDHANPUR, KHARIJA-KASHIGRAM & UNIATATARPUR Piped Water Supply Scheme under Mangolkote Block, District:- Purba-Bardhaman [NEW SCHEME] | 3491/BWD | 09/08/2023 | 1058 | POWER TOOLS & ENGINEERING | 1741.05 | 34.35 | 7.31 | 10
5398 | PURBA BARDHAMAN | Central Mechanical | DEULIA PIPED WATER SUPPLY SCHEME , SM/14973 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at DEULIA Water Supply Scheme [ Block- MONGOLKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4098/CMD | 29/08/2023 | 640 | CHOUDHURY ENTERPRISE | 28.94 | 0 | 0 | 43
5399 | PURBA BARDHAMAN | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME , SM/14740 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 10.1 | 0 | 0 | 0
5400 | PURBA BARDHAMAN | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME , SM/14740 | New | Material Requisition To Resource Division | 3994/BWD | 08/09/2023 | 0 | Resource Division | 12.51 | 0 | 0 | 0
5401 | PURBA BARDHAMAN | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME , SM/14740 | New | Material Requisition To Resource Division | 5059/BWD | 23/11/2023 | 0 | Resource Division | 20.46 | 0 | 0 | 0
5402 | PURBA BARDHAMAN | Central Mechanical | TATARPUR PIPED WATER SUPPLY SCHEME , SM/14740 | New | New service connection charges for Tatarpur PWSS TW-1 | BP-2023-24-271 | 15/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 38.7 | 0 | 0 | 0
5403 | PURBA BARDHAMAN | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME , SM/14740 | New | Continuation order for "Supply of one No. Diesel Driven Ambassador Car on hire basis for the office of the Assistant Engineer, Burdwan Sub-Division, PHE Dte for the period of 01.12.2023 to 31.05.2024 | 2751/BSD | 28/11/2023 | 183 | SK.ASFIA | 2.4 | 0.4 | 99.56 | 70
5404 | PURBA BARDHAMAN | Central Mechanical | TATARPUR PIPED WATER SUPPLY SCHEME , SM/14740 | New | New Service connection for Tatarpur W/S Scheme PH No.-II | BP-2023-24-309 | 30/12/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 9.61 | 0 | 0 | 0
5405 | PURBA BARDHAMAN | Central Mechanical | TATARPUR PIPED WATER SUPPLY SCHEME , SM/14740 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Tatarpur Water Supply Scheme [ Block- Memari-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3723/CMD | 08/08/2023 | 30 | M.S. ENTERPRISE | 30.11 | 0 | 0 | 95
5406 | PURBA BARDHAMAN | Burdwan Division | TATARPUR PIPED WATER SUPPLY SCHEME , SM/14740 | New | Restoration of concrete road by Cement concrete (mix 1:1.5:3), Providing balance FHTC, parallel pipeline, drainage system, boundary wall, Bridge, land development, Sluice valve chamber for smooth water supply of FHTC work for TATARPUR PWSS and its adjoining mouzas within MEMARI-I BLOCK under Burdwan Division, PHE Dte. | 479/BWD | 24/01/2025 | 90 | RANADHIR SINHA | 74.75 | 0 | 0 | 0
5407 | PURBA BARDHAMAN | Burdwan Division | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14906 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 4.69 | 0 | 0 | 0
5408 | PURBA BARDHAMAN | Burdwan Division | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14906 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 4.03 | 0 | 0 | 0
5409 | PURBA BARDHAMAN | Burdwan Division | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14906 | New | Land demarcation and preparation of sketch map for Haldi, Sultanpur, Berugram & Karail Piped W/S. Scheme (New Scheme) at different Blocks under JJM under Burdwan Division, PHE Dte. | 842/AE/HQ | 01/11/2023 | 15 | M/S S. CHOUDHURY | 0.33 | 0 | 0 | 100
5410 | PURBA BARDHAMAN | Central Mechanical | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14906 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at MALKITA & others water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2388/CMD | 02/08/2024 | 90 | ELECTRICAL & MECHANICAL ENGINEERING CORPORATION | 55.95 | 0 | 0 | 0
5411 | PURBA BARDHAMAN | Burdwan Division | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14906 | New | Material Requisition To Resource Division | 332/BWD | 24/01/2024 | 0 | Resource Division | 21.17 | 0 | 0 | 0
5412 | PURBA BARDHAMAN | Central Mechanical | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14906 | New | New service connection for HALDI PWSS TW 1. | BP-2023-24-523 | 09/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5 | 0 | 0 | 0
5413 | PURBA BARDHAMAN | Central Mechanical | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14906 | New | NEW SERVICE CONNECTION FOR HALDI PWSS | BP-2023-24-591 | 04/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.5 | 0 | 0 | 0
5414 | PURBA BARDHAMAN | Central Mechanical | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14906 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at Haldi Water Supply Scheme [ Block- Burdwan-1 ] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3996/CMD | 29/08/2023 | 30 | C.M. ENTERPRISE | 28.9 | 22.74 | 95.2 | 95
5415 | PURBA BARDHAMAN | Burdwan Division | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14906 | New | HALDI Single Village Scheme with sinking of Tube-well & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME] | 4734/BWD | 03/11/2023 | 456 | ANIRUDDHA FARUQUE | 50.21 | 32.71 | 57.88 | 90
5416 | PURBA BARDHAMAN | Burdwan Division | HALDI PIPED WATER SUPPLY SINGLE VILLAGE SCHEME , SM/14906 | New | HALDI Single Village Scheme with Rising main, LDS and FHTC work under Burdwan-I Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1120/BWD | 14/03/2024 | 382 | ANIRUDDHA FARUQUE | 64.85 | 30.1 | 46.42 | 75
5417 | PURBA BARDHAMAN | Burdwan Division | KUNDA PIPED WATER SUPPLY SCHEME , SM/14913 | New | Material Requisition To Resource Division | 1965/BWD | 26/04/2023 | 0 | Resource Division | 1.64 | 0 | 0 | 0
5418 | PURBA BARDHAMAN | Burdwan Division | KUNDA PIPED WATER SUPPLY SCHEME , SM/14913 | New | Material Requisition To Resource Division | 2155/BWD | 10/05/2023 | 0 | Resource Division | 12.34 | 0 | 0 | 0
5419 | PURBA BARDHAMAN | Central Mechanical | KUNDA PIPED WATER SUPPLY SCHEME , SM/14913 | New | New service connection charges of Kunda W/S Scheme TW-1 | BP-2023-24-34 | 26/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.56 | 0 | 0 | 0
5420 | PURBA BARDHAMAN | Central Mechanical | KUNDA PIPED WATER SUPPLY SCHEME , SM/14913 | New | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at KUNDA Water Supply Scheme [Block - MANGALKOTE] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2518/CMD | 02/06/2023 | 30 | M/S. S.R. ENTERPRISE | 21.04 | 9.94 | 47.26 | 40
5421 | PURBA BARDHAMAN | Central Mechanical | KUNDA PIPED WATER SUPPLY SCHEME , SM/14913 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jabagram & others water supply scheme under Mangalkote Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2590/CMD | 27/08/2024 | 90 | M/S SAJAHAN CHOWDHURY | 62.06 | 0 | 0 | 0
5422 | PURBA BARDHAMAN | Burdwan Division | KUNDA PIPED WATER SUPPLY SCHEME , SM/14913 | New | KUNDA Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at Brahmapur, Jartha village (J.L No -76, 75) under Mongolkote Block, District:- Purba-Bardhaman [NEW SCHEME]. | 1341/BWD | 22/03/2023 | 90 | KHEPIMA ENGINEERS CO. OPERATIVE SOCIETY LTD. | 57.05 | 56.83 | 100 | 60
5423 | PURBA BARDHAMAN | Burdwan Division | KUNDA PIPED WATER SUPPLY SCHEME , SM/14913 | New | KUNDA Piped Water Supply Scheme with balance LDS and FHTC at Kunda village, J.L No- 74 under Mongolkote Block, District:- Purba-Bardhaman. [NEW SCHEME]. | 2232/BWD | 16/05/2023 | 90 | ASMA ENTERPRISE | 32.47 | 32.16 | 100 | 35
5424 | PURBA BARDHAMAN | Burdwan Division | KUNDA PIPED WATER SUPPLY SCHEME , SM/14913 | New | Material Requisition To Resource Division | 302/BWD | 24/01/2024 | 0 | Resource Division | 14.25 | 0 | 0 | 0
5425 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B , SM/08699 | Retrofitting | Extension of pipeline for Chhotobainan water supply scheme at Pahalanpur and Rupsara village within Raina-II Block under Burdwan Division, PHE Dte.[Gr.-C] | 1119/BSD | 24/08/2021 | 45 | BOSE ENTERPRISE | 4.67 | 2.43 | 100 | 1
5426 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B , SM/08699 | Retrofitting | Quotation of new connection charges of Chhotobainan water supply scheme under Burdwan Division, PHE Dte. [Application No.-5003481960, Ref ID-503178571], | 709/DW/22-23 | 21/10/2022 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION COMPANY LTD. | 3.37 | 0 | 0 | 0
5427 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B , SM/08699 | Retrofitting | Supply of materials for different water supply scheme under Burdwan Division, PHE Dte. |  | 21/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
5428 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B , SM/08699 | Retrofitting | Payment for supply of materials for different water supply scheme under Burdwan Division, PHE Dte. | 934/DW | 31/01/2022 | 0 | EXECUTIVE ENGINEER, RESOURCES DIVISION, P.H.E. DTE. | 617.98 | 0 | 0 | 0
5429 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B , SM/08699 | Retrofitting | Extension of pipeline with FHTC for CHHOTOBAINAN Piped Water Supply Scheme (Akina (P), Pahalanpur, Dakshin Gopalpur, Bajekumarpur, Binodpur, Momrejpur village) within Raina II Block under Burdwan Division, PHE. Dte. | 2163/BWD | 26/04/2022 | 45 | BRINDABAN KONAR | 71.69 | 56.07 | 78.21 | 1
5430 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B , SM/08699 | Retrofitting | Providing leftout water tap connection in different villages for 100% coverage to make it Sajal Gram from existing distribution system within scheme jurisdiction of different Piped Water Supply Schemes within Raina ¿ II Block under Burdwan Division, PHE. Dte. | 269/BWD | 14/01/2022 | 30 | PRONAB KUMAR DEY | 6.99 | 0 | 0 | 1
5431 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B , SM/08699 | Retrofitting | Sinking of additional 250 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for CHHOTOBAINAN Piped Water Supply Scheme, Block - Raina - II, Dist - Purba Bardhaman under Burdwan Division, PHE Dte. | 2233/BWD | 29/04/2022 | 30 | J. K. CORPORATION | 10.76 | 9.72 | 100 | 1
5432 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B , SM/08699 | Retrofitting | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at 3rd Tube Well Site (Baje Kumarpur) to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17(Size 3.60 mtr x 3.00 mtr room) for Chhotobainan its Adjoining Mouza W/S Scheme, block -Raina-II within Burdwan Sub-Division, PHE Dte. Gr.B. | 1526/BSD | 05/09/2022 | 60 | BRINDABAN KONAR | 3.03 | 2.6 | 100 | 1
5433 | PURBA BARDHAMAN | Burdwan Division | Providing Functional House hold Tap Connection (FHTC) by retrofitting at Akhina , Baje Kowarpur, Binodpur, Dakshin Gopalpur, Dakshin Mohanpur and Pahalanpur mouzas within the command area of Chhotobainan piped Water Supply Scheme at Raina-II Block under B , SM/08699 | Retrofitting | Material Requisition To Resource Division | 424/BWD | 20/01/2022 | 0 | Resource Division | 5.5 | 0 | 0 | 0
5434 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF RAYAN (PART-II) PWSS , SM/16486 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1&2 at Augumentation of Rayan Part - 2 Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2595/CMD | 07/06/2023 | 30 | P.K. ENGINEERING | 24.2 | 0 | 0 | 0
5435 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF RAYAN (PART-II) PWSS , SM/16486 | Augmentation | New service connection charges for Aug. Rayan PWSS TW-1 | BP-2023-24-151 | 05/09/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 5.11 | 0 | 0 | 0
5436 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF RAYAN (PART-II) PWSS , SM/16486 | Augmentation | Augmentation of RAYAN (PART-II) Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 500 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under Burdwan -I Block, District:- Purba-Bardhaman. | 2377/BWD | 25/06/2024 | 270 | MATRI ENTERPRISE | 697.52 | 0 | 0 | 0
5437 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF RAYAN (PART-II) PWSS , SM/16486 | Augmentation | Route Survey & Preparation of DPR for RAYAN -PART-II W/S Scheme under Burdwan-I Block under Burdwan Sub-Division under Burdwan Division PHE Dte. | 2585/BSD | 26/11/2024 | 45 | APEX ENGINEERING | 2.95 | 0 | 0 | 0
5438 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF RAYAN (PART-II) PWSS , SM/16486 | Augmentation | Material Requisition To Resource Division | 4101/BWD | 25/11/2024 | 0 | Resource Division | 9.24 | 0 | 0 | 0
5439 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR , SM/15187 | Augmentation | Construction of 3.60 mtr x 3.0 mtr size Pump House cum chlorine room with sanitary and water supply arrangement at to departmental drawing for RAMKRISHNAPUR Water Supply Scheme within Burdwan Division, PHE Dte. Dist.-Purba Bardhaman. | 4821/BWD | 08/11/2023 | 60 | SK BADIUZZAMAL | 4.32 | 0 | 0 | 0
5440 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR , SM/15187 | Augmentation | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of RAMKRISHNAPUR Piped Water Supply Scheme within Raina I Block of Burdwan Sub-Division under Burdwan Division, PHE Dte. | 1730/BWD | 13/04/2023 | 60 | SUPRIYA RAY | 40.13 | 20.84 | 51.93 | 45
5441 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR , SM/15187 | Augmentation | Designing, Making and Erection of Sign Board for SAJAL GRAM in Khemta Village, Raina - I Block within Ramkrishnapur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 877/AE/HQ | 07/11/2023 | 30 | PAPRI HAZRA | 0.76 | 0.72 | 100 | 100
5442 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR , SM/15187 | Augmentation | Preparation and Submission of DPR for Augmentation of Ramkrishnapur PWSS under Raina-I Development Block under Burdwan Division, P.H.E Dte (2nd Call) | 2972/BSD | 20/12/2023 | 15 | GEO-SOLUTION | 0.78 | 0.78 | 100 | 100
5443 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR , SM/15187 | Augmentation | NEW SERVICE CONNECTION FOR RAMKRISHNAPUR (AUGMENTATION) PWSS TW 03 | BP-2024-25-57 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 3.52 | 0 | 0 | 0
5444 | PURBA BARDHAMAN | Central Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR , SM/15187 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Ramkrishnapur Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2599/CMD | 07/06/2023 | 680 | SOUVIK HALDER | 10.42 | 9.83 | 94.65 | 90
5445 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR , SM/15187 | Augmentation | Construction of switch rooms & Rising main at different TW site for RAMKRISHNAPUR Piped Water Supply Scheme under Raina - I Block, District:- Purba-Bardhaman under Burdwan Division, PHE. Dte. | 4163/BWD | 20/09/2023 | 469 | LAKSHMIKANTA DAS | 8.93 | 7.79 | 88.19 | 100
5446 | PURBA BARDHAMAN | Burdwan Division | AUGUMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR RAMKRISHNAPUR , SM/15187 | Augmentation | Sinking of 300 X 200mm dia Tube Well 150 mtr. Depth by D.R. Rig method using UPVC pipe (CD) and UPVC Deep Well Screen (RDS) for 4TH TW site of RAMKRISHNAPUR W/S Scheme under Raina - I Block within Burdwan Sub-Division, PHE Dte. | 2708/BWD | 08/06/2023 | 30 | M/S D. PALIT & CO. | 13.25 | 10.14 | 100 | 100
5447 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION BHALKI Z-I & Z-II PWSS , SM/15560 | Augmentation | New service connection charges for Bhalki PWSS TW-1 | BP-2024-25-298 | 17/09/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.63 | 0 | 0 | 0
5448 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION BHALKI Z-I & Z-II PWSS , SM/15560 | Augmentation | Quotation for new service connection at Bhalki Zone-I/Zone-II, Aug-1. PWSS | BP-2024-25-337 | 04/10/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.77 | 0 | 0 | 0
5449 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION BHALKI Z-I & Z-II PWSS , SM/15560 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of BHALKI (ZONE-I & II) [AUSGRAM-II] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4510/CMD | 06/10/2023 | 726 | C.M. ENTERPRISE | 24.42 | 3.11 | 12.74 | 50
5450 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION BHALKI Z-I & Z-II PWSS , SM/15560 | Augmentation | Aug. of BHALKI ZONE-I Piped Water Supply Scheme with Rising Main & Construction of 400 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation at Headwork TW site under Ausgram-II Block, District:- Purba-Bardhaman. | 474/BWD | 05/02/2024 | 510 | SK AFJAL RAHAMAN | 114.56 | 0 | 0 | 25
5451 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION BHALKI Z-I & Z-II PWSS , SM/15560 | Augmentation | Aug. of BHALKI ZONE-II Piped Water Supply Scheme with Rising Main & Construction of 200 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation at Headwork TW site under Ausgram-II Block, District:- Purba-Bardhaman. | 568/BWD | 08/02/2024 | 360 | SK ABDUL LALAN | 74.12 | 0 | 0 | 0
5452 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION BHALKI Z-I & Z-II PWSS , SM/15560 | Augmentation | Source Augmentation of BHALKI Zone-I & Zone-II Piped Water Supply Scheme [Tube Well, Pump House, Boundary Wall, Rising Main, FHTC, etc.], Block-Ausgram-II, Dist.- Purba Bardhaman, under Burdwan Division P.H.E. Dte. | 2273/BWD | 18/05/2023 | 713 | S.R. ENTERPRISE | 92.2 | 11.5 | 47.57 | 40
5453 | PURBA BARDHAMAN | Burdwan Division | GOPKHANJI PIPED WATER SUPPLY SCHEME , SM/15171 | New | Material Requisition To Resource Division | 1962/BWD | 25/04/2023 | 0 | Resource Division | 37.55 | 0 | 0 | 0
5454 | PURBA BARDHAMAN | Central Mechanical | GOPKHANJI PIPED WATER SUPPLY SCHEME , SM/15171 | New | New service connection charges for Gopkhanji PWSS TW-2 | BP-2023-24-100 | 03/08/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.87 | 0 | 0 | 0
5455 | PURBA BARDHAMAN | Central Mechanical | GOPKHANJI PIPED WATER SUPPLY SCHEME , SM/15171 | New | New service connection charges for Gopkhanji W/S Scheme TW-1 | BP-2023-24-39 | 27/06/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 4.65 | 0 | 0 | 0
5456 | PURBA BARDHAMAN | Burdwan Division | GOPKHANJI PIPED WATER SUPPLY SCHEME , SM/15171 | New | GOPKHANJI Piped Water Supply Scheme with sinking of Tube-well, LDS, Rising Main, FHTC, Construction of 250 cum capacity RCC OHR with 20.0 mtr. with Staging height including soil investigation & construction of switch rooms & boundary walls with gates and land development, drain and internal pathway at different TW site under KATWA -I Block, District:- Purba-Bardhaman [NEW SCHEME] | 1134/BWD | 13/03/2023 | 1237 | POWER TOOLS & ENGINEERING | 482.85 | 232.66 | 48.18 | 74
5457 | PURBA BARDHAMAN | Central Mechanical | GOPKHANJI PIPED WATER SUPPLY SCHEME , SM/15171 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
5458 | PURBA BARDHAMAN | Central Mechanical | GOPKHANJI PIPED WATER SUPPLY SCHEME , SM/15171 | New | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.-1 & 2 at GOPKHANJI Water Supply Scheme [ Block- KATWA-1] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2660/CMD | 16/06/2023 | 30 | JYOTY SOLAR POWER. | 26.98 | 21.81 | 100 | 100
5459 | PURBA BARDHAMAN | Central Mechanical | GOPKHANJI PIPED WATER SUPPLY SCHEME , SM/15171 | New | Supply and installation of Electro-Magnetic flow meter at HARIGRAM, KUCHUT & others water supply scheme under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 3103/CMD | 11/12/2024 | 60 | S DUTTA | 15.06 | 0 | 0 | 0
5460 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI , SM/15565 | Augmentation | Construction of Boundary wall at Head Works Site of LOHAI Water Supply scheme under RAINA-II Block of Burdwan Division, PHE Dte. (Length -190.00 Mtr, Col-60 Nos). | 2053/BWD | 04/05/2023 | 60 | S. MITRA & CO. | 20.43 | 0 | 0 | 0
5461 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI , SM/15565 | Augmentation | Supply & Installation of Submersible Pumping Machinery , Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 at Augumentation of Lohai Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 2592/CMD | 07/06/2023 | 30 | SOUVIK HALDER | 11.36 | 0 | 0 | 0
5462 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI , SM/15565 | Augmentation | Extension Pipeline with Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of LOHAI Piped Water Supply Scheme within Raina II Block of Burdwan Sub-Division under Burdwan Division, PHE Dte._2ND CALL | 2422/BWD | 30/05/2023 | 30 | JAI MAA DURGA & CO. | 19.37 | 5.31 | 27.41 | 50
5463 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI , SM/15565 | Augmentation | Preparation and Submission of DPR for Augmentation of Lohai PWSS under Raina-II Development Block under Burdwan Division, P.H.E Dte (2nd Call) | 2973/BSD | 20/12/2023 | 15 | MEASURE LAND | 0.78 | 0.78 | 100 | 100
5464 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR LOHAI , SM/15565 | Augmentation | Making illumination arrangement and mise works at LOHAI water supply scheme RAINA-II BLOCK under Central Mechanical Division P.H.E. Dte. Purba-Bardhaman. | 2953/CMD | 20/11/2024 | 60 | M/S GHOSH ENTERPRISE | 9.84 | 0 | 0 | 60
5465 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I , SM/15571 | Augmentation | Material Requisition To Resource Division | 3970/BWD | 08/09/2023 | 0 | Resource Division | 18.33 | 0 | 0 | 0
5466 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I , SM/15571 | Augmentation | Work order for "Route Survey & Preparation of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-I (Zone-1A) (SM/15571) under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-6) | 2081/KSD | 29/02/2024 | 45 | APEX ENGINEERING | 2.23 | 0 | 0 | 100
5467 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I , SM/15571 | Augmentation | Material Requisition To Resource Division | 202/BWD | 10/01/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
5468 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I , SM/15571 | Augmentation | Quotation for meter shifting at Purbasthali PWSS PH 1. | BP-2024-25-409 | 11/12/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.05 | 0 | 0 | 0
5469 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I , SM/15571 | Augmentation | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | 2296/BWD | 20/06/2024 | 616 | M/S DATTA ENTERPRISE | 579.85 | 0 | 0 | 2
5470 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I , SM/15571 | Augmentation | Supply and installation of disinfection arrangement (Gaseous Chlorination) and other works at different OHR sites of Aug. of Purbasthali Surface Water Based PWSS Zone-I under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 1031/CMD | 25/04/2025 | 30 | EASTERN INDIA SALES & SERVICE | 147.66 | 0 | 0 | 0
5471 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE I , SM/15571 | Augmentation | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
5472 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ruppur Piped Water Supply Scheme at Jamalpur Block , SM/07778 | Retrofitting | Extensionof pipe linefor providing functional house hold tap connection at Ruppur village(Habitation)of RUPPUR Piped Water Supply Scheme Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte".Gr.B. | 275/BSD | 15/02/2022 | 30 | SAMANTA CONSTRUCTION | 4.82 | 4.74 | 100 | 1
5473 | PURBA BARDHAMAN | Burdwan Division | Providing Functional Household Tap Connection (FHTC) by retrofitting within the command area of Ruppur Piped Water Supply Scheme at Jamalpur Block , SM/07778 | Retrofitting | Providing Functional Household Tap Connection (FHTC) from existing distribution system within the command area of Ruppur Piped Water Supply Scheme at Ruppur Village (6 Nos. habitations), Biswambharpur Village & Dhuluk Village (6 Nos. habitations) Jamalpur Block under Burdwan Division, PHE Dte. | 3446/BWD | 29/06/2021 | 60 | NATIONAL CONSTRUCTION | 87.06 | 84.9 | 100 | 1
5474 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV , SM/16307 | Augmentation | Material Requisition To Resource Division | 3968/BWD | 08/09/2023 | 0 | Resource Division | 28.36 | 0 | 0 | 0
5475 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV , SM/16307 | Augmentation | Work Order for "Route Survey & Preparation of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-IV (Zone-IV B) (SM/16307) under Kalna Sub-Division under Burdwan Division, PHE Dte." Sl-3 | 2071/KSD | 29/02/2024 | 45 | APEX ENGINEERING | 2.53 | 0 | 0 | 100
5476 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV , SM/16307 | Augmentation | Work order for "Route Survey & Preparation of DPR for Augmentation of Purbasthali Surface Water Based PWSS Zone-IV (Zone-IV A) (SM/16307) under Kalna Sub-Division under Burdwan Division, PHE Dte." (SL-5) | 2080/KSD | 29/02/2024 | 45 | APEX ENGINEERING | 2.27 | 0 | 0 | 100
5477 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV , SM/16307 | Augmentation | Material Requisition To Resource Division | 203/BWD | 10/01/2024 | 0 | Resource Division | 6.16 | 0 | 0 | 0
5478 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV , SM/16307 | Augmentation | Different types of works involve in connection with Augmentation of KRISHNABATI (SM/07827), PURBASTHLI (SM/07866), SINHARI (SM/09716) & SURFACE based W/S Scheme (SM/15571) Piped water supply scheme under Purbasthali-II Block, Kalna Sub-Division, PHE Dte. | 2296/BWD | 20/06/2024 | 616 | M/S DATTA ENTERPRISE | 579.85 | 0 | 0 | 2
5479 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF PURBASTHALI SURFACE WATER BASED PWSS ZONE IV , SM/16307 | Augmentation | Supply & Laying of 300mm Dia M.S.E.R.W Pipe including Jack Pushing along with other allied work in connection with different Augmentation & New [(SM/18439, SM/14437, SM/14435, SM/07805, SM/14440, SM/15571, SM/08030, SM/16014, SM/15588, SM/16298 & SM/16307)] under Kalna Sub-Division under Burdwan Division, PHE Dte. | 608/BWD | 11/02/2025 | 361 | MANASH GHOSH | 1209.62 | 0 | 0 | 51
5480 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF RAHATPUR PIPED WATER SUPPLY SCHEME , SM/16306 | Augmentation | Different Types of work involved in connection with Augmentation of RAHATPUR (SM/16306) & LAKSHMANPUR (SM/13493) Piped water supply scheme within Kalna Sub-Division under Burdwan Division, PHE Dte. | 2069/BWD | 07/06/2024 | 240 | SAIKAT RAY | 213.73 | 0 | 0 | 2
5481 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF RAHATPUR PIPED WATER SUPPLY SCHEME , SM/16306 | Augmentation | Augmentation of RAHATPUR PWSS to accommodate FHTC, Laying Distribution System, Laying Rising Main, under Jal Jeevan Mission of Purbasthali - I Block, Purba Burdwan District under Burdwan Division, PHE. Dte. | 2114/BWD | 10/05/2023 | 60 | BARDHAMAN AQUA ENGINEERING | 18.67 | 17.56 | 100 | 100
5482 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF RAHATPUR PIPED WATER SUPPLY SCHEME , SM/16306 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of RAHATPUR[PURBASTHALI-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 4474/CMD | 05/10/2023 | 580 | S.K. ELECTRICALS | 23.71 | 0 | 0 | 100
5483 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR , SM/15722 | Augmentation | Preparation and Submission of DPR for Augmentation of Gobindapur PWSS under Memari-I Development Block under Burdwan Division, P.H.E Dte.[2nd Call] | 1529/BSD | 17/07/2023 | 15 | CARTO | 0.78 | 0.77 | 100 | 100
5484 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR , SM/15722 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination System and Internal House Wiring for Tube well No.- 4 at Augmentation of GOBINDAPUR Water Supply Scheme [BLOCK- MEMARI-I] under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 1538/CMD | 05/03/2024 | 60 | BEHERA ENTERPRISE | 12.33 | 0 | 0 | 0
5485 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR , SM/15722 | Augmentation | Extension of PVC water supply line for GOBINDAPUR and its adjoining Mouza W/S Scheme, Block-Memari-I within Burdwan Sub-Division, PHE Dte. | 3920/BWD | 05/09/2023 | 938 | J K CORPORATION | 27.92 | 23.56 | 84.37 | 98
5486 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF GROUND WATER BASED PIPE WATER SUPPLY SCHEME FOR GOBINDAPUR , SM/15722 | Augmentation | Designing, making and erection of Sign Board for SWAJAL GRAM in Ichhabacha village of Memari-I Block under Gobindapur Piped Water Supply Scheme within Burdwan Sub-Division under Burdwan Division,PHE Dte(5 nos Board) | 2338/BSD | 21/08/2025 | 10 | RAJ-N-MAHARAJ MANPOWER & SECURITY SOLUTIONS | 0.72 | 0 | 0 | 0
5487 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) , SM/18112 | Augmentation | Construction of Pump House cum chlorine room without sanitary and water supply arrangement at Tube Well Site to departmental drawing no-PHE/BD/P.H/DRG/02/DEC-17 (Size 3.60 mtr x 3.00 mtr room) for TALIT its Adjoining Mouza W/S Scheme, Block -Bardhaman-I within Burdwan Sub-Division, PHE Dte. (Mouza- TALIT) | 500/BSD | 21/03/2023 | 45 | MAHAKE CONTRACTOR & GENERAL ORDER SUPPLIERS | 3.16 | 2.59 | 100 | 100
5488 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) , SM/18112 | Augmentation | New service connection charges for Aug. Talit-Simdal PWSS TW-3 | BP-2023-24-58 | 17/07/2023 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.36 | 0 | 0 | 0
5489 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) , SM/18112 | Augmentation | Illumination arrangement & different electro-mechanical works at TALIT SIMDAL water supply scheme under Bardhaman-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman. | 2957/CMD | 20/11/2024 | 60 | SUDIKSHA CONSTRUCTION | 17.91 | 0 | 0 | 0
5490 | PURBA BARDHAMAN | Central Mechanical | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) , SM/18112 | Augmentation | Supply & Installation of Submersible Pumping Machinery, Voltage Stabilizer, Chlorination system and internal House wiring for Tube well no.- 1 & 2 at Augmentation of TALIT SIMDAL( Part-B)[BURDWAN-I] Water Supply Scheme under CMD, PHE Dte., Dist.- Purba-Bardhaman. | 3900/CMD | 18/08/2023 | 30 | CINZANO | 22.41 | 10.54 | 47.03 | 100
5491 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) , SM/18112 | Augmentation | Balance Work for extension of pipe lines to provide FHTC With Sinking of Tub well , Construction of pump house with Boundary wall & other related work for TALIT-SIMDAL (SM/18112), NABABHAT (SM-15166) and DEWANDIGHI-MIRJAPUR (SM/09494) PWSS under Burdwan Sub-Div., Block -Bwn-1, under Burdwan Division PHE Dte. | 793/BWD | 03/03/2025 | 120 | M/S S.S. ENTERPRISE | 227.66 | 0 | 0 | 0
5492 | PURBA BARDHAMAN | Burdwan Division | AUGMENTATION OF TALIT-SIMDAL PWSS (PART-B) , SM/18112 | Augmentation | 150MM DI bypass pipeline at KHETIA mouza for smooth water supply for FHTC under KHETIA & Talit Simdal pwss within Bardhaman- I block under Burdwan Division PHE DTE. | 111/BSD | 16/01/2025 | 30 | ROY CONSTRUCTION | 4.77 | 0 | 0 | 100
5493 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman , SM/17188 | Solarisation | Quotation for Solar power plant at Tendul PWSS (Solar). | BP-2024-25-209 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
5494 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman , SM/17188 | Solarisation | Application for Solar power plant at Sasinara Zone-I, TW 1 | BP-2024-25-233 | 30/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
5495 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman , SM/17188 | Solarisation | Application fees for connectivity of solar plant metering system at Kaithan W/W No.-1 Sadarghat | BP-2024-25-185 | 08/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
5496 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman , SM/17188 | Solarisation | Quotation for load enhancement of Mugura PWSS (Solar) | BP-2024-25-123 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.2 | 0 | 0 | 0
5497 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman , SM/17188 | Solarisation | Quotation for Solar power plant at NATU PWSS (Solar). | BP-2024-25-210 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
5498 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman , SM/17188 | Solarisation | Electric quotation for installation of Solar Power plant at Sasinara W/S Zone-I | BP-2024-25-153 | 21/06/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
5499 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman , SM/17188 | Solarisation | Quotation for load enhancement of Natu PWSS (Solar) | BP-2024-25-124 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.21 | 0 | 0 | 0
5500 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman , SM/17188 | Solarisation | New solar connection for Patuli PWSS . | BP-2023-24-575 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.32 | 0 | 0 | 0
5501 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman , SM/17188 | Solarisation | Quotation for load enhancement of Tendual PWSS (Solar) | BP-2024-25-125 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.33 | 0 | 0 | 0
5502 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman , SM/17188 | Solarisation | New solar connection for Parulia PWSS . | BP-2023-24-576 | 27/02/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.31 | 0 | 0 | 0
5503 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman , SM/17188 | Solarisation | Quotation for for application fee for new smart export import meter for a new solar plant at Khandaghosh PH-I PWSS (Solar) | BP-2024-25-122 | 29/05/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
5504 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman , SM/17188 | Solarisation | Quotation for solar power plant at Mugura PWSS. | BP-2024-25-211 | 18/07/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.01 | 0 | 0 | 0
5505 | PURBA BARDHAMAN | Central Mechanical | Solarisation of WBSEDCL energised electrical installation at PWSS at different Blocks under Central Mechanical Division,PHED District Purba Bardhaman , SM/17188 | Solarisation | Solarisation of WBSEDCL energised electrical installations of PWSS of different Blocks in the district Purba Bardhaman under Central Mechanical Division, PHE Dte. | 2693/CMD | 23/06/2023 | 183 | A K INDUSTRIES | 203.81 | 197.82 | 97.06 | 95
5506 | PURBA BARDHAMAN | Burdwan Division | NANAGAR PIPED WATER SUPPLY SCHEME , SM/18479 | New | Material Requisition To Resource Division | 2197/BWD | 12/05/2023 | 0 | Resource Division | 11.62 | 0 | 0 | 0
5507 | PURBA BARDHAMAN | Burdwan Division | NANAGAR PIPED WATER SUPPLY SCHEME , SM/18479 | New | Material Requisition To Resource Division | 4935/BWD | 10/11/2023 | 0 | Resource Division | 56.21 | 0 | 0 | 0
5508 | PURBA BARDHAMAN | Central Mechanical | NANAGAR PIPED WATER SUPPLY SCHEME , SM/18479 | New | Installation of two tank chlorination system, Yard lighting arrangement & allied works at Jajigram & others water supply scheme under Katwa-I Block under Central Mechanical Division, P.H.E. Dte., Dist.- Purba Bardhaman | 2399/CMD | 02/08/2024 | 90 | SUBRATA BHADRA | 55.16 | 0 | 0 | 0
5509 | PURBA BARDHAMAN | Burdwan Division | NANAGAR PIPED WATER SUPPLY SCHEME , SM/18479 | New | Balance work of OHR, construction Concrete Road, Functional Household Tap Connection, Road restoration etc. for Nanagar PWSS, Srikhanda PWSS, under KATWA -I Block under Katwa Sub-Divn under Burdwan Division, PHE Dte. District:- Purba-Bardhaman. | 3655/BWD | 21/10/2024 | 120 | HAMID SK | 121.69 | 0 | 0 | 0
5510 | PURBA BARDHAMAN | Central Mechanical | NANAGAR PIPED WATER SUPPLY SCHEME , SM/18479 | New | ADDITIONAL QUOTATION NEW SERVICE CONNECTION FOR NANAGAR PWSS TW -1. | BP-2023-24-644 | 15/03/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 1.02 | 0 | 0 | 0
5511 | PURBA BARDHAMAN | Central Mechanical | NANAGAR PIPED WATER SUPPLY SCHEME , SM/18479 | New | NEW SERVICE CONNECTION FOR NANAGAR PWSS TW-2 | BP-2024-25-59 | 26/04/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 8.11 | 0 | 0 | 0
5512 | PURBA BARDHAMAN | Central Mechanical | NANAGAR PIPED WATER SUPPLY SCHEME , SM/18479 | New | New service connection for NANAGAR PWSS PH-1. | BP-2023-24-416 | 19/01/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 2.83 | 0 | 0 | 0
5513 | PURBA BARDHAMAN | Central Mechanical | NANAGAR PIPED WATER SUPPLY SCHEME , SM/18479 | New | Second time additional quotation for Nanagar PWSS TW-1 | BP-2024-25-267 | 20/08/2024 | 0 | WEST BENGAL STATE ELECTRICITY DISTRIBUTION CO. LTD. (WBSEDCL) | 0.34 | 0 | 0 | 0
5514 | PURBA BARDHAMAN | Burdwan Division | Regular Monitoring of Drinking Water Testing Laboratories Related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19288 | Support-WQMSP | Continuation work order for Maintenance in Ketugram Sub District Water Testing Laboratory within Katwa sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [01.08.2025 to 31.03.2026] | 1772/KTS | 31/07/2025 | 243 | JAGADHATRI CONSTRUCTION AND BUILDERS | 0.56 | 0 | 0 | 0
5515 | PURBA BARDHAMAN | Resource | Engagement of Implementation Support Agency (ISA) for Implementation of Community Mobilization and Capacity Building Activities under JJM Support Activities at Purba Barddhaman District. , SM/08992 | Support-M&E | Engagement of lmplementation Support Agencies (lSAs) under JJM/ Jal Swapna in the districts of the Purba Bardhaman District. | 4736/RS | 22/08/2022 | 365 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 479.18 | 479.18 | 100 | 100
5516 | PURBA BARDHAMAN | Burdwan Division | IEC Activities related to judicious & safe use of drinking water, water conservation, water quality issues under JJM support activities , SM/19094 | Support-IEC | Organize one day Sub Division level orientation programme on JJM at involving PRI Functionaries and VWSC members at Purba Bardhaman and Conceptualization, design, implementing implementation of community sensitization / mobilization activities through Wall Painting on legal provision damage or illegal connection of PWSS; safe handling & storage of safe water Quality issues, water conservation and WASH related issues as per guideline of JJM at Purba Bardhaman under Burdwan Division, PHE Dte, Govt. of West Bengal. | 788/BWD | 27/02/2024 | 60 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 20.68 | 0 | 0 | 0
5517 | PURBA BARDHAMAN | Burdwan Division | IEC Activities related to judicious & safe use of drinking water, water conservation, water quality issues under JJM support activities , SM/19094 | Support-IEC | Organize IEC activities and Block Level Orientation programme on JJM at Purba Bardhaman and Flex tagging(Scheme information), Wall Painting & Har Ghar Jal Logo , Light Board; Conceptualization, design and implementing mass awareness generation through Tableau & Miking, Local News Channel, Printing & Supply Of IEC Banner & leaflets by dissemination of awareness generation IEC messages regarding JJM/FHTC, Prevention of illegal connection or damages of PWSS; safe handling & storage of safe water Quality issues, water conservation and wash related issues as per guideline of JJM in different place of Gram Panchayets. | 3056/BWD | 06/08/2024 | 60 | TUBGRAM GRAMMYAK UNNAYAN SAMITY | 30.4 | 30.4 | 100 | 100
5518 | PURBA BARDHAMAN | Burdwan Division | IEC Activities related to judicious & safe use of drinking water, water conservation, water quality issues under JJM support activities , SM/19094 | Support-IEC | Arrangement of different items required in DWSM (District Water and Sanitation Mission) meeting and training program on "Good Chlorine Practice & Analysis of Chlorine Demand & Chlorine available in disinfectants" under Burdwan Division, P.H.E. Dte. | 310/AE/HQ | 10/06/2024 | 15 | HAZRA COMPUTER | 0.58 | 0.58 | 100 | 100
5519 | PURBA BARDHAMAN | Burdwan Division | IEC Activities related to judicious & safe use of drinking water, water conservation, water quality issues under JJM support activities , SM/19094 | Support-IEC | Conceptualization, design and implementing mass awareness generation through Tableau and using Bus Panel advisement at Purba Bardhaman and printing & Supply 6 types of IEC leaflets & banner for distribution on FHTC, Provision on legal provision damage or illegal connection of PWSS; safe handling & storage of safe Water Quality issues, water conservation and WASH related issues as per guideline of JJM and preparation of web based Digital (A/V) awareness generation cum training material (Bengali) with voice over showcasing IEC and HRD initiative at Purba Bardhaman under Burdwan Division, PHE Dte, Govt. of West Bengal. | 787/BWD | 27/02/2024 | 360 | DEBNATH BROTHERS | 22.72 | 11.3 | 33.23 | 100
5520 | PURBA BARDHAMAN | Burdwan Division | Annual Procurement of Chemicals, Consumables and Glassware for water testing Laboratories. , SM/06624 | Support-WQMSP | Procurement of consumables for OMAS for different Sub-District Laboratories under Burdwan Division, PHE Dte. [Gr.-A] | 1265/AE/HQ | 26/02/2021 | 7 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT LTD. | 4.72 | 9.44 | 200 | 0
5521 | PURBA BARDHAMAN | Burdwan Division | Annual Procurement of Chemicals, Consumables and Glassware for water testing Laboratories. , SM/06624 | Support-WQMSP | Supply & Delivery of Chemicals, reagents and consumables for 14 (Fourteen) Nos. laboratories under Burdwan Division, PHE Dte. (Tr No.-212/BWD/20-21) | 3362/BWD | 21/09/2020 | 20 | NATURAL RESOURCES CONSORTIUM | 25.22 | 50.45 | 200 | 0
5522 | PURBA BARDHAMAN | Burdwan Division | Annual Procurement of Chemicals, Consumables and Glassware for water testing Laboratories. , SM/06624 | Support-WQMSP | Supply & Delivery of Chemicals, reagents and consumables for 14 (Fourteen) laboratories under Burdwan Division, P.H.E. Dte. | 3468/BWD | 29/06/2021 | 20 | NATURAL RESOURCES CONSORTIUM | 22.49 | 12.69 | 100 | 0
5523 | PURBA BARDHAMAN | Burdwan Division | Annual Procurement of Chemicals, Consumables and Glassware for water testing Laboratories. , SM/06624 | Support-WQMSP | Supply & delivery of Residual Chlorine Kit and DPD Tablet for 14 (Fourteen) Nos Laboratories under Burdwan Division, PHE Dte.[Gr.-B] | 1579/AE/HQ | 14/07/2021 | 7 | COMPUTER MEDIA | 4.22 | 8.43 | 200 | 0
5524 | PURBA BARDHAMAN | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. , SM/11993 | Support-M&E | Preparation & Submission of DPR for New Water Supply Scheme under JAMALPUR Development Block under Burdwan Division, P.H.E. Dte. [Gr. A] | 3901/BWD | 08/09/2022 | 45 | APEX ENGINEERING | 8.83 | 6.18 | 70 | 0
5525 | PURBA BARDHAMAN | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. , SM/11993 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Mongalkote Dev. Block under Katwa Sub-Division under Purba Bardhaman. | 3931/BWD | 09/09/2022 | 60 | RUDRABHISHEK ENTERPRISES LIMITED | 90 | 88.45 | 98.28 | 0
5526 | PURBA BARDHAMAN | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. , SM/11993 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW, PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Ausgram II, Galsi I & Bhatar Dev. Block under Durgapur (Burdwan North) Sub-Division under Purba Bardhaman. | 3825/BWD | 02/09/2022 | 60 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 225 | 221.17 | 100 | 0
5527 | PURBA BARDHAMAN | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. , SM/11993 | Support-M&E | Preparation & Submission of DPR for New Water Supply Scheme under KETUGRAM - I Development Block under Burdwan Division, P.H.E. Dte. [Gr. A] | 3972/BWD | 13/09/2022 | 45 | ENVIROTECH SOLUTIONS | 60.07 | 54.11 | 100 | 0
5528 | PURBA BARDHAMAN | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. , SM/11993 | Support-M&E | Preparation & Submission of DPR for New Water Supply Scheme under KETUGRAM - II Development Block under Burdwan Division, P.H.E. Dte. [Gr. B] | 3988/BWD | 13/09/2022 | 45 | ENVIROTECH SOLUTIONS | 30.03 | 26.56 | 100 | 0
5529 | PURBA BARDHAMAN | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. , SM/11993 | Support-M&E | Work Order for Service for land acquisition for different PWSS under JJM of Purbasthali-I block under Kalna Sub-Division, PHE Dte. | 519/KSD | 06/06/2023 | 366 | PARTHA PRATIM ACHARYA | 0.81 | 0.81 | 100 | 100
5530 | PURBA BARDHAMAN | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. , SM/11993 | Support-M&E | Work Order for Service for land acquisition for different PWSS under JJM of Monteswar block under Kalna Sub-Division, PHE Dte. | 535/KSD | 07/06/2023 | 366 | PARTHA PRATIM ACHARYA | 0.81 | 0.33 | 40 | 42
5531 | PURBA BARDHAMAN | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. , SM/11993 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW, PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Burdwan II, Khandaghosh, Memari I & Raina II Dev. Block, under Burdwan Sub-Division under Purba Bardhaman. | 3841/BWD | 05/09/2022 | 60 | MARS PLANNING AND ENGINEERING SERVICES PVT LTD. | 300 | 270.91 | 100 | 100
5532 | PURBA BARDHAMAN | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. , SM/11993 | Support-M&E | Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Kalna I & Monteswar Dev. Block under Kalna Sub-Division under Purba Bardhaman. | 3956/BWD | 09/09/2022 | 60 | VENKATESHWARA ENTERPRISES | 180 | 179.89 | 100 | 100
5533 | PURBA BARDHAMAN | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. , SM/11993 | Support-M&E | Preparation & Submission of DPR for New Water Supply Scheme under PURBASTHALI - I Development Block under Burdwan Division, P.H.E. Dte. [Gr. C] | 4056/BWD | 15/09/2022 | 45 | ECO CARE | 60.07 | 60.04 | 100 | 100
5534 | PURBA BARDHAMAN | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. , SM/11993 | Support-M&E | Preparation & Submission of DPR for New Water Supply Scheme under PURBASTHALI - II Development Block under Burdwan Division, P.H.E. Dte. [Gr. D] | 4079/BWD | 16/09/2022 | 45 | ECO CARE | 6.76 | 5.56 | 100 | 100
5535 | PURBA BARDHAMAN | Burdwan Division | Consultancy Service for making DPR to implement New Piped Water Supply Scheme (MVS) within the Purba Bardhaman District. , SM/11993 | Support-M&E | Continuation Work for Preparation & Submission of DPR for New Water Supply Scheme under KETUGRAM - I Development Block under Burdwan Division, P.H.E. Dte. | 4636/BWD | 17/10/2022 | 45 | ENVIROTECH SOLUTIONS | 17.27 | 17.17 | 100 | 100
5536 | PURBA BARDHAMAN | Central Mechanical | Procurement of Computer and Peripherals for the office use in Central Mechanical Division, Central Mechanical Sub-Division, Bardhaman Mechanical Sub-Division(Drilling) PHE.Dte. , SM/13017 | Support-MIS | Procurement of Computer and peripherals for office use of Central Mechanical Division, PHE.Dte. | 29 | 18/01/2023 | 0 | IONET | 13.47 | 0 | 0 | 0
5537 | PURBA BARDHAMAN | Burdwan Division | ADDITIONAL COST TOWARDS CONSULTANCY SERVICE FOR MAKING DPR TO IMPLEMENT NEW PIPED WATER SUPPLY SCHEME (MVS) WITHIN THE PURBA BARDHAMAN DISTRICT , SM/14441 | Support-M&E | Continuation work for Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Mongalkote Dev. Block under Katwa Sub-Division under Purba Bardhaman. | 341/BWD | 27/01/2023 | 60 | RUDRABHISHEK ENTERPRISES LIMITED | 65 | 60.65 | 93.31 | 0
5538 | PURBA BARDHAMAN | Burdwan Division | ADDITIONAL COST TOWARDS CONSULTANCY SERVICE FOR MAKING DPR TO IMPLEMENT NEW PIPED WATER SUPPLY SCHEME (MVS) WITHIN THE PURBA BARDHAMAN DISTRICT , SM/14441 | Support-M&E | Continuation work order for Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW, PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Ausgram I & II and Galsi I & II Dev. Block under Durgapur (Burdwan North) Sub-Division under Purba Bardhaman. | 333/BWD | 24/01/2023 | 60 | SRIJAN ECOLOGICAL UPLIFTMENT PVT LTD. | 170 | 169.01 | 100 | 0
5539 | PURBA BARDHAMAN | Burdwan Division | ADDITIONAL COST TOWARDS CONSULTANCY SERVICE FOR MAKING DPR TO IMPLEMENT NEW PIPED WATER SUPPLY SCHEME (MVS) WITHIN THE PURBA BARDHAMAN DISTRICT , SM/14441 | Support-M&E | Continuation work for Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW, PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Burdwan ¿ I, Memari ¿ II & Raina ¿ I Dev. Block, under Burdwan Sub-Division under Purba Bardhaman. | 334/BWD | 24/01/2023 | 60 | MARS PLANNING AND ENGINEERING SERVICES PVT LTD. | 215 | 214.14 | 100 | 100
5540 | PURBA BARDHAMAN | Burdwan Division | ADDITIONAL COST TOWARDS CONSULTANCY SERVICE FOR MAKING DPR TO IMPLEMENT NEW PIPED WATER SUPPLY SCHEME (MVS) WITHIN THE PURBA BARDHAMAN DISTRICT , SM/14441 | Support-M&E | Continuation work for Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Katwa I & II Dev. Block under Katwa Sub-Division under Purba Bardhaman. | 325/BWD | 20/01/2023 | 60 | VENKATESHWARA ENTERPRISES | 175 | 169.73 | 100 | 100
5541 | PURBA BARDHAMAN | Burdwan Division | ADDITIONAL COST TOWARDS CONSULTANCY SERVICE FOR MAKING DPR TO IMPLEMENT NEW PIPED WATER SUPPLY SCHEME (MVS) WITHIN THE PURBA BARDHAMAN DISTRICT , SM/14441 | Support-M&E | Continuation work for Preparation of piped network system & design the same including Route Survey using DGPS & all related field work for technical data and JJM compliant data collection preparation and supply of Geo reference drawing (CAD-GIS) layout of plan of the zone wise command area of water distribution and transmission network (WD & TN) Showing all requisite design physical features including cost and estimate of different real component of PWSS like OHR, TW,PUMP HOUSE, B/W electronica component etc. including preparation and submission of DPR booklet of PWSS all complete in consultation with PHED Planning Wings and clearance from SLSSC including preparation of bid documents in different PWSS of uncovered area within Kalna II Dev. Block under Kalna Sub-Division under Purba Bardhaman. | 342/BWD | 27/01/2023 | 60 | VENKATESHWARA ENTERPRISES | 27 | 22.37 | 82.86 | 70
5542 | PURBA BARDHAMAN | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. , SM/08997 | Support-M&E | Survey and Collection of data through mobile application regarding availability of drinking water, sanitation facilities and other parameters in Primary & Upper Primary Schools, Anganwadi Centers under Katwa -I , Katwa- II , Ketugram-I, Ketugram-II and Mongalkote Block within Purba Bardhaman District under Katwa Sub-Division under Burdwan Division, PHE Dte (Sl No-1) | 314/A/KTS | 09/11/2020 | 100 | GHOSH CONSTRUCTION | 2.47 | 2.47 | 100 | 0
5543 | PURBA BARDHAMAN | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. , SM/08997 | Support-M&E | Survey and collection of data through mobile application regarding availability of drinking water, sanitation, facilities and other parameters in Primary & Upper Primary schools, Anganwari Centres under Burdwan-I, Burdwan-II, Raina-II, Memari-I, Memari-II, Jamalpur & Khandaghosh Block within Purba Bardhaman District under Burdwan Division, PHE Dte. | 1031/BSD | 13/11/2020 | 92 | ALAKA GHOSH | 3.27 | 2.34 | 100 | 0
5544 | PURBA BARDHAMAN | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. , SM/08997 | Support-M&E | Survey and collection of data through mobile application regarding availability of drinking water, sanitation facilities and other parameters in Primary & Upper Primary schools, Anganwari Centres under Kalna-I, Kalna-II, Purbasthali-I, Purbasthali-II and Monteswar Block within Purba Bardhaman District under Burdwan Division, PHE Dte. | 767/KSD | 27/11/2020 | 100 | SETH ENTERPRISE | 1.46 | 1.46 | 100 | 0
5545 | PURBA BARDHAMAN | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. , SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Samaspur Village, Monteswar Block within Lohana PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 829/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0.72 | 100 | 100
5546 | PURBA BARDHAMAN | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. , SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Takipur Village, Ausgram-I Block within Takipur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 824/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0.72 | 100 | 100
5547 | PURBA BARDHAMAN | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. , SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Chonari Village, Ausgram-I Block within Takipur PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 822/AE/HQ | 30/10/2023 | 30 | ISHAN CONSTRUCTION | 0.76 | 0.72 | 100 | 100
5548 | PURBA BARDHAMAN | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. , SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Jarul Village, Khandaghosh Block within Taraposh PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 868/AE/HQ | 07/11/2023 | 30 | PAPRI HAZRA | 0.76 | 0.72 | 100 | 100
5549 | PURBA BARDHAMAN | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. , SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Chalbalpur Village, Jamalpur Block within Chak Sanjadi PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 874/AE/HQ | 07/11/2023 | 30 | PAPRI HAZRA | 0.76 | 0.72 | 100 | 100
5550 | PURBA BARDHAMAN | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. , SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Paschim Memari Village, Memari - I Block within Nabagram PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 865/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 100 | 100
5551 | PURBA BARDHAMAN | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. , SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Pingur Village, Memari - I Block within Nabagram PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 864/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 100 | 100
5552 | PURBA BARDHAMAN | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. , SM/08997 | Support-M&E | Supply, fitting & fixing of Har Ghar Jal Logo and Wall painting of Scheme detailing of Nabagram & Kulingram Piped W/S. Scheme under Jamalpur Block under Burdwan Division, PHE. Dte. | 912/AE/HQ | 29/11/2023 | 10 | MANABSEBA PROKALPA & CONSTRUCTIONS | 1 | 1 | 100 | 100
5553 | PURBA BARDHAMAN | Burdwan Division | Survey and Water Sample Collection of Schools and Anganwari Centers through customised mobile application and data entry in IMIS within Purba Bardhaman District under Burdwan Division, PHE Dte. , SM/08997 | Support-M&E | Designing, Making and Erection of Sign Board for SAJAL GRAM in Konarpara Village, Memari - I Block within Nabagram PWSS under Burdwan Division, PHE Dte. (5 Nos Board) | 858/AE/HQ | 06/11/2023 | 30 | MANABSEBA PROKALPA & CONSTRUCTIONS | 0.75 | 0.72 | 100 | 100
5554 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for Supply & delivery of Chemicals for Arsenic test through AAS at District Laboratories under Burdwan Division PHE Dte. [Group : A] | 275/AE/HQ | 10/05/2022 | 7 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 3.09 | 0 | 0 | 0
5555 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Proposed extension, renovation and modification for NABL accreditation of SANKARI Sub District Laboratory under Burdwan Division P.H.E. Dte. Dist:Purba Bardhaman._2ND CALL. | 4930/BWD | 28/09/2021 | 45 | KAJAL MUKHERJEE | 5.84 | 5.94 | 100 | 0
5556 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) in 1 No. Sub District Laboratory within Durgapur Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/01/2022 to 30/04/2022] | 726/DSD | 22/12/2021 | 121 | CLIFFORD FACILITY SERVICES PVT.LTD. | 1.13 | 0.26 | 100 | 0
5557 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant)in 2 Sub District Laboratories within Burdwan Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman for the period from 01-01-2022 to 30-06-2022¿.Gr.C. | 1799/BSD | 31/12/2021 | 181 | CLIFFORD FACILITY SERVICES PVT.LTD. | 3.14 | 2.09 | 100 | 0
5558 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work for 'Operation & Maintenance of 08 (Eight) Nos. Sub District Laboratories in different Blocks under Burdwan Division, PHE Dte. (Period from 01.03.2022 to 31.08.2022)' [GROUP : A] | 111/AE/HQ | 28/02/2022 | 184 | COMPUTER MEDIA | 3.01 | 2.83 | 100 | 0
5559 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of laboratory personnels i.e. Chemist (One Person), Bacteriologist (One Person), Laboratory Assistant (One Person) , Sampling Assistant (One Person) and Computer Operator/Data Entry Operator (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman For the period from 01.03.2022 to 31.08.2022.Gr.C. | 360/BSD | 28/02/2022 | 6 | ALAKA GHOSH | 4.69 | 4.69 | 100 | 0
5560 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for Annual Maintenance Contract (AMC) for software up-gradation and other software related issues in existing computers, refilling of cartridge of the printers, replacement of battery of UPS in District, Sub-District and NGO Laboratories under Burdwan Division, PHE Dte.[Period from 01/09/2021 to 31/08/2022] | 1733/AE/HQ | 27/08/2021 | 365 | COMPUTER MEDIA | 1.96 | 0.98 | 100 | 0
5561 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of resource person to operate AAS at District Laboratory under Burdwan Division, PHE. Dte. [Period from 16.11.2021 to 15.05.2022]_Gr-A | 1903/AE/HQ | 16/11/2021 | 181 | ALAKA GHOSH | 0.79 | 0.79 | 100 | 0
5562 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for engagement of laboratory personnel (Sampling Assistant) in 7 Nos. Sub-District Laboratories under Burdwan Division, PHE Dte. [Period from 01/01/2022 to 30/06/2022] | 1961/AE/HQ | 28/12/2021 | 182 | COMPUTER MEDIA | 4.69 | 4.69 | 49.94 | 0
5563 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Providing service by assigning resource person for a period of 03 Months supervision of process of preparation for NABL recognition for Chemical Testing of portable water of Sub-District Level water quality laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereof for SANKARI Sub-District water Testing Laboratory under Burdwan Division, PHE Dte.[Gr.-A] | 1724/AE/HQ | 25/08/2021 | 15 | NATURAL RESOURCES CONSORTIUM | 4.83 | 4.83 | 100 | 0
5564 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Providing service by assigning resource person for a period of 03 Months supervision of process of preparation for NABL recognition for Chemical Testing of portable water of Sub-District Level water quality laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereof for SHAKTIGARH Sub-District water Testing Laboratory under Burdwan Division, PHE Dte.[Gr.-B] | 1723/AE/HQ | 25/08/2021 | 15 | NATURAL RESOURCES CONSORTIUM | 4.83 | 4.83 | 100 | 0
5565 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Maintenance charges of Burdwan District Laboratory under Burdwan Division PHE Dte. [Period from 01/08/2021 to 31/07/2022] | 983/BSD | 29/07/2021 | 365 | ALAKA GHOSH | 0.97 | 0.77 | 100 | 0
5566 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Supply & delivery of Chemicals for Arsenic test through AAS at District Laboratories under Burdwan Division PHE Dte. | 1578/AE/HQ | 14/07/2021 | 7 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 3.09 | 2.57 | 100 | 0
5567 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Providing service by assigning Resource person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District Level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereof for ANUKHAL Sub-District Water Testing Laboratory under Burdwan Divn., PHE. Dte. [Group : D] | 1726/AE/HQ | 25/08/2021 | 90 | LAXMI ENTERPRISE | 4.83 | 4.83 | 100 | 0
5568 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Providing service by assigning Resource person for a period of 3 months supervision of process of preparation for NABL recognition for Chemical Testing of potable water of Sub-District Level Water Quality Testing Laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereof for BANNABAGRAM Sub-District Water Testing Laboratory under Burdwan Divn., PHE. Dte. [Group : F] | 1721/AE/HQ | 25/08/2021 | 90 | LAXMI ENTERPRISE | 4.83 | 4.83 | 100 | 0
5569 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab Personnel (Chemist/Bacteriologist and Lab Assistant) For the month of April May & June'2022 under Burdwan division, PHE Dte. | 517/LAB/22-23 | 06/09/2022 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.99 | 0 | 0 | 0
5570 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Payment of NGO LAB Personnel (Chemist/Bacteriologist & Lab Assistant) for the month of August'22. | 795/LAB/22-23 | 24/11/2022 | 0 | SHASTRI SMRITI SANGHA | 0.31 | 0 | 0 | 0
5571 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab Personnel (Chemist/Bacteriologist and Lab Assistant) For the month of April May & June'2022 under Burdwan division, PHE Dte. | 515/LAB/22-23 | 06/09/2022 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.99 | 0 | 0 | 0
5572 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab Personnel (Chemist/Bacteriologist and Lab Assistant) For the month of April May & June'2022 under Burdwan division, PHE Dte. | 519/LAB/22-23 | 06/09/2022 | 0 | SHASTRI SMRITI SANGHA | 0.9 | 0 | 0 | 0
5573 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary bill of NGO Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) under Burdwan Division, PHE Dte. for the month of July'2022. | 719/LAB/22-23 | 28/10/2022 | 0 | SIDHU KANU GRAM UNNAYAN SAMITI | 0.33 | 0 | 0 | 0
5574 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Payment of NGO LAB Personnel (Chemist/Bacteriologist & Lab Assistant) for the month of August'22. | 794/LAB/22-23 | 24/11/2022 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.33 | 0 | 0 | 0
5575 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab Personnel (Chemist/Bacteriologist and Lab Assistant) For the month of April May & June'2022 under Burdwan division, PHE Dte. | 518/LAB/22-23 | 06/09/2022 | 0 | SIKSHA-NIKATAN | 0.75 | 0 | 0 | 0
5576 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary bill of NGO Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) under Burdwan Division, PHE Dte. for the month of July'2022. | 716/LAB/22-23 | 28/10/2022 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.33 | 0 | 0 | 0
5577 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary bill of NGO Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) under Burdwan Division, PHE Dte. for the month of July'2022. | 717/LAB/22-23 | 28/10/2022 | 0 | SHASTRI SMRITI SANGHA | 0.31 | 0 | 0 | 0
5578 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel (Chemist/Bacteriologist and Lab Assistant) of NGO managed laboratory for the month of September'2022. | 810/LAB/22-23 | 29/11/2022 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.33 | 0 | 0 | 0
5579 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel (Chemist/Bacteriologist and Lab Assistant) of NGO managed laboratory for the month of September'2022. | 811/LAB/22-23 | 29/11/2022 | 0 | SHASTRI SMRITI SANGHA | 0.31 | 0 | 0 | 0
5580 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab Personnel (Chemist/Bacteriologist and Lab Assistant) For the month of April May & June'2022 under Burdwan division, PHE Dte. | 516/LAB/22-23 | 06/09/2022 | 0 | SIDHU KANU GRAM UNNAYAN SAMITI | 0.99 | 0 | 0 | 0
5581 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary bill of NGO Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) under Burdwan Division, PHE Dte. for the month of July'2022. | 718/LAB/22-23 | 28/10/2022 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.33 | 0 | 0 | 0
5582 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel (Chemist/Bacteriologist and Lab Assistant) of NGO managed laboratory for the month of September'2022. | 809/LAB/22-23 | 29/11/2022 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.33 | 0 | 0 | 0
5583 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Payment of NGO LAB Personnel (Chemist/Bacteriologist & Lab Assistant) for the month of August'22. | 793/LAB/22-23 | 24/11/2022 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.33 | 0 | 0 | 0
5584 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Ganganandapur Sub District Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.01.2022 to 30.06.2022] | 1302/KSD | 31/12/2021 | 180 | CLIFFORD FACILITY SERVICES PVT.LTD. | 1.57 | 0 | 0 | 0
5585 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Anukhal Sub-District Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.01.2022 to 30.06.2022]. | 1301/KSD | 31/12/2021 | 180 | CLIFFORD FACILITY SERVICES PVT.LTD. | 1.57 | 0 | 0 | 0
5586 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Work Order for "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Parulia Sub District Water Testing Laboratory & Kamalnagar WTP laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.01.2023 to 31.01.2023]" | 1145/KSD | 30/12/2022 | 31 | SURATH DEY | 0.59 | 0.59 | 100 | 0
5587 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Work Order for "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Ganganandapur Sub-District Water Testing Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.01.2023 to 31.01.2023]" | 1149/KSD | 30/12/2022 | 31 | BUILD-TECH | 0.37 | 0.37 | 100 | 0
5588 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Parulia Sub District Water Testing Laboratory & Kamalnagar WTP laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.02.2023 to 28.02.2023]" | 71/B/KSD | 30/01/2023 | 28 | SURATH DEY | 0.59 | 0.59 | 100 | 0
5589 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Ganganandapur Sub-District Water Testing Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.02.2023 to 28.02.2023]" | 71/A/KSD | 30/01/2023 | 28 | BUILD-TECH | 0.37 | 0.37 | 100 | 0
5590 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for engagement of laboratory personnel i.e. AAS Operator (One Person) and Computer Operator/Data Entry Operator (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman, For the period from 01.03.2023 to 31.03.2023. | 337/BSD | 27/02/2023 | 31 | ALAKA GHOSH | 0.4 | 0.4 | 100 | 0
5591 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for engagement of laboratory personnel i.e. Chemist (One Person), Bacteriologist (One Person), Laboratory Assistant (One Person), Sampling Assistant (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman. For the period from 01.03.2023 to 31.03.2023. | 336/BSD | 27/02/2023 | 31 | ALAKA GHOSH | 0.84 | 0.84 | 100 | 0
5592 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Ganganandapur Sub-District Water Testing Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.04.2023 to 30.04.2023]" | 292/KSD | 31/03/2023 | 30 | BUILD-TECH | 0.37 | 0.37 | 100 | 0
5593 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Cotinuation work order for "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Anukhal Sub District Water Testing laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.03.2023 to 31.03.2023]" | 165/KSD | 27/02/2023 | 31 | ALAKA GHOSH | 0.37 | 0.37 | 100 | 0
5594 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for "Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Manteswar Sub District Water Testing Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.03.2023 to 31.03.2023]." | 166/KSD | 27/02/2023 | 31 | ALAKA GHOSH | 0.59 | 0.59 | 100 | 0
5595 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Parulia Sub District Water Testing Laboratory & Kamalnagar WTP laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.03.2023 to 31.03.2023]" | 168/KSD | 27/02/2023 | 31 | SURATH DEY | 0.59 | 0.59 | 100 | 0
5596 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant)in 2 Sub District Laboratories within Burdwan Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman for the period from 01-05-2023 to 31-05-2023 | 792/BSD | 28/04/2023 | 31 | CLIFFORD FACILITY SERVICES PVT.LTD. | 0.52 | 0 | 0 | 0
5597 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of laboratory personnel i.e. Chemist (One Person), AAS Operator (One person) Bacteriologist (One Person), Laboratory Assistant (One Person), Sampling Assistant (One Person) and Computer Operator/Data Entry Operator (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman. [Period for 6 (Six) Months i.e. 01.06.2023 to 30.11.2023]. | 2449/BWD | 31/05/2023 | 183 | ALAKA GHOSH | 7.4 | 7.41 | 100 | 100
5598 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Arrangement of drinking water supply in BONNABAGRAM Water Testing Laboratory by sinking of 75 Mtr. Deep 40 x 100 mm. dia., with PVC pipe, DWP Tube wells in the district of Purba Bardhaman under Burdwan Division, PHE. Dte. | 357/AE/HQ | 18/07/2023 | 30 | UDYOG CONSTRUCTION | 0.96 | 0 | 0 | 0
5599 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Parulia Sub District Laboratory & Kamalnagar WTP laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.07.2021 to 30.06.2022 (Sl No-1) | 564/KSD | 30/06/2021 | 365 | CLIFFORD FACILITY SERVICES PVT.LTD. | 4.93 | 1.64 | 100 | 0
5600 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for Engagement of resource person to operate AAS at District Laboratory under Burdwan Division, PHE. Dte. [Period from 16.05.2022 to 31.08.2022] [Gr. A] | 276/AE/HQ | 10/05/2022 | 108 | ALAKA GHOSH | 0.46 | 0.46 | 100 | 0
5601 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Supply of different laboratory equipment's at UPVC pipe Testing laboratory at Nababhat PHE Complex for monitoring and control over the quality of concrete of different water supply scheme under Burdwan Division, PHE Dte._2nd Call | 195/DSD | 04/04/2022 | 7 | MAUVE ENGINEERING AND SERVICES PVT LTD | 2.74 | 2.74 | 100 | 0
5602 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work for Engagement of laboratory personnel (Contractual) for smooth running of the uPVC pipe testing laboratory at Nababhat under Burdwan Division, PHE. Dte. [Period from 15.04.2022 to 14.09.2022]_Gr-A | 132/AE/HQ | 10/03/2022 | 6 | M/S ASHA CONSTRUCTION | 2.99 | 2.99 | 100 | 0
5603 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for engagement of laboratory personnel (Chemist/Bacteriologist and Lab Assistant) in Ganganandapur Sub-District Laboratory within Kalna Sub-Division under Burdwan Division, PHE Dte.[Period from 01/01/2022 to 30/06/2022] | 1302/KSD | 31/12/2021 | 181 | CLIFFORD FACILITY SERVICES PVT.LTD. | 1.57 | 1.05 | 80 | 0
5604 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for engagement of laboratory personnel (Chemist/Bacteriologist and Lab Assistant) in Anukhal Sub-District Laboratory within Kalna Sub-Division under Burdwan Division, PHE Dte.[Period from 01/01/2022 to 30/06/2022] | 1301/KSD | 31/12/2021 | 181 | CLIFFORD FACILITY SERVICES PVT.LTD. | 1.57 | 1.05 | 100 | 0
5605 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for engagement of laboratory personnel (Chemist/Bacteriologist and Lab Assistant) in 02 Nos. Sub-District laboratories within Head Quarters under Burdwan Division, PHE Dte. [Period from 01/01/2022 to 30/06/2022] | 1962/AE/HQ | 28/12/2021 | 182 | COMPUTER MEDIA | 3.14 | 3.14 | 100 | 0
5606 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of laboratory personnel (Sampling Assistant) in 7 Nos. Sub District Laboratories under Burdwan Division, P.H.E. Dte. [Period from 01.08.2022 to 31.12.2022] GROUP : B | 418/AE/HQ | 29/07/2022 | 153 | COMPUTER MEDIA | 3.92 | 3.92 | 100 | 0
5607 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work for Engagement of resource person to operate AAS at District Laboratory under Burdwan Division, PHE. Dte. [Period from 01.09.2022 to 30.09.2022] [Gr. A] | 457/AE/HQ | 31/08/2022 | 30 | ALAKA GHOSH | 0.13 | 0.13 | 100 | 0
5608 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Providing service by assigning resource person for a period of 03 Months supervision of process of preparation for NABL recognition for Chemical Testing of portable water of Sub-District Level water quality laboratory including supply, installation of a requisites for NABL recognition through NABL GLAP application for 11 mandatory parameters and training on procedures with documentation thereof for SATGACHIA Sub-District water Testing Laboratory under Burdwan Division, PHE Dte.[Gr.-C] | 1725/AE/HQ | 25/08/2021 | 15 | NATURAL RESOURCES CONSORTIUM | 4.83 | 4.83 | 100 | 0
5609 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) in 2 Sub District Laboratories within Burdwan Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman for the period from 01-07-2022 to 31-12-2022. Sl.No.69. | 1129/BSD | 30/06/2022 | 184 | CLIFFORD FACILITY SERVICES PVT.LTD. | 3.33 | 3.33 | 100 | 0
5610 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for "Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Ganganandapur Sub District Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.07.2022 to 30.09.2022]". | 581/KSD | 30/06/2022 | 92 | CLIFFORD FACILITY SERVICES PVT.LTD. | 0.78 | 0.78 | 100 | 0
5611 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for "Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Anukhal Sub-District Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.07.2022 to 30.09.2022]" | 582/KSD | 30/06/2022 | 92 | CLIFFORD FACILITY SERVICES PVT.LTD. | 0.78 | 0.78 | 100 | 0
5612 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for "Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Parulia Sub District Laboratory & Kamalnagar WTP laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.07.2022 to 30.09.2022]" | 583/KSD | 30/06/2022 | 92 | CLIFFORD FACILITY SERVICES PVT.LTD. | 1.23 | 1.23 | 100 | 0
5613 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work for 'Operation & Maintenance of 08 (Eight) Nos. Sub District Laboratories in different Blocks under Burdwan Division, PHE Dte. (Period from 01.09.2022 to 31.12.2022)' [GROUP : A] | 459/AE/HQ | 31/08/2022 | 122 | COMPUTER MEDIA | 1.99 | 1.81 | 100 | 100
5614 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for Annual Maintenance Contract (AMC) for software upgradation and other software related issues in existing computers, refilling of Cartridge of the printers, replacement of battery of UPS in District, Sub-Dist. and NGO Laboratories under Burdwan Division, P.H.E. Dte. [Period from 01.09.2022 to 31.12.2022] [Group : A] | 458/AE/HQ | 31/08/2022 | 122 | COMPUTER MEDIA | 0.65 | 0.65 | 100 | 100
5615 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in 1 (One) Sub District Laboratoriy within Headquaters under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.07.2022 to 31.07.2022] [GROUP : A] | 362/AE/HQ | 30/06/2022 | 31 | COMPUTER MEDIA | 0.26 | 0.26 | 100 | 0
5616 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Supply & Delivery of Chemicals, reagents and consumables for 14(Fourteen) laboratories under Burdwan Division, P.H.E. Dte. | 3598/BWD | 18/08/2022 | 20 | M/S LAXMI ENTERPRISE | 26.61 | 26.61 | 100 | 0
5617 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Work order for "Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Anukhal Sub-District Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.10.2022 to 31.12.2022] " | 941/KSD | 29/09/2022 | 92 | CLIFFORD FACILITY SERVICES PVT.LTD. | 0.78 | 0.78 | 100 | 100
5618 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | work order for "Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Ganganandapur Sub District Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.10.2022 to 31.12.2022]" | 941/B/KSD | 29/09/2022 | 92 | CLIFFORD FACILITY SERVICES PVT.LTD. | 0.78 | 0.78 | 100 | 100
5619 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Work Order for Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Parulia Sub District Laboratory & Kamalnagar WTP laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.10.2022 to 31.12.2022] | 941/C/KSD | 29/09/2022 | 92 | CLIFFORD FACILITY SERVICES PVT.LTD. | 1.23 | 1.23 | 100 | 100
5620 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of resource person to operate AAS at District Laboratory under Burdwan Division, PHE. Dte. [Period from 01.10.2022 to 31.12.2022] | 520/AE/HQ | 29/09/2022 | 91 | ALAKA GHOSH | 0.5 | 0.5 | 100 | 0
5621 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Work Order for "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Anukhal Sub District Water Testing laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.01.2023 to 31.01.2023]" | 1148/KSD | 30/12/2022 | 31 | ALAKA GHOSH | 0.37 | 0.37 | 100 | 0
5622 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Payment of festival bonus for the accounting year 2021-22 to laboratory personnel of District and Sub-District laboratory under Burdwan Division, PHE Dte. | 511/AE/HQ | 26/09/2022 | 7 | M/S S. CHOUDHURY | 0.83 | 0 | 0 | 100
5623 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of Laboratory personnel (Chemist/Bacteriologist, Lab Assistant & Sampling Assistant) in Satgachia Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/01/2023 to 31/01/2023] | 661/AE/HQ | 30/12/2022 | 31 | COMPUTER MEDIA | 0.51 | 0.51 | 100 | 100
5624 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of Laboratory personnel (Chemist/Bacteriologist & Lab Assistant) in Barshul Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/01/2023 to 31/01/2023] | 663/AE/HQ | 30/12/2022 | 31 | COMPUTER MEDIA | 0.58 | 0.58 | 100 | 100
5625 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for Engagement of Laboratory Personnel i.e. Chemist (One Person), Bacteriologist (One Person), Laboratory Assistant(One Person), Sampling Assistant (One Person) and Computer Operator/Data Entry Operator (One Person) for Burdwan District Laboratory under Burdwan Division, PHE Dte at PHE Complex, Nababhat, Burdwan. For the period from 01.09.2022 to 31.12.2022¿. | 1489/BSD | 26/08/2022 | 122 | ALAKA GHOSH | 3.14 | 3.14 | 100 | 0
5626 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Work Order for "Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Manteswar Sub District Water Testing Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.01.2023 to 31.01.2023]." | 1115/KSD | 23/12/2022 | 31 | ALAKA GHOSH | 0.59 | 0.59 | 100 | 0
5627 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Maintenance charges of Burdwan District Laboratory under Burdwan Division,PHE Dte (Period from 01.08.2022 to 31.12.2022). Gr.A. | 1328/BSD | 28/07/2022 | 153 | ALAKA GHOSH | 0.37 | 0.35 | 100 | 0
5628 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Work Order for "Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Manteswar Sub District Water Testing Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.10.2022 to 31.10.2022]." | 937/KSD | 29/09/2022 | 31 | ALAKA GHOSH | 0.43 | 0.43 | 100 | 0
5629 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Work Order for "Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Manteswar Sub District Water Testing Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.09.2022 to 30.09.2022]." | 711/KSD | 23/08/2022 | 30 | ALAKA GHOSH | 0.43 | 0.43 | 100 | 0
5630 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Construction of concrete road & providing plinth protection due to soil erosion including wiring work at SANKARI Sub District Laboratory under Burdwan Division, PHE. Dte. | 521/AE/HQ | 29/09/2022 | 30 | KAJAL MUKHERJEE | 0.72 | 0.71 | 100 | 0
5631 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Work Order for "Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Manteswar Sub District Water Testing Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.08.2022 to 31.08.2022]". | 607/KSD | 25/07/2022 | 31 | ALAKA GHOSH | 0.43 | 0.43 | 100 | 0
5632 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Work Order for "Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Manteswar Sub District Water Testing Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.11.2022 to 31.12.2022]." | 969/KSD | 20/10/2022 | 61 | ALAKA GHOSH | 0.87 | 0.87 | 100 | 0
5633 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of laboratory personnel i.e. Chemist (One Person), Bacteriologist (One Person), Laboratory Assistant (One Person), Sampling Assistant (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman. For the period from 01.01.2023 to 31.01.2023. | 2328/BSD | 30/12/2022 | 31 | ALAKA GHOSH | 0.84 | 0.84 | 100 | 0
5634 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of laboratory personnel i.e. AAS Operator (One Person) and Computer Operator/Data Entry Operator (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman, For the period from 01.01.2023 to 31.01.2023. | 2329/BSD | 30/12/2022 | 31 | ALAKA GHOSH | 0.4 | 0.4 | 100 | 0
5635 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Providing acrylic distemper including electrical wiring work and fitting of wash basin for modification of old building of Bursul Godown area to set up Sikhaniketan Sub-Dist. Laboratory under Burdwan Division, PHE. Dte. | 598/AE/HQ | 07/12/2022 | 15 | ANWESHA CONSTRUCTION | 0.4 | 0.4 | 100 | 0
5636 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Proposed renovation extension and modification (Civil Structure Part) of Old Building of Borsul Godown area to set up Barshul Sub District Laboratory under Burdwan Division, PHE. Dte. | 522/AE/HQ | 29/09/2022 | 30 | ANWESHA CONSTRUCTION | 0.89 | 0.83 | 100 | 0
5637 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Supplying, delivery and installation of metal vinyle ACP board (4' x 3') for various water testing laboratories under Burdwan Division PHE Dte. | 115/AE/HQ | 22/02/2023 | 15 | ISHAN CONSTRUCTION | 0.84 | 0.84 | 100 | 0
5638 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for "Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Manteswar Sub District Water Testing Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.02.2023 to 28.02.2023]." | 70/A/KSD | 30/01/2023 | 28 | ALAKA GHOSH | 0.59 | 0.59 | 100 | 0
5639 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Anukhal Sub District Water Testing laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.02.2023 to 28.02.2023]" | 70/B/KSD | 30/01/2023 | 28 | ALAKA GHOSH | 0.37 | 0.37 | 100 | 0
5640 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for engagement of laboratory personnel (Chemist/Bacteriologist and Lab Assistant) in 2 Nos. Sub-Dist Laboratories within Head Quarters under Burdwan Division, PHE Dte. [Period from 01/07/2022 to 31/07/2022] | 358/AE/HQ | 28/06/2022 | 30 | COMPUTER MEDIA | 0.52 | 0.52 | 100 | 0
5641 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for engagement of laboratory personnel (Sampling Assistant) in 7 Nos. Sub-Dist Laboratories within Head Quarters under Burdwan Division, PHE Dte. [Period from 01/07/2022 to 31/07/2022] | 357/AE/HQ | 28/06/2022 | 30 | COMPUTER MEDIA | 0.78 | 0.78 | 100 | 0
5642 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Parulia Sub District Water Testing Laboratory & Kamalnagar WTP laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.04.2023 to 30.04.2023]" | 293/KSD | 31/03/2023 | 30 | SURATH DEY | 0.59 | 0.59 | 100 | 100
5643 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for engagement of laboratory personnel i.e. Chemist (One Person), Bacteriologist (One Person), Laboratory Assistant (One Person) , Sampling Assistant (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman. For the period from 01.02.2023 to 28.02.2023. | 121/BSD | 01/02/2023 | 28 | ALAKA GHOSH | 0.84 | 0.84 | 100 | 0
5644 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work order "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Ganganandapur Sub-District Water Testing Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.03.2023 to 31.03.2023]" | 167/KSD | 27/02/2023 | 31 | BUILD-TECH | 0.37 | 0.37 | 100 | 100
5645 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Anukhal Sub District Water Testing laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.04.2023 to 30.04.2023]" | 290/KSD | 31/03/2023 | 30 | ALAKA GHOSH | 0.37 | 0.37 | 100 | 100
5646 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work Order for "Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Manteswar Sub District Water Testing Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.04.2023 to 30.04.2023]." | 291/KSD | 31/03/2023 | 30 | ALAKA GHOSH | 0.59 | 0.59 | 100 | 100
5647 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for ¿engagement of laboratory personnels i.e. AAS Operator (One Person) and Computer Operator/Data Entry Operator (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman, For the period from 01.02.2023 to 28.02.2023. | 122/BSD | 01/02/2023 | 28 | ALAKA GHOSH | 0.4 | 0.4 | 100 | 0
5648 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of Laboratory personnel (Sampling Assistant) in 5 Nos. Sub District Laboratories within Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.01.2023 to 31.01.2023] | 666/AE/HQ | 30/12/2022 | 31 | COMPUTER MEDIA | 0.74 | 0.74 | 100 | 100
5649 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for Engagement of Laboratory personnel (Chemist/ Bacteriologist & Lab Assistant) in Barshul Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/02/2023 to 28/02/2023] | 89-A/AE/HQ | 31/01/2023 | 28 | COMPUTER MEDIA | 0.58 | 0.58 | 100 | 100
5650 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for Engagement of laboratory personnel i.e. Chemist (One Person), Bacteriologist (One Person), Laboratory Assistant (One Person) , Sampling Assistant (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman. For the period from 01.04.2023 to 30.04.2023. | 599/BSD | 30/03/2023 | 30 | ALAKA GHOSH | 0.84 | 0.84 | 100 | 100
5651 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for Engagement of laboratory personnel i.e. AAS Operator (One Person) and Computer Operator/Data Entry Operator (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman, For the period from 01.04.2023 to 30.04.2023. | 600/BSD | 30/03/2023 | 30 | ALAKA GHOSH | 0.4 | 0.4 | 100 | 100
5652 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Laboratory maintenance in 7 Nos. Sub District Laboratories under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.03.2023 to 30.04.2023] | 122/AE/HQ | 27/02/2023 | 59 | COMPUTER MEDIA | 0.85 | 0.82 | 100 | 100
5653 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Ganganandapur Sub-District Water Testing Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.05.2023 to 31.05.2023]". | 373/KSD | 25/04/2023 | 31 | BUILD-TECH | 0.37 | 0.37 | 100 | 100
5654 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of Laboratory personnel (Chemist/Bacteriologist, Lab Assistant & Sampling Assistant) in Shaktigarh Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/02/2023 to 28/02/2023] | 89/AE/HQ | 31/01/2023 | 28 | COMPUTER MEDIA | 0.51 | 0.51 | 100 | 100
5655 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Anukhal Sub District Water Testing laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.05.2023 to 31.05.2023]" | 371/KSD | 25/04/2023 | 31 | ALAKA GHOSH | 0.37 | 0.37 | 100 | 100
5656 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for engagement of laboratory personnels i.e. Chemist (One Person), Bacteriologist (One Person), Laboratory Assistant (One Person), Sampling Assistant (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman. For the period from 01.05.2023 to 31.05.2023. | 777/BSD | 27/04/2023 | 31 | ALAKA GHOSH | 0.84 | 0.84 | 100 | 100
5657 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for engagement of laboratory personnel i.e. AAS Operator (One Person) and Computer Operator/Data Entry Operator (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman, For the period from 01.05.2023 to 31.05.2023. | 778/BSD | 27/04/2023 | 31 | ALAKA GHOSH | 0.4 | 0.4 | 100 | 100
5658 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Sampling Assistant) in 5 Nos. Sub District Laboratories within Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.03.2023 to 31.03.2023] | 121/AE/HQ | 27/02/2023 | 31 | COMPUTER MEDIA | 0.74 | 0.74 | 100 | 100
5659 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Supply & Delivery of Chemicals, reagents and consumables for 14(Fourteen) laboratories under Burdwan Division, P.H.E. Dte. | 2153/BWD | 10/05/2023 | 20 | BHARATI CHEMICAL & SCIENTIFIC WORKS | 30.43 | 30.43 | 100 | 100
5660 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for Engagement of Laboratory personnel (Chemist/ Bacteriologist & Lab Assistant) in Barshul Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/05/2023 to 31/05/2023] | 274-A/AE/HQ | 27/04/2023 | 31 | COMPUTER MEDIA | 0.58 | 0.58 | 100 | 100
5661 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for Engagement of laboratory personnel (Chemist / Bacteriologist and Lab Assistant) in Manteswar Sub District Water Testing Laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.05.2023 to 31.05.2023]. | 372/KSD | 25/04/2023 | 31 | ALAKA GHOSH | 0.59 | 0.59 | 100 | 100
5662 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for Engagement of Laboratory personnel (Chemist/ Bacteriologist, Lab Assistant & Sampling Assistant) in Satgachia Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/03/2023 to 31/03/2023] | 120/AE/HQ | 27/02/2023 | 31 | COMPUTER MEDIA | 0.51 | 0.51 | 100 | 100
5663 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for Engagement of Laboratory personnel (Chemist/ Bacteriologist, Lab Assistant & Sampling Assistant) in Satgachia Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/04/2023 to 30/04/2023] | 206/AE/HQ | 31/03/2023 | 30 | COMPUTER MEDIA | 0.51 | 0.51 | 100 | 100
5664 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for Engagement of Laboratory personnel (Chemist/ Bacteriologist, Lab Assistant & Sampling Assistant) in Satgachia Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/05/2023 to 31/05/2023] | 273/AE/HQ | 27/04/2023 | 31 | COMPUTER MEDIA | 0.51 | 0.51 | 100 | 100
5665 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Sampling Assistant) in 5 Nos. Sub District Laboratories within Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.02.2023 to 28.02.2023] | 87/AE/HQ | 31/01/2023 | 28 | COMPUTER MEDIA | 0.74 | 0.74 | 100 | 100
5666 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for Engagement of Laboratory personnel (Chemist/ Bacteriologist & Lab Assistant) in Barshul Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/04/2023 to 30/04/2023] | 207/AE/HQ | 31/03/2023 | 30 | COMPUTER MEDIA | 0.58 | 0.58 | 100 | 100
5667 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for Engagement of Laboratory personnel (Chemist/ Bacteriologist, Lab Assistant & Sampling Assistant) in Satgachia Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/02/2023 to 28/02/2023] | 88/AE/HQ | 31/01/2023 | 28 | COMPUTER MEDIA | 0.51 | 0.51 | 100 | 100
5668 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of Laboratory personnel (Chemist/Bacteriologist, Lab Assistant & Sampling Assistant) in Shaktigarh Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/03/2023 to 31/03/2023] | 119/AE/HQ | 27/02/2023 | 31 | COMPUTER MEDIA | 0.51 | 0.51 | 100 | 100
5669 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for Engagement of Laboratory personnel (Chemist/ Bacteriologist & Lab Assistant) in Barshul Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/03/2023 to 31/03/2023] | 118/AE/HQ | 27/02/2023 | 31 | COMPUTER MEDIA | 0.58 | 0.58 | 100 | 100
5670 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Renovation of District Laboratory with meeting hall at Nababhat P.H.E Complex within RWS Sub-Division under Burdwan Division, PHE Dte. | 788/BSD | 28/04/2023 | 30 | GHOSH ENTERPRISE | 0.94 | 0.94 | 100 | 100
5671 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Procurement of consumables for OMAS for different Sub District Laboratories under Burdwan Division PHE Dte. [GROUP : A] | 450/AE/HQ | 25/08/2022 | 7 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT LTD. | 4.97 | 4.97 | 100 | 0
5672 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) in 3 Nos. Sub District Laboratories within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/08/2022 to 31/12/2022] GROUP : A | 417/AE/HQ | 29/07/2022 | 153 | COMPUTER MEDIA | 4.66 | 4.66 | 100 | 0
5673 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of Laboratory personnel (Chemist/Bacteriologist, Lab Assistant & Sampling Assistant) in Shaktigarh Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/01/2023 to 31/01/2023] | 662/AE/HQ | 30/12/2022 | 31 | COMPUTER MEDIA | 0.51 | 0.51 | 100 | 100
5674 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel (Chemist/Bacteriologist and Lab Assistant) of NGO managed laboratory for the month of November'2022. | 1064/JJM | 13/02/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.33 | 0 | 0 | 0
5675 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel of NGO managed laboratory under Burdwan Division, PHE Dte. for the month of December'2022. | 1156/JJM | 09/03/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.33 | 0 | 0 | 0
5676 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab Personnel for the month of June & July'23. | 550/JJM | 21/08/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.9 | 0 | 0 | 0
5677 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel of NGO managed laboratory for the month of September'23 and festival bonus. | 879/JJM | 10/11/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.61 | 0 | 0 | 0
5678 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Festival Bonus F.Y.-2021-2022 | 1067/JJM | 15/02/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.14 | 0 | 0 | 0
5679 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel of NGO managed laboratory under Burdwan Division, PHE Dte. for the month of January'23. | 1159/JJM | 09/03/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5680 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab Personnel for the month of June & July'23. | 551/JJM | 21/08/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.9 | 0 | 0 | 0
5681 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab Personnel for the month of June & July'23. | 552/JJM | 21/08/2023 | 0 | SHASTRI SMRITI SANGHA | 0.9 | 0 | 0 | 0
5682 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary bill of NGO for the month of October & November 2023. | 1067/JJM | 13/12/2023 | 0 | SHASTRI SMRITI SANGHA | 0.9 | 0 | 0 | 0
5683 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel of NGO managed laboratory under Burdwan Division, PHE Dte. for the month of December'22. | 1158/JJM | 09/03/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.33 | 0 | 0 | 0
5684 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel (Chemist/Bacteriologist and Lab Assistant) of NGO managed laboratory for the month of November'2022. | 1065/JJM | 13/02/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.33 | 0 | 0 | 0
5685 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Festival Bonus F.Y.-2021-2022 | 1068/JJM | 15/02/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.14 | 0 | 0 | 0
5686 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel of NGO managed laboratory under Burdwan Division, PHE Dte. for the month of December'22. | 1157/JJM | 09/03/2023 | 0 | SHASTRI SMRITI SANGHA | 0.31 | 0 | 0 | 0
5687 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Maintenance charges bill for the period January'22 to June'22. | 52/JJM | 27/04/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.4 | 0 | 0 | 0
5688 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | NGO Salary bill for the month of February'23. | 12/JJM | 17/04/2023 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5689 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab personnel (Chemist/Bacteriologist and Lab Assistant) for the month of March'23. | 170/JJM | 26/05/2023 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5690 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab personnel (Chemist/Bacteriologist and Lab Assistant) for the month of March'23. | 168/JJM | 26/05/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5691 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary bill of NGO for the month of October & November 2023. | 1066/JJM | 13/12/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.9 | 0 | 0 | 0
5692 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Payment for NGO Lab personnel (Chemist/Bacteriologist and Lab Assistant) for the month of October'2022. | 946/JJM/22-23 | 09/01/2023 | 0 | SHASTRI SMRITI SANGHA | 0.26 | 0 | 0 | 0
5693 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel of NGO managed laboratory under Burdwan Division, PHE Dte. for the month of January'23. | 1160/JJM | 09/03/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5694 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | NGO Salary bill for the month of February'23. | 10/JJM | 17/04/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5695 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Maintenance of NGO managed laboratory for the period July'22 to December'22. | 381/JJM | 19/07/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.35 | 0 | 0 | 0
5696 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Maintenance charges bill for the Period January'22 to June'22. | 52/JJM | 27/04/2023 | 0 | SHASTRI SMRITI SANGHA | 0.4 | 0 | 0 | 0
5697 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO for the month of May'23. | 514/JJM | 16/08/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5698 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab for the month of August'23. | 754/JJM | 11/10/2023 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5699 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel of NGO managed laboratory for the month of September'23 and festival bonus. | 878/JJM | 10/11/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.61 | 0 | 0 | 0
5700 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Payment of NGO lab personnel (Chemist/Bacteriologist and Lab Assistant) for the month of April'23. | 198/JJM | 31/05/2023 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5701 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Maintenance of NGO managed laboratory for the period July'22 to December'22. | 382/JJM | 19/07/2023 | 0 | SHASTRI SMRITI SANGHA | 0.35 | 0 | 0 | 0
5702 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO for the month of May'23. | 515/JJM | 16/08/2023 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5703 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO for the month of May'23. | 513/JJM | 16/08/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5704 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary bill for the month of October & November'2023. | 1065/JJM | 13/12/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.9 | 0 | 0 | 0
5705 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Festival Bonus F.Y.-2021-2022 | 1069/JJM | 15/02/2023 | 0 | SHASTRI SMRITI SANGHA | 0.1 | 0 | 0 | 0
5706 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Maintenance charges bill for the period January'2022 to June'2022. | 53/JJM | 27/04/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.4 | 0 | 0 | 0
5707 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab personnel (Chemist/Bacteriologist and Lab Assistant) for the month of March'23. | 169/JJM | 26/05/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5708 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab for the month of August'23. | 756/JJM | 11/10/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5709 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Payment for NGO Lab personnel (Chemist/Bacteriologist and Lab Assistant) for the month of October'2022. | 944/JJM/22-23 | 09/01/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.33 | 0 | 0 | 0
5710 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel (Chemist/Bacteriologist and Lab Assistant) of NGO managed laboratory for the month of November'2022. | 1066/JJM | 13/02/2023 | 0 | SHASTRI SMRITI SANGHA | 0.31 | 0 | 0 | 0
5711 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel of NGO managed laboratory under Burdwan Division, PHE Dte. for the month of January'23. | 1161/JJM | 09/03/2023 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5712 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab for the month of August'23. | 755/JJM | 11/10/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5713 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Payment for NGO Lab personnel (Chemist/Bacteriologist and Lab Assistant) for the month of October'2022. | 945/JJM/22-23 | 09/01/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.33 | 0 | 0 | 0
5714 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | NGO Salary bill for the month of February'23. | 11/JJM | 17/04/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5715 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Payment of NGO lab personnel (Chemist/Bacteriologist and Lab Assistant) for the month of April'23. | 196/JJM | 31/05/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5716 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Payment of NGO lab personnel (Chemist/Bacteriologist and Lab Assistant) for the month of April'23. | 197/JJM | 31/05/2023 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5717 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Maintenance of NGO managed laboratory for the period July'22 to December'22. | 380/JJM | 19/07/2023 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.35 | 0 | 0 | 0
5718 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Maintenance of NGO managed laboratory for the period January'22 to June'22. | 594/JJM | 31/08/2023 | 0 | SIKSHA-NIKATAN | 0.21 | 0 | 0 | 0
5719 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of Lab personnel of NGO managed laboratory for the month of September'23 and festival bonus. | 880/JJM | 10/11/2023 | 0 | SHASTRI SMRITI SANGHA | 0.61 | 0 | 0 | 0
5720 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation work order for "Engagement of laboratory personnel (Chemist , Bacteriologist and Lab Assistant) in Parulia Sub District Water Testing Laboratory & Kamalnagar WTP laboratory within Kalna Sub-Division under Burdwan Division, P.H.E. Dte., Purba Bardhaman. [Period from 01.05.2023 to 31.05.2023]" | 370/KSD | 25/04/2023 | 31 | SURATH DEY | 0.59 | 0 | 0 | 0
5721 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 2 Nos. Sub District Laboratories within Burdwan Sadar Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For Six Months i.e. 01.06.2023 to 30.11.2023]._2ND CALL. | 2451/BWD | 31/05/2023 | 183 | DULAL MAJUMDER | 6.99 | 6.26 | 100 | 100
5722 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Arrangement of drinking water supply in SHAKTIGARH Water Testing Laboratory by sinking of 75Mtr. Deep 40 x 100 mm. dia., with PVC pipe, DWP Tube wells in the district of Purba Bardhaman under Burdwan Division, PHE. Dte. | 350/AE/HQ | 18/07/2023 | 30 | A R TRADERS | 0.77 | 0.77 | 100 | 100
5723 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Arrangement of drinking water supply in SANKARI Water Testing Laboratory by sinking of 75 Mtr. Deep 40 x 100 mm. dia., with PVC pipe, DWP Tube wells in the district of Purba Bardhaman under Burdwan Division, PHE. Dte. | 354/AE/HQ | 18/07/2023 | 30 | SOUMYAVASH DAS | 0.96 | 0.94 | 100 | 100
5724 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Arrangement of drinking water supply in ANUKHAL Water Testing Laboratory by sinking of 75 Mtr. Deep 40 x 100 mm. dia., with PVC pipe, DWP Tube wells in the district of Purba Bardhaman under Burdwan Division, PHE. Dte. | 356/AE/HQ | 18/07/2023 | 30 | M/S F.S. ENTERPRISE | 0.96 | 0.96 | 100 | 100
5725 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Arrangement of drinking water supply in MONTESWAR Water Testing Laboratory by sinking of 75 Mtr. Deep 40 x 100 mm. dia., with PVC pipe, DWP Tube wells in the district of Purba Bardhaman under Burdwan Division, PHE. Dte. | 358/AE/HQ | 18/07/2023 | 30 | SUPRIYA RAY | 0.88 | 0.88 | 100 | 100
5726 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Arrangement of drinking water supply in BARSHUL Water Testing Laboratory by sinking of 75 Mtr. Deep 40 x 100 mm. dia., with PVC pipe, DWP Tube wells in the district of Purba Bardhaman under Burdwan Division, PHE. Dte. | 353/AE/HQ | 18/07/2023 | 30 | ANWESHA CONSTRUCTION | 0.8 | 0.79 | 100 | 100
5727 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Arrangement of drinking water supply in SEHERA Water Testing Laboratory by sinking of 75 Mtr. Deep 40 x 100 mm. dia., with PVC pipe, DWP Tube wells in the district of Purba Bardhaman under Burdwan Division, PHE. Dte. | 352/AE/HQ | 18/07/2023 | 30 | RUPALI ENTERPRISE | 0.96 | 0.95 | 100 | 100
5728 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Arrangement of drinking water supply in GANGANANDAPUR Water Testing Laboratory by sinking of 75 Mtr. Deep 40 x 100 mm. dia., with PVC pipe, DWP Tube wells in the district of Purba Bardhaman under Burdwan Division, PHE. Dte. | 355/AE/HQ | 18/07/2023 | 30 | DEBJYOTI GOSWAMI | 0.96 | 0.95 | 100 | 100
5729 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Continuation Work Order for Annual Maintenance Contract (AMC) for software upgradation and other software related issues in existing computers, refilling of Cartridge of the printers, replacement of battery of UPS in District, Sub-Dist. and NGO Laboratories under Burdwan Division, P.H.E. Dte. [Period from 01.08.2023 to 31.01.2024] | 396/AE/HQ | 27/07/2023 | 184 | COMPUTER MEDIA | 0.99 | 0.99 | 100 | 100
5730 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | SALARY OF NGO LAB PERSONNEL FOR THE MONTH OF DECEMBER'2023. | 1286/JJM | 29/01/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5731 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | SALARY OF NGO LAB PERSONNEL FOR THE MONTH OF DECEMBER'2023. | 1287/JJM | 29/01/2024 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5732 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary for the month of February'2024. | 1711/JJM | 20/03/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5733 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary for the month of February'2024. | 1712/JJM | 20/03/2024 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5734 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Maintenance charges for the period July'23 to December'23. | 1708/JJM | 20/03/2024 | 0 | SHASTRI SMRITI SANGHA | 0.35 | 0 | 0 | 0
5735 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab Personnel for the month of January'2024. | 1379/JJM | 21/02/2024 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5736 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Maintenance charges bill for the month of January'23 to June'23. | 1377/JJM | 21/02/2024 | 0 | SHASTRI SMRITI SANGHA | 0.4 | 0 | 0 | 0
5737 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab Personnel for the month of January'2024. | 1378/JJM | 21/02/2024 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5738 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | SALARY OF NGO LAB PERSONNEL FOR THE MONTH OF DECEMBER'2023. | 1285/JJM | 29/01/2024 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5739 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Maintenance charges for the period JANUARY'23 to DECEMBER'23. | 1709-10/JJM | 20/03/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.75 | 0 | 0 | 0
5740 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Maintenance charges bill for the period January to June 2023. | 1376/JJM | 21/02/2024 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.4 | 0 | 0 | 0
5741 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary of NGO Lab Personnel for the month of January'2024. | 1380/JJM | 21/02/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5742 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Salary for the month of February'2024. | 1713/JJM | 20/03/2024 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5743 | PURBA BARDHAMAN | Burdwan Division | OPERATIONAL CHARGES OF PHED & NGO MANAGED LABORATORIES RELATED WATER QUALITY MONITORING & SURVEILLANCE UNDER JAL JEEVAN MISSION , SM/11857 | Support-WQMSP | Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) in 1 No. Sub District Laboratory (Banonabagram Sub District Laboratory) within Durgapur Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01/08/2022 to 31/12/2023] | 463/DSD | 29/07/2022 | 518 | CLIFFORD FACILITY SERVICES PVT.LTD. | 4.55 | 3.77 | 82.77 | 72
5744 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Supply of Inverter Battery, MS Rack, office table and Plastic Chair for 14 Nos. laboratory under Burdwan Division, PHE. Dte. | 102/AE/HQ | 19/02/2024 | 30 | SANDIPAN SENGUPTA | 8.79 | 5.74 | 65.29 | 20
5745 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work order for Annual Maintenance Contract (AMC) for software upgradation and other software related issues in existing computers, refilling of Cartridge of the printers, replacement of battery of UPS in District, Sub-Dist. and NGO Laboratories under Burdwan Division, P.H.E. Dte. [Period from 01.02.2024 to 31.07.2024] | 46/AE/HQ | 29/01/2024 | 182 | COMPUTER MEDIA | 0.99 | 0.99 | 100 | 100
5746 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Engagement of 4 Nos Laboratory personnel (Analyst) at 4 Nos Water Testing Laboratories under Burdwan Division, PHE Dte [Period: One Month (01.03.24 to 31.03.24)] | 133/AE/HQ | 28/02/2024 | 31 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
5747 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 4 Nos Water Testing Laboratories under Burdwan Division, PHE Dte [Period:One Month (01.04.24 to 30.04.24)] | 234/AE/HQ | 28/03/2024 | 30 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
5748 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 4 Nos. Sub District Laboratories within Kalna Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.06.2024 to 31.07.2024] | 2007/BWD | 30/05/2024 | 61 | DULAL MAJUMDER | 5.04 | 5.04 | 100 | 100
5749 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at 03 (Three) nos Laboratories (SDWTL) (Satgachia, Monteswar, Parulia) under Burdwan Division, PHE Dte. | 193/RWS | 18/06/2024 | 7 | DAS ENTERPRISE | 0.72 | 0.72 | 100 | 100
5750 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at 03 (Three) nos Laboratories (SDWTL) (Saktigarh, Ganganandapur, Bonnobogram) under Burdwan Division, PHE Dte. | 194/RWS | 18/06/2024 | 7 | KHUSI BHAKAT | 0.73 | 0.73 | 100 | 100
5751 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Engagement of 1 No. Laboratory Assistant at Bonnabagram Water Testing Laboratories under Burdwan Division, PHE Dte [Period: For Four Months (01.03.24 to 30.06.24)] | 131/AE/HQ | 27/02/2024 | 121 | DULAL MAJUMDER | 0.63 | 0.63 | 100 | 100
5752 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.06.24 to 30.06.24)] | 299/AE/HQ | 30/05/2024 | 30 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
5753 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of laboratory personnels i.e. Chemist (One Person), Additional Chemist (One person), Bacteriologist (One Person), Laboratory Assistant (One Person), Sampling Assistant (One Person) and Computer Operator/Data Entry Operator (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman. [Period for 6 (Six) Months i.e. 01.06.2024 to 30.11.2024] | 1997/BWD | 30/05/2024 | 184 | ALAKA GHOSH | 7.67 | 7.67 | 100 | 100
5754 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at 03 (Three) nos Laboratories (SDWTL) (Sehara, Sankari, Anukhal) under Burdwan Division, PHE Dte. | 192/RWS | 18/06/2024 | 7 | GHOSH ENTERPRISE | 0.72 | 0.72 | 100 | 100
5755 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.03.24 to 31.03.24)] | 134/AE/HQ | 28/02/2024 | 31 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
5756 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 4 Nos Water Testing Laboratories under Burdwan Division, PHE Dte [Period:One Month (01.05.24 to 31.05.24)] | 275/AE/HQ | 30/04/2024 | 31 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
5757 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Repair & renovation of Barsul Sub District Water Testing Laboratory under Burdwan Division, P.H.E. Dte. | 1018/AE/HQ | 28/12/2023 | 30 | PRATIVA CONSTRUCTION | 4.24 | 4.13 | 100 | 100
5758 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at Four nos Laboratories (SDWTL) (Dr. ChatterjeeVWS,Aikyatan,Shastri Smriti Sangha,Barshul) under Burdwan Division, PHE Dte. | 98/RWS | 13/03/2024 | 15 | KHUSI BHAKAT | 0.88 | 0.85 | 100 | 100
5759 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 3 Nos. Sub District Laboratories within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.03.2024 to 31.05.2024] | 812/BWD | 27/02/2024 | 90 | DULAL MAJUMDER | 5.3 | 5.3 | 100 | 100
5760 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 2 Nos. Sub District Laboratories within Burdwan Sadar Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.03.2024 to 31.05.2024] | 830/BWD | 28/02/2024 | 90 | DULAL MAJUMDER | 2.99 | 2.99 | 100 | 100
5761 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 4 Nos. Sub District Laboratories within Kalna Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.03.2024 to 31.05.2024] | 858/BWD | 29/02/2024 | 92 | DULAL MAJUMDER | 7.59 | 7.59 | 100 | 50
5762 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Sampling Assistant) in Bananabagram Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period for 01.03.2024 to 31.05.2024]. | 145/AE/HQ | 28/02/2024 | 90 | DULAL MAJUMDER | 0.37 | 0.37 | 100 | 100
5763 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Supply of Materials required for maintaining NABL Accreditation as per ISO:I 17025:2017 of Bardhaman District water testing Laboratory, PHED, Govt of West Bengal. | 151/RWS | 26/04/2024 | 7 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.79 | 0.79 | 100 | 100
5764 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Installation of Aquaguard purifier at District Laboratory with meeting hall at Nababhat P.H.E. Complex within RWS Burdwan Sub-Division, under Burdwan Division. | 05/RWS | 05/01/2024 | 7 | KHUSI BHAKAT | 0.21 | 0.2 | 100 | 100
5765 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 4 Nos Water Testing Laboratories under Burdwan Division, PHE Dte [Period:One Month (01.06.24 to 30.06.24)] | 298/AE/HQ | 30/05/2024 | 30 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
5766 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Supply of Residual Chlorine Kit, Iron Test Kit and Sample Collection Bottle for Burdwan District Laboratory under Burdwan Division, PHE Dte., Purba Bardhaman. | 863/AE/HQ | 24/10/2024 | 15 | ALAKA GHOSH | 1 | 1 | 100 | 100
5767 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.04.24 to 30.04.24)] | 235/AE/HQ | 28/03/2024 | 30 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
5768 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.05.24 to 31.05.24)] | 276/AE/HQ | 30/04/2024 | 31 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
5769 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Salary payment for the month of March'2024. | 295/JJM | 29/05/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5770 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Monthly Remuneration Of Lab Personnel For The Month Of September 2024 | 1044/JJM | 30/10/2024 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5771 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | SALARY BILL FOR THE MONTH OF MAY-2024' | 459/JJM | 02/07/2024 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5772 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Salary Bill For The Month Of September 2024 | 1043/JJM | 30/10/2024 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5773 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Remuneration of Laboratory Personal for the month April-2024 | 370/JJM | 21/06/2024 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5774 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Festival Bonus of lab personnel | 1032/JJM | 25/10/2024 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.18 | 0 | 0 | 0
5775 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Laboratory contingency charges bill [Period January'22 to June'22] | 446/JJM | 02/07/2024 | 0 | SIDHU KANU GRAM UNNAYAN SAMITY | 0.4 | 0 | 0 | 0
5776 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Monthly remuneration of lab personnel for the month of July 2024 | 757/JJM | 30/08/2024 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5777 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | SALARY BILL FOR THE MONTH OF MAY-2024. | 460/JJM | 02/07/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5778 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Grant The Remuneration Of Lab Staff For The Month Of November-2024 | 1175/JJM | 17/12/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5779 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | MAINTENANCE CHARGE FOR THE MONTH OF JANUARY 2024 TO JUNE 2024(6 MONTH) | 1049/JJM | 05/11/2024 | 0 | SHASTRI SMRITI SANGHA | 0.4 | 0 | 0 | 0
5780 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Salary Bill for the month of August- 2024 | 858/JJM | 20/09/2024 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5781 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Grant The Remuneration Of Lab Staff For The Month Of October-2024. | 1086/JJM | 29/11/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5782 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Salary Bill for the month of April-2024 | 371/JJM | 21/06/2024 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5783 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Salary bill for the month of July 2024 | 757/JJM | 30/08/2024 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5784 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Grant The Festival Bonus For Laboratory personnel | 1034/JJM | 25/10/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.18 | 0 | 0 | 0
5785 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Salary Bill For The Month Of November-2024 | 1174/JJM | 17/12/2024 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5786 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Remuneration of lab personnel for the month of June 2024. | 747/JJM | 29/08/2024 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5787 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | LABORATORY MAINTENANCE BILL FOR JANUARY TO JUNE 2024 | 1050/JJM | 05/11/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.4 | 0 | 0 | 0
5788 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | SALARY BILL FOR THE MONTH OF MAY-2024' | 461/JJM | 02/07/2024 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5789 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Salary bill for the month of June 2024 | 748/JJM | 29/08/2024 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5790 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Salary payment for the month of March'2024. | 294/JJM | 29/05/2024 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5791 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Remuneration of lab personnel for the month of August2024 | 857/JJM | 20/09/2024 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5792 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Grant The Remuneration of Lab Staff for Month of June- 2024 | 749/JJM | 29/08/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5793 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Festival Bonus For The Lab Personnel | 1033/JJM | 25/10/2024 | 0 | SHASTRI SMRITI SANGHA | 0.18 | 0 | 0 | 0
5794 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Grant The Remuneration of Lab Staff For The Month Of September-2024 | 1045/JJM | 30/10/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5795 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Monthly remuneration for the month of October 2024 | 1087/JJM | 29/11/2024 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5796 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Salary Bill for the month of October-2024 | 1088/JJM | 29/11/2024 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5797 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Grant the Remuneration of lab staff for the month of April-2024. | 369/JJM | 21/06/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5798 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Monthly Remuneration Of Lab Personnel For The Month of November-2024 | 1176/JJM | 17/12/2024 | 0 | AIKYATAN DEVELOPMENT SOCIETY | 0.45 | 0 | 0 | 0
5799 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Grant the remuneration of lab staff for the month of July 2024 | 757/JJM | 30/08/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5800 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Salary payment for the month of March'2024. | 293/JJM | 29/05/2024 | 0 | SHASTRI SMRITI SANGHA | 0.45 | 0 | 0 | 0
5801 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Grant the remuneration of lab staff for the month of August-2024 | 856/JJM | 20/09/2024 | 0 | DR CHATTERJEES VILLAGE WELFARE SOCIETY | 0.45 | 0 | 0 | 0
5802 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work order for Supply & Delivery of Chemicals, reagents and consumables for 14(Fourteen) laboratories under Burdwan Division, P.H.E. Dte. [For s (six) Months] | 1825/BWD | 30/06/2025 | 30 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 19.69 | 0 | 0 | 0
5803 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Supply of Residual Chlorine Kit and engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant and Sampling Assistant) including maintenance in 1 No. Sub District Laboratory within Durgapur Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period 01.08.2025 to 31.08.2025 i.e. 1 (one) Month] | 2206/BWD | 01/08/2025 | 31 | DULAL MAJUMDER | 0.8 | 0 | 0 | 0
5804 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Arrear salary (From January'23 to August'23) for the laboratory personnel (Bacteriologist, Laboratory Assistant) of Bonnabagram Subdivision laboratory under Durgapur Division PHE Dte. | 899/DSD | 13/12/2023 | 15 | CLIFFORD FACILITY SERVICES PVT.LTD. | 0.66 | 0.66 | 100 | 100
5805 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | SupervisionandextendsupporttoNABLrecognizedWaterQualityTestingBlocklevelLaboratoryunderTheExecutiveEngineer,BurdwanDivision,PublicHealthEngineeringDirectorate,GovernmentofWestBengalbyassigningteamofcompetentresourcepersonnelwhowillbeengagedforcompletesupervisionforretainingNABLrecognitionandcompilationofpreparatoryup-to-datedocumentation,Calibrationforon-sitesurveillancebyNABL(asperNABL139)foraperiodofonemonthfromthedateofcommencement.(NameofSDL: Sankari Sub District Water Testing Laboratory under Burdwan Sadar Sub Division.) | 3059/BSD | 29/12/2023 | 45 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.9 | 0.9 | 100 | 100
5806 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | SupervisionandextendsupporttoNABLrecognizedWaterQualityTestingBlocklevelLaboratoryunderTheExecutiveEngineer,BurdwanDivision,PublicHealthEngineeringDirectorate,GovernmentofWestBengalbyassigningteamofcompetentresourcepersonnelwhowillbeengagedforcompletesupervisionforretainingNABLrecognitionandcompilationofpreparatoryup-to-datedocumentation,Calibrationforon-sitesurveillancebyNABL(asperNABL139)foraperiodofonemonthfromthedateofcommencement.(NameofSDL:Sehera Sub District Water Testing Laboratory under Burdwan Sadar Sub Division | 3060/BSD | 29/12/2023 | 45 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 0.51 | 0.51 | 100 | 100
5807 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work order for Engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant in 1 No. Ketugram Sub District Water Testing Laboratory within Katwa sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For 01.01.2025 to 31.01.2025] [Sl No -01] | 1812/KTS | 31/12/2024 | 31 | JAGADHATRI CONSTRUCTION AND BUILDERS | 0.59 | 0.59 | 100 | 100
5808 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 3 Nos Water Testing Laboratories under Burdwan Division, PHE Dte. [Period: For One Month (01.07.24 to 31.07.24)] | 374/AE/HQ | 01/07/2024 | 31 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
5809 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant in 1 No. Ketugram Sub District Water Testing Laboratory within Katwa sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For 01 Months] | 1660/KTS | 26/11/2024 | 30 | JAGADHATRI CONSTRUCTION AND BUILDERS | 0.59 | 0.59 | 100 | 100
5810 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Sampling Assistant) in Bananabagram Sub District Laboratory within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period for 01.06.2024 to 31.07.2024]. | 303/AE/HQ | 31/05/2024 | 61 | DULAL MAJUMDER | 0.25 | 0.25 | 100 | 100
5811 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Salary bill (from January 2024 to February 2024) for the laboratory personnel (Bacteriologist, Laboratory Assistant) of Bonnabagrum Sub-Division laboratory under Durgapur Sub-Division, P.H.E. DTE. | 994/DSD | 29/12/2023 | 65 | CLIFFORD FACILITY SERVICES PVT.LTD. | 0.63 | 0.63 | 100 | 100
5812 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Supply & Delivery of Chemicals, reagents and consumables for 14(Fourteen) laboratories under Burdwan Division, P.H.E. Dte. | 3712/BWD | 28/10/2024 | 30 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 39.74 | 39.74 | 100 | 100
5813 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 2 Nos. Sub District Laboratories within Burdwan Sadar Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.06.2024 to 31.07.2024] | 1981/BWD | 28/05/2024 | 61 | DULAL MAJUMDER | 1.98 | 1.98 | 100 | 100
5814 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Supply of Residual Chlorine Kit and engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant and Sampling Assistant) including maintenance in 3 Nos. Sub District Laboratories within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For Twelve Months] i.e. period from 01.08.2024 to 31.07.2025. | 2961/BWD | 31/07/2024 | 365 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 29.46 | 14.83 | 50.4 | 50
5815 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Supply of Residual Chlorine Kit and engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant and Sampling Assistant) including maintenance in 1 No. Sub District Laboratory within Durgapur sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For Twelve Months] i.e. period from 01.08.2024 to 31.07.2025. | 2963/BWD | 31/07/2024 | 365 | DULAL MAJUMDER | 10.49 | 10.49 | 100 | 75
5816 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Supply of Residual Chlorine Kit and engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant and Sampling Assistant) including maintenance in 4 Nos. Sub District Laboratories within Kalna Sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For Twelve Months] i.e. period from 01.08.2024 to 31.07.2025. | 2964/BWD | 31/07/2024 | 365 | DULAL MAJUMDER | 40.12 | 40.12 | 100 | 2
5817 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of Laboratory personnel (Chemist/Bacteriologist and Lab Assistant) including maintenance in 3 Nos. Sub District Laboratories within Headquarters under Burdwan Division, PHE Dte., Purba Bardhaman. [Period from 01.06.2024 to 31.07.2024] | 1980/BWD | 29/05/2024 | 61 | DULAL MAJUMDER | 3.56 | 3.56 | 100 | 100
5818 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Payment of festival bonus for 6 (six) nos Laboratory Staff of Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman. | 403/RWS | 12/12/2024 | 3 | ALAKA GHOSH | 0.47 | 0.47 | 100 | 100
5819 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of laboratory personnels i.e. Chemist (One Person), Additional Chemist (One person), Bacteriologist (One Person), Laboratory Assistant (One Person), Sampling Assistant (One Person) and Computer Operator/Data Entry Operator (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman. [Period for 6 (Six) Months i.e. 01.12.2024 to 31.05.2025] | 4167-A/BWD | 29/11/2024 | 181 | ALAKA GHOSH | 7.67 | 7.67 | 100 | 100
5820 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work for Engagement of 4 Nos Laboratory personnel (Analyst) at 4 Nos Water Testing Laboratories under Burdwan Division, PHE Dte [Period:One Month (01.07.24 to 31.07.24)] | 373/AE/HQ | 01/07/2024 | 31 | DULAL MAJUMDER | 0.87 | 0.87 | 100 | 100
5821 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation Work Order for Engagement of 1 No. Laboratory Assistant at Bonnabagram Water Testing Laboratories under Burdwan Division, PHE Dte [Period: For Four Months (01.07.24 to 31.07.24)] | 375/AE/HQ | 01/07/2024 | 31 | DULAL MAJUMDER | 0.16 | 0.16 | 100 | 100
5822 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant in 1 No. Ketugram Sub District Water Testing Laboratory within Katwa sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For 01.03.2025 to 31.07.2025] (Sl No-01) | 318/KTS | 28/02/2025 | 153 | JAGADHATRI CONSTRUCTION AND BUILDERS | 2.94 | 5.1 | 100 | 100
5823 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work Order for Engagement of Laboratory personnel (Chemist/Bacteriologist/ Lab Assistant in 1 No. Ketugram Sub District Water Testing Laboratory within Katwa sub Division under Burdwan Division, PHE Dte., Purba Bardhaman. [Period For 01.02.2025 to 28.02.2025] [Sl No -1] | 147/KTS | 30/01/2025 | 29 | JAGADHATRI CONSTRUCTION AND BUILDERS | 0.59 | 0.59 | 100 | 100
5824 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Supply, fitting, fixing of different computer spare parts of District Lab (1no.), Sub-Dist. Lab (11Nos.) (Barshul SDWTL, Satgachia SDWTL, Monteswar SDWTL, Sankari SDWTL, Anukhal SDWTL, Saktigarh SDWTL, Parulia SDWTL, Ganganandapur SDWTL, Sehera SDWTL, Bonnobogram SDWTL, Ketugram SDWTL) and NGO Lab (2Nos.) (Shastri Smriti Sangha & Aikyatan Development Society) under Burdwan Division, PHE. Dte. | 167/AE/HQ | 31/01/2025 | 30 | COMPUTER MEDIA | 0.94 | 0.94 | 100 | 100
5825 | PURBA BARDHAMAN | Burdwan Division | Operational charges of PHED & NGO Managed Laboratories related to Water Quality Monitoring & Surveillance under Jal Jeevan Mission , SM/19071 | Support-WQMSP | Continuation work order for Engagement of laboratory personnels i.e. Chemist (One Person), Additional Chemist (One person), Bacteriologist (One Person), Laboratory Assistant (One Person), Sampling Assistant (One Person) and Computer Operator/Data Entry Operator (One Person) for Burdwan District Laboratory under Burdwan Division P.H.E Dte. at PHE Complex, Nababhat, Purba Bardhaman. [Period for 3 (Three) Months i.e. 01.06.2025 to 31.08.2025] | 1556/BWD | 30/05/2025 | 92 | ALAKA GHOSH | 3.83 | 3.83 | 100 | 100
5826 | PURBA BARDHAMAN | Burdwan Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission , SM/19072 | Support-WQMSP | Carriage of FTK Box to different BMOH office under Burdwan Division, PHE. Dte. | 308/AE/HQ | 10/06/2024 | 10 | KHUSI BHAKAT | 0.29 | 0.29 | 100 | 100
5827 | PURBA BARDHAMAN | Burdwan Division | Drinking water sample collection & testing through Field Test Kits (FTKs Phase-II) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme under Jal Jeevan Mission , SM/19072 | Support-WQMSP | Uploading charges of all collected & tested data management to State WQ Dashboard using FTK/H2S vials for FHTCs in Burdwan district related to Water Quality Monitoring & Surveillance Activities under Jal Jeevan Mission. | 353/AE/HQ | 10/03/2025 | 30 | ALAKA GHOSH | 4.65 | 0 | 0 | 100
5828 | PURBA BARDHAMAN | Burdwan Division | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR THE DIFFERENT SUB DIVISION OFFICES AND BURDWAN DIVISION OFFICE PHE Dte , SM/16459 | Support-MIS | Procurement of materials from GEM (Invoice No.-GEM-29241467, dt.-20/03/2023, GEM-29240808, dt.-20/03/2023, GEM-28710492, dt.-11/03/2023) | 250/JJM | 14/06/2023 | 0 | M/S S.S. INFOTECH | 0.46 | 0 | 0 | 0
5829 | PURBA BARDHAMAN | Burdwan Division | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR THE DIFFERENT SUB DIVISION OFFICES AND BURDWAN DIVISION OFFICE PHE Dte , SM/16459 | Support-MIS | Supply of 02 Nos. HP Intel Core i5 windows 10 professional desktop computer.[GEM Invoice No.-GEM-28789462, DT.-13/03/2023] | 190/JJM | 31/05/2023 | 0 | M/S S.S. INFOTECH | 1.3 | 0 | 0 | 0
5830 | PURBA BARDHAMAN | Burdwan Division | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR THE DIFFERENT SUB DIVISION OFFICES AND BURDWAN DIVISION OFFICE PHE Dte , SM/16459 | Support-MIS | Supply of tonner NPG-51 for Canon Photocopier Machine. | 262/JJM | 15/06/2023 | 0 | ELECTRO SERVICES PVT LTD. | 0.06 | 0 | 0 | 0
5831 | PURBA BARDHAMAN | Burdwan Division | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR THE DIFFERENT SUB DIVISION OFFICES AND BURDWAN DIVISION OFFICE PHE Dte , SM/16459 | Support-MIS | Procurement of materials from GEM (HP Intel Core i3 windows 11 Professional) GEM Invoice No.-GEM-30241483, dt.-24/04/2023 | 247/JJM | 14/06/2023 | 0 | EASY DAY ENTERPRISE | 4.47 | 0 | 0 | 0
5832 | PURBA BARDHAMAN | Burdwan Division | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR THE DIFFERENT SUB DIVISION OFFICES AND BURDWAN DIVISION OFFICE PHE Dte , SM/16459 | Support-MIS | Procurement of materials from GEM (Canon Multifunction Machine) GEM Invoice No.-GEM-30301834, DT.-27/04/2023 | 248/JJM | 14/06/2023 | 0 | IONET | 3.75 | 0 | 0 | 0
5833 | PURBA BARDHAMAN | Burdwan Division | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR THE DIFFERENT SUB DIVISION OFFICES AND BURDWAN DIVISION OFFICE PHE Dte , SM/16459 | Support-MIS | Supply & delivery of computer monitor with necessary items at Durgapur (Burdwan North) Sub-Division and Headquarters, Burdwan Divn. under Burdwan Division, P.H.E. Dte. at PHE complex, Nababhat, Fagupur, Purba bardhaman-713104 | 147/AE/HQ | 04/03/2024 | 15 | HAZRA COMPUTER | 1 | 1 | 100 | 100
5834 | PURBA BARDHAMAN | Burdwan Division | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR THE DIFFERENT SUB DIVISION OFFICES AND BURDWAN DIVISION OFFICE PHE Dte , SM/16459 | Support-MIS | Supply, delivery & Installation of CCTV Camera at Burdwan Division P.H.E. Dte. | 149/AE/HQ | 04/03/2024 | 15 | HAZRA COMPUTER | 1 | 1 | 100 | 100
5835 | PURBA BARDHAMAN | Burdwan Division | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR THE DIFFERENT SUB DIVISION OFFICES AND BURDWAN DIVISION OFFICE PHE Dte , SM/16459 | Support-MIS | Supply & delivery of computer monitor with necessary items at Accounts Section under Burdwan Division, P.H.E. Dte. at PHE complex, Nababhat, Fagupur, Purba bardhaman-713104 | 148/AE/HQ | 04/03/2024 | 15 | HAZRA COMPUTER | 1 | 1 | 100 | 100
5836 | PURBA BARDHAMAN | Burdwan Division | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR THE DIFFERENT SUB DIVISION OFFICES AND BURDWAN DIVISION OFFICE PHE Dte , SM/16459 | Support-MIS | Supply & delivery of computer peripheral items at Burdwan Division P.H.E. Dte. | 150/AE/HQ | 04/03/2024 | 15 | HAZRA COMPUTER | 0.99 | 0.99 | 100 | 100
5837 | PURBA BARDHAMAN | Burdwan Division | PROCUREMENT OF COMPUTER AND PERIPHERALS FOR THE DIFFERENT SUB DIVISION OFFICES AND BURDWAN DIVISION OFFICE PHE Dte , SM/16459 | Support-MIS | Procurement of computer peripheral through GEM (HP Desktop & HP Monitor)[08 Nos.] and HP Laserjet Printer [02 Nos.] | 1921/JJM | 30/03/2024 | 0 | M/S S.S. INFOTECH | 5.25 | 0 | 0 | 0
5838 | PURBA BARDHAMAN | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. , SM/09241 | Support-WQMSP | Sanction order for deposit of Final assessment fee for NABL Accreditation of Burdwan District Laboratory under Burdwan Division, PHE Dte. | 877/BSD | 24/05/2022 | 92 | ALAKA GHOSH | 0.25 | 0 | 0 | 0
5839 | PURBA BARDHAMAN | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. , SM/09241 | Support-WQMSP | Sanction order for deposit of annual accreditation fee for NABL Accreditation of Burdwan District Laboratory under Burdwan Division, PHE Dte. | 1005/BSD | 17/06/2022 | 92 | ALAKA GHOSH | 0.28 | 0 | 0 | 0
5840 | PURBA BARDHAMAN | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. , SM/09241 | Support-WQMSP | Supply & Delivery of Chemicals, reagents and consumables at District Laboratory and 8 (Eight) Sub-District laboratories for NABL accreditation under Burdwan Division, P.H.E. Dte._Group : A | 290/AE/HQ | 17/05/2022 | 7 | LAB SOLUTION | 4.23 | 4.23 | 100 | 0
5841 | PURBA BARDHAMAN | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. , SM/09241 | Support-WQMSP | Supply & installation of approved quality Curtain with fixing of other allied works for NABL recognition of District Laboratory, Nababhat PHE Complex under Burdwan Divn., PHE. Dte. [Group : E] | 160/AE/HQ | 17/03/2022 | 10 | BHARAT CONSTRUCTION | 0.79 | 0.79 | 100 | 0
5842 | PURBA BARDHAMAN | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. , SM/09241 | Support-WQMSP | Procurement of Equipment's, Glassware and Chemicals required for NABL accreditation of the District Laboratory at Nababhat under Burdwan Division, PHE Dte._2nd Call. | 6769/BWD | 03/12/2021 | 20 | LAB SOLUTION | 9.15 | 9.15 | 100 | 0
5843 | PURBA BARDHAMAN | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. , SM/09241 | Support-WQMSP | Calibration of Equipment/Glassware for Burdwan District Water Testing laboratory under Burdwan Division, PHE Dte. (Part-A) | 1622/BSD | 16/09/2022 | 3 | MEASURE & PRECISION ENGINEERS | 0.15 | 0 | 0 | 100
5844 | PURBA BARDHAMAN | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. , SM/09241 | Support-WQMSP | Calibration of Equipment/Glassware for Burdwan District Water Testing laboratory under Burdwan Division,PHE Dte. (Part-B) | 1623/BSD | 16/09/2022 | 3 | MEASURE & PRECISION ENGINEERS | 0.12 | 0 | 0 | 100
5845 | PURBA BARDHAMAN | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. , SM/09241 | Support-WQMSP | Providing NABL related expenses for renewal audit of Burdwan District Water testing Laboratory under Burdwan Division, PHE Dte. | 145/RWS | 18/04/2024 | 7 | BHARATI CHEMICAL AND SCIENTIFIC WORKS | 1.28 | 1.28 | 100 | 100
5846 | PURBA BARDHAMAN | Burdwan Division | Procurement of equipments, glassware and chemicals required for NABL Accreditation of the District Laboratory, Nababhat under Burdwan Division. , SM/09241 | Support-WQMSP | Hire charges of 62.5 KVA Diesel Generator set for District Laboratory NABL Audit purpose including engagement one operator Technician and Diesel (8lit/hour) and all other incidental charges. | 690/JJM | 14/08/2024 | 0 | KHUSI BHAKAT | 0.08 | 0 | 0 | 0
5847 | PURBA BARDHAMAN | Burdwan Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. , SM/08993 | Support-WQMSP | Transfer of fund for Field Test Kit (FTK) programme to CMOH, Purba Bardhaman. | 392/FTK/22-23 | 05/08/2022 | 0 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 20 | 0 | 0 | 0
5848 | PURBA BARDHAMAN | Burdwan Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. , SM/08993 | Support-WQMSP | Transfer of fund for Field Test Kit (FTK) programme to CMOH, Purba Bardhaman. |  | 01/08/2022 | 0 | DISTRICT HEALTH & FAMILY WELFARE SAMITY | 25.8 | 0 | 0 | 0
5849 | PURBA BARDHAMAN | Burdwan Division | Drinking water sample collection & testing through Filed Test Kits (FTKs) & uploading charges for the same related to Water Quality Monitoring & Surveillance Programme. , SM/08993 | Support-WQMSP | Supply and delivery of portable multi-parameter water quality testing device including training on operation of the device in addition to online entry, management, analysis and reporting of water quality test results in State Water Quality Dashboard and IMIS both for monitoring water safety status of rural drinking water sources of 138 Nos. Gram Panchayats in Purba Bardhaman District of West Bengal under PHE Department. ........ [Excluding Sl. No. 03 in the B.O.Q.] | 119/BWD | 07/01/2022 | 60 | SUNANDA ENVIROMENTAL INTERNATIONAL PVT LTD. | 20.46 | 6.57 | 75.27 | 0
Total | [9 empty] | 518500.42 | 103264.97 | 19.92